## Slide 1
Construction Milestones
IPWG June 26, 2018 Draft for Discussion Only

## Slide 2: Current SIR Timeline
180 Business Days from receipt of CESIR to full payment for system modifications
Nine month window to start construction
Twelve months to “final acceptance” or possible removal from queue

## Slide 3: April 2018 SIR Timeline
210 Business Days from receipt of CESIR to full payment
Equals over ten months (42 weeks) to start construction
April 2018 Order: schedule work to achieve interconnection within the time frame allowed by the SIR
SIR allows twelve months from contract to “final acceptance”

## Slide 4: Slow Downs in the Queue
Problem: projects progress at different rates
Utilities may not be able to deploy resources efficiently
Delay creates uncertainties for projects attempting to move ahead
Would specific construction phase milestones help?

## Slide 5: Straw Proposal
Require project to confirm that it has permit to construct by 210 Business Days after receipt of CESIR (75% payment date)
If no permit, utility cancels project and returns unspent deposit funds; project may re-apply
Allow utility to revise its work schedules and change in-service dates for projects that start construction but miss important Appendix K milestones

## Slide 6: Possible Appendix K Milestones
Notice to proceed with procurement
Submission of final design
Mechanical completion
Others?