## Slide 1: Interconnection Queue Management Proposal
DPS & NYSERDA Ombudsman Meeting 6/29/16

## Slide 2: Current Interconnection Queue Issues
Significant increase in large scale system applications in late 2015 and early 2016
Increase primarily driven by CDG order and floating of the net metering cap
Based on the SIR requirements when these applications were filed there is no requirements for developers to advance their projects or be removed from the queue
As a result projects that may want to move forward cannot
In order to resolve this and get projects constructed a queue management modifications need to be put in place
Implementation of changes will require broad consensus and additional details
Implementation will likely require Commission approval including waiver on timelines and requirements that are different than what is included in the old and revised versions of the SIR
Proposal has been developed by JU Ombudsman group with input from PSC and NYSERDA Ombudsman

## Slide 3: Initial Requirements
Complete initial steps to clear the queue
  Reduce inventories using existing provisions such as the 12 month review
  Meet with developers to review circuit-level information and identify applications they are willing to voluntarily withdraw.
  Much of this work is already underway with some developers more willing to cooperate than others
These steps would be completed prior to the initiation of the revised protocol that follows

## Slide 4: Queue Management Proposal
Apply new SIR timeline guidelines for CESIR and construction decision to all pre-April 29 applications above (XXX)kW
  Would not apply new pre-application process or technical screens
    follows prior SIR process except for items below
  Exact timeline or required payments at every part of the process which if not met by developer would result in automatic removal from the queue
  Developer required to submit demonstration of site control within 10 business days of start date for this revised protocol

## Slide 5: Process Implementation for pre-April 29 Applications
Complete initial requirements and receive site control verification (see slide 3)
Within 30 business days the utility will develop an updated queue
Utility will identify opportunities for clustering for projects from same developer on same circuit
  No queue jumping would be allowed
  Protocol on how cluster study would be performed would be established in advance of study initiation
Based on the remaining applications that desire to go through CESIR the utility will develop a CESIR study schedule that will be shared with the developers
  Utility may consider geographic location or number of applications in developing schedule

## Slide 6: Process Implementation for pre-April 29 Applications
Developers will be required to make full CESIR payment within 10 business days of the scheduled start date of the CESIR
Projects for which CESIR payment has not been received prior to that date would be removed from the queue
CESIR results will be provided to the developer as the studies are completed
Developers will have 30 business days to make full payment for construction
Projects selecting to move forward to construction will be provided a construction schedule within 30 business days of their payment being received
Process continues until all pre- April 29 applications have moved through this protocol

## Slide 7: Process Implementation post-April 29 Applications
Applications would be added to the updated Interconnection queue
Applications would progress through the new pre-application process
Pre-application process would assume that all other applications in front of it will go into service
If the pre-application process is completed project can move to the full Application process and the Preliminary/ Supplemental Screening Analysis and the Develop Cost Estimate for CESIR process Step

## Slide 8: Process Implementation post-April 29 Applications
If the application passes all technical screens it will continue through the process to contract
  Construction timeline would be provided to the developer
If the application does not pass all technical screens developer will have the option to (as per Step 4)
  Proceed to Preliminary Results meeting
  Proceed to Supplemental Review
  Proceed to full CESIR
  Withdraw application
Projects that select a Supplemental review and/or full CESIR will have a schedule provided by the utility within 20 business days based on the queue of Supplemental review/CESIR studies

## Slide 9: Process Implementation post-April 29 Applications
Projects that desire to continue to move forward are required to pay for the Supplemental Review and/or CESIR costs within 10 business days of the anticipated start date of the review/study
Projects for which payment has not been received prior to start of the study would be removed from the queue
Status updates on the CESIR schedules to be provided to developers