## SIR Construction Timelines
Upgrade status | Status | Cost estimate | Initial payment | IX Contract | Construction schedule | Complete design package | Final payment | 25% Payment Breakdown
No upgrades required | Current | NA | NA |  | NA |  | NA | NA
| Proposed | NA | NA |  | NA |  | NA | NA
Upgrades/Interconnection facilities identified in preliminary or supplemental review | Current | 15 business days from results meeting | 15 business days + 15 business days (extension) to "accept upgrade costs" |  |  |  |  | OPTION 1 (default): Authorizes design/engineering/planning. OPTION 2 (by developer request) Utility takes no action, all funds remain until developer requests to move forward or pays 100% / Construction schedule due 30 business days from date of request to move forward. OPTION 1 & 2: Unspent funds are fully refundable.
| Proposed | 15 business days from results meeting | 25% payment 30 business days from receipt of cost estimate | 10 business days from receipt of 25% | 15 business days from 25% payment |  | TBD
CESIR required | Current |  | 25% payment 60 business days from receipt of complete CESIR |  | 30 days from 25% payment (currently only included in Jan 25 Queue Mgmt Order) |  | 120 business days from receipt of complete CESIR
| Proposed |  | 25% payment 60 business days from receipt of complete CESIR | 10 business days from receipt of 25% | 30 days from 25% payment | OPTION 1: 30 business days from 25% payment. OPTION 2: 30 business days from request to move forward | 120 business days from receipt of complete CESIR
Note on C4: Valessa Souter-Kline: What is the process here?
Note on E5: Valessa Souter-Kline: Ballpark, appropriate timeframe TBD
Note on F5: Valessa Souter-Kline: Or from IX contract?
Note on G7: Valessa Souter-Kline: Need clarification prior to establishing this step. Not clear what this step encompasses.

## Key
Color key
Current
Proposed same
Proposed new