## Slide 1
Aggregating Projects up to 5 MW
IPWG 11/14/2017 Draft

## Slide 2: SIR Implementation for Larger Projects
No process modifications have been identified so far
Transitional rules for combining existing projects are needed
Possible opportunity to define “material change” requiring re-study going forward

## Slide 3: Rules for Aggregating Projects
  Qualifications for combining project applications
    Same PCC
    Applications must be sequential on both the Circuit and Substation Bus
    No projects from NYISO or Non-SIR Utility Queues between projects that propose to aggregate
    Adjacent or combined parcels
    One compensation category/one meter

## Slide 4: Timing of Requests
Transition rules apply to applications in the queue as of Commission order on compensation
Applications in technical review: submit request and pay for additional study
After 25% downpayment: same approach
After first project in queue pays 75% balance: submit request, adjust project schedule, suspend due date for second project balance payment; pay for re-study
If combined project “pencils out,” pay any additional funds due for construction costs and proceed to construct
    If not, construct original proposed project or withdraw

## Slide 5: Material Changes
SIR already govern: “any modifications affecting the interface at the PCC to existing DG facilities … that have been interconnected to the utility distribution system(.)”
Study process already allows for some changes; for example, after the preliminary analysis
What changes require a new application/loss of queue position?