## Backup-Additions (hidden)
BUDGET # | DESCRIPTION | WO # | SOURCE CD | JUL | AUG | SEP | OCT | NOV | DEC
D000FX | URD BLANKET |  |  | -1.2 | 0 | 0 | -5.3 | 0 | -1.8
D003FX | FIRST INSTALL TRANSFORMERS - OVERHE | 10-0683 | CL | 175.9 | 186 | 256.1 | 270.4 | 310.4 | 277.6
D005FX | OVERHEAD POLES TOWERS AND FIXTURES | 10-0743 | CL | 311.5 | 350 | 440.6 | 243.4 | 384.1 | 601.5
D006FX | OVERHEAD CONDUCTOR BLANKET | 10-0753 | CL | 302.7 | 270.8 | 232.8 | 293.9 | 269.3 | 355.6
D007FX | OVERHEAD STREETLIGHTING BLANKET | 10-0773 | CL | 7.2 | 8.8 | 10.8 | 4.3 | 8.7 | 8.7
D008FX | OVERHEAD SERVICES BLANKET | 10-0793 | CL | 44.8 | 43.5 | 32.2 | 29.3 | 41.5 | 25.2
D009FX | O/H BLANKET - G.O.A.B. INSTALLATION | 10-0733 | CL | 15.3 | 15.1 | 51.4 | 105.4 | 53 | 21.5
D010FP | 2008 TRANSFORMER PURCHASE BLANKET - OH | 10-0128 | CL | 162.3 | 293.9 | 451.7 | 405.6 | 297 | 384
D010FP | 2008 TRANSFORMER PURCHASE BLANKET - UG | 50-0128 | CL | 268.4 | 305.4 | 189.9 | 240.6 | 271.5 | 367.4
D011FR | 2008 OVERHEAD LINE DEPT CAPITAL TOO | 10-2109 | CL | 27.4 | 0 | 0 | 78.7 | 0 | 2.2
D012FM | 2008 TRANSMISSION POLE REPLACEMENT | 10-2096 | CL | 0 | 212.3 | 0 | 0 | 0 | 0
D107WT | ELECTRIC METER PURCHASE BLANKET | 10-0777 | CL | 63.3 | 0 | 20.3 | 0 | 95.3 | 96.7
D144VF | TRANSFORMER INTERCOMPANY SALES BLAN | 10-0100 | CL | -22.1 | -1816 | 0 | 0 | 0 | -269.4
D144VW | TRANSFORMER RETIREMENT AND METER IN | 10-0101 | CL | 0 | -92.5 | 0 | 0 | 0 | 0
D171FR | 2008 CABLE REBUILD BLANKET | 53-2322 | CL | 44.3 | 0 | 0 | 118.1 | 25.9 | 130
D172FT | UNDERGROUND CABLE INJECTION BLANKET | 50-0696 | CL | 114.7 | 72.7 | 87 | 27.6 | 0.8 | 8.8
D194WT | ELECTRIC METER FIRST INSTALL BLANKE | 10-0888 | CL | 54.7 | 50.8 | 124.9 | 101.4 | 108.8 | 41.8
D203CR | SMART GRID DEVICES FOR CAPACITOR CO | 10-2152 | CL | 0 | 0 | 68.4 | 0 | 0 | 0
D240CP | 2007 DISTRIBUTION AUTOMATION BLANKE | 10-1807 | CL | 29.4 | 0 | 0 | 32.2 | 0 | 0
D240CR | 2008 DISTRIBUTION AUTOMATION BLANKE | 10-2108 | CL | 50.9 | 0 | 523.2 | 1.9 | 0 | 0
D290GP | 2007 SALE OF SCRAP | 14-1886 | CL | 0 | 0 | 0 | 0 | -88 | 0
D290GR | 2008 SALE OF SCRAP | 14-2207 | CL | 7.7 | 8.9 | 17.9 | 7.7 | 10.5 | 36.3
D291FP | 2007 PCB OIL TESTING AND DISPOSAL B | 14-1850 | CL | 1.3 | 0 | 0 | 0 | 0 | 0
D400WR | 2008 ELEC METER DEPARTMENT MISCELLA | 10-2190 | CL | 0 | 0 | 0 | 0 | 0 | 74.3
D439BM | 2006 BANK METERING UPGRADE BLANKET | 10-1438 | CL | -3.9 | 0 | 0 | 0 | 0 | 0
D550FX | UNDERGROUND TRENCHING BLANKET | 50-0616 | CL | -1.6 | 12.7 | -10.9 | 15.1 | 78.9 | 17.7
D551FX | UNDERGROUND CONDUIT BLANKET | 50-0626 | CL | 0 | 0 | 0 | 0 | 0 | 0.2
D552FX | UNDERGROUND BOX PADS BLANKET | 50-0636 | CL | 14.1 | 9.6 | 9.9 | 28.7 | 42.6 | 28.2
D553FX | UNDERGROUND PRIMARY CONDUCTOR BLANK | 50-0646 | CL | 38.1 | 141 | 96.1 | 84.4 | 138.3 | 189.1
D554FX | UNDERGROUND DEVICES BLANKET | 50-0656 | CL | 0 | 0 | 6.7 | -0.9 | 16.5 | 23.3
D555FX | UNDERGROUND STREET LIGHTING BLANKET | 50-0666 | CL | 10.2 | 3.2 | 16.7 | 2.6 | 6.1 | 14.8
D556FX | UNDERGROUND SECONDARY CONDUCTOR BLA | 50-0676 | CL | 5.3 | 6.6 | 7.5 | 17.1 | 10 | 6.9
D558FX | FIRST INSTALL TRANSFORMERS - UNDERG | 50-0686 | CL | 46.1 | 17.4 | 115.8 | 74.9 | 111.4 | 53.6
D559FX | UNDERGROUND CUSTOMER OWNED SERVICES | 50-0816 | CL | 41.9 | 57.7 | 29.7 | 34.4 | 45.7 | 73
D561FX | UNDERGROUND DEFECTIVE SERVICES - TA | 50-0826 | CL | 0 | 0 | 1 | 0.7 | 0 | 0
D563FX | UNDERGROUND CUSTOMER OWNED SERVICE | 50-0813 | CL | 11.7 | 28.1 | 16.6 | 39.4 | 39.2 | 21.4
D564FX | UNDERGROUND CUSTOMER SERVICE CREDIT | 50-0916 | CL | 2 | 0.1 | 0.2 | 0.7 | 0.9 | 0.4
D565FR | 2008 UNDERGROUND CAPITAL TOOLS BLAN | 50-2110 | CL | 72.6 | 0 | 0 | 0 | 0 | 23.4
D583FR | 2008 INCREMENTAL RELIABILITY - DEFE | 10-2259 | CL | 357.4 | 11.8 | 54.7 | 0 | 0 | 0
D660FX | UNDERGROUND COMPANY OWNED SERVICES | 50-0806 | CL | 1.9 | -0.8 | 0 | 1.8 | 0.6 | 0
T015ZR | 2008 SUBSTATION DEPT BLANKET | 10-2112 | CL | 0 | 0 | 0 | 0 | 108.8 | 46.2
T016ZR | 2008 BATTERY BANK REPLACEMENT BLANK | 10-2119 | CL | 0 | 0 | 16.6 | 0 | 0 | 0
T017ZR | 2008 RELAY DEPT CAPITAL PURCHASE BL | 10-2120 | CL | 0 | 0 | 29.8 | 8 | 0 | 0
T239CP | EMS HARDWARE EXPANSION SV & BG - 20 | 10-1817 | CL | 0 | 0 | 0 | 0 | 0 | 860.2
| Total Blankets |  |  | 2254.3 | 197.1 | 2897.6 | 2262.1 | 2387.8 | 3518.8
D102FX | REBUILD APPROX. 1900 FT - FERNDALE | 50-2298 | CL | 0 | 0 | 0 | 0 | 56 | 0
D103FD | RECONDUCTOR PENN AVE & JERSEY AVE I | 10-1513 | CL | 0 | 0 | 292.5 | 0 | 0 | 0
D105FX | WALLKILL INDUSTRIAL PARK - RYKOWSKI | 50-2316 | CL | 0 | 0 | 0 | 163.5 | 0 | 0
D112FX | 2008 CABLE REBUILD, 2100' BEAUMONT | 50-2332 | CL | 0 | 0 | 0 | 0 | 0 | 22.2
D117FX | URD HIDDEN CREEK SECTION 1, MONROE, | 50-2334 | CL | 0 | 0 | 0 | 0 | 0 | 72
D121BX | SPARE 34.5 TO 13.8KV | 10-2331 | CL | 0 | 0 | 0 | 125.8 | 0 | 2.9
D122CX | CONGERS SUBSTATION U/G CIRCUIT EXIT | 50-2367 | CL | 0 | 0 | 0 | 0 | 0 | 284.6
D125FX | BLAISDELL RD, CIRCUIT 54-8-13 CIRCU | 10-2369 | CL | 0 | 0 | 0 | 0 | 0 | 213.9
D128FX | BRADLEY CORPORATE PARK, WESTERN HIG | 50-2389 | CL | 0 | 0 | 0 | 0 | 89 | 0
D132FX | SCHUNEMUNK RD - WOODBURY, NY - LTS | 10-2393 | CL | 0 | 0 | 0 | 0 | 0 | 116.3
D201CB | 2008 PURCHASE PC HARDWARE DEVICES F | 10-2150 | CL | 0 | 0 | 0 | 0 | 209.2 | 0
D206FX | CONVERT CIRCUIT 9-2-48 TO 34KV | 10-1482 | CL | 0 | 0 | 20 | 0 | 0 | -4.1
D270FC | RECONDUCTOR RTE 302 TO BULLVILLE SU | 10-1716 | CL | 0 | 0 | -0.8 | 0 | 0 | 0
D284FX | WASHINGTON AVENUE RECONDUCTOR - NEW | 10-2236 | CL | 0 | 0 | 298.1 | 0 | 0.6 | 0
D319CA | WORK MANAGEMENT SYSTEM (WMS) WEB DE | 10-2158 | CL | 0 | 0 | 0 | 0 | 0 | 876.9
D337FX | SCHUTT ROAD / ROLLING MEADOWS ROAD | 10-1851 | CL | 0 | 0 | 7.2 | 0 | 0 | 0
D339FX | RECONDUCTOR LYBOLT,BRIMSTONE ROADS | 10-1973 | CL | 160.1 | 0 | 0 | 0 | 0 | 0
D343FX | ROUND HILL RD, DOUBLE CT - BLOOMING | 10-2074 | CL | 0 | 0 | 187.7 | 0 | 5.2 | 0
D362FE | SNAKE HILL RD - CRUSHER/STORMS RD D | 10-2242 | CL | 0 | 0 | 0 | 0 | 0 | 811.9
D362FG | INSTALL 6000' OF NEW CONDUCTOR - LA | 10-1855 | CL | 1.9 | 0 | 0 | 0 | 0 | 0
D363FB | LITTLE TOR RD TO PHILLIPS HILL RD D | 10-1856 | CL | 10.3 | 0.8 | 0 | 0 | 0 | 0
D387BD | REPLACE RELAYING FOR L-541 - BURNS | 10-2140 | CL | 0 | 0 | 0 | 0 | 0 | 193.9
D387BE | REPLACE RELAYING FOR LINE 541 - WES | 10-2141 | CL | 0 | 0 | 0 | 0 | 0 | 204.9
D402FX | 2007 U/G REBUILD - MINUTEMAN CIR, O | 50-1841 | CL | 0 | 0 | 0 | 0 | 3.7 | 0
D410FX | LAROE ROAD - PART 1 RECONSTRUCTION | 10-1983 | CL | 0 | 0 | 0 | 0 | 0 | 0
D413BX | REPLACE 6 STRUCTURES ON LINE 841/85 | 10-1985 | CL | 0 | 0 | 2 | 0 | 0 | 0
D424FX | NYCDEP WWT PLANT - UPGRADE LINE TO | 10-2035 | CL | 0 | 0.1 | 0 | 0 | 0 | 0
D462BX | REPLACE 69KV SWITCH FOR DISTRIBUTIO | 10-2104 | CL | 0 | 105.4 | 0 | 0 | 0 | 0
D546CX | NEW MAINLINE CROSSING OVER RT 17 AL | 50-1918 | CL | 0 | 0 | 122.9 | 0 | 0 | 127.6
D568FX | REBUILD PARLIMENT DR - NEW CITY - 0 | 50-1707 | CL | 0 | 18.6 | 0 | 0 | 0 | 0
D569FX | SMITH FARM SUBDIVISION, LITTLE TOR | 50-2065 | CL | 0 | 0 | 0 | 0 | 76.2 | 0
D570FX | TERRACE VIEW ESTATES, SUBDIVISION U | 50-2066 | CL | 14.8 | 0 | 0 | 0 | 250.9 | 0
D571FX | 2007 LTS SYSTEM IMPROVEMENT, SLEEPY | 10-2067 | CL | 0 | 0 | 98.6 | 0 | 0 | 0
D572BA | PURCHASE OF PROPERTY FOR NEW DEER P | 10-2076 | CL | 0 | 0 | 28.5 | 0 | 0 | 0
D573FA | RECONDUCTOR RTE 9W SPARKHILL TO PAL | 10-2206 | CL | 0 | 0 | 0 | 0 | 0 | 646.4
D574FX | BAKERTOWN ROAD SUB PHASE 1 - KIRYAS | 50-2111 | CL | 0 | 0 | 0 | 0 | 123.4 | 0
D577BX | REPLACEMENT OF TIE SWITCH T1-76-1 A | 10-2107 | CL | 0 | 0 | 0 | 0 | 58.2 | 0
D579FX | LIBERTY GREEN - WARWICK, NY | 50-2252 | CL | 0 | 0 | 115.2 | 0 | 0 | 0
D580FX | TUXEDO GOLF COURSE PUMPHOUSE, | 10-2253 | CL | 0 | 0 | 0 | 0 | 0 | 121.6
D581FX | ROUTE 306 CIRCUIT 44-4-13 UPGRADE & | 10-2254 | CL | 0 | 0 | 0 | 0 | 0 | 247
D586CX | WHISPERING HILLS VOLTAGE CONVERSION | 50-2266 | CL | 0 | 0 | 301.1 | 0 | 0 | 0
D587FX | URD WOODSIDE KNOLLS II - MIDDLETOWN | 50-2267 | CL | 0 | 0 | 0 | 0 | 54.5 | 0
D588FX | MEYERSON ROAD CONVERSION | 10-2268 | CL | 0 | 0 | 0 | 139.6 | 0 | 0
D591BX | SWINGING BRIDGE TRANSFORMER PAD REP | 10-2280 | CL | 0 | 0 | 23.5 | 0 | 0 | 0
D595CX | REPLACE CIRCUITS 21-13 & 21-14 - WE | 50-2284 | CL | 0 | 0 | 226.7 | 0 | 0 | 0
T120BA | LINE 11 69KV DOUBLE CIRCUIT UPGRADE | 10-1928 | CL | 474 | 0 | 0 | 0 | 0 | 375
T120BX | LINE 11/14 69KV DOUBLE CIRCUIT UPGR | 10-6583 | CL | 0 | 0 | -20.3 | 35.6 | 0 | 0
T173BA | INSTALL BANK 811 AND REMOVE BANK 21 | 10-1798 | CL | 0 | 52.8 | 0 | 0 | 0 | 0
T297BX | REPLACE UPS BATTERIES A&B AT SVOC | 10-1468 | CL | 0 | 64.8 | 0 | 0 | 0 | 0
T446ZX | REBUILD FOUR 345KV PK-4 COGENEL BRE | 10-1756 | CL | 0 | 0 | 496.6 | 8.9 | 0 | 0
T447BX | TRANSMISSION LINE 75 POLE REPLACEME | 10-1927 | CL | 0 | 0 | 0 | 0 | 0.8 | 0
T455BX | INSTALL RIP RAP FOR 2 STRUCTURES ON | 10-2020 | CL | 0 | 0 | 0 | 0 | 0 | 266.9
T457ZX | REPLACE WINDOW AC UNITS WITH SPLIT | 10-2046 | CL | 0 | 0 | 131.9 | 0 | 0 | 0
T465BX | REPLACEMENT OF 138KV OIL CIRCUIT BR | 10-2258 | CL | 0 | 66.4 | 0 | 0 | 0 | 0
T466BX | HILLBURN SUB BANK 317 SERVICE UPGRA | 10-2270 | CL | 0 | 0 | 102.4 | 0 | 0 | 0
T474BX | REPLACE BREAKER 12-2-2 @ MONGAUP DU | 10-2366 | CL | 0 | 190.9 | 0 | 0 | 0 | 6.9
T476BX | REPLACE STRUCTURE 90 LINES 551 AND | 10-2371 | CL | 0 | 0 | 0 | 0 | 0 | 308
| Total Projects Under $1M |  |  | 661.1 | 499.8 | 2433.8 | 473.4 | 927.7 | 4894.8
D115BA | PURCHASE OF PROPERTY FOR NEW POCATE | 10-2061 | CL | 0 | 0 | 836.7 | 0 | 0 | 0 | 836.7
D387BX | LITTLE TOR SUBSTATION - CONSTRUCTIO | 10-1075 | CL | 0 | 181.3 | 0 | 0 | 0 | 0 | 181.3
D151CX | REPLACEMENT OF OUTAGE MANAGEMENT SY | 10-7233 | CL | 1204.3 | 0 | 0 | 0 | 0 | 0 | 1204.3
D263BX | PURCHASE LAND FOR THE NEW WEST WARW | 10-2055 | CL | 0 | 0 | 0 | 0 | 0 | 1934.6 | 1934.6
D223CX | MONROE UNDERGROUND CIRCUIT EXITS | 50-1805 | CL | 0 | 0 | 852.5 | 0 | 1336 | 0 | 2188.5
D223BX | INSTALL A SECOND TRANSFORMER BANK - | 10-6914 | CL | 0 | 0 | 0 | 2507.9 | 0 | 0 | 2507.9
| Total Projects Over $1M |  |  | 1204.3 | 181.3 | 1689.2 | 2507.9 | 1336 | 1934.6

## Total T&D Plant Add Exhibit
Orange and Rockland Utilities, Inc.
Electric Rate Case - Annual Update
Electric Plant Additions
Rate Year 3
|  | Rate Year 3 | Rate Year 3
|  | Agreement | Actual | Variance
Project Description
| Blankets | 27634.8 | 21371.7 | 6263.1
| Regular Projects Under $1 Million | 4715.0386 | 15576.1 | -10861.0614
Regular Projects Over $1 Million
T120BA | Transmission Line 11 Upgrade Part 2 | 0 | 26.5 | -26.5
D223B/C | Monroe Substation Upgrade and UG Exits | 0 | 0 | 0
T127BA | Transmission Line 28 (77A) Ramapo to Sugarloaf | 0 | 0 | 0
T127BB | Ramapo 138kV Terminal | 0 | 4279.5 | -4279.5
T127BC/BX | Sugarloaf 138kV Substation and Transmission Reconfiguration | 0 | 11453.3 | -11453.3
D387B/C | Little Tor Substation, UG Exits and Transmission | 0 | 0 | 0
D374B/C | Snake Hill Road Substation, UG Exits, Transm OH Tap and Terminal Relays | 0 | 0 | 0
D167B/C | Port Jervis Substation Upgrade and UG Exits | 0 | 34.8 | -34.8
T167BD | Transmission Line 18 Upgrade | 0 | 0 | 0
T182BX | Spare 138 - 69kV 175MVA Transformer | 0 | 2093.5 | -2093.5
| Mirant | 0 | 0 | 0
T174BX | Transmission Line 31 Upgrade | 0 | 5934.9 | -5934.9
D115B/C | Pocatello Substation and UG Exits | 0 | 0 | 0
D253B/C | Hartley Road Substation and UG Exits | 0 | 0 | 0
D293B/C | Corporate Drive Substation, UG Exits and Transmission Tap | -995 | 27549.2 | -28544.2
D320BX | Spare 138X69 13.2kV 35MVA Bank | 0 | 1085.7 | -1085.7
D474B/C | Tappan Substation and UG Exits | 582 | 0 | 582
T126BX | Sterling Forest Line 26 Transmission Tap | 3728 | 0 | 3728
T179BX | Spare 345 - 138kV 400MVA Transformer | 4000 | 4156.9 | -156.9
T125BX | Transmission Line 24 and 25 Upgrade | 13931 | 0 | 13931
D258B/C | New Hempstead Substation Upgrade and UG Exits | 7982 | 0 | 7982
D263B/C | West Warwick Substation and UG Exits | 7045 | 0 | 7045
D134B/C/M | Smart Grid Projects (Distribution, Substation and Communication) | 0 | 0.3 | -0.3
D491B/C | Dean Substation | 0 | 2761.4 | -2761.4
D263BA | Transmission Line - Wisner to West Warwick | 4610 | 0 | 4610
T175BX | Transmission Lines 55 and 551 Upgrade | 1490 | 0 | 1490
D245B/C | Westtown Substation Upgrade and UG Exits | 0 | 0 | 0
D145BA | Transmission Line 6 Upgrade - Pocatello to Decker | 0 | 0 | 0
| Silver Lake Substation Upgrade | 0 | 0 | 0
|  | 42373 | 59376 | -17003
|  | 74722.8386 | 96323.8 | -21600.9614

## Backup-Expenditures (hidden)
BUDGET # | WO # | DESCRIPTION | SOURCE CD | JUL | AUG | SEP | OCT | NOV | DEC
D000FX | 51-2380 | URD PINE LAKE ESTATES, MASTEN LAKE | CC | 0 | -59.1 | 0 | 0 | 0 | 0
D000FX | 51-2466 | URD SUNRISE HILLS - SECTION A, MIDD | CC | 0 | 0 | 0 | 0 | 0 | -10.9
D000FX | 51-2455 | URD SKI SIDE VILLA, KATRINA CT, TUX | CC | 0 | 0 | 0 | 0 | -10.2 | 0
D000FX | 51-1757 | URD STABLES, NAVAJO TRAIL, SLOATSBU | CC | 0 | 0 | 0 | 0 | -1.8 | 0
D000FX | 51-2277 | URD ALBERT WISNER PUBLIC LIBRARY, W | CC | 0 | 0 | -0.1 | 0 | 0 | 0
D000FX | 51-2325 | URD HORIZONS AT WAWAYANDA-SECT 2, H | CC | 0 | 0 | 0 | 0 | -0.1 | 0
D000FX | 51-2381 | URD COUNTRY COMFORT HOMES CORP, MID | CC | 0 | 0 | 0 | -0.1 | 0 | 0
D000FX | 51-2277 | URD ALBERT WISNER PUBLIC LIBRARY, W | PR | 0 | 0 | 0.1 | 0 | 0 | 0
D000FX | 51-2325 | URD HORIZONS AT WAWAYANDA-SECT 2, H | PR | 0 | 0 | 0 | 0 | 0.1 | 0
D000FX | 51-2381 | URD COUNTRY COMFORT HOMES CORP, MID | PR | 0 | 0 | 0 | 0.1 | 0 | 0
D003FX | 10-0683 | FIRST INSTALL TRANSFORMERS - OVERHE | CC | 1 | 1.1 | 1.5 | 1.6 | 1.8 | 1.3
D003FX | 14-0683 | FIRST INSTALL TRANSFORMERS - OVERHE | AP | 0 | 0 | 0 | 0 | 0 | 57.3
D003FX | 10-0683 | FIRST INSTALL TRANSFORMERS - OVERHE | MS | 11.9 | 12.6 | 17.3 | 18.3 | 21 | 14.9
D003FX | 10-0683 | FIRST INSTALL TRANSFORMERS - OVERHE | PR | 32.1 | 34 | 46.8 | 49.4 | 56.7 | 40.2
D003FX | 10-0683 | FIRST INSTALL TRANSFORMERS - OVERHE | A3 | 49.6 | 52.4 | 72.1 | 76.1 | 87.4 | 62
D003FX | 10-0683 | FIRST INSTALL TRANSFORMERS - OVERHE | A4 | 81.3 | 85.9 | 118.3 | 125 | 143.5 | 101.8
D005FX | 10-0743 | OVERHEAD POLES TOWERS AND FIXTURES | CC | -83.1 | -25.2 | -9.6 | -59.9 | -3 | -3.1
D005FX | 10-0744 | POLE BUTT REMOVAL BLANKET - LAST OF | CC | 0 | 0 | 0 | 0 | -0.3 | 0
D005FX | 14-0744 | POLE BUTT REMOVAL BLANKET - LAST OF | CC | 0 | 0 | 0 | 0 | 0.3 | 0
D005FX | 14-0743 | OVERHEAD POLES TOWERS AND FIXTURES | AP | 6.4 | 0.3 | 0 | 0 | 0 | 2
D005FX | 14-0743 | OVERHEAD POLES TOWERS AND FIXTURES | PR | 11.3 | 11.6 | 7.2 | 9.3 | 7.9 | 4.4
D005FX | 14-0743 | OVERHEAD POLES TOWERS AND FIXTURES | A3 | 15.7 | 15.2 | 9.6 | 15 | 12.7 | 10.4
D005FX | 14-0743 | OVERHEAD POLES TOWERS AND FIXTURES | A4 | 25.8 | 25.1 | 15 | 24.1 | 19.6 | 13.9
D005FX | 10-0743 | OVERHEAD POLES TOWERS AND FIXTURES | AP | 23.5 | 24.3 | 17.7 | 42 | 38.9 | 23.5
D005FX | 10-0743 | OVERHEAD POLES TOWERS AND FIXTURES | MS | 48.8 | 47.1 | 49.6 | 34.1 | 41 | 27.7
D005FX | 10-0743 | OVERHEAD POLES TOWERS AND FIXTURES | PR | 49.7 | 50.9 | 72.7 | 31.2 | 48.9 | 44.1
D005FX | 10-0743 | OVERHEAD POLES TOWERS AND FIXTURES | A3 | 78.8 | 73 | 105.7 | 55.7 | 84.6 | 112
D005FX | 10-0743 | OVERHEAD POLES TOWERS AND FIXTURES | A4 | 134.7 | 127.6 | 172.8 | 92 | 133.3 | 366.5
D006FX | 10-0753 | OVERHEAD CONDUCTOR BLANKET | CC | -2.9 | -38.4 | -10.4 | -2.4 | 1.1 | 0.7
D006FX | 14-0753 | OVERHEAD CONDUCTOR BLANKET | CC | 0 | -1.4 | 0 | 0 | 0 | 0
D006FX | 14-0753 | OVERHEAD CONDUCTOR BLANKET | MS | 0 | -0.3 | 0 | 0 | 0 | -0.6
D006FX | 11-7808 | 2008 NON PCB CAPACITOR REPLACEMENT | MS | 0 | 0.4 | 0 | 0 | 0 | 0
D006FX | 14-7808 | 2008 NON PCB CAPACITOR REPLACEMENT | PR | 0.1 | 0.4 | 0 | 0 | 0 | 0
D006FX | 14-7808 | 2008 NON PCB CAPACITOR REPLACEMENT | A3 | 0.1 | 0.5 | 0 | 0 | 0 | 0
D006FX | 11-7808 | 2008 NON PCB CAPACITOR REPLACEMENT | PR | 0.2 | 0.8 | 0 | 0 | 0 | 0
D006FX | 14-7808 | 2008 NON PCB CAPACITOR REPLACEMENT | A4 | 0.2 | 0.9 | 0 | 0 | 0 | 0
D006FX | 14-0763 | OVERHEAD CAPACITORS BLANKET | PR | 0.8 | 0.2 | 0 | 0.2 | 0 | 0
D006FX | 11-7808 | 2008 NON PCB CAPACITOR REPLACEMENT | A3 | 0.2 | 1.1 | 0 | 0 | 0 | 0
D006FX | 14-0763 | OVERHEAD CAPACITORS BLANKET | A3 | 1.1 | 0.3 | 0 | 0.2 | 0 | 0
D006FX | 11-7808 | 2008 NON PCB CAPACITOR REPLACEMENT | A4 | 0.4 | 1.9 | 0 | 0 | 0 | 0
D006FX | 10-0763 | OVERHEAD CAPACITORS BLANKET | CC | 0.6 | 0.6 | 1 | 0.1 | 0 | 0
D006FX | 14-0763 | OVERHEAD CAPACITORS BLANKET | A4 | 1.8 | 0.5 | 0.1 | 0.4 | 0 | 0
D006FX | 10-0763 | OVERHEAD CAPACITORS BLANKET | PR | 0.3 | 1.2 | 1.2 | 3.1 | -0.9 | 0
D006FX | 10-0763 | OVERHEAD CAPACITORS BLANKET | A3 | 1.8 | 2.3 | 3.6 | 5.4 | -1.5 | 0
D006FX | 10-0763 | OVERHEAD CAPACITORS BLANKET | A4 | 3.9 | 5 | 7.7 | 8.8 | -2.3 | 0
D006FX | 10-0763 | OVERHEAD CAPACITORS BLANKET | MS | 7.6 | 7.4 | 12.7 | 1.9 | 0 | 0
D006FX | 14-0753 | OVERHEAD CONDUCTOR BLANKET | PR | 7.5 | 15.7 | 6.2 | 8.9 | 6.9 | 3
D006FX | 10-0753 | OVERHEAD CONDUCTOR BLANKET | AP | 0.7 | 3.8 | 2.5 | 12 | 8.6 | 38.1
D006FX | 14-0753 | OVERHEAD CONDUCTOR BLANKET | A3 | 10.3 | 20.5 | 8.2 | 14.2 | 11.1 | 7
D006FX | 14-0753 | OVERHEAD CONDUCTOR BLANKET | A4 | 17 | 33.9 | 12.8 | 22.9 | 17.2 | 9.2
D006FX | 10-0753 | OVERHEAD CONDUCTOR BLANKET | PR | 26.5 | 40.4 | 30.9 | 28 | 31.7 | 15.4
D006FX | 10-0753 | OVERHEAD CONDUCTOR BLANKET | MS | 79.7 | 25.3 | 31.2 | 50.4 | 48.8 | 41.4
D006FX | 10-0753 | OVERHEAD CONDUCTOR BLANKET | A3 | 51.6 | 56.6 | 46.9 | 52 | 57 | 45.9
D006FX | 10-0753 | OVERHEAD CONDUCTOR BLANKET | A4 | 94.5 | 97.1 | 78 | 87.8 | 91.7 | 195.5
D007FX | 14-0773 | OVERHEAD STREETLIGHTING BLANKET | PR | 0 | 0.2 | 0.1 | 0.4 | 0.1 | 0.1
D007FX | 10-0773 | OVERHEAD STREETLIGHTING BLANKET | CC | 0.1 | 0.1 | 0.3 | 0.1 | 0.2 | 0.2
D007FX | 14-0773 | OVERHEAD STREETLIGHTING BLANKET | A3 | 0 | 0.3 | 0.1 | 0.6 | 0.2 | 0.2
D007FX | 14-0773 | OVERHEAD STREETLIGHTING BLANKET | A4 | 0.1 | 0.5 | 0.2 | 1 | 0.4 | 0.3
D007FX | 10-0773 | OVERHEAD STREETLIGHTING BLANKET | PR | 1 | 1.2 | 1 | 0.1 | 0.9 | 0.5
D007FX | 10-0773 | OVERHEAD STREETLIGHTING BLANKET | A3 | 1.7 | 1.7 | 1.9 | 0.3 | 1.7 | 1.8
D007FX | 10-0773 | OVERHEAD STREETLIGHTING BLANKET | MS | 1.4 | 1.6 | 3.7 | 1.1 | 2.4 | 2.8
D007FX | 10-0773 | OVERHEAD STREETLIGHTING BLANKET | A4 | 2.9 | 3.1 | 3.6 | 0.6 | 2.8 | 2.7
D008FX | 10-0793 | OVERHEAD SERVICES BLANKET | CC | -0.5 | -0.6 | 0 | -0.1 | 0 | -1.2
D008FX | 14-0793 | OVERHEAD SERVICES BLANKET | AP | 0 | 0 | 0 | 0 | 0 | 2.3
D008FX | 14-0793 | OVERHEAD SERVICES BLANKET | PR | 2.5 | 3.4 | 2.2 | 2 | 2.8 | 0.9
D008FX | 10-0793 | OVERHEAD SERVICES BLANKET | MS | 3.9 | 2.8 | 4.3 | 3.6 | 2.3 | 2.1
D008FX | 14-0793 | OVERHEAD SERVICES BLANKET | A3 | 3.4 | 4.4 | 2.9 | 3.2 | 4.5 | 2.1
D008FX | 10-0793 | OVERHEAD SERVICES BLANKET | PR | 5.9 | 5.5 | 3.5 | 2.7 | 4.7 | 2.3
D008FX | 14-0793 | OVERHEAD SERVICES BLANKET | A4 | 5.6 | 7.3 | 4.6 | 5.1 | 6.9 | 2.8
D008FX | 10-0793 | OVERHEAD SERVICES BLANKET | A3 | 9 | 7.6 | 5.5 | 4.8 | 7.9 | 5.9
D008FX | 10-0793 | OVERHEAD SERVICES BLANKET | A4 | 15.1 | 13 | 9.2 | 8 | 12.4 | 8
D009FX | 10-0733 | O/H BLANKET - G.O.A.B. INSTALLATION | AP | 0 | 0 | 0 | 0 | 2.7 | 0
D009FX | 14-0733 | O/H BLANKET - G.O.A.B. INSTALLATION | PR | 0.4 | 0.3 | 0.3 | 2 | 1.7 | -0.3
D009FX | 14-0733 | O/H BLANKET - G.O.A.B. INSTALLATION | A3 | 0.5 | 0.4 | 0.4 | 3.3 | 2.7 | -0.8
D009FX | 10-0733 | O/H BLANKET - G.O.A.B. INSTALLATION | CC | 0.4 | 0.3 | 1.7 | 4.1 | 1 | 1.2
D009FX | 14-0733 | O/H BLANKET - G.O.A.B. INSTALLATION | A4 | 0.9 | 0.7 | 0.6 | 5.3 | 4.2 | -1
D009FX | 10-0733 | O/H BLANKET - G.O.A.B. INSTALLATION | PR | 1.1 | 1.8 | 3.8 | 3.9 | 5 | -0.3
D009FX | 10-0733 | O/H BLANKET - G.O.A.B. INSTALLATION | A3 | 2.4 | 2.8 | 8.4 | 12.5 | 9.4 | 2.5
D009FX | 10-0733 | O/H BLANKET - G.O.A.B. INSTALLATION | A4 | 4.6 | 5.2 | 16.4 | 24.6 | 15.4 | 5
D009FX | 10-0733 | O/H BLANKET - G.O.A.B. INSTALLATION | MS | 5.2 | 3.6 | 20.2 | 50.1 | 11.4 | 15.3
D010FP | 50-0127 | 2007 TRANSFORMER PURCHASE BLANKET - | AP | -11.2 | 0 | 0 | 0 | 0 | 0
D010FP | 10-0127 | 2007 TRANSFORMER PURCHASE BLANKET - | AP | -1.1 | 0 | 0 | 0 | 0 | 0
D010FP | 50-0127 | 2007 TRANSFORMER PURCHASE BLANKET - | A4 | -0.3 | 0 | 0 | 0 | 0 | 0
D010FP | 50-0127 | 2007 TRANSFORMER PURCHASE BLANKET - | A3 | -0.3 | 0 | 0 | 0 | 0 | 0
D010FP | 50-0128 | 2008 TRANSFORMER PURCHASE BLANKET - | A3 | 5.3 | 4.7 | 2.9 | 4.7 | 5.6 | 1.9
D010FP | 50-0128 | 2008 TRANSFORMER PURCHASE BLANKET - | A4 | 5.6 | 5.1 | 3.1 | 5.1 | 6.1 | 2
D010FP | 10-0128 | 2008 TRANSFORMER PURCHASE BLANKET - | A3 | 5.2 | 10 | 10.6 | 6.2 | 7.4 | 1.9
D010FP | 10-0128 | 2008 TRANSFORMER PURCHASE BLANKET - | A4 | 5.7 | 10.8 | 11.4 | 6.7 | 7.9 | 2
D010FP | 50-0128 | 2008 TRANSFORMER PURCHASE BLANKET - | CC | 13.6 | 22.7 | 14.3 | 17.9 | 20.1 | 0
D010FP | 10-0128 | 2008 TRANSFORMER PURCHASE BLANKET - | CC | 11.7 | 21.3 | 33.1 | 30.2 | 21.8 | 0
D010FP | 50-0128 | 2008 TRANSFORMER PURCHASE BLANKET - | AP | 282.7 | 170.5 | 213.5 | 240.3 | 332.7 | 599.6
D010FP | 10-0128 | 2008 TRANSFORMER PURCHASE BLANKET - | AP | 289.1 | 362.4 | 360.5 | 260.2 | 320.4 | 807.7
D011FR | 10-2109 | 2008 OVERHEAD LINE DEPT CAPITAL TOO | A3 | 8.4 | 0 | 0 | 0 | 0.3 | 3.3
D011FR | 10-2109 | 2008 OVERHEAD LINE DEPT CAPITAL TOO | A4 | 11.1 | 0 | 0 | 0 | 0.4 | 2.3
D011FR | 10-2109 | 2008 OVERHEAD LINE DEPT CAPITAL TOO | AP | 8.3 | 0 | 0 | 0 | 22.5 | 18.8
D012FM | 10-1442 | 2006 TRANSMISSION POLE BLANKET | CC | 0.1 | 0 | 0 | 0 | 0 | 0
D012FM | 10-2096 | 2008 TRANSMISSION POLE REPLACEMENT | CC | 0 | 0 | 0 | 0.1 | 0.2 | 0
D012FM | 13-1442 | 2006 TRANSMISSION POLE BLANKET | PR | 1 | -0.5 | 0 | 0 | 0 | 0
D012FM | 10-1442 | 2006 TRANSMISSION POLE BLANKET | MS | 0.7 | 0 | 0 | 0 | 0 | 0
D012FM | 13-1442 | 2006 TRANSMISSION POLE BLANKET | A3 | 1.4 | -0.6 | 0 | 0 | 0 | 0
D012FM | 13-1442 | 2006 TRANSMISSION POLE BLANKET | A4 | 2.3 | -1 | 0 | 0 | 0 | 0
D012FM | 10-1442 | 2006 TRANSMISSION POLE BLANKET | PR | 5.2 | -2.3 | 0 | 0 | 0 | 0
D012FM | 10-1442 | 2006 TRANSMISSION POLE BLANKET | A3 | 7.5 | -3.1 | 0 | 0 | 0 | 0
D012FM | 10-2096 | 2008 TRANSMISSION POLE REPLACEMENT | MS | 0 | 0 | 0 | 1.6 | 2.9 | 0
D012FM | 10-1442 | 2006 TRANSMISSION POLE BLANKET | AP | -1.5 | 6.3 | 0 | 0 | 0 | 0
D012FM | 10-2096 | 2008 TRANSMISSION POLE REPLACEMENT | AP | 6.3 | 0.5 | 0 | 0 | 0 | 0
D012FM | 10-1442 | 2006 TRANSMISSION POLE BLANKET | A4 | 12.3 | -5.1 | 0 | 0 | 0 | 0
D012FM | 10-2096 | 2008 TRANSMISSION POLE REPLACEMENT | PR | -0.6 | 0 | 0.6 | 8.7 | 16.6 | -3.4
D012FM | 10-2096 | 2008 TRANSMISSION POLE REPLACEMENT | A3 | -0.9 | 0.1 | 0.1 | 14.5 | 27.6 | -8.6
D012FM | 10-2096 | 2008 TRANSMISSION POLE REPLACEMENT | A4 | -1.4 | 0.1 | 0.6 | 23.3 | 42.6 | -11.3
D107WT | 10-0777 | ELECTRIC METER PURCHASE BLANKET | CC | 0.1 | 0.1 | 0.2 | 0 | 0 | 0.1
D107WT | 10-0777 | ELECTRIC METER PURCHASE BLANKET | MS | 1.7 | 0.7 | 2 | 0.5 | 0 | 1.5
D107WT | 10-0777 | ELECTRIC METER PURCHASE BLANKET | A3 | 0.3 | 0.3 | 1 | 1.7 | 10.2 | 1.8
D107WT | 10-0777 | ELECTRIC METER PURCHASE BLANKET | A4 | 0.7 | 0.4 | 1.6 | 1.9 | 13.6 | 1.8
D107WT | 10-0777 | ELECTRIC METER PURCHASE BLANKET | AP | 3.6 | 18 | 74.4 | 168.5 | 34.5 | 100.8
D110YX | 11-1999 | A&G CLEARING BLANKET WORK ORDER | A4 | -23.1 | -26 | -25.4 | -25.2 | -25.4 | -1420.2
D110YX | 11-1999 | A&G CLEARING BLANKET WORK ORDER | A3 | -78.3 | -88.6 | -86.5 | -85.7 | -86.3 | -81.4
D110YX | 11-1999 | A&G CLEARING BLANKET WORK ORDER | CC | 25 | 25 | 25 | 25 | 25 | 25
D110YX | 11-1999 | A&G CLEARING BLANKET WORK ORDER | PR | 85 | 85 | 85 | 85 | 85 | 85
D127GT | 10-2401 | ELECTRIC RATE CASE INCREMENTAL VEHI | A3 | 0 | 0 | 0 | 0 | 3.6 | 0
D127GT | 10-2401 | ELECTRIC RATE CASE INCREMENTAL VEHI | A4 | 0 | 0 | 0 | 0 | 3.8 | 0
D127GT | 10-2401 | ELECTRIC RATE CASE INCREMENTAL VEHI | AP | 0 | 0 | 0 | 0 | 435.1 | 0
D139BR | 10-2129 | 2008 TRANS ENGINEERING SOFTWARE/HAR | AP | 0 | 0 | 0 | 0 | 0 | 14.2
D144VF | 14-0100 | TRANSFORMER INTERCOMPANY SALES BLAN | CC | -11.1 | -1689.3 | 0 | 0 | 0 | 0
D144VF | 10-0100 | TRANSFORMER INTERCOMPANY SALES BLAN | CC | 10.8 | 0 | 0 | 0 | 0 | -206.9
D144VF | 54-0100 | TRANSFORMER INTERCOMPANY SALES BLAN | CC | -25.9 | -126.7 | 0 | 0 | 0 | 0
D144VF | 50-0100 | TRANSFORMER INTERCOMPANY SALES BLAN | CC | 4.1 | 0 | 0 | 0 | 0 | -62.6
D144VW | 13-0101 | TRANSFORMER RETIREMENT AND METER IN | CC | 0 | -97 | 0 | 0 | 0 | 0
D144VW | 10-0101 | TRANSFORMER RETIREMENT AND METER IN | CC | 0 | 4.5 | 0 | 0 | 0 | 0
D164BP | 10-1792 | 2007 DISTRIB SUBSTATION AUTOMATION | PR | -1 | 0 | 0 | 0 | 0 | 0
D171FR | 50-2293 | 2008 CABLE REBUILD, SCHER DR., NEW | AP | -3 | -2 | 0 | 0 | 0 | 0
D171FR | 50-2290 | 2008 NY CABLE REBUILD, COLGATE DR, | AP | -4 | -0.9 | 0 | 0 | 0 | 0
D171FR | 50-2320 | 2008 CABLE REBUILD, CORINTHIAN RD, | A4 | -0.9 | 0 | 0 | 0 | 0 | 0
D171FR | 50-2320 | 2008 CABLE REBUILD, CORINTHIAN RD, | A3 | -0.6 | 0 | 0 | 0 | 0 | 0
D171FR | 53-2320 | 2008 CABLE REBUILD, CORINTHIAN RD, | A4 | -0.4 | 0 | 0 | 0 | 0 | 0
D171FR | 50-2320 | 2008 CABLE REBUILD, CORINTHIAN RD, | PR | -0.4 | 0 | 0 | 0 | 0 | 0
D171FR | 53-2320 | 2008 CABLE REBUILD, CORINTHIAN RD, | A3 | -0.3 | 0 | 0 | 0 | 0 | 0
D171FR | 50-2351 | 2008 NY CABLE REBUILD, WARREN ST. M | MS | -3 | 0 | 0 | 0 | 2.7 | 0
D171FR | 53-2320 | 2008 CABLE REBUILD, CORINTHIAN RD, | PR | -0.2 | 0 | 0 | 0 | 0 | 0
D171FR | 50-2351 | 2008 NY CABLE REBUILD, WARREN ST. M | CC | -0.3 | 0 | 0 | 0 | 0.2 | 0
D171FR | 53-2352 | 2008 CABLE REBUILD, GRIFFITH PL., P | PR | 0 | 0 | 0 | 0.1 | 0 | 0
D171FR | 50-2406 | 2008 CABLE REBUILD, BON-AIRE/SOMMER | CC | 0 | 0.2 | -0.1 | 0 | 0 | 0
D171FR | 50-2322 | 2008 CABLE REBUILD, YORK CT., NEW C | CC | 0.1 | 0 | 0 | 0 | 0 | 0
D171FR | 50-2290 | 2008 NY CABLE REBUILD, COLGATE DR, | CC | 0 | 0 | 0 | 0.1 | 0 | 0
D171FR | 50-2365 | 2008 CABLE REBUILD - FLORAL CT - NA | CC | 0.1 | 0 | 0 | 0 | 0 | 0
D171FR | 50-2352 | 2008 CABLE REBUILD, GRIFFITH PL., P | CC | 0 | 0 | 0 | 0.1 | 0 | 0
D171FR | 50-2287 | 2008 NY CABLE REBUILD, PARLIMENT DR | A3 | 0.1 | 0 | 0 | 0 | 0 | 0
D171FR | 50-2287 | 2008 NY CABLE REBUILD, PARLIMENT DR | A4 | 0.1 | 0 | 0 | 0 | 0 | 0
D171FR | 50-2291 | 2008 NY CABLE REBUILD, ARDEN, PL, N | CC | 0.3 | -0.1 | 0 | 0 | 0 | 0
D171FR | 50-2387 | 2008 CABLE REBUILD - PONDVIEW DRIVE | CC | 0.3 | -0.1 | 0 | 0 | 0 | 0
D171FR | 53-2365 | 2008 CABLE REBUILD - FLORAL CT - NA | PR | 0.2 | 0 | 0 | 0 | 0 | 0
D171FR | 53-2290 | 2008 NY CABLE REBUILD, COLGATE DR, | PR | 0.2 | 0 | 0 | 0 | 0 | 0
D171FR | 53-2352 | 2008 CABLE REBUILD, GRIFFITH PL., P | AP | 0.2 | 0 | 0 | 0 | 0 | 0
D171FR | 53-2365 | 2008 CABLE REBUILD - FLORAL CT - NA | A3 | 0.2 | 0 | 0 | 0 | 0 | 0
D171FR | 53-2291 | 2008 NY CABLE REBUILD, ARDEN, PL, N | PR | 0 | 0 | 0.2 | 0 | 0 | 0
D171FR | 53-2406 | 2008 CABLE REBUILD, BON-AIRE/SOMMER | PR | 0 | 0 | 0 | 0 | 0.2 | 0
D171FR | 53-2352 | 2008 CABLE REBUILD, GRIFFITH PL., P | A3 | 0 | 0 | 0 | 0.2 | 0 | 0
D171FR | 53-2365 | 2008 CABLE REBUILD - FLORAL CT - NA | AP | 0.2 | 0 | 0 | 0 | 0 | 0
D171FR | 53-2406 | 2008 CABLE REBUILD, BON-AIRE/SOMMER | AP | 0 | 0 | 0.2 | 0 | 0 | 0
D171FR | 53-2291 | 2008 NY CABLE REBUILD, ARDEN, PL, N | AP | 0.2 | 0 | 0 | 0 | 0 | 0
D171FR | 53-2351 | 2008 NY CABLE REBUILD, WARREN ST. M | PR | 0.1 | 0.1 | 0 | 0 | 0 | 0
D171FR | 53-2290 | 2008 NY CABLE REBUILD, COLGATE DR, | A3 | 0.3 | 0 | 0 | 0 | 0 | 0
D171FR | 53-2291 | 2008 NY CABLE REBUILD, ARDEN, PL, N | A3 | 0 | 0 | 0.3 | 0 | 0 | 0
D171FR | 53-2352 | 2008 CABLE REBUILD, GRIFFITH PL., P | A4 | 0 | 0 | 0 | 0.3 | 0 | 0
D171FR | 53-2406 | 2008 CABLE REBUILD, BON-AIRE/SOMMER | A3 | 0 | 0 | 0 | 0 | 0.3 | 0
D171FR | 53-2365 | 2008 CABLE REBUILD - FLORAL CT - NA | A4 | 0.3 | 0 | 0 | 0 | 0 | 0
D171FR | 50-2295 | 2008 CABLE REBUILD, THE PROMENADE, | CC | 0 | 0.3 | 0 | 0 | 0 | 0
D171FR | 53-2290 | 2008 NY CABLE REBUILD, COLGATE DR, | A4 | 0.4 | -0.1 | 0 | 0 | 0 | 0
D171FR | 50-2365 | 2008 CABLE REBUILD - FLORAL CT - NA | MS | 0.6 | 0 | 0 | -0.2 | 0 | 0
D171FR | 53-2351 | 2008 NY CABLE REBUILD, WARREN ST. M | A3 | 0.2 | 0.2 | 0 | 0 | 0 | 0
D171FR | 53-2351 | 2008 NY CABLE REBUILD, WARREN ST. M | AP | 0.4 | 0 | 0 | 0 | 0 | 0
D171FR | 50-2322 | 2008 CABLE REBUILD, YORK CT., NEW C | PR | 0.3 | 0 | 0.1 | 0 | 0 | 0
D171FR | 53-2291 | 2008 NY CABLE REBUILD, ARDEN, PL, N | A4 | 0 | 0 | 0.4 | 0 | 0 | 0
D171FR | 53-2387 | 2008 CABLE REBUILD - PONDVIEW DRIVE | AP | 0 | 0.4 | 0 | 0 | 0 | 0
D171FR | 53-2406 | 2008 CABLE REBUILD, BON-AIRE/SOMMER | A4 | 0 | 0 | 0 | 0 | 0.5 | 0
D171FR | 53-2351 | 2008 NY CABLE REBUILD, WARREN ST. M | A4 | 0.2 | 0.3 | 0 | 0 | 0 | 0
D171FR | 50-2406 | 2008 CABLE REBUILD, BON-AIRE/SOMMER | PR | 0 | 0 | 0 | 0 | 0.5 | 0
D171FR | 50-2352 | 2008 CABLE REBUILD, GRIFFITH PL., P | MS | -0.6 | 0 | 0 | 1.4 | -0.2 | 0
D171FR | 50-2290 | 2008 NY CABLE REBUILD, COLGATE DR, | PR | 0.7 | -0.1 | 0 | 0 | 0 | 0
D171FR | 50-2235 | 2008 UNDERGROUND REBUILD BLANKET - | CC | 0 | 0 | 0 | 0 | 0 | 0.6
D171FR | 50-2295 | 2008 CABLE REBUILD, THE PROMENADE, | PR | 0 | 0.6 | 0 | 0 | 0 | 0
D171FR | 50-2365 | 2008 CABLE REBUILD - FLORAL CT - NA | PR | 0.6 | 0 | 0 | 0 | 0 | 0
D171FR | 50-2290 | 2008 NY CABLE REBUILD, COLGATE DR, | MS | 0 | 0 | 0 | 0.7 | 0 | 0
D171FR | 50-2291 | 2008 NY CABLE REBUILD, ARDEN, PL, N | PR | 0 | 0 | 0.8 | 0 | 0 | 0
D171FR | 50-2322 | 2008 CABLE REBUILD, YORK CT., NEW C | A3 | 0.6 | 0 | 0.2 | 0 | 0 | 0
D171FR | 50-2387 | 2008 CABLE REBUILD - PONDVIEW DRIVE | A3 | 0.7 | 0.2 | 0 | 0 | 0 | 0
D171FR | 50-2290 | 2008 NY CABLE REBUILD, COLGATE DR, | A3 | 1 | -0.1 | 0 | 0.1 | 0 | 0
D171FR | 50-2352 | 2008 CABLE REBUILD, GRIFFITH PL., P | PR | 0 | 0 | 0 | 1 | 0 | 0
D171FR | 50-2365 | 2008 CABLE REBUILD - FLORAL CT - NA | A3 | 1 | 0 | 0 | 0 | 0 | 0
D171FR | 50-2351 | 2008 NY CABLE REBUILD, WARREN ST. M | PR | 0.5 | 0.6 | 0 | 0 | 0 | 0
D171FR | 50-2322 | 2008 CABLE REBUILD, YORK CT., NEW C | MS | 1.1 | 0 | 0 | 0 | 0 | 0
D171FR | 50-2406 | 2008 CABLE REBUILD, BON-AIRE/SOMMER | A3 | 0 | 0.3 | 0.1 | 0 | 0.9 | 0
D171FR | 50-2322 | 2008 CABLE REBUILD, YORK CT., NEW C | A4 | 1 | 0 | 0.3 | 0 | 0 | 0
D171FR | 50-2235 | 2008 UNDERGROUND REBUILD BLANKET - | A3 | 0 | 0 | 0 | 0 | 0 | 1.4
D171FR | 50-2351 | 2008 NY CABLE REBUILD, WARREN ST. M | A3 | 0.3 | 0.8 | 0 | 0 | 0.3 | 0
D171FR | 50-2290 | 2008 NY CABLE REBUILD, COLGATE DR, | A4 | 1.5 | -0.2 | 0 | 0.2 | 0 | 0
D171FR | 50-2295 | 2008 CABLE REBUILD, THE PROMENADE, | A3 | 0 | 1.5 | 0 | 0 | 0 | 0.1
D171FR | 50-2387 | 2008 CABLE REBUILD - PONDVIEW DRIVE | A4 | 1.6 | 0 | 0 | 0 | 0 | 0
D171FR | 50-2365 | 2008 CABLE REBUILD - FLORAL CT - NA | A4 | 1.6 | 0 | 0 | 0 | 0 | 0
D171FR | 50-2352 | 2008 CABLE REBUILD, GRIFFITH PL., P | A3 | 0 | 0 | 0 | 1.7 | 0 | 0
D171FR | 50-2291 | 2008 NY CABLE REBUILD, ARDEN, PL, N | A3 | 0.8 | -0.1 | 1.2 | 0 | 0 | 0
D171FR | 50-2351 | 2008 NY CABLE REBUILD, WARREN ST. M | A4 | 0 | 1.3 | 0 | 0 | 0.7 | 0
D171FR | 50-2406 | 2008 CABLE REBUILD, BON-AIRE/SOMMER | A4 | 0 | 0.9 | -0.1 | 0 | 1.4 | 0
D171FR | 50-2322 | 2008 CABLE REBUILD, YORK CT., NEW C | AP | 0 | 2.2 | 0 | 0 | 0 | 0
D171FR | 50-2406 | 2008 CABLE REBUILD, BON-AIRE/SOMMER | MS | 0 | 2.7 | -0.8 | 0 | 0.5 | 0
D171FR | 50-2352 | 2008 CABLE REBUILD, GRIFFITH PL., P | A4 | -0.1 | 0 | 0 | 2.6 | 0 | 0
D171FR | 50-2235 | 2008 UNDERGROUND REBUILD BLANKET - | A4 | 0 | 0 | 0 | 0 | 0 | 2.7
D171FR | 50-2320 | 2008 CABLE REBUILD, CORINTHIAN RD, | AP | 0 | 0.9 | 4.3 | -2.5 | 0 | 0
D171FR | 50-2295 | 2008 CABLE REBUILD, THE PROMENADE, | A4 | 0 | 2.9 | -0.1 | 0 | 0 | 0.1
D171FR | 50-2291 | 2008 NY CABLE REBUILD, ARDEN, PL, N | MS | 4 | -0.8 | 0 | 0 | 0 | 0
D171FR | 50-2387 | 2008 CABLE REBUILD - PONDVIEW DRIVE | MS | 3.7 | -0.6 | 0 | 0.1 | 0 | 0
D171FR | 50-2291 | 2008 NY CABLE REBUILD, ARDEN, PL, N | A4 | 1.8 | -0.3 | 1.7 | 0 | 0 | 0
D171FR | 50-2295 | 2008 CABLE REBUILD, THE PROMENADE, | MS | 0 | 3.9 | 0 | 0 | 0 | 0
D171FR | 50-2287 | 2008 NY CABLE REBUILD, PARLIMENT DR | AP | 5.6 | 0 | 0 | 0 | 0 | 0
D171FR | 50-2235 | 2008 UNDERGROUND REBUILD BLANKET - | MS | 0 | 0 | 0 | 0 | 0 | 6.9
D171FR | 50-2351 | 2008 NY CABLE REBUILD, WARREN ST. M | AP | 8.1 | -1.6 | 0 | 0 | 0 | 3.2
D171FR | 50-2365 | 2008 CABLE REBUILD - FLORAL CT - NA | AP | 11 | 0 | 0 | 0 | 2.5 | 0
D171FR | 50-2291 | 2008 NY CABLE REBUILD, ARDEN, PL, N | AP | 12.1 | 0.7 | 0 | 0 | 3.1 | 0
D171FR | 50-2235 | 2008 UNDERGROUND REBUILD BLANKET - | AP | 0 | 0 | 0 | 0 | 0 | 18.5
D171FR | 50-2352 | 2008 CABLE REBUILD, GRIFFITH PL., P | AP | 17.5 | 1.5 | 0 | 1.3 | 0 | -1.3
D171FR | 50-2387 | 2008 CABLE REBUILD - PONDVIEW DRIVE | AP | 18 | 6.2 | 0.8 | 0 | -2 | 0
D171FR | 50-2406 | 2008 CABLE REBUILD, BON-AIRE/SOMMER | AP | 0 | 22 | 23.3 | -17 | -5 | 0
D171FR | 50-2295 | 2008 CABLE REBUILD, THE PROMENADE, | AP | 0 | 54.7 | -28.2 | 0 | -5 | 11.6
D172FT | 50-0696 | UNDERGROUND CABLE INJECTION BLANKET | CC | 0.3 | 0.3 | 0 | 0 | 0 | 0
D172FT | 50-0696 | UNDERGROUND CABLE INJECTION BLANKET | MS | 4.1 | 3.8 | 0.3 | 0 | 0 | 0
D172FT | 50-0696 | UNDERGROUND CABLE INJECTION BLANKET | PR | 7.3 | 2.9 | 2.1 | 0 | 0.2 | 0
D172FT | 50-0696 | UNDERGROUND CABLE INJECTION BLANKET | A3 | 10.9 | 4.9 | 4.4 | 0.3 | 0.2 | 0.1
D172FT | 50-0696 | UNDERGROUND CABLE INJECTION BLANKET | A4 | 17.5 | 7.9 | 5.9 | 0.3 | 0.4 | 0.1
D172FT | 50-0696 | UNDERGROUND CABLE INJECTION BLANKET | AP | 74.5 | 52.9 | 74.2 | 27.1 | 0 | 8.7
D194WT | 10-0888 | ELECTRIC METER FIRST INSTALL BLANKE | CC | 0.2 | 0 | 0 | 0 | 0 | 0
D194WT | 10-0888 | ELECTRIC METER FIRST INSTALL BLANKE | MS | 2.4 | 0 | 0 | 0 | 0 | 0
D194WT | 10-0888 | ELECTRIC METER FIRST INSTALL BLANKE | AP | 0.1 | 6.3 | 6.5 | 0 | 2.5 | 54
D194WT | 10-0888 | ELECTRIC METER FIRST INSTALL BLANKE | A3 | 13.3 | 11.3 | 17.3 | 23.1 | 23.3 | 10.5
D194WT | 10-0888 | ELECTRIC METER FIRST INSTALL BLANKE | PR | 19.2 | 15.7 | 25.4 | 34.1 | 33.9 | 15.2
D194WT | 10-0888 | ELECTRIC METER FIRST INSTALL BLANKE | A4 | 31.2 | 25.5 | 40 | 53.7 | 53.7 | 24.1
D203CR | 10-2152 | SMART GRID DEVICES FOR CAPACITOR CO | CC | 0 | 0 | 0 | 0 | 0.1 | 0
D203CR | 10-2152 | SMART GRID DEVICES FOR CAPACITOR CO | A3 | 0 | 0.2 | 0 | 0.1 | 0.1 | 0
D203CR | 10-2152 | SMART GRID DEVICES FOR CAPACITOR CO | PR | 0 | 0.8 | 0 | 0.3 | 0.5 | 0
D203CR | 10-2152 | SMART GRID DEVICES FOR CAPACITOR CO | A4 | 0 | 0.9 | 0 | 0.3 | 0.5 | 0
D203CR | 10-2152 | SMART GRID DEVICES FOR CAPACITOR CO | AP | 0 | 0 | 0 | 0 | 4.9 | 0
D240CP | 10-1807 | 2007 DISTRIBUTION AUTOMATION BLANKE | CC | 0 | 0 | 0.3 | 0 | 0 | 0
D240CP | 10-1807 | 2007 DISTRIBUTION AUTOMATION BLANKE | PR | 0 | 0.3 | 0.5 | 0 | 0 | 0
D240CP | 10-1807 | 2007 DISTRIBUTION AUTOMATION BLANKE | A3 | 0 | 0.4 | 1.3 | 0 | 0 | 0
D240CP | 10-1807 | 2007 DISTRIBUTION AUTOMATION BLANKE | A4 | 0 | 0.8 | 2.6 | 0 | 0 | 0
D240CP | 10-1807 | 2007 DISTRIBUTION AUTOMATION BLANKE | MS | 0 | 0.5 | 3.6 | 0 | 0 | 0
D240CR | 10-2108 | 2008 DISTRIBUTION AUTOMATION BLANKE | CC | 0.1 | 1.1 | 0.8 | 0.4 | 0.3 | 0.7
D240CR | 14-2108 | 2008 DISTRIBUTION AUTOMATION BLANKE | PR | 0.7 | 2.6 | 0.1 | 0.7 | 0.2 | 3.3
D240CR | 14-2108 | 2008 DISTRIBUTION AUTOMATION BLANKE | A3 | 0.9 | 3.4 | 0.1 | 1.1 | 0.3 | 7.7
D240CR | 14-2108 | 2008 DISTRIBUTION AUTOMATION BLANKE | A4 | 1.5 | 5.6 | 0.3 | 1.8 | 0.4 | 10.3
D240CR | 10-2108 | 2008 DISTRIBUTION AUTOMATION BLANKE | MS | 0.9 | 13.5 | 7.2 | 4.2 | 3 | 8.7
D240CR | 10-2108 | 2008 DISTRIBUTION AUTOMATION BLANKE | PR | 10.2 | 16.1 | 11 | 15.2 | 18.9 | 21.8
D240CR | 10-2108 | 2008 DISTRIBUTION AUTOMATION BLANKE | A3 | 3.6 | 40.1 | 9.1 | 6.3 | 8.8 | 28.4
D240CR | 10-2108 | 2008 DISTRIBUTION AUTOMATION BLANKE | A4 | 12.8 | 65.2 | 20.8 | 20.3 | 25.9 | 47.9
D240CR | 10-2108 | 2008 DISTRIBUTION AUTOMATION BLANKE | AP | 0.6 | 353.9 | 16.6 | 0 | 0 | 552.7
D243CR | 10-2154 | 2008 OMS HARDWARE BLANKET | PR | 0 | 0 | 0 | 3.4 | -6.1 | 1
D243CR | 10-2154 | 2008 OMS HARDWARE BLANKET | A3 | 0 | 0 | 0 | 0.1 | 0 | 4.4
D243CR | 10-2154 | 2008 OMS HARDWARE BLANKET | A4 | 0 | 0 | 0 | 2.7 | 0 | 4
D243CR | 10-2154 | 2008 OMS HARDWARE BLANKET | AP | 0 | 0 | 0 | 1.1 | 11.6 | 67.3
D277CR | 10-2153 | 2008 DISTRIBUTION ENGINEERING TEST | A3 | 0 | 0 | 0 | 0 | 0 | 0.2
D277CR | 10-2153 | 2008 DISTRIBUTION ENGINEERING TEST | A4 | 0 | 0 | 0 | 0 | 0 | 0.3
D277CR | 10-2153 | 2008 DISTRIBUTION ENGINEERING TEST | AP | 0 | 0 | 0 | 0 | 36.4 | 3.6
D290GP | 14-1886 | 2007 SALE OF SCRAP | CC | 0 | -1.2 | -8.7 | 0 | 0 | 0
D290GR | 14-2207 | 2008 SALE OF SCRAP | CC | -20.3 | -40.2 | -13.6 | -21.3 | 0.1 | -15.5
D290GR | 14-2207 | 2008 SALE OF SCRAP | A3 | 0.4 | 0.3 | 1.4 | 0.5 | 0.3 | 4.1
D290GR | 14-2207 | 2008 SALE OF SCRAP | A4 | 1.1 | 0.9 | 3.7 | 1.1 | 0.7 | 7.8
D290GR | 14-2207 | 2008 SALE OF SCRAP | AP | 3.3 | 4.5 | 2.9 | 1.7 | 6.2 | 3.2
D290GR | 14-2207 | 2008 SALE OF SCRAP | MS | 2.6 | 2.9 | 9.2 | 4.1 | 3.1 | 20.9
D291FR | 14-2238 | 2008 PCB OIL TESTING AND DISPOSAL B | AP | 8.8 | 5.6 | -3 | 10.2 | 0 | 49.4
D400WR | 10-2190 | 2008 ELEC METER DEPARTMENT MISCELLA | A4 | 0 | 0 | 0 | 0.2 | 2.6 | 4
D400WR | 10-2190 | 2008 ELEC METER DEPARTMENT MISCELLA | A3 | 0 | 0 | 0 | 0.2 | 2 | 5.7
D400WR | 10-2190 | 2008 ELEC METER DEPARTMENT MISCELLA | AP | 0 | 0 | 0 | 39.1 | 165.4 | -83.2
D439BR | 13-2142 | 2008 BANK METERING UPGRADE BLANKET | PR | 0 | 0 | 0 | 0 | 0.4 | 0
D439BR | 13-2142 | 2008 BANK METERING UPGRADE BLANKET | A3 | 0 | 0 | 0 | 0 | 0.4 | 0
D439BR | 13-2142 | 2008 BANK METERING UPGRADE BLANKET | A4 | 0 | 0 | 0 | 0 | 0.8 | 0
D439BR | 10-2142 | 2008 BANK METERING UPGRADE BLANKET | A3 | 0.1 | 0.9 | 0.3 | -0.1 | 6.5 | 2.5
D439BR | 10-2142 | 2008 BANK METERING UPGRADE BLANKET | AP | 0 | 12 | 0 | 0 | 0 | 0
D439BR | 10-2142 | 2008 BANK METERING UPGRADE BLANKET | PR | 0.3 | 0 | 1.6 | -0.2 | 9.1 | 7.7
D439BR | 10-2142 | 2008 BANK METERING UPGRADE BLANKET | A4 | 0.4 | 1.2 | 1.6 | -0.3 | 14.9 | 9.5
D440NR | 13-2118 | 2008 POLE BUTT REMOVAL BLANKET | AP | 1.8 | 0.8 | 0.8 | 4 | 3.5 | 6
D445BR | 10-2143 | 2008 PAVING & DRAINAGE BLANKET - CI | A3 | 0 | 0 | 0.2 | 0.1 | 0.8 | 2.1
D445BR | 10-2143 | 2008 PAVING & DRAINAGE BLANKET - CI | PR | 0 | 0 | 1.1 | 0.5 | 2.1 | 4.4
D445BR | 10-2143 | 2008 PAVING & DRAINAGE BLANKET - CI | A4 | 0 | 0 | 1.2 | 0.6 | 2.7 | 6.2
D445BR | 10-2143 | 2008 PAVING & DRAINAGE BLANKET - CI | AP | 0 | 0 | 0 | 0 | 22.1 | 31.7
D550FX | 50-0616 | UNDERGROUND TRENCHING BLANKET | CC | -22.9 | -14.9 | -23.4 | -15.7 | 21.1 | 0
D550FX | 51-2288 | URD KOHL INDUSTRIAL PK, N RTE 303, | CC | 0 | 0 | 0 | 0 | 0 | -9.4
D550FX | 51-2388 | URD TAMMY FLANNERY, DEER POND DRIVE | CC | 0 | -8.1 | 0 | 0 | 0 | 0
D550FX | 51-2277 | URD ALBERT WISNER PUBLIC LIBRARY, W | CC | 0 | 0 | -5.1 | 0 | 0 | 0
D550FX | 51-2092 | URD/ST. LGTS WILLOWS SUB., WESLEY H | CC | 0 | 0 | 0 | -3.1 | 0 | 0
D550FX | 51-2091 | URD WILLOWS SUB-OUTSIDE LOTS, WESLE | CC | -2.2 | 0 | 0 | 0 | 0 | 0
D550FX | 51-2283 | URD BOYLE SUBDIVISION, TERRACE LN, | CC | -1.6 | 0 | 0 | 0 | 0 | 0
D550FX | 51-2325 | URD HORIZONS AT WAWAYANDA-SECT 2, H | CC | 0 | 0 | 0 | 0 | -1.2 | 0
D550FX | 51-2361 | URD CARRIAGE PARK, WEST MAIN ST, GO | CC | 0 | 0 | -0.9 | 0 | 0 | 0
D550FX | 51-2095 | URD ZEV DRESNER, 1 GWEN LANE, MONSE | CC | -0.9 | 0 | 0 | 0 | 0 | 0
D550FX | 51-2285 | URD ROBERT RINO, 20 VIOLA RD, MONTE | CC | 0 | -0.8 | 0 | 0 | 0 | 0
D550FX | 51-2286 | URD SMK HOME BLDRS, SUMMIT AVE, TAP | CC | -0.8 | 0 | 0 | 0 | 0 | 0
D550FX | 51-2363 | URD ZARA CROWLEY, CASTLE HGTS AV, U | CC | 0 | 0 | 0 | 0 | -0.7 | 0
D550FX | 51-2381 | URD COUNTRY COMFORT HOMES CORP, MID | CC | 0 | 0 | 0 | -0.7 | 0 | 0
D550FX | 51-2360 | URD BARBARA PEPEYRA, STEGMEYER LN., | CC | 0 | 0 | 0 | 0 | -0.3 | 0
D550FX | 51-2381 | URD COUNTRY COMFORT HOMES CORP, MID | A3 | 0 | 0.1 | 0 | 0 | 0 | 0
D550FX | 51-2388 | URD TAMMY FLANNERY, DEER POND DRIVE | A3 | 0 | 0 | 0 | 0 | 0.1 | 0
D550FX | 51-2388 | URD TAMMY FLANNERY, DEER POND DRIVE | A4 | 0 | 0 | 0 | 0 | 0.1 | 0
D550FX | 51-2381 | URD COUNTRY COMFORT HOMES CORP, MID | A4 | 0 | 0.1 | 0 | 0 | 0 | 0
D550FX | 51-2092 | URD/ST. LGTS WILLOWS SUB., WESLEY H | PR | 0.2 | 0 | 0 | 0 | 0 | 0
D550FX | 51-2360 | URD BARBARA PEPEYRA, STEGMEYER LN., | AP | 0 | 0 | 0 | 0.3 | 0 | 0
D550FX | 51-2325 | URD HORIZONS AT WAWAYANDA-SECT 2, H | PR | 0.4 | 0 | 0 | 0 | 0 | 0
D550FX | 51-2092 | URD/ST. LGTS WILLOWS SUB., WESLEY H | A3 | 0.3 | 0 | 0.1 | 0 | 0 | 0
D550FX | 51-2435 | URD WOODSIDE KNOLLS DRIVE, MIDDLETO | PR | 0 | 0 | 0 | 0.5 | 0 | 0
D550FX | 51-2277 | URD ALBERT WISNER PUBLIC LIBRARY, W | PR | 0.5 | 0 | 0 | 0 | 0 | 0
D550FX | 51-2092 | URD/ST. LGTS WILLOWS SUB., WESLEY H | A4 | 0.4 | 0 | 0.1 | 0 | 0 | 0
D550FX | 51-2325 | URD HORIZONS AT WAWAYANDA-SECT 2, H | A3 | 0.6 | 0 | 0 | 0 | 0 | 0
D550FX | 51-2378 | URD MADISON PARK CONDOMINIUMS, SPRI | AP | 0 | 0 | 0 | 0 | 0.6 | 0
D550FX | 51-2361 | URD CARRIAGE PARK, WEST MAIN ST, GO | PR | 0.6 | 0 | 0 | 0 | 0 | 0
D550FX | 51-2381 | URD COUNTRY COMFORT HOMES CORP, MID | AP | 0 | 0.7 | 0 | 0 | 0 | 0
D550FX | 51-2277 | URD ALBERT WISNER PUBLIC LIBRARY, W | A3 | 0.7 | 0 | 0 | 0 | 0.1 | 0
D550FX | 51-2288 | URD KOHL INDUSTRIAL PK, N RTE 303, | PR | 0 | 0 | 0 | 0.8 | 0 | 0
D550FX | 51-2435 | URD WOODSIDE KNOLLS DRIVE, MIDDLETO | A3 | 0 | 0 | 0 | 0.8 | 0 | 0
D550FX | 51-2361 | URD CARRIAGE PARK, WEST MAIN ST, GO | A3 | 0.8 | 0 | 0 | 0 | 0 | 0
D550FX | 51-2325 | URD HORIZONS AT WAWAYANDA-SECT 2, H | A4 | 0.9 | 0 | 0 | 0 | 0 | 0
D550FX | 51-2378 | URD MADISON PARK CONDOMINIUMS, SPRI | PR | 0 | 0 | 0 | 0 | 0 | 1.1
D550FX | 51-2435 | URD WOODSIDE KNOLLS DRIVE, MIDDLETO | A4 | 0 | 0 | 0 | 1.2 | 0 | 0
D550FX | 51-2277 | URD ALBERT WISNER PUBLIC LIBRARY, W | A4 | 1.1 | 0 | 0 | 0 | 0.1 | 0
D550FX | 51-2361 | URD CARRIAGE PARK, WEST MAIN ST, GO | A4 | 1.3 | 0 | 0 | 0 | 0 | 0
D550FX | 51-2288 | URD KOHL INDUSTRIAL PK, N RTE 303, | A3 | 0 | 0 | 0 | 1.2 | 0.1 | 0
D550FX | 51-2288 | URD KOHL INDUSTRIAL PK, N RTE 303, | A4 | 0 | 0 | 0 | 1.8 | 0.1 | 0
D550FX | 51-2378 | URD MADISON PARK CONDOMINIUMS, SPRI | A3 | 0 | 0 | 0 | 0 | 0 | 2
D550FX | 51-2423 | URD JB ENTERPRISE, 2 SUNRISE DR, MO | AP | 0 | 0 | 0 | 0 | 0 | 2.3
D550FX | 51-2326 | URD BESIATA DESHMAYA LLC, MERON DR, | AP | 0 | 2.5 | 0 | 0 | 0 | 0
D550FX | 51-2378 | URD MADISON PARK CONDOMINIUMS, SPRI | A4 | 0 | 0 | 0 | 0 | 0 | 2.8
D550FX | 51-2424 | URD S V SENIOR APTS., N. MAIN ST, S | AP | 0 | 0 | 0 | 5.6 | -1.9 | 0
D550FX | 51-2354 | URD BEN VELTIDI, 4 LINDA DR., SUFFE | AP | 0 | 0 | 0 | 0 | 0 | 3.7
D550FX | 51-2454 | URD SHLOIMY TAUBER, CALVERT DR, MON | AP | 0 | 0 | 0 | 0 | 0 | 4.2
D550FX | 51-2285 | URD ROBERT RINO, 20 VIOLA RD, MONTE | AP | 4.7 | 0 | 0 | 0 | 0 | 0
D550FX | 51-2288 | URD KOHL INDUSTRIAL PK, N RTE 303, | AP | 0 | 0 | 0 | 0 | 8.2 | 0
D550FX | 51-2388 | URD TAMMY FLANNERY, DEER POND DRIVE | AP | 0 | 0 | 0 | 0 | 8.3 | 0
D550FX | 51-2363 | URD ZARA CROWLEY, CASTLE HGTS AV, U | AP | 0 | 0 | 0 | 3.3 | 5.2 | 0
D550FX | 51-2092 | URD/ST. LGTS WILLOWS SUB., WESLEY H | AP | 18 | -16.8 | 9.5 | 0 | 0 | 0
D550FX | 51-2277 | URD ALBERT WISNER PUBLIC LIBRARY, W | AP | 0 | 0 | 0 | 0 | 11 | 0
D550FX | 50-0616 | UNDERGROUND TRENCHING BLANKET | PR | 0.9 | 3.1 | 0.9 | 4 | 2.2 | 0.5
D550FX | 50-0616 | UNDERGROUND TRENCHING BLANKET | A3 | 1.3 | 4.3 | 1.2 | 6.2 | 3.3 | 1.1
D550FX | 51-2083 | URD & ST - LGTS POLO COURT SUB, SUF | AP | 0 | 0 | 0 | 0 | 13.8 | 6.6
D550FX | 50-0616 | UNDERGROUND TRENCHING BLANKET | A4 | 2 | 6.6 | 1.8 | 9.2 | 5 | 1.5
D550FX | 51-2349 | URD JOON MANAGEMENT 1, AMONA CT, MO | AP | 0 | 0 | 0 | 9 | -1.1 | 19.1
D550FX | 50-0616 | UNDERGROUND TRENCHING BLANKET | AP | 5.6 | 7.1 | 4.2 | -0.3 | 38.3 | 0.6
D551FX | 50-0626 | UNDERGROUND CONDUIT BLANKET | MS | 0 | 0 | 0 | 0 | 0 | 0.1
D552FX | 51-2382 | URD HIDDEN CREEK CONDOS SECT-2, MON | CC | 0 | 0 | 0.1 | 0 | 0 | 0
D552FX | 51-2423 | URD JB ENTERPRISE, 2 SUNRISE DR, MO | PR | 0 | 0 | 0 | 0 | 0 | 0.1
D552FX | 51-2454 | URD SHLOIMY TAUBER, CALVERT DR, MON | A3 | 0 | 0 | 0 | 0 | 0 | 0.1
D552FX | 51-2288 | URD KOHL INDUSTRIAL PK, N RTE 303, | CC | 0 | 0.1 | 0 | 0 | 0 | 0
D552FX | 51-1323 | URD-AIRMONT PROFESSIONAL CTR, AIRMO | CC | 0 | 0.1 | 0 | 0 | 0 | 0
D552FX | 51-2455 | URD SKI SIDE VILLA, KATRINA CT, TUX | CC | 0 | 0 | 0 | 0 | 0.1 | 0
D552FX | 51-2456 | URD DOROTHY JORDAN, ACKERTOWN RD, C | A3 | 0 | 0 | 0 | 0 | 0 | 0.1
D552FX | 51-2083 | URD & ST - LGTS POLO COURT SUB, SUF | CC | 0 | 0 | 0 | 0 | 0.1 | 0
D552FX | 51-2388 | URD TAMMY FLANNERY, DEER POND DRIVE | A3 | 0 | 0 | 0.1 | 0 | 0 | 0
D552FX | 51-2288 | URD KOHL INDUSTRIAL PK, N RTE 303, | A3 | 0 | 0.1 | 0 | 0 | 0 | 0
D552FX | 51-1323 | URD-AIRMONT PROFESSIONAL CTR, AIRMO | A3 | 0 | 0.1 | 0 | 0 | 0 | 0
D552FX | 51-2378 | URD MADISON PARK CONDOMINIUMS, SPRI | CC | 0 | 0 | 0 | 0 | 0.1 | 0
D552FX | 51-2454 | URD SHLOIMY TAUBER, CALVERT DR, MON | A4 | 0 | 0 | 0 | 0 | 0 | 0.1
D552FX | 51-2383 | URD HIDDEN CRK CONDOS SECT-3, MONRO | CC | 0 | 0 | 0.1 | 0 | 0 | 0
D552FX | 51-2361 | URD CARRIAGE PARK, WEST MAIN ST, GO | PR | 0.2 | -0.1 | 0 | 0 | 0 | 0
D552FX | 51-2083 | URD & ST - LGTS POLO COURT SUB, SUF | A3 | 0 | 0 | 0 | 0 | 0.1 | 0
D552FX | 51-2423 | URD JB ENTERPRISE, 2 SUNRISE DR, MO | A3 | 0 | 0 | 0 | 0 | 0 | 0.1
D552FX | 51-2425 | PINES HOMES CORP, VINCENT RD, SPRIN | PR | 0 | 0 | 0 | 0 | 0 | 0.1
D552FX | 51-2378 | URD MADISON PARK CONDOMINIUMS, SPRI | A3 | 0 | 0 | 0 | 0 | 0.1 | 0
D552FX | 51-2277 | URD ALBERT WISNER PUBLIC LIBRARY, W | A4 | 0.1 | 0 | 0 | 0 | 0 | 0
D552FX | 51-2325 | URD HORIZONS AT WAWAYANDA-SECT 2, H | A3 | 0.1 | 0 | 0 | 0 | 0 | 0
D552FX | 51-2325 | URD HORIZONS AT WAWAYANDA-SECT 2, H | A4 | 0.1 | 0 | 0 | 0 | 0 | 0
D552FX | 51-2319 | URD HORIZONS AT WAWAYANDA, HORIZONS | PR | 0.2 | 0 | 0 | 0 | 0 | 0
D552FX | 51-2456 | URD DOROTHY JORDAN, ACKERTOWN RD, C | A4 | 0 | 0 | 0 | 0 | 0 | 0.2
D552FX | 51-2092 | URD/ST. LGTS WILLOWS SUB., WESLEY H | CC | 0.2 | 0 | 0 | 0 | 0 | 0
D552FX | 51-2349 | URD JOON MANAGEMENT 1, AMONA CT, MO | CC | 0 | 0 | 0 | 0 | 0.2 | 0
D552FX | 51-2388 | URD TAMMY FLANNERY, DEER POND DRIVE | AP | 0 | 0 | 0 | 0 | 0.2 | 0
D552FX | 51-2388 | URD TAMMY FLANNERY, DEER POND DRIVE | A4 | 0 | 0 | 0.2 | 0 | 0 | 0
D552FX | 51-2465 | URD WOODSIDE KNOLLS - PH V, MIDDLET | CC | 0 | 0 | 0 | 0 | 0 | 0.2
D552FX | 51-2248 | URD FAIRWAYS SECT-3, EAGLES WAY, WA | PR | 0.2 | 0 | 0 | 0 | 0 | 0
D552FX | 51-2319 | URD HORIZONS AT WAWAYANDA, HORIZONS | A3 | 0.2 | 0 | 0 | 0 | 0 | 0
D552FX | 51-2260 | URD BREEZY KNOLLS ESTATES PART 2, U | PR | 0.5 | -0.3 | 0 | 0 | 0 | 0
D552FX | 51-2435 | URD WOODSIDE KNOLLS DRIVE, MIDDLETO | CC | 0 | 0 | 0 | 0.3 | 0 | 0
D552FX | 51-2349 | URD JOON MANAGEMENT 1, AMONA CT, MO | A3 | 0 | 0 | 0 | 0 | 0.3 | 0
D552FX | 51-2381 | URD COUNTRY COMFORT HOMES CORP, MID | MS | 0.3 | 0 | 0 | 0 | 0 | 0
D552FX | 51-2454 | URD SHLOIMY TAUBER, CALVERT DR, MON | MS | 0 | 0 | 0 | 0 | 0 | 0.3
D552FX | 51-2423 | URD JB ENTERPRISE, 2 SUNRISE DR, MO | MS | 0 | 0 | 0 | 0.3 | 0 | 0
D552FX | 51-2083 | URD & ST - LGTS POLO COURT SUB, SUF | A4 | 0 | 0 | 0 | 0 | 0.3 | 0
D552FX | 51-2288 | URD KOHL INDUSTRIAL PK, N RTE 303, | A4 | 0 | 0.3 | 0 | 0 | 0 | 0
D552FX | 51-2435 | URD WOODSIDE KNOLLS DRIVE, MIDDLETO | PR | 0 | 0 | 0 | 0.5 | -0.2 | 0
D552FX | 51-1323 | URD-AIRMONT PROFESSIONAL CTR, AIRMO | A4 | 0 | 0.3 | 0 | 0 | 0 | 0
D552FX | 51-2319 | URD HORIZONS AT WAWAYANDA, HORIZONS | A4 | 0.3 | 0 | 0 | 0 | 0 | 0
D552FX | 51-2248 | URD FAIRWAYS SECT-3, EAGLES WAY, WA | A3 | 0.3 | 0 | 0 | 0 | 0 | 0
D552FX | 51-2423 | URD JB ENTERPRISE, 2 SUNRISE DR, MO | A4 | 0 | 0 | 0 | 0.1 | 0 | 0.2
D552FX | 51-2381 | URD COUNTRY COMFORT HOMES CORP, MID | PR | 0.2 | 0.1 | 0 | 0 | 0 | 0
D552FX | 51-2361 | URD CARRIAGE PARK, WEST MAIN ST, GO | A3 | 0.4 | -0.1 | 0 | 0 | 0 | 0
D552FX | 51-2405 | URD/ST.LGT - BAKERTOWN RD CONDO'S P | CC | 0 | 0.4 | 0 | 0 | 0 | 0
D552FX | 51-2425 | PINES HOMES CORP, VINCENT RD, SPRIN | A3 | 0 | 0 | 0 | 0.1 | 0.1 | 0.2
D552FX | 51-2378 | URD MADISON PARK CONDOMINIUMS, SPRI | A4 | 0 | 0 | 0 | 0 | 0.3 | 0.1
D552FX | 51-2455 | URD SKI SIDE VILLA, KATRINA CT, TUX | PR | 0 | 0 | 0 | 0 | 0.4 | 0
D552FX | 51-2092 | URD/ST. LGTS WILLOWS SUB., WESLEY H | A3 | 0.4 | 0 | 0 | 0 | 0 | 0
D552FX | 51-2381 | URD COUNTRY COMFORT HOMES CORP, MID | A3 | 0.3 | 0.1 | 0 | 0 | 0 | 0
D552FX | 51-2388 | URD TAMMY FLANNERY, DEER POND DRIVE | MS | 0 | 0 | 0.4 | 0 | 0 | 0
D552FX | 51-2456 | URD DOROTHY JORDAN, ACKERTOWN RD, C | MS | 0 | 0 | 0 | 0 | 0 | 0.4
D552FX | 54-0636 | UNDERGROUND BOX PADS BLANKET | PR | 0 | 0.5 | -0.1 | 0 | 0 | 0
D552FX | 51-2248 | URD FAIRWAYS SECT-3, EAGLES WAY, WA | A4 | 0.4 | 0 | 0 | 0 | 0 | 0
D552FX | 51-2361 | URD CARRIAGE PARK, WEST MAIN ST, GO | A4 | 0.7 | -0.2 | 0 | 0 | 0 | 0
D552FX | 51-2405 | URD/ST.LGT - BAKERTOWN RD CONDO'S P | A3 | 0 | 0.5 | 0 | 0 | 0 | 0
D552FX | 51-2425 | PINES HOMES CORP, VINCENT RD, SPRIN | MS | 0 | 0 | 0 | 0.5 | 0 | 0
D552FX | 51-2288 | URD KOHL INDUSTRIAL PK, N RTE 303, | AP | 0 | 0 | 0 | 0.3 | 0.2 | 0
D552FX | 51-2382 | URD HIDDEN CREEK CONDOS SECT-2, MON | PR | 0 | 0 | 0 | 0.6 | -0.1 | 0
D552FX | 51-2425 | PINES HOMES CORP, VINCENT RD, SPRIN | A4 | 0 | 0 | 0 | 0.1 | 0.1 | 0.3
D552FX | 51-2361 | URD CARRIAGE PARK, WEST MAIN ST, GO | MS | 0.5 | 0 | 0 | 0 | 0 | 0
D552FX | 51-2260 | URD BREEZY KNOLLS ESTATES PART 2, U | A3 | 0.8 | -0.5 | 0 | 0 | 0 | 0.2
D552FX | 51-2465 | URD WOODSIDE KNOLLS - PH V, MIDDLET | A3 | 0 | 0 | 0 | 0 | 0 | 0.6
D552FX | 51-2423 | URD JB ENTERPRISE, 2 SUNRISE DR, MO | AP | 0 | 0 | 0 | 0 | 0.3 | 0.3
D552FX | 51-2382 | URD HIDDEN CREEK CONDOS SECT-2, MON | MS | 0 | 0 | 0.6 | 0 | 0 | 0
D552FX | 51-2383 | URD HIDDEN CRK CONDOS SECT-3, MONRO | PR | 0 | 0 | 0 | 0.6 | 0 | 0
D552FX | 51-2277 | URD ALBERT WISNER PUBLIC LIBRARY, W | AP | 0 | 0 | 0 | 0 | 0.6 | 0
D552FX | 51-2349 | URD JOON MANAGEMENT 1, AMONA CT, MO | A4 | 0 | 0 | 0 | 0 | 0.6 | 0
D552FX | 51-2381 | URD COUNTRY COMFORT HOMES CORP, MID | A4 | 0.5 | 0.1 | 0 | 0 | 0 | 0
D552FX | 54-0636 | UNDERGROUND BOX PADS BLANKET | A3 | 0 | 0.7 | -0.2 | 0.1 | 0 | 0
D552FX | 51-2455 | URD SKI SIDE VILLA, KATRINA CT, TUX | A3 | 0 | 0 | 0 | 0 | 0.6 | 0.1
D552FX | 51-2425 | PINES HOMES CORP, VINCENT RD, SPRIN | AP | 0 | 0 | 0 | 0 | 0.7 | 0
D552FX | 51-2260 | URD BREEZY KNOLLS ESTATES PART 2, U | A4 | 1.2 | -0.7 | 0 | 0 | 0 | 0.2
D552FX | 51-2435 | URD WOODSIDE KNOLLS DRIVE, MIDDLETO | A3 | 0 | 0 | 0 | 1.2 | -0.3 | 0
D552FX | 51-2382 | URD HIDDEN CREEK CONDOS SECT-2, MON | A3 | 0 | 0 | 0.1 | 0.9 | -0.1 | 0
D552FX | 51-2288 | URD KOHL INDUSTRIAL PK, N RTE 303, | MS | 0 | 0.9 | 0 | 0 | 0 | 0
D552FX | 51-2092 | URD/ST. LGTS WILLOWS SUB., WESLEY H | A4 | 0.9 | 0 | 0 | 0 | 0 | 0
D552FX | 51-1323 | URD-AIRMONT PROFESSIONAL CTR, AIRMO | MS | 0 | 0.9 | 0.1 | 0 | 0 | 0
D552FX | 51-1323 | URD-AIRMONT PROFESSIONAL CTR, AIRMO | AP | 0 | 0 | 0 | 0 | 1 | 0
D552FX | 51-2283 | URD BOYLE SUBDIVISION, TERRACE LN, | AP | 1 | 0 | 0 | 0 | 0 | 0
D552FX | 51-2455 | URD SKI SIDE VILLA, KATRINA CT, TUX | MS | 0 | 0 | 0 | 0 | 1 | 0
D552FX | 54-0636 | UNDERGROUND BOX PADS BLANKET | A4 | 0 | 1.1 | -0.3 | 0.1 | 0.1 | 0
D552FX | 51-2326 | URD BESIATA DESHMAYA LLC, MERON DR, | AP | 0.3 | 0.8 | 0 | 0 | 0 | 0
D552FX | 50-0636 | UNDERGROUND BOX PADS BLANKET | CC | 0.1 | 0.1 | 0.1 | 0.6 | 0.2 | 0
D552FX | 51-2465 | URD WOODSIDE KNOLLS - PH V, MIDDLET | A4 | 0 | 0 | 0 | 0 | 0 | 1.2
D552FX | 51-2455 | URD SKI SIDE VILLA, KATRINA CT, TUX | A4 | 0 | 0 | 0 | 0 | 1.1 | 0.1
D552FX | 51-2383 | URD HIDDEN CRK CONDOS SECT-3, MONRO | A3 | 0 | 0 | 0.3 | 1 | 0 | 0
D552FX | 51-2083 | URD & ST - LGTS POLO COURT SUB, SUF | MS | 0 | 0 | 0 | 0 | 1.3 | 0
D552FX | 51-2382 | URD HIDDEN CREEK CONDOS SECT-2, MON | A4 | 0 | 0 | 0.3 | 1.4 | -0.2 | 0
D552FX | 51-2378 | URD MADISON PARK CONDOMINIUMS, SPRI | MS | 0 | 0 | 0 | 0 | 1.3 | 0.2
D552FX | 51-2083 | URD & ST - LGTS POLO COURT SUB, SUF | AP | 0 | 0 | 0 | 0 | 0 | 1.5
D552FX | 51-2405 | URD/ST.LGT - BAKERTOWN RD CONDO'S P | A4 | 0 | 1.5 | 0 | 0 | 0 | 0
D552FX | 51-2383 | URD HIDDEN CRK CONDOS SECT-3, MONRO | MS | 0 | 0 | 1.6 | 0 | 0 | 0
D552FX | 51-2435 | URD WOODSIDE KNOLLS DRIVE, MIDDLETO | A4 | 0 | 0 | 0 | 2.2 | -0.4 | 0
D552FX | 51-2383 | URD HIDDEN CRK CONDOS SECT-3, MONRO | A4 | 0 | 0 | 0.6 | 1.4 | 0 | 0
D552FX | 51-2092 | URD/ST. LGTS WILLOWS SUB., WESLEY H | MS | 2.2 | 0 | 0 | 0 | 0 | 0
D552FX | 51-2349 | URD JOON MANAGEMENT 1, AMONA CT, MO | MS | 0 | 0 | 0 | 0 | 2.6 | 0
D552FX | 51-2349 | URD JOON MANAGEMENT 1, AMONA CT, MO | AP | 0 | 0 | 0 | 0 | 0 | 2.8
D552FX | 50-0636 | UNDERGROUND BOX PADS BLANKET | PR | 0.4 | 0.6 | 0 | 1.1 | 0.5 | 0.2
D552FX | 51-2465 | URD WOODSIDE KNOLLS - PH V, MIDDLET | MS | 0 | 0 | 0 | 0 | 0 | 3
D552FX | 51-2435 | URD WOODSIDE KNOLLS DRIVE, MIDDLETO | MS | 0 | 0 | 0 | 3.5 | 0 | 0
D552FX | 51-2405 | URD/ST.LGT - BAKERTOWN RD CONDO'S P | MS | 0 | 4.4 | 0 | 0 | 0 | 0
D552FX | 50-0636 | UNDERGROUND BOX PADS BLANKET | A3 | 0.8 | 1 | 0.2 | 2.6 | 1.1 | 0.4
D552FX | 50-0636 | UNDERGROUND BOX PADS BLANKET | A4 | 1.3 | 1.8 | 0.4 | 4.6 | 1.9 | 0.6
D552FX | 50-0636 | UNDERGROUND BOX PADS BLANKET | AP | 0.8 | 0 | 2.9 | 0.8 | 2.7 | 4.5
D552FX | 50-0636 | UNDERGROUND BOX PADS BLANKET | MS | 1.2 | 1.5 | 1.1 | 7.4 | 2.9 | 0.4
D552FX | 51-2260 | URD BREEZY KNOLLS ESTATES PART 2, U | AP | 0 | 0 | 0 | 0 | 0 | 30.7
D553FX | 50-0646 | UNDERGROUND PRIMARY CONDUCTOR BLANK | CC | -13.9 | 0.2 | 0.5 | -22.6 | 1.4 | -5
D553FX | 51-2260 | URD BREEZY KNOLLS ESTATES PART 2, U | CC | 0 | 0 | 0 | 0 | -18.2 | 0
D553FX | 51-2248 | URD FAIRWAYS SECT-3, EAGLES WAY, WA | CC | 0 | 0 | 0 | 0 | -10.7 | 0
D553FX | 51-2319 | URD HORIZONS AT WAWAYANDA, HORIZONS | CC | 0 | 0 | 0 | -3.6 | 0 | 0
D553FX | 51-2383 | URD HIDDEN CRK CONDOS SECT-3, MONRO | CC | 0 | 0 | 0.2 | 0.1 | 0 | -2.6
D553FX | 51-2388 | URD TAMMY FLANNERY, DEER POND DRIVE | CC | 0 | 0 | 0.1 | 0 | -2.3 | 0
D553FX | 51-2405 | URD/ST.LGT - BAKERTOWN RD CONDO'S P | CC | 0.1 | 0.5 | 0 | 0 | 0 | -2.2
D553FX | 51-1675 | URD & ST.LTG. RIVER RIDGE EST, S, N | MS | 0 | 0 | 0 | 0 | -1.3 | 0
D553FX | 51-2318 | URD RESTORATIVE ESTATES I-A, MAPES | CC | 0 | 0 | 0 | -1.1 | 0 | 0
D553FX | 51-2382 | URD HIDDEN CREEK CONDOS SECT-2, MON | CC | 0 | 0 | 0.1 | 0 | 0 | -1.1
D553FX | 51-2323 | URD SERGEI LOPUCHIN, CHRISTIAN HERA | CC | 0 | 0 | 0 | 0 | 0 | -0.8
D553FX | 51-2354 | URD BEN VELTIDI, 4 LINDA DR., SUFFE | CC | 0 | 0 | 0 | -0.8 | 0 | 0
D553FX | 51-2321 | URD SMK HOME BLDRS INC., OLD TAPPAN | CC | -0.7 | 0 | 0 | 0 | 0 | 0
D553FX | 51-2423 | URD JB ENTERPRISE, 2 SUNRISE DR, MO | CC | 0 | 0 | 0 | 0.1 | 0 | -0.6
D553FX | 51-2360 | URD BARBARA PEPEYRA, STEGMEYER LN., | CC | 0 | 0 | 0 | 0 | -0.5 | 0
D553FX | 51-1936 | URD-CALICO HILLS, W RAILROAD AV, GA | CC | 0 | -0.5 | 0 | 0 | 0 | 0
D553FX | 51-1675 | URD & ST.LTG. RIVER RIDGE EST, S, N | CC | 0 | 0 | 0 | 0 | -0.1 | 0
D553FX | 51-1675 | URD & ST.LTG. RIVER RIDGE EST, S, N | A3 | 0.3 | -0.2 | 0 | 0 | -0.1 | 0
D553FX | 51-2380 | URD PINE LAKE ESTATES, MASTEN LAKE | CC | 0.1 | 0 | 0 | 0 | 0 | 0
D553FX | 54-2382 | URD HIDDEN CREEK CONDOS SECT-2, MON | A3 | 0 | 0 | 0 | 0.1 | 0 | 0
D553FX | 51-2456 | URD DOROTHY JORDAN, ACKERTOWN RD, C | CC | 0 | 0 | 0 | 0 | 0 | 0.1
D553FX | 54-2382 | URD HIDDEN CREEK CONDOS SECT-2, MON | A4 | 0 | 0 | 0 | 0.1 | 0 | 0
D553FX | 51-1593 | URD FAIRWAYS WALLKILL III, GOLF LIN | A3 | 0 | 0 | 0 | 0 | 0 | 0.1
D553FX | 51-2466 | URD SUNRISE HILLS - SECTION A, MIDD | CC | 0 | 0 | 0 | 0 | 0 | 0.1
D553FX | 51-2354 | URD BEN VELTIDI, 4 LINDA DR., SUFFE | A3 | 0.1 | 0 | 0 | 0 | 0 | 0
D553FX | 51-2454 | URD SHLOIMY TAUBER, CALVERT DR, MON | CC | 0 | 0 | 0 | 0 | 0 | 0.1
D553FX | 51-1593 | URD FAIRWAYS WALLKILL III, GOLF LIN | A4 | 0 | 0 | 0 | 0 | 0 | 0.1
D553FX | 51-2493 | BAKERTOWN RD CONDO'S SEC 3 - KIRYAS | A3 | 0 | 0 | 0 | 0 | 0 | 0.1
D553FX | 51-2380 | URD PINE LAKE ESTATES, MASTEN LAKE | A3 | 0.1 | 0 | 0 | 0 | 0 | 0
D553FX | 51-2425 | PINES HOMES CORP, VINCENT RD, SPRIN | CC | 0 | 0 | 0 | 0.1 | 0 | 0
D553FX | 51-2360 | URD BARBARA PEPEYRA, STEGMEYER LN., | A3 | 0.1 | 0 | 0 | 0 | 0 | 0
D553FX | 51-1675 | URD & ST.LTG. RIVER RIDGE EST, S, N | PR | 0.2 | -0.1 | 0 | 0 | 0 | 0
D553FX | 51-2381 | URD COUNTRY COMFORT HOMES CORP, MID | CC | 0.1 | 0 | 0 | 0 | 0 | 0
D553FX | 51-2323 | URD SERGEI LOPUCHIN, CHRISTIAN HERA | A4 | 0 | 0 | 0.1 | 0 | 0 | 0
D553FX | 51-2363 | URD ZARA CROWLEY, CASTLE HGTS AV, U | A3 | 0 | 0 | 0.1 | 0 | 0 | 0
D553FX | 51-2277 | URD ALBERT WISNER PUBLIC LIBRARY, W | MS | 0.1 | 0 | 0 | 0 | 0 | 0
D553FX | 51-2325 | URD HORIZONS AT WAWAYANDA-SECT 2, H | PR | 0.2 | 0 | 0 | 0 | 0 | 0
D553FX | 51-1323 | URD-AIRMONT PROFESSIONAL CTR, AIRMO | CC | 0 | 0.2 | 0 | 0 | 0 | 0
D553FX | 51-2456 | URD DOROTHY JORDAN, ACKERTOWN RD, C | A3 | 0 | 0 | 0 | 0 | 0 | 0.2
D553FX | 51-2354 | URD BEN VELTIDI, 4 LINDA DR., SUFFE | A4 | 0.2 | 0 | 0 | 0 | 0 | 0
D553FX | 51-2493 | BAKERTOWN RD CONDO'S SEC 3 - KIRYAS | A4 | 0 | 0 | 0 | 0 | 0 | 0.2
D553FX | 51-2360 | URD BARBARA PEPEYRA, STEGMEYER LN., | A4 | 0.2 | 0 | 0 | 0 | 0 | 0
D553FX | 51-2454 | URD SHLOIMY TAUBER, CALVERT DR, MON | A3 | 0 | 0 | 0 | 0 | 0 | 0.2
D553FX | 51-1323 | URD-AIRMONT PROFESSIONAL CTR, AIRMO | A3 | 0 | 0.2 | 0 | 0 | 0 | 0
D553FX | 51-2466 | URD SUNRISE HILLS - SECTION A, MIDD | A3 | 0 | 0 | 0 | 0 | 0 | 0.2
D553FX | 51-2325 | URD HORIZONS AT WAWAYANDA-SECT 2, H | A3 | 0.2 | 0 | 0 | 0 | 0 | 0
D553FX | 51-2424 | URD S V SENIOR APTS., N. MAIN ST, S | CC | 0 | 0 | 0 | 0.3 | 0 | 0
D553FX | 51-2323 | URD SERGEI LOPUCHIN, CHRISTIAN HERA | MS | 0 | 0 | 0.3 | 0 | 0 | 0
D553FX | 51-2465 | URD WOODSIDE KNOLLS - PH V, MIDDLET | CC | 0 | 0 | 0 | 0 | 0 | 0.3
D553FX | 51-2380 | URD PINE LAKE ESTATES, MASTEN LAKE | A4 | 0.3 | 0 | 0 | 0 | 0 | 0
D553FX | 51-2354 | URD BEN VELTIDI, 4 LINDA DR., SUFFE | MS | 0.3 | 0 | 0 | 0 | 0 | 0
D553FX | 51-2360 | URD BARBARA PEPEYRA, STEGMEYER LN., | MS | 0.3 | 0 | 0 | 0 | 0 | 0
D553FX | 51-2354 | URD BEN VELTIDI, 4 LINDA DR., SUFFE | AP | 0 | 0.3 | 0 | 0 | 0 | 0
D553FX | 51-2456 | URD DOROTHY JORDAN, ACKERTOWN RD, C | A4 | 0 | 0 | 0 | 0 | 0 | 0.3
D553FX | 51-2378 | URD MADISON PARK CONDOMINIUMS, SPRI | PR | 0 | 0 | 0 | 0 | 0 | 0.3
D553FX | 51-2361 | URD CARRIAGE PARK, WEST MAIN ST, GO | CC | 0.3 | 0 | 0 | 0 | 0 | 0
D553FX | 51-2325 | URD HORIZONS AT WAWAYANDA-SECT 2, H | A4 | 0.3 | 0 | 0 | 0 | 0 | 0
D553FX | 51-2378 | URD MADISON PARK CONDOMINIUMS, SPRI | CC | 0 | 0 | 0 | 0 | 0.2 | 0.1
D553FX | 51-2424 | URD S V SENIOR APTS., N. MAIN ST, S | A3 | 0 | 0 | 0 | 0.4 | 0 | 0
D553FX | 51-2083 | URD & ST - LGTS POLO COURT SUB, SUF | CC | 0 | 0 | 0 | 0 | 0.3 | 0.1
D553FX | 51-2363 | URD ZARA CROWLEY, CASTLE HGTS AV, U | A4 | 0 | 0.1 | 0.2 | 0.1 | 0 | 0
D553FX | 51-2423 | URD JB ENTERPRISE, 2 SUNRISE DR, MO | PR | 0 | 0 | 0 | 0 | 0 | 0.4
D553FX | 51-2455 | URD SKI SIDE VILLA, KATRINA CT, TUX | CC | 0 | 0 | 0 | 0 | 0.4 | 0
D553FX | 51-2454 | URD SHLOIMY TAUBER, CALVERT DR, MON | A4 | 0 | 0 | 0 | 0 | 0 | 0.4
D553FX | 51-2466 | URD SUNRISE HILLS - SECTION A, MIDD | A4 | 0 | 0 | 0 | 0 | 0 | 0.4
D553FX | 51-2260 | URD BREEZY KNOLLS ESTATES PART 2, U | PR | 1.4 | -0.9 | 0 | 0 | 0 | 0
D553FX | 51-2277 | URD ALBERT WISNER PUBLIC LIBRARY, W | PR | 0.7 | -0.2 | 0 | 0 | 0 | 0
D553FX | 51-2288 | URD KOHL INDUSTRIAL PK, N RTE 303, | CC | 0 | 0.6 | -0.2 | 0.1 | 0 | 0
D553FX | 51-2384 | URD HIDDEN CRK CONDOS SECT-3, MONRO | CC | 0.1 | 0 | 0 | 0.4 | 0 | 0
D553FX | 51-2493 | BAKERTOWN RD CONDO'S SEC 3 - KIRYAS | MS | 0 | 0 | 0 | 0 | 0 | 0.5
D553FX | 51-2435 | URD WOODSIDE KNOLLS DRIVE, MIDDLETO | CC | 0 | 0 | 0 | 0.6 | 0 | 0
D553FX | 51-2349 | URD JOON MANAGEMENT 1, AMONA CT, MO | CC | 0 | 0 | 0 | 0 | 0.5 | 0.1
D553FX | 51-2092 | URD/ST. LGTS WILLOWS SUB., WESLEY H | CC | 0.5 | 0.1 | 0 | 0 | 0 | 0
D553FX | 51-2248 | URD FAIRWAYS SECT-3, EAGLES WAY, WA | PR | 0.6 | 0 | 0 | 0 | 0 | 0
D553FX | 51-2380 | URD PINE LAKE ESTATES, MASTEN LAKE | MS | 0.7 | 0 | 0 | 0 | 0 | 0
D553FX | 51-2465 | URD WOODSIDE KNOLLS - PH V, MIDDLET | A3 | 0 | 0 | 0 | 0 | 0 | 0.7
D553FX | 51-2319 | URD HORIZONS AT WAWAYANDA, HORIZONS | PR | 0.7 | 0 | 0 | 0 | 0 | 0
D553FX | 51-1323 | URD-AIRMONT PROFESSIONAL CTR, AIRMO | A4 | 0 | 0.7 | 0 | 0 | 0 | 0
D553FX | 51-2083 | URD & ST - LGTS POLO COURT SUB, SUF | PR | 0 | 0 | 0 | 0 | 0 | 0.7
D553FX | 51-2277 | URD ALBERT WISNER PUBLIC LIBRARY, W | A3 | 1 | -0.3 | 0 | 0 | 0 | 0
D553FX | 51-2260 | URD BREEZY KNOLLS ESTATES PART 2, U | A3 | 1.9 | -1.2 | 0 | 0 | 0 | 0
D553FX | 51-2384 | URD HIDDEN CRK CONDOS SECT-3, MONRO | A3 | 0.2 | 0 | 0 | 0.6 | 0 | 0
D553FX | 51-2363 | URD ZARA CROWLEY, CASTLE HGTS AV, U | MS | 0 | 0.3 | 0.3 | 0 | 0.2 | 0
D553FX | 51-1323 | URD-AIRMONT PROFESSIONAL CTR, AIRMO | AP | 0 | 2 | -2 | 0 | 0.8 | 0
D553FX | 51-2424 | URD S V SENIOR APTS., N. MAIN ST, S | A4 | 0 | 0 | 0 | 0.9 | -0.1 | 0
D553FX | 51-2388 | URD TAMMY FLANNERY, DEER POND DRIVE | AP | 0 | 0 | 0 | 0 | 0.8 | 0
D553FX | 51-2388 | URD TAMMY FLANNERY, DEER POND DRIVE | A3 | 0.1 | 0.1 | 0.6 | 0 | 0 | 0
D553FX | 51-2248 | URD FAIRWAYS SECT-3, EAGLES WAY, WA | A3 | 0.8 | 0 | 0 | 0 | 0 | 0
D553FX | 51-2456 | URD DOROTHY JORDAN, ACKERTOWN RD, C | MS | 0 | 0 | 0 | 0 | 0 | 0.9
D553FX | 51-2381 | URD COUNTRY COMFORT HOMES CORP, MID | AP | 0 | 0.9 | -0.9 | 0 | 0.9 | 0
D553FX | 51-2423 | URD JB ENTERPRISE, 2 SUNRISE DR, MO | A3 | 0 | 0 | 0 | 0.1 | 0 | 0.8
D553FX | 51-2319 | URD HORIZONS AT WAWAYANDA, HORIZONS | A3 | 1 | 0 | 0 | 0 | 0 | 0
D553FX | 51-2425 | PINES HOMES CORP, VINCENT RD, SPRIN | PR | 0 | 0 | 0 | 0 | 0.3 | 0.8
D553FX | 51-2378 | URD MADISON PARK CONDOMINIUMS, SPRI | A3 | 0 | 0 | 0 | 0 | 0.3 | 0.8
D553FX | 51-2454 | URD SHLOIMY TAUBER, CALVERT DR, MON | MS | 0 | 0 | 0 | 0 | 0 | 1.1
D553FX | 51-2466 | URD SUNRISE HILLS - SECTION A, MIDD | MS | 0 | 0 | 0 | 0 | 0 | 1.1
D553FX | 51-2092 | URD/ST. LGTS WILLOWS SUB., WESLEY H | PR | 0 | 1.1 | 0 | 0 | 0 | 0
D553FX | 51-2277 | URD ALBERT WISNER PUBLIC LIBRARY, W | A4 | 1.6 | -0.5 | 0 | 0 | 0 | 0
D553FX | 51-2260 | URD BREEZY KNOLLS ESTATES PART 2, U | A4 | 3 | -1.9 | 0 | 0 | 0 | 0
D553FX | 51-2349 | URD JOON MANAGEMENT 1, AMONA CT, MO | PR | 0 | 0 | 0 | 0 | 0 | 1.3
D553FX | 51-2465 | URD WOODSIDE KNOLLS - PH V, MIDDLET | A4 | 0 | 0 | 0 | 0 | 0 | 1.3
D553FX | 51-2423 | URD JB ENTERPRISE, 2 SUNRISE DR, MO | MS | 0 | 0 | 0 | 0.8 | 0 | 0.5
D553FX | 51-2285 | URD ROBERT RINO, 20 VIOLA RD, MONTE | AP | 1.3 | 0 | 0 | 0 | 0 | 0
D553FX | 51-2248 | URD FAIRWAYS SECT-3, EAGLES WAY, WA | A4 | 1.3 | 0 | 0 | 0 | 0 | 0
D553FX | 51-2318 | URD RESTORATIVE ESTATES I-A, MAPES | AP | 0 | 0 | 0 | 0 | 0 | 1.4
D553FX | 51-2423 | URD JB ENTERPRISE, 2 SUNRISE DR, MO | A4 | 0 | 0 | 0 | 0.2 | 0 | 1.2
D553FX | 51-2405 | URD/ST.LGT - BAKERTOWN RD CONDO'S P | PR | 0 | 0 | 1.8 | -0.4 | 0 | 0
D553FX | 51-2363 | URD ZARA CROWLEY, CASTLE HGTS AV, U | AP | 0 | 0 | 0.3 | 0 | 1.1 | 0
D553FX | 51-2425 | PINES HOMES CORP, VINCENT RD, SPRIN | MS | 0 | 0 | 0 | 1.1 | 0.4 | 0
D553FX | 51-2319 | URD HORIZONS AT WAWAYANDA, HORIZONS | A4 | 1.5 | 0 | 0 | 0 | 0 | 0
D553FX | 51-2388 | URD TAMMY FLANNERY, DEER POND DRIVE | MS | 0 | 0 | 1.6 | 0 | 0 | 0
D553FX | 51-2383 | URD HIDDEN CRK CONDOS SECT-3, MONRO | PR | 0 | 0 | 0 | 1.6 | 0 | 0
D553FX | 51-2435 | URD WOODSIDE KNOLLS DRIVE, MIDDLETO | PR | 0 | 0 | 0 | 2.5 | -0.8 | 0
D553FX | 51-2381 | URD COUNTRY COMFORT HOMES CORP, MID | MS | 1.7 | 0 | 0 | 0 | 0 | 0
D553FX | 54-0646 | UNDERGROUND PRIMARY CONDUCTOR BLANK | AP | 0 | 0 | 0 | 0 | 1.7 | 0
D553FX | 51-2384 | URD HIDDEN CRK CONDOS SECT-3, MONRO | A4 | 0.4 | 0 | 0 | 1.3 | 0 | 0
D553FX | 51-2382 | URD HIDDEN CREEK CONDOS SECT-2, MON | MS | 0.2 | 0 | 1.1 | 0.4 | 0 | 0
D553FX | 51-2381 | URD COUNTRY COMFORT HOMES CORP, MID | PR | 1.3 | 0.5 | 0 | 0 | 0 | 0
D553FX | 51-2423 | URD JB ENTERPRISE, 2 SUNRISE DR, MO | AP | 0 | 0 | 0 | 0 | 0 | 1.8
D553FX | 51-2378 | URD MADISON PARK CONDOMINIUMS, SPRI | A4 | 0 | 0 | 0 | 0 | 0.7 | 1.1
D553FX | 51-2455 | URD SKI SIDE VILLA, KATRINA CT, TUX | PR | 0 | 0 | 0 | 0 | 1.7 | 0.1
D553FX | 51-2083 | URD & ST - LGTS POLO COURT SUB, SUF | A3 | 0 | 0 | 0 | 0 | 0.4 | 1.5
D553FX | 51-2288 | URD KOHL INDUSTRIAL PK, N RTE 303, | PR | 0 | 0 | 0 | 0 | 3.7 | -1.8
D553FX | 51-2382 | URD HIDDEN CREEK CONDOS SECT-2, MON | PR | 0 | 0 | 0 | 2.2 | -0.3 | 0
D553FX | 51-2388 | URD TAMMY FLANNERY, DEER POND DRIVE | PR | 1.1 | 0.6 | 0.3 | 0 | 0 | 0
D553FX | 51-1323 | URD-AIRMONT PROFESSIONAL CTR, AIRMO | MS | 0 | 2.1 | 0 | 0 | 0 | 0
D553FX | 51-2425 | PINES HOMES CORP, VINCENT RD, SPRIN | A3 | 0 | 0 | 0 | 0.1 | 0.5 | 1.5
D553FX | 51-2424 | URD S V SENIOR APTS., N. MAIN ST, S | MS | 0 | 0 | 0 | 3.1 | -0.6 | 0
D553FX | 51-2288 | URD KOHL INDUSTRIAL PK, N RTE 303, | A3 | 0 | 0.7 | -0.4 | 0.1 | 5.5 | -3.4
D553FX | 51-2326 | URD BESIATA DESHMAYA LLC, MERON DR, | AP | 0 | 2.6 | 0 | 0 | 0 | 0
D553FX | 51-2405 | URD/ST.LGT - BAKERTOWN RD CONDO'S P | A3 | 0.1 | 0.6 | 2.5 | -0.5 | 0 | 0
D553FX | 51-2388 | URD TAMMY FLANNERY, DEER POND DRIVE | A4 | 1 | 0.6 | 1.2 | 0 | 0 | 0
D553FX | 51-2381 | URD COUNTRY COMFORT HOMES CORP, MID | A3 | 2.2 | 0.6 | 0 | 0 | 0 | 0
D553FX | 51-2092 | URD/ST. LGTS WILLOWS SUB., WESLEY H | A3 | 1 | 1.7 | 0.1 | 0 | 0 | 0
D553FX | 51-2083 | URD & ST - LGTS POLO COURT SUB, SUF | AP | 0 | 0 | 0 | 0 | 3 | 0
D553FX | 51-2083 | URD & ST - LGTS POLO COURT SUB, SUF | A4 | 0 | 0 | 0 | 0 | 0.9 | 2.1
D553FX | 51-2383 | URD HIDDEN CRK CONDOS SECT-3, MONRO | A3 | 0 | 0 | 0.4 | 2.6 | 0 | 0
D553FX | 51-2425 | PINES HOMES CORP, VINCENT RD, SPRIN | A4 | 0 | 0 | 0 | 0.3 | 0.7 | 2.1
D553FX | 51-2382 | URD HIDDEN CREEK CONDOS SECT-2, MON | A3 | 0 | 0 | 0.2 | 3.4 | -0.5 | 0
D553FX | 51-2361 | URD CARRIAGE PARK, WEST MAIN ST, GO | PR | 5.1 | -1.9 | 0 | 0 | 0 | 0
D553FX | 51-2465 | URD WOODSIDE KNOLLS - PH V, MIDDLET | MS | 0 | 0 | 0 | 0 | 0 | 3.3
D553FX | 51-2349 | URD JOON MANAGEMENT 1, AMONA CT, MO | A3 | 0 | 0 | 0 | 0 | 0.6 | 2.7
D553FX | 51-2455 | URD SKI SIDE VILLA, KATRINA CT, TUX | A3 | 0 | 0 | 0 | 0 | 3.1 | 0.3
D553FX | 51-2383 | URD HIDDEN CRK CONDOS SECT-3, MONRO | MS | 0 | 0 | 2.7 | 0.7 | 0 | 0
D553FX | 51-2378 | URD MADISON PARK CONDOMINIUMS, SPRI | MS | 0 | 0 | 0 | 0 | 2.8 | 0.7
D553FX | 51-2435 | URD WOODSIDE KNOLLS DRIVE, MIDDLETO | A3 | 0 | 0 | 0 | 4.8 | -1.3 | 0
D553FX | 51-2361 | URD CARRIAGE PARK, WEST MAIN ST, GO | MS | 3.5 | 0 | 0 | 0 | 0 | 0
D553FX | 54-0646 | UNDERGROUND PRIMARY CONDUCTOR BLANK | PR | 0 | 0.3 | 1.9 | -0.3 | 0.6 | 1.8
D553FX | 51-2083 | URD & ST - LGTS POLO COURT SUB, SUF | MS | 0 | 0 | 0 | 0 | 3.8 | 0.7
D553FX | 51-2381 | URD COUNTRY COMFORT HOMES CORP, MID | A4 | 3.5 | 1 | 0 | 0 | 0 | 0
D553FX | 51-2360 | URD BARBARA PEPEYRA, STEGMEYER LN., | AP | 0 | 0.3 | 0 | 4.5 | 0 | 0
D553FX | 51-2425 | PINES HOMES CORP, VINCENT RD, SPRIN | AP | 0 | 0 | 0 | 0.4 | 4.4 | 0
D553FX | 51-2382 | URD HIDDEN CREEK CONDOS SECT-2, MON | A4 | 0.1 | 0 | 0.5 | 5.1 | -0.8 | 0
D553FX | 51-2455 | URD SKI SIDE VILLA, KATRINA CT, TUX | MS | 0 | 0 | 0 | 0 | 4.9 | 0
D553FX | 51-2383 | URD HIDDEN CRK CONDOS SECT-3, MONRO | A4 | 0 | 0 | 1.1 | 3.9 | 0 | 0
D553FX | 51-2277 | URD ALBERT WISNER PUBLIC LIBRARY, W | AP | 0 | 0 | 0 | 0 | 5.1 | 0
D553FX | 51-2361 | URD CARRIAGE PARK, WEST MAIN ST, GO | A3 | 7.8 | -2.6 | 0 | 0 | 0 | 0
D553FX | 51-2288 | URD KOHL INDUSTRIAL PK, N RTE 303, | A4 | 0 | 2.3 | -1.1 | 0.2 | 8.5 | -4.7
D553FX | 51-2405 | URD/ST.LGT - BAKERTOWN RD CONDO'S P | A4 | 0.3 | 2 | 3.7 | -0.8 | 0 | 0
D553FX | 51-2349 | URD JOON MANAGEMENT 1, AMONA CT, MO | A4 | 0 | 0 | 0 | 0.1 | 1.4 | 3.8
D553FX | 51-2092 | URD/ST. LGTS WILLOWS SUB., WESLEY H | A4 | 2.3 | 2.8 | 0.2 | 0 | 0 | 0
D553FX | 51-2288 | URD KOHL INDUSTRIAL PK, N RTE 303, | MS | 0 | 6.8 | -2.7 | 0.8 | 0.5 | 0
D553FX | 51-2384 | URD HIDDEN CRK CONDOS SECT-3, MONRO | MS | 0.9 | 0 | 0 | 4.5 | 0 | 0
D553FX | 51-2455 | URD SKI SIDE VILLA, KATRINA CT, TUX | A4 | 0 | 0 | 0 | 0 | 5.1 | 0.4
D553FX | 51-2323 | URD SERGEI LOPUCHIN, CHRISTIAN HERA | AP | 0 | 0 | 0 | 0 | 5.5 | 0
D553FX | 51-2288 | URD KOHL INDUSTRIAL PK, N RTE 303, | AP | 0 | 0 | 0 | 0 | 5.8 | 0
D553FX | 51-2349 | URD JOON MANAGEMENT 1, AMONA CT, MO | AP | 0 | 0 | 0 | 10 | -5 | 0.9
D553FX | 51-2435 | URD WOODSIDE KNOLLS DRIVE, MIDDLETO | A4 | 0 | 0 | 0 | 7.8 | -1.9 | 0
D553FX | 51-2424 | URD S V SENIOR APTS., N. MAIN ST, S | AP | 0 | 0 | 0 | 5 | -1.9 | 3.2
D553FX | 51-2405 | URD/ST.LGT - BAKERTOWN RD CONDO'S P | MS | 0.7 | 5.8 | 0 | 0 | 0 | 0
D553FX | 54-0646 | UNDERGROUND PRIMARY CONDUCTOR BLANK | A3 | 0 | 0.5 | 2.7 | -0.5 | 0.8 | 3.3
D553FX | 51-2092 | URD/ST. LGTS WILLOWS SUB., WESLEY H | MS | 5.4 | 1.5 | 0 | 0 | 0 | 0
D553FX | 51-2435 | URD WOODSIDE KNOLLS DRIVE, MIDDLETO | MS | 0 | 0 | 0 | 7.4 | 0 | 0
D553FX | 51-2349 | URD JOON MANAGEMENT 1, AMONA CT, MO | MS | 0 | 0 | 0 | 0.3 | 5.7 | 1.5
D553FX | 51-2361 | URD CARRIAGE PARK, WEST MAIN ST, GO | A4 | 12.4 | -4 | 0 | 0 | 0 | 0
D553FX | 54-0646 | UNDERGROUND PRIMARY CONDUCTOR BLANK | A4 | 0 | 0.7 | 3.9 | -0.7 | 1.3 | 4.6
D553FX | 51-2456 | URD DOROTHY JORDAN, ACKERTOWN RD, C | AP | 0 | 0 | 0 | 0 | 0 | 9.9
D553FX | 51-2378 | URD MADISON PARK CONDOMINIUMS, SPRI | AP | 0 | 0 | 0 | 0 | 0 | 10.3
D553FX | 51-2092 | URD/ST. LGTS WILLOWS SUB., WESLEY H | AP | 12 | -11.2 | 10 | 0 | 0 | 0
D553FX | 51-1593 | URD FAIRWAYS WALLKILL III, GOLF LIN | AP | 0 | 0 | 0 | 0 | 0 | 14.9
D553FX | 50-0646 | UNDERGROUND PRIMARY CONDUCTOR BLANK | AP | 3.4 | 0 | 2.8 | 19.5 | -9.6 | 13.2
D553FX | 50-0646 | UNDERGROUND PRIMARY CONDUCTOR BLANK | PR | 3.8 | 18.9 | 7.1 | 0.1 | 10.8 | 7.8
D553FX | 50-0646 | UNDERGROUND PRIMARY CONDUCTOR BLANK | A3 | 6.1 | 28.7 | 11 | 2.4 | 18 | 17.8
D553FX | 50-0646 | UNDERGROUND PRIMARY CONDUCTOR BLANK | MS | 4.9 | 25.4 | 6.6 | 18.5 | 17.1 | 15.4
D553FX | 50-0646 | UNDERGROUND PRIMARY CONDUCTOR BLANK | A4 | 10.1 | 48.4 | 17.5 | 5.5 | 28.9 | 55.8
D554FX | 51-2435 | URD WOODSIDE KNOLLS DRIVE, MIDDLETO | CC | 0 | 0 | 0 | 0.3 | 0 | 0
D554FX | 51-2435 | URD WOODSIDE KNOLLS DRIVE, MIDDLETO | A3 | 0 | 0 | 0 | 0.4 | 0 | 0
D554FX | 51-2435 | URD WOODSIDE KNOLLS DRIVE, MIDDLETO | A4 | 0 | 0 | 0 | 1 | 0 | 0
D554FX | 50-0656 | UNDERGROUND DEVICES BLANKET | CC | 0 | 0 | 0.3 | 0 | 0.7 | 0
D554FX | 51-2288 | URD KOHL INDUSTRIAL PK, N RTE 303, | CC | 0 | 0 | 0 | 1.2 | 0 | 0
D554FX | 50-0656 | UNDERGROUND DEVICES BLANKET | PR | 0 | 0 | 0.3 | -0.2 | 1.1 | 0
D554FX | 51-2288 | URD KOHL INDUSTRIAL PK, N RTE 303, | A3 | 0 | 0 | 0 | 1.7 | 0 | 0
D554FX | 51-2288 | URD KOHL INDUSTRIAL PK, N RTE 303, | AP | 0 | 0 | 1.9 | 0 | 0.7 | 0
D554FX | 50-0656 | UNDERGROUND DEVICES BLANKET | A3 | 0 | 0 | 1 | -0.3 | 2.5 | -0.1
D554FX | 51-2435 | URD WOODSIDE KNOLLS DRIVE, MIDDLETO | MS | 0 | 0 | 0 | 3.3 | 0 | 0
D554FX | 51-2288 | URD KOHL INDUSTRIAL PK, N RTE 303, | A4 | 0 | 0 | 0 | 4 | 0 | 0
D554FX | 50-0656 | UNDERGROUND DEVICES BLANKET | A4 | 0 | 0 | 2 | -0.4 | 4.4 | -0.1
D554FX | 50-0656 | UNDERGROUND DEVICES BLANKET | MS | 0 | 0 | 3.2 | 0 | 7.9 | 0
D554FX | 51-2288 | URD KOHL INDUSTRIAL PK, N RTE 303, | MS | 0 | 0 | 0 | 13.8 | 0 | 0
D555FX | 50-0666 | UNDERGROUND STREET LIGHTING BLANKET | CC | -4.3 | 0 | 0.2 | 0 | 0.1 | -1.9
D555FX | 51-2466 | URD SUNRISE HILLS - SECTION A, MIDD | A4 | 0 | 0 | 0 | 0 | 0 | 0.1
D555FX | 51-2493 | BAKERTOWN RD CONDO'S SEC 3 - KIRYAS | PR | 0 | 0 | 0 | 0 | 0 | 0.1
D555FX | 51-2092 | URD/ST. LGTS WILLOWS SUB., WESLEY H | CC | 0 | 0.1 | 0 | 0 | 0 | 0
D555FX | 54-0666 | UNDERGROUND STREET LIGHTING BLANKET | PR | -0.1 | 0.1 | 0.2 | -0.1 | 0 | 0
D555FX | 54-0666 | UNDERGROUND STREET LIGHTING BLANKET | A3 | -0.1 | 0.1 | 0.3 | -0.1 | 0 | 0
D555FX | 51-2466 | URD SUNRISE HILLS - SECTION A, MIDD | MS | 0 | 0 | 0 | 0 | 0 | 0.2
D555FX | 51-2493 | BAKERTOWN RD CONDO'S SEC 3 - KIRYAS | A3 | 0 | 0 | 0 | 0 | 0 | 0.2
D555FX | 54-0666 | UNDERGROUND STREET LIGHTING BLANKET | A4 | -0.2 | 0.1 | 0.4 | -0.2 | 0.1 | 0
D555FX | 51-2493 | BAKERTOWN RD CONDO'S SEC 3 - KIRYAS | A4 | 0 | 0 | 0 | 0 | 0 | 0.3
D555FX | 51-2092 | URD/ST. LGTS WILLOWS SUB., WESLEY H | PR | 0 | 0.6 | -0.3 | 0 | 0 | 0
D555FX | 51-2405 | URD/ST.LGT - BAKERTOWN RD CONDO'S P | CC | 0 | 0 | 0.5 | 0 | 0 | 0
D555FX | 51-2092 | URD/ST. LGTS WILLOWS SUB., WESLEY H | A3 | 0 | 1 | -0.4 | 0 | 0 | 0
D555FX | 51-1675 | URD & ST.LTG. RIVER RIDGE EST, S, N | PR | 0 | 0 | 0 | 0 | 0 | 0.6
D555FX | 50-0666 | UNDERGROUND STREET LIGHTING BLANKET | AP | 0 | 0.5 | 0.5 | 0 | 0 | 0
D555FX | 51-1675 | URD & ST.LTG. RIVER RIDGE EST, S, N | A3 | 0 | 0 | 0 | 0 | 0 | 1.1
D555FX | 51-2092 | URD/ST. LGTS WILLOWS SUB., WESLEY H | A4 | 0 | 1.8 | -0.6 | 0 | 0 | 0
D555FX | 51-1675 | URD & ST.LTG. RIVER RIDGE EST, S, N | A4 | 0 | 0 | 0 | 0 | 0 | 1.5
D555FX | 51-1675 | URD & ST.LTG. RIVER RIDGE EST, S, N | MS | 0 | 0 | 0 | 0 | 0 | 1.7
D555FX | 51-2092 | URD/ST. LGTS WILLOWS SUB., WESLEY H | MS | 0 | 1.7 | 0 | 0 | 0 | 0
D555FX | 51-2405 | URD/ST.LGT - BAKERTOWN RD CONDO'S P | PR | 0 | 0 | 2.1 | -0.4 | 0 | 0
D555FX | 51-2405 | URD/ST.LGT - BAKERTOWN RD CONDO'S P | A3 | 0 | 0 | 3.9 | -0.6 | 0 | 0
D555FX | 50-0666 | UNDERGROUND STREET LIGHTING BLANKET | PR | 1.7 | 0.4 | 2.7 | -0.2 | 1 | -0.3
D555FX | 51-2405 | URD/ST.LGT - BAKERTOWN RD CONDO'S P | MS | 0.1 | 0 | 5.6 | 0 | 0 | 0
D555FX | 51-2405 | URD/ST.LGT - BAKERTOWN RD CONDO'S P | A4 | 0 | 0 | 6.7 | -0.9 | 0 | 0
D555FX | 50-0666 | UNDERGROUND STREET LIGHTING BLANKET | MS | 4.5 | 0.5 | 2 | 0 | 0.8 | 0.9
D555FX | 50-0666 | UNDERGROUND STREET LIGHTING BLANKET | A3 | 3.2 | 0.6 | 4.1 | -0.3 | 1.6 | -0.4
D555FX | 50-0666 | UNDERGROUND STREET LIGHTING BLANKET | A4 | 5.5 | 0.9 | 6.4 | -0.4 | 2.5 | -0.4
D556FX | 50-0676 | UNDERGROUND SECONDARY CONDUCTOR BLA | CC | -3.4 | -3.8 | 0.1 | 0.1 | 0 | 0
D556FX | 51-2360 | URD BARBARA PEPEYRA, STEGMEYER LN., | MS | 0.3 | 0 | 0 | 0 | 0 | -0.6
D556FX | 51-2285 | URD ROBERT RINO, 20 VIOLA RD, MONTE | A3 | -0.2 | 0 | 0 | 0 | 0 | 0
D556FX | 51-2285 | URD ROBERT RINO, 20 VIOLA RD, MONTE | A4 | -0.2 | 0 | 0 | 0 | 0 | 0
D556FX | 51-2323 | URD SERGEI LOPUCHIN, CHRISTIAN HERA | MS | 0 | 0 | -0.1 | 0 | 0 | 0
D556FX | 51-2285 | URD ROBERT RINO, 20 VIOLA RD, MONTE | PR | -0.1 | 0 | 0 | 0 | 0 | 0
D556FX | 51-2361 | URD CARRIAGE PARK, WEST MAIN ST, GO | A4 | 0.1 | 0 | 0 | 0 | 0 | 0
D556FX | 51-2435 | URD WOODSIDE KNOLLS DRIVE, MIDDLETO | A3 | 0 | 0 | 0 | 0.1 | 0 | 0
D556FX | 51-2354 | URD BEN VELTIDI, 4 LINDA DR., SUFFE | PR | 0.1 | 0 | 0 | 0 | 0 | 0
D556FX | 51-2092 | URD/ST. LGTS WILLOWS SUB., WESLEY H | CC | 0.1 | 0 | 0 | 0 | 0 | 0
D556FX | 51-2435 | URD WOODSIDE KNOLLS DRIVE, MIDDLETO | MS | 0 | 0 | 0 | 0.1 | 0 | 0
D556FX | 51-2435 | URD WOODSIDE KNOLLS DRIVE, MIDDLETO | A4 | 0 | 0 | 0 | 0.1 | 0 | 0
D556FX | 51-2323 | URD SERGEI LOPUCHIN, CHRISTIAN HERA | PR | 0 | 0 | 0 | 0.1 | 0 | 0
D556FX | 51-2092 | URD/ST. LGTS WILLOWS SUB., WESLEY H | PR | 0 | 0.1 | 0 | 0 | 0 | 0
D556FX | 51-2363 | URD ZARA CROWLEY, CASTLE HGTS AV, U | PR | 0 | 0 | 0.1 | 0 | 0 | 0
D556FX | 51-2349 | URD JOON MANAGEMENT 1, AMONA CT, MO | A3 | 0 | 0 | 0 | 0 | 0.1 | 0
D556FX | 51-2363 | URD ZARA CROWLEY, CASTLE HGTS AV, U | CC | 0 | 0 | 0.1 | 0 | 0 | 0
D556FX | 51-2323 | URD SERGEI LOPUCHIN, CHRISTIAN HERA | A3 | 0 | 0 | 0 | 0.1 | 0 | 0
D556FX | 51-2362 | CAROL LOPATIN OLD RTE 304 - NEW CIT | A3 | 0 | 0 | 0 | 0 | 0 | 0.1
D556FX | 51-2354 | URD BEN VELTIDI, 4 LINDA DR., SUFFE | A3 | 0.1 | 0 | 0 | 0 | 0 | 0
D556FX | 51-2425 | PINES HOMES CORP, VINCENT RD, SPRIN | PR | 0 | 0 | 0 | 0 | 0 | 0.1
D556FX | 51-2349 | URD JOON MANAGEMENT 1, AMONA CT, MO | A4 | 0 | 0 | 0 | 0 | 0.1 | 0
D556FX | 51-2323 | URD SERGEI LOPUCHIN, CHRISTIAN HERA | A4 | 0 | 0 | 0 | 0.2 | 0 | 0
D556FX | 51-2362 | CAROL LOPATIN OLD RTE 304 - NEW CIT | A4 | 0 | 0 | 0 | 0 | 0 | 0.2
D556FX | 51-2092 | URD/ST. LGTS WILLOWS SUB., WESLEY H | A3 | 0.1 | 0.1 | 0 | 0 | 0 | 0
D556FX | 51-2425 | PINES HOMES CORP, VINCENT RD, SPRIN | A3 | 0 | 0 | 0 | 0 | 0 | 0.2
D556FX | 51-2354 | URD BEN VELTIDI, 4 LINDA DR., SUFFE | A4 | 0.2 | 0 | 0 | 0 | 0 | 0
D556FX | 51-2354 | URD BEN VELTIDI, 4 LINDA DR., SUFFE | MS | 0.3 | 0 | 0 | 0 | 0 | 0
D556FX | 51-2349 | URD JOON MANAGEMENT 1, AMONA CT, MO | MS | 0 | 0 | 0 | 0 | 0.5 | -0.2
D556FX | 51-2323 | URD SERGEI LOPUCHIN, CHRISTIAN HERA | AP | 0 | 0 | 0 | 0.3 | 0 | 0
D556FX | 51-2363 | URD ZARA CROWLEY, CASTLE HGTS AV, U | A3 | 0 | 0 | 0.2 | 0.1 | 0 | 0
D556FX | 51-2425 | PINES HOMES CORP, VINCENT RD, SPRIN | A4 | 0 | 0 | 0 | 0 | 0.1 | 0.2
D556FX | 51-2092 | URD/ST. LGTS WILLOWS SUB., WESLEY H | A4 | 0.3 | 0.2 | 0 | 0 | 0 | 0
D556FX | 51-2425 | PINES HOMES CORP, VINCENT RD, SPRIN | AP | 0 | 0 | 0 | 0 | 0.5 | 0
D556FX | 51-2362 | CAROL LOPATIN OLD RTE 304 - NEW CIT | MS | 0 | 0 | 0 | 0 | 0 | 0.6
D556FX | 51-2092 | URD/ST. LGTS WILLOWS SUB., WESLEY H | MS | 0.6 | 0 | 0 | 0 | 0 | 0
D556FX | 51-2363 | URD ZARA CROWLEY, CASTLE HGTS AV, U | A4 | 0 | 0.1 | 0.5 | 0.1 | 0 | 0
D556FX | 54-0676 | UNDERGROUND SECONDARY CONDUCTOR BLA | AP | 0 | 0 | 0 | 0 | 0.2 | 0.6
D556FX | 51-2363 | URD ZARA CROWLEY, CASTLE HGTS AV, U | MS | 0 | 0.4 | 0.8 | 0 | 0 | 0
D556FX | 54-0676 | UNDERGROUND SECONDARY CONDUCTOR BLA | PR | 0 | 0.1 | 0.2 | 1 | 0 | 0.1
D556FX | 54-0676 | UNDERGROUND SECONDARY CONDUCTOR BLA | A3 | 0 | 0.1 | 0.2 | 1.5 | 0.1 | 0.1
D556FX | 51-2363 | URD ZARA CROWLEY, CASTLE HGTS AV, U | AP | 0 | 0 | 0 | 0.4 | 0.2 | 1.6
D556FX | 50-0676 | UNDERGROUND SECONDARY CONDUCTOR BLA | AP | 0 | 0 | 0 | 0 | 0.8 | 1.4
D556FX | 54-0676 | UNDERGROUND SECONDARY CONDUCTOR BLA | A4 | 0 | 0.1 | 0.3 | 2.2 | 0.1 | 0.1
D556FX | 50-0676 | UNDERGROUND SECONDARY CONDUCTOR BLA | MS | 0.3 | 1.1 | 0.9 | 0.8 | 0.2 | 0
D556FX | 51-2360 | URD BARBARA PEPEYRA, STEGMEYER LN., | AP | 0 | 0 | 3.8 | 0 | 0 | 0
D556FX | 50-0676 | UNDERGROUND SECONDARY CONDUCTOR BLA | PR | -0.1 | 1.7 | 1.2 | 1.8 | 0.2 | 0.5
D556FX | 50-0676 | UNDERGROUND SECONDARY CONDUCTOR BLA | A3 | -0.1 | 2.4 | 1.8 | 3 | 0.3 | 0.9
D556FX | 50-0676 | UNDERGROUND SECONDARY CONDUCTOR BLA | A4 | -0.2 | 3.9 | 2.8 | 4.5 | 0.5 | 1.3
D558FX | 50-0686 | FIRST INSTALL TRANSFORMERS - UNDERG | CC | 0.7 | 0.3 | 1.9 | 1.2 | 1.8 | 0.6
D558FX | 54-0686 | FIRST INSTALL TRANSFORMERS - UNDERG | AP | 0 | 0 | 0 | 0 | 0 | 14.5
D558FX | 50-0686 | FIRST INSTALL TRANSFORMERS - UNDERG | PR | 6.7 | 2.5 | 16.8 | 10.9 | 16.2 | 5.7
D558FX | 50-0686 | FIRST INSTALL TRANSFORMERS - UNDERG | MS | 8.5 | 3.2 | 21.3 | 13.8 | 20.5 | 7.2
D558FX | 50-0686 | FIRST INSTALL TRANSFORMERS - UNDERG | A3 | 11.5 | 4.4 | 29 | 18.7 | 27.9 | 9.8
D558FX | 50-0686 | FIRST INSTALL TRANSFORMERS - UNDERG | A4 | 18.7 | 7 | 46.8 | 30.3 | 45.1 | 15.8
D559FX | 50-0816 | UNDERGROUND CUSTOMER OWNED SERVICES | MS | 0.1 | 0.3 | 0.2 | 0.1 | 0.1 | 0.5
D559FX | 54-0816 | UNDERGROUND CUSTOMER OWNED SERVICES | PR | 0.2 | 0.4 | 0.3 | 0.1 | 0.2 | 0.2
D559FX | 54-0816 | UNDERGROUND CUSTOMER OWNED SERVICES | A3 | 0.3 | 0.5 | 0.3 | 0.2 | 0.2 | 0.5
D559FX | 54-0816 | UNDERGROUND CUSTOMER OWNED SERVICES | A4 | 0.4 | 0.8 | 0.5 | 0.2 | 0.4 | 0.7
D559FX | 50-0816 | UNDERGROUND CUSTOMER OWNED SERVICES | PR | 9 | 12.4 | 6.3 | 6.9 | 9.3 | 6.4
D559FX | 50-0816 | UNDERGROUND CUSTOMER OWNED SERVICES | A3 | 12.5 | 17.1 | 8.9 | 10.8 | 14.1 | 12.6
D559FX | 50-0816 | UNDERGROUND CUSTOMER OWNED SERVICES | A4 | 19.3 | 26.2 | 13.2 | 16.1 | 21.5 | 52.2
D561FX | 50-0826 | UNDERGROUND DEFECTIVE SERVICES - TA | PR | 0 | 0 | 0.2 | 0.1 | 0 | 0
D561FX | 50-0826 | UNDERGROUND DEFECTIVE SERVICES - TA | A3 | 0 | 0 | 0.3 | 0.2 | 0 | 0
D561FX | 50-0826 | UNDERGROUND DEFECTIVE SERVICES - TA | A4 | 0 | 0 | 0.5 | 0.3 | 0 | 0
D563FX | 50-0813 | UNDERGROUND CUSTOMER OWNED SERVICE | AP | -10.6 | 0 | 0 | 0 | 0 | 0
D563FX | 50-0813 | UNDERGROUND CUSTOMER OWNED SERVICE | CC | 0 | 0.1 | 0.1 | 0.1 | 0.1 | 0
D563FX | 54-0813 | UNDERGROUND CUSTOMER OWNED SERVICE | AP | -1 | 0 | 1.6 | 0 | 0 | 0
D563FX | 54-0813 | UNDERGROUND CUSTOMER OWNED SERVICE | PR | 0.4 | 0.8 | 0.3 | 0.1 | 0.2 | 0.2
D563FX | 54-0813 | UNDERGROUND CUSTOMER OWNED SERVICE | A3 | 0.5 | 1.1 | 0.4 | 0.1 | 0.3 | 0.5
D563FX | 54-0813 | UNDERGROUND CUSTOMER OWNED SERVICE | A4 | 0.9 | 1.8 | 0.6 | 0.2 | 0.5 | 0.6
D563FX | 50-0813 | UNDERGROUND CUSTOMER OWNED SERVICE | MS | 0.6 | 0.9 | 0.8 | 1.4 | 1.1 | 0.5
D563FX | 50-0813 | UNDERGROUND CUSTOMER OWNED SERVICE | PR | 4.4 | 5.1 | 2.8 | 7 | 7.1 | 2.9
D563FX | 50-0813 | UNDERGROUND CUSTOMER OWNED SERVICE | A3 | 6.2 | 6.9 | 3.9 | 11.7 | 11.7 | 7.1
D563FX | 50-0813 | UNDERGROUND CUSTOMER OWNED SERVICE | A4 | 10.3 | 11.5 | 6.2 | 18.8 | 18.1 | 9.5
D564FX | 50-0916 | UNDERGROUND CUSTOMER SERVICE CREDIT | AP | 2 | 0.1 | 0.2 | 0.7 | 0.9 | 0.4
D565FR | 50-2110 | 2008 UNDERGROUND CAPITAL TOOLS BLAN | A3 | 1.3 | 0.8 | 0 | 0 | 0 | 0.5
D565FR | 50-2110 | 2008 UNDERGROUND CAPITAL TOOLS BLAN | A4 | 1.7 | 1 | 0 | 0 | 0 | 0.4
D565FR | 50-2110 | 2008 UNDERGROUND CAPITAL TOOLS BLAN | AP | 0 | 9.6 | 0 | 0 | 0 | 76.1
D583FR | 10-2259 | 2008 INCREMENTAL RELIABILITY - DEFE | CC | 0.4 | 0.3 | 0.1 | 0 | 0.3 | 0
D583FR | 13-2259 | 2008 INCREMENTAL RELIABILITY - DEFE | PR | 0.2 | 0.5 | 0.8 | 0.3 | 0.9 | 0.6
D583FR | 13-2259 | 2008 INCREMENTAL RELIABILITY - DEFE | A3 | 0.2 | 0.7 | 1.1 | 0.4 | 1.4 | 1.4
D583FR | 13-2259 | 2008 INCREMENTAL RELIABILITY - DEFE | A4 | 0.4 | 1.1 | 1.7 | 0.7 | 2.1 | 1.9
D583FR | 10-2259 | 2008 INCREMENTAL RELIABILITY - DEFE | PR | 0.4 | 1.5 | 2.5 | 0.8 | 2 | 1.4
D583FR | 10-2259 | 2008 INCREMENTAL RELIABILITY - DEFE | MS | 4.5 | 3.7 | 1.5 | 0.5 | 4.1 | 0
D583FR | 10-2259 | 2008 INCREMENTAL RELIABILITY - DEFE | A3 | 1.4 | 2.5 | 3.6 | 1.4 | 3.8 | 3.9
D583FR | 10-2259 | 2008 INCREMENTAL RELIABILITY - DEFE | A4 | 2.8 | 4.6 | 5.8 | 2.3 | 6.2 | 5
D583FR | 10-2259 | 2008 INCREMENTAL RELIABILITY - DEFE | AP | 1.6 | 2.3 | 6.7 | -1.6 | 39 | 119.5
D660FX | 54-0806 | UNDERGROUND COMPANY OWNED SERVICES | PR | 0 | 0 | 0 | 0.2 | -0.1 | 0
D660FX | 54-0806 | UNDERGROUND COMPANY OWNED SERVICES | A3 | 0 | 0 | 0 | 0.3 | -0.1 | 0
D660FX | 54-0806 | UNDERGROUND COMPANY OWNED SERVICES | A4 | 0 | 0 | 0 | 0.5 | -0.2 | 0
D660FX | 50-0806 | UNDERGROUND COMPANY OWNED SERVICES | PR | 0.4 | -0.2 | 0 | 0.2 | 0.1 | 0
D660FX | 50-0806 | UNDERGROUND COMPANY OWNED SERVICES | MS | 0 | 0 | 0 | 0 | 0.6 | 0
D660FX | 50-0806 | UNDERGROUND COMPANY OWNED SERVICES | A3 | 0.6 | -0.3 | 0 | 0.3 | 0.1 | 0
D660FX | 50-0806 | UNDERGROUND COMPANY OWNED SERVICES | A4 | 0.9 | -0.4 | 0 | 0.4 | 0.3 | 0
T015ZR | 10-2112 | 2008 SUBSTATION DEPT BLANKET | MS | 0 | 0 | 0 | 0 | 0 | 0.1
T015ZR | 13-2112 | 2008 SUBSTATION DEPT BLANKET | MS | 0 | 0 | 0 | 0 | 0.2 | 0
T015ZR | 10-2112 | 2008 SUBSTATION DEPT BLANKET | AP | 0 | 9.9 | -6.4 | 6.9 | 3.9 | 0
T015ZR | 10-2112 | 2008 SUBSTATION DEPT BLANKET | PR | 2.3 | 13.4 | 0.5 | -0.5 | 0 | 5.9
T015ZR | 10-2112 | 2008 SUBSTATION DEPT BLANKET | A3 | 3.4 | 19 | 0.5 | -0.5 | 0 | 5
T015ZR | 13-2112 | 2008 SUBSTATION DEPT BLANKET | PR | 0.7 | 10.3 | 0 | 0 | 30.7 | -6.6
T015ZR | 13-2112 | 2008 SUBSTATION DEPT BLANKET | A3 | 1.1 | 14.3 | 0 | 0 | 31.5 | -7.8
T015ZR | 10-2112 | 2008 SUBSTATION DEPT BLANKET | A4 | 5.8 | 33.4 | 1 | -1 | 0 | 10.7
T015ZR | 13-2112 | 2008 SUBSTATION DEPT BLANKET | A4 | 1.8 | 25.3 | 0 | 0 | 60.6 | -14.5
T016ZR | 10-2119 | 2008 BATTERY BANK REPLACEMENT BLANK | CC | 0 | 0 | -5.6 | 0 | 0 | 0
T016ZR | 13-2119 | 2008 BATTERY BANK REPLACEMENT BLANK | PR | 0 | 0 | 0.8 | 0 | 0 | 0
T016ZR | 13-2119 | 2008 BATTERY BANK REPLACEMENT BLANK | A3 | 0 | 0 | 0.8 | 0 | 0 | 0
T016ZR | 13-2119 | 2008 BATTERY BANK REPLACEMENT BLANK | A4 | 0 | 0 | 1.5 | 0 | 0 | 0
T016ZR | 10-2119 | 2008 BATTERY BANK REPLACEMENT BLANK | PR | 0 | 0 | 1.6 | 0 | 0 | 0
T016ZR | 10-2119 | 2008 BATTERY BANK REPLACEMENT BLANK | A3 | 0 | 0 | 1.7 | 0 | 0 | 0
T016ZR | 10-2119 | 2008 BATTERY BANK REPLACEMENT BLANK | A4 | 0 | 0 | 3.2 | 0 | 0 | 0
T017ZR | 10-2120 | 2008 RELAY DEPT CAPITAL PURCHASE BL | A3 | 4 | 0 | 0 | 0 | 0 | 0
T017ZR | 10-2120 | 2008 RELAY DEPT CAPITAL PURCHASE BL | A4 | 5.2 | 0 | 0 | 0 | 0 | 0
T017ZR | 10-2120 | 2008 RELAY DEPT CAPITAL PURCHASE BL | AP | 28.5 | 0 | 0 | 0 | 0 | 0
T018ZR | 13-2113 | PURCHASE NEW RELAY TEST SET FOR S/S | PR | 0 | 0 | 0 | 0 | 0 | 0.6
T018ZR | 13-2113 | PURCHASE NEW RELAY TEST SET FOR S/S | A3 | 0 | 0 | 0 | 0 | 0 | 0.6
T018ZR | 13-2113 | PURCHASE NEW RELAY TEST SET FOR S/S | A4 | 0 | 0 | 0 | 0 | 0 | 1.2
T114MP | 10-1916 | 2007 SUBSTATION COMMUNICATION PROTE | AP | 0 | -6.3 | 0 | 0 | 0 | 0
T114MR | 10-2234 | 2008 SUBSTATION COMMUNICATION PROTE | A3 | 0 | 0 | 0 | 0.1 | 0.1 | 0
T114MR | 10-2234 | 2008 SUBSTATION COMMUNICATION PROTE | A4 | 0 | 0 | 0 | 0.1 | 0.1 | 0
T114MR | 10-2234 | 2008 SUBSTATION COMMUNICATION PROTE | AP | 13 | 1.1 | 0 | 23.1 | -4.1 | 19.1
T133AR | 10-2159 | ELECTRONIC MAP BOARDS FOR ECC/DCC | A3 | 0 | 0.4 | 0.7 | 0.3 | 0 | 0
T133AR | 10-2159 | ELECTRONIC MAP BOARDS FOR ECC/DCC | A4 | 0 | 2 | 6.1 | 0.7 | 0.1 | 0
T133AR | 10-2159 | ELECTRONIC MAP BOARDS FOR ECC/DCC | PR | 0 | 1.9 | 6.7 | 0.5 | 0.1 | 0
T133AR | 10-2159 | ELECTRONIC MAP BOARDS FOR ECC/DCC | AP | 0 | 0 | 0 | 0 | 5 | 52.7
T134BR | 10-2147 | BURNS LINE-702 CARRIER DTT EQUIPMEN | A3 | -0.1 | 0.6 | 0.2 | 0.3 | 0.3 | 0.2
T134BR | 10-2147 | BURNS LINE-702 CARRIER DTT EQUIPMEN | PR | -0.4 | 2.7 | 1.1 | 1.6 | 0.6 | 0.7
T134BR | 10-2147 | BURNS LINE-702 CARRIER DTT EQUIPMEN | A4 | -0.4 | 2.9 | 1.2 | 1.8 | 0.8 | 0.9
T134BR | 10-2147 | BURNS LINE-702 CARRIER DTT EQUIPMEN | AP | 0 | 0 | 0 | 0 | 4.4 | 51.4
T239CP | 10-1817 | EMS HARDWARE EXPANSION SV & BG - 20 | CC | 0 | 0 | 0 | 0.3 | 0 | 0
T239CP | 10-1817 | EMS HARDWARE EXPANSION SV & BG - 20 | A3 | 0 | 0.2 | 0.5 | 1.1 | 0.4 | 0
T239CP | 10-1817 | EMS HARDWARE EXPANSION SV & BG - 20 | A4 | 0 | 0.9 | 3.1 | 9.4 | 2.9 | 0
T239CP | 10-1817 | EMS HARDWARE EXPANSION SV & BG - 20 | PR | 0 | 0.8 | 3.1 | 9.8 | 2.9 | 0
T305AR | 10-2160 | 2008 EMS EXPANSION JOINT UTILITY MA | A3 | 0 | 0 | 0 | 0 | 0.6 | 0.3
T305AR | 10-2160 | 2008 EMS EXPANSION JOINT UTILITY MA | A4 | 0 | 0 | 1.6 | 0.6 | 8.7 | 14
T305AR | 10-2160 | 2008 EMS EXPANSION JOINT UTILITY MA | PR | 0 | 0 | 2 | 0.7 | 10.1 | 17.8
T356ZR | 10-2121 | 2008 SUBSTATION SMALL EQUIPMENT BLA | AP | 0 | 1.2 | 0 | 0 | 0 | 28
|  | Total Blankets |  | 2133.4 | 669.2 | 2348.3 | 2365.9 | 3539.2 | 2952.6
D100BA | 10-1691 | PRELIMARY ENGINERING ASSOC. WITH NE | PR | 0 | 0 | 0 | 0 | 0.1 | 0
D100BA | 10-1691 | PRELIMARY ENGINERING ASSOC. WITH NE | A3 | 0 | 0 | 1.7 | 0 | 0 | 0
D100BA | 10-1691 | PRELIMARY ENGINERING ASSOC. WITH NE | A4 | 0 | 0 | 1.8 | 0 | 0.1 | 0
|  |  |  | 0 | 0 | 3.5 | 0 | 0.2 | 0 | 3.7
D102FX | 50-2298 | REBUILD APPROX. 1900 FT - FERNDALE | MS | -1.4 | 1.1 | 0 | 0 | 0 | 0
D102FX | 53-2298 | REBUILD APPROX. 1900 FT - FERNDALE | A4 | 0 | 0 | 0.1 | 0 | 0 | 0
D102FX | 50-2298 | REBUILD APPROX. 1900 FT - FERNDALE | PR | 0 | 0 | 1.1 | 0 | 0 | 0
D102FX | 50-2298 | REBUILD APPROX. 1900 FT - FERNDALE | A3 | -0.2 | 0.1 | 1.5 | 0 | 0 | 0
D102FX | 50-2298 | REBUILD APPROX. 1900 FT - FERNDALE | A4 | -0.6 | 0.4 | 2.2 | 0 | 0 | 0
D102FX | 50-2298 | REBUILD APPROX. 1900 FT - FERNDALE | AP | 9.6 | 0 | -2.3 | -5 | 0 | 0
|  |  |  | 7.4 | 1.6 | 2.6 | -5 | 0 | 0 | 6.6
D103FB | 10-1511 | RECONDUCTOR CLARK ST TO HAMMOND ST | MS | 0.6 | -3.4 | 0 | 0 | 0 | 0
D103FB | 10-1511 | RECONDUCTOR CLARK ST TO HAMMOND ST | A4 | 0.3 | -0.9 | 0.1 | 0 | 0 | 0
D103FB | 10-1511 | RECONDUCTOR CLARK ST TO HAMMOND ST | CC | 0 | -0.3 | 0 | 0 | 0 | 0
D103FB | 10-1511 | RECONDUCTOR CLARK ST TO HAMMOND ST | A3 | 0.2 | -0.2 | 0.1 | 0 | 0 | 0
D103FB | 13-1511 | RECONDUCTOR CLARK ST TO HAMMOND ST | AP | 2 | -0.6 | -0.2 | 0.2 | 0 | 0
D103FB | 10-1511 | RECONDUCTOR CLARK ST TO HAMMOND ST | AP | 3 | 0.8 | -2 | 2 | 0 | 0
|  |  |  | 6.1 | -4.6 | -2 | 2.2 | 0 | 0 | 1.7
D103FC | 13-1512 | RECONDUCTOR MAIN ST TO KINGSTON AVE | PR | 0 | 0 | 0 | 0 | 0.1 | 0
D103FC | 10-1512 | RECONDUCTOR MAIN ST TO KINGSTON AVE | CC | 0.1 | 0 | 0 | 0 | 0 | 0
D103FC | 13-1512 | RECONDUCTOR MAIN ST TO KINGSTON AVE | A3 | 0 | 0 | 0 | 0 | 0.2 | 0
D103FC | 13-1512 | RECONDUCTOR MAIN ST TO KINGSTON AVE | A4 | 0 | 0 | 0 | 0 | 0.3 | 0
D103FC | 10-1512 | RECONDUCTOR MAIN ST TO KINGSTON AVE | PR | 0 | 0 | 0 | 0 | 1.3 | 0
D103FC | 10-1512 | RECONDUCTOR MAIN ST TO KINGSTON AVE | MS | 1.8 | 0 | 0 | 0 | 0 | 0
D103FC | 10-1512 | RECONDUCTOR MAIN ST TO KINGSTON AVE | A3 | 0.5 | 0.3 | 0 | 0.2 | 2.2 | 0
D103FC | 13-1512 | RECONDUCTOR MAIN ST TO KINGSTON AVE | AP | 4.5 | -0.7 | -1.2 | 1.2 | 0 | 0
D103FC | 10-1512 | RECONDUCTOR MAIN ST TO KINGSTON AVE | A4 | 0.9 | 0.3 | 0 | 0.2 | 3.4 | 0
D103FC | 10-1512 | RECONDUCTOR MAIN ST TO KINGSTON AVE | AP | 58.9 | -9.1 | -15.8 | 15.8 | 0 | 0
|  |  |  | 66.7 | -9.2 | -17 | 17.4 | 7.5 | 0 | 65.4
D103FD | 13-1513 | RECONDUCTOR PENN AVE & JERSEY AVE I | MS | -18 | 0 | 0 | 0 | 0 | 0
D103FD | 13-1513 | RECONDUCTOR PENN AVE & JERSEY AVE I | A4 | -7.3 | 0 | 0 | 0 | 0 | 0
D103FD | 13-1513 | RECONDUCTOR PENN AVE & JERSEY AVE I | A3 | -3 | 0 | 0 | 0 | 0 | 0
D103FD | 10-1513 | RECONDUCTOR PENN AVE & JERSEY AVE I | CC | 0 | 0 | 0.1 | 0 | 0 | 0
D103FD | 10-1513 | RECONDUCTOR PENN AVE & JERSEY AVE I | MS | 0 | 0 | 0.7 | 0 | 0 | 0
D103FD | 10-1513 | RECONDUCTOR PENN AVE & JERSEY AVE I | A3 | 0.3 | 0.1 | 0.5 | 0 | 0 | 0
D103FD | 10-1513 | RECONDUCTOR PENN AVE & JERSEY AVE I | A4 | 0.3 | 0.1 | 0.7 | 0 | 0 | 0
D103FD | 13-1513 | RECONDUCTOR PENN AVE & JERSEY AVE I | AP | 2.4 | 2 | 0 | 0 | 0 | 0
D103FD | 10-1513 | RECONDUCTOR PENN AVE & JERSEY AVE I | AP | 18.9 | 6.6 | 0 | 0 | 0 | 0
|  |  |  | -6.4 | 8.8 | 2 | 0 | 0 | 0 | 4.4
D105FX | 50-2316 | WALLKILL INDUSTRIAL PARK - RYKOWSKI | PR | 5.6 | -3.2 | 0 | 0 | 0 | 0
D105FX | 50-2316 | WALLKILL INDUSTRIAL PARK - RYKOWSKI | A3 | 7.7 | -4.4 | 0 | 0 | 0 | 0
D105FX | 50-2316 | WALLKILL INDUSTRIAL PARK - RYKOWSKI | A4 | 11.9 | -6.7 | 0 | 0 | 0 | 0
|  |  |  | 25.2 | -14.3 | 0 | 0 | 0 | 0 | 10.9
D109FX | 10-2317 | RD WIDENING - ROUTE 32 - WOODBURY - | CC | 0 | 0 | 0.1 | 0 | 0 | 0
D109FX | 13-2317 | RD WIDENING - ROUTE 32 - WOODBURY - | PR | -0.6 | 0 | 1.1 | -0.1 | 0.5 | 0.3
D109FX | 10-2317 | RD WIDENING - ROUTE 32 - WOODBURY - | MS | 0 | 0 | 1.1 | 0.1 | 0 | 0
D109FX | 13-2317 | RD WIDENING - ROUTE 32 - WOODBURY - | A3 | -0.9 | 0.1 | 1.4 | -0.2 | 0.8 | 0.7
D109FX | 13-2317 | RD WIDENING - ROUTE 32 - WOODBURY - | A4 | -1.4 | 0.1 | 2.2 | -0.3 | 1.2 | 0.9
D109FX | 10-2317 | RD WIDENING - ROUTE 32 - WOODBURY - | PR | -1.7 | 0.1 | 2.9 | -0.3 | 1.3 | 0.7
D109FX | 10-2317 | RD WIDENING - ROUTE 32 - WOODBURY - | A3 | -2.4 | 0.1 | 4.1 | -0.5 | 2.1 | 1.7
D109FX | 10-2317 | RD WIDENING - ROUTE 32 - WOODBURY - | A4 | -3.9 | 0.2 | 6.5 | -0.8 | 3.3 | 2.3
|  |  |  | -10.9 | 0.6 | 19.4 | -2.1 | 9.2 | 6.6 | 22.8
D110FX | 10-2073 | HARTLEY ROAD DOUBLE CIRCUIT STATION | CC | 0 | 4.3 | 0 | 0 | 0 | 0
D110FX | 13-2073 | HARTLEY ROAD DOUBLE CIRCUIT STATION | PR | 1.7 | 0.3 | 0 | 2.8 | 0.1 | 0
D110FX | 13-2073 | HARTLEY ROAD DOUBLE CIRCUIT STATION | A3 | 2.4 | 0.4 | 0 | 4.5 | 0.2 | 0
D110FX | 13-2073 | HARTLEY ROAD DOUBLE CIRCUIT STATION | A4 | 3.9 | 0.6 | 0 | 7.3 | 0.3 | 0
D110FX | 10-2073 | HARTLEY ROAD DOUBLE CIRCUIT STATION | PR | 7.8 | 1.3 | 0 | 12.9 | 0.6 | 0
D110FX | 10-2073 | HARTLEY ROAD DOUBLE CIRCUIT STATION | AP | 3.7 | 1.6 | 16.1 | 1.3 | 0 | 0
D110FX | 10-2073 | HARTLEY ROAD DOUBLE CIRCUIT STATION | A3 | 11 | 7.5 | 0 | 21.2 | 1 | 0
D110FX | 10-2073 | HARTLEY ROAD DOUBLE CIRCUIT STATION | MS | 0.4 | 52.9 | 0 | 0 | 0 | 0
D110FX | 10-2073 | HARTLEY ROAD DOUBLE CIRCUIT STATION | A4 | 18.1 | 20.8 | 0 | 33.9 | 1.5 | 0
|  |  |  | 49 | 89.7 | 16.1 | 83.9 | 3.7 | 0 | 242.4
D112FX | 53-2332 | 2008 CABLE REBUILD, 2100' BEAUMONT | A4 | 0 | 0 | 0.1 | 0 | 0 | 0
D112FX | 50-2332 | 2008 CABLE REBUILD, 2100' BEAUMONT | CC | 0 | 0 | 0.1 | 0 | 0 | 0
D112FX | 50-2332 | 2008 CABLE REBUILD, 2100' BEAUMONT | PR | 0 | 0 | 0.9 | -0.4 | 0 | 0
D112FX | 50-2332 | 2008 CABLE REBUILD, 2100' BEAUMONT | A3 | 0 | 0 | 1.5 | -0.5 | 0 | 0
D112FX | 50-2332 | 2008 CABLE REBUILD, 2100' BEAUMONT | MS | 0 | 0 | 1.5 | 0 | 0 | 0
D112FX | 50-2332 | 2008 CABLE REBUILD, 2100' BEAUMONT | A4 | 0 | 0 | 2.5 | -0.8 | 0 | 0
|  |  |  | 0 | 0 | 6.6 | -1.7 | 0 | 0 | 4.9
D116FX | 50-2333 | 2008 CABLE REBUILD, 1470' BRADLEY C | CC | 0 | 0 | 0 | 0 | 0 | 2.9
D116FX | 50-2333 | 2008 CABLE REBUILD, 1470' BRADLEY C | A3 | 0 | 0 | 0 | 0 | 0 | 7.1
D116FX | 50-2333 | 2008 CABLE REBUILD, 1470' BRADLEY C | A4 | 0 | 0 | 0 | 0 | 0 | 13.4
D116FX | 50-2333 | 2008 CABLE REBUILD, 1470' BRADLEY C | AP | 0 | 0 | 0 | 0 | 0 | 21.6
D116FX | 50-2333 | 2008 CABLE REBUILD, 1470' BRADLEY C | MS | 0 | 0 | 0 | 0 | 0 | 34.8
|  |  |  | 0 | 0 | 0 | 0 | 0 | 79.8 | 79.8
D117FX | 50-2334 | URD HIDDEN CREEK SECTION 1, MONROE, | CC | 0.1 | 0 | 1.3 | 1.3 | 0 | -8.2
D117FX | 50-2334 | URD HIDDEN CREEK SECTION 1, MONROE, | PR | 0 | 0 | 0 | 6.8 | -1 | 0
D117FX | 50-2334 | URD HIDDEN CREEK SECTION 1, MONROE, | A3 | 0.2 | 0 | 2.5 | 12.6 | -1.5 | 0
D117FX | 50-2334 | URD HIDDEN CREEK SECTION 1, MONROE, | A4 | 0.4 | 0 | 6.5 | 20.3 | -2.4 | 0
D117FX | 50-2334 | URD HIDDEN CREEK SECTION 1, MONROE, | MS | 0.9 | 0 | 15.6 | 16.5 | 0 | 0
|  |  |  | 1.6 | 0 | 25.9 | 57.5 | -4.9 | -8.2 | 71.9
D118FX | 50-2335 | URD WOODBURY JUNCTION, - PHASE 1A, | CC | 0 | 0 | 0.3 | 2.3 | -41.8 | 0.8
D118FX | 50-2335 | URD WOODBURY JUNCTION, - PHASE 1A, | PR | 0 | 0 | 0 | 3.4 | 6.3 | 0.8
D118FX | 50-2335 | URD WOODBURY JUNCTION, - PHASE 1A, | A3 | 0 | 0 | 0.7 | 8.6 | 9.9 | 3.4
D118FX | 50-2335 | URD WOODBURY JUNCTION, - PHASE 1A, | A4 | 0 | 0 | 1.8 | 15.6 | 15.5 | 5.7
D118FX | 50-2335 | URD WOODBURY JUNCTION, - PHASE 1A, | MS | 0 | 0 | 4.3 | 27.7 | 4.8 | 9.6
|  |  |  | 0 | 0 | 7.1 | 57.6 | -5.3 | 20.3 | 79.7
D120FX | 10-2346 | INSTALL 13.2KV CIRCUIT, RT 17M, HAR | A3 | 0.1 | 0 | 0 | 0 | 0 | 0
D120FX | 10-2346 | INSTALL 13.2KV CIRCUIT, RT 17M, HAR | A4 | 0.1 | 0 | 0 | 0 | 0 | 0
D120FX | 10-2346 | INSTALL 13.2KV CIRCUIT, RT 17M, HAR | AP | 7.1 | 0 | 0 | 0.5 | 0 | 0
|  |  |  | 7.3 | 0 | 0 | 0.5 | 0 | 0 | 7.8
D121BX | 10-2331 | SPARE 34.5 TO 13.8KV | PR | 1.3 | 1.8 | 1.1 | 0 | 0.3 | 0.3
D121BX | 10-2331 | SPARE 34.5 TO 13.8KV | A3 | 0.3 | 8 | 0.2 | 0 | 0.1 | 0.1
D121BX | 10-2331 | SPARE 34.5 TO 13.8KV | A4 | 1.5 | 11.9 | 1.2 | 0 | 0.3 | 0.3
D121BX | 10-2331 | SPARE 34.5 TO 13.8KV | AP | 0 | 92.8 | 0 | 0 | 2.3 | 0
|  |  |  | 3.1 | 114.5 | 2.5 | 0 | 3 | 0.7 | 123.8
D122CX | 53-2367 | CONGERS SUBSTATION U/G CIRCUIT EXIT | PR | 0 | 0 | 0 | 0.3 | -0.1 | 0
D122CX | 53-2367 | CONGERS SUBSTATION U/G CIRCUIT EXIT | A3 | 0 | 0 | 0 | 0.3 | -0.1 | 0
D122CX | 53-2367 | CONGERS SUBSTATION U/G CIRCUIT EXIT | A4 | 0 | 0 | 0 | 0.6 | -0.2 | 0
D122CX | 50-2367 | CONGERS SUBSTATION U/G CIRCUIT EXIT | CC | 0 | 0 | 0 | 9.4 | 0.1 | 0.1
D122CX | 50-2367 | CONGERS SUBSTATION U/G CIRCUIT EXIT | PR | 1.5 | 2.7 | 1.1 | 2.6 | 12.2 | 0.3
D122CX | 50-2367 | CONGERS SUBSTATION U/G CIRCUIT EXIT | A3 | 0.8 | 1.1 | 0.8 | 16.1 | 7.1 | 0.6
D122CX | 50-2367 | CONGERS SUBSTATION U/G CIRCUIT EXIT | AP | 0 | 0 | 0 | 0.5 | 50.7 | 0.2
D122CX | 50-2367 | CONGERS SUBSTATION U/G CIRCUIT EXIT | A4 | 2.1 | 3.4 | 1.7 | 36.9 | 17.9 | 0.9
D122CX | 50-2367 | CONGERS SUBSTATION U/G CIRCUIT EXIT | MS | 0 | 0 | 0 | 111.4 | 0.1 | 0
|  |  |  | 4.4 | 7.2 | 3.6 | 178.1 | 87.7 | 2.1 | 283.1
D125FX | 13-2369 | BLAISDELL RD, CIRCUIT 54-8-13 CIRCU | AP | 0 | 0 | 0 | 0 | 0 | 1.7
D125FX | 10-2369 | BLAISDELL RD, CIRCUIT 54-8-13 CIRCU | CC | 0 | 0 | 0.5 | 1.5 | 0 | 0
D125FX | 13-2369 | BLAISDELL RD, CIRCUIT 54-8-13 CIRCU | PR | 0 | 0 | 0.4 | 2.4 | 0.2 | -0.2
D125FX | 13-2369 | BLAISDELL RD, CIRCUIT 54-8-13 CIRCU | A3 | 0 | 0 | 0.5 | 3.9 | 0.3 | -0.3
D125FX | 13-2369 | BLAISDELL RD, CIRCUIT 54-8-13 CIRCU | A4 | 0 | 0 | 0.8 | 6.2 | 0.5 | -0.5
D125FX | 10-2369 | BLAISDELL RD, CIRCUIT 54-8-13 CIRCU | PR | 0 | 0 | 2.8 | 18.4 | 1.4 | -1.1
D125FX | 10-2369 | BLAISDELL RD, CIRCUIT 54-8-13 CIRCU | MS | 0 | 0 | 6.3 | 18.2 | -0.1 | 0
D125FX | 10-2369 | BLAISDELL RD, CIRCUIT 54-8-13 CIRCU | A3 | 0 | 0 | 4.8 | 32 | 2.3 | -2.5
D125FX | 10-2369 | BLAISDELL RD, CIRCUIT 54-8-13 CIRCU | AP | 0 | 0 | 10.3 | 26 | 12.7 | 2.4
D125FX | 10-2369 | BLAISDELL RD, CIRCUIT 54-8-13 CIRCU | A4 | 0 | 0 | 8.5 | 52.8 | 3.6 | -3.4
|  |  |  | 0 | 0 | 34.9 | 161.4 | 20.9 | -3.9 | 213.3
D128FX | 50-2389 | BRADLEY CORPORATE PARK, WESTERN HIG | CC | 0 | 3.9 | -9.4 | 0 | 0 | 0
D128FX | 50-2389 | BRADLEY CORPORATE PARK, WESTERN HIG | PR | 0 | 6 | -1.7 | 3.2 | -1.6 | 0
D128FX | 50-2389 | BRADLEY CORPORATE PARK, WESTERN HIG | A3 | 0 | 13.3 | -2.4 | 5 | -2.4 | 0
D128FX | 50-2389 | BRADLEY CORPORATE PARK, WESTERN HIG | A4 | 0 | 28.3 | -3.6 | 7.4 | -3.7 | 0
D128FX | 50-2389 | BRADLEY CORPORATE PARK, WESTERN HIG | MS | 0 | 46.1 | 0 | 0 | 0 | 0
|  |  |  | 0 | 97.6 | -17.1 | 15.6 | -7.7 | 0 | 88.4
D129FX | 50-2390 | 2008 CABLE REBUILD, RAMLAND ROAD, O | CC | 0 | 3.1 | 0.3 | -0.5 | 0 | 0
D129FX | 50-2390 | 2008 CABLE REBUILD, RAMLAND ROAD, O | A3 | 0 | 3.9 | 0.6 | -0.5 | 0.2 | 0.1
D129FX | 53-2390 | 2008 CABLE REBUILD, RAMLAND ROAD, O | AP | 0 | 0 | 0 | 0.8 | 0 | 11.4
D129FX | 50-2390 | 2008 CABLE REBUILD, RAMLAND ROAD, O | A4 | 0 | 12.4 | 1.6 | -1.6 | 0.2 | 0.1
D129FX | 50-2390 | 2008 CABLE REBUILD, RAMLAND ROAD, O | MS | 0 | 36.7 | 3.8 | -6.5 | -0.1 | 0
D129FX | 50-2390 | 2008 CABLE REBUILD, RAMLAND ROAD, O | AP | 0 | 0 | 0 | 34.3 | 17.7 | 20
|  |  |  | 0 | 56.1 | 6.3 | 26 | 18 | 31.6 | 138
D130FX | 10-2391 | MAPLE AVENUE RD WIDENING, MONSEY, N | CC | 0 | 0.4 | 1.3 | -0.1 | 0.2 | 0
D130FX | 13-2391 | MAPLE AVENUE RD WIDENING, MONSEY, N | PR | 0 | 0.4 | 4 | 3.1 | -0.7 | 0.1
D130FX | 13-2391 | MAPLE AVENUE RD WIDENING, MONSEY, N | A3 | 0 | 0.6 | 5.3 | 5 | -1.1 | 0.2
D130FX | 13-2391 | MAPLE AVENUE RD WIDENING, MONSEY, N | A4 | 0 | 1 | 8.2 | 8.1 | -1.7 | 0.2
D130FX | 10-2391 | MAPLE AVENUE RD WIDENING, MONSEY, N | PR | 0 | 1 | 9.3 | 7.2 | -1.6 | 0.2
D130FX | 10-2391 | MAPLE AVENUE RD WIDENING, MONSEY, N | MS | 0 | 4.9 | 16.1 | -1.8 | 2.6 | 0
D130FX | 10-2391 | MAPLE AVENUE RD WIDENING, MONSEY, N | A3 | 0 | 1.9 | 15.2 | 11.7 | -2.1 | 0.4
D130FX | 10-2391 | MAPLE AVENUE RD WIDENING, MONSEY, N | AP | 0 | 0 | 1.1 | 27.8 | 7.6 | 0.9
D130FX | 10-2391 | MAPLE AVENUE RD WIDENING, MONSEY, N | A4 | 0 | 3.9 | 26.2 | 18.6 | -3.1 | 0.6
|  |  |  | 0 | 14.1 | 86.7 | 79.6 | 0.1 | 2.6 | 183.1
D131FX | 10-2392 | PINE LAKES ESTATES / COUNTY RT 56 U | CC | 0 | 0 | 0.9 | 0 | 0 | 0.8
D131FX | 13-2392 | PINE LAKES ESTATES / COUNTY RT 56 U | PR | 0 | 0 | 0.3 | 1.6 | -0.1 | 0.3
D131FX | 10-2392 | PINE LAKES ESTATES / COUNTY RT 56 U | AP | 0 | 0 | 0 | 0 | 3 | 0
D131FX | 13-2392 | PINE LAKES ESTATES / COUNTY RT 56 U | A3 | 0 | 0 | 0.4 | 2.5 | -0.1 | 0.8
D131FX | 13-2392 | PINE LAKES ESTATES / COUNTY RT 56 U | A4 | 0 | 0 | 0.6 | 4.1 | -0.2 | 1
D131FX | 10-2392 | PINE LAKES ESTATES / COUNTY RT 56 U | PR | 0 | 0 | 1.3 | 7.3 | -0.4 | 1.5
D131FX | 10-2392 | PINE LAKES ESTATES / COUNTY RT 56 U | A3 | 0 | 0 | 3.7 | 11.9 | -0.6 | 5.8
D131FX | 10-2392 | PINE LAKES ESTATES / COUNTY RT 56 U | MS | 0 | 0 | 11.4 | 0 | 0 | 10.3
D131FX | 10-2392 | PINE LAKES ESTATES / COUNTY RT 56 U | A4 | 0 | 0 | 7.5 | 19.1 | -0.9 | 8.8
|  |  |  | 0 | 0 | 26.1 | 46.5 | 0.7 | 29.3 | 102.6
D132FX | 13-2393 | SCHUNEMUNK RD - WOODBURY, NY - LTS | MS | 0 | 0 | 0 | 0 | -5.1 | 0
D132FX | 10-2393 | SCHUNEMUNK RD - WOODBURY, NY - LTS | CC | 0 | 0 | 0.7 | 1.2 | -0.2 | 0
D132FX | 13-2393 | SCHUNEMUNK RD - WOODBURY, NY - LTS | PR | 0 | 0 | 1.8 | 0.5 | 2.2 | -0.5
D132FX | 13-2393 | SCHUNEMUNK RD - WOODBURY, NY - LTS | A3 | 0 | 0 | 2.4 | 0.9 | 3 | -1.2
D132FX | 13-2393 | SCHUNEMUNK RD - WOODBURY, NY - LTS | A4 | 0 | 0 | 3.7 | 1.4 | 4.3 | -1.7
D132FX | 10-2393 | SCHUNEMUNK RD - WOODBURY, NY - LTS | PR | 0 | 0 | 4.8 | 1.4 | 5.9 | -1.4
D132FX | 10-2393 | SCHUNEMUNK RD - WOODBURY, NY - LTS | A3 | 0 | 0 | 7.9 | 4.3 | 9.5 | -3.4
D132FX | 10-2393 | SCHUNEMUNK RD - WOODBURY, NY - LTS | AP | 0 | 0 | 15.7 | 10 | -5.6 | 0
D132FX | 10-2393 | SCHUNEMUNK RD - WOODBURY, NY - LTS | MS | 0 | 0 | 8.9 | 14.3 | -2 | 0
D132FX | 10-2393 | SCHUNEMUNK RD - WOODBURY, NY - LTS | A4 | 0 | 0 | 13.8 | 8.1 | 14.4 | -4.5
|  |  |  | 0 | 0 | 59.7 | 42.1 | 26.4 | -12.7 | 115.5
D133FX | 10-2400 | CONVERSION OF RTE 9W FROM 4.16KV TO | AP | 0 | 0 | 0.1 | 9.7 | -8.4 | 0
D133FX | 10-2400 | CONVERSION OF RTE 9W FROM 4.16KV TO | CC | 0 | 0.5 | 0.5 | 0.1 | 0.9 | 0.1
D133FX | 13-2400 | CONVERSION OF RTE 9W FROM 4.16KV TO | PR | 0 | 0.3 | 2.7 | 0.9 | 2.9 | 1.2
D133FX | 13-2400 | CONVERSION OF RTE 9W FROM 4.16KV TO | A3 | 0 | 0.4 | 3.6 | 1.4 | 4.6 | 2.8
D133FX | 13-2400 | CONVERSION OF RTE 9W FROM 4.16KV TO | A4 | 0 | 0.7 | 5.7 | 2.3 | 7.2 | 3.7
D133FX | 10-2400 | CONVERSION OF RTE 9W FROM 4.16KV TO | MS | 0 | 5.5 | 5.5 | 0.7 | 10.3 | 0.9
D133FX | 10-2400 | CONVERSION OF RTE 9W FROM 4.16KV TO | PR | 0 | 1 | 8.4 | 2.6 | 8.1 | 3.3
D133FX | 10-2400 | CONVERSION OF RTE 9W FROM 4.16KV TO | A3 | 0 | 1.9 | 11.5 | 4.3 | 14.4 | 8.2
D133FX | 10-2400 | CONVERSION OF RTE 9W FROM 4.16KV TO | A4 | 0 | 4 | 19.3 | 7 | 22.9 | 10.9
|  |  |  | 0 | 14.3 | 57.3 | 29 | 62.9 | 31.1 | 194.6
D134CC | 10-2403 | SMART GRID PROJECT FOR - COMMUNICAT | AP | 0 | 0 | 0 | 8.3 | 13 | 136 | 157.3
D134CD | 10-2404 | NY SMART GRID DISTRIBUTION PORTION | A3 | 0 | 0 | 0 | 0 | 0 | 0.6
D134CD | 10-2404 | NY SMART GRID DISTRIBUTION PORTION | A4 | 0 | 0 | 0 | 0.7 | 1.5 | 4.3
D134CD | 10-2404 | NY SMART GRID DISTRIBUTION PORTION | PR | 0 | 0 | 0 | 0.9 | 1.9 | 4.5
D134CD | 10-2404 | NY SMART GRID DISTRIBUTION PORTION | AP | 0 | 0 | 0 | 0 | 0 | 278.7
|  |  |  | 0 | 0 | 0 | 1.6 | 3.4 | 288.1 | 293.1
D136BX | 10-2409 | REPLACE TWELVE CIRCUIT BREAKERS - B | AP | 0 | 0 | 0 | 0 | 0 | 40 | 40
D137CX | 50-2410 | INSTALL NEW UNDERGROUND CIRCUIT EXI | CC | 0 | 0 | 0 | 0 | 0.3 | 0
D137CX | 50-2410 | INSTALL NEW UNDERGROUND CIRCUIT EXI | MS | 0 | 0 | 0 | 0 | 1.7 | 0
D137CX | 50-2410 | INSTALL NEW UNDERGROUND CIRCUIT EXI | A3 | 0 | 0 | 0.1 | 1.1 | 0.8 | 6.2
D137CX | 50-2410 | INSTALL NEW UNDERGROUND CIRCUIT EXI | PR | 0 | 0 | 0.3 | 1.2 | 3.7 | 4.2
D137CX | 50-2410 | INSTALL NEW UNDERGROUND CIRCUIT EXI | A4 | 0 | 0 | 0.3 | 2.2 | 4.2 | 9.5
D137CX | 50-2410 | INSTALL NEW UNDERGROUND CIRCUIT EXI | AP | 0 | 0 | 0 | 0 | 40.6 | 0
|  |  |  | 0 | 0 | 0.7 | 4.5 | 51.3 | 19.9 | 76.4
D140ZX | 13-2411 | DISPOSAL OF STORED SUBSTATION EQUIP | PR | 0 | 0 | 0 | 0 | 7.6 | -1.4
D140ZX | 13-2411 | DISPOSAL OF STORED SUBSTATION EQUIP | A3 | 0 | 0 | 0 | 0 | 7.7 | -1.4
D140ZX | 13-2411 | DISPOSAL OF STORED SUBSTATION EQUIP | A4 | 0 | 0 | 0 | 0 | 15.1 | -2.9
|  |  |  | 0 | 0 | 0 | 0 | 30.4 | -5.7 | 24.7
D143FX | 10-2440 | DOT BRIDGE & ROAD WIDENING - RIVERS | CC | 0 | 0 | 0 | 0 | 0 | 0.2
D143FX | 13-2440 | DOT BRIDGE & ROAD WIDENING - RIVERS | PR | 0 | 0 | 0 | 0 | 0.2 | 0.5
D143FX | 10-2440 | DOT BRIDGE & ROAD WIDENING - RIVERS | PR | 0 | 0 | 0 | 0 | 0.4 | 0.7
D143FX | 13-2440 | DOT BRIDGE & ROAD WIDENING - RIVERS | A3 | 0 | 0 | 0 | 0 | 0.4 | 1.1
D143FX | 13-2440 | DOT BRIDGE & ROAD WIDENING - RIVERS | A4 | 0 | 0 | 0 | 0 | 0.6 | 1.5
D143FX | 10-2440 | DOT BRIDGE & ROAD WIDENING - RIVERS | A3 | 0 | 0 | 0 | 0 | 0.6 | 2.3
D143FX | 10-2440 | DOT BRIDGE & ROAD WIDENING - RIVERS | MS | 0 | 0 | 0 | 0 | 0.4 | 2.6
D143FX | 10-2440 | DOT BRIDGE & ROAD WIDENING - RIVERS | A4 | 0 | 0 | 0 | 0 | 1 | 3.3
|  |  |  | 0 | 0 | 0 | 0 | 3.6 | 12.2 | 15.8
D148FX | 13-2450 | UPGRADE PINE HILL RD FOR GLENMERE B | MS | 0 | 0 | 0 | 0 | -0.9 | 0
D148FX | 10-2450 | UPGRADE PINE HILL RD FOR GLENMERE B | CC | 0 | 0 | 0 | 0 | 0.5 | 0.3
D148FX | 13-2450 | UPGRADE PINE HILL RD FOR GLENMERE B | PR | 0 | 0 | 0 | 0 | 1.2 | 1
D148FX | 13-2450 | UPGRADE PINE HILL RD FOR GLENMERE B | A3 | 0 | 0 | 0 | 0 | 1.8 | 2.4
D148FX | 13-2450 | UPGRADE PINE HILL RD FOR GLENMERE B | A4 | 0 | 0 | 0 | 0 | 2.7 | 3.1
D148FX | 10-2450 | UPGRADE PINE HILL RD FOR GLENMERE B | PR | 0 | 0 | 0 | 0 | 3.2 | 2.7
D148FX | 10-2450 | UPGRADE PINE HILL RD FOR GLENMERE B | MS | 0 | 0 | 0 | 0 | 5.5 | 4.2
D148FX | 10-2450 | UPGRADE PINE HILL RD FOR GLENMERE B | A3 | 0 | 0 | 0 | 0 | 5.8 | 7.3
D148FX | 10-2450 | UPGRADE PINE HILL RD FOR GLENMERE B | A4 | 0 | 0 | 0 | 0 | 9.4 | 10.1
|  |  |  | 0 | 0 | 0 | 0 | 29.2 | 31.1 | 60.3
D149FX | 10-2461 | KJ MOUNTAIN CORP - OWENS ROAD, GOSH | PR | 0 | 0 | 0 | 0 | 0 | 0.2
D149FX | 10-2461 | KJ MOUNTAIN CORP - OWENS ROAD, GOSH | A4 | 0 | 0 | 0 | 0 | 0 | 0.2
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0.4 | 0.4
D150BX | 10-2463 | RELOCATE TRANSMISSION LINES 841 & 8 | CC | 0 | 0 | 0 | 0 | 0 | 2.7
D150BX | 10-2463 | RELOCATE TRANSMISSION LINES 841 & 8 | A3 | 0 | 0 | 0 | 0 | 0 | 6.7
D150BX | 10-2463 | RELOCATE TRANSMISSION LINES 841 & 8 | A4 | 0 | 0 | 0 | 0 | 0 | 12.5
D150BX | 10-2463 | RELOCATE TRANSMISSION LINES 841 & 8 | MS | 0 | 0 | 0 | 0 | 0 | 32.5
|  |  |  | 0 | 0 | 0 | 0 | 0 | 54.4 | 54.4
D151CX | 10-7233 | REPLACEMENT OF OUTAGE MANAGEMENT SY | A3 | 0.7 | 0.1 | 0 | 0 | 0.9 | 0.5
D151CX | 10-7233 | REPLACEMENT OF OUTAGE MANAGEMENT SY | A4 | 6.1 | 4.8 | 2.5 | 0 | 1 | 0.6
D151CX | 10-7233 | REPLACEMENT OF OUTAGE MANAGEMENT SY | PR | 7 | 6.1 | 3.2 | 0 | 0 | 0
D151CX | 10-7233 | REPLACEMENT OF OUTAGE MANAGEMENT SY | AP | 75.2 | 0 | 0 | 87.5 | 25 | 145.7
|  |  |  | 89 | 11 | 5.7 | 87.5 | 26.9 | 146.8 | 366.9
D201CB | 10-2150 | 2008 PURCHASE PC HARDWARE DEVICES F | CC | 0 | 0.3 | 0 | 0 | 0 | 0.5
D201CB | 10-2150 | 2008 PURCHASE PC HARDWARE DEVICES F | A3 | 0.2 | 0.2 | 0.2 | 0.1 | 0.4 | 0.8
D201CB | 10-2150 | 2008 PURCHASE PC HARDWARE DEVICES F | A4 | 5.3 | 3.1 | 3.9 | 1 | 5.2 | 5.1
D201CB | 10-2150 | 2008 PURCHASE PC HARDWARE DEVICES F | PR | 6.6 | 3.8 | 4.7 | 0.9 | 12.3 | 5.4
D201CB | 10-2150 | 2008 PURCHASE PC HARDWARE DEVICES F | AP | 0 | -0.4 | 0 | 138.2 | 179 | 183.3
|  |  |  | 12.1 | 7 | 8.8 | 140.2 | 196.9 | 195.1 | 560.1
D206FX | 10-1482 | CONVERT CIRCUIT 9-2-48 TO 34KV | MS | 0 | 0 | 2.3 | -2.7 | 0 | 0
D206FX | 10-1482 | CONVERT CIRCUIT 9-2-48 TO 34KV | A3 | 0 | 0 | 0.4 | -0.3 | 0 | 0
D206FX | 10-1482 | CONVERT CIRCUIT 9-2-48 TO 34KV | A4 | 0 | 0 | 1 | -0.8 | 0 | 0
|  |  |  | 0 | 0 | 3.7 | -3.8 | 0 | 0 | -0.1
D209FX | 13-1972 | RECONDUCTOR EAST SHORE RD FROM HUNT | MS | 0 | -2.3 | 0 | 0 | 0 | 0
D209FX | 13-1972 | RECONDUCTOR EAST SHORE RD FROM HUNT | A4 | 0 | -0.7 | 0 | 0 | 0 | 0
D209FX | 13-1972 | RECONDUCTOR EAST SHORE RD FROM HUNT | A3 | 0 | -0.2 | 0 | 0 | 0 | 0
D209FX | 10-1972 | RECONDUCTOR EAST SHORE RD FROM HUNT | CC | 0.1 | 0 | 0 | 0 | 0 | 0
D209FX | 10-1972 | RECONDUCTOR EAST SHORE RD FROM HUNT | MS | 0.6 | 0.2 | 0 | 0 | 0 | 0
D209FX | 10-1972 | RECONDUCTOR EAST SHORE RD FROM HUNT | A3 | 0.5 | 1 | 0.2 | 0 | 0 | 0
D209FX | 10-1972 | RECONDUCTOR EAST SHORE RD FROM HUNT | A4 | 0.7 | 1.1 | 0.2 | 0.1 | 0 | 0
D209FX | 13-1972 | RECONDUCTOR EAST SHORE RD FROM HUNT | AP | 21.8 | 19.4 | -6.9 | -6.7 | 0 | 0
D209FX | 10-1972 | RECONDUCTOR EAST SHORE RD FROM HUNT | AP | 68.2 | 60.2 | -17.5 | -17 | 0 | 0
|  |  |  | 91.9 | 78.7 | -24 | -23.6 | 0 | 0 | 123
D245CX | 50-2156 | NEW WESTTOWN UNDERGROUND CIRCUIT 10 | CC | 0 | 0.1 | 0.1 | 0.5 | 1.5 | 8.6
D245CX | 50-2156 | NEW WESTTOWN UNDERGROUND CIRCUIT 10 | PR | 1.6 | 2.2 | 9.3 | 4.9 | 3.5 | 11.3
D245CX | 50-2156 | NEW WESTTOWN UNDERGROUND CIRCUIT 10 | A3 | 1.2 | 0.9 | 3.6 | 2.4 | 3.1 | 26
D245CX | 50-2156 | NEW WESTTOWN UNDERGROUND CIRCUIT 10 | A4 | 2.6 | 2.7 | 11.2 | 6.9 | 8.4 | 54.8
D245CX | 50-2156 | NEW WESTTOWN UNDERGROUND CIRCUIT 10 | MS | 0 | 0 | 0 | 0 | 16.7 | 104
D245CX | 50-2156 | NEW WESTTOWN UNDERGROUND CIRCUIT 10 | AP | 0 | 0 | 11.2 | 0 | 159 | 43.7
|  |  |  | 5.4 | 5.9 | 35.4 | 14.7 | 192.2 | 248.4 | 502
D284FX | 10-2236 | WASHINGTON AVENUE RECONDUCTOR - NEW | MS | -4.8 | 0 | 2.1 | 0 | 0 | 0
D284FX | 10-2236 | WASHINGTON AVENUE RECONDUCTOR - NEW | CC | -0.4 | 0 | 0.2 | 0 | 0 | 0
D284FX | 13-2236 | WASHINGTON AVENUE RECONDUCTOR - NEW | PR | 1.5 | 0 | 0 | 0 | 0 | 0
D284FX | 13-2236 | WASHINGTON AVENUE RECONDUCTOR - NEW | A3 | 2.1 | 0 | 0 | 0 | 0 | 0
D284FX | 10-2236 | WASHINGTON AVENUE RECONDUCTOR - NEW | PR | 3.1 | 0 | 0 | 0 | 0 | 0
D284FX | 13-2236 | WASHINGTON AVENUE RECONDUCTOR - NEW | A4 | 3.4 | 0 | 0 | 0 | 0 | 0
D284FX | 10-2236 | WASHINGTON AVENUE RECONDUCTOR - NEW | A3 | 3.6 | 0.1 | 0.4 | 0 | 0 | 0
D284FX | 10-2236 | WASHINGTON AVENUE RECONDUCTOR - NEW | A4 | 5.2 | 0.1 | 0.9 | 0 | 0 | 0
D284FX | 10-2236 | WASHINGTON AVENUE RECONDUCTOR - NEW | AP | 14.1 | 10.8 | 0 | 0.6 | 0 | 0
|  |  |  | 27.8 | 11 | 3.6 | 0.6 | 0 | 0 | 43
D294BX | 10-2131 | NEW CIRCUIT POSITION AT BLOOMING GR | CC | 0 | 0 | 0 | 0 | 0 | 0.1
D294BX | 10-2131 | NEW CIRCUIT POSITION AT BLOOMING GR | A3 | 0 | 0 | 0 | 0.8 | 0 | 0
D294BX | 10-2131 | NEW CIRCUIT POSITION AT BLOOMING GR | PR | 0 | 0 | 0 | 4.3 | 0.1 | 0
D294BX | 10-2131 | NEW CIRCUIT POSITION AT BLOOMING GR | A4 | 0 | 0 | 0 | 4.7 | 0.1 | 0
|  |  |  | 0 | 0 | 0 | 9.8 | 0.2 | 0.1 | 10.1
D319CA | 10-2158 | WORK MANAGEMENT SYSTEM (WMS) WEB DE | PR | 20 | 15.4 | 20.4 | 34.6 | 19.3 | 19.9
D319CA | 10-2158 | WORK MANAGEMENT SYSTEM (WMS) WEB DE | A4 | 15.4 | 11.8 | 15.7 | 26.7 | 14.9 | 45.2
D319CA | 10-2158 | WORK MANAGEMENT SYSTEM (WMS) WEB DE | AP | 100.3 | 6.2 | 47.3 | 48.8 | 46.1 | 56
|  |  |  | 135.7 | 33.4 | 83.4 | 110.1 | 80.3 | 121.1 | 564
D320BX | 10-2132 | SPARE 138X69 - 13.2KV 35MVA BANK - | PR | 0.3 | 0 | 0 | 0 | 0 | 0
D320BX | 10-2132 | SPARE 138X69 - 13.2KV 35MVA BANK - | A3 | 0.5 | 0 | 0 | 0 | 0 | 0
D320BX | 10-2132 | SPARE 138X69 - 13.2KV 35MVA BANK - | A4 | 0.8 | 0 | 0 | 0 | 0 | 0
|  |  |  | 1.6 | 0 | 0 | 0 | 0 | 0 | 1.6
D337FX | 10-1851 | SCHUTT ROAD / ROLLING MEADOWS ROAD | CC | 0 | 0 | 0.5 | 0 | 0 | 0
D337FX | 10-1851 | SCHUTT ROAD / ROLLING MEADOWS ROAD | A3 | 0 | 0 | 0.9 | 0 | 0 | 0
D337FX | 10-1851 | SCHUTT ROAD / ROLLING MEADOWS ROAD | A4 | 0 | 0 | 2.4 | 0 | 0 | 0
D337FX | 10-1851 | SCHUTT ROAD / ROLLING MEADOWS ROAD | MS | 0 | 0 | 5.8 | 0 | 0 | 0
|  |  |  | 0 | 0 | 9.6 | 0 | 0 | 0 | 9.6
D343FX | 10-2074 | ROUND HILL RD, DOUBLE CT - BLOOMING | CC | 0 | 0.2 | 0 | 0 | 0 | 0
D343FX | 13-2074 | ROUND HILL RD, DOUBLE CT - BLOOMING | PR | 1 | 0.3 | -0.1 | 0 | 0 | 0
D343FX | 13-2074 | ROUND HILL RD, DOUBLE CT - BLOOMING | A3 | 1.4 | 0.4 | -0.1 | 0 | 0 | 0
D343FX | 10-2074 | ROUND HILL RD, DOUBLE CT - BLOOMING | MS | 0 | 2 | 0 | 0 | 0 | 0
D343FX | 13-2074 | ROUND HILL RD, DOUBLE CT - BLOOMING | A4 | 2.3 | 0.6 | -0.2 | 0 | 0 | 0
D343FX | 10-2074 | ROUND HILL RD, DOUBLE CT - BLOOMING | PR | 7.4 | 2.2 | -0.6 | 0 | 0 | 0
D343FX | 10-2074 | ROUND HILL RD, DOUBLE CT - BLOOMING | A3 | 10.4 | 3.1 | -0.7 | 0 | 0 | 0
D343FX | 10-2074 | ROUND HILL RD, DOUBLE CT - BLOOMING | AP | 0 | 0 | 17 | 1.5 | 0 | 0
D343FX | 10-2074 | ROUND HILL RD, DOUBLE CT - BLOOMING | A4 | 17 | 5.5 | -1.2 | 0.1 | 0 | 0
|  |  |  | 39.5 | 14.3 | 14.1 | 1.6 | 0 | 0 | 69.5
D347FA | 10-2375 | BURLINGHAM RD-NA-SHO-PA TO HAMILTON | PR | 0 | 0 | 0.1 | 0 | 0 | 0
D347FA | 10-2375 | BURLINGHAM RD-NA-SHO-PA TO HAMILTON | A4 | 0 | 0 | 0.1 | 0 | 0 | 0
D347FA | 10-2375 | BURLINGHAM RD-NA-SHO-PA TO HAMILTON | AP | 0 | 0 | 0 | 0 | 2.4 | 2.4
|  |  |  | 0 | 0 | 0.2 | 0 | 2.4 | 2.4 | 5
D347FC | 10-2376 | COUNTY ROUTE 48-ROUTE 302 TO BIRLIN | PR | 0 | 0 | 0.1 | 0 | 0 | 0
D347FC | 10-2376 | COUNTY ROUTE 48-ROUTE 302 TO BIRLIN | A3 | 0 | 0 | 0.1 | 0.1 | 0 | 0
D347FC | 10-2376 | COUNTY ROUTE 48-ROUTE 302 TO BIRLIN | A4 | 0 | 0.1 | 0.1 | 0.1 | 0 | 0
D347FC | 10-2376 | COUNTY ROUTE 48-ROUTE 302 TO BIRLIN | AP | 0 | 4.8 | 10.4 | 8.4 | 0 | 0.5
|  |  |  | 0 | 4.9 | 10.7 | 8.6 | 0 | 0.5 | 24.7
D362FE | 10-2242 | SNAKE HILL RD - CRUSHER/STORMS RD D | CC | 2.1 | 0.8 | 1 | 0 | 0.2 | 0
D362FE | 13-2242 | SNAKE HILL RD - CRUSHER/STORMS RD D | PR | 2.8 | 2.7 | 0.6 | 1.3 | 0.2 | 0
D362FE | 13-2242 | SNAKE HILL RD - CRUSHER/STORMS RD D | A3 | 3.9 | 3.5 | 0.8 | 2.1 | 0.3 | 0
D362FE | 13-2242 | SNAKE HILL RD - CRUSHER/STORMS RD D | A4 | 6.4 | 5.8 | 1.3 | 3.4 | 0.5 | 0
D362FE | 10-2242 | SNAKE HILL RD - CRUSHER/STORMS RD D | PR | 13.6 | 13.1 | 3 | 6.4 | 1 | 0
D362FE | 10-2242 | SNAKE HILL RD - CRUSHER/STORMS RD D | AP | 10.2 | 20.6 | -0.3 | 6.3 | 5.1 | 1.1
D362FE | 10-2242 | SNAKE HILL RD - CRUSHER/STORMS RD D | MS | 25.5 | 9.6 | 11.5 | -0.1 | 2.6 | 0
D362FE | 10-2242 | SNAKE HILL RD - CRUSHER/STORMS RD D | A3 | 23.8 | 18.7 | 6.1 | 10.5 | 1.9 | 0
D362FE | 10-2242 | SNAKE HILL RD - CRUSHER/STORMS RD D | A4 | 42 | 32.2 | 11.3 | 16.7 | 3.1 | 37.6
|  |  |  | 130.3 | 107 | 35.3 | 46.6 | 14.9 | 38.7 | 372.8
D363FB | 10-1856 | LITTLE TOR RD TO PHILLIPS HILL RD D | A4 | -3.7 | 0 | 0 | 0 | 0 | 0
D363FB | 10-1856 | LITTLE TOR RD TO PHILLIPS HILL RD D | A3 | -2.2 | 0 | 0 | 0 | 0 | 0
D363FB | 10-1856 | LITTLE TOR RD TO PHILLIPS HILL RD D | PR | -1.6 | 0 | 0 | 0 | 0 | 0
D363FB | 10-1856 | LITTLE TOR RD TO PHILLIPS HILL RD D | AP | -1.6 | 0 | 0 | 0 | 0 | 0
D363FB | 13-1856 | LITTLE TOR RD TO PHILLIPS HILL RD D | A4 | -0.6 | 0 | 0 | 0 | 0 | 0
D363FB | 13-1856 | LITTLE TOR RD TO PHILLIPS HILL RD D | A3 | -0.4 | 0 | 0 | 0 | 0 | 0
D363FB | 13-1856 | LITTLE TOR RD TO PHILLIPS HILL RD D | PR | -0.3 | 0 | 0 | 0 | 0 | 0
|  |  |  | -10.4 | 0 | 0 | 0 | 0 | 0 | -10.4
D374BB | 10-2137 | REPLACE RELAYING FOR L-562 - CONGER | A4 | -0.4 | 0 | 0.1 | 0.3 | 0 | 0.3
D374BB | 10-2137 | REPLACE RELAYING FOR L-562 - CONGER | A3 | -0.1 | 0 | 0.1 | 0.1 | 0 | 0.2
D374BB | 10-2137 | REPLACE RELAYING FOR L-562 - CONGER | AP | 0 | 0 | 7.1 | 0 | 26.3 | 2.3
|  |  |  | -0.5 | 0 | 7.3 | 0.4 | 26.3 | 2.8 | 36.3
D374BC | 10-2138 | REPLACE RELAYING FOR L-562 - WEST N | A3 | 0 | 0 | 0.1 | 0.2 | 0 | 0.2
D374BC | 10-2138 | REPLACE RELAYING FOR L-562 - WEST N | PR | 0 | 0 | 0 | 1.2 | 0.2 | 0.1
D374BC | 10-2138 | REPLACE RELAYING FOR L-562 - WEST N | A4 | 0 | 0 | 0.1 | 1.3 | 0.2 | 0.3
D374BC | 10-2138 | REPLACE RELAYING FOR L-562 - WEST N | AP | 0 | 0 | 6.5 | 0 | 26.3 | 2.3
|  |  |  | 0 | 0 | 6.7 | 2.7 | 26.7 | 2.9 | 39
D383BX | 10-2094 | SHOEMAKER 138 KV YARD EXPANSION - P | A3 | 0 | 0 | 0 | 0.1 | 0 | 0
D383BX | 10-2094 | SHOEMAKER 138 KV YARD EXPANSION - P | A4 | 0 | 0 | 0 | 0.1 | 0 | 0
D383BX | 10-2094 | SHOEMAKER 138 KV YARD EXPANSION - P | AP | 4.2 | 1.5 | 1.2 | 2.6 | 0.3 | 0
|  |  |  | 4.2 | 1.5 | 1.2 | 2.8 | 0.3 | 0 | 10
D387BC | 10-2139 | LITTLE TOR SUBSTATION TRANSMISSION | A3 | 0 | 0.3 | 0.2 | 0.1 | 0 | 0.3
D387BC | 10-2139 | LITTLE TOR SUBSTATION TRANSMISSION | PR | 0 | 1.2 | 0.8 | 0.2 | 0 | 0.8
D387BC | 10-2139 | LITTLE TOR SUBSTATION TRANSMISSION | A4 | 0 | 1.2 | 0.8 | 0.3 | 0 | 1
D387BC | 10-2139 | LITTLE TOR SUBSTATION TRANSMISSION | AP | 3.2 | 0 | 2.6 | 0 | 0.2 | 0
|  |  |  | 3.2 | 2.7 | 4.4 | 0.6 | 0.2 | 2.1 | 13.2
D387BD | 10-2140 | REPLACE RELAYING FOR L-541 - BURNS | CC | 0 | 0 | 0 | 0 | 0 | 0.1
D387BD | 10-2140 | REPLACE RELAYING FOR L-541 - BURNS | MS | 0 | 0 | 0 | 0 | 0 | 1.4
D387BD | 13-2140 | REPLACE RELAYING FOR L-541 - BURNS | PR | 0 | 0 | 0 | 0 | 0 | 3.6
D387BD | 13-2140 | REPLACE RELAYING FOR L-541 - BURNS | A3 | 0 | 0 | 0 | 0 | 0 | 3.6
D387BD | 13-2140 | REPLACE RELAYING FOR L-541 - BURNS | A4 | 0 | 0 | 0 | 0 | 0 | 7.1
D387BD | 10-2140 | REPLACE RELAYING FOR L-541 - BURNS | A3 | 0.1 | 0.2 | 0.4 | 0.5 | 0.6 | 21.1
D387BD | 10-2140 | REPLACE RELAYING FOR L-541 - BURNS | PR | 0.6 | 1 | 1 | 2.8 | 2.7 | 24.6
D387BD | 10-2140 | REPLACE RELAYING FOR L-541 - BURNS | A4 | 0.6 | 1.1 | 1.2 | 3.1 | 3 | 45.1
D387BD | 10-2140 | REPLACE RELAYING FOR L-541 - BURNS | AP | 0 | 1.1 | 20.2 | 0 | 17.2 | 54.2
|  |  |  | 1.3 | 3.4 | 22.8 | 6.4 | 23.5 | 160.8 | 218.2
D387BE | 10-2141 | REPLACE RELAYING FOR LINE 541 - WES | CC | 0 | 0 | 0 | 0 | 0.2 | 0.1
D387BE | 10-2141 | REPLACE RELAYING FOR LINE 541 - WES | MS | 0 | 0 | 0 | 0 | 0 | 0.9
D387BE | 13-2141 | REPLACE RELAYING FOR LINE 541 - WES | PR | 0 | 0 | 0 | 0 | 0 | 3.6
D387BE | 13-2141 | REPLACE RELAYING FOR LINE 541 - WES | A3 | 0 | 0 | 0 | 0 | 0 | 3.7
D387BE | 13-2141 | REPLACE RELAYING FOR LINE 541 - WES | A4 | 0 | 0 | 0 | 0 | 0 | 7.3
D387BE | 10-2141 | REPLACE RELAYING FOR LINE 541 - WES | A3 | 0.2 | 0.4 | 0.5 | 0.6 | 0.6 | 23.9
D387BE | 10-2141 | REPLACE RELAYING FOR LINE 541 - WES | PR | 1 | 1.9 | 1.4 | 3.3 | 2.4 | 25.6
D387BE | 10-2141 | REPLACE RELAYING FOR LINE 541 - WES | A4 | 1.1 | 2 | 1.6 | 3.6 | 2.7 | 49
D387BE | 10-2141 | REPLACE RELAYING FOR LINE 541 - WES | AP | 0 | 2.1 | 20.2 | 0 | 17.2 | 54.3
|  |  |  | 2.3 | 6.4 | 23.7 | 7.5 | 23.1 | 168.4 | 231.4
D399FX | 10-2245 | SILVER LAKE CIRCUIT TO TOWER DRIVE | A3 | 0 | 0 | 0 | 0 | 0.1 | 0
D399FX | 10-2245 | SILVER LAKE CIRCUIT TO TOWER DRIVE | PR | 0 | 0 | 0.2 | 0 | 0 | 0
D399FX | 10-2245 | SILVER LAKE CIRCUIT TO TOWER DRIVE | A4 | 0 | 0 | 0.2 | 0 | 0.1 | 0
D399FX | 10-2245 | SILVER LAKE CIRCUIT TO TOWER DRIVE | AP | 0 | 0 | 0 | 3.1 | 4.8 | 1.9
|  |  |  | 0 | 0 | 0.4 | 3.1 | 5 | 1.9 | 10.4
D402FX | 50-1841 | 2007 U/G REBUILD - MINUTEMAN CIR, O | AP | 0 | 0 | 0 | -5.1 | 0 | 0 | -5.1
D416BX | 10-2003 | PURCHASE PROPERTY FOR A CENTRAL ROC | A3 | 0 | 0 | 0 | 0 | 0.1 | 0
D416BX | 10-2003 | PURCHASE PROPERTY FOR A CENTRAL ROC | A4 | 0 | 0 | 0 | 0 | 0.1 | 0
D416BX | 10-2003 | PURCHASE PROPERTY FOR A CENTRAL ROC | AP | 0.3 | 2.4 | 6.7 | 10.2 | 19.6 | 184.2
|  |  |  | 0.3 | 2.4 | 6.7 | 10.2 | 19.8 | 184.2 | 223.6
D417BX | 10-2004 | EVALUATION OF PROPERTIES FOR PURCHA | AP | 0 | 0 | 0 | -0.8 | 0 | 0 | -0.8
D422FX | 50-2028 | REPLACE U/G DIST CROSSING OF THRUWA | CC | 0 | 0 | 0 | 0 | 0 | 0.5
D422FX | 53-2028 | REPLACE U/G DIST CROSSING OF THRUWA | PR | 0 | 0 | 0 | 0 | 0.2 | 1.2
D422FX | 53-2028 | REPLACE U/G DIST CROSSING OF THRUWA | AP | 0 | 0 | 0 | 0 | 0 | 2
D422FX | 53-2028 | REPLACE U/G DIST CROSSING OF THRUWA | A3 | 0 | 0 | 0 | 0 | 0.4 | 2.1
D422FX | 53-2028 | REPLACE U/G DIST CROSSING OF THRUWA | A4 | 0 | 0 | 0 | 0 | 0.6 | 2.9
D422FX | 50-2028 | REPLACE U/G DIST CROSSING OF THRUWA | PR | 0 | 0 | 0 | 0 | 1.1 | 5.2
D422FX | 50-2028 | REPLACE U/G DIST CROSSING OF THRUWA | MS | 0 | 0 | 0 | 0 | 0 | 6.7
D422FX | 50-2028 | REPLACE U/G DIST CROSSING OF THRUWA | A3 | 0 | 0 | 0 | 0 | 1.7 | 11
D422FX | 50-2028 | REPLACE U/G DIST CROSSING OF THRUWA | A4 | 0 | 0 | 0 | 0 | 2.5 | 15.8
|  |  |  | 0 | 0 | 0 | 0 | 6.5 | 47.4 | 53.9
D424FX | 13-2035 | NYCDEP WWT PLANT - UPGRADE LINE TO | A3 | 0.1 | 0 | 0 | 0 | 0 | 0
D424FX | 13-2035 | NYCDEP WWT PLANT - UPGRADE LINE TO | A4 | 0.1 | 0 | 0 | 0 | 0 | 0
D424FX | 10-2035 | NYCDEP WWT PLANT - UPGRADE LINE TO | PR | 0.1 | 0 | 0 | 0 | 0 | 0
D424FX | 10-2035 | NYCDEP WWT PLANT - UPGRADE LINE TO | A3 | 0.2 | 0 | 0 | 0 | 0 | 0
D424FX | 10-2035 | NYCDEP WWT PLANT - UPGRADE LINE TO | A4 | 0.3 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0.8 | 0 | 0 | 0 | 0 | 0 | 0.8
D462BX | 10-2104 | REPLACE 69KV SWITCH FOR DISTRIBUTIO | CC | 0.2 | -37.8 | 0 | 0 | 0 | 0
D462BX | 13-2104 | REPLACE 69KV SWITCH FOR DISTRIBUTIO | CC | 0 | -22.4 | 0 | 0 | 0 | 0
D462BX | 10-2104 | REPLACE 69KV SWITCH FOR DISTRIBUTIO | A3 | 1.9 | 0 | 0 | 0 | 0 | 0
D462BX | 10-2104 | REPLACE 69KV SWITCH FOR DISTRIBUTIO | A4 | 2.3 | 0 | 0 | 0 | 0 | 0
D462BX | 10-2104 | REPLACE 69KV SWITCH FOR DISTRIBUTIO | AP | 13.1 | 0 | 0 | 0 | 0 | 0
|  |  |  | 17.5 | -60.2 | 0 | 0 | 0 | 0 | -42.7
D532FA | 10-1859 | REPLACE DEFECTIVE POLES CIRCUIT 5-1 | CC | 0 | 0 | 0 | 1 | 0 | 0.1
D532FA | 13-1859 | REPLACE DEFECTIVE POLES CIRCUIT 5-1 | PR | 0 | 0 | 0 | 0.1 | 1.2 | 0.5
D532FA | 10-1859 | REPLACE DEFECTIVE POLES CIRCUIT 5-1 | AP | 0 | 0 | 0 | 0 | 0 | 1.8
D532FA | 13-1859 | REPLACE DEFECTIVE POLES CIRCUIT 5-1 | A3 | 0 | 0 | 0 | 0.1 | 1.9 | 1.2
D532FA | 10-1859 | REPLACE DEFECTIVE POLES CIRCUIT 5-1 | PR | 0 | 0 | 0.1 | 0.2 | 2.9 | 1.3
D532FA | 13-1859 | REPLACE DEFECTIVE POLES CIRCUIT 5-1 | A4 | 0 | 0 | 0 | 0.2 | 2.9 | 1.6
D532FA | 10-1859 | REPLACE DEFECTIVE POLES CIRCUIT 5-1 | A3 | 0 | 0 | 0 | 1.8 | 4.8 | 3.5
D532FA | 10-1859 | REPLACE DEFECTIVE POLES CIRCUIT 5-1 | MS | 0 | 0 | 0 | 12.7 | 0 | 1.6
D532FA | 10-1859 | REPLACE DEFECTIVE POLES CIRCUIT 5-1 | A4 | 0 | 0 | 0.1 | 4.1 | 7.3 | 4.8
|  |  |  | 0 | 0 | 0.2 | 20.2 | 21 | 16.4 | 57.8
D546CX | 50-1918 | NEW MAINLINE CROSSING OVER RT 17 AL | CC | 0 | 0 | 0 | 0 | 5.5 | 0.1
D546CX | 50-1918 | NEW MAINLINE CROSSING OVER RT 17 AL | PR | 0 | 0.1 | 0 | 0 | 9.3 | -2.4
D546CX | 50-1918 | NEW MAINLINE CROSSING OVER RT 17 AL | A3 | 0 | 0 | 0 | 0 | 20.8 | -4.2
D546CX | 50-1918 | NEW MAINLINE CROSSING OVER RT 17 AL | A4 | 0 | 0.1 | 0.1 | 0 | 37.1 | -5.7
D546CX | 50-1918 | NEW MAINLINE CROSSING OVER RT 17 AL | MS | 0 | 0 | 0 | 0.1 | 65.3 | 0.8
|  |  |  | 0 | 0.2 | 0.1 | 0.1 | 138 | -11.4 | 127
D568FX | 50-1707 | REBUILD PARLIMENT DR - NEW CITY - 0 | A3 | 0.2 | 0 | 0 | 0 | 0 | 0
D568FX | 50-1707 | REBUILD PARLIMENT DR - NEW CITY - 0 | A4 | 0.2 | 0 | 0 | 0 | 0 | 0
D568FX | 50-1707 | REBUILD PARLIMENT DR - NEW CITY - 0 | AP | 18.3 | 0 | 0 | 0 | 0 | 0
|  |  |  | 18.7 | 0 | 0 | 0 | 0 | 0 | 18.7
D569FX | 50-2065 | SMITH FARM SUBDIVISION, LITTLE TOR | CC | -43.8 | 0.1 | 0.5 | 0 | 0 | 0
D569FX | 50-2065 | SMITH FARM SUBDIVISION, LITTLE TOR | PR | 3.5 | 3 | 1.3 | -0.1 | 0 | 0
D569FX | 50-2065 | SMITH FARM SUBDIVISION, LITTLE TOR | A3 | 6.5 | 4.3 | 2.8 | -0.2 | 0 | 0
D569FX | 50-2065 | SMITH FARM SUBDIVISION, LITTLE TOR | MS | 8.9 | 1.4 | 5.7 | 0 | 0 | 0
D569FX | 50-2065 | SMITH FARM SUBDIVISION, LITTLE TOR | A4 | 11.2 | 6.9 | 5.1 | -0.3 | 0 | 0
|  |  |  | -13.7 | 15.7 | 15.4 | -0.6 | 0 | 0 | 16.8
D570FX | 50-2066 | TERRACE VIEW ESTATES, SUBDIVISION U | MS | -2.4 | 1 | 0 | 0 | -5 | 0
D570FX | 50-2066 | TERRACE VIEW ESTATES, SUBDIVISION U | A4 | -1 | 0.3 | 0 | 0 | -1.2 | 0
D570FX | 50-2066 | TERRACE VIEW ESTATES, SUBDIVISION U | A3 | -0.4 | 0.1 | 0 | 0 | -0.5 | 0
D570FX | 50-2066 | TERRACE VIEW ESTATES, SUBDIVISION U | CC | -0.2 | 0.1 | 0 | 0 | -0.4 | 0
|  |  |  | -4 | 1.5 | 0 | 0 | -7.1 | 0 | -9.6
D572BA | 10-2076 | PURCHASE OF PROPERTY FOR NEW DEER P | A3 | 0 | 0 | 0 | 0.1 | 0 | 0
D572BA | 10-2076 | PURCHASE OF PROPERTY FOR NEW DEER P | A4 | 0 | 0 | 0 | 0.1 | 0 | 0
D572BA | 10-2076 | PURCHASE OF PROPERTY FOR NEW DEER P | AP | 5.6 | 1.8 | -0.3 | 1.6 | 1.8 | 6.8
|  |  |  | 5.6 | 1.8 | -0.3 | 1.8 | 1.8 | 6.8 | 17.5
D573FA | 10-2206 | RECONDUCTOR RTE 9W SPARKHILL TO PAL | CC | 0.9 | 0.8 | 0 | 0 | 0.1 | 0
D573FA | 13-2206 | RECONDUCTOR RTE 9W SPARKHILL TO PAL | PR | 2.7 | 3.4 | 1.2 | 1.2 | 0.1 | 0
D573FA | 13-2206 | RECONDUCTOR RTE 9W SPARKHILL TO PAL | A3 | 3.8 | 4.5 | 1.6 | 1.9 | 0.1 | 0
D573FA | 13-2206 | RECONDUCTOR RTE 9W SPARKHILL TO PAL | A4 | 6.2 | 7.4 | 2.5 | 3.1 | 0.2 | 0
D573FA | 10-2206 | RECONDUCTOR RTE 9W SPARKHILL TO PAL | MS | 11.3 | 9.3 | -0.3 | 0.3 | 1.2 | 0
D573FA | 10-2206 | RECONDUCTOR RTE 9W SPARKHILL TO PAL | PR | 8.9 | 11.1 | 3.8 | 3.9 | 0.3 | 0
D573FA | 10-2206 | RECONDUCTOR RTE 9W SPARKHILL TO PAL | A3 | 14.6 | 15.7 | 5.3 | 6.7 | 0.7 | 0.1
D573FA | 10-2206 | RECONDUCTOR RTE 9W SPARKHILL TO PAL | AP | 0.2 | 2.7 | 15.6 | 48 | 23 | 7.2
D573FA | 10-2206 | RECONDUCTOR RTE 9W SPARKHILL TO PAL | A4 | 25.2 | 27.4 | 8.1 | 10.6 | 1.2 | 26.1
|  |  |  | 73.8 | 82.3 | 37.8 | 75.7 | 26.9 | 33.4 | 329.9
D574FX | 50-2111 | BAKERTOWN ROAD SUB PHASE 1 - KIRYAS | CC | 3.6 | -10.3 | 0 | 0 | 0 | 0
D574FX | 50-2111 | BAKERTOWN ROAD SUB PHASE 1 - KIRYAS | PR | 3.1 | 3.4 | 0.7 | -0.1 | 0 | 0
D574FX | 50-2111 | BAKERTOWN ROAD SUB PHASE 1 - KIRYAS | AP | 15 | 3 | -2 | 0 | 0 | 0
D574FX | 50-2111 | BAKERTOWN ROAD SUB PHASE 1 - KIRYAS | A3 | 12.2 | 5.4 | 1 | -0.2 | 0 | 0
D574FX | 50-2111 | BAKERTOWN ROAD SUB PHASE 1 - KIRYAS | A4 | 25 | 9.3 | 1.5 | -0.3 | 0 | 0
D574FX | 50-2111 | BAKERTOWN ROAD SUB PHASE 1 - KIRYAS | MS | 43.7 | 6.1 | 0 | 0 | 0 | 0
|  |  |  | 102.6 | 16.9 | 1.2 | -0.6 | 0 | 0 | 120.1
D576FX | 10-2103 | STRAY VOLTAGE - ELECTRIC INFORMATIO | A4 | 4.5 | 6 | 6.2 | 3 | 2.6 | 2.7
D576FX | 10-2103 | STRAY VOLTAGE - ELECTRIC INFORMATIO | PR | 5.8 | 7.8 | 8.1 | 3.9 | 3.4 | 3.5
D576FX | 10-2103 | STRAY VOLTAGE - ELECTRIC INFORMATIO | AP | 17.3 | 26 | 13.4 | 1.3 | 32.1 | -8.1
|  |  |  | 27.6 | 39.8 | 27.7 | 8.2 | 38.1 | -1.9 | 139.5
D577BX | 10-2107 | REPLACEMENT OF TIE SWITCH T1-76-1 A | A3 | 0 | 0 | 0 | 0 | 0.1 | 0.1
D577BX | 10-2107 | REPLACEMENT OF TIE SWITCH T1-76-1 A | PR | 0 | 0 | 0 | 0 | 0.4 | 0.4
D577BX | 10-2107 | REPLACEMENT OF TIE SWITCH T1-76-1 A | A4 | 0 | 0 | 0 | 0 | 0.4 | 0.5
D577BX | 10-2107 | REPLACEMENT OF TIE SWITCH T1-76-1 A | CC | 0 | 0 | 0 | 1.9 | 0 | 0
D577BX | 10-2107 | REPLACEMENT OF TIE SWITCH T1-76-1 A | AP | 0 | -4.5 | 0 | 63.4 | -41 | 0
|  |  |  | 0 | -4.5 | 0 | 65.3 | -40.1 | 1 | 21.7
D578FX | 10-2251 | HILLCREST SCHOOL - ADDISON BOYCE RD | CC | 0 | 0.6 | 0 | 0 | 0 | 0
D578FX | 13-2251 | HILLCREST SCHOOL - ADDISON BOYCE RD | PR | 0 | 2 | -0.3 | 0 | 0 | 0.2
D578FX | 13-2251 | HILLCREST SCHOOL - ADDISON BOYCE RD | A3 | 0 | 2.6 | -0.5 | 0 | 0 | 0.5
D578FX | 10-2251 | HILLCREST SCHOOL - ADDISON BOYCE RD | PR | 0 | 4.1 | -0.7 | 0 | 0 | 0.4
D578FX | 13-2251 | HILLCREST SCHOOL - ADDISON BOYCE RD | A4 | 0 | 4.4 | -0.7 | 0 | 0 | 0.7
D578FX | 10-2251 | HILLCREST SCHOOL - ADDISON BOYCE RD | A3 | 0 | 6.2 | -1 | 0 | 0 | 1
D578FX | 10-2251 | HILLCREST SCHOOL - ADDISON BOYCE RD | MS | 0 | 6.8 | 0 | 0 | 0 | 0
D578FX | 10-2251 | HILLCREST SCHOOL - ADDISON BOYCE RD | A4 | 0 | 11.4 | -1.5 | 0 | 0 | 1.4
|  |  |  | 0 | 38.1 | -4.7 | 0 | 0 | 4.2 | 37.6
D579FX | 50-2252 | LIBERTY GREEN - WARWICK, NY | MS | 0.1 | 0 | 0 | 0 | 0 | 0
D579FX | 50-2252 | LIBERTY GREEN - WARWICK, NY | PR | 2.6 | -0.2 | 0 | 0 | 0 | 0
D579FX | 50-2252 | LIBERTY GREEN - WARWICK, NY | A3 | 3.7 | -0.3 | 0 | 0 | 0 | 0
D579FX | 50-2252 | LIBERTY GREEN - WARWICK, NY | A4 | 5.7 | -0.5 | 0 | 0 | 0 | 0
D579FX | 50-2252 | LIBERTY GREEN - WARWICK, NY | AP | 14.4 | 0 | 0 | 0 | 0 | 0
|  |  |  | 26.5 | -1 | 0 | 0 | 0 | 0 | 25.5
D580FX | 10-2253 | TUXEDO GOLF COURSE PUMPHOUSE, | MS | 0.4 | 0 | 0 | 0 | -0.2 | 0
D580FX | 13-2253 | TUXEDO GOLF COURSE PUMPHOUSE, | PR | -0.6 | 2 | 1.1 | -0.3 | 0 | 0
D580FX | 13-2253 | TUXEDO GOLF COURSE PUMPHOUSE, | A3 | -0.9 | 2.6 | 1.5 | -0.4 | 0 | 0
D580FX | 10-2253 | TUXEDO GOLF COURSE PUMPHOUSE, | PR | -1.1 | 3.6 | 2.1 | -0.5 | 0 | 0
D580FX | 13-2253 | TUXEDO GOLF COURSE PUMPHOUSE, | A4 | -1.4 | 4.2 | 2.4 | -0.7 | 0 | 0
D580FX | 10-2253 | TUXEDO GOLF COURSE PUMPHOUSE, | A3 | -1.5 | 4.8 | 2.9 | -0.7 | 0 | 0
D580FX | 10-2253 | TUXEDO GOLF COURSE PUMPHOUSE, | A4 | -2.4 | 7.9 | 4.4 | -1.2 | 0 | 0
D580FX | 10-2253 | TUXEDO GOLF COURSE PUMPHOUSE, | AP | 0 | 0 | 4 | 5.6 | 2.3 | 0.2
|  |  |  | -7.5 | 25.1 | 18.4 | 1.8 | 2.1 | 0.2 | 40.1
D581FX | 10-2254 | ROUTE 306 CIRCUIT 44-4-13 UPGRADE & | CC | 0.2 | -0.1 | 0.1 | 0 | -0.2 | 0.1
D581FX | 13-2254 | ROUTE 306 CIRCUIT 44-4-13 UPGRADE & | PR | 0.7 | 0.2 | 0 | 0 | 0 | 0
D581FX | 10-2254 | ROUTE 306 CIRCUIT 44-4-13 UPGRADE & | MS | 1.9 | -0.7 | 0.8 | 0 | -1.8 | 0.8
D581FX | 13-2254 | ROUTE 306 CIRCUIT 44-4-13 UPGRADE & | A3 | 1 | 0.3 | 0 | 0 | 0 | 0
D581FX | 13-2254 | ROUTE 306 CIRCUIT 44-4-13 UPGRADE & | A4 | 1.7 | 0.5 | 0 | 0 | 0 | 0
D581FX | 10-2254 | ROUTE 306 CIRCUIT 44-4-13 UPGRADE & | PR | 3.5 | 1.2 | 0 | 0 | 0 | 0
D581FX | 10-2254 | ROUTE 306 CIRCUIT 44-4-13 UPGRADE & | A3 | 5.6 | 1.6 | 0.2 | 0 | -0.2 | 0.2
D581FX | 10-2254 | ROUTE 306 CIRCUIT 44-4-13 UPGRADE & | A4 | 9.1 | 2.4 | 0.4 | 0 | -0.4 | 0.3
D581FX | 10-2254 | ROUTE 306 CIRCUIT 44-4-13 UPGRADE & | AP | 11.7 | 9.3 | 1.2 | 0 | 0 | 0
|  |  |  | 35.4 | 14.7 | 2.7 | 0 | -2.6 | 1.4 | 51.6
D582FX | 10-2256 | CHESTER DISTRIBUTION PART 1 - LEONE | PR | 0 | 0 | 0 | 0 | 0.3 | 0
D582FX | 10-2256 | CHESTER DISTRIBUTION PART 1 - LEONE | A4 | 0 | 0 | 0 | 0 | 0.3 | 0
D582FX | 10-2256 | CHESTER DISTRIBUTION PART 1 - LEONE | AP | 0.2 | 0 | 0 | 0 | 3.3 | 0
|  |  |  | 0.2 | 0 | 0 | 0 | 3.9 | 0 | 4.1
D585CX | 50-2265 | RIVERSIDE AVE. UNDERGROUND MAINLINE | CC | 0 | 0 | 0 | 0 | 0.3 | 1.7
D585CX | 50-2265 | RIVERSIDE AVE. UNDERGROUND MAINLINE | PR | 0 | 0 | 0 | 0.3 | 0 | 3.2
D585CX | 50-2265 | RIVERSIDE AVE. UNDERGROUND MAINLINE | A3 | 0 | 0 | 0 | 0 | 0.4 | 10.2
D585CX | 50-2265 | RIVERSIDE AVE. UNDERGROUND MAINLINE | A4 | 0 | 0 | 0 | 0.3 | 0.8 | 16.1
D585CX | 50-2265 | RIVERSIDE AVE. UNDERGROUND MAINLINE | MS | 0 | 0 | 0 | 0 | 3.4 | 20.3
|  |  |  | 0 | 0 | 0 | 0.6 | 4.9 | 51.5 | 57
D586CX | 50-2266 | WHISPERING HILLS VOLTAGE CONVERSION | PR | -0.2 | 0 | 0 | 0 | 0 | 0
D586CX | 53-2266 | WHISPERING HILLS VOLTAGE CONVERSION | PR | 0.4 | 0 | 0 | 0 | 0 | 0
D586CX | 53-2266 | WHISPERING HILLS VOLTAGE CONVERSION | A3 | 0.5 | 0 | 0 | 0 | 0 | 0
D586CX | 53-2266 | WHISPERING HILLS VOLTAGE CONVERSION | A4 | 0.8 | 0 | 0 | 0 | 0 | 0
D586CX | 50-2266 | WHISPERING HILLS VOLTAGE CONVERSION | CC | 1 | 0 | 0 | 0 | 0 | 0
D586CX | 50-2266 | WHISPERING HILLS VOLTAGE CONVERSION | AP | 1.4 | 0 | 0 | 0 | 0 | 0
D586CX | 50-2266 | WHISPERING HILLS VOLTAGE CONVERSION | A3 | 2.1 | 0 | 0 | 0 | 0 | 0
D586CX | 50-2266 | WHISPERING HILLS VOLTAGE CONVERSION | A4 | 5 | 0 | 0 | 0 | 0 | 0
D586CX | 50-2266 | WHISPERING HILLS VOLTAGE CONVERSION | MS | 12.9 | 0 | 0 | 0 | 0 | 0
|  |  |  | 23.9 | 0 | 0 | 0 | 0 | 0 | 23.9
D587FX | 50-2267 | URD WOODSIDE KNOLLS II - MIDDLETOWN | CC | 0 | 0 | 0 | 0 | -10.1 | 0
D587FX | 50-2267 | URD WOODSIDE KNOLLS II - MIDDLETOWN | PR | 0.7 | -0.2 | 0 | 0 | 0 | 0
D587FX | 50-2267 | URD WOODSIDE KNOLLS II - MIDDLETOWN | A3 | 1 | -0.3 | 0 | 0 | 0 | 0
D587FX | 50-2267 | URD WOODSIDE KNOLLS II - MIDDLETOWN | A4 | 1.6 | -0.5 | 0 | 0 | 0 | 0
|  |  |  | 3.3 | -1 | 0 | 0 | -10.1 | 0 | -7.8
D588FX | 10-2268 | MEYERSON ROAD CONVERSION | A4 | -1.1 | 0 | -0.3 | 0 | 0 | 0
D588FX | 10-2268 | MEYERSON ROAD CONVERSION | A3 | -0.7 | 0 | -0.1 | 0 | 0 | 0
D588FX | 10-2268 | MEYERSON ROAD CONVERSION | MS | 0 | 0 | -0.7 | 0 | 0 | 0
D588FX | 10-2268 | MEYERSON ROAD CONVERSION | PR | -0.5 | 0 | 0 | 0 | 0 | 0
D588FX | 13-2268 | MEYERSON ROAD CONVERSION | A4 | -0.2 | 0 | 0 | 0 | 0 | 0
D588FX | 10-2268 | MEYERSON ROAD CONVERSION | CC | 0 | 0 | -0.1 | 0 | 0 | 0
D588FX | 13-2268 | MEYERSON ROAD CONVERSION | PR | -0.1 | 0 | 0 | 0 | 0 | 0
D588FX | 13-2268 | MEYERSON ROAD CONVERSION | A3 | -0.1 | 0 | 0 | 0 | 0 | 0
|  |  |  | -2.7 | 0 | -1.2 | 0 | 0 | 0 | -3.9
D590FX | 10-2269 | MCNAMARA ROAD RECONDUCTOR - NEW HEM | PR | 0 | 0 | 0.9 | 0 | 0 | 0
D590FX | 10-2269 | MCNAMARA ROAD RECONDUCTOR - NEW HEM | CC | 0 | 4.9 | 0.5 | 0 | 0 | 0.2
D590FX | 10-2269 | MCNAMARA ROAD RECONDUCTOR - NEW HEM | A3 | 0 | 6.2 | 1.3 | 0.8 | 0.1 | 0.6
D590FX | 13-2269 | MCNAMARA ROAD RECONDUCTOR - NEW HEM | AP | 0 | 10.5 | 13.7 | 0 | 0 | 0
D590FX | 10-2269 | MCNAMARA ROAD RECONDUCTOR - NEW HEM | A4 | 0 | 19.6 | 3.6 | 0.8 | 0.2 | 1
D590FX | 10-2269 | MCNAMARA ROAD RECONDUCTOR - NEW HEM | MS | 0 | 58.2 | 6.2 | 0 | 0.6 | 2.1
D590FX | 10-2269 | MCNAMARA ROAD RECONDUCTOR - NEW HEM | AP | 0 | 30.7 | 53.8 | 15.1 | 67.3 | 94.4
|  |  |  | 0 | 130.1 | 80 | 16.7 | 68.2 | 98.3 | 393.3
D591BX | 10-2280 | SWINGING BRIDGE TRANSFORMER PAD REP | A3 | 0 | 0 | 0.1 | 0 | 0 | 0
D591BX | 10-2280 | SWINGING BRIDGE TRANSFORMER PAD REP | A4 | 0 | 0 | 0.1 | 0 | 0 | 0
D591BX | 10-2280 | SWINGING BRIDGE TRANSFORMER PAD REP | AP | -9.8 | 0 | 10.5 | 0 | 0 | 0
D591BX | 13-2280 | SWINGING BRIDGE TRANSFORMER PAD REP | AP | 0 | 8.9 | 0 | 0 | 0 | 0
|  |  |  | -9.8 | 8.9 | 10.7 | 0 | 0 | 0 | 9.8
D593FX | 13-2281 | COUNTY HIGHWAY 105-RT 17 TO SPRING | A4 | 0 | 0 | 0 | 0 | 0.1 | 0
D593FX | 10-2281 | COUNTY HIGHWAY 105-RT 17 TO SPRING | PR | 0 | 0 | 0.1 | 0 | 0.1 | -0.1
D593FX | 10-2281 | COUNTY HIGHWAY 105-RT 17 TO SPRING | CC | 0 | 0 | 0 | 0 | 0.4 | 0
D593FX | 10-2281 | COUNTY HIGHWAY 105-RT 17 TO SPRING | A3 | 0 | 0 | 0 | 0 | 0.8 | -0.2
D593FX | 10-2281 | COUNTY HIGHWAY 105-RT 17 TO SPRING | A4 | 0 | 0 | 0.1 | 0 | 1.6 | -0.2
D593FX | 10-2281 | COUNTY HIGHWAY 105-RT 17 TO SPRING | AP | 1.1 | 0 | 0.6 | 0 | 0 | 0
D593FX | 10-2281 | COUNTY HIGHWAY 105-RT 17 TO SPRING | MS | 0 | 0 | 0 | 0 | 5 | 0
|  |  |  | 1.1 | 0 | 0.8 | 0 | 8 | -0.5 | 9.4
D594FX | 10-2282 | COUNTY HIGHWAY 105-RT 17 TO ACRES R | AP | 0.5 | 0 | 0.2 | 0 | 0 | 0 | 0.7
D595CX | 50-2284 | REPLACE CIRCUITS 21-13 & 21-14 - WE | MS | 0 | -0.1 | 0 | 0 | 0 | 0
D595CX | 50-2284 | REPLACE CIRCUITS 21-13 & 21-14 - WE | AP | 0.1 | 0 | 0 | 0 | 0 | 0
D595CX | 50-2284 | REPLACE CIRCUITS 21-13 & 21-14 - WE | A3 | 0.2 | 0.4 | 0.3 | 0 | 0 | 0.4
D595CX | 50-2284 | REPLACE CIRCUITS 21-13 & 21-14 - WE | PR | 0.9 | 2.1 | 1.2 | 0 | 0 | 1.7
D595CX | 50-2284 | REPLACE CIRCUITS 21-13 & 21-14 - WE | A4 | 1 | 2.2 | 1.3 | 0 | 0 | 1.8
|  |  |  | 2.2 | 4.6 | 2.8 | 0 | 0 | 3.9 | 13.5
D597FX | 10-2297 | SOUTH GATE ROAD PART 1 | CC | 0 | 0 | 1.5 | 1 | 0 | 0
D597FX | 13-2297 | SOUTH GATE ROAD PART 1 | PR | 0 | 0 | 1 | 1.7 | -0.4 | 1.2
D597FX | 13-2297 | SOUTH GATE ROAD PART 1 | A3 | 0 | 0 | 1.3 | 2.7 | -0.7 | 2.9
D597FX | 10-2297 | SOUTH GATE ROAD PART 1 | PR | 0 | 0 | 2.5 | 4.4 | -1.1 | 3.1
D597FX | 13-2297 | SOUTH GATE ROAD PART 1 | A4 | 0 | 0 | 2 | 4.3 | -1.1 | 3.8
D597FX | 10-2297 | SOUTH GATE ROAD PART 1 | AP | 0 | 0 | 2.6 | 20.8 | -5.2 | 0.5
D597FX | 10-2297 | SOUTH GATE ROAD PART 1 | A3 | 0 | 0 | 6.3 | 8.7 | -1.8 | 7.5
D597FX | 10-2297 | SOUTH GATE ROAD PART 1 | MS | 0 | 0 | 18.1 | 12.3 | 0 | 0
D597FX | 10-2297 | SOUTH GATE ROAD PART 1 | A4 | 0 | 0 | 12.8 | 15 | -2.8 | 10
|  |  |  | 0 | 0 | 48.1 | 70.9 | -13.1 | 29 | 134.9
T120BX | 10-6583 | LINE 11/14 69KV DOUBLE CIRCUIT UPGR | A3 | 0 | 0.1 | 0 | 0 | 0 | 0
T120BX | 10-6583 | LINE 11/14 69KV DOUBLE CIRCUIT UPGR | A4 | 0 | 0.1 | 0 | 0 | 0 | 0
T120BX | 10-6583 | LINE 11/14 69KV DOUBLE CIRCUIT UPGR | AP | 10.4 | 0.9 | 0 | 0 | 0 | 0
|  |  |  | 10.4 | 1.1 | 0 | 0 | 0 | 0 | 11.5
T150BX | 10-1466 | TRANSMISSION LINE 26 UPGRADE - NY | A3 | 0 | 0.1 | 0.1 | 0.3 | 0 | 0
T150BX | 10-1466 | TRANSMISSION LINE 26 UPGRADE - NY | PR | 0.1 | 0.3 | 0.3 | 0.3 | 0.3 | 0
T150BX | 10-1466 | TRANSMISSION LINE 26 UPGRADE - NY | A4 | 0.1 | 0.3 | 0.3 | 0.6 | 0.3 | 0
T150BX | 10-1466 | TRANSMISSION LINE 26 UPGRADE - NY | AP | 0 | 0 | 23.8 | 0 | 0 | 0.4
|  |  |  | 0.2 | 0.7 | 24.5 | 1.2 | 0.6 | 0.4 | 27.6
T168CX | 10-1815 | LOVETT PUMPING PLANT UPGRADES FOR L | A3 | 0 | 0 | 0 | 0 | 5 | -1.3
T168CX | 10-1815 | LOVETT PUMPING PLANT UPGRADES FOR L | PR | 1.9 | 0.6 | 0.2 | 0 | 4.6 | -0.4
T168CX | 10-1815 | LOVETT PUMPING PLANT UPGRADES FOR L | A4 | 1.5 | 0.5 | 0.2 | 0 | 9.6 | -2
T168CX | 10-1815 | LOVETT PUMPING PLANT UPGRADES FOR L | AP | 0 | 0 | 0 | 0 | 140.9 | 0
|  |  |  | 3.4 | 1.1 | 0.4 | 0 | 160.1 | -3.7 | 161.3
T296BA | 10-2062 | PURCHASE OF PROPERTY FOR NEW DECKER | CC | 0 | 0 | 0 | 0.3 | 0.4 | 0.2
T296BA | 10-2062 | PURCHASE OF PROPERTY FOR NEW DECKER | A3 | 0.2 | 0.6 | 1.3 | 0.7 | 0.8 | 1.2
T296BA | 10-2062 | PURCHASE OF PROPERTY FOR NEW DECKER | PR | 0.8 | 2.8 | 6.2 | 3.9 | 6.5 | 3.9
T296BA | 10-2062 | PURCHASE OF PROPERTY FOR NEW DECKER | A4 | 1 | 3 | 6.4 | 4.2 | 6.4 | 4.7
T296BA | 10-2062 | PURCHASE OF PROPERTY FOR NEW DECKER | AP | 7.7 | 1.9 | 7.1 | 3.3 | 8.1 | 0.8
|  |  |  | 9.7 | 8.3 | 21 | 12.4 | 22.2 | 10.8 | 84.4
T297BX | 10-1468 | REPLACE UPS BATTERIES A&B AT SVOC | PR | 0.3 | 0 | 0 | 0 | 0 | 0
T297BX | 10-1468 | REPLACE UPS BATTERIES A&B AT SVOC | A3 | 0.4 | 0.6 | 0 | 0 | 0 | 0
T297BX | 10-1468 | REPLACE UPS BATTERIES A&B AT SVOC | A4 | 0.7 | 0.7 | 0 | 0 | 0 | 0
T297BX | 10-1468 | REPLACE UPS BATTERIES A&B AT SVOC | AP | 0 | 62 | 0 | 0 | 0 | 0
|  |  |  | 1.4 | 63.3 | 0 | 0 | 0 | 0 | 64.7
T298BX | 10-2149 | PRELIMINARY ENG., REPLACE FIRE SUPP | A3 | 0 | 0 | 0.1 | 0 | 0 | 0
T298BX | 10-2149 | PRELIMINARY ENG., REPLACE FIRE SUPP | PR | 0 | 0 | 0.5 | 0 | 0 | 0
T298BX | 10-2359 | PRELIMINARY ENG., REPLACE FIRE SUPP | A3 | 0.1 | 0 | -0.1 | 0.1 | 0 | 0.5
T298BX | 10-2149 | PRELIMINARY ENG., REPLACE FIRE SUPP | A4 | 0 | 0 | 0.6 | 0 | 0 | 0
T298BX | 10-2359 | PRELIMINARY ENG., REPLACE FIRE SUPP | PR | 0.5 | 0 | -0.5 | 0.5 | 0 | 1.4
T298BX | 10-2359 | PRELIMINARY ENG., REPLACE FIRE SUPP | A4 | 0.6 | 0 | -0.6 | 0.6 | 0 | 1.8
|  |  |  | 1.2 | 0 | 0 | 1.2 | 0 | 3.7 | 6.1
T446ZX | 10-1756 | REBUILD FOUR 345KV PK-4 COGENEL BRE | AP | 0 | 0 | -59.7 | 0 | 0 | 0
T446ZX | 10-1756 | REBUILD FOUR 345KV PK-4 COGENEL BRE | A3 | 0 | 0 | 0 | 4.3 | 0 | 0
T446ZX | 10-1756 | REBUILD FOUR 345KV PK-4 COGENEL BRE | A4 | 0 | 0 | 0 | 4.6 | 0 | 0
T446ZX | 10-1756 | REBUILD FOUR 345KV PK-4 COGENEL BRE | CC | 51.3 | 0 | 0 | 0 | 0 | 0
|  |  |  | 51.3 | 0 | -59.7 | 8.9 | 0 | 0 | 0.5
T447BX | 10-2412 | INSTALL CONDUIT IN THE MONSEY SUBST | A3 | 0 | 0 | 0 | 0 | 0 | 0.1
T447BX | 10-2412 | INSTALL CONDUIT IN THE MONSEY SUBST | PR | 0 | 0 | 0 | 0 | 0 | 0.2
T447BX | 10-2412 | INSTALL CONDUIT IN THE MONSEY SUBST | A4 | 0 | 0 | 0 | 0 | 0 | 0.2
T447BX | 10-1927 | TRANSMISSION LINE 75 POLE REPLACEME | AP | 0 | 0 | 0.8 | 0 | 0 | 6.7
|  |  |  | 0 | 0 | 0.8 | 0 | 0 | 7.2 | 8
T455BX | 10-2020 | INSTALL RIP RAP FOR 2 STRUCTURES ON | CC | 0.1 | 0 | 0 | 0 | 0 | 0
T455BX | 10-2020 | INSTALL RIP RAP FOR 2 STRUCTURES ON | A3 | 0.7 | 0.7 | 1.7 | 0.3 | 0 | 0
T455BX | 10-2020 | INSTALL RIP RAP FOR 2 STRUCTURES ON | PR | 6.9 | 3.6 | 0.2 | 0 | 0 | 0
T455BX | 10-2020 | INSTALL RIP RAP FOR 2 STRUCTURES ON | A4 | 6.4 | 3.7 | 2 | 0.3 | 0 | 0
T455BX | 10-2020 | INSTALL RIP RAP FOR 2 STRUCTURES ON | AP | 11.7 | -153 | 189.4 | 1.9 | 0 | 0
|  |  |  | 25.8 | -145 | 193.3 | 2.5 | 0 | 0 | 76.6
T457ZX | 10-2046 | REPLACE WINDOW AC UNITS WITH SPLIT | AP | -47.8 | 79.2 | -43.1 | 0 | 0 | 0
T457ZX | 10-2046 | REPLACE WINDOW AC UNITS WITH SPLIT | A3 | 0 | 0.3 | 0.5 | 0 | 0 | 0
T457ZX | 10-2046 | REPLACE WINDOW AC UNITS WITH SPLIT | A4 | 0 | 0.3 | 0.5 | 0 | 0 | 0
|  |  |  | -47.8 | 79.8 | -42.1 | 0 | 0 | 0 | -10.1
T458BX | 10-2075 | RELOCATE T/L 551/561 STRUCTURES 91 | CC | 0.2 | 0 | 0 | 3 | 0.4 | -254.4
T458BX | 10-2075 | RELOCATE T/L 551/561 STRUCTURES 91 | MS | 0 | 0 | 0 | 30.9 | 4.4 | -24.4
T458BX | 10-2075 | RELOCATE T/L 551/561 STRUCTURES 91 | A3 | 0.6 | 0.5 | 0.9 | 6.9 | 10.8 | -2.1
T458BX | 10-2075 | RELOCATE T/L 551/561 STRUCTURES 91 | A4 | 2.8 | 3 | 3.1 | 30.7 | 35.5 | -32.7
T458BX | 10-2075 | RELOCATE T/L 551/561 STRUCTURES 91 | PR | 2.5 | 3 | 2.6 | 21.7 | 26.9 | 2.8
T458BX | 10-2075 | RELOCATE T/L 551/561 STRUCTURES 91 | AP | 0.7 | 0.4 | 32.3 | 0.4 | 12.9 | 20.3
|  |  |  | 6.8 | 6.9 | 38.9 | 93.6 | 90.9 | -290.5 | -53.4
T460BX | 13-2122 | REMOVE L-120 DLP RELAY SCHEME & ADD | AP | 0.1 | 0 | 0 | 0 | 0 | 0
T460BX | 13-2122 | REMOVE L-120 DLP RELAY SCHEME & ADD | A3 | 0 | 0 | 0 | 0 | 0 | 0.5
T460BX | 10-2122 | REMOVE L-120 DLP RELAY SCHEME & ADD | PR | 0 | 0 | 0 | 0 | 0 | 1
T460BX | 10-2122 | REMOVE L-120 DLP RELAY SCHEME & ADD | A3 | 0 | 0 | 0 | 0 | 0 | 1
T460BX | 13-2122 | REMOVE L-120 DLP RELAY SCHEME & ADD | PR | 0 | 0 | 0 | 0 | 0 | 1.5
T460BX | 13-2122 | REMOVE L-120 DLP RELAY SCHEME & ADD | A4 | 0 | 0 | 0 | 0 | 0 | 1.8
T460BX | 10-2122 | REMOVE L-120 DLP RELAY SCHEME & ADD | A4 | 0 | 0 | 0 | 0 | 0 | 2
|  |  |  | 0.1 | 0 | 0 | 0 | 0 | 7.8 | 7.9
T464BX | 10-2250 | LOVETT PLANT RETIREMENT - S/S WORK | CC | 0 | -4.6 | 0 | 0 | -129.5 | 0
T464BX | 13-2250 | LOVETT PLANT RETIREMENT - S/S WORK | CC | 0 | -44.6 | 0 | 0 | 0 | 0
T464BX | 10-2250 | LOVETT PLANT RETIREMENT - S/S WORK | PR | -0.3 | 0 | 0 | 0 | 0 | 0
T464BX | 13-2250 | LOVETT PLANT RETIREMENT - S/S WORK | PR | -0.2 | 0 | 0 | 0 | 0 | 0
T464BX | 13-2250 | LOVETT PLANT RETIREMENT - S/S WORK | A4 | -0.2 | 0 | 0 | 0 | 0 | 0
T464BX | 10-2250 | LOVETT PLANT RETIREMENT - S/S WORK | A4 | -0.3 | 0 | 1.3 | 0 | 0 | 0
T464BX | 10-2250 | LOVETT PLANT RETIREMENT - S/S WORK | A3 | -0.1 | 0 | 1.2 | 0 | 0 | 0
T464BX | 10-2250 | LOVETT PLANT RETIREMENT - S/S WORK | AP | 0.2 | 0 | 126.9 | 0 | 0 | 0
|  |  |  | -0.9 | -49.2 | 129.4 | 0 | -129.5 | 0 | -50.2
T466BX | 10-2270 | HILLBURN SUB BANK 317 SERVICE UPGRA | CC | 0 | 0 | 0.5 | 0 | 0 | 0
T466BX | 10-2270 | HILLBURN SUB BANK 317 SERVICE UPGRA | PR | 2.4 | 0 | 0 | 0 | 0 | 0
T466BX | 10-2270 | HILLBURN SUB BANK 317 SERVICE UPGRA | A3 | 3.6 | 0 | 0 | 0 | 0 | 0
T466BX | 10-2270 | HILLBURN SUB BANK 317 SERVICE UPGRA | A4 | 6.1 | 0 | 0 | 0 | 0 | 0
T466BX | 10-2270 | HILLBURN SUB BANK 317 SERVICE UPGRA | AP | 0 | 0 | 6.4 | 0 | 0 | 0
|  |  |  | 12.1 | 0 | 6.9 | 0 | 0 | 0 | 19
T474BX | 13-2366 | REPLACE BREAKER 12-2-2 @ MONGAUP DU | PR | 0.9 | 0 | 0 | 0 | 0 | 0
T474BX | 13-2366 | REPLACE BREAKER 12-2-2 @ MONGAUP DU | A3 | 1.2 | 0 | 0 | 0 | 0 | 0
T474BX | 10-2366 | REPLACE BREAKER 12-2-2 @ MONGAUP DU | AP | -4 | 0 | 5.5 | 0 | 0 | 0
T474BX | 13-2366 | REPLACE BREAKER 12-2-2 @ MONGAUP DU | A4 | 2.1 | 0 | 0 | 0 | 0 | 0
T474BX | 10-2366 | REPLACE BREAKER 12-2-2 @ MONGAUP DU | A3 | 5.7 | 0 | 0.1 | 0 | 0 | 0
T474BX | 10-2366 | REPLACE BREAKER 12-2-2 @ MONGAUP DU | PR | 8.4 | 0 | 0.4 | 0.3 | 0 | 0
T474BX | 10-2366 | REPLACE BREAKER 12-2-2 @ MONGAUP DU | A4 | 13.5 | 0 | 0.4 | 0.2 | 0 | 0
|  |  |  | 27.8 | 0 | 6.4 | 0.5 | 0 | 0 | 34.7
T475CX | 50-2370 | U/G 138 KV LINE 541 TIE REPLACEMENT | A3 | 0.3 | 0 | 0 | 0 | 0 | 0.4
T475CX | 50-2370 | U/G 138 KV LINE 541 TIE REPLACEMENT | PR | 0.2 | 0.3 | 0.5 | 0.4 | 0.9 | 0.8
T475CX | 50-2370 | U/G 138 KV LINE 541 TIE REPLACEMENT | A4 | 0.6 | 0.2 | 0.4 | 0.4 | 0.7 | 1
T475CX | 50-2370 | U/G 138 KV LINE 541 TIE REPLACEMENT | AP | 0 | 0 | 97.3 | -97.3 | 0 | 139.1
|  |  |  | 1.1 | 0.5 | 98.2 | -96.5 | 1.6 | 141.3 | 146.2
T476BX | 10-2371 | REPLACE STRUCTURE 90 LINES 551 AND | CC | 0 | 0 | 0 | 0.3 | 0.2 | 0.1
T476BX | 10-2371 | REPLACE STRUCTURE 90 LINES 551 AND | MS | 0 | 0 | 0 | 3.3 | 1.9 | -0.1
T476BX | 10-2371 | REPLACE STRUCTURE 90 LINES 551 AND | A3 | 0.1 | 0.1 | 0.2 | 0.8 | 2.3 | 3.9
T476BX | 13-2371 | REPLACE STRUCTURE 90 LINES 551 AND | AP | 0 | 0 | 0 | 0 | 0 | 12.2
T476BX | 10-2371 | REPLACE STRUCTURE 90 LINES 551 AND | PR | 0.4 | 0.3 | 0.8 | 2.8 | 5.4 | 7.9
T476BX | 10-2371 | REPLACE STRUCTURE 90 LINES 551 AND | A4 | 0.5 | 0.3 | 0.8 | 3.7 | 7.3 | 11.1
T476BX | 10-2371 | REPLACE STRUCTURE 90 LINES 551 AND | AP | 0.1 | 0 | 1.5 | 39.7 | 199.4 | 77.4
|  |  |  | 1.1 | 0.7 | 3.3 | 50.6 | 216.5 | 112.5 | 384.7
T478BX | 10-2413 | INSTALL FIBER OPTIC GROUND CABLE (O | A3 | 0 | 0 | 0.2 | 0.5 | 1.7 | 0.5
T478BX | 10-2413 | INSTALL FIBER OPTIC GROUND CABLE (O | PR | 0 | 0 | 1 | 2.7 | 0.7 | 1.4
T478BX | 10-2413 | INSTALL FIBER OPTIC GROUND CABLE (O | A4 | 0 | 0 | 1 | 2.9 | 2.8 | 1.7
T478BX | 10-2413 | INSTALL FIBER OPTIC GROUND CABLE (O | AP | 0 | 0 | 0 | 0 | 17.5 | 0
|  |  |  | 0 | 0 | 2.2 | 6.1 | 22.7 | 3.6 | 34.6
T480CX | 50-2415 | PRELIMINARY ENG STUDY, 69KV U/G TRA | A3 | 0 | 0 | 0.1 | 0 | 0 | 0.2
T480CX | 50-2415 | PRELIMINARY ENG STUDY, 69KV U/G TRA | PR | 0 | 0 | 0.2 | 0.6 | 0.3 | 0
T480CX | 50-2415 | PRELIMINARY ENG STUDY, 69KV U/G TRA | A4 | 0 | 0 | 0.3 | 0.5 | 0.2 | 0.2
T480CX | 50-2415 | PRELIMINARY ENG STUDY, 69KV U/G TRA | AP | 0 | 0 | 0 | 0 | 0 | 28
|  |  |  | 0 | 0 | 0.6 | 1.1 | 0.5 | 28.4 | 30.6
T481CX | 50-2416 | INSTALL FIBER OPTIC U/G CONDUIT SYS | CC | 0 | 0 | 0 | 0 | 0.1 | 0.1
T481CX | 50-2416 | INSTALL FIBER OPTIC U/G CONDUIT SYS | MS | 0 | 0 | 0 | 0 | 1.3 | 0.6
T481CX | 50-2416 | INSTALL FIBER OPTIC U/G CONDUIT SYS | A3 | 0 | 0 | 0.3 | 0.3 | 1.2 | 2.2
T481CX | 50-2416 | INSTALL FIBER OPTIC U/G CONDUIT SYS | PR | 0 | 0 | 2.9 | 0.8 | 2.5 | 3.4
T481CX | 50-2416 | INSTALL FIBER OPTIC U/G CONDUIT SYS | A4 | 0 | 0 | 2.6 | 0.9 | 3.4 | 5
T481CX | 50-2416 | INSTALL FIBER OPTIC U/G CONDUIT SYS | AP | 0 | 0 | 0 | 0 | 146.5 | 90.9
|  |  |  | 0 | 0 | 5.8 | 2 | 155 | 102.2 | 265
T482FX | 10-2417 | EHV NRG MAPPING PROGRAM | A3 | 0 | 0 | 0 | 0.2 | 0 | 0.2
T482FX | 10-2417 | EHV NRG MAPPING PROGRAM | A4 | 0 | 0 | 0 | 0.2 | 0 | 0.2
T482FX | 10-2417 | EHV NRG MAPPING PROGRAM | AP | 0 | 0 | 24 | 30 | 30 | 71.2
|  |  |  | 0 | 0 | 24 | 30.4 | 30 | 71.6 | 156
T488BX | 10-2442 | REPLACE BREAKER 131-2-2 AT MONGAUP | CC | 0 | 0 | 0 | 0 | 0 | 0.2
T488BX | 10-2442 | REPLACE BREAKER 131-2-2 AT MONGAUP | A3 | 0 | 0 | 0 | 0 | 0.4 | 0.2
T488BX | 10-2442 | REPLACE BREAKER 131-2-2 AT MONGAUP | AP | 0 | 0 | 0 | 0 | 4 | -0.7
T488BX | 10-2442 | REPLACE BREAKER 131-2-2 AT MONGAUP | PR | 0 | 0 | 0 | 0 | 2.6 | 1.1
T488BX | 10-2442 | REPLACE BREAKER 131-2-2 AT MONGAUP | A4 | 0 | 0 | 0 | 0 | 2.6 | 1.2
|  |  |  | 0 | 0 | 0 | 0 | 9.6 | 2 | 11.6
T489BX | 10-2444 | CLEAR ADDITIONAL R-O-W FOR NY TRANS | AP | 0 | 0 | 0 | 22.2 | 0 | 0 | 22.2
T491AX | 30-2447 | INSTALL ADDITIONAL ACCESS CONTROL F | AP | 0 | 0 | 0 | 0 | 0 | 39.3 | 39.3
T495BX | 13-2467 | LINE 25 BREAKER REPLACEMENT - SUGAR | A4 | 0 | 0 | 0 | 0 | 0 | 0.3
T495BX | 10-2467 | LINE 25 BREAKER REPLACEMENT - SUGAR | CC | 0 | 0 | 0 | 0 | 0 | 2.6
T495BX | 13-2467 | LINE 25 BREAKER REPLACEMENT - SUGAR | PR | 0 | 0 | 0 | 0 | 0 | 2.9
T495BX | 13-2467 | LINE 25 BREAKER REPLACEMENT - SUGAR | AP | 0 | 0 | 0 | 0 | 0 | 23.2
T495BX | 10-2467 | LINE 25 BREAKER REPLACEMENT - SUGAR | A3 | 0 | 0 | 0 | 0 | 0 | 23.8
T495BX | 10-2467 | LINE 25 BREAKER REPLACEMENT - SUGAR | AP | 0 | 0 | 0 | 0 | 0 | 43.9
T495BX | 10-2467 | LINE 25 BREAKER REPLACEMENT - SUGAR | A4 | 0 | 0 | 0 | 0 | 0 | 51.8
T495BX | 10-2467 | LINE 25 BREAKER REPLACEMENT - SUGAR | PR | 0 | 0 | 0 | 0 | 0 | 119.8
|  |  |  | 0 | 0 | 0 | 0 | 0 | 268.3 | 268.3
T173BA | 10-1798 | INSTALL BANK 811 AND REMOVE BANK 21 | AP | -13.1 | 2.7 | 0 | 0 | 0 | 0
T173BA | 10-1798 | INSTALL BANK 811 AND REMOVE BANK 21 | A4 | -2.3 | 0 | 0 | 0 | 0 | 0
T173BA | 10-1798 | INSTALL BANK 811 AND REMOVE BANK 21 | A3 | -1.9 | 0 | 0 | 0 | 0 | 0
|  |  |  | -17.3 | 2.7 | 0 | 0 | 0 | 0 | -14.6
T299BX | 10-1338 | LINE 60/601 REBUILD - BURNS TO RAMA | AP | 2.3 | 0.2 | 3 | 0 | 0.5 | 0.4 | 6.4
PROJECTS OVER $1M
T127BA | 10-1463 | INSTALL NEW T/L FROM RAMAPO TO SUGA | A3 | 0.9 | 0.7 | 2.7 | 21 | 12.7 | 4.8
T127BA | 10-1463 | INSTALL NEW T/L FROM RAMAPO TO SUGA | A4 | 3.6 | 3.5 | 6.9 | 31 | 22 | 11.9
T127BA | 10-1463 | INSTALL NEW T/L FROM RAMAPO TO SUGA | AP | 22.5 | 1.8 | 126.1 | 143.3 | 331.4 | 298.6
T127BA | 10-1463 | INSTALL NEW T/L FROM RAMAPO TO SUGA | CC | 0 | 0 | 0 | 0.2 | 0.1 | 0.3
T127BA | 10-1463 | INSTALL NEW T/L FROM RAMAPO TO SUGA | PR | 3.1 | 3.3 | 4.9 | 6.4 | 6.7 | 7.7
|  |  |  | 30.1 | 9.3 | 140.6 | 201.9 | 372.9 | 323.3 | 1078.1
T120BA | 10-1928 | LINE 11 69KV DOUBLE CIRCUIT UPGRADE | A3 | 8.8 | 1.9 | -6.6 | 2 | 1 | 1.2
T120BA | 10-1928 | LINE 11 69KV DOUBLE CIRCUIT UPGRADE | A4 | 22.2 | 9.1 | -20.2 | 5.8 | 4.1 | 48.6
T120BA | 13-1928 | LINE 11 69KV DOUBLE CIRCUIT UPGRADE | AP | 10 | 0 | 0 | 0 | 0 | 0
T120BA | 10-1928 | LINE 11 69KV DOUBLE CIRCUIT UPGRADE | AP | 790.1 | -500 | 678 | 82.4 | 290.6 | -87.7
T120BA | 10-1928 | LINE 11 69KV DOUBLE CIRCUIT UPGRADE | CC | 0.2 | 0.3 | -0.7 | 0.2 | 0.2 | 0.1
T120BA | 10-1928 | LINE 11 69KV DOUBLE CIRCUIT UPGRADE | MS | 0 | 0 | -68.9 | -0.1 | 0.4 | 0
T120BA | 10-1928 | LINE 11 69KV DOUBLE CIRCUIT UPGRADE | PR | 14.7 | 8.5 | 4.3 | 4.1 | 3.4 | 1.5
|  |  |  | 846 | -480.2 | 585.9 | 94.4 | 299.7 | -36.3 | 1309.5
D420CX | 10-2015 | STONY POINT S/S - 2 NEW EXITS | A3 | 0 | 0 | 1 | -0.4 | 0 | 0
D420CX | 50-2015 | STONY POINT S/S - 2 NEW EXITS | A3 | 4.2 | 4.1 | 7.1 | 34.6 | 7.4 | 3.4
D420CX | 10-2015 | STONY POINT S/S - 2 NEW EXITS | A4 | 0 | 0 | 1.8 | -0.8 | 0 | 0
D420CX | 50-2015 | STONY POINT S/S - 2 NEW EXITS | A4 | 10.2 | 11.3 | 17.3 | 80.9 | 16.6 | 6.7
D420CX | 10-2015 | STONY POINT S/S - 2 NEW EXITS | AP | 0 | 0 | 0 | 0.1 | 0 | 0
D420CX | 50-2015 | STONY POINT S/S - 2 NEW EXITS | AP | 0 | 2.1 | 31.1 | 433.2 | 63 | 3
D420CX | 50-2015 | STONY POINT S/S - 2 NEW EXITS | CC | 0.4 | 0.2 | 2.3 | 22.3 | 0 | 0.2
D420CX | 50-2015 | STONY POINT S/S - 2 NEW EXITS | MS | 4.2 | 0 | 26.9 | 265.9 | -0.4 | 0
D420CX | 10-2015 | STONY POINT S/S - 2 NEW EXITS | PR | 0 | 0 | 0.9 | -0.4 | 0 | 0
D420CX | 50-2015 | STONY POINT S/S - 2 NEW EXITS | PR | 5.6 | 8.6 | 4.3 | 2.7 | 10.5 | 3.9
|  |  |  | 24.6 | 26.3 | 92.7 | 838.1 | 97.1 | 17.2 | 1096
D387BX | 10-1075 | LITTLE TOR SUBSTATION - CONSTRUCTIO | A3 | 2.7 | 2.5 | 3.2 | 1.1 | 3.3 | 10
D387BX | 10-1075 | LITTLE TOR SUBSTATION - CONSTRUCTIO | A4 | 13.8 | 8.9 | 11 | 6.4 | 5.7 | 17.4
D387BX | 10-1075 | LITTLE TOR SUBSTATION - CONSTRUCTIO | AP | 102.4 | 67.4 | 3.9 | 141 | 237.6 | 1278.2
D387BX | 10-1075 | LITTLE TOR SUBSTATION - CONSTRUCTIO | CC | 0 | 0 | 0 | 0.1 | 0 | 0.1
D387BX | 10-1075 | LITTLE TOR SUBSTATION - CONSTRUCTIO | PR | 12.5 | 7.5 | 9.3 | 6 | 2.7 | 7.8
|  |  |  | 131.4 | 86.3 | 27.4 | 154.6 | 249.3 | 1313.5 | 1962.5
D263BX | 10-2055 | PURCHASE LAND FOR THE NEW WEST WARW | A3 | 0 | 0 | 0 | 0 | 1.6 | 10.2
D263BX | 10-2055 | PURCHASE LAND FOR THE NEW WEST WARW | A4 | 0 | 0 | 0 | 0 | 1.8 | 10.8
D263BX | 10-2055 | PURCHASE LAND FOR THE NEW WEST WARW | AP | 1.1 | 0.3 | 5.1 | 0.4 | 197.2 | 1692.3
D263BX | 10-2055 | PURCHASE LAND FOR THE NEW WEST WARW | PR | 0 | 0 | 0 | 0 | 0.1 | 0
|  |  |  | 1.1 | 0.3 | 5.1 | 0.4 | 200.7 | 1713.3 | 1920.9
D223BX | 10-6914 | INSTALL A SECOND TRANSFORMER BANK - | A3 | 39.6 | 29.4 | 13.9 | 13.5 | -6.6 | 3.8
D223BX | 10-6914 | INSTALL A SECOND TRANSFORMER BANK - | A4 | 68.9 | 67.2 | 32.8 | 32.6 | -13.3 | 140
D223BX | 13-6914 | INSTALL A SECOND TRANSFORMER BANK - | AP | 7.8 | 66.2 | 0 | 0 | 0 | 0
D223BX | 10-6914 | INSTALL A SECOND TRANSFORMER BANK - | AP | 1541.4 | 5 | 190.5 | 117.1 | -6.4 | 181.4
D223BX | 10-6914 | INSTALL A SECOND TRANSFORMER BANK - | CC | 1.1 | 0.9 | 0.4 | -0.4 | 0.2 | 0.3
D223BX | 10-6914 | INSTALL A SECOND TRANSFORMER BANK - | MS | 0.8 | -0.7 | 0 | 0.2 | -1.8 | 0
D223BX | 10-6914 | INSTALL A SECOND TRANSFORMER BANK - | PR | 29.1 | 40.4 | 22.2 | 20.2 | -5.5 | 4.4
|  |  |  | 1688.7 | 208.4 | 259.8 | 183.2 | -33.4 | 329.9 | 2636.6
D223CX | 53-1805 | MONROE UNDERGROUND CIRCUIT EXITS | A3 | 0 | 0 | 0 | 0.2 | -0.1 | 0
D223CX | 50-1805 | MONROE UNDERGROUND CIRCUIT EXITS | A3 | 3.5 | 0 | 0.2 | 6 | -0.8 | 0
D223CX | 53-1805 | MONROE UNDERGROUND CIRCUIT EXITS | A4 | 0 | 0 | 0 | 0.4 | -0.1 | 0
D223CX | 50-1805 | MONROE UNDERGROUND CIRCUIT EXITS | A4 | 8.4 | 0 | 0.2 | 13.8 | -0.4 | 0
D223CX | 53-1805 | MONROE UNDERGROUND CIRCUIT EXITS | AP | 9.2 | 0 | 0 | 0 | 0 | 0
D223CX | 50-1805 | MONROE UNDERGROUND CIRCUIT EXITS | AP | 23.6 | 0 | 19.5 | 51.2 | 3.5 | 0
D223CX | 50-1805 | MONROE UNDERGROUND CIRCUIT EXITS | CC | 0.4 | 0.2 | 0 | 0.1 | 0 | 0
D223CX | 50-1805 | MONROE UNDERGROUND CIRCUIT EXITS | MS | 0 | 0 | 0 | 1.1 | 0 | 0
D223CX | 53-1805 | MONROE UNDERGROUND CIRCUIT EXITS | PR | 0 | 0 | 0 | 0.1 | 0 | 0
D223CX | 50-1805 | MONROE UNDERGROUND CIRCUIT EXITS | PR | 5.5 | 0 | 0 | 8.3 | 0.5 | 0
|  |  |  | 50.6 | 0.2 | 19.9 | 81.2 | 2.6 | 0 | 154.5
D115BA | 10-2061 | PURCHASE OF PROPERTY FOR NEW POCATE | A3 | 0 | 0 | 10.7 | 0.1 | 0 | 0
D115BA | 10-2061 | PURCHASE OF PROPERTY FOR NEW POCATE | A4 | 0 | 0 | 0.1 | 0.1 | 0 | 0
D115BA | 10-2061 | PURCHASE OF PROPERTY FOR NEW POCATE | AP | 7.2 | 2.8 | 826.9 | 3.5 | 3 | 0.2
D115BA | 10-2061 | PURCHASE OF PROPERTY FOR NEW POCATE | CC | 0 | 0 | 5.8 | 0 | 0 | 0
|  |  |  | 7.2 | 2.8 | 843.5 | 3.7 | 3 | 0.2 | 860.4
D115BX | 10-6569 | INSTALL 25MVA BANK AT THE POCOTELLO | A3 | 0 | 7.5 | -10.6 | 0 | 0.1 | 0
D115BX | 10-6569 | INSTALL 25MVA BANK AT THE POCOTELLO | A4 | 0 | 8.4 | 0.1 | 0 | 0.1 | 0
D115BX | 10-6569 | INSTALL 25MVA BANK AT THE POCOTELLO | AP | 0 | 714.4 | -807.5 | 0 | 8.6 | 0
D115BX | 10-6569 | INSTALL 25MVA BANK AT THE POCOTELLO | CC | 0 | 0 | -6.3 | 0 | 0 | 0
D115BX | 10-6569 | INSTALL 25MVA BANK AT THE POCOTELLO | PR | 0 | 0.6 | 0.1 | 0 | 0 | 0
|  |  |  | 0 | 730.9 | -824.2 | 0 | 8.8 | 0 | -84.5
D167BA | 10-6912 | INSTALL 2 25MVA BANKS AT THE PJ SUB | A3 | 1.5 | 2.5 | 0.7 | 0.6 | 0.6 | 0.8
D167BA | 10-6912 | INSTALL 2 25MVA BANKS AT THE PJ SUB | A4 | 7.4 | 7.6 | 3.5 | 3.5 | 4.1 | 3.1
D167BA | 10-6912 | INSTALL 2 25MVA BANKS AT THE PJ SUB | AP | 1.2 | 62.6 | 3.9 | 4.7 | 7.7 | -32.1
D167BA | 10-6912 | INSTALL 2 25MVA BANKS AT THE PJ SUB | CC | 0.1 | 0 | 0 | 0 | 0 | -2.5
D167BA | 10-6912 | INSTALL 2 25MVA BANKS AT THE PJ SUB | PR | 6.7 | 6 | 3.3 | 3.2 | 4.1 | 2.5
|  |  |  | 16.9 | 78.7 | 11.4 | 12 | 16.5 | -28.2 | 107.3
D293BX | 10-2443 | PREL.ENG. - NEW CORPORATE DRIVE SUB | A3 | 0 | 0 | 0 | 0 | 0 | 0.1
D293BX | 10-2443 | PREL.ENG. - NEW CORPORATE DRIVE SUB | A4 | 0 | 0 | 0 | 0 | 0 | 0.3
D293BX | 10-2443 | PREL.ENG. - NEW CORPORATE DRIVE SUB | PR | 0 | 0 | 0 | 0 | 0 | 0.3
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0.7 | 0.7
D374BX | 10-7130 | SNAKE HILL ROAD SUBSTATION - WEST N | A3 | 0.5 | 1.9 | 3.2 | 0.6 | 0.6 | 1.4
D374BX | 10-7130 | SNAKE HILL ROAD SUBSTATION - WEST N | A4 | 2.5 | 7.1 | 6.4 | 3.6 | 4.2 | 5.3
D374BX | 10-7130 | SNAKE HILL ROAD SUBSTATION - WEST N | AP | 95.8 | 76.5 | 260.6 | 3 | 5 | 7.7
D374BX | 10-7130 | SNAKE HILL ROAD SUBSTATION - WEST N | PR | 2.3 | 6.2 | 3.7 | 3.3 | 4.2 | 4.4
|  |  |  | 101.1 | 91.7 | 273.9 | 10.5 | 14 | 18.8 | 510
D474BA | 10-2144 | NEW TAPPAN SUBSTATION - 250MVA BANK | A3 | 2 | 2.4 | 1.2 | 2.2 | 0.6 | 2.3
D474BA | 10-2144 | NEW TAPPAN SUBSTATION - 250MVA BANK | A4 | 9.6 | 11.7 | 6 | 11.7 | 4 | 8.9
D474BA | 10-2144 | NEW TAPPAN SUBSTATION - 250MVA BANK | AP | 7.4 | 0.9 | 1.6 | 20.1 | 0 | 0
D474BA | 10-2144 | NEW TAPPAN SUBSTATION - 250MVA BANK | CC | 0 | 0.1 | 0 | 0.1 | 0 | 0.1
D474BA | 10-2144 | NEW TAPPAN SUBSTATION - 250MVA BANK | PR | 8.6 | 11 | 5.7 | 10.6 | 4 | 7.3
|  |  |  | 27.6 | 26.1 | 14.5 | 44.7 | 8.6 | 18.6 | 140.1
D474BB | 10-2060 | TAPPAN AREA SUBSTATION - PROPERTY P | A3 | 0.3 | 0.4 | 1.1 | 1.2 | 0.5 | 1.1
D474BB | 10-2060 | TAPPAN AREA SUBSTATION - PROPERTY P | A4 | 1.6 | 1.5 | 5.6 | 4 | 2.9 | 3.7
D474BB | 10-2060 | TAPPAN AREA SUBSTATION - PROPERTY P | AP | 11.3 | 7.5 | 16.9 | 75.9 | 23.6 | 14
D474BB | 10-2060 | TAPPAN AREA SUBSTATION - PROPERTY P | CC | 135.4 | 0 | 0 | 0.1 | 0 | 0
D474BB | 10-2060 | TAPPAN AREA SUBSTATION - PROPERTY P | PR | 1.4 | 1.2 | 5.4 | 3.1 | 2.9 | 2.9
|  |  |  | 150 | 10.6 | 29 | 84.3 | 29.9 | 21.7 | 325.5
T125BX | 10-1440 | T/L 24, 25 & 26 SHIELD WIRE | A3 | 0 | 0.1 | 0.1 | 0.3 | 0.1 | 0
T125BX | 10-1440 | T/L 24, 25 & 26 SHIELD WIRE | A4 | 0.1 | 0.3 | 0.3 | 0.6 | 0.1 | 0
T125BX | 10-1440 | T/L 24, 25 & 26 SHIELD WIRE | AP | 0 | 0 | 23.8 | 0 | 5.1 | 19.7
T125BX | 10-1440 | T/L 24, 25 & 26 SHIELD WIRE | PR | 0.1 | 0.3 | 0.3 | 0.3 | 0.1 | 0
|  |  |  | 0.2 | 0.7 | 24.5 | 1.2 | 5.4 | 19.7 | 51.7
T127BB | 10-1464 | INSTALL NEW 138 KV TERMINAL - RAMAP | A3 | 1.7 | 3 | 4.4 | 2.9 | 1.5 | 2.5
T127BB | 10-1464 | INSTALL NEW 138 KV TERMINAL - RAMAP | A4 | 8.7 | 13.5 | 18.4 | 16.6 | 10.6 | 5.7
T127BB | 10-1464 | INSTALL NEW 138 KV TERMINAL - RAMAP | AP | 0 | 36.3 | 36.3 | 250 | -80.7 | 45.7
T127BB | 10-1464 | INSTALL NEW 138 KV TERMINAL - RAMAP | CC | 0 | 0 | 0 | 0 | 0 | 0.1
T127BB | 10-1464 | INSTALL NEW 138 KV TERMINAL - RAMAP | PR | 7.8 | 12.3 | 16.7 | 15.3 | 10.5 | 3.4
|  |  |  | 18.2 | 65.1 | 75.8 | 284.8 | -58.1 | 57.4 | 443.2
T127BX | 10-7333 | INSTALL NEW 138KV BAY SUGARLOAF S/S | A3 | 3.2 | 2.7 | 7.4 | 2.6 | 5 | 1.4
T127BX | 10-7333 | INSTALL NEW 138KV BAY SUGARLOAF S/S | A4 | 16.1 | 8.2 | 24.1 | 11.4 | 9.2 | 26.8
T127BX | 10-7333 | INSTALL NEW 138KV BAY SUGARLOAF S/S | AP | 12.3 | 112.1 | 119.3 | 502.1 | 36.5 | 12.4
T127BX | 10-7333 | INSTALL NEW 138KV BAY SUGARLOAF S/S | CC | 0 | 0 | 0 | 0.1 | 0 | 0.1
T127BX | 10-7333 | INSTALL NEW 138KV BAY SUGARLOAF S/S | PR | 14.5 | 6.5 | 19.9 | 9.7 | 4.5 | 4.3
|  |  |  | 46.1 | 129.5 | 170.7 | 525.9 | 55.2 | 45 | 972.4
T167BD | 10-2377 | ENGINEERING AND DESIGN, TRANSMISSIO | A3 | 0.1 | 0 | 0 | 0 | 0 | 0
T167BD | 10-2377 | ENGINEERING AND DESIGN, TRANSMISSIO | A4 | 0.4 | 0.2 | 0.2 | 0 | 0.1 | 0
T167BD | 10-2377 | ENGINEERING AND DESIGN, TRANSMISSIO | AP | 0 | 0 | 0 | 0 | 0 | 14.3
T167BD | 10-2377 | ENGINEERING AND DESIGN, TRANSMISSIO | PR | 0.4 | 0.2 | 0.2 | 0 | 0.1 | 0
|  |  |  | 0.9 | 0.4 | 0.4 | 0 | 0.2 | 14.3 | 16.2
T174BX | 10-2148 | PE - LINE 31 RECONDUCTOR | A3 | 0.7 | 0.5 | 0.6 | 0.4 | 0.1 | 0.8
T174BX | 10-2148 | PE - LINE 31 RECONDUCTOR | A4 | 3.3 | 2.3 | 2.9 | 2.1 | 1 | 3
T174BX | 10-2148 | PE - LINE 31 RECONDUCTOR | AP | 1.1 | 0 | 0 | 0 | 0 | 29.8
T174BX | 10-2148 | PE - LINE 31 RECONDUCTOR | PR | 3 | 2.1 | 2.8 | 2 | 1 | 2.4
|  |  |  | 8.1 | 4.9 | 6.3 | 4.5 | 2.1 | 36 | 61.9
T182BX | 10-2357 | SPARE 138 TO 69KV | A3 | 0.4 | 0.4 | 0.1 | 0 | 0 | 0.3
T182BX | 10-2357 | SPARE 138 TO 69KV | A4 | 1.8 | 1.9 | 0.4 | 0 | 0 | 1.3
T182BX | 10-2357 | SPARE 138 TO 69KV | PR | 1.7 | 1.8 | 0.4 | 0 | 0 | 1.1
|  |  |  | 3.9 | 4.1 | 0.9 | 0 | 0 | 2.7 | 11.6

## Total T&D Expend Exhibit
Orange and Rockland Utilities, Inc.
Electric Rate Case - Annual Update
Electric Capital Expenditures
Rate Year 3
|  | Rate Year 3 | Rate Year 3
|  | Agreement | Actual | Variance
Project Description
| Blankets | 28419 | 21288.5 | 7130.5
| Regular Projects Under $1 Million | 5883.8 | 11728 | -5844.2
Regular Projects Over $1 Million
T120BA | Transmission Line 11 Upgrade Part 2 | 0 | 3 | -3
D420CX | Stony Point UG Exits | 0 | 0 | 0
D223B/C | Monroe Substation Upgrade and UG Exits | 0 | 0 | 0
T127BA | Transmission Line 28 (77A) - Ramapo to Sugarloaf | 0 | 224.5 | -224.5
T127BB | Ramapo 138kV Terminal | 0 | 1755.8 | -1755.8
T127BC/BX | Sugarloaf 138kV Substation and Transmission Reconfiguration | 0 | 6281.1 | -6281.1
D387B/C | Little Tor Substation, UG Exits and Transmission | 0 | 264.6 | -264.6
D374B/C | Snake Hill Road Subst, UG Exits, Transm OH Tap and Terminal Relays | 0 | 1583.3 | -1583.3
D167B/C | Port Jervis Substation Upgrade and UG Exits | 0 | 330.6 | -330.6
T167BD | Transmission Line 18 Upgrade | 0 | 145.6 | -145.6
T182BX | Spare 138 - 69kV 175MVA Transformer | 0 | 1880.4 | -1880.4
| Mirant | 0 | 0 | 0
T174BX | Transmission Line 31 Upgrade | 0 | 2682.8 | -2682.8
D115B/C | Pocatello Substation and UG Exits | 0 | 0.6 | -0.6
D253B/C | Hartley Road Substation and UG Exits | 0 | 1915.7 | -1915.7
D293B/C | Corporate Drive Substation, UG Exits and Transmission Tap | -995 | 12778.2 | -13773.2
D320BX | Spare 138X69 13.2kV 35MVA Bank | 0 | 751.5 | -751.5
D474B/C | Tappan Substation and UG Exits | 581 | 259.8 | 321.2
T126BX | Sterling Forest Line 26 Transmission Tap | 836 | 0.4 | 835.6
T179BX | Spare 345 - 138kV 400MVA Transformer | 3990 | 3777.1 | 212.9
T125BX | Transmission Line 24 and 25 Upgrade | 3353 | 155.8 | 3197.2
D258B/C | New Hempstead Substation Upgrade and UG Exits | 7753 | 613.2 | 7139.8
D263B/C | West Warwick Substation and UG Exits | 5683.5 | 46.8 | 5636.7
D134B/C/M | Smart Grid Projects (Distribution, Substation, Communication) | 0 | 1191.7 | -1191.7
D491B/C | Dean Substation | 0 | 488.4 | -488.4
D263BA | Transmission Line - Wisner to West Warwick | 3570 | 0 | 3570
T175BX | Transmission Lines 55 and 551 Upgrade | 1482 | 0 | 1482
D245B/C | Westtown Substation Upgrade and UG Exits | 1697 | 0 | 1697
D145BA | Transmission Line 6 Upgrade - Pocatello to Decker | 1720 | 0 | 1720
| Silver Lake Substation Upgrade | 1355 | 0 | 1355
D397FC | Mine Torne Rd -Dean to Queensboro Dbl Ck | 0 | 956.4 | -956.4
| Total | 31025.5 | 38087.3 | -7061.8
|  | 65328.3 | 71103.8 | -5775.5

## Blanket Expenditures Exhibit
Orange and Rockland Utilities, Inc.
Electric Rate Case - Annual Update
Electric Blanket Expenditures
Rate Year 3
|  | Rate Year 3 | Actual | Variance
Project Description
| Incremental Electric Vehicles | 0 | 7.8 | -7.8
| Mobile OMS Blanket | 0 | 91.2 | -91.2
| Incremental Reliability Blanket - Defective Poles | 0 | 495.8 | -495.8
| NY Transmission Pole Replacement Blanket - Stray Voltage | 0 | 54.8 | -54.8
| EMS Jump Program | 0 | 346.2 | -346.2
| Electric Distribution Blankets - OH | 8104.1 | 10298.8 | -2194.7
| Electric Distribution Blankets - UG | 2665.3 | 3430.1 | -764.8
| Pole Inspection/Treatment Program | 556.2 | 0 | 556.2
| Transformers - OH | 4882.1 | 1280.6 | 3601.5
| Transformers - UG | 1805.2 | 1290.1 | 515.1
| O/H Capital Tools Blanket | 85.3 | 118.8 | -33.5
| Electric Meter Purchases | 1683.8 | 212.3 | 1471.5
| T & S Engineerin Software/Hardware Bkt | 37.1 | 8.5 | 28.6
| Distrib Substation Automation Blanket | 200 | 18.9 | 181.1
| U/G Rebuild Blanket | 780.4 | 225.3 | 555.1
| U/G Gasification (Rehab) Blanket | 204.7 | 193.3 | 11.4
| Electric Meter 1st Install Bkt | 1439.8 | 569.3 | 870.5
| Load Research Meters Bkt | 141.8 | 0 | 141.8
| Smart Grid Devices | 100 | 27.7 | 72.3
| Distribution Engineering Test Equip Bkt | 35.5 | 57.4 | -21.9
| Distribution Automation Blanket | 1750 | 1665.1 | 84.9
| OMS Hardware Blanket | 101.6 | 30.9 | 70.7
| Weather Station | 48.5 | 0 | 48.5
| Sale Of Scrap Blanket | -5 | -147.6 | 142.6
| PCB Oil Testing And Disposal Blanket | 104.1 | 91.8 | 12.3
| Smart Grid Pilot Project | 598.8 | 0 | 598.8
| Property Program | 1000 | 0 | 1000
| AMI - Electric Program | 245.3 | 0 | 245.3
| Electric Meter Dept. Misc. Equipment Bkt | 179.2 | 103.2 | 76
| Bank Metering Upgrade Blanket | 60.2 | 10.6 | 49.6
| Pole Butt Removal Blanket | 33.8 | 25.2 | 8.6
| Paving & Drainage Blanket | 71.2 | 28.5 | 42.7
| U/G Capital Tools Blanket | 53.7 | 31.1 | 22.6
| Gas Meter AMR Upgrade Program Bkt | 534.8 | 0 | 534.8
| Substation Department Blanket | 78.6 | 29.2 | 49.4
| Install Battery Banks Blanket | 34.2 | 36.4 | -2.2
| Relay Department Blanket | 42 | 31.9 | 10.1
| Purchase Relay Test Set Blanket | 67.4 | 63.2 | 4.2
| Substation Comm. Protection Bkt | 45 | 31 | 14
| Transmission Relay Upgrade Bkt | 156.3 | 81.3 | 75
| EMS Equipment Upgrade Blanket | 450 | 423.2 | 26.8
| Substation Small Equipment Blanket | 48 | 26.6 | 21.4
|  | 28419 | 21288.5 | 7130.5

## Proj<$1M Expend Exhibit
Orange and Rockland Utilities, Inc.
Electric Rate Case - Annual Update
Electric Projects Under $1 Million Expenditures
Rate Year 3
|  | Rate Year 3 | Actual | Variance
Project Description
D104FX | REBUILD APPROX. 1050 FT - RICHARD C | 0 | 2.1 | -2.1
D118FB | URD WOODBURY JUNCTION PHASE 2, DUND | 0 | 78.6 | -78.6
D120FX | INSTALL 13.2KV CIRCUIT, RT 17M, HAR | 0 | 11.3 | -11.3
D126BX | PRELIMINARY ENG. - WURTSBORO S/S EX | 0 | 8.9 | -8.9
D150BX | RELOCATE TRANSMISSION LINES 841 & 8 | 0 | 15.3 | -15.3
D152FA | E.I.M.S. DIST. ENG INSPECTION & OUT | 0 | 365.9 | -365.9
D153CX | RTE 9W BRIDGE CROSSING CEDAR POND B | 0 | 53 | -53
D166FX | REBUILD BREVOORT DRIVE - POMONA - 0 | 0 | -41.2 | 41.2
D169FX | REBUILD SECORA ROAD - SPRING VALLEY | 0 | 29 | -29
D174FX | RECONDUCTOR LIVINGSTON & OAK TREE L | 0 | 298.3 | -298.3
D175BX | INSTALL NEW MOBILE 6 - TILCON FACIL | 0 | 4.2 | -4.2
D178FX | RELOCATE POLES FOR DOT - RTE 59 @ S | 0 | 32.3 | -32.3
D179FX | RECOND OAKLAND VALLEY RD TO 477 - F | 0 | -2 | 2
D180FX | NY INCREMENTAL RELIABILITY - DEFECT | 0 | 6 | -6
D181CX | REPLACE DUCT & WIRE - WN U/G 21-9,1 | 0 | 112.8 | -112.8
D183FX | 2009 CABLE REBUILD - FOREST BROOK R | 0 | 17.6 | -17.6
D184FX | 2009 CABLE REBUILD - CLAY STREET - | 0 | 7.8 | -7.8
D186FX | REBUILD 3100FT - DENVER DR., NEW CI | 0 | 31.8 | -31.8
D195CX | INSTALL 2 UNDERGROUND CIRCUIT EXITS | 0 | 409.6 | -409.6
D196BX | LOVETT BACKUP STATION AND T1 COMMUN | 0 | 67.5 | -67.5
D197CX | ARDEN BRIDGE UG THRUWAY CROSSING, A | 0 | 145.1 | -145.1
D199CX | PALISADES PKWY CROSSING, NORTH MAIN | 0 | -3.3 | 3.3
D216FX | 2009 LTS SYS IMPROV - ROUND HILL RD | 0 | 3.2 | -3.2
D217FX | TWIN AVE RECONDUCTOR - SPRING VALLE | 0 | 33.6 | -33.6
D229FB | KNIGHT RD TO CTY RD 31 TO WHITE RD, | 0 | 328.8 | -328.8
D238CX | DISTRIBUTION SCADA SYSTEM PURCHASES | 0 | 531.1 | -531.1
D238FX | RELOCATION OF POLES, GOLF RIDGE EST | 0 | 81.2 | -81.2
D248FX | OLD PHILLIPS HILL RD. CONVERSION/EX | 0 | 119.5 | -119.5
D250FX | SYSTEM IMPR - HELM HILL RD - B.GROV | 0 | 71.3 | -71.3
D255FX | 2010 - INCREMENTAL RELIABILITY - DE | 0 | 432.7 | -432.7
D256BL | EXPANSION OF BLOOMING GROVE S/ | 0 | 82.7 | -82.7
D260BA | POMONA S/S - PRELIMINARY DESIGN - | 0 | 0.6 | -0.6
D261FX | MAPLE AVENUE ROAD WIDENING, MONSEY, | 0 | 250.4 | -250.4
D262BX | REPLACE ORANGEBURG BREAKER 54-3-2B | 0 | 3.7 | -3.7
D264FX | RELOCATION OF ROUTE 59 WESTERN HWY | 0 | -6 | 6
D265FX | 2010 REBUILD 1250FT QUICKWAY ROAD, | 0 | 40.8 | -40.8
D266FX | 2010 REBUILD ROCKWOOD GARDENS, ROCK | 0 | 146.8 | -146.8
D273FX | 2010 U/G REBUILD, SUNDRY DR, NEW C | 0 | 36.1 | -36.1
D274FX | 2010 U/G REBUILD, JEAN LANE, MONSEY | 0 | 60.9 | -60.9
D275FX | 2010 U/G REBUILD, PACESETTER PARK, | 0 | 78.6 | -78.6
D276FX | 2010 U/G REBUILD, HOOVER LANE, NEW | 0 | 96.8 | -96.8
D295FX | U/G CROSSROADS @ STONY POINT - SHOP | 0 | 206.4 | -206.4
D296CX | UG CROSSING CABLE REPLACEMENT, UNDE | 0 | 100.9 | -100.9
D303BX | REPLACE RECLOSER 89-2-2K AT THE SOU | 0 | 36.5 | -36.5
D306FX | SHUART ROAD CONVERSION-MONSEY (SUMM | 0 | 69.7 | -69.7
D307FX | SAMSONDALE AVE. CONVERSION - WEST H | 0 | 171.1 | -171.1
D309CX | INSTALL NEW U/G CIRCUIT - 61-1-13 @ | 0 | 223.3 | -223.3
D310FX | REBUILD 2600' AND INSTALL F/I & MOV | 0 | 94.9 | -94.9
D316BX | Congers 562-22-2 Breaker Replacemen | 0 | 66 | -66
D317CC | 2010 OUTAGE MANAGEMENT SYSTEM (OMS) | 0 | 131.7 | -131.7
D323BX | Land Purchase - Bullville Upgrade | 0 | 18.7 | -18.7
D326BX | Wisner Property Purchase - Prel Eng | 0 | 2.4 | -2.4
D327FX | New Hempstead Rd Widening Project | 0 | 193.2 | -193.2
D328FX | Leber Road Recondctor & Extension | 0 | 163.3 | -163.3
D329BX | Queensboro Substation Demolition | 0 | 10.6 | -10.6
D331FA | U/G Rebuild Blossom Rd/Bookhill Hms | 0 | 166.8 | -166.8
D331FC | U/g Rebuild Country Club La, Pomona | 0 | 100.3 | -100.3
D331FG | UG Rebuild 4200' - W. Burda Place | 0 | 22.6 | -22.6
D333CX | UG Mainline Rt-17M/Exit 122 N.Main | 0 | 356 | -356
D341FX | Country Rd 41 Recond & Conver - Rio | 0 | 445.7 | -445.7
D347FB | SKI-RUN ROAD, BURLINGTON ROAD TO ST | 0 | 54.6 | -54.6
D351FX | South Street Conversion - Goshen | 0 | 22.2 | -22.2
D362FA | Snake Hill & Old Mill roads recond. | 0 | 341.4 | -341.4
D362FH | Double Circuit - WN Road | 0 | 12 | -12
D376VA | Smart grid - Capacitor optimization | 0 | 173.6 | -173.6
D378FX | Closter Road Reconductor | 0 | 1.9 | -1.9
D397FX | MINE TORNE RD - QUEENSBORO TO ROUTE | 0 | 586.1 | -586.1
D404CX | SCOTLAND HILL RD / G.S.PKWY BORING | 0 | -2.5 | 2.5
D410FC | LAROE ROAD WIDENING - PART 4 | 0 | -121.3 | 121.3
D418BX | EVALUATION OF PROPERTIES FOR PURCHA | 0 | 1.1 | -1.1
D463FC | .hunt road reconductor - 1007001101 | 0 | 154.6 | -154.6
D464FX | North Main Street Conversion - SV | 0 | 82.6 | -82.6
D470FX | Brick Church Road Reconductor, N Hm | 0 | 203.5 | -203.5
D492CX | CHESTER CABLE BANK 168 REPLACEMENT | 0 | 26.3 | -26.3
D493CX | WEST HAVERSTRAW SUBSTATION UNDERGRO | 0 | 18.2 | -18.2
D496FX | College Av Recond & Ext, Nanuet NY | 0 | 135 | -135
D497FX | Williams Ave reconductor - S.V. | 0 | 497.8 | -497.8
D532FA | REPLACE DEFECTIVE POLES CIRCUIT 5-1 | 0 | -2.3 | 2.3
D572BA | PURCHASE OF PROPERTY FOR NEW DEER P | 0 | 0.1 | -0.1
D576FX | STRAY VOLTAGE - ELECTRIC INFORMATIO | 0 | 49.2 | -49.2
D582FX | CHESTER DISTRIBUTION PART 1 - LEONE | 0 | 145.6 | -145.6
T120KX | O&R VS LOCKWOOD, KESSLER & BARTLETT | 0 | -554.2 | 554.2
T133AR | ELECTRONIC MAP BOARDS FOR ECC/DCC | 0 | 4.7 | -4.7
T172BX | INSTALL CAPACITOR BANK AND RELATED | 0 | 269 | -269
T184BX | BANK 1300/2300 CIRCUIT SWITCHES | 0 | 621.5 | -621.5
T186BX | INSTALL FIBER OPTIC GROUND CABLE (O | 0 | 39.5 | -39.5
T187BX | LINE 55 & 56 STRUCTURE REPLACEMENTS | 0 | 260.7 | -260.7
T272BX | INSTALL FIBER OPTIC GROUND CABLE (O | 0 | 45.8 | -45.8
T273BX | Replace 69Kv OCBs at Sugarloaf S/S | 0 | 191.7 | -191.7
T296BA | PURCHASE OF PROPERTY FOR NEW DECKER | 0 | 0.8 | -0.8
T298BX | REPLACE FIRE SUPP @ RAMAPO | 0 | 81.7 | -81.7
T299BX | LINE 60/601 REBUILD - BURNS TO RAMA | 0 | 105 | -105
T473BX | T/L'X Y88/94, TOWER MODIFICATIONS T | 0 | 128.3 | -128.3
T498BX | REPLACEMENT OF OIL CIRCUIT BREAKER | 0 | 0.7 | -0.7
T504BX | PE - T/L 311 SHORELINE PROTECTION | 0 | 114.7 | -114.7
T505BX | REPLACE ROOF @ HUDSON RIVER CROSSIN | 0 | 2.5 | -2.5
T506BX | REMOVE LINES 73/74 CONDUCTORS, BETW | 0 | 3.5 | -3.5
T508BX | INSTALL FIBER OPTIC GROUND CABLE (O | 0 | 389.7 | -389.7
T509BX | T/L 311 RECONDUCTOR UPGRADE - SLOAT | 0 | 79.8 | -79.8
T513BX | TOWER 147, T/L 25 SHORELINE PROTECT | 0 | 20.3 | -20.3
T514BX | TOWER 3, FORMER C H TIE LINES, SHOR | 0 | 21.6 | -21.6
T515BX | TOWER 163, T/L 26- Shoreline Protec | 0 | 12.1 | -12.1
T516BX | REMOVE POLES 75 FROM FORMER T/L 73/ | 0 | 31.1 | -31.1
T517BX | TRANSMISSION LINE 31 POLE REPLACEME | 0 | 227.4 | -227.4
T518BX | RECONDUCTOR OF T/L 751 BETWEEN SPAR | 0 | 197.9 | -197.9
T522BX | NY - Relay Protection Upgrades | 0 | 38.6 | -38.6
T523BX | Replace Line 701/702 Pole | 0 | 3.3 | -3.3
T524BX | Repl.W. Nyack S/S Control Hous Roof | 0 | 59.1 | -59.1
T525BX | Replace Genung St. S/S Roof | 0 | 92.1 | -92.1
T526BX | 345Kv CPV Interconnection - Midltwn | 0 | 10.2 | -10.2
T527BX | 345Kv Line 94 Tap\- Preliminary En | 0 | 13.1 | -13.1
D108FA | Central Rockland - Subst Distrib Part 1 | 94.3 | 0 | 94.3
D108FB | Central Rockland - Subst Distrib Part 2 | 94.3 | 0 | 94.3
D108FC | Central Rockland - Subst Distrib Part 3 | 100.4 | 0 | 100.4
D108FD | Central Rockland - Subst Distrib Part 4 | 100.4 | 0 | 100.4
D108FE | Central Rockland - Subst Distrib Part 5 | 100.4 | 0 | 100.4
D108FF | Central Rockland - Subst Distrib Part 6 | 100.4 | 0 | 100.4
D110FX | Hartley Sub-Hartley Rd-Sub to Rt17M Dbl | 45.6 | 143.1 | -97.5
D145BC | Line 100 Upgrade | 719.3 | 0 | 719.3
D200BA | SVOC UPS C Battery Requirements | 75.9 | 0 | 75.9
D211FX | Recond 102-3-13 Rt 302-Rt17K to Cty Rt48 | 35.1 | -65.9 | 101
D214FX | Silver Lk Scotchtn Rd-Maltese Dr to Bert | 88.1 | 0 | 88.1
D241BX | Monsey 50MVA Banks & Switchgear | 24 | 0 | 24
D254BA | Blooming Grove Bank Upgrade & 2nd 35MVA Bk | 210 | 0 | 210
D261BX | West Haverstraw Bank Upgrades | 690 | 0 | 690
D267FD | Ingrassia Rd-Rt 17M to Howells Rd Recond | 40.1 | 0 | 40.1
D268FA | Pomona - Distribution Part 1 | 94.3 | 0 | 94.3
D268FB | Pomona - Distribution Part 2 | 94.3 | 0 | 94.3
D268FC | Pomona - Distribution Part 3 | 118.2 | 0 | 118.2
D268FD | Pomona - Distribution Part 4 | 118.2 | 0 | 118.2
D286FA | Decker-Howells/Decker/Dosen Reconductor | 49.4 | 0 | 49.4
D286FB | Decker-Myer Rd/Properous Valley Rd Recon | 20.2 | 0 | 20.2
D286FC | Decker-Properous Valley Rd-Howells Tnpk | 48.2 | 0 | 48.2
D286FD | Decker-Properous Valley Rd Station-Rt 17 | 331.6 | 0 | 331.6
D286FE | Decker-VanBurenville to Dosen Rd Ingrasi | 110.5 | 0 | 110.5
D287FA | Black Meadow Rd-Station-Pine Hill Recond | 363.6 | 0 | 363.6
D287FB | Pine Hill/Hillside/Gotlet-Black Meadow | 342.9 | 0 | 342.9
D298FA | SG-Reservior Rd-South St to Conklingtn R | 149.7 | 0 | 149.7
D298FB | SG-Lower Reservor Rd-Sub to South St Dbl | 91.8 | 0 | 91.8
D298FD | SG-Clowes/W Main/Grand/Canal Reconductor | 97.2 | 0 | 97.2
D299FC | Rt 42-New Vernon Rd-Winterton to Howells | 54.5 | 0 | 54.5
D343FX | B Grove Roundhill Rd Sub to Rt 208 Dbl C | 96.6 | 0 | 96.6
D345FX | KJ Forest Rd/Stevens Springs/Mntn Rd to | 22.5 | 0 | 22.5
D346FX | Midland Lakes Rd Baker Rd to Goshen Tnpk | 24.9 | 0 | 24.9
D373BX | South Goshen Second 13.2kV-35MVA Bank | 125 | 0 | 125
D378FA | Queensboro-Mine Rd - Sub to Rt 9W Recond | 7.3 | 0 | 7.3
D378FB | Queensboro-Old Rt9W-Mine Rdto Rt9W Recon | 42.5 | 0 | 42.5
D378FC | Queensboro-Rt9W-Old Rt9W to Morgan Rd Re | 53.8 | 0 | 53.8
D580FX | Old Orangeburg Rd- Lester Drive Backup | 52.7 | 0 | 52.7
D592FA | Cty Rt1-Pulaski Hwy to Pine Is Sub Recon | 24.6 | 0 | 24.6
T150BX | T/L 26 Upgrade | 12 | 135.4 | -123.4
T290BX | Hillburn 138kV Yard | 20 | 0 | 20
T296BX | Decker Switching Station | 441 | 0 | 441
T305CX | EMS Expansion | 358 | 0 | 358
|  | 5883.8 | 11728 | -5844.2

## Proj>$1M Total Spending Summary
Orange and Rockland Utilities, Inc.
Electric Rate Case - Twelve Months Ending Rate Year 3 Update
Total Estimate and Spending Summary - Projects Over $1 Million
Detail Narrative - Original vs. Current
Electric Capital Expenditures:
|  |  | Previous |  |  | Delta |  | Total
|  | Original | Quarterly | Current |  | From Prev. |  | Project Spending
| Project Description | Estimate | Estimate | Estimate | Delta | Quarter | Reason for difference | Thru 06-30-11
| Monroe Substation Upgrade & U/G Exits | 6257.3 | 8207.3 | 8207.3 | -1950 | 0 | No change | 6077.5
| Transmission Line 28 (77A) | 8199.7 | 15700 | 17240 | -9040.3 | -1540 | Revised estimate reflects escalation and contingency. Bid Pricing significantly higher for civil work associated with project. Increase also reflects need for additional staffing on project to meet regulatory requirements. | 4607.5
| Ramapo Line Terminal | 1512.4 | 4300 | 4150 | -2637.6 | 150 | Lowered cost to match projected final spending. | 4019.4
| Sugarloaf 138kv Substation | 4995.7 | 11400 | 11271 | -6275.3 | 129 | Revised to match current appropriation | 10830.7
| Little Tor Substation, OH Transmission Tap and UG Exits | 7545.8 | 14720 | 14660 | -7114.2 | 60 | Revised estimate includes OH transmission tap, escalation and contingency | 5900.5
| Snake Hill Road Substation OH Transmission Tap & Underground Circuits | 7026.6 | 16100 | 15720 | -8693.4 | 380 | Adjustment to escalation contingency and bid level pricing. | 7606.4
| Port Jervis Substation Upgrade UG Transmission Station Tie and UG Dist. Circuits | 8771.5 | 19200 | 19360 | -10588.5 | -160 | Revised estimate includes UG Transmission station tie, escalation and contingency | 3114.9
| Transmission Line 18 Upgrade | 1500 | 2072.7 | 2072.7 | -572.7 | 0 | No change | 252.7
| Spare 138 - 69kV 175MVA Transformer | 2000 | 2093 | 2097.3 | -97.3 | -4.3 | Revised to actual project costs | 2093.8
| Transmission Line 31 Upgrade | 1527.3 | 6230.4 | 6230.4 | -4703.1 | 0 | No change | 5739.3
| Pocatello Substation and UG Exits | 7505.4 | 7505.4 | 7505.4 | 0 | 0 | No change | 165.8
| Hartley Road Substation, OH Transmission Tap and UG Dist. Exits | 7359.9 | 17400 | 17620 | -10260.1 | -220 | Revised estimate includes OH transmission tap, escalation and contingency | 2686.8
| Corporate Drive Substation, UG Exits and Transmission Tap | 9800 | 33382.1 | 33382.1 | -23582.1 | 0 | No change | 28253
| Tappan Substation, OH & UG Transmission Taps and UG Dist. Exits | 8650 | 18500 | 19580 | -10930 | -1080 | Revised estimate includes OH & UG transmission taps, escalation and contingency | 1634.7
| Sterling Forest Transmission Station and Line 26 Transmission Tap | 3616.6 | 11250 | 12420 | -8803.4 | -1170 | Revised estimate includes design review, escalation & contingency | 432.4
| Spare 345 - 138kV 400MVA Transformer | 4000 | 4148.4 | 4156.9 | -156.9 | -8.5 | Revised to actual project costs | 4156.9
| Transmission Line 24 and 25 Upgrade | 13283.6 | 15106.2 | 15106.2 | -1822.6 | 0 | No change | 431
| New Hempstead Substation Upgrade and UG Exits | 7982 | 14200 | 14310 | -6328 | -110 | Revised estimate includes design review and additional UG Dist. work, escalation & contingency | 1281.4
| West Warwick Substation OH & UG Transmission Taps and UG Exits | 6884.4 | 18600 | 33830 | -26945.6 | -15230 | Wisner to West Warwick project combined with substation project. Estimate also reflects OH Transmission work, escalation and contingency. | 5.2
| Smart Grid Projects (Distribution, Substation, Communication) |  | 3678.3 | 3678.3 | -3678.3 | 0 | No change | 3403.8
| Dean Substation and UG Exits |  | 2700 | 2700 | -2700 | 0 | No change | 2714.5
| Transmission Line - Wisner to West Warwick (Moved into West Warwick Substation Project) | 4610 | 13800 | 0 | 4610 | 13800 | Project combined with West Warwick substation project. | 0
| Transmission Lines 55 and 551 Upgrade | 1490 | 988.7 | 988.7 | 501.3 | 0 | No change | 0
| Westtown Substation Upgrade and UG Exits | 2100 | 4450 | 5270 | -3170 | -820 | Revised estimate includes design review, escalation & contingency | 0
| Transmission Line 6 Upgrade - Pocatello to Decker | 2090 | 3271 | 3271 | -1181 | 0 | No change | 0
| Silver Lake Substation Upgrade | 1355 | 1355 | 1355 | 0 | 0 | No change | 0

## Proj > $1M Detail Breakdown
Orange and Rockland Utilities, Inc.
Electric Rate Case - Twelve Months Ending Rate Year 3 Update
Detail Breakdown - Projects Over $1 Million
Twelve Mo. Ending
Rate Year 3
| Project Description | Rate Case | Projected Actual |  | Accounts | Materials
|  | In Service Date | In Service Date | Payroll | Payable | & Supplies | Overheads | Total $ | Remarks
| Tranmission Line 11 Upgrade Part 2 | N/A | 2008-06-01 | 0.3 | 2.5 |  | 0.2 | 3 | This project was completed in June 2008
| Stony Point UG Exits | N/A | 2008-12-01 |  |  |  |  | 0 | This project was completed in Dec 2008.
| Monroe Substation Upgrade and UG Exits | 2008-10-31 | 2008-10-01 |  |  |  |  | 0 | This project was completed in October 2008.
| Transmission Line 28 (77A) - Ramapo to Sugarloaf | 2008-12-01 | 2012-06-01 | 27.3 | 165.2 |  | 32 | 224.5 | Final approvals have been received; project will commence in late Fall 2011.
| Ramapo 138kV Terminal | 2008-12-01 | 2011-03-01 | 248.1 | 752.8 | 87.3 | 667.6 | 1755.8 | This project was completed in March 2011
| Sugarloaf 138kV Substation and Transmission Reconfiguration | 2008-12-01 | 2011-03-01 | 626.8 | 3688.5 | 270.2 | 1695.6 | 6281.1 | The first phaes of this project was completed in April 2011. Phase 2 will be complete with the Line 28 completion.
| Little Tor Substation, OH Transmission Tap and UG Exits | 2009-02-01 | 2014-06-10 | 45.5 | 162.5 |  | 56.6 | 264.6 | Major material has been received. Working with Town on comments for DEIS. The completion date for this project has been re-prioritized to 2014.
| Snake Hill Road Substation OH Transmission Tap & Underground Circuits | 2009-05-01 | 2012-06-15 | 247.2 | 999.1 | 0.3 | 336.7 | 1583.3 | Site clearing and foundation installation currenlty underway. Completion mid-2012.
| Port Jervis Substation Upgrade UG Transmission Station Tie and UG Dist. Circuits | 2009-05-01 | 2014-06-01 | 86.9 | 122.5 |  | 121.2 | 330.6 | Planning Board approval complete. Civil contruction package currently being engineered.
| Transmission Line 18 Upgrade | 2009-06-01 | 2019-12-01 | 2.6 | 137.7 |  | 5.3 | 145.6 | This project has been delayed to coordinate with the completion of the Rio Substation in 2019.
| Spare 138 - 69kV 175MVA Transformer | 2009-06-01 | 2010-12-01 | 11.9 | 1818.8 |  | 49.7 | 1880.4 | Bank received in December 2010.
| Transmission Line 31 Upgrade | 2009-12-01 | 2011-05-01 | 163.3 | 2242.5 | 26.8 | 250.2 | 2682.8 | Constuction of the upgrade is complete with only right-of-way restoration remaining.
| Pocatello Substation and UG Exits | 2009-12-01 | 2017-06-01 | 0.3 |  |  | 0.3 | 0.6 | Project in service date re-prioritized to 2017.
| Hartley Road Substation, OH Transmission Tap and UG Dist. Exits | 2009-12-01 | 2014-06-01 | 98 | 1629.3 |  | 188.4 | 1915.7 | Currently before Planning Board for SEQRA review / Site Plan approval. EIS is also new required which may further delay project. The completion date for this project has been re-prioritized to 2014.
| Corporate Drive Substation, UG Exits and Transmission Tap | 2010-05-01 | 2011-05-01 | 824.7 | 8397 | 1242.9 | 2313.6 | 12778.2 | This project was completed in May 2011
| Spare 138X69 13.2kV 35MVA Bank | N/A | 2010-12-01 | 14.5 | 693.9 |  | 43.1 | 751.5 | Bank received in December 2010.
| Tappan Substation, OH & UG Transmission Taps and UG Dist. Exits | 2010-05-01 | 2015-06-01 | 41 | 164.9 |  | 53.9 | 259.8 | Reviewing new sites due to wetland and railroad contraints. Project has been re-piroritized to June 2015
| Sterling Forest Transmission Station and Line 26 Transmission Tap | 2010-09-01 | 2014-06-01 | 0.2 |  |  | 0.2 | 0.4 | The project in service date has been re-prioritized to 2014.
| Spare 345 - 138kV 400MVA Transformer | 2010-12-01 | 2011-06-01 | 10 | 3573.9 |  | 193.2 | 3777.1 | Bank delivery date expected in Spring 2011.
| Transmission Line 24 and 25 Upgrade | 2010-12-01 | 2018-12-01 | 0.9 | 152.3 |  | 2.6 | 155.8 | Alternate conductor types as well as a revised project of larger scope are presently being considered. The completion date for this project has been re-prioritized to 2018.
| New Hempstead Substation Upgrade and UG Exits | 2011-05-01 | 2013-06-01 | 30.1 | 522 |  | 61.1 | 613.2 | Completion date re-prioritized to June 2013.
| West Warwick Substation OH & UG Transmission Taps and UG Exits | 2011-06-01 | 2016-12-01 | 2.7 | 40.2 |  | 3.9 | 46.8 | Project in-service date re-prioritized to December 2014.
| Smart Grid Projects (Distribution, Substation, Communication) | N/A | 2012-12-31 | 81.8 | 955 |  | 154.9 | 1191.7 | Completion date adjusted to Dec. 2012.
| Dean Substation and UG Exits | N/A | 2010-12-31 | 37.7 | 373 | 0.1 | 77.6 | 488.4 | Energized in July 2010.
| Transmission Line - Wisner to West Warwick (Moved into West Warwick Project) | 2011-06-01 | [5 empty] | 0 | Moved into West warwick substation project
| Transmission Lines 55 and 551 Upgrade | 2011-06-01 | 2018-12-01 |  |  |  |  | 0 | Project in-service date re-prioritized to December 2018.
| Westtown Substation Upgrade and UG Exits | 2011-09-01 | 2014-12-01 |  |  |  |  | 0 | Project completion re-prioritized to 2014.. Project can not be started until the Port Jervis Substation Upgrade project is completed.
| Transmission Line 6 Upgrade - Pocatello to Decker | 2011-12-01 | 2018-12-01 |  |  |  |  | 0 | Project in-service date re-prioritized to December 2018.
| Silver Lake Substation Upgrade | 2011-12-01 | 2027-06-01 |  |  |  |  | 0 | Project in-service date re-prioritized to June 2027.
| Mine Torne Rd -Dean to Queensboro Dbl Ck |  | 2010-12-31 | 30.8 | 580.4 | 172 | 173.2 | 956.4 | New 13.2kV circuits from Dean assume the retired Queensboro Substation load serving Highland Falls and Fort Montgomery.
| Total | [6 empty] | 38087.3

## Narrative
Orange and Rockland Utilities, Inc.
Electric Rate Case - Twelve Months Ending Rate Year 3 Update
Electric Capital Expenditures - Projects Over $1 Million
Detail Narrative - Forecasted vs. Actuals
Electric Capital Expenditures:
|  | Actual | Expenditures
|  | Plant | in Rate
| Project Description | Expenditures | Case | Delta | Reason for difference
| Transmission Line 11 Upgrade Part 2 | 3 | 0 | -3
| Monroe Substation Upgrade and UG Exits | 0 | 0 | 0
| Transmission Line 28 (77A) Ramapo to Sugarloaf | 224.5 | 0 | -224.5 | Final approvals have been received; project will commence in late Fall 2011.
| Ramapo Line Terminal | 1755.8 | 0 | -1755.8 | Project completed in March 2011.
| Sugarloaf 138kv Substation and Transmission Reconfiguration | 6281.1 | 0 | -6281.1 | Construction continues for completion in early 2011 with outages scheduled for March 2011.
| Little Tor Substation, UG Exits and Transmission | 264.6 | 0 | -264.6 | Major material has been received. Planning Board DEIS meeting in September, 2011. The completion date for this project has been re-prioritized to 2014.
| Snake Hill Road Substation, UG Exits, Transmission OH Tap and Terminal Relays | 1583.3 | 0 | -1583.3 | Site clearing and foundation installation currenlty underway. Completion mid-2012.
| Port Jervis Substation Upgrade and UG Exits | 330.6 | 0 | -330.6 | Planning Board approval complete. Civil contruction package currently being engineered.
| Transmission Line 18 Upgrade | 145.6 | 0 | -145.6
| Transmission Line 31 Upgrade | 2682.8 | 0 | -2682.8
| Pocatello Substation and UG Exits | 0.6 | 0 | -0.6 | Project in service date re-prioritized to 2017.
| Hartley Road Substation and UG Exits | 1915.7 | 0 | -1915.7 | Currently before Planning Board for SEQRA review / Site Plan approval. EIS is also new required which may further delay project. The completion date for this project has been re-prioritized to 2014.
| Corporate Drive Substation, UG Exits and Transmission Tap | 12778.2 | -995 | -13773.2 | This project completed in May 2011
| Spare 138X69 13.2kV 35MVA Bank | 751.5 | 0 | -751.5 | Bank received in December 2010.
| Tappan Substation and UG Exits | 259.8 | 581 | 321.2 | Reviewing new sites due to wetland and railroad contraints. Project has been re-piroritized to June 2015
| Sterling Forest Line 26 Transmission Tap | 0.4 | 836 | 835.6 | The project in service date has been re-prioritized to 2014.
| Spare 345 - 138kV 400MVA Transformer | 3777.1 | 3990 | 212.9 | Bank delivery date expected in Spring 2011.
| Transmission Line 24 and 25 Upgrade | 155.8 | 3353 | 3197.2 | Alternate conductor types as well as a revised project of larger scope are presently being considered. The completion date for this project has been re-prioritized to 2018.
| New Hempstead Substation Upgrade and UG Exits | 613.2 | 7753 | 7139.8 | Completion date re-prioritized to June 2013.
| West Warwick Substation and UG Exits | 46.8 | 5683.5 | 5636.7 | Project in-service date re-prioritized to December 2014.
| Smart Grid (Distribution, Substation and Communication) | 1191.7 | 0 | -1191.7 | Completion date adjusted to Dec. 2012.
| Dean Substation | 488.4 | 0 | -488.4 | Energized in July 2010.
| Transmission Line - Wisner to West Warwick | 0 | 3570 | 3570 | Moved into West warwick substation project
| Transmission Lines 55 and 551 Upgrade | 0 | 1482 | 1482 | Project in-service date re-prioritized to December 2018.
| Westtown Substation Upgrade and UG Ckt Exits | 0 | 1697 | 1697 | Project completion re-prioritized to 2014.. Project can not be started until the Port Jervis Substation Upgrade project is completed.
| Transmission Line 6 Upgrade - Pocatello to Decker | 0 | 1720 | 1720 | Project in-service date re-prioritized to December 2018.
| Silver Lake Substation Upgrade | 0 | 1355 | 1355 | Project in-service date re-prioritized to June 2027.
| Mine Torne Rd -Dean to Queensboro Dbl Ck | 956.4 | 0 | -956.4 | New 13.2kV circuits from Dean assume the retired Queensboro Substation load serving Highland Falls and Fort Montgomery.

## Cap Ex for Calendar Year
Orange and Rockland Utilities, Inc.
Electric Rate Case - Annual Update
Summary of Electric Capital Expenditures
Calendar Year 2011 | [9 empty] | F I N A L
[5 empty] | 2011 Annual Budget |  |  | Period Ended: |  | 2011-07-31
[5 empty] | Authorized | Living |  | YTD | YTD | YTD
Budget # |  |  | 2011 Capital Expenditures | WO # | Annual Budget | Y/E Projection | Conting. | Actual | Budget | Variance
Org 30 - Control Center
New York
T | 133 | AR | Electronic Map Boards & Room Renovation for ECC/DCC | 10-2159 | 750 | 750 | 0 | 9.6 | 40.7 | 31.1
T | 239 | AE | 2011 EMS Equipment Upgrade Blanket | 10-3117 | 443 | 443 | 0 | 12.7 | 253.2 | 240.5
T | 239 | AV | 2010 EMS Equipment Upgrade Blanket | 10-2825 | 0 | -12.8 | 12.8 | -12.8 | 0 | 12.8
T | 305 | AE | 2011 JUMP Program - EMS Expansion Bkt | 10-3118 | 368 | 368 | 0 | 346.2 | 368 | 21.8
|  |  | Total Org 30- Control Center |  | 1561 | 1548.2 | 12.8 | 355.7 | 661.9 | 306.2
Org 02 - Transmission and Substation Engineering
New York
D | 115 | BX | Pocatello 69kV Substation 2-35MVA 6 Ckts | 10-6569 | 0 | 2 | -2 | 1.5 | 0 | -1.5
D | 126 | BX | Wurtsboro Upgrade | 10-2374 | 0 | 10 | -10 | 5.4 | 0 | -5.4
D | 134 | BS | NY Smart Grid Project - Subst Portion | 10-2402 | 121.7 | 121.7 | 0 | 57.4 | 121.7 | 64.3
D | 139 | BV | 2010 T&S Engneering Software/Hardware Bkt | 10-2827 | 0 | 0.4 | -0.4 | 0.4 | 0 | -0.4
D | 139 | BE | 2011 T&S Engneering Software/Hardware Bkt | 10-3119 | 40.6 | 40.6 | 0 | 0 | 0 | 0
D | 150 | BX | Relocate T/L's 841 & 851 at Mine Torn Rd and Rt 293 | 10-2463 | 0 | 1.1 | -1.1 | 1.1 | 0 | -1.1
D | 164 | BE | 2011 Distrib Substation Automation Bkt - NY |  | 120 | 0 | 120 | 0 | 9.7 | 9.7
D | 164 | BV | 2010 Distrib Substation Automation Bkt - NY | 10-2828 | 0 | 2.3 | -2.3 | 6.6 | 0 | -6.6
D | 167 | BA | Port Jervis Subst 2-35MVA Bank, 6 Ckts | 10-6912 | 408.2 | 408.2 | 0 | 194.5 | 154.4 | -40.1
D | 175 | BX | New Mobile 6 - Tilcon Facilities | 10-2695 | 0 | 4.2 | -4.2 | 4.2 | 0 | -4.2
D | 223 | BX | Monroe Two 50MVA Bank (Plus Tie Breaker) | 10-6914 | 0 | -232.1 | 232.1 | -232.1 | 0 | 232.1
D | 253 | BA | New Hartley Road Substation | 10-1420 | 3745.1 | 1873.9 | 1871.2 | 1490.1 | 1871.8 | 381.7
D | 253 | BC | New Hartley Road Transmission Tap | 10-3046 | 221.7 | 20 | 201.7 | 11.7 | 133 | 121.3
D | 256 | BL | Blooming Grove Property Purchase | 10-2970 | 0 | 300 | -300 | 14.4 | 0 | -14.4
D | 258 | BA | New Hempstead 2-50MVA Bank Upgrd & SWGR | 10-2476 | 1397.5 | 1397.5 | 0 | 34.1 | 832 | 797.9
D | 259 | BA | New Woodbury Substation Property Purchase |  | 50 | 10 | 40 | 0 | 3.2 | 3.2
D | 260 | BA | Pomona Substation | 10-1419 | 0 | 2 | -2 | 0.9 | 0 | -0.9
D | 262 | BX | Orangeburg Substation Breaker 54-3-2B Failure | 10/13-2984 | 0 | -3.4 | 3.4 | -3.4 | 0 | 3.4
D | 263 | BB | West Warwick Substation | 10-2672 | 340.6 | 340.6 | 0 | 5.6 | 12.7 | 7.1
D | 263 | BC | Transmission - Wisner to West Warwick OH | 10-3271 | 0 | 84.2 | -84.2 | 60.2 | 0 | -60.2
D | 293 | BA | New Corporate Drive Substation | 10-2443 | 613.7 | 2543 | -1929.3 | 2082.9 | 613.7 | -1469.2
D | 301 | BX | Mobile #1 Replacement |  | 201.6 | 50 | 151.6 | 0 | 20.6 | 20.6
D | 303 | BX | South Goshen Recloser 89-2-2K Replacement | 10-3041 | 0 | 35 | -35 | 6.8 | 0 | -6.8
D | 316 | BX | Congers 562-22-2 Breaker Replacement | 10-3068 | 0 | 13.5 | -13.5 | 13.5 | 0 | -13.5
D | 320 | BX | 2008/9 Spare 138X69 - 13.2kV 35MVA Bank | 10-2132 | 0 | 43.3 | -43.3 | 43.3 | 0 | -43.3
D | 323 | BX | Bullville Property Purchase | 10-3104 | 0 | 160 | -160 | 21.5 | 0 | -21.5
D | 326 | BX | Wisner Property Purchase | 10-3218 | 0 | 25 | -25 | 10 | 0 | -10
D | 329 | BX | Queensboro Substation Demolition | 13-3225 | 0 | 205.8 | -205.8 | 17.1 | 0 | -17.1
D | 374 | BA | Snake Hill Transmission OH Tap | 10-2481 | 1102 | 267.1 | 834.9 | 25.7 | 905.4 | 879.7
D | 374 | BX | Snake Hill Rd Substation W Nyack/Congers | 10-7130 | 3361.2 | 2762.3 | 598.9 | 376 | 2013.5 | 1637.5
D | 387 | BC | Little Tor Substation Transmission Tap | 10-2139 | 278.8 | 10 | 268.8 | 0 | 267.3 | 267.3
D | 387 | BX | Little Tor Substation | 10-1075 | 821.7 | 200 | 621.7 | 133.7 | 9.4 | -124.3
D | 418 | BX | Woodbury Substation Property Purchase | 10-2005 | 0 | 0.6 | -0.6 | 0.6 | 0 | -0.6
D | 445 | BE | 2011 Paving & Drainage Blanket - NY | 10-3123 | 83.9 | 83.9 | 0 | 0 | 1.2 | 1.2
D | 445 | BV | 2010 Paving & Drainage Blanket - NY | 10-2830 | 0 | 0 | 0 | 0.5 | 0 | -0.5
D | 474 | BA | New Tappan Substation - 2 50MVA Banks | 10-2144 | 601.8 | 100 | 501.8 | 45.6 | 170.2 | 124.6
D | 474 | BB | Tappan Area Substation Property Purchase | 10-2060 | 1314.8 | 300 | 1014.8 | 93.4 | 0 | -93.4
D | 474 | BC | New Tappan Substation Transmission Tap | 10-3047 | 446.7 | 10 | 436.7 | 0 | 167.7 | 167.7
D | 491 | BA | Dean 13.2kV Substation | 10-2717 | 0 | 90 | -90 | 69.9 | 0 | -69.9
D | 589 | BX | Replace Recloser Circuit - Wisner | 10-3304 | 0 | 200 | -200 | 196.2 | 0 | -196.2
T | 120 | BA | Line 11 69KV Double Circuit Upgrade II | 10-1928 | 0 | 1.3 | -1.3 | 1.3 | 0 | -1.3
T | 125 | BX | T/L 24 & 25 Upgrade | 10-1440 | 0 | 5 | -5 | -3.2 | 0 | 3.2
T | 126 | BX | Sterling Forest New 69kV Source L26 Tap | 10-2712 | 0 | 1 | -1 | 1.9 | 0 | -1.9
T | 127 | BA | New T/L Ramapo to Sugarloaf Line 28 | 10-1463 | 8474.3 | 4000 | 4474.3 | 94 | 4951.6 | 4857.6
T | 127 | BB | New Ramapo 138kV Terminal | 10-1464 | 0 | 775 | -775 | 660.9 | 0 | -660.9
T | 127 | BC | Sugarloaf Area Transm Reconfigurations | 10-2485 | 278.9 | 830 | -551.1 | 750.9 | 278.9 | -472
T | 127 | BX | Sugarloaf 138kV Yard | 10-7333 | 596.6 | 1570 | -973.4 | 1206.7 | 596.6 | -610.1
T | 134 | BE | 2011 Transmission Relay Upgrade Bkt - NY |  | 542.9 | 0 | 542.9 | 0 | 194.4 | 194.4
T | 134 | BV | 2010 Transmission Relay Upgrade Bkt - NY | 10-2831 | 0 | 50 | -50 | 18.6 | 0 | -18.6
T | 150 | BX | T/L 26 Upgrade | 10-1466 | 0 | 2.6 | -2.6 | -5.5 | 0 | 5.5
T | 167 | BD | Line 18 Upgrade | 10-2377 | 0 | 13.3 | -13.3 | -3.8 | 0 | 3.8
T | 172 | BX | Wisner Cap Bank | 10-2487 | 0 | 151 | -151 | 131.3 | 0 | -131.3
T | 174 | BX | Line 31 Reconductor | 10-2148 | 0 | 700 | -700 | 426.2 | 0 | -426.2
T | 179 | BX | Spare 345 to 138kV; 400/448 MVA Auto-transformer | 10-2358 | 3170.7 | 3350 | -179.3 | 3326.6 | 3170.7 | -155.9
T | 182 | BX | 2010 Spare 138 - 69kV 175MVA Transf Repl | 10-2357 | 0 | 10.3 | -10.3 | 13.8 | 0 | -13.8
T | 184 | BX | Bank 1300/2300 Circuit Switches | 10-2832 | 0 | 318.5 | -318.5 | 318.5 | 0 | -318.5
T | 186 | BX | TL 551 OPGW W Nyack to Snake Hill Rd | 10-2783 | 836.6 | 436.6 | 400 | 22.5 | 530.3 | 507.8
T | 187 | BX | Line 55 & 56 Structure Replacements | 10-2833 | 782.7 | 925 | -142.3 | 305.9 | 33 | -272.9
T | 272 | BX | Line 562/563 CAT-1 Optical Ground Wire | 10-2775 | 336 | 10 | 326 | 0.1 | 140 | 139.9
T | 273 | BX | Replace 69 kV Oil Circuit Breakers at Sugarloaf Substation | 10-3226 | 0 | 191.6 | -191.6 | 226.5 | 0 | -226.5
T | 279 | BA | Line 551/562 Structure Replacements | 10-3319 | 0 | 50 | -50 | 0 | 0 | 0
T | 296 | BA | Decker Substation Property Purchase | 10-2062 | 0 | 0.8 | -0.8 | 0.9 | 0 | -0.9
T | 298 | BX | Ramapo Fire Suppression System Replacemt | 10-2359 | 1004 | 100 | 904 | 66.6 | 1004 | 937.4
T | 299 | BX | ELP - Line 60 Rebuild | 10-1338 | 0 | 50 | -50 | 28 | 0 | -28
T | 473 | BX | Hudson River Crossing Towers | 10-2348 | 110.9 | 120 | -9.1 | 111.1 | 75.8 | -35.3
T | 504 | BX | T/L 311 - Shoreline Protection | 10-2668 | 712.4 | 712.4 | 0 | 94.6 | 289 | 194.4
T | 505 | BX | Replace roof at Hudson River Crossing Twr Equip Bldg | 10-2704 | 0 | 2.5 | -2.5 | 2.5 | 0 | -2.5
T | 508 | BX | Install OPGW on T/L 702 btw Burns & Harings Corner - NY | 10-2737 | 1115.2 | 1115.2 | 0 | 348.9 | 975.8 | 626.9
T | 509 | BX | T/L 311 Reconductor/Upgrade - Sloatsburg to Harriman Sub | 10-2738 | 0 | 4.1 | -4.1 | 6.6 | 0 | -6.6
T | 513 | BX | Shoreline Protection & Foundation Replacement - Tower 147, T/L 26 | 10-2966 | 275 | 275 | 0 | 10.2 | 163.8 | 153.6
T | 514 | BX | Shoreline Protection & Foundation Replacement - Tower 3, Former CH Tie Lines | 10-2967 | 345 | 345 | 0 | 10.8 | 345 | 334.2
T | 515 | BX | Shoreline Protection & Foundation Replacement - Tower 163, T/L 26 | 10-2968 | 275 | 275 | 0 | 3.6 | 163.8 | 160.2
T | 517 | BX | Line 31 Pole Replacements | 10-2974 | 0 | 12.8 | -12.8 | 12.8 | 0 | -12.8
T | 518 | BX | Line 751 Upgrade | 10/13-2983 | 0 | 883 | -883 | 195.3 | 0 | -195.3
T | 520 | BX | Line 60 CAT-1 System | 10-3125 | 222.5 | 261.9 | -39.4 | 0 | 105.4 | 105.4
T | 521 | BX | Transmission Lines Y88/94 - Drainage Improvments | 10-3048 | 0 | 5 | -5 | 0 | 0 | 0
T | 522 | BX | Relay Protection Upgrade – Line 562, Line 563, Line 702 | 10-3059 | 0 | 700 | -700 | 41.4 | 0 | -41.4
T | 523 | BX | Line 701/702 Pole Replacements | 10-3090 | 0 | 300 | -300 | 199.7 | 0 | -199.7
T | 524 | BX | West Nyack Substation Control House Roof | 10-3089 | 0 | 6.2 | -6.2 | 6.2 | 0 | -6.2
T | 525 | BX | Genung Street Substation Roof | 10-3094 | 0 | 5.2 | -5.2 | 5.2 | 0 | -5.2
T | 526 | BX | 345kV CPV Interconnection - Middletown | 10-3106 | 0 | 10.1 | -10.1 | 10.1 | 0 | -10.1
T | 527 | BX | 345kV Line 94 Tap | 10-3107 | 0 | 25 | -25 | 13 | 0 | -13
T | 529 | BX | T/L 49 Upgrade, Burns to Nanuet | 10-3287 | 0 | 75 | -75 | 0 | 0 | 0
T | 530 | BX | T/L 702 Upgrade, Burns to West Nyack | 10-3288 | 0 | 75 | -75 | 0 | 0 | 0
T | 531 | BX | Sugarloaf 69kV Substation Wiring Removal | 13-3298 | 0 | 129.5 | -129.5 | 0 | 0 | 0
|  |  | Total Org 02- T&S Engineering |  | 34350.3 | 30362.6 | 3987.7 | 13450 | 20325.6 | 6875.6
Org 02 - Distribution Engineering
New York
D | 134 | CD | NY Smart Grid Project-Distribution Portion | 10-2404 | -179.1 | 100 | -279.1 | 9.7 | -63.3 | -73
D | 153 | CX | Rt 9W Bridge Crossing - Stony Point | 50-2496 | 112 | 112 | 0 | 49.9 | 0 | -49.9
D | 167 | CA | Port Jervis Substation UG Circuit Exits | 50-3321 | 0 | 435 | -435 | 0 | 0 | 0
D | 181 | CX | Rt 59 Bridge Crossing - West Nyack | 50-2700 | 786.1 | 1000 | -213.9 | 77.3 | 201 | 123.7
D | 195 | CX | Rio Substation - UG Circuit Exits | 50-2736 | 0 | 150 | -150 | 135.3 | 0 | -135.3
D | 197 | CX | Arden Bridge - UG Thruway Crossing | 50-2760 | 0 | 26.5 | -26.5 | 26.5 | 0 | -26.5
D | 199 | CX | UG PIP Crossing - N Main St, Pomona | 50-2762 | 0 | 1.1 | -1.1 | 1.1 | 0 | -1.1
D | 201 | CE | 2011 Mobile OMS Blanket - NY | 10-3126 | 115.6 | 115.6 | 0 | 0 | 67.1 | 67.1
D | 201 | CT | 2009 Mobile OMS Blanket - NY | 10-2505 | 0 | 0 | 0 | 6.6 | 0 | -6.6
D | 201 | CV | Mobile OMS Blanket - NY | 10-2837 | 0 | 0 | 0 | 6.2 | 0 | -6.2
D | 203 | CE | 2011 Smart Grid Devices Bkt - NY |  | 115.6 | 115.6 | 0 | 0 | 84.1 | 84.1
D | 203 | CV | 2010 Smart Grid Devices Bkt - NY | 10-2839 | 0 | -16.9 | 16.9 | -16.9 | 0 | 16.9
D | 236 | CE | 2011 Distribution Cap Program Blanket - NY |  | 52.5 | 52.5 | 0 | 0 | 17.5 | 17.5
D | 236 | CT | 2009 Distribution Cap Program Blanket - NY | 10-2509 | 0 | 50.1 | -50.1 | 50.1 | 0 | -50.1
D | 240 | CE | 2011 Distribution Automation Blanket - NY | 10-3129 | 553.2 | 933.2 | -380 | 321.5 | 292.6 | -28.9
D | 240 | CT | 2009 Distribution Automation Blanket - NY | 10-2508 | 0 | -1.9 | 1.9 | -1.9 | 0 | 1.9
D | 240 | CV | 2010 Distribution Automation Blanket - NY | 10-2774 Budget 10-2842 | 0 | -78.4 | 78.4 | -78.4 | 0 | 78.4
D | 243 | CE | 2011 OMS Hardware Blanket - NY | 10-3130 | 57.2 | 57.2 | 0 | 0 | 33.3 | 33.3
D | 253 | CA | New Hartley Substation U/G Circuit Exits |  | 65 | 0 | 65 | 0 | -135.9 | -135.9
D | 258 | CA | New Hempstead U/G Circuit Exits | 50-2844 | 529.1 | 915 | -385.9 | 51.4 | 275.1 | 223.7
D | 263 | CA | Transmission from Wisner to West Warwick |  | 246.9 | 0 | 246.9 | 0 | 89.3 | 89.3
D | 277 | CE | 2011 Distrib Engineering Equipmt/Hardware Bkt |  | 45.6 | 45.6 | 0 | 0 | 27.7 | 27.7
D | 293 | CA | Corporate Dr Substation UG Circuit Exits | 50-2515 | 338.3 | 240 | 98.3 | 220.6 | 332.9 | 112.3
D | 293 | CB | New 138kV UG Transm to Corporate Dr Sub | 50-2415 | 3331.4 | 4075 | -743.6 | 3343.7 | 3331.4 | -12.3
D | 296 | CX | Cable Failure - UG Cable Replacement - Ckt 60-3-13 Under Garden State Parkway | 50-3031 | 0 | 0.1 | -0.1 | 0.1 | 0 | -0.1
D | 317 | CD | 2011 OMS Development | 10-3133 | 225.2 | 225.2 | 0 | 0 | 131.4 | 131.4
D | 333 | CX | UG Mainline Rt 17M/Exit 122 (N Main St.) Reconfig NYSDOT Proj. | 50-3246 | 0 | 375 | -375 | 356 | 0 | -356
D | 374 | CX | Snake Hill Road Substation U/G Exits | 50-1812 | 1650 | 1240.5 | 409.5 | 234.5 | 1020.6 | 786.1
D | 387 | CA | Little Tor Substation UG Ckt Exits |  | 393.3 | 0 | 393.3 | 0 | 14 | 14
D | 404 | CX | Scotland Hill Rd. Electric and Gas Utility Boring Study | 50-1974 | 0 | -2.5 | 2.5 | -2.5 | 0 | 2.5
D | 474 | CA | Tappan Substation U/G Circuit Exits |  | 54.8 | 0 | 54.8 | 0 | 0 | 0
D | 492 | CX | Chester Cable Bank 168 Replacement | 50-2521 | 347.3 | 347.3 | 0 | 17.3 | 0 | -17.3
D | 494 | CC | 2011 NRG Development | 10-3134 | 225.4 | 50 | 175.4 | 0 | 131.3 | 131.3
|  |  | Total Org 02 - Dist Engr |  | 9065.4 | 10562.8 | -1497.4 | 4808.1 | 5850.1 | 1042
[6 empty] | Should be | 2174
Org 07 - Electric Operations
New York
D |  | FX | Electric Distribution Blankets - NY | 10-various | 11392.2 | 11580.4 | -188.2 | 5148 | 7658.5 | 2510.5
D |  | FX | New Business Blankets - NY | 10-various | 3264.2 | 3264.2 | 0 | 1013.8 | 648.6 | -365.2
D | 010 | FE | 2011 Transformers - O/H NY (Incl Contributions) | 10-0131 | 1939.3 | 1939.3 | 0 | 1461.6 | 1172.1 | -289.5
D | 010 | FV | 2010 Transformers - O/H NY (Incl Contributions) | 10-0130 | 0 | -394.6 | 394.6 | -394.6 | 0 | 394.6
D | 011 | FE | 2011 O/H Capital Tools Blanket (NY) | 10-3145 | 91.7 | 81.8 | 9.9 | 14.3 | 55.1 | 40.8
D | 011 | FT | 2009 O/H Capital Tools Blanket (NY) | 10-2546 | 0 | -1 | 1 | -1 | 0 | 1
D | 011 | FV | 2010 O/H Capital Tools Blanket (NY) | 10-2873 | 0 | 16.2 | -16.2 | 6.8 | 0 | -6.8
D | 110 | FA | Hartley Sub-Owens Rd-Sub to Philipsburg |  | 378.5 | 0 | 378.5 | 0 | 378.5 | 378.5
D | 110 | FB | Hartley Sub-Echo Lk Rd-Sub to Golf Links |  | 472.9 | 0 | 472.9 | 0 | 472.9 | 472.9
D | 110 | FX | Hartley Sub-Hartley Rd-Sub to Rt17M Dbl | 10-2073 | 0 | 45.2 | -45.2 | 45.2 | 0 | -45.2
D | 120 | FX | Route 17M - Hartley Rd to Denton Hill Rd | 10-2346 | 287.3 | 287.3 | 0 | 77.6 | 135.5 | 57.9
D | 152 | FA | 2010 Electric Information Management System | 10-2958 | 0 | 88.2 | -88.2 | 88.2 | 0 | -88.2
D | 174 | FX | Tappan Sub-Livingston to Oak Tree Recon | 10-2567 | 0 | 50 | -50 | 31.8 | 0 | -31.8
D | 180 | FE | 2011 NY Incremental Reliability - Defective Poles | 10-3216 | 0 | 949 | -949 | 568.3 | 0 | -568.3
D | 180 | FX | 2009 NY Incremental Reliability - Defective Poles | 10-2699 | 0 | 6.3 | -6.3 | 6.3 | 0 | -6.3
D | 217 | FX | Twin Ave Reconductor - Spring Valley | 10-2765 | 0 | 11.7 | -11.7 | 11.7 | 0 | -11.7
D | 229 | FB | Knight Rd to Cty Rd 31 to White Rd, Rio | 10-2551 | 0 | 278.3 | -278.3 | 266 | 0 | -266
D | 231 | FA | Mud Mills-Silver Lk to Cottage St Recond |  | 154.6 | 154.6 | 0 | 0 | 0 | 0
D | 250 | FX | 2010 System Improvement - Helm Hill & Round Hill Rd | 10-2957 | 0 | 40 | -40 | 14.5 | 0 | -14.5
D | 252 | FX | Sarah Wells Trail, Goshen | 10-2964 | 0 | 269 | -269 | 0 | 0 | 0
D | 255 | FX | NY Incremental Defective Poles | 10-2965 | 0 | 65.7 | -65.7 | 62.2 | 0 | -62.2
D | 267 | FD | Ingrassia Rd-Rt 17M to Howells Rd Recond | 10-2552 | 399.9 | 0 | 399.9 | 0 | 0 | 0
D | 291 | FE | 2011 PCB Oil Testing And Disposal Blanket | 14-3148 | 104.4 | 104.4 | 0 | 66.5 | 13.2 | -53.3
D | 291 | FV | 2010 PCB Oil Testing And Disposal Blanket | 10-2878 | 0 | -0.4 | 0.4 | -0.4 | 87.3 | 87.7
D | 299 | FA | Rt 42 - Peenpack Rd to End of Ckt Recond |  | 336.8 | 0 | 336.8 | 0 | 275.6 | 275.6
D | 299 | FB | Rt 42-End of Ckt to Old Plank Rd Recondu |  | 275.6 | 0 | 275.6 | 0 | 0 | 0
D | 304 | FX | NYSDOT - Rt 59 Dbl Ckt - West Nyack |  | 157.4 | 157.4 | 0 | 0 | 0 | 0
D | 305 | FX | NYSDOT - Viaduct Rd Recond - West Nyack |  | 77.7 | 0 | 77.7 | 0 | 0 | 0
D | 307 | FX | Samsondale Ave Conversion - W Haverstraw | 10-2884 | 0 | 1.6 | -1.6 | 1.6 | 0 | -1.6
D | 308 | FX | Rye Hill Rd Subdivision Feed 61-2-13 |  | 79.9 | 79.9 | 0 | 0 | 0 | 0
D | 327 | FX | New Hempstead Road Widening Project, Phase 1 | 10-3223 | 0 | 199.3 | -199.3 | 199.3 | 0 | -199.3
D | 327 | FC | New Hempstead Road - Eberling to John St | 10-3317 | 0 | 223.5 | -223.5 | 0 | 0 | 0
D | 328 | FX | Leber Road Reconductor & Extension Blauvelt, NY | 10-3224 | 0 | 163.6 | -163.6 | 163.6 | 0 | -163.6
D | 330 | FX | Chester Distribution Part 1B - Hambletonian Ave | 10-3236 | 0 | 83.8 | -83.8 | 0 | 0 | 0
D | 341 | FX | County Rd 41 Reconduct and Convert - Rio | 10-2887 | 675.2 | 625.1 | 50.1 | 625.1 | 675.2 | 50.1
D | 347 | FB | Ski-Run Road - Burlingham Road to Step | 10-2556 | 0 | -3.3 | 3.3 | -3.3 | 0 | 3.3
D | 351 | FX | South St Conversion - Goshen | 10-3149 | 328.8 | 328.8 | 0 | 88.1 | 328.8 | 240.7
D | 353 | FX | Orchard Hill Rd Conversion - Monroe |  | 561.8 | 0 | 561.8 | 0 | 492.7 | 492.7
D | 358 | FA | Oak Tree Rd West Double Ckt - Tappan |  | 290.7 | 0 | 290.7 | 0 | 0 | 0
D | 360 | FC | Westtown Ckt103-2-13 Unionville Conv Pt2 |  | 462.1 | 0 | 462.1 | 0 | 462.1 | 462.1
D | 362 | FA | Snake Hill Rd - Old Mill Rd West Dbl Ckt | 10-1852 | 0 | 33.1 | -33.1 | 33.1 | 0 | -33.1
D | 362 | FH | Snake Hill Rd - West Nyack Rd Double Ckt | 10-2889 | 209.6 | 239.9 | -30.3 | 134.9 | 209.6 | 74.7
D | 370 | FX | Rio-County Road 31 | 10-2891 | 0 | 350.5 | -350.5 | 0 | 0 | 0
D | 378 | FX | Closter Rd Reconductor | 10-3152 | 147.8 | 210.3 | -62.5 | 68.7 | 147.8 | 79.1
D | 379 | FX | Willow Grove Rd Extension/Tie |  | 238 | 0 | 238 | 0 | 168.1 | 168.1
D | 381 | FX | 2010 LTS Sys Improv - Arden House |  | 93.7 | 0 | 93.7 | 0 | 0 | 0
D | 388 | FX | Rio-White Rd | 10-3302 | 0 | 730.1 | -730.1 | 137.3 | 0 | -137.3
D | 397 | FC | Mine Torne Rd -Dean to Queensboro Dbl Ck | 10-2805 | 0 | -117.3 | 117.3 | -117.3 | 0 | 117.3
D | 397 | FX | Mine Torne Rd -Queensboro to Rt9W Recond | 10-2559 | 0 | -2.8 | 2.8 | -2.8 | 0 | 2.8
D | 399 | FC | Tower Dr - Rt 211 to Industrial Dbl Ckt | 10-2893 | 0 | 242.1 | -242.1 | 0 | 0 | 0
D | 410 | FC | Laroe Road Widening - Part 4 | 10-2894 | 0 | 15 | -15 | 7.3 | 0 | -7.3
D | 459 | FX | Saddle River Rd Reconductor - Monsey |  | 272.3 | 272.3 | 0 | 0 | 81.6 | 81.6
D | 463 | FC | Corporate Drive - Hunt Rd Reconductor | 10-2896 | 0 | 21.9 | -21.9 | 21.9 | 0 | -21.9
D | 464 | FX | SV-Upgrade&Rem Step from Main St - 25/18 | 10-3155 | 104.2 | 104.2 | 0 | 77.8 | 104.2 | 26.4
D | 470 | FX | Spring Valley - Brick Church Rd Reconductor | 10-3156 | 167.8 | 240 | -72.2 | 228.1 | 167.8 | -60.3
D | 496 | FX | Nanuet - College Rd Reconductor & Extend | 10-2897 | 51.4 | 135 | -83.6 | 135 | 51.4 | -83.6
D | 497 | FX | Williams Ave Upgrade Conv, Spring Valley | 10-2898 | 0 | 249.3 | -249.3 | 223.2 | 0 | -223.2
D | 532 | FA | Repl Defect Poles Ckt 5-10-34 Rt209 Pt 2 | 10-1859 | 307.8 | 0 | 307.8 | 0 | 307.8 | 307.8
D | 532 | FC | Repl Defect Poles Ckt 5-10-34 Rt209 Pt 3 | 10-3322 | 0 | 310.1 | -310.1 | 0 | 0 | 0
D | 562 | FX | Warwick RR Easement/Third Street | 10-3277 | 0 | 238.9 | -238.9 | 0 | 0 | 0
D | 576 | FX | Stray Voltage - Electric Information Mgt Sys Upgrade | 10-2103 | 0 | 46.8 | -46.8 | 46.8 | 0 | -46.8
D | 582 | FA | Chester Dist Part 2 Carpenter Ave Feed C | 10-2565 | 45.3 | 122.8 | -77.5 | 0 | 45.3 | 45.3
D | 582 | FX | Chester Distribution Part 1 - Elkay Exits/Leone Lane | 10-2256 | 0 | 79.3 | -79.3 | 79.3 | 0 | -79.3
D | 583 | FR | 2008 NY incremental Reliability - Defective Poles | 10-2259 | 0 | -5.9 | 5.9 | -5.9 | 0 | 5.9
D | 598 | FX | Route 9W Road Widening Stony Point | 10-3313 | 0 | 167.1 | -167.1 | 0 | 0 | 0
T | 528 | FE | NY Trans Sys Defective Repair Stray Voltage Bkt | 10-3215 | 0 | 450 | -450 | 44.1 | 0 | -44.1
D |  | FX | Electric Distribution Blankets - NY | 50-various | 838.9 | 1441.3 | -602.4 | 949.7 | 1602.3 | 652.6
D |  | FX | New Business Blankets - NY | 50-various | 2601.4 | 1851.4 | 750 | 1150.2 | 450.9 | -699.3
D | 010 | FE | 2011 Transformers - U/G NY (Incl Contributions) | 50-0131 | 3666.2 | 3321.3 | 344.9 | 241 | 2449.7 | 2208.7
D | 010 | FV | 2010 Transformers - U/G NY (Incl Contributions) | 50-0130 | 0 | 208.2 | -208.2 | 208.2 | 0 | -208.2
D | 104 | FX | UG Rebuild - Rebuild approx 1050' - Richard Court | 50-2299 | 0 | 2.1 | -2.1 | 1 | 0 | -1
D | 118 | FB | Woodbury Junction - Phase 2 | 50-3037 | 0 | -18.2 | 18.2 | -18.2 | 0 | 18.2
D | 171 | FE | 2011 U/G Rebuild Blanket (NY) | 50-3146 | 1548.6 | 356.3 | 1192.3 | 247.9 | 832.7 | 584.8
D | 171 | FV | 2010 U/G Rebuild Blanket (NY) | 50-2874 | 0 | 37.4 | -37.4 | 26.9 | 0 | -26.9
D | 172 | FE | 2011 U/G Gasification (Rehab) Blanket (NY) | 50-0696 | 232.3 | 232.3 | 0 | 156.7 | 165.4 | 8.7
D | 266 | FX | UG Rebuild - Rockwood Circle - Middletown, NY | 50-3000 | 0 | 4.2 | -4.2 | 4.2 | 0 | -4.2
D | 273 | FX | UG Rebuild - Sunbury Dr. New City, NY Install F/I & MOVs | 50-3010 | 0 | 15.7 | -15.7 | 15.7 | 0 | -15.7
D | 274 | FX | UG Rebuild - Jean Ln. Monsey, NY & Install F/I & MOVs | 50-3011 | 0 | 21.7 | -21.7 | 21.7 | 0 | -21.7
D | 275 | FX | UG Rebuild - Pacesetter Park Pomona, NY & Install F/I & MOVs | 50-3012 | 0 | 16.4 | -16.4 | 16.4 | 0 | -16.4
D | 310 | FX | UG Rebuild Fringe Ct and install F/I & MOV | 50-3050 | 0 | 42.7 | -42.7 | 42.7 | 0 | -42.7
D | 331 | FA | UG Rebuild - Blossom Road - Bookhill Homes | 50-3250 | 0 | 127.1 | -127.1 | 127.1 | 0 | -127.1
D | 331 | FB | UG Rebuild - Worthington Court - West Nyack | 50-3244 | 0 | 133.2 | -133.2 | 0 | 0 | 0
D | 331 | FC | UG Rebuild - Country Club Lane - Pomona | 50-3254 | 0 | 191.6 | -191.6 | 103.7 | 0 | -103.7
D | 331 | FD | UG Rebuild - Dashew Drive, Suffern | 50-3262 | 0 | 233.3 | -233.3 | 0 | 0 | 0
D | 331 | FE | UG Rebuild - Rebuild 2,600' - Lillian St, Pomona | 50-3278 | 0 | 145.3 | -145.3 | 10.4 | 0 | -10.4
D | 331 | FF | UG Rebuild - Rebuild 1,000' - Crownlyn Ct, Bardonia | 50-3279 | 0 | 146.7 | -146.7 | 25.7 | 0 | -25.7
D | 331 | FG | UG Rebuild - Rebuild approx. 4,200' - West Burda Place, New City | 50-3280 | 0 | 202.9 | -202.9 | 22.6 | 0 | -22.6
D | 536 | FX | Bradley Corporate Park | 50-3261 | 0 | 167 | -167 | 0 | 0 | 0
D | 565 | FE | 2011 U/G Capital Tools Blanket (NY) | 50-3157 | 57.8 | 57.8 | 0 | 4 | 38.5 | 34.5
D | 565 | FV | 2010 U/G Capital Tools Blanket (NY) | 50-2900 | 0 | 7.5 | -7.5 | 7.5 | 0 | -7.5
|  |  | Total Organization 07 |  | 32314.1 | 33773.2 | -1459.1 | 14037.8 | 19679.2 | 5641.4
Org 29 - Substations
New York
T | 015 | ZE | 2011 Substation Department Blanket - NY | 10-3159 | 65.3 | 65.3 | 0 | 20.2 | 37.2 | 17
T | 015 | ZV | 2010 Substation Department Blanket - NY | 10-2905 | 0 | 0 | 0 | -12 | 0 | 12
T | 016 | ZE | 2011 Install Battery Banks Blanket - NY | 10-3158 | 28.4 | 28.4 | 0 | 10.8 | 28.4 | 17.6
T | 016 | ZT | 2009 Install Battery Banks Blanket - NY | 10-2569 | 0 | 0 | 0 | -2.2 | 0 | 2.2
T | 016 | ZV | 2010 Install Battery Banks Blanket - NY | 10-2906 | 0 | 0 | 0 | 1.9 | 0 | -1.9
T | 017 | ZE | 2011 Relay Department Blanket | 10-3160 | 42 | 42 | 0 | 1.6 | 42 | 40.4
T | 018 | ZE | 2011 Purchase Relay Test Set Bkt | 10-3161 | 67.3 | 67.3 | 0 | 0 | 67.3 | 67.3
T | 018 | ZV | 2010 Purchase Relay Test Set Bkt | 10-2908 | 0 | 0 | 0 | 9.9 | 0 | -9.9
T | 356 | ZE | 2011 Substation Small Equipment Blanket - NY | 10-3162 | 48 | 48 | 0 | 6.3 | 24 | 17.7
|  |  | Total Org 29 |  | 251 | 251 | 0 | 36.5 | 198.9 | 162.4
Org 23 - Information Resources
New York
D | 134 | MC | NY Smart Grid Project-Communications Por | 10-2403 | 266.7 | 266.7 | 0 | 140.5 | 176.6 | 36.1
T | 114 | ME | 2011 Substation Comm. Protection Bkt - NY | 10-3207 | 47.2 | 47.2 | 0 | 0 | 19 | 19
T | 114 | MV | 2010 Substation Comm. Protection Bkt - NY | 10-2956 | 0 | 0.3 | -0.3 | 0.3 | 0 | -0.3
|  |  | Total Org 23 |  | 313.9 | 314.2 | -0.3 | 140.8 | 195.6 | 54.8
Org 19 - Facilities
D | 200 | NB | SVOC UPS A&B Battery Requirements |  | 96 | 0 | 96 | 0 | 51.5 | 51.5
D | 440 | NE | 2011 Pole Butt Removal Blanket | 13-3105 | 29.8 | 29.8 | 0 | 12.9 | 17.4 | 4.5
D | 440 | NV | Pole Butt Removal Blanket | 13-2921 | 0 | -2.3 | 2.3 | -3 | 0 | 3
|  |  | Total Org 19 |  | 125.8 | 27.5 | 98.3 | 9.9 | 68.9 | 59
Org 13 - Stores
D | 290 | GE | 2011 Sale Of Scrap Blanket | 14-3185 | 45 | 45 | 0 | -45.2 | 21.6 | 66.8
D | 290 | GV | 2010 Sale Of Scrap Blanket | 14-2931 | 0 | 0 | 0 | -17.1 | 0 | 17.1
|  |  | Total Stores |  | 45 | 45 | 0 | -62.3 | 21.6 | 83.9
Org 14 - Customer Service
New York
D | 107 | WV | Electric Meter Purchases - NY | 10-0777 | 692.4 | 692.4 | 0 | 126.9 | 343.6 | 216.7
D | 194 | WV | Electric Meter 1st Install Bkt - NY | 10-0888 | 1293 | 1000 | 293 | 332.2 | 718.9 | 386.7
D | 202 | WE | 2011 SG Metering Upgrade Bkt - NY |  | 235.2 | 0 | 235.2 | 0 | 137.2 | 137.2
D | 237 | WE | 2011 Load Study Meters - NY |  | 32.4 | 0 | 32.4 | 0 | 18.9 | 18.9
D | 400 | WE | 2011 Electric Meter Dept. Misc. Equipment Bkt | 10-3167 | 164.2 | 161.2 | 3 | 0 | 90.4 | 90.4
D | 400 | WV | 2010 Electric Meter Dept. Misc. Equipment Bkt | 10-2914 | 0 | -49.6 | 49.6 | -49.6 | 0 | 49.6
D | 439 | WE | 2011 Bank Metering Upgrade Blanket - NY |  | 57.6 | 57.6 | 0 | 0 | 33.6 | 33.6
D | 439 | WV | 2010 Bank Metering Upgrade Blanket - NY | 10-2915 | 0 | 0.4 | -0.4 | 0.4 | 0 | -0.4
|  |  | Total Org 14 |  | 2474.8 | 1862 | 612.8 | 409.9 | 1342.6 | 932.7
Corporate
New York
D | 144 | VF | Transformer Intercompany Sales Blanket - NY OH & UG | 10/50-0100 | 0 | -510.7 | 510.7 | -510.7 | 0 | 510.7
D | 144 | VW | Meter Intercompany Sales Blanket - NY | 10-0101 | 0 | 13.1 | -13.1 | 13.1 | 0 | -13.1
[5 empty] | 0 | -497.6 | 497.6 | -497.6 | 0 | 497.6
No Organization - Carryover
D | 110 | YX | 1999 A&G Blanket | 11-1999 | 0 | 0 | 0 | 0.6 | 0 | -0.6
T | 120 | KX | ORU v. Lockwood, Kessler & Bartlett Engineers - Line 11 | 10-2671 | 0 | 0 | 0 | -449.9 | 0 | 449.9
|  |  | Total Org |  | 0 | 0 | 0 | -449.3 | 0 | 449.3
SMART GRID
D | 376 | VA | Capacitor Opimization & Phase Balancing - Smart Grid Investment Grant | 10-3021 | 208.2 | 250.8 | -42.6 | 191.5 | 166 | -25.5
T | 376 | VA | NYISO Transmission Capacitors |  | 330 | 330 | 0 | 0 | 245.8 | 245.8
|  |  | Total Smart Grid |  | 538.2 | 580.8 | -42.6 | 191.5 | 411.8 | 220.3
|  |  | TOTAL Co. |  | 81039.5 | 78829.7 | 2209.8 | 32431 | 48756.2 | 16325.2
[6 empty] | should be | 2174
Note on H13: murphyrodriguezk: Year end accrual credit
Note on H20: murphyrodriguezk: $2.0 per MJ Zazzero email 07/22/11
Note on H21: murphyrodriguezk: $10.0 per MJ Zazzero email 06/17/11
Note on H23: murphyrodriguezk: $0.4 per MJ Zazzero email 04/25/11
Note on H25: murphyrodriguezk: $0.3 per M J Zazzero email 03/21/11 $0.8 per MJ Zazzero email 04/25/11
Note on H26: murphyrodriguezk: $120.0 per MJ Zazzero email 04/25/11
Note on H27: murphyrodriguezk: $2.3 per MJ Zazzero email 02/22/11
Note on H29: murphyrodriguezk: $4.2 per M J Zazzero email 03/21/11
Note on H30: murphyrodriguezk: $232.1 per M J Zazzero email 03/21/11
Note on H31: murphyrodriguezk: $1745.1 per MJ Zazzero email 02/22/11 $116.1 to fund D693BX per CBPC approp 03/24/11 $10.0 to fund R661VX per CBPC approp 03/24/11
Note on H32: murphyrodriguezk: $201.7 per MJ Zazzero email 06/17/11
Note on H33: murphyrodriguezk: $300.0 per M J Zazzero email 03/21/11
Note on H35: murphyrodriguezk: $40.0 per MJ Zazzero email 04/25/11
Note on H36: murphyrodriguezk: $2.0 per MJ Zazzero email 07/22/11
Note on H37: murphyrodriguezk: $3.4 per MJ Zazzero email 02/22/11
Note on H39: murphyrodriguezk: $84.2 per MJ Zazzero email 05/20/11
Note on H40: murphyrodriguezk: $1636.3 per MJ Zazzero email 02/22/11 $293.0 per MJ Zazzero email 06/17/11
Note on H41: murphyrodriguezk: $151.6 per MJ Zazzero email 02/22/11
Note on H42: murphyrodriguezk: $35.0 per M J Zazzero email 03/21/11
Note on H43: murphyrodriguezk: $9.5 per M J Zazzero email 03/21/11 $4.0 per MJ Zazzero email 04/25/11
Note on H44: murphyrodriguezk: $35.0 per M J Zazzero email 03/21/11 $8.0 per MJ Zazzero email 04/25/11 $10.0 per MJ Zazzero email 06/17/11 $0.3 per MJ Zazzero email 06/17/11
Note on H45: murphyrodriguezk: $30.0 per M J Zazzero email 03/21/11 $20.0 per MJ Zazzero email 04/25/11 $150.0 per MJ Zazzero email 06/17/11
Note on H46: murphyrodriguezk: $25.0 per MJ Zazzero email 05/20/11
Note on H47: murphyrodriguezk: $205.8per MJ Zazzero email 04/25/11
Note on H48: murphyrodriguezk: $834.9 per MJ Zazzero email 04/25/11
Note on H49: murphyrodriguezk: $363.7 per MJ Zazzero email 04/25/11 $235.2 per MJ Zazzero email 06/17/11
Note on H50: murphyrodriguezk: $268.8 per MJ Zazzero email 02/22/11
Note on H51: murphyrodriguezk: $521.7 per MJ Zazzero email 02/22/11 $100.0 per MJ Zazzero email 04/25/11
Note on H52: murphyrodriguezk: $0.6 per MJ Zazzero email 07/22/11
Note on H55: murphyrodriguezk: $501.8 per MJ Zazzero email 02/22/11
Note on H56: murphyrodriguezk: $1014.8 per MJ Zazzero email 02/22/11
Note on H57: murphyrodriguezk: $436.7 per MJ Zazzero email 02/22/11
Note on H58: murphyrodriguezk: $50.0 per M J Zazzero email 03/21/11 $40.0 per MJ Zazzero email 04/25/11
Note on H59: murphyrodriguezk: $200.0 per MJ Zazzero email 08/22/11
Note on H60: murphyrodriguezk: $1.3 per M J Zazzero email 03/21/11
Note on H61: murphyrodriguezk: $3.2 per M J Zazzero email 03/21/11 $1.8 per MJ Zazzero email 05/20/11
Note on H62: murphyrodriguezk: $1.0 per MJ Zazzero email 07/22/11
Note on H63: murphyrodriguezk: $150.0 to fund T529BX and T530BX per CBPC auth 05/25/11 $129.5 to fund T531BX per CBPC auth 06/22/11 $114.4 to fund T520BX and T732BC per CBPC auth 07/28/11 $50.0 to fund T279BA per CBPC auth 07/28/11 $4030.4 per MJ Zazzero email 08/22/11
Note on H64: murphyrodriguezk: $958.0 per MJ Zazzero email 02/22/11 $183.0 per MJ Zazzero email 05/20/11
Note on H65: murphyrodriguezk: $391.1 per MJ Zazzero email 02/22/11 $90.0 per MJ Zazzero email 04/25/11 $70.0 per MJ Zazzero email 05/20/11
Note on H66: murphyrodriguezk: $458.4 per MJ Zazzero email 02/22/11 $345.0 per MJ Zazzero email 04/25/11 $170.0per MJ Zazzero email 05/20/11
Note on H67: murphyrodriguezk: $542.9 per MJ Zazzero email 04/25/11
Note on H68: murphyrodriguezk: $50.0 per MJ Zazzero email 02/22/11
Note on H69: murphyrodriguezk: $2.6 per M J Zazzero email 03/21/11
Note on H70: murphyrodriguezk: $13.3 per M J Zazzero email 03/21/11
Note on H71: murphyrodriguezk: $130.0 per MJ Zazzero email 02/22/11 $21.0 per MJ Zazzero email 08/22/11
Note on H72: murphyrodriguezk: $500.0 per MJ Zazzero email 02/22/11 $200.0 per MJ Zazzero email 07/22/11
Note on H73: murphyrodriguezk: $170.7 per MJ Zazzero email 02/22/11 $400.0 per MJ Zazzero email 05/20/11 $50.0 per MJ Zazzero email 06/17/11
Note on H74: murphyrodriguezk: $9.5 per MJ Zazzero email 02/22/11 $0.8 per MJ Zazzero email 07/22/11
Note on H75: murphyrodriguezk: $300.0 per MJ Zazzero email 02/22/11 $5.3 per MJ Zazzero email 05/20/11 $13.2 per MJ Zazzero email 06/17/11
Note on H76: murphyrodriguezk: $400.0 per MJ Zazzero email 08/22/11
Note on H77: murphyrodriguezk: $142.3 per MJ Zazzero email 06/17/11
Note on H78: murphyrodriguezk: $326.0 per MJ Zazzero email 06/17/11
Note on H79: murphyrodriguezk: $200.0 per M J Zazzero email 03/21/11 $8.4 per MJ Zazzero email 06/17/11
Note on H80: murphyrodriguezk: $50.0 funded by T127BA per CBPC auth 07/28/11
Note on H81: murphyrodriguezk: $0.4 per MJ Zazzero email 04/25/11 $0.4 per MJ Zazzero email 05/20/11
Note on H82: murphyrodriguezk: $220.0 per MJ Zazzero email 02/24/11 $684.0 per MJ Zazzero email 04/25/11
Note on H83: murphyrodriguezk: $18.0 per MJ Zazzero email 02/22/11 $32.0 per M J Zazzero email 03/21/11
Note on H84: murphyrodriguezk: $2.3 per MJ Zazzero email 06/17/11 $11.4 per MJ Zazzero email 07/22/11
Note on H86: murphyrodriguezk: $2.5 per MJ Zazzero email 04/25/11
Note on H88: murphyrodriguezk: $0.5 per M J Zazzero email 03/21/11 $1.0 per MJ Zazzero email 05/20/11 $2.6 per MJ Zazzero email 06/17/11
Note on H92: murphyrodriguezk: $12.7 per MJ Zazzero email 05/20/11 $0.1 per MJ Zazzero email 06/17/11
Note on H93: murphyrodriguezk: $716.0 per M J Zazzero email 03/21/11 $167.0 per MJ Zazzero email 07/22/11
Note on H94: murphyrodriguezk: $39.4 funded by T127BA per CBPC auth 07/28/11
Note on H95: murphyrodriguezk: $5.0 per MJ Zazzero email 06/17/11
Note on H96: murphyrodriguezk: $700.0 per MJ Zazzero email 06/17/11
Note on H97: murphyrodriguezk: $300.0 per MJ Zazzero email 02/22/11
Note on H98: murphyrodriguezk: $5.2 per MJ Zazzero email 02/22/11 $16.5 per M J Zazzero email 03/21/11 $15.5 per MJ Zazzero email 06/17/11
Note on H99: murphyrodriguezk: $5.2 per MJ Zazzero email 02/22/11
Note on H100: murphyrodriguezk: $10.0 per MJ Zazzero email 02/22/11 $0.1 per MJ Zazzero email 07/22/11
Note on H101: murphyrodriguezk: $10.0 per MJ Zazzero email 02/22/11 $15.0 per MJ Zazzero email 05/20/11
Note on H102: murphyrodriguezk: $75.0 funded by T127BA per CBPC auth 05/25/11
Note on H103: murphyrodriguezk: $75.0 funded by T127BA per CBPC auth 05/25/11
Note on H104: murphyrodriguezk: $129.5 funded by T127BA per CBPC auth 06/22/11
Note on H110: murphyrodriguezk: $179.1 per MJ Zazzero email 02/22/11 $100.0 per M J Zazzero email 03/21/11
Note on H113: murphyrodriguezk: $213.9 per MJ Zazzero email 04/25/11
Note on H114: murphyrodriguezk: $170.0 per MJ Zazzero email 02/22/11 $20.0 per MJ Zazzero email 08/22/11
Note on H115: murphyrodriguezk: $25.0 per MJ Zazzero email 02/22/11 $9.1 per M J Zazzero email 03/21/11 $7.6 per MJ Zazzero email 04/25/11
Note on H121: murphyrodriguezk: $16.9 per MJ Zazzero email 02/22/11 $2.5 per M J Zazzero email 03/21/11 $2.5 per MJ Zazzero email 04/25/11
Note on H123: murphyrodriguezk: $22.0 per MJ Zazzero email 02/22/11 $0.4 per M J Zazzero email 03/21/11 $10.1 per MJ Zazzero email 05/20/11 $17.6 per MJ Zazzero email 06/17/11
Note on H124: murphyrodriguezk: $380.0 per MJ Zazzero email 07/22/11
Note on H125: murphyrodriguezk: $1.9 per MJ Zazzero email 02/22/11
Note on H126: murphyrodriguezk: $25.0 per MJ Zazzero email 02/22/11 $75.0 per M J Zazzero email 03/21/11 $31.0 per MJ Zazzero email 05/20/11 $1.2 per MJ Zazzero email 06/17/11 $1.4 per MJ Zazzero email 07/22/11
Note on H128: murphyrodriguezk: $65.0 per MJ Zazzero email 06/17/11
Note on H129: murphyrodriguezk: $385.9 per MJ Zazzero email 04/25/11
Note on H130: murphyrodriguezk: $246.9 per MJ Zazzero email 06/17/11
Note on H132: murphyrodriguezk: $88.3 per MJ Zazzero email 04/25/11 $10.0 per MJ Zazzero email 08/22/11
Note on H133: murphyrodriguezk: $331.4 per MJ Zazzero email 02/22/11 $248.9 to fund D333CX per CBPC approp 03/24/11 $1323.9 per MJ Zazzero email 06/17/11
Note on H134: murphyrodriguezk: $0.1 per MJ Zazzero email 08/22/11
Note on H136: murphyrodriguezk: $498.9 funded by D293CB and D387CA per CBPC approp 03/24/11 $98.9 per MJ Zazzero email 04/25/11 $25.0 per MJ Zazzero email 06/17/11
Note on H137: murphyrodriguezk: $409.5 per MJ Zazzero email 04/25/11
Note on H138: murphyrodriguezk: $93.3 per MJ Zazzero email 02/22/11 $250.0 per M J Zazzero email 03/21/11 $50.0 per MJ Zazzero email 04/25/11
Note on H139: murphyrodriguezk: $2.5 per MJ Zazzero email 04/25/11
Note on H140: murphyrodriguezk: $34.8 per MJ Zazzero email 02/22/11 $00.0 per MJ Zazzero email 04/25/11
Note on H142: murphyrodriguezk: $175.4 per MJ Zazzero email 08/22/11
Note on H149: murphyrodriguezk: $553.2 per S Abuhamda email 02/22/11 $3256.5 per A Quinn email 03/16/11 $30.3 to fund D362FH per CBPC approp 03/24/11 $197.8 per A Quinn email 04/19/11 $68.6 per A Quinn email 05/20/11 $62.5 to fund D378FX per CBPC auth 05/25/11 $113.7 per A Quinn email 06/17/11 $77.5 to fund D582FA per CBPC auth 06/22/11 $322.5 per A Quinn email 07/18/11 $390.6 to fund D598FX and D238FC per CBPC auth 07/28/11 $1997.2 per A Quinn email 08/19/11
Note on H150: murphyrodriguezk: $3264.2 per A Quinn email 03/16/11
Note on H152: murphyrodriguezk: $15.8 per A Quinn email 03/16/11 $26.3 per A Quinn email 04/19/11 $9.2 per A Quinn email 05/20/11 $1.2 per A Quinn email 06/17/11 $344.5 per A Quinn email 08/19/11
Note on H153: murphyrodriguezk: $19.9 per A Quinn email 04/19/11 $10.0 per A Quinn email 08/19/11
Note on H154: murphyrodriguezk: $1.0 per A Quinn email 04/19/11
Note on H155: murphyrodriguezk: $3.7 per A Quinn email 03/16/11 $19.9 per A Quinn email 04/19/11
Note on H156: murphyrodriguezk: $378.5 per 07/28/11 CBPC meeting
Note on H157: murphyrodriguezk: $238.9 to fund D562FX per CBPC auth 05/25/11 $234.0 per 07/28/11 CBPC meeting
Note on H158: murphyrodriguezk: $46.4 per S Abuhamda email 02/22/11 $23.6 per A Quinn email 03/16/11 $24.8 per A Quinn email 08/19/11
Note on H160: murphyrodriguezk: $26.2 per S Abuhamda email 02/22/11 $2.4 per A Quinn email 03/16/11 $18.8 per A Quinn email 04/19/11 $27.6 per A Quinn email 05/20/11 $10.9 per A Quinn email 06/17/11 $2.3 per A Quinn email 07/18/11
Note on H161: murphyrodriguezk: $24.6 per S Abuhamda email 02/22/11 $25.4 per A Quinn email 03/16/11
Note on H162: murphyrodriguezk: $499.0 per A Quinn email 03/16/11 $450.0 per A Quinn email 08/19/11
Note on H163: murphyrodriguezk: $16.1 per S Abuhamda email 02/22/11 $6.1 per A Quinn email 03/16/11 $3.7 per A Quinn email 08/19/11
Note on H164: murphyrodriguezk: $11.7 per S Abuhamda email 02/22/11
Note on H165: murphyrodriguezk: $100.0 per A Quinn email 03/16/11 $45.0 per A Quinn email 04/19/11 $50.8 per A Quinn email 05/20/11 $82.5 per A Quinn email 06/17/11
Note on H166: murphyrodriguezk: $154.6 per 07/28/11 CBPC meeting $154.6 per A Quinn email 08/19/11
Note on H167: murphyrodriguezk: $12.3 per S Abuhamda email 02/22/11 $27.7 per A Quinn email 03/16/11
Note on H168: murphyrodriguezk: $269.0 per A Quinn email 03/16/11
Note on H169: murphyrodriguezk: $65.9 per S Abuhamda email 02/22/11 $35.2 per A Quinn email 03/16/11 $35.0 per A Quinn email 04/19/11
Note on H170: murphyrodriguezk: $399.9 per A Quinn email 03/16/11
Note on H172: murphyrodriguezk: $1.2 per A Quinn email 03/16/11 $0.8 per A Quinn email 04/19/11
Note on H173: murphyrodriguezk: $336.8 per A Quinn email 03/16/11
Note on H174: murphyrodriguezk: $275.6 per A Quinn email 03/16/11
Note on H176: murphyrodriguezk: $77.7 per 07/28/11 CBPC meeting
Note on H177: murphyrodriguezk: $1.8 per S Abuhamda email 02/22/11 $0.2 per A Quinn email 03/16/11
Note on H179: murphyrodriguezk: $145.6 per A Quinn email 03/16/11 $13.4 per A Quinn email 06/17/11 $34.4 per A Quinn email 07/18/11 $5.9 per A Quinn email 08/19/11
Note on H180: murphyrodriguezk: $223.5 funded by OH Dist Bkts per CBPC auth 07/28/11
Note on H181: murphyrodriguezk: $155.3 per A Quinn email 03/16/11 $8.3 per A Quinn email 06/17/11
Note on H182: murphyrodriguezk: $83.8 per A Quinn email 03/16/11
Note on H183: murphyrodriguezk: $234.1 per A Quinn email 03/16/11 $234.1 to fund vD388FX per CBPC auth 06/22/11 $239.0 per A Quinn email 07/18/11 $179.1 per A Quinn email 08/19/11
Note on H184: murphyrodriguezk: $3.3 per A Quinn email 04/19/11
Note on H186: murphyrodriguezk: $561.8 per A Quinn email 03/16/11
Note on H187: murphyrodriguezk: $290.7 per A Quinn email 08/19/11
Note on H188: murphyrodriguezk: $462.1 per A Quinn email 08/19/11
Note on H189: murphyrodriguezk: $16.5 per S Abuhamda email 02/22/11 $17.1 per A Quinn email 03/16/11 $0.5 per A Quinn email 06/17/11
Note on H190: murphyrodriguezk: $30.3 funded by OH Dist Bkts per CBPC approp 03/24/11
Note on H191: murphyrodriguezk: $350.5 funded by D267FD per CBPC approp 03/24/11
Note on H192: murphyrodriguezk: $62.5 funded by OH Dist Bkts per CBPC auth 05/25/11
Note on H193: murphyrodriguezk: $238.0 per 07/28/11 CBPC meeting
Note on H194: murphyrodriguezk: $93.7 per 07/28/11 CBPC meeting
Note on H195: murphyrodriguezk: $730.1 funded by D341FX, D299FA, D299FB per CBPC auth 06/22/11
Note on H196: murphyrodriguezk: $145.4 per A Quinn email 03/16/11 $26.0 per A Quinn email 04/19/11 $2.1 per A Quinn email 05/20/11
Note on H197: murphyrodriguezk: $9.6 per A Quinn email 03/16/11 $8.2 per A Quinn email 04/19/11 $1.4 per A Quinn email 05/20/11
Note on H198: murphyrodriguezk: $242.1 per A Quinn email 08/19/11
Note on H199: murphyrodriguezk: $15.0 per A Quinn email 04/19/11
Note on H201: murphyrodriguezk: $21.9 per S Abuhamda email 02/22/11
Note on H203: murphyrodriguezk: $72.2 per A Quinn email 03/16/11
Note on H204: murphyrodriguezk: $23.0 per A Quinn email 03/16/11 $75.6 per A Quinn email 04/19/11 $15.0 per A Quinn email 08/19/11
Note on H205: murphyrodriguezk: $249.3 per S Abuhamda email 02/22/11
Note on H206: murphyrodriguezk: $307.8 per A Quinn email 08/19/11
Note on H207: murphyrodriguezk: $310.0 per A Quinn email 08/19/11
Note on H208: murphyrodriguezk: $238.9 funded by D110FB per CBPC auth 05/25/11
Note on H209: murphyrodriguezk: $46.8 per A Quinn email 07/18/11
Note on H210: murphyrodriguezk: $77.5 funded by OH Dist Bkts per CBPC auth 06/22/11
Note on H211: murphyrodriguezk: $60.5 per S Abuhamda email 02/22/11 $89.5 per A Quinn email 03/16/11 $70.7 per A Quinn email 08/19/11
Note on H212: murphyrodriguezk: $3.5 per A Quinn email 03/16/11 $1.0 per A Quinn email 04/19/11 $1.3 per A Quinn email 05/20/11 $2.1 per A Quinn email 06/17/11
Note on H213: murphyrodriguezk: $167.1 funded by OH Dist Bkts per CBPC auth 07/28/11
Note on H214: murphyrodriguezk: $450.0 per A Quinn email 03/16/11
Note on H215: murphyrodriguezk: $128.6 per S Abuhamda email 02/22/11 $2444.0 per A Quinn email 03/16/11 $11.3 per A Quinn email 04/19/11 $167.0 to fund D536FX per A Quinn email after CBPC meeting 04/28/11 $1.9 per A Quinn email 06/17/11 $750.0 per A Quinn email 08/19/11
Note on H216: murphyrodriguezk: $2601.4 per A Quinn email 03/16/11 $750.0 per A Quinn email 08/19/11
Note on H217: murphyrodriguezk: $344.9 per A Quinn email 08/19/11
Note on H218: murphyrodriguezk: $134.8 per A Quinn email 03/16/11 $1.9 per A Quinn email 06/17/11 $344.9 per A Quinn email 08/19/11
Note on H219: murphyrodriguezk: $2.1 per A Quinn email 07/18/11
Note on H220: murphyrodriguezk: $29.5 per A Quinn email 03/16/11 $11.3 per A Quinn email 04/19/11
Note on H221: murphyrodriguezk: $438.7 to fund D331FA, D331FB, and D331FC per CBPC meeting 03/24/11 $36.0 per A Quinn email 04/19/11 $233.3 to fund D331FD per CBPC auth 04/28/11 $494.9 to fund D331FE, D331FF, and D331FG per CBPC auth 05/25/11 $57.2 per A Quinn email 06/17/11 $55.1 per A Quinn email 07/18/11 $122.9 per A Quinn email 08/19/11
Note on H222: murphyrodriguezk: $1.4 per A Quinn email 03/16/11 $36.0 per A Quinn email 04/19/11
Note on H224: murphyrodriguezk: $4.2 per A Quinn email 03/16/11
Note on H225: murphyrodriguezk: $57.2 per A Quinn email 06/17/11 $41.5 per A Quinn email 08/19/11
Note on H226: murphyrodriguezk: $35.3 per S Abuhamda email 02/22/11 $13.6 per A Quinn email 08/19/11
Note on H227: murphyrodriguezk: $16.4 per S Abuhamda email 02/22/11
Note on H228: murphyrodriguezk: $70.7 per S Abuhamda email 02/22/11 $28.0 per A Quinn email 08/19/11
Note on H229: murphyrodriguezk: $113.9 funded by UG Rebuild Bkt per CBPC meeting 03/24/11 $53.0 per A Quinn email 07/18/11 $39.8 per A Quinn email 08/19/11
Note on H230: murphyrodriguezk: $133.2 funded by UG Rebuild Bkt per CBPC meeting 03/24/11
Note on H231: murphyrodriguezk: $191.6 funded by UG Rebuild Bkt per CBPC meeting 03/24/11
Note on H232: murphyrodriguezk: $233.3 funded by UG Rebuild Bkt per CBPC meeting 04/28/11
Note on H233: murphyrodriguezk: $145.3 funded by UG Rebuild Bkt per CBPC meeting 05/25/11
Note on H234: murphyrodriguezk: $146.7 funded by UG Rebuild Bkt per CBPC meeting 05/25/11
Note on H235: murphyrodriguezk: $202.9 funded by UG Rebuild Bkt per CBPC meeting 05/25/11
Note on H236: murphyrodriguezk: $167.0 funded by UG Dist Bkets per A Quinn email following CBPC meeting 04/28/11
Note on H238: murphyrodriguezk: $6.2 per S Abuhamda email 02/22/11 $1.3 per A Quinn email 03/16/11
Note on H260: murphyrodriguezk: $0.3 per M Durling email 06/19/11
Note on H265: murphyrodriguezk: $96.0 per K Kiene email 06/14/11
Note on H267: murphyrodriguezk: $2.3 per K Kiene email 03/15/11
Note on H279: murphyrodriguezk: $293.0 per 07/28/11 CBPC meeting
Note on H280: murphyrodriguezk: $42.0 to fund P486WX per CBPC approp 03/24/11 $193.2 per T Bautz email 07/12/11
Note on H281: murphyrodriguezk: $32.4 per T Bautz email 07/12/11
Note on H282: murphyrodriguezk: $3.0 per T Bautz email 01/31/11
Note on H283: murphyrodriguezk: $23.6 per T Bautz email 03/1/11 $26.0 per 07/28/11 CBPC meeting
Note on H285: murphyrodriguezk: $0.4 per T Bautz email 03/1/11
Note on H301: murphyrodriguezk: $42.6 per MJ Zazzero email 04/25/11

## previous half yr auths over $1M
Orange and Rockland Utilities, Inc.
Electric Rate Case - Annual Update
Capital Authorizations over $1 Million
January thru June 2011
[7 empty] | F I N A L |  |  | - All Years -
|  |  |  | 2011 Annual Budget |  |  | Period Ended: |  | 2011-07-31
|  |  |  | Authorized | Living |  | YTD | YTD | YTD | Total | Total | Original | Supplmt | Supplmt | Supplmt | Supplmt | Supplmt
Budget # |  |  | 2011 Capital Expenditures | Annual Budget | Y/E Projection | Conting. | Actual | Budget | Variance | Project | Appropr. | Appropriation | #1 | #2 | #3 | #4 | #5
Org 30 - Control Center
New York
T | 127 | BB | New Ramapo 138kV Terminal | 0 | 775 | -775 | 660.9 | 0 | -660.9 | 4016.9 | 4412 | 2006-07-27 | 2007-07-26 | 2010-05-27 | 2011-01-27
T | 127 | BX | Sugarloaf 138kV Yard | 596.6 | 1570 | -973.4 | 1206.7 | 596.6 | -610.1 | 8697.7 | 9021 | PA 04/05/04 | 2006-07-27 | 2007-09-27 | 2010-08-27 | 2010-12-21 | 2011-06-22
D | 181 | CX | Rt 59 Bridge Crossing - West Nyack | 786.1 | 1000 | -213.9 | 77.3 | 201 | 123.7 | 664.9 | 1698.6 | 2009-05-28 | 2011-06-22
D | 195 | CX | Rio Substation - UG Circuit Exits | 0 | 150 | -150 | 135.3 | 0 | -135.3 | 1488.6 | 1523.2 | 2009-07-24 | 2009-09-24 | 2011-02-24
D |  | FX | Electric Distribution Blankets - NY | 11392.2 | 11580.4 | -188.2 | 5148 | 7658.5 | 2510.5 | 5148 | 11392.2 | 2011-02-24
D |  | FX | New Business Blankets - NY | 3264.2 | 3264.2 | 0 | 1013.8 | 648.6 | -365.2 | 1013.8 | 3264.2 | 2011-02-24
D | 010 | FT | 2009 Transformers - O/H NY (Incl Contributions) | 0 | 0 | 0 | 0 | 0 | 0 | 2760.2 | 2532 | 2008-10-23 | 2011-04-28
D | 010 | FE | 2011 Transformers - O/H NY (Incl Contributions) | 1939.3 | 1939.3 | 0 | 1461.6 | 1172.1 | -289.5 | 1461.6 | 1939.3 | 2011-04-28 | 2011-04-28
D | 010 | FV | 2010 Transformers - O/H NY (Incl Contributions) | 0 | -394.6 | 394.6 | -394.6 | 0 | 394.6 | 2240.3 | 2645 | 2009-10-29 | 2010-10-28 | 2011-04-28
D |  | FX | New Business Blankets - NY | 2601.4 | 1851.4 | 750 | 1150.2 | 450.9 | -699.3 | 1150.2 | 2601.4 | 2011-02-24
D | 010 | FT | 2009 Transformers - U/G NY (Incl Contributions) | 0 | 0 | 0 | 0 | 0 | 0 | 2616.2 | 2490.2 | 2008-10-23 | 2011-04-28
D | 010 | FE | 2011 Transformers - U/G NY (Incl Contributions) | 3666.2 | 3321.3 | 344.9 | 241 | 2449.7 | 2208.7 | 241 | 3666.2 | 2011-04-28 | 2011-04-28
D | 010 | FV | 2010 Transformers - U/G NY (Incl Contributions) | 0 | 208.2 | -208.2 | 208.2 | 0 | -208.2 | 1671.8 | 1329.6 | 2009-10-29 | 2011-04-28
D | 171 | FE | 2011 U/G Rebuild Blanket (NY) | 1548.6 | 356.3 | 1192.3 | 247.9 | 832.7 | 584.8 | 247.9 | 1548.6 | 2011-01-27
Note on G12: murphyrodriguezk: $958.0 per MJ Zazzero email 02/22/11 $183.0 per MJ Zazzero email 05/20/11
Note on G13: murphyrodriguezk: $458.4 per MJ Zazzero email 02/22/11 $345.0 per MJ Zazzero email 04/25/11 $170.0per MJ Zazzero email 05/20/11
Note on G14: murphyrodriguezk: $213.9 per MJ Zazzero email 04/25/11
Note on G15: murphyrodriguezk: $170.0 per MJ Zazzero email 02/22/11 $20.0 per MJ Zazzero email 08/22/11
Note on G16: murphyrodriguezk: $553.2 per S Abuhamda email 02/22/11 $3256.5 per A Quinn email 03/16/11 $30.3 to fund D362FH per CBPC approp 03/24/11 $197.8 per A Quinn email 04/19/11 $68.6 per A Quinn email 05/20/11 $62.5 to fund D378FX per CBPC auth 05/25/11 $113.7 per A Quinn email 06/17/11 $77.5 to fund D582FA per CBPC auth 06/22/11 $322.5 per A Quinn email 07/18/11 $390.6 to fund D598FX and D238FC per CBPC auth 07/28/11 $1997.2 per A Quinn email 08/19/11
Note on G17: murphyrodriguezk: $3264.2 per A Quinn email 03/16/11
Note on G20: murphyrodriguezk: $15.8 per A Quinn email 03/16/11 $26.3 per A Quinn email 04/19/11 $9.2 per A Quinn email 05/20/11 $1.2 per A Quinn email 06/17/11 $344.5 per A Quinn email 08/19/11
Note on G21: murphyrodriguezk: $2601.4 per A Quinn email 03/16/11 $750.0 per A Quinn email 08/19/11
Note on G23: murphyrodriguezk: $344.9 per A Quinn email 08/19/11
Note on G24: murphyrodriguezk: $134.8 per A Quinn email 03/16/11 $1.9 per A Quinn email 06/17/11 $344.9 per A Quinn email 08/19/11
Note on G25: murphyrodriguezk: $438.7 to fund D331FA, D331FB, and D331FC per CBPC meeting 03/24/11 $36.0 per A Quinn email 04/19/11 $233.3 to fund D331FD per CBPC auth 04/28/11 $494.9 to fund D331FE, D331FF, and D331FG per CBPC auth 05/25/11 $57.2 per A Quinn email 06/17/11 $55.1 per A Quinn email 07/18/11 $122.9 per A Quinn email 08/19/11

## Ramapo Fire Suppression System
Activity | 2010-01-01 | 2010-04-01 | 2010-07-01 | 2010-10-01 | 2011-01-01 | 2011-04-01 | 2011-07-01 | 2011-10-01
Engineering
Design
Municipal Approvals
Material Procurement
Construction
Checkout
Energize

## Ramapo Terminal
Activity | 2009-01-01 | 2009-04-01 | 2009-07-01 | 2009-10-01 | 2010-01-01 | 2010-04-01 | 2010-07-01 | 2010-10-01 | 2011-01-01
Engineering
Design
Environmental Review
Municipal Approvals
Material Procurement
Breakers
Steel
Construction
Checkout
Energize

## Sugarloaf TL Re-Configuration
Activity | 2009-10-01 | 2010-01-01 | 2010-04-01 | 2010-07-01 | 2010-10-09 | 2011-01-01 | 2011-04-01
Engineering
Survey
Design
Environmental Review
PSC Approval /Municipal Permits
Marerial Procurement
Conductor
Insulators
Hardware
Construction
Structures
Conductor
Energization
Clean-up/Restoration

## Sugarloaf Substation
Activity | 2009-01-01 | 2009-04-01 | 2009-07-01 | 2009-10-01 | 2010-01-01 | 2010-04-01 | 2010-07-01 | 2010-10-01 | 2011-01-01
Engineering
Design
Environmental Review
Municipal Approvals
Material Procurement
Breakers
Control House
Steel
Construction
Checkout
Energize

## TL 28 Ramapo to Sugarloaf
Activity | 2010-01-01 | 2010-04-01 | 2010-07-01 | 2010-10-09 | 2011-01-01 | 2011-04-01 | 2011-07-01 | 2011-10-09 | 2012-01-17 | 2012-04-26
Engineering
Survey
Design
Environmental Review
PSC Approval /Municipal Permits
Marerial Procurement
Conductor
Insulators
Hardware
Construction
Structures
Conductor
Energization
Clean-up/Restoration

## Tappan Substation
Activity | 2011-01-01 | 2011-04-01 | 2011-07-01 | 2011-10-01 | 2012-01-01 | 2012-04-01 | 2012-07-01 | 2012-10-01 | 2013-01-01 | 2013-04-01 | 2013-07-01 | 2013-10-01 | 2014-01-01 | 2014-04-01 | 2014-07-01 | 2014-10-01 | 2015-01-01 | 2015-04-01 | 2015-07-01
Property Search / Review
Property Assement
Property Purchase
Engineering
Design
Environmental Review
Municipal Approvals
Material Procurement
Transformers
Breakers
Switchgear
Construction
Checkout
Energize

## Little Tor Substation
Activity | 2009-01-01 | 2009-04-01 | 2009-07-01 | 2009-10-01 | 2010-01-01 | 2010-04-01 | 2010-07-01 | 2010-10-01 | 2011-01-01 | 2011-04-01 | 2011-07-01 | 2011-10-01 | 2012-01-01 | 2012-04-01 | 2012-10-01 | 2013-01-01 | 2013-04-01 | 2013-07-01 | 2013-10-01 | 2014-01-01 | 2014-04-01 | 2014-07-01
Engineering
Design
Environmental Review
Municipal Approvals
Material Procurement
Transformers
Breakers
Switchgear
Construction
Checkout
Energize

## Transmission Line 31
Activity | 2009-01-01 | 2009-04-01 | 2009-07-01 | 2009-10-09 | 2010-01-01 | 2010-04-01 | 2010-07-01 | 2010-10-09 | 2011-01-01 | 2011-03-26
Engineering
Survey
Design
Environmental Review
PSC Approval /Municipal Permits
Marerial Procurement
Conductor
Insulators
Hardware
Construction
Structures
Conductor
Energization
Clean-up/Restoration

## Hartley Road Substation
Activity | 2009-10-01 | 2010-01-01 | 2010-04-01 | 2010-07-01 | 2010-10-01 | 2011-01-01 | 2011-04-01 | 2011-07-01 | 2011-10-01 | 2012-01-01 | 2012-04-01 | 2012-07-01 | 2012-10-01 | 2013-01-01 | 2013-04-01 | 2013-07-01 | 2013-10-01 | 2014-01-01 | 2014-04-01 | 2014-07-01
Engineering
Design
Environmental Review
Municipal Approvals
Material Procurement
Transformers
Breakers
Switchgear
Construction
Checkout
Energize

## W. Warwick Substation
Activity | 2013-04-01 | 2013-07-01 | 2013-10-01 | 2014-01-01 | 2014-04-01 | 2014-07-01 | 2014-10-01 | 2015-01-01 | 2015-04-01 | 2015-07-01 | 2015-10-01 | 2016-01-01 | 2016-04-01
Engineering
Design
Environmental Review
Municipal Approvals
Material Procurement
Transformers
Breakers
Switchgear
Construction
Checkout
Energize

## Spare Transformers
Activity | 2010 | 2011 | 2012
Transformer Procurement
345 - 138kV 400MVA Auto Bank
138 - 69kV 175MVA
Mobile Transformer #1

## Port Jervis Substation
Activity | 2010-10-01 | 2011-01-01 | 2011-04-01 | 2011-07-01 | 2011-10-01 | 2012-01-01 | 2012-04-01 | 2012-07-01 | 2012-10-01 | 2013-01-01 | 2013-04-01 | 2013-07-01 | 2013-10-01 | 2014-01-01 | 2014-04-01
Engineering
Design
Environmental Review
Municipal Approvals
Material Procurement
UG Transmission Cable
UG Transmission Terminations
Transformers
Breakers
Switchgear
Construction
Checkout
Energize

## Snake Hill Road
Activity | 2009-01-01 | 2009-04-01 | 2009-07-01 | 2009-10-01 | 2010-01-01 | 2010-04-01 | 2010-07-01 | 2010-10-01 | 2011-01-01 | 2011-04-01 | 2011-07-01 | 2011-12-01 | 2012-04-01 | 2012-07-01
Engineering
Design
Environmental Review
Municipal Approvals
Material Procurement
Transformers
Breakers
Switchgear
Construction
Checkout
Energize

## Corporate Drive Substation
Activity | 2008-10-01 | 2009-01-01 | 2009-04-01 | 2009-07-01 | 2009-10-01 | 2010-01-01 | 2010-04-01 | 2010-07-01 | 2010-10-01 | 2011-01-01 | 2011-04-01
Engineering
Design
Environmental Review
Municipal Approvals
Material Procurement
Transformers
Breakers
Switchgear
Construction
Checkout
Energize

## TL 702 OPGW
Activity | 2010-01-01 | 2010-04-01 | 2010-07-01 | 2010-10-01 | 2011-01-01 | 2011-04-01 | 2011-07-01 | 2011-10-01
Engineering
Survey
Design
Environmental Review
State / Municipal Permits
Marerial Procurement
Conductor
Insulators
Hardware
Construction
Structures
Conductor
Energization
Clean-up/Restoration

## UG TL 702 to Corporate
Activity | 2008-10-01 | 2009-01-01 | 2009-04-01 | 2009-07-01 | 2009-10-01 | 2010-01-01 | 2010-04-01 | 2010-07-01 | 2010-10-10 | 2011-01-10 | 2011-04-10
Engineering
Design
Environmental Review
State / Municipal Permits
Material Procurement
Cable
Terminations
Splices
Construction
Final Acceptance
Energize
Transition Structure State/Municipal Approvals
Transition Structure Construction

## Sterling Forest TL 26 Tap
Activity | 2012-01-01 | 2012-04-01 | 2012-07-01 | 2012-10-01 | 2013-01-01 | 2013-04-01 | 2013-07-01 | 2013-10-01 | 2014-01-01 | 2014-04-01
Engineering
Survey
Design
Environmental Review
State / Municipal Permits
Marerial Procurement
Conductor
Insulators
Hardware
Construction
Structures
Conductor
Energization
Clean-up/Restoration

## Dean Substation
Activity | 2009-01-01 | 2009-04-01 | 2009-07-01 | 2009-10-01 | 2010-01-01 | 2010-04-01 | 2010-07-01 | 2010-10-01 | 2011-01-01
Engineering
Design
Material Procurement
Transformers
Switchgear
Construction
Checkout
Energize

## New Hempstead Substation
Activity | 2010-04-01 | 2010-07-01 | 2010-10-01 | 2011-01-01 | 2011-04-01 | 2011-07-01 | 2011-10-01 | 2012-01-01 | 2012-04-01 | 2012-07-01 | 2012-10-01 | 2013-01-01 | 2013-04-01 | 2013-07-01
Engineering
Design
Municipal Approvals
Material Procurement
Transformers
Breakers
Switchgear
Construction
Checkout
Energize

## OH-UG TL Wisner to W. Warwick
Activity | 2013-04-01 | 2013-07-01 | 2013-10-01 | 2014-01-01 | 2014-04-01 | 2014-07-01 | 2014-10-01 | 2015-01-01 | 2015-04-01 | 2015-07-01 | 2015-10-01 | 2016-01-01 | 2016-04-01
Engineering
Survey
Design
Environmental Review
State / Municipal Permits
Marerial Procurement
Conductor / Cable
Insulators
Hardware
Construction
Structures / Conduit
Conductor / Cable
Energization
Clean-up/Restoration

## TL 18 Upgrade
Activity | 2018-04-01 | 2018-07-01 | 2018-01-01 | 2019-04-01 | 2019-07-01 | 2019-10-01
Engineering
Survey
Design
Environmental Review
State / Municipal Permits
Marerial Procurement
Conductor
Insulators
Hardware
Construction
Structures
Conductor
Energization
Clean-up/Restoration

## NY Smart Grid Dist & Sub
Activity | 2011-07-01 | 2011-10-01 | 2012-01-01 | 2012-04-01 | 2012-07-01 | 2012-10-01 | 2013-01-01
Snake Hill Site work
Snake Hill Data Equipment
West Nyack Data equipment
New Distribution Circuitry
Circuit Smart Device Installation
IT hardware
DEW Software
DEW’s Reconfiguration for Restoration Algorithm
DEW Setup and Test
DEW Real-time Loss and Capacity Applications
Data collection and evaluation