## Slide 1
Construction Milestones
IPWG July 24, 2018 Draft for Discussion Only

## Slide 2: Slow Downs in the Queue
Problem: projects progress at different rates
Utilities may not be able to deploy resources efficiently
Delay creates uncertainties for projects attempting to move ahead
Transparent construction phase milestones would decrease uncertainty

## Slide 3: New SIR Timeline
Full timeline from receipt of CESIR is very long
25% due at 90 Business Days (BD)
Developer signs contract at 120 BD (24 weeks)
Balance of payment due at 210 BD (42 weeks)
SIR contemplate interconnection within 12 months after signing interconnection contract – almost 18 months after receipt of CESIR – unless additional time is justified

## Slide 4: Revised Straw Proposal
Require developer to issue utility notice to start procurement within 30 BD of full payment date
Add the date of this notice to the public data base
If developer does not release funds, project is cancelled; utility returns unspent deposit
Utility retains existing flexibility to work with developers who start procurement but don’t make interconnection milestone in 12 months