## Inventory
SIR Inventory
Date Range: | 2025-11-15 09:47
[11 empty] | System Type | [15 empty] | Metering |  |  | APPLICATION REVIEW |  |  |  | PRELIMINARY REVIEW |  |  | CESIR |  |  |  | SIR Costs |  |  | Construction
[30 empty] | 10 business days2,3 |  |  |  | 15 business days3 |  |  | 60 (up to 100) business days3 |  |  |  | CESIR Costs | Project Installation / Upgrade Costs |  | Payments
Company | Applicant Name | Developer | Application / Job # | Division | City/Town | County | Zip Code | NYISO Load Zone | Circuit ID | Substation | Hybrid (Y/N) | Related Application / Job # | PV (kWAC) | ESS (kWAC) | WIND (kWAC) | MT (kWAC) | SG (kWAC) | IG (kWAC) | FW (kWAC) | FC (kWAC) | CHP (kWAC) | GT (kWAC) | HYDRO (kWAC) | ICE (kWAC) | ST (kWAC) | OTHER (kWAC) | Metering1 (NA / NM / RNM / RC / CDG / S-SFA) | Value Stack (Y/N) | Protective Equipment | Start Date | End Date | Calculated Duration | Application Approved Date (Utility) | Start Date (Must Match Application Approved Date) | End Date | Calculated Duration | CESIR Payment Received Date | Start Date | End Date | Calculated Duration | CESIR Study cost paid by applicant4 | Estimated Upgrade Costs Identified by Utility (CESIR or Not) | Actual Project Costs Paid by Applicant | Down Payment Date | Full Payment Date | Construction Start Date | Construction Complete Date | Verification Testing or Final Acceptance Date5 | Final Letter of Acceptance Date | Project Reconciliation Date6 | Project Complete (Y/N/W) | Utility Retention of REC (Y/N) | Comments / Misc.
Central Hudson |  | Solar Works | CH-09052 | Kingston | Napanoch | Ulster | 12458 | G | 3091 | Neversink | N |  | 4 | [13 empty] | NM | N | SW 4048 | 2001-01-31 | 2001-01-31 | 0 | 2001-01-31 | [14 empty] | 2002-08-20 | 2002-08-20 |  | Y
Central Hudson |  | Solar Works | CH-09054 | Fishkill | Beacon | Dutchess | 12508 | G | 8087 | Tioronda | N |  | 4 | [13 empty] | NM | N | SW 4048 | 2001-03-02 | 2001-03-02 | 0 | 2001-03-02 | [14 empty] | 2002-09-04 | 2002-09-04 |  | Y
Central Hudson |  | Self | CH-08877 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6042 | Spackenkill | N |  | 2 | [13 empty] | NM | N | GC-1000 | 2001-07-23 | 2001-07-23 | 0 | 2001-07-23 | [14 empty] | 2001-12-06 | 2001-12-06 |  | Y
Central Hudson |  | Sunstruck Design | CH-09690 | Newburgh | Highland | Ulster | 12528 | G | 5084 | Highland | N | CH-09690 | 4 | [13 empty] | NM | N | SW 4024 | 2001-07-25 | 2001-07-29 | 2 | 2001-07-29 | [14 empty] | 2003-03-17 | 2003-03-28 |  | Y
Central Hudson |  | SunWize Technologies Inc | CH-09697 | Kingston | Kingston | Ulster | 12401 | G | 2094 | Hurley Ave | N |  | 2.5 | [13 empty] | NM | N | SMR-2500U | 2002-03-11 | 2002-03-14 | 3 | 2002-03-14 | [14 empty] | 2002-07-03 | 2002-07-03 |  | Y
Central Hudson |  | Sunnyside Solar | CH-09638 | Kingston | Saugerties | Ulster | 12477 | G | 3003 | Saugerties | N |  | 1.8 | [13 empty] | NM | N | SW 2024 | 2002-05-14 | 2002-05-17 | 3 | 2002-05-17 | [14 empty] | 2003-07-15 | 2003-07-23 |  | Y
Central Hudson |  | Sunnyside Solar | CH-09637 | Fishkill | Garrison | Putnam | 10524 | G | 8066 | Merritt Park | N |  | 1 | [13 empty] | NM | N | GC-1000 | 2002-06-05 | 2002-06-10 | 3 | 2002-06-10 | [14 empty] | 2002-06-05 | 2002-06-10 |  | Y
Central Hudson |  | Hudson Solar | CH-02134 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7053 | Rhinebeck | N | CH-02134 | 2.5 | [13 empty] | NM | N | SWR-2500U | 2002-07-16 | 2002-07-18 | 2 | 2002-07-18 | [14 empty] | 2002-12-20 | 2002-12-26 |  | Y
Central Hudson |  | Solar Works | CH-09050 | Catskill | Westerlo | Albany | 12193 | G | 2061 | Freehold | N |  | 2.5 | [13 empty] | NM | N | SWR-2500U | 2002-09-11 | 2002-09-17 | 4 | 2002-09-17 | [14 empty] | 2002-10-11 | 2002-10-15 |  | W
Central Hudson |  | Solar Works | CH-09051 | Catskill | Athens | Greene | 12015 | G | 2002 | North Catskill | N |  | 2.5 | [13 empty] | NM | N | SMA2500 | 2002-09-12 | 2002-09-17 | 3 | 2002-09-17 | [14 empty] | 2006-07-10 | 2006-07-10 |  | Y
Central Hudson |  | Solar Works | CH-09042 | Kingston | Stone Ridge | Ulster | 12484 | G | 3023 | High Falls | N | CH-09042 | 3 | [13 empty] | NM | N | GC-1000 | 2002-09-13 | 2002-09-17 | 2 | 2002-09-17 | [14 empty] | 2002-10-11 | 2002-10-15 |  | Y
Central Hudson |  | Solar Works | CH-09046 | Fishkill | Beacon | Dutchess | 12508 | G | 8087 | Tioronda | N |  | 1 | [13 empty] | NM | N | SWR-2500U | 2002-10-07 | 2002-10-11 | 4 | 2002-10-11 | [14 empty] | 2002-12-19 | 2002-12-19 |  | Y
Central Hudson |  | Sunstruck Design | CH-09685 | Kingston | Saugerties | Ulster | 12432 | G | 3001 | Saugerties | N |  | 2.5 | [13 empty] | NM | N | SMA 2500U | 2002-11-06 | 2002-11-12 | 4 | 2002-11-12 | [14 empty] | 2003-04-24 | 2003-04-25 |  | Y
Central Hudson |  | Hudson Solar | CH-02521 | Poughkeepsie | Rhinebeck |  | 12572 | G | 7052 | Rhinebeck | TBD |  | 2.5 | [13 empty] | NM | N | SWR-2500 | 2003-03-02 | 2003-03-02 | 0 | 2003-03-02 | [15 empty] | 2003-03-22 |  | W |  | contractor performed SIR test and sent documentation
Central Hudson |  | Global Resource Options | CH-01148 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6094 | Manchester | N |  | 12.6 | [13 empty] | NM | N | SB-1800U | 2003-04-23 | 2003-05-04 | 7 | 2003-05-04 | [14 empty] | 2003-06-24 | 2003-06-26 |  | Y
Central Hudson |  | Global Resource Options | CH-01141 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7013 | Hibernia | N |  | 2.5 | [13 empty] | NM | N | SB 1800U | 2003-05-02 | 2003-05-05 | 1 | 2003-05-05 | [14 empty] | 2003-07-28 | 2003-09-16 |  | Y
Central Hudson |  | Solar Works | CH-09039 | Kingston | Saugerties | Ulster | 12477 | G | 3004 | Saugerties | N |  | 2.5 | [13 empty] | NM | N | SWR-2500U | 2003-05-23 | 2003-05-23 | 0 | 2003-05-23 | [14 empty] | 2003-06-16 | 2003-06-16 |  | Y
Central Hudson |  | Sun Mountain | CH-09099 | Kingston | Rosendale |  | 12472 | G | 3022 | High Falls | N |  | 1 | [13 empty] | NM | N | GC-1000 | 2003-05-30 | 2003-06-09 | 6 | 2003-06-09 | [14 empty] | 2003-06-26 | 2003-07-08 |  | W
Central Hudson |  | Hudson Solar | CH-02006 | Catskill | Catskill | Greene | 12414 | G | 2001 | North Catskill | N |  | 2.5 | [13 empty] | NM | N | SWR-2500U | 2003-06-09 | 2003-06-12 | 3 | 2003-06-12 | [14 empty] | 2003-06-20 | 2003-06-20 |  | Y
Central Hudson |  | Sunstruck Design | CH-09688 | Kingston | Olive Brdg | Ulster | 12461 | G | 3023 | High Falls | N |  | 2.5 | [13 empty] | NM | N | STXR-2500 | 2003-06-11 | 2003-06-11 | 0 | 2003-06-11 | [14 empty] | 2003-06-30 | 2003-06-30 |  | Y
Central Hudson |  | Hudson Solar | CH-02019 | Kingston | Kingston | Ulster | 12401 | G | 3023 | High Falls | N |  | 25 | [13 empty] | NA | N | SMR-2500U | 2003-06-17 | 2003-08-31 | 52 | 2003-08-31 | [14 empty] | 2003-09-26 | 2003-09-26 |  | W
Central Hudson |  | Hudson Solar | CH-01783 | Poughkeepsie | Lagrange | Dutchess | 12540 | G | 6053 | Todd Hill | N |  | 2.5 | [13 empty] | NM | N | SWR-2500U | 2003-07-28 | 2003-07-28 | 0 | 2003-07-28 | [14 empty] | 2003-09-05 | 2003-09-05 |  | Y
Central Hudson |  | Sun Masters Corp. | CH-09080 | Catskill | Elka Pk | Greene | 12427 | G | 2385 | Lawrenceville | N |  | 13 | [13 empty] | NM | N | SWR-2500U | 2003-08-15 | 2003-08-22 | 5 | 2003-08-22 | [14 empty] | 2003-10-20 | 2003-10-21 |  | Y
Central Hudson |  | Sunstruck Design | CH-09689 | Kingston | Kerhonkson | Ulster | 12446 | G | 3082 | Kerhonkson | N |  | 2.5 | [13 empty] | NM | N | SWR-2500U | 2003-09-26 | 2003-10-23 | 18 | 2003-10-23 | [14 empty] | 2004-04-23 | 2004-04-23 |  | Y
Central Hudson |  | Hudson Solar | CH-01698 | Kingston | Kingston | Ulster | 12401 | G | 1011 | Boulevard | N | CH-01698 | 3 | [13 empty] | NM | N | JH-3500U | 2003-10-02 | 2003-10-06 | 2 | 2003-10-06 | [14 empty] | 2003-11-24 | 2003-12-19 |  | Y
Central Hudson |  | Sun Mountain | CH-09125 | Kingston | Kerhonkson | Ulster | 12446 | G | 3082 | Kerhonkson | N |  | 2.5 | [13 empty] | NM | N | (1) SWR-2500U | 2003-10-03 | 2003-10-07 | 2 | 2003-10-07 | [14 empty] | 2004-05-03 | 2004-05-03 |  | Y
Central Hudson |  | Sunstruck Design | CH-09691 | Kingston | Naranoch |  | 12458 | G | 3072 | Honk Falls | TBD |  | 2.5 | [13 empty] | NM | N | STXR-2500 | 2003-10-30 | 2003-10-30 | 0 | 2003-10-30 | [17 empty] | W
Central Hudson |  | Hudson Solar | CH-01591 | Kingston | Cementon | Greene | 12414 | G | 3004 | Saugerties | N |  | 3.5 | [13 empty] | NM | N | JH-3500U | 2003-11-05 | 2003-11-06 | 1 | 2003-11-06 | [14 empty] | 2003-12-31 | 2003-12-31 |  | Y
Central Hudson |  | ETM Solar Works | CH-01124 | Fishkill | Cold Spring | Putnam | 10516 | G | 8066 | Merritt Park | N |  | 2.5 | [13 empty] | NM | N | SWR-2500U | 2003-11-06 | 2003-11-06 | 0 | 2003-11-06 | [14 empty] | 2004-02-05 | 2004-02-09 |  | Y
Central Hudson |  | Hudson Solar | CH-01880 | Poughkeepsie | Ancramdale | Columbia | 12503 | G | 7092 | Pulvers Corners | N |  | 3.5 | [13 empty] | NM | N | JH-3500U | 2003-11-18 | 2003-11-18 | 0 | 2003-11-18 | [14 empty] | 2003-12-31 | 2003-12-31 |  | Y
Central Hudson |  | Prime Energy Solutions | CH-02934 | Kingston | Ellenvl | Ulster | 12428 | G | 3076 | Greenfield Rd | N |  | 2.5 | [13 empty] | NM | N | (1) SWR-2500U | 2003-11-18 | 2003-11-24 | 4 | 2003-11-24 | [14 empty] | 2004-05-27 | 2004-06-04 |  | Y
Central Hudson |  | Prime Energy Solutions | CH-02937 | Kingston | Kerhonkson |  | 12446 | G | 3082 | Kerhonkson | TBD |  | 2.5 | [13 empty] | NM | N | SWR-2500U | 2004-02-11 | 2004-02-11 | 0 | 2004-02-11 | [15 empty] | 2004-05-27 |  | W
Central Hudson |  | Global Resource Options | CH-01147 | Fishkill | Holmes | Dutchess | 12531 | G | 8071 | Shenandoah | N | CH-01147 | 6.9 | [13 empty] | NM | N | SWR-2500U | 2004-02-18 | 2004-02-19 | 1 | 2004-02-19 | [14 empty] | 2004-04-29 | 2004-04-29 |  | Y
Central Hudson |  | HVCE | CH-20870 | Catskill | West Kill | Greene | 12492 | E | 2389 | Vinegar Hill | N |  | 2.5 | [13 empty] | NM | N | SMA America SMA America 2500 | 2004-02-20 | 2004-02-25 | 3 | 2004-02-25 | [14 empty] | 2004-05-07 | 2004-05-10 |  | Y
Central Hudson |  | Hudson Solar | CH-01668 | Kingston | Ulster Pk | Ulster | 12487 | G | 1014 | Boulevard | N |  | 3.5 | [13 empty] | NM | N | JH-3500U | 2004-02-23 | 2004-02-24 | 1 | 2004-02-24 | [14 empty] | 2004-04-29 | 2004-04-29 |  | Y
Central Hudson |  | Hudson Solar | CH-01889 | Poughkeepsie | Pine Plns | Dutchess | 12567 | G | 7091 | Pulvers Corners | N |  | 3.5 | [13 empty] | NM | N | JH-3500U | 2004-02-23 | 2004-02-24 | 1 | 2004-02-24 | [14 empty] | 2004-04-27 | 2004-04-27 |  | Y
Central Hudson |  | Sun Mountain | CH-09089 | Kingston | Olive Brdg |  | 12461 | G | 3081 | Kerhonkson | TBD |  | 1.8 | [13 empty] | NM | N | SB-1800U | 2004-03-05 | 2004-03-09 | 2 | 2004-03-09 | [17 empty] | W
Central Hudson |  | Hudson Solar | CH-01837 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7053 | Rhinebeck | N |  | 3.5 | [13 empty] | NM | N | JH-3500U | 2004-03-08 | 2004-03-09 | 1 | 2004-03-09 | [14 empty] | 2004-04-02 | 2004-04-02 |  | Y
Central Hudson |  | Hudson Solar | CH-01891 | Poughkeepsie | Pine Plns | Dutchess | 12567 | G | 7091 | Pulvers Corners | N |  | 2.5 | [13 empty] | NM | N | SWR-2500U | 2004-03-08 | 2004-03-09 | 1 | 2004-03-09 | [14 empty] | 2004-04-23 | 2004-04-23 |  | Y
Central Hudson |  | Great Brook Enterprises | CH-01152 | Newburgh | W Park | Ulster | 12493 | G | 5084 | Highland | N |  | 5 | [13 empty] | NM | N | SWR-2500U | 2004-03-19 | 2004-03-22 | 1 | 2004-03-22 | [14 empty] | 2004-10-29 | 2004-10-29 |  | Y
Central Hudson |  | Hudson Solar | CH-01291 | Kingston | Kingston | Ulster | 12401 | G | 2013 | Lincoln Park | N |  | 13.2 | [13 empty] | NM | N | SWR-2500U | 2004-04-08 | 2004-04-08 | 0 | 2004-04-08 | [14 empty] | 2004-09-08 | 2004-09-08 |  | Y
Central Hudson |  | Hudson Solar | CH-01343 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8096 | Fishkill Plains | N |  | 14 | [13 empty] | NM | N | JH-3500U | 2004-04-08 | 2004-04-08 | 0 | 2004-04-08 | [14 empty] | 2004-05-20 | 2004-05-20 |  | Y
Central Hudson |  | Hudson Solar | CH-01485 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6003 | Reynolds Hill | N |  | 12.6 | [13 empty] | NM | N | SMA-6000U, SMA-2500U | 2004-04-08 | 2004-04-08 | 0 | 2004-04-08 | [14 empty] | 2006-05-31 | 2006-06-09 |  | Y
Central Hudson |  | Hudson Solar | CH-01565 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6003 | Reynolds Hill | N |  | 12.6 | [13 empty] | NM | N | SMA-6000U, SMA-2500U | 2004-04-08 | 2004-04-08 | 0 | 2004-04-08 | [14 empty] | 2006-05-31 | 2006-06-09 |  | Y
Central Hudson |  | Hudson Solar | CH-01664 | Kingston | Kingston |  | 12401 | G | 2013 | Lincoln Park | TBD |  | 13.2 | [13 empty] | NM | N | SWR-2500U | 2004-04-08 | 2004-04-08 | 0 | 2004-04-08 | [15 empty] | 2004-09-08 |  | W |  | SC14 customer swtiched to commercial NM after 2/09; contractor performed SIR test and sent documentation
Central Hudson |  | Hudson Solar | CH-01740 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7053 | Rhinebeck | N |  | 2.5 | [13 empty] | NM | N | SWR-2500U | 2004-03-30 | 2004-03-30 | 0 | 2004-03-30 | [14 empty] | 2004-05-07 | 2004-05-07 |  | Y
Central Hudson |  | Solar Works | CH-09045 | Newburgh | Highland | Ulster | 12528 | G | 5082 | Highland | N |  | 2.5 | [13 empty] | NM | N | SWR-2500U | 2004-04-08 | 2004-04-08 | 0 | 2004-04-08 | [14 empty] | 2004-09-13 | 2004-10-04 |  | Y
Central Hudson |  | Sunstruck Design | CH-09683 | Poughkeepsie | Millerton | Dutchess | 12546 | G | 7081 | Millerton | N |  | 2.5 | [13 empty] | NM | N | SWR-2500 | 2004-04-27 | 2004-04-27 | 0 | 2004-04-27 | [14 empty] | 2004-07-15 | 2004-07-15 |  | Y
Central Hudson |  | Hudson Solar | CH-01885 | Poughkeepsie | Millerton | Dutchess | 12546 | G | 7092 | Pulvers Corners | N | CH-01885 | 7.5 | [13 empty] | NM | N | SWR-2500U | 2004-05-28 | 2004-06-07 | 5 | 2004-06-07 | [14 empty] | 2004-07-28 | 2004-07-28 |  | Y
Central Hudson |  | Hudson Solar | CH-01908 | Newburgh | Highland | Ulster | 12528 | G | 5084 | Highland | N |  | 2.5 | [13 empty] | NM | N | SWR-2500U | 2004-06-01 | 2004-06-07 | 4 | 2004-06-07 | [14 empty] | 2004-08-18 | 2004-08-18 |  | Y
Central Hudson |  | Global Resource Options | CH-01146 | Newburgh | Wallkill | Ulster | 12589 | G | 5043 | East Walden | N | CH-01146 | 2.5 | [13 empty] | NM | N | SWR-2500U | 2004-06-02 | 2004-06-07 | 3 | 2004-06-07 | [14 empty] | 2004-07-02 | 2004-07-02 |  | Y
Central Hudson |  | Prime Energy Solutions | CH-02932 | Kingston | Saugerties | Ulster | 12477 | G | 3003 | Saugerties | N |  | 6.8 | [13 empty] | NM | N | SWR-2500U | 2004-06-02 | 2004-06-07 | 3 | 2004-06-07 | [14 empty] | 2004-11-24 | 2004-11-24 |  | Y
Central Hudson |  | Hudson Solar | CH-01770 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7055 | Rhinebeck | Y | CH-01770 | 5 | [13 empty] | NM | N | M5V4-109 | 2004-06-07 | 2004-06-07 | 0 | 2004-06-07 | [14 empty] | 2004-07-19 | 2004-07-19 |  | Y
Central Hudson |  | Hudson Solar | CH-01845 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7053 | Rhinebeck | N |  | 7 | [13 empty] | NM | N | JH-3500U | 2004-07-01 | 2004-07-01 | 0 | 2004-07-01 | [14 empty] | 2004-09-14 | 2004-09-14 |  | Y
Central Hudson |  | Solar Works | CH-09040 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6045 | Spackenkill | N |  | 2.5 | [13 empty] | NM | N | SWR-2500U | 2004-07-01 | 2004-07-01 | 0 | 2004-07-01 | [14 empty] | 2004-09-14 | 2004-12-20 |  | Y
Central Hudson |  | NPCP LLC | CH-02795 | Newburgh | New Paltz | Ulster | 12561 | G | 5031 | Galeville | N |  | 7.5 | [13 empty] | NM | N | SWR-2500U (double check w/ kW) | 2004-06-30 | 2004-06-30 | 0 | 2004-06-30 | [14 empty] | 2004-07-07 | 2004-07-08 |  | Y
Central Hudson |  | Hudson Solar | CH-01899 | Poughkeepsie | Stanfordvl | Dutchess | 12581 | G | 7061 | Milan | N |  | 5 | [13 empty] | NM | N | SWR-2500U | 2004-07-19 | 2004-07-20 | 1 | 2004-07-20 | [14 empty] | 2004-09-03 | 2004-09-07 |  | Y
Central Hudson |  | Solar Works | CH-09044 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6003 | Reynolds Hill | N |  | 2.5 | [13 empty] | NM | N | SWR-2500U | 2004-08-06 | 2004-08-06 | 0 | 2004-08-06 | [14 empty] | 2005-05-31 | 2005-05-31 |  | Y
Central Hudson |  | Hudson Solar | CH-01673 | Kingston | New Paltz | Ulster | 12561 | G | 3022 | High Falls | N |  | 2.7 | [13 empty] | NM | N | JH-3500U | 2004-08-12 | 2004-08-12 | 0 | 2004-08-12 | [14 empty] | 2004-12-14 | 2004-12-20 |  | Y
Central Hudson |  | Hudson Solar | CH-01949 | Newburgh | Gardiner | Ulster | 12561 | G | 5011 | Modena | N | CH-01949 | 3.6 | [13 empty] | NM | N | SWR-2500U | 2004-08-11 | 2004-08-13 | 2 | 2004-08-13 | [14 empty] | 2004-09-24 | 2004-09-24 |  | Y
Central Hudson |  | Prime Energy Solutions | CH-02936 | Newburgh | Cornwall | Orange | 12518 | G | 4093 | Bethlehem Rd | N |  | 2.5 | [13 empty] | NM | N | SWR-2500U | 2004-08-12 | 2004-08-17 | 3 | 2004-08-17 | [14 empty] | 2004-10-29 | 2004-11-11 |  | Y
Central Hudson |  | Global Resource Options | CH-01142 | Catskill | Greenvl |  | 12083 | G | 1092 | Westerlo | N |  | 15 | [13 empty] | NM | N | SMA America SWR-2500 | 2004-09-16 | 2004-09-16 | 0 | 2004-09-16 | [14 empty] | 2004-12-20 | 2004-12-20 |  | W
Central Hudson |  | Hudson Solar | CH-01775 | Poughkeepsie | Millbrook | Dutchess | 12545 | G | 7025 | Tinkertown | N |  | 12.5 | [13 empty] | NM | N | SWR-2500U | 2004-09-09 | 2004-09-10 | 1 | 2004-09-10 | [14 empty] | 2004-12-10 | 2004-12-10 |  | Y
Central Hudson |  | Hudson Solar | CH-01226 | Kingston | Kerhonkson | Ulster | 12446 | G | 3071 | Honk Falls | N | CH-01226 | 3.5 | [13 empty] | NM | N | Sharp JH-3500U, SMJ-04 | 2004-09-10 | 2004-09-15 | 3 | 2004-09-15 | [14 empty] | 2004-12-02 | 2004-12-06 |  | Y
Central Hudson |  | SunWize Technologies Inc | CH-09696 | Kingston | Kingston | Ulster | 12401 | G | 1021 | East Kingston | N |  | 12.4 | [13 empty] | NM | N | SWR-2500U | 2004-12-02 | 2004-12-02 | 0 | 2004-12-02 | [14 empty] | 2005-12-08 | 2005-12-13 |  | Y
Central Hudson |  | Hudson Solar | CH-01996 | Newburgh | New Windsor | Orange | 12553 | G | 4091 | Bethlehem Rd | N |  | 14.4 | [13 empty] | NM | N | SWR-1800U | 2004-12-06 | 2004-12-06 | 0 | 2004-12-06 | [14 empty] | 2005-01-13 | 2005-01-14 |  | Y
Central Hudson |  | Self | CH-08876 | Kingston | Saugerties | Ulster | 12477 | G | 2015 | Lincoln Park | N |  |  |  | 20 | [11 empty] | NM | N | SEL-547 | 2005-10-11 | 2005-10-14 | 3 | 2005-10-14 | [14 empty] | 2005-12-27 | 2006-01-06 |  | Y
Central Hudson |  | Hudson Solar | CH-01334 | Poughkeepsie | Millerton | Dutchess | 12546 | G | 7081 | Millerton | N |  | 3.6 | [13 empty] | NM | N | SWR-1800 | 2004-12-07 | 2004-12-07 | 0 | 2004-12-07 | [14 empty] | 2005-05-14 | 2005-05-16 |  | Y
Central Hudson |  | Hudson Solar | CH-01327 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7061 | Milan | N | CH-01327 | 3.6 | [13 empty] | NM | N | SWR-1800U | 2004-12-21 | 2004-12-21 | 0 | 2004-12-21 | [14 empty] | 2005-03-23 | 2005-03-23 |  | Y
Central Hudson |  | Renewable Power Systems | CH-02968 | Kingston | High Fls | Ulster | 12440 | G | 3022 | High Falls | N |  | 2.88 | [13 empty] | NM | N | Fronius IG-3000 | 2004-12-27 | 2004-12-27 | 0 | 2004-12-27 | [14 empty] | 2005-01-17 | 2005-01-17 |  | Y
Central Hudson |  | Hudson Solar | CH-01864 | Poughkeepsie | Tivoli | Dutchess | 12583 | G | 7062 | Milan | N | CH-01864 | 12 | [13 empty] | NM | N | SWR-2500U | 2005-01-11 | 2005-01-11 | 0 | 2005-01-11 | [14 empty] | 2005-04-20 | 2005-04-22 |  | Y
Central Hudson |  | Randolph Horner | CH-02954 | Kingston | Woodstock | Ulster | 12498 | G | 3012 | Woodstock | N |  | 15 | [13 empty] | NA | N | Fronius 4500LV | 2005-01-12 | 2005-01-13 | 1 | 2005-01-13 | [14 empty] | 2005-08-01 | 2005-08-03 |  | Y
Central Hudson |  | Hudson Solar | CH-02110 | Poughkeepsie | Wappingrs Fls | Dutchess | 12590 | G | 6052 | Todd Hill | N |  | 6 | [13 empty] | NM | N | SMA-6000 | 2005-02-09 | 2005-02-10 | 1 | 2005-02-10 | [14 empty] | 2005-05-05 | 2005-05-10 |  | Y
Central Hudson |  | Hudson Solar | CH-01317 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7055 | Rhinebeck | N |  | 5.4 | [13 empty] | NM | N | SMA-1800U | 2005-02-14 | 2005-02-17 | 3 | 2005-02-17 | [14 empty] | 2005-03-30 | 2005-03-31 |  | Y
Central Hudson |  | Hudson Solar | CH-01580 | Newburgh | Gardiner | Ulster | 12525 | G | 5031 | Galeville | N | CH-01580 | 3.5 | [13 empty] | NM | N | Sharp JH_3500U, SMJ-04 | 2005-02-14 | 2005-02-16 | 2 | 2005-02-16 | [14 empty] | 2005-06-02 | 2005-06-03 |  | Y
Central Hudson |  | Akeena Solar | CH-00642 | Fishkill | Beacon | Dutchess | 12508 | G | 8017 | Forgebrook | N |  | 5.92 | [13 empty] | NM | N | SWR-2500 | 2005-03-01 | 2005-03-02 | 1 | 2005-03-02 | [14 empty] | 2005-03-09 | 2005-03-09 |  | W
Central Hudson |  | Global Resource Options | CH-01144 | Catskill | Rensselaervl |  | 12147 | G | 1092 | Westerlo | N |  | 8.5 | [13 empty] | NM | N | SMA-1800U, SMA-2500U | 2005-03-04 | 2005-03-12 | 5 | 2005-03-12 | [14 empty] | 2005-07-01 | 2005-08-03 |  | W
Central Hudson |  | Hudson Solar | CH-01953 | Newburgh | New Paltz | Ulster | 12561 | G | 5023 | Ohioville | N |  | 3.6 | [13 empty] | NM | N | SMA-1800U | 2005-03-04 | 2005-03-09 | 3 | 2005-03-09 | [14 empty] | 2005-03-28 | 2005-03-28 |  | Y
Central Hudson |  | Sun Mountain | CH-09100 | Kingston | Bearsvl | Ulster | 12409 | G | 3012 | Woodstock | N | CH-09100 | 3 | [13 empty] | NM | N | Sharp GT-3.0 | 2005-05-19 | 2005-05-25 | 4 | 2005-05-25 | [14 empty] | 2005-06-08 | 2005-06-08 |  | Y
Central Hudson |  | Sun Mountain | CH-09105 | Kingston | Bearsvl | Ulster | 12409 | G | 3012 | Woodstock | N |  | 1.8 | [13 empty] | NM | N | SMA-1800U | 2005-05-19 | 2005-05-24 | 3 | 2005-05-24 | [14 empty] | 2005-08-01 | 2005-08-03 |  | Y
Central Hudson |  | Hudson Solar | CH-01481 | Poughkeepsie | Staatsburg | Dutchess | 12580 | G | 7042 | Staatsburg | N |  | 12 | [13 empty] | NM | N | SMA-6000U | 2005-03-21 | 2005-03-21 | 0 | 2005-03-21 | [14 empty] | 2005-05-04 | 2005-05-06 |  | Y
Central Hudson |  | Hudson Solar | CH-01848 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7061 | Milan | N |  | 6 | [13 empty] | NM | N | SMA-6000U | 2005-03-28 | 2005-03-29 | 1 | 2005-03-29 | [14 empty] | 2005-06-03 | 2005-06-06 |  | Y
Central Hudson |  | Northern Power Systems | CH-02775 | Newburgh | Cornwall | Orange | 12518 | G | 4041 | Union Ave | N |  | 24 | [13 empty] | NM | N | SMA-6000U, SMA-1800U | 2005-03-28 | 2005-03-31 | 3 | 2005-03-31 | [14 empty] | 2006-01-10 | 2006-01-13 |  | Y
Central Hudson |  | Hudson Solar | CH-01841 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7053 | Rhinebeck | N |  | 3.5 | [13 empty] | NM | N | Sharp JH-3500U, SMJ-04 | 2005-04-22 | 2005-04-27 | 3 | 2005-04-27 | [14 empty] | 2005-07-13 | 2005-07-14 |  | Y
Central Hudson |  | Hudson Solar | CH-02513 | Kingston | Kingston |  | 12401 | G | 2012 | Lincoln Park | TBD |  | 6.1 | [13 empty] | NM | N | SMA-1800U, SMA-2500U | 2005-04-22 | 2005-04-27 | 3 | 2005-04-27 | [15 empty] | 2007-10-24 |  | W |  | decided to install a smaller system instead
Central Hudson |  | Hudson Solar | CH-02232 | Kingston | Kingston |  | 12401 | G | 1012 | Boulevard | TBD |  | 2.5 | [13 empty] | NM | N | SMA-2500U | 2005-05-10 | 2005-05-13 | 3 | 2005-05-13 | [17 empty] | W
Central Hudson |  | Hudson Solar | CH-01388 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 6075 | East Park | N |  | 7.8 | [13 empty] | NM | N | SMA-6000U, SMA-1800U | 2005-05-11 | 2005-05-13 | 2 | 2005-05-13 | [14 empty] | 2005-06-20 | 2005-06-21 |  | Y
Central Hudson |  | Hudson Solar | CH-01592 | Catskill | Catskill | Greene | 12414 | G | 2001 | North Catskill | N |  | 7.8 | [13 empty] | NM | N | SMA-6000U, SMA-1800U | 2005-05-16 | 2005-05-17 | 1 | 2005-05-17 | [14 empty] | 2005-07-07 | 2005-07-11 |  | Y
Central Hudson |  | ETM Solar Works | CH-01121 | Kingston | Rosendale | Ulster | 12472 | G | 3021 | High Falls | N |  | 12 | [13 empty] | NM | N | SMA-6000U | 2005-06-09 | 2005-06-13 | 2 | 2005-06-13 | [14 empty] | 2005-07-01 | 2005-07-11 |  | Y
Central Hudson |  | Global Resource Options | CH-01145 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6068 | Inwood Ave | N |  | 3 | [13 empty] | NM | N | Magnetek PVI-3000-I-OUTD-US | 2005-05-23 | 2005-05-25 | 2 | 2005-05-25 | [14 empty] | 2005-06-24 | 2005-06-24 |  | Y
Central Hudson |  | Hudson Solar | CH-01554 | Poughkeepsie | Ancramdale | Columbia | 12503 | G | 7092 | Pulvers Corners | N |  | 13.8 | [13 empty] | NM | N | SMA-6000U, SMA-1800U | 2005-06-08 | 2005-06-13 | 3 | 2005-06-13 | [14 empty] | 2005-09-21 | 2005-09-22 |  | Y
Central Hudson |  | Wiley Electronics LLC | CH-09944 | Kingston | Shokan | Ulster | 12481 | G | 3011 | Woodstock | N |  | 2.8 | [13 empty] | NM | N | PVP 2800 | 2005-06-22 | 2005-06-23 | 1 | 2005-06-23 | [14 empty] | 2005-11-22 | 2005-11-23 |  | Y
Central Hudson |  | Hudson Solar | CH-01535 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7062 | Milan | N |  | 9.8 | [13 empty] | NM | N | SMA-6000U, SMA-3800U | 2005-06-15 | 2005-06-17 | 2 | 2005-06-17 | [14 empty] | 2005-10-12 | 2005-10-12 |  | Y
Central Hudson |  | Sun Mountain | CH-09111 | Kingston | Stone Ridge | Ulster | 12484 | G | 3023 | High Falls | N |  | 7.2 | [13 empty] | NM | N | Outback-GVFX3648 | 2005-07-14 | 2005-07-20 | 4 | 2005-07-20 | [14 empty] | 2005-10-14 | 2005-10-19 |  | Y
Central Hudson |  | Hudson Solar | CH-02092 | Poughkeepsie | Millbrook | Dutchess | 12545 | G | 7025 | Tinkertown | N |  | 6 | [13 empty] | NM | N | SMA-6000U | 2005-07-21 | 2005-07-25 | 2 | 2005-07-25 | [14 empty] | 2005-10-07 | 2005-10-11 |  | Y
Central Hudson |  | Hudson Solar | CH-01990 | Newburgh | New Paltz |  | 12561 | G | 5021 | Ohioville | TBD |  | 6 | [13 empty] | NM | N | SMA-6000U | 2005-07-26 | 2005-08-01 | 4 | 2005-08-01 | [15 empty] | 2005-09-22 |  | W |  | SC14 customer switched to commercial NM after 2/09; contractor performed SIR test and sent documentation. 2/8/2010 - Customer abandons this site and combines it with existing system at the Village Hall, CH Acct # 8643-0580-00.
Central Hudson |  | Hudson Solar | CH-01991 | Newburgh | New Paltz | Ulster | 12561 | G | 5021 | Ohioville | N |  | 5 | [13 empty] | NM | N | Beacon M5 | 2005-07-26 | 2005-08-01 | 4 | 2005-08-01 | [14 empty] | 2005-09-28 | 2005-09-28 |  | W
Central Hudson |  | Hudson Solar | CH-01992 | Newburgh | New Paltz | Ulster | 12561 | G | 5021 | Ohioville | N |  | 8.5 | [13 empty] | NM | N | SMA-2500U | 2005-07-26 | 2005-08-01 | 4 | 2005-08-01 | [14 empty] | 2005-09-22 | 2005-09-22 |  | Y
Central Hudson |  | Self | CH-08897 | Kingston | Kingston |  | 12401 | G | 3023 | High Falls | TBD |  | 3 | [13 empty] | NM | N | Aurora 3000 | 2005-07-26 | 2005-08-02 | 5 | 2005-08-02 | [17 empty] | W |  | customer reapplied with a new design and contractor; also upgraded to 6kW
Central Hudson |  | Hudson Solar | CH-01722 | Kingston | Kingston | Ulster | 12401 | G | 2094 | Hurley Ave | N |  | 14.5 | [13 empty] | NM | N | SMA-6000U, SMA-2500U | 2005-08-05 | 2005-08-08 | 1 | 2005-08-08 | [14 empty] | 2005-11-16 | 2005-11-18 |  | Y
Central Hudson |  | Self | CH-08865 | Poughkeepsie | Wassaic |  | 12592 | G | 6005 | Reynolds Hill | TBD |  | 11 | [13 empty] | NM | N | Xantrex SW-5548 | 2005-09-08 | 2005-09-14 | 4 | 2005-09-14 | [14 empty] | 2005-10-05 | 2005-10-11 |  | W
Central Hudson |  | Hudson Solar | CH-01838 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7053 | Rhinebeck | N |  | 7 | [13 empty] | NM | N | Sharp JH-3500U | 2005-08-16 | 2005-08-17 | 1 | 2005-08-17 | [14 empty] | 2005-10-24 | 2005-10-25 |  | Y
Central Hudson |  | Hudson Solar | CH-01476 | Kingston | Bearsvl | Ulster | 12409 | G | 3012 | Woodstock | N |  | 7.5 | [13 empty] | NM | N | SMA-6000U, SMA-2500U | 2005-08-17 | 2005-08-17 | 0 | 2005-08-17 | [14 empty] | 2005-12-01 | 2005-12-05 |  | Y
Central Hudson |  | Hudson Solar | CH-01525 | Kingston | Glenford | Ulster | 12433 | G | 3013 | Woodstock | N |  | 8.5 | [13 empty] | NM | N | SMA-6000U, SMA-1800U | 2005-08-30 | 2005-09-01 | 2 | 2005-09-01 | [14 empty] | 2006-01-20 | 2006-01-23 |  | Y
Central Hudson |  | Hudson Solar | CH-02173 | Fishkill | Fishkill | Dutchess | 12524 | G | 8094 | Fishkill Plains | N |  | 2.5 | [13 empty] | NM | N | SB2500U | 2005-08-30 | 2005-09-01 | 2 | 2005-09-01 | [14 empty] | 2005-11-07 | 2005-11-08 |  | Y
Central Hudson |  | Hudson Solar | CH-01905 | Poughkeepsie | Stanfordvl | Dutchess | 12581 | G | 7071 | Stanfordville | N |  | 3.5 | [13 empty] | NM | N | JH-3500U | 2005-10-07 | 2005-10-07 | 0 | 2005-10-07 | [14 empty] | 2005-12-08 | 2005-12-13 |  | Y
Central Hudson |  | Hudson Solar | CH-02089 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 7042 | Staatsburg | N |  | 12.6 | [13 empty] | NM | N | SMA-6000U | 2005-10-07 | 2005-10-07 | 0 | 2005-10-07 | [14 empty] | 2005-12-21 | 2005-12-22 |  | Y
Central Hudson |  | Hudson Solar | CH-02005 | Catskill | Catskill | Greene | 12414 | G | 2001 | North Catskill | N |  | 12 | [13 empty] | NM | N | SMA-6000U | 2005-10-21 | 2005-10-26 | 3 | 2005-10-26 | [14 empty] | 2005-12-22 | 2005-12-27 |  | Y
Central Hudson |  | Hudson Solar | CH-02243 | Kingston | Napanoch |  | 12458 | G | 3072 | Honk Falls | TBD |  | 6 | [13 empty] | NM | N | SMA-6000U | 2005-10-21 | 2005-10-26 | 3 | 2005-10-26 | [17 empty] | W
Central Hudson |  | Hudson Solar | CH-01660 | Kingston | Accord | Ulster | 12404 | G | 3081 | Kerhonkson | N |  | 5 | [13 empty] | NM | N | SMA-2500U | 2005-10-24 | 2005-10-26 | 2 | 2005-10-26 | [14 empty] | 2006-02-02 | 2006-02-03 |  | Y
Central Hudson |  | Hudson Solar | CH-02216 | Newburgh | Cornwall | Orange | 12518 | G | 4041 | Union Ave | N |  | 6.3 | [13 empty] | NM | N | SMA-2500U, SMA-3800U | 2005-10-28 | 2005-10-31 | 1 | 2005-10-31 | [14 empty] | 2006-03-28 | 2006-03-29 |  | Y
Central Hudson |  | Hudson Solar | CH-01900 | Poughkeepsie | Stanfordvl | Dutchess | 12581 | G | 7061 | Milan | N |  | 12 | [13 empty] | NM | N | 2 SMA America SB6.0-1SP-US-41 (240V) [SI1] SMA-6000U | 2005-11-01 | 2005-11-03 | 2 | 2005-11-03 | [14 empty] | 2006-01-25 | 2006-01-25 |  | Y
Central Hudson |  | Hudson Solar | CH-02273 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6092 | Manchester | N |  | 15 | [13 empty] | NM | N | (5) xantrex GT3.0 inverters | 2005-11-14 | 2005-11-18 | 4 | 2005-11-18 | [14 empty] | 2006-05-31 | 2006-06-01 |  | Y
Central Hudson |  | Hudson Solar | CH-02266 | Poughkeepsie | Lagrangevl | Dutchess | 12540 | G | 6053 | Todd Hill | N |  | 10.1 | [13 empty] | NM | N | SPR-5200 (2x) | 2005-11-28 | 2005-11-29 | 1 | 2005-11-29 | [14 empty] | 2006-06-23 | 2006-06-23 |  | Y
Central Hudson |  | Hudson Solar | CH-02464 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7053 | Rhinebeck | N | CH-02134 | 12 | [13 empty] | NM | N | (4) Xantrex GT3.0 | 2005-11-28 | 2005-11-29 | 1 | 2005-11-29 | [14 empty] | 2006-10-03 | 2006-10-03 |  | Y
Central Hudson |  | Hudson Solar | CH-01703 | Kingston | Kingston | Ulster | 12401 | G | 2094 | Hurley Ave | N |  | 6.5 | [13 empty] | NM | N | SMA-3800U | 2005-11-30 | 2005-12-07 | 5 | 2005-12-07 | [14 empty] | 2006-04-11 | 2006-04-12 |  | Y
Central Hudson |  | Hudson Solar | CH-01772 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7042 | Staatsburg | N |  | 8.3 | [13 empty] | NM | N | Xantrex GT2.5, Xantrex GT3.3 | 2005-12-05 | 2005-12-07 | 2 | 2005-12-07 | [14 empty] | 2006-02-17 | 2006-02-21 |  | Y
Central Hudson |  | Hudson Solar | CH-01460 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7052 | Rhinebeck | N |  | 8.3 | [13 empty] | NM | N | Xantrex GT2.5, Xantrex GT3.3 | 2005-12-12 | 2005-12-19 | 5 | 2005-12-19 | [14 empty] | 2006-02-14 | 2006-02-15 |  | Y
Central Hudson |  | Hudson Solar | CH-01513 | Newburgh | New Paltz | Ulster | 12561 | G | 5011 | Modena | N |  | 5.6 | [13 empty] | NM | N | SB-3800U and SWR-1800U | 2005-12-14 | 2005-12-19 | 3 | 2005-12-19 | [14 empty] | 2006-04-19 | 2006-04-21 |  | Y
Central Hudson |  | Hudson Solar | CH-01805 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 6051 | Todd Hill | N |  | 6 | [13 empty] | NM | N | SMA-6000U | 2005-12-14 | 2005-12-19 | 3 | 2005-12-19 | [14 empty] | 2006-05-10 | 2006-05-10 |  | Y
Central Hudson |  | Hudson Solar | CH-02195 | Newburgh | New Paltz |  | 12561 | G | 5011 | Modena | TBD |  | 5.6 | [13 empty] | NM | N | SMA-3800U, SMA-1800U | 2005-12-14 | 2005-12-19 | 3 | 2005-12-19 | [15 empty] | 2006-04-21 |  | W |  | contractor performed SIR test and sent documentation
Central Hudson |  | Hudson Solar | CH-02511 | Kingston | Cottekill |  | 12419 | G | 3021 | High Falls | TBD |  | 8.1 | [13 empty] | NM | N | SPR 5200 & 2000 | 2005-12-21 | 2005-12-22 | 1 | 2005-12-22 | [17 empty] | W
Central Hudson |  | Hudson Solar | CH-01279 | Kingston | New Paltz | Ulster | 12561 | G | 3041 | Sturgeon Pool | N |  | 10.4 | [13 empty] | NM | N | Xantrex GT2.5, Xantrex GT3.3 | 2005-12-27 | 2005-12-29 | 2 | 2005-12-29 | [14 empty] | 2006-06-09 | 2006-06-14 |  | Y
Central Hudson |  | Hudson Solar | CH-01394 | Poughkeepsie | Clinton Corners | Dutchess | 12514 | G | 7061 | Milan | N |  | 3.5 | [13 empty] | NM | N | Sharp JH-3500U | 2006-01-04 | 2006-01-06 | 2 | 2006-01-06 | [14 empty] | 2006-02-22 | 2006-02-22 |  | Y
Central Hudson |  | Hudson Solar | CH-01386 | Kingston | Saugerties | Ulster | 12477 | G | 3003 | Saugerties | N | CH-01386 | 5 | [13 empty] | NM | N | Xantrex GT2.5 | 2006-01-09 | 2006-01-13 | 4 | 2006-01-13 | [14 empty] | 2006-05-26 | 2006-06-01 |  | Y
Central Hudson |  | Hudson Solar | CH-02213 | Newburgh | Wallkill | Ulster | 12589 | G | 5043 | East Walden | N | CH-02213 | 6.3 | [13 empty] | NM | N | SMA-3800U, SMA-2500U | 2006-01-09 | 2006-01-13 | 4 | 2006-01-13 | [14 empty] | 2006-05-26 | 2006-06-01 |  | Y
Central Hudson |  | Hudson Solar | CH-02202 | Newburgh | Highland | Ulster | 12528 | G | 5024 | Ohioville | N |  | 8.5 | [13 empty] | NM | N | SMA-6000U, SMA-2500U | 2006-01-16 | 2006-01-23 | 5 | 2006-01-23 | [14 empty] | 2006-05-05 | 2006-05-09 |  | Y
Central Hudson |  | Hudson Solar | CH-01806 | Poughkeepsie | Wappingrs Fls | Dutchess | 12590 | G | 6052 | Todd Hill | N |  | 3.6 | [13 empty] | NM | N | SMA-1800U | 2006-02-07 | 2006-02-10 | 3 | 2006-02-10 | [14 empty] | 2006-05-12 | 2006-05-17 |  | Y
Central Hudson |  | Akeena Solar | CH-00639 | Poughkeepsie | Dover Plains | Dutchess | 12522 | G | 7025 | Tinkertown | N |  | 15 | [13 empty] | NM | N | SPR-3200 | 2006-02-13 | 2006-02-15 | 2 | 2006-02-15 | [14 empty] | 2006-04-25 | 2006-04-25 |  | Y
Central Hudson |  | Akeena Solar | CH-00641 | Kingston | High Fls | Ulster | 12440 | G | 3024 | High Falls | N |  | 4 | [13 empty] | NM | N | Fronius IG-4000 | 2006-02-13 | 2006-02-15 | 2 | 2006-02-15 | [14 empty] | 2006-05-04 | 2006-05-10 |  | Y
Central Hudson |  | Hudson Solar | CH-01487 | Poughkeepsie | Wappingrs Fls | Dutchess | 12590 | G | 6052 | Todd Hill | N |  | 14.5 | [13 empty] | NM | N | SMA-6000U, SMA-2500U | 2006-03-16 | 2006-03-17 | 1 | 2006-03-17 | [14 empty] | 2006-05-04 | 2006-05-09 |  | Y
Central Hudson |  | Hudson Solar | CH-01469 | Kingston | Olive Brdg | Ulster | 12461 | G | 3024 | High Falls | N |  | 6 | [13 empty] | NM | N | (1) SMA-6000U | 2006-03-21 | 2006-03-22 | 1 | 2006-03-22 | [14 empty] | 2006-06-30 | 2006-07-10 |  | Y
Central Hudson |  | Hudson Solar | CH-01284 | Kingston | Accord | Ulster | 12404 | G | 3024 | High Falls | N |  | 6 | [13 empty] | NM | N | SMA-6000U | 2006-03-28 | 2006-04-03 | 4 | 2006-04-03 | [14 empty] | 2006-09-21 | 2006-09-25 |  | Y
Central Hudson |  | Randolph Horner | CH-02956 | Kingston | Woodstock |  | 12598 | G | 3014 | Woodstock | TBD |  | 15 | [13 empty] | NM | N | Fronius IG-4000, IG-3000 | 2006-04-17 | 2006-04-21 | 4 | 2006-04-21 | [17 empty] | W
Central Hudson |  | Hudson Solar | CH-01987 | Newburgh | Gardiner | Ulster | 12525 | G | 5011 | Modena | N | CH-01987 | 4 | [13 empty] | NM | N | Sunpowered SPR-2000 | 2006-04-21 | 2006-04-26 | 3 | 2006-04-26 | [14 empty] | 2006-06-14 | 2006-06-14 |  | Y
Central Hudson |  | Hudson Solar | CH-01229 | Poughkeepsie | Stanfordvl | Dutchess | 12581 | G | 7072 | Stanfordville | N | CH-01229 | 2.5 | [13 empty] | NM | N | Xantrex GT2.5 | 2006-05-01 | 2006-05-03 | 2 | 2006-05-03 | [14 empty] | 2006-08-16 | 2006-08-17 |  | Y
Central Hudson |  | Hudson Solar | CH-01499 | Poughkeepsie | Ancram | Columbia | 12502 | G | 7092 | Pulvers Corners | N |  | 6.4 | [13 empty] | NM | N | SPR-3200 | 2006-05-01 | 2006-05-03 | 2 | 2006-05-03 | [14 empty] | 2006-09-15 | 2006-09-19 |  | Y
Central Hudson |  | Hudson Solar | CH-01819 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6065 | Inwood Ave | N | CH-01819 | 8 | [13 empty] | NM | N | Sunpowered SPR-2000 | 2006-05-01 | 2006-05-03 | 2 | 2006-05-03 | [14 empty] | 2006-09-15 | 2006-09-19 |  | Y
Central Hudson |  | Hudson Solar | CH-01944 | Newburgh | New Paltz | Ulster | 12561 | G | 5031 | Galeville | N | CH-01944 | 5 | [13 empty] | NM | N | Xantrex GT2.5 | 2006-05-01 | 2006-05-03 | 2 | 2006-05-03 | [14 empty] | 2006-12-04 | 2006-12-05 |  | Y
Central Hudson |  | Hudson Solar | CH-02088 | Poughkeepsie | Staatsburg | Dutchess | 12580 | G | 7041 | Staatsburg | N |  | 3.2 | [13 empty] | NM | N | Sunpowered SPR-3200 | 2006-05-15 | 2006-05-18 | 3 | 2006-05-18 | [14 empty] | 2006-09-15 | 2006-09-19 |  | Y
Central Hudson |  | Hudson Solar | CH-01354 | Newburgh | Gardiner | Ulster | 12525 | G | 5031 | Galeville | N |  | 6.6 | [13 empty] | NM | N | GT3.3 | 2006-05-26 | 2006-06-02 | 4 | 2006-06-02 | [14 empty] | 2006-10-02 | 2006-10-05 |  | Y
Central Hudson |  | Sunstruck Design | CH-09687 | Kingston | Olive Brdg | Ulster | 12461 | G | 3082 | Kerhonkson | N | CH-09687 | 2.4 | [13 empty] | NM | N | Xantrex GT2.5 | 2006-05-31 | 2006-06-06 | 4 | 2006-06-06 | [14 empty] | 2006-07-14 | 2006-07-14 |  | Y
Central Hudson |  | Hudson Solar | CH-01588 | Newburgh | Gardiner | Ulster | 12525 | G | 5031 | Galeville | N |  | 2.5 | [13 empty] | NM | N | SB-2500U | 2006-06-06 | 2006-06-09 | 3 | 2006-06-09 | [14 empty] | 2006-08-08 | 2006-08-09 |  | Y
Central Hudson |  | Hudson Solar | CH-01731 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6046 | Spackenkill | N |  | 4 | [13 empty] | NM | N | SPR-2000 | 2006-06-09 | 2006-06-09 | 0 | 2006-06-09 | [14 empty] | 2006-09-15 | 2006-09-19 |  | Y
Central Hudson |  | Hudson Solar | CH-01813 | Poughkeepsie | Salt Pt | Dutchess | 12578 | G | 7011 | Hibernia | N | CH-01813 | 5.2 | [13 empty] | NM | N | SPR-5200 | 2006-06-09 | 2006-06-09 | 0 | 2006-06-09 | [14 empty] | 2006-09-12 | 2006-09-12 |  | Y
Central Hudson |  | ISI Solar | CH-02564 | Newburgh | Walden | Orange | 12586 | G | 5043 | East Walden | Y | CH-02564 | 3.8 | [13 empty] | NM | N | SMA-3800U | 2006-06-06 | 2006-06-09 | 3 | 2006-06-09 | [14 empty] | 2006-07-21 | 2006-07-21 |  | Y
Central Hudson |  | Hudson Solar | CH-01901 | Poughkeepsie | Millbrook | Dutchess | 12545 | G | 7012 | Hibernia | N |  | 5.2 | [13 empty] | NM | N | SR-5200 | 2006-06-21 | 2006-06-26 | 3 | 2006-06-26 | [14 empty] | 2006-09-18 | 2006-09-19 |  | Y
Central Hudson |  | Hudson Solar | CH-01711 | Kingston | Napanoch | Ulster | 12458 | G | 3072 | Honk Falls | Y | CH-01711 | 2.5 | [13 empty] | NM | N | SMA-2500 | 2006-07-03 | 2006-07-10 | 4 | 2006-07-10 | [14 empty] | 2006-08-14 | 2006-08-17 |  | Y
Central Hudson |  | Hudson Solar | CH-01676 | Kingston | High Fls | Ulster | 12440 | G | 3024 | High Falls | N |  | 7.3 | [13 empty] | NM | N | SB3800U | 2006-07-10 | 2006-07-10 | 0 | 2006-07-10 | [14 empty] | 2006-09-21 | 2006-09-25 |  | W
Central Hudson |  | Hudson Solar | CH-01957 | Newburgh | Newburgh | Orange | 12550 | G | 410 | Montgomery St | N |  | 4.6 | [13 empty] | NM | N | SPR-5200 | 2006-07-10 | 2006-07-10 | 0 | 2006-07-10 | [14 empty] | 2006-11-06 | 2006-11-07 |  | Y
Central Hudson |  | Hudson Solar | CH-02263 | Poughkeepsie | Staatsburg | Dutchess | 12580 | G | 7041 | Staatsburg | N |  | 8 | [13 empty] | NM | N | SPR-4000x | 2006-07-10 | 2006-07-10 | 0 | 2006-07-10 | [14 empty] | 2006-11-27 | 2006-11-30 |  | Y
Central Hudson |  | Hudson Solar | CH-02269 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7041 | Staatsburg | N |  | 14.6 | [13 empty] | NM | N | SPR-3300x, SPR-4000x | 2006-07-10 | 2006-07-10 | 0 | 2006-07-10 | [14 empty] | 2006-11-27 | 2006-11-30 |  | Y
Central Hudson |  | Hudson Solar | CH-02294 | Poughkeepsie | Pine Plns | Dutchess | 12567 | G | 7091 | Pulvers Corners | N |  | 5.2 | [13 empty] | NM | N | SPR-5200 | 2006-07-12 | 2006-07-13 | 1 | 2006-07-13 | [14 empty] | 2006-10-20 | 2006-10-23 |  | Y
Central Hudson |  | Hudson Solar | CH-01791 | Poughkeepsie | Clinton Corners | Dutchess | 12514 | G | 7071 | Stanfordville | N |  | 5 | [13 empty] | NM | N | SMA 6000U | 2006-07-18 | 2006-07-18 | 0 | 2006-07-18 | [14 empty] | 2006-11-03 | 2006-11-07 |  | Y
Central Hudson |  | Hudson Solar | CH-02240 | Kingston | Mt Tremper | Ulster | 12457 | G | 3012 | Woodstock | N |  | 7.6 | [13 empty] | NM | N | SB3800 | 2006-07-24 | 2006-07-24 | 0 | 2006-07-24 | [14 empty] | 2007-03-01 | 2007-03-05 |  | Y
Central Hudson |  | Sunstruck Design | CH-09686 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7051 | Rhinebeck | N |  | 12 | [13 empty] | NM | N | SB6000U | 2006-07-24 | 2006-07-24 | 0 | 2006-07-24 | [14 empty] | 2007-03-27 | 2007-04-02 |  | Y
Central Hudson |  | Wiley Electronics LLC | CH-09941 | Catskill | Jewett | Greene | 12444 | E | 2081 | Hunter | N |  | 5.6 | [13 empty] | NM | N | PVP-2800XV | 2006-07-25 | 2006-07-31 | 4 | 2006-07-31 | [14 empty] | 2006-09-13 | 2006-09-19 |  | Y
Central Hudson |  | Global Resource Options | CH-01149 | Catskill | Westerlo |  | 12193 | G | 1091 | Westerlo | TBD |  | 2.1 | [13 empty] | NM | N | SB2100 | 2006-07-26 | 2006-07-26 | 0 | 2006-07-26 | [14 empty] | 2006-09-21 | 2006-10-05 |  | W
Central Hudson |  | Bruce E. Brooks & Associates | CH-00759 | Poughkeepsie | Millbrook |  | 12545 | G | 7011 | Hibernia | TBD |  | 2.8 | [13 empty] | NA | N | Xantrex GT 3.3 | 2006-08-04 | 2006-08-08 | 2 | 2006-08-08 | [17 empty] | W
Central Hudson |  | Hudson Solar | CH-02035 | Kingston | Woodstock | Ulster | 12498 | G | 3012 | Woodstock | N |  | 3.8 | [13 empty] | NM | N | SMA-3800 | 2006-08-07 | 2006-08-08 | 1 | 2006-08-08 | [14 empty] | 2007-03-01 | 2007-03-05 |  | Y
Central Hudson |  | Hudson Solar | CH-01422 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7062 | Milan | N |  | 14.5 | [13 empty] | NM | N | SMA-6000U, SMA-2500U | 2006-08-14 | 2006-08-16 | 2 | 2006-08-16 | [14 empty] | 2006-12-07 | 2006-12-12 |  | W
Central Hudson |  | Hudson Solar | CH-02137 | Poughkeepsie | Milan |  | 12571 | G | 7061 | Milan | TBD |  | 14.5 | [13 empty] | NM | N | SMA-6000U, SMA-2500U | 2006-08-14 | 2006-08-16 | 2 | 2006-08-16 | [15 empty] | 2006-12-12 |  | W |  | SC14 customer switched to residential NM after 2/09; contractor performed SIR test and sent documentation
Central Hudson |  | Hudson Solar | CH-02485 | Newburgh | New Paltz | Ulster | 12561 | G | 5011 | Modena | N | CH-01949 | 2.4 | [13 empty] | NM | N | SMA-6000U | 2006-08-15 | 2006-08-16 | 1 | 2006-08-16 | [14 empty] | 2006-09-15 | 2006-09-19 |  | Y
Central Hudson |  | Hudson Solar | CH-01749 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 7011 | Hibernia | N |  | 12 | [13 empty] | NM | N | SPR-4000X | 2006-08-25 | 2006-08-28 | 1 | 2006-08-28 | [14 empty] | 2006-10-20 | 2006-10-23 |  | Y
Central Hudson |  | Hudson Solar | CH-01895 | Poughkeepsie | Stanfordvl | Dutchess | 12581 | G | 7071 | Stanfordville | N |  | 6.6 | [13 empty] | NM | N | SPR-3300x | 2006-08-25 | 2006-08-28 | 1 | 2006-08-28 | [14 empty] | 2007-01-20 | 2007-01-23 |  | Y
Central Hudson |  | Hudson Solar | CH-01754 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 6075 | East Park | N |  | 7.3 | [13 empty] | NM | N | SPR-4000x, SPR-3300x | 2006-09-25 | 2006-09-26 | 1 | 2006-09-26 | [14 empty] | 2007-07-06 | 2007-07-11 |  | Y
Central Hudson |  | Hudson Solar | CH-02098 | Poughkeepsie | Clinton Cors | Dutchess | 12514 | G | 7071 | Stanfordville | N |  | 6.6 | [13 empty] | NM | N | SunPower SPR-3300x | 2006-09-29 | 2006-10-05 | 4 | 2006-10-05 | [14 empty] | 2006-12-14 | 2006-12-19 |  | Y
Central Hudson |  | Hudson Solar | CH-01378 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7056 | Rhinebeck | N | CH-01378 | 14.6 | [13 empty] | NM | N | SunPower 3300x & 4000x | 2006-10-05 | 2006-11-08 | 23 | 2006-11-08 | [14 empty] | 2007-07-06 | 2007-07-10 |  | Y
Central Hudson |  | Hudson Solar | CH-01471 | Newburgh | Esopus | Ulster | 12429 | G | 5084 | Highland | N |  | 14.6 | [13 empty] | NM | N | SunPower 3300x & 4000x | 2006-10-05 | 2006-11-08 | 23 | 2006-11-08 | [14 empty] | 2007-05-29 | 2007-06-01 |  | Y
Central Hudson |  | Hudson Solar | CH-01531 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7041 | Staatsburg | N |  | 12 | [13 empty] | NM | N | SunPower 4000x | 2006-10-05 | 2006-11-08 | 23 | 2006-11-08 | [14 empty] | 2009-01-07 | 2009-01-15 |  | Y
Central Hudson |  | Hudson Solar | CH-01721 | Kingston | Kingston | Ulster | 12401 | G | 2016 | Lincoln Park | N |  | 2.58 | [13 empty] | NM | N | SPR-2000 | 2006-10-16 | 2006-10-24 | 6 | 2006-10-24 | [14 empty] | 2007-01-02 | 2007-01-03 |  | Y
Central Hudson |  | Hudson Solar | CH-02471 | Poughkeepsie | Millerton | Dutchess | 12546 | G | 7092 | Pulvers Corners | N | CH-01885 | 7.5 | [13 empty] | NM | N | SB2500U | 2006-10-05 | 2006-11-08 | 23 | 2006-11-08 | [14 empty] | 2007-02-14 | 2007-02-20 |  | Y
Central Hudson |  | Hudson Solar | CH-02539 | Poughkeepsie | Staatsburg |  | 12580 | G | 7053 | Rhinebeck | TBD |  | 12 | [13 empty] | NM | N | Sunpower 4000X | 2006-10-05 | 2006-11-08 | 23 | 2006-11-08 | [17 empty] | W |  | delay due to changes in net metering regulations for CH
Central Hudson |  | Hudson Solar | CH-01555 | Kingston | Ulster Pk | Ulster | 12487 | G | 1023 | East Kingston | N |  | 4 | [13 empty] | NM | N | SPR-2000 | 2006-10-17 | 2006-10-24 | 5 | 2006-10-24 | [14 empty] | 2007-01-31 | 2007-02-06 |  | Y
Central Hudson |  | Hudson Solar | CH-02424 | Kingston | Ulster Pk | Ulster | 12487 | G | 1014 | Boulevard | N |  | 6.4 | [13 empty] | NM | N | SPR-3200 | 2006-10-06 | 2006-10-24 | 11 | 2006-10-24 | [14 empty] | 2007-01-31 | 2007-02-06 |  | Y
Central Hudson |  | Hudson Solar | CH-01271 | Kingston | Accord |  | 12404 | G | 3024 | High Falls | TBD |  | 4.99 | [13 empty] | NA | N | SMA-6000 | 2006-10-23 | 2006-10-25 | 2 | 2006-10-25 | [15 empty] | 2007-02-22 |  | W |  | SC14 commercial customer; contractor performed SIR test and sent documentation
Central Hudson |  | Hudson Solar | CH-01575 | Poughkeepsie | Staatsburg | Dutchess | 12580 | G | 7042 | Staatsburg | N |  | 6 | [13 empty] | NM | N | SB6000U | 2006-10-23 | 2006-10-25 | 2 | 2006-10-25 | [14 empty] | 2007-09-07 | 2007-09-13 |  | Y
Central Hudson |  | Sun Mountain | CH-09115 | Kingston | Glenford | Ulster | 12433 | G | 3013 | Woodstock | N |  | 3.8 | [13 empty] | NM | N | SMA-3800U | 2006-10-25 | 2006-10-25 | 0 | 2006-10-25 | [14 empty] | 2006-12-06 | 2006-12-12 |  | Y
Central Hudson |  | Hudson Solar | CH-01706 | Kingston | Ellenvl | Ulster | 12428 | G | 3078 | Greenfield Rd | N |  | 5 | [13 empty] | NM | N | Xantrex GT2.5 | 2006-10-24 | 2006-10-25 | 1 | 2006-10-25 | [14 empty] | 2007-01-20 | 2007-01-23 |  | Y
Central Hudson |  | SunDog Solar | CH-09141 | Catskill | Westerlo |  | 12193 | G | 1091 | Westerlo | TBD |  | 7.2 | [13 empty] | NM | N | Outback GPTX 3648 | 2006-11-06 | 2006-11-10 | 4 | 2006-11-10 | [17 empty] | W
Central Hudson |  | Hudson Solar | CH-01741 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7053 | Rhinebeck | N |  | 6.6 | [13 empty] | NM | N | SPR-3300x | 2006-11-07 | 2006-11-09 | 2 | 2006-11-09 | [14 empty] | 2007-01-31 | 2007-02-06 |  | Y
Central Hudson |  | altPower | CH-00648 | Poughkeepsie | Rhinebeck | Dutchess | 12574 | G | 7055 | Rhinebeck | N | CH-00648 | 10.6 | [13 empty] | NM | N | SunPower 5200 | 2007-01-19 | 2007-01-22 | 1 | 2007-01-22 | [14 empty] | 2007-05-24 | 2007-06-01 |  | Y
Central Hudson |  | Hudson Solar | CH-01677 | Kingston | High Fls | Ulster | 12440 | G | 3024 | High Falls | N |  | 9.7 | [13 empty] | NM | N | SMA 3800 & 6000 | 2006-11-10 | 2006-11-15 | 3 | 2006-11-15 | [14 empty] | 2007-04-10 | 2007-04-18 |  | Y
Central Hudson |  | Hudson Solar | CH-02295 | Poughkeepsie | Pine Plns | Dutchess | 12567 | G | 7091 | Pulvers Corners | N | CH-02295 | 6.6 | [13 empty] | NM | N | SPR-3300x | 2006-11-15 | 2006-11-22 | 5 | 2006-11-22 | [14 empty] | 2007-02-14 | 2007-02-20 |  | Y
Central Hudson |  | Hudson Solar | CH-01893 | Poughkeepsie | Milan | Dutchess | 12571 | G | 7061 | Milan | N |  | 9.98 | [13 empty] | NM | N | SMA 6000 & 4000 | 2006-11-20 | 2006-11-22 | 2 | 2006-11-22 | [14 empty] | 2007-06-13 | 2007-06-19 |  | Y
Central Hudson |  | Hudson Solar | CH-02044 | Kingston | Kingston | Ulster | 12401 | G | 122 | Converse St | N |  | 3.3 | [13 empty] | NM | N | SPR-3300x | 2006-11-20 | 2006-11-22 | 2 | 2006-11-22 | [14 empty] | 2007-03-02 | 2007-03-14 |  | Y
Central Hudson |  | Hudson Solar | CH-01383 | Newburgh | Milton | Ulster | 12547 | G | 5083 | Highland | N |  | 10.6 | [13 empty] | NM | N | SPR 4000x & SPR 3300x | 2006-11-29 | 2006-12-04 | 3 | 2006-12-04 | [14 empty] | 2007-06-19 | 2007-07-03 |  | Y
Central Hudson |  | Hudson Solar | CH-01404 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7053 | Rhinebeck | N | CH-01404 | 5.2 | [13 empty] | NM | N | SPR-5200 | 2006-11-29 | 2006-12-04 | 3 | 2006-12-04 | [14 empty] | 2007-03-06 | 2007-03-14 |  | Y
Central Hudson |  | Hudson Solar | CH-01498 | Poughkeepsie | Tivoli | Dutchess | 12583 | G | 7062 | Milan | N |  | 6.6 | [13 empty] | NM | N | SPR-3300x | 2006-12-12 | 2006-12-18 | 4 | 2006-12-18 | [14 empty] | 2007-06-28 | 2007-07-03 |  | Y
Central Hudson |  | Global Resource Options | CH-01143 | Catskill | Rensselaervl | Albany | 12147 | G | 1092 | Westerlo | N |  | 3.8 | [13 empty] | NM | N | SMA-3800 | 2006-12-13 | 2006-12-18 | 3 | 2006-12-18 | [14 empty] | 2007-02-08 | 2007-02-09 |  | W
Central Hudson |  | Hudson Solar | CH-01598 | Catskill | Haines Fls | Greene | 12436 | G | 2385 | Lawrenceville | N | CH-01598 | 6 | [13 empty] | NM | N | SMA-6000U | 2006-12-13 | 2006-12-18 | 3 | 2006-12-18 | [14 empty] | 2007-06-04 | 2007-06-11 |  | Y
Central Hudson |  | Hudson Solar | CH-01674 | Kingston | Tillson | Ulster | 12486 | G | 3022 | High Falls | N |  | 4.2 | [13 empty] | NM | N | SMA 2100 | 2006-12-19 | 2006-12-26 | 3 | 2006-12-26 | [14 empty] | 2007-05-04 | 2007-05-11 |  | Y
Central Hudson |  | Hudson Solar | CH-02015 | Kingston | Stone Ridge | Ulster | 12484 | G | 3024 | High Falls | N |  | 4 | [13 empty] | NM | N | SPR-4000x | 2006-12-20 | 2006-12-26 | 2 | 2006-12-26 | [14 empty] | 2007-02-16 | 2007-02-20 |  | Y
Central Hudson |  | Renewable Power Systems | CH-02979 | Poughkeepsie | Verbank | Dutchess | 12585 | G | 6057 | Todd Hill | N |  | 3.8 | [13 empty] | NM | N | SMA-3800U | 2006-12-21 | 2006-12-28 | 3 | 2006-12-28 | [14 empty] | 2007-01-08 | 2007-01-09 |  | Y
Central Hudson |  | Hudson Solar | CH-01972 | Newburgh | Gardiner | Ulster | 12525 | G | 5034 | Galeville | N |  | 9.9 | [13 empty] | NM | N | SPR-3300x | 2007-01-04 | 2007-01-09 | 3 | 2007-01-09 | [14 empty] | 2007-04-25 | 2007-05-03 |  | Y
Central Hudson |  | Hudson Solar | CH-01960 | Newburgh | Newburgh | Orange | 12550 | G | 4015 | West Balmville | N | CH-01960 | 5.2 | [13 empty] | NM | N | SPR-5200 | 2007-01-09 | 2007-01-09 | 0 | 2007-01-09 | [14 empty] | 2007-05-15 | 2007-05-17 |  | W
Central Hudson |  | Hudson Solar | CH-01276 | Newburgh | Esopus | Ulster | 12429 | G | 5084 | Highland | N |  | 6.6 | [13 empty] | NM | N | SPR-3300x | 2007-01-16 | 2007-01-18 | 2 | 2007-01-18 | [14 empty] | 2007-04-27 | 2007-05-03 |  | W
Central Hudson |  | Hudson Solar | CH-02231 | Kingston | Kingston | Ulster | 12401 | G | 1022 | East Kingston | N |  | 3.3 | [13 empty] | NM | N | SB3300U | 2007-01-16 | 2007-01-18 | 2 | 2007-01-18 | [14 empty] | 2007-05-29 | 2007-06-01 |  | Y
Central Hudson |  | Hudson Solar | CH-02343 | Poughkeepsie | Lagrangeville | Dutchess | 12540 | G | 6055 | Todd Hill | N |  | 6.6 | [13 empty] | NM | N | SPR-3300x | 2007-01-16 | 2007-01-18 | 2 | 2007-01-18 | [14 empty] | 2007-09-05 | 2007-09-13 |  | Y
Central Hudson |  | Hudson Solar | CH-01417 | Newburgh | New Paltz | Ulster | 12561 | G | 5084 | Highland | N |  | 9.9 | [13 empty] | NM | N | SPR-3300x | 2007-01-22 | 2007-01-23 | 1 | 2007-01-23 | [14 empty] | 2007-06-22 | 2007-07-03 |  | Y
Central Hudson |  | Hudson Solar | CH-01280 | Kingston | Marbletown | Ulster | 12484 | G | 3023 | High Falls | N |  | 9.9 | [13 empty] | NM | N | SPR-3300x | 2007-01-25 | 2007-01-31 | 4 | 2007-01-31 | [14 empty] | 2007-07-06 | 2007-07-10 |  | W
Central Hudson |  | Wiley Electronics LLC | CH-09949 | Kingston | Woodstock | Ulster | 12498 | G | 3012 | Woodstock | N |  | 3 | [13 empty] | NM | N | (1) GTFX3048 | 2007-02-06 | 2007-02-23 | 13 | 2007-02-23 | [14 empty] | 2007-04-11 | 2007-04-18 |  | Y
Central Hudson |  | The Solar Center | CH-09711 | Newburgh | Newburgh | Orange | 12550 | G | 4011 | West Balmville | N |  | 4 | [13 empty] | NM | N | Fronius IG4000 | 2007-02-23 | 2007-02-27 | 2 | 2007-02-27 | [14 empty] | 2007-03-30 | 2007-04-03 |  | Y
Central Hudson |  | Advanced Energy Design | CH-00635 | Newburgh | Campbell Hall | Orange | 10916 | G | 5051 | Maybrook | N |  | 6 | [13 empty] | NM | N | SB6000U | 2007-03-27 | 2007-03-28 | 1 | 2007-03-28 | [14 empty] | 2007-06-20 | 2007-07-03 |  | Y
Central Hudson |  | Hudson Solar | CH-01608 | Catskill | Medusa | Albany | 12120 | G | 1092 | Westerlo | N |  | 9.9 | [13 empty] | NM | N | SPR-3300x | 2007-03-05 | 2007-03-07 | 2 | 2007-03-07 | [14 empty] | 2007-08-22 | 2007-08-31 |  | Y
Central Hudson |  | Hudson Solar | CH-01654 | Kingston | Kerhonkson |  | 12446 | G | 3081 | Kerhonkson | TBD |  | 9.8 | [13 empty] | NM | N | SMA 3800U, SMA 6000U | 2007-03-05 | 2007-03-07 | 2 | 2007-03-07 | [17 empty] | W |  | This project has been abandoned per the customers email 5/23/12.
Central Hudson |  | Hudson Solar | CH-01694 | Kingston | Mt Tremper | Ulster | 12457 | G | 3012 | Woodstock | N |  | 6.56 | [13 empty] | NM | N | SPR-3300x | 2007-03-05 | 2007-03-07 | 2 | 2007-03-07 | [14 empty] | 2007-07-24 | 2007-07-26 |  | Y
Central Hudson |  | Hudson Solar | CH-01736 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6096 | Manchester | N | CH-01736 | 4 | [13 empty] | NM | N | SPR-4000x | 2007-03-05 | 2007-03-07 | 2 | 2007-03-07 | [14 empty] | 2007-07-06 | 2007-07-11 |  | Y
Central Hudson |  | Hudson Solar | CH-01737 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6065 | Inwood Ave | N |  | 9.9 | [13 empty] | NM | N | Sun Power 3300x | 2007-03-05 | 2007-03-07 | 2 | 2007-03-07 | [14 empty] | 2007-07-19 | 2007-07-26 |  | Y
Central Hudson |  | Hudson Solar | CH-01884 | Poughkeepsie | Millerton | Dutchess | 12546 | G | 7095 | Smithfield | N |  | 9.9 | [13 empty] | NM | N | SPR-3300x | 2007-03-05 | 2007-03-07 | 2 | 2007-03-07 | [14 empty] | 2007-12-21 | 2007-12-27 |  | Y
Central Hudson |  | Hudson Solar | CH-02032 | Kingston | Bearsvl | Ulster | 12409 | G | 3012 | Woodstock | N |  | 8 | [13 empty] | NM | N | SPR-4000x | 2007-03-05 | 2007-03-07 | 2 | 2007-03-07 | [14 empty] | 2007-11-20 | 2007-11-26 |  | Y
Central Hudson |  | Hudson Solar | CH-02091 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7042 | Staatsburg | N |  | 10 | [13 empty] | NM | N | SB3300U | 2007-03-05 | 2007-03-07 | 2 | 2007-03-07 | [14 empty] | 2007-08-07 | 2007-08-15 |  | Y
Central Hudson |  | Hudson Solar | CH-02196 | Newburgh | New Paltz | Ulster | 12561 | G | 5021 | Ohioville | N | CH-02196 | 3.3 | [13 empty] | NM | N | SPR-3300x | 2007-03-05 | 2007-03-07 | 2 | 2007-03-07 | [14 empty] | 2007-07-24 | 2007-07-26 |  | Y
Central Hudson |  | Hudson Solar | CH-02457 | Poughkeepsie | Salt Pt | Dutchess | 12578 | G | 7011 | Hibernia | N | CH-01813 | 4 | [13 empty] | NM | N | SPR-4000x | 2007-03-05 | 2007-03-07 | 2 | 2007-03-07 | [14 empty] | 2007-08-08 | 2007-08-15 |  | Y
Central Hudson |  | Hudson Solar | CH-02484 | Newburgh | New Paltz | Ulster | 12561 | G | 5031 | Galeville | N | CH-01944 | 4.76 | [13 empty] | NM | N | Xantrex GT2.5 | 2007-03-05 | 2007-03-07 | 2 | 2007-03-07 | [14 empty] | 2007-07-06 | 2007-07-11 |  | Y
Central Hudson |  | Hudson Solar | CH-02525 | Newburgh | Mountainville |  | 10953 | G | 4093 | Bethlehem Rd | TBD |  | 7.3 | [13 empty] | NM | N | Sun Power 3300x & 4000x | 2007-03-05 | 2007-03-07 | 2 | 2007-03-07 | [17 empty] | W
Central Hudson |  | altPower | CH-00646 | Kingston | Saugerties | Ulster | 12477 | G | 3001 | Saugerties | N |  | 2.5 | [13 empty] | NM | N | Xantrex GT2.5 | 2007-03-06 | 2007-03-09 | 3 | 2007-03-09 | [14 empty] | 2007-12-09 | 2007-12-14 |  | Y
Central Hudson |  | Sun Mountain | CH-09106 | Kingston | Woodstock | Ulster | 12498 | G | 3012 | Woodstock | N |  | 7.2 | [13 empty] | NM | N | SMA 6000U, SMA 3000U | 2007-03-06 | 2007-03-09 | 3 | 2007-03-09 | [14 empty] | 2007-08-22 | 2007-08-31 |  | Y
Central Hudson |  | Self | CH-08874 | Kingston | Saugerties |  | 12477 | G | 3002 | Saugerties | TBD |  | 5 | [13 empty] | NM | N | Trace PS25-12 | 2007-03-23 | 2007-04-24 | 21 | 2007-04-24 | [17 empty] | W |  | incomplete application - sent notice 3/13/2007 of what was missing, completed 3/23/2007; reviewed 3/27/2007 - AC disconnect not manual - spoke with customer that day and sent followup letter 4/10/2007, received info from electrician 4/18/2007. Abandoned.
Central Hudson |  | Hudson Solar | CH-02430 | Catskill | Hunter | Greene | 12442 | E | 2081 | Hunter | N |  | 3.3 | [13 empty] | NM | N | (1) SPR-3300x | 2007-03-09 | 2007-03-14 | 3 | 2007-03-14 | [14 empty] | 2007-08-22 | 2007-08-31 |  | Y
Central Hudson |  | Hudson Solar | CH-02027 | Kingston | Kingston | Ulster | 12401 | G | 2012 | Lincoln Park | N |  | 2.87 | [13 empty] | NM | N | SPR-3300x | 2007-03-12 | 2007-03-14 | 2 | 2007-03-14 | [14 empty] | 2007-10-09 | 2007-10-24 |  | Y
Central Hudson |  | EBM Consulting | CH-01091 | Poughkeepsie | Clinton Corners |  | 12514 | G | 7012 | Hibernia | TBD |  | 32.4 | [13 empty] | NM | N | SMA 6000U | 2007-03-26 | 2007-03-27 | 1 | 2007-03-27 | [15 empty] | 2007-10-31 |  | W |  | CH performed SIR test.
Central Hudson |  | Hudson Solar | CH-01663 | Kingston | Stone Ridge | Ulster | 12484 | G | 3023 | High Falls | N |  | 6 | [13 empty] | NM | N | SB6000U | 2007-03-26 | 2007-03-28 | 2 | 2007-03-28 | [14 empty] | 2007-08-08 | 2007-08-15 |  | Y
Central Hudson |  | Self | CH-08875 | Kingston | W Hurley | Ulster | 12491 | G | 3013 | Woodstock | N |  |  |  | 2.4 | [11 empty] | NM | N | Southwest Windpower Skystream 3.7 | 2007-04-11 | 2007-04-16 | 3 | 2007-04-16 | [14 empty] | 2007-07-02 | 2007-07-03 |  | W
Central Hudson |  | Solar Generation | CH-08221 | Kingston | Glenford | Ulster | 12433 | G | 3013 | Woodstock | N |  | 6 | [13 empty] | NM | N | SMA 6000U | 2007-04-09 | 2007-04-10 | 1 | 2007-04-10 | [14 empty] | 2007-10-25 | 2007-10-31 |  | Y
Central Hudson |  | Sunstruck Design | CH-09681 | Kingston | High Fls | Ulster | 12440 | G | 3022 | High Falls | N | CH-09681 | 3 | [13 empty] | NM | N | Xantrex GT3.0 | 2007-04-09 | 2007-04-10 | 1 | 2007-04-10 | [14 empty] | 2007-09-11 | 2007-09-13 |  | Y
Central Hudson |  | Hudson Solar | CH-01348 | Newburgh | New Paltz | Ulster | 12561 | G | 5023 | Ohioville | N |  | 4 | [13 empty] | NM | N | SPR-4000x | 2007-04-17 | 2007-04-24 | 5 | 2007-04-24 | [14 empty] | 2007-08-28 | 2007-08-31 |  | Y
Central Hudson |  | Hudson Solar | CH-01764 | Poughkeepsie | Staatsburg | Dutchess | 12580 | G | 7041 | Staatsburg | N |  | 4.92 | [13 empty] | NM | N | SPR-5200 | 2007-04-17 | 2007-04-24 | 5 | 2007-04-24 | [14 empty] | 2007-08-28 | 2007-08-31 |  | Y
Central Hudson |  | Mercury Solar Systems | CH-02626 | Newburgh | Montgomery | Orange | 12549 | G | 4026 | Coldenham | N | CH-23628 | 5.04 | [13 empty] | NM | N | SPR-5200 | 2007-04-24 | 2007-05-01 | 5 | 2007-05-01 | [14 empty] | 2007-08-17 | 2007-08-22 |  | Y
Central Hudson |  | Hudson Solar | CH-01296 | Poughkeepsie | Salt Pt | Dutchess | 12578 | G | 7011 | Hibernia | N |  | 4.92 | [13 empty] | NM | N | SPR-5200 | 2007-04-27 | 2007-05-01 | 2 | 2007-05-01 | [14 empty] | 2007-08-30 | 2007-08-31 |  | Y
Central Hudson |  | Renewable Power Systems | CH-02980 | Catskill | Greenvl | Greene | 12083 | G | 1091 | Westerlo | N |  | 2.94 | [13 empty] | NM | N | SPRx 3300 | 2007-05-07 | 2007-05-11 | 4 | 2007-05-11 | [14 empty] | 2007-07-29 | 2007-08-02 |  | Y
Central Hudson |  | Renewable Power Systems | CH-02981 | Newburgh | Highland | Ulster | 12528 | G | 5084 | Highland | N | CH-09690 | 5.1 | [13 empty] | NM | N | Fronius IG 5100 | 2007-05-07 | 2007-05-16 | 7 | 2007-05-16 | [14 empty] | 2007-11-09 | 2007-11-26 |  | Y
Central Hudson |  | Hudson Solar | CH-01817 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 7024 | Tinkertown | N |  | 6.56 | [13 empty] | NM | N | SPR-3300x | 2007-05-09 | 2007-05-11 | 2 | 2007-05-11 | [14 empty] | 2007-09-04 | 2007-09-12 |  | Y
Central Hudson |  | Solarias, Inc. | CH-09060 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8071 | Shenandoah | N | CH-09060 | 3.8 | [13 empty] | NM | N | PVB-3800 | 2007-05-14 | 2007-05-17 | 3 | 2007-05-17 | [14 empty] | 2007-10-12 | 2007-10-24 |  | Y
Central Hudson |  | The Solar Center | CH-09710 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7053 | Rhinebeck | N |  | 5 | [13 empty] | NM | N | Beacon M5+ | 2007-05-14 | 2007-05-17 | 3 | 2007-05-17 | [14 empty] | 2007-07-06 | 2007-07-11 |  | Y
Central Hudson |  | Hudson Solar | CH-02370 | Poughkeepsie | Tivoli | Dutchess | 12583 | G | 7062 | Milan | N |  | 4 | [13 empty] | NM | N | SPR-4000x | 2007-05-18 | 2007-05-25 | 5 | 2007-05-25 | [14 empty] | 2007-10-01 | 2007-10-04 |  | Y
Central Hudson |  | Solarias, Inc. | CH-09061 | Poughkeepsie | Stanfordville |  | 12581 | G | 7072 | Stanfordville | TBD |  | 6 | [13 empty] | NM | N | SMA-6000U | 2007-05-18 | 2007-05-25 | 5 | 2007-05-25 | [17 empty] | W |  | 10/03/14 Project abandoned as per customer.
Central Hudson |  | altPower | CH-00645 | Catskill | Jewett | Greene | 12444 | E | 2389 | Vinegar Hill | N | CH-00645 | 5.2 | [13 empty] | NM | N | SPR-5200 | 2007-05-21 | 2007-05-25 | 4 | 2007-05-25 | [14 empty] | 2007-08-22 | 2007-10-31 |  | Y
Central Hudson |  | altPower | CH-00650 | Fishkill | Garrison | Putnam | 10524 | G | 8086 | Tioronda | N |  | 7 | [13 empty] | NM | N | Outback GVFX3648 | 2007-05-21 | 2007-05-25 | 4 | 2007-05-25 | [14 empty] | 2009-03-18 | 2009-03-18 |  | W
Central Hudson |  | Hudson Solar | CH-01470 | Kingston | Stone Ridge | Ulster | 12484 | G | 3023 | High Falls | N |  | 3.28 | [13 empty] | NM | N | SPR-3300x | 2007-05-21 | 2007-05-25 | 4 | 2007-05-25 | [14 empty] | 2007-11-02 | 2007-11-07 |  | Y
Central Hudson |  | Solar Generation | CH-08159 | Kingston | Bearsville |  | 12409 | G | 3012 | Woodstock | TBD |  | 4 | [13 empty] | NM | N | SMA SB4000U | 2007-05-24 | 2007-05-25 | 1 | 2007-05-25 | [17 empty] | W
Central Hudson |  | Hudson Solar | CH-02227 | Kingston | Accord | Ulster | 12404 | G | 3024 | High Falls | N | CH-02227 | 4.99 | [13 empty] | NM | N | SMA-6000 | 2007-06-12 | 2007-06-19 | 5 | 2007-06-19 | [14 empty] | 2007-11-16 | 2007-11-26 |  | Y
Central Hudson |  | ISI Solar | CH-02563 | Newburgh | Walden | Orange | 12586 | G | 5043 | East Walden | N |  | 5 | [13 empty] | NM | N | Xantrex GT-5.0 | 2007-06-25 | 2007-06-29 | 4 | 2007-06-29 | [14 empty] | 2007-10-29 | 2007-11-01 |  | Y
Central Hudson |  | SunTechnics Energy Systems | CH-09694 | Newburgh | Washingtonvl | Orange | 10922 | G | 5052 | Maybrook | N |  | 9 | [13 empty] | NM | N | Xantrex GT3.0 | 2007-06-19 | 2007-06-28 | 7 | 2007-06-28 | [14 empty] | 2007-08-08 | 2007-08-15 |  | Y
Central Hudson |  | Renewable Power Systems | CH-02971 | Newburgh | New Paltz | Ulster | 12561 | G | 5021 | Ohioville | N |  | 3.3 | [13 empty] | NM | N | SPR-3300X | 2007-06-28 | 2007-07-03 | 3 | 2007-07-03 | [14 empty] | 2007-11-13 | 2007-11-26 |  | Y
Central Hudson |  | Renewable Power Systems | CH-02972 | Newburgh | New Paltz | Ulster | 12561 | G | 5021 | Ohioville | N |  | 3.3 | [13 empty] | NM | N | SPR-3300X | 2007-06-28 | 2007-07-03 | 3 | 2007-07-03 | [14 empty] | 2007-11-13 | 2007-11-26 |  | Y
Central Hudson |  | SunTechnics Energy Systems | CH-09692 | Newburgh | Montgomery | Orange | 12549 | G | 5073 | Montgomery | N |  | 6 | [13 empty] | NM | N | GT 3.0 | 2007-07-10 | 2007-07-12 | 2 | 2007-07-12 | [14 empty] | 2007-08-15 | 2007-08-15 |  | Y
Central Hudson |  | SunTechnics Energy Systems | CH-09693 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8043 | Myers Corners | N |  | 4.73 | [13 empty] | NM | N | GT 3.0 | 2007-07-10 | 2007-07-12 | 2 | 2007-07-12 | [14 empty] | 2007-11-28 | 2007-12-06 |  | Y
Central Hudson |  | Mesa Environmental Sciences | CH-02633 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8093 | Fishkill Plains | N |  | 3 | [13 empty] | NM | N | GT-3.0 | 2007-07-10 | 2007-07-12 | 2 | 2007-07-12 | [14 empty] | 2007-08-08 | 2007-08-15 |  | Y
Central Hudson |  | Hudson Solar | CH-01669 | Kingston | Rifton | Ulster | 12471 | G | 3041 | Sturgeon Pool | N |  | 9.9 | [13 empty] | NM | N | SPR-3300x | 2007-07-02 | 2007-07-05 | 2 | 2007-07-05 | [14 empty] | 2007-09-18 | 2007-09-27 |  | Y
Central Hudson |  | Hudson Solar | CH-01812 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 7023 | Tinkertown | N |  | 5.2 | [13 empty] | NM | N | SPR-5200 | 2007-07-02 | 2007-07-05 | 2 | 2007-07-05 | [14 empty] | 2007-09-25 | 2007-09-27 |  | Y
Central Hudson |  | Hudson Solar | CH-01882 | Poughkeepsie | Ancramdale | Columbia | 12503 | G | 7092 | Pulvers Corners | N |  | 6.6 | [13 empty] | NM | N | SPR-3300x | 2007-07-02 | 2007-07-03 | 1 | 2007-07-03 | [14 empty] | 2007-10-15 | 2007-10-24 |  | W
Central Hudson |  | Sun Mountain | CH-09110 | Kingston | Olivebridge | Ulster | 12461 | G | 3024 | High Falls | N |  | 3 | [13 empty] | NM | N | Xantrex GT3.0 | 2007-07-20 | 2007-07-24 | 2 | 2007-07-24 | [14 empty] | 2007-10-01 | 2007-10-04 |  | Y
Central Hudson |  | Sun Mountain | CH-09119 | Kingston | Stone Ridge | Ulster | 12484 | G | 3024 | High Falls | N |  | 4.8 | [13 empty] | NM | N | SMA 6000U | 2007-07-20 | 2007-07-24 | 2 | 2007-07-24 | [14 empty] | 2007-10-15 | 2007-10-24 |  | Y
Central Hudson |  | Hudson Solar | CH-01631 | Catskill | Catskill | Greene | 12414 | G | 2003 | North Catskill | N |  | 3.3 | [13 empty] | NM | N | SPR-3300x | 2007-07-20 | 2007-07-24 | 2 | 2007-07-24 | [14 empty] | 2007-11-16 | 2007-12-06 |  | Y
Central Hudson |  | Hudson Solar | CH-02209 | Newburgh | Gardiner | Ulster | 12525 | G | 5011 | Modena | N |  | 6.6 | [13 empty] | NM | N | SPR-3300x | 2007-07-20 | 2007-07-24 | 2 | 2007-07-24 | [14 empty] | 2007-09-19 | 2007-09-27 |  | Y
Central Hudson |  | Hudson Solar | CH-01897 | Poughkeepsie | Stanfordvl | Dutchess | 12581 | G | 7071 | Stanfordville | N |  | 6.6 | [13 empty] | NM | N | SPR-3300x | 2007-07-23 | 2007-07-24 | 1 | 2007-07-24 | [14 empty] | 2008-01-24 | 2008-01-24 |  | Y
Central Hudson |  | Hudson Solar | CH-02289 | Poughkeepsie | Pine Plns | Dutchess | 12567 | G | 7091 | Pulvers Corners | N |  | 4 | [13 empty] | NM | N | SunPower 4000x | 2007-07-23 | 2007-07-24 | 1 | 2007-07-24 | [14 empty] | 2007-10-11 | 2007-10-24 |  | Y
Central Hudson |  | Hudson Solar | CH-01320 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7053 | Rhinebeck | N |  | 3.3 | [13 empty] | NM | N | SPR-3300x | 2007-07-26 | 2007-08-02 | 5 | 2007-08-02 | [14 empty] | 2007-09-18 | 2007-09-27 |  | Y
Central Hudson |  | Hudson Solar | CH-01434 | Poughkeepsie | Millbrook | Dutchess | 12545 | G | 7012 | Hibernia | N |  | 2.87 | [13 empty] | NM | N | SPR-3300x | 2007-07-26 | 2007-08-02 | 5 | 2007-08-02 | [14 empty] | 2008-01-28 | 2008-01-31 |  | W
Central Hudson |  | Hudson Solar | CH-01537 | Poughkeepsie | Millerton | Dutchess | 12546 | G | 7095 | Smithfield | N |  | 9.9 | [13 empty] | NM | N | SPR-3300x | 2007-07-30 | 2007-08-02 | 3 | 2007-08-02 | [14 empty] | 2008-06-12 | 2008-06-16 |  | Y
Central Hudson |  | Hudson Solar | CH-01532 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6061 | Inwood Ave | N |  | 6.6 | [13 empty] | NM | N | SPR-3300x | 2007-08-01 | 2007-08-02 | 1 | 2007-08-02 | [14 empty] | 2007-11-09 | 2007-11-26 |  | Y
Central Hudson |  | Hudson Solar | CH-02270 | Poughkeepsie | Bangall | Dutchess | 12506 | G | 7072 | Stanfordville | N |  | 7.18 | [13 empty] | NM | N | 3300x & 4000x | 2007-08-01 | 2007-08-02 | 1 | 2007-08-02 | [14 empty] | 2008-01-28 | 2008-01-31 |  | Y
Central Hudson |  | Hudson Solar | CH-01274 | Kingston | Stone Ridge | Ulster | 12484 | G | 3023 | High Falls | N |  | 4 | [13 empty] | NM | N | SPR-4000x | 2007-08-02 | 2007-08-02 | 0 | 2007-08-02 | [14 empty] | 2007-12-20 | 2007-12-27 |  | Y
Central Hudson |  | Hudson Solar | CH-01733 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6093 | Manchester | N |  | 4.92 | [13 empty] | NM | N | SPR-5200 | 2007-08-02 | 2007-08-02 | 0 | 2007-08-02 | [14 empty] | 2007-12-03 | 2007-12-06 |  | Y
Central Hudson |  | Hudson Solar | CH-02101 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7056 | Rhinebeck | N | CH-02101 | 48 | [13 empty] | NM | N | SunPower 4000x | 2007-08-06 | 2007-09-14 | 28 | 2007-09-14 | [14 empty] | 2007-11-28 | 2007-12-06 |  | Y
Central Hudson |  | USA Wind Energy | CH-09751 | Kingston | Saugerties |  | 12477 | G | 3003 | Saugerties | TBD |  | 1.8 |  | 3.6 | [11 empty] | NM | N | Skystream Version 3.7 | 2007-08-14 | 2007-08-15 | 1 | 2007-08-15 | [17 empty] | W
Central Hudson |  | Hudson Solar | CH-01523 | Kingston | High Falls | Ulster | 12440 | G | 3024 | High Falls | N |  | 4.92 | [13 empty] | NM | N | SPR-5200 | 2007-09-11 | 2007-09-17 | 4 | 2007-09-17 | [14 empty] | 2007-12-22 | 2007-12-27 |  | Y
Central Hudson |  | Hudson Solar | CH-01616 | Catskill | Catskill | Greene | 12414 | G | 2006 | North Catskill | N | CH-01616 | 4 | [13 empty] | NM | N | SPR-4000x | 2007-09-11 | 2007-09-17 | 4 | 2007-09-17 | [14 empty] | 2008-01-28 | 2008-01-31 |  | Y
Central Hudson |  | Hudson Solar | CH-01719 | Kingston | Saugerties | Ulster | 12477 | G | 3003 | Saugerties | N |  | 4.92 | [13 empty] | NM | N | SPR-5000x | 2007-09-11 | 2007-09-17 | 4 | 2007-09-17 | [14 empty] | 2007-12-05 | 2007-12-14 |  | Y
Central Hudson |  | Hudson Solar | CH-02239 | Kingston | Shokan | Ulster | 12481 | G | 3011 | Woodstock | N |  | 5.13 | [13 empty] | NM | N | SPR-3300x | 2007-09-11 | 2007-09-17 | 4 | 2007-09-17 | [14 empty] | 2008-03-31 | 2008-04-02 |  | Y
Central Hudson |  | Hudson Solar | CH-02389 | Fishkill | Beacon | Dutchess | 12508 | G | 8017 | Forgebrook | N |  | 4 | [13 empty] | NM | N | SPR 4000 | 2007-09-11 | 2007-09-17 | 4 | 2007-09-17 | [14 empty] | 2008-05-21 | 2008-05-21 |  | Y
Central Hudson |  | Hudson Solar | CH-01384 | Newburgh | Marlboro | Ulster | 12542 | G | 5003 | Marlboro | N | CH-01384 | 27.9 | [13 empty] | NM | N | SPR-3300x | 2007-09-12 | 2007-09-18 | 4 | 2007-09-18 | [14 empty] | 2008-01-14 | 2008-01-14 |  | Y
Central Hudson |  | Hudson Solar | CH-02031 | Kingston | Bearsvl | Ulster | 12409 | G | 3012 | Woodstock | N | CH-02031 | 7 | [13 empty] | NM | N | SunPower 3000m, 4000m | 2007-09-17 | 2007-09-18 | 1 | 2007-09-18 | [14 empty] | 2008-05-13 | 2008-05-16 |  | W
Central Hudson |  | Solar Generation | CH-08230 | Kingston | Woodstock | Ulster | 12498 | G | 3012 | Woodstock | N |  | 3 | [13 empty] | NM | N | Fronius IG 3000 | 2007-09-20 | 2007-09-27 | 5 | 2007-09-27 | [14 empty] | 2008-03-16 | 2008-03-17 |  | Y
Central Hudson |  | Hudson Solar | CH-02268 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6097 | Manchester | N |  | 9.9 | [13 empty] | NM | N | SunPower 3300x, 208V | 2007-09-24 | 2007-09-27 | 3 | 2007-09-27 | [14 empty] | 2007-10-31 | 2007-11-01 |  | Y
Central Hudson |  | Solar Generation | CH-08172 | Kingston | Woodstock | Ulster | 12498 | G | 3013 | Woodstock | N | CH-08172 | 5 | [13 empty] | NM | N | SMA-SB5000U | 2007-10-03 | 2007-10-03 | 0 | 2007-10-03 | [14 empty] | 2008-01-03 | 2008-01-09 |  | Y
Central Hudson |  | Hudson Solar | CH-01503 | Poughkeepsie | Stanfordvl | Dutchess | 12581 | G | 7072 | Stanfordville | N |  | 9.9 | [13 empty] | NM | N | SPR-3300x | 2007-10-11 | 2007-10-18 | 5 | 2007-10-18 | [14 empty] | 2007-12-22 | 2007-12-27 |  | Y
Central Hudson |  | Hudson Solar | CH-01842 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7053 | Rhinebeck | N | CH-01842 | 8 | [13 empty] | NM | N | SPR-4000x | 2007-10-11 | 2007-10-18 | 5 | 2007-10-18 | [14 empty] | 2007-12-26 | 2007-12-27 |  | Y
Central Hudson |  | Hudson Solar | CH-01747 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7013 | Hibernia | N |  | 4.92 | [13 empty] | NM | N | SPR-5000x | 2007-10-15 | 2007-10-18 | 3 | 2007-10-18 | [14 empty] | 2008-03-12 | 2008-03-13 |  | Y
Central Hudson |  | Hudson Solar | CH-01650 | Kingston | Kerhonkson | Ulster | 12446 | G | 3082 | Kerhonkson | N |  | 4.92 | [13 empty] | NM | N | SPR-5000x | 2007-10-15 | 2007-10-19 | 4 | 2007-10-19 | [14 empty] | 2007-12-21 | 2007-12-27 |  | Y
Central Hudson |  | Hudson Solar | CH-01856 | Poughkeepsie | Rhinebeck |  | 12572 | G | 7053 | Rhinebeck | TBD |  | 9.9 | [13 empty] | NA | N | SPR-3300x | 2007-10-16 | 2007-10-18 | 2 | 2007-10-18 | [17 empty] | W |  | per HVCE order was cancelled
Central Hudson |  | Hudson Solar | CH-01225 | Kingston | Saugerties | Ulster | 12477 | G | 2015 | Lincoln Park | N | CH-01225 | 4 | [13 empty] | NM | N | SPR-4000x | 2007-10-26 | 2007-10-31 | 3 | 2007-10-31 | [14 empty] | 2008-02-21 | 2008-02-22 |  | Y
Central Hudson |  | Hudson Solar | CH-01782 | Poughkeepsie | Millbrook | Dutchess | 12545 | G | 6057 | Todd Hill | N |  | 2.1 | [13 empty] | NM | N | SPR-3300x | 2007-10-26 | 2007-10-30 | 2 | 2007-10-30 | [14 empty] | 2008-03-21 | 2008-03-25 |  | Y
Central Hudson |  | Hudson Solar | CH-01947 | Newburgh | Gardiner | Ulster | 12525 | G | 5031 | Galeville | N |  | 9.9 | [13 empty] | NM | N | SPR-3300x | 2007-10-26 | 2007-10-30 | 2 | 2007-10-30 | [14 empty] | 2008-03-31 | 2008-04-02 |  | Y
Central Hudson |  | groSolar | CH-01182 | Catskill | Greenvl | Greene | 12083 | G | 2061 | Freehold | N |  | 6 | [13 empty] | NM | N | PVI-3000 | 2007-10-29 | 2007-11-01 | 3 | 2007-11-01 | [14 empty] | 2008-04-09 | 2008-04-10 |  | Y
Central Hudson |  | Hudson Solar | CH-01981 | Newburgh | Wallkill | Ulster | 12589 | G | 5041 | East Walden | N | CH-01981 | 9.9 | [13 empty] | NM | N | SPR-3300x | 2007-11-05 | 2007-11-07 | 2 | 2007-11-07 | [14 empty] | 2008-05-21 | 2008-05-21 |  | Y
Central Hudson |  | Hudson Solar | CH-01541 | Newburgh | New Paltz | Ulster | 12561 | G | 5024 | Ohioville | N |  | 5.74 | [13 empty] | NM | N | SPR-3300x | 2007-11-06 | 2007-11-07 | 1 | 2007-11-07 | [14 empty] | 2008-02-21 | 2008-02-22 |  | Y
Central Hudson |  | Hudson Solar | CH-02374 | Fishkill | Beacon | Dutchess | 12508 | G | 8085 | Tioronda | N |  | 5 | [13 empty] | NM | N | SPR-5000x | 2007-11-07 | 2007-11-07 | 0 | 2007-11-07 | [14 empty] | 2008-03-28 | 2008-04-02 |  | Y
Central Hudson |  | Sun Mountain | CH-09107 | Newburgh | New Paltz | Ulster | 12561 | G | 5031 | Galeville | N |  | 2.4 | [13 empty] | NM | N | GT-2.8 | 2007-11-07 | 2007-11-07 | 0 | 2007-11-07 | [14 empty] | 2008-03-25 | 2008-03-26 |  | Y
Central Hudson |  | Hudson Solar | CH-01934 | Fishkill | Beacon | Dutchess | 12508 | G | 8087 | Tioronda | N | CH-01934 | 3.3 | [13 empty] | NM | N | SPR-3300x | 2007-11-12 | 2007-11-14 | 2 | 2007-11-14 | [14 empty] | 2008-03-28 | 2008-04-02 |  | Y
Central Hudson |  | Wiley Electronics LLC | CH-09939 | Kingston | W Hurley | Ulster | 12491 | G | 2094 | Hurley Ave | N |  | 2.5 | [13 empty] | NM | N | PVP-2500 | 2007-11-19 | 2007-11-26 | 3 | 2007-11-26 | [14 empty] | 2007-11-19 | 2007-12-14 |  | Y
Central Hudson |  | Sun Mountain | CH-09086 | Kingston | Saugerties | Ulster | 12477 | G | 3014 | Woodstock | N |  | 3 | [13 empty] | NM | N | GT-3.0 | 2007-11-20 | 2007-11-26 | 2 | 2007-11-26 | [14 empty] | 2008-05-23 | 2008-06-03 |  | Y
Central Hudson |  | Hudson Solar | CH-01874 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7052 | Rhinebeck | N |  | 2.7 | [13 empty] | NM | N | SPR-3300x | 2007-11-26 | 2007-11-26 | 0 | 2007-11-26 | [14 empty] | 2008-04-29 | 2008-04-29 |  | Y
Central Hudson |  | Hudson Solar | CH-02379 | Fishkill | Cold Spg | Putnam | 10516 | G | 8066 | Merritt Park | N |  | 4 | [13 empty] | NM | N | SPR-4000x | 2007-11-29 | 2007-12-03 | 2 | 2007-12-03 | [14 empty] | 2008-03-18 | 2008-04-02 |  | Y
Central Hudson |  | Hudson Solar | CH-01478 | Kingston | Saugerties | Ulster | 12477 | G | 3003 | Saugerties | N |  | 7 | [13 empty] | NM | N | SPR-7000m | 2007-11-30 | 2007-12-03 | 1 | 2007-12-03 | [14 empty] | 2008-04-25 | 2008-04-29 |  | Y
Central Hudson |  | Hudson Solar | CH-01534 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7062 | Milan | N | CH-01534 | 9 | [13 empty] | NM | N | SPR-4000x and SPR-5000x | 2007-11-30 | 2007-12-03 | 1 | 2007-12-03 | [14 empty] | 2008-04-10 | 2008-04-14 |  | Y
Central Hudson |  | Hudson Solar | CH-01662 | Kingston | W Hurley | Ulster | 12491 | G | 2094 | Hurley Ave | N | CH-01662 | 4 | [13 empty] | NM | N | SPR-4000x | 2007-11-30 | 2007-12-03 | 1 | 2007-12-03 | [14 empty] | 2008-08-09 | 2008-08-11 |  | Y
Central Hudson |  | Hudson Solar | CH-02181 | Fishkill | Cold Spg | Putnam | 10516 | G | 8087 | Tioronda | N | CH-02181 | 5.85 | [13 empty] | NM | N | SPR-3300x | 2007-11-30 | 2007-12-03 | 1 | 2007-12-03 | [14 empty] | 2008-08-05 | 2008-08-06 |  | Y
Central Hudson |  | Hudson Solar | CH-02237 | Kingston | Bearsvl | Ulster | 12409 | G | 3012 | Woodstock | N |  | 5.2 | [13 empty] | NM | N | SPR-5000x | 2007-11-30 | 2007-12-03 | 1 | 2007-12-03 | [14 empty] | 2009-01-12 | 2009-01-19 |  | Y
Central Hudson |  | Hudson Solar | CH-02192 | Newburgh | New Paltz | Ulster | 12561 | G | 5011 | Modena | N |  | 6.6 | [13 empty] | NM | N | SPR-3300x | 2007-12-03 | 2007-12-04 | 1 | 2007-12-04 | [14 empty] | 2008-08-26 | 2008-08-28 |  | Y
Central Hudson |  | Hudson Solar | CH-01506 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8051 | North Chelsea | N |  | 4.725 | [13 empty] | NM | N | SPR-5000x | 2007-12-11 | 2007-12-18 | 5 | 2007-12-18 | [14 empty] | 2008-06-26 | 2008-07-02 |  | Y
Central Hudson |  | Hudson Solar | CH-01518 | Newburgh | Highland Mills | Orange | 10930 | G | 4041 | Union Ave | N |  | 5 | [13 empty] | NM | N | SPR-5000x | 2007-12-11 | 2007-12-11 | 0 | 2007-12-11 | [14 empty] | 2008-07-18 | 2008-07-22 |  | Y
Central Hudson |  | Hudson Solar | CH-01844 | Poughkeepsie | Red Hook |  | 12571 | G | 7061 | Milan | TBD |  | 6.6 | [13 empty] | NM | N | SPR-3300x | 2007-12-11 | 2007-12-11 | 0 | 2007-12-11 | [17 empty] | W |  | 5/21/12 Per customer email, this installation has been abandoned.
Central Hudson |  | Hudson Solar | CH-01997 | Newburgh | Newburgh | Orange | 12550 | G | 406 | Montgomery St | N |  | 10.82 | [13 empty] | NM | N | GT-3.3 | 2007-12-11 | 2007-12-14 | 3 | 2007-12-14 | [14 empty] | 2008-03-10 | 2008-03-17 |  | Y
Central Hudson |  | Hudson Solar | CH-02317 | Newburgh | New Paltz | Ulster | 12561 | G | 5011 | Modena | N |  | 4.725 | [13 empty] | NM | N | SPR-5000x | 2007-12-14 | 2007-12-17 | 1 | 2007-12-17 | [14 empty] | 2008-06-17 | 2008-06-20 |  | Y
Central Hudson |  | Hudson Solar | CH-01771 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7055 | Rhinebeck | N |  | 4 | [13 empty] | NM | N | SPR-4000x | 2007-12-21 | 2007-12-27 | 2 | 2007-12-27 | [14 empty] | 2008-06-03 | 2008-06-03 |  | Y
Central Hudson |  | Hudson Solar | CH-01681 | Kingston | Kingston | Ulster | 12401 | G | 1022 | East Kingston | N |  | 4 | [13 empty] | NM | N | SPR-4000x | 2008-01-02 | 2008-01-08 | 4 | 2008-01-08 | [14 empty] | 2008-08-09 | 2008-08-15 |  | Y
Central Hudson |  | Hudson Solar | CH-01863 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7062 | Milan | N | CH-01863 | 8 | [13 empty] | NM | N | SPR-4000x | 2008-01-02 | 2008-01-08 | 4 | 2008-01-08 | [14 empty] | 2008-05-01 | 2008-05-05 |  | Y
Central Hudson |  | Hudson Solar | CH-02072 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7053 | Rhinebeck | N | CH-02072 | 4 | [13 empty] | NM | N | SPR-4000x | 2008-01-02 | 2008-01-08 | 4 | 2008-01-08 | [14 empty] | 2008-07-09 | 2008-07-09 |  | Y
Central Hudson |  | Prime Energy Solutions | CH-02933 | Poughkeepsie | Hyde Park |  | 12538 | G | 6074 | East Park | TBD |  | 8 | [13 empty] | NM | N | SB4000US | 2008-01-11 | 2008-01-16 | 3 | 2008-01-16 | [17 empty] | W
Central Hudson |  | Sunnyside Solar | CH-09640 | Newburgh | Wallkill | Ulster | 12589 | G | 4011 | West Balmville | N |  | 4.1 | [13 empty] | NM | N | SB5000US | 2008-01-22 | 2008-01-24 | 2 | 2008-01-24 | [14 empty] | 2008-01-31 | 2008-02-01 |  | Y
Central Hudson |  | Hudson Solar | CH-01215 | Poughkeepsie | Clinton | Dutchess | 12572 | G | 7013 | Hibernia | N | CH-01215 | 2.1 | [13 empty] | NM | N | SPR-3300x | 2008-01-23 | 2008-01-23 | 0 | 2008-01-23 | [14 empty] | 2008-07-29 | 2008-07-30 |  | Y
Central Hudson |  | Hudson Solar | CH-02132 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7052 | Rhinebeck | N |  | 6.6 | [13 empty] | NM | N | SPR-3300x | 2008-01-23 | 2008-01-23 | 0 | 2008-01-23 | [14 empty] | 2008-06-26 | 2008-06-26 |  | Y
Central Hudson |  | Hudson Solar | CH-01391 | Poughkeepsie | Poughkeepsie | Dutchess | 12604 | G | 6003 | Reynolds Hill | N |  | 7 | [13 empty] | NM | N | SB3000US and SB4000US (208) | 2008-01-24 | 2008-01-31 | 5 | 2008-01-31 | [14 empty] | 2008-05-14 | 2008-05-16 |  | Y
Central Hudson |  | Solar Design Associates | CH-09010 | Poughkeepsie | Lagrangevl | Dutchess | 12540 | G | 6053 | Todd Hill | N |  | 41.4 | [13 empty] | NM | N | PVI-13, PVI-15 | 2008-01-31 | 2008-02-06 | 4 | 2008-02-06 | [14 empty] | 2008-08-01 | 2008-08-15 |  | Y
Central Hudson |  | Solar Design Associates | CH-09011 | Newburgh | New Windsor | Orange | 12553 | G | 4094 | Bethlehem Rd | N |  | 41.4 | [13 empty] | NM | N | PVI-13, PVI-15 | 2008-01-31 | 2008-02-06 | 4 | 2008-02-06 | [14 empty] | 2008-08-01 | 2008-08-15 |  | Y
Central Hudson |  | Solar Design Associates | CH-09012 | Newburgh | New Windsor |  | 12553 | G | 4094 | Bethlehem Rd | TBD |  | 41.4 | [13 empty] | NM | N | PVI-13, PVI-15 | 2008-01-31 | 2008-02-06 | 4 | 2008-02-06 | [15 empty] | 2008-08-15 |  | W |  | SC14 customer switched to commercial NM after 2/09; CH performed SIR test.
Central Hudson |  | SunDog Solar | CH-09152 | Newburgh | New Paltz | Ulster | 12561 | G | 5023 | Ohioville | N |  | 5.1 | [13 empty] | NM | N | SMA SB6000U | 2008-02-28 | 2008-03-06 | 5 | 2008-03-06 | [14 empty] | 2008-03-07 | 2008-03-13 |  | Y
Central Hudson |  | Solar Generation | CH-08263 | Kingston | W Hurley | Ulster | 12491 | G | 2094 | Hurley Ave | N |  | 3.9 | [13 empty] | NM | N | Fronius IG 4000 | 2008-02-01 | 2008-02-08 | 5 | 2008-02-08 | [14 empty] | 2008-05-05 | 2008-05-09 |  | Y
Central Hudson |  | Hudson Solar | CH-02392 | Newburgh | New Windsor | Orange | 12553 | G | 4095 | Bethlehem Rd | N |  | 6.6 | [13 empty] | NM | N | SPR-3300x | 2009-06-01 | 2009-06-01 | 0 | 2009-06-01 | [14 empty] | 2009-12-02 | 2009-12-03 |  | Y
Central Hudson |  | Hudson Solar | CH-01562 | Kingston | Saugerties | Ulster | 12477 | G | 2016 | Lincoln Park | N |  | 4 | [13 empty] | NM | N | SPR-4000x | 2008-02-08 | 2008-02-12 | 2 | 2008-02-12 | [14 empty] | 2008-06-23 | 2008-06-24 |  | Y
Central Hudson |  | Hudson Solar | CH-01647 | Kingston | Olive Brdg | Ulster | 12461 | G | 3024 | High Falls | N |  | 3.3 | [13 empty] | NM | N | SPR-3300x | 2008-02-08 | 2008-02-12 | 2 | 2008-02-12 | [14 empty] | 2008-07-08 | 2008-07-09 |  | Y
Central Hudson |  | Hudson Solar | CH-02069 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6091 | Manchester | N |  | 8 | [13 empty] | NM | N | SPR-4000x | 2008-02-08 | 2008-02-12 | 2 | 2008-02-12 | [14 empty] | 2008-07-18 | 2008-07-21 |  | Y
Central Hudson |  | Hudson Solar | CH-02363 | Kingston | High Fls | Ulster | 12440 | G | 3022 | High Falls | N | CH-02363 | 3 | [13 empty] | NM | N | SPR-3300x | 2008-02-08 | 2008-02-12 | 2 | 2008-02-12 | [14 empty] | 2008-08-09 | 2008-08-19 |  | Y
Central Hudson |  | Hudson Solar | CH-02043 | Kingston | Hurley | Ulster | 12443 | G | 2094 | Hurley Ave | N |  | 6.948 | [13 empty] | NM | N | SB4000US | 2008-02-15 | 2008-02-19 | 1 | 2008-02-19 | [14 empty] | 2008-05-23 | 2008-06-03 |  | Y
Central Hudson |  | Hudson Solar | CH-01937 | Newburgh | New Paltz | Ulster | 12561 | G | 5031 | Galeville | N | CH-01937 | 5 | [13 empty] | NM | N | SPR-5000x | 2008-02-28 | 2008-02-28 | 0 | 2008-02-28 | [14 empty] | 2008-07-23 | 2008-07-24 |  | Y
Central Hudson |  | Hudson Solar | CH-01950 | Newburgh | New Paltz | Ulster | 12561 | G | 5024 | Ohioville | N |  | 4 | [13 empty] | NM | N | SPR-4000x | 2008-02-29 | 2008-03-03 | 1 | 2008-03-03 | [14 empty] | 2008-07-23 | 2008-07-24 |  | Y
Central Hudson |  | Hudson Solar | CH-01604 | Catskill | Round Top | Greene | 12473 | G | 2042 | South Cairo | N | CH-01604 | 4 | [13 empty] | NM | N | 1 SunPower SPR-4000x (240V) SPR-4000x | 2008-03-13 | 2008-03-13 | 0 | 2008-03-13 | [14 empty] | 2008-08-09 | 2008-10-07 |  | Y
Central Hudson |  | Hudson Solar | CH-01406 | Newburgh | New Paltz | Ulster | 12561 | G | 5031 | Galeville | N |  | 6.3 | [13 empty] | NM | N | SPR-3300x | 2008-03-14 | 2008-03-14 | 0 | 2008-03-14 | [14 empty] | 2008-08-01 | 2008-08-04 |  | Y
Central Hudson |  | Hudson Solar | CH-01576 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8093 | Fishkill Plains | N |  | 8.775 | [13 empty] | NM | N | SPR-4000x and SPR-5000x | 2008-03-14 | 2008-03-14 | 0 | 2008-03-14 | [14 empty] | 2008-08-05 | 2008-08-06 |  | Y
Central Hudson |  | Hudson Solar | CH-01946 | Newburgh | New Paltz | Ulster | 12561 | G | 5031 | Galeville | N | CH-01946 | 10 | [13 empty] | NM | N | SPR-5000x2SunPowerSPR-5000x | 2008-03-14 | 2008-03-14 | 0 | 2008-03-14 | [14 empty] | 2008-09-09 | 2008-09-12 |  | Y
Central Hudson |  | Hudson Solar | CH-01967 | Newburgh | Marlboro | Ulster | 12542 | G | 5004 | Marlboro | N |  | 5 | [13 empty] | NM | N | SPR-5000x | 2008-03-14 | 2008-03-14 | 0 | 2008-03-14 | [14 empty] | 2008-08-09 | 2008-08-11 |  | Y
Central Hudson |  | Hudson Solar | CH-02259 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 6074 | East Park | N |  | 3.6 | [13 empty] | NM | N | SPR-3300f | 2008-03-14 | 2008-03-14 | 0 | 2008-03-14 | [14 empty] | 2009-08-10 | 2009-08-12 |  | Y
Central Hudson |  | Renewable Power Systems | CH-02962 | Catskill | Rensselaervl | Albany | 12147 | G | 1092 | Westerlo | N |  | 5 | [13 empty] | NM | N | SPR-5000m | 2008-03-14 | 2008-03-14 | 0 | 2008-03-14 | [14 empty] | 2008-05-06 | 2008-05-07 |  | Y
Central Hudson |  | Hudson Solar | CH-01762 | Poughkeepsie | Staatsburgh |  | 12580 | G | 7011 | Hibernia | TBD |  | 10 | [13 empty] | NM | N | SPR-5000x | 2008-03-18 | 2008-03-19 | 1 | 2008-03-19 | [17 empty] | W
Central Hudson |  | Wiley Electronics LLC | CH-09942 | Catskill | Jewett | Greene | 12444 | E | 2389 | Vinegar Hill | N |  | 4.8 | [13 empty] | NM | N | PVP-4800 | 2008-03-24 | 2008-03-26 | 2 | 2008-03-26 | [14 empty] | 2008-06-23 | 2008-06-26 |  | Y
Central Hudson |  | Mercury Solar Systems | CH-02621 | Kingston | Saugerties | Ulster | 12477 | G | 3004 | Saugerties | N |  | 4 | [13 empty] | NM | N | SPR-4000x | 2008-03-28 | 2008-03-31 | 1 | 2008-03-31 | [14 empty] | 2009-03-09 | 2009-03-09 |  | Y
Central Hudson |  | Mercury Solar Systems | CH-02629 | Newburgh | Newburgh | Orange | 12550 | G | 5004 | Marlboro | N |  | 5 | [13 empty] | NM | N | SPR-5000m | 2008-04-18 | 2008-04-25 | 5 | 2008-04-25 | [14 empty] | 2008-06-20 | 2008-06-20 |  | Y
Central Hudson |  | Solar Generation | CH-08135 | Kingston | Saugerties | Ulster | 12477 | G | 3003 | Saugerties | N |  | 5.46 | [13 empty] | NM | N | SB6000US | 2008-04-18 | 2008-04-25 | 5 | 2008-04-25 | [14 empty] | 2008-08-11 | 2008-08-15 |  | Y
Central Hudson |  | Wiley Electronics LLC | CH-09940 | Kingston | Saugerties | Ulster | 12477 | G | 3001 | Saugerties | N |  | 4.8 | [13 empty] | NM | N | PVP4800 | 2008-04-21 | 2008-04-25 | 4 | 2008-04-25 | [14 empty] | 2008-08-11 | 2008-08-15 |  | Y
Central Hudson |  | 1st Light Energy | CH-00584 | Newburgh | New Windsor | Orange | 12553 | G | 4046 | Union Ave | N |  | 3.2 | [13 empty] | NM | N | SB4000US | 2008-04-28 | 2008-04-29 | 1 | 2008-04-29 | [14 empty] | 2008-05-30 | 2008-06-03 |  | Y
Central Hudson |  | Hudson Solar | CH-01969 | Newburgh | Marlboro | Ulster | 12542 | G | 5003 | Marlboro | N | CH-01969 | 7.3 | [13 empty] | NM | N | SPR-3300x and SPR-4000x | 2008-05-09 | 2008-05-09 | 0 | 2008-05-09 | [14 empty] | 2008-08-09 | 2008-08-11 |  | Y
Central Hudson |  | Sun Mountain | CH-09095 | Kingston | Kingston | Ulster | 12401 | G | 2094 | Hurley Ave | N |  | 9.6 | [13 empty] | NM | N | SB5000US | 2008-05-16 | 2008-05-20 | 2 | 2008-05-20 | [14 empty] | 2008-08-15 | 2008-08-19 |  | W
Central Hudson |  | RGS Energy | CH-03013 | Catskill | E Durham | Greene | 12423 | G | 1092 | Westerlo | N |  | 4 | [13 empty] | NM | N | SPR-4000m | 2008-05-19 | 2008-05-20 | 1 | 2008-05-20 | [14 empty] | 2010-03-31 | 2010-04-01 |  | Y
Central Hudson |  | Hudson Solar | CH-02329 | Newburgh | Wallkill | Ulster | 12589 | G | 5042 | East Walden | N |  | 5.85 | [13 empty] | NM | N | SPR-3300x | 2008-05-27 | 2008-06-03 | 5 | 2008-06-03 | [14 empty] | 2008-08-09 | 2008-08-11 |  | Y
Central Hudson |  | Renewable Power Systems | CH-02963 | Catskill | Catskill | Greene | 12414 | G | 2006 | North Catskill | N |  | 10 | [13 empty] | NM | N | SPR-5000m | 2008-05-30 | 2008-06-03 | 2 | 2008-06-03 | [14 empty] | 2008-12-15 | 2008-12-18 |  | Y
Central Hudson |  | The Solar Center | CH-09712 | Newburgh | Milton | Ulster | 12547 | G | 5002 | Marlboro | N |  | 4.32 | [13 empty] | NM | N | Beacon M4 Plus | 2008-06-06 | 2008-06-09 | 1 | 2008-06-09 | [14 empty] | 2010-06-16 | 2010-06-16 |  | Y
Central Hudson |  | T-KAR Smart Energy Systems | CH-09723 | Fishkill | Cold Spg | Putnam | 10516 | G | 8087 | Tioronda | N | CH-09723 | 5 | [13 empty] | NM | N | SB5000US | 2008-06-02 | 2008-06-09 | 5 | 2008-06-09 | [14 empty] | 2008-12-23 | 2008-12-23 |  | Y
Central Hudson |  | Solar Generation | CH-08188 | Kingston | Saugerties | Ulster | 12477 | G | 3002 | Saugerties | N |  | 4.68 | [13 empty] | NM | N | SB5000US | 2008-06-04 | 2008-06-09 | 3 | 2008-06-09 | [14 empty] | 2008-09-10 | 2008-09-12 |  | Y
Central Hudson |  | Damiani and Sun Inc. | CH-00823 | Kingston | Saugerties | Ulster | 12477 | G | 1021 | East Kingston | N | CH-00823 | 10 | [13 empty] | NM | N | SB6000US | 2008-06-09 | 2008-06-10 | 1 | 2008-06-10 | [14 empty] | 2008-08-25 | 2008-08-28 |  | Y
Central Hudson |  | Solar Generation | CH-08102 | Kingston | Kingston | Ulster | 12401 | G | 2016 | Lincoln Park | N | CH-08102 | 5.6 | [13 empty] | NM | N | SB6000US | 2008-06-09 | 2008-06-10 | 1 | 2008-06-10 | [14 empty] | 2009-01-29 | 2009-01-29 |  | Y
Central Hudson |  | Solar Generation | CH-08149 | Kingston | W Hurley | Ulster | 12491 | G | 2094 | Hurley Ave | N | CH-08149 | 4 | [13 empty] | NM | N | SB4000US | 2008-06-09 | 2008-06-10 | 1 | 2008-06-10 | [14 empty] | 2008-09-02 | 2008-09-05 |  | Y
Central Hudson |  | Solar Generation | CH-08246 | Kingston | Saugerties | Ulster | 12477 | G | 2015 | Lincoln Park | N |  | 4 | [13 empty] | NM | N | SB4000US | 2008-06-09 | 2008-06-10 | 1 | 2008-06-10 | [14 empty] | 2008-09-02 | 2008-09-03 |  | Y
Central Hudson |  | Sun Mountain | CH-09123 | Kingston | Lk Hill | Ulster | 12448 | G | 3012 | Woodstock | N |  | 7 | [13 empty] | NM | N | SB7000US | 2008-06-09 | 2008-06-12 | 3 | 2008-06-12 | [14 empty] | 2008-11-11 | 2008-11-11 |  | Y
Central Hudson |  | Hudson Solar | CH-01522 | Newburgh | Gardiner |  | 12525 | G | 5011 | Modena | TBD |  | 14 | [13 empty] | NM | N | SPR-5000x and SPR-4000x | 2011-11-14 | 2008-06-12 | -859 | 2008-06-12 | [14 empty] | 2012-05-18 |  |  | W |  | per HVCE on 3/16/09 customer is not installing system
Central Hudson |  | 1st Light Energy | CH-00579 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8093 | Fishkill Plains | N | CH-00579 | 4 | [13 empty] | NM | N | SB4000US | 2008-07-07 | 2008-07-07 | 0 | 2008-07-07 | [14 empty] | 2008-07-10 | 2008-07-14 |  | Y
Central Hudson |  | Hudson Solar | CH-01292 | Kingston | Stone Ridge | Ulster | 12484 | G | 3023 | High Falls | N |  | 30 | [13 empty] | NM | N | SPR-5000x | 2008-07-24 | 2008-07-30 | 4 | 2008-07-30 |  |  |  | 2008-07-24 | 2008-07-29 | 2008-08-20 | 16 | 350 | [6 empty] | 2008-11-24 | 2008-12-01 |  | Y
Central Hudson |  | Hudson Solar | CH-01241 | Kingston | Saugerties | Ulster | 12477 | G | 3003 | Saugerties | N | CH-01241 | 5 | [13 empty] | NM | N | SPR-5000x | 2008-07-07 | 2008-07-09 | 2 | 2008-07-09 | [14 empty] | 2008-08-11 | 2008-08-12 |  | Y
Central Hudson |  | Hudson Solar | CH-01780 | Poughkeepsie | Lagrangeville |  | 12540 | G | 6055 | Todd Hill | TBD |  | 5 | [13 empty] | NM | N | SPR-5000x | 2008-07-07 | 2008-07-08 | 1 | 2008-07-08 | [17 empty] | W |  | This project has been abandoned per the customers email 5/22/12.
Central Hudson |  | Hudson Solar | CH-01913 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8046 | Myers Corners | N | CH-01913 | 5 | [13 empty] | NM | N | SPR-5000x | 2008-07-07 | 2008-07-08 | 1 | 2008-07-08 | [14 empty] | 2008-09-04 | 2008-09-12 |  | Y
Central Hudson |  | Hudson Solar | CH-01979 | Newburgh | Wallkill | Ulster | 12589 | G | 5043 | East Walden | N |  | 3.3 | [13 empty] | NM | N | SPR-3300x | 2008-07-07 | 2008-07-08 | 1 | 2008-07-08 | [14 empty] | 2008-10-06 | 2008-10-14 |  | Y
Central Hudson |  | Hudson Solar | CH-02033 | Kingston | Woodstock | Ulster | 12498 | G | 3013 | Woodstock | N |  | 4 | [13 empty] | NM | N | SPR-4000x | 2008-07-07 | 2008-07-08 | 1 | 2008-07-08 | [14 empty] | 2008-09-30 | 2008-10-03 |  | W
Central Hudson |  | Hudson Solar | CH-02150 | Poughkeepsie | Tivoli | Dutchess | 12583 | G | 7062 | Milan | N |  | 3.3 | [13 empty] | NM | N | SPR-3300x | 2008-07-07 | 2008-07-08 | 1 | 2008-07-08 | [14 empty] | 2009-01-09 | 2009-01-14 |  | Y
Central Hudson |  | Hudson Solar | CH-02290 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7061 | Milan | N |  | 10 | [13 empty] | NM | N | SPR-5000x | 2008-07-07 | 2008-07-08 | 1 | 2008-07-08 | [14 empty] | 2008-10-01 | 2008-10-07 |  | Y
Central Hudson |  | Hudson Solar | CH-01244 | Poughkeepsie | Millerton | Dutchess | 12546 | G | 7081 | Millerton | N |  | 3.3 | [13 empty] | NM | N | SPR-3300x | 2008-07-11 | 2008-07-16 | 3 | 2008-07-16 | [14 empty] | 2008-10-01 | 2008-10-07 |  | Y
Central Hudson |  | Hudson Solar | CH-01878 | Poughkeepsie | Pine Plns | Dutchess | 12567 | G | 7085 | Ancram | N |  | 10 | [13 empty] | NM | N | SPR-5000x | 2008-07-11 | 2008-07-18 | 5 | 2008-07-18 | [14 empty] | 2009-02-17 | 2009-02-17 |  | Y
Central Hudson |  | Hudson Solar | CH-01289 | Kingston | Woodstock | Ulster | 12498 | G | 3012 | Woodstock | N |  | 10.5 | [13 empty] | NM | N | SPR-4000x and SPR-3300x | 2008-07-14 | 2008-07-16 | 2 | 2008-07-16 | [14 empty] | 2009-03-18 | 2009-03-18 |  | Y
Central Hudson |  | Quad State Solar, Inc. | CH-02948 | Fishkill | Cold Spg | Putnam | 10516 | G | 8063 | Merritt Park | N |  | 4 | [13 empty] | NM | N | SPR-4000x | 2008-07-15 | 2008-07-21 | 4 | 2008-07-21 | [14 empty] | 2008-12-02 | 2008-12-02 |  | Y
Central Hudson |  | Sun Mountain | CH-09116 | Kingston | West Shokan | Ulster | 12494 | G | 3011 | Woodstock | N |  | 2.4 | [13 empty] | NM | N | GT-2.8 | 2008-07-15 | 2008-07-18 | 3 | 2008-07-18 | [14 empty] | 2008-11-28 | 2008-12-09 |  | Y
Central Hudson |  | Hudson Solar | CH-01375 | Poughkeepsie | Staatsburg | Dutchess | 12580 | G | 7041 | Staatsburg | N |  | 19 | [13 empty] | NM | N | SPR-5000x, SPR-4000x | 2008-08-14 | 2008-08-21 | 5 | 2008-08-21 |  |  |  | 2008-08-14 | 2008-08-14 | 2008-08-21 | 5 | 350 | [6 empty] | 2008-10-06 | 2008-10-10 |  | Y
Central Hudson |  | Hudson Solar | CH-01985 | Newburgh | Gardiner | Ulster | 12525 | G | 5011 | Modena | N | CH-01985 | 13 | [13 empty] | NM | N | SPR-5000x and SPR-4000x | 2008-07-21 | 2008-07-24 | 3 | 2008-07-24 | [14 empty] | 2008-12-23 | 2008-12-29 |  | Y
Central Hudson |  | Hudson Solar | CH-02288 | Poughkeepsie | Ancram | Columbia | 12502 | G | 7085 | Ancram | N |  | 5 | [13 empty] | NM | N | SPR-5000x | 2008-07-21 | 2008-07-24 | 3 | 2008-07-24 | [14 empty] | 2009-01-19 | 2009-01-20 |  | Y
Central Hudson |  | Cramer Electrical | CH-00812 | Catskill | Coxsackie |  | 12051 | G | 1072 | Coxsackie | TBD |  | 4.7 | [13 empty] | NA | N | Ecopower Micro CHP | 2008-08-26 | 2008-08-28 | 2 | 2008-08-28 | [15 empty] | 2009-01-29 |  | W |  | application held by request of customer until Marathon system was added to PSC-certified list. Electrician sent revised one-line diagram on 8/26/08. CH performed SIR test. 3/18/2010 - No longer has this system - MT Abandoned. Set up with electronic meter
Central Hudson |  | Solar Generation | CH-08095 | Kingston | Saugerties | Ulster | 12477 | G | 3002 | Saugerties | N |  | 4 | [13 empty] | NM | N | SB4000US | 2008-07-22 | 2008-07-25 | 3 | 2008-07-25 | [14 empty] | 2008-11-13 | 2008-12-08 |  | Y
Central Hudson |  | Solar Generation | CH-08187 | Kingston | Saugerties | Ulster | 12477 | G | 3002 | Saugerties | N |  | 4 | [13 empty] | NM | N | SB4000US | 2008-07-22 | 2008-07-25 | 3 | 2008-07-25 | [14 empty] | 2008-11-13 | 2008-12-08 |  | Y
Central Hudson |  | Hudson Solar | CH-01593 | Catskill | Catskill | Greene | 12414 | G | 2001 | North Catskill | N |  | 9 | [13 empty] | NM | N | SPR-5000x and SPR-4000x | 2008-07-25 | 2008-07-28 | 1 | 2008-07-28 | [14 empty] | 2009-04-01 | 2009-04-01 |  | Y
Central Hudson |  | Hudson Solar | CH-01931 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8093 | Fishkill Plains | N | CH-01931 | 8 | [13 empty] | NM | N | SPR-4000x | 2008-07-25 | 2008-07-28 | 1 | 2008-07-28 | [14 empty] | 2009-02-25 | 2009-02-25 |  | Y
Central Hudson |  | Hudson Solar | CH-02093 | Poughkeepsie | Millbrook | Dutchess | 12545 | G | 6057 | Todd Hill | N |  | 5 | [13 empty] | NM | N | SPR-5000x | 2008-07-25 | 2008-07-29 | 2 | 2008-07-29 | [14 empty] | 2009-02-11 | 2009-02-11 |  | Y
Central Hudson |  | groSolar | CH-01187 | Catskill | Westerlo | Albany | 12193 | G | 1091 | Westerlo | N |  | 4 | [13 empty] | NM | N | IG 2000 | 2008-07-28 | 2008-07-29 | 1 | 2008-07-29 | [14 empty] | 2009-02-26 | 2009-02-26 |  | Y
Central Hudson |  | Sun Mountain | CH-09094 | Kingston | Kerhonkson | Ulster | 12446 | G | 3082 | Kerhonkson | N | CH-09094 | 4.8 | [13 empty] | NM | N | SB5000US | 2008-07-29 | 2008-08-05 | 5 | 2008-08-05 | [14 empty] | 2009-02-12 | 2009-02-12 |  | Y
Central Hudson |  | Solar Generation | CH-08247 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6042 | Spackenkill | N |  | 3.9 | [13 empty] | NM | N | SB4000US | 2008-08-04 | 2008-08-05 | 1 | 2008-08-05 | [14 empty] | 2008-10-31 | 2008-12-08 |  | Y
Central Hudson |  | Solar Generation | CH-08248 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6042 | Spackenkill | N |  | 3.9 | [13 empty] | NM | N | SB4000US | 2008-08-04 | 2008-08-05 | 1 | 2008-08-05 | [14 empty] | 2008-12-02 | 2008-12-08 |  | Y
Central Hudson |  | Hudson Solar | CH-01720 | Kingston | Saugerties | Ulster | 12477 | G | 3003 | Saugerties | N |  | 7.875 | [13 empty] | NM | N | SPR-5000x and SPR-3300x | 2008-08-14 | 2008-08-15 | 1 | 2008-08-15 | [14 empty] | 2009-02-13 | 2009-02-13 |  | Y
Central Hudson |  | Hudson Solar | CH-02211 | Newburgh | Gardiner | Ulster | 12525 | G | 5033 | Galeville | N |  | 5 | [13 empty] | NM | N | SPR-5000x | 2008-08-14 | 2008-08-15 | 1 | 2008-08-15 | [14 empty] | 2009-02-05 | 2009-02-05 |  | Y
Central Hudson |  | Hudson Solar | CH-02245 | Kingston | Malden On Hudson | Ulster | 12453 | G | 3004 | Saugerties | N |  | 5 | [13 empty] | NM | N | SPR-5000x | 2008-08-14 | 2008-08-15 | 1 | 2008-08-15 | [14 empty] | 2016-09-06 | 2016-09-07 |  | Y
Central Hudson |  | Hudson Solar | CH-01240 | Newburgh | Gardiner | Ulster | 12525 | G | 5011 | Modena | N |  | 43.2 | [13 empty] | NM | N | GT-5.0 and GT-2.8 | 2008-09-11 | 2008-09-17 | 4 | 2008-09-17 | [14 empty] | 2008-11-18 | 2008-11-18 |  | Y
Central Hudson |  | Hudson Solar | CH-01249 | Newburgh | Gardiner | Ulster | 12525 | G | 5011 | Modena | N |  | 43.2 | [13 empty] | NM | N | GT-5.0 and GT-2.8 | 2008-09-11 | 2008-09-17 | 4 | 2008-09-17 |  |  |  | 2008-09-11 | 2008-09-11 | 2008-09-29 | 12 | 350 | [6 empty] | 2008-12-02 | 2008-12-03 |  | Y
Central Hudson |  | Solar Generation | CH-08115 | Kingston | Hurley | Ulster | 12443 | G | 2094 | Hurley Ave | N | CH-08115 | 4 | [13 empty] | NM | N | SB3000US | 2008-08-15 | 2008-08-20 | 3 | 2008-08-20 | [14 empty] | 2009-04-17 | 2009-04-17 |  | Y
Central Hudson |  | Solar Generation | CH-08169 | Kingston | Woodstock | Ulster | 12498 | G | 3013 | Woodstock | N |  | 3 | [13 empty] | NM | N | SB3000US | 2008-08-15 | 2008-08-19 | 2 | 2008-08-19 | [14 empty] | 2009-03-24 | 2009-03-24 |  | Y
Central Hudson |  | Hudson Solar | CH-01708 | Kingston | Napanoch | Ulster | 12458 | G | 3091 | Neversink | N |  | 5 | [13 empty] | NM | N | SPR-5000x | 2008-08-18 | 2008-08-19 | 1 | 2008-08-19 | [14 empty] | 2009-02-24 | 2009-02-24 |  | Y
Central Hudson |  | Hudson Solar | CH-01928 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8072 | Shenandoah | N |  | 5 | [13 empty] | NM | N | SPR-5000x | 2008-08-18 | 2008-08-19 | 1 | 2008-08-19 | [14 empty] | 2009-05-05 | 2009-05-05 |  | Y
Central Hudson |  | Hudson Solar | CH-01993 | Newburgh | Gardiner | Ulster | 12525 | G | 5011 | Modena | N |  | 23.47 | [13 empty] | NM | N | GT 5.0-240 | 2008-09-11 | 2008-09-17 | 4 | 2008-09-17 | [14 empty] | 2008-12-30 | 2009-01-02 |  | W
Central Hudson |  | Hudson Solar | CH-01994 | Newburgh | Gardiner | Ulster | 12525 | G | 5011 | Modena | N |  | 23.47 | [13 empty] | NM | N | GT 5.0-240 | 2008-09-11 | 2008-09-17 | 4 | 2008-09-17 | [14 empty] | 2008-12-30 | 2009-01-02 |  | W
Central Hudson |  | Hudson Solar | CH-02230 | Kingston | Rosendale | Ulster | 12472 | G | 3022 | High Falls | N |  | 8 | [13 empty] | NM | N | SPR-4000x | 2008-08-18 | 2008-08-19 | 1 | 2008-08-19 | [14 empty] | 2009-03-09 | 2009-03-09 |  | Y
Central Hudson |  | Hudson Solar | CH-02251 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6044 | Spackenkill | N |  | 10 | [13 empty] | NM | N | SPR-5000x | 2008-08-18 | 2008-08-19 | 1 | 2008-08-19 | [14 empty] | 2009-04-21 | 2009-04-21 |  | Y
Central Hudson |  | Hudson Solar | CH-02252 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6042 | Spackenkill | N |  | 4 | [13 empty] | NM | N | SPR-4000x | 2008-08-18 | 2008-08-19 | 1 | 2008-08-19 | [14 empty] | 2009-01-02 | 2009-04-02 |  | Y
Central Hudson |  | Hudson Solar | CH-01371 | Kingston | Kingston | Ulster | 12401 | G | 3023 | High Falls | N |  | 7.56 | [13 empty] | NM | N | SPR-4000x | 2008-08-28 | 2008-09-04 | 4 | 2008-09-04 | [14 empty] | 2010-02-12 | 2010-02-12 |  | Y
Central Hudson |  | Hudson Solar | CH-01504 | Newburgh | Highland |  | 12528 | G | 5022 | Ohioville | TBD |  | 5 | [13 empty] | NM | N | SPR-5000x | 2008-08-28 | 2008-08-28 | 0 | 2008-08-28 | [17 empty] | W |  | 6/1/12 Per customer letter this project has been abandoned.
Central Hudson |  | Hudson Solar | CH-01959 | Newburgh | Newburgh |  | 12550 | G | 4022 | Coldenham | TBD |  | 4 | [13 empty] | NM | N | SPR-4000x | 2008-08-28 | 2008-08-28 | 0 | 2008-08-28 | [17 empty] | W |  | 7/6/12 Installation abandoned as per customer letter.
Central Hudson |  | Hudson Solar | CH-02078 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7013 | Hibernia | N |  | 20 | [13 empty] | NM | N | SPR-5000x | 2008-09-16 | 2008-09-19 | 3 | 2008-09-19 |  |  |  | 2008-09-16 | 2008-09-16 | 2008-10-14 | 19 | 350 | [6 empty] | 2009-01-05 | 2009-01-06 |  | W
Central Hudson |  | Hudson Solar | CH-02199 | Newburgh | New Paltz | Ulster | 12561 | G | 5023 | Ohioville | N |  | 4.725 | [13 empty] | NM | N | SPR-5000x | 2008-08-28 | 2008-08-28 | 0 | 2008-08-28 | [14 empty] | 2009-02-13 | 2009-02-13 |  | Y
Central Hudson |  | Hudson Solar | CH-02242 | Kingston | Kingston | Ulster | 12401 | G | 2093 | Hurley Ave | N |  | 4.725 | [13 empty] | NM | N | SPR-5000x | 2008-08-28 | 2008-09-03 | 3 | 2008-09-03 | [14 empty] | 2009-05-11 | 2009-05-11 |  | Y
Central Hudson |  | Akeena Solar | CH-00643 | Kingston | Kingston | Ulster | 12401 | G | 112 | South Wall St | N | CH-00643 | 2.7 | [13 empty] | NM | N | IG 3000 | 2008-10-14 | 2008-10-15 | 1 | 2008-10-15 | [14 empty] | 2009-01-02 | 2009-01-05 |  | Y
Central Hudson |  | Solar Works | CH-09049 | Newburgh | New Paltz | Ulster | 12561 | G | 5024 | Ohioville | N |  | 5 | [13 empty] | NM | N | SPR-5000m | 2008-09-02 | 2008-09-08 | 4 | 2008-09-08 | [14 empty] | 2008-11-05 | 2008-11-05 |  | Y
Central Hudson |  | Damiani and Sun Inc. | CH-00822 | Newburgh | Campbell Hall | Orange | 10916 | G | 5051 | Maybrook | N |  | 10 | [13 empty] | NM | N | SB6000US, SB4000US | 2008-09-12 | 2008-09-15 | 1 | 2008-09-15 | [14 empty] | 2009-07-17 | 2009-07-21 |  | Y
Central Hudson |  | Hudson Solar | CH-01211 | Kingston | Glenford | Ulster | 12433 | G | 3013 | Woodstock | N |  | 5 | [13 empty] | NM | N | SPR-5000x | 2008-09-12 | 2008-09-12 | 0 | 2008-09-12 | [14 empty] | 2009-02-24 | 2009-02-24 |  | Y
Central Hudson |  | Hudson Solar | CH-01287 | Kingston | Glenford |  | 12433 | G | 3013 | Woodstock | TBD |  | 5 | [13 empty] | NM | N | SPR-5000x | 2008-09-12 | 2008-09-12 | 0 | 2008-09-12 | [15 empty] | 2009-02-24 |  | W |  | Contractor performed SIR test and sent documentation 2/24/2009.
Central Hudson |  | Hudson Solar | CH-01376 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7054 | Rhinebeck | N | CH-01376 | 3.78 | [13 empty] | NM | N | SPR-4000x | 2008-09-17 | 2008-09-19 | 2 | 2008-09-19 | [14 empty] | 2008-10-03 | 2008-10-14 |  | Y
Central Hudson |  | Hudson Solar | CH-01529 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7041 | Staatsburg | N |  | 3.87 | [13 empty] | NM | N | SPR-4000x | 2008-09-19 | 2008-09-24 | 3 | 2008-09-24 | [14 empty] | 2009-01-07 | 2009-01-15 |  | Y
Central Hudson |  | Hudson Solar | CH-01688 | Kingston | Woodstock | Ulster | 12498 | G | 3012 | Woodstock | N |  | 6.6 | [13 empty] | NM | N | SPR-3300x | 2008-09-19 | 2008-09-22 | 1 | 2008-09-22 | [14 empty] | 2009-03-18 | 2009-03-18 |  | Y
Central Hudson |  | Hudson Solar | CH-02197 | Newburgh | Highland | Ulster | 12528 | G | 5022 | Ohioville | N |  | 4 | [13 empty] | NM | N | SPR-4000x | 2008-09-19 | 2008-09-22 | 1 | 2008-09-22 | [14 empty] | 2009-04-09 | 2009-04-09 |  | Y
Central Hudson |  | Hudson Solar | CH-02368 | Poughkeepsie | Staatsburg | Dutchess | 12580 | G | 7041 | Staatsburg | N |  | 8 | [13 empty] | NM | N | SPR-4000x | 2008-09-19 | 2008-09-24 | 3 | 2008-09-24 | [14 empty] | 2009-01-07 | 2009-01-15 |  | Y
Central Hudson |  | Solar Generation | CH-08064 | Kingston | High Fls | Ulster | 12440 | G | 3022 | High Falls | N | CH-08064 | 6 | [13 empty] | NM | N | SB5000US1SMASB6.0-1SP-US-41 | 2008-09-19 | 2008-09-22 | 1 | 2008-09-22 | [14 empty] | 2009-03-16 | 2009-03-16 |  | Y
Central Hudson |  | Solar Generation | CH-08163 | Kingston | Bearsvl | Ulster | 12409 | G | 3012 | Woodstock | N |  | 3 | [13 empty] | NM | N | SB3000US | 2008-09-19 | 2008-09-24 | 3 | 2008-09-24 | [14 empty] | 2009-02-05 | 2009-02-17 |  | Y
Central Hudson |  | SunDog Solar | CH-09140 | Catskill | Freehold |  | 12431 | G | 2071 | Freehold | TBD |  | 4.8 | [13 empty] | NM | N | SB5000US | 2008-09-22 | 2008-09-29 | 5 | 2008-09-29 | [17 empty] | W
Central Hudson |  | SunDog Solar | CH-09150 | Poughkeepsie | Ancramdale | Columbia | 12503 | G | 7092 | Pulvers Corners | N |  | 5.25 | [13 empty] | NM | N | SB6000US | 2008-09-22 | 2008-09-29 | 5 | 2008-09-29 | [14 empty] | 2009-05-21 | 2009-05-27 |  | Y
Central Hudson |  | SunDog Solar | CH-09164 | Catskill | Westerlo | Albany | 12193 | G | 1091 | Westerlo | N |  | 5.25 | [13 empty] | NM | N | GVFX3648 | 2008-10-24 | 2008-10-28 | 2 | 2008-10-28 | [14 empty] | 2009-08-07 | 2009-08-10 |  | W
Central Hudson |  | Hudson Solar | CH-01622 | Catskill | Leeds | Greene | 12451 | G | 2071 | Freehold | N |  | 10 | [13 empty] | NM | N | SPR-5000x | 2008-09-26 | 2008-09-30 | 2 | 2008-09-30 | [14 empty] | 2009-04-06 | 2009-04-06 |  | Y
Central Hudson |  | Hudson Solar | CH-02498 | Newburgh | Marlboro | Ulster | 12542 | G | 5003 | Marlboro | N | CH-01384 | 9.3 | [13 empty] | NM | N | SPR-3300x | 2008-09-26 | 2008-09-30 | 2 | 2008-09-30 | [14 empty] | 2008-12-30 | 2009-01-02 |  | Y
Central Hudson |  | Hudson Solar | CH-01573 | Newburgh | New Paltz | Ulster | 12561 | G | 5023 | Ohioville | N |  | 8 | [13 empty] | NM | N | (2) SPR-4000x | 2008-09-29 | 2008-10-06 | 5 | 2008-10-06 | [14 empty] | 2009-06-04 | 2009-06-04 |  | Y
Central Hudson |  | Hudson Solar | CH-02170 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8095 | Fishkill Plains | N | CH-02170 | 10 | [13 empty] | NM | N | SPR-5000x | 2008-09-29 | 2008-10-02 | 3 | 2008-10-02 | [14 empty] | 2009-02-25 | 2009-02-25 |  | Y
Central Hudson |  | RGS Energy | CH-03022 | Catskill | W Coxsackie | Greene | 12192 | G | 1071 | Coxsackie | N |  | 7.2 | [13 empty] | NM | N | SPR-7000m | 2008-10-01 | 2008-10-08 | 5 | 2008-10-08 | [14 empty] | 2009-06-05 | 2009-06-08 |  | Y
Central Hudson |  | Hudson Solar | CH-02244 | Kingston | Saugerties | Ulster | 12477 | G | 3004 | Saugerties | N |  | 19 | [13 empty] | NM | N | SPR-4000x | 2008-10-24 | 2008-10-27 | 1 | 2008-10-27 | [14 empty] | 2009-12-29 | 2010-01-05 |  | Y
Central Hudson |  | Hudson Solar | CH-01433 | Poughkeepsie | Clinton Corners | Dutchess | 12514 | G | 7013 | Hibernia | N |  | 3.78 | [13 empty] | NM | N | SPR-4000x | 2008-10-03 | 2008-10-06 | 1 | 2008-10-06 | [14 empty] | 2009-03-16 | 2009-03-16 |  | W
Central Hudson |  | Hudson Solar | CH-01709 | Kingston | Woodbourne | Sullivan | 12788 | G | 3091 | Neversink | N |  | 10 | [13 empty] | NM | N | SPR-5000x | 2008-10-03 | 2008-10-06 | 1 | 2008-10-06 | [14 empty] | 2009-05-20 | 2009-05-28 |  | Y
Central Hudson |  | Hudson Solar | CH-02036 | Kingston | Mount Tremper | Ulster | 12457 | G | 3012 | Woodstock | N |  | 7.3 | [13 empty] | NM | N | SPR-4000x, SPR-3300x | 2008-10-03 | 2008-10-06 | 1 | 2008-10-06 | [14 empty] | 2009-11-30 | 2009-11-30 |  | Y
Central Hudson |  | Hudson Solar | CH-02138 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7062 | Milan | N |  | 5.98 | [13 empty] | NM | N | SB4000US, SB3000US | 2008-10-03 | 2008-10-06 | 1 | 2008-10-06 | [14 empty] | 2009-04-20 | 2009-04-20 |  | Y
Central Hudson |  | Hudson Solar | CH-02293 | Poughkeepsie | Stanfordvl | Dutchess | 12581 | G | 7072 | Stanfordville | N | CH-02293 | 10 | [13 empty] | NM | N | SPR-5000x | 2008-10-03 | 2008-10-06 | 1 | 2008-10-06 | [14 empty] | 2009-06-03 | 2009-06-09 |  | Y
Central Hudson |  | Renewable Power Systems | CH-02958 | Catskill | Coeymans | Albany | 12045 | G | 1081 | New Baltimore | N |  | 6 | [13 empty] | NM | N | SPR-6000m | 2008-10-06 | 2008-10-10 | 4 | 2008-10-10 | [14 empty] | 2009-01-19 | 2009-01-22 |  | Y
Central Hudson |  | Renewable Power Systems | CH-02959 | Catskill | Greenvl | Greene | 12083 | G | 2061 | Freehold | N |  | 5 | [13 empty] | NM | N | SPR5000M | 2008-10-06 | 2008-10-10 | 4 | 2008-10-10 | [14 empty] | 2009-01-19 | 2009-01-19 |  | Y
Central Hudson |  | Hudson Solar | CH-02281 | Poughkeepsie | Milan | Dutchess | 12571 | G | 7062 | Milan | N |  | 3.78 | [13 empty] | NM | N | (1) SPR-4000m | 2008-10-15 | 2008-10-20 | 3 | 2008-10-20 | [14 empty] | 2009-04-02 | 2009-04-02 |  | Y
Central Hudson |  | Green in Greene | CH-01166 | Catskill | Earlton |  | 12058 | G | 1071 | Coxsackie | TBD |  | 1.8 |  | 3.6 | [11 empty] | NM | N | Southwest Windpower Skystream 3.7 | 2008-10-20 | 2008-10-27 | 5 | 2008-10-27 | [17 empty] | W
Central Hudson |  | Hudson Solar | CH-02241 | Kingston | Kingston | Ulster | 12401 | G | 2092 | Hurley Ave | N |  | 11.6 | [13 empty] | NM | N | (2) SPR-3300x & (1) SPR-5000x SPR-5000x | 2008-10-27 | 2008-10-31 | 4 | 2008-10-31 | [14 empty] | 2009-12-16 | 2009-12-18 |  | Y
Central Hudson |  | Solar Works | CH-09053 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6003 | Reynolds Hill | N |  | 5 | [13 empty] | NM | N | Sun Power 5000m | 2008-10-27 | 2008-10-31 | 4 | 2008-10-31 | [14 empty] | 2009-07-24 | 2009-07-24 |  | Y
Central Hudson |  | Hudson Solar | CH-01942 | Newburgh | New Paltz | Ulster | 12561 | G | 5031 | Galeville | N |  | 5 | [13 empty] | NM | N | SPR-5000x | 2008-10-29 | 2008-11-05 | 5 | 2008-11-05 | [14 empty] | 2009-04-24 | 2009-04-24 |  | Y
Central Hudson |  | Hudson Solar | CH-02087 | Poughkeepsie | Staatsburg | Dutchess | 12580 | G | 7041 | Staatsburg | N | CH-02087 | 6 | [13 empty] | NM | N | SPR-6000m | 2008-10-29 | 2008-11-04 | 4 | 2008-11-04 | [14 empty] | 2009-10-14 | 2009-10-15 |  | Y
Central Hudson |  | Hudson Solar | CH-01923 | Fishkill | Beacon | Dutchess | 12508 | G | 8015 | Forgebrook | N | CH-01923 | 4 | [13 empty] | NM | N | SPR-4000m | 2008-10-31 | 2008-11-07 | 5 | 2008-11-07 | [14 empty] | 2009-04-14 | 2009-04-14 |  | Y
Central Hudson |  | Hudson Solar | CH-02258 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 6074 | East Park | N | CH-02258 | 5.6 | [13 empty] | NM | N | SPR-5000x | 2008-10-31 | 2008-11-07 | 5 | 2008-11-07 | [14 empty] | 2009-04-02 | 2009-04-02 |  | Y
Central Hudson |  | Solar Generation | CH-08282 | Kingston | Lake Hill | Ulster | 12448 | G | 3012 | Woodstock | N |  | 4.8 | [13 empty] | NM | N | SB5000US | 2008-10-31 | 2008-11-06 | 4 | 2008-11-06 | [14 empty] | 2009-04-17 | 2009-04-17 |  | Y
Central Hudson |  | Solar Generation | CH-08298 | Kingston | Boicevl | Ulster | 12412 | G | 3011 | Woodstock | N |  | 4.8 | [13 empty] | NM | N | SB5000US | 2008-10-31 | 2008-11-04 | 2 | 2008-11-04 | [14 empty] | 2009-06-22 | 2009-06-23 |  | Y
Central Hudson |  | Hudson Solar | CH-02075 | Poughkeepsie | Clinton Corners | Dutchess | 12514 | G | 7013 | Hibernia | N | CH-02075 | 3.3 | [13 empty] | NM | N | SPR-3300x | 2008-11-04 | 2008-11-07 | 3 | 2008-11-07 | [14 empty] | 2009-11-30 | 2009-12-02 |  | Y
Central Hudson |  | Hudson Solar | CH-01792 | Poughkeepsie | Clinton Corners | Dutchess | 12514 | G | 7071 | Stanfordville | N |  | 5 | [13 empty] | NM | N | SPR-5000x | 2008-11-10 | 2008-11-10 | 0 | 2008-11-10 | [14 empty] | 2009-03-30 | 2009-03-30 |  | Y
Central Hudson |  | Hudson Solar | CH-02049 | Kingston | Napanoch | Ulster | 12458 | G | 3091 | Neversink | N |  | 5 | [13 empty] | NM | N | SPR-5000x | 2008-11-10 | 2008-11-10 | 0 | 2008-11-10 | [14 empty] | 2009-04-13 | 2009-04-13 |  | Y
Central Hudson |  | Hudson Solar | CH-01980 | Newburgh | Gardiner | Ulster | 12525 | G | 5011 | Modena | N |  | 4 | [13 empty] | NM | N | SPR-4000x | 2008-11-13 | 2008-11-13 | 0 | 2008-11-13 | [14 empty] | 2009-04-20 | 2009-04-20 |  | Y
Central Hudson |  | Green in Greene | CH-01167 | Catskill | Greenvl | Greene | 12083 | G | 2061 | Freehold | N |  |  |  | 3.6 | [11 empty] | NM | N | 2-Southwest Windpower Skystream3.7 (Rated continuous output power 1.8kW) | 2008-11-14 | 2008-11-20 | 4 | 2008-11-20 | [14 empty] | 2015-08-31 | 2015-08-31 |  | Y
Central Hudson |  | Hudson Solar | CH-01815 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 7025 | Tinkertown | N |  | 8 | [13 empty] | NM | N | SPR-4000x | 2008-11-20 | 2008-11-21 | 1 | 2008-11-21 | [14 empty] | 2009-04-21 | 2009-04-21 |  | Y
Central Hudson |  | Solar Generation | CH-08157 | Kingston | Accord | Ulster | 12404 | G | 3024 | High Falls | N |  | 4 | [13 empty] | NM | N | SB4000US | 2008-11-24 | 2008-11-24 | 0 | 2008-11-24 | [14 empty] | 2010-01-22 | 2010-01-22 |  | Y
Central Hudson |  | ETM Solar Works | CH-01122 | Catskill | Hannacroix | Greene | 12087 | G | 2061 | Freehold | N |  | 10 | [13 empty] | NM | N | SMA 5000 | 2008-12-01 | 2008-12-03 | 2 | 2008-12-03 | [14 empty] | 2009-07-20 | 2009-07-21 |  | Y
Central Hudson |  | Hudson Solar | CH-01219 | Newburgh | New Paltz |  | 12561 | G | 5021 | Ohioville | TBD |  | 10 | [13 empty] | NM | N | SPR-5000x | 2008-12-01 | 2008-12-02 | 1 | 2008-12-02 | [15 empty] | 2009-03-13 |  | W |  | Contractor performed SIR test and sent documentation 3/13/2009.
Central Hudson |  | Hudson Solar | CH-01412 | Newburgh | New Paltz | Ulster | 12561 | G | 5023 | Ohioville | N |  | 10 | [13 empty] | NM | N | SPR-5000x | 2008-12-01 | 2008-12-02 | 1 | 2008-12-02 | [14 empty] | 2009-03-13 | 2009-03-13 |  | Y
Central Hudson |  | T-KAR Smart Energy Systems | CH-09720 | Newburgh | New Paltz |  | 12561 | G | 5024 | Ohioville | N |  | 18.2 | [13 empty] | NM | N | SB-5000US; SB7000US | 2008-12-16 | 2008-12-18 | 2 | 2008-12-18 | [14 empty] | 2009-06-15 | 2009-06-15 |  | W
Central Hudson |  | Solar Generation | CH-08227 | Kingston | Boicevl | Ulster | 12412 | G | 3011 | Woodstock | N |  | 5 | [13 empty] | NM | N | SB5000US | 2008-12-03 | 2008-12-08 | 3 | 2008-12-08 | [14 empty] | 2010-09-23 | 2010-09-23 |  | Y
Central Hudson |  | Damiani and Sun Inc. | CH-00821 | Newburgh | Mountainvl | Orange | 10953 | G | 4095 | Bethlehem Rd | N | CH-00821 | 6 | [13 empty] | NM | N | SB 6000US | 2008-12-04 | 2008-12-04 | 0 | 2008-12-04 | [14 empty] | 2009-11-23 | 2009-12-02 |  | Y
Central Hudson |  | Hudson Solar | CH-01718 | Kingston | Saugerties |  | 12477 | G | 3003 | Saugerties | TBD |  | 10 | [13 empty] | NM | N | Two SPR-5000x | 2008-12-08 | 2008-12-08 | 0 | 2008-12-08 | [17 empty] | W |  | 6/1/12 Per customer letter this project has been abandoned.
Central Hudson |  | Solar Generation | CH-08223 | Kingston | Boicevl | Ulster | 12412 | G | 3011 | Woodstock | N |  | 6 | [13 empty] | NM | N | SB6000US | 2008-12-10 | 2008-12-11 | 1 | 2008-12-11 | [14 empty] | 2009-09-03 | 2009-09-10 |  | Y
Central Hudson |  | Renewable Power Systems | CH-02976 | Poughkeepsie | Ancram | Columbia | 12502 | G | 7085 | Ancram | N |  | 4 | [13 empty] | NM | N | SPR4000m | 2008-12-11 | 2008-12-11 | 0 | 2008-12-11 | [14 empty] | 2009-04-13 | 2009-04-13 |  | Y
Central Hudson |  | Hudson Solar | CH-01692 | Kingston | Woodstock | Ulster | 12498 | G | 3012 | Woodstock | N |  | 7.3 | [13 empty] | NM | N | SPR-4000x & SPR-3300x | 2008-12-18 | 2008-12-18 | 0 | 2008-12-18 | [14 empty] | 2009-04-24 | 2009-04-24 |  | Y
Central Hudson |  | Hudson Solar | CH-01830 | Poughkeepsie | Barrytown | Dutchess | 12507 | G | 7056 | Rhinebeck | N |  | 8 | [13 empty] | NM | N | SPR-3300x | 2008-12-18 | 2008-12-18 | 0 | 2008-12-18 | [14 empty] | 2009-08-17 | 2009-08-18 |  | Y
Central Hudson |  | Hudson Solar | CH-01785 | Poughkeepsie | Lagrangeville |  | 12540 | G | 6055 | Todd Hill | TBD |  | 3.3 | [13 empty] | NM | N | SPR-3300x | 2008-12-23 | 2008-12-23 | 0 | 2008-12-23 | [17 empty] | W |  | 6/1/12 Per customer letter this project has been abandoned.
Central Hudson |  | Solar Generation | CH-08278 | Kingston | Saugerties | Ulster | 12477 | G | 3014 | Woodstock | N |  | 7.5 | [13 empty] | NM | N | Fronius IG Plus 7.5 | 2008-12-29 | 2008-12-29 | 0 | 2008-12-29 | [14 empty] | 2009-10-25 | 2009-10-25 |  | Y
Central Hudson |  | Renewable Power Systems | CH-02961 | Catskill | Preston Holw | Albany | 12469 | G | 1092 | Westerlo | N |  | 3 | [13 empty] | NM | N | SPR 3000m | 2009-01-05 | 2009-01-08 | 3 | 2009-01-08 | [14 empty] | 2009-02-25 | 2009-02-26 |  | Y
Central Hudson |  | Solar Generation | CH-08233 | Kingston | Woodstock | Ulster | 12498 | G | 3014 | Woodstock | N |  | 8.5 | [13 empty] | NM | N | SB5000US | 2009-01-09 | 2009-01-14 | 3 | 2009-01-14 | [14 empty] | 2009-08-21 | 2009-08-27 |  | Y
Central Hudson |  | Hudson Solar | CH-01850 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7053 | Rhinebeck | N |  | 8 | [13 empty] | NM | N | SPR-4000x | 2009-01-06 | 2009-01-06 | 0 | 2009-01-06 | [14 empty] | 2009-05-11 | 2009-05-11 |  | Y
Central Hudson |  | Hudson Solar | CH-01705 | Kingston | Ellenvl | Ulster | 12428 | G | 3078 | Greenfield Rd | N |  | 5 | [13 empty] | NM | N | SPR-5000x | 2009-01-09 | 2009-01-09 | 0 | 2009-01-09 | [14 empty] | 2009-05-29 | 2009-06-01 |  | Y
Central Hudson |  | Hudson Solar | CH-01914 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8091 | Fishkill Plains | N |  | 5 | [13 empty] | NM | N | (1) SPR-5000m | 2009-01-09 | 2009-01-09 | 0 | 2009-01-09 | [14 empty] | 2009-06-30 | 2009-06-30 |  | Y
Central Hudson |  | Hudson Solar | CH-02096 | Poughkeepsie | Lagrangevl | Dutchess | 12540 | G | 6055 | Todd Hill | N |  | 4.7 | [13 empty] | NM | N | SPR-5000x | 2009-01-09 | 2009-01-09 | 0 | 2009-01-09 | [14 empty] | 2009-05-12 | 2009-05-27 |  | Y
Central Hudson |  | Hudson Solar | CH-02129 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7054 | Rhinebeck | N |  | 4 | [13 empty] | NM | N | SPR-4000x | 2009-01-09 | 2009-01-09 | 0 | 2009-01-09 | [14 empty] | 2009-05-21 | 2009-05-27 |  | Y
Central Hudson |  | Hudson Solar | CH-02185 | Newburgh | New Paltz |  | 12561 | G | 5021 | Ohioville | TBD |  | 6.6 | [13 empty] | NM | N | (2) SPR-3300x | 2009-01-09 | 2009-01-09 | 0 | 2009-01-09 | [17 empty] | W |  | Per customer letter received 5/22/12 this installation has been abandoned.
Central Hudson |  | Hudson Solar | CH-02188 | Newburgh | New Paltz | Ulster | 12561 | G | 5031 | Galeville | N |  | 3.6 | [13 empty] | NM | N | SPR-4000m | 2009-01-09 | 2009-01-09 | 0 | 2009-01-09 | [14 empty] | 2009-07-23 | 2009-07-27 |  | Y
Central Hudson |  | Hudson Solar | CH-02265 | Poughkeepsie | Wassaic | Dutchess | 12592 | G | 7012 | Hibernia | N |  | 10 | [13 empty] | NM | N | SUNPOWER SPR-5000M | 2009-01-09 | 2009-01-09 | 0 | 2009-01-09 | [14 empty] | 2009-08-10 | 2009-08-12 |  | Y
Central Hudson |  | Solar Generation | CH-08269 | Kingston | Glenford | Ulster | 12433 | G | 3013 | Woodstock | N | CH-08269 | 6.8 | [13 empty] | NM | N | SB7000US | 2009-01-12 | 2009-01-12 | 0 | 2009-01-12 | [14 empty] | 2009-07-15 | 2009-07-16 |  | Y
Central Hudson |  | T-KAR Smart Energy Systems | CH-09717 | Newburgh | Highland | Ulster | 12528 | G | 5083 | Highland | N |  | 10.53 | [13 empty] | NM | N | IG-4500 LV | 2009-01-13 | 2009-01-15 | 2 | 2009-01-15 | [14 empty] | 2009-11-04 | 2009-11-11 |  | Y
Central Hudson |  | Orange Green Energy LLC | CH-02822 | Newburgh | New Windsor |  | 12553 | G | 4041 | Union Ave | TBD |  | 2 |  | 4 | [11 empty] | NM | N | Skystream 3.7 | 2009-02-04 | 2009-02-04 | 0 | 2009-02-04 | [17 empty] | W |  | This project has been abandoned. Customer finaled CHGE account 11/7/11.
Central Hudson |  | Sustainable Energy Developments, Inc. | CH-09702 | Poughkeepsie | Millerton | Dutchess | 12546 | G | 7081 | Millerton | N |  |  |  | 10 | [11 empty] | NM | N | Diversified Technology Powersynch II AMFA-27 | 2009-01-14 | 2009-01-20 | 4 | 2009-01-20 | [14 empty] | 2009-11-05 | 2009-11-11 |  | W
Central Hudson |  | Hudson Solar | CH-01861 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7062 | Milan | N |  | 10 | [13 empty] | NM | N | SPR-5000m | 2009-01-16 | 2009-01-19 | 1 | 2009-01-19 | [14 empty] | 2009-08-03 | 2009-08-06 |  | W
Central Hudson |  | Hudson Solar | CH-02100 | Poughkeepsie | Clinton Corners | Dutchess | 12514 | G | 7071 | Stanfordville | N |  | 6.6 | [13 empty] | NM | N | (1) SPR-4000m; (1) SPR-3000m | 2009-01-16 | 2009-01-19 | 1 | 2009-01-19 | [14 empty] | 2009-06-03 | 2009-06-04 |  | Y
Central Hudson |  | Hudson Solar | CH-02516 | Poughkeepsie | Rhinebeck |  | 12572 | G | 7072 | Stanfordville | TBD |  | 10 | [13 empty] | NM | N | SPR-5000x | 2009-01-16 | 2009-01-16 | 0 | 2009-01-16 | [17 empty] | W |  | Customer abandoned this solar installation and reapplied with new contractor on 11/22/2011.
Central Hudson |  | Solar Generation | CH-08155 | Kingston | High Fls | Ulster | 12440 | G | 3022 | High Falls | N |  | 7 | [13 empty] | NM | N | SB7000US | 2009-01-19 | 2009-01-19 | 0 | 2009-01-19 | [14 empty] | 2009-07-09 | 2009-07-10 |  | Y
Central Hudson |  | Solar Generation | CH-08134 | Kingston | Kingston |  | 12401 | G | 1003 | Jansen Ave | TBD |  | 28.665 | [13 empty] | NM | N | PVP 30kW | 2009-02-10 | 2009-02-11 | 1 | 2009-02-11 | [17 empty] | W |  | Need $350 application fee. Application incomplete notice sent on 1/23/09. Fee paid on 2/10/09.
Central Hudson |  | Hudson Solar | CH-01238 | Newburgh | Newburgh |  | 12550 | G | 5001 | Marlboro | TBD |  | 4 | [13 empty] | NM | N | SPR-4000x | 2009-01-29 | 2009-02-04 | 4 | 2009-02-04 | [17 empty] | W
Central Hudson |  | Hudson Solar | CH-01379 | Poughkeepsie | Ancramdale | Columbia | 12503 | G | 7092 | Pulvers Corners | N |  | 24 | [13 empty] | NM | N | SPR-5000x | 2009-03-04 | 2009-03-06 | 2 | 2009-03-06 | [14 empty] | 2011-09-30 | 2011-10-06 |  | Y
Central Hudson |  | Hudson Solar | CH-01651 | Kingston | Stone Ridge | Ulster | 12484 | G | 3024 | High Falls | N |  | 9 | [13 empty] | NM | N | (1) SPR-5000x & (1) SPR-4000x | 2009-01-29 | 2009-02-02 | 2 | 2009-02-02 | [14 empty] | 2010-04-12 | 2010-04-12 |  | Y
Central Hudson |  | Hudson Solar | CH-01683 | Kingston | Ulster Pk | Ulster | 12487 | G | 1014 | Boulevard | N |  | 4 | [13 empty] | NM | N | SPR-4000x | 2009-01-29 | 2009-02-02 | 2 | 2009-02-02 | [14 empty] | 2009-06-22 | 2009-06-24 |  | W
Central Hudson |  | Hudson Solar | CH-01769 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 7042 | Staatsburg | N |  | 10.35 | [13 empty] | NM | N | (2) SPR-4000m SPR-3000m | 2009-01-29 | 2009-02-02 | 2 | 2009-02-02 | [14 empty] | 2009-07-21 | 2009-07-21 |  | Y
Central Hudson |  | Hudson Solar | CH-02131 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7052 | Rhinebeck | N |  | 5 | [13 empty] | NM | N | SPR-5000x | 2009-01-29 | 2009-02-02 | 2 | 2009-02-02 | [14 empty] | 2009-06-26 | 2009-06-26 |  | Y
Central Hudson |  | Hudson Solar | CH-02149 | Poughkeepsie | Tivoli | Dutchess | 12583 | G | 7062 | Milan | N |  | 3.3 | [13 empty] | NM | N | SPR-3300x | 2009-01-29 | 2009-02-02 | 2 | 2009-02-02 | [14 empty] | 2009-05-28 | 2009-06-03 |  | Y
Central Hudson |  | Hudson Solar | CH-01303 | Poughkeepsie | Millbrook |  | 12545 | G | 6057 | Todd Hill | TBD |  | 48 | [13 empty] | NM | N | SPR-5000x and SPR-4000x | 2009-02-26 | 2009-03-04 | 4 | 2009-03-04 | [17 empty] | W |  | 2/2/09 Need $350 application fee. 2/26/09 Application fee paid.
Central Hudson |  | Hudson Solar | CH-01602 | Catskill | West Kill | Greene | 12492 | E | 2389 | Vinegar Hill | N |  | 5 | [13 empty] | NM | N | SPR-5000m | 2009-01-30 | 2009-02-02 | 1 | 2009-02-02 | [14 empty] | 2009-06-26 | 2009-06-26 |  | Y
Central Hudson |  | Hudson Solar | CH-01670 | Kingston | Cottekill | Ulster | 12419 | G | 3021 | High Falls | N |  | 8 | [13 empty] | NM | N | SPR-5000x, SPR-3300x | 2009-01-30 | 2009-02-02 | 1 | 2009-02-02 | [14 empty] | 2009-08-18 | 2009-08-21 |  | Y
Central Hudson |  | Hudson Solar | CH-01890 | Poughkeepsie | Pine Plns | Dutchess | 12567 | G | 7091 | Pulvers Corners | N |  | 5 | [13 empty] | NM | N | SPR-5000m | 2009-01-30 | 2009-02-02 | 1 | 2009-02-02 | [14 empty] | 2009-06-26 | 2009-06-29 |  | Y
Central Hudson |  | Hudson Solar | CH-02009 | Catskill | West Kill | Greene | 12492 | E | 2389 | Vinegar Hill | N |  | 5 | [13 empty] | NM | N | SPR-5000x | 2009-01-30 | 2009-02-02 | 1 | 2009-02-02 | [14 empty] | 2009-06-26 | 2009-06-26 |  | Y
Central Hudson |  | Hudson Solar | CH-02102 | Poughkeepsie | Poughkeepsie |  | 12601 | G | 6001 | Reynolds Hill | TBD |  | 49.105 | [13 empty] | NM | N | SatCon PVS-50 | 2009-02-26 | 2009-03-04 | 4 | 2009-03-04 | [17 empty] | W |  | 2/2/09: Need $350 application fee. 2/26/09: Application fee paid. As per customer letter received on 5/22/12 this installation has been abandoned.
Central Hudson |  | Sun Mountain | CH-09091 | Kingston | Accord | Ulster | 12404 | G | 3024 | High Falls | N |  | 2.08 | [13 empty] | NM | N | SB3000US | 2009-01-30 | 2009-02-02 | 1 | 2009-02-02 | [14 empty] | 2009-12-21 | 2009-12-29 |  | Y
Central Hudson |  | Sun Mountain | CH-09093 | Kingston | Kerhonkson | Ulster | 12446 | G | 3081 | Kerhonkson | N |  | 4.8 | [13 empty] | NM | N | SB5000US | 2009-01-30 | 2009-02-02 | 1 | 2009-02-02 | [14 empty] | 2009-07-23 | 2009-07-23 |  | Y
Central Hudson |  | Hudson Solar | CH-01258 | Catskill | Palenvl | Greene | 12463 | G | 2001 | North Catskill | N |  | 5 | [13 empty] | NM | N | SPR-5000x | 2009-02-02 | 2009-02-04 | 2 | 2009-02-04 | [14 empty] | 2009-12-29 | 2010-01-04 |  | Y
Central Hudson |  | Hudson Solar | CH-01344 | Newburgh | New Paltz |  | 12561 | G | 5021 | Ohioville | TBD |  | 10 | [13 empty] | NM | N | SPR-5000x | 2009-02-02 | 2009-02-02 | 0 | 2009-02-02 | [17 empty] | W
Central Hudson |  | Hudson Solar | CH-01377 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6092 | Manchester | N |  | 48 | [13 empty] | NA | N | SPR-5000x, SPR-3300x | 2009-03-05 | 2009-03-09 | 2 | 2009-03-09 | [14 empty] | 2010-11-01 | 2010-11-01 |  | Y
Central Hudson |  | Hudson Solar | CH-01385 | Kingston | Stone Ridge | Ulster | 12484 | G | 3023 | High Falls | N |  | 4 | [13 empty] | NM | N | SPR-4000x | 2009-02-02 | 2009-02-09 | 5 | 2009-02-09 | [14 empty] | 2009-05-27 | 2009-06-01 |  | Y
Central Hudson |  | Hudson Solar | CH-01477 | Kingston | Saugerties | Ulster | 12477 | G | 3003 | Saugerties | N |  | 10 | [13 empty] | NM | N | (2) SPR-5000x | 2009-02-02 | 2009-02-05 | 3 | 2009-02-05 | [14 empty] | 2009-12-04 | 2009-12-07 |  | Y
Central Hudson |  | Hudson Solar | CH-01484 | Poughkeepsie | Poughquag | Dutchess | 12570 | G | 6055 | Todd Hill | N | CH-01484 | 10 | [13 empty] | NM | N | SPR-5000x | 2009-02-02 | 2009-02-05 | 3 | 2009-02-05 | [14 empty] | 2009-10-22 | 2009-10-28 |  | Y
Central Hudson |  | Hudson Solar | CH-01547 | Newburgh | New Paltz | Ulster | 12561 | G | 5011 | Modena | N |  | 6 | [13 empty] | NM | N | SPR-3000m | 2009-02-02 | 2009-02-02 | 0 | 2009-02-02 | [14 empty] | 2009-08-11 | 2009-08-11 |  | Y
Central Hudson |  | Hudson Solar | CH-01642 | Catskill | Hunter | Greene | 12442 | E | 2081 | Hunter | N |  | 20 | [13 empty] | NM | N | SPR-4000x | 2009-02-26 | 2009-03-04 | 4 | 2009-03-04 | [14 empty] | 2009-09-10 | 2009-09-10 |  | Y
Central Hudson |  | Hudson Solar | CH-01728 | Kingston | Kingston | Ulster | 12401 | G | 1021 | East Kingston | N |  | 4 | [13 empty] | NM | N | SPR-5000x | 2009-02-02 | 2009-02-05 | 3 | 2009-02-05 | [14 empty] | 2009-12-15 | 2009-12-16 |  | Y
Central Hudson |  | Hudson Solar | CH-01887 | Poughkeepsie | Millerton | Dutchess | 12546 | G | 7092 | Pulvers Corners | N |  | 10 | [13 empty] | NM | N | SPR-5000x | 2009-02-02 | 2009-02-05 | 3 | 2009-02-05 | [14 empty] | 2009-12-31 | 2010-01-06 |  | Y
Central Hudson |  | Hudson Solar | CH-01926 | Fishkill | Cold Spg | Putnam | 10516 | G | 8063 | Merritt Park | N |  | 5 | [13 empty] | NM | N | SPR-5000x | 2009-02-02 | 2009-02-02 | 0 | 2009-02-02 | [14 empty] | 2009-07-01 | 2009-07-01 |  | Y
Central Hudson |  | Hudson Solar | CH-02050 | Kingston | Kerhonkson | Ulster | 12446 | G | 3071 | Honk Falls | N |  | 7.2 | [13 empty] | NM | N | SunPower SPR-4000m | 2009-02-02 | 2009-02-05 | 3 | 2009-02-05 | [14 empty] | 2009-07-31 | 2009-08-05 |  | Y
Central Hudson |  | Hudson Solar | CH-02325 | Newburgh | Wallkill | Ulster | 12589 | G | 5033 | Galeville | N |  | 6.6 | [13 empty] | NM | N | SPR-3300x | 2009-02-02 | 2009-02-02 | 0 | 2009-02-02 | [14 empty] | 2009-09-25 | 2009-09-29 |  | Y
Central Hudson |  | Renewable Power Systems | CH-02965 | Catskill | Westerlo | Albany | 12193 | G | 1091 | Westerlo | N |  | 5 | [13 empty] | NM | N | SPR-5000x | 2009-02-13 | 2009-02-19 | 3 | 2009-02-19 | [14 empty] | 2009-05-20 | 2009-05-20 |  | Y
Central Hudson |  | Renewable Power Systems | CH-02973 | Catskill | Catskill | Greene | 12414 | G | 2003 | North Catskill | N |  | 4 | [13 empty] | NM | N | SPR-4000m | 2009-02-19 | 2009-02-19 | 0 | 2009-02-19 | [14 empty] | 2009-06-12 | 2009-06-12 |  | Y
Central Hudson |  | Hudson Solar | CH-01338 | Newburgh | Highland |  | 12528 | G | 5082 | Highland | TBD |  | 11.475 | [13 empty] | NM | N | SPR-3300x | 2009-02-04 | 2009-02-05 | 1 | 2009-02-05 | [17 empty] | W |  | 9/30/14 Project abandoned, as per customer.
Central Hudson |  | Hudson Solar | CH-01536 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7054 | Rhinebeck | N |  | 9 | [13 empty] | NM | N | SPR-5000x | 2009-02-04 | 2009-02-05 | 1 | 2009-02-05 | [14 empty] | 2009-10-09 | 2009-10-15 |  | Y
Central Hudson |  | Hudson Solar | CH-01542 | Newburgh | Gardiner | Ulster | 12525 | G | 5031 | Galeville | N |  | 6 | [13 empty] | NM | N | SPR-5000x | 2009-02-04 | 2009-02-05 | 1 | 2009-02-05 | [14 empty] | 2010-04-23 | 2010-04-23 |  | Y
Central Hudson |  | Hudson Solar | CH-01854 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7055 | Rhinebeck | N |  | 2.5 | [13 empty] | NM | N | SPR-5000x | 2009-02-04 | 2009-02-05 | 1 | 2009-02-05 | [14 empty] | 2009-12-23 | 2009-12-28 |  | Y
Central Hudson |  | Hudson Solar | CH-01909 | Newburgh | Highland |  | 12528 | G | 5022 | Ohioville | TBD |  | 5 | [13 empty] | NM | N | SPR-5000x | 2009-02-04 | 2009-02-05 | 1 | 2009-02-05 | [17 empty] | W |  | 9/30/14 Project abandoned, as per customer.
Central Hudson |  | Hudson Solar | CH-01986 | Newburgh | Gardiner | Ulster | 12525 | G | 5011 | Modena | N |  | 23.3 | [13 empty] | NM | N | SPR-5000x, SPR-3300x | 2009-03-04 | 2009-03-06 | 2 | 2009-03-06 | [14 empty] | 2009-11-16 | 2009-11-18 |  | Y
Central Hudson |  | Hudson Solar | CH-02469 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7056 | Rhinebeck | N | CH-01378 | 9.45 | [13 empty] | NM | N | SPR-5000x | 2009-09-09 | 2009-09-16 | 5 | 2009-09-16 | [14 empty] | 2009-12-31 | 2010-01-08 |  | Y
Central Hudson |  | Hudson Solar | CH-01260 | Catskill | Tannersville |  | 12485 | G | 2385 | Lawrenceville | TBD |  | 5 | [13 empty] | NM | N | SPR-5000x | 2009-02-05 | 2009-02-11 | 4 | 2009-02-11 | [17 empty] | W
Central Hudson |  | Hudson Solar | CH-01293 | Kingston | Woodstock | Ulster | 12498 | G | 3014 | Woodstock | N | CH-01293 | 4 | [13 empty] | NM | N | SPR-4000x | 2009-02-05 | 2009-02-11 | 4 | 2009-02-11 | [14 empty] | 2009-12-23 | 2009-12-31 |  | Y
Central Hudson |  | Hudson Solar | CH-01583 | Newburgh | Newburgh |  | 12550 | G | 5001 | Marlboro | TBD |  | 6.6 | [13 empty] | NM | N | (2) SPR-3300x | 2009-02-05 | 2009-02-11 | 4 | 2009-02-11 | [17 empty] | W |  | 10/7/14 Project abandoned as per customer.
Central Hudson |  | Hudson Solar | CH-01788 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 6057 | Todd Hill | N | CH-01788 | 4 | [13 empty] | NM | N | SPR-3000m SPR-4000m | 2009-02-05 | 2009-02-11 | 4 | 2009-02-11 | [14 empty] | 2009-07-21 | 2009-07-21 |  | Y
Central Hudson |  | Hudson Solar | CH-01883 | Poughkeepsie | Millerton |  | 12546 | G | 7095 | Smithfield | TBD |  | 5 | [13 empty] | NM | N | SPR-5000x | 2009-02-05 | 2009-02-11 | 4 | 2009-02-11 | [17 empty] | W |  | 10/1/14 Project abandoned as per customer.
Central Hudson |  | Hudson Solar | CH-02324 | Newburgh | Gardiner | Ulster | 12525 | G | 5034 | Galeville | N | CH-02324 | 5 | [13 empty] | NM | N | SPR-5000x | 2009-02-05 | 2009-02-11 | 4 | 2009-02-11 | [14 empty] | 2009-09-04 | 2009-09-08 |  | Y
Central Hudson |  | Hudson Solar | CH-02397 | Poughkeepsie | Red Hook |  | 12571 | G | 7054 | Rhinebeck | TBD |  | 21.8 | [13 empty] | NM | N | SPR-5000x, SPR-4000x | 2009-03-04 | 2009-03-06 | 2 | 2009-03-06 | [17 empty] | W
Central Hudson |  | Renewable Power Systems | CH-02964 | Catskill | Greenvl | Greene | 12083 | G | 2061 | Freehold | N |  | 5 | [13 empty] | NM | N | SPR-5000m | 2009-02-09 | 2009-02-12 | 3 | 2009-02-12 | [14 empty] | 2009-12-10 | 2009-12-11 |  | Y
Central Hudson |  | Renewable Power Systems | CH-02967 | Catskill | Coxsackie |  | 12051 | G | 1076 | Coxsackie | TBD |  | 4 | [13 empty] | NM | N | SPR4000m | 2009-02-09 | 2009-02-17 | 5 | 2009-02-17 | [14 empty] | 2009-06-08 | 2009-06-09 |  | W
Central Hudson |  | Renewable Power Systems | CH-02974 | Catskill | Newburgh | Greene | 12051 | G | 1076 | Coxsackie | N |  | 4 | [13 empty] | NM | N | SPR4000m | 2009-02-09 | 2009-02-17 | 5 | 2009-02-17 | [14 empty] | 2009-06-08 | 2009-06-09 |  | Y
Central Hudson |  | groSolar | CH-01188 | Kingston | Grahamsvl | Sullivan | 12740 | G | 391 | Neversink | N |  | 6.63 | [13 empty] | NM | N | (1) IG3000, (1) IG4000 | 2009-02-10 | 2009-02-12 | 2 | 2009-02-12 | [14 empty] | 2009-09-08 | 2009-09-08 |  | Y
Central Hudson |  | T-KAR Smart Energy Systems | CH-09722 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 7024 | Tinkertown | N |  | 4.8 | [13 empty] | NM | N | Fronius IG 5100 | 2009-02-27 | 2009-02-27 | 0 | 2009-02-27 | [14 empty] | 2010-01-11 | 2010-01-13 |  | Y
Central Hudson |  | Solar Generation | CH-08099 | Kingston | Woodstock |  | 12498 | G | 3014 | Woodstock | TBD |  | 4.25 | [13 empty] | NM | N | SB5000US | 2009-03-13 | 2009-03-18 | 3 | 2009-03-18 | [17 empty] | W |  | Customer already had net meter prior to application. Installation abandoned.
Central Hudson |  | Solar Generation | CH-08236 | Kingston | Woodstock | Ulster | 12498 | G | 3012 | Woodstock | N |  | 3.8 | [13 empty] | NM | N | SB4000US | 2009-03-13 | 2009-03-18 | 3 | 2009-03-18 | [14 empty] | 2009-10-30 | 2009-11-04 |  | Y
Central Hudson |  | Solar Generation | CH-08238 | Kingston | Woodstock | Ulster | 12498 | G | 3012 | Woodstock | N |  | 5.6 | [13 empty] | NM | N | SB6000US | 2009-03-13 | 2009-03-18 | 3 | 2009-03-18 | [14 empty] | 2009-10-30 | 2009-11-04 |  | Y
Central Hudson |  | 2K Solar Inc | CH-00619 | Newburgh | New Paltz | Ulster | 12561 | G | 5031 | Galeville | N |  | 7 | [13 empty] | NM | N | SunnyBoy 7000 US | 2009-03-26 | 2009-03-31 | 3 | 2009-03-31 | [14 empty] | 2009-04-21 | 2009-04-21 |  | Y
Central Hudson |  | Quality Electric | CH-02951 | Kingston | Kingston | Ulster | 12401 | G | 1022 | East Kingston | N | CH-02951 | 4 | [13 empty] | NM | N | Fronius IG 4000 | 2009-03-26 | 2009-03-31 | 3 | 2009-03-31 | [14 empty] | 2009-07-07 | 2009-07-07 |  | Y
Central Hudson |  | Renewable Power Systems | CH-02960 | Catskill | Rensselaervl | Albany | 12147 | G | 1092 | Westerlo | N |  | 10 | [13 empty] | NM | N | SPR5000m | 2009-03-31 | 2009-03-31 | 0 | 2009-03-31 | [14 empty] | 2009-07-30 | 2009-07-31 |  | Y
Central Hudson |  | 2K Solar Inc | CH-00623 | Newburgh | New Windsor | Orange | 12553 | G | 4043 | Union Ave | N |  | 7 | [13 empty] | NM | N | Sunny Boy 6000 US | 2009-04-02 | 2009-04-02 | 0 | 2009-04-02 | [14 empty] | 2009-04-21 | 2009-04-21 |  | Y
Central Hudson |  | Mercury Solar Systems | CH-02624 | Newburgh | Newburgh | Orange | 12550 | G | 4055 | Union Ave | N |  | 50.4 | [13 empty] | NM | N | Fronius IG Plus 11.4-3 Delta | 2009-05-05 | 2009-05-05 | 0 | 2009-05-05 | [14 empty] | 2009-08-25 | 2009-08-27 |  | Y
Central Hudson |  | 1st Light Energy | CH-00583 | Newburgh | Newburgh | Orange | 12550 | G | 4023 | Coldenham | N |  | 4 | [13 empty] | NM | N | Fronius IG4000 | 2009-04-14 | 2009-04-14 | 0 | 2009-04-14 | [14 empty] | 2009-04-24 | 2009-04-24 |  | Y
Central Hudson |  | Sun Mountain | CH-09082 | Kingston | W Hurley | Ulster | 12491 | G | 2094 | Hurley Ave | N |  | 5 | [13 empty] | NM | N | SB 5000 US | 2009-04-16 | 2009-04-21 | 3 | 2009-04-21 | [14 empty] | 2009-12-02 | 2009-12-08 |  | Y
Central Hudson |  | ETM Solar Works | CH-01120 | Kingston | Lk Katrine | Albany | 12249 | G | 2011 | Lincoln Park | N |  | 6 | [13 empty] | NM | N | (2) SB 3000US | 2009-05-12 | 2009-06-03 | 15 | 2009-06-03 | [14 empty] | 2009-06-10 | 2009-06-16 |  | Y
Central Hudson |  | 2K Solar Inc | CH-00624 | Newburgh | Salisbury Mls | Orange | 12577 | G | 4095 | Bethlehem Rd | N |  | 8.6 | [13 empty] | NM | N | Fronius IG 5100/IG 4000 | 2009-05-06 | 2009-05-06 | 0 | 2009-05-06 | [14 empty] | 2009-05-13 | 2009-05-13 |  | Y
Central Hudson |  | Hudson Solar | CH-01349 | Newburgh | Newburgh | Orange | 12550 | G | 4013 | West Balmville | N |  | 8 | [13 empty] | NM | N | 2 SPR-4000m | 2009-05-27 | 2009-05-27 | 0 | 2009-05-27 | [14 empty] | 2010-02-15 | 2010-02-15 |  | Y
Central Hudson |  | Hudson Solar | CH-01678 | Kingston | High Fls | Ulster | 12440 | G | 3024 | High Falls | N |  | 7 | [13 empty] | NM | N | SPR-7000m | 2009-05-11 | 2009-05-12 | 1 | 2009-05-12 | [14 empty] | 2009-10-20 | 2009-10-22 |  | Y
Central Hudson |  | RGS Energy | CH-03002 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7013 | Hibernia | N |  | 48 | [13 empty] | NM | N | (3) SPR-5000m, (1) SPR-6000m, (4) SPR-7000m | 2009-06-15 | 2009-06-23 | 6 | 2009-06-23 | [14 empty] | 2009-10-13 | 2009-10-29 |  | Y
Central Hudson |  | RGS Energy | CH-03028 | Kingston | Ellenvl | Ulster | 12428 | G | 3078 | Greenfield Rd | N |  | 6 | [13 empty] | NM | N | 6000M | 2009-05-26 | 2009-06-01 | 4 | 2009-06-01 | [14 empty] | 2010-03-30 | 2010-04-01 |  | Y
Central Hudson |  | 1st Light Energy | CH-00592 | Fishkill | Hopewell Junction | Dutchess | 12533 | G | 8071 | Shenandoah | N |  | 4 | [13 empty] | NM | N | IG4000 | 2009-06-12 | 2009-06-12 | 0 | 2009-06-12 | [14 empty] | 2009-06-16 | 2009-06-16 |  | Y
Central Hudson |  | Hudson Solar | CH-02452 | Poughkeepsie | Stanfordvl | Dutchess | 12581 | G | 7072 | Stanfordville | N | CH-01229 | 7 | [13 empty] | NM | N | 1 SMA SB 4000US 1 SMA SB 3000US | 2009-06-01 | 2009-06-01 | 0 | 2009-06-01 | [14 empty] | 2009-10-08 | 2009-10-13 |  | Y
Central Hudson |  | Sun Mountain | CH-09117 | Kingston | Kerhonkson | Ulster | 12446 | G | 3082 | Kerhonkson | N |  | 14.4 | [13 empty] | NM | N | 3-SB 5000 US | 2009-06-01 | 2009-06-02 | 1 | 2009-06-02 | [14 empty] | 2010-01-16 | 2010-01-22 |  | Y
Central Hudson |  | Hudson Solar | CH-01952 | Newburgh | New Paltz | Ulster | 12561 | G | 5022 | Ohioville | N |  | 10 | [13 empty] | NM | N | 2 SunPower SPR-5000m | 2009-06-02 | 2009-06-04 | 2 | 2009-06-04 | [14 empty] | 2009-08-31 | 2009-09-02 |  | Y
Central Hudson |  | Hudson Solar | CH-02442 | Kingston | Saugerties | Ulster | 12477 | G | 3003 | Saugerties | N | CH-01241 | 2.52 | [13 empty] | NM | N | SunPower SPR-3000m | 2009-06-02 | 2009-06-04 | 2 | 2009-06-04 | [14 empty] | 2009-08-10 | 2009-08-12 |  | Y
Central Hudson |  | RGS Energy | CH-02999 | Poughkeepsie | Pine Plns | Dutchess | 12567 | G | 7091 | Pulvers Corners | N |  | 4.5 | [13 empty] | NM | N | SPR4000M | 2009-06-04 | 2009-06-05 | 1 | 2009-06-05 | [14 empty] | 2009-09-02 | 2009-09-02 |  | Y
Central Hudson |  | RKB Contruction Company, Inc. | CH-02987 | Newburgh | New Windsor | Orange | 12553 | G | 4054 | Union Ave | N |  | 2.4 | [13 empty] | NM | N | GT 2.8 | 2009-06-12 | 2009-06-17 | 3 | 2009-06-17 | [14 empty] | 2009-07-24 | 2009-07-24 |  | Y
Central Hudson |  | SunDog Solar | CH-09161 | Newburgh | Highland | Ulster | 12528 | G | 5084 | Highland | N |  | 5 | [13 empty] | NM | N | SB5000US | 2009-06-25 | 2009-06-26 | 1 | 2009-06-26 | [14 empty] | 2009-07-24 | 2009-07-24 |  | Y
Central Hudson |  | Solar Generation | CH-08130 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6056 | Todd Hill | N |  | 5.46 | [13 empty] | NM | N | SB6000US | 2009-06-15 | 2009-06-16 | 1 | 2009-06-16 | [14 empty] | 2009-09-17 | 2009-09-22 |  | Y
Central Hudson |  | altPower | CH-00647 | Kingston | Saugerties | Ulster | 12477 | G | 3001 | Saugerties | N |  | 2.3 | [13 empty] | NM | N | Fronius IG3000 | 2009-06-17 | 2009-06-18 | 1 | 2009-06-18 | [14 empty] | 2009-09-11 | 2009-09-17 |  | Y
Central Hudson |  | 1st Light Energy | CH-00581 | Kingston | Grahamsvl | Sullivan | 12740 | G | 3091 | Neversink | N |  | 8 | [13 empty] | NM | N | SB3000US SB5000US | 2009-06-19 | 2009-06-22 | 1 | 2009-06-22 | [14 empty] | 2009-09-04 | 2009-09-08 |  | Y
Central Hudson |  | Green Building and Material Supply, Inc. | CH-01154 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 7024 | Tinkertown | N |  | 50.4 | [13 empty] | NM | N | 5 Fronius 11.4-3 Delta | 2009-06-19 | 2009-06-19 | 0 | 2009-06-19 | [14 empty] | 2010-10-21 | 2010-10-26 |  | Y
Central Hudson |  | Renovus Energy | CH-02982 | Newburgh | Highland | Ulster | 12528 | G | 5024 | Ohioville | N | CH-02982 | 9 | [13 empty] | NM | N | SPR 4000m SPR 5000m | 2009-06-29 | 2009-06-29 | 0 | 2009-06-29 | [14 empty] | 2009-07-10 | 2009-07-10 |  | Y
Central Hudson |  | 1st Light Energy | CH-00580 | Newburgh | Salisbury Mls | Orange | 12577 | G | 4095 | Bethlehem Rd | N |  | 5.2 | [13 empty] | NM | N | SB 6000US | 2009-06-22 | 2009-06-23 | 1 | 2009-06-23 | [14 empty] | 2009-08-11 | 2009-08-12 |  | Y
Central Hudson |  | 1st Light Energy | CH-00585 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 5 | [13 empty] | NM | N | GT 5.0 | 2009-06-22 | 2009-06-22 | 0 | 2009-06-22 | [14 empty] | 2009-08-11 | 2009-08-17 |  | Y
Central Hudson |  | Solar Generation | CH-08211 | Kingston | Stone Ridge |  | 12484 | G | 3023 | High Falls | TBD |  | 6 | [13 empty] | NM | N | SB 6000US | 2009-06-22 | 2009-06-23 | 1 | 2009-06-23 | [17 empty] | W |  | 6/1/12 Per customer letter this project has been abandoned.
Central Hudson |  | Solar Generation | CH-08224 | Kingston | W Shokan | Ulster | 12494 | G | 3011 | Woodstock | N |  | 6 | [13 empty] | NM | N | SB 6000 US | 2009-06-22 | 2009-06-24 | 2 | 2009-06-24 | [14 empty] | 2010-02-03 | 2010-02-03 |  | Y
Central Hudson |  | Hudson Solar | CH-01689 | Kingston | Shokan | Ulster | 12481 | G | 3011 | Woodstock | N |  | 5 | [13 empty] | NM | N | SunPower SPR-5000m | 2009-06-29 | 2009-06-29 | 0 | 2009-06-29 | [14 empty] | 2009-08-11 | 2009-08-11 |  | Y
Central Hudson |  | SunDog Solar | CH-09153 | Newburgh | New Paltz | Ulster | 12561 | G | 5023 | Ohioville | N |  | 5 | [13 empty] | NM | N | SB5000US | 2009-06-29 | 2009-06-29 | 0 | 2009-06-29 | [14 empty] | 2009-11-03 | 2009-11-04 |  | Y
Central Hudson |  | Solar Generation | CH-08128 | Kingston | Saugerties | Ulster | 12477 | G | 3002 | Saugerties | N |  | 7 | [13 empty] | NM | N | SB7000US | 2009-07-01 | 2009-07-01 | 0 | 2009-07-01 | [14 empty] | 2010-02-05 | 2010-02-05 |  | Y
Central Hudson |  | Hudson Solar | CH-01811 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 7024 | Tinkertown | N |  | 6.5 | [13 empty] | NM | N | SunPower SPR-6500f | 2009-07-02 | 2009-07-07 | 2 | 2009-07-07 | [14 empty] | 2009-10-29 | 2009-10-30 |  | Y
Central Hudson |  | Hudson Solar | CH-02347 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7054 | Rhinebeck | N |  | 5 | [13 empty] | NM | N | SunPower SPR-5000m | 2009-07-02 | 2009-07-06 | 1 | 2009-07-06 | [14 empty] | 2009-10-06 | 2009-10-09 |  | Y
Central Hudson |  | SunDog Solar | CH-09146 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7054 | Rhinebeck | N |  | 7.56 | [13 empty] | NM | N | SB5000US SB3000US | 2009-07-07 | 2009-07-09 | 2 | 2009-07-09 | [14 empty] | 2010-03-12 | 2010-03-12 |  | Y
Central Hudson |  | Green in Greene | CH-01165 | Catskill | Athens | Greene | 12015 | G | 2002 | North Catskill | N |  | 2.3 | [13 empty] | NM | N | Skystream 3.7 | 2009-07-09 | 2009-07-13 | 2 | 2009-07-13 | [14 empty] | 2010-01-18 | 2010-01-18 |  | Y
Central Hudson |  | Green Building and Material Supply, Inc. | CH-01157 | Poughkeepsie | Salt Pt | Dutchess | 12569 | G | 7011 | Hibernia | N |  | 24 | [13 empty] | NM | N | Fronius IG 11.4-1 UNI | 2009-07-16 | 2009-07-22 | 4 | 2009-07-22 | [14 empty] | 2010-05-20 | 2010-05-27 |  | Y
Central Hudson |  | 1st Light Energy | CH-00577 | Newburgh | Campbell Hall | Orange | 10916 | G | 5052 | Maybrook | N | CH-00577 | 5 | [13 empty] | NM | N | GT 5.0-NA-240/208 | 2009-07-31 | 2009-08-03 | 1 | 2009-08-03 | [14 empty] | 2009-08-14 | 2009-08-14 |  | Y
Central Hudson |  | Hudson Solar | CH-02228 | Kingston | Tillson | Ulster | 12486 | G | 3022 | High Falls | N |  | 10 | [13 empty] | NM | N | (2) SPR-5000m | 2009-07-29 | 2009-07-30 | 1 | 2009-07-30 | [14 empty] | 2009-09-28 | 2009-09-29 |  | Y
Central Hudson |  | Hudson Solar | CH-01479 | Poughkeepsie | Staatsburg | Dutchess | 12580 | G | 7011 | Hibernia | N |  | 7.2 | [13 empty] | NM | N | 2 SunPower SPR-4000m | 2009-08-03 | 2009-08-04 | 1 | 2009-08-04 | [14 empty] | 2009-11-09 | 2009-11-09 |  | Y
Central Hudson |  | Hudson Solar | CH-01528 | Kingston | Saugerties | Ulster | 12477 | G | 2015 | Lincoln Park | N |  | 9 | [13 empty] | NM | N | (1) SPR-5000m & (1) SPR-4000m | 2009-08-12 | 2009-08-17 | 3 | 2009-08-17 | [14 empty] | 2009-12-04 | 2009-12-07 |  | Y
Central Hudson |  | Hudson Solar | CH-01940 | Newburgh | New Paltz | Ulster | 12561 | G | 5031 | Galeville | N | CH-01940 | 5 | [13 empty] | NM | N | SPR-5000m | 2009-08-12 | 2009-08-14 | 2 | 2009-08-14 | [14 empty] | 2009-12-18 | 2009-12-22 |  | Y
Central Hudson |  | Hudson Solar | CH-01965 | Newburgh | Newburgh | Orange | 12550 | G | 5001 | Marlboro | N |  | 6.075 | [13 empty] | NM | N | SPR-6500f | 2009-08-03 | 2009-08-06 | 3 | 2009-08-06 | [14 empty] | 2009-09-11 | 2009-09-14 |  | Y
Central Hudson |  | Hudson Solar | CH-02441 | Kingston | Saugerties | Ulster | 12477 | G | 2015 | Lincoln Park | N | CH-01225 | 10 | [13 empty] | NM | N | (2) SPR-5000m | 2009-08-05 | 2009-08-06 | 1 | 2009-08-06 | [14 empty] | 2009-12-07 | 2009-12-08 |  | Y
Central Hudson |  | Sunnyside Solar | CH-09635 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6061 | Inwood Ave | N |  | 11.52 | [13 empty] | NM | N | (2) Sunny Boy SB6000US | 2009-08-27 | 2009-08-27 | 0 | 2009-08-27 | [14 empty] | 2009-10-19 | 2009-10-23 |  | Y
Central Hudson |  | T-KAR Smart Energy Systems | CH-09718 | Fishkill | Fishkill | Dutchess | 12524 | G | 8015 | Forgebrook | N |  | 12.3 | [13 empty] | NM | N | (3) SB5000US | 2009-08-10 | 2009-08-14 | 4 | 2009-08-14 | [14 empty] | 2010-07-15 | 2010-07-21 |  | Y
Central Hudson |  | Hudson Solar | CH-01717 | Kingston | Saugerties | Ulster | 12477 | G | 3003 | Saugerties | N |  | 8 | [13 empty] | NM | N | (2) SPR-4000m | 2009-08-14 | 2009-08-17 | 1 | 2009-08-17 | [14 empty] | 2010-02-08 | 2010-02-08 |  | W
Central Hudson |  | Hudson Solar | CH-01483 | Poughkeepsie | Lagrangeville | Dutchess | 12540 | G | 6057 | Todd Hill | N |  | 5 | [13 empty] | NM | N | (1) SPR-5000m | 2009-08-17 | 2009-08-17 | 0 | 2009-08-17 | [14 empty] | 2009-11-30 | 2009-12-03 |  | Y
Central Hudson |  | Green in Greene | CH-01168 | Catskill | Jewett | Greene | 12444 | E | 2389 | Vinegar Hill | Y | CH-01168 |  |  | 2.4 | [11 empty] | NM | N | Southwest Windpower Skystream 3.7 | 2009-09-02 | 2009-09-08 | 3 | 2009-09-08 | [14 empty] | 2010-01-14 | 2010-01-20 |  | Y
Central Hudson |  | Hudson Solar | CH-01239 | Newburgh | Marlboro | Ulster | 12542 | G | 5003 | Marlboro | N |  | 5 | [13 empty] | NM | N | Sunpower SPR-5000m | 2009-08-18 | 2009-08-25 | 5 | 2009-08-25 | [14 empty] | 2010-12-29 | 2010-12-29 |  | Y
Central Hudson |  | Hudson Solar | CH-01454 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8065 | Merritt Park | N |  | 4 | [13 empty] | NM | N | (1) SPR-4000m | 2009-08-18 | 2009-08-18 | 0 | 2009-08-18 | [14 empty] | 2009-11-09 | 2009-11-19 |  | Y
Central Hudson |  | Hudson Solar | CH-01939 | Newburgh | New Paltz | Ulster | 12561 | G | 5023 | Ohioville | N |  | 2.52 | [13 empty] | NM | N | SunPower SPR 4000m | 2009-08-18 | 2009-08-21 | 3 | 2009-08-21 | [14 empty] | 2009-11-05 | 2009-11-11 |  | Y
Central Hudson |  | Hudson Solar | CH-02308 | Fishkill | Beacon | Dutchess | 12508 | G | 8017 | Forgebrook | N |  | 2.52 | [13 empty] | NM | N | (1) SPR-4000m | 2009-08-18 | 2009-08-18 | 0 | 2009-08-18 | [14 empty] | 2009-12-31 | 2010-01-06 |  | Y
Central Hudson |  | Hudson Solar | CH-02492 | Newburgh | Gardiner | Ulster | 12525 | G | 5011 | Modena | N | CH-01987 | 3.6 | [13 empty] | NM | N | (1) SPR-4000m | 2009-08-18 | 2009-08-19 | 1 | 2009-08-19 | [14 empty] | 2009-11-05 | 2009-11-05 |  | Y
Central Hudson |  | T-KAR Smart Energy Systems | CH-09719 | Fishkill | Fishkill | Dutchess | 12524 | G | 8015 | Forgebrook | N |  | 11.07 | [13 empty] | NM | N | (3) SB4000US | 2009-12-22 | 2009-12-22 | 0 | 2009-12-22 | [14 empty] | 2010-08-18 | 2010-08-24 |  | Y
Central Hudson |  | Solar Generation | CH-08182 | Kingston | Woodstock | Ulster | 12498 | G | 3014 | Woodstock | N | CH-08182 | 9.45 | [13 empty] | NM | N | (1) Fronius 1G 11.4-3 | 2009-08-21 | 2009-08-25 | 2 | 2009-08-25 | [14 empty] | 2009-09-17 | 2009-09-17 |  | Y
Central Hudson |  | Solar Generation | CH-08183 | Kingston | Woodstock | Ulster | 12498 | G | 3014 | Woodstock | N | CH-08182 | 22.68 | [13 empty] | NM | N | (2) Fronius IG 11.4-3 | 2009-08-21 | 2009-08-25 | 2 | 2009-08-25 | [14 empty] | 2009-09-17 | 2009-09-17 |  | Y
Central Hudson |  | 2K Solar Inc | CH-00625 | Newburgh | Campbell Hall | Orange | 10916 | G | 5052 | Maybrook | N |  | 4 | [13 empty] | NM | N | (1) Sunny Boy 4000US | 2009-08-24 | 2009-08-25 | 1 | 2009-08-25 | [14 empty] | 2009-10-26 | 2009-10-26 |  | Y
Central Hudson |  | 2K Solar Inc | CH-00626 | Newburgh | Campbell Hall | Orange | 10916 | G | 5052 | Maybrook | N |  | 8 | [13 empty] | NM | N | (2) Sunny Boy 4000US | 2009-08-24 | 2009-08-25 | 1 | 2009-08-25 | [14 empty] | 2009-10-06 | 2009-10-07 |  | Y
Central Hudson |  | Hudson Solar | CH-01707 | Kingston | Cragsmoor | Ulster | 12420 | G | 3078 | Greenfield Rd | N | CH-01707 | 5 | [13 empty] | NM | N | SPR - 5000m | 2009-08-27 | 2009-08-27 | 0 | 2009-08-27 | [14 empty] | 2009-11-10 | 2009-11-11 |  | Y
Central Hudson |  | Hudson Solar | CH-01558 | Newburgh | New Paltz | Ulster | 12561 | G | 5023 | Ohioville | N |  | 8 | [13 empty] | NM | N | (2) SPR-4000x | 2009-08-31 | 2009-08-31 | 0 | 2009-08-31 | [14 empty] | 2009-09-17 | 2009-09-17 |  | Y
Central Hudson |  | Malcarne Contracting | CH-03900 | Poughkeepsie | Staatsburg | Dutchess | 12580 | G | 7041 | Staatsburg | N |  | 4 | [13 empty] | NM | N | (1) Fronius IG 4000 | 2009-09-03 | 2009-09-09 | 3 | 2009-09-09 | [14 empty] | 2010-08-23 | 2010-08-23 |  | Y
Central Hudson |  | Malcarne Contracting | CH-03908 | Poughkeepsie | Staatsburg | Dutchess | 12580 | G | 7041 | Staatsburg | N | CH-03908 | 4 | [13 empty] | NM | N | (6) Enphase M190-72-240-S11 | 2009-09-03 | 2009-09-09 | 3 | 2009-09-09 | [14 empty] | 2010-08-23 | 2010-08-23 |  | Y
Central Hudson |  | Sunshine Solar Systems LLC | CH-09677 | Newburgh | New Paltz | Ulster | 12561 | G | 5021 | Ohioville | N |  | 8.4 | [13 empty] | NM | N | Enphase Energy M190-24-240 S11 | 2009-09-22 | 2009-09-23 | 1 | 2009-09-23 | [14 empty] | 2010-05-05 | 2010-05-05 |  | Y
Central Hudson |  | Sunnyside Solar | CH-09636 | Poughkeepsie | Poughkeepsie |  | 12601 | G | 6065 | Inwood Ave | TBD |  | 9.36 | [13 empty] | NM | N | (2) SB6000US | 2009-09-11 | 2009-10-20 | 26 | 2009-10-20 | [15 empty] | 2009-11-13 |  | W |  | Contractor performed SIR test and sent documentation 11/11/2009.
Central Hudson |  | Sunnyside Solar | CH-09642 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6065 | Inwood Ave | N |  | 9.36 | [13 empty] | NM | N | (2) SB6000US | 2009-09-11 | 2009-10-20 | 26 | 2009-10-20 | [14 empty] | 2009-11-11 | 2009-11-13 |  | Y
Central Hudson |  | Payneless Energy | CH-02857 | Catskill | Freehold | Greene | 12431 | G | 2071 | Freehold | N |  | 5 | [13 empty] | NM | N | (Fronius IG Plus 5.0-1 UNI | 2009-09-15 | 2009-09-16 | 1 | 2009-09-16 | [14 empty] | 2009-10-27 | 2009-10-29 |  | Y
Central Hudson |  | GreenBeingSolar | CH-01171 | Kingston | Hurley | Ulster | 12443 | G | 2093 | Hurley Ave | N |  | 2.3 | [13 empty] | NM | N | Enphase Energy M190-72-240-S1` | 2009-09-25 | 2009-09-28 | 1 | 2009-09-28 | [14 empty] | 2009-12-04 | 2009-12-09 |  | Y
Central Hudson |  | groSolar | CH-01184 | Catskill | Dormansvl | Albany | 12055 | G | 1091 | Westerlo | N |  | 2.9 | [13 empty] | NM | N | PVMate 2900U | 2009-09-18 | 2009-09-25 | 5 | 2009-09-25 | [14 empty] | 2010-03-19 | 2010-03-24 |  | Y
Central Hudson |  | ISI Solar | CH-02565 | Newburgh | Walden | Orange | 12586 | G | 5043 | East Walden | Y | CH-02564 |  |  | 2.3 | [11 empty] | NM | N | Southwest Windpower Skystream 3.7 | 2009-10-07 | 2009-10-07 | 0 | 2009-10-07 | [14 empty] | 2009-11-23 | 2009-11-23 |  | Y
Central Hudson |  | Hudson Solar | CH-01594 | Catskill | Catskill | Greene | 12414 | G | 2001 | North Catskill | N |  | 8 | [13 empty] | NM | N | (2) SPR-4000m | 2009-09-28 | 2009-09-28 | 0 | 2009-09-28 | [14 empty] | 2010-01-27 | 2010-01-28 |  | Y
Central Hudson |  | Hudson Solar | CH-02103 | Poughkeepsie | Staatsburg | Dutchess | 12580 | G | 7042 | Staatsburg | N |  | 32 | [13 empty] | NM | N | (3) SPR-7000m,(2) SPR-4000m, (1) SPR-3000m | 2009-09-30 | 2009-10-27 | 18 | 2009-10-27 | [14 empty] | 2010-06-16 | 2010-06-23 |  | Y
Central Hudson |  | Sunnyside Solar | CH-09639 | Newburgh | Highland | Ulster | 12589 | G | 5083 | Highland | N |  | 5.8 | [13 empty] | NM | N | SB-6000US | 2009-09-28 | 2009-09-28 | 0 | 2009-09-28 | [14 empty] | 2009-10-08 | 2009-10-08 |  | Y
Central Hudson |  | Sunshine Solar Systems LLC | CH-09670 | Kingston | Ulster Park |  | 12487 | G | 1012 | Boulevard | TBD |  | 1.045 | [13 empty] | NM | N | 6 Enphase Microinveretrs M190-72-240-S11 | 2009-09-28 | 2009-10-02 | 4 | 2009-10-02 | [17 empty] | W |  | Installation abandoned.
Central Hudson |  | Sunshine Solar Systems LLC | CH-09672 | Kingston | Ulster Park. |  | 12487 | G | 1014 | Boulevard | TBD |  | 0.945 | [13 empty] | NM | N | 6 Enphase microinverters M190-72-240-S11 | 2009-09-28 | 2009-10-02 | 4 | 2009-10-02 | [17 empty] | W
Central Hudson |  | Hudson Solar | CH-01600 | Catskill | Prattsvl | Greene | 12468 | E | 2389 | Vinegar Hill | N |  | 4 | [13 empty] | NM | N | SPR-4000m | 2009-10-01 | 2009-10-01 | 0 | 2009-10-01 | [14 empty] | 2009-11-12 | 2009-11-19 |  | Y
Central Hudson |  | Hudson Solar | CH-02434 | Kingston | High Fls | Ulster | 12440 | G | 3022 | High Falls | N | CH-02363 | 4 | [13 empty] | NM | N | SPR-4000m | 2009-10-01 | 2009-10-01 | 0 | 2009-10-01 | [14 empty] | 2010-03-17 | 2010-03-17 |  | Y
Central Hudson |  | Hudson Solar | CH-02193 | Newburgh | New Paltz | Ulster | 12561 | G | 5011 | Modena | N |  | 5 | [13 empty] | NM | N | SunPower SPR-5000m | 2009-10-08 | 2009-10-14 | 3 | 2009-10-14 | [14 empty] | 2010-03-08 | 2010-03-08 |  | Y
Central Hudson |  | SunDog Solar | CH-09138 | Catskill | Elka Pk | Greene | 12427 | G | 2385 | Lawrenceville | N |  | 4 | [13 empty] | NM | N | Fronius IG 4000 | 2009-10-08 | 2009-10-13 | 2 | 2009-10-13 | [14 empty] | 2009-11-18 | 2009-11-23 |  | Y
Central Hudson |  | 1st Light Energy | CH-00590 | Newburgh | Newburgh | Orange | 12550 | G | 4012 | West Balmville | N |  | 5.2 | [13 empty] | NM | N | (1) Fronius IG 4000; (1) Fronius IG 2000 | 2009-10-13 | 2009-10-13 | 0 | 2009-10-13 | [14 empty] | 2009-12-03 | 2009-12-03 |  | Y
Central Hudson |  | RGS Energy | CH-03035 | Poughkeepsie | Millerton | Dutchess | 12546 | G | 7081 | Millerton | N |  | 6 | [13 empty] | NM | N | (1) SPR-6000m | 2009-10-20 | 2009-10-29 | 7 | 2009-10-29 | [14 empty] | 2009-11-02 | 2009-11-02 |  | Y
Central Hudson |  | Conscious Energy | CH-00799 | Newburgh | Gardiner | Ulster | 12525 | G | 5011 | Modena | N |  | 4 | [13 empty] | NM | N | (1) Fronius IG4000 | 2009-10-20 | 2009-10-21 | 1 | 2009-10-21 | [14 empty] | 2009-12-03 | 2009-12-03 |  | Y
Central Hudson |  | Hudson Solar | CH-02458 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6065 | Inwood Ave | N | CH-01819 | 3 | [13 empty] | NM | N | SPR-3000m | 2009-10-20 | 2009-10-20 | 0 | 2009-10-20 | [14 empty] | 2009-12-30 | 2010-01-05 |  | Y
Central Hudson |  | Syracuse Solar and Wind | CH-09705 | Poughkeepsie | Staatsburg | Dutchess | 12580 | G | 7042 | Staatsburg | N |  | 7.56 | [13 empty] | NM | N | 36 enphase microinverters ,M210-84-208-S12 | 2009-11-09 | 2009-11-12 | 3 | 2009-11-12 | [14 empty] | 2009-12-04 | 2009-12-10 |  | Y
Central Hudson |  | Hudson Solar | CH-01839 | Poughkeepsie | Rhinebeck |  | 12572 | G | 7053 | Rhinebeck | TBD |  | 4 | [13 empty] | NM | N | SunPower SPR-4000m | 2009-10-26 | 2009-10-30 | 4 | 2009-10-30 | [17 empty] | W |  | 7/6/12 Installation abandoned as per customer letter.
Central Hudson |  | Hudson Solar | CH-02296 | Poughkeepsie | Milan | Dutchess | 12571 | G | 7061 | Milan | N |  | 8 | [13 empty] | NM | N | 2 Sunpower SPR- 4000m | 2009-10-26 | 2009-10-30 | 4 | 2009-10-30 | [14 empty] | 2010-04-07 | 2010-04-12 |  | Y
Central Hudson |  | Mercury Solar Systems | CH-02623 | Fishkill | Cold Spg | Putnam | 10516 | G | 8063 | Merritt Park | N |  | 20.09 | [13 empty] | NM | N | 3 SB 7000W | 2009-10-26 | 2009-10-29 | 3 | 2009-10-29 | [14 empty] | 2009-12-08 | 2009-12-09 |  | Y
Central Hudson |  | RGS Energy | CH-03048 | Poughkeepsie | Lagrangevl | Dutchess | 12540 | G | 6055 | Todd Hill | N |  | 4 | [13 empty] | NM | N | (1) PVI-4000 | 2009-10-27 | 2009-11-04 | 6 | 2009-11-04 | [14 empty] | 2009-12-21 | 2009-12-21 |  | Y
Central Hudson |  | groSolar | CH-01185 | Kingston | Grahamsvl | Sullivan | 12740 | G | 3091 | Neversink | N |  | 17.5 | [13 empty] | NM | N | 1-Fronius IG Plus 10.0, 1-Fronius IG Plus 7.5 | 2009-10-27 | 2009-11-03 | 5 | 2009-11-03 | [14 empty] | 2010-08-09 | 2010-08-09 |  | Y
Central Hudson |  | Hudson Solar | CH-01325 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7061 | Milan | N |  | 7 | [13 empty] | NM | N | (1) SPR-7000m | 2009-10-27 | 2009-10-28 | 1 | 2009-10-28 | [14 empty] | 2010-02-16 | 2010-02-22 |  | Y
Central Hudson |  | Hudson Solar | CH-01560 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6003 | Reynolds Hill | N |  | 23 | [13 empty] | NM | N | (1) SPR-4000m, (1) SPR-5000m, and (2) SPR-7000m | 2010-04-15 | 2010-04-20 | 3 | 2010-04-20 | [14 empty] | 2010-08-04 | 2010-08-06 |  | Y
Central Hudson |  | Hudson Solar | CH-02508 | Catskill | Catskill |  | 12414 | G | 2006 | North Catskill | TBD |  | 9 | [13 empty] | NM | N | (1) SPR-4000m and (1) SPR-5000m | 2009-10-27 | 2009-10-28 | 1 | 2009-10-28 | [17 empty] | W
Central Hudson |  | Mass Megawatts/Caskill Mountain Wind Management | CH-02609 | Catskill | Tannersvl | Greene | 12485 | G | 2385 | Lawrenceville | N |  |  |  | 7.5 | [11 empty] | NM | N | Beckwith M-3410A Relay | 2009-11-12 | 2009-11-18 | 4 | 2009-11-18 | [14 empty] | 2009-12-10 | 2009-12-17 |  | Y
Central Hudson |  | Solar Generation | CH-08070 | Kingston | West Hurley |  | 12491 | G | 2094 | Hurley Ave | TBD |  | 4 | [13 empty] | NM | N | (1) Fronius IG 4000 | 2009-11-04 | 2009-11-04 | 0 | 2009-11-04 | [15 empty] | 2010-01-05 |  | W |  | Contractor performed SIR test and sent documentation 12/29/2009.
Central Hudson |  | SunDog Solar | CH-09148 | Poughkeepsie | Ancram | Columbia | 12502 | G | 7085 | Ancram | N |  | 5.04 | [13 empty] | NM | N | 28- Emphase micro inverter M-190-72-240-S12 | 2010-01-26 | 2010-02-01 | 4 | 2010-02-01 | [14 empty] | 2010-02-22 | 2010-03-04 |  | Y
Central Hudson |  | Hudson Solar | CH-01449 | Newburgh | New Paltz | Ulster | 12561 | G | 5023 | Ohioville | N |  | 8 | [13 empty] | NM | N | 2-SPR-4000m | 2009-11-05 | 2009-11-11 | 4 | 2009-11-11 | [14 empty] | 2010-06-21 | 2010-06-21 |  | Y
Central Hudson |  | Hudson Solar | CH-01464 | Newburgh | New Paltz | Ulster | 12561 | G | 5023 | Ohioville | N |  | 8 | [13 empty] | NM | N | 2-SPR-4000m | 2009-11-05 | 2009-11-11 | 4 | 2009-11-11 | [14 empty] | 2010-10-13 | 2010-10-13 |  | Y
Central Hudson |  | Hudson Solar | CH-01582 | Newburgh | New Paltz | Ulster | 12561 | G | 5023 | Ohioville | N |  | 8 | [13 empty] | NM | N | SPR 4000M (2) | 2009-11-05 | 2009-11-09 | 2 | 2009-11-09 | [14 empty] | 2010-05-12 | 2010-05-12 |  | Y
Central Hudson |  | Hudson Solar | CH-01586 | Newburgh | New Paltz | Ulster | 12561 | G | 5023 | Ohioville | N |  | 8 | [13 empty] | NM | N | 2-SPR-4000m | 2009-11-05 | 2009-11-11 | 4 | 2009-11-11 | [14 empty] | 2010-05-12 | 2010-05-12 |  | Y
Central Hudson |  | Hudson Solar | CH-01971 | Newburgh | Gardiner | Ulster | 12525 | G | 5034 | Galeville | N | CH-01971 | 8 | [13 empty] | NM | N | (2) SPR-4000m | 2009-11-05 | 2009-11-06 | 1 | 2009-11-06 | [14 empty] | 2010-03-04 | 2010-03-04 |  | Y
Central Hudson |  | Hudson Solar | CH-02076 | Poughkeepsie | Staatsburg | Dutchess | 12580 | G | 7011 | Hibernia | N |  | 4 | [13 empty] | NM | N | (1) SPR-4000m | 2009-11-05 | 2009-11-06 | 1 | 2009-11-06 | [14 empty] | 2010-07-15 | 2010-07-19 |  | Y
Central Hudson |  | Hudson Solar | CH-02465 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7053 | Rhinebeck | N | CH-01404 | 3 | [13 empty] | NM | N | (1)SPR-3000m | 2009-11-05 | 2009-11-06 | 1 | 2009-11-06 | [14 empty] | 2010-07-14 | 2010-07-19 |  | Y
Central Hudson |  | Mercury Solar Systems | CH-02630 | Poughkeepsie | Millerton | Dutchess | 12546 | G | 7081 | Millerton | N |  | 15 | [13 empty] | NM | N | (3) Fronius IG Plus 5.0-1 | 2009-11-05 | 2009-11-06 | 1 | 2009-11-06 | [14 empty] | 2010-06-04 | 2010-06-08 |  | Y
Central Hudson |  | Hudson Solar | CH-01358 | Catskill | Coxsackie |  | 12051 | G | 1076 | Coxsackie | N | CH-01358 | 28 | [13 empty] | RNM | Y | (4) SPR-7000m | 2009-11-06 | 2009-11-11 | 3 | 2009-11-11 | [14 empty] | 2010-10-15 | 2010-10-15 |  | W | Y
Central Hudson |  | Hudson Solar | CH-01370 | Catskill | Coxsackie |  | 12051 | G | 1076 | Coxsackie | N |  | 16 | [13 empty] | NM | N | (2) SB-6000, (1) SB4000 | 2009-11-06 | 2009-11-12 | 4 | 2009-11-12 | [14 empty] | 2011-10-20 | 2011-10-26 |  | W
Central Hudson |  | Hudson Solar | CH-01693 | Kingston | Mount Tremper |  | 12457 | G | 3012 | Woodstock | TBD |  | 9 | [13 empty] | NM | N | (1) SPR-5000m;(1) SPR-4000m | 2009-11-06 | 2009-11-09 | 1 | 2009-11-09 | [17 empty] | W
Central Hudson |  | Hudson Solar | CH-01695 | Kingston | Woodstock | Ulster | 12498 | G | 3014 | Woodstock | N |  | 8 | [13 empty] | NM | N | (2) SPR-4000m | 2009-11-06 | 2009-11-09 | 1 | 2009-11-09 | [14 empty] | 2010-12-28 | 2010-12-28 |  | Y
Central Hudson |  | Hudson Solar | CH-02365 | Kingston | Port Ewen | Ulster | 12466 | G | 1012 | Boulevard | N |  | 5 | [13 empty] | NM | N | SPR-5000m | 2009-11-06 | 2009-11-12 | 4 | 2009-11-12 | [14 empty] | 2010-07-06 | 2010-07-08 |  | Y
Central Hudson |  | Hudson Solar | CH-02461 | Poughkeepsie | Milan |  | 12572 | G | 6073 | East Park | TBD |  | 6 | [13 empty] | NM | N | 1-Sunpower SPR-6000m | 2009-11-19 | 2009-11-23 | 2 | 2009-11-23 | [17 empty] | W
Central Hudson |  | SunDog Solar | CH-09154 | Newburgh | Milton | Ulster | 12547 | G | 5002 | Marlboro | N |  | 42 | [13 empty] | NM | N | (6) SB 7000US | 2009-11-06 | 2009-11-12 | 4 | 2009-11-12 | [14 empty] | 2009-12-08 | 2009-12-09 |  | Y
Central Hudson |  | 2K Solar Inc | CH-00629 | Newburgh | Montgomery | Orange | 12549 | G | 5073 | Montgomery | N |  | 6 | [13 empty] | NM | N | (1) SB 6000 US | 2009-11-09 | 2009-11-09 | 0 | 2009-11-09 | [14 empty] | 2009-12-29 | 2010-01-05 |  | Y
Central Hudson |  | Mannino Electric | CH-02596 | Kingston | High Fls | Ulster | 12440 | G | 3022 | High Falls | N |  | 1.75 | [13 empty] | NM | N | 10 - Enphase microinverters M190-72-240 | 2010-08-09 | 2010-08-10 | 1 | 2010-08-10 | [14 empty] | 2010-09-17 | 2010-09-17 |  | Y
Central Hudson |  | EBM Consulting | CH-01089 | Poughkeepsie | Millerton | Dutchess | 12546 | G | 7081 | Millerton | N | CH-01089 | 4.2 | [13 empty] | NM | N | (1) SB5000US | 2009-11-10 | 2009-11-11 | 1 | 2009-11-11 | [14 empty] | 2010-08-24 | 2010-08-24 |  | Y
Central Hudson |  | Hudson Solar | CH-01234 | Fishkill | Fishkill | Dutchess | 12524 | G | 8011 | Forgebrook | N |  | 20.25 | [13 empty] | NM | N | 3-SPR-7000m inverters | 2009-12-03 | 2009-12-04 | 1 | 2009-12-04 | [14 empty] | 2010-02-23 | 2010-03-04 |  | Y
Central Hudson |  | Hudson Solar | CH-01330 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7058 | Rhinebeck | N |  | 9 | [13 empty] | NM | N | (1) SPR-5000m; (1) SPR-4000m | 2009-11-16 | 2009-11-16 | 0 | 2009-11-16 | [14 empty] | 2010-09-16 | 2010-09-16 |  | Y
Central Hudson |  | Hudson Solar | CH-01373 | Poughkeepsie | Rhinebeck |  | 12572 | G | 7055 | Rhinebeck | TBD |  | 9 | [13 empty] | NM | N | (1) SPR-5000m; (1) SPR-4000m | 2009-11-16 | 2009-11-16 | 0 | 2009-11-16 | [15 empty] | 2010-09-16 |  | W |  | contractor performed SIR test and sent documentation
Central Hudson |  | Hudson Solar | CH-01871 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7058 | Rhinebeck | N |  | 18 | [13 empty] | NM | N | (2) SPR-7000m; (1) SPR-4000m | 2009-11-16 | 2009-11-16 | 0 | 2009-11-16 | [14 empty] | 2010-09-20 | 2010-09-20 |  | Y
Central Hudson |  | Hudson Solar | CH-01872 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7058 | Rhinebeck | N |  | 11 | [13 empty] | NM | N | (1) SPR-7000m; (1) SPR-4000m | 2009-11-16 | 2009-11-16 | 0 | 2009-11-16 | [14 empty] | 2010-09-27 | 2010-09-27 |  | Y
Central Hudson |  | Sun Volt Solar | CH-09128 | Kingston | Kerhonkson | Ulster | 12446 | G | 3081 | Kerhonkson | N |  | 4.1 | [13 empty] | NM | N | 20 enphase M210-84-240-S12 | 2009-11-25 | 2009-12-02 | 3 | 2009-12-02 | [14 empty] | 2010-02-09 | 2010-02-09 |  | Y
Central Hudson |  | RGS Energy | CH-03019 | Catskill | Greenvl | Greene | 12083 | G | 1091 | Westerlo | N | CH-03019 | 7 | [13 empty] | NM | N | SPR-7000m | 2009-11-23 | 2009-12-02 | 5 | 2009-12-02 | [14 empty] | 2010-03-29 | 2010-03-31 |  | Y
Central Hudson |  | RGS Energy | CH-03021 | Catskill | Coxsackie | Greene | 12051 | G | 1074 | Coxsackie | N |  | 3.87 | [13 empty] | NM | N | SPR-4000m | 2009-11-23 | 2009-12-02 | 5 | 2009-12-02 | [14 empty] | 2010-03-05 | 2010-03-08 |  | Y
Central Hudson |  | Hudson Solar | CH-01357 | Newburgh | Newburgh |  | 12550 | G | 4003 | Montgomery St | TBD |  | 16.128 | [13 empty] | NM | N | (3) SMA-6000US | 2009-11-25 | 2009-12-02 | 3 | 2009-12-02 | [14 empty] | 2010-11-29 | 2010-11-29 |  | W |  | Contractor performed SIR test and sent documentation.
Central Hudson |  | Hudson Solar | CH-01936 | Newburgh | Newburgh | Orange | 12550 | G | 4003 | Montgomery St | N |  | 16.128 | [13 empty] | NM | N | (3) SMA-6000US | 2009-11-25 | 2009-12-02 | 3 | 2009-12-02 | [14 empty] | 2010-11-29 | 2010-11-29 |  | Y
Central Hudson |  | RGS Energy | CH-03014 | Catskill | Medusa | Albany | 12120 | G | 1092 | Westerlo | N | CH-03014 | 4.14 | [13 empty] | NM | N | Sunpower SPR-6000m | 2009-12-01 | 2009-12-04 | 3 | 2009-12-04 | [14 empty] | 2010-07-07 | 2010-07-08 |  | Y
Central Hudson |  | Hudson Solar | CH-01853 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7053 | Rhinebeck | N |  | 14.85 | [13 empty] | NM | N | (2) SPR-3000m; (1) SPR-5000m; (1) SPR-4000m | 2009-11-30 | 2009-12-01 | 1 | 2009-12-01 | [14 empty] | 2010-09-29 | 2010-09-29 |  | Y
Central Hudson |  | Hudson Solar | CH-02143 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7055 | Rhinebeck | N |  | 8.19 | [13 empty] | RNM | N | 1-SPR-6000m and 1-SPR-6000m | 2009-11-30 | 2009-12-04 | 4 | 2009-12-04 | [14 empty] | 2010-05-20 | 2010-05-27 |  | Y
Central Hudson |  | Hudson Solar | CH-02144 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7055 | Rhinebeck | N |  | 12 | [13 empty] | NM | N | 2-SPR-6000m | 2009-11-30 | 2009-12-04 | 4 | 2009-12-04 | [14 empty] | 2010-05-20 | 2010-05-27 |  | Y
Central Hudson |  | Hudson Solar | CH-02145 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7055 | Rhinebeck | N |  | 12 | [13 empty] | NM | N | 2-SPR 6000m | 2009-11-30 | 2009-12-04 | 4 | 2009-12-04 | [14 empty] | 2010-05-20 | 2010-05-27 |  | Y
Central Hudson |  | Hudson Solar | CH-02146 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7055 | Rhinebeck | N |  | 13.65 | [13 empty] | NM | N | 1-SPR-6000m, 2-SPR-4000m | 2009-11-30 | 2009-12-04 | 4 | 2009-12-04 | [14 empty] | 2010-05-20 | 2010-05-27 |  | Y
Central Hudson |  | Hudson Solar | CH-02147 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7055 | Rhinebeck | N |  | 14 | [13 empty] | NM | N | 1-SPR 6000m, 2-SPR-4000m | 2009-11-30 | 2009-12-04 | 4 | 2009-12-04 | [14 empty] | 2010-05-20 | 2010-05-27 |  | Y
Central Hudson |  | Hudson Solar | CH-02502 | Newburgh | New Paltz | Ulster | 12561 | G | 5031 | Galeville | N | CH-01944 | 4.928 | [13 empty] | NM | N | (2) Xantrex GT2.8 | 2009-11-30 | 2009-12-01 | 1 | 2009-12-01 | [14 empty] | 2010-03-31 | 2010-03-31 |  | Y
Central Hudson |  | Pure Point Energy LLC | CH-02941 | Newburgh | Milton | Ulster | 12547 | G | 5002 | Marlboro | N |  | 20 | [13 empty] | NM | N | (2) Fronius IG 10.0-1 UNI | 2010-01-05 | 2010-01-05 | 0 | 2010-01-05 | [14 empty] | 2010-05-19 | 2010-05-25 |  | Y
Central Hudson |  | Hudson Solar | CH-01214 | Newburgh | Highland | Ulster | 12528 | G | 5084 | Highland | N | CH-01214 | 39 | [13 empty] | NM | N | (3) SPR-6000m; (3) SPR-7000m | 2009-12-02 | 2009-12-04 | 2 | 2009-12-04 | [14 empty] | 2010-08-04 | 2010-08-10 |  | Y
Central Hudson |  | Hudson Solar | CH-01615 | Catskill | Catskill |  | 12414 | G | 2006 | North Catskill | TBD |  | 4 | [13 empty] | NM | N | Sunpower SPR-4000m | 2009-12-02 | 2009-12-09 | 5 | 2009-12-09 | [17 empty] | W |  | Installation abondoned.
Central Hudson |  | Hudson Solar | CH-02256 | Poughkeepsie | Clinton Corners | Dutchess | 12514 | G | 7013 | Hibernia | N |  | 4 | [13 empty] | NM | N | (1) SPR-4000m | 2009-12-02 | 2009-12-04 | 2 | 2009-12-04 | [14 empty] | 2010-04-30 | 2010-05-05 |  | Y
Central Hudson |  | Solar Generation | CH-08116 | Kingston | Kingston | Ulster | 12401 | G | 1003 | Jansen Ave | N |  | 28.665 | [13 empty] | NM | N | (1) PVP 30lW | 2009-12-03 | 2009-12-03 | 0 | 2009-12-03 | [14 empty] | 2010-01-25 | 2010-01-25 |  | Y
Central Hudson |  | 1st Light Energy | CH-00589 | Newburgh | New Windsor | Orange | 12553 | G | 4095 | Bethlehem Rd | N |  | 6.9 | [13 empty] | NM | N | 1-PVI 4.2 and 1-SB4000US | 2009-12-23 | 2009-12-28 | 1 | 2009-12-28 | [14 empty] | 2010-01-07 | 2010-01-07 |  | Y
Central Hudson |  | Mountain View Services, Inc. | CH-02703 | Catskill | Westerlo | Albany | 12193 | G | 1091 | Westerlo | N | CH-02703 | 1.8 | [13 empty] | NM | N | (1) Solectria PVI 1800 | 2009-12-09 | 2009-12-15 | 4 | 2009-12-15 | [14 empty] | 2010-01-19 | 2010-01-22 |  | Y
Central Hudson |  | Sunshine Solar Systems LLC | CH-09678 | Newburgh | Esopus |  | 12429 | G | 5084 | Highland | TBD |  | 2.3 | [13 empty] | NM | N | 16-Enphase 190-72-240-S12 microinverters | 2009-12-15 | 2009-12-15 | 0 | 2009-12-15 | [17 empty] | W
Central Hudson |  | Sunshine Solar Systems LLC | CH-09679 | Newburgh | Esopus |  | 12429 | G | 5084 | Highland | TBD |  | 20.9 | [13 empty] | NM | N | 16-Enphase M190-72-240-S12 | 2009-12-09 | 2009-12-15 | 4 | 2009-12-15 | [8 empty] | 1739 | 1738.51 | [7 empty] | W
Central Hudson |  | Conscious Energy | CH-00803 | Newburgh | Gardiner | Ulster | 12525 | G | 5011 | Modena | N |  | 6.56 | [13 empty] | NM | N | (1) SB 7000US | 2009-12-10 | 2009-12-11 | 1 | 2009-12-11 | [14 empty] | 2010-01-05 | 2010-01-06 |  | Y
Central Hudson |  | Sunshine Solar Systems LLC | CH-09671 | Newburgh | Esopus |  | 12429 | G | 5084 | Highland | TBD |  | 2.3 | [13 empty] | NM | N | (16) M190-72-240-S12 Microinverters | 2009-12-10 | 2009-12-15 | 3 | 2009-12-15 | [17 empty] | W
Central Hudson |  | Hudson Solar | CH-01431 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8093 | Fishkill Plains | N |  | 7.14 | [13 empty] | NM | N | (2) SPR-4000m | 2009-12-11 | 2009-12-15 | 2 | 2009-12-15 | [14 empty] | 2010-07-08 | 2010-07-12 |  | Y
Central Hudson |  | Hudson Solar | CH-01505 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8091 | Fishkill Plains | N |  | 4.2 | [13 empty] | NM | N | SPR-4000m | 2009-12-11 | 2009-12-15 | 2 | 2009-12-15 | [14 empty] | 2010-04-30 | 2010-05-04 |  | Y
Central Hudson |  | Hudson Solar | CH-01778 | Poughkeepsie | Wingdale | Dutchess | 12594 | G | 6055 | Todd Hill | N |  | 5 | [13 empty] | NM | N | (1) SPR-5000m | 2009-12-11 | 2009-12-15 | 2 | 2009-12-15 | [14 empty] | 2010-08-02 | 2010-08-03 |  | Y
Central Hudson |  | Hudson Solar | CH-01910 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8091 | Fishkill Plains | N | CH-01910 | 8 | [13 empty] | NM | N | (2) SPR-4000m | 2009-12-11 | 2009-12-15 | 2 | 2009-12-15 | [14 empty] | 2010-06-29 | 2010-07-02 |  | Y
Central Hudson |  | Hudson Solar | CH-02302 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8092 | Fishkill Plains | N |  | 5 | [13 empty] | NM | N | SPR-5000m | 2009-12-11 | 2009-12-15 | 2 | 2009-12-15 | [14 empty] | 2010-08-02 | 2010-08-06 |  | Y
Central Hudson |  | Solar Generation | CH-08185 | Kingston | Saugerties | Ulster | 12477 | G | 3002 | Saugerties | N |  | 49.14 | [13 empty] | NM | N | (1) Satcon PVS-50 | 2010-02-01 | 2010-02-03 | 2 | 2010-02-03 | [14 empty] | 2010-06-01 | 2010-06-01 |  | Y
Central Hudson |  | Solar Generation | CH-08186 | Kingston | Saugerties | Ulster | 12477 | G | 3002 | Saugerties | N | CH-08186 | 47.98 | [13 empty] | NM | N | (1) Satcon PVS-50 | 2010-02-01 | 2010-02-03 | 2 | 2010-02-03 | [14 empty] | 2010-06-01 | 2010-06-01 |  | Y
Central Hudson |  | Hudson Solar | CH-02073 | Poughkeepsie | Staatsburg | Dutchess | 12580 | G | 7041 | Staatsburg | N |  | 4 | [13 empty] | NM | N | Sunpower SPR4000-m | 2009-12-15 | 2009-12-17 | 2 | 2009-12-17 | [14 empty] | 2010-08-13 | 2010-08-20 |  | Y
Central Hudson |  | Hudson Solar | CH-02462 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7053 | Rhinebeck | N | CH-01842 | 3.6 | [13 empty] | NM | N | (1) SPR-4000m | 2009-12-15 | 2009-12-16 | 1 | 2009-12-16 | [14 empty] | 2010-03-19 | 2010-03-25 |  | Y
Central Hudson |  | Stephen Lee | CH-09077 | Poughkeepsie | Millerton | Dutchess | 12546 | G | 7081 | Millerton | N |  | 18 | [13 empty] | NM | N | 3 - SPR 6000-m | 2010-01-25 | 2010-02-01 | 5 | 2010-02-01 | [14 empty] | 2011-03-25 | 2011-03-29 |  | Y
Central Hudson |  | Hudson Solar | CH-01341 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8092 | Fishkill Plains | N |  | 4.9 | [13 empty] | NM | N | SPR-5000m (1) | 2009-12-18 | 2009-12-21 | 1 | 2009-12-21 | [14 empty] | 2012-07-05 | 2012-07-09 |  | Y
Central Hudson |  | Hudson Solar | CH-01840 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7053 | Rhinebeck | N |  | 5 | [13 empty] | NM | N | (1) SPR-5000m | 2009-12-18 | 2009-12-21 | 1 | 2009-12-21 | [14 empty] | 2010-07-02 | 2010-07-07 |  | Y
Central Hudson |  | Hudson Solar | CH-02292 | Poughkeepsie | Millerton | Dutchess | 12546 | G | 7081 | Millerton | N |  | 14.7 | [13 empty] | NM | N | (3) Xantrex GT5.0 | 2009-12-18 | 2009-12-21 | 1 | 2009-12-21 | [14 empty] | 2010-09-17 | 2010-09-20 |  | Y
Central Hudson |  | Solar Works | CH-09055 | Newburgh | New Paltz | Ulster | 12561 | G | 5031 | Galeville | N |  | 2 | [13 empty] | NM | N | (1) GC-1000 | 2009-12-22 | 2009-12-22 | 0 | 2009-12-22 | [14 empty] | 2009-12-22 | 2009-12-22 |  | W
Central Hudson |  | Sunshine Solar Systems LLC | CH-09680 | Newburgh | New Paltz |  | 12561 | G | 5023 | Ohioville | TBD |  | 4.2 | [13 empty] | NM | N | 24-Enphase Microinverters M190-72-240-S12 | 2010-01-08 | 2010-01-14 | 4 | 2010-01-14 | [17 empty] | W
Central Hudson |  | 1st Light Energy | CH-00586 | Newburgh | New Windsor | Orange | 12553 | G | 4095 | Bethlehem Rd | N |  | 6.4 | [13 empty] | NM | N | (2) SPR-3000 | 2009-12-29 | 2010-01-04 | 3 | 2010-01-04 | [14 empty] | 2010-01-07 | 2010-01-14 |  | Y
Central Hudson |  | 1st Light Energy | CH-00593 | Newburgh | New Windsor | Orange | 12553 | G | 4095 | Bethlehem Rd | N |  | 7 | [13 empty] | NM | N | (1) SB 4000US; (1) SB 3000US | 2009-12-29 | 2010-01-04 | 3 | 2010-01-04 | [14 empty] | 2010-01-07 | 2010-01-13 |  | Y
Central Hudson |  | groSolar | CH-01183 | Kingston | Accord | Ulster | 12404 | G | 3082 | Kerhonkson | N |  | 10 | [13 empty] | NM | N | (1) SB 7000US; (1) SB 3000US | 2009-12-31 | 2010-01-07 | 4 | 2010-01-07 | [14 empty] | 2010-10-01 | 2010-10-01 |  | Y
Central Hudson |  | groSolar | CH-01186 | Poughkeepsie | Pine Plns | Dutchess | 12567 | G | 7091 | Pulvers Corners | N |  | 6.72 | [13 empty] | NM | N | 1-Fronius IGP 3.8 and 1-Fronius 3.0 | 2010-01-12 | 2010-01-15 | 3 | 2010-01-15 | [14 empty] | 2010-08-12 | 2010-08-18 |  | Y
Central Hudson |  | Solar Works | CH-09058 | Kingston | Cottekill |  | 12419 | G | 3021 | High Falls | TBD |  | 1 | [13 empty] | NM | N | (1) GC-1000 | 2010-01-07 | 2010-01-08 | 1 | 2010-01-08 | [15 empty] | 2010-01-08 |  | W |  | Customer already had net meter prior to application. PV installed by previous customer. Account transferred from 3152-0570-11 to 3152-0570-12 eff 11/22/2011.
Central Hudson |  | Solar Works | CH-09059 | Kingston | Cottekill | Ulster | 12419 | G | 3021 | High Falls | N | CH-09059 | 1 | [13 empty] | NM | N | (1) GC-1000 | 2010-01-07 | 2010-01-08 | 1 | 2010-01-08 | [14 empty] | 2010-01-07 | 2010-01-08 |  | Y
Central Hudson |  | RGS Energy | CH-03026 | Catskill | New Baltimore | Greene | 12124 | G | 1083 | New Baltimore | N |  | 6.88 | [13 empty] | NM | N | SPR-7000m | 2010-01-08 | 2010-01-12 | 2 | 2010-01-12 | [14 empty] | 2010-06-21 | 2010-06-23 |  | Y
Central Hudson |  | 1st Light Energy | CH-00588 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8055 | North Chelsea | N |  | 4 | [13 empty] | NM | N | Fronius IG 4000 | 2010-01-11 | 2010-01-15 | 4 | 2010-01-15 | [14 empty] | 2010-03-16 | 2010-03-22 |  | Y
Central Hudson |  | Hudson Solar | CH-01272 | Kingston | Kingston | Ulster | 12401 | G | 2094 | Hurley Ave | N |  | 4 | [13 empty] | NM | N | (1) SPR-4000m | 2010-01-11 | 2010-01-11 | 0 | 2010-01-11 | [14 empty] | 2010-10-11 | 2010-10-11 |  | Y
Central Hudson |  | Hudson Solar | CH-02455 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7013 | Hibernia | N | CH-01215 | 2.1 | [13 empty] | NM | N | SPR-4000m | 2010-01-11 | 2010-01-14 | 3 | 2010-01-14 | [14 empty] | 2010-08-04 | 2010-08-10 |  | Y
Central Hudson |  | Hudson Solar | CH-02467 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7061 | Milan | N | CH-01327 | 4 | [13 empty] | NM | N | SPR-4000m | 2010-01-11 | 2010-01-12 | 1 | 2010-01-12 | [14 empty] | 2010-07-30 | 2010-08-03 |  | Y
Central Hudson |  | Hudson Solar | CH-01868 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7062 | Milan | N |  | 9 | [13 empty] | NM | N | 1-SPR 4000m and 1-SPR5000m | 2010-01-12 | 2010-01-15 | 3 | 2010-01-15 | [14 empty] | 2010-08-05 | 2010-08-11 |  | Y
Central Hudson |  | Hudson Solar | CH-02218 | Newburgh | Rock Tvrn | Orange | 12575 | G | 4097 | Bethlehem Rd | N | CH-02218 | 3.6 | [13 empty] | NM | N | (1) SPR-4000m | 2010-01-12 | 2010-01-12 | 0 | 2010-01-12 | [14 empty] | 2010-06-14 | 2010-06-14 |  | Y
Central Hudson |  | RGS Energy | CH-03055 | Poughkeepsie | Lagrangevl | Dutchess | 12540 | G | 6055 | Todd Hill | N |  | 4 | [13 empty] | NM | N | Solectria PVI4000 | 2010-01-13 | 2010-01-20 | 5 | 2010-01-20 | [14 empty] | 2010-06-03 | 2010-06-03 |  | Y
Central Hudson |  | Hudson Solar | CH-01710 | Kingston | Neversink | Sullivan | 12765 | G | 3091 | Neversink | N |  | 8 | [13 empty] | NM | N | (2) SPR-4000m (2) SPR-4000m | 2010-01-13 | 2010-01-13 | 0 | 2010-01-13 | [14 empty] | 2010-08-26 | 2010-08-27 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03590 | Newburgh | New Paltz | Ulster | 12561 | G | 5011 | Modena | N | CH-03590 | 4.995 | [13 empty] | NM | N | (1) SB 5000 US | 2010-01-20 | 2010-01-20 | 0 | 2010-01-20 | [14 empty] | 2010-02-01 | 2010-02-01 |  | Y
Central Hudson |  | Hudson Solar | CH-01311 | Poughkeepsie | Ancram | Columbia | 12502 | G | 7085 | Ancram | N |  | 24 | [13 empty] | NM | N | (5) PVP4800 | 2010-01-14 | 2010-01-20 | 4 | 2010-01-20 | [14 empty] | 2010-05-21 | 2010-05-28 |  | Y
Central Hudson |  | Hudson Solar | CH-01907 | Newburgh | Highland |  | 12528 | G | 5082 | Highland | TBD |  | 6.75 | [13 empty] | NM | N | SPR-4000m, SPR-3000m | 2010-01-14 | 2010-01-20 | 4 | 2010-01-20 | [17 empty] | W |  | Installation abandoned.
Central Hudson |  | Hudson Solar | CH-01212 | Kingston | Kingston |  | 12401 | G | 2015 | Lincoln Park | TBD |  | 78 | [13 empty] | NM | N | (9) SPR-6000m; (6) SPR-4000m | 2010-01-19 | 2010-01-19 | 0 | 2010-01-19 | [17 empty] | W
Central Hudson |  | Hudson Solar | CH-01302 | Poughkeepsie | Poughquag | Dutchess | 12570 | G | 6055 | Todd Hill | N |  | 7 | [13 empty] | NM | N | (1) SPR-7000m | 2010-01-15 | 2010-01-15 | 0 | 2010-01-15 | [14 empty] | 2010-07-15 | 2010-07-19 |  | Y
Central Hudson |  | Hudson Solar | CH-01337 | TBD | Stanfordville |  | 12581 | Tbd | TBD | Tbd | TBD |  | 8 | [13 empty] | NM | N | (2) SPR-4000m | 2010-01-15 | 2010-01-15 | 0 | 2010-01-15 | [17 empty] | W |  | Installation abandoned.
Central Hudson |  | Solar Generation | CH-08244 | Kingston | Saugerties | Ulster | 12477 | G | 3014 | Woodstock | N |  | 4 | [13 empty] | NM | N | (1) SB 4000 US | 2010-04-15 | 2010-04-27 | 8 | 2010-04-27 | [14 empty] | 2010-04-15 | 2010-04-27 |  | Y
Central Hudson |  | RGS Energy | CH-03005 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8071 | Shenandoah | N |  | 6 | [13 empty] | NM | N | SPR-6000m | 2010-01-22 | 2010-01-28 | 4 | 2010-01-28 | [14 empty] | 2010-03-15 | 2010-03-19 |  | Y
Central Hudson |  | Sun Mountain | CH-09097 | Kingston | Tillson | Ulster | 12486 | G | 3022 | High Falls | N |  | 16 | [13 empty] | NM | N | (2) SB 8000 US | 2010-01-22 | 2010-01-22 | 0 | 2010-01-22 | [14 empty] | 2010-07-21 | 2010-07-23 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03688 | Newburgh | New Paltz | Ulster | 12561 | G | 5031 | Galeville | N |  | 6.7 | [13 empty] | NM | N | (1) SB 7000 | 2010-01-25 | 2010-01-25 | 0 | 2010-01-25 | [14 empty] | 2010-03-09 | 2010-03-09 |  | Y
Central Hudson |  | Hudson Solar | CH-01362 | Poughkeepsie | Poughkeepsie |  | 12603 | G | 6097 | Manchester | TBD |  | 79 | [13 empty] | NM | N | 1 Satcon PVS-75 and 1 SPR 4000m | 2010-02-09 | 2010-02-09 | 0 | 2010-02-09 | [17 empty] | W |  | Application complete letter sent on 2/3/2010.
Central Hudson |  | Lighthouse Solar | CH-03683 | Newburgh | New Paltz | Ulster | 12561 | G | 5021 | Ohioville | N |  | 8 | [13 empty] | NM | N | SB8000 | 2010-02-08 | 2010-02-08 | 0 | 2010-02-08 | [14 empty] | 2010-03-04 | 2010-03-04 |  | Y
Central Hudson |  | RGS Energy | CH-03054 | Newburgh | New Windsor | Orange | 12553 | G | 4094 | Bethlehem Rd | N |  | 7 | [13 empty] | NM | N | SPR 7000M | 2010-02-09 | 2010-02-09 | 0 | 2010-02-09 | [14 empty] | 2010-04-26 | 2010-04-26 |  | Y
Central Hudson |  | Self | CH-08878 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6052 | Todd Hill | N | CH-08878 | 1.29 | [13 empty] | NM | N | Enphase M215 (6) | 2013-11-11 | 2013-11-14 | 3 | 2013-11-14 | [14 empty] | 2014-01-10 | 2014-01-22 |  | Y
Central Hudson |  | RGS Energy | CH-02996 | Kingston | Port Ewen | Ulster | 12466 | G | 1012 | Boulevard | N |  | 75 | [13 empty] | NM | N | Satcon Powergate Plus PVS-75 | 2010-02-16 | 2010-02-23 | 5 | 2010-02-23 | [14 empty] | 2010-06-02 | 2010-06-02 |  | Y
Central Hudson |  | Archibald Heating and A/C | CH-00721 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7056 | Rhinebeck | N | [9 empty] | 1.8 | [5 empty] | NM | N | Micro CHP Inverter | 2010-02-26 | 2010-03-05 | 5 | 2010-03-05 | [14 empty] | 2010-03-26 | 2010-03-31 |  | Y
Central Hudson |  | 1st Light Energy | CH-00587 | Newburgh | Cornwall | Orange | 12518 | G | 4041 | Union Ave | N |  | 5 | [13 empty] | NM | N | SB5000US | 2010-03-10 | 2010-03-10 | 0 | 2010-03-10 | [14 empty] | 2010-08-02 | 2010-08-03 |  | Y
Central Hudson |  | Green Building and Material Supply, Inc. | CH-01156 | Newburgh | Newburgh | Orange | 12550 | G | 4013 | West Balmville | N |  | 14 | [13 empty] | NM | N | Fronius IG Plus 5.0-1 UNI | 2010-03-08 | 2010-03-10 | 2 | 2010-03-10 | [14 empty] | 2010-07-21 | 2010-07-23 |  | Y
Central Hudson |  | Sun Volt Solar | CH-09127 | Kingston | Kerhonkson | Ulster | 12446 | G | 3081 | Kerhonkson | N |  | 4.6 | [13 empty] | NM | N | Enphase M190-72-240-S12 | 2010-03-08 | 2010-03-10 | 2 | 2010-03-10 | [14 empty] | 2010-11-01 | 2010-11-01 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03787 | Newburgh | New Paltz | Ulster | 12561 | G | 5031 | Galeville | N |  | 4.44 | [13 empty] | NM | N | Enphase M190-72-240 | 2010-03-11 | 2010-03-15 | 2 | 2010-03-15 | [14 empty] | 2010-03-29 | 2010-03-29 |  | Y
Central Hudson |  | Self | CH-08895 | Kingston | Kingston | Ulster | 12401 | G | 1022 | East Kingston | N | CH-02951 | 1.05 | [13 empty] | NM | N | Fronius IG 2000 | 2010-03-16 | 2010-03-19 | 3 | 2010-03-19 | [14 empty] | 2010-05-07 | 2010-05-07 |  | Y
Central Hudson |  | RGS Energy | CH-03012 | Catskill | Catskill | Greene | 12414 | G | 2042 | South Cairo | N |  | 5 | [13 empty] | NM | N | Sunny Boy 5000 US | 2010-03-17 | 2010-03-23 | 4 | 2010-03-23 | [14 empty] | 2010-07-06 | 2010-07-08 |  | Y
Central Hudson |  | RGS Energy | CH-03032 | Poughkeepsie | Clinton Corners |  | 12514 | G | 7072 | Stanfordville | TBD |  | 7 | [13 empty] | NM | N | Sunny Boy SMA 7 | 2010-03-17 | 2010-03-23 | 4 | 2010-03-23 | [17 empty] | W
Central Hudson |  | Conscious Energy | CH-00794 | Newburgh | Highland | Ulster | 12528 | G | 5022 | Ohioville | N |  | 3.9 | [13 empty] | NM | N | Solectria PVI 4000 | 2010-03-19 | 2010-03-23 | 2 | 2010-03-23 | [14 empty] | 2010-04-09 | 2010-04-09 |  | Y
Central Hudson |  | RGS Energy | CH-03027 | Catskill | Coeymans | Albany | 12045 | G | 1082 | New Baltimore | N | CH-03027 | 2.5 | [13 empty] | NM | N | Fronius IG 3000 | 2010-03-23 | 2010-03-30 | 5 | 2010-03-30 | [14 empty] | 2010-07-06 | 2010-07-08 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03723 | Newburgh | New Paltz | Ulster | 12561 | G | 5021 | Ohioville | N |  | 4.995 | [13 empty] | NM | N | SB 5000 US | 2010-04-01 | 2010-04-05 | 1 | 2010-04-05 | [14 empty] | 2010-04-27 | 2010-04-27 |  | Y
Central Hudson |  | SunDog Solar | CH-09143 | Catskill | Ravena | Albany | 12143 | G | 1081 | New Baltimore | N |  | 4 | [13 empty] | NM | N | Fronius IG 4000 | 2010-04-05 | 2010-04-06 | 1 | 2010-04-06 | [14 empty] | 2010-04-19 | 2010-04-21 |  | Y
Central Hudson |  | RGS Energy | CH-03017 | Catskill | Rensselaervle | Albany | 12147 | G | 1092 | Westerlo | N |  | 5.94 | [13 empty] | NM | N | Sunny Boy 6000US | 2010-04-05 | 2010-04-07 | 2 | 2010-04-07 | [14 empty] | 2010-09-22 | 2010-09-22 |  | Y
Central Hudson |  | Hudson Solar | CH-02208 | Newburgh | Gardiner | Ulster | 12525 | G | 5031 | Galeville | N |  | 4.99 | [13 empty] | NM | N | SunPower SPR-5000m | 2010-04-07 | 2010-04-14 | 5 | 2010-04-14 | [14 empty] | 2010-05-21 | 2010-05-21 |  | Y
Central Hudson |  | OnForce Solar | CH-02808 | Newburgh | Cornwall | Orange | 12518 | G | 4041 | Union Ave | N |  | 6 | [13 empty] | NM | N | SMA SB6000US | 2010-04-07 | 2010-04-12 | 3 | 2010-04-12 | [14 empty] | 2010-06-28 | 2010-06-29 |  | Y
Central Hudson |  | Hudson Solar | CH-02162 | Poughkeepsie | Stanfordvl | Dutchess | 12581 | G | 7072 | Stanfordville | N |  | 4.95 | [13 empty] | NM | N | 2-SPR 3000m | 2010-04-15 | 2010-04-20 | 3 | 2010-04-20 | [14 empty] | 2010-09-07 | 2010-09-07 |  | Y
Central Hudson |  | Hudson Solar | CH-01286 | Kingston | Bearsvl | Ulster | 12409 | G | 3012 | Woodstock | N | CH-01286 | 4.998 | [13 empty] | NM | N | (2) SPR-3000m | 2010-04-20 | 2010-04-27 | 5 | 2010-04-27 | [14 empty] | 2011-01-05 | 2011-01-05 |  | Y
Central Hudson |  | Hudson Solar | CH-01603 | Catskill | S Cairo |  | 12482 | G | 2005 | North Catskill | TBD |  | 8.1 | [13 empty] | NM | N | 1 Xantrex GT-5.0 and 1 Zantrex GT-3.3 | 2010-04-24 | 2010-05-06 | 9 | 2010-05-06 | [17 empty] | W |  | Application Complete letter sent out 4/23/2010. Performing engineering review of transformer. Prelim. Approval sent out on 5/6/2010. Installation abandoned.
Central Hudson |  | Hudson Solar | CH-02348 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7062 | Milan | N |  | 1.62 | [13 empty] | NM | N | PVP Powered PVP-2000 | 2010-04-27 | 2010-04-28 | 1 | 2010-04-28 | [14 empty] | 2010-06-22 | 2010-06-24 |  | Y
Central Hudson |  | Prism Solar Technologies | CH-02938 | Newburgh | Highland | Ulster | 12528 | G | 5024 | Ohioville | N |  | 0.24 | [13 empty] | NM | N | Enphase M210-84-208 | 2010-04-28 | 2010-05-05 | 5 | 2010-05-05 | [14 empty] | 2010-06-29 | 2010-07-02 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03747 | Newburgh | New Paltz | Ulster | 12561 | G | 5031 | Galeville | N |  | 3.33 | [13 empty] | NM | N | SB 4000 | 2010-04-29 | 2010-05-04 | 3 | 2010-05-04 | [14 empty] | 2010-05-14 | 2010-05-14 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03748 | Newburgh | New Paltz |  | 12561 | G | 5021 | Ohioville | TBD |  | 3.33 | [13 empty] | NM | N | SB 4000 | 2010-04-29 | 2010-05-04 | 3 | 2010-05-04 | [15 empty] | 2010-05-14 |  | W |  | Contractor performed SIR test on 5/14/2010 and sent documentation on 5/18/2010.
Central Hudson |  | Lighthouse Solar | CH-03754 | Newburgh | New Paltz | Ulster | 12561 | G | 5021 | Ohioville | N | CH-03754 | 3.5 | [13 empty] | NM | N | PVP 3500 | 2010-04-29 | 2010-05-04 | 3 | 2010-05-04 | [14 empty] | 2010-05-13 | 2010-05-13 |  | Y
Central Hudson |  | Damiani and Sun Inc. | CH-00818 | Newburgh | Wallkill | Ulster | 12589 | G | 5043 | East Walden | N |  | 6.9 | [13 empty] | NM | N | SMA SB 7000US | 2010-04-30 | 2010-05-06 | 4 | 2010-05-06 | [14 empty] | 2010-08-04 | 2010-08-04 |  | Y
Central Hudson |  | Sunshine Solar Systems LLC | CH-09674 | Newburgh | Gardiner |  | 12525 | G | 5011 | Modena | TBD |  | 16.24 | [13 empty] | NM | N | Enphase M190-72-240-S12 | 2010-05-04 | 2010-05-11 | 5 | 2010-05-11 | [17 empty] | W
Central Hudson |  | Sunshine Solar Systems LLC | CH-09675 | Newburgh | Gardiner |  | 12525 | G | 5011 | Modena | TBD |  | 16.24 | [13 empty] | NM | N | Enphase M190-72-240-S12 | 2010-05-04 | 2010-05-11 | 5 | 2010-05-11 | [17 empty] | W
Central Hudson |  | Hudson Solar | CH-02191 | Newburgh | Gardiner | Ulster | 12525 | G | 5034 | Galeville | N |  | 3 | [13 empty] | NM | N | SunPower SPR-3000a | 2010-05-05 | 2010-05-07 | 2 | 2010-05-07 | [14 empty] | 2010-09-07 | 2010-09-07 |  | Y
Central Hudson |  | Hudson Solar | CH-01361 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7052 | Rhinebeck | N | CH-01361 | 10 | [13 empty] | NM | N | SPR -4000m and SPR-6000m | 2010-05-06 | 2010-05-06 | 0 | 2010-05-06 | [14 empty] | 2010-10-12 | 2010-10-12 |  | Y
Central Hudson |  | Hudson Solar | CH-01508 | Fishkill | Stormville | Dutchess | 12582 | G | 8071 | Shenandoah | N |  | 3.44 | [13 empty] | NM | N | SPR-4000m | 2010-05-06 | 2010-05-12 | 4 | 2010-05-12 | [14 empty] | 2010-12-31 | 2010-12-31 |  | Y
Central Hudson |  | Hudson Solar | CH-01828 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7056 | Rhinebeck | N |  | 10 | [13 empty] | NM | N | 2-SPR-500m | 2010-05-12 | 2010-05-27 | 11 | 2010-05-27 | [14 empty] | 2010-12-13 | 2010-12-13 |  | Y
Central Hudson |  | Hudson Solar | CH-02176 | Fishkill | Stormville | Dutchess | 12582 | G | 8071 | Shenandoah | N |  | 5 | [13 empty] | NM | N | SPR-5000m | 2010-05-06 | 2010-05-12 | 4 | 2010-05-12 | [14 empty] | 2010-12-31 | 2010-12-31 |  | Y
Central Hudson |  | UniAssociates | CH-09727 | Catskill | Catskill | Greene | 12414 | G | 2001 | North Catskill | Y | CH-09727 | 3.8 | [13 empty] | NM | N | Sunny Boy 3800 U | 2010-12-03 | 2010-12-06 | 1 | 2010-12-06 | [14 empty] | 2011-03-31 | 2011-04-07 |  | Y
Central Hudson |  | UniAssociates | CH-09728 | Catskill | Catskill |  | 12414 | G | 2001 | North Catskill | TBD |  | 1.9 |  | 3.8 | [11 empty] | NM | N | SkyStream3.7 ISSL10120 | 2010-12-03 | 2010-12-06 | 1 | 2010-12-06 | [14 empty] | 2011-03-31 | 2011-04-07 |  | W |  | System was already installed when CHGE received application. Application incomplete letter sent out 5/19/10.
Central Hudson |  | UniAssociates | CH-09730 | Catskill | Catskill | Greene | 12414 | G | 2001 | North Catskill | Y | CH-09727 |  |  | 1.9 | [11 empty] | NM | N | Southwest Windpower Skystream 3.7 | 2010-12-03 | 2010-12-06 | 1 | 2010-12-06 | [14 empty] | 2011-03-31 | 2011-04-07 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03612 | Newburgh | Wallkill | Ulster | 12589 | G | 5031 | Galeville | N |  | 3.33 | [13 empty] | NM | N | Sunny Boy SB 4000US | 2010-05-13 | 2010-05-17 | 2 | 2010-05-17 | [14 empty] | 2010-05-25 | 2010-05-25 |  | Y
Central Hudson |  | Sunnyside Solar | CH-09643 | Kingston | Saugerties |  | 12477 | G | 3002 | Saugerties | TBD |  | 8 | [13 empty] | NM | N | SB 8000 US | 2010-05-19 | 2010-05-21 | 2 | 2010-05-21 | [8 empty] | 350 | 350 | [7 empty] | W
Central Hudson |  | EBM Consulting | CH-01090 | Poughkeepsie | Millerton | Dutchess | 12546 | G | 7081 | Millerton | N |  | 3 | [13 empty] | NM | N | Fronius IG 3000 | 2010-06-07 | 2010-06-07 | 0 | 2010-06-07 | [14 empty] | 2010-07-21 | 2010-07-23 |  | Y
Central Hudson |  | T-KAR Smart Energy Systems | CH-09721 | Newburgh | Gardiner | Ulster | 12525 | G | 5011 | Modena | N |  | 13.8 | [13 empty] | NM | N | Enphase M190-72-208-12 | 2010-06-04 | 2010-06-07 | 1 | 2010-06-07 | [14 empty] | 2010-10-27 | 2010-10-27 |  | Y
Central Hudson |  | groSolar | CH-01189 | Kingston | Grahamsvl | Sullivan | 12740 | G | 3091 | Neversink | N |  | 5.28 | [13 empty] | NM | N | PV Powered PVP-2500 and PVP-3000 | 2010-06-09 | 2010-06-09 | 0 | 2010-06-09 | [14 empty] | 2010-11-24 | 2010-11-24 |  | Y
Central Hudson |  | Mercury Solar Systems | CH-02620 | Kingston | Accord | Ulster | 12404 | G | 3024 | High Falls | N |  | 10 | [13 empty] | NM | N | 2-Sun Power SPR-5000m | 2010-06-24 | 2010-06-28 | 2 | 2010-06-28 | [14 empty] | 2010-12-10 | 2010-12-10 |  | Y
Central Hudson |  | Hudson Solar | CH-01228 | Kingston | Kingston | Ulster | 12401 | G | 1021 | East Kingston | N |  | 5.88 | [13 empty] | NM | N | 2 SunPower SPR-3000m | 2010-06-10 | 2010-06-14 | 2 | 2010-06-14 | [14 empty] | 2010-09-30 | 2010-09-30 |  | Y
Central Hudson |  | Hudson Solar | CH-02175 | Fishkill | Glenham |  | 12527 | G | 8015 | Forgebrook | TBD |  | 3.87 | [13 empty] | NM | N | SunPower SPR-4000m | 2010-06-10 | 2010-06-15 | 3 | 2010-06-15 | [17 empty] | W |  | Installation abandoned.
Central Hudson |  | Hudson Solar | CH-02249 | Kingston | Saugerties | Ulster | 12477 | G | 2015 | Lincoln Park | N | CH-02249 | 5 | [13 empty] | NM | N | Sunpower SPR 5000m | 2010-06-10 | 2010-06-15 | 3 | 2010-06-15 | [14 empty] | 2010-09-21 | 2010-09-21 |  | Y
Central Hudson |  | Hudson Solar | CH-02451 | Poughkeepsie | Clinton Corners |  | 12514 | G | 7071 | Stanfordville | TBD |  | 5.52 | [13 empty] | NM | N | SunPower SPR-6000m | 2010-06-10 | 2010-06-16 | 4 | 2010-06-16 | [17 empty] | W |  | Installation abandoned.
Central Hudson |  | Lighthouse Solar | CH-03631 | Newburgh | New Paltz | Ulster | 12561 | G | 5023 | Ohioville | N |  | 3.7 | [13 empty] | NM | N | Enphase M190-72-240 | 2010-06-11 | 2010-06-18 | 5 | 2010-06-18 | [14 empty] | 2010-07-06 | 2010-07-06 |  | Y
Central Hudson |  | Hudson Solar | CH-01911 | Fishkill | Wappingers Falls | Dutchess | 12590 | G | 8091 | Fishkill Plains | N |  | 2.3 | [13 empty] | NM | N | Sunpower SPR 4000m | 2010-06-11 | 2010-06-16 | 3 | 2010-06-16 | [14 empty] | 2010-10-21 | 2010-10-21 |  | Y
Central Hudson |  | Hudson Solar | CH-02086 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 7041 | Staatsburg | N |  | 5 | [13 empty] | NM | N | Sunpower SPR 5000m | 2010-06-11 | 2010-06-16 | 3 | 2010-06-16 | [14 empty] | 2010-11-24 | 2010-11-24 |  | Y
Central Hudson |  | Malcarne Contracting | CH-03898 | Poughkeepsie | Staatsburg | Dutchess | 12580 | G | 7041 | Staatsburg | N | CH-03898 | 9 | [13 empty] | NM | N | SPR 5000m, SPR 4000m | 2010-06-14 | 2010-06-21 | 5 | 2010-06-21 | [14 empty] | 2010-11-01 | 2010-11-01 |  | Y
Central Hudson |  | Hudson Solar | CH-02106 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 6053 | Todd Hill | N |  | 3.36 | [13 empty] | NM | N | Sunpower SPR 4000m | 2010-06-14 | 2010-06-18 | 4 | 2010-06-18 | [14 empty] | 2010-10-26 | 2010-10-26 |  | Y
Central Hudson |  | RGS Energy | CH-03010 | Catskill | Catskill | Greene | 12414 | G | 2001 | North Catskill | N |  | 6 | [13 empty] | NM | N | SMA Sunny Boy-6000US | 2010-06-18 | 2010-06-23 | 3 | 2010-06-23 | [14 empty] | 2010-08-05 | 2010-08-11 |  | Y
Central Hudson |  | RGS Energy | CH-03016 | Catskill | Medusa | Albany | 12120 | G | 1092 | Westerlo | N |  | 6 | [13 empty] | NM | N | SMA Sunny Boy-6000US | 2010-06-18 | 2010-06-23 | 3 | 2010-06-23 | [14 empty] | 2010-08-12 | 2010-08-18 |  | Y
Central Hudson |  | Solar Generation | CH-08150 | Kingston | W Hurley | Ulster | 12491 | G | 2094 | Hurley Ave | N |  | 4 | [13 empty] | NM | N | Fronius IG 4000 | 2010-06-21 | 2010-06-23 | 2 | 2010-06-23 | [14 empty] | 2010-07-01 | 2010-07-06 |  | Y
Central Hudson |  | Hudson Solar | CH-01245 | Fishkill | Beacon | Dutchess | 12508 | G | 8085 | Tioronda | N |  | 11.4 | [13 empty] | NM | N | Sun Power SPR-12000f | 2010-06-23 | 2010-06-29 | 4 | 2010-06-29 | [14 empty] | 2011-01-17 | 2011-01-17 |  | Y
Central Hudson |  | Solar Generation | CH-08191 | Kingston | Saugerties | Ulster | 12477 | G | 3014 | Woodstock | N |  | 11.4 | [13 empty] | NM | N | Fronius IG Plus 11.4-1 | 2010-09-20 | 2010-09-23 | 3 | 2010-09-23 | [14 empty] | 2010-11-05 | 2010-11-05 |  | Y
Central Hudson |  | Solar Generation | CH-08090 | Kingston | Woodstock | Ulster | 12498 | G | 3012 | Woodstock | N |  | 22.8 | [13 empty] | NM | N | (2) Fronius IG Plus 11.4-3 Delta | 2010-06-24 | 2010-06-28 | 2 | 2010-06-28 | [14 empty] | 2011-01-18 | 2011-01-18 |  | Y
Central Hudson |  | Solar Generation | CH-08174 | Kingston | Woodstock | Ulster | 12498 | G | 3012 | Woodstock | N |  | 22.8 | [13 empty] | NM | N | (2) Fronius IG Plus 11.4-3 Delta | 2010-06-24 | 2010-06-29 | 3 | 2010-06-29 | [14 empty] | 2011-01-18 | 2011-01-18 |  | Y
Central Hudson |  | RGS Energy | CH-03015 | Catskill | Medusa | Albany | 12120 | G | 1092 | Westerlo | N |  | 9.72 | [13 empty] | NM | N | Fronius IG Plus 10.0-1 | 2010-06-25 | 2010-06-29 | 2 | 2010-06-29 | [14 empty] | 2010-12-06 | 2010-12-06 |  | Y
Central Hudson |  | Solar Generation | CH-08068 | Catskill | Lexington | Greene | 12452 | E | 2389 | Vinegar Hill | N | CH-08068 | 7.5 | [13 empty] | NM | N | Fronius IG Plus 7.5-1 | 2010-06-29 | 2010-07-06 | 4 | 2010-07-06 | [14 empty] | 2011-05-17 | 2011-05-19 |  | Y
Central Hudson |  | Solar Generation | CH-08141 | Catskill | Lexington | Greene | 12452 | E | 2389 | Vinegar Hill | N |  | 3.8 | [13 empty] | NM | N | Fronius IG Plus 3.8-1 | 2010-06-29 | 2010-07-06 | 4 | 2010-07-06 | [14 empty] | 2010-09-30 | 2010-09-30 |  | Y
Central Hudson |  | Solar Generation | CH-08199 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7056 | Rhinebeck | N |  | 20.24 | [13 empty] | NM | N | (2) Fronius IG Plus 11.4-3 | 2010-06-29 | 2010-07-07 | 5 | 2010-07-07 | [14 empty] | 2010-10-05 | 2010-10-05 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03616 | Newburgh | New Paltz | Ulster | 12561 | G | 5021 | Ohioville | N |  | 14.985 | [13 empty] | NM | N | SMA Sunny Boy 5000US (x3) | 2010-06-30 | 2010-07-02 | 2 | 2010-07-02 | [14 empty] | 2010-08-31 | 2010-08-31 |  | Y
Central Hudson |  | Hudson Solar | CH-01355 | Newburgh | New Paltz | Ulster | 12561 | G | 5031 | Galeville | N |  | 28.7 | [13 empty] | NM | N | (6) PV Powered PVP-4800 | 2010-07-01 | 2010-07-08 | 4 | 2010-07-08 | [14 empty] | 2010-09-14 | 2010-09-14 |  | Y
Central Hudson |  | Solar Liberty Energy Systems | CH-04921 | Kingston | Port Ewen | Ulster | 12466 | G | 1024 | East Kingston | N |  | 22.56 | [13 empty] | NM | N | PV Powered PVP-30kW-LV | 2010-07-12 | 2010-07-13 | 1 | 2010-07-13 | [14 empty] | 2010-08-06 | 2010-08-10 |  | Y
Central Hudson |  | RGS Energy | CH-03020 | Catskill | Westerlo | Albany | 12193 | G | 1091 | Westerlo | N |  | 5 | [13 empty] | NM | N | SMA Sunny Boy 5000US | 2010-07-12 | 2010-07-14 | 2 | 2010-07-14 | [14 empty] | 2010-09-18 | 2010-09-18 |  | Y
Central Hudson |  | Hudson Solar | CH-01645 | Catskill | Coxsackie | Greene | 12051 | G | 1072 | Coxsackie | N |  | 27.1 | [13 empty] | NM | N | PVPowered PVP-30kW-LV | 2010-07-14 | 2010-07-21 | 5 | 2010-07-21 | [14 empty] | 2011-05-19 | 2011-05-25 |  | Y
Central Hudson |  | Hudson Solar | CH-01646 | Catskill | Athens | Greene | 12015 | G | 2002 | North Catskill | N |  | 24.84 | [13 empty] | NM | N | PVPowered PVP-30kW-LV | 2010-07-14 | 2010-07-21 | 5 | 2010-07-21 | [14 empty] | 2011-04-29 | 2011-05-04 |  | Y
Central Hudson |  | Green Energy Systems | CH-01161 | Catskill | Cairo |  | 12413 | G | 2042 | South Cairo | TBD |  | 1.36 | [13 empty] | NM | N | Fronius IG 2000 | 2010-07-16 | 2010-07-22 | 4 | 2010-07-22 | [17 empty] | W
Central Hudson |  | Hudson Solar | CH-01596 | Catskill | Coxsackie | Greene | 12051 | G | 1072 | Coxsackie | N |  | 24.84 | [13 empty] | NM | N | PVPowered PVP-30kW-LV | 2010-07-19 | 2010-07-21 | 2 | 2010-07-21 | [14 empty] | 2011-09-20 | 2011-09-26 |  | Y
Central Hudson |  | Hudson Solar | CH-01644 | Catskill | Coxsackie |  | 12051 | G | 1072 | Coxsackie | TBD |  | 24.84 | [13 empty] | NM | N | PVPowered PVP-30kW-LV | 2010-07-19 | 2010-07-21 | 2 | 2010-07-21 | [15 empty] | 2011-09-26 |  | W
Central Hudson |  | Hudson Solar | CH-01927 | Fishkill | Cold Spg | Putnam | 10516 | G | 8063 | Merritt Park | N |  | 4.84 | [13 empty] | NM | N | SMA SB 5000US | 2010-07-23 | 2010-07-30 | 5 | 2010-07-30 | [14 empty] | 2010-07-30 | 2010-07-30 |  | Y
Central Hudson |  | 1st Light Energy | CH-00582 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7056 | Rhinebeck | N |  | 8 | [13 empty] | NM | N | Fronius IG 4000 X2 | 2011-01-04 | 2011-01-05 | 1 | 2011-01-05 | [14 empty] | 2011-02-15 | 2011-02-17 |  | Y
Central Hudson |  | 1st Light Energy | CH-00591 | Newburgh | Cornwall | Orange | 12518 | G | 4093 | Bethlehem Rd | N |  | 7 | [13 empty] | NM | N | Sunny Boy 7000US | 2010-07-28 | 2010-07-30 | 2 | 2010-07-30 | [14 empty] | 2010-08-06 | 2010-08-06 |  | Y
Central Hudson |  | SunDog Solar | CH-09151 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8072 | Shenandoah | N |  | 42 | [13 empty] | NM | N | SMA Sunny Boy-7000US | 2010-08-13 | 2010-08-19 | 4 | 2010-08-19 | [14 empty] | 2010-12-02 | 2010-12-02 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03775 | Newburgh | Gardiner | Ulster | 12525 | G | 5011 | Modena | N |  | 5.16 | [13 empty] | NM | N | SMA Sunny Boy-6000 | 2010-08-02 | 2010-08-03 | 1 | 2010-08-03 | [14 empty] | 2010-08-13 | 2010-08-13 |  | Y
Central Hudson |  | Hudson Solar | CH-01340 | Fishkill | Wappingrs Falls |  | 12590 | G | 8052 | North Chelsea | TBD |  | 9 | [13 empty] | NM | N | 1 SPR-5000m and 1 SPR-4000m | 2010-08-09 | 2010-08-16 | 5 | 2010-08-16 | [17 empty] | W |  | Installation abandoned.
Central Hudson |  | Hudson Solar | CH-01725 | Kingston | Lk Katrine | Ulster | 12449 | G | 2011 | Lincoln Park | N |  | 5 | [13 empty] | NM | N | SunPower SPR 5000m | 2010-08-10 | 2010-08-10 | 0 | 2010-08-10 | [14 empty] | 2010-12-06 | 2010-12-06 |  | Y
Central Hudson |  | Hudson Solar | CH-02267 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 6057 | Todd Hill | N | CH-02267 | 8 | [13 empty] | NM | N | 2 SunPower SPR-4000m | 2010-08-09 | 2010-08-16 | 5 | 2010-08-16 | [14 empty] | 2010-01-03 | 2011-01-03 |  | Y
Central Hudson |  | Hudson Solar | CH-02395 | Kingston | Lk Katrine | Ulster | 12449 | G | 2011 | Lincoln Park | N |  | 5 | [13 empty] | NM | N | SunPower SPR 5000m | 2010-08-10 | 2010-08-10 | 0 | 2010-08-10 | [14 empty] | 2011-06-08 | 2011-06-15 |  | Y
Central Hudson |  | Sunnyside Solar | CH-09641 | Catskill | Round Top | Greene | 12473 | G | 2042 | South Cairo | N |  | 2.1 | [13 empty] | NM | N | SB 3000 | 2010-09-23 | 2010-09-23 | 0 | 2010-09-23 | [14 empty] | 2010-09-30 | 2010-09-30 |  | Y
Central Hudson |  | Sun Mountain | CH-09103 | Kingston | Woodstock | Ulster | 12498 | G | 3013 | Woodstock | N | CH-09103 | 2.85 | [13 empty] | NM | N | Enphase M190-72-240 | 2010-08-20 | 2010-08-20 | 0 | 2010-08-20 | [14 empty] | 2010-11-30 | 2010-11-30 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03718 | Newburgh | Gardiner | Ulster | 12525 | G | 5031 | Galeville | N |  | 7 | [13 empty] | NM | N | SMA SB 7000 | 2010-08-12 | 2010-08-13 | 1 | 2010-08-13 | [14 empty] | 2010-09-13 | 2010-09-13 |  | W
Central Hudson |  | Burke Electric and Solar | CH-00760 | Fishkill | Cold Spg | Putnam | 10516 | G | 8063 | Merritt Park | N |  | 7 | [13 empty] | NM | N | SB 7000 US | 2010-08-26 | 2010-08-27 | 1 | 2010-08-27 | [14 empty] | 2010-09-15 | 2010-09-15 |  | Y
Central Hudson |  | Hudson Solar | CH-01599 | Catskill | Elka Pk | Greene | 12427 | G | 2385 | Lawrenceville | N | CH-01599 | 5 | [13 empty] | NM | N | (2) SB 3000US | 2010-08-13 | 2010-08-19 | 4 | 2010-08-19 | [14 empty] | 2010-12-28 | 2010-12-28 |  | Y
Central Hudson |  | Hudson Solar | CH-01948 | Newburgh | Gardiner | Ulster | 12525 | G | 5034 | Galeville | N |  | 3.44 | [13 empty] | NM | N | SunPower SPR-4000m | 2010-08-13 | 2010-08-13 | 0 | 2010-08-13 | [14 empty] | 2010-10-07 | 2010-10-07 |  | Y
Central Hudson |  | Hudson Solar | CH-01751 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 6073 | East Park | N |  | 3 | [13 empty] | NM | N | 1 SPR-3000m | 2010-08-16 | 2010-08-20 | 4 | 2010-08-20 | [14 empty] | 2011-01-25 | 2011-01-25 |  | Y
Central Hudson |  | Hudson Solar | CH-02046 | Kingston | Hurley | Ulster | 12443 | G | 2094 | Hurley Ave | N |  | 11.34 | [13 empty] | NM | N | Solectria PVI 13kW | 2010-08-16 | 2010-08-18 | 2 | 2010-08-18 | [14 empty] | 2011-01-25 | 2011-01-25 |  | Y
Central Hudson |  | Hudson Solar | CH-02082 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 6073 | East Park | N |  | 3 | [13 empty] | NM | N | 1 SunPower SPR-3000m | 2010-08-16 | 2010-08-20 | 4 | 2010-08-20 | [14 empty] | 2012-05-03 | 2012-05-08 |  | Y
Central Hudson |  | Hudson Solar | CH-02141 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7052 | Rhinebeck | N |  | 4 | [13 empty] | NM | N | SB4000 | 2010-08-16 | 2010-08-19 | 3 | 2010-08-19 | [14 empty] | 2010-10-21 | 2010-10-25 |  | Y
Central Hudson |  | Mannino Electric | CH-02601 | Newburgh | New Paltz | Ulster | 12561 | G | 5023 | Ohioville | N |  | 5.3 | [13 empty] | NM | N | Enphase | 2010-08-16 | 2010-08-23 | 5 | 2010-08-23 | [14 empty] | 2010-12-28 | 2010-12-28 |  | Y
Central Hudson |  | RKB Contruction Company, Inc. | CH-02985 | Newburgh | Highland | Ulster | 12528 | G | 5084 | Highland | N |  | 4 | [13 empty] | NM | N | SMA 4000U | 2010-08-16 | 2010-08-23 | 5 | 2010-08-23 | [14 empty] | 2010-09-10 | 2010-09-13 |  | Y
Central Hudson |  | Malcarne Contracting | CH-03895 | Kingston | Kingston | Ulster | 12401 | G | 2013 | Lincoln Park | N |  | 21 | [13 empty] | NM | N | SMA-7000 | 2010-08-23 | 2010-08-24 | 1 | 2010-08-24 | [14 empty] | 2010-12-20 | 2010-12-20 |  | Y
Central Hudson |  | Malcarne Contracting | CH-03896 | Kingston | Kingston |  | 12401 | G | 2017 | Lincoln Park | TBD |  | 21 | [13 empty] | NM | N | SMA-7000 | 2010-08-23 | 2010-08-24 | 1 | 2010-08-24 | [15 empty] | 2010-12-20 |  | W |  | contractor performed SIR test and sent documentation
Central Hudson |  | Malcarne Contracting | CH-03901 | Kingston | Kingston | Ulster | 12401 | G | 2013 | Lincoln Park | N |  | 21 | [13 empty] | NM | N | SMA-7000 | 2010-08-23 | 2010-08-24 | 1 | 2010-08-24 | [14 empty] | 2010-12-17 | 2010-12-17 |  | Y
Central Hudson |  | Malcarne Contracting | CH-03902 | Kingston | Kingston |  | 12401 | G | 2017 | Lincoln Park | TBD |  | 21 | [13 empty] | NM | N | SMA-7000 | 2010-08-23 | 2010-08-24 | 1 | 2010-08-24 | [15 empty] | 2010-12-17 |  | W |  | contractor performed SIR test and sent documentation
Central Hudson |  | Hudson Solar | CH-01497 | Poughkeepsie | Tivoli | Dutchess | 12583 | G | 7062 | Milan | N | CH-01497 | 5 | [13 empty] | NM | N | 1 SunPower SPR-5000m | 2010-08-23 | 2010-08-25 | 2 | 2010-08-25 | [14 empty] | 2011-06-01 | 2011-06-02 |  | Y
Central Hudson |  | Hudson Solar | CH-01526 | Kingston | Willow | Ulster | 12495 | G | 3012 | Woodstock | N |  | 5 | [13 empty] | NM | N | SPR-5000M | 2010-08-23 | 2010-08-23 | 0 | 2010-08-23 | [14 empty] | 2011-06-08 | 2011-06-15 |  | Y
Central Hudson |  | Hudson Solar | CH-01605 | Catskill | Round Top | Greene | 12473 | G | 2042 | South Cairo | N |  | 6 | [13 empty] | NM | N | SPR-3000m | 2010-08-23 | 2010-08-25 | 2 | 2010-08-25 | [14 empty] | 2010-12-10 | 2010-12-10 |  | Y
Central Hudson |  | Hudson Solar | CH-01892 | Poughkeepsie | Milan | Dutchess | 12571 | G | 7061 | Milan | N |  | 3 | [13 empty] | NM | N | 1 SunPower SPR-3000m | 2010-08-23 | 2010-08-25 | 2 | 2010-08-25 | [14 empty] | 2010-10-18 | 2010-10-19 |  | Y
Central Hudson |  | Hudson Solar | CH-02491 | Newburgh | Wallkill | Ulster | 12589 | G | 5043 | East Walden | N | CH-02213 | 3 | [13 empty] | NM | N | 1 SunPower SPR-3000m | 2010-08-23 | 2010-08-27 | 4 | 2010-08-27 | [14 empty] | 2010-11-09 | 2010-11-09 |  | Y
Central Hudson |  | Hudson Solar | CH-01821 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6092 | Manchester | N |  | 4 | [13 empty] | NM | N | SPR-4000M | 2010-08-24 | 2010-08-25 | 1 | 2010-08-25 | [14 empty] | 2010-11-11 | 2010-11-11 |  | Y
Central Hudson |  | Hudson Solar | CH-02136 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7054 | Rhinebeck | N |  | 16 | [13 empty] | NM | N | (2) SB8000US | 2010-08-24 | 2010-08-27 | 3 | 2010-08-27 | [14 empty] | 2010-12-08 | 2010-12-08 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03741 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7061 | Milan | N |  | 7.5 | [13 empty] | NM | N | FRONIUS IG | 2010-08-26 | 2010-08-27 | 1 | 2010-08-27 | [14 empty] | 2010-09-27 | 2010-09-27 |  | Y
Central Hudson |  | SunDog Solar | CH-09136 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6065 | Inwood Ave | N |  | 3 | [13 empty] | NM | N | SB3000US | 2010-09-02 | 2010-09-10 | 5 | 2010-09-10 | [14 empty] | 2010-09-23 | 2010-09-23 |  | Y
Central Hudson |  | Sun Mountain | CH-09113 | Kingston | Bearsvl | Ulster | 12409 | G | 3012 | Woodstock | N |  | 6 | [13 empty] | NM | N | SB 6000 US | 2010-09-03 | 2010-09-13 | 5 | 2010-09-13 | [14 empty] | 2010-12-21 | 2010-12-21 |  | Y
Central Hudson |  | Damiani and Sun Inc. | CH-00819 | Newburgh | Gardiner | Ulster | 12525 | G | 5033 | Galeville | N |  | 6.025 | [13 empty] | NM | N | (1) PV2500 (2) 3500 | 2010-09-15 | 2010-09-15 | 0 | 2010-09-15 | [14 empty] | 2010-11-04 | 2010-11-09 |  | Y
Central Hudson |  | Murphy Solar Power | CH-02724 | Catskill | E Durham | Greene | 12423 | G | 2043 | South Cairo | N |  | 4 | [13 empty] | NM | N | (2) Sunny Boy 3000 | 2010-09-27 | 2010-09-27 | 0 | 2010-09-27 | [14 empty] | 2010-10-29 | 2010-10-29 |  | Y
Central Hudson |  | Solar Generation | CH-08140 | Catskill | Lexington | Greene | 12452 | E | 2389 | Vinegar Hill | N |  | 7.5 | [13 empty] | NM | N | FRONIUS IG Plus | 2010-09-17 | 2010-09-20 | 1 | 2010-09-20 | [14 empty] | 2010-12-01 | 2010-12-01 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03675 | Poughkeepsie | Milan | Dutchess | 12571 | G | 7061 | Milan | N | CH-03675 | 5.2 | [13 empty] | NM | N | PVP5200-240 | 2010-09-20 | 2010-09-20 | 0 | 2010-09-20 | [14 empty] | 2010-09-27 | 2010-09-27 |  | Y
Central Hudson |  | T-KAR Smart Energy Systems | CH-09724 | Newburgh | Marlboro | Ulster | 12542 | G | 5003 | Marlboro | N |  | 4.2 | [13 empty] | NM | N | enphase | 2010-09-20 | 2010-09-27 | 5 | 2010-09-27 | [14 empty] | 2010-10-04 | 2010-10-04 |  | Y
Central Hudson |  | Hudson Solar | CH-01700 | Kingston | Kingston | Ulster | 12401 | G | 1014 | Boulevard | N | CH-01700 | 7 | [13 empty] | NM | N | SPR-7000 | 2010-09-21 | 2010-09-21 | 0 | 2010-09-21 | [14 empty] | 2010-11-09 | 2010-11-09 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03724 | Newburgh | Newburgh | Orange | 12550 | G | 4023 | Coldenham | N |  | 22 | [13 empty] | NM | N | (2) IG PLUS 11.4-3 | 2010-09-22 | 2010-09-23 | 1 | 2010-09-23 | [14 empty] | 2010-11-05 | 2010-11-05 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03725 | Newburgh | Newburgh | Orange | 12550 | G | 4023 | Coldenham | N |  | 22 | [13 empty] | NM | N | (2) IG PLUS 11.4-3 | 2010-09-22 | 2010-09-23 | 1 | 2010-09-23 | [14 empty] | 2010-11-05 | 2010-11-05 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03750 | Newburgh | New Paltz | Ulster | 12561 | G | 5031 | Galeville | N |  | 5 | [13 empty] | NM | N | PVP5200-240 | 2010-09-22 | 2010-09-22 | 0 | 2010-09-22 | [14 empty] | 2010-10-08 | 2010-10-08 |  | Y
Central Hudson |  | Solar Generation | CH-08273 | Kingston | Woodstock | Ulster | 12498 | G | 3012 | Woodstock | N |  | 9.24 | [13 empty] | NM | N | Enphase | 2010-09-28 | 2010-10-04 | 4 | 2010-10-04 | [14 empty] | 2011-11-09 | 2011-11-09 |  | Y
Central Hudson |  | Hudson Solar | CH-01480 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 7011 | Hibernia | N |  | 7 | [13 empty] | NM | N | (2) SB3000 | 2010-10-01 | 2010-10-04 | 1 | 2010-10-04 | [14 empty] | 2011-05-11 | 2011-05-16 |  | W
Central Hudson |  | Hudson Solar | CH-01912 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8043 | Myers Corners | N |  | 6.75 | [13 empty] | NM | N | (2) SPR-3000 | 2010-10-01 | 2010-10-04 | 1 | 2010-10-04 | [14 empty] | 2011-08-16 | 2011-08-23 |  | Y
Central Hudson |  | Hudson Solar | CH-02085 | Poughkeepsie | Clinton Corners | Dutchess | 12514 | G | 7013 | Hibernia | N |  | 8 | [13 empty] | NM | N | (2) SPR-4000 | 2010-10-01 | 2010-10-04 | 1 | 2010-10-04 | [14 empty] | 2011-01-26 | 2011-01-26 |  | Y
Central Hudson |  | Solar Generation | CH-08127 | Kingston | Willow |  | 12495 | G | 3012 | Woodstock | N |  | 22.8 | [13 empty] | NM | N | (2) Fronius 11.4 | 2010-10-04 | 2010-10-04 | 0 | 2010-10-04 | [14 empty] | 2012-05-30 | 2012-05-30 |  | W
Central Hudson |  | Hudson Solar | CH-01501 | Poughkeepsie | Millerton | Dutchess | 12546 | G | 7095 | Smithfield | N |  | 27 | [13 empty] | NM | N | (1) SPR-4000M (2) SPR-5000M (1) SPR-7000M | 2010-10-06 | 2010-10-07 | 1 | 2010-10-07 | [14 empty] | 2011-05-26 | 2011-06-02 |  | Y
Central Hudson |  | Hudson Solar | CH-01976 | Newburgh | Wallkill | Ulster | 12589 | G | 5043 | East Walden | N |  | 6 | [13 empty] | NM | N | (2) SB3000US | 2010-10-06 | 2010-10-07 | 1 | 2010-10-07 | [14 empty] | 2011-01-03 | 2011-01-03 |  | Y
Central Hudson |  | Hudson Solar | CH-01977 | Newburgh | Wallkill | Ulster | 12589 | G | 5043 | East Walden | N |  | 3 | [13 empty] | NM | N | SB3000US | 2010-10-06 | 2010-10-07 | 1 | 2010-10-07 | [14 empty] | 2011-05-13 | 2011-05-19 |  | Y
Central Hudson |  | Hudson Solar | CH-01739 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 6062 | Inwood Ave | N | CH-01739 | 7 | [13 empty] | NM | N | SPR-7000M | 2010-10-07 | 2010-10-08 | 1 | 2010-10-08 | [14 empty] | 2011-04-01 | 2011-04-05 |  | Y
Central Hudson |  | Hudson Solar | CH-01790 | Poughkeepsie | Clinton Cors | Dutchess | 12514 | G | 7071 | Stanfordville | N |  | 7 | [13 empty] | NM | N | SPR-7000M | 2010-10-07 | 2010-10-08 | 1 | 2010-10-08 | [14 empty] | 2010-12-01 | 2010-12-01 |  | Y
Central Hudson |  | Honderosa Valley Consulting | CH-01209 | Newburgh | Highland Mls | Orange | 10930 | G | 4041 | Union Ave | N | [11 empty] | 3 |  |  |  | NM | N | Beckwith M-3410A-IB-02MC5 | 2011-04-04 | 2011-04-06 | 2 | 2011-04-06 | [14 empty] | 2011-04-11 | 2011-04-18 |  | Y
Central Hudson |  | Hudson Solar | CH-01492 | Poughkeepsie | Red Hook |  |  | G | 7061 | Milan | TBD |  | 11 | [13 empty] | NM | N | SPR-4000M SPR-7000M | 2010-10-14 | 2010-10-14 | 0 | 2010-10-14 | [17 empty] | W |  | Installation abandoned.
Central Hudson |  | 2K Solar Inc | CH-00628 | Newburgh | New Paltz | Ulster | 12561 | G | 5031 | Galeville | N | CH-00628 | 6 | [13 empty] | NM | N | Fronius 6.0 | 2010-10-15 | 2010-10-15 | 0 | 2010-10-15 | [14 empty] | 2010-12-05 | 2010-12-07 |  | Y
Central Hudson |  | Murphy Solar Power | CH-02715 | Catskill | Earlton |  | 12058 | G | 2006 | North Catskill | TBD |  | 2.1 | [13 empty] | NM | N | SB 3000 | 2010-10-18 | 2010-10-18 | 0 | 2010-10-18 | [17 empty] | W
Central Hudson |  | Mannino Electric | CH-02600 | Newburgh | New Paltz | Ulster | 12561 | G | 5031 | Galeville | N |  | 2.6 | [13 empty] | NM | N | Enphase | 2010-10-19 | 2010-10-19 | 0 | 2010-10-19 | [14 empty] | 2010-12-30 | 2010-12-30 |  | Y
Central Hudson |  | Hudson Solar | CH-01321 | Poughkeepsie | Rhinebeck |  | 12572 | G | 7053 | Rhinebeck | TBD |  | 6 | [13 empty] | NM | N | (2) SPR-3000M | 2010-10-20 | 2010-10-21 | 1 | 2010-10-21 | [17 empty] | W |  | Installation abandoned.
Central Hudson |  | Hudson Solar | CH-01758 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 6074 | East Park | N |  | 5 | [13 empty] | NM | N | SPR-5000M | 2010-10-20 | 2010-10-20 | 0 | 2010-10-20 | [14 empty] | 2011-08-08 | 2011-08-10 |  | Y
Central Hudson |  | Hudson Solar | CH-02186 | Newburgh | New Paltz | Ulster | 12561 | G | 5021 | Ohioville | N | CH-02186 | 5 | [13 empty] | NM | N | SPR-5000M | 2010-10-20 | 2010-10-21 | 1 | 2010-10-21 | [14 empty] | 2010-12-27 | 2010-12-27 |  | Y
Central Hudson |  | Hudson Solar | CH-02200 | Newburgh | New Paltz | Ulster | 12561 | G | 5023 | Ohioville | N |  | 4 | [13 empty] | NM | N | SPR-4000M | 2010-10-20 | 2010-10-21 | 1 | 2010-10-21 | [14 empty] | 2010-11-05 | 2010-11-09 |  | Y
Central Hudson |  | Hudson Solar | CH-01265 | Catskill | Athens | Greene | 12015 | G | 1074 | Coxsackie | N |  | 6.6 | [13 empty] | NM | N | (2) XANTREX GT 3.3 | 2010-10-21 | 2010-10-21 | 0 | 2010-10-21 | [14 empty] | 2011-03-11 | 2011-03-14 |  | Y
Central Hudson |  | Hudson Solar | CH-02540 | TBD | Red Hook |  | 12571 | Tbd | TBD | Tbd | TBD |  | 8 | [13 empty] | NM | N | SPR-4000M | 2010-10-21 | 2010-10-25 | 2 | 2010-10-25 | [17 empty] | W |  | Installation abandoned.
Central Hudson |  | Lighthouse Solar | CH-03818 | Newburgh | Wallkill | Ulster | 12589 | G | 5042 | East Walden | N | CH-03818 | 5 | [13 empty] | NM | N | PVP5200-240 | 2010-10-25 | 2010-10-26 | 1 | 2010-10-26 | [14 empty] | 2010-12-01 | 2010-12-01 |  | Y
Central Hudson |  | Hudson Solar | CH-01606 | Catskill | Durham | Greene | 12422 | G | 1092 | Westerlo | N |  | 6.75 | [13 empty] | NM | N | SPR-7000M | 2010-10-25 | 2010-10-26 | 1 | 2010-10-26 | [14 empty] | 2011-12-27 | 2011-12-29 |  | Y
Central Hudson |  | Hudson Solar | CH-01759 | Poughkeepsie | Staatsburg | Dutchess | 12580 | G | 7011 | Hibernia | N |  | 4 | [13 empty] | NM | N | SPR-4000M | 2010-10-25 | 2010-10-26 | 1 | 2010-10-26 | [14 empty] | 2011-05-24 | 2011-05-26 |  | Y
Central Hudson |  | Hudson Solar | CH-01851 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7053 | Rhinebeck | N |  | 7 | [13 empty] | NM | N | SPR-7000M | 2010-10-25 | 2010-10-26 | 1 | 2010-10-26 | [14 empty] | 2011-04-29 | 2011-05-04 |  | Y
Central Hudson |  | Hudson Solar | CH-02405 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7062 | Milan | N |  | 5 | [13 empty] | NM | N | SPR-5000M | 2010-10-25 | 2010-10-26 | 1 | 2010-10-26 | [14 empty] | 2011-01-03 | 2011-01-03 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03831 | Newburgh | Gardiner | Ulster | 12525 | G | 5034 | Galeville | N | CH-02324 | 3 | [13 empty] | NM | N | SB 4000 | 2010-10-26 | 2010-10-26 | 0 | 2010-10-26 | [14 empty] | 2010-12-01 | 2010-12-01 |  | Y
Central Hudson |  | Conscious Energy | CH-00788 | Newburgh | Gardiner | Ulster | 12525 | G | 5043 | East Walden | N | CH-00788 | 7 | [13 empty] | NM | N | SMA SB7000 US | 2010-10-26 | 2010-10-27 | 1 | 2010-10-27 | [14 empty] | 2010-11-08 | 2010-11-08 |  | Y
Central Hudson |  | Solar Generation | CH-08178 | Kingston | West Shokan | Ulster | 12494 | G | 3011 | Woodstock | N |  | 8.4 | [13 empty] | NM | N | Fronius IG plus 7.5 | 2010-10-29 | 2010-11-04 | 4 | 2010-11-04 | [14 empty] | 2011-04-06 | 2011-04-06 |  | Y
Central Hudson |  | Inverters Unlimited Inc | CH-02560 | Catskill | Greenvl | Greene | 12083 | G | 2061 | Freehold | N |  | 4.6 | [13 empty] | NM | N | SUN-AC3000 | 2010-11-01 | 2010-11-08 | 5 | 2010-11-08 | [14 empty] | 2010-11-19 | 2010-11-19 |  | Y
Central Hudson |  | Wiley Electronics LLC | CH-09945 | Kingston | Saugerties | Ulster | 12477 | G | 3003 | Saugerties | N |  | 6.6 | [13 empty] | NM | N | Enphase | 2010-11-01 | 2010-11-02 | 1 | 2010-11-02 | [14 empty] | 2010-12-08 | 2010-12-08 |  | Y
Central Hudson |  | Mercury Solar Systems | CH-02616 | Fishkill | Fishkill | Dutchess | 12524 | G | 8051 | North Chelsea | N | CH-02616 | 4.95 | [13 empty] | NM | N | Sunpower3000M Sunpower4000M | 2010-11-02 | 2010-11-04 | 2 | 2010-11-04 | [14 empty] | 2011-03-23 | 2011-03-24 |  | Y
Central Hudson |  | Solar Generation | CH-08177 | Kingston | W Shokan | Ulster | 12494 | G | 3011 | Woodstock | N |  | 1.68 | [13 empty] | NM | N | Enphase | 2010-11-04 | 2010-11-09 | 3 | 2010-11-09 | [14 empty] | 2011-04-06 | 2011-04-06 |  | Y
Central Hudson |  | Rural Generation and Wind | CH-08848 | Catskill | Earlton |  | 12058 | G | 2006 | North Catskill | TBD |  | 20 |  | 40 | [11 empty] | NM | N | (4) Power One PVI6000 | 2010-11-15 | 2010-11-17 | 2 | 2010-11-17 | [15 empty] | 2011-02-11 |  | W |  | Incomplete issused 11/11/10 Preliminary granted 11/17/10 CH performed Verification Test. 4/13/12 Verified customer removed this installation and built a new wind generation installation.
Central Hudson |  | Sunshine Solar Systems LLC | CH-09676 | Kingston | Kingston |  | 12401 | G | 3021 | High Falls | TBD |  | 0.84 | [13 empty] | NM | N | Enphase | 2010-11-04 | 2010-11-08 | 2 | 2010-11-08 | [17 empty] | W
Central Hudson |  | Hudson Solar | CH-01339 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8043 | Myers Corners | N |  | 6 | [13 empty] | NM | N | SPR - 3000M | 2010-11-08 | 2010-11-10 | 2 | 2010-11-10 | [14 empty] | 2011-02-21 | 2011-02-23 |  | Y
Central Hudson |  | Hudson Solar | CH-02523 | TBD | New Paltz |  | 12561 | Tbd | TBD | Tbd | TBD |  | 8 | [13 empty] | NM | N | (2) SPR-4000M | 2010-11-08 | 2010-11-10 | 2 | 2010-11-10 | [17 empty] | W |  | Installation abandoned.
Central Hudson |  | Lighthouse Solar | CH-03614 | Fishkill | Fishkill | Dutchess | 12524 | G | 8017 | Forgebrook | N |  | 44.1 | [13 empty] | NM | N | (4) Fronius IG Plus 11.4-3 delta | 2010-11-11 | 2010-11-11 | 0 | 2010-11-11 | [14 empty] | 2010-12-28 | 2010-12-28 |  | Y
Central Hudson |  | Malcarne Contracting | CH-03907 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6042 | Spackenkill | N |  | 4.9 | [13 empty] | NM | N | SB4000 | 2010-11-11 | 2010-11-15 | 2 | 2010-11-15 | [14 empty] | 2010-12-29 | 2010-12-29 |  | Y
Central Hudson |  | Green Building and Material Supply, Inc. | CH-01155 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6001 | Reynolds Hill | N |  | 52.92 | [13 empty] | NM | N | Satcon Power Gate plus 50kW | 2010-11-16 | 2010-11-16 | 0 | 2010-11-16 | [14 empty] | 2011-09-15 | 2011-09-21 |  | Y
Central Hudson |  | Green Building and Material Supply, Inc. | CH-01158 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6001 | Reynolds Hill | N |  | 26.01 | [13 empty] | NM | N | Fronius 11.4 | 2010-11-16 | 2010-11-16 | 0 | 2010-11-16 | [14 empty] | 2011-09-15 | 2011-09-21 |  | Y
Central Hudson |  | Sun Mountain | CH-09088 | Kingston | Stone Ridge | Ulster | 12484 | G | 3023 | High Falls | N |  | 2.3 | [13 empty] | NM | N | SMA SB3000 | 2010-11-16 | 2010-11-16 | 0 | 2010-11-16 | [14 empty] | 2011-03-23 | 2011-03-24 |  | Y
Central Hudson |  | Rural Generation and Wind | CH-02995 | Catskill | Freehold | Greene | 12431 | G | 2071 | Freehold | N |  |  |  | 10 | [11 empty] | NM | N | SMA Windy Boy 6000 (2) | 2010-11-17 | 2010-11-24 | 5 | 2010-11-24 | [14 empty] | 2011-02-04 | 2011-02-11 |  | W
Central Hudson |  | groSolar | CH-01190 | Poughkeepsie | Verbank | Dutchess | 12585 | G | 6057 | Todd Hill | N | CH-01190 | 8.2 | [13 empty] | NM | N | Enphase 190 | 2010-11-22 | 2010-11-24 | 2 | 2010-11-24 | [14 empty] | 2011-02-14 | 2011-02-15 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03791 | Newburgh | Gardiner | Ulster | 12525 | G | 5011 | Modena | N |  | 7 | [13 empty] | NM | N | SMA SB7000US | 2010-11-24 | 2010-11-24 | 0 | 2010-11-24 | [14 empty] | 2010-12-28 | 2010-12-28 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03642 | Newburgh | Wallkill | Ulster | 12589 | G | 5043 | East Walden | N |  | 5 | [13 empty] | NM | N | PVP4800-240 | 2010-12-06 | 2010-12-08 | 2 | 2010-12-08 | [14 empty] | 2010-12-29 | 2010-12-29 |  | Y
Central Hudson |  | Self | CH-08889 | Kingston | Saugerties | Ulster | 12477 | G | 3002 | Saugerties | N |  | 2.28 | [13 empty] | NM | N | Fronius | 2010-12-06 | 2010-12-09 | 3 | 2010-12-09 | [14 empty] | 2011-01-20 | 2011-01-20 |  | W
Central Hudson |  | Malcarne Contracting | CH-03899 | Poughkeepsie | Salt Pt | Dutchess | 12578 | G | 7011 | Hibernia | N |  | 7.35 | [13 empty] | NM | N | SMA 8000 | 2010-12-20 | 2010-12-21 | 1 | 2010-12-21 | [14 empty] | 2011-03-28 | 2011-04-01 |  | Y
Central Hudson |  | Hudson Solar | CH-01702 | Kingston | Kingston | Ulster | 12401 | G | 2094 | Hurley Ave | N |  | 5 | [13 empty] | NM | N | Xantrex GT 5.0 | 2010-12-20 | 2010-12-22 | 2 | 2010-12-22 | [14 empty] | 2011-03-11 | 2011-03-14 |  | Y
Central Hudson |  | Hudson Solar | CH-02369 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7061 | Milan | N |  | 7 | [13 empty] | NM | N | SPR-7000M | 2010-12-20 | 2010-12-21 | 1 | 2010-12-21 | [14 empty] | 2011-03-18 | 2011-03-23 |  | Y
Central Hudson |  | Hudson Solar | CH-01879 | Poughkeepsie | Pine Plns | Dutchess | 12567 | G | 7092 | Pulvers Corners | N |  | 10 | [13 empty] | NM | N | (1) SPR-6000 (1) Spr-4000 | 2010-12-21 | 2010-12-21 | 0 | 2010-12-21 | [14 empty] | 2011-05-24 | 2011-05-26 |  | Y
Central Hudson |  | Hudson Solar | CH-02432 | Catskill | Elka Pk | Greene | 12427 | G | 2385 | Lawrenceville | N | CH-01599 | 8 | [13 empty] | NM | N | (2) SB4000US | 2010-12-21 | 2010-12-21 | 0 | 2010-12-21 | [14 empty] | 2010-12-28 | 2010-12-28 |  | Y
Central Hudson |  | Hudson Solar | CH-01418 | Kingston | Kingston | Ulster | 12401 | G | 2093 | Hurley Ave | N |  | 10 | [13 empty] | NM | N | (1) SPR-3000 (2) spr-4000 | 2010-12-22 | 2010-12-27 | 1 | 2010-12-27 | [14 empty] | 2011-03-30 | 2011-04-05 |  | Y
Central Hudson |  | Hudson Solar | CH-01866 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7062 | Milan | N |  | 7 | [13 empty] | NM | N | spr-7000 | 2010-12-22 | 2010-12-27 | 1 | 2010-12-27 | [14 empty] | 2010-03-11 | 2011-03-15 |  | Y
Central Hudson |  | Hudson Solar | CH-01932 | Fishkill | Hopewell Junction | Dutchess | 12533 | G | 8093 | Fishkill Plains | N |  | 4 | [13 empty] | NM | N | SPR-4000M | 2010-12-27 | 2010-12-29 | 2 | 2010-12-29 | [14 empty] | 2011-03-25 | 2011-03-30 |  | Y
Central Hudson |  | Mannino Electric | CH-02602 | Kingston | Stone Ridge | Ulster | 12484 | G | 3023 | High Falls | N |  | 4.6 | [13 empty] | NM | N | Enphase | 2010-12-27 | 2010-12-29 | 2 | 2010-12-29 | [14 empty] | 2010-12-30 | 2010-12-30 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03665 | Kingston | Kerhonkson | Ulster | 12446 | G | 3081 | Kerhonkson | N |  | 50.16 | [13 empty] | NM | N | (6)-sb8000 | 2011-01-05 | 2011-01-05 | 0 | 2011-01-05 | [14 empty] | 2011-02-22 | 2011-02-22 |  | Y
Central Hudson |  | Hudson Solar | CH-02276 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7056 | Rhinebeck | N | CH-02276 | 8 | [13 empty] | NM | N | SPR-3000 SPR-5000 | 2011-01-12 | 2011-01-14 | 2 | 2011-01-14 | [14 empty] | 2011-05-13 | 2011-05-19 |  | Y
Central Hudson |  | Hudson Solar | CH-02299 | Poughkeepsie | Stanfordvl | Dutchess | 12581 | G | 7071 | Stanfordville | N |  | 9 | [13 empty] | NM | N | (1) SPR 4000 (1) SPR 5000 | 2011-01-12 | 2011-01-13 | 1 | 2011-01-13 | [14 empty] | 2011-08-19 | 2011-08-19 |  | Y
Central Hudson |  | Hudson Solar | CH-02321 | Newburgh | Newburgh | Orange | 12550 | G | 5004 | Marlboro | N |  | 5 | [13 empty] | NM | N | GT 5.0 | 2011-01-12 | 2011-01-14 | 2 | 2011-01-14 | [14 empty] | 2011-04-08 | 2011-04-13 |  | Y
Central Hudson |  | Hudson Solar | CH-02437 | Kingston | Bearsvl | Ulster | 12409 | G | 3012 | Woodstock | N | CH-01286 | 4 | [13 empty] | NM | N | SPR-4000M | 2011-01-12 | 2011-01-13 | 1 | 2011-01-13 | [14 empty] | 2011-04-08 | 2011-04-12 |  | Y
Central Hudson |  | Hudson Solar | CH-02474 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8046 | Myers Corners | N | CH-01913 | 4 | [13 empty] | NM | N | SPR-4000 | 2011-01-12 | 2011-01-13 | 1 | 2011-01-13 | [14 empty] | 2011-03-24 | 2011-03-28 |  | Y
Central Hudson |  | Hudson Solar | CH-01563 | Kingston | Saugerties | Ulster | 12477 | G | 3001 | Saugerties | N |  | 4 | [13 empty] | NM | N | SPR-4000m | 2011-01-13 | 2011-01-14 | 1 | 2011-01-14 | [14 empty] | 2011-05-11 | 2011-05-16 |  | Y
Central Hudson |  | Hudson Solar | CH-02179 | Fishkill | Beacon |  | 12508 | G | 8051 | North Chelsea | TBD |  | 6 | [13 empty] | NM | N | SMA SB6000US | 2011-01-18 | 2011-01-19 | 1 | 2011-01-19 | [17 empty] | W |  | Customer already had net meter prior to application. Installation abandoned.
Central Hudson |  | Hudson Solar | CH-01445 | Fishkill | Beacon |  | 12508 | G | 8051 | North Chelsea | TBD |  | 5 | [13 empty] | NM | N | SB5000US | 2011-01-26 | 2011-02-01 | 4 | 2011-02-01 | [17 empty] | W |  | Customer already had net meter prior to application. Installation abandoned.
Central Hudson |  | Hudson Solar | CH-01509 | Fishkill | Beacon |  | 12508 | G | 8051 | North Chelsea | TBD |  | 6 | [13 empty] | NM | N | SB6000US | 2011-01-26 | 2011-02-01 | 4 | 2011-02-01 | [17 empty] | W |  | Customer already had net meter prior to application. Installation abandoned.
Central Hudson |  | Hudson Solar | CH-02178 | Fishkill | Beacon |  | 12508 | G | 8051 | North Chelsea | TBD |  | 5 | [13 empty] | NM | N | SB5000US | 2011-01-26 | 2011-02-01 | 4 | 2011-02-01 | [17 empty] | W |  | Customer already had net meter prior to application. Installation abandoned.
Central Hudson |  | Hudson Solar | CH-01425 | Fishkill | Beacon |  | 12508 | G | 8051 | North Chelsea | TBD |  | 6 | [13 empty] | NM | N | (2) sb3000 | 2011-01-27 | 2011-02-01 | 3 | 2011-02-01 | [17 empty] | W |  | Customer already had net meter prior to application. Installation abandoned.
Central Hudson |  | Hudson Solar | CH-01438 | Fishkill | Beacon |  | 12508 | G | 8051 | North Chelsea | TBD |  | 6 | [13 empty] | NM | N | sb6000us | 2011-01-27 | 2011-02-01 | 3 | 2011-02-01 | [17 empty] | W |  | Customer already had net meter prior to application. Installation abandoned.
Central Hudson |  | Hudson Solar | CH-01439 | Fishkill | Beacon |  | 12508 | G | 8051 | North Chelsea | TBD |  | 5 | [13 empty] | NM | N | sb5000 | 2011-01-27 | 2011-02-01 | 3 | 2011-02-01 | [17 empty] | W |  | Customer already had net meter prior to application. Installation abandoned.
Central Hudson |  | Hudson Solar | CH-01440 | Fishkill | Beacon |  | 12508 | G | 8051 | North Chelsea | TBD |  | 5 | [13 empty] | NM | N | SB5000US | 2011-01-27 | 2011-02-01 | 3 | 2011-02-01 | [17 empty] | W |  | Customer already had net meter prior to application. Installation abandoned.
Central Hudson |  | Hudson Solar | CH-01441 | Fishkill | Beacon |  | 12508 | G | 8051 | North Chelsea | TBD |  | 5 | [13 empty] | NM | N | SB5000 | 2011-01-27 | 2011-02-01 | 3 | 2011-02-01 | [17 empty] | W |  | Customer already had net meter prior to application. Installation abandoned.
Central Hudson |  | Hudson Solar | CH-01442 | Fishkill | Beacon |  | 12508 | G | 8051 | North Chelsea | TBD |  | 6 | [13 empty] | NM | N | SB6000M | 2011-01-27 | 2011-02-01 | 3 | 2011-02-01 | [17 empty] | W |  | Customer already had net meter prior to application. Installation abandoned.
Central Hudson |  | Hudson Solar | CH-01443 | Fishkill | Beacon |  | 12508 | G | 8051 | North Chelsea | TBD |  | 5 | [13 empty] | NM | N | SB5000US | 2011-01-27 | 2011-02-01 | 3 | 2011-02-01 | [17 empty] | W |  | Customer already had net meter prior to application. Installation abandoned.
Central Hudson |  | Hudson Solar | CH-01444 | Fishkill | Beacon |  | 12508 | G | 8051 | North Chelsea | TBD |  | 5 | [13 empty] | NM | N | SB5000US | 2011-01-27 | 2011-02-01 | 3 | 2011-02-01 | [17 empty] | W |  | Customer already had net meter prior to application. Installation abandoned.
Central Hudson |  | Hudson Solar | CH-01446 | Fishkill | Beacon |  | 12508 | G | 8051 | North Chelsea | TBD |  | 5 | [13 empty] | NM | N | SB5000us | 2011-01-27 | 2011-02-01 | 3 | 2011-02-01 | [17 empty] | W |  | Customer already had net meter prior to application. Installation abandoned.
Central Hudson |  | Hudson Solar | CH-01447 | Fishkill | Beacon |  | 12508 | G | 8051 | North Chelsea | TBD |  | 5 | [13 empty] | NM | N | SB5000US | 2011-01-27 | 2011-02-01 | 3 | 2011-02-01 | [17 empty] | W |  | Customer already had net meter prior to application. Installation abandoned.
Central Hudson |  | Hudson Solar | CH-02177 | Fishkill | Beacon |  | 12508 | G | 8051 | North Chelsea | TBD |  | 5 | [13 empty] | NM | N | SB5000 | 2011-01-27 | 2011-02-01 | 3 | 2011-02-01 | [17 empty] | W |  | Customer already had net meter prior to application. Installation abandoned.
Central Hudson |  | Mercury Solar Systems | CH-02618 | Newburgh | New Windsor | Orange | 12553 | G | 4091 | Bethlehem Rd | N |  | 71.5 | [13 empty] | NM | N | PVP75KW | 2011-01-28 | 2011-02-03 | 4 | 2011-02-03 | [14 empty] | 2011-03-07 | 2011-03-11 |  | Y
Central Hudson |  | Solar Liberty Energy Systems | CH-04901 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 6051 | Todd Hill | N | CH-04901 | 23.9 | [13 empty] | NM | N | PVP30kW | 2011-01-28 | 2011-02-04 | 5 | 2011-02-04 | [14 empty] | 2011-02-14 | 2011-02-17 |  | Y
Central Hudson |  | Hudson Solar | CH-01402 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7054 | Rhinebeck | N |  | 15 | [13 empty] | NM | N | (3) SPR-5000M | 2011-02-02 | 2011-02-07 | 3 | 2011-02-07 | [14 empty] | 2011-06-17 | 2011-06-22 |  | Y
Central Hudson |  | Hudson Solar | CH-02454 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7054 | Rhinebeck | N | CH-01376 | 12 | [13 empty] | NM | N | (3) SPR-4000M | 2011-02-02 | 2011-02-07 | 3 | 2011-02-07 | [14 empty] | 2011-06-17 | 2011-06-22 |  | Y
Central Hudson |  | Solar Alchemy | CH-08986 | Kingston | Saugerties | Ulster | 12477 | G | 3001 | Saugerties | N | CH-08986 | 2.5 | [13 empty] | NM | N | PVP2500 | 2011-02-02 | 2011-02-08 | 4 | 2011-02-08 | [14 empty] | 2011-05-23 | 2011-05-26 |  | Y
Central Hudson |  | Murphy Solar Power | CH-02730 | Catskill | Leeds | Greene | 12451 | G | 2006 | North Catskill | N |  | 12 | [13 empty] | NM | N | SMA7000 SMA3000 | 2011-02-04 | 2011-02-10 | 4 | 2011-02-10 | [14 empty] | 2011-05-06 | 2011-05-10 |  | Y
Central Hudson |  | Murphy Solar Power | CH-02751 | Catskill | Coxsackie | Greene | 12051 | G | 1072 | Coxsackie | N |  | 2.1 | [13 empty] | NM | N | SB3000 | 2011-02-04 | 2011-02-10 | 4 | 2011-02-10 | [14 empty] | 2012-02-02 | 2012-02-07 |  | Y
Central Hudson |  | Damiani and Sun Inc. | CH-00820 | Newburgh | Gardiner | Ulster | 12525 | G | 5011 | Modena | N |  | 6.6 | [13 empty] | NM | N | sb7000 | 2011-02-07 | 2011-02-14 | 5 | 2011-02-14 | [14 empty] | 2011-03-08 | 2011-03-14 |  | Y
Central Hudson |  | New York Light Energy, LLC | CH-02771 | Kingston | Kingston | Ulster | 12401 | G | 2094 | Hurley Ave | N |  | 50 | [13 empty] | NM | N | Satcon PVS-50-208 | 2011-02-16 | 2011-02-24 | 5 | 2011-02-24 | [8 empty] | 4811 | 4811 |  | 2011-05-06 | 2011-05-06 | 2011-06-16 | 2011-07-12 | 2011-07-13 |  | Y
Central Hudson |  | Hudson Valley Wind Energy, LLC | CH-02556 | Poughkeepsie | Pine Plns | Dutchess | 12567 | G | 7091 | Pulvers Corners | Y | CH-02556 |  |  | 10 | [11 empty] | NM | N | Diversified Technology Powersynch II AMFA-27 | 2011-02-11 | 2011-02-15 | 2 | 2011-02-15 | [14 empty] | 2011-02-22 | 2011-02-24 |  | Y
Central Hudson |  | Hudson Solar | CH-01336 | Poughkeepsie | Stanfordvl | Dutchess | 12581 | G | 7072 | Stanfordville | N |  | 7.36 | [13 empty] | NM | N | sun power 7.0 | 2011-02-16 | 2011-02-18 | 2 | 2011-02-18 | [14 empty] | 2011-06-02 | 2011-06-03 |  | Y
Central Hudson |  | Hudson Solar | CH-01951 | Newburgh | Highland | Ulster | 12528 | G | 5022 | Ohioville | N |  | 11 | [13 empty] | NM | N | (1) Sunpower 7000m (1) Sunpower 4000M (1) Sunpower 3000M | 2011-02-16 | 2011-02-18 | 2 | 2011-02-18 | [14 empty] | 2011-07-05 | 2011-07-07 |  | Y
Central Hudson |  | Hudson Solar | CH-01970 | Newburgh | New Paltz | Ulster | 12561 | G | 5031 | Galeville | N |  | 4.8 | [13 empty] | NM | N | (1) Xantrex 3300 (1) Xantrex 5000 | 2011-02-16 | 2011-02-18 | 2 | 2011-02-18 | [14 empty] | 2011-05-25 | 2011-06-01 |  | Y
Central Hudson |  | Mercury Solar Systems | CH-02619 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8096 | Fishkill Plains | N |  | 6.44 | [13 empty] | NM | N | PVP3500 PVP2500 | 2011-02-22 | 2011-02-25 | 3 | 2011-02-25 | [14 empty] | 2011-03-24 | 2011-03-24 |  | Y
Central Hudson |  | Hudson Solar | CH-01796 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7054 | Rhinebeck | N |  | 1.88 | [13 empty] | NM | N | SMA3000 | 2011-03-02 | 2011-03-03 | 1 | 2011-03-03 | [14 empty] | 2011-06-17 | 2011-06-22 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03778 | Kingston | Kerhonkson | Ulster | 12446 | G | 3081 | Kerhonkson | N |  | 4.44 | [13 empty] | NM | N | PVP 4800 | 2011-03-03 | 2011-03-16 | 9 | 2011-03-16 | [14 empty] | 2011-05-20 | 2011-05-26 |  | Y
Central Hudson |  | Mercury Solar Systems | CH-02627 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6056 | Todd Hill | N |  | 5.04 | [13 empty] | NM | N | (2) pvp 2500 | 2011-03-14 | 2011-03-15 | 1 | 2011-03-15 | [14 empty] | 2011-07-11 | 2011-07-13 |  | Y
Central Hudson |  | Lotus Energy Inc. | CH-03858 | Catskill | Athens | Greene | 12015 | G | 2002 | North Catskill | N |  | 4 | [13 empty] | NM | N | (17) Enphase M190 | 2011-03-16 | 2011-03-16 | 0 | 2011-03-16 | [14 empty] | 2011-07-12 | 2011-07-13 |  | Y
Central Hudson |  | Lotus Energy Inc. | CH-03877 | Kingston | Saugerties | Ulster | 12477 | G | 3004 | Saugerties | N |  | 4.23 | [13 empty] | NM | N | (18) Enphase M190 | 2011-03-28 | 2011-03-30 | 2 | 2011-03-30 | [14 empty] | 2011-07-12 | 2011-07-13 |  | Y
Central Hudson |  | Solar Generation | CH-08168 | Kingston | Woodstock | Ulster | 12498 | G | 3013 | Woodstock | N | CH-08168 | 6.66 | [13 empty] | NM | N | 31 Enohase M210 | 2011-03-14 | 2011-03-24 | 8 | 2011-03-24 | [14 empty] | 2011-04-28 | 2011-05-02 |  | Y
Central Hudson |  | Hudson Valley Wind Energy, LLC | CH-02548 | Poughkeepsie | Ancram | Dutchess | 12546 | G | 7081 | Millerton | N |  |  |  | 10 | [11 empty] | NM | N | Diversified Technology Powersynch II AMFA-27 | 2011-03-16 | 2011-03-23 | 5 | 2011-03-23 | [14 empty] | 2011-06-23 | 2011-06-27 |  | Y
Central Hudson |  | Mountain View Services, Inc. | CH-02702 | Catskill | Rensselaervl | Albany | 12147 | G | 1092 | Westerlo | N |  | 4 | [13 empty] | NM | N | PVI 4000 | 2011-03-17 | 2011-03-23 | 4 | 2011-03-23 | [14 empty] | 2011-07-28 | 2011-08-03 |  | Y
Central Hudson |  | Hudson Solar | CH-01870 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7052 | Rhinebeck | N |  | 4.14 | [13 empty] | NM | N | Sun Power 4000M | 2011-03-18 | 2011-03-23 | 3 | 2011-03-23 | [14 empty] | 2011-07-01 | 2011-07-06 |  | Y
Central Hudson |  | Solar Generation | CH-08171 | Kingston | Woodstock | Ulster | 12498 | G | 3013 | Woodstock | N | CH-08171 | 7 | [13 empty] | NM | N | Fronius IG Plus 7.5 | 2011-04-14 | 2011-04-18 | 2 | 2011-04-18 | [14 empty] | 2011-07-07 | 2011-07-12 |  | Y
Central Hudson |  | Solar Liberty Energy Systems | CH-04907 | Poughkeepsie | Millerton | Dutchess | 12546 | G | 7081 | Millerton | N |  | 45 | [13 empty] | NM | N | Solectria 15kW | 2011-04-26 | 2011-05-03 | 5 | 2011-05-03 | [14 empty] | 2011-05-24 | 2011-05-26 |  | Y
Central Hudson |  | Self | CH-08862 | Poughkeepsie | Staatsburg | Dutchess | 12580 | G | 7011 | Hibernia | N |  | 1.88 | [13 empty] | NM | N | Enphase M190 | 2011-04-26 | 2011-04-27 | 1 | 2011-04-27 | [14 empty] | 2011-12-09 | 2011-12-19 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03687 | Newburgh | New Paltz | Ulster | 12561 | G | 5031 | Galeville | N |  | 7.2 | [13 empty] | NM | N | Fronius 7.5 | 2011-04-29 | 2011-05-03 | 2 | 2011-05-03 | [14 empty] | 2011-05-20 | 2011-05-26 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03692 | Newburgh | New Paltz | Ulster | 12561 | G | 5024 | Ohioville | N |  | 7.2 | [13 empty] | NM | N | Fronius | 2011-05-02 | 2011-05-06 | 4 | 2011-05-06 | [14 empty] | 2011-06-01 | 2011-06-02 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03786 | Newburgh | New Paltz | Ulster | 12561 | G | 5031 | Galeville | N |  | 7.92 | [13 empty] | NM | N | Fronius IG plus | 2011-05-02 | 2011-05-05 | 3 | 2011-05-05 | [14 empty] | 2011-06-01 | 2011-06-02 |  | Y
Central Hudson |  | Quad State Solar, Inc. | CH-02950 | Kingston | Saugerties | Ulster | 12477 | G | 3002 | Saugerties | N |  | 25 | [13 empty] | NM | N | SB7000 (4) | 2011-05-03 | 2011-05-09 | 4 | 2011-05-09 | [14 empty] | 2011-10-18 | 2011-10-18 |  | Y
Central Hudson |  | RGS Energy | CH-03024 | Catskill | W Coxsackie | Greene | 12192 | G | 1076 | Coxsackie | N |  | 6 | [13 empty] | NM | N | SMA sb6000 | 2011-05-10 | 2011-05-13 | 3 | 2011-05-13 | [14 empty] | 2011-10-14 | 2011-10-20 |  | Y
Central Hudson |  | Burke Electric and Solar | CH-00762 | Fishkill | Hopewell Jct |  | 12533 | G | 8072 | Shenandoah | N |  | 8.1 | [13 empty] | NM | N | Enphase | 2011-05-10 | 2011-05-17 | 5 | 2011-05-17 | [14 empty] | 2011-06-02 | 2011-06-09 |  | W
Central Hudson |  | Green Building and Material Supply, Inc. | CH-01153 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 7024 | Tinkertown | N |  | 21.84 | [13 empty] | NM | N | Fronious 11.2 | 2011-05-18 | 2011-05-18 | 0 | 2011-05-18 | [14 empty] | 2011-10-20 | 2011-10-26 |  | Y
Central Hudson |  | EMSA Solar, LLC | CH-01106 | Newburgh | New Paltz | Ulster | 12561 | G | 5021 | Ohioville | N | CH-00621 | 48.75 | [13 empty] | NM | N | Satcon 50kW | 2011-05-12 | 2011-05-18 | 4 | 2011-05-18 | [14 empty] | 2011-06-08 | 2011-06-08 |  | Y
Central Hudson |  | Mercury Solar Systems | CH-02622 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8096 | Fishkill Plains | N |  | 9 | [13 empty] | NM | N | SPR Sunpower 5000 (1) 4000 (1) | 2011-05-17 | 2011-05-20 | 3 | 2011-05-20 | [14 empty] | 2011-12-06 | 2011-12-06 |  | Y
Central Hudson |  | Mannino Electric | CH-02605 | Newburgh | New Paltz | Ulster | 12561 | G | 5031 | Galeville | N |  | 5 | [13 empty] | NM | N | (26) Enphase 0.19 | 2011-05-18 | 2011-05-23 | 3 | 2011-05-23 | [14 empty] | 2011-05-23 | 2011-05-26 |  | Y
Central Hudson |  | SolarCity | CH-05555 | Catskill | Freehold | Greene | 12431 | G | 2061 | Freehold | N |  | 10 | [13 empty] | NM | N | Fronious 10 | 2011-05-18 | 2011-05-24 | 4 | 2011-05-24 | [14 empty] | 2011-08-01 | 2011-08-04 |  | Y
Central Hudson |  | Solar Generation | CH-08209 | Kingston | W Hurley | Ulster | 12491 | G | 2094 | Hurley Ave | N | CH-08209 | 4 | [13 empty] | NM | N | Fronius IG4000 | 2011-05-18 | 2011-05-24 | 4 | 2011-05-24 | [14 empty] | 2011-10-14 | 2011-10-20 |  | Y
Central Hudson |  | RGS Energy | CH-02998 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7061 | Milan | N |  | 16 | [13 empty] | NM | N | SMA 8000 | 2011-05-19 | 2011-05-25 | 4 | 2011-05-25 | [14 empty] | 2011-09-12 | 2011-09-12 |  | Y
Central Hudson |  | RGS Energy | CH-03025 | Catskill | New Baltimore | Greene | 12124 | G | 1083 | New Baltimore | N |  | 6 | [13 empty] | NM | N | SMA6000 | 2011-05-19 | 2011-05-25 | 4 | 2011-05-25 | [14 empty] | 2011-10-31 | 2011-11-04 |  | Y
Central Hudson |  | Solar Generation | CH-08092 | Kingston | Woodstock | Ulster | 12498 | G | 3012 | Woodstock | N |  | 16.2 | [13 empty] | NA | N | Enphase | 2011-05-25 | 2011-06-01 | 4 | 2011-06-01 | [14 empty] | 2011-07-12 | 2011-07-14 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03587 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7061 | Milan | N |  | 11.75 | [13 empty] | NM | N | (2) Aurura Power one PVI6000 | 2011-05-26 | 2011-06-01 | 3 | 2011-06-01 | [14 empty] | 2011-06-29 | 2011-07-01 |  | Y
Central Hudson |  | Sun Mountain | CH-09090 | Kingston | Kerhonkson | Ulster | 12446 | G | 3082 | Kerhonkson | N |  | 6 | [13 empty] | NM | N | SMA 6000 | 2011-05-27 | 2011-06-02 | 3 | 2011-06-02 | [14 empty] | 2011-09-06 | 2011-09-09 |  | Y
Central Hudson |  | ETM Solar Works | CH-01123 | Kingston | Stone Ridge | Ulster | 12484 | G | 3021 | High Falls | N |  | 2.5 | [13 empty] | NM | N | Fronious 2500 | 2011-05-31 | 2011-06-02 | 2 | 2011-06-02 | [14 empty] | 2012-10-16 | 2012-10-23 |  | W
Central Hudson |  | Renewable Energy Solutions | CH-02957 | Newburgh | Highland |  | 12528 | G | 5082 | Highland | TBD |  | 0.43 | [13 empty] | NM | N | Enphase | 2011-06-17 | 2011-06-22 | 3 | 2011-06-22 | [17 empty] | W |  | Customer has Net Meter
Central Hudson |  | SunDog Solar | CH-09155 | Catskill | Palenville |  | 12463 | G | 2001 | North Catskill | TBD |  | 4.44 | [13 empty] | NM | N | Enphase | 2011-06-02 | 2011-06-08 | 4 | 2011-06-08 | [17 empty] | W |  | Customer has Net Meter
Central Hudson |  | Mercury Solar Systems | CH-02628 | Fishkill | Cold Spg | Putnam | 10516 | G | 8086 | Tioronda | N |  | 4 | [13 empty] | NM | N | SMA SB4000 | 2011-06-09 | 2011-06-15 | 4 | 2011-06-15 | [14 empty] | 2011-12-09 | 2011-12-09 |  | Y
Central Hudson |  | Empire Solar Store | CH-01095 | Catskill | Catskill | Greene | 12414 | G | 2003 | North Catskill | N |  | 2.66 | [13 empty] | NM | N | (14) Enphase M190 | 2011-06-10 | 2011-06-15 | 3 | 2011-06-15 | [14 empty] | 2012-01-04 | 2012-01-12 |  | Y
Central Hudson |  | Hudson Solar | CH-02029 | Kingston | Shady | Ulster | 12409 | G | 3012 | Woodstock | N | CH-02029 | 3 | [13 empty] | NM | N | SMA | 2011-06-15 | 2011-06-20 | 3 | 2011-06-20 | [14 empty] | 2011-08-17 | 2011-08-24 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03585 | Kingston | Olive Brdg | Ulster | 12461 | G | 3023 | High Falls | N |  | 19.5 | [13 empty] | NM | N | Aurura | 2011-06-22 | 2011-06-28 | 4 | 2011-06-28 | [14 empty] | 2011-07-22 | 2011-07-27 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03653 | Newburgh | Newburgh | Orange | 12550 | G | 4011 | West Balmville | N |  | 9 | [13 empty] | NM | N | Power one | 2011-06-22 | 2011-06-29 | 5 | 2011-06-29 | [14 empty] | 2011-08-12 | 2011-08-16 |  | Y
Central Hudson |  | Mannino Electric | CH-02607 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7055 | Rhinebeck | N |  | 38 | [13 empty] | NM | N | enphase | 2011-06-24 | 2011-06-30 | 4 | 2011-06-30 | [14 empty] | 2011-07-19 | 2011-07-20 |  | Y
Central Hudson |  | Hudson Solar | CH-01625 | Catskill | Westerlo | Albany | 12193 | G | 1091 | Westerlo | N |  | 7 | [13 empty] | NM | N | SPR-7000M | 2011-06-30 | 2011-07-07 | 4 | 2011-07-07 | [14 empty] | 2011-07-07 | 2011-07-11 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03676 | Newburgh | Highland | Ulster | 12528 | G | 5082 | Highland | N | CH-03676 | 2.94 | [13 empty] | NM | N | Power One Aurora | 2011-07-05 | 2011-07-07 | 2 | 2011-07-07 | [14 empty] | 2011-08-03 | 2011-08-04 |  | Y
Central Hudson |  | Solar Generation | CH-08184 | Kingston | Saugerties | Ulster | 12477 | G | 3001 | Saugerties | N |  | 6 | [13 empty] | NM | N | Fronius IG plus 6.0 | 2011-07-07 | 2011-07-12 | 3 | 2011-07-12 | [14 empty] | 2012-05-30 | 2012-06-08 |  | Y
Central Hudson |  | Mannino Electric | CH-02594 | Poughkeepsie | Tivoli | Dutchess | 12583 | G | 7062 | Milan | N |  | 8.55 | [13 empty] | NM | N | Enphase | 2011-07-08 | 2011-07-13 | 3 | 2011-07-13 | [14 empty] | 2012-01-27 | 2012-02-03 |  | Y
Central Hudson |  | Hudson Solar | CH-01305 | Poughkeepsie | Clinton Corners | Dutchess | 12514 | G | 7071 | Stanfordville | N |  | 12.88 | [13 empty] | NM | N | SMA 6000M SMA 7000M | 2011-07-12 | 2011-07-15 | 3 | 2011-07-15 | [14 empty] | 2011-11-07 | 2011-11-07 |  | Y
Central Hudson |  | Hudson Solar | CH-01461 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8095 | Fishkill Plains | N |  | 6.66 | [13 empty] | NM | N | SMA 7000US | 2011-07-12 | 2011-07-14 | 2 | 2011-07-14 | [14 empty] | 2011-08-18 | 2011-08-18 |  | Y
Central Hudson |  | Hudson Solar | CH-01886 | Poughkeepsie | Pine Plns | Dutchess | 12567 | G | 7095 | Smithfield | N |  | 23 | [13 empty] | NM | N | (2) SMA 7000M (1) sma 5000M (1) SMA4000M | 2011-07-12 | 2011-07-14 | 2 | 2011-07-14 | [14 empty] | 2011-09-19 | 2011-09-22 |  | Y
Central Hudson |  | Hudson Solar | CH-02315 | Newburgh | Gardiner | Ulster | 12525 | G | 5031 | Galeville | N |  | 6 | [13 empty] | NM | N | SMA 6000 | 2011-07-12 | 2011-07-15 | 3 | 2011-07-15 | [14 empty] | 2011-08-10 | 2011-08-16 |  | Y
Central Hudson |  | Hudson Solar | CH-02443 | Kingston | Saugerties | Ulster | 12477 | G | 3003 | Saugerties | N | CH-01386 | 3.33 | [13 empty] | NM | N | SMA 4000US | 2011-07-12 | 2011-07-14 | 2 | 2011-07-14 | [14 empty] | 2011-08-08 | 2011-08-10 |  | Y
Central Hudson |  | Hudson Solar | CH-02482 | Newburgh | New Paltz | Ulster | 12561 | G | 5031 | Galeville | N | CH-01940 | 1.8 | [13 empty] | NM | N | SMA 3000 | 2011-07-12 | 2011-07-13 | 1 | 2011-07-13 | [14 empty] | 2011-07-28 | 2011-08-03 |  | Y
Central Hudson |  | Conscious Energy | CH-00800 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7052 | Rhinebeck | N | CH-00800 | 2.28 | [13 empty] | NM | N | (12) Enphase M190 | 2011-07-19 | 2011-07-21 | 2 | 2011-07-21 | [14 empty] | 2011-08-23 | 2011-08-26 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03572 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6097 | Manchester | N |  | 24.5 | [13 empty] | NM | N | (2) Fronius 11.4 | 2011-07-20 | 2011-07-22 | 2 | 2011-07-22 | [14 empty] | 2011-09-14 | 2011-09-21 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03576 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6097 | Manchester | N |  | 12.74 | [13 empty] | NM | N | Fronious 11.4 | 2011-07-20 | 2011-07-22 | 2 | 2011-07-22 | [14 empty] | 2011-09-16 | 2011-09-21 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03619 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6097 | Manchester | N |  | 12.74 | [13 empty] | NM | N | Fronious 11.4 | 2011-07-20 | 2011-07-22 | 2 | 2011-07-22 | [14 empty] | 2011-09-16 | 2011-09-21 |  | Y
Central Hudson |  | Skylands Renewable Energy, LLC | CH-08899 | Kingston | Grahamsvl | Sullivan | 12740 | G | 3091 | Neversink | N |  |  |  | 11 | [11 empty] | NM | N | Weg Ter 11.0 (1) | 2011-08-04 | 2011-08-09 | 3 | 2011-08-09 | [14 empty] | 2011-12-28 | 2011-12-30 |  | Y
Central Hudson |  | Appolo-Hudson Valley | CH-00719 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8095 | Fishkill Plains | N |  | 0.75 | [13 empty] | NM | N | 2 Enphase M215-60-2LL | 2011-08-03 | 2011-08-03 | 0 | 2011-08-03 | [14 empty] | 2015-07-27 | 2015-07-30 |  | Y
Central Hudson |  | Self | CH-08882 | Newburgh | New Windsor | Orange | 12553 | G | 4045 | Union Ave | N |  | 0.5 | [13 empty] | NM | N | (1) Trace Engineering ST1500 | 2011-08-01 | 2011-08-05 | 4 | 2011-08-05 | [14 empty] | 2011-08-09 | 2011-08-12 |  | Y
Central Hudson |  | SolarCity | CH-06707 | Poughkeepsie | Lagrangevl | Dutchess | 12540 | G | 6055 | Todd Hill | N |  | 5 | [13 empty] | NM | N | Solar Edge | 2011-08-04 | 2011-08-10 | 4 | 2011-08-10 | [14 empty] | 2012-03-23 | 2012-03-26 |  | Y
Central Hudson |  | Solar Generation | CH-08073 | Kingston | Saugerties | Ulster | 12477 | G | 3014 | Woodstock | N |  | 14.7 | [13 empty] | NM | N | (2) Fronius 7.5 | 2011-08-04 | 2011-08-10 | 4 | 2011-08-10 | [14 empty] | 2011-12-15 | 2011-12-28 |  | Y
Central Hudson |  | Solar Alchemy | CH-08999 | Kingston | Kerhonkson | Ulster | 12446 | G | 3081 | Kerhonkson | N |  | 7.02 | [13 empty] | NM | N | Enphase | 2011-08-04 | 2011-08-10 | 4 | 2011-08-10 | [14 empty] | 2011-10-21 | 2011-10-27 |  | Y
Central Hudson |  | D&M Alternative Energy | CH-00813 | Catskill | Coxsackie | Greene | 12051 | G | 1071 | Coxsackie | N |  | 0.92 | [13 empty] | NM | N | (4) Enphase M190 | 2011-08-17 | 2011-08-17 | 0 | 2011-08-17 | [14 empty] | 2011-10-25 | 2011-10-27 |  | Y
Central Hudson |  | Hudson Valley Wind Energy, LLC | CH-02554 | Poughkeepsie | Millerton | Dutchess | 12546 | G | 7081 | Millerton | N |  |  |  | 10 | [11 empty] | NM | N | Diversified Technology Powersynch II AMFA-27 | 2011-08-09 | 2011-08-12 | 3 | 2011-08-12 | [14 empty] | 2011-08-22 | 2011-08-25 |  | Y
Central Hudson |  | Hudson Solar | CH-01613 | Catskill | Catskill | Greene | 12414 | G | 2005 | North Catskill | N |  | 5 | [13 empty] | NM | N | SMA 5000M | 2011-08-10 | 2011-08-15 | 3 | 2011-08-15 | [14 empty] | 2011-09-09 | 2011-09-14 |  | Y
Central Hudson |  | Hudson Solar | CH-01685 | Kingston | W Hurley | Ulster | 12491 | G | 3014 | Woodstock | N | CH-01685 | 8 | [13 empty] | NM | N | (2) SPR 4000M | 2011-08-10 | 2011-08-15 | 3 | 2011-08-15 | [14 empty] | 2011-11-30 | 2011-12-01 |  | Y
Central Hudson |  | Hudson Solar | CH-01797 | Poughkeepsie | Tivoli | Dutchess | 12583 | G | 7062 | Milan | N |  | 18 | [13 empty] | NM | N | (2) SMA 7000US (1) SMA 4000US | 2011-08-10 | 2011-08-15 | 3 | 2011-08-15 | [14 empty] | 2011-09-19 | 2011-09-22 |  | Y
Central Hudson |  | Hudson Solar | CH-01833 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7056 | Rhinebeck | N |  | 9 | [13 empty] | NM | N | (1) SMA 4000M (1) SMA 5000M | 2011-08-10 | 2011-08-15 | 3 | 2011-08-15 | [14 empty] | 2011-09-27 | 2011-10-03 |  | Y
Central Hudson |  | Hudson Solar | CH-02436 | Kingston | W Hurley | Ulster | 12491 | G | 3014 | Woodstock | N | CH-01685 | 2.76 | [13 empty] | NM | N | SB 3000US | 2011-08-10 | 2011-08-15 | 3 | 2011-08-15 | [14 empty] | 2011-11-30 | 2011-12-01 |  | Y
Central Hudson |  | Hudson Solar | CH-02440 | Kingston | Kingston | Ulster | 12401 | G | 1014 | Boulevard | Y | CH-01700 | 6 | 6 | [12 empty] | NM | N | Xantrex XW60481XantrexXW6048 (DC) | 2011-08-10 | 2011-08-12 | 2 | 2011-08-12 | [14 empty] | 2011-10-24 | 2011-10-27 |  | Y
Central Hudson |  | Murphy Solar Power | CH-02756 | Catskill | Coxsackie | Greene | 12051 | G | 1071 | Coxsackie | N |  | 2.3 | [13 empty] | NM | N | SMA 3000US | 2011-08-10 | 2011-08-12 | 2 | 2011-08-12 | [14 empty] | 2011-11-11 | 2011-11-11 |  | Y
Central Hudson |  | Self | CH-08864 | Kingston | Kingston | Ulster | 12401 | G | 2014 | Lincoln Park | N |  | 49.68 | [13 empty] | NM | N | (3) SMA SB8000 (54) DGM-240 | 2011-08-12 | 2011-08-19 | 5 | 2011-08-19 | [14 empty] | 2011-09-07 | 2011-09-12 |  | W
Central Hudson |  | Solar Generation | CH-08088 | Kingston | West Shokan | Ulster | 12494 | G | 3011 | Woodstock | Y | CH-08088 | 3.36 | [13 empty] | NM | N | (14) Enphase M215 | 2011-08-24 | 2011-08-30 | 4 | 2011-08-30 | [14 empty] | 2012-01-13 | 2012-01-16 |  | Y
Central Hudson |  | Hudson Solar | CH-02303 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8092 | Fishkill Plains | N |  | 5 | [13 empty] | NM | N | SMA 5000 | 2011-08-26 | 2011-09-02 | 5 | 2011-09-02 | [14 empty] | 2011-09-27 | 2011-10-03 |  | Y
Central Hudson |  | Hudson Solar | CH-02307 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8071 | Shenandoah | N | CH-02307 | 3.68 | [13 empty] | NM | N | SMA 4000 | 2011-08-26 | 2011-09-02 | 5 | 2011-09-02 | [14 empty] | 2011-11-28 | 2011-12-01 |  | Y
Central Hudson |  | SolarCity | CH-05598 | Catskill | Ravena | Columbia | 12173 | G | 1081 | New Baltimore | N |  | 9.1 | [13 empty] | NM | N | (2) Frounious 5100 (1) Frounious 4000 | 2011-08-26 | 2011-09-02 | 5 | 2011-09-02 | [14 empty] | 2011-12-22 | 2011-12-28 |  | Y
Central Hudson |  | SolarCity | CH-06180 | Newburgh | New Paltz | Ulster | 12561 | G | 5023 | Ohioville | N |  | 6 | [13 empty] | NM | N | (1) Fronious 2000 (1) Fronious 400 | 2011-08-30 | 2011-09-06 | 4 | 2011-09-06 | [14 empty] | 2012-04-17 | 2012-04-23 |  | Y
Central Hudson |  | Mannino Electric | CH-02597 | Kingston | Saugerties | Ulster | 12477 | G | 3004 | Saugerties | N |  | 9.2 | [13 empty] | NM | N | (1) PVI4000 (2) PVI5300 | 2011-08-31 | 2011-09-07 | 4 | 2011-09-07 | [14 empty] | 2011-12-27 | 2011-12-29 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03578 | Newburgh | Gardiner | Ulster | 12525 | G | 5034 | Galeville | N | CH-03578 | 9 | [13 empty] | NM | N | (2) PVI 6000 | 2011-09-01 | 2011-09-08 | 4 | 2011-09-08 | [14 empty] | 2011-10-27 | 2011-11-02 |  | Y
Central Hudson |  | Mercury Solar Systems | CH-02613 | Newburgh | Cornwall-Hdsn | Orange | 12520 | G | 4043 | Union Ave | N |  | 6 | [13 empty] | NM | N | (1) PVI6000 | 2011-09-01 | 2011-09-07 | 3 | 2011-09-07 | [14 empty] | 2012-02-28 | 2012-03-06 |  | Y
Central Hudson |  | Lotus Energy Inc. | CH-03874 | Kingston | Rosendale | Ulster | 12472 | G | 3022 | High Falls | N |  | 13.2 | [13 empty] | RNM | N | (2) SB7000 | 2011-09-02 | 2011-09-08 | 3 | 2011-09-08 | [14 empty] | 2011-11-16 | 2011-11-16 |  | Y
Central Hudson |  | SunDog Solar | CH-09147 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7041 | Staatsburg | N |  | 5.76 | [13 empty] | NM | N | GVFX3648 | 2011-09-07 | 2011-09-14 | 5 | 2011-09-14 | [14 empty] | 2011-12-28 | 2011-12-30 |  | Y
Central Hudson |  | Hudson Solar | CH-01684 | Kingston | Lk Hill | Ulster | 12448 | G | 3012 | Woodstock | N | CH-01684 | 2.85 | [13 empty] | NM | N | SMA3000 | 2011-09-14 | 2011-09-20 | 4 | 2011-09-20 | [14 empty] | 2011-09-30 | 2011-10-05 |  | Y
Central Hudson |  | Hudson Solar | CH-02114 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6096 | Manchester | N |  | 7 | [13 empty] | NM | N | SMA 7000 | 2011-09-14 | 2011-09-20 | 4 | 2011-09-20 | [14 empty] | 2011-12-27 | 2011-12-29 |  | Y
Central Hudson |  | Sungevity Inc | CH-09352 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8065 | Merritt Park | N |  | 5 | [13 empty] | NM | N | PVI5000 | 2011-09-14 | 2011-09-20 | 4 | 2011-09-20 | [14 empty] | 2012-01-04 | 2012-01-12 |  | Y
Central Hudson |  | Hudson Solar | CH-01798 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7061 | Milan | N |  | 21 | [13 empty] | NM | N | (3) SB7000US | 2011-09-21 | 2011-09-26 | 3 | 2011-09-26 | [14 empty] | 2011-10-03 | 2011-10-06 |  | Y
Central Hudson |  | Hudson Solar | CH-02332 | Kingston | Stone Ridge | Ulster | 12484 | G | 3023 | High Falls | N |  | 11 | [13 empty] | NM | N | (2) Sunpower 6000M | 2011-10-04 | 2011-10-10 | 4 | 2011-10-10 | [14 empty] | 2011-10-14 | 2011-10-20 |  | Y
Central Hudson |  | Sunrise Solar Solutions, LLC | CH-09659 | Catskill | Hunter | Greene | 12442 | E | 2081 | Hunter | N |  | 29.45 | [13 empty] | NM | N | (139) Enphase M215 | 2011-09-27 | 2011-10-04 | 5 | 2011-10-04 | [14 empty] | 2011-12-20 | 2011-12-28 |  | Y
Central Hudson |  | Solar Generation | CH-08101 | Kingston | Kingston | Ulster | 12401 | G | 2016 | Lincoln Park | N |  | 7.04 | [13 empty] | NM | N | Enphase | 2011-10-03 | 2011-10-10 | 5 | 2011-10-10 | [14 empty] | 2011-10-20 | 2011-10-26 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03626 | Fishkill | Stormvl | Dutchess | 12582 | G | 8095 | Fishkill Plains | N | CH-03626 | 5 | [13 empty] | NM | N | Aurora PVI5000 | 2011-10-04 | 2011-10-11 | 5 | 2011-10-11 | [14 empty] | 2011-11-21 | 2011-11-28 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03638 | Newburgh | New Paltz | Ulster | 12561 | G | 5023 | Ohioville | N |  | 5 | [13 empty] | NM | N | Aurora PVI5000 | 2011-10-04 | 2011-10-10 | 4 | 2011-10-10 | [14 empty] | 2011-10-28 | 2011-11-04 |  | Y
Central Hudson |  | Sol Providers | CH-08946 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7042 | Staatsburg | N | CH-08946 | 1.505 | [13 empty] | NM | N | Enphase M215 (7) | 2011-10-04 | 2011-10-10 | 4 | 2011-10-10 | [14 empty] | 2012-02-27 | 2012-03-05 |  | Y
Central Hudson |  | Sun Mountain | CH-09081 | Kingston | Rosendale | Ulster | 12472 | G | 3022 | High Falls | N |  | 6 | [13 empty] | NM | N | SMA 6000 | 2011-10-11 | 2011-10-13 | 2 | 2011-10-13 | [14 empty] | 2012-03-20 | 2012-03-27 |  | Y
Central Hudson |  | Deem Solar LLC | CH-00826 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8056 | North Chelsea | N |  | 2.5 | [13 empty] | NM | N | SunnyBoy SMA-2500U | 2011-11-16 | 2011-11-16 | 0 | 2011-11-16 | [14 empty] | 2013-11-22 | 2013-12-03 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00888 | Catskill | Leeds | Greene | 12451 | G | 2006 | North Catskill | N |  | 6.45 | [13 empty] | NM | N | Enphase 215 | 2011-10-13 | 2011-10-19 | 4 | 2011-10-19 | [14 empty] | 2011-12-22 | 2011-12-30 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03673 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7052 | Rhinebeck | N |  | 14 | [13 empty] | NM | N | (1) PVI-3000 (1) PVI-5000 (1) PVI-6000 | 2011-10-14 | 2011-10-19 | 3 | 2011-10-19 | [14 empty] | 2011-12-01 | 2011-12-01 |  | Y
Central Hudson |  | Hudson Solar | CH-01310 | Poughkeepsie | Tivoli | Dutchess | 12583 | G | 7051 | Rhinebeck | N |  | 27.75 | [13 empty] | NM | N | (3) SB7000US (1) SB5000US | 2011-10-20 | 2011-10-26 | 4 | 2011-10-26 | [14 empty] | 2012-04-03 | 2012-04-04 |  | Y
Central Hudson |  | Hudson Solar | CH-01468 | Catskill | Palenvl | Greene | 12463 | G | 2042 | South Cairo | N |  | 6.29 | [13 empty] | NM | N | (1) SB4000US (1) SB3000US | 2011-10-20 | 2011-10-26 | 4 | 2011-10-26 | [14 empty] | 2011-10-26 | 2011-11-01 |  | Y
Central Hudson |  | SolarCity | CH-04976 | Catskill | Tannersvl | Greene | 12485 | G | 2385 | Lawrenceville | N |  | 8.3 | [13 empty] | NM | N | (1) SE5000 & (1) SE3300 | 2011-10-20 | 2011-10-24 | 2 | 2011-10-24 | [14 empty] | 2012-06-08 | 2012-06-13 |  | Y
Central Hudson |  | SolarCity | CH-07691 | Catskill | Athens | Greene | 12015 | G | 2002 | North Catskill | N |  | 6 | [13 empty] | NM | N | IG Fronious 6.0 | 2011-10-20 | 2011-10-24 | 2 | 2011-10-24 | [14 empty] | 2012-03-26 | 2012-03-27 |  | Y
Central Hudson |  | Solar Alchemy | CH-09004 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6042 | Spackenkill | N |  | 6.45 | [13 empty] | NM | N | Enphase M215(30) | 2011-10-21 | 2011-10-27 | 4 | 2011-10-27 | [14 empty] | 2012-01-30 | 2012-02-08 |  | Y
Central Hudson |  | Sun Mountain | CH-09126 | Kingston | Stone Ridge | Ulster | 12484 | G | 3023 | High Falls | N |  | 14 | [13 empty] | NM | N | SB7000 (2) | 2011-10-25 | 2011-11-01 | 5 | 2011-11-01 | [8 empty] | 350 | 350 |  | 2012-06-12 | 2012-06-12 | 2012-06-13 | 2012-06-06 | 2012-06-14 |  | Y
Central Hudson |  | Hudson Solar | CH-01243 | Poughkeepsie | Clinton Corners |  | 12514 | G | 7071 | Stanfordville | TBD |  | 11.84 | [13 empty] | NM | N | (2) SB6000US | 2011-10-26 | 2011-10-28 | 2 | 2011-10-28 | [17 empty] | W |  | Customer has net meter. Installation abandoned.
Central Hudson |  | Hudson Solar | CH-01288 | Kingston | Boicevl | Ulster | 12412 | G | 3011 | Woodstock | N |  | 11.5 | [13 empty] | NM | N | (1) Sunpower 4000M (1) Sunpower 7000M | 2011-10-26 | 2011-11-02 | 5 | 2011-11-02 | [14 empty] | 2011-12-14 | 2011-12-16 |  | Y
Central Hudson |  | Hudson Solar | CH-01659 | Kingston | Accord | Ulster | 12404 | G | 3081 | Kerhonkson | N |  | 5 | [13 empty] | NM | N | (1) SMA SB5000US | 2011-10-26 | 2011-11-02 | 5 | 2011-11-02 | [14 empty] | 2011-11-29 | 2011-11-30 |  | Y
Central Hudson |  | Hudson Solar | CH-02236 | Kingston | Shady | Ulster | 12409 | G | 3012 | Woodstock | N |  | 5.55 | [13 empty] | NM | N | SB6000 US | 2011-10-26 | 2011-10-28 | 2 | 2011-10-28 | [14 empty] | 2011-10-28 | 2011-11-04 |  | Y
Central Hudson |  | Hudson Solar | CH-02271 | Poughkeepsie | Clinton Corners | Dutchess | 12514 | G | 7071 | Stanfordville | N |  | 20.72 | [13 empty] | NM | N | (3) SB7000 | 2011-10-26 | 2011-10-28 | 2 | 2011-10-28 | [14 empty] | 2011-12-13 | 2011-12-13 |  | Y
Central Hudson |  | Hudson Solar | CH-02488 | Newburgh | Marlboro | Ulster | 12542 | G | 5003 | Marlboro | N | CH-01969 | 15 | [13 empty] | NM | N | (3) Sunpower SPR-5000m | 2011-10-26 | 2011-11-01 | 4 | 2011-11-01 | [14 empty] | 2011-11-28 | 2011-12-02 |  | Y
Central Hudson |  | Hudson Solar | CH-02503 | Newburgh | Marlboro | Ulster | 12542 | G | 5003 | Marlboro | N | CH-01384 | 7 | [13 empty] | NM | N | (2) SB 4000-US | 2011-10-26 | 2011-10-28 | 2 | 2011-10-28 | [14 empty] | 2012-03-07 | 2012-03-12 |  | Y
Central Hudson |  | Solar Generation | CH-08094 | Kingston | Saugerties | Ulster | 12477 | G | 3003 | Saugerties | N |  | 6.75 | [13 empty] | NM | N | (30) Enphase M210 | 2011-10-26 | 2011-11-02 | 5 | 2011-11-02 | [14 empty] | 2011-11-23 | 2011-11-23 |  | Y
Central Hudson |  | RGS Energy | CH-03042 | Catskill | Ravena | Albany | 12143 | G | 1082 | New Baltimore | N |  | 7 | [13 empty] | NM | N | sma 7000us | 2011-10-28 | 2011-11-04 | 5 | 2011-11-04 | [14 empty] | 2012-03-12 | 2012-03-14 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03570 | Newburgh | New Paltz | Ulster | 12561 | G | 5031 | Galeville | N | CH-03570 | 6 | [13 empty] | NM | N | (1) Power One Aurora | 2011-10-28 | 2011-11-04 | 5 | 2011-11-04 | [14 empty] | 2012-04-30 | 2012-05-07 |  | W
Central Hudson |  | Lighthouse Solar | CH-03625 | Kingston | Grahamsvl | Sullivan | 12740 | G | 3091 | Neversink | N |  | 7.5 | [13 empty] | NM | N | Fronius IG Plus 7.5 | 2011-10-28 | 2011-11-03 | 4 | 2011-11-03 | [14 empty] | 2012-04-09 | 2012-04-11 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03667 | Kingston | Grahamsvl | Sullivan | 12740 | G | 3091 | Neversink | N |  | 7.5 | [13 empty] | NM | N | Frounius 7.5 | 2011-10-28 | 2011-11-03 | 4 | 2011-11-03 | [14 empty] | 2012-04-09 | 2012-04-10 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03697 | Newburgh | Newburgh | Orange | 12550 | G | 4023 | Coldenham | N |  | 5.16 | [13 empty] | NM | N | (24) Enphase M 215 | 2011-10-28 | 2011-11-03 | 4 | 2011-11-03 | [14 empty] | 2012-01-30 | 2012-02-06 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03744 | Newburgh | New Paltz | Ulster | 12561 | G | 5031 | Galeville | N | CH-03744 | 6 | [13 empty] | NM | N | (1) Aurora PVI-6000 | 2011-10-28 | 2011-11-03 | 4 | 2011-11-03 | [14 empty] | 2012-01-16 | 2012-01-16 |  | Y
Central Hudson |  | RGS Energy | CH-03018 | Catskill | Surprise | Greene | 12176 | G | 2061 | Freehold | N |  | 4 | [13 empty] | NM | N | SMA SunnyBoy 4000US | 2011-11-07 | 2011-11-08 | 1 | 2011-11-08 | [14 empty] | 2011-12-13 | 2011-12-16 |  | Y
Central Hudson |  | SunDog Solar | CH-09144 | Kingston | Ulster Pk | Ulster | 12487 | G | 1014 | Boulevard | N |  | 6.45 | [13 empty] | NM | N | Enphase M215-60-240-S22 | 2011-11-08 | 2011-11-09 | 1 | 2011-11-09 | [14 empty] | 2011-12-29 | 2011-12-29 |  | Y
Central Hudson |  | Sungevity Inc | CH-09545 | Newburgh | Highland | Ulster | 12528 | G | 5022 | Ohioville | N |  | 6 | [13 empty] | NM | N | Power-One PVI-6000-OUTD-US | 2011-11-08 | 2011-11-11 | 3 | 2011-11-11 | [14 empty] | 2012-04-02 | 2012-04-03 |  | Y
Central Hudson |  | Sol Providers | CH-08922 | Poughkeepsie | Pleasant Vly |  | 12569 | G | 6057 | Todd Hill | TBD |  | 5.16 | [13 empty] | NM | N | Enphase M215 (24) | 2011-11-10 | 2011-11-14 | 2 | 2011-11-14 | [14 empty] | 2012-02-24 | 2012-03-02 |  | W
Central Hudson |  | Lighthouse Solar | CH-03825 | Newburgh | Highland | Ulster | 12528 | G | 5082 | Highland | N | CH-03676 | 4.2 | [13 empty] | NM | N | PVI-4.2-OUTD-US | 2011-11-14 | 2011-11-16 | 2 | 2011-11-16 | [14 empty] | 2011-12-27 | 2011-12-28 |  | Y
Central Hudson |  | Inverters Unlimited Inc | CH-02561 | Catskill | Greenvl | Greene | 12083 | G | 2061 | Freehold | N |  | 5.35 | [13 empty] | NM | N | SunnyBoy SB 3000 | 2011-11-14 | 2011-11-15 | 1 | 2011-11-15 | [14 empty] | 2011-11-30 | 2011-11-30 |  | Y
Central Hudson |  | Sungevity Inc | CH-09199 | Newburgh | Gardiner | Ulster | 12525 | G | 5011 | Modena | N |  | 20 | [13 empty] | NM | N | SMA 6000US & SMA 8000US | 2011-11-14 | 2011-11-15 | 1 | 2011-11-15 | [14 empty] | 2012-05-18 | 2012-05-24 |  | Y
Central Hudson |  | E2/ECTA Inc. | CH-01086 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6094 | Manchester | N |  | 55 | [13 empty] | NM | N | 3 x SMA SB10000, 3 x SMA SB7000, 1 x SMA SB4000 | 2011-12-02 | 2011-12-05 | 1 | 2011-12-05 | [14 empty] | 2011-12-20 | 2011-12-29 |  | Y
Central Hudson |  | E2/ECTA Inc. | CH-01087 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6094 | Manchester | N |  | 23 | [13 empty] | NM | N | 2x SB7000, 1x SB6000, 1x SB3000 | 2011-12-02 | 2011-12-05 | 1 | 2011-12-05 | [14 empty] | 2011-12-20 | 2011-12-29 |  | Y
Central Hudson |  | Pure Point Energy LLC | CH-02945 | Poughkeepsie | Verbank | Dutchess | 12585 | G | 6057 | Todd Hill | N | CH-01190 | 13.5 | [13 empty] | NM | N | Fronius IG Plus 11.4 (1) & Enphase M210 (10) | 2012-06-20 | 2012-06-26 | 4 | 2012-06-26 | [14 empty] | 2012-08-08 | 2012-08-15 |  | Y
Central Hudson |  | BQ Energy, LLC | CH-00755 | Newburgh | W Park | Ulster | 12429 | G | 5084 | Highland | N |  | 600 | [13 empty] | RNM | N | (24) Huawei SUN2000-25kTL-US | 2012-02-07 | 2012-02-27 | 13 | 2012-02-27 | 2012-02-07 | 2012-02-27 | 13 | 2012-03-22 | 2012-03-23 | 2012-06-19 | 60 | 20000 | 189750 | 221435.04 | 2016-07-28 | 2017-02-14 | 2017-02-14 | 2017-08-08 | 2017-08-10 | 2017-08-10 | 2017-10-30 | Y
Central Hudson |  | Hudson Solar | CH-02030 | Kingston | Bearsvl | Ulster | 12409 | G | 3012 | Woodstock | N |  | 10.8 | [13 empty] | NM | N | (1) SPR-3000m, (1) SPR-4000m, (1) SPR-5000m | 2011-11-21 | 2011-11-23 | 2 | 2011-11-23 | [14 empty] | 2011-12-20 | 2011-12-21 |  | Y
Central Hudson |  | Hudson Valley Wind Energy, LLC | CH-02552 | Catskill | Acra | Greene | 12405 | G | 2043 | South Cairo | N |  |  |  | 10 | [11 empty] | NM | N | Diversified Technology Powersynch II AMFA-27 | 2011-11-21 | 2011-11-22 | 1 | 2011-11-22 | [14 empty] | 2012-01-06 | 2012-01-11 |  | Y
Central Hudson |  | Mannino Electric | CH-02599 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7052 | Rhinebeck | N |  | 22.7 | [13 empty] | NM | N | M215-60-2LL-S22 | 2011-11-22 | 2011-11-22 | 0 | 2011-11-22 | [14 empty] | 2012-01-26 | 2012-01-30 |  | Y
Central Hudson |  | SolarCity | CH-06676 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7011 | Hibernia | N | CH-06676 | 20.5 | [13 empty] | NM | N | Fronius IG Plus V10, 7.5, 3.0 | 2011-11-22 | 2011-11-22 | 0 | 2011-11-22 | [14 empty] | 2012-01-25 | 2012-02-08 |  | Y
Central Hudson |  | Hudson Solar | CH-01251 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7053 | Rhinebeck | N |  | 21 | [13 empty] | NM | N | 3 SunPower SPR-7000m | 2011-11-30 | 2011-11-30 | 0 | 2011-11-30 | [14 empty] | 2011-12-27 | 2011-12-30 |  | Y
Central Hudson |  | Hudson Solar | CH-01322 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7051 | Rhinebeck | N |  | 4 | [13 empty] | NM | N | SMA SB-4000US | 2011-11-28 | 2011-11-29 | 1 | 2011-11-29 | [14 empty] | 2011-12-27 | 2011-12-29 |  | Y
Central Hudson |  | Hudson Solar | CH-01822 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6092 | Manchester | N |  | 5 | [13 empty] | NM | N | SunPower SPR-5000m | 2011-11-28 | 2011-11-29 | 1 | 2011-11-29 | [14 empty] | 2011-12-27 | 2011-12-30 |  | Y
Central Hudson |  | Hudson Solar | CH-02297 | Poughkeepsie | Stanfordville | Dutchess | 12581 | G | 7056 | Rhinebeck | N |  | 22 | [13 empty] | NM | N | SB7000 & 3xSB5000US | 2011-11-28 | 2011-12-02 | 4 | 2011-12-02 | [14 empty] | 2011-12-29 | 2011-12-30 |  | Y
Central Hudson |  | Hudson Solar | CH-02298 | Poughkeepsie | Stanfordvl | Dutchess | 12581 | G | 7072 | Stanfordville | N | CH-02298 | 10 | [13 empty] | NM | N | 2 x SPR-5000m1 | 2011-11-28 | 2011-11-29 | 1 | 2011-11-29 | [14 empty] | 2011-12-22 | 2011-12-30 |  | Y
Central Hudson |  | Hudson Solar | CH-01304 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 6057 | Todd Hill | N | CH-01304 | 10 | [13 empty] | NM | N | 4000m and 6000m SunPower | 2011-11-28 | 2011-11-30 | 2 | 2011-11-30 | [14 empty] | 2011-12-28 | 2011-12-30 |  | Y
Central Hudson |  | Hudson Solar | CH-01916 | Fishkill | Fishkill | Dutchess | 12524 | G | 8094 | Fishkill Plains | N |  | 4 | [13 empty] | NM | N | SunPower SPR-4000m | 2011-11-28 | 2011-11-28 | 0 | 2011-11-28 | [14 empty] | 2011-12-05 | 2011-12-05 |  | Y
Central Hudson |  | Hudson Solar | CH-01961 | Newburgh | New Windsor | Orange | 12553 | G | 4044 | Union Ave | N |  | 6 | [13 empty] | NM | N | SunnyBoy SMA SB-5000US | 2011-11-28 | 2011-11-28 | 0 | 2011-11-28 | [14 empty] | 2012-06-14 | 2012-06-21 |  | Y
Central Hudson |  | Hudson Solar | CH-02012 | Catskill | Catskill | Greene | 12414 | G | 2005 | North Catskill | N |  | 5 | [13 empty] | NM | N | SMA SunnyBoy SB-5000US | 2011-11-28 | 2011-11-28 | 0 | 2011-11-28 | [14 empty] | 2011-12-20 | 2011-12-21 |  | Y
Central Hudson |  | Hudson Solar | CH-02038 | Kingston | Woodstock |  | 12498 | G | 3012 | Woodstock | N |  | 7.4 | [13 empty] | NM | N | (2) SMA SunnyBoy SB-4000US | 2011-11-28 | 2011-11-28 | 0 | 2011-11-28 | [14 empty] | 2011-12-30 | 2012-01-04 |  | W
Central Hudson |  | Hudson Solar | CH-02234 | Kingston | Kingston | Ulster | 12401 | G | 1024 | East Kingston | Y |  | 4.5 | 4.5 | [12 empty] | NM | N | Xantrex XW4548-120/240-601XantrexXW4548 (DC) | 2011-11-30 | 2011-11-30 | 0 | 2011-11-30 | [14 empty] | 2013-10-04 | 2013-10-11 |  | Y
Central Hudson |  | SolarCity | CH-05891 | Poughkeepsie | Lagrange | Dutchess | 12540 | G | 6055 | Todd Hill | N |  | 10 | [13 empty] | NM | N | IG PLUS 10.0-240 | 2011-12-02 | 2011-12-02 | 0 | 2011-12-02 | [14 empty] | 2012-03-13 | 2012-03-20 |  | Y
Central Hudson |  | SolarCity | CH-06275 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 12 | [13 empty] | NM | N | Fronius IG Plus V 6.0-240 (2) | 2011-11-28 | 2011-11-29 | 1 | 2011-11-29 | [14 empty] | 2012-05-03 | 2012-05-08 |  | Y
Central Hudson |  | SolarCity | CH-07069 | Newburgh | Newburgh | Orange | 12550 | G | 5004 | Marlboro | N |  | 4 | [13 empty] | NM | N | Fronius IG 4000 | 2011-11-28 | 2011-11-29 | 1 | 2011-11-29 | [14 empty] | 2012-06-06 | 2012-06-11 |  | Y
Central Hudson |  | Kirchhoff Green Energy LLC | CH-03553 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7054 | Rhinebeck | N |  | 35 | [13 empty] | NM | N | SMA SB7000-US | 2011-11-29 | 2011-12-06 | 5 | 2011-12-06 | [14 empty] | 2012-02-29 | 2012-03-09 |  | Y
Central Hudson |  | Mannino Electric | CH-02603 | Kingston | High Fls | Ulster | 12440 | G | 3022 | High Falls | N |  | 3.01 | [13 empty] | NM | N | Enphase M215-60-2LL-S12 | 2011-11-29 | 2011-11-30 | 1 | 2011-11-30 | [14 empty] | 2011-12-27 | 2011-12-30 |  | Y
Central Hudson |  | SolarCity | CH-05268 | Newburgh | Highland | Ulster | 12528 | G | 5082 | Highland | N |  | 7.5 | [13 empty] | NM | N | Fronius IG Plus ver. 7.5 | 2011-11-29 | 2011-12-01 | 2 | 2011-12-01 | [14 empty] | 2012-03-19 | 2012-03-20 |  | Y
Central Hudson |  | Hudson Solar | CH-02450 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 6057 | Todd Hill | N | CH-01304 | 13 | [13 empty] | NM | N | SPR 7000m and SPR 6000m | 2011-11-30 | 2011-12-06 | 4 | 2011-12-06 | [14 empty] | 2011-12-28 | 2011-12-30 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03798 | Kingston | Port Ewen | Ulster | 12466 | G | 1012 | Boulevard | N | CH-03798 | 8.5 | [13 empty] | NM | N | PVI 4-2-OUTO-US | 2011-12-05 | 2011-12-05 | 0 | 2011-12-05 | [14 empty] | 2012-03-26 | 2012-03-28 |  | Y
Central Hudson |  | Mountaintop Greene Clean Energy | CH-02706 | Catskill | Elka Pk | Greene | 12427 | G | 2385 | Lawrenceville | N |  | 2.58 | [13 empty] | NM | N | (12) Enphase M215 | 2011-12-15 | 2011-12-15 | 0 | 2011-12-15 | [14 empty] | 2012-01-24 | 2012-01-24 |  | Y
Central Hudson |  | SolarCity | CH-07012 | Newburgh | Newburgh | Orange | 12550 | G | 4051 | Union Ave | N |  | 3.8 | [13 empty] | NM | N | Solaredge SE3800 | 2011-12-05 | 2011-12-05 | 0 | 2011-12-05 | [14 empty] | 2012-05-25 | 2012-05-30 |  | Y
Central Hudson |  | Northeast Smart Energy LLC | CH-02773 | Fishkill | Garrison | Putnam | 10524 | G | 8086 | Tioronda | N |  | 19 | [13 empty] | NM | N | SMA 7000US(1) & SMA6000US(2) | 2011-12-22 | 2011-12-22 | 0 | 2011-12-22 | [14 empty] | 2012-07-11 | 2012-07-13 |  | Y
Central Hudson |  | Solar Generation | CH-08310 | Newburgh | Wallkill | Ulster | 12589 | G | 5043 | East Walden | N | CH-01146 | 4.4 | [13 empty] | NM | N | SMA 5000US | 2011-12-07 | 2011-12-08 | 1 | 2011-12-08 | [14 empty] | 2012-01-13 | 2012-01-16 |  | Y
Central Hudson |  | Solar Generation | CH-08154 | Kingston | Kingston | Ulster | 12401 | G | 2094 | Hurley Ave | N |  | 6.93 | [13 empty] | NM | N | enphase m210 | 2011-12-08 | 2011-12-09 | 1 | 2011-12-09 | [14 empty] | 2012-01-13 | 2012-01-16 |  | Y
Central Hudson |  | Solar Generation | CH-08162 | Kingston | Bearsvl | Ulster | 12409 | G | 3012 | Woodstock | N |  | 3.15 | [13 empty] | NM | N | enphase m210 | 2011-12-08 | 2011-12-09 | 1 | 2011-12-09 | [14 empty] | 2012-01-16 | 2012-01-18 |  | Y
Central Hudson |  | United Green Solutions LLC | CH-09731 | Newburgh | Newburgh | Orange | 12550 | G | 4015 | West Balmville | N |  | 6.37 | [13 empty] | NM | N | SMA 7000 | 2011-12-14 | 2011-12-14 | 0 | 2011-12-14 | [14 empty] | 2012-01-06 | 2012-01-12 |  | Y
Central Hudson |  | SolarCity | CH-05534 | Catskill | Catskill | Greene | 12414 | G | 2001 | North Catskill | N |  | 5 | [13 empty] | NM | N | Fronius IG Plus V 5000 | 2011-12-12 | 2011-12-16 | 4 | 2011-12-16 | [14 empty] | 2012-06-06 | 2012-06-11 |  | Y
Central Hudson |  | 2K Solar Inc | CH-00621 | Newburgh | New Paltz | Ulster | 12561 | G | 5025 | Ohioville | Y | CH-00621 | 4.2 | [13 empty] | NM | N | SMA Sunnyboy 3000(3) | 2011-12-27 | 2011-12-29 | 2 | 2011-12-29 | [14 empty] | 2012-02-07 | 2012-02-10 |  | Y
Central Hudson |  | SolarCity | CH-05238 | Catskill | Athens | Greene | 12015 | G | 1074 | Coxsackie | N |  | 4.7 | [13 empty] | NM | N | Fronius IG Plus V 5.0 | 2011-12-20 | 2011-12-20 | 0 | 2011-12-20 | [14 empty] | 2012-03-06 | 2012-03-06 |  | Y
Central Hudson |  | Sungevity Inc | CH-09339 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8094 | Fishkill Plains | N |  | 8.5 | [13 empty] | NM | N | (1) KACO 5002xi & (1) KACO 3502xi | 2011-12-20 | 2011-12-21 | 1 | 2011-12-21 | [14 empty] | 2012-05-18 | 2012-05-23 |  | Y
Central Hudson |  | SolarCity | CH-05014 | Kingston | Kingston | Ulster | 12401 | G | 2094 | Hurley Ave | N |  | 6 | [13 empty] | NM | N | (1) SMA SB6000 | 2011-12-27 | 2012-01-03 | 4 | 2012-01-03 | [14 empty] | 2012-03-26 | 2012-03-26 |  | Y
Central Hudson |  | SunDog Solar | CH-09156 | Catskill | Westerlo | Albany | 12193 | G | 1091 | Westerlo | N |  | 4.73 | [13 empty] | NM | N | (1) Fronius USA IG Plus 5.0 | 2011-12-27 | 2012-01-03 | 4 | 2012-01-03 | [14 empty] | 2012-02-06 | 2012-02-09 |  | Y
Central Hudson |  | Mountaintop Greene Clean Energy | CH-02709 | Catskill | Lexington | Greene | 12452 | E | 2389 | Vinegar Hill | N |  | 2.58 | [13 empty] | NM | N | (12) Enphase M215 | 2011-12-28 | 2012-01-04 | 4 | 2012-01-04 | [14 empty] | 2012-05-21 | 2012-05-31 |  | W
Central Hudson |  | Solar Generation | CH-08280 | Kingston | Woodstock | Ulster | 12498 | G | 3014 | Woodstock | N | CH-08280 | 3.44 | [13 empty] | NM | N | (16) Enphase M215 | 2011-12-30 | 2012-01-05 | 3 | 2012-01-05 | [14 empty] | 2012-01-30 | 2012-02-03 |  | Y
Central Hudson |  | Titan Power Systems LLC | CH-09716 | Kingston | W Hurley | Ulster | 12491 | G | 2094 | Hurley Ave | Y | CH-09716 |  |  | 5.5 | [11 empty] | NM | N | Aurora PVI-6000-OUTD-US (1) | 2012-01-19 | 2012-01-19 | 0 | 2012-01-19 | [14 empty] | 2013-01-18 | 2013-01-21 |  | Y
Central Hudson |  | SolarCity | CH-05278 | Fishkill | Beacon | Dutchess | 12508 | G | 8017 | Forgebrook | N |  | 5 | [13 empty] | NM | N | SMA SB5000 (1) | 2012-01-03 | 2012-01-05 | 2 | 2012-01-05 | [14 empty] | 2012-03-26 | 2012-03-26 |  | Y
Central Hudson |  | SolarCity | CH-05879 | Poughkeepsie | Verbank | Dutchess | 12585 | G | 6057 | Todd Hill | N |  | 9.4 | [13 empty] | NM | N | Solaredge SE5000 | 2012-01-03 | 2012-01-05 | 2 | 2012-01-05 | [14 empty] | 2012-03-26 | 2012-04-09 |  | Y
Central Hudson |  | Lotus Energy Inc. | CH-03879 | Poughkeepsie | Barrytown | Dutchess | 12507 | G | 7056 | Rhinebeck | N |  | 3.01 | [13 empty] | NM | N | Enphase M215 (14) | 2012-01-05 | 2012-01-11 | 4 | 2012-01-11 | [14 empty] | 2012-03-16 | 2012-03-22 |  | Y
Central Hudson |  | Titan Power Systems LLC | CH-09713 | Catskill | Hunter | Greene | 12442 | G | 2385 | Lawrenceville | N |  |  |  | 12 | [11 empty] | NM | N | Aurora PVI-6000-OUTD-US (2) | 2012-01-19 | 2012-01-20 | 1 | 2012-01-20 | [14 empty] | 2012-03-08 | 2012-03-08 |  | Y
Central Hudson |  | Novel Approaches | CH-02783 | Kingston | Kingston | Ulster | 12401 | G | 1011 | Boulevard | N |  | 5 | [13 empty] | NM | N | SMA SB5000US (1) | 2012-01-10 | 2012-01-13 | 3 | 2012-01-13 | [14 empty] | 2012-01-31 | 2012-02-03 |  | Y
Central Hudson |  | Conscious Energy | CH-00793 | Kingston | Saugerties | Ulster | 12477 | G | 3003 | Saugerties | N |  | 10.32 | [13 empty] | NM | N | Enphase M215 (48) | 2012-01-30 | 2012-02-02 | 3 | 2012-02-02 | [14 empty] | 2012-02-03 | 2012-02-24 |  | Y
Central Hudson |  | Titan Power Systems LLC | CH-09714 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7053 | Rhinebeck | N |  |  |  | 1.2 | [11 empty] | NM | N | Windspire 1.2 kW (1) | 2012-01-12 | 2012-01-19 | 5 | 2012-01-19 | [14 empty] | 2012-03-30 | 2012-03-30 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00847 | Poughkeepsie | Clinton Corners | Dutchess | 12514 | G | 7011 | Hibernia | N | CH-00847 | 4.515 | [13 empty] | NM | N | Enphase M215 (21) | 2012-01-18 | 2012-01-23 | 3 | 2012-01-23 | [14 empty] | 2012-04-04 | 2012-04-10 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00851 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7062 | Milan | N |  | 6.45 | [13 empty] | NM | N | Enphase M215 (30) | 2012-01-23 | 2012-01-23 | 0 | 2012-01-23 | [14 empty] | 2012-04-04 | 2012-04-09 |  | Y
Central Hudson |  | SolarCity | CH-06745 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6096 | Manchester | N | CH-06745 | 6.58 | [13 empty] | NM | N | Fronius IG Plus 3.0 (1) & Fronius IG 4000 (1) | 2012-01-20 | 2012-01-23 | 1 | 2012-01-23 | [14 empty] | 2012-05-03 | 2012-05-07 |  | Y
Central Hudson |  | SolarCity | CH-07781 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8045 | Myers Corners | N |  | 6 | [13 empty] | NM | N | Power-one PVI-6000 (1) | 2012-01-20 | 2012-01-23 | 1 | 2012-01-23 | [14 empty] | 2012-03-23 | 2012-03-26 |  | Y
Central Hudson |  | Sungevity Inc | CH-09555 | Newburgh | Wallkill | Ulster | 12589 | G | 5042 | East Walden | N |  | 10.2 | [13 empty] | NM | N | Power-One PVI 4.2-OUTD-S-US (1) & Power-One PVI-6000-OUTD-US (1) | 2012-01-23 | 2012-01-23 | 0 | 2012-01-23 | [14 empty] | 2012-04-27 | 2012-05-07 |  | Y
Central Hudson |  | SolarCity | CH-05614 | Kingston | W Hurley | Ulster | 12491 | G | 2094 | Hurley Ave | N |  | 13 | [13 empty] | NM | N | SMA SB5000 (2) & SMA SB3000 (1) | 2012-01-24 | 2012-01-26 | 2 | 2012-01-26 | [14 empty] | 2012-05-01 | 2012-05-09 |  | Y
Central Hudson |  | Hudson Solar | CH-01416 | Poughkeepsie | Millerton | Dutchess | 12546 | G | 7081 | Millerton | N |  | 48 | [13 empty] | NM | N | Sunpower 12001F (4) | 2012-01-26 | 2012-01-30 | 2 | 2012-01-30 | [14 empty] | 2012-03-22 | 2012-03-23 |  | Y
Central Hudson |  | Hudson Solar | CH-01794 | Poughkeepsie | Millerton | Dutchess | 12546 | G | 7081 | Millerton | N |  | 44.4 | [13 empty] | NM | N | Sunpower 12001F (4) | 2012-01-26 | 2012-01-30 | 2 | 2012-01-30 | [14 empty] | 2012-03-22 | 2012-03-23 |  | Y
Central Hudson |  | Hudson Solar | CH-02453 | Newburgh | Highland | Ulster | 12528 | G | 5084 | Highland | N | CH-01214 | 11.4 | [13 empty] | NM | N | Sunpower 11401F (1) | 2012-01-27 | 2012-01-30 | 1 | 2012-01-30 | [14 empty] | 2012-02-15 | 2012-02-16 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00838 | Kingston | Ulster Pk | Ulster | 12487 | G | 1014 | Boulevard | N |  | 7.31 | [13 empty] | NM | N | Enphase M215 (34) | 2012-02-03 | 2012-02-06 | 1 | 2012-02-06 | [14 empty] | 2012-04-04 | 2012-04-10 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00862 | Poughkeepsie | Lagrangevl | Dutchess | 12540 | G | 6057 | Todd Hill | N |  | 6.665 | [13 empty] | NM | N | Enphase M215 (31) | 2012-02-03 | 2012-02-06 | 1 | 2012-02-06 | [14 empty] | 2012-04-04 | 2012-04-10 |  | Y
Central Hudson |  | Solar Generation | CH-08079 | Kingston | Kingston | Ulster | 12401 | G | 121 | Converse St | N |  | 30.1 | [13 empty] | NM | N | Enphase M215 (205) | 2012-02-27 | 2012-02-27 | 0 | 2012-02-27 | [14 empty] | 2012-05-17 | 2012-05-21 |  | Y
Central Hudson |  | Sungevity Inc | CH-09574 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8095 | Fishkill Plains | N |  | 7.6 | [13 empty] | NM | N | Kaco 3502XI (1) & Kaco 5002XI (1) | 2012-01-30 | 2012-02-03 | 4 | 2012-02-03 | [14 empty] | 2012-04-25 | 2012-05-24 |  | Y
Central Hudson |  | SolarCity | CH-07038 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 8.58 | [13 empty] | NM | N | Power-one PVI-5000(1) & Power-one PVI-3.6(1) | 2012-02-01 | 2012-02-07 | 4 | 2012-02-07 | [14 empty] | 2012-09-17 | 2012-09-24 |  | Y
Central Hudson |  | Malcarne Contracting | CH-03909 | Kingston | Saugerties | Ulster | 12477 | G | 3001 | Saugerties | N |  | 9 | [13 empty] | NM | N | SMA 3000 & SMA 6000 | 2012-02-06 | 2012-02-07 | 1 | 2012-02-07 | [14 empty] | 2012-04-09 | 2012-04-09 |  | Y
Central Hudson |  | Green Energy Systems | CH-01160 | Catskill | Cairo | Greene | 12413 | G | 2041 | South Cairo | N |  | 5 | [13 empty] | NM | N | SMA 2500 (2) | 2012-02-09 | 2012-02-09 | 0 | 2012-02-09 | [14 empty] | 2012-07-16 | 2012-07-25 |  | Y
Central Hudson |  | Hudson Valley Wind Energy, LLC | CH-02547 | Catskill | Cornwallvl | Greene | 12418 | G | 2043 | South Cairo | N |  |  |  | 10 | [11 empty] | NM | N | Diversified Technology Powersynch II AMFA-27 | 2012-02-16 | 2012-02-16 | 0 | 2012-02-16 | [14 empty] | 2012-03-02 | 2012-03-06 |  | Y
Central Hudson |  | RGS Energy | CH-03058 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6042 | Spackenkill | N |  | 3.75 | [13 empty] | NM | N | Solectria PVI-4000-240 | 2012-02-16 | 2012-02-16 | 0 | 2012-02-16 | [14 empty] | 2012-06-04 | 2012-06-11 |  | Y
Central Hudson |  | SolarCity | CH-07319 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7051 | Rhinebeck | N |  | 7 | [13 empty] | NM | N | SMA 7000 | 2012-02-14 | 2012-02-15 | 1 | 2012-02-15 | [14 empty] | 2012-06-04 | 2012-06-11 |  | Y
Central Hudson |  | Sungevity Inc | CH-09209 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7013 | Hibernia | N |  | 10 | [13 empty] | NM | N | Kaco 5002xi (2) | 2012-02-15 | 2012-02-16 | 1 | 2012-02-16 | [14 empty] | 2012-07-03 | 2012-07-06 |  | Y
Central Hudson |  | SolarCity | CH-04939 | Kingston | Kerhonkson | Ulster | 12446 | G | 3082 | Kerhonkson | N |  | 7 | [13 empty] | NM | N | SMA Sunny Boy 7000 (1) | 2012-02-16 | 2012-02-17 | 1 | 2012-02-17 | [14 empty] | 2012-06-06 | 2012-06-11 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03605 | Kingston | Accord | Ulster | 12404 | G | 3081 | Kerhonkson | N |  | 12.2 | [13 empty] | NM | N | Power-One Aurora PVI 3000 (1), Power-One Aurora PVI 4200 (1), & Power-One Aurora PVI 5000 (1) | 2012-02-17 | 2012-02-24 | 4 | 2012-02-24 | [14 empty] | 2012-09-04 | 2012-09-07 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03618 | Newburgh | New Windsor | Orange | 12553 | G | 4047 | Union Ave | N |  | 12.6 | [13 empty] | NM | N | Power-One Aurora PVI-4.2-OUTD-US (3) | 2012-02-17 | 2012-02-24 | 4 | 2012-02-24 | [14 empty] | 2012-07-27 | 2012-08-02 |  | Y
Central Hudson |  | Direct Energy Solar | CH-01019 | Newburgh | New Paltz | Ulster | 12561 | G | 5023 | Ohioville | N |  | 6.235 | [13 empty] | NM | N | Enphase M215 (29) | 2012-02-27 | 2012-02-27 | 0 | 2012-02-27 | [14 empty] | 2012-04-09 | 2012-04-16 |  | Y
Central Hudson |  | Sungevity Inc | CH-09324 | Poughkeepsie | Lagrangevl | Dutchess | 12540 | G | 6053 | Todd Hill | N |  | 4.94 | [13 empty] | NM | N | POWER-ONE PVI-5000-OUTD-US | 2012-02-22 | 2012-02-24 | 2 | 2012-02-24 | [14 empty] | 2012-06-07 | 2012-06-13 |  | Y
Central Hudson |  | Sungevity Inc | CH-09404 | Kingston | High Fls | Ulster | 12440 | G | 3022 | High Falls | N |  | 1.5 | [13 empty] | NM | N | Kaco 1502xi (1) | 2012-02-22 | 2012-02-24 | 2 | 2012-02-24 | [14 empty] | 2012-06-26 | 2012-06-29 |  | Y
Central Hudson |  | Solar Generation | CH-08117 | Kingston | Kingston | Ulster | 12401 | G | 121 | Converse St | N |  | 13.975 | [13 empty] | NM | N | Enphase M215 (65) | 2012-02-23 | 2012-02-27 | 2 | 2012-02-27 | [14 empty] | 2012-05-17 | 2012-05-21 |  | Y
Central Hudson |  | Kirchhoff Green Energy LLC | CH-03548 | Fishkill | Poughkeepsie | Dutchess | 12601 | G | 8024 | Knapps Corners | N |  | 45.6 | [13 empty] | NM | N | Fronius 11.4 Delta (4) | 2012-02-27 | 2012-02-27 | 0 | 2012-02-27 | [14 empty] | 2012-04-03 | 2012-04-04 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00870 | Newburgh | Cornwall-Hdsn | Orange | 12520 | G | 4043 | Union Ave | N |  | 4.945 | [13 empty] | NM | N | Enphase M215 (23) | 2012-02-27 | 2012-02-28 | 1 | 2012-02-28 | [14 empty] | 2012-07-27 | 2012-08-02 |  | Y
Central Hudson |  | Hudson Solar | CH-01356 | Newburgh | Milton | Ulster | 12547 | G | 5083 | Highland | N |  | 30 | [13 empty] | NM | N | XANTREX GT 30 (1) | 2012-03-01 | 2012-03-01 | 0 | 2012-03-01 | [14 empty] | 2012-04-04 | 2012-04-05 |  | Y
Central Hudson |  | Hudson Solar | CH-01426 | Newburgh | New Paltz | Ulster | 12561 | G | 5011 | Modena | N |  | 7 | [13 empty] | NM | N | SMA 3000 (1) & SMA 4000 (1) | 2012-03-01 | 2012-03-01 | 0 | 2012-03-01 | [14 empty] | 2012-04-03 | 2012-04-04 |  | Y
Central Hudson |  | Hudson Solar | CH-02109 | Poughkeepsie | Wappingrs Fls | Dutchess | 12590 | G | 6052 | Todd Hill | N |  | 4.6 | [13 empty] | NM | N | Sunpower 5000 (1) | 2012-02-27 | 2012-03-01 | 3 | 2012-03-01 | [14 empty] | 2012-04-03 | 2012-04-04 |  | Y
Central Hudson |  | Hudson Solar | CH-02135 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7054 | Rhinebeck | N |  | 9 | [13 empty] | NM | N | SMA 5000 (1) & SMA 4000 (1) | 2012-02-27 | 2012-02-29 | 2 | 2012-02-29 | [14 empty] | 2012-03-14 | 2012-03-26 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Hudson Solar | CH-02420 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7052 | Rhinebeck | N |  | 9 | [13 empty] | NM | N | Sunpower 5000 (1) & Sunpower 4000 (1) | 2012-02-27 | 2012-03-01 | 3 | 2012-03-01 | [14 empty] | 2012-04-09 | 2012-04-11 |  | Y
Central Hudson |  | SolarCity | CH-06802 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8091 | Fishkill Plains | N |  | 6.58 | [13 empty] | NM | N | Fronius IG4000 (2) | 2012-02-28 | 2012-03-02 | 3 | 2012-03-02 | [14 empty] | 2012-06-18 | 2012-06-25 |  | Y
Central Hudson |  | SolarCity | CH-07052 | Newburgh | Plattekill | Ulster | 12568 | G | 5013 | Modena | N |  | 7.2 | [13 empty] | NM | N | Power-One 3.6 (2) | 2012-02-28 | 2012-03-05 | 4 | 2012-03-05 | [14 empty] | 2012-06-15 | 2012-06-22 |  | Y
Central Hudson |  | SunDog Solar | CH-09158 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7062 | Milan | N |  | 6.02 | [13 empty] | NM | N | Enphase M215 (28) | 2012-03-08 | 2012-03-08 | 0 | 2012-03-08 | [14 empty] | 2012-05-23 | 2012-05-30 |  | Y
Central Hudson |  | UniAssociates | CH-09729 | Catskill | Catskill |  | 12414 | G | 2001 | North Catskill | TBD |  | 1.9 |  | 3.8 | [11 empty] | NM | N | SkyStrem3.7 ISSL10120 | 2012-03-02 | 2012-03-02 | 0 | 2012-03-02 | [15 empty] | 2012-03-02 |  | W |  | Customer already had net meter prior to application. System installed at previous account 1248-0030-01. New customer 1248-0030-02 effective 3/2/12. Mailed contract appendix A. Received signed contract 4/20/12.
Central Hudson |  | Direct Energy Solar | CH-00994 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6043 | Spackenkill | N |  | 11.8 | [13 empty] | NM | N | Enphase M215 (52) | 2012-03-05 | 2012-03-07 | 2 | 2012-03-07 | [14 empty] | 2012-06-06 | 2012-06-22 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00995 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 6068 | Inwood Ave | N |  | 2.795 | [13 empty] | NM | N | Enphase M215 (13) | 2012-03-05 | 2012-03-07 | 2 | 2012-03-07 | [14 empty] | 2012-06-07 | 2012-06-13 |  | Y
Central Hudson |  | SolarCity | CH-05356 | Newburgh | New Paltz | Ulster | 12561 | G | 5024 | Ohioville | N |  | 10 | [13 empty] | NM | N | SMA SunnyBoy 5000 (2) | 2012-03-06 | 2012-03-07 | 1 | 2012-03-07 | [14 empty] | 2012-09-05 | 2012-09-07 |  | Y
Central Hudson |  | Self | CH-08863 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6046 | Spackenkill | N |  | 4.515 | [13 empty] | NM | N | Enphase M215 (21) | 2012-03-27 | 2012-03-27 | 0 | 2012-03-27 | [14 empty] | 2013-06-06 | 2013-06-12 |  | Y
Central Hudson |  | Sungevity Inc | CH-09494 | Newburgh | Wallkill | Ulster | 12589 | G | 5043 | East Walden | N |  | 7 | [13 empty] | NM | N | SMA SB7000US | 2012-03-06 | 2012-03-07 | 1 | 2012-03-07 | [14 empty] | 2012-08-03 | 2012-08-09 |  | Y
Central Hudson |  | Rural Generation and Wind | CH-08847 | Catskill | Earlton |  | 12058 | G | 2006 | North Catskill | TBD |  | 11 |  | 22 | [11 empty] | NM | N | Gaia (model 133.13, version 11.34) | 2012-04-09 | 2012-04-09 | 0 | 2012-04-09 | [15 empty] | 2012-04-17 |  | W |  | Customer had net meter. 3/9/12 Needs non-inverter based verification test procedure, Manufacturer's commissioning test procedure, controller settings and specs. 3/15/12 Letter of Incomplete issued. 4/9/12 Received adequate verification test procedure.
Central Hudson |  | CNR Energy Solutions, LLC | CH-00774 | Newburgh | Wallkill | Ulster | 12589 | G | 5043 | East Walden | N |  | 6.88 | [13 empty] | NM | N | Enphase M215 (32) | 2012-03-20 | 2012-03-20 | 0 | 2012-03-20 | [14 empty] | 2012-03-28 | 2012-03-30 |  | Y
Central Hudson |  | Hudson Valley Wind Energy, LLC | CH-02553 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7061 | Milan | N |  |  |  | 10 | [11 empty] | NM | N | Diversified Technology Powersynch II AMFA-27 | 2012-03-16 | 2012-03-20 | 2 | 2012-03-20 | [14 empty] | 2012-04-13 | 2012-04-25 |  | Y
Central Hudson |  | Endless Mtn Solar Services | CH-01117 | Fishkill | Wappingrs Falls |  | 12590 | G | 8092 | Fishkill Plains | TBD |  | 4.3 | [13 empty] | NM | N | Enphase M215 (20) | 2012-03-22 | 2012-03-22 | 0 | 2012-03-22 | [17 empty] | W |  | 3/19/12 Application is missing signed contract, detailed 3-line diagram, verification test procedure & adequate letter of authorization. 3/22/12 Received completed application. 10/7/14 Project abandoned, customer advised changing contractor.
Central Hudson |  | Hudson Solar | CH-02431 | Catskill | Haines Fls | Greene | 12436 | G | 2385 | Lawrenceville | N | CH-01598 | 6 | [13 empty] | NM | N | SMA 6000 | 2012-03-21 | 2012-03-23 | 2 | 2012-03-23 | [14 empty] | 2012-04-17 | 2012-04-23 |  | Y
Central Hudson |  | Direct Energy Solar | CH-01041 | Poughkeepsie | Lagrangevl | Dutchess | 12540 | G | 6055 | Todd Hill | N |  | 9.89 | [13 empty] | NM | N | Enphase M215 (46) | 2012-03-23 | 2012-03-23 | 0 | 2012-03-23 | [14 empty] | 2012-07-03 | 2012-07-05 |  | Y
Central Hudson |  | Hudson Solar | CH-01326 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7062 | Milan | N |  | 20 | [13 empty] | NM | N | Schneider Conext 5000 (4) | 2012-03-26 | 2012-03-28 | 2 | 2012-03-28 | [14 empty] | 2012-05-25 | 2012-05-30 |  | Y
Central Hudson |  | Murphy Solar Power | CH-02738 | Catskill | Catskill |  | 12414 | G | 2006 | North Catskill | N | CH-02738 | 3 | [13 empty] | NM | N | SMA SunnyBoy 3000 | 2012-04-10 | 2012-04-10 | 0 | 2012-04-10 | [14 empty] | 2012-04-23 | 2012-05-02 |  | W
Central Hudson |  | SolarCity | CH-06431 | Newburgh | New Windsor | Orange | 12553 | G | 4053 | Union Ave | N |  | 44.4 | [13 empty] | NM | N | Fronius CL 44.4 | 2012-03-30 | 2012-03-30 | 0 | 2012-03-30 | [14 empty] | 2012-06-19 | 2012-06-29 |  | Y
Central Hudson |  | SolarCity | CH-05773 | Kingston | Lk Katrine | Ulster | 12449 | G | 2016 | Lincoln Park | N |  | 4.2 | [13 empty] | NM | N | Power-One Aurora PVI-4.2 (1) | 2012-03-28 | 2012-03-29 | 1 | 2012-03-29 | [14 empty] | 2012-06-04 | 2012-06-08 |  | Y
Central Hudson |  | SolarCity | CH-07480 | Newburgh | New Windsor | Orange | 12553 | G | 4094 | Bethlehem Rd | N |  | 6.345 | [13 empty] | NM | N | Power-One Aurora PVI-3.0 (1) & Power-One Aurora PVI-3.8 (1) | 2012-03-28 | 2012-03-29 | 1 | 2012-03-29 | [14 empty] | 2012-08-23 | 2012-08-28 |  | Y
Central Hudson |  | Sungevity Inc | CH-09188 | Newburgh | Wallkill | Ulster | 12589 | G | 5043 | East Walden | N |  | 3.6 | [13 empty] | NM | N | Power One PVI-3.6-OUTD (1) | 2012-04-05 | 2012-04-05 | 0 | 2012-04-05 | [14 empty] | 2012-07-11 | 2012-07-17 |  | Y
Central Hudson |  | SolarCity | CH-05301 | Newburgh | Newburgh | Orange | 12550 | G | 4011 | West Balmville | N |  | 6 | [13 empty] | NM | N | Power-One PVI-6000 (1) | 2012-04-04 | 2012-04-04 | 0 | 2012-04-04 | [14 empty] | 2012-07-06 | 2012-07-09 |  | Y
Central Hudson |  | Appolo-Hudson Valley | CH-00720 | Fishkill | Stormvl | Dutchess | 12582 | G | 8093 | Fishkill Plains | N |  | 0.7 | [13 empty] | NM | N | Andalay ST175W panels integrated with Enphase M190 micro inverters (4) | 2013-02-08 | 2013-02-08 | 0 | 2013-02-08 | [14 empty] | 2013-02-09 | 2013-02-20 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Burke Electric and Solar | CH-00766 | Fishkill | Beacon | Dutchess | 12508 | G | 8085 | Tioronda | N |  | 3.69 | [13 empty] | NM | N | SMA Sunny Boy US3800 | 2012-04-16 | 2012-04-17 | 1 | 2012-04-17 | [14 empty] | 2012-04-20 | 2012-04-26 |  | Y
Central Hudson |  | SolarCity | CH-04940 | Kingston | Lk Katrine | Ulster | 12449 | G | 2015 | Lincoln Park | N |  | 15 | [13 empty] | RNM | N | Fronius IG Plus V 7.5 (2) | 2012-04-16 | 2012-04-16 | 0 | 2012-04-16 | [8 empty] | 350 | 350 |  |  |  |  | 2012-07-11 | 2012-07-16 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03563 | Newburgh | New Windsor | Orange | 12553 | G | 4047 | Union Ave | N |  | 17.4 | [13 empty] | NM | N | Fronius IG Plus 11.4 (1) & 6.0 (1) | 2012-04-30 | 2012-05-04 | 4 | 2012-05-04 | [14 empty] | 2012-08-29 | 2012-09-06 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03564 | Newburgh | New Windsor | Orange | 12553 | G | 4047 | Union Ave | N |  | 17.4 | [13 empty] | NM | N | Fronius IG Plus 11.4 (1) & 6.0 (1) | 2012-04-30 | 2012-05-04 | 4 | 2012-05-04 | [14 empty] | 2012-08-29 | 2012-09-06 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03571 | Newburgh | New Windsor | Orange | 12553 | G | 4047 | Union Ave | N |  | 28.8 | [13 empty] | NM | N | Fronius IG Plus 11.4 (2) & Fronius IG Plus 6.0 (1) | 2012-05-03 | 2012-05-04 | 1 | 2012-05-04 | [14 empty] | 2012-09-24 | 2012-10-01 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03574 | Newburgh | New Windsor | Orange | 12553 | G | 4047 | Union Ave | N |  | 17.4 | [13 empty] | NM | N | Fronius IG Plus 11.4 (1) & Fronius IG Plus 6.0 (1) | 2012-04-30 | 2012-05-04 | 4 | 2012-05-04 | [14 empty] | 2012-09-24 | 2012-10-01 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03579 | Newburgh | New Windsor | Orange | 12553 | G | 4047 | Union Ave | N |  | 22.8 | [13 empty] | NM | N | Fronius IG Plus 11.4 (2) | 2012-04-30 | 2012-05-04 | 4 | 2012-05-04 | [14 empty] | 2012-09-24 | 2012-10-01 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03598 | Newburgh | New Windsor | Orange | 12553 | G | 4047 | Union Ave | N |  | 17.4 | [13 empty] | NM | N | Fronius IG Plus 11.4 (1) & 6.0 (1) | 2012-04-30 | 2012-05-04 | 4 | 2012-05-04 | [14 empty] | 2012-09-24 | 2012-10-01 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03604 | Newburgh | New Windsor | Orange | 12553 | G | 4047 | Union Ave | N |  | 17.4 | [13 empty] | NM | N | Fronius IG Plus 11.4 (1) & 6.0 (1) | 2012-04-30 | 2012-05-04 | 4 | 2012-05-04 | [14 empty] | 2012-08-29 | 2012-09-06 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03610 | Newburgh | New Windsor | Orange | 12553 | G | 4047 | Union Ave | N |  | 22.8 | [13 empty] | NM | N | Fronius IG Plus 11.4 (2) | 2012-04-30 | 2012-05-04 | 4 | 2012-05-04 | [14 empty] | 2012-09-24 | 2012-10-01 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03613 | Newburgh | New Windsor | Orange | 12553 | G | 4047 | Union Ave | N |  | 22.8 | [13 empty] | NM | N | Fronius IG Plus 11.4 (2) | 2012-04-30 | 2012-05-04 | 4 | 2012-05-04 | [14 empty] | 2012-09-24 | 2012-10-01 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03652 | Newburgh | New Windsor | Orange | 12553 | G | 4047 | Union Ave | N |  | 48.2 | [13 empty] | RNM | N | Fronius IG Plus 11.4 (3), 6.0 (1), 5.0 (1) & 3.0 (1) | 2012-05-03 | 2012-05-04 | 1 | 2012-05-04 | [14 empty] | 2012-08-29 | 2012-09-06 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03729 | Newburgh | New Windsor | Orange | 12553 | G | 4047 | Union Ave | N |  | 17.4 | [13 empty] | NM | N | Fronius IG Plus 11.4 (1) & 6.0 (1) | 2012-04-30 | 2012-05-04 | 4 | 2012-05-04 | [14 empty] | 2012-09-24 | 2012-10-01 |  | Y
Central Hudson |  | SolarCity | CH-07733 | Kingston | Lk Katrine | Ulster | 12449 | G | 2011 | Lincoln Park | N |  | 3 | [13 empty] | NM | N | SolarEdge SE3000US | 2012-04-12 | 2012-04-17 | 3 | 2012-04-17 | [14 empty] | 2012-09-13 | 2012-09-17 |  | Y
Central Hudson |  | Sungevity Inc | CH-09280 | Kingston | Rosendale | Ulster | 12472 | G | 3022 | High Falls | N |  | 2.47 | [13 empty] | NM | N | Power One PVI-3.0-OUTD-S-US (1) | 2012-04-12 | 2012-04-17 | 3 | 2012-04-17 | [14 empty] | 2012-08-03 | 2012-08-10 |  | Y
Central Hudson |  | Sungevity Inc | CH-09493 | Newburgh | Wallkill | Ulster | 12589 | G | 5043 | East Walden | N |  | 7 | [13 empty] | NM | N | SMA SB7000US (1) | 2012-04-12 | 2012-04-17 | 3 | 2012-04-17 | [14 empty] | 2012-08-30 | 2012-09-07 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00835 | Newburgh | W Park | Ulster | 12493 | G | 5084 | Highland | N |  | 8.17 | [13 empty] | NM | N | Enphase M215 (38) | 2012-04-13 | 2012-04-20 | 5 | 2012-04-20 | [14 empty] | 2012-07-19 | 2012-07-25 |  | Y
Central Hudson |  | Sea Bright Solar LLC | CH-08858 | Newburgh | Rock Tvrn |  | 12575 | G | 4097 | Bethlehem Rd | TBD |  | 6.45 | [13 empty] | NM | N | Enphase M215 (30) | 2012-05-03 | 2012-05-04 | 1 | 2012-05-04 | [17 empty] | W |  | 4/13/12 Application missing signed contract, letter of authorization and verification test procedure. 4/20/12 Issued Letter of Incomplete. 5/3/12 Received completed application.
Central Hudson |  | Sungevity Inc | CH-09233 | Newburgh | Gardiner | Ulster | 12525 | G | 5011 | Modena | N |  | 3.42 | [13 empty] | NM | N | KACO BluePlanet 3502XI (1) | 2012-04-13 | 2012-04-20 | 5 | 2012-04-20 | [14 empty] | 2012-07-17 | 2012-07-24 |  | Y
Central Hudson |  | Sungevity Inc | CH-09600 | Newburgh | New Paltz | Ulster | 12561 | G | 5011 | Modena | N |  | 5 | [13 empty] | NM | N | Power One PVI-5000-OUTD-US (1) | 2012-04-13 | 2012-04-19 | 4 | 2012-04-19 | [14 empty] | 2012-06-22 | 2012-06-29 |  | Y
Central Hudson |  | Sungevity Inc | CH-09604 | Newburgh | New Paltz | Ulster | 12561 | G | 5011 | Modena | N |  | 3.5 | [13 empty] | NM | N | Kaco Blueplanet 3502xi(1) | 2012-04-13 | 2012-04-18 | 3 | 2012-04-18 | [14 empty] | 2012-06-29 | 2012-07-03 |  | Y
Central Hudson |  | Murphy Solar Power | CH-02713 | Newburgh | Highland | Ulster | 12528 | G | 5083 | Highland | N |  | 7.8 | [13 empty] | NM | N | SMA SunnyBoy 8000 (1) | 2012-04-16 | 2012-04-23 | 5 | 2012-04-23 | [14 empty] | 2012-05-07 | 2012-05-30 |  | Y
Central Hudson |  | Sungevity Inc | CH-09211 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8091 | Fishkill Plains | N |  | 7 | [13 empty] | NM | N | SMA America SB7000us (1) | 2012-04-16 | 2012-04-23 | 5 | 2012-04-23 | [14 empty] | 2012-09-26 | 2012-10-02 |  | Y
Central Hudson |  | Hudson Solar | CH-02262 | Poughkeepsie | Salt Pt | Dutchess | 12578 | G | 7011 | Hibernia | N |  | 7.68 | [13 empty] | NM | N | SMA 3000us (1) & SMA 5000us (1) | 2012-04-19 | 2012-04-25 | 4 | 2012-04-25 | [14 empty] | 2012-06-06 | 2012-06-11 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03824 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7056 | Rhinebeck | N | CH-02101 | 48 | [13 empty] | NM | N | Power One Aurora PVI6000us (8) | 2012-04-30 | 2012-05-18 | 14 | 2012-05-18 | [14 empty] | 2012-06-26 | 2012-07-02 |  | Y
Central Hudson |  | Sungevity Inc | CH-09495 | Newburgh | Wallkill | Ulster | 12589 | G | 5033 | Galeville | N |  | 6 | [13 empty] | NM | N | Power One PVI-6000-OUTD (1) | 2012-04-20 | 2012-04-27 | 5 | 2012-04-27 | [14 empty] | 2012-06-29 | 2012-07-05 |  | Y
Central Hudson |  | Sungevity Inc | CH-09497 | Newburgh | Wallkill | Ulster | 12589 | G | 5041 | East Walden | N |  | 9.6 | [13 empty] | NM | N | Power One PVI-6000 (1) & Power One PVI 3.6 (1) | 2012-04-26 | 2012-04-27 | 1 | 2012-04-27 | [14 empty] | 2013-04-23 | 2013-04-25 |  | Y
Central Hudson |  | Sungevity Inc | CH-09593 | Newburgh | Gardiner | Ulster | 12525 | G | 5011 | Modena | N |  | 2.8 | [13 empty] | NM | N | Power One PVI 3.0 | 2012-04-20 | 2012-04-26 | 4 | 2012-04-26 | [14 empty] | 2012-07-12 | 2012-07-17 |  | Y
Central Hudson |  | Sungevity Inc | CH-09607 | Newburgh | Gardiner | Ulster | 12525 | G | 5011 | Modena | N |  | 7.2 | [13 empty] | NM | N | POWER ONE PVI-4.2-OUTD (1) & POWER ONE PVI-3.0_OUTD (1) | 2012-04-20 | 2012-04-27 | 5 | 2012-04-27 | [14 empty] | 2012-09-12 | 2012-09-25 |  | Y
Central Hudson |  | Sungevity Inc | CH-09633 | Newburgh | Gardiner |  | 12525 | G | 5011 | Modena | TBD |  | 7.2 | [13 empty] | NM | N | POWER ONE PVI-4.2-OUTD (1) & POWER ONE PVI-3.0_OUTD (1) | 2012-04-20 | 2012-04-27 | 5 | 2012-04-27 | [17 empty] | W
Central Hudson |  | Lighthouse Solar | CH-03575 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 6074 | East Park | N |  | 12 | [13 empty] | NM | N | Sunny Boy SB6000US (2) | 2012-04-23 | 2012-04-30 | 5 | 2012-04-30 | [14 empty] | 2012-10-05 | 2012-10-11 |  | Y
Central Hudson |  | Burke Electric and Solar | CH-00763 | Newburgh | Newburgh | Orange | 12550 | G | 5041 | East Walden | N |  | 3.78 | [13 empty] | NM | N | Fronius IG4000 (1) | 2012-04-30 | 2012-04-30 | 0 | 2012-04-30 | [14 empty] | 2013-06-26 | 2013-07-03 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00979 | Kingston | Kerhonkson | Ulster | 12446 | G | 3081 | Kerhonkson | N |  | 8.6 | [13 empty] | NM | N | Enphase M215 (40) | 2012-04-23 | 2012-04-30 | 5 | 2012-04-30 | [8 empty] | 350 | 350 |  | 2012-05-11 | 2012-05-11 | 2012-05-18 | 2012-06-22 | 2012-06-29 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03827 | Newburgh | New Paltz | Ulster | 12561 | G | 5025 | Ohioville | Y | CH-00621 | 5 | [13 empty] | NM | N | Power One Aurora PVI 5000 (1) | 2012-04-25 | 2012-05-02 | 5 | 2012-05-02 | [14 empty] | 2012-09-24 | 2012-10-01 |  | Y
Central Hudson |  | Sol Providers | CH-08925 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 6051 | Todd Hill | N | CH-08925 | 3.44 | [13 empty] | NM | N | Enphase M215 (16) | 2012-05-02 | 2012-05-02 | 0 | 2012-05-02 | [14 empty] | 2012-07-10 | 2012-07-13 |  | Y
Central Hudson |  | Sungevity Inc | CH-09548 | Newburgh | New Windsor | Orange | 12553 | G | 4044 | Union Ave | N |  | 5.89 | [13 empty] | NM | N | Power One PVI 3.0 OUTD (2) | 2012-05-02 | 2012-05-02 | 0 | 2012-05-02 | [14 empty] | 2012-10-12 | 2012-10-12 |  | Y
Central Hudson |  | Sungevity Inc | CH-09295 | Kingston | Ellenvl | Ulster | 12428 | G | 3078 | Greenfield Rd | N |  | 3.6 | [13 empty] | NM | N | Power One PVI 3.6 OUTD (1) | 2012-05-03 | 2012-05-03 | 0 | 2012-05-03 | [14 empty] | 2012-10-18 | 2012-10-24 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00834 | Fishkill | Fishkill | Dutchess | 12524 | G | 8092 | Fishkill Plains | N | CH-00834 | 9.03 | [13 empty] | NM | N | M-215 enphase Energy (42) | 2012-04-30 | 2012-04-30 | 0 | 2012-04-30 | [14 empty] | 2012-08-31 | 2012-09-10 |  | Y
Central Hudson |  | SolarCity | CH-05228 | Newburgh | Wallkill | Ulster | 12589 | G | 5042 | East Walden | N |  | 7.68 | [13 empty] | NM | N | SMA Sunny Boy 5000 (1) & SMA Sunny Boy 3000 (1) | 2012-05-01 | 2012-05-08 | 5 | 2012-05-08 | [14 empty] | 2012-09-05 | 2012-09-12 |  | Y
Central Hudson |  | SolarCity | CH-05265 | Newburgh | Highland | Ulster | 12528 | G | 5083 | Highland | N |  | 5 | [13 empty] | NM | N | Sunny Boy 5000 | 2012-05-01 | 2012-05-07 | 4 | 2012-05-07 | [14 empty] | 2012-08-31 | 2012-09-10 |  | Y
Central Hudson |  | SolarCity | CH-06788 | Newburgh | Highland | Ulster | 12528 | G | 5084 | Highland | N |  | 7.05 | [13 empty] | NM | N | Power One PVI 3.6 (2) | 2012-05-01 | 2012-05-07 | 4 | 2012-05-07 | [14 empty] | 2012-06-15 | 2012-06-22 |  | Y
Central Hudson |  | SolarCity | CH-07757 | Kingston | Lk Katrine | Ulster | 12449 | G | 2016 | Lincoln Park | N |  | 6 | [13 empty] | NM | N | Power One 6000 | 2012-05-01 | 2012-05-07 | 4 | 2012-05-07 | [14 empty] | 2012-08-23 | 2012-09-10 |  | Y
Central Hudson |  | Hudson Solar | CH-01938 | Newburgh | New Paltz | Ulster | 12561 | G | 5031 | Galeville | N |  | 7 | [13 empty] | NM | N | Sunpower 7000M | 2012-05-02 | 2012-05-08 | 4 | 2012-05-08 | [14 empty] | 2012-06-20 | 2012-06-27 |  | W
Central Hudson |  | Malcarne Contracting | CH-03897 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6066 | Inwood Ave | N |  | 7.5 | [13 empty] | NM | N | Fronius IG Plus 7.5 (1) | 2012-05-11 | 2012-05-11 | 0 | 2012-05-11 | [14 empty] | 2012-07-13 | 2012-07-18 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00976 | Newburgh | Montgomery | Orange | 12549 | G | 5072 | Montgomery | N |  | 7.955 | [13 empty] | NM | N | Enphase M215 (37) | 2012-05-07 | 2012-05-08 | 1 | 2012-05-08 | [14 empty] | 2012-07-26 | 2012-07-27 |  | Y
Central Hudson |  | SolarCity | CH-06312 | Newburgh | Newburgh | Orange | 12550 | G | 5004 | Marlboro | N |  | 7.095 | [13 empty] | NM | N | Fronius IG Plus 7.5 (1) | 2012-05-07 | 2012-05-08 | 1 | 2012-05-08 | [14 empty] | 2012-11-05 | 2012-11-05 |  | Y
Central Hudson |  | SolarCity | CH-06320 | Newburgh | Marlboro | Ulster | 12542 | G | 5004 | Marlboro | N | CH-06320 | 7.2 | [13 empty] | NM | N | Power One Aurora PVI 3.6 (2) | 2012-05-07 | 2012-05-09 | 2 | 2012-05-09 | [14 empty] | 2012-07-03 | 2012-07-06 |  | Y
Central Hudson |  | SolarCity | CH-06683 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6073 | East Park | N |  | 7 | [13 empty] | NM | N | SMA SunnyBoy 7000 (1) | 2012-05-07 | 2012-05-08 | 1 | 2012-05-08 | [14 empty] | 2012-07-06 | 2012-07-09 |  | Y
Central Hudson |  | SolarCity | CH-06722 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6051 | Todd Hill | N |  | 5 | [13 empty] | NM | N | SMA Sunny Boy 5000 (1) | 2012-05-07 | 2012-05-09 | 2 | 2012-05-09 | [14 empty] | 2012-07-06 | 2012-07-09 |  | Y
Central Hudson |  | SolarCity | CH-05065 | Newburgh | Newburgh | Orange | 12550 | G | 4023 | Coldenham | N |  | 5 | [13 empty] | NM | N | SMA Sunny Boy 5000 | 2012-05-08 | 2012-05-11 | 3 | 2012-05-11 | [14 empty] | 2012-09-05 | 2012-09-11 |  | Y
Central Hudson |  | SolarCity | CH-05368 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 7.5 | [13 empty] | NM | N | Fronius IG Plus V 7.5 (1) | 2012-05-11 | 2012-05-11 | 0 | 2012-05-11 | [14 empty] | 2012-08-29 | 2012-09-05 |  | Y
Central Hudson |  | SolarCity | CH-05423 | Newburgh | New Paltz | Ulster | 12561 | G | 5011 | Modena | N |  | 7.6 | [13 empty] | NM | N | Power One Aurora PVI 3.8 (2) | 2012-05-08 | 2012-05-11 | 3 | 2012-05-11 | [14 empty] | 2012-08-29 | 2012-09-05 |  | Y
Central Hudson |  | SolarCity | CH-05701 | Kingston | Kingston |  | 12401 | G | 1011 | Boulevard | TBD |  | 6 | [13 empty] | NM | N | Power One Aurora PVI 6000 | 2012-05-08 | 2012-05-14 | 4 | 2012-05-14 | [14 empty] | 2012-07-23 | 2012-07-30 |  | W
Central Hudson |  | SolarCity | CH-06005 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8091 | Fishkill Plains | N |  | 6 | [13 empty] | NM | N | Power One Aurora PVI 6000 (1) | 2012-05-11 | 2012-05-15 | 2 | 2012-05-15 | [14 empty] | 2012-10-03 | 2012-10-10 |  | Y
Central Hudson |  | SolarCity | CH-06936 | Fishkill | Beacon | Dutchess | 12508 | G | 8085 | Tioronda | N |  | 2.585 | [13 empty] | NM | N | SMA Sunny Boy 3000 (1) | 2012-05-08 | 2012-05-14 | 4 | 2012-05-14 | [14 empty] | 2012-11-29 | 2012-12-06 |  | Y
Central Hudson |  | SolarCity | CH-07376 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8072 | Shenandoah | N |  | 6 | [13 empty] | NM | N | Power One Aurora PVI 6000 | 2012-05-08 | 2012-05-11 | 3 | 2012-05-11 | [14 empty] | 2012-09-13 | 2012-09-17 |  | Y
Central Hudson |  | SolarCity | CH-07493 | Kingston | Accord | Ulster | 12404 | G | 3024 | High Falls | N |  | 6 | [13 empty] | NM | N | Power One Aurora PVI 6000 | 2012-05-08 | 2012-05-09 | 1 | 2012-05-09 | [14 empty] | 2012-09-19 | 2012-09-26 |  | Y
Central Hudson |  | D&M Alternative Energy | CH-00816 | Catskill | Coxsackie | Greene | 12051 | G | 1076 | Coxsackie | N |  | 2 | [13 empty] | NM | N | SMA 2000HF-US (1) | 2012-06-04 | 2012-06-07 | 3 | 2012-06-07 | [14 empty] | 2012-08-15 | 2012-08-27 |  | Y
Central Hudson |  | Solar Generation | CH-08229 | Kingston | Bearsvl | Ulster | 12409 | G | 3012 | Woodstock | N |  | 7.5 | [13 empty] | NM | N | Fronius IG Plus 7.5 (1) | 2012-05-15 | 2012-05-18 | 3 | 2012-05-18 | [14 empty] | 2012-07-10 | 2012-07-16 |  | Y
Central Hudson |  | Lotus Energy Inc. | CH-03847 | Catskill | Catskill | Greene | 12414 | G | 2001 | North Catskill | N | CH-03847 | 11.52 | [13 empty] | NM | N | SMA SB6000U (2) | 2012-06-05 | 2012-06-08 | 3 | 2012-06-08 | [8 empty] | 350 | 350 |  | 2015-11-04 | 2015-11-04 | 2015-11-23 | 2012-10-24 | 2012-10-29 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03740 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7052 | Rhinebeck | N |  | 24 | [13 empty] | NM | N | Power One Aurora PVI6000 (4) | 2012-05-22 | 2012-05-22 | 0 | 2012-05-22 | [8 empty] | 350 | 350 |  |  |  |  | 2012-08-08 | 2012-08-15 |  | Y
Central Hudson |  | Hudson Solar | CH-01800 | Poughkeepsie | Salt Pt | Dutchess | 12578 | G | 7011 | Hibernia | N |  | 50 | [13 empty] | RNM | N | Schneider Conext 5000 (10) | 2012-05-16 | 2012-05-22 | 4 | 2012-05-22 | [14 empty] | 2012-06-15 | 2012-07-06 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SunDog Solar | CH-09162 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8043 | Myers Corners | N |  | 5.16 | [13 empty] | NM | N | Enphase M215 (24) | 2012-05-16 | 2012-05-21 | 3 | 2012-05-21 | [14 empty] | 2012-08-03 | 2012-08-10 |  | Y
Central Hudson |  | Lotus Energy Inc. | CH-03841 | Catskill | Catskill | Greene | 12414 | G | 2001 | North Catskill | N |  | 15 | [13 empty] | NM | N | Fronius USA IG Plus 7.5 (2) | 2012-06-05 | 2012-06-07 | 2 | 2012-06-07 | [14 empty] | 2012-09-24 | 2012-09-24 |  | Y
Central Hudson |  | Lotus Energy Inc. | CH-03870 | Catskill | Catskill |  | 12414 | G | 2001 | North Catskill | TBD |  | 15 | [13 empty] | NM | N | Fronius USA IG Plus 7.5 (2) | 2012-06-05 | 2012-06-07 | 2 | 2012-06-07 | [15 empty] | 2012-09-24 |  | W |  | 5/24/12 Incomplete issued.
Central Hudson |  | Endless Mtn Solar Services | CH-01116 | Fishkill | Fishkill | Dutchess | 12524 | G | 8014 | Forgebrook | N |  | 3.44 | [13 empty] | NM | N | Enphase M215 (16) | 2012-05-17 | 2012-05-22 | 3 | 2012-05-22 | [14 empty] | 2012-08-28 | 2012-09-11 |  | Y
Central Hudson |  | Hudson Solar | CH-01768 | Poughkeepsie | Staatsburg | Dutchess | 12580 | G | 7041 | Staatsburg | N |  | 3.87 | [13 empty] | NM | N | Xantrex XW 4500 | 2012-05-25 | 2012-05-30 | 2 | 2012-05-30 | [14 empty] | 2012-06-18 | 2012-06-22 |  | Y
Central Hudson |  | Endless Mtn Solar Services | CH-01114 | Fishkill | Cold Spring | Putnam | 10516 | G | 8087 | Tioronda | N |  | 2.15 | [13 empty] | NM | N | Enphase M215 (10) | 2012-05-21 | 2012-05-24 | 3 | 2012-05-24 | [14 empty] | 2012-11-19 | 2012-11-27 |  | Y
Central Hudson |  | Endless Mtn Solar Services | CH-01115 | Fishkill | Cold Spg | Putnam | 10516 | G | 8087 | Tioronda | N |  | 6.45 | [13 empty] | NM | N | Enphase M215 (30) | 2012-05-31 | 2012-05-31 | 0 | 2012-05-31 | [14 empty] | 2012-09-27 | 2012-10-04 |  | Y
Central Hudson |  | Solar Generation | CH-08228 | Kingston | Bearsvl | Ulster | 12409 | G | 3012 | Woodstock | N |  | 2.7 | [13 empty] | NM | N | Fronius IG Plus 3000 | 2012-05-30 | 2012-05-30 | 0 | 2012-05-30 | [14 empty] | 2012-07-10 | 2012-07-13 |  | Y
Central Hudson |  | SolarCity | CH-05321 | Kingston | Rosendale | Ulster | 12472 | G | 3022 | High Falls | N | CH-05321 | 6 | [13 empty] | NM | N | Power One Aurora PVI 6000 (1) | 2012-07-02 | 2012-07-05 | 2 | 2012-07-05 | [14 empty] | 2012-09-06 | 2012-09-12 |  | Y
Central Hudson |  | SolarCity | CH-05025 | Poughkeepsie | Millbrook | Dutchess | 12545 | G | 7025 | Tinkertown | N |  | 13.6 | [13 empty] | NM | N | Power-One Aurora PVI 5000 (2) & Power-One Aurora PVI 3.6 (1) | 2012-06-05 | 2012-06-06 | 1 | 2012-06-06 | [14 empty] | 2012-07-26 | 2012-07-31 |  | Y
Central Hudson |  | SolarCity | CH-06488 | Kingston | Rosendale | Ulster | 12472 | G | 3022 | High Falls | N |  | 3.6 | [13 empty] | NM | N | Power-One Aurora PVI 3.6 (1) | 2012-05-30 | 2012-06-04 | 3 | 2012-06-04 | [14 empty] | 2012-08-29 | 2012-09-04 |  | Y
Central Hudson |  | SolarCity | CH-07473 | Newburgh | Montgomery | Orange | 12549 | G | 5073 | Montgomery | N |  | 7 | [13 empty] | NM | N | Sunny Boy 7000 PVI 7.0 (1) | 2012-05-30 | 2012-06-04 | 3 | 2012-06-04 | [14 empty] | 2013-07-24 | 2013-08-01 |  | Y
Central Hudson |  | Hudson Solar | CH-01390 | Poughkeepsie | Amenia | Dutchess | 12501 | G | 7095 | Smithfield | N |  | 36 | [13 empty] | NM | N | Sunpower 7000m PVI (3) & Sunpower 5000m PVI (3) | 2012-05-31 | 2012-06-06 | 4 | 2012-06-06 | [14 empty] | 2012-11-02 | 2012-11-09 |  | Y
Central Hudson |  | SolarCity | CH-06606 | Kingston | Kingston | Ulster | 12401 | G | 2013 | Lincoln Park | N |  | 6 | [13 empty] | NM | N | Power-One Aurora PVI-6000 (1) | 2012-06-04 | 2012-06-06 | 2 | 2012-06-06 | [14 empty] | 2012-08-29 | 2012-09-05 |  | Y
Central Hudson |  | SolarCity | CH-06616 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6045 | Spackenkill | N | CH-06616 | 7.5 | [13 empty] | NM | N | Frontius IG Plus V 7.5 (1) | 2012-06-04 | 2012-06-06 | 2 | 2012-06-06 | [14 empty] | 2012-08-29 | 2012-09-04 |  | Y
Central Hudson |  | Harragin Water Conditioning | CH-01197 | Newburgh | Campbell Hall | Orange | 10916 | G | 5051 | Maybrook | N |  | 13 | [13 empty] | NM | N | SMA SB6000US (1) & SMA SB7000US (1) | 2012-06-22 | 2012-06-28 | 4 | 2012-06-28 | [14 empty] | 2014-11-13 | 2014-11-13 |  | Y
Central Hudson |  | Solar Generation | CH-08293 | Kingston | Bearsville | Ulster | 12409 | G | 3012 | Woodstock | N |  | 7.5 | [13 empty] | NM | N | SPR-7501F (1) | 2012-06-06 | 2012-06-08 | 2 | 2012-06-08 | [8 empty] | 350 | 350 |  | 2012-07-06 | 2012-07-06 | 2012-07-06 | 2012-07-19 | 2012-07-25 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00965 | Newburgh | Newburgh | Orange | 12550 | G | 4013 | West Balmville | N |  | 8.385 | [13 empty] | NM | N | Enphase 215 (39) | 2012-06-22 | 2012-06-22 | 0 | 2012-06-22 | [14 empty] | 2012-08-08 | 2012-08-15 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00977 | Newburgh | Montgomery | Orange | 12549 | G | 5072 | Montgomery | N |  | 8.385 | [13 empty] | NM | N | Enphase M215 (39) | 2012-07-10 | 2012-07-13 | 3 | 2012-07-13 | [14 empty] | 2012-08-13 | 2012-08-17 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03739 | Poughkeepsie | Lagrangevl | Dutchess | 12540 | G | 6053 | Todd Hill | N | CH-03739 | 6.45 | [13 empty] | NM | N | Enphase M215 (30) | 2012-06-06 | 2012-06-11 | 3 | 2012-06-11 | [14 empty] | 2012-10-11 | 2012-10-11 |  | W
Central Hudson |  | Sungevity Inc | CH-09216 | Newburgh | New Paltz | Ulster | 12561 | G | 5011 | Modena | N |  | 7 | [13 empty] | NM | N | SMA AMERICA SB7000US (1) | 2012-06-13 | 2012-06-13 | 0 | 2012-06-13 | [14 empty] | 2013-02-14 | 2013-02-22 |  | Y
Central Hudson |  | Conscious Energy | CH-00797 | Newburgh | Gardiner | Ulster | 12525 | G | 5011 | Modena | N |  | 3.655 | [13 empty] | NM | N | Enphase M215(17) | 2012-07-02 | 2012-07-02 | 0 | 2012-07-02 | [14 empty] | 2012-07-16 | 2012-07-18 |  | Y
Central Hudson |  | Mountaintop Greene Clean Energy | CH-02707 | Catskill | Durham | Greene | 12422 | G | 1092 | Westerlo | N |  | 2.58 | [13 empty] | NM | N | Enphase M215 (12) | 2012-06-20 | 2012-06-26 | 4 | 2012-06-26 | [14 empty] | 2012-09-10 | 2012-09-14 |  | Y
Central Hudson |  | SURE Sustainable Renewable Energy | CH-09700 | Fishkill | Beacon | Dutchess | 12508 | G | 8085 | Tioronda | N |  | 5 | [13 empty] | NM | N | SMA 5000US (1) | 2012-06-15 | 2012-06-18 | 1 | 2012-06-18 | [14 empty] | 2012-06-19 | 2012-06-29 |  | Y
Central Hudson |  | SolarCity | CH-05638 | Kingston | Kingston | Ulster | 12401 | G | 2093 | Hurley Ave | N |  | 3 | [13 empty] | NM | N | Power One 3.0 | 2012-06-12 | 2012-06-15 | 3 | 2012-06-15 | [14 empty] | 2012-08-29 | 2012-09-05 |  | Y
Central Hudson |  | SolarCity | CH-05817 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6065 | Inwood Ave | N | CH-05817 | 6 | [13 empty] | NM | N | Fronius IG 4000 (1) & Fronius IG 2000 (1) | 2012-06-15 | 2012-06-15 | 0 | 2012-06-15 | [14 empty] | 2012-10-03 | 2012-10-10 |  | Y
Central Hudson |  | SolarCity | CH-06610 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6046 | Spackenkill | N |  | 6 | [13 empty] | NM | N | SolarEdge SE6000A | 2012-06-12 | 2012-06-15 | 3 | 2012-06-15 | [14 empty] | 2012-08-07 | 2012-08-13 |  | Y
Central Hudson |  | Solar Generation | CH-08151 | Kingston | Kingston | Ulster | 12401 | G | 2094 | Hurley Ave | N |  | 4.905 | [13 empty] | NM | N | Sunpower SPR 5000M | 2012-06-22 | 2012-06-28 | 4 | 2012-06-28 | [14 empty] | 2013-03-22 | 2013-03-27 |  | Y
Central Hudson |  | SolarCity | CH-04957 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8095 | Fishkill Plains | N |  | 7.2 | [13 empty] | NM | N | Fronius IG Plus (1) | 2012-06-13 | 2012-06-19 | 4 | 2012-06-19 | [14 empty] | 2012-09-12 | 2012-09-17 |  | Y
Central Hudson |  | SolarCity | CH-05440 | Kingston | Saugerties | Ulster | 12477 | G | 3004 | Saugerties | N |  | 5 | [13 empty] | NM | N | SMA SUNNY BOY 5000 | 2012-06-13 | 2012-06-15 | 2 | 2012-06-15 | [14 empty] | 2012-09-19 | 2012-09-20 |  | Y
Central Hudson |  | SolarCity | CH-05968 | Poughkeepsie | Millerton | Dutchess | 12546 | G | 7081 | Millerton | N |  | 7 | [13 empty] | NM | N | SMA Sunny Boy 7000 | 2012-06-13 | 2012-06-20 | 5 | 2012-06-20 | [14 empty] | 2012-08-31 | 2012-09-10 |  | Y
Central Hudson |  | SolarCity | CH-06837 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8043 | Myers Corners | N |  | 4.2 | [13 empty] | NM | N | Power One 4.2 (1) | 2012-06-13 | 2012-06-18 | 3 | 2012-06-18 | [14 empty] | 2012-08-29 | 2012-09-05 |  | Y
Central Hudson |  | RGS Energy | CH-03008 | Poughkeepsie | Pleasant Vly |  | 12569 | G | 6051 | Todd Hill | TBD |  | 7 | [13 empty] | NM | N | SMA SB7000 | 2012-06-22 | 2012-06-29 | 5 | 2012-06-29 | [17 empty] | W |  | VTP missing from application packet. 6/21/12 Incomplete Issued. 6/22/12 Received VTP. 8/1/12 Received notification that the project has been abandoned.
Central Hudson |  | SolarCity | CH-04972 | Newburgh | New Paltz | Ulster | 12561 | G | 5031 | Galeville | N |  | 6 | [13 empty] | NM | N | Power One 6000 | 2012-06-14 | 2012-06-20 | 4 | 2012-06-20 | [14 empty] | 2012-10-02 | 2012-10-09 |  | Y
Central Hudson |  | SolarCity | CH-05800 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6094 | Manchester | N |  | 4.2 | [13 empty] | NM | N | Power-One Autora PVI-4.2 | 2012-06-14 | 2012-06-21 | 5 | 2012-06-21 | [14 empty] | 2012-12-06 | 2012-12-13 |  | Y
Central Hudson |  | SolarCity | CH-06270 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 7 | [13 empty] | NM | N | SMA Sunny Boy 7000 | 2012-06-20 | 2012-06-21 | 1 | 2012-06-21 | [14 empty] | 2012-09-26 | 2012-10-03 |  | Y
Central Hudson |  | SolarCity | CH-06523 | Kingston | Ulster Pk | Ulster | 12487 | G | 1014 | Boulevard | N |  | 6 | [13 empty] | NM | N | Power One 6000 | 2012-06-14 | 2012-06-20 | 4 | 2012-06-20 | [8 empty] | 350 | 350 |  |  |  |  | 2012-09-14 | 2012-11-16 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00942 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7062 | Milan | N |  | 6.665 | [13 empty] | NM | N | ENPHASE ENERGY 60-2LL-S22 (31) | 2012-06-25 | 2012-06-25 | 0 | 2012-06-25 | [14 empty] | 2012-08-17 | 2012-08-24 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00982 | Kingston | Stone Ridge | Ulster | 12484 | G | 3023 | High Falls | N |  | 6.45 | [13 empty] | NM | N | ENPHASE ENERGY M215 (30) | 2012-06-25 | 2012-06-29 | 4 | 2012-06-29 | [14 empty] | 2012-09-24 | 2012-10-01 |  | Y
Central Hudson |  | Hudson Solar | CH-01262 | Catskill | Westerlo |  | 12193 | G | 1092 | Westerlo | TBD |  | 37.8 | [13 empty] | NM | N | CONEXT 5000NA (7) & CONEXT 2800NA (1) | 2012-06-18 | 2012-06-25 | 5 | 2012-06-25 | [8 empty] | 2000 | 2000 | [7 empty] | W |  | Transformer upgrade required to accommodate PV installation. 10/7/14 Project abandoned as per customer.
Central Hudson |  | Hudson Solar | CH-01462 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8071 | Shenandoah | N | CH-01462 | 6.867 | [13 empty] | NM | N | SUNPOWER 7000M (1) | 2012-06-18 | 2012-06-25 | 5 | 2012-06-25 | [14 empty] | 2012-07-13 | 2012-07-17 |  | Y
Central Hudson |  | Hudson Solar | CH-01671 | Kingston | Cottekill | Ulster | 12419 | G | 3021 | High Falls | Y | CH-01671 | 6 | 4.5 | [12 empty] | NM | N | (1) Schneider XW60481XantrexXW4548 (DC) | 2012-06-18 | 2012-06-22 | 4 | 2012-06-22 | [14 empty] | 2012-07-30 | 2012-08-02 |  | Y
Central Hudson |  | Hudson Solar | CH-02384 | Kingston | Woodstock | Ulster | 12498 | G | 3014 | Woodstock | N |  | 9.89 | [13 empty] | NM | N | SunPower 6000M (1) & SunPower 4000M (1) | 2012-06-25 | 2012-06-25 | 0 | 2012-06-25 | [8 empty] | 350 | 350 |  |  |  |  | 2013-01-03 | 2013-01-08 |  | Y
Central Hudson |  | Hudson Solar | CH-02398 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7061 | Milan | N |  | 9.8 | [13 empty] | NM | N | SunPower 5000M (2) | 2012-06-18 | 2012-06-22 | 4 | 2012-06-22 | [14 empty] | 2012-08-20 | 2012-08-27 |  | Y
Central Hudson |  | Hudson Solar | CH-02439 | Kingston | Kingston | Ulster | 12401 | G | 1011 | Boulevard | N | CH-01698 | 2.96 | [13 empty] | NM | N | SMA SB3000US (1) | 2012-06-18 | 2012-06-25 | 5 | 2012-06-25 | [14 empty] | 2012-08-01 | 2012-08-08 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Direct Energy Solar | CH-00929 | Poughkeepsie | Clinton Cors | Dutchess | 12514 | G | 7013 | Hibernia | N |  | 8.385 | [13 empty] | NM | N | Enphase M215 (39) | 2012-06-19 | 2012-06-26 | 5 | 2012-06-26 | [14 empty] | 2012-08-17 | 2012-08-20 |  | Y
Central Hudson |  | SolarCity | CH-05237 | Catskill | Coxsackie |  | 12051 | G | 1076 | Coxsackie | N |  | 6 | [13 empty] | NM | N | Power-One 6000 (1) | 2012-06-19 | 2012-06-20 | 1 | 2012-06-20 | [14 empty] | 2012-08-31 | 2012-09-10 |  | W
Central Hudson |  | Direct Energy Solar | CH-01000 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6092 | Manchester | N |  | 10.32 | [13 empty] | NM | N | Enphase M215 (48) | 2012-06-25 | 2012-06-27 | 2 | 2012-06-27 | [14 empty] | 2012-09-04 | 2012-09-11 |  | Y
Central Hudson |  | Hudson Solar | CH-01435 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 7024 | Tinkertown | N |  | 64.092 | [13 empty] | NM | N | Sunpower 11401F-3-208 (6) | 2012-06-21 | 2012-06-28 | 5 | 2012-06-28 | [14 empty] | 2012-09-28 | 2012-10-05 |  | Y
Central Hudson |  | SolarCity | CH-05336 | Newburgh | New Paltz | Ulster | 12561 | G | 5031 | Galeville | N |  | 7.2 | [13 empty] | NM | N | Power One PVI 3.6 (2) | 2012-06-28 | 2012-06-28 | 0 | 2012-06-28 | [14 empty] | 2012-10-29 | 2012-11-07 |  | Y
Central Hudson |  | SolarCity | CH-05620 | Kingston | New Paltz | Ulster | 12561 | G | 3041 | Sturgeon Pool | N |  | 8 | [13 empty] | NM | N | Power One Aurora PVI 5000 (1) & Power One Aurora PVI 3.0 (1) | 2012-06-21 | 2012-06-27 | 4 | 2012-06-27 | [14 empty] | 2012-09-13 | 2012-09-18 |  | Y
Central Hudson |  | SolarCity | CH-05902 | Poughkeepsie | Millbrook | Dutchess | 12545 | G | 7012 | Hibernia | N | CH-05902 | 5 | [13 empty] | NM | N | SMA Sunny Boy 5000 | 2012-06-21 | 2012-06-27 | 4 | 2012-06-27 | [14 empty] | 2012-10-24 | 2012-10-29 |  | Y
Central Hudson |  | SolarCity | CH-06697 | Poughkeepsie | Staatsburg | Dutchess | 12580 | G | 7042 | Staatsburg | N | CH-06697 | 6 | [13 empty] | NM | N | SMA SUNNY BOY 6000 (1) | 2012-06-21 | 2012-06-27 | 4 | 2012-06-27 | [14 empty] | 2012-12-31 | 2012-12-31 |  | Y
Central Hudson |  | SolarCity | CH-07095 | Newburgh | Modena | Ulster | 12548 | G | 5011 | Modena | N |  | 7.2 | [13 empty] | NM | N | POWER-ONE AURORA PVI-4.2 (1) & POWER-ONE AURORA PVI-3 (1) | 2012-06-29 | 2012-07-05 | 3 | 2012-07-05 | [14 empty] | 2012-09-26 | 2012-10-02 |  | Y
Central Hudson |  | SolarCity | CH-07605 | Newburgh | Marlboro | Ulster | 12542 | G | 5004 | Marlboro | N |  | 5 | [13 empty] | NM | N | Power One Aurora PVI 5000 | 2012-06-21 | 2012-06-27 | 4 | 2012-06-27 | [14 empty] | 2012-08-29 | 2012-09-05 |  | Y
Central Hudson |  | Endless Mtn Solar Services | CH-01113 | Fishkill | Cold Spg | Putnam | 10516 | G | 8063 | Merritt Park | N |  | 4.085 | [13 empty] | NM | N | Enphase M215 (19) | 2012-06-28 | 2012-06-28 | 0 | 2012-06-28 | [14 empty] | 2012-10-12 | 2012-10-16 |  | Y
Central Hudson |  | Hudson Solar | CH-01624 | Catskill | Westerlo | Albany | 12193 | G | 1091 | Westerlo | N |  | 5.76 | [13 empty] | NM | N | SMA 6000US (1) | 2012-06-22 | 2012-06-29 | 5 | 2012-06-29 | [14 empty] | 2012-07-17 | 2012-07-17 |  | Y
Central Hudson |  | Malcarne Contracting | CH-03903 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 7023 | Tinkertown | N |  | 5 | [13 empty] | NM | N | SMA SB50000 (1) | 2012-06-25 | 2012-06-29 | 4 | 2012-06-29 | [14 empty] | 2012-08-09 | 2012-08-22 |  | Y
Central Hudson |  | Solar Generation | CH-08083 | Kingston | Hurley | Ulster | 12443 | G | 2094 | Hurley Ave | N |  | 7.5 | [13 empty] | NM | N | SUNPOWER SPR-7501F-1 (1) | 2012-06-29 | 2012-06-29 | 0 | 2012-06-29 | [14 empty] | 2012-10-05 | 2012-10-11 |  | Y
Central Hudson |  | Solar Generation | CH-08237 | Kingston | Hurley | Ulster | 12443 | G | 2094 | Hurley Ave | N |  | 6.5 | [13 empty] | NM | N | SUNPOWER SPR-6501F-1 | 2012-06-29 | 2012-07-02 | 1 | 2012-07-02 | [14 empty] | 2012-10-05 | 2012-10-11 |  | Y
Central Hudson |  | Hudson Solar | CH-01618 | Catskill | Surprise | Greene | 12176 | G | 2061 | Freehold | N |  | 5.76 | [13 empty] | NM | N | SMA SB6000US (1) | 2012-06-27 | 2012-07-02 | 3 | 2012-07-02 | [14 empty] | 2012-09-11 | 2012-09-14 |  | Y
Central Hudson |  | SolarCity | CH-06096 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8045 | Myers Corners | N |  | 7.2 | [13 empty] | NM | N | POWER-ONE AURORA PVI-4.2 (1) & POWER-ONE AURORA PVI-3.0 (1) | 2012-06-27 | 2012-07-02 | 3 | 2012-07-02 | [14 empty] | 2012-11-29 | 2012-12-06 |  | Y
Central Hudson |  | SolarCity | CH-07494 | Kingston | Stone Ridge | Ulster | 12484 | G | 3023 | High Falls | N |  | 6 | [13 empty] | NM | N | SOLOAREDGE SE6000A | 2012-06-27 | 2012-07-02 | 3 | 2012-07-02 | [14 empty] | 2012-09-26 | 2012-10-03 |  | Y
Central Hudson |  | Direct Energy Solar | CH-01054 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6044 | Spackenkill | N |  | 7.74 | [13 empty] | NM | N | Enphase M215 (36) | 2012-07-10 | 2012-07-13 | 3 | 2012-07-13 | [14 empty] | 2012-08-15 | 2012-08-22 |  | Y
Central Hudson |  | Hudson Solar | CH-02402 | Newburgh | Esopus | Ulster | 12429 | G | 5084 | Highland | N |  | 3.597 | [13 empty] | NM | N | SUNPOWER 3600P | 2012-06-29 | 2012-07-03 | 2 | 2012-07-03 | [14 empty] | 2012-10-17 | 2012-10-24 |  | Y
Central Hudson |  | Sungevity Inc | CH-09460 | Fishkill | Beacon | Dutchess | 12508 | G | 8017 | Forgebrook | N |  | 3.04 | [13 empty] | NM | N | Kaco 3502 (1) | 2012-06-29 | 2012-07-03 | 2 | 2012-07-03 | [14 empty] | 2012-09-26 | 2012-10-02 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03696 | Newburgh | Wallkill | Ulster | 12589 | G | 5041 | East Walden | N |  | 7.14 | [13 empty] | NM | N | POWER ONE AURORA PVI 3.6-OUTD-US (2) | 2012-07-06 | 2012-07-06 | 0 | 2012-07-06 | [14 empty] | 2012-10-05 | 2012-10-11 |  | Y
Central Hudson |  | SolarCity | CH-05526 | Catskill | Medusa | Albany | 12120 | G | 1092 | Westerlo | N |  | 7.2 | [13 empty] | NM | N | FRONIUS IG PLUS V 7.5 | 2012-07-03 | 2012-07-05 | 1 | 2012-07-05 | [14 empty] | 2012-09-20 | 2012-09-26 |  | Y
Central Hudson |  | Direct Energy Solar | CH-01025 | Newburgh | Cornwall | Orange | 12518 | G | 4043 | Union Ave | N |  | 11.18 | [13 empty] | NM | N | Enphase M215 (52) | 2012-07-11 | 2012-07-12 | 1 | 2012-07-12 | [14 empty] | 2012-08-14 | 2012-08-17 |  | Y
Central Hudson |  | Murphy Solar Power | CH-02722 | Catskill | Cairo | Greene | 12413 | G | 2043 | South Cairo | N |  | 3 | [13 empty] | NM | N | SMA Sunny Boy 3000 (1) | 2012-07-09 | 2012-07-09 | 0 | 2012-07-09 | [14 empty] | 2012-07-19 | 2012-07-25 |  | Y
Central Hudson |  | RGS Energy | CH-03050 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8055 | North Chelsea | N |  | 6.02 | [13 empty] | NM | N | Enphase M215 (28) | 2012-07-17 | 2012-07-23 | 4 | 2012-07-23 | [14 empty] | 2013-03-08 | 2013-03-13 |  | Y
Central Hudson |  | SunDog Solar | CH-09137 | Poughkeepsie | Clinton Corners | Dutchess | 12514 | G | 7071 | Stanfordville | N |  | 5.1 | [13 empty] | NM | N | OUTBACK POWER RADIAN GS8048 | 2012-07-13 | 2012-07-16 | 1 | 2012-07-16 | [14 empty] | 2012-09-12 | 2012-09-13 |  | Y
Central Hudson |  | Hudson Solar | CH-01213 | Poughkeepsie | Staatsburg | Dutchess | 12580 | G | 7041 | Staatsburg | N |  | 8.829 | [13 empty] | NM | N | SunPower SPR 3000 (1) & SunPower SPR 6000 (1) | 2012-07-16 | 2012-07-16 | 0 | 2012-07-16 | [14 empty] | 2012-11-29 | 2012-12-06 |  | Y
Central Hudson |  | Hudson Solar | CH-01283 | Kingston | High Fls | Ulster | 12440 | G | 3024 | High Falls | N |  | 6 | [13 empty] | NM | N | SUNPOWER 6000P (1) | 2012-07-11 | 2012-07-16 | 3 | 2012-07-16 | [14 empty] | 2012-10-19 | 2012-10-25 |  | Y
Central Hudson |  | Hudson Solar | CH-01956 | Newburgh | Clintondale | Ulster | 12515 | G | 5012 | Modena | N |  | 10 | [13 empty] | NM | N | Sunpower 5000M (2) | 2012-07-11 | 2012-07-13 | 2 | 2012-07-13 | [14 empty] | 2012-12-13 | 2012-12-18 |  | Y
Central Hudson |  | Solar Generation | CH-08252 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7056 | Rhinebeck | N |  | 9.81 | [13 empty] | NM | N | SUNPOWER 1000F-1 UNI | 2012-07-19 | 2012-07-25 | 4 | 2012-07-25 | [14 empty] | 2012-09-06 | 2012-09-12 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00861 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8043 | Myers Corners | N |  | 4.3 | [13 empty] | NM | N | Enphase M215 (20) | 2012-07-17 | 2012-07-17 | 0 | 2012-07-17 | [14 empty] | 2012-09-13 | 2012-09-14 |  | Y
Central Hudson |  | Hudson Solar | CH-01502 | Poughkeepsie | Pine Plns | Dutchess | 12567 | G | 7091 | Pulvers Corners | N |  | 10 | [13 empty] | NM | N | SCHNEIDER CONEXT 5000NA (2) | 2012-07-12 | 2012-07-17 | 3 | 2012-07-17 | [14 empty] | 2012-07-23 | 2012-07-30 |  | Y
Central Hudson |  | Solar Generation | CH-08153 | Kingston | Stone Ridge | Ulster | 12484 | G | 3023 | High Falls | N |  | 7.5 | [13 empty] | NM | N | SUNPOWER SPR-7501F-240 (1) | 2012-07-12 | 2012-07-17 | 3 | 2012-07-17 | [14 empty] | 2013-05-01 | 2013-05-01 |  | Y
Central Hudson |  | Hudson Solar | CH-01915 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8092 | Fishkill Plains | N | CH-01915 | 6 | [13 empty] | NM | N | SUNPOWER 6000P | 2012-07-16 | 2012-07-23 | 5 | 2012-07-23 | [14 empty] | 2012-11-21 | 2012-11-30 |  | Y
Central Hudson |  | SolarCity | CH-04974 | Catskill | Catskill |  | 12414 | G | 2004 | North Catskill | TBD |  | 485.745 | [13 empty] | NM | N | XANTREX GT500-480 | 2012-07-24 | 2012-08-10 | 13 | 2012-08-10 | 2012-07-24 | 2012-08-10 | 13 | [14 empty] | W |  | System determined eligible for fast track process during preliminary review Section C, Step 4.
Central Hudson |  | SolarCity | CH-05054 | Newburgh | Newburgh | Orange | 12550 | G | 4092 | Bethlehem Rd | N |  | 439.92 | [13 empty] | NM | N | XANTREX GT500-480 | 2012-07-24 | 2012-08-10 | 13 | 2012-08-10 | [14 empty] | 2012-10-02 | 2012-10-15 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03569 | Newburgh | Newburgh |  | 12550 | G | 4051 | Union Ave | TBD |  | 15 | [13 empty] | NM | N | POWER ONE AURORA PVI5000 (3) | 2012-07-19 | 2012-07-25 | 4 | 2012-07-25 | [14 empty] | 2012-12-21 | 2012-12-21 |  | W
Central Hudson |  | Lighthouse Solar | CH-03599 | Newburgh | Newburgh | Orange | 12550 | G | 4051 | Union Ave | N |  | 15 | [13 empty] | NM | N | POWER ONE AURORA PVI5000 (3) | 2012-07-19 | 2012-07-25 | 4 | 2012-07-25 | [14 empty] | 2012-12-21 | 2012-12-21 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03711 | Newburgh | Wallkill | Ulster | 12589 | G | 5013 | Modena | N |  | 5 | [13 empty] | NM | N | POWER-ONE AURORA PVI5000 (1) | 2012-07-19 | 2012-07-25 | 4 | 2012-07-25 | [14 empty] | 2013-05-02 | 2013-05-09 |  | Y
Central Hudson |  | Hudson Solar | CH-02024 | Kingston | Kingston | Ulster | 12401 | G | 2017 | Lincoln Park | N |  | 6 | [13 empty] | NM | N | SUNPOWER 6000P (1) | 2012-07-19 | 2012-07-25 | 4 | 2012-07-25 | [14 empty] | 2012-12-13 | 2012-12-18 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03726 | Newburgh | Newburgh | Orange | 12550 | G | 4015 | West Balmville | N |  | 10 | [13 empty] | NM | N | POWER ONE AURORA PVI10 (1) | 2012-07-20 | 2012-07-26 | 4 | 2012-07-26 | [14 empty] | 2013-01-15 | 2013-01-17 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03727 | Newburgh | Newburgh | Orange | 12550 | G | 4015 | West Balmville | N |  | 10 | [13 empty] | NM | N | POWER ONE AURORA PVI10 (1) | 2012-07-20 | 2012-07-26 | 4 | 2012-07-26 | [14 empty] | 2013-01-15 | 2013-01-17 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03728 | Newburgh | Newburgh | Orange | 12550 | G | 4015 | West Balmville | N |  | 30 | [13 empty] | NM | N | Aurora PVI 10 (3) | 2012-07-30 | 2012-07-30 | 0 | 2012-07-30 | [14 empty] | 2013-01-15 | 2013-01-17 |  | Y
Central Hudson |  | Hudson Solar | CH-02247 | Kingston | Saugerties | Ulster | 12477 | G | 2016 | Lincoln Park | N |  | 6 | [13 empty] | NM | N | POWERONE PVI-6000 (1) | 2012-07-20 | 2012-07-27 | 5 | 2012-07-27 | [14 empty] | 2012-10-18 | 2012-10-24 |  | Y
Central Hudson |  | SolarCity | CH-07157 | Newburgh | New Windsor | Orange | 12553 | G | 4053 | Union Ave | N |  | 6 | [13 empty] | NM | N | POWER ONE AURORA PVI-6000 | 2012-07-20 | 2012-07-27 | 5 | 2012-07-27 | [14 empty] | 2013-02-06 | 2013-02-06 |  | Y
Central Hudson |  | SolarCity | CH-05027 | Poughkeepsie | Clinton Corners | Dutchess | 12514 | G | 7013 | Hibernia | N |  | 6 | [13 empty] | NM | N | POWER-ONE AURORA PVI-6000 (1) | 2012-07-27 | 2012-07-30 | 1 | 2012-07-30 | [14 empty] | 2012-10-03 | 2012-10-10 |  | Y
Central Hudson |  | SolarCity | CH-06242 | Newburgh | Newburgh | Orange | 12550 | G | 4051 | Union Ave | N |  | 5 | [13 empty] | NM | N | POWER-ONE AURORA PVI-5000 | 2012-07-24 | 2012-07-30 | 4 | 2012-07-30 | [14 empty] | 2012-11-05 | 2012-11-12 |  | Y
Central Hudson |  | SolarCity | CH-06440 | Catskill | Jewett | Greene | 12444 | E | 2389 | Vinegar Hill | N |  | 6 | [13 empty] | NM | N | POWER-ONE AURORA PVI-6000 (1) | 2012-07-24 | 2012-07-30 | 4 | 2012-07-30 | [14 empty] | 2013-03-06 | 2013-03-13 |  | W
Central Hudson |  | SolarCity | CH-07447 | Newburgh | Newburgh | Orange | 12550 | G | 4055 | Union Ave | N |  | 3.8 | [13 empty] | NM | N | POWER-ONE AURORA PVI-3.8 (1) | 2012-07-27 | 2012-07-31 | 2 | 2012-07-31 | [14 empty] | 2012-10-09 | 2012-10-15 |  | Y
Central Hudson |  | SolarCity | CH-07874 | Poughkeepsie | Poughkeepsie |  | 12601 | G | 6061 | Inwood Ave | TBD |  | 6 | [13 empty] | NM | N | POWER-ONE AURORA PVI-6000 (1) | 2012-07-25 | 2012-07-31 | 4 | 2012-07-31 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | Solartech Renewables | CH-09064 | Newburgh | New Paltz | Ulster | 12561 | G | 5011 | Modena | N |  | 6.9 | [13 empty] | NM | N | SMA 7000 | 2012-07-31 | 2012-07-31 | 0 | 2012-07-31 | [14 empty] | 2012-11-03 | 2012-11-14 |  | Y
Central Hudson |  | Solartech Renewables | CH-09066 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8043 | Myers Corners | N |  | 6 | [13 empty] | NM | N | SMA 6000 | 2012-07-31 | 2012-07-31 | 0 | 2012-07-31 | [14 empty] | 2012-11-21 | 2012-11-30 |  | Y
Central Hudson |  | Harvest Power | CH-01198 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 6075 | East Park | N |  | 6.235 | [13 empty] | NM | N | ENPHASE M215 (29) | 2012-08-09 | 2012-08-16 | 5 | 2012-08-16 | [14 empty] | 2012-10-01 | 2012-10-05 |  | Y
Central Hudson |  | Sungevity Inc | CH-09214 | Fishkill | Fishkill |  | 12524 | G | 8065 | Merritt Park | TBD |  | 7.5 | [13 empty] | NM | N | KACO BLUEPLANET 5002XI (1) KACO BLUEPLANET 2502XI (1) | 2012-07-27 | 2012-07-31 | 2 | 2012-07-31 | [17 empty] | W
Central Hudson |  | Sungevity Inc | CH-09560 | Kingston | Olive Brdg | Ulster | 12461 | G | 3024 | High Falls | N |  | 2.94 | [13 empty] | NM | N | POWER ONE PVI-3.0-OUTD-S-US (1) | 2012-07-26 | 2012-07-31 | 3 | 2012-07-31 | [14 empty] | 2013-04-23 | 2013-04-29 |  | Y
Central Hudson |  | Lotus Energy Inc. | CH-03892 | Kingston | Olive Brdg | Ulster | 12461 | G | 3082 | Kerhonkson | N | CH-09687 | 2.4 | [13 empty] | NM | N | SMA AMERICA SB3000 (1) | 2012-07-27 | 2012-08-03 | 5 | 2012-08-03 | [14 empty] | 2012-11-14 | 2012-11-20 |  | Y
Central Hudson |  | Hudson Solar | CH-01387 | Kingston | Lk Katrine | Ulster | 12449 | G | 2016 | Lincoln Park | N |  | 4.2 | [13 empty] | NM | N | SUNPOWER SPR-4200P-TL-1 (1) | 2012-07-27 | 2012-08-02 | 4 | 2012-08-02 | [14 empty] | 2012-11-26 | 2012-12-03 |  | Y
Central Hudson |  | Hudson Solar | CH-01904 | Poughkeepsie | Stanfordvl | Dutchess | 12581 | G | 7072 | Stanfordville | N |  | 6 | [13 empty] | NM | N | SUNPOWER SPR-6000P-TL-1 (1) | 2012-07-27 | 2012-08-01 | 3 | 2012-08-01 | [14 empty] | 2013-01-14 | 2013-01-16 |  | Y
Central Hudson |  | Hudson Solar | CH-02022 | Kingston | High Fls | Ulster | 12440 | G | 3024 | High Falls | N |  | 9.2 | [13 empty] | NM | N | POWERONE PVI-4.2-OUT (1) & POWERONE PVI-5000 (1) | 2012-07-27 | 2012-08-02 | 4 | 2012-08-02 | [14 empty] | 2012-12-06 | 2012-12-13 |  | Y
Central Hudson |  | Hudson Solar | CH-02301 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8096 | Fishkill Plains | N |  | 15.6 | [13 empty] | NM | N | SUNPOWER SPR-6000P-TL-1 (2) SUNPOWER SPR-3600P-TL-1 (1) | 2012-07-27 | 2012-08-02 | 4 | 2012-08-02 | [14 empty] | 2012-12-12 | 2012-12-17 |  | Y
Central Hudson |  | Solartech Renewables | CH-09062 | Kingston | Stone Ridge | Ulster | 12484 | G | 3023 | High Falls | N |  | 5.16 | [13 empty] | NM | N | ENPHASE M215 (24) | 2012-08-15 | 2012-08-15 | 0 | 2012-08-15 | [14 empty] | 2013-01-04 | 2013-01-04 |  | Y
Central Hudson |  | Hudson Solar | CH-01419 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6045 | Spackenkill | N |  | 12 | [13 empty] | NM | N | SUNPOWER SPR-6000P-TL-1 (2) | 2012-07-30 | 2012-08-06 | 5 | 2012-08-06 | [14 empty] | 2012-12-13 | 2012-12-19 |  | Y
Central Hudson |  | Hudson Solar | CH-02250 | Poughkeepsie | Poughkeepsie |  | 12603 | G | 6095 | Manchester | TBD |  | 7 | [13 empty] | NM | N | SUNPOWER 7000M (1) | 2012-07-30 | 2012-08-06 | 5 | 2012-08-06 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | SolarCity | CH-05496 | Catskill | Jewett |  | 12444 | E | 2389 | Vinegar Hill | N |  | 6 | [13 empty] | NM | N | POWER-ONE AURORA PVI-6000 | 2012-07-30 | 2012-08-06 | 5 | 2012-08-06 | [14 empty] | 2012-12-11 | 2012-12-17 |  | W
Central Hudson |  | Hudson Solar | CH-01632 | Catskill | Athens | Greene | 12015 | G | 1074 | Coxsackie | N |  | 6 | [13 empty] | NM | N | SUNPOWER SPR-6000P-TL-1 | 2012-08-06 | 2012-08-06 | 0 | 2012-08-06 | [14 empty] | 2012-12-13 | 2012-12-13 |  | Y
Central Hudson |  | Kool-Temp | CH-02573 | Catskill | Earlton | Greene | 12058 | G | 2006 | North Catskill | N |  | 20 | [13 empty] | NM | N | FRONIUS IG PLUS 10.0-1 (2) | 2012-08-07 | 2012-08-07 | 0 | 2012-08-07 | [14 empty] | 2012-09-24 | 2012-09-26 |  | Y
Central Hudson |  | SolarCity | CH-05635 | Kingston | Kingston | Ulster | 12401 | G | 3021 | High Falls | N |  | 4.2 | [13 empty] | NM | N | POWER-ONE # AURORA PVI-4.2 (1) | 2012-07-31 | 2012-08-06 | 4 | 2012-08-06 | [14 empty] | 2012-09-17 | 2012-09-24 |  | Y
Central Hudson |  | Hudson Solar | CH-01633 | Catskill | Athens | Greene | 12015 | G | 2002 | North Catskill | N |  | 7 | [13 empty] | NM | N | SUNPOWER 7000M (1) | 2012-08-01 | 2012-08-06 | 3 | 2012-08-06 | [14 empty] | 2012-12-07 | 2012-12-13 |  | Y
Central Hudson |  | Sungevity Inc | CH-09333 | Poughkeepsie | Millerton | Dutchess | 12546 | G | 7095 | Smithfield | N |  | 7.8 | [13 empty] | NM | N | POWER-ONE PVI-4.2-OUTD-S (1) POWER-ONE PVI-3.6-OUTD-S (1) | 2012-08-01 | 2012-08-08 | 5 | 2012-08-08 | [14 empty] | 2012-12-06 | 2012-12-06 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00852 | Newburgh | New Paltz | Ulster | 12561 | G | 5031 | Galeville | N |  | 8.815 | [13 empty] | NM | N | ENPHASE ENERGY M215 (41) | 2012-08-09 | 2012-08-09 | 0 | 2012-08-09 | [14 empty] | 2012-11-26 | 2012-12-03 |  | Y
Central Hudson |  | New York State Solar Farm | CH-04018 | Newburgh | Milton | Ulster | 12547 | G | 5083 | Highland | N |  | 8.085 | [13 empty] | NM | N | FRONIUS 3.0 (3) | 2012-09-14 | 2012-09-14 | 0 | 2012-09-14 | [14 empty] | 2013-01-28 | 2013-01-30 |  | Y
Central Hudson |  | SolarCity | CH-07656 | Newburgh | Highland |  | 12528 | G | 5083 | Highland | TBD |  | 1.56 | [13 empty] | NM | N | POWER-ONE AURORA PVI-3.0 (1) | 2012-08-03 | 2012-08-10 | 5 | 2012-08-10 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | SolarCity | CH-07715 | Newburgh | New Paltz | Ulster | 12561 | G | 5031 | Galeville | N |  | 6 | [13 empty] | NM | N | POWER-ONE AURORA PVI-6000 | 2012-08-03 | 2012-08-10 | 5 | 2012-08-10 | [14 empty] | 2012-10-30 | 2012-11-09 |  | Y |  | 10/29/12 - HURRICANE SANDY.
Central Hudson |  | Solar Generation | CH-08124 | Kingston | Ulster Park | Ulster | 12487 | G | 3041 | Sturgeon Pool | N |  | 6 | [13 empty] | NM | N | POWER-ONE PVI6000 (1) | 2012-08-03 | 2012-08-10 | 5 | 2012-08-10 | [14 empty] | 2012-11-16 | 2012-11-27 |  | Y
Central Hudson |  | Solar Alchemy | CH-09008 | Fishkill | Cold Spg |  | 10516 | G | 8087 | Tioronda | TBD |  | 2.15 | [13 empty] | NM | N | Enphase M215 (10) | 2012-08-10 | 2012-08-10 | 0 | 2012-08-10 | [17 empty] | W |  | 9/24/12 Per email from Solar Alchemy this project has been abandoned by the applicant.
Central Hudson |  | Sun Mountain | CH-09121 | Kingston | Kingston | Ulster | 12401 | G | 2094 | Hurley Ave | N |  | 14 | [13 empty] | NM | N | SMA Sunny Boy 7000 (2) | 2012-08-06 | 2012-08-13 | 5 | 2012-08-13 | [8 empty] | 350 | 350 |  |  |  |  | 2013-02-21 | 2013-02-28 |  | Y
Central Hudson |  | Sungevity Inc | CH-09184 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7041 | Staatsburg | N |  | 6 | [13 empty] | NM | N | POWER-ONE PVI-6000 (1) | 2012-08-06 | 2012-08-13 | 5 | 2012-08-13 | [14 empty] | 2013-03-19 | 2013-03-19 |  | Y
Central Hudson |  | Sungevity Inc | CH-09392 | Kingston | Cementon | Greene | 12414 | G | 3004 | Saugerties | N |  | 3.6 | [13 empty] | NM | N | POWER-ONE PVI-3.6-OUTD (1) | 2012-08-06 | 2012-08-10 | 4 | 2012-08-10 | [14 empty] | 2013-03-06 | 2013-03-13 |  | Y
Central Hudson |  | Direct Energy Solar | CH-01015 | Fishkill | Hopewell Junction | Dutchess | 12533 | G | 8093 | Fishkill Plains | N |  | 9.675 | [13 empty] | NM | N | Enphase M215 (45) | 2012-08-13 | 2012-08-13 | 0 | 2012-08-13 | [14 empty] | 2012-10-15 | 2012-10-22 |  | Y
Central Hudson |  | Direct Energy Solar | CH-01042 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 6057 | Todd Hill | N |  | 7.31 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (34) | 2012-08-13 | 2012-08-13 | 0 | 2012-08-13 | [14 empty] | 2012-09-12 | 2012-09-17 |  | Y
Central Hudson |  | Sungevity Inc | CH-09381 | Newburgh | Wallkill | Ulster | 12589 | G | 5033 | Galeville | N |  | 3.6 | [13 empty] | NM | N | POWER ONE PVI-3.6 (1) | 2012-08-10 | 2012-08-16 | 4 | 2012-08-16 | [14 empty] | 2013-03-04 | 2013-03-08 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00971 | Newburgh | Wallkill | Ulster | 12589 | G | 5011 | Modena | N |  | 10.535 | [13 empty] | NM | N | Enphase M215 (49) | 2012-08-20 | 2012-08-20 | 0 | 2012-08-20 | [14 empty] | 2012-09-14 | 2012-09-18 |  | Y
Central Hudson |  | Direct Energy Solar | CH-01020 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 3.44 | [13 empty] | NM | N | Enphase M215 (16) | 2012-08-20 | 2012-08-20 | 0 | 2012-08-20 | [14 empty] | 2012-10-08 | 2012-10-15 |  | Y
Central Hudson |  | Sol Providers | CH-08968 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7042 | Staatsburg | N | CH-08946 | 1.29 | [13 empty] | NM | N | Enphase M215(6) | 2012-09-13 | 2012-09-14 | 1 | 2012-09-14 | [14 empty] | 2012-10-01 | 2012-10-08 |  | Y
Central Hudson |  | Sungevity Inc | CH-09502 | Newburgh | Cornwall Hdsn | Orange | 12520 | G | 4043 | Union Ave | N |  | 6.6 | [13 empty] | NM | N | POWER-ONE PVI-3.0 (1) & POWER-ONE PVI-3.6 (1) | 2012-08-13 | 2012-08-17 | 4 | 2012-08-17 | [14 empty] | 2013-03-19 | 2013-03-19 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03662 | Kingston | Kingston | Ulster | 12401 | G | 2094 | Hurley Ave | N |  | 4.085 | [13 empty] | NM | N | Enphase M215 (19) | 2012-08-14 | 2012-08-20 | 4 | 2012-08-20 | [14 empty] | 2012-10-24 | 2012-10-29 |  | Y
Central Hudson |  | SolarCity | CH-06284 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 5 | [13 empty] | NM | N | POWER-ONE AURORA PVI-5000 (1) | 2012-08-14 | 2012-08-20 | 4 | 2012-08-20 | [14 empty] | 2012-12-04 | 2012-12-11 |  | Y
Central Hudson |  | Sunrise Solar Solutions, LLC | CH-09658 | Catskill | Hunter | Greene | 12442 | E | 2081 | Hunter | N |  | 2.58 | [13 empty] | NM | N | Enphase M215 (12) | 2012-09-11 | 2012-09-11 | 0 | 2012-09-11 | [14 empty] | 2013-04-10 | 2013-04-16 |  | Y
Central Hudson |  | Kirchhoff Green Energy LLC | CH-03547 | Fishkill | Beacon | Dutchess | 12508 | G | 8085 | Tioronda | N |  | 13.975 | [13 empty] | NM | N | ENPHASE M215 (65) | 2012-08-22 | 2012-08-22 | 0 | 2012-08-22 | [14 empty] | 2012-12-14 | 2012-12-19 |  | Y
Central Hudson |  | D&M Alternative Energy | CH-00815 | Catskill | Coxsackie | Greene | 12051 | G | 1076 | Coxsackie | N |  | 2.5 | [13 empty] | NM | N | SMA SUNNY BOY 2500HF | 2012-08-21 | 2012-08-22 | 1 | 2012-08-22 | [14 empty] | 2012-09-05 | 2012-09-11 |  | Y
Central Hudson |  | Sungevity Inc | CH-09546 | Newburgh | Newburgh | Orange | 12550 | G | 4023 | Coldenham | N |  | 5 | [13 empty] | NM | N | POWER-ONE PVI-5000 | 2012-08-15 | 2012-08-22 | 5 | 2012-08-22 | [14 empty] | 2013-03-20 | 2013-03-26 |  | Y
Central Hudson |  | RGS Energy | CH-03036 | Poughkeepsie | Stanfordvl | Dutchess | 12581 | G | 7072 | Stanfordville | N |  | 7 | [13 empty] | NM | N | SMA Sunny Boy 7000 (1) | 2012-08-24 | 2012-08-24 | 0 | 2012-08-24 | [14 empty] | 2012-11-19 | 2012-11-27 |  | Y
Central Hudson |  | Hudson Valley Wind Energy, LLC | CH-02543 | Poughkeepsie | Millerton | Dutchess | 12546 | G | 7081 | Millerton | N |  |  |  | 10 | [11 empty] | NM | N | Diversified Technology Powersynch II AMFA-27 | 2012-09-05 | 2012-09-05 | 0 | 2012-09-05 | [14 empty] | 2012-09-10 | 2012-09-17 |  | Y
Central Hudson |  | Murphy Solar Power | CH-02735 | Catskill | Catskill | Greene | 12414 | G | 2006 | North Catskill | N |  | 3 | [13 empty] | NM | N | SMA Sunny Boy 3000 | 2012-08-27 | 2012-08-28 | 1 | 2012-08-28 | [14 empty] | 2012-09-06 | 2012-09-13 |  | Y
Central Hudson |  | Murphy Solar Power | CH-02754 | Catskill | Leeds | Greene | 12451 | G | 2005 | North Catskill | N |  | 3 | [13 empty] | NM | N | SMA Sunny Boy 3000 | 2012-08-17 | 2012-08-24 | 5 | 2012-08-24 | [14 empty] | 2012-09-26 | 2012-10-03 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | RGS Energy | CH-03000 | Kingston | Ellenvl | Ulster | 12428 | G | 396 | Clinton Ave | N |  | 48 | [13 empty] | NM | N | SMA Sunny Boy 8000 (6) | 2012-09-13 | 2012-09-14 | 1 | 2012-09-14 | [14 empty] | 2013-08-19 | 2013-08-29 |  | Y
Central Hudson |  | RGS Energy | CH-03033 | Poughkeepsie | Lagrangevl | Dutchess | 12540 | G | 6055 | Todd Hill | N | CH-03033 | 2.94 | [13 empty] | NM | N | Fronius IG Plus 3.0 | 2012-08-29 | 2012-08-30 | 1 | 2012-08-30 | [14 empty] | 2012-11-26 | 2012-11-26 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00842 | Kingston | Saugerties | Ulster | 12477 | G | 3003 | Saugerties | N |  | 7.955 | [13 empty] | NM | N | Enphase M215 (37) | 2012-09-12 | 2012-09-13 | 1 | 2012-09-13 | [14 empty] | 2012-10-17 | 2012-10-24 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00911 | Kingston | Saugerties | Ulster | 12477 | G | 3004 | Saugerties | N |  | 7.74 | [13 empty] | NM | N | Enphase M215 (36) | 2012-08-23 | 2012-08-28 | 3 | 2012-08-28 | [14 empty] | 2012-10-10 | 2012-10-16 |  | Y
Central Hudson |  | SolarCity | CH-05047 | Fishkill | Hughsonvl |  | 12537 | G | 8052 | North Chelsea | TBD |  | 6 | [13 empty] | NM | N | POWER-ONE AURORA PVI-6000 | 2012-08-23 | 2012-08-28 | 3 | 2012-08-28 | [17 empty] | W
Central Hudson |  | SolarCity | CH-06404 | Newburgh | Rock Tvrn | Orange | 12575 | G | 4097 | Bethlehem Rd | N |  | 7.2 | [13 empty] | NM | N | FRONIUS IG PLUS V 7.5 | 2012-08-23 | 2012-08-27 | 2 | 2012-08-27 | [14 empty] | 2012-10-17 | 2012-10-24 |  | Y
Central Hudson |  | Allura Solar | CH-00644 | Catskill | Hannacroix | Greene | 12087 | G | 1083 | New Baltimore | N |  | 6.45 | [13 empty] | NM | N | Enphase M215 (30) | 2012-09-14 | 2012-09-14 | 0 | 2012-09-14 | [14 empty] | 2012-10-18 | 2012-10-25 |  | Y
Central Hudson |  | SolarCity | CH-05093 | Kingston | Woodstock | Ulster | 12498 | G | 3012 | Woodstock | N |  | 7.92 | [13 empty] | NM | N | FRONIUS IG PLUS V 10.0 | 2012-08-28 | 2012-09-04 | 4 | 2012-09-04 | [14 empty] | 2013-12-30 | 2013-12-31 |  | Y
Central Hudson |  | SolarCity | CH-05822 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6061 | Inwood Ave | N |  | 8 | [13 empty] | NM | N | Power-One Aurora PVI 5000 (1) & Power-One PVI Aurora 3.0 (1) | 2012-09-05 | 2012-09-05 | 0 | 2012-09-05 | [14 empty] | 2013-01-10 | 2013-01-14 |  | Y
Central Hudson |  | SolarCity | CH-05963 | Poughkeepsie | Tivoli | Dutchess | 12583 | G | 7062 | Milan | N |  | 11 | [13 empty] | NM | N | SMA SUNNY BOY 6000-US (1) & SMA SUNNY BOY 5000-US (1) | 2012-08-28 | 2012-09-04 | 4 | 2012-09-04 | [14 empty] | 2012-11-02 | 2012-11-12 |  | Y |  | 10/29/12 - HURRICANE SANDY.
Central Hudson |  | SolarCity | CH-06592 | Kingston | Kingston | Ulster | 12401 | G | 1021 | East Kingston | N |  | 3 | [13 empty] | NM | N | FRONIUS IG 3000 | 2012-09-19 | 2012-09-20 | 1 | 2012-09-20 | [14 empty] | 2012-11-27 | 2012-12-04 |  | W
Central Hudson |  | SolarCity | CH-06805 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8043 | Myers Corners | N | CH-06805 | 9.6 | [13 empty] | NM | N | POWER-ONE AURORA PVI-6000 & POWER-ONE AURORA PVI-3.6 | 2012-10-29 | 2012-11-08 | 8 | 2012-11-08 | [14 empty] | 2013-03-06 | 2013-03-13 |  | Y |  | 10/29/12 - HURRICANE SANDY.
Central Hudson |  | SolarCity | CH-07291 | Poughkeepsie | Clinton Corners | Dutchess | 12514 | G | 7013 | Hibernia | N |  | 6 | [13 empty] | NM | N | POWER-ONE AURORA PVI-6000 | 2012-08-28 | 2012-09-04 | 4 | 2012-09-04 | [14 empty] | 2012-12-06 | 2012-12-12 |  | Y
Central Hudson |  | East Coast Alternative Energy | CH-01088 | Newburgh | New Windsor | Orange | 12553 | G | 4046 | Union Ave | N |  | 5.16 | [13 empty] | NM | N | Enphase M215 (24) | 2012-09-05 | 2012-09-05 | 0 | 2012-09-05 | [14 empty] | 2012-12-14 | 2012-12-20 |  | Y
Central Hudson |  | SolarCity | CH-07820 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8071 | Shenandoah | N | CH-09060 | 3.6 | [13 empty] | NM | N | POWER-ONE AURORA PVI-3.8 | 2012-10-03 | 2012-10-04 | 1 | 2012-10-04 | [14 empty] | 2012-11-28 | 2012-12-05 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03830 | Newburgh | New Paltz | Ulster | 12561 | G | 5031 | Galeville | N | CH-03570 | 6 | [13 empty] | NM | N | POWER ONE AURORA PVI-6000 | 2012-09-13 | 2012-09-14 | 1 | 2012-09-14 | [14 empty] | 2012-10-23 | 2012-10-23 |  | W
Central Hudson |  | Direct Energy Solar | CH-00896 | Kingston | Hurley | Ulster | 12443 | G | 2094 | Hurley Ave | N |  | 5.375 | [13 empty] | NM | N | Enphase M215 (25) | 2012-09-04 | 2012-09-10 | 4 | 2012-09-10 | [14 empty] | 2012-10-10 | 2012-10-16 |  | Y
Central Hudson |  | Murphy Solar Power | CH-02755 | Catskill | Catskill | Greene | 12414 | G | 2006 | North Catskill | N |  | 3 | [13 empty] | NM | N | SMA Sunny Boy 3000 | 2012-09-04 | 2012-09-11 | 5 | 2012-09-11 | [14 empty] | 2012-09-26 | 2012-10-03 |  | Y
Central Hudson |  | Murphy Solar Power | CH-02719 | Catskill | Leeds | Greene | 12451 | G | 2005 | North Catskill | N |  | 5 | [13 empty] | NM | N | SMA Sunny Boy 5000 | 2012-09-06 | 2012-09-13 | 5 | 2012-09-13 | [14 empty] | 2012-10-15 | 2012-10-22 |  | Y
Central Hudson |  | Ross Solar Group | CH-02990 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7053 | Rhinebeck | N |  | 51.982 | [13 empty] | NM | N | Fronius IG Plus 11.4 (4) & Fronius IG Plus 6.5 (1) | 2012-09-26 | 2012-10-02 | 4 | 2012-10-02 | [8 empty] | 4335 | 2760 |  |  |  |  | 2013-05-08 | 2013-05-14 |  | Y
Central Hudson |  | Murphy Solar Power | CH-02736 | Catskill | Catskill | Greene | 12414 | G | 2006 | North Catskill | N |  | 3 | [13 empty] | NM | N | SMA Sunny Boy 3000 | 2012-09-12 | 2012-09-17 | 3 | 2012-09-17 | [14 empty] | 2012-09-26 | 2012-10-03 |  | Y
Central Hudson |  | Sol Providers | CH-08905 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 6051 | Todd Hill | N |  | 8.6 | [13 empty] | RNM | N | Enphase M215 (40) | 2012-09-18 | 2012-09-18 | 0 | 2012-09-18 | [14 empty] | 2012-11-20 | 2012-11-29 |  | Y
Central Hudson |  | Hudson Solar | CH-01261 | Catskill | Westerlo | Albany | 12193 | G | 1091 | Westerlo | N |  | 9.2 | [13 empty] | NM | N | POWERONE PVI-5000 (1) & POWERONE PVI-4.2 (1) | 2012-09-18 | 2012-09-19 | 1 | 2012-09-19 | [14 empty] | 2013-02-25 | 2013-03-04 |  | Y
Central Hudson |  | Hudson Solar | CH-02331 | Catskill | Westerlo |  | 12193 | G | 1091 | Westerlo | TBD |  | 9.2 | [13 empty] | NM | N | POWERONE PVI-5000 (1) & POWERONE PVI-4.2 (1) | 2012-09-18 | 2012-09-19 | 1 | 2012-09-19 | [15 empty] | 2013-03-04 |  | W |  | Customer already had net meter prior to application.
Central Hudson |  | Sol Providers | CH-08963 | Poughkeepsie | Millerton | Dutchess | 12546 | G | 7081 | Millerton | N |  | 7.425 | [13 empty] | NM | N | SUNPOWER E19/240 Integrated w/ SOLARBRIDGE P235HV-240 micro inverters (33) | 2012-09-25 | 2012-10-01 | 4 | 2012-10-01 | [14 empty] | 2012-11-30 | 2012-12-12 |  | Y
Central Hudson |  | Hudson Solar | CH-01266 | Catskill | Athens | Greene | 12015 | G | 2002 | North Catskill | N |  | 9.6 | [13 empty] | NM | N | POWERONE PVI-6000 (1) & POWERONE PVI-3.6 (1) | 2012-09-14 | 2012-09-21 | 5 | 2012-09-21 | [14 empty] | 2013-03-22 | 2013-04-01 |  | Y
Central Hudson |  | Hudson Solar | CH-01396 | Fishkill | Cold Spg | Putnam | 10516 | G | 8086 | Tioronda | N |  | 5 | [13 empty] | NM | N | POWERONE PVI-5000 | 2012-09-14 | 2012-09-20 | 4 | 2012-09-20 | [14 empty] | 2012-12-20 | 2012-12-21 |  | Y
Central Hudson |  | Hudson Solar | CH-01427 | Newburgh | New Paltz | Ulster | 12561 | G | 5011 | Modena | N |  | 10 | [13 empty] | NM | N | PowerOne PVI 5000 (2) | 2012-09-20 | 2012-09-20 | 0 | 2012-09-20 | [14 empty] | 2013-02-07 | 2013-02-14 |  | Y
Central Hudson |  | Hudson Solar | CH-01488 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 7024 | Tinkertown | N |  | 6.88 | [13 empty] | NM | N | Enphase M215 (32) | 2012-09-24 | 2012-10-01 | 5 | 2012-10-01 | [14 empty] | 2012-11-13 | 2012-11-20 |  | Y
Central Hudson |  | Hudson Solar | CH-01597 | Catskill | Palenvl | Greene | 12463 | G | 2042 | South Cairo | N |  | 10 | [13 empty] | NM | N | POWERONE PVI-5000 (2) | 2012-09-14 | 2012-09-21 | 5 | 2012-09-21 | [14 empty] | 2013-02-08 | 2013-02-15 |  | Y
Central Hudson |  | Hudson Solar | CH-02255 | Poughkeepsie | Poughkeepsie |  | 12601 | G | 6065 | Inwood Ave | TBD |  | 4.905 | [13 empty] | NM | N | POWERONE PVI-5000 | 2012-09-14 | 2012-09-21 | 5 | 2012-09-21 | [17 empty] | W
Central Hudson |  | Hudson Solar | CH-02291 | Poughkeepsie | Millerton | Dutchess | 12546 | G | 7081 | Millerton | N |  | 10 | [13 empty] | NM | N | POWERONE PVI-5000(2) | 2012-09-14 | 2012-09-21 | 5 | 2012-09-21 | [14 empty] | 2013-05-14 | 2013-05-21 |  | Y
Central Hudson |  | Hudson Solar | CH-02433 | Kingston | W Hurley | Ulster | 12491 | G | 2094 | Hurley Ave | N | CH-01662 | 6 | [13 empty] | NM | N | POWERONE PVI-6000 | 2012-09-14 | 2012-09-20 | 4 | 2012-09-20 | [14 empty] | 2012-12-20 | 2012-12-21 |  | Y
Central Hudson |  | SolarCity | CH-05811 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6046 | Spackenkill | N |  | 6 | [13 empty] | NM | N | SMA SOLAREDGE SE6000 | 2012-09-24 | 2012-09-24 | 0 | 2012-09-24 | [14 empty] | 2012-12-17 | 2012-12-19 |  | Y
Central Hudson |  | SolarCity | CH-06962 | Newburgh | New Paltz | Ulster | 12561 | G | 5024 | Ohioville | N |  | 6 | [13 empty] | NM | N | POWER-ONE AURORA PVI 6000 | 2012-09-17 | 2012-09-24 | 5 | 2012-09-24 | [14 empty] | 2012-12-21 | 2012-12-21 |  | Y
Central Hudson |  | SolarCity | CH-07003 | Newburgh | Newburgh | Orange | 12550 | G | 4012 | West Balmville | N |  | 5 | [13 empty] | NM | N | SMA SUNNY BOY 5000 | 2012-09-17 | 2012-09-21 | 4 | 2012-09-21 | [14 empty] | 2012-11-09 | 2012-11-15 |  | Y
Central Hudson |  | SolarCity | CH-07308 | Poughkeepsie | Pleasant Valley | Dutchess | 12569 | G | 7024 | Tinkertown | N |  | 5 | [13 empty] | NM | N | POWER-ONE AURORA PVI 5000 | 2012-09-17 | 2012-09-21 | 4 | 2012-09-21 | [14 empty] | 2013-05-23 | 2013-05-29 |  | Y
Central Hudson |  | SolarCity | CH-05083 | Newburgh | Wallkill | Ulster | 12589 | G | 5041 | East Walden | N |  | 9 | [13 empty] | NM | N | SMA SUNNY BOY 6000 (1) & SMA SUNNY BOY 3000 | 2012-09-25 | 2012-09-25 | 0 | 2012-09-25 | [8 empty] | 350 | 350 |  |  |  |  | 2013-01-03 | 2013-01-03 |  | Y
Central Hudson |  | SolarCity | CH-05718 | Kingston | Saugerties | Ulster | 12477 | G | 3002 | Saugerties | N |  | 3.8 | [13 empty] | NM | N | SOLAREDGE SE3800 | 2012-09-27 | 2012-10-04 | 5 | 2012-10-04 | [14 empty] | 2012-11-21 | 2012-11-26 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03595 | Newburgh | Newburgh | Orange | 12550 | G | 4015 | West Balmville | N |  | 20 | [13 empty] | NM | N | POWER ONE AURORA PVI 10.0 (2) | 2012-09-20 | 2012-09-26 | 4 | 2012-09-26 | [14 empty] | 2013-04-10 | 2013-04-17 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03596 | Newburgh | Newburgh | Orange | 12550 | G | 4015 | West Balmville | N |  | 30 | [13 empty] | NM | N | POWER-ONE AURORA PVI 10.0 (3) | 2012-09-27 | 2012-09-27 | 0 | 2012-09-27 | [14 empty] | 2013-04-10 | 2013-04-17 |  | Y
Central Hudson |  | Endless Mtn Solar Services | CH-01107 | Fishkill | Beacon | Dutchess | 12508 | G | 8087 | Tioronda | N |  | 6.02 | [13 empty] | NM | N | Enphase M215 (28) | 2012-10-01 | 2012-10-05 | 4 | 2012-10-05 | [14 empty] | 2013-07-08 | 2013-07-09 |  | Y
Central Hudson |  | Sunrise Solar Solutions, LLC | CH-09666 | Newburgh | Cornwall | Orange | 12518 | G | 4041 | Union Ave | N | CH-09666 | 10.35 | [13 empty] | NM | N | SUNPOWER E19/240 Integrated w/ SOLARBRIDGE P235HV-240 micro inverters (46) | 2012-10-01 | 2012-10-01 | 0 | 2012-10-01 | [14 empty] | 2013-01-15 | 2013-01-21 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00868 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8095 | Fishkill Plains | N |  | 10.75 | [13 empty] | NM | N | ENPHASE M215 (50) | 2012-09-26 | 2012-10-02 | 4 | 2012-10-02 | [14 empty] | 2012-11-19 | 2012-11-27 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00905 | Kingston | Grahamsvl | Sullivan | 12740 | G | 3091 | Neversink | N | CH-00905 | 9.46 | [13 empty] | NM | N | ENPHASE M215 (44) | 2012-09-26 | 2012-10-02 | 4 | 2012-10-02 | [8 empty] | 350 | 350 |  |  |  |  | 2012-11-27 | 2012-12-05 |  | Y
Central Hudson |  | Murphy Solar Power | CH-02727 | Catskill | E Durham | Greene | 12423 | G | 1092 | Westerlo | N |  | 3 | [13 empty] | NM | N | SMA Sunny Boy 3000 | 2012-09-26 | 2012-10-03 | 5 | 2012-10-03 | [14 empty] | 2012-11-05 | 2012-11-12 |  | Y
Central Hudson |  | Self | CH-08872 | Kingston | Saugerties | Ulster | 12477 | G | 3002 | Saugerties | N |  | 12.9 | [13 empty] | NM | N | Enphase M215 (60) | 2012-10-03 | 2012-10-03 | 0 | 2012-10-03 | [8 empty] | 350 | 350 |  |  |  |  | 2013-03-24 | 2013-04-02 |  | Y
Central Hudson |  | RGS Energy | CH-03057 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7061 | Milan | N | CH-03057 | 6 | [13 empty] | NM | N | SMA SUNNY BOY 6000 | 2012-10-05 | 2012-10-11 | 4 | 2012-10-11 | [14 empty] | 2013-03-01 | 2013-03-08 |  | Y
Central Hudson |  | Lotus Energy Inc. | CH-03880 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7061 | Milan | N |  | 12 | [13 empty] | NM | N | SUNPOWER SPR 6000 (2) | 2012-10-04 | 2012-10-04 | 0 | 2012-10-04 | [14 empty] | 2013-02-14 | 2013-02-22 |  | Y
Central Hudson |  | SolarCity | CH-06412 | Newburgh | Montgomery | Orange | 12549 | G | 5073 | Montgomery | N |  | 6 | [13 empty] | NM | N | POWER-ONE AURORA PVI-6000 | 2012-09-28 | 2012-10-05 | 5 | 2012-10-05 | [14 empty] | 2013-02-08 | 2013-02-15 |  | Y
Central Hudson |  | CNR Energy Solutions, LLC | CH-00773 | Newburgh | Highland | Ulster | 12528 | G | 5082 | Highland | N |  | 6.02 | [13 empty] | NM | N | Enphase M215 (28) | 2012-10-02 | 2012-10-09 | 5 | 2012-10-09 | [14 empty] | 2012-12-13 | 2012-12-17 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00999 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6052 | Todd Hill | N |  | 8.6 | [13 empty] | NM | N | ENPHASE M215 (40) | 2012-10-10 | 2012-10-15 | 3 | 2012-10-15 | [14 empty] | 2012-11-27 | 2012-11-27 |  | Y
Central Hudson |  | SolarCity | CH-05418 | Newburgh | Highland | Ulster | 12528 | G | 5024 | Ohioville | N |  | 7 | [13 empty] | NM | N | SMA SUNNY BOY 7000 | 2012-10-02 | 2012-10-09 | 5 | 2012-10-09 | [14 empty] | 2012-11-27 | 2012-12-04 |  | Y
Central Hudson |  | SolarCity | CH-06454 | Catskill | Catskill |  | 12414 | G | 2005 | North Catskill | TBD |  | 4.8 | [13 empty] | NM | N | POWER-ONE AURORA PVI-5000 | 2012-10-02 | 2012-10-09 | 5 | 2012-10-09 | [17 empty] | W |  | Customer already had net meter prior to application. 09/30/14 Project abandoned as per customer.
Central Hudson |  | SolarCity | CH-07115 | Newburgh | New Windsor | Orange | 12553 | G | 4095 | Bethlehem Rd | N |  | 7.44 | [13 empty] | NM | N | SOLAREDGE SE5000A (1) & SOLAREDGE SE3000A (1) | 2012-10-02 | 2012-10-09 | 5 | 2012-10-09 | [14 empty] | 2012-12-04 | 2012-12-11 |  | Y
Central Hudson |  | SolarCity | CH-07298 | Poughkeepsie | Lagrangevl | Dutchess | 12540 | G | 6053 | Todd Hill | N |  | 5 | [13 empty] | NM | N | POWER-ONE AURORA PVI-5000 | 2012-10-02 | 2012-10-09 | 5 | 2012-10-09 | [14 empty] | 2012-12-21 | 2012-12-21 |  | Y
Central Hudson |  | SolarCity | CH-07693 | Kingston | High Fls |  | 12440 | G | 3022 | High Falls | N |  | 3.8 | [13 empty] | NM | N | SOLAREDGE SE3800A | 2012-11-27 | 2012-12-05 | 6 | 2012-12-05 | [14 empty] | 2013-02-19 | 2013-02-26 |  | W
Central Hudson |  | Sungevity Inc | CH-09406 | Kingston | Accord | Ulster | 12404 | G | 3024 | High Falls | N |  | 12 | [13 empty] | NM | N | Power One PVI 6000 (2) | 2012-10-02 | 2012-10-09 | 5 | 2012-10-09 | [14 empty] | 2013-04-05 | 2013-04-12 |  | Y
Central Hudson |  | RGS Energy | CH-03059 | Catskill | Medusa | Albany | 12120 | G | 1092 | Westerlo | N | CH-03014 | 2.07 | [13 empty] | NM | N | SunPower SPR 6000 | 2012-10-10 | 2012-10-10 | 0 | 2012-10-10 | [14 empty] | 2013-03-08 | 2013-03-15 |  | Y
Central Hudson |  | Sol Providers | CH-08921 | Poughkeepsie | Lagrangevl | Dutchess | 12540 | G | 6057 | Todd Hill | N | CH-08921 | 4.515 | [13 empty] | NM | N | Enphase M215 (21) | 2012-10-05 | 2012-10-11 | 4 | 2012-10-11 | [14 empty] | 2012-12-21 | 2012-12-21 |  | W
Central Hudson |  | Direct Energy Solar | CH-00877 | Newburgh | New Paltz | Ulster | 12561 | G | 5011 | Modena | N |  | 10.105 | [13 empty] | NM | N | Enphase M215 (47) | 2012-10-08 | 2012-10-12 | 4 | 2012-10-12 | [14 empty] | 2012-12-13 | 2012-12-13 |  | Y
Central Hudson |  | Direct Energy Solar | CH-01046 | Newburgh | Cornwall-Hdsn | Orange | 12520 | G | 4043 | Union Ave | N |  | 8.6 | [13 empty] | NM | N | Enphase M215 (40) | 2012-10-15 | 2012-10-15 | 0 | 2012-10-15 | [14 empty] | 2012-11-19 | 2012-11-27 |  | Y
Central Hudson |  | Endless Mtn Solar Services | CH-01108 | Kingston | Greenfield Pk | Ulster | 12435 | G | 3096 | Grimley Rd | N | CH-01108 | 4.085 | [13 empty] | NM | N | Enphase M215 (19) | 2012-10-22 | 2012-10-26 | 4 | 2012-10-26 | [14 empty] | 2012-12-04 | 2012-12-11 |  | Y
Central Hudson |  | Gould Erectors | CH-01150 | Catskill | Rensselaervl | Albany | 12147 | G | 1092 | Westerlo | N |  | 5.76 | [13 empty] | NM | N | SolarEdge SE6000 | 2012-10-17 | 2012-10-17 | 0 | 2012-10-17 | [14 empty] | 2012-11-06 | 2012-11-09 |  | Y
Central Hudson |  | Mercury Solar Systems | CH-02632 | Newburgh | Newburgh |  | 12550 | G | 4051 | Union Ave | TBD |  | 583 | [13 empty] | NM | N | Advanced Energy Solaron 250 (1) & Advanced Energy Solaron 333 (1) | 2012-10-25 | 2012-11-20 | 18 | 2012-11-20 | [9 empty] | 7633 | [7 empty] | W |  | 10/18/12 Incomplete issued. System determined eligible for fast track process during preliminary review Section C, Step 4. Completion delayed due to HURRICANE SANDY emergency restoration. 3/8/13 Received email from customer that project is abandoned.
Central Hudson |  | SolarCity | CH-05413 | Catskill | Hannacroix | Greene | 12087 | G | 2061 | Freehold | N |  | 12 | [13 empty] | NM | N | POWER-ONE AURORA PVI-6000 (2) | 2012-10-11 | 2012-10-18 | 5 | 2012-10-18 | [14 empty] | 2013-01-30 | 2013-01-30 |  | Y
Central Hudson |  | Murphy Solar Power | CH-02725 | Catskill | E Durham | Greene | 12423 | G | 1092 | Westerlo | N |  | 3 | [13 empty] | NM | N | SMA Sunny Boy 3000 | 2012-10-22 | 2012-10-26 | 4 | 2012-10-26 | [14 empty] | 2012-11-05 | 2012-11-12 |  | Y
Central Hudson |  | SolarCity | CH-05247 | Kingston | Saugerties | Ulster | 12477 | G | 3001 | Saugerties | N |  | 6 | [13 empty] | NM | N | POWER-ONE AURORA PVI-6000 | 2012-10-15 | 2012-10-22 | 5 | 2012-10-22 | [14 empty] | 2013-01-31 | 2013-01-31 |  | Y
Central Hudson |  | SolarCity | CH-05266 | Newburgh | Highland | Ulster | 12528 | G | 5081 | Highland | N |  | 3.8 | [13 empty] | NM | N | Power One PVI 3.8 | 2012-10-15 | 2012-10-22 | 5 | 2012-10-22 | [14 empty] | 2013-03-04 | 2013-03-11 |  | Y
Central Hudson |  | SolarCity | CH-05648 | Kingston | High Fls | Ulster | 12440 | G | 3024 | High Falls | N |  | 7.44 | [13 empty] | NM | N | SUNNY BOY 6000 (1) & SUNNY BOY 3000 (1) | 2012-10-15 | 2012-10-22 | 5 | 2012-10-22 | [14 empty] | 2013-01-22 | 2013-01-29 |  | Y
Central Hudson |  | SolarCity | CH-05759 | Kingston | Kingston | Ulster | 12401 | G | 2016 | Lincoln Park | N | CH-05759 | 7 | [13 empty] | NM | N | SMA SUNNY BOY 7000 | 2012-10-15 | 2012-10-22 | 5 | 2012-10-22 | [14 empty] | 2012-12-27 | 2012-12-31 |  | Y
Central Hudson |  | SolarCity | CH-06007 | Fishkill | Wappingers Falls | Dutchess | 12590 | G | 8091 | Fishkill Plains | N | CH-06007 | 6 | [13 empty] | NM | N | POWER-ONE AURORA PVI-6000 | 2012-10-15 | 2012-10-19 | 4 | 2012-10-19 | [14 empty] | 2013-01-24 | 2013-01-29 |  | Y
Central Hudson |  | SolarCity | CH-06331 | Newburgh | Marlboro | Ulster | 12542 | G | 5003 | Marlboro | N |  | 6.8 | [13 empty] | NM | N | SOLAREDGE SE3800A (1) & SOLAREDGE SE3000A (1) | 2012-10-15 | 2012-10-22 | 5 | 2012-10-22 | [14 empty] | 2012-12-13 | 2012-12-19 |  | Y
Central Hudson |  | SolarCity | CH-06467 | Catskill | Coxsackie | Greene | 12051 | G | 1074 | Coxsackie | N |  | 22.8 | [13 empty] | NM | N | Fronius IG Plus V 11.4 (2) | 2012-10-15 | 2012-10-23 | 6 | 2012-10-23 | [8 empty] | 350 | 350 |  |  |  |  | 2013-11-21 | 2013-11-21 |  | Y
Central Hudson |  | Solar Generation | CH-08283 | Kingston | Glenford | Ulster | 12433 | G | 3013 | Woodstock | N |  | 11.4 | [13 empty] | NM | N | SUNPOWER SPR 11400 | 2012-10-15 | 2012-10-22 | 5 | 2012-10-22 | [14 empty] | 2013-02-28 | 2013-02-28 |  | Y
Central Hudson |  | RGS Energy | CH-03046 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7054 | Rhinebeck | N |  | 175 | [13 empty] | NM | N | SATCON PVS-75 (1) & SATCON PVS-100 (1) | 2012-10-30 | 2012-11-09 | 8 | 2012-11-09 | [14 empty] | 2013-01-21 | 2013-01-29 |  | Y |  | 10/29/12 - HURRICANE SANDY.
Central Hudson |  | SolarCity | CH-05004 | Kingston | Saugerties | Ulster | 12477 | G | 3002 | Saugerties | N |  | 7.2 | [13 empty] | NM | N | POWER-ONE AURORA PVI-4.2 (1) & POWER-ONE AURORA PVI-3.0 (1) | 2012-10-18 | 2012-10-24 | 4 | 2012-10-24 | [14 empty] | 2013-02-05 | 2013-02-12 |  | Y
Central Hudson |  | SolarCity | CH-07730 | Kingston | Kingston | Ulster | 12401 | G | 1011 | Boulevard | N |  | 6 | [13 empty] | NM | N | POWER-ONE AURORA PVI-6000 | 2012-10-18 | 2012-10-24 | 4 | 2012-10-24 | [14 empty] | 2013-01-29 | 2013-01-31 |  | Y
Central Hudson |  | Solar Alchemy | CH-08991 | Kingston | Saugerties | Ulster | 12477 | G | 3001 | Saugerties | N |  | 6.02 | [13 empty] | NM | N | Enphase M215 (28) | 2012-10-25 | 2012-10-25 | 0 | 2012-10-25 | [14 empty] | 2013-04-09 | 2013-04-09 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00928 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6093 | Manchester | N |  | 4.515 | [13 empty] | NM | N | Enphase M215 (21) | 2012-10-22 | 2012-10-26 | 4 | 2012-10-26 | [14 empty] | 2012-11-20 | 2012-11-29 |  | Y
Central Hudson |  | Hudson Solar | CH-02120 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7056 | Rhinebeck | N |  | 6 | [13 empty] | NM | N | POWERONE PVI-6000 | 2012-10-22 | 2012-10-26 | 4 | 2012-10-26 | [14 empty] | 2012-12-18 | 2012-12-21 |  | Y
Central Hudson |  | Hudson Solar | CH-02171 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8095 | Fishkill Plains | N | CH-02171 | 6 | [13 empty] | NM | N | POWERONE PVI-6000 | 2012-10-22 | 2012-10-29 | 5 | 2012-10-29 | [14 empty] | 2012-12-14 | 2012-12-19 |  | Y
Central Hudson |  | Hudson Solar | CH-02489 | Newburgh | Gardiner | Ulster | 12525 | G | 5031 | Galeville | N | CH-01580 | 2.289 | [13 empty] | NM | N | POWERONE PVI-3.0 | 2012-10-29 | 2012-11-08 | 8 | 2012-11-08 | [14 empty] | 2012-12-13 | 2012-12-18 |  | Y |  | 10/29/12 - HURRICANE SANDY.
Central Hudson |  | SolarCity | CH-05458 | Newburgh | Marlboro | Ulster | 12542 | G | 5004 | Marlboro | N |  | 4.2 | [13 empty] | NM | N | POWER-ONE PVI-4.2 | 2012-10-22 | 2012-10-29 | 5 | 2012-10-29 | [14 empty] | 2012-12-31 | 2012-12-31 |  | Y
Central Hudson |  | SolarCity | CH-05753 | Kingston | Lk Katrine | Ulster | 12449 | G | 2011 | Lincoln Park | N |  | 5 | [13 empty] | NM | N | POWER ONE AUROA PVI-5000 | 2012-10-23 | 2012-10-29 | 4 | 2012-10-29 | [14 empty] | 2012-12-17 | 2012-12-20 |  | Y
Central Hudson |  | SolarCity | CH-05774 | Kingston | Lk Katrine | Ulster | 12449 | G | 2016 | Lincoln Park | N |  | 9.6 | [13 empty] | NM | N | FRONIUS IG PLUS V 10.0 | 2012-10-23 | 2012-10-29 | 4 | 2012-10-29 | [14 empty] | 2013-01-22 | 2013-01-29 |  | Y
Central Hudson |  | Endless Mtn Solar Services | CH-01111 | Fishkill | Beacon | Dutchess | 12508 | G | 8087 | Tioronda | N |  | 2.15 | [13 empty] | NM | N | Enphase M215 (10) | 2012-10-24 | 2012-10-29 | 3 | 2012-10-29 | [14 empty] | 2013-07-09 | 2013-07-16 |  | Y
Central Hudson |  | SolarCity | CH-05516 | Catskill | Cairo | Greene | 12413 | G | 2041 | South Cairo | N |  | 12 | [13 empty] | NM | N | SMA SUNNY BOY 7000 (1) & SMA SUNNY BOY 5000 (1) | 2012-10-25 | 2012-10-29 | 2 | 2012-10-29 | [8 empty] | 350 | 350 |  |  |  |  | 2013-02-06 | 2013-02-06 |  | Y
Central Hudson |  | Solar Generation | CH-08232 | Kingston | Mt Tremper | Ulster | 12457 | G | 3012 | Woodstock | Y |  | 4.5 | 4.5 | [12 empty] | NM | N | XANTREX XW45481XantrexXW4548 (DC) | 2012-10-25 | 2012-11-07 | 9 | 2012-11-07 | [14 empty] | 2013-01-16 | 2013-01-21 |  | Y
Central Hudson |  | Sol Providers | CH-08932 | Fishkill | Garrison | Putnam | 10524 | G | 8066 | Merritt Park | N |  | 3.375 | [13 empty] | NM | N | SUNPOWER E19/240 Integrated w/ SOLARBRIDGE P235HV-240 micro inverters (15) | 2012-10-30 | 2012-11-05 | 4 | 2012-11-05 | [14 empty] | 2013-03-08 | 2013-03-15 |  | Y
Central Hudson |  | Sol Providers | CH-08953 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8045 | Myers Corners | N |  | 2.7 | [13 empty] | NM | N | SUNPOWER E19/240 Integrated w/ SOLARBRIDGE P235HV-240 micro inverters (12) | 2012-10-30 | 2012-11-05 | 4 | 2012-11-05 | [14 empty] | 2012-12-14 | 2012-12-19 |  | Y
Central Hudson |  | SolarCity | CH-06879 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8092 | Fishkill Plains | N |  | 6 | [13 empty] | NM | N | POWER-ONE AURORA PVI-6000 | 2012-10-26 | 2012-11-05 | 6 | 2012-11-05 | [14 empty] | 2013-02-21 | 2013-02-28 |  | Y
Central Hudson |  | RGS Energy | CH-02997 | Catskill | Greenvl | Greene | 12083 | G | 1091 | Westerlo | N |  | 7.5 | [13 empty] | NM | N | Fronius IG Plus 7.5 | 2012-12-04 | 2012-12-05 | 1 | 2012-12-05 | [14 empty] | 2013-03-21 | 2013-03-21 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03677 | Fishkill | Stormvl | Dutchess | 12582 | G | 8071 | Shenandoah | N |  | 8.4 | [13 empty] | NM | N | POWER ONE AURORA PVI 4.2 (2) | 2012-10-29 | 2012-11-08 | 8 | 2012-11-08 | [14 empty] | 2013-02-28 | 2013-03-07 |  | Y
Central Hudson |  | SolarCity | CH-05007 | Kingston | Saugerties | Ulster | 12477 | G | 3004 | Saugerties | N |  | 7.2 | [13 empty] | NM | N | POWER-ONE AURORA PVI-4.2 (1) & POWER-ONE AURORA PVI-3.0 (1) | 2012-10-29 | 2012-11-07 | 7 | 2012-11-07 | [14 empty] | 2013-03-04 | 2013-03-04 |  | Y
Central Hudson |  | Finlo Solar Powers | CH-01127 | Poughkeepsie | Poughkeepsie |  | 12603 | G | 6044 | Spackenkill | N |  | 4.3 | [13 empty] | NM | N | ENPHASE M215 (20) | 2013-01-22 | 2013-01-24 | 2 | 2013-01-24 | [14 empty] | 2013-06-13 | 2013-06-20 |  | W
Central Hudson |  | Solar Generation | CH-08121 | Kingston | Hurley | Ulster | 12443 | G | 2094 | Hurley Ave | N |  | 7 | [13 empty] | NM | N | SMA SB7000US | 2012-10-31 | 2012-11-09 | 7 | 2012-11-09 | [14 empty] | 2012-12-17 | 2012-12-20 |  | Y
Central Hudson |  | Hudson Solar | CH-01803 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6056 | Todd Hill | N |  | 4.2 | [13 empty] | NM | N | POWERONE PVI-4.2 | 2012-11-01 | 2012-11-09 | 6 | 2012-11-09 | [14 empty] | 2012-12-18 | 2012-12-21 |  | Y
Central Hudson |  | SolarCity | CH-07485 | Catskill | Jewett | Greene | 12444 | E | 2081 | Hunter | N |  | 1.72 | [13 empty] | NM | N | POWER ONE PVI-3.0 | 2012-11-06 | 2012-11-13 | 5 | 2012-11-13 | [14 empty] | 2013-01-24 | 2013-01-31 |  | Y
Central Hudson |  | Direct Energy Solar | CH-01003 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7051 | Rhinebeck | N |  | 5.805 | [13 empty] | NM | N | Enphase M215 (27) | 2012-11-07 | 2012-11-13 | 4 | 2012-11-13 | [14 empty] | 2013-06-17 | 2013-06-24 |  | Y
Central Hudson |  | Direct Energy Solar | CH-01023 | Newburgh | Wallkill |  | 12589 | G | 5043 | East Walden | TBD |  | 7.955 | [13 empty] | NM | N | Enphase M215 (37) | 2012-11-07 | 2012-11-13 | 4 | 2012-11-13 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | Solar Generation | CH-08235 | Kingston | Willow | Ulster | 12495 | G | 3012 | Woodstock | N |  | 5.76 | [13 empty] | NM | N | SMA Sunny Boy 6000 | 2012-11-07 | 2012-11-14 | 5 | 2012-11-14 | [14 empty] | 2013-02-26 | 2013-03-05 |  | Y
Central Hudson |  | Hudson Solar | CH-01634 | Catskill | Coxsackie | Greene | 12051 | G | 1074 | Coxsackie | N |  | 8.175 | [13 empty] | NM | N | POWERONE PVI-6000 (1) & POWERONE PVI-3.0 (1) | 2012-11-08 | 2012-11-15 | 5 | 2012-11-15 | [14 empty] | 2012-12-31 | 2012-12-31 |  | Y
Central Hudson |  | Hudson Solar | CH-01696 | Kingston | Hurley | Ulster | 12443 | G | 2094 | Hurley Ave | N |  | 6 | [13 empty] | NM | N | POWERONE PVI-6000 | 2012-11-08 | 2012-11-15 | 5 | 2012-11-15 | [14 empty] | 2012-12-27 | 2012-12-31 |  | Y
Central Hudson |  | Hudson Solar | CH-02478 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8093 | Fishkill Plains | N | CH-00579 | 4.2 | [13 empty] | NM | N | POWERONE PVI-4.2 | 2012-11-08 | 2012-11-15 | 5 | 2012-11-15 | [14 empty] | 2012-12-14 | 2012-12-19 |  | Y
Central Hudson |  | SolarCity | CH-06944 | Fishkill | Beacon | Dutchess | 12508 | G | 8087 | Tioronda | N |  | 4.68 | [13 empty] | NM | N | XANTREX GT 2.8 (2) | 2012-11-08 | 2012-11-15 | 5 | 2012-11-15 | [14 empty] | 2013-04-11 | 2013-04-17 |  | Y
Central Hudson |  | Sungevity Inc | CH-09256 | Catskill | Jewett |  | 12444 | E | 2081 | Hunter | N | CH-09256 | 2.94 | [13 empty] | NM | N | POWER ONE PVI 3.0 | 2012-11-08 | 2012-11-15 | 5 | 2012-11-15 | [14 empty] | 2013-06-14 | 2013-06-21 |  | W
Central Hudson |  | SolarCity | CH-06388 | Newburgh | New Windsor | Orange | 12553 | G | 4095 | Bethlehem Rd | N |  | 4.2 | [13 empty] | NM | N | POWER-ONE AURORA 4.2 | 2012-11-13 | 2012-11-19 | 4 | 2012-11-19 | [14 empty] | 2013-05-23 | 2013-05-31 |  | Y
Central Hudson |  | SolarCity | CH-07557 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8091 | Fishkill Plains | N |  | 7.5 | [13 empty] | NM | N | FRONIUS IG PLUS V 7.5 | 2012-11-13 | 2012-11-20 | 5 | 2012-11-20 | [14 empty] | 2013-04-17 | 2013-04-24 |  | Y
Central Hudson |  | Solar Energy Systems, LLC | CH-09016 | Newburgh | New Windsor | Orange | 12553 | G | 4095 | Bethlehem Rd | N |  | 34.2 | [13 empty] | NM | N | FRONIUS 11.4 (3) | 2012-12-06 | 2012-12-06 | 0 | 2012-12-06 | [14 empty] | 2013-03-20 | 2013-03-20 |  | Y
Central Hudson |  | 2K Solar Inc | CH-00620 | Newburgh | Rock Tvrn | Orange | 12575 | G | 4097 | Bethlehem Rd | N |  | 7.5 | [13 empty] | NM | N | POWER-ONE PVI-6000 (1) & POWER-ONE PVI-3.0 | 2012-12-11 | 2012-12-11 | 0 | 2012-12-11 | [14 empty] | 2012-12-21 | 2012-12-31 |  | Y
Central Hudson |  | SolarCity | CH-05086 | Newburgh | New Windsor | Orange | 12553 | G | 4093 | Bethlehem Rd | N |  | 7.6 | [13 empty] | NM | N | POWER-ONE AURORA PVI-3.8 (2) | 2012-11-19 | 2012-11-27 | 4 | 2012-11-27 | [14 empty] | 2013-02-01 | 2013-02-01 |  | Y
Central Hudson |  | Hudson Solar | CH-01467 | Newburgh | Newburgh | Orange | 12550 | G | 4015 | West Balmville | N |  | 20 | [13 empty] | NM | N | POWERONE PVI-5000 (4) | 2012-11-20 | 2012-11-30 | 6 | 2012-11-30 | [14 empty] | 2012-12-28 | 2013-01-03 |  | Y
Central Hudson |  | Hudson Solar | CH-01543 | Newburgh | Newburgh | Orange | 12550 | G | 4015 | West Balmville | N |  | 18 | [13 empty] | NM | N | POWERONE PVI-6000 (3) | 2012-11-20 | 2012-11-30 | 6 | 2012-11-30 | [14 empty] | 2012-12-31 | 2012-12-31 |  | Y
Central Hudson |  | Hudson Solar | CH-02481 | Fishkill | Cold Spg | Putnam | 10516 | G | 8087 | Tioronda | N | CH-02181 | 2.07 | [13 empty] | NM | N | POWERONE PVI-3.0 | 2012-11-20 | 2012-11-27 | 3 | 2012-11-27 | [14 empty] | 2013-05-06 | 2013-05-07 |  | Y
Central Hudson |  | SolarCity | CH-06153 | Fishkill | Cold Spg | Putnam | 10516 | G | 8086 | Tioronda | N |  | 3.8 | [13 empty] | NM | N | SOLAREDGE SE3800A-US | 2012-11-20 | 2012-11-27 | 3 | 2012-11-27 | [14 empty] | 2013-07-05 | 2013-07-12 |  | Y
Central Hudson |  | Solar Generation | CH-08166 | Kingston | Glenford | Ulster | 12433 | G | 3013 | Woodstock | N |  | 3.6 | [13 empty] | NM | N | POWER ONE 3.6 | 2012-11-20 | 2012-11-27 | 3 | 2012-11-27 | [14 empty] | 2013-03-18 | 2013-03-22 |  | Y
Central Hudson |  | Solar Generation | CH-08195 | Kingston | Woodstock | Ulster | 12498 | G | 3014 | Woodstock | N |  | 7 | [13 empty] | NM | N | SMA 7000 | 2012-11-20 | 2012-11-27 | 3 | 2012-11-27 | [14 empty] | 2013-01-02 | 2013-01-02 |  | Y
Central Hudson |  | SolarCity | CH-06829 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8044 | Myers Corners | N |  | 6 | [13 empty] | NM | N | POWER-ONE AURORA PVI-6000 | 2012-11-21 | 2012-11-27 | 2 | 2012-11-27 | [14 empty] | 2013-06-06 | 2013-06-13 |  | Y
Central Hudson |  | Solar Generation | CH-08241 | Kingston | Saugerties | Ulster | 12477 | G | 3004 | Saugerties | N |  | 5.805 | [13 empty] | NM | N | ENPHASE M215 (27) | 2012-11-21 | 2012-12-03 | 6 | 2012-12-03 | [14 empty] | 2013-01-15 | 2013-01-16 |  | Y
Central Hudson |  | Hudson Solar | CH-01221 | Newburgh | Gardiner | Ulster | 12525 | G | 5031 | Galeville | N |  | 45 | [13 empty] | NM | N | POWERONE PVI-5000 (9) | 2012-11-26 | 2012-12-06 | 8 | 2012-12-06 | [14 empty] | 2013-06-28 | 2013-07-03 |  | W
Central Hudson |  | Sungevity Inc | CH-09192 | Newburgh | Newburgh | Orange | 12550 | G | 4012 | West Balmville | N |  | 6.6 | [13 empty] | NM | N | POWER ONE PVI-3.6 (1) & POWER ONE PVI-3.0 (1) | 2012-11-26 | 2012-12-04 | 6 | 2012-12-04 | [14 empty] | 2013-04-04 | 2013-04-11 |  | Y
Central Hudson |  | SolarCity | CH-07124 | Newburgh | Cornwall | Orange | 12518 | G | 4041 | Union Ave | N |  | 6 | [13 empty] | NM | N | SMA SUNNY BOY 6000 | 2012-11-27 | 2012-12-06 | 7 | 2012-12-06 | [14 empty] | 2013-06-20 | 2013-06-27 |  | Y
Central Hudson |  | Solar Energy Systems, LLC | CH-09019 | Newburgh | Newburgh |  | 12550 | G | 4027 | Coldenham | TBD |  | 42 | [13 empty] | NM | N | FRONIUS 10.0 (3) & FRONIUS 12.0 (1) | 2012-12-04 | 2012-12-20 | 12 | 2012-12-20 | [17 empty] | W |  | System determined eligible for fast track process during preliminary review Section C, Step 4. 3/26/13 This project has been abandoned.
Central Hudson |  | Solar Energy Systems, LLC | CH-09020 | Newburgh | Newburgh |  | 12550 | G | 4027 | Coldenham | TBD |  | 41.4 | [13 empty] | NM | N | FRONIUS 10.0 (3) & FRONIUS 11.4 (1) | 2012-12-04 | 2012-12-20 | 12 | 2012-12-20 | [17 empty] | W |  | System determined eligible for fast track process during preliminary review Section C, Step 4. 3/26/13 This project has been abandoned.
Central Hudson |  | Solar Energy Systems, LLC | CH-09021 | Newburgh | Newburgh |  | 12550 | G | 4027 | Coldenham | TBD |  | 41.4 | [13 empty] | NM | N | FRONIUS 10.0 (3) & FRONIUS 11.4 (1) | 2012-12-04 | 2012-12-20 | 12 | 2012-12-20 | [17 empty] | W |  | System determined eligible for fast track process during preliminary review Section C, Step 4. 3/26/13 This project has been abandoned.
Central Hudson |  | Lotus Energy Inc. | CH-03857 | Catskill | Catskill | Greene | 12414 | G | 2003 | North Catskill | N |  | 5 | [13 empty] | NM | N | SUNPOWER SPR5000 | 2012-11-28 | 2012-12-05 | 5 | 2012-12-05 | [14 empty] | 2013-02-04 | 2013-02-11 |  | Y
Central Hudson |  | SolarCity | CH-07239 | Kingston | Kingston | Ulster | 12401 | G | 2016 | Lincoln Park | N |  | 6 | [13 empty] | NM | N | POWER-ONE AURORA PVI-6000 | 2012-11-28 | 2012-12-06 | 6 | 2012-12-06 | [14 empty] | 2013-03-26 | 2013-04-03 |  | Y
Central Hudson |  | Sungevity Inc | CH-09385 | Newburgh | Wallkill | Ulster | 12589 | G | 5041 | East Walden | N |  | 7.2 | [13 empty] | NM | N | POWER ONE PVI 4.2 (1) & POWER ONE PVI 3.0 (1) | 2012-11-29 | 2012-12-06 | 5 | 2012-12-06 | [14 empty] | 2013-03-21 | 2013-03-27 |  | Y
Central Hudson |  | SolarCity | CH-06149 | Fishkill | Beacon |  | 12508 | G | 8087 | Tioronda | TBD |  | 3.6 | [13 empty] | NM | N | SOLAREDGE SE3800A | 2012-11-30 | 2012-12-10 | 6 | 2012-12-10 | [17 empty] | W |  | Customer already had net meter prior to application. 09/30/14 Project abandoned as per customer.
Central Hudson |  | SolarCity | CH-06576 | Kingston | Saugerties |  | 12477 | G | 3004 | Saugerties | TBD |  | 5.76 | [13 empty] | NM | N | SMA SUNNY BOY 6000 | 2012-11-30 | 2012-12-10 | 6 | 2012-12-10 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | SolarCity | CH-06613 | Poughkeepsie | Poughkeepsie |  | 12603 | G | 6045 | Spackenkill | TBD |  | 4.94 | [13 empty] | NM | N | POWER-ONE AURORA PVI-5000 | 2012-11-30 | 2012-12-10 | 6 | 2012-12-10 | [17 empty] | W |  | Customer already had net meter prior to application. 10/21/14 Project abandoned as per customer.
Central Hudson |  | SolarCity | CH-07175 | Newburgh | New Windsor | Orange | 12553 | G | 4094 | Bethlehem Rd | N |  | 7.2 | [13 empty] | NM | N | POWER-ONE PVI-4.2-OUTD (1) & POWER-ONE AURORA PVI-3.0 (1) | 2012-12-03 | 2012-12-11 | 6 | 2012-12-11 | [14 empty] | 2013-03-26 | 2013-04-03 |  | Y
Central Hudson |  | SolarCity | CH-07533 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 6074 | East Park | N |  | 3.92 | [13 empty] | NM | N | FRONIUS IG 5100 NEG | 2012-12-03 | 2012-12-11 | 6 | 2012-12-11 | [14 empty] | 2013-06-11 | 2013-06-18 |  | W
Central Hudson |  | SunDog Solar | CH-09139 | Catskill | Hensonvl | Greene | 12439 | E | 2081 | Hunter | N | CH-09139 | 4 | [13 empty] | NM | N | SMA SB4000 | 2012-12-03 | 2012-12-12 | 7 | 2012-12-12 | [14 empty] | 2013-08-16 | 2013-08-22 |  | Y
Central Hudson |  | Inverters Unlimited Inc | CH-02559 | Catskill | Greenvl | Greene | 12083 | G | 2061 | Freehold | N |  | 3 | [13 empty] | NM | N | SMA SB3000US | 2012-12-10 | 2012-12-17 | 5 | 2012-12-17 | [14 empty] | 2013-02-11 | 2013-02-19 |  | Y
Central Hudson |  | SolarCity | CH-05510 | Catskill | Purling | Greene | 12470 | G | 2042 | South Cairo | N | CH-05510 | 4 | [13 empty] | NM | N | SMA SUNNY BOY 4000 | 2012-12-10 | 2012-12-13 | 3 | 2012-12-13 | [14 empty] | 2013-03-11 | 2013-03-18 |  | Y
Central Hudson |  | SolarCity | CH-07185 | Catskill | Acra | Greene | 12405 | G | 2043 | South Cairo | N |  | 6 | [13 empty] | NM | N | POWER-ONE AURORA PVI-6000 | 2012-12-12 | 2012-12-17 | 3 | 2012-12-17 | [14 empty] | 2013-03-18 | 2013-03-22 |  | Y
Central Hudson |  | SolarCity | CH-07916 | Newburgh | Rock Tvrn |  | 12575 | G | 4097 | Bethlehem Rd | TBD |  | 10.2 | [13 empty] | NM | N | POWER-ONE AURORA PVI-6000 (1) & POWER-ONE AURORA PVI-4.2(1) | 2012-12-12 | 2012-12-17 | 3 | 2012-12-17 | [17 empty] | W |  | Customer already had net meter prior to application. 1/28/13 Received email from customer advising that this project has been abandoned.
Central Hudson |  | RGS Energy | CH-03040 | Newburgh | Cornwall-Hdsn | Orange | 12520 | G | 4043 | Union Ave | N |  | 7 | [13 empty] | NM | N | SUNPOWER SPR-7000M | 2012-12-13 | 2012-12-19 | 4 | 2012-12-19 | [14 empty] | 2013-01-18 | 2013-01-24 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00989 | Kingston | Saugerties | Ulster | 12477 | G | 3004 | Saugerties | N |  | 5.16 | [13 empty] | NM | N | ENPHASE M215 (24) | 2012-12-17 | 2012-12-20 | 3 | 2012-12-20 | [14 empty] | 2013-01-17 | 2013-01-23 |  | Y
Central Hudson |  | Hudson Solar | CH-01527 | Kingston | Saugerties | Ulster | 12477 | G | 3003 | Saugerties | N |  | 6 | [13 empty] | NM | N | POWERONE PVI-6000 | 2012-12-17 | 2012-12-21 | 4 | 2012-12-21 | [14 empty] | 2013-03-21 | 2013-03-27 |  | Y
Central Hudson |  | Hudson Solar | CH-01569 | Newburgh | Mountainvl | Orange | 10953 | G | 4093 | Bethlehem Rd | N |  | 16 | [13 empty] | NM | N | POWERONE PVI-6000 (1) & POWERONE PVI-5000 (2) | 2012-12-17 | 2012-12-20 | 3 | 2012-12-20 | [14 empty] | 2013-05-14 | 2013-05-21 |  | Y
Central Hudson |  | Hudson Solar | CH-01682 | Kingston | Port Ewen | Ulster | 12466 | G | 1024 | East Kingston | N |  | 4.905 | [13 empty] | NM | N | POWERONE PVI-5000 | 2012-12-20 | 2012-12-21 | 1 | 2012-12-21 | [14 empty] | 2013-02-26 | 2013-03-04 |  | Y
Central Hudson |  | Hudson Solar | CH-01767 | Poughkeepsie | Staatsburg | Dutchess | 12580 | G | 7041 | Staatsburg | Y |  | 9.6 | 9.6 | [12 empty] | NM | N | XANTREX XW-6048 (1) & POWERONE PVI-3.6 (1)1XantrexXW6048 (DC) | 2012-12-17 | 2012-12-21 | 4 | 2012-12-21 | [14 empty] | 2013-04-04 | 2013-04-11 |  | Y
Central Hudson |  | Hudson Solar | CH-02277 | Poughkeepsie | Annandle-Hdsn | Dutchess | 12504 | G | 7056 | Rhinebeck | N | CH-02277 | 3.924 | [13 empty] | NM | N | POWERONE PVI-4.2 | 2012-12-17 | 2012-12-21 | 4 | 2012-12-21 | [14 empty] | 2013-05-07 | 2013-05-10 |  | W
Central Hudson |  | Hudson Solar | CH-02311 | Fishkill | Cold Spg | Putnam | 10516 | G | 8087 | Tioronda | N |  | 2.289 | [13 empty] | NM | N | POWERONE PVI-3.0 | 2012-12-17 | 2012-12-21 | 4 | 2012-12-21 | [14 empty] | 2013-03-28 | 2013-04-05 |  | Y
Central Hudson |  | Hudson Solar | CH-02358 | Fishkill | Cold Spg | Putnam | 10516 | G | 8087 | Tioronda | N |  | 7.194 | [13 empty] | NM | N | POWERONE PVI-3.6 (2) | 2012-12-20 | 2012-12-21 | 1 | 2012-12-21 | [14 empty] | 2013-03-28 | 2013-04-05 |  | Y
Central Hudson |  | Solartech Renewables | CH-09063 | Poughkeepsie | Annandale On Hudson | Dutchess | 12504 | G | 7056 | Rhinebeck | N | CH-09063 | 60 | [13 empty] | NM | Y | Chint Inverter SC20KTL (3) | 2013-01-04 | 2013-01-25 | 15 | 2013-01-25 | [14 empty] | 2013-10-21 | 2013-10-28 |  | Y | N
Central Hudson |  | Solartech Renewables | CH-09067 | Poughkeepsie | Annandale On Hudson | Dutchess | 12504 | G | 7056 | Rhinebeck | N | CH-09063 | 140 | [13 empty] | NM | Y | Chint Inverter SC20KTL (4) & Chint Inverter S100KTL (1) | 2013-01-04 | 2013-01-25 | 15 | 2013-01-25 | 2013-01-04 | 2013-01-25 | 15 | [11 empty] | 2013-12-02 | 2013-12-05 |  | Y | N
Central Hudson |  | Solartech Renewables | CH-09068 | Poughkeepsie | Annandale On Hudson | Dutchess | 12504 | G | 7056 | Rhinebeck | N | CH-09063 | 40 | [13 empty] | NM | Y | Chint Inverter SC20KTL (2) | 2013-01-04 | 2013-01-25 | 15 | 2013-01-25 | 2013-01-04 | 2013-01-25 | 15 | [11 empty] | 2014-01-08 | 2014-01-17 |  | Y | N
Central Hudson |  | GREEN POWER SOLUTIONS | CH-01170 | Catskill | Preston Holw | Albany | 12469 | G | 1092 | Westerlo | Y |  | 6 | 6 | [12 empty] | NM | N | Xantrex XW60481XantrexXW6048 (DC) | 2013-01-16 | 2013-01-16 | 0 | 2013-01-16 | [14 empty] | 2013-02-07 | 2013-02-08 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06842 | Fishkill | Stormvl | Dutchess | 12582 | G | 8095 | Fishkill Plains | N |  | 4.2 | [13 empty] | NM | N | POWER-ONE AURORA PVI-4.2 | 2012-12-21 | 2012-12-21 | 0 | 2012-12-21 | [14 empty] | 2013-03-04 | 2013-03-11 |  | Y
Central Hudson |  | SolarCity | CH-07625 | Catskill | Earlton | Greene | 12058 | G | 2071 | Freehold | N |  | 4.2 | [13 empty] | NM | N | POWER-ONE AURORA PVI-4.2 | 2012-12-31 | 2013-01-07 | 4 | 2013-01-07 | [14 empty] | 2013-03-18 | 2013-03-22 |  | Y
Central Hudson |  | Conscious Energy | CH-00802 | Newburgh | New Paltz | Ulster | 12561 | G | 5084 | Highland | N |  | 5 | [13 empty] | NM | N | SMA SB2500HFUS (2) | 2013-02-25 | 2013-03-04 | 5 | 2013-03-04 | [14 empty] | 2013-04-16 | 2013-04-23 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03782 | Fishkill | Garrison | Putnam | 10524 | G | 8086 | Tioronda | N |  | 6 | [13 empty] | NM | N | POWER-ONE AURORA PVI6000-OUTD-US | 2013-01-04 | 2013-01-08 | 2 | 2013-01-08 | [14 empty] | 2013-04-26 | 2013-05-03 |  | Y
Central Hudson |  | SolarCity | CH-07039 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 7 | [13 empty] | NM | N | SMA SUNNY BOY 7000 | 2013-01-04 | 2013-01-08 | 2 | 2013-01-08 | [14 empty] | 2013-03-22 | 2013-04-01 |  | Y
Central Hudson |  | RGS Energy | CH-03011 | Catskill | Catskill |  | 12414 | G | 2001 | North Catskill | TBD |  | 8.385 | [13 empty] | NM | N | ENPHASE M215 (39) | 2013-01-14 | 2013-01-14 | 0 | 2013-01-14 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | Lighthouse Solar | CH-03809 | Kingston | Saugerties | Ulster | 12477 | G | 3003 | Saugerties | N |  | 7.5 | [13 empty] | NM | N | FRONIUS IG PLUS 7.5 | 2013-01-11 | 2013-01-14 | 1 | 2013-01-14 | [14 empty] | 2013-03-25 | 2013-04-02 |  | Y
Central Hudson |  | SolarCity | CH-05626 | Kingston | Tillson |  | 12486 | G | 3022 | High Falls | TBD |  | 7.2 | [13 empty] | NM | N | FRONIUS IG PLUS V 7.5 | 2013-01-14 | 2013-01-16 | 2 | 2013-01-16 | [17 empty] | W
Central Hudson |  | SolarCity | CH-05540 | Catskill | Catskill | Greene | 12414 | G | 2006 | North Catskill | N |  | 6 | [13 empty] | NM | N | POWER-ONE AURORA PVI 6000 | 2013-01-17 | 2013-01-23 | 4 | 2013-01-23 | [14 empty] | 2013-05-03 | 2013-05-07 |  | Y
Central Hudson |  | SolarCity | CH-07218 | Kingston | Kingston | Ulster | 12401 | G | 1022 | East Kingston | N |  | 3.36 | [13 empty] | NM | N | SMA SUNNY BOY 3800 | 2013-01-17 | 2013-01-21 | 2 | 2013-01-21 | [14 empty] | 2013-04-22 | 2013-04-29 |  | Y
Central Hudson |  | SolarCity | CH-06767 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7051 | Rhinebeck | N |  | 12.985 | [13 empty] | NM | N | POWER-ONE AURORA PVI-5000 (3) | 2013-01-18 | 2013-01-24 | 4 | 2013-01-24 | [14 empty] | 2013-04-18 | 2013-04-18 |  | Y
Central Hudson |  | SolarCity | CH-06776 | Poughkeepsie | Tivoli | Dutchess | 12583 | G | 7062 | Milan | N |  | 4.2 | [13 empty] | NM | N | POWER-ONE AURORA PVI-4.2 | 2013-01-18 | 2013-01-24 | 4 | 2013-01-24 | [14 empty] | 2013-04-05 | 2013-04-12 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03686 | Newburgh | Gardiner | Ulster | 12525 | G | 5031 | Galeville | N | CH-03686 | 4.73 | [13 empty] | NM | N | Enphase M215 (22) | 2013-01-25 | 2013-01-30 | 3 | 2013-01-30 | [14 empty] | 2013-04-10 | 2013-04-10 |  | Y
Central Hudson |  | DayStar Solar LLC | CH-00824 | Catskill | Hannacroix |  | 12087 | G | 1083 | New Baltimore | TBD |  | 7.74 | [13 empty] | NM | N | ENPHASE M215 (36) | 2013-02-07 | 2013-02-15 | 6 | 2013-02-15 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | SolarCity | CH-05539 | Catskill | Catskill | Greene | 12414 | G | 2006 | North Catskill | N |  | 9.6 | [13 empty] | NM | N | FRONIUS IG PLUS V 10.0 | 2013-01-25 | 2013-02-06 | 8 | 2013-02-06 | [8 empty] | 350 | 350 |  |  |  |  | 2013-04-02 | 2013-04-09 |  | Y
Central Hudson |  | SolarCity | CH-05147 | Fishkill | Stormvl | Dutchess | 12582 | G | 8095 | Fishkill Plains | N |  | 5 | [13 empty] | NM | N | POWER-ONE AURORA PVI-5000 | 2013-01-28 | 2013-01-31 | 3 | 2013-01-31 | [14 empty] | 2013-03-14 | 2013-03-20 |  | Y
Central Hudson |  | SolarCity | CH-05480 | Catskill | Catskill | Greene | 12414 | G | 2004 | North Catskill | N |  | 5 | [13 empty] | NM | N | Schneider TX 5000 | 2013-01-28 | 2013-01-31 | 3 | 2013-01-31 | [14 empty] | 2013-04-30 | 2013-05-07 |  | Y
Central Hudson |  | SolarCity | CH-06843 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8095 | Fishkill Plains | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A | 2013-01-28 | 2013-02-08 | 9 | 2013-02-08 | [14 empty] | 2013-04-08 | 2013-04-15 |  | Y
Central Hudson |  | SolarCity | CH-05530 | Catskill | Preston Holw | Albany | 12469 | G | 1092 | Westerlo | N |  | 6 | [13 empty] | NM | N | POWER-ONE AURORA PVI 3.0 (2) | 2013-01-29 | 2013-02-08 | 8 | 2013-02-08 | [14 empty] | 2013-05-02 | 2013-05-09 |  | Y
Central Hudson |  | SolarCity | CH-05525 | Catskill | Durham | Greene | 12422 | G | 1092 | Westerlo | N |  | 7.2 | [13 empty] | NM | N | FRONIUS IG PLUS V 7.5 | 2013-01-30 | 2013-02-08 | 7 | 2013-02-08 | [14 empty] | 2013-06-11 | 2013-06-18 |  | Y
Central Hudson |  | SolarCity | CH-07050 | Newburgh | Wallkill | Ulster | 12589 | G | 5012 | Modena | N |  | 8.085 | [13 empty] | NM | N | Fronuis IG Plus V 10.0 | 2013-01-31 | 2013-02-11 | 7 | 2013-02-11 | [14 empty] | 2013-10-02 | 2013-10-09 |  | Y
Central Hudson |  | SolarCity | CH-05767 | Kingston | Kingston | Ulster | 12401 | G | 1021 | East Kingston | N |  | 3.6 | [13 empty] | NM | N | POWER-ONE AURORA PVI-3.6 | 2013-02-01 | 2013-02-11 | 6 | 2013-02-11 | [14 empty] | 2013-08-07 | 2013-08-13 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03629 | Newburgh | New Paltz | Ulster | 12561 | G | 5031 | Galeville | N |  | 6 | [13 empty] | NM | N | POWER-ONE AURORA PVI6000-OUTS-S-US | 2013-02-04 | 2013-02-12 | 6 | 2013-02-12 | [14 empty] | 2013-04-19 | 2013-04-26 |  | Y
Central Hudson |  | Direct Energy Solar | CH-01070 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7053 | Rhinebeck | N |  | 6.235 | [13 empty] | NM | N | ENPHASE M215 (29) | 2013-02-04 | 2013-02-19 | 10 | 2013-02-19 | [14 empty] | 2013-06-05 | 2013-06-12 |  | Y
Central Hudson |  | SolarCity | CH-05636 | Kingston | Cottekill | Ulster | 12419 | G | 3021 | High Falls | N |  | 4.9 | [13 empty] | NM | N | SMA SUNNY BOY SB 5000 | 2013-02-04 | 2013-02-12 | 6 | 2013-02-12 | [14 empty] | 2013-05-06 | 2013-05-10 |  | Y
Central Hudson |  | Solar Alchemy | CH-08980 | Kingston | Napanoch | Ulster | 12458 | G | 3091 | Neversink | Y |  | 4.5 | 4.5 | [12 empty] | NM | N | Xantrex XW Hybrid Inverter/Charger XW45481XantrexXW4548 (DC) | 2013-08-28 | 2013-08-29 | 1 | 2013-08-29 | [14 empty] | 2013-09-06 | 2013-09-13 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-05502 | Catskill | Catskill | Greene | 12414 | G | 2005 | North Catskill | N |  | 6 | [13 empty] | NM | N | POWER-ONE AURORA PVI 6000 | 2013-02-06 | 2013-02-15 | 7 | 2013-02-15 | [14 empty] | 2013-04-12 | 2013-04-19 |  | Y
Central Hudson |  | Solar Energy Systems, LLC | CH-09015 | Newburgh | New Windsor | Orange | 12553 | G | 4095 | Bethlehem Rd | N |  | 15 | [13 empty] | NM | N | FRONIUS 7.5 (2) | 2013-02-06 | 2013-02-20 | 9 | 2013-02-20 | [8 empty] | 350 | 350 |  |  |  |  | 2014-01-07 | 2014-01-07 |  | Y
Central Hudson |  | Sungevity Inc | CH-09569 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7042 | Staatsburg | N |  | 6 | [13 empty] | NM | N | SMA AMERICA SB6000US | 2013-02-08 | 2013-02-15 | 5 | 2013-02-15 | [14 empty] | 2013-04-18 | 2013-04-24 |  | Y
Central Hudson |  | Hudson Solar | CH-01250 | Poughkeepsie | Lagrangevl | Dutchess | 12540 | G | 6055 | Todd Hill | N |  | 5.886 | [13 empty] | NM | N | POWER ONE PVI-6000 | 2013-02-11 | 2013-02-22 | 8 | 2013-02-22 | [14 empty] | 2013-04-22 | 2013-04-23 |  | Y
Central Hudson |  | Hudson Solar | CH-01607 | Catskill | Preston Holw | Albany | 12469 | G | 2071 | Freehold | N |  | 5 | [13 empty] | NM | N | POWERONE PVI-5000 | 2013-02-11 | 2013-02-22 | 8 | 2013-02-22 | [14 empty] | 2013-04-09 | 2013-04-16 |  | Y
Central Hudson |  | Lotus Energy Inc. | CH-03852 | Catskill | Coxsackie | Greene | 12051 | G | 1071 | Coxsackie | N |  | 3.924 | [13 empty] | NM | N | SUNPOWER SPR 4000 | 2013-02-12 | 2013-02-19 | 4 | 2013-02-19 | [14 empty] | 2013-04-01 | 2013-04-08 |  | W
Central Hudson |  | Hudson Solar | CH-01734 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6095 | Manchester | N |  | 5 | [13 empty] | NM | N | POWERONE PVI-5000 | 2013-02-26 | 2013-03-04 | 4 | 2013-03-04 | [14 empty] | 2013-06-05 | 2013-06-12 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00894 | Kingston | Ulster Pk | Ulster | 12487 | G | 1014 | Boulevard | N |  | 5.805 | [13 empty] | NM | N | ENPHASE M215 (27) | 2013-02-14 | 2013-02-22 | 5 | 2013-02-22 | [14 empty] | 2013-04-01 | 2013-04-08 |  | Y
Central Hudson |  | Sol Providers | CH-08955 | Newburgh | Clintondale |  | 12515 | G | 5012 | Modena | TBD |  | 6.02 | [13 empty] | NM | N | ENPHASE M215 (28) | 2013-02-19 | 2013-02-28 | 7 | 2013-02-28 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | Sol Providers | CH-08969 | Poughkeepsie | Lagrangevl | Dutchess | 12540 | G | 6057 | Todd Hill | N | CH-08921 | 1.505 | [13 empty] | NM | N | ENPHASE M215 (7) | 2013-02-19 | 2013-02-28 | 7 | 2013-02-28 | [14 empty] | 2013-04-10 | 2013-04-17 |  | W
Central Hudson |  | Solar Energy Systems, LLC | CH-09018 | Newburgh | Newburgh | Orange | 12550 | G | 4092 | Bethlehem Rd | N |  | 27.5 | [13 empty] | NM | N | FRONIUS 10.0 (2) & FRONIUS 7.5 (1) | 2013-02-19 | 2013-02-27 | 6 | 2013-02-27 | [14 empty] | 2013-10-24 | 2013-10-29 |  | Y
Central Hudson |  | New York State Solar Farm | CH-03956 | Newburgh | Mountainvl | Orange | 10953 | G | 4095 | Bethlehem Rd | N |  | 6 | [13 empty] | NM | N | POWER ONE PVI-6000 | 2013-03-05 | 2013-03-12 | 5 | 2013-03-12 | [14 empty] | 2013-07-19 | 2013-07-19 |  | Y
Central Hudson |  | SolarCity | CH-05957 | Poughkeepsie | Rhinebeck |  | 12572 | G | 7052 | Rhinebeck | TBD |  | 2.64 | [13 empty] | NM | N | POWER-ONE AURORA PVI 3.0 | 2013-02-27 | 2013-03-13 | 10 | 2013-03-13 | [17 empty] | W
Central Hudson |  | Direct Energy Solar | CH-00952 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8092 | Fishkill Plains | N |  | 6.665 | [13 empty] | NM | N | ENPHASE M215 (31) | 2013-02-28 | 2013-03-13 | 9 | 2013-03-13 | [14 empty] | 2013-05-01 | 2013-05-08 |  | Y
Central Hudson |  | Kirchhoff Green Energy LLC | CH-03540 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 6092 | Manchester | N |  | 11.52 | [13 empty] | NM | N | SMA 6000 (2) | 2013-03-06 | 2013-03-19 | 9 | 2013-03-19 | [14 empty] | 2013-07-03 | 2013-07-11 |  | Y
Central Hudson |  | SolarCity | CH-06757 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7062 | Milan | N |  | 8.4 | [13 empty] | NM | N | POWER-ONE AURORA PVI 4.2 (2) | 2013-03-06 | 2013-03-14 | 6 | 2013-03-14 | [14 empty] | 2013-05-13 | 2013-05-13 |  | Y
Central Hudson |  | SolarCity | CH-06451 | Catskill | Rensselaervl | Albany | 12147 | G | 1092 | Westerlo | N |  | 7 | [13 empty] | NM | N | SMA SUNNY BOY 7000 | 2013-03-07 | 2013-03-15 | 6 | 2013-03-15 | [14 empty] | 2013-04-19 | 2013-04-26 |  | Y
Central Hudson |  | SolarCity | CH-06479 | Kingston | Kerhonkson | Ulster | 12446 | G | 3082 | Kerhonkson | N |  | 7 | [13 empty] | NM | N | SMA SUNNY BOY 7000 | 2013-03-07 | 2013-03-15 | 6 | 2013-03-15 | [14 empty] | 2013-05-30 | 2013-06-06 |  | Y
Central Hudson |  | SolarCity | CH-07673 | Newburgh | New Paltz | Ulster | 12561 | G | 5023 | Ohioville | N |  | 7.6 | [13 empty] | NM | N | POWER-ONE AURORA PVI 3.8 (2) | 2013-03-07 | 2013-03-18 | 7 | 2013-03-18 | [14 empty] | 2013-05-08 | 2013-05-10 |  | Y
Central Hudson |  | Monolith Solar Associates LLC | CH-02669 | Kingston | Lk Katrine | Ulster | 12449 | G | 2015 | Lincoln Park | N |  | 22.8 | [13 empty] | NM | N | Fronius IG Plus V 11.4 (2) | 2013-05-17 | 2013-06-10 | 15 | 2013-06-10 | 2013-05-17 | 2013-06-10 | 15 | [11 empty] | 2013-09-09 | 2013-09-11 |  | Y
Central Hudson |  | Monolith Solar Associates LLC | CH-02670 | Kingston | Lk Katrine | Ulster | 12449 | G | 2015 | Lincoln Park | N |  | 22.8 | [13 empty] | NM | N | Fronius IG Plus V 11.4 (2) | 2013-05-17 | 2013-06-10 | 15 | 2013-06-10 | [14 empty] | 2013-09-09 | 2013-09-11 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03617 | Newburgh | Wallkill | Ulster | 12589 | G | 5043 | East Walden | N |  | 5 | [13 empty] | NM | N | POWER-ONE AURORA PVI 5000 | 2013-03-20 | 2013-03-20 | 0 | 2013-03-20 | [14 empty] | 2013-05-09 | 2013-05-14 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03620 | Newburgh | Wallkill |  | 12589 | G | 4011 | West Balmville | TBD |  | 11.4 | [13 empty] | NM | N | FRONIUS IG PLUS 11.4 | 2013-03-13 | 2013-03-20 | 5 | 2013-03-20 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | Lighthouse Solar | CH-03823 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 6051 | Todd Hill | N | CH-04901 | 12.48 | [13 empty] | NM | N | POWER ONE AURORA PVI-10.0-I-OUTD (new) & PV POWERED PVP30KW (existing) | 2013-03-13 | 2013-03-22 | 7 | 2013-03-22 | [14 empty] | 2013-04-09 | 2013-04-09 |  | Y
Central Hudson |  | SolarCity | CH-05587 | Catskill | Coxsackie |  | 12051 | G | 1072 | Coxsackie | TBD |  | 6 | [13 empty] | NM | N | POWER-ONE AURORA PVI 6000 | 2013-03-13 | 2013-03-19 | 4 | 2013-03-19 | [17 empty] | W |  | Customer already had net meter prior to application. 9/30/14 Project abandoned as per customer.
Central Hudson |  | SolarCity | CH-05683 | Kingston | Woodstock | Ulster | 12498 | G | 3012 | Woodstock | N |  | 6.8 | [13 empty] | NM | N | SOLAREDGE SE3800 (1) & SOLAREDGE SE3000 (1) | 2013-03-13 | 2013-03-19 | 4 | 2013-03-19 | [14 empty] | 2013-05-06 | 2013-05-10 |  | Y
Central Hudson |  | SolarCity | CH-05012 | Kingston | Kingston | Ulster | 12401 | G | 2094 | Hurley Ave | N | CH-05012 | 7.6 | [13 empty] | NM | N | SolarEdge SE3800A-US (2) | 2013-03-15 | 2013-03-22 | 5 | 2013-03-22 | [14 empty] | 2013-10-10 | 2013-10-15 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06780 | Poughkeepsie | Stanfordvl | Dutchess | 12581 | G | 7072 | Stanfordville | N |  | 9.6 | [13 empty] | NM | N | FRONIUS IG PLUS V 10.0 | 2013-03-19 | 2013-03-22 | 3 | 2013-03-22 | [14 empty] | 2013-06-04 | 2013-06-11 |  | Y
Central Hudson |  | 2K Solar Inc | CH-00622 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 5.16 | [13 empty] | NM | N | SIEMENS SMIINV215R60MC (24) | 2013-03-26 | 2013-03-27 | 1 | 2013-03-27 | [14 empty] | 2013-04-02 | 2013-04-08 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06239 | Newburgh | Newburgh | Orange | 12550 | G | 4014 | West Balmville | N |  | 7 | [13 empty] | NM | N | SMA SUNNY BOY 7000 | 2013-03-20 | 2013-03-26 | 4 | 2013-03-26 | [14 empty] | 2013-05-30 | 2013-06-06 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00990 | Kingston | Saugerties | Ulster | 12477 | G | 3004 | Saugerties | N |  | 4.3 | [13 empty] | NM | N | ENPHASE M215 (20) | 2013-03-27 | 2013-03-27 | 0 | 2013-03-27 | [14 empty] | 2013-06-25 | 2013-07-01 |  | Y
Central Hudson |  | Hudson Solar | CH-01392 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 6051 | Todd Hill | Y |  | 6 | 6 | [12 empty] | NM | N | XANTREX XW6048-120/240-601XantrexXW6048 (DC) | 2013-03-21 | 2013-03-27 | 4 | 2013-03-27 | [14 empty] | 2013-05-03 | 2013-05-10 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00927 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6041 | Spackenkill | N |  | 9.245 | [13 empty] | NM | N | ENPHASE M215 (43) | 2013-03-27 | 2013-04-01 | 2 | 2013-04-01 | [14 empty] | 2013-09-06 | 2013-09-13 |  | Y
Central Hudson |  | Direct Energy Solar | CH-01047 | Newburgh | Campbell Hall | Orange | 10916 | G | 5052 | Maybrook | N |  | 7.31 | [13 empty] | NM | N | ENPHASE M215 (34) | 2013-03-27 | 2013-04-01 | 2 | 2013-04-01 | [14 empty] | 2013-06-05 | 2013-06-12 |  | Y
Central Hudson |  | Monolith Solar Associates LLC | CH-02676 | Catskill | Athens | Greene | 12015 | G | 2006 | North Catskill | N |  | 7 | [13 empty] | NM | N | SMA Sunny Boy 7000 | 2013-03-26 | 2013-04-01 | 3 | 2013-04-01 | [14 empty] | 2013-08-02 | 2013-08-07 |  | Y
Central Hudson |  | SolarCity | CH-06515 | Kingston | Port Ewen | Ulster | 12466 | G | 1012 | Boulevard | N |  | 3.6 | [13 empty] | NM | N | POWER-ONE AURORA PVI 3.6 | 2013-03-22 | 2013-04-01 | 5 | 2013-04-01 | [14 empty] | 2013-06-10 | 2013-06-14 |  | Y
Central Hudson |  | Hudson Solar | CH-01222 | Catskill | Greenvl | Greene | 12083 | G | 2061 | Freehold | Y |  | 9 | 9 | [12 empty] | NM | N | XANTREX XW4548 (2)2XantrexXW4548 (DC) | 2013-03-25 | 2013-04-09 | 10 | 2013-04-09 | [14 empty] | 2013-06-20 | 2013-06-27 |  | Y
Central Hudson |  | Hudson Solar | CH-02351 | Poughkeepsie | Tivoli | Dutchess | 12583 | G | 7062 | Milan | N |  | 6 | [13 empty] | NM | N | POWERONE PVI-6000 | 2013-03-25 | 2013-04-02 | 5 | 2013-04-02 | [14 empty] | 2013-05-03 | 2013-05-10 |  | W
Central Hudson |  | Solar Energy Systems, LLC | CH-09017 | Newburgh | Newburgh | Orange | 12550 | G | 4092 | Bethlehem Rd | N |  | 34.2 | [13 empty] | NM | N | FRONIUS 11.4 (3) | 2013-03-26 | 2013-04-03 | 5 | 2013-04-03 | [14 empty] | 2013-10-24 | 2013-10-29 |  | Y
Central Hudson |  | SolarCity | CH-05732 | Kingston | Saugerties | Ulster | 12477 | G | 3004 | Saugerties | N |  | 12 | [13 empty] | NM | N | SOLAREDGE SE6000 (2) | 2013-03-27 | 2013-04-04 | 5 | 2013-04-04 | [14 empty] | 2013-07-09 | 2013-07-09 |  | Y
Central Hudson |  | SolarCity | CH-06841 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8093 | Fishkill Plains | N |  | 8 | [13 empty] | NM | N | FRONIUS IG PLUS 8000 | 2013-03-28 | 2013-04-09 | 7 | 2013-04-09 | [14 empty] | 2013-10-23 | 2013-10-30 |  | Y
Central Hudson |  | Solar Energy Systems, LLC | CH-09014 | Newburgh | Walden | Orange | 12586 | G | 4026 | Coldenham | N |  | 40 | [13 empty] | NM | N | FRONIUS 10.0 (4) | 2013-05-02 | 2013-05-23 | 15 | 2013-05-23 | 2013-05-02 | 2013-05-23 | 15 | [11 empty] | 2013-10-10 | 2013-10-11 |  | Y
Central Hudson |  | Sungevity Inc | CH-09451 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8091 | Fishkill Plains | N |  | 6 | [13 empty] | NM | N | POWER-ONE PVI-6000 | 2013-03-28 | 2013-04-09 | 7 | 2013-04-09 | [14 empty] | 2013-07-09 | 2013-07-16 |  | Y
Central Hudson |  | Conscious Energy | CH-00809 | Kingston | Kingston | Ulster | 12401 | G | 2094 | Hurley Ave | N |  | 10 | [13 empty] | NM | N | SMA SB5000 (2) | 2013-04-29 | 2013-05-01 | 2 | 2013-05-01 | [14 empty] | 2013-08-15 | 2013-08-22 |  | Y
Central Hudson |  | Mannino Electric | CH-02606 | Newburgh | New Paltz | Ulster | 12561 | G | 5031 | Galeville | N | CH-02606 | 3.01 | [13 empty] | NM | N | ENPHASE M215 (14) | 2013-04-12 | 2013-04-19 | 5 | 2013-04-19 | [14 empty] | 2013-04-25 | 2013-05-01 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Murphy Solar Power | CH-02726 | Catskill | E Durham | Greene | 12423 | G | 1092 | Westerlo | N |  | 3 | [13 empty] | NM | N | SMA SUNNY BOY 3000 | 2013-04-01 | 2013-04-10 | 7 | 2013-04-10 | [14 empty] | 2013-04-29 | 2013-05-01 |  | Y
Central Hudson |  | SolarCity | CH-05040 | Poughkeepsie | Millerton | Dutchess | 12546 | G | 7081 | Millerton | N |  | 10 | [13 empty] | NM | N | FRONIUS IG PLUS V 10.0 | 2013-04-01 | 2013-04-10 | 7 | 2013-04-10 | [14 empty] | 2013-08-27 | 2013-09-03 |  | Y
Central Hudson |  | SolarCity | CH-05264 | Poughkeepsie | Tivoli | Dutchess | 12583 | G | 7062 | Milan | N |  | 2.88 | [13 empty] | NM | N | FRONIUS IG PLUS V 3.0 | 2013-04-01 | 2013-04-10 | 7 | 2013-04-10 | [14 empty] | 2013-07-17 | 2013-07-17 |  | Y
Central Hudson |  | Sungevity Inc | CH-09356 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8045 | Myers Corners | N |  | 5 | [13 empty] | NM | N | SMA AMERICA SB5000US | 2013-04-02 | 2013-04-10 | 6 | 2013-04-10 | [14 empty] | 2013-05-28 | 2013-06-03 |  | Y
Central Hudson |  | Kirchhoff Green Energy LLC | CH-03558 | Poughkeepsie | Salt Point | Dutchess | 12578 | G | 7011 | Hibernia | N |  | 4.8 | [13 empty] | NM | N | FRONIUS 5.0 UNI | 2013-04-03 | 2013-04-10 | 5 | 2013-04-10 | [14 empty] | 2013-05-14 | 2013-05-21 |  | Y
Central Hudson |  | SolarCity | CH-06542 | Kingston | Kingston | Ulster | 12401 | G | 2093 | Hurley Ave | N |  | 6 | [13 empty] | NM | N | POWER-ONE AURORA PVI 6000 | 2013-04-04 | 2013-04-11 | 5 | 2013-04-11 | [14 empty] | 2013-06-05 | 2013-06-12 |  | Y
Central Hudson |  | Self | CH-08891 | Kingston | Woodstock | Ulster | 12498 | G | 3012 | Woodstock | N |  | 3.87 | [13 empty] | NM | N | ENPHASE M215 (18) | 2013-04-24 | 2013-04-25 | 1 | 2013-04-25 | [14 empty] | 2013-04-26 | 2013-05-03 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Harvest Power | CH-01199 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 6075 | East Park | N |  | 6.02 | [13 empty] | NM | N | ENPHASE M215 (28) | 2013-04-08 | 2013-04-15 | 5 | 2013-04-15 | [14 empty] | 2013-09-19 | 2013-09-26 |  | Y
Central Hudson |  | SolarCity | CH-05568 | Catskill | Westerlo | Albany | 12193 | G | 1091 | Westerlo | N |  | 5 | [13 empty] | NM | N | SCHNEIDER TX-5000 | 2013-04-08 | 2013-04-15 | 5 | 2013-04-15 | [14 empty] | 2013-07-18 | 2013-07-22 |  | Y
Central Hudson |  | Sungevity Inc | CH-09222 | Newburgh | Pine Bush | Orange | 12566 | G | 5043 | East Walden | N |  | 6 | [13 empty] | NM | N | Power One PVI 3.0 (2) | 2013-04-08 | 2013-04-15 | 5 | 2013-04-15 | [14 empty] | 2013-06-13 | 2013-06-20 |  | Y
Central Hudson |  | SolarCity | CH-05369 | Newburgh | Wallkill | Ulster | 12589 | G | 5012 | Modena | N | CH-05369 | 6 | [13 empty] | NM | N | POWER-ONE AURORA PVI 6000 | 2013-04-16 | 2013-04-16 | 0 | 2013-04-16 | [14 empty] | 2013-06-14 | 2013-06-21 |  | Y
Central Hudson |  | SolarCity | CH-06905 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8072 | Shenandoah | N |  | 9 | [13 empty] | NM | N | POWER-ONE AURORA PVI 6000 (1) & POWER-ONE AURORA PVI 3.0 (1) | 2013-04-09 | 2013-04-16 | 5 | 2013-04-16 | [14 empty] | 2013-07-12 | 2013-07-17 |  | Y
Central Hudson |  | Sungevity Inc | CH-09220 | Newburgh | Gardiner | Ulster | 12525 | G | 5033 | Galeville | N |  | 10 | [13 empty] | NM | N | POWER-ONE PVI-5000 (2) | 2013-04-09 | 2013-04-15 | 4 | 2013-04-15 | [15 empty] | 2013-05-10 |  | Y |  | Customer already had net meter prior to application.
Central Hudson |  | Sungevity Inc | CH-09525 | Kingston | Kingston | Ulster | 12401 | G | 2017 | Lincoln Park | N |  | 5 | [13 empty] | NM | N | POWER-ONE PVI-5000-OUTD-US | 2013-04-09 | 2013-04-15 | 4 | 2013-04-15 | [14 empty] | 2013-06-04 | 2013-06-11 |  | Y
Central Hudson |  | Sunrise Solar Solutions, LLC | CH-09660 | Fishkill | Garrison | Putnam | 10524 | G | 8066 | Merritt Park | N |  | 3.44 | [13 empty] | NM | N | ENPHASE M215 (16) | 2013-04-09 | 2013-04-16 | 5 | 2013-04-16 | [14 empty] | 2014-06-18 | 2014-06-25 |  | Y
Central Hudson |  | Ross Solar Group | CH-02992 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6093 | Manchester | N |  | 10 | [13 empty] | NM | N | SUNPOWER 5000 P TL (2) | 2013-05-07 | 2013-05-09 | 2 | 2013-05-09 | [14 empty] | 2013-08-09 | 2013-08-09 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-03490 | Newburgh | Montgomery | Orange | 12549 | G | 5073 | Montgomery | N |  | 8.4 | [13 empty] | NM | N | POWER ONE PVI-4.2 (2) | 2013-05-07 | 2013-05-10 | 3 | 2013-05-10 | [14 empty] | 2013-08-12 | 2013-08-12 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03672 | Poughkeepsie | Wappingrs Fls | Dutchess | 12590 | G | 6052 | Todd Hill | N |  | 7.5 | [13 empty] | NM | N | FRONIUS IG PLUS 7.5 | 2013-04-12 | 2013-04-19 | 5 | 2013-04-19 | [14 empty] | 2013-06-07 | 2013-06-13 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03730 | Kingston | Accord |  | 12404 | G | 3024 | High Falls | TBD |  | 3.6 | [13 empty] | NM | N | POWER ONE AURORA PVI3.6-OUTD-US | 2013-04-12 | 2013-04-22 | 6 | 2013-04-22 | [17 empty] | W
Central Hudson |  | Solar Alchemy | CH-08998 | Kingston | Kerhonkson | Ulster | 12446 | G | 3082 | Kerhonkson | N |  | 8.385 | [13 empty] | NM | N | ENPHASE M215 (39) | 2013-04-12 | 2013-04-18 | 4 | 2013-04-18 | [8 empty] | 350 | 350 |  |  |  |  | 2013-11-20 | 2013-11-26 |  | Y
Central Hudson |  | Hudson Solar | CH-02354 | Fishkill | Cold Spg | Putnam | 10516 | G | 8087 | Tioronda | N |  | 5 | [13 empty] | NM | N | POWERONE PVI-5000 | 2013-04-15 | 2013-04-23 | 6 | 2013-04-23 | [14 empty] | 2013-06-20 | 2013-06-27 |  | W
Central Hudson |  | SolarCity | CH-07288 | Poughkeepsie | Hyde Park | Dutchess | 12538 | G | 7041 | Staatsburg | N |  | 7 | [13 empty] | NM | N | SMA SUNNY BOY 7000-US | 2013-04-15 | 2013-04-23 | 6 | 2013-04-23 | [14 empty] | 2013-10-02 | 2013-10-07 |  | Y
Central Hudson |  | SolarCity | CH-06176 | Newburgh | New Paltz | Ulster | 12561 | G | 5024 | Ohioville | N |  | 5.88 | [13 empty] | NM | N | SMA SUNNY BOY 7000 | 2013-04-16 | 2013-04-24 | 6 | 2013-04-24 | [14 empty] | 2013-07-22 | 2013-07-25 |  | Y
Central Hudson |  | Hudson Solar | CH-01623 | Catskill | Freehold | Greene | 12431 | G | 2071 | Freehold | Y |  | 25 | 25 | [12 empty] | NM | N | XANTREX XW4548 (2), POWERONE PVI-6000 (1) & POWERONE PVI-5000 (2)2XantrexXW4548 (DC) | 2013-04-17 | 2013-05-01 | 10 | 2013-05-01 | [8 empty] | 350 | 350 |  |  |  |  | 2013-07-05 | 2013-07-05 |  | Y
Central Hudson |  | SolarCity | CH-05950 | Poughkeepsie | Red Hook |  | 12571 | G | 7054 | Rhinebeck | TBD |  | 6 | [13 empty] | NM | N | POWER-ONE AURORA PVI 6000 | 2013-04-24 | 2013-05-01 | 5 | 2013-05-01 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | SolarCity | CH-07083 | Newburgh | Wallkill | Ulster | 12589 | G | 5043 | East Walden | N |  | 7.5 | [13 empty] | NM | N | FRONIUS IG PLUS V 7.5 | 2013-04-17 | 2013-04-24 | 5 | 2013-04-24 | [14 empty] | 2013-09-17 | 2013-09-18 |  | Y
Central Hudson |  | SolarCity | CH-07173 | Newburgh | New Windsor | Orange | 12553 | G | 4094 | Bethlehem Rd | N |  | 8.8 | [13 empty] | NM | N | SOLAREDGE SE 3800 (1) & SOLAREDGE SE5000 (1) | 2013-04-17 | 2013-04-24 | 5 | 2013-04-24 | [14 empty] | 2013-06-11 | 2013-06-18 |  | Y
Central Hudson |  | Direct Energy Solar | CH-01075 | Poughkeepsie | Clinton Corners | Dutchess | 12514 | G | 7011 | Hibernia | N | CH-00847 | 3.225 | [13 empty] | NM | N | Enphase M215 (15) | 2013-04-29 | 2013-05-07 | 6 | 2013-05-07 | [14 empty] | 2013-06-17 | 2013-06-24 |  | Y
Central Hudson |  | SolarCity | CH-06154 | Fishkill | Garrison | Putnam | 10524 | G | 8086 | Tioronda | N |  | 10 | [13 empty] | NM | N | FRONIUS IG PLUS V 10.0 | 2013-04-19 | 2013-05-02 | 9 | 2013-05-02 | [14 empty] | 2013-10-15 | 2013-10-22 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03663 | Kingston | Bloomington | Ulster | 12411 | G | 1011 | Boulevard | N |  | 9 | [13 empty] | NM | N | POWER ONE AURORA PVI3.0-OUTD-US (1) & POWER ONE AURORA PVI6000-OUTD-US (1) | 2013-04-22 | 2013-05-06 | 10 | 2013-05-06 | [8 empty] | 350 | 350 |  |  |  |  | 2013-06-24 | 2013-07-01 |  | Y
Central Hudson |  | Murphy Solar Power | CH-02737 | Catskill | Athens | Greene | 12015 | G | 2006 | North Catskill | N |  | 5 | [13 empty] | NM | N | SMA Sunny Boy 5000 US | 2013-04-22 | 2013-05-06 | 10 | 2013-05-06 | [14 empty] | 2013-08-27 | 2013-09-03 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00962 | Newburgh | Milton | Ulster | 12547 | G | 5083 | Highland | N |  | 8.385 | [13 empty] | NM | N | Enphase M215 (39) | 2013-04-23 | 2013-05-07 | 10 | 2013-05-07 | [14 empty] | 2013-07-18 | 2013-07-22 |  | Y
Central Hudson |  | Direct Energy Solar | CH-01079 | Kingston | Saugerties |  | 12477 | G | 3002 | Saugerties | TBD |  | 8.385 | [13 empty] | NM | N | ENPHASE M215 (39) | 2013-04-23 | 2013-05-07 | 10 | 2013-05-07 | [8 empty] | 350 | 350 | [7 empty] | W |  | Customer already had net meter prior to application. 10/01/14 Project abandoned as per customer.
Central Hudson |  | SolarCity | CH-06029 | Fishkill | Fishkill | Dutchess | 12524 | G | 8012 | Forgebrook | N |  | 225 | [13 empty] | NM | N | Solectria SGI 225 | 2013-06-12 | 2013-06-21 | 7 | 2013-06-21 | 2013-06-12 | 2013-06-21 | 7 | [11 empty] | 2013-11-06 | 2013-11-08 |  | Y
Central Hudson |  | Sungevity Inc | CH-09383 | Newburgh | Wallkill | Ulster | 12589 | G | 5043 | East Walden | N |  | 8.4 | [13 empty] | NM | N | POWER-ONE PVI-4.2-OUTD-S-US (2) | 2013-04-25 | 2013-05-07 | 8 | 2013-05-07 | [14 empty] | 2013-07-02 | 2013-07-10 |  | Y
Central Hudson |  | Hudson Solar | CH-01351 | Newburgh | Newburgh | Orange | 12550 | G | 4045 | Union Ave | N | CH-01351 | 6 | [13 empty] | NM | N | POWERONE PVI-6000 | 2013-05-06 | 2013-05-08 | 2 | 2013-05-08 | [14 empty] | 2013-06-19 | 2013-06-25 |  | Y
Central Hudson |  | Hudson Solar | CH-01738 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6068 | Inwood Ave | N |  | 7.2 | [13 empty] | NM | N | POWERONE PVI-3.6 (2) | 2013-04-29 | 2013-05-09 | 8 | 2013-05-09 | [14 empty] | 2013-05-24 | 2013-05-31 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Hudson Solar | CH-01860 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7062 | Milan | N |  | 8.6 | [13 empty] | NM | N | POWERONE PVI-5000 (1) & POWERONE PVI-3.6 (1) | 2013-04-29 | 2013-05-09 | 8 | 2013-05-09 | [14 empty] | 2013-08-23 | 2013-08-30 |  | Y
Central Hudson |  | SolarCity | CH-04981 | Catskill | Catskill |  | 12414 | G | 2002 | North Catskill | TBD |  | 2.45 | [13 empty] | NM | N | SolarEdge SE3000A-US | 2013-04-30 | 2013-05-09 | 7 | 2013-05-09 | [17 empty] | W |  | 9/30/14 Project abandoned as per customer.
Central Hudson |  | SolarCity | CH-07554 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7062 | Milan | Y | CH-07554 | 7 | [13 empty] | NM | N | SMA SUNNY BOY 7000 | 2013-05-01 | 2013-05-09 | 6 | 2013-05-09 | [14 empty] | 2014-08-22 | 2014-08-28 |  | Y
Central Hudson |  | Sungevity Inc | CH-09430 | Poughkeepsie | Lagrangevl | Dutchess | 12540 | G | 6051 | Todd Hill | N |  | 6 | [13 empty] | NM | N | POWER-ONE PVI-6000 | 2013-05-01 | 2013-05-09 | 6 | 2013-05-09 | [14 empty] | 2013-07-29 | 2013-08-05 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03623 | Kingston | Accord | Ulster | 12404 | G | 3024 | High Falls | N | CH-23247 | 7.5 | [13 empty] | NM | N | FRONIUS IG PLUS V 7.5 | 2013-05-02 | 2013-05-09 | 5 | 2013-05-09 | [14 empty] | 2013-06-18 | 2013-06-25 |  | Y
Central Hudson |  | SolarCity | CH-05848 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 7041 | Staatsburg | N |  | 5 | [13 empty] | NM | N | POWER-ONE AURORA PVI 5000 | 2013-05-02 | 2013-05-09 | 5 | 2013-05-09 | [14 empty] | 2013-08-01 | 2013-08-05 |  | Y
Central Hudson |  | Sungevity Inc | CH-09204 | Newburgh | New Paltz | Ulster | 12561 | G | 5031 | Galeville | N |  | 6 | [13 empty] | NM | N | POWER-ONE PVI-6000-OUTD-US | 2013-05-02 | 2013-05-09 | 5 | 2013-05-09 | [14 empty] | 2013-08-06 | 2013-08-09 |  | Y
Central Hudson |  | Sungevity Inc | CH-09566 | Kingston | Kingston | Ulster | 12401 | G | 2016 | Lincoln Park | N |  | 4.2 | [13 empty] | NM | N | POWER-ONE PVI-4.2-OUTD-S-US | 2013-05-09 | 2013-05-09 | 0 | 2013-05-09 | [14 empty] | 2013-07-18 | 2013-07-22 |  | Y
Central Hudson |  | Direct Energy Solar | CH-01040 | Poughkeepsie | Lagrangevl | Dutchess | 12540 | G | 6055 | Todd Hill | N |  | 10.75 | [13 empty] | NM | N | Enphase M215 (50) | 2013-05-08 | 2013-05-14 | 4 | 2013-05-14 | [14 empty] | 2013-11-04 | 2013-11-11 |  | Y
Central Hudson |  | SolarCity | CH-06603 | Kingston | Lk Katrine | Ulster | 12449 | G | 2016 | Lincoln Park | N |  | 11 | [13 empty] | NM | N | POWER-ONE AURORA PVI 5000 (1) & POWER-ONE AURORA PVI 6000 (1) | 2013-05-10 | 2013-05-14 | 2 | 2013-05-14 | [14 empty] | 2013-09-18 | 2013-09-25 |  | Y
Central Hudson |  | Sungevity Inc | CH-09382 | Newburgh | Wallkill | Ulster | 12589 | G | 5033 | Galeville | N |  | 6 | [13 empty] | NM | N | POWER ONE PVI-6000-OUTD-US | 2013-05-10 | 2013-05-13 | 1 | 2013-05-13 | [14 empty] | 2013-07-22 | 2013-07-25 |  | Y
Central Hudson |  | Monolith Solar Associates LLC | CH-02634 | Kingston | Lk Katrine | Ulster | 12449 | G | 2015 | Lincoln Park | N |  | 12.5 | [13 empty] | NM | N | Fronius IG Plus V 7.5 (1) & Fronius IG Plus V 5.0 (1) | 2013-05-24 | 2013-05-31 | 4 | 2013-05-31 | [8 empty] | 350 | 350 |  |  |  |  | 2013-09-09 | 2013-09-12 |  | Y
Central Hudson |  | Sungevity Inc | CH-09351 | Fishkill | Fishkill | Dutchess | 12524 | G | 8094 | Fishkill Plains | N |  | 6.6 | [13 empty] | NM | N | POWER-ONE PVI-3.0-OUTD-S-US (1) & POWER-ONE PVI-3.6-OUTD-S-US (1) | 2013-05-13 | 2013-05-15 | 2 | 2013-05-15 | [14 empty] | 2013-08-23 | 2013-08-30 |  | Y
Central Hudson |  | Conscious Energy | CH-00790 | Kingston | Saugerties | Ulster | 12477 | G | 1021 | East Kingston | N |  | 8.6 | [13 empty] | NM | N | Enphase M215 (40) | 2013-05-14 | 2013-05-29 | 10 | 2013-05-29 | [14 empty] | 2013-06-17 | 2013-06-21 |  | Y
Central Hudson |  | Hudson Solar | CH-02220 | Newburgh | Campbell Hall | Orange | 10916 | G | 5051 | Maybrook | Y |  | 7.5 | 7.5 | [12 empty] | NM | N | POWERONE PVI-3.0 (1) & XANTREX XW4548 (1)1XantrexXW4548 (DC) | 2013-05-22 | 2013-05-30 | 5 | 2013-05-30 | [14 empty] | 2013-10-03 | 2013-10-10 |  | Y
Central Hudson |  | Murphy Solar Power | CH-02711 | Catskill | Athens | Greene | 12015 | G | 1074 | Coxsackie | N |  | 4 | [13 empty] | NM | N | SMA SUNNY BOY 4000 | 2013-05-14 | 2013-05-29 | 10 | 2013-05-29 | [14 empty] | 2013-06-19 | 2013-06-19 |  | Y
Central Hudson |  | Novel Approaches | CH-02790 | Kingston | Wawarsing | Ulster | 12489 | G | 3071 | Honk Falls | N | CH-02790 | 18 | [13 empty] | NM | N | SOLAR EDGE SE6000A-US (3) | 2013-05-22 | 2013-06-06 | 10 | 2013-06-06 | [8 empty] | 350 | 350 |  |  |  |  | 2013-07-24 | 2013-07-29 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-04951 | Newburgh | Newburgh | Orange | 12550 | G | 5004 | Marlboro | N |  | 6 | [13 empty] | NM | N | SMA SUNNY BOY 6000 | 2013-05-15 | 2013-05-30 | 10 | 2013-05-30 | [14 empty] | 2013-07-18 | 2013-07-22 |  | Y
Central Hudson |  | SolarCity | CH-05117 | Kingston | Kingston | Ulster | 12401 | G | 1021 | East Kingston | N |  | 7.5 | [13 empty] | NM | N | FRONIUS IG PLUS V 7.5 | 2013-05-15 | 2013-05-30 | 10 | 2013-05-30 | [14 empty] | 2013-08-28 | 2013-09-05 |  | Y
Central Hudson |  | Sungevity Inc | CH-09254 | Catskill | Palenvl | Greene | 12463 | G | 2001 | North Catskill | N |  | 5 | [13 empty] | NM | N | POWER-ONE PVI-5000 | 2013-05-15 | 2013-05-30 | 10 | 2013-05-30 | [14 empty] | 2013-08-07 | 2013-08-09 |  | Y
Central Hudson |  | Sungevity Inc | CH-09258 | Catskill | Catskill | Greene | 12414 | G | 2042 | South Cairo | N |  | 9 | [13 empty] | NM | N | POWER ONE PVI-6000 (1) & POWER ONE PVI-3000 (1) | 2013-05-23 | 2013-06-06 | 9 | 2013-06-06 | [14 empty] | 2013-07-24 | 2013-07-24 |  | Y
Central Hudson |  | Sungevity Inc | CH-09565 | Kingston | Saugerties | Ulster | 12477 | G | 3004 | Saugerties | N |  | 3.6 | [13 empty] | NM | N | POWER-ONE PVI-3.6 | 2013-05-15 | 2013-05-30 | 10 | 2013-05-30 | [14 empty] | 2013-09-17 | 2013-09-24 |  | Y
Central Hudson |  | OnForce Solar | CH-02811 | Newburgh | New Windsor | Orange | 12553 | G | 4094 | Bethlehem Rd | N |  | 8 | [13 empty] | NM | N | POWER-ONE 8000 | 2013-05-24 | 2013-06-07 | 9 | 2013-06-07 | [14 empty] | 2013-08-20 | 2013-08-20 |  | Y
Central Hudson |  | SolarCity | CH-05610 | Kingston | Kerhonkson | Ulster | 12446 | G | 3081 | Kerhonkson | N |  | 3.6 | [13 empty] | NM | N | POWER-ONE AURORA PVI 3.6 | 2013-05-16 | 2013-05-30 | 9 | 2013-05-30 | [14 empty] | 2013-07-02 | 2013-07-10 |  | Y
Central Hudson |  | NRG Home Solar | CH-04264 | Kingston | Kingston | Ulster | 12401 | G | 1022 | East Kingston | N |  | 6 | [13 empty] | NM | N | SUNPOWER SPR 6000 | 2013-05-30 | 2013-06-06 | 5 | 2013-06-06 | [14 empty] | 2013-11-21 | 2013-12-02 |  | Y
Central Hudson |  | Sungevity Inc | CH-09402 | Kingston | Kingston | Ulster | 12401 | G | 3021 | High Falls | N |  | 6 | [13 empty] | NM | N | POWER-ONE PVI-6000 | 2013-06-03 | 2013-06-10 | 5 | 2013-06-10 | [14 empty] | 2016-09-06 | 2016-09-07 |  | Y
Central Hudson |  | New York State Solar Farm | CH-03990 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8092 | Fishkill Plains | N | CH-03990 | 6.6 | [13 empty] | NM | N | POWER ONE PVI 3.0 (1) & POWER ONE PVI 3.6 (1) | 2013-05-20 | 2013-05-31 | 8 | 2013-05-31 | [14 empty] | 2013-08-22 | 2013-08-23 |  | Y
Central Hudson |  | NRG Home Solar | CH-04486 | Newburgh | Wallkill | Ulster | 12589 | G | 5043 | East Walden | N |  | 5 | [13 empty] | NM | N | SUNPOWER SPR-5000 | 2013-05-20 | 2013-05-31 | 8 | 2013-05-31 | [14 empty] | 2013-12-26 | 2013-12-30 |  | Y
Central Hudson |  | NRG Home Solar | CH-04567 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6093 | Manchester | N |  | 6 | [13 empty] | NM | N | SUNPOWER SPR-6000 | 2013-05-20 | 2013-05-31 | 8 | 2013-05-31 | [14 empty] | 2014-03-11 | 2014-03-14 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00860 | Newburgh | Highland | Ulster | 12528 | G | 5084 | Highland | N |  | 7.525 | [13 empty] | NM | N | Enphase M215 (35) | 2013-05-20 | 2013-05-30 | 7 | 2013-05-30 | [14 empty] | 2013-10-29 | 2013-11-05 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00879 | Newburgh | Campbell Hall | Orange | 10916 | G | 5052 | Maybrook | N |  | 6.88 | [13 empty] | NM | N | Enphase M215 (32) | 2013-06-06 | 2013-06-13 | 5 | 2013-06-13 | [14 empty] | 2013-09-24 | 2013-10-01 |  | Y
Central Hudson |  | SolarCity | CH-07532 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 6074 | East Park | N |  | 3 | [13 empty] | NM | N | POWER-ONE AURORA PVI 3.0 | 2013-05-28 | 2013-05-30 | 2 | 2013-05-30 | [14 empty] | 2013-08-09 | 2013-08-15 |  | Y
Central Hudson |  | NRG Home Solar | CH-04336 | Poughkeepsie | Poughkeepsie |  | 12603 | G | 6092 | Manchester | TBD |  | 4.2 | [13 empty] | NM | N | POWER-ONE PVI-4.2-OUTD | 2013-05-21 | 2013-06-05 | 10 | 2013-06-05 | [17 empty] | W |  | Customer already had net meter prior to application. 5/27/13 Company Holiday.
Central Hudson |  | NRG Home Solar | CH-04622 | Fishkill | Beacon | Dutchess | 12508 | G | 8016 | Forgebrook | N |  | 3.6 | [13 empty] | NM | N | POWER-ONE PVI-3.6-OUTD | 2013-05-21 | 2013-06-05 | 10 | 2013-06-05 | [14 empty] | 2014-01-16 | 2014-01-22 |  | Y
Central Hudson |  | NRG Home Solar | CH-04711 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6096 | Manchester | N | CH-04711 | 3 | [13 empty] | NM | N | PowerOne PVI 3.0 | 2013-05-21 | 2013-06-05 | 10 | 2013-06-05 | [14 empty] | 2014-05-21 | 2014-05-28 |  | Y
Central Hudson |  | SolarCity | CH-07556 | Newburgh | Highland | Ulster | 12528 | G | 5082 | Highland | N |  | 7.5 | [13 empty] | NM | N | FRONIUS IG PLUS V 7.5 | 2013-05-21 | 2013-05-31 | 7 | 2013-05-31 | [14 empty] | 2013-09-27 | 2013-10-03 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06472 | Catskill | Ravena | Albany | 12143 | G | 1081 | New Baltimore | N |  | 7.2 | [13 empty] | NM | N | POWER-ONE AURORA PVI 3.0 (1) & POWER ONE AURORA PVI 4.2 (1) | 2013-05-23 | 2013-06-06 | 9 | 2013-06-06 | [14 empty] | 2013-08-02 | 2013-08-08 |  | Y
Central Hudson |  | Solar Generation | CH-08084 | Kingston | Rosendale | Ulster | 12472 | G | 1011 | Boulevard | N |  | 6 | [13 empty] | NM | N | POWER ONE PVI6000-OUTD | 2013-05-31 | 2013-06-06 | 4 | 2013-06-06 | [14 empty] | 2013-07-15 | 2013-07-18 |  | Y
Central Hudson |  | Tecta Solar | CH-09708 | Newburgh | Montgomery | Orange | 12549 | G | 5054 | Maybrook | N |  | 780 | [13 empty] | NM | N | Advanced Energy AE 260TX (3) | 2013-06-14 | 2013-07-08 | 15 | 2013-07-08 | 2013-06-14 | 2013-07-08 | 15 | [11 empty] | 2013-12-19 | 2013-12-19 |  | Y
Central Hudson |  | JJ Marquis Electrical | CH-02566 | Newburgh | Milton |  | 12547 | G | 5003 | Marlboro | N | CH-02566 | 6 | [13 empty] | NM | N | POWER ONE 6000 | 2013-06-03 | 2013-06-06 | 3 | 2013-06-06 | [14 empty] | 2013-07-16 | 2013-07-22 |  | W
Central Hudson |  | Sungevity Inc | CH-09599 | Poughkeepsie | Pine Plns | Dutchess | 12567 | G | 7091 | Pulvers Corners | N |  | 6 | [13 empty] | NM | N | POWER ONE PVI-6000 | 2013-06-25 | 2013-06-26 | 1 | 2013-06-26 | [14 empty] | 2013-09-04 | 2013-09-11 |  | Y
Central Hudson |  | Pro-Tech Energy Solutions LLC | CH-02939 | Kingston | Kingston | Ulster | 12401 | G | 2017 | Lincoln Park | N |  | 500 | [13 empty] | NM | N | Advanced Energy AE 500TX | 2013-06-14 | 2013-07-08 | 15 | 2013-07-08 | 2013-06-14 | 2013-07-08 | 15 | [11 empty] | 2013-09-03 | 2013-09-11 |  | Y
Central Hudson |  | Sol Providers | CH-08914 | Fishkill | Poughkeepsie | Dutchess | 12603 | G | 8022 | Knapps Corners | N |  | 6.45 | [13 empty] | NM | N | ENPHASE M215 (30) | 2013-05-29 | 2013-06-06 | 6 | 2013-06-06 | [14 empty] | 2013-09-11 | 2013-09-12 |  | Y
Central Hudson |  | Hudson Solar | CH-01571 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6095 | Manchester | N |  | 5 | [13 empty] | NM | N | POWERONE PVI-5000 | 2013-05-30 | 2013-06-10 | 7 | 2013-06-10 | [14 empty] | 2013-09-27 | 2013-10-04 |  | Y
Central Hudson |  | Solar Generation | CH-08257 | Newburgh | Highland | Ulster | 12528 | G | 5081 | Highland | N |  | 8.6 | [13 empty] | NM | N | SUNPOWER SPR 5000P (1) & SUNPOWER SPR 3600P (1) | 2013-06-06 | 2013-06-10 | 2 | 2013-06-10 | [14 empty] | 2013-08-20 | 2013-08-27 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03582 | Kingston | High Fls | Ulster | 12440 | G | 3022 | High Falls | N |  | 6 | [13 empty] | NM | N | POWER-ONE AURORA PVI6000-OUTD-US | 2013-06-03 | 2013-06-14 | 9 | 2013-06-14 | [14 empty] | 2013-11-06 | 2013-11-13 |  | Y
Central Hudson |  | Sungevity Inc | CH-09435 | Poughkeepsie | Pine Plns | Dutchess | 12567 | G | 7081 | Millerton | N |  | 8 | [13 empty] | NM | N | SMA AMERICA SB8000US | 2013-06-04 | 2013-06-10 | 4 | 2013-06-10 | [14 empty] | 2013-09-04 | 2013-09-11 |  | Y
Central Hudson |  | New York State Solar Farm | CH-04080 | Newburgh | Gardiner | Ulster | 12525 | G | 5011 | Modena | N |  | 11.4 | [13 empty] | NM | N | FRONIUS 11.4 | 2013-06-12 | 2013-06-13 | 1 | 2013-06-13 | [14 empty] | 2013-07-15 | 2013-07-16 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03680 | Newburgh | New Paltz | Ulster | 12561 | G | 5031 | Galeville | N |  | 4.2 | [13 empty] | NM | N | POWER ONE AURORA PVI 4.2-OUTD-US | 2013-06-10 | 2013-06-14 | 4 | 2013-06-14 | [14 empty] | 2013-08-06 | 2013-08-09 |  | Y
Central Hudson |  | Hudson Solar | CH-02399 | Poughkeepsie | Red Hook |  | 12571 | G | 7051 | Rhinebeck | TBD |  | 9.36 | [13 empty] | NM | N | POWERONE PVI-6000 (1) & POWERONE PVI-3.6 (1) | 2013-06-10 | 2013-06-19 | 7 | 2013-06-19 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | SolarCity | CH-07745 | Fishkill | Beacon | Dutchess | 12508 | G | 8087 | Tioronda | N |  | 3.6 | [13 empty] | NM | N | POWER-ONE AURORA PVI 3.6 | 2013-06-10 | 2013-06-14 | 4 | 2013-06-14 | [14 empty] | 2013-09-26 | 2013-10-03 |  | Y
Central Hudson |  | RGS Energy | CH-03037 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8045 | Myers Corners | N |  | 7.5 | [13 empty] | NM | N | FRONIUS IG PLUS 7.5 | 2013-06-11 | 2013-06-19 | 6 | 2013-06-19 | [14 empty] | 2014-05-06 | 2014-05-13 |  | Y
Central Hudson |  | NRG Home Solar | CH-04432 | Fishkill | Beacon | Dutchess | 12508 | G | 8015 | Forgebrook | N |  | 5 | [13 empty] | NM | N | SUN POWER SRP5000 | 2013-06-11 | 2013-06-20 | 7 | 2013-06-20 | [14 empty] | 2014-03-18 | 2014-03-24 |  | Y
Central Hudson |  | NRG Home Solar | CH-04684 | Newburgh | New Windsor | Orange | 12553 | G | 4094 | Bethlehem Rd | N |  | 5 | [13 empty] | NM | N | POWERONE PVI5000 | 2013-06-11 | 2013-06-20 | 7 | 2013-06-20 | [14 empty] | 2013-08-15 | 2013-08-20 |  | Y
Central Hudson |  | Hudson Solar | CH-01995 | Newburgh | Wallkill | Ulster | 12589 | G | 5030 | Galeville | N |  | 500 | [13 empty] | RNM | N | ADVANCED ENERGY AE 500TX | 2013-07-02 | 2013-07-24 | 15 | 2013-07-24 | 2013-07-02 | 2013-07-24 | 15 | [5 empty] | 5500 | 6744 |  |  |  |  | 2013-09-20 | 2013-09-26 |  | Y
Central Hudson |  | Kool-Temp | CH-02570 | Catskill | Earlton | Greene | 12058 | G | 2006 | North Catskill | N |  | 12 | [13 empty] | NM | N | CHINT CPS SCE6KTL (2) | 2013-06-11 | 2013-06-20 | 7 | 2013-06-20 | [8 empty] | 350 | 350 |  |  |  |  | 2013-10-17 | 2013-10-17 |  | Y
Central Hudson |  | NRG Home Solar | CH-04324 | Poughkeepsie | Staatsburg | Dutchess | 12580 | G | 7041 | Staatsburg | N |  | 5 | [13 empty] | NM | N | SUNPOWER SPR5000 | 2013-06-12 | 2013-06-21 | 7 | 2013-06-21 | [14 empty] | 2014-03-18 | 2014-03-25 |  | Y
Central Hudson |  | NRG Home Solar | CH-04640 | Newburgh | Newburgh | Orange | 12550 | G | 4014 | West Balmville | N |  | 6 | [13 empty] | NM | N | POWERONE PVI6000 | 2013-06-13 | 2013-06-24 | 7 | 2013-06-24 | [14 empty] | 2013-11-12 | 2013-11-19 |  | Y
Central Hudson |  | NRG Home Solar | CH-04644 | Newburgh | New Windsor | Orange | 12553 | G | 4043 | Union Ave | N |  | 5 | [13 empty] | NM | N | POWER ONE PVI5000 OUTD-US | 2013-06-13 | 2013-06-24 | 7 | 2013-06-24 | [14 empty] | 2013-08-28 | 2013-08-29 |  | Y
Central Hudson |  | Direct Energy Solar | CH-01045 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8072 | Shenandoah | N |  | 9.03 | [13 empty] | NM | N | ENPHASE M215 (42) | 2013-06-13 | 2013-06-24 | 7 | 2013-06-24 | [14 empty] | 2013-11-01 | 2013-11-08 |  | Y
Central Hudson |  | SolarCity | CH-05558 | Catskill | E Durham | Greene | 12423 | G | 2071 | Freehold | N |  | 3 | [13 empty] | NM | N | POWER-ONE PVI-3.0 | 2013-06-13 | 2013-06-24 | 7 | 2013-06-24 | [14 empty] | 2013-07-22 | 2013-07-25 |  | Y
Central Hudson |  | Paradise Energy Solutions LLC | CH-02848 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8024 | Knapps Corners | N |  | 200.7 | [13 empty] | NM | N | POWER-ONE TRIO 27.6 TL (7) & POWER-ONE UNO 2.5 (3) | 2013-07-05 | 2013-07-25 | 14 | 2013-07-25 | 2013-07-05 | 2013-07-25 | 14 | [11 empty] | 2013-10-30 | 2013-11-04 |  | Y
Central Hudson |  | SolarCity | CH-07093 | Newburgh | Modena | Ulster | 12548 | G | 5013 | Modena | N | CH-07093 | 6 | [13 empty] | NM | N | POWER-ONE PVI-3.0-OUTD-S-US (2) | 2013-06-17 | 2013-06-24 | 5 | 2013-06-24 | [14 empty] | 2013-08-12 | 2013-08-19 |  | Y
Central Hudson |  | Sungevity Inc | CH-09343 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8045 | Myers Corners | N |  | 6 | [13 empty] | NM | N | POWER-ONE PVI-6000-OUTD-US | 2013-06-17 | 2013-06-24 | 5 | 2013-06-24 | [14 empty] | 2013-08-13 | 2013-08-15 |  | Y
Central Hudson |  | Sungevity Inc | CH-09463 | Fishkill | Nelsonvl | Putnam | 10516 | G | 8087 | Tioronda | N |  | 2.5 | [13 empty] | NM | N | SMA AMERICA SB2500HFUS | 2013-06-17 | 2013-06-24 | 5 | 2013-06-24 | [14 empty] | 2013-11-13 | 2013-11-20 |  | Y
Central Hudson |  | NRG Home Solar | CH-04202 | Newburgh | Newburgh | Orange | 12550 | G | 4023 | Coldenham | N |  | 6 | [13 empty] | NM | N | POWER-ONE PVI-6000 | 2013-06-26 | 2013-07-02 | 4 | 2013-07-02 | [14 empty] | 2013-09-20 | 2013-09-27 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00961 | Newburgh | Milton | Ulster | 12547 | G | 5083 | Highland | N |  | 14.405 | [13 empty] | NM | N | ENPHASE M215 (67) | 2013-06-26 | 2013-07-02 | 4 | 2013-07-02 | [8 empty] | 350 | 350 |  |  |  |  | 2013-09-13 | 2013-09-20 |  | Y
Central Hudson |  | Kirchhoff Green Energy LLC | CH-03546 | Poughkeepsie | Clinton Corners | Dutchess | 12514 | G | 7071 | Stanfordville | N |  | 10 | [13 empty] | NM | N | FRONUIS 10.0-1 | 2013-07-01 | 2013-07-05 | 3 | 2013-07-05 | [14 empty] | 2013-10-16 | 2013-10-23 |  | Y
Central Hudson |  | Direct Energy Solar | CH-01016 | Fishkill | Stormvl | Dutchess | 12582 | G | 8071 | Shenandoah | N |  | 6.665 | [13 empty] | NM | N | ENPHASE M215 (31) | 2013-06-27 | 2013-07-02 | 3 | 2013-07-02 | [14 empty] | 2013-08-01 | 2013-08-02 |  | Y
Central Hudson |  | Hollitronics Energy Solutions | CH-01208 | Catskill | Freehold | Greene | 12431 | G | 2071 | Freehold | N |  | 4.284 | [13 empty] | NM | N | SOLARBRIDGE P250HV-208/240 (18) | 2013-07-08 | 2013-07-09 | 1 | 2013-07-09 | [14 empty] | 2013-08-29 | 2013-09-05 |  | Y
Central Hudson |  | Hudson Solar | CH-01414 | Newburgh | New Paltz | Ulster | 12561 | G | 5012 | Modena | N |  | 6 | [13 empty] | NM | N | POWERONE PVI-6000 | 2013-06-27 | 2013-07-02 | 3 | 2013-07-02 | [14 empty] | 2013-08-28 | 2013-09-05 |  | Y
Central Hudson |  | Hudson Solar | CH-01611 | Catskill | Rensselaervl | Albany | 12147 | G | 1092 | Westerlo | N |  | 6 | [13 empty] | NM | N | POWERONE PVI-6000 | 2013-06-20 | 2013-06-26 | 4 | 2013-06-26 | [14 empty] | 2013-09-20 | 2013-09-27 |  | Y
Central Hudson |  | Hudson Solar | CH-01628 | Catskill | Westerlo | Albany | 12193 | G | 1091 | Westerlo | N |  | 6 | [13 empty] | NM | N | POWERONE PVI-3.0 (2) | 2013-06-20 | 2013-06-26 | 4 | 2013-06-26 | [14 empty] | 2013-07-12 | 2013-07-17 |  | Y
Central Hudson |  | SolarCity | CH-05650 | Kingston | High Fls | Ulster | 12440 | G | 3024 | High Falls | N |  | 6 | [13 empty] | NM | N | POWER ONE PVI-3.0-OUTD-S-US (2) | 2013-06-20 | 2013-06-26 | 4 | 2013-06-26 | [14 empty] | 2013-08-27 | 2013-08-30 |  | Y
Central Hudson |  | SolarCity | CH-05896 | Poughkeepsie | Lagrangevl | Dutchess | 12540 | G | 6055 | Todd Hill | N |  | 3.6 | [13 empty] | NM | N | POWERON PVI 3.6 | 2013-06-20 | 2013-06-26 | 4 | 2013-06-26 | [14 empty] | 2013-11-19 | 2013-11-26 |  | Y
Central Hudson |  | SolarCity | CH-06170 | Newburgh | New Paltz | Ulster | 12561 | G | 5024 | Ohioville | N |  | 7 | [13 empty] | NM | N | SMA AMERICA SB7000US | 2013-06-20 | 2013-06-26 | 4 | 2013-06-26 | [14 empty] | 2013-09-13 | 2013-09-20 |  | Y
Central Hudson |  | Hudson Solar | CH-01309 | Poughkeepsie | Tivoli |  | 12583 | G | 7051 | Rhinebeck | TBD |  | 36 | [13 empty] | NM | N | POWERONE PVI-6000 (6) | 2013-06-21 | 2013-07-05 | 9 | 2013-07-05 | 2013-06-21 | 2013-07-05 | 9 | [5 empty] | 1776 | 1776 | [7 empty] | W |  | Transformer upgrade required to accommodate PV installation.
Central Hudson |  | Hudson Solar | CH-01549 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6096 | Manchester | N |  | 4.2 | [13 empty] | NM | N | POWERONE PVI-4.2 | 2013-06-21 | 2013-07-03 | 8 | 2013-07-03 | [14 empty] | 2013-07-31 | 2013-08-05 |  | Y
Central Hudson |  | Hudson Solar | CH-01742 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7041 | Staatsburg | N |  | 15.6 | [13 empty] | NM | N | POWERONE PVI-6000 (2) & POWERONE PVI-3.6 (1) | 2013-06-21 | 2013-07-03 | 8 | 2013-07-03 | [14 empty] | 2013-09-27 | 2013-10-04 |  | Y
Central Hudson |  | Hudson Solar | CH-01774 | Poughkeepsie | Millbrook |  | 12545 | G | 7012 | Hibernia | TBD |  | 7.2 | [13 empty] | NM | N | POWERONE PVI-3.6 (2) | 2013-06-21 | 2013-07-02 | 7 | 2013-07-02 | [17 empty] | W |  | 9/27/14 Project abandoned as per customer.
Central Hudson |  | Hudson Solar | CH-02055 | Kingston | Saugerties | Ulster | 12477 | G | 2016 | Lincoln Park | N |  | 7.2 | [13 empty] | NM | N | POWERONE PVI-3.6 (2) | 2013-08-01 | 2013-08-05 | 2 | 2013-08-05 | [14 empty] | 2013-08-16 | 2013-08-23 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Hudson Solar | CH-02164 | Newburgh | Highland | Ulster | 12528 | G | 5082 | Highland | N |  | 8.4 | [13 empty] | NM | N | POWERONE PVI-4.2 (2) | 2013-06-21 | 2013-07-02 | 7 | 2013-07-02 | [14 empty] | 2013-07-24 | 2013-07-31 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03751 | Newburgh | New Paltz | Ulster | 12561 | G | 5031 | Galeville | N |  | 6 | [13 empty] | NM | N | POWER ONE AURORA PVI6000-OUTD-US | 2013-06-24 | 2013-07-05 | 8 | 2013-07-05 | [14 empty] | 2013-09-30 | 2013-10-04 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03562 | Fishkill | Garrison | Putnam | 10524 | G | 8066 | Merritt Park | N | CH-03562 | 6 | [13 empty] | NM | N | POWER-ONE AURORA PVI6000-OUTD-US | 2013-06-26 | 2013-07-05 | 6 | 2013-07-05 | [14 empty] | 2013-10-21 | 2013-10-28 |  | Y
Central Hudson |  | Sungevity Inc | CH-09244 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8043 | Myers Corners | N | CH-09244 | 7 | [13 empty] | NM | N | SMA AMERICA SB7000US | 2013-06-26 | 2013-07-05 | 6 | 2013-07-05 | [14 empty] | 2013-08-23 | 2013-08-30 |  | Y
Central Hudson |  | Sungevity Inc | CH-09370 | Newburgh | Highland | Ulster | 12528 | G | 5081 | Highland | N |  | 7.6 | [13 empty] | NM | N | POWER-ONE PVI-3.8-OUTD-S-US (2) | 2013-06-26 | 2013-07-05 | 6 | 2013-07-05 | [14 empty] | 2014-01-23 | 2014-01-30 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00946 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7062 | Milan | N |  | 7.31 | [13 empty] | NM | N | ENPHASE M215 (34) | 2013-06-27 | 2013-07-05 | 5 | 2013-07-05 | [14 empty] | 2013-08-28 | 2013-09-05 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00959 | Newburgh | New Paltz | Ulster | 12561 | G | 5024 | Ohioville | N |  | 10.965 | [13 empty] | NM | N | ENPHASE M215 (51) | 2013-07-05 | 2013-07-05 | 0 | 2013-07-05 | [14 empty] | 2013-09-11 | 2013-09-18 |  | Y
Central Hudson |  | SolarCity | CH-06397 | Newburgh | Cornwall | Orange | 12518 | G | 4041 | Union Ave | N |  | 3 | [13 empty] | NM | N | SOLAREDGE SE3000A-US | 2013-07-05 | 2013-07-05 | 0 | 2013-07-05 | [14 empty] | 2013-09-18 | 2013-09-25 |  | Y
Central Hudson |  | SolarCity | CH-06793 | Fishkill | Wappingers Falls | Dutchess | 12590 | G | 8091 | Fishkill Plains | N |  | 6 | [13 empty] | NM | N | POWER ONE PVI-6000-OUTD-US | 2013-06-28 | 2013-07-05 | 4 | 2013-07-05 | [14 empty] | 2013-08-12 | 2013-08-15 |  | Y
Central Hudson |  | NRG Home Solar | CH-04383 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8044 | Myers Corners | N |  | 4.2 | [13 empty] | NM | N | POWER ONE PVI4.2 OUTD-S-US | 2013-07-01 | 2013-07-05 | 3 | 2013-07-05 | [14 empty] | 2014-02-19 | 2014-02-26 |  | Y
Central Hudson |  | RGS Energy | CH-03049 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8071 | Shenandoah | N |  | 11 | [13 empty] | NM | N | FRONIUS IG PLUS 6.0 (1) & FRONIUS IG PLUS 5.0 (1) | 2013-07-10 | 2013-07-16 | 4 | 2013-07-16 | [14 empty] | 2013-10-30 | 2013-10-31 |  | Y
Central Hudson |  | Lotus Energy Inc. | CH-03844 | Poughkeepsie | Ancram | Columbia | 12502 | G | 7091 | Pulvers Corners | N |  | 16 | [13 empty] | NM | N | SUNPOWER SPR8000M (2) | 2013-07-10 | 2013-07-16 | 4 | 2013-07-16 | [14 empty] | 2013-08-19 | 2013-08-26 |  | Y
Central Hudson |  | CPC Contracting Group | CH-00811 | Kingston | Kingston | Ulster | 12401 | G | 2093 | Hurley Ave | N |  | 5 | [13 empty] | NM | N | SMA Sunny Boy 5000 | 2013-07-19 | 2013-07-19 | 0 | 2013-07-19 | [14 empty] | 2015-06-03 | 2015-06-03 |  | Y
Central Hudson |  | SolarCity | CH-05619 | Kingston | High Fls | Ulster | 12440 | G | 3024 | High Falls | N |  | 4.2 | [13 empty] | NM | N | POWER-ONE PVI-4.2-OUTD-S-US | 2013-07-09 | 2013-07-09 | 0 | 2013-07-09 | [14 empty] | 2013-08-27 | 2013-08-29 |  | Y
Central Hudson |  | NRG Home Solar | CH-04158 | Newburgh | Modena | Ulster | 12548 | G | 5012 | Modena | N | CH-04158 | 6 | [13 empty] | NM | N | POWER-ONE PVI-6000 | 2013-07-03 | 2013-07-11 | 5 | 2013-07-11 | [14 empty] | 2013-09-06 | 2013-09-09 |  | Y
Central Hudson |  | NRG Home Solar | CH-04312 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6042 | Spackenkill | N |  | 5 | [13 empty] | NM | N | SUNPOWER SPR-5000 | 2013-07-18 | 2013-07-22 | 2 | 2013-07-22 | [14 empty] | 2014-09-05 | 2014-09-08 |  | Y
Central Hudson |  | NRG Home Solar | CH-04389 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8043 | Myers Corners | N |  | 6 | [13 empty] | NM | N | POWER-ONE PVI-6000-OUTD | 2013-07-03 | 2013-07-11 | 5 | 2013-07-11 | [14 empty] | 2013-12-06 | 2013-12-13 |  | Y
Central Hudson |  | NRG Home Solar | CH-04752 | Catskill | Durham | Greene | 12422 | G | 1092 | Westerlo | N |  | 6 | [13 empty] | NM | N | POWER-ONE PVI-6000-OUTD | 2013-07-03 | 2013-07-11 | 5 | 2013-07-11 | [14 empty] | 2013-11-20 | 2013-11-26 |  | Y
Central Hudson |  | CB&I | CH-00768 | Newburgh | Newburgh | Orange | 12550 | G | 4091 | Bethlehem Rd | Y |  | 258 | 120 | [12 empty] | NA | N | PRINCETON POWER SYSTEM GTIB-30-480BGNSC (4) & POWERONE TRIO-27.6-TL-OUTD (5)4PRINCETON POWER SYSTEMGTIB-30-480BGNSC | 2014-02-27 | 2014-03-18 | 13 | 2014-03-18 | 2014-02-27 | 2014-03-18 | 13 | 2014-04-08 | 2014-04-08 | 2014-06-10 | 43 | 3057 | [6 empty] | 2015-05-06 | 2015-05-12 |  | Y
Central Hudson |  | SolarCity | CH-05546 | Catskill | Greenvl | Greene | 12083 | G | 2061 | Freehold | N |  | 4.2 | [13 empty] | NM | N | POWER-ONE PVI-4.2-OUTD-S-US | 2013-07-12 | 2013-07-16 | 2 | 2013-07-16 | [14 empty] | 2013-09-11 | 2013-09-17 |  | Y
Central Hudson |  | SolarCity | CH-07626 | Catskill | Catskill | Greene | 12414 | G | 2003 | North Catskill | N |  | 3 | [13 empty] | NM | N | POWER-ONE PVI03.0-OUTD-S-US | 2013-07-15 | 2013-07-16 | 1 | 2013-07-16 | [14 empty] | 2013-09-06 | 2013-09-13 |  | Y
Central Hudson |  | Lotus Energy Inc. | CH-03894 | Catskill | Catskill |  | 12414 | G | 2003 | North Catskill | TBD |  | 3 | [13 empty] | NM | N | SUNPOWER SPR3000 | 2013-07-08 | 2013-07-12 | 4 | 2013-07-12 | [14 empty] | 2013-09-23 | 2013-09-30 |  | W
Central Hudson |  | Murphy Solar Power | CH-02750 | Catskill | Athens | Greene | 12015 | G | 1074 | Coxsackie | N |  | 3 | [13 empty] | NM | N | SMA SUNNY BOY 3000 | 2013-07-19 | 2013-07-25 | 4 | 2013-07-25 | [14 empty] | 2013-08-27 | 2013-09-03 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00849 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 6092 | Manchester | N |  | 6.88 | [13 empty] | NM | N | ENPHASE M215 (32) | 2013-07-09 | 2013-07-16 | 5 | 2013-07-16 | [14 empty] | 2013-08-22 | 2013-08-29 |  | Y
Central Hudson |  | SolarCity | CH-06535 | Kingston | Woodstock | Ulster | 12498 | G | 3013 | Woodstock | N |  | 3.64 | [13 empty] | NM | N | SOLAREDGE SE3800A-US | 2013-07-17 | 2013-07-17 | 0 | 2013-07-17 | [14 empty] | 2013-10-07 | 2013-10-07 |  | Y
Central Hudson |  | Green Energy Systems | CH-01159 | Catskill | S Cairo | Greene | 12482 | G | 2005 | North Catskill | N |  | 8.385 | [13 empty] | NM | N | ENPHASE M215 (39) | 2013-12-02 | 2013-12-05 | 3 | 2013-12-05 | [14 empty] | 2015-05-04 | 2015-05-14 |  | Y
Central Hudson |  | SolarCity | CH-06193 | Newburgh | Newburgh | Orange | 12550 | G | 5004 | Marlboro | N |  | 3 | [13 empty] | NM | N | POWER-ONE PVI-3.0 | 2013-07-17 | 2013-07-17 | 0 | 2013-07-17 | [14 empty] | 2013-09-27 | 2013-10-04 |  | Y
Central Hudson |  | SolarCity | CH-06513 | Kingston | Kingston | Ulster | 12401 | G | 1022 | East Kingston | N |  | 4.2 | [13 empty] | NM | N | POWER-ONE PVI-4.2 | 2013-07-11 | 2013-07-17 | 4 | 2013-07-17 | [14 empty] | 2013-09-12 | 2013-09-19 |  | Y
Central Hudson |  | SolarCity | CH-06533 | Kingston | Shokan | Ulster | 12481 | G | 3011 | Woodstock | N | CH-06533 | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A-US | 2013-07-11 | 2013-07-17 | 4 | 2013-07-17 | [14 empty] | 2013-10-24 | 2013-10-31 |  | Y
Central Hudson |  | SolarCity | CH-06945 | Fishkill | Beacon | Dutchess | 12508 | G | 8087 | Tioronda | N |  | 3.6 | [13 empty] | NM | N | POWER-ONE PVI-3.6 | 2013-07-11 | 2013-07-17 | 4 | 2013-07-17 | [14 empty] | 2013-10-02 | 2013-10-07 |  | Y
Central Hudson |  | SolarCity | CH-06972 | Newburgh | Newburgh | Orange | 12550 | G | 5001 | Marlboro | N |  | 6 | [13 empty] | NM | N | POWER-ONE PVI-6000 | 2013-07-11 | 2013-07-17 | 4 | 2013-07-17 | [14 empty] | 2013-08-21 | 2013-08-27 |  | Y
Central Hudson |  | Sungevity Inc | CH-09442 | Newburgh | Highland | Ulster | 12528 | G | 5084 | Highland | N |  | 4.2 | [13 empty] | NM | N | POWER-ONE PVI-4.2 | 2013-07-12 | 2013-07-17 | 3 | 2013-07-17 | [14 empty] | 2013-08-19 | 2013-08-26 |  | Y
Central Hudson |  | NRG Home Solar | CH-04355 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7054 | Rhinebeck | N |  | 5 | [13 empty] | NM | N | SUNPOWER SPR-5000M | 2013-07-19 | 2013-07-19 | 0 | 2013-07-19 | [14 empty] | 2014-01-16 | 2014-01-23 |  | Y
Central Hudson |  | Hudson Solar | CH-01629 | Catskill | Westerlo | Albany | 12193 | G | 1091 | Westerlo | N |  | 8 | [13 empty] | NM | N | POWERONE PVI-3.0 (1) & POWERONE PVI-5000 (1) | 2013-07-15 | 2013-07-18 | 3 | 2013-07-18 | [14 empty] | 2013-09-09 | 2013-09-16 |  | Y
Central Hudson |  | Hudson Solar | CH-01919 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8045 | Myers Corners | N |  | 4.2 | [13 empty] | NM | N | POWERONE PVI-4.2 | 2013-07-15 | 2013-07-18 | 3 | 2013-07-18 | [14 empty] | 2013-07-25 | 2013-08-01 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | NRG Home Solar | CH-04571 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6092 | Manchester | N |  | 5 | [13 empty] | NM | N | POWER-ONE PVI-5000 | 2013-07-16 | 2013-07-19 | 3 | 2013-07-19 | [14 empty] | 2013-11-15 | 2013-11-22 |  | Y
Central Hudson |  | NRG Home Solar | CH-04720 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8094 | Fishkill Plains | N |  | 6 | [13 empty] | NM | N | POWER-ONE PVI-6000 | 2013-07-16 | 2013-07-19 | 3 | 2013-07-19 | [14 empty] | 2013-10-28 | 2013-11-04 |  | Y
Central Hudson |  | NRG Home Solar | CH-04786 | Fishkill | Stormvl |  | 12582 | G | 8071 | Shenandoah | TBD |  | 3 | [13 empty] | NM | N | POWER-ONE PVI-3.0 | 2013-07-16 | 2013-07-19 | 3 | 2013-07-19 | [17 empty] | W
Central Hudson |  | Solar Generation | CH-08114 | Kingston | Saugerties | Ulster | 12477 | G | 3014 | Woodstock | N |  | 10 | [13 empty] | NM | N | POWER ONE PVI-10.0 | 2013-07-16 | 2013-07-19 | 3 | 2013-07-19 | [14 empty] | 2013-08-26 | 2013-08-30 |  | Y
Central Hudson |  | SunBlue Energy | CH-09130 | Newburgh | New Windsor | Orange | 12553 | G | 4054 | Union Ave | N |  | 3.87 | [13 empty] | NM | N | ENPHASE M215 (18) | 2013-07-24 | 2013-08-02 | 7 | 2013-08-02 | [14 empty] | 2013-09-06 | 2013-09-10 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03668 | Kingston | Kerhonkson | Ulster | 12446 | G | 3081 | Kerhonkson | N |  | 6 | [13 empty] | NM | N | POWER ONE AURORA PVI6000-OUTD-US | 2013-07-17 | 2013-07-22 | 3 | 2013-07-22 | [14 empty] | 2013-09-19 | 2013-09-26 |  | Y
Central Hudson |  | RGS Energy | CH-03003 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8092 | Fishkill Plains | N | CH-03003 | 7.5 | [13 empty] | NM | N | FRONIUS IG PLUS V 7.5 | 2013-07-19 | 2013-07-24 | 3 | 2013-07-24 | [14 empty] | 2013-10-07 | 2013-10-11 |  | Y
Central Hudson |  | NRG Home Solar | CH-04547 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6011 | Sand Dock | N |  | 6 | [13 empty] | NM | N | POWER-ONE PVI-6000 | 2013-07-19 | 2013-07-25 | 4 | 2013-07-25 | [14 empty] | 2013-09-20 | 2013-09-27 |  | Y
Central Hudson |  | NRG Home Solar | CH-04802 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 6 | [13 empty] | NM | N | POWER-ONE PVI 6.0 | 2013-07-19 | 2013-07-25 | 4 | 2013-07-25 | [14 empty] | 2013-11-19 | 2013-11-26 |  | Y
Central Hudson |  | Murphy Solar Power | CH-02721 | Catskill | Cairo | Greene | 12413 | G | 2043 | South Cairo | N |  | 7 | [13 empty] | NM | N | SMA SUNNY BOY 7000 | 2013-07-19 | 2013-07-24 | 3 | 2013-07-24 | [14 empty] | 2013-08-27 | 2013-09-03 |  | Y
Central Hudson |  | SolarCity | CH-05565 | Catskill | Westerlo | Albany | 12193 | G | 1091 | Westerlo | N |  | 4.2 | [13 empty] | NM | N | POWER-ONE PVI-4.2 | 2013-07-19 | 2013-07-25 | 4 | 2013-07-25 | [14 empty] | 2013-08-28 | 2013-09-05 |  | Y
Central Hudson |  | Sungevity Inc | CH-09549 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 5 | [13 empty] | NM | N | POWER-ONE PVI-5000 | 2013-07-19 | 2013-07-24 | 3 | 2013-07-24 | [14 empty] | 2013-10-21 | 2013-10-28 |  | Y
Central Hudson |  | Verengo Solar | CH-09762 | Newburgh | Salisbury Mls | Orange | 12577 | G | 4097 | Bethlehem Rd | N | CH-09762 | 9 | [13 empty] | NM | N | POWERONE PVI 6000 (1) & POWERONE PVI 3000 (1) | 2013-07-24 | 2013-07-24 | 0 | 2013-07-24 | [14 empty] | 2013-09-09 | 2013-09-10 |  | Y
Central Hudson |  | NRG Home Solar | CH-04683 | Newburgh | Montgomery | Orange | 12549 | G | 5073 | Montgomery | N | CH-04683 | 6 | [13 empty] | NM | N | POWER-ONE PVI-6000 | 2013-07-22 | 2013-07-25 | 3 | 2013-07-25 | [14 empty] | 2013-10-10 | 2013-10-16 |  | Y
Central Hudson |  | SolarCity | CH-05313 | Newburgh | New Windsor | Orange | 12553 | G | 4094 | Bethlehem Rd | N |  | 3.8 | [13 empty] | NM | N | SOLAREDGE SE3800A-US | 2013-07-22 | 2013-07-25 | 3 | 2013-07-25 | [14 empty] | 2013-09-16 | 2013-09-19 |  | Y
Central Hudson |  | SolarCity | CH-06080 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8092 | Fishkill Plains | N |  | 6 | [13 empty] | NM | N | POWER-ONE PVI-3.0 (2) | 2013-07-23 | 2013-07-29 | 4 | 2013-07-29 | [14 empty] | 2013-09-12 | 2013-09-19 |  | Y
Central Hudson |  | Solar Generation | CH-08240 | Kingston | Saugerties | Ulster | 12477 | G | 3003 | Saugerties | N |  | 6 | [13 empty] | NM | N | SPR-6000P | 2013-07-23 | 2013-07-26 | 3 | 2013-07-26 | [14 empty] | 2013-09-09 | 2013-09-16 |  | Y
Central Hudson |  | NRG Home Solar | CH-04469 | Newburgh | Newburgh | Orange | 12550 | G | 4015 | West Balmville | N |  | 6 | [13 empty] | NM | N | POWER-ONE PVI-6000 | 2013-07-24 | 2013-08-05 | 8 | 2013-08-05 | [14 empty] | 2013-11-19 | 2013-11-26 |  | Y
Central Hudson |  | NRG Home Solar | CH-04777 | Newburgh | Newburgh | Orange | 12550 | G | 4051 | Union Ave | N |  | 6 | [13 empty] | NM | N | POWER-ONE PVI-6000 | 2013-07-24 | 2013-08-05 | 8 | 2013-08-05 | [14 empty] | 2013-11-04 | 2013-11-19 |  | Y
Central Hudson |  | Amberjack Solar Energy LLC | CH-00651 | Poughkeepsie | Poughkeepsie |  | 12603 | G | 6052 | Todd Hill | TBD |  | 150 | [13 empty] | NM | N | SMA Sunny Boy 10000TL-US (15) | 2014-01-30 | 2014-02-21 | 15 | 2014-02-21 | 2014-01-30 | 2014-02-21 | 15 | 2015-02-23 | 2015-06-05 | 2015-08-31 | 60 | 14450 | 8750 | [8 empty] | W
Central Hudson |  | SolarCity | CH-05491 | Catskill | Palenvl | Greene | 12463 | G | 2042 | South Cairo | N |  | 6 | [13 empty] | NM | N | POWER ONE PVI-6000-OUTD-US | 2013-08-08 | 2013-08-13 | 3 | 2013-08-13 | [14 empty] | 2013-10-25 | 2013-11-01 |  | Y
Central Hudson |  | SolarCity | CH-06969 | Newburgh | Newburgh | Orange | 12550 | G | 4013 | West Balmville | N |  | 3.8 | [13 empty] | NM | N | POWER ONE PVI-3.8-I-OUTD-S-US | 2013-07-26 | 2013-08-02 | 5 | 2013-08-02 | [14 empty] | 2014-02-03 | 2014-02-03 |  | Y
Central Hudson |  | Novel Approaches | CH-02791 | Kingston | Grahamsvl | Sullivan | 12740 | G | 3091 | Neversink | N | CH-02791 | 12 | [13 empty] | NM | N | SOLAR EDGE SE6000A-US (2) | 2013-08-06 | 2013-08-07 | 1 | 2013-08-07 | [8 empty] | 350 | 350 |  |  |  |  | 2013-10-15 | 2013-10-22 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Paradise Energy Solutions LLC | CH-02825 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8046 | Myers Corners | N |  | 8 | [13 empty] | NM | N | SMA SB 4000TL-US (2) | 2013-08-07 | 2013-08-13 | 4 | 2013-08-13 | [14 empty] | 2014-01-20 | 2014-01-30 |  | Y
Central Hudson |  | SolarCity | CH-05717 | Kingston | Saugerties | Ulster | 12477 | G | 3003 | Saugerties | N |  | 18.9 | [13 empty] | NM | N | FRONIUS USA IG PLUS V 11.4 (1) & FRONIUS USA IG PLUS V 7.5 (1) | 2013-07-31 | 2013-08-05 | 3 | 2013-08-05 | [14 empty] | 2013-09-13 | 2013-09-20 |  | Y
Central Hudson |  | SolarCity | CH-07374 | Fishkill | Beacon | Dutchess | 12508 | G | 8015 | Forgebrook | N | CH-07374 | 3.8 | [13 empty] | NM | N | SOLAREDGE SE3800A-US | 2013-07-31 | 2013-08-05 | 3 | 2013-08-05 | [14 empty] | 2013-10-02 | 2013-10-07 |  | Y
Central Hudson |  | Solar Generation | CH-08219 | Kingston | Bearsvl | Ulster | 12409 | G | 3012 | Woodstock | N |  | 3.6 | [13 empty] | NM | N | SUNPOWER SPR-3600P | 2013-07-31 | 2013-08-05 | 3 | 2013-08-05 | [14 empty] | 2013-09-16 | 2013-09-23 |  | Y
Central Hudson |  | Novel Approaches | CH-02789 | Kingston | Grahamsvl | Sullivan | 12740 | G | 3091 | Neversink | N |  | 6 | [13 empty] | NM | N | SOLAR EDGE SE6000A-US | 2013-08-06 | 2013-08-07 | 1 | 2013-08-07 | [14 empty] | 2013-10-15 | 2013-10-22 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-05592 | Catskill | W Coxsackie | Greene | 12192 | G | 1071 | Coxsackie | N | CH-05592 | 6 | [13 empty] | NM | N | POWER ONE PVI 6000 | 2013-08-01 | 2013-08-05 | 2 | 2013-08-05 | [14 empty] | 2013-09-18 | 2013-09-25 |  | Y
Central Hudson |  | SolarCity | CH-07848 | Kingston | Stone Ridge |  | 12484 | G | 3024 | High Falls | TBD |  | 5 | [13 empty] | NM | N | SOLAREDGE TECH SE5000A-US | 2013-08-02 | 2013-08-08 | 4 | 2013-08-08 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | Solar Energy World LLC | CH-09022 | Kingston | Greenfield Pk | Ulster | 12435 | G | 3095 | Grimley Rd | N |  | 8.93 | [13 empty] | NM | N | SMA Sunny Boy 6000 (1) & SMA Sunny Boy 3000 (1) | 2013-10-04 | 2013-10-07 | 1 | 2013-10-07 | [14 empty] | 2013-12-23 | 2013-12-23 |  | Y
Central Hudson |  | Direct Energy Solar | CH-01061 | Kingston | Port Ewen | Ulster | 12466 | G | 1012 | Boulevard | N |  | 6.235 | [13 empty] | NM | N | ENPHASE M215 (29) | 2013-08-05 | 2013-08-09 | 4 | 2013-08-09 | [14 empty] | 2013-09-06 | 2013-09-13 |  | Y
Central Hudson |  | SolarCity | CH-05697 | Kingston | Kingston | Ulster | 12401 | G | 2093 | Hurley Ave | N |  | 3 | [13 empty] | NM | N | POWER-ONE PVI-3.0-OUTD | 2013-08-05 | 2013-08-09 | 4 | 2013-08-09 | [14 empty] | 2013-12-06 | 2013-12-13 |  | Y
Central Hudson |  | SolarCity | CH-06184 | Newburgh | Clintondale | Ulster | 12515 | G | 5081 | Highland | N |  | 7.5 | [13 empty] | NM | N | FRONIUS IG PLUS V 7.5 | 2013-08-05 | 2013-08-09 | 4 | 2013-08-09 | [14 empty] | 2013-10-21 | 2013-10-28 |  | Y
Central Hudson |  | SolarCity | CH-07923 | Newburgh | New Windsor |  | 12553 | G | 4094 | Bethlehem Rd | TBD |  | 5.75 | [13 empty] | NM | N | SOLAREDGE SE6000A-US | 2013-08-05 | 2013-08-09 | 4 | 2013-08-09 | [17 empty] | W
Central Hudson |  | RGS Energy | CH-03030 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6043 | Spackenkill | N |  | 8 | [13 empty] | NM | N | POWERONE PVI-5000 (1) & POWERONE PVI-3.0 (1) | 2013-08-09 | 2013-08-09 | 0 | 2013-08-09 | [14 empty] | 2014-01-09 | 2014-01-15 |  | Y
Central Hudson |  | SolarCity | CH-07205 | Kingston | Tillson | Ulster | 12486 | G | 3022 | High Falls | N |  | 3 | [13 empty] | NM | N | SOLAREDGE SE3000A-US | 2013-08-06 | 2013-08-09 | 3 | 2013-08-09 | [14 empty] | 2013-09-25 | 2013-10-02 |  | Y
Central Hudson |  | SolarCity | CH-07504 | Kingston | Kerhonkson | Ulster | 12446 | G | 3081 | Kerhonkson | N |  | 10 | [13 empty] | NM | N | FRONIUS USA IG PLUS V 10.0 | 2013-08-06 | 2013-08-09 | 3 | 2013-08-09 | [14 empty] | 2013-12-18 | 2013-12-19 |  | Y
Central Hudson |  | SolarCity | CH-06497 | Kingston | High Fls |  | 12440 | G | 3024 | High Falls | TBD |  | 1.96 | [13 empty] | NM | N | SOLAREDGE SE3000A-US | 2013-08-07 | 2013-08-09 | 2 | 2013-08-09 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | SolarCity | CH-05018 | Kingston | Lk Katrine | Ulster | 12449 | G | 2016 | Lincoln Park | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A-US | 2013-10-07 | 2013-10-11 | 4 | 2013-10-11 | [14 empty] | 2013-10-23 | 2013-10-30 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-05346 | Newburgh | Marlboro | Ulster | 12542 | G | 5004 | Marlboro | N |  | 10 | [13 empty] | NM | N | SOLAREDGE SE5000A-US (2) | 2013-08-08 | 2013-08-13 | 3 | 2013-08-13 | [14 empty] | 2013-11-11 | 2013-11-18 |  | Y
Central Hudson |  | SolarCity | CH-07706 | Poughkeepsie | Tivoli | Dutchess | 12583 | G | 7062 | Milan | N |  | 15 | [13 empty] | NM | N | FRONIUS USA IG PLUS V 7.5 (2) | 2013-08-08 | 2013-08-14 | 4 | 2013-08-14 | [14 empty] | 2014-01-29 | 2014-02-05 |  | Y
Central Hudson |  | New York State Solar Farm | CH-03998 | Newburgh | Newburgh | Orange | 12550 | G | 5001 | Marlboro | N |  | 7.5 | [13 empty] | NM | N | POWERONE 5000; POWERONE 2.5 | 2013-08-09 | 2013-08-16 | 5 | 2013-08-16 | [14 empty] | 2013-09-23 | 2013-09-27 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00886 | Catskill | Preston Holw | Albany | 12469 | G | 1092 | Westerlo | N | CH-00886 | 7.31 | [13 empty] | RNM | N | ENPHASE ENERGY M215 (34) | 2013-08-09 | 2013-08-14 | 3 | 2013-08-14 | [14 empty] | 2013-10-21 | 2013-10-28 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00887 | Catskill | Preston Holw |  | 12469 | G | 1092 | Westerlo | TBD |  | 4.945 | [13 empty] | NM | N | ENPHASE ENERGY M215 (23) | 2013-08-09 | 2013-08-14 | 3 | 2013-08-14 | [15 empty] | 2013-10-28 |  | W |  | Customer already had net meter prior to application. As per email from customer on 6/30/14 this project has been abandoned. This system will be interconnected as an expansion on 1272-0220-00.
Central Hudson |  | SolarCity | CH-07516 | Kingston | Kingston | Ulster | 12401 | G | 2013 | Lincoln Park | N |  | 3 | [13 empty] | NM | N | SOLAREDGE SE3000A-US | 2013-08-09 | 2013-08-15 | 4 | 2013-08-15 | [14 empty] | 2013-09-26 | 2013-10-03 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-03479 | Kingston | Woodstock |  | 12498 | G | 3014 | Woodstock | TBD |  | 5.886 | [13 empty] | NM | N | POWERONE PVI6000 | 2013-08-19 | 2013-08-23 | 4 | 2013-08-23 | [17 empty] | W |  | 8/19/13 Incomplete issued. 9/30/14 Project abandoned as per customer.
Central Hudson |  | Hudson Solar | CH-01973 | Newburgh | Gardiner | Ulster | 12525 | G | 5034 | Galeville | N |  | 6 | [13 empty] | NM | N | POWERONE PVI-6000 | 2013-08-12 | 2013-08-16 | 4 | 2013-08-16 | [14 empty] | 2013-12-16 | 2013-12-23 |  | Y
Central Hudson |  | Hudson Solar | CH-02350 | Poughkeepsie | Tivoli | Dutchess | 12583 | G | 7054 | Rhinebeck | Y | CH-02350 | 19 | 19 | [12 empty] | NM | N | XANTREX XW-6048; POWERONE PVI-3.0; POWERONE PVI-5000 (2)1XantrexXW6048 (DC) | 2013-08-12 | 2013-08-16 | 4 | 2013-08-16 | [14 empty] | 2013-12-26 | 2013-12-30 |  | W
Central Hudson |  | Hollitronics Energy Solutions | CH-01207 | Catskill | Medusa | Albany | 12120 | G | 1092 | Westerlo | N |  | 4.76 | [13 empty] | NM | N | Solar Bridge P250 4V - 208/240 | 2013-08-13 | 2013-08-16 | 3 | 2013-08-16 | [14 empty] | 2013-09-18 | 2013-09-25 |  | Y
Central Hudson |  | New York State Solar Farm | CH-04063 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8046 | Myers Corners | N |  | 5 | [13 empty] | NM | N | POWER-ONE PVI5000 | 2013-08-21 | 2013-08-23 | 2 | 2013-08-23 | [14 empty] | 2013-10-14 | 2013-10-18 |  | Y
Central Hudson |  | NRG Home Solar | CH-04450 | Newburgh | Walden | Orange | 12586 | G | 5043 | East Walden | N |  | 6 | [13 empty] | NM | N | POWER-ONE PVI-6000-OUTD-US | 2013-08-14 | 2013-08-23 | 7 | 2013-08-23 | [14 empty] | 2013-10-31 | 2013-11-01 |  | Y
Central Hudson |  | NRG Home Solar | CH-04719 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8092 | Fishkill Plains | N |  | 6 | [13 empty] | NM | N | POWER-ONE PVI-6000-OUTD-US | 2013-08-14 | 2013-08-23 | 7 | 2013-08-23 | [14 empty] | 2013-11-01 | 2013-11-08 |  | Y
Central Hudson |  | NRG Home Solar | CH-04695 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6046 | Spackenkill | N |  | 6 | [13 empty] | NM | N | POWER-ONE PVI-6000-OUTD-US | 2013-08-15 | 2013-08-22 | 5 | 2013-08-22 | [14 empty] | 2013-12-27 | 2013-12-31 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03797 | Newburgh | Rock Tvrn | Orange | 12575 | G | 4097 | Bethlehem Rd | N |  | 9.2 | [13 empty] | NM | N | POWER ONE AUROA PVI5000US-OUTS-US (1) & POWER ONE AUROA PVI4.2-OUT-US | 2013-08-16 | 2013-08-23 | 5 | 2013-08-23 | [14 empty] | 2013-09-26 | 2013-10-03 |  | Y
Central Hudson |  | SolarCity | CH-06956 | Newburgh | Newburgh | Orange | 12550 | G | 4027 | Coldenham | N |  | 600 | [13 empty] | NM | N | Solectria SGI-500 kW (1) & Solectria SGI-100kW (1) | 2013-09-19 | 2013-10-10 | 15 | 2013-10-10 | 2013-09-19 | 2013-10-10 | 15 | 2013-10-22 | 2013-10-22 | 2014-01-16 | 57 | 11357 | [6 empty] | 2014-04-21 | 2014-04-21 |  | Y
Central Hudson |  | NRG Home Solar | CH-04116 | Kingston | Kerhonkson | Ulster | 12446 | G | 3081 | Kerhonkson | N |  | 5 | [13 empty] | NM | N | POWER-ONE PVI-5000_OUTD-US | 2013-08-20 | 2013-08-29 | 7 | 2013-08-29 | [14 empty] | 2013-11-26 | 2013-12-05 |  | Y
Central Hudson |  | NRG Home Solar | CH-04259 | Kingston | High Fls | Ulster | 12440 | G | 3022 | High Falls | N |  | 3.6 | [13 empty] | NM | N | POWER-ONE PVI-3.6-OUTD-S-US | 2013-08-27 | 2013-08-29 | 2 | 2013-08-29 | [14 empty] | 2013-12-05 | 2013-12-12 |  | Y
Central Hudson |  | NRG Home Solar | CH-04442 | Newburgh | New Windsor | Orange | 12553 | G | 4044 | Union Ave | N |  | 6 | [13 empty] | NM | N | POWER-ONE PVI-6000-OUTD-US | 2013-08-27 | 2013-08-29 | 2 | 2013-08-29 | [14 empty] | 2013-10-31 | 2013-11-07 |  | Y
Central Hudson |  | NRG Home Solar | CH-04700 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6061 | Inwood Ave | N |  | 3 | [13 empty] | NM | N | POWER-ONE PVI-3.0-OUTD-S-US | 2013-08-20 | 2013-08-29 | 7 | 2013-08-29 | [14 empty] | 2013-11-25 | 2013-12-03 |  | Y
Central Hudson |  | NRG Home Solar | CH-04811 | Kingston | Kingston |  | 12401 | G | 1024 | East Kingston | TBD |  | 4.2 | [13 empty] | NM | N | POWER-ONE PVI-4.2-OUTD-S-US | 2013-08-27 | 2013-08-29 | 2 | 2013-08-29 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | NRG Home Solar | CH-04285 | Kingston | Saugerties | Ulster | 12477 | G | 3002 | Saugerties | N |  | 6 | [13 empty] | NM | N | POWER-ONE PVI-6000-OUTD-US | 2013-08-21 | 2013-08-29 | 6 | 2013-08-29 | [14 empty] | 2013-11-04 | 2013-11-08 |  | Y
Central Hudson |  | SolarCity | CH-05515 | Catskill | Cairo | Greene | 12413 | G | 2041 | South Cairo | N |  | 10 | [13 empty] | NM | N | FRONIUS USA IG PLUS V 10.0 | 2013-08-22 | 2013-08-30 | 6 | 2013-08-30 | [8 empty] | 350 | 350 |  |  |  |  | 2013-12-05 | 2013-12-09 |  | Y
Central Hudson |  | NRG Home Solar | CH-04221 | Newburgh | Clintondale | Ulster | 12515 | G | 5012 | Modena | N |  | 5 | [13 empty] | NM | N | SUNPOWER SPR-5000M | 2013-08-23 | 2013-09-09 | 10 | 2013-09-09 | [14 empty] | 2014-01-29 | 2014-02-05 |  | Y
Central Hudson |  | NRG Home Solar | CH-04653 | Newburgh | Newburgh | Orange | 12550 | G | 4015 | West Balmville | N |  | 4.2 | [13 empty] | NM | N | POWER-ONE PVI-4.2-OUTD-S-US | 2013-08-23 | 2013-09-09 | 10 | 2013-09-09 | [14 empty] | 2014-04-16 | 2014-04-23 |  | Y
Central Hudson |  | NRG Home Solar | CH-04745 | Newburgh | Wallkill | Ulster | 12589 | G | 5013 | Modena | N |  | 5 | [13 empty] | NM | N | SUNPOWER SPR-5000M | 2013-08-23 | 2013-09-09 | 10 | 2013-09-09 | [14 empty] | 2014-02-18 | 2014-02-25 |  | Y
Central Hudson |  | NRG Home Solar | CH-04772 | Fishkill | Fishkill | Dutchess | 12524 | G | 8094 | Fishkill Plains | N |  | 4.2 | [13 empty] | NM | N | POWER-ONE PVI-4.2-OUTD-S-US | 2013-08-23 | 2013-09-09 | 10 | 2013-09-09 | [14 empty] | 2014-04-02 | 2014-04-07 |  | Y
Central Hudson |  | SolarCity | CH-07260 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6003 | Reynolds Hill | N |  | 6 | [13 empty] | NM | N | POWER-ONE PVI-6000-OUTD-US | 2013-08-23 | 2013-09-09 | 10 | 2013-09-09 | [14 empty] | 2013-11-01 | 2013-11-08 |  | Y
Central Hudson |  | Sunrise Solar Solutions, LLC | CH-09668 | Kingston | Kingston | Ulster | 12401 | G | 121 | Converse St | N |  | 13.76 | [13 empty] | NM | N | ENPHASE ENERGY M215 (64) | 2014-02-04 | 2014-02-05 | 1 | 2014-02-05 | [14 empty] | 2014-02-05 | 2014-02-11 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | NRG Home Solar | CH-04253 | Kingston | Olive Brdg |  | 12461 | G | 3024 | High Falls | TBD |  | 5 | [13 empty] | NM | N | SUNPOWER SPR-5000M | 2013-08-26 | 2013-09-09 | 9 | 2013-09-09 | [17 empty] | W |  | 10/12/14 Project abandoned as per customer.
Central Hudson |  | NRG Home Solar | CH-04176 | Fishkill | Beacon | Dutchess | 12508 | G | 8015 | Forgebrook | N |  | 3.87 | [13 empty] | NM | N | Enphase M215 (18) | 2013-08-27 | 2013-09-09 | 8 | 2013-09-09 | [14 empty] | 2014-08-04 | 2014-08-08 |  | Y
Central Hudson |  | NRG Home Solar | CH-04748 | Newburgh | Washingtonvl | Orange | 10992 | G | 4097 | Bethlehem Rd | N |  | 6 | [13 empty] | NM | N | POWER-ONE PVI-6000-OUTD-US | 2013-09-19 | 2013-10-01 | 8 | 2013-10-01 | [14 empty] | 2014-03-19 | 2014-03-25 |  | Y
Central Hudson |  | Sungevity Inc | CH-09519 | Kingston | Bearsvl | Ulster | 12409 | G | 3012 | Woodstock | N |  | 7 | [13 empty] | NM | N | SMA AMERICA SB7000US | 2013-08-27 | 2013-09-09 | 8 | 2013-09-09 | [14 empty] | 2013-10-08 | 2013-10-11 |  | Y
Central Hudson |  | SolarCity | CH-06227 | Newburgh | Newburgh | Orange | 12550 | G | 4023 | Coldenham | N | CH-06227 | 7 | [13 empty] | NM | N | SMA SB7000US | 2013-08-28 | 2013-09-11 | 9 | 2013-09-11 | [14 empty] | 2013-10-25 | 2013-11-01 |  | Y
Central Hudson |  | Solar Generation | CH-08190 | Kingston | Saugerties | Ulster | 12477 | G | 3003 | Saugerties | N |  | 7.08 | [13 empty] | NM | N | OUTBACK 8048 | 2013-08-28 | 2013-09-10 | 8 | 2013-09-10 | [8 empty] | 350 | 350 |  |  |  |  | 2013-11-05 | 2013-11-05 |  | Y
Central Hudson |  | NRG Home Solar | CH-04407 | Fishkill | Fishkill | Dutchess | 12524 | G | 8094 | Fishkill Plains | N |  | 6 | [13 empty] | NM | N | POWER-ONE PVI-6000-OUTD-US | 2013-08-29 | 2013-09-11 | 8 | 2013-09-11 | [14 empty] | 2013-12-31 | 2013-12-31 |  | Y
Central Hudson |  | NRG Home Solar | CH-04805 | Fishkill | Beacon | Dutchess | 12508 | G | 8016 | Forgebrook | N |  | 6 | [13 empty] | NM | N | POWER-ONE PVI-6000-OUTD-US | 2013-08-29 | 2013-09-11 | 8 | 2013-09-11 | [14 empty] | 2014-01-28 | 2014-02-04 |  | Y
Central Hudson |  | Sun Edison | CH-09079 | Newburgh | Newburgh | Orange | 12550 | G | 4045 | Union Ave | N |  | 260 | [13 empty] | NM | N | Advanced Energy AE260TX | 2013-09-19 | 2013-10-10 | 15 | 2013-10-10 | 2013-09-19 | 2013-10-10 | 15 | [11 empty] | 2013-11-21 | 2013-12-03 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03817 | Newburgh | Gardiner | Ulster | 12525 | G | 5034 | Galeville | N |  | 7.5 | [13 empty] | NM | N | FRONIUS IG PLUS 07.5-1 UNI | 2013-09-09 | 2013-09-11 | 2 | 2013-09-11 | [14 empty] | 2013-11-22 | 2013-12-03 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03832 | Newburgh | Gardiner | Ulster | 12525 | G | 5034 | Galeville | N | CH-03578 | 3.36 | [13 empty] | NM | N | POWER ONE AUROA PVI6000-OUTD-US (2) | 2013-08-30 | 2013-09-11 | 7 | 2013-09-11 | [14 empty] | 2014-02-06 | 2014-02-13 |  | Y
Central Hudson |  | Self | CH-08894 | Catskill | Westerlo | Albany | 12193 | G | 1091 | Westerlo | N | CH-02703 | 3.92 | [13 empty] | NM | N | SOLECTRIA PVI 4000W | 2013-09-18 | 2013-09-23 | 3 | 2013-09-23 | [14 empty] | 2014-07-31 | 2014-07-31 |  | Y
Central Hudson |  | Sun Mountain | CH-09085 | Kingston | Accord | Ulster | 12404 | G | 3024 | High Falls | N |  | 3 | [13 empty] | NM | N | SMA SB3000US | 2013-09-11 | 2013-09-17 | 4 | 2013-09-17 | [14 empty] | 2013-10-07 | 2013-10-07 |  | Y
Central Hudson |  | NRG Home Solar | CH-04460 | Newburgh | New Windsor | Orange | 12553 | G | 4044 | Union Ave | N |  | 3.6 | [13 empty] | NM | N | POWER-ONE PVI-3.6-OUTD-S-US | 2013-09-03 | 2013-09-13 | 8 | 2013-09-13 | [14 empty] | 2013-11-26 | 2013-12-05 |  | Y
Central Hudson |  | NRG Home Solar | CH-04524 | Kingston | Kingston | Ulster | 12401 | G | 1012 | Boulevard | N |  | 3 | [13 empty] | NM | N | POWER-ONE PVI-3.0-OUTD-S-US | 2013-09-03 | 2013-09-13 | 8 | 2013-09-13 | [14 empty] | 2014-01-24 | 2014-01-31 |  | Y
Central Hudson |  | NRG Home Solar | CH-04681 | Newburgh | Campbell Hall | Orange | 10916 | G | 5051 | Maybrook | N | CH-04681 | 5 | [13 empty] | NM | N | POWER-ONE PVI-5000-OUTD-US | 2013-09-03 | 2013-09-13 | 8 | 2013-09-13 | [14 empty] | 2013-12-27 | 2013-12-31 |  | Y
Central Hudson |  | NRG Home Solar | CH-04699 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6042 | Spackenkill | N |  | 6 | [13 empty] | NM | N | POWER-ONE PVI-6000-OUTD-US | 2013-09-03 | 2013-09-13 | 8 | 2013-09-13 | [14 empty] | 2014-02-19 | 2014-02-26 |  | Y
Central Hudson |  | NRG Home Solar | CH-04115 | Kingston | Accord | Ulster | 12404 | G | 3081 | Kerhonkson | N |  | 4.2 | [13 empty] | NM | N | POWER-ONE PVI-4.2-OUTD-US | 2013-09-04 | 2013-09-13 | 7 | 2013-09-13 | [14 empty] | 2013-12-05 | 2013-12-11 |  | Y
Central Hudson |  | NRG Home Solar | CH-04162 | Catskill | Catskill | Greene | 12414 | G | 2002 | North Catskill | N |  | 6 | [13 empty] | NM | N | POWER-ONE PVI-6000-OUTD-US | 2013-09-04 | 2013-09-13 | 7 | 2013-09-13 | [14 empty] | 2013-12-27 | 2013-12-31 |  | Y
Central Hudson |  | NRG Home Solar | CH-04298 | Kingston | Kingston | Ulster | 12401 | G | 1021 | East Kingston | N |  | 3.6 | [13 empty] | NM | N | POWER-ONE PVI 3.6 | 2013-09-12 | 2013-09-19 | 5 | 2013-09-19 | [14 empty] | 2013-11-07 | 2013-11-12 |  | Y
Central Hudson |  | NRG Home Solar | CH-04302 | Kingston | Lk Katrine | Ulster | 12449 | G | 2016 | Lincoln Park | N |  | 5 | [13 empty] | NM | N | POWER-ONE PVI-5000-OUTD-US | 2013-09-04 | 2013-09-13 | 7 | 2013-09-13 | [14 empty] | 2013-11-26 | 2013-11-26 |  | Y
Central Hudson |  | NRG Home Solar | CH-04515 | Catskill | Cairo | Greene | 12413 | G | 2043 | South Cairo | N |  | 5 | [13 empty] | NM | N | POWER-ONE PVI-5000-OUTD-US | 2013-09-04 | 2013-09-13 | 7 | 2013-09-13 | [14 empty] | 2014-01-17 | 2014-01-24 |  | Y
Central Hudson |  | NRG Home Solar | CH-04410 | Fishkill | Fishkill | Dutchess | 12524 | G | 8065 | Merritt Park | N |  | 6 | [13 empty] | NM | N | POWER-ONE PVI-6000-OUTD-US | 2013-09-05 | 2013-09-13 | 6 | 2013-09-13 | [14 empty] | 2014-01-24 | 2014-01-31 |  | Y
Central Hudson |  | Sungevity Inc | CH-09325 | Poughkeepsie | Clinton Corners | Dutchess | 12514 | G | 7013 | Hibernia | N |  | 9 | [13 empty] | NM | N | POWER ONE PVI-6000-OUTD-US (1) & POWER ONE PVI-3.0-OUTD-S-US (1) | 2013-09-20 | 2013-09-27 | 5 | 2013-09-27 | [14 empty] | 2013-10-24 | 2013-10-31 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03568 | Newburgh | New Paltz | Ulster | 12561 | G | 5011 | Modena | N |  | 6 | [13 empty] | NM | N | POWER ONE AURURA PVI6000-OUTD-US | 2013-09-06 | 2013-09-13 | 5 | 2013-09-13 | [14 empty] | 2013-11-19 | 2013-11-26 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03622 | Newburgh | Gardiner | Ulster | 12525 | G | 5011 | Modena | N |  | 6 | [13 empty] | NM | N | POWER ONE AURORA PVI6000-OUTS-US | 2013-09-06 | 2013-09-13 | 5 | 2013-09-13 | [14 empty] | 2013-11-06 | 2013-11-13 |  | Y
Central Hudson |  | NRG Home Solar | CH-04569 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6092 | Manchester | N |  | 7.962 | [13 empty] | NM | N | POWER-ONE PVI-6000-OUTD_US (1) & POWER-ONE PVI-3.0-OUTD-S-US (1) | 2013-09-06 | 2013-09-13 | 5 | 2013-09-13 | [14 empty] | 2014-05-13 | 2014-05-20 |  | Y
Central Hudson |  | SolarCity | CH-07543 | Poughkeepsie | Clinton Corners | Dutchess | 12514 | G | 7012 | Hibernia | N |  | 11.4 | [13 empty] | NM | N | POWER ONE PVI-3.6-OUTD-S-US (2) & POWER ONE PVI-4.2-OUTD-S-US (1) | 2013-10-14 | 2013-10-16 | 2 | 2013-10-16 | [14 empty] | 2014-03-25 | 2014-03-31 |  | Y
Central Hudson |  | Malcarne Contracting | CH-03904 | Kingston | Kingston | Ulster | 12401 | G | 2093 | Hurley Ave | N |  | 6 | [13 empty] | NM | N | SMA AMERICA SB3000TLUS (2) | 2013-09-09 | 2013-09-16 | 5 | 2013-09-16 | [14 empty] | 2013-11-25 | 2013-12-04 |  | Y
Central Hudson |  | SolarCity | CH-05912 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6051 | Todd Hill | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A-US | 2013-09-09 | 2013-09-16 | 5 | 2013-09-16 | [14 empty] | 2013-11-13 | 2013-11-20 |  | Y
Central Hudson |  | SolarCity | CH-06955 | Newburgh | Newburgh | Orange | 12550 | G | 4027 | Coldenham | N |  | 100 | [13 empty] | NM | N | Solectria PVI-100kW (2) | 2013-09-19 | 2013-10-01 | 8 | 2013-10-01 | 2013-09-19 | 2013-10-01 | 8 | [11 empty] | 2013-12-31 | 2014-01-08 |  | Y
Central Hudson |  | Sungevity Inc | CH-09500 | Newburgh | New Windsor | Orange | 12553 | G | 4095 | Bethlehem Rd | N |  | 6 | [13 empty] | NM | N | POWER ONE PVI-6000-OUTD-US | 2013-09-09 | 2013-09-16 | 5 | 2013-09-16 | [14 empty] | 2013-11-18 | 2013-11-18 |  | Y
Central Hudson |  | Sunrise Solar Solutions, LLC | CH-09656 | Newburgh | New Paltz | Ulster | 12561 | G | 5023 | Ohioville | N |  | 27.95 | [13 empty] | NM | N | Enphase M215 (130) | 2013-10-01 | 2013-10-03 | 2 | 2013-10-03 | [14 empty] | 2014-03-27 | 2014-04-01 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-03476 | Newburgh | Montgomery | Orange | 12549 | G | 5073 | Montgomery | N |  | 13 | [13 empty] | NM | N | SUNPOWER SPR 6501F (2) | 2013-09-18 | 2013-09-25 | 5 | 2013-09-25 | [14 empty] | 2013-12-30 | 2013-12-31 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03669 | Kingston | Saugerties | Ulster | 12477 | G | 3002 | Saugerties | N |  | 20 | [13 empty] | NM | N | FRONIUS IG PLUS 10.0-1 UNI (2) | 2013-09-10 | 2013-09-18 | 6 | 2013-09-18 | [8 empty] | 350 | 350 |  |  |  |  | 2013-12-20 | 2013-12-30 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-03470 | Newburgh | Wallkill | Ulster | 12589 | G | 5033 | Galeville | N |  | 10 | [13 empty] | NM | N | POWERONE PVI5000 (2) | 2013-10-02 | 2013-10-07 | 3 | 2013-10-07 | [14 empty] | 2013-12-23 | 2013-12-23 |  | Y
Central Hudson |  | New York State Solar Farm | CH-04039 | Newburgh | Newburgh | Orange | 12550 | G | 5001 | Marlboro | N |  | 9 | [13 empty] | NM | N | POWERONE 6.0 (1) & POWERONE 3.0 (1) | 2013-09-11 | 2013-09-18 | 5 | 2013-09-18 | [14 empty] | 2013-10-09 | 2013-10-15 |  | Y
Central Hudson |  | NRG Home Solar | CH-04236 | Catskill | Purling | Greene | 12470 | G | 2041 | South Cairo | N |  | 6 | [13 empty] | NM | N | POWER-ONE PVI-6000-OUTD-US | 2013-09-11 | 2013-09-17 | 4 | 2013-09-17 | [14 empty] | 2013-12-13 | 2013-12-20 |  | Y
Central Hudson |  | NRG Home Solar | CH-04377 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8091 | Fishkill Plains | N |  | 6 | [13 empty] | NM | N | POWER-ONE PVI-6000-OUTD-US | 2013-09-11 | 2013-09-17 | 4 | 2013-09-17 | [14 empty] | 2014-07-01 | 2014-07-09 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03776 | Newburgh | Newburgh | Orange | 12550 | G | 4055 | Union Ave | N |  | 50 | [13 empty] | NM | N | PowerOne PVI 10.0 (5) | 2013-09-12 | 2013-09-26 | 10 | 2013-09-26 | 2013-09-12 | 2013-09-26 | 10 | [5 empty] | 2000 | 2821.96 |  |  |  |  | 2014-07-31 | 2014-08-05 |  | Y
Central Hudson |  | NRG Home Solar | CH-04448 | Newburgh | Newburgh | Orange | 12550 | G | 4014 | West Balmville | N |  | 6 | [13 empty] | NM | N | POWER-ONE PVI-6000-OUTD-US | 2013-09-12 | 2013-09-19 | 5 | 2013-09-19 | [14 empty] | 2014-02-04 | 2014-02-11 |  | Y
Central Hudson |  | NRG Home Solar | CH-04648 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N | CH-04648 | 6 | [13 empty] | NM | N | POWER-ONE PVI-6000-OUTD-US | 2013-09-19 | 2013-09-19 | 0 | 2013-09-19 | [14 empty] | 2013-12-19 | 2013-12-30 |  | Y
Central Hudson |  | NRG Home Solar | CH-04669 | Newburgh | Cornwall | Orange | 12518 | G | 4041 | Union Ave | N |  | 5 | [13 empty] | NM | N | POWER-ONE PVI-5000-OUTD-US | 2013-09-12 | 2013-09-18 | 4 | 2013-09-18 | [14 empty] | 2013-12-12 | 2013-12-19 |  | Y
Central Hudson |  | Hudson Solar | CH-01620 | Catskill | Earlton | Greene | 12058 | G | 1071 | Coxsackie | N |  | 5 | [13 empty] | NM | N | POWERONEPVI 5000 | 2013-09-12 | 2013-09-18 | 4 | 2013-09-18 | [8 empty] | 350 | 350 |  |  |  |  | 2014-09-05 | 2014-09-12 |  | Y
Central Hudson |  | Hudson Solar | CH-02341 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 7041 | Staatsburg | N | CH-02341 | 5 | [13 empty] | NM | N | SMA SB 5000TL | 2013-09-12 | 2013-09-18 | 4 | 2013-09-18 | [14 empty] | 2014-05-29 | 2014-06-05 |  | Y
Central Hudson |  | Monolith Solar Associates LLC | CH-02636 | Fishkill | Cold Spg | Putnam | 10516 | G | 8087 | Tioronda | N |  | 32 | [13 empty] | NM | N | (1) Fronius 12.0-3 SYMO (2) Fronius 10.0-3 SYMO | 2013-09-12 | 2013-09-26 | 10 | 2013-09-26 | 2013-09-12 | 2013-09-26 | 10 | [11 empty] | 2015-11-05 | 2015-11-16 |  | Y
Central Hudson |  | Monolith Solar Associates LLC | CH-02637 | Fishkill | Cold Spg | Putnam | 10516 | G | 8087 | Tioronda | N |  | 48 | [13 empty] | NM | N | (4) Fronius 12.0-3 SYMO | 2013-09-12 | 2013-09-26 | 10 | 2013-09-26 | 2013-09-12 | 2013-09-26 | 10 | [11 empty] | 2015-11-11 | 2015-11-16 |  | Y
Central Hudson |  | Monolith Solar Associates LLC | CH-02696 | Fishkill | Cold Spg |  | 10516 | G | 8087 | Tioronda | TBD |  | 45.6 | [13 empty] | NM | N | FRONIUS IG PLUS 11.4 (4) | 2013-09-12 | 2013-09-26 | 10 | 2013-09-26 | 2013-09-12 | 2013-09-26 | 10 | [5 empty] | 4000 | 4344.04 | [7 empty] | W |  | Resubmitted new system design
Central Hudson |  | SolarCity | CH-05731 | Kingston | Saugerties | Ulster | 12477 | G | 3001 | Saugerties | N |  | 3.8 | [13 empty] | NM | N | SOLAREDGE SE3800A-US | 2013-09-12 | 2013-09-18 | 4 | 2013-09-18 | [14 empty] | 2013-11-15 | 2013-11-22 |  | Y
Central Hudson |  | SolarCity | CH-05889 | Poughkeepsie | Lagrangevl | Dutchess | 12540 | G | 6053 | Todd Hill | N |  | 9.8 | [13 empty] | NM | N | SOLAREDGE SE6000A-US (1) & SOLAREDGE SE3800A-US (1) | 2013-09-12 | 2013-09-18 | 4 | 2013-09-18 | [14 empty] | 2013-12-26 | 2013-12-31 |  | Y
Central Hudson |  | NRG Home Solar | CH-04200 | Newburgh | Newburgh | Orange | 12550 | G | 4023 | Coldenham | N |  | 3.6 | [13 empty] | NM | N | POWER-ONE PVI-3.6-OUTD-S-US | 2013-09-13 | 2013-09-20 | 5 | 2013-09-20 | [14 empty] | 2013-11-14 | 2013-11-21 |  | Y
Central Hudson |  | NRG Home Solar | CH-04678 | Newburgh | Rock Tvrn | Orange | 12575 | G | 4097 | Bethlehem Rd | N |  | 6 | [13 empty] | NM | N | POWER-ONE PVI-6000-OUTD-US | 2013-09-13 | 2013-09-20 | 5 | 2013-09-20 | [14 empty] | 2013-12-05 | 2013-12-09 |  | Y
Central Hudson |  | Hudson Solar | CH-01364 | Newburgh | New Paltz | Ulster | 12561 | G | 5024 | Ohioville | N |  | 7.2 | [13 empty] | NM | N | POWERONE PVI 3.6 (2) | 2013-09-13 | 2013-09-24 | 7 | 2013-09-24 | [14 empty] | 2013-11-12 | 2013-11-19 |  | Y
Central Hudson |  | Hudson Solar | CH-01411 | Newburgh | New Paltz | Ulster | 12561 | G | 5024 | Ohioville | N |  | 7.2 | [13 empty] | NM | N | POWERONE PVI 3.6 (2) | 2013-09-13 | 2013-09-24 | 7 | 2013-09-24 | [14 empty] | 2013-10-21 | 2013-10-28 |  | Y
Central Hudson |  | Hudson Solar | CH-01428 | Newburgh | New Paltz | Ulster | 12561 | G | 5024 | Ohioville | N |  | 7.2 | [13 empty] | NM | N | POWERONE PVI 3.6 (2) | 2013-09-13 | 2013-09-24 | 7 | 2013-09-24 | [14 empty] | 2013-10-21 | 2013-10-28 |  | W
Central Hudson |  | Hudson Solar | CH-01448 | Newburgh | New Paltz | Ulster | 12561 | G | 5024 | Ohioville | N |  | 7.2 | [13 empty] | NM | N | POWERONE PVI 3.6 (2) | 2013-09-13 | 2013-09-24 | 7 | 2013-09-24 | [14 empty] | 2013-11-12 | 2013-11-19 |  | Y
Central Hudson |  | Hudson Solar | CH-01463 | Newburgh | New Paltz | Ulster | 12561 | G | 5024 | Ohioville | N |  | 7.2 | [13 empty] | NM | N | POWERONE PVI 3.6 (2) | 2013-09-13 | 2013-09-24 | 7 | 2013-09-24 | [14 empty] | 2013-10-21 | 2013-10-28 |  | Y
Central Hudson |  | Hudson Solar | CH-01515 | Newburgh | New Paltz | Ulster | 12561 | G | 5024 | Ohioville | N | CH-01515 | 7.2 | [13 empty] | NM | N | POWERONE PVI 3.6 (2) | 2013-09-13 | 2013-09-24 | 7 | 2013-09-24 | [14 empty] | 2013-11-12 | 2013-11-19 |  | Y
Central Hudson |  | Hudson Solar | CH-01567 | Newburgh | New Paltz | Ulster | 12561 | G | 5024 | Ohioville | N |  | 7.2 | [13 empty] | NM | N | POWERONE PVI 3.6 (2) | 2013-09-13 | 2013-09-24 | 7 | 2013-09-24 | [14 empty] | 2013-11-12 | 2013-11-19 |  | Y
Central Hudson |  | Hudson Solar | CH-01578 | Newburgh | New Paltz | Ulster | 12561 | G | 5024 | Ohioville | N |  | 7.2 | [13 empty] | NM | N | POWERONE PVI 3.6 (2) | 2013-09-13 | 2013-09-24 | 7 | 2013-09-24 | [14 empty] | 2013-10-30 | 2013-11-06 |  | Y
Central Hudson |  | Hudson Solar | CH-01585 | Newburgh | New Paltz | Ulster | 12561 | G | 5024 | Ohioville | N |  | 7.2 | [13 empty] | NM | N | POWERONE PVI 3.6 (2) | 2013-09-13 | 2013-09-24 | 7 | 2013-09-24 | [14 empty] | 2013-10-30 | 2013-11-06 |  | Y
Central Hudson |  | Hudson Solar | CH-01627 | Catskill | Westerlo | Albany | 12193 | G | 1091 | Westerlo | N |  | 8.4 | [13 empty] | NM | N | POWERONE PVI 4.2 (2) | 2013-09-24 | 2013-10-01 | 5 | 2013-10-01 | [14 empty] | 2013-12-26 | 2013-12-31 |  | Y
Central Hudson |  | Hudson Solar | CH-01998 | Newburgh | Newburgh | Orange | 12550 | G | 4055 | Union Ave | N |  | 45 | [13 empty] | NM | N | SMA AMERICA 15000 (3) | 2013-09-13 | 2013-09-27 | 10 | 2013-09-27 | 2013-09-13 | 2013-09-27 | 10 | [11 empty] | 2013-12-16 | 2013-12-19 |  | Y
Central Hudson |  | Hudson Solar | CH-01999 | Newburgh | Newburgh | Orange | 12550 | G | 4055 | Union Ave | N |  | 48 | [13 empty] | NM | N | SMA AMERICA STP 24000TL (2) | 2013-09-13 | 2013-09-27 | 10 | 2013-09-27 | 2013-09-13 | 2013-09-27 | 10 | [11 empty] | 2013-12-12 | 2013-12-19 |  | Y
Central Hudson |  | Hudson Solar | CH-02000 | Newburgh | Newburgh | Orange | 12550 | G | 4055 | Union Ave | N |  | 40 | [13 empty] | NM | N | SMA AMERICA STP 20000TL (2) | 2013-09-13 | 2013-09-27 | 10 | 2013-09-27 | 2013-09-13 | 2013-09-27 | 10 | [11 empty] | 2013-12-19 | 2013-12-19 |  | Y
Central Hudson |  | Hudson Solar | CH-02001 | Newburgh | Newburgh | Orange | 12550 | G | 4055 | Union Ave | N |  | 44 | [13 empty] | NM | N | SMA AMERICA STP 20000TL (1) & SMA AMERICA STP 24000TL (1) | 2013-09-13 | 2013-09-27 | 10 | 2013-09-27 | 2013-09-13 | 2013-09-27 | 10 | [11 empty] | 2013-12-04 | 2013-12-09 |  | Y
Central Hudson |  | Hudson Solar | CH-02002 | Newburgh | Newburgh | Orange | 12550 | G | 4055 | Union Ave | N |  | 15 | [13 empty] | NM | N | SMA AMERICA STP 15000TL | 2013-09-13 | 2013-09-27 | 10 | 2013-09-27 | [14 empty] | 2013-12-04 | 2013-12-09 |  | Y
Central Hudson |  | Hudson Solar | CH-02003 | Newburgh | Newburgh | Orange | 12550 | G | 4055 | Union Ave | N |  | 30 | [13 empty] | NM | N | SMA AMERICA STP 15000TL (2) | 2013-09-13 | 2013-09-27 | 10 | 2013-09-27 | 2013-09-13 | 2013-09-27 | 10 | [11 empty] | 2013-12-04 | 2013-12-09 |  | Y
Central Hudson |  | Hudson Solar | CH-02004 | Newburgh | Newburgh | Orange | 12550 | G | 4055 | Union Ave | N |  | 35 | [13 empty] | NM | N | SMA AMERICA STP 15000TL (1) & SMA AMERICA STP 20000TL (1) | 2013-09-13 | 2013-09-27 | 10 | 2013-09-27 | 2013-09-13 | 2013-09-27 | 10 | [11 empty] | 2013-12-12 | 2013-12-19 |  | Y
Central Hudson |  | Solar Generation | CH-08072 | Kingston | Accord | Ulster | 12404 | G | 3024 | High Falls | N |  | 7.2 | [13 empty] | NM | N | POWER ONE PVI-3.6-US-240 (2) | 2013-09-13 | 2013-09-20 | 5 | 2013-09-20 | [14 empty] | 2013-11-06 | 2013-11-13 |  | Y
Central Hudson |  | Solar Generation | CH-08103 | Kingston | Saugerties | Ulster | 12477 | G | 2015 | Lincoln Park | N |  | 7 | [13 empty] | NM | N | SMA SB7000US-240 | 2013-09-13 | 2013-09-20 | 5 | 2013-09-20 | [14 empty] | 2014-01-27 | 2014-02-03 |  | Y
Central Hudson |  | Solar Generation | CH-08216 | Kingston | Bloomington | Ulster | 12411 | G | 1011 | Boulevard | N | CH-08216 | 10 | [13 empty] | NM | N | SUNPOWER SPR-5000M-240 (2) | 2013-09-13 | 2013-09-20 | 5 | 2013-09-20 | [14 empty] | 2014-01-08 | 2014-01-15 |  | Y
Central Hudson |  | Solar Generation | CH-08220 | Kingston | Glenford | Ulster | 12433 | G | 3013 | Woodstock | N | CH-08220 | 8.4 | [13 empty] | NM | N | POWER ONE PVI-4.2-OUTD-US-240 (1) & POWER ONE PVI-4.2-OUTD-US-240 | 2013-09-13 | 2013-09-20 | 5 | 2013-09-20 | [14 empty] | 2013-12-17 | 2013-12-23 |  | Y
Central Hudson |  | NRG Home Solar | CH-04830 | Fishkill | Hopewell Jct |  | 12533 | G | 8071 | Shenandoah | TBD |  | 4 | [13 empty] | NM | N | SUNPOWER SPR-4000M | 2013-09-24 | 2013-10-01 | 5 | 2013-10-01 | [8 empty] | 350 | 350 | [7 empty] | W
Central Hudson |  | Sol Providers | CH-08911 | Newburgh | Modena | Ulster | 12548 | G | 5012 | Modena | N |  | 5.16 | [13 empty] | NM | N | Enphase M215 (24) | 2013-09-16 | 2013-09-23 | 5 | 2013-09-23 | [14 empty] | 2013-12-31 | 2013-12-31 |  | Y
Central Hudson |  | Sol Providers | CH-08929 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7054 | Rhinebeck | N |  | 6.88 | [13 empty] | NM | N | Enphase M215 (32) | 2013-09-16 | 2013-09-23 | 5 | 2013-09-23 | [14 empty] | 2013-11-25 | 2013-12-04 |  | Y
Central Hudson |  | Sol Providers | CH-08956 | Newburgh | Newburgh |  | 12550 | G | 5001 | Marlboro | TBD |  | 10 | [13 empty] | NM | N | POWERONE PVI 5000TL (2) | 2013-09-26 | 2013-10-03 | 5 | 2013-10-03 | [17 empty] | W
Central Hudson |  | Lighthouse Solar | CH-03657 | Kingston | Kerhonkson | Ulster | 12446 | G | 3082 | Kerhonkson | N |  | 9 | [13 empty] | NM | N | POWER ONE AURORA PVI3.0-OUTD-S-US (1) & POWER ONE AURORA PVI6000-OUTD-S-US (1) | 2013-09-17 | 2013-09-23 | 4 | 2013-09-23 | [14 empty] | 2013-11-22 | 2013-12-03 |  | Y
Central Hudson |  | NRG Home Solar | CH-04142 | Newburgh | Marlboro | Ulster | 12542 | G | 5003 | Marlboro | N |  | 4 | [13 empty] | NM | N | SUNPOWER SPR-4000M | 2013-09-17 | 2013-09-23 | 4 | 2013-09-23 | [14 empty] | 2014-02-19 | 2014-02-26 |  | Y
Central Hudson |  | SolarCity | CH-05961 | Poughkeepsie | Tivoli | Dutchess | 12583 | G | 7062 | Milan | N |  | 3.8 | [13 empty] | NM | N | SOLAREDGE SE3800A-US | 2013-09-17 | 2013-09-23 | 4 | 2013-09-23 | [14 empty] | 2013-11-04 | 2013-11-11 |  | Y
Central Hudson |  | Solar Generation | CH-08119 | Kingston | Woodstock | Ulster | 12498 | G | 3012 | Woodstock | N |  | 13.8 | [13 empty] | NM | N | SMA SB 3000-US (1), SMA SB 3800-US (1) & SMA SB 7000-US (1) | 2013-09-24 | 2013-09-24 | 0 | 2013-09-24 | [8 empty] | 350 | 350 |  |  |  |  | 2014-01-13 | 2014-01-16 |  | Y
Central Hudson |  | NRG Home Solar | CH-04576 | Poughkeepsie | Pine Plns | Dutchess | 12567 | G | 7091 | Pulvers Corners | N |  | 6 | [13 empty] | NM | N | POWER-ONE PVI-6000-OUTD-US | 2013-09-18 | 2013-09-25 | 5 | 2013-09-25 | [14 empty] | 2013-12-12 | 2013-12-19 |  | Y
Central Hudson |  | OnForce Solar | CH-02803 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 5 | [13 empty] | NM | N | SMA SB-5000TL-US | 2013-10-03 | 2013-10-04 | 1 | 2013-10-04 | [14 empty] | 2014-01-17 | 2014-01-24 |  | Y
Central Hudson |  | SolarCity | CH-05730 | Kingston | Saugerties | Ulster | 12477 | G | 3001 | Saugerties | N |  | 6 | [13 empty] | NM | N | POWER-ONE PVI-6000-OUTD-US | 2013-09-18 | 2013-09-25 | 5 | 2013-09-25 | [14 empty] | 2013-12-11 | 2013-12-18 |  | Y
Central Hudson |  | SolarCity | CH-06487 | Kingston | Kingston |  | 12401 | G | 3023 | High Falls | TBD |  | 6 | [13 empty] | NM | N | POWER-ONE PVI-6000-OUTD-US | 2013-09-18 | 2013-09-25 | 5 | 2013-09-25 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | Solar Generation | CH-08289 | Kingston | Woodstock | Ulster | 12498 | G | 3014 | Woodstock | N |  | 7.955 | [13 empty] | NM | N | Enphase M215 (37) | 2013-09-18 | 2013-09-25 | 5 | 2013-09-25 | [14 empty] | 2013-12-16 | 2013-12-19 |  | Y
Central Hudson |  | NRG Home Solar | CH-04205 | Newburgh | Wallkill | Ulster | 12589 | G | 5041 | East Walden | N |  | 5 | [13 empty] | NM | N | POWER-ONE PVI-6000-OUTD-US | 2013-09-19 | 2013-09-26 | 5 | 2013-09-26 | [14 empty] | 2014-01-10 | 2014-01-17 |  | Y
Central Hudson |  | SolarCity | CH-05670 | Kingston | Port Ewen | Ulster | 12466 | G | 1012 | Boulevard | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A-US | 2013-09-19 | 2013-09-26 | 5 | 2013-09-26 | [14 empty] | 2013-12-30 | 2013-12-31 |  | Y
Central Hudson |  | Sungevity Inc | CH-09464 | Newburgh | New Paltz | Ulster | 12561 | G | 5031 | Galeville | N |  | 6.8 | [13 empty] | NM | N | POWER-ONE PVI-3.8-OUTD-S-US (1) & POWER-ONE PVI-3.0-OUTD-S-US | 2013-09-19 | 2013-09-26 | 5 | 2013-09-26 | [14 empty] | 2013-11-19 | 2013-11-26 |  | Y
Central Hudson |  | Sunrun Inc. | CH-09701 | Newburgh | Campbell Hall | Orange | 10916 | G | 5051 | Maybrook | N |  | 5 | [13 empty] | NM | N | FRONIUS IG PLUS 5.0 | 2013-10-02 | 2013-10-09 | 5 | 2013-10-09 | [14 empty] | 2013-11-04 | 2013-11-07 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00934 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 7024 | Tinkertown | N |  | 6.45 | [13 empty] | NM | N | ENPHASE ENERGY M215 (30) | 2013-09-27 | 2013-09-27 | 0 | 2013-09-27 | [14 empty] | 2014-01-10 | 2014-01-17 |  | Y
Central Hudson |  | SolarCity | CH-05156 | Newburgh | Highland | Ulster | 12528 | G | 5082 | Highland | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A-US | 2013-09-20 | 2013-09-27 | 5 | 2013-09-27 | [14 empty] | 2013-12-02 | 2013-12-09 |  | Y
Central Hudson |  | SolarCity | CH-05637 | Kingston | Cottekill | Ulster | 12419 | G | 3021 | High Falls | N |  | 3.8 | [13 empty] | NM | N | SOLAREDGE SE3800A-US | 2013-09-20 | 2013-09-27 | 5 | 2013-09-27 | [14 empty] | 2013-12-02 | 2013-12-09 |  | Y
Central Hudson |  | Sungevity Inc | CH-09272 | Kingston | Stone Ridge | Ulster | 12484 | G | 3023 | High Falls | N |  | 6.6 | [13 empty] | NM | N | POWER-ONE PVI-3.6-OUTD-S-US (1) & POWER-ONE PVI-3.0-OUTD-S-US | 2013-09-20 | 2013-09-27 | 5 | 2013-09-27 | [14 empty] | 2013-11-21 | 2013-11-26 |  | Y
Central Hudson |  | CNR Energy Solutions, LLC | CH-00775 | Newburgh | Wallkill | Ulster | 12589 | G | 5042 | East Walden | N |  | 41.28 | [13 empty] | NM | N | ENPHASE ENERGY M215 (192) | 2013-10-31 | 2013-11-20 | 14 | 2013-11-20 | 2013-10-31 | 2013-11-20 | 14 | [5 empty] | 1000 | 648.45 |  |  |  |  | 2014-06-09 | 2014-06-12 |  | Y
Central Hudson |  | Murphy Solar Power | CH-02718 | Catskill | Catskill | Greene | 12414 | G | 2001 | North Catskill | N |  | 3 | [13 empty] | NM | N | SMA SUNNYBOY 3000 | 2013-10-08 | 2013-10-15 | 5 | 2013-10-15 | [14 empty] | 2013-10-28 | 2013-11-04 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-05352 | Kingston | Tillson | Ulster | 12486 | G | 3022 | High Falls | N |  | 3.8 | [13 empty] | NM | N | SOLAREDGE SE3800A-US | 2013-11-05 | 2013-11-12 | 5 | 2013-11-12 | [14 empty] | 2013-12-16 | 2013-12-20 |  | Y
Central Hudson |  | Sunshine Plus | CH-09669 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8091 | Fishkill Plains | N |  | 7.5 | [13 empty] | NM | N | FRONIUS IG V 7.5 | 2013-09-23 | 2013-09-30 | 5 | 2013-09-30 | [14 empty] | 2013-09-30 | 2013-10-10 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Lighthouse Solar | CH-03606 | Newburgh | Marlboro | Ulster | 12542 | G | 5004 | Marlboro | N |  | 12 | [13 empty] | NM | N | POWER-ONE AURORA PVI6000-OUTD-US (2) | 2013-09-24 | 2013-10-01 | 5 | 2013-10-01 | [14 empty] | 2013-12-30 | 2013-12-30 |  | Y
Central Hudson |  | SolarCity | CH-05069 | Newburgh | Newburgh | Orange | 12550 | G | 4015 | West Balmville | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE3800A-US (2) | 2013-09-24 | 2013-10-01 | 5 | 2013-10-01 | [14 empty] | 2013-12-26 | 2013-12-31 |  | Y
Central Hudson |  | NRG Home Solar | CH-04271 | Kingston | Kingston | Ulster | 12401 | G | 1013 | Boulevard | N |  | 3 | [13 empty] | NM | N | POWER-ONE PVI-3.0-OUTD-S-US | 2013-09-25 | 2013-10-02 | 5 | 2013-10-02 | [14 empty] | 2014-03-20 | 2014-03-27 |  | Y
Central Hudson |  | NRG Home Solar | CH-04428 | Fishkill | Hopewell Junction | Dutchess | 12533 | G | 8071 | Shenandoah | N |  | 3.6 | [13 empty] | NM | N | POWER-ONE PVI-3.6-OUTD-S-US | 2013-09-25 | 2013-10-02 | 5 | 2013-10-02 | [14 empty] | 2014-01-22 | 2014-01-29 |  | Y
Central Hudson |  | OnForce Solar | CH-02812 | Newburgh | New Windsor | Orange | 12553 | G | 4094 | Bethlehem Rd | N |  | 7 | [13 empty] | NM | N | SMA SB 7000 US | 2013-09-25 | 2013-10-02 | 5 | 2013-10-02 | [14 empty] | 2014-01-17 | 2014-01-24 |  | Y
Central Hudson |  | SolarCity | CH-07329 | Newburgh | Highland | Ulster | 12528 | G | 5083 | Highland | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A-US | 2013-09-25 | 2013-10-02 | 5 | 2013-10-02 | [14 empty] | 2014-04-14 | 2014-04-15 |  | Y
Central Hudson |  | SolarCity | CH-07655 | Newburgh | Highland | Ulster | 12528 | G | 5083 | Highland | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE3800A-US (2) | 2013-09-25 | 2013-10-02 | 5 | 2013-10-02 | [14 empty] | 2013-12-09 | 2013-12-09 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-03370 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8045 | Myers Corners | N |  | 11 | [13 empty] | NM | N | POWERONE PVI 5000 (1) & POWERONE PVI 6000 (1) | 2013-09-26 | 2013-10-03 | 5 | 2013-10-03 | [14 empty] | 2014-02-19 | 2014-02-26 |  | Y
Central Hudson |  | Sunrise Solar Solutions, LLC | CH-09664 | Newburgh | New Paltz | Ulster | 12561 | G | 5011 | Modena | N |  | 5.59 | [13 empty] | NM | N | ENPHASE M215 (26) | 2013-09-26 | 2013-10-03 | 5 | 2013-10-03 | [14 empty] | 2014-02-19 | 2014-02-26 |  | Y
Central Hudson |  | Apex Solar Power | CH-03090 | Catskill | E Durham | Greene | 12405 | G | 2041 | South Cairo | N |  | 10.32 | [13 empty] | NM | N | Enphase M215 (48) | 2013-12-02 | 2013-12-05 | 3 | 2013-12-05 | [14 empty] | 2014-04-25 | 2014-05-02 |  | Y
Central Hudson |  | NRG Home Solar | CH-04447 | Newburgh | Newburgh |  | 12550 | G | 4011 | West Balmville | TBD |  | 3.6 | [13 empty] | NM | N | POWER-ONE PVI-3.6-OUTD-S-US | 2013-09-27 | 2013-10-04 | 5 | 2013-10-04 | [17 empty] | W
Central Hudson |  | New York State Solar Farm | CH-04011 | Newburgh | Gardiner | Ulster | 12525 | G | 5031 | Galeville | N |  | 10 | [13 empty] | NM | N | SPR FRONIUS IG PLUS 10.0 | 2013-09-30 | 2013-10-04 | 4 | 2013-10-04 | [14 empty] | 2014-03-04 | 2014-03-13 |  | Y
Central Hudson |  | NRG Home Solar | CH-04761 | Poughkeepsie | Hyde Pk |  | 12538 | G | 6068 | Inwood Ave | TBD |  | 5 | [13 empty] | NM | N | SUNPOWER SPR-5000 | 2013-10-01 | 2013-10-04 | 3 | 2013-10-04 | [17 empty] | W
Central Hudson |  | New York State Solar Farm | CH-04096 | Fishkill | Fishkill | Dutchess | 12524 | G | 8051 | North Chelsea | N | CH-02616 | 4.2 | [13 empty] | NM | N | SUNPOWER 4200P | 2013-10-03 | 2013-10-07 | 2 | 2013-10-07 | [14 empty] | 2013-12-26 | 2013-12-30 |  | Y
Central Hudson |  | NRG Home Solar | CH-04164 | Kingston | Woodbourne | Sullivan | 12788 | G | 3091 | Neversink | N |  | 6 | [13 empty] | NM | N | POWER-ONE PVI-6000-OUTD-US | 2013-10-03 | 2013-10-10 | 5 | 2013-10-10 | [14 empty] | 2013-12-27 | 2013-12-31 |  | Y
Central Hudson |  | Hudson Solar | CH-02352 | Poughkeepsie | Millerton | Dutchess | 12546 | G | 7081 | Millerton | N | CH-02352 | 7.2 | [13 empty] | NM | N | POWERONE PVI 3.6 (2) | 2013-10-14 | 2013-10-18 | 4 | 2013-10-18 | [14 empty] | 2013-12-31 | 2013-12-31 |  | Y
Central Hudson |  | Hudson Solar | CH-02367 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6003 | Reynolds Hill | N |  | 4.2 | [13 empty] | NM | N | POWERONE PVI 4.2 | 2013-10-10 | 2013-10-16 | 4 | 2013-10-16 | [14 empty] | 2013-12-31 | 2013-12-31 |  | Y
Central Hudson |  | SolarCity | CH-05790 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6043 | Spackenkill | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A-US | 2013-10-03 | 2013-10-09 | 4 | 2013-10-09 | [14 empty] | 2014-01-24 | 2014-01-31 |  | Y
Central Hudson |  | SolarCity | CH-06403 | Newburgh | Rock Tvrn | Orange | 12575 | G | 4097 | Bethlehem Rd | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A-US | 2013-10-03 | 2013-10-10 | 5 | 2013-10-10 | [14 empty] | 2013-12-27 | 2013-12-31 |  | Y
Central Hudson |  | Sungevity Inc | CH-09541 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8092 | Fishkill Plains | N | CH-09541 | 6 | [13 empty] | NM | N | POWER ONE PVI 6000 | 2013-10-11 | 2013-10-16 | 3 | 2013-10-16 | [14 empty] | 2013-12-05 | 2013-12-09 |  | Y
Central Hudson |  | NRG Home Solar | CH-04173 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8095 | Fishkill Plains | N |  | 3 | [13 empty] | NM | N | POWER-ONE PVI-3.0-OUTD-S-US | 2013-10-07 | 2013-10-11 | 4 | 2013-10-11 | [14 empty] | 2014-05-16 | 2014-05-20 |  | Y
Central Hudson |  | NRG Home Solar | CH-04292 | Kingston | Saugerties | Ulster | 12477 | G | 3001 | Saugerties | N |  | 6 | [13 empty] | NM | N | POWER-ONE PVI-6000-OUTD-US | 2013-10-07 | 2013-10-11 | 4 | 2013-10-11 | [14 empty] | 2014-01-28 | 2014-02-04 |  | Y
Central Hudson |  | NRG Home Solar | CH-04479 | Newburgh | Newburgh | Orange | 12550 | G | 5001 | Marlboro | N |  | 6 | [13 empty] | NM | N | POWER-ONE PVI-6000 | 2013-10-07 | 2013-10-11 | 4 | 2013-10-11 | [14 empty] | 2014-06-20 | 2014-06-26 |  | Y
Central Hudson |  | NRG Home Solar | CH-04518 | Catskill | Athens | Greene | 12015 | G | 1074 | Coxsackie | N |  | 6 | [13 empty] | NM | N | POWER-ONE PVI-6000-OUTD-US | 2013-10-11 | 2013-10-16 | 3 | 2013-10-16 | [14 empty] | 2014-03-06 | 2014-03-12 |  | Y
Central Hudson |  | Hudson Solar | CH-01432 | Fishkill | Beacon | Dutchess | 12508 | G | 8015 | Forgebrook | N |  | 6 | [13 empty] | NM | N | POWERONE PVI 3.0 (2) | 2013-10-07 | 2013-10-11 | 4 | 2013-10-11 | [14 empty] | 2015-11-02 | 2015-11-05 |  | Y
Central Hudson |  | Hudson Solar | CH-01666 | Kingston | Stone Ridge | Ulster | 12484 | G | 3023 | High Falls | N |  | 12 | [13 empty] | NM | N | POWERONE PVI 6000 (2) | 2013-10-07 | 2013-10-11 | 4 | 2013-10-11 | [14 empty] | 2013-12-26 | 2013-12-31 |  | Y
Central Hudson |  | Hudson Solar | CH-01686 | Kingston | Glenford | Ulster | 12433 | G | 3013 | Woodstock | N |  | 8.4 | [13 empty] | NM | N | POWERONE PVI 4.2 (2) | 2013-10-07 | 2013-10-11 | 4 | 2013-10-11 | [14 empty] | 2013-11-27 | 2013-12-06 |  | Y
Central Hudson |  | Hudson Solar | CH-02161 | Poughkeepsie | Stanfordvl | Dutchess | 12581 | G | 7072 | Stanfordville | N | CH-02161 | 3 | [13 empty] | NM | N | POWERONE PVI 3.0 | 2013-10-07 | 2013-10-11 | 4 | 2013-10-11 | [14 empty] | 2013-12-16 | 2013-12-23 |  | W
Central Hudson |  | SolarCity | CH-07633 | Kingston | Kingston |  | 12401 | G | 1022 | East Kingston | TBD |  | 3 | [13 empty] | NM | N | SolarEdge SE3000A-US | 2013-10-07 | 2013-10-11 | 4 | 2013-10-11 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | NRG Home Solar | CH-04598 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8092 | Fishkill Plains | N |  | 4.2 | [13 empty] | NM | N | POWER-ONE PVI-4.2-OUTD-S-US | 2013-10-08 | 2013-10-15 | 5 | 2013-10-15 | [14 empty] | 2014-02-19 | 2014-02-26 |  | Y
Central Hudson |  | Sungevity Inc | CH-09587 | Newburgh | Highland | Ulster | 12528 | G | 5083 | Highland | N |  | 8 | [13 empty] | NM | N | SMA AMERICA SB8000US-12 | 2013-10-08 | 2013-10-15 | 5 | 2013-10-15 | [14 empty] | 2013-12-20 | 2013-12-30 |  | Y
Central Hudson |  | Verengo Solar | CH-09892 | Newburgh | New Windsor | Orange | 12553 | G | 4094 | Bethlehem Rd | N |  | 6 | [13 empty] | NM | N | PowerOne PVI-6000 | 2013-10-15 | 2013-10-15 | 0 | 2013-10-15 | [14 empty] | 2013-11-07 | 2013-11-14 |  | Y
Central Hudson |  | New York State Solar Farm | CH-04001 | Newburgh | Newburgh | Orange | 12550 | G | 4014 | West Balmville | N |  | 6 | [13 empty] | NM | N | SUNPOWER SPR6000 | 2013-10-10 | 2013-10-15 | 3 | 2013-10-15 | [14 empty] | 2014-01-13 | 2014-01-20 |  | Y
Central Hudson |  | NRG Home Solar | CH-04670 | Newburgh | New Windsor | Orange | 12553 | G | 4095 | Bethlehem Rd | N | CH-04670 | 6 | [13 empty] | NM | N | POWER-ONE PVI-6000-OUTD-US | 2013-10-11 | 2013-10-16 | 3 | 2013-10-16 | [14 empty] | 2014-01-20 | 2014-01-27 |  | Y
Central Hudson |  | Hudson Solar | CH-01420 | Poughkeepsie | Lagrangevl | Dutchess | 12540 | G | 6055 | Todd Hill | N |  | 6 | [13 empty] | NM | N | POWERONE PVI 6000 | 2013-10-14 | 2013-10-18 | 4 | 2013-10-18 | [14 empty] | 2014-02-11 | 2014-02-12 |  | Y
Central Hudson |  | Hudson Solar | CH-02514 | Kingston | W Shokan |  | 12494 | G | 3011 | Woodstock | TBD |  | 10 | [13 empty] | NM | N | POWERONE PVI 2.0 (2) | 2013-10-14 | 2013-10-18 | 4 | 2013-10-18 | [17 empty] | W
Central Hudson |  | Hudson Solar | CH-02524 | Newburgh | Wallkill |  | 12589 | G | 5041 | East Walden | TBD |  | 3.6 | [13 empty] | NM | N | POWERONE PVI 3.6 | 2013-10-14 | 2013-10-18 | 4 | 2013-10-18 | [8 empty] | 350 | 350 | [7 empty] | W |  | Customer already had net meter prior to application. Transformer upgrade required to accommodate PV installation. Utility System Upgrade Costs TBD. 3/4/14 Customer called to advise that the PV expansion project has been canceled.
Central Hudson |  | Sungevity Inc | CH-09323 | Poughkeepsie | Hopewell Jct | Dutchess | 12533 | G | 6052 | Todd Hill | N |  | 6 | [13 empty] | NM | N | POWER ONE PVI-6000-OUTD-US | 2013-10-14 | 2013-10-18 | 4 | 2013-10-18 | [14 empty] | 2014-04-10 | 2014-04-17 |  | Y
Central Hudson |  | Sungevity Inc | CH-09408 | Kingston | Kingston | Ulster | 12401 | G | 1022 | East Kingston | N |  | 5 | [13 empty] | NM | N | POWER-ONE PVI-5000-OUTD-US-A | 2013-10-14 | 2013-10-18 | 4 | 2013-10-18 | [14 empty] | 2014-01-22 | 2014-01-29 |  | Y
Central Hudson |  | SolarCity | CH-05446 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6045 | Spackenkill | N |  | 3 | [13 empty] | NM | N | SOLAREDGE SE3000A-US | 2013-10-15 | 2013-10-22 | 5 | 2013-10-22 | [14 empty] | 2014-03-04 | 2014-03-11 |  | Y
Central Hudson |  | Sungevity Inc | CH-09206 | Kingston | Saugerties | Ulster | 12477 | G | 3003 | Saugerties | N |  | 6.8 | [13 empty] | NM | N | POWER-ONE PVI-3.8-OUTD-S-US (1) & POWER-ONE PVI-3.0-OUTD-S-US | 2013-10-15 | 2013-10-22 | 5 | 2013-10-22 | [14 empty] | 2014-01-10 | 2014-01-17 |  | Y
Central Hudson |  | New York State Solar Farm | CH-03983 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6051 | Todd Hill | N |  | 9.6 | [13 empty] | NM | N | SUNPOWER SPR 6000P TL (1) & SUNPOWER SPR 3600P TL (1) | 2013-11-14 | 2013-11-21 | 5 | 2013-11-21 | [14 empty] | 2014-03-04 | 2014-03-11 |  | Y
Central Hudson |  | New York State Solar Farm | CH-03991 | Newburgh | New Paltz | Ulster | 12561 | G | 5031 | Galeville | N | CH-03991 | 12 | [13 empty] | NM | N | POWERONE PVI6000 (2) | 2013-10-16 | 2013-10-24 | 6 | 2013-10-24 | [14 empty] | 2013-12-23 | 2013-12-30 |  | Y
Central Hudson |  | Sungevity Inc | CH-09550 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 3 | [13 empty] | NM | N | POWER ONE PVI-3.0-OUTD-S-US | 2013-10-16 | 2013-10-24 | 6 | 2013-10-24 | [14 empty] | 2014-01-22 | 2014-01-29 |  | Y
Central Hudson |  | Direct Energy Solar | CH-01078 | Newburgh | Campbell Hall | Orange | 10916 | G | 5052 | Maybrook | N | CH-00577 | 10.105 | [13 empty] | NM | N | Enphase M215 (47) | 2013-11-01 | 2013-11-08 | 5 | 2013-11-08 | [14 empty] | 2014-01-06 | 2014-01-13 |  | Y
Central Hudson |  | Hudson Valley Wind Energy, LLC | CH-02555 | Poughkeepsie | Ancram | Columbia | 12502 | G | 7091 | Pulvers Corners | Y | CH-02556 | 6.02 | [13 empty] | NM | N | ENPHASE M215 (28) | 2013-11-01 | 2013-11-08 | 5 | 2013-11-08 | [14 empty] | 2014-01-08 | 2014-01-13 |  | Y
Central Hudson |  | SolarCity | CH-05716 | Kingston | Saugerties | Ulster | 12477 | G | 3003 | Saugerties | N |  | 21.4 | [13 empty] | NM | N | FRONIUS USA IG PLUS V 11.4 (1) & FRONIUS USA IG PLUS V 10.0 (1) | 2013-10-17 | 2013-10-30 | 9 | 2013-10-30 | [8 empty] | 350 | 350 |  |  |  |  | 2014-09-08 | 2014-09-15 |  | Y
Central Hudson |  | SolarCity | CH-05958 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7053 | Rhinebeck | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A-US | 2013-10-17 | 2013-10-24 | 5 | 2013-10-24 | [14 empty] | 2013-12-19 | 2013-12-30 |  | Y
Central Hudson |  | NRG Home Solar | CH-04216 | Fishkill | Fishkill | Dutchess | 12524 | G | 8062 | Merritt Park | N |  | 4.2 | [13 empty] | NM | N | POWER-ONE PVI-4.2-OUTD | 2013-10-18 | 2013-10-25 | 5 | 2013-10-25 | [14 empty] | 2014-01-22 | 2014-01-29 |  | Y
Central Hudson |  | NRG Home Solar | CH-04487 | Newburgh | Wallkill | Ulster | 12589 | G | 5043 | East Walden | N |  | 6 | [13 empty] | NM | N | POWER-ONE PVI-6000-OUTD | 2013-10-18 | 2013-10-25 | 5 | 2013-10-25 | [14 empty] | 2014-02-18 | 2014-02-25 |  | Y
Central Hudson |  | NRG Home Solar | CH-04672 | Newburgh | Cornwall | Orange | 12518 | G | 4094 | Bethlehem Rd | N |  | 3 | [13 empty] | NM | N | POWER-ONE PVI-3.0OUTD | 2013-10-18 | 2013-10-25 | 5 | 2013-10-25 | [14 empty] | 2014-01-22 | 2014-01-29 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00895 | Kingston | Stone Ridge | Ulster | 12484 | G | 3023 | High Falls | N |  | 8.815 | [13 empty] | NM | N | ENPHASE M215 (41) | 2013-10-18 | 2013-10-25 | 5 | 2013-10-25 | [14 empty] | 2014-01-27 | 2014-02-03 |  | Y
Central Hudson |  | Hollitronics Energy Solutions | CH-01203 | Catskill | Potter Holw | Albany | 12469 | G | 1092 | Westerlo | N |  | 12.9 | [13 empty] | NM | N | Enphase M215 (60) | 2013-11-04 | 2013-11-18 | 10 | 2013-11-18 | [14 empty] | 2014-03-20 | 2014-03-20 |  | Y
Central Hudson |  | SolarCity | CH-07606 | Newburgh | Milton |  | 12547 | G | 5083 | Highland | TBD |  | 3.8 | [13 empty] | NM | N | SOLAREDGE SE3800A-US | 2013-10-30 | 2013-11-06 | 5 | 2013-11-06 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | RGS Energy | CH-03043 | Kingston | Mt Tremper |  | 12457 | G | 3012 | Woodstock | TBD |  | 15 | [13 empty] | NM | N | FRONIUS IG PLUS V 7.5 (2) | 2013-10-30 | 2013-11-06 | 5 | 2013-11-06 | [8 empty] | 350 | 350 | [7 empty] | W |  | Customer already had net meter prior to application. 10/28/13 Incomplete issued. Transformer upgrade required to accommodate PV installation. Utility System Upgrade Costs TBD.
Central Hudson |  | NRG Home Solar | CH-04680 | Newburgh | Campbell Hall | Orange | 10916 | G | 5051 | Maybrook | N |  | 6 | [13 empty] | NM | N | POWER-ONE PVI-6000-OUTD | 2013-10-21 | 2013-10-28 | 5 | 2013-10-28 | [14 empty] | 2014-02-14 | 2014-02-24 |  | Y
Central Hudson |  | NRG Home Solar | CH-04682 | Newburgh | Montgomery | Orange | 12549 | G | 5071 | Montgomery | N |  | 6 | [13 empty] | NM | N | POWER-ONE PVI-6000-OUTD | 2013-10-21 | 2013-10-28 | 5 | 2013-10-28 | [14 empty] | 2014-03-14 | 2014-03-21 |  | Y
Central Hudson |  | NRG Home Solar | CH-04740 | Newburgh | Newburgh | Orange | 12550 | G | 4014 | West Balmville | N |  | 5 | [13 empty] | NM | N | POWER-ONE PVI-5000-OUTD | 2013-10-21 | 2013-10-28 | 5 | 2013-10-28 | [14 empty] | 2014-05-20 | 2014-05-28 |  | Y
Central Hudson |  | Apex Solar Power | CH-00700 | Kingston | Kingston | Ulster | 12401 | G | 2016 | Lincoln Park | N |  | 16.34 | [13 empty] | NM | N | Enphase M215 (76) | 2013-12-02 | 2013-12-05 | 3 | 2013-12-05 | [8 empty] | 350 | 350 |  |  |  |  | 2014-01-15 | 2014-01-27 |  | Y
Central Hudson |  | NRG Home Solar | CH-04801 | Fishkill | Beacon | Dutchess | 12508 | G | 8017 | Forgebrook | N |  | 4.2 | [13 empty] | NM | N | POWER-ONE PVI-4.2-OUTD | 2013-10-22 | 2013-10-29 | 5 | 2013-10-29 | [14 empty] | 2014-04-30 | 2014-05-07 |  | Y
Central Hudson |  | Monolith Solar Associates LLC | CH-02641 | Catskill | W Coxsackie | Greene | 12192 | G | 1071 | Coxsackie | N |  | 24 | [13 empty] | NM | N | 4 SMA 6000TL-US-22 | 2013-11-13 | 2013-11-26 | 9 | 2013-11-26 | [8 empty] | 350 | 350 |  |  |  |  | 2015-02-25 | 2015-03-09 |  | Y
Central Hudson |  | Sungevity Inc | CH-09171 | Catskill | Athens | Greene | 12015 | G | 2006 | North Catskill | N |  | 12 | [13 empty] | NM | N | POWER ONE PVI-6000-OUTD (2) | 2013-11-01 | 2013-11-08 | 5 | 2013-11-08 | [8 empty] | 350 | 350 |  |  |  |  | 2014-05-05 | 2014-05-12 |  | Y
Central Hudson |  | Sungevity Inc | CH-09588 | Fishkill | Fishkill | Dutchess | 12524 | G | 8094 | Fishkill Plains | N |  | 6 | [13 empty] | NM | N | POWER-ONE PVI-3.0-OUTD (2) | 2013-11-04 | 2013-11-11 | 5 | 2013-11-11 | [14 empty] | 2014-01-02 | 2014-01-09 |  | Y
Central Hudson |  | NRG Home Solar | CH-04305 | Poughkeepsie | Poughkeepsie |  | 12603 | G | 6046 | Spackenkill | TBD |  | 3.6 | [13 empty] | NM | N | POWER-ONE PVI-3.6-OUTD-S-US | 2013-10-23 | 2013-11-05 | 9 | 2013-11-05 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | Solar Generation | CH-08234 | Kingston | Willow | Ulster | 12495 | G | 3012 | Woodstock | N |  | 6.6 | [13 empty] | NM | N | SUNPOWER SPR 3000P (1) & SUNPOWER SPR 3600P (1) | 2013-10-23 | 2013-11-05 | 9 | 2013-11-05 | [8 empty] | 350 | 350 |  | 2013-12-16 | 2013-12-16 | 2014-03-05 | 2014-03-10 | 2014-03-11 |  | Y
Central Hudson |  | Sungevity Inc | CH-09292 | Kingston | Kingston | Ulster | 12401 | G | 2091 | Hurley Ave | N |  | 7 | [13 empty] | NM | N | SMA AMERICA SB7000US | 2013-10-23 | 2013-11-05 | 9 | 2013-11-05 | [14 empty] | 2014-01-08 | 2014-01-15 |  | Y
Central Hudson |  | NRG Home Solar | CH-04233 | Catskill | Hunter | Greene | 12442 | E | 2081 | Hunter | N |  | 5 | [13 empty] | NM | N | POWER-ONE PVI-5000-OUTD-US | 2013-10-24 | 2013-11-05 | 8 | 2013-11-05 | [14 empty] | 2014-04-02 | 2014-04-07 |  | Y
Central Hudson |  | NRG Home Solar | CH-04521 | Kingston | High Fls | Ulster | 12440 | G | 3023 | High Falls | N |  | 5 | [13 empty] | NM | N | POWER-ONE PVI-5000-OUTD | 2013-10-24 | 2013-11-05 | 8 | 2013-11-05 | [14 empty] | 2014-03-26 | 2014-04-01 |  | Y
Central Hudson |  | NRG Home Solar | CH-04660 | Newburgh | Milton | Ulster | 12547 | G | 5083 | Highland | N |  | 3.6 | [13 empty] | NM | N | POWER-ONE PVI-3.6-OUTD-S-US | 2013-10-24 | 2013-11-05 | 8 | 2013-11-05 | [14 empty] | 2014-01-28 | 2014-02-04 |  | Y
Central Hudson |  | NRG Home Solar | CH-04673 | Newburgh | Cornwall | Orange | 12518 | G | 4094 | Bethlehem Rd | N |  | 6 | [13 empty] | NM | N | POWER-ONE PVI-6000-OUTD-US | 2013-10-24 | 2013-11-05 | 8 | 2013-11-05 | [14 empty] | 2014-02-26 | 2014-03-05 |  | Y
Central Hudson |  | NRG Home Solar | CH-04755 | Kingston | Kingston | Ulster | 12401 | G | 2093 | Hurley Ave | N |  | 3.6 | [13 empty] | NM | N | POWER-ONE PVI-3.6-OUTD-S-US | 2013-11-04 | 2013-11-11 | 5 | 2013-11-11 | [14 empty] | 2014-04-17 | 2014-04-17 |  | Y
Central Hudson |  | Solar Generation | CH-08302 | Kingston | Woodstock | Ulster | 12498 | G | 3014 | Woodstock | N |  | 4 | [13 empty] | NM | N | SMA 4000TL-US | 2013-10-24 | 2013-11-05 | 8 | 2013-11-05 | [14 empty] | 2013-12-16 | 2013-12-23 |  | Y
Central Hudson |  | Apex Solar Power | CH-03089 | Catskill | Acra | Greene | 12405 | G | 2041 | South Cairo | N |  | 7.5 | [13 empty] | NM | N | FRONIUS IG PLUS 7.5-1 | 2013-11-20 | 2013-11-26 | 4 | 2013-11-26 | [14 empty] | 2014-05-12 | 2014-05-19 |  | Y
Central Hudson |  | SolarCity | CH-04994 | Kingston | Accord | Ulster | 12404 | G | 3024 | High Falls | N |  | 3 | [13 empty] | NM | N | SOLAREDGE SE3000A-US | 2013-10-28 | 2013-11-05 | 6 | 2013-11-05 | [14 empty] | 2014-02-04 | 2014-02-11 |  | Y
Central Hudson |  | Solar Alchemy | CH-09000 | Kingston | Saugerties | Ulster | 12477 | G | 3005 | Saugerties | N |  | 7 | [13 empty] | NM | N | SolarEdge SE7000A-US | 2013-11-12 | 2013-11-19 | 5 | 2013-11-19 | [14 empty] | 2014-07-24 | 2014-07-24 |  | Y
Central Hudson |  | NRG Home Solar | CH-04847 | Newburgh | Washingtonvl |  | 10992 | G | 4097 | Bethlehem Rd | TBD |  | 9 | [13 empty] | NM | N | POWER-ONE PVI-6000-OUTD-US (1) & POWER-ONE PVI-3.0-OUTD-S-US (1) | 2013-10-29 | 2013-11-05 | 5 | 2013-11-05 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | Sungevity Inc | CH-09310 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6046 | Spackenkill | N |  | 8.4 | [13 empty] | NM | N | POWER-ONE PVI-4.2-OUTD-S-US (2) | 2013-11-05 | 2013-11-08 | 3 | 2013-11-08 | [14 empty] | 2014-04-22 | 2014-04-28 |  | Y
Central Hudson |  | NRG Home Solar | CH-04270 | Kingston | Bloomington |  | 12411 | G | 1011 | Boulevard | TBD |  | 6 | [13 empty] | NM | N | POWER-ONE PVI-6000-OUTD-US | 2013-10-30 | 2013-11-06 | 5 | 2013-11-06 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | NRG Home Solar | CH-04530 | Kingston | Saugerties | Ulster | 12477 | G | 3002 | Saugerties | N |  | 4.2 | [13 empty] | NM | N | POWER-ONE PVI-4.2-OUTD-S-US | 2013-10-30 | 2013-11-06 | 5 | 2013-11-06 | [14 empty] | 2014-04-02 | 2014-04-07 |  | Y
Central Hudson |  | NRG Home Solar | CH-04581 | Fishkill | Wappingers Falls | Dutchess | 12590 | G | 8091 | Fishkill Plains | N |  | 5 | [13 empty] | NM | N | POWER-ONE PVI-5000-OUTD-US | 2013-10-30 | 2013-11-06 | 5 | 2013-11-06 | [14 empty] | 2014-04-11 | 2014-04-21 |  | Y
Central Hudson |  | NRG Home Solar | CH-04614 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8051 | North Chelsea | N |  | 7.2 | [13 empty] | NM | N | POWER-ONE PVI-3.0-OUTD-S-US (1) & POWER-ONE PVI-4.2-OUTD-S-US (1) | 2013-10-30 | 2013-11-06 | 5 | 2013-11-06 | [14 empty] | 2014-04-16 | 2014-04-16 |  | Y
Central Hudson |  | SolarCity | CH-06481 | Kingston | Stone Ridge | Ulster | 12484 | G | 3024 | High Falls | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A-US | 2013-10-30 | 2013-11-06 | 5 | 2013-11-06 | [14 empty] | 2013-12-16 | 2013-12-23 |  | Y
Central Hudson |  | SolarCity | CH-06630 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6044 | Spackenkill | N |  | 3.8 | [13 empty] | NM | N | SOLAREDGE SE3800A-US | 2013-10-31 | 2013-11-07 | 5 | 2013-11-07 | [14 empty] | 2014-02-19 | 2014-02-26 |  | Y
Central Hudson |  | Sungevity Inc | CH-09375 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 8 | [13 empty] | NM | N | SMA AMERICA SB5000TL-US-22 (1) & SMA AMERICA SB3000TL-US-22 (1) | 2013-10-31 | 2013-11-07 | 5 | 2013-11-07 | [14 empty] | 2014-04-10 | 2014-04-17 |  | Y
Central Hudson |  | Sungevity Inc | CH-09228 | Newburgh | Newburgh | Orange | 12550 | G | 5004 | Marlboro | N |  | 6 | [13 empty] | NM | N | POWER-ONE PVI-6000-OUTD-US | 2013-11-01 | 2013-11-08 | 5 | 2013-11-08 | [14 empty] | 2014-05-13 | 2014-05-20 |  | Y
Central Hudson |  | Mountaintop Greene Clean Energy | CH-02708 | Catskill | Purling | Greene | 12470 | G | 2042 | South Cairo | N |  | 40 | [13 empty] | NM | N | FRONIUS IG PLUS V 10.0 (4) | 2013-11-15 | 2013-11-19 | 2 | 2013-11-19 | 2013-11-15 | 2013-11-19 | 2 | [11 empty] | 2014-08-01 | 2014-08-08 |  | Y
Central Hudson |  | SolarCity | CH-07210 | Kingston | Hurley | Ulster | 12443 | G | 2094 | Hurley Ave | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE3800A-SU (2) | 2013-11-04 | 2013-11-11 | 5 | 2013-11-11 | [14 empty] | 2014-02-28 | 2014-03-06 |  | Y
Central Hudson |  | New York State Solar Farm | CH-04020 | Kingston | High Fls | Ulster | 12440 | G | 3024 | High Falls | N |  | 8 | [13 empty] | NM | N | SUNPOWER SPR 8000M | 2013-11-05 | 2013-11-12 | 5 | 2013-11-12 | [14 empty] | 2014-01-23 | 2014-01-30 |  | Y
Central Hudson |  | Direct Energy Solar | CH-01037 | Kingston | Saugerties | Ulster | 12477 | G | 3003 | Saugerties | N |  | 8.815 | [13 empty] | NM | N | ENPHASE ENERGY M215 (41) | 2013-11-05 | 2013-11-12 | 5 | 2013-11-12 | [14 empty] | 2014-03-04 | 2014-03-11 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03637 | Newburgh | Newburgh | Orange | 12550 | G | 4022 | Coldenham | N |  | 11.4 | [13 empty] | NM | N | FRONIUS IG PLUS 11.4-1 | 2013-11-06 | 2013-11-13 | 5 | 2013-11-13 | [14 empty] | 2014-05-07 | 2014-05-14 |  | Y
Central Hudson |  | SolarCity | CH-05710 | Kingston | Ellenvl | Ulster | 12428 | G | 3078 | Greenfield Rd | N |  | 12 | [13 empty] | NM | N | SOLAREDGE SE6000A-US (2) | 2013-11-13 | 2013-11-13 | 0 | 2013-11-13 | [14 empty] | 2013-12-27 | 2013-12-31 |  | Y
Central Hudson |  | Sungevity Inc | CH-09575 | Fishkill | Fishkill | Dutchess | 12524 | G | 8094 | Fishkill Plains | N | CH-09575 | 8 | [13 empty] | NM | N | SMA AMERICA SB8000US-12 | 2013-11-06 | 2013-11-13 | 5 | 2013-11-13 | [14 empty] | 2014-04-22 | 2014-04-28 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-03435 | Newburgh | Cornwall | Orange | 12518 | G | 4093 | Bethlehem Rd | N |  | 10.7 | [13 empty] | NM | N | Sunpower SPR-6501f UNI (1) & PowerOne PVI 4.2 (1) | 2014-01-17 | 2014-01-24 | 5 | 2014-01-24 | [8 empty] | 350 | 350 |  |  |  |  | 2014-03-20 | 2014-03-21 |  | Y
Central Hudson |  | NRG Home Solar | CH-04475 | Newburgh | Newburgh | Orange | 12550 | G | 5004 | Marlboro | N |  | 8 | [13 empty] | NM | N | POWER-ONE PVI-5000-OUTD-US (1) & POWER-ONE PVI-3.0-OUTD-S-US (1) | 2013-11-07 | 2013-11-14 | 5 | 2013-11-14 | [14 empty] | 2014-05-07 | 2014-05-14 |  | W
Central Hudson |  | SolarCity | CH-07169 | Newburgh | New Windsor | Orange | 12553 | G | 4094 | Bethlehem Rd | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A-US | 2013-11-07 | 2013-11-14 | 5 | 2013-11-14 | [14 empty] | 2014-01-24 | 2014-01-31 |  | Y
Central Hudson |  | SolarCity | CH-07318 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7051 | Rhinebeck | N |  | 3.8 | [13 empty] | NM | N | SOLAREDGE SE3800A-US | 2013-11-11 | 2013-11-15 | 4 | 2013-11-15 | [14 empty] | 2014-02-06 | 2014-02-11 |  | Y
Central Hudson |  | NRG Home Solar | CH-04117 | Kingston | Saugerties | Ulster | 12477 | G | 3004 | Saugerties | N |  | 6 | [13 empty] | NM | N | POWER-ONE PVI-6000-OUTD-US | 2013-11-11 | 2013-11-18 | 5 | 2013-11-18 | [14 empty] | 2014-06-13 | 2014-06-20 |  | Y
Central Hudson |  | NRG Home Solar | CH-04250 | Catskill | Ravena | Albany | 12143 | G | 1081 | New Baltimore | N |  | 6 | [13 empty] | NM | N | POWER-ONE PVI-6000-OUTD-US | 2013-11-11 | 2013-11-15 | 4 | 2013-11-15 | [14 empty] | 2014-01-24 | 2014-01-31 |  | Y
Central Hudson |  | NRG Home Solar | CH-04255 | Kingston | Kerhonkson | Ulster | 12446 | G | 3081 | Kerhonkson | N |  | 8 | [13 empty] | NM | N | POWER-ONE PVI-5000-OUTD-US (1) & POWER-ONE PVI-3.0-OUTD-S-US (1) | 2013-11-11 | 2013-11-18 | 5 | 2013-11-18 | [14 empty] | 2014-03-31 | 2014-04-01 |  | Y
Central Hudson |  | Verengo Solar | CH-09844 | Newburgh | Campbell Hall | Orange | 10916 | G | 5051 | Maybrook | N | CH-09844 | 6 | [13 empty] | NM | N | 1 SMA America SBSE5.8-US-50 (240V) [SI1] SMA AMERICA SB6000 | 2013-11-11 | 2013-11-19 | 6 | 2013-11-19 | [14 empty] | 2014-02-21 | 2014-02-28 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03733 | Kingston | Accord | Ulster | 12404 | G | 3024 | High Falls | N |  | 7.74 | [13 empty] | NM | N | ENPHASE M215-60-2LL-S22 | 2013-11-12 | 2013-11-19 | 5 | 2013-11-19 | [14 empty] | 2014-02-18 | 2014-02-25 |  | Y
Central Hudson |  | Hudson Solar | CH-01672 | Kingston | New Paltz | Ulster | 12561 | G | 3022 | High Falls | N |  | 8 | [13 empty] | NM | N | SMA AMERICA SB 8000 | 2013-11-12 | 2013-11-18 | 4 | 2013-11-18 | [14 empty] | 2014-04-23 | 2014-04-29 |  | Y
Central Hudson |  | Hudson Solar | CH-02080 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 6074 | East Park | N | CH-02080 | 7 | [13 empty] | NM | N | SMA SB 7000-US | 2013-11-12 | 2013-11-18 | 4 | 2013-11-18 | [14 empty] | 2014-10-24 | 2014-10-31 |  | Y
Central Hudson |  | Hudson Solar | CH-02157 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7061 | Milan | N | CH-02157 | 15 | [13 empty] | NM | N | SUNPOWER SPR7000M (2)1Sol Ark15K-2P-N | 2013-11-12 | 2013-11-20 | 6 | 2013-11-20 | [8 empty] | 350 | 350 |  |  |  |  | 2014-03-27 | 2014-04-01 |  | Y
Central Hudson |  | SolarCity | CH-06058 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8091 | Fishkill Plains | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A-US | 2013-11-13 | 2013-11-20 | 5 | 2013-11-20 | [14 empty] | 2014-02-25 | 2014-03-04 |  | Y
Central Hudson |  | SolarCity | CH-06509 | Kingston | Kingston | Ulster | 12401 | G | 2017 | Lincoln Park | N |  | 3.8 | [13 empty] | NM | N | SOLAREDGE SE3800A-US | 2013-11-13 | 2013-11-20 | 5 | 2013-11-20 | [14 empty] | 2014-02-25 | 2014-03-04 |  | Y
Central Hudson |  | New York State Solar Farm | CH-03923 | Newburgh | Newburgh | Orange | 12550 | G | 4011 | West Balmville | N |  | 10.5 | [13 empty] | NM | N | Enphase M250 (42) | 2014-01-27 | 2014-01-31 | 4 | 2014-01-31 | [14 empty] | 2014-09-19 | 2014-09-24 |  | Y
Central Hudson |  | Solar Generation | CH-08285 | Kingston | Woodstock | Ulster | 12498 | G | 3014 | Woodstock | N | CH-08285 | 7.2 | [13 empty] | NM | N | SPR 3600P-TL-1 (2) | 2013-11-14 | 2013-11-21 | 5 | 2013-11-21 | [14 empty] | 2014-04-01 | 2014-04-07 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-03419 | Newburgh | Newburgh | Orange | 12550 | G | 4024 | Coldenham | N |  | 6 | [13 empty] | NM | N | PowerOne PVI 6000 | 2013-12-05 | 2013-12-05 | 0 | 2013-12-05 | [14 empty] | 2014-03-26 | 2014-04-01 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03630 | Newburgh | New Paltz | Ulster | 12561 | G | 5021 | Ohioville | N |  | 5.59 | [13 empty] | NM | N | ENPHASE M215 (26) | 2013-11-15 | 2013-11-22 | 5 | 2013-11-22 | [14 empty] | 2014-02-18 | 2014-02-25 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00854 | Newburgh | Pine Bush | Orange | 12566 | G | 5033 | Galeville | N |  | 7.955 | [13 empty] | NM | N | ENPHASE M215 (37) | 2013-11-15 | 2013-11-22 | 5 | 2013-11-22 | [14 empty] | 2014-03-18 | 2014-03-24 |  | Y
Central Hudson |  | Mannino Electric | CH-02592 | Fishkill | Fishkill | Dutchess | 12524 | G | 8061 | Merritt Park | N |  | 42 | [13 empty] | NM | N | CHINT CHPI 14KTL-US (3) | 2013-11-26 | 2013-11-26 | 0 | 2013-11-26 | [14 empty] | 2014-07-18 | 2014-07-22 |  | Y
Central Hudson |  | SolarCity | CH-05907 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 6051 | Todd Hill | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE3800A-US (2) | 2013-11-15 | 2013-11-22 | 5 | 2013-11-22 | [14 empty] | 2014-03-25 | 2014-03-26 |  | Y
Central Hudson |  | SolarCity | CH-07071 | Newburgh | Marlboro | Ulster | 12542 | G | 5004 | Marlboro | N |  | 9.8 | [13 empty] | NM | N | SOLAREDGE SE600A-US & SOLAREDGE SE3800A-US | 2013-11-15 | 2013-11-22 | 5 | 2013-11-22 | [14 empty] | 2014-04-25 | 2014-04-30 |  | Y
Central Hudson |  | Solar Generation | CH-08161 | Kingston | Bearsvl | Ulster | 12409 | G | 3012 | Woodstock | N |  | 8 | [13 empty] | NM | N | SB 4000US (2) | 2013-11-22 | 2013-11-22 | 0 | 2013-11-22 | [14 empty] | 2014-04-02 | 2014-04-02 |  | Y
Central Hudson |  | NRG Home Solar | CH-04306 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6045 | Spackenkill | N |  | 5 | [13 empty] | NM | N | POWER-ONE PVI-5000-OUTD-US | 2013-11-18 | 2013-11-25 | 5 | 2013-11-25 | [14 empty] | 2014-05-02 | 2014-05-08 |  | Y
Central Hudson |  | NRG Home Solar | CH-04375 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8091 | Fishkill Plains | N |  | 6 | [13 empty] | NM | N | SUNPOWER SPR-6000M | 2013-11-18 | 2013-11-25 | 5 | 2013-11-25 | [14 empty] | 2014-04-29 | 2014-05-06 |  | Y
Central Hudson |  | NRG Home Solar | CH-04474 | Newburgh | Newburgh | Orange | 12550 | G | 5004 | Marlboro | N |  | 6 | [13 empty] | NM | N | POWER-ONE PVI-6000-OUTD-US | 2013-11-18 | 2013-11-25 | 5 | 2013-11-25 | [14 empty] | 2014-03-31 | 2014-04-01 |  | Y
Central Hudson |  | NRG Home Solar | CH-04496 | Newburgh | Cornwall-Hdsn | Orange | 12520 | G | 4043 | Union Ave | N |  | 5 | [13 empty] | NM | N | POWER-ONE PVI-5000-OUTD-US | 2013-11-18 | 2013-11-25 | 5 | 2013-11-25 | [14 empty] | 2014-05-14 | 2014-05-20 |  | Y
Central Hudson |  | Murphy Solar Power | CH-02759 | Kingston | Stone Ridge | Ulster | 12484 | G | 3023 | High Falls | N |  | 10 | [13 empty] | NM | N | FRONIUS 10KW IG PLUS V DELTA | 2013-12-16 | 2013-12-19 | 3 | 2013-12-19 | [14 empty] | 2014-07-14 | 2014-07-14 |  | Y
Central Hudson |  | SolarCity | CH-05057 | Newburgh | Highland | Ulster | 12528 | G | 5022 | Ohioville | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A-US | 2013-11-18 | 2013-11-25 | 5 | 2013-11-25 | [14 empty] | 2014-03-18 | 2014-03-25 |  | Y
Central Hudson |  | SolarCity | CH-05261 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6056 | Todd Hill | N |  | 3.6 | [13 empty] | NM | N | POWER ONE PVI-3.6-OUTD-S-US | 2013-11-18 | 2013-11-25 | 5 | 2013-11-25 | [14 empty] | 2014-03-12 | 2014-03-19 |  | Y
Central Hudson |  | SolarCity | CH-05799 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6094 | Manchester | N |  | 3.8 | [13 empty] | NM | N | SOLAREDGE SE3800A-US | 2013-11-18 | 2013-11-25 | 5 | 2013-11-25 | [14 empty] | 2014-03-19 | 2014-03-25 |  | Y
Central Hudson |  | SolarCity | CH-06168 | Newburgh | New Paltz | Ulster | 12561 | G | 5024 | Ohioville | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A-US | 2013-11-18 | 2013-11-25 | 5 | 2013-11-25 | [14 empty] | 2014-03-19 | 2014-03-25 |  | Y
Central Hudson |  | SolarCity | CH-07675 | Newburgh | Newburgh | Orange | 12550 | G | 4054 | Union Ave | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A-US | 2013-11-19 | 2013-11-26 | 5 | 2013-11-26 | [14 empty] | 2014-06-16 | 2014-06-23 |  | Y
Central Hudson |  | SolarCity | CH-04949 | Newburgh | Newburgh | Orange | 12550 | G | 5001 | Marlboro | N |  | 12 | [13 empty] | NM | N | SOLAREDGE SE6000A-US (2) | 2013-11-19 | 2013-11-26 | 5 | 2013-11-26 | [14 empty] | 2014-03-12 | 2014-03-19 |  | Y
Central Hudson |  | SolarCity | CH-05934 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6092 | Manchester | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A-US | 2013-11-19 | 2013-11-26 | 5 | 2013-11-26 | [14 empty] | 2014-03-19 | 2014-03-25 |  | Y
Central Hudson |  | SolarCity | CH-07034 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A-US | 2013-11-19 | 2013-11-26 | 5 | 2013-11-26 | [14 empty] | 2014-05-23 | 2014-06-02 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03608 | Newburgh | Gardiner | Ulster | 12525 | G | 5034 | Galeville | N | CH-03608 | 5 | [13 empty] | NM | N | POWER ONE AURORA PVI5000-OUTD-US | 2013-11-21 | 2013-12-02 | 5 | 2013-12-02 | [14 empty] | 2014-02-06 | 2014-02-13 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00900 | Kingston | Kingston | Ulster | 12401 | G | 2093 | Hurley Ave | N | CH-00900 | 13.545 | [13 empty] | NM | N | ENPHASE ENERGY M216 (63) | 2013-12-02 | 2013-12-05 | 3 | 2013-12-05 | [14 empty] | 2014-03-04 | 2014-03-11 |  | Y
Central Hudson |  | Hudson Solar | CH-01626 | Catskill | Westerlo | Albany | 12193 | G | 1091 | Westerlo | N |  | 6 | [13 empty] | NM | N | SMA SB 6000US | 2013-12-20 | 2013-12-20 | 0 | 2013-12-20 | [14 empty] | 2013-12-26 | 2013-12-30 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07216 | Kingston | Port Ewen | Ulster | 12466 | G | 1012 | Boulevard | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A-US | 2013-11-21 | 2013-11-27 | 4 | 2013-11-27 | [14 empty] | 2014-04-11 | 2014-04-21 |  | Y
Central Hudson |  | Apex Solar Power | CH-03092 | Catskill | Preston Holw | Albany | 12469 | G | 1092 | Westerlo | N |  | 6 | [13 empty] | NM | N | SolarEdge SE 6000 US 240 | 2013-12-11 | 2013-12-23 | 8 | 2013-12-23 | [14 empty] | 2014-06-10 | 2014-06-12 |  | Y
Central Hudson |  | Direct Energy Solar | CH-01073 | Catskill | Preston Holw |  | 12469 | G | 1092 | Westerlo | TBD |  | 7.31 | [13 empty] | NM | N | ENPHASE ENERGY M215 (34) | 2013-12-04 | 2013-12-09 | 3 | 2013-12-09 | [17 empty] | W |  | Customer already had net meter prior to application. 11/28/13 & 11/29/13 Company Holidays. As per email from customer on 6/30/14 this project has been abandoned.
Central Hudson |  | OnForce Solar | CH-02807 | Newburgh | Newburgh | Orange | 12550 | G | 5001 | Marlboro | N |  | 7.5 | [13 empty] | NM | N | SMA SB5000TL & SMA SB2500 | 2013-12-09 | 2013-12-16 | 5 | 2013-12-16 | [14 empty] | 2014-03-17 | 2014-03-24 |  | Y
Central Hudson |  | SolarCity | CH-05190 | Newburgh | Highland | Ulster | 12528 | G | 5083 | Highland | N | CH-05190 | 7.6 | [13 empty] | NM | N | SOLAREDGE SE3800A-US (2) | 2013-12-03 | 2013-12-16 | 9 | 2013-12-16 | [14 empty] | 2014-04-11 | 2014-04-17 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03671 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6056 | Todd Hill | N |  | 9 | [13 empty] | NM | N | POWER ONE AURORA PVI6000US-OUTD-US & POWER ONE AURORA PVI3.0US | 2013-12-04 | 2013-12-16 | 8 | 2013-12-16 | [14 empty] | 2014-03-04 | 2014-03-11 |  | Y
Central Hudson |  | Murphy Solar Power | CH-02744 | Catskill | Earlton | Greene | 12058 | G | 1071 | Coxsackie | N |  | 3 | [13 empty] | NM | N | SMA SB 3000US | 2014-01-23 | 2014-01-30 | 5 | 2014-01-30 | [14 empty] | 2014-04-28 | 2014-05-05 |  | Y
Central Hudson |  | SolarCity | CH-05035 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7053 | Rhinebeck | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A-US | 2013-12-04 | 2013-12-16 | 8 | 2013-12-16 | [14 empty] | 2014-04-11 | 2014-04-21 |  | Y
Central Hudson |  | SolarCity | CH-05320 | Kingston | Olive Brdg | Ulster | 12461 | G | 3024 | High Falls | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A-US | 2013-12-04 | 2013-12-16 | 8 | 2013-12-16 | [14 empty] | 2014-04-15 | 2014-04-23 |  | Y
Central Hudson |  | SolarCity | CH-06690 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 7041 | Staatsburg | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE3800A-US (2) | 2013-12-04 | 2013-12-16 | 8 | 2013-12-16 | [14 empty] | 2014-03-27 | 2014-03-27 |  | Y
Central Hudson |  | SolarCity | CH-06827 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8046 | Myers Corners | N |  | 3 | [13 empty] | NM | N | SOLAREDGE SE3000A-US | 2013-12-04 | 2013-12-16 | 8 | 2013-12-16 | [14 empty] | 2014-04-14 | 2014-04-22 |  | Y
Central Hudson |  | Solar Generation | CH-08306 | Kingston | Woodstock | Ulster | 12498 | G | 3013 | Woodstock | N | CH-08168 | 15 | [13 empty] | NM | N | SMA SB 5000US (3) | 2013-12-04 | 2013-12-16 | 8 | 2013-12-16 | [8 empty] | 350 | 350 |  |  |  |  | 2014-03-28 | 2014-04-02 |  | Y
Central Hudson |  | SolarCity | CH-06563 | Kingston | Ellenvl | Ulster | 12428 | G | 3078 | Greenfield Rd | N |  | 10 | [13 empty] | NM | N | (2) SOLAREDGE SE5000A-US | 2013-12-05 | 2013-12-19 | 10 | 2013-12-19 | [14 empty] | 2014-04-07 | 2014-04-10 |  | Y
Central Hudson |  | SolarCity | CH-07171 | Newburgh | New Windsor | Orange | 12553 | G | 4094 | Bethlehem Rd | N |  | 5 | [13 empty] | NM | N | (1) SOLAREDGE SE5000A-US | 2013-12-05 | 2013-12-19 | 10 | 2013-12-19 | [14 empty] | 2014-05-05 | 2014-05-12 |  | Y
Central Hudson |  | SolarCity | CH-07711 | Fishkill | Beacon | Dutchess | 12508 | G | 8017 | Forgebrook | N |  | 6 | [13 empty] | NM | N | (1) SOLAREDGE SE6000A-US | 2013-12-05 | 2013-12-19 | 10 | 2013-12-19 | [14 empty] | 2014-05-02 | 2014-05-08 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03752 | Newburgh | New Paltz | Ulster | 12561 | G | 5011 | Modena | N |  | 7.6 | [13 empty] | NM | N | POWER ONE AURORA PVI 7.6 (1) | 2013-12-06 | 2013-12-20 | 10 | 2013-12-20 | [14 empty] | 2014-12-05 | 2014-12-11 |  | Y
Central Hudson |  | OnForce Solar | CH-02804 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 6 | [13 empty] | NM | N | PowerOne PVI 6000 | 2014-03-17 | 2014-03-24 | 5 | 2014-03-24 | [14 empty] | 2014-03-24 | 2014-03-24 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07311 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 7024 | Tinkertown | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A-US | 2013-12-09 | 2013-12-20 | 9 | 2013-12-20 | [14 empty] | 2014-05-15 | 2014-05-22 |  | Y
Central Hudson |  | SolarCity | CH-07402 | Fishkill | Beacon | Dutchess | 12508 | G | 8087 | Tioronda | N |  | 3 | [13 empty] | NM | N | SOLAREDGE SE3000A-US | 2013-12-09 | 2013-12-20 | 9 | 2013-12-20 | [14 empty] | 2014-04-14 | 2014-04-22 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03780 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 6074 | East Park | N | CH-03780 | 13.8 | [13 empty] | NM | N | POWER ONE AURORA PVI6000-OUTD-US-S & POWER ONE AURORA PVI4.2-OUTD-US-S (1) POWER ONE AURORA PVI3.6-OUTD-US-S | 2013-12-10 | 2013-12-20 | 8 | 2013-12-20 | [14 empty] | 2014-07-10 | 2014-07-17 |  | Y
Central Hudson |  | NRG Home Solar | CH-04222 | Newburgh | Campbell Hall | Orange | 10916 | G | 5051 | Maybrook | N |  | 7.095 | [13 empty] | NM | N | Enphase M215 (33) | 2013-12-10 | 2013-12-20 | 8 | 2013-12-20 | [14 empty] | 2014-05-23 | 2014-06-02 |  | Y
Central Hudson |  | NRG Home Solar | CH-04718 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8092 | Fishkill Plains | N |  | 4.2 | [13 empty] | NM | N | POWER-ONE PVI-4.2-OUTD-S-US | 2013-12-10 | 2013-12-20 | 8 | 2013-12-20 | [14 empty] | 2014-04-04 | 2014-04-11 |  | Y
Central Hudson |  | NRG Home Solar | CH-04791 | Poughkeepsie | Verbank | Dutchess | 12585 | G | 6057 | Todd Hill | N |  | 4.2 | [13 empty] | NM | N | POWER-ONE PVI-4.2-OUTD-S-US | 2013-12-10 | 2013-12-20 | 8 | 2013-12-20 | [14 empty] | 2014-03-18 | 2014-03-25 |  | Y
Central Hudson |  | OnForce Solar | CH-02802 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 6 | [13 empty] | NM | N | PowerOne PVI 6000 OUTD US | 2013-12-10 | 2013-12-20 | 8 | 2013-12-20 | [14 empty] | 2014-02-11 | 2014-02-19 |  | Y
Central Hudson |  | Solar Generation | CH-08118 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7062 | Milan | N |  | 10 | [13 empty] | NM | N | (2) SMA SB5000TL | 2013-12-10 | 2013-12-20 | 8 | 2013-12-20 | [14 empty] | 2014-01-14 | 2014-01-21 |  | Y
Central Hudson |  | Sol Providers | CH-08923 | Poughkeepsie | Clinton Corners | Dutchess | 12514 | G | 7013 | Hibernia | N | CH-08923 | 5 | [13 empty] | NM | N | SMA 5000W TL | 2013-12-23 | 2013-12-30 | 3 | 2013-12-30 | [14 empty] | 2014-06-24 | 2014-07-01 |  | Y
Central Hudson |  | Sol Providers | CH-08947 | Poughkeepsie | Millbrook | Dutchess | 12545 | G | 7012 | Hibernia | N |  | 6.88 | [13 empty] | NM | N | Enphase M215 (32) | 2014-02-12 | 2014-02-20 | 5 | 2014-02-20 | [14 empty] | 2014-05-08 | 2014-05-14 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03709 | Newburgh | Clintondale | Ulster | 12515 | G | 5012 | Modena | N |  | 7 | [13 empty] | NM | N | POWER-ONE AURORA PVI5000-OUTD-US & POWER-ONE AURORA UNO2.0-I | 2013-12-11 | 2013-12-23 | 8 | 2013-12-23 | [14 empty] | 2014-11-07 | 2014-11-11 |  | Y
Central Hudson |  | NRG Home Solar | CH-04341 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6055 | Todd Hill | N |  | 5 | [13 empty] | NM | N | POWER-ONE PVI-5000-OUTD-S-US | 2013-12-11 | 2013-12-20 | 7 | 2013-12-20 | [14 empty] | 2014-05-02 | 2014-05-08 |  | Y
Central Hudson |  | NRG Home Solar | CH-04688 | Kingston | Kingston | Ulster | 12401 | G | 2013 | Lincoln Park | N |  | 8.4 | [13 empty] | NM | N | POWER-ONE PVI-4.2-OUTD-S-US (2) | 2013-12-11 | 2013-12-20 | 7 | 2013-12-20 | [14 empty] | 2014-04-17 | 2014-04-17 |  | Y
Central Hudson |  | OnForce Solar | CH-02805 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N | CH-22528 | 10.2 | [13 empty] | NM | N | POWERONE PVI6000 & POWERONE PV 4.2 | 2013-12-11 | 2013-12-23 | 8 | 2013-12-23 | [14 empty] | 2014-03-03 | 2014-03-05 |  | Y
Central Hudson |  | SolarCity | CH-06524 | Newburgh | Ulster Pk | Ulster | 12487 | G | 5084 | Highland | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A-US | 2014-01-15 | 2014-01-16 | 1 | 2014-01-16 | [14 empty] | 2014-03-19 | 2014-03-25 |  | Y
Central Hudson |  | Monolith Solar Associates LLC | CH-02668 | Kingston | Kingston |  | 12401 | G | 121 | Converse St | TBD |  | 45.6 | [13 empty] | NM | N | FRONIUS IG PLUS 11.4 (4) | 2013-12-16 | 2013-12-23 | 5 | 2013-12-23 | [17 empty] | W
Central Hudson |  | SolarCity | CH-05913 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6051 | Todd Hill | N |  | 8.8 | [13 empty] | NM | N | SOLAREDGE SE5000A-US & SOLAREDGE SE3800A-US | 2013-12-16 | 2013-12-23 | 5 | 2013-12-23 | [14 empty] | 2014-03-25 | 2014-03-25 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03736 | Kingston | Stone Ridge | Ulster | 12484 | G | 3023 | High Falls | N | CH-03736 | 4.2 | [13 empty] | NM | N | POWER-ONE AURORA PVI4.2-OUTD-US | 2013-12-17 | 2013-12-23 | 4 | 2013-12-23 | [14 empty] | 2014-03-27 | 2014-04-01 |  | Y
Central Hudson |  | Conscious Energy | CH-00796 | Kingston | High Fls | Ulster | 12440 | G | 3024 | High Falls | N | CH-00796 | 15 | [13 empty] | NM | N | SMA SB 5000 TL (3) | 2013-12-18 | 2013-12-23 | 3 | 2013-12-23 | [8 empty] | 350 | 350 |  |  |  |  | 2014-04-04 | 2014-04-04 |  | Y
Central Hudson |  | Lotus Energy Inc. | CH-03848 | Catskill | Palenvl | Greene | 12463 | G | 2001 | North Catskill | N |  | 6 | [13 empty] | NM | N | SUNPOWER SPR6000 | 2013-12-19 | 2013-12-30 | 5 | 2013-12-30 | [14 empty] | 2014-04-01 | 2014-04-07 |  | Y
Central Hudson |  | Sol Providers | CH-08924 | Poughkeepsie | Verbank | Dutchess | 12585 | G | 6057 | Todd Hill | N |  | 10 | [13 empty] | RNM | N | SMA 5000TL (2) | 2013-12-31 | 2014-01-07 | 4 | 2014-01-07 | [14 empty] | 2014-08-08 | 2014-08-13 |  | Y
Central Hudson |  | Sol Providers | CH-08937 | Newburgh | Marlboro | Ulster | 12542 | G | 5003 | Marlboro | N |  | 8 | [13 empty] | NM | N | SMA 4000TL (2) | 2013-12-31 | 2014-01-07 | 4 | 2014-01-07 | [14 empty] | 2014-08-07 | 2014-08-12 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-03371 | Newburgh | Highland Mls | Orange | 10930 | G | 4041 | Union Ave | N |  | 6.5 | [13 empty] | NM | N | SPR-6501f-240 | 2013-12-26 | 2014-01-07 | 7 | 2014-01-07 | [14 empty] | 2014-04-03 | 2014-04-08 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00856 | Newburgh | Campbell Hall | Orange | 10916 | G | 5052 | Maybrook | N |  | 8.815 | [13 empty] | NM | N | ENPHASE ENERGY M215 (41) | 2013-12-27 | 2014-01-06 | 5 | 2014-01-06 | [14 empty] | 2014-03-18 | 2014-03-18 |  | Y
Central Hudson |  | In House Group | CH-02557 | Kingston | Kerhonkson | Ulster | 12446 | G | 3081 | Kerhonkson | N |  | 1.8 | [13 empty] | NM | N | Solectria PVI 1800 | 2014-01-08 | 2014-01-08 | 0 | 2014-01-08 | [14 empty] | 2014-08-06 | 2014-08-14 |  | Y
Central Hudson |  | SolarCity | CH-07635 | Kingston | Woodstock | Ulster | 12498 | G | 3013 | Woodstock | N |  | 3.8 | [13 empty] | NM | N | SOLAREDGE SE3800A-US | 2013-12-30 | 2014-01-07 | 5 | 2014-01-07 | [14 empty] | 2014-04-11 | 2014-04-21 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03658 | Kingston | Kerhonkson | Ulster | 12446 | G | 3082 | Kerhonkson | N |  | 20 | [13 empty] | NM | N | FRONIUS IG PLUS 10.0-1 UNI (2) | 2014-01-02 | 2014-01-08 | 4 | 2014-01-08 | [8 empty] | 350 | 350 |  |  |  |  | 2014-05-28 | 2014-06-03 |  | Y
Central Hudson |  | SolarCity | CH-05780 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6046 | Spackenkill | N |  | 3.8 | [13 empty] | NM | N | SOLAREDGE SE3800A-US | 2014-01-02 | 2014-01-09 | 5 | 2014-01-09 | [14 empty] | 2014-04-14 | 2014-04-22 |  | Y
Central Hudson |  | SolarCity | CH-07412 | Newburgh | New Paltz | Ulster | 12561 | G | 5024 | Ohioville | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A-US | 2014-01-02 | 2014-01-09 | 5 | 2014-01-09 | [14 empty] | 2014-05-02 | 2014-05-08 |  | Y
Central Hudson |  | New York Light Energy, LLC | CH-02770 | Catskill | Ravena | Albany | 12143 | G | 1082 | New Baltimore | N |  | 150 | [13 empty] | NM | N | Advanced Energy AE 250TX (Manufacturer Curtailed to 150kW) | 2014-02-03 | 2014-02-25 | 15 | 2014-02-25 | 2014-02-03 | 2014-02-25 | 15 | [11 empty] | 2014-03-26 | 2014-03-27 |  | Y
Central Hudson |  | SolarCity | CH-05876 | Poughkeepsie | Lagrangevl |  | 12540 | G | 6057 | Todd Hill | TBD |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A-US | 2014-01-06 | 2014-01-20 | 10 | 2014-01-20 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | Sea Bright Solar LLC | CH-08857 | Newburgh | Newburgh | Orange | 12550 | G | 4023 | Coldenham | N |  | 10 | [13 empty] | NM | N | SPR-5000P-TL (2) | 2014-01-16 | 2014-01-23 | 5 | 2014-01-23 | [8 empty] | 350 | 350 |  |  |  |  | 2014-06-23 | 2014-07-02 |  | Y
Central Hudson |  | Sungevity Inc | CH-09203 | Newburgh | Marlboro | Ulster | 12542 | G | 5004 | Marlboro | N | CH-09203 | 3 | [13 empty] | NM | N | SMA AMERICA SB3000TLUS-22 | 2014-01-06 | 2014-01-10 | 4 | 2014-01-10 | [14 empty] | 2014-05-14 | 2014-05-20 |  | Y
Central Hudson |  | Sungevity Inc | CH-09213 | Fishkill | Hopewell Jct |  | 12533 | G | 8072 | Shenandoah | TBD |  | 8 | [13 empty] | NM | N | SMA AMERICA SB8000US-12 | 2014-01-06 | 2014-01-10 | 4 | 2014-01-10 | [17 empty] | W
Central Hudson |  | Sungevity Inc | CH-09504 | Newburgh | Washingtonvl | Orange | 10992 | G | 5052 | Maybrook | N |  | 13.6 | [13 empty] | NM | N | POWER-ONE PVI-3.8-OUTD (2) & POWERONE PVI-6000-OUTD (1) | 2014-01-06 | 2014-01-20 | 10 | 2014-01-20 | [14 empty] | 2014-05-08 | 2014-05-15 |  | Y
Central Hudson |  | Sungevity Inc | CH-09522 | Kingston | Ellenville | Ulster | 12428 | G | 3078 | Greenfield Rd | N | CH-09522 | 7.6 | [13 empty] | NM | N | POWER-ONE PVI-3.8-OUTD (2) | 2014-01-06 | 2014-01-10 | 4 | 2014-01-10 | [14 empty] | 2014-05-13 | 2014-05-20 |  | W
Central Hudson |  | SolarCity | CH-05316 | Newburgh | Montgomery | Orange | 12549 | G | 5054 | Maybrook | N |  | 10 | [13 empty] | NM | N | SOLAREDGE SE5000A-US (2) | 2014-01-07 | 2014-01-20 | 9 | 2014-01-20 | [14 empty] | 2014-04-23 | 2014-04-30 |  | Y
Central Hudson |  | Solar Generation | CH-08249 | Poughkeepsie | Staatsburg | Dutchess | 12580 | G | 7011 | Hibernia | N |  | 14 | [13 empty] | NM | N | SMA SB7000US (2) | 2014-01-07 | 2014-01-20 | 9 | 2014-01-20 | [14 empty] | 2014-02-05 | 2014-02-12 |  | Y
Central Hudson |  | Hudson Solar | CH-01801 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 6051 | Todd Hill | N |  | 6 | [13 empty] | NM | N | POWERONE PVI 6000 | 2014-01-08 | 2014-01-20 | 8 | 2014-01-20 | [14 empty] | 2014-02-11 | 2014-02-12 |  | Y
Central Hudson |  | SolarCity | CH-05639 | Kingston | High Fls | Ulster | 12440 | G | 3022 | High Falls | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A-US | 2014-01-08 | 2014-01-20 | 8 | 2014-01-20 | [14 empty] | 2014-05-05 | 2014-05-12 |  | Y
Central Hudson |  | SolarCity | CH-06100 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8014 | Forgebrook | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A-US | 2014-02-27 | 2014-03-04 | 3 | 2014-03-04 | [14 empty] | 2014-04-23 | 2014-04-23 |  | Y
Central Hudson |  | SolarCity | CH-06466 | Catskill | Coxsackie | Greene | 12051 | G | 1074 | Coxsackie | N |  | 3.6 | [13 empty] | NM | N | POWER ONE PVI-3.6-OUTD-S-US | 2014-01-09 | 2014-01-21 | 8 | 2014-01-21 | [14 empty] | 2014-04-14 | 2014-04-22 |  | Y
Central Hudson |  | Hudson Valley Wind Energy, LLC | CH-02549 | Fishkill | Garrison |  | 10524 | G | 8086 | Tioronda | N |  |  |  | 10 | [11 empty] | NM | N | DIVERSIFIED TECHNOLOGY AMFA27 POWERSYNC2 | 2014-01-20 | 2014-01-27 | 5 | 2014-01-27 | [14 empty] | 2014-03-25 | 2014-03-31 |  | W
Central Hudson |  | SolarCity | CH-05294 | Newburgh | Wallkill | Ulster | 12589 | G | 5013 | Modena | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE600A-US | 2014-01-13 | 2014-01-21 | 6 | 2014-01-21 | [14 empty] | 2014-09-25 | 2014-10-01 |  | Y
Central Hudson |  | SolarCity | CH-07671 | Newburgh | New Paltz |  | 12561 | G | 5024 | Ohioville | TBD |  | 6 | [13 empty] | NM | N | SOLAR EDGE SE6000A | 2014-01-13 | 2014-01-21 | 6 | 2014-01-21 | [17 empty] | W
Central Hudson |  | SolarCity | CH-06091 | Fishkill | Fishkill | Dutchess | 12524 | G | 8094 | Fishkill Plains | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A-US | 2014-01-14 | 2014-01-21 | 5 | 2014-01-21 | [14 empty] | 2014-04-11 | 2014-04-17 |  | Y
Central Hudson |  | NRG Home Solar | CH-04559 | Poughkeepsie | Billings | Dutchess | 12510 | G | 6057 | Todd Hill | N |  | 4 | [13 empty] | NM | N | SPR 4000 | 2014-01-15 | 2014-01-22 | 5 | 2014-01-22 | [14 empty] | 2014-04-29 | 2014-05-06 |  | Y
Central Hudson |  | Hudson Solar | CH-02225 | Catskill | S Westerlo | Greene | 12083 | G | 1091 | Westerlo | N |  | 9 | [13 empty] | NM | N | SMA SB 5000TL & SMA SB 4000TL | 2014-01-15 | 2014-01-22 | 5 | 2014-01-22 | [14 empty] | 2014-04-21 | 2014-04-24 |  | Y
Central Hudson |  | RER Energy Group, LLC. | CH-04899 | Fishkill | Cold Spg | Putnam | 10516 | G | 8063 | Merritt Park | N |  | 19 | [13 empty] | NM | N | SMA SB7000 (2) & SMA SB5000 (1) | 2014-01-27 | 2014-01-31 | 4 | 2014-01-31 | [8 empty] | 350 | 350 |  |  |  |  | 2014-09-27 | 2014-09-27 |  | Y
Central Hudson |  | Hudson Solar | CH-02306 | Fishkill | Cold Spg | Putnam | 10516 | G | 8063 | Merritt Park | Y |  | 6 | 6 | [12 empty] | NM | N | XANTREX XW6048-120/240-601XantrexXW6048 (DC) | 2014-01-16 | 2014-01-28 | 8 | 2014-01-28 | [14 empty] | 2014-04-21 | 2014-04-25 |  | Y
Central Hudson |  | SolarCity | CH-05097 | Poughkeepsie | Millbrook | Dutchess | 12545 | G | 7012 | Hibernia | N |  | 1368 | [13 empty] | RNM | N | SolarMax MTA 18 (76) | 2014-02-19 | 2014-03-11 | 14 | 2014-03-11 | 2014-02-19 | 2014-03-11 | 14 | 2014-03-21 | 2014-03-20 | 2014-06-16 | 60 | 16500 | 160000 | 180496 |  | 2014-08-11 | 2014-08-11 | 2015-02-25 | 2015-03-25 | 2015-03-31 |  | Y
Central Hudson |  | SolarCity | CH-07245 | Kingston | Kingston | Ulster | 12401 | G | 2017 | Lincoln Park | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A-US | 2014-01-16 | 2014-01-23 | 5 | 2014-01-23 | [14 empty] | 2014-05-02 | 2014-05-08 |  | Y
Central Hudson |  | Paradise Energy Solutions LLC | CH-02852 | Kingston | W Hurley | Ulster | 12491 | G | 2094 | Hurley Ave | Y | CH-09716 | 8 | [13 empty] | NM | N | SE5000-240V & SE3000A-240V | 2014-01-29 | 2014-02-05 | 5 | 2014-02-05 | [8 empty] | 350 | 350 |  |  |  |  | 2014-04-24 | 2014-04-30 |  | Y
Central Hudson |  | SolarCity | CH-07118 | Newburgh | Cornwall | Orange | 12518 | G | 4093 | Bethlehem Rd | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A-US | 2014-01-17 | 2014-01-24 | 5 | 2014-01-24 | [14 empty] | 2014-04-11 | 2014-04-21 |  | Y
Central Hudson |  | SolarCity | CH-07156 | Newburgh | Newburgh | Orange | 12550 | G | 4052 | Union Ave | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A-US | 2014-10-15 | 2014-10-22 | 5 | 2014-10-22 | [14 empty] | 2015-05-13 | 2015-05-19 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Sungevity Inc | CH-09440 | Newburgh | Highland | Ulster | 12528 | G | 5083 | Highland | N |  | 6 | [13 empty] | NM | N | POWER-ONE PVI-6000-OUTD-US | 2014-01-17 | 2014-01-24 | 5 | 2014-01-24 | [14 empty] | 2014-05-14 | 2014-05-20 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03603 | Newburgh | Marlboro | Ulster | 12542 | G | 5004 | Marlboro | N |  | 12 | [13 empty] | NM | N | POWER-ONE AURORA PVI6000-OUTD-US (2) | 2014-01-20 | 2014-01-27 | 5 | 2014-01-27 | [14 empty] | 2014-07-01 | 2014-07-09 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03678 | Newburgh | New Paltz | Ulster | 12561 | G | 5031 | Galeville | N |  | 12 | [13 empty] | NM | N | POWER-ONE AURORA PVI6000-OUTD-US (2) | 2014-01-20 | 2014-01-27 | 5 | 2014-01-27 | [8 empty] | 350 | 350 |  |  |  |  | 2014-04-21 | 2014-04-22 |  | Y
Central Hudson |  | New York State Solar Farm | CH-03930 | Newburgh | Gardiner | Ulster | 12525 | G | 5034 | Galeville | N |  | 12 | [13 empty] | NM | N | SUNPOWER SPR-6000 (2) | 2014-01-27 | 2014-01-28 | 1 | 2014-01-28 | [14 empty] | 2014-03-31 | 2014-04-04 |  | Y
Central Hudson |  | Sungevity Inc | CH-09576 | Newburgh | Gardiner | Ulster | 12525 | G | 5031 | Galeville | N | CH-09576 | 5 | [13 empty] | NM | N | SMA AMERICA SB5000TL-US-22 | 2014-01-20 | 2014-01-27 | 5 | 2014-01-27 | [14 empty] | 2014-05-22 | 2014-05-23 |  | Y
Central Hudson |  | Verengo Solar | CH-09783 | Newburgh | Campbell Hall | Orange | 10916 | G | 5051 | Maybrook | N |  | 6 | [13 empty] | NM | N | SMA SB6000 US | 2014-01-20 | 2014-01-27 | 5 | 2014-01-27 | [14 empty] | 2014-03-06 | 2014-03-07 |  | Y
Central Hudson |  | SolarCity | CH-06674 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7041 | Staatsburg | N |  | 9 | [13 empty] | NM | N | SOLAREDGE SE600A-US & SOLAREDGE SE3000A-US | 2014-01-21 | 2014-01-28 | 5 | 2014-01-28 | [14 empty] | 2014-07-17 | 2014-07-24 |  | Y
Central Hudson |  | SolarCity | CH-04947 | Fishkill | Cold Spg | Putnam | 10516 | G | 8063 | Merritt Park | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A-US | 2014-01-22 | 2014-01-29 | 5 | 2014-01-29 | [14 empty] | 2014-04-11 | 2014-04-21 |  | Y
Central Hudson |  | NRG Home Solar | CH-04181 | Newburgh | Milton | Ulster | 12547 | G | 5003 | Marlboro | N |  | 3.225 | [13 empty] | NM | N | ENPHASE ENERGY M-215-60-2LL-S22 (15) | 2014-01-30 | 2014-02-03 | 2 | 2014-02-03 | [14 empty] | 2014-04-08 | 2014-04-15 |  | Y
Central Hudson |  | NRG Home Solar | CH-04297 | Kingston | Saugerties | Ulster | 12477 | G | 2015 | Lincoln Park | N |  | 5 | [13 empty] | NM | N | POWER-ONE PVI-5000-OUTD-US | 2014-01-23 | 2014-01-30 | 5 | 2014-01-30 | [14 empty] | 2014-03-18 | 2014-03-25 |  | Y
Central Hudson |  | NRG Home Solar | CH-04380 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8044 | Myers Corners | N |  | 6 | [13 empty] | NM | N | POWER-ONE PVI-6000-OUTD-US | 2014-01-30 | 2014-02-03 | 2 | 2014-02-03 | [14 empty] | 2014-04-04 | 2014-04-10 |  | Y
Central Hudson |  | NRG Home Solar | CH-04399 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8092 | Fishkill Plains | N |  | 6 | [13 empty] | NM | N | POWER-ONE PVI-6000-OUTD-US | 2014-01-23 | 2014-01-30 | 5 | 2014-01-30 | [14 empty] | 2014-04-25 | 2014-05-01 |  | Y
Central Hudson |  | NRG Home Solar | CH-04505 | Newburgh | Rock Tvrn | Orange | 12575 | G | 4097 | Bethlehem Rd | N |  | 14 | [13 empty] | NM | N | POWER-ONE PVI-6000-OUTD, POWER-ONE PVI-3.0-OUTD & POWER-ONE PVI-5000-OUTD | 2014-01-30 | 2014-02-03 | 2 | 2014-02-03 | [14 empty] | 2014-05-23 | 2014-05-23 |  | Y
Central Hudson |  | NRG Home Solar | CH-04512 | Newburgh | Campbell Hall | Orange | 10916 | G | 5051 | Maybrook | N |  | 7.74 | [13 empty] | NM | N | ENPHASE ENERGY M-215-60-2LL-S22 (36) | 2014-01-30 | 2014-02-03 | 2 | 2014-02-03 | [14 empty] | 2014-04-04 | 2014-04-11 |  | Y
Central Hudson |  | NRG Home Solar | CH-04572 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7056 | Rhinebeck | N |  | 3.6 | [13 empty] | NM | N | POWER-ONE PVI-3.6-OUTD-S-US | 2014-01-30 | 2014-02-03 | 2 | 2014-02-03 | [14 empty] | 2014-05-06 | 2014-05-13 |  | Y
Central Hudson |  | Murphy Solar Power | CH-02757 | Catskill | Catskill | Greene | 12414 | G | 2003 | North Catskill | N |  | 4 | [13 empty] | NM | N | SMA 4000us | 2014-03-31 | 2014-03-31 | 0 | 2014-03-31 | [14 empty] | 2014-04-08 | 2014-04-15 |  | W |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | New York State Solar Farm | CH-03951 | Newburgh | Milton | Ulster | 12547 | G | 5083 | Highland | N |  | 11.5 | [13 empty] | NM | N | Enphase Energy M250 (46) | 2014-02-03 | 2014-02-03 | 0 | 2014-02-03 | [14 empty] | 2014-04-29 | 2014-05-07 |  | Y
Central Hudson |  | New York State Solar Farm | CH-04006 | Newburgh | Marlboro | Ulster | 12542 | G | 5003 | Marlboro | N |  | 6 | [13 empty] | NM | N | Enphase Energy M250 (24) | 2014-01-24 | 2014-01-31 | 5 | 2014-01-31 | [14 empty] | 2014-05-14 | 2014-05-14 |  | Y
Central Hudson |  | You Save Green | CH-09958 | Fishkill | Beacon | Dutchess | 12508 | G | 8016 | Forgebrook | N |  | 4 | [13 empty] | NM | N | SMA SB4000 TL | 2014-02-18 | 2014-02-21 | 3 | 2014-02-21 | [14 empty] | 2014-07-14 | 2014-07-21 |  | Y
Central Hudson |  | RGS Energy | CH-03007 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 6074 | East Park | N |  | 7.5 | [13 empty] | NM | N | FRONIUS IG PLUS V 7.5-240 | 2014-01-28 | 2014-02-04 | 5 | 2014-02-04 | [14 empty] | 2014-04-23 | 2014-04-29 |  | Y
Central Hudson |  | NRG Home Solar | CH-04266 | Kingston | Port Ewen | Ulster | 12466 | G | 1012 | Boulevard | N |  | 5.59 | [13 empty] | NM | N | ENPHASE ENERGY (26) | 2014-01-28 | 2014-02-04 | 5 | 2014-02-04 | [14 empty] | 2014-04-21 | 2014-04-22 |  | Y
Central Hudson |  | Sol Providers | CH-08916 | Catskill | Round Top | Greene | 12473 | G | 2042 | South Cairo | N |  | 6 | [13 empty] | NM | N | SMA 6000 | 2014-02-10 | 2014-02-18 | 5 | 2014-02-18 | [14 empty] | 2014-07-01 | 2014-07-01 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-03386 | Newburgh | New Windsor | Orange | 12553 | G | 4097 | Bethlehem Rd | N |  | 12 | [13 empty] | NM | N | PowerOne PVI 6000 (2) | 2014-02-11 | 2014-02-19 | 5 | 2014-02-19 | [14 empty] | 2014-02-28 | 2014-03-07 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | NRG Home Solar | CH-04796 | Newburgh | Newburgh | Orange | 12550 | G | 4053 | Union Ave | N |  | 3.01 | [13 empty] | NM | N | ENPHASE ENERGY M215 (14) | 2014-01-29 | 2014-02-05 | 5 | 2014-02-05 | [14 empty] | 2014-09-10 | 2014-09-16 |  | Y
Central Hudson |  | SolarCity | CH-07529 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6002 | Reynolds Hill | N |  | 3 | [13 empty] | NM | N | SOLAREDGE SE3000A-US | 2014-01-29 | 2014-02-05 | 5 | 2014-02-05 | [14 empty] | 2014-04-21 | 2014-04-28 |  | Y
Central Hudson |  | NRG Home Solar | CH-04185 | Newburgh | Goshen | Orange | 10924 | G | 5051 | Maybrook | N |  | 8.385 | [13 empty] | NM | N | ENPHASE ENERGY M-215-60-2LL-S22 (39) | 2014-02-06 | 2014-02-10 | 2 | 2014-02-10 | [14 empty] | 2014-06-09 | 2014-06-16 |  | Y
Central Hudson |  | NRG Home Solar | CH-04265 | Kingston | Kingston | Ulster | 12401 | G | 1022 | East Kingston | N |  | 4.3 | [13 empty] | NM | N | ENPHASE ENERGY M-215-60-2LL-S22 (20) | 2014-01-30 | 2014-02-06 | 5 | 2014-02-06 | [14 empty] | 2014-06-05 | 2014-06-12 |  | Y
Central Hudson |  | SolarCity | CH-04977 | Catskill | Catskill | Greene | 12414 | G | 2001 | North Catskill | N |  | 12 | [13 empty] | NM | N | SOLAREDGE SE600A-US (2) | 2014-01-30 | 2014-02-06 | 5 | 2014-02-06 | [14 empty] | 2014-04-21 | 2014-04-24 |  | Y
Central Hudson |  | SolarCity | CH-05085 | Newburgh | Mountainvl | Orange | 10953 | G | 4095 | Bethlehem Rd | Y | CH-05085 | 3 | [13 empty] | NM | N | SOLAREDGE SE3000A-US | 2014-01-30 | 2014-02-06 | 5 | 2014-02-06 | [8 empty] | 350 | 350 |  | 2015-02-24 | 2015-02-24 | 2015-03-10 | 2014-04-11 | 2014-04-21 |  | Y
Central Hudson |  | NRG Home Solar | CH-04241 | Catskill | Freehold | Greene | 12431 | G | 2061 | Freehold | N |  | 5 | [13 empty] | NM | N | POWER-ONE PVI-5000-OUTD-US | 2014-01-31 | 2014-02-10 | 6 | 2014-02-10 | [14 empty] | 2014-04-02 | 2014-04-07 |  | Y
Central Hudson |  | NRG Home Solar | CH-04652 | Newburgh | Wallkill | Ulster | 12589 | G | 5012 | Modena | N |  | 8.385 | [13 empty] | NM | N | ENPHASE ENERGY M-215-60-2LL-S22 (39) | 2014-01-31 | 2014-02-10 | 6 | 2014-02-10 | [14 empty] | 2014-05-28 | 2014-05-28 |  | Y
Central Hudson |  | SolarCity | CH-06232 | Newburgh | Newburgh | Orange | 12550 | G | 4012 | West Balmville | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A-US | 2014-02-03 | 2014-02-10 | 5 | 2014-02-10 | [14 empty] | 2014-04-30 | 2014-05-07 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-03469 | Newburgh | Pine Bush | Orange | 12566 | G | 5033 | Galeville | N |  | 10 | [13 empty] | NM | N | SUNPOWER SPR-1000IF | 2014-05-22 | 2014-05-30 | 5 | 2014-05-30 | [8 empty] | 350 | 350 |  |  |  |  | 2014-07-11 | 2014-07-18 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Lighthouse Solar | CH-03771 | Newburgh | Wallkill | Ulster | 12589 | G | 5043 | East Walden | N |  | 7.5 | [13 empty] | NM | N | FRONIUS IG PLUS 07.5-1 UNI | 2014-02-04 | 2014-02-11 | 5 | 2014-02-11 | [14 empty] | 2014-05-22 | 2014-05-30 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00845 | Kingston | Ruby | Ulster | 12475 | G | 2016 | Lincoln Park | N |  | 10.105 | [13 empty] | NM | N | ENPHASE ENERGY M215 (47) | 2014-02-04 | 2014-02-11 | 5 | 2014-02-11 | [14 empty] | 2015-02-04 | 2015-02-11 |  | Y
Central Hudson |  | NRG Home Solar | CH-04848 | Newburgh | Montgomery |  | 12549 | G | 4021 | Coldenham | TBD |  | 4.945 | [13 empty] | NM | N | ENPHASE ENERGY M-215-60-2LL-S22 (23) | 2014-02-05 | 2014-02-12 | 5 | 2014-02-12 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | Direct Energy Solar | CH-00839 | Kingston | Kingston | Ulster | 12401 | G | 1011 | Boulevard | N |  | 12.9 | [13 empty] | NM | N | ENPHASE ENERGY M215 (60) | 2014-02-05 | 2014-02-12 | 5 | 2014-02-12 | [14 empty] | 2014-04-21 | 2014-04-21 |  | Y
Central Hudson |  | SolarCity | CH-07595 | Newburgh | Newburgh |  | 12550 | G | 4022 | Coldenham | TBD |  | 8 | [13 empty] | NM | N | SOLAREDGE SE5000A-US & SOLAREDGE SE3000A-US | 2014-02-05 | 2014-02-12 | 5 | 2014-02-12 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | Sungevity Inc | CH-09266 | Kingston | Olive Brdg | Ulster | 12461 | G | 3024 | High Falls | N |  | 5 | [13 empty] | NM | N | SMA AMERICA SB5000TL-US-22 | 2014-02-05 | 2014-02-12 | 5 | 2014-02-12 | [14 empty] | 2014-07-07 | 2014-07-07 |  | Y
Central Hudson |  | Sungevity Inc | CH-09367 | Newburgh | New Paltz | Ulster | 12561 | G | 5024 | Ohioville | N | CH-09367 | 5 | [13 empty] | NM | N | SMA AMERICA SB5000TL-US-22 | 2014-02-05 | 2014-02-12 | 5 | 2014-02-12 | [14 empty] | 2014-05-30 | 2014-06-06 |  | Y
Central Hudson |  | New York State Solar Farm | CH-03929 | Newburgh | Newburgh | Orange | 12550 | G | 5004 | Marlboro | N |  | 7 | [13 empty] | NM | N | SMA AMERICA SMA SUNNY BOY 7000 | 2014-02-18 | 2014-02-25 | 5 | 2014-02-25 | [14 empty] | 2014-08-11 | 2014-08-14 |  | Y
Central Hudson |  | SolarCity | CH-07336 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8091 | Fishkill Plains | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A-US | 2014-02-07 | 2014-02-14 | 5 | 2014-02-14 | [14 empty] | 2014-04-25 | 2014-04-30 |  | Y
Central Hudson |  | SolarCity | CH-07339 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8091 | Fishkill Plains | N |  | 15 | [13 empty] | NM | N | SOLAREDGE SE5000A-US (3) | 2014-02-07 | 2014-02-14 | 5 | 2014-02-14 | [14 empty] | 2014-05-05 | 2014-05-12 |  | Y
Central Hudson |  | SolarCity | CH-07666 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8093 | Fishkill Plains | N |  | 3.8 | [13 empty] | NM | N | SOLAREDGE SE3800A-US | 2014-02-07 | 2014-02-18 | 6 | 2014-02-18 | [14 empty] | 2014-04-30 | 2014-05-07 |  | Y
Central Hudson |  | SolarCity | CH-07763 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8091 | Fishkill Plains | N |  | 11 | [13 empty] | NM | N | SOLAREDGE SE6000A-US & SOLAREDGE SE5000A-US | 2014-03-05 | 2014-03-05 | 0 | 2014-03-05 | [14 empty] | 2014-06-20 | 2014-06-26 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00957 | Newburgh | New Paltz | Ulster | 12561 | G | 5024 | Ohioville | N |  | 7.955 | [13 empty] | NM | N | ENPHASE ENERGY M215 (37) | 2014-02-20 | 2014-02-28 | 6 | 2014-02-28 | [14 empty] | 2014-04-02 | 2014-04-07 |  | Y
Central Hudson |  | SolarCity | CH-05022 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 6074 | East Park | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A-US | 2014-02-10 | 2014-02-18 | 5 | 2014-02-18 | [14 empty] | 2014-05-05 | 2014-05-12 |  | Y
Central Hudson |  | Sungevity Inc | CH-09559 | Catskill | Greenvl | Greene | 12083 | G | 2061 | Freehold | N |  | 15 | [13 empty] | NM | N | POWER-ONE PVI-6000-OUTD-US-A (2) & POWER-ONE PVI-3.0-OUTD-S-US-A (1) | 2014-02-11 | 2014-02-19 | 5 | 2014-02-19 | [14 empty] | 2014-05-12 | 2014-05-19 |  | Y
Central Hudson |  | Murphy Solar Power | CH-02732 | Catskill | Leeds | Greene | 12451 | G | 2005 | North Catskill | N |  | 3 | [13 empty] | NM | N | SMA 3000 US | 2014-02-12 | 2014-02-20 | 5 | 2014-02-20 | [14 empty] | 2014-04-08 | 2014-04-15 |  | Y
Central Hudson |  | Novel Approaches | CH-02784 | Kingston | Ellenvl | Ulster | 12428 | G | 3076 | Greenfield Rd | N |  | 16 | [13 empty] | NM | N | SMA SB8000 (2) | 2014-02-12 | 2014-02-20 | 5 | 2014-02-20 | [14 empty] | 2014-06-20 | 2014-06-26 |  | Y
Central Hudson |  | SolarCity | CH-05805 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6093 | Manchester | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A-US | 2014-02-12 | 2014-02-20 | 5 | 2014-02-20 | [14 empty] | 2014-04-28 | 2014-05-05 |  | Y
Central Hudson |  | Sungevity Inc | CH-09178 | Kingston | Stone Ridge | Ulster | 12484 | G | 3023 | High Falls | N |  | 8 | [13 empty] | NM | N | SMA AMERICA SB8000US-12 | 2014-02-21 | 2014-02-28 | 5 | 2014-02-28 | [14 empty] | 2014-06-10 | 2014-06-17 |  | Y
Central Hudson |  | Direct Energy Solar | CH-01010 | Fishkill | Poughkeepsie | Dutchess | 12601 | G | 8024 | Knapps Corners | N |  | 7.095 | [13 empty] | NM | N | ENPHASE ENERGY M215 (33) | 2014-02-14 | 2014-02-24 | 5 | 2014-02-24 | [14 empty] | 2014-04-08 | 2014-04-15 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03743 | Newburgh | New Paltz | Ulster | 12561 | G | 5031 | Galeville | N |  | 7.6 | [13 empty] | NM | N | SolarEdge SE7600A-US | 2014-02-18 | 2014-03-03 | 9 | 2014-03-03 | [14 empty] | 2014-06-17 | 2014-06-24 |  | Y
Central Hudson |  | New York State Solar Farm | CH-03981 | Poughkeepsie | Staatsburg | Dutchess | 12580 | G | 7042 | Staatsburg | N |  | 6 | [13 empty] | NM | N | PowerOnce 6000 PVI | 2014-02-27 | 2014-03-03 | 2 | 2014-03-03 | [14 empty] | 2014-05-12 | 2014-05-19 |  | Y
Central Hudson |  | NRG Home Solar | CH-04724 | Fishkill | Fishkill |  | 12524 | G | 8014 | Forgebrook | TBD |  | 5.59 | [13 empty] | NM | N | ENPHASE M215 (26) | 2014-02-18 | 2014-03-03 | 9 | 2014-03-03 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | Sol Providers | CH-08927 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6092 | Manchester | N |  | 11.4 | [13 empty] | NM | N | SolarEdge 11400A-US | 2014-02-18 | 2014-03-03 | 9 | 2014-03-03 | [14 empty] | 2015-05-07 | 2015-05-13 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-03383 | Newburgh | Cornwall-Hdsn | Orange | 12520 | G | 4041 | Union Ave | N |  | 7.5 | [13 empty] | NM | N | SUNPOWER SPR-7501F | 2014-02-20 | 2014-03-03 | 7 | 2014-03-03 | [14 empty] | 2014-05-15 | 2014-05-22 |  | Y
Central Hudson |  | Hudson Solar | CH-01298 | Poughkeepsie | Staatsburg | Dutchess | 12580 | G | 7041 | Staatsburg | N |  | 5 | [13 empty] | NM | N | POWERONE PVI 5000 | 2014-02-20 | 2014-03-03 | 7 | 2014-03-03 | [14 empty] | 2014-03-27 | 2014-04-01 |  | Y
Central Hudson |  | SolarCity | CH-06019 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8043 | Myers Corners | N |  | 6 | [13 empty] | NM | N | SE6000A-US | 2014-02-28 | 2014-03-05 | 3 | 2014-03-05 | [14 empty] | 2015-02-25 | 2015-03-04 |  | Y
Central Hudson |  | Murphy Solar Power | CH-02716 | Catskill | Leeds | Greene | 12451 | G | 2005 | North Catskill | N |  | 5 | [13 empty] | NM | N | SMA 5000US | 2014-02-24 | 2014-03-05 | 7 | 2014-03-05 | [14 empty] | 2014-09-19 | 2014-09-26 |  | Y
Central Hudson |  | Sungevity Inc | CH-09273 | Kingston | Stone Ridge | Ulster | 12484 | G | 3023 | High Falls | N |  | 5 | [13 empty] | NM | N | SMA AMERICA SB5000TL-US-22 | 2014-02-24 | 2014-03-05 | 7 | 2014-03-05 | [14 empty] | 2014-05-05 | 2014-05-12 |  | Y
Central Hudson |  | Sungevity Inc | CH-09446 | Newburgh | Highland | Ulster | 12528 | G | 5082 | Highland | N |  | 5 | [13 empty] | NM | N | SMA AMERICA SB5000TL-US-22 | 2014-02-26 | 2014-03-05 | 5 | 2014-03-05 | [14 empty] | 2014-04-24 | 2014-04-30 |  | Y
Central Hudson |  | NRG Home Solar | CH-04637 | Newburgh | Newburgh | Orange | 12550 | G | 4012 | West Balmville | N |  | 6.45 | [13 empty] | NM | N | ENPHASE ENERGY M-215-60-2LL-S22 (30) | 2014-02-27 | 2014-03-05 | 4 | 2014-03-05 | [14 empty] | 2014-05-21 | 2014-05-28 |  | Y
Central Hudson |  | SolarCity | CH-06553 | Newburgh | Ulster Pk | Ulster | 12487 | G | 5084 | Highland | N |  | 17.5 | [13 empty] | NM | N | FRONIUS USA IG PLUS A 10.0 & FRONIUS USA IG PLUS A 7.5 | 2014-06-04 | 2014-06-11 | 5 | 2014-06-11 | [14 empty] | 2014-10-01 | 2014-10-08 |  | Y
Central Hudson |  | SolarCity | CH-07421 | Newburgh | Newburgh | Orange | 12550 | G | 4023 | Coldenham | N |  | 3.8 | [13 empty] | NM | N | SOLAREDGE SE3800A-US | 2014-02-27 | 2014-03-05 | 4 | 2014-03-05 | [14 empty] | 2014-05-28 | 2014-06-03 |  | Y
Central Hudson |  | Sunrise Solar Solutions, LLC | CH-09662 | Kingston | Stone Ridge | Ulster | 12484 | G | 3023 | High Falls | N |  | 5.16 | [13 empty] | NM | N | ENPHASE M215 (33) | 2014-03-06 | 2014-03-07 | 1 | 2014-03-07 | [14 empty] | 2015-04-23 | 2015-04-23 |  | Y
Central Hudson |  | Hudson Solar | CH-02499 | Kingston | Kingston | Ulster | 12401 | G | 1014 | Boulevard | Y | CH-01700 | 6 | 6 | [12 empty] | NM | N | Xantrex XW60481XantrexXW6048 (DC) | 2014-03-03 | 2014-03-10 | 5 | 2014-03-10 | [8 empty] | 350 | 350 |  |  |  |  | 2014-08-12 | 2014-08-19 |  | Y
Central Hudson |  | SolarCity | CH-05715 | Kingston | Saugerties | Ulster | 12477 | G | 3003 | Saugerties | N |  | 15 | [13 empty] | NM | N | FRONIUS IG PLUS 7.5 (2) | 2014-03-03 | 2014-03-17 | 10 | 2014-03-17 | [14 empty] | 2014-07-29 | 2014-07-29 |  | Y
Central Hudson |  | Hudson Solar | CH-01474 | Kingston | Port Ewen | Ulster | 12466 | G | 1012 | Boulevard | N |  | 5 | [13 empty] | NM | N | POWERONE PVI 5000 | 2014-03-05 | 2014-03-12 | 5 | 2014-03-12 | [14 empty] | 2014-05-14 | 2014-05-20 |  | Y
Central Hudson |  | Hudson Solar | CH-01636 | Catskill | Hannacroix | Greene | 12087 | G | 1083 | New Baltimore | N |  | 8 | [13 empty] | NM | N | SMA SB 4000TL-US (2) | 2014-03-05 | 2014-03-12 | 5 | 2014-03-12 | [14 empty] | 2014-06-12 | 2014-06-19 |  | Y
Central Hudson |  | Hudson Solar | CH-02172 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8092 | Fishkill Plains | N | CH-02172 | 8 | [13 empty] | NM | N | SMA SB 4000TL-US (2) | 2014-03-05 | 2014-03-12 | 5 | 2014-03-12 | [14 empty] | 2014-05-05 | 2014-05-12 |  | Y
Central Hudson |  | NRG Home Solar | CH-04468 | Newburgh | Plattekill | Ulster | 12568 | G | 5013 | Modena | N |  | 5.59 | [13 empty] | NM | N | ENPHASE ENERGY M-215-60-2LL-S22 (26) | 2014-03-06 | 2014-03-12 | 4 | 2014-03-12 | [14 empty] | 2014-06-12 | 2014-06-19 |  | Y
Central Hudson |  | Sungevity Inc | CH-09234 | Kingston | Kingston | Ulster | 12401 | G | 1012 | Boulevard | N |  | 6 | [13 empty] | NM | N | POWER-ONE PVI-6000-OUTD | 2014-03-07 | 2014-03-14 | 5 | 2014-03-14 | [14 empty] | 2014-06-11 | 2014-06-18 |  | Y
Central Hudson |  | New York State Solar Farm | CH-04032 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8056 | North Chelsea | N |  | 9 | [13 empty] | NM | N | POWER ONE PVI 5000 & POWER ONE PVI 4000 | 2014-03-10 | 2014-03-14 | 4 | 2014-03-14 | [14 empty] | 2014-06-20 | 2014-06-26 |  | Y
Central Hudson |  | NRG Home Solar | CH-04168 | Poughkeepsie | Staatsburg | Dutchess | 12580 | G | 7011 | Hibernia | N |  | 4.3 | [13 empty] | NM | N | ENPHASE ENERGY M-215-60-2LL-S22 (20) | 2014-03-10 | 2014-03-14 | 4 | 2014-03-14 | [14 empty] | 2014-06-13 | 2014-06-20 |  | Y
Central Hudson |  | NRG Home Solar | CH-04348 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 7024 | Tinkertown | N |  | 4.085 | [13 empty] | NM | N | ENPHASE ENERGY M-215-60-2LL-S22 (19) | 2014-03-10 | 2014-03-14 | 4 | 2014-03-14 | [14 empty] | 2014-07-02 | 2014-07-10 |  | Y
Central Hudson |  | NRG Home Solar | CH-04481 | Newburgh | Marlboro | Ulster | 12542 | G | 5004 | Marlboro | N |  | 6.665 | [13 empty] | NM | N | ENPHASE ENERGY M-215-60-2LL-S22 (31) | 2014-03-10 | 2014-03-14 | 4 | 2014-03-14 | [14 empty] | 2014-05-28 | 2014-06-03 |  | Y
Central Hudson |  | Murphy Solar Power | CH-02733 | Catskill | Leeds | Greene | 12451 | G | 2006 | North Catskill | N |  | 8 | [13 empty] | NM | N | SMA 8000 US | 2014-03-10 | 2014-03-14 | 4 | 2014-03-14 | [14 empty] | 2014-09-15 | 2014-09-22 |  | Y
Central Hudson |  | NRG Home Solar | CH-04668 | Newburgh | Cornwall | Orange | 12518 | G | 4093 | Bethlehem Rd | N |  | 9.675 | [13 empty] | NM | N | ENPHASE ENERGY M-215-60-2LL-S22 (45) | 2014-03-11 | 2014-03-17 | 4 | 2014-03-17 | [14 empty] | 2014-06-17 | 2014-06-24 |  | Y
Central Hudson |  | SolarCity | CH-06980 | Newburgh | Walden | Orange | 12586 | G | 5043 | East Walden | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A-US | 2014-03-18 | 2014-03-25 | 5 | 2014-03-25 | [14 empty] | 2014-05-09 | 2014-05-16 |  | Y
Central Hudson |  | Sungevity Inc | CH-09189 | Poughkeepsie | Tivoli | Dutchess | 12583 | G | 7062 | Milan | N |  | 6.8 | [13 empty] | NM | N | POWER-ONE PVI-3.0-OUTD & POWER-ONE PVI-3.8-OUTD | 2014-04-16 | 2014-04-16 | 0 | 2014-04-16 | [14 empty] | 2014-05-30 | 2014-06-06 |  | Y
Central Hudson |  | Positive Energy NY, LLC | CH-02930 | Catskill | Alcove | Albany | 12007 | G | 1081 | New Baltimore | N |  | 14 | [13 empty] | NM | N | SMA SB 7000 US (2) | 2014-03-19 | 2014-03-21 | 2 | 2014-03-21 | [14 empty] | 2014-06-19 | 2014-06-24 |  | Y
Central Hudson |  | SolarCity | CH-06810 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8044 | Myers Corners | N |  | 3 | [13 empty] | NM | N | SOLAREDGE SE3000A-US | 2014-03-18 | 2014-03-19 | 1 | 2014-03-19 | [14 empty] | 2014-07-16 | 2014-07-23 |  | Y
Central Hudson |  | New York State Solar Farm | CH-03922 | Poughkeepsie | Lagrangevl | Dutchess | 12540 | G | 6057 | Todd Hill | N |  | 23 | [13 empty] | NM | N | SMA AMERICA SUNNY BOY 8.0 (2) & SMA AMERICA SUNNY BOY 7.0 | 2014-03-13 | 2014-03-19 | 4 | 2014-03-19 | [8 empty] | 350 | 350 |  |  |  |  | 2014-06-27 | 2014-07-07 |  | Y
Central Hudson |  | NRG Home Solar | CH-04771 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8092 | Fishkill Plains | N |  | 4.73 | [13 empty] | NM | N | ENPHASE ENERGY M-215-60-2LL-S22 (22) | 2014-03-13 | 2014-03-19 | 4 | 2014-03-19 | [14 empty] | 2014-05-30 | 2014-06-06 |  | Y
Central Hudson |  | NRG Home Solar | CH-04463 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 6.02 | [13 empty] | NM | N | ENPHASE ENERGY M-215-60-2LL-S22 (28) | 2014-03-14 | 2014-03-21 | 5 | 2014-03-21 | [14 empty] | 2014-06-03 | 2014-06-10 |  | Y
Central Hudson |  | SolarCity | CH-05579 | Catskill | Athens | Greene | 12015 | G | 2002 | North Catskill | N |  | 8.8 | [13 empty] | NM | N | SOLAREDGE SE5000A-US & SOLAREDGE SE3800A-US | 2014-03-25 | 2014-03-31 | 4 | 2014-03-31 | [14 empty] | 2014-06-03 | 2014-06-10 |  | Y
Central Hudson |  | SolarCity | CH-07255 | Poughkeepsie | Poughkeepsie |  | 12601 | G | 6011 | Sand Dock | TBD |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A-US | 2014-03-14 | 2014-03-21 | 5 | 2014-03-21 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | Sungevity Inc | CH-09278 | Kingston | Tillson | Ulster | 12486 | G | 3022 | High Falls | N |  | 9.8 | [13 empty] | NM | N | POWER-ONE PVI-3.8-OUTD & POWER-ONE PVI-6000-OUTD | 2014-03-14 | 2014-03-21 | 5 | 2014-03-21 | [14 empty] | 2014-06-03 | 2014-06-10 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03644 | Newburgh | Wallkill | Ulster | 12589 | G | 5041 | East Walden | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE7600A-US | 2014-03-17 | 2014-03-24 | 5 | 2014-03-24 | [14 empty] | 2014-06-24 | 2014-07-01 |  | Y
Central Hudson |  | New York State Solar Farm | CH-03924 | Newburgh | Gardiner | Ulster | 12525 | G | 5031 | Galeville | N |  | 7.6 | [13 empty] | NM | N | SE7600A-US | 2014-03-18 | 2014-03-25 | 5 | 2014-03-25 | [14 empty] | 2014-06-03 | 2014-06-10 |  | Y
Central Hudson |  | Sungevity Inc | CH-09290 | Kingston | W Shokan | Ulster | 12494 | G | 3011 | Woodstock | N |  | 7 | [13 empty] | NM | N | SMA AMERICA SB7000US-12 | 2014-03-18 | 2014-03-25 | 5 | 2014-03-25 | [14 empty] | 2014-06-30 | 2014-06-30 |  | Y
Central Hudson |  | Sungevity Inc | CH-09477 | Newburgh | Newburgh | Orange | 12550 | G | 4012 | West Balmville | N |  | 7 | [13 empty] | NM | N | SMA AMERICA SB7000US-12 | 2014-03-18 | 2014-03-25 | 5 | 2014-03-25 | [14 empty] | 2014-05-19 | 2014-05-27 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03734 | Kingston | Kerhonkson | Ulster | 12446 | G | 3081 | Kerhonkson | N |  | 12.6 | [13 empty] | NM | N | SOLAREDGE SE7600A-US & SOLAREDGE SE5000A-US | 2014-03-19 | 2014-03-25 | 4 | 2014-03-25 | [14 empty] | 2014-08-21 | 2014-08-28 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00972 | Newburgh | Cornwall | Orange | 12518 | G | 4043 | Union Ave | N |  | 9.46 | [13 empty] | NM | N | ENPHASE M-215 (44) | 2014-03-19 | 2014-03-25 | 4 | 2014-03-25 | [14 empty] | 2014-05-27 | 2014-06-03 |  | Y
Central Hudson |  | Mountaintop Greene Clean Energy | CH-02705 | Catskill | Freehold | Greene | 12431 | G | 2071 | Freehold | N |  | 5 | [13 empty] | NM | N | SMA SB5000TL | 2014-03-20 | 2014-03-25 | 3 | 2014-03-25 | [14 empty] | 2014-06-19 | 2014-06-26 |  | Y
Central Hudson |  | SolarCity | CH-05046 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8091 | Fishkill Plains | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A-US | 2014-03-20 | 2014-03-26 | 4 | 2014-03-26 | [14 empty] | 2014-05-05 | 2014-05-12 |  | Y
Central Hudson |  | SolarCity | CH-05052 | Fishkill | Beacon |  | 12508 | G | 8015 | Forgebrook | TBD |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A-US | 2014-03-20 | 2014-03-27 | 5 | 2014-03-27 | [14 empty] | 2014-07-17 | 2014-07-24 |  | W
Central Hudson |  | SolarCity | CH-07744 | Fishkill | Fishkill |  | 12524 | G | 8014 | Forgebrook | TBD |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE3800A-US (2) | 2014-03-20 | 2014-03-27 | 5 | 2014-03-27 | [17 empty] | W
Central Hudson |  | Sungevity Inc | CH-09480 | Newburgh | Newburgh | Orange | 12550 | G | 4044 | Union Ave | N |  | 4 | [13 empty] | NM | N | SMA AMERICA SB4000TL-US-22 | 2014-03-21 | 2014-03-28 | 5 | 2014-03-28 | [14 empty] | 2014-05-13 | 2014-05-20 |  | Y
Central Hudson |  | NRG Home Solar | CH-04603 | Fishkill | Fishkill | Dutchess | 12524 | G | 8065 | Merritt Park | N |  | 5.59 | [13 empty] | NM | N | ENPHASE ENERGY M-215-60-2LL-S22 (26) | 2014-03-24 | 2014-03-28 | 4 | 2014-03-28 | [14 empty] | 2014-06-10 | 2014-06-17 |  | Y
Central Hudson |  | NRG Home Solar | CH-04763 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 6073 | East Park | N |  | 3 | [13 empty] | NM | N | PowerOne PVI 3.0 | 2014-03-25 | 2014-03-31 | 4 | 2014-03-31 | [14 empty] | 2014-07-14 | 2014-07-21 |  | Y
Central Hudson |  | Solar Generation | CH-08270 | Kingston | Woodstock | Ulster | 12498 | G | 3013 | Woodstock | N | CH-08270 | 3 | [13 empty] | NM | N | SMA SB3000TL | 2014-03-25 | 2014-03-31 | 4 | 2014-03-31 | [14 empty] | 2014-04-10 | 2014-04-17 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | NRG Home Solar | CH-04712 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6092 | Manchester | N |  | 3.44 | [13 empty] | NM | N | Enphase M215 (16) | 2014-03-27 | 2014-04-02 | 4 | 2014-04-02 | [14 empty] | 2014-06-06 | 2014-06-13 |  | Y
Central Hudson |  | Hudson Solar | CH-01648 | Kingston | Krumvl |  | 12461 | G | 3024 | High Falls | TBD |  | 5 | [13 empty] | NM | N | PowerOne PVI-5000-OUTD-US | 2014-03-27 | 2014-04-02 | 4 | 2014-04-02 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | Hudson Solar | CH-01781 | Poughkeepsie | Lagrangevl | Dutchess | 12540 | G | 6053 | Todd Hill | N |  | 5 | [13 empty] | NM | N | SMA AMERICA SB5000 | 2014-03-27 | 2014-04-02 | 4 | 2014-04-02 | [14 empty] | 2014-05-05 | 2014-05-12 |  | Y
Central Hudson |  | Hudson Solar | CH-01963 | Newburgh | Clintondale | Ulster | 12515 | G | 5012 | Modena | N |  | 5 | [13 empty] | NM | N | SMA AMERICA SB5000 | 2014-03-27 | 2014-04-02 | 4 | 2014-04-02 | [14 empty] | 2014-05-05 | 2014-05-12 |  | Y
Central Hudson |  | Hudson Solar | CH-01665 | Kingston | Ulster Pk | Ulster | 12487 | G | 3041 | Sturgeon Pool | N |  | 5 | [13 empty] | NM | N | POWERONE PVI-5000 | 2014-03-31 | 2014-04-04 | 4 | 2014-04-04 | [14 empty] | 2014-04-21 | 2014-04-25 |  | Y
Central Hudson |  | Hudson Solar | CH-02169 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8095 | Fishkill Plains | N | CH-02169 | 4 | [13 empty] | NM | N | SMA AMERICA SB4000 | 2014-03-31 | 2014-04-04 | 4 | 2014-04-04 | [14 empty] | 2014-05-19 | 2014-05-27 |  | Y
Central Hudson |  | Sungevity Inc | CH-09366 | Newburgh | New Paltz | Ulster | 12561 | G | 5011 | Modena | N |  | 8 | [13 empty] | NM | N | SMA AMERICA SB8000US-12 | 2014-03-31 | 2014-04-07 | 5 | 2014-04-07 | [14 empty] | 2014-06-19 | 2014-06-26 |  | Y
Central Hudson |  | New York State Solar Farm | CH-03935 | Newburgh | Wallkill | Ulster | 12589 | G | 5041 | East Walden | N | CH-03935 | 7.6 | [13 empty] | NM | N | SolarEdge SE7600A-US | 2014-04-07 | 2014-04-07 | 0 | 2014-04-07 | [14 empty] | 2014-05-30 | 2014-06-06 |  | Y
Central Hudson |  | Sol Providers | CH-08948 | Poughkeepsie | Clinton Corners | Dutchess | 12514 | G | 7013 | Hibernia | N |  | 8 | [13 empty] | NM | N | SMA 4000TL (2) | 2014-04-21 | 2014-04-22 | 1 | 2014-04-22 | [14 empty] | 2014-06-24 | 2014-07-01 |  | Y
Central Hudson |  | Sungevity Inc | CH-09595 | Kingston | Kingston | Ulster | 12401 | G | 1022 | East Kingston | N |  | 6 | [13 empty] | NM | N | POWER-ONE PVI-6000-OUTD-US | 2014-04-01 | 2014-04-07 | 4 | 2014-04-07 | [14 empty] | 2014-06-06 | 2014-06-13 |  | Y
Central Hudson |  | NRG Home Solar | CH-04138 | Newburgh | New Windsor | Orange | 12553 | G | 4097 | Bethlehem Rd | N |  | 9.03 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (42) | 2014-04-02 | 2014-04-08 | 4 | 2014-04-08 | [14 empty] | 2014-06-10 | 2014-06-17 |  | Y
Central Hudson |  | SolarCity | CH-05662 | Kingston | Kingston | Ulster | 12401 | G | 1014 | Boulevard | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A-US | 2014-04-09 | 2014-04-09 | 0 | 2014-04-09 | [14 empty] | 2014-06-11 | 2014-06-18 |  | Y
Central Hudson |  | SolarCity | CH-05688 | Kingston | Hurley | Ulster | 12443 | G | 2094 | Hurley Ave | N | CH-05688 | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A-US | 2014-04-09 | 2014-04-10 | 1 | 2014-04-10 | [14 empty] | 2014-05-05 | 2014-05-12 |  | Y
Central Hudson |  | SolarCity | CH-06308 | Newburgh | Newburgh | Orange | 12550 | G | 4011 | West Balmville | N |  | 8.8 | [13 empty] | NM | N | SOLAREDGE SE3800A-US & SOLAREDGE SE5000A-US | 2014-04-02 | 2014-04-08 | 4 | 2014-04-08 | [14 empty] | 2014-05-15 | 2014-05-22 |  | Y
Central Hudson |  | SolarCity | CH-06471 | Catskill | W Coxsackie | Greene | 12192 | G | 1071 | Coxsackie | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A-US | 2014-04-02 | 2014-04-08 | 4 | 2014-04-08 | [14 empty] | 2014-05-16 | 2014-05-23 |  | Y
Central Hudson |  | SolarCity | CH-06789 | Newburgh | Highland | Ulster | 12528 | G | 5082 | Highland | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A-US | 2014-04-02 | 2014-04-07 | 3 | 2014-04-07 | [14 empty] | 2014-05-02 | 2014-05-08 |  | Y
Central Hudson |  | SolarCity | CH-07001 | Newburgh | Newburgh | Orange | 12550 | G | 4012 | West Balmville | N |  | 10 | [13 empty] | NM | N | SOLAREDGE SE5000A-US (2) | 2014-06-12 | 2014-06-19 | 5 | 2014-06-19 | [14 empty] | 2014-06-26 | 2014-07-03 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07346 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8052 | North Chelsea | N |  | 3.8 | [13 empty] | NM | N | SOLAREDGE SE3800A-US | 2014-04-02 | 2014-04-08 | 4 | 2014-04-08 | [14 empty] | 2014-07-08 | 2014-07-15 |  | Y
Central Hudson |  | NRG Home Solar | CH-04491 | Newburgh | Wallkill | Ulster | 12589 | G | 5042 | East Walden | N |  | 8.6 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (40) | 2014-04-08 | 2014-04-08 | 0 | 2014-04-08 | [8 empty] | 350 | 350 |  |  |  |  | 2014-06-05 | 2014-06-12 |  | Y
Central Hudson |  | SolarCity | CH-06754 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7055 | Rhinebeck | N |  | 9.8 | [13 empty] | NM | N | SOLAREDGE SE6000A-US & SOLAREDGE SE3800A-US | 2014-04-03 | 2014-04-10 | 5 | 2014-04-10 | [14 empty] | 2014-10-03 | 2014-10-10 |  | Y
Central Hudson |  | SolarCity | CH-07578 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8071 | Shenandoah | N |  | 8 | [13 empty] | NM | N | SOLAREDGE SE5000A-US & SOLAREDGE SE3000A-US | 2014-04-03 | 2014-04-08 | 3 | 2014-04-08 | [14 empty] | 2014-09-16 | 2014-09-18 |  | Y
Central Hudson |  | Solar Generation | CH-08076 | Kingston | Saugerties | Ulster | 12477 | G | 3003 | Saugerties | N |  | 6 | [13 empty] | NM | N | SMA SB3000TL-US (2) | 2014-04-09 | 2014-04-10 | 1 | 2014-04-10 | [14 empty] | 2014-05-07 | 2014-05-14 |  | Y
Central Hudson |  | Solar Generation | CH-08143 | Kingston | Samsonvl | Ulster | 12461 | G | 3082 | Kerhonkson | N | CH-08143 | 6 | [13 empty] | NM | N | SMA SB 6000 | 2014-04-03 | 2014-04-10 | 5 | 2014-04-10 | [14 empty] | 2014-05-05 | 2014-05-12 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03715 | Newburgh | Gardiner | Ulster | 12525 | G | 5011 | Modena | N |  | 6 | [13 empty] | NM | N | POWER ONE AURORA PVI6000-OUTD-US | 2014-04-04 | 2014-04-11 | 5 | 2014-04-11 | [14 empty] | 2014-08-04 | 2014-08-08 |  | Y
Central Hudson |  | RGS Energy | CH-03041 | Newburgh | Rock Tvrn | Orange | 12575 | G | 4097 | Bethlehem Rd | N |  | 15 | [13 empty] | NM | N | FRONIUS IG PLUS 10.0-1 UNI & FRONIUS IGPLUS 3.0-1 UNI | 2014-04-07 | 2014-04-11 | 4 | 2014-04-11 | [14 empty] | 2014-10-06 | 2014-10-13 |  | Y
Central Hudson |  | SolarCity | CH-05203 | Poughkeepsie | Pleasant Valley | Dutchess | 12569 | G | 7024 | Tinkertown | N |  | 12 | [13 empty] | NM | N | SOLAREDGE SE6000A-US (2) | 2014-04-07 | 2014-04-11 | 4 | 2014-04-11 | [14 empty] | 2014-06-19 | 2014-06-26 |  | Y
Central Hudson |  | SolarCity | CH-05438 | Newburgh | Montgomery | Orange | 12549 | G | 5072 | Montgomery | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A-US | 2014-04-07 | 2014-04-11 | 4 | 2014-04-11 | [14 empty] | 2014-05-16 | 2014-05-19 |  | Y
Central Hudson |  | SolarCity | CH-07490 | Catskill | Westerlo | Albany | 12193 | G | 1091 | Westerlo | N |  | 6 | [13 empty] | NM | N | SolarEdge SE6000A-US | 2014-04-07 | 2014-04-11 | 4 | 2014-04-11 | [14 empty] | 2014-05-20 | 2014-05-28 |  | Y
Central Hudson |  | Solar Generation | CH-08281 | Newburgh | Wallkill | Ulster | 12589 | G | 5033 | Galeville | N | CH-08281 | 12 | [13 empty] | NM | N | SMA SB4000TL-US (3) | 2014-04-07 | 2014-04-11 | 4 | 2014-04-11 | [8 empty] | 350 | 350 |  | 2016-02-04 | 2016-02-04 | 2016-02-11 | 2014-05-19 | 2014-05-22 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03788 | Newburgh | New Paltz | Ulster | 12561 | G | 5011 | Modena | N |  | 6 | [13 empty] | NM | N | POWER ONE AURORA PVI-6000 | 2014-04-08 | 2014-04-15 | 5 | 2014-04-15 | [14 empty] | 2014-07-22 | 2014-07-28 |  | Y
Central Hudson |  | NRG Home Solar | CH-04133 | Newburgh | Newburgh | Orange | 12550 | G | 5041 | East Walden | N |  | 6.88 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (32) | 2014-04-08 | 2014-04-15 | 5 | 2014-04-15 | [14 empty] | 2014-06-05 | 2014-06-12 |  | Y
Central Hudson |  | NRG Home Solar | CH-04234 | Catskill | Catskill | Greene | 12414 | G | 2042 | South Cairo | N |  | 5.59 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (26) | 2014-04-08 | 2014-04-11 | 3 | 2014-04-11 | [14 empty] | 2014-06-02 | 2014-06-09 |  | Y
Central Hudson |  | NRG Home Solar | CH-04284 | Kingston | Wawarsing | Ulster | 12489 | G | 3071 | Honk Falls | N |  | 4.945 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (23) | 2014-04-16 | 2014-04-16 | 0 | 2014-04-16 | [14 empty] | 2014-06-06 | 2014-06-13 |  | Y
Central Hudson |  | NRG Home Solar | CH-04616 | Fishkill | Fishkill | Dutchess | 12524 | G | 8012 | Forgebrook | N |  | 7.31 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (34) | 2014-04-08 | 2014-04-15 | 5 | 2014-04-15 | [14 empty] | 2014-06-09 | 2014-06-16 |  | Y
Central Hudson |  | NRG Home Solar | CH-04840 | Newburgh | Wallkill |  | 12589 | G | 5043 | East Walden | TBD |  | 6.88 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (32) | 2014-04-08 | 2014-04-11 | 3 | 2014-04-11 | [17 empty] | W |  | Customer already had net meter prior to application. 10/29/14 - As per customer, this project is abandoned, they will be moving forward with a different contractor.
Central Hudson |  | Murphy Solar Power | CH-02712 | Catskill | Athens | Greene | 12015 | G | 2002 | North Catskill | N |  | 5 | [13 empty] | NM | N | SMA 5000US | 2014-04-15 | 2014-04-16 | 1 | 2014-04-16 | [14 empty] | 2014-05-06 | 2014-05-13 |  | Y
Central Hudson |  | SolarCity | CH-06236 | Newburgh | Newburgh | Orange | 12550 | G | 4014 | West Balmville | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A-US | 2014-04-08 | 2014-04-15 | 5 | 2014-04-15 | [14 empty] | 2014-05-05 | 2014-05-12 |  | Y
Central Hudson |  | NRG Home Solar | CH-04440 | Newburgh | New Paltz | Ulster | 12561 | G | 5024 | Ohioville | N |  | 6.02 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (28) | 2014-04-09 | 2014-04-16 | 5 | 2014-04-16 | [14 empty] | 2014-06-11 | 2014-06-18 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00970 | Newburgh | Wallkill | Ulster | 12589 | G | 5043 | East Walden | N |  | 4.3 | [13 empty] | NM | N | ENPHASE ENERGY M215 (20) | 2014-04-09 | 2014-04-16 | 5 | 2014-04-16 | [14 empty] | 2014-07-18 | 2014-07-24 |  | Y
Central Hudson |  | SolarCity | CH-06117 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8071 | Shenandoah | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A-US | 2014-04-09 | 2014-04-16 | 5 | 2014-04-16 | [14 empty] | 2014-05-02 | 2014-05-08 |  | Y
Central Hudson |  | Self | CH-08861 | Kingston | Saugerties | Ulster | 12477 | G | 3002 | Saugerties | N |  | 17.2 | [13 empty] | NM | N | Enphase M215 (80) | 2014-05-05 | 2014-05-05 | 0 | 2014-05-05 | [14 empty] | 2014-10-24 | 2014-11-05 |  | Y
Central Hudson |  | SolarCity | CH-06335 | Newburgh | Milton | Ulster | 12547 | G | 5002 | Marlboro | N |  | 10 | [13 empty] | NM | N | SOLAREDGE SE5000A-US (2) | 2014-04-10 | 2014-04-17 | 5 | 2014-04-17 | [14 empty] | 2014-07-08 | 2014-07-15 |  | Y
Central Hudson |  | SolarCity | CH-07203 | Kingston | Rifton | Ulster | 12471 | G | 3041 | Sturgeon Pool | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A-US | 2014-04-10 | 2014-04-17 | 5 | 2014-04-17 | [14 empty] | 2014-05-28 | 2014-06-03 |  | Y
Central Hudson |  | Solar Generation | CH-08173 | Kingston | Glenford | Ulster | 12433 | G | 3013 | Woodstock | N | CH-23354 | 6 | [13 empty] | NM | N | PowerOne PVI 6000 | 2014-04-10 | 2014-04-17 | 5 | 2014-04-17 | [14 empty] | 2014-05-23 | 2014-06-02 |  | Y
Central Hudson |  | SolarCity | CH-06528 | Kingston | Kingston | Ulster | 12401 | G | 1022 | East Kingston | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A-US | 2014-04-11 | 2014-04-21 | 5 | 2014-04-21 | [14 empty] | 2014-05-20 | 2014-05-28 |  | Y
Central Hudson |  | SolarCity | CH-05100 | Poughkeepsie | Ancramdale | Columbia | 12503 | G | 7085 | Ancram | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A-US | 2014-04-14 | 2014-04-22 | 5 | 2014-04-22 | [14 empty] | 2014-07-30 | 2014-08-06 |  | Y
Central Hudson |  | SolarCity | CH-06557 | Kingston | Cragsmoor | Ulster | 12420 | G | 3078 | Greenfield Rd | N |  | 3.8 | [13 empty] | NM | N | SOLAREDGE SE3800A-US | 2014-04-17 | 2014-04-23 | 3 | 2014-04-23 | [14 empty] | 2014-07-17 | 2014-07-17 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03654 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6046 | Spackenkill | N |  | 10 | [13 empty] | NM | N | POWER ONE AURORA PVI5000-OUTD-S-US (2) | 2014-04-21 | 2014-04-24 | 3 | 2014-04-24 | [14 empty] | 2014-09-03 | 2014-09-10 |  | Y
Central Hudson |  | NRG Home Solar | CH-04105 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8096 | Fishkill Plains | N |  | 4.73 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (22) | 2014-04-21 | 2014-04-24 | 3 | 2014-04-24 | [14 empty] | 2014-07-11 | 2014-07-18 |  | Y
Central Hudson |  | SolarCity | CH-05481 | Catskill | Catskill | Greene | 12414 | G | 2004 | North Catskill | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A-US | 2014-04-21 | 2014-04-25 | 4 | 2014-04-25 | [14 empty] | 2014-06-03 | 2014-06-10 |  | Y
Central Hudson |  | SolarCity | CH-05628 | Kingston | New Paltz | Ulster | 12561 | G | 3021 | High Falls | N |  | 8.8 | [13 empty] | NM | N | SOLAREDGE SE3800A-US & SOLAREDGE SE5000A-US | 2014-04-21 | 2014-04-28 | 5 | 2014-04-28 | [14 empty] | 2014-07-24 | 2014-07-31 |  | Y
Central Hudson |  | SolarCity | CH-05647 | Kingston | Hurley | Ulster | 12443 | G | 2094 | Hurley Ave | N | CH-05647 | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A-US | 2014-04-21 | 2014-04-24 | 3 | 2014-04-24 | [14 empty] | 2014-06-13 | 2014-06-20 |  | Y
Central Hudson |  | SolarCity | CH-05721 | Kingston | Saugerties | Ulster | 12477 | G | 3002 | Saugerties | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A-US | 2014-04-21 | 2014-04-24 | 3 | 2014-04-24 | [14 empty] | 2014-06-09 | 2014-06-16 |  | Y
Central Hudson |  | SolarCity | CH-05816 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6062 | Inwood Ave | N |  | 8.8 | [13 empty] | NM | N | SOLAREDGE SE3800A-US & SOLAREDGE SE5000A-US | 2014-04-21 | 2014-04-24 | 3 | 2014-04-24 | [14 empty] | 2014-07-25 | 2014-08-01 |  | Y
Central Hudson |  | SolarCity | CH-05916 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 6092 | Manchester | N |  | 8.8 | [13 empty] | NM | N | SOLAREDGE SE3800A-US & SOLAREDGE SE5000A-US | 2014-04-21 | 2014-04-24 | 3 | 2014-04-24 | [14 empty] | 2014-06-23 | 2014-06-30 |  | Y
Central Hudson |  | SolarCity | CH-05972 | Poughkeepsie | Millerton | Dutchess | 12546 | G | 7095 | Smithfield | N |  | 12 | [13 empty] | NM | N | SOLAREDGE SE6000A-US (2) | 2014-04-21 | 2014-04-24 | 3 | 2014-04-24 | [14 empty] | 2014-10-15 | 2014-10-22 |  | Y
Central Hudson |  | SolarCity | CH-05982 | Newburgh | Highland | Ulster | 12528 | G | 5084 | Highland | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A-US | 2014-04-21 | 2014-04-24 | 3 | 2014-04-24 | [14 empty] | 2014-10-27 | 2014-11-03 |  | Y
Central Hudson |  | SolarCity | CH-06089 | Fishkill | Fishkill | Dutchess | 12524 | G | 8094 | Fishkill Plains | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A-US | 2014-04-21 | 2014-04-24 | 3 | 2014-04-24 | [14 empty] | 2014-09-18 | 2014-09-24 |  | Y
Central Hudson |  | SolarCity | CH-06692 | Poughkeepsie | Salt Pt | Dutchess | 12578 | G | 7011 | Hibernia | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A-US | 2014-04-21 | 2014-04-24 | 3 | 2014-04-24 | [14 empty] | 2014-07-14 | 2014-07-21 |  | Y
Central Hudson |  | SolarCity | CH-06997 | Newburgh | Newburgh | Orange | 12550 | G | 4023 | Coldenham | N |  | 3.8 | [13 empty] | NM | N | SOLAREDGE SE3800A-US | 2014-04-21 | 2014-04-28 | 5 | 2014-04-28 | [14 empty] | 2014-07-28 | 2014-08-04 |  | Y
Central Hudson |  | SolarCity | CH-07228 | Kingston | Ellenvl | Ulster | 12428 | G | 3078 | Greenfield Rd | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A-US | 2014-04-21 | 2014-04-28 | 5 | 2014-04-28 | [14 empty] | 2014-06-12 | 2014-06-19 |  | W
Central Hudson |  | SolarCity | CH-07559 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8091 | Fishkill Plains | N |  | 3.8 | [13 empty] | NM | N | SOLAREDGE SE3800A-US | 2014-04-21 | 2014-04-24 | 3 | 2014-04-24 | [14 empty] | 2014-06-17 | 2014-06-24 |  | Y
Central Hudson |  | Solar Generation | CH-08146 | Kingston | Stone Ridge | Ulster | 12484 | G | 3024 | High Falls | N |  | 6 | [13 empty] | NM | N | SMA SB 3000TL (2) | 2014-04-28 | 2014-04-29 | 1 | 2014-04-29 | [14 empty] | 2014-07-16 | 2014-07-16 |  | Y
Central Hudson |  | Solar Generation | CH-08213 | Kingston | Ulster Pk | Ulster | 12487 | G | 3041 | Sturgeon Pool | N |  | 7.6 | [13 empty] | NM | N | SMA SB 3800-TL | 2014-04-28 | 2014-05-02 | 4 | 2014-05-02 | [14 empty] | 2014-06-19 | 2014-06-26 |  | Y
Central Hudson |  | New York State Solar Farm | CH-03934 | Newburgh | Wallkill | Ulster | 12589 | G | 4011 | West Balmville | N |  | 5 | [13 empty] | NM | N | POWERONE PVI 5000 | 2014-04-22 | 2014-04-28 | 4 | 2014-04-28 | [14 empty] | 2014-08-04 | 2014-08-08 |  | Y
Central Hudson |  | NRG Home Solar | CH-04396 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8092 | Fishkill Plains | N |  | 3.44 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (16) | 2014-04-22 | 2014-04-28 | 4 | 2014-04-28 | [14 empty] | 2014-07-17 | 2014-07-23 |  | Y
Central Hudson |  | NRG Home Solar | CH-04587 | Fishkill | Wappingrs Falls |  | 12590 | G | 8044 | Myers Corners | TBD |  | 3.655 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (17) | 2014-04-22 | 2014-04-28 | 4 | 2014-04-28 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | NRG Home Solar | CH-04664 | Newburgh | Wallkill | Ulster | 12589 | G | 5043 | East Walden | N |  | 5.16 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (24) | 2014-04-22 | 2014-04-28 | 4 | 2014-04-28 | [14 empty] | 2014-08-13 | 2014-08-15 |  | Y
Central Hudson |  | SolarCity | CH-05272 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8095 | Fishkill Plains | N |  | 9.8 | [13 empty] | NM | N | SOLAREDGE SE3800A-US & SOLAREDGE SE6000A-US | 2014-04-22 | 2014-04-29 | 5 | 2014-04-29 | [14 empty] | 2014-06-09 | 2014-06-16 |  | Y
Central Hudson |  | SolarCity | CH-06759 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7056 | Rhinebeck | N |  | 12 | [13 empty] | NM | N | SOLAREDGE SE6000A-US (2) | 2014-04-22 | 2014-04-28 | 4 | 2014-04-28 | [14 empty] | 2014-06-11 | 2014-06-18 |  | Y
Central Hudson |  | New York State Solar Farm | CH-03966 | Kingston | Stone Ridge | Ulster | 12484 | G | 3023 | High Falls | N |  | 6 | [13 empty] | NM | N | POWERONE PVI 6000 | 2014-04-23 | 2014-04-30 | 5 | 2014-04-30 | [14 empty] | 2014-07-18 | 2014-07-18 |  | Y
Central Hudson |  | NRG Home Solar | CH-04171 | Fishkill | Hopewell Junction | Dutchess | 12533 | G | 8093 | Fishkill Plains | N |  | 10.535 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (49) | 2014-04-23 | 2014-04-30 | 5 | 2014-04-30 | [8 empty] | 350 | 350 |  |  |  |  | 2014-07-09 | 2014-07-16 |  | Y
Central Hudson |  | SolarCity | CH-05026 | Poughkeepsie | Clinton Corners | Dutchess | 12514 | G | 7071 | Stanfordville | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE3800A-US (2) | 2014-04-23 | 2014-04-29 | 4 | 2014-04-29 | [14 empty] | 2014-06-12 | 2014-06-19 |  | Y
Central Hudson |  | SolarCity | CH-06591 | Kingston | Saugerties | Ulster | 12477 | G | 2015 | Lincoln Park | N |  | 10 | [13 empty] | NM | N | SOLAREDGE SE5000A-US (2) | 2014-04-23 | 2014-04-30 | 5 | 2014-04-30 | [14 empty] | 2014-06-30 | 2014-06-30 |  | Y
Central Hudson |  | SolarCity | CH-06774 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7062 | Milan | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A-US | 2014-04-23 | 2014-04-29 | 4 | 2014-04-29 | [14 empty] | 2014-07-22 | 2014-07-28 |  | Y
Central Hudson |  | Sol Providers | CH-08959 | Poughkeepsie | Clinton Corners | Dutchess | 12514 | G | 7013 | Hibernia | N |  | 8 | [13 empty] | NM | N | SMA SB 4000W (2) | 2014-04-23 | 2014-04-29 | 4 | 2014-04-29 | [14 empty] | 2014-06-24 | 2014-07-01 |  | Y
Central Hudson |  | Sungevity Inc | CH-09344 | Fishkill | Wappingers Falls | Dutchess | 12590 | G | 8023 | Knapps Corners | N |  | 7 | [13 empty] | NM | N | SMA AMERICA SB7000US-12 | 2014-04-23 | 2014-04-29 | 4 | 2014-04-29 | [14 empty] | 2014-07-08 | 2014-07-15 |  | Y
Central Hudson |  | NRG Home Solar | CH-04613 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8056 | North Chelsea | N |  | 6.665 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (31) | 2014-04-24 | 2014-04-30 | 4 | 2014-04-30 | [14 empty] | 2014-06-17 | 2014-06-24 |  | Y
Central Hudson |  | SolarCity | CH-05627 | Kingston | New Paltz | Ulster | 12561 | G | 3021 | High Falls | N |  | 10 | [13 empty] | NM | N | SOLAREDGE SE5000 (2) | 2014-04-24 | 2014-04-30 | 4 | 2014-04-30 | [14 empty] | 2014-07-17 | 2014-07-17 |  | Y
Central Hudson |  | SolarCity | CH-05936 | Poughkeepsie | Hyde Park | Dutchess | 12538 | G | 7024 | Tinkertown | N |  | 8.8 | [13 empty] | NM | N | SOLAREDGE SE3800A-US & SOLAREDGE SE5000A-US | 2014-04-24 | 2014-04-30 | 4 | 2014-04-30 | [14 empty] | 2014-10-15 | 2014-10-16 |  | Y
Central Hudson |  | Lotus Energy Inc. | CH-03872 | Catskill | Coeymans Hollow | Albany | 12046 | G | 1081 | New Baltimore | N |  | 7.6 | [13 empty] | NM | N | SMA SB3800 (2) | 2014-04-25 | 2014-05-01 | 4 | 2014-05-01 | [14 empty] | 2014-07-08 | 2014-07-08 |  | Y
Central Hudson |  | SolarCity | CH-05119 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8091 | Fishkill Plains | N |  | 12 | [13 empty] | NM | N | SOLAREDGE SE6000A-US (2) | 2014-04-25 | 2014-05-01 | 4 | 2014-05-01 | [14 empty] | 2014-11-03 | 2014-11-07 |  | Y
Central Hudson |  | SolarCity | CH-05815 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6003 | Reynolds Hill | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE3800A-US (2) | 2014-04-25 | 2014-05-01 | 4 | 2014-05-01 | [14 empty] | 2014-07-24 | 2014-07-31 |  | Y
Central Hudson |  | SolarCity | CH-06881 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8045 | Myers Corners | N |  | 11 | [13 empty] | NM | N | SOLAREDGE SE5000A-US & SOLAREDGE SE6000A-US | 2014-04-25 | 2014-04-30 | 3 | 2014-04-30 | [14 empty] | 2014-06-26 | 2014-07-03 |  | Y
Central Hudson |  | SolarCity | CH-07199 | Kingston | Olive Brdg | Ulster | 12461 | G | 3024 | High Falls | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A-US | 2014-04-25 | 2014-05-01 | 4 | 2014-05-01 | [14 empty] | 2014-07-22 | 2014-07-29 |  | Y
Central Hudson |  | Sungevity Inc | CH-09283 | Kingston | Accord |  | 12404 | G | 3024 | High Falls | TBD |  | 6 | [13 empty] | NM | N | POWER-ONE PVI-6000 | 2014-04-25 | 2014-04-30 | 3 | 2014-04-30 | [17 empty] | W
Central Hudson |  | Sungevity Inc | CH-09298 | Kingston | Kerhonkson | Ulster | 12446 | G | 3081 | Kerhonkson | N |  | 8 | [13 empty] | NM | N | SMA AMERICA SB4000TL-US-22 (2) | 2014-04-25 | 2014-04-30 | 3 | 2014-04-30 | [14 empty] | 2014-07-24 | 2014-07-31 |  | Y
Central Hudson |  | Sungevity Inc | CH-09319 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 7041 | Staatsburg | N |  | 6 | [13 empty] | NM | N | POWER-ONE PVI-6000 | 2014-05-01 | 2014-05-01 | 0 | 2014-05-01 | [14 empty] | 2014-05-28 | 2014-06-03 |  | Y
Central Hudson |  | Sungevity Inc | CH-09422 | Poughkeepsie | Poughkeepsie |  | 12603 | G | 6043 | Spackenkill | TBD |  | 6 | [13 empty] | NM | N | POWER-ONE PVI-6000 | 2014-05-08 | 2014-05-14 | 4 | 2014-05-14 | [17 empty] | W
Central Hudson |  | Infinity Solar Systems | CH-03461 | Newburgh | Newburgh | Orange | 12550 | G | 4013 | West Balmville | N |  | 6 | [13 empty] | NM | N | POWERONE PVI-6000 | 2014-05-05 | 2014-05-12 | 5 | 2014-05-12 | [14 empty] | 2014-07-09 | 2014-07-16 |  | Y
Central Hudson |  | Baxstar Solar LLC | CH-00753 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 6074 | East Park | N |  | 6.9 | [13 empty] | NM | N | POWERONE MICRO-0.3-I (23) | 2014-06-10 | 2014-06-17 | 5 | 2014-06-17 | [14 empty] | 2014-07-09 | 2014-07-18 |  | Y
Central Hudson |  | NRG Home Solar | CH-04330 | Poughkeepsie | Clinton Corners | Dutchess | 12514 | G | 7013 | Hibernia | N |  | 5.16 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (24) | 2014-05-16 | 2014-05-23 | 5 | 2014-05-23 | [14 empty] | 2014-06-10 | 2014-06-17 |  | Y
Central Hudson |  | NRG Home Solar | CH-04818 | Poughkeepsie | Red Hook |  | 12571 | G | 7051 | Rhinebeck | TBD |  | 7.955 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (37) | 2014-04-29 | 2014-05-05 | 4 | 2014-05-05 | [17 empty] | W
Central Hudson |  | SolarCity | CH-04989 | Kingston | Stone Ridge |  | 12484 | G | 3024 | High Falls | TBD |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A-US | 2014-04-29 | 2014-05-05 | 4 | 2014-05-05 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | SolarCity | CH-05249 | Kingston | Saugerties | Ulster | 12477 | G | 3001 | Saugerties | N |  | 3.8 | [13 empty] | NM | N | SOLAREDGE SE3800A-US | 2014-04-29 | 2014-05-06 | 5 | 2014-05-06 | [14 empty] | 2014-06-11 | 2014-06-18 |  | Y
Central Hudson |  | SolarCity | CH-05543 | Catskill | Catskill | Greene | 12414 | G | 2006 | North Catskill | N |  | 3 | [13 empty] | NM | N | SOLAREDGE SE3000A-US | 2014-04-29 | 2014-05-05 | 4 | 2014-05-05 | [14 empty] | 2014-08-11 | 2014-08-18 |  | Y
Central Hudson |  | SolarCity | CH-06002 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8091 | Fishkill Plains | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A-US | 2014-04-29 | 2014-05-05 | 4 | 2014-05-05 | [14 empty] | 2014-06-26 | 2014-07-03 |  | Y
Central Hudson |  | Solar Generation | CH-08192 | Kingston | Woodstock | Ulster | 12498 | G | 3014 | Woodstock | N |  | 7 | [13 empty] | NM | N | SunPower SPR 7000 | 2014-08-22 | 2014-08-29 | 5 | 2014-08-29 | [14 empty] | 2015-03-10 | 2015-03-17 |  | Y
Central Hudson |  | NRG Home Solar | CH-04498 | Newburgh | Cornwall-Hdsn | Orange | 12520 | G | 4043 | Union Ave | N |  | 7.31 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (34) | 2014-04-30 | 2014-05-07 | 5 | 2014-05-07 | [14 empty] | 2014-06-11 | 2014-06-18 |  | Y
Central Hudson |  | Hudson Valley Wind Energy, LLC | CH-02545 | Newburgh | Marlboro | Ulster | 12542 | G | 5003 | Marlboro | N |  |  |  | 10 | [11 empty] | NM | N | DT POWERSYNCH II AMFA-27 | 2014-05-01 | 2014-05-07 | 4 | 2014-05-07 | [8 empty] | 350 | 350 |  |  |  |  | 2014-05-20 | 2014-05-23 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Sungevity Inc | CH-09250 | Newburgh | Montgomery | Orange | 12549 | G | 5072 | Montgomery | N |  | 6 | [13 empty] | NM | N | POWER ONE PVI 6000 | 2014-05-01 | 2014-05-07 | 4 | 2014-05-07 | [14 empty] | 2014-06-02 | 2014-06-09 |  | Y
Central Hudson |  | Sungevity Inc | CH-09326 | Poughkeepsie | Clinton Corners | Dutchess | 12514 | G | 7013 | Hibernia | N | CH-09326 | 6 | [13 empty] | NM | N | POWER ONE PVI 6000 | 2014-05-01 | 2014-05-07 | 4 | 2014-05-07 | [14 empty] | 2014-07-25 | 2014-08-01 |  | Y
Central Hudson |  | Sungevity Inc | CH-09437 | Newburgh | Highland | Ulster | 12528 | G | 5024 | Ohioville | N |  | 8 | [13 empty] | NM | N | POWER ONE PVI 4.2 & POWER ONE PVI 3.8 | 2014-07-08 | 2014-07-15 | 5 | 2014-07-15 | [14 empty] | 2014-08-22 | 2014-08-29 |  | Y
Central Hudson |  | Sungevity Inc | CH-09498 | Newburgh | Wallkill | Ulster | 12589 | G | 5013 | Modena | N |  | 5 | [13 empty] | NM | N | SMA SB5000 | 2014-05-01 | 2014-05-07 | 4 | 2014-05-07 | [14 empty] | 2014-06-19 | 2014-06-26 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03693 | Newburgh | New Paltz | Ulster | 12561 | G | 5024 | Ohioville | N |  | 8.4 | [13 empty] | NM | N | POWER-ONE AURORA PVI4.2-OUTD-US (2) | 2014-05-02 | 2014-05-08 | 4 | 2014-05-08 | [14 empty] | 2014-08-04 | 2014-08-08 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03742 | Newburgh | Highland | Ulster | 12528 | G | 5022 | Ohioville | N |  | 4.2 | [13 empty] | NM | N | POWER-ONE AURORA PVI4.2-OUTD-US | 2014-05-02 | 2014-05-08 | 4 | 2014-05-08 | [14 empty] | 2014-08-04 | 2014-08-08 |  | Y
Central Hudson |  | NRG Home Solar | CH-04728 | Fishkill | Fishkill | Dutchess | 12524 | G | 8013 | Forgebrook | N |  | 7.31 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (34) | 2014-05-02 | 2014-05-08 | 4 | 2014-05-08 | [14 empty] | 2014-08-01 | 2014-08-08 |  | Y
Central Hudson |  | SolarCity | CH-05267 | Newburgh | Highland | Ulster | 12528 | G | 5082 | Highland | N |  | 15 | [13 empty] | NM | N | SOLAREDGE SE6000A-US (2) & SOLAREDGE SE3000A-US | 2014-05-02 | 2014-05-08 | 4 | 2014-05-08 | [14 empty] | 2014-07-01 | 2014-07-01 |  | Y
Central Hudson |  | SolarCity | CH-05615 | Kingston | Accord | Ulster | 12404 | G | 3081 | Kerhonkson | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A-US | 2014-05-02 | 2014-05-08 | 4 | 2014-05-08 | [14 empty] | 2014-06-11 | 2014-06-18 |  | Y
Central Hudson |  | SolarCity | CH-06035 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8052 | North Chelsea | N |  | 3.8 | [13 empty] | NM | N | SOLAREDGE SE3800A-US | 2014-05-02 | 2014-05-08 | 4 | 2014-05-08 | [14 empty] | 2014-08-19 | 2014-08-21 |  | Y
Central Hudson |  | SolarCity | CH-06123 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8093 | Fishkill Plains | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A-US | 2014-05-02 | 2014-05-08 | 4 | 2014-05-08 | [14 empty] | 2014-07-03 | 2014-07-11 |  | Y
Central Hudson |  | SolarCity | CH-06885 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8014 | Forgebrook | N |  | 8 | [13 empty] | NM | N | SOLAREDGE SE5000 & SOLAREDGE SE3000 | 2014-05-02 | 2014-05-08 | 4 | 2014-05-08 | [14 empty] | 2014-07-30 | 2014-08-06 |  | Y
Central Hudson |  | SolarCity | CH-07489 | Catskill | Greenvl | Greene | 12083 | G | 2061 | Freehold | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A-US | 2014-05-02 | 2014-05-08 | 4 | 2014-05-08 | [14 empty] | 2014-07-28 | 2014-08-04 |  | Y
Central Hudson |  | Solar Generation | CH-08165 | Kingston | Glenford | Ulster | 12433 | G | 3013 | Woodstock | N |  | 4 | [13 empty] | NM | N | SMA SB-TL 4000 | 2014-05-02 | 2014-05-08 | 4 | 2014-05-08 | [14 empty] | 2014-06-06 | 2014-06-13 |  | Y
Central Hudson |  | NRG Home Solar | CH-04584 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8094 | Fishkill Plains | N |  | 5.16 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (24) | 2014-05-12 | 2014-05-12 | 0 | 2014-05-12 | [14 empty] | 2014-07-03 | 2014-07-11 |  | Y
Central Hudson |  | OnForce Solar | CH-02813 | Fishkill | Cold Spg |  | 10516 | G | 8063 | Merritt Park | TBD |  | 28 | [13 empty] | NM | N | SMA SB11000TL-US (2) & SMA SB6000TL-US (1) | 2014-07-16 | 2014-07-23 | 5 | 2014-07-23 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | SolarCity | CH-05307 | Newburgh | Wallkill | Ulster | 12589 | G | 5043 | East Walden | N |  | 8 | [13 empty] | NM | N | SOLAREDGE SE3000A-US & SOLAREDGE SE5000A-US | 2014-05-05 | 2014-05-12 | 5 | 2014-05-12 | [14 empty] | 2014-09-09 | 2014-09-15 |  | Y
Central Hudson |  | SolarCity | CH-06371 | Newburgh | Wallkill | Ulster | 12589 | G | 5042 | East Walden | N |  | 8 | [13 empty] | NM | N | SOLAREDGE SE3000A-US & SOLAREDGE SE5000A-US | 2014-06-17 | 2014-06-24 | 5 | 2014-06-24 | [14 empty] | 2014-08-25 | 2014-09-02 |  | Y
Central Hudson |  | SolarCity | CH-06578 | Kingston | Saugerties | Ulster | 12477 | G | 3001 | Saugerties | N |  | 3 | [13 empty] | NM | N | POWERONE PVI-3.0-OUTD | 2014-05-05 | 2014-05-12 | 5 | 2014-05-12 | [14 empty] | 2014-06-30 | 2014-06-30 |  | Y
Central Hudson |  | SolarCity | CH-07845 | Catskill | Greenvl |  | 12083 | G | 1091 | Westerlo | TBD |  | 20 | [13 empty] | NM | N | FRONIUS IG PLUS A 10.0-1 UNI (2) | 2014-05-05 | 2014-05-12 | 5 | 2014-05-12 | [17 empty] | W
Central Hudson |  | Lighthouse Solar | CH-03708 | Newburgh | New Windsor | Orange | 12553 | G | 4047 | Union Ave | N |  | 30 | [13 empty] | NM | N | POWER-ONE AURORA PVI10.0-I-OUTD-US (3) | 2014-05-16 | 2014-05-27 | 6 | 2014-05-27 | [14 empty] | 2014-08-22 | 2014-08-28 |  | Y
Central Hudson |  | New York State Solar Farm | CH-03952 | Newburgh | Wallkill | Ulster | 12589 | G | 5033 | Galeville | N |  | 11 | [13 empty] | NM | N | SMA AMERICA SB 7.0 & SMA AMERICA SB 4.0 | 2014-05-14 | 2014-05-20 | 4 | 2014-05-20 | [14 empty] | 2014-07-18 | 2014-07-24 |  | Y
Central Hudson |  | SolarCity | CH-07468 | Newburgh | Newburgh | Orange | 12550 | G | 4093 | Bethlehem Rd | N |  | 8.8 | [13 empty] | NM | N | SOLAREDGE SE5000A-US & SOLAREDGE SE3800A-US | 2014-05-06 | 2014-05-13 | 5 | 2014-05-13 | [14 empty] | 2014-06-05 | 2014-06-12 |  | Y
Central Hudson |  | Sea Bright Solar LLC | CH-08856 | Poughkeepsie | Clinton Corners | Dutchess | 12514 | G | 7013 | Hibernia | N |  | 5 | [13 empty] | NM | N | SMA 5000 | 2014-05-21 | 2014-05-29 | 5 | 2014-05-29 | [14 empty] | 2014-08-28 | 2014-09-05 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-03398 | Newburgh | Campbell Hall | Orange | 10916 | G | 5052 | Maybrook | N |  | 16 | [13 empty] | NM | N | SMA America SB8000US (2) | 2014-05-14 | 2014-05-14 | 0 | 2014-05-14 | [8 empty] | 350 | 350 |  |  |  |  | 2014-07-21 | 2014-07-28 |  | Y
Central Hudson |  | SunDog Solar | CH-09149 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7091 | Pulvers Corners | N |  | 10 | [13 empty] | NM | N | SMA SB3000-TL (2) & SMA SB4000-TL | 2014-05-07 | 2014-05-16 | 7 | 2014-05-16 | [14 empty] | 2014-05-16 | 2014-05-16 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Sungevity Inc | CH-09221 | Newburgh | Gardiner | Ulster | 12525 | G | 5031 | Galeville | N |  | 6 | [13 empty] | NM | N | POWER ONE PVI 6000 | 2014-05-07 | 2014-05-14 | 5 | 2014-05-14 | [14 empty] | 2014-07-31 | 2014-08-07 |  | Y
Central Hudson |  | Sungevity Inc | CH-09416 | Kingston | Saugerties | Ulster | 12477 | G | 3002 | Saugerties | N |  | 12 | [13 empty] | NM | N | POWER ONE PVI 6000 (2) | 2014-05-07 | 2014-05-21 | 10 | 2014-05-21 | [14 empty] | 2014-07-02 | 2014-07-02 |  | Y
Central Hudson |  | Sungevity Inc | CH-09528 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6046 | Spackenkill | N |  | 7.2 | [13 empty] | NM | N | PowerOne PVI 4.2 & PowerOne PVI 3.0 | 2014-05-07 | 2014-05-14 | 5 | 2014-05-14 | [14 empty] | 2014-07-24 | 2014-07-31 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-03375 | Fishkill | Fishkill | Dutchess | 12524 | G | 8011 | Forgebrook | N |  | 10 | [13 empty] | NM | N | FRONIUS IG PLUS A 10.0 | 2014-05-15 | 2014-05-22 | 5 | 2014-05-22 | [14 empty] | 2014-07-21 | 2014-07-25 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-03388 | Fishkill | Fishkill | Dutchess | 12524 | G | 8013 | Forgebrook | N |  | 5 | [13 empty] | NM | N | PVI-5000-240 | 2014-05-08 | 2014-05-15 | 5 | 2014-05-15 | [14 empty] | 2014-07-25 | 2014-08-01 |  | Y
Central Hudson |  | New York State Solar Farm | CH-04030 | Poughkeepsie | Pine Plns | Dutchess | 12567 | G | 7091 | Pulvers Corners | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE 7600A | 2014-05-08 | 2014-05-15 | 5 | 2014-05-15 | [14 empty] | 2014-07-31 | 2014-08-07 |  | Y
Central Hudson |  | NRG Home Solar | CH-04643 | Newburgh | New Windsor | Orange | 12553 | G | 4044 | Union Ave | N |  | 3.655 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (17) | 2014-05-08 | 2014-05-15 | 5 | 2014-05-15 | [14 empty] | 2014-06-09 | 2014-06-16 |  | Y
Central Hudson |  | NRG Home Solar | CH-04760 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6091 | Manchester | N |  | 5.375 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (25) | 2014-05-08 | 2014-05-15 | 5 | 2014-05-15 | [14 empty] | 2014-08-26 | 2014-09-03 |  | Y
Central Hudson |  | SolarCity | CH-07279 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6061 | Inwood Ave | N |  | 10 | [13 empty] | NM | N | SOLAREDGE SE5000A-US (2) | 2014-05-08 | 2014-05-15 | 5 | 2014-05-15 | [14 empty] | 2014-06-11 | 2014-06-18 |  | Y
Central Hudson |  | Sungevity Inc | CH-09317 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7041 | Staatsburg | N | CH-09317 | 16 | [13 empty] | NM | N | POWER ONE PVI 6.0, POWER ONE PVI 5.0, & POWER ONE PVI 3.8 | 2014-06-06 | 2014-06-13 | 5 | 2014-06-13 | [8 empty] | 350 | 350 |  |  |  |  | 2014-07-21 | 2014-07-25 |  | Y
Central Hudson |  | Sungevity Inc | CH-09434 | Poughkeepsie | Ancramdale |  | 12503 | G | 7092 | Pulvers Corners | TBD |  | 7.6 | [13 empty] | NM | N | POWER ONE PVI 3800 (2) | 2014-05-08 | 2014-05-22 | 10 | 2014-05-22 | [17 empty] | W |  | Customer already had net meter prior to application. 10/1/14 As per customer, this project has been abandoned.
Central Hudson |  | NRG Home Solar | CH-04121 | Poughkeepsie | Lagrangevl | Dutchess | 12540 | G | 6057 | Todd Hill | N |  | 12.255 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (57) | 2014-05-09 | 2014-05-16 | 5 | 2014-05-16 | [14 empty] | 2014-07-08 | 2014-07-15 |  | Y
Central Hudson |  | Atlantean Solar LLC | CH-00738 | Newburgh | Newburgh | Orange | 12550 | G | 4022 | Coldenham | N |  | 46.5 | [13 empty] | NM | N | Enphase M250 (186) | 2014-05-30 | 2014-06-06 | 5 | 2014-06-06 | [14 empty] | 2014-10-22 | 2014-10-27 |  | Y
Central Hudson |  | Atlantean Solar LLC | CH-00739 | Newburgh | Newburgh | Orange | 12550 | G | 4022 | Coldenham | N |  | 38.25 | [13 empty] | NM | N | Enphase M250 (153) | 2014-06-02 | 2014-06-06 | 4 | 2014-06-06 | [14 empty] | 2014-10-22 | 2014-10-27 |  | Y
Central Hudson |  | Atlantean Solar LLC | CH-00740 | Newburgh | Newburgh | Orange | 12550 | G | 4022 | Coldenham | N |  | 21.75 | [13 empty] | NM | N | Enphase M250 (87) | 2014-06-02 | 2014-06-06 | 4 | 2014-06-06 | [14 empty] | 2014-10-22 | 2014-10-27 |  | Y
Central Hudson |  | SolarCity | CH-04955 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8091 | Fishkill Plains | N |  | 8.8 | [13 empty] | NM | N | SOLAREDGE SE3800A-US & SOLAREDGE SE5000A-US | 2014-05-09 | 2014-05-15 | 4 | 2014-05-15 | [14 empty] | 2014-10-21 | 2014-10-24 |  | Y
Central Hudson |  | SolarCity | CH-05039 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7062 | Milan | N | CH-05039 | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A-US | 2014-05-09 | 2014-05-16 | 5 | 2014-05-16 | [14 empty] | 2014-08-19 | 2014-08-21 |  | Y
Central Hudson |  | SolarCity | CH-05505 | Catskill | Catskill | Greene | 12414 | G | 2042 | South Cairo | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A-US | 2014-05-09 | 2014-05-15 | 4 | 2014-05-15 | [14 empty] | 2014-08-19 | 2014-08-26 |  | Y
Central Hudson |  | SolarCity | CH-05560 | Catskill | Hannacroix | Greene | 12087 | G | 2061 | Freehold | N |  | 10 | [13 empty] | NM | N | SOLAREDGE SE5000A-US (2) | 2014-05-09 | 2014-05-16 | 5 | 2014-05-16 | [14 empty] | 2014-07-02 | 2014-07-02 |  | Y
Central Hudson |  | SolarCity | CH-05621 | Kingston | High Fls | Ulster | 12440 | G | 3022 | High Falls | N |  | 3 | [13 empty] | NM | N | SOLAREDGE SE3000A-US | 2014-05-09 | 2014-05-15 | 4 | 2014-05-15 | [14 empty] | 2014-08-22 | 2014-08-29 |  | Y
Central Hudson |  | SolarCity | CH-05630 | Kingston | Tillson | Ulster | 12486 | G | 3021 | High Falls | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A-US | 2014-05-09 | 2014-05-15 | 4 | 2014-05-15 | [14 empty] | 2014-08-26 | 2014-08-29 |  | Y
Central Hudson |  | SolarCity | CH-06001 | Fishkill | Hopewell Jct |  | 12533 | G | 8091 | Fishkill Plains | TBD |  | 15 | [13 empty] | NM | N | SOLAREDGE SE6000A-US (2) & SOLAREDGE SE3000A-US | 2014-05-09 | 2014-05-16 | 5 | 2014-05-16 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | SolarCity | CH-06280 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A-US | 2014-05-09 | 2014-05-15 | 4 | 2014-05-15 | [14 empty] | 2014-07-11 | 2014-07-18 |  | Y
Central Hudson |  | SolarCity | CH-06862 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8092 | Fishkill Plains | N |  | 13.8 | [13 empty] | NM | N | SOLAREDGE SE5000A-US (2) & SOLAREDGE SE3800A-US | 2014-05-09 | 2014-05-15 | 4 | 2014-05-15 | [14 empty] | 2015-01-23 | 2015-01-30 |  | Y
Central Hudson |  | NRG Home Solar | CH-04184 | Newburgh | Rock Tvrn | Orange | 12575 | G | 5052 | Maybrook | N |  | 11.61 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (54) | 2014-05-12 | 2014-05-19 | 5 | 2014-05-19 | [8 empty] | 350 | 350 |  |  |  |  | 2014-06-27 | 2014-06-30 |  | Y
Central Hudson |  | NRG Home Solar | CH-04541 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6046 | Spackenkill | N |  | 4.73 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (22) | 2014-05-20 | 2014-05-28 | 5 | 2014-05-28 | [14 empty] | 2014-07-03 | 2014-07-11 |  | Y
Central Hudson |  | NRG Home Solar | CH-04814 | Poughkeepsie | Staatsburg |  | 12580 | G | 7041 | Staatsburg | TBD |  | 11.61 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (54) | 2014-05-12 | 2014-05-19 | 5 | 2014-05-19 | [8 empty] | 350 | 350 | [7 empty] | W |  | Customer already had net meter prior to application. Transformer upgrade required to accommodate PV installation. Utility System Upgrade Costs TBD.
Central Hudson |  | SolarCity | CH-05883 | Poughkeepsie | Poughquag | Dutchess | 12570 | G | 6055 | Todd Hill | N |  | 16 | [13 empty] | NM | N | SOLAREDGE SE5000A-US (2) & SOLAREDGE SE6000A-US | 2014-05-12 | 2014-05-19 | 5 | 2014-05-19 | [14 empty] | 2014-06-18 | 2014-06-24 |  | Y
Central Hudson |  | New York State Solar Farm | CH-04083 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6043 | Spackenkill | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE7600A | 2014-05-13 | 2014-05-19 | 4 | 2014-05-19 | [14 empty] | 2014-07-29 | 2014-08-01 |  | Y
Central Hudson |  | SolarCity | CH-07566 | Fishkill | Stormvl | Dutchess | 12582 | G | 8095 | Fishkill Plains | N |  | 11 | [13 empty] | NM | N | SOLAREDGE SE5000A-US & SOLAREDGE SE6000A-US | 2014-05-13 | 2014-05-20 | 5 | 2014-05-20 | [14 empty] | 2014-06-23 | 2014-06-23 |  | Y
Central Hudson |  | SunConnect Corporation | CH-09135 | Fishkill | Poughkeepsie | Dutchess | 12603 | G | 8025 | Knapps Corners | N |  | 394.4 | [13 empty] | NM | N | Advanced Energy AE 3TL-23 (17) | 2014-06-11 | 2014-07-02 | 15 | 2014-07-02 | 2014-06-11 | 2014-07-02 | 15 | [11 empty] | 2014-09-22 | 2014-09-30 |  | Y
Central Hudson |  | Sungevity Inc | CH-09553 | Newburgh | Walden | Orange | 12586 | G | 5043 | East Walden | N |  | 9.2 | [13 empty] | NM | N | POWER-ONE PVI-4.2-OUTD & POWER-ONE PVI-5000-OUTD | 2014-05-13 | 2014-05-19 | 4 | 2014-05-19 | [14 empty] | 2014-07-11 | 2014-07-18 |  | Y
Central Hudson |  | Sungevity Inc | CH-09579 | Newburgh | Marlboro | Ulster | 12542 | G | 5002 | Marlboro | N |  | 7 | [13 empty] | NM | N | SMA AMERICA SB7000US-12 | 2014-05-13 | 2014-05-19 | 4 | 2014-05-19 | [14 empty] | 2014-06-17 | 2014-06-24 |  | Y
Central Hudson |  | Sunrise Solar Solutions, LLC | CH-09657 | Newburgh | New Paltz | Ulster | 12561 | G | 5024 | Ohioville | N |  | 6.75 | [13 empty] | NM | N | ENPHASE M250 (27) | 2014-05-13 | 2014-05-20 | 5 | 2014-05-20 | [14 empty] | 2014-12-01 | 2014-12-05 |  | Y
Central Hudson |  | Sunrise Solar Solutions, LLC | CH-09665 | Newburgh | New Paltz | Ulster | 12561 | G | 5022 | Ohioville | N |  | 7.74 | [13 empty] | NM | N | ENPHASE M215 (36) | 2014-05-13 | 2014-05-20 | 5 | 2014-05-20 | [14 empty] | 2014-08-14 | 2014-08-15 |  | Y
Central Hudson |  | New York State Solar Farm | CH-03980 | Poughkeepsie | Salt Pt | Dutchess | 12578 | G | 7011 | Hibernia | N |  | 6 | [13 empty] | NM | N | POWER ONE PVI 6000 | 2014-05-14 | 2014-05-20 | 4 | 2014-05-20 | [14 empty] | 2014-07-17 | 2014-07-24 |  | Y
Central Hudson |  | NRG Home Solar | CH-04596 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8091 | Fishkill Plains | N |  | 9.46 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (44) | 2014-05-14 | 2014-05-20 | 4 | 2014-05-20 | [14 empty] | 2014-06-27 | 2014-07-07 |  | Y
Central Hudson |  | NRG Home Solar | CH-04790 | Newburgh | Rock Tvrn | Orange | 12575 | G | 4097 | Bethlehem Rd | N |  | 10.535 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (49) | 2014-05-14 | 2014-05-20 | 4 | 2014-05-20 | [14 empty] | 2014-06-11 | 2014-06-18 |  | Y
Central Hudson |  | Self | CH-08896 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6052 | Todd Hill | N | CH-08878 | 1.29 | [13 empty] | NM | N | Enphase M215 (6) | 2014-05-14 | 2014-05-14 | 0 | 2014-05-14 | [14 empty] | 2014-06-13 | 2014-06-26 |  | Y
Central Hudson |  | NRG Home Solar | CH-04197 | Newburgh | Wallkill | Ulster | 12589 | G | 5043 | East Walden | N |  | 8.17 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (38) | 2014-05-15 | 2014-05-22 | 5 | 2014-05-22 | [14 empty] | 2014-07-11 | 2014-07-18 |  | Y
Central Hudson |  | NRG Home Solar | CH-04604 | Fishkill | Fishkill | Dutchess | 12524 | G | 8065 | Merritt Park | N |  | 6.665 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (31) | 2014-05-15 | 2014-05-22 | 5 | 2014-05-22 | [14 empty] | 2014-07-22 | 2014-07-25 |  | Y
Central Hudson |  | SolarCity | CH-06172 | Newburgh | Highland | Ulster | 12528 | G | 5022 | Ohioville | N |  | 12 | [13 empty] | NM | N | SOLAREDGE SE6000A-US (2) | 2014-05-15 | 2014-05-22 | 5 | 2014-05-22 | [14 empty] | 2014-06-23 | 2014-06-30 |  | Y
Central Hudson |  | SolarCity | CH-06435 | Catskill | Palenville | Greene | 12463 | G | 2001 | North Catskill | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A-US | 2014-05-15 | 2014-05-22 | 5 | 2014-05-22 | [14 empty] | 2014-06-11 | 2014-06-18 |  | Y
Central Hudson |  | Hudson Solar | CH-02224 | Newburgh | New Windsor | Orange | 12553 | G | 4095 | Bethlehem Rd | N |  | 5 | [13 empty] | NM | N | SMA AMERICA SB5000 | 2014-05-16 | 2014-05-23 | 5 | 2014-05-23 | [14 empty] | 2014-06-19 | 2014-06-26 |  | Y
Central Hudson |  | Hudson Solar | CH-02248 | Kingston | Woodstock | Ulster | 12498 | G | 3014 | Woodstock | N |  | 9 | [13 empty] | NM | N | SMA AMERICA SB9000 | 2014-05-16 | 2014-05-23 | 5 | 2014-05-23 | [14 empty] | 2014-06-19 | 2014-06-26 |  | Y
Central Hudson |  | Hudson Solar | CH-02480 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8071 | Shenandoah | N | CH-01462 | 7 | [13 empty] | NM | N | SMA AMERICA SB7000 | 2014-05-16 | 2014-05-23 | 5 | 2014-05-23 | [14 empty] | 2014-06-19 | 2014-06-26 |  | Y
Central Hudson |  | SolarCity | CH-06889 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8056 | North Chelsea | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE3800A-US (2) | 2014-05-16 | 2014-05-23 | 5 | 2014-05-23 | [14 empty] | 2014-08-19 | 2014-08-21 |  | Y
Central Hudson |  | Sungevity Inc | CH-09296 | Kingston | Grahamsvl | Sullivan | 12740 | G | 3091 | Neversink | N |  | 8 | [13 empty] | NM | N | SMA AMERICA SB8000US-12 | 2014-05-16 | 2014-05-23 | 5 | 2014-05-23 | [14 empty] | 2014-07-29 | 2014-08-05 |  | Y
Central Hudson |  | Sungevity Inc | CH-09365 | Newburgh | Gardiner | Ulster | 12525 | G | 5031 | Galeville | N |  | 7.6 | [13 empty] | NM | N | POWER-ONE PVI-3.8-OUTD (2) | 2014-05-16 | 2014-05-23 | 5 | 2014-05-23 | [14 empty] | 2014-08-20 | 2014-08-25 |  | Y
Central Hudson |  | NRG Home Solar | CH-04273 | Kingston | Spring Glen | Ulster | 12483 | G | 3078 | Greenfield Rd | N |  | 9.675 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (45) | 2014-05-19 | 2014-05-27 | 5 | 2014-05-27 | [14 empty] | 2014-09-30 | 2014-10-01 |  | Y
Central Hudson |  | New York Light Energy, LLC | CH-02769 | Catskill | Coxsackie | Greene | 12051 | G | 1074 | Coxsackie | N |  | 75 | [13 empty] | RNM | N | AE 75TX | 2014-05-30 | 2014-06-20 | 15 | 2014-06-20 | 2014-05-30 | 2014-06-20 | 15 | [5 empty] | 8000 | 10071.64 |  |  |  |  | 2014-11-14 | 2014-11-18 |  | Y
Central Hudson |  | Solar Generation | CH-08258 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8096 | Fishkill Plains | N |  | 10 | [13 empty] | NM | N | SMA 5000 SB-TL (2) | 2014-05-28 | 2014-06-03 | 4 | 2014-06-03 | [14 empty] | 2014-08-01 | 2014-08-08 |  | Y
Central Hudson |  | Sungevity Inc | CH-09235 | Newburgh | Gardiner | Ulster | 12525 | G | 5011 | Modena | N |  | 7 | [13 empty] | NM | N | SMA AMERICA SB7000US-12 | 2014-05-19 | 2014-05-27 | 5 | 2014-05-27 | [14 empty] | 2014-06-27 | 2014-07-07 |  | Y
Central Hudson |  | Sungevity Inc | CH-09387 | Newburgh | Wallkill | Ulster | 12589 | G | 5041 | East Walden | N |  | 8 | [13 empty] | NM | N | SMA AMERICA SB8000US-12 | 2014-05-19 | 2014-05-27 | 5 | 2014-05-27 | [14 empty] | 2014-07-08 | 2014-07-15 |  | Y
Central Hudson |  | Sungevity Inc | CH-09466 | Newburgh | New Paltz | Ulster | 12561 | G | 5024 | Ohioville | N | CH-09466 | 5 | [13 empty] | NM | N | SMA AMERICA SB5000TL-US | 2014-05-19 | 2014-05-27 | 5 | 2014-05-27 | [14 empty] | 2014-07-08 | 2014-07-15 |  | Y
Central Hudson |  | Hollitronics Energy Solutions | CH-01205 | Catskill | Rensselaervl | Albany | 12147 | G | 1092 | Westerlo | N |  | 4.5 | [13 empty] | NM | N | Enphase M250 (18) Enphase M250 (18) | 2014-05-28 | 2014-06-03 | 4 | 2014-06-03 | [14 empty] | 2014-08-11 | 2014-08-18 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03588 | Newburgh | New Paltz | Ulster | 12561 | G | 5031 | Galeville | N |  | 8.6 | [13 empty] | NM | N | POWER-ONE AURORA UNO 8.6-OUTD-S-US | 2014-05-21 | 2014-06-02 | 7 | 2014-06-02 | [14 empty] | 2014-11-11 | 2014-11-13 |  | Y
Central Hudson |  | NRG Home Solar | CH-04213 | Newburgh | Marlboro |  | 12542 | G | 5004 | Marlboro | TBD |  | 8.6 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (40) | 2014-05-21 | 2014-05-30 | 6 | 2014-05-30 | [17 empty] | W |  | 5/26/14 Company Holiday.
Central Hudson |  | NRG Home Solar | CH-04506 | Newburgh | Rock Tvrn |  | 12575 | G | 4097 | Bethlehem Rd | TBD |  | 9.89 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (46) | 2014-05-21 | 2014-05-30 | 6 | 2014-05-30 | [17 empty] | W |  | Customer already had net meter prior to application. 5/26/14 Company Holiday.
Central Hudson |  | Murphy Solar Power | CH-02752 | Kingston | Connelly | Ulster | 12417 | G | 1024 | East Kingston | N |  | 5 | [13 empty] | NM | N | SMA 5000US | 2014-06-12 | 2014-06-20 | 6 | 2014-06-20 | [14 empty] | 2014-09-02 | 2014-09-05 |  | Y
Central Hudson |  | SolarCity | CH-05310 | Newburgh | Wallkill | Ulster | 12589 | G | 5013 | Modena | N |  | 6.8 | [13 empty] | NM | N | SOLAREDGE SE3000A-US & SOLAREDGE SE3800A-US | 2014-05-21 | 2014-05-29 | 5 | 2014-05-29 | [14 empty] | 2014-07-10 | 2014-07-17 |  | Y
Central Hudson |  | SolarCity | CH-05410 | Newburgh | New Windsor | Orange | 12553 | G | 4046 | Union Ave | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A-US | 2014-05-21 | 2014-05-29 | 5 | 2014-05-29 | [14 empty] | 2014-06-20 | 2014-06-26 |  | Y
Central Hudson |  | SolarCity | CH-05422 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8072 | Shenandoah | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A-US | 2014-05-21 | 2014-05-29 | 5 | 2014-05-29 | [14 empty] | 2014-08-19 | 2014-08-21 |  | Y
Central Hudson |  | SolarCity | CH-06470 | Catskill | W Coxsackie | Greene | 12192 | G | 1071 | Coxsackie | N |  | 8.8 | [13 empty] | NM | N | SOLAREDGE SE3800A-US & SOLAREDGE SE5000A-US | 2014-05-21 | 2014-05-29 | 5 | 2014-05-29 | [14 empty] | 2014-07-29 | 2014-07-29 |  | Y
Central Hudson |  | SolarCity | CH-06708 | Poughkeepsie | Lagrangevl | Dutchess | 12540 | G | 6055 | Todd Hill | N |  | 11 | [13 empty] | NM | N | SOLAREDGE SE5000A-US & SOLAREDGE SE6000A-US | 2014-05-21 | 2014-05-29 | 5 | 2014-05-29 | [8 empty] | 350 | 350 |  |  |  |  | 2014-08-14 | 2014-08-15 |  | Y
Central Hudson |  | SolarCity | CH-06779 | Poughkeepsie | Millerton | Dutchess | 12546 | G | 7081 | Millerton | N |  | 3 | [13 empty] | NM | N | SOLAREDGE SE3000A-US | 2014-05-21 | 2014-06-05 | 10 | 2014-06-05 | [14 empty] | 2014-08-25 | 2014-09-02 |  | Y
Central Hudson |  | SolarCity | CH-07420 | Newburgh | Walden | Orange | 12586 | G | 5041 | East Walden | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A-US | 2014-06-05 | 2014-06-12 | 5 | 2014-06-12 | [14 empty] | 2014-07-22 | 2014-07-28 |  | Y
Central Hudson |  | Sungevity Inc | CH-09307 | Kingston | Ruby | Ulster | 12475 | G | 2016 | Lincoln Park | N |  | 6 | [13 empty] | NM | N | POWER ONE PVI 6000 | 2014-05-21 | 2014-05-28 | 4 | 2014-05-28 | [14 empty] | 2014-07-30 | 2014-07-30 |  | Y
Central Hudson |  | Sungevity Inc | CH-09535 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8091 | Fishkill Plains | N |  | 9.2 | [13 empty] | NM | N | POWER ONE PVI 4.2 & POWER ONE PVI 5.0 | 2014-05-21 | 2014-05-28 | 4 | 2014-05-28 | [14 empty] | 2014-07-15 | 2014-07-16 |  | Y
Central Hudson |  | NRG Home Solar | CH-04191 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6051 | Todd Hill | N |  | 6.88 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (32) | 2014-05-22 | 2014-06-05 | 9 | 2014-06-05 | [14 empty] | 2014-07-08 | 2014-07-15 |  | Y
Central Hudson |  | NRG Home Solar | CH-04715 | Fishkill | Wappingers Falls | Dutchess | 12590 | G | 8091 | Fishkill Plains | N |  | 6.235 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (29) | 2014-05-22 | 2014-06-05 | 9 | 2014-06-05 | [14 empty] | 2014-07-02 | 2014-07-10 |  | Y
Central Hudson |  | Sol Providers | CH-08951 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8043 | Myers Corners | N |  | 6 | [13 empty] | NM | N | SMA SB3000TL (2) | 2014-05-22 | 2014-06-02 | 6 | 2014-06-02 | [14 empty] | 2014-07-01 | 2014-07-09 |  | Y
Central Hudson |  | NRG Home Solar | CH-04206 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6093 | Manchester | N |  | 5.16 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (24) | 2014-06-04 | 2014-06-11 | 5 | 2014-06-11 | [14 empty] | 2014-07-02 | 2014-07-10 |  | Y
Central Hudson |  | NRG Home Solar | CH-04240 | Catskill | Catskill | Greene | 12414 | G | 2003 | North Catskill | N |  | 4.945 | [13 empty] | NM | N | ENPHASE ENERGY M215 (23) | 2014-05-23 | 2014-06-09 | 10 | 2014-06-09 | [14 empty] | 2014-06-10 | 2014-06-17 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | NRG Home Solar | CH-04762 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 6073 | East Park | N |  | 5.16 | [13 empty] | NM | N | ENPHASE ENERGY M215 (24) | 2014-05-23 | 2014-06-06 | 9 | 2014-06-06 | [14 empty] | 2014-06-27 | 2014-07-07 |  | Y
Central Hudson |  | SolarCity | CH-05334 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8071 | Shenandoah | N |  | 15 | [13 empty] | NM | N | SOLAREDGE SE5000A-US (3) | 2014-05-23 | 2014-06-06 | 9 | 2014-06-06 | [14 empty] | 2014-06-23 | 2014-06-30 |  | Y
Central Hudson |  | SolarCity | CH-05980 | Newburgh | Highland | Ulster | 12528 | G | 5081 | Highland | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A-US | 2014-05-23 | 2014-06-06 | 9 | 2014-06-06 | [14 empty] | 2014-07-24 | 2014-07-31 |  | Y
Central Hudson |  | SolarCity | CH-06033 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8052 | North Chelsea | N |  | 6.8 | [13 empty] | NM | N | SOLAREDGE SE3000A-US & SOLAREDGE SE3800A-US | 2014-05-23 | 2014-06-02 | 5 | 2014-06-02 | [14 empty] | 2014-07-22 | 2014-07-28 |  | Y
Central Hudson |  | SolarCity | CH-06055 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8091 | Fishkill Plains | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE3800A-US (2) | 2014-05-23 | 2014-06-06 | 9 | 2014-06-06 | [14 empty] | 2014-08-19 | 2014-08-21 |  | Y
Central Hudson |  | SolarCity | CH-06570 | Kingston | Saugerties | Ulster | 12477 | G | 3002 | Saugerties | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A-US | 2014-05-23 | 2014-06-06 | 9 | 2014-06-06 | [14 empty] | 2014-07-29 | 2014-07-29 |  | Y
Central Hudson |  | SolarCity | CH-06984 | Newburgh | Newburgh | Orange | 12550 | G | 4024 | Coldenham | N |  | 13.8 | [13 empty] | NM | N | SOLAREDGE SE3800A-US & SOLAREDGE SE5000A-US (2) | 2014-05-23 | 2014-06-06 | 9 | 2014-06-06 | [14 empty] | 2014-10-27 | 2014-10-31 |  | Y
Central Hudson |  | Sungevity Inc | CH-09193 | Newburgh | Wallkill | Ulster | 12589 | G | 5033 | Galeville | N |  | 5 | [13 empty] | NM | N | SMA AMERICA SB5000TL-US-22 | 2014-05-23 | 2014-06-06 | 9 | 2014-06-06 | [14 empty] | 2014-08-05 | 2014-08-11 |  | Y
Central Hudson |  | Sungevity Inc | CH-09417 | Kingston | Saugerties | Ulster | 12477 | G | 3001 | Saugerties | N |  | 5 | [13 empty] | NM | N | SMA AMERICA SB5000TL-US | 2014-05-23 | 2014-06-09 | 10 | 2014-06-09 | [14 empty] | 2014-07-31 | 2014-08-07 |  | Y
Central Hudson |  | CNR Energy Solutions, LLC | CH-00776 | Newburgh | Highland | Ulster | 12528 | G | 5081 | Highland | N |  | 7.5 | [13 empty] | NM | N | ENPHASE M250 (30) | 2014-05-27 | 2014-06-03 | 5 | 2014-06-03 | [14 empty] | 2014-06-30 | 2014-07-08 |  | Y
Central Hudson |  | New York State Solar Farm | CH-04085 | Newburgh | Gardiner | Ulster | 12525 | G | 5034 | Galeville | N |  | 5 | [13 empty] | NM | N | PowerOne PVI 5000 | 2014-05-28 | 2014-06-11 | 10 | 2014-06-11 | [14 empty] | 2014-07-22 | 2014-07-28 |  | Y
Central Hudson |  | NRG Home Solar | CH-04453 | Newburgh | Newburgh | Orange | 12550 | G | 4024 | Coldenham | N |  | 5.16 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (24) | 2014-05-28 | 2014-06-11 | 10 | 2014-06-11 | [14 empty] | 2014-08-26 | 2014-09-03 |  | Y
Central Hudson |  | NRG Home Solar | CH-04631 | Newburgh | Newburgh |  | 12550 | G | 4054 | Union Ave | TBD |  | 4.73 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (22) | 2014-05-28 | 2014-06-11 | 10 | 2014-06-11 | [17 empty] | W
Central Hudson |  | Hudson Solar | CH-01410 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6046 | Spackenkill | N | CH-01410 | 5 | [13 empty] | NM | N | SMA AMERICA SB5000 | 2014-05-29 | 2014-06-05 | 5 | 2014-06-05 | [14 empty] | 2014-07-02 | 2014-07-10 |  | Y
Central Hudson |  | SolarCity | CH-04937 | Catskill | Greenvl | Greene | 12083 | G | 2061 | Freehold | N |  | 10 | [13 empty] | NM | N | SOLAREDGE SE5000A-US (2) | 2014-05-29 | 2014-06-05 | 5 | 2014-06-05 | [14 empty] | 2014-08-19 | 2014-08-26 |  | Y
Central Hudson |  | SolarCity | CH-05402 | Newburgh | Highland | Ulster | 12528 | G | 5082 | Highland | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A-US | 2014-05-29 | 2014-06-05 | 5 | 2014-06-05 | [14 empty] | 2014-07-24 | 2014-07-31 |  | Y
Central Hudson |  | SolarCity | CH-05674 | Kingston | Kingston | Ulster | 12401 | G | 1022 | East Kingston | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE3800A-US (2) | 2014-05-29 | 2014-06-05 | 5 | 2014-06-05 | [14 empty] | 2015-05-21 | 2015-05-29 |  | Y
Central Hudson |  | SolarCity | CH-06432 | Catskill | Catskill | Greene | 12414 | G | 2004 | North Catskill | N |  | 10 | [13 empty] | NM | N | SOLAREDGE SE5000A-US (2) | 2014-05-29 | 2014-06-05 | 5 | 2014-06-05 | [8 empty] | 350 | 350 |  |  |  |  | 2014-08-04 | 2014-08-11 |  | Y
Central Hudson |  | SolarCity | CH-06821 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8052 | North Chelsea | N |  | 10 | [13 empty] | NM | N | SOLAREDGE SE5000A-US (2) | 2014-05-29 | 2014-06-05 | 5 | 2014-06-05 | [14 empty] | 2015-02-27 | 2015-03-02 |  | Y
Central Hudson |  | Hudson Solar | CH-01295 | Kingston | Glasco | Ulster | 12432 | G | 2015 | Lincoln Park | N |  | 5 | [13 empty] | NM | N | SMA SB5000 | 2014-05-30 | 2014-06-06 | 5 | 2014-06-06 | [14 empty] | 2014-07-31 | 2014-08-07 |  | Y
Central Hudson |  | Hudson Solar | CH-02333 | Kingston | Kingston | Ulster | 12401 | G | 2094 | Hurley Ave | N |  | 8 | [13 empty] | NM | N | SMA SB8000 | 2014-05-30 | 2014-06-06 | 5 | 2014-06-06 | [14 empty] | 2014-07-10 | 2014-07-10 |  | Y
Central Hudson |  | Hudson Solar | CH-02386 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7052 | Rhinebeck | N |  | 5 | [13 empty] | NM | N | SMA SB5000 | 2014-05-30 | 2014-06-06 | 5 | 2014-06-06 | [14 empty] | 2014-07-02 | 2014-07-10 |  | Y
Central Hudson |  | SolarCity | CH-06464 | Catskill | Westerlo | Albany | 12193 | G | 1091 | Westerlo | N |  | 9 | [13 empty] | NM | N | SOLAREDGE SE3000A-US & SOLAREDGE SE6000A-US | 2014-05-30 | 2014-06-06 | 5 | 2014-06-06 | [14 empty] | 2014-08-07 | 2014-08-14 |  | Y
Central Hudson |  | Solar Generation | CH-08106 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7062 | Milan | N |  | 8 | [13 empty] | NM | N | SMA 4000TL (2) | 2014-05-30 | 2014-06-06 | 5 | 2014-06-06 | [14 empty] | 2014-09-03 | 2014-09-10 |  | Y
Central Hudson |  | Sungevity Inc | CH-09426 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6065 | Inwood Ave | N |  | 6 | [13 empty] | NM | N | POWER-ONE PVI-6000-OUTD | 2014-05-30 | 2014-06-06 | 5 | 2014-06-06 | [14 empty] | 2014-08-28 | 2014-09-05 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-03407 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8023 | Knapps Corners | N |  | 8 | [13 empty] | NM | N | SMA SB 8000US | 2014-06-02 | 2014-06-12 | 8 | 2014-06-12 | [14 empty] | 2014-07-21 | 2014-07-25 |  | Y
Central Hudson |  | Sungevity Inc | CH-09182 | Kingston | Napanoch | Ulster | 12458 | G | 3091 | Neversink | N |  | 6 | [13 empty] | NM | N | POWER-ONE PVI-6000-OUTD | 2014-06-02 | 2014-06-09 | 5 | 2014-06-09 | [14 empty] | 2014-07-23 | 2014-07-30 |  | Y
Central Hudson |  | Sungevity Inc | CH-09311 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6045 | Spackenkill | N |  | 6 | [13 empty] | NM | N | SMA AMERICA SB6000TL-US | 2014-06-02 | 2014-06-09 | 5 | 2014-06-09 | [14 empty] | 2014-08-08 | 2014-08-13 |  | Y
Central Hudson |  | Sungevity Inc | CH-09314 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6044 | Spackenkill | N |  | 6 | [13 empty] | NM | N | POWER-ONE PVI-6000-OUTD | 2014-06-02 | 2014-06-09 | 5 | 2014-06-09 | [14 empty] | 2014-09-11 | 2014-09-18 |  | Y
Central Hudson |  | Sungevity Inc | CH-09393 | Catskill | Palenvl | Greene | 12463 | G | 2042 | South Cairo | N |  | 7 | [13 empty] | NM | N | SMA AMERICA SB7000US-12 | 2014-06-12 | 2014-06-19 | 5 | 2014-06-19 | [14 empty] | 2014-08-14 | 2014-08-20 |  | Y
Central Hudson |  | Sungevity Inc | CH-09490 | Newburgh | Newburgh | Orange | 12550 | G | 5004 | Marlboro | N |  | 5 | [13 empty] | NM | N | SMA AMERICA SB5000TL-US | 2014-06-02 | 2014-06-09 | 5 | 2014-06-09 | [14 empty] | 2016-09-06 | 2016-09-07 |  | Y
Central Hudson |  | Sunrise Solar Solutions, LLC | CH-09663 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8094 | Fishkill Plains | N |  | 6.235 | [13 empty] | NM | N | ENPHASE M215 (30) | 2014-06-10 | 2014-06-17 | 5 | 2014-06-17 | [14 empty] | 2014-12-01 | 2014-12-08 |  | Y
Central Hudson |  | NRG Home Solar | CH-04775 | Newburgh | Newburgh | Orange | 12550 | G | 4012 | West Balmville | N |  | 4.73 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (22) | 2014-06-03 | 2014-06-10 | 5 | 2014-06-10 | [14 empty] | 2014-07-09 | 2014-07-16 |  | Y
Central Hudson |  | NRG Home Solar | CH-04835 | Newburgh | Newburgh |  | 12550 | G | 4053 | Union Ave | TBD |  | 9.03 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (42) | 2014-06-03 | 2014-06-11 | 6 | 2014-06-11 | [17 empty] | W
Central Hudson |  | Direct Energy Solar | CH-00869 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8051 | North Chelsea | N |  | 7.095 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (33) | 2014-06-03 | 2014-06-10 | 5 | 2014-06-10 | [14 empty] | 2014-07-10 | 2014-07-17 |  | Y
Central Hudson |  | Hudson Solar | CH-01493 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7053 | Rhinebeck | N |  | 9 | [13 empty] | NM | N | SMA SB5000 & SMA SB4000 | 2014-06-30 | 2014-07-08 | 5 | 2014-07-08 | [14 empty] | 2014-08-01 | 2014-08-08 |  | Y
Central Hudson |  | Hudson Solar | CH-02017 | Kingston | New Paltz | Ulster | 12561 | G | 3041 | Sturgeon Pool | N |  | 12 | [13 empty] | NM | N | SMA SB6000 | 2014-06-03 | 2014-06-10 | 5 | 2014-06-10 | [8 empty] | 350 | 350 |  |  |  |  | 2014-10-02 | 2014-10-09 |  | Y
Central Hudson |  | Hudson Solar | CH-02260 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 7041 | Staatsburg | N |  | 7 | [13 empty] | NM | N | SMA SB7000 TL-US | 2014-06-03 | 2014-06-10 | 5 | 2014-06-10 | [14 empty] | 2014-07-02 | 2014-07-10 |  | Y
Central Hudson |  | Sungevity Inc | CH-09505 | Newburgh | Washingtonvl | Orange | 10992 | G | 5052 | Maybrook | N |  | 6.8 | [13 empty] | NM | N | SMA SB3800TL & SMA SB 3000TL | 2014-06-12 | 2014-06-19 | 5 | 2014-06-19 | [14 empty] | 2014-08-12 | 2014-08-14 |  | Y
Central Hudson |  | New York State Solar Farm | CH-03974 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6042 | Spackenkill | N |  | 22 | [13 empty] | NM | N | SMA AMERICA SB8000 (2) & POWER ONE PVI6.0 | 2014-06-11 | 2014-06-18 | 5 | 2014-06-18 | [8 empty] | 350 | 350 |  |  |  |  | 2014-11-14 | 2014-11-17 |  | Y
Central Hudson |  | New York State Solar Farm | CH-04005 | Newburgh | Marlboro | Ulster | 12542 | G | 5003 | Marlboro | N |  | 8.8 | [13 empty] | NM | N | POWER ONE PVI 3.8 & POWER ONE PVI 5.0 | 2014-06-13 | 2014-06-20 | 5 | 2014-06-20 | [14 empty] | 2014-08-27 | 2014-09-04 |  | Y
Central Hudson |  | New York State Solar Farm | CH-04009 | Newburgh | Milton | Ulster | 12547 | G | 5003 | Marlboro | N |  | 12.6 | [13 empty] | NM | N | POWER ONE PVI 3.8 (2) & POWER ONE PVI 5.0 | 2014-06-04 | 2014-06-11 | 5 | 2014-06-11 | [14 empty] | 2014-08-21 | 2014-08-28 |  | Y
Central Hudson |  | New York State Solar Farm | CH-04049 | Newburgh | Gardiner | Ulster | 12525 | G | 5031 | Galeville | N |  | 7 | [13 empty] | NM | N | SMA AMERICA SB 7000 | 2014-06-04 | 2014-06-11 | 5 | 2014-06-11 | [14 empty] | 2014-08-18 | 2014-08-19 |  | Y
Central Hudson |  | SolarCity | CH-05164 | Newburgh | Newburgh | Orange | 12550 | G | 4012 | West Balmville | N |  | 11 | [13 empty] | NM | N | SOLAREDGE SE6000A-US & SOLAREDGE SE5000A-US | 2014-06-04 | 2014-06-11 | 5 | 2014-06-11 | [14 empty] | 2014-08-29 | 2014-09-08 |  | Y
Central Hudson |  | SolarCity | CH-05476 | Newburgh | Highland | Ulster | 12528 | G | 5012 | Modena | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A-US | 2014-06-04 | 2014-06-11 | 5 | 2014-06-11 | [14 empty] | 2014-07-22 | 2014-07-24 |  | Y
Central Hudson |  | Sungevity Inc | CH-09432 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6096 | Manchester | N |  | 5 | [13 empty] | NM | N | POWER ONE PVI 5000 | 2014-06-17 | 2014-06-24 | 5 | 2014-06-24 | [14 empty] | 2014-09-12 | 2014-09-18 |  | Y
Central Hudson |  | Sungevity Inc | CH-09506 | Newburgh | Campbell Hall |  | 10916 | G | 5052 | Maybrook | TBD |  | 11 | [13 empty] | NM | N | POWER-ONE PVI-6000-OUTD & POWER-ONE PVI-5000-OUTD | 2014-06-12 | 2014-06-19 | 5 | 2014-06-19 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | NRG Home Solar | CH-04260 | Kingston | Rosendale | Ulster | 12472 | G | 3022 | High Falls | N |  | 4.3 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (20) | 2014-06-05 | 2014-06-12 | 5 | 2014-06-12 | [14 empty] | 2014-07-16 | 2014-07-16 |  | Y
Central Hudson |  | Sungevity Inc | CH-09386 | Newburgh | Modena | Ulster | 12548 | G | 5012 | Modena | N |  | 6 | [13 empty] | NM | N | POWER ONE PVI-6000-OUTD | 2014-06-17 | 2014-06-24 | 5 | 2014-06-24 | [14 empty] | 2014-11-17 | 2014-11-21 |  | Y
Central Hudson |  | Sungevity Inc | CH-09585 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6052 | Todd Hill | N |  | 8 | [13 empty] | NM | N | SMA AMERICA SB8000-US-12 | 2014-06-05 | 2014-06-12 | 5 | 2014-06-12 | [14 empty] | 2014-08-20 | 2014-08-25 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03689 | Newburgh | Gardiner | Ulster | 12525 | G | 5031 | Galeville | N |  | 15.2 | [13 empty] | NM | N | POWER-ONE AURORA UNO 7.6-OUTD-S-US (2) | 2014-06-06 | 2014-06-13 | 5 | 2014-06-13 | [14 empty] | 2014-09-04 | 2014-09-10 |  | Y
Central Hudson |  | Lotus Energy Inc. | CH-03881 | Poughkeepsie | Ancram | Columbia | 12502 | G | 7091 | Pulvers Corners | N |  | 6 | [13 empty] | NM | N | SMA 3800 (2) | 2014-06-16 | 2014-06-23 | 5 | 2014-06-23 | [14 empty] | 2014-08-21 | 2014-08-21 |  | Y
Central Hudson |  | SolarCity | CH-06009 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8091 | Fishkill Plains | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A-US | 2014-06-06 | 2014-06-16 | 6 | 2014-06-16 | [14 empty] | 2014-07-22 | 2014-07-28 |  | Y
Central Hudson |  | SolarCity | CH-06399 | Newburgh | Newburgh | Orange | 12550 | G | 4091 | Bethlehem Rd | N |  | 6.8 | [13 empty] | NM | N | SOLAREDGE SE3000A-US & SOLAREDGE SE3800A-US | 2014-06-06 | 2014-06-13 | 5 | 2014-06-13 | [14 empty] | 2014-08-11 | 2014-08-14 |  | Y
Central Hudson |  | SolarCity | CH-07403 | Fishkill | Beacon | Dutchess | 12508 | G | 8087 | Tioronda | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A-US | 2014-06-06 | 2014-06-16 | 6 | 2014-06-16 | [14 empty] | 2014-08-27 | 2014-09-04 |  | Y
Central Hudson |  | SolarCity | CH-07562 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8094 | Fishkill Plains | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A-US | 2014-06-06 | 2014-06-13 | 5 | 2014-06-13 | [14 empty] | 2014-08-06 | 2014-08-13 |  | Y
Central Hudson |  | Sun Mountain | CH-09104 | Kingston | West Shokan | Ulster | 12494 | G | 3011 | Woodstock | N |  | 7 | [13 empty] | NM | N | SMA AS7000 US | 2014-06-06 | 2014-06-16 | 6 | 2014-06-16 | [14 empty] | 2014-08-14 | 2014-08-20 |  | Y
Central Hudson |  | Sungevity Inc | CH-09231 | Newburgh | Clintondale | Ulster | 12515 | G | 5012 | Modena | N |  | 5 | [13 empty] | NM | N | SMA AMERICA SB5000TL-US-22 | 2014-06-06 | 2014-06-13 | 5 | 2014-06-13 | [14 empty] | 2014-09-02 | 2014-09-09 |  | Y
Central Hudson |  | Sungevity Inc | CH-09305 | Kingston | Saugerties | Ulster | 12477 | G | 3001 | Saugerties | N |  | 5 | [13 empty] | NM | N | SMA SB5000TL | 2014-06-06 | 2014-06-13 | 5 | 2014-06-13 | [14 empty] | 2014-08-12 | 2014-08-19 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03720 | Newburgh | Wallkill | Ulster | 12589 | G | 5043 | East Walden | N |  | 11 | [13 empty] | NM | N | POWER-ONE AURORA PVI6000-OUTD-US & POWER-ONE AURORA PVI5000-OUTD-US | 2014-06-09 | 2014-06-16 | 5 | 2014-06-16 | [14 empty] | 2014-08-21 | 2014-08-28 |  | Y
Central Hudson |  | NRG Home Solar | CH-04364 | Poughkeepsie | Millerton | Dutchess | 12546 | G | 7081 | Millerton | N |  | 5.16 | [13 empty] | NM | N | (24) Enphase Energy M-215-60-2LL-S22-IG | 2014-06-09 | 2014-06-17 | 6 | 2014-06-17 | [14 empty] | 2014-08-06 | 2014-08-12 |  | Y
Central Hudson |  | NRG Home Solar | CH-04497 | Newburgh | Cornwall-Hdsn | Orange | 12520 | G | 4043 | Union Ave | N |  | 3.01 | [13 empty] | NM | N | (14) ENPHASE ENERGY M-215-60-2LL-S22-IG | 2014-06-09 | 2014-06-16 | 5 | 2014-06-16 | [14 empty] | 2014-07-08 | 2014-07-15 |  | Y
Central Hudson |  | SolarCity | CH-05024 | Poughkeepsie | Millbrook | Dutchess | 12545 | G | 7025 | Tinkertown | N |  | 8.8 | [13 empty] | NM | N | 1 - SOLAREDGE SE5000A-US 1 - SOLAREDGE SE3800A-US | 2014-06-09 | 2014-06-16 | 5 | 2014-06-16 | [8 empty] | 350 | 350 |  |  |  |  | 2014-12-05 | 2014-12-08 |  | Y
Central Hudson |  | SolarCity | CH-05904 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6056 | Todd Hill | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A-US | 2014-06-09 | 2014-06-16 | 5 | 2014-06-16 | [14 empty] | 2014-07-23 | 2014-07-30 |  | Y
Central Hudson |  | SolarCity | CH-06438 | Catskill | Elka Pk | Greene | 12427 | G | 2385 | Lawrenceville | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A-US | 2014-06-09 | 2014-06-17 | 6 | 2014-06-17 | [14 empty] | 2014-08-26 | 2014-08-29 |  | Y
Central Hudson |  | SolarCity | CH-06888 | Fishkill | Fishkill | Dutchess | 12524 | G | 8014 | Forgebrook | N |  | 12 | [13 empty] | NM | N | (2) SOLAREDGE SE6000A-US | 2014-06-09 | 2014-06-17 | 6 | 2014-06-17 | [14 empty] | 2014-08-25 | 2014-09-02 |  | Y
Central Hudson |  | SolarCity | CH-07815 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6096 | Manchester | N | CH-06745 | 7.5 | [13 empty] | NM | N | FRONIUS IG PLUS A 7.5 | 2014-06-09 | 2014-06-16 | 5 | 2014-06-16 | [14 empty] | 2014-09-04 | 2014-09-11 |  | Y
Central Hudson |  | SunBlue Energy | CH-09129 | Fishkill | Garrison | Putnam | 10524 | G | 8086 | Tioronda | N |  | 14 | [13 empty] | NM | N | SMA SUNNYBOY 7000TL (2) | 2014-06-25 | 2014-06-25 | 0 | 2014-06-25 | [8 empty] | 350 | 350 |  |  |  |  | 2014-09-25 | 2014-10-01 |  | Y
Central Hudson |  | Sungevity Inc | CH-09200 | Newburgh | Wallkill | Ulster | 12589 | G | 5043 | East Walden | N |  | 6.8 | [13 empty] | NM | N | POWER ONE PVI 3.8 & POWER ONE PVI 3.0 | 2014-06-09 | 2014-06-16 | 5 | 2014-06-16 | [14 empty] | 2014-08-12 | 2014-08-14 |  | Y
Central Hudson |  | NRG Home Solar | CH-04108 | Kingston | Kingston | Ulster | 12401 | G | 2016 | Lincoln Park | N |  | 7.52 | [13 empty] | NM | N | ENPHASE ENERGY M-215-60-2LL-S22-IG | 2014-06-10 | 2014-06-17 | 5 | 2014-06-17 | [14 empty] | 2014-08-26 | 2014-08-29 |  | Y
Central Hudson |  | NRG Home Solar | CH-04654 | Newburgh | Wallkill | Ulster | 12589 | G | 4011 | West Balmville | N |  | 3.225 | [13 empty] | NM | N | (15) ENPHASE ENERGY M-215-60-2LL-S22-IG | 2014-06-10 | 2014-06-18 | 6 | 2014-06-18 | [14 empty] | 2014-08-27 | 2014-09-04 |  | Y
Central Hudson |  | SolarCity | CH-06175 | Newburgh | New Paltz | Ulster | 12561 | G | 5023 | Ohioville | N |  | 11 | [13 empty] | NM | N | SOLAREDGE SE5000A-US & SOLAREDGE SE6000A-US | 2014-06-10 | 2014-06-18 | 6 | 2014-06-18 | [14 empty] | 2014-10-08 | 2014-10-14 |  | Y
Central Hudson |  | SolarCity | CH-07672 | Newburgh | New Paltz | Ulster | 12561 | G | 5023 | Ohioville | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE3800A-US (2) | 2014-06-10 | 2014-06-18 | 6 | 2014-06-18 | [14 empty] | 2014-08-27 | 2014-09-04 |  | Y
Central Hudson |  | Solar Generation | CH-08222 | Kingston | Woodstock | Ulster | 12498 | G | 3013 | Woodstock | N |  | 3.8 | [13 empty] | NM | N | SMA SB5000-TL-US | 2014-06-10 | 2014-06-17 | 5 | 2014-06-17 | [14 empty] | 2014-08-12 | 2014-08-19 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08846 | Catskill | Westerlo | Albany | 12193 | G | 1091 | Westerlo | N |  | 5.59 | [13 empty] | NM | N | ENPHASE M215 (26) | 2014-06-18 | 2014-06-25 | 5 | 2014-06-25 | [14 empty] | 2015-03-18 | 2015-03-25 |  | Y
Central Hudson |  | Sungevity Inc | CH-09478 | Newburgh | Newburgh | Orange | 12550 | G | 4014 | West Balmville | N |  | 4 | [13 empty] | NM | N | SMA SB 4000 | 2014-06-10 | 2014-06-18 | 6 | 2014-06-18 | [14 empty] | 2014-08-12 | 2014-08-14 |  | Y
Central Hudson |  | New York State Solar Farm | CH-04017 | Newburgh | Montgomery | Orange | 12549 | G | 5073 | Montgomery | N |  | 7 | [13 empty] | NM | N | SMA SunnyBoy 7000 | 2014-06-27 | 2014-07-07 | 5 | 2014-07-07 | [14 empty] | 2014-09-02 | 2014-09-09 |  | Y
Central Hudson |  | New York State Solar Farm | CH-04066 | Newburgh | New Paltz | Ulster | 12561 | G | 5011 | Modena | N |  | 10 | [13 empty] | NM | N | (2) SB 5000 | 2014-06-11 | 2014-06-18 | 5 | 2014-06-18 | [14 empty] | 2014-10-21 | 2014-10-24 |  | Y
Central Hudson |  | New York State Solar Farm | CH-04082 | Newburgh | Gardiner | Ulster | 12525 | G | 5011 | Modena | N |  | 8 | [13 empty] | NM | N | SMA AMERICA SB8000 - US | 2014-06-11 | 2014-06-17 | 4 | 2014-06-17 | [14 empty] | 2014-09-25 | 2014-10-01 |  | Y
Central Hudson |  | NRG Home Solar | CH-04384 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8052 | North Chelsea | N |  | 6.665 | [13 empty] | NM | N | (31) ENPHASE ENERGY M-215-60-2LL-S22-IG | 2014-06-11 | 2014-06-19 | 6 | 2014-06-19 | [14 empty] | 2014-07-29 | 2014-08-05 |  | Y
Central Hudson |  | Hudson Solar | CH-01223 | Kingston | Stone Ridge |  | 12484 | G | 3023 | High Falls | TBD |  | 6 | [13 empty] | NM | N | POWERONE PVI-6000 | 2014-06-19 | 2014-06-19 | 0 | 2014-06-19 | [17 empty] | W
Central Hudson |  | Hudson Solar | CH-02460 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7056 | Rhinebeck | N | CH-02276 | 8 | [13 empty] | NM | N | SMA SB4000 (2) | 2014-06-19 | 2014-06-26 | 5 | 2014-06-26 | [8 empty] | 350 | 350 |  |  |  |  | 2015-07-09 | 2015-07-16 |  | Y
Central Hudson |  | SolarCity | CH-06006 | Fishkill | Wappingers Falls | Dutchess | 12590 | G | 8091 | Fishkill Plains | N |  | 9.8 | [13 empty] | NM | N | (1) SOLAREDGE SE6000A-US & (1) SOLAREDGE SE3800A-US | 2014-06-11 | 2014-06-19 | 6 | 2014-06-19 | [14 empty] | 2014-08-19 | 2014-08-21 |  | Y
Central Hudson |  | Sungevity Inc | CH-09215 | Fishkill | Cold Spg | Putnam | 10516 | G | 8086 | Tioronda | N |  | 5 | [13 empty] | NM | N | SMA AMERICA SB5000TL-US-22 | 2014-06-11 | 2014-06-17 | 4 | 2014-06-17 | [14 empty] | 2014-08-20 | 2014-08-25 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03682 | Newburgh | New Paltz | Ulster | 12561 | G | 5031 | Galeville | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE7600A | 2014-06-12 | 2014-06-23 | 7 | 2014-06-23 | [14 empty] | 2014-09-12 | 2014-09-19 |  | Y
Central Hudson |  | NRG Home Solar | CH-04136 | Newburgh | Marlboro | Ulster | 12542 | G | 5002 | Marlboro | N |  | 7.955 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (37) | 2014-06-12 | 2014-06-23 | 7 | 2014-06-23 | [14 empty] | 2014-07-16 | 2014-07-23 |  | Y
Central Hudson |  | Hudson Solar | CH-01898 | Poughkeepsie | Standfordville |  | 12581 | G | 7061 | Milan | TBD |  | 8 | [13 empty] | NM | N | SMA AMERICA 8000 | 2014-06-12 | 2014-06-23 | 7 | 2014-06-23 | [17 empty] | W
Central Hudson |  | Hudson Solar | CH-02133 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7053 | Rhinebeck | N |  | 14 | [13 empty] | NM | N | SMA AMERICA 9000 & SMA AMERICA 5000 | 2014-06-19 | 2014-06-23 | 2 | 2014-06-23 | [8 empty] | 350 | 350 |  |  |  |  | 2014-09-05 | 2014-09-11 |  | Y
Central Hudson |  | SolarCity | CH-05497 | Catskill | Hunter | Greene | 12442 | E | 2389 | Vinegar Hill | N |  | 11 | [13 empty] | NM | N | SOLAREDGE SE5000A-US (1) SOLAREDGE SE6000A-US (2) | 2014-06-12 | 2014-06-18 | 4 | 2014-06-18 | [14 empty] | 2014-09-09 | 2014-09-16 |  | Y
Central Hudson |  | SolarCity | CH-05617 | Kingston | High Fls |  | 12440 | G | 3024 | High Falls | TBD |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A-US | 2014-06-12 | 2014-06-18 | 4 | 2014-06-18 | [17 empty] | W
Central Hudson |  | SolarCity | CH-05854 | Poughkeepsie | Staatsburg | Dutchess | 12580 | G | 7041 | Staatsburg | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A-US | 2014-06-12 | 2014-06-23 | 7 | 2014-06-23 | [14 empty] | 2014-09-19 | 2014-09-26 |  | Y
Central Hudson |  | SolarCity | CH-05865 | Poughkeepsie | Staatsburg | Dutchess | 12580 | G | 7041 | Staatsburg | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A-US | 2014-06-23 | 2014-06-30 | 5 | 2014-06-30 | [14 empty] | 2014-09-09 | 2014-09-15 |  | Y
Central Hudson |  | SolarCity | CH-06030 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8024 | Knapps Corners | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A-US | 2014-06-12 | 2014-06-23 | 7 | 2014-06-23 | [14 empty] | 2014-07-31 | 2014-08-07 |  | Y
Central Hudson |  | SolarCity | CH-06038 | Fishkill | Poughkeepsie | Dutchess | 12603 | G | 8024 | Knapps Corners | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A-US | 2014-06-12 | 2014-06-23 | 7 | 2014-06-23 | [14 empty] | 2014-07-28 | 2014-08-04 |  | Y
Central Hudson |  | SolarCity | CH-06082 | Fishkill | Fishkill | Dutchess | 12524 | G | 8094 | Fishkill Plains | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE3800A-US (2) | 2014-06-12 | 2014-06-23 | 7 | 2014-06-23 | [14 empty] | 2014-10-13 | 2014-10-20 |  | Y
Central Hudson |  | SolarCity | CH-06348 | Newburgh | Wallkill | Ulster | 12589 | G | 5043 | East Walden | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE3800A-US (1) SOLAREDGE SE3800A-US (2) | 2014-06-12 | 2014-06-18 | 4 | 2014-06-18 | [14 empty] | 2014-11-05 | 2014-11-10 |  | Y
Central Hudson |  | SolarCity | CH-06598 | Kingston | Kingston | Ulster | 12401 | G | 2013 | Lincoln Park | N |  | 3.8 | [13 empty] | NM | N | SOLAREDGE SE3800A-US | 2014-06-12 | 2014-06-18 | 4 | 2014-06-18 | [14 empty] | 2014-08-18 | 2014-08-26 |  | Y
Central Hudson |  | SolarCity | CH-07332 | Newburgh | Highland | Ulster | 12528 | G | 5082 | Highland | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A-US | 2014-06-12 | 2014-06-19 | 5 | 2014-06-19 | [14 empty] | 2014-08-26 | 2014-09-03 |  | Y
Central Hudson |  | SolarCity | CH-07541 | Poughkeepsie | Lagrangeville | Dutchess | 12540 | G | 6055 | Todd Hill | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A-US | 2014-06-12 | 2014-06-23 | 7 | 2014-06-23 | [14 empty] | 2014-09-17 | 2014-09-24 |  | Y
Central Hudson |  | SolarCity | CH-07599 | Newburgh | Newburgh |  | 12550 | G | 4051 | Union Ave | TBD |  | 3 | [13 empty] | NM | N | SOLAREDGE SE3000A-US | 2014-06-12 | 2014-06-23 | 7 | 2014-06-23 | [17 empty] | W
Central Hudson |  | Sungevity Inc | CH-09230 | Poughkeepsie | Pleasant Valley | Dutchess | 12569 | G | 6051 | Todd Hill | N |  | 14 | [13 empty] | NM | N | (2) SMA AMERICA SB7000US-12 | 2014-06-20 | 2014-06-20 | 0 | 2014-06-20 | [14 empty] | 2014-07-17 | 2014-07-24 |  | Y
Central Hudson |  | Sungevity Inc | CH-09265 | Catskill | W Coxsackie | Greene | 12192 | G | 1076 | Coxsackie | N | CH-09265 | 6.8 | [13 empty] | NM | N | POWER-ONE PVI-3.8-OUTD-US-A POWER-ONE PVI-3.0-OUTD-US-A (2) | 2014-06-12 | 2014-06-18 | 4 | 2014-06-18 | [14 empty] | 2014-09-18 | 2014-09-25 |  | Y
Central Hudson |  | Sungevity Inc | CH-09284 | Kingston | Kingston | Ulster | 12401 | G | 2017 | Lincoln Park | N |  | 7 | [13 empty] | NM | N | SMA AMERICA SB7000US-12 | 2014-06-12 | 2014-06-18 | 4 | 2014-06-18 | [14 empty] | 2014-09-12 | 2014-09-18 |  | Y
Central Hudson |  | Sungevity Inc | CH-09524 | Kingston | Saugerties | Ulster | 12477 | G | 2015 | Lincoln Park | N |  | 7 | [13 empty] | NM | N | SMA AMERICA SB7000US-12 | 2014-06-12 | 2014-06-18 | 4 | 2014-06-18 | [14 empty] | 2014-08-14 | 2014-08-20 |  | Y
Central Hudson |  | NRG Home Solar | CH-04122 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 7025 | Tinkertown | N | CH-04122 | 7.095 | [13 empty] | NM | N | ENPHASE ENERGY M-215-60-2LL-S22-IG (33) | 2014-06-13 | 2014-06-26 | 9 | 2014-06-26 | [14 empty] | 2014-11-04 | 2014-11-10 |  | Y
Central Hudson |  | Hudson Solar | CH-01690 | Kingston | Boicevl | Ulster | 12412 | G | 3011 | Woodstock | N |  | 6 | [13 empty] | NM | N | SMA AMERICA6000 (1) | 2014-06-13 | 2014-06-26 | 9 | 2014-06-26 | [14 empty] | 2014-08-15 | 2014-08-21 |  | Y
Central Hudson |  | HUDSON SOLAR | CH-02007 | Catskill | Haines Fls | Greene | 12436 | G | 2385 | Lawrenceville | N |  | 8 | [13 empty] | NM | N | SMA AMERICA 4000 (1) SMA AMERICA 4000 (2) | 2014-06-13 | 2014-06-26 | 9 | 2014-06-26 | [14 empty] | 2014-08-05 | 2014-08-12 |  | Y
Central Hudson |  | SolarCity | CH-04950 | Newburgh | Wallkill | Ulster | 12589 | G | 4011 | West Balmville | N |  | 8 | [13 empty] | NM | N | SOLAREDGE SE3000A-US (1) SOLAREDGE SE5000A-US (1) | 2014-06-13 | 2014-06-25 | 8 | 2014-06-25 | [14 empty] | 2014-08-25 | 2014-09-02 |  | Y
Central Hudson |  | SolarCity | CH-05253 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6005 | Reynolds Hill | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A-US (1) | 2014-06-13 | 2014-06-26 | 9 | 2014-06-26 | [14 empty] | 2014-11-07 | 2014-11-14 |  | Y
Central Hudson |  | SolarCity | CH-05485 | Catskill | Catskill | Greene | 12414 | G | 2001 | North Catskill | N |  | 5 | [13 empty] | NM | N | POWERONE PVI-5000-OUTD-US (1) | 2014-06-13 | 2014-06-25 | 8 | 2014-06-25 | [8 empty] | 350 | 350 |  |  |  |  | 2014-10-28 | 2014-10-30 |  | Y
Central Hudson |  | SolarCity | CH-05524 | Catskill | E Durham |  | 12423 | G | 1092 | Westerlo | TBD |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A-US | 2014-06-13 | 2014-06-20 | 5 | 2014-06-20 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | SolarCity | CH-05604 | Catskill | Ravena | Albany | 12143 | G | 1083 | New Baltimore | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE3800A-US (2) | 2014-06-13 | 2014-06-25 | 8 | 2014-06-25 | [14 empty] | 2015-02-23 | 2015-03-02 |  | Y
Central Hudson |  | SolarCity | CH-05644 | Kingston | Rosendale | Ulster | 12472 | G | 1011 | Boulevard | N |  | 3 | [13 empty] | NM | N | SOLAREDGE SE3000A-US (1) | 2014-06-13 | 2014-06-25 | 8 | 2014-06-25 | [14 empty] | 2014-09-22 | 2014-09-29 |  | Y
Central Hudson |  | SolarCity | CH-05751 | Kingston | Saugerties | Ulster | 12477 | G | 3005 | Saugerties | N |  | 10 | [13 empty] | NM | N | SOLAREDGE SE5000A-US (2) | 2014-06-13 | 2014-06-25 | 8 | 2014-06-25 | [14 empty] | 2014-08-19 | 2014-08-26 |  | Y
Central Hudson |  | SolarCity | CH-05779 | Poughkeepsie | Poughkeepsie |  | 12603 | G | 6046 | Spackenkill | TBD |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A-US (1) | 2014-06-13 | 2014-06-26 | 9 | 2014-06-26 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | SolarCity | CH-05785 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6095 | Manchester | N |  | 8 | [13 empty] | NM | N | SOLAREDGE SE3000A-US & SOLAREDGE SE5000A-US | 2014-07-28 | 2014-08-04 | 5 | 2014-08-04 | [14 empty] | 2014-11-13 | 2014-11-19 |  | Y
Central Hudson |  | SolarCity | CH-05866 | Poughkeepsie | Staatsburg | Dutchess | 12580 | G | 7041 | Staatsburg | N |  | 20 | [13 empty] | NM | N | FRONIUS IG PPLUS A 10.0 (2) | 2014-06-13 | 2014-06-25 | 8 | 2014-06-25 | [8 empty] | 350 | 350 |  |  |  |  | 2014-10-08 | 2014-10-08 |  | Y
Central Hudson |  | SolarCity | CH-05908 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6056 | Todd Hill | N |  | 3 | [13 empty] | NM | N | SOLAREDGE SE3000A-US | 2014-06-13 | 2014-06-24 | 7 | 2014-06-24 | [14 empty] | 2014-07-24 | 2014-07-31 |  | Y
Central Hudson |  | SolarCity | CH-06108 | Fishkill | Beacon | Dutchess | 12508 | G | 8017 | Forgebrook | N |  | 3 | [13 empty] | NM | N | SOLAREDGE SE3000A-US (1) | 2014-06-13 | 2014-06-26 | 9 | 2014-06-26 | [14 empty] | 2014-10-10 | 2014-10-16 |  | Y
Central Hudson |  | SolarCity | CH-06129 | Fishkill | Stormvl | Dutchess | 12582 | G | 8093 | Fishkill Plains | N |  | 11 | [13 empty] | NM | N | SOLAREDGE SE5000A-US (1) SOLAREDGE SE6000A-US (1) | 2014-06-13 | 2014-06-26 | 9 | 2014-06-26 | [14 empty] | 2014-09-22 | 2014-09-29 |  | Y
Central Hudson |  | SolarCity | CH-06214 | Newburgh | Newburgh | Orange | 12550 | G | 4024 | Coldenham | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A-US (1) | 2014-06-13 | 2014-06-25 | 8 | 2014-06-25 | [14 empty] | 2014-11-04 | 2014-11-07 |  | Y
Central Hudson |  | SolarCity | CH-06394 | Newburgh | Cornwall-Hdsn | Orange | 12520 | G | 4043 | Union Ave | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A-US | 2014-06-23 | 2014-06-30 | 5 | 2014-06-30 | [14 empty] | 2014-08-27 | 2014-09-04 |  | Y
Central Hudson |  | SolarCity | CH-06462 | Catskill | Climax | Greene | 12042 | G | 2061 | Freehold | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A-US (1) | 2014-06-13 | 2014-06-25 | 8 | 2014-06-25 | [14 empty] | 2014-07-30 | 2014-08-06 |  | Y
Central Hudson |  | SolarCity | CH-06593 | Kingston | Kingston | Ulster | 12401 | G | 2014 | Lincoln Park | N |  | 6.8 | [13 empty] | NM | N | SOLAREDGE SE3800A-US (1) SOLAREDGE SE3000A-US (1) | 2014-06-13 | 2014-06-25 | 8 | 2014-06-25 | [14 empty] | 2014-10-20 | 2014-10-27 |  | Y
Central Hudson |  | SolarCity | CH-06600 | Kingston | Kingston | Ulster | 12401 | G | 2012 | Lincoln Park | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A-US | 2014-09-09 | 2014-09-12 | 3 | 2014-09-12 | [14 empty] | 2014-09-22 | 2014-09-29 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06710 | Poughkeepsie | Lagrangevl | Dutchess | 12540 | G | 6053 | Todd Hill | N |  | 8.8 | [13 empty] | NM | N | SOLAREDGE SE5000A-US (1) SOLAREDGE SE3800A-US (1) | 2014-06-13 | 2014-06-26 | 9 | 2014-06-26 | [14 empty] | 2014-09-08 | 2014-09-11 |  | Y
Central Hudson |  | SolarCity | CH-06857 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8092 | Fishkill Plains | N |  | 3.8 | [13 empty] | NM | N | SOLAREDGE SE3800A-US | 2014-06-13 | 2014-06-26 | 9 | 2014-06-26 | [14 empty] | 2014-09-05 | 2014-09-11 |  | Y
Central Hudson |  | SolarCity | CH-07181 | Catskill | Catskill | Greene | 12414 | G | 2001 | North Catskill | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A-US (1) | 2014-06-13 | 2014-06-25 | 8 | 2014-06-25 | [14 empty] | 2014-10-28 | 2014-10-30 |  | Y
Central Hudson |  | SolarCity | CH-07372 | Fishkill | Beacon | Dutchess | 12508 | G | 8015 | Forgebrook | N |  | 3.8 | [13 empty] | NM | N | SOLAREDGE SE3800A-US (1) | 2014-06-13 | 2014-06-26 | 9 | 2014-06-26 | [14 empty] | 2014-10-10 | 2014-10-16 |  | Y
Central Hudson |  | SolarCity | CH-07544 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6051 | Todd Hill | N |  | 3.8 | [13 empty] | NM | N | SolarEdge SE3800 | 2014-06-23 | 2014-06-30 | 5 | 2014-06-30 | [14 empty] | 2014-12-31 | 2015-01-08 |  | Y
Central Hudson |  | SolarCity | CH-07659 | Fishkill | Wappingers Falls | Dutchess | 12590 | G | 8046 | Myers Corners | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A-US | 2014-06-13 | 2014-06-26 | 9 | 2014-06-26 | [14 empty] | 2014-08-27 | 2014-09-04 |  | Y
Central Hudson |  | SolarCity | CH-07806 | Kingston | Rosendale | Ulster | 12472 | G | 3022 | High Falls | N | CH-05321 | 10 | [13 empty] | NM | N | SOLAREDGE SE5000A-US (2) | 2014-07-15 | 2014-07-22 | 5 | 2014-07-22 | [8 empty] | 350 | 350 |  |  |  |  | 2014-11-24 | 2014-11-24 |  | Y
Central Hudson |  | SolarCity | CH-07852 | Kingston | Cottekill |  | 12419 | G | 3021 | High Falls | TBD |  | 3 | [13 empty] | NM | N | POWERONE PVI-3.0-OUTD-S-US | 2014-06-13 | 2014-06-20 | 5 | 2014-06-20 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | SolarCity | CH-07881 | Poughkeepsie | Poughkeepsie |  | 12603 | G | 6051 | Todd Hill | TBD |  | 8.8 | [13 empty] | NM | N | SOLAREDGE SE5000A-US & SOLAREDGE SE3800A-US | 2014-10-14 | 2014-10-21 | 5 | 2014-10-21 | [17 empty] | W
Central Hudson |  | SolarCity | CH-07907 | Newburgh | New Windsor |  | 12553 | G | 4042 | Union Ave | TBD |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A-US | 2014-06-13 | 2014-06-26 | 9 | 2014-06-26 | [17 empty] | W
Central Hudson |  | NRG Home Solar | CH-04696 | Poughkeepsie | Poughkeepsie |  | 12603 | G | 6045 | Spackenkill | N |  | 5.59 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (26) | 2014-06-16 | 2014-06-23 | 5 | 2014-06-23 | [14 empty] | 2014-09-16 | 2014-09-23 |  | W
Central Hudson |  | NRG Home Solar | CH-04778 | Newburgh | New Windsor | Orange | 12553 | G | 4044 | Union Ave | N |  | 4.945 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (23) | 2014-06-23 | 2014-06-30 | 5 | 2014-06-30 | [14 empty] | 2014-09-09 | 2014-09-15 |  | Y
Central Hudson |  | NRG Home Solar | CH-04780 | Newburgh | Cornwall-Hdsn |  | 12520 | G | 4043 | Union Ave | TBD |  | 8.385 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (39) | 2014-06-16 | 2014-06-23 | 5 | 2014-06-23 | [17 empty] | W
Central Hudson |  | NRG Home Solar | CH-04788 | Newburgh | Clintondale | Ulster | 12515 | G | 5012 | Modena | N |  | 2.795 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (13) | 2014-06-16 | 2014-06-23 | 5 | 2014-06-23 | [14 empty] | 2014-08-26 | 2014-09-03 |  | Y
Central Hudson |  | GAF Solar | CH-01129 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 6062 | Inwood Ave | N |  | 6.02 | [13 empty] | NM | N | ENPHASE ENERGY M215 (28) | 2014-06-18 | 2014-06-24 | 4 | 2014-06-24 | [14 empty] | 2014-11-14 | 2014-11-19 |  | Y
Central Hudson |  | Sungevity Inc | CH-09268 | Kingston | Kerhonkson | Ulster | 12446 | G | 3082 | Kerhonkson | N |  | 8 | [13 empty] | NM | N | SMA AMERICA SB8000US-12 | 2014-06-24 | 2014-07-01 | 5 | 2014-07-01 | [14 empty] | 2014-11-10 | 2014-11-17 |  | Y
Central Hudson |  | Sungevity Inc | CH-09291 | Kingston | Kingston | Ulster | 12401 | G | 2093 | Hurley Ave | N |  | 6 | [13 empty] | NM | N | SMA AMERICA SB3000TL-US-22 (1) SMA AMERICA SB3000TL-US-22 (2) | 2014-06-16 | 2014-06-23 | 5 | 2014-06-23 | [14 empty] | 2014-07-22 | 2014-07-22 |  | Y
Central Hudson |  | SolarCity | CH-05340 | Newburgh | Walden | Orange | 12586 | G | 5043 | East Walden | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE3800A-US (2) | 2014-06-26 | 2014-07-07 | 6 | 2014-07-07 | [14 empty] | 2014-09-22 | 2014-09-25 |  | Y
Central Hudson |  | SolarCity | CH-06066 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8092 | Fishkill Plains | N | CH-06066 | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A-US | 2014-06-17 | 2014-06-24 | 5 | 2014-06-24 | [14 empty] | 2014-08-11 | 2014-08-14 |  | Y
Central Hudson |  | SolarCity | CH-07627 | Catskill | Coxsackie | Greene | 12051 | G | 1072 | Coxsackie | N |  | 12 | [13 empty] | NM | N | (2) SOLAREDGE SE6000A-US | 2014-06-17 | 2014-06-24 | 5 | 2014-06-24 | [14 empty] | 2014-07-15 | 2014-07-15 |  | Y
Central Hudson |  | NRG Home Solar | CH-04328 | Poughkeepsie | Lagrangevl | Dutchess | 12540 | G | 6057 | Todd Hill | N |  | 6.02 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (28) | 2014-06-18 | 2014-06-25 | 5 | 2014-06-25 | [14 empty] | 2014-09-25 | 2014-10-02 |  | Y
Central Hudson |  | SolarCity | CH-06074 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8092 | Fishkill Plains | N |  | 6.8 | [13 empty] | NM | N | 1 -SOLAREDGE SE3000A-US 1 -SOLAREDGE SE3800A-US | 2014-06-18 | 2014-06-26 | 6 | 2014-06-26 | [14 empty] | 2014-09-08 | 2014-09-11 |  | Y
Central Hudson |  | Self | CH-08885 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 6068 | Inwood Ave | N |  | 6 | [13 empty] | NM | N | SMA SunnyBoy 6000US | 2014-07-08 | 2014-07-15 | 5 | 2014-07-15 | [14 empty] | 2014-07-18 | 2014-07-21 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Kirchhoff Green Energy LLC | CH-03544 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6043 | Spackenkill | N |  | 10 | [13 empty] | NM | N | FRONIUS 10.0-1 | 2014-07-01 | 2014-07-09 | 5 | 2014-07-09 | [14 empty] | 2014-11-07 | 2014-11-14 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03589 | Newburgh | New Paltz | Ulster | 12561 | G | 5011 | Modena | N |  | 10 | [13 empty] | NM | N | SOLAREDGE10000A-UA | 2014-06-19 | 2014-06-26 | 5 | 2014-06-26 | [14 empty] | 2014-09-26 | 2014-10-02 |  | Y
Central Hudson |  | Lotus Energy Inc. | CH-03850 | Catskill | Medusa | Albany | 12120 | G | 1092 | Westerlo | N |  | 5 | [13 empty] | NM | N | SMA 5000 | 2014-06-19 | 2014-06-26 | 5 | 2014-06-26 | [14 empty] | 2014-08-11 | 2014-08-18 |  | Y
Central Hudson |  | NRG Home Solar | CH-04464 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 4.085 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (19) | 2014-06-19 | 2014-06-26 | 5 | 2014-06-26 | [14 empty] | 2014-09-16 | 2014-09-22 |  | Y
Central Hudson |  | Novel Approaches | CH-02782 | Kingston | Ellenville | Ulster | 12428 | G | 3076 | Greenfield Rd | N |  | 13.6 | [13 empty] | NM | N | SOLAR EDGE SE6000-US SOLAR EDGE SE7600A-US | 2014-06-19 | 2014-07-03 | 10 | 2014-07-03 | [14 empty] | 2014-08-11 | 2014-08-18 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-03406 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8091 | Fishkill Plains | N |  | 12 | [13 empty] | NM | N | SMA AMERICA SB6000 (2) | 2014-06-20 | 2014-06-30 | 6 | 2014-06-30 | [14 empty] | 2014-10-15 | 2014-10-20 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-03412 | Newburgh | New Windsor | Orange | 12553 | G | 4054 | Union Ave | N |  | 8 | [13 empty] | NM | N | POWERONE PVI 3.0 US (1) POWERONE PVI 5000 US (1) | 2014-06-20 | 2014-06-30 | 6 | 2014-06-30 | [14 empty] | 2014-08-25 | 2014-09-02 |  | Y
Central Hudson |  | NRG Home Solar | CH-04148 | Fishkill | Cold Spg | Putnam | 10516 | G | 8087 | Tioronda | N | CH-04148 | 7.74 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (36) | 2014-07-15 | 2014-07-22 | 5 | 2014-07-22 | [14 empty] | 2014-10-10 | 2014-10-16 |  | Y
Central Hudson |  | NRG Home Solar | CH-04612 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8056 | North Chelsea | N |  | 6.45 | [13 empty] | NM | N | ENPHASE ENERGY M-215-60-2LL-S22-IG (30) | 2014-06-20 | 2014-06-30 | 6 | 2014-06-30 | [14 empty] | 2014-08-13 | 2014-08-15 |  | Y
Central Hudson |  | Direct Energy Solar | CH-01072 | Catskill | Preston Holw | Albany | 12469 | G | 1092 | Westerlo | N | CH-00886 | 4.945 | [13 empty] | RNM | N | ENPHASE ENERGY M215 (23) | 2014-07-03 | 2014-07-11 | 5 | 2014-07-11 | [14 empty] | 2014-08-19 | 2014-08-28 |  | Y
Central Hudson |  | Verengo Solar | CH-09785 | Newburgh | Newburgh | Orange | 12550 | G | 4014 | West Balmville | N |  | 5 | [13 empty] | NM | N | POWERONE PVI-5000 (1) | 2014-06-20 | 2014-06-30 | 6 | 2014-06-30 | [14 empty] | 2014-08-18 | 2014-08-19 |  | Y
Central Hudson |  | Verengo Solar | CH-09822 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 7 | [13 empty] | NM | N | SMA AMERICA SB4000 & SMA AMERICA SB3000 | 2014-06-30 | 2014-07-08 | 5 | 2014-07-08 | [14 empty] | 2014-08-21 | 2014-08-28 |  | Y
Central Hudson |  | Verengo Solar | CH-09890 | Newburgh | New Windsor | Orange | 12553 | G | 4094 | Bethlehem Rd | N |  | 5.49 | [13 empty] | NM | N | POWERONE PVI-5000 (1) | 2014-06-20 | 2014-06-30 | 6 | 2014-06-30 | [14 empty] | 2014-09-05 | 2014-09-11 |  | Y
Central Hudson |  | NRG Home Solar | CH-04112 | Newburgh | Salisbury Mls | Orange | 12577 | G | 4095 | Bethlehem Rd | N |  | 8.81 | [13 empty] | NM | N | ENPHASE ENERGY M-215-60-2LL-S22-IG (41) | 2014-06-23 | 2014-06-30 | 5 | 2014-06-30 | [14 empty] | 2014-08-15 | 2014-08-15 |  | Y
Central Hudson |  | NRG Home Solar | CH-04210 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6093 | Manchester | N |  | 5.16 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (24) | 2014-07-03 | 2014-07-11 | 5 | 2014-07-11 | [14 empty] | 2014-08-13 | 2014-08-15 |  | Y
Central Hudson |  | NRG Home Solar | CH-04269 | Kingston | Hurley |  | 12443 | G | 2094 | Hurley Ave | TBD |  | 6.45 | [13 empty] | NM | N | ENPHASE ENERGY M-215-60-2LL-S22-IG (30) | 2014-06-23 | 2014-06-30 | 5 | 2014-06-30 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | NRG Home Solar | CH-04287 | Kingston | Saugerties | Ulster | 12477 | G | 3004 | Saugerties | N |  | 4.73 | [13 empty] | NM | N | ENPHASE ENERGY M-215-60-2LL-S22-IG (22) | 2014-06-23 | 2014-06-30 | 5 | 2014-06-30 | [14 empty] | 2014-08-13 | 2014-08-20 |  | Y
Central Hudson |  | NRG Home Solar | CH-04408 | Fishkill | Fishkill |  | 12524 | G | 8094 | Fishkill Plains | TBD |  | 3.22 | [13 empty] | NM | N | ENPHASE ENERGY M-215-60-2LL-S22-IG (15) | 2014-06-23 | 2014-07-01 | 6 | 2014-07-01 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | NRG Home Solar | CH-04621 | Fishkill | Beacon | Dutchess | 12508 | G | 8085 | Tioronda | N |  | 3.01 | [13 empty] | NM | N | ENPHASE ENERGY M-215-60-2LL-S22-IG (14) | 2014-06-23 | 2014-07-01 | 6 | 2014-07-01 | [14 empty] | 2014-10-15 | 2014-10-21 |  | Y
Central Hudson |  | Sungevity Inc | CH-09586 | Poughkeepsie | Ancramdale | Columbia | 12503 | G | 7085 | Ancram | N | CH-09586 | 3.8 | [13 empty] | NM | N | SMA AMERICA SB3800TL-US-22 (1) | 2014-06-23 | 2014-06-30 | 5 | 2014-06-30 | [14 empty] | 2014-09-04 | 2014-09-11 |  | Y
Central Hudson |  | Verengo Solar | CH-09878 | Newburgh | Newburgh |  | 12550 | G | 4045 | Union Ave | TBD |  | 5.25 | [13 empty] | NM | N | ENPHASE ENERGY M215 (24) | 2014-07-09 | 2014-07-17 | 6 | 2014-07-17 | [17 empty] | W
Central Hudson |  | Verengo Solar | CH-09893 | Newburgh | New Windsor | Orange | 12553 | G | 4095 | Bethlehem Rd | N |  | 6.11 | [13 empty] | NM | N | ENPHASE ENERGY M215 (28) | 2014-07-09 | 2014-07-17 | 6 | 2014-07-17 | [14 empty] | 2014-10-06 | 2014-10-09 |  | Y
Central Hudson |  | Verengo Solar | CH-09906 | Newburgh | Newburgh | Orange | 12550 | G | 4045 | Union Ave | N |  | 5.46 | [13 empty] | NM | N | ENPHASE ENERGY M215 (25) | 2014-07-09 | 2014-07-16 | 5 | 2014-07-16 | [14 empty] | 2014-12-22 | 2014-12-30 |  | Y
Central Hudson |  | Verengo Solar | CH-09937 | Newburgh | New Windsor |  | 12553 | G | 4094 | Bethlehem Rd | TBD |  | 7.43 | [13 empty] | NM | N | ENPHASE ENERGY M215 60-2LL-S2X (34) | 2014-07-09 | 2014-07-17 | 6 | 2014-07-17 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | NRG Home Solar | CH-04703 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 6075 | East Park | N |  | 5.16 | [13 empty] | NM | N | ENPHASE ENERGY M215 (24) | 2014-06-24 | 2014-07-01 | 5 | 2014-07-01 | [14 empty] | 2014-11-04 | 2014-11-10 |  | Y
Central Hudson |  | SolarCity | CH-06016 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8091 | Fishkill Plains | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A-US | 2014-06-24 | 2014-07-01 | 5 | 2014-07-01 | [14 empty] | 2014-07-22 | 2014-07-28 |  | Y
Central Hudson |  | SolarCity | CH-07641 | Kingston | Saugerties | Ulster | 12477 | G | 3003 | Saugerties | N |  | 3 | [13 empty] | NM | N | SOLAREDGE SE3000A-US | 2014-06-24 | 2014-07-01 | 5 | 2014-07-01 | [14 empty] | 2014-08-19 | 2014-08-26 |  | Y
Central Hudson |  | Sungevity Inc | CH-09465 | Newburgh | New Paltz | Ulster | 12561 | G | 5021 | Ohioville | N |  | 6 | [13 empty] | NM | N | SMA AMERICA SB6000TL-US-22 | 2014-06-24 | 2014-07-01 | 5 | 2014-07-01 | [14 empty] | 2014-08-12 | 2014-08-14 |  | Y
Central Hudson |  | Verengo Solar | CH-09753 | Newburgh | Washingtonvl | Orange | 10992 | G | 4097 | Bethlehem Rd | N |  | 6.665 | [13 empty] | NM | N | ENPHASE ENERGY M215 (31) | 2014-07-09 | 2014-07-17 | 6 | 2014-07-17 | [14 empty] | 2014-10-06 | 2014-10-09 |  | Y
Central Hudson |  | Verengo Solar | CH-09759 | Newburgh | Wallkill | Ulster | 12589 | G | 5043 | East Walden | N |  | 2.58 | [13 empty] | NM | N | ENPHASE ENERGY M215 (12) | 2014-07-09 | 2014-07-17 | 6 | 2014-07-17 | [14 empty] | 2014-10-20 | 2014-10-24 |  | Y
Central Hudson |  | Verengo Solar | CH-09820 | Newburgh | New Windsor | Orange | 12553 | G | 4045 | Union Ave | N |  | 6.235 | [13 empty] | NM | N | ENPHASE ENERGY M215 (29) | 2014-07-09 | 2014-07-17 | 6 | 2014-07-17 | [14 empty] | 2014-09-26 | 2014-10-02 |  | Y
Central Hudson |  | Verengo Solar | CH-09907 | Newburgh | Newburgh | Orange | 12550 | G | 5004 | Marlboro | N |  | 8.6 | [13 empty] | NM | N | ENPHASE ENERGY M215 (40) | 2014-07-09 | 2014-07-17 | 6 | 2014-07-17 | [14 empty] | 2014-09-26 | 2014-10-02 |  | Y
Central Hudson |  | NRG Home Solar | CH-04550 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6046 | Spackenkill | N |  | 9.46 | [13 empty] | NM | N | ENPHASE ENERGY M215 (44) | 2014-06-25 | 2014-07-08 | 8 | 2014-07-08 | [14 empty] | 2014-10-02 | 2014-10-02 |  | Y
Central Hudson |  | NRG Home Solar | CH-04837 | Newburgh | New Windsor |  | 12553 | G | 4045 | Union Ave | TBD |  | 8.6 | [13 empty] | NM | N | ENPHASE ENERGY M215 (40) | 2014-06-25 | 2014-07-02 | 5 | 2014-07-02 | [17 empty] | W |  | Customer already had net meter prior to application. 10/22 - Customer advised will be moving forward with project but with a different contractor.
Central Hudson |  | Autonomous Energies LLC | CH-00749 | Poughkeepsie | Millerton | Dutchess | 12546 | G | 7081 | Millerton | N |  | 4 | [13 empty] | NM | N | SMA SB 4000TL | 2014-07-03 | 2014-07-11 | 5 | 2014-07-11 | [14 empty] | 2014-09-09 | 2014-09-10 |  | Y
Central Hudson |  | Hudson Solar | CH-02418 | Catskill | Greenvl | Greene | 12083 | G | 1091 | Westerlo | N |  | 8 | [13 empty] | NM | N | SMA AMERICA SB8000 | 2014-06-26 | 2014-07-03 | 5 | 2014-07-03 | [14 empty] | 2014-10-13 | 2014-10-20 |  | Y
Central Hudson |  | Sol Providers | CH-08962 | Newburgh | New Paltz | Ulster | 12561 | G | 5024 | Ohioville | N |  | 5.16 | [13 empty] | NM | N | ENPHASE ENERGY M215 (24) | 2014-07-03 | 2014-07-11 | 5 | 2014-07-11 | [14 empty] | 2014-10-09 | 2014-10-15 |  | Y
Central Hudson |  | Sungevity Inc | CH-09394 | Catskill | Medusa | Albany | 12120 | G | 1092 | Westerlo | N |  | 7 | [13 empty] | NM | N | SMA AMERICA SB7000US-12 | 2014-07-07 | 2014-07-14 | 5 | 2014-07-14 | [14 empty] | 2014-09-30 | 2014-10-15 |  | Y
Central Hudson |  | NRG Home Solar | CH-04798 | Newburgh | Maybrook |  | 12543 | G | 5052 | Maybrook | TBD |  | 3.44 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (16) | 2014-07-08 | 2014-07-15 | 5 | 2014-07-15 | [17 empty] | W |  | 7/4/14 Company Holiday.
Central Hudson |  | Hudson Solar | CH-01753 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 6075 | East Park | N |  | 3 | [13 empty] | NM | N | SMA AMERICA 3000 | 2014-07-08 | 2014-07-15 | 5 | 2014-07-15 | [14 empty] | 2014-09-02 | 2014-09-09 |  | Y
Central Hudson |  | Hudson Solar | CH-02257 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7013 | Hibernia | N |  | 8 | [13 empty] | NM | N | SMA AMERICA 4000 (2) | 2014-06-27 | 2014-07-07 | 5 | 2014-07-07 | [14 empty] | 2014-09-04 | 2014-09-11 |  | Y
Central Hudson |  | NRG Home Solar | CH-04585 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8043 | Myers Corners | N |  | 7.095 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (33) | 2014-06-30 | 2014-07-08 | 5 | 2014-07-08 | [14 empty] | 2014-08-13 | 2014-08-15 |  | Y
Central Hudson |  | NRG Home Solar | CH-04636 | Newburgh | Newburgh | Orange | 12550 | G | 4023 | Coldenham | N |  | 3.655 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (17) | 2014-06-30 | 2014-07-08 | 5 | 2014-07-08 | [14 empty] | 2014-08-12 | 2014-08-14 |  | Y
Central Hudson |  | Hudson Solar | CH-01273 | Kingston | Kingston | Ulster | 12401 | G | 2094 | Hurley Ave | N |  | 24 | [13 empty] | NM | N | 4 - SMA AMERICA 6000 | 2014-06-30 | 2014-07-07 | 4 | 2014-07-07 | [14 empty] | 2014-10-17 | 2014-10-24 |  | Y
Central Hudson |  | SolarCity | CH-06296 | Newburgh | Plattekill | Ulster | 12568 | G | 5013 | Modena | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A-US | 2014-06-30 | 2014-07-08 | 5 | 2014-07-08 | [14 empty] | 2014-08-18 | 2014-08-19 |  | Y
Central Hudson |  | Sungevity Inc | CH-09520 | Kingston | Kingston | Ulster | 12401 | G | 2093 | Hurley Ave | N |  | 8 | [13 empty] | NM | N | SMA AMERICA SB8000US-12 | 2014-06-30 | 2014-07-07 | 4 | 2014-07-07 | [14 empty] | 2014-08-28 | 2014-09-05 |  | Y
Central Hudson |  | Kirchhoff Green Energy LLC | CH-03537 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6095 | Manchester | N |  | 11.4 | [13 empty] | NM | N | FRONIUS USA 11.4-1 UNI | 2014-08-11 | 2014-08-11 | 0 | 2014-08-11 | [14 empty] | 2014-10-03 | 2014-10-10 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03593 | Newburgh | New Windsor | Orange | 12553 | G | 4097 | Bethlehem Rd | N |  | 10 | [13 empty] | NM | N | SOLAREDGE SE 10 | 2014-07-01 | 2014-07-15 | 9 | 2014-07-15 | [14 empty] | 2014-10-14 | 2014-10-20 |  | Y
Central Hudson |  | NRG Home Solar | CH-04661 | Newburgh | Wallkill | Ulster | 12589 | G | 5043 | East Walden | N |  | 6.45 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (30) | 2014-07-01 | 2014-07-09 | 5 | 2014-07-09 | [14 empty] | 2014-08-27 | 2014-09-04 |  | Y
Central Hudson |  | Hudson Solar | CH-02407 | Newburgh | New Paltz | Ulster | 12561 | G | 5031 | Galeville | N |  | 21 | [13 empty] | NM | N | SMA AMERICA SB10000TL-US, SMA AMERICA SB7000TL-US & SMA AMERICA SB4000TL-US | 2014-07-01 | 2014-07-09 | 5 | 2014-07-09 | [14 empty] | 2014-10-29 | 2014-11-03 |  | Y
Central Hudson |  | Hudson Valley Wind Energy, LLC | CH-02550 | Newburgh | Milton | Ulster | 12547 | G | 5003 | Marlboro | N |  | 10 | [13 empty] | NM | N | FRONIUS USA IG PLUS A 10.0-240 | 2014-07-10 | 2014-07-17 | 5 | 2014-07-17 | [8 empty] | 350 | 350 |  |  |  |  | 2014-09-04 | 2014-09-08 |  | Y
Central Hudson |  | Novel Approaches | CH-02776 | Kingston | Grahamsvl | Sullivan | 12740 | G | 3091 | Neversink | N |  | 7.6 | [13 empty] | NM | N | SOLAR EDGE SE7600A-US | 2014-07-01 | 2014-07-09 | 5 | 2014-07-09 | [14 empty] | 2014-08-17 | 2014-08-22 |  | Y
Central Hudson |  | Sungevity Inc | CH-09598 | Kingston | Saugerties | Ulster | 12453 | G | 3004 | Saugerties | N |  | 7.6 | [13 empty] | NM | N | (2) SMA AMERICA SB3800TL-US-22 | 2014-07-01 | 2014-07-08 | 4 | 2014-07-08 | [14 empty] | 2014-10-03 | 2014-10-10 |  | Y
Central Hudson |  | EnterSolar LLC | CH-03358 | Newburgh | New Windsor | Orange | 12553 | G | 4041 | Union Ave | N |  | 224 | [13 empty] | RC | Y | SOLECTRIA PVI 28TLM (18) | 2014-08-11 | 2014-09-02 | 15 | 2014-09-02 | 2014-08-11 | 2014-09-02 | 15 | [5 empty] | 12000 | 11779.03 |  |  |  |  | 2015-12-16 | 2015-12-18 |  | Y | Y
Central Hudson |  | Paradise Energy Solutions LLC | CH-02839 | Kingston | Saugerties | Ulster | 12477 | G | 3003 | Saugerties | N |  | 5 | [13 empty] | NM | N | SOLAR EDGE SE5000A | 2014-07-02 | 2014-07-10 | 5 | 2014-07-10 | [14 empty] | 2014-10-15 | 2014-10-21 |  | Y
Central Hudson |  | SolarCity | CH-07580 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8093 | Fishkill Plains | N |  | 3.8 | [13 empty] | NM | N | SOLAREDGE SE3800A-US | 2014-07-02 | 2014-07-10 | 5 | 2014-07-10 | [14 empty] | 2014-08-19 | 2014-08-21 |  | Y
Central Hudson |  | Sungevity Inc | CH-09521 | Kingston | Kingston | Ulster | 12401 | G | 1003 | Jansen Ave | N |  | 4 | [13 empty] | NM | N | SMA AMERICA SB4000TL-US-22 | 2014-07-02 | 2014-07-10 | 5 | 2014-07-10 | [14 empty] | 2014-10-07 | 2014-10-14 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03796 | Newburgh | New Paltz | Ulster | 12561 | G | 5011 | Modena | N |  | 12 | [13 empty] | NM | N | POWERONE AURORA PVI-6000 (2) | 2014-07-03 | 2014-07-11 | 5 | 2014-07-11 | [14 empty] | 2014-12-31 | 2014-12-31 |  | Y
Central Hudson |  | NRG Home Solar | CH-04435 | Fishkill | Beacon |  | 12508 | G | 8015 | Forgebrook | TBD |  | 7.095 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (33) | 2014-07-23 | 2014-07-28 | 3 | 2014-07-28 | [17 empty] | W |  | Customer already had net meter prior to application. 7/4/14 Company Holiday.
Central Hudson |  | SolarCity | CH-05194 | Fishkill | Hopewell Jct |  | 12533 | G | 8071 | Shenandoah | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A-US | 2014-07-03 | 2014-07-11 | 5 | 2014-07-11 | [14 empty] | 2014-09-22 | 2014-09-25 |  | W
Central Hudson |  | SolarCity | CH-06752 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6092 | Manchester | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A-US | 2014-07-03 | 2014-07-11 | 5 | 2014-07-11 | [14 empty] | 2014-07-30 | 2014-08-06 |  | Y
Central Hudson |  | SolarCity | CH-07408 | Newburgh | Gardiner | Ulster | 12525 | G | 5031 | Galeville | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A-US | 2014-07-03 | 2014-07-11 | 5 | 2014-07-11 | [14 empty] | 2014-07-22 | 2014-07-28 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Solar Generation | CH-08304 | Kingston | Hurley | Ulster | 12443 | G | 2094 | Hurley Ave | N | CH-08115 | 5 | [13 empty] | NM | N | SMA SB5000TL-US | 2014-07-03 | 2014-07-11 | 5 | 2014-07-11 | [8 empty] | 350 | 350 |  |  |  |  | 2014-09-30 | 2014-09-30 |  | Y
Central Hudson |  | Sungevity Inc | CH-09357 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8054 | North Chelsea | N |  | 7 | [13 empty] | NM | N | SMA AMERICA SB7000US-12 | 2014-07-03 | 2014-07-11 | 5 | 2014-07-11 | [14 empty] | 2014-09-22 | 2014-09-25 |  | Y
Central Hudson |  | SolarCity | CH-07180 | Catskill | Catskill | Greene | 12414 | G | 2004 | North Catskill | N |  | 12 | [13 empty] | NM | N | (2) SOLAREDGE SE6000A-US | 2014-07-07 | 2014-07-14 | 5 | 2014-07-14 | [14 empty] | 2014-10-13 | 2014-10-20 |  | Y
Central Hudson |  | SolarCity | CH-07457 | Newburgh | Milton | Ulster | 12547 | G | 5083 | Highland | N |  | 13.6 | [13 empty] | NM | N | (2) SE38000A-US and (1) SE6000A-US | 2014-09-24 | 2014-10-03 | 7 | 2014-10-03 | [14 empty] | 2014-10-27 | 2014-11-03 |  | Y
Central Hudson |  | SolarCity | CH-07647 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6094 | Manchester | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A-US | 2014-07-07 | 2014-07-14 | 5 | 2014-07-14 | [14 empty] | 2014-08-19 | 2014-08-21 |  | Y
Central Hudson |  | Hudson Solar | CH-01453 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6046 | Spackenkill | N |  | 12 | [13 empty] | NM | N | SMA AMERICA SB6000 (2) | 2014-07-08 | 2014-07-16 | 6 | 2014-07-16 | [14 empty] | 2014-08-20 | 2014-08-25 |  | Y
Central Hudson |  | Hudson Solar | CH-02077 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7013 | Hibernia | N |  | 8 | [13 empty] | NM | N | SMA AMERICA SB8000 | 2014-07-08 | 2014-07-16 | 6 | 2014-07-16 | [14 empty] | 2014-10-03 | 2014-10-10 |  | Y
Central Hudson |  | Hudson Solar | CH-02184 | Fishkill | Fishkill | Dutchess | 12524 | G | 8013 | Forgebrook | N |  | 39 | [13 empty] | NM | N | SMA AMERICA STP24000 & SMA AMERICA SPT15000 | 2014-07-16 | 2014-07-23 | 5 | 2014-07-23 | [14 empty] | 2014-11-14 | 2014-11-24 |  | Y
Central Hudson |  | SolarCity | CH-07109 | Newburgh | Cornwall | Orange | 12518 | G | 4041 | Union Ave | N |  | 11 | [13 empty] | NM | N | SOLAREDGE SE5000A - US & SOLAREDGE SE6000A - US | 2014-07-08 | 2014-07-16 | 6 | 2014-07-16 | [14 empty] | 2014-08-19 | 2014-08-21 |  | Y
Central Hudson |  | Verengo Solar | CH-09936 | Newburgh | Montgomery |  | 12549 | G | 4021 | Coldenham | TBD |  | 4.945 | [13 empty] | NM | N | Enphase Energy M215 (23) | 2014-07-08 | 2014-07-15 | 5 | 2014-07-15 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | Infinity Solar Systems | CH-03494 | Newburgh | Newburgh | Orange | 12550 | G | 4011 | West Balmville | N |  | 7.5 | [13 empty] | NM | N | Fronius 7.5-1 UNI | 2014-07-09 | 2014-07-16 | 5 | 2014-07-16 | [14 empty] | 2014-08-25 | 2014-09-02 |  | Y
Central Hudson |  | Lotus Energy Inc. | CH-03888 | Poughkeepsie | Ancram | Columbia | 12502 | G | 7085 | Ancram | N |  | 5 | [13 empty] | NM | N | SMA SB-5000TL | 2014-07-09 | 2014-07-16 | 5 | 2014-07-16 | [14 empty] | 2014-09-30 | 2014-10-07 |  | Y
Central Hudson |  | NRG Home Solar | CH-04212 | Newburgh | New Paltz | Ulster | 12561 | G | 5022 | Ohioville | N |  | 3.655 | [13 empty] | NM | N | ENPHASE ENERGY M-215-60-2LL-S22-IG (17) | 2014-07-09 | 2014-07-16 | 5 | 2014-07-16 | [14 empty] | 2014-09-23 | 2014-09-26 |  | Y
Central Hudson |  | NRG Home Solar | CH-04525 | Kingston | Woodstock | Ulster | 12498 | G | 3013 | Woodstock | N | CH-04525 | 5.8 | [13 empty] | NM | N | ENPHASE ENERGY M-215-60-2LL-S22-IG (27) | 2014-07-09 | 2014-07-16 | 5 | 2014-07-16 | [14 empty] | 2014-09-19 | 2014-09-26 |  | Y
Central Hudson |  | NRG Home Solar | CH-04789 | Newburgh | Milton |  | 12547 | G | 5002 | Marlboro | TBD |  | 5.59 | [13 empty] | NM | N | ENPHASE ENERGY M-215-60-2LL-S22-IG (26) | 2014-07-09 | 2014-07-16 | 5 | 2014-07-16 | [17 empty] | W
Central Hudson |  | Direct Energy Solar | CH-00875 | Kingston | Saugerties | Ulster | 12477 | G | 3004 | Saugerties | N |  | 10 | [13 empty] | NM | N | ENPHASE M250 60-2LL-S22 (40) | 2014-07-09 | 2014-07-16 | 5 | 2014-07-16 | [14 empty] | 2014-08-05 | 2014-09-22 |  | Y
Central Hudson |  | Hudson Solar | CH-01661 | Kingston | Accord |  | 12404 | G | 3082 | Kerhonkson | TBD |  | 5 | [13 empty] | NM | N | SMA AMERICA 5000 TL-US-22 (1) | 2014-07-09 | 2014-07-16 | 5 | 2014-07-16 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | Hudson Solar | CH-01714 | Kingston | Saugerties | Ulster | 12477 | G | 3002 | Saugerties | N |  | 3.8 | [13 empty] | NM | N | SMA AMERICA SB3800 (1) | 2014-07-09 | 2014-07-16 | 5 | 2014-07-16 | [14 empty] | 2014-10-13 | 2014-10-20 |  | Y
Central Hudson |  | Hudson Solar | CH-01750 | Poughkeepsie | Salt Pt | Dutchess | 12578 | G | 7011 | Hibernia | N | CH-01750 | 6 | [13 empty] | NM | N | SMA AMERICA SB6000 (1) | 2014-07-09 | 2014-07-16 | 5 | 2014-07-16 | [14 empty] | 2014-10-17 | 2014-10-24 |  | Y
Central Hudson |  | Hudson Solar | CH-01922 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8051 | North Chelsea | N |  | 9 | [13 empty] | NM | N | SMA AMERICA SB5000 TL-US-22 & SMA AMERICA SB4000 TL-US-22 | 2014-07-09 | 2014-07-16 | 5 | 2014-07-16 | [14 empty] | 2014-11-10 | 2014-11-12 |  | Y
Central Hudson |  | Hudson Solar | CH-02079 | Poughkeepsie | Salt Pt | Dutchess | 12578 | G | 7011 | Hibernia | N |  | 8 | [13 empty] | NM | N | SMA AMERICA SB4000 (2) | 2014-07-09 | 2014-07-16 | 5 | 2014-07-16 | [14 empty] | 2014-09-10 | 2014-09-17 |  | Y
Central Hudson |  | Hudson Solar | CH-02486 | Newburgh | Newburgh | Orange | 12550 | G | 4015 | West Balmville | N | CH-01960 | 3.8 | [13 empty] | NM | N | SMA AMERICA SB3800 | 2014-07-09 | 2014-07-16 | 5 | 2014-07-16 | [14 empty] | 2014-10-09 | 2014-10-15 |  | W
Central Hudson |  | SolarCity | CH-05567 | Catskill | Westerlo | Albany | 12193 | G | 1091 | Westerlo | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A-US | 2014-07-23 | 2014-07-30 | 5 | 2014-07-30 | [14 empty] | 2014-09-17 | 2014-09-24 |  | Y
Central Hudson |  | SolarCity | CH-05845 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 6073 | East Park | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A-US | 2014-07-09 | 2014-07-16 | 5 | 2014-07-16 | [14 empty] | 2014-09-26 | 2014-10-03 |  | Y
Central Hudson |  | Solar Generation | CH-08096 | Kingston | Saugerties | Ulster | 12477 | G | 3002 | Saugerties | N |  | 10 | [13 empty] | NM | N | SMA SB6000-TL SMA SB4000-TL | 2014-07-09 | 2014-07-16 | 5 | 2014-07-16 | [8 empty] | 350 | 350 |  |  |  |  | 2014-08-28 | 2014-09-05 |  | Y
Central Hudson |  | Sungevity Inc | CH-09175 | Newburgh | Wallkill | Ulster | 12568 | G | 5013 | Modena | N |  | 5 | [13 empty] | NM | N | SMA AMERICA SB5000TL-US-22 (1) | 2014-07-09 | 2014-07-16 | 5 | 2014-07-16 | [14 empty] | 2014-08-26 | 2014-09-03 |  | Y
Central Hudson |  | Sungevity Inc | CH-09190 | Kingston | Lk Katrine | Ulster | 12449 | G | 2011 | Lincoln Park | N |  | 7.6 | [13 empty] | NM | N | SMA AMERICAS SB 3800TL-US-22 (2) | 2014-07-09 | 2014-07-16 | 5 | 2014-07-16 | [14 empty] | 2014-10-02 | 2014-10-09 |  | Y
Central Hudson |  | Sungevity Inc | CH-09210 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 7024 | Tinkertown | N |  | 6 | [13 empty] | NM | N | SMA AMERICA SB6000TL-US-22 | 2014-07-09 | 2014-07-16 | 5 | 2014-07-16 | [14 empty] | 2014-09-16 | 2014-09-23 |  | Y
Central Hudson |  | Sungevity Inc | CH-09223 | Newburgh | Campbell Hall | Orange | 10916 | G | 5051 | Maybrook | N |  | 8.4 | [13 empty] | NM | N | POWER-ONE PVI-4.2-OUTD-S-US-A (2) | 2014-07-09 | 2014-07-16 | 5 | 2014-07-16 | [14 empty] | 2014-09-19 | 2014-09-26 |  | Y
Central Hudson |  | Sungevity Inc | CH-09335 | Newburgh | Highland | Ulster | 12528 | G | 5082 | Highland | N |  | 6 | [13 empty] | NM | N | POWER-ONE PVI-6000-OUTD-US-A | 2014-07-21 | 2014-07-24 | 3 | 2014-07-24 | [14 empty] | 2014-09-23 | 2014-09-29 |  | Y
Central Hudson |  | Sungevity Inc | CH-09400 | Kingston | Olive Brdg | Ulster | 12461 | G | 3023 | High Falls | N |  | 12 | [13 empty] | NM | N | SMA AMERICA SB6000TL-US-22 (2) | 2014-07-09 | 2014-07-19 | 7 | 2014-07-19 | [14 empty] | 2014-10-14 | 2014-10-21 |  | Y
Central Hudson |  | NRG Home Solar | CH-04471 | Newburgh | Wallkill |  | 12589 | G | 4011 | West Balmville | TBD |  | 4.085 | [13 empty] | NM | N | ENPHASE ENERGY M-215-60-2LL-S22-IG (19) | 2014-07-10 | 2014-07-18 | 6 | 2014-07-18 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | Direct Energy Solar | CH-00981 | Kingston | Accord |  | 12404 | G | 3081 | Kerhonkson | TBD |  | 9.89 | [13 empty] | NM | N | ENPHASE M215 60-2LL-S22 (46) | 2014-07-10 | 2014-07-17 | 5 | 2014-07-17 | [8 empty] | 350 | 350 | [7 empty] | W |  | Customer already had net meter prior to application. Transformer upgrade required to accommodate PV installation. Utility System Upgrade Costs TBD.
Central Hudson |  | Direct Energy Solar | CH-01008 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7054 | Rhinebeck | N |  | 5.16 | [13 empty] | NM | N | ENPHASE 215 60-2LL-S22 (24) | 2014-07-18 | 2014-07-24 | 4 | 2014-07-24 | [14 empty] | 2014-08-25 | 2014-09-02 |  | Y
Central Hudson |  | Hudson Solar | CH-01269 | Catskill | Coxsackie | Greene | 12051 | G | 1071 | Coxsackie | N |  | 5 | [13 empty] | NM | N | SMA AMERICA SB5000 TL-US-22 (1) | 2014-07-10 | 2014-07-17 | 5 | 2014-07-17 | [14 empty] | 2014-10-31 | 2014-11-07 |  | Y
Central Hudson |  | Hudson Solar | CH-01545 | Kingston | Kingston | Ulster | 12401 | G | 112 | South Wall St | N |  | 6 | [13 empty] | NM | N | SMA AMERICA SB6000 TL-US-22 | 2014-07-10 | 2014-07-17 | 5 | 2014-07-17 | [14 empty] | 2014-10-17 | 2014-10-24 |  | Y
Central Hudson |  | Hudson Solar | CH-01617 | Catskill | Climax | Greene | 12042 | G | 2061 | Freehold | N |  | 5 | [13 empty] | NM | N | SMA AMERICA SB5000 TL-US-22 (1) | 2014-07-10 | 2014-07-17 | 5 | 2014-07-17 | [14 empty] | 2014-11-10 | 2014-11-17 |  | Y
Central Hudson |  | Hudson Solar | CH-01658 | Kingston | Accord | Ulster | 12404 | G | 3081 | Kerhonkson | N |  | 6.8 | [13 empty] | NM | N | SMA AMERICA SB3800 TL-US (1) SMA AMERICA SB3000 TL-US-22 (1) | 2014-07-10 | 2014-07-17 | 5 | 2014-07-17 | [14 empty] | 2014-11-19 | 2014-11-25 |  | Y
Central Hudson |  | Hudson Solar | CH-02322 | Newburgh | Milton | Ulster | 12547 | G | 5083 | Highland | N |  | 3.8 | [13 empty] | NM | N | SMA AMERICA SB3800 | 2014-07-10 | 2014-07-17 | 5 | 2014-07-17 | [14 empty] | 2014-11-14 | 2014-11-19 |  | Y
Central Hudson |  | Hudson Solar | CH-02493 | Newburgh | Rock Tvrn | Orange | 12575 | G | 4097 | Bethlehem Rd | N | CH-02218 | 4 | [13 empty] | NM | N | SMA AMERICA SB4000 | 2014-07-10 | 2014-07-17 | 5 | 2014-07-17 | [14 empty] | 2014-10-24 | 2014-10-30 |  | Y
Central Hudson |  | Solar Generation | CH-08170 | Kingston | Woodstock | Ulster | 12498 | G | 3013 | Woodstock | N |  | 7.6 | [13 empty] | NM | N | SMA TL US 3.8 (2) | 2014-07-10 | 2014-07-17 | 5 | 2014-07-17 | [14 empty] | 2014-10-21 | 2014-10-27 |  | Y
Central Hudson |  | Solar Generation | CH-08265 | Kingston | Stone Ridge | Ulster | 12484 | G | 3023 | High Falls | N |  | 6.8 | [13 empty] | NM | N | SMA TL US 3.8 (1) SMA TL US 3.0 (1) | 2014-07-10 | 2014-07-17 | 5 | 2014-07-17 | [14 empty] | 2014-09-11 | 2014-09-18 |  | Y
Central Hudson |  | New York State Solar Farm | CH-03944 | Fishkill | Beacon | Dutchess | 12508 | G | 8015 | Forgebrook | N |  | 7.2 | [13 empty] | NM | N | POWERONE PVI 3.0 & POWERONE PVI 4.2 | 2014-07-11 | 2014-07-24 | 9 | 2014-07-24 | [14 empty] | 2014-10-03 | 2014-10-09 |  | Y
Central Hudson |  | New York State Solar Farm | CH-03992 | Newburgh | New Paltz | Ulster | 12561 | G | 5031 | Galeville | N |  | 15 | [13 empty] | NM | N | POWERONE PVI 5.0 (3) | 2014-07-11 | 2014-07-18 | 5 | 2014-07-18 | [14 empty] | 2014-12-19 | 2014-12-30 |  | Y
Central Hudson |  | New York State Solar Farm | CH-04044 | Newburgh | Milton | Ulster | 12547 | G | 5002 | Marlboro | N |  | 8.4 | [13 empty] | NM | N | POWERONE PVI 4.2 (2) | 2014-07-11 | 2014-07-21 | 6 | 2014-07-21 | [14 empty] | 2014-08-13 | 2014-08-15 |  | Y
Central Hudson |  | New York State Solar Farm | CH-04057 | Catskill | Cairo | Greene | 12413 | G | 2042 | South Cairo | N |  | 10 | [13 empty] | NM | N | (2) POWER ONE PVI | 2014-07-11 | 2014-07-18 | 5 | 2014-07-18 | [14 empty] | 2014-09-09 | 2014-09-16 |  | Y
Central Hudson |  | New York State Solar Farm | CH-04077 | Newburgh | Newburgh | Orange | 12550 | G | 4022 | Coldenham | N |  | 4.2 | [13 empty] | NM | N | POWERONE PVI 4.2 | 2014-07-11 | 2014-07-24 | 9 | 2014-07-24 | [14 empty] | 2014-09-09 | 2014-09-11 |  | Y
Central Hudson |  | NRG Home Solar | CH-04437 | Fishkill | Beacon | Dutchess | 12508 | G | 8087 | Tioronda | N |  | 6.235 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (29) | 2014-07-11 | 2014-07-24 | 9 | 2014-07-24 | [14 empty] | 2014-10-02 | 2014-10-08 |  | Y
Central Hudson |  | NRG Home Solar | CH-04538 | Kingston | Lk Katrine | Ulster | 12449 | G | 2016 | Lincoln Park | N |  | 10.32 | [13 empty] | NM | N | (48) ENPHASE ENERGY M-215-60-2LL-S22-IG | 2014-07-11 | 2014-07-18 | 5 | 2014-07-18 | [14 empty] | 2014-09-25 | 2014-10-02 |  | Y
Central Hudson |  | Paradise Energy Solutions LLC | CH-02833 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 7041 | Staatsburg | N |  | 20 | [13 empty] | NM | N | SOLAREDGE SE 10000A (2) | 2014-07-11 | 2014-07-24 | 9 | 2014-07-24 | [8 empty] | 350 | 350 |  |  |  |  | 2014-10-23 | 2014-10-23 |  | Y
Central Hudson |  | Paradise Energy Solutions LLC | CH-02844 | Newburgh | New Windsor | Orange | 12553 | G | 4053 | Union Ave | N |  | 72 | [13 empty] | NM | N | SMA STP 24000 (3) | 2014-09-08 | 2014-09-29 | 15 | 2014-09-29 | 2014-09-08 | 2014-09-29 | 15 | [5 empty] | 1550 | 2215.63 |  |  |  |  | 2015-04-02 | 2015-04-15 |  | Y
Central Hudson |  | SolarCity | CH-07221 | Kingston | Kingston | Ulster | 12401 | G | 112 | South Wall St | N |  | 3.8 | [13 empty] | NM | N | SOLAREDGE SE3800A-US | 2014-07-11 | 2014-07-18 | 5 | 2014-07-18 | [14 empty] | 2014-10-20 | 2014-10-27 |  | Y
Central Hudson |  | Safari Energy, LLC | CH-08849 | Newburgh | New Paltz | Ulster | 12561 | G | 5023 | Ohioville | N |  | 52 | [13 empty] | RNM | N | SMA AMERICA SUNNY TRIPOWER 20000 (2) & SMA AMERICA SUNNY TRIPOWER 12000 (1) | 2014-07-24 | 2014-08-14 | 15 | 2014-08-14 | 2014-07-24 | 2014-08-14 | 15 | [11 empty] | 2014-12-12 | 2014-12-17 |  | Y
Central Hudson |  | Safari Energy, LLC | CH-08853 | Fishkill | Poughkeepsie | Dutchess | 12601 | G | 8021 | Knapps Corners | N |  | 100 | [13 empty] | NM | N | SMA AMERICA SUNNY TRIPOWER 20000 (5) | 2014-07-24 | 2014-08-14 | 15 | 2014-08-14 | 2014-07-24 | 2014-08-14 | 15 | [5 empty] | 3700 | 3445.89 |  |  |  |  | 2014-12-03 | 2014-12-11 |  | Y
Central Hudson |  | Safari Energy, LLC | CH-08854 | Kingston | Kingston | Ulster | 12401 | G | 2091 | Hurley Ave | N |  | 70 | [13 empty] | RNM | N | SOLECTRIA SOLREN PVI-14TL (5) | 2014-07-24 | 2014-08-14 | 15 | 2014-08-14 | 2014-07-24 | 2014-08-14 | 15 | [5 empty] | 3700 | 2872.49 |  |  |  |  | 2014-12-22 | 2014-12-22 |  | Y
Central Hudson |  | Sungevity Inc | CH-09176 | Catskill | Athens | Greene | 12015 | G | 2002 | North Catskill | N |  | 16 | [13 empty] | NM | N | (2) SMA AMERICA SB8000US-12 | 2014-07-11 | 2014-07-18 | 5 | 2014-07-18 | [14 empty] | 2016-01-07 | 2016-01-14 |  | Y
Central Hudson |  | Sungevity Inc | CH-09349 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8092 | Fishkill Plains | N |  | 6 | [13 empty] | NM | N | SMA AMERICA B3000TL-US-22 (2) | 2014-07-11 | 2014-07-18 | 5 | 2014-07-18 | [14 empty] | 2014-10-03 | 2014-10-09 |  | Y
Central Hudson |  | Sungevity Inc | CH-09567 | Kingston | Kingston | Ulster | 12401 | G | 2091 | Hurley Ave | N |  | 14 | [13 empty] | NM | N | (1) SMA AMERICA SB6000TL-US-22 (1) SMA AMERICA SB8000US-12 | 2014-08-15 | 2014-08-21 | 4 | 2014-08-21 | [8 empty] | 350 | 350 |  |  |  |  | 2014-11-24 | 2014-11-24 |  | Y
Central Hudson |  | Autonomous Energies LLC | CH-00741 | Kingston | Ellenvl | Ulster | 12428 | G | 3096 | Grimley Rd | N |  | 4 | [13 empty] | NM | N | ENPHASE M250 | 2014-07-22 | 2014-07-29 | 5 | 2014-07-29 | [14 empty] | 2014-10-06 | 2014-10-08 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00923 | Kingston | Saugerties | Ulster | 12477 | G | 3005 | Saugerties | N |  | 12.25 | [13 empty] | NM | N | (49) ENPHASE ENERGY M-250 | 2014-07-14 | 2014-07-21 | 5 | 2014-07-21 | [8 empty] | 350 | 350 |  |  |  |  | 2014-11-19 | 2014-11-25 |  | Y
Central Hudson |  | Sol Providers | CH-08935 | Newburgh | New Windsor |  | 12553 | G | 4044 | Union Ave | N |  | 18 | [13 empty] | NM | N | SUNPOWERCORP SPR-5000P TL-1 (2) & SUNPOWERCORP SPR-4000P TL-1 (2) | 2014-07-25 | 2014-08-07 | 9 | 2014-08-07 | [8 empty] | 350 | 350 |  |  |  |  | 2014-10-09 | 2014-10-15 |  | W
Central Hudson |  | Sungevity Inc | CH-09631 | Newburgh | Marlboro |  | 12542 | G | 5004 | Marlboro | TBD |  | 7.6 | [13 empty] | NM | N | SMA AMERICA SB3800TL-US-22 (2) | 2014-07-14 | 2014-07-21 | 5 | 2014-07-21 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | Verengo Solar | CH-09876 | Newburgh | New Windsor | Orange | 12553 | G | 4044 | Union Ave | N |  | 7.31 | [13 empty] | NM | N | ENPHASE ENERGY M215 (34) | 2014-07-14 | 2014-07-21 | 5 | 2014-07-21 | [14 empty] | 2014-10-15 | 2014-10-20 |  | Y
Central Hudson |  | New York State Solar Farm | CH-04041 | Newburgh | Marlboro | Ulster | 12542 | G | 5003 | Marlboro | N | CH-04041 | 5 | [13 empty] | NM | N | SMA AMERICA SB 5000 | 2014-07-15 | 2014-07-22 | 5 | 2014-07-22 | [14 empty] | 2014-09-22 | 2014-09-25 |  | Y
Central Hudson |  | SolarCity | CH-04956 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8096 | Fishkill Plains | N |  | 8.8 | [13 empty] | NM | N | SOLAREDGE SE5000A-US & SOLAREDGE SE3800A-US | 2014-08-13 | 2014-08-15 | 2 | 2014-08-15 | [14 empty] | 2014-08-15 | 2014-08-15 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-05245 | Kingston | Shokan | Ulster | 12481 | G | 3011 | Woodstock | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A-US | 2014-07-15 | 2014-07-22 | 5 | 2014-07-22 | [14 empty] | 2014-11-10 | 2014-11-17 |  | Y
Central Hudson |  | SolarCity | CH-05324 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6042 | Spackenkill | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE3800A-US (2) | 2014-07-15 | 2014-07-22 | 5 | 2014-07-22 | [14 empty] | 2014-10-14 | 2014-10-20 |  | Y
Central Hudson |  | SolarCity | CH-05649 | Kingston | High Fls | Ulster | 12440 | G | 3024 | High Falls | N | CH-05649 | 16 | [13 empty] | NM | N | (1) SOLAREDGE SE6000A-US (2) SOLAREDGE SE5000A-US | 2014-07-15 | 2014-07-22 | 5 | 2014-07-22 | [8 empty] | 350 | 350 |  | 2014-09-14 | 2014-09-14 | 2014-11-18 | 2014-11-18 | 2014-11-19 |  | Y
Central Hudson |  | SolarCity | CH-06083 | Fishkill | Fishkill | Dutchess | 12524 | G | 8094 | Fishkill Plains | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A-US | 2014-07-15 | 2014-07-22 | 5 | 2014-07-22 | [14 empty] | 2014-11-06 | 2014-11-10 |  | Y
Central Hudson |  | SolarCity | CH-06300 | Newburgh | Newburgh | Orange | 12550 | G | 4011 | West Balmville | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A-US | 2014-07-15 | 2014-07-22 | 5 | 2014-07-22 | [14 empty] | 2014-08-27 | 2014-09-04 |  | Y
Central Hudson |  | SolarCity | CH-06740 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6093 | Manchester | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A-US | 2014-07-15 | 2014-07-22 | 5 | 2014-07-22 | [14 empty] | 2014-08-27 | 2014-09-04 |  | Y
Central Hudson |  | New York State Solar Farm | CH-03960 | Fishkill | Cold Spg | Putnam | 10516 | G | 8063 | Merritt Park | N |  | 11.4 | [13 empty] | NM | N | SOLAREDGE SE7600 & SOLAREDGE SE3800 | 2014-07-16 | 2014-07-23 | 5 | 2014-07-23 | [14 empty] | 2014-09-05 | 2014-09-11 |  | Y
Central Hudson |  | NRG Home Solar | CH-04477 | Newburgh | Newburgh | Orange | 12550 | G | 5001 | Marlboro | N |  | 10.105 | [13 empty] | NM | N | ENPHASE ENERGY M215 (47) | 2014-07-16 | 2014-07-23 | 5 | 2014-07-23 | [14 empty] | 2014-09-10 | 2014-09-16 |  | Y
Central Hudson |  | NRG Home Solar | CH-04478 | Newburgh | Newburgh | Orange | 12550 | G | 5001 | Marlboro | N |  | 7.31 | [13 empty] | NM | N | Enphase M215 (34) | 2014-07-16 | 2014-07-23 | 5 | 2014-07-23 | [14 empty] | 2014-09-30 | 2014-10-06 |  | Y
Central Hudson |  | NRG Home Solar | CH-04732 | Fishkill | Beacon | Dutchess | 12508 | G | 8013 | Forgebrook | N |  | 6.02 | [13 empty] | NM | N | Enphase M215 (28) | 2014-07-16 | 2014-07-23 | 5 | 2014-07-23 | [14 empty] | 2014-09-23 | 2014-09-26 |  | Y
Central Hudson |  | Conscious Energy | CH-00805 | Kingston | High Fls | Ulster | 12440 | G | 3022 | High Falls | N |  | 5 | [13 empty] | NM | N | SMA SB5000 | 2014-07-16 | 2014-07-23 | 5 | 2014-07-23 | [14 empty] | 2014-10-06 | 2014-10-13 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00831 | Newburgh | Gardiner | Ulster | 12525 | G | 5012 | Modena | N |  | 9.46 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (44) | 2014-07-16 | 2014-07-23 | 5 | 2014-07-23 | [8 empty] | 350 | 350 |  | 2014-08-21 | 2014-08-21 | 2014-09-09 | 2014-09-09 | 2014-09-10 |  | Y
Central Hudson |  | SolarCity | CH-04969 | Newburgh | Newburgh | Orange | 12550 | G | 4024 | Coldenham | N |  | 3 | [13 empty] | NM | N | SolarEdge SE3000A-US | 2014-08-08 | 2014-08-13 | 3 | 2014-08-13 | [14 empty] | 2014-09-23 | 2014-09-26 |  | Y
Central Hudson |  | SolarCity | CH-05037 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7062 | Milan | N |  | 18 | [13 empty] | NM | N | SOLAREDGE SE6000A-US (3) | 2014-07-16 | 2014-07-24 | 6 | 2014-07-24 | [14 empty] | 2014-10-07 | 2014-10-14 |  | Y
Central Hudson |  | SolarCity | CH-05165 | Newburgh | Marlboro | Ulster | 12542 | G | 5004 | Marlboro | N |  | 9.8 | [13 empty] | NM | N | SOLAREDGE SE3800A-US & SOLAREDGE SE6000A-US | 2014-07-16 | 2014-07-23 | 5 | 2014-07-23 | [14 empty] | 2014-09-05 | 2014-09-11 |  | Y
Central Hudson |  | SolarCity | CH-05176 | Newburgh | New Paltz | Ulster | 12561 | G | 5022 | Ohioville | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE3800A-US (2) | 2014-07-16 | 2014-07-23 | 5 | 2014-07-23 | [14 empty] | 2014-12-19 | 2014-12-29 |  | Y
Central Hudson |  | SolarCity | CH-05482 | Kingston | Cementon | Greene | 12414 | G | 3002 | Saugerties | N |  | 3.8 | [13 empty] | NM | N | SOLAREDGE SE3800A-US | 2014-07-16 | 2014-07-23 | 5 | 2014-07-23 | [14 empty] | 2014-09-30 | 2014-10-07 |  | Y
Central Hudson |  | SolarCity | CH-05564 | Catskill | Dormansvl | Albany | 12055 | G | 1091 | Westerlo | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A-US | 2014-07-16 | 2014-07-23 | 5 | 2014-07-23 | [14 empty] | 2014-10-16 | 2014-10-23 |  | Y
Central Hudson |  | SolarCity | CH-05727 | Kingston | Malden-Hdsn |  | 12453 | G | 3002 | Saugerties | TBD |  | 16 | [13 empty] | NM | N | (1) SOLAREDGE SE6000A-US (2) SOLAREDGE SE5000A-US | 2014-07-16 | 2014-07-23 | 5 | 2014-07-23 | [17 empty] | W
Central Hudson |  | SolarCity | CH-05975 | Newburgh | Highland | Ulster | 12528 | G | 5081 | Highland | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A-US | 2014-08-25 | 2014-09-02 | 5 | 2014-09-02 | [14 empty] | 2014-09-05 | 2014-09-11 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06076 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8092 | Fishkill Plains | N |  | 3 | [13 empty] | NM | N | SOLAREDGE SE3000A-US | 2014-07-16 | 2014-07-23 | 5 | 2014-07-23 | [14 empty] | 2014-10-14 | 2014-10-20 |  | Y
Central Hudson |  | SolarCity | CH-06090 | Fishkill | Fishkill | Dutchess | 12524 | G | 8094 | Fishkill Plains | N |  | 11 | [13 empty] | NM | N | SOLAREDGE SE5000A-US & SOLAREDGE SE6000A-US | 2014-07-16 | 2014-07-23 | 5 | 2014-07-23 | [14 empty] | 2014-09-05 | 2014-09-11 |  | Y
Central Hudson |  | SolarCity | CH-06771 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7051 | Rhinebeck | N |  | 9.8 | [13 empty] | NM | N | SOLAREDGE SE3800A-US & SOLAREDGE SE6000A-US | 2014-07-16 | 2014-07-23 | 5 | 2014-07-23 | [14 empty] | 2014-09-05 | 2014-09-11 |  | Y
Central Hudson |  | SolarCity | CH-06785 | Newburgh | Highland | Ulster | 12528 | G | 5084 | Highland | N |  | 10 | [13 empty] | NM | N | SOLAREDGE SE5000A-US (2) | 2014-07-16 | 2014-07-23 | 5 | 2014-07-23 | [14 empty] | 2014-09-22 | 2014-09-26 |  | Y
Central Hudson |  | SolarCity | CH-07312 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 7024 | Tinkertown | N |  | 17 | [13 empty] | NM | N | SOLAREDGE SE5000A-US (1) & SOLAREDGE SE6000A-US (2) | 2014-07-16 | 2014-07-23 | 5 | 2014-07-23 | [14 empty] | 2015-01-29 | 2015-02-05 |  | Y
Central Hudson |  | Sungevity Inc | CH-09510 | Newburgh | New Windsor | Orange | 12553 | G | 4094 | Bethlehem Rd | N |  | 12 | [13 empty] | NM | N | SMA AMERICA SB6000TL-US-22 (2) | 2014-07-16 | 2014-07-23 | 5 | 2014-07-23 | [14 empty] | 2014-10-06 | 2014-10-13 |  | Y
Central Hudson |  | Sungevity Inc | CH-09558 | Newburgh | Middletown | Orange | 10941 | G | 5051 | Maybrook | N |  | 7.6 | [13 empty] | NM | N | SMA AMERICA SB 3800TL-US-22 (2) | 2014-07-29 | 2014-08-05 | 5 | 2014-08-05 | [14 empty] | 2014-10-17 | 2014-10-22 |  | Y
Central Hudson |  | Verengo Solar | CH-09889 | Newburgh | New Windsor | Orange | 12553 | G | 4094 | Bethlehem Rd | N |  | 3.44 | [13 empty] | NM | N | ENPHASE ENERGY M215 (16) | 2014-07-24 | 2014-08-07 | 10 | 2014-08-07 | [14 empty] | 2014-11-03 | 2014-11-07 |  | Y
Central Hudson |  | Lotus Energy Inc. | CH-03853 | Catskill | Leeds | Greene | 12451 | G | 2005 | North Catskill | N |  | 4 | [13 empty] | NM | N | SMA SB-4000 (1) | 2014-07-17 | 2014-07-24 | 5 | 2014-07-24 | [14 empty] | 2014-10-30 | 2014-11-06 |  | Y
Central Hudson |  | Kool-Temp | CH-02577 | Catskill | Coxsackie | Greene | 12051 | G | 1076 | Coxsackie | N |  | 15 | [13 empty] | NM | N | (2) FRONIUS IG PLUS 7.5 UNI | 2014-07-17 | 2014-07-24 | 5 | 2014-07-24 | [8 empty] | 350 | 350 |  |  |  |  | 2015-01-06 | 2015-01-13 |  | Y
Central Hudson |  | Sunrise Solar Solutions, LLC | CH-09667 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7054 | Rhinebeck | N |  | 6.02 | [13 empty] | NM | N | ENPHASE M215 (28) | 2014-07-17 | 2014-07-24 | 5 | 2014-07-24 | [14 empty] | 2014-12-16 | 2014-12-22 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03573 | Newburgh | New Paltz | Ulster | 12561 | G | 5031 | Galeville | N | CH-03573 | 7.6 | [13 empty] | NM | N | POWERONE UNO 7.6 | 2014-07-18 | 2014-07-24 | 4 | 2014-07-24 | [14 empty] | 2014-12-05 | 2014-12-11 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03756 | Newburgh | New Paltz | Ulster | 12561 | G | 5023 | Ohioville | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE7600A | 2014-07-18 | 2014-07-24 | 4 | 2014-07-24 | [14 empty] | 2014-12-05 | 2014-12-11 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03746 | Newburgh | New Paltz | Ulster | 12561 | G | 5031 | Galeville | N |  | 10 | [13 empty] | NM | N | SOLAREDGE 10000A | 2014-07-21 | 2014-07-25 | 4 | 2014-07-25 | [14 empty] | 2015-02-26 | 2015-03-05 |  | Y
Central Hudson |  | New York State Solar Farm | CH-04045 | Newburgh | Gardiner | Ulster | 12525 | G | 5011 | Modena | N |  | 11 | [13 empty] | NM | N | POWERONE PVI-6000 & POWERONE PVI-5000 | 2014-07-28 | 2014-08-04 | 5 | 2014-08-04 | [14 empty] | 2014-09-22 | 2014-09-23 |  | Y
Central Hudson |  | NRG Home Solar | CH-04192 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8095 | Fishkill Plains | N |  | 4.3 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (20) | 2014-07-21 | 2014-07-28 | 5 | 2014-07-28 | [14 empty] | 2014-08-27 | 2014-09-04 |  | Y
Central Hudson |  | NRG Home Solar | CH-04329 | Poughkeepsie | Hopewell Jct | Dutchess | 12533 | G | 6052 | Todd Hill | N |  | 3.01 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (14) | 2014-07-21 | 2014-07-25 | 4 | 2014-07-25 | [14 empty] | 2014-10-06 | 2014-10-10 |  | Y
Central Hudson |  | NRG Home Solar | CH-04556 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 7041 | Staatsburg | N |  | 6.88 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (32) | 2014-07-21 | 2014-07-25 | 4 | 2014-07-25 | [14 empty] | 2014-10-06 | 2014-10-10 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00963 | Newburgh | Milton | Ulster | 12547 | G | 5083 | Highland | N |  | 8.6 | [13 empty] | NM | N | ENPHASE M215 (40) | 2014-07-21 | 2014-07-25 | 4 | 2014-07-25 | [14 empty] | 2014-08-22 | 2014-08-29 |  | Y
Central Hudson |  | Novel Approaches | CH-02777 | Kingston | Accord | Ulster | 12404 | G | 3081 | Kerhonkson | N |  | 10 | [13 empty] | NM | N | SMA SB10000TL | 2014-07-21 | 2014-07-28 | 5 | 2014-07-28 | [14 empty] | 2014-09-29 | 2014-10-06 |  | Y
Central Hudson |  | Sungevity Inc | CH-09183 | Kingston | Grahamsvl | Sullivan | 12740 | G | 3091 | Neversink | N |  | 15 | [13 empty] | NM | N | SMA AMERICA SB7000US-12 | 2014-07-21 | 2014-07-28 | 5 | 2014-07-28 | [14 empty] | 2014-10-24 | 2014-10-31 |  | Y
Central Hudson |  | Sungevity Inc | CH-09242 | Newburgh | New Windsor | Orange | 12553 | G | 4042 | Union Ave | N |  | 5 | [13 empty] | NM | N | SMA AMERICA SB5000TL-US-22 | 2014-07-21 | 2014-07-28 | 5 | 2014-07-28 | [14 empty] | 2014-10-17 | 2014-10-22 |  | Y
Central Hudson |  | NRG Home Solar | CH-04376 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8091 | Fishkill Plains | N |  | 5.805 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (27) | 2014-07-22 | 2014-07-28 | 4 | 2014-07-28 | [14 empty] | 2014-09-24 | 2014-09-29 |  | Y
Central Hudson |  | Conscious Energy | CH-00806 | Kingston | Kingston |  | 12401 | G | 121 | Converse St | TBD |  | 4.8 | [13 empty] | NM | N | SMA SB240 | 2014-07-22 | 2014-07-29 | 5 | 2014-07-29 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | Sungevity Inc | CH-09467 | Newburgh | Clintondale | Ulster | 12515 | G | 5024 | Ohioville | N |  | 3.8 | [13 empty] | NM | N | SMA AMERICA SB3800TL-US-22 | 2014-07-28 | 2014-08-04 | 5 | 2014-08-04 | [14 empty] | 2014-10-30 | 2014-11-05 |  | Y
Central Hudson |  | NRG Home Solar | CH-04462 | Newburgh | New Windsor | Orange | 12553 | G | 4046 | Union Ave | N |  | 6.665 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (31) | 2014-08-07 | 2014-08-12 | 3 | 2014-08-12 | [14 empty] | 2015-01-30 | 2015-02-06 |  | Y
Central Hudson |  | NRG Home Solar | CH-04635 | Newburgh | Newburgh |  | 12550 | G | 4023 | Coldenham | TBD |  | 3.225 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (15) | 2014-07-30 | 2014-08-06 | 5 | 2014-08-06 | [17 empty] | W
Central Hudson |  | SolarCity | CH-05180 | Newburgh | New Windsor | Orange | 12553 | G | 4093 | Bethlehem Rd | N |  | 11 | [13 empty] | NM | N | SOLAREDGE SE6000A-US & SOLAREDGE SE5000A-US | 2014-07-23 | 2014-07-30 | 5 | 2014-07-30 | [14 empty] | 2014-08-11 | 2014-08-14 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Sungevity Inc | CH-09240 | Newburgh | Wallkill | Ulster | 12589 | G | 5043 | East Walden | N |  | 6.8 | [13 empty] | NM | N | SMA AMERICA SB3000TL-US-22 & SMA AMERICA SB3800TL-US-22 | 2014-07-31 | 2014-08-07 | 5 | 2014-08-07 | [14 empty] | 2014-09-19 | 2014-09-24 |  | Y
Central Hudson |  | NRG Home Solar | CH-04501 | Newburgh | Rock Tvrn | Orange | 12575 | G | 4097 | Bethlehem Rd | N |  | 6.88 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (32) | 2014-08-18 | 2014-08-20 | 2 | 2014-08-20 | [14 empty] | 2014-09-23 | 2014-09-26 |  | Y
Central Hudson |  | NRG Home Solar | CH-04560 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6055 | Todd Hill | N |  | 9.245 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (43) | 2014-07-24 | 2014-08-07 | 10 | 2014-08-07 | [14 empty] | 2014-09-23 | 2014-09-29 |  | Y
Central Hudson |  | NRG Home Solar | CH-04564 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6092 | Manchester | N |  | 6.88 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (32) | 2014-07-24 | 2014-08-07 | 10 | 2014-08-07 | [14 empty] | 2014-09-19 | 2014-09-26 |  | Y
Central Hudson |  | NRG Home Solar | CH-04444 | Newburgh | Newburgh | Orange | 12550 | G | 4013 | West Balmville | N |  | 4.085 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (19) | 2014-07-25 | 2014-08-01 | 5 | 2014-08-01 | [14 empty] | 2014-11-10 | 2014-11-13 |  | Y
Central Hudson |  | NRG Home Solar | CH-04480 | Newburgh | Marlboro | Ulster | 12542 | G | 5004 | Marlboro | N |  | 8.6 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (40) | 2014-07-25 | 2014-08-01 | 5 | 2014-08-01 | [14 empty] | 2014-09-25 | 2014-10-01 |  | Y
Central Hudson |  | NRG Home Solar | CH-04656 | Newburgh | Newburgh |  | 12550 | G | 5001 | Marlboro | TBD |  | 11 | [13 empty] | NM | N | ENPHASE ENERGY M-250 (44) | 2014-07-25 | 2014-08-01 | 5 | 2014-08-01 | [17 empty] | W
Central Hudson |  | NRG Home Solar | CH-04662 | Newburgh | Gardiner | Ulster | 12525 | G | 5031 | Galeville | N |  | 7.31 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (34) | 2014-07-25 | 2014-08-01 | 5 | 2014-08-01 | [14 empty] | 2014-09-04 | 2014-09-10 |  | Y
Central Hudson |  | Conscious Energy | CH-00795 | Kingston | High Fls | Ulster | 12440 | G | 3024 | High Falls | N |  | 15 | [13 empty] | NM | N | (3) SMA SB5000-TL-US | 2014-07-25 | 2014-08-01 | 5 | 2014-08-01 | [14 empty] | 2014-09-22 | 2014-09-29 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00865 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8072 | Shenandoah | N |  | 9.03 | [13 empty] | NM | N | ENPHASE M215 (42) | 2014-07-25 | 2014-08-01 | 5 | 2014-08-01 | [14 empty] | 2014-09-04 | 2014-09-04 |  | Y
Central Hudson |  | Direct Energy Solar | CH-01033 | Kingston | Grahamsvl | Greene | 12470 | G | 3091 | Neversink | N |  | 6.6 | [13 empty] | NM | N | ENPHASE M215 | 2014-07-25 | 2014-08-01 | 5 | 2014-08-01 | [14 empty] | 2014-08-21 | 2014-08-28 |  | Y
Central Hudson |  | SolarCity | CH-06087 | Fishkill | Fishkill | Dutchess | 12524 | G | 8094 | Fishkill Plains | N |  | 3 | [13 empty] | NM | N | SOLAREDGE SE3000A-US | 2014-07-25 | 2014-08-01 | 5 | 2014-08-01 | [14 empty] | 2014-10-14 | 2014-10-20 |  | Y
Central Hudson |  | Sol Providers | CH-08907 | Newburgh | New Paltz | Ulster | 12561 | G | 5023 | Ohioville | N |  | 10 | [13 empty] | NM | N | SMA SB 5000TL-US (2) | 2014-07-25 | 2014-08-01 | 5 | 2014-08-01 | [14 empty] | 2014-12-04 | 2014-12-10 |  | Y
Central Hudson |  | Sungevity Inc | CH-09208 | Kingston | Saugerties | Ulster | 12477 | G | 2015 | Lincoln Park | N |  | 8.8 | [13 empty] | NM | N | (1) SMA AMERICA SB3800TL-US-22 (2) SMA AMERICA SB5000TL-US-22 | 2014-07-25 | 2014-08-01 | 5 | 2014-08-01 | [14 empty] | 2014-10-07 | 2014-10-14 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00836 | Catskill | E Durham | Greene | 12423 | G | 1092 | Westerlo | N |  | 17.2 | [13 empty] | NM | N | (80) ENPHASE ENERGY M-215 | 2014-07-28 | 2014-08-04 | 5 | 2014-08-04 | [14 empty] | 2014-10-23 | 2014-10-30 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00975 | Newburgh | Campbell Hall | Orange | 10916 | G | 5052 | Maybrook | N |  | 8.6 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (40) | 2014-07-28 | 2014-08-04 | 5 | 2014-08-04 | [14 empty] | 2014-12-03 | 2014-12-09 |  | Y
Central Hudson |  | Hudson Solar | CH-01637 | Catskill | W Coxsackie | Greene | 12192 | G | 1071 | Coxsackie | N |  | 9 | [13 empty] | NM | N | (1) SMA AMERICA SB5000 (1) SMA AMERICA SB4000 | 2014-07-28 | 2014-08-04 | 5 | 2014-08-04 | [14 empty] | 2014-11-11 | 2014-11-18 |  | Y
Central Hudson |  | SolarCity | CH-04931 | Poughkeepsie | Millbrook | Dutchess | 12545 | G | 7025 | Tinkertown | N |  | 12 | [13 empty] | NM | N | POWERONE PVI-6000 (2) | 2014-08-06 | 2014-08-11 | 3 | 2014-08-11 | [14 empty] | 2014-10-10 | 2014-10-17 |  | Y
Central Hudson |  | SolarCity | CH-05483 | Catskill | Catskill | Greene | 12414 | G | 2004 | North Catskill | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A-US | 2014-07-28 | 2014-08-04 | 5 | 2014-08-04 | [14 empty] | 2014-12-02 | 2014-12-09 |  | Y
Central Hudson |  | SolarCity | CH-05484 | Catskill | Catskill | Greene | 12414 | G | 2001 | North Catskill | N |  | 13.6 | [13 empty] | NM | N | (1) SOLAREDGE SE6000A-US (2) SOLAREDGE SE3800A-US | 2014-07-28 | 2014-08-04 | 5 | 2014-08-04 | [14 empty] | 2014-10-16 | 2014-10-23 |  | Y
Central Hudson |  | SolarCity | CH-05573 | Catskill | Athens | Greene | 12051 | G | 1074 | Coxsackie | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A-US | 2014-07-28 | 2014-08-04 | 5 | 2014-08-04 | [14 empty] | 2014-10-30 | 2014-11-06 |  | Y
Central Hudson |  | SolarCity | CH-05797 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6044 | Spackenkill | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A-US | 2014-07-28 | 2014-08-04 | 5 | 2014-08-04 | [14 empty] | 2014-09-17 | 2014-09-24 |  | Y
Central Hudson |  | SolarCity | CH-06072 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8092 | Fishkill Plains | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A-US | 2014-07-28 | 2014-08-04 | 5 | 2014-08-04 | [14 empty] | 2014-09-17 | 2014-09-23 |  | Y
Central Hudson |  | SolarCity | CH-06143 | Fishkill | Beacon | Dutchess | 12508 | G | 8017 | Forgebrook | N |  | 3 | [13 empty] | NM | N | SOLAREDGE SE3000A-US | 2014-07-28 | 2014-08-04 | 5 | 2014-08-04 | [14 empty] | 2014-10-10 | 2014-10-16 |  | Y
Central Hudson |  | SolarCity | CH-06365 | Newburgh | Wallkill | Ulster | 12589 | G | 5041 | East Walden | N |  | 15.8 | [13 empty] | NM | N | SOLAREDGE SE6000A-US (2) & SOLAREDGE SE3800A-US (1) | 2014-08-06 | 2014-08-11 | 3 | 2014-08-11 | [14 empty] | 2015-02-09 | 2015-02-17 |  | Y
Central Hudson |  | SolarCity | CH-07388 | Fishkill | Beacon | Dutchess | 12508 | G | 8018 | Forgebrook | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE3800A-US (2) | 2014-07-28 | 2014-08-04 | 5 | 2014-08-04 | [14 empty] | 2014-08-26 | 2014-09-03 |  | Y
Central Hudson |  | SolarCity | CH-07705 | Poughkeepsie | Salt Pt | Dutchess | 12578 | G | 7012 | Hibernia | N |  | 9 | [13 empty] | NM | N | SOLAREDGE SE6000A-US & SOLAREDGE SE3000A-US | 2014-08-06 | 2014-08-11 | 3 | 2014-08-11 | [14 empty] | 2014-10-01 | 2014-10-08 |  | Y
Central Hudson |  | Self | CH-08881 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8091 | Fishkill Plains | N |  | 11.4 | [13 empty] | NM | N | SOLAR EDGE SE-114000A-US | 2014-08-05 | 2014-08-11 | 4 | 2014-08-11 | [14 empty] | 2014-11-18 | 2014-11-18 |  | Y
Central Hudson |  | RGS Energy | CH-03053 | Newburgh | New Windsor | Orange | 12553 | G | 4095 | Bethlehem Rd | N |  | 10 | [13 empty] | NM | N | Fronius IG Plus A 10.0.1 UNI | 2014-08-11 | 2014-08-14 | 3 | 2014-08-14 | [14 empty] | 2014-10-23 | 2014-10-29 |  | Y
Central Hudson |  | NRG Home Solar | CH-04151 | Fishkill | Hopewell Jct |  | 12533 | G | 8091 | Fishkill Plains | TBD |  | 6.88 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (32) | 2014-07-29 | 2014-08-05 | 5 | 2014-08-05 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | Sungevity Inc | CH-09431 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6046 | Spackenkill | N |  | 10 | [13 empty] | NM | N | SMA AMERICA SB5000TL-US-22 (2) | 2014-08-15 | 2014-08-15 | 0 | 2014-08-15 | [14 empty] | 2014-10-08 | 2014-10-15 |  | Y
Central Hudson |  | Lotus Energy Inc. | CH-03851 | Catskill | Medusa | Albany | 12120 | G | 1092 | Westerlo | N |  | 8 | [13 empty] | NM | N | SUNPOWER 8000M | 2014-07-30 | 2014-08-04 | 3 | 2014-08-04 | [14 empty] | 2014-11-20 | 2014-12-01 |  | Y
Central Hudson |  | New York State Solar Farm | CH-04056 | Newburgh | Rock Tvrn | Orange | 12575 | G | 4097 | Bethlehem Rd | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE 7.6 | 2014-07-30 | 2014-08-07 | 6 | 2014-08-07 | [14 empty] | 2014-09-25 | 2014-10-01 |  | Y
Central Hudson |  | Hudson Solar | CH-01732 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6043 | Spackenkill | N |  | 5 | [13 empty] | NM | N | SMA AMERICA SB5000 | 2014-07-30 | 2014-08-06 | 5 | 2014-08-06 | [14 empty] | 2014-11-17 | 2014-11-24 |  | Y
Central Hudson |  | Hudson Solar | CH-02377 | Fishkill | Cold Spg |  | 10516 | G | 8087 | Tioronda | TBD |  | 5 | [13 empty] | NM | N | SMA AMERICA SB5000 | 2014-07-30 | 2014-08-06 | 5 | 2014-08-06 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | Inverters Unlimited Inc | CH-02558 | Catskill | Hannacroix | Greene | 12087 | G | 1083 | New Baltimore | N |  | 10.8 | [13 empty] | NM | N | (1) SMA SB7000 (1) SMA SB3800 | 2014-12-09 | 2014-12-10 | 1 | 2014-12-10 | [14 empty] | 2015-03-12 | 2015-03-18 |  | Y
Central Hudson |  | SolarCity | CH-05479 | Newburgh | New Windsor | Orange | 12553 | G | 4093 | Bethlehem Rd | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A-US | 2014-07-30 | 2014-08-06 | 5 | 2014-08-06 | [14 empty] | 2014-09-08 | 2014-09-11 |  | Y
Central Hudson |  | SolarCity | CH-07043 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A-US | 2014-07-30 | 2014-08-07 | 6 | 2014-08-07 | [14 empty] | 2014-10-21 | 2014-10-24 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07747 | Newburgh | New Windsor | Orange | 12553 | G | 4054 | Union Ave | N |  | 3.8 | [13 empty] | NM | N | SOLAREDGE SE3800A-US | 2014-07-30 | 2014-08-06 | 5 | 2014-08-06 | [14 empty] | 2014-12-18 | 2014-12-26 |  | W
Central Hudson |  | Sungevity Inc | CH-09486 | Newburgh | New Windsor | Orange | 12553 | G | 4046 | Union Ave | N |  | 7 | [13 empty] | NM | N | SMA AMERICA SB7000-US-12 | 2014-07-31 | 2014-08-07 | 5 | 2014-08-07 | [14 empty] | 2014-10-16 | 2014-10-21 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03757 | Newburgh | New Paltz |  | 12561 | G | 5023 | Ohioville | TBD |  | 7.6 | [13 empty] | NM | N | SOLAREDGE 7600 | 2014-08-08 | 2014-08-08 | 0 | 2014-08-08 | [17 empty] | W
Central Hudson |  | Lighthouse Solar | CH-03820 | Newburgh | New Paltz | Ulster | 12561 | G | 5031 | Galeville | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE 6000 | 2014-08-01 | 2014-08-08 | 5 | 2014-08-08 | [14 empty] | 2014-10-16 | 2014-10-22 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-03422 | Newburgh | New Windsor | Orange | 12553 | G | 4044 | Union Ave | N |  | 3 | [13 empty] | NM | N | Fronius IG Plus A 3.0-1 UNI | 2014-08-04 | 2014-08-08 | 4 | 2014-08-08 | [14 empty] | 2014-09-04 | 2014-09-11 |  | Y
Central Hudson |  | NRG Home Solar | CH-04671 | Newburgh | Cornwall | Orange | 12518 | G | 4041 | Union Ave | N |  | 3.44 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (16) | 2014-09-22 | 2014-09-25 | 3 | 2014-09-25 | [14 empty] | 2014-10-15 | 2014-10-21 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-03471 | Newburgh | Gardiner | Ulster | 12525 | G | 5012 | Modena | N |  | 10 | [13 empty] | NM | N | FRONIUS IG PLUS A 10.0-1 | 2014-08-05 | 2014-08-11 | 4 | 2014-08-11 | [8 empty] | 350 | 350 |  |  |  |  | 2014-10-07 | 2014-10-08 |  | Y
Central Hudson |  | Kasselman Solar | CH-03522 | Catskill | Ravena | Albany | 12143 | G | 1081 | New Baltimore | N | CH-03522 | 5.16 | [13 empty] | NM | N | ENPHASE M215 | 2014-08-05 | 2014-08-12 | 5 | 2014-08-12 | [14 empty] | 2014-09-03 | 2014-09-08 |  | Y
Central Hudson |  | NRG Home Solar | CH-04414 | Fishkill | Beacon | Dutchess | 12508 | G | 8015 | Forgebrook | N |  | 8.17 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (38) | 2014-08-05 | 2014-08-11 | 4 | 2014-08-11 | [14 empty] | 2014-11-04 | 2014-11-07 |  | Y
Central Hudson |  | Kool-Temp | CH-02571 | Catskill | Athens | Greene | 12015 | G | 1074 | Coxsackie | N |  | 7.5 | [13 empty] | NM | N | FRONIUS IG PLUS 7.5-1 UNI | 2014-08-05 | 2014-08-12 | 5 | 2014-08-12 | [14 empty] | 2015-01-21 | 2015-01-28 |  | Y
Central Hudson |  | Sungevity Inc | CH-09449 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8023 | Knapps Corners | N | CH-09449 | 3 | [13 empty] | NM | N | SMA AMERICA SB3000TL-US-22 | 2014-08-11 | 2014-08-14 | 3 | 2014-08-14 | [14 empty] | 2014-10-15 | 2014-10-20 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03719 | Newburgh | Wallkill | Ulster | 12589 | G | 5033 | Galeville | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000 | 2014-08-06 | 2014-08-12 | 4 | 2014-08-12 | [14 empty] | 2014-10-29 | 2014-11-03 |  | Y
Central Hudson |  | NRG Home Solar | CH-04503 | Newburgh | Washingtonvl |  | 10992 | G | 4097 | Bethlehem Rd | TBD |  | 12 | [13 empty] | NM | N | ENPHASE ENERGY M-250 (48) | 2014-08-06 | 2014-08-12 | 4 | 2014-08-12 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | NRG Home Solar | CH-04658 | Newburgh | Marlboro | Ulster | 12542 | G | 5004 | Marlboro | N |  | 7.31 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (34) | 2014-08-12 | 2014-08-15 | 3 | 2014-08-15 | [14 empty] | 2014-09-22 | 2014-09-25 |  | Y
Central Hudson |  | NRG Home Solar | CH-04843 | Newburgh | Wallkill |  | 12589 | G | 5012 | Modena | TBD |  | 11.825 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (55) | 2014-08-06 | 2014-08-14 | 6 | 2014-08-14 | [8 empty] | 350 | 350 | [7 empty] | W |  | Customer already had net meter prior to application. Transformer upgrade required to accommodate PV installation. Utility System Upgrade Costs TBD. 8/15/14 Customer advised that they will not be moving forward with this project.
Central Hudson |  | SolarCity | CH-04936 | Newburgh | New Windsor | Orange | 12553 | G | 4097 | Bethlehem Rd | N |  | 13.6 | [13 empty] | NM | N | SOLAREDGE SE6000A-US & SOLAREDGE SE3800A-US (2) | 2014-08-06 | 2014-08-12 | 4 | 2014-08-12 | [14 empty] | 2014-09-19 | 2014-09-26 |  | Y
Central Hudson |  | SolarCity | CH-05633 | Kingston | High Fls | Ulster | 12440 | G | 3022 | High Falls | N |  | 8 | [13 empty] | NM | N | (1)SOLAREDGE SE5000A-US (1)SOLAREDGE SE3000A-US | 2014-08-06 | 2014-08-13 | 5 | 2014-08-13 | [14 empty] | 2014-12-03 | 2014-12-10 |  | Y
Central Hudson |  | SolarCity | CH-06385 | Newburgh | New Windsor | Orange | 12553 | G | 4095 | Bethlehem Rd | N |  | 15 | [13 empty] | NM | N | SOLAREDGE SE6000A-US (2) SOLAREDGE SE3000A-US (1) | 2014-10-08 | 2014-10-14 | 4 | 2014-10-14 | [8 empty] | 350 | 350 |  | 2014-10-27 | 2014-10-27 | 2014-11-06 | 2014-11-04 | 2014-11-06 |  | Y
Central Hudson |  | SolarCity | CH-06534 | Kingston | Shokan | Ulster | 12481 | G | 3011 | Woodstock | N |  | 7.6 | [13 empty] | NM | N | (2) SOLAREDGE SE3800A-US | 2014-08-06 | 2014-08-13 | 5 | 2014-08-13 | [8 empty] | 350 | 350 |  |  |  |  | 2015-05-07 | 2015-05-08 |  | Y
Central Hudson |  | SolarCity | CH-06873 | Fishkill | Fishkill | Dutchess | 12524 | G | 8065 | Merritt Park | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE3800A-US (2) | 2014-08-06 | 2014-08-12 | 4 | 2014-08-12 | [14 empty] | 2014-12-02 | 2014-12-08 |  | Y
Central Hudson |  | SolarCity | CH-07575 | Fishkill | Fishkill | Dutchess | 12524 | G | 8094 | Fishkill Plains | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE3800A-US (2) | 2014-08-06 | 2014-08-12 | 4 | 2014-08-12 | [14 empty] | 2015-02-23 | 2015-03-02 |  | Y
Central Hudson |  | Solar Generation | CH-08189 | Kingston | Woodstock | Ulster | 12498 | G | 3003 | Saugerties | N |  | 17 | [13 empty] | NM | N | (1) SMA SB7000 (1) SMA SB10000 | 2014-08-14 | 2014-08-20 | 4 | 2014-08-20 | [14 empty] | 2014-09-25 | 2014-10-02 |  | Y
Central Hudson |  | Sungevity Inc | CH-09243 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6096 | Manchester | N |  | 9.8 | [13 empty] | NM | N | SMA AMERICA SB3800TL-US-22 (1) SMA AMERICA SB6000TL-US-22 (1) | 2014-08-06 | 2014-08-12 | 4 | 2014-08-12 | [14 empty] | 2014-10-17 | 2014-10-24 |  | Y
Central Hudson |  | Sungevity Inc | CH-09262 | Catskill | Berne |  | 12023 | G | 1091 | Westerlo | TBD |  | 5 | [13 empty] | NM | N | SMA AMERICA SB5000TL-US-22 | 2014-08-06 | 2014-08-13 | 5 | 2014-08-13 | [17 empty] | W
Central Hudson |  | NRG Home Solar | CH-04624 | Fishkill | Beacon | Dutchess | 12508 | G | 8087 | Tioronda | N |  | 3.225 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (15) | 2014-08-07 | 2014-08-13 | 4 | 2014-08-13 | [14 empty] | 2014-10-27 | 2014-11-03 |  | Y
Central Hudson |  | NRG Home Solar | CH-04634 | Newburgh | Walden | Orange | 12586 | G | 4026 | Coldenham | N |  | 7.525 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (35) | 2014-08-07 | 2014-08-13 | 4 | 2014-08-13 | [14 empty] | 2015-01-05 | 2015-01-06 |  | Y
Central Hudson |  | Sungevity Inc | CH-09455 | Fishkill | Fishkill | Dutchess | 12524 | G | 8094 | Fishkill Plains | N |  | 6 | [13 empty] | NM | N | SMA AMERICA SB6000TL-US-22 | 2014-08-07 | 2014-08-13 | 4 | 2014-08-13 | [14 empty] | 2014-10-07 | 2014-10-13 |  | Y
Central Hudson |  | RGS Energy | CH-03045 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6011 | Sand Dock | N |  | 6 | [13 empty] | NM | N | ENPHASE M250 (24) | 2014-08-08 | 2014-08-14 | 4 | 2014-08-14 | [14 empty] | 2014-12-15 | 2014-12-22 |  | Y
Central Hudson |  | NRG Home Solar | CH-04130 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8056 | North Chelsea | N |  | 9.89 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (46) | 2014-08-08 | 2014-08-13 | 3 | 2014-08-13 | [14 empty] | 2014-10-28 | 2014-10-31 |  | Y
Central Hudson |  | NRG Home Solar | CH-04242 | Catskill | Freehold | Greene | 12431 | G | 2071 | Freehold | N |  | 6.235 | [13 empty] | NM | N | ENPHASE ENERGY M-215-60-2LL-S22-IG | 2014-08-08 | 2014-08-15 | 5 | 2014-08-15 | [14 empty] | 2014-12-17 | 2014-12-26 |  | Y
Central Hudson |  | NRG Home Solar | CH-04388 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8046 | Myers Corners | N |  | 10.535 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (49) | 2014-08-08 | 2014-08-13 | 3 | 2014-08-13 | [14 empty] | 2015-04-17 | 2015-04-24 |  | Y
Central Hudson |  | NRG Home Solar | CH-04441 | Newburgh | New Paltz | Ulster | 12561 | G | 5024 | Ohioville | N |  | 7.31 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (34) | 2014-08-08 | 2014-08-13 | 3 | 2014-08-13 | [14 empty] | 2014-10-22 | 2014-10-28 |  | Y
Central Hudson |  | NRG Home Solar | CH-04723 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8014 | Forgebrook | N |  | 5.805 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (27) | 2014-08-08 | 2014-08-13 | 3 | 2014-08-13 | [14 empty] | 2014-11-07 | 2014-11-07 |  | Y
Central Hudson |  | NRG Home Solar | CH-04794 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8045 | Myers Corners | N |  | 6.5 | [13 empty] | NM | N | ENPHASE ENERGY M-250 (26) | 2014-08-08 | 2014-08-13 | 3 | 2014-08-13 | [14 empty] | 2015-04-14 | 2015-04-21 |  | Y
Central Hudson |  | NRG Home Solar | CH-04393 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8091 | Fishkill Plains | N |  | 5.16 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (24) | 2014-08-11 | 2014-08-14 | 3 | 2014-08-14 | [14 empty] | 2014-11-17 | 2014-11-21 |  | Y
Central Hudson |  | NRG Home Solar | CH-04461 | Newburgh | New Windsor |  | 12553 | G | 4044 | Union Ave | TBD |  | 4 | [13 empty] | NM | N | ENPHASE ENERGY M-250 (16) | 2014-08-11 | 2014-08-14 | 3 | 2014-08-14 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | NRG Home Solar | CH-04476 | Newburgh | Newburgh | Orange | 12550 | G | 5004 | Marlboro | N |  | 10.535 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (49) | 2014-08-11 | 2014-08-14 | 3 | 2014-08-14 | [14 empty] | 2014-10-06 | 2014-10-13 |  | Y
Central Hudson |  | NRG Home Solar | CH-04710 | Poughkeepsie | Salt Pt | Dutchess | 12578 | G | 7011 | Hibernia | N |  | 4.515 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (21) | 2014-08-11 | 2014-08-14 | 3 | 2014-08-14 | [14 empty] | 2014-10-29 | 2014-11-05 |  | Y
Central Hudson |  | NRG Home Solar | CH-04806 | Poughkeepsie | Poughkeepsie |  | 12601 | G | 6002 | Reynolds Hill | TBD |  | 6.75 | [13 empty] | NM | N | ENPHASE ENERGY M-250 (27) | 2014-08-14 | 2014-08-15 | 1 | 2014-08-15 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | SunBlue Energy | CH-09131 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 7011 | Hibernia | N |  | 7.75 | [13 empty] | NM | N | Enphase M250 (31) | 2014-08-15 | 2014-08-15 | 0 | 2014-08-15 | [14 empty] | 2014-10-03 | 2014-10-14 |  | Y
Central Hudson |  | Sungevity Inc | CH-09424 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6011 | Sand Dock | N |  | 7.6 | [13 empty] | NM | N | SMA AMERICA SB3800TL-US-22 (2) | 2014-08-12 | 2014-08-15 | 3 | 2014-08-15 | [14 empty] | 2014-11-19 | 2014-11-24 |  | Y
Central Hudson |  | Kirchhoff Green Energy LLC | CH-03539 | Poughkeepsie | Staatsburg | Dutchess | 12580 | G | 7041 | Staatsburg | N |  | 7.5 | [13 empty] | NM | N | FRONIUS 7.5 | 2014-08-18 | 2014-09-02 | 10 | 2014-09-02 | [14 empty] | 2014-10-03 | 2014-10-10 |  | Y
Central Hudson |  | Kirchhoff Green Energy LLC | CH-03545 | Poughkeepsie | Clinton Corners | Dutchess | 12514 | G | 7071 | Stanfordville | N |  | 7.5 | [13 empty] | NM | N | FRONIUS USA 7.5 UNI | 2014-08-13 | 2014-08-15 | 2 | 2014-08-15 | [14 empty] | 2014-10-03 | 2014-10-10 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03694 | Newburgh | New Paltz | Ulster | 12561 | G | 5023 | Ohioville | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000 | 2014-08-15 | 2014-08-15 | 0 | 2014-08-15 | [14 empty] | 2014-10-16 | 2014-10-22 |  | Y
Central Hudson |  | Murphy Solar Power | CH-02761 | Newburgh | Marlboro | Ulster | 12542 | G | 5004 | Marlboro | N |  | 3 | [13 empty] | NM | N | SMA 3000 | 2014-08-13 | 2014-08-15 | 2 | 2014-08-15 | [14 empty] | 2014-09-22 | 2014-09-25 |  | Y
Central Hudson |  | SolarCity | CH-06277 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A-US | 2014-08-13 | 2014-08-15 | 2 | 2014-08-15 | [14 empty] | 2014-08-26 | 2014-09-03 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Verengo Solar | CH-09846 | Newburgh | Maybrook | Orange | 12543 | G | 4026 | Coldenham | N |  | 6.02 | [13 empty] | NM | N | Enphase M215 (28) | 2014-08-13 | 2014-08-15 | 2 | 2014-08-15 | [14 empty] | 2015-01-07 | 2015-01-14 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03695 | Newburgh | New Paltz | Ulster | 12561 | G | 5023 | Ohioville | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000 | 2014-08-14 | 2014-08-18 | 2 | 2014-08-18 | [14 empty] | 2014-10-28 | 2014-11-03 |  | Y
Central Hudson |  | NRG Home Solar | CH-04836 | Newburgh | New Windsor |  | 12553 | G | 4044 | Union Ave | TBD |  | 7.525 | [13 empty] | NM | N | ENPHASE M-215 (35) | 2014-08-14 | 2014-08-18 | 2 | 2014-08-18 | [17 empty] | W |  | Customer already had net meter prior to application. Customer moving forward with project, with a different contractor.
Central Hudson |  | Sungevity Inc | CH-09253 | Newburgh | Walden | Orange | 12586 | G | 5041 | East Walden | N |  | 7.6 | [13 empty] | NM | N | SMA AMERICA SB3800TL-US-22 (2) | 2014-08-14 | 2014-08-18 | 2 | 2014-08-18 | [14 empty] | 2014-11-13 | 2014-11-17 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03636 | Newburgh | Wallkill | Ulster | 12589 | G | 5013 | Modena | N |  | 34.4 | [13 empty] | RNM | N | 4 - POWERONE UNO 8.6 | 2014-08-20 | 2014-08-29 | 7 | 2014-08-29 | [8 empty] | 2000 | 1247.75 |  |  |  |  | 2014-11-17 | 2014-11-25 |  | Y
Central Hudson |  | NRG Home Solar | CH-04523 | Kingston | Kingston | Ulster | 12401 | G | 1022 | East Kingston | N |  | 2.2 | [13 empty] | NM | N | (13)ENPHASE ENERGY M-215-60-2LL-S22-IG | 2014-08-15 | 2014-08-21 | 4 | 2014-08-21 | [14 empty] | 2014-10-15 | 2014-10-22 |  | Y
Central Hudson |  | SolarCity | CH-06290 | Newburgh | Wallkill | Ulster | 12589 | G | 5013 | Modena | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A-US | 2014-08-15 | 2014-08-19 | 2 | 2014-08-19 | [14 empty] | 2014-10-29 | 2014-11-03 |  | Y
Central Hudson |  | Sunrise Solar Solutions, LLC | CH-09661 | Newburgh | Walden | Orange | 12586 | G | 5043 | East Walden | N |  | 6.02 | [13 empty] | NM | N | ENPHASE M215 (28) | 2014-08-15 | 2014-08-19 | 2 | 2014-08-19 | [14 empty] | 2015-05-11 | 2015-05-14 |  | Y
Central Hudson |  | Verengo Solar | CH-09761 | Newburgh | Newburgh | Orange | 12550 | G | 5004 | Marlboro | N |  | 5.375 | [13 empty] | NM | N | ENPHASE ENERGY M215 (25) | 2014-08-15 | 2014-08-19 | 2 | 2014-08-19 | [14 empty] | 2014-10-15 | 2014-10-20 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-03389 | Fishkill | Fishkill | Dutchess | 12524 | G | 8013 | Forgebrook | N |  | 6 | [13 empty] | NM | N | PowerOne PVI-6000-OUTD-US | 2014-08-18 | 2014-08-20 | 2 | 2014-08-20 | [14 empty] | 2014-10-22 | 2014-10-28 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-03491 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6068 | Inwood Ave | N |  | 6 | [13 empty] | NM | N | POWERONE PVI-6000-OUTD-US | 2014-08-18 | 2014-08-20 | 2 | 2014-08-20 | [14 empty] | 2014-11-13 | 2014-11-20 |  | Y
Central Hudson |  | NRG Home Solar | CH-04470 | Newburgh | Marlboro |  | 12542 | G | 5004 | Marlboro | TBD |  | 5.375 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (25) | 2014-08-18 | 2014-08-20 | 2 | 2014-08-20 | [17 empty] | W
Central Hudson |  | NRG Home Solar | CH-04751 | Catskill | Cornwallville |  | 12418 | G | 2043 | South Cairo | TBD |  | 3.44 | [13 empty] | NM | N | (16) ENPHASE ENERGY M-215-60-2LL-S22-IG | 2014-08-18 | 2014-08-22 | 4 | 2014-08-22 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | Hudson Solar | CH-01590 | Newburgh | New Paltz | Ulster | 12561 | G | 5023 | Ohioville | N |  | 10 | [13 empty] | NM | N | SMA America SB5000 (2) | 2014-08-18 | 2014-08-29 | 9 | 2014-08-29 | [14 empty] | 2014-10-22 | 2014-10-28 |  | Y
Central Hudson |  | SolarCity | CH-06373 | Newburgh | Gardiner | Ulster | 12525 | G | 5011 | Modena | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A-US | 2014-08-18 | 2014-08-20 | 2 | 2014-08-20 | [14 empty] | 2014-09-22 | 2014-09-25 |  | Y
Central Hudson |  | SolarCity | CH-06392 | Newburgh | Cornwall | Orange | 12518 | G | 4041 | Union Ave | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A-US | 2014-08-18 | 2014-08-20 | 2 | 2014-08-20 | [14 empty] | 2014-08-27 | 2014-09-03 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Sungevity Inc | CH-09341 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8043 | Myers Corners | N |  | 12.6 | [13 empty] | NM | N | SMA AMERICA SB3800TL (2) & SMA AMERICA SB5000TL (1) | 2014-08-25 | 2014-08-29 | 4 | 2014-08-29 | [14 empty] | 2014-10-30 | 2014-11-06 |  | Y
Central Hudson |  | Sungevity Inc | CH-09472 | Newburgh | Newburgh | Orange | 12550 | G | 4024 | Coldenham | N |  | 7.6 | [13 empty] | NM | N | SMA AMERICA SB3800TL-US (2) | 2014-08-18 | 2014-08-20 | 2 | 2014-08-20 | [14 empty] | 2014-10-31 | 2014-11-05 |  | Y
Central Hudson |  | Verengo Solar | CH-09913 | Newburgh | Newburgh | Orange | 12550 | G | 4024 | Coldenham | N |  | 11.61 | [13 empty] | NM | N | ENPHASE M215 (54) | 2014-08-18 | 2014-08-20 | 2 | 2014-08-20 | [14 empty] | 2015-01-06 | 2015-01-13 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-03413 | Newburgh | Newburgh | Orange | 12550 | G | 4002 | Montgomery St | N |  | 6 | [13 empty] | NM | N | POWERONE PVI-6000-0UTD-US (1) | 2014-08-19 | 2014-08-29 | 8 | 2014-08-29 | [14 empty] | 2014-10-22 | 2014-10-28 |  | Y
Central Hudson |  | NRG Home Solar | CH-04128 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8092 | Fishkill Plains | N |  | 9.03 | [13 empty] | NM | N | ENPHASE ENERGY M215 (42) | 2014-08-19 | 2014-08-29 | 8 | 2014-08-29 | [14 empty] | 2014-12-31 | 2014-12-31 |  | Y
Central Hudson |  | NRG Home Solar | CH-04425 | Fishkill | Hopewell Jct |  | 12533 | G | 8072 | Shenandoah | TBD |  | 5.375 | [13 empty] | NM | N | ENPHASE ENERGY M215 (25) | 2014-08-19 | 2014-08-29 | 8 | 2014-08-29 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | NRG Home Solar | CH-04618 | Fishkill | Hopewell Jct |  | 12533 | G | 8071 | Shenandoah | TBD |  | 6.665 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (31) | 2014-08-19 | 2014-08-28 | 7 | 2014-08-28 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | NRG Home Solar | CH-04706 | Poughkeepsie | Lagrangevl |  | 12540 | G | 6055 | Todd Hill | TBD |  | 10.105 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (47) | 2014-08-19 | 2014-08-29 | 8 | 2014-08-29 | [17 empty] | W
Central Hudson |  | NRG Home Solar | CH-04773 | Fishkill | Hopewell Jct |  | 12533 | G | 8072 | Shenandoah | TBD |  | 8.385 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (39) | 2014-08-19 | 2014-08-28 | 7 | 2014-08-28 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | Hudson Solar | CH-01366 | Newburgh | New Paltz | Ulster | 12561 | G | 5023 | Ohioville | N |  | 9 | [13 empty] | NM | N | SMA America SB 6000 (1) SMA America SB 3000 (1) | 2014-08-21 | 2014-08-29 | 6 | 2014-08-29 | [14 empty] | 2014-11-05 | 2014-11-10 |  | Y
Central Hudson |  | Hudson Solar | CH-01430 | Newburgh | New Paltz | Ulster | 12561 | G | 5023 | Ohioville | N |  | 9 | [13 empty] | NM | N | SMA America SB6000 (1) SMA America SB3000 (1) | 2014-08-19 | 2014-08-29 | 8 | 2014-08-29 | [14 empty] | 2014-12-03 | 2014-12-09 |  | Y
Central Hudson |  | Hudson Solar | CH-01450 | Newburgh | New Paltz | Ulster | 12561 | G | 5023 | Ohioville | N |  | 9 | [13 empty] | NM | N | SMA AMERICA SB6000 (1) SMA AMERICA SB3000 (1) | 2014-08-19 | 2014-08-29 | 8 | 2014-08-29 | [14 empty] | 2014-12-10 | 2014-12-16 |  | Y
Central Hudson |  | Hudson Solar | CH-01465 | Newburgh | New Paltz | Ulster | 12561 | G | 5023 | Ohioville | N |  | 9 | [13 empty] | NM | N | SMA AMERICA SB6000 (1) SMA AMERICA SB3000 (1) | 2014-08-19 | 2014-08-29 | 8 | 2014-08-29 | [14 empty] | 2014-12-26 | 2014-12-31 |  | Y
Central Hudson |  | Hudson Solar | CH-01516 | Newburgh | New Paltz | Ulster | 12561 | G | 5023 | Ohioville | N |  | 9 | [13 empty] | NM | N | SMA AMERICA SB6000 (1) SMA AMERICA SB3000 (1) | 2014-08-19 | 2014-08-29 | 8 | 2014-08-29 | [14 empty] | 2014-12-26 | 2014-12-31 |  | Y
Central Hudson |  | Hudson Solar | CH-01877 | Poughkeepsie | Tivoli |  | 12583 | G | 7051 | Rhinebeck | TBD |  | 7 | [13 empty] | NM | N | SMA America SB7000 (1) | 2014-08-19 | 2014-08-29 | 8 | 2014-08-29 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | Hudson Solar | CH-02160 | Poughkeepsie | Stanfordville | Dutchess | 12581 | G | 7072 | Stanfordville | N |  | 5 | [13 empty] | NM | N | SMA AMERICA SB5000 | 2014-08-26 | 2014-09-04 | 6 | 2014-09-04 | [14 empty] | 2014-12-08 | 2014-12-11 |  | Y
Central Hudson |  | Hudson Solar | CH-02165 | Fishkill | Wappingrs Falls |  | 12590 | G | 8091 | Fishkill Plains | TBD |  | 6 | [13 empty] | NM | N | SMA America SB6000 (1) | 2014-08-19 | 2014-08-29 | 8 | 2014-08-29 | [17 empty] | W
Central Hudson |  | Hudson Solar | CH-02201 | Newburgh | New Paltz | Ulster | 12561 | G | 5023 | Ohioville | N |  | 11 | [13 empty] | NM | N | 1 - SMA America SB6000 1 - SMA America SB5000 | 2014-08-19 | 2014-08-29 | 8 | 2014-08-29 | [14 empty] | 2015-05-04 | 2015-05-11 |  | Y
Central Hudson |  | Hudson Solar | CH-02223 | Newburgh | New Windsor | Orange | 12553 | G | 4095 | Bethlehem Rd | N |  | 6 | [13 empty] | NM | N | SMA America SB 3000 (2) | 2014-08-19 | 2014-08-29 | 8 | 2014-08-29 | [14 empty] | 2014-11-25 | 2014-12-03 |  | Y
Central Hudson |  | SolarCity | CH-06233 | Newburgh | Newburgh | Orange | 12550 | G | 4012 | West Balmville | N |  | 9 | [13 empty] | NM | N | SOLAREDGE SE3000A & SOLAREDGE SE6000A | 2014-08-19 | 2014-08-28 | 7 | 2014-08-28 | [14 empty] | 2014-10-21 | 2014-10-24 |  | Y
Central Hudson |  | SolarCity | CH-06289 | Newburgh | Wallkill | Ulster | 12589 | G | 5013 | Modena | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A-US | 2014-08-26 | 2014-09-04 | 6 | 2014-09-04 | [14 empty] | 2014-10-10 | 2014-10-16 |  | Y
Central Hudson |  | SolarCity | CH-06304 | Newburgh | Newburgh | Orange | 12550 | G | 4011 | West Balmville | N |  | 11 | [13 empty] | NM | N | SOLAREDGE SE5000A & SOLAREDGESE 6000A | 2014-08-19 | 2014-08-28 | 7 | 2014-08-28 | [14 empty] | 2014-10-20 | 2014-10-24 |  | Y
Central Hudson |  | Sungevity Inc | CH-09300 | Kingston | Saugerties | Ulster | 12477 | G | 3002 | Saugerties | N |  | 16 | [13 empty] | NM | N | (2) SMA AMERICA SB8000US-12 | 2014-08-19 | 2014-08-26 | 5 | 2014-08-26 | [8 empty] | 350 | 350 |  |  |  |  | 2014-11-05 | 2014-11-12 |  | Y
Central Hudson |  | Sungevity Inc | CH-09403 | Kingston | Hurley |  | 12443 | G | 2093 | Hurley Ave | TBD |  | 16 | [13 empty] | NM | N | (2)SMA AMERICA 8000-US-12 | 2014-08-19 | 2014-08-26 | 5 | 2014-08-26 | [8 empty] | 350 | 350 | [7 empty] | W |  | Customer already had net meter prior to application. Transformer upgrade required to accommodate PV installation. Utility System Upgrade Costs TBD. 10/3/14 As per contractor, this project has been abandoned.
Central Hudson |  | Sungevity Inc | CH-09456 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8051 | North Chelsea | N |  | 9.8 | [13 empty] | NM | N | SMA America SB3800 & SMA AMERICA SB6000 | 2014-08-19 | 2014-08-29 | 8 | 2014-08-29 | [14 empty] | 2014-11-06 | 2014-11-10 |  | Y
Central Hudson |  | Verengo Solar | CH-09824 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 5.59 | [13 empty] | NM | N | ENPHASE ENERGY M215 (26) | 2014-08-19 | 2014-08-29 | 8 | 2014-08-29 | [14 empty] | 2014-10-15 | 2014-10-20 |  | Y
Central Hudson |  | Verengo Solar | CH-09875 | Newburgh | New Windsor | Orange | 12553 | G | 4054 | Union Ave | N |  | 6.45 | [13 empty] | NM | N | ENPHASE ENERGY M215 (30) | 2014-08-19 | 2014-08-29 | 8 | 2014-08-29 | [14 empty] | 2014-10-15 | 2014-10-21 |  | Y
Central Hudson |  | Paradise Energy Solutions LLC | CH-02846 | Kingston | Hurley | Ulster | 12443 | G | 2094 | Hurley Ave | N | CH-02846 | 5 | [13 empty] | NM | N | (1) SOLAR EDGE SE5000A-US | 2014-08-20 | 2014-08-27 | 5 | 2014-08-27 | [14 empty] | 2014-12-02 | 2014-12-09 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08845 | Catskill | Ravena | Albany | 12143 | G | 1081 | New Baltimore | N |  | 8.17 | [13 empty] | NM | N | (29) ENPHASE ENERGY M215 | 2014-08-20 | 2014-08-27 | 5 | 2014-08-27 | [14 empty] | 2015-07-07 | 2015-07-07 |  | Y
Central Hudson |  | SunDog Solar | CH-09165 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7054 | Rhinebeck | N |  | 9 | [13 empty] | NM | N | ENPHASE ENERGY M250 (36) | 2014-08-27 | 2014-09-05 | 6 | 2014-09-05 | [14 empty] | 2014-10-23 | 2014-10-28 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00893 | Kingston | Olive Brdg | Ulster | 12461 | G | 3024 | High Falls | N |  | 2.79 | [13 empty] | NM | N | (13) ENPHASE M215 60-2LL-S22 | 2014-08-22 | 2014-08-29 | 5 | 2014-08-29 | [14 empty] | 2014-09-16 | 2014-09-23 |  | Y
Central Hudson |  | Green Hybrid Energy Solutions | CH-01162 | Fishkill | Beacon | Dutchess | 12508 | G | 8016 | Forgebrook | N |  | 8.6 | [13 empty] | NM | N | ENPHASE ENERGY M215 (40) | 2014-08-28 | 2014-08-29 | 1 | 2014-08-29 | [14 empty] | 2014-10-28 | 2014-10-28 |  | Y
Central Hudson |  | Sungevity Inc | CH-09379 | Newburgh | Milton | Ulster | 12547 | G | 5002 | Marlboro | N |  | 6.8 | [13 empty] | NM | N | SMA America SB3800 & SMA AMERICASB3000 | 2014-08-22 | 2014-08-29 | 5 | 2014-08-29 | [14 empty] | 2014-10-15 | 2014-10-21 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03684 | Newburgh | New Paltz | Ulster | 12561 | G | 5031 | Galeville | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000 | 2014-08-26 | 2014-09-05 | 7 | 2014-09-05 | [14 empty] | 2014-11-17 | 2014-11-21 |  | Y
Central Hudson |  | Direct Energy Solar | CH-01063 | Kingston | Saugerties | Ulster | 12477 | G | 3004 | Saugerties | N |  | 8.17 | [13 empty] | NM | N | (38) ENPHASE M215 | 2014-08-26 | 2014-09-02 | 4 | 2014-09-02 | [14 empty] | 2014-09-16 | 2014-09-23 |  | Y
Central Hudson |  | Sungevity Inc | CH-09523 | Kingston | Grahamsvl | Sullivan | 12740 | G | 3091 | Neversink | N |  | 13 | [13 empty] | NM | N | (1) SMA AMERICA SB7000US-12 (1) SMA AMERICA SB6000TL-US-22 | 2014-08-26 | 2014-09-02 | 4 | 2014-09-02 | [14 empty] | 2014-10-23 | 2014-10-24 |  | Y
Central Hudson |  | New York State Solar Farm | CH-00457 | Newburgh | Clintondale | Ulster | 12515 | G | 5012 | Modena | N | CH-00457 | 3 | [13 empty] | NM | N | PowerOne PVI-3.0-OUTD-S-US-A (1) | 2014-08-27 | 2014-09-04 | 5 | 2014-09-04 | [14 empty] | 2014-09-30 | 2014-10-06 |  | Y
Central Hudson |  | NRG Home Solar | CH-04139 | Kingston | Saugerties |  | 12477 | G | 3004 | Saugerties | TBD |  | 8.17 | [13 empty] | NM | N | (38) ENPHASE ENERGY M-215-60-2LL-S22-IG | 2014-08-27 | 2014-09-03 | 4 | 2014-09-03 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | NRG Home Solar | CH-04485 | Newburgh | Gardiner | Ulster | 12525 | G | 5033 | Galeville | N |  | 9.675 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (45) | 2014-08-27 | 2014-09-04 | 5 | 2014-09-04 | [8 empty] | 350 | 350 |  |  |  |  | 2014-12-03 | 2014-12-09 |  | Y
Central Hudson |  | NRG Home Solar | CH-04708 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | NYSEG8 | NYSEG | N |  | 6.665 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (31) | 2014-08-27 | 2014-09-04 | 5 | 2014-09-04 | [14 empty] | 2014-12-30 | 2014-12-31 |  | Y
Central Hudson |  | NRG Home Solar | CH-04714 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8091 | Fishkill Plains | N |  | 10.32 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (48) | 2014-08-27 | 2014-09-04 | 5 | 2014-09-04 | [14 empty] | 2014-11-14 | 2014-11-19 |  | Y
Central Hudson |  | NRG Home Solar | CH-04281 | Kingston | Grahamsvl |  | 12740 | G | 3091 | Neversink | TBD |  | 7.31 | [13 empty] | NM | N | (34) ENPHASE ENERGY M-215-60-2LL-S22-IG | 2014-08-28 | 2014-09-05 | 5 | 2014-09-05 | [17 empty] | W |  | Customer already had net meter prior to application. 9/1/14 Company Holiday.
Central Hudson |  | NRG Home Solar | CH-04283 | Kingston | Sundown |  | 12782 | G | 3091 | Neversink | TBD |  | 4.085 | [13 empty] | NM | N |  | 2014-08-28 | 2014-09-05 | 5 | 2014-09-05 | [17 empty] | W |  | Customer already had net meter prior to application. 9/1/14 Company Holiday.
Central Hudson |  | NRG Home Solar | CH-04482 | Newburgh | Marlboro | Ulster | 12542 | G | 5004 | Marlboro | N |  | 4.3 | [13 empty] | NM | N | 20 - ENPHASE ENERGYM-215 | 2014-08-28 | 2014-09-05 | 5 | 2014-09-05 | [14 empty] | 2014-11-04 | 2014-11-07 |  | Y
Central Hudson |  | Pure Point Energy LLC | CH-02943 | Poughkeepsie | Lagrangevl | Dutchess | 12540 | G | 6057 | Todd Hill | N |  | 10 | [13 empty] | NM | N | FRONIUS 10.0 UNI | 2014-09-09 | 2014-09-23 | 10 | 2014-09-23 | [8 empty] | 350 | 350 |  | 2014-10-06 | 2014-10-06 | 2014-10-20 | 2014-10-24 | 2014-10-31 |  | Y
Central Hudson |  | Solar Alchemy | CH-08982 | Kingston | Kerhonkson | Ulster | 12446 | G | 3081 | Kerhonkson | N |  | 15.25 | [13 empty] | NM | N | ENPHASE M250 (61) | 2014-09-17 | 2014-09-17 | 0 | 2014-09-17 | [14 empty] | 2015-07-23 | 2015-07-30 |  | Y
Central Hudson |  | Sungevity Inc | CH-09201 | Newburgh | Newburgh | Orange | 12550 | G | 5004 | Marlboro | N |  | 10.2 | [13 empty] | NM | N | 1 - PVI-4.2-OUTD 1 - PVI-6000-OUTD | 2014-09-05 | 2014-09-11 | 4 | 2014-09-11 | [14 empty] | 2014-10-24 | 2014-10-30 |  | Y
Central Hudson |  | NRG Home Solar | CH-04457 | Newburgh | Newburgh | Orange | 12550 | G | 4015 | West Balmville | N |  | 5.59 | [13 empty] | NM | N | 26 - ENPHASE ENERGY M-215 | 2014-08-29 | 2014-09-08 | 5 | 2014-09-08 | [14 empty] | 2014-11-12 | 2014-11-17 |  | Y
Central Hudson |  | NRG Home Solar | CH-04466 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 5.805 | [13 empty] | NM | N | 27 - ENPHASE ENERGY M-215 | 2014-08-29 | 2014-09-08 | 5 | 2014-09-08 | [14 empty] | 2014-12-01 | 2014-12-08 |  | Y
Central Hudson |  | SolarCity | CH-06531 | Kingston | W Hurley | Ulster | 12491 | G | 3013 | Woodstock | N |  | 8.8 | [13 empty] | NM | N | (1) SOLAREDGE SE5000A-US (1) SOLAREDGE SE3800A-US | 2014-08-29 | 2014-09-08 | 5 | 2014-09-08 | [14 empty] | 2014-12-04 | 2014-12-11 |  | Y
Central Hudson |  | Sungevity Inc | CH-09318 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 7041 | Staatsburg | N |  | 11 | [13 empty] | NM | N | 1 - ABB PVI-6000-OUTD-US-A 1 - ABB PVI-5000-OUTD-US-A | 2014-08-29 | 2014-09-08 | 5 | 2014-09-08 | [14 empty] | 2015-04-28 | 2015-05-05 |  | Y
Central Hudson |  | Sungevity Inc | CH-09328 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 6092 | Manchester | N |  | 7.6 | [13 empty] | NM | N | SMA AMERICA SB3800TL (2) | 2014-09-05 | 2014-09-11 | 4 | 2014-09-11 | [14 empty] | 2014-12-01 | 2014-12-08 |  | Y
Central Hudson |  | Verengo Solar | CH-09883 | Newburgh | New Windsor | Orange | 12553 | G | 4095 | Bethlehem Rd | N |  | 5.375 | [13 empty] | NM | N | ENPHASE ENERGY M215 (25) | 2014-08-29 | 2014-09-05 | 4 | 2014-09-05 | [14 empty] | 2014-11-10 | 2014-11-13 |  | Y
Central Hudson |  | NRG Home Solar | CH-04563 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6092 | Manchester | N |  | 3.87 | [13 empty] | NM | N | Enphase M215 (18) | 2014-09-02 | 2014-09-10 | 6 | 2014-09-10 | [14 empty] | 2015-01-05 | 2015-01-12 |  | Y
Central Hudson |  | Murphy Solar Power | CH-02741 | Catskill | Earlton | Greene | 12058 | G | 2071 | Freehold | N |  | 8 | [13 empty] | NM | N | SMA 8000-US | 2014-09-02 | 2014-09-09 | 5 | 2014-09-09 | [14 empty] | 2014-09-22 | 2014-09-29 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Pure Point Energy LLC | CH-02944 | Poughkeepsie | Pleasant Valley | Dutchess | 12569 | G | 6057 | Todd Hill | N |  | 10 | [13 empty] | NM | N | Fronius 10.0-1 UNI | 2014-09-10 | 2014-09-17 | 5 | 2014-09-17 | [14 empty] | 2014-10-16 | 2014-10-21 |  | Y
Central Hudson |  | Sungevity Inc | CH-09274 | Kingston | High Fls | Ulster | 12440 | G | 3023 | High Falls | N |  | 3.3 | [13 empty] | NM | N | ABB PVI-3.0-OUTD-S-US-A | 2014-09-02 | 2014-09-09 | 5 | 2014-09-09 | [14 empty] | 2014-10-17 | 2014-10-24 |  | Y
Central Hudson |  | Sungevity Inc | CH-09277 | Kingston | Tillson | Ulster | 12486 | G | 3022 | High Falls | N |  | 5 | [13 empty] | NM | N | SMA AMERICA SB5000TL-US-22 | 2014-09-02 | 2014-09-09 | 5 | 2014-09-09 | [14 empty] | 2014-10-29 | 2014-11-04 |  | Y
Central Hudson |  | Verengo Solar | CH-09786 | Newburgh | Newburgh | Orange | 12550 | G | 4024 | Coldenham | N |  | 3.655 | [13 empty] | NM | N | ENPHASE ENERGY M215 (17) | 2014-09-02 | 2014-09-10 | 6 | 2014-09-10 | [14 empty] | 2014-10-20 | 2014-10-23 |  | Y
Central Hudson |  | Verengo Solar | CH-09877 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 6.665 | [13 empty] | NM | N | ENPHASE ENERGY M215 (31) | 2014-09-02 | 2014-09-10 | 6 | 2014-09-10 | [14 empty] | 2014-10-28 | 2014-11-04 |  | Y
Central Hudson |  | Verengo Solar | CH-09911 | Newburgh | Montgomery | Orange | 12549 | G | 5073 | Montgomery | N |  | 6.45 | [13 empty] | NM | N | ENPHASE ENERGY M215 (30) | 2014-09-02 | 2014-09-10 | 6 | 2014-09-10 | [14 empty] | 2014-10-20 | 2014-10-23 |  | Y
Central Hudson |  | Verengo Solar | CH-09920 | Newburgh | Cornwall | Orange | 12518 | G | 4041 | Union Ave | N |  | 15.05 | [13 empty] | NM | N | ENPHASE ENERGY M215 (70) | 2014-10-02 | 2014-10-15 | 9 | 2014-10-15 | [14 empty] | 2014-12-22 | 2014-12-26 |  | Y
Central Hudson |  | Verengo Solar | CH-09930 | Newburgh | Newburgh |  | 12550 | G | 4023 | Coldenham | TBD |  | 11.825 | [13 empty] | NM | N | ENPHASE ENERGY M215 (55) | 2014-09-10 | 2014-09-16 | 4 | 2014-09-16 | [17 empty] | W
Central Hudson |  | Kirchhoff Green Energy LLC | CH-03541 | Newburgh | Esopus | Ulster | 12429 | G | 5084 | Highland | N |  | 6 | [13 empty] | NM | N | SMA (1) SUNNY BOY 6000TL-US | 2014-09-03 | 2014-09-12 | 7 | 2014-09-12 | [14 empty] | 2014-11-18 | 2014-11-25 |  | Y
Central Hudson |  | New York State Solar Farm | CH-03965 | Newburgh | W Park | Ulster | 12493 | G | 5084 | Highland | N |  | 16 | [13 empty] | NM | N | SMA AMERICA (2) SB | 2014-09-03 | 2014-09-12 | 7 | 2014-09-12 | [14 empty] | 2014-10-03 | 2014-10-10 |  | Y
Central Hudson |  | NRG Home Solar | CH-04224 | Newburgh | Wallkill | Ulster | 12589 | G | 5042 | East Walden | N |  | 5.59 | [13 empty] | NM | N | 26 - Enphase M215 | 2014-09-03 | 2014-09-11 | 6 | 2014-09-11 | [14 empty] | 2014-12-03 | 2014-12-09 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00858 | Kingston | Kingston | Ulster | 12401 | G | 1011 | Boulevard | N |  | 9.03 | [13 empty] | NM | N | ENPHASE (42) M215 | 2014-09-03 | 2014-09-12 | 7 | 2014-09-12 | [14 empty] | 2014-10-27 | 2014-11-03 |  | Y
Central Hudson |  | NRG Home Solar | CH-04193 | Poughkeepsie | Verbank | Dutchess | 12585 | G | 6057 | Todd Hill | N |  | 8.815 | [13 empty] | NM | N | ENPHASE ENERGY (41) M-215-60-2LL-S22-IG | 2014-09-04 | 2014-09-11 | 5 | 2014-09-11 | [14 empty] | 2014-12-30 | 2014-12-31 |  | Y
Central Hudson |  | NRG Home Solar | CH-04416 | Fishkill | Beacon | Dutchess | 12508 | G | 8016 | Forgebrook | N |  | 8.815 | [13 empty] | NM | N | ENPHASE ENERGY (41) M-215-60-2LL-S22-IG | 2014-09-11 | 2014-09-17 | 4 | 2014-09-17 | [14 empty] | 2014-11-26 | 2014-12-03 |  | Y
Central Hudson |  | SolarCity | CH-06340 | Newburgh | Gardiner | Ulster | 12525 | G | 5031 | Galeville | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A-US | 2014-09-04 | 2014-09-11 | 5 | 2014-09-11 | [14 empty] | 2014-10-10 | 2014-10-16 |  | Y
Central Hudson |  | Sungevity Inc | CH-09503 | Newburgh | Washingtonvl | Orange | 10992 | G | 4097 | Bethlehem Rd | N | CH-09503 | 8 | [13 empty] | NM | N | SMA AMERICA SB8000 (1) | 2014-09-04 | 2014-09-11 | 5 | 2014-09-11 | [14 empty] | 2014-11-07 | 2014-11-11 |  | Y
Central Hudson |  | NRG Home Solar | CH-04381 | Fishkill | Wappingrs Falls |  | 12590 | G | 8044 | Myers Corners | TBD |  | 5.805 | [13 empty] | NM | N | ENPHASE ENERGY (27) M-215-60-2LL-S22-IG | 2014-09-05 | 2014-09-12 | 5 | 2014-09-12 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | NRG Home Solar | CH-04394 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8092 | Fishkill Plains | N |  | 5.805 | [13 empty] | NM | N | ENPHASE ENERGY (27) M-215-60-2LL-S22-IG | 2014-09-05 | 2014-09-12 | 5 | 2014-09-12 | [14 empty] | 2014-11-26 | 2014-12-03 |  | Y
Central Hudson |  | Solar Maximum LLC, dba RevoluSun | CH-09025 | Newburgh | New Windsor | Orange | 12553 | G | 4095 | Bethlehem Rd | N |  | 18 | [13 empty] | NM | N | (3) SMA AMERICA SB6000TL | 2014-10-06 | 2014-10-16 | 8 | 2014-10-16 | [14 empty] | 2015-03-13 | 2015-03-24 |  | Y
Central Hudson |  | Sungevity Inc | CH-09248 | Kingston | New Paltz | Ulster | 12561 | G | 3041 | Sturgeon Pool | N |  | 8.8 | [13 empty] | NM | N | (1) SMA AMERICA SB3800TL-US-22 (1) SMA AMERICA SB5000TL-US-22 | 2014-09-05 | 2014-09-12 | 5 | 2014-09-12 | [14 empty] | 2014-11-18 | 2014-11-25 |  | Y
Central Hudson |  | Verengo Solar | CH-09879 | Newburgh | Newburgh | Orange | 12550 | G | 5004 | Marlboro | N |  | 9.03 | [13 empty] | NM | N | ENPHASE ENERGY (42) M215-60-2LL-S2X-IG | 2014-09-05 | 2014-09-12 | 5 | 2014-09-12 | [14 empty] | 2014-10-20 | 2014-10-23 |  | Y
Central Hudson |  | NRG Home Solar | CH-04439 | Newburgh | New Paltz | Ulster | 12561 | G | 5031 | Galeville | N |  | 8.815 | [13 empty] | NM | N | ENPHASE ENERGY (41) M-215-60-2LL-S22-IG | 2014-09-08 | 2014-09-15 | 5 | 2014-09-15 | [14 empty] | 2015-08-03 | 2015-08-10 |  | Y
Central Hudson |  | NRG Home Solar | CH-04816 | Poughkeepsie | Red Hook |  | 12571 | G | 7051 | Rhinebeck | TBD |  | 6.45 | [13 empty] | NM | N | ENPHASE ENERGY (30) M-215-60-2LL-S22-IG | 2014-09-08 | 2014-09-16 | 6 | 2014-09-16 | [17 empty] | W
Central Hudson |  | Murphy Solar Power | CH-02749 | Catskill | Athens | Greene | 12015 | G | 1074 | Coxsackie | N |  | 5 | [13 empty] | NM | N | SMA 5000TL-22 | 2014-09-08 | 2014-09-15 | 5 | 2014-09-15 | [14 empty] | 2014-09-22 | 2014-09-29 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Solar Generation | CH-08277 | Kingston | Saugerties | Ulster | 12477 | G | 3003 | Saugerties | N |  | 4 | [13 empty] | NM | N | (1) SMA SB 4000TL | 2014-09-16 | 2014-09-23 | 5 | 2014-09-23 | [14 empty] | 2014-10-21 | 2014-10-27 |  | Y
Central Hudson |  | NRG Home Solar | CH-04570 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6092 | Manchester | N |  | 10.32 | [13 empty] | NM | N | 48 - ENPHASE ENERGY M-215 | 2014-09-09 | 2014-09-16 | 5 | 2014-09-16 | [14 empty] | 2015-02-17 | 2015-02-23 |  | Y
Central Hudson |  | SolarCity | CH-05312 | Newburgh | Wallkill | Ulster | 12589 | G | 5011 | Modena | N |  | 10 | [13 empty] | NM | N | SOLAREDGE (2) SE5000A-US | 2014-09-09 | 2014-09-15 | 4 | 2014-09-15 | [14 empty] | 2015-01-08 | 2015-01-15 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-05947 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7051 | Rhinebeck | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A-US | 2014-09-09 | 2014-09-16 | 5 | 2014-09-16 | [14 empty] | 2014-09-22 | 2014-09-29 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06872 | Fishkill | Hopewell Junction | Dutchess | 12533 | G | 8065 | Merritt Park | N |  | 6.8 | [13 empty] | NM | N | SOLAREDGE SE3000A-US (1) SOLAREDGE SE3800A-US (1) | 2014-09-09 | 2014-09-15 | 4 | 2014-09-15 | [14 empty] | 2014-09-22 | 2014-09-25 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Sungevity Inc | CH-09304 | Kingston | Saugerties | Ulster | 12477 | G | 3001 | Saugerties | N |  | 5 | [13 empty] | NM | N | SMA AMERICA SB5000TL-US-22 | 2014-09-09 | 2014-09-16 | 5 | 2014-09-16 | [14 empty] | 2014-10-17 | 2014-10-24 |  | Y
Central Hudson |  | Sungevity Inc | CH-09348 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8092 | Fishkill Plains | N |  | 6.8 | [13 empty] | NM | N | SMA SB3000TL (1) SMA SB3800TL (1) | 2014-09-09 | 2014-09-15 | 4 | 2014-09-15 | [14 empty] | 2014-11-10 | 2014-11-12 |  | Y
Central Hudson |  | New York State Solar Farm | CH-04000 | Newburgh | Newburgh | Orange | 12550 | G | 4023 | Coldenham | N |  | 15 | [13 empty] | NM | N | POWERONE PVI (3) | 2014-09-10 | 2014-09-17 | 5 | 2014-09-17 | [14 empty] | 2014-10-14 | 2014-10-20 |  | Y
Central Hudson |  | New York State Solar Farm | CH-04013 | Newburgh | Wallkill | Ulster | 12589 | G | 5013 | Modena | N |  | 9.2 | [13 empty] | NM | N | POWER ONE PVI (1) POWER ONE PVI (1) | 2014-09-10 | 2014-09-17 | 5 | 2014-09-17 | [14 empty] | 2014-10-14 | 2014-10-20 |  | Y
Central Hudson |  | SolarCity | CH-06852 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8093 | Fishkill Plains | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE3800A-US (2) | 2014-09-10 | 2014-09-17 | 5 | 2014-09-17 | [14 empty] | 2014-10-14 | 2014-10-20 |  | Y
Central Hudson |  | Sungevity Inc | CH-09368 | Newburgh | Highland | Ulster | 12528 | G | 5022 | Ohioville | N |  | 11 | [13 empty] | NM | N | SMA AMERICA SB6000TL (1) SMA AMERICA SB5000TL (1) | 2014-09-10 | 2014-09-17 | 5 | 2014-09-17 | [14 empty] | 2014-11-19 | 2014-11-20 |  | Y
Central Hudson |  | Sungevity Inc | CH-09445 | Newburgh | Highland | Ulster | 12528 | G | 5082 | Highland | N |  | 6.8 | [13 empty] | NM | N | 1 - ABB PVI-3.0-OUTD-S-US-A & 1 - ABB PVI-3.8-OUTD-S-US-A | 2014-09-10 | 2014-09-15 | 3 | 2014-09-15 | [14 empty] | 2014-12-09 | 2014-12-15 |  | Y
Central Hudson |  | New York State Solar Farm | CH-03939 | Newburgh | Milton | Ulster | 12547 | G | 5083 | Highland | N | CH-03939 | 7 | [13 empty] | NM | N | SMA AMERICA SB (1) | 2014-09-11 | 2014-09-17 | 4 | 2014-09-17 | [14 empty] | 2014-10-16 | 2014-10-22 |  | Y
Central Hudson |  | NRG Home Solar | CH-04163 | Kingston | Kingston | Ulster | 12401 | G | 1024 | East Kingston | N |  | 3.87 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (18) | 2014-09-11 | 2014-09-18 | 5 | 2014-09-18 | [14 empty] | 2014-11-19 | 2014-11-25 |  | Y
Central Hudson |  | NRG Home Solar | CH-04317 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6063 | Inwood Ave | N |  | 7.31 | [13 empty] | NM | N | 34 - ENPHASE ENERGY M-215 | 2014-09-11 | 2014-09-24 | 9 | 2014-09-24 | [14 empty] | 2015-02-11 | 2015-02-19 |  | Y
Central Hudson |  | Hudson Solar | CH-01405 | Newburgh | Highland | Ulster | 12528 | G | 5082 | Highland | N | CH-01405 | 5 | [13 empty] | NM | N | SMA AMERICA SB5000 | 2014-09-11 | 2014-09-24 | 9 | 2014-09-24 | [14 empty] | 2014-12-31 | 2015-01-08 |  | Y
Central Hudson |  | Hudson Solar | CH-01640 | Catskill | New Baltimore | Greene | 12124 | G | 1083 | New Baltimore | N |  | 12 | [13 empty] | NM | N | SMA AMERICA SB6000 (2) | 2014-09-11 | 2014-09-18 | 5 | 2014-09-18 | [8 empty] | 350 | 350 |  |  |  |  | 2014-12-11 | 2014-12-18 |  | Y
Central Hudson |  | Hudson Solar | CH-01816 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 7024 | Tinkertown | N |  | 13 | [13 empty] | NM | N | SMA AMERICA SB5000 (1) SMA AMERICA SB4000 (2) | 2014-09-11 | 2014-09-24 | 9 | 2014-09-24 | [14 empty] | 2014-12-10 | 2014-12-17 |  | Y
Central Hudson |  | Hudson Solar | CH-02059 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6095 | Manchester | N |  | 14 | [13 empty] | NM | N | 1 - SMA AMERICA SB5000 & 1 - SMA AMERICA SB9000 | 2014-09-11 | 2014-09-18 | 5 | 2014-09-18 | [8 empty] | 350 | 350 |  |  |  |  | 2014-12-31 | 2015-01-08 |  | Y
Central Hudson |  | Hudson Solar | CH-02071 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6065 | Inwood Ave | N |  | 10.8 | [13 empty] | NM | N | 1 - SMA SB7000TL & 1 - SMA SB3800TL | 2014-09-11 | 2014-09-18 | 5 | 2014-09-18 | [14 empty] | 2014-10-31 | 2014-11-07 |  | Y
Central Hudson |  | SolarCity | CH-05905 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6056 | Todd Hill | N |  | 3 | [13 empty] | NM | N | SOLAREDGE SE3000A-US | 2014-09-11 | 2014-09-24 | 9 | 2014-09-24 | [14 empty] | 2014-10-21 | 2014-10-28 |  | Y
Central Hudson |  | Sungevity Inc | CH-09436 | Poughkeepsie | Stanfordvl | Dutchess | 12581 | G | 7072 | Stanfordville | N |  | 11 | [13 empty] | NM | N | 1 -SMA AMERICA SB5000TL-US & 1 - SMA AMERICA SB6000TL-US | 2014-09-11 | 2014-09-18 | 5 | 2014-09-18 | [14 empty] | 2015-07-20 | 2015-07-22 |  | Y
Central Hudson |  | Kasselman Solar | CH-03514 | Catskill | Greenvl | Greene | 12083 | G | 2061 | Freehold | N |  | 5.16 | [13 empty] | NM | N | (24) ENPHASE M2515 | 2014-09-12 | 2014-09-19 | 5 | 2014-09-19 | [14 empty] | 2014-10-24 | 2014-10-28 |  | Y
Central Hudson |  | SolarCity | CH-06004 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8091 | Fishkill Plains | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A-US (1) | 2014-09-12 | 2014-09-17 | 3 | 2014-09-17 | [14 empty] | 2014-09-26 | 2014-10-02 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06382 | Newburgh | New Windsor | Orange | 12553 | G | 4093 | Bethlehem Rd | N |  | 10 | [13 empty] | NM | N | 2 - SOLAREDGE SE5000A-US | 2014-09-12 | 2014-09-26 | 10 | 2014-09-26 | [14 empty] | 2014-11-19 | 2014-11-25 |  | Y
Central Hudson |  | Verengo Solar | CH-09842 | Newburgh | Salisbury Mls | Orange | 12577 | G | 4097 | Bethlehem Rd | N |  | 7.31 | [13 empty] | NM | N | ENPHASE ENERGY M215 (34) | 2014-09-12 | 2014-09-18 | 4 | 2014-09-18 | [14 empty] | 2015-06-30 | 2015-07-08 |  | Y
Central Hudson |  | RGS Energy | CH-03038 | Fishkill | Stormvl | Dutchess | 12582 | G | 8071 | Shenandoah | N |  | 5.25 | [13 empty] | NM | N | ENPHASE M250 (21) | 2014-09-15 | 2014-09-19 | 4 | 2014-09-19 | [14 empty] | 2015-04-08 | 2015-04-15 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-03486 | Newburgh | Newburgh | Orange | 12550 | G | 4023 | Coldenham | N |  | 7.5 | [13 empty] | NM | N | FRONIUS IG PLUS (1) | 2014-09-15 | 2014-09-22 | 5 | 2014-09-22 | [14 empty] | 2014-12-12 | 2014-12-17 |  | Y
Central Hudson |  | Murphy Solar Power | CH-02748 | Catskill | Catskill | Greene | 12414 | G | 2003 | North Catskill | N |  | 5 | [13 empty] | NM | N | SMA SB5000 LT-22 | 2014-09-15 | 2014-09-22 | 5 | 2014-09-22 | [14 empty] | 2014-09-26 | 2014-10-03 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Paradise Energy Solutions LLC | CH-02826 | Newburgh | New Paltz | Ulster | 12561 | G | 5011 | Modena | N |  | 8 | [13 empty] | NM | N | SMA SB4000TL (2) | 2014-09-22 | 2014-09-25 | 3 | 2014-09-25 | [14 empty] | 2014-12-17 | 2014-12-22 |  | Y
Central Hudson |  | Paradise Energy Solutions LLC | CH-02832 | Kingston | Kingston | Ulster | 12401 | G | 1021 | East Kingston | N |  | 5 | [13 empty] | NM | N | SolarEdge 5000a-US | 2014-09-23 | 2014-09-23 | 0 | 2014-09-23 | [14 empty] | 2014-12-01 | 2014-12-05 |  | Y
Central Hudson |  | SolarCity | CH-07459 | Newburgh | Wallkill | Ulster | 12589 | G | 5043 | East Walden | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A (1) | 2014-09-15 | 2014-09-22 | 5 | 2014-09-22 | [14 empty] | 2014-10-10 | 2014-10-16 |  | Y
Central Hudson |  | Verengo Solar | CH-09843 | Newburgh | Rock Tvrn | Orange | 12575 | G | 4097 | Bethlehem Rd | N |  | 12.255 | [13 empty] | NM | N | ENPHASE ENERGY M215 (57) | 2014-09-15 | 2014-09-22 | 5 | 2014-09-22 | [14 empty] | 2014-10-28 | 2014-11-04 |  | Y
Central Hudson |  | Verengo Solar | CH-09845 | Newburgh | Maybrook | Orange | 12543 | G | 4026 | Coldenham | N |  | 6.88 | [13 empty] | NM | N | ENPHASE ENERGY M215 (32) | 2014-09-22 | 2014-09-22 | 0 | 2014-09-22 | [14 empty] | 2014-12-18 | 2014-12-26 |  | Y
Central Hudson |  | Verengo Solar | CH-09923 | Newburgh | Salisbury Mls | Orange | 12577 | G | 4097 | Bethlehem Rd | N |  | 6.88 | [13 empty] | NM | N | ENPHASE ENERGY M215 (32) | 2014-10-06 | 2014-10-16 | 8 | 2014-10-16 | [14 empty] | 2014-12-16 | 2014-12-22 |  | Y
Central Hudson |  | NRG Home Solar | CH-04327 | Poughkeepsie | Poughquag | Dutchess | 12570 | G | 6055 | Todd Hill | N |  | 5.805 | [13 empty] | NM | N | 27 - ENPHASE ENERGY M-215 | 2014-09-16 | 2014-09-23 | 5 | 2014-09-23 | [14 empty] | 2014-12-02 | 2014-12-09 |  | Y
Central Hudson |  | NRG Home Solar | CH-04548 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6003 | Reynolds Hill | N |  | 7.095 | [13 empty] | NM | N | 33 - ENPHASE ENERGY M-215 | 2014-09-16 | 2014-09-23 | 5 | 2014-09-23 | [14 empty] | 2015-02-05 | 2015-02-12 |  | Y
Central Hudson |  | NRG Home Solar | CH-04554 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6073 | East Park | N |  | 8.815 | [13 empty] | NM | N | 41 - ENPHASE ENERGY M-215 | 2014-09-16 | 2014-09-23 | 5 | 2014-09-23 | [14 empty] | 2015-01-28 | 2015-02-04 |  | Y
Central Hudson |  | Geo of Camden, LLC dba Solar Universe Camden | CH-01130 | Kingston | Kingston | Ulster | 12401 | G | 2093 | Hurley Ave | N |  | 6.88 | [13 empty] | NM | N | (32) ENPHASE 215-60-2LL-S2X-NA | 2014-09-16 | 2014-09-23 | 5 | 2014-09-23 | [14 empty] | 2015-01-12 | 2015-01-19 |  | Y
Central Hudson |  | Sungevity Inc | CH-09371 | Newburgh | Newburgh | Orange | 12550 | G | 4013 | West Balmville | N |  | 3 | [13 empty] | NM | N | SMA AMERICA SB3000TL (1) | 2014-09-16 | 2014-09-23 | 5 | 2014-09-23 | [14 empty] | 2015-02-27 | 2015-03-06 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-03409 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8092 | Fishkill Plains | N |  | 10 | [13 empty] | NM | N | FRONIUS IG PLUS (1) | 2014-09-17 | 2014-09-23 | 4 | 2014-09-23 | [14 empty] | 2014-12-12 | 2014-12-19 |  | Y
Central Hudson |  | NRG Home Solar | CH-04301 | Kingston | Lk Katrine | Ulster | 12449 | G | 2015 | Lincoln Park | N |  | 11.61 | [13 empty] | NM | N | (54) ENPHASE ENERGY M-215-60-2LL-S22-IG | 2014-09-17 | 2014-09-24 | 5 | 2014-09-24 | [8 empty] | 350 | 350 |  |  |  |  | 2014-11-17 | 2014-11-24 |  | Y
Central Hudson |  | NRG Home Solar | CH-04446 | Newburgh | Newburgh | Orange | 12550 | G | 4013 | West Balmville | N |  | 5.59 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (26) | 2014-09-17 | 2014-09-23 | 4 | 2014-09-23 | [14 empty] | 2014-12-17 | 2014-12-22 |  | Y
Central Hudson |  | NRG Home Solar | CH-04452 | Newburgh | Newburgh | Orange | 12550 | G | 4022 | Coldenham | N |  | 7.31 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (34) | 2014-09-17 | 2014-09-23 | 4 | 2014-09-23 | [14 empty] | 2014-12-02 | 2014-12-09 |  | Y
Central Hudson |  | NRG Home Solar | CH-04484 | Newburgh | Milton | Ulster | 12547 | G | 5083 | Highland | N |  | 10.32 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (48) | 2014-09-17 | 2014-09-23 | 4 | 2014-09-23 | [14 empty] | 2014-12-01 | 2014-12-08 |  | Y
Central Hudson |  | NRG Home Solar | CH-04605 | Fishkill | Fishkill | Dutchess | 12524 | G | 8062 | Merritt Park | N |  | 5.16 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (24) | 2014-09-17 | 2014-09-24 | 5 | 2014-09-24 | [14 empty] | 2014-10-29 | 2014-11-03 |  | Y
Central Hudson |  | NRG Home Solar | CH-04698 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6003 | Reynolds Hill | N |  | 3.44 | [13 empty] | NM | N | 16 - ENPHASE ENERGY M-215 | 2014-09-17 | 2014-09-24 | 5 | 2014-09-24 | [14 empty] | 2014-11-14 | 2014-11-21 |  | Y
Central Hudson |  | NRG Home Solar | CH-04754 | Kingston | Kingston | Ulster | 12401 | G | 1024 | East Kingston | N |  | 3.225 | [13 empty] | NM | N | (15) ENPHASE ENERGY M-215-60-2LL-S22-IG | 2014-09-17 | 2014-09-24 | 5 | 2014-09-24 | [14 empty] | 2015-10-14 | 2015-10-20 |  | Y
Central Hudson |  | NRG Home Solar | CH-04827 | Fishkill | Fishkill |  | 12524 | G | 8064 | Merritt Park | TBD |  | 7.95 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (37) | 2014-09-23 | 2014-09-29 | 4 | 2014-09-29 | [17 empty] | W
Central Hudson |  | SolarCity | CH-06342 | Newburgh | Gardiner | Ulster | 12525 | G | 5031 | Galeville | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A (1) | 2014-09-17 | 2014-09-23 | 4 | 2014-09-23 | [14 empty] | 2014-10-20 | 2014-10-24 |  | Y
Central Hudson |  | NRG Home Solar | CH-04218 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8043 | Myers Corners | N |  | 7.095 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (33) | 2014-09-18 | 2014-09-24 | 4 | 2014-09-24 | [14 empty] | 2015-02-25 | 2015-03-04 |  | Y
Central Hudson |  | NRG Home Solar | CH-04320 | Poughkeepsie | Salt Pt |  | 12578 | G | 7011 | Hibernia | TBD |  | 7.774 | [13 empty] | NM | N | 36 - ENPHASE ENERGY M-215 | 2014-09-18 | 2014-09-24 | 4 | 2014-09-24 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | NRG Home Solar | CH-04419 | Fishkill | Beacon | Dutchess | 12508 | G | 8013 | Forgebrook | N |  | 5.805 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (27) | 2014-09-18 | 2014-09-24 | 4 | 2014-09-24 | [14 empty] | 2014-12-30 | 2015-01-02 |  | Y
Central Hudson |  | NRG Home Solar | CH-04717 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8023 | Knapps Corners | N |  | 5.805 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (27) | 2014-09-18 | 2014-09-24 | 4 | 2014-09-24 | [14 empty] | 2015-02-26 | 2015-03-02 |  | Y
Central Hudson |  | NRG Home Solar | CH-04737 | Newburgh | Highland | Ulster | 12528 | G | 5081 | Highland | N |  | 5.16 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (24) | 2014-09-18 | 2014-09-24 | 4 | 2014-09-24 | [14 empty] | 2014-12-03 | 2014-12-09 |  | Y
Central Hudson |  | SolarCity | CH-05296 | Newburgh | Wallkill | Ulster | 12589 | G | 5041 | East Walden | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE3800A-US (2) | 2014-09-18 | 2014-09-24 | 4 | 2014-09-24 | [14 empty] | 2014-10-21 | 2014-10-24 |  | Y
Central Hudson |  | SolarCity | CH-05426 | Newburgh | Wallkill | Ulster | 12589 | G | 5041 | East Walden | N |  | 8.8 | [13 empty] | NM | N | SOLAREDGE SE5000A-US (1) SOLAREDGE SE3800A-US (1) | 2014-09-18 | 2014-09-24 | 4 | 2014-09-24 | [14 empty] | 2014-10-21 | 2014-10-24 |  | Y
Central Hudson |  | Sungevity Inc | CH-09409 | Kingston | Kingston | Ulster | 12401 | G | 2092 | Hurley Ave | N |  | 11 | [13 empty] | NM | N | (1) SMA AMERICA SB5000TL-US-22 (1) SMA AMERICA SB6000TL-US-22 | 2014-09-18 | 2014-09-25 | 5 | 2014-09-25 | [14 empty] | 2014-11-19 | 2014-11-25 |  | Y
Central Hudson |  | New York State Solar Farm | CH-03961 | Newburgh | Milton | Ulster | 12547 | G | 5003 | Marlboro | N |  | 12 | [13 empty] | NM | N | SMA AMERICA SB (2) | 2014-09-19 | 2014-09-25 | 4 | 2014-09-25 | [14 empty] | 2014-11-06 | 2014-11-10 |  | Y
Central Hudson |  | New York State Solar Farm | CH-04050 | Newburgh | Pine Bush | Orange | 12566 | G | 5033 | Galeville | N |  | 9.8 | [13 empty] | NM | N | POWERONE PVI (1) POWERONE PVI (1) | 2014-09-19 | 2014-09-25 | 4 | 2014-09-25 | [14 empty] | 2014-11-04 | 2014-11-07 |  | Y
Central Hudson |  | New York State Solar Farm | CH-04059 | Kingston | Malden | Ulster | 12477 | G | 3004 | Saugerties | N |  | 6 | [13 empty] | NM | N | SMA AMERICA SB 6.0 | 2014-09-19 | 2014-09-26 | 5 | 2014-09-26 | [14 empty] | 2014-09-30 | 2014-10-07 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | NRG Home Solar | CH-04263 | Kingston | Kingston |  | 12401 | G | 2092 | Hurley Ave | TBD |  | 2.795 | [13 empty] | NM | N | (13) ENPHASE ENERGY M-215-60-2LL-S22-IG | 2014-09-19 | 2014-09-26 | 5 | 2014-09-26 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | OnForce Solar | CH-02801 | Newburgh | Rock Tvrn |  | 12575 | G | 4026 | Coldenham | TBD |  | 6 | [13 empty] | NM | N | SMA SB (1) | 2014-09-19 | 2014-09-25 | 4 | 2014-09-25 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | Sun Mountain | CH-09124 | Kingston | Shokan | Ulster | 12481 | G | 3011 | Woodstock | N |  | 12 | [13 empty] | NM | N | (2) SMA SM6000 US-12 | 2014-09-19 | 2014-09-26 | 5 | 2014-09-26 | [14 empty] | 2014-12-26 | 2014-12-31 |  | Y
Central Hudson |  | Sungevity Inc | CH-09538 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8043 | Myers Corners | N |  | 9.8 | [13 empty] | NM | N | SMA AMERICA SB6000TL-US (1) SMA AMERICA SB3800TL-US (1) | 2014-09-19 | 2014-09-25 | 4 | 2014-09-25 | [14 empty] | 2014-11-12 | 2014-11-17 |  | Y
Central Hudson |  | NRG Home Solar | CH-04844 | Newburgh | Cornwall |  | 12518 | G | 4041 | Union Ave | TBD |  | 7.095 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (33) | 2014-09-22 | 2014-09-26 | 4 | 2014-09-26 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | Quixotic Systems, Inc. | CH-02952 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8023 | Knapps Corners | N |  | 22.8 | [13 empty] | NM | N | 2 - SPR IG Plus 11.4-1 Uno | 2014-10-13 | 2014-10-20 | 5 | 2014-10-20 | [14 empty] | 2014-12-16 | 2014-12-23 |  | Y
Central Hudson |  | Quixotic Systems, Inc. | CH-02953 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8023 | Knapps Corners | N |  | 66.6 | [13 empty] | NM | N | 2 - FRONIUS CL 33.3 DELTA | 2014-11-10 | 2014-12-03 | 15 | 2014-12-03 | 2014-11-10 | 2014-12-03 | 15 | [11 empty] | 2014-12-23 | 2014-12-31 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Sungevity Inc | CH-09259 | Catskill | Potter Holw | Albany | 12469 | G | 1092 | Westerlo | N |  | 12 | [13 empty] | NM | N | 2 - SMA AMERICA SB6000TL-US-22 | 2014-09-22 | 2014-10-06 | 10 | 2014-10-06 | [14 empty] | 2015-01-09 | 2015-01-16 |  | Y
Central Hudson |  | Sungevity Inc | CH-09334 | Newburgh | Highland | Ulster | 12528 | G | 5083 | Highland | N |  | 7.6 | [13 empty] | NM | N | 2 - ABB PVI 3.8 | 2014-09-22 | 2014-09-29 | 5 | 2014-09-29 | [14 empty] | 2014-12-04 | 2014-12-10 |  | Y
Central Hudson |  | Sungevity Inc | CH-09410 | Kingston | Kingston | Ulster | 12401 | G | 2092 | Hurley Ave | N |  | 3.8 | [13 empty] | NM | N | SMA AMERICA SB3800TL-US-22 | 2014-09-22 | 2014-09-29 | 5 | 2014-09-29 | [14 empty] | 2014-11-17 | 2014-11-24 |  | Y
Central Hudson |  | Sungevity Inc | CH-09443 | Newburgh | Highland | Ulster | 12528 | G | 5022 | Ohioville | N |  | 8 | [13 empty] | NM | N | 2 - SMA AMERICA SB4000TL-US-22 | 2014-09-22 | 2014-09-29 | 5 | 2014-09-29 | [14 empty] | 2014-11-24 | 2014-11-24 |  | Y
Central Hudson |  | Verengo Solar | CH-09754 | Newburgh | New Windsor |  | 12553 | G | 4095 | Bethlehem Rd | TBD |  | 11.61 | [13 empty] | NM | N | ENPHASE ENERGY M215 (54) | 2014-09-22 | 2014-09-26 | 4 | 2014-09-26 | [17 empty] | W
Central Hudson |  | Verengo Solar | CH-09866 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8045 | Myers Corners | N |  | 6.02 | [13 empty] | NM | N | ENPHASE ENERGY M215 (28) | 2014-09-22 | 2014-09-26 | 4 | 2014-09-26 | [14 empty] | 2015-02-03 | 2015-02-10 |  | Y
Central Hudson |  | Verengo Solar | CH-09891 | Newburgh | New Windsor | Orange | 12553 | G | 4094 | Bethlehem Rd | N |  | 3.655 | [13 empty] | NM | N | ENPHASE ENERGY M215 (17) | 2014-09-22 | 2014-09-26 | 4 | 2014-09-26 | [14 empty] | 2014-11-07 | 2014-11-12 |  | Y
Central Hudson |  | Verengo Solar | CH-09901 | Newburgh | Newburgh | Orange | 12550 | G | 5001 | Marlboro | N |  | 6.235 | [13 empty] | NM | N | ENPHASE ENERGY M215 (29) | 2014-09-22 | 2014-09-26 | 4 | 2014-09-26 | [14 empty] | 2015-06-01 | 2015-06-08 |  | Y
Central Hudson |  | Verengo Solar | CH-09924 | Poughkeepsie | Pleasant Vly |  | 12569 | G | 7024 | Tinkertown | TBD |  | 4.3 | [13 empty] | NM | N | 20 - ENPHASE M215 | 2014-09-22 | 2014-09-29 | 5 | 2014-09-29 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | Verengo Solar | CH-09931 | Newburgh | Milton |  | 12547 | G | 5003 | Marlboro | TBD |  | 8.17 | [13 empty] | NM | N | ENPHASE ENERGY M215 (38) | 2014-09-22 | 2014-09-26 | 4 | 2014-09-26 | [17 empty] | W
Central Hudson |  | Geo of Camden, LLC dba Solar Universe Camden | CH-01131 | Newburgh | Modena | Ulster | 12548 | G | 5012 | Modena | N |  | 2.58 | [13 empty] | NM | N | ENPHASE M215 (12) | 2014-09-23 | 2014-09-29 | 4 | 2014-09-29 | [14 empty] | 2015-03-18 | 2015-03-19 |  | Y
Central Hudson |  | SolarCity | CH-06566 | Kingston | Kerhonkson | Ulster | 12446 | G | 3082 | Kerhonkson | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A-US-ZB-U | 2014-09-23 | 2014-09-30 | 5 | 2014-09-30 | [14 empty] | 2014-10-03 | 2014-10-10 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Solar Generation | CH-08299 | Kingston | Boicevl | Ulster | 12412 | G | 3011 | Woodstock | N |  | 10 | [13 empty] | NM | N | (1) SMA SB 6000 TL (1) SMA SB 4000 TL | 2014-09-23 | 2014-09-30 | 5 | 2014-09-30 | [14 empty] | 2014-12-16 | 2014-12-23 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03583 | Kingston | Tillson | Ulster | 12486 | G | 3021 | High Falls | N | CH-03583 | 13.6 | [13 empty] | NM | N | (1) SOLAREDGE SE7600A US (1) SOLAREDGE SE6000A US | 2014-09-24 | 2014-10-01 | 5 | 2014-10-01 | [14 empty] | 2014-11-25 | 2014-12-02 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03716 | Newburgh | Gardiner | Ulster | 12525 | G | 5031 | Galeville | N |  | 17.6 | [13 empty] | NM | N | 2 - ABB PVI 5000 1 - POWERONE UNO 7.6-TL | 2014-09-24 | 2014-10-08 | 10 | 2014-10-08 | [14 empty] | 2014-12-31 | 2014-12-31 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03759 | Newburgh | Highland | Ulster | 12528 | G | 5081 | Highland | N |  | 13.6 | [13 empty] | NM | N | SOLAREDGE SE7600A (1) SOLAREDGE SE6000A (1) | 2014-09-24 | 2014-10-03 | 7 | 2014-10-03 | [14 empty] | 2014-12-05 | 2014-12-11 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03811 | Fishkill | Cold Spg | Putnam | 10516 | G | 8087 | Tioronda | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE7600A (1) | 2014-09-24 | 2014-10-03 | 7 | 2014-10-03 | [14 empty] | 2015-09-04 | 2015-09-14 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03829 | Newburgh | New Paltz | Ulster | 12561 | G | 5021 | Ohioville | N | CH-02196 | 7.6 | [13 empty] | NM | N | SOLAREDGE SE7600A (1) | 2014-09-24 | 2014-10-02 | 6 | 2014-10-02 | [8 empty] | 350 | 350 |  |  |  |  | 2014-11-20 | 2014-11-25 |  | Y
Central Hudson |  | SolarCity | CH-04946 | Newburgh | Highland | Ulster | 12528 | G | 5081 | Highland | N |  | 10 | [13 empty] | NM | N | 2 - SOLAREDGE SE5000A | 2014-09-24 | 2014-10-08 | 10 | 2014-10-08 | [14 empty] | 2014-11-11 | 2014-11-18 |  | Y
Central Hudson |  | SolarCity | CH-05041 | Poughkeepsie | Milan | Dutchess | 12571 | G | 7061 | Milan | N |  | 10 | [13 empty] | NM | N | 2 - SOLAREDGE SE5000A | 2014-09-24 | 2014-10-08 | 10 | 2014-10-08 | [14 empty] | 2014-10-21 | 2014-10-28 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-05072 | Newburgh | Newburgh | Orange | 12550 | G | 5004 | Marlboro | N |  | 10 | [13 empty] | NM | N | SOLAREDGE SE5000A-US (2) | 2014-10-01 | 2014-10-10 | 7 | 2014-10-10 | [14 empty] | 2014-10-27 | 2014-11-03 |  | Y
Central Hudson |  | SolarCity | CH-05153 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6011 | Sand Dock | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A | 2014-09-24 | 2014-10-08 | 10 | 2014-10-08 | [14 empty] | 2014-11-13 | 2014-11-20 |  | Y
Central Hudson |  | SolarCity | CH-05378 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 7041 | Staatsburg | N |  | 9.8 | [13 empty] | NM | N | 1 - SOLAREDGE SE6000A 1 - SOLAREDGE SE3800A | 2014-09-24 | 2014-10-08 | 10 | 2014-10-08 | [14 empty] | 2015-02-02 | 2015-02-09 |  | Y
Central Hudson |  | SolarCity | CH-05393 | Newburgh | Newburgh | Orange | 12550 | G | 4015 | West Balmville | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE3800A (2) | 2014-09-24 | 2014-10-03 | 7 | 2014-10-03 | [14 empty] | 2014-10-20 | 2014-10-27 |  | Y
Central Hudson |  | SolarCity | CH-05576 | Catskill | Athens | Greene | 12015 | G | 2002 | North Catskill | N |  | 7.6 | [13 empty] | NM | N | (2) SOLAREDGE SE3800A US-ZB-U | 2014-09-24 | 2014-10-01 | 5 | 2014-10-01 | [14 empty] | 2015-01-29 | 2015-02-05 |  | Y
Central Hudson |  | SolarCity | CH-05675 | Kingston | Kingston | Ulster | 12401 | G | 1022 | East Kingston | N |  | 7.6 | [13 empty] | NM | N | (2) SOLAREDGE SE3800A US-ZB-U | 2014-09-24 | 2014-10-01 | 5 | 2014-10-01 | [14 empty] | 2014-10-20 | 2014-10-27 |  | Y
Central Hudson |  | SolarCity | CH-05793 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6011 | Sand Dock | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A | 2014-09-24 | 2014-10-03 | 7 | 2014-10-03 | [14 empty] | 2014-10-28 | 2014-11-04 |  | Y
Central Hudson |  | SolarCity | CH-05886 | Poughkeepsie | Verbank | Dutchess | 12585 | G | 7025 | Tinkertown | N |  | 12 | [13 empty] | NM | N | 2 - SOLAREDGE #SE6000A | 2014-09-24 | 2014-10-08 | 10 | 2014-10-08 | [14 empty] | 2015-01-30 | 2015-02-06 |  | Y
Central Hudson |  | SolarCity | CH-05903 | Poughkeepsie | Clinton Corners | Dutchess | 12514 | G | 7071 | Stanfordville | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A | 2014-09-24 | 2014-10-08 | 10 | 2014-10-08 | [14 empty] | 2014-10-21 | 2014-10-28 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-05914 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 6051 | Todd Hill | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A | 2014-09-24 | 2014-10-08 | 10 | 2014-10-08 | [14 empty] | 2014-11-26 | 2014-12-05 |  | Y
Central Hudson |  | SolarCity | CH-05940 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6002 | Reynolds Hill | N |  | 3.8 | [13 empty] | NM | N | SOLAREDGE SE3800A-US | 2014-11-25 | 2014-12-04 | 5 | 2014-12-04 | [14 empty] | 2014-12-26 | 2014-12-31 |  | Y
Central Hudson |  | SolarCity | CH-05985 | Newburgh | Highland | Ulster | 12528 | G | 5082 | Highland | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A-US | 2014-09-24 | 2014-10-08 | 10 | 2014-10-08 | [14 empty] | 2014-11-26 | 2014-12-05 |  | Y
Central Hudson |  | SolarCity | CH-06026 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8052 | North Chelsea | N |  | 3 | [13 empty] | NM | N | SOLAREDGE SE3000A (1) | 2014-09-24 | 2014-10-03 | 7 | 2014-10-03 | [14 empty] | 2014-12-26 | 2014-12-31 |  | Y
Central Hudson |  | SolarCity | CH-06031 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8024 | Knapps Corners | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A-US (1) | 2014-10-03 | 2014-10-15 | 8 | 2014-10-15 | [14 empty] | 2014-12-02 | 2014-12-09 |  | Y
Central Hudson |  | SolarCity | CH-06032 | Fishkill | Wappingrs Falls |  | 12590 | G | 8024 | Knapps Corners | TBD |  | 3 | [13 empty] | NM | N | SOLAREDGE SE3000A (1) | 2014-09-24 | 2014-10-03 | 7 | 2014-10-03 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | SolarCity | CH-06048 | Fishkill | Stormvl | Dutchess | 12582 | G | 8093 | Fishkill Plains | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A (1) | 2014-09-24 | 2014-10-03 | 7 | 2014-10-03 | [14 empty] | 2014-10-10 | 2014-10-16 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06061 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8093 | Fishkill Plains | N |  | 8 | [13 empty] | NM | N | SOLAREDGE SE5000A (1) SOLAREDGE SE3000A (1) | 2014-09-24 | 2014-10-03 | 7 | 2014-10-03 | [14 empty] | 2014-10-27 | 2014-10-31 |  | Y
Central Hudson |  | SolarCity | CH-06134 | Fishkill | Beacon | Dutchess | 12508 | G | 8017 | Forgebrook | N |  | 9 | [13 empty] | NM | N | SOLAREDGE SE6000A (2) | 2014-09-24 | 2014-10-03 | 7 | 2014-10-03 | [14 empty] | 2014-10-10 | 2014-10-16 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06151 | Fishkill | Beacon | Dutchess | 12508 | G | 8087 | Tioronda | N |  | 9 | [13 empty] | NM | N | SOLAREDGE SE6000A (2) | 2014-09-24 | 2014-10-03 | 7 | 2014-10-03 | [14 empty] | 2014-10-27 | 2014-10-31 |  | Y
Central Hudson |  | SolarCity | CH-06182 | Newburgh | Clintondale | Ulster | 12515 | G | 5024 | Ohioville | N | CH-06182 | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A-US | 2015-01-22 | 2015-02-05 | 10 | 2015-02-05 | [14 empty] | 2015-02-19 | 2015-02-19 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06265 | Newburgh | Newburgh | Orange | 12550 | G | 4052 | Union Ave | N |  | 3 | [13 empty] | NM | N | SOLAREDGE SE3000A (1) | 2014-09-24 | 2014-10-03 | 7 | 2014-10-03 | [14 empty] | 2014-11-18 | 2014-11-21 |  | Y
Central Hudson |  | SolarCity | CH-06310 | Newburgh | Newburgh | Orange | 12550 | G | 4011 | West Balmville | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE3800A (2) | 2014-09-24 | 2014-10-03 | 7 | 2014-10-03 | [14 empty] | 2014-10-07 | 2014-10-14 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06319 | Newburgh | Marlboro | Ulster | 12542 | G | 5004 | Marlboro | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A (1) | 2014-09-24 | 2014-10-03 | 7 | 2014-10-03 | [14 empty] | 2014-10-07 | 2014-10-14 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06375 | Newburgh | Gardiner | Ulster | 12525 | G | 5011 | Modena | N |  | 6.8 | [13 empty] | NM | N | SOLAREDGE SE3800A-US (1) SOLAREDGE SE3000A-US (1) | 2014-10-08 | 2014-10-17 | 7 | 2014-10-17 | [8 empty] | 350 | 350 |  |  |  |  | 2014-11-25 | 2014-12-03 |  | Y
Central Hudson |  | SolarCity | CH-06529 | Kingston | W Hurley | Ulster | 12491 | G | 3013 | Woodstock | N |  | 9 | [13 empty] | NM | N | (1) SOLAREDGE SE6000A US-ZB-U (1) SOLAREDGE SE3000A US-ZB-U | 2014-09-24 | 2014-10-01 | 5 | 2014-10-01 | [14 empty] | 2015-01-12 | 2015-01-19 |  | Y
Central Hudson |  | SolarCity | CH-06583 | Kingston | Woodstock | Ulster | 12498 | G | 3014 | Woodstock | N |  | 3.8 | [13 empty] | NM | N | SOLAREDGE SE3800A US-ZB-U | 2014-09-24 | 2014-09-30 | 4 | 2014-09-30 | [14 empty] | 2014-11-26 | 2014-12-03 |  | Y
Central Hudson |  | SolarCity | CH-06657 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6094 | Manchester | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A | 2014-09-24 | 2014-10-08 | 10 | 2014-10-08 | [14 empty] | 2014-11-26 | 2014-12-05 |  | Y
Central Hudson |  | SolarCity | CH-06706 | Poughkeepsie | Lagrangevl | Dutchess | 12540 | G | 6053 | Todd Hill | N |  | 7.6 | [13 empty] | NM | N | 1 - SOLAREDGE SE7600A-US | 2014-10-17 | 2014-10-27 | 6 | 2014-10-27 | [14 empty] | 2015-01-05 | 2015-01-12 |  | Y
Central Hudson |  | SolarCity | CH-06717 | Poughkeepsie | Clinton Corners | Dutchess | 12514 | G | 7071 | Stanfordville | N |  | 9.8 | [13 empty] | NM | N | 1 - SOLAREDGE SE6000A 1 - SOLAREDGE SE3800A | 2014-09-24 | 2014-10-08 | 10 | 2014-10-08 | [14 empty] | 2014-11-26 | 2014-12-05 |  | Y
Central Hudson |  | SolarCity | CH-06782 | Newburgh | Highland | Ulster | 12528 | G | 5083 | Highland | N |  | 9.8 | [13 empty] | NM | N | 1 - SOLAREDGE SE6000A 1 - SOLAREDGE SE3800A | 2014-09-24 | 2014-10-08 | 10 | 2014-10-08 | [14 empty] | 2014-12-23 | 2014-12-30 |  | Y
Central Hudson |  | SolarCity | CH-06812 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8044 | Myers Corners | N |  | 11 | [13 empty] | NM | N | SOLAREDGE SE6000A (1) SOLAREDGE SE5000A (1) | 2014-09-24 | 2014-10-03 | 7 | 2014-10-03 | [14 empty] | 2014-10-27 | 2014-10-31 |  | Y
Central Hudson |  | SolarCity | CH-06890 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8056 | North Chelsea | N |  | 3.8 | [13 empty] | NM | N | SOLAREDGE SE3800A (1) | 2014-09-24 | 2014-10-03 | 7 | 2014-10-03 | [14 empty] | 2014-10-22 | 2014-10-28 |  | Y
Central Hudson |  | SolarCity | CH-06916 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8093 | Fishkill Plains | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A (1) | 2014-09-24 | 2014-10-03 | 7 | 2014-10-03 | [14 empty] | 2014-11-04 | 2014-11-07 |  | Y
Central Hudson |  | SolarCity | CH-06983 | Newburgh | Newburgh | Orange | 12550 | G | 4022 | Coldenham | N |  | 3.8 | [13 empty] | NM | N | SOLAREDGE SE3800A (1) | 2014-09-24 | 2014-10-03 | 7 | 2014-10-03 | [14 empty] | 2014-11-26 | 2014-12-03 |  | Y
Central Hudson |  | SolarCity | CH-07054 | Newburgh | Wallkill | Ulster | 12589 | G | 4011 | West Balmville | N |  | 10 | [13 empty] | NM | N | SOLAREDGE SE5000A-US (2) | 2014-10-08 | 2014-10-17 | 7 | 2014-10-17 | [14 empty] | 2014-10-27 | 2014-10-31 |  | Y
Central Hudson |  | SolarCity | CH-07138 | Newburgh | Campbell Hall | Orange | 10916 | G | 5052 | Maybrook | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A (1) | 2014-09-24 | 2014-10-03 | 7 | 2014-10-03 | [14 empty] | 2014-11-13 | 2014-11-17 |  | Y
Central Hudson |  | SolarCity | CH-07225 | Kingston | Hurley | Ulster | 12443 | G | 2093 | Hurley Ave | N |  | 3.8 | [13 empty] | NM | N | SOLAREDGE SE3800A | 2014-09-24 | 2014-09-30 | 4 | 2014-09-30 | [14 empty] | 2014-12-15 | 2014-12-22 |  | Y
Central Hudson |  | SolarCity | CH-07263 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6003 | Reynolds Hill | N |  | 3.8 | [13 empty] | NM | N | SOLAREDGE SE3800A | 2014-09-24 | 2014-10-08 | 10 | 2014-10-08 | [14 empty] | 2015-01-15 | 2015-01-22 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07327 | Newburgh | Highland | Ulster | 12528 | G | 5083 | Highland | N |  | 9.8 | [13 empty] | NM | N | 1 - SOLAREDGE SE3800A-US 1 - SOLAREDGE SE6000A-US | 2014-09-24 | 2014-10-08 | 10 | 2014-10-08 | [14 empty] | 2014-10-13 | 2014-10-20 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07482 | Newburgh | New Windsor | Orange | 12553 | G | 4094 | Bethlehem Rd | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE3800A (2) | 2014-09-24 | 2014-10-03 | 7 | 2014-10-03 | [14 empty] | 2014-10-27 | 2014-10-31 |  | Y
Central Hudson |  | SolarCity | CH-07772 | Fishkill | Wappingrs Fls |  | 12590 | G | 8092 | Fishkill Plains | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A (1) | 2014-09-24 | 2014-10-03 | 7 | 2014-10-03 | [14 empty] | 2014-11-07 | 2014-11-11 |  | W
Central Hudson |  | SolarCity | CH-07789 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8043 | Myers Corners | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A-US (1) | 2014-10-03 | 2014-10-15 | 8 | 2014-10-15 | [14 empty] | 2014-12-04 | 2014-12-10 |  | Y
Central Hudson |  | SolarCity | CH-07813 | Poughkeepsie | Staatsburg | Dutchess | 12580 | G | 7042 | Staatsburg | N | CH-06697 | 7.6 | [13 empty] | NM | N | SOLAREDGE SE7600A | 2014-10-23 | 2014-10-30 | 5 | 2014-10-30 | [8 empty] | 350 | 350 |  |  |  |  | 2014-12-12 | 2014-12-18 |  | Y
Central Hudson |  | SolarCity | CH-07894 | Fishkill | Hopewell Jct |  | 12533 | G | 8071 | Shenandoah | TBD |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A (1) | 2014-10-01 | 2014-10-10 | 7 | 2014-10-10 | [17 empty] | W
Central Hudson |  | Sungevity Inc | CH-09180 | Kingston | Accord | Ulster | 12404 | G | 3024 | High Falls | N |  | 5 | [13 empty] | NM | N | SMA AMERICA SB5000TL-US-22 | 2014-09-24 | 2014-10-01 | 5 | 2014-10-01 | [14 empty] | 2014-12-11 | 2014-12-18 |  | Y
Central Hudson |  | Sungevity Inc | CH-09507 | Newburgh | Campbell Hall | Orange | 10916 | G | 5052 | Maybrook | N |  | 6.8 | [13 empty] | NM | N | SMA SB3800TL (1) SMA SB3000TL (1) | 2014-09-24 | 2014-10-03 | 7 | 2014-10-03 | [14 empty] | 2014-11-24 | 2014-12-03 |  | Y
Central Hudson |  | Verengo Solar | CH-09888 | Newburgh | New Windsor | Orange | 12553 | G | 4095 | Bethlehem Rd | N |  | 6.665 | [13 empty] | NM | N | ENPHASE ENERGY M215 (31) | 2014-09-24 | 2014-10-03 | 7 | 2014-10-03 | [14 empty] | 2014-11-13 | 2014-11-17 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-03399 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6046 | Spackenkill | N |  | 6 | [13 empty] | NM | N | FRONIUS IG PLUS A 6.0 | 2014-09-25 | 2014-10-09 | 10 | 2014-10-09 | [14 empty] | 2014-12-02 | 2014-12-09 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-03506 | Fishkill | Hopewell Jct |  | 12533 | G | 8094 | Fishkill Plains | TBD |  | 8 | [13 empty] | NM | N | SMA AMERICA SB8000US (1) | 2014-09-25 | 2014-10-06 | 7 | 2014-10-06 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | NRG Home Solar | CH-04445 | Newburgh | Newburgh |  | 12550 | G | 5041 | East Walden | TBD |  | 8.815 | [13 empty] | NM | N | ENPHASE ENERGYM-215 (41) | 2014-09-25 | 2014-10-02 | 5 | 2014-10-02 | [17 empty] | W |  | Transformer upgrade required to accommodate PV installation. Utility System Upgrade Costs TBD.
Central Hudson |  | Hudson Solar | CH-01294 | Kingston | Woodstock | Ulster | 12498 | G | 3014 | Woodstock | N |  | 3.8 | [13 empty] | NM | N | SMA AMERICA SB3800 (1) | 2014-09-25 | 2014-10-02 | 5 | 2014-10-02 | [14 empty] | 2014-12-09 | 2014-12-16 |  | Y
Central Hudson |  | SolarCity | CH-04986 | Catskill | Ravena | Albany | 12143 | G | 1083 | New Baltimore | N |  | 12 | [13 empty] | NM | N | (2) SOLAREDGE SE6000A US-ZB-U | 2014-09-25 | 2014-10-02 | 5 | 2014-10-02 | [14 empty] | 2014-10-28 | 2014-11-03 |  | Y
Central Hudson |  | SolarCity | CH-04998 | Kingston | Hurley | Ulster | 12443 | G | 2093 | Hurley Ave | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A-US-ZB-U | 2014-09-25 | 2014-10-02 | 5 | 2014-10-02 | [14 empty] | 2014-10-20 | 2014-10-27 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-05071 | Newburgh | Newburgh | Orange | 12550 | G | 4011 | West Balmville | N |  | 11 | [13 empty] | NM | N | SOLAREDGE SE6000A (1) SOLAREDGE SE5000A (1) | 2015-02-17 | 2015-02-24 | 5 | 2015-02-24 | [14 empty] | 2015-03-06 | 2015-03-06 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-05287 | Newburgh | Newburgh | Orange | 12550 | G | 4023 | Coldenham | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A (1) | 2014-09-25 | 2014-10-06 | 7 | 2014-10-06 | [14 empty] | 2014-10-29 | 2014-11-03 |  | Y
Central Hudson |  | SolarCity | CH-05288 | Newburgh | Newburgh | Orange | 12550 | G | 4023 | Coldenham | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A-US (1) | 2014-10-02 | 2014-10-15 | 9 | 2014-10-15 | [14 empty] | 2014-11-11 | 2014-11-13 |  | Y
Central Hudson |  | SolarCity | CH-05331 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8091 | Fishkill Plains | N |  | 6.8 | [13 empty] | NM | N | SOLAREDGE SE3800A (1) SOLAREDGE 3000A (1) | 2014-09-25 | 2014-10-06 | 7 | 2014-10-06 | [14 empty] | 2014-10-21 | 2014-10-27 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-05395 | Newburgh | Milton | Ulster | 12547 | G | 5083 | Highland | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE3800A (2) | 2014-09-25 | 2014-10-06 | 7 | 2014-10-06 | [14 empty] | 2014-10-21 | 2014-10-24 |  | Y
Central Hudson |  | SolarCity | CH-05588 | Catskill | Coxsackie | Greene | 12051 | G | 1076 | Coxsackie | N |  | 6.8 | [13 empty] | NM | N | SOLAREDGE SE3000A US SOLAREDGE SE3800A US | 2014-09-25 | 2014-10-02 | 5 | 2014-10-02 | [14 empty] | 2014-11-03 | 2014-11-07 |  | Y
Central Hudson |  | SolarCity | CH-05593 | Catskill | Ravena | Albany | 12143 | G | 1081 | New Baltimore | N |  | 12 | [13 empty] | NM | N | (2) SOLAREDGE SE6000A US-ZB-U | 2014-09-25 | 2014-10-02 | 5 | 2014-10-02 | [8 empty] | 350 | 350 |  |  |  |  | 2014-11-26 | 2014-12-03 |  | Y
Central Hudson |  | SolarCity | CH-05612 | Kingston | Accord | Ulster | 12404 | G | 3024 | High Falls | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A US-ZB-U | 2014-09-25 | 2014-10-02 | 5 | 2014-10-02 | [14 empty] | 2014-12-15 | 2014-12-22 |  | Y
Central Hudson |  | SolarCity | CH-05850 | Poughkeepsie | Hyde Pk |  | 12538 | G | 7041 | Staatsburg | TBD |  | 3.8 | [13 empty] | NM | N | SOLAREDGE SE3800A-US | 2014-10-06 | 2014-10-17 | 9 | 2014-10-17 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | SolarCity | CH-05944 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7056 | Rhinebeck | N |  | 18 | [13 empty] | NM | N | 3 - SOLAREDGE SE6000A-US | 2014-09-25 | 2014-10-09 | 10 | 2014-10-09 | [14 empty] | 2015-03-19 | 2015-03-26 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-05945 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7056 | Rhinebeck | N |  | 8.8 | [13 empty] | NM | N | 1 - SOLAREDGE SE3800-US 1 - SOLAREDGE SE5000-US | 2014-12-11 | 2014-12-18 | 5 | 2014-12-18 | [14 empty] | 2014-12-26 | 2014-12-31 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-05987 | Newburgh | Highland | Ulster | 12528 | G | 5084 | Highland | N | CH-05987 | 6 | [13 empty] | NM | N | SOLARADGE SE6000A | 2014-09-25 | 2014-10-09 | 10 | 2014-10-09 | [14 empty] | 2014-10-13 | 2014-10-20 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-05999 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8091 | Fishkill Plains | N |  | 8 | [13 empty] | NM | N | SOLAREDGE SE5000A (1) SOLAREDGESE3000A(1) | 2014-09-25 | 2014-10-06 | 7 | 2014-10-06 | [14 empty] | 2014-10-10 | 2014-10-16 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06124 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8093 | Fishkill Plains | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A (1) | 2014-09-25 | 2014-10-06 | 7 | 2014-10-06 | [14 empty] | 2014-12-03 | 2014-12-09 |  | Y
Central Hudson |  | SolarCity | CH-06131 | Fishkill | Stormvl | Dutchess | 12582 | G | 8093 | Fishkill Plains | N |  | 6.8 | [13 empty] | NM | N | SOLAREDGE SE3800A-US (1) SOLAREDGE SE3000A-US (1) | 2014-10-02 | 2014-10-15 | 9 | 2014-10-15 | [14 empty] | 2014-11-26 | 2014-12-03 |  | Y
Central Hudson |  | SolarCity | CH-06133 | Fishkill | Beacon | Dutchess | 12508 | G | 8017 | Forgebrook | N |  | 8 | [13 empty] | NM | N | SOLAREDGE SE5000A-US (1) SOLAREDGE SE3000A-US (1) | 2014-10-02 | 2014-10-15 | 9 | 2014-10-15 | [14 empty] | 2014-11-21 | 2014-12-01 |  | Y
Central Hudson |  | SolarCity | CH-06303 | Newburgh | Newburgh | Orange | 12550 | G | 4011 | West Balmville | N |  | 4.2 | [13 empty] | NM | N | ABB PVI 4.2 | 2014-10-02 | 2014-10-15 | 9 | 2014-10-15 | [14 empty] | 2014-12-22 | 2014-12-30 |  | Y
Central Hudson |  | SolarCity | CH-06434 | Catskill | Catskill | Greene | 12414 | G | 2001 | North Catskill | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A US-ZB-U | 2014-09-25 | 2014-10-02 | 5 | 2014-10-02 | [14 empty] | 2014-11-06 | 2014-11-13 |  | Y
Central Hudson |  | SolarCity | CH-06459 | Catskill | Greenvl | Greene | 12083 | G | 2061 | Freehold | N |  | 10 | [13 empty] | NM | N | (2)SOLAREDGE SE5000A-US-ZB-U | 2014-09-25 | 2014-10-02 | 5 | 2014-10-02 | [14 empty] | 2014-10-21 | 2014-10-27 |  | Y
Central Hudson |  | SolarCity | CH-06519 | Kingston | Port Ewen | Ulster | 12466 | G | 1012 | Boulevard | N |  | 18 | [13 empty] | NM | N | (3) SOLAREDGE SE6000A US-ZB-U | 2014-09-25 | 2014-10-02 | 5 | 2014-10-02 | [14 empty] | 2014-10-27 | 2014-11-03 |  | Y
Central Hudson |  | SolarCity | CH-06880 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8045 | Myers Corners | N |  | 12 | [13 empty] | NM | N | SOLAREDGE SE6000A-US (2) | 2014-10-02 | 2014-10-15 | 9 | 2014-10-15 | [14 empty] | 2015-02-25 | 2015-03-04 |  | Y
Central Hudson |  | SolarCity | CH-07081 | Newburgh | Wallkill | Ulster | 12589 | G | 5043 | East Walden | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A-US (1) | 2014-10-02 | 2014-10-15 | 9 | 2014-10-15 | [14 empty] | 2014-10-27 | 2014-10-31 |  | Y
Central Hudson |  | SolarCity | CH-07167 | Newburgh | New Windsor | Orange | 12553 | G | 4095 | Bethlehem Rd | N |  | 8 | [13 empty] | NM | N | SOLAREDGE SE3000A (1) SOLAREDGE 5000A(1) | 2014-09-25 | 2014-10-06 | 7 | 2014-10-06 | [14 empty] | 2014-11-03 | 2014-11-07 |  | Y
Central Hudson |  | SolarCity | CH-07365 | Fishkill | Fishkill | Dutchess | 12524 | G | 8094 | Fishkill Plains | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE600A(1) | 2014-09-25 | 2014-10-06 | 7 | 2014-10-06 | [14 empty] | 2014-12-15 | 2014-12-22 |  | Y
Central Hudson |  | SolarCity | CH-07574 | Fishkill | Fishkill | Dutchess | 12524 | G | 8094 | Fishkill Plains | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A-US (1) | 2014-10-02 | 2014-10-15 | 9 | 2014-10-15 | [14 empty] | 2014-12-29 | 2014-12-31 |  | Y
Central Hudson |  | SolarCity | CH-07788 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8052 | North Chelsea | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A-US (1) | 2014-10-02 | 2014-10-15 | 9 | 2014-10-15 | [14 empty] | 2015-01-15 | 2015-01-22 |  | Y
Central Hudson |  | SolarCity | CH-07826 | Newburgh | Wallkill |  | 12589 | G | 5012 | Modena | TBD |  | 3 | [13 empty] | NM | N | SOLAREDGE SE3000A-US (1) | 2014-10-02 | 2014-10-15 | 9 | 2014-10-15 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | Solar Generation | CH-08288 | Kingston | Kingston | Ulster | 12401 | G | 1022 | East Kingston | N |  | 6 | [13 empty] | NM | N | (2) SMA SB3000 TL | 2014-09-25 | 2014-10-02 | 5 | 2014-10-02 | [14 empty] | 2014-11-17 | 2014-11-24 |  | Y
Central Hudson |  | Sungevity Inc | CH-09282 | Kingston | Hurley | Ulster | 12443 | G | 2094 | Hurley Ave | N |  | 5 | [13 empty] | NM | N | SMA SB5000TL 22 | 2014-09-25 | 2014-10-02 | 5 | 2014-10-02 | [14 empty] | 2014-11-20 | 2014-12-01 |  | Y
Central Hudson |  | Sungevity Inc | CH-09354 | Fishkill | Fishkill |  | 12524 | G | 8065 | Merritt Park | TBD |  | 6 | [13 empty] | NM | N | SMA SB6000TL (1) | 2014-09-25 | 2014-10-06 | 7 | 2014-10-06 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | Sungevity Inc | CH-09473 | Newburgh | Newburgh |  | 12550 | G | 4027 | Coldenham | TBD |  | 5 | [13 empty] | NM | N | SMA SB5000TL (1) | 2014-09-25 | 2014-10-06 | 7 | 2014-10-06 | [17 empty] | W
Central Hudson |  | Sungevity Inc | CH-09536 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8091 | Fishkill Plains | N |  | 7.6 | [13 empty] | NM | N | SMA SB3800TL (2) | 2014-09-25 | 2014-10-06 | 7 | 2014-10-06 | [14 empty] | 2014-10-31 | 2014-11-07 |  | Y
Central Hudson |  | Verengo Solar | CH-09782 | Newburgh | Newburgh | Orange | 12550 | G | 5004 | Marlboro | N |  | 7.095 | [13 empty] | NM | N | ENPHASE ENERGY M215 (33) | 2014-09-25 | 2014-10-06 | 7 | 2014-10-06 | [14 empty] | 2015-02-04 | 2015-02-11 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-03432 | Newburgh | Marlboro | Ulster | 12542 | G | 5004 | Marlboro | N |  | 8 | [13 empty] | NM | N | SMA AMERICA SB8000US-12 (1) | 2014-09-26 | 2014-10-06 | 6 | 2014-10-06 | [14 empty] | 2014-12-16 | 2014-12-22 |  | Y
Central Hudson |  | New York State Solar Farm | CH-03988 | Fishkill | Wappingers Falls | Dutchess | 12590 | G | 8023 | Knapps Corners | N | CH-03988 | 5 | [13 empty] | NM | N | SMA SB5000-TL | 2014-09-26 | 2014-10-07 | 7 | 2014-10-07 | [14 empty] | 2015-04-30 | 2015-05-07 |  | Y
Central Hudson |  | New York State Solar Farm | CH-04026 | Kingston | Kingston | Ulster | 12401 | G | 2016 | Lincoln Park | N |  | 6 | [13 empty] | NM | N | SMA AMERICA SB 6.0 | 2014-09-26 | 2014-10-03 | 5 | 2014-10-03 | [14 empty] | 2014-10-28 | 2014-11-04 |  | Y
Central Hudson |  | NRG Home Solar | CH-04119 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6073 | East Park | N |  | 10.32 | [13 empty] | NM | N | 48 - ENPHASE ENERGY M-215 | 2014-09-26 | 2014-10-10 | 10 | 2014-10-10 | [14 empty] | 2015-04-28 | 2015-05-05 |  | Y
Central Hudson |  | NRG Home Solar | CH-04424 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8072 | Shenandoah | N |  | 5.16 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (24) | 2014-09-26 | 2014-10-06 | 6 | 2014-10-06 | [14 empty] | 2014-12-30 | 2015-01-02 |  | Y
Central Hudson |  | NRG Home Solar | CH-04451 | Newburgh | Wallkill | Ulster | 12589 | G | 5041 | East Walden | N |  | 4.75 | [13 empty] | NM | N | ENPHASE ENERGY M-250 (19) | 2014-09-26 | 2014-10-07 | 7 | 2014-10-07 | [14 empty] | 2015-04-28 | 2015-05-04 |  | Y
Central Hudson |  | NRG Home Solar | CH-04787 | Newburgh | Newburgh | Orange | 12550 | G | 4053 | Union Ave | N |  | 3.225 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (15) | 2014-09-26 | 2014-10-06 | 6 | 2014-10-06 | [14 empty] | 2014-12-30 | 2015-01-02 |  | Y
Central Hudson |  | NRG Home Solar | CH-04792 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8096 | Fishkill Plains | N |  | 4.945 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (23) | 2014-09-26 | 2014-10-07 | 7 | 2014-10-07 | [14 empty] | 2014-12-30 | 2015-01-02 |  | Y
Central Hudson |  | NRG Home Solar | CH-04834 | Newburgh | Newburgh |  | 12550 | G | 4023 | Coldenham | TBD |  | 9 | [13 empty] | NM | N | ENPHASE ENERGY M-250 (36) | 2014-09-26 | 2014-10-07 | 7 | 2014-10-07 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | Murphy Solar Power | CH-02743 | Catskill | Earlton | Greene | 12058 | G | 1071 | Coxsackie | N |  | 5 | [13 empty] | NM | N | SMA SB5000 TL-22 | 2014-09-26 | 2014-10-03 | 5 | 2014-10-03 | [14 empty] | 2015-07-24 | 2015-07-31 |  | Y
Central Hudson |  | SolarCity | CH-04973 | Newburgh | Gardiner | Ulster | 12525 | G | 5043 | East Walden | N |  | 15 | [13 empty] | NM | N | SOLAREDGE SE5000A (3) | 2014-09-26 | 2014-10-06 | 6 | 2014-10-06 | [14 empty] | 2014-10-30 | 2014-11-05 |  | Y
Central Hudson |  | SolarCity | CH-05070 | Newburgh | Newburgh | Orange | 12550 | G | 5004 | Marlboro | N | CH-05070 | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A (1) | 2014-09-26 | 2014-10-07 | 7 | 2014-10-07 | [14 empty] | 2014-12-03 | 2014-12-09 |  | Y
Central Hudson |  | SolarCity | CH-05182 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8091 | Fishkill Plains | N |  | 9.8 | [13 empty] | NM | N | SOLAREDGE SE6000A-US (1) SOLAREDGE SE3800A-US (1) | 2014-10-06 | 2014-10-16 | 8 | 2014-10-16 | [14 empty] | 2014-11-26 | 2014-12-03 |  | Y
Central Hudson |  | SolarCity | CH-05193 | Fishkill | Hopewell Jct |  | 12533 | G | 8072 | Shenandoah | TBD |  | 14.8 | [13 empty] | NM | N | SOLAREDGE SE6000A-US (1) SOLAREDGE SE3800A-US (1) SOLAREDGE SE5000A-US (1) | 2014-09-26 | 2014-10-06 | 6 | 2014-10-06 | [17 empty] | W
Central Hudson |  | SolarCity | CH-05349 | Newburgh | Campbell Hall | Orange | 10916 | G | 5052 | Maybrook | N |  | 12 | [13 empty] | NM | N | SOLAREDGE SE6000A (2) | 2014-09-26 | 2014-10-06 | 6 | 2014-10-06 | [14 empty] | 2015-01-05 | 2015-01-12 |  | Y
Central Hudson |  | SolarCity | CH-05434 | Kingston | Kerhonkson | Ulster | 12446 | G | 3082 | Kerhonkson | N |  | 7.6 | [13 empty] | NM | N | (2)SOLAREDGE SE3800A US-ZB-U | 2014-09-26 | 2014-10-03 | 5 | 2014-10-03 | [14 empty] | 2014-12-01 | 2014-12-05 |  | Y
Central Hudson |  | SolarCity | CH-05455 | Newburgh | Wallkill | Ulster | 12589 | G | 4011 | West Balmville | N |  | 8.8 | [13 empty] | NM | N | SOLAREDGE SE3800A-US (1) SOLAREDGE SE5000A-US (1) | 2014-10-03 | 2014-10-16 | 9 | 2014-10-16 | [14 empty] | 2014-10-29 | 2014-11-03 |  | Y
Central Hudson |  | SolarCity | CH-05618 | Kingston | High Fls | Ulster | 12440 | G | 3024 | High Falls | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A US-ZB-U | 2014-09-26 | 2014-10-03 | 5 | 2014-10-03 | [14 empty] | 2015-01-05 | 2015-01-12 |  | Y
Central Hudson |  | SolarCity | CH-05695 | Kingston | Hurley | Ulster | 12401 | G | 2094 | Hurley Ave | N |  | 7.6 | [13 empty] | NM | N | (2)SOLAREDGE SE3800A-US-ZB-U | 2014-09-26 | 2014-10-03 | 5 | 2014-10-03 | [14 empty] | 2015-01-09 | 2015-01-16 |  | Y
Central Hudson |  | SolarCity | CH-05733 | Kingston | Saugerties | Ulster | 12477 | G | 3001 | Saugerties | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A US-ZB-U | 2014-09-26 | 2014-10-03 | 5 | 2014-10-03 | [14 empty] | 2015-01-31 | 2015-02-06 |  | Y
Central Hudson |  | SolarCity | CH-05762 | Kingston | Saugerties | Ulster | 12477 | G | 2015 | Lincoln Park | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A US-ZB-U | 2014-09-26 | 2014-10-03 | 5 | 2014-10-03 | [14 empty] | 2014-12-18 | 2014-12-29 |  | Y
Central Hudson |  | SolarCity | CH-05783 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6046 | Spackenkill | N |  | 3.8 | [13 empty] | NM | N | SOLAREDGE SE3800A | 2014-09-26 | 2014-10-10 | 10 | 2014-10-10 | [14 empty] | 2014-11-26 | 2014-12-05 |  | Y
Central Hudson |  | SolarCity | CH-05791 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6043 | Spackenkill | N |  | 7.6 | [13 empty] | NM | N | 2 - SOLAREDGE SE3800A-US | 2014-10-03 | 2014-10-17 | 10 | 2014-10-17 | [14 empty] | 2014-12-15 | 2014-12-22 |  | Y
Central Hudson |  | SolarCity | CH-05796 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6044 | Spackenkill | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A | 2014-09-26 | 2014-10-10 | 10 | 2014-10-10 | [14 empty] | 2014-12-19 | 2014-12-23 |  | Y
Central Hudson |  | SolarCity | CH-05973 | Poughkeepsie | Pine Plns | Dutchess | 12567 | G | 7091 | Pulvers Corners | N | CH-05973 | 3 | [13 empty] | NM | N | SOLAREDGE SE3000A | 2014-09-26 | 2014-10-10 | 10 | 2014-10-10 | [14 empty] | 2015-01-05 | 2015-01-12 |  | Y
Central Hudson |  | SolarCity | CH-06615 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6095 | Manchester | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A | 2014-09-26 | 2014-10-10 | 10 | 2014-10-10 | [14 empty] | 2015-02-02 | 2015-02-09 |  | Y
Central Hudson |  | SolarCity | CH-06860 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8092 | Fishkill Plains | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A (1) | 2014-09-26 | 2014-10-07 | 7 | 2014-10-07 | [14 empty] | 2015-02-25 | 2015-03-04 |  | Y
Central Hudson |  | SolarCity | CH-06943 | Fishkill | Beacon | Dutchess | 12508 | G | 8085 | Tioronda | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE3800A-US (1) | 2014-10-06 | 2014-10-16 | 8 | 2014-10-16 | [14 empty] | 2014-12-02 | 2014-12-09 |  | Y
Central Hudson |  | SolarCity | CH-06970 | Newburgh | Newburgh | Orange | 12550 | G | 4051 | Union Ave | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A-US (1) | 2014-09-26 | 2014-10-06 | 6 | 2014-10-06 | [14 empty] | 2015-01-20 | 2015-01-26 |  | Y
Central Hudson |  | SolarCity | CH-07170 | Newburgh | New Windsor | Orange | 12553 | G | 4094 | Bethlehem Rd | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A (1) | 2015-02-19 | 2015-02-26 | 5 | 2015-02-26 | [14 empty] | 2015-03-10 | 2015-03-10 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07391 | Fishkill | Beacon | Dutchess | 12508 | G | 8017 | Forgebrook | N |  | 3.8 | [13 empty] | NM | N | SOLAREDGE SE3800A (1) | 2014-10-03 | 2014-10-16 | 9 | 2014-10-16 | [14 empty] | 2014-12-26 | 2014-12-31 |  | Y
Central Hudson |  | SolarCity | CH-07392 | Fishkill | Beacon | Dutchess | 12508 | G | 8017 | Forgebrook | N |  | 3.8 | [13 empty] | NM | N | SOLAREDGE SE3800A | 2014-09-26 | 2014-10-07 | 7 | 2014-10-07 | [14 empty] | 2014-12-26 | 2014-12-31 |  | Y
Central Hudson |  | SolarCity | CH-07450 | Newburgh | Wallkill |  | 12589 | G | 4011 | West Balmville | TBD |  | 8 | [13 empty] | NM | N | SOLAREDGE SE5000A (1) SOLAREDGE SE3000A (1) | 2014-09-26 | 2014-10-06 | 6 | 2014-10-06 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | SolarCity | CH-07828 | Newburgh | Marlboro | Ulster | 12542 | G | 5004 | Marlboro | N | CH-06320 | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A-US (1) | 2014-10-06 | 2014-10-16 | 8 | 2014-10-16 | [14 empty] | 2015-01-05 | 2015-01-09 |  | Y
Central Hudson |  | SolarCity | CH-07865 | Kingston | Kingston |  | 12401 | G | 1022 | East Kingston | TBD |  | 3 | [13 empty] | NM | N | SOLAREDGE SE3000A-US-ZB-U | 2014-09-26 | 2014-10-03 | 5 | 2014-10-03 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | Sungevity Inc | CH-09512 | Newburgh | New Windsor | Orange | 12553 | G | 4095 | Bethlehem Rd | N |  | 7.6 | [13 empty] | NM | N | ABB PVI-3.8-OUTD (2) | 2014-09-26 | 2014-10-07 | 7 | 2014-10-07 | [14 empty] | 2014-11-05 | 2014-11-10 |  | Y
Central Hudson |  | NRG Home Solar | CH-04153 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6043 | Spackenkill | N |  | 3.87 | [13 empty] | NM | N | 18 - ENPHASE ENERGY M-215 | 2014-09-29 | 2014-10-06 | 5 | 2014-10-06 | [14 empty] | 2015-02-06 | 2015-02-13 |  | Y
Central Hudson |  | NRG Home Solar | CH-04561 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6056 | Todd Hill | N |  | 8.815 | [13 empty] | NM | N | 41 - ENPHASE ENERGY M-215 | 2014-09-29 | 2014-10-06 | 5 | 2014-10-06 | [14 empty] | 2015-01-21 | 2015-01-28 |  | Y
Central Hudson |  | NRG Home Solar | CH-04573 | Poughkeepsie | Red Hook |  | 12571 | G | 7061 | Milan | TBD |  | 8.815 | [13 empty] | NM | N | 41 - ENPHASE ENERGY M-215 | 2014-09-29 | 2014-10-06 | 5 | 2014-10-06 | [17 empty] | W
Central Hudson |  | NRG Home Solar | CH-04649 | Newburgh | Newburgh | Orange | 12550 | G | 4045 | Union Ave | N |  | 5.805 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (27) | 2014-09-29 | 2014-10-07 | 6 | 2014-10-07 | [14 empty] | 2015-02-11 | 2015-02-19 |  | Y
Central Hudson |  | NRG Home Solar | CH-04779 | Newburgh | Marlboro | Ulster | 12542 | G | 5003 | Marlboro | N |  | 3.225 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (15) | 2014-09-29 | 2014-10-07 | 6 | 2014-10-07 | [14 empty] | 2015-01-16 | 2015-01-23 |  | Y
Central Hudson |  | SolarCity | CH-05074 | Newburgh | Marlboro | Ulster | 12542 | G | 5004 | Marlboro | N |  | 9 | [13 empty] | NM | N | (1) SOLAREDGE SE6000A-US (1) SOLAREDGE SE3000A-US | 2015-02-11 | 2015-02-11 | 0 | 2015-02-11 | [14 empty] | 2015-02-12 | 2015-02-20 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-05556 | Catskill | Greenvl | Greene | 12083 | G | 2061 | Freehold | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A-US-ZB-U | 2014-09-29 | 2014-10-06 | 5 | 2014-10-06 | [14 empty] | 2014-12-11 | 2014-12-18 |  | Y
Central Hudson |  | SolarCity | CH-06174 | Newburgh | New Paltz | Ulster | 12561 | G | 5022 | Ohioville | N |  | 6.8 | [13 empty] | NM | N | SOLAREDGE SE3000A-US (1) SOLAREDGE SE3800A-US (1) | 2014-09-29 | 2014-10-07 | 6 | 2014-10-07 | [14 empty] | 2014-10-27 | 2014-10-31 |  | Y
Central Hudson |  | SolarCity | CH-06865 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8092 | Fishkill Plains | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A-US (1) | 2014-09-29 | 2014-10-07 | 6 | 2014-10-07 | [14 empty] | 2015-01-05 | 2015-01-12 |  | Y
Central Hudson |  | SolarCity | CH-07563 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8046 | Myers Corners | N |  | 3.8 | [13 empty] | NM | N | SOLAREDGE SE3800A-US (1) | 2014-10-07 | 2014-10-17 | 8 | 2014-10-17 | [14 empty] | 2014-11-26 | 2014-12-03 |  | Y
Central Hudson |  | Solar Generation | CH-08295 | Kingston | Saugerties | Ulster | 12477 | G | 3003 | Saugerties | N | CH-08295 | 6 | [13 empty] | NM | N | SMA SB6000 TL | 2014-09-29 | 2014-10-06 | 5 | 2014-10-06 | [14 empty] | 2014-11-04 | 2014-11-11 |  | Y
Central Hudson |  | Sungevity Inc | CH-09170 | Catskill | Medusa | Albany | 12120 | G | 1092 | Westerlo | N |  | 9.8 | [13 empty] | NM | N | (1)SMA AMERICA SB3800TL-US-22 (1)SMA AMERICA SB6000TL-US-22 | 2014-09-29 | 2014-10-06 | 5 | 2014-10-06 | [14 empty] | 2014-11-19 | 2014-11-25 |  | Y
Central Hudson |  | Sungevity Inc | CH-09584 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6046 | Spackenkill | N |  | 3.8 | [13 empty] | NM | N | SMA AMERICA SB3800TL-US-22 | 2014-09-29 | 2014-10-06 | 5 | 2014-10-06 | [14 empty] | 2014-11-13 | 2014-11-20 |  | Y
Central Hudson |  | Kirchhoff Green Energy LLC | CH-03551 | Poughkeepsie | Clinton Cors | Dutchess | 12514 | G | 7071 | Stanfordville | N |  | 11.4 | [13 empty] | NM | N | FRONIUS 11.4-1 | 2014-09-30 | 2014-10-14 | 10 | 2014-10-14 | [14 empty] | 2014-12-09 | 2014-12-15 |  | Y
Central Hudson |  | New York State Solar Farm | CH-03948 | Newburgh | Highland | Ulster | 12528 | G | 5022 | Ohioville | N |  | 11 | [13 empty] | NM | N | POWERONE PVI 6.0 (1) POWERONE PVI 5.0 (1) | 2014-09-30 | 2014-10-10 | 8 | 2014-10-10 | [14 empty] | 2014-10-23 | 2014-10-29 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | New York State Solar Farm | CH-03955 | Newburgh | Milton | Ulster | 12547 | G | 5002 | Marlboro | N |  | 7.6 | [13 empty] | NM | N | POWERONE PVI 3.8 (2) | 2014-09-30 | 2014-10-10 | 8 | 2014-10-10 | [14 empty] | 2014-11-18 | 2014-11-21 |  | Y
Central Hudson |  | Hudson Solar | CH-01814 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 7024 | Tinkertown | N |  | 6 | [13 empty] | NM | N | 1 - SPR 6000 | 2014-09-30 | 2014-10-14 | 10 | 2014-10-14 | [14 empty] | 2015-01-20 | 2015-01-26 |  | Y
Central Hudson |  | Hudson Solar | CH-01964 | Newburgh | Highland | Ulster | 12528 | G | 5013 | Modena | N |  | 5 | [13 empty] | NM | N | SMA AMERICA SB5000 (1) | 2014-09-30 | 2014-10-10 | 8 | 2014-10-10 | [14 empty] | 2014-12-30 | 2014-12-31 |  | Y
Central Hudson |  | Murphy Solar Power | CH-02758 | Catskill | Athens | Greene | 12015 | G | 2002 | North Catskill | N |  | 5 | [13 empty] | NM | N | SMA SB5000 T-L-22 | 2014-09-30 | 2014-10-07 | 5 | 2014-10-07 | [14 empty] | 2014-11-07 | 2014-11-14 |  | Y
Central Hudson |  | SolarCity | CH-05930 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 7025 | Tinkertown | N |  | 8.8 | [13 empty] | NM | N | 1 - SOLAREDGE SE3800A 1 - SOLAREDGE SE5000A | 2014-09-30 | 2014-10-14 | 10 | 2014-10-14 | [14 empty] | 2014-11-26 | 2014-12-05 |  | Y
Central Hudson |  | SolarCity | CH-07089 | Newburgh | Gardiner | Ulster | 12525 | G | 5043 | East Walden | N | CH-07089 | 9 | [13 empty] | NM | N | SOLAREDGE SE6000A-US (1) SOLAREDGE SE3000A-US (1) | 2014-10-07 | 2014-10-17 | 8 | 2014-10-17 | [14 empty] | 2014-11-26 | 2014-12-03 |  | Y
Central Hudson |  | SolarCity | CH-07740 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8043 | Myers Corners | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A (1) | 2014-09-30 | 2014-10-10 | 8 | 2014-10-10 | [14 empty] | 2014-12-02 | 2014-12-09 |  | Y
Central Hudson |  | SolarCity | CH-07795 | Kingston | Rosendale | Ulster | 12472 | G | 3021 | High Falls | N |  | 3 | [13 empty] | NM | N | SOLAREDGE SE3000A US-ZB-U | 2014-09-30 | 2014-10-07 | 5 | 2014-10-07 | [14 empty] | 2015-06-01 | 2015-06-05 |  | Y
Central Hudson |  | Sungevity Inc | CH-09380 | Newburgh | Milton | Ulster | 12547 | G | 5002 | Marlboro | N |  | 6 | [13 empty] | NM | N | SMA AMERICA SB6000TL-US (1) | 2014-09-30 | 2014-10-10 | 8 | 2014-10-10 | [14 empty] | 2014-11-12 | 2014-11-17 |  | Y
Central Hudson |  | Sungevity Inc | CH-09499 | Newburgh | Wallkill | Ulster | 12589 | G | 5013 | Modena | N |  | 7.8 | [13 empty] | NM | N | SMA AMERICA SB4000TL-US (1) SMA AMERICA SB3800TL-US (1) | 2014-09-30 | 2014-10-10 | 8 | 2014-10-10 | [14 empty] | 2014-11-19 | 2014-11-25 |  | Y
Central Hudson |  | Verengo Solar | CH-09766 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 7024 | Tinkertown | N |  | 10.32 | [13 empty] | NM | N | 48 - ENPHASE M215 | 2014-09-30 | 2014-10-14 | 10 | 2014-10-14 | [14 empty] | 2014-12-22 | 2014-12-30 |  | Y
Central Hudson |  | Verengo Solar | CH-09856 | Poughkeepsie | Hyde Pk |  | 12538 | G | 6075 | East Park | TBD |  | 3.87 | [13 empty] | NM | N | 18 - Enphase M215 | 2014-11-07 | 2014-11-18 | 7 | 2014-11-18 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | Infinity Solar Systems | CH-03384 | Fishkill | Beacon | Dutchess | 12508 | G | 8015 | Forgebrook | N |  | 4.2 | [13 empty] | NM | N | POWERONE PVI-4.2 (1) | 2014-10-01 | 2014-10-10 | 7 | 2014-10-10 | [14 empty] | 2014-12-18 | 2014-12-26 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-03444 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6046 | Spackenkill | N |  | 6 | [13 empty] | NM | N | 2 - SMA AMERICA SB3000 | 2014-10-01 | 2014-10-15 | 10 | 2014-10-15 | [14 empty] | 2014-12-23 | 2014-12-30 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-03473 | Newburgh | Campbell Hall | Orange | 10916 | G | 5052 | Maybrook | N |  | 8 | [13 empty] | NM | N | SMA AMERICA SB8000US-12 (1) | 2014-10-01 | 2014-10-10 | 7 | 2014-10-10 | [14 empty] | 2015-05-29 | 2015-06-05 |  | Y
Central Hudson |  | New York State Solar Farm | CH-03949 | Newburgh | New Paltz | Ulster | 12561 | G | 5023 | Ohioville | N |  | 5 | [13 empty] | NM | N | POWERONE PVI 5.0 (1) | 2014-10-13 | 2014-10-21 | 6 | 2014-10-21 | [14 empty] | 2014-12-04 | 2014-12-10 |  | Y
Central Hudson |  | New York State Solar Farm | CH-04019 | Kingston | Rosendale | Ulster | 12472 | G | 3022 | High Falls | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE 5.0 | 2014-10-01 | 2014-10-08 | 5 | 2014-10-08 | [14 empty] | 2014-11-18 | 2014-11-25 |  | Y
Central Hudson |  | NRG Home Solar | CH-04174 | Fishkill | Hopewell Jct |  | 12533 | G | 8096 | Fishkill Plains | TBD |  | 8.815 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (41) | 2014-10-01 | 2014-10-10 | 7 | 2014-10-10 | [17 empty] | W
Central Hudson |  | NRG Home Solar | CH-04220 | Fishkill | Beacon | Dutchess | 12508 | G | 8085 | Tioronda | N |  | 8.81 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (41) | 2014-10-09 | 2014-10-17 | 6 | 2014-10-17 | [14 empty] | 2014-12-30 | 2015-01-02 |  | Y
Central Hudson |  | NRG Home Solar | CH-04509 | Newburgh | Campbell Hall | Orange | 10916 | G | 5052 | Maybrook | N |  | 8.815 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (41) | 2014-10-01 | 2014-10-10 | 7 | 2014-10-10 | [14 empty] | 2015-04-20 | 2015-04-27 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00954 | Fishkill | Fishkill | Dutchess | 12524 | G | 8065 | Merritt Park | N |  | 6.02 | [13 empty] | NM | N | ENPHASE 215 (28) | 2014-10-01 | 2014-10-10 | 7 | 2014-10-10 | [14 empty] | 2014-10-24 | 2014-10-30 |  | Y
Central Hudson |  | Hudson Solar | CH-01436 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6092 | Manchester | N |  | 5 | [13 empty] | NM | N | SUNPOWER SPR-5000P | 2014-10-01 | 2014-10-15 | 10 | 2014-10-15 | [14 empty] | 2014-12-23 | 2014-12-30 |  | Y
Central Hudson |  | Hudson Solar | CH-01530 | Poughkeepsie | Lagrangevl | Dutchess | 12540 | G | 6055 | Todd Hill | N |  | 13 | [13 empty] | NM | N | 1 - SMA AMERICA SB7000 1 - SMA AMERICA SB6000 | 2014-10-01 | 2014-10-15 | 10 | 2014-10-15 | [14 empty] | 2014-12-29 | 2014-12-31 |  | Y
Central Hudson |  | Hudson Solar | CH-01943 | Newburgh | New Paltz | Ulster | 12561 | G | 5031 | Galeville | N |  | 6 | [13 empty] | NM | N | SMA AMERICA SB6000 (1) | 2014-10-01 | 2014-10-10 | 7 | 2014-10-10 | [14 empty] | 2014-12-30 | 2015-01-02 |  | Y
Central Hudson |  | Hudson Solar | CH-02274 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7055 | Rhinebeck | N |  | 7.6 | [13 empty] | NM | N | 2 - SMA AMERICA SB3800 | 2014-10-01 | 2014-10-15 | 10 | 2014-10-15 | [14 empty] | 2014-12-01 | 2014-12-08 |  | Y
Central Hudson |  | Monolith Solar Associates LLC | CH-02638 | Catskill | Round Top | Greene | 12473 | G | 2042 | South Cairo | N |  | 7 | [13 empty] | NM | N | SMA 6000USA | 2014-10-01 | 2015-01-23 | 77 | 2015-01-23 | [14 empty] | 2015-03-25 | 2015-04-01 |  | Y
Central Hudson |  | Monolith Solar Associates LLC | CH-02653 | Catskill | Round Top |  | 12473 | G | 2042 | South Cairo | TBD |  | 7.7 | [13 empty] | NM | N | SMA 7700 TL-US-22 | 2014-10-01 | 2014-10-08 | 5 | 2014-10-08 | [17 empty] | W
Central Hudson |  | Monolith Solar Associates LLC | CH-02672 | Kingston | Saugerties | Ulster | 12477 | G | 3001 | Saugerties | N |  | 7 | [13 empty] | NM | N | SMA 7000 US | 2014-10-01 | 2014-10-08 | 5 | 2014-10-08 | [14 empty] | 2014-12-02 | 2014-12-09 |  | Y
Central Hudson |  | Solar Alchemy | CH-08979 | Fishkill | Wappingrs Falls |  | 12590 | G | 8023 | Knapps Corners | TBD |  | 9 | [13 empty] | NM | N | ENPHASE ENERGY M250 | 2014-10-09 | 2014-10-17 | 6 | 2014-10-17 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | Verengo Solar | CH-09812 | Fishkill | Beacon | Dutchess | 12508 | G | 8017 | Forgebrook | N |  | 4.51 | [13 empty] | NM | N | ENPHASE ENERGY M215 (21) | 2014-10-01 | 2014-10-10 | 7 | 2014-10-10 | [14 empty] | 2015-01-06 | 2015-01-13 |  | Y
Central Hudson |  | Verengo Solar | CH-09817 | Newburgh | New Paltz | Ulster | 12561 | G | 5024 | Ohioville | N |  | 7.09 | [13 empty] | NM | N | ENPHASE ENERGY M215 (33) | 2014-10-01 | 2014-10-10 | 7 | 2014-10-10 | [14 empty] | 2015-01-13 | 2015-01-19 |  | Y
Central Hudson |  | Verengo Solar | CH-09821 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 3.87 | [13 empty] | NM | N | ENPHASE ENERGY M215 (18) | 2014-10-01 | 2014-10-10 | 7 | 2014-10-10 | [14 empty] | 2014-11-10 | 2014-11-13 |  | Y
Central Hudson |  | Verengo Solar | CH-09823 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 4.08 | [13 empty] | NM | N | ENPHASE ENERGY M215 | 2014-10-01 | 2014-10-10 | 7 | 2014-10-10 | [14 empty] | 2014-11-19 | 2014-11-25 |  | Y
Central Hudson |  | Verengo Solar | CH-09848 | Kingston | Kingston | Ulster | 12401 | G | 1011 | Boulevard | N |  | 12.685 | [13 empty] | NM | N | (59) ENPHASE M215-602LL-S22 | 2014-10-01 | 2014-10-08 | 5 | 2014-10-08 | [14 empty] | 2015-01-26 | 2015-02-02 |  | Y
Central Hudson |  | Verengo Solar | CH-09859 | Poughkeepsie | Poughkeepsie |  | 12603 | G | 6092 | Manchester | TBD |  | 6.45 | [13 empty] | NM | N | 30 - ENPHASE M215 | 2014-10-01 | 2014-10-15 | 10 | 2014-10-15 | [17 empty] | W
Central Hudson |  | Verengo Solar | CH-09904 | Newburgh | Newburgh | Orange | 12550 | G | 4023 | Coldenham | N |  | 10.965 | [13 empty] | NM | N | ENPHASE ENERGY M215 (51) | 2014-10-01 | 2014-10-10 | 7 | 2014-10-10 | [14 empty] | 2014-12-01 | 2014-12-08 |  | Y
Central Hudson |  | Verengo Solar | CH-09912 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 7024 | Tinkertown | N |  | 11.61 | [13 empty] | NM | N | 54 - ENPHASE M215 | 2014-10-01 | 2014-10-15 | 10 | 2014-10-15 | [14 empty] | 2014-12-22 | 2014-12-30 |  | Y
Central Hudson |  | NRG Home Solar | CH-04350 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 7024 | Tinkertown | N |  | 8.385 | [13 empty] | NM | N | 39 - ENPHASE ENERGY M-215 | 2014-10-09 | 2014-10-16 | 5 | 2014-10-16 | [14 empty] | 2015-01-22 | 2015-01-29 |  | Y
Central Hudson |  | NRG Home Solar | CH-04539 | Kingston | Kingston | Ulster | 12401 | G | 2013 | Lincoln Park | N |  | 8.5 | [13 empty] | NM | N | (34) ENPHASE ENERGY M-250-60-2LL-S22 | 2014-10-02 | 2014-10-09 | 5 | 2014-10-09 | [14 empty] | 2015-06-29 | 2015-07-07 |  | Y
Central Hudson |  | SolarCity | CH-05640 | Kingston | High Fls | Ulster | 12440 | G | 3022 | High Falls | N |  | 3.8 | [13 empty] | NM | N | SOLAREDGE SE3800A US-ZB-U | 2014-10-02 | 2014-10-09 | 5 | 2014-10-09 | [14 empty] | 2014-10-28 | 2014-11-03 |  | Y
Central Hudson |  | SolarCity | CH-05906 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 6051 | Todd Hill | N |  | 7.6 | [13 empty] | NM | N | 2 - SOLAREDGE SE3800A-US | 2014-10-02 | 2014-10-09 | 5 | 2014-10-09 | [14 empty] | 2014-10-28 | 2014-11-04 |  | Y
Central Hudson |  | SolarCity | CH-06735 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6093 | Manchester | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A-US | 2014-10-02 | 2014-10-16 | 10 | 2014-10-16 | [14 empty] | 2014-11-03 | 2014-11-07 |  | Y
Central Hudson |  | Verengo Solar | CH-09774 | Newburgh | New Windsor | Orange | 12553 | G | 4094 | Bethlehem Rd | N |  | 7.74 | [13 empty] | NM | N | ENPHASE ENERGY M215 (36) | 2014-10-02 | 2014-10-15 | 9 | 2014-10-15 | [14 empty] | 2014-11-10 | 2014-11-13 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-03400 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6044 | Spackenkill | N |  | 14 | [13 empty] | NM | N | 2 - SMA AMERICA SB7000 | 2014-10-03 | 2014-10-17 | 10 | 2014-10-17 | [14 empty] | 2014-12-11 | 2014-12-18 |  | Y
Central Hudson |  | NRG Home Solar | CH-04390 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8023 | Knapps Corners | N |  | 6.88 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (32) | 2014-10-03 | 2014-10-15 | 8 | 2014-10-15 | [14 empty] | 2015-02-25 | 2015-03-04 |  | Y
Central Hudson |  | NRG Home Solar | CH-04519 | Catskill | Athens | Greene | 12015 | G | 2002 | North Catskill | N |  | 3.44 | [13 empty] | NM | N | 16 ENPHASE ENERGY M-215-60-2LL-S22-IG | 2014-10-03 | 2014-10-10 | 5 | 2014-10-10 | [14 empty] | 2015-08-05 | 2015-08-12 |  | Y
Central Hudson |  | SolarCity | CH-04943 | Poughkeepsie | Hyde Pk |  | 12538 | G | 6074 | East Park | TBD |  | 13.8 | [13 empty] | NM | N | 1 - SOLAREDGE SE38000A-US 2 - SOLAREDGE SE5000A-US | 2014-10-03 | 2014-10-17 | 10 | 2014-10-17 | [17 empty] | W
Central Hudson |  | Infinity Solar Systems | CH-03496 | Newburgh | Wallkill | Ulster | 12589 | G | 5043 | East Walden | N |  | 6 | [13 empty] | NM | N | FRONIUS IG PLUS A 6.0 | 2014-10-06 | 2014-10-17 | 9 | 2014-10-17 | [14 empty] | 2014-10-23 | 2014-10-29 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03777 | Kingston | Accord | Ulster | 12404 | G | 3024 | High Falls | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE 7600A-U | 2014-10-06 | 2014-10-17 | 9 | 2014-10-17 | [14 empty] | 2014-11-17 | 2014-11-24 |  | Y
Central Hudson |  | NRG Home Solar | CH-04403 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8094 | Fishkill Plains | N |  | 5.805 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (27) | 2014-10-06 | 2014-10-17 | 9 | 2014-10-17 | [14 empty] | 2015-01-28 | 2015-02-04 |  | Y
Central Hudson |  | AROSA SOLAR | CH-00722 | Kingston | Greenfield Pk | Ulster | 12435 | G | 3096 | Grimley Rd | N |  | 56 | [13 empty] | RNM | N | (2) Solectria PVI 28TL2SolectriaPVI 28TL | 2015-06-10 | 2015-06-10 | 0 | 2015-06-10 | 2015-05-18 | 2015-06-10 | 16 | 2015-08-19 | 2015-09-02 | 2015-11-30 | 60 | 4517.74 | 47875 | 30475.4 | 2017-04-27 | 2017-10-09 | 2017-10-09 | 2018-03-19 | 2018-04-11 | 2018-04-11 | 2018-05-25 | Y |  | There are 4 accounts at this location with an aggregate CESIR Cost to Customer of $20,000 & Estimated Project Upgrade Costs of $191,500.
Central Hudson |  | Arosa Solar | CH-00723 | Kingston | Kerhonkson | Ulster | 12446 | G | 3082 | Kerhonkson | N |  | 56 | [13 empty] | RNM | N | (2) Solectria PVI 28TL | 2015-05-18 | 2015-06-10 | 16 | 2015-06-10 | 2015-05-18 | 2015-06-10 | 16 | 2015-08-18 | 2015-08-18 | 2015-10-22 | 46 | 200 | [6 empty] | 2016-06-29 | 2016-07-01 |  | Y |  | There are 5 accounts at this location with an aggregate CESIR Cost to Customer of $1,000.
Central Hudson |  | Arosa Solar | CH-00724 | Kingston | Napanoch | Ulster | 12458 | G | 3072 | Honk Falls | N |  | 112 | [13 empty] | RNM | N | (4) Solectria PVI 28TL | 2015-05-18 | 2015-06-10 | 16 | 2015-06-10 | 2015-05-18 | 2015-06-10 | 16 | 2015-07-31 | 2015-07-31 | 2015-10-22 | 58 | 200 | [6 empty] | 2016-06-28 | 2016-07-01 |  | Y |  | There are 5 accounts at this location with an aggregate CESIR Cost to Customer of $1,000.
Central Hudson |  | AROSA SOLAR | CH-00725 | Kingston | Greenfield Pk | Ulster | 12435 | G | 3096 | Grimley Rd | N |  | 102 | [13 empty] | RNM | N | (2) Solectria PVI 28TL (2) Solectria PVI 23TL2SolectriaPVI 28TL2SolectriaPVI 23TL | 2015-06-10 | 2015-06-10 | 0 | 2015-06-10 | 2015-05-18 | 2015-06-10 | 16 | 2015-08-19 | 2015-09-02 | 2015-11-30 | 60 | 4517.75 | 47875 | 30475.41 | 2017-04-27 | 2017-10-09 | 2017-10-09 | 2018-03-19 | 2018-04-11 | 2018-04-11 | 2018-05-25 | Y |  | There are 4 accounts at this location with an aggregate CESIR Cost to Customer of $20,000 & Estimated Project Upgrade Costs of $191,500.
Central Hudson |  | Arosa Solar | CH-00726 | Kingston | Kerhonkson | Ulster | 12446 | G | 3082 | Kerhonkson | N |  | 69 | [13 empty] | RNM | N | (3) Solectria PVI 23TL | 2015-05-18 | 2015-06-10 | 16 | 2015-06-10 | 2015-05-18 | 2015-06-10 | 16 | 2015-08-18 | 2015-08-18 | 2015-10-22 | 46 | 200 | [6 empty] | 2016-06-29 | 2016-07-01 |  | Y |  | There are 5 accounts at this location with an aggregate CESIR Cost to Customer of $1,000.
Central Hudson |  | Arosa Solar | CH-00727 | Kingston | Napanoch | Ulster | 12458 | G | 3072 | Honk Falls | N |  | 84 | [13 empty] | RNM | N | (3) Solectria PVI 28TL | 2015-05-18 | 2015-06-10 | 16 | 2015-06-10 | 2015-05-18 | 2015-06-10 | 16 | 2015-07-31 | 2015-07-31 | 2015-10-22 | 58 | 200 | [6 empty] | 2016-06-28 | 2016-07-01 |  | Y |  | There are 5 accounts at this location with an aggregate CESIR Cost to Customer of $1,000.
Central Hudson |  | AROSA SOLAR | CH-00728 | Kingston | Greenfield Pk | Ulster | 12435 | G | 3096 | Grimley Rd | N |  | 84 | [13 empty] | RNM | N | (3) Solectria PVI 28TL3SolectriaPVI 28TL | 2015-06-10 | 2015-06-10 | 0 | 2015-06-10 | 2015-05-18 | 2015-06-10 | 16 | 2015-08-19 | 2015-09-02 | 2015-11-30 | 60 | 4517.75 | 47875 | 30475.41 | 2017-04-27 | 2017-10-09 | 2017-10-09 | 2018-03-19 | 2018-04-11 | 2018-04-11 | 2018-05-25 | Y |  | There are 4 accounts at this location with an aggregate CESIR Cost to Customer of $20,000 & Estimated Project Upgrade Costs of $191,500.
Central Hudson |  | Arosa Solar | CH-00729 | Kingston | Kerhonkson | Ulster | 12446 | G | 3082 | Kerhonkson | N |  | 46 | [13 empty] | RNM | N | (2) Solectria PVI 23TL | 2015-05-18 | 2015-06-10 | 16 | 2015-06-10 | 2015-05-18 | 2015-06-10 | 16 | 2015-08-18 | 2015-08-18 | 2015-10-22 | 46 | 200 | [6 empty] | 2016-06-29 | 2016-07-01 |  | Y |  | There are 5 accounts at this location with an aggregate CESIR Cost to Customer of $1,000.
Central Hudson |  | Arosa Solar | CH-00730 | Kingston | Napanoch | Ulster | 12458 | G | 3072 | Honk Falls | N |  | 56 | [13 empty] | RNM | N | (2) Solectria PVI 28TL | 2015-05-18 | 2015-06-10 | 16 | 2015-06-10 | 2015-05-18 | 2015-06-10 | 16 | 2015-07-31 | 2015-07-31 | 2015-10-22 | 58 | 200 | [6 empty] | 2016-06-28 | 2016-07-01 |  | Y |  | There are 5 accounts at this location with an aggregate CESIR Cost to Customer of $1,000.
Central Hudson |  | AROSA SOLAR | CH-00731 | Kingston | Greenfield Pk | Ulster | 12435 | G | 3096 | Grimley Rd | N |  | 56 | [13 empty] | RNM | N | (2) Solectria PVI 28TL2SolectriaPVI 28TL | 2015-06-10 | 2015-06-10 | 0 | 2015-06-10 | 2015-05-18 | 2015-06-10 | 16 | 2015-08-19 | 2015-09-02 | 2015-11-30 | 60 | 4517.75 | 47875 | 30475.41 | 2017-04-27 | 2017-10-09 | 2017-10-09 | 2018-03-19 | 2018-04-11 | 2018-04-11 | 2018-05-25 | Y |  | There are 4 accounts at this location with an aggregate CESIR Cost to Customer of $20,000 & Estimated Project Upgrade Costs of $191,500.
Central Hudson |  | Arosa Solar | CH-00732 | Kingston | Kerhonkson | Ulster | 12446 | G | 3082 | Kerhonkson | N |  | 112 | [13 empty] | RNM | N | (4) Solectria PVI 28TL | 2015-05-18 | 2015-06-10 | 16 | 2015-06-10 | 2015-05-18 | 2015-06-10 | 16 | 2015-08-18 | 2015-08-18 | 2015-10-22 | 46 | 200 | [6 empty] | 2016-06-29 | 2016-07-01 |  | Y |  | There are 5 accounts at this location with an aggregate CESIR Cost to Customer of $1,000.
Central Hudson |  | Arosa Solar | CH-00733 | Kingston | Napanoch | Ulster | 12458 | G | 3072 | Honk Falls | N |  | 112 | [13 empty] | RNM | N | (4) Solectria PVI 28TL | 2015-05-18 | 2015-06-10 | 16 | 2015-06-10 | 2015-05-18 | 2015-06-10 | 16 | 2015-07-31 | 2015-07-31 | 2015-10-22 | 58 | 200 | [6 empty] | 2016-06-28 | 2016-07-01 |  | Y |  | There are 5 accounts at this location with an aggregate CESIR Cost to Customer of $1,000.
Central Hudson |  | Arosa Solar | CH-00734 | Kingston | Ellenvl | Ulster | 12458 | G | 3072 | Honk Falls | N |  | 56 | [13 empty] | RNM | N | (2) Solectria PVI 28TL | 2015-08-12 | 2015-08-17 | 3 | 2015-08-17 | 2015-08-12 | 2015-08-17 | 3 | 2015-07-31 | 2015-08-19 | 2015-11-12 | 60 | 200 | [6 empty] | 2016-06-28 | 2016-07-01 |  | Y |  | There are 5 accounts at this location with an aggregate CESIR Cost to Customer of $1,000.
Central Hudson |  | Arosa Solar | CH-00735 | Kingston | Kerhonkson | Ulster | 12446 | G | 3082 | Kerhonkson | N |  | 56 | [13 empty] | RNM | N | (2) Solectria PVI 28TL | 2015-05-18 | 2015-06-10 | 16 | 2015-06-10 | 2015-05-18 | 2015-06-10 | 16 | 2015-08-18 | 2015-08-18 | 2015-10-22 | 46 | 200 | [6 empty] | 2016-06-29 | 2016-07-01 |  | Y |  | There are 5 accounts at this location with an aggregate CESIR Cost to Customer of $1,000.
Central Hudson |  | Arosa Solar | CH-00736 | Kingston | Ellenvl | Ulster | 12428 | G | 3076 | Greenfield Rd | N |  | 69 | [13 empty] | RNM | N | (3) Solectria PVI 23TL | 2015-05-18 | 2015-06-10 | 16 | 2015-06-10 | 2015-05-18 | 2015-06-10 | 16 | 2015-08-19 | 2015-08-19 | 2015-11-12 | 60 | 9000 | [6 empty] | 2016-03-10 | 2016-03-17 |  | Y |  | There are 2 accounts at this location with an aggregate CESIR Cost to Customer of $18,000 .
Central Hudson |  | Arosa Solar | CH-00737 | Kingston | Ellenvl |  | 12428 | G | 3076 | Greenfield Rd | TBD |  | 84 | [13 empty] | RNM | N | (3) Solectria PVI 28TL | 2015-05-18 | 2015-06-10 | 16 | 2015-06-10 | 2015-05-18 | 2015-06-10 | 16 |  | 2015-08-19 | 2015-11-12 | 60 | 9000 | [9 empty] | W |  | 5/25/15 & 9/7/15 Company Holidays. CESIR determined necessary during preliminary review Section C, Step 4. There are 2 accounts at this location with an aggregate CESIR Cost to Customer of $18,000 & Estimated Project Upgrade Costs of $646,000.
Central Hudson |  | Hudson Solar | CH-01649 | Kingston | Olive Brdg | Ulster | 12461 | G | 3024 | High Falls | N | CH-01649 | 3 | [13 empty] | NM | N | SMA AMERICA SB3000 TL-US-22 | 2014-10-06 | 2014-10-17 | 9 | 2014-10-17 | [14 empty] | 2014-12-17 | 2014-12-26 |  | Y
Central Hudson |  | SolarCity | CH-04945 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7053 | Rhinebeck | N | CH-04945 | 3.8 | [13 empty] | NM | N | SOLAREDGE SE3000A | 2014-10-06 | 2014-10-17 | 9 | 2014-10-17 | [14 empty] | 2015-05-05 | 2015-05-12 |  | Y
Central Hudson |  | SolarCity | CH-05548 | Catskill | Leeds | Greene | 12451 | G | 2005 | North Catskill | N |  | 9 | [13 empty] | NM | N | (1) SOLAREDGE SE3000A USZBU (1) SOLAREDGE SE6000A US-ZB-U | 2014-10-06 | 2014-10-17 | 9 | 2014-10-17 | [14 empty] | 2015-01-14 | 2015-01-21 |  | Y
Central Hudson |  | SolarCity | CH-06255 | Newburgh | Newburgh | Orange | 12550 | G | 4046 | Union Ave | N |  | 10 | [13 empty] | NM | N | SOLAREDGE SE5000A (2) | 2014-10-06 | 2014-10-17 | 9 | 2014-10-17 | [14 empty] | 2014-12-26 | 2014-12-31 |  | Y
Central Hudson |  | SolarCity | CH-06584 | Kingston | Woodstock | Ulster | 12498 | G | 3014 | Woodstock | N |  | 9.8 | [13 empty] | NM | N | (1) SOLAREDGE SE3800A US-ZB (1) SOLAREDGE SE6000A US-ZB | 2014-10-06 | 2014-10-13 | 5 | 2014-10-13 | [14 empty] | 2015-01-06 | 2015-01-13 |  | Y
Central Hudson |  | SolarCity | CH-06813 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8044 | Myers Corners | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE3800A (2) | 2014-10-06 | 2014-10-16 | 8 | 2014-10-16 | [14 empty] | 2014-11-26 | 2014-12-03 |  | Y
Central Hudson |  | SolarCity | CH-06996 | Newburgh | Newburgh | Orange | 12550 | G | 4023 | Coldenham | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A (1) | 2014-10-06 | 2014-10-17 | 9 | 2014-10-17 | [14 empty] | 2014-11-26 | 2014-12-03 |  | Y
Central Hudson |  | SolarCity | CH-07149 | Newburgh | Montgomery | Orange | 12549 | G | 5073 | Montgomery | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE3800A (2) | 2014-10-06 | 2014-10-16 | 8 | 2014-10-16 | [14 empty] | 2015-01-05 | 2015-01-12 |  | Y
Central Hudson |  | SolarCity | CH-07405 | Fishkill | Cold Spg | Putnam | 10516 | G | 8087 | Tioronda | N |  | 3 | [13 empty] | NM | N | SOLAREDGE SE3000A (1) | 2014-10-06 | 2014-10-17 | 9 | 2014-10-17 | [14 empty] | 2015-01-22 | 2015-01-29 |  | Y
Central Hudson |  | Sungevity Inc | CH-09346 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8092 | Fishkill Plains | N |  | 5 | [13 empty] | NM | N | SMA AMERICA SB5000TL-US (1) | 2014-10-06 | 2014-10-17 | 9 | 2014-10-17 | [14 empty] | 2014-12-26 | 2014-12-31 |  | Y
Central Hudson |  | Sungevity Inc | CH-09347 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8092 | Fishkill Plains | N |  | 5 | [13 empty] | NM | N | SMA SB5000TL (1) | 2014-10-06 | 2014-10-17 | 9 | 2014-10-17 | [14 empty] | 2014-12-10 | 2014-12-10 |  | Y
Central Hudson |  | Sungevity Inc | CH-09562 | Kingston | Kerhonkson | Ulster | 12446 | G | 3081 | Kerhonkson | N |  | 12.6 | [13 empty] | NM | N | (1) SMA SB5000TL (2) SMA SB3800TL | 2014-10-06 | 2014-10-13 | 5 | 2014-10-13 | [14 empty] | 2015-01-02 | 2015-01-07 |  | Y
Central Hudson |  | NRG Home Solar | CH-04531 | Kingston | Saugerties | Ulster | 12477 | G | 3004 | Saugerties | N |  | 3.87 | [13 empty] | NM | N | (18) ENPHASE ENERGY M-215-60-2LL-S22-IG | 2014-10-07 | 2014-10-17 | 8 | 2014-10-17 | [14 empty] | 2014-12-17 | 2014-12-26 |  | Y
Central Hudson |  | SolarCity | CH-06457 | Catskill | Leeds | Greene | 12451 | G | 2006 | North Catskill | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE6000A US-ZB-U | 2014-10-07 | 2014-10-17 | 8 | 2014-10-17 | [14 empty] | 2015-02-12 | 2015-02-19 |  | Y
Central Hudson |  | SolarCity | CH-06737 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6093 | Manchester | N |  | 3.8 | [13 empty] | NM | N | SOLAREDGE SE3800A | 2014-11-26 | 2014-12-09 | 7 | 2014-12-09 | [14 empty] | 2014-12-19 | 2014-12-23 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | US Energy Concierge, Inc. | CH-09745 | Catskill | Lexington | Greene | 12452 | E | 2389 | Vinegar Hill | N |  | 3.8 | [13 empty] | NM | N | POWER ONE PVI 3.8 | 2014-10-07 | 2014-10-17 | 8 | 2014-10-17 | [14 empty] | 2015-02-17 | 2015-02-24 |  | Y
Central Hudson |  | Verengo Solar | CH-09884 | Newburgh | Cornwall | Orange | 12518 | G | 4094 | Bethlehem Rd | N |  | 8.6 | [13 empty] | NM | N | ENPHASE ENERGY M215 (40) | 2014-10-07 | 2014-10-17 | 8 | 2014-10-17 | [14 empty] | 2014-11-18 | 2014-11-25 |  | Y
Central Hudson |  | New York State Solar Farm | CH-04031 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8091 | Fishkill Plains | N |  | 5 | [13 empty] | NM | N | POWERONE PVI 5.0 | 2014-10-16 | 2014-10-23 | 5 | 2014-10-23 | [14 empty] | 2014-12-10 | 2014-12-16 |  | Y
Central Hudson |  | New York State Solar Farm | CH-04076 | Newburgh | New Paltz | Ulster | 12561 | G | 5011 | Modena | N |  | 3.8 | [13 empty] | NM | N | SMA AMERICA SB SB3.8 (1) | 2014-10-08 | 2014-10-17 | 7 | 2014-10-17 | [14 empty] | 2015-01-15 | 2015-01-22 |  | Y
Central Hudson |  | SolarCity | CH-07277 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6065 | Inwood Ave | N |  | 3 | [13 empty] | NM | N | SOLAREDGE SE3000A-US | 2014-10-08 | 2014-10-15 | 5 | 2014-10-15 | [14 empty] | 2014-10-31 | 2014-11-07 |  | Y
Central Hudson |  | Solar Generation | CH-08217 | Kingston | Kingston | Ulster | 12401 | G | 1012 | Boulevard | N |  | 11 | [13 empty] | NM | N | SOLAREDGE SE 6000 A | 2014-10-08 | 2014-10-17 | 7 | 2014-10-17 | [14 empty] | 2014-12-16 | 2014-12-23 |  | Y
Central Hudson |  | New York State Solar Farm | CH-03920 | Kingston | Saugerties | Ulster | 12477 | G | 3004 | Saugerties | N |  | 12 | [13 empty] | NM | N | (2) POWERONE PVI 6.0 | 2014-10-09 | 2014-10-17 | 6 | 2014-10-17 | [14 empty] | 2014-11-24 | 2014-12-01 |  | Y
Central Hudson |  | New York State Solar Farm | CH-04090 | Newburgh | Gardiner | Ulster | 12525 | G | 5011 | Modena | N |  | 12 | [13 empty] | NM | N | POWERONE PVI 6.0 (2) | 2014-10-09 | 2014-10-17 | 6 | 2014-10-17 | [8 empty] | 350 | 350 |  |  |  |  | 2015-01-08 | 2015-01-13 |  | Y
Central Hudson |  | Aegis Energy Services, Inc. | CH-00637 | Fishkill | Beacon | Dutchess | 12508 | G | 8015 | Forgebrook | N | [9 empty] | 75 | [5 empty] | NA | N | Aegen Thermo Power TP-75 | 2014-11-07 | 2014-12-02 | 15 | 2014-12-02 | 2014-11-07 | 2014-12-02 | 15 | 2014-12-23 | 2014-12-23 | 2015-03-20 | 59 | 3000 | [6 empty] | 2015-05-13 | 2015-05-15 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Murphy Solar Power | CH-02717 | Newburgh | Montgomery | Orange | 12549 | G | 5073 | Montgomery | N |  | 8 | [13 empty] | NM | N | SMA 8000US (1) | 2014-10-09 | 2014-10-17 | 6 | 2014-10-17 | [14 empty] | 2015-02-10 | 2015-02-18 |  | Y
Central Hudson |  | Solar Generation | CH-08139 | Catskill | Lexington | Ulster | 12457 | E | 2387 | NYSEG | N | CH-08139 | 7.6 | [13 empty] | NM | N | 2 SMA America SB3800TL-US-22 (240V) | 2014-10-09 | 2014-10-17 | 6 | 2014-10-17 | [14 empty] | 2015-01-26 | 2015-02-02 |  | Y
Central Hudson |  | Sungevity Inc | CH-09169 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 6051 | Todd Hill | N |  | 6 | [13 empty] | NM | N | SMA AMERICA SB6000TL-US-22 | 2014-10-09 | 2014-10-16 | 5 | 2014-10-16 | [14 empty] | 2014-12-31 | 2015-01-08 |  | Y
Central Hudson |  | Sungevity Inc | CH-09309 | Kingston | Kingston | Ulster | 12401 | G | 2012 | Lincoln Park | N |  | 8 | [13 empty] | NM | N | (1) SMA AMERICA SB5000TL-US-22 (1) SMA AMERICA SB3000TL-US-22 | 2014-10-09 | 2014-10-20 | 7 | 2014-10-20 | [14 empty] | 2014-11-18 | 2014-11-25 |  | Y
Central Hudson |  | Sungevity Inc | CH-09619 | Kingston | West Hurley |  | 12491 | G | 2094 | Hurley Ave | TBD |  | 5 | [13 empty] | NM | N | SMA AMERICA SB5000TL-US-22 | 2014-10-09 | 2014-10-20 | 7 | 2014-10-20 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | NRG Home Solar | CH-04431 | Fishkill | Beacon | Dutchess | 12508 | G | 8085 | Tioronda | N |  | 5.805 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (27) | 2014-10-10 | 2014-10-17 | 5 | 2014-10-17 | [14 empty] | 2015-02-18 | 2015-02-25 |  | Y
Central Hudson |  | NRG Home Solar | CH-04566 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 7024 | Tinkertown | N |  | 8.815 | [13 empty] | NM | N | 41 - ENPHASE ENERGY M-215 | 2014-10-10 | 2014-10-17 | 5 | 2014-10-17 | [14 empty] | 2015-01-13 | 2015-01-19 |  | Y
Central Hudson |  | NRG Home Solar | CH-04709 | Poughkeepsie | Pleasant Vly |  | 12569 | G | 6092 | Manchester | TBD |  | 6.88 | [13 empty] | NM | N | 32 - ENPHASE ENERGY M-215 | 2014-10-10 | 2014-10-17 | 5 | 2014-10-17 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | US Energy Concierge, Inc. | CH-09739 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8091 | Fishkill Plains | N |  | 7.7 | [13 empty] | NM | N | SB 7700 (1) | 2014-10-20 | 2014-10-28 | 6 | 2014-10-28 | [14 empty] | 2014-12-31 | 2015-01-07 |  | Y
Central Hudson |  | RGS Energy | CH-03004 | Fishkill | Hopewell Jct |  | 12533 | G | 8072 | Shenandoah | TBD |  | 11 | [13 empty] | NM | N | ENPHASE M250 (44) | 2014-10-13 | 2014-10-21 | 6 | 2014-10-21 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | Sungevity Inc | CH-09297 | Kingston | Grahamsvl | Sullivan | 12740 | G | 3091 | Neversink | N |  | 10 | [13 empty] | NM | N | (1) SMA SB6000TL US-22 (1) SMA SB4000TL US-22 | 2014-10-13 | 2014-10-20 | 5 | 2014-10-20 | [14 empty] | 2014-12-02 | 2014-12-09 |  | Y
Central Hudson |  | Sungevity Inc | CH-09340 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8043 | Myers Corners | N |  | 6 | [13 empty] | NM | N | ABB PVI-3.0 (2) | 2014-10-13 | 2014-10-21 | 6 | 2014-10-21 | [14 empty] | 2015-01-12 | 2015-01-19 |  | Y
Central Hudson |  | Verengo Solar | CH-09834 | Newburgh | Newburgh | Orange | 12550 | G | 5004 | Marlboro | N |  | 13.545 | [13 empty] | NM | N | ENPHASE ENERGY M215 (63) | 2014-10-13 | 2014-10-21 | 6 | 2014-10-21 | [14 empty] | 2014-11-07 | 2014-11-13 |  | Y
Central Hudson |  | New York State Solar Farm | CH-04028 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6042 | Spackenkill | N |  | 5 | [13 empty] | NM | N | POWERONE PVI 5.0 (1) | 2014-10-21 | 2014-10-29 | 6 | 2014-10-29 | [14 empty] | 2015-03-05 | 2015-03-11 |  | Y
Central Hudson |  | NRG Home Solar | CH-04141 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8092 | Fishkill Plains | N |  | 8.6 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (40) | 2014-10-14 | 2014-10-21 | 5 | 2014-10-21 | [14 empty] | 2015-01-28 | 2015-02-04 |  | Y
Central Hudson |  | NRG Home Solar | CH-04326 | Poughkeepsie | Lagrangevl | Dutchess | 12540 | G | 6057 | Todd Hill | N |  | 4.73 | [13 empty] | NM | N | 22 - ENPHASE ENERGY M-215 | 2014-10-23 | 2014-10-30 | 5 | 2014-10-30 | [14 empty] | 2014-12-30 | 2014-12-31 |  | Y
Central Hudson |  | NRG Home Solar | CH-04354 | Poughkeepsie | Rhinecliff |  | 12574 | G | 7055 | Rhinebeck | TBD |  | 7.31 | [13 empty] | NM | N | 34 - ENPHASE ENERGY M-215 | 2014-10-14 | 2014-10-22 | 6 | 2014-10-22 | [17 empty] | W
Central Hudson |  | Autonomous Energies LLC | CH-00743 | Newburgh | Highland | Ulster | 12528 | G | 5083 | Highland | N |  | 6 | [13 empty] | NM | N | SMA SB 6000TL | 2014-10-14 | 2014-10-21 | 5 | 2014-10-21 | [14 empty] | 2014-11-04 | 2014-11-10 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00867 | Poughkeepsie | Pine Plns | Dutchess | 12567 | G | 7091 | Pulvers Corners | N |  | 8.385 | [13 empty] | NM | N | 39 - ENPHASE M215 | 2014-10-14 | 2014-10-21 | 5 | 2014-10-21 | [14 empty] | 2015-02-17 | 2015-02-23 |  | Y
Central Hudson |  | SolarCity | CH-05709 | Kingston | Cragsmoor | Ulster | 12420 | G | 3078 | Greenfield Rd | N |  | 13.6 | [13 empty] | NM | N | (1) SOLAREDGE SE7600A-US ZB (1) SOLAREDGE SE6000A-US ZB | 2014-10-14 | 2014-10-21 | 5 | 2014-10-21 | [14 empty] | 2014-12-31 | 2015-01-08 |  | Y
Central Hudson |  | SolarCity | CH-05920 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6046 | Spackenkill | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A-US | 2014-10-14 | 2014-10-21 | 5 | 2014-10-21 | [14 empty] | 2014-11-03 | 2014-11-07 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06185 | Newburgh | Clintondale | Ulster | 12515 | G | 5012 | Modena | N |  | 3.8 | [13 empty] | NM | N | SOLAREDGE SE3800A-US (1) | 2014-10-14 | 2014-10-21 | 5 | 2014-10-21 | [14 empty] | 2014-12-17 | 2014-12-22 |  | Y
Central Hudson |  | Sungevity Inc | CH-09350 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8092 | Fishkill Plains | N | CH-09350 | 5 | [13 empty] | NM | N | SMA AMERICA SB5000TL-US (1) | 2014-10-14 | 2014-10-21 | 5 | 2014-10-21 | [14 empty] | 2014-12-01 | 2014-12-08 |  | Y
Central Hudson |  | Verengo Solar | CH-09763 | Newburgh | Newburgh | Orange | 12550 | G | 5004 | Marlboro | N |  | 6.45 | [13 empty] | NM | N | ENPHASE ENERGY M215 (30) | 2014-10-14 | 2014-10-21 | 5 | 2014-10-21 | [14 empty] | 2014-12-05 | 2014-12-11 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03601 | Kingston | Ulster Pk | Ulster | 12487 | G | 1014 | Boulevard | N |  | 48.6 | [13 empty] | RNM | N | 3 - POWERONE PVI 8.6 3 - POWERONE PVI 7.6 | 2015-05-20 | 2015-06-11 | 15 | 2015-06-11 | 2015-05-20 | 2015-06-11 | 15 | [11 empty] | 2015-12-07 | 2015-12-14 |  | Y
Central Hudson |  | Lotus Energy Inc. | CH-03854 | Catskill | Freehold | Greene | 12431 | G | 2071 | Freehold | N |  | 7 | [13 empty] | NM | N | SMA SB7000 US | 2014-10-15 | 2014-10-22 | 5 | 2014-10-22 | [14 empty] | 2014-11-25 | 2014-12-03 |  | Y
Central Hudson |  | Lotus Energy Inc. | CH-03867 | Kingston | Woodstock | Ulster | 12498 | G | 3014 | Woodstock | N |  | 8 | [13 empty] | NM | N | SUNPOWER 8000 M | 2014-10-15 | 2014-10-22 | 5 | 2014-10-22 | [14 empty] | 2015-02-18 | 2015-02-25 |  | Y
Central Hudson |  | NRG Home Solar | CH-04303 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6046 | Spackenkill | N |  | 8.815 | [13 empty] | NM | N | 41 - ENPHASE ENERGY M-215 | 2014-10-15 | 2014-10-22 | 5 | 2014-10-22 | [14 empty] | 2015-05-12 | 2015-05-18 |  | Y
Central Hudson |  | NRG Home Solar | CH-04339 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 6092 | Manchester | N |  | 12.04 | [13 empty] | NM | N | 41 - ENPHASE ENERGY M-215 | 2014-10-15 | 2014-10-22 | 5 | 2014-10-22 | [14 empty] | 2015-06-01 | 2015-06-08 |  | Y
Central Hudson |  | NRG Home Solar | CH-04725 | Fishkill | Fishkill | Dutchess | 12524 | G | 8051 | North Chelsea | N |  | 5.805 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (27) | 2014-10-15 | 2014-10-22 | 5 | 2014-10-22 | [14 empty] | 2015-10-22 | 2015-10-27 |  | Y
Central Hudson |  | NRG Home Solar | CH-04726 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8051 | North Chelsea | N |  | 8.815 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (41) | 2014-10-15 | 2014-10-22 | 5 | 2014-10-22 | [14 empty] | 2015-01-28 | 2015-02-04 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00904 | Kingston | Grahamsvl | Sullivan | 12740 | G | 3091 | Neversink | N |  | 9.675 | [13 empty] | NM | N | (45) ENPHASE M215 60-240-S22 | 2014-10-15 | 2014-10-22 | 5 | 2014-10-22 | [8 empty] | 350 | 350 |  | 2014-12-12 | 2014-12-12 | 2015-01-19 | 2015-01-19 | 2015-01-20 |  | Y
Central Hudson |  | Monolith Solar Associates LLC | CH-02681 | Catskill | Westerlo | Albany | 12193 | G | 1091 | Westerlo | N |  | 7.7 | [13 empty] | NM | N | (2) SMA SB4000 US-22 | 2014-10-15 | 2014-10-22 | 5 | 2014-10-22 | [14 empty] | 2015-07-01 | 2015-07-08 |  | Y
Central Hudson |  | SolarCity | CH-06747 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6097 | Manchester | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A | 2014-10-15 | 2014-10-22 | 5 | 2014-10-22 | [14 empty] | 2015-02-10 | 2015-02-18 |  | Y
Central Hudson |  | RGS Energy | CH-03029 | Kingston | Woodstock | Ulster | 12498 | G | 3014 | Woodstock | N |  | 4.3 | [13 empty] | NM | N | (20) ENPHASE M250-60-2LL-S22 | 2014-10-16 | 2014-10-23 | 5 | 2014-10-23 | [14 empty] | 2015-02-19 | 2015-02-26 |  | Y
Central Hudson |  | New York State Solar Farm | CH-04002 | Newburgh | New Windsor | Orange | 12553 | G | 4044 | Union Ave | N |  | 7.6 | [13 empty] | NM | N | POWERONE OUTD PVI 3.8 (2) | 2014-10-27 | 2014-10-29 | 2 | 2014-10-29 | [14 empty] | 2015-01-21 | 2015-01-28 |  | Y
Central Hudson |  | Apex Solar Power | CH-00672 | Kingston | Saugerties | Ulster | 12477 | G | 3002 | Saugerties | N |  | 6.88 | [13 empty] | NM | N | SUNNYBOY 7000 TL-US-22 | 2014-10-16 | 2014-10-23 | 5 | 2014-10-23 | [14 empty] | 2015-07-14 | 2015-07-20 |  | Y
Central Hudson |  | Solar Generation | CH-08065 | Kingston | West Shokan | Ulster | 12494 | G | 3011 | Woodstock | N |  | 10 | [13 empty] | NM | N | (2) SMA SB 5000 TL | 2014-10-16 | 2014-10-23 | 5 | 2014-10-23 | [14 empty] | 2015-05-19 | 2015-05-20 |  | Y
Central Hudson |  | Sungevity Inc | CH-09212 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8045 | Myers Corners | N |  | 6 | [13 empty] | NM | N | ABB PVI 6000 | 2014-10-16 | 2014-10-22 | 4 | 2014-10-22 | [14 empty] | 2014-12-10 | 2014-12-16 |  | Y
Central Hudson |  | Verengo Solar | CH-09788 | Kingston | Kingston | Ulster | 12401 | G | 1022 | East Kingston | N |  | 7.31 | [13 empty] | NM | N | 34 ENPHASE ENERGY M215-60-2LL-S2X-IG | 2014-10-16 | 2014-10-23 | 5 | 2014-10-23 | [14 empty] | 2015-01-20 | 2015-01-26 |  | Y
Central Hudson |  | Verengo Solar | CH-09795 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6046 | Spackenkill | N |  | 5.805 | [13 empty] | NM | N | 27 - ENPHASE ENERGY M215 | 2014-10-16 | 2014-10-23 | 5 | 2014-10-23 | [14 empty] | 2015-04-07 | 2015-04-14 |  | Y
Central Hudson |  | Verengo Solar | CH-09825 | Newburgh | New Windsor | Orange | 12553 | G | 4046 | Union Ave | N |  | 4.73 | [13 empty] | NM | N | ENPHASE ENERGY M215 (22) | 2014-10-16 | 2014-10-22 | 4 | 2014-10-22 | [14 empty] | 2014-12-16 | 2014-12-22 |  | Y
Central Hudson |  | Verengo Solar | CH-09839 | Newburgh | Wallkill | Ulster | 12589 | G | 5041 | East Walden | N |  | 11.395 | [13 empty] | NM | N | ENPHASE ENERGY M215 (53) | 2014-10-16 | 2014-10-22 | 4 | 2014-10-22 | [14 empty] | 2015-02-04 | 2015-02-11 |  | Y
Central Hudson |  | Verengo Solar | CH-09880 | Newburgh | Marlboro | Ulster | 12542 | G | 5003 | Marlboro | N |  | 6.45 | [13 empty] | NM | N | ENPHASE ENERGY M215 (30) | 2014-10-16 | 2014-10-22 | 4 | 2014-10-22 | [14 empty] | 2014-12-22 | 2014-12-31 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-03382 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8095 | Fishkill Plains | N |  | 10 | [13 empty] | NM | N | FRONIUS IG PLUS A 10.0 (1) | 2014-10-17 | 2014-10-23 | 4 | 2014-10-23 | [14 empty] | 2015-03-19 | 2015-03-26 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-03429 | Newburgh | Wallkill | Ulster | 12589 | G | 4011 | West Balmville | N |  | 14 | [13 empty] | NM | N | SMA AMERICA SB7000US (2) | 2014-10-17 | 2014-10-23 | 4 | 2014-10-23 | [14 empty] | 2015-02-19 | 2015-02-26 |  | Y
Central Hudson |  | SolarCity | CH-05081 | Newburgh | New Paltz | Ulster | 12561 | G | 5012 | Modena | N |  | 7.5 | [13 empty] | NM | N | Fronius IG Plus 7.5 | 2014-10-17 | 2014-10-23 | 4 | 2014-10-23 | [14 empty] | 2015-01-13 | 2015-01-19 |  | Y
Central Hudson |  | SolarCity | CH-06259 | Newburgh | New Windsor | Orange | 12553 | G | 4045 | Union Ave | N |  | 10 | [13 empty] | NM | N | SOLAREDGE #SE5000A (2) | 2014-10-17 | 2014-10-23 | 4 | 2014-10-23 | [14 empty] | 2014-11-26 | 2014-12-03 |  | Y
Central Hudson |  | Verengo Solar | CH-09773 | Newburgh | New Windsor | Orange | 12553 | G | 4094 | Bethlehem Rd | N |  | 10.96 | [13 empty] | NM | N | ENPHASE ENERGY M215 (51) | 2014-10-17 | 2014-10-23 | 4 | 2014-10-23 | [14 empty] | 2015-01-06 | 2015-01-06 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00950 | Newburgh | Highland | Ulster | 12528 | G | 5083 | Highland | N |  | 8.385 | [13 empty] | NM | N | 39 - ENPHASE M215 | 2014-10-28 | 2014-11-03 | 4 | 2014-11-03 | [14 empty] | 2015-01-13 | 2015-01-19 |  | Y
Central Hudson |  | SolarCity | CH-05849 | Poughkeepsie | Staatsburg | Dutchess | 12580 | G | 7041 | Staatsburg | N |  | 11 | [13 empty] | NM | N | 1 - SOLAREDGE SE6000A-US 1 - SOLAREDGE SE5000A-US | 2014-10-20 | 2014-11-03 | 10 | 2014-11-03 | [8 empty] | 350 | 350 |  |  |  |  | 2014-12-02 | 2014-12-04 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06217 | Newburgh | Newburgh | Orange | 12550 | G | 4027 | Coldenham | N |  | 11 | [13 empty] | NM | N | SOLAREDGE SE5000A (1) SOLAREDGE SE6000A (1) | 2014-10-20 | 2014-10-28 | 6 | 2014-10-28 | [14 empty] | 2015-02-26 | 2015-03-05 |  | Y
Central Hudson |  | SolarCity | CH-06345 | Newburgh | Wallkill | Ulster | 12589 | G | 5043 | East Walden | N |  | 9.8 | [13 empty] | NM | N | SOLAREDGE SE3800A (1) SOLAREDGE SE6000A (1) | 2014-10-20 | 2014-10-28 | 6 | 2014-10-28 | [14 empty] | 2014-11-18 | 2014-11-21 |  | Y
Central Hudson |  | SolarCity | CH-07070 | Newburgh | Newburgh | Orange | 12550 | G | 5004 | Marlboro | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A (1) | 2014-10-20 | 2014-10-28 | 6 | 2014-10-28 | [14 empty] | 2014-10-30 | 2014-11-05 |  | Y
Central Hudson |  | Sungevity Inc | CH-09470 | Newburgh | Walden | Orange | 12586 | G | 5041 | East Walden | N |  | 7.6 | [13 empty] | NM | N | SMA AMERICA SB3800TL (2) | 2014-10-20 | 2014-10-28 | 6 | 2014-10-28 | [14 empty] | 2015-04-20 | 2015-04-27 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00938 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7051 | Rhinebeck | N |  | 7.75 | [13 empty] | NM | N | 31 - ENPHASE M250 | 2014-10-21 | 2014-10-28 | 5 | 2014-10-28 | [14 empty] | 2014-12-19 | 2014-12-23 |  | Y
Central Hudson |  | SolarCity | CH-05391 | Newburgh | Newburgh | Orange | 12550 | G | 4023 | Coldenham | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A (1) | 2014-10-21 | 2014-10-29 | 6 | 2014-10-29 | [14 empty] | 2014-12-08 | 2014-12-15 |  | Y
Central Hudson |  | SolarCity | CH-05922 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6052 | Todd Hill | N |  | 5 | [13 empty] | NM | N | POWER-ONE (ABB) PVI-5000-OUTD | 2014-10-21 | 2014-10-28 | 5 | 2014-10-28 | [14 empty] | 2014-12-30 | 2014-12-31 |  | Y
Central Hudson |  | SolarCity | CH-06150 | Fishkill | Beacon | Dutchess | 12508 | G | 8087 | Tioronda | N |  | 3.8 | [13 empty] | NM | N | SOLAREDGE SE3800A (1) | 2014-10-21 | 2014-10-29 | 6 | 2014-10-29 | [14 empty] | 2015-02-02 | 2015-02-09 |  | Y
Central Hudson |  | SolarCity | CH-06286 | Newburgh | Newburgh | Orange | 12550 | G | 4045 | Union Ave | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A | 2014-10-21 | 2014-10-29 | 6 | 2014-10-29 | [14 empty] | 2015-01-05 | 2015-01-12 |  | Y
Central Hudson |  | SolarCity | CH-06297 | Newburgh | Marlboro | Ulster | 12542 | G | 5004 | Marlboro | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A-US (1) | 2014-10-21 | 2014-10-29 | 6 | 2014-10-29 | [14 empty] | 2015-01-05 | 2015-01-06 |  | Y
Central Hudson |  | SolarCity | CH-06564 | Kingston | Ellenvl | Ulster | 12428 | G | 3078 | Greenfield Rd | N | CH-06564 | 3.8 | [13 empty] | NM | N | SOLAREDGE SE3800A US-ZB-U | 2014-10-21 | 2014-10-27 | 4 | 2014-10-27 | [14 empty] | 2015-01-02 | 2015-01-09 |  | Y
Central Hudson |  | SolarCity | CH-06908 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8071 | Shenandoah | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A | 2014-10-21 | 2014-10-28 | 5 | 2014-10-28 | [14 empty] | 2015-01-08 | 2015-01-15 |  | Y
Central Hudson |  | SolarCity | CH-07061 | Newburgh | Newburgh | Orange | 12550 | G | 4011 | West Balmville | N |  | 7.2 | [13 empty] | NM | N | POWER-ONE (ABB) PVI-4.2 (1) POWER-ONE (ABB) PVI-3.0 (1) | 2014-10-21 | 2014-10-28 | 5 | 2014-10-28 | [14 empty] | 2014-12-31 | 2015-01-02 |  | Y
Central Hudson |  | SolarCity | CH-07176 | Newburgh | New Windsor | Orange | 12553 | G | 4094 | Bethlehem Rd | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A | 2014-10-21 | 2014-10-29 | 6 | 2014-10-29 | [14 empty] | 2014-11-26 | 2014-12-03 |  | Y
Central Hudson |  | SolarCity | CH-07530 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 7011 | Hibernia | N |  | 5 | [13 empty] | NM | N | ABB PVI-5000-OUTD | 2014-10-21 | 2014-10-28 | 5 | 2014-10-28 | [14 empty] | 2014-12-09 | 2014-12-15 |  | Y
Central Hudson |  | Sungevity Inc | CH-09419 | Kingston | Kingston | Ulster | 12401 | G | 1021 | East Kingston | N |  | 4 | [13 empty] | NM | N | SMA AMERICA SB4000TL-US-22 | 2014-10-21 | 2014-10-28 | 5 | 2014-10-28 | [14 empty] | 2014-12-18 | 2014-12-29 |  | Y
Central Hudson |  | Verengo Solar | CH-09819 | Newburgh | Newburgh | Orange | 12550 | G | 4024 | Coldenham | N |  | 7.31 | [13 empty] | NM | N | ENPHASE ENERGY M215 (34) | 2014-10-21 | 2014-10-29 | 6 | 2014-10-29 | [14 empty] | 2014-12-26 | 2014-12-31 |  | Y
Central Hudson |  | Paradise Energy Solutions LLC | CH-02849 | Newburgh | New Paltz | Ulster | 12561 | G | 5011 | Modena | N |  | 7.6 | [13 empty] | NM | N | SOLAR EDGE 7600 A-US (1) | 2014-10-22 | 2014-10-29 | 5 | 2014-10-29 | [14 empty] | 2014-12-23 | 2014-12-31 |  | Y
Central Hudson |  | SolarCity | CH-05298 | Newburgh | Marlboro | Ulster | 12542 | G | 5004 | Marlboro | N |  | 8 | [13 empty] | NM | N | SOLAREDGE SE5000A (1) SOLAREDGE 3000A (1) | 2014-10-22 | 2014-10-29 | 5 | 2014-10-29 | [14 empty] | 2015-01-06 | 2015-01-13 |  | Y
Central Hudson |  | SolarCity | CH-05803 | Poughkeepsie | Poughkeepsie |  | 12603 | G | 6095 | Manchester | TBD |  | 5 | [13 empty] | NM | N | ABB PVI-5000 | 2014-10-22 | 2014-10-29 | 5 | 2014-10-29 | [17 empty] | W
Central Hudson |  | SolarCity | CH-05877 | Poughkeepsie | Lagrangevl | Dutchess | 12540 | G | 6057 | Todd Hill | N |  | 10.2 | [13 empty] | NM | N | 1 - POWER-ONE (ABB) PVI-4.2 1 - POWER-ONE (ABB) PVI-6000 | 2014-10-22 | 2014-10-29 | 5 | 2014-10-29 | [14 empty] | 2014-12-09 | 2014-12-15 |  | Y
Central Hudson |  | SolarCity | CH-06904 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8072 | Shenandoah | N |  | 17 | [13 empty] | NM | N | SOLAREDGE SE6000A (2) SOLAREDGE SE5000A (1) | 2014-10-22 | 2014-10-29 | 5 | 2014-10-29 | [14 empty] | 2015-01-22 | 2015-01-29 |  | Y
Central Hudson |  | Sungevity Inc | CH-09271 | Kingston | Olive Brdg | Ulster | 12461 | G | 2094 | Hurley Ave | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000-OUTD-US-A | 2014-10-22 | 2014-10-29 | 5 | 2014-10-29 | [14 empty] | 2014-12-17 | 2014-12-26 |  | Y
Central Hudson |  | Sungevity Inc | CH-09551 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 4.2 | [13 empty] | NM | N | ABB PVI-4.2 (1) | 2014-10-22 | 2014-10-29 | 5 | 2014-10-29 | [14 empty] | 2014-11-24 | 2014-12-03 |  | Y
Central Hudson |  | RGS Energy | CH-03006 | Fishkill | Wappingrs Falls |  | 12590 | G | 8046 | Myers Corners | TBD |  | 10 | [13 empty] | NM | N | ENPHASE M250 (40) | 2014-10-23 | 2014-10-30 | 5 | 2014-10-30 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | RGS Energy | CH-03023 | Catskill | Hannacroix | Greene | 12087 | G | 1083 | New Baltimore | N |  | 12.75 | [13 empty] | NM | N | ENPHASE M250-60-2LL-S22 | 2014-10-23 | 2014-10-30 | 5 | 2014-10-30 | [8 empty] | 350 | 350 |  |  |  |  | 2015-03-09 | 2015-03-16 |  | Y
Central Hudson |  | NRG Home Solar | CH-04307 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6011 | Sand Dock | N |  | 6.88 | [13 empty] | NM | N | 32 - ENPHASE ENERGY M-215 | 2014-10-23 | 2014-10-31 | 6 | 2014-10-31 | [14 empty] | 2015-07-27 | 2015-07-31 |  | Y
Central Hudson |  | NRG Home Solar | CH-04757 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6011 | Sand Dock | N |  | 4.515 | [13 empty] | NM | N | 21 - ENPHASE ENERGY M-215 | 2014-10-23 | 2014-10-30 | 5 | 2014-10-30 | [14 empty] | 2015-10-22 | 2015-10-29 |  | Y
Central Hudson |  | NRG Home Solar | CH-04774 | Newburgh | Newburgh | Orange | 12550 | G | 4027 | Coldenham | N |  | 3.01 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (14) | 2014-10-23 | 2014-10-31 | 6 | 2014-10-31 | [14 empty] | 2015-04-22 | 2015-04-28 |  | W
Central Hudson |  | Monolith Solar Associates LLC | CH-02690 | Catskill | Ravena |  | 12143 | G | 1082 | New Baltimore | TBD |  | 7 | [13 empty] | NM | N | SMA SB7000 - US | 2014-10-23 | 2014-10-30 | 5 | 2014-10-30 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | SolarCity | CH-05297 | Newburgh | Wallkill | Ulster | 12589 | G | 5041 | East Walden | N |  | 11 | [13 empty] | NM | N | SOLAREDGE SE5000A (1) SOLAREDGE SE6000A (1) | 2014-10-23 | 2014-10-30 | 5 | 2014-10-30 | [14 empty] | 2014-12-18 | 2014-12-26 |  | Y
Central Hudson |  | SolarCity | CH-05468 | Kingston | Lk Katrine | Ulster | 12449 | G | 2011 | Lincoln Park | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000-US-ZBU | 2014-10-23 | 2014-10-30 | 5 | 2014-10-30 | [14 empty] | 2015-01-29 | 2015-02-05 |  | Y
Central Hudson |  | SolarCity | CH-05597 | Catskill | Ravena | Albany | 12143 | G | 1081 | New Baltimore | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE7600A US-ZB-U | 2014-10-23 | 2014-10-30 | 5 | 2014-10-30 | [14 empty] | 2015-01-05 | 2015-01-12 |  | Y
Central Hudson |  | SolarCity | CH-05600 | Catskill | Ravena | Albany | 12143 | G | 1081 | New Baltimore | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A US-ZB-U | 2014-10-23 | 2014-10-30 | 5 | 2014-10-30 | [14 empty] | 2014-12-17 | 2014-12-26 |  | Y
Central Hudson |  | SolarCity | CH-05631 | Kingston | Tillson |  | 12486 | G | 3022 | High Falls | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A US-Z-A | 2014-10-23 | 2014-10-30 | 5 | 2014-10-30 | [14 empty] | 2015-01-05 | 2015-01-12 |  | W
Central Hudson |  | SolarCity | CH-05997 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8091 | Fishkill Plains | N |  | 6.6 | [13 empty] | NM | N | ABB PIV-3.0OUTD (1) ABB PVI-3.6-OUTD (1) | 2014-10-23 | 2014-10-31 | 6 | 2014-10-31 | [14 empty] | 2015-01-05 | 2015-01-12 |  | Y
Central Hudson |  | SolarCity | CH-06778 | Poughkeepsie | Millerton | Dutchess | 12546 | G | 7081 | Millerton | N |  | 5 | [13 empty] | NM | N | ABB PVI-5000-OUTD | 2014-10-23 | 2014-10-30 | 5 | 2014-10-30 | [14 empty] | 2014-12-19 | 2014-12-23 |  | Y
Central Hudson |  | SolarCity | CH-06839 | Fishkill | Stormvl | Dutchess | 12582 | G | 8095 | Fishkill Plains | N |  | 9.8 | [13 empty] | NM | N | SOLAREDGE SE6000A-US (1) SOLAREDGE SE3800A-US (1) | 2014-10-23 | 2014-10-30 | 5 | 2014-10-30 | [14 empty] | 2014-12-26 | 2014-12-31 |  | Y
Central Hudson |  | SolarCity | CH-07177 | Newburgh | New Windsor | Orange | 12553 | G | 4094 | Bethlehem Rd | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A-US (1) | 2014-10-23 | 2014-10-30 | 5 | 2014-10-30 | [14 empty] | 2015-01-05 | 2015-01-12 |  | Y
Central Hudson |  | SolarCity | CH-07306 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6046 | Spackenkill | N |  | 3.6 | [13 empty] | NM | N | ABB PVI-3.6-OUTD | 2014-10-23 | 2014-10-31 | 6 | 2014-10-31 | [14 empty] | 2015-01-26 | 2015-02-02 |  | Y
Central Hudson |  | SolarCity | CH-07363 | Fishkill | Fishkill | Dutchess | 12524 | G | 8094 | Fishkill Plains | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A-US (1) | 2014-10-23 | 2014-10-31 | 6 | 2014-10-31 | [14 empty] | 2015-01-05 | 2015-01-12 |  | Y
Central Hudson |  | SolarCity | CH-07464 | Newburgh | Modena | Ulster | 12548 | G | 5012 | Modena | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A (1) | 2014-10-23 | 2014-10-30 | 5 | 2014-10-30 | [14 empty] | 2014-12-31 | 2015-01-02 |  | Y
Central Hudson |  | SolarCity | CH-07746 | Fishkill | Garrison | Putnam | 10524 | G | 8066 | Merritt Park | N | CH-07746 | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A-US (1) | 2014-10-23 | 2014-10-31 | 6 | 2014-10-31 | [14 empty] | 2015-01-21 | 2015-01-28 |  | Y
Central Hudson |  | Sungevity Inc | CH-09308 | Kingston | Saugerties | Ulster | 12477 | G | 2015 | Lincoln Park | N |  | 5 | [13 empty] | NM | N | ABB PVI-5000-OUTD-US-A | 2014-10-23 | 2014-10-30 | 5 | 2014-10-30 | [14 empty] | 2014-12-18 | 2014-12-29 |  | Y
Central Hudson |  | Sungevity Inc | CH-09369 | Newburgh | New Paltz |  | 12561 | G | 5023 | Ohioville | TBD |  | 7.6 | [13 empty] | NM | N | SMA AMERICA SB3800TL-US (2) | 2014-10-23 | 2014-10-30 | 5 | 2014-10-30 | [17 empty] | W |  | Customer already had net meter prior to application. 6/17/15 Customer advised not going solar at this time. 7/20/15 Emailed customer & contractor to confirm project abandoned.
Central Hudson |  | Verengo Solar | CH-09900 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8051 | North Chelsea | N |  | 7.095 | [13 empty] | NM | N | ENPHASE ENERGY M215 (33) | 2014-10-23 | 2014-10-31 | 6 | 2014-10-31 | [14 empty] | 2014-12-18 | 2014-12-26 |  | Y
Central Hudson |  | Verengo Solar | CH-09935 | Newburgh | Wallkill |  | 12589 | G | 5041 | East Walden | TBD |  | 7.74 | [13 empty] | NM | N | ENPHASE ENERGY M215 (36) | 2014-10-23 | 2014-10-31 | 6 | 2014-10-31 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | NRG Home Solar | CH-04131 | Fishkill | Stormvl | Dutchess | 12582 | G | 8093 | Fishkill Plains | N |  | 4.75 | [13 empty] | NM | N | ENPHASE ENERGY M-250 (19) | 2014-10-24 | 2014-10-31 | 5 | 2014-10-31 | [14 empty] | 2015-07-28 | 2015-08-03 |  | Y
Central Hudson |  | NRG Home Solar | CH-04422 | Fishkill | Cold Spg |  | 10516 | G | 8063 | Merritt Park | TBD |  | 6.665 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (31) | 2014-10-24 | 2014-10-31 | 5 | 2014-10-31 | [17 empty] | W
Central Hudson |  | SolarCity | CH-05512 | Catskill | Cairo | Greene | 12413 | G | 2043 | South Cairo | N |  | 11 | [13 empty] | NM | N | (1) SOLAREDGE SE6000A US-ZB-U (1) SOLAREDGE SE5000A US-ZB-U | 2014-10-24 | 2014-10-31 | 5 | 2014-10-31 | [8 empty] | 350 | 350 |  |  |  |  | 2015-01-16 | 2015-01-23 |  | Y
Central Hudson |  | SolarCity | CH-06008 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8091 | Fishkill Plains | N |  | 11 | [13 empty] | NM | N | SOLAREDGE SE5000A-US (1) SOLAREDGE SE6000A-US (1) | 2014-10-24 | 2014-10-31 | 5 | 2014-10-31 | [14 empty] | 2015-02-03 | 2015-02-10 |  | Y
Central Hudson |  | SolarCity | CH-07130 | Newburgh | New Windsor | Orange | 12553 | G | 4097 | Bethlehem Rd | N |  | 11 | [13 empty] | NM | N | POWER-ONE (ABB) PVI-6000 (1) POWER-ONE (ABB) PVI-5000 (1) | 2014-10-24 | 2014-10-31 | 5 | 2014-10-31 | [14 empty] | 2014-12-19 | 2014-12-30 |  | Y
Central Hudson |  | SolarCity | CH-07250 | Fishkill | Poughkeepsie | Dutchess | 12603 | G | 8022 | Knapps Corners | N |  | 8.8 | [13 empty] | NM | N | 1 - SOLAREDGE SE3800A-US 1 - SOLAREDGE SE5000A-US | 2014-10-24 | 2014-10-31 | 5 | 2014-10-31 | [14 empty] | 2015-02-10 | 2015-02-18 |  | Y
Central Hudson |  | SolarCity | CH-07264 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6003 | Reynolds Hill | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A-US | 2014-10-24 | 2014-10-31 | 5 | 2014-10-31 | [14 empty] | 2015-01-15 | 2015-01-22 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Monolith Solar Associates LLC | CH-02673 | Fishkill | Cold Spg | Putnam | 10516 | G | 8087 | Tioronda | N |  | 160 | [13 empty] | NM | N | (8) SMA TriPower 20000 | 2014-11-26 | 2014-12-19 | 15 | 2014-12-19 | 2014-11-26 | 2014-12-19 | 15 | [5 empty] | 4000 | 4344.04 |  |  |  |  | 2015-12-14 | 2015-12-18 |  | Y
Central Hudson |  | Solar Generation | CH-08108 | Kingston | Hurley | Ulster | 12443 | G | 2094 | Hurley Ave | N |  | 11 | [13 empty] | NM | N | SMA SB 11000-TL | 2014-10-27 | 2014-11-03 | 5 | 2014-11-03 | [14 empty] | 2015-07-02 | 2015-07-02 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03835 | Newburgh | New Paltz |  | 12561 | G | 5031 | Galeville | TBD |  | 6 | [13 empty] | NM | N | POWER ONE AURORA PVI-6000 (1) | 2014-10-28 | 2014-11-04 | 5 | 2014-11-04 | [17 empty] | W
Central Hudson |  | NRG Home Solar | CH-04188 | Newburgh | Marlboro | Ulster | 12542 | G | 5001 | Marlboro | N |  | 8.815 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (41) | 2014-10-28 | 2014-11-04 | 5 | 2014-11-04 | [14 empty] | 2015-05-29 | 2015-06-04 |  | Y
Central Hudson |  | NRG Home Solar | CH-04553 | Poughkeepsie | Poughkeepsie |  | 12601 | G | 6068 | Inwood Ave | TBD |  | 4.3 | [13 empty] | NM | N | 20 - ENPHASE ENERGY M-215 | 2014-10-28 | 2014-11-04 | 5 | 2014-11-04 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | NRG Home Solar | CH-04657 | Newburgh | Marlboro | Ulster | 12542 | G | 5003 | Marlboro | N |  | 8.815 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (41) | 2014-10-28 | 2014-11-04 | 5 | 2014-11-04 | [14 empty] | 2015-01-28 | 2015-02-04 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00987 | Kingston | Saugerties | Ulster | 12477 | G | 3004 | Saugerties | N |  | 7.74 | [13 empty] | NM | N | (36) ENPHASE 215 60-2LL-S22 | 2014-10-28 | 2014-11-04 | 5 | 2014-11-04 | [14 empty] | 2015-01-19 | 2015-01-26 |  | Y
Central Hudson |  | Novel Approaches | CH-02793 | Kingston | Grahamsvl | Sullivan | 12740 | G | 3091 | Neversink | N | CH-02791 | 7 | [13 empty] | NM | N | (1) SOLAREDGE SE11400 US (1) SOLAREDGE SE7600 US | 2014-10-28 | 2014-11-04 | 5 | 2014-11-04 | [8 empty] | 350 | 350 |  |  |  |  | 2015-02-25 | 2015-02-26 |  | Y
Central Hudson |  | SolarCity | CH-05860 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 7011 | Hibernia | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A | 2014-10-28 | 2014-11-04 | 5 | 2014-11-04 | [14 empty] | 2014-11-05 | 2014-11-12 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Solar Generation | CH-08107 | Newburgh | Wallkill | Ulster | 12589 | G | 5043 | East Walden | N |  | 7.6 | [13 empty] | NM | N | SMA SB 3800 (2) | 2014-10-28 | 2014-11-04 | 5 | 2014-11-04 | [14 empty] | 2014-12-23 | 2014-12-31 |  | Y
Central Hudson |  | Solar Generation | CH-08218 | Kingston | W Hurley | Ulster | 12491 | G | 3013 | Woodstock | N |  | 6 | [13 empty] | NM | N | SMA SB6000 TL | 2014-10-28 | 2014-11-03 | 4 | 2014-11-03 | [14 empty] | 2015-01-30 | 2015-02-06 |  | Y
Central Hudson |  | Sol Providers | CH-08964 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8045 | Myers Corners | N |  | 10 | [13 empty] | NM | N | SMA 5000TL (2) | 2014-10-28 | 2014-11-04 | 5 | 2014-11-04 | [14 empty] | 2014-12-30 | 2014-12-30 |  | W
Central Hudson |  | Sungevity Inc | CH-09227 | Newburgh | Walden | Orange | 12586 | G | 5041 | East Walden | N |  | 6 | [13 empty] | NM | N | ABB PVI-3.0 (2) | 2014-10-28 | 2014-11-04 | 5 | 2014-11-04 | [14 empty] | 2015-01-23 | 2015-01-30 |  | Y
Central Hudson |  | Sungevity Inc | CH-09420 | Kingston | Kingston | Ulster | 12401 | G | 1021 | East Kingston | N |  | 6 | [13 empty] | NM | N | SMA AMERICA SB6000TL-US-22 | 2014-10-28 | 2014-11-03 | 4 | 2014-11-03 | [14 empty] | 2014-12-15 | 2014-12-22 |  | Y
Central Hudson |  | Sungevity Inc | CH-09527 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6046 | Spackenkill | N |  | 8 | [13 empty] | NM | N | SMA SB8000US | 2014-10-28 | 2014-11-04 | 5 | 2014-11-04 | [14 empty] | 2015-01-09 | 2015-01-23 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-03495 | Newburgh | Pine Bush | Orange | 12566 | G | 5033 | Galeville | N |  | 13 | [13 empty] | NM | N | SMA AMERICA SB7000-US (1) SMA AMERICA SB6000TL-US (1) | 2014-10-29 | 2014-11-04 | 4 | 2014-11-04 | [14 empty] | 2015-02-19 | 2015-02-26 |  | Y
Central Hudson |  | NRG Home Solar | CH-04304 | Fishkill | Poughkeepsie | Dutchess | 12603 | G | 8022 | Knapps Corners | N |  | 4.945 | [13 empty] | NM | N | 23 - ENPHASE ENERGY M-215 | 2014-10-29 | 2014-11-05 | 5 | 2014-11-05 | [14 empty] | 2015-10-12 | 2015-10-19 |  | Y
Central Hudson |  | NRG Home Solar | CH-04309 | Poughkeepsie | Poughkeepsie |  | 12603 | G | 6043 | Spackenkill | TBD |  | 6.88 | [13 empty] | NM | N | 32 - ENPHASE ENERGY M-215 | 2014-10-29 | 2014-11-05 | 5 | 2014-11-05 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | NRG Home Solar | CH-04332 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6056 | Todd Hill | N |  | 8.815 | [13 empty] | NM | N | 41 - ENPHASE ENERGY M-215 | 2014-10-29 | 2014-11-05 | 5 | 2014-11-05 | [14 empty] | 2015-01-21 | 2015-01-28 |  | Y
Central Hudson |  | NRG Home Solar | CH-04379 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8043 | Myers Corners | N |  | 5.375 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (25) | 2014-10-29 | 2014-11-04 | 4 | 2014-11-04 | [14 empty] | 2015-01-28 | 2015-02-04 |  | Y
Central Hudson |  | NRG Home Solar | CH-04472 | Newburgh | Newburgh | Orange | 12550 | G | 4011 | West Balmville | N |  | 8.815 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (41) | 2014-10-29 | 2014-11-04 | 4 | 2014-11-04 | [14 empty] | 2015-10-29 | 2015-10-30 |  | Y
Central Hudson |  | NRG Home Solar | CH-04495 | Newburgh | Salisbury Mls | Orange | 12577 | G | 4095 | Bethlehem Rd | N |  | 6.88 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (32) | 2014-10-29 | 2014-11-04 | 4 | 2014-11-04 | [14 empty] | 2015-02-11 | 2015-02-19 |  | Y
Central Hudson |  | NRG Home Solar | CH-04502 | Newburgh | Rock Tvrn |  | 12575 | G | 4097 | Bethlehem Rd | TBD |  | 8.815 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (41) | 2014-10-29 | 2014-11-04 | 4 | 2014-11-04 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | NRG Home Solar | CH-04546 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6011 | Sand Dock | N |  | 5.375 | [13 empty] | NM | N | 25 - ENPHASE ENERGY M-215 | 2014-10-29 | 2014-11-05 | 5 | 2014-11-05 | [14 empty] | 2015-10-09 | 2015-10-16 |  | Y
Central Hudson |  | NRG Home Solar | CH-04642 | Newburgh | New Windsor | Orange | 12553 | G | 4044 | Union Ave | N |  | 3.87 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (18) | 2014-10-29 | 2014-11-04 | 4 | 2014-11-04 | [14 empty] | 2015-03-23 | 2015-03-30 |  | Y
Central Hudson |  | NRG Home Solar | CH-04733 | Fishkill | Beacon | Dutchess | 12508 | G | 8015 | Forgebrook | N |  | 3.225 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (15) | 2014-10-29 | 2014-11-04 | 4 | 2014-11-04 | [14 empty] | 2015-01-28 | 2015-02-04 |  | Y
Central Hudson |  | NRG Home Solar | CH-04759 | Poughkeepsie | Poughkeepsie |  | 12603 | G | 6042 | Spackenkill | TBD |  | 3.87 | [13 empty] | NM | N | 18 - ENPHASE ENERGY M-215 | 2014-10-29 | 2014-11-05 | 5 | 2014-11-05 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | NRG Home Solar | CH-04820 | Poughkeepsie | Pine Plns |  | 12567 | G | 7091 | Pulvers Corners | TBD |  | 5.375 | [13 empty] | NM | N | 25 - ENPHASE ENERGY M-215 | 2014-10-29 | 2014-11-05 | 5 | 2014-11-05 | [17 empty] | W
Central Hudson |  | Direct Energy Solar | CH-00922 | Kingston | Saugerties | Ulster | 12477 | G | 3001 | Saugerties | N |  | 5.81 | [13 empty] | NM | N | (27) ENPHASE M215 2LL-S22 | 2014-10-29 | 2014-11-04 | 4 | 2014-11-04 | [14 empty] | 2015-01-22 | 2015-01-29 |  | Y
Central Hudson |  | Hudson Solar | CH-01570 | Newburgh | Montgomery | Orange | 12549 | G | 5054 | Maybrook | N | CH-01570 | 9 | [13 empty] | NM | N | SMA AMERICA SB9000 (1) | 2014-10-29 | 2014-11-04 | 4 | 2014-11-04 | [14 empty] | 2014-12-30 | 2014-12-31 |  | Y
Central Hudson |  | Hudson Solar | CH-02107 | Poughkeepsie | Wappingrs Fls | Dutchess | 12590 | G | 6052 | Todd Hill | N |  | 7 | [13 empty] | NM | N | SMA AMERICA SB7000 | 2014-10-29 | 2014-11-05 | 5 | 2014-11-05 | [14 empty] | 2015-01-26 | 2015-02-02 |  | Y
Central Hudson |  | Hudson Solar | CH-02117 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7052 | Rhinebeck | N |  | 4 | [13 empty] | NM | N | SMA AMERICA SB4000 | 2014-10-29 | 2014-11-05 | 5 | 2014-11-05 | [14 empty] | 2015-03-17 | 2015-03-23 |  | Y
Central Hudson |  | Hudson Solar | CH-02128 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7054 | Rhinebeck | N |  | 7 | [13 empty] | NM | N | SMA AMERICA SB7000 | 2014-10-29 | 2014-11-05 | 5 | 2014-11-05 | [14 empty] | 2015-02-06 | 2015-02-13 |  | Y
Central Hudson |  | SolarCity | CH-05248 | Kingston | Saugerties | Ulster | 12477 | G | 3014 | Woodstock | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE 7600A-US-ZB-U | 2014-10-29 | 2014-11-04 | 4 | 2014-11-04 | [14 empty] | 2014-12-22 | 2014-12-30 |  | Y
Central Hudson |  | SolarCity | CH-05270 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8095 | Fishkill Plains | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A-US (1) | 2014-10-29 | 2014-11-04 | 4 | 2014-11-04 | [14 empty] | 2014-12-26 | 2014-12-31 |  | Y
Central Hudson |  | SolarCity | CH-05341 | Newburgh | Newburgh | Orange | 12550 | G | 4023 | Coldenham | N |  | 8 | [13 empty] | NM | N | SOLAREDGE SE5000A-US (1) SOLAREDGE SE3000A-US (1) | 2014-10-29 | 2014-11-04 | 4 | 2014-11-04 | [14 empty] | 2015-02-13 | 2015-02-23 |  | Y
Central Hudson |  | SolarCity | CH-05456 | Newburgh | Wallkill | Ulster | 12589 | G | 4011 | West Balmville | N |  | 8.8 | [13 empty] | NM | N | SOLAREDGE SE3800A (1) SOLAREDGE SE5000A (1) | 2014-10-29 | 2014-11-04 | 4 | 2014-11-04 | [14 empty] | 2014-11-05 | 2014-11-10 |  | Y
Central Hudson |  | SolarCity | CH-05487 | Catskill | Palenvl | Greene | 12463 | G | 2001 | North Catskill | N |  | 3 | [13 empty] | NM | N | ABB(POWER-ONE)PVI-3.0-OUTD-S US-Z-A | 2014-10-29 | 2014-11-05 | 5 | 2014-11-05 | [14 empty] | 2014-12-19 | 2014-12-30 |  | Y
Central Hudson |  | SolarCity | CH-05623 | Kingston | Rifton | Ulster | 12471 | G | 3041 | Sturgeon Pool | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000-OUTD US-Z-A | 2014-10-29 | 2014-11-05 | 5 | 2014-11-05 | [14 empty] | 2015-01-09 | 2015-01-16 |  | Y
Central Hudson |  | SolarCity | CH-06478 | Catskill | Ravena | Albany | 12143 | G | 1081 | New Baltimore | N |  | 7.5 | [13 empty] | NM | N | Fronius IG Plus A 7.5 | 2014-10-29 | 2014-11-04 | 4 | 2014-11-04 | [14 empty] | 2015-01-29 | 2015-01-30 |  | Y
Central Hudson |  | SolarCity | CH-06558 | Kingston | Cragsmoor | Ulster | 12420 | G | 3078 | Greenfield Rd | N |  | 3 | [13 empty] | NM | N | SOLAREDGE SE3000A-US ZB-U | 2014-10-29 | 2014-11-05 | 5 | 2014-11-05 | [14 empty] | 2015-01-02 | 2015-01-09 |  | Y
Central Hudson |  | SolarCity | CH-06672 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7053 | Rhinebeck | N | CH-06672 | 4.2 | [13 empty] | NM | N | ABB PVI-4.2 | 2014-11-06 | 2014-11-07 | 1 | 2014-11-07 | [14 empty] | 2014-12-18 | 2014-12-23 |  | Y
Central Hudson |  | SolarCity | CH-06896 | Fishkill | Beacon | Dutchess | 12508 | G | 8013 | Forgebrook | N |  | 3.8 | [13 empty] | NM | N | SOLAREDGE SE3800A-US (1) | 2014-10-29 | 2014-11-04 | 4 | 2014-11-04 | [14 empty] | 2015-01-13 | 2015-01-20 |  | Y
Central Hudson |  | SolarCity | CH-07197 | Catskill | Ravena | Albany | 12143 | G | 1081 | New Baltimore | N |  | 13.6 | [13 empty] | NM | N | (2) SOLAREDGE SE3800A US-ZB-U SOLAREDGE SE6000A US-ZB-U | 2014-10-29 | 2014-11-05 | 5 | 2014-11-05 | [8 empty] | 350 | 350 |  |  |  |  | 2015-01-16 | 2015-02-03 |  | Y
Central Hudson |  | SolarCity | CH-07522 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6044 | Spackenkill | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A | 2014-10-29 | 2014-11-05 | 5 | 2014-11-05 | [14 empty] | 2015-01-05 | 2015-01-12 |  | Y
Central Hudson |  | SolarCity | CH-07631 | Kingston | Kingston | Ulster | 12401 | G | 3021 | High Falls | N |  | 3 | [13 empty] | NM | N | ABB PVI 3.0 - OUTD-S-US-Z-A | 2014-10-29 | 2014-11-04 | 4 | 2014-11-04 | [14 empty] | 2015-01-05 | 2015-01-12 |  | Y
Central Hudson |  | Verengo Solar | CH-09756 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8043 | Myers Corners | N |  | 5.59 | [13 empty] | NM | N | ENPHASE ENERGY M215 (26) | 2014-10-29 | 2014-11-04 | 4 | 2014-11-04 | [14 empty] | 2015-04-13 | 2015-04-20 |  | Y
Central Hudson |  | New York State Solar Farm | CH-04067 | Newburgh | Newburgh | Orange | 12550 | G | 4013 | West Balmville | N |  | 12 | [13 empty] | NM | N | POWERONE PVI 6.0 (2) | 2014-10-30 | 2014-11-06 | 5 | 2014-11-06 | [14 empty] | 2014-12-04 | 2014-12-11 |  | Y
Central Hudson |  | NRG Home Solar | CH-04400 | Fishkill | Wappingers Falls | Dutchess | 12590 | G | 8092 | Fishkill Plains | N |  | 7.095 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (33) | 2014-10-30 | 2014-11-06 | 5 | 2014-11-06 | [14 empty] | 2015-02-24 | 2015-03-03 |  | Y
Central Hudson |  | NRG Home Solar | CH-04665 | Newburgh | Wallkill | Ulster | 12589 | G | 5043 | East Walden | N |  | 2.795 | [13 empty] | NM | N | 13 - ENPHASE ENERGY M-215 | 2014-10-31 | 2014-10-31 | 0 | 2014-10-31 | [14 empty] | 2014-12-03 | 2014-12-09 |  | Y
Central Hudson |  | NRG Home Solar | CH-04782 | Newburgh | Maybrook | Orange | 12543 | G | 4026 | Coldenham | N |  | 4.085 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (19) | 2014-10-30 | 2014-11-06 | 5 | 2014-11-06 | [14 empty] | 2015-03-23 | 2015-03-30 |  | Y
Central Hudson |  | NRG Home Solar | CH-04812 | Poughkeepsie | Poughkeepsie |  | 12603 | G | 6096 | Manchester | N |  | 4.73 | [13 empty] | NM | N | 22 - ENPHASE ENERGY M-215 | 2014-10-30 | 2014-11-06 | 5 | 2014-11-06 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | Direct Energy Solar | CH-00969 | Newburgh | Wallkill | Ulster | 12589 | G | 5043 | East Walden | N | CH-00969 | 6.02 | [13 empty] | NM | N | ENPHASE 215 (28) | 2014-10-30 | 2014-11-06 | 5 | 2014-11-06 | [14 empty] | 2015-01-20 | 2015-01-26 |  | Y
Central Hudson |  | SolarCity | CH-05125 | Kingston | Kingston | Ulster | 12401 | G | 2017 | Lincoln Park | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A US-ZB-U | 2014-10-30 | 2014-11-06 | 5 | 2014-11-06 | [14 empty] | 2014-11-26 | 2014-12-03 |  | Y
Central Hudson |  | SolarCity | CH-05804 | Poughkeepsie | Poughkeepsie |  | 12603 | G | 6042 | Spackenkill | TBD |  | 4.2 | [13 empty] | NM | N | ABB (POWER-ONE) PVI-4.2 | 2014-10-30 | 2014-11-06 | 5 | 2014-11-06 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | SolarCity | CH-06044 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8043 | Myers Corners | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000 (1) | 2014-10-30 | 2014-11-06 | 5 | 2014-11-06 | [14 empty] | 2015-01-29 | 2015-02-05 |  | Y
Central Hudson |  | SolarCity | CH-06137 | Fishkill | Beacon | Dutchess | 12508 | G | 8017 | Forgebrook | N |  | 6 | [13 empty] | NM | N | ABB PVI- 6000-TL (1) | 2014-10-30 | 2014-11-05 | 4 | 2014-11-05 | [14 empty] | 2015-02-02 | 2015-02-09 |  | Y
Central Hudson |  | SolarCity | CH-06228 | Newburgh | Newburgh | Orange | 12550 | G | 4023 | Coldenham | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A (1) | 2014-10-30 | 2014-11-06 | 5 | 2014-11-06 | [14 empty] | 2014-11-19 | 2014-11-20 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06495 | Kingston | Hurley | Ulster | 12443 | G | 2093 | Hurley Ave | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A US-ZB-U | 2014-10-30 | 2014-11-06 | 5 | 2014-11-06 | [14 empty] | 2015-07-31 | 2015-08-07 |  | Y
Central Hudson |  | SolarCity | CH-06540 | Kingston | Kingston | Ulster | 12401 | G | 1011 | Boulevard | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A-US ZB-U | 2014-10-30 | 2014-11-06 | 5 | 2014-11-06 | [14 empty] | 2014-12-15 | 2014-12-22 |  | Y
Central Hudson |  | SolarCity | CH-06982 | Newburgh | Wallkill | Ulster | 12589 | G | 5041 | East Walden | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000-TL (1) | 2014-10-30 | 2014-11-05 | 4 | 2014-11-05 | [14 empty] | 2015-03-26 | 2015-04-02 |  | Y
Central Hudson |  | SolarCity | CH-07108 | Newburgh | Cornwall | Orange | 12518 | G | 4093 | Bethlehem Rd | N |  | 11 | [13 empty] | NM | N | ABB PVI-6000 (1) ABB PVI-5000 (1) | 2014-10-30 | 2014-11-05 | 4 | 2014-11-05 | [14 empty] | 2015-01-02 | 2015-01-07 |  | Y
Central Hudson |  | SolarCity | CH-07333 | Newburgh | Highland | Ulster | 12528 | G | 5082 | Highland | N |  | 6 | [13 empty] | NM | N | ABB (POWER-ONE) PVI-6000 | 2014-10-30 | 2014-11-06 | 5 | 2014-11-06 | [14 empty] | 2015-01-05 | 2015-01-12 |  | Y
Central Hudson |  | SolarCity | CH-07608 | Newburgh | Gardiner | Ulster | 12525 | G | 5034 | Galeville | N |  | 9.2 | [13 empty] | NM | N | ABB PVI-4.2 (1) ABB PVI-5000 (1) | 2014-10-30 | 2014-11-05 | 4 | 2014-11-05 | [14 empty] | 2015-01-05 | 2015-01-12 |  | Y
Central Hudson |  | SolarCity | CH-07629 | Newburgh | Esopus | Ulster | 12429 | G | 5084 | Highland | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A US-ZB-U | 2014-10-30 | 2014-11-06 | 5 | 2014-11-06 | [14 empty] | 2015-01-05 | 2015-01-12 |  | Y
Central Hudson |  | Verengo Solar | CH-09758 | Fishkill | Hopewell Jct |  | 12533 | G | 8095 | Fishkill Plains | TBD |  | 15.695 | [13 empty] | NM | N | ENPHASE ENERGY M215 (73) | 2014-10-30 | 2014-11-06 | 5 | 2014-11-06 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | Verengo Solar | CH-09781 | Newburgh | Highland | Ulster | 12528 | G | 5081 | Highland | N |  | 6.665 | [13 empty] | NM | N | 31 - ENPHASE ENERGY M215 | 2014-10-30 | 2014-11-06 | 5 | 2014-11-06 | [14 empty] | 2015-01-26 | 2015-02-02 |  | Y
Central Hudson |  | Verengo Solar | CH-09815 | Fishkill | Beacon | Dutchess | 12508 | G | 8017 | Forgebrook | N |  | 3.87 | [13 empty] | NM | N | ENPHASE ENERGY M215 (18) | 2014-10-30 | 2014-11-06 | 5 | 2014-11-06 | [14 empty] | 2014-12-29 | 2014-12-31 |  | Y
Central Hudson |  | Verengo Solar | CH-09863 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8095 | Fishkill Plains | N |  | 17.2 | [13 empty] | NM | N | ENPHASE ENERGY M215 (80) | 2014-10-30 | 2014-11-06 | 5 | 2014-11-06 | [8 empty] | 350 | 350 |  |  |  |  | 2015-04-13 | 2015-04-20 |  | Y
Central Hudson |  | Verengo Solar | CH-09869 | Newburgh | New Paltz | Ulster | 12561 | G | 5024 | Ohioville | N |  | 5.16 | [13 empty] | NM | N | ENPHASE ENERGY M215 (24) | 2014-10-30 | 2014-11-06 | 5 | 2014-11-06 | [14 empty] | 2015-03-18 | 2015-03-25 |  | Y
Central Hudson |  | Verengo Solar | CH-09874 | Newburgh | Newburgh | Orange | 12550 | G | 4014 | West Balmville | N |  | 6.665 | [13 empty] | NM | N | ENPHASE ENERGY M215 (31) | 2014-10-30 | 2014-11-06 | 5 | 2014-11-06 | [14 empty] | 2015-04-23 | 2015-04-30 |  | Y
Central Hudson |  | SolarCity | CH-05563 | Catskill | Greenvl | Greene | 12083 | G | 2061 | Freehold | N | CH-05563 | 3.8 | [13 empty] | NM | N | SOLAREDGE SE3800A US-ZB-U | 2014-10-31 | 2014-11-07 | 5 | 2014-11-07 | [14 empty] | 2014-12-12 | 2014-12-19 |  | Y
Central Hudson |  | SolarCity | CH-05684 | Kingston | W Shokan | Ulster | 12494 | G | 3011 | Woodstock | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000 OUTD-US | 2014-10-31 | 2014-11-07 | 5 | 2014-11-07 | [14 empty] | 2015-01-26 | 2015-02-02 |  | Y
Central Hudson |  | SolarCity | CH-05810 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6046 | Spackenkill | N |  | 9 | [13 empty] | NM | N | 1 - SOLAREDGE SE6000A 1 - SOLAREDGE SE3000A | 2014-11-10 | 2014-11-17 | 5 | 2014-11-17 | [14 empty] | 2015-01-22 | 2015-01-29 |  | Y
Central Hudson |  | SolarCity | CH-05924 | Poughkeepsie | Wappingrs Fls | Dutchess | 12590 | G | 6052 | Todd Hill | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE600A | 2014-10-31 | 2014-11-07 | 5 | 2014-11-07 | [14 empty] | 2015-02-09 | 2015-02-13 |  | Y
Central Hudson |  | SolarCity | CH-05967 | Poughkeepsie | Pine Plns | Dutchess | 12567 | G | 7091 | Pulvers Corners | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A | 2014-10-31 | 2014-11-07 | 5 | 2014-11-07 | [14 empty] | 2015-03-20 | 2015-03-26 |  | Y
Central Hudson |  | SolarCity | CH-06226 | Newburgh | Newburgh | Orange | 12550 | G | 4023 | Coldenham | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A-US (1) | 2014-10-31 | 2014-10-31 | 0 | 2014-10-31 | [14 empty] | 2014-12-04 | 2014-12-05 |  | Y
Central Hudson |  | SolarCity | CH-07164 | Newburgh | New Windsor | Orange | 12553 | G | 4095 | Bethlehem Rd | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE3800A (2) | 2014-10-31 | 2014-11-06 | 4 | 2014-11-06 | [14 empty] | 2015-08-26 | 2015-09-02 |  | Y
Central Hudson |  | SolarCity | CH-07537 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7052 | Rhinebeck | N |  | 10 | [13 empty] | NM | N | 2 - SOLAREDGE SE5000A | 2014-10-31 | 2014-11-07 | 5 | 2014-11-07 | [14 empty] | 2015-05-26 | 2015-06-02 |  | Y
Central Hudson |  | Sungevity Inc | CH-09173 | Newburgh | Highland | Ulster | 12528 | G | 5082 | Highland | N |  | 12 | [13 empty] | NM | N | 2 - SMA AMERICA SB6000TL-US | 2014-10-31 | 2014-11-07 | 5 | 2014-11-07 | [14 empty] | 2015-01-14 | 2015-01-21 |  | Y
Central Hudson |  | Sungevity Inc | CH-09508 | Newburgh | Campbell Hall | Orange | 10916 | G | 5051 | Maybrook | N |  | 3 | [13 empty] | NM | N | ABB PVI-3.0 (1) | 2014-10-31 | 2014-11-06 | 4 | 2014-11-06 | [14 empty] | 2015-01-21 | 2015-01-28 |  | Y
Central Hudson |  | RGS Energy | CH-03001 | Catskill | Cairo | Greene | 12451 | G | 2071 | Freehold | N |  | 10.5 | [13 empty] | NM | N | (42) ENPHASE M250-60-2LL-S22 | 2014-11-03 | 2014-11-10 | 5 | 2014-11-10 | [14 empty] | 2015-01-09 | 2015-01-16 |  | Y
Central Hudson |  | NRG Home Solar | CH-04459 | Newburgh | Newburgh | Orange | 12550 | G | 4047 | Union Ave | N |  | 3.225 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (15) | 2014-11-03 | 2014-11-10 | 5 | 2014-11-10 | [14 empty] | 2015-01-21 | 2015-01-28 |  | Y
Central Hudson |  | SolarCity | CH-05088 | Newburgh | Campbell Hall | Orange | 10916 | G | 5052 | Maybrook | N |  | 3 | [13 empty] | NM | N | ABB PVI-3.0 (1) | 2014-11-03 | 2014-11-10 | 5 | 2014-11-10 | [14 empty] | 2015-01-05 | 2015-01-13 |  | Y
Central Hudson |  | SolarCity | CH-05533 | Catskill | Catskill | Greene | 12414 | G | 2001 | North Catskill | N |  | 3.6 | [13 empty] | NM | N | ABB PVI-3.6-OUTD-S US-Z-A | 2014-11-03 | 2014-11-10 | 5 | 2014-11-10 | [14 empty] | 2015-02-02 | 2015-02-09 |  | Y
Central Hudson |  | SolarCity | CH-05575 | Catskill | Coxsackie | Greene | 12051 | G | 1076 | Coxsackie | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A US-ZB-U | 2014-11-03 | 2014-11-10 | 5 | 2014-11-10 | [14 empty] | 2014-12-19 | 2014-12-30 |  | Y
Central Hudson |  | SolarCity | CH-05832 | Poughkeepsie | Poughkeepsie |  | 12601 | G | 6063 | Inwood Ave | TBD |  | 4.2 | [13 empty] | NM | N | ABB (POWER-ONE) PVI-4.2 | 2014-11-03 | 2014-11-17 | 10 | 2014-11-17 | [17 empty] | W
Central Hudson |  | SolarCity | CH-06073 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8092 | Fishkill Plains | N |  | 5 | [13 empty] | NM | N | ABB PVI-5000 (1) | 2014-11-03 | 2014-11-10 | 5 | 2014-11-10 | [14 empty] | 2015-02-10 | 2015-02-18 |  | Y
Central Hudson |  | SolarCity | CH-06327 | Newburgh | Marlboro | Ulster | 12542 | G | 5001 | Marlboro | N |  | 3.6 | [13 empty] | NM | N | ABB PVI-3.6 (1) | 2014-11-03 | 2014-11-10 | 5 | 2014-11-10 | [14 empty] | 2015-03-17 | 2015-03-24 |  | Y
Central Hudson |  | SolarCity | CH-06798 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8091 | Fishkill Plains | N |  | 9 | [13 empty] | NM | N | (1) ABB PVI-3.0 & (1) ABB PVI-6000 | 2014-11-03 | 2014-11-10 | 5 | 2014-11-10 | [14 empty] | 2015-05-04 | 2015-05-11 |  | Y
Central Hudson |  | SolarCity | CH-07281 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7053 | Rhinebeck | N | CH-06672 | 3 | [13 empty] | NM | N | ABB (POWER-ONE) PVI-3.0 | 2014-11-03 | 2014-11-07 | 4 | 2014-11-07 | [14 empty] | 2014-12-19 | 2014-12-29 |  | Y
Central Hudson |  | SolarCity | CH-07642 | Kingston | Lk Katrine | Ulster | 12449 | G | 2016 | Lincoln Park | N |  | 6.8 | [13 empty] | NM | N | (1) SOLAREDGE SE3800A US-ZB-U (1) SOLAREDGE SE3000A US-ZB-U | 2014-11-03 | 2014-11-10 | 5 | 2014-11-10 | [14 empty] | 2014-11-18 | 2014-11-25 |  | Y
Central Hudson |  | SolarCity | CH-07847 | Catskill | Ravena |  | 12143 | G | 1082 | New Baltimore | TBD |  | 11 | [13 empty] | NM | N | (1)ABB PVI-6000-OUTD US-Z-A (1)ABB PVI-5000-OUTD US-Z-A | 2014-11-03 | 2014-11-10 | 5 | 2014-11-10 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | Sungevity Inc | CH-09179 | Kingston | Ulster Pk | Ulster | 12487 | G | 3041 | Sturgeon Pool | N | CH-09179 | 7 | [13 empty] | NM | N | SMA AMERICA SB7000US-12 | 2014-11-03 | 2014-11-10 | 5 | 2014-11-10 | [14 empty] | 2014-12-19 | 2014-12-30 |  | Y
Central Hudson |  | US Energy Concierge, Inc. | CH-09742 | Poughkeepsie | Lagrangevl | Dutchess | 12540 | G | 6055 | Todd Hill | N |  | 15.2 | [13 empty] | NM | N | 2 - SOLECTRIA PVI 7.6 | 2014-11-10 | 2014-11-17 | 5 | 2014-11-17 | [14 empty] | 2014-12-31 | 2015-01-08 |  | Y
Central Hudson |  | RGS Energy | CH-03034 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6092 | Manchester | N |  | 10 | [13 empty] | NM | N | FRONIUS IG PLUS 10.0-1 UNI | 2014-11-11 | 2014-11-18 | 5 | 2014-11-18 | [14 empty] | 2015-06-25 | 2015-07-02 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-03453 | Fishkill | Poughkeepsie | Dutchess | 12603 | G | 8024 | Knapps Corners | N |  | 5 | [13 empty] | NM | N | FRONIUS IG PLUS A 5.0 (1) | 2014-11-04 | 2014-11-10 | 4 | 2014-11-10 | [14 empty] | 2015-03-18 | 2015-03-25 |  | Y
Central Hudson |  | SolarCity | CH-04983 | Catskill | Athens | Greene | 12015 | G | 1074 | Coxsackie | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A US-ZB-U | 2014-11-04 | 2014-11-10 | 4 | 2014-11-10 | [14 empty] | 2014-12-19 | 2014-12-30 |  | Y
Central Hudson |  | SolarCity | CH-05394 | Newburgh | Newburgh | Orange | 12550 | G | 4011 | West Balmville | N |  | 3.6 | [13 empty] | NM | N | ABB PVI-3.6 (1) | 2014-11-04 | 2014-11-10 | 4 | 2014-11-10 | [14 empty] | 2015-07-09 | 2015-07-15 |  | Y
Central Hudson |  | SolarCity | CH-07042 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 3.8 | [13 empty] | NM | N | SOLAREDGE SE3800A | 2014-11-04 | 2014-11-10 | 4 | 2014-11-10 | [14 empty] | 2015-01-26 | 2015-02-09 |  | Y
Central Hudson |  | SolarCity | CH-07449 | Newburgh | Wallkill | Ulster | 12589 | G | 5041 | East Walden | N |  | 11.4 | [13 empty] | NM | N | FRONIUS IG PLUS 11.4 | 2014-11-04 | 2014-11-10 | 4 | 2014-11-10 | [14 empty] | 2015-01-05 | 2015-01-12 |  | Y
Central Hudson |  | SolarCity | CH-07727 | Newburgh | Campbell Hall | Orange | 10916 | G | 5051 | Maybrook | N |  | 9 | [13 empty] | NM | N | SOLAREDGE SE6000A (1) SOLAREDGE SE3000A (1) | 2014-11-04 | 2014-11-10 | 4 | 2014-11-10 | [14 empty] | 2014-12-30 | 2015-01-07 |  | Y
Central Hudson |  | Solar Generation | CH-08250 | Poughkeepsie | Staatsburg | Dutchess | 12580 | G | 7011 | Hibernia | N |  | 20 | [13 empty] | NM | N | 4 SMA America SB5000TL-US-22 (240V) 4 - SMA SB 5000TL | 2014-11-04 | 2014-11-18 | 10 | 2014-11-18 | [14 empty] | 2015-01-13 | 2015-01-19 |  | Y
Central Hudson |  | Sungevity Inc | CH-09401 | Kingston | W Hurley | Ulster | 12491 | G | 2094 | Hurley Ave | N |  | 5 | [13 empty] | NM | N | SMA AMERICA SB5000 TL-US-22 | 2014-11-04 | 2014-11-05 | 1 | 2014-11-05 | [14 empty] | 2015-01-27 | 2015-02-03 |  | Y
Central Hudson |  | Sungevity Inc | CH-09537 | Fishkill | Poughkeepsie | Dutchess | 12601 | G | 8021 | Knapps Corners | N |  | 6 | [13 empty] | NM | N | SMA AMERICA SB6000TL (1) | 2014-11-04 | 2014-11-10 | 4 | 2014-11-10 | [14 empty] | 2015-03-02 | 2015-03-09 |  | Y
Central Hudson |  | Sungevity Inc | CH-09554 | Newburgh | Gardiner | Ulster | 12525 | G | 5043 | East Walden | N | CH-09554 | 3.8 | [13 empty] | NM | N | SMA AMERICA SB3800TL (1) | 2014-11-04 | 2014-11-10 | 4 | 2014-11-10 | [14 empty] | 2014-12-04 | 2014-12-10 |  | Y
Central Hudson |  | Verengo Solar | CH-09755 | Newburgh | Newburgh | Orange | 12550 | G | 4024 | Coldenham | N |  | 2.795 | [13 empty] | NM | N | ENPHASE ENERGY M215 (13) | 2014-11-04 | 2014-11-10 | 4 | 2014-11-10 | [14 empty] | 2014-12-29 | 2014-12-31 |  | Y
Central Hudson |  | NRG Home Solar | CH-04120 | Poughkeepsie | Staatsburg |  | 12580 | G | 7042 | Staatsburg | TBD |  | 5.59 | [13 empty] | NM | N | 26 - ENPHASE ENERGY M-215 | 2014-11-05 | 2014-11-12 | 5 | 2014-11-12 | [17 empty] | W
Central Hudson |  | NRG Home Solar | CH-04415 | Fishkill | Beacon |  | 12508 | G | 8016 | Forgebrook | TBD |  | 5.805 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (27) | 2014-11-05 | 2014-11-11 | 4 | 2014-11-11 | [17 empty] | W
Central Hudson |  | NRG Home Solar | CH-04574 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7061 | Milan | N |  | 7.31 | [13 empty] | NM | N | 34 - ENPHASE ENERGY M-215 | 2014-11-05 | 2014-11-12 | 5 | 2014-11-12 | [14 empty] | 2015-01-28 | 2015-02-04 |  | Y
Central Hudson |  | NRG Home Solar | CH-04768 | Poughkeepsie | Pine Plns | Dutchess | 12567 | G | 7091 | Pulvers Corners | N |  | 6.88 | [13 empty] | NM | N | 32 - ENPHASE ENERGY M-215 | 2014-11-05 | 2014-11-12 | 5 | 2014-11-12 | [14 empty] | 2015-10-12 | 2015-10-19 |  | Y
Central Hudson |  | SolarCity | CH-05309 | Newburgh | Wallkill | Ulster | 12589 | G | 5043 | East Walden | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000 (1) | 2014-11-05 | 2014-11-11 | 4 | 2014-11-11 | [14 empty] | 2014-12-11 | 2014-12-17 |  | Y
Central Hudson |  | SolarCity | CH-05786 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6095 | Manchester | N |  | 6 | [13 empty] | NM | N | ABB (POWER-ONE) PVI-6000-OUTD | 2014-11-05 | 2014-11-12 | 5 | 2014-11-12 | [14 empty] | 2014-12-26 | 2014-12-31 |  | Y
Central Hudson |  | SolarCity | CH-06136 | Fishkill | Beacon | Dutchess | 12508 | G | 8013 | Forgebrook | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A (1) | 2014-11-05 | 2014-11-11 | 4 | 2014-11-11 | [14 empty] | 2014-12-30 | 2014-12-31 |  | Y
Central Hudson |  | SolarCity | CH-06393 | Newburgh | Cornwall | Orange | 12518 | G | 4041 | Union Ave | N |  | 5 | [13 empty] | NM | N | ABB PVI-5000 (1) | 2014-11-05 | 2014-11-12 | 5 | 2014-11-12 | [14 empty] | 2014-12-01 | 2014-12-08 |  | Y
Central Hudson |  | SolarCity | CH-07862 | Kingston | Willow |  | 12495 | G | 3012 | Woodstock | TBD |  | 3.6 | [13 empty] | NM | N | ABB PVI-3.6-OUTD-S-US | 2014-11-05 | 2014-11-12 | 5 | 2014-11-12 | [17 empty] | W |  | Customer already had net meter prior to application. 6/19/15 Customer says he is no longer going to do solar and does not want a net meter installed.
Central Hudson |  | Self | CH-08868 | Catskill | Leeds | Greene | 12451 | G | 2005 | North Catskill | N |  | 11 | [13 empty] | NM | N | SMA SB11000-TL-US | 2014-11-05 | 2014-11-11 | 4 | 2014-11-11 | [14 empty] | 2014-12-15 | 2014-12-15 |  | Y
Central Hudson |  | Sungevity Inc | CH-09263 | Catskill | Athens | Greene | 12015 | G | 2002 | North Catskill | N |  | 3 | [13 empty] | NM | N | SMA AMERICA SB3000TL-US-22 | 2014-11-05 | 2014-11-12 | 5 | 2014-11-12 | [14 empty] | 2015-01-19 | 2015-01-26 |  | Y
Central Hudson |  | Sungevity Inc | CH-09293 | Kingston | Kingston | Ulster | 12401 | G | 2091 | Hurley Ave | N |  | 12 | [13 empty] | NM | N | (2) SMA AMERICA SB6000TL-US-22 | 2014-11-05 | 2014-11-11 | 4 | 2014-11-11 | [14 empty] | 2014-12-15 | 2014-12-22 |  | Y
Central Hudson |  | Sungevity Inc | CH-09414 | Kingston | Kingston | Ulster | 12401 | G | 1022 | East Kingston | N |  | 3 | [13 empty] | NM | N | SMA AMERICA SB3000TL-US-22 | 2014-11-05 | 2014-11-12 | 5 | 2014-11-12 | [14 empty] | 2015-03-05 | 2015-03-11 |  | Y
Central Hudson |  | Sungevity Inc | CH-09612 | Poughkeepsie | Ancramdale | Columbia | 12503 | G | 7085 | Ancram | N | CH-09586 | 3 | [13 empty] | NM | N | SMA AMERICA SB3000TLUS-22 | 2014-11-20 | 2014-12-01 | 5 | 2014-12-01 | [14 empty] | 2015-01-29 | 2015-02-05 |  | Y
Central Hudson |  | Verengo Solar | CH-09864 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8094 | Fishkill Plains | N |  | 6.02 | [13 empty] | NM | N | ENPHASE ENERGY M215 (28) | 2014-11-05 | 2014-11-11 | 4 | 2014-11-11 | [14 empty] | 2015-04-13 | 2015-04-20 |  | Y
Central Hudson |  | NRG Home Solar | CH-04137 | Newburgh | New Windsor | Orange | 12553 | G | 4095 | Bethlehem Rd | N |  | 6.45 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (30) | 2014-11-06 | 2014-11-11 | 3 | 2014-11-11 | [14 empty] | 2015-03-02 | 2015-03-09 |  | Y
Central Hudson |  | NRG Home Solar | CH-04261 | Kingston | Hurley |  | 12443 | G | 2094 | Hurley Ave | TBD |  | 4.515 | [13 empty] | NM | N | 21 ENPHASE M-215-60-2LL-S22-IG | 2014-11-06 | 2014-11-13 | 5 | 2014-11-13 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | Hudson Solar | CH-01227 | Kingston | Saugerties | Ulster | 12477 | G | 3003 | Saugerties | N | CH-01227 | 72 | [13 empty] | RNM | N | 3 - SMA America STP 24000TL | 2014-11-21 | 2014-12-16 | 15 | 2014-12-16 | 2014-11-21 | 2014-12-16 | 15 | [11 empty] | 2015-06-01 | 2015-06-05 |  | Y
Central Hudson |  | Hudson Solar | CH-02515 | Kingston | Saugerties |  | 12477 | G | 3003 | Saugerties | TBD |  | 12 | [13 empty] | NM | N | SMA America STP 12000TL | 2014-12-16 | 2014-12-16 | 0 | 2014-12-16 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | Quad State Solar, Inc. | CH-02949 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8093 | Fishkill Plains | N |  | 8 | [13 empty] | NM | N | SMA SB400TL (2) | 2015-05-29 | 2015-06-09 | 7 | 2015-06-09 | [14 empty] | 2015-06-23 | 2015-07-02 |  | Y
Central Hudson |  | SolarCity | CH-05010 | Kingston | Ruby | Ulster | 12475 | G | 2016 | Lincoln Park | N | CH-05010 | 10 | [13 empty] | NM | N | 2 SOLAREDGE SE5000A US-ZB-U | 2014-11-06 | 2014-11-13 | 5 | 2014-11-13 | [8 empty] | 350 | 350 |  |  |  |  | 2015-02-09 | 2015-02-17 |  | Y
Central Hudson |  | SolarCity | CH-05489 | Catskill | Saugerties | Ulster | 12477 | G | 2001 | North Catskill | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE7600A US-ZB-U | 2014-11-06 | 2014-11-13 | 5 | 2014-11-13 | [14 empty] | 2015-01-06 | 2015-01-13 |  | Y
Central Hudson |  | SolarCity | CH-06442 | Catskill | Catskill | Greene | 12414 | G | 2042 | South Cairo | N |  | 12 | [13 empty] | NM | N | (2)ABB PVI-6000-OUTD US-Z-A | 2014-11-06 | 2014-11-13 | 5 | 2014-11-13 | [8 empty] | 350 | 350 |  |  |  |  | 2014-12-31 | 2015-02-03 |  | Y
Central Hudson |  | SolarCity | CH-07186 | Catskill | Catskill | Greene | 12414 | G | 2005 | North Catskill | N |  | 10 | [13 empty] | NM | N | 2 SOLAREDGE SE5000A US-ZB-U | 2014-11-06 | 2014-11-13 | 5 | 2014-11-13 | [14 empty] | 2015-02-23 | 2015-03-02 |  | W
Central Hudson |  | SolarCity | CH-07487 | Catskill | Catskill |  | 12414 | G | 2005 | North Catskill | TBD |  | 10 | [13 empty] | NM | N | 2 SOLAREDGE SE5000A US-ZB-U | 2014-11-06 | 2014-11-13 | 5 | 2014-11-13 | [14 empty] | 2015-02-22 | 2015-03-02 |  | W
Central Hudson |  | SolarCity | CH-07717 | Newburgh | Clintondale | Ulster | 12515 | G | 5024 | Ohioville | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A-US (1) | 2014-11-06 | 2014-11-11 | 3 | 2014-11-11 | [14 empty] | 2014-11-18 | 2014-11-19 |  | Y
Central Hudson |  | Solar Alchemy | CH-08981 | Kingston | Kerhonkson | Ulster | 12404 | G | 3082 | Kerhonkson | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE7600A-US | 2014-11-06 | 2014-11-13 | 5 | 2014-11-13 | [14 empty] | 2015-03-09 | 2015-03-16 |  | Y
Central Hudson |  | Sungevity Inc | CH-09261 | Catskill | Hannacroix | Greene | 12087 | G | 2061 | Freehold | N |  | 6 | [13 empty] | NM | N | ABB PVI6000 OU-TD | 2014-11-06 | 2014-11-13 | 5 | 2014-11-13 | [14 empty] | 2015-04-13 | 2015-04-20 |  | Y
Central Hudson |  | SolarCity | CH-05814 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6002 | Reynolds Hill | N |  | 8 | [13 empty] | NM | N | 1 - SOLAREDGE SE5000A 1 - SOLAREDGE SE3000A | 2014-11-07 | 2014-11-19 | 8 | 2014-11-19 | [14 empty] | 2015-04-22 | 2015-04-29 |  | Y
Central Hudson |  | SolarCity | CH-06039 | Fishkill | Poughkeepsie |  | 12601 | G | 8021 | Knapps Corners | TBD |  | 9.8 | [13 empty] | NM | N | SOLAREDGE SE6000A (1) SOLAREDGE SE3800A (1) | 2014-11-07 | 2014-11-11 | 2 | 2014-11-11 | [17 empty] | W
Central Hudson |  | SolarCity | CH-06915 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8093 | Fishkill Plains | N |  | 8.8 | [13 empty] | NM | N | SOLAREDGE SE3800A (1) SOLAREDGE SE5000A (1) | 2014-11-07 | 2014-11-11 | 2 | 2014-11-11 | [14 empty] | 2014-12-02 | 2015-02-24 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Sungevity Inc | CH-09289 | Kingston | West Shokan | Ulster | 12494 | G | 3011 | Woodstock | N |  | 8 | [13 empty] | NM | N | SMA AMERICA SB8000-US-12 | 2014-11-07 | 2014-11-14 | 5 | 2014-11-14 | [14 empty] | 2014-12-15 | 2014-12-22 |  | Y
Central Hudson |  | Verengo Solar | CH-09757 | Newburgh | Cornwall-Hdsn | Orange | 12520 | G | 4043 | Union Ave | N |  | 6.235 | [13 empty] | NM | N | ENPHASE ENERGY M215 (29) | 2014-11-07 | 2014-11-11 | 2 | 2014-11-11 | [14 empty] | 2015-05-01 | 2015-05-07 |  | Y
Central Hudson |  | Verengo Solar | CH-09800 | Poughkeepsie | Wingdale | Dutchess | 12594 | G | 6055 | Todd Hill | N |  | 8.6 | [13 empty] | NM | N | 40 - ENPHASE ENERGY M215 | 2014-11-07 | 2014-11-19 | 8 | 2014-11-19 | [14 empty] | 2015-06-09 | 2015-06-10 |  | Y
Central Hudson |  | Verengo Solar | CH-09811 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8054 | North Chelsea | N |  | 11.825 | [13 empty] | NM | N | ENPHASE ENERGY M215 (55) | 2014-11-07 | 2014-11-11 | 2 | 2014-11-11 | [14 empty] | 2015-01-16 | 2015-01-23 |  | Y
Central Hudson |  | Verengo Solar | CH-09818 | Newburgh | Newburgh | Orange | 12550 | G | 4024 | Coldenham | N |  | 5.16 | [13 empty] | NM | N | ENPHASE ENERGY M215 (24) | 2014-11-24 | 2014-11-25 | 1 | 2014-11-25 | [14 empty] | 2015-01-06 | 2015-01-13 |  | Y
Central Hudson |  | Verengo Solar | CH-09908 | Newburgh | Marlboro | Ulster | 12542 | G | 5001 | Marlboro | N |  | 4.515 | [13 empty] | NM | N | ENPHASE ENERGY M215 (21) | 2014-11-07 | 2014-11-11 | 2 | 2014-11-11 | [14 empty] | 2014-12-29 | 2015-01-06 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00866 | Kingston | Malden-Hdsn | Ulster | 12453 | G | 3004 | Saugerties | N |  | 7.74 | [13 empty] | NM | N | (36) ENPHASE M215 60-2LL-S22 | 2014-11-10 | 2014-11-17 | 5 | 2014-11-17 | [14 empty] | 2014-12-16 | 2014-12-23 |  | Y
Central Hudson |  | SolarCity | CH-05374 | Newburgh | New Paltz | Ulster | 12561 | G | 5023 | Ohioville | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000 (1) | 2014-11-12 | 2014-11-14 | 2 | 2014-11-14 | [14 empty] | 2015-02-09 | 2015-02-17 |  | Y
Central Hudson |  | SolarCity | CH-05417 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6002 | Reynolds Hill | N |  | 5 | [13 empty] | NM | N | ABB PVI 5000 | 2014-11-10 | 2014-11-17 | 5 | 2014-11-17 | [14 empty] | 2015-02-18 | 2015-02-23 |  | Y
Central Hudson |  | SolarCity | CH-05669 | Kingston | Port Ewen | Ulster | 12466 | G | 1012 | Boulevard | N |  | 3 | [13 empty] | NM | N | SOLAREDGE SE3000A US-ZB-U | 2014-11-10 | 2014-11-17 | 5 | 2014-11-17 | [14 empty] | 2015-01-02 | 2015-01-09 |  | Y
Central Hudson |  | SolarCity | CH-06291 | Newburgh | Highland | Ulster | 12528 | G | 5013 | Modena | N |  | 8 | [13 empty] | NM | N | SOLAR EDGE SE5000 (1) SOLAR EDGE SE3000 (1) | 2014-11-10 | 2014-11-20 | 8 | 2014-11-20 | [14 empty] | 2015-01-20 | 2015-01-26 |  | Y
Central Hudson |  | SolarCity | CH-06477 | Catskill | Ravena | Albany | 12143 | G | 1081 | New Baltimore | N |  | 4.2 | [13 empty] | NM | N | ABB PVI-4.2-OUTD-S-US-Z-A | 2014-11-10 | 2014-11-17 | 5 | 2014-11-17 | [14 empty] | 2015-01-14 | 2015-01-21 |  | Y
Central Hudson |  | SolarCity | CH-06751 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6092 | Manchester | N |  | 8.8 | [13 empty] | NM | N | 1 - SOLAREDGE SE3800A 1 - SOLAREDGE SE5000A | 2014-11-10 | 2014-11-17 | 5 | 2014-11-17 | [14 empty] | 2015-02-04 | 2015-02-11 |  | Y
Central Hudson |  | SolarCity | CH-06864 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8092 | Fishkill Plains | N |  | 9 | [13 empty] | NM | N | ABB PVI-6000 (1) ABB PVI-3.0 (1) | 2014-11-10 | 2014-11-14 | 4 | 2014-11-14 | [14 empty] | 2015-01-05 | 2015-01-13 |  | Y
Central Hudson |  | SolarCity | CH-07232 | Kingston | Saugerties | Ulster | 12477 | G | 3003 | Saugerties | N |  | 3.6 | [13 empty] | NM | N | ABB PVI-3.0-OUTD-S-US-Z-A | 2014-11-10 | 2014-11-17 | 5 | 2014-11-17 | [14 empty] | 2015-03-05 | 2015-03-06 |  | Y
Central Hudson |  | SolarCity | CH-07853 | Kingston | High Falls |  | 12440 | G | 3022 | High Falls | TBD |  | 6 | [13 empty] | NM | N | ABB PVI-6000-OUTD-US-Z-A | 2014-11-10 | 2014-11-17 | 5 | 2014-11-17 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | Verengo Solar | CH-09894 | Kingston | Kingston | Ulster | 12401 | G | 1022 | East Kingston | N |  | 6.45 | [13 empty] | NM | N | 30 ENPHASE M215-60-2LL-S22-IG | 2014-11-10 | 2014-11-17 | 5 | 2014-11-17 | [14 empty] | 2015-02-04 | 2015-02-11 |  | Y
Central Hudson |  | SolarCity | CH-05459 | Newburgh | New Windsor | Orange | 12553 | G | 4093 | Bethlehem Rd | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A (1) | 2014-11-11 | 2014-11-18 | 5 | 2014-11-18 | [14 empty] | 2014-12-31 | 2015-01-07 |  | Y
Central Hudson |  | SolarCity | CH-05562 | Catskill | Coeymans Hollow | Albany | 12046 | G | 1081 | New Baltimore | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A-US-ZB-U | 2014-11-11 | 2014-11-18 | 5 | 2014-11-18 | [14 empty] | 2015-02-02 | 2015-02-09 |  | Y
Central Hudson |  | SolarCity | CH-05763 | Kingston | Saugerties | Ulster | 12477 | G | 1021 | East Kingston | N |  | 7.2 | [13 empty] | NM | N | 2 ABB PVI-3.6-OUTD-S-US-Z-A | 2014-11-11 | 2014-11-18 | 5 | 2014-11-18 | [14 empty] | 2015-04-14 | 2015-04-21 |  | Y
Central Hudson |  | SolarCity | CH-05853 | Poughkeepsie | Staatsburg |  | 12580 | G | 7041 | Staatsburg | TBD |  | 3 | [13 empty] | NM | N | ABB PVI 3.0 | 2014-11-11 | 2014-11-18 | 5 | 2014-11-18 | [17 empty] | W
Central Hudson |  | SolarCity | CH-05941 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6093 | Manchester | N |  | 7.6 | [13 empty] | NM | N | SolarEdge SE7600A-US | 2014-11-11 | 2014-11-18 | 5 | 2014-11-18 | [14 empty] | 2015-05-05 | 2015-05-12 |  | Y
Central Hudson |  | SolarCity | CH-06369 | Newburgh | Wallkill | Ulster | 12589 | G | 5042 | East Walden | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE3800A (2) | 2014-11-11 | 2014-11-18 | 5 | 2014-11-18 | [14 empty] | 2015-02-02 | 2015-02-09 |  | Y
Central Hudson |  | SolarCity | CH-06386 | Newburgh | New Windsor | Orange | 12553 | G | 4095 | Bethlehem Rd | N |  | 8 | [13 empty] | NM | N | SOLAREDGE SE5000A (1) SOLAREDGE SE3000A (1) | 2014-11-11 | 2014-11-14 | 3 | 2014-11-14 | [14 empty] | 2014-12-01 | 2014-12-08 |  | Y
Central Hudson |  | SolarCity | CH-06631 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6003 | Reynolds Hill | N |  | 3.6 | [13 empty] | NM | N | ABB PVI 3.6 OUTD | 2014-11-11 | 2014-11-18 | 5 | 2014-11-18 | [14 empty] | 2015-09-17 | 2015-09-24 |  | Y
Central Hudson |  | SolarCity | CH-07030 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 3.6 | [13 empty] | NM | N | ABB PVI-3.6 (1) | 2014-11-11 | 2014-11-14 | 3 | 2014-11-14 | [14 empty] | 2014-12-29 | 2014-12-31 |  | Y
Central Hudson |  | SolarCity | CH-07330 | Newburgh | Highland | Ulster | 12528 | G | 5084 | Highland | N |  | 5 | [13 empty] | NM | N | SolarEdge SE5000A-US | 2014-11-11 | 2014-11-18 | 5 | 2014-11-18 | [14 empty] | 2014-12-26 | 2015-01-05 |  | Y
Central Hudson |  | SolarCity | CH-07414 | Newburgh | Highland |  | 12528 | G | 5081 | Highland | TBD |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE3800A (2) | 2014-11-11 | 2014-11-18 | 5 | 2014-11-18 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | SolarCity | CH-07501 | Kingston | Kingston | Ulster | 12401 | G | 1022 | East Kingston | N |  | 5 | [13 empty] | NM | N | ABB PVI-5000-OUTD-Z-A | 2014-11-11 | 2014-11-18 | 5 | 2014-11-18 | [14 empty] | 2015-06-01 | 2015-06-08 |  | Y
Central Hudson |  | SolarCity | CH-07565 | Fishkill | New Hamburg |  | 12590 | G | 8023 | Knapps Corners | TBD |  | 3 | [13 empty] | NM | N | ABB PVI 3.0 (1) | 2014-11-17 | 2014-11-18 | 1 | 2014-11-18 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | SolarCity | CH-07850 | Kingston | Ulster |  | 12487 | G | 1014 | Boulevard | TBD |  | 7.5 | [13 empty] | NM | N | FRONIUS IG PLUS A 7.5 | 2014-11-11 | 2014-11-18 | 5 | 2014-11-18 | [17 empty] | W
Central Hudson |  | SolarCity | CH-07866 | Kingston | Ellenville |  | 12428 | G | 3078 | Greenfield Rd | TBD |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A-US-ZB-U | 2014-11-11 | 2014-11-18 | 5 | 2014-11-18 | [15 empty] | 2015-02-05 |  | W |  | Customer already had net meter prior to application.
Central Hudson |  | SolarCity | CH-07867 | Kingston | Woodstock |  | 12498 | G | 3014 | Woodstock | TBD |  | 6 | [13 empty] | NM | N | ABB PVI-6000-OUTD-Z-A | 2014-11-11 | 2014-11-18 | 5 | 2014-11-18 | [17 empty] | W
Central Hudson |  | Sungevity Inc | CH-09237 | Newburgh | Rock Tvrn | Orange | 12575 | G | 4097 | Bethlehem Rd | N |  | 8 | [13 empty] | NM | N | SMA AMERICA SB4000TL-US (2) | 2014-11-11 | 2014-11-14 | 3 | 2014-11-14 | [14 empty] | 2015-05-08 | 2015-05-13 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-03416 | Newburgh | Newburgh | Orange | 12550 | G | 4013 | West Balmville | N |  | 5 | [13 empty] | NM | N | SMA AMERICA SB5000US (1) | 2014-11-12 | 2014-11-18 | 4 | 2014-11-18 | [14 empty] | 2015-03-31 | 2015-04-08 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-03484 | Fishkill | Glenham | Dutchess | 12527 | G | 8016 | Forgebrook | N |  | 5 | [13 empty] | NM | N | SMA AMERICA SB5000TL (1) | 2014-11-12 | 2014-11-18 | 4 | 2014-11-18 | [14 empty] | 2015-03-24 | 2015-03-31 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-03500 | Newburgh | New Windsor | Orange | 12553 | G | 4046 | Union Ave | N |  | 5 | [13 empty] | NM | N | SMA AMERICA SB5000US (1) | 2014-11-12 | 2014-11-18 | 4 | 2014-11-18 | [14 empty] | 2015-05-05 | 2015-05-11 |  | Y
Central Hudson |  | Novel Approaches | CH-02787 | Newburgh | Montgomery | Orange | 12549 | G | 5073 | Montgomery | N |  | 17.6 | [13 empty] | NM | N | SOLAR EDGE SE10000 (1) SOLAR EDGE SE7600 (1) | 2014-11-12 | 2014-11-18 | 4 | 2014-11-18 | [8 empty] | 350 | 350 |  |  |  |  | 2014-12-18 | 2014-12-19 |  | Y
Central Hudson |  | SolarCity | CH-04975 | Catskill | Haines Fls | Greene | 12436 | G | 2385 | Lawrenceville | N |  | 10 | [13 empty] | NM | N | 2 SOLAREDGE SE5000A US-ZB-U | 2014-11-12 | 2014-11-19 | 5 | 2014-11-19 | [8 empty] | 350 | 350 |  |  |  |  | 2015-03-04 | 2015-03-04 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-05151 | Kingston | Saugerties | Ulster | 12477 | G | 3014 | Woodstock | N | CH-05151 | 3.8 | [13 empty] | NM | N | SOLAREDGE SE3800A US-ZB-U | 2014-11-12 | 2014-11-19 | 5 | 2014-11-19 | [14 empty] | 2015-01-14 | 2015-01-21 |  | Y
Central Hudson |  | SolarCity | CH-05996 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8091 | Fishkill Plains | N |  | 9.6 | [13 empty] | NM | N | ABB PVI-6000 (1) ABB PVI-3.6 (1) | 2014-11-12 | 2014-11-18 | 4 | 2014-11-18 | [14 empty] | 2015-02-09 | 2015-02-17 |  | Y
Central Hudson |  | SolarCity | CH-06510 | Kingston | Kingston |  | 12401 | G | 1022 | East Kingston | TBD |  | 3 | [13 empty] | NM | N | ABB PVI-3.0-OUTD-S US-Z-A | 2014-11-12 | 2014-11-19 | 5 | 2014-11-19 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | SolarCity | CH-06720 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6051 | Todd Hill | N |  | 10.6 | [13 empty] | NM | N | 1 - SOLAREDGE SE7600A 1 - SOLAREDGE SE3000A | 2014-11-12 | 2014-11-19 | 5 | 2014-11-19 | [14 empty] | 2015-01-22 | 2015-01-29 |  | Y
Central Hudson |  | SolarCity | CH-07324 | Poughkeepsie | Ancramdale |  | 12503 | G | 7092 | Pulvers Corners | TBD |  | 8 | [13 empty] | NM | N | 1 - SolarEdge SE5000A-US 1 - SolarEdge SE3000A-US | 2014-11-12 | 2014-11-19 | 5 | 2014-11-19 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | SolarCity | CH-07552 | Poughkeepsie | Rhinebeck |  | 12572 | G | 7052 | Rhinebeck | TBD |  | 3 | [13 empty] | NM | N | SolarEdge SE3000A-US | 2014-11-12 | 2014-11-19 | 5 | 2014-11-19 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | SolarCity | CH-07754 | Kingston | Kingston | Ulster | 12401 | G | 1003 | Jansen Ave | N |  | 11 | [13 empty] | NM | N | 1 SOLAREDGE SE6000A-US-ZB-U 1 SOLAREDGE SE5000A-US-ZB-U | 2014-11-12 | 2014-11-19 | 5 | 2014-11-19 | [14 empty] | 2015-02-09 | 2015-02-17 |  | Y
Central Hudson |  | SolarCity | CH-07825 | Newburgh | Wallkill | Ulster | 12589 | G | 5012 | Modena | N | CH-05369 | 5 | [13 empty] | NM | N | ABB PVI-5000 (1) | 2014-11-12 | 2014-11-18 | 4 | 2014-11-18 | [14 empty] | 2014-12-19 | 2014-12-29 |  | Y
Central Hudson |  | Sol Providers | CH-08918 | Kingston | Napanoch | Ulster | 12458 | G | 3072 | Honk Falls | N |  | 11.4 | [13 empty] | NM | N | SOLAREDGE 114000 US | 2014-11-12 | 2014-11-19 | 5 | 2014-11-19 | [8 empty] | 350 | 350 |  |  |  |  | 2015-01-08 | 2015-01-15 |  | Y
Central Hudson |  | Verengo Solar | CH-09777 | Newburgh | New Windsor | Orange | 12553 | G | 4094 | Bethlehem Rd | N |  | 9.03 | [13 empty] | NM | N | ENPHASE ENERGY M215 (42) | 2014-11-12 | 2014-11-18 | 4 | 2014-11-18 | [14 empty] | 2015-04-13 | 2015-04-20 |  | Y
Central Hudson |  | Verengo Solar | CH-09804 | Fishkill | Wappingrs Falls |  | 12590 | G | 8091 | Fishkill Plains | TBD |  | 7.74 | [13 empty] | NM | N | ENPHASE ENERGY M215 (36) | 2014-11-12 | 2014-11-18 | 4 | 2014-11-18 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | New York State Solar Farm | CH-03989 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8095 | Fishkill Plains | N |  | 9.2 | [13 empty] | NM | N | POWER ONE PVI 5000 (1) POWER ONE PVI 4.2 (1) | 2014-11-26 | 2014-12-05 | 5 | 2014-12-05 | [14 empty] | 2015-03-17 | 2015-03-24 |  | Y
Central Hudson |  | New York State Solar Farm | CH-04095 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8092 | Fishkill Plains | N | CH-03990 | 2 | [13 empty] | NM | N | POWER ONE PVI 5.0 (1) | 2014-11-13 | 2014-11-20 | 5 | 2014-11-20 | [14 empty] | 2015-01-05 | 2015-01-12 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00843 | Kingston | Saugerties | Ulster | 12477 | G | 3001 | Saugerties | N |  | 4.3 | [13 empty] | NM | N | 20 ENPHASE M215 60-2LL-S22 | 2014-11-13 | 2014-11-20 | 5 | 2014-11-20 | [14 empty] | 2014-12-22 | 2014-12-31 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00924 | Kingston | Saugerties | Ulster | 12477 | G | 2015 | Lincoln Park | N |  | 6.45 | [13 empty] | NM | N | 30 ENPHASE M215 60-2LL-S22 | 2014-11-13 | 2014-11-20 | 5 | 2014-11-20 | [14 empty] | 2015-02-25 | 2015-03-04 |  | Y
Central Hudson |  | George J Martin & Sons, Inc. | CH-01135 | Catskill | Medusa | Albany | 12120 | G | 1092 | Westerlo | N |  | 6.5 | [13 empty] | NM | N | 28 ENPHASE ENERGY M215 60-2LL-S22 | 2014-11-13 | 2014-11-20 | 5 | 2014-11-20 | [14 empty] | 2015-01-14 | 2015-01-14 |  | Y
Central Hudson |  | SolarCity | CH-05161 | Fishkill | Beacon | Dutchess | 12508 | G | 8087 | Tioronda | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A (1) | 2014-11-13 | 2014-11-20 | 5 | 2014-11-20 | [14 empty] | 2015-01-09 | 2015-01-16 |  | Y
Central Hudson |  | SolarCity | CH-06349 | Newburgh | Wallkill | Ulster | 12589 | G | 5043 | East Walden | N |  | 3.8 | [13 empty] | NM | N | SOLAREDGE SE3800A (1) | 2014-11-13 | 2014-11-20 | 5 | 2014-11-20 | [14 empty] | 2015-01-05 | 2015-01-13 |  | Y
Central Hudson |  | Solar Generation | CH-08242 | Kingston | Woodstock | Ulster | 12498 | G | 3014 | Woodstock | N |  | 5 | [13 empty] | NM | N | SMA SB 5000 TL | 2014-11-13 | 2014-11-20 | 5 | 2014-11-20 | [14 empty] | 2015-02-18 | 2015-02-25 |  | W
Central Hudson |  | Sungevity Inc | CH-09186 | Newburgh | Walden |  | 12586 | G | 5041 | East Walden | TBD |  | 7 | [13 empty] | NM | N | SMA AMERICA SB7000US (1) | 2014-11-13 | 2014-11-20 | 5 | 2014-11-20 | [17 empty] | W
Central Hudson |  | Sungevity Inc | CH-09454 | Fishkill | Fishkill | Dutchess | 12524 | G | 8094 | Fishkill Plains | N |  | 5 | [13 empty] | NM | N | SMA AMERICA SB5000TL (1) | 2014-11-13 | 2014-11-20 | 5 | 2014-11-20 | [14 empty] | 2014-12-19 | 2014-12-29 |  | Y
Central Hudson |  | New York State Solar Farm | CH-03942 | Poughkeepsie | Lagrangevl | Dutchess | 12540 | G | 6057 | Todd Hill | N |  | 24 | [13 empty] | NM | N | 4 - POWERONE PVI 6000 | 2014-11-14 | 2014-11-24 | 6 | 2014-11-24 | [8 empty] | 350 | 350 |  |  |  |  | 2015-01-13 | 2015-01-21 |  | Y
Central Hudson |  | New York State Solar Farm | CH-04035 | Newburgh | Highland | Ulster | 12528 | G | 5012 | Modena | N |  | 6 | [13 empty] | NM | N | SMA AMERICA SB 6.0 (1) | 2014-11-14 | 2014-11-20 | 4 | 2014-11-20 | [14 empty] | 2015-02-06 | 2015-02-13 |  | Y
Central Hudson |  | New York State Solar Farm | CH-04065 | Fishkill | Cold Spg | Putnam | 10516 | G | 8086 | Tioronda | N |  | 7 | [13 empty] | NM | N | SMA SB7000US (1) | 2014-11-14 | 2014-11-20 | 4 | 2014-11-20 | [14 empty] | 2015-01-12 | 2015-01-19 |  | Y
Central Hudson |  | Natural Energy Solutions | CH-02764 | Poughkeepsie | Salt Pt | Dutchess | 12578 | G | 7011 | Hibernia | N |  | 18 | [13 empty] | NM | N | 72 -ENPHASE M250 | 2014-11-25 | 2014-12-04 | 5 | 2014-12-04 | [14 empty] | 2015-01-09 | 2015-01-16 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-05077 | Newburgh | Milton | Ulster | 12547 | G | 5002 | Marlboro | N |  | 12 | [13 empty] | NM | N | SOLAREDGE SE6000A (2) | 2014-11-14 | 2014-11-20 | 4 | 2014-11-20 | [14 empty] | 2015-01-26 | 2015-02-02 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-05277 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8093 | Fishkill Plains | N |  | 6.8 | [13 empty] | NM | N | SOLAREDGE SE3000A (1) SOLAREDGE SE3800A (1) | 2014-11-14 | 2014-11-20 | 4 | 2014-11-20 | [14 empty] | 2015-01-29 | 2015-02-05 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06010 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8091 | Fishkill Plains | N |  | 8.8 | [13 empty] | NM | N | SOLAREDGE SE3800A (1) SOLAREDGE SE5000A (1) | 2014-11-14 | 2014-11-20 | 4 | 2014-11-20 | [14 empty] | 2015-01-30 | 2015-02-06 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06205 | Newburgh | Wallkill | Ulster | 12589 | G | 5041 | East Walden | N |  | 11 | [13 empty] | NM | N | SOLAREDGE SE5000A (1) SOLAREDGE SE6000A (1) | 2014-11-14 | 2014-11-20 | 4 | 2014-11-20 | [8 empty] | 350 | 350 |  |  |  |  | 2015-01-29 | 2015-02-05 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06419 | Newburgh | Montgomery | Orange | 12549 | G | 5073 | Montgomery | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A (1) | 2014-11-21 | 2014-12-02 | 5 | 2014-12-02 | [14 empty] | 2015-05-26 | 2015-06-02 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06733 | Poughkeepsie | Salt Pt | Dutchess | 12578 | G | 7011 | Hibernia | N |  | 3 | [13 empty] | NM | N | ABB (POWER-ONE) PVI-3.0-OUTD-S | 2014-11-14 | 2014-11-21 | 5 | 2014-11-21 | [14 empty] | 2015-01-05 | 2015-01-12 |  | Y
Central Hudson |  | SolarCity | CH-06966 | Newburgh | New Paltz | Ulster | 12561 | G | 5022 | Ohioville | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A (1) | 2014-11-14 | 2014-11-20 | 4 | 2014-11-20 | [14 empty] | 2015-01-23 | 2015-01-30 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06998 | Newburgh | Newburgh | Orange | 12550 | G | 5041 | East Walden | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE500A (1) | 2014-11-21 | 2014-12-02 | 5 | 2014-12-02 | [14 empty] | 2015-01-15 | 2015-01-22 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07351 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8043 | Myers Corners | N |  | 3.8 | [13 empty] | NM | N | SOLAREDGE SE3800A (1) | 2014-11-14 | 2014-11-20 | 4 | 2014-11-20 | [14 empty] | 2015-01-05 | 2015-01-12 |  | Y
Central Hudson |  | SolarCity | CH-07496 | Kingston | Rosendale | Ulster | 12472 | G | 3022 | High Falls | N |  | 5 | [13 empty] | NM | N | ABB PVI-5000-OUTD-US-Z-A | 2014-11-14 | 2014-11-21 | 5 | 2014-11-21 | [14 empty] | 2015-03-02 | 2015-03-09 |  | Y
Central Hudson |  | SolarCity | CH-07597 | Newburgh | Newburgh | Orange | 12550 | G | 4023 | Coldenham | N |  | 3 | [13 empty] | NM | N | ABB PVI-3.0 | 2014-11-14 | 2014-11-20 | 4 | 2014-11-20 | [14 empty] | 2014-12-22 | 2014-12-31 |  | Y
Central Hudson |  | Sun Mountain | CH-09120 | Kingston | Kingston | Ulster | 12401 | G | 2094 | Hurley Ave | N |  | 8 | [13 empty] | NM | N | SMA SB8000 US-12 | 2014-11-14 | 2014-11-21 | 5 | 2014-11-21 | [14 empty] | 2015-01-16 | 2015-01-23 |  | Y
Central Hudson |  | Sungevity Inc | CH-09197 | Kingston | New Paltz | Ulster | 12561 | G | 3041 | Sturgeon Pool | N |  | 11 | [13 empty] | NM | N | 1 SMA SB5000TL-US-22 240 1 SMA SB6000TL-US-22 240 | 2014-11-14 | 2014-11-21 | 5 | 2014-11-21 | [8 empty] | 350 | 350 |  |  |  |  | 2015-02-11 | 2015-02-19 |  | Y
Central Hudson |  | NRG Home Solar | CH-04421 | Fishkill | Fishkill |  | 12524 | G | 8014 | Forgebrook | TBD |  | 15.75 | [13 empty] | NM | N | ENPHASE ENERGY M-250 (63) | 2014-11-17 | 2014-11-25 | 6 | 2014-11-25 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | NRG Home Solar | CH-04808 | Catskill | Rensselaerville |  | 12147 | G | 1092 | Westerlo | TBD |  | 5.805 | [13 empty] | NM | N | 27 ENPHASE M-215-60-2LL-S22-IG | 2014-11-17 | 2014-11-24 | 5 | 2014-11-24 | [17 empty] | W
Central Hudson |  | SolarCity | CH-05003 | Kingston | Saugerties | Ulster | 12477 | G | 3002 | Saugerties | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A US-ZB-U | 2014-11-17 | 2014-11-24 | 5 | 2014-11-24 | [14 empty] | 2014-12-15 | 2014-12-22 |  | Y
Central Hudson |  | SolarCity | CH-05219 | Newburgh | Highland | Ulster | 12528 | G | 5083 | Highland | N |  | 10.6 | [13 empty] | NM | N | 1 - SOLAREDGE SE7600A 1 - SOLAREDGE SE3000A | 2014-11-17 | 2014-11-24 | 5 | 2014-11-24 | [14 empty] | 2015-01-12 | 2015-01-19 |  | Y
Central Hudson |  | SolarCity | CH-05581 | Catskill | Coxsackie | Greene | 12051 | G | 1076 | Coxsackie | N |  | 7.6 | [13 empty] | NM | N | 2 SOLAREDGE SE3800A US-ZB-U | 2014-11-17 | 2014-11-24 | 5 | 2014-11-24 | [14 empty] | 2015-01-26 | 2015-02-02 |  | Y
Central Hudson |  | SolarCity | CH-05897 | Poughkeepsie | Lagrangevl | Dutchess | 12540 | G | 6055 | Todd Hill | N |  | 11 | [13 empty] | NM | N | 1 - SOLAREDGE SE6000A 1 - SOLAREDGE SE5000A | 2014-11-17 | 2014-11-24 | 5 | 2014-11-24 | [14 empty] | 2015-01-07 | 2015-01-14 |  | Y
Central Hudson |  | Solar Generation | CH-08181 | Kingston | Eddyville |  | 12401 | G | 1014 | Boulevard | TBD |  | 5 | [13 empty] | NM | N | SMA SB 5000 TL | 2014-11-17 | 2014-11-24 | 5 | 2014-11-24 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | Sungevity Inc | CH-09571 | Poughkeepsie | Pine Plns | Dutchess | 12567 | G | 7091 | Pulvers Corners | N |  | 6 | [13 empty] | NM | N | SMA SB6000TL | 2014-12-09 | 2014-12-23 | 10 | 2014-12-23 | [14 empty] | 2015-01-07 | 2015-01-14 |  | Y
Central Hudson |  | Verengo Solar | CH-09775 | Kingston | Woodstock | Ulster | 12498 | G | 3014 | Woodstock | N |  | 5.8 | [13 empty] | NM | N | 27 ENPHASE ENERGY M215-60-2LL-S22-IG | 2014-11-17 | 2014-12-03 | 10 | 2014-12-03 | [14 empty] | 2015-01-20 | 2015-01-26 |  | Y
Central Hudson |  | Verengo Solar | CH-09789 | Kingston | Kingston | Ulster | 12401 | G | 1022 | East Kingston | N |  | 3.65 | [13 empty] | NM | N | 17 ENPHASE M215-60-2LL-S22-IG | 2014-11-17 | 2014-11-24 | 5 | 2014-11-24 | [14 empty] | 2015-01-12 | 2015-01-19 |  | Y
Central Hudson |  | Verengo Solar | CH-09827 | Newburgh | Wallkill | Ulster | 12589 | G | 4011 | West Balmville | N |  | 6.45 | [13 empty] | NM | N | ENPHASE ENERGY M215 (30) | 2014-11-17 | 2014-11-25 | 6 | 2014-11-25 | [14 empty] | 2015-01-12 | 2015-01-19 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03834 | Newburgh | New Paltz | Ulster | 12561 | G | 5025 | Ohioville | Y | CH-00621 | 2.5 | [13 empty] | NM | N | ABB PowerOne UNO 2.5 | 2014-12-04 | 2014-12-10 | 4 | 2014-12-10 | [14 empty] | 2015-03-19 | 2015-03-26 |  | Y
Central Hudson |  | New York State Solar Farm | CH-04043 | Newburgh | Marlboro | Ulster | 12542 | G | 5002 | Marlboro | N |  | 6 | [13 empty] | NM | N | SMA AMERICA SB-TL 6.0 (1) | 2014-11-18 | 2014-12-02 | 8 | 2014-12-02 | [14 empty] | 2015-05-06 | 2015-05-12 |  | Y
Central Hudson |  | Paradise Energy Solutions LLC | CH-02836 | Newburgh | Gardiner | Ulster | 12525 | G | 5031 | Galeville | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE 7600 (1) | 2014-11-18 | 2014-12-01 | 7 | 2014-12-01 | [14 empty] | 2014-12-23 | 2014-12-31 |  | Y
Central Hudson |  | SolarCity | CH-05244 | Kingston | Ulster Park | Ulster | 12487 | G | 1014 | Boulevard | N |  | 15 | [13 empty] | NM | N | 2 FRONIUS IG PLUS A 7.5 | 2014-11-18 | 2014-11-25 | 5 | 2014-11-25 | [8 empty] | 350 | 350 |  |  |  |  | 2015-04-07 | 2015-04-14 |  | Y
Central Hudson |  | SolarCity | CH-05469 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6052 | Todd Hill | N |  | 8 | [13 empty] | NM | N | 1 - SOLAREDGE SE5000A 1 - SOLAREDGE SE3000A | 2014-11-18 | 2014-11-24 | 4 | 2014-11-24 | [14 empty] | 2015-01-21 | 2015-01-30 |  | Y
Central Hudson |  | SolarCity | CH-06194 | Newburgh | Newburgh | Orange | 12550 | G | 5004 | Marlboro | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE7600A (1) | 2014-11-18 | 2014-11-26 | 6 | 2014-11-26 | [14 empty] | 2015-01-05 | 2015-01-13 |  | Y
Central Hudson |  | SolarCity | CH-06347 | Newburgh | Wallkill | Ulster | 12589 | G | 5043 | East Walden | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A (1) | 2014-11-18 | 2014-11-26 | 6 | 2014-11-26 | [14 empty] | 2015-01-05 | 2015-01-09 |  | Y
Central Hudson |  | SolarCity | CH-06370 | Newburgh | Wallkill | Ulster | 12589 | G | 5043 | East Walden | N |  | 10.2 | [13 empty] | NM | N | ABB PVI-6000 (1) ABB PVI-4.2 (1) | 2014-11-18 | 2014-11-26 | 6 | 2014-11-26 | [14 empty] | 2015-01-14 | 2015-01-21 |  | Y
Central Hudson |  | SolarCity | CH-06607 | Kingston | Kingston | Ulster | 12401 | G | 2013 | Lincoln Park | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A US-ZB-U | 2014-11-18 | 2014-11-25 | 5 | 2014-11-25 | [14 empty] | 2014-12-29 | 2014-12-31 |  | Y
Central Hudson |  | SolarCity | CH-07121 | Newburgh | Cornwall-Hdsn | Orange | 12520 | G | 4043 | Union Ave | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A (1) | 2014-11-18 | 2014-12-01 | 7 | 2014-12-01 | [14 empty] | 2014-12-18 | 2014-12-26 |  | Y
Central Hudson |  | Sungevity Inc | CH-09353 | Fishkill | Fishkill | Dutchess | 12524 | G | 8065 | Merritt Park | N |  | 7.8 | [13 empty] | NM | N | SMA AMERICA SB4000TL (1) SMA AMERICA SB3800TL (1) | 2014-11-18 | 2014-12-01 | 7 | 2014-12-01 | [14 empty] | 2014-12-19 | 2014-12-30 |  | Y
Central Hudson |  | Verengo Solar | CH-09872 | Newburgh | Newburgh | Orange | 12550 | G | 4023 | Coldenham | N |  | 7.955 | [13 empty] | NM | N | ENPHASE ENERGY M215 (37) | 2014-11-18 | 2014-12-01 | 7 | 2014-12-01 | [14 empty] | 2015-08-20 | 2015-08-25 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03628 | Newburgh | New Paltz | Ulster | 12561 | G | 5031 | Galeville | N | CH-03628 | 15.2 | [13 empty] | NM | N | SOLAREDGE SE 7600 (2) | 2015-05-12 | 2015-05-18 | 4 | 2015-05-18 | [8 empty] | 350 | 350 |  |  |  |  | 2015-08-03 | 2015-08-10 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03643 | Newburgh | Highland | Ulster | 12528 | G | 5022 | Ohioville | N |  | 20 | [13 empty] | NM | N | 2 SOLAREDGE SE 10000 | 2014-11-19 | 2014-11-26 | 5 | 2014-11-26 | [14 empty] | 2015-04-28 | 2015-05-05 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03685 | Newburgh | New Paltz | Ulster | 12561 | G | 5031 | Galeville | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE 7600 (1) | 2014-11-19 | 2014-12-02 | 7 | 2014-12-02 | [14 empty] | 2015-07-22 | 2015-07-27 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03769 | Newburgh | Milton | Ulster | 12547 | G | 5003 | Marlboro | N |  | 10 | [13 empty] | NM | N | SOLAREDGE SE 10000 (1) | 2014-11-19 | 2014-12-02 | 7 | 2014-12-02 | [14 empty] | 2015-02-09 | 2015-02-17 |  | Y
Central Hudson |  | New York State Solar Farm | CH-03933 | Newburgh | Wallkill | Ulster | 12589 | G | 5041 | East Walden | N |  | 10.2 | [13 empty] | NM | N | POWERONE PVI 6000 (1) POWERONE PVI 4.2 (1) | 2014-11-19 | 2014-12-02 | 7 | 2014-12-02 | [14 empty] | 2015-03-25 | 2015-04-01 |  | Y
Central Hudson |  | New York State Solar Farm | CH-03982 | Poughkeepsie | Lagrangevl | Dutchess | 12540 | G | 6057 | Todd Hill | N |  | 24.8 | [13 empty] | NM | N | 3 - POWERONE PVI 6.0, 1 - POWERONE PVI 3.8, 1 - Powerone 3.0 | 2015-01-13 | 2015-01-26 | 9 | 2015-01-26 | [8 empty] | 350 | 350 |  |  |  |  | 2015-04-15 | 2015-04-22 |  | Y
Central Hudson |  | NRG Home Solar | CH-04239 | Catskill | Medusa | Albany | 12120 | G | 1092 | Westerlo | N |  | 3.75 | [13 empty] | NM | N | 15 ENPHASE M-250-60-2LL-S22 | 2014-11-19 | 2014-11-26 | 5 | 2014-11-26 | [14 empty] | 2015-08-27 | 2015-09-03 |  | Y
Central Hudson |  | NRG Home Solar | CH-04535 | Kingston | Woodstock | Ulster | 12498 | G | 3014 | Woodstock | N |  | 5.59 | [13 empty] | NM | N | 26 ENPHASE M-215-60-2LL-S22-IG | 2014-12-04 | 2014-12-04 | 0 | 2014-12-04 | [14 empty] | 2015-06-03 | 2015-06-10 |  | Y
Central Hudson |  | Murphy Solar Power | CH-02720 | Catskill | Leeds | Greene | 12451 | G | 2071 | Freehold | N |  | 5 | [13 empty] | NM | N | SMA 5000 TL-22 | 2014-11-19 | 2014-11-26 | 5 | 2014-11-26 | [14 empty] | 2015-08-11 | 2015-08-18 |  | Y
Central Hudson |  | Solar Generation | CH-08098 | Kingston | Saugerties | Ulster | 12477 | G | 3003 | Saugerties | N |  | 5 | [13 empty] | NM | N | SMA SB 5000 TL | 2014-11-19 | 2014-11-26 | 5 | 2014-11-26 | [14 empty] | 2015-04-08 | 2015-04-15 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-03395 | Newburgh | Newburgh | Orange | 12550 | G | 4023 | Coldenham | N |  | 6 | [13 empty] | NM | N | SMA AMERICA SB6000TL (1) | 2014-11-20 | 2014-12-02 | 6 | 2014-12-02 | [14 empty] | 2015-04-15 | 2015-04-22 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-03424 | Newburgh | New Windsor | Orange | 12553 | G | 4043 | Union Ave | N |  | 7.6 | [13 empty] | NM | N | SMA AMERICA SB3800TL (2) | 2014-11-20 | 2014-12-02 | 6 | 2014-12-02 | [14 empty] | 2015-04-13 | 2015-04-20 |  | Y
Central Hudson |  | Hudson Solar | CH-01242 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7041 | Staatsburg | N |  | 15 | [13 empty] | RNM | N | 1 - SMA AMERICA SB10000 1 - SMA AMERICA SB5000 | 2014-11-25 | 2014-12-04 | 5 | 2014-12-04 | [14 empty] | 2015-04-17 | 2015-04-24 |  | Y
Central Hudson |  | Hudson Solar | CH-01572 | Poughkeepsie | Tivoli | Dutchess | 12583 | G | 7062 | Milan | N |  | 8.8 | [13 empty] | NM | N | 1 - SMA AMERICA SB5000 1 - SMA AMERICA SB3800 | 2014-11-20 | 2014-12-08 | 10 | 2014-12-08 | [14 empty] | 2015-01-23 | 2015-01-30 |  | Y
Central Hudson |  | Hudson Solar | CH-01727 | Kingston | Kingston | Ulster | 12401 | G | 2014 | Lincoln Park | N |  | 6 | [13 empty] | NM | N | SMA AMERICA SB6000 TL-US-22 | 2014-11-20 | 2014-11-27 | 4 | 2014-11-27 | [14 empty] | 2015-05-13 | 2015-05-15 |  | Y
Central Hudson |  | Hudson Solar | CH-01823 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6092 | Manchester | N |  | 7 | [13 empty] | NM | N | SMA AMERICA SB7000 | 2014-11-20 | 2014-12-01 | 5 | 2014-12-01 | [14 empty] | 2015-03-04 | 2015-03-10 |  | Y
Central Hudson |  | Hudson Solar | CH-02115 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6092 | Manchester | N | CH-02115 | 6 | [13 empty] | NM | N | SMA AMERICA SB6000 | 2014-11-20 | 2014-12-01 | 5 | 2014-12-01 | [14 empty] | 2015-05-20 | 2015-05-28 |  | Y
Central Hudson |  | Hudson Solar | CH-02479 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8093 | Fishkill Plains | N | CH-01931 | 2 | [13 empty] | NM | N | SMA AMERICA SB2000 (1) | 2014-11-20 | 2014-12-02 | 6 | 2014-12-02 | [14 empty] | 2015-02-13 | 2015-02-23 |  | Y
Central Hudson |  | SolarCity | CH-05553 | Catskill | Freehold | Greene | 12431 | G | 2071 | Freehold | N |  | 10 | [13 empty] | NM | N | 2 SOLAREDGE SE5000A US-ZB-U | 2014-11-20 | 2014-11-27 | 4 | 2014-11-27 | [14 empty] | 2015-05-29 | 2015-06-05 |  | Y
Central Hudson |  | SolarCity | CH-05728 | Kingston | Malden-Hdsn | Ulster | 12453 | G | 3004 | Saugerties | N |  | 9.8 | [13 empty] | NM | N | (1) SOLAREDGE SE6000A US-ZB (1) SOLAREDGE SE3800A US-ZB | 2014-11-20 | 2014-12-01 | 5 | 2014-12-01 | [8 empty] | 350 | 350 |  |  |  |  | 2014-12-26 | 2014-12-29 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07756 | Kingston | Woodstock | Ulster | 12498 | G | 3012 | Woodstock | N |  | 4.2 | [13 empty] | NM | N | ABB PVI-4.2-OUTD-S US-Z-A | 2014-11-20 | 2014-11-27 | 4 | 2014-11-27 | [14 empty] | 2015-02-26 | 2015-03-05 |  | Y
Central Hudson |  | Hudson Solar | CH-01328 | Poughkeepsie | Milan | Dutchess | 12571 | G | 7061 | Milan | N |  | 5 | [13 empty] | NM | N | SMA AMERICA SB5000 | 2014-11-21 | 2014-12-09 | 10 | 2014-12-09 | [14 empty] | 2015-05-18 | 2015-05-26 |  | Y
Central Hudson |  | Hudson Solar | CH-01520 | Newburgh | Cornwall-Hdsn | Orange | 12520 | G | 4043 | Union Ave | N |  | 7 | [13 empty] | NM | N | SMA AMERICA SB7000 (1) | 2014-11-21 | 2014-12-02 | 5 | 2014-12-02 | [14 empty] | 2015-04-02 | 2015-04-10 |  | Y
Central Hudson |  | Hudson Solar | CH-01765 | Poughkeepsie | Staatsburg | Dutchess | 12580 | G | 7041 | Staatsburg | N |  | 11.4 | [13 empty] | NM | N | SolarEdge 11400A-US | 2014-12-03 | 2014-12-11 | 6 | 2014-12-11 | [14 empty] | 2015-12-29 | 2016-01-06 |  | Y
Central Hudson |  | Hudson Solar | CH-01787 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 6057 | Todd Hill | N |  | 9 | [13 empty] | NM | N | SMA AMERICA SB9000 | 2014-11-21 | 2014-12-09 | 10 | 2014-12-09 | [8 empty] | 350 | 350 |  |  |  |  | 2016-05-25 | 2016-06-01 |  | Y
Central Hudson |  | Hudson Solar | CH-01829 | Poughkeepsie | Barrytown |  | 12507 | G | 7056 | Rhinebeck | TBD |  | 7.7 | [13 empty] | NM | N | SMA AMERICA SB7700 | 2014-12-11 | 2014-12-18 | 5 | 2014-12-18 | [17 empty] | W |  | Customer already had net meter prior to application. 11/27/14 & 11/28/14 Company Holidays.
Central Hudson |  | Hudson Solar | CH-01941 | Newburgh | New Paltz | Ulster | 12561 | G | 5031 | Galeville | N |  | 5 | [13 empty] | NM | N | SB5000 TL-US (1) | 2014-11-21 | 2014-12-02 | 5 | 2014-12-02 | [14 empty] | 2015-02-11 | 2015-02-19 |  | Y
Central Hudson |  | Hudson Solar | CH-02130 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7052 | Rhinebeck | N |  | 10 | [13 empty] | NM | N | 2 - SMA AMERICA SB5000 | 2014-11-21 | 2014-12-09 | 10 | 2014-12-09 | [14 empty] | 2015-05-04 | 2015-05-11 |  | Y
Central Hudson |  | Hudson Solar | CH-02314 | Fishkill | Cold Spg | Putnam | 10516 | G | 8063 | Merritt Park | N |  | 6.8 | [13 empty] | NM | N | SMA AMERICA SB3800 (1) SMA AMERICA SB3000 (1) | 2014-11-21 | 2014-12-02 | 5 | 2014-12-02 | [14 empty] | 2015-06-23 | 2015-06-30 |  | Y
Central Hudson |  | Murphy Solar Power | CH-02714 | Newburgh | Highland |  | 12528 | G | 5083 | Highland | TBD |  | 8 | [13 empty] | NM | N | SMA SB8000US | 2014-11-21 | 2014-12-03 | 6 | 2014-12-03 | [17 empty] | W
Central Hudson |  | SolarCity | CH-05273 | Fishkill | Hopewell Jct |  | 12533 | G | 8093 | Fishkill Plains | TBD |  | 20.2 | [13 empty] | NM | N | SOLAREDGE SE7600A (2) SOLAREDGE SE5000A (1) | 2014-11-21 | 2014-12-02 | 5 | 2014-12-02 | [17 empty] | W |  | 11/27/14 & 11/28/14 Company Holidays.
Central Hudson |  | Sungevity Inc | CH-09198 | Fishkill | Beacon | Dutchess | 12508 | G | 8017 | Forgebrook | N |  | 6 | [13 empty] | NM | N | SMA AMERICA SB6000TL (1) | 2014-11-21 | 2014-12-02 | 5 | 2014-12-02 | [14 empty] | 2015-01-08 | 2015-01-15 |  | Y
Central Hudson |  | Sungevity Inc | CH-09453 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8092 | Fishkill Plains | N |  | 5 | [13 empty] | NM | N | SMA SB 5000TL (1) | 2014-11-21 | 2014-12-02 | 5 | 2014-12-02 | [14 empty] | 2015-01-12 | 2015-01-19 |  | Y
Central Hudson |  | Verengo Solar | CH-09772 | Newburgh | Newburgh | Orange | 12550 | G | 5004 | Marlboro | N |  | 4.515 | [13 empty] | NM | N | ENPHASE ENERGY M215 (21) | 2014-11-21 | 2014-12-02 | 5 | 2014-12-02 | [14 empty] | 2015-02-05 | 2015-02-12 |  | Y
Central Hudson |  | Verengo Solar | CH-09801 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6056 | Todd Hill | N |  | 6.45 | [13 empty] | NM | N | 30 - ENPHASE ENERGY M215 | 2014-11-21 | 2014-12-02 | 5 | 2014-12-02 | [14 empty] | 2015-05-12 | 2015-05-18 |  | Y
Central Hudson |  | Verengo Solar | CH-09868 | Fishkill | Beacon | Dutchess | 12508 | G | 8087 | Tioronda | N |  | 5.59 | [13 empty] | NM | N | ENPHASE ENERGY M215 (26) | 2014-11-21 | 2014-12-02 | 5 | 2014-12-02 | [14 empty] | 2015-01-12 | 2015-01-19 |  | Y
Central Hudson |  | NRG Home Solar | CH-04406 | Fishkill | Fishkill | Dutchess | 12524 | G | 8094 | Fishkill Plains | N |  | 4.73 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (22) | 2014-11-24 | 2014-12-04 | 6 | 2014-12-04 | [14 empty] | 2015-04-17 | 2015-04-24 |  | Y
Central Hudson |  | JJ Marquis Electrical | CH-02567 | Newburgh | Milton |  | 12547 | G | 5003 | Marlboro | TBD |  | 6 | [13 empty] | NM | N | SOLAR EDGE 6000 | 2014-12-04 | 2014-12-04 | 0 | 2014-12-04 | [17 empty] | W |  | Customer already had net meter prior to application.11/27/14 & 11/28/14 Company Holidays.
Central Hudson |  | SolarCity | CH-05770 | Kingston | Lk Katrine | Ulster | 12449 | G | 2016 | Lincoln Park | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A US-ZB-U | 2014-11-24 | 2014-12-01 | 3 | 2014-12-01 | [14 empty] | 2014-12-29 | 2014-12-31 |  | Y
Central Hudson |  | SolarCity | CH-07139 | Newburgh | Washingtonvl | Orange | 10992 | G | 4097 | Bethlehem Rd | N |  | 12 | [13 empty] | NM | N | SOLAREDGE SE6000A-US (2) | 2014-11-24 | 2014-12-04 | 6 | 2014-12-04 | [14 empty] | 2015-01-20 | 2015-01-26 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08655 | Catskill | Ravena | Albany | 12143 | G | 1081 | New Baltimore | N |  | 8.17 | [13 empty] | NM | N | 38 ENPHASE M215-60-2LL-S2X-ZC | 2014-11-24 | 2014-12-01 | 3 | 2014-12-01 | [14 empty] | 2015-10-13 | 2015-10-16 |  | Y
Central Hudson |  | Sungevity Inc | CH-09399 | Kingston | Olive Brdg | Ulster | 12461 | G | 3023 | High Falls | N |  | 7.6 | [13 empty] | NM | N | 2 SMA AMERICA SB3800TL-US-22 | 2014-11-24 | 2014-12-01 | 3 | 2014-12-01 | [14 empty] | 2015-01-23 | 2015-01-30 |  | Y
Central Hudson |  | Verengo Solar | CH-09796 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6011 | Sand Dock | N |  | 4.085 | [13 empty] | NM | N | 19 - ENPHASE ENERGY M215 | 2014-11-24 | 2014-12-03 | 5 | 2014-12-03 | [14 empty] | 2015-04-29 | 2015-05-06 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00901 | Kingston | Kingston | Ulster | 12401 | G | 2094 | Hurley Ave | N |  | 27 | [13 empty] | NM | N | 3 SOLAR EDGE 9000 SE9KUS | 2014-11-25 | 2014-12-04 | 5 | 2014-12-04 | [14 empty] | 2015-01-13 | 2015-01-22 |  | Y
Central Hudson |  | SolarCity | CH-05285 | Newburgh | Newburgh | Orange | 12550 | G | 5001 | Marlboro | N |  | 11.4 | [13 empty] | NM | N | FRONIUS IG PLUS A 11.4 | 2014-11-25 | 2014-12-04 | 5 | 2014-12-04 | [14 empty] | 2014-12-30 | 2015-01-07 |  | Y
Central Hudson |  | SolarCity | CH-07486 | Catskill | Oak Hill | Greene | 12460 | G | 1092 | Westerlo | N |  | 10 | [13 empty] | NM | N | 2 SCHNEIDER CONEXT TX-5000 NA-240 | 2014-11-25 | 2014-12-04 | 5 | 2014-12-04 | [14 empty] | 2015-02-20 | 2015-02-27 |  | Y |  | 11/27/14 & 11/28/14 Company Holidays.
Central Hudson |  | Sungevity Inc | CH-09433 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6092 | Manchester | N |  | 6.8 | [13 empty] | NM | N | 1 - SMA AMERICA SB3800TL-US 1 - SMA AMERICA SB3000TL-US | 2014-11-25 | 2014-12-04 | 5 | 2014-12-04 | [14 empty] | 2015-04-09 | 2015-04-16 |  | Y
Central Hudson |  | Sungevity Inc | CH-09581 | Kingston | Kingston | Ulster | 12401 | G | 2094 | Hurley Ave | N |  | 7.6 | [13 empty] | NM | N | 2 SMA AMERICA SB3800TL-US-22 | 2014-11-25 | 2014-12-04 | 5 | 2014-12-04 | [14 empty] | 2015-01-08 | 2015-01-15 |  | Y
Central Hudson |  | Sungevity Inc | CH-09596 | Kingston | Hurley | Ulster | 12443 | G | 2094 | Hurley Ave | N |  | 3.8 | [13 empty] | NM | N | SMA AMERICA SB3800TL-US-22 | 2014-11-25 | 2014-12-04 | 5 | 2014-12-04 | [14 empty] | 2015-01-22 | 2015-01-29 |  | Y
Central Hudson |  | Sungevity Inc | CH-09613 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8092 | Fishkill Plains | N | CH-09541 | 3 | [13 empty] | NM | N | SMA AMERICA SB3000TL (1) | 2014-12-05 | 2014-12-12 | 5 | 2014-12-12 | [14 empty] | 2015-01-09 | 2015-01-16 |  | Y
Central Hudson |  | New York State Solar Farm | CH-03946 | Newburgh | Gardiner | Ulster | 12525 | G | 5012 | Modena | N |  | 12.8 | [13 empty] | NM | N | SMA SB 3.0 (1), SMA SB 3.8 (1), & SMA SB 6.0 (1) | 2015-03-18 | 2015-03-18 | 0 | 2015-03-18 | [14 empty] | 2015-05-12 | 2015-05-18 |  | Y
Central Hudson |  | Solar Generation | CH-08067 | Kingston | Kingston |  | 12401 | G | 2091 | Hurley Ave | TBD |  | 9 | [13 empty] | NM | N | 3 SMA SB 3000 TL | 2014-11-26 | 2014-12-04 | 4 | 2014-12-04 | [17 empty] | W |  | 11/27/14 & 11/28/14 Company Holidays.
Central Hudson |  | Sungevity Inc | CH-09543 | Fishkill | Beacon | Dutchess | 12508 | G | 8015 | Forgebrook | N |  | 6 | [13 empty] | NM | N | SMA SB 6000 | 2014-11-26 | 2014-12-05 | 5 | 2014-12-05 | [14 empty] | 2015-01-28 | 2015-02-04 |  | Y
Central Hudson |  | Verengo Solar | CH-09813 | Fishkill | Beacon | Dutchess | 12508 | G | 8015 | Forgebrook | N |  | 4.73 | [13 empty] | NM | N | ENPHASE ENERGY M215 (22) | 2014-11-26 | 2014-12-05 | 5 | 2014-12-05 | [14 empty] | 2015-03-23 | 2015-03-30 |  | Y
Central Hudson |  | Verengo Solar | CH-09925 | Poughkeepsie | Red Hook |  | 12571 | G | 7061 | Milan | TBD |  | 6.665 | [13 empty] | NM | N | 31 - ENPHASE ENERGY M215 | 2014-11-26 | 2014-12-09 | 7 | 2014-12-09 | [17 empty] | W |  | Customer already had net meter prior to application. 11/27/14 & 11/28/14 Company Holidays.
Central Hudson |  | Trinity Solar | CH-08553 | Newburgh | Rock Tvrn | Orange | 12575 | G | 4097 | Bethlehem Rd | N |  | 5.75 | [13 empty] | NM | N | ENPHASE M250 (23) | 2014-12-04 | 2014-12-12 | 6 | 2014-12-12 | [14 empty] | 2015-05-19 | 2015-05-20 |  | Y
Central Hudson |  | New York State Solar Farm | CH-03932 | Newburgh | Campbell Hall | Orange | 10916 | G | 5051 | Maybrook | N |  | 10 | [13 empty] | NM | N | POWERONE PVI 5.0 (2) | 2014-12-01 | 2014-12-10 | 7 | 2014-12-10 | [14 empty] | 2015-02-03 | 2015-02-10 |  | Y
Central Hudson |  | NRG Home Solar | CH-04382 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8045 | Myers Corners | N |  | 6 | [13 empty] | NM | N | Solar Edge SE6000A-US | 2014-12-01 | 2014-12-10 | 7 | 2014-12-10 | [14 empty] | 2015-10-20 | 2015-10-23 |  | Y
Central Hudson |  | NRG Home Solar | CH-04465 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 5.805 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (27) | 2014-12-01 | 2014-12-10 | 7 | 2014-12-10 | [14 empty] | 2015-03-23 | 2015-03-30 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00986 | Kingston | Saugerties | Ulster | 12477 | G | 3003 | Saugerties | N |  | 7.74 | [13 empty] | NM | N | 36 ENPHASE M215 60-2LL-S22 | 2014-12-01 | 2014-12-05 | 4 | 2014-12-05 | [14 empty] | 2015-05-05 | 2015-05-12 |  | Y
Central Hudson |  | Hudson Solar | CH-01290 | Kingston | Kingston | Ulster | 12401 | G | 1022 | East Kingston | N |  | 10 | [13 empty] | NM | N | 2 SMA AMERICA SB5000 TL-US-22 | 2014-12-01 | 2014-12-04 | 3 | 2014-12-04 | [14 empty] | 2015-04-17 | 2015-04-24 |  | Y
Central Hudson |  | Hudson Solar | CH-01297 | Poughkeepsie | Staatsburg |  | 12580 | G | 7011 | Hibernia | TBD |  | 5 | [13 empty] | NM | N | SMA AMERICA SB5000 | 2014-12-12 | 2014-12-15 | 1 | 2014-12-15 | [17 empty] | W
Central Hudson |  | Hudson Solar | CH-01401 | Newburgh | Campbell Hall |  | 10916 | G | 5051 | Maybrook | TBD |  | 14 | [13 empty] | NM | N | SMA AMERICA SB7000 (2) | 2014-12-01 | 2014-12-10 | 7 | 2014-12-10 | [17 empty] | W
Central Hudson |  | Hudson Solar | CH-01724 | Kingston | Lk Katrine | Ulster | 12449 | G | 2011 | Lincoln Park | N |  | 4 | [13 empty] | NM | N | SMA AMERICA SB4000 TL-US-22 | 2014-12-01 | 2014-12-04 | 3 | 2014-12-04 | [14 empty] | 2015-05-26 | 2015-06-02 |  | Y
Central Hudson |  | Hudson Solar | CH-01920 | Fishkill | Fishkill | Dutchess | 12524 | G | 8014 | Forgebrook | N |  | 7.6 | [13 empty] | NM | N | SMA AMERICA SB3800 (2) | 2014-12-01 | 2014-12-10 | 7 | 2014-12-10 | [14 empty] | 2015-06-23 | 2015-06-30 |  | Y
Central Hudson |  | Hudson Solar | CH-02159 | Poughkeepsie | Clinton Corners | Dutchess | 12514 | G | 7071 | Stanfordville | N |  | 5 | [13 empty] | NM | N | SMA AMERICA SB5000 | 2014-12-01 | 2014-12-08 | 5 | 2014-12-08 | [14 empty] | 2015-04-17 | 2015-04-24 |  | Y
Central Hudson |  | Hudson Solar | CH-02447 | Poughkeepsie | Salt Pt | Dutchess | 12578 | G | 7011 | Hibernia | N | CH-01750 | 3 | [13 empty] | NM | N | SMA AMERICA SB3000 | 2014-12-01 | 2014-12-08 | 5 | 2014-12-08 | [14 empty] | 2015-05-22 | 2015-06-01 |  | Y
Central Hudson |  | Hudson Solar | CH-02475 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8095 | Fishkill Plains | N | CH-02169 | 9 | [13 empty] | NM | N | SMA AMERICA SB3000 (1) SMA AMERICA SB6000 (1) | 2014-12-01 | 2014-12-10 | 7 | 2014-12-10 | [14 empty] | 2015-05-26 | 2015-06-02 |  | Y
Central Hudson |  | SolarCity | CH-05857 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 6074 | East Park | N |  | 13.6 | [13 empty] | NM | N | 1- SOLAREDGE SE6000A 1- SOLAREDGE SE7600A | 2014-12-01 | 2014-12-08 | 5 | 2014-12-08 | [8 empty] | 350 | 350 |  | 2015-01-20 | 2015-01-20 | 2018-02-10 | 2015-03-31 | 2015-04-08 |  | Y
Central Hudson |  | SolarCity | CH-05884 | Poughkeepsie | Lagrangevl | Dutchess | 12540 | G | 6055 | Todd Hill | N |  | 7.6 | [13 empty] | NM | N | 2 - SOLAREDGE SE3800A | 2014-12-01 | 2014-12-08 | 5 | 2014-12-08 | [14 empty] | 2015-01-02 | 2015-01-09 |  | Y
Central Hudson |  | SolarCity | CH-05974 | Newburgh | Highland | Ulster | 12528 | G | 5024 | Ohioville | N |  | 7.6 | [13 empty] | NM | N | 1 - SOLAREDGE SE7600A | 2014-12-01 | 2014-12-08 | 5 | 2014-12-08 | [14 empty] | 2015-05-07 | 2015-05-11 |  | Y
Central Hudson |  | SolarCity | CH-06135 | Fishkill | Beacon | Dutchess | 12508 | G | 8013 | Forgebrook | N |  | 9.8 | [13 empty] | NM | N | SOLAREDGE SE6000A (1) SOLAREDGE SE3800A (1) | 2014-12-01 | 2014-12-10 | 7 | 2014-12-10 | [14 empty] | 2015-01-13 | 2015-01-19 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06580 | Kingston | Saugerties |  | 12477 | G | 3001 | Saugerties | TBD |  | 12.6 | [13 empty] | NM | N | SOLAREDGE SE7600A US-ZB-U SOLAREDGE SE5000A US-ZB-U | 2014-12-01 | 2014-12-04 | 3 | 2014-12-04 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | SolarCity | CH-06876 | Fishkill | Fishkill |  | 12524 | G | 8064 | Merritt Park | TBD |  | 7.5 | [13 empty] | NM | N | FRONIUS IG PLUS A 7.5 | 2014-12-01 | 2014-12-10 | 7 | 2014-12-10 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | SolarCity | CH-06902 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8072 | Shenandoah | N |  | 5 | [13 empty] | NM | N | ABB PVI-5000 (1) | 2014-12-01 | 2014-12-10 | 7 | 2014-12-10 | [14 empty] | 2015-02-09 | 2015-02-17 |  | Y
Central Hudson |  | SolarCity | CH-07242 | Kingston | Saugerties | Ulster | 12477 | G | 2015 | Lincoln Park | N |  | 6 | [13 empty] | NM | N | 2 ABB PVI-3.0-OUTD-S US-Z-A | 2014-12-01 | 2014-12-04 | 3 | 2014-12-04 | [14 empty] | 2015-01-05 | 2015-01-12 |  | Y
Central Hudson |  | Verengo Solar | CH-09798 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6073 | East Park | N |  | 3.225 | [13 empty] | NM | N | 15 - ENPHASE ENERGY M215 | 2014-12-01 | 2014-12-08 | 5 | 2014-12-08 | [14 empty] | 2015-05-20 | 2015-05-28 |  | Y
Central Hudson |  | Verengo Solar | CH-09805 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8091 | Fishkill Plains | N |  | 8.815 | [13 empty] | NM | N | ENPHASE ENERGY M215 (41) | 2014-12-01 | 2014-12-10 | 7 | 2014-12-10 | [14 empty] | 2015-04-27 | 2015-05-01 |  | Y
Central Hudson |  | Verengo Solar | CH-09840 | Newburgh | Wallkill | Ulster | 12589 | G | 5042 | East Walden | N |  | 10.965 | [13 empty] | NM | N | ENPHASE ENERGY M215 (51) | 2014-12-01 | 2014-12-10 | 7 | 2014-12-10 | [14 empty] | 2015-05-20 | 2015-05-27 |  | Y
Central Hudson |  | Verengo Solar | CH-09919 | Kingston | Kingston |  | 12401 | G | 1011 | Boulevard | TBD |  | 7.74 | [13 empty] | NM | N | 36 ENPHASE M215-60-2LL-S22-IG | 2014-12-01 | 2014-12-04 | 3 | 2014-12-04 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | SolarCity | CH-05406 | Newburgh | Wallkill | Ulster | 12589 | G | 5043 | East Walden | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000 (1) | 2014-12-02 | 2014-12-12 | 8 | 2014-12-12 | [14 empty] | 2015-01-21 | 2015-01-28 |  | Y
Central Hudson |  | SolarCity | CH-05750 | Kingston | Kingston | Ulster | 12401 | G | 2016 | Lincoln Park | N | CH-05750 | 3 | [13 empty] | NM | N | SOLAREDGE SE3000A US-ZB-U | 2014-12-02 | 2014-12-09 | 5 | 2014-12-09 | [14 empty] | 2015-02-09 | 2015-02-17 |  | Y
Central Hudson |  | SolarCity | CH-07011 | Newburgh | Newburgh | Orange | 12550 | G | 4051 | Union Ave | N |  | 3 | [13 empty] | NM | N | ABB PVI-3.0 (1) | 2014-12-02 | 2014-12-12 | 8 | 2014-12-12 | [14 empty] | 2015-04-20 | 2015-04-27 |  | Y
Central Hudson |  | SolarCity | CH-07028 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE7600A (1) | 2014-12-02 | 2014-12-12 | 8 | 2014-12-12 | [14 empty] | 2014-12-30 | 2015-01-02 |  | Y
Central Hudson |  | SolarCity | CH-07096 | Newburgh | Modena | Ulster | 12548 | G | 5012 | Modena | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A (1) | 2014-12-02 | 2014-12-11 | 7 | 2014-12-11 | [14 empty] | 2015-01-21 | 2015-01-28 |  | Y
Central Hudson |  | SolarCity | CH-07726 | Newburgh | Campbell Hall | Orange | 10916 | G | 5052 | Maybrook | N |  | 10.6 | [13 empty] | NM | N | SOLAREDGE SE7600A (1) SOLAREDGE SE3000A (1) | 2014-12-02 | 2014-12-11 | 7 | 2014-12-11 | [8 empty] | 350 | 350 |  |  |  |  | 2015-01-23 | 2015-01-26 |  | Y
Central Hudson |  | Sungevity Inc | CH-09306 | Kingston | Kingston | Ulster | 12401 | G | 2016 | Lincoln Park | N |  | 3 | [13 empty] | NM | N | SMA AMERICA SB3000TL-US-22 | 2014-12-02 | 2014-12-09 | 5 | 2014-12-09 | [14 empty] | 2015-03-13 | 2015-03-19 |  | Y
Central Hudson |  | Verengo Solar | CH-09836 | Newburgh | Marlboro | Ulster | 12542 | G | 5004 | Marlboro | N |  | 8.6 | [13 empty] | NM | N | ENPHASE ENERGY M215 (40) | 2014-12-02 | 2014-12-11 | 7 | 2014-12-11 | [14 empty] | 2015-04-15 | 2015-04-22 |  | Y
Central Hudson |  | NRG Home Solar | CH-04404 | Fishkill | Fishkill |  | 12524 | G | 8094 | Fishkill Plains | TBD |  | 6.5 | [13 empty] | NM | N | ENPHASE ENERGY M-250 (26) | 2014-12-03 | 2014-12-12 | 7 | 2014-12-12 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | NRG Home Solar | CH-04579 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8091 | Fishkill Plains | N |  | 12.5 | [13 empty] | NM | N | ENPHASE ENERGY M-250 (50) | 2014-12-03 | 2014-12-12 | 7 | 2014-12-12 | [14 empty] | 2015-05-20 | 2015-05-28 |  | Y
Central Hudson |  | Direct Energy Solar | CH-01034 | Kingston | Woodbourne | Sullivan | 12788 | G | 3091 | Neversink | N |  | 12.04 | [13 empty] | NM | N | 56 ENPHASE M215-60-2LL-S22 | 2014-12-03 | 2014-12-10 | 5 | 2014-12-10 | [8 empty] | 350 | 350 |  |  |  |  | 2015-02-27 | 2015-03-06 |  | Y
Central Hudson |  | OnForce Solar | CH-02800 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6051 | Todd Hill | N |  | 8 | [13 empty] | NM | N | 2 - SMA SB-4000TL | 2014-12-03 | 2014-12-09 | 4 | 2014-12-09 | [14 empty] | 2015-04-23 | 2015-04-23 |  | Y
Central Hudson |  | SolarCity | CH-05154 | Newburgh | Highland | Ulster | 12528 | G | 5081 | Highland | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A | 2014-12-03 | 2014-12-09 | 4 | 2014-12-09 | [14 empty] | 2015-01-06 | 2015-01-13 |  | Y
Central Hudson |  | SolarCity | CH-06330 | Newburgh | Marlboro | Ulster | 12542 | G | 5003 | Marlboro | N |  | 10 | [13 empty] | NM | N | SOLAREDGE SE5000A (2) | 2014-12-03 | 2014-12-12 | 7 | 2014-12-12 | [14 empty] | 2015-01-23 | 2015-01-30 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07774 | Newburgh | Newburgh | Orange | 12550 | G | 4053 | Union Ave | N |  | 3 | [13 empty] | NM | N | SOLAREDGE SE3000A (1) | 2014-12-03 | 2014-12-12 | 7 | 2014-12-12 | [14 empty] | 2015-02-10 | 2015-02-10 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Sungevity Inc | CH-09252 | Poughkeepsie | Pine Plns | Dutchess | 12567 | G | 7091 | Pulvers Corners | N |  | 8 | [13 empty] | NM | N | 1 - SMA AMERICA SB5000TL-US 1 - SMA AMERICA SB3000TL-US | 2015-01-12 | 2015-01-19 | 5 | 2015-01-19 | [14 empty] | 2015-01-22 | 2015-01-29 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Verengo Solar | CH-09886 | Newburgh | Salisbury Mls | Orange | 12577 | G | 4097 | Bethlehem Rd | N |  | 6.665 | [13 empty] | NM | N | ENPHASE ENERGY M215 (31) | 2014-12-03 | 2014-12-12 | 7 | 2014-12-12 | [14 empty] | 2015-03-13 | 2015-03-20 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-03420 | Newburgh | Newburgh | Orange | 12550 | G | 5041 | East Walden | N |  | 6 | [13 empty] | NM | N | SMA SB6000 (1) | 2014-12-04 | 2014-12-12 | 6 | 2014-12-12 | [14 empty] | 2015-03-24 | 2015-03-31 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03634 | Newburgh | Gardiner | Ulster | 12525 | G | 5031 | Galeville | N |  | 11.4 | [13 empty] | NM | N | SOLAREDGE SE 11.4 (1) | 2014-12-04 | 2014-12-12 | 6 | 2014-12-12 | [8 empty] | 350 | 350 |  |  |  |  | 2015-07-06 | 2015-07-07 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03793 | Newburgh | Wallkill | Ulster | 12589 | G | 5033 | Galeville | N |  | 15.2 | [13 empty] | NM | N | SOLAREDGE SE7600 (2) | 2014-12-04 | 2014-12-18 | 10 | 2014-12-18 | [8 empty] | 350 | 350 |  |  |  |  | 2015-12-01 | 2015-12-01 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03815 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6068 | Inwood Ave | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000 | 2014-12-04 | 2014-12-10 | 4 | 2014-12-10 | [14 empty] | 2015-07-07 | 2015-07-14 |  | Y
Central Hudson |  | SolarCity | CH-06028 | Fishkill | Wappingrs Falls |  | 12590 | G | 8052 | North Chelsea | TBD |  | 12 | [13 empty] | NM | N | SOLAREDGE SE6000A (2) | 2014-12-04 | 2014-12-12 | 6 | 2014-12-12 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | SolarCity | CH-06863 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8092 | Fishkill Plains | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000 (1) | 2014-12-04 | 2014-12-12 | 6 | 2014-12-12 | [14 empty] | 2015-01-05 | 2015-01-12 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-03380 | Newburgh | Newburgh | Orange | 12550 | G | 4011 | West Balmville | N |  | 5 | [13 empty] | NM | N | SMA AMERICA SB5000 (1) | 2014-12-05 | 2014-12-12 | 5 | 2014-12-12 | [14 empty] | 2015-05-06 | 2015-05-12 |  | Y
Central Hudson |  | New York State Solar Farm | CH-03964 | Kingston | Accord | Ulster | 12404 | G | 3081 | Kerhonkson | N |  | 16 | [13 empty] | NM | N | 2 POWERONE PVI 5.0 1 POWERONE PVI 6.0 | 2014-12-05 | 2014-12-12 | 5 | 2014-12-12 | [8 empty] | 350 | 350 |  |  |  |  | 2015-04-07 | 2015-04-14 |  | Y
Central Hudson |  | SolarCity | CH-06682 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6073 | East Park | N |  | 6.6 | [13 empty] | NM | N | 1 - ABB PVI-3.6-OUTD 1 - ABB PVI-3.0-OUTD | 2014-12-05 | 2014-12-11 | 4 | 2014-12-11 | [14 empty] | 2015-02-04 | 2015-02-11 |  | Y
Central Hudson |  | Sungevity Inc | CH-09246 | Newburgh | Highland | Ulster | 12528 | G | 5083 | Highland | N |  | 6 | [13 empty] | NM | N | SMA AMERICA SB6000TL-US-22 | 2014-12-05 | 2014-12-11 | 4 | 2014-12-11 | [14 empty] | 2015-01-05 | 2015-01-12 |  | Y
Central Hudson |  | Verengo Solar | CH-09770 | Newburgh | Newburgh | Orange | 12550 | G | 4023 | Coldenham | N |  | 4.945 | [13 empty] | NM | N | ENPHASE ENERGY M215 (23) | 2014-12-05 | 2014-12-12 | 5 | 2014-12-12 | [14 empty] | 2015-04-14 | 2015-04-21 |  | Y
Central Hudson |  | Kirchhoff Green Energy LLC | CH-03555 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6092 | Manchester | N |  | 15 | [13 empty] | NM | N | 2 - FRONIUS IG PLUS 7.5 | 2014-12-08 | 2014-12-15 | 5 | 2014-12-15 | [14 empty] | 2014-12-15 | 2014-12-15 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | NRG Home Solar | CH-04655 | Newburgh | Newburgh | Orange | 12550 | G | 5001 | Marlboro | N |  | 5.5 | [13 empty] | NM | N | ENPHASE ENERGY M-250 (22) | 2014-12-08 | 2014-12-19 | 9 | 2014-12-19 | [14 empty] | 2015-04-14 | 2015-04-21 |  | Y
Central Hudson |  | NRG Home Solar | CH-04758 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6003 | Reynolds Hill | N |  | 3.655 | [13 empty] | NM | N | 17 - ENPHASE ENERGY M-215 | 2014-12-08 | 2014-12-11 | 3 | 2014-12-11 | [14 empty] | 2015-06-10 | 2015-06-17 |  | Y
Central Hudson |  | NRG Home Solar | CH-04839 | Newburgh | Marlboro |  | 12542 | G | 5004 | Marlboro | TBD |  | 9 | [13 empty] | NM | N | ENPHASE ENERGY M-250 (36) | 2014-12-08 | 2014-12-19 | 9 | 2014-12-19 | [8 empty] | 350 | 350 | [7 empty] | W
Central Hudson |  | OnForce Solar | CH-02810 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 5 | [13 empty] | NM | N | SMA SB-5000TL (1) | 2014-12-08 | 2014-12-19 | 9 | 2014-12-19 | [14 empty] | 2015-05-14 | 2015-05-14 |  | Y
Central Hudson |  | NRG Home Solar | CH-04160 | Fishkill | Hopewell Jct |  | 12533 | G | 8095 | Fishkill Plains | TBD |  | 6.02 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (28) | 2014-12-09 | 2014-12-22 | 9 | 2014-12-22 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | NRG Home Solar | CH-04198 | Newburgh | Campbell Hall |  | 10916 | G | 5051 | Maybrook | TBD |  | 7.5 | [13 empty] | NM | N | ENPHASE ENERGY M-250 (30) | 2014-12-09 | 2014-12-22 | 9 | 2014-12-22 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | NRG Home Solar | CH-04426 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8071 | Shenandoah | N |  | 7.31 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (34) | 2014-12-09 | 2014-12-22 | 9 | 2014-12-22 | [14 empty] | 2015-06-29 | 2015-07-07 |  | Y
Central Hudson |  | NRG Home Solar | CH-04508 | Newburgh | Campbell Hall |  | 10916 | G | 5052 | Maybrook | TBD |  | 9.675 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (45) | 2014-12-09 | 2014-12-22 | 9 | 2014-12-22 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | NRG Home Solar | CH-04510 | Newburgh | Campbell Hall |  | 10916 | G | 5051 | Maybrook | TBD |  | 7.31 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (34) | 2014-12-09 | 2014-12-22 | 9 | 2014-12-22 | [17 empty] | W
Central Hudson |  | SolarCity | CH-05549 | Catskill | Earlton | Greene | 12058 | G | 2005 | North Catskill | N |  | 11 | [13 empty] | NM | N | (1)ABB PVI-6000-OUTD-US 1 ABB PVI-6000-OUTD-US 1 ABB PVI-5000-OUTD-US | 2014-12-09 | 2014-12-16 | 5 | 2014-12-16 | [8 empty] | 350 | 350 |  |  |  |  | 2015-08-03 | 2015-08-10 |  | Y
Central Hudson |  | SolarCity | CH-05867 | Poughkeepsie | Staatsburg |  | 12580 | G | 7041 | Staatsburg | TBD |  | 5 | [13 empty] | NM | N | ABB PVI-5000 | 2014-12-15 | 2014-12-23 | 6 | 2014-12-23 | [14 empty] | 2015-04-27 | 2015-05-04 |  | W |  | Customer already had net meter prior to application.
Central Hudson |  | SolarCity | CH-05894 | Poughkeepsie | Lagrangevl | Dutchess | 12540 | G | 6055 | Todd Hill | N |  | 9.8 | [13 empty] | NM | N | 1 - SOLAREDGE SE6000A 1 - SOLAREDGE SE3800A | 2014-12-09 | 2014-12-23 | 10 | 2014-12-23 | [14 empty] | 2015-02-09 | 2015-02-13 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06052 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8096 | Fishkill Plains | N |  | 12 | [13 empty] | NM | N | SOLAREDGE SE6000A (2) | 2014-12-09 | 2014-12-22 | 9 | 2014-12-22 | [14 empty] | 2015-01-30 | 2015-02-06 |  | Y
Central Hudson |  | SolarCity | CH-06696 | Poughkeepsie | Staatsburg | Dutchess | 12580 | G | 7041 | Staatsburg | N |  | 5 | [13 empty] | NM | N | ABB PVI-5000 | 2014-12-15 | 2014-12-23 | 6 | 2014-12-23 | [14 empty] | 2015-04-27 | 2015-05-04 |  | Y
Central Hudson |  | Verengo Solar | CH-09847 | Kingston | Kerhonkson | Ulster | 12446 | G | 3082 | Kerhonkson | N |  | 7.96 | [13 empty] | NM | N | 37 ENPHASE M215-60-2LL-S22-IG | 2014-12-09 | 2014-12-16 | 5 | 2014-12-16 | [14 empty] | 2015-05-01 | 2015-05-08 |  | Y
Central Hudson |  | Verengo Solar | CH-09852 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6046 | Spackenkill | N |  | 5.805 | [13 empty] | NM | N | 27 - ENPHASE ENERGY M215 | 2014-12-09 | 2014-12-22 | 9 | 2014-12-22 | [14 empty] | 2015-06-30 | 2015-07-08 |  | Y
Central Hudson |  | NRG Home Solar | CH-04500 | Newburgh | New Windsor |  | 12553 | G | 4093 | Bethlehem Rd | TBD |  | 7.31 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (34) | 2014-12-10 | 2014-12-22 | 8 | 2014-12-22 | [17 empty] | W
Central Hudson |  | NRG Home Solar | CH-04824 | Fishkill | Poughkeepsie |  | 12601 | G | 8024 | Knapps Corners | TBD |  | 7.095 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (33) | 2014-12-17 | 2015-01-05 | 10 | 2015-01-05 | [17 empty] | W |  | Customer already had net meter prior to application.12/24/14 & 12/25/14 Company Holidays.1/1/15 Company Holidays
Central Hudson |  | Direct Energy Solar | CH-00897 | Kingston | Hurley | Ulster | 12443 | G | 2094 | Hurley Ave | N |  | 12.04 | [13 empty] | NM | N | 56 ENPHASE M215 60-2LL-S22 | 2014-12-10 | 2014-12-17 | 5 | 2014-12-17 | [14 empty] | 2015-04-06 | 2015-04-13 |  | Y
Central Hudson |  | Hudson Solar | CH-01826 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7052 | Rhinebeck | N | CH-01826 | 7 | [13 empty] | NM | N | 1 - SMA AMERICA SB4000 1 - SMA AMERICA SB3000 | 2014-12-10 | 2014-12-23 | 9 | 2014-12-23 | [14 empty] | 2014-12-23 | 2014-12-30 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | OnForce Solar | CH-02806 | Newburgh | Newburgh | Orange | 12550 | G | 4011 | West Balmville | N |  | 6 | [13 empty] | NM | N | SMA SB-6000TL (1) | 2014-12-10 | 2014-12-22 | 8 | 2014-12-22 | [14 empty] | 2015-10-16 | 2015-10-22 |  | Y
Central Hudson |  | SolarCity | CH-06113 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8094 | Fishkill Plains | N |  | 13.6 | [13 empty] | NM | N | SOLAREDGE SE7600A (1) SOLAREDGE SE6000A (1) | 2014-12-23 | 2015-01-07 | 8 | 2015-01-07 | [14 empty] | 2015-03-10 | 2015-03-17 |  | Y
Central Hudson |  | Solar Generation | CH-08268 | Kingston | Bearsvl | Ulster | 12409 | G | 3012 | Woodstock | N |  | 7.7 | [13 empty] | NM | N | SMA SB 7700 TL | 2014-12-10 | 2014-12-17 | 5 | 2014-12-17 | [14 empty] | 2015-03-02 | 2015-03-09 |  | Y
Central Hudson |  | Sungevity Inc | CH-09573 | Newburgh | Highland | Ulster | 12528 | G | 5081 | Highland | N |  | 9.8 | [13 empty] | NM | N | 1 - SMA AMERICA SB6000TL-US 1 - SMA AMERICA SB3800TL-US | 2014-12-10 | 2014-12-23 | 9 | 2014-12-23 | [14 empty] | 2016-01-08 | 2016-01-15 |  | Y
Central Hudson |  | Verengo Solar | CH-09791 | Kingston | Saugerties |  | 12477 | G | 3001 | Saugerties | TBD |  | 4.51 | [13 empty] | NM | N | 21 ENPHASE M215-60-2LL-S22-IG | 2014-12-10 | 2014-12-17 | 5 | 2014-12-17 | [17 empty] | W
Central Hudson |  | Infinity Solar Systems | CH-03463 | Newburgh | Newburgh | Orange | 12550 | G | 4014 | West Balmville | N |  | 6 | [13 empty] | NM | N | SMA AMERICA SB6000 (1) | 2014-12-11 | 2014-12-23 | 8 | 2014-12-23 | [14 empty] | 2015-04-15 | 2015-04-22 |  | Y
Central Hudson |  | Kirchhoff Green Energy LLC | CH-03556 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7051 | Rhinebeck | N |  | 10 | [13 empty] | NM | N | FRONIUS IG PLUS 10.0-1UNI | 2014-12-11 | 2014-12-18 | 5 | 2014-12-18 | [14 empty] | 2015-01-19 | 2015-01-26 |  | Y
Central Hudson |  | NRG Home Solar | CH-04749 | Newburgh | Washingtonvl | Orange | 10992 | G | 5052 | Maybrook | N |  | 3.01 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (14) | 2014-12-11 | 2014-12-23 | 8 | 2014-12-23 | [14 empty] | 2015-10-08 | 2015-10-14 |  | Y
Central Hudson |  | SolarCity | CH-05580 | Catskill | Athens | Greene | 12015 | G | 1074 | Coxsackie | N | CH-05580 | 11.4 | [13 empty] | NM | N | SOLAREDGE SE7600A US-ZB-U SOLAREDGE SE3800AUS-ZB-U | 2014-12-11 | 2014-12-18 | 5 | 2014-12-18 | [14 empty] | 2015-05-05 | 2015-05-18 |  | Y
Central Hudson |  | SolarCity | CH-05585 | Catskill | Coxsackie | Greene | 12051 | G | 1076 | Coxsackie | N | CH-05585 | 3 | [13 empty] | NM | N | SOLAREDGE SE3000A US-ZB-U | 2014-12-11 | 2014-12-18 | 5 | 2014-12-18 | [14 empty] | 2015-03-24 | 2015-03-30 |  | Y
Central Hudson |  | SolarCity | CH-06350 | Newburgh | Wallkill | Ulster | 12589 | G | 5043 | East Walden | N |  | 9 | [13 empty] | NM | N | ABB PVI-6000 (1) ABB PVI-3.0 (1) | 2014-12-11 | 2014-12-23 | 8 | 2014-12-23 | [14 empty] | 2015-01-21 | 2015-01-28 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL. Customer already had net meter prior to application.
Central Hudson |  | SolarCity | CH-06587 | Kingston | Saugerties | Ulster | 12477 | G | 2016 | Lincoln Park | N |  | 7.6 | [13 empty] | NM | N | 2 SOLAREDGE SE3800A US-ZB-U | 2014-12-11 | 2014-12-18 | 5 | 2014-12-18 | [14 empty] | 2015-01-26 | 2015-02-02 |  | Y
Central Hudson |  | SolarCity | CH-06629 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6043 | Spackenkill | N |  | 3 | [13 empty] | NM | N | ABB PVI-3.0-OUTD | 2014-12-11 | 2014-12-18 | 5 | 2014-12-18 | [14 empty] | 2015-02-02 | 2015-02-09 |  | Y
Central Hudson |  | SolarCity | CH-06848 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8096 | Fishkill Plains | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A (1) | 2014-12-11 | 2014-12-23 | 8 | 2014-12-23 | [14 empty] | 2015-01-28 | 2015-02-04 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07035 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A (1) | 2014-12-11 | 2014-12-23 | 8 | 2014-12-23 | [14 empty] | 2015-06-29 | 2015-07-07 |  | Y
Central Hudson |  | SolarCity | CH-07416 | Newburgh | New Windsor | Orange | 12553 | G | 4054 | Union Ave | N |  | 3 | [13 empty] | NM | N | SOLAREDGE SE3000A (1) | 2014-12-11 | 2014-12-23 | 8 | 2014-12-23 | [14 empty] | 2015-01-28 | 2015-02-04 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Sol Providers | CH-08931 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8091 | Fishkill Plains | N |  | 11 | [13 empty] | NM | N | POWER ONE 5 (1) POWER ONE 6 (1) | 2014-12-11 | 2014-12-23 | 8 | 2014-12-23 | [14 empty] | 2015-01-15 | 2015-01-22 |  | Y
Central Hudson |  | Sungevity Inc | CH-09439 | Newburgh | Highland |  | 12528 | G | 5082 | Highland | TBD |  | 7.6 | [13 empty] | NM | N | 2 - SMA AMERICA SB3800TL | 2014-12-11 | 2014-12-18 | 5 | 2014-12-18 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | NRG Home Solar | CH-04511 | Newburgh | Campbell Hall | Orange | 10916 | G | 5051 | Maybrook | N |  | 3.75 | [13 empty] | NM | N | ENPHASE ENERGY M-250 (15) | 2014-12-12 | 2014-12-29 | 9 | 2014-12-29 | [14 empty] | 2016-01-07 | 2016-01-13 |  | Y
Central Hudson |  | NRG Home Solar | CH-04542 | Poughkeepsie | Poughkeepsie |  | 12603 | G | 6046 | Spackenkill | TBD |  | 7.75 | [13 empty] | NM | N | 31 - ENPHASE ENERGY M-250 | 2014-12-12 | 2014-12-22 | 6 | 2014-12-22 | [17 empty] | W
Central Hudson |  | SolarCity | CH-06088 | Fishkill | Fishkill | Dutchess | 12524 | G | 8094 | Fishkill Plains | N |  | 3 | [13 empty] | NM | N | ABB PVI-3.0 (1) | 2014-12-12 | 2014-12-29 | 9 | 2014-12-29 | [14 empty] | 2015-02-02 | 2015-02-09 |  | Y
Central Hudson |  | SolarCity | CH-07425 | Newburgh | Newburgh | Orange | 12550 | G | 4023 | Coldenham | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE7600A (1) | 2014-12-12 | 2014-12-29 | 9 | 2014-12-29 | [14 empty] | 2015-02-06 | 2015-02-19 |  | Y
Central Hudson |  | SolarCity | CH-07577 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8051 | North Chelsea | N |  | 6.8 | [13 empty] | NM | N | SOLAREDGE SE3800A (1) SOLAREDGE SE3000A (1) | 2014-12-12 | 2014-12-23 | 7 | 2014-12-23 | [14 empty] | 2015-01-29 | 2015-02-05 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Verengo Solar | CH-09832 | Newburgh | Newburgh | Orange | 12550 | G | 5004 | Marlboro | N |  | 5.805 | [13 empty] | NM | N | ENPHASE ENERGY M215 (27) | 2014-12-12 | 2014-12-23 | 7 | 2014-12-23 | [14 empty] | 2015-03-30 | 2015-04-07 |  | Y
Central Hudson |  | Conscious Energy | CH-00789 | Kingston | Olive Brdg | Ulster | 12461 | G | 3023 | High Falls | N |  | 10 | [13 empty] | NM | N | 40 ENPHASE ENERGY M250 | 2014-12-15 | 2014-12-22 | 5 | 2014-12-22 | [14 empty] | 2015-05-26 | 2015-06-02 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00908 | Kingston | Grahamsvl | Sullivan | 12740 | G | 3091 | Neversink | N |  | 4.52 | [13 empty] | NM | N | 21 ENPHASE M215 60-2LL-S22 | 2014-12-15 | 2014-12-22 | 5 | 2014-12-22 | [14 empty] | 2015-04-16 | 2015-04-23 |  | Y
Central Hudson |  | SolarCity | CH-05259 | Poughkeepsie | Stanfordvl | Dutchess | 12581 | G | 7072 | Stanfordville | N |  | 3 | [13 empty] | NM | N | SOLAREDGE SE3000A-US | 2014-12-15 | 2014-12-22 | 5 | 2014-12-22 | [14 empty] | 2015-06-24 | 2015-07-01 |  | Y
Central Hudson |  | SolarCity | CH-05642 | Kingston | High Fls | Ulster | 12440 | G | 3022 | High Falls | N |  | 4.2 | [13 empty] | NM | N | ABB PVI-3.0-OUTD-S-US Z | 2014-12-15 | 2014-12-22 | 5 | 2014-12-22 | [14 empty] | 2015-06-29 | 2015-07-06 |  | Y
Central Hudson |  | SolarCity | CH-05833 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7053 | Rhinebeck | N | CH-05833 | 5 | [13 empty] | NM | N | ABB PVI-5000-OUTD-US | 2014-12-15 | 2014-12-22 | 5 | 2014-12-22 | [14 empty] | 2015-05-20 | 2015-05-28 |  | Y
Central Hudson |  | SolarCity | CH-05959 | Poughkeepsie | Milan | Dutchess | 12571 | G | 7062 | Milan | N |  | 3 | [13 empty] | NM | N | SOLAREDGE SE3000A | 2014-12-15 | 2014-12-22 | 5 | 2014-12-22 | [14 empty] | 2015-06-22 | 2015-06-29 |  | Y
Central Hudson |  | SolarCity | CH-06064 | Fishkill | Hopewell Jct |  | 12533 | G | 8094 | Fishkill Plains | TBD |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A-US (1) | 2014-12-15 | 2014-12-29 | 8 | 2014-12-29 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | SolarCity | CH-06832 | Fishkill | Poughkeepsie | Dutchess | 12601 | G | 8021 | Knapps Corners | N |  | 11 | [13 empty] | NM | N | SOLAREDGE SE5000A (1) SOLAREDGE SE6000A (1) | 2014-12-15 | 2014-12-29 | 8 | 2014-12-29 | [14 empty] | 2015-03-02 | 2015-03-09 |  | Y
Central Hudson |  | SolarCity | CH-04963 | Kingston | W Shokan | Ulster | 12494 | G | 3011 | Woodstock | N |  | 6 | [13 empty] | NM | N | 2 ABB PVI-3.0-OUTD-S US-Z-A | 2014-12-16 | 2014-12-23 | 5 | 2014-12-23 | [14 empty] | 2015-06-22 | 2015-06-29 |  | Y
Central Hudson |  | SolarCity | CH-04987 | Catskill | W Coxsackie | Greene | 12192 | G | 1083 | New Baltimore | N |  | 9.2 | [13 empty] | NM | N | ABB PVI-5000-OUTD US-Z-A ABB PVI-4.2-OUTD-S US-Z-A | 2014-12-16 | 2014-12-23 | 5 | 2014-12-23 | [14 empty] | 2015-03-23 | 2015-03-30 |  | Y
Central Hudson |  | New York State Solar Farm | CH-03962 | Newburgh | Wallkill | Ulster | 12589 | G | 5041 | East Walden | N |  | 12 | [13 empty] | NM | N | SMA AMERICA SB 6000 (2) | 2014-12-29 | 2015-01-05 | 4 | 2015-01-05 | [14 empty] | 2015-03-25 | 2015-04-01 |  | Y
Central Hudson |  | SolarCity | CH-05403 | Newburgh | Newburgh | Orange | 12550 | G | 4023 | Coldenham | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A (1) | 2015-01-05 | 2015-01-19 | 10 | 2015-01-19 | [14 empty] | 2015-01-22 | 2015-01-29 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-05802 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6095 | Manchester | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000 | 2014-12-17 | 2014-12-23 | 4 | 2014-12-23 | [14 empty] | 2015-02-04 | 2015-02-11 |  | Y
Central Hudson |  | SolarCity | CH-05863 | Poughkeepsie | Staatsburg | Dutchess | 12580 | G | 7041 | Staatsburg | N |  | 7.5 | [13 empty] | NM | N | FRONIUS IG PLUS A 7.5 | 2014-12-17 | 2014-12-22 | 3 | 2014-12-22 | [14 empty] | 2015-03-09 | 2015-03-16 |  | Y
Central Hudson |  | SolarCity | CH-06079 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8092 | Fishkill Plains | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A (1) | 2014-12-17 | 2015-01-05 | 10 | 2015-01-05 | [14 empty] | 2015-02-02 | 2015-02-09 |  | Y
Central Hudson |  | SolarCity | CH-06192 | Newburgh | Newburgh | Orange | 12550 | G | 4013 | West Balmville | N |  | 9 | [13 empty] | NM | N | ABB PVI-6000 ABB PVI-3.0 | 2014-12-17 | 2015-01-05 | 10 | 2015-01-05 | [14 empty] | 2015-04-07 | 2015-04-14 |  | Y
Central Hudson |  | SolarCity | CH-06314 | Newburgh | Newburgh | Orange | 12550 | G | 4011 | West Balmville | N |  | 7.8 | [13 empty] | NM | N | ABB PVI-4.2 ABB PVI-3.6 | 2014-12-17 | 2015-01-05 | 10 | 2015-01-05 | [14 empty] | 2015-02-02 | 2015-02-09 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06721 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6057 | Todd Hill | N |  | 6.8 | [13 empty] | NM | N | 1 - SOLAREDGE SE3000A 1 - SOLAREDGE SE3800A | 2014-12-17 | 2014-12-22 | 3 | 2014-12-22 | [14 empty] | 2015-01-09 | 2015-01-16 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07299 | Poughkeepsie | Clinton Corners | Dutchess | 12514 | G | 7071 | Stanfordville | N |  | 7.2 | [13 empty] | NM | N | 2 - ABB PVI 3.6 | 2015-05-07 | 2015-05-14 | 5 | 2015-05-14 | [14 empty] | 2015-05-15 | 2015-05-22 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07349 | Fishkill | Poughkeepsie | Dutchess | 12601 | G | 8024 | Knapps Corners | N |  | 3.8 | [13 empty] | NM | N | SOLAREDGE SE3800A (1) | 2014-12-17 | 2015-01-05 | 10 | 2015-01-05 | [14 empty] | 2015-01-12 | 2015-01-19 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07462 | Newburgh | Wallkill | Ulster | 12589 | G | 5043 | East Walden | N |  | 3.6 | [13 empty] | NM | N | ABB PVI-3.6 | 2014-12-17 | 2015-01-05 | 10 | 2015-01-05 | [14 empty] | 2015-02-11 | 2015-02-19 |  | Y
Central Hudson |  | SolarCity | CH-07876 | Poughkeepsie | Hyde Pk |  | 12538 | G | 6075 | East Park | TBD |  | 9 | [13 empty] | NM | N | 1 - ABB PVI-6000 1 - ABB PVI-3.0 | 2014-12-17 | 2014-12-23 | 4 | 2014-12-23 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | Sungevity Inc | CH-09329 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7054 | Rhinebeck | N |  | 3.8 | [13 empty] | NM | N | SMA AMERICA SB3800TL-US | 2014-12-17 | 2014-12-23 | 4 | 2014-12-23 | [14 empty] | 2015-03-16 | 2015-03-23 |  | Y
Central Hudson |  | Verengo Solar | CH-09767 | Fishkill | Hopewell Jct |  | 12533 | G | 8072 | Shenandoah | TBD |  | 4.73 | [13 empty] | NM | N | ENPHASE ENERGY M215 (22) | 2014-12-17 | 2015-01-05 | 10 | 2015-01-05 | [17 empty] | W |  | Customer already had net meter prior to application.12/24/14 & 12/25/14 Company Holidays.1/1/15 Company Holidays
Central Hudson |  | Infinity Solar Systems | CH-03430 | Newburgh | Newburgh | Orange | 12550 | G | 4015 | West Balmville | N |  | 8 | [13 empty] | NM | N | SMA AMERICA SB8000US (1) | 2014-12-18 | 2015-01-05 | 9 | 2015-01-05 | [14 empty] | 2015-04-09 | 2015-04-16 |  | Y
Central Hudson |  | NRG Home Solar | CH-04135 | Newburgh | Wallkill | Ulster | 12589 | G | 4011 | West Balmville | N |  | 5.805 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (27) | 2014-12-29 | 2015-01-05 | 4 | 2015-01-05 | [14 empty] | 2015-08-27 | 2015-09-03 |  | Y
Central Hudson |  | Autonomous Energies LLC | CH-00745 | Kingston | Boicevl | Ulster | 12412 | G | 3012 | Woodstock | N |  | 4 | [13 empty] | NM | N | SMA SB 4000TL 22 | 2014-12-18 | 2014-12-29 | 5 | 2014-12-29 | [14 empty] | 2015-04-22 | 2015-04-29 |  | Y
Central Hudson |  | Autonomous Energies LLC | CH-00746 | Kingston | Boicevl | Columbia | 12526 | G | 3012 | Woodstock | N |  | 5 | [13 empty] | NM | N | SMA SB5000 TL-US | 2014-12-18 | 2014-12-29 | 5 | 2014-12-29 | [14 empty] | 2015-04-22 | 2015-04-29 |  | Y
Central Hudson |  | Autonomous Energies LLC | CH-00747 | Kingston | Boicevl | Ulster | 12412 | G | 3012 | Woodstock | N |  | 6 | [13 empty] | NM | N | SMA SB6000TL 22 | 2014-12-18 | 2014-12-29 | 5 | 2014-12-29 | [14 empty] | 2015-04-22 | 2015-04-29 |  | Y
Central Hudson |  | NRG Home Solar | CH-04647 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 3.655 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (17) | 2014-12-19 | 2015-01-06 | 9 | 2015-01-06 | [14 empty] | 2015-04-14 | 2015-04-21 |  | Y
Central Hudson |  | NRG Home Solar | CH-04741 | Newburgh | Newburgh | Orange | 12550 | G | 4024 | Coldenham | N |  | 6.02 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (28) | 2014-12-19 | 2015-01-06 | 9 | 2015-01-06 | [14 empty] | 2015-06-02 | 2015-06-09 |  | Y
Central Hudson |  | SolarCity | CH-07246 | Kingston | Lk Katrine | Ulster | 12449 | G | 2016 | Lincoln Park | N | CH-07246 | 7.6 | [13 empty] | NM | N | SOLAREDGE SE7600A US-ZB-U | 2014-12-19 | 2014-12-31 | 6 | 2014-12-31 | [14 empty] | 2015-01-12 | 2015-01-19 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Verengo Solar | CH-09806 | Fishkill | Poughkeepsie | Dutchess | 12601 | G | 8022 | Knapps Corners | N |  | 11.395 | [13 empty] | NM | N | ENPHASE ENERGY M215 (53) | 2014-12-19 | 2015-01-06 | 9 | 2015-01-06 | [14 empty] | 2015-05-13 | 2015-05-19 |  | Y
Central Hudson |  | Verengo Solar | CH-09810 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8092 | Fishkill Plains | N |  | 9.89 | [13 empty] | NM | N | ENPHASE ENERGY M215 (46) | 2014-12-19 | 2015-01-06 | 9 | 2015-01-06 | [14 empty] | 2015-04-27 | 2015-05-01 |  | Y
Central Hudson |  | Verengo Solar | CH-09826 | Newburgh | Wallkill | Ulster | 12589 | G | 5013 | Modena | N |  | 8.17 | [13 empty] | NM | N | ENPHASE ENERGY M215 (38) | 2014-12-19 | 2015-01-06 | 9 | 2015-01-06 | [14 empty] | 2015-05-13 | 2015-05-18 |  | Y
Central Hudson |  | Verengo Solar | CH-09898 | Poughkeepsie | Poughkeepsie |  | 12603 | G | 6061 | Inwood Ave | TBD |  | 3.655 | [13 empty] | NM | N | 17 - ENPHASE ENERGY M215 | 2014-12-19 | 2014-12-23 | 2 | 2014-12-23 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | SolarCity | CH-05809 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6046 | Spackenkill | N |  | 6.6 | [13 empty] | NM | N | 1 - ABB PVI-3.6 1 - ABB PVI-3.0 | 2014-12-22 | 2014-12-30 | 4 | 2014-12-30 | [14 empty] | 2015-02-11 | 2015-02-19 |  | Y
Central Hudson |  | SolarCity | CH-06253 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 3 | [13 empty] | NM | N | ABB PVI-3.0 (1) | 2014-12-22 | 2015-01-06 | 8 | 2015-01-06 | [14 empty] | 2015-02-19 | 2015-02-26 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07889 | Fishkill | Wappingrs Falls |  | 12590 | G | 8046 | Myers Corners | TBD |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A (1) | 2014-12-22 | 2015-01-06 | 8 | 2015-01-06 | [17 empty] | W |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL. 12/24/14, 12/25/14 & 1/1/15 Company Holidays.
Central Hudson |  | SolarCity | CH-07909 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 3 | [13 empty] | NM | N | ABB PVI-3.0 | 2014-12-22 | 2015-01-06 | 8 | 2015-01-06 | [14 empty] | 2015-01-21 | 2015-01-28 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | New York State Solar Farm | CH-00374 | Newburgh | Rock Tvrn | Orange | 12575 | G | 4097 | Bethlehem Rd | N | CH-00374 | 10 | [13 empty] | NM | N | SMA AMERIC SB-TL 5.0 (2) | 2014-12-23 | 2015-01-07 | 8 | 2015-01-07 | [14 empty] | 2016-06-21 | 2016-06-24 |  | Y
Central Hudson |  | New York State Solar Farm | CH-04008 | Newburgh | Milton | Ulster | 12547 | G | 5083 | Highland | N |  | 6 | [13 empty] | NM | N | SMA AMERICA SB-TL 6.0 (1) | 2014-12-23 | 2015-01-07 | 8 | 2015-01-07 | [14 empty] | 2015-03-03 | 2015-03-10 |  | Y
Central Hudson |  | SolarCity | CH-04980 | Catskill | Leeds | Greene | 12451 | G | 2006 | North Catskill | N |  | 3 | [13 empty] | NM | N | ABB PVI-3.0 (1) | 2014-12-23 | 2015-01-02 | 5 | 2015-01-02 | [14 empty] | 2015-03-02 | 2015-03-09 |  | Y
Central Hudson |  | SolarCity | CH-05964 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7062 | Milan | N |  | 8.8 | [13 empty] | NM | N | 1 - SOLAREDGE SE5000A 1 - SOLAREDGE SE3800A | 2014-12-23 | 2015-01-09 | 10 | 2015-01-09 | [14 empty] | 2015-02-02 | 2015-02-09 |  | Y
Central Hudson |  | SolarCity | CH-06703 | Poughkeepsie | Lagrangevl | Dutchess | 12540 | G | 6053 | Todd Hill | N |  | 3.8 | [13 empty] | NM | N | Aurora Power-One PVI-3.8 | 2015-01-02 | 2015-01-09 | 5 | 2015-01-09 | [14 empty] | 2015-03-02 | 2015-03-09 |  | Y
Central Hudson |  | SolarCity | CH-06950 | Fishkill | Beacon | Dutchess | 12508 | G | 8087 | Tioronda | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000 (1) | 2014-12-23 | 2015-01-07 | 8 | 2015-01-07 | [14 empty] | 2015-03-31 | 2015-04-08 |  | Y
Central Hudson |  | SolarCity | CH-07547 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6052 | Todd Hill | N |  | 3.8 | [13 empty] | NM | N | SOLAREDGE SE3800A | 2014-12-23 | 2014-12-30 | 3 | 2014-12-30 | [14 empty] | 2015-01-26 | 2015-02-02 |  | Y
Central Hudson |  | Sungevity Inc | CH-09275 | Kingston | High Fls | Ulster | 12440 | G | 3023 | High Falls | N |  | 6 | [13 empty] | NM | N | 2 SMA AMERICA SB3000TL-US-22 | 2014-12-23 | 2014-12-30 | 3 | 2014-12-30 | [14 empty] | 2015-02-10 | 2015-02-18 |  | Y
Central Hudson |  | Sungevity Inc | CH-09288 | Kingston | Kingston | Ulster | 12401 | G | 2093 | Hurley Ave | N |  | 5 | [13 empty] | NM | N | SMA AMERICA SB5000TL-US-22 | 2014-12-23 | 2014-12-30 | 3 | 2014-12-30 | [14 empty] | 2015-04-21 | 2015-04-28 |  | Y
Central Hudson |  | Sungevity Inc | CH-09441 | Newburgh | Highland |  | 12528 | G | 5082 | Highland | TBD |  | 5 | [13 empty] | NM | N | SOLAREDGE SE 5000A-US | 2014-12-23 | 2014-12-30 | 3 | 2014-12-30 | [17 empty] | W
Central Hudson |  | Hudson Solar | CH-01368 | Newburgh | New Paltz | Ulster | 12561 | G | 5031 | Galeville | N |  | 40 | [13 empty] | NM | N | SMA AMERICA SB11000 (3) SMA AMERICA SB7000 (1) | 2015-01-19 | 2015-02-02 | 10 | 2015-02-02 | [8 empty] | 2100 | 1261.75 |  |  |  |  | 2016-11-29 | 2016-11-29 |  | Y
Central Hudson |  | Hudson Solar | CH-02527 | Newburgh | New Paltz |  | 12561 | G | 5031 | Galeville | TBD |  | 29.7 | [13 empty] | NM | N | SMA AMERICA SB11000 (2) SMA AMERICA SB7700 (1) | 2015-01-08 | 2015-01-22 | 10 | 2015-01-22 | [15 empty] | 2015-07-21 |  | W |  | 12/24/14, 12/25/14 & 1/1/15 Company Holidays.
Central Hudson |  | SolarCity | CH-05286 | Newburgh | Walden | Orange | 12586 | G | 5041 | East Walden | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A (1) | 2014-12-26 | 2015-01-12 | 10 | 2015-01-12 | [14 empty] | 2015-01-23 | 2015-01-30 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06043 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8043 | Myers Corners | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE7600A (1) | 2014-12-26 | 2015-01-12 | 10 | 2015-01-12 | [14 empty] | 2015-02-23 | 2015-03-02 |  | Y
Central Hudson |  | SolarCity | CH-07669 | Fishkill | Beacon | Dutchess | 12508 | G | 8085 | Tioronda | N |  | 3 | [13 empty] | NM | N | ABB PVI-3.0 (1) | 2014-12-26 | 2015-01-12 | 10 | 2015-01-12 | [14 empty] | 2015-02-02 | 2015-02-10 |  | Y
Central Hudson |  | Sungevity Inc | CH-09202 | Newburgh | Montgomery | Orange | 12549 | G | 5073 | Montgomery | N |  | 6 | [13 empty] | NM | N | SMA SB 6000 (1) | 2014-12-26 | 2015-01-12 | 10 | 2015-01-12 | [14 empty] | 2015-03-13 | 2015-03-20 |  | Y
Central Hudson |  | Verengo Solar | CH-09799 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6073 | East Park | N |  | 4.945 | [13 empty] | NM | N | 23 - ENPHASE ENERGY M215 | 2014-12-26 | 2015-01-05 | 5 | 2015-01-05 | [14 empty] | 2015-03-27 | 2015-04-06 |  | Y
Central Hudson |  | Verengo Solar | CH-09809 | Fishkill | Wappingrs Falls |  | 12590 | G | 8092 | Fishkill Plains | TBD |  | 9.245 | [13 empty] | NM | N | ENPHASE ENERGY M215 (43) | 2014-12-26 | 2015-01-12 | 10 | 2015-01-12 | [17 empty] | W |  | Customer already had net meter prior to application. 12/24/14, 12/25/14 & 1/1/15 Company Holidays.
Central Hudson |  | Verengo Solar | CH-09829 | Newburgh | Newburgh | Orange | 12550 | G | 4012 | West Balmville | N |  | 12.9 | [13 empty] | NM | N | ENPHASE ENERGY M215 (60) | 2014-12-26 | 2015-01-12 | 10 | 2015-01-12 | [14 empty] | 2015-06-05 | 2015-06-12 |  | Y
Central Hudson |  | Verengo Solar | CH-09841 | Newburgh | Cornwall | Orange | 12518 | G | 4093 | Bethlehem Rd | N |  | 14.83 | [13 empty] | NM | N | ENPHASE ENERGY M215 (69) | 2014-12-26 | 2015-01-12 | 10 | 2015-01-12 | [14 empty] | 2015-05-08 | 2015-05-13 |  | Y
Central Hudson |  | Verengo Solar | CH-09849 | Kingston | Kingston | Ulster | 12401 | G | 111 | South Wall St | N |  | 6.67 | [13 empty] | NM | N | 31 ENPHASE M215-60-2LL-S22-IG | 2014-12-26 | 2015-01-05 | 5 | 2015-01-05 | [14 empty] | 2015-04-08 | 2015-04-15 |  | Y
Central Hudson |  | Verengo Solar | CH-09861 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8091 | Fishkill Plains | N |  | 6.02 | [13 empty] | NM | N | ENPHASE ENERGY M215 (28) | 2014-12-26 | 2015-01-12 | 10 | 2015-01-12 | [14 empty] | 2015-04-15 | 2015-04-22 |  | Y
Central Hudson |  | Verengo Solar | CH-09915 | Newburgh | Wallkill | Ulster | 12589 | G | 5042 | East Walden | N |  | 11.18 | [13 empty] | NM | N | ENPHASE ENERGY M215 (52) | 2014-12-26 | 2015-01-12 | 10 | 2015-01-12 | [14 empty] | 2015-04-27 | 2015-05-01 |  | Y
Central Hudson |  | NRG Home Solar | CH-04146 | Newburgh | Campbell Hall |  | 10916 | G | 5051 | Maybrook | TBD |  | 9.75 | [13 empty] | NM | N | ENPHASE ENERGY M-250 (39) | 2014-12-29 | 2015-01-13 | 10 | 2015-01-13 | [17 empty] | W |  | 1/1/15 Company Holiday.
Central Hudson |  | NRG Home Solar | CH-04152 | Fishkill | Beacon | Dutchess | 12508 | G | 8085 | Tioronda | N |  | 4.73 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (22) | 2014-12-29 | 2015-01-13 | 10 | 2015-01-13 | [14 empty] | 2015-03-23 | 2015-03-30 |  | Y
Central Hudson |  | NRG Home Solar | CH-04633 | Newburgh | Newburgh | Orange | 12550 | G | 5001 | Marlboro | N |  | 5.25 | [13 empty] | NM | N | 21 ENPHASE M-250-60-2LL-S22 | 2014-12-29 | 2015-01-13 | 10 | 2015-01-13 | [14 empty] | 2015-08-27 | 2015-08-31 |  | Y
Central Hudson |  | NRG Home Solar | CH-04731 | Fishkill | Beacon |  | 12508 | G | 8085 | Tioronda | TBD |  | 3.75 | [13 empty] | NM | N | 15 ENPHASE M-250-60-2LL-S22 | 2014-12-29 | 2015-01-13 | 10 | 2015-01-13 | [17 empty] | W |  | Customer already had net meter prior to application. /1/15 Company Holiday
Central Hudson |  | NRG Home Solar | CH-04833 | Newburgh | Newburgh |  | 12550 | G | 4023 | Coldenham | TBD |  | 3.87 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (18) | 2014-12-29 | 2015-01-13 | 10 | 2015-01-13 | [17 empty] | W |  | 1/1/15 Company Holiday.
Central Hudson |  | Natural Energy Solutions | CH-02768 | Kingston | Kingston | Ulster | 12401 | G | 1022 | East Kingston | N |  | 6 | [13 empty] | NM | N | SOLAR EDGE SE6000 US | 2014-12-29 | 2015-01-06 | 5 | 2015-01-06 | [14 empty] | 2015-01-20 | 2015-01-21 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Novel Approaches | CH-02779 | Kingston | Grahamsvl |  | 12740 | G | 3091 | Neversink | N |  | 4 | [13 empty] | NM | N | SMA SB4000 US | 2014-12-29 | 2015-01-06 | 5 | 2015-01-06 | [14 empty] | 2015-02-17 | 2015-02-19 |  | W
Central Hudson |  | SolarCity | CH-05946 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7056 | Rhinebeck | N |  | 7.5 | [13 empty] | NM | N | FRONIUS IG PLUS A 7.5 | 2015-01-07 | 2015-01-21 | 10 | 2015-01-21 | [14 empty] | 2015-02-09 | 2015-02-13 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | New York State Solar Farm | CH-04040 | Newburgh | Marlboro | Ulster | 12542 | G | 5004 | Marlboro | N |  | 13.6 | [13 empty] | NM | N | POWERONE PVI 3.8 (2) POWERONE PVI 6.0 (1) | 2015-01-19 | 2015-01-26 | 5 | 2015-01-26 | [8 empty] | 350 | 350 |  |  |  |  | 2015-04-21 | 2015-04-21 |  | Y
Central Hudson |  | SolarCity | CH-06799 | Fishkill | Hopewell Junction | Dutchess | 12533 | G | 8091 | Fishkill Plains | N |  | 8 | [13 empty] | NM | N | SOLAREDGE SE3000A (1) SOLAREDGE SE5000A (1) | 2014-12-30 | 2015-01-14 | 10 | 2015-01-14 | [14 empty] | 2015-01-15 | 2015-01-22 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07518 | Fishkill | Poughkeepsie |  | 12603 | G | 8022 | Knapps Corners | TBD |  | 8.6 | [13 empty] | NM | N | 1 - ABB PVI-5000 1 - ABB PVI-3.6 | 2014-12-30 | 2015-01-07 | 5 | 2015-01-07 | [17 empty] | W |  | Customer already had net meter prior to application. 1/1/15 Company Holiday.
Central Hudson |  | Verengo Solar | CH-09778 | Newburgh | Highland | Ulster | 12528 | G | 5081 | Highland | N |  | 6.235 | [13 empty] | NM | N | 29 - ENPHASE ENERGY M215 | 2014-12-30 | 2015-01-07 | 5 | 2015-01-07 | [14 empty] | 2015-05-04 | 2015-05-11 |  | Y
Central Hudson |  | NRG Home Solar | CH-04413 | Fishkill | Wappingrs Falls |  | 12590 | G | 8051 | North Chelsea | TBD |  | 4.945 | [13 empty] | NM | N | 23 - ENPHASE ENERGY M-215 | 2014-12-31 | 2015-01-08 | 5 | 2015-01-08 | [17 empty] | W |  | Customer already had net meter prior to application. 1/1/15 Company Holiday.
Central Hudson |  | NRG Home Solar | CH-04601 | Fishkill | Fishkill | Dutchess | 12524 | G | 8094 | Fishkill Plains | N |  | 5.25 | [13 empty] | NM | N | 21 - ENPHASE ENERGY M-250 | 2015-01-16 | 2015-01-23 | 5 | 2015-01-23 | [14 empty] | 2015-04-17 | 2015-04-24 |  | Y
Central Hudson |  | SolarCity | CH-05118 | Kingston | Saugerties | Ulster | 12477 | G | 2015 | Lincoln Park | N |  | 4.2 | [13 empty] | NM | N | ABB PVI-4.2-OUTD-S US-Z-A | 2014-12-31 | 2015-01-15 | 10 | 2015-01-15 | [14 empty] | 2015-04-01 | 2015-04-06 |  | Y
Central Hudson |  | SolarCity | CH-05743 | Kingston | Saugerties | Ulster | 12477 | G | 3001 | Saugerties | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000-OUTD US-Z-A | 2014-12-31 | 2015-01-14 | 9 | 2015-01-14 | [14 empty] | 2015-04-13 | 2015-04-20 |  | Y
Central Hudson |  | SolarCity | CH-06608 | Kingston | Kingston | Ulster | 12401 | G | 2013 | Lincoln Park | N |  | 9.8 | [13 empty] | NM | N | SOLAREDGE SE3800A US-ZB-U SOLAREDGE SE6000A US-ZB-U | 2014-12-31 | 2015-01-14 | 9 | 2015-01-14 | [14 empty] | 2015-01-29 | 2015-02-05 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Sungevity Inc | CH-09360 | Fishkill | Beacon | Dutchess | 12508 | G | 8087 | Tioronda | N |  | 5 | [13 empty] | NM | N | SMA AMERICA SB5000TL-US | 2014-12-31 | 2015-01-08 | 5 | 2015-01-08 | [14 empty] | 2015-03-26 | 2015-04-02 |  | Y
Central Hudson |  | Murphy Solar Power | CH-02762 | Catskill | Cairo | Greene | 12413 | G | 2042 | South Cairo | N |  | 8 | [13 empty] | NM | N | SMA 8000 US | 2015-01-02 | 2015-01-15 | 9 | 2015-01-15 | [14 empty] | 2015-02-10 | 2015-02-18 |  | Y
Central Hudson |  | SolarCity | CH-05862 | Poughkeepsie | Salt Pt | Dutchess | 12578 | G | 7011 | Hibernia | N |  | 3.8 | [13 empty] | NM | N | SOLAREDGE SE3800A-US | 2015-01-02 | 2015-01-09 | 5 | 2015-01-09 | [14 empty] | 2015-01-26 | 2015-02-02 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06739 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6093 | Manchester | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000 | 2015-01-02 | 2015-01-09 | 5 | 2015-01-09 | [14 empty] | 2015-02-05 | 2015-02-12 |  | Y
Central Hudson |  | SolarCity | CH-06866 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8092 | Fishkill Plains | N |  | 10.6 | [13 empty] | NM | N | 1 - SOLAREDGE SE3000A-US 1- SOLAREDGE SE7600A-US | 2015-01-02 | 2015-01-09 | 5 | 2015-01-09 | [14 empty] | 2015-03-02 | 2015-03-09 |  | Y
Central Hudson |  | NRG Home Solar | CH-04110 | Newburgh | Campbell Hall | Orange | 10916 | G | 5052 | Maybrook | N |  | 11.825 | [13 empty] | NM | N | (55) ENPHASE ENERGY M-215-60-2LL-S22-IG | 2015-01-05 | 2015-01-19 | 10 | 2015-01-19 | [8 empty] | 350 | 350 |  |  |  |  | 2015-04-28 | 2015-05-04 |  | Y
Central Hudson |  | SolarCity | CH-05852 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 7041 | Staatsburg | N |  | 10 | [13 empty] | NM | N | SOLAREDGE SE10000A | 2015-01-05 | 2015-01-19 | 10 | 2015-01-19 | [14 empty] | 2015-03-09 | 2015-03-16 |  | Y
Central Hudson |  | NRG Home Solar | CH-04562 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6056 | Todd Hill | N |  | 11.5 | [13 empty] | NM | N | 46 - ENPHASE ENERGY M-250 | 2015-01-06 | 2015-01-19 | 9 | 2015-01-19 | [14 empty] | 2015-04-14 | 2015-04-21 |  | Y
Central Hudson |  | NRG Home Solar | CH-04565 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 7024 | Tinkertown | N |  | 4.945 | [13 empty] | NM | N | 23 - ENPHASE ENERGY M-215 | 2015-01-06 | 2015-01-19 | 9 | 2015-01-19 | [14 empty] | 2015-09-04 | 2015-09-14 |  | Y
Central Hudson |  | SolarCity | CH-05977 | Newburgh | Highland | Ulster | 12528 | G | 5081 | Highland | N |  | 9 | [13 empty] | NM | N | 1 - ABB PVI-3.0 1 - ABB PVI-6000 | 2015-01-06 | 2015-01-13 | 5 | 2015-01-13 | [14 empty] | 2015-02-02 | 2015-02-09 |  | Y
Central Hudson |  | SolarCity | CH-06985 | Newburgh | Newburgh | Orange | 12550 | G | 4023 | Coldenham | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000 (1) | 2015-01-06 | 2015-01-13 | 5 | 2015-01-13 | [14 empty] | 2015-03-02 | 2015-03-09 |  | Y
Central Hudson |  | SolarCity | CH-07147 | Newburgh | Montgomery | Orange | 12549 | G | 5073 | Montgomery | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000 (1) | 2015-03-02 | 2015-03-02 | 0 | 2015-03-02 | [14 empty] | 2015-03-03 | 2015-03-10 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Verengo Solar | CH-09833 | Newburgh | Newburgh | Orange | 12550 | G | 5004 | Marlboro | N |  | 7.955 | [13 empty] | NM | N | (37) ENPHASE ENERGY M215 | 2015-01-13 | 2015-01-26 | 9 | 2015-01-26 | [14 empty] | 2015-04-10 | 2015-04-17 |  | Y
Central Hudson |  | Verengo Solar | CH-09835 | Newburgh | Marlboro | Ulster | 12542 | G | 5004 | Marlboro | N |  | 7.74 | [13 empty] | NM | N | ENPHASE ENERGY M215 (36) | 2015-01-06 | 2015-01-13 | 5 | 2015-01-13 | [14 empty] | 2015-04-23 | 2015-04-30 |  | Y
Central Hudson |  | Verengo Solar | CH-09860 | Newburgh | Highland | Ulster | 12528 | G | 5081 | Highland | N |  | 8.17 | [13 empty] | NM | N | 38 - ENPHASE ENERGY M215 | 2015-01-06 | 2015-01-13 | 5 | 2015-01-13 | [14 empty] | 2015-04-06 | 2015-04-13 |  | Y
Central Hudson |  | Verengo Solar | CH-09881 | Newburgh | Wallkill | Ulster | 12589 | G | 5043 | East Walden | N | CH-09881 | 4.085 | [13 empty] | NM | N | ENPHASE ENERGY M215 (14) | 2015-01-06 | 2015-01-13 | 5 | 2015-01-13 | [14 empty] | 2015-06-26 | 2015-07-06 |  | Y
Central Hudson |  | Verengo Solar | CH-09905 | Newburgh | Newburgh | Orange | 12550 | G | 4052 | Union Ave | N |  | 6.02 | [13 empty] | NM | N | ENPHASE ENERGY M215 (28) | 2015-01-06 | 2015-01-13 | 5 | 2015-01-13 | [14 empty] | 2015-05-21 | 2015-05-29 |  | Y
Central Hudson |  | RGS Energy | CH-03052 | Newburgh | Wallkill | Ulster | 12589 | G | 5043 | East Walden | N |  | 5.25 | [13 empty] | NM | N | ENPHASE M250 (21) | 2015-03-11 | 2015-03-18 | 5 | 2015-03-18 | [14 empty] | 2015-05-01 | 2015-05-08 |  | Y
Central Hudson |  | Kirchhoff Green Energy LLC | CH-03554 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6055 | Todd Hill | N |  | 7.5 | [13 empty] | NM | N | FRONIUS USA IG PLUS 7.5-1 | 2015-01-07 | 2015-01-21 | 10 | 2015-01-21 | [14 empty] | 2015-06-29 | 2015-07-06 |  | Y
Central Hudson |  | NRG Home Solar | CH-04537 | Kingston | Kingston |  | 12401 | G | 1021 | East Kingston | TBD |  | 3.25 | [13 empty] | NM | N | 13 ENPHASE M-250-60-2LL-S22 | 2015-01-07 | 2015-01-20 | 9 | 2015-01-20 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | NRG Home Solar | CH-04693 | Kingston | Saugerties |  | 12477 | G | 3003 | Saugerties | TBD |  | 3.87 | [13 empty] | NM | N | 18 ENPHASE M-215-60-2LL-S22-IG | 2015-01-07 | 2015-01-20 | 9 | 2015-01-20 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | Hudson Solar | CH-01342 | Fishkill | Beacon | Dutchess | 12508 | G | 8015 | Forgebrook | N |  | 35 | [13 empty] | NM | N | 1 - SMA AMERICA STP20000 1 - SMA AMERICA STP15000 | 2015-01-07 | 2015-01-21 | 10 | 2015-01-21 | [8 empty] | 3200 | 1529.5 |  |  |  |  | 2015-09-15 | 2015-09-16 |  | Y
Central Hudson |  | Hudson Solar | CH-01519 | Newburgh | New Windsor | Orange | 12553 | G | 4095 | Bethlehem Rd | N |  | 6 | [13 empty] | NM | N | SMA AMERICA SB6000 (1) | 2015-02-12 | 2015-02-24 | 7 | 2015-02-24 | [14 empty] | 2015-04-29 | 2015-05-05 |  | Y
Central Hudson |  | Hudson Solar | CH-01852 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7053 | Rhinebeck | N |  | 6 | [13 empty] | NM | N | SMA AMERICASB6000 | 2015-01-07 | 2015-01-14 | 5 | 2015-01-14 | [14 empty] | 2015-03-27 | 2015-04-06 |  | W
Central Hudson |  | Hudson Solar | CH-01935 | Fishkill | Beacon | Dutchess | 12508 | G | 8015 | Forgebrook | N |  | 85 | [13 empty] | NM | N | (2) SMA STP20000 & (3) SMA STP15000 | 2015-02-02 | 2015-02-24 | 15 | 2015-02-24 | 2015-02-02 | 2015-02-24 | 15 | [11 empty] | 2015-10-07 | 2015-10-13 |  | Y
Central Hudson |  | Hudson Solar | CH-02057 | Kingston | Lake Katrine | Ulster | 12449 | G | 2011 | Lincoln Park | N |  | 9 | [13 empty] | NM | N | SMA AMERICA SB9000 TL-US-12 | 2015-01-07 | 2015-01-20 | 9 | 2015-01-20 | [14 empty] | 2015-03-27 | 2015-04-06 |  | Y
Central Hudson |  | SolarCity | CH-05371 | Poughkeepsie | Stanfordvl | Dutchess | 12581 | G | 7072 | Stanfordville | N |  | 3 | [13 empty] | NM | N | ABB PVI-3.0-OUTD-S | 2015-01-07 | 2015-01-14 | 5 | 2015-01-14 | [14 empty] | 2015-04-06 | 2015-04-13 |  | Y
Central Hudson |  | SolarCity | CH-05847 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 6073 | East Park | Y | CH-05847 | 8.6 | [13 empty] | NM | N | 1 - ABB PVI-3.6 1 - ABB PVI-5000 | 2015-01-07 | 2015-01-21 | 10 | 2015-01-21 | [14 empty] | 2015-03-09 | 2015-03-16 |  | Y
Central Hudson |  | SolarCity | CH-06307 | Newburgh | Marlboro | Ulster | 12542 | G | 5004 | Marlboro | N |  | 3.8 | [13 empty] | NM | N | SOLAREDGE SE3800A (1) | 2015-01-07 | 2015-01-14 | 5 | 2015-01-14 | [14 empty] | 2015-02-13 | 2015-02-13 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07222 | Kingston | Kingston | Ulster | 12401 | G | 1011 | Boulevard | N |  | 7.6 | [13 empty] | NM | N | (2) SOLAREDGE SE3800A-US | 2015-01-07 | 2015-01-20 | 9 | 2015-01-20 | [14 empty] | 2015-01-22 | 2015-01-29 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Sunrise Solar Solutions, LLC | CH-09650 | Fishkill | Garrison | Putnam | 10524 | G | 8066 | Merritt Park | N |  | 4.5 | [13 empty] | NM | N | ENPHASE M250 (18) | 2015-01-14 | 2015-01-28 | 10 | 2015-01-28 | [14 empty] | 2015-04-30 | 2015-05-07 |  | Y
Central Hudson |  | Verengo Solar | CH-09865 | Fishkill | Wappingrs Falls |  | 12590 | G | 8092 | Fishkill Plains | TBD |  | 10.32 | [13 empty] | NM | N | ENPHASE ENERGY M215 (48) | 2015-01-07 | 2015-01-14 | 5 | 2015-01-14 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | Infinity Solar Systems | CH-03390 | Newburgh | Newburgh | Orange | 12550 | G | 4023 | Coldenham | N |  | 13 | [13 empty] | NM | N | SMA AMERICA SB6000TL SMA AMERICA SB7000 | 2015-01-08 | 2015-01-16 | 6 | 2015-01-16 | [14 empty] | 2015-04-22 | 2015-04-28 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-03417 | Newburgh | Newburgh | Orange | 12550 | G | 4011 | West Balmville | N |  | 5 | [13 empty] | NM | N | SMA AMERICA SB5000 (1) | 2015-01-08 | 2015-01-15 | 5 | 2015-01-15 | [14 empty] | 2015-03-31 | 2015-04-08 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-03434 | Newburgh | Wallkill | Ulster | 12589 | G | 5043 | East Walden | N |  | 6.8 | [13 empty] | NM | N | SMA AMERICA SB3800TL SMA AMERICA SB3000TL | 2015-01-08 | 2015-01-16 | 6 | 2015-01-16 | [14 empty] | 2015-05-15 | 2015-05-21 |  | Y
Central Hudson |  | NRG Home Solar | CH-04434 | Fishkill | Beacon | Dutchess | 12508 | G | 8087 | Tioronda | N |  | 3.44 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (16) | 2015-01-08 | 2015-01-15 | 5 | 2015-01-15 | [14 empty] | 2015-04-14 | 2015-04-21 |  | Y
Central Hudson |  | NRG Home Solar | CH-04527 | Kingston | Ellenville |  | 12428 | G | 3078 | Greenfield Rd | TBD |  | 3.65 | [13 empty] | NM | N | 17 ENPHASE M-215-60-2LL-S22-IG | 2015-01-08 | 2015-01-22 | 10 | 2015-01-22 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | Direct Energy Solar | CH-00891 | Catskill | Greenville | Greene | 12083 | G | 2061 | Freehold | N |  | 4.73 | [13 empty] | NM | N | 22 ENPHASE 215 60-240-S22 | 2015-01-08 | 2015-01-22 | 10 | 2015-01-22 | [14 empty] | 2015-02-23 | 2015-03-02 |  | Y
Central Hudson |  | Hudson Solar | CH-01353 | Newburgh | Milton | Ulster | 12547 | G | 5003 | Marlboro | N |  | 24 | [13 empty] | RNM | N | (4) SMA America SB6000-TL-US-22 | 2015-01-08 | 2015-01-22 | 10 | 2015-01-22 | [14 empty] | 2015-08-07 | 2015-08-13 |  | Y
Central Hudson |  | Hudson Solar | CH-01510 | Newburgh | New Paltz | Ulster | 12561 | G | 5031 | Galeville | N | CH-01510 | 3.8 | [13 empty] | NM | N | SMA AMERICA SB3800 (1) | 2015-01-08 | 2015-01-15 | 5 | 2015-01-15 | [14 empty] | 2015-04-30 | 2015-05-06 |  | Y
Central Hudson |  | Hudson Solar | CH-02126 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7053 | Rhinebeck | N | CH-02126 | 4 | [13 empty] | NM | N | SMA AMERICA SB4000 | 2015-01-15 | 2015-01-29 | 10 | 2015-01-29 | [14 empty] | 2015-03-16 | 2015-03-23 |  | Y
Central Hudson |  | Hudson Solar | CH-02219 | Newburgh | Rock Tvrn |  | 12575 | G | 4097 | Bethlehem Rd | TBD |  | 7.7 | [13 empty] | NM | N | SMA AMERICA SB7700 (1) | 2015-01-08 | 2015-01-15 | 5 | 2015-01-15 | [17 empty] | W
Central Hudson |  | Hudson Solar | CH-02456 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6046 | Spackenkill | N | CH-01410 | 6 | [13 empty] | NM | N | 2 -SMA AMERICA SB3000 | 2015-01-16 | 2015-01-23 | 5 | 2015-01-23 | [14 empty] | 2015-09-30 | 2015-10-06 |  | Y
Central Hudson |  | SolarCity | CH-06056 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8095 | Fishkill Plains | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A (1) | 2015-01-19 | 2015-01-22 | 3 | 2015-01-22 | [14 empty] | 2015-02-03 | 2015-02-04 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07770 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8043 | Myers Corners | N |  | 5 | [13 empty] | NM | N | ABB PVI-5000-OUTD | 2015-01-22 | 2015-02-05 | 10 | 2015-02-05 | [14 empty] | 2015-02-06 | 2015-02-13 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Sungevity Inc | CH-09358 | Fishkill | Beacon | Dutchess | 12508 | G | 8017 | Forgebrook | N |  | 8.8 | [13 empty] | NM | N | SMA SB 3800TL (1) SMASB 5000TL (1) | 2015-01-08 | 2015-01-15 | 5 | 2015-01-15 | [14 empty] | 2015-04-23 | 2015-04-30 |  | Y
Central Hudson |  | Sungevity Inc | CH-09476 | Newburgh | Newburgh |  | 12550 | G | 4012 | West Balmville | N |  | 8 | [13 empty] | NM | N | SMA SB 5000TL (1) SMA SB 3000TL (1) | 2015-02-11 | 2015-02-24 | 8 | 2015-02-24 | [14 empty] | 2015-03-25 | 2015-04-01 |  | W
Central Hudson |  | Lighthouse Solar | CH-03615 | Newburgh | New Paltz | Ulster | 12561 | G | 5031 | Galeville | N |  | 11.4 | [13 empty] | NM | N | SOLAREDGE 11400 (1) | 2015-01-09 | 2015-01-23 | 10 | 2015-01-23 | [8 empty] | 350 | 350 |  |  |  |  | 2015-11-19 | 2015-11-19 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03640 | Newburgh | Clintondale | Ulster | 12515 | G | 5012 | Modena | N |  | 13.8 | [13 empty] | NM | N | SOLAREDGE 10000 (1) SOLAREDGE 3800 (1) | 2015-01-09 | 2015-01-23 | 10 | 2015-01-23 | [14 empty] | 2015-02-26 | 2015-03-05 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Lighthouse Solar | CH-03650 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8072 | Shenandoah | N |  | 10 | [13 empty] | NM | N | SOLAREDGE 10000 (1) | 2015-01-16 | 2015-01-30 | 10 | 2015-01-30 | [14 empty] | 2015-04-07 | 2015-04-14 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03681 | Newburgh | New Paltz | Ulster | 12561 | G | 5031 | Galeville | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE 7600 (1) | 2015-01-09 | 2015-01-16 | 5 | 2015-01-16 | [14 empty] | 2015-08-31 | 2015-09-08 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03804 | Newburgh | New Paltz | Ulster | 12561 | G | 5024 | Ohioville | N |  | 10 | [13 empty] | NM | N | SOLAREDGE 10000 (1) | 2015-03-17 | 2015-03-27 | 8 | 2015-03-27 | [14 empty] | 2015-04-14 | 2015-04-21 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Lighthouse Solar | CH-03821 | Newburgh | Highland | Ulster | 12528 | G | 5082 | Highland | N |  | 5 | [13 empty] | NM | N | SOLAREDGE 5000 | 2015-01-20 | 2015-02-03 | 10 | 2015-02-03 | [14 empty] | 2015-04-02 | 2015-04-10 |  | Y
Central Hudson |  | NRG Home Solar | CH-04345 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6046 | Spackenkill | N |  | 5.59 | [13 empty] | NM | N | 26 - NPHASE ENERGY M-215 | 2015-01-09 | 2015-01-23 | 10 | 2015-01-23 | [14 empty] | 2015-10-13 | 2015-10-20 |  | Y
Central Hudson |  | Hudson Solar | CH-01621 | Catskill | Earlton | Greene | 12058 | G | 2005 | North Catskill | N |  | 10.7 | [13 empty] | NM | N | SMA AMERICA SB7700 TL-US-22 SMA MERICA SB3000 TL-US22 | 2015-01-09 | 2015-01-23 | 10 | 2015-01-23 | [8 empty] | 350 | 350 |  |  |  |  | 2015-05-15 | 2015-05-19 |  | Y
Central Hudson |  | SolarCity | CH-05993 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8091 | Fishkill Plains | N |  | 9 | [13 empty] | NM | N | ABB PVI-6000-OUTD ABB PVI-3.0-OUTD-S | 2015-01-09 | 2015-01-16 | 5 | 2015-01-16 | [14 empty] | 2015-08-11 | 2015-08-11 |  | Y
Central Hudson |  | SolarCity | CH-06933 | Fishkill | Beacon | Dutchess | 12508 | G | 8017 | Forgebrook | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A (1) | 2015-01-09 | 2015-01-16 | 5 | 2015-01-16 | [14 empty] | 2015-06-29 | 2015-07-07 |  | Y
Central Hudson |  | SolarCity | CH-07471 | Newburgh | Rock Tvrn | Orange | 12575 | G | 4097 | Bethlehem Rd | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A | 2015-01-21 | 2015-02-04 | 10 | 2015-02-04 | [14 empty] | 2015-06-22 | 2015-06-29 |  | Y
Central Hudson |  | SolarCity | CH-07502 | Kingston | W Hurley | Ulster | 12491 | G | 3013 | Woodstock | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A US | 2015-01-09 | 2015-01-22 | 9 | 2015-01-22 | [14 empty] | 2015-02-09 | 2015-02-17 |  | W
Central Hudson |  | RGS Energy | CH-03051 | Newburgh | Newburgh | Orange | 12550 | G | 4051 | Union Ave | N |  | 3.75 | [13 empty] | NM | N | (15) ENPHASE M250-60-2LL-S22 | 2015-01-12 | 2015-01-26 | 10 | 2015-01-26 | [14 empty] | 2015-04-09 | 2015-04-16 |  | Y
Central Hudson |  | NRG Home Solar | CH-04199 | Fishkill | Beacon | Dutchess | 12508 | G | 8017 | Forgebrook | N |  | 4.515 | [13 empty] | NM | N | (21) ENPHASE ENERGY M-215-60-2LL-S22-IG | 2015-01-12 | 2015-01-26 | 10 | 2015-01-26 | [14 empty] | 2015-09-23 | 2015-09-30 |  | Y
Central Hudson |  | NRG Home Solar | CH-04650 | Newburgh | Newburgh |  | 12550 | G | 4045 | Union Ave | TBD |  | 8 | [13 empty] | NM | N | 32 - ENPHASE ENERGY M-250 | 2015-01-12 | 2015-01-26 | 10 | 2015-01-26 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | NRG Home Solar | CH-04813 | Poughkeepsie | Pleasant Vly |  | 12569 | G | 7011 | Hibernia | TBD |  | 6.88 | [13 empty] | NM | N | 32 - ENPHASE ENERGY M-215 | 2015-01-12 | 2015-01-19 | 5 | 2015-01-19 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | Direct Energy Solar | CH-00898 | Kingston | Kingston |  | 12401 | G | 2092 | Hurley Ave | TBD |  | 5.59 | [13 empty] | NM | N | 26 ENPHASE M215-60-2LL-S22 | 2015-01-12 | 2015-01-23 | 9 | 2015-01-23 | [17 empty] | W
Central Hudson |  | SolarCity | CH-05049 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8046 | Myers Corners | N |  | 5 | [13 empty] | NM | N | ABB PVI-5000-OUTD | 2015-01-12 | 2015-01-26 | 10 | 2015-01-26 | [14 empty] | 2015-02-04 | 2015-02-11 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06649 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6046 | Spackenkill | N |  | 3 | [13 empty] | NM | N | ABB PVI-3.0 | 2015-01-13 | 2015-01-26 | 9 | 2015-01-26 | [14 empty] | 2015-02-12 | 2015-02-20 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07209 | Kingston | Hurley | Ulster | 12443 | G | 2094 | Hurley Ave | N |  | 3 | [13 empty] | NM | N | ABB PVI-3.0-OUTD-S-Z-A | 2015-01-13 | 2015-01-23 | 8 | 2015-01-23 | [14 empty] | 2015-03-02 | 2015-03-09 |  | Y
Central Hudson |  | Solar Generation | CH-08198 | Poughkeepsie | Clinton Corners | Dutchess | 12514 | G | 7071 | Stanfordville | N |  | 10 | [13 empty] | NM | N | 2 - SMA SB 5000 | 2015-01-13 | 2015-01-26 | 9 | 2015-01-26 | [14 empty] | 2015-03-25 | 2015-04-01 |  | Y
Central Hudson |  | Solar Alchemy | CH-08988 | Kingston | Accord | Ulster | 12404 | G | 3081 | Kerhonkson | N |  | 8.75 | [13 empty] | NM | N | (35) ENPHASE M-250 | 2015-01-13 | 2015-01-23 | 8 | 2015-01-23 | [14 empty] | 2016-04-28 | 2016-04-28 |  | Y
Central Hudson |  | Sungevity Inc | CH-09626 | Fishkill | Wappingrs Falls |  | 12590 | G | 8045 | Myers Corners | TBD |  | 5 | [13 empty] | NM | N | SMA AMERICA SB5000TL-US-22 | 2015-01-13 | 2015-01-26 | 9 | 2015-01-26 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | Verengo Solar | CH-09927 | Fishkill | Hopewell Jct |  | 12533 | G | 8095 | Fishkill Plains | TBD |  | 7.95 | [13 empty] | NM | N | (37) ENPHASE ENERGY M215-60-2LL-S22-IG | 2015-01-13 | 2015-01-26 | 9 | 2015-01-26 | [17 empty] | W
Central Hudson |  | RGS Energy | CH-03060 | Catskill | Leeds |  | 12451 | G | 2005 | North Catskill | TBD |  | 8 | [13 empty] | NM | N | 32 ENPHASE M250-60-2LL-S22 | 2015-01-14 | 2015-01-28 | 10 | 2015-01-28 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | Infinity Solar Systems | CH-03372 | Newburgh | Washingtonvl | Orange | 10992 | G | 4097 | Bethlehem Rd | N |  | 8.8 | [13 empty] | NM | N | (1) SMA AMERICA SB3800TL (1) SMA AMERICA SB5000TL | 2015-01-14 | 2015-01-28 | 10 | 2015-01-28 | [14 empty] | 2015-04-22 | 2015-04-28 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-03439 | Newburgh | Campbell Hall | Orange | 10916 | G | 5051 | Maybrook | N |  | 20 | [13 empty] | NM | N | (1) FRONIUS IG PLUS 10.0 (2) FRONIUS IG PLUS 5.0 | 2015-04-28 | 2015-05-05 | 5 | 2015-05-05 | [14 empty] | 2015-05-14 | 2015-05-20 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | New York State Solar Farm | CH-03963 | Catskill | Palenvl | Greene | 12463 | G | 2042 | South Cairo | N |  | 12 | [13 empty] | NM | N | 2 POWERONE PVI 6.0 | 2015-01-14 | 2015-01-28 | 10 | 2015-01-28 | [14 empty] | 2015-04-20 | 2015-04-27 |  | Y
Central Hudson |  | New York State Solar Farm | CH-04015 | Newburgh | New Windsor | Orange | 12553 | G | 4097 | Bethlehem Rd | N |  | 8.8 | [13 empty] | NM | N | (1) POWERONE PVI 5.0 (1) POWERONE PVI 3.8 | 2015-01-14 | 2015-01-28 | 10 | 2015-01-28 | [8 empty] | 350 | 350 |  |  |  |  | 2015-03-16 | 2015-03-23 |  | Y
Central Hudson |  | New York State Solar Farm | CH-04097 | Newburgh | Highland | Ulster | 12528 | G | 5013 | Modena | N |  | 8 | [13 empty] | NM | N | 25 SunPower SPR-X21-345-C-AC (240V) | 2015-01-14 | 2015-01-28 | 10 | 2015-01-28 | [14 empty] | 2017-10-26 | 2017-10-30 |  | Y
Central Hudson |  | SolarCity | CH-05002 | Kingston | Kerhonkson | Ulster | 12446 | G | 3081 | Kerhonkson | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000-OUTD US-Z-A | 2015-01-14 | 2015-01-28 | 10 | 2015-01-28 | [14 empty] | 2015-04-02 | 2015-04-10 |  | Y
Central Hudson |  | SolarCity | CH-05170 | Newburgh | Wallkill |  | 12589 | G | 5043 | East Walden | TBD |  | 7.5 | [13 empty] | NM | N | FRONIUS IG PLUS A 7.5 | 2015-01-14 | 2015-01-28 | 10 | 2015-01-28 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | SolarCity | CH-06384 | Newburgh | New Windsor | Orange | 12553 | G | 4095 | Bethlehem Rd | N |  | 7.2 | [13 empty] | NM | N | (2) ABB PVI-3.6-OUTD-S | 2015-01-14 | 2015-01-28 | 10 | 2015-01-28 | [14 empty] | 2015-04-09 | 2015-04-16 |  | Y
Central Hudson |  | Sungevity Inc | CH-09224 | Newburgh | New Windsor | Orange | 12553 | G | 4094 | Bethlehem Rd | N | CH-09224 | 8 | [13 empty] | NM | N | (1) SMA AMERICA SB8000US-12 | 2015-01-14 | 2015-01-28 | 10 | 2015-01-28 | [14 empty] | 2015-06-24 | 2015-07-01 |  | Y
Central Hudson |  | Sungevity Inc | CH-09269 | Kingston | Accord |  | 12404 | G | 3024 | High Falls | TBD |  | 7.7 | [13 empty] | NM | N | SMA SB 7700TL | 2015-01-14 | 2015-01-28 | 10 | 2015-01-28 | [17 empty] | W
Central Hudson |  | Sungevity Inc | CH-09488 | Newburgh | Highland |  | 12528 | G | 5013 | Modena | TBD |  | 10 | [13 empty] | NM | N | (2) SMA AMERICA SB5000TL-US-22 | 2015-01-14 | 2015-01-28 | 10 | 2015-01-28 | [8 empty] | 350 | 350 | [7 empty] | W |  | Customer already had net meter prior to application. Transformer upgrade required to accommodate PV installation. Utility System Upgrade Costs TBD.
Central Hudson |  | Verengo Solar | CH-09926 | Newburgh | Highland |  | 12528 | G | 5081 | Highland | TBD |  | 7.31 | [13 empty] | NM | N | 34 - ENPHASE ENERGY M215 | 2015-01-14 | 2015-01-28 | 10 | 2015-01-28 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | NRG Home Solar | CH-04166 | Kingston | Kingston | Ulster | 12401 | G | 1021 | East Kingston | N |  | 2.37 | [13 empty] | NM | N | 11 ENPHASE M-215-60-2LL-S22-IG | 2015-01-15 | 2015-01-29 | 10 | 2015-01-29 | [14 empty] | 2015-04-14 | 2015-04-21 |  | Y
Central Hudson |  | NRG Home Solar | CH-04551 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6096 | Manchester | N |  | 7.31 | [13 empty] | NM | N | 34 - ENPHASE ENERGY M-215 | 2015-01-15 | 2015-01-23 | 6 | 2015-01-23 | [14 empty] | 2015-04-14 | 2015-04-21 |  | Y
Central Hudson |  | SolarCity | CH-07784 | Fishkill | Beacon | Dutchess | 12508 | G | 8015 | Forgebrook | N |  | 3.6 | [13 empty] | NM | N | ABB PVI-3.6-OUTD-S | 2015-01-15 | 2015-01-29 | 10 | 2015-01-29 | [14 empty] | 2015-06-05 | 2015-06-12 |  | Y
Central Hudson |  | Sungevity Inc | CH-09225 | Kingston | Accord | Ulster | 12404 | G | 3024 | High Falls | N |  | 4 | [13 empty] | NM | N | SMA AMERICA SB4000TL-US-22 | 2015-01-15 | 2015-01-29 | 10 | 2015-01-29 | [14 empty] | 2015-02-25 | 2015-03-04 |  | Y
Central Hudson |  | Verengo Solar | CH-09837 | Newburgh | Marlboro | Ulster | 12542 | G | 5004 | Marlboro | N |  | 13.11 | [13 empty] | NM | N | (61) ENPHASE ENERGY M215-60-2LL-S22-IG | 2015-01-15 | 2015-01-29 | 10 | 2015-01-29 | [14 empty] | 2015-04-15 | 2015-04-22 |  | Y
Central Hudson |  | Verengo Solar | CH-09870 | Newburgh | Walden | Orange | 12586 | G | 5041 | East Walden | N |  | 6.66 | [13 empty] | NM | N | (31) ENPHASE ENERGY M215-60-2LL-S22-IG | 2015-01-28 | 2015-02-10 | 9 | 2015-02-10 | [14 empty] | 2015-06-01 | 2015-06-08 |  | Y
Central Hudson |  | NRG Home Solar | CH-04589 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8023 | Knapps Corners | N |  | 4.845 | [13 empty] | NM | N | (19) ENPHASE ENERGY M-215-60-2LL-S22-IG | 2015-01-16 | 2015-01-30 | 10 | 2015-01-30 | [14 empty] | 2015-04-21 | 2015-04-28 |  | Y
Central Hudson |  | SolarCity | CH-05370 | Newburgh | Newburgh | Orange | 12550 | G | 4011 | West Balmville | N |  | 3 | [13 empty] | NM | N | ABB PVI-3.0-OUTD-S | 2015-02-03 | 2015-02-12 | 7 | 2015-02-12 | [14 empty] | 2015-03-02 | 2015-03-09 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06212 | Newburgh | Newburgh | Orange | 12550 | G | 4023 | Coldenham | N |  | 7.6 | [13 empty] | NM | N | (2) SOLAREDGE SE3800A | 2015-01-16 | 2015-01-30 | 10 | 2015-01-30 | [14 empty] | 2015-02-19 | 2015-02-26 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06383 | Newburgh | New Windsor | Orange | 12553 | G | 4095 | Bethlehem Rd | N |  | 5 | [13 empty] | NM | N | ABB PVI-5000-OUTD | 2015-01-16 | 2015-01-30 | 10 | 2015-01-30 | [14 empty] | 2015-03-19 | 2015-03-26 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06644 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6042 | Spackenkill | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A | 2015-01-16 | 2015-01-23 | 5 | 2015-01-23 | [14 empty] | 2015-01-23 | 2015-01-30 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Verengo Solar | CH-09768 | Newburgh | Newburgh | Orange | 12550 | G | 4023 | Coldenham | N |  | 6.45 | [13 empty] | NM | N | (30) ENPHASE ENERGY M215-60-2LL-S22-IG | 2015-01-16 | 2015-01-30 | 10 | 2015-01-30 | [14 empty] | 2015-04-15 | 2015-04-22 |  | Y
Central Hudson |  | Verengo Solar | CH-09792 | Kingston | Saugerties | Ulster | 12477 | G | 3001 | Saugerties | N |  | 4.73 | [13 empty] | NM | N | 22 ENPHASE M215-60-2LL-S22-IG | 2015-01-16 | 2015-01-30 | 10 | 2015-01-30 | [14 empty] | 2015-03-23 | 2015-03-30 |  | Y
Central Hudson |  | Verengo Solar | CH-09853 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6046 | Spackenkill | N |  | 8.6 | [13 empty] | NM | N | 40 - ENPHASE ENERGY M215 | 2015-01-16 | 2015-01-23 | 5 | 2015-01-23 | [14 empty] | 2015-04-27 | 2015-05-01 |  | Y
Central Hudson |  | Verengo Solar | CH-09855 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6066 | Inwood Ave | N |  | 6.45 | [13 empty] | NM | N | 30 - ENPHASE ENERGY M215 | 2015-01-16 | 2015-01-23 | 5 | 2015-01-23 | [14 empty] | 2015-05-13 | 2015-05-19 |  | Y
Central Hudson |  | Verengo Solar | CH-09921 | Fishkill | Beacon | Dutchess | 12508 | G | 8085 | Tioronda | N |  | 4.73 | [13 empty] | NM | N | (22) ENPHASE ENERGY M215-60-2LL-S22-IG | 2015-01-16 | 2015-01-30 | 10 | 2015-01-30 | [14 empty] | 2015-06-01 | 2015-06-08 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03722 | Newburgh | Wallkill | Ulster | 12589 | G | 5041 | East Walden | N |  | 11.4 | [13 empty] | NM | N | SOLAREDGE SE11400 | 2015-01-19 | 2015-02-02 | 10 | 2015-02-02 | [14 empty] | 2015-06-09 | 2015-06-16 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03794 | Newburgh | Gardiner | Ulster | 12525 | G | 5012 | Modena | N |  | 10 | [13 empty] | NM | N | SOLAREDGE 10000 (1) | 2015-01-19 | 2015-02-02 | 10 | 2015-02-02 | [14 empty] | 2015-04-02 | 2015-04-10 |  | Y
Central Hudson |  | New York State Solar Farm | CH-04074 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6011 | Sand Dock | N |  | 10 | [13 empty] | NM | N | 2 - POWERONE PVI 5.0 | 2015-01-19 | 2015-02-02 | 10 | 2015-02-02 | [14 empty] | 2015-02-27 | 2015-03-06 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00878 | Kingston | Grahamsvl | Sullivan | 12740 | G | 3091 | Neversink | N |  | 5.16 | [13 empty] | NM | N | (24) ENPHASE M215 | 2015-01-19 | 2015-02-02 | 10 | 2015-02-02 | [14 empty] | 2015-03-06 | 2015-03-13 |  | Y
Central Hudson |  | SolarCity | CH-04958 | Fishkill | Fishkill | Dutchess | 12524 | G | 8055 | North Chelsea | N |  | 10.2 | [13 empty] | NM | N | (1) ABB PVI-4.2-OUTD-S (1) ABB PVI-6000-OUTD | 2015-01-19 | 2015-02-02 | 10 | 2015-02-02 | [14 empty] | 2015-03-02 | 2015-03-09 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07110 | Newburgh | Cornwall | Orange | 12518 | G | 4041 | Union Ave | N |  | 10 | [13 empty] | NM | N | (1) SOLAREDGE SE10000 | 2015-01-29 | 2015-02-11 | 9 | 2015-02-11 | [14 empty] | 2015-07-30 | 2015-08-05 |  | Y
Central Hudson |  | SolarCity | CH-07256 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6044 | Spackenkill | N |  | 3 | [13 empty] | NM | N | ABB PVI-3.0 | 2015-01-19 | 2015-02-02 | 10 | 2015-02-02 | [14 empty] | 2015-04-15 | 2015-04-22 |  | Y
Central Hudson |  | SolarCity | CH-07378 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8072 | Shenandoah | N |  | 6 | [13 empty] | NM | N | (1) ABB PVI-6000-OUTD | 2015-01-19 | 2015-02-02 | 10 | 2015-02-02 | [14 empty] | 2015-10-21 | 2015-10-26 |  | Y
Central Hudson |  | Verengo Solar | CH-09851 | Kingston | Wawarsing | Ulster | 12489 | G | 3071 | Honk Falls | N |  | 4.73 | [13 empty] | NM | N | 22 - ENPHASE ENERGY M215 | 2015-01-19 | 2015-02-02 | 10 | 2015-02-02 | [14 empty] | 2015-05-12 | 2015-05-15 |  | Y
Central Hudson |  | You Save Green | CH-09957 | Newburgh | Montgomery | Orange | 12549 | G | 4026 | Coldenham | N |  | 11 | [13 empty] | NM | N | (44) ENPHASE M250 | 2015-02-09 | 2015-02-20 | 8 | 2015-02-20 | [14 empty] | 2015-12-17 | 2015-12-17 |  | Y
Central Hudson |  | NRG Home Solar | CH-04111 | Fishkill | Hopewell Junction | Dutchess | 12533 | G | 8094 | Fishkill Plains | N |  | 6.23 | [13 empty] | NM | N | (29) ENPHASE ENERGY M-215-60-2LL-S22-IG | 2015-01-20 | 2015-02-03 | 10 | 2015-02-03 | [14 empty] | 2015-04-20 | 2015-04-27 |  | Y
Central Hudson |  | NRG Home Solar | CH-04129 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8054 | North Chelsea | N |  | 6 | [13 empty] | NM | N | (24) ENPHASE ENERGY M-250-60-2LL-S22 | 2015-01-20 | 2015-02-03 | 10 | 2015-02-03 | [14 empty] | 2015-07-22 | 2015-07-27 |  | Y
Central Hudson |  | NRG Home Solar | CH-04179 | Newburgh | Newburgh |  | 12550 | G | 4012 | West Balmville | TBD |  | 3.87 | [13 empty] | NM | N | (18) ENPHASE ENERGY M-215-60-2LL-S22-IG | 2015-01-20 | 2015-02-03 | 10 | 2015-02-03 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | NRG Home Solar | CH-04194 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6056 | Todd Hill | N |  | 5.16 | [13 empty] | NM | N | 24 ENPHASE M-215-60-2LL-S22-IG | 2015-01-20 | 2015-02-03 | 10 | 2015-02-03 | [14 empty] | 2015-04-14 | 2015-04-21 |  | Y
Central Hudson |  | NRG Home Solar | CH-04280 | Kingston | Grahamsville |  | 12740 | G | 3091 | Neversink | TBD |  | 3.66 | [13 empty] | NM | N | 17 ENPHASE M-215-60-2LL-S22-IG | 2015-01-20 | 2015-02-03 | 10 | 2015-02-03 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | NRG Home Solar | CH-04405 | Fishkill | Fishkill | Dutchess | 12524 | G | 8094 | Fishkill Plains | N |  | 4.94 | [13 empty] | NM | N | (23) ENPHASE ENERGY M-215-60-2LL-S22-IG | 2015-01-20 | 2015-02-03 | 10 | 2015-02-03 | [14 empty] | 2015-04-14 | 2015-04-21 |  | Y
Central Hudson |  | NRG Home Solar | CH-04534 | Kingston | Saugerties | Ulster | 12477 | G | 3003 | Saugerties | N |  | 7.96 | [13 empty] | NM | N | 37 ENPHASE M-215-60-2LL-S22-IG | 2015-01-20 | 2015-02-03 | 10 | 2015-02-03 | [14 empty] | 2015-04-24 | 2015-05-01 |  | Y
Central Hudson |  | NRG Home Solar | CH-04555 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 6075 | East Park | N |  | 6.24 | [13 empty] | NM | N | 29 ENPHASE M-215-60-2LL-S22-IG | 2015-01-20 | 2015-02-03 | 10 | 2015-02-03 | [14 empty] | 2015-10-12 | 2015-10-19 |  | Y
Central Hudson |  | NRG Home Solar | CH-04716 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8043 | Myers Corners | N |  | 3.01 | [13 empty] | NM | N | (14) ENPHASE ENERGY M-215-60-2LL-S22-IG | 2015-01-20 | 2015-02-03 | 10 | 2015-02-03 | [14 empty] | 2015-04-14 | 2015-04-21 |  | Y
Central Hudson |  | SolarCity | CH-05436 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6046 | Spackenkill | N |  | 7.5 | [13 empty] | NM | N | FRONIUS IG PLUS A 7.5 | 2015-01-20 | 2015-02-03 | 10 | 2015-02-03 | [14 empty] | 2015-03-20 | 2015-03-26 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | NRG Home Solar | CH-04175 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8096 | Fishkill Plains | N |  | 4.5 | [13 empty] | NM | N | (18) ENPHASE ENERGY M-250-60-2LL-S22 | 2015-01-21 | 2015-02-04 | 10 | 2015-02-04 | [14 empty] | 2015-04-14 | 2015-04-21 |  | Y
Central Hudson |  | SolarCity | CH-05045 | Newburgh | Highland | Ulster | 12528 | G | 5082 | Highland | N |  | 4.2 | [13 empty] | NM | N | ABB PVI-4.2 | 2015-01-29 | 2015-02-11 | 9 | 2015-02-11 | [14 empty] | 2015-03-09 | 2015-03-16 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-05641 | Kingston | High Fls | Ulster | 12440 | G | 3022 | High Falls | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000-OUTD-US-Z-A | 2015-01-21 | 2015-02-04 | 10 | 2015-02-04 | [14 empty] | 2015-02-12 | 2015-02-19 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06816 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8045 | Myers Corners | N |  | 7.2 | [13 empty] | NM | N | (1) ABB PVI-4.2-OUTD-S (1) ABB PVI-3.0-OUTD-S | 2015-01-21 | 2015-02-04 | 10 | 2015-02-04 | [14 empty] | 2015-03-18 | 2015-03-25 |  | Y
Central Hudson |  | SolarCity | CH-06838 | Fishkill | Wappingrs Falls |  | 12590 | G | 8023 | Knapps Corners | TBD |  | 3.6 | [13 empty] | NM | N | (1) ABB PVI-3.6-OUTD-S | 2015-01-21 | 2015-02-04 | 10 | 2015-02-04 | [17 empty] | W
Central Hudson |  | SolarCity | CH-07079 | Newburgh | Gardiner | Ulster | 12525 | G | 5031 | Galeville | N | CH-07079 | 3 | [13 empty] | NM | N | (1) ABB PVI-3.0-OUTD-S | 2015-01-21 | 2015-02-04 | 10 | 2015-02-04 | [14 empty] | 2015-03-02 | 2015-03-09 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07265 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6003 | Reynolds Hill | N |  | 3.6 | [13 empty] | NM | N | ABB PVI-3.6 | 2015-02-23 | 2015-03-02 | 5 | 2015-03-02 | [14 empty] | 2015-03-23 | 2015-03-27 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07785 | Fishkill | Beacon | Dutchess | 12508 | G | 8017 | Forgebrook | N |  | 3 | [13 empty] | NM | N | ABB PVI-3.0-OUTD-S | 2015-01-21 | 2015-02-04 | 10 | 2015-02-04 | [14 empty] | 2015-04-09 | 2015-04-16 |  | Y
Central Hudson |  | SolarCity | CH-07829 | Newburgh | Gardiner | Ulster | 12525 | G | 5031 | Galeville | N | CH-07079 | 4.2 | [13 empty] | NM | N | ABB PVI-4.2OUTD-S-US | 2015-01-21 | 2015-02-04 | 10 | 2015-02-04 | [14 empty] | 2016-09-21 | 2016-10-20 |  | Y
Central Hudson |  | NRG Home Solar | CH-04467 | Newburgh | New Windsor |  | 12553 | G | 4042 | Union Ave | TBD |  | 5.8 | [13 empty] | NM | N | (27) ENPHASE ENERGY M-215-60-2LL-S22-IG | 2015-01-22 | 2015-02-05 | 10 | 2015-02-05 | [17 empty] | W
Central Hudson |  | SolarCity | CH-05666 | Kingston | Kingston | Ulster | 12401 | G | 1024 | East Kingston | N |  | 3 | [13 empty] | NM | N | ABB PVI-3.0-OUTD-S US-Z-A | 2015-01-22 | 2015-02-05 | 10 | 2015-02-05 | [14 empty] | 2015-08-24 | 2015-08-28 |  | Y
Central Hudson |  | SolarCity | CH-06101 | Fishkill | Wappingers Falls | Dutchess | 12590 | G | 8014 | Forgebrook | N |  | 3 | [13 empty] | NM | N | ABB PVI-3.0-OUTD-S | 2015-01-22 | 2015-02-05 | 10 | 2015-02-05 | [14 empty] | 2016-04-11 | 2016-04-12 |  | Y
Central Hudson |  | SolarCity | CH-06171 | Newburgh | Highland | Ulster | 12528 | G | 5022 | Ohioville | N |  | 6 | [13 empty] | NM | N | (2) ABB PVI-3.0-OUTD | 2015-02-05 | 2015-02-20 | 10 | 2015-02-20 | [14 empty] | 2015-03-09 | 2015-03-16 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06313 | Newburgh | Newburgh | Orange | 12550 | G | 4011 | West Balmville | N |  | 6 | [13 empty] | NM | N | (1) SOLAREDGE SE6000A | 2015-01-22 | 2015-02-05 | 10 | 2015-02-05 | [14 empty] | 2015-02-09 | 2015-02-17 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07525 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6094 | Manchester | N |  | 3 | [13 empty] | NM | N | SOLAREDGE SE3000A | 2015-01-22 | 2015-02-05 | 10 | 2015-02-05 | [14 empty] | 2015-08-26 | 2015-09-02 |  | Y
Central Hudson |  | SolarCity | CH-07921 | Newburgh | Maybrook |  | 12543 | G | 5052 | Maybrook | TBD |  | 5 | [13 empty] | NM | N | (1) SOLAREDGE SE5000A | 2015-01-22 | 2015-02-05 | 10 | 2015-02-05 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | Sungevity Inc | CH-09181 | Kingston | Napanoch | Ulster | 12458 | G | 3071 | Honk Falls | N |  | 9.8 | [13 empty] | NM | N | SMA SB6000TL-US-22 240 SMA SB3800TL-US-22 240 | 2015-01-22 | 2015-02-05 | 10 | 2015-02-05 | [14 empty] | 2015-05-06 | 2015-05-13 |  | Y
Central Hudson |  | Verengo Solar | CH-09771 | Newburgh | Marlboro | Ulster | 12542 | G | 5004 | Marlboro | N |  | 7.09 | [13 empty] | NM | N | (33) ENPHASE ENERGY M215-60-2LL-S22-IG | 2015-01-22 | 2015-02-05 | 10 | 2015-02-05 | [14 empty] | 2015-04-16 | 2015-04-23 |  | Y
Central Hudson |  | Verengo Solar | CH-09854 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6011 | Sand Dock | N |  | 4.945 | [13 empty] | NM | N | 23 - ENPHASE ENERGY M215 | 2015-01-22 | 2015-02-05 | 10 | 2015-02-05 | [14 empty] | 2015-05-13 | 2015-05-19 |  | Y
Central Hudson |  | Verengo Solar | CH-09896 | Poughkeepsie | Hyde Pk |  | 12538 | G | 6075 | East Park | TBD |  | 4.085 | [13 empty] | NM | N | 19 - ENPHASE ENERGY M215 | 2015-01-22 | 2015-02-05 | 10 | 2015-02-05 | [17 empty] | W
Central Hudson |  | Verengo Solar | CH-09899 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8091 | Fishkill Plains | N |  | 5.8 | [13 empty] | NM | N | (27) ENPHASE ENERGY M215-60-2LL-S22-IG | 2015-01-22 | 2015-02-05 | 10 | 2015-02-05 | [14 empty] | 2015-04-23 | 2015-04-30 |  | Y
Central Hudson |  | Verengo Solar | CH-09918 | Newburgh | Campbell Hall | Orange | 10916 | G | 5051 | Maybrook | N |  | 8.17 | [13 empty] | NM | N | (38) ENPHASE ENERGY M215-60-2LL-S22-IG | 2015-01-22 | 2015-02-05 | 10 | 2015-02-05 | [14 empty] | 2015-05-15 | 2015-05-21 |  | Y
Central Hudson |  | Verengo Solar | CH-09932 | Newburgh | Marlboro |  | 12542 | G | 5002 | Marlboro | TBD |  | 7.52 | [13 empty] | NM | N | (35) ENPHASE ENERGY M215-60-2LL-S22-IG | 2015-01-22 | 2015-02-05 | 10 | 2015-02-05 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | SolarCity | CH-05091 | Newburgh | Montgomery | Orange | 12549 | G | 5073 | Montgomery | N |  | 11 | [13 empty] | NM | N | (1) ABB PVI-5000-OUTD (1) ABB PVI-6000-OUTD | 2015-01-23 | 2015-02-06 | 10 | 2015-02-06 | [14 empty] | 2015-03-04 | 2015-03-11 |  | Y
Central Hudson |  | SolarCity | CH-05776 | Kingston | Glasco | Ulster | 12432 | G | 2015 | Lincoln Park | N |  | 5 | [13 empty] | NM | N | (1) SOLAREDGE SE5000A | 2015-01-23 | 2015-02-06 | 10 | 2015-02-06 | [14 empty] | 2015-02-09 | 2015-02-17 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06092 | Fishkill | Fishkill |  | 12524 | G | 8065 | Merritt Park | TBD |  | 11 | [13 empty] | NM | N | (1) ABB PVI-5000-OUTD (1) ABB PVI-6000-OUTD | 2015-01-23 | 2015-02-06 | 10 | 2015-02-06 | [17 empty] | W
Central Hudson |  | Verengo Solar | CH-09793 | Kingston | Saugerties |  | 12477 | G | 2015 | Lincoln Park | TBD |  | 13.97 | [13 empty] | NM | N | (65) ENPHASE ENERGY M215-60-2LL-S22-IG | 2015-01-23 | 2015-02-06 | 10 | 2015-02-06 | [8 empty] | 350 | 350 | [7 empty] | W |  | Customer already had net meter prior to application. Transformer upgrade required to accommodate PV installation. 7/17/15 As per customer, no longer installing solar.
Central Hudson |  | SolarCity | CH-05218 | Poughkeepsie | Rhinebeck |  | 12572 | G | 7053 | Rhinebeck | TBD |  | 3.6 | [13 empty] | NM | N | ABB PVI-3.6 | 2015-01-26 | 2015-02-09 | 10 | 2015-02-09 | [17 empty] | W
Central Hudson |  | SolarCity | CH-05354 | Kingston | Lk Katrine | Ulster | 12449 | G | 2016 | Lincoln Park | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000-OUTD US | 2015-01-26 | 2015-02-09 | 10 | 2015-02-09 | [14 empty] | 2015-03-02 | 2015-03-09 |  | Y
Central Hudson |  | SolarCity | CH-06127 | Fishkill | Stormvl | Dutchess | 12582 | G | 8071 | Shenandoah | N |  | 10.2 | [13 empty] | NM | N | (1) ABB PVI-6000-OUTD (1) ABB PVI-4.2-OUTD-S | 2015-01-26 | 2015-02-09 | 10 | 2015-02-09 | [14 empty] | 2015-05-01 | 2015-05-08 |  | Y
Central Hudson |  | SolarCity | CH-06328 | Newburgh | Marlboro |  | 12542 | G | 5001 | Marlboro | TBD |  | 3 | [13 empty] | NM | N | (1) ABB PVI-3.0-OUTD-S-US-Z | 2015-01-26 | 2015-02-09 | 10 | 2015-02-09 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | SolarCity | CH-06620 | Poughkeepsie | Poughkeepsie |  | 12603 | G | 6044 | Spackenkill | TBD |  | 6 | [13 empty] | NM | N | ABB PVI-6000 | 2015-01-26 | 2015-02-09 | 10 | 2015-02-09 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | SolarCity | CH-06844 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8095 | Fishkill Plains | N |  | 10 | [13 empty] | NM | N | (2) SOLAREDGE SE5000A | 2015-02-03 | 2015-02-12 | 7 | 2015-02-12 | [14 empty] | 2015-05-01 | 2015-05-08 |  | Y
Central Hudson |  | SolarCity | CH-06914 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8093 | Fishkill Plains | N |  | 3 | [13 empty] | NM | N | (1) ABB PVI-3.0-OUTD-S | 2015-01-26 | 2015-02-09 | 10 | 2015-02-09 | [14 empty] | 2015-08-17 | 2015-08-24 |  | Y
Central Hudson |  | SolarCity | CH-07247 | Kingston | Lk Katrine | Ulster | 12449 | G | 2016 | Lincoln Park | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000-OUTD US-Z-A | 2015-01-26 | 2015-02-09 | 10 | 2015-02-09 | [14 empty] | 2015-03-09 | 2015-03-16 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07472 | Newburgh | Campbell Hall |  | 10916 | G | 5051 | Maybrook | TBD |  | 7.6 | [13 empty] | NM | N | (1) SOLAREDGE SE7600A | 2015-01-26 | 2015-02-09 | 10 | 2015-02-09 | [17 empty] | W
Central Hudson |  | SolarCity | CH-07899 | Newburgh | New Paltz |  | 12561 | G | 5024 | Ohioville | TBD |  | 5 | [9 empty] | 10 |  |  |  | NM | N | (1) ABB PVI-5000-OUTD | 2015-01-26 | 2015-02-09 | 10 | 2015-02-09 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | Sungevity Inc | CH-09251 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6096 | Manchester | N |  | 14.4 | [13 empty] | NM | N | 2 - ABB 4.2 1 - ABB PVI 6000 | 2015-01-26 | 2015-02-09 | 10 | 2015-02-09 | [14 empty] | 2015-03-17 | 2015-03-23 |  | Y
Central Hudson |  | SolarCity | CH-05155 | Newburgh | Highland | Ulster | 12528 | G | 5083 | Highland | N |  | 3 | [13 empty] | NM | N | ABB PVI-3.0 | 2015-01-27 | 2015-02-10 | 10 | 2015-02-10 | [14 empty] | 2015-04-27 | 2015-05-04 |  | Y
Central Hudson |  | SolarCity | CH-05293 | Newburgh | Clintondale | Ulster | 12515 | G | 5012 | Modena | N |  | 7.6 | [13 empty] | NM | N | (1) SOLAREDGE SE7600A | 2015-01-27 | 2015-02-10 | 10 | 2015-02-10 | [14 empty] | 2015-05-01 | 2015-05-08 |  | Y
Central Hudson |  | SolarCity | CH-05405 | Newburgh | Newburgh | Orange | 12550 | G | 4011 | West Balmville | N |  | 12 | [13 empty] | NM | N | (2) ABB PVI-6000-OUTD-US-Z-A | 2015-01-27 | 2015-02-10 | 10 | 2015-02-10 | [14 empty] | 2015-03-09 | 2015-03-16 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-05976 | Newburgh | Highland | Ulster | 12528 | G | 5081 | Highland | N |  | 5 | [13 empty] | NM | N | ABB PVI-5000 | 2015-01-27 | 2015-02-10 | 10 | 2015-02-10 | [14 empty] | 2015-04-14 | 2015-04-21 |  | Y
Central Hudson |  | SolarCity | CH-06532 | Kingston | Glenford | Ulster | 12433 | G | 3013 | Woodstock | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000-OUTD-US-Z-A | 2015-01-27 | 2015-02-10 | 10 | 2015-02-10 | [14 empty] | 2015-09-17 | 2015-09-24 |  | Y
Central Hudson |  | SolarCity | CH-06942 | Fishkill | Beacon | Dutchess | 12508 | G | 8085 | Tioronda | N |  | 3 | [13 empty] | NM | N | (1) ABB PVI-3.0-OUTD-S | 2015-01-27 | 2015-02-10 | 10 | 2015-02-10 | [14 empty] | 2015-03-31 | 2015-04-08 |  | Y
Central Hudson |  | Sungevity Inc | CH-09332 | Poughkeepsie | Tivoli | Dutchess | 12583 | G | 7062 | Milan | N |  | 5 | [13 empty] | NM | N | SMA AMERICA SB5000TL-US-22 | 2015-02-24 | 2015-03-02 | 4 | 2015-03-02 | [14 empty] | 2015-03-30 | 2015-03-31 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Verengo Solar | CH-09776 | Kingston | Saugerties | Ulster | 12477 | G | 2015 | Lincoln Park | N |  | 5.59 | [13 empty] | NM | N | 26 ENPHASE M215-60-2LL-S22-IG | 2015-01-27 | 2015-02-10 | 10 | 2015-02-10 | [14 empty] | 2015-03-25 | 2015-04-01 |  | Y
Central Hudson |  | Verengo Solar | CH-09862 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8023 | Knapps Corners | N |  | 6.45 | [13 empty] | NM | N | (30) ENPHASE ENERGY M215-60-2LL-S22-IG | 2015-01-27 | 2015-02-10 | 10 | 2015-02-10 | [14 empty] | 2015-05-22 | 2015-06-01 |  | Y
Central Hudson |  | New York State Solar Farm | CH-04016 | Newburgh | Montgomery | Orange | 12549 | G | 5071 | Montgomery | N |  | 8.4 | [13 empty] | NM | N | (2) POWERONE PVI 4.2 | 2015-02-05 | 2015-02-20 | 10 | 2015-02-20 | [14 empty] | 2015-03-31 | 2015-04-08 |  | Y
Central Hudson |  | NRG Home Solar | CH-04799 | Fishkill | Beacon | Dutchess | 12508 | G | 8015 | Forgebrook | N |  | 3.655 | [13 empty] | NM | N | (17) ENPHASE ENERGY M-215-60-2LL-S22-IG | 2015-01-28 | 2015-02-10 | 9 | 2015-02-10 | [14 empty] | 2015-04-14 | 2015-04-21 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00933 | Poughkeepsie | Poughquag | Dutchess | 12570 | G | 6055 | Todd Hill | N |  | 7.74 | [13 empty] | NM | N | 36 - ENPHASE M215 | 2015-01-28 | 2015-02-11 | 10 | 2015-02-11 | [14 empty] | 2015-03-16 | 2015-03-23 |  | Y
Central Hudson |  | Direct Energy Solar | CH-01077 | Newburgh | Wallkill | Ulster | 12589 | G | 5043 | East Walden | N | CH-00969 | 0.43 | [13 empty] | NM | N | ENPHASE 215 (2) | 2015-01-28 | 2015-02-10 | 9 | 2015-02-10 | [14 empty] | 2015-04-20 | 2015-04-27 |  | Y
Central Hudson |  | SolarCity | CH-04967 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8096 | Fishkill Plains | N |  | 3 | [13 empty] | NM | N | (1) ABB PVI-3.0-OUTD-S | 2015-01-28 | 2015-02-10 | 9 | 2015-02-10 | [14 empty] | 2015-03-31 | 2015-04-08 |  | Y
Central Hudson |  | SolarCity | CH-05127 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7053 | Rhinebeck | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000 | 2015-02-18 | 2015-02-23 | 3 | 2015-02-23 | [14 empty] | 2015-03-17 | 2015-03-23 |  | Y
Central Hudson |  | SolarCity | CH-07303 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6051 | Todd Hill | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000-OUTD | 2015-01-28 | 2015-02-11 | 10 | 2015-02-11 | [14 empty] | 2015-02-17 | 2015-02-23 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07515 | Kingston | Kingston | Ulster | 12401 | G | 2013 | Lincoln Park | N |  | 7.2 | [13 empty] | NM | N | ABB PVI-3.6-OUTD-S-US-Z | 2015-01-28 | 2015-02-10 | 9 | 2015-02-10 | [14 empty] | 2015-03-09 | 2015-03-16 |  | Y
Central Hudson |  | Verengo Solar | CH-09914 | Newburgh | Marlboro | Ulster | 12542 | G | 5004 | Marlboro | N |  | 6.88 | [13 empty] | NM | N | (32) ENPHASE ENERGY M215-60-2LL-S22-IG | 2015-01-28 | 2015-02-10 | 9 | 2015-02-10 | [14 empty] | 2015-05-05 | 2015-05-11 |  | Y
Central Hudson |  | Kasselman Solar | CH-03524 | Catskill | Coeymans | Albany | 12045 | G | 1082 | New Baltimore | N |  | 10.5 | [13 empty] | NM | N | 42 ENPHASE M250 | 2015-02-18 | 2015-03-20 | 22 | 2015-03-20 | [14 empty] | 2015-07-29 | 2015-08-10 |  | Y
Central Hudson |  | NRG Home Solar | CH-04522 | Kingston | Kingston | Ulster | 12401 | G | 2094 | Hurley Ave | N |  | 3.44 | [13 empty] | NM | N | 16 ENPHASE M-215-60-2LL-S22-IG | 2015-01-29 | 2015-02-10 | 8 | 2015-02-10 | [14 empty] | 2015-08-27 | 2015-09-03 |  | Y
Central Hudson |  | SolarCity | CH-05158 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8094 | Fishkill Plains | N |  | 7.6 | [13 empty] | NM | N | (1) SOLAREDGE SE7600A | 2015-02-06 | 2015-02-13 | 5 | 2015-02-13 | [14 empty] | 2015-02-24 | 2015-03-03 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06738 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6093 | Manchester | N |  | 5 | [13 empty] | NM | N | ABB PVI-5000-OUTD | 2015-01-29 | 2015-02-11 | 9 | 2015-02-11 | [14 empty] | 2015-05-26 | 2015-06-02 |  | Y
Central Hudson |  | SolarCity | CH-07119 | Newburgh | Cornwall | Orange | 12518 | G | 4041 | Union Ave | N |  | 5 | [13 empty] | NM | N | (1) ABB PVI-5000-OUTD | 2015-01-29 | 2015-02-11 | 9 | 2015-02-11 | [14 empty] | 2015-03-02 | 2015-03-09 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Sungevity Inc | CH-09207 | Kingston | Lk Katrine | Ulster | 12449 | G | 2011 | Lincoln Park | N |  | 5 | [13 empty] | NM | N | SMA AMERICA SB5000TL-US-22 | 2015-01-29 | 2015-02-10 | 8 | 2015-02-10 | [14 empty] | 2015-04-29 | 2015-05-06 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03577 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8091 | Fishkill Plains | N |  | 10 | [13 empty] | NM | N | (1) SOLAREDGE 10000 | 2015-01-30 | 2015-02-11 | 8 | 2015-02-11 | [14 empty] | 2015-12-17 | 2015-12-17 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03679 | Newburgh | New Paltz | Ulster | 12561 | G | 5031 | Galeville | N |  | 6 | [13 empty] | NM | N | (1) SOLAREDGE SE6000 | 2015-01-30 | 2015-02-11 | 8 | 2015-02-11 | [14 empty] | 2015-04-02 | 2015-04-10 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03732 | Kingston | Kerhonkson | Ulster | 12446 | G | 3082 | Kerhonkson | N |  | 10 | [13 empty] | NM | N | SOLAREDGE 10000 A-US | 2015-01-30 | 2015-02-10 | 7 | 2015-02-10 | [8 empty] | 350 | 350 |  |  |  |  | 2015-04-02 | 2015-04-02 |  | Y
Central Hudson |  | SolarCity | CH-05527 | Catskill | Medusa | Albany | 12120 | G | 1092 | Westerlo | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A-US | 2015-01-30 | 2015-02-10 | 7 | 2015-02-10 | [14 empty] | 2015-03-30 | 2015-04-06 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00973 | Newburgh | New Windsor | Orange | 12553 | G | 4097 | Bethlehem Rd | N |  | 8.17 | [13 empty] | NM | N | (38) ENPHASE M215 | 2015-02-02 | 2015-02-12 | 8 | 2015-02-12 | [14 empty] | 2015-04-06 | 2015-04-13 |  | Y
Central Hudson |  | SolarCity | CH-05396 | Newburgh | Wallkill | Ulster | 12589 | G | 5041 | East Walden | N |  | 7.6 | [13 empty] | NM | N | (1) SOLAREDGE SE7600A | 2015-02-02 | 2015-02-12 | 8 | 2015-02-12 | [14 empty] | 2015-03-06 | 2015-03-13 |  | Y
Central Hudson |  | SolarCity | CH-06577 | Kingston | Saugerties | Ulster | 12477 | G | 3014 | Woodstock | N |  | 4.2 | [13 empty] | NM | N | ABB PVI-4.2-OUTD-S US | 2015-02-02 | 2015-02-10 | 6 | 2015-02-10 | [14 empty] | 2015-03-23 | 2015-03-30 |  | Y
Central Hudson |  | SolarCity | CH-07616 | Newburgh | Rock Tvrn | Orange | 12575 | G | 5052 | Maybrook | N |  | 3 | [13 empty] | NM | N | (1) ABB PVI-3.0-OUTD-S-US | 2015-02-02 | 2015-02-12 | 8 | 2015-02-12 | [14 empty] | 2015-03-17 | 2015-03-24 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03607 | Newburgh | Gardiner | Ulster | 12525 | G | 5011 | Modena | N |  | 10 | [13 empty] | NM | N | (1) SOLAREDGE SE10000 | 2015-02-03 | 2015-02-12 | 7 | 2015-02-12 | [8 empty] | 350 | 350 |  |  |  |  | 2015-09-25 | 2015-10-02 |  | Y
Central Hudson |  | NRG Home Solar | CH-04268 | Kingston | Woodstock | Ulster | 12498 | G | 3012 | Woodstock | N |  | 3.01 | [13 empty] | NM | N | 14 ENPHASE M-215-60-2LL-S22-IG | 2015-02-03 | 2015-02-11 | 6 | 2015-02-11 | [14 empty] | 2015-09-01 | 2015-09-09 |  | Y
Central Hudson |  | NRG Home Solar | CH-04401 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8092 | Fishkill Plains | N |  | 7.31 | [13 empty] | NM | N | (34) ENPHASE ENERGY M-215-60-2LL-S22-IG | 2015-02-03 | 2015-02-12 | 7 | 2015-02-12 | [14 empty] | 2015-09-30 | 2015-10-07 |  | Y
Central Hudson |  | NRG Home Solar | CH-04781 | Newburgh | Salisbury Mls | Orange | 12577 | G | 4095 | Bethlehem Rd | N |  | 5.16 | [13 empty] | NM | N | (24) ENPHASE ENERGY M-215-60-2LL-S22-IG | 2015-02-03 | 2015-02-12 | 7 | 2015-02-12 | [14 empty] | 2015-08-11 | 2015-08-18 |  | Y
Central Hudson |  | SolarCity | CH-05661 | Kingston | Kingston |  | 12401 | G | 1022 | East Kingston | TBD |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A US | 2015-02-03 | 2015-02-11 | 6 | 2015-02-11 | [17 empty] | W
Central Hudson |  | SolarCity | CH-06498 | Kingston | Hurley |  | 12443 | G | 2094 | Hurley Ave | TBD |  | 11 | [13 empty] | NM | N | SOLAREDGE SE6000A US SOLAREDGE SE5000A US | 2015-02-03 | 2015-02-11 | 6 | 2015-02-11 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | SolarCity | CH-06901 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8072 | Shenandoah | N |  | 8.8 | [13 empty] | NM | N | (1) SOLAREDGE SE3800A (1) SOLAREDGE SE5000A | 2015-02-03 | 2015-02-12 | 7 | 2015-02-12 | [14 empty] | 2015-08-07 | 2015-08-13 |  | Y
Central Hudson |  | Sungevity Inc | CH-09267 | Kingston | Accord | Ulster | 12404 | G | 3081 | Kerhonkson | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE 6000A-US | 2015-02-03 | 2015-02-11 | 6 | 2015-02-11 | [14 empty] | 2015-04-08 | 2015-04-15 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-03397 | Newburgh | Montgomery | Orange | 12549 | G | 5073 | Montgomery | N |  | 9.8 | [13 empty] | NM | N | (1) SMA AMERICA SB3800TL (1) SMA AMERICA SB6000TL | 2015-02-04 | 2015-02-19 | 10 | 2015-02-19 | [14 empty] | 2015-07-01 | 2015-07-09 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-03478 | Newburgh | New Windsor | Orange | 12553 | G | 4094 | Bethlehem Rd | N |  | 5 | [13 empty] | NM | N | SMA AMERICA SB5000TL | 2015-02-04 | 2015-02-19 | 10 | 2015-02-19 | [14 empty] | 2015-04-22 | 2015-04-28 |  | Y
Central Hudson |  | NRG Home Solar | CH-04729 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8094 | Fishkill Plains | N |  | 7.74 | [13 empty] | NM | N | (36) ENPHASE ENERGY M-215-60-2LL-S22-IG | 2015-02-04 | 2015-02-19 | 10 | 2015-02-19 | [14 empty] | 2015-04-17 | 2015-04-24 |  | Y
Central Hudson |  | SolarCity | CH-05305 | Newburgh | Wallkill |  | 12589 | G | 5033 | Galeville | TBD |  | 8.4 | [13 empty] | NM | N | (2) ABB PVI-4.2-OUTD-S-US | 2015-02-04 | 2015-02-19 | 10 | 2015-02-19 | [17 empty] | W |  | Customer already had net meter prior to application. 2/16/15 Company Holiday.
Central Hudson |  | SolarCity | CH-05492 | Catskill | Haines Falls |  | 12436 | G | 2385 | Lawrenceville | TBD |  | 3 | [13 empty] | NM | N | SOLAREDGE SE3000A-US-ZB-U | 2015-02-04 | 2015-02-13 | 7 | 2015-02-13 | [17 empty] | W |  | Customer already had net meter prior to application. 6/24/15 As per customer, she will not be having solar installed.
Central Hudson |  | SolarCity | CH-05685 | Kingston | Mt Tremper | Ulster | 12457 | G | 3012 | Woodstock | N |  | 3 | [13 empty] | NM | N | ABB PVI 3.0 | 2015-02-04 | 2015-02-12 | 6 | 2015-02-12 | [8 empty] | 350 | 350 |  | 2015-02-13 | 2015-02-13 | 2015-04-13 | 2016-02-18 | 2016-02-25 |  | Y |  | Customer already had net meter prior to application.Transformer upgrade required to accommodate PV installation. Utility System Upgrade Costs TBD.
Central Hudson |  | SolarCity | CH-05890 | Poughkeepsie | Lagrangevl |  | 12540 | G | 6057 | Todd Hill | TBD |  | 10 | [13 empty] | NM | N | 2 - SOLAREDGE SE5000A-US | 2015-02-04 | 2015-02-18 | 9 | 2015-02-18 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | SolarCity | CH-06015 | Fishkill | Wappingrs Fls |  | 12590 | G | 8091 | Fishkill Plains | TBD |  | 7.6 | [13 empty] | NM | N | (1) SOLAREDGE SE7600A-US | 2015-02-04 | 2015-02-19 | 10 | 2015-02-19 | [17 empty] | W |  | 2/16/15 Company Holiday.
Central Hudson |  | SolarCity | CH-06054 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8091 | Fishkill Plains | N |  | 10 | [13 empty] | NM | N | (2) ABB PVI-5000-OUTD-US | 2015-02-04 | 2015-02-19 | 10 | 2015-02-19 | [14 empty] | 2015-08-26 | 2015-09-02 |  | Y
Central Hudson |  | SolarCity | CH-06281 | Newburgh | New Windsor |  | 12553 | G | 4052 | Union Ave | TBD |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A-US-ZB-U | 2015-02-04 | 2015-02-19 | 10 | 2015-02-19 | [17 empty] | W |  | Customer already had net meter prior to application. 2/16/15 Company Holiday.
Central Hudson |  | SolarCity | CH-06396 | Newburgh | Cornwall | Orange | 12518 | G | 4041 | Union Ave | N |  | 5 | [13 empty] | NM | N | ABB PVI-5000-OUTD-US-Z-A | 2015-02-04 | 2015-02-19 | 10 | 2015-02-19 | [14 empty] | 2015-05-05 | 2015-05-11 |  | Y
Central Hudson |  | SolarCity | CH-06406 | Newburgh | Washingtonvl | Orange | 10992 | G | 5052 | Maybrook | N |  | 9.6 | [13 empty] | NM | N | (1) ABB PVI-6000-OUTD-US (1) ABB PVI-3.6-OUTD-S-US | 2015-02-04 | 2015-02-19 | 10 | 2015-02-19 | [14 empty] | 2015-04-20 | 2015-04-27 |  | Y
Central Hudson |  | SolarCity | CH-06634 | Poughkeepsie | Poughkeepsie |  | 12601 | G | 6042 | Spackenkill | TBD |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE76000A-US | 2015-02-04 | 2015-02-11 | 5 | 2015-02-11 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | SolarCity | CH-06795 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8091 | Fishkill Plains | N |  | 11 | [13 empty] | NM | N | ABB PVI-6000-OUTD-US-Z-A ABB PVI-5000-OUTD-US-Z-A | 2015-02-04 | 2015-02-19 | 10 | 2015-02-19 | [14 empty] | 2015-05-18 | 2015-05-26 |  | Y
Central Hudson |  | SolarCity | CH-06875 | Fishkill | Fishkill |  | 12524 | G | 8094 | Fishkill Plains | TBD |  | 3 | [13 empty] | NM | N | (1) SOLAREDGE SE3000A-US | 2015-02-04 | 2015-02-19 | 10 | 2015-02-19 | [14 empty] | 2015-04-02 | 2015-04-10 |  | W |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07833 | Newburgh | Mountainvl | Orange | 10953 | G | 4095 | Bethlehem Rd | Y | CH-05085 | 12 | [13 empty] | NM | N | (2) SOLAREDGE SE6000A | 2015-02-04 | 2015-02-19 | 10 | 2015-02-19 | [8 empty] | 350 | 350 |  | 2015-02-24 | 2015-02-24 | 2015-03-10 | 2015-03-10 | 2015-03-17 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07869 | Kingston | Kingston |  | 12401 | G | 2013 | Lincoln Park | TBD |  | 3.6 | [13 empty] | NM | N | ABB PVI-3.6-OUTD-S-US | 2015-02-04 | 2015-02-11 | 5 | 2015-02-11 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | SolarCity | CH-07902 | Newburgh | Newburgh |  | 12550 | G | 5004 | Marlboro | TBD |  | 3 | [13 empty] | NM | N | (1) ABB PVI-3.0-OUTD | 2015-02-04 | 2015-02-19 | 10 | 2015-02-19 | [17 empty] | W |  | Customer already had net meter prior to application. 2/16/15 Company Holiday.
Central Hudson |  | Solar Generation | CH-08109 | Kingston | Hurley | Ulster | 12443 | G | 2094 | Hurley Ave | N |  | 10 | [13 empty] | NM | N | 2 SMA SB 5000 TL | 2015-02-04 | 2015-02-13 | 7 | 2015-02-13 | [14 empty] | 2015-06-11 | 2015-06-18 |  | Y
Central Hudson |  | Solar Generation | CH-08203 | Catskill | Elka Pk | Ulster | 12417 | G | 2385 | Lawrenceville | N |  | 3 | [13 empty] | NM | N | SMA SB 3000 TL | 2015-02-04 | 2015-02-13 | 7 | 2015-02-13 | [14 empty] | 2015-10-08 | 2015-10-15 |  | Y
Central Hudson |  | Solar Generation | CH-08206 | Kingston | W Hurley | Ulster | 12491 | G | 2094 | Hurley Ave | N |  | 10.8 | [13 empty] | NM | N | SMA SB 3800 TL SMA SB 7000 TL | 2015-02-04 | 2015-02-13 | 7 | 2015-02-13 | [8 empty] | 350 | 350 |  | 2015-02-17 | 2015-02-17 | 2015-04-13 | 2015-06-08 | 2015-06-15 |  | Y
Central Hudson |  | Verengo Solar | CH-09808 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8092 | Fishkill Plains | N |  | 5.59 | [13 empty] | NM | N | (26) ENPHASE ENERGY M215-60-2LL-S22-IG | 2015-02-04 | 2015-02-19 | 10 | 2015-02-19 | [14 empty] | 2015-06-08 | 2015-06-12 |  | Y
Central Hudson |  | You Save Green | CH-09960 | Newburgh | Rock Tavern | Orange | 12575 | G | 4097 | Bethlehem Rd | N |  | 6 | [13 empty] | NM | N | (24) ENPHASE M250 | 2015-02-04 | 2015-02-19 | 10 | 2015-02-19 | [14 empty] | 2015-10-23 | 2015-11-04 |  | Y
Central Hudson |  | SolarCity | CH-06027 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8052 | North Chelsea | N |  | 7.6 | [13 empty] | NM | N | (2) SOLAREDGE SE3800A-US-ZB-U | 2015-02-05 | 2015-02-20 | 10 | 2015-02-20 | [14 empty] | 2015-03-24 | 2015-03-31 |  | Y
Central Hudson |  | SolarCity | CH-06045 | Fishkill | New Hamburg | Dutchess | 12590 | G | 8052 | North Chelsea | N |  | 3 | [13 empty] | NM | N | (1) ABB PVI-3.0-OUTD-S | 2015-02-05 | 2015-02-20 | 10 | 2015-02-20 | [14 empty] | 2015-03-23 | 2015-03-30 |  | Y
Central Hudson |  | SolarCity | CH-06377 | Newburgh | New Windsor | Orange | 12553 | G | 4095 | Bethlehem Rd | N |  | 11 | [13 empty] | NM | N | (1) ABB PVI-6000-OUTD (1) ABB PVI-5000-OUTD | 2015-02-05 | 2015-02-20 | 10 | 2015-02-20 | [14 empty] | 2015-03-02 | 2015-03-09 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Solar Generation | CH-08075 | Kingston | Kerhonkson | Ulster | 12446 | G | 3081 | Kerhonkson | N |  | 10 | [13 empty] | NM | N | 2 SMA SB 5000 TL | 2015-02-05 | 2015-02-13 | 6 | 2015-02-13 | [14 empty] | 2015-05-06 | 2015-05-13 |  | Y
Central Hudson |  | Solar Generation | CH-08111 | Kingston | Saugerties | Ulster | 12477 | G | 3003 | Saugerties | N |  | 7.7 | [13 empty] | NM | N | SMA SB 7700 TL | 2015-02-05 | 2015-02-13 | 6 | 2015-02-13 | [14 empty] | 2015-04-08 | 2015-04-15 |  | Y
Central Hudson |  | New York State Solar Farm | CH-04048 | Newburgh | Gardiner | Ulster | 12525 | G | 5034 | Galeville | N |  | 12 | [13 empty] | NM | N | (2) SMA AMERICA SB 6000TL | 2015-02-06 | 2015-02-20 | 9 | 2015-02-20 | [8 empty] | 350 | 350 |  |  |  |  | 2015-06-25 | 2015-07-01 |  | Y
Central Hudson |  | SolarCity | CH-05658 | Kingston | Connelly | Ulster | 12417 | G | 1024 | East Kingston | N |  | 3.8 | [13 empty] | NM | N | SOLAREDGE SE3800A-US | 2015-02-06 | 2015-02-13 | 5 | 2015-02-13 | [14 empty] | 2015-02-17 | 2015-02-24 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-05956 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7013 | Hibernia | N |  | 8 | [13 empty] | NM | N | 1 - SOLAREDGE SE3000A-US 1 - SOLAREDGE SE5000A-US | 2015-02-18 | 2015-02-23 | 3 | 2015-02-23 | [14 empty] | 2015-06-22 | 2015-06-29 |  | Y
Central Hudson |  | SolarCity | CH-06446 | Catskill | Westerlo | Albany | 12193 | G | 1092 | Westerlo | N |  | 12 | [13 empty] | NM | N | 2 SOLAREDGE SE6000A US-ZB-U | 2015-02-06 | 2015-02-13 | 5 | 2015-02-13 | [8 empty] | 350 | 350 |  |  |  |  | 2015-05-01 | 2015-05-08 |  | Y
Central Hudson |  | SolarCity | CH-07132 | Newburgh | Washingtonvl | Orange | 10992 | G | 4097 | Bethlehem Rd | N |  | 10 | [13 empty] | NM | N | (2) ABB PVI-5000 | 2015-02-06 | 2015-02-20 | 9 | 2015-02-20 | [14 empty] | 2015-03-17 | 2015-03-24 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | RGS Energy | CH-03009 | Kingston | Bearsvl | Ulster | 12409 | G | 3012 | Woodstock | N |  | 10 | [13 empty] | NM | N | FRONIUS IG PLUS 10.0-1 UNI | 2015-02-09 | 2015-02-19 | 7 | 2015-02-19 | [8 empty] | 350 | 350 |  | 2015-03-27 | 2015-03-27 | 2015-04-13 | 2015-09-11 | 2015-09-18 |  | Y
Central Hudson |  | NRG Home Solar | CH-04540 | Kingston | Kingston | Ulster | 12401 | G | 2013 | Lincoln Park | N |  | 6.88 | [13 empty] | NM | N | 32 ENPHASE M-215-60-2LL-S22-IG | 2015-02-09 | 2015-02-19 | 7 | 2015-02-19 | [14 empty] | 2015-09-04 | 2015-09-14 |  | Y
Central Hudson |  | SolarCity | CH-05197 | Newburgh | Newburgh | Orange | 12550 | G | 4014 | West Balmville | N |  | 7.8 | [13 empty] | NM | N | (1) ABB PVI-4.2-OUTD (1) ABB PVI-3.6-OUTD | 2015-02-19 | 2015-02-26 | 5 | 2015-02-26 | [14 empty] | 2015-03-11 | 2015-03-11 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-05254 | Poughkeepsie | Salt Pt | Dutchess | 12578 | G | 7011 | Hibernia | Y | CH-05254 | 10.8 | [13 empty] | NM | N | 1 - ABB PVI-4.2, 1 - ABB PVI-3.6 & 1 - ABB PVI-3.0 | 2015-02-09 | 2015-02-20 | 8 | 2015-02-20 | [8 empty] | 350 | 350 |  |  |  |  | 2015-03-23 | 2015-03-27 |  | Y
Central Hudson |  | Verengo Solar | CH-09873 | Newburgh | Newburgh | Orange | 12550 | G | 4023 | Coldenham | N |  | 6.45 | [13 empty] | NM | N | (30)ENPHASE ENERGY M215-60-2LL-S22-IG | 2015-02-09 | 2015-02-20 | 8 | 2015-02-20 | [14 empty] | 2015-06-04 | 2015-06-11 |  | Y
Central Hudson |  | SolarCity | CH-05839 | Poughkeepsie | Hyde Pk |  | 12538 | G | 6073 | East Park | TBD |  | 10 | [13 empty] | NM | N | 2 - SOLAREDGE SE5000A | 2015-02-10 | 2015-02-18 | 5 | 2015-02-18 | [17 empty] | W |  | 2/16/15 Company Holiday.
Central Hudson |  | SolarCity | CH-06402 | Newburgh | Rock Tvrn | Orange | 12575 | G | 4097 | Bethlehem Rd | N |  | 10.2 | [13 empty] | NM | N | (1) ABB PVI-3.0-OUTD-S (2) ABB PVI-3.6-OUTD-S | 2015-03-16 | 2015-03-23 | 5 | 2015-03-23 | [14 empty] | 2015-06-01 | 2015-06-03 |  | Y
Central Hudson |  | SolarCity | CH-06585 | Kingston | Kingston | Ulster | 12401 | G | 2091 | Hurley Ave | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A-US | 2015-02-10 | 2015-02-19 | 6 | 2015-02-19 | [14 empty] | 2015-02-19 | 2015-02-19 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07503 | Kingston | Kingston | Ulster | 12401 | G | 2093 | Hurley Ave | N |  | 6.6 | [13 empty] | NM | N | FRONIUS IG PLUS A 7.5 | 2015-02-10 | 2015-02-19 | 6 | 2015-02-19 | [14 empty] | 2015-05-05 | 2015-05-12 |  | Y
Central Hudson |  | SolarCity | CH-07648 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6066 | Inwood Ave | N | CH-23020 | 3 | [13 empty] | NM | N | ABB PVI-3.0-OUTD | 2015-03-23 | 2015-03-27 | 4 | 2015-03-27 | [14 empty] | 2015-04-08 | 2015-04-09 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07702 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6094 | Manchester | N |  | 3 | [13 empty] | NM | N | ABB PVI-3.0-OUTD | 2015-02-10 | 2015-02-18 | 5 | 2015-02-18 | [14 empty] | 2015-04-27 | 2015-05-01 |  | Y
Central Hudson |  | Solar Generation | CH-08253 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7051 | Rhinebeck | N |  | 10 | [13 empty] | NM | N | 2- SMA SB 5000 | 2015-02-10 | 2015-02-18 | 5 | 2015-02-18 | [14 empty] | 2015-05-07 | 2015-05-13 |  | Y
Central Hudson |  | Sunrun Inc. | CH-08358 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6046 | Spackenkill | N |  | 14.4 | [13 empty] | NM | N | 4 - ABB PVI-3.6 | 2015-02-10 | 2015-02-18 | 5 | 2015-02-18 | [14 empty] | 2015-05-08 | 2015-05-21 |  | Y
Central Hudson |  | Hudson Solar | CH-01218 | Newburgh | New Paltz | Ulster | 12561 | G | 5023 | Ohioville | N |  | 9 | [13 empty] | NM | N | (1) SMA AMERICA SB9000 | 2015-02-11 | 2015-02-24 | 8 | 2015-02-24 | [14 empty] | 2015-05-04 | 2015-05-11 |  | Y
Central Hudson |  | Hudson Solar | CH-01429 | Newburgh | New Paltz | Ulster | 12561 | G | 5023 | Ohioville | N |  | 10 | [13 empty] | NM | N | (2) SMA AMERICA SB5000 | 2015-02-11 | 2015-02-24 | 8 | 2015-02-24 | [14 empty] | 2015-05-04 | 2015-05-11 |  | Y
Central Hudson |  | Hudson Solar | CH-02063 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6011 | Sand Dock | N |  | 7.7 | [13 empty] | NM | N | SMA AMERICA SB7700 | 2015-02-11 | 2015-02-19 | 5 | 2015-02-19 | [14 empty] | 2015-07-09 | 2015-07-16 |  | Y
Central Hudson |  | Hudson Solar | CH-02094 | Poughkeepsie | Lagrangevl |  | 12540 | G | 6055 | Todd Hill | TBD |  | 10 | [13 empty] | NM | N | 2 - SMA AMERICA SB5000 | 2015-02-11 | 2015-02-19 | 5 | 2015-02-19 | [17 empty] | W |  | 2/19/15 Company Holiday.
Central Hudson |  | Hudson Solar | CH-02142 | Poughkeepsie | Rhinebeck |  | 12572 | G | 7052 | Rhinebeck | TBD |  | 7 | [13 empty] | NM | N | SMA AMERICA SB7000 | 2015-02-11 | 2015-02-19 | 5 | 2015-02-19 | [17 empty] | W |  | 2/16/15 Company Holiday.
Central Hudson |  | Hudson Solar | CH-02215 | Newburgh | Cornwall | Orange | 12518 | G | 4093 | Bethlehem Rd | N |  | 12 | [13 empty] | NM | N | (2) SMA AMERICA SB6000 | 2015-02-11 | 2015-02-24 | 8 | 2015-02-24 | [14 empty] | 2015-06-02 | 2015-06-09 |  | Y
Central Hudson |  | Hudson Solar | CH-02526 | Newburgh | Montgomery |  | 12549 | G | 4021 | Coldenham | TBD |  | 6 | [13 empty] | NM | N | (1) SMA AMERICA SB6000 | 2015-02-11 | 2015-02-24 | 8 | 2015-02-24 | [17 empty] | W |  | 2/16/15 Company Holiday.
Central Hudson |  | SolarCity | CH-05858 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 6074 | East Park | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A | 2015-02-11 | 2015-02-19 | 5 | 2015-02-19 | [14 empty] | 2016-06-23 | 2016-06-30 |  | Y
Central Hudson |  | SolarCity | CH-06648 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6046 | Spackenkill | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A | 2015-02-11 | 2015-02-19 | 5 | 2015-02-19 | [14 empty] | 2015-04-27 | 2015-05-04 |  | Y
Central Hudson |  | SolarCity | CH-06685 | Poughkeepsie | Hyde Pk |  | 12538 | G | 7041 | Staatsburg | TBD |  | 9 | [13 empty] | NM | N | 1 - SOLAREDGE SE6000A-US 1 - SOLAREDGE SE3000A-US | 2015-02-20 | 2015-02-27 | 5 | 2015-02-27 | [17 empty] | W
Central Hudson |  | SolarCity | CH-06730 | Poughkeepsie | Wappingrs Fls | Dutchess | 12590 | G | 6052 | Todd Hill | N |  | 7.2 | [13 empty] | NM | N | 2 - ABB PVI-3.6-OUTD | 2015-02-11 | 2015-02-19 | 5 | 2015-02-19 | [14 empty] | 2015-03-31 | 2015-04-08 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06734 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 7025 | Tinkertown | N |  | 7.6 | [13 empty] | NM | N | Fronius Primo 7.6 | 2015-02-11 | 2015-02-19 | 5 | 2015-02-19 | [8 empty] | 350 | 350 |  |  |  |  | 2015-10-06 | 2015-10-12 |  | Y
Central Hudson |  | SolarCity | CH-06773 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7062 | Milan | N |  | 9 | [13 empty] | NM | N | 1 - SOLAREDGE SE6000A 1 - SOLAREDGE SE3000A | 2015-02-11 | 2015-02-19 | 5 | 2015-02-19 | [14 empty] | 2015-03-31 | 2015-04-08 |  | Y
Central Hudson |  | SolarCity | CH-07654 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 7024 | Tinkertown | N |  | 7.6 | [13 empty] | NM | N | 2 - SOLAREDGE SE3800A | 2015-02-20 | 2015-02-27 | 5 | 2015-02-27 | [14 empty] | 2015-05-07 | 2015-05-13 |  | Y
Central Hudson |  | Sungevity Inc | CH-09355 | Fishkill | Fishkill | Dutchess | 12524 | G | 8065 | Merritt Park | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000-OUTD-US-A | 2015-02-11 | 2015-02-24 | 8 | 2015-02-24 | [14 empty] | 2015-05-28 | 2015-05-28 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03609 | Newburgh | Gardiner | Ulster | 12525 | G | 5011 | Modena | N |  | 20 | [13 empty] | RNM | N | (2) POWERONE PVI 10000 | 2015-02-12 | 2015-02-24 | 7 | 2015-02-24 | [14 empty] | 2015-03-13 | 2015-03-20 |  | Y
Central Hudson |  | New York State Solar Farm | CH-03959 | Newburgh | Highland | Ulster | 12528 | G | 5083 | Highland | N |  | 11 | [13 empty] | NM | N | 1- POWERONE PVI 5.0 1 - POWERONE PVI 6.0 | 2015-02-20 | 2015-03-03 | 7 | 2015-03-03 | [14 empty] | 2015-04-21 | 2015-04-28 |  | Y
Central Hudson |  | New York State Solar Farm | CH-04029 | Poughkeepsie | Millbrook | Dutchess | 12545 | G | 7025 | Tinkertown | N |  | 5 | [13 empty] | NM | N | SMA AMERICA 5.0 SB | 2015-02-20 | 2015-02-27 | 5 | 2015-02-27 | [14 empty] | 2015-05-07 | 2015-05-12 |  | Y
Central Hudson |  | SolarCity | CH-05367 | Newburgh | Highland | Ulster | 12528 | G | 5083 | Highland | N |  | 3 | [13 empty] | NM | N | ABB PVI-3.0 | 2015-02-12 | 2015-02-20 | 5 | 2015-02-20 | [14 empty] | 2015-04-27 | 2015-05-04 |  | Y
Central Hudson |  | Sungevity Inc | CH-09448 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8045 | Myers Corners | N | CH-23541 | 6.8 | [13 empty] | NM | N | (1) SMA AMERICA SB3800TL (1) SMA AMERICA SB3000TL | 2015-02-12 | 2015-02-24 | 7 | 2015-02-24 | [14 empty] | 2015-06-12 | 2015-06-19 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-03467 | Newburgh | Newburgh | Orange | 12550 | G | 4042 | Union Ave | N |  | 8 | [13 empty] | NM | N | (1) SMA AMERICA SB8000 | 2015-02-24 | 2015-03-03 | 5 | 2015-03-03 | [14 empty] | 2015-04-27 | 2015-05-01 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-03475 | Newburgh | Montgomery | Orange | 12549 | G | 5073 | Montgomery | N |  | 20 | [13 empty] | NM | N | (1) SMA AMERICA SB8000 (1) SMA AMERICA SB5000TL (1) SMA AMERICA SB7000 | 2015-02-13 | 2015-02-24 | 6 | 2015-02-24 | [14 empty] | 2015-05-15 | 2015-05-21 |  | Y
Central Hudson |  | NRG Home Solar | CH-04311 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6094 | Manchester | N |  | 10.75 | [13 empty] | NM | N | 43 - ENPHASE ENERGY M-250 | 2015-02-13 | 2015-02-23 | 5 | 2015-02-23 | [14 empty] | 2015-06-03 | 2015-06-10 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00935 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6055 | Todd Hill | N |  | 5.59 | [13 empty] | NM | N | 26 - ENPHASE M215 | 2015-02-13 | 2015-02-23 | 5 | 2015-02-23 | [14 empty] | 2015-03-19 | 2015-03-26 |  | Y
Central Hudson |  | Direct Energy Solar | CH-01014 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8093 | Fishkill Plains | N |  | 5.805 | [13 empty] | NM | N | (27) ENPHASE M215 | 2015-02-13 | 2015-02-24 | 6 | 2015-02-24 | [14 empty] | 2015-04-16 | 2015-04-23 |  | Y
Central Hudson |  | Hudson Solar | CH-01612 | Catskill | Berne | Albany | 12023 | G | 1092 | Westerlo | N |  | 10 | [13 empty] | NM | N | SMA AMERICA SB6000 TL-US-22 SMA AMERICA SB4000 TL-US-22 | 2015-02-13 | 2015-02-20 | 4 | 2015-02-20 | [14 empty] | 2015-12-07 | 2015-12-11 |  | Y
Central Hudson |  | Hudson Solar | CH-02507 | Catskill | Berne |  | 12023 | G | 1092 | Westerlo | TBD |  | 10 | [13 empty] | NM | N | SMA AMERICA SB6000 TL-US-22 SMAMERICA SB4000 TL-US-22 | 2015-02-13 | 2015-02-20 | 4 | 2015-02-20 | [17 empty] | W
Central Hudson |  | SolarCity | CH-05499 | Catskill | Jewett | Greene | 12444 | E | 2389 | Vinegar Hill | Y | CH-01168 | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A US-ZB-U | 2015-02-13 | 2015-02-19 | 3 | 2015-02-19 | [14 empty] | 2015-02-23 | 2015-03-02 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07871 | Poughkeepsie | Poughkeepsie |  | 12601 | G | 6011 | Sand Dock | TBD |  | 4.2 | [13 empty] | NM | N | ABB PVI-4.2-OUTD | 2015-02-13 | 2015-02-23 | 5 | 2015-02-23 | [17 empty] | W |  | Customer already had net meter prior to application. 2/16/15 Company Holiday.
Central Hudson |  | Solar Alchemy | CH-08977 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8052 | North Chelsea | N |  | 23.1 | [13 empty] | NM | N | SMA 7700 (3) | 2015-04-21 | 2015-04-28 | 5 | 2015-04-28 | [8 empty] | 350 | 350 |  | 2015-05-07 | 2015-05-07 | 2015-05-12 | 2016-08-01 | 2016-08-03 |  | Y
Central Hudson |  | Solar Alchemy | CH-08996 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8052 | North Chelsea | N |  | 23.1 | [13 empty] | NM | N | SMA 7700 (3) | 2015-04-21 | 2015-04-28 | 5 | 2015-04-28 | [8 empty] | 350 | 350 |  | 2015-05-07 | 2015-05-07 | 2016-05-12 | 2016-07-28 | 2016-08-03 |  | Y
Central Hudson |  | NRG Home Solar | CH-04169 | Poughkeepsie | Staatsburg | Dutchess | 12580 | G | 7041 | Staatsburg | N |  | 9 | [13 empty] | NM | N | 36 - ENPHASE ENERGY M-250 | 2015-02-17 | 2015-02-23 | 4 | 2015-02-23 | [14 empty] | 2015-08-27 | 2015-09-03 |  | Y
Central Hudson |  | NRG Home Solar | CH-04290 | Kingston | Saugerties | Ulster | 12477 | G | 3001 | Saugerties | N |  | 6.02 | [13 empty] | NM | N | 28 ENPHASE M-215-60-2LL-S22-IG | 2015-02-18 | 2015-02-27 | 7 | 2015-02-27 | [14 empty] | 2015-05-20 | 2015-05-27 |  | Y
Central Hudson |  | SolarCity | CH-05500 | Catskill | Prattsville |  | 12468 | E | 2389 | Vinegar Hill | TBD |  | 3 | [13 empty] | NM | N | ABB PVI-3.0-OUTD-S-US | 2015-02-18 | 2015-02-27 | 7 | 2015-02-27 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | SolarCity | CH-06977 | Newburgh | Walden | Orange | 12586 | G | 5041 | East Walden | N | CH-06977 | 6 | [13 empty] | NM | N | (1) ABB PVI-6000-OUTD | 2015-02-18 | 2015-02-25 | 5 | 2015-02-25 | [14 empty] | 2015-03-31 | 2015-04-08 |  | Y
Central Hudson |  | SolarCity | CH-07474 | Newburgh | Montgomery | Orange | 12549 | G | 5073 | Montgomery | N |  | 4.2 | [13 empty] | NM | N | (1) ABB PVI-4.2 | 2015-02-25 | 2015-03-04 | 5 | 2015-03-04 | [14 empty] | 2015-03-09 | 2015-03-16 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06562 | Kingston | Ellenvl | Ulster | 12428 | G | 3078 | Greenfield Rd | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A-US-ZB-U | 2015-02-19 | 2015-02-26 | 5 | 2015-02-26 | [14 empty] | 2015-02-26 | 2015-02-26 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06602 | Kingston | Saugerties | Ulster | 12477 | G | 2015 | Lincoln Park | N |  | 3 | [13 empty] | NM | N | SOLAREDGE SE3000A-US | 2015-02-20 | 2015-02-27 | 5 | 2015-02-27 | [14 empty] | 2015-03-31 | 2015-04-06 |  | Y
Central Hudson |  | Solar Generation | CH-08259 | Newburgh | New Paltz | Ulster | 12561 | G | 5024 | Ohioville | N | CH-08259 | 6 | [13 empty] | NM | N | (1) SMA SB 6000 | 2015-02-20 | 2015-02-27 | 5 | 2015-02-27 | [14 empty] | 2015-09-08 | 2015-09-15 |  | Y
Central Hudson |  | Solar Generation | CH-08272 | Kingston | Woodstock | Ulster | 12498 | G | 3012 | Woodstock | N |  | 7.7 | [13 empty] | NM | N | SMA SB 7700 TL | 2015-02-20 | 2015-02-27 | 5 | 2015-02-27 | [14 empty] | 2015-09-01 | 2015-09-09 |  | Y
Central Hudson |  | Sungevity Inc | CH-09299 | Kingston | Kerhonkson | Ulster | 12446 | G | 3082 | Kerhonkson | N |  | 10.2 | [13 empty] | NM | N | ABB PVI-6000-OUTD-US-A ABB PVI-4.8-OUTD-US-A | 2015-02-20 | 2015-02-27 | 5 | 2015-02-27 | [14 empty] | 2015-05-28 | 2015-05-28 |  | Y
Central Hudson |  | Sungevity Inc | CH-09491 | Newburgh | Marlboro | Ulster | 12542 | G | 5003 | Marlboro | N |  | 18 | [13 empty] | NM | N | (3) SMA AMERICA SB6000TL-US-22 | 2015-02-20 | 2015-02-27 | 5 | 2015-02-27 | [14 empty] | 2015-07-08 | 2015-07-14 |  | Y
Central Hudson |  | Kasselman Solar | CH-03518 | Catskill | Athens | Greene | 12015 | G | 2002 | North Catskill | N | CH-03518 | 5.04 | [13 empty] | NM | N | 21 ENPHASE ENERGY M-250 | 2015-02-23 | 2015-03-02 | 5 | 2015-03-02 | [14 empty] | 2015-06-03 | 2015-06-10 |  | Y
Central Hudson |  | SolarCity | CH-05302 | Newburgh | Newburgh | Orange | 12550 | G | 4011 | West Balmville | N |  | 11.4 | [13 empty] | NM | N | (1) SOLAREDGE SE11400A | 2015-02-23 | 2015-03-02 | 5 | 2015-03-02 | [14 empty] | 2015-04-02 | 2015-04-10 |  | Y
Central Hudson |  | SolarCity | CH-06263 | Newburgh | New Windsor | Orange | 12553 | G | 4045 | Union Ave | N |  | 6.6 | [13 empty] | NM | N | (1) ABB PVI-3.6-OUTD-S (1) ABB PVI-3.0-OUTD-S | 2015-02-23 | 2015-03-02 | 5 | 2015-03-02 | [14 empty] | 2015-03-31 | 2015-04-08 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06895 | Fishkill | Beacon | Dutchess | 12508 | G | 8016 | Forgebrook | N |  | 4.2 | [13 empty] | NM | N | (1) ABB PVI-4.2-OUTD-S | 2015-02-23 | 2015-03-03 | 6 | 2015-03-03 | [14 empty] | 2015-10-14 | 2015-10-19 |  | Y
Central Hudson |  | Sungevity Inc | CH-09301 | Kingston | Saugerties | Ulster | 12477 | G | 3002 | Saugerties | N | CH-09301 | 7.7 | [13 empty] | NM | N | SMA AMERICA SB7700TL-US-22 | 2015-02-23 | 2015-03-02 | 5 | 2015-03-02 | [14 empty] | 2015-03-30 | 2015-04-06 |  | Y
Central Hudson |  | Verengo Solar | CH-09760 | Kingston | Kingston | Ulster | 12401 | G | 1021 | East Kingston | N |  | 5.16 | [13 empty] | NM | N | 24 ENPHASE M215-60-2LL-S22-IG | 2015-02-23 | 2015-03-02 | 5 | 2015-03-02 | [14 empty] | 2015-05-12 | 2015-05-15 |  | Y
Central Hudson |  | Verengo Solar | CH-09769 | Newburgh | Newburgh | Orange | 12550 | G | 4023 | Coldenham | N |  | 5.16 | [13 empty] | NM | N | (24) ENPHASE ENERGY M215-60-2LL-S22-IG | 2015-02-23 | 2015-03-02 | 5 | 2015-03-02 | [14 empty] | 2015-05-15 | 2015-05-21 |  | Y
Central Hudson |  | NRG Home Solar | CH-04667 | Newburgh | New Windsor | Orange | 12553 | G | 4093 | Bethlehem Rd | N |  | 5.16 | [13 empty] | NM | N | (24) ENPHASE ENERGY M-215-60-2LL-S22-IG | 2015-02-24 | 2015-03-03 | 5 | 2015-03-03 | [14 empty] | 2015-07-15 | 2015-07-21 |  | Y
Central Hudson |  | SolarCity | CH-06351 | Newburgh | Wallkill |  | 12589 | G | 5043 | East Walden | TBD |  | 6 | [13 empty] | NM | N | (1) SOLAREDGE SE6000A | 2015-02-24 | 2015-03-03 | 5 | 2015-03-03 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | SolarCity | CH-07051 | Newburgh | Wallkill |  | 12589 | G | 5013 | Modena | TBD |  | 5 | [13 empty] | NM | N | (1) ABB PVI-5000-OUTD | 2015-03-05 | 2015-03-17 | 8 | 2015-03-17 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | Solar Generation | CH-08137 | Catskill | Haines Fls | Greene | 12436 | G | 2385 | Lawrenceville | N |  | 9 | [13 empty] | NM | N | SMA SB 5000 TL SMA SB 4000 TL | 2015-02-24 | 2015-03-06 | 8 | 2015-03-06 | [14 empty] | 2015-07-13 | 2015-07-20 |  | Y
Central Hudson |  | Solar Generation | CH-08303 | Kingston | W Hurley | Ulster | 12491 | G | 2094 | Hurley Ave | N | CH-08209 | 7 | [13 empty] | NM | N | SMA SB 7000 TL | 2015-02-24 | 2015-03-06 | 8 | 2015-03-06 | [14 empty] | 2015-04-08 | 2015-04-15 |  | Y
Central Hudson |  | Verengo Solar | CH-09857 | Poughkeepsie | Poughquag | Dutchess | 12570 | G | 6055 | Todd Hill | N |  | 8.815 | [13 empty] | NM | N | 41 - ENPHASE ENERGY M215 | 2015-02-24 | 2015-03-02 | 4 | 2015-03-02 | [14 empty] | 2015-06-09 | 2015-06-16 |  | Y
Central Hudson |  | Monolith Solar Associates LLC | CH-02661 | Catskill | Coxsackie | Greene | 12192 | G | 1076 | Coxsackie | N |  | 12 | [13 empty] | NM | N | 2 SMA SB6000 US | 2015-02-25 | 2015-03-11 | 10 | 2015-03-11 | [14 empty] | 2015-12-09 | 2015-12-16 |  | Y
Central Hudson |  | Monolith Solar Associates LLC | CH-02675 | Catskill | Rensselaervl | Albany | 12147 | G | 1092 | Westerlo | N |  | 7.7 | [13 empty] | NM | N | SMA SB 7700-22 | 2015-02-25 | 2015-03-06 | 7 | 2015-03-06 | [14 empty] | 2015-06-15 | 2015-06-22 |  | Y
Central Hudson |  | Paradise Energy Solutions LLC | CH-02831 | Kingston | Shokan | Ulster | 12481 | G | 3011 | Woodstock | N |  | 10 | [13 empty] | NM | N | SOLAR EDGE 10000 A-US | 2015-02-25 | 2015-03-20 | 17 | 2015-03-20 | [8 empty] | 350 | 350 |  | 2015-04-01 | 2015-04-01 | 2015-04-13 | 2015-05-12 | 2015-05-15 |  | Y
Central Hudson |  | SolarCity | CH-07058 | Newburgh | Newburgh | Orange | 12550 | G | 4015 | West Balmville | N |  | 15.2 | [13 empty] | NM | N | (2) SOLAREDGE SE7600-US-ZB-U | 2015-02-25 | 2015-03-04 | 5 | 2015-03-04 | [14 empty] | 2015-06-30 | 2015-07-09 |  | Y
Central Hudson |  | Verengo Solar | CH-09830 | Newburgh | Newburgh | Orange | 12550 | G | 4011 | West Balmville | N |  | 9.46 | [13 empty] | NM | N | (44) ENPHASE ENERGY M215-60-2LL-S22-IG | 2015-02-25 | 2015-03-04 | 5 | 2015-03-04 | [14 empty] | 2015-04-27 | 2015-05-01 |  | Y
Central Hudson |  | NRG Home Solar | CH-04514 | Catskill | Palenville |  | 12463 | G | 2001 | North Catskill | TBD |  | 7.31 | [13 empty] | NM | N | 34 ENPHASE M-215-60-2LL-S22-IG | 2015-02-26 | 2015-03-11 | 9 | 2015-03-11 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | NRG Home Solar | CH-04797 | Newburgh | Wallkill |  | 12589 | G | 5033 | Galeville | TBD |  | 3.65 | [13 empty] | NM | N | (17) ENPHASE ENERGY M-215-60-2LL-S22-IG | 2015-02-26 | 2015-03-05 | 5 | 2015-03-05 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | SolarCity | CH-04925 | Catskill | Hunter | Greene | 12442 | E | 2081 | Hunter | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000-OUTD US | 2015-02-26 | 2015-03-11 | 9 | 2015-03-11 | [14 empty] | 2015-07-06 | 2015-07-10 |  | Y
Central Hudson |  | SolarCity | CH-06573 | Kingston | Saugerties | Ulster | 12477 | G | 3004 | Saugerties | N |  | 7.2 | [13 empty] | NM | N | (2) ABB PVI-3.6-OUTD-S-US-Z | 2015-02-26 | 2015-03-11 | 9 | 2015-03-11 | [14 empty] | 2015-04-29 | 2015-05-06 |  | Y
Central Hudson |  | SolarCity | CH-07458 | Newburgh | Gardiner | Ulster | 12525 | G | 5034 | Galeville | N |  | 4.2 | [13 empty] | NM | N | (1) ABB PVI-4.2-OUTD | 2015-02-26 | 2015-03-05 | 5 | 2015-03-05 | [14 empty] | 2015-04-23 | 2015-04-30 |  | Y
Central Hudson |  | SolarCity | CH-07535 | Poughkeepsie | Salt Pt | Dutchess | 12578 | G | 7011 | Hibernia | N |  | 4.2 | [13 empty] | NM | N | ABB PVI-4.2-OUTD | 2015-02-26 | 2015-03-02 | 2 | 2015-03-02 | [14 empty] | 2015-04-09 | 2015-04-16 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00846 | Kingston | Saugerties | Ulster | 12477 | G | 2015 | Lincoln Park | N |  | 12.04 | [13 empty] | NM | N | 56 ENPHASE M215 60-2LL-S22 | 2015-02-27 | 2015-03-13 | 10 | 2015-03-13 | [14 empty] | 2015-04-16 | 2015-04-23 |  | Y
Central Hudson |  | SolarCity | CH-05030 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 7025 | Tinkertown | N |  | 6.6 | [13 empty] | NM | N | 1 - ABB PVI-3.0-OUTD 1 - ABB PVI-3.6-OUTD | 2015-03-10 | 2015-03-23 | 9 | 2015-03-23 | [14 empty] | 2015-08-07 | 2015-08-11 |  | Y
Central Hudson |  | SolarCity | CH-06530 | Kingston | W Hurley | Ulster | 12491 | G | 3013 | Woodstock | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A-US-ZB-U | 2015-02-27 | 2015-03-13 | 10 | 2015-03-13 | [14 empty] | 2015-03-16 | 2015-03-20 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08782 | Catskill | Ravena | Albany | 12143 | G | 1081 | New Baltimore | N |  | 8.17 | [13 empty] | NM | N | 18 ENPHASE M215 60-2LL-S2 | 2015-02-27 | 2015-03-13 | 10 | 2015-03-13 | [14 empty] | 2015-05-01 | 2015-05-08 |  | Y
Central Hudson |  | NRG Home Solar | CH-04178 | Newburgh | Newburgh |  | 12550 | G | 4023 | Coldenham | TBD |  | 8.17 | [13 empty] | NM | N | (38) ENPHASE ENERGY M-215-60-2LL-S22-IG | 2015-03-02 | 2015-03-09 | 5 | 2015-03-09 | [17 empty] | W
Central Hudson |  | NRG Home Solar | CH-04293 | Kingston | Saugerties | Ulster | 12477 | G | 3001 | Saugerties | N |  | 3.87 | [13 empty] | NM | N | 18 ENPHASE M-215-60-2LL-S22-IG | 2015-03-02 | 2015-03-13 | 9 | 2015-03-13 | [14 empty] | 2015-06-25 | 2015-07-02 |  | Y
Central Hudson |  | NRG Home Solar | CH-04488 | Newburgh | Wallkill | Ulster | 12589 | G | 5043 | East Walden | N |  | 9.46 | [13 empty] | NM | N | (44) ENPHASE ENERGY M-215-60-2LL-S22-IG | 2015-03-02 | 2015-03-09 | 5 | 2015-03-09 | [14 empty] | 2015-05-20 | 2015-05-27 |  | Y
Central Hudson |  | NRG Home Solar | CH-04694 | Kingston | Saugerties | Ulster | 12477 | G | 3001 | Saugerties | N |  | 5.8 | [13 empty] | NM | N | 27 ENPHASE M-215-60-2LL-S22-IG | 2015-03-02 | 2015-03-13 | 9 | 2015-03-13 | [14 empty] | 2015-10-13 | 2015-10-16 |  | Y
Central Hudson |  | SolarCity | CH-05450 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8093 | Fishkill Plains | N |  | 10 | [13 empty] | NM | N | (1) SOLAREDGE SE10000A | 2015-03-03 | 2015-03-10 | 5 | 2015-03-10 | [14 empty] | 2015-05-28 | 2015-06-04 |  | Y
Central Hudson |  | SolarCity | CH-06781 | Newburgh | Highland | Ulster | 12528 | G | 5083 | Highland | N |  | 11 | [13 empty] | NM | N | 1 - ABB PVI-5000-OUTD 1 - ABB PVI-6000-OUTD | 2015-03-03 | 2015-03-10 | 5 | 2015-03-10 | [14 empty] | 2015-04-27 | 2015-05-01 |  | Y
Central Hudson |  | Sungevity Inc | CH-09286 | Kingston | Port Ewen |  | 12466 | G | 1024 | East Kingston | TBD |  | 3 | [13 empty] | NM | N | ABB PVI-3.0-OUTD-S-US-A | 2015-03-03 | 2015-03-16 | 9 | 2015-03-16 | [17 empty] | W |  | Customer already had net meter prior to application. 7/20/15 As per customer, their HOA does not allow solar, therefore solar cancelled.
Central Hudson |  | NRG Home Solar | CH-04183 | Newburgh | Washingtonvl |  | 10992 | G | 4097 | Bethlehem Rd | TBD |  | 8.17 | [13 empty] | NM | N | (38) ENPHASE ENERGY M-215-60-2LL-S22-IG | 2015-03-11 | 2015-03-18 | 5 | 2015-03-18 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | CNR Energy Solutions LLC | CH-00772 | Newburgh | Wallkill | Ulster | 12589 | G | 5043 | East Walden | N |  | 6.88 | [13 empty] | NM | N | (32) ENPHASE ENERGY M215 | 2015-03-13 | 2015-03-19 | 4 | 2015-03-19 | [14 empty] | 2015-04-06 | 2015-04-06 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-05028 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6044 | Spackenkill | N |  | 448 | [13 empty] | RNM | N | 16 - Solectria PVI-28TL-US | 2015-05-20 | 2015-06-10 | 14 | 2015-06-10 | 2015-05-20 | 2015-06-10 | 14 | [11 empty] | 2016-05-11 | 2016-05-20 |  | Y
Central Hudson |  | SolarCity | CH-05595 | Catskill | Ravena | Albany | 12143 | G | 1081 | New Baltimore | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000-OUTD-US | 2015-03-04 | 2015-03-16 | 8 | 2015-03-16 | [14 empty] | 2015-05-26 | 2015-06-02 |  | Y
Central Hudson |  | SolarCity | CH-07857 | Kingston | West Hurley |  | 12491 | G | 3013 | Woodstock | TBD |  | 5 | [13 empty] | NM | N | ABB PVI-5000-OUTD-US | 2015-03-04 | 2015-03-16 | 8 | 2015-03-16 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | Sungevity Inc | CH-09589 | Fishkill | Beacon | Dutchess | 12508 | G | 8017 | Forgebrook | N |  | 6 | [13 empty] | NM | N | (2) SOLAREDGE 3000A-US | 2015-03-17 | 2015-03-27 | 8 | 2015-03-27 | [14 empty] | 2015-05-07 | 2015-05-13 |  | Y
Central Hudson |  | SolarCity | CH-05179 | Newburgh | Wallkill | Ulster | 12589 | G | 5041 | East Walden | N |  | 6 | [13 empty] | NM | N | (1) ABB PVI-6000-OUTD-US-Z-A | 2015-03-05 | 2015-03-17 | 8 | 2015-03-17 | [14 empty] | 2015-05-18 | 2015-05-22 |  | Y
Central Hudson |  | SolarCity | CH-06362 | Newburgh | Wallkill | Ulster | 12589 | G | 5041 | East Walden | N |  | 5 | [13 empty] | NM | N | (1) ABB PVI-5000-OUTD | 2015-03-05 | 2015-03-17 | 8 | 2015-03-17 | [14 empty] | 2015-06-05 | 2015-06-12 |  | Y
Central Hudson |  | Sungevity Inc | CH-09529 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 7011 | Hibernia | N |  | 8.4 | [13 empty] | NM | N | 2 - ABB PVI-4.2-OUTD | 2015-03-05 | 2015-03-18 | 9 | 2015-03-18 | [14 empty] | 2015-06-18 | 2015-06-25 |  | Y
Central Hudson |  | NRG Home Solar | CH-04609 | Fishkill | Wappingrs Falls |  | 12590 | G | 8014 | Forgebrook | TBD |  | 5.59 | [13 empty] | NM | N | (26) ENPHASE ENERGY M-215-60-2LL-S22-IG | 2015-03-06 | 2015-03-19 | 9 | 2015-03-19 | [17 empty] | W
Central Hudson |  | NRG Home Solar | CH-04707 | Poughkeepsie | Lagrangevl | Dutchess | 12540 | G | 6055 | Todd Hill | N |  | 8.815 | [13 empty] | NM | N | 41 - ENPHASE ENERGY M-215 | 2015-03-06 | 2015-03-18 | 8 | 2015-03-18 | [8 empty] | 350 | 350 |  | 2015-10-30 | 2015-10-30 | 2015-11-06 | 2015-11-06 | 2015-11-13 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00830 | Newburgh | Marlboro | Ulster | 12542 | G | 5004 | Marlboro | N |  | 8.6 | [13 empty] | NM | N | (40) ENPHASE M215 60-2LL-S22 | 2015-03-06 | 2015-03-19 | 9 | 2015-03-19 | [14 empty] | 2015-05-18 | 2015-05-22 |  | Y
Central Hudson |  | SolarCity | CH-04932 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8046 | Myers Corners | N |  | 5 | [13 empty] | NM | N | (1) ABB PVI-5000-OUTD | 2015-04-13 | 2015-04-27 | 10 | 2015-04-27 | [14 empty] | 2015-07-13 | 2015-07-17 |  | Y
Central Hudson |  | SolarCity | CH-04993 | Kingston | Tillson | Ulster | 12486 | G | 3021 | High Falls | N |  | 7.2 | [13 empty] | NM | N | (2) ABB PVI-3.6-OUTD-S | 2015-03-06 | 2015-03-20 | 10 | 2015-03-20 | [14 empty] | 2015-06-16 | 2015-06-23 |  | Y
Central Hudson |  | SolarCity | CH-05191 | Fishkill | Stormvl | Dutchess | 12582 | G | 8095 | Fishkill Plains | N |  | 11 | [13 empty] | NM | N | (1) ABB PVI-6000-OUTD (1) ABB PVI-5000-OUTD | 2015-03-06 | 2015-03-18 | 8 | 2015-03-18 | [14 empty] | 2015-05-05 | 2015-05-12 |  | Y
Central Hudson |  | SolarCity | CH-06195 | Newburgh | Newburgh | Orange | 12550 | G | 5004 | Marlboro | N |  | 3 | [13 empty] | NM | N | (1) ABB PVI-3.0-OUTD-S | 2015-03-06 | 2015-03-18 | 8 | 2015-03-18 | [14 empty] | 2015-04-27 | 2015-05-01 |  | Y
Central Hudson |  | SolarCity | CH-06605 | Kingston | Lake Katrine |  | 12449 | G | 2016 | Lincoln Park | TBD |  | 6 | [13 empty] | NM | N | 2 ABB PVI-3.0-OUTD-S US | 2015-03-06 | 2015-03-16 | 6 | 2015-03-16 | [17 empty] | W
Central Hudson |  | SolarCity | CH-07410 | Newburgh | New Paltz | Ulster | 12561 | G | 5024 | Ohioville | N |  | 21.4 | [13 empty] | NM | N | (1) FRONIUS IG PLUS A 11.4 (1) FRONIUS IG PLUS A 10.0 | 2015-03-06 | 2015-03-20 | 10 | 2015-03-20 | [14 empty] | 2015-05-12 | 2015-05-15 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08656 | Catskill | Ravena | Albany | 12143 | G | 1081 | New Baltimore | N |  | 9.25 | [13 empty] | NM | N | 43 ENPHASE M215 602LLS2XZC | 2015-03-06 | 2015-03-16 | 6 | 2015-03-16 | [8 empty] | 350 | 350 |  |  |  |  | 2015-06-19 | 2015-06-26 |  | Y
Central Hudson |  | NRG Home Solar | CH-04697 | Poughkeepsie | Poughkeepsie |  | 12601 | G | 6011 | Sand Dock | TBD |  | 4.5 | [13 empty] | NM | N | 18 - ENPHASE ENERGY M250 | 2015-03-17 | 2015-03-23 | 4 | 2015-03-23 | [17 empty] | W |  | Customer already had net meter prior to application. 2/16/15 Company Holiday.
Central Hudson |  | SolarCity | CH-06659 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6003 | Reynolds Hill | N |  | 3 | [13 empty] | NM | N | ABB PVI-3.0-OUTD | 2015-03-09 | 2015-03-18 | 7 | 2015-03-18 | [14 empty] | 2015-09-23 | 2015-09-29 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00857 | Poughkeepsie | Lagrangevl | Dutchess | 12540 | G | 6057 | Todd Hill | N |  | 9.46 | [13 empty] | NM | N | 44 - ENPHASE M215 | 2015-03-10 | 2015-03-23 | 9 | 2015-03-23 | [14 empty] | 2015-04-16 | 2015-04-23 |  | Y
Central Hudson |  | OnForce Solar | CH-02799 | Kingston | Woodstock |  | 12498 | G | 3014 | Woodstock | TBD |  | 420 | [13 empty] | RNM | N | (14) SMA STP-30000TLUS-10 | 2015-05-19 | 2015-06-04 | 11 | 2015-06-04 | 2015-05-19 | 2015-06-04 | 11 | [14 empty] | W
Central Hudson |  | SolarCity | CH-06112 | Fishkill | Fishkill | Dutchess | 12524 | G | 8014 | Forgebrook | N |  | 3 | [13 empty] | NM | N | (1) ABB PVI-3.0-OUTD-S | 2015-03-10 | 2015-03-19 | 7 | 2015-03-19 | [14 empty] | 2015-04-27 | 2015-05-04 |  | Y
Central Hudson |  | SolarCity | CH-07922 | Newburgh | Maybrook |  | 12543 | G | 5052 | Maybrook | TBD |  | 3 | [13 empty] | NM | N | (1) SOLAREDGE SE3000A | 2015-03-10 | 2015-03-19 | 7 | 2015-03-19 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | Verengo Solar | CH-09831 | Newburgh | Newburgh |  | 12550 | G | 5004 | Marlboro | TBD |  | 4.3 | [13 empty] | NM | N | (20) ENPHASE ENERGY M215-60-S22-IG | 2015-03-10 | 2015-03-20 | 8 | 2015-03-20 | [17 empty] | W
Central Hudson |  | NRG Home Solar | CH-04735 | Fishkill | Cold Spg | Putnam | 10516 | G | 8087 | Tioronda | N |  | 7.74 | [13 empty] | NM | N | (36) ENPHASE ENERGY M-215-60-2LL-S22-IG | 2015-03-11 | 2015-03-18 | 5 | 2015-03-18 | [14 empty] | 2015-10-16 | 2015-10-22 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00998 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 6092 | Manchester | N |  | 11.18 | [13 empty] | NM | N | 52 - ENPHASE M215 | 2015-03-11 | 2015-03-18 | 5 | 2015-03-18 | [14 empty] | 2015-04-16 | 2015-04-23 |  | Y
Central Hudson |  | OnForce Solar | CH-02814 | Newburgh | New Windsor |  | 12553 | G | 4052 | Union Ave | TBD |  | 3.8 | [13 empty] | NM | N | (1) SMA SB-3800TL | 2015-03-11 | 2015-03-18 | 5 | 2015-03-18 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | SolarCity | CH-07698 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6043 | Spackenkill | N |  | 5 | [13 empty] | NM | N | ABB PVI-5000-OUTD | 2015-04-14 | 2015-04-21 | 5 | 2015-04-21 | [14 empty] | 2016-01-29 | 2016-02-05 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Verengo Solar | CH-09797 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6066 | Inwood Ave | N | CH-09797 | 5.16 | [13 empty] | NM | N | 24 - ENPHASE ENERGY M215 | 2015-03-11 | 2015-03-18 | 5 | 2015-03-18 | [14 empty] | 2015-04-27 | 2015-05-01 |  | Y
Central Hudson |  | SolarCity | CH-05782 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6046 | Spackenkill | N |  | 5 | [13 empty] | NM | N | ABB PVI-5000-OUTD | 2015-03-12 | 2015-03-19 | 5 | 2015-03-19 | [14 empty] | 2015-09-09 | 2015-09-16 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06059 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8096 | Fishkill Plains | N |  | 6 | [13 empty] | NM | N | (1) SOLAREDGE SE6000A | 2015-03-12 | 2015-03-19 | 5 | 2015-03-19 | [14 empty] | 2015-06-16 | 2015-06-23 |  | Y
Central Hudson |  | Sungevity Inc | CH-09563 | Kingston | High Fls | Ulster | 12440 | G | 3024 | High Falls | N |  | 10 | [13 empty] | NM | N | 2 SMA SB5000TL-US-22 | 2015-03-12 | 2015-03-17 | 3 | 2015-03-17 | [14 empty] | 2015-06-03 | 2015-06-10 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-03462 | Newburgh | Newburgh |  | 12550 | G | 4013 | West Balmville | TBD |  | 16 | [13 empty] | NM | N | (1) FRONIUS IG PLUS A 6.0 (1) FRONIUS IG PLUS A 10.0 | 2015-03-13 | 2015-03-20 | 5 | 2015-03-20 | [17 empty] | W
Central Hudson |  | NRG Home Solar | CH-04157 | Newburgh | Marlboro | Ulster | 12542 | G | 5003 | Marlboro | N |  | 7.31 | [13 empty] | NM | N | (34) ENPHASE ENERGY M-215-60-2LL-S22-IG | 2015-03-13 | 2015-03-19 | 4 | 2015-03-19 | [14 empty] | 2015-10-02 | 2015-10-09 |  | Y
Central Hudson |  | NRG Home Solar | CH-04172 | Fishkill | Hopewell Jct |  | 12533 | G | 8095 | Fishkill Plains | TBD |  | 8.17 | [13 empty] | NM | N | (38) ENPHASE ENERGY M-215-60-2LL-S22-IG | 2015-03-13 | 2015-03-20 | 5 | 2015-03-20 | [17 empty] | W
Central Hudson |  | NRG Home Solar | CH-04262 | Kingston | Kerhonkson | Ulster | 12446 | G | 3081 | Kerhonkson | N |  | 9.89 | [13 empty] | NM | N | 46 ENPHASE M-215-60-2LL-S22-IG | 2015-03-13 | 2015-03-19 | 4 | 2015-03-19 | [14 empty] | 2015-05-20 | 2015-05-27 |  | Y
Central Hudson |  | NRG Home Solar | CH-04277 | Kingston | Grahamsvl | Sullivan | 12740 | G | 3091 | Neversink | N |  | 8.5 | [13 empty] | NM | N | 34 ENPHASE M-250-60-2LL-S22 | 2015-03-13 | 2015-03-19 | 4 | 2015-03-19 | [14 empty] | 2015-08-27 | 2015-09-03 |  | Y
Central Hudson |  | NRG Home Solar | CH-04372 | Fishkill | Wappingrs Fls |  | 12590 | G | 8091 | Fishkill Plains | TBD |  | 5.8 | [13 empty] | NM | N | (27) ENPHASE ENERGY M-215-60-2LL-S22-IG | 2015-03-13 | 2015-03-23 | 6 | 2015-03-23 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | NRG Home Solar | CH-04544 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6045 | Spackenkill | N |  | 5.375 | [13 empty] | NM | N | 25 - ENPHASE ENERGY M-215 | 2015-03-13 | 2015-03-19 | 4 | 2015-03-19 | [14 empty] | 2015-10-20 | 2015-10-27 |  | Y
Central Hudson |  | NRG Home Solar | CH-04590 | Fishkill | Wappingers Falls | Dutchess | 12590 | G | 8044 | Myers Corners | N |  | 5.59 | [13 empty] | NM | N | (26) ENPHASE ENERGY M-215-60-2LL-S22-IG | 2015-03-13 | 2015-03-23 | 6 | 2015-03-23 | [14 empty] | 2015-09-25 | 2015-10-01 |  | Y
Central Hudson |  | NRG Home Solar | CH-04607 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8045 | Myers Corners | N |  | 5.8 | [13 empty] | NM | N | (27) ENPHASE ENERGY M-215-60-2LL-S22-IG | 2015-03-13 | 2015-03-23 | 6 | 2015-03-23 | [14 empty] | 2015-06-03 | 2015-06-10 |  | Y
Central Hudson |  | NRG Home Solar | CH-04730 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8071 | Shenandoah | N |  | 2.79 | [13 empty] | NM | N | (13) ENPHASE ENERGY M-215-60-2LL-S22-IG | 2015-04-30 | 2015-04-30 | 0 | 2015-04-30 | [14 empty] | 2016-02-24 | 2016-02-29 |  | Y
Central Hudson |  | Hudson Solar | CH-02472 | Newburgh | Highland | Ulster | 12528 | G | 5082 | Highland | N | CH-01405 | 5 | [13 empty] | NM | N | SMA AMERICA SB5000 | 2015-03-19 | 2015-03-26 | 5 | 2015-03-26 | [14 empty] | 2015-09-14 | 2015-09-21 |  | Y
Central Hudson |  | NRG Home Solar | CH-04203 | Newburgh | Milton | Ulster | 12547 | G | 5002 | Marlboro | N |  | 2.58 | [13 empty] | NM | N | (12) ENPHASE ENERGY M-215-60-2LL-S22-IG | 2015-03-16 | 2015-03-23 | 5 | 2015-03-23 | [14 empty] | 2015-10-14 | 2015-10-15 |  | Y
Central Hudson |  | SolarCity | CH-07417 | Newburgh | Newburgh | Orange | 12550 | G | 4013 | West Balmville | N |  | 15 | [13 empty] | NM | N | (2) ABB PVI-6000-OUTD-US-Z-A (1) ABB PVI-3.0-OUTD-S-US-Z | 2015-03-16 | 2015-03-23 | 5 | 2015-03-23 | [14 empty] | 2015-04-27 | 2015-05-01 |  | Y
Central Hudson |  | SolarCity | CH-07844 | Catskill | Greenville |  | 12193 | G | 1092 | Westerlo | TBD |  | 10 | [13 empty] | NM | N | FRONIUS IG PLUS A 10.0 | 2015-03-16 | 2015-03-20 | 4 | 2015-03-20 | [17 empty] | W
Central Hudson |  | Sungevity Inc | CH-09303 | Kingston | Saugerties | Ulster | 12477 | G | 3003 | Saugerties | N |  | 7.6 | [13 empty] | NM | N | (2) SMA AMERICA SB3800TL-US-22 | 2015-03-16 | 2015-03-20 | 4 | 2015-03-20 | [14 empty] | 2015-06-29 | 2015-07-07 |  | Y
Central Hudson |  | NRG Home Solar | CH-04109 | Fishkill | Fishkill |  | 12524 | G | 8011 | Forgebrook | TBD |  | 3 | [13 empty] | NM | N | (12) ENPHASE ENERGY M-250-60-2LL-S22 | 2015-03-17 | 2015-03-24 | 5 | 2015-03-24 | [17 empty] | W
Central Hudson |  | NRG Home Solar | CH-04201 | Fishkill | Stormvl |  | 12582 | G | 8095 | Fishkill Plains | TBD |  | 11.395 | [13 empty] | NM | N | (53) ENPHASE ENERGY M-215-60-2LL-S22-IG | 2015-03-17 | 2015-03-27 | 8 | 2015-03-27 | [17 empty] | W
Central Hudson |  | NRG Home Solar | CH-04666 | Newburgh | Modena | Ulster | 12548 | G | 5013 | Modena | N |  | 5.8 | [13 empty] | NM | N | (27) ENPHASE ENERGY M-215-60-2LL-S22-IG | 2015-03-17 | 2015-03-27 | 8 | 2015-03-27 | [14 empty] | 2015-10-14 | 2015-10-19 |  | Y
Central Hudson |  | Hudson Solar | CH-01512 | Newburgh | New Paltz | Ulster | 12561 | G | 5011 | Modena | N |  | 6.8 | [13 empty] | NM | N | (1) SMA AMERICA SB3000 (1) SMA AMERICA SB3800 | 2015-03-17 | 2015-03-27 | 8 | 2015-03-27 | [14 empty] | 2015-06-04 | 2015-06-11 |  | Y
Central Hudson |  | Hudson Solar | CH-01680 | Kingston | Accord | Ulster | 12404 | G | 3024 | High Falls | N |  | 16 | [13 empty] | NM | N | 2 SMA SB5000 TL-US-22 1 SMA SB6000 TL-US-22 | 2015-03-17 | 2015-03-23 | 4 | 2015-03-23 | [14 empty] | 2015-09-09 | 2015-09-16 |  | Y
Central Hudson |  | Hudson Solar | CH-01726 | Kingston | Saugerties | Ulster | 12477 | G | 2015 | Lincoln Park | N |  | 6 | [13 empty] | NM | N | SMA AMERICA SB6000 TL-US-22 | 2015-03-17 | 2015-03-23 | 4 | 2015-03-23 | [14 empty] | 2015-06-22 | 2015-06-29 |  | Y
Central Hudson |  | Hudson Solar | CH-02013 | Catskill | Earlton | Greene | 12058 | G | 2005 | North Catskill | N |  | 11 | [13 empty] | NM | N | SMA AMERICA SB5000 TL-US-22 SMA AMERICA SB6000 TL-US-22 | 2015-03-17 | 2015-03-23 | 4 | 2015-03-23 | [8 empty] | 350 | 350 |  |  |  |  | 2015-07-01 | 2015-07-08 |  | Y
Central Hudson |  | Hudson Solar | CH-02246 | Kingston | Saugerties | Ulster | 12477 | G | 3004 | Saugerties | N |  | 7 | [13 empty] | NM | N | SMA AMERICA SB7000 TL-US-22 | 2015-03-17 | 2015-03-23 | 4 | 2015-03-23 | [14 empty] | 2015-06-29 | 2015-07-07 |  | Y
Central Hudson |  | Hudson Solar | CH-02497 | Newburgh | Montgomery | Orange | 12549 | G | 5054 | Maybrook | N | CH-01570 | 9 | [13 empty] | NM | N | SMA AMERICA SB9000 | 2015-03-17 | 2015-03-24 | 5 | 2015-03-24 | [14 empty] | 2015-04-14 | 2015-04-21 |  | Y
Central Hudson |  | SolarCity | CH-05400 | Newburgh | Montgomery | Orange | 12549 | G | 5073 | Montgomery | N |  | 7.6 | [13 empty] | NM | N | (1) SOLAREDGE SE7600A | 2015-03-17 | 2015-03-26 | 7 | 2015-03-26 | [14 empty] | 2015-05-06 | 2015-05-12 |  | Y
Central Hudson |  | SolarCity | CH-05465 | Newburgh | Wallkill | Ulster | 12589 | G | 5041 | East Walden | N |  | 9.6 | [13 empty] | NM | N | (1) ABB PVI-6000-OUTD (1) ABB PVI-3.6-OUTD-S | 2015-04-28 | 2015-05-05 | 5 | 2015-05-05 | [14 empty] | 2015-05-06 | 2015-05-12 |  | Y
Central Hudson |  | SolarCity | CH-05550 | Catskill | Leeds | Greene | 12451 | G | 2071 | Freehold | N |  | 3.6 | [13 empty] | NM | N | ABB PVI-3.6-OUTD-S-US-Z | 2015-03-17 | 2015-03-23 | 4 | 2015-03-23 | [14 empty] | 2015-05-01 | 2015-05-08 |  | Y
Central Hudson |  | SolarCity | CH-05668 | Kingston | Port Ewen | Ulster | 12466 | G | 1012 | Boulevard | N |  | 4.2 | [13 empty] | NM | N | ABB PVI-4.2-OUTD-S-US | 2015-03-17 | 2015-03-23 | 4 | 2015-03-23 | [14 empty] | 2015-05-01 | 2015-05-08 |  | Y
Central Hudson |  | SolarCity | CH-06882 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8045 | Myers Corners | N | CH-06882 | 6 | [13 empty] | NM | N | (1) ABB 6000-OUTD-US-Z-A | 2015-03-17 | 2015-03-24 | 5 | 2015-03-24 | [14 empty] | 2015-05-01 | 2015-05-08 |  | Y
Central Hudson |  | Verengo Solar | CH-09897 | Poughkeepsie | Lagrangevl | Dutchess | 12540 | G | 6052 | Todd Hill | N |  | 3.87 | [13 empty] | NM | N | 18 - ENPHASE ENERGY M215 | 2015-03-18 | 2015-03-23 | 3 | 2015-03-23 | [14 empty] | 2015-06-10 | 2015-06-17 |  | Y
Central Hudson |  | Verengo Solar | CH-09929 | Newburgh | Newburgh |  | 12550 | G | 4013 | West Balmville | TBD |  | 7.525 | [13 empty] | NM | N | (35) ENPHASE ENERGY M215-60-S22-IG | 2015-03-17 | 2015-03-27 | 8 | 2015-03-27 | [17 empty] | W
Central Hudson |  | New York State Solar Farm | CH-03967 | Kingston | Ulster Pk | Ulster | 12487 | G | 3041 | Sturgeon Pool | N |  | 8 | [13 empty] | NM | N | POWERONE PVI 3.0 POWERONE PVI 5.0 | 2015-03-18 | 2015-03-26 | 6 | 2015-03-26 | [14 empty] | 2015-05-06 | 2015-05-13 |  | Y
Central Hudson |  | New York State Solar Farm | CH-04036 | Newburgh | Newburgh | Orange | 12550 | G | 5001 | Marlboro | N |  | 12 | [13 empty] | NM | N | (2) POWERONE PVI 6000 | 2015-03-18 | 2015-03-30 | 8 | 2015-03-30 | [14 empty] | 2015-04-30 | 2015-05-06 |  | Y
Central Hudson |  | NRG Home Solar | CH-04209 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 7011 | Hibernia | N |  | 5.805 | [13 empty] | NM | N | 27 - ENPHASE ENERGY M-215 | 2015-03-26 | 2015-04-02 | 5 | 2015-04-02 | [14 empty] | 2015-11-19 | 2015-11-30 |  | Y
Central Hudson |  | Green Hybrid Energy Solutions | CH-01163 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8093 | Fishkill Plains | N |  | 25 | [13 empty] | NM | N | 1 - SOLAREDGE SE11400, SE7600, SE6000 | 2015-04-13 | 2015-04-27 | 10 | 2015-04-27 | [8 empty] | 350 | 350 |  |  |  |  | 2015-07-23 | 2015-07-29 |  | Y
Central Hudson |  | Hudson Solar | CH-02034 | Kingston | W Shokan | Ulster | 12494 | G | 3011 | Woodstock | N |  | 7 | [13 empty] | NM | N | SMA AMERICA SB7000 TL-US-22 | 2015-03-18 | 2015-03-26 | 6 | 2015-03-26 | [14 empty] | 2015-07-09 | 2015-07-16 |  | Y
Central Hudson |  | Hudson Solar | CH-02330 | Newburgh | Campbell Hall |  | 10916 | G | 5051 | Maybrook | TBD |  | 12 | [13 empty] | NM | N | (2) SMA AMERICA SB6000 | 2015-03-18 | 2015-03-27 | 7 | 2015-03-27 | [17 empty] | W |  | Transformer upgrade required to accommodate PV installation. Utility System Upgrade Costs TBD. Customer already had net meter prior to application.
Central Hudson |  | SolarCity | CH-07864 | Kingston | Kingston |  | 12401 | G | 1003 | Jansen Ave | TBD |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A US | 2015-03-18 | 2015-03-26 | 6 | 2015-03-26 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | SolarCity | CH-07887 | Poughkeepsie | Ancram |  | 12502 | G | 7091 | Pulvers Corners | TBD |  | 6.6 | [13 empty] | NM | N | 1 - ABB PVI-3.6-OUTD 1 - ABB PVI-3.0-OUTD | 2015-03-18 | 2015-03-25 | 5 | 2015-03-25 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | Seed Solar | CH-08860 | Kingston | Saugerties | Ulster | 12477 | G | 3001 | Saugerties | N |  | 5 | [13 empty] | NM | N | SMA 5000 TL | 2015-03-18 | 2015-03-26 | 6 | 2015-03-26 | [14 empty] | 2015-06-01 | 2015-06-05 |  | Y
Central Hudson |  | Sungevity Inc | CH-09218 | Newburgh | Newburgh | Orange | 12550 | G | 4027 | Coldenham | N |  | 7 | [13 empty] | NM | N | (1) SMA AMERICA SB7000US-12 | 2015-03-18 | 2015-03-30 | 8 | 2015-03-30 | [14 empty] | 2015-04-22 | 2015-04-28 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-03426 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 6 | [13 empty] | NM | N | (1) SMA AMERICA SB6000TL | 2015-03-19 | 2015-03-26 | 5 | 2015-03-26 | [14 empty] | 2015-09-09 | 2015-09-16 |  | Y
Central Hudson |  | NRG Home Solar | CH-04143 | Newburgh | Milton |  | 12547 | G | 5002 | Marlboro | TBD |  | 6.02 | [13 empty] | NM | N | (28) ENPHASE ENERGY M-215-60-2LL-S22-IG | 2015-03-19 | 2015-03-26 | 5 | 2015-03-26 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | NRG Home Solar | CH-04373 | Fishkill | Wappingers Falls | Dutchess | 12590 | G | 8091 | Fishkill Plains | N |  | 7.09 | [13 empty] | NM | N | (33) ENPHASE ENERGY M-215-60-2LL-S22-IG | 2015-03-19 | 2015-03-26 | 5 | 2015-03-26 | [14 empty] | 2015-12-02 | 2015-12-02 |  | Y
Central Hudson |  | SolarCity | CH-05758 | Kingston | Lk Katrine | Ulster | 12449 | G | 1021 | East Kingston | N |  | 22.8 | [13 empty] | NM | N | (2) FRONIUS IG PLUS A 11.4 | 2015-03-19 | 2015-03-26 | 5 | 2015-03-26 | [8 empty] | 350 | 350 |  |  |  |  | 2015-05-11 | 2015-05-11 |  | Y
Central Hudson |  | SolarCity | CH-06612 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6045 | Spackenkill | N |  | 3.6 | [13 empty] | NM | N | ABB PVI-3.6-OUTD | 2015-03-19 | 2015-03-26 | 5 | 2015-03-26 | [14 empty] | 2015-06-01 | 2015-06-08 |  | Y
Central Hudson |  | SolarCity | CH-07057 | Newburgh | Newburgh | Orange | 12550 | G | 4015 | West Balmville | N |  | 6 | [13 empty] | NM | N | (1) ABB PVI-6000-OUTD | 2015-03-19 | 2015-03-26 | 5 | 2015-03-26 | [14 empty] | 2015-04-27 | 2015-05-01 |  | Y
Central Hudson |  | New York State Solar Farm | CH-04055 | Newburgh | New Windsor | Orange | 12553 | G | 4095 | Bethlehem Rd | N |  | 7.2 | [13 empty] | NM | N | (1) POWERONE PVI-4.2 (1) POWERONE PVI-3.0 | 2015-03-20 | 2015-03-27 | 5 | 2015-03-27 | [14 empty] | 2015-04-27 | 2015-05-04 |  | Y
Central Hudson |  | NRG Home Solar | CH-04427 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8071 | Shenandoah | N |  | 6.88 | [13 empty] | NM | N | (32) ENPHASE ENERGY M-215-60-2LL-S22-IG | 2015-03-20 | 2015-03-27 | 5 | 2015-03-27 | [14 empty] | 2015-10-08 | 2015-10-13 |  | Y
Central Hudson |  | SolarCity | CH-07223 | Kingston | Kingston | Ulster | 12401 | G | 1013 | Boulevard | N |  | 4.2 | [13 empty] | NM | N | ABB PVI-4.2-OUTD-S US | 2015-03-20 | 2015-03-26 | 4 | 2015-03-26 | [14 empty] | 2015-05-05 | 2015-05-12 |  | Y
Central Hudson |  | Monolith Solar Associates LLC | CH-02660 | Catskill | Coxsackie | Greene | 12051 | G | 1074 | Coxsackie | N | CH-02660 | 6 | [13 empty] | NM | N | SMA 6000-22 | 2015-03-23 | 2015-03-30 | 5 | 2015-03-30 | [14 empty] | 2015-06-05 | 2015-06-12 |  | Y
Central Hudson |  | Positive Energy NY, LLC | CH-02929 | Catskill | Westerlo | Albany | 12193 | G | 1092 | Westerlo | N | CH-02929 | 8 | [13 empty] | NM | N | SMA SB8000-TL-12 | 2015-03-23 | 2015-03-30 | 5 | 2015-03-30 | [14 empty] | 2015-08-10 | 2015-08-17 |  | W
Central Hudson |  | Verengo Solar | CH-09917 | Newburgh | New Windsor | Orange | 12553 | G | 4095 | Bethlehem Rd | N |  | 7.095 | [13 empty] | NM | N | (33) ENPHASE ENERGY M215-60-S22-IG | 2015-03-23 | 2015-03-30 | 5 | 2015-03-30 | [14 empty] | 2015-06-19 | 2015-06-25 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-03505 | Newburgh | Newburgh | Orange | 12550 | G | 4024 | Coldenham | N |  | 13 | [13 empty] | NM | N | (1) SMA AMERICA SB6000 (1) SMA AMERICA SB7000 | 2015-03-24 | 2015-04-02 | 7 | 2015-04-02 | [14 empty] | 2015-06-03 | 2015-06-10 |  | Y
Central Hudson |  | Monolith Solar Associates LLC | CH-02640 | Catskill | Hannacroix | Greene | 12087 | G | 1083 | New Baltimore | N |  | 7.7 | [13 empty] | NM | N | SMA SB7700-US-TL | 2015-03-24 | 2015-04-02 | 7 | 2015-04-02 | [14 empty] | 2015-06-05 | 2015-06-12 |  | Y
Central Hudson |  | SolarCity | CH-06654 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6091 | Manchester | N |  | 7.2 | [13 empty] | NM | N | 2 - ABB PVI-3.6-OUTD | 2015-03-24 | 2015-04-07 | 9 | 2015-04-07 | [14 empty] | 2015-06-26 | 2015-07-02 |  | Y
Central Hudson |  | Sungevity Inc | CH-09396 | Catskill | Coxsackie | Greene | 12051 | G | 1076 | Coxsackie | N |  | 6 | [13 empty] | NM | N | SMA SB6000TL-US-22 | 2015-03-24 | 2015-03-30 | 4 | 2015-03-30 | [14 empty] | 2015-07-07 | 2015-07-14 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03646 | Kingston | Kingston | Ulster | 12401 | G | 1022 | East Kingston | N |  | 155.2 | [13 empty] | NM | N | (6) AE 3TL-23 & (1) AE 3TL-16 | 2015-05-01 | 2015-05-22 | 15 | 2015-05-22 | 2015-05-01 | 2015-05-22 | 15 | [11 empty] | 2015-07-01 | 2015-07-09 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03664 | Kingston | Bloomington | Ulster | 12411 | G | 1011 | Boulevard | N |  | 10 | [13 empty] | NM | N | SOLAREDGE 10000 A-US | 2015-03-25 | 2015-04-06 | 7 | 2015-04-06 | [14 empty] | 2015-05-07 | 2015-05-13 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03813 | Newburgh | New Paltz | Ulster | 12561 | G | 5023 | Ohioville | N |  | 5 | [13 empty] | NM | N | (1) SOLAREDGE 50000 | 2015-03-25 | 2015-04-06 | 7 | 2015-04-06 | [14 empty] | 2015-06-24 | 2015-07-01 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00873 | Poughkeepsie | Lagrangevl | Dutchess | 12540 | G | 6053 | Todd Hill | N |  | 8.815 | [13 empty] | NM | N | 41 - ENPHASE M215 | 2015-04-09 | 2015-04-09 | 0 | 2015-04-09 | [14 empty] | 2015-05-19 | 2015-05-19 |  | Y
Central Hudson |  | Kool-Temp | CH-02574 | Catskill | Athens | Greene | 12015 | G | 2002 | North Catskill | N |  | 1.5 | [13 empty] | NM | N | FRONIUS GALVO 1.5-1 | 2015-03-25 | 2015-04-06 | 7 | 2015-04-06 | [14 empty] | 2016-07-11 | 2016-07-18 |  | Y
Central Hudson |  | SolarCity | CH-07423 | Newburgh | Newburgh | Orange | 12550 | G | 4024 | Coldenham | N |  | 3 | [13 empty] | NM | N | (1) ABB PVI-3.0-OUTD-S | 2015-03-25 | 2015-04-02 | 6 | 2015-04-02 | [14 empty] | 2015-05-05 | 2015-05-11 |  | Y
Central Hudson |  | SolarCity | CH-07807 | Kingston | Hurley | Ulster | 12443 | G | 2094 | Hurley Ave | N | CH-05647 | 3 | [13 empty] | NM | N | POWERONE PVI-3.0-OUTD-S-US | 2015-03-25 | 2015-04-01 | 5 | 2015-04-01 | [14 empty] | 2015-04-17 | 2015-04-24 |  | Y
Central Hudson |  | Solar Generation | CH-08264 | Kingston | High Falls |  | 12440 | G | 3024 | High Falls | TBD |  | 14 | [13 empty] | NM | N | 2 SMA SB7000 TL | 2015-03-25 | 2015-03-27 | 2 | 2015-03-27 | [17 empty] | W
Central Hudson |  | Verengo Solar | CH-09779 | Newburgh | Newburgh | Orange | 12550 | G | 5004 | Marlboro | N |  | 7.955 | [13 empty] | NM | N | (37) ENPHASE ENERGY M215-60-S22-IG | 2015-04-01 | 2015-04-09 | 5 | 2015-04-09 | [14 empty] | 2015-07-21 | 2015-07-28 |  | Y
Central Hudson |  | Verengo Solar | CH-09784 | Newburgh | Marlboro | Ulster | 12542 | G | 5004 | Marlboro | N |  | 5.375 | [13 empty] | NM | N | (25) ENPHASE ENERGY M215-60-S22-IG | 2015-04-01 | 2015-04-09 | 5 | 2015-04-09 | [14 empty] | 2015-05-13 | 2015-05-18 |  | Y
Central Hudson |  | Verengo Solar | CH-09828 | Newburgh | Newburgh | Orange | 12550 | G | 4015 | West Balmville | N |  | 5.805 | [13 empty] | NM | N | (27) ENPHASE ENERGY M215-60-S22-IG | 2015-04-01 | 2015-04-09 | 5 | 2015-04-09 | [14 empty] | 2015-06-01 | 2015-06-08 |  | Y
Central Hudson |  | Verengo Solar | CH-09838 | Newburgh | Milton | Ulster | 12547 | G | 5003 | Marlboro | N |  | 12.47 | [13 empty] | NM | N | (58) ENPHASE ENERGY M215-60-S22-IG | 2015-04-02 | 2015-04-10 | 5 | 2015-04-10 | [8 empty] | 350 | 350 |  |  |  |  | 2015-07-20 | 2015-07-21 |  | Y
Central Hudson |  | Verengo Solar | CH-09867 | Fishkill | Fishkill | Dutchess | 12524 | G | 8072 | Shenandoah | N |  | 4.73 | [13 empty] | NM | N | (22) ENPHASE ENERGY M215-60-S22-IG | 2015-03-25 | 2015-04-09 | 10 | 2015-04-09 | [14 empty] | 2015-06-09 | 2015-06-16 |  | Y
Central Hudson |  | NRG Home Solar | CH-04846 | Newburgh | New Windsor |  | 12553 | G | 4097 | Bethlehem Rd | TBD |  | 5.8 | [13 empty] | NM | N | (27) ENPHASE ENERGY M215-60-2LL-S22-IG | 2015-03-26 | 2015-04-02 | 5 | 2015-04-02 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | SolarCity | CH-04928 | Kingston | Kingston |  | 12401 | G | 1024 | East Kingston | TBD |  | 3 | [13 empty] | NM | N | SOLAREDGE SE3000A US | 2015-03-26 | 2015-04-08 | 8 | 2015-04-08 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | NRG Home Solar | CH-04599 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8092 | Fishkill Plains | N |  | 5.37 | [13 empty] | NM | N | (25) ENPHASE ENERGY M-215-60-2LL-S22-IG | 2015-04-07 | 2015-04-14 | 5 | 2015-04-14 | [14 empty] | 2015-08-04 | 2015-08-11 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00871 | Poughkeepsie | Pine Plns | Dutchess | 12567 | G | 7091 | Pulvers Corners | N |  | 5.16 | [13 empty] | NM | N | 24 - ENPHASE M215 | 2015-03-27 | 2015-04-10 | 9 | 2015-04-10 | [14 empty] | 2015-05-01 | 2015-05-15 |  | Y
Central Hudson |  | SolarCity | CH-05528 | Catskill | Medusa | Albany | 12120 | G | 1092 | Westerlo | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A US | 2015-03-27 | 2015-04-08 | 7 | 2015-04-08 | [14 empty] | 2015-05-08 | 2015-05-15 |  | Y
Central Hudson |  | SolarCity | CH-05794 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6043 | Spackenkill | N |  | 4.2 | [13 empty] | NM | N | ABB PVI-4.2-OUTD | 2015-03-27 | 2015-04-09 | 8 | 2015-04-09 | [14 empty] | 2015-05-27 | 2015-06-03 |  | Y
Central Hudson |  | SolarCity | CH-07427 | Newburgh | Newburgh | Orange | 12550 | G | 4015 | West Balmville | N |  | 6 | [13 empty] | NM | N | (1) ABB PVI-6000-OUTD | 2015-03-27 | 2015-04-09 | 8 | 2015-04-09 | [14 empty] | 2015-05-01 | 2015-05-08 |  | Y
Central Hudson |  | Sunrun Inc. | CH-08342 | Fishkill | Garrison | Putnam | 10524 | G | 8066 | Merritt Park | N |  | 8 | [13 empty] | NM | N | (1) ABB PVI-3.0-OUTD-S-US-A (1) ABB PVI-5000-OUTD-US-A | 2015-03-27 | 2015-04-09 | 8 | 2015-04-09 | [14 empty] | 2015-05-22 | 2015-06-01 |  | Y
Central Hudson |  | Verengo Solar | CH-09871 | Newburgh | Newburgh | Orange | 12550 | G | 4024 | Coldenham | N |  | 11.18 | [13 empty] | NM | N | (52) ENPHASE ENERGY M215-60-S22-IG | 2015-04-07 | 2015-04-21 | 10 | 2015-04-21 | [14 empty] | 2015-07-20 | 2015-07-24 |  | Y
Central Hudson |  | SolarCity | CH-05134 | Newburgh | Newburgh | Orange | 12550 | G | 4023 | Coldenham | N |  | 6.6 | [13 empty] | NM | N | (1) ABB PVI-3.6-OUTD-S (1) ABB PVI-3.0-OUTD-S | 2015-03-30 | 2015-04-13 | 9 | 2015-04-13 | [14 empty] | 2015-05-01 | 2015-05-08 |  | Y
Central Hudson |  | SolarCity | CH-05163 | Newburgh | Newburgh | Orange | 12550 | G | 410 | Montgomery St | N |  | 6 | [13 empty] | NM | N | (1) SOLAREDGE SE6000A | 2015-03-30 | 2015-04-07 | 5 | 2015-04-07 | [14 empty] | 2015-06-01 | 2015-06-08 |  | Y
Central Hudson |  | SolarCity | CH-06794 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8091 | Fishkill Plains | N |  | 6 | [13 empty] | NM | N | (1) ABB PVI-6000-OUTD | 2015-03-30 | 2015-04-07 | 5 | 2015-04-07 | [14 empty] | 2015-06-01 | 2015-06-08 |  | Y
Central Hudson |  | NRG Home Solar | CH-04335 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6096 | Manchester | N |  | 6.45 | [13 empty] | NM | N | 30 - ENPHASE ENERGY M-215 | 2015-03-31 | 2015-04-08 | 5 | 2015-04-08 | [14 empty] | 2015-08-04 | 2015-08-11 |  | Y
Central Hudson |  | SolarCity | CH-05643 | Kingston | Rosendale | Ulster | 12472 | G | 3022 | High Falls | N |  | 3 | [13 empty] | NM | N | ABB PVI-3.0-OUTD-S US | 2015-03-31 | 2015-04-08 | 5 | 2015-04-08 | [14 empty] | 2016-03-04 | 2016-03-11 |  | Y
Central Hudson |  | SolarCity | CH-07700 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6097 | Manchester | N |  | 3 | [13 empty] | NM | N | ABB PVI-3.0-OUTD | 2015-03-31 | 2015-04-08 | 5 | 2015-04-08 | [14 empty] | 2015-05-26 | 2015-06-02 |  | Y
Central Hudson |  | Sungevity Inc | CH-09447 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8091 | Fishkill Plains | N |  | 8 | [13 empty] | NM | N | (1) ABB PVI-4.2-OUTD-S (1) ABB PVI-3.8-OUTD-S | 2015-03-31 | 2015-04-15 | 10 | 2015-04-15 | [14 empty] | 2015-05-12 | 2015-05-18 |  | Y
Central Hudson |  | Verengo Solar | CH-09787 | Kingston | Port Ewen | Ulster | 12466 | G | 1012 | Boulevard | N |  | 6.02 | [13 empty] | NM | N | 28 ENPHASE M215-60-S22-IG | 2015-03-31 | 2015-04-15 | 10 | 2015-04-15 | [14 empty] | 2015-06-11 | 2015-06-18 |  | Y
Central Hudson |  | Verengo Solar | CH-09802 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7052 | Rhinebeck | N |  | 12.47 | [13 empty] | NM | N | 58 - ENPHASE ENERGY M215 | 2015-03-31 | 2015-04-08 | 5 | 2015-04-08 | [14 empty] | 2015-06-16 | 2015-06-23 |  | Y
Central Hudson |  | Verengo Solar | CH-09858 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 7025 | Tinkertown | N |  | 8.17 | [13 empty] | NM | N | 38 - ENPHASE ENERGY M215 | 2015-03-31 | 2015-04-08 | 5 | 2015-04-08 | [14 empty] | 2015-07-28 | 2015-08-04 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03660 | Kingston | Tillson |  | 12486 | G | 3021 | High Falls | TBD |  | 7.6 | [13 empty] | NM | N | SOLAREDGE 7600 A-U | 2015-04-01 | 2015-04-16 | 10 | 2015-04-16 | [17 empty] | W |  | 4/3/2015 Company Holiday.
Central Hudson |  | Direct Energy Solar | CH-01022 | Newburgh | Marlboro | Ulster | 12542 | G | 5003 | Marlboro | N |  | 7.31 | [13 empty] | NM | N | (34) ENPHASE M215 | 2015-04-10 | 2015-04-17 | 5 | 2015-04-17 | [14 empty] | 2015-05-28 | 2015-06-04 |  | Y
Central Hudson |  | SolarCity | CH-05806 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6046 | Spackenkill | N |  | 7.2 | [13 empty] | NM | N | 1 - ABB PVI-4.2-OUTD 1 - ABB PVI-3.0-OUTD | 2015-04-01 | 2015-04-09 | 5 | 2015-04-09 | [14 empty] | 2015-05-01 | 2015-05-08 |  | Y
Central Hudson |  | SolarCity | CH-06380 | Newburgh | Highland Mls | Orange | 10930 | G | 4041 | Union Ave | N |  | 4.2 | [13 empty] | NM | N | (1) ABB PVI-4.2-OUTD-S | 2015-04-01 | 2015-04-16 | 10 | 2015-04-16 | [14 empty] | 2015-05-13 | 2015-05-19 |  | Y
Central Hudson |  | SolarCity | CH-05036 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7061 | Milan | N |  | 4.2 | [13 empty] | NM | N | ABB PVI-4.2-OUTD | 2015-04-02 | 2015-04-10 | 5 | 2015-04-10 | [14 empty] | 2015-05-04 | 2015-05-11 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-03474 | Newburgh | Montgomery | Orange | 12549 | G | 5073 | Montgomery | N |  | 14 | [13 empty] | NM | N | (1) SMA AMERICA SB3000TL (1) SMA AMERICA SB5000TL (1) SMA AMERICA SB6000TL | 2015-04-06 | 2015-04-20 | 10 | 2015-04-20 | [8 empty] | 350 | 350 |  |  |  |  | 2015-10-15 | 2015-10-30 |  | Y
Central Hudson |  | New York State Solar Farm | CH-04088 | Newburgh | Wallkill | Ulster | 12589 | G | 5041 | East Walden | N |  | 6 | [13 empty] | NM | N | (1) Aurora POWERONE PVI 6.0 | 2015-04-28 | 2015-05-05 | 5 | 2015-05-05 | [14 empty] | 2015-05-27 | 2015-06-03 |  | Y
Central Hudson |  | NRG Home Solar | CH-04387 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8046 | Myers Corners | N |  | 3.225 | [13 empty] | NM | N | (15) ENPHASE ENERGY M-215-60-2LL-S22-IG | 2015-04-06 | 2015-04-20 | 10 | 2015-04-20 | [14 empty] | 2015-08-27 | 2015-09-03 |  | Y
Central Hudson |  | NRG Home Solar | CH-04593 | Fishkill | Wappingrs Falls |  | 12590 | G | 8046 | Myers Corners | TBD |  | 7 | [13 empty] | NM | N | (28) ENPHASE ENERGY M-250-60-2LL-S22 | 2015-04-15 | 2015-04-28 | 9 | 2015-04-28 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | NRG Home Solar | CH-04753 | Kingston | Kerhonkson | Ulster | 12446 | G | 3082 | Kerhonkson | N |  | 5.81 | [13 empty] | NM | N | 27 ENPHASE M-215-60-2LL-S22-IG | 2015-04-06 | 2015-04-16 | 8 | 2015-04-16 | [14 empty] | 2015-10-29 | 2015-10-30 |  | Y
Central Hudson |  | SolarCity | CH-05241 | Kingston | Stone Ridge | Ulster | 12484 | G | 3023 | High Falls | N |  | 10 | [13 empty] | NM | N | FRONIUS IG PLUS A 10.0 | 2015-04-06 | 2015-04-17 | 9 | 2015-04-17 | [8 empty] | 350 | 350 |  | 2015-05-28 | 2015-05-28 | 2015-06-22 | 2015-06-22 | 2015-07-01 |  | Y
Central Hudson |  | SolarCity | CH-06594 | Kingston | Saugerties | Ulster | 12477 | G | 1021 | East Kingston | N |  | 7.5 | [13 empty] | NM | N | FRONIUS IG PLUS A 7.5 | 2015-04-06 | 2015-04-17 | 9 | 2015-04-17 | [14 empty] | 2015-05-01 | 2015-05-08 |  | Y
Central Hudson |  | SolarCity | CH-06729 | Poughkeepsie | Wappingers Falls | Dutchess | 12590 | G | 6052 | Todd Hill | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000-OUTD-US | 2015-04-06 | 2015-04-13 | 5 | 2015-04-13 | [14 empty] | 2015-05-04 | 2015-05-11 |  | Y
Central Hudson |  | Solar Generation | CH-08160 | Kingston | Woodstock | Ulster | 12498 | G | 3012 | Woodstock | N |  | 6 | [13 empty] | NM | N | SMA SB 6000 TL | 2015-04-06 | 2015-04-17 | 9 | 2015-04-17 | [14 empty] | 2015-07-13 | 2015-07-20 |  | Y
Central Hudson |  | Verengo Solar | CH-09933 | Newburgh | Marlboro |  | 12542 | G | 5002 | Marlboro | TBD |  | 7.74 | [13 empty] | NM | N | (36) ENPHASE ENERGY M215-60-S22-IG | 2015-04-06 | 2015-04-13 | 5 | 2015-04-13 | [17 empty] | W
Central Hudson |  | NRG Home Solar | CH-04294 | Kingston | Saugerties | Ulster | 12477 | G | 3003 | Saugerties | N |  | 3.25 | [13 empty] | NM | N | 13 ENPHASE M-250-60-2LL-S22 | 2015-04-07 | 2015-04-20 | 9 | 2015-04-20 | [14 empty] | 2015-07-23 | 2015-07-29 |  | Y
Central Hudson |  | NRG Home Solar | CH-04344 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6056 | Todd Hill | N |  | 10 | [13 empty] | NM | N | 40 - ENPHASE ENERGY M-250 | 2015-04-07 | 2015-04-21 | 10 | 2015-04-21 | [14 empty] | 2015-08-04 | 2015-08-11 |  | Y
Central Hudson |  | NRG Home Solar | CH-04592 | Fishkill | Wappingers Falls | Dutchess | 12590 | G | 8046 | Myers Corners | N |  | 5.8 | [13 empty] | NM | N | (27) ENPHASE ENERGY M-215-60-2LL-S22-IG | 2015-04-07 | 2015-04-21 | 10 | 2015-04-21 | [14 empty] | 2015-09-25 | 2015-10-01 |  | Y
Central Hudson |  | Natural Energy Solutions | CH-02766 | Poughkeepsie | Clinton Corners | Dutchess | 12514 | G | 7013 | Hibernia | N |  | 10 | [13 empty] | NM | N | 2 - SOLAR EDGE SE5000A | 2015-05-15 | 2015-05-22 | 5 | 2015-05-22 | [14 empty] | 2015-07-15 | 2015-07-16 |  | Y
Central Hudson |  | SolarCity | CH-05911 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6051 | Todd Hill | N |  | 4.2 | [13 empty] | NM | N | ABB PVI-4.2-OUTD | 2015-04-07 | 2015-04-21 | 10 | 2015-04-21 | [14 empty] | 2015-05-26 | 2015-06-02 |  | Y
Central Hudson |  | SolarCity | CH-05988 | Newburgh | Highland | Ulster | 12528 | G | 5082 | Highland | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000-OUTD | 2015-04-07 | 2015-04-14 | 5 | 2015-04-14 | [14 empty] | 2015-06-22 | 2015-06-29 |  | Y
Central Hudson |  | SolarCity | CH-06878 | Fishkill | Fishkill | Dutchess | 12524 | G | 8094 | Fishkill Plains | N |  | 6 | [13 empty] | NM | N | (1) ABB PVI-6000-OUTD | 2015-04-15 | 2015-04-28 | 9 | 2015-04-28 | [14 empty] | 2015-05-01 | 2015-05-08 |  | Y
Central Hudson |  | Sungevity Inc | CH-09405 | Kingston | Accord | Ulster | 12404 | G | 3024 | High Falls | N |  | 7.2 | [13 empty] | NM | N | 2 SMA SB3800TL-US-22 | 2015-04-07 | 2015-04-20 | 9 | 2015-04-20 | [14 empty] | 2015-07-06 | 2015-07-10 |  | Y
Central Hudson |  | NRG Home Solar | CH-04252 | Catskill | Ravena | Albany | 12143 | G | 1083 | New Baltimore | N |  | 3.87 | [13 empty] | NM | N | 18 ENPHASE M215-60-2LL-S22-IG | 2015-04-08 | 2015-04-20 | 8 | 2015-04-20 | [14 empty] | 2015-08-27 | 2015-09-03 |  | Y
Central Hudson |  | NRG Home Solar | CH-04810 | Kingston | Tillson |  | 12486 | G | 3021 | High Falls | TBD |  | 6.02 | [13 empty] | NM | N | 28 ENPHASE M-215-60-2LL-S22-IG | 2015-04-08 | 2015-04-20 | 8 | 2015-04-20 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | SolarCity | CH-06760 | Poughkeepsie | Red Hook |  | 12571 | G | 7054 | Rhinebeck | TBD |  | 3 | [13 empty] | NM | N | ABB PVI-3.0-OUTD | 2015-04-08 | 2015-04-15 | 5 | 2015-04-15 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | Verengo Solar | CH-09790 | Kingston | Saugerties | Ulster | 12477 | G | 3002 | Saugerties | N |  | 12.04 | [13 empty] | NM | N | 56 ENPHASE M215-60-S22-IG | 2015-04-08 | 2015-04-20 | 8 | 2015-04-20 | [14 empty] | 2015-06-11 | 2015-06-18 |  | Y
Central Hudson |  | New York State Solar Farm | CH-04033 | Newburgh | New Paltz | Ulster | 12561 | G | 5031 | Galeville | N |  | 10 | [13 empty] | NM | N | (2) ABB POWERONE PVI-5000 | 2015-04-16 | 2015-04-29 | 9 | 2015-04-29 | [14 empty] | 2015-06-09 | 2015-06-16 |  | Y
Central Hudson |  | NRG Home Solar | CH-04196 | Newburgh | Newburgh |  | 12550 | G | 4023 | Coldenham | TBD |  | 7.31 | [13 empty] | NM | N | (34) ENPHASE ENERGY M-215-60-2LL-S22-IG | 2015-04-09 | 2015-04-23 | 10 | 2015-04-23 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | NRG Home Solar | CH-04418 | Fishkill | Beacon | Dutchess | 12508 | G | 8013 | Forgebrook | N |  | 4.94 | [13 empty] | NM | N | (23) ENPHASE ENERGY M-215-60-2LL-S22-IG | 2015-04-09 | 2015-04-23 | 10 | 2015-04-23 | [14 empty] | 2015-10-20 | 2015-10-23 |  | Y
Central Hudson |  | NRG Home Solar | CH-04517 | Catskill | Athens |  | 12015 | G | 1074 | Coxsackie | TBD |  | 3.87 | [13 empty] | NM | N | 18 ENPHASE M215-60-2LL-S22-IG | 2015-04-09 | 2015-04-23 | 10 | 2015-04-23 | [17 empty] | W
Central Hudson |  | NRG Home Solar | CH-04736 | Newburgh | New Paltz | Ulster | 12561 | G | 5031 | Galeville | N | CH-04736 | 5.375 | [13 empty] | NM | N | (25) ENPHASE ENERGY M-215-60-2LL-S22-IG | 2015-04-09 | 2015-04-23 | 10 | 2015-04-23 | [14 empty] | 2015-10-14 | 2015-10-20 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00853 | Newburgh | Newburgh | Orange | 12550 | G | 4011 | West Balmville | N |  | 8.25 | [13 empty] | NM | N | (33) ENPHASE M250 | 2015-04-09 | 2015-04-23 | 10 | 2015-04-23 | [14 empty] | 2015-06-08 | 2015-06-10 |  | Y
Central Hudson |  | SolarCity | CH-07914 | Newburgh | Marlboro |  | 12542 | G | 5002 | Marlboro | TBD |  | 7.5 | [13 empty] | NM | N | (1) FRONIUS IG PLUS A 7.5 | 2015-04-09 | 2015-04-23 | 10 | 2015-04-23 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | Verengo Solar | CH-09803 | Poughkeepsie | Pine Plns | Dutchess | 12567 | G | 7091 | Pulvers Corners | N |  | 8.6 | [13 empty] | NM | N | 40 - ENPHASE ENERGY M215 | 2015-04-09 | 2015-04-16 | 5 | 2015-04-16 | [14 empty] | 2015-07-02 | 2015-07-10 |  | Y
Central Hudson |  | RGS Energy | CH-03039 | Newburgh | Newburgh | Orange | 12550 | G | 5001 | Marlboro | N |  | 4.25 | [13 empty] | NM | N | (17) ENPHASE M250-60-2LL-S22 | 2015-04-10 | 2015-04-24 | 10 | 2015-04-24 | [14 empty] | 2015-07-30 | 2015-08-05 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-03415 | Newburgh | Newburgh | Orange | 12550 | G | 4013 | West Balmville | N |  | 3 | [13 empty] | NM | N | (1) SMA SMERICA SB3000TL | 2015-04-10 | 2015-04-24 | 10 | 2015-04-24 | [14 empty] | 2015-06-12 | 2015-06-19 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-03418 | Newburgh | Newburgh | Orange | 12550 | G | 4024 | Coldenham | N |  | 6 | [13 empty] | NM | N | (1) SMA AMERICA SB60000TL | 2015-04-10 | 2015-04-24 | 10 | 2015-04-24 | [14 empty] | 2015-07-24 | 2015-07-27 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-03436 | Newburgh | Cornwall | Orange | 12518 | G | 4041 | Union Ave | N |  | 3.8 | [13 empty] | NM | N | (1) SMA AMERICA SB3800TL | 2015-04-10 | 2015-04-24 | 10 | 2015-04-24 | [14 empty] | 2015-06-12 | 2015-06-18 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-03497 | Newburgh | New Windsor | Orange | 12553 | G | 4091 | Bethlehem Rd | N |  | 15 | [13 empty] | NM | N | (1) FRONIUS IG PLUS 10.0 (1) SMA AMERICA SB5000TL | 2015-04-10 | 2015-04-24 | 10 | 2015-04-24 | [14 empty] | 2015-07-27 | 2015-08-03 |  | Y
Central Hudson |  | NRG Home Solar | CH-04338 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6051 | Todd Hill | N |  | 4.945 | [13 empty] | NM | N | 23 - ENPHASE ENERGY M-215 | 2015-04-10 | 2015-04-17 | 5 | 2015-04-17 | [14 empty] | 2015-10-13 | 2015-10-20 |  | Y
Central Hudson |  | SolarCity | CH-06951 | Fishkill | Beacon | Dutchess | 12508 | G | 8087 | Tioronda | N |  | 5 | [13 empty] | NM | N | (1) ABB PVI-5000-OUTD-US | 2015-04-10 | 2015-04-24 | 10 | 2015-04-24 | [14 empty] | 2015-06-01 | 2015-06-08 |  | Y
Central Hudson |  | NRG Home Solar | CH-04124 | Poughkeepsie | Pine Plns | Dutchess | 12567 | G | 7091 | Pulvers Corners | N |  | 12.04 | [13 empty] | NM | N | 56 - ENPHASE ENERGY M-215 | 2015-04-13 | 2015-04-20 | 5 | 2015-04-20 | [14 empty] | 2015-10-15 | 2015-10-22 |  | Y
Central Hudson |  | NRG Home Solar | CH-04134 | Newburgh | Wallkill | Ulster | 12589 | G | 4011 | West Balmville | N |  | 8.25 | [13 empty] | NM | N | (33) ENPHASE ENERGY M-250-60-2LL-S22 | 2015-04-13 | 2015-04-27 | 10 | 2015-04-27 | [14 empty] | 2015-10-13 | 2015-10-15 |  | Y
Central Hudson |  | NRG Home Solar | CH-04144 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7062 | Milan | N |  | 4.25 | [13 empty] | NM | N | 17 - ENPHASE ENERGY M-250 | 2015-04-13 | 2015-04-20 | 5 | 2015-04-20 | [14 empty] | 2015-10-08 | 2015-10-15 |  | Y
Central Hudson |  | NRG Home Solar | CH-04337 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6051 | Todd Hill | N |  | 8.385 | [13 empty] | NM | N | 39 - ENPHASE ENERGY M-215 | 2015-04-13 | 2015-04-22 | 7 | 2015-04-22 | [14 empty] | 2015-10-19 | 2015-10-26 |  | Y
Central Hudson |  | SolarCity | CH-05453 | Newburgh | New Paltz | Ulster | 12561 | G | 5031 | Galeville | N |  | 6 | [13 empty] | NM | N | (1) ABB PVI-6000-OUTD | 2015-04-13 | 2015-04-27 | 10 | 2015-04-27 | [14 empty] | 2015-05-26 | 2015-06-02 |  | Y
Central Hudson |  | Sungevity Inc | CH-09539 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8095 | Fishkill Plains | N |  | 7 | [13 empty] | NM | N | (1) SMA AMERICA SB7000TL-US-22 | 2015-04-13 | 2015-04-27 | 10 | 2015-04-27 | [14 empty] | 2015-08-03 | 2015-08-07 |  | Y
Central Hudson |  | Verengo Solar | CH-09902 | Newburgh | Newburgh | Orange | 12550 | G | 4022 | Coldenham | N |  | 5.59 | [13 empty] | NM | N | (26) ENPHASE ENERGY M215-60-S22-IG | 2015-04-13 | 2015-04-27 | 10 | 2015-04-27 | [14 empty] | 2015-07-23 | 2015-07-29 |  | Y
Central Hudson |  | SolarCity | CH-05357 | Newburgh | Newburgh | Orange | 12550 | G | 4023 | Coldenham | N |  | 3.6 | [13 empty] | NM | N | ABB PVI-3.6-OUTD | 2015-04-22 | 2015-04-22 | 0 | 2015-04-22 | [14 empty] | 2015-05-27 | 2015-06-03 |  | Y
Central Hudson |  | Self | CH-08869 | Kingston | Stone Ridge | Ulster | 12484 | G | 3024 | High Falls | N |  | 6 | [13 empty] | NM | N | SMA SB6000-US-12 | 2015-04-14 | 2015-04-21 | 5 | 2015-04-21 | [14 empty] | 2015-06-01 | 2015-06-02 |  | Y
Central Hudson |  | Sungevity Inc | CH-09479 | Newburgh | Newburgh | Orange | 12550 | G | 4053 | Union Ave | N |  | 4.2 | [13 empty] | NM | N | ABB PVI-4.2 | 2015-05-08 | 2015-05-13 | 3 | 2015-05-13 | [14 empty] | 2015-07-20 | 2015-07-24 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-03465 | Newburgh | Newburgh |  | 12550 | G | 4022 | Coldenham | N |  | 6 | [13 empty] | NM | N | (1) SMA AMERICA SB6000TL | 2015-04-16 | 2015-04-28 | 8 | 2015-04-28 | [14 empty] | 2015-05-11 | 2015-05-14 |  | W
Central Hudson |  | Kasselman Solar | CH-03520 | Catskill | Coxsackie | Greene | 12051 | G | 1071 | Coxsackie | N | CH-03520 | 10.5 | [13 empty] | NM | N | 42 ENPHASE M-250 | 2015-04-16 | 2015-04-28 | 8 | 2015-04-28 | [14 empty] | 2015-06-18 | 2015-07-02 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03567 | Newburgh | New Paltz | Ulster | 12561 | G | 5031 | Galeville | N |  | 7.6 | [13 empty] | NM | N | (1) SOLAREDGE SE7600 | 2015-04-16 | 2015-04-29 | 9 | 2015-04-29 | [14 empty] | 2015-06-30 | 2015-07-08 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03792 | Newburgh | Gardiner |  | 12525 | G | 5033 | Galeville | TBD |  | 11.4 | [13 empty] | NM | N | (1) SOLAREDGE SE11400 | 2015-04-16 | 2015-04-28 | 8 | 2015-04-28 | [8 empty] | 350 | 350 |  | 2015-05-26 | 2015-05-26 | 2015-06-19 |  |  |  | W
Central Hudson |  | Lighthouse Solar | CH-03803 | Newburgh | New Paltz | Ulster | 12561 | G | 5024 | Ohioville | N |  | 10 | [13 empty] | NM | N | (1) SOLAREDGE 10000 | 2015-04-16 | 2015-04-29 | 9 | 2015-04-29 | [14 empty] | 2016-01-22 | 2016-01-26 |  | Y
Central Hudson |  | NRG Home Solar | CH-04159 | Newburgh | New Windsor | Orange | 12553 | G | 4092 | Bethlehem Rd | N |  | 4.51 | [13 empty] | NM | N | (21) ENPHASE ENERGY M-215-60-2LL-S22-IG | 2015-04-16 | 2015-04-28 | 8 | 2015-04-28 | [14 empty] | 2015-08-04 | 2015-08-11 |  | Y
Central Hudson |  | NRG Home Solar | CH-04591 | Fishkill | Poughkeepsie | Dutchess | 12603 | G | 8024 | Knapps Corners | N |  | 2.795 | [13 empty] | NM | N | 13 - ENPHASE ENERGY M-215 | 2015-04-30 | 2015-05-07 | 5 | 2015-05-07 | [14 empty] | 2015-10-30 | 2015-10-30 |  | Y
Central Hudson |  | NRG Home Solar | CH-04793 | Fishkill | Hopewell Junction | Dutchess | 12533 | G | 8091 | Fishkill Plains | N |  | 7.31 | [13 empty] | NM | N | (34) ENPHASE ENERGY M-215-60-2LL-S22-IG | 2015-04-16 | 2015-04-29 | 9 | 2015-04-29 | [14 empty] | 2015-11-17 | 2015-11-17 |  | Y
Central Hudson |  | Hudson Solar | CH-01210 | Kingston | Olive Brdg | Ulster | 12461 | G | 3023 | High Falls | N | CH-01210 | 6 | [13 empty] | NM | N | SMA AMERICA SB6000 TL-US-22 | 2015-04-16 | 2015-04-28 | 8 | 2015-04-28 | [14 empty] | 2015-09-18 | 2015-09-24 |  | Y
Central Hudson |  | Hudson Solar | CH-01836 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7054 | Rhinebeck | N |  | 5 | [13 empty] | NM | N | SMA AMERICA SB5000 | 2015-04-16 | 2015-04-23 | 5 | 2015-04-23 | [14 empty] | 2015-06-04 | 2015-06-11 |  | Y
Central Hudson |  | Hudson Solar | CH-01881 | Poughkeepsie | Millerton |  | 12546 | G | 7092 | Pulvers Corners | TBD |  | 5 | [13 empty] | NM | N | SMA AMERICA SB5000 | 2015-04-16 | 2015-04-23 | 5 | 2015-04-23 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | Hudson Solar | CH-01962 | Newburgh | Newburgh | Orange | 12550 | G | 4045 | Union Ave | N |  | 6 | [13 empty] | NM | N | (1) SMA AMERICA SB6000 | 2015-04-16 | 2015-04-28 | 8 | 2015-04-28 | [14 empty] | 2015-06-22 | 2015-06-29 |  | Y
Central Hudson |  | Hudson Solar | CH-02056 | Kingston | Saugerties | Ulster | 12477 | G | 2016 | Lincoln Park | N | CH-02056 | 3.8 | [13 empty] | NM | N | SMA AMERICA SB3800 TL-US-22 | 2015-04-16 | 2015-04-28 | 8 | 2015-04-28 | [14 empty] | 2015-09-25 | 2015-10-02 |  | Y
Central Hudson |  | Hudson Solar | CH-02203 | Newburgh | Marlboro |  | 12542 | G | 5004 | Marlboro | TBD |  | 17 | [13 empty] | NM | N | (1) SMA AMERICA SB10000 (1) SMA AMERICA SB7000 | 2015-04-16 | 2015-04-29 | 9 | 2015-04-29 | [8 empty] | 350 | 350 | [7 empty] | W |  | Customer already had net meter prior to application. Transformer upgrade required to accommodate PV installation.
Central Hudson |  | Hudson Solar | CH-02411 | Newburgh | New Paltz | Ulster | 12561 | G | 5023 | Ohioville | N |  | 7.6 | [13 empty] | NM | N | (1) SMA AMERICA SB3800 | 2015-04-16 | 2015-04-28 | 8 | 2015-04-28 | [14 empty] | 2015-08-28 | 2015-09-04 |  | W
Central Hudson |  | SolarCity | CH-05840 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 6073 | East Park | N |  | 5 | [13 empty] | NM | N | ABB PVI-5000-OUTD | 2015-04-16 | 2015-04-23 | 5 | 2015-04-23 | [14 empty] | 2015-06-30 | 2015-07-08 |  | Y
Central Hudson |  | NRG Home Solar | CH-04318 | Poughkeepsie | Rhinebeck |  | 12572 | G | 7071 | Stanfordville | TBD |  | 7 | [13 empty] | NM | N | 28 - ENPHASE ENERGY M-250 | 2015-04-17 | 2015-04-24 | 5 | 2015-04-24 | [8 empty] | 350 | 350 | [7 empty] | W |  | Customer already had net meter prior to application. Transformer upgrade required to accommodate PV installation. Utility System Upgrade Costs TBD.
Central Hudson |  | NRG Home Solar | CH-04371 | Newburgh | Highland | Ulster | 12528 | G | 5083 | Highland | N |  | 7.6 | [13 empty] | NM | N | SolarEdge SE7600A-US | 2015-04-17 | 2015-04-24 | 5 | 2015-04-24 | [14 empty] | 2015-10-13 | 2015-10-20 |  | Y
Central Hudson |  | Verengo Solar | CH-09794 | Kingston | Lk Katrine | Ulster | 12449 | G | 2016 | Lincoln Park | N |  | 6.02 | [13 empty] | NM | N | 28 ENPHASE M215-60-S22-IG | 2015-04-17 | 2015-04-28 | 7 | 2015-04-28 | [14 empty] | 2015-06-09 | 2015-06-16 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03655 | Catskill | Leeds | Greene | 12451 | G | 2005 | North Catskill | N |  | 5 | [13 empty] | NM | N | SOLAREDGE 5000 A-US | 2015-04-20 | 2015-04-28 | 6 | 2015-04-28 | [14 empty] | 2016-01-11 | 2016-01-18 |  | Y
Central Hudson |  | New York State Solar Farm | CH-03994 | Newburgh | New Paltz | Ulster | 12561 | G | 5024 | Ohioville | N |  | 12 | [13 empty] | NM | N | 2 - POWERONE-AURORA PVI 6.0 | 2015-04-27 | 2015-05-01 | 4 | 2015-05-01 | [14 empty] | 2015-05-27 | 2015-06-03 |  | Y
Central Hudson |  | NRG Home Solar | CH-04769 | Fishkill | Hopewell Jct |  | 12533 | G | 8095 | Fishkill Plains | TBD |  | 4.3 | [13 empty] | NM | N | 20 - ENPHASE ENERGY M-215 | 2015-04-20 | 2015-04-27 | 5 | 2015-04-27 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | SolarCity | CH-05798 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6044 | Spackenkill | N | CH-23114 | 3.6 | [13 empty] | NM | N | ABB PVI-3.6-OUTD | 2015-04-29 | 2015-05-06 | 5 | 2015-05-06 | [14 empty] | 2015-06-01 | 2015-06-08 |  | Y
Central Hudson |  | SolarCity | CH-07105 | Newburgh | New Windsor | Orange | 12553 | G | 4095 | Bethlehem Rd | N |  | 7.5 | [13 empty] | NM | N | FRONIUS IG PLUS A 7.5 | 2015-04-20 | 2015-04-27 | 5 | 2015-04-27 | [14 empty] | 2015-05-26 | 2015-06-02 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03807 | Newburgh | Montgomery | Orange | 12549 | G | 5073 | Montgomery | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000 | 2015-04-23 | 2015-04-30 | 5 | 2015-04-30 | [14 empty] | 2015-08-10 | 2015-08-17 |  | Y
Central Hudson |  | NRG Home Solar | CH-04125 | Newburgh | Highland | Ulster | 12528 | G | 5083 | Highland | N |  | 5.805 | [13 empty] | NM | N | 27 - ENPHASE ENERGY M-215 | 2015-04-21 | 2015-04-28 | 5 | 2015-04-28 | [14 empty] | 2015-10-13 | 2015-10-20 |  | Y
Central Hudson |  | NRG Home Solar | CH-00495 | Fishkill | Beacon | Dutchess | 12508 | G | 8085 | Tioronda | N |  | 3.225 | [13 empty] | NM | N | 15 - ENPHASE ENERGY M-215 | 2015-04-21 | 2015-04-28 | 5 | 2015-04-28 | [14 empty] | 2016-04-13 | 2016-04-18 |  | Y
Central Hudson |  | NRG Home Solar | CH-04343 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6046 | Spackenkill | N |  | 5.805 | [13 empty] | NM | N | 27 - ENPHASE ENERGY M-215 | 2015-04-21 | 2015-04-28 | 5 | 2015-04-28 | [14 empty] | 2015-10-27 | 2015-11-02 |  | Y
Central Hudson |  | NRG Home Solar | CH-04411 | Fishkill | Fishkill | Dutchess | 12524 | G | 8065 | Merritt Park | N |  | 3.225 | [13 empty] | NM | N | 15 - ENPHASE ENERGY M-215 | 2015-04-21 | 2015-04-28 | 5 | 2015-04-28 | [14 empty] | 2015-10-29 | 2015-10-30 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00881 | Newburgh | Highland | Ulster | 12528 | G | 5081 | Highland | N |  | 4.945 | [13 empty] | NM | N | 23 - ENPHASE M215 | 2015-04-21 | 2015-04-28 | 5 | 2015-04-28 | [14 empty] | 2015-06-05 | 2015-06-12 |  | Y
Central Hudson |  | Hudson Solar | CH-01230 | Poughkeepsie | Barrytown | Dutchess | 12507 | G | 7056 | Rhinebeck | N |  | 7.7 | [13 empty] | NM | N | SMA AMERICA SB7700 | 2015-04-21 | 2015-04-28 | 5 | 2015-04-28 | [14 empty] | 2015-04-28 | 2015-04-28 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Sungevity Inc | CH-09276 | Kingston | Cottekill | Ulster | 12419 | G | 3021 | High Falls | N |  | 10.8 | [13 empty] | NM | N | SMA AMERICA SB7000TL-US-22 SMA AMERICA SB3800TL-US-22 | 2015-04-21 | 2015-04-30 | 7 | 2015-04-30 | [14 empty] | 2015-06-23 | 2015-06-29 |  | Y
Central Hudson |  | Sungevity Inc | CH-09594 | Newburgh | Salisbury Mls | Orange | 12577 | G | 4097 | Bethlehem Rd | N |  | 8 | [13 empty] | NM | N | ABB PVI-4.2 (1) ABB PVI-3.8 (1) | 2015-04-28 | 2015-05-05 | 5 | 2015-05-05 | [14 empty] | 2015-06-09 | 2015-06-16 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03690 | Newburgh | New Paltz | Ulster | 12561 | G | 5011 | Modena | N |  | 6 | [13 empty] | NM | N | ABB/POWERONE PVI 6000 | 2015-04-22 | 2015-04-29 | 5 | 2015-04-29 | [14 empty] | 2015-08-31 | 2015-09-08 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03785 | Newburgh | New Paltz | Ulster | 12561 | G | 5021 | Ohioville | N |  | 10 | [13 empty] | NM | N | SOLAREDGE SE10000 | 2015-04-22 | 2015-04-29 | 5 | 2015-04-29 | [14 empty] | 2015-06-24 | 2015-07-01 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00903 | Kingston | Grahamsvl | Orange | 10941 | G | 3091 | Neversink | N |  | 4.73 | [13 empty] | NM | N | 22 ENPHASE M215 60-2LL-S22 | 2015-04-22 | 2015-05-01 | 7 | 2015-05-01 | [14 empty] | 2015-06-29 | 2015-07-07 |  | Y
Central Hudson |  | SolarCity | CH-05311 | Newburgh | Modena | Ulster | 12548 | G | 5013 | Modena | N |  | 3 | [13 empty] | NM | N | ABB PVI-3.0 | 2015-05-04 | 2015-05-11 | 5 | 2015-05-11 | [14 empty] | 2015-07-09 | 2015-07-15 |  | Y
Central Hudson |  | SolarCity | CH-05586 | Catskill | Coxsackie |  | 12051 | G | 1076 | Coxsackie | TBD |  | 12 | [13 empty] | NM | N | 2 ABB PVI-6000-OUTD US | 2015-04-22 | 2015-05-01 | 7 | 2015-05-01 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | Solar Generation | CH-08202 | Newburgh | Gardiner | Ulster | 12525 | G | 5031 | Galeville | N |  | 5 | [13 empty] | NM | N | SMA SB 5000 | 2015-04-22 | 2015-04-29 | 5 | 2015-04-29 | [14 empty] | 2015-08-05 | 2015-08-12 |  | Y
Central Hudson |  | SunDog Solar | CH-09159 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7055 | Rhinebeck | N |  | 7.5 | [13 empty] | NM | N | 30 - ENPHASE ENERGY M250 | 2015-05-04 | 2015-05-08 | 4 | 2015-05-08 | [14 empty] | 2015-07-09 | 2015-07-16 |  | Y
Central Hudson |  | SolarCity | CH-06099 | Fishkill | Wappingrs Falls |  | 12590 | G | 8052 | North Chelsea | TBD |  | 18 | [13 empty] | NM | N | 3 - ABB PVI-6000-OUTD | 2015-04-23 | 2015-05-06 | 9 | 2015-05-06 | [17 empty] | W
Central Hudson |  | NRG Home Solar | CH-04106 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8092 | Fishkill Plains | N |  | 5.805 | [13 empty] | NM | N | 27 - ENPHASE ENERGY M-215 | 2015-04-24 | 2015-04-30 | 4 | 2015-04-30 | [14 empty] | 2015-10-08 | 2015-10-13 |  | Y
Central Hudson |  | NRG Home Solar | CH-04177 | Newburgh | Newburgh | Orange | 12550 | G | 4011 | West Balmville | N |  | 7.525 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (35) | 2015-04-24 | 2015-05-05 | 7 | 2015-05-05 | [14 empty] | 2015-11-18 | 2015-11-19 |  | Y
Central Hudson |  | NRG Home Solar | CH-04299 | Kingston | Saugerties | Ulster | 12477 | G | 2015 | Lincoln Park | N |  | 8.5 | [13 empty] | NM | N | 34 ENPHASE M-250-60-2LL-S22 | 2015-04-24 | 2015-05-01 | 5 | 2015-05-01 | [14 empty] | 2015-09-01 | 2015-09-09 |  | Y
Central Hudson |  | NRG Home Solar | CH-04374 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8091 | Fishkill Plains | N |  | 5.805 | [13 empty] | NM | N | 27 - ENPHASE ENERGY M-215 | 2015-04-24 | 2015-04-30 | 4 | 2015-04-30 | [14 empty] | 2015-10-08 | 2015-10-13 |  | Y
Central Hudson |  | NRG Home Solar | CH-04456 | Newburgh | Newburgh |  | 12550 | G | 5041 | East Walden | TBD |  | 14.5 | [13 empty] | NM | N | ENPHASE ENERGY M-250 (58) | 2015-04-24 | 2015-04-30 | 4 | 2015-04-30 | [8 empty] | 350 | 350 | [7 empty] | W |  | Customer already had net meter prior to application.Transformer upgrade required to accommodate PV installation. Utility System Upgrade Costs TBD.
Central Hudson |  | NRG Home Solar | CH-04750 | Newburgh | New Windsor | Orange | 12553 | G | 4094 | Bethlehem Rd | N |  | 8.6 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (40) | 2015-04-24 | 2015-04-30 | 4 | 2015-04-30 | [14 empty] | 2015-09-28 | 2015-10-05 |  | Y
Central Hudson |  | NRG Home Solar | CH-04829 | Fishkill | Beacon |  | 12508 | G | 8016 | Forgebrook | TBD |  | 4.3 | [13 empty] | NM | N | 20 - ENPHASE ENERGY M-215 | 2015-04-24 | 2015-04-30 | 4 | 2015-04-30 | [17 empty] | W
Central Hudson |  | Autonomous Energies LLC | CH-00750 | Kingston | Kingston | Ulster | 12401 | G | 1013 | Boulevard | N |  | 1.5 | [13 empty] | NM | N | 6 ENPHASE-250-M | 2015-04-24 | 2015-05-01 | 5 | 2015-05-01 | [14 empty] | 2015-07-23 | 2015-07-29 |  | Y
Central Hudson |  | Autonomous Energies LLC | CH-00751 | Kingston | Kingston | Ulster | 12401 | G | 1013 | Boulevard | N |  | 7 | [13 empty] | NM | N | SMA SB-7000-TL | 2015-04-24 | 2015-05-01 | 5 | 2015-05-01 | [14 empty] | 2015-10-01 | 2015-10-08 |  | Y
Central Hudson |  | Direct Energy Solar | CH-01056 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7051 | Rhinebeck | N |  | 5.59 | [13 empty] | NM | N | 26 - ENPHASE M215 | 2015-04-24 | 2015-04-30 | 4 | 2015-04-30 | [14 empty] | 2015-06-29 | 2015-07-06 |  | Y
Central Hudson |  | Sungevity Inc | CH-09313 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6044 | Spackenkill | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000-OUTD | 2015-04-24 | 2015-04-30 | 4 | 2015-04-30 | [14 empty] | 2015-06-10 | 2015-06-17 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03645 | Newburgh | Campbell Hall | Orange | 10916 | G | 5051 | Maybrook | N |  | 10 | [13 empty] | NM | N | SOLAREDGE SE10000 (1) | 2015-04-27 | 2015-05-04 | 5 | 2015-05-04 | [14 empty] | 2015-05-21 | 2015-06-04 |  | Y
Central Hudson |  | SolarCity | CH-06060 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8095 | Fishkill Plains | N |  | 7.8 | [13 empty] | NM | N | 1 ABB PVI-4.2-US 1 ABB PVI-3.8-US | 2015-04-27 | 2015-05-07 | 8 | 2015-05-07 | [14 empty] | 2015-06-29 | 2015-07-07 |  | Y
Central Hudson |  | SolarCity | CH-06222 | Newburgh | Newburgh | Orange | 12550 | G | 4024 | Coldenham | N |  | 3 | [13 empty] | NM | N | ABB PVI-3 | 2015-04-27 | 2015-05-01 | 4 | 2015-05-01 | [14 empty] | 2015-06-24 | 2015-06-24 |  | Y
Central Hudson |  | SolarCity | CH-06790 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8091 | Fishkill Plains | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000-OUTD US | 2015-04-27 | 2015-05-11 | 10 | 2015-05-11 | [14 empty] | 2015-05-26 | 2015-06-02 |  | Y
Central Hudson |  | SolarCity | CH-07854 | Kingston | Rosendale |  | 12472 | G | 3021 | High Falls | TBD |  | 3 | [13 empty] | NA | N | SOLAREDGE SE3000A-US | 2015-04-27 | 2015-04-27 | 0 | 2015-04-27 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | Direct Energy Solar | CH-00833 | Kingston | Cragsmoor | Ulster | 12420 | G | 3078 | Greenfield Rd | N |  | 7.74 | [13 empty] | NM | N | 36 ENPHASE M215 60-2LL-S22 | 2015-04-28 | 2015-05-05 | 5 | 2015-05-05 | [14 empty] | 2015-07-16 | 2015-07-22 |  | Y
Central Hudson |  | Hudson Solar | CH-02490 | Newburgh | Wallkill | Ulster | 12589 | G | 5041 | East Walden | N | CH-01981 | 5 | [13 empty] | NM | N | sunpower spr 5.0 | 2015-05-06 | 2015-05-06 | 0 | 2015-05-06 | [14 empty] | 2015-08-13 | 2015-08-20 |  | Y
Central Hudson |  | Paradise Energy Solutions LLC | CH-02835 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7061 | Milan | N |  | 14 | [13 empty] | NM | N | (2) SMA 7000-TL-US-22 | 2015-05-13 | 2015-05-20 | 5 | 2015-05-20 | [8 empty] | 350 | 350 |  |  |  |  | 2015-08-14 | 2015-08-21 |  | Y
Central Hudson |  | Sol Providers | CH-08909 | Poughkeepsie | Lagrangevl | Dutchess | 12540 | G | 6055 | Todd Hill | N |  | 18 | [13 empty] | NM | N | (3) SMA SB6000-US | 2015-08-21 | 2015-08-25 | 2 | 2015-08-25 | [14 empty] | 2015-08-25 | 2015-09-01 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Sol Providers | CH-08944 | Fishkill | Poughkeepsie | Dutchess | 12603 | G | 8022 | Knapps Corners | N |  | 10 | [13 empty] | NM | N | (1) SMA SB4000TL-US-22 (1) SMA SB6000TL-US-22 | 2015-07-02 | 2015-07-10 | 5 | 2015-07-10 | [14 empty] | 2015-07-22 | 2015-07-29 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Sol Providers | CH-08971 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 6051 | Todd Hill | N | CH-08925 | 4.73 | [13 empty] | NM | N | Enphase M215 (22) | 2015-07-02 | 2015-07-10 | 5 | 2015-07-10 | [14 empty] | 2015-08-06 | 2015-08-13 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Verengo Solar | CH-09895 | Kingston | Kingston | Ulster | 12401 | G | 2093 | Hurley Ave | N |  | 6.67 | [13 empty] | NM | N | 31 ENPHASE M215-60-2LL-S22-IG | 2015-04-28 | 2015-05-05 | 5 | 2015-05-05 | [14 empty] | 2015-08-04 | 2015-08-11 |  | Y
Central Hudson |  | NRG Home Solar | CH-04686 | Catskill | Catskill |  | 12414 | G | 2005 | North Catskill | TBD |  | 11.18 | [13 empty] | NM | N | 52 ENPHASE M215-60-2LL-S22-IG | 2015-04-29 | 2015-05-07 | 6 | 2015-05-07 | [8 empty] | 350 | 350 | [7 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | SolarCity | CH-05235 | Newburgh | Marlboro | Ulster | 12542 | G | 5003 | Marlboro | N |  | 7.2 | [13 empty] | NM | N | ABB PVI-3.6 (2) | 2015-04-29 | 2015-05-05 | 4 | 2015-05-05 | [14 empty] | 2015-06-09 | 2015-06-15 |  | Y
Central Hudson |  | SolarCity | CH-06718 | Poughkeepsie | Salt Pt | Dutchess | 12578 | G | 7012 | Hibernia | N |  | 8.4 | [13 empty] | NM | N | 2 - ABB PVI-4.2-OUTD | 2015-04-29 | 2015-05-06 | 5 | 2015-05-06 | [14 empty] | 2016-01-22 | 2016-01-28 |  | Y
Central Hudson |  | Sunrun Inc. | CH-08340 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6044 | Spackenkill | N | CH-08340 | 10 | [13 empty] | NM | N | 2 - SOLAREDGE SE5000 | 2015-04-29 | 2015-05-06 | 5 | 2015-05-06 | [14 empty] | 2015-06-01 | 2015-06-08 |  | Y
Central Hudson |  | Tesla | CH-05094 | Kingston | Kingston | Ulster | 12402 | G | 2017 | Lincoln Park | N |  | 1368 | [13 empty] | RNM | N | 57 Fronius USA Fronius Symo 24.0-3 480 (480V) | 2015-05-11 | 2015-06-02 | 15 | 2015-06-02 | 2015-05-11 | 2015-06-02 | 15 | 2015-08-12 | 2015-08-12 | 2015-11-05 | 60 | 18590 | 149000 | 229393.76 |  | 2016-05-24 | 2016-05-24 | 2018-02-09 | 2018-05-10 | 2018-05-11 | 2018-07-25 | Y |  | System failed verification testing on 3/27/2018 and 5/1/2018. Central Hudson worked with developer on solutions. 5/10/2018 - Successful verification test witnessed.
Central Hudson |  | SolarCity | CH-05315 | Newburgh | New Windsor | Orange | 12553 | G | 4093 | Bethlehem Rd | N |  | 5 | [13 empty] | NM | N | ABB PVI-5000 (1) | 2015-04-30 | 2015-05-07 | 5 | 2015-05-07 | [14 empty] | 2015-05-28 | 2015-06-04 |  | Y
Central Hudson |  | SolarCity | CH-05544 | Catskill | Earlton | Greene | 12058 | G | 1071 | Coxsackie | N |  | 10 | [13 empty] | NM | N | FRONIUS IG PLUS A 10.0 | 2015-04-30 | 2015-05-08 | 6 | 2015-05-08 | [8 empty] | 350 | 350 |  | 2015-06-30 | 2015-06-30 | 2015-07-08 | 2015-09-14 | 2015-09-21 |  | Y
Central Hudson |  | SolarCity | CH-07190 | Catskill | Coeymans Holw | Albany | 12046 | G | 1081 | New Baltimore | N |  | 13 | [13 empty] | NM | N | ABB PVI-3.0-OUTD-S-US (2) ABB PVI-5000-OUTD-S-US | 2015-04-30 | 2015-05-08 | 6 | 2015-05-08 | [8 empty] | 350 | 350 |  | 2015-06-30 | 2015-06-30 | 2015-07-08 | 2015-08-03 | 2015-08-03 |  | Y
Central Hudson |  | NRG Home Solar | CH-04208 | Fishkill | Beacon | Dutchess | 12508 | G | 8017 | Forgebrook | N |  | 4.73 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (22) | 2015-05-01 | 2015-05-13 | 8 | 2015-05-13 | [14 empty] | 2015-10-02 | 2015-10-08 |  | Y
Central Hudson |  | NRG Home Solar | CH-04610 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8014 | Forgebrook | N |  | 5.805 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (27) | 2015-05-01 | 2015-05-13 | 8 | 2015-05-13 | [14 empty] | 2015-08-27 | 2015-09-03 |  | Y
Central Hudson |  | NRG Home Solar | CH-04838 | Newburgh | Wallkill |  | 12589 | G | 5041 | East Walden | TBD |  | 7.095 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (33) | 2015-05-01 | 2015-05-08 | 5 | 2015-05-08 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | SolarCity | CH-06986 | Newburgh | Newburgh | Orange | 12550 | G | 4023 | Coldenham | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000 (1) | 2015-05-01 | 2015-05-08 | 5 | 2015-05-08 | [14 empty] | 2015-06-18 | 2015-06-25 |  | Y
Central Hudson |  | SolarCity | CH-07413 | Newburgh | New Paltz | Ulster | 12561 | G | 5022 | Ohioville | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE7600A-US | 2015-05-08 | 2015-05-14 | 4 | 2015-05-14 | [14 empty] | 2015-05-27 | 2015-06-03 |  | Y
Central Hudson |  | NRG Home Solar | CH-04536 | Kingston | Lk Katrine | Ulster | 12449 | G | 2016 | Lincoln Park | N |  | 5.59 | [13 empty] | NM | N | 26 ENPHASE M-215-60-2LL-S22-IG | 2015-05-04 | 2015-05-12 | 6 | 2015-05-12 | [14 empty] | 2015-08-27 | 2015-09-03 |  | Y
Central Hudson |  | SolarCity | CH-06299 | Newburgh | Newburgh | Orange | 12550 | G | 5041 | East Walden | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000 | 2015-05-04 | 2015-05-11 | 5 | 2015-05-11 | [14 empty] | 2015-06-02 | 2015-06-09 |  | Y
Central Hudson |  | Trinity Solar | CH-08378 | Newburgh | Newburgh | Orange | 12550 | G | 4011 | West Balmville | N |  | 10 | [13 empty] | NM | N | SUNNY BOY SMA SB 5000 (2) | 2015-06-09 | 2015-06-16 | 5 | 2015-06-16 | [14 empty] | 2015-07-31 | 2015-08-06 |  | Y
Central Hudson |  | Verengo Solar | CH-09814 | Fishkill | Beacon | Dutchess | 12508 | G | 8017 | Forgebrook | N |  | 13.76 | [13 empty] | NM | N | 64 - ENPHASE ENERGY M215 | 2015-05-04 | 2015-05-11 | 5 | 2015-05-11 | [14 empty] | 2015-06-19 | 2015-06-25 |  | Y
Central Hudson |  | Verengo Solar | CH-09928 | Newburgh | New Paltz |  | 12561 | G | 5024 | Ohioville | TBD |  | 6.235 | [13 empty] | NM | N | ENPHASE ENERGY M215 (29) | 2015-05-04 | 2015-05-11 | 5 | 2015-05-11 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | NRG Home Solar | CH-04346 | Poughkeepsie | Wappingrs Fls | Dutchess | 12590 | G | 6052 | Todd Hill | N |  | 5.805 | [13 empty] | NM | N | 27 - ENPHASE ENERGY M-215 | 2015-05-05 | 2015-05-13 | 6 | 2015-05-13 | [14 empty] | 2015-10-13 | 2015-10-20 |  | Y
Central Hudson |  | NRG Home Solar | CH-04395 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8092 | Fishkill Plains | N |  | 5.375 | [13 empty] | NM | N | 25 - ENPHASE ENERGY M-215 | 2015-05-05 | 2015-05-13 | 6 | 2015-05-13 | [14 empty] | 2015-10-22 | 2015-10-27 |  | Y
Central Hudson |  | NRG Home Solar | CH-04828 | Fishkill | Beacon |  | 12508 | G | 8015 | Forgebrook | TBD |  | 4.515 | [13 empty] | NM | N | 21 - ENPHASE ENERGY M-215 | 2015-05-05 | 2015-05-12 | 5 | 2015-05-12 | [17 empty] | W
Central Hudson |  | Direct Energy Solar | CH-00850 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 7011 | Hibernia | N |  | 7.74 | [13 empty] | NM | N | 36 - ENPHASE M215 | 2015-05-13 | 2015-05-20 | 5 | 2015-05-20 | [14 empty] | 2015-06-17 | 2015-06-24 |  | Y
Central Hudson |  | SolarCity | CH-06761 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7061 | Milan | N |  | 5 | [13 empty] | NM | N | ABB PVI-5000-OUTD-US | 2015-05-05 | 2015-05-12 | 5 | 2015-05-12 | [14 empty] | 2015-06-23 | 2015-06-30 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-03441 | Newburgh | Middletown | Orange | 10941 | G | 5051 | Maybrook | N |  | 6 | [13 empty] | NM | N | SMA AMERICA SB6000 (1) | 2015-05-06 | 2015-05-12 | 4 | 2015-05-12 | [14 empty] | 2015-08-03 | 2015-08-10 |  | Y
Central Hudson |  | SolarCity | CH-05073 | Newburgh | Newburgh | Orange | 12550 | G | 5004 | Marlboro | N |  | 6 | [13 empty] | NM | N | ABB PVI-3.0 (2) | 2015-05-06 | 2015-05-12 | 4 | 2015-05-12 | [14 empty] | 2015-05-26 | 2015-06-02 |  | Y
Central Hudson |  | SolarCity | CH-06409 | Newburgh | Middletown | Orange | 10941 | G | 5051 | Maybrook | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000 | 2015-05-06 | 2015-05-12 | 4 | 2015-05-12 | [14 empty] | 2015-05-14 | 2015-05-20 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07125 | Newburgh | New Windsor | Orange | 12553 | G | 4091 | Bethlehem Rd | N |  | 11.4 | [13 empty] | NM | N | SOLAREDGE SE11400A (1) | 2015-05-06 | 2015-05-12 | 4 | 2015-05-12 | [14 empty] | 2015-06-02 | 2015-06-09 |  | Y
Central Hudson |  | NRG Home Solar | CH-04227 | Kingston | Cementon |  | 12414 | G | 3002 | Saugerties | TBD |  | 8.25 | [13 empty] | NM | N | 33 ENPHASE M250-60-2LL-S22 | 2015-05-07 | 2015-05-14 | 5 | 2015-05-14 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | Kool-Temp | CH-02575 | Poughkeepsie | Staatsburg | Dutchess | 12580 | G | 7041 | Staatsburg | N |  | 6 | [13 empty] | NM | N | SUNNY BOY 6000 (1) | 2015-06-11 | 2015-06-16 | 3 | 2015-06-16 | [14 empty] | 2016-07-12 | 2016-07-18 |  | Y
Central Hudson |  | Pure Power Systems | CH-02946 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6001 | Reynolds Hill | N |  | 225 | [13 empty] | NM | N | SOLECTRIA SGI 225 | 2015-06-16 | 2015-07-08 | 15 | 2015-07-08 | 2015-06-16 | 2015-07-08 | 15 | [11 empty] | 2015-08-10 | 2015-08-13 |  | Y
Central Hudson |  | SolarCity | CH-05942 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6097 | Manchester | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000-OUTD | 2015-05-07 | 2015-05-13 | 4 | 2015-05-13 | [14 empty] | 2015-06-03 | 2015-06-10 |  | Y
Central Hudson |  | SolarCity | CH-06178 | Newburgh | New Paltz | Ulster | 12561 | G | 5023 | Ohioville | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A | 2015-05-07 | 2015-05-12 | 3 | 2015-05-12 | [14 empty] | 2015-09-21 | 2015-09-28 |  | Y
Central Hudson |  | SolarCity | CH-06678 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 7011 | Hibernia | N |  | 11 | [13 empty] | NM | N | (1) ABB PVI-5000-OUTD & (1) ABB PVI-6000-OUTD | 2015-05-07 | 2015-05-13 | 4 | 2015-05-13 | [14 empty] | 2015-06-01 | 2015-06-08 |  | Y
Central Hudson |  | SolarCity | CH-06699 | Poughkeepsie | Lagrangevl | Dutchess | 12540 | G | 6057 | Todd Hill | N |  | 16.4 | [13 empty] | NM | N | (1) SOLAREDGE SE11400A-US & (1) SOLAREDGE SE5000A-US | 2015-05-07 | 2015-05-20 | 9 | 2015-05-20 | [14 empty] | 2015-06-04 | 2015-06-12 |  | Y
Central Hudson |  | Sungevity Inc | CH-09561 | Kingston | Kerhonkson | Ulster | 12446 | G | 3082 | Kerhonkson | N |  | 6 | [13 empty] | NM | N | SMA AMERICA SB6000TL-US-22 | 2015-05-07 | 2015-05-14 | 5 | 2015-05-14 | [14 empty] | 2015-08-06 | 2015-08-13 |  | Y
Central Hudson |  | Verengo Solar | CH-09850 | Kingston | Ellenvl | Ulster | 12428 | G | 3078 | Greenfield Rd | N |  | 3.87 | [13 empty] | NM | N | 18 ENPHASE M215-60-S22-IG | 2015-05-07 | 2015-05-14 | 5 | 2015-05-14 | [14 empty] | 2015-06-19 | 2015-06-26 |  | Y
Central Hudson |  | New York State Solar Farm | CH-03926 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6008 | Reynolds Hill | N |  | 5 | [13 empty] | NM | N | ABB POWERONE PVI 5.0 | 2015-05-18 | 2015-05-27 | 6 | 2015-05-27 | [14 empty] | 2015-07-28 | 2015-08-04 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | NRG Home Solar | CH-04821 | Newburgh | Highland |  | 12528 | G | 5083 | Highland | TBD |  | 5.805 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (27) | 2015-05-08 | 2015-05-15 | 5 | 2015-05-15 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | NRG Home Solar | CH-04826 | Fishkill | Wappingrs Falls |  | 12590 | G | 8092 | Fishkill Plains | TBD |  | 3.66 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (17) | 2015-05-08 | 2015-05-15 | 5 | 2015-05-15 | [17 empty] | W
Central Hudson |  | ECNY Electric Inc. | CH-01092 | Newburgh | Newburgh | Orange | 12550 | G | 4051 | Union Ave | N |  | 325 | [13 empty] | NM | N | (13) Schneider Conext CL25000NA | 2015-06-18 | 2015-07-10 | 15 | 2015-07-10 | 2015-06-18 | 2015-07-10 | 15 | [11 empty] | 2015-12-04 | 2015-12-08 |  | Y
Central Hudson |  | SolarCity | CH-05063 | Newburgh | Newburgh | Orange | 12550 | G | 5041 | East Walden | N |  | 5 | [13 empty] | NM | N | ABB PVI-5000 | 2015-05-08 | 2015-05-14 | 4 | 2015-05-14 | [14 empty] | 2015-06-23 | 2015-06-30 |  | Y
Central Hudson |  | SolarCity | CH-05596 | Catskill | Ravena | Albany | 12143 | G | 1081 | New Baltimore | N |  | 9 | [13 empty] | NM | N | 1 ABB PVI-3.0-OUTD-S-US 1 ABB PVI-6000-OUTD-S-US | 2015-05-08 | 2015-05-15 | 5 | 2015-05-15 | [14 empty] | 2015-06-29 | 2015-07-06 |  | Y
Central Hudson |  | SolarCity | CH-07135 | Newburgh | Rock Tvrn | Orange | 12575 | G | 4097 | Bethlehem Rd | N |  | 11 | [13 empty] | NM | N | ABB PVI-5000 (1) ABB PVI-6000 (1) | 2015-05-08 | 2015-05-14 | 4 | 2015-05-14 | [14 empty] | 2015-07-23 | 2015-07-29 |  | Y
Central Hudson |  | SolarCity | CH-07572 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8092 | Fishkill Plains | N | CH-07572 | 10 | [13 empty] | NM | N | SOLAREDGE SE10000A | 2015-05-08 | 2015-05-15 | 5 | 2015-05-15 | [14 empty] | 2015-06-03 | 2015-06-11 |  | Y
Central Hudson |  | Solar Maximum LLC, dba RevoluSun | CH-09030 | Newburgh | Montgomery | Orange | 12549 | G | 5073 | Montgomery | N |  | 22.8 | [13 empty] | NM | N | SOLAREDGE 11400 (1) SOLAREDGE 11400 (1) | 2015-12-09 | 2015-12-14 | 3 | 2015-12-14 | [8 empty] | 350 | 350 |  | 2015-12-15 | 2015-12-15 | 2016-01-14 | 2016-01-20 | 2016-01-27 |  | Y
Central Hudson |  | Sungevity Inc | CH-09458 | Fishkill | Beacon | Dutchess | 12508 | G | 8017 | Forgebrook | N |  | 3.8 | [13 empty] | NM | N | SMA AMERICA SB3800 | 2015-05-08 | 2015-05-15 | 5 | 2015-05-15 | [14 empty] | 2015-07-01 | 2015-07-09 |  | Y
Central Hudson |  | Hudson Solar | CH-01639 | Catskill | New Baltimore | Greene | 12124 | G | 1083 | New Baltimore | N |  | 10 | [13 empty] | NM | N | 2 SMA AMERICA SB5000 TLUS22 | 2015-05-12 | 2015-05-18 | 4 | 2015-05-18 | [14 empty] | 2015-06-29 | 2015-07-06 |  | Y
Central Hudson |  | SolarCity | CH-05801 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6094 | Manchester | N |  | 3 | [13 empty] | NM | N | SOLAREDGE SE3000A | 2015-05-12 | 2015-05-19 | 5 | 2015-05-19 | [14 empty] | 2015-06-02 | 2015-06-09 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06201 | Newburgh | Walden | Orange | 12586 | G | 5042 | East Walden | N |  | 18 | [13 empty] | NM | N | ABB PVI-6000 (3) | 2015-05-12 | 2015-05-18 | 4 | 2015-05-18 | [8 empty] | 350 | 350 |  |  |  |  | 2015-07-30 | 2015-08-05 |  | Y
Central Hudson |  | SolarCity | CH-06817 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8044 | Myers Corners | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000 | 2015-05-12 | 2015-05-19 | 5 | 2015-05-19 | [14 empty] | 2015-06-23 | 2015-06-30 |  | Y
Central Hudson |  | SolarCity | CH-06903 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8072 | Shenandoah | N |  | 6.6 | [13 empty] | NM | N | ABB PVI-3.0 (1) ABB PVI-3.6 (1) | 2015-05-12 | 2015-05-19 | 5 | 2015-05-19 | [14 empty] | 2015-06-23 | 2015-06-30 |  | Y
Central Hudson |  | SolarCity | CH-07742 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8095 | Fishkill Plains | N |  | 3.6 | [13 empty] | NM | N | ABB PVI-3.6 | 2015-05-21 | 2015-05-29 | 5 | 2015-05-29 | [14 empty] | 2015-06-01 | 2015-06-08 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | New York State Solar Farm | CH-04058 | Kingston | W Hurley | Ulster | 12491 | G | 3013 | Woodstock | N | CH-04058 | 7.6 | [13 empty] | NM | N | SMA AMERICA SB 3.0 SMA AMERICA SB 3.8 | 2015-05-13 | 2015-05-18 | 3 | 2015-05-18 | [14 empty] | 2015-06-29 | 2015-07-07 |  | Y
Central Hudson |  | Direct Energy Solar | CH-01026 | Newburgh | Campbell Hall | Orange | 10916 | G | 5052 | Maybrook | N |  | 10.32 | [13 empty] | NM | N | ENPHASE M215 (48) | 2015-05-20 | 2015-05-29 | 6 | 2015-05-29 | [14 empty] | 2015-08-10 | 2015-08-17 |  | Y
Central Hudson |  | Tesla | CH-05103 | Poughkeepsie | Wappingrs Fls | Dutchess | 12590 | G | 6046 | Spackenkill | N |  | 1610.4 | [13 empty] | RNM | N | 44 Huawei Technologies SUN2000-33KTL-US (76) Fronius Symo 24.0-3 480 | 2015-07-31 | 2015-08-21 | 15 | 2015-08-21 | 2015-07-31 | 2015-08-21 | 15 | 2015-10-09 | 2015-11-05 | 2016-02-04 | 60 | 20896.27 | 236518.75 | 145798.35 |  | 2016-11-03 | 2016-11-03 | 2020-08-12 | 2020-08-31 | 2020-09-01 | 2020-11-25 | Y |  | 11/10/17 - Contractor has requested project to be placed "on hold". 4/17/18 - Customer requested project be taken off hold.
Central Hudson |  | SolarCity | CH-05788 | Poughkeepsie | Poughkeepsie |  | 12603 | G | 6044 | Spackenkill | TBD |  | 6 | [13 empty] | NM | N | ABB PVI-6000 | 2015-05-13 | 2015-05-20 | 5 | 2015-05-20 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | SolarCity | CH-05926 | Poughkeepsie | Wappingrs Fls | Dutchess | 12590 | G | 6052 | Todd Hill | N |  | 16 | [13 empty] | NM | N | ABB PVI-6000 (1) ABB PVI-5000 (2) | 2015-05-13 | 2015-05-20 | 5 | 2015-05-20 | [14 empty] | 2015-06-22 | 2015-06-29 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07883 | Poughkeepsie | Poughkeepsie |  | 12603 | G | 6093 | Manchester | TBD |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A | 2015-05-22 | 2015-06-01 | 5 | 2015-06-01 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | Trinity Solar | CH-08523 | Newburgh | New Windsor | Orange | 12553 | G | 4094 | Bethlehem Rd | N |  | 11.4 | [13 empty] | NM | N | SOLAR EDGE SE11400A-US | 2015-05-20 | 2015-05-29 | 6 | 2015-05-29 | [14 empty] | 2015-09-25 | 2015-10-01 |  | Y
Central Hudson |  | Sungevity Inc | CH-09496 | Newburgh | Wallkill |  | 12589 | G | 5043 | East Walden | TBD |  | 7 | [13 empty] | NM | N | SMA AMERICA SB7000TL (1) | 2015-05-21 | 2015-06-01 | 6 | 2015-06-01 | [17 empty] | W
Central Hudson |  | NRG Home Solar | CH-04626 | Fishkill | Garrison | Putnam | 10524 | G | 8086 | Tioronda | N |  | 3.87 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (18) | 2015-06-18 | 2015-06-25 | 5 | 2015-06-25 | [14 empty] | 2015-10-16 | 2015-10-22 |  | Y
Central Hudson |  | SolarCity | CH-05104 | Catskill | Cairo | Greene | 12413 | G | 2041 | South Cairo | N |  | 1584 | [13 empty] | RNM | N | 66 Fronius USA Fronius Symo 24.0-3 480 (480V) (66) Fronius Symo 24.0-3 | 2015-08-11 | 2015-09-01 | 15 | 2015-09-01 | 2015-08-11 | 2015-09-01 | 15 | 2015-11-24 | 2015-11-24 | 2016-02-24 | 60 | 15286.07 | 200000 | 280951.88 |  | 2016-05-04 | 2016-05-04 | 2017-01-31 | 2018-02-27 | 2018-02-27 | 2018-05-25 | Y |  | System failed verification testing on 1/31/2017. Central Hudson worked with developer on solutions. System passed verification testing on 12/21/2017. Final interconnection approval was granted once developer provided proof of signage at the meter and AC disconnect, as well as 24/7 access to AC disconnect.
Central Hudson |  | SolarCity | CH-06106 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8056 | North Chelsea | N |  | 11.4 | [13 empty] | NM | N | SOLAR EDGE SE11400A | 2015-05-14 | 2015-05-21 | 5 | 2015-05-21 | [14 empty] | 2015-07-23 | 2015-07-29 |  | Y
Central Hudson |  | SolarCity | CH-06871 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8094 | Fishkill Plains | N |  | 5 | [13 empty] | NM | N | ABB PVI-5000 (1) | 2015-07-14 | 2015-07-20 | 4 | 2015-07-20 | [14 empty] | 2015-08-21 | 2015-08-26 |  | Y
Central Hudson |  | Trinity Solar | CH-08366 | Poughkeepsie | Millbrook | Dutchess | 12545 | G | 7025 | Tinkertown | N | CH-08366 | 7.6 | [13 empty] | NM | N | SOLAR EDGE SE 76000A | 2015-05-28 | 2015-06-04 | 5 | 2015-06-04 | [14 empty] | 2015-10-22 | 2015-10-29 |  | Y
Central Hudson |  | Trinity Solar | CH-08390 | Catskill | Surprise | Greene | 12176 | G | 2061 | Freehold | N |  | 5 | [13 empty] | NM | N | SOLAR EDGE SE 5000A-US | 2015-05-14 | 2015-05-18 | 2 | 2015-05-18 | [14 empty] | 2015-08-14 | 2015-08-21 |  | Y
Central Hudson |  | Trinity Solar | CH-08592 | Catskill | Jewett |  | 12444 | E | 2081 | Hunter | TBD |  | 6 | [13 empty] | NM | N | SOLAR EDGE SE 6000A | 2015-05-21 | 2015-06-01 | 6 | 2015-06-01 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | NRG Home Solar | CH-04154 | Poughkeepsie | Red Hook |  | 12571 | G | 7051 | Rhinebeck | TBD |  | 9.46 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (44) | 2015-05-15 | 2015-05-22 | 5 | 2015-05-22 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | SolarCity | CH-06491 | Kingston | Kingston | Ulster | 12401 | G | 2094 | Hurley Ave | N |  | 3 | [13 empty] | NM | N | ABB PVI-3.0 | 2015-05-15 | 2015-05-22 | 5 | 2015-05-22 | [14 empty] | 2015-06-30 | 2015-07-08 |  | Y
Central Hudson |  | Solar Energy Systems LLC | CH-09013 | Poughkeepsie | Clinton Corners | Dutchess | 12514 | G | 7012 | Hibernia | N |  | 24 | [13 empty] | NM | N | (4) SMA SB6000 | 2015-05-26 | 2015-06-09 | 10 | 2015-06-09 | [14 empty] | 2015-08-03 | 2015-08-13 |  | Y
Central Hudson |  | Solar Maximum LLC, dba RevoluSun | CH-09029 | Newburgh | Montgomery | Orange | 12549 | G | 5073 | Montgomery | N |  | 6 | [13 empty] | NM | N | (1) SMA AMERICA SB6000 | 2015-05-22 | 2015-06-01 | 5 | 2015-06-01 | [14 empty] | 2015-06-30 | 2015-06-30 |  | Y
Central Hudson |  | Sungevity Inc | CH-09597 | Kingston | Saugerties | Ulster | 12477 | G | 3003 | Saugerties | N |  | 4.2 | [13 empty] | NM | N | ABB PVI-4.2 | 2015-05-15 | 2015-05-22 | 5 | 2015-05-22 | [14 empty] | 2015-07-10 | 2015-07-17 |  | Y
Central Hudson |  | New York State Solar Farm | CH-03943 | Newburgh | Highland | Ulster | 12528 | G | 5083 | Highland | N |  | 9.8 | [13 empty] | NM | N | SMA AMERICA SB 6.0 (1) SMA AMERICA SB 3.8 (1) | 2015-05-18 | 2015-05-27 | 6 | 2015-05-27 | [14 empty] | 2015-07-16 | 2015-07-21 |  | Y
Central Hudson |  | New York State Solar Farm | CH-03950 | Newburgh | Marlboro | Ulster | 12542 | G | 5001 | Marlboro | N |  | 13.6 | [13 empty] | NM | N | SMA AMERICA SB 3.8 (2) SMA AMERICA SB 6.0 (1) | 2015-05-18 | 2015-05-27 | 6 | 2015-05-27 | [8 empty] | 350 | 350 |  |  |  |  | 2015-07-21 | 2015-07-22 |  | Y
Central Hudson |  | NRG Home Solar | CH-04248 | Catskill | Athens | Greene | 12015 | G | 2002 | North Catskill | N |  | 10.32 | [13 empty] | NM | N | ENPHASE M215 (48) | 2015-05-18 | 2015-05-26 | 5 | 2015-05-26 | [14 empty] | 2015-08-28 | 2015-09-04 |  | Y
Central Hudson |  | NRG Home Solar | CH-04397 | Fishkill | Wappingrs Falls |  | 12590 | G | 8092 | Fishkill Plains | TBD |  | 5.805 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (27) | 2015-05-19 | 2015-05-26 | 4 | 2015-05-26 | [17 empty] | W
Central Hudson |  | NRG Home Solar | CH-04663 | Newburgh | Wallkill | Ulster | 12589 | G | 5043 | East Walden | N |  | 6.235 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (29) | 2015-05-19 | 2015-05-26 | 4 | 2015-05-26 | [14 empty] | 2015-10-13 | 2015-10-15 |  | Y
Central Hudson |  | BQ Energy, LLC | CH-00754 | Poughkeepsie | Millerton |  | 12546 | G | 7081 | Millerton | TBD |  | 1995.2 | [13 empty] | RNM | N | (86) Advanced Energy AE-3TL23 | 2015-06-03 | 2015-06-19 | 12 | 2015-06-19 | 2015-06-03 | 2015-06-19 | 12 |  |  |  |  | 22000 | [9 empty] | W |  | Customer already had net meter prior to application. 5/25/15 Company Holiday. CESIR determined necessary during preliminary review Section C, Step 4.
Central Hudson |  | Direct Energy Solar | CH-01011 | Fishkill | Poughkeepsie |  | 12601 | G | 8024 | Knapps Corners | N |  | 6.665 | [13 empty] | NM | N | ENPHASE M215 (31) | 2015-05-19 | 2015-05-26 | 4 | 2015-05-26 | [17 empty] | W
Central Hudson |  | SolarCity | CH-05115 | Newburgh | Maybrook | Orange | 12543 | G | 5052 | Maybrook | N |  | 10 | [13 empty] | NM | N | ABB PVI-5000 (2) | 2015-05-19 | 2015-05-26 | 4 | 2015-05-26 | [14 empty] | 2015-06-23 | 2015-06-30 |  | Y
Central Hudson |  | SolarCity | CH-05360 | Newburgh | Marlboro | Ulster | 12542 | G | 5003 | Marlboro | N |  | 7.2 | [13 empty] | NM | N | ABB PVI-4.2 (1) ABB PVI-3.0 (1) | 2015-05-19 | 2015-05-26 | 4 | 2015-05-26 | [14 empty] | 2015-06-09 | 2015-06-09 |  | Y
Central Hudson |  | SolarCity | CH-06337 | Newburgh | Marlboro | Ulster | 12542 | G | 5003 | Marlboro | N |  | 12 | [13 empty] | NM | N | ABB PVI-6000 (2) | 2015-05-19 | 2015-05-26 | 4 | 2015-05-26 | [14 empty] | 2015-06-03 | 2015-06-11 |  | Y
Central Hudson |  | SolarCity | CH-06389 | Newburgh | New Windsor | Orange | 12553 | G | 4095 | Bethlehem Rd | N |  | 5 | [13 empty] | NM | N | ABB PVI-5000 | 2015-05-19 | 2015-05-26 | 4 | 2015-05-26 | [14 empty] | 2015-06-23 | 2015-06-30 |  | Y
Central Hudson |  | SolarCity | CH-07499 | Kingston | Kingston | Ulster | 12401 | G | 3021 | High Falls | N |  | 5 | [13 empty] | NM | N | ABB PVI-5000 | 2015-05-19 | 2015-05-28 | 6 | 2015-05-28 | [14 empty] | 2015-07-29 | 2015-08-05 |  | Y
Central Hudson |  | SolarCity | CH-07802 | Catskill | Coxsackie | Greene | 12051 | G | 1076 | Coxsackie | N | CH-05585 | 6 | [13 empty] | NM | N | ABB PVI-6000 (1) | 2015-05-19 | 2015-06-03 | 10 | 2015-06-03 | [14 empty] | 2015-07-07 | 2015-07-14 |  | Y
Central Hudson |  | SolarCity | CH-04961 | Catskill | Athens | Greene | 12015 | G | 2002 | North Catskill | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000 | 2015-05-20 | 2015-05-29 | 6 | 2015-05-29 | [14 empty] | 2015-06-12 | 2015-06-15 |  | Y
Central Hudson |  | SolarCity | CH-06085 | Fishkill | Fishkill |  | 12524 | G | 8065 | Merritt Park | TBD |  | 12 | [13 empty] | NM | N | (2) ABB PVI-6000-OUTD | 2015-05-20 | 2015-05-28 | 5 | 2015-05-28 | [17 empty] | W |  | 5/25/15 Company Holiday.
Central Hudson |  | SolarCity | CH-06486 | Kingston | Tillson | Ulster | 12486 | G | 3022 | High Falls | N |  | 6 | [13 empty] | NM | N | ABB PVI-3.0 (2) | 2015-05-20 | 2015-05-29 | 6 | 2015-05-29 | [14 empty] | 2015-06-29 | 2015-07-07 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03566 | Kingston | Kingston | Ulster | 12401 | G | 3021 | High Falls | N |  | 30 | [13 empty] | NM | N | SOLAREDGE 10000 (3) | 2015-06-01 | 2015-06-15 | 10 | 2015-06-15 | [14 empty] | 2015-08-12 | 2015-08-20 |  | Y
Central Hudson |  | NRG Home Solar | CH-04679 | Newburgh | Rock Tvrn | Orange | 12575 | G | 4097 | Bethlehem Rd | N |  | 5.805 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (27) | 2015-05-21 | 2015-06-01 | 6 | 2015-06-01 | [14 empty] | 2015-10-13 | 2015-10-15 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00951 | Newburgh | Highland | Ulster | 12528 | G | 5084 | Highland | N |  | 5.805 | [13 empty] | NM | N | (27) ENPHASE M215 | 2015-05-21 | 2015-06-05 | 10 | 2015-06-05 | [14 empty] | 2015-06-23 | 2015-06-30 |  | Y
Central Hudson |  | SolarCity | CH-05137 | Newburgh | Montgomery | Orange | 12549 | G | 5054 | Maybrook | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000 | 2015-05-21 | 2015-06-01 | 6 | 2015-06-01 | [14 empty] | 2015-06-23 | 2015-06-30 |  | Y
Central Hudson |  | SolarCity | CH-05673 | Newburgh | Ulster Pk | Ulster | 12487 | G | 5084 | Highland | N |  | 3 | [13 empty] | NM | N | ABB PVI-3.0 | 2015-05-21 | 2015-06-01 | 6 | 2015-06-01 | [14 empty] | 2015-06-05 | 2015-06-12 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Solar Generation | CH-08290 | Kingston | Woodstock | Ulster | 12498 | G | 3014 | Woodstock | N |  | 12.7 | [13 empty] | NM | N | SMA SB 7700 (1) SMA SB 5000 (1) | 2015-06-01 | 2015-06-15 | 10 | 2015-06-15 | [14 empty] | 2015-08-05 | 2015-08-12 |  | Y
Central Hudson |  | Sungevity Inc | CH-09395 | Catskill | Catskill | Greene | 12414 | G | 2006 | North Catskill | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE 7600A (1) | 2015-05-21 | 2015-06-01 | 6 | 2015-06-01 | [14 empty] | 2015-07-06 | 2015-07-10 |  | Y
Central Hudson |  | Solar Maximum LLC, dba RevoluSun | CH-09027 | Newburgh | Newburgh | Orange | 12550 | G | 5004 | Marlboro | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A (1) | 2015-05-22 | 2015-06-03 | 7 | 2015-06-03 | [14 empty] | 2015-06-25 | 2015-07-02 |  | Y
Central Hudson |  | New York State Solar Farm | CH-03968 | Kingston | High Fls | Ulster | 12440 | G | 3022 | High Falls | N |  | 9.8 | [13 empty] | NM | N | SMA SB 6.0 SMA SB 3.8 | 2015-05-26 | 2015-06-04 | 7 | 2015-06-04 | [14 empty] | 2015-06-29 | 2015-07-07 |  | Y
Central Hudson |  | NRG Home Solar | CH-04765 | Poughkeepsie | Staatsburg |  | 12580 | G | 7011 | Hibernia | TBD |  | 8.6 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (40) | 2015-05-26 | 2015-06-09 | 10 | 2015-06-09 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | Freedom Solar, LLC | CH-01128 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8052 | North Chelsea | N |  | 11.4 | [13 empty] | NM | N | SOLAREDGE SE11400 | 2015-06-03 | 2015-06-12 | 7 | 2015-06-12 | [14 empty] | 2015-07-31 | 2015-07-31 |  | Y
Central Hudson |  | SolarCity | CH-06646 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6046 | Spackenkill | N |  | 5 | [13 empty] | NM | N | ABB PVI-5000 | 2015-05-26 | 2015-06-02 | 5 | 2015-06-02 | [14 empty] | 2015-06-23 | 2015-06-30 |  | Y
Central Hudson |  | SolarCity | CH-06700 | Poughkeepsie | Lagrangevl | Dutchess | 12540 | G | 6057 | Todd Hill | N |  | 9 | [13 empty] | NM | N | ABB PVI-6000 (1) ABB PVI-3.0 (1) | 2015-05-26 | 2015-06-03 | 6 | 2015-06-03 | [14 empty] | 2015-06-29 | 2015-07-06 |  | Y
Central Hudson |  | SolarCity | CH-07322 | Poughkeepsie | Millerton | Dutchess | 12546 | G | 7081 | Millerton | N |  | 7.8 | [13 empty] | NM | N | ABB PVI-3.6 (1) ABB PVI-4.2 (1) | 2015-06-03 | 2015-06-11 | 6 | 2015-06-11 | [14 empty] | 2015-08-26 | 2015-09-02 |  | Y
Central Hudson |  | Sea Bright Solar LLC | CH-08855 | Newburgh | New Windsor | Orange | 12553 | G | 4091 | Bethlehem Rd | N | CH-08855 | 57.75 | [13 empty] | NM | N | (231) ENPHASE M250 | 2015-08-10 | 2015-08-31 | 15 | 2015-08-31 | 2015-08-10 | 2015-08-31 | 15 | [11 empty] | 2015-09-29 | 2015-10-02 |  | Y
Central Hudson |  | Sungevity Inc | CH-09461 | Fishkill | Beacon | Dutchess | 12508 | G | 8087 | Tioronda | N |  | 3 | [13 empty] | NM | N | ABB PVI-3.0 | 2015-05-26 | 2015-06-09 | 10 | 2015-06-09 | [14 empty] | 2015-08-18 | 2015-08-25 |  | Y
Central Hudson |  | NRG Home Solar | CH-04392 | Fishkill | Hopewell Jct |  | 12533 | G | 8096 | Fishkill Plains | TBD |  | 6.235 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (29) | 2015-05-27 | 2015-06-04 | 6 | 2015-06-04 | [17 empty] | W
Central Hudson |  | NRG Home Solar | CH-04602 | Fishkill | Fishkill | Dutchess | 12524 | G | 8094 | Fishkill Plains | N |  | 4.085 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (19) | 2015-05-27 | 2015-06-04 | 6 | 2015-06-04 | [14 empty] | 2015-10-22 | 2015-10-27 |  | Y
Central Hudson |  | SolarCity | CH-05448 | Newburgh | Highland | Ulster | 12528 | G | 5083 | Highland | N |  | 7.2 | [13 empty] | NM | N | ABB PVI-4.2 (1) ABB PVI-3 (1) | 2015-06-08 | 2015-06-15 | 5 | 2015-06-15 | [14 empty] | 2015-06-24 | 2015-07-01 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06224 | Newburgh | Newburgh | Orange | 12550 | G | 4024 | Coldenham | N |  | 5 | [13 empty] | NM | N | ABB PVI-5000 (1) | 2015-05-27 | 2015-06-03 | 5 | 2015-06-03 | [14 empty] | 2015-06-29 | 2015-07-07 |  | Y
Central Hudson |  | SolarCity | CH-06288 | Newburgh | Wallkill | Ulster | 12589 | G | 5012 | Modena | N |  | 4.2 | [13 empty] | NM | N | ABB PVI-4.2 | 2015-05-27 | 2015-06-03 | 5 | 2015-06-03 | [14 empty] | 2015-07-23 | 2015-07-29 |  | Y
Central Hudson |  | SolarCity | CH-06407 | Newburgh | Campbell Hall | Orange | 10916 | G | 5052 | Maybrook | N |  | 13 | [13 empty] | NM | N | ABB PVI-5000 (2) ABB PVI-3.0 (1) | 2015-05-27 | 2015-06-03 | 5 | 2015-06-03 | [14 empty] | 2015-11-18 | 2015-12-31 |  | Y
Central Hudson |  | SolarCity | CH-07183 | Catskill | Hunter | Greene | 12442 | E | 2389 | Vinegar Hill | N |  | 3 | [13 empty] | NM | N | ABB PVI-3.0-OUTD-S US | 2015-05-27 | 2015-06-04 | 6 | 2015-06-04 | [14 empty] | 2015-07-23 | 2015-07-30 |  | Y
Central Hudson |  | SolarCity | CH-07601 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 3 | [13 empty] | NM | N | ABB PVI-3.0 | 2015-05-27 | 2015-06-03 | 5 | 2015-06-03 | [14 empty] | 2015-07-23 | 2015-07-29 |  | Y
Central Hudson |  | Sunrun Inc. | CH-08328 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7054 | Rhinebeck | N |  | 7.2 | [13 empty] | NM | N | POWER ONE PVI-4.2 (1) POWER ONE PVI-3.0 (1) | 2015-05-27 | 2015-06-04 | 6 | 2015-06-04 | [14 empty] | 2015-06-24 | 2015-07-01 |  | Y
Central Hudson |  | Sungevity Inc | CH-09285 | Kingston | Connelly | Ulster | 12417 | G | 1024 | East Kingston | N |  | 5 | [13 empty] | NM | N | SMA AMERICA SB5000TL-US-22 | 2015-05-27 | 2015-06-04 | 6 | 2015-06-04 | [14 empty] | 2015-07-09 | 2015-07-16 |  | Y
Central Hudson |  | Sunrise Solar Solutions, LLC | CH-09646 | Fishkill | Hopewell Jct |  | 12533 | G | 8091 | Fishkill Plains | TBD |  | 165.12 | [13 empty] | NM | N | (688) Enphase C250 | 2015-07-22 | 2015-08-12 | 15 | 2015-08-12 | 2015-07-22 | 2015-08-12 | 15 | [14 empty] | W |  | Customer already had net meter prior to application. System determined eligible for fast track process during preliminary review Section C, Step 4. Upgrades required to accommodate PV installation.
Central Hudson |  | Sunrise Solar Solutions, LLC | CH-09649 | Fishkill | Hopewell Jct |  | 12533 | G | 8091 | Fishkill Plains | TBD |  | 165.12 | [13 empty] | NM | N | (688) Enphase C250 | 2015-07-24 | 2015-08-12 | 13 | 2015-08-12 | 2015-07-24 | 2015-08-12 | 13 | [14 empty] | W |  | Customer already had net meter prior to application. System determined eligible for fast track process during preliminary review Section C, Step 4. Upgrades required to accommodate PV installation.
Central Hudson |  | NRG Home Solar | CH-04588 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8052 | North Chelsea | N |  | 4 | [13 empty] | NM | N | ENPHASE ENERGY M-250 (16) | 2015-06-08 | 2015-06-15 | 5 | 2015-06-15 | [14 empty] | 2015-12-28 | 2016-01-05 |  | Y
Central Hudson |  | Gravity Renewables, Inc. | CH-01151 | Fishkill | Beacon | Dutchess | 12508 | G | 8013 | Forgebrook | N | [11 empty] | 927 |  |  |  | RNM | N | (3) WestingHouse VSW1 Lite Line D | 2016-06-23 | 2016-06-23 | 0 | 2016-06-23 | 2016-06-23 | 2016-06-23 | 0 | [11 empty] | 2016-07-01 | 2016-07-01 |  | Y
Central Hudson |  | SolarCity | CH-05140 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8093 | Fishkill Plains | N |  | 9.2 | [13 empty] | NM | N | ABB PVI-5000 (1) ABB PVI-4.2 (1) | 2015-05-28 | 2015-06-04 | 5 | 2015-06-04 | [14 empty] | 2015-07-23 | 2015-07-29 |  | Y
Central Hudson |  | SolarCity | CH-05322 | Kingston | Saugerties | Ulster | 12477 | G | 2015 | Lincoln Park | N |  | 15 | [13 empty] | NM | N | 2 ABB PVI-6000-OUTD US ABB PVI-3.0-OUTD-S | 2015-05-28 | 2015-06-04 | 5 | 2015-06-04 | [14 empty] | 2015-07-23 | 2015-07-29 |  | Y
Central Hudson |  | SolarCity | CH-05881 | Poughkeepsie | Poughquag | Dutchess | 12570 | G | 6055 | Todd Hill | N |  | 9 | [13 empty] | NM | N | ABB PVI-3.0 (1) ABB PVI-6000 (1) | 2015-05-28 | 2015-06-09 | 8 | 2015-06-09 | [14 empty] | 2015-06-29 | 2015-07-06 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06684 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 6073 | East Park | N |  | 5 | [13 empty] | NM | N | ABB PVI-5000 (1) | 2015-05-28 | 2015-06-04 | 5 | 2015-06-04 | [14 empty] | 2015-07-23 | 2015-07-29 |  | Y
Central Hudson |  | SolarCity | CH-07343 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8043 | Myers Corners | N |  | 3.6 | [13 empty] | NM | N | ABB PVI-3.6 | 2015-05-28 | 2015-06-04 | 5 | 2015-06-04 | [14 empty] | 2015-08-17 | 2015-08-24 |  | Y
Central Hudson |  | American Solar Partners | CH-03067 | Kingston | Olive Brdg | Ulster | 12461 | G | 3024 | High Falls | N |  | 3.8 | [13 empty] | NM | N | SE 3.8 (1) | 2015-05-29 | 2015-06-12 | 10 | 2015-06-12 | [14 empty] | 2016-01-20 | 2016-01-27 |  | Y
Central Hudson |  | Hudson Solar | CH-01282 | Kingston | High Fls | Ulster | 12440 | G | 3024 | High Falls | N | CH-01282 | 3.8 | [13 empty] | NM | N | SMA SB3800 TL-US-22 | 2015-05-29 | 2015-06-12 | 10 | 2015-06-12 | [14 empty] | 2015-09-18 | 2015-09-24 |  | Y
Central Hudson |  | Hudson Solar | CH-01350 | Newburgh | Newburgh | Orange | 12550 | G | 5001 | Marlboro | N |  | 10.8 | [13 empty] | NM | N | SMA AMERICA SB3800 (1) SMA AMERICA SB7000 (1) | 2015-05-29 | 2015-06-05 | 5 | 2015-06-05 | [14 empty] | 2015-09-09 | 2015-09-16 |  | Y
Central Hudson |  | Hudson Solar | CH-01491 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7061 | Milan | N | CH-01491 | 4 | [13 empty] | NM | N | SMA AMERICA SB4000 | 2015-06-05 | 2015-06-12 | 5 | 2015-06-12 | [14 empty] | 2015-07-13 | 2015-07-20 |  | Y
Central Hudson |  | Hudson Solar | CH-01589 | Newburgh | Montgomery | Orange | 12549 | G | 5054 | Maybrook | N | CH-01589 | 7.7 | [13 empty] | NM | N | SMA AMERICA SB7700 (1) | 2015-05-29 | 2015-06-09 | 7 | 2015-06-09 | [14 empty] | 2015-07-30 | 2015-08-05 |  | Y
Central Hudson |  | Hudson Solar | CH-01902 | Poughkeepsie | Stanfordvl |  | 12581 | G | 7072 | Stanfordville | TBD |  | 5 | [13 empty] | NM | N | SMA AMERICA SB5000 | 2015-05-29 | 2015-06-09 | 7 | 2015-06-09 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | Hudson Solar | CH-01918 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8045 | Myers Corners | N |  | 7 | [13 empty] | NM | N | SMA AMERICA SB7000 | 2015-05-29 | 2015-06-09 | 7 | 2015-06-09 | [14 empty] | 2015-08-14 | 2015-08-21 |  | Y
Central Hudson |  | Hudson Solar | CH-01958 | Newburgh | Walden | Orange | 12586 | G | 5041 | East Walden | N |  | 7 | [13 empty] | NM | N | SMA AMERICA SB7000 | 2015-05-29 | 2015-06-05 | 5 | 2015-06-05 | [14 empty] | 2015-09-14 | 2015-09-21 |  | Y
Central Hudson |  | Hudson Solar | CH-02116 | Poughkeepsie | Rhinebeck |  | 12572 | G | 7052 | Rhinebeck | TBD |  | 7 | [13 empty] | NM | N | SMA AMERICA SB7000 | 2015-05-29 | 2015-06-09 | 7 | 2015-06-09 | [17 empty] | W
Central Hudson |  | Hudson Solar | CH-02337 | Kingston | Saugerties | Ulster | 12477 | G | 3003 | Saugerties | N |  | 7.7 | [13 empty] | NM | N | SMA AMERICA SB7700 | 2015-05-29 | 2015-06-12 | 10 | 2015-06-12 | [14 empty] | 2015-09-03 | 2015-09-11 |  | Y
Central Hudson |  | Hudson Solar | CH-02406 | Fishkill | Beacon | Dutchess | 12508 | G | 8087 | Tioronda | N |  | 9 | [13 empty] | NM | N | SMA AMERICA SB3000 SMA AMERICA SB6000 | 2015-05-29 | 2015-06-05 | 5 | 2015-06-05 | [14 empty] | 2015-11-13 | 2015-11-13 |  | Y
Central Hudson |  | Hudson Solar | CH-02463 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7053 | Rhinebeck | N | CH-02126 | 3 | [13 empty] | NM | N | SMA AMERICA SB3000 | 2015-05-29 | 2015-06-05 | 5 | 2015-06-05 | [14 empty] | 2016-08-29 | 2016-08-29 |  | Y
Central Hudson |  | Hudson Solar | CH-02509 | Catskill | Coxsackie |  | 12051 | G | 1071 | Coxsackie | TBD |  | 3.8 | [13 empty] | NM | N | SMA AMERICA SB3800 | 2015-05-29 | 2015-06-12 | 10 | 2015-06-12 | [17 empty] | W
Central Hudson |  | SolarCity | CH-05460 | Newburgh | Campbell Hall | Orange | 10916 | G | 5052 | Maybrook | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000 (1) | 2015-05-29 | 2015-06-05 | 5 | 2015-06-05 | [14 empty] | 2015-08-28 | 2015-09-04 |  | Y
Central Hudson |  | SolarCity | CH-07812 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7053 | Rhinebeck | N | CH-05833 | 1 | [13 empty] | NM | N | 1 - ABB PVI-6000 (Replaced 5kW inverter with 6kW) | 2015-05-29 | 2015-06-05 | 5 | 2015-06-05 | [14 empty] | 2015-09-16 | 2015-09-23 |  | Y
Central Hudson |  | Trinity Solar | CH-08598 | Newburgh | Rock Tvrn |  | 12575 | G | 4097 | Bethlehem Rd | TBD |  | 3.8 | [13 empty] | NM | N | SOLAR EDGE SE 3.8 | 2015-05-29 | 2015-06-05 | 5 | 2015-06-05 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | Safari Energy, LLC | CH-08850 | Newburgh | New Windsor |  | 12533 | G | 4092 | Bethlehem Rd | TBD |  | 1988 | [13 empty] | RNM | N | (71) Solectria PVI 28TL | 2015-06-25 | 2015-07-17 | 15 | 2015-07-17 | 2015-06-25 | 2015-07-17 | 15 |  |  |  |  | 17000 | [9 empty] | W |  | 7/3/15 Company Holiday. CESIR determined necessary during preliminary review Section C, Step 4.
Central Hudson |  | Safari Energy, LLC | CH-08851 | Newburgh | New Windsor |  | 12533 | G | 4092 | Bethlehem Rd | TBD |  | 1988 | [13 empty] | RNM | N | (71) Solectria PVI 28TL | 2015-06-25 | 2015-07-17 | 15 | 2015-07-17 | 2015-06-25 | 2015-07-17 | 15 |  |  |  |  | 17000 | [9 empty] | W |  | 7/3/15 Company Holiday. CESIR determined necessary during preliminary review Section C, Step 4.
Central Hudson |  | Safari Energy, LLC | CH-08852 | Newburgh | New Windsor |  | 12533 | G | 4092 | Bethlehem Rd | TBD |  | 1988 | [13 empty] | RNM | N | (71) Solectria PVI 28TL | 2015-06-25 | 2015-07-17 | 15 | 2015-07-17 | 2015-06-25 | 2015-07-17 | 15 |  |  |  |  | 17000 | [9 empty] | W |  | 7/3/15 Company Holiday. CESIR determined necessary during preliminary review Section C, Step 4.
Central Hudson |  | Solar Power Financial | CH-09034 | Catskill | Medusa |  | 12120 | G | 1092 | Westerlo | TBD |  | 2000 | [13 empty] | RNM | N | (2) Advanced Energy AE 1000NX; SMART INVERTERS | 2015-06-23 | 2015-07-15 | 15 | 2015-07-15 | 2015-06-23 | 2015-07-15 | 15 |  |  |  |  | 22000 | [9 empty] | W |  | 7/3/15 Company Holiday. CESIR determined necessary during preliminary review Section C, Step 4. Received confirmation from customer on 5/2/16 to withdraw application.
Central Hudson |  | Solar Power Financial | CH-09035 | Catskill | Greenvl |  | 12083 | G | 2071 | Freehold | TBD |  | 2000 | [13 empty] | RNM | N | (2) Advanced Energy AE 1000NX SMART INVERTERS | 2015-06-23 | 2015-07-15 | 15 | 2015-07-15 | 2015-06-23 | 2015-07-15 | 15 |  |  |  |  | 22000 | [9 empty] | W |  | 7/3/15 Company Holiday. CESIR determined necessary during preliminary review Section C, Step 4. Received confirmation from customer on 5/2/16 to withdraw application.
Central Hudson |  | Solar Power Financial | CH-09036 | Catskill | Medusa |  | 12120 | G | 1092 | Westerlo | TBD |  | 1170 | [13 empty] | RNM | N | ABB Ultra-1100-TL-OUTD-1-US-690 | 2015-06-26 | 2015-07-20 | 15 | 2015-07-20 | 2015-06-26 | 2015-07-20 | 15 |  |  |  |  | 22000 | [9 empty] | W |  | 7/3/15 Company Holiday. CESIR determined necessary during preliminary review Section C, Step 4.
Central Hudson |  | Sungevity Inc | CH-09487 | Newburgh | Clintondale | Ulster | 12515 | G | 5012 | Modena | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000 | 2015-05-29 | 2015-06-05 | 5 | 2015-06-05 | [14 empty] | 2015-08-11 | 2015-08-18 |  | Y
Central Hudson |  | Kasselman Solar | CH-03512 | Catskill | Greenville |  | 12193 | G | 1092 | Westerlo | TBD |  | 7.5 | [13 empty] | NM | N | ENPHASE M250 (30) | 2015-06-01 | 2015-06-15 | 10 | 2015-06-15 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | New York State Solar Farm | CH-04014 | Newburgh | New Paltz | Ulster | 12561 | G | 5011 | Modena | N |  | 10 | [13 empty] | NM | N | ABB POWERONE PVI 5.0 (2) | 2015-06-01 | 2015-06-11 | 8 | 2015-06-11 | [14 empty] | 2015-08-04 | 2015-08-11 |  | Y
Central Hudson |  | Solar Liberty Energy Services | CH-04920 | Kingston | Wawarsing | Ulster | 12446 | G | 3071 | Honk Falls | N |  | 875 | [13 empty] | RNM | N | 35 Huawei Technologies SUN2000-25KTL-US | 2015-11-02 | 2015-11-23 | 15 | 2015-11-23 | 2015-11-23 | 2015-11-23 | 0 | 2016-03-18 | 2016-03-23 | 2016-06-17 | 60 | 27564 | 58000 | 58000 | 2016-12-05 | 2017-05-31 | 2017-05-31 | 2017-12-26 | 2018-01-19 | 2018-01-26 | 2018-06-07 | Y
Central Hudson |  | SolarCity | CH-05152 | Kingston | Saugerties | Ulster | 12477 | G | 3001 | Saugerties | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE7600A (1) | 2015-06-01 | 2015-06-15 | 10 | 2015-06-15 | [14 empty] | 2015-06-30 | 2015-07-08 |  | Y
Central Hudson |  | SolarCity | CH-05260 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7054 | Rhinebeck | N |  | 10 | [13 empty] | NM | N | FRONIUS IG PLUS A 10.0 (1) | 2015-06-01 | 2015-06-11 | 8 | 2015-06-11 | [14 empty] | 2016-01-27 | 2016-02-03 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06568 | Kingston | Saugerties | Ulster | 12477 | G | 3003 | Saugerties | N | CH-06568 | 7.6 | [13 empty] | NM | N | ABB PVI-5000 (1) ABB PVI-3000 (1) | 2015-06-01 | 2015-06-15 | 10 | 2015-06-15 | [14 empty] | 2015-06-29 | 2015-07-01 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06665 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6064 | Inwood Ave | N |  | 5 | [13 empty] | NM | N | ABB PVI-5000 (1) | 2015-06-01 | 2015-06-11 | 8 | 2015-06-11 | [14 empty] | 2015-09-02 | 2015-09-10 |  | Y
Central Hudson |  | SolarCity | CH-07550 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6092 | Manchester | N |  | 4.2 | [13 empty] | NM | N | ABB PVI-4.2 (1) | 2015-06-01 | 2015-06-11 | 8 | 2015-06-11 | [14 empty] | 2015-08-31 | 2015-09-08 |  | Y
Central Hudson |  | Sungevity Inc | CH-09564 | Kingston | Kingston | Ulster | 12401 | G | 1024 | East Kingston | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE 7600A (1) | 2015-06-01 | 2015-06-15 | 10 | 2015-06-15 | [14 empty] | 2015-08-11 | 2015-08-18 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03659 | Kingston | Kingston | Ulster | 12401 | G | 3021 | High Falls | N |  | 20 | [13 empty] | NM | N | SOLAREDGE 10000 (2) | 2015-06-02 | 2015-06-16 | 10 | 2015-06-16 | [14 empty] | 2015-08-04 | 2015-08-11 |  | Y
Central Hudson |  | Lotus Energy Inc. | CH-03868 | Poughkeepsie | Ancram | Columbia | 12502 | G | 7091 | Pulvers Corners | N |  | 6 | [13 empty] | NM | N | SMA SB 6000 (1) | 2015-06-02 | 2015-06-11 | 7 | 2015-06-11 | [14 empty] | 2015-09-10 | 2015-09-14 |  | Y
Central Hudson |  | NRG Home Solar | CH-04132 | Fishkill | Stormvl |  | 12582 | G | 8071 | Shenandoah | TBD |  | 5.16 | [13 empty] | NM | N | ENPHASE ENERGY M-215 (24) | 2015-06-02 | 2015-06-11 | 7 | 2015-06-11 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | NRG Home Solar | CH-04249 | Catskill | W Coxsackie | Greene | 12192 | G | 1076 | Coxsackie | N |  | 3.5 | [13 empty] | NM | N | 14 ENPHASE M-250-60-2LL-S22 | 2015-06-02 | 2015-06-16 | 10 | 2015-06-16 | [14 empty] | 2015-08-05 | 2015-08-12 |  | Y
Central Hudson |  | NRG Home Solar | CH-04702 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6073 | East Park | N |  | 6.665 | [13 empty] | NM | N | ENPHASE M-215 (31) | 2015-06-02 | 2015-06-11 | 7 | 2015-06-11 | [14 empty] | 2015-11-16 | 2015-11-23 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00956 | Newburgh | New Paltz | Ulster | 12561 | G | 5024 | Ohioville | N |  | 13.33 | [13 empty] | NM | N | ENPHASE M215 (62) | 2015-06-02 | 2015-06-11 | 7 | 2015-06-11 | [14 empty] | 2015-08-18 | 2015-08-25 |  | Y
Central Hudson |  | Paradise Energy Solutions LLC | CH-02847 | Kingston | High Fls | Ulster | 12440 | G | 3022 | High Falls | N |  | 10 | [13 empty] | NM | N | SOLAR EDGE 10000A-US | 2015-06-02 | 2015-06-16 | 10 | 2015-06-16 | [8 empty] | 350 | 350 |  | 2015-06-25 | 2015-06-25 | 2015-07-07 | 2015-08-25 | 2015-09-01 |  | Y
Central Hudson |  | SolarCity | CH-06526 | Kingston | Kingston |  | 12401 | G | 1022 | East Kingston | TBD |  | 6 | [13 empty] | NM | N | ABB PVI-6000-OUTD US | 2015-06-02 | 2015-06-16 | 10 | 2015-06-16 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | SolarCity | CH-07386 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8055 | North Chelsea | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000 | 2015-07-14 | 2015-07-20 | 4 | 2015-07-20 | [14 empty] | 2015-12-28 | 2016-01-05 |  | Y
Central Hudson |  | New York State Solar Farm | CH-03925 | Kingston | Saugerties | Ulster | 12477 | G | 3003 | Saugerties | N |  | 13 | [13 empty] | NM | N | 2 ABB POWERONE PVI 5.0 ABB POWERONE PVI 3.0 | 2015-06-03 | 2015-06-17 | 10 | 2015-06-17 | [14 empty] | 2015-07-24 | 2015-07-31 |  | Y
Central Hudson |  | Murphy Solar Power | CH-02729 | Catskill | Catskill | Greene | 12414 | G | 2006 | North Catskill | N |  | 7 | [13 empty] | NM | N | SMA SB7000-US | 2015-06-03 | 2015-06-17 | 10 | 2015-06-17 | [14 empty] | 2015-07-13 | 2015-07-20 |  | Y
Central Hudson |  | SolarCity | CH-05227 | Newburgh | Wallkill | Ulster | 12589 | G | 5041 | East Walden | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000 (1) | 2015-06-03 | 2015-06-11 | 6 | 2015-06-11 | [14 empty] | 2015-10-15 | 2015-10-22 |  | Y
Central Hudson |  | SolarCity | CH-05873 | Poughkeepsie | Millbrook | Dutchess | 12545 | G | 7012 | Hibernia | N |  | 3.6 | [13 empty] | NM | N | ABB PVI-3.6 | 2015-06-03 | 2015-06-11 | 6 | 2015-06-11 | [14 empty] | 2015-06-23 | 2015-06-30 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06909 | Fishkill | Hopewell Jct |  | 12533 | G | 8071 | Shenandoah | TBD |  | 8 | [13 empty] | NM | N | ABB PVI-5000 (1) ABB PVI-3.0 (1) | 2015-06-03 | 2015-06-11 | 6 | 2015-06-11 | [17 empty] | W |  | 6/25/15 - As per customer, cancelled solar install.
Central Hudson |  | Solar Generation | CH-08305 | Kingston | Glenford | Ulster | 12433 | G | 3013 | Woodstock | N | CH-08269 | 10 | [13 empty] | NM | N | 2 SMA SB 5000 TL | 2015-06-03 | 2015-06-17 | 10 | 2015-06-17 | [14 empty] | 2015-10-19 | 2015-10-26 |  | Y
Central Hudson |  | Lotus Energy Inc. | CH-03882 | Catskill | Greenvl | Greene | 12083 | G | 1091 | Westerlo | N |  | 13.7 | [13 empty] | NM | N | SMA SB6000 TL-US-22 SMA SB7700 TL-US-22 | 2015-06-04 | 2015-06-18 | 10 | 2015-06-18 | [14 empty] | 2015-09-24 | 2015-09-30 |  | Y
Central Hudson |  | Direct Energy Solar | CH-01029 | Kingston | Kingston | Ulster | 12401 | G | 2094 | Hurley Ave | N |  | 2.8 | [13 empty] | NM | N | 13 ENPHASE M215 60-2LL-S22 | 2015-06-04 | 2015-06-18 | 10 | 2015-06-18 | [14 empty] | 2015-09-08 | 2015-09-15 |  | Y
Central Hudson |  | Direct Energy Solar | CH-01074 | Kingston | Kingston | Ulster | 12401 | G | 2093 | Hurley Ave | N | CH-00900 | 0.43 | [13 empty] | NM | N | 2 ENPHASE 215 60-2LL-S22 | 2015-06-04 | 2015-06-18 | 10 | 2015-06-18 | [14 empty] | 2015-07-02 | 2015-07-10 |  | Y
Central Hudson |  | Direct Energy Solar | CH-01076 | Poughkeepsie | Rhinebeck | Dutchess | 12574 | G | 7055 | Rhinebeck | N | CH-00648 | 6.02 | [13 empty] | NM | N | ENPHASE M215 (28) | 2015-06-04 | 2015-06-12 | 6 | 2015-06-12 | [8 empty] | 350 | 350 |  |  |  |  | 2015-11-16 | 2015-11-23 |  | Y
Central Hudson |  | SolarCity | CH-05005 | Kingston | Saugerties | Ulster | 12477 | G | 3002 | Saugerties | N |  | 5 | [13 empty] | RNM | N | ABB PVI-5000-OUTD US | 2015-06-04 | 2015-06-18 | 10 | 2015-06-18 | [14 empty] | 2015-06-29 | 2015-07-07 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-05429 | Newburgh | Milton | Ulster | 12547 | G | 5003 | Marlboro | N |  | 7.2 | [13 empty] | NM | N | ABB PVI-3.6 (2) | 2015-07-30 | 2015-07-31 | 1 | 2015-07-31 | [14 empty] | 2015-08-04 | 2015-08-11 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07150 | Newburgh | Maybrook | Orange | 12543 | G | 4026 | Coldenham | N |  | 3.6 | [13 empty] | NM | N | ABB PVI-3.6 | 2015-06-04 | 2015-06-12 | 6 | 2015-06-12 | [14 empty] | 2015-07-23 | 2015-07-29 |  | Y
Central Hudson |  | SolarCity | CH-05777 | Kingston | Saugerties | Ulster | 12477 | G | 3001 | Saugerties | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000-OUTD-US | 2015-06-05 | 2015-06-19 | 10 | 2015-06-19 | [14 empty] | 2015-06-25 | 2015-07-02 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06357 | Newburgh | Modena | Ulster | 12548 | G | 5013 | Modena | N |  | 7.2 | [13 empty] | NM | N | ABB PVI-3.6 (2) | 2015-06-05 | 2015-06-12 | 5 | 2015-06-12 | [14 empty] | 2015-07-31 | 2015-08-06 |  | Y
Central Hudson |  | SolarCity | CH-06973 | Newburgh | Newburgh | Orange | 12550 | G | 4011 | West Balmville | N |  | 7.8 | [13 empty] | NM | N | ABB PVI-4.2 | 2015-06-05 | 2015-06-18 | 9 | 2015-06-18 | [14 empty] | 2015-09-29 | 2015-10-06 |  | Y
Central Hudson |  | SolarCity | CH-06988 | Newburgh | Newburgh | Orange | 12550 | G | 4027 | Coldenham | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A (1) | 2015-06-05 | 2015-06-18 | 9 | 2015-06-18 | [14 empty] | 2015-06-29 | 2015-07-07 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00974 | Newburgh | Campbell Hall | Orange | 10916 | G | 5052 | Maybrook | N |  | 10.32 | [13 empty] | NM | N | ENPHASE M215 (48) | 2015-06-08 | 2015-06-15 | 5 | 2015-06-15 | [14 empty] | 2015-08-03 | 2015-08-04 |  | Y
Central Hudson |  | SolarCity | CH-06704 | Poughkeepsie | Lagrangevl | Dutchess | 12540 | G | 6053 | Todd Hill | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000-OUTD-US | 2015-06-08 | 2015-06-15 | 5 | 2015-06-15 | [14 empty] | 2015-06-29 | 2015-07-06 |  | Y
Central Hudson |  | SolarCity | CH-07660 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8046 | Myers Corners | N |  | 7.5 | [13 empty] | NM | N | FRONIUS IG PLUS A 7.5 | 2015-06-08 | 2015-06-15 | 5 | 2015-06-15 | [14 empty] | 2015-08-17 | 2015-08-24 |  | Y
Central Hudson |  | Solar Generation | CH-08069 | Kingston | Kerhonkson | Ulster | 12446 | G | 3082 | Kerhonkson | N |  | 10 | [13 empty] | NM | N | 2 SMA SB 4000 TL | 2015-06-08 | 2015-06-22 | 10 | 2015-06-22 | [14 empty] | 2015-07-06 | 2015-07-10 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Lotus Energy Inc. | CH-03855 | Catskill | East Durham | Greene | 12423 | G | 2071 | Freehold | N |  | 7.7 | [13 empty] | NM | N | SMA SB7700 TL-US-22 | 2015-06-09 | 2015-06-23 | 10 | 2015-06-23 | [14 empty] | 2015-07-31 | 2015-08-07 |  | Y |  | Customer already had net meter prior to application.
Central Hudson |  | NRG Home Solar | CH-04617 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8072 | Shenandoah | N |  | 5.805 | [13 empty] | NM | N | (27) ENPHASE ENERGY M-215 | 2015-06-09 | 2015-06-16 | 5 | 2015-06-16 | [14 empty] | 2015-10-12 | 2015-10-15 |  | Y
Central Hudson |  | NRG Home Solar | CH-04764 | Poughkeepsie | Hyde Pk |  | 12538 | G | 6075 | East Park | TBD |  | 6.45 | [13 empty] | NM | N | (30) Enphase Energy M215 | 2015-07-01 | 2015-07-09 | 5 | 2015-07-09 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | Autonomous Energies LLC | CH-00742 | Poughkeepsie | Millerton | Dutchess | 12546 | G | 7081 | Millerton | N |  | 6.25 | [13 empty] | NM | N | (25) ENPHASE M-250 | 2015-06-16 | 2015-06-16 | 0 | 2015-06-16 | [14 empty] | 2015-06-26 | 2015-07-02 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Monolith Solar Associates LLC | CH-02691 | Catskill | Leeds | Greene | 12451 | G | 2005 | North Catskill | N |  | 7 | [13 empty] | NM | N | SMA SB7000 US | 2015-06-09 | 2015-06-11 | 2 | 2015-06-11 | [14 empty] | 2015-06-24 | 2015-07-01 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-05428 | Newburgh | Marlboro | Ulster | 12542 | G | 5003 | Marlboro | N |  | 7.2 | [13 empty] | NM | N | ABB PVI-3.6 (2) | 2015-06-09 | 2015-06-16 | 5 | 2015-06-16 | [14 empty] | 2015-07-29 | 2015-07-30 |  | Y
Central Hudson |  | SolarCity | CH-05509 | Catskill | Leeds | Greene | 12451 | G | 2005 | North Catskill | N |  | 7.2 | [13 empty] | NM | N | 2 ABB PVI-3.6-OUTD-S US | 2015-06-09 | 2015-06-23 | 10 | 2015-06-23 | [14 empty] | 2015-07-23 | 2015-07-29 |  | Y
Central Hudson |  | SolarCity | CH-07068 | Newburgh | Newburgh | Orange | 12550 | G | 4011 | West Balmville | N |  | 6 | [13 empty] | NM | N | ABB PVI-3.0 (2) | 2015-06-09 | 2015-06-16 | 5 | 2015-06-16 | [14 empty] | 2015-08-18 | 2015-08-25 |  | Y
Central Hudson |  | SolarCity | CH-07248 | Kingston | Glasco | Ulster | 12432 | G | 2015 | Lincoln Park | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000-OUTD-US | 2015-06-09 | 2015-06-23 | 10 | 2015-06-23 | [14 empty] | 2015-08-26 | 2015-09-02 |  | Y
Central Hudson |  | SolarCity | CH-07612 | Newburgh | Modena |  | 12548 | G | 5013 | Modena | TBD |  | 5 | [13 empty] | NM | N | ABB PVI-5000 (1) | 2015-06-09 | 2015-06-16 | 5 | 2015-06-16 | [17 empty] | W
Central Hudson |  | Lighthouse Solar | CH-03639 | Newburgh | Gardiner | Ulster | 12525 | G | 5034 | Galeville | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE 7600 (1) | 2015-06-10 | 2015-06-17 | 5 | 2015-06-17 | [14 empty] | 2015-08-24 | 2015-08-31 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03721 | Newburgh | Modena | Ulster | 12548 | G | 5013 | Modena | N |  | 10 | [13 empty] | NM | N | SOLAREDGE 10000 (1) | 2015-06-10 | 2015-06-17 | 5 | 2015-06-17 | [8 empty] | 350 | 350 |  |  |  |  | 2015-09-11 | 2015-09-18 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03755 | Newburgh | New Paltz |  | 12561 | G | 5011 | Modena | TBD |  | 11.4 | [13 empty] | NM | N | SOLAREDGE 11400 (1) | 2015-06-10 | 2015-06-17 | 5 | 2015-06-17 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | Lighthouse Solar | CH-03781 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8094 | Fishkill Plains | N |  | 6 | [13 empty] | NM | N | SOLAREDGE 6000 | 2015-06-17 | 2015-06-17 | 0 | 2015-06-17 | [14 empty] | 2015-08-20 | 2015-08-25 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03828 | Newburgh | New Paltz | Ulster | 12561 | G | 5011 | Modena | N | CH-03590 | 5 | [13 empty] | NM | N | SOLAREDGE 5000 (1) | 2015-06-10 | 2015-06-17 | 5 | 2015-06-17 | [14 empty] | 2015-07-13 | 2015-07-17 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03838 | Poughkeepsie | Rhinebeck |  | 12572 | G | 7053 | Rhinebeck | TBD |  | 5 | [13 empty] | NM | N | SOLAREDGE 5000 | 2015-06-10 | 2015-06-17 | 5 | 2015-06-17 | [17 empty] | W
Central Hudson |  | NRG Home Solar | CH-04825 | Fishkill | Hopewell Jct |  | 12533 | G | 8095 | Fishkill Plains | TBD |  | 6.5 | [13 empty] | NM | N | (26) ENPHASE ENERGY M-250 | 2015-06-17 | 2015-06-24 | 5 | 2015-06-24 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | Natural Energy Solutions | CH-02767 | Catskill | W Coxsackie | Greene | 12192 | G | 1076 | Coxsackie | N |  | 10.32 | [13 empty] | NM | N | 48 ENPHASE M215 | 2015-06-10 | 2015-06-24 | 10 | 2015-06-24 | [14 empty] | 2015-07-16 | 2015-07-22 |  | Y
Central Hudson |  | SolarCity | CH-05280 | Newburgh | New Paltz | Ulster | 12561 | G | 5021 | Ohioville | N |  | 3 | [13 empty] | NM | N | ABB PVI-3.0 | 2015-07-21 | 2015-07-24 | 3 | 2015-07-24 | [14 empty] | 2015-08-26 | 2015-09-02 |  | Y
Central Hudson |  | SolarCity | CH-06455 | Catskill | Catskill | Greene | 12414 | G | 2005 | North Catskill | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000-OUTD-US | 2015-06-10 | 2015-06-24 | 10 | 2015-06-24 | [14 empty] | 2015-08-04 | 2015-08-11 |  | Y
Central Hudson |  | SolarCity | CH-07023 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 3 | [13 empty] | NM | N | ABB PVI-3.0 (1) | 2015-06-10 | 2015-06-17 | 5 | 2015-06-17 | [14 empty] | 2015-07-30 | 2015-08-05 |  | Y
Central Hudson |  | Solar Generation | CH-08142 | Catskill | Climax | Greene | 12042 | G | 1071 | Coxsackie | N |  | 6 | [13 empty] | NM | N | SMA SB6000 TL | 2015-06-10 | 2015-06-24 | 10 | 2015-06-24 | [14 empty] | 2015-08-20 | 2015-08-25 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-03488 | Newburgh | Rock Tvrn | Orange | 12575 | G | 4097 | Bethlehem Rd | N |  | 10 | [13 empty] | NM | N | SMA SB3000 (1) SMA SB7000 (1) | 2015-06-11 | 2015-06-18 | 5 | 2015-06-18 | [14 empty] | 2015-09-24 | 2015-09-30 |  | Y
Central Hudson |  | Hollitronics Energy Solutions | CH-01206 | Catskill | Rensselaerville | Albany | 12147 | G | 1092 | Westerlo | N |  | 6 | [13 empty] | NM | N | 12 APS Y500A | 2015-06-11 | 2015-06-11 | 0 | 2015-06-11 | [14 empty] | 2015-07-15 | 2015-07-22 |  | Y
Central Hudson |  | SolarCity | CH-05031 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7056 | Rhinebeck | N |  | 9 | [13 empty] | NM | N | ABB PVI-6000 (1) ABB PVI-3000 (1) | 2015-06-11 | 2015-06-25 | 10 | 2015-06-25 | [8 empty] | 350 | 350 |  |  |  |  | 2015-09-09 | 2015-09-16 |  | Y
Central Hudson |  | SolarCity | CH-05488 | Catskill | Palenvl | Greene | 12463 | G | 2001 | North Catskill | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A US | 2015-06-11 | 2015-06-25 | 10 | 2015-06-25 | [14 empty] | 2015-07-23 | 2015-07-30 |  | Y
Central Hudson |  | SolarCity | CH-05680 | Kingston | W Hurley | Ulster | 12491 | G | 3013 | Woodstock | N |  | 4.2 | [13 empty] | NM | N | ABB PVI-4.2-OUTD-S-US | 2015-06-11 | 2015-06-25 | 10 | 2015-06-25 | [14 empty] | 2015-12-15 | 2015-12-22 |  | Y
Central Hudson |  | SolarCity | CH-07694 | Kingston | Kingston | Ulster | 12401 | G | 1024 | East Kingston | N |  | 4.2 | [13 empty] | NM | N | ABB PVI-4.2-OUTD-S-US-Z | 2015-06-11 | 2015-06-25 | 10 | 2015-06-25 | [14 empty] | 2015-10-01 | 2015-10-08 |  | Y
Central Hudson |  | Trinity Solar | CH-08417 | Poughkeepsie | Billings | Dutchess | 12510 | G | 6057 | Todd Hill | N |  | 17.4 | [13 empty] | NM | N | (1) SOLAR EDGE SE11400A-US (1) SOLAR EDGE SE6000A-US | 2015-06-11 | 2015-06-18 | 5 | 2015-06-18 | [8 empty] | 350 | 350 |  |  |  |  | 2015-12-14 | 2015-12-17 |  | Y
Central Hudson |  | You Save Green | CH-09961 | Newburgh | Washingtonvl | Orange | 10992 | G | 5052 | Maybrook | N |  | 9 | [13 empty] | NM | N | ENPHASE 250 (36) | 2015-06-22 | 2015-07-01 | 7 | 2015-07-01 | [8 empty] | 350 | 350 |  | 2015-08-19 | 2015-08-19 | 2016-01-14 | 2015-10-23 | 2015-11-04 |  | Y
Central Hudson |  | NRG Home Solar | CH-04557 | Poughkeepsie | Staatsburg | Dutchess | 12580 | G | 7042 | Staatsburg | N |  | 7.5 | [13 empty] | NM | N | (30) ENPHASE ENERGY M-250 | 2015-06-22 | 2015-07-02 | 8 | 2015-07-02 | [14 empty] | 2015-10-27 | 2015-11-02 |  | Y
Central Hudson |  | NRG Home Solar | CH-04713 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8091 | Fishkill Plains | N |  | 10.32 | [13 empty] | NM | N | (48) ENPHASE ENERGY M-215-60-S22-2LL-IG | 2015-06-18 | 2015-06-25 | 5 | 2015-06-25 | [14 empty] | 2015-08-27 | 2015-09-03 |  | Y
Central Hudson |  | SolarCity | CH-06046 | Fishkill | Stormvl | Dutchess | 12582 | G | 8095 | Fishkill Plains | N |  | 11.4 | [13 empty] | NM | N | SOLAREDGE SE11400A-US | 2015-06-12 | 2015-06-19 | 5 | 2015-06-19 | [14 empty] | 2015-09-01 | 2015-09-09 |  | Y
Central Hudson |  | SolarCity | CH-06801 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8091 | Fishkill Plains | N |  | 12 | [13 empty] | NM | N | (2) ABB PVI-6000-OUTD-US | 2015-08-05 | 2015-08-13 | 6 | 2015-08-13 | [14 empty] | 2015-08-31 | 2015-09-08 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07129 | Newburgh | Rock Tvrn | Orange | 12575 | G | 4097 | Bethlehem Rd | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000 (1) | 2015-06-12 | 2015-06-18 | 4 | 2015-06-18 | [14 empty] | 2015-06-26 | 2015-07-06 |  | Y
Central Hudson |  | SolarCity | CH-07520 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6044 | Spackenkill | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE7600A-US | 2015-06-12 | 2015-06-19 | 5 | 2015-06-19 | [14 empty] | 2015-11-06 | 2015-11-13 |  | Y
Central Hudson |  | SolarCity | CH-07832 | Newburgh | Modena | Ulster | 12548 | G | 5013 | Modena | N | CH-07093 | 3 | [13 empty] | NM | N | ABB PVI-3.0 (1) | 2015-06-12 | 2015-06-18 | 4 | 2015-06-18 | [14 empty] | 2015-08-12 | 2015-08-19 |  | Y
Central Hudson |  | Trinity Solar | CH-08428 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8091 | Fishkill Plains | N |  | 7.6 | [13 empty] | NM | N | SOLAR EDGE SE 7600A-US | 2015-06-12 | 2015-06-19 | 5 | 2015-06-19 | [14 empty] | 2015-10-21 | 2015-10-26 |  | Y
Central Hudson |  | Sungevity Inc | CH-09602 | Newburgh | New Paltz | Ulster | 12561 | G | 5023 | Ohioville | N |  | 9.8 | [13 empty] | NM | N | ABB PVI-6000 (1) ABB PVI-3.8 (1) | 2015-06-12 | 2015-06-18 | 4 | 2015-06-18 | [14 empty] | 2015-08-20 | 2015-08-25 |  | Y
Central Hudson |  | New York State Solar Farm | CH-03985 | Poughkeepsie | Milan | Dutchess | 12571 | G | 7061 | Milan | N |  | 11 | [13 empty] | NM | N | SMA SB 6.0 (1) SMA SB 5.0 (1) | 2015-06-19 | 2015-06-26 | 5 | 2015-06-26 | [14 empty] | 2015-07-24 | 2015-07-31 |  | Y
Central Hudson |  | NRG Home Solar | CH-04114 | Catskill | Westerlo | Albany | 12193 | G | 1092 | Westerlo | N |  | 8 | [13 empty] | NM | N | ENPHASE M250 (32) | 2015-06-15 | 2015-06-19 | 4 | 2015-06-19 | [14 empty] | 2015-10-08 | 2015-10-15 |  | Y
Central Hudson |  | NRG Home Solar | CH-04127 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8092 | Fishkill Plains | N |  | 5.59 | [13 empty] | NM | N | ENPHASE M-215 (26) | 2015-06-22 | 2015-07-01 | 7 | 2015-07-01 | [14 empty] | 2015-10-12 | 2015-10-15 |  | Y
Central Hudson |  | NRG Home Solar | CH-04243 | Catskill | Westerlo | Albany | 12193 | G | 1091 | Westerlo | N |  | 6.5 | [13 empty] | NM | N | ENPHASE M250 (26) | 2015-06-15 | 2015-06-19 | 4 | 2015-06-19 | [14 empty] | 2015-11-05 | 2015-11-12 |  | Y
Central Hudson |  | NRG Home Solar | CH-04577 | Newburgh | Highland | Ulster | 12528 | G | 5081 | Highland | N |  | 4.3 | [13 empty] | NM | N | ENPHASE M-215 (20) | 2015-06-29 | 2015-07-07 | 5 | 2015-07-07 | [14 empty] | 2015-09-28 | 2015-10-05 |  | Y
Central Hudson |  | Monolith Solar Associates LLC | CH-02652 | Catskill | Round Top | Greene | 12473 | G | 2042 | South Cairo | N |  | 5 | [13 empty] | NM | N | sma sb 5000 (1) | 2015-08-26 | 2015-09-10 | 10 | 2015-09-10 | [14 empty] | 2015-11-19 | 2015-11-30 |  | Y
Central Hudson |  | SolarCity | CH-05818 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6068 | Inwood Ave | N |  | 6.6 | [13 empty] | NM | N | ABB PVI-3.0 (1) ABB PVI-3.6 (1) | 2015-06-15 | 2015-06-19 | 4 | 2015-06-19 | [14 empty] | 2015-10-19 | 2015-10-26 |  | Y
Central Hudson |  | SolarCity | CH-06846 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8096 | Fishkill Plains | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000 (1) | 2015-06-15 | 2015-06-19 | 4 | 2015-06-19 | [14 empty] | 2015-08-19 | 2015-08-25 |  | Y
Central Hudson |  | Sungevity Inc | CH-09345 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8096 | Fishkill Plains | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000 (1) | 2015-06-15 | 2015-06-19 | 4 | 2015-06-19 | [14 empty] | 2015-07-29 | 2015-08-04 |  | Y
Central Hudson |  | Lotus Energy Inc. | CH-03883 | Catskill | Athens | Greene | 12015 | G | 1074 | Coxsackie | N |  | 5 | [13 empty] | NM | N | SMA SB5000 TL-US-22 | 2015-06-16 | 2015-06-26 | 8 | 2015-06-26 | [14 empty] | 2015-08-04 | 2015-08-11 |  | Y
Central Hudson |  | NRG Home Solar | CH-04625 | Fishkill | Garrison | Putnam | 10524 | G | 8086 | Tioronda | N |  | 4.73 | [13 empty] | NM | N | (22) ENPHASE ENERGY M-215 | 2015-06-24 | 2015-07-02 | 6 | 2015-07-02 | [14 empty] | 2015-11-17 | 2015-11-17 |  | Y
Central Hudson |  | NRG Home Solar | CH-04630 | Newburgh | New Windsor | Orange | 12553 | G | 4054 | Union Ave | N |  | 6.88 | [13 empty] | NM | N | ENPHASE M-215 (32) | 2015-06-24 | 2015-07-02 | 6 | 2015-07-02 | [14 empty] | 2015-10-13 | 2015-10-15 |  | Y
Central Hudson |  | NRG Home Solar | CH-04747 | Newburgh | Wallkill | Ulster | 12589 | G | 5042 | East Walden | N |  | 8.6 | [13 empty] | NM | N | ENPHASE M-215 (40) | 2015-06-23 | 2015-06-24 | 1 | 2015-06-24 | [14 empty] | 2015-10-13 | 2015-10-15 |  | Y
Central Hudson |  | NRG Home Solar | CH-04766 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 7025 | Tinkertown | N |  | 4.515 | [13 empty] | NM | N | (21) ENPHASE ENERGY M-215 | 2015-06-24 | 2015-07-01 | 5 | 2015-07-01 | [14 empty] | 2015-09-09 | 2015-09-16 |  | Y
Central Hudson |  | NRG Home Solar | CH-04807 | Kingston | Kingston | Ulster | 12401 | G | 1013 | Boulevard | N |  | 3.01 | [13 empty] | NM | N | 14 ENPHASE M-215-60-S22-2LL-IG | 2015-06-16 | 2015-06-26 | 8 | 2015-06-26 | [14 empty] | 2016-01-11 | 2016-01-18 |  | Y
Central Hudson |  | Hudson Valley Wind Energy, LLC | CH-02541 | Catskill | E Durham | Greene | 12423 | G | 2043 | South Cairo | N |  | 13.5 | [13 empty] | NM | N | FRONIUS IG A PLUS 6.0 (1) FRONIUS IG A PLUS 7.5 (1) | 2015-06-16 | 2015-06-26 | 8 | 2015-06-26 | [14 empty] | 2015-07-29 | 2015-08-05 |  | Y
Central Hudson |  | Mountaintop Greene Clean Energy | CH-02704 | Catskill | Jewett | Greene | 12444 | E | 2389 | Vinegar Hill | N |  | 7.7 | [13 empty] | NM | N | SMA 7700TL (1) | 2015-06-16 | 2015-06-26 | 8 | 2015-06-26 | [14 empty] | 2015-07-21 | 2015-07-23 |  | Y
Central Hudson |  | Solar Generation | CH-08308 | Kingston | Woodstock | Ulster | 12498 | G | 3014 | Woodstock | N | CH-08280 | 3 | [13 empty] | NM | N | 12 ENPHASE M250 | 2015-06-16 | 2015-06-26 | 8 | 2015-06-26 | [14 empty] | 2015-09-01 | 2015-09-08 |  | Y
Central Hudson |  | Apex Solar Power | CH-03080 | Newburgh | Walden | Orange | 12586 | G | 5041 | East Walden | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE 7600 (1) | 2015-07-22 | 2015-07-28 | 4 | 2015-07-28 | [14 empty] | 2015-12-01 | 2015-12-01 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-03425 | Newburgh | New Windsor | Orange | 12553 | G | 4043 | Union Ave | N |  | 3.8 | [13 empty] | NM | N | SMA SB3800 (1) | 2015-06-17 | 2015-06-24 | 5 | 2015-06-24 | [14 empty] | 2015-09-08 | 2015-09-15 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03565 | Kingston | Kingston | Ulster | 12401 | G | 1011 | Boulevard | N |  | 10 | [13 empty] | NM | N | SOLAREDGE 10000 A-US | 2015-06-17 | 2015-06-26 | 7 | 2015-06-26 | [14 empty] | 2015-10-27 | 2015-11-02 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03713 | Newburgh | Milton | Ulster | 12547 | G | 5083 | Highland | N |  | 3.8 | [13 empty] | NM | N | SOLAREDGE 3800 | 2015-06-23 | 2015-06-24 | 1 | 2015-06-24 | [14 empty] | 2015-09-04 | 2015-09-14 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03758 | Newburgh | New Paltz | Ulster | 12561 | G | 5024 | Ohioville | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE 7600 (1) | 2015-06-17 | 2015-06-24 | 5 | 2015-06-24 | [14 empty] | 2015-09-04 | 2015-09-14 |  | Y
Central Hudson |  | SolarCity | CH-05029 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 7011 | Hibernia | N |  | 3.6 | [13 empty] | NM | N | ABB PVI-3.6 (1) | 2015-06-17 | 2015-06-24 | 5 | 2015-06-24 | [14 empty] | 2015-08-27 | 2015-09-03 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-05061 | Newburgh | Walden | Orange | 12586 | G | 5041 | East Walden | N |  | 3.6 | [13 empty] | NM | N | ABB PVI-3.6 (1) | 2015-06-17 | 2015-06-24 | 5 | 2015-06-24 | [14 empty] | 2015-07-01 | 2015-07-09 |  | Y
Central Hudson |  | SolarCity | CH-05263 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7052 | Rhinebeck | N |  | 9 | [13 empty] | NM | N | ABB PVI-3.0 (1) ABB PVI-6.0 (1) | 2015-06-24 | 2015-07-02 | 6 | 2015-07-02 | [14 empty] | 2015-08-06 | 2015-08-13 |  | Y
Central Hudson |  | SolarCity | CH-06036 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8044 | Myers Corners | N |  | 5 | [13 empty] | NM | N | ABB PVI-5000 (1) | 2015-06-17 | 2015-06-24 | 5 | 2015-06-24 | [14 empty] | 2015-10-15 | 2015-10-22 |  | Y
Central Hudson |  | SolarCity | CH-06804 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8094 | Fishkill Plains | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000 | 2015-06-23 | 2015-07-01 | 6 | 2015-07-01 | [14 empty] | 2015-07-23 | 2015-07-29 |  | Y
Central Hudson |  | SolarCity | CH-07010 | Newburgh | Newburgh | Orange | 12550 | G | 4051 | Union Ave | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE7600A (1) | 2015-06-17 | 2015-07-01 | 10 | 2015-07-01 | [14 empty] | 2015-10-27 | 2015-10-30 |  | Y
Central Hudson |  | SolarCity | CH-05123 | Kingston | Rifton | Ulster | 12471 | G | 3041 | Sturgeon Pool | N |  | 8.6 | [13 empty] | NM | N | ABB PVI-3.6-OUTD-S-US ABB PVI-5000-OUTD-S-US | 2015-06-18 | 2015-06-26 | 6 | 2015-06-26 | [14 empty] | 2015-07-31 | 2015-08-07 |  | Y
Central Hudson |  | SolarCity | CH-06877 | Fishkill | Fishkill | Dutchess | 12524 | G | 8065 | Merritt Park | N |  | 6 | [13 empty] | NM | N | ABB PVI-3.0 (2) | 2015-06-18 | 2015-06-25 | 5 | 2015-06-25 | [14 empty] | 2015-10-14 | 2015-10-19 |  | Y
Central Hudson |  | SolarCity | CH-07571 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8092 | Fishkill Plains | N |  | 6 | [13 empty] | NM | N | ABB PVI-3.0 (2) | 2015-06-24 | 2015-06-25 | 1 | 2015-06-25 | [14 empty] | 2015-07-02 | 2015-07-10 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | American Solar Partners | CH-03062 | Newburgh | Highland | Ulster | 12528 | G | 5082 | Highland | N |  | 12 | [13 empty] | NM | N | SMA SB 6000 (2) | 2015-07-10 | 2015-07-17 | 5 | 2015-07-17 | [14 empty] | 2015-12-17 | 2015-12-22 |  | Y
Central Hudson |  | Kasselman Solar | CH-03525 | Kingston | Hurley | Ulster | 12443 | G | 2094 | Hurley Ave | N |  | 24.5 | [13 empty] | RNM | N | 98 ENPHASE M250 US | 2015-06-19 | 2015-06-29 | 6 | 2015-06-29 | [14 empty] | 2015-07-24 | 2015-07-31 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00889 | Catskill | Freehold | Greene | 12431 | G | 2071 | Freehold | N |  | 20 | [13 empty] | NM | N | 80 ENPHASE M250 6-2LL-S22 | 2015-06-19 | 2015-06-29 | 6 | 2015-06-29 | [8 empty] | 350 | 350 |  | 2015-07-23 | 2015-07-23 | 2015-07-30 | 2015-09-18 | 2015-09-24 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00931 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 6074 | East Park | N |  | 8.82 | [13 empty] | NM | N | ENPHASE M215 (41) | 2015-06-19 | 2015-07-02 | 9 | 2015-07-02 | [14 empty] | 2015-09-23 | 2015-09-29 |  | Y
Central Hudson |  | SolarCity | CH-05726 | Kingston | Malden-Hdsn | Ulster | 12453 | G | 3004 | Saugerties | N |  | 3 | [13 empty] | NM | N | ABB PVI-3.0-OUTD-S-US | 2015-06-19 | 2015-07-02 | 9 | 2015-07-02 | [14 empty] | 2015-07-30 | 2015-08-06 |  | Y
Central Hudson |  | SolarCity | CH-06077 | Fishkill | Wappingrs Falls |  | 12590 | G | 8092 | Fishkill Plains | TBD |  | 6 | [13 empty] | NM | N | ABB PVI-6000 (1) | 2015-06-19 | 2015-06-26 | 5 | 2015-06-26 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | SolarCity | CH-06208 | Newburgh | Walden | Orange | 12586 | G | 4023 | Coldenham | N |  | 15 | [13 empty] | NM | N | ABB PVI-3.0 (1) ABB PVI-6.0 (2) | 2015-06-19 | 2015-06-26 | 5 | 2015-06-26 | [14 empty] | 2015-08-24 | 2015-08-31 |  | Y
Central Hudson |  | SolarCity | CH-06887 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8014 | Forgebrook | N |  | 5 | [13 empty] | NM | N | ABB PVI-5000 (1) | 2015-06-30 | 2015-07-08 | 5 | 2015-07-08 | [14 empty] | 2015-10-05 | 2015-10-09 |  | Y
Central Hudson |  | SolarCity | CH-07136 | Newburgh | Rock Tvrn | Orange | 12575 | G | 4097 | Bethlehem Rd | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000 (1) | 2015-06-29 | 2015-07-08 | 6 | 2015-07-08 | [14 empty] | 2015-08-07 | 2015-08-13 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03717 | Newburgh | Wallkill | Ulster | 12589 | G | 5030 | Galeville | N |  | 15.2 | [13 empty] | NM | N | ABB POWERONE UNO-7.6 (2) | 2015-06-29 | 2015-07-08 | 6 | 2015-07-08 | [14 empty] | 2015-08-24 | 2015-08-28 |  | Y
Central Hudson |  | SolarCity | CH-05332 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8091 | Fishkill Plains | N |  | 7.2 | [13 empty] | NM | N | ABB PVI-3.6 (2) | 2015-06-22 | 2015-07-01 | 7 | 2015-07-01 | [14 empty] | 2015-08-14 | 2015-08-21 |  | Y
Central Hudson |  | SolarCity | CH-06849 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8096 | Fishkill Plains | N |  | 9 | [13 empty] | NM | N | ABB PVI-6000 (1) ABB PVI-3000 (1) | 2015-06-22 | 2015-07-01 | 7 | 2015-07-01 | [14 empty] | 2016-03-14 | 2016-03-21 |  | Y
Central Hudson |  | Solar Generation | CH-08180 | Kingston | Kingston | Ulster | 12401 | G | 2093 | Hurley Ave | N |  | 10 | [13 empty] | NM | N | 2 SMA SB 500 TL | 2015-06-22 | 2015-07-02 | 8 | 2015-07-02 | [14 empty] | 2015-12-07 | 2015-12-11 |  | Y
Central Hudson |  | Greenskies Renewable Energy LLC | CH-01173 | Newburgh | Newburgh | Orange | 12550 | G | 4055 | Union Ave | N |  | 308 | [13 empty] | NM | N | (11) Solectria PVI28TL | 2015-08-14 | 2015-09-04 | 15 | 2015-09-04 | 2015-08-14 | 2015-09-04 | 15 | [11 empty] | 2016-08-25 | 2016-08-25 |  | Y
Central Hudson |  | Monolith Solar Associates LLC | CH-02667 | Catskill | Coeymans | Albany | 12045 | G | 1082 | New Baltimore | N |  | 10 | [13 empty] | NM | N | 2 SMA 5000 TL | 2015-06-23 | 2015-07-06 | 8 | 2015-07-06 | [14 empty] | 2015-12-02 | 2015-12-09 |  | Y
Central Hudson |  | Murphy Solar Power | CH-02746 | Catskill | Leeds | Columbia | 12541 | G | 2005 | North Catskill | N |  | 5 | [13 empty] | NM | N | SMA SB 5000-TL-US | 2015-06-23 | 2015-07-06 | 8 | 2015-07-06 | [14 empty] | 2015-07-20 | 2015-07-27 |  | Y
Central Hudson |  | SolarCity | CH-04979 | Catskill | Cairo | Greene | 12413 | G | 2043 | South Cairo | N |  | 3.6 | [13 empty] | NM | N | ABB PVI-3.6-OUTD-S-US | 2015-06-23 | 2015-07-06 | 8 | 2015-07-06 | [14 empty] | 2015-07-24 | 2015-08-03 |  | Y
Central Hudson |  | SolarCity | CH-06638 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6003 | Reynolds Hill | N |  | 3.8 | [13 empty] | NM | N | SOLAREDGE SE3800A | 2015-06-23 | 2015-07-01 | 6 | 2015-07-01 | [14 empty] | 2015-08-26 | 2015-09-02 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06891 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8051 | North Chelsea | N |  | 8.6 | [13 empty] | NM | N | ABB PVI-5000 (1) ABB PVI-3600 (1) | 2015-07-01 | 2015-07-09 | 5 | 2015-07-09 | [14 empty] | 2015-07-13 | 2015-07-17 |  | Y
Central Hudson |  | SolarCity | CH-07639 | Kingston | Kingston | Ulster | 12401 | G | 2093 | Hurley Ave | N |  | 3 | [13 empty] | NM | N | ABB PVI-3.0-OUTD-S-US | 2015-06-23 | 2015-07-06 | 8 | 2015-07-06 | [14 empty] | 2015-12-08 | 2015-12-15 |  | Y
Central Hudson |  | Sungevity Inc | CH-09415 | Kingston | Saugerties |  | 12477 | G | 3002 | Saugerties | TBD |  | 7.6 | [13 empty] | NM | N | 2 ABB PVI-3.8-OUTD-S-US-A | 2015-06-23 | 2015-07-06 | 8 | 2015-07-06 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | Hudson Solar | CH-01318 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7051 | Rhinebeck | N |  | 11 | [13 empty] | NM | N | (1) SMA AMERICA SB5000 (1) SMA AMERICA SB6000 | 2015-06-24 | 2015-07-09 | 10 | 2015-07-09 | [8 empty] | 350 | 350 |  |  |  |  | 2015-08-13 | 2015-08-19 |  | Y
Central Hudson |  | Hudson Solar | CH-01831 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7051 | Rhinebeck | N |  | 8 | [13 empty] | NM | N | (2) SMA AMERICA SB4000 | 2015-06-24 | 2015-07-09 | 10 | 2015-07-09 | [14 empty] | 2015-09-21 | 2015-09-25 |  | Y
Central Hudson |  | Hudson Solar | CH-01924 | Fishkill | Fishkill | Dutchess | 12524 | G | 8012 | Forgebrook | N |  | 7 | [13 empty] | NM | N | SMA AMERICA SB7000 (1) | 2015-06-24 | 2015-07-02 | 6 | 2015-07-02 | [14 empty] | 2015-12-09 | 2015-12-09 |  | Y
Central Hudson |  | Hudson Solar | CH-01929 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8071 | Shenandoah | N |  | 7.7 | [13 empty] | NM | N | SMA AMERICA SB7000 (1) | 2015-06-24 | 2015-07-02 | 6 | 2015-07-02 | [14 empty] | 2015-09-29 | 2015-09-30 |  | Y
Central Hudson |  | Hudson Solar | CH-01930 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8071 | Shenandoah | N |  | 8.8 | [13 empty] | NM | N | SMA AMERICA SB3800 (1) SMA AMERICA SB5000 (1) | 2015-06-24 | 2015-07-02 | 6 | 2015-07-02 | [14 empty] | 2015-10-09 | 2015-10-14 |  | Y
Central Hudson |  | Hudson Solar | CH-02118 | Poughkeepsie | Barrytown | Dutchess | 12507 | G | 7056 | Rhinebeck | N |  | 3.8 | [13 empty] | NM | N | SMA AMERICA SB3800 | 2015-06-24 | 2015-07-09 | 10 | 2015-07-09 | [14 empty] | 2015-09-25 | 2015-10-02 |  | Y
Central Hudson |  | SolarCity | CH-05019 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6042 | Spackenkill | N | CH-05019 | 3 | [13 empty] | NM | N | 1 ABB ABB PVI-3.0-OUTD-S1ABBPVI-3.0-OUTD-S-US-Z-A | 2015-06-24 | 2015-07-09 | 10 | 2015-07-09 | [14 empty] | 2015-08-26 | 2015-09-02 |  | Y
Central Hudson |  | SolarCity | CH-06329 | Newburgh | Marlboro | Ulster | 12542 | G | 5001 | Marlboro | N |  | 5 | [13 empty] | NM | N | ABB PVI-5000 (1) | 2015-07-06 | 2015-07-13 | 5 | 2015-07-13 | [14 empty] | 2015-07-20 | 2015-07-24 |  | Y
Central Hudson |  | SolarCity | CH-06361 | Newburgh | Wallkill | Ulster | 12589 | G | 5041 | East Walden | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 (1) | 2015-06-24 | 2015-07-09 | 10 | 2015-07-09 | [14 empty] | 2016-01-13 | 2016-01-15 |  | Y
Central Hudson |  | SolarCity | CH-06701 | Poughkeepsie | Lagrangevl | Dutchess | 12540 | G | 6053 | Todd Hill | N |  | 5 | [13 empty] | NM | N | ABB PVI-5000-OUTD-US | 2015-06-24 | 2015-07-09 | 10 | 2015-07-09 | [14 empty] | 2015-08-14 | 2015-08-21 |  | Y
Central Hudson |  | SolarCity | CH-07773 | Newburgh | Newburgh | Orange | 12550 | G | 4012 | West Balmville | N |  | 3 | [13 empty] | NM | N | ABB PVI-3.0 (1) | 2015-07-06 | 2015-07-13 | 5 | 2015-07-13 | [14 empty] | 2015-07-22 | 2015-07-28 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08657 | Catskill | New Baltimore | Greene | 12124 | G | 1083 | New Baltimore | N |  | 12.9 | [13 empty] | NM | N | 60 ENPHASE M215 602LLS2XZC | 2015-06-24 | 2015-07-06 | 7 | 2015-07-06 | [14 empty] | 2016-03-16 | 2016-03-22 |  | Y
Central Hudson |  | Sol Providers | CH-08958 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6045 | Spackenkill | N |  | 3 | [13 empty] | NM | N | SolarEdge SE3000A-US | 2015-07-28 | 2015-08-04 | 5 | 2015-08-04 | [14 empty] | 2015-08-13 | 2015-08-19 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | NRG Home Solar | CH-04692 | Kingston | Saugerties | Ulster | 12477 | G | 3003 | Saugerties | N |  | 7.25 | [13 empty] | NM | N | 29 ENPHASE M-250-60-2LL-S22 | 2015-06-25 | 2015-07-06 | 6 | 2015-07-06 | [14 empty] | 2015-09-10 | 2015-09-17 |  | Y
Central Hudson |  | NRG Home Solar | CH-04734 | Fishkill | Beacon |  | 12508 | G | 8087 | Tioronda | TBD |  | 5.25 | [13 empty] | NM | N | ENPHASE ENERGY M-250 (21) | 2015-07-08 | 2015-07-14 | 4 | 2015-07-14 | [17 empty] | W |  | Customer already had net meter prior to application. 9/28/15 - Customer advised meter rep that they are not installing solar.
Central Hudson |  | SolarCity | CH-06356 | Newburgh | Modena | Ulster | 12548 | G | 5013 | Modena | N |  | 9 | [13 empty] | NM | N | ABB PVI-3.0 (1) ABB PVI-6000 (1) | 2015-06-25 | 2015-07-06 | 6 | 2015-07-06 | [14 empty] | 2015-07-09 | 2015-07-15 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06408 | Newburgh | Campbell Hall | Orange | 10916 | G | 5051 | Maybrook | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000 | 2015-07-06 | 2015-07-13 | 5 | 2015-07-13 | [14 empty] | 2015-08-13 | 2015-08-20 |  | Y
Central Hudson |  | SolarCity | CH-07790 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8072 | Shenandoah | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2015-06-25 | 2015-07-06 | 6 | 2015-07-06 | [14 empty] | 2015-08-26 | 2015-09-02 |  | Y
Central Hudson |  | Sungevity Inc | CH-09485 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 5 | [13 empty] | NM | N | ABB PVI-5000 | 2015-07-17 | 2015-07-23 | 4 | 2015-07-23 | [14 empty] | 2015-09-01 | 2015-09-09 |  | Y
Central Hudson |  | Lotus Energy Inc. | CH-03885 | Poughkeepsie | Poughkeepsie |  | 12601 | G | 6002 | Reynolds Hill | TBD |  | 6 | [13 empty] | NM | N | SMA 6000TL | 2015-07-10 | 2015-07-16 | 4 | 2015-07-16 | [17 empty] | W |  | Customer already had net meter prior to application. 7/3/15 Company Holiday.
Central Hudson |  | Apex Solar Power | CH-00687 | Newburgh | Newburgh | Orange | 12550 | G | 4051 | Union Ave | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE7600 | 2015-07-28 | 2015-08-04 | 5 | 2015-08-04 | [14 empty] | 2015-10-01 | 2015-10-08 |  | Y
Central Hudson |  | SolarCity | CH-05373 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8091 | Fishkill Plains | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE7600A (1) | 2015-06-26 | 2015-07-06 | 5 | 2015-07-06 | [14 empty] | 2016-09-22 | 2016-09-22 |  | Y
Central Hudson |  | SolarCity | CH-05462 | Newburgh | Maybrook | Orange | 12543 | G | 5052 | Maybrook | N |  | 9 | [13 empty] | NM | N | ABB PVI-6000 (1) ABB PVI-3000 (1) | 2015-07-07 | 2015-07-13 | 4 | 2015-07-13 | [14 empty] | 2015-07-29 | 2015-08-10 |  | Y
Central Hudson |  | SolarCity | CH-06235 | Newburgh | Newburgh | Orange | 12550 | G | 4014 | West Balmville | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 (1) | 2015-07-09 | 2015-07-15 | 4 | 2015-07-15 | [14 empty] | 2015-07-24 | 2015-07-31 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06360 | Newburgh | Wallkill | Ulster | 12589 | G | 5041 | East Walden | N |  | 3 | [13 empty] | NM | N | SE 3000 (1) | 2015-07-09 | 2015-07-15 | 4 | 2015-07-15 | [8 empty] | 350 | 350 |  | 2015-08-20 | 2015-08-20 | 2015-08-25 | 2016-08-30 | 2016-08-31 |  | Y
Central Hudson |  | SolarCity | CH-07200 | Kingston | Accord | Ulster | 12404 | G | 3081 | Kerhonkson | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000-OUTD-US | 2015-06-26 | 2015-07-06 | 5 | 2015-07-06 | [14 empty] | 2015-08-12 | 2015-08-19 |  | Y
Central Hudson |  | SolarCity | CH-07282 | Poughkeepsie | Rhinebeck |  | 12572 | G | 7011 | Hibernia | TBD |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2015-06-26 | 2015-07-06 | 5 | 2015-07-06 | [17 empty] | W |  | 7/3/15 Company Holiday.
Central Hudson |  | SolarCity | CH-07382 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8093 | Fishkill Plains | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A (1) | 2015-06-26 | 2015-07-06 | 5 | 2015-07-06 | [14 empty] | 2015-09-30 | 2015-10-07 |  | Y
Central Hudson |  | SolarCity | CH-07404 | Fishkill | Beacon | Dutchess | 12508 | G | 8087 | Tioronda | N |  | 3.6 | [13 empty] | NM | N | ABB PVI-3.6 (1) | 2015-06-26 | 2015-07-06 | 5 | 2015-07-06 | [14 empty] | 2015-08-03 | 2015-08-10 |  | Y
Central Hudson |  | SolarCity | CH-07645 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6011 | Sand Dock | N |  | 3 | [13 empty] | NM | N | ABB PVI-3.0-OUTD | 2015-06-26 | 2015-07-06 | 5 | 2015-07-06 | [14 empty] | 2015-08-19 | 2015-08-25 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00885 | Catskill | West Kill | Greene | 12492 | E | 2389 | Vinegar Hill | N |  | 4.515 | [13 empty] | NM | N | 21 ENPHASE M215 60-2LL-S22 | 2015-06-29 | 2015-07-06 | 4 | 2015-07-06 | [14 empty] | 2015-09-15 | 2015-09-22 |  | Y
Central Hudson |  | Hudson Solar | CH-01312 | Poughkeepsie | Pine Plns | Dutchess | 12567 | G | 7091 | Pulvers Corners | N |  | 30 | [13 empty] | NM | N | (2) SMA AMERICA STP15000 | 2015-07-15 | 2015-07-21 | 4 | 2015-07-21 | [14 empty] | 2015-07-21 | 2015-07-30 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Mannino Electric | CH-02595 | Newburgh | Wallkill | Ulster | 12589 | G | 5043 | East Walden | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE7600 | 2015-07-08 | 2015-07-14 | 4 | 2015-07-14 | [14 empty] | 2015-08-10 | 2015-08-17 |  | Y
Central Hudson |  | SolarCity | CH-06854 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8094 | Fishkill Plains | N |  | 9.6 | [13 empty] | NM | N | ABB PVI-3.0 (2) ABB PVI-3.6 (1) | 2015-06-29 | 2015-07-08 | 6 | 2015-07-08 | [14 empty] | 2015-08-03 | 2015-08-07 |  | Y
Central Hudson |  | Solar States LLC | CH-09038 | Newburgh | Marlboro | Ulster | 12542 | G | 5003 | Marlboro | N |  | 8.8 | [13 empty] | NM | N | SB 3800TL (1) SMA SB 5000TL (1) | 2015-07-22 | 2015-07-28 | 4 | 2015-07-28 | [14 empty] | 2016-04-05 | 2016-04-07 |  | Y
Central Hudson |  | Sungevity Inc | CH-09245 | Newburgh | New Paltz |  | 12561 | G | 5031 | Galeville | TBD |  | 8 | [13 empty] | NM | N | ABB PVI-4.2 (1) ABB PVI-3.8 (1) | 2015-06-29 | 2015-07-08 | 6 | 2015-07-08 | [17 empty] | W |  | Customer already had net meter prior to application. 7/3/2015 COMPANY HOLIDAY.
Central Hudson |  | Sungevity Inc | CH-09264 | Catskill | Athens | Greene | 12015 | G | 2002 | North Catskill | N |  | 7.7 | [13 empty] | NM | N | SMA AMERICA SB7700TL-US-22 | 2015-06-29 | 2015-07-08 | 6 | 2015-07-08 | [14 empty] | 2015-08-04 | 2015-08-11 |  | Y
Central Hudson |  | Van Der Koos Construction | CH-09752 | Fishkill | Cold Spg | Putnam | 10516 | G | 8087 | Tioronda | N |  | 10.32 | [13 empty] | NM | N | enphase M215 (48) | 2015-08-19 | 2015-08-19 | 0 | 2015-08-19 | [14 empty] | 2015-09-17 | 2015-09-21 |  | Y
Central Hudson |  | Hudson Solar | CH-01609 | Catskill | Rensselaervl | Albany | 12147 | G | 1092 | Westerlo | N | CH-01609 | 8 | [13 empty] | NM | N | 2 SMA AMERICA SB4000 TL-US-22 | 2015-06-30 | 2015-07-08 | 5 | 2015-07-08 | [14 empty] | 2015-11-03 | 2015-11-09 |  | Y
Central Hudson |  | Hudson Solar | CH-01652 | Kingston | Accord | Ulster | 12404 | G | 3024 | High Falls | N |  | 6 | [13 empty] | NM | N | SMA AMERICA SB6000 TL-US-22 | 2015-06-30 | 2015-07-08 | 5 | 2015-07-08 | [14 empty] | 2015-09-14 | 2015-09-21 |  | Y
Central Hudson |  | Paradise Energy Solutions LLC | CH-02841 | Fishkill | Fishkill | Dutchess | 12524 | G | 8011 | Forgebrook | N |  | 7 | [13 empty] | NM | N | SMA 7000 (1) | 2015-07-21 | 2015-07-24 | 3 | 2015-07-24 | [14 empty] | 2015-10-06 | 2015-10-06 |  | Y
Central Hudson |  | SolarCity | CH-05258 | Poughkeepsie | Lagrangevl | Dutchess | 12540 | G | 6053 | Todd Hill | N |  | 9.2 | [13 empty] | NM | N | (1) ABB PVI-5000-OUTD (1) ABB PVI-4.2-OUTD | 2015-06-30 | 2015-07-09 | 6 | 2015-07-09 | [14 empty] | 2015-08-19 | 2015-08-25 |  | Y
Central Hudson |  | SolarCity | CH-06130 | Fishkill | Stormvl | Dutchess | 12582 | G | 8093 | Fishkill Plains | N |  | 9.6 | [13 empty] | NM | N | ABB PVI-3.6 (1) ABB PVI-6000 (1) | 2015-06-30 | 2015-07-09 | 6 | 2015-07-09 | [14 empty] | 2015-09-14 | 2015-09-21 |  | Y
Central Hudson |  | SolarCity | CH-07484 | Newburgh | New Windsor | Orange | 12553 | G | 4095 | Bethlehem Rd | N |  | 3 | [13 empty] | NM | N | ABB PVI-3.0 (1) | 2015-07-13 | 2015-07-17 | 4 | 2015-07-17 | [14 empty] | 2015-12-03 | 2015-12-03 |  | Y
Central Hudson |  | SolarCity | CH-07596 | Newburgh | Newburgh | Orange | 12550 | G | 4024 | Coldenham | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000 (1) | 2015-06-30 | 2015-07-09 | 6 | 2015-07-09 | [14 empty] | 2015-08-27 | 2015-09-03 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07751 | Newburgh | Montgomery | Orange | 12549 | G | 5073 | Montgomery | N | CH-07751 | 3 | [13 empty] | NM | N | ABB PVI-3.0 (1) | 2015-06-30 | 2015-07-08 | 5 | 2015-07-08 | [14 empty] | 2015-07-29 | 2015-08-04 |  | Y
Central Hudson |  | SolarCity | CH-07759 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 6062 | Inwood Ave | N |  | 10 | [13 empty] | NM | N | (2) ABB PVI-5000-OUTD | 2015-06-30 | 2015-07-09 | 6 | 2015-07-09 | [14 empty] | 2015-08-26 | 2015-09-02 |  | Y
Central Hudson |  | SolarCity | CH-07849 | Kingston | Stone Ridge |  | 12484 | G | 3021 | High Falls | TBD |  | 952 | [13 empty] | NM | N | (34) SOLECTRIA PVI 28TL-US | 2015-12-08 | 2015-12-30 | 14 | 2015-12-30 | 2015-12-08 | 2015-12-30 | 14 | 2016-02-08 |  |  |  | 30000 | [9 empty] | W |  | Customer already had net meter prior to application. 7/3/15 Company Holiday. 12/24/15 & 12/25/15 Company Holidays. CESIR determined necessary during preliminary review Section C, Step 4.
Central Hudson |  | Kasselman Solar | CH-03530 | Catskill | Hunter |  | 12442 | E | 2081 | Hunter | TBD |  | 24 | [13 empty] | NM | N | 98 ENPHASE M250-US | 2015-07-01 | 2015-07-09 | 5 | 2015-07-09 | [17 empty] | W |  | 07/03/2015 Company Holiday
Central Hudson |  | Hudson Solar | CH-01521 | Newburgh | Cornwall | Orange | 12518 | G | 4041 | Union Ave | N |  | 8.8 | [13 empty] | NM | N | SMA AMERICA SB5000 (1) SMA AMERICA SB3800 (1) | 2015-07-01 | 2015-07-09 | 5 | 2015-07-09 | [14 empty] | 2015-08-28 | 2015-09-04 |  | Y
Central Hudson |  | Hudson Solar | CH-01810 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 7025 | Tinkertown | N | CH-01810 | 7.7 | [13 empty] | NM | N | SMA AMERICA SB7700 | 2015-07-01 | 2015-07-09 | 5 | 2015-07-09 | [14 empty] | 2015-09-04 | 2015-09-14 |  | Y
Central Hudson |  | Hudson Solar | CH-02018 | Kingston | Tillson | Ulster | 12486 | G | 3022 | High Falls | N | CH-02018 | 6 | [13 empty] | NM | N | SMA AMERICA SB6000 TL-US-22 | 2015-07-01 | 2015-07-09 | 5 | 2015-07-09 | [14 empty] | 2015-10-30 | 2015-11-06 |  | Y
Central Hudson |  | Hudson Solar | CH-02054 | Kingston | Woodstock |  | 12498 | G | 3014 | Woodstock | N |  | 5 | [13 empty] | NM | N | SMA AMERICA SB5000 TL-US-22 | 2015-07-01 | 2015-07-09 | 5 | 2015-07-09 | [14 empty] | 2015-10-13 | 2015-10-16 |  | W
Central Hudson |  | Hudson Solar | CH-02285 | Poughkeepsie | Tivoli |  | 12583 | G | 7051 | Rhinebeck | TBD |  | 8 | [13 empty] | NM | N | (1) SMA AMERICA SB5000 (1) SMA AMERICA SB3000 | 2015-07-01 | 2015-07-09 | 5 | 2015-07-09 | [17 empty] | W
Central Hudson |  | Hudson Solar | CH-02360 | Newburgh | Wallkill | Ulster | 12589 | G | 5043 | East Walden | N |  | 6 | [13 empty] | NM | N | SMA AMERICA SB6000 (1) | 2015-07-01 | 2015-07-09 | 5 | 2015-07-09 | [14 empty] | 2015-09-30 | 2015-10-07 |  | Y
Central Hudson |  | SolarCity | CH-05079 | Newburgh | Marlboro | Ulster | 12542 | G | 5003 | Marlboro | N |  | 7.2 | [13 empty] | NM | N | ABB PVI-3.6 (2) | 2015-07-10 | 2015-07-13 | 1 | 2015-07-13 | [14 empty] | 2015-10-21 | 2015-10-27 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-05306 | Newburgh | Wallkill | Ulster | 12589 | G | 5043 | East Walden | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000 (1) | 2015-07-13 | 2015-07-17 | 4 | 2015-07-17 | [14 empty] | 2015-08-26 | 2015-09-02 |  | Y
Central Hudson |  | SolarCity | CH-05605 | Catskill | Ravena | Albany | 12143 | G | 1082 | New Baltimore | N |  | 5 | [13 empty] | NM | N | ABB PVI-5000-OUTD US | 2015-07-01 | 2015-07-09 | 5 | 2015-07-09 | [14 empty] | 2015-08-03 | 2015-08-10 |  | Y
Central Hudson |  | SolarCity | CH-05869 | Poughkeepsie | Rhinebeck |  | 12572 | G | 7052 | Rhinebeck | TBD |  | 6 | [13 empty] | NM | N | 2 - ABB PVI-3.0-OUTD | 2015-07-01 | 2015-07-09 | 5 | 2015-07-09 | [17 empty] | W |  | Customer already had net meter prior to application. 7/3/15 Company Holiday.
Central Hudson |  | SolarCity | CH-05880 | Poughkeepsie | Lagrangevl | Dutchess | 12540 | G | 6055 | Todd Hill | N |  | 13.8 | [13 empty] | NM | N | (1) ABB PVI-3.6-OUTD, (1) ABB PVI-4.2-OUTD & (1) ABB PVI-6000-OUTD | 2015-07-01 | 2015-07-09 | 5 | 2015-07-09 | [8 empty] | 350 | 350 |  |  |  |  | 2015-08-13 | 2015-08-25 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06164 | Newburgh | New Paltz | Ulster | 12561 | G | 5011 | Modena | N |  | 7.2 | [13 empty] | NM | N | ABB PVI-3.6 (2) | 2015-07-01 | 2015-07-09 | 5 | 2015-07-09 | [14 empty] | 2015-08-26 | 2015-09-02 |  | Y
Central Hudson |  | SolarCity | CH-06934 | Fishkill | Beacon | Dutchess | 12508 | G | 8017 | Forgebrook | N |  | 5 | [13 empty] | NM | N | ABB PVI-5000 (1) | 2015-07-01 | 2015-07-09 | 5 | 2015-07-09 | [14 empty] | 2015-07-30 | 2015-08-05 |  | Y
Central Hudson |  | SolarCity | CH-06995 | Newburgh | Newburgh | Orange | 12550 | G | 4023 | Coldenham | N |  | 3.6 | [13 empty] | NM | N | ABB PVI-3.6 (1) | 2015-07-01 | 2015-07-09 | 5 | 2015-07-09 | [14 empty] | 2015-07-30 | 2015-08-05 |  | Y
Central Hudson |  | SolarCity | CH-07638 | Kingston | Kingston | Ulster | 12401 | G | 2093 | Hurley Ave | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000-OUTD-US-Z-A | 2015-07-01 | 2015-07-09 | 5 | 2015-07-09 | [14 empty] | 2015-12-08 | 2015-12-15 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-03437 | Newburgh | Cornwall | Orange | 12518 | G | 4041 | Union Ave | N |  | 8 | [13 empty] | NM | N | SMA SB3000TL (1) SMA SB5000TL (1) | 2015-07-02 | 2015-07-10 | 5 | 2015-07-10 | [14 empty] | 2015-09-08 | 2015-09-15 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-03451 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6092 | Manchester | N |  | 5 | [13 empty] | NM | N | SMA America SB5000-TL-22 | 2015-07-02 | 2015-07-10 | 5 | 2015-07-10 | [14 empty] | 2015-10-20 | 2015-11-02 |  | Y
Central Hudson |  | Pfister Energy, Inc. | CH-02858 | Newburgh | Newburgh | Orange | 12550 | G | 4091 | Bethlehem Rd | N |  | 75 | [13 empty] | NM | N | (300) Enphase M250 | 2015-12-16 | 2016-01-11 | 15 | 2016-01-11 | 2015-12-16 | 2016-01-11 | 15 | [11 empty] | 2016-10-28 | 2016-10-28 |  | Y
Central Hudson |  | SolarCity | CH-06352 | Newburgh | Wallkill | Ulster | 12589 | G | 5041 | East Walden | N |  | 10 | [13 empty] | NM | N | SOLAREDGE SE10000A (1) | 2015-07-02 | 2015-07-16 | 9 | 2015-07-16 | [14 empty] | 2015-07-30 | 2015-08-05 |  | Y
Central Hudson |  | Sungevity Inc | CH-09438 | Newburgh | Highland | Ulster | 12528 | G | 5024 | Ohioville | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000-OUTD | 2015-07-02 | 2015-07-10 | 5 | 2015-07-10 | [14 empty] | 2015-10-12 | 2015-10-19 |  | Y
Central Hudson |  | Apex Solar Power | CH-03093 | Catskill | Greenville | Greene | 12083 | G | 2061 | Freehold | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000 A-US | 2015-07-06 | 2015-07-15 | 7 | 2015-07-15 | [14 empty] | 2015-09-02 | 2015-09-03 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-03379 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8095 | Fishkill Plains | N |  | 8 | [13 empty] | NM | N | sma sb8000 (1) | 2015-07-06 | 2015-07-13 | 5 | 2015-07-13 | [14 empty] | 2015-10-30 | 2015-11-03 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00890 | Catskill | Greenvl | Greene | 12083 | G | 2061 | Freehold | N |  | 9.89 | [13 empty] | NM | N | 46 ENPHASE M215 60-2LL-S22 | 2015-07-06 | 2015-07-14 | 6 | 2015-07-14 | [14 empty] | 2015-08-26 | 2015-09-01 |  | Y
Central Hudson |  | SolarCity | CH-05172 | Newburgh | Washingtonvl | Orange | 10992 | G | 4097 | Bethlehem Rd | N |  | 14 | [13 empty] | NM | N | ABB PVI-6000 (1) ABB PVI-5000 (1) ABB PVI-3000 (1) | 2015-07-06 | 2015-07-13 | 5 | 2015-07-13 | [14 empty] | 2015-07-31 | 2015-08-06 |  | Y
Central Hudson |  | SolarCity | CH-05183 | Newburgh | New Paltz | Ulster | 12561 | G | 5024 | Ohioville | N |  | 5 | [13 empty] | NM | N | ABB PVI-5000 | 2015-07-22 | 2015-07-28 | 4 | 2015-07-28 | [14 empty] | 2015-08-26 | 2015-09-02 |  | Y
Central Hudson |  | SolarCity | CH-05778 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6046 | Spackenkill | N |  | 3 | [13 empty] | NM | N | ABB PVI-3.0-OUTD | 2015-07-06 | 2015-07-10 | 4 | 2015-07-10 | [14 empty] | 2015-08-31 | 2015-09-08 |  | Y
Central Hudson |  | SolarCity | CH-06013 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8091 | Fishkill Plains | N |  | 8.6 | [13 empty] | NM | N | ABB PVI-5000 (1) ABB PVI-3.600 (1) | 2015-07-23 | 2015-07-23 | 0 | 2015-07-23 | [14 empty] | 2015-08-03 | 2015-08-07 |  | Y
Central Hudson |  | SolarCity | CH-06111 | Fishkill | Fishkill | Dutchess | 12524 | G | 8016 | Forgebrook | N |  | 7.8 | [13 empty] | NM | N | ABB PVI-4.2 (1) ABB PVI-3.6 (1) | 2015-07-06 | 2015-07-10 | 4 | 2015-07-10 | [14 empty] | 2015-08-03 | 2015-08-07 |  | Y
Central Hudson |  | SolarCity | CH-06144 | Fishkill | Beacon | Dutchess | 12508 | G | 8017 | Forgebrook | N |  | 6 | [13 empty] | NM | N | ABB PVI-3.0 (2) | 2015-07-17 | 2015-07-20 | 1 | 2015-07-20 | [14 empty] | 2015-10-05 | 2015-10-09 |  | Y
Central Hudson |  | SolarCity | CH-06363 | Newburgh | Wallkill | Ulster | 12589 | G | 5041 | East Walden | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000 (1) | 2015-07-06 | 2015-07-16 | 8 | 2015-07-16 | [8 empty] | 350 | 350 |  |  |  |  | 2015-10-19 | 2015-10-22 |  | Y
Central Hudson |  | SolarCity | CH-06716 | Poughkeepsie | Lagrangevl |  | 12540 | G | 6053 | Todd Hill | N |  | 15 | [13 empty] | NM | N | (1) SOLAREDGE SE10000A (1) SOLAREDGE SE5000A | 2015-07-06 | 2015-07-20 | 10 | 2015-07-20 | [14 empty] | 2015-08-26 | 2015-09-02 |  | W
Central Hudson |  | SolarCity | CH-06743 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6065 | Inwood Ave | N |  | 3 | [13 empty] | NM | N | ABB PVI-3.0-OUTD | 2015-07-06 | 2015-07-10 | 4 | 2015-07-10 | [14 empty] | 2015-09-22 | 2015-09-28 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06809 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8044 | Myers Corners | N |  | 5 | [13 empty] | NM | N | ABB PVI-5000 (1) | 2015-07-22 | 2015-07-28 | 4 | 2015-07-28 | [14 empty] | 2015-09-22 | 2015-09-28 |  | Y
Central Hudson |  | SolarCity | CH-06853 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8094 | Fishkill Plains | N |  | 5 | [13 empty] | NM | N | ABB PVI-5000 (1) | 2015-07-06 | 2015-07-10 | 4 | 2015-07-10 | [14 empty] | 2015-08-26 | 2015-09-02 |  | Y
Central Hudson |  | SolarCity | CH-07213 | Kingston | Kingston | Ulster | 12401 | G | 2017 | Lincoln Park | N |  | 3 | [13 empty] | NM | N | ABB PVI-3.0-OUTD-S US | 2015-07-06 | 2015-07-14 | 6 | 2015-07-14 | [14 empty] | 2015-10-09 | 2015-10-16 |  | Y
Central Hudson |  | SolarCity | CH-07313 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6093 | Manchester | N |  | 5 | [13 empty] | NM | N | ABB PVI-5000-OUTD | 2015-07-06 | 2015-07-10 | 4 | 2015-07-10 | [14 empty] | 2015-09-02 | 2015-09-10 |  | Y
Central Hudson |  | SolarCity | CH-07354 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8095 | Fishkill Plains | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2015-07-06 | 2015-07-10 | 4 | 2015-07-10 | [14 empty] | 2015-08-12 | 2015-08-19 |  | Y
Central Hudson |  | SolarCity | CH-07483 | Newburgh | New Windsor | Orange | 12553 | G | 4095 | Bethlehem Rd | N |  | 3 | [13 empty] | NM | N | ABB PVI-3.0 (1) | 2015-07-06 | 2015-07-13 | 5 | 2015-07-13 | [14 empty] | 2015-08-03 | 2015-08-07 |  | Y
Central Hudson |  | Solar Generation | CH-08193 | Kingston | Woodstock | Ulster | 12498 | G | 3014 | Woodstock | N |  | 10 | [13 empty] | NM | N | SMA SB 5000 (2) | 2015-07-06 | 2015-07-15 | 7 | 2015-07-15 | [14 empty] | 2016-04-13 | 2016-04-19 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-03447 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6091 | Manchester | N | CH-03447 | 6 | [13 empty] | NM | N | SUNNYBOY SPR-6000TL-US | 2015-07-15 | 2015-07-20 | 3 | 2015-07-20 | [14 empty] | 2015-09-16 | 2015-09-23 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-03489 | Newburgh | Rock Tavern | Orange | 12575 | G | 4097 | Bethlehem Rd | N |  | 7 | [13 empty] | NM | N | SMA SB7000 (1) | 2015-07-07 | 2015-07-13 | 4 | 2015-07-13 | [14 empty] | 2016-02-17 | 2016-02-24 |  | Y
Central Hudson |  | Apex Solar Power | CH-00681 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7055 | Rhinebeck | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000 | 2015-07-28 | 2015-08-04 | 5 | 2015-08-04 | [14 empty] | 2016-03-21 | 2016-03-29 |  | Y
Central Hudson |  | SolarCity | CH-05748 | Kingston | Kingston | Ulster | 12401 | G | 2016 | Lincoln Park | Y | CH-05748 | 7.2 | [13 empty] | NM | N | 2 ABB PVI-3.6-OUTD-S US | 2015-07-07 | 2015-07-15 | 6 | 2015-07-15 | [14 empty] | 2015-07-31 | 2015-08-07 |  | Y
Central Hudson |  | New York State Solar Farm | CH-04042 | Newburgh | Milton | Ulster | 12547 | G | 5003 | Marlboro | N |  | 8.4 | [13 empty] | NM | N | ABB POWERONE PVI 4.2 (2) | 2015-07-14 | 2015-07-20 | 4 | 2015-07-20 | [14 empty] | 2015-07-27 | 2015-08-03 |  | Y
Central Hudson |  | SolarCity | CH-04927 | Catskill | Greenvl | Greene | 12083 | G | 2071 | Freehold | N |  | 7.2 | [13 empty] | NM | N | (2) ABB PVI-3.6-OUTD-S US | 2015-07-08 | 2015-07-15 | 5 | 2015-07-15 | [14 empty] | 2015-07-31 | 2015-08-04 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-04991 | Kingston | Napanoch | Ulster | 12458 | G | 3071 | Honk Falls | N |  | 264 | [13 empty] | NM | N | (11) Fronius Symo 24.0-3 | 2015-09-24 | 2015-10-15 | 15 | 2015-10-15 | 2015-09-24 | 2015-10-15 | 15 | [11 empty] | 2016-01-07 | 2016-01-14 |  | Y
Central Hudson |  | SolarCity | CH-05101 | Poughkeepsie | Pine Plns | Dutchess | 12567 | G | 7091 | Pulvers Corners | N |  | 5 | [13 empty] | NM | N | ABB PVI-5000-OUTD | 2015-07-08 | 2015-07-15 | 5 | 2015-07-15 | [14 empty] | 2015-08-03 | 2015-08-07 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-05133 | Newburgh | Newburgh | Orange | 12550 | G | 4024 | Coldenham | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 (1) | 2015-07-08 | 2015-07-14 | 4 | 2015-07-14 | [14 empty] | 2015-09-22 | 2015-09-29 |  | Y
Central Hudson |  | SolarCity | CH-05520 | Catskill | Cairo | Greene | 12413 | G | 2043 | South Cairo | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000-OUTD-US | 2015-07-08 | 2015-07-15 | 5 | 2015-07-15 | [14 empty] | 2015-10-09 | 2015-10-16 |  | Y
Central Hudson |  | SolarCity | CH-06203 | Newburgh | Walden | Orange | 12586 | G | 5041 | East Walden | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000 (1) | 2015-07-08 | 2015-07-14 | 4 | 2015-07-14 | [14 empty] | 2015-08-24 | 2015-08-31 |  | Y
Central Hudson |  | SolarCity | CH-06379 | Newburgh | New Windsor | Orange | 12553 | G | 4095 | Bethlehem Rd | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000 (1) | 2015-07-08 | 2015-07-14 | 4 | 2015-07-14 | [14 empty] | 2015-08-03 | 2015-08-07 |  | Y
Central Hudson |  | SolarCity | CH-06543 | Kingston | Kingston | Ulster | 12401 | G | 2093 | Hurley Ave | N |  | 22.08 | [13 empty] | NM | N | 3 FRONIUS PRIMO 7.6 US | 2015-07-08 | 2015-07-15 | 5 | 2015-07-15 | [14 empty] | 2015-08-17 | 2015-08-24 |  | Y
Central Hudson |  | SolarCity | CH-06724 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 7024 | Tinkertown | N |  | 3.6 | [13 empty] | NM | N | ABB PVI-3.6-OUTD-S | 2015-07-08 | 2015-07-15 | 5 | 2015-07-15 | [14 empty] | 2015-08-18 | 2015-08-25 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Kasselman Solar | CH-03507 | Catskill | Westerlo | Albany | 12193 | G | 1091 | Westerlo | N | CH-03507 | 8 | [13 empty] | NM | N | 32 ENPHASE M250 US | 2015-07-09 | 2015-07-17 | 6 | 2015-07-17 | [14 empty] | 2015-09-28 | 2015-10-05 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03633 | Newburgh | Walden | Orange | 12586 | G | 5041 | East Walden | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE 7600 (1) | 2015-07-15 | 2015-07-21 | 4 | 2015-07-21 | [14 empty] | 2015-08-10 | 2015-08-17 |  | Y
Central Hudson |  | New York State Solar Farm | CH-04053 | Newburgh | Wallkill | Ulster | 12589 | G | 5011 | Modena | N |  | 8.8 | [13 empty] | NM | N | SMA AMERICA 5.0 (1) SMA AMERICA 3.8 (1) | 2015-07-23 | 2015-07-23 | 0 | 2015-07-23 | [14 empty] | 2015-08-04 | 2015-08-04 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-05744 | Kingston | Kingston | Ulster | 12401 | G | 2016 | Lincoln Park | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000-OUTD US | 2015-07-09 | 2015-07-17 | 6 | 2015-07-17 | [14 empty] | 2015-08-10 | 2015-08-17 |  | Y
Central Hudson |  | SolarCity | CH-06924 | Fishkill | Beacon | Dutchess | 12508 | G | 8085 | Tioronda | N |  | 3 | [13 empty] | NM | N | ABB PVI-3.0 (1) | 2015-07-31 | 2015-08-07 | 5 | 2015-08-07 | [14 empty] | 2015-08-26 | 2015-09-02 |  | Y
Central Hudson |  | SolarCity | CH-06941 | Fishkill | Beacon | Dutchess | 12508 | G | 8017 | Forgebrook | N |  | 3.6 | [13 empty] | NM | N | ABB PVI-3.6 (1) | 2015-07-09 | 2015-07-15 | 4 | 2015-07-15 | [14 empty] | 2015-07-31 | 2015-08-06 |  | Y
Central Hudson |  | SolarCity | CH-07098 | Newburgh | Wallkill | Ulster | 12589 | G | 5013 | Modena | N |  | 10 | [13 empty] | NM | N | SOLAREDGE SE10000A (1) | 2015-07-22 | 2015-07-23 | 1 | 2015-07-23 | [14 empty] | 2015-08-11 | 2015-08-18 |  | Y
Central Hudson |  | SolarCity | CH-07123 | Newburgh | Cornwall | Orange | 12518 | G | 4041 | Union Ave | N |  | 5 | [13 empty] | NM | N | ABB PVI-5000 (1) | 2015-07-09 | 2015-07-15 | 4 | 2015-07-15 | [14 empty] | 2015-11-06 | 2015-11-06 |  | Y
Central Hudson |  | Solar Generation | CH-08239 | Kingston | Woodstock | Ulster | 12498 | G | 3012 | Woodstock | N |  | 27 | [13 empty] | NM | N | 3 SOLAREDGE SE9K-US | 2015-07-09 | 2015-07-17 | 6 | 2015-07-17 | [14 empty] | 2015-11-05 | 2015-11-05 |  | Y
Central Hudson |  | Solar Generation | CH-08284 | Kingston | Woodstock | Ulster | 12498 | G | 3012 | Woodstock | N |  | 7 | [13 empty] | NM | N | SMA SB 7000 TL | 2015-07-09 | 2015-07-17 | 6 | 2015-07-17 | [14 empty] | 2015-09-29 | 2015-10-06 |  | Y
Central Hudson |  | Sol Providers | CH-08904 | Newburgh | Marlboro | Ulster | 12542 | G | 5003 | Marlboro | N |  | 12 | [13 empty] | NM | N | sma sb 6000 (2) | 2015-08-04 | 2015-08-12 | 6 | 2015-08-12 | [14 empty] | 2015-08-24 | 2015-08-31 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Lighthouse Solar | CH-03670 | Poughkeepsie | Millbrook | Dutchess | 12545 | G | 7012 | Hibernia | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE 7600A-US | 2015-07-21 | 2015-07-22 | 1 | 2015-07-22 | [14 empty] | 2015-08-28 | 2015-09-04 |  | Y
Central Hudson |  | SolarCity | CH-05021 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7053 | Rhinebeck | N |  | 8.4 | [13 empty] | NM | N | (2) ABB PVI-4.2-OUTD | 2015-07-10 | 2015-07-17 | 5 | 2015-07-17 | [14 empty] | 2015-08-17 | 2015-08-24 |  | Y
Central Hudson |  | SolarCity | CH-05478 | Newburgh | Newburgh | Orange | 12550 | G | 4051 | Union Ave | N |  | 3.6 | [13 empty] | NM | N | ABB PVI-3.6 (1) | 2015-07-10 | 2015-07-16 | 4 | 2015-07-16 | [14 empty] | 2015-09-21 | 2015-09-28 |  | Y
Central Hudson |  | SolarCity | CH-05654 | Kingston | Kingston | Ulster | 12401 | G | 2013 | Lincoln Park | N |  | 11.4 | [13 empty] | NM | N | SOLAREDGE SE11400A US | 2015-07-10 | 2015-07-17 | 5 | 2015-07-17 | [14 empty] | 2015-08-11 | 2015-08-18 |  | Y
Central Hudson |  | SolarCity | CH-06057 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8095 | Fishkill Plains | N |  | 3 | [13 empty] | NM | N | ABB PVI-3.0 (1) | 2015-07-10 | 2015-07-16 | 4 | 2015-07-16 | [14 empty] | 2015-08-31 | 2015-09-08 |  | Y
Central Hudson |  | SolarCity | CH-07134 | Newburgh | Rock Tvrn | Orange | 12575 | G | 4097 | Bethlehem Rd | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000 (1) | 2015-07-10 | 2015-07-16 | 4 | 2015-07-16 | [14 empty] | 2015-08-26 | 2015-09-02 |  | Y
Central Hudson |  | Sungevity Inc | CH-09331 | Poughkeepsie | Tivoli | Dutchess | 12583 | G | 7062 | Milan | N |  | 3.8 | [13 empty] | NM | N | ABB PVI-3.8-OUTD | 2015-07-13 | 2015-07-20 | 5 | 2015-07-20 | [14 empty] | 2015-09-03 | 2015-09-10 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-03472 | Newburgh | Washingtonvl | Orange | 10992 | G | 4097 | Bethlehem Rd | N |  | 10 | [13 empty] | NM | N | Fronius IG Plus 10.0 | 2015-07-14 | 2015-07-20 | 4 | 2015-07-20 | [14 empty] | 2015-11-02 | 2015-11-06 |  | Y
Central Hudson |  | NRG Home Solar | CH-04231 | Catskill | Catskill |  | 12414 | G | 2001 | North Catskill | TBD |  | 3.66 | [13 empty] | NM | N | 17 ENPHASE M215-60-2LL-S22-IG | 2015-07-14 | 2015-07-22 | 6 | 2015-07-22 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | Direct Energy Solar | CH-00892 | Catskill | W Coxsackie | Greene | 12192 | G | 1071 | Coxsackie | N |  | 8.17 | [13 empty] | NM | N | 38 ENPHASE M215 60-2LL-S22 | 2015-07-14 | 2015-07-22 | 6 | 2015-07-22 | [14 empty] | 2015-08-18 | 2015-08-18 |  | Y
Central Hudson |  | Verengo Solar | CH-09764 | Kingston | Saugerties | Ulster | 12477 | G | 3002 | Saugerties | N |  | 8.17 | [13 empty] | NM | N | 38 ENPHASE M215-60-2LL-S22-IG | 2015-07-14 | 2015-07-14 | 0 | 2015-07-14 | [14 empty] | 2015-07-28 | 2015-08-04 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-05899 | Poughkeepsie | Clinton Cors | Dutchess | 12514 | G | 7013 | Hibernia | N | CH-05899 | 10 | [13 empty] | NM | N | (2) ABB PVI-5000-OUTD-US | 2015-07-15 | 2015-07-21 | 4 | 2015-07-21 | [14 empty] | 2016-03-31 | 2016-04-07 |  | Y
Central Hudson |  | SolarCity | CH-06017 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8094 | Fishkill Plains | N |  | 22.8 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 (3) | 2015-09-11 | 2015-09-17 | 4 | 2015-09-17 | [14 empty] | 2015-10-19 | 2015-10-22 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06742 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6093 | Manchester | N |  | 3 | [13 empty] | NM | N | ABB PVI-3.0-OUTD-S-US | 2015-07-15 | 2015-07-21 | 4 | 2015-07-21 | [14 empty] | 2015-08-26 | 2015-09-02 |  | Y
Central Hudson |  | SolarCity | CH-07892 | Fishkill | Fishkill |  | 12524 | G | 8065 | Merritt Park | TBD |  | 6 | [13 empty] | NM | N | ABB PVI-6000 (1) | 2015-07-15 | 2015-07-21 | 4 | 2015-07-21 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | New York State Solar Farm | CH-03972 | Kingston | Kingston | Ulster | 12401 | G | 1011 | Boulevard | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE 5.0 | 2015-07-16 | 2015-07-28 | 8 | 2015-07-28 | [14 empty] | 2015-08-24 | 2015-08-27 |  | Y
Central Hudson |  | Apex Solar Power | CH-00699 | Catskill | Cairo | Greene | 12413 | G | 2041 | South Cairo | N |  | 10.6 | [13 empty] | NM | N | SOLAREDGE SE7600 A-US SOLAREDGE SE3000 A-US | 2015-07-16 | 2015-07-28 | 8 | 2015-07-28 | [14 empty] | 2015-08-26 | 2015-09-01 |  | Y
Central Hudson |  | Hudson Solar | CH-01561 | Fishkill | Fishkill | Dutchess | 12524 | G | 8012 | Forgebrook | N |  | 10.8 | [13 empty] | NM | N | SMA AMERICA SB3800 (1) SMA AMERICA SB7000 (1) | 2015-07-16 | 2015-07-22 | 4 | 2015-07-22 | [14 empty] | 2015-10-09 | 2015-10-14 |  | Y
Central Hudson |  | Hudson Solar | CH-02026 | Kingston | Kingston | Ulster | 12401 | G | 1012 | Boulevard | N |  | 6 | [13 empty] | NM | N | SMA AMERICA SB6000 TL-US-22 | 2015-07-16 | 2015-07-28 | 8 | 2015-07-28 | [14 empty] | 2015-10-13 | 2015-10-16 |  | Y
Central Hudson |  | Hudson Solar | CH-02327 | Newburgh | Wallkill | Ulster | 12589 | G | 5043 | East Walden | N |  | 6 | [13 empty] | NM | N | SMA AMERICA SB6000 (1) | 2015-07-16 | 2015-07-22 | 4 | 2015-07-22 | [14 empty] | 2015-09-30 | 2015-10-07 |  | Y
Central Hudson |  | Hudson Solar | CH-02356 | Fishkill | Cold Spg | Putnam | 10516 | G | 8087 | Tioronda | N |  | 6 | [13 empty] | NM | N | SMA AMERICA SB3000 (2) | 2015-07-16 | 2015-07-22 | 4 | 2015-07-22 | [14 empty] | 2015-11-05 | 2015-11-06 |  | Y
Central Hudson |  | SolarCity | CH-06867 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8092 | Fishkill Plains | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000 (1) | 2015-10-01 | 2015-10-08 | 5 | 2015-10-08 | [14 empty] | 2015-10-12 | 2015-10-15 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Infinity Solar Systems | CH-03378 | Newburgh | Newburgh | Orange | 12550 | G | 4023 | Coldenham | N |  | 5 | [13 empty] | NM | N | SB 5000 (1) | 2015-07-17 | 2015-07-23 | 4 | 2015-07-23 | [14 empty] | 2015-11-18 | 2015-11-23 |  | Y
Central Hudson |  | NRG Home Solar | CH-04217 | Newburgh | Newburgh | Orange | 12550 | G | 4011 | West Balmville | N |  | 3 | [13 empty] | NM | N | ENPHASE M-250 (12) | 2015-07-17 | 2015-07-23 | 4 | 2015-07-23 | [14 empty] | 2015-10-13 | 2015-10-20 |  | Y
Central Hudson |  | NRG Home Solar | CH-04286 | Kingston | Saugerties | Ulster | 12477 | G | 3002 | Saugerties | N |  | 5 | [13 empty] | NM | N | 20 ENPHASE M-250-60-2LL-S22 | 2015-07-17 | 2015-07-27 | 6 | 2015-07-27 | [14 empty] | 2015-09-01 | 2015-09-16 |  | Y
Central Hudson |  | NRG Home Solar | CH-04291 | Kingston | Saugerties | Ulster | 12477 | G | 3001 | Saugerties | N |  | 7 | [13 empty] | NM | N | 28 ENPHASE M-250-60-2LL-S22 | 2015-07-17 | 2015-07-27 | 6 | 2015-07-27 | [14 empty] | 2015-10-30 | 2015-11-06 |  | Y
Central Hudson |  | NRG Home Solar | CH-04313 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6042 | Spackenkill | N |  | 6.25 | [13 empty] | NM | N | (25) ENPHASE ENERGY M-250 | 2015-07-17 | 2015-07-22 | 3 | 2015-07-22 | [14 empty] | 2015-10-13 | 2015-10-20 |  | Y
Central Hudson |  | NRG Home Solar | CH-04322 | Poughkeepsie | Staatsburg |  | 12580 | G | 7041 | Staatsburg | TBD |  | 6.25 | [13 empty] | NM | N | (25) ENPHASE ENERGY M-250 | 2015-07-17 | 2015-07-22 | 3 | 2015-07-22 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | NRG Home Solar | CH-04430 | Fishkill | Stormvl | Dutchess | 12582 | G | 8071 | Shenandoah | N |  | 3.75 | [13 empty] | NM | N | ENPHASE ENERGY M-250 (15) | 2015-07-17 | 2015-07-23 | 4 | 2015-07-23 | [14 empty] | 2015-10-13 | 2015-10-15 |  | Y
Central Hudson |  | NRG Home Solar | CH-04628 | Newburgh | New Paltz | Ulster | 12561 | G | 5021 | Ohioville | N |  | 8 | [13 empty] | NM | N | ENPHASE ENERGY M-250 (32) | 2015-07-17 | 2015-07-23 | 4 | 2015-07-23 | [14 empty] | 2015-10-07 | 2015-10-12 |  | Y
Central Hudson |  | SolarCity | CH-05542 | Catskill | Coxsackie | Greene | 12051 | G | 1071 | Coxsackie | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000-OUTD-US | 2015-07-17 | 2015-07-27 | 6 | 2015-07-27 | [14 empty] | 2015-09-30 | 2015-10-07 |  | Y
Central Hudson |  | SolarCity | CH-06311 | Newburgh | Newburgh | Orange | 12550 | G | 4011 | West Balmville | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000 (1) | 2015-07-17 | 2015-07-23 | 4 | 2015-07-23 | [14 empty] | 2015-08-13 | 2015-08-20 |  | Y
Central Hudson |  | Self | CH-08883 | Kingston | Grahamsville |  | 12740 | G | 3091 | Neversink | TBD |  | 7.7 | [13 empty] | NM | N | SOLECTRA PVI 7600 TL | 2015-07-17 | 2015-07-27 | 6 | 2015-07-27 | [17 empty] | W
Central Hudson |  | American Solar Partners | CH-03074 | Kingston | Accord | Ulster | 12404 | G | 3081 | Kerhonkson | N |  | 11.4 | [13 empty] | NM | N | SOLAR EDGE SE11400 US | 2015-07-20 | 2015-07-27 | 5 | 2015-07-27 | [8 empty] | 350 | 350 |  | 2015-08-12 | 2015-08-12 | 2015-08-17 | 2015-09-03 | 2015-09-09 |  | Y
Central Hudson |  | Kasselman Solar | CH-03508 | Catskill | Athens | Greene | 12015 | G | 2002 | North Catskill | N |  | 9.5 | [13 empty] | NM | N | 38 ENPHASE M-250 US | 2015-07-20 | 2015-07-27 | 5 | 2015-07-27 | [8 empty] | 350 | 350 |  | 2015-12-10 | 2015-12-10 | 2015-12-16 | 2016-06-15 | 2016-06-20 |  | Y
Central Hudson |  | Active Solar Development | CH-00631 | Catskill | W Coxsackie | Greene | 12192 | G | 1083 | New Baltimore | N |  | 5 | [13 empty] | NM | N | FRONIUS PRIMO 5.0-1 | 2015-12-09 | 2015-12-16 | 5 | 2015-12-16 | [14 empty] | 2016-04-22 | 2016-04-25 |  | Y
Central Hudson |  | Murphy Solar Power | CH-02745 | Catskill | Earlton | Greene | 12058 | G | 2005 | North Catskill | N |  | 7 | [13 empty] | NM | N | SMA 7000 SB | 2015-07-20 | 2015-07-27 | 5 | 2015-07-27 | [14 empty] | 2015-08-24 | 2015-08-27 |  | Y
Central Hudson |  | SolarCity | CH-06040 | Fishkill | Poughkeepsie | Dutchess | 12601 | G | 8021 | Knapps Corners | N |  | 6.6 | [13 empty] | NM | N | ABB PVI-3.6 (1) ABB PVI-3.0 (1) | 2015-07-20 | 2015-07-24 | 4 | 2015-07-24 | [14 empty] | 2015-08-13 | 2015-08-20 |  | Y
Central Hudson |  | SolarCity | CH-06353 | Newburgh | Wallkill | Ulster | 12589 | G | 5012 | Modena | N |  | 9.2 | [13 empty] | NM | N | ABB PVI-4.2 (1) ABB PVI-5000 (1) | 2015-07-20 | 2015-07-24 | 4 | 2015-07-24 | [8 empty] | 350 | 350 |  |  |  |  | 2015-09-04 | 2015-09-16 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Sungevity Inc | CH-09320 | Poughkeepsie | Staatsburg | Dutchess | 12580 | G | 7041 | Staatsburg | N |  | 18 | [13 empty] | NM | N | (3) ABB PVI-6000-OUTD-US-A | 2015-07-23 | 2015-07-23 | 0 | 2015-07-23 | [8 empty] | 350 | 350 |  | 2015-08-07 | 2015-08-07 | 2015-09-24 | 2015-10-01 | 2015-10-07 |  | Y
Central Hudson |  | Sunrun Inc. | CH-08333 | Newburgh | New Windsor | Orange | 12553 | G | 4045 | Union Ave | N |  | 10 | [13 empty] | NM | N | SOLAREDGE SE10000A (1) | 2015-07-24 | 2015-07-28 | 2 | 2015-07-28 | [14 empty] | 2015-09-18 | 2015-09-25 |  | Y
Central Hudson |  | American Solar Partners | CH-03076 | Newburgh | Newburgh | Orange | 12550 | G | 4027 | Coldenham | N |  | 3 | [13 empty] | NM | N | SE 3000 (1) | 2015-07-28 | 2015-08-04 | 5 | 2015-08-04 | [14 empty] | 2015-10-07 | 2015-10-12 |  | Y
Central Hudson |  | Lotus Energy Inc. | CH-03856 | Catskill | Greenvl | Greene | 12083 | G | 2071 | Freehold | N |  | 12 | [13 empty] | NM | N | 2 SMA SB6000TL-US-22 | 2015-07-22 | 2015-07-29 | 5 | 2015-07-29 | [14 empty] | 2015-09-03 | 2015-09-11 |  | Y
Central Hudson |  | Hudson Solar | CH-01619 | Catskill | Freehold | Greene | 12431 | G | 2061 | Freehold | N |  | 7 | [13 empty] | NM | N | SMA AMERICA SB7000 TL-US-22 | 2015-07-22 | 2015-07-29 | 5 | 2015-07-29 | [14 empty] | 2016-02-01 | 2016-02-08 |  | Y
Central Hudson |  | Hudson Solar | CH-02083 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 6075 | East Park | N | CH-02083 | 2 | [13 empty] | NM | N | SMA AMERICA SB2000 (1) | 2015-07-22 | 2015-07-29 | 5 | 2015-07-29 | [14 empty] | 2015-11-20 | 2015-12-01 |  | Y
Central Hudson |  | Hudson Solar | CH-02326 | Newburgh | Wallkill | Ulster | 12589 | G | 5043 | East Walden | N |  | 9 | [13 empty] | NM | N | SMA AMERICA SB5000 (1) SMA AMERICA SB4000 (1) | 2015-07-22 | 2015-07-28 | 4 | 2015-07-28 | [14 empty] | 2015-10-21 | 2015-10-23 |  | Y
Central Hudson |  | SolarCity | CH-04930 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6042 | Spackenkill | N |  | 3 | [13 empty] | NM | N | ABB PVI-3.0 (1) | 2015-07-22 | 2015-07-29 | 5 | 2015-07-29 | [14 empty] | 2015-09-14 | 2015-09-21 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07104 | Newburgh | New Paltz | Ulster | 12561 | G | 5011 | Modena | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000 (1) | 2015-07-22 | 2015-07-28 | 4 | 2015-07-28 | [14 empty] | 2015-09-30 | 2015-10-07 |  | Y
Central Hudson |  | Solar Generation | CH-08071 | Kingston | Ulster Pk | Ulster | 12487 | G | 1014 | Boulevard | N |  | 12 | [13 empty] | NM | N | 2 SMA SB 6000 TL | 2015-07-22 | 2015-07-29 | 5 | 2015-07-29 | [14 empty] | 2015-12-11 | 2015-12-18 |  | Y
Central Hudson |  | Solar Maximum LLC, dba RevoluSun | CH-09026 | Newburgh | Wallkill | Ulster | 12589 | G | 5041 | East Walden | N |  | 7.7 | [13 empty] | NM | N | sma sb7700 (1) | 2015-07-27 | 2015-08-03 | 5 | 2015-08-03 | [14 empty] | 2015-09-22 | 2015-09-28 |  | Y
Central Hudson |  | Kirchhoff Green Energy LLC | CH-03550 | Kingston | Kingston | Ulster | 12401 | G | 2015 | Lincoln Park | N |  | 49.975 | [13 empty] | NM | N | (5) Fronius 10.0 | 2015-07-23 | 2015-07-29 | 4 | 2015-07-29 | [14 empty] | 2015-10-09 | 2015-10-09 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03731 | Kingston | Accord | Ulster | 12404 | G | 3024 | High Falls | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE 7600 A-US | 2015-07-23 | 2015-08-03 | 7 | 2015-08-03 | [14 empty] | 2015-11-18 | 2015-11-25 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03772 | Newburgh | Wallkill | Ulster | 12589 | G | 5043 | East Walden | N |  | 3.8 | [13 empty] | NM | N | SOLAREDGE 3800 (1) | 2015-08-03 | 2015-08-11 | 6 | 2015-08-11 | [14 empty] | 2015-09-24 | 2015-09-30 |  | Y
Central Hudson |  | New York State Solar Farm | CH-04052 | Newburgh | New Paltz | Ulster | 12561 | G | 5012 | Modena | N |  | 12 | [13 empty] | NM | N | abb pvi 6000 (2) | 2015-07-23 | 2015-07-31 | 6 | 2015-07-31 | [14 empty] | 2015-08-06 | 2015-08-13 |  | Y
Central Hudson |  | SolarCity | CH-05994 | Fishkill | Wappingers Falls | Dutchess | 12590 | G | 8091 | Fishkill Plains | N |  | 14.4 | [13 empty] | NM | N | ABB PVI-6000 (1) ABB PVI-4.2 (2) | 2015-07-23 | 2015-07-31 | 6 | 2015-07-31 | [8 empty] | 350 | 350 |  | 2015-10-06 | 2015-10-06 | 2015-10-19 | 2015-10-19 | 2015-11-02 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06641 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6042 | Spackenkill | N |  | 5 | [13 empty] | NM | N | ABB PVI-5000 (1) | 2015-07-23 | 2015-07-31 | 6 | 2015-07-31 | [14 empty] | 2015-11-30 | 2015-12-07 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Sungevity Inc | CH-09330 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7054 | Rhinebeck | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000 (1) | 2015-07-23 | 2015-07-31 | 6 | 2015-07-31 | [14 empty] | 2015-09-02 | 2015-09-10 |  | Y
Central Hudson |  | Kasselman Solar | CH-03527 | Catskill | Freehold | Greene | 12431 | G | 2061 | Freehold | N |  | 3 | [13 empty] | NM | N | 12 ENPHASE-M250-US | 2015-07-24 | 2015-08-03 | 6 | 2015-08-03 | [14 empty] | 2015-09-28 | 2015-10-05 |  | Y
Central Hudson |  | New York State Solar Farm | CH-04007 | Newburgh | Milton | Ulster | 12547 | G | 5083 | Highland | N |  | 14 | [13 empty] | NM | N | ABB PVI 6.0 (1) ABB PVI 5.0 (1) ABB PVI 3.0 (1) | 2015-07-24 | 2015-07-31 | 5 | 2015-07-31 | [14 empty] | 2015-08-28 | 2015-09-04 |  | Y
Central Hudson |  | NRG Home Solar | CH-04483 | Newburgh | Marlboro | Ulster | 12542 | G | 5003 | Marlboro | N |  | 5.375 | [13 empty] | NM | N | ENPHASE ENGERY M215 (25) | 2015-07-24 | 2015-07-31 | 5 | 2015-07-31 | [14 empty] | 2015-10-13 | 2015-10-15 |  | Y
Central Hudson |  | SolarCity | CH-05131 | Fishkill | Beacon | Dutchess | 12508 | G | 8018 | Forgebrook | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000 (1) | 2015-07-27 | 2015-08-03 | 5 | 2015-08-03 | [14 empty] | 2015-08-26 | 2015-09-02 |  | Y
Central Hudson |  | Sol Providers | CH-08939 | Newburgh | Marlboro | Ulster | 12542 | G | 5002 | Marlboro | N |  | 6 | [13 empty] | NM | N | SMA SB 6000 (1) | 2015-08-03 | 2015-08-11 | 6 | 2015-08-11 | [14 empty] | 2015-08-24 | 2015-08-31 |  | Y
Central Hudson |  | Sungevity Inc | CH-09552 | Newburgh | Wallkill | Ulster | 12589 | G | 5043 | East Walden | N |  | 8.4 | [13 empty] | NM | N | ABB PVI-4.2 (2) | 2015-07-27 | 2015-08-03 | 5 | 2015-08-03 | [14 empty] | 2015-09-21 | 2015-09-25 |  | Y
Central Hudson |  | American Solar Partners | CH-03065 | Newburgh | New Windsor | Orange | 12553 | G | 4095 | Bethlehem Rd | N |  | 10 | [13 empty] | NM | N | sma sb 5000 (2) | 2015-07-28 | 2015-08-04 | 5 | 2015-08-04 | [14 empty] | 2015-12-10 | 2015-12-14 |  | Y
Central Hudson |  | NRG Home Solar | CH-04232 | Kingston | Saugerties |  | 12477 | G | 3002 | Saugerties | TBD |  | 16.5 | [13 empty] | NM | N | 66 ENPHASE M250602LLS22 | 2015-07-28 | 2015-08-03 | 4 | 2015-08-03 | [8 empty] | 350 | 350 | [7 empty] | W |  | Transformer upgrade required to accommodate PV installation. Utility System Upgrade Costs TBD.
Central Hudson |  | Hudson Solar | CH-01610 | Catskill | Medusa | Albany | 12120 | G | 1092 | Westerlo | N |  | 3 | [13 empty] | NM | N | SMA AMERICA SB3000 HFUS-30 | 2015-07-28 | 2015-08-03 | 4 | 2015-08-03 | [14 empty] | 2015-10-26 | 2015-10-30 |  | Y
Central Hudson |  | Hudson Solar | CH-02217 | Newburgh | Cornwall | Orange | 12518 | G | 4041 | Union Ave | N |  | 7.7 | [13 empty] | NM | N | SMA AMERICA SB7700 (1) | 2015-07-28 | 2015-08-07 | 8 | 2015-08-07 | [14 empty] | 2015-10-21 | 2015-10-23 |  | Y
Central Hudson |  | SolarCity | CH-05343 | Newburgh | New Windsor | Orange | 12553 | G | 4044 | Union Ave | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2015-07-28 | 2015-08-04 | 5 | 2015-08-04 | [14 empty] | 2015-10-20 | 2015-10-22 |  | Y
Central Hudson |  | SolarCity | CH-05978 | Newburgh | Highland | Ulster | 12528 | G | 5081 | Highland | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000-OUTD | 2015-07-28 | 2015-08-04 | 5 | 2015-08-04 | [14 empty] | 2015-12-15 | 2015-12-21 |  | Y
Central Hudson |  | SolarCity | CH-06886 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8014 | Forgebrook | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 (1) | 2015-07-28 | 2015-08-04 | 5 | 2015-08-04 | [14 empty] | 2015-09-30 | 2015-10-07 |  | Y
Central Hudson |  | SolarCity | CH-06907 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8071 | Shenandoah | N |  | 5 | [13 empty] | NM | N | ABB PVI-5000 (1) | 2015-07-28 | 2015-08-04 | 5 | 2015-08-04 | [14 empty] | 2015-08-26 | 2015-09-02 |  | Y
Central Hudson |  | SolarCity | CH-07072 | Newburgh | Marlboro |  | 12542 | G | 5003 | Marlboro | TBD |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2015-07-28 | 2015-08-04 | 5 | 2015-08-04 | [17 empty] | W
Central Hudson |  | Sungevity Inc | CH-09315 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6065 | Inwood Ave | N |  | 3.8 | [13 empty] | NM | N | SMA AMERICA SB3800-TL-US-22 | 2015-07-28 | 2015-08-04 | 5 | 2015-08-04 | [14 empty] | 2015-09-29 | 2015-10-06 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03624 | Kingston | High Fls | Ulster | 12440 | G | 3022 | High Falls | N |  | 15.2 | [13 empty] | NM | N | 2 SOLAREDGE 7600 A-US | 2015-07-29 | 2015-08-07 | 7 | 2015-08-07 | [8 empty] | 350 | 350 |  | 2015-09-03 | 2015-09-03 | 2015-10-05 | 2015-10-05 | 2015-10-09 |  | Y
Central Hudson |  | New York State Solar Farm | CH-03973 | Kingston | Kingston | Ulster | 12401 | G | 1024 | East Kingston | N |  | 37.8 | [13 empty] | NM | N | 3 SOLAREDGE SE 7.6 3 SOLAREDGE SE 5.0 | 2015-09-01 | 2015-09-01 | 0 | 2015-09-01 | [8 empty] | 350 | 350 |  | 2015-09-24 | 2015-09-24 | 2016-01-08 | 2015-10-01 | 2015-10-08 |  | Y
Central Hudson |  | New York State Solar Farm | CH-04071 | Kingston | Stone Ridge |  | 12484 | G | 3023 | High Falls | TBD |  | 8 | [13 empty] | NM | N | SMA SB 5.0 SMA SB 3.8 | 2015-07-29 | 2015-08-06 | 6 | 2015-08-06 | [17 empty] | W
Central Hudson |  | NRG Home Solar | CH-04357 | Poughkeepsie | Red Hook |  | 12571 | G | 7051 | Rhinebeck | TBD |  | 6.45 | [13 empty] | NM | N | (30) ENPHASE ENGERY M215-60-2LL-S22-IG | 2015-07-29 | 2015-08-05 | 5 | 2015-08-05 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | NRG Home Solar | CH-04402 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8094 | Fishkill Plains | N |  | 5 | [13 empty] | NM | N | ENPHASE ENGERY M250 (20) | 2015-07-29 | 2015-08-05 | 5 | 2015-08-05 | [14 empty] | 2015-10-08 | 2015-10-13 |  | Y
Central Hudson |  | NRG Home Solar | CH-04549 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6042 | Spackenkill | N |  | 6 | [13 empty] | NM | N | (24) ENPHASE ENGERY M250-60-2LL-S22 | 2015-07-29 | 2015-08-05 | 5 | 2015-08-05 | [14 empty] | 2015-10-13 | 2015-10-20 |  | Y
Central Hudson |  | NRG Home Solar | CH-04727 | Fishkill | Beacon | Dutchess | 12508 | G | 8015 | Forgebrook | N |  | 5.5 | [13 empty] | NM | N | ENPHASE ENGERY M250 (22) | 2015-07-29 | 2015-08-05 | 5 | 2015-08-05 | [14 empty] | 2016-02-01 | 2016-02-01 |  | Y
Central Hudson |  | NRG Home Solar | CH-04809 | Kingston | Accord |  | 12404 | G | 3081 | Kerhonkson | TBD |  | 7 | [13 empty] | NM | N | 28 ENPHASE M250-60-2LL-S22 | 2015-07-29 | 2015-08-06 | 6 | 2015-08-06 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | Direct Energy Solar | CH-00844 | Kingston | Woodstock | Ulster | 12498 | G | 3014 | Woodstock | N |  | 4.09 | [13 empty] | NM | N | 19 ENPHASE M215 60-2LL-S22 | 2015-07-29 | 2015-08-10 | 8 | 2015-08-10 | [14 empty] | 2015-10-08 | 2015-10-15 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00948 | Poughkeepsie | Pine Plns | Dutchess | 12567 | G | 7091 | Pulvers Corners | N |  | 4.3 | [13 empty] | NM | N | (20) ENPHASE M215 | 2015-07-29 | 2015-08-12 | 10 | 2015-08-12 | [14 empty] | 2015-10-28 | 2015-11-04 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00978 | Newburgh | Montgomery | Orange | 12549 | G | 5073 | Montgomery | N |  | 6.88 | [13 empty] | NM | N | ENPHASE M215 (32) | 2015-07-29 | 2015-08-05 | 5 | 2015-08-05 | [14 empty] | 2015-10-14 | 2015-10-20 |  | Y
Central Hudson |  | Monolith Solar Associates LLC | CH-02651 | Catskill | Round Top | Greene | 12473 | G | 2042 | South Cairo | N |  | 6 | [13 empty] | NM | N | SMA 6000 TL-22 | 2015-07-29 | 2015-08-10 | 8 | 2015-08-10 | [14 empty] | 2015-11-24 | 2015-12-07 |  | Y
Central Hudson |  | Solar Generation | CH-08175 | Kingston | Mt Tremper | Ulster | 12457 | G | 3012 | Woodstock | N | CH-08175 | 10 | [13 empty] | NM | N | SE10000A-US | 2015-07-29 | 2015-08-10 | 8 | 2015-08-10 | [14 empty] | 2015-09-28 | 2015-10-05 |  | Y
Central Hudson |  | Apex Solar Power | CH-03083 | Catskill | Catskill | Greene | 12414 | G | 2002 | North Catskill | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A-US | 2015-07-30 | 2015-08-10 | 7 | 2015-08-10 | [14 empty] | 2015-10-06 | 2015-10-13 |  | Y
Central Hudson |  | Apex Solar Power | CH-00717 | Newburgh | Newburgh |  | 12550 | G | 4024 | Coldenham | TBD |  | 9.8 | [13 empty] | NM | N | SE 6000 (1) SE 3800 (1) | 2015-08-06 | 2015-08-14 | 6 | 2015-08-14 | [17 empty] | W
Central Hudson |  | SolarCity | CH-05477 | Newburgh | Highland | Ulster | 12528 | G | 5081 | Highland | N |  | 8.4 | [13 empty] | NM | N | ABB PVI-4.2 (2) | 2015-07-30 | 2015-08-06 | 5 | 2015-08-06 | [14 empty] | 2015-08-28 | 2015-09-04 |  | Y
Central Hudson |  | NRG Home Solar | CH-04528 | Kingston | Napanoch | Ulster | 12458 | G | 3091 | Neversink | N |  | 2.75 | [13 empty] | NM | N | 10 ENPHASE M250-60-2LL-S22 | 2015-07-31 | 2015-08-13 | 9 | 2015-08-13 | [14 empty] | 2016-01-29 | 2016-02-05 |  | Y
Central Hudson |  | Apex Solar Power | CH-00689 | Newburgh | Campbell Hall | Orange | 10916 | G | 5051 | Maybrook | N |  | 11.4 | [13 empty] | NM | N | SE 3800 (1) SE 7600 (1) | 2015-08-06 | 2015-08-14 | 6 | 2015-08-14 | [14 empty] | 2015-11-09 | 2015-11-09 |  | Y
Central Hudson |  | SolarCity | CH-05517 | Catskill | Cairo | Greene | 12413 | G | 2043 | South Cairo | N |  | 10 | [13 empty] | NM | N | FRONIUS IG PLUS A 10 | 2015-07-31 | 2015-08-14 | 10 | 2015-08-14 | [8 empty] | 350 | 350 |  | 2015-09-01 | 2015-09-01 | 2015-09-15 | 2015-10-08 | 2015-10-15 |  | Y
Central Hudson |  | SolarCity | CH-05705 | Kingston | Kingston | Ulster | 12401 | G | 2091 | Hurley Ave | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000-OUTD-US-Z-A | 2015-07-31 | 2015-08-13 | 9 | 2015-08-13 | [14 empty] | 2015-08-26 | 2015-09-02 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-05771 | Kingston | Lk Katrine | Ulster | 12449 | G | 2011 | Lincoln Park | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A-US | 2015-07-31 | 2015-08-10 | 6 | 2015-08-10 | [14 empty] | 2015-08-26 | 2015-09-02 |  | Y
Central Hudson |  | SolarCity | CH-05895 | Poughkeepsie | Lagrangevl | Dutchess | 12540 | G | 6055 | Todd Hill | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE7600A | 2015-07-31 | 2015-08-07 | 5 | 2015-08-07 | [14 empty] | 2015-08-28 | 2015-09-04 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07055 | Newburgh | Wallkill | Ulster | 12589 | G | 4011 | West Balmville | N |  | 9.2 | [13 empty] | NM | N | ABB PVI-5000 (1) ABB PVI-4.2 (1) | 2015-07-31 | 2015-08-07 | 5 | 2015-08-07 | [8 empty] | 350 | 350 |  |  |  |  | 2015-08-26 | 2015-09-02 |  | Y
Central Hudson |  | SolarCity | CH-07189 | Catskill | Coeymans Hollow | Albany | 12046 | G | 1081 | New Baltimore | N |  | 12.6 | [13 empty] | NM | N | ABB PVI-6000-OUTD-US ABB PVI-3.6-OUTD-US ABB PVI-3.0-OUTD-US | 2015-07-31 | 2015-08-10 | 6 | 2015-08-10 | [8 empty] | 350 | 350 |  | 2015-08-20 | 2015-08-20 | 2015-09-07 | 2015-09-30 | 2015-10-07 |  | Y
Central Hudson |  | SolarCity | CH-07196 | Catskill | Climax | Greene | 12042 | G | 1071 | Coxsackie | N |  | 3 | [13 empty] | NM | N | ABB PVI-3.0-OUTD-S US | 2015-07-31 | 2015-08-10 | 6 | 2015-08-10 | [14 empty] | 2015-09-03 | 2015-09-11 |  | Y
Central Hudson |  | SolarCity | CH-07619 | Newburgh | Montgomery | Orange | 12549 | G | 5072 | Montgomery | N |  | 5 | [13 empty] | NM | N | ABB PVI-5000 (1) | 2015-07-31 | 2015-08-07 | 5 | 2015-08-07 | [14 empty] | 2015-08-26 | 2015-09-02 |  | Y
Central Hudson |  | Sol Providers | CH-08919 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6093 | Manchester | N |  | 6 | [13 empty] | NM | N | (2) SMA SB3000TL-US-22 | 2015-09-21 | 2015-09-25 | 4 | 2015-09-25 | [14 empty] | 2015-10-09 | 2015-10-09 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Solar Project Solutions | CH-09037 | Catskill | Coxsackie | Greene | 12051 | G | 1071 | Coxsackie | N |  | 6 | [13 empty] | RNM | N | SMA SB 6000 (1) | 2015-07-31 | 2015-08-14 | 10 | 2015-08-14 | [14 empty] | 2015-09-30 | 2015-10-06 |  | Y
Central Hudson |  | Sungevity Inc | CH-09372 | Newburgh | Walden | Orange | 12586 | G | 5041 | East Walden | N |  | 14.4 | [13 empty] | NM | N | ABB PVI-4.2 (2) ABB PVI-6000 (1) | 2015-07-31 | 2015-08-07 | 5 | 2015-08-07 | [8 empty] | 350 | 350 |  | 2015-11-17 | 2015-11-17 | 2015-12-07 | 2015-12-07 | 2015-12-08 |  | Y
Central Hudson |  | American Solar Partners | CH-03072 | Newburgh | Montgomery | Orange | 12549 | G | 5073 | Montgomery | N |  | 7.7 | [13 empty] | NM | N | SMA SB 7700 (1) | 2015-08-03 | 2015-08-11 | 6 | 2015-08-11 | [14 empty] | 2015-09-28 | 2015-10-05 |  | Y
Central Hudson |  | NRG Home Solar | CH-04308 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6011 | Sand Dock | N |  | 5.75 | [13 empty] | NM | N | (23) ENPHASE ENGERY M250-60-2LL-S22 | 2015-08-03 | 2015-08-17 | 10 | 2015-08-17 | [14 empty] | 2015-12-10 | 2015-12-16 |  | Y
Central Hudson |  | SolarCity | CH-06025 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8054 | North Chelsea | N |  | 3.6 | [13 empty] | NM | N | ABB PVI-3.6 (1) | 2015-08-03 | 2015-08-11 | 6 | 2015-08-11 | [14 empty] | 2015-09-11 | 2015-09-18 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07152 | Newburgh | Maybrook | Orange | 12543 | G | 4026 | Coldenham | N |  | 3 | [13 empty] | NM | N | SOLAREDGE SE3000A (1) | 2015-08-03 | 2015-08-11 | 6 | 2015-08-11 | [14 empty] | 2015-09-04 | 2015-09-14 |  | Y
Central Hudson |  | SolarCity | CH-07289 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 7041 | Staatsburg | N |  | 5 | [13 empty] | NM | N | ABB PVI-5000-OUTD-US | 2015-09-16 | 2015-09-23 | 5 | 2015-09-23 | [14 empty] | 2015-09-28 | 2015-10-05 |  | Y
Central Hudson |  | SolarCity | CH-07442 | Newburgh | New Windsor | Orange | 12553 | G | 4046 | Union Ave | N |  | 5 | [13 empty] | NM | N | ABB PVI-5000 (1) | 2015-08-03 | 2015-08-11 | 6 | 2015-08-11 | [14 empty] | 2015-10-19 | 2015-10-22 |  | Y
Central Hudson |  | US Energy Concierge, Inc. | CH-09743 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8096 | Fishkill Plains | N |  | 10 | [13 empty] | NM | N | SOLAREDGE SE 10000A-US (1) | 2015-08-11 | 2015-08-18 | 5 | 2015-08-18 | [14 empty] | 2015-11-06 | 2015-11-06 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-03457 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8095 | Fishkill Plains | N |  | 7 | [13 empty] | NM | N | SMA SB 7000 (1) | 2015-08-04 | 2015-08-12 | 6 | 2015-08-12 | [14 empty] | 2015-10-27 | 2015-10-30 |  | Y
Central Hudson |  | New York State Solar Farm | CH-03984 | Poughkeepsie | Wappingrs Fls | Dutchess | 12590 | G | 6052 | Todd Hill | N |  | 9.8 | [13 empty] | NM | N | (1) SMA SB 6000TL (1) SMA SB 3800TL | 2015-08-24 | 2015-08-27 | 3 | 2015-08-27 | [14 empty] | 2015-09-24 | 2015-09-30 |  | Y
Central Hudson |  | New York State Solar Farm | CH-04093 | Kingston | Kingston | Ulster | 12401 | G | 2016 | Lincoln Park | N | CH-05750 | 9.8 | [13 empty] | NM | N | SMA AMERICA SB-TL 6.0 SMA AMERICA SB-TL 3.8 | 2015-08-04 | 2015-08-18 | 10 | 2015-08-18 | [14 empty] | 2015-08-25 | 2015-09-01 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-05112 | Newburgh | Marlboro | Ulster | 12542 | G | 5001 | Marlboro | N |  | 13.6 | [13 empty] | NM | N | SOLAREDGE SE7600A (1) SOLAREDGE SE6000A (1) | 2015-08-04 | 2015-08-12 | 6 | 2015-08-12 | [14 empty] | 2015-11-24 | 2015-11-24 |  | Y
Central Hudson |  | SolarCity | CH-05213 | Kingston | Kingston | Ulster | 12401 | G | 3021 | High Falls | N |  | 3 | [13 empty] | NM | N | ABB PVI-3.0-OUTD-S-US | 2015-08-04 | 2015-08-18 | 10 | 2015-08-18 | [14 empty] | 2015-09-29 | 2015-10-06 |  | Y
Central Hudson |  | SolarCity | CH-05292 | Newburgh | Clintondale | Ulster | 12515 | G | 5012 | Modena | N |  | 8.2 | [13 empty] | NM | N | FRONIUS PRIMO 8.2 (1) | 2015-08-04 | 2015-08-12 | 6 | 2015-08-12 | [14 empty] | 2015-10-08 | 2015-10-13 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-05353 | Kingston | Saugerties | Ulster | 12477 | G | 3002 | Saugerties | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000-OUTD-US | 2015-08-04 | 2015-08-18 | 10 | 2015-08-18 | [14 empty] | 2015-09-30 | 2015-10-07 |  | Y
Central Hudson |  | SolarCity | CH-05514 | Catskill | Acra | Greene | 12405 | G | 2043 | South Cairo | N |  | 3.6 | [13 empty] | NM | N | ABB PVI-3.6-OUTD-S-US | 2015-08-04 | 2015-08-18 | 10 | 2015-08-18 | [14 empty] | 2015-08-26 | 2015-09-02 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-05601 | Catskill | Hannacroix | Greene | 12087 | G | 1083 | New Baltimore | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2015-08-04 | 2015-08-17 | 9 | 2015-08-17 | [14 empty] | 2015-08-28 | 2015-09-04 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-05747 | Kingston | Kingston | Ulster | 12401 | G | 3014 | Woodstock | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2015-08-04 | 2015-08-18 | 10 | 2015-08-18 | [14 empty] | 2015-09-02 | 2015-09-10 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-05808 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6046 | Spackenkill | N |  | 7.2 | [13 empty] | NM | N | (2) ABB PVI-3.6-OUTD-S-US | 2015-08-04 | 2015-08-11 | 5 | 2015-08-11 | [14 empty] | 2015-09-17 | 2015-09-24 |  | Y
Central Hudson |  | SolarCity | CH-06022 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8044 | Myers Corners | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 (1) | 2015-08-04 | 2015-08-12 | 6 | 2015-08-12 | [14 empty] | 2015-10-01 | 2015-10-08 |  | Y
Central Hudson |  | SolarCity | CH-06070 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8094 | Fishkill Plains | N |  | 5 | [13 empty] | NM | N | ABB PVI-5000 (1) | 2015-08-04 | 2015-08-12 | 6 | 2015-08-12 | [14 empty] | 2015-09-14 | 2015-09-21 |  | Y
Central Hudson |  | SolarCity | CH-06209 | Newburgh | Newburgh | Orange | 12550 | G | 4024 | Coldenham | N |  | 3 | [13 empty] | NM | N | ABB PVI-3.0 (1) | 2015-08-04 | 2015-08-12 | 6 | 2015-08-12 | [14 empty] | 2015-08-28 | 2015-09-04 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06741 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6002 | Reynolds Hill | N |  | 3 | [13 empty] | NM | N | ABB PVI-3.0-OUTD-S-US | 2015-08-04 | 2015-08-11 | 5 | 2015-08-11 | [14 empty] | 2015-08-28 | 2015-09-04 |  | Y
Central Hudson |  | SolarCity | CH-07227 | Kingston | Ellenvl | Ulster | 12428 | G | 3076 | Greenfield Rd | N |  | 3 | [13 empty] | NM | N | ABB PVI-3.0-OUTD-S US | 2015-08-04 | 2015-08-17 | 9 | 2015-08-17 | [14 empty] | 2016-05-27 | 2016-07-06 |  | Y
Central Hudson |  | SolarCity | CH-07475 | Newburgh | Maybrook | Orange | 12543 | G | 4026 | Coldenham | N |  | 3 | [13 empty] | NM | N | ABB PVI-3.0 (1) | 2015-08-04 | 2015-08-12 | 6 | 2015-08-12 | [14 empty] | 2015-09-30 | 2015-10-07 |  | Y
Central Hudson |  | SolarCity | CH-07750 | Newburgh | Newburgh | Orange | 12550 | G | 4015 | West Balmville | N |  | 3.6 | [13 empty] | NM | N | ABB PVI-3.6 (1) | 2015-08-04 | 2015-08-12 | 6 | 2015-08-12 | [14 empty] | 2015-08-26 | 2015-09-02 |  | Y
Central Hudson |  | Self | CH-08892 | Kingston | Kerhonkson | Ulster | 12446 | G | 3083 | Kerhonkson | N | CH-08892 | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A-US | 2016-07-06 | 2016-07-06 | 0 | 2016-07-06 | [14 empty] | 2017-08-02 | 2017-08-03 |  | Y
Central Hudson |  | Sol Providers | CH-08941 | Newburgh | Washingtonvl | Orange | 10992 | G | 5052 | Maybrook | N |  | 6 | [13 empty] | NM | N | SMA SB6000 (1) | 2015-08-11 | 2015-08-18 | 5 | 2015-08-18 | [14 empty] | 2015-09-17 | 2015-09-24 |  | Y
Central Hudson |  | Sungevity Inc | CH-09364 | Newburgh | Gardiner | Ulster | 12525 | G | 5031 | Galeville | N |  | 7.6 | [13 empty] | NM | N | ABB PVI-3.8 (2) | 2015-08-04 | 2015-08-12 | 6 | 2015-08-12 | [14 empty] | 2015-09-29 | 2015-10-06 |  | Y
Central Hudson |  | Sungevity Inc | CH-09425 | Poughkeepsie | Poughkeepsie |  | 12601 | G | 6068 | Inwood Ave | TBD |  | 8.4 | [13 empty] | NM | N | (2) ABB PVI-4.2-OUTD-S-US-A | 2015-08-04 | 2015-08-11 | 5 | 2015-08-11 | [17 empty] | W
Central Hudson |  | American Solar Partners | CH-03073 | Newburgh | Montgomery | Orange | 12549 | G | 5073 | Montgomery | N |  | 12 | [13 empty] | NM | N | SMA SB6000 (2) | 2015-08-05 | 2015-08-13 | 6 | 2015-08-13 | [14 empty] | 2016-01-14 | 2016-01-15 |  | Y
Central Hudson |  | NRG Home Solar | CH-04615 | Fishkill | Beacon | Dutchess | 12508 | G | 8016 | Forgebrook | N |  | 5.75 | [13 empty] | NM | N | ENPHASE ENGERY M250 (23) | 2015-08-05 | 2015-08-13 | 6 | 2015-08-13 | [14 empty] | 2015-12-31 | 2016-01-25 |  | Y
Central Hudson |  | NRG Home Solar | CH-04705 | Poughkeepsie | Staatsburg | Dutchess | 12580 | G | 7042 | Staatsburg | N |  | 5.25 | [13 empty] | NM | N | (21) ENPHASE ENGERY M250-60-2LL-S22 | 2015-08-13 | 2015-08-19 | 4 | 2015-08-19 | [14 empty] | 2015-12-30 | 2016-01-07 |  | Y
Central Hudson |  | Apex Solar Power | CH-00663 | Newburgh | Newburgh | Orange | 12550 | G | 4023 | Coldenham | N |  | 11.4 | [13 empty] | NM | N | SE 7600 (1) SE 3800 (1) | 2015-08-12 | 2015-08-26 | 10 | 2015-08-26 | [14 empty] | 2015-09-25 | 2015-10-08 |  | Y
Central Hudson |  | Pure Point Energy LLC | CH-02940 | Poughkeepsie | Stanfordvl | Dutchess | 12581 | G | 7072 | Stanfordville | N |  | 18 | [13 empty] | NM | N | (2) SMA SB9000TL-US | 2015-08-18 | 2015-08-24 | 4 | 2015-08-24 | [14 empty] | 2015-12-22 | 2015-12-29 |  | Y
Central Hudson |  | SolarCity | CH-05953 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7054 | Rhinebeck | N |  | 7.2 | [13 empty] | NM | N | (2) ABB PVI-3.6-OUTD-S-US | 2015-08-05 | 2015-08-17 | 8 | 2015-08-17 | [14 empty] | 2015-08-26 | 2015-09-02 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07369 | Fishkill | Fishkill | Dutchess | 12524 | G | 8014 | Forgebrook | N |  | 8.6 | [13 empty] | NM | N | ABB PVI-3.6 (1) ABB PVI-5000 (1) | 2015-08-05 | 2015-08-13 | 6 | 2015-08-13 | [14 empty] | 2015-09-17 | 2015-09-24 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Apex Solar Power | CH-03086 | Catskill | Catskill | Greene | 12414 | G | 2004 | North Catskill | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000-US | 2015-08-06 | 2015-08-19 | 9 | 2015-08-19 | [14 empty] | 2015-11-03 | 2015-11-09 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-03410 | Fishkill | Fishkill | Dutchess | 12524 | G | 8012 | Forgebrook | N |  | 11 | [13 empty] | NM | N | SMA SB5000 (1) SMA SB6000 (1) SMA SB3000 (1) | 2015-08-06 | 2015-08-14 | 6 | 2015-08-14 | [14 empty] | 2016-02-02 | 2016-02-02 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00958 | Newburgh | New Paltz | Ulster | 12561 | G | 5021 | Ohioville | N | CH-00958 | 6.88 | [13 empty] | NM | N | ENPHASE M215 (32) | 2015-08-24 | 2015-09-08 | 10 | 2015-09-08 | [14 empty] | 2015-10-02 | 2015-10-09 |  | Y
Central Hudson |  | SolarCity | CH-05925 | Poughkeepsie | Wappingrs Fls | Dutchess | 12590 | G | 6052 | Todd Hill | N |  | 11 | [13 empty] | NM | N | (1) ABB PVI-5000-OUTD-US (1) ABB PVI-6000-OUTD-US | 2015-08-06 | 2015-08-13 | 5 | 2015-08-13 | [14 empty] | 2015-08-31 | 2015-09-08 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-05983 | Newburgh | Highland | Ulster | 12528 | G | 5084 | Highland | N |  | 3.6 | [13 empty] | NM | N | ABB PVI-3.6-OUTD-S-US-Z | 2015-08-06 | 2015-08-17 | 7 | 2015-08-17 | [14 empty] | 2015-08-26 | 2015-09-02 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06062 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8094 | Fishkill Plains | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 (1) | 2015-08-06 | 2015-08-14 | 6 | 2015-08-14 | [14 empty] | 2015-08-26 | 2015-09-02 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Lighthouse Solar | CH-03647 | Newburgh | Gardiner | Ulster | 12525 | G | 5011 | Modena | N |  | 12 | [13 empty] | NM | N | ABB PVI 6000 (2) | 2015-08-07 | 2015-08-14 | 5 | 2015-08-14 | [8 empty] | 350 | 350 |  |  |  |  | 2015-10-01 | 2015-10-08 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03656 | Kingston | Accord | Ulster | 12404 | G | 3082 | Kerhonkson | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE 7600 A-US | 2015-08-07 | 2015-08-19 | 8 | 2015-08-19 | [14 empty] | 2015-09-24 | 2015-09-30 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03735 | Newburgh | Esopus | Ulster | 12429 | G | 5084 | Highland | N |  | 3 | [13 empty] | NM | N | SOLAREDGE 3000 A-US | 2015-08-07 | 2015-08-20 | 9 | 2015-08-20 | [14 empty] | 2015-09-24 | 2015-09-30 |  | Y
Central Hudson |  | Lotus Energy Inc. | CH-03891 | Catskill | Catskill | Greene | 12414 | G | 2001 | North Catskill | N | CH-03847 | 6 | [13 empty] | NM | N | SMA SB6000 TL | 2015-08-07 | 2015-08-20 | 9 | 2015-08-20 | [8 empty] | 350 | 350 |  | 2015-11-04 | 2015-11-04 | 2015-11-23 | 2015-11-12 | 2015-11-19 |  | Y
Central Hudson |  | NRG Home Solar | CH-04254 | Kingston | Kerhonkson | Ulster | 12446 | G | 3082 | Kerhonkson | N |  | 8.75 | [13 empty] | NM | N | 35 ENPHASE M250-60-2LL-S22 | 2015-08-07 | 2015-08-21 | 10 | 2015-08-21 | [14 empty] | 2015-10-02 | 2015-10-09 |  | Y
Central Hudson |  | NRG Home Solar | CH-04278 | Kingston | Grahamsvl |  | 12740 | G | 3091 | Neversink | TBD |  | 5.5 | [13 empty] | NM | N | 22 ENPHASE M250-60-2LL-S22 | 2015-08-07 | 2015-08-21 | 10 | 2015-08-21 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | NRG Home Solar | CH-04674 | Newburgh | Cornwall | Orange | 12518 | G | 4041 | Union Ave | N |  | 7 | [13 empty] | NM | N | ENPHASE M250 (28) | 2015-08-07 | 2015-08-14 | 5 | 2015-08-14 | [14 empty] | 2016-01-11 | 2016-01-13 |  | Y
Central Hudson |  | SolarCity | CH-06967 | Newburgh | New Paltz | Ulster | 12561 | G | 5023 | Ohioville | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000 (1) | 2015-08-07 | 2015-08-14 | 5 | 2015-08-14 | [14 empty] | 2016-01-05 | 2016-01-12 |  | Y
Central Hudson |  | Apex Solar Power | CH-03082 | Newburgh | Walden |  | 12586 | G | 5041 | East Walden | TBD |  | 9.8 | [13 empty] | NM | N | SE 6000 (1) SE 3800 (1) | 2015-08-24 | 2015-09-08 | 10 | 2015-09-08 | [17 empty] | W
Central Hudson |  | Infinity Solar Systems | CH-03408 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8092 | Fishkill Plains | N |  | 6 | [13 empty] | NM | N | SMA SB 6000 (1) | 2015-08-10 | 2015-08-18 | 6 | 2015-08-18 | [14 empty] | 2015-10-27 | 2015-10-30 |  | Y
Central Hudson |  | NRG Home Solar | CH-04366 | Poughkeepsie | Pine Plns |  | 12567 | G | 7091 | Pulvers Corners | TBD |  | 5 | [13 empty] | NM | N | SOLAR EDGE SE5000A-US | 2015-08-18 | 2015-08-24 | 4 | 2015-08-24 | [17 empty] | W
Central Hudson |  | Apex Solar Power | CH-00668 | Newburgh | Newburgh |  | 12550 | G | 4014 | West Balmville | TBD |  | 6 | [13 empty] | NM | N | SolarEdge SE6000 | 2015-08-24 | 2015-09-08 | 10 | 2015-09-08 | [17 empty] | W |  | 9/7/15 Company Holiday. 9/18 - Customer advised meter rep; to cancel meter change that they are no longer installing solar.
Central Hudson |  | Hudson Solar | CH-01679 | Kingston | Accord | Ulster | 12404 | G | 3024 | High Falls | N |  | 3.8 | [13 empty] | NM | N | SMA AMERICA SB3800 TL-US-22 | 2015-08-10 | 2015-08-21 | 9 | 2015-08-21 | [14 empty] | 2015-12-09 | 2015-12-16 |  | Y
Central Hudson |  | Hudson Solar | CH-02068 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6003 | Reynolds Hill | N |  | 8 | [13 empty] | NM | N | (1) SMA AMERICA SB3000TL-US (1) SMA AMERICA SB5000TL-US | 2015-08-10 | 2015-08-17 | 5 | 2015-08-17 | [14 empty] | 2015-11-13 | 2015-11-19 |  | Y
Central Hudson |  | Hudson Solar | CH-02204 | Newburgh | Marlboro | Ulster | 12542 | G | 5003 | Marlboro | N |  | 7.6 | [13 empty] | NM | N | SMA AMERICA SB3800 (2) | 2015-08-10 | 2015-08-18 | 6 | 2015-08-18 | [14 empty] | 2015-11-09 | 2015-11-09 |  | Y
Central Hudson |  | SolarCity | CH-06103 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8014 | Forgebrook | N |  | 11.4 | [13 empty] | NM | N | FRONIUS IG PLUS A 11.4 (1) | 2015-08-10 | 2015-08-18 | 6 | 2015-08-18 | [14 empty] | 2015-10-12 | 2015-10-15 |  | Y
Central Hudson |  | SolarCity | CH-06400 | Newburgh | Salisbury Mls | Orange | 12577 | G | 4095 | Bethlehem Rd | N |  | 5 | [13 empty] | NM | N | ABB PVI-5000 (1) | 2015-08-10 | 2015-08-18 | 6 | 2015-08-18 | [14 empty] | 2015-09-08 | 2015-09-15 |  | Y
Central Hudson |  | SolarCity | CH-07004 | Newburgh | Newburgh | Orange | 12550 | G | 4012 | West Balmville | N |  | 6 | [13 empty] | NM | N | ABB PVI-3.0 (2) | 2015-08-10 | 2015-08-18 | 6 | 2015-08-18 | [14 empty] | 2015-11-03 | 2015-11-05 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Apex Solar Power | CH-00661 | Newburgh | Walden | Orange | 12586 | G | 5041 | East Walden | N |  | 11.4 | [13 empty] | NM | N | SOLAREDGE SE7600 (1) SOLAREDGE SE3800 (1) | 2015-08-11 | 2015-08-18 | 5 | 2015-08-18 | [14 empty] | 2016-04-26 | 2016-04-28 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00902 | Kingston | Saugerties |  | 12477 | G | 3003 | Saugerties | TBD |  | 153.2 | [13 empty] | NM | N | (13) SOLAREDGE SE11400A-US (1) SOLAREDGE SE5000A-US | 2015-09-01 | 2015-09-23 | 15 | 2015-09-23 | 2015-09-01 | 2015-09-23 | 15 |  |  |  |  | 15500 | [9 empty] | W |  | 9/7/15 Company Holiday. CESIR determined necessary during preliminary review Section C, Step 4.
Central Hudson |  | SolarCity | CH-07088 | Newburgh | Gardiner | Ulster | 12525 | G | 5043 | East Walden | N | CH-07089 | 9 | [13 empty] | NM | N | SOLAREDGE SE6000A-US SOLAREDGE SE3000A-US | 2015-08-11 | 2015-08-12 | 1 | 2015-08-12 | [14 empty] | 2015-08-12 | 2015-08-13 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08605 | Catskill | Ravena |  | 12143 | G | 1081 | New Baltimore | TBD |  | 2.58 | [13 empty] | NM | N | 12 ENPHASE M215-60-2LL-S2-XZC | 2015-08-11 | 2015-08-21 | 8 | 2015-08-21 | [8 empty] | 350 | 350 | [7 empty] | W |  | Customer already had net meter prior to application. 8/27/15 - As per contractor, this customer has canceled this project and will no longer be getting solar.
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08828 | Catskill | Cornwallville |  | 12418 | G | 2043 | South Cairo | TBD |  | 6.45 | [13 empty] | NM | N | 30 ENPHASE M215-60-2LL-S2-XZC | 2015-08-11 | 2015-08-21 | 8 | 2015-08-21 | [17 empty] | W
Central Hudson |  | Lighthouse Solar | CH-03712 | Newburgh | Newburgh | Orange | 12550 | G | 5001 | Marlboro | N |  | 16 | [13 empty] | NM | N | SOLAREDGE SE6000 (1) SOLAREDGE SE10000 (1) | 2015-08-20 | 2015-08-26 | 4 | 2015-08-26 | [14 empty] | 2015-12-21 | 2015-12-30 |  | Y
Central Hudson |  | Lotus Energy Inc. | CH-03864 | Kingston | Shady | Ulster | 12409 | G | 3012 | Woodstock | N | CH-03864 | 7.7 | [13 empty] | NM | N | SMA SB7700 TL-US-22 | 2015-08-12 | 2015-08-21 | 7 | 2015-08-21 | [14 empty] | 2015-12-01 | 2015-12-08 |  | Y
Central Hudson |  | Apex Solar Power | CH-00665 | Newburgh | Newburgh |  | 12550 | G | 4023 | Coldenham | TBD |  | 7.6 | [13 empty] | NM | N | SE 7600 (1) | 2015-08-19 | 2015-08-25 | 4 | 2015-08-25 | [17 empty] | W |  | 9/1/15 Customer cancelled solar contract.
Central Hudson |  | SolarCity | CH-05144 | Newburgh | New Windsor | Orange | 12553 | G | 4095 | Bethlehem Rd | N |  | 7.8 | [13 empty] | NM | N | ABB PVI-3.6 (1) ABB PVI-4.2 (1) | 2015-08-12 | 2015-08-19 | 5 | 2015-08-19 | [14 empty] | 2015-09-18 | 2015-09-25 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-05166 | Newburgh | Newburgh | Orange | 12550 | G | 4011 | West Balmville | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000 (1) | 2015-08-12 | 2015-08-19 | 5 | 2015-08-19 | [14 empty] | 2015-09-08 | 2015-09-15 |  | Y
Central Hudson |  | SolarCity | CH-06496 | Kingston | Hurley | Ulster | 12443 | G | 2093 | Hurley Ave | N |  | 5 | [13 empty] | NM | N | ABB PVI-5000-OUTD-US-Z-A | 2015-08-12 | 2015-08-21 | 7 | 2015-08-21 | [14 empty] | 2015-09-08 | 2015-09-15 |  | Y
Central Hudson |  | SolarCity | CH-07016 | Newburgh | New Windsor | Orange | 12553 | G | 4044 | Union Ave | N |  | 5 | [13 empty] | NM | N | ABB PVI-5000 (1) | 2015-08-12 | 2015-08-19 | 5 | 2015-08-19 | [14 empty] | 2015-11-09 | 2015-11-09 |  | Y
Central Hudson |  | SolarCity | CH-07041 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 7.2 | [13 empty] | NM | N | ABB PVI-4.2 (1) ABB PVI-3.0 (1) | 2015-08-12 | 2015-08-19 | 5 | 2015-08-19 | [14 empty] | 2015-09-08 | 2015-09-15 |  | Y
Central Hudson |  | SolarCity | CH-07389 | Fishkill | Beacon | Dutchess | 12508 | G | 8015 | Forgebrook | N |  | 3.8 | [13 empty] | NM | N | SOLAREDGE SE3800A (1) | 2015-08-21 | 2015-09-04 | 10 | 2015-09-04 | [14 empty] | 2015-09-21 | 2015-09-28 |  | Y
Central Hudson |  | Monolith Solar Associates LLC | CH-02671 | Kingston | Saugerties | Ulster | 12477 | G | 3003 | Saugerties | N |  | 7.6 | [13 empty] | NM | N | SOLAR EDGE SE7600A-US-U | 2015-08-13 | 2015-08-24 | 7 | 2015-08-24 | [14 empty] | 2015-10-27 | 2015-11-02 |  | Y
Central Hudson |  | SolarCity | CH-05291 | Newburgh | Clintondale | Ulster | 12515 | G | 5012 | Modena | N |  | 7.2 | [13 empty] | NM | N | ABB PVI-3.6 (2) | 2015-08-13 | 2015-08-21 | 6 | 2015-08-21 | [14 empty] | 2015-09-29 | 2015-10-06 |  | Y
Central Hudson |  | SolarCity | CH-05898 | Poughkeepsie | Lagrangevl | Dutchess | 12540 | G | 6055 | Todd Hill | N |  | 8.2 | [13 empty] | NM | N | (1) FRONIUS PRIMO 8.2 | 2015-08-13 | 2015-08-19 | 4 | 2015-08-19 | [14 empty] | 2015-09-24 | 2015-09-25 |  | Y
Central Hudson |  | SolarCity | CH-06086 | Fishkill | Fishkill | Dutchess | 12524 | G | 8065 | Merritt Park | N |  | 3.6 | [13 empty] | NM | N | ABB PVI-3.6 (1) | 2015-08-13 | 2015-08-21 | 6 | 2015-08-21 | [14 empty] | 2015-09-17 | 2015-09-24 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06927 | Fishkill | Beacon | Dutchess | 12508 | G | 8017 | Forgebrook | N |  | 6.6 | [13 empty] | NM | N | ABB PVI-3.6 (1) ABB PVI-3.0 (1) | 2015-08-13 | 2015-08-21 | 6 | 2015-08-21 | [14 empty] | 2015-10-26 | 2015-10-26 |  | Y
Central Hudson |  | Sungevity Inc | CH-09412 | Kingston | Kingston | Ulster | 12401 | G | 1013 | Boulevard | N |  | 5 | [13 empty] | NM | N | ABB PVI-5000-OUTD-US-A | 2015-08-13 | 2015-08-24 | 7 | 2015-08-24 | [14 empty] | 2015-11-13 | 2015-11-20 |  | Y
Central Hudson |  | NRG Home Solar | CH-04186 | Newburgh | New Windsor | Orange | 12553 | G | 4094 | Bethlehem Rd | N |  | 5.5 | [13 empty] | NM | N | ENPHASe M250 (22) | 2015-08-14 | 2015-08-21 | 5 | 2015-08-21 | [14 empty] | 2015-12-28 | 2016-01-05 |  | Y
Central Hudson |  | NRG Home Solar | CH-04314 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6097 | Manchester | N |  | 3.75 | [13 empty] | NM | N | (15) ENPHASE ENGERY M250-60-2LL-S22 | 2015-08-14 | 2015-08-21 | 5 | 2015-08-21 | [14 empty] | 2015-12-30 | 2016-01-07 |  | Y
Central Hudson |  | NRG Home Solar | CH-04362 | Poughkeepsie | Pine Plns | Dutchess | 12567 | G | 7091 | Pulvers Corners | N |  | 4.5 | [13 empty] | NM | N | (18) ENPHASE ENGERY M250-60-2LL-S22 | 2015-08-14 | 2015-08-21 | 5 | 2015-08-21 | [14 empty] | 2015-12-02 | 2015-12-08 |  | Y
Central Hudson |  | NRG Home Solar | CH-04804 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6044 | Spackenkill | N |  | 5.25 | [13 empty] | NM | N | (21) ENPHASE ENGERY M250-60-2LL-S22 | 2015-08-14 | 2015-08-21 | 5 | 2015-08-21 | [14 empty] | 2015-11-09 | 2015-11-16 |  | Y
Central Hudson |  | Apex Solar Power | CH-00670 | Newburgh | Newburgh | Orange | 12550 | G | 4051 | Union Ave | N |  | 13.6 | [13 empty] | NM | N | SE 7600 (1) SE 6000 (1) | 2015-08-14 | 2015-08-21 | 5 | 2015-08-21 | [14 empty] | 2015-10-08 | 2015-10-13 |  | Y
Central Hudson |  | Sol Providers | CH-08908 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8096 | Fishkill Plains | N |  | 10 | [13 empty] | NM | N | SMA SB 5000 (2) | 2015-08-14 | 2015-08-21 | 5 | 2015-08-21 | [14 empty] | 2015-09-25 | 2015-10-01 |  | Y
Central Hudson |  | NRG Home Solar | CH-04623 | Fishkill | Beacon | Dutchess | 12508 | G | 8085 | Tioronda | N |  | 5 | [13 empty] | NM | N | SOLAR EDGE SE5000A (1) | 2015-08-17 | 2015-08-24 | 5 | 2015-08-24 | [14 empty] | 2015-12-01 | 2015-12-01 |  | Y
Central Hudson |  | Apex Solar Power | CH-00688 | Newburgh | Marlboro | Ulster | 12542 | G | 5003 | Marlboro | N |  | 7.6 | [13 empty] | NM | N | SE 7.6 | 2015-09-08 | 2015-09-11 | 3 | 2015-09-11 | [14 empty] | 2015-10-13 | 2015-10-15 |  | Y
Central Hudson |  | Hudson Solar | CH-02404 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7052 | Rhinebeck | N |  | 7.6 | [13 empty] | NM | N | SolarEdge SE7600A-US | 2015-08-26 | 2015-09-10 | 10 | 2015-09-10 | [14 empty] | 2015-10-14 | 2015-10-23 |  | Y
Central Hudson |  | Hudson Valley Wind Energy, LLC | CH-02551 | Newburgh | Milton | Ulster | 12547 | G | 5083 | Highland | N |  | 22.8 | [13 empty] | NM | N | FRONIUS IG PLUS 11.4 (2) | 2015-08-27 | 2015-09-10 | 9 | 2015-09-10 | [8 empty] | 350 | 350 |  | 2015-10-15 | 2015-10-15 | 2015-11-12 | 2015-11-12 | 2015-11-17 |  | Y
Central Hudson |  | SolarCity | CH-07122 | Newburgh | Cornwall | Orange | 12518 | G | 4043 | Union Ave | N |  | 3 | [13 empty] | NM | N | SOLAREDGE SE3000A (1) | 2015-10-28 | 2015-10-28 | 0 | 2015-10-28 | [14 empty] | 2015-11-11 | 2015-11-11 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07142 | Newburgh | Campbell Hall | Orange | 10916 | G | 5052 | Maybrook | N |  | 15.8 | [13 empty] | NM | N | FRONIUS PRIMO 8.2 (1) FRONIUS PRIMO 7.6 (1) | 2015-10-22 | 2015-10-27 | 3 | 2015-10-27 | [14 empty] | 2015-11-05 | 2015-11-06 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Apex Solar Power | CH-03096 | Catskill | W Coxsackie |  | 12192 | G | 1071 | Coxsackie | TBD |  | 10 | [13 empty] | NM | N | SOLAREDGE SE10000 A-US | 2015-08-18 | 2015-08-24 | 4 | 2015-08-24 | [17 empty] | W
Central Hudson |  | NRG Home Solar | CH-04842 | Newburgh | Wallkill |  | 12589 | G | 5013 | Modena | TBD |  | 9 | [13 empty] | NM | N | ENPHASE M250 (36) | 2015-08-18 | 2015-08-25 | 5 | 2015-08-25 | [8 empty] | 350 | 350 | [7 empty] | W |  | Transformer upgrade required to accommodate PV installation. Utility System Upgrade Costs TBD.
Central Hudson |  | Novel Approaches | CH-02786 | Kingston | Grahamsvl | Sullivan | 12740 | G | 3091 | Neversink | N |  | 11 | [13 empty] | NM | N | SMA SB11000 TL-US | 2015-08-18 | 2015-08-24 | 4 | 2015-08-24 | [8 empty] | 350 | 350 |  |  |  |  | 2015-09-21 | 2015-09-28 |  | Y
Central Hudson |  | SolarCity | CH-05421 | Fishkill | Fishkill | Dutchess | 12524 | G | 8055 | North Chelsea | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 (1) | 2015-08-18 | 2015-08-25 | 5 | 2015-08-25 | [14 empty] | 2015-12-15 | 2015-12-15 |  | Y
Central Hudson |  | SolarCity | CH-07338 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8091 | Fishkill Plains | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE7600A (1) | 2015-08-18 | 2015-08-25 | 5 | 2015-08-25 | [14 empty] | 2015-09-04 | 2015-09-14 |  | Y
Central Hudson |  | SolarCity | CH-07586 | Fishkill | Beacon | Dutchess | 12508 | G | 8017 | Forgebrook | N |  | 3.6 | [13 empty] | NM | N | ABB PVI-3.6 (1) | 2015-08-18 | 2015-08-25 | 5 | 2015-08-25 | [14 empty] | 2015-09-30 | 2015-10-07 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Infinity Solar Systems | CH-03448 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 7041 | Staatsburg | N |  | 14 | [13 empty] | NM | N | SMA America SB7000TL-US-22 | 2015-08-25 | 2015-09-09 | 10 | 2015-09-09 | [14 empty] | 2015-12-15 | 2015-12-21 |  | Y
Central Hudson |  | Direct Energy Solar | CH-01059 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8044 | Myers Corners | N |  | 6.02 | [13 empty] | NM | N | ENPHASE M215 (28) | 2015-08-19 | 2015-08-25 | 4 | 2015-08-25 | [14 empty] | 2015-11-09 | 2015-11-09 |  | Y
Central Hudson |  | Sungevity Inc | CH-09390 | Newburgh | Campbell Hall | Orange | 10916 | G | 5051 | Maybrook | N |  | 4.2 | [13 empty] | NM | N | ABB PVI-4.2 (1) | 2015-08-19 | 2015-08-25 | 4 | 2015-08-25 | [14 empty] | 2016-01-15 | 2016-01-15 |  | Y
Central Hudson |  | Sungevity Inc | CH-09617 | Catskill | Catskill |  | 12414 | G | 2005 | North Catskill | TBD |  | 8 | [13 empty] | NM | N | ABB PVI-4.2-OUTD-S-US-A ABB PVI-3.8-OUTD-S-US-A | 2015-08-19 | 2015-08-25 | 4 | 2015-08-25 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | Apex Solar Power | CH-03081 | Catskill | Westerlo | Albany | 12193 | G | 1091 | Westerlo | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE7600A-US | 2015-08-20 | 2015-08-26 | 4 | 2015-08-26 | [14 empty] | 2015-10-12 | 2015-10-16 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-03381 | Newburgh | Marlboro | Ulster | 12542 | G | 5003 | Marlboro | N |  | 21.7 | [13 empty] | NM | N | SMA SB 7700 (1) SMA SB 7000 (2) | 2015-08-20 | 2015-09-03 | 10 | 2015-09-03 | [14 empty] | 2015-10-14 | 2015-10-20 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-03387 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8095 | Fishkill Plains | N |  | 6 | [13 empty] | NM | N | SMA SB 6000 (1) | 2015-08-26 | 2015-09-09 | 9 | 2015-09-09 | [14 empty] | 2015-10-29 | 2015-10-30 |  | Y
Central Hudson |  | SolarCity | CH-05055 | Newburgh | Gardiner | Ulster | 12525 | G | 5031 | Galeville | N |  | 10 | [13 empty] | NM | N | ABB PVI-5000 (2) | 2015-08-20 | 2015-08-26 | 4 | 2015-08-26 | [14 empty] | 2015-09-14 | 2015-09-21 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06443 | Catskill | Cairo | Greene | 12413 | G | 2041 | South Cairo | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2015-08-20 | 2015-08-27 | 5 | 2015-08-27 | [14 empty] | 2015-10-08 | 2015-10-08 |  | Y
Central Hudson |  | Sol Providers | CH-08940 | Newburgh | Rock Tvrn | Orange | 12575 | G | 4097 | Bethlehem Rd | N |  | 6 | [13 empty] | NM | N | SMA SB 6000 (1) | 2015-08-20 | 2015-08-26 | 4 | 2015-08-26 | [14 empty] | 2015-10-09 | 2015-10-14 |  | Y
Central Hudson |  | Apex Solar Power | CH-03079 | Newburgh | Wallkill | Ulster | 12589 | G | 5041 | East Walden | N |  | 9.8 | [13 empty] | NM | N | SE 3800 (1) SE 6000 (1) | 2015-08-21 | 2015-09-04 | 10 | 2015-09-04 | [8 empty] | 350 | 350 |  | 2015-11-18 | 2015-11-18 | 2015-12-07 | 2015-12-09 | 2015-12-09 |  | Y
Central Hudson |  | Apex Solar Power | CH-03085 | Newburgh | Wallkill | Ulster | 12589 | G | 5013 | Modena | N |  | 11.4 | [13 empty] | NM | N | SE 7600 (1) SE 3800 (1) | 2015-08-21 | 2015-09-04 | 10 | 2015-09-04 | [14 empty] | 2015-11-17 | 2015-11-17 |  | Y
Central Hudson |  | NRG Home Solar | CH-04333 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6056 | Todd Hill | N |  | 3.44 | [13 empty] | NM | N | (16) ENPHASE M215-60-2LL-S22-IG | 2015-08-21 | 2015-08-27 | 4 | 2015-08-27 | [14 empty] | 2015-11-13 | 2015-11-19 |  | Y
Central Hudson |  | NRG Home Solar | CH-04795 | Newburgh | Newburgh | Orange | 12550 | G | 4054 | Union Ave | N |  | 8.5 | [13 empty] | NM | N | ENPHASE M250 (34) | 2015-08-21 | 2015-09-04 | 10 | 2015-09-04 | [14 empty] | 2015-12-08 | 2015-12-08 |  | Y
Central Hudson |  | Hudson Solar | CH-02444 | Kingston | Saugerties | Ulster | 12477 | G | 3003 | Saugerties | N | CH-01227 | 20 | [13 empty] | RNM | N | SMA STP20000 TL-US | 2015-09-01 | 2015-09-16 | 10 | 2015-09-16 | [14 empty] | 2015-11-11 | 2015-11-18 |  | Y
Central Hudson |  | SolarCity | CH-05092 | Newburgh | Montgomery | Orange | 12549 | G | 5073 | Montgomery | N |  | 6 | [13 empty] | NM | N | ABB PVI-3.0 (2) | 2015-08-21 | 2015-09-04 | 10 | 2015-09-04 | [14 empty] | 2015-09-29 | 2015-10-06 |  | Y
Central Hudson |  | SolarCity | CH-05114 | Newburgh | Milton | Ulster | 12547 | G | 5003 | Marlboro | N |  | 10 | [13 empty] | NM | N | ABB PVI-5000 (2) | 2015-08-21 | 2015-09-04 | 10 | 2015-09-04 | [14 empty] | 2015-10-02 | 2015-10-09 |  | Y
Central Hudson |  | SolarCity | CH-05250 | Kingston | Ruby | Ulster | 12475 | G | 2016 | Lincoln Park | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000-OUTD-US-Z-A | 2015-08-21 | 2015-08-27 | 4 | 2015-08-27 | [14 empty] | 2015-09-14 | 2015-09-21 |  | Y
Central Hudson |  | SolarCity | CH-06053 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8091 | Fishkill Plains | N |  | 8.6 | [13 empty] | NM | N | ABB PVI-5000 (1) ABB PVI-3600 (1) | 2015-08-21 | 2015-09-04 | 10 | 2015-09-04 | [14 empty] | 2015-10-14 | 2015-10-20 |  | Y
Central Hudson |  | SolarCity | CH-06702 | Poughkeepsie | Lagrangevl | Dutchess | 12540 | G | 6053 | Todd Hill | N |  | 9.6 | [13 empty] | NM | N | (1) ABB PVI-6000-OUTD (1) ABB PVI-3.6-OUTD | 2015-08-21 | 2015-08-27 | 4 | 2015-08-27 | [14 empty] | 2015-09-14 | 2015-09-21 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06732 | Poughkeepsie | Pleasant Valley | Dutchess | 12569 | G | 7025 | Tinkertown | N |  | 10 | [13 empty] | NM | N | FRONIUS IG PLUS A 10.0 | 2015-08-21 | 2015-09-04 | 10 | 2015-09-04 | [8 empty] | 350 | 350 |  | 2015-10-06 | 2015-10-06 | 2015-10-09 | 2015-10-09 | 2015-10-13 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06931 | Fishkill | Beacon | Dutchess | 12508 | G | 8017 | Forgebrook | N |  | 3 | [13 empty] | NM | N | ABB PVI-3.0 (1) | 2015-08-21 | 2015-09-04 | 10 | 2015-09-04 | [14 empty] | 2016-01-04 | 2016-01-11 |  | Y
Central Hudson |  | SolarCity | CH-07257 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6095 | Manchester | N |  | 3 | [13 empty] | NM | N | ABB PVI-3.0-OUTD-S | 2015-08-21 | 2015-08-27 | 4 | 2015-08-27 | [14 empty] | 2015-10-01 | 2015-10-07 |  | Y
Central Hudson |  | Monolith Solar Associates LLC | CH-02659 | Catskill | Athens | Greene | 12015 | G | 2002 | North Catskill | N |  | 10 | [13 empty] | NM | N | SolarEdge SE10000-US | 2015-08-24 | 2015-09-08 | 10 | 2015-09-08 | [14 empty] | 2016-01-05 | 2016-01-11 |  | Y
Central Hudson |  | SolarCity | CH-05529 | Catskill | Rensselaervl | Albany | 12147 | G | 1092 | Westerlo | N |  | 3 | [13 empty] | NM | N | ABB PVI-3.0-OUTD-S US | 2015-08-24 | 2015-09-08 | 10 | 2015-09-08 | [14 empty] | 2015-10-26 | 2015-10-30 |  | Y
Central Hudson |  | SolarCity | CH-05775 | Kingston | Kingston | Ulster | 12401 | G | 2013 | Lincoln Park | N |  | 4.2 | [13 empty] | NM | N | ABB PVI-5000-OUTD-US (1) | 2015-08-24 | 2015-09-08 | 10 | 2015-09-08 | [14 empty] | 2016-01-14 | 2016-01-21 |  | Y
Central Hudson |  | SolarCity | CH-05901 | Poughkeepsie | Clinton Corners | Dutchess | 12514 | G | 7013 | Hibernia | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000-OUTD-US | 2015-08-24 | 2015-08-28 | 4 | 2015-08-28 | [14 empty] | 2016-03-21 | 2016-03-29 |  | Y
Central Hudson |  | SolarCity | CH-06855 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8094 | Fishkill Plains | N |  | 5 | [13 empty] | NM | N | ABB PVI-5000-OUTD | 2015-08-24 | 2015-09-08 | 10 | 2015-09-08 | [14 empty] | 2015-09-14 | 2015-09-21 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07214 | Kingston | Kingston | Ulster | 12401 | G | 1022 | East Kingston | N |  | 3.6 | [13 empty] | NM | N | ABB PVI-3.6-OUTD-S US | 2015-08-24 | 2015-09-08 | 10 | 2015-09-08 | [14 empty] | 2015-12-18 | 2015-12-29 |  | Y
Central Hudson |  | SolarCity | CH-07356 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8095 | Fishkill Plains | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000-OUTD | 2015-08-24 | 2015-09-08 | 10 | 2015-09-08 | [14 empty] | 2015-11-03 | 2015-11-05 |  | Y
Central Hudson |  | Sungevity Inc | CH-09302 | Kingston | Saugerties | Ulster | 12477 | G | 3003 | Saugerties | N |  | 7.2 | [13 empty] | NM | N | ABB PVI-3.8-OUTD-S-US-A 240 (2) | 2015-08-24 | 2015-09-08 | 10 | 2015-09-08 | [14 empty] | 2015-10-02 | 2015-10-09 |  | Y
Central Hudson |  | Sungevity Inc | CH-09327 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6056 | Todd Hill | N |  | 16.2 | [13 empty] | NM | N | (2) ABB PVI-6000-OUTD-US-A (1) ABB PVI-4.2-OUTD-S-US-A | 2015-08-24 | 2015-08-28 | 4 | 2015-08-28 | [8 empty] | 350 | 350 |  | 2015-09-30 | 2015-09-30 | 2015-10-02 | 2015-11-16 | 2015-11-18 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00966 | Newburgh | Walden | Orange | 12586 | G | 5041 | East Walden | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000 | 2015-08-25 | 2015-09-09 | 10 | 2015-09-09 | [14 empty] | 2015-11-13 | 2015-11-13 |  | Y
Central Hudson |  | Hudson Solar | CH-01825 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7052 | Rhinebeck | N |  | 8.96 | [13 empty] | NM | N | SUNPOWER X21-345-C-AC (28) | 2015-08-25 | 2015-09-01 | 5 | 2015-09-01 | [14 empty] | 2017-01-23 | 2017-01-23 |  | Y
Central Hudson |  | SolarCity | CH-04952 | Newburgh | Montgomery | Orange | 12549 | G | 5072 | Montgomery | N |  | 3.6 | [13 empty] | NM | N | ABB PVI-3.6-OUTD-S-US | 2015-08-25 | 2015-09-09 | 10 | 2015-09-09 | [14 empty] | 2015-09-29 | 2015-10-06 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07340 | Fishkill | Wappingrs Falls |  | 12590 | G | 8043 | Myers Corners | TBD |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE7600A-US | 2015-08-25 | 2015-09-09 | 10 | 2015-09-09 | [17 empty] | W |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL. 9/7/15 Company Holiday.
Central Hudson |  | Sungevity Inc | CH-09378 | Newburgh | Marlboro | Ulster | 12542 | G | 5003 | Marlboro | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000-OUTD-US-A | 2015-08-25 | 2015-09-09 | 10 | 2015-09-09 | [14 empty] | 2015-10-14 | 2015-10-20 |  | Y
Central Hudson |  | Sungevity Inc | CH-09592 | Newburgh | Newburgh | Orange | 12550 | G | 4012 | West Balmville | N |  | 5 | [13 empty] | NM | N | ABB PVI-5000 | 2015-09-22 | 2015-10-01 | 7 | 2015-10-01 | [14 empty] | 2016-01-20 | 2016-01-26 |  | Y
Central Hudson |  | SolarCity | CH-05739 | Kingston | Saugerties | Ulster | 12477 | G | 3001 | Saugerties | N |  | 4.2 | [13 empty] | NM | N | ABB PVI-4.2-OUTD-S-US | 2015-08-26 | 2015-09-10 | 10 | 2015-09-10 | [14 empty] | 2015-10-05 | 2015-10-12 |  | Y
Central Hudson |  | SolarCity | CH-07513 | Kingston | Glasco | Ulster | 12432 | G | 2015 | Lincoln Park | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000-OUTD US | 2015-08-26 | 2015-09-10 | 10 | 2015-09-10 | [14 empty] | 2015-09-17 | 2015-09-24 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07697 | Kingston | Kingston | Ulster | 12401 | G | 1021 | East Kingston | N |  | 7.2 | [13 empty] | NM | N | ABB PVI-3.6-OUTD-S-US-Z- (2) | 2015-08-26 | 2015-09-10 | 10 | 2015-09-10 | [14 empty] | 2015-09-29 | 2015-10-06 |  | Y
Central Hudson |  | Sungevity Inc | CH-09518 | Kingston | High Fls | Ulster | 12440 | G | 3022 | High Falls | N |  | 3 | [13 empty] | NM | N | ABB PVI-3.0-OUTD-S-US-A | 2015-08-26 | 2015-09-10 | 10 | 2015-09-10 | [14 empty] | 2016-01-05 | 2016-01-11 |  | Y
Central Hudson |  | New York State Solar Farm | CH-03970 | Kingston | Port Ewen | Ulster | 12466 | G | 1012 | Boulevard | N |  | 3.8 | [13 empty] | NM | N | SMA AMERICA SE3800A-US | 2015-08-27 | 2015-09-10 | 9 | 2015-09-10 | [14 empty] | 2015-09-14 | 2015-09-21 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Apex Solar Power | CH-00666 | Newburgh | Newburgh |  | 12550 | G | 4023 | Coldenham | TBD |  | 7.6 | [13 empty] | NM | N | SolarEdge SE7600A-US | 2015-10-30 | 2015-11-06 | 5 | 2015-11-06 | [17 empty] | W
Central Hudson |  | Apex Solar Power | CH-00667 | Newburgh | Newburgh | Orange | 12550 | G | 4012 | West Balmville | N |  | 3.8 | [13 empty] | NM | N | SolarEdge SE3800A-US | 2015-09-18 | 2015-09-23 | 3 | 2015-09-23 | [14 empty] | 2016-01-25 | 2016-01-26 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Direct Energy Solar | CH-00874 | Newburgh | Newburgh | Orange | 12550 | G | 4051 | Union Ave | N |  | 6.02 | [13 empty] | NM | N | (28) Enphase M215 | 2015-08-27 | 2015-09-08 | 7 | 2015-09-08 | [14 empty] | 2015-11-12 | 2015-11-12 |  | Y
Central Hudson |  | Monolith Solar Associates LLC | CH-02654 | Catskill | Rensselaervl | Albany | 12147 | G | 1092 | Westerlo | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A-US | 2015-08-27 | 2015-09-10 | 9 | 2015-09-10 | [14 empty] | 2015-11-09 | 2015-11-16 |  | Y
Central Hudson |  | Monolith Solar Associates LLC | CH-02665 | Catskill | W Coxsackie | Greene | 12192 | G | 1071 | Coxsackie | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A-US-U | 2015-08-27 | 2015-09-10 | 9 | 2015-09-10 | [14 empty] | 2016-02-01 | 2016-02-08 |  | Y
Central Hudson |  | SolarCity | CH-07445 | Newburgh | New Windsor | Orange | 12553 | G | 4042 | Union Ave | N |  | 3 | [13 empty] | NM | N | ABB PVI-3.0-OUTD-S-US | 2015-08-27 | 2015-09-08 | 7 | 2015-09-08 | [14 empty] | 2015-09-14 | 2015-09-21 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07465 | Newburgh | Wallkill | Ulster | 12589 | G | 5041 | East Walden | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000-OUTD-US | 2015-08-27 | 2015-09-08 | 7 | 2015-09-08 | [14 empty] | 2015-09-14 | 2015-09-21 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | New York State Solar Farm | CH-04072 | Kingston | Kingston | Ulster | 12401 | G | 1011 | Boulevard | N |  | 3 | [13 empty] | NM | N | SMA 3.0-US | 2015-08-28 | 2015-09-11 | 9 | 2015-09-11 | [14 empty] | 2015-09-14 | 2015-09-21 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-05566 | Catskill | Westerlo | Albany | 12193 | G | 1091 | Westerlo | N |  | 4.2 | [13 empty] | NM | N | ABB PVI-4.2-OUTD-S-US-Z | 2015-08-28 | 2015-09-11 | 9 | 2015-09-11 | [14 empty] | 2015-09-29 | 2015-10-06 |  | Y
Central Hudson |  | SolarCity | CH-05819 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6068 | Inwood Ave | N |  | 6 | [13 empty] | NM | N | (1) ABB PVI-6000 | 2015-08-28 | 2015-09-04 | 5 | 2015-09-04 | [14 empty] | 2016-01-04 | 2016-01-11 |  | Y
Central Hudson |  | SolarCity | CH-06251 | Newburgh | New Windsor | Orange | 12553 | G | 4043 | Union Ave | N |  | 3 | [13 empty] | NM | N | ABB PVI-3.0-OUTD-S-US-Z- | 2015-08-28 | 2015-09-09 | 7 | 2015-09-09 | [14 empty] | 2015-09-29 | 2015-10-06 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06728 | Poughkeepsie | Wappingrs Fls | Dutchess | 12590 | G | 6052 | Todd Hill | N |  | 7.2 | [13 empty] | NM | N | (1) ABB PVI-4.2-OUTD-S-US-Z (1) ABB PVI-3.0-OUTD-S-US-Z | 2015-08-28 | 2015-09-04 | 5 | 2015-09-04 | [14 empty] | 2015-10-12 | 2015-10-19 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06765 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7054 | Rhinebeck | N |  | 8.2 | [13 empty] | NM | N | FRONIUS PRIMO 8.2 | 2015-08-28 | 2015-09-14 | 10 | 2015-09-14 | [14 empty] | 2015-09-21 | 2015-09-24 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07713 | Fishkill | Garrison | Putnam | 10524 | G | 8066 | Merritt Park | N |  | 6 | [13 empty] | NM | N | ABB PVI-3.0-OUTD-S-US (2) | 2015-08-28 | 2015-09-09 | 7 | 2015-09-09 | [14 empty] | 2015-09-28 | 2015-10-02 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | New York State Solar Farm | CH-03996 | Newburgh | New Paltz | Ulster | 12561 | G | 5021 | Ohioville | N |  | 5 | [13 empty] | NM | N | SOLAREDGE 5000SE-A-US | 2015-08-31 | 2015-09-10 | 7 | 2015-09-10 | [14 empty] | 2015-09-14 | 2015-09-21 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | New York State Solar Farm | CH-03999 | Newburgh | Walden | Orange | 12586 | G | 5041 | East Walden | N |  | 3.8 | [13 empty] | NM | N | SOLAREDGE SE3800A | 2015-09-08 | 2015-09-16 | 6 | 2015-09-16 | [14 empty] | 2015-09-17 | 2015-09-24 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | NRG Home Solar | CH-04516 | Catskill | Catskill |  | 12414 | G | 2003 | North Catskill | TBD |  | 6.75 | [13 empty] | NM | N | 27 ENPHASE M250-60-2LL-S22 | 2015-08-31 | 2015-09-11 | 8 | 2015-09-11 | [17 empty] | W |  | Customer already had net meter prior to application. 9/17/15 - Customer advised not installing solar.
Central Hudson |  | EthoSolar | CH-01119 | Newburgh | Cornwall Hdsn | Orange | 12520 | G | 4043 | Union Ave | N |  | 180 | [13 empty] | NM | N | (5) Chint Power System CPS-SCA36KTL | 2015-10-06 | 2015-10-27 | 15 | 2015-10-27 | 2015-10-06 | 2015-10-27 | 15 | [5 empty] | 4500 | 7473.76 |  | 2016-08-25 | 2016-08-25 | 2016-11-14 | 2016-11-22 | 2016-11-22 |  | Y
Central Hudson |  | Murphy Solar Power | CH-02740 | Catskill | Freehold | Greene | 12431 | G | 2071 | Freehold | N |  | 7 | [13 empty] | NM | N | SMA 7000T-L22-US | 2015-08-31 | 2015-09-11 | 8 | 2015-09-11 | [14 empty] | 2015-09-22 | 2015-09-29 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-04929 | Kingston | Kingston | Ulster | 12401 | G | 1011 | Boulevard | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2015-08-31 | 2015-09-11 | 8 | 2015-09-11 | [14 empty] | 2015-10-08 | 2015-10-15 |  | Y
Central Hudson |  | SolarCity | CH-04990 | Kingston | Kingston | Ulster | 12401 | G | 2094 | Hurley Ave | N |  | 3.6 | [13 empty] | NM | N | ABB PVI-3.6-OUTD-S-US-Z- | 2015-08-31 | 2015-09-11 | 8 | 2015-09-11 | [14 empty] | 2015-12-08 | 2015-12-15 |  | Y
Central Hudson |  | SolarCity | CH-05578 | Catskill | Athens | Greene | 12015 | G | 1074 | Coxsackie | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000-OUTD-US-Z-A | 2015-08-31 | 2015-09-11 | 8 | 2015-09-11 | [14 empty] | 2015-10-14 | 2015-10-14 |  | Y
Central Hudson |  | SolarCity | CH-05830 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6063 | Inwood Ave | N |  | 3.6 | [13 empty] | NM | N | ABB PVI-3.6-OUTD-S-US-Z | 2015-08-31 | 2015-09-10 | 7 | 2015-09-10 | [14 empty] | 2015-09-25 | 2015-09-30 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06051 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8096 | Fishkill Plains | N | CH-06051 | 3.6 | [13 empty] | NM | N | ABB PVI-3.6-OUTD-S-US | 2015-08-31 | 2015-09-10 | 7 | 2015-09-10 | [14 empty] | 2015-09-29 | 2015-10-06 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06221 | Newburgh | Newburgh | Orange | 12550 | G | 4024 | Coldenham | N |  | 8.2 | [13 empty] | NM | N | FRONIUS PRIMO 8.2 | 2015-08-31 | 2015-09-10 | 7 | 2015-09-10 | [14 empty] | 2015-10-12 | 2015-10-15 |  | Y
Central Hudson |  | SolarCity | CH-06758 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7056 | Rhinebeck | N |  | 3.6 | [13 empty] | NM | N | ABB PVI-3.6-OUTD-S-US-Z | 2015-08-31 | 2015-09-10 | 7 | 2015-09-10 | [14 empty] | 2015-09-29 | 2015-10-06 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07433 | Newburgh | Newburgh | Orange | 12550 | G | 4051 | Union Ave | N |  | 3 | [13 empty] | NM | N | ABB PVI-3.0-OUTD-S | 2015-12-02 | 2015-12-02 | 0 | 2015-12-02 | [14 empty] | 2015-12-31 | 2016-01-07 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07436 | Newburgh | New Windsor | Orange | 12553 | G | 4044 | Union Ave | N |  | 5 | [13 empty] | NM | N | ABB PVI-5000-OUTD-US-Z-A | 2015-09-17 | 2015-09-23 | 4 | 2015-09-23 | [14 empty] | 2015-10-19 | 2015-10-26 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07837 | Fishkill | Wappingrs Falls |  | 12590 | G | 8043 | Myers Corners | TBD |  | 7.6 | [13 empty] | NM | N | SOLAREDGE STOREDGE 7600 | 2015-08-31 | 2015-09-10 | 7 | 2015-09-10 | [17 empty] | W
Central Hudson |  | Trinity Solar | CH-08462 | Catskill | Freehold | Greene | 12431 | G | 2071 | Freehold | N |  | 3 | [13 empty] | NM | N | SOLAR EDGE SE3000 | 2015-08-31 | 2015-09-11 | 8 | 2015-09-11 | [14 empty] | 2016-01-25 | 2016-02-01 |  | Y
Central Hudson |  | Sungevity Inc | CH-09624 | Poughkeepsie | Hyde Pk |  | 12538 | G | 7041 | Staatsburg | TBD |  | 5 | [13 empty] | NM | N | ABB PVI-5000-OUTD-US-A | 2015-08-31 | 2015-09-10 | 7 | 2015-09-10 | [17 empty] | W |  | 9/7/15 Company Holiday.
Central Hudson |  | American Solar Partners | CH-03069 | Newburgh | Highland | Ulster | 12528 | G | 5084 | Highland | N |  | 5 | [13 empty] | NM | N | SMA SB5000TL-US | 2015-09-29 | 2015-10-06 | 5 | 2015-10-06 | [14 empty] | 2016-01-07 | 2016-01-14 |  | Y
Central Hudson |  | American Solar Partners | CH-03075 | Kingston | Grahamsvl | Sullivan | 12740 | G | 3091 | Neversink | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE7600-US | 2015-09-01 | 2015-09-16 | 10 | 2015-09-16 | [14 empty] | 2015-12-17 | 2015-12-28 |  | Y
Central Hudson |  | Monolith Solar Associates LLC | CH-02677 | Catskill | Freehold | Greene | 12431 | G | 2061 | Freehold | N |  | 7.7 | [13 empty] | NM | N | SMA 7700 TL-22 | 2015-09-01 | 2015-09-16 | 10 | 2015-09-16 | [14 empty] | 2016-01-06 | 2016-01-13 |  | Y
Central Hudson |  | Monolith Solar Associates LLC | CH-02684 | Catskill | S Cairo | Greene | 12451 | G | 2005 | North Catskill | N | CH-02684 | 10 | [13 empty] | NM | N | SOLAREDGE SE10000-US | 2016-05-26 | 2016-05-26 | 0 | 2016-05-26 | [14 empty] | 2016-06-09 | 2016-06-15 |  | Y
Central Hudson |  | Paradise Energy Solutions LLC | CH-02840 | Fishkill | Stormvl | Dutchess | 12582 | G | 8095 | Fishkill Plains | N |  | 20 | [13 empty] | NM | N | 4 SMA SB5000 TL-US-22 | 2015-09-01 | 2015-09-16 | 10 | 2015-09-16 | [14 empty] | 2015-10-27 | 2015-10-30 |  | Y
Central Hudson |  | SolarCity | CH-06673 | Poughkeepsie | Staatsburg | Dutchess | 12580 | G | 7041 | Staatsburg | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A-US | 2015-10-14 | 2015-10-21 | 5 | 2015-10-21 | [14 empty] | 2015-11-04 | 2015-11-11 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Solar Generation | CH-08093 | Kingston | Kingston | Ulster | 12401 | G | 2011 | Lincoln Park | N |  | 45.6 | [13 empty] | NM | N | 4 SOLAREDGE 11400A-US | 2015-09-01 | 2015-09-16 | 10 | 2015-09-16 | [14 empty] | 2016-04-18 | 2016-04-20 |  | Y
Central Hudson |  | Solar Generation | CH-08307 | Kingston | Woodstock | Ulster | 12498 | G | 3013 | Woodstock | N | CH-08270 | 3 | [13 empty] | NM | N | SMA SB 3000 TL | 2015-09-01 | 2015-09-16 | 10 | 2015-09-16 | [14 empty] | 2015-10-19 | 2015-10-26 |  | Y
Central Hudson |  | Sol Providers | CH-08967 | Fishkill | Hopewell Jct |  | 12533 | G | 8094 | Fishkill Plains | TBD |  | 24 | [13 empty] | NM | N | 3 SMA 8000TL-US-22 | 2015-09-01 | 2015-09-16 | 10 | 2015-09-16 | [8 empty] | 350 | 350 | [7 empty] | W
Central Hudson |  | Trinity Solar | CH-08549 | Newburgh | Highland | Ulster | 12528 | G | 5022 | Ohioville | N |  | 11.5 | [13 empty] | NM | N | ENPHASE M250 60-2LL-S22 (46) | 2015-09-11 | 2015-09-17 | 4 | 2015-09-17 | [14 empty] | 2016-03-08 | 2016-03-09 |  | Y
Central Hudson |  | Hudson Solar | CH-01278 | Kingston | Stone Ridge | Ulster | 12484 | G | 3023 | High Falls | N |  | 7 | [13 empty] | NM | N | SMA AMERICA SB7000 TL-US-22 | 2015-09-03 | 2015-09-17 | 9 | 2015-09-17 | [14 empty] | 2015-11-10 | 2015-11-17 |  | Y
Central Hudson |  | Hudson Solar | CH-01888 | Poughkeepsie | Pine Plns | Dutchess | 12567 | G | 7092 | Pulvers Corners | Y |  | 5.5 | 5.5 | [12 empty] | NM | N | SCHNEIDER XW+5548 NA1XantrexXW5548 (DC) | 2015-09-23 | 2015-09-23 | 0 | 2015-09-23 | [14 empty] | 2015-11-24 | 2015-12-03 |  | Y
Central Hudson |  | Hudson Solar | CH-01945 | Newburgh | New Paltz | Ulster | 12561 | G | 5031 | Galeville | N | CH-01945 | 7.6 | [13 empty] | NM | N | SMA AMERICA SB7000 TL-US-22 | 2015-09-03 | 2015-09-17 | 9 | 2015-09-17 | [14 empty] | 2016-01-14 | 2016-01-15 |  | Y
Central Hudson |  | Hudson Solar | CH-02282 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7062 | Milan | N |  | 6 | [13 empty] | NM | N | SMA AMERICA SB6000 | 2015-09-03 | 2015-09-18 | 10 | 2015-09-18 | [14 empty] | 2016-06-21 | 2016-06-28 |  | Y
Central Hudson |  | Monolith Solar Associates LLC | CH-02642 | Catskill | Hannacroix | Greene | 12087 | G | 1083 | New Baltimore | N |  | 12 | [13 empty] | NM | N | SOLAREDGE SE6000 (2) | 2015-09-03 | 2015-09-17 | 9 | 2015-09-17 | [14 empty] | 2015-12-09 | 2015-12-16 |  | Y
Central Hudson |  | SolarCity | CH-06415 | Newburgh | Montgomery | Orange | 12549 | G | 5073 | Montgomery | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2015-09-03 | 2015-09-17 | 9 | 2015-09-17 | [14 empty] | 2015-09-22 | 2015-09-28 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07707 | Newburgh | Highland |  | 12528 | G | 5081 | Highland | TBD |  | 6 | [13 empty] | NM | N | ABB PVI-6000-OUTD-US | 2015-09-03 | 2015-09-18 | 10 | 2015-09-18 | [17 empty] | W
Central Hudson |  | Infinity Solar Systems | CH-03431 | Newburgh | Newburgh | Orange | 12550 | G | 5004 | Marlboro | N |  | 5 | [13 empty] | NM | N | SMA AMERICA SB5000TL-US-22 | 2015-09-04 | 2015-09-14 | 5 | 2015-09-14 | [14 empty] | 2015-11-10 | 2015-11-10 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03580 | Newburgh | Esopus | Ulster | 12429 | G | 5084 | Highland | N |  | 42 | [13 empty] | RNM | N | 7 ABB PVI 6000 | 2015-09-04 | 2015-09-21 | 10 | 2015-09-21 | [8 empty] | 1739 | 1738.51 |  | 2015-10-23 | 2015-10-23 | 2015-10-23 | 2015-11-05 | 2015-11-05 |  | Y
Central Hudson |  | New York State Solar Farm | CH-04094 | Fishkill | Wappingers Falls | Dutchess | 12590 | G | 8023 | Knapps Corners | N | CH-03988 | 3.8 | [13 empty] | NM | N | SMA SB3800-TL | 2015-09-17 | 2015-09-18 | 1 | 2015-09-18 | [14 empty] | 2015-09-18 | 2015-09-18 |  | Y
Central Hudson |  | Apex Solar Power | CH-00697 | Newburgh | Newburgh | Orange | 12550 | G | 4023 | Coldenham | N |  | 9.8 | [13 empty] | NM | N | SOLAR EDGE SE3800A-US SOLAR EDGE SE6000A-US | 2015-09-04 | 2015-09-14 | 5 | 2015-09-14 | [14 empty] | 2015-12-30 | 2016-01-07 |  | Y
Central Hudson |  | SolarCity | CH-05160 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8072 | Shenandoah | N |  | 3 | [13 empty] | NM | N | ABB PVI-3.0-OUTD-S-US-Z- | 2015-09-16 | 2015-09-22 | 4 | 2015-09-22 | [14 empty] | 2015-10-19 | 2015-10-22 |  | Y
Central Hudson |  | SolarCity | CH-05583 | Catskill | Coxsackie | Greene | 12051 | G | 1076 | Coxsackie | N |  | 3 | [13 empty] | NM | N | ABB PVI-3.0-OUTD-S-US-Z- | 2015-09-04 | 2015-09-21 | 10 | 2015-09-21 | [14 empty] | 2015-11-03 | 2015-11-09 |  | Y
Central Hudson |  | SolarCity | CH-06679 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6073 | East Park | N |  | 11 | [13 empty] | NM | N | ABB PVI-5000-OUTD-US-Z-A ABB PVI-6000-OUTD-US-Z-A | 2015-09-04 | 2015-09-14 | 5 | 2015-09-14 | [14 empty] | 2015-10-21 | 2015-10-28 |  | Y
Central Hudson |  | SolarCity | CH-06869 | Fishkill | Fishkill | Dutchess | 12524 | G | 8094 | Fishkill Plains | N |  | 3 | [13 empty] | NM | N | ABB PVI-3.0-OUTD-S-US-Z- | 2015-09-04 | 2015-09-14 | 5 | 2015-09-14 | [14 empty] | 2015-10-19 | 2015-10-22 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Sol Providers | CH-08906 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8091 | Fishkill Plains | N |  | 6 | [13 empty] | NM | N | SMA SB6000TL-65-22 | 2015-09-21 | 2015-09-22 | 1 | 2015-09-22 | [14 empty] | 2015-10-07 | 2015-10-12 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-03442 | Newburgh | Walden | Orange | 12586 | G | 4026 | Coldenham | N |  | 15 | [13 empty] | NM | N | FRONIUS IG PLUS A 10.0 SMA AMERICA SB5000TL-US-22 | 2015-09-08 | 2015-09-16 | 6 | 2015-09-16 | [14 empty] | 2015-11-13 | 2015-11-13 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03800 | Newburgh | New Paltz |  | 12561 | G | 5031 | Galeville | TBD |  | 10 | [13 empty] | NM | N | SOLAREDGE 10000 | 2015-09-08 | 2015-09-16 | 6 | 2015-09-16 | [8 empty] | 350 | 350 | [7 empty] | W |  | Transformer upgrade required to accommodate PV installation. Utility System Upgrade Costs TBD.
Central Hudson |  | Lighthouse Solar | CH-03805 | Newburgh | Marlboro | Ulster | 12542 | G | 5004 | Marlboro | N | CH-03805 | 7.6 | [13 empty] | NM | N | SOLAREDGE 7600 | 2015-09-08 | 2015-09-16 | 6 | 2015-09-16 | [14 empty] | 2015-10-27 | 2015-10-30 |  | Y
Central Hudson |  | New York State Solar Farm | CH-04025 | Kingston | Saugerties | Ulster | 12477 | G | 3001 | Saugerties | N |  | 3 | [13 empty] | NM | N | SOLAREDGE SE | 2015-09-08 | 2015-09-22 | 10 | 2015-09-22 | [14 empty] | 2015-09-24 | 2015-09-30 |  | Y
Central Hudson |  | New York State Solar Farm | CH-04068 | Newburgh | New Paltz | Ulster | 12561 | G | 5031 | Galeville | N |  | 9.8 | [13 empty] | NM | N | SMA AMERICA SB-TL6000 SMA AMERICA SB-TL3800 | 2015-09-08 | 2015-09-16 | 6 | 2015-09-16 | [14 empty] | 2015-09-24 | 2015-09-30 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | NRG Home Solar | CH-04323 | Poughkeepsie | Staatsburg | Dutchess | 12580 | G | 7041 | Staatsburg | N |  | 7.25 | [13 empty] | NM | N | ENPHASE ENGERY M250-60-2LL-S22 (29) | 2015-09-08 | 2015-09-22 | 10 | 2015-09-22 | [14 empty] | 2015-12-28 | 2016-01-05 |  | Y
Central Hudson |  | NRG Home Solar | CH-04378 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8094 | Fishkill Plains | N |  | 8.25 | [13 empty] | NM | N | ENPHASE ENGERY M250-60-2LL-S22 (33) | 2015-09-08 | 2015-09-16 | 6 | 2015-09-16 | [14 empty] | 2015-12-31 | 2016-01-07 |  | Y
Central Hudson |  | Hudson Solar | CH-01533 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7054 | Rhinebeck | N |  | 22.8 | [13 empty] | NM | N | (2) SolarEdge SE11400A-US | 2015-09-08 | 2015-09-22 | 10 | 2015-09-22 | [14 empty] | 2016-03-11 | 2016-03-18 |  | Y
Central Hudson |  | SolarCity | CH-05001 | Kingston | Grahamsvl | Sullivan | 12740 | G | 3095 | Grimley Rd | N |  | 11 | [13 empty] | NM | N | ABB PVI-6000-OUTD ABB PVI-5000-OUTD | 2015-09-08 | 2015-09-22 | 10 | 2015-09-22 | [8 empty] | 350 | 350 |  | 2015-12-11 | 2015-12-11 | 2016-01-05 | 2016-01-05 | 2016-01-11 |  | Y
Central Hudson |  | SolarCity | CH-05068 | Newburgh | Wallkill |  | 12589 | G | 4011 | West Balmville | TBD |  | 6 | [13 empty] | NM | N | ABB PVI-6000-OUTD | 2015-09-24 | 2015-09-29 | 3 | 2015-09-29 | [17 empty] | W
Central Hudson |  | SolarCity | CH-05591 | Catskill | W Coxsackie | Greene | 12192 | G | 1071 | Coxsackie | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2015-09-08 | 2015-09-22 | 10 | 2015-09-22 | [14 empty] | 2015-10-05 | 2015-10-12 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-05821 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6061 | Inwood Ave | N |  | 8 | [13 empty] | NM | N | ABB PVI-5000-OUTD-US-Z-A ABB PVI-3.0-OUTD-S-US-Z- | 2015-11-25 | 2015-12-04 | 5 | 2015-12-04 | [14 empty] | 2015-12-15 | 2015-12-21 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07024 | Newburgh | New Windsor | Orange | 12553 | G | 4045 | Union Ave | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000-OUTD-US-Z-A | 2015-09-08 | 2015-09-16 | 6 | 2015-09-16 | [14 empty] | 2015-10-15 | 2015-10-22 |  | Y
Central Hudson |  | SolarCity | CH-07078 | Newburgh | Gardiner | Ulster | 12525 | G | 5031 | Galeville | N |  | 7.2 | [13 empty] | NM | N | ABB PVI-3.6-OUTD-S-US-Z- (2) | 2015-09-08 | 2015-09-16 | 6 | 2015-09-16 | [14 empty] | 2015-09-21 | 2015-09-28 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07344 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8044 | Myers Corners | N |  | 5 | [13 empty] | NM | N | ABB PVI-5000-OUTD | 2015-09-08 | 2015-09-16 | 6 | 2015-09-16 | [14 empty] | 2015-11-13 | 2015-11-13 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Infinity Solar Systems | CH-03452 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8091 | Fishkill Plains | N |  | 7.7 | [13 empty] | NM | N | SMA AMERICA SB7700TL-US-22 | 2015-09-09 | 2015-09-17 | 6 | 2015-09-17 | [14 empty] | 2015-10-27 | 2015-10-30 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03621 | Newburgh | Gardiner | Ulster | 12525 | G | 5031 | Galeville | N |  | 10 | [13 empty] | NM | N | ABB 5000 OUTD-US (2) | 2015-09-09 | 2015-09-17 | 6 | 2015-09-17 | [14 empty] | 2015-10-08 | 2015-10-13 |  | Y
Central Hudson |  | NRG Home Solar | CH-04358 | Poughkeepsie | Milan | Dutchess | 12571 | G | 7062 | Milan | N |  | 4 | [13 empty] | NM | N | ENPHASE ENGERY M250-60-2LL-S22 (16) | 2015-09-09 | 2015-09-23 | 10 | 2015-09-23 | [14 empty] | 2015-12-28 | 2016-01-05 |  | Y
Central Hudson |  | NRG Home Solar | CH-04638 | Newburgh | Newburgh | Orange | 12550 | G | 4012 | West Balmville | N |  | 5 | [13 empty] | NM | N | SOLAR EDGE SE5000A-US | 2015-10-26 | 2015-10-29 | 3 | 2015-10-29 | [14 empty] | 2015-12-14 | 2015-12-14 |  | Y
Central Hudson |  | NRG Home Solar | CH-04641 | Newburgh | Newburgh | Orange | 12550 | G | 4012 | West Balmville | N |  | 3 | [13 empty] | NM | N | ENPHASE ENGERY M250-60-2LL-S22 (12) | 2015-09-09 | 2015-09-17 | 6 | 2015-09-17 | [14 empty] | 2015-12-14 | 2015-12-15 |  | Y
Central Hudson |  | SolarCity | CH-05198 | Newburgh | Gardiner | Ulster | 12525 | G | 5031 | Galeville | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2015-09-09 | 2015-09-17 | 6 | 2015-09-17 | [14 empty] | 2015-12-14 | 2015-12-14 |  | Y
Central Hudson |  | SolarCity | CH-05719 | Kingston | Saugerties | Ulster | 12477 | G | 3002 | Saugerties | N |  | 8.2 | [13 empty] | NM | N | FRONIUS PRIMO 8.2 | 2015-09-09 | 2015-09-22 | 9 | 2015-09-22 | [14 empty] | 2015-11-12 | 2015-11-19 |  | Y
Central Hudson |  | SolarCity | CH-07116 | Newburgh | New Windsor | Orange | 12553 | G | 4095 | Bethlehem Rd | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2015-09-09 | 2015-09-17 | 6 | 2015-09-17 | [14 empty] | 2015-09-29 | 2015-10-06 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07438 | Newburgh | New Windsor | Orange | 12553 | G | 4044 | Union Ave | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000-OUTD-US-Z-A | 2015-09-09 | 2015-09-17 | 6 | 2015-09-17 | [14 empty] | 2015-11-24 | 2015-11-24 |  | Y
Central Hudson |  | Sunrun Inc. | CH-08322 | Newburgh | New Windsor | Orange | 12553 | G | 4094 | Bethlehem Rd | N | CH-08322 | 5 | [13 empty] | NM | N | ABB PVI-5000-OUTD-US | 2015-09-18 | 2015-09-23 | 3 | 2015-09-23 | [14 empty] | 2015-10-08 | 2015-10-14 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | American Solar Partners | CH-03068 | Newburgh | Highland | Ulster | 12528 | G | 5012 | Modena | N |  | 10 | [13 empty] | NM | N | SOLAR EDGE SE10000 | 2015-09-10 | 2015-09-17 | 5 | 2015-09-17 | [14 empty] | 2016-01-13 | 2016-01-15 |  | Y
Central Hudson |  | Apex Solar Power | CH-03087 | Catskill | Prattsville |  | 12468 | E | 2389 | Vinegar Hill | TBD |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000 A-US | 2015-09-10 | 2015-09-23 | 9 | 2015-09-23 | [17 empty] | W |  | Transformer upgrade required to accommodate PV installation. Utility System Upgrade Costs TBD. Contractor advised that customer is no longer going to install solar 10/13/15.
Central Hudson |  | Apex Solar Power | CH-00680 | Kingston | Ellenvl | Ulster | 12428 | G | 3078 | Greenfield Rd | N |  | 12 | [13 empty] | NM | N | 2 SOLAREDGE SE6000 A-US | 2015-09-10 | 2015-09-23 | 9 | 2015-09-23 | [14 empty] | 2015-10-26 | 2015-10-30 |  | Y
Central Hudson |  | Monolith Solar Associates LLC | CH-02662 | Catskill | W Coxsackie | Greene | 12192 | G | 1071 | Coxsackie | N |  | 11 | [13 empty] | NM | N | SOLAREDGE SE5000 A-US (1) SOLAREDGE SE6000 A-US (1) | 2015-09-10 | 2015-09-23 | 9 | 2015-09-23 | [14 empty] | 2015-12-09 | 2015-12-16 |  | Y
Central Hudson |  | SolarCity | CH-07904 | Newburgh | Newburgh |  | 12550 | G | 4022 | Coldenham | TBD |  | 10.2 | [13 empty] | NM | N | ABB PVI-6000-OUTD ABB PVI-4.2-OUTD-S | 2015-09-10 | 2015-09-24 | 10 | 2015-09-24 | [17 empty] | W
Central Hudson |  | Sungevity Inc | CH-09236 | Newburgh | New Windsor | Orange | 12553 | G | 4095 | Bethlehem Rd | N |  | 3.8 | [13 empty] | NM | N | ABB PVI-3.8-OUTD-S-US-A | 2015-09-18 | 2015-09-18 | 0 | 2015-09-18 | [14 empty] | 2015-11-18 | 2015-11-18 |  | Y
Central Hudson |  | American Solar Partners | CH-03064 | Newburgh | Highland | Ulster | 12528 | G | 5012 | Modena | N |  | 16 | [13 empty] | NM | N | SOLAR EDGE SE10000 SOLAR EDGE SE6000 | 2015-09-11 | 2015-09-24 | 9 | 2015-09-24 | [8 empty] | 350 | 350 |  | 2016-02-19 | 2016-02-19 | 2016-03-11 | 2016-03-11 | 2016-03-18 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-03438 | Newburgh | New Windsor | Orange | 12553 | G | 4095 | Bethlehem Rd | N |  | 7.6 | [13 empty] | NM | N | SMA AMERICA SB3800TL-US-22(2) | 2015-09-22 | 2015-09-24 | 2 | 2015-09-24 | [14 empty] | 2015-10-09 | 2015-10-09 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-03440 | Newburgh | Campbell Hall | Orange | 10916 | G | 5051 | Maybrook | N |  | 5 | [13 empty] | NM | N | SMA AMERICA SB5000TL-US-22 | 2015-09-11 | 2015-09-18 | 5 | 2015-09-18 | [14 empty] | 2016-01-04 | 2016-01-11 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03584 | Kingston | High Fls | Ulster | 12440 | G | 3024 | High Falls | N |  | 15.2 | [13 empty] | NM | N | 2 SOLAREDGE 7600 A-US | 2015-09-11 | 2015-09-23 | 8 | 2015-09-23 | [14 empty] | 2015-11-13 | 2015-11-20 |  | Y
Central Hudson |  | SolarCity | CH-04935 | Newburgh | Newburgh | Orange | 12550 | G | 4024 | Coldenham | N |  | 3.6 | [13 empty] | NM | N | ABB PVI-3.6-OUTD-S-US-Z- | 2015-09-11 | 2015-09-18 | 5 | 2015-09-18 | [14 empty] | 2015-11-05 | 2015-11-06 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Lighthouse Solar | CH-03648 | Kingston | Accord | Ulster | 12404 | G | 3081 | Kerhonkson | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000 | 2015-09-14 | 2015-09-28 | 10 | 2015-09-28 | [14 empty] | 2015-11-18 | 2015-11-25 |  | Y
Central Hudson |  | NRG Home Solar | CH-04140 | Poughkeepsie | Millerton | Dutchess | 12546 | G | 7081 | Millerton | N |  | 2.75 | [13 empty] | NM | N | ENPHASE ENGERY M250-60-2LL-S22 (11) | 2015-09-14 | 2015-09-24 | 8 | 2015-09-24 | [14 empty] | 2015-12-28 | 2016-01-05 |  | Y
Central Hudson |  | NRG Home Solar | CH-04282 | Kingston | Grahamsvl | Sullivan | 12740 | G | 3091 | Neversink | N |  | 7.6 | [13 empty] | NM | N | SOLAR EDGE SE7600-A | 2015-09-14 | 2015-09-28 | 10 | 2015-09-28 | [14 empty] | 2015-12-11 | 2015-12-18 |  | Y
Central Hudson |  | NRG Home Solar | CH-04360 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7062 | Milan | N |  | 3.25 | [13 empty] | NM | N | ENPHASE ENGERY M250-60-2LL-S22 (13) | 2015-09-14 | 2015-09-24 | 8 | 2015-09-24 | [14 empty] | 2015-12-28 | 2016-01-05 |  | Y
Central Hudson |  | NRG Home Solar | CH-04385 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8046 | Myers Corners | N |  | 4.75 | [13 empty] | NM | N | ENPHASE ENGERY M250-60-2LL-S22 (19) | 2015-09-14 | 2015-09-22 | 6 | 2015-09-22 | [14 empty] | 2015-12-22 | 2015-12-31 |  | Y
Central Hudson |  | NRG Home Solar | CH-04391 | Fishkill | Stormvl | Dutchess | 12582 | G | 8095 | Fishkill Plains | N |  | 10.5 | [13 empty] | NM | N | ENPHASE ENGERY M250-60-2LL-S22 (42) | 2015-09-14 | 2015-09-22 | 6 | 2015-09-22 | [14 empty] | 2015-12-22 | 2015-12-30 |  | Y
Central Hudson |  | NRG Home Solar | CH-04756 | Kingston | Kingston | Ulster | 12401 | G | 1021 | East Kingston | N |  | 15.2 | [13 empty] | NM | N | 2 SOLAR EDGE SE7600-A | 2015-09-14 | 2015-09-28 | 10 | 2015-09-28 | [14 empty] | 2015-12-30 | 2016-01-12 |  | Y
Central Hudson |  | Direct Energy Solar | CH-01018 | Fishkill | Garrison | Putnam | 10524 | G | 8086 | Tioronda | N |  | 8.6 | [13 empty] | NM | N | ENPHASE M215 60-2LL-S22 (40) | 2015-09-21 | 2015-09-22 | 1 | 2015-09-22 | [14 empty] | 2015-12-10 | 2015-12-17 |  | Y
Central Hudson |  | Novel Approaches | CH-02778 | Kingston | Napanoch | Ulster | 12458 | G | 3091 | Neversink | N |  | 11.4 | [13 empty] | NM | N | SOLAREDGE SE11400 A-US | 2015-09-14 | 2015-09-28 | 10 | 2015-09-28 | [8 empty] | 350 | 350 |  | 2015-10-12 | 2015-10-12 | 2015-12-02 | 2015-12-02 | 2015-12-02 |  | Y
Central Hudson |  | SolarCity | CH-06250 | Newburgh | New Windsor | Orange | 12553 | G | 4043 | Union Ave | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000-OUTD-US-Z-A | 2015-09-14 | 2015-09-22 | 6 | 2015-09-22 | [14 empty] | 2015-11-05 | 2015-11-06 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06298 | Newburgh | Wallkill | Ulster | 12589 | G | 5013 | Modena | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000-OUTD US | 2015-09-14 | 2015-09-22 | 6 | 2015-09-22 | [14 empty] | 2015-11-04 | 2015-11-05 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07066 | Newburgh | Newburgh | Orange | 12550 | G | 5004 | Marlboro | N |  | 7.6 | [13 empty] | NM | N | PRONIUS PRIMO 7.6 | 2015-09-14 | 2015-09-22 | 6 | 2015-09-22 | [14 empty] | 2015-10-06 | 2015-10-13 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07270 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6046 | Spackenkill | N |  | 6.6 | [13 empty] | NM | N | ABB PVI-3.6-OUTD-S-US-Z- ABB PVI-3.0-OUTD-S-US-Z | 2015-09-14 | 2015-09-24 | 8 | 2015-09-24 | [14 empty] | 2015-10-06 | 2015-10-12 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07463 | Newburgh | Gardiner | Ulster | 12525 | G | 5043 | East Walden | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2015-09-14 | 2015-09-22 | 6 | 2015-09-22 | [14 empty] | 2015-09-29 | 2015-10-06 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07667 | Fishkill | Beacon | Dutchess | 12508 | G | 8085 | Tioronda | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE7600A-US | 2015-09-23 | 2015-09-29 | 4 | 2015-09-29 | [14 empty] | 2015-10-06 | 2015-10-09 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Sun Mountain | CH-09083 | Kingston | High Fls | Ulster | 12440 | G | 3024 | High Falls | N |  | 12 | [13 empty] | NM | N | SMA SB6000TL-US 22 (2) | 2015-09-14 | 2015-09-28 | 10 | 2015-09-28 | [8 empty] | 350 | 350 |  | 2015-12-22 | 2015-12-22 | 2016-01-08 | 2016-01-14 | 2016-01-15 |  | Y
Central Hudson |  | Sungevity Inc | CH-09270 | Kingston | Kerhonkson | Ulster | 12446 | G | 3081 | Kerhonkson | N |  | 6.8 | [13 empty] | NM | N | ABB PVI-3.8-OUTD-S-US-A(1) ABB PVI-3.0-OUTD-S-US-A(1) | 2015-09-14 | 2015-09-15 | 1 | 2015-09-15 | [14 empty] | 2015-10-14 | 2015-10-20 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-03477 | Newburgh | New Windsor | Orange | 12553 | G | 4094 | Bethlehem Rd | N |  | 8 | [13 empty] | NM | N | SMA AMERICA SB8000 US-12 | 2015-09-15 | 2015-09-22 | 5 | 2015-09-22 | [14 empty] | 2015-10-19 | 2015-10-22 |  | Y
Central Hudson |  | SolarCity | CH-05269 | Newburgh | Highland | Ulster | 12528 | G | 5082 | Highland | N |  | 8.2 | [13 empty] | NM | N | FRONIUS PRIMO 8.2 | 2015-09-15 | 2015-09-22 | 5 | 2015-09-22 | [14 empty] | 2015-10-16 | 2015-10-23 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-05518 | Catskill | Cairo | Greene | 12413 | G | 2043 | South Cairo | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2015-09-15 | 2015-09-29 | 10 | 2015-09-29 | [14 empty] | 2016-01-05 | 2016-01-11 |  | Y
Central Hudson |  | SolarCity | CH-06405 | Newburgh | Rock Tvrn | Orange | 12575 | G | 4097 | Bethlehem Rd | N |  | 3.6 | [13 empty] | NM | N | ABB PVI-3.6-OUTD-S US | 2015-09-15 | 2015-09-22 | 5 | 2015-09-22 | [14 empty] | 2016-01-04 | 2016-01-11 |  | Y
Central Hudson |  | SolarCity | CH-06425 | Newburgh | Maybrook | Orange | 12543 | G | 4026 | Coldenham | N |  | 3.6 | [13 empty] | NM | N | ABB PVI-3.6-OUTD-S US | 2015-09-15 | 2015-09-22 | 5 | 2015-09-22 | [14 empty] | 2015-10-19 | 2015-10-22 |  | Y
Central Hudson |  | SolarCity | CH-07321 | Poughkeepsie | Tivoli | Dutchess | 12583 | G | 7062 | Milan | N |  | 12 | [13 empty] | NM | N | (2) ABB PVI-6000-OUTD US | 2015-09-15 | 2015-09-22 | 5 | 2015-09-22 | [14 empty] | 2016-01-11 | 2016-01-15 |  | Y
Central Hudson |  | SolarCity | CH-07455 | Newburgh | Marlboro | Ulster | 12542 | G | 5003 | Marlboro | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2015-09-15 | 2015-09-22 | 5 | 2015-09-22 | [14 empty] | 2015-10-02 | 2015-10-09 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07683 | Newburgh | Newburgh | Orange | 12550 | G | 4047 | Union Ave | N |  | 5 | [13 empty] | NM | N | ABB PVI-5000-OUTD US | 2015-09-15 | 2015-09-22 | 5 | 2015-09-22 | [14 empty] | 2016-01-27 | 2016-01-28 |  | Y
Central Hudson |  | SolarCity | CH-07761 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 6092 | Manchester | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000-OUTD US | 2015-09-15 | 2015-09-22 | 5 | 2015-09-22 | [14 empty] | 2015-10-09 | 2015-10-16 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Sungevity Inc | CH-09322 | Poughkeepsie | Lagrangevl | Dutchess | 12540 | G | 6057 | Todd Hill | N |  | 11.4 | [13 empty] | NM | N | (3) ABB PVI-3.8-OUTD-S-US-A | 2015-09-15 | 2015-09-22 | 5 | 2015-09-22 | [14 empty] | 2015-10-27 | 2015-11-02 |  | Y
Central Hudson |  | RGS Energy | CH-03044 | Kingston | Saugerties | Ulster | 12477 | G | 3001 | Saugerties | N |  | 6.45 | [13 empty] | NM | N | 30 ENPHASE M215-60-2LL-S22-IG | 2015-09-16 | 2015-09-30 | 10 | 2015-09-30 | [14 empty] | 2015-11-03 | 2015-11-09 |  | Y
Central Hudson |  | American Solar Partners | CH-00006 | Poughkeepsie | Wappingrs Fls | Dutchess | 12590 | G | 6052 | Todd Hill | N |  | 10 | [13 empty] | NM | N | SOLAR EDGE SE10000 | 2015-09-16 | 2015-09-23 | 5 | 2015-09-23 | [14 empty] | 2016-06-23 | 2016-06-30 |  | Y
Central Hudson |  | Paradise Energy Solutions LLC | CH-02845 | Newburgh | New Windsor | Orange | 12553 | G | 4047 | Union Ave | N |  | 192 | [13 empty] | RNM | N | (8) SMA STP24000TL | 2015-10-23 | 2015-11-13 | 15 | 2015-11-13 | 2015-10-23 | 2015-11-13 | 15 | 2015-12-03 | 2015-12-03 | 2015-12-23 | 14 | 9200 | 9036 | 6473.9244 |  | 2015-12-23 | 2015-12-23 | 2016-02-15 | 2016-03-09 | 2016-03-17 |  | Y
Central Hudson |  | SolarCity | CH-06374 | Newburgh | Modena | Ulster | 12548 | G | 5011 | Modena | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2015-09-23 | 2015-09-29 | 4 | 2015-09-29 | [14 empty] | 2015-12-15 | 2015-12-15 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06597 | Kingston | Kingston | Ulster | 12401 | G | 2013 | Lincoln Park | N |  | 3.6 | [13 empty] | NM | N | ABB PVI-3.6-OUTD-S-US | 2015-09-16 | 2015-09-30 | 10 | 2015-09-30 | [14 empty] | 2015-10-08 | 2015-10-15 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL. Customer already had net meter prior to application.
Central Hudson |  | Lighthouse Solar | CH-03632 | Newburgh | Newburgh | Orange | 12550 | G | 4011 | West Balmville | N |  | 10 | [13 empty] | NM | N | SOLAREDGE SE10000 A-US | 2015-09-17 | 2015-09-23 | 4 | 2015-09-23 | [14 empty] | 2015-11-05 | 2015-11-06 |  | Y
Central Hudson |  | Kasselman Solar | CH-03511 | Catskill | Acra | Greene | 12405 | G | 2041 | South Cairo | N |  | 7.5 | [13 empty] | NM | N | 30 ENPHASE M-250 US | 2015-09-18 | 2015-09-30 | 8 | 2015-09-30 | [14 empty] | 2015-12-28 | 2016-01-05 |  | Y
Central Hudson |  | Kasselman Solar | CH-03521 | Catskill | Coxsackie | Greene | 12051 | G | 1071 | Coxsackie | N |  | 3.75 | [13 empty] | NM | N | 15 ENPHASE M250 US | 2015-09-18 | 2015-09-30 | 8 | 2015-09-30 | [14 empty] | 2015-12-09 | 2015-12-16 |  | Y
Central Hudson |  | New York State Solar Farm | CH-04087 | Newburgh | Highland | Ulster | 12528 | G | 5012 | Modena | N |  | 7.6 | [13 empty] | NM | N | SMA-SB-3800-TL-US-22 (2) | 2015-09-18 | 2015-09-23 | 3 | 2015-09-23 | [14 empty] | 2015-09-30 | 2015-09-30 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | NRG Home Solar | CH-04235 | Catskill | Round Top | Greene | 12473 | G | 2042 | South Cairo | N |  | 2.5 | [13 empty] | NM | N | 10 ENPHASE M250-60-2LL-S22 | 2015-09-18 | 2015-09-30 | 8 | 2015-09-30 | [14 empty] | 2015-12-03 | 2015-12-09 |  | Y
Central Hudson |  | SolarCity | CH-06122 | Fishkill | Hopewell Junction | Dutchess | 12533 | G | 8093 | Fishkill Plains | N | CH-06122 | 3 | [13 empty] | NM | N | ABB PVI-3.0-OUTD-S US | 2015-09-18 | 2015-09-23 | 3 | 2015-09-23 | [14 empty] | 2015-10-08 | 2015-10-15 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07154 | Newburgh | Maybrook | Orange | 12543 | G | 5052 | Maybrook | N | CH-07154 | 3 | [13 empty] | NM | N | ABB PVI-3.0-OUTD-S-US-Z- | 2015-09-18 | 2015-09-24 | 4 | 2015-09-24 | [14 empty] | 2015-12-15 | 2015-12-15 |  | Y
Central Hudson |  | Kasselman Solar | CH-03516 | Catskill | Westerlo | Albany | 12193 | G | 1091 | Westerlo | N |  | 9.5 | [13 empty] | NM | N | 38 ENPHASE M-250-US | 2015-09-21 | 2015-10-02 | 9 | 2015-10-02 | [14 empty] | 2016-01-06 | 2016-01-13 |  | Y
Central Hudson |  | Monolith Solar Associates LLC | CH-02679 | Catskill | Freehold | Greene | 12431 | G | 2071 | Freehold | N |  | 7.6 | [13 empty] | NM | N | SOLAR EDGE SE7600A-US | 2015-09-21 | 2015-10-02 | 9 | 2015-10-02 | [14 empty] | 2016-05-24 | 2016-05-31 |  | Y
Central Hudson |  | SolarCity | CH-06324 | Newburgh | Marlboro | Ulster | 12542 | G | 5001 | Marlboro | N |  | 15.8 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 FRONIUS PRIMO 8.2 | 2015-09-21 | 2015-09-24 | 3 | 2015-09-24 | [14 empty] | 2015-11-05 | 2015-11-06 |  | Y
Central Hudson |  | SolarCity | CH-06474 | Catskill | Ravena | Albany | 12143 | G | 1082 | New Baltimore | N |  | 7.2 | [13 empty] | NM | N | 2 ABB PVI-3.6-OUTD-S-US-Z | 2015-09-21 | 2015-10-02 | 9 | 2015-10-02 | [14 empty] | 2015-10-16 | 2015-10-21 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07476 | Newburgh | Maybrook | Orange | 12543 | G | 4026 | Coldenham | N |  | 5 | [13 empty] | NM | N | ABB PVI-5000-OUTD=US-Z-A | 2015-09-21 | 2015-09-24 | 3 | 2015-09-24 | [14 empty] | 2015-11-09 | 2015-11-09 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-03421 | Newburgh | Newburgh | Orange | 12550 | G | 4012 | West Balmville | N |  | 7.7 | [13 empty] | NM | N | SMA SB7700TL-US-22 | 2015-09-22 | 2015-09-24 | 2 | 2015-09-24 | [14 empty] | 2015-12-02 | 2015-12-02 |  | Y
Central Hudson |  | Kasselman Solar | CH-03513 | Catskill | Catskill | Greene | 12414 | G | 2005 | North Catskill | N | CH-03513 | 7.25 | [13 empty] | NM | N | 29 ENPHASE M250-US | 2015-09-22 | 2015-10-06 | 10 | 2015-10-06 | [14 empty] | 2015-12-28 | 2016-01-05 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03592 | Newburgh | Marlboro | Ulster | 12542 | G | 5004 | Marlboro | N |  | 10 | [13 empty] | NM | N | SOLAREDGE 10000A-US | 2015-09-22 | 2015-09-25 | 3 | 2015-09-25 | [14 empty] | 2015-11-05 | 2015-11-06 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03710 | Newburgh | Highland | Ulster | 12528 | G | 5012 | Modena | N |  | 11.4 | [13 empty] | NM | N | SOLAREDGE SE11400 A-US | 2015-09-22 | 2015-09-24 | 2 | 2015-09-24 | [14 empty] | 2015-10-27 | 2015-10-30 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03802 | Newburgh | New Paltz | Ulster | 12561 | G | 5023 | Ohioville | N |  | 3.8 | [13 empty] | NM | N | SOLAREDGE 3800A-US | 2015-09-22 | 2015-09-25 | 3 | 2015-09-25 | [14 empty] | 2015-11-13 | 2015-11-13 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03833 | Newburgh | Gardiner | Ulster | 12525 | G | 5034 | Galeville | N | CH-03608 | 2.5 | [13 empty] | NM | N | ABB 2.5 S-US | 2015-09-22 | 2015-09-28 | 4 | 2015-09-28 | [14 empty] | 2015-10-27 | 2015-10-30 |  | Y
Central Hudson |  | Monolith Solar Associates LLC | CH-02666 | Catskill | W Coxsackie | Greene | 12192 | G | 1076 | Coxsackie | N |  | 10 | [13 empty] | NM | N | SOLAREDGE SE10000A-US | 2015-09-22 | 2015-10-06 | 10 | 2015-10-06 | [14 empty] | 2016-03-09 | 2016-03-16 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08654 | Catskill | W Coxsackie |  | 12192 | G | 1083 | New Baltimore | TBD |  | 5.59 | [13 empty] | NM | N | 26 ENPHASE M215-60-2LL-S2-XZC | 2015-09-22 | 2015-10-02 | 8 | 2015-10-02 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | Sol Providers | CH-08930 | Poughkeepsie | Pine Plns | Dutchess | 12567 | G | 7091 | Pulvers Corners | N |  | 12 | [13 empty] | NM | N | (2) SMA SB6000-US-22 | 2015-09-29 | 2015-10-13 | 10 | 2015-10-13 | [14 empty] | 2015-11-06 | 2015-11-13 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Sungevity Inc | CH-09568 | Poughkeepsie | Poughkeepsie |  | 12603 | G | 6093 | Manchester | TBD |  | 8 | [13 empty] | NM | N | (1) ABB PVI-4.2-OUTD-S-US-A (1) ABB PVI-3.8-OUTD-S-US-A | 2015-10-07 | 2015-10-14 | 5 | 2015-10-14 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | Lighthouse Solar | CH-03801 | Newburgh | New Paltz | Ulster | 12561 | G | 5023 | Ohioville | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE 7600 A-US | 2015-09-23 | 2015-09-29 | 4 | 2015-09-29 | [14 empty] | 2016-12-09 | 2016-12-09 |  | Y
Central Hudson |  | Lotus Energy Inc. | CH-03843 | Kingston | Accord | Ulster | 12404 | G | 3024 | High Falls | N |  | 6 | [13 empty] | NM | N | SMA SB6000TL-US 22 | 2015-09-23 | 2015-10-07 | 10 | 2015-10-07 | [14 empty] | 2015-10-26 | 2015-11-02 |  | Y
Central Hudson |  | SolarCity | CH-05087 | Newburgh | Rock Tvrn | Orange | 12575 | G | 4097 | Bethlehem Rd | N |  | 5 | [13 empty] | NM | N | ABB PVI-5000-OUTD-US-Z-A | 2015-09-23 | 2015-09-29 | 4 | 2015-09-29 | [14 empty] | 2015-11-03 | 2015-11-05 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-05969 | Poughkeepsie | Ancram | Columbia | 12502 | G | 7085 | Ancram | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2015-09-23 | 2015-09-30 | 5 | 2015-09-30 | [14 empty] | 2015-11-02 | 2015-11-06 |  | Y
Central Hudson |  | SolarCity | CH-07583 | Fishkill | Beacon | Dutchess | 12508 | G | 8085 | Tioronda | N |  | 4.2 | [13 empty] | NM | N | ABB PVI-4.2-OUTD-S-US-Z- | 2015-09-23 | 2015-09-29 | 4 | 2015-09-29 | [14 empty] | 2016-01-11 | 2016-01-13 |  | Y
Central Hudson |  | SunBlue Energy | CH-09133 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8072 | Shenandoah | N |  | 7 | [13 empty] | NM | N | SMA SB7000TL-US 22 | 2015-09-23 | 2015-09-29 | 4 | 2015-09-29 | [14 empty] | 2015-11-09 | 2015-11-10 |  | Y
Central Hudson |  | Kirchhoff Green Energy LLC | CH-03542 | Poughkeepsie | Stanfordvl | Dutchess | 12581 | G | 7072 | Stanfordville | N |  | 7.3 | [13 empty] | NM | N | ABB UNO 7.6 | 2015-12-02 | 2015-12-04 | 2 | 2015-12-04 | [14 empty] | 2016-01-22 | 2016-01-28 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Kirchhoff Green Energy LLC | CH-03552 | Poughkeepsie | Clinton Corners | Dutchess | 12514 | G | 7071 | Stanfordville | N |  | 7 | [13 empty] | NM | N | (28) ENPHASE M250 | 2015-10-01 | 2015-10-07 | 4 | 2015-10-07 | [14 empty] | 2016-01-07 | 2016-01-14 |  | Y
Central Hudson |  | New York State Solar Farm | CH-04061 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 6075 | East Park | N |  | 3.8 | [13 empty] | NM | N | SMA AMERICA SE3800 | 2015-10-09 | 2015-10-09 | 0 | 2015-10-09 | [14 empty] | 2015-10-23 | 2015-10-26 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Direct Energy Solar | CH-01069 | Newburgh | Wallkill | Ulster | 12589 | G | 5041 | East Walden | N |  | 7.53 | [13 empty] | NM | N | ENPHASE M215 60-2LL-S22 (35) | 2015-09-24 | 2015-09-29 | 3 | 2015-09-29 | [14 empty] | 2015-12-23 | 2015-12-31 |  | Y
Central Hudson |  | SolarCity | CH-05204 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 6092 | Manchester | N |  | 8.2 | [13 empty] | NM | N | FRONIUS PRIMO 8.2 | 2015-09-24 | 2015-10-01 | 5 | 2015-10-01 | [14 empty] | 2015-10-26 | 2015-11-02 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-05545 | Catskill | Freehold | Greene | 12431 | G | 2061 | Freehold | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2015-09-24 | 2015-10-07 | 9 | 2015-10-07 | [14 empty] | 2015-12-15 | 2015-12-22 |  | Y
Central Hudson |  | SolarCity | CH-05954 | Poughkeepsie | Milan | Dutchess | 12571 | G | 7061 | Milan | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000-OUTD-US-Z-A | 2015-09-24 | 2015-10-01 | 5 | 2015-10-01 | [14 empty] | 2015-12-21 | 2015-12-21 |  | Y
Central Hudson |  | SolarCity | CH-06225 | Newburgh | Newburgh | Orange | 12550 | G | 4024 | Coldenham | N |  | 3.6 | [13 empty] | NM | N | ABB PVI-3.6-OUTD-S-US-Z- | 2015-09-24 | 2015-09-30 | 4 | 2015-09-30 | [14 empty] | 2015-10-20 | 2015-10-22 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06964 | Newburgh | New Paltz | Ulster | 12561 | G | 5024 | Ohioville | N |  | 10 | [13 empty] | NM | N | ABB PVI-5000-OUTD-US-Z-A ABB PVI-5000-OUTD-US-Z-A | 2015-09-24 | 2015-09-29 | 3 | 2015-09-29 | [14 empty] | 2015-11-06 | 2015-11-06 |  | Y
Central Hudson |  | SolarCity | CH-07286 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 6073 | East Park | N |  | 3.6 | [13 empty] | NM | N | ABB PVI-3.6-OUTD-S-US-Z | 2015-10-02 | 2015-10-09 | 5 | 2015-10-09 | [14 empty] | 2015-10-21 | 2015-10-28 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07590 | Newburgh | Clintondale |  | 12515 | G | 5081 | Highland | TBD |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2015-12-04 | [17 empty] | 2015-12-21 |  |  | W |  | Customer already had net meter prior to application.
Central Hudson |  | SolarCity | CH-07718 | Newburgh | Clintondale | Ulster | 12515 | G | 5081 | Highland | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2015-12-04 | 2015-12-04 | 0 | 2015-12-04 | [14 empty] | 2015-12-21 | 2015-12-30 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Sol Providers | CH-08936 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 9 | [13 empty] | NM | N | SMA 3000TL-US-22 SMA 6000TL-US-22 | 2015-09-24 | 2015-09-30 | 4 | 2015-09-30 | [14 empty] | 2015-11-10 | 2015-11-10 |  | Y
Central Hudson |  | Sungevity Inc | CH-09312 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6095 | Manchester | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000-OUTD-US-A | 2015-09-24 | 2015-10-01 | 5 | 2015-10-01 | [14 empty] | 2015-11-05 | 2015-11-12 |  | Y
Central Hudson |  | SolarCity | CH-04933 | Fishkill | Fishkill | Dutchess | 12524 | G | 8065 | Merritt Park | N |  | 4.2 | [13 empty] | NM | N | ABB PVI-4.2-OUTD-S-US-Z- | 2015-09-25 | 2015-10-01 | 4 | 2015-10-01 | [14 empty] | 2015-11-02 | 2015-11-06 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-04934 | Fishkill | Beacon | Dutchess | 12508 | G | 8087 | Tioronda | N |  | 10 | [13 empty] | NM | N | ABB PVI-5000-OUTD-US-Z-A (2) | 2015-09-25 | 2015-10-01 | 4 | 2015-10-01 | [14 empty] | 2015-11-09 | 2015-11-09 |  | Y
Central Hudson |  | SolarCity | CH-05712 | Kingston | Kerhonkson | Ulster | 12446 | G | 3081 | Kerhonkson | N |  | 5 | [13 empty] | NM | N | ABB PVI-5000-OUTD US | 2015-09-25 | 2015-10-09 | 10 | 2015-10-09 | [14 empty] | 2015-10-19 | 2015-10-26 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06671 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6008 | Reynolds Hill | N |  | 3.6 | [13 empty] | NM | N | ABB PVI-3.6-OUTD-US-Z-A | 2015-10-06 | 2015-10-12 | 4 | 2015-10-12 | [14 empty] | 2015-12-31 | 2016-01-08 |  | Y
Central Hudson |  | Apex Solar Power | CH-03099 | Newburgh | Montgomery | Orange | 12549 | G | 5041 | East Walden | N |  | 12 | [13 empty] | NM | N | SOLAR EDGE SE6000A-US (2) | 2015-09-28 | 2015-10-06 | 6 | 2015-10-06 | [14 empty] | 2015-12-30 | 2016-01-07 |  | Y
Central Hudson |  | Kirchhoff Green Energy LLC | CH-00258 | Fishkill | Fishkill |  | 12590 | G | 8062 | Merritt Park | N |  | 4.72 | [13 empty] | NM | N | ENPHASE M 215 (21) | 2016-06-29 | 2016-07-12 | 8 | 2016-07-12 | [17 empty] | W
Central Hudson |  | New York State Solar Farm | CH-03936 | Newburgh | Clintondale | Ulster | 12515 | G | 5081 | Highland | N |  | 16 | [13 empty] | NM | N | ABB POWERONE PVI 5.000 (2) ABB POWERONE PVI 6.000 (1) | 2015-09-28 | 2015-10-12 | 10 | 2015-10-12 | [8 empty] | 350 | 350 |  |  |  |  | 2015-10-14 | 2015-10-20 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | New York State Solar Farm | CH-03993 | Newburgh | New Paltz | Ulster | 12561 | G | 5024 | Ohioville | N |  | 6.8 | [13 empty] | NM | N | SMA AMERICA SB-TL 3.000 SMA AMERICA SB-TL 3.800 | 2015-09-28 | 2015-10-05 | 5 | 2015-10-05 | [14 empty] | 2015-10-12 | 2015-10-15 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | New York State Solar Farm | CH-04037 | Newburgh | Newburgh | Orange | 12550 | G | 4022 | Coldenham | N |  | 25 | [13 empty] | NM | N | ABB POWERONE PVI 5.000 (5) | 2015-09-28 | 2015-10-05 | 5 | 2015-10-05 | [8 empty] | 350 | 350 |  |  |  |  | 2015-12-21 | 2015-12-30 |  | Y
Central Hudson |  | New York State Solar Farm | CH-04046 | Newburgh | New Paltz | Ulster | 12561 | G | 5031 | Galeville | N |  | 7.6 | [13 empty] | NM | N | SMA AMERICA SB-TL 3.800 (2) | 2015-09-28 | 2015-10-06 | 6 | 2015-10-06 | [14 empty] | 2015-10-12 | 2015-10-15 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | New York State Solar Farm | CH-04062 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8091 | Fishkill Plains | N |  | 8.8 | [13 empty] | NM | N | (1) SMA AMERICA SB-TL 3.800 (1) SMA AMERICA SB-TL 5.000 | 2015-10-06 | 2015-10-12 | 4 | 2015-10-12 | [14 empty] | 2015-11-16 | 2015-11-16 |  | Y
Central Hudson |  | Cedar Electric | CH-00770 | Fishkill | Garrison | Putnam | 10524 | G | 8066 | Merritt Park | N |  | 10.5 | [13 empty] | NM | N | SMA SB8000US SMA SB2500HFUS | 2015-10-14 | 2015-10-14 | 0 | 2015-10-14 | [14 empty] | 2015-11-04 | 2015-11-10 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-05142 | Fishkill | Stormvl | Dutchess | 12582 | G | 8093 | Fishkill Plains | N |  | 5 | [13 empty] | NM | N | ABB PVI-5000-OUTD-US | 2015-09-28 | 2015-10-05 | 5 | 2015-10-05 | [14 empty] | 2015-10-26 | 2015-10-29 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-05208 | Kingston | New Paltz | Ulster | 12561 | G | 3041 | Sturgeon Pool | N |  | 12 | [13 empty] | NM | N | 2 ABB PVI-6000-OUTD-US-Z-A | 2015-09-28 | 2015-10-12 | 10 | 2015-10-12 | [14 empty] | 2015-11-16 | 2015-11-23 |  | Y
Central Hudson |  | SolarCity | CH-05220 | Newburgh | Highland | Ulster | 12528 | G | 5083 | Highland | N |  | 4.2 | [13 empty] | NM | N | ABB PVI-4.2-OUTD-S-US-Z | 2015-09-28 | 2015-10-05 | 5 | 2015-10-05 | [14 empty] | 2015-11-18 | 2015-11-24 |  | Y
Central Hudson |  | SolarCity | CH-05222 | Newburgh | New Paltz | Ulster | 12561 | G | 5024 | Ohioville | N |  | 3.6 | [13 empty] | NM | N | ABB PVI-3.6-OUTD-S-US-Z- | 2015-09-28 | 2015-10-05 | 5 | 2015-10-05 | [14 empty] | 2015-10-26 | 2015-10-29 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-05380 | Poughkeepsie | Lagrangevl |  | 12540 | G | 6057 | Todd Hill | TBD |  | 11 | [13 empty] | NM | N | (1) ABB PVI-6000-OUTD-US-Z-A (1) ABB PVI-5000-OUTD-US-Z-A | 2015-09-28 | 2015-10-05 | 5 | 2015-10-05 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | SolarCity | CH-05454 | Newburgh | Newburgh | Orange | 12550 | G | 4022 | Coldenham | N |  | 3 | [13 empty] | NM | N | ABB PVI-3.0-OUTD-S-US-Z- | 2015-09-28 | 2015-10-06 | 6 | 2015-10-06 | [14 empty] | 2015-11-17 | 2015-11-17 |  | Y
Central Hudson |  | SolarCity | CH-05651 | Kingston | Accord | Ulster | 12404 | G | 3024 | High Falls | N |  | 4.2 | [13 empty] | NM | N | ABB PVI-4.2-OUTD-S US | 2015-09-28 | 2015-10-12 | 10 | 2015-10-12 | [14 empty] | 2015-11-09 | 2015-11-16 |  | Y
Central Hudson |  | SolarCity | CH-06196 | Newburgh | Newburgh | Orange | 12550 | G | 4014 | West Balmville | N |  | 7.2 | [13 empty] | NM | N | ABB PVI-3.6-OUTD-S-US-Z- (2) | 2015-09-28 | 2015-10-05 | 5 | 2015-10-05 | [14 empty] | 2015-10-21 | 2015-10-23 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07005 | Newburgh | Newburgh | Orange | 12550 | G | 4012 | West Balmville | N |  | 3.6 | [13 empty] | NM | N | ABB PVI-3.6-OUTD-S-US-Z- | 2015-09-28 | 2015-10-05 | 5 | 2015-10-05 | [14 empty] | 2015-10-22 | 2015-10-27 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07368 | Fishkill | Fishkill | Dutchess | 12524 | G | 8014 | Forgebrook | N |  | 3 | [13 empty] | NM | N | ABB PVI-3.0-OUTD-S-US-Z- | 2015-10-14 | 2015-10-20 | 4 | 2015-10-20 | [14 empty] | 2015-10-26 | 2015-11-02 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Sol Providers | CH-08938 | Newburgh | Milton | Ulster | 12547 | G | 5002 | Marlboro | N |  | 13 | [13 empty] | NM | N | SMA AMERICA 7000TL-US-22 SMA AMERICA 6000TL-US-22 | 2015-10-28 | 2015-10-28 | 0 | 2015-10-28 | [14 empty] | 2015-11-13 | 2015-11-13 |  | Y
Central Hudson |  | Sol Providers | CH-08961 | Fishkill | Stormvl | Dutchess | 12582 | G | 8095 | Fishkill Plains | N |  | 7.6 | [13 empty] | NM | N | SOLAR EDGE SE7600A-US | 2015-10-06 | 2015-10-12 | 4 | 2015-10-12 | [14 empty] | 2015-11-13 | 2015-11-13 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-03385 | Fishkill | Garrison | Putnam | 10524 | G | 8066 | Merritt Park | N |  | 11.5 | [13 empty] | NM | N | SMA AMERICA SB3800TL-US-22 SMA AMERICA SB7700TL-US-22 | 2015-10-07 | 2015-10-07 | 0 | 2015-10-07 | [14 empty] | 2016-01-14 | 2016-01-15 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-03401 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6094 | Manchester | N |  | 11.4 | [13 empty] | NM | N | Fronius IG Plus A 11.4 | 2015-10-07 | 2015-10-14 | 5 | 2015-10-14 | [14 empty] | 2016-01-29 | 2016-02-05 |  | Y
Central Hudson |  | SolarCity | CH-07594 | Newburgh | Walden | Orange | 12586 | G | 5041 | East Walden | N |  | 10.2 | [13 empty] | NM | N | ABB PVI-6000-OUTD US ABB PVI-4.2-OUTD-S US | 2015-09-29 | 2015-10-06 | 5 | 2015-10-06 | [14 empty] | 2015-12-14 | 2015-12-15 |  | Y
Central Hudson |  | SolarCity | CH-06571 | Kingston | Saugerties | Ulster | 12477 | G | 3002 | Saugerties | N |  | 3.6 | [13 empty] | NM | N | ABB PVI-3.6-OUTD-S US | 2015-09-30 | 2015-09-30 | 0 | 2015-09-30 | [14 empty] | 2015-09-30 | 2015-09-30 |  | Y
Central Hudson |  | Lotus Energy Inc. | CH-03869 | Catskill | Catskill | Greene | 12414 | G | 2001 | North Catskill | N |  | 10 | [13 empty] | RNM | N | 2 SMA 5000TL-US-22 | 2015-10-01 | 2015-10-12 | 7 | 2015-10-12 | [8 empty] | 350 | 350 |  | 2015-12-03 | 2015-12-03 | 2015-12-09 | 2015-12-02 | 2015-12-09 |  | Y
Central Hudson |  | Lotus Energy Inc. | CH-03887 | Kingston | Kingston | Ulster | 12401 | G | 1014 | Boulevard | N |  | 6 | [13 empty] | NM | N | SMA 6000TL-US 22 | 2015-10-01 | 2015-10-13 | 8 | 2015-10-13 | [14 empty] | 2015-11-12 | 2015-11-19 |  | Y
Central Hudson |  | SolarCity | CH-04966 | Poughkeepsie | Millerton | Dutchess | 12546 | G | 7081 | Millerton | N |  | 8.6 | [13 empty] | NM | N | (1) ABB PVI-3.6-OUTD-S-US (1) ABB PVI-5000-OUTD-S-US | 2015-10-01 | 2015-10-08 | 5 | 2015-10-08 | [14 empty] | 2016-01-11 | 2016-01-15 |  | Y
Central Hudson |  | SolarCity | CH-05230 | Newburgh | Montgomery | Orange | 12549 | G | 5054 | Maybrook | N |  | 5 | [13 empty] | NM | N | ABB PVI-5000-OUTD | 2015-10-01 | 2015-10-08 | 5 | 2015-10-08 | [14 empty] | 2015-12-08 | 2015-12-08 |  | Y
Central Hudson |  | SolarCity | CH-05386 | Newburgh | Highland | Ulster | 12528 | G | 5083 | Highland | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2015-10-01 | 2015-10-07 | 4 | 2015-10-07 | [14 empty] | 2015-11-11 | 2015-11-18 |  | Y
Central Hudson |  | SolarCity | CH-05541 | Catskill | Leeds | Greene | 12451 | G | 2006 | North Catskill | N |  | 10.2 | [13 empty] | NM | N | ABB PVI-6000-OUTD-US-Z-A ABB PVI-4.2-OUTD-US-Z | 2015-10-01 | 2015-10-13 | 8 | 2015-10-13 | [8 empty] | 350 | 350 |  | 2015-12-23 | 2015-12-23 | 2016-01-14 | 2016-02-11 | 2016-02-19 |  | Y
Central Hudson |  | SolarCity | CH-05885 | Poughkeepsie | Lagrangevl | Dutchess | 12540 | G | 6055 | Todd Hill | N |  | 9.6 | [13 empty] | NM | N | (1) ABB PVI-6000-OUTD-US-Z-A (1) ABB PVI-3.6-OUTD-S-US-Z-A | 2015-10-01 | 2015-10-15 | 10 | 2015-10-15 | [8 empty] | 350 | 350 |  | 2015-11-09 | 2015-11-09 | 2015-11-13 | 2015-11-13 | 2015-11-20 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06093 | Fishkill | Fishkill | Dutchess | 12524 | G | 8062 | Merritt Park | N |  | 3 | [13 empty] | NM | N | ABB PVI-5000-OUTD-US | 2015-10-01 | 2015-10-08 | 5 | 2015-10-08 | [14 empty] | 2016-04-20 | 2016-04-25 |  | Y
Central Hudson |  | SolarCity | CH-06257 | Newburgh | New Windsor | Orange | 12553 | G | 4045 | Union Ave | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2015-10-01 | 2015-10-08 | 5 | 2015-10-08 | [14 empty] | 2015-11-03 | 2015-11-05 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06818 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8045 | Myers Corners | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2015-10-01 | 2015-10-12 | 7 | 2015-10-12 | [14 empty] | 2016-01-12 | 2016-01-12 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08604 | Catskill | Athens | Greene | 12015 | G | 2002 | North Catskill | N | CH-08604 | 6.45 | [13 empty] | NM | N | 30 ENPHASE M215 60-2LL-S2-XZC | 2015-10-01 | 2015-10-12 | 7 | 2015-10-12 | [14 empty] | 2016-01-04 | 2016-01-11 |  | Y
Central Hudson |  | Sol Providers | CH-08912 | Newburgh | Newburgh |  | 12550 | G | 5004 | Marlboro | TBD |  | 17 | [13 empty] | NM | N | SMA SB5000TL-US-22 (2) SMA SB7000TL-US-22 | 2015-10-09 | 2015-10-15 | 4 | 2015-10-15 | [17 empty] | W
Central Hudson |  | Lighthouse Solar | CH-03836 | Poughkeepsie | Verbank |  | 12585 | G | 6057 | Todd Hill | TBD |  | 10 | [13 empty] | NM | N | SOLAREDGE 10000A-US | 2015-10-09 | 2015-10-09 | 0 | 2015-10-09 | [17 empty] | W
Central Hudson |  | SolarCity | CH-06199 | Newburgh | Newburgh | Orange | 12550 | G | 4014 | West Balmville | N |  | 3 | [13 empty] | NM | N | ABB PVI-3.0-OUTD-S-US-Z- | 2015-10-02 | 2015-10-09 | 5 | 2015-10-09 | [14 empty] | 2015-11-16 | 2015-11-16 |  | Y
Central Hudson |  | Solar Generation | CH-08125 | Kingston | High Fls | Ulster | 12440 | G | 3023 | High Falls | N |  | 9 | [13 empty] | NM | N | SMA SB 6000 TL SMA SB 3000 TL | 2015-10-02 | 2015-10-13 | 7 | 2015-10-13 | [14 empty] | 2015-11-10 | 2015-11-17 |  | Y
Central Hudson |  | Sungevity Inc | CH-09429 | Poughkeepsie | Clinton Corners | Dutchess | 12514 | G | 7071 | Stanfordville | N |  | 6 | [13 empty] | NM | N | (2) ABB PVI-3.0-OUTD-S-US-A | 2015-10-02 | 2015-10-09 | 5 | 2015-10-09 | [14 empty] | 2015-11-17 | 2015-11-24 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-03433 | Newburgh | Milton | Ulster | 12547 | G | 5083 | Highland | N |  | 8.8 | [13 empty] | NM | N | SMA AMERICA SB3800TL-US-22 SMA AMERICA SB5000TL-US-22 | 2015-10-12 | 2015-10-16 | 4 | 2015-10-16 | [14 empty] | 2015-11-30 | 2015-11-30 |  | Y
Central Hudson |  | Kasselman Solar | CH-03515 | Catskill | Coeymans Hollow | Albany | 12046 | G | 1081 | New Baltimore | N |  | 6.5 | [13 empty] | NM | N | 26 ENPHASE M-250 US | 2015-10-05 | 2015-10-13 | 6 | 2015-10-13 | [14 empty] | 2015-12-28 | 2016-01-05 |  | Y
Central Hudson |  | Kasselman Solar | CH-03523 | Catskill | Ravena | Albany | 12143 | G | 1081 | New Baltimore | N | CH-03523 | 6 | [13 empty] | NM | N | 24 ENPHASE M250-US | 2015-10-05 | 2015-10-13 | 6 | 2015-10-13 | [14 empty] | 2015-12-28 | 2016-01-05 |  | Y
Central Hudson |  | Direct Energy Solar | CH-01007 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7053 | Rhinebeck | N |  | 7 | [13 empty] | NM | N | (28) ENPHASE M250 60-2LL-S22 | 2015-10-05 | 2015-10-12 | 5 | 2015-10-12 | [14 empty] | 2015-11-16 | 2015-11-23 |  | Y
Central Hudson |  | Direct Energy Solar | CH-01080 | Poughkeepsie | Rhinebeck |  | 12572 | G | 7052 | Rhinebeck | TBD |  | 2.58 | [13 empty] | NM | N | (12) ENPHASE M215 60-2LL-S22 | 2015-10-05 | 2015-10-12 | 5 | 2015-10-12 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | SolarCity | CH-05102 | Fishkill | Cold Spg | Putnam | 10516 | G | 8063 | Merritt Park | N |  | 4.2 | [13 empty] | NM | N | ABB PVI-4.2-OUTD-SUS | 2015-10-05 | 2015-10-09 | 4 | 2015-10-09 | [14 empty] | 2015-12-08 | 2015-12-08 |  | Y
Central Hudson |  | SolarCity | CH-05233 | Newburgh | Clintondale | Ulster | 12515 | G | 5024 | Ohioville | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000-OUTD US | 2015-10-05 | 2015-10-09 | 4 | 2015-10-09 | [14 empty] | 2015-11-16 | 2015-11-16 |  | Y
Central Hudson |  | SolarCity | CH-07810 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6045 | Spackenkill | N | CH-06616 | 3.6 | [13 empty] | NM | N | ABB PVI-3.6-OUTD-S | 2015-11-16 | 2015-11-23 | 5 | 2015-11-23 | [14 empty] | 2015-12-14 | 2015-12-17 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07901 | Newburgh | Highland |  | 12528 | G | 5081 | Highland | TBD |  | 10 | [13 empty] | NM | N | ABB PVI-5000-OUTD US (2) | 2015-10-05 | 2015-10-09 | 4 | 2015-10-09 | [17 empty] | W
Central Hudson |  | Infinity Solar Systems | CH-03492 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8045 | Myers Corners | N |  | 8 | [13 empty] | NM | N | SMA SB3000TL-US-22 SMA SB5000TL-US-22 | 2015-10-12 | 2015-10-16 | 4 | 2015-10-16 | [14 empty] | 2016-01-18 | 2016-01-25 |  | Y
Central Hudson |  | New York State Solar Farm | CH-04021 | Kingston | West Shokan | Ulster | 12494 | G | 3011 | Woodstock | N |  | 6 | [13 empty] | NM | N | SOLAREDGE 6000SE | 2015-10-06 | 2015-10-14 | 6 | 2015-10-14 | [14 empty] | 2015-10-20 | 2015-10-27 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | New York State Solar Farm | CH-04023 | Kingston | Kingston | Ulster | 12401 | G | 1003 | Jansen Ave | N |  | 6 | [13 empty] | NM | N | SOLAREDGE 6000 SE | 2015-10-06 | 2015-10-14 | 6 | 2015-10-14 | [14 empty] | 2015-11-16 | 2015-11-23 |  | Y
Central Hudson |  | Direct Energy Solar | CH-01068 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7052 | Rhinebeck | N |  | 5.16 | [13 empty] | NM | N | (24) ENPHASE M215 60-2LL-S22 | 2015-10-12 | 2015-10-19 | 5 | 2015-10-19 | [14 empty] | 2016-05-10 | 2016-05-16 |  | Y
Central Hudson |  | SolarCity | CH-05439 | Newburgh | Maybrook | Orange | 12543 | G | 4026 | Coldenham | N |  | 3 | [13 empty] | NM | N | ABB PVI-3.0-OUTD-S US | 2015-10-06 | 2015-10-12 | 4 | 2015-10-12 | [14 empty] | 2015-12-15 | 2015-12-15 |  | Y
Central Hudson |  | SolarCity | CH-06344 | Newburgh | Wallkill | Ulster | 12589 | G | 5043 | East Walden | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2015-10-06 | 2015-10-12 | 4 | 2015-10-12 | [14 empty] | 2015-11-02 | 2015-11-04 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07623 | Newburgh | New Windsor | Orange | 12553 | G | 4094 | Bethlehem Rd | N |  | 4.2 | [13 empty] | NM | N | ABB PVI-4.2-OUTD-S-US-Z- | 2015-10-06 | 2015-10-12 | 4 | 2015-10-12 | [14 empty] | 2015-10-29 | 2015-10-30 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Empire Solar Solutions | CH-03337 | Newburgh | Newburgh | Orange | 12550 | G | 4014 | West Balmville | N |  | 7.7 | [13 empty] | NM | N | SMA SB7700/US | 2015-10-14 | 2015-10-20 | 4 | 2015-10-20 | [14 empty] | 2015-12-18 | 2015-12-28 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-03446 | Poughkeepsie | Poughkeepsie |  | 12603 | G | 6093 | Manchester | TBD |  | 5 | [13 empty] | NM | N | SMA America SB5000TL-US-22 | 2015-10-14 | 2015-10-21 | 5 | 2015-10-21 | [17 empty] | W
Central Hudson |  | New York State Solar Farm | CH-03979 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 7011 | Hibernia | N |  | 9.8 | [13 empty] | NM | N | (1) SMA AMERICA SB 3.8 TL (1) SMA AMERICA SB 6.0 TL | 2015-10-14 | 2015-10-21 | 5 | 2015-10-21 | [14 empty] | 2015-11-10 | 2015-11-17 |  | Y
Central Hudson |  | Hudson Solar | CH-02468 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7062 | Milan | N | CH-01863 | 5 | [13 empty] | NM | N | SMA AMERICA SB5000 TL-US-22 | 2015-10-07 | 2015-10-14 | 5 | 2015-10-14 | [14 empty] | 2015-12-22 | 2015-12-29 |  | Y
Central Hudson |  | Paradise Energy Solutions LLC | CH-02828 | Poughkeepsie | Tivoli | Dutchess | 12583 | G | 7054 | Rhinebeck | N | CH-02828 | 16.5 | [13 empty] | NM | N | (66) Enphase M250 | 2015-11-03 | 2015-11-04 | 1 | 2015-11-04 | [14 empty] | 2016-02-02 | 2016-02-08 |  | Y
Central Hudson |  | SolarCity | CH-05653 | Kingston | Accord | Ulster | 12404 | G | 3083 | Kerhonkson | N |  | 12 | [13 empty] | NM | N | 2 ABB PVI-4.2-OUTD-S US | 2015-10-07 | 2015-10-14 | 5 | 2015-10-14 | [14 empty] | 2016-02-29 | 2016-03-07 |  | Y
Central Hudson |  | SolarCity | CH-05933 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6061 | Inwood Ave | N |  | 7.6 | [13 empty] | NM | N | SolarEdge SE7600A-US | 2015-10-07 | 2015-10-14 | 5 | 2015-10-14 | [14 empty] | 2016-02-11 | 2016-02-19 |  | Y
Central Hudson |  | SolarCity | CH-06012 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8091 | Fishkill Plains | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2015-10-07 | 2015-10-13 | 4 | 2015-10-13 | [14 empty] | 2015-11-03 | 2015-11-05 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06744 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6096 | Manchester | N |  | 5 | [13 empty] | NM | N | ABB PVI-5000-OUTD | 2015-10-07 | 2015-10-14 | 5 | 2015-10-14 | [14 empty] | 2015-11-03 | 2015-11-09 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07524 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6042 | Spackenkill | N |  | 3.6 | [13 empty] | NM | N | ABB PVI-3.6-OUTD-S | 2015-10-07 | 2015-10-14 | 5 | 2015-10-14 | [14 empty] | 2015-11-19 | 2015-11-30 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Sungevity Inc | CH-09376 | Newburgh | New Windsor | Orange | 12553 | G | 4045 | Union Ave | N |  | 5 | [13 empty] | NM | N | ABB PVI-5000-OUTD-US-A | 2015-10-13 | 2015-10-16 | 3 | 2015-10-16 | [14 empty] | 2015-11-17 | 2015-11-17 |  | Y
Central Hudson |  | Sungevity Inc | CH-09388 | Newburgh | New Windsor | Orange | 12553 | G | 4095 | Bethlehem Rd | N |  | 3.8 | [13 empty] | NM | N | ABB PVI-3.8-OUTD-S-US-A | 2015-10-07 | 2015-10-12 | 3 | 2015-10-12 | [14 empty] | 2016-03-04 | 2016-03-11 |  | Y
Central Hudson |  | Sungevity Inc | CH-09489 | Newburgh | Newburgh | Orange | 12550 | G | 4012 | West Balmville | N |  | 5 | [13 empty] | NM | N | ABB PVI-5000-OUTD-US-A | 2015-10-13 | 2015-10-16 | 3 | 2015-10-16 | [14 empty] | 2015-11-19 | 2015-11-24 |  | Y
Central Hudson |  | Sungevity Inc | CH-09501 | Newburgh | New Windsor | Orange | 12553 | G | 4095 | Bethlehem Rd | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000-OUTD-US-A | 2015-10-19 | 2015-10-26 | 5 | 2015-10-26 | [14 empty] | 2015-12-08 | 2015-12-08 |  | Y
Central Hudson |  | SolarCity | CH-05299 | Newburgh | Wallkill | Ulster | 12589 | G | 4011 | West Balmville | N |  | 5 | [13 empty] | NM | N | ABB PVI-5000-OUTD US | 2015-10-08 | 2015-10-14 | 4 | 2015-10-14 | [14 empty] | 2015-12-14 | 2015-12-14 |  | Y
Central Hudson |  | SolarCity | CH-05433 | Newburgh | Montgomery | Orange | 12549 | G | 5054 | Maybrook | N |  | 16.4 | [13 empty] | NM | N | FRONIUS PRIMO 8.2 (2) | 2015-10-08 | 2015-10-14 | 4 | 2015-10-14 | [14 empty] | 2015-11-16 | 2015-11-16 |  | Y
Central Hudson |  | SolarCity | CH-06387 | Newburgh | New Windsor | Orange | 12553 | G | 4095 | Bethlehem Rd | N |  | 15.2 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 (2) | 2015-10-08 | 2015-10-14 | 4 | 2015-10-14 | [14 empty] | 2015-11-19 | 2015-11-19 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06979 | Newburgh | Walden | Orange | 12586 | G | 5041 | East Walden | N |  | 15 | [13 empty] | NM | N | ABB PVI-5000-OUTD US (3) | 2015-10-08 | 2015-10-14 | 4 | 2015-10-14 | [14 empty] | 2016-01-04 | 2016-01-11 |  | Y
Central Hudson |  | SolarCity | CH-07296 | Poughkeepsie | Lagrangevl | Dutchess | 12540 | G | 6053 | Todd Hill | N |  | 6 | [13 empty] | NM | N | (2) ABB PVI-3.0-OUTD-S-US-Z | 2015-10-08 | 2015-10-15 | 5 | 2015-10-15 | [14 empty] | 2015-11-03 | 2015-11-09 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Sol Providers | CH-08917 | Kingston | Tillson | Ulster | 12486 | G | 3021 | High Falls | N |  | 6.8 | [13 empty] | NM | N | 1 SMA 3800 TL-US 1 SMA 3000 TL-US | 2015-10-08 | 2015-10-16 | 6 | 2015-10-16 | [14 empty] | 2015-11-04 | 2015-11-11 |  | Y
Central Hudson |  | Sungevity Inc | CH-09194 | Kingston | Cragsmoor | Ulster | 12420 | G | 3078 | Greenfield Rd | N |  | 3.8 | [13 empty] | NM | N | ABB PVI-3.8-OUTD-S-US-A | 2015-10-08 | 2015-10-16 | 6 | 2015-10-16 | [14 empty] | 2015-12-08 | 2015-12-15 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-03394 | Newburgh | Gardiner |  | 12525 | G | 5031 | Galeville | TBD |  | 6 | [13 empty] | NM | N | SMA AMERICA SB6000TL-US-22 | 2015-10-15 | 2015-10-22 | 5 | 2015-10-22 | [17 empty] | W
Central Hudson |  | Infinity Solar Systems | CH-03403 | Poughkeepsie | Verbank | Dutchess | 12585 | G | 6057 | Todd Hill | N |  | 7.7 | [13 empty] | NM | N | SMA AMERICA SB7700TL-US-22 | 2015-10-16 | 2015-10-23 | 5 | 2015-10-23 | [14 empty] | 2015-12-02 | 2015-12-08 |  | Y
Central Hudson |  | SolarCity | CH-06893 | Fishkill | Beacon | Dutchess | 12508 | G | 8016 | Forgebrook | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000-OUTD-US-Z-A | 2015-10-20 | 2015-10-26 | 4 | 2015-10-26 | [14 empty] | 2015-12-03 | 2015-12-03 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-03458 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8096 | Fishkill Plains | N |  | 8.8 | [13 empty] | NM | N | SMA AMERICA SB3800TL-US-22 SMA AMERICA SB5000TL-US-22 | 2015-10-12 | 2015-10-16 | 4 | 2015-10-16 | [14 empty] | 2016-02-01 | 2016-02-01 |  | Y
Central Hudson |  | New York State Solar Farm | CH-03921 | Kingston | Lake Katrine | Ulster | 12449 | G | 2011 | Lincoln Park | N |  | 6 | [13 empty] | NM | N | SMA AMERICA SB6000 TL | 2015-10-12 | 2015-10-19 | 5 | 2015-10-19 | [14 empty] | 2015-11-06 | 2015-11-13 |  | Y
Central Hudson |  | New York State Solar Farm | CH-03941 | Newburgh | Marlboro | Ulster | 12542 | G | 5003 | Marlboro | N |  | 15 | [13 empty] | NM | N | SMA AMERICA SB5000TL-US (3) | 2015-10-12 | 2015-10-16 | 4 | 2015-10-16 | [14 empty] | 2015-11-23 | 2015-11-23 |  | Y
Central Hudson |  | SolarCity | CH-05082 | Newburgh | Wallkill | Ulster | 12589 | G | 5013 | Modena | N |  | 8.2 | [13 empty] | NM | N | FRONIUS PRIMO 8.2 | 2015-10-12 | 2015-10-16 | 4 | 2015-10-16 | [14 empty] | 2015-12-15 | 2015-12-15 |  | Y
Central Hudson |  | SolarCity | CH-05325 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 6073 | East Park | N |  | 11 | [13 empty] | NM | N | ABB PVI-6000-OUTD-US ABB PVI-5000-OUTD-US | 2015-10-22 | 2015-10-29 | 5 | 2015-10-29 | [14 empty] | 2015-11-11 | 2015-11-18 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-05401 | Newburgh | Highland | Ulster | 12528 | G | 5081 | Highland | N |  | 5 | [13 empty] | NM | N | ABB PVI-5000-OUTD-US-Z-A | 2015-10-12 | 2015-10-19 | 5 | 2015-10-19 | [14 empty] | 2015-12-15 | 2015-12-21 |  | Y
Central Hudson |  | SolarCity | CH-05589 | Catskill | Climax | Greene | 12042 | G | 1071 | Coxsackie | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2015-10-12 | 2015-10-19 | 5 | 2015-10-19 | [14 empty] | 2015-11-30 | 2015-12-07 |  | Y
Central Hudson |  | SolarCity | CH-05841 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 6073 | East Park | N |  | 9.6 | [13 empty] | NM | N | ABB PVI-3.6-OUTD-S-US ABB PVI-6000-OUTD-US | 2015-10-20 | 2015-10-27 | 5 | 2015-10-27 | [14 empty] | 2015-12-15 | 2015-12-21 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-05915 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6051 | Todd Hill | N |  | 7.2 | [13 empty] | NM | N | ABB PVI-3.0-OUTD-S-US-Z- ABB PVI-4.2-OUTD-S-US-Z- | 2015-10-12 | 2015-10-19 | 5 | 2015-10-19 | [14 empty] | 2015-11-23 | 2015-12-01 |  | Y
Central Hudson |  | SolarCity | CH-05984 | Newburgh | Highland | Ulster | 12528 | G | 5022 | Ohioville | N | CH-05984 | 3 | [13 empty] | NM | N | ABB PVI-3.0-OUTD-S US | 2015-10-12 | 2015-10-19 | 5 | 2015-10-19 | [14 empty] | 2015-11-02 | 2015-11-06 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06627 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6011 | Sand Dock | N |  | 3 | [13 empty] | NM | N | SOLAREDGE SE3000A-US-ZB-U | 2015-10-12 | 2015-10-19 | 5 | 2015-10-19 | [14 empty] | 2015-12-08 | 2015-12-11 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06926 | Fishkill | Beacon | Dutchess | 12508 | G | 8017 | Forgebrook | N |  | 3.6 | [13 empty] | NM | N | ABB PVI-3.6-OUTD-S US | 2015-10-12 | 2015-10-23 | 9 | 2015-10-23 | [14 empty] | 2015-11-16 | 2015-11-16 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07262 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6042 | Spackenkill | N |  | 3 | [13 empty] | NM | N | ABB PVI-3.0-OUTD-S-US | 2015-10-12 | 2015-10-20 | 6 | 2015-10-20 | [14 empty] | 2015-11-11 | 2015-11-18 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Solar Alchemy | CH-09006 | Kingston | Saugerties | Ulster | 12477 | G | 1021 | East Kingston | N | CH-00823 | 14 | [13 empty] | NM | N | 2 SMA SB 7000 | 2015-10-30 | 2015-12-07 | 24 | 2015-12-07 | [14 empty] | 2016-03-10 | 2016-03-17 |  | Y
Central Hudson |  | SolarCity | CH-04997 | Kingston | Kingston |  | 12401 | G | 1013 | Boulevard | TBD |  | 15.8 | [13 empty] | NM | N | 1 FRONIUS PRIMO 7.6 1 FRONIUS PRIMO 8.2 | 2015-10-13 | 2015-10-19 | 4 | 2015-10-19 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | SolarCity | CH-05122 | Newburgh | Gardiner | Ulster | 12525 | G | 5011 | Modena | N |  | 12 | [13 empty] | NM | N | ABB PVI-6000-OUTD-US (2) | 2015-10-13 | 2015-10-19 | 4 | 2015-10-19 | [14 empty] | 2015-11-16 | 2015-11-16 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-05192 | Fishkill | Fishkill | Dutchess | 12524 | G | 8094 | Fishkill Plains | N |  | 10.2 | [13 empty] | NM | N | ABB PVI-6000-OUTD-US ABB PVI-4.2-OUTD-S-US | 2015-10-13 | 2015-10-16 | 3 | 2015-10-16 | [14 empty] | 2015-12-14 | 2015-12-15 |  | Y
Central Hudson |  | SolarCity | CH-05435 | Poughkeepsie | Lagrangeville | Dutchess | 12540 | G | 6053 | Todd Hill | N |  | 7.2 | [13 empty] | NM | N | (2) ABB PVI-3.6-OUTD-S-US | 2015-10-13 | 2015-10-20 | 5 | 2015-10-20 | [14 empty] | 2015-12-16 | 2015-12-22 |  | Y
Central Hudson |  | SolarCity | CH-05547 | Catskill | Earlton | Greene | 12058 | G | 2005 | North Catskill | N |  | 5 | [13 empty] | NM | N | ABB PVI-5000-OUTD-US | 2015-10-13 | 2015-10-19 | 4 | 2015-10-19 | [14 empty] | 2015-12-18 | 2015-12-29 |  | Y
Central Hudson |  | SolarCity | CH-05952 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7054 | Rhinebeck | N |  | 5 | [13 empty] | NM | N | ABB PVI-5000-OUTD-US | 2015-10-13 | 2015-10-20 | 5 | 2015-10-20 | [14 empty] | 2015-12-15 | 2015-12-21 |  | Y
Central Hudson |  | SolarCity | CH-05965 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7062 | Milan | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2015-10-13 | 2015-10-21 | 6 | 2015-10-21 | [14 empty] | 2015-12-15 | 2015-12-21 |  | Y
Central Hudson |  | SolarCity | CH-06316 | Newburgh | Newburgh | Orange | 12550 | G | 5004 | Marlboro | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2015-10-13 | 2015-10-16 | 3 | 2015-10-16 | [14 empty] | 2015-12-08 | 2015-12-08 |  | Y
Central Hudson |  | SolarCity | CH-06325 | Newburgh | Marlboro | Ulster | 12542 | G | 5001 | Marlboro | N |  | 12 | [13 empty] | NM | N | ABB PVI-3.6-OUTD-S-US (1) ABB PVI-4.2-OUTD-S-US (2) | 2015-10-13 | 2015-10-16 | 3 | 2015-10-16 | [14 empty] | 2015-12-14 | 2015-12-14 |  | Y
Central Hudson |  | SolarCity | CH-06416 | Newburgh | Montgomery | Orange | 12549 | G | 5072 | Montgomery | N |  | 3 | [13 empty] | NM | N | SOLAREDGE SE3000A-US | 2015-10-13 | 2015-10-19 | 4 | 2015-10-19 | [14 empty] | 2015-12-15 | 2015-12-15 |  | Y
Central Hudson |  | SolarCity | CH-07056 | Newburgh | Wallkill | Ulster | 12589 | G | 4011 | West Balmville | N |  | 12 | [13 empty] | NM | N | ABB PVI-6000-OUTD-US (2) | 2016-02-11 | 2016-02-26 | 10 | 2016-02-26 | [14 empty] | 2016-03-01 | 2016-03-08 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Infinity Solar Systems | CH-03482 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8046 | Myers Corners | N |  | 7.7 | [13 empty] | NM | N | SMA AMERICA SB7700TL-US-22 | 2015-10-14 | 2015-10-20 | 4 | 2015-10-20 | [14 empty] | 2015-12-15 | 2015-12-16 |  | Y
Central Hudson |  | Apex Solar Power | CH-00684 | Fishkill | Beacon |  | 12508 | G | 8051 | North Chelsea | TBD |  | 3.8 | [13 empty] | NM | N | SOLAREDGE SE3800A-US | 2015-10-14 | 2015-10-20 | 4 | 2015-10-20 | [17 empty] | W |  | Contractor advised that customer is no longer installing solar.
Central Hudson |  | SolarCity | CH-05159 | Fishkill | Fishkill | Dutchess | 12524 | G | 8065 | Merritt Park | N |  | 3 | [13 empty] | NM | N | ABB PVI-3.0-OUTD-S US | 2015-10-14 | 2015-10-20 | 4 | 2015-10-20 | [14 empty] | 2015-12-15 | 2015-12-15 |  | Y
Central Hudson |  | SolarCity | CH-05211 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8043 | Myers Corners | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2015-10-14 | 2015-10-20 | 4 | 2015-10-20 | [14 empty] | 2016-01-22 | 2016-01-26 |  | Y
Central Hudson |  | SolarCity | CH-05503 | Catskill | Catskill | Greene | 12414 | G | 2042 | South Cairo | N |  | 24 | [13 empty] | NM | N | 2 FRONIUS PRIMO 8.2 1 FRONIUS PRIMO 7.6 | 2015-10-14 | 2015-10-21 | 5 | 2015-10-21 | [14 empty] | 2016-02-24 | 2016-03-02 |  | Y
Central Hudson |  | SolarCity | CH-05569 | Catskill | Westerlo | Albany | 12193 | G | 1091 | Westerlo | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000-OUTD US | 2015-11-16 | 2015-11-24 | 6 | 2015-11-24 | [14 empty] | 2015-12-15 | 2015-12-22 |  | Y
Central Hudson |  | SolarCity | CH-06436 | Catskill | Palenvl | Greene | 12463 | G | 2001 | North Catskill | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2015-10-14 | 2015-10-21 | 5 | 2015-10-21 | [14 empty] | 2015-12-14 | 2015-12-21 |  | Y
Central Hudson |  | SolarCity | CH-06460 | Catskill | S Westerlo |  | 12083 | G | 1091 | Westerlo | TBD |  | 10.2 | [13 empty] | NM | N | ABB PVI-6000-OUTD US ABB PVI-4.2-OUTD US | 2015-10-14 | 2015-10-21 | 5 | 2015-10-21 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | SolarCity | CH-07031 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 7.2 | [13 empty] | NM | N | ABB PVI-3.6-OUTD-S US (2) | 2015-10-14 | 2015-10-20 | 4 | 2015-10-20 | [14 empty] | 2015-12-14 | 2015-12-14 |  | Y
Central Hudson |  | Sungevity Inc | CH-09363 | Newburgh | New Paltz | Ulster | 12561 | G | 5031 | Galeville | N |  | 3.8 | [13 empty] | NM | N | ABB PVI-3.8-OUTD-S-US-A | 2015-10-14 | 2015-10-20 | 4 | 2015-10-20 | [14 empty] | 2015-12-15 | 2015-12-16 |  | Y
Central Hudson |  | Sungevity Inc | CH-09418 | Kingston | Kingston | Ulster | 12401 | G | 2091 | Hurley Ave | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000-OUTD-US-A | 2015-10-14 | 2015-10-21 | 5 | 2015-10-21 | [14 empty] | 2016-01-22 | 2016-01-29 |  | Y
Central Hudson |  | SolarCity | CH-05221 | Newburgh | Highland | Ulster | 12528 | G | 5083 | Highland | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2015-10-15 | 2015-10-22 | 5 | 2015-10-22 | [14 empty] | 2015-12-09 | 2015-12-15 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-05834 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 7011 | Hibernia | N |  | 10.2 | [13 empty] | NM | N | ABB PVI-6000-OUTD-US ABB PVI-4.2-OUTD-S-US | 2015-10-15 | 2015-10-22 | 5 | 2015-10-22 | [8 empty] | 350 | 350 |  | 2015-12-11 | 2015-12-11 | 2016-01-04 | 2016-01-04 | 2016-01-06 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06599 | Kingston | Kingston | Ulster | 12401 | G | 2012 | Lincoln Park | N |  | 3.6 | [13 empty] | NM | N | ABB PVI-3.6-OUTD-S US | 2015-10-15 | 2015-10-21 | 4 | 2015-10-21 | [14 empty] | 2015-12-10 | 2015-12-17 |  | Y
Central Hudson |  | SolarCity | CH-07553 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7054 | Rhinebeck | N |  | 5 | [13 empty] | NM | N | ABB PVI-5000-OUTD-S | 2015-10-15 | 2015-10-22 | 5 | 2015-10-22 | [14 empty] | 2015-12-09 | 2015-12-15 |  | Y
Central Hudson |  | Solar Generation | CH-08126 | Kingston | Lk Hill | Ulster | 12448 | G | 3012 | Woodstock | N |  | 18 | [13 empty] | NM | N | 3 SMA SB 6000 TL | 2015-10-15 | 2015-10-21 | 4 | 2015-10-21 | [14 empty] | 2016-07-26 | 2016-07-26 |  | Y
Central Hudson |  | Solar Generation | CH-08231 | Kingston | Mt Tremper | Ulster | 12457 | G | 3012 | Woodstock | N |  | 10 | [13 empty] | NM | N | SOLAREDGE 10,000 A | 2015-10-15 | 2015-10-22 | 5 | 2015-10-22 | [14 empty] | 2016-06-09 | 2016-06-15 |  | Y
Central Hudson |  | Solar Generation | CH-08300 | Kingston | Woodstock | Ulster | 12498 | G | 3012 | Woodstock | N |  | 5 | [13 empty] | NM | N | SMA SB 5000 TL | 2015-10-15 | 2015-10-22 | 5 | 2015-10-22 | [14 empty] | 2016-06-21 | 2016-06-24 |  | Y
Central Hudson |  | NRG Home Solar | CH-04310 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6043 | Spackenkill | N |  | 12 | [13 empty] | NM | N | (48) ENPHASE M-250-60-2LL-S22 | 2015-10-16 | 2015-10-29 | 9 | 2015-10-29 | [8 empty] | 350 | 350 |  | 2015-11-02 | 2015-11-02 | 2015-11-16 | 2015-12-14 | 2015-12-17 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | NRG Home Solar | CH-04489 | Newburgh | Wallkill | Ulster | 12589 | G | 5043 | East Walden | N |  | 3 | [13 empty] | NM | N | SOLAR EDGE SE3000 | 2015-10-16 | 2015-10-22 | 4 | 2015-10-22 | [14 empty] | 2015-12-22 | 2015-12-31 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00964 | Newburgh | Milton | Ulster | 12547 | G | 5083 | Highland | N |  | 6.02 | [13 empty] | NM | N | ENPHASE M215 60-2LL-S22 (28) | 2015-10-16 | 2015-10-23 | 5 | 2015-10-23 | [14 empty] | 2015-12-04 | 2015-12-04 |  | Y
Central Hudson |  | SolarCity | CH-05124 | Kingston | Kingston | Ulster | 12401 | G | 2094 | Hurley Ave | N |  | 11 | [13 empty] | NM | N | ABB PVI-5000-OUTD-US-Z-A ABB PVI-6000-OUTD-US-Z-A | 2015-10-16 | 2015-10-22 | 4 | 2015-10-22 | [14 empty] | 2015-12-15 | 2015-12-22 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07234 | Kingston | Saugerties | Ulster | 12477 | G | 3001 | Saugerties | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000-OUTD-US-Z-A | 2015-11-17 | 2015-11-24 | 5 | 2015-11-24 | [14 empty] | 2015-12-15 | 2015-12-22 |  | Y
Central Hudson |  | Sungevity Inc | CH-09195 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7052 | Rhinebeck | N |  | 6.8 | [13 empty] | NM | N | (1) ABB PVI-3.8-OUTD-S-US-A (1) ABB PVI-3.0-OUTD-S-US-A | 2015-10-16 | 2015-10-23 | 5 | 2015-10-23 | [14 empty] | 2015-12-29 | 2016-01-06 |  | Y
Central Hudson |  | Sungevity Inc | CH-09287 | Kingston | Kingston | Ulster | 12401 | G | 1024 | East Kingston | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000-OUTD-US-A | 2015-10-16 | 2015-10-22 | 4 | 2015-10-22 | [14 empty] | 2016-01-19 | 2016-01-26 |  | Y
Central Hudson |  | Sungevity Inc | CH-09459 | Fishkill | Stormvl | Dutchess | 12582 | G | 8071 | Shenandoah | N |  | 5 | [13 empty] | NM | N | ABB PVI-5000-OUTD-US-A | 2015-10-16 | 2015-10-22 | 4 | 2015-10-22 | [14 empty] | 2016-01-28 | 2016-01-29 |  | Y
Central Hudson |  | Apex Solar Power | CH-03097 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6046 | Spackenkill | N |  | 6 | [13 empty] | NM | N | SolarEdge SE6000A-US | 2015-11-23 | 2015-12-02 | 5 | 2015-12-02 | [14 empty] | 2015-12-03 | 2015-12-08 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | High Peaks Solar, LLC | CH-03369 | Catskill | Coeymans Hollow | Albany | 12046 | G | 1081 | New Baltimore | N |  | 4 | [13 empty] | NM | N | SMA SB4000 TL-US-22 | 2015-10-19 | 2015-10-27 | 6 | 2015-10-27 | [14 empty] | 2016-02-25 | 2016-03-09 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00955 | Fishkill | Beacon |  | 12508 | G | 8015 | Forgebrook | TBD |  | 1.72 | [13 empty] | NM | N | ENPHASE M215 60-2LL-S22 (8) | 2015-10-19 | 2015-10-27 | 6 | 2015-10-27 | [17 empty] | W
Central Hudson |  | Geo of Camden, LLC dba Solar Universe Camden | CH-01132 | Poughkeepsie | Poughkeepsie |  | 12603 | G | 6092 | Manchester | TBD |  | 11.61 | [13 empty] | NM | N | (54) Enphase M215 | 2015-10-27 | 2015-11-02 | 4 | 2015-11-02 | [17 empty] | W
Central Hudson |  | SolarCity | CH-05723 | Kingston | Saugerties |  | 12477 | G | 3002 | Saugerties | TBD |  | 3 | [13 empty] | NM | N | ABB PVI-3.0-OUTD-S-US-Z | 2015-10-19 | 2015-10-27 | 6 | 2015-10-27 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | SolarCity | CH-05995 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8091 | Fishkill Plains | N |  | 12 | [13 empty] | NM | N | ABB PVI-6000-OUTD-US-Z-A (2) | 2015-10-19 | 2015-10-26 | 5 | 2015-10-26 | [14 empty] | 2015-12-08 | 2015-12-08 |  | Y
Central Hudson |  | SolarCity | CH-06772 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7054 | Rhinebeck | N |  | 5 | [13 empty] | NM | N | ABB PVI-5000-OUTD-US-Z-A | 2015-10-27 | 2015-11-02 | 4 | 2015-11-02 | [14 empty] | 2015-12-31 | 2016-01-08 |  | W
Central Hudson |  | SolarCity | CH-07361 | Fishkill | Wappingers Falls | Dutchess | 12590 | G | 8092 | Fishkill Plains | N |  | 3.6 | [13 empty] | NM | N | ABB PVI-3.6-OUTD-S-US-Z- | 2015-11-03 | 2015-11-05 | 2 | 2015-11-05 | [14 empty] | 2015-12-18 | 2015-12-21 |  | Y
Central Hudson |  | SolarCity | CH-07446 | Newburgh | New Windsor | Orange | 12553 | G | 4046 | Union Ave | N |  | 3 | [13 empty] | NM | N | ABB PVI-3.0-OUTD-S-US-Z- | 2015-10-19 | 2015-10-26 | 5 | 2015-10-26 | [14 empty] | 2015-12-15 | 2015-12-15 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07569 | Fishkill | Wappingers Falls | Dutchess | 12590 | G | 8094 | Fishkill Plains | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2015-10-19 | 2015-10-26 | 5 | 2015-10-26 | [14 empty] | 2016-01-04 | 2016-01-11 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00876 | Kingston | Cragsmoore |  | 12420 | G | 3078 | Greenfield Rd | TBD |  | 6.67 | [13 empty] | NM | N | 31 ENPHASE M215 60-2LL-S22 | 2015-10-20 | 2015-10-27 | 5 | 2015-10-27 | [17 empty] | W
Central Hudson |  | Hudson Solar | CH-01559 | Newburgh | Montgomery | Orange | 12549 | G | 5054 | Maybrook | N |  | 10 | [13 empty] | NM | N | SOLAREDGE SE-10000 A-US-U | 2015-10-20 | 2015-10-26 | 4 | 2015-10-26 | [14 empty] | 2015-12-31 | 2016-01-07 |  | Y
Central Hudson |  | Hudson Solar | CH-01723 | Kingston | Kingston | Ulster | 12401 | G | 2016 | Lincoln Park | N |  | 10 | [13 empty] | NM | N | SOLAREDGE SE-10000 A-US-U | 2015-10-20 | 2015-10-27 | 5 | 2015-10-27 | [14 empty] | 2015-12-03 | 2015-12-10 |  | Y
Central Hudson |  | PosiGen Solar | CH-02869 | Catskill | Purling | Greene | 12470 | G | 2042 | South Cairo | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A-US | 2015-10-20 | 2015-10-27 | 5 | 2015-10-27 | [14 empty] | 2015-11-24 | 2015-12-02 |  | Y
Central Hudson |  | PosiGen Solar | CH-02874 | Catskill | Westerlo | Albany | 12193 | G | 1091 | Westerlo | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE7600A-US | 2015-10-20 | 2015-10-27 | 5 | 2015-10-27 | [14 empty] | 2016-01-14 | 2016-01-21 |  | Y
Central Hudson |  | SolarCity | CH-05084 | Newburgh | Wallkill | Ulster | 12589 | G | 5042 | East Walden | N |  | 7.8 | [13 empty] | NM | N | ABB PVI-4.2-OUTD-S-US-Z- ABB PVI-3.6-OUTD-S-US-Z- | 2015-10-20 | 2015-10-26 | 4 | 2015-10-26 | [14 empty] | 2015-12-08 | 2015-12-08 |  | Y
Central Hudson |  | SolarCity | CH-06974 | Newburgh | Newburgh | Orange | 12550 | G | 4014 | West Balmville | N | CH-06974 | 3.6 | [13 empty] | NM | N | ABB PVI-3.6-OUTD-S-US-Z- | 2015-10-20 | 2015-10-26 | 4 | 2015-10-26 | [14 empty] | 2015-11-19 | 2015-11-19 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07006 | Newburgh | Newburgh | Orange | 12550 | G | 4014 | West Balmville | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2015-10-20 | 2015-10-26 | 4 | 2015-10-26 | [14 empty] | 2016-04-12 | 2016-04-12 |  | Y
Central Hudson |  | SolarCity | CH-07126 | Newburgh | New Windsor | Orange | 12553 | G | 4095 | Bethlehem Rd | N |  | 9 | [13 empty] | NM | N | ABB PVI-6000-OUTD-US ABB PVI-3.0-OUTD-S-US | 2015-10-20 | 2015-10-26 | 4 | 2015-10-26 | [14 empty] | 2015-11-02 | 2015-11-03 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07573 | Fishkill | Fishkill | Dutchess | 12524 | G | 8094 | Fishkill Plains | N |  | 11 | [13 empty] | NM | N | SOLAREDGE SE6000A-US SOLAREDGE SE5000A-US | 2015-10-27 | 2015-10-30 | 3 | 2015-10-30 | [14 empty] | 2015-11-05 | 2015-11-20 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Solar Generation | CH-08309 | Newburgh | Wallkill | Ulster | 12589 | G | 5033 | Galeville | N | CH-08281 | 10 | [13 empty] | NM | N | SOLAREDGE 10,000A US | 2016-01-04 | 2016-01-18 | 10 | 2016-01-18 | [8 empty] | 350 | 350 |  | 2016-02-04 | 2016-02-04 | 2016-02-11 | 2016-02-11 | 2016-02-11 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Sol Providers | CH-08972 | Poughkeepsie | Poughkeepsie |  | 12601 | G | 6011 | Sand Dock | TBD |  | 7.6 | [13 empty] | NM | N | (2) SMA SB3800TL | 2015-10-28 | 2015-11-06 | 7 | 2015-11-06 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | Sungevity Inc | CH-09373 | Newburgh | Newburgh |  | 12550 | G | 5041 | East Walden | TBD |  | 7.6 | [13 empty] | NM | N | ABB PVI-3.8-OUTD-S-US-A | 2015-10-20 | 2015-10-26 | 4 | 2015-10-26 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | Infinity Solar Systems | CH-03377 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8071 | Shenandoah | N |  | 10 | [13 empty] | NM | N | SMA AMERICA SB5000TL-US-22(2) | 2015-10-21 | 2015-10-27 | 4 | 2015-10-27 | [14 empty] | 2016-01-15 | 2016-01-15 |  | Y
Central Hudson |  | NRG Home Solar | CH-04289 | Kingston | Saugerties | Ulster | 12477 | G | 3004 | Saugerties | N |  | 4.73 | [13 empty] | NM | N | 22 ENPHASE M-215-60-2LL-S22-IG | 2015-10-21 | 2015-10-28 | 5 | 2015-10-28 | [14 empty] | 2015-12-03 | 2015-12-10 |  | Y
Central Hudson |  | NRG Home Solar | CH-04369 | Newburgh | Highland | Ulster | 12528 | G | 5081 | Highland | N |  | 4.3 | [13 empty] | NM | N | (20) ENPHASE M-215-60-2LL-S22-IG | 2015-10-21 | 2015-10-28 | 5 | 2015-10-28 | [14 empty] | 2016-02-23 | 2016-03-01 |  | Y
Central Hudson |  | NRG Home Solar | CH-00524 | Catskill | Athens | Greene | 12015 | G | 2002 | North Catskill | N |  | 5.59 | [13 empty] | NM | N | 26 ENPHASE M-215-60-2LL-S22-IG | 2015-10-21 | 2015-10-28 | 5 | 2015-10-28 | [14 empty] | 2016-05-10 | 2016-05-12 |  | Y
Central Hudson |  | NRG Home Solar | CH-04803 | Poughkeepsie | Poughkeepsie |  | 12601 | G | 6002 | Reynolds Hill | TBD |  | 3.225 | [13 empty] | NM | N | (15) ENPHASE M-215-60-2LL-S22-IG | 2015-10-28 | 2015-10-28 | 0 | 2015-10-28 | [17 empty] | W
Central Hudson |  | Apex Solar Power | CH-00669 | Newburgh | Newburgh | Orange | 12550 | G | 4014 | West Balmville | N |  | 7.6 | [13 empty] | NM | N | SOLAR EDGE SE7600A-US | 2015-11-23 | 2015-11-23 | 0 | 2015-11-23 | [14 empty] | 2015-12-30 | 2016-01-07 |  | Y
Central Hudson |  | SolarCity | CH-07082 | Newburgh | Wallkill | Ulster | 12589 | G | 5043 | East Walden | N |  | 10.2 | [13 empty] | NM | N | ABB PVI-6000-OUTD ABB PVI-4.2-OUTD-S | 2015-10-21 | 2015-10-27 | 4 | 2015-10-27 | [14 empty] | 2015-12-15 | 2015-12-15 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Infinity Solar Systems | CH-03374 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 6057 | Todd Hill | N | CH-03374 | 11 | [13 empty] | NM | N | (1) SMA America SB6000TL-22 (1) SMA America SB5000TL-22 | 2015-10-22 | 2015-11-05 | 10 | 2015-11-05 | [14 empty] | 2016-01-28 | 2016-02-04 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-03402 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 7011 | Hibernia | N |  | 7.7 | [13 empty] | NM | N | SMA America SB7700TL-US-22 | 2015-10-22 | 2015-11-05 | 10 | 2015-11-05 | [14 empty] | 2016-06-14 | 2016-06-21 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03714 | Newburgh | Marlboro | Ulster | 12542 | G | 5003 | Marlboro | N |  | 6 | [13 empty] | NM | N | SOLAREDGE 6000 A-US | 2015-10-22 | 2015-10-28 | 4 | 2015-10-28 | [14 empty] | 2015-12-11 | 2015-12-14 |  | Y
Central Hudson |  | NRG Home Solar | CH-04190 | Fishkill | Wappingers Falls | Dutchess | 12590 | G | 8043 | Myers Corners | N |  | 7.25 | [13 empty] | NM | N | ENPHASE M-250-60-2LL-S22 (29) | 2015-10-22 | 2015-11-04 | 9 | 2015-11-04 | [8 empty] | 350 | 350 |  | 2015-11-19 | 2015-11-19 | 2015-12-04 | 2016-01-04 | 2016-01-11 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | NRG Home Solar | CH-04274 | Kingston | Ellenvl | Ulster | 12428 | G | 3095 | Grimley Rd | N |  | 4 | [13 empty] | NM | N | 16 ENPHASE M-250-60-2LL-S22 | 2015-10-22 | 2015-10-28 | 4 | 2015-10-28 | [14 empty] | 2015-12-22 | 2015-12-31 |  | Y
Central Hudson |  | NRG Home Solar | CH-04347 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 7024 | Tinkertown | N |  | 5.5 | [13 empty] | NM | N | (22) ENPHASE M-250-60-2LL-S22 | 2015-10-22 | 2015-10-29 | 5 | 2015-10-29 | [14 empty] | 2015-12-22 | 2015-12-29 |  | Y
Central Hudson |  | NRG Home Solar | CH-04365 | Poughkeepsie | Pine Plns | Dutchess | 12567 | G | 7091 | Pulvers Corners | N |  | 6.5 | [13 empty] | NM | N | (26) ENPHASE M-250-60-2LL-S22 | 2015-10-22 | 2015-10-29 | 5 | 2015-10-29 | [14 empty] | 2015-12-28 | 2016-01-05 |  | Y
Central Hudson |  | NRG Home Solar | CH-04687 | Kingston | Kerhonkson | Ulster | 12446 | G | 3081 | Kerhonkson | N |  | 4.5 | [13 empty] | NM | N | 18 ENPHASE M-250-60-2LL-S22 | 2015-10-22 | 2015-10-28 | 4 | 2015-10-28 | [14 empty] | 2015-12-22 | 2015-12-31 |  | Y
Central Hudson |  | Direct Energy Solar | CH-01035 | Kingston | Saugerties | Ulster | 12477 | G | 3003 | Saugerties | N |  | 8.17 | [13 empty] | NM | N | 38 ENPHASE M215 60-2LL-S22 | 2015-10-22 | 2015-10-28 | 4 | 2015-10-28 | [14 empty] | 2016-01-15 | 2016-01-21 |  | Y
Central Hudson |  | Hudson Solar | CH-02275 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7052 | Rhinebeck | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE-7600A-US-U | 2015-10-29 | 2015-11-05 | 5 | 2015-11-05 | [14 empty] | 2015-12-09 | 2015-12-15 |  | Y
Central Hudson |  | SolarCity | CH-05239 | Catskill | Hannacroix | Greene | 12087 | G | 1083 | New Baltimore | N |  | 6.6 | [13 empty] | NM | N | ABB PVI-3.0-OUTD_S-US-Z ABB PVI-3.6-OUTD_S-US-Z | 2015-10-22 | 2015-10-30 | 6 | 2015-10-30 | [14 empty] | 2016-06-07 | 2016-06-08 |  | Y
Central Hudson |  | SolarCity | CH-05687 | Kingston | Hurley | Ulster | 12443 | G | 2094 | Hurley Ave | N |  | 15.8 | [13 empty] | NM | N | FRONIUS PRIMO 8.2 FRONIUS PRIMO 7.6 | 2015-10-22 | 2015-10-28 | 4 | 2015-10-28 | [14 empty] | 2016-01-14 | 2016-01-21 |  | Y
Central Hudson |  | SolarCity | CH-05991 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8091 | Fishkill Plains | N |  | 3.6 | [13 empty] | NM | N | ABB PVI-3.6-OUTD-S-US-Z- | 2015-10-22 | 2015-10-28 | 4 | 2015-10-28 | [14 empty] | 2015-11-23 | 2015-12-02 |  | Y
Central Hudson |  | SolarCity | CH-06256 | Newburgh | New Windsor | Orange | 12553 | G | 4045 | Union Ave | N |  | 4.2 | [13 empty] | NM | N | ABB PVI-4.2-OUTD-S-US-Z- | 2015-10-22 | 2015-10-28 | 4 | 2015-10-28 | [14 empty] | 2015-12-14 | 2015-12-14 |  | Y
Central Hudson |  | SolarCity | CH-06500 | Kingston | Kingston | Ulster | 12401 | G | 2013 | Lincoln Park | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2015-10-22 | 2015-10-28 | 4 | 2015-10-28 | [14 empty] | 2015-12-14 | 2015-12-21 |  | Y
Central Hudson |  | SolarCity | CH-06825 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8024 | Knapps Corners | N |  | 3 | [13 empty] | NM | N | ABB PVI-3.0-OUTD-S-US-Z- | 2015-10-22 | 2015-10-29 | 5 | 2015-10-29 | [14 empty] | 2015-11-10 | 2015-11-10 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07014 | Newburgh | Newburgh | Orange | 12550 | G | 4053 | Union Ave | N |  | 3 | [13 empty] | NM | N | SOLAREDGE SE3000A-US | 2015-10-22 | 2015-10-27 | 3 | 2015-10-27 | [14 empty] | 2015-12-15 | 2015-12-15 |  | Y
Central Hudson |  | SolarCity | CH-07019 | Newburgh | New Windsor | Orange | 12553 | G | 4043 | Union Ave | N |  | 4.2 | [13 empty] | NM | N | ABB PVI-4.2-OUTD-S-US-Z- | 2015-10-22 | 2015-10-27 | 3 | 2015-10-27 | [14 empty] | 2015-11-23 | 2015-11-23 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07148 | Newburgh | Montgomery | Orange | 12549 | G | 5073 | Montgomery | N |  | 3.6 | [13 empty] | NM | N | ABB PVI-3.6-OUTD-S-US-Z- | 2015-10-22 | 2015-10-28 | 4 | 2015-10-28 | [14 empty] | 2015-12-08 | 2015-12-08 |  | Y
Central Hudson |  | SolarCity | CH-07607 | Newburgh | Marlboro | Ulster | 12542 | G | 5002 | Marlboro | N |  | 3 | [13 empty] | NM | N | ABB PVI-3.0-OUTD-S-US-Z- | 2015-10-22 | 2015-10-28 | 4 | 2015-10-28 | [14 empty] | 2016-01-04 | 2016-01-11 |  | Y
Central Hudson |  | Solar Generation | CH-08152 | Kingston | Ulster Pk | Ulster | 12487 | G | 3041 | Sturgeon Pool | N |  | 18 | [13 empty] | NM | N | 3 SMA SB 6000 TL | 2015-10-22 | 2015-10-28 | 4 | 2015-10-28 | [8 empty] | 350 | 350 |  | 2015-12-11 | 2015-12-11 | 2016-01-07 | 2016-01-29 | 2016-02-05 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08733 | Catskill | Westerlo | Albany | 12193 | G | 1091 | Westerlo | N |  | 6.235 | [13 empty] | NM | N | 29 ENPHASE M215 602LLS2XZC | 2015-10-22 | 2015-10-28 | 4 | 2015-10-28 | [14 empty] | 2015-11-02 | 2015-11-09 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Sungevity Inc | CH-09257 | Catskill | Prattsville |  | 12468 | E | 2389 | Vinegar Hill | TBD |  | 3 | [13 empty] | NM | N | 2 ABB PVI-3.8-OUTD-S-US-A | 2015-10-22 | 2015-10-28 | 4 | 2015-10-28 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | US Energy Concierge, Inc. | CH-09735 | Poughkeepsie | Millbrook | Dutchess | 12545 | G | 7012 | Hibernia | N |  | 13.6 | [13 empty] | NM | N | (1) SOLAREDGE SE7600 (1) SOLAREDGE SE6000 | 2015-11-02 | 2015-11-09 | 5 | 2015-11-09 | [14 empty] | 2015-12-18 | 2015-12-23 |  | Y
Central Hudson |  | US Energy Concierge, Inc. | CH-09741 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6068 | Inwood Ave | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE7600 | 2015-10-30 | 2015-11-06 | 5 | 2015-11-06 | [14 empty] | 2015-12-22 | 2015-12-23 |  | Y
Central Hudson |  | US Energy Concierge, Inc. | CH-09747 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8091 | Fishkill Plains | N |  | 15.2 | [13 empty] | NM | N | SOLAREDGE SE7600 (2) | 2015-10-28 | 2015-11-02 | 3 | 2015-11-02 | [14 empty] | 2016-06-27 | 2016-07-21 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-03499 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6003 | Reynolds Hill | N |  | 6 | [13 empty] | NM | N | SMA America SB6000TL-US-22 | 2015-10-23 | 2015-11-06 | 10 | 2015-11-06 | [14 empty] | 2016-02-22 | 2016-02-26 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03819 | Newburgh | New Paltz | Ulster | 12561 | G | 5031 | Galeville | N | CH-03819 | 10 | [13 empty] | NM | N | SOLAREDGE 10000 A-US | 2015-10-23 | 2015-10-29 | 4 | 2015-10-29 | [14 empty] | 2015-11-25 | 2015-11-25 |  | Y
Central Hudson |  | NRG Home Solar | CH-04150 | Poughkeepsie | Tivoli | Dutchess | 12583 | G | 7062 | Milan | N |  | 7.25 | [13 empty] | NM | N | (29) ENPHASE M-250-60-2LL-S22 | 2015-10-23 | 2015-11-06 | 10 | 2015-11-06 | [14 empty] | 2015-12-30 | 2016-01-07 |  | Y
Central Hudson |  | NRG Home Solar | CH-04155 | Fishkill | Hopewell Junction | Dutchess | 12533 | G | 8093 | Fishkill Plains | N |  | 7.6 | [13 empty] | NM | N | SOLAR EDGE SE7600A-US | 2015-10-28 | 2015-11-02 | 3 | 2015-11-02 | [14 empty] | 2015-12-15 | 2015-12-16 |  | Y
Central Hudson |  | NRG Home Solar | CH-04195 | Newburgh | New Paltz | Ulster | 12561 | G | 5011 | Modena | N |  | 8.5 | [13 empty] | NM | N | ENPHASE M-250-60-2LL-S22 (34) | 2015-10-23 | 2015-10-29 | 4 | 2015-10-29 | [14 empty] | 2015-12-16 | 2015-12-17 |  | Y
Central Hudson |  | NRG Home Solar | CH-04207 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8072 | Shenandoah | N |  | 10 | [13 empty] | NM | N | SOLAR EDGE SE10000A-US | 2015-10-23 | 2015-10-29 | 4 | 2015-10-29 | [14 empty] | 2015-12-22 | 2015-12-31 |  | Y
Central Hudson |  | NRG Home Solar | CH-04219 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8095 | Fishkill Plains | N |  | 4.25 | [13 empty] | NM | N | ENPHASE M-250-60-2LL-S22 (17) | 2015-10-29 | 2015-11-02 | 2 | 2015-11-02 | [14 empty] | 2015-12-15 | 2015-12-16 |  | Y
Central Hudson |  | NRG Home Solar | CH-04316 | Poughkeepsie | Poughkeepsie |  | 12601 | G | 6068 | Inwood Ave | TBD |  | 3.75 | [13 empty] | NM | N | (15) ENPHASE M-250-60-2LL-S22 | 2015-10-23 | 2015-10-30 | 5 | 2015-10-30 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | NRG Home Solar | CH-04370 | Newburgh | Highland | Ulster | 12528 | G | 5083 | Highland | N |  | 5.75 | [13 empty] | NM | N | (23) ENPHASE M-250-60-2LL-S22 | 2015-10-23 | 2015-11-06 | 10 | 2015-11-06 | [14 empty] | 2016-01-11 | 2016-01-15 |  | Y
Central Hudson |  | NRG Home Solar | CH-04436 | Fishkill | Beacon | Dutchess | 12508 | G | 8015 | Forgebrook | N |  | 4.75 | [13 empty] | NM | N | ENPHASE M-250-60-2LL-S22 (19) | 2015-10-23 | 2015-10-29 | 4 | 2015-10-29 | [14 empty] | 2016-01-13 | 2016-01-15 |  | Y
Central Hudson |  | NRG Home Solar | CH-04739 | Newburgh | Newburgh | Orange | 12550 | G | 4013 | West Balmville | N |  | 3.44 | [13 empty] | NM | N | ENPHASE M-215-60-2LL-S22-IG (16) | 2015-11-17 | 2015-11-17 | 0 | 2015-11-17 | [14 empty] | 2016-02-11 | 2016-02-19 |  | Y
Central Hudson |  | NRG Home Solar | CH-04784 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8045 | Myers Corners | N |  | 6.5 | [13 empty] | NM | N | ENPHASE M-250-60-2LL-S22 (26) | 2015-10-23 | 2015-10-28 | 3 | 2015-10-28 | [14 empty] | 2016-01-06 | 2016-01-13 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07592 | Newburgh | Newburgh | Orange | 12550 | G | 4013 | West Balmville | N |  | 3.6 | [13 empty] | NM | N | ABB PVI-3.6-OUTD-S-US | 2015-10-23 | 2015-10-29 | 4 | 2015-10-29 | [14 empty] | 2016-02-26 | 2016-03-04 |  | Y
Central Hudson |  | Solar Generation | CH-08144 | Kingston | Kerhonkson | Ulster | 12446 | G | 3082 | Kerhonkson | N |  | 10.8 | [13 empty] | NM | N | SMA SB 7000 TL SMA SB 3800 TL | 2015-10-23 | 2015-10-30 | 5 | 2015-10-30 | [8 empty] | 350 | 350 |  | 2015-12-14 | 2015-12-14 | 2015-12-23 | 2015-12-21 | 2015-12-30 |  | Y
Central Hudson |  | Trinity Solar | CH-08585 | Kingston | Kingston | Ulster | 12401 | G | 1021 | East Kingston | N |  | 3.8 | [13 empty] | NM | N | SOLAR EDGE SE 3800A-US | 2015-10-23 | 2015-10-30 | 5 | 2015-10-30 | [14 empty] | 2015-11-10 | 2015-11-17 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Sungevity Inc | CH-09177 | Kingston | High Falls |  | 12440 | G | 3024 | High Falls | TBD |  | 6 | [13 empty] | NM | N | ABB PVI-6000-OUTD-US-A | 2015-10-23 | 2015-10-30 | 5 | 2015-10-30 | [17 empty] | W
Central Hudson |  | Sungevity Inc | CH-09557 | Newburgh | Cornwall | Orange | 12518 | G | 4041 | Union Ave | N |  | 6 | [13 empty] | NM | N | ABB PVI-3.0-OUTD-S-US-A (2) | 2015-10-23 | 2015-10-29 | 4 | 2015-10-29 | [14 empty] | 2015-12-01 | 2015-12-01 |  | Y
Central Hudson |  | Sungevity Inc | CH-09603 | Fishkill | Beacon |  | 12508 | G | 8085 | Tioronda | TBD |  | 4.2 | [13 empty] | NM | N | ABB PVI-4.2-OUTD-S-US-A | 2015-10-23 | 2015-10-28 | 3 | 2015-10-28 | [17 empty] | W
Central Hudson |  | Apex Solar Power | CH-00664 | Newburgh | Newburgh | Orange | 12550 | G | 4023 | Coldenham | N |  | 11.4 | [13 empty] | NM | N | SOLAR EDGE SE7600A-US SOLAR EDGE SE3800A-US | 2015-12-02 | 2015-12-02 | 0 | 2015-12-02 | [14 empty] | 2016-02-03 | 2016-02-03 |  | Y
Central Hudson |  | PosiGen Solar | CH-02890 | Catskill | Ravena | Albany | 12143 | G | 1082 | New Baltimore | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE7600A-US | 2015-10-26 | 2015-11-02 | 5 | 2015-11-02 | [14 empty] | 2016-03-07 | 2016-03-14 |  | Y
Central Hudson |  | PosiGen Solar | CH-02919 | Catskill | Cairo | Greene | 12413 | G | 2041 | South Cairo | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE7600A-US | 2015-10-26 | 2015-11-02 | 5 | 2015-11-02 | [14 empty] | 2015-12-01 | 2015-12-08 |  | Y
Central Hudson |  | SolarCity | CH-05725 | Kingston | West Camp | Ulster | 12490 | G | 3004 | Saugerties | N |  | 4.2 | [13 empty] | NM | N | ABB PVI-4.2-OUTD-S-US | 2015-10-26 | 2015-10-30 | 4 | 2015-10-30 | [14 empty] | 2015-12-04 | 2015-12-11 |  | Y
Central Hudson |  | SolarCity | CH-06252 | Newburgh | New Windsor | Orange | 12553 | G | 4043 | Union Ave | N |  | 8.2 | [13 empty] | NM | N | FRONIUS PRIMO 8.2 | 2015-11-13 | 2015-11-13 | 0 | 2015-11-13 | [14 empty] | 2015-12-15 | 2015-12-15 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06372 | Newburgh | Wallkill | Ulster | 12589 | G | 5011 | Modena | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2015-10-26 | 2015-10-29 | 3 | 2015-10-29 | [14 empty] | 2016-01-25 | 2016-01-26 |  | Y
Central Hudson |  | SolarCity | CH-06609 | Kingston | Kingston | Ulster | 12401 | G | 2013 | Lincoln Park | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A US | 2015-10-26 | 2015-11-02 | 5 | 2015-11-02 | [14 empty] | 2015-12-30 | 2016-01-08 |  | Y
Central Hudson |  | SolarCity | CH-07362 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8092 | Fishkill Plains | N |  | 10 | [13 empty] | NM | N | SOLAREDGE SE10000A US | 2015-10-26 | 2015-10-29 | 3 | 2015-10-29 | [14 empty] | 2016-01-27 | 2016-01-28 |  | Y
Central Hudson |  | Sol Providers | CH-08933 | Newburgh | New Windsor |  | 12553 | G | 4054 | Union Ave | TBD |  | 6 | [13 empty] | NM | N | SMA AMERICA SB6000TL-US-22 | 2015-11-12 | 2015-11-13 | 1 | 2015-11-13 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | The Conti Group | CH-09709 | Kingston | Saugerties |  | 12477 | G | 3002 | Saugerties | TBD |  | 1980 | [13 empty] | CDG | N | (55) Solectria PVI-36TL-480 | 2016-01-27 | 2016-02-18 | 15 | 2016-02-18 | 2016-01-27 | 2016-02-18 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Infinity Solar Systems | CH-03481 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8052 | North Chelsea | N |  | 8.8 | [13 empty] | NM | N | SMA AMERICA SB3800TL-US-22 SMA AMERICA SB5000TL-US-22 | 2015-11-03 | 2015-11-09 | 4 | 2015-11-09 | [14 empty] | 2015-12-23 | 2016-01-04 |  | Y
Central Hudson |  | NRG Home Solar | CH-04276 | Kingston | Grahamsvl | Sullivan | 12740 | G | 3091 | Neversink | N |  | 4.25 | [13 empty] | NM | N | 17 ENPHASE M-250-60-2LL-S22 | 2015-10-27 | 2015-11-05 | 7 | 2015-11-05 | [14 empty] | 2015-12-14 | 2015-12-21 |  | Y
Central Hudson |  | NRG Home Solar | CH-04417 | Fishkill | Beacon | Dutchess | 12508 | G | 8015 | Forgebrook | N |  | 4.3 | [13 empty] | NM | N | ENPHASE M-215-60-2LL-S22 (20) | 2015-12-21 | 2016-01-06 | 9 | 2016-01-06 | [14 empty] | 2016-02-12 | 2016-02-19 |  | Y
Central Hudson |  | NRG Home Solar | CH-04744 | Newburgh | New Windsor | Orange | 12553 | G | 4045 | Union Ave | N |  | 7.6 | [13 empty] | NM | N | SOLAR EDGE SE7600A-US | 2015-11-02 | 2015-11-05 | 3 | 2015-11-05 | [14 empty] | 2015-12-30 | 2016-01-07 |  | Y
Central Hudson |  | Apex Solar Power | CH-00679 | Kingston | Woodstock | Ulster | 12498 | G | 3012 | Woodstock | N |  | 14.4 | [13 empty] | NM | N | SOLAREDGE SE11400A-US SOLAREDGE SE3000A-US | 2015-10-27 | 2015-11-03 | 5 | 2015-11-03 | [14 empty] | 2016-09-27 | 2016-09-28 |  | Y
Central Hudson |  | Apex Solar Power | CH-00718 | Newburgh | Newburgh |  | 12550 | G | 4024 | Coldenham | TBD |  | 7.6 | [13 empty] | NM | N | SOLAR EDGE SE7600A-US | 2015-11-11 | 2015-11-11 | 0 | 2015-11-11 | [17 empty] | W
Central Hudson |  | PosiGen Solar | CH-02872 | Catskill | Greenvl | Greene | 12083 | G | 1091 | Westerlo | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE7600A-US | 2015-10-27 | 2015-11-03 | 5 | 2015-11-03 | [14 empty] | 2015-11-24 | 2015-12-02 |  | Y
Central Hudson |  | SolarCity | CH-05864 | Poughkeepsie | Staatsburg | Dutchess | 12580 | G | 7041 | Staatsburg | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000-OUTD-US-Z-A | 2015-11-11 | 2015-11-18 | 5 | 2015-11-18 | [14 empty] | 2015-12-21 | 2015-12-21 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Solar Generation | CH-08089 | Kingston | Kingston |  | 12401 | G | 1012 | Boulevard | TBD |  | 4 | [13 empty] | NM | N | SOLAREDGE 4000A | 2015-10-27 | 2015-11-03 | 5 | 2015-11-03 | [17 empty] | W
Central Hudson |  | Solar Generation | CH-08158 | Kingston | Kingston | Ulster | 12401 | G | 1024 | East Kingston | N |  | 6 | [13 empty] | NM | N | SOLAREDGE 6000A | 2015-10-27 | 2015-11-03 | 5 | 2015-11-03 | [14 empty] | 2016-05-02 | 2016-05-02 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08653 | Catskill | Athens | Greene | 12015 | G | 2002 | North Catskill | N |  | 3.44 | [13 empty] | NM | N | 16 ENPHASE M215-602LLS2XZC | 2015-10-27 | 2015-11-03 | 5 | 2015-11-03 | [14 empty] | 2015-12-11 | 2015-12-18 |  | Y
Central Hudson |  | Solar Maximum LLC, dba RevoluSun | CH-09031 | Kingston | Saugerties | Ulster | 12477 | G | 3014 | Woodstock | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A-US-ZB-U | 2015-10-27 | 2015-11-03 | 5 | 2015-11-03 | [14 empty] | 2015-11-23 | 2015-12-01 |  | Y
Central Hudson |  | Apex Solar Power | CH-03088 | Catskill | Leeds | Greene | 12451 | G | 2005 | North Catskill | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000 A-US | 2015-10-28 | 2015-11-04 | 5 | 2015-11-04 | [14 empty] | 2015-12-07 | 2015-12-11 |  | Y
Central Hudson |  | Apex Solar Power | CH-03094 | Catskill | Greenvl | Greene | 12083 | G | 2061 | Freehold | N |  | 10 | [13 empty] | NM | N | SOLAREDGE SE10000A-US | 2015-10-28 | 2015-11-04 | 5 | 2015-11-04 | [14 empty] | 2015-11-24 | 2015-12-02 |  | Y
Central Hudson |  | New York State Solar Farm | CH-03938 | Newburgh | Wallkill | Ulster | 12589 | G | 5013 | Modena | N |  | 6 | [13 empty] | NM | N | SMA AMERICA SB6000 TL | 2015-11-16 | 2015-11-16 | 0 | 2015-11-16 | [14 empty] | 2015-12-02 | 2015-12-07 |  | Y
Central Hudson |  | New York State Solar Farm | CH-04038 | Newburgh | Newburgh | Orange | 12550 | G | 4024 | Coldenham | N |  | 6 | [13 empty] | NM | N | SMA AMERICA SB 6000TL | 2015-11-03 | 2015-11-06 | 3 | 2015-11-06 | [14 empty] | 2015-12-02 | 2015-12-02 |  | Y
Central Hudson |  | NRG Home Solar | CH-04279 | Kingston | Grahamsvl | Sullivan | 12740 | G | 3091 | Neversink | N |  | 2.75 | [13 empty] | NM | N | 11 ENPHASE M-250-60-2LL-S22 | 2015-10-28 | 2015-11-04 | 5 | 2015-11-04 | [14 empty] | 2015-12-11 | 2015-12-18 |  | Y
Central Hudson |  | NRG Home Solar | CH-04295 | Kingston | Lk Katrine |  | 12449 | G | 2011 | Lincoln Park | TBD |  | 6.25 | [13 empty] | NM | N | 25 ENPHASE M-250-60-2LL-S22 | 2015-10-28 | 2015-11-05 | 6 | 2015-11-05 | [17 empty] | W
Central Hudson |  | NRG Home Solar | CH-04334 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6051 | Todd Hill | N |  | 5.375 | [13 empty] | NM | N | (25) ENPHASE M-215-60-2LL-S22-IG | 2015-11-11 | 2015-11-11 | 0 | 2015-11-11 | [14 empty] | 2016-02-22 | 2016-02-29 |  | Y
Central Hudson |  | NRG Home Solar | CH-04504 | Newburgh | Rock Tvrn |  | 12575 | G | 4097 | Bethlehem Rd | TBD |  | 5.5 | [13 empty] | NM | N | ENPHASE M-250-60-2LL-S22 (22) | 2015-11-02 | 2015-11-05 | 3 | 2015-11-05 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | NRG Home Solar | CH-04568 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6065 | Inwood Ave | N |  | 3.5 | [13 empty] | NM | N | (14) ENPHASE M-250-60-2LL-S22 | 2015-11-04 | 2015-11-11 | 5 | 2015-11-11 | [14 empty] | 2015-12-22 | 2015-12-29 |  | Y
Central Hudson |  | NRG Home Solar | CH-04608 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8045 | Myers Corners | N |  | 4.5 | [13 empty] | NM | N | ENPHASE M-250-60-2LL-S22 (18) | 2015-11-02 | 2015-11-05 | 3 | 2015-11-05 | [14 empty] | 2016-01-27 | 2016-01-28 |  | Y
Central Hudson |  | NRG Home Solar | CH-04659 | Newburgh | Marlboro | Ulster | 12542 | G | 5003 | Marlboro | N |  | 6 | [13 empty] | NM | N | ENPHASE M-250-60-2LL-S22 (24) | 2015-11-02 | 2015-11-05 | 3 | 2015-11-05 | [14 empty] | 2015-12-15 | 2015-12-16 |  | Y
Central Hudson |  | Apex Solar Power | CH-00673 | Catskill | Leeds |  | 12451 | G | 2005 | North Catskill | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A-US | 2015-10-28 | 2015-11-04 | 5 | 2015-11-04 | [14 empty] | 2015-12-07 | 2015-12-11 |  | W
Central Hudson |  | Apex Solar Power | CH-00710 | Fishkill | Beacon | Dutchess | 12508 | G | 8087 | Tioronda | N |  | 3.8 | [13 empty] | NM | N | SOLAR EDGE SE3800A-US | 2015-11-10 | 2015-11-10 | 0 | 2015-11-10 | [14 empty] | 2015-12-17 | 2015-12-17 |  | Y
Central Hudson |  | SolarCity | CH-05432 | Newburgh | Montgomery | Orange | 12549 | G | 5054 | Maybrook | N |  | 12 | [13 empty] | NM | N | ABB PVI-6000-OUTD-US-Z-A (2) | 2015-11-03 | 2015-11-05 | 2 | 2015-11-05 | [14 empty] | 2015-12-14 | 2015-12-14 |  | Y
Central Hudson |  | SolarCity | CH-06339 | Newburgh | Gardiner | Ulster | 12525 | G | 5031 | Galeville | N |  | 9 | [13 empty] | NM | N | ABB PVI-3.0-OUTD-S-US-Z- ABB PVI-6000-OUTD-US-Z-A | 2015-11-03 | 2015-11-05 | 2 | 2015-11-05 | [14 empty] | 2015-12-14 | 2015-12-14 |  | Y
Central Hudson |  | SolarCity | CH-06851 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8095 | Fishkill Plains | N |  | 9.2 | [13 empty] | NM | N | ABB PVI-4.2-OUTD-S-US-Z- ABB PVI-5000-OUTD-US-Z-A | 2015-11-03 | 2015-11-05 | 2 | 2015-11-05 | [14 empty] | 2015-12-07 | 2015-12-07 |  | Y
Central Hudson |  | SolarCity | CH-06952 | Fishkill | Garrison | Putnam | 10524 | G | 8086 | Tioronda | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000-OUTD-US-Z-A | 2015-10-28 | 2015-11-02 | 3 | 2015-11-02 | [14 empty] | 2016-03-14 | 2016-03-21 |  | Y
Central Hudson |  | SolarCity | CH-06953 | Fishkill | Garrison | Putnam | 10524 | G | 8086 | Tioronda | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000-OUTD-US-Z-A | 2015-11-03 | 2015-11-05 | 2 | 2015-11-05 | [14 empty] | 2016-01-27 | 2016-01-28 |  | Y
Central Hudson |  | SolarCity | CH-07080 | Newburgh | Wallkill | Ulster | 12589 | G | 5043 | East Walden | N |  | 15.8 | [13 empty] | NM | N | FRONIUS PRIMO 8.2 FRONIUS PRIMO 7.6 | 2015-11-06 | 2015-11-17 | 7 | 2015-11-17 | [8 empty] | 350 | 350 |  |  |  |  | 2016-01-06 | 2016-01-13 |  | Y
Central Hudson |  | SolarCity | CH-07261 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6042 | Spackenkill | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000-OUT-US-Z-A | 2015-11-04 | 2015-11-11 | 5 | 2015-11-11 | [14 empty] | 2016-07-14 | 2016-07-14 |  | Y
Central Hudson |  | SolarCity | CH-07895 | Fishkill | Hopewell Jct |  | 12533 | G | 8094 | Fishkill Plains | TBD |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2015-11-06 | 2015-11-09 | 1 | 2015-11-09 | [17 empty] | W
Central Hudson |  | Sunrun Inc. | CH-08346 | Newburgh | New Windsor | Orange | 12553 | G | 4044 | Union Ave | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000 | 2015-11-10 | 2015-11-10 | 0 | 2015-11-10 | [14 empty] | 2015-12-03 | 2015-12-03 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08644 | Catskill | Earlton | Greene | 12058 | G | 1071 | Coxsackie | N |  | 8.17 | [13 empty] | NM | N | 38 ENPHASE M215 602LLS2XZC | 2015-10-28 | 2015-11-04 | 5 | 2015-11-04 | [14 empty] | 2016-07-20 | 2016-07-20 |  | Y
Central Hudson |  | You Save Green | CH-09959 | Newburgh | Rock Tvrn | Orange | 12575 | G | 4097 | Bethlehem Rd | N |  | 10 | [13 empty] | NM | N | SOLAR EDGE SE10000A-US | 2015-11-06 | 2015-11-17 | 7 | 2015-11-17 | [8 empty] | 350 | 350 |  | 2015-12-04 | 2015-12-04 | 2015-12-31 | 2015-12-28 | 2016-01-05 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-03480 | Poughkeepsie | Wingdale | Dutchess | 12594 | G | 6055 | Todd Hill | N |  | 10.8 | [13 empty] | NM | N | (1) SMA America SB3800TL-US-22 (1) SMA America SB7000TL-US-22 | 2015-10-29 | 2015-11-05 | 5 | 2015-11-05 | [14 empty] | 2015-12-23 | 2016-01-04 |  | Y
Central Hudson |  | Lotus Energy Inc. | CH-03846 | Kingston | Willow | Ulster | 12495 | G | 3012 | Woodstock | N |  | 5 | [13 empty] | NM | N | SMA 5000 TL-US-22 | 2015-10-29 | 2015-11-06 | 6 | 2015-11-06 | [14 empty] | 2015-11-20 | 2015-12-01 |  | Y
Central Hudson |  | Lotus Energy Inc. | CH-03878 | Kingston | Woodstock | Ulster | 12498 | G | 3014 | Woodstock | N |  | 5 | [13 empty] | NM | N | SMA 5000 TL-US-22 | 2015-10-29 | 2015-11-06 | 6 | 2015-11-06 | [14 empty] | 2015-12-09 | 2015-12-16 |  | Y
Central Hudson |  | NRG Home Solar | CH-04161 | Fishkill | Hopewell Jct |  | 12533 | G | 8095 | Fishkill Plains | TBD |  | 10 | [13 empty] | NM | N | SOLAR EDGE SE10000A-US | 2015-11-05 | 2015-11-06 | 1 | 2015-11-06 | [8 empty] | 350 | 350 | [7 empty] | W |  | Transformer upgrade required to accommodate PV installation. Utility System Upgrade Costs TBD. 11/20 - Customer called to abandon project.
Central Hudson |  | NRG Home Solar | CH-04170 | Poughkeepsie | Lagrangevl | Dutchess | 12540 | G | 6057 | Todd Hill | N |  | 10 | [13 empty] | NM | N | (2) SOLAR EDGE SE5000 | 2015-10-29 | 2015-11-05 | 5 | 2015-11-05 | [14 empty] | 2015-12-22 | 2015-12-29 |  | Y
Central Hudson |  | NRG Home Solar | CH-04182 | Newburgh | Cornwall | Orange | 12518 | G | 4041 | Union Ave | N |  | 5 | [13 empty] | NM | N | ENPHASE M-250-60-2LL-S22 (20) | 2015-10-29 | 2015-11-02 | 2 | 2015-11-02 | [14 empty] | 2016-01-19 | 2016-01-20 |  | Y
Central Hudson |  | NRG Home Solar | CH-04214 | Kingston | Kingston | Ulster | 12401 | G | 1011 | Boulevard | N | CH-04214 | 2.64 | [13 empty] | NM | N | 11ENPHASE M-250-60-2LL-S22 | 2015-10-29 | 2015-11-05 | 5 | 2015-11-05 | [14 empty] | 2016-02-01 | 2016-02-08 |  | Y
Central Hudson |  | NRG Home Solar | CH-04226 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8072 | Shenandoah | N |  | 10 | [13 empty] | NM | N | SOLAR EDGE SE10000A-US | 2015-10-29 | 2015-11-04 | 4 | 2015-11-04 | [14 empty] | 2016-01-11 | 2016-01-13 |  | Y
Central Hudson |  | NRG Home Solar | CH-04443 | Newburgh | Newburgh | Orange | 12550 | G | 4013 | West Balmville | N |  | 10 | [13 empty] | NM | N | SOLAR EDGE SE10000A-US | 2015-10-29 | 2015-11-02 | 2 | 2015-11-02 | [14 empty] | 2015-12-22 | 2015-12-31 |  | Y
Central Hudson |  | NRG Home Solar | CH-04473 | Newburgh | Newburgh | Orange | 12550 | G | 5004 | Marlboro | N |  | 3.25 | [13 empty] | NM | N | ENPHASE M-250-60-2LL-S22 (13) | 2015-11-03 | 2015-11-05 | 2 | 2015-11-05 | [14 empty] | 2015-12-14 | 2015-12-14 |  | Y
Central Hudson |  | NRG Home Solar | CH-04552 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6008 | Reynolds Hill | N |  | 6 | [13 empty] | NM | N | SOLAR EDGE SE6000A-US | 2015-10-29 | 2015-11-05 | 5 | 2015-11-05 | [14 empty] | 2015-12-22 | 2015-12-29 |  | Y
Central Hudson |  | NRG Home Solar | CH-04558 | Poughkeepsie | Verbank |  | 12585 | G | 6057 | Todd Hill | TBD |  | 10 | [13 empty] | NM | N | SOLAR EDGE SE10000A-US | 2015-10-29 | 2015-11-05 | 5 | 2015-11-05 | [17 empty] | W |  | Customer already had net meter prior to application. Customer is not doing solar.
Central Hudson |  | NRG Home Solar | CH-04691 | Kingston | Saugerties | Ulster | 12477 | G | 3004 | Saugerties | N |  | 8.5 | [13 empty] | NM | N | 34 ENPHASE M-250-60-2LL-S22 | 2015-10-29 | 2015-11-06 | 6 | 2015-11-06 | [14 empty] | 2016-01-11 | 2016-01-18 |  | Y
Central Hudson |  | SolarCity | CH-05098 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6092 | Manchester | N |  | 6 | [13 empty] | NM | N | ABB PVI-6.0-OUTD | 2015-10-29 | 2015-11-05 | 5 | 2015-11-05 | [14 empty] | 2016-01-04 | 2016-01-11 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06095 | Fishkill | Fishkill | Dutchess | 12524 | G | 8065 | Merritt Park | N |  | 4.2 | [13 empty] | NM | N | ABB PVI-4.2-OUTD-S US | 2015-10-29 | 2015-11-02 | 2 | 2015-11-02 | [14 empty] | 2015-12-15 | 2015-12-15 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07091 | Newburgh | Wallkill | Ulster | 12589 | G | 5013 | Modena | N |  | 3.6 | [13 empty] | NM | N | ABB PVI-3.6-OUTD-S-US | 2015-10-29 | 2015-11-04 | 4 | 2015-11-04 | [14 empty] | 2015-12-15 | 2015-12-15 |  | Y
Central Hudson |  | Sungevity Inc | CH-09628 | Fishkill | Hopewell Jct |  | 12533 | G | 8072 | Shenandoah | TBD |  | 3.8 | [13 empty] | NM | N | ABB PVI-3.8-OUTD-S-U | 2015-10-29 | 2015-11-02 | 2 | 2015-11-02 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | Infinity Solar Systems | CH-03449 | Poughkeepsie | Salt Pt | Dutchess | 12578 | G | 7012 | Hibernia | N |  | 10 | [13 empty] | NM | N | (2) SMA America SB5000TL-US-22 | 2015-11-19 | 2015-11-30 | 5 | 2015-11-30 | [14 empty] | 2015-12-23 | 2016-01-04 |  | Y
Central Hudson |  | Lotus Energy Inc. | CH-03873 | Kingston | Rosendale | Ulster | 12472 | G | 3022 | High Falls | N |  | 6 | [13 empty] | NM | N | SMA6000 TL-US-22 | 2015-10-30 | 2015-11-06 | 5 | 2015-11-06 | [14 empty] | 2015-12-14 | 2015-12-21 |  | Y
Central Hudson |  | SolarCity | CH-06023 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8044 | Myers Corners | N |  | 12 | [13 empty] | NM | N | ABB PVI-6000-OUTD-US-Z-A (2) | 2015-10-30 | 2015-11-04 | 3 | 2015-11-04 | [14 empty] | 2016-03-04 | 2016-03-11 |  | Y
Central Hudson |  | SolarCity | CH-06551 | Kingston | Kingston | Ulster | 12401 | G | 1022 | East Kingston | N |  | 3 | [13 empty] | NM | N | ABB PVI-3.0-OUTD-S-US | 2015-10-30 | 2015-11-06 | 5 | 2015-11-06 | [14 empty] | 2016-02-09 | 2016-02-16 |  | Y
Central Hudson |  | SolarCity | CH-06619 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6044 | Spackenkill | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2015-10-30 | 2015-11-06 | 5 | 2015-11-06 | [14 empty] | 2016-02-04 | 2016-02-10 |  | Y
Central Hudson |  | Sungevity Inc | CH-09540 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8092 | Fishkill Plains | N |  | 8 | [13 empty] | NM | N | ABB PVI-3.8-OUTD-S-US-A ABB PVI-4.2-OUTD-S-US-A | 2015-10-30 | 2015-11-04 | 3 | 2015-11-04 | [14 empty] | 2016-02-12 | 2016-02-22 |  | Y
Central Hudson |  | Lotus Energy Inc. | CH-03865 | Kingston | Woodstock | Ulster | 12498 | G | 3012 | Woodstock | N |  | 10 | [13 empty] | NM | N | 2 SMA 5000 TL-US-22 | 2015-11-02 | 2015-11-09 | 5 | 2015-11-09 | [14 empty] | 2015-12-07 | 2015-12-14 |  | Y
Central Hudson |  | Lotus Energy Inc. | CH-03890 | Kingston | Woodstock | Ulster | 12498 | G | 3014 | Woodstock | N |  | 3 | [13 empty] | NM | N | SMA 3000 TL-US-22 | 2015-11-02 | 2015-11-09 | 5 | 2015-11-09 | [14 empty] | 2016-01-04 | 2016-01-11 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00985 | Kingston | Grahamsvl | Sullivan | 12740 | G | 3091 | Neversink | N |  | 5.16 | [13 empty] | NM | N | 24 ENPHASE M215 60-2LL-S22 | 2015-11-02 | 2015-11-09 | 5 | 2015-11-09 | [14 empty] | 2016-01-14 | 2016-01-21 |  | Y
Central Hudson |  | Paradise Energy Solutions LLC | CH-02838 | Newburgh | Newburgh | Orange | 12550 | G | 4002 | Montgomery St | N |  | 16 | [13 empty] | NM | N | SMA AMERICA 5000TL-US-22 (2) SMA AMERICA 6000TL-US-22 (1) | 2015-11-02 | 2015-11-09 | 5 | 2015-11-09 | [14 empty] | 2016-01-18 | 2016-01-25 |  | Y
Central Hudson |  | Sungevity Inc | CH-09172 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7053 | Rhinebeck | N |  | 8 | [13 empty] | NM | N | (1) ABB PVI-4.2-OUTD-S-US-A (1) ABB PVI-3.8-OUTD-S-US-A | 2015-11-02 | 2015-11-09 | 5 | 2015-11-09 | [14 empty] | 2016-01-15 | 2016-01-22 |  | Y
Central Hudson |  | Kasselman Solar | CH-03519 | Catskill | Coxsackie | Greene | 12051 | G | 1071 | Coxsackie | N |  | 15 | [13 empty] | NM | N | 60 ENPHASE M250 US | 2015-11-03 | 2015-11-09 | 4 | 2015-11-09 | [14 empty] | 2015-12-29 | 2016-01-06 |  | Y
Central Hudson |  | NRG Home Solar | CH-04225 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8091 | Fishkill Plains | N |  | 5.16 | [13 empty] | NM | N | ENPHASEM-215-60-2LL-S22-IG (24) | 2015-11-03 | 2015-11-06 | 3 | 2015-11-06 | [14 empty] | 2016-03-01 | 2016-03-08 |  | Y
Central Hudson |  | Green Hybrid Energy Solutions | CH-01164 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8093 | Fishkill Plains | N |  | 11.4 | [13 empty] | NM | N | SOLAR EDGE SE11400A-US | 2015-12-02 | 2015-12-02 | 0 | 2015-12-02 | [14 empty] | 2016-06-02 | 2016-06-03 |  | Y
Central Hudson |  | Hudson Solar | CH-01855 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7053 | Rhinebeck | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE-7600A-US | 2015-11-11 | 2015-11-18 | 5 | 2015-11-18 | [14 empty] | 2015-12-09 | 2015-12-15 |  | Y
Central Hudson |  | Hudson Solar | CH-02058 | Kingston | Saugerties | Ulster | 12477 | G | 3001 | Saugerties | N |  | 7 | [13 empty] | NM | N | SMA AMERICA SB7000 TL-US-22 | 2015-11-03 | 2015-11-10 | 5 | 2015-11-10 | [14 empty] | 2015-12-31 | 2016-01-08 |  | Y
Central Hudson |  | Northeast Smart Energy LLC | CH-02772 | Fishkill | Garrison | Putnam | 10524 | G | 8066 | Merritt Park | N |  | 20.2 | [13 empty] | NM | N | SOLAR EDGE SE5000A SOLAR EDGE SE7600A (2) | 2015-11-11 | 2015-11-11 | 0 | 2015-11-11 | [14 empty] | 2016-04-27 | 2016-05-03 |  | Y
Central Hudson |  | PosiGen Solar | CH-02902 | Catskill | Catskill | Greene | 12414 | G | 2001 | North Catskill | N |  | 10 | [13 empty] | NM | N | SOLAREDGE SE10000A-US | 2015-11-03 | 2015-11-10 | 5 | 2015-11-10 | [14 empty] | 2016-01-21 | 2016-01-28 |  | Y
Central Hudson |  | SolarCity | CH-05020 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6096 | Manchester | N |  | 7.2 | [13 empty] | NM | N | (2) ABB PVI-3.6-OUTD-S | 2015-11-03 | 2015-11-10 | 5 | 2015-11-10 | [14 empty] | 2015-11-30 | 2015-11-30 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-05043 | Newburgh | Highland | Ulster | 12528 | G | 5022 | Ohioville | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000-OUTD | 2015-11-03 | 2015-11-10 | 5 | 2015-11-10 | [14 empty] | 2015-11-30 | 2015-12-07 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-05231 | Kingston | Saugerties | Ulster | 12477 | G | 2015 | Lincoln Park | N |  | 12 | [13 empty] | NM | N | 2 ABB PVI-6000-OUTD US | 2015-11-03 | 2015-11-09 | 4 | 2015-11-09 | [8 empty] | 350 | 350 |  | 2015-12-11 | 2015-12-11 | 2016-01-08 | 2016-05-10 | 2016-05-16 |  | Y
Central Hudson |  | SolarCity | CH-05399 | Newburgh | Rock Tvrn | Orange | 12575 | G | 4097 | Bethlehem Rd | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000-OUTD | 2015-11-03 | 2015-11-06 | 3 | 2015-11-06 | [14 empty] | 2015-12-15 | 2015-12-15 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-05807 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6046 | Spackenkill | N |  | 15.8 | [13 empty] | NM | N | (1) FRONIUS PRIMO 8.2 (1) FRONIUS PRIMO 7.6 | 2015-11-03 | 2015-11-10 | 5 | 2015-11-10 | [14 empty] | 2015-12-21 | 2015-12-21 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06271 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 9 | [13 empty] | NM | N | ABB PVI-6000-OUTD ABB PVI-3.0-OUTD-S | 2015-11-03 | 2015-11-06 | 3 | 2015-11-06 | [14 empty] | 2016-01-11 | 2016-01-13 |  | Y
Central Hudson |  | SolarCity | CH-06301 | Newburgh | Newburgh | Orange | 12550 | G | 4015 | West Balmville | N |  | 10.2 | [13 empty] | NM | N | ABB PVI-6000-OUTD ABB PVI-4.2-OUTD-S | 2015-11-03 | 2015-11-06 | 3 | 2015-11-06 | [14 empty] | 2016-02-03 | 2016-02-03 |  | Y
Central Hudson |  | SolarCity | CH-06957 | Newburgh | New Paltz | Ulster | 12561 | G | 5031 | Galeville | N | CH-06957 | 5 | [13 empty] | NM | N | ABB PVI-5000-OUTD | 2015-11-03 | 2015-11-05 | 2 | 2015-11-05 | [14 empty] | 2015-12-14 | 2016-01-05 |  | Y
Central Hudson |  | SolarCity | CH-07233 | Kingston | Saugerties | Ulster | 12477 | G | 3003 | Saugerties | N |  | 5 | [13 empty] | NM | N | ABB PVI-5000-OUTD US | 2015-11-03 | 2015-11-09 | 4 | 2015-11-09 | [14 empty] | 2015-12-15 | 2015-12-22 |  | Y
Central Hudson |  | SolarCity | CH-07731 | Kingston | Kingston | Ulster | 12401 | G | 1003 | Jansen Ave | N |  | 5 | [13 empty] | NM | N | ABB PVI-5000-OUTD US | 2015-11-03 | 2015-11-09 | 4 | 2015-11-09 | [14 empty] | 2015-12-15 | 2015-12-22 |  | Y
Central Hudson |  | SolarCity | CH-07859 | Kingston | W Shokan |  | 12494 | G | 3011 | Woodstock | TBD |  | 4.2 | [13 empty] | NM | N | ABB PVI-4.2-OUTD-S US | 2015-11-03 | 2015-11-10 | 5 | 2015-11-10 | [17 empty] | W
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08781 | Catskill | Westerlo | Albany | 12193 | G | 1091 | Westerlo | N |  | 7.31 | [13 empty] | NM | N | 34 ENPHASE M215 602LLS2XZC | 2015-11-03 | 2015-11-10 | 5 | 2015-11-10 | [14 empty] | 2016-04-29 | 2016-05-06 |  | Y
Central Hudson |  | Sol Providers | CH-08928 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7052 | Rhinebeck | N |  | 4 | [13 empty] | NM | N | SMA SunnyBoy 4000TL | 2015-11-11 | 2015-11-18 | 5 | 2015-11-18 | [14 empty] | 2015-11-18 | 2015-11-24 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Sungevity Inc | CH-09342 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8043 | Myers Corners | N |  | 3.8 | [13 empty] | NM | N | ABB PVI-3.8-OUTD-S-US-A | 2015-11-03 | 2015-11-06 | 3 | 2015-11-06 | [14 empty] | 2016-05-31 | 2016-06-03 |  | Y
Central Hudson |  | Sungevity Inc | CH-09450 | Fishkill | Stormvl | Dutchess | 12582 | G | 8095 | Fishkill Plains | N |  | 9.8 | [13 empty] | NM | N | ABB PVI-6000-OUTD-US-A ABB PVI-3.8-OUTD-S-US-A | 2015-11-03 | 2015-11-06 | 3 | 2015-11-06 | [14 empty] | 2016-01-22 | 2016-01-26 |  | Y
Central Hudson |  | NRG Home Solar | CH-04575 | Poughkeepsie | Tivoli | Dutchess | 12583 | G | 7062 | Milan | N |  | 6.02 | [13 empty] | NM | N | (28) ENPHASE ENERGY M-215 | 2015-11-11 | 2015-11-18 | 5 | 2015-11-18 | [14 empty] | 2016-01-07 | 2016-01-14 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | PosiGen Solar | CH-02891 | Kingston | Tillson | Ulster | 12486 | G | 3021 | High Falls | N |  | 4.75 | [13 empty] | NM | N | 19 ENPHASE M250 US | 2015-11-04 | 2015-11-11 | 5 | 2015-11-11 | [14 empty] | 2016-01-21 | 2016-01-28 |  | Y
Central Hudson |  | NRG Home Solar | CH-04246 | Catskill | Athens | Greene | 12051 | G | 2002 | North Catskill | N |  | 4.5 | [13 empty] | NM | N | 18 ENPHASE M-250-60-2LL-S22 | 2015-11-05 | 2015-11-13 | 6 | 2015-11-13 | [14 empty] | 2016-01-11 | 2016-01-18 |  | Y
Central Hudson |  | NRG Home Solar | CH-04454 | Newburgh | Newburgh | Orange | 12550 | G | 4024 | Coldenham | N |  | 5.75 | [13 empty] | NM | N | ENPHASE M-250-60-2LL-S22 (23) | 2015-11-05 | 2015-11-09 | 2 | 2015-11-09 | [14 empty] | 2016-02-01 | 2016-02-01 |  | Y
Central Hudson |  | NRG Home Solar | CH-04543 | Poughkeepsie | Poughkeepsie |  | 12603 | G | 6046 | Spackenkill | TBD |  | 5 | [13 empty] | NM | N | ENPHASE M-250-60-2LL-S22 (20) | 2015-11-05 | 2015-11-18 | 9 | 2015-11-18 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | NRG Home Solar | CH-04586 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8043 | Myers Corners | N |  | 4.3 | [13 empty] | NM | N | ENPHASE M-215-60-2LL-S22-IG (20) | 2015-11-09 | 2015-11-10 | 1 | 2015-11-10 | [14 empty] | 2016-01-27 | 2016-01-28 |  | Y
Central Hudson |  | Conscious Energy | CH-00804 | Kingston | Olive Brdg | Ulster | 12461 | G | 3023 | High Falls | N |  | 10 | [13 empty] | NM | N | 40 ENPHASE M250 US | 2015-11-05 | 2015-11-13 | 6 | 2015-11-13 | [14 empty] | 2016-01-28 | 2016-02-04 |  | Y
Central Hudson |  | Hudson Solar | CH-01466 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6056 | Todd Hill | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE-5000 | 2015-11-05 | 2015-11-18 | 9 | 2015-11-18 | [14 empty] | 2015-12-17 | 2015-12-22 |  | Y
Central Hudson |  | Hudson Solar | CH-01873 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7054 | Rhinebeck | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE-5000 | 2015-11-05 | 2015-11-18 | 9 | 2015-11-18 | [14 empty] | 2016-01-18 | 2016-01-25 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Hudson Solar | CH-02062 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6011 | Sand Dock | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE-5000 | 2015-11-05 | 2015-11-18 | 9 | 2015-11-18 | [14 empty] | 2015-12-31 | 2016-01-08 |  | Y
Central Hudson |  | SolarCity | CH-07507 | Kingston | Saugerties | Ulster | 12477 | G | 3003 | Saugerties | N |  | 3 | [13 empty] | NM | N | ABB PVI-3.0-OUTD-S-US-Z | 2015-11-05 | 2015-11-13 | 6 | 2015-11-13 | [14 empty] | 2016-02-01 | 2016-02-08 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08746 | Kingston | Lk Katrine | Ulster | 12449 | G | 2016 | Lincoln Park | N |  | 6.45 | [13 empty] | NM | N | 30 ENPHASE M125 602LLS2XZC | 2015-11-05 | 2015-11-13 | 6 | 2015-11-13 | [14 empty] | 2016-06-09 | 2016-06-15 |  | Y
Central Hudson |  | Lotus Energy Inc. | CH-03849 | Catskill | Palenvl | Greene | 12463 | G | 2001 | North Catskill | N |  | 7 | [13 empty] | NM | N | SMA SB7000 TL-US-22 | 2015-11-06 | 2015-11-16 | 6 | 2015-11-16 | [8 empty] | 350 | 350 |  | 2015-12-17 | 2015-12-17 | 2015-12-26 | 2015-12-28 | 2016-01-05 |  | Y
Central Hudson |  | NRG Home Solar | CH-04272 | Kingston | Ellenvl | Ulster | 12428 | G | 3076 | Greenfield Rd | N |  | 6 | [13 empty] | NM | N | 24 ENPHASE M-250-60-2LL-S22 | 2015-11-06 | 2015-11-16 | 6 | 2015-11-16 | [14 empty] | 2016-02-01 | 2016-02-08 |  | Y
Central Hudson |  | NRG Home Solar | CH-04321 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 6074 | East Park | N |  | 6.75 | [13 empty] | NM | N | (27) ENPHASE M-250-60-2LL-S22 | 2015-11-06 | 2015-11-20 | 10 | 2015-11-20 | [14 empty] | 2016-03-24 | 2016-04-01 |  | Y
Central Hudson |  | NRG Home Solar | CH-04356 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7051 | Rhinebeck | N |  | 3.25 | [13 empty] | NM | N | (13) ENPHASE M-250-60-2LL-S22 | 2015-11-06 | 2015-11-20 | 10 | 2015-11-20 | [14 empty] | 2016-02-08 | 2016-02-08 |  | Y
Central Hudson |  | SolarCity | CH-05201 | Newburgh | Montgomery | Orange | 12549 | G | 5054 | Maybrook | N |  | 15.2 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 (2) | 2015-11-06 | 2015-11-09 | 1 | 2015-11-09 | [14 empty] | 2015-11-30 | 2015-12-02 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07801 | Catskill | Athens | Greene | 12015 | G | 1074 | Coxsackie | N | CH-05580 | 3 | [13 empty] | NM | N | SOLAREDGE SE3000A US | 2015-11-06 | 2015-11-16 | 6 | 2015-11-16 | [14 empty] | 2016-01-18 | 2016-01-19 |  | Y
Central Hudson |  | Sungevity Inc | CH-09457 | Fishkill | Beacon | Dutchess | 12508 | G | 8015 | Forgebrook | N |  | 3 | [13 empty] | NM | N | ABB PVI-3.0-OUTD-S-US-A | 2015-11-06 | 2015-11-09 | 1 | 2015-11-09 | [14 empty] | 2016-02-25 | 2016-02-29 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03790 | Newburgh | New Paltz | Ulster | 12561 | G | 5023 | Ohioville | N |  | 10 | [13 empty] | NM | N | SOLAREDGE 10000 A-US | 2015-11-19 | 2015-11-19 | 0 | 2015-11-19 | [14 empty] | 2015-12-18 | 2015-12-28 |  | Y
Central Hudson |  | Apex Solar Power | CH-00694 | Fishkill | Beacon | Dutchess | 12508 | G | 8085 | Tioronda | N |  | 7.6 | [13 empty] | NM | N | SOLAR EDGE SE7600-US | 2015-11-12 | 2015-11-13 | 1 | 2015-11-13 | [14 empty] | 2015-12-30 | 2016-01-07 |  | Y
Central Hudson |  | SolarCity | CH-05255 | Poughkeepsie | Salt Pt | Dutchess | 12578 | G | 7011 | Hibernia | N |  | 5 | [13 empty] | NM | N | ABB PVI-5000-OUTD | 2015-11-09 | 2015-11-23 | 10 | 2015-11-23 | [14 empty] | 2015-12-15 | 2015-12-21 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-05319 | Catskill | Athens | Greene | 12015 | G | 1074 | Coxsackie | N |  | 3 | [13 empty] | NM | N | ABB PVI-3.0-OUTD-S US | 2015-11-09 | 2015-11-16 | 5 | 2015-11-16 | [14 empty] | 2015-12-15 | 2015-12-22 |  | Y
Central Hudson |  | SolarCity | CH-05385 | Newburgh | Highland | Ulster | 12528 | G | 5083 | Highland | N |  | 4.2 | [13 empty] | NM | N | ABB PVI-4.2-OUTD-S | 2015-11-09 | 2015-11-23 | 10 | 2015-11-23 | [14 empty] | 2015-12-15 | 2015-12-21 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06020 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8043 | Myers Corners | N |  | 9 | [13 empty] | NM | N | ABB PVI-6000-OUTD ABB PVI-3.0-OUTD-S | 2015-11-09 | 2015-11-09 | 0 | 2015-11-09 | [14 empty] | 2015-12-14 | 2015-12-14 |  | Y
Central Hudson |  | SolarCity | CH-06200 | Newburgh | Newburgh | Orange | 12550 | G | 4014 | West Balmville | N |  | 6.6 | [13 empty] | NM | N | ABB PVI-3.0-OUTD-S ABB PVI-3.6-OUTD-S | 2015-11-09 | 2015-11-09 | 0 | 2015-11-09 | [14 empty] | 2016-02-12 | 2016-02-19 |  | Y
Central Hudson |  | SolarCity | CH-07131 | Newburgh | New Windsor | Orange | 12553 | G | 4097 | Bethlehem Rd | N |  | 8.2 | [13 empty] | NM | N | FRONIUS PRIMO 8.2 | 2015-11-09 | 2015-11-09 | 0 | 2015-11-09 | [14 empty] | 2015-12-29 | 2016-01-06 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Sunrun Inc. | CH-08336 | Newburgh | Newburgh | Orange | 12550 | G | 4011 | West Balmville | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE7600A-US | 2015-11-09 | 2015-11-09 | 0 | 2015-11-09 | [14 empty] | 2015-12-03 | 2015-12-03 |  | Y
Central Hudson |  | New York State Solar Farm | CH-04027 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6042 | Spackenkill | N |  | 9 | [13 empty] | NM | N | SMA AMERICA SB3000TL SMA AMERICA SB6000TL | 2015-11-17 | 2015-12-01 | 8 | 2015-12-01 | [14 empty] | 2015-12-04 | 2015-12-10 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | NRG Home Solar | CH-04165 | Kingston | Kingston | Ulster | 12401 | G | 2011 | Lincoln Park | N |  | 10 | [13 empty] | NM | N | SOLAR EDGE SE10000A-US | 2015-11-10 | 2015-11-17 | 5 | 2015-11-17 | [14 empty] | 2015-12-31 | 2016-01-08 |  | Y
Central Hudson |  | NRG Home Solar | CH-04319 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 6073 | East Park | N |  | 3.75 | [13 empty] | NM | N | (15) ENPHASE M-250-60-2LL-S22 | 2015-11-10 | 2015-11-23 | 9 | 2015-11-23 | [14 empty] | 2016-01-05 | 2016-01-12 |  | Y
Central Hudson |  | NRG Home Solar | CH-04349 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 7024 | Tinkertown | N |  | 5.805 | [13 empty] | NM | N | (27) ENPHASE M-215-60-2LL-S22-IG | 2015-11-23 | 2015-12-02 | 5 | 2015-12-02 | [14 empty] | 2016-02-04 | 2016-02-10 |  | Y
Central Hudson |  | NRG Home Solar | CH-04353 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6092 | Manchester | N |  | 4 | [13 empty] | NM | N | (16) ENPHASE M-250-60-2LL-S22 | 2015-11-10 | 2015-11-23 | 9 | 2015-11-23 | [14 empty] | 2016-01-11 | 2016-01-15 |  | Y
Central Hudson |  | NRG Home Solar | CH-04367 | Poughkeepsie | Pine Plns | Dutchess | 12567 | G | 7091 | Pulvers Corners | N |  | 4.5 | [13 empty] | NM | N | (18) ENPHASE M-250-60-2LL-S22 | 2015-11-19 | 2015-11-30 | 5 | 2015-11-30 | [14 empty] | 2016-01-12 | 2016-01-13 |  | Y
Central Hudson |  | NRG Home Solar | CH-04368 | Poughkeepsie | Clinton Corners |  | 12514 | G | 7071 | Stanfordville | TBD |  | 7.6 | [13 empty] | NM | N | SOLAR EDGE SE7600A-US | 2015-11-30 | 2015-12-07 | 5 | 2015-12-07 | [17 empty] | W
Central Hudson |  | NRG Home Solar | CH-04493 | Newburgh | New Windsor | Orange | 12553 | G | 4046 | Union Ave | N |  | 7.6 | [13 empty] | NM | N | SOLAR EDGE SE7600A-US | 2015-12-03 | 2015-12-03 | 0 | 2015-12-03 | [14 empty] | 2016-01-04 | 2016-01-11 |  | Y
Central Hudson |  | NRG Home Solar | CH-04701 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 6073 | East Park | N |  | 5.25 | [13 empty] | NM | N | (21) ENPHASE M-250-60-2LL-S22 | 2015-11-17 | 2015-11-24 | 5 | 2015-11-24 | [14 empty] | 2016-03-24 | 2016-04-01 |  | Y
Central Hudson |  | NRG Home Solar | CH-04767 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7054 | Rhinebeck | N |  | 5.59 | [13 empty] | NM | N | (26) ENPHASE M-215-60-2LL-S22-IG | 2015-11-17 | 2015-12-01 | 8 | 2015-12-01 | [14 empty] | 2016-02-12 | 2016-02-22 |  | Y
Central Hudson |  | SolarCity | CH-05327 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6051 | Todd Hill | N |  | 9.2 | [13 empty] | NM | N | (1) ABB PVI-4.2-OUTD-S US (1) ABB PVI-5000-OUTD-S US | 2015-11-10 | 2015-11-23 | 9 | 2015-11-23 | [14 empty] | 2016-02-03 | 2016-02-09 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06162 | Newburgh | New Paltz | Ulster | 12561 | G | 5011 | Modena | N |  | 8.2 | [13 empty] | NM | N | FRONIUS PRIMO 8.2 | 2015-11-10 | 2015-11-10 | 0 | 2015-11-10 | [14 empty] | 2015-12-14 | 2015-12-15 |  | Y
Central Hudson |  | SolarCity | CH-06617 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6044 | Spackenkill | N |  | 8 | [13 empty] | NM | N | ABB PVI-3.0-OUTD-S US ABB PVI-5000-OUTD US | 2015-11-10 | 2015-11-23 | 9 | 2015-11-23 | [14 empty] | 2016-05-23 | 2016-05-27 |  | Y
Central Hudson |  | SolarCity | CH-07087 | Newburgh | Wallkill | Ulster | 12589 | G | 5043 | East Walden | N |  | 8.2 | [13 empty] | NM | N | FRONIUS PRIMO 8.2 | 2015-11-10 | 2015-11-10 | 0 | 2015-11-10 | [14 empty] | 2015-12-31 | 2016-01-07 |  | Y
Central Hudson |  | SolarCity | CH-07461 | Newburgh | Wallkill | Ulster | 12589 | G | 5043 | East Walden | N |  | 16.4 | [13 empty] | NM | N | FRONIUS PRIMO 8.2 (2) | 2015-11-10 | 2015-11-10 | 0 | 2015-11-10 | [14 empty] | 2016-01-11 | 2016-01-13 |  | Y
Central Hudson |  | American Solar Partners | CH-03071 | Fishkill | Stormvl | Dutchess | 12582 | G | 8071 | Shenandoah | N |  | 7.6 | [13 empty] | NM | N | SOLAR EDGE SE7600 | 2015-11-11 | 2015-11-18 | 5 | 2015-11-18 | [14 empty] | 2016-01-20 | 2016-01-26 |  | Y
Central Hudson |  | Lotus Energy Inc. | CH-03889 | Kingston | Kingston | Ulster | 12401 | G | 1011 | Boulevard | N |  | 3.8 | [13 empty] | NM | N | SMA SB3800 TL-US-22 | 2015-11-11 | 2015-11-20 | 7 | 2015-11-20 | [14 empty] | 2016-02-03 | 2016-02-10 |  | Y
Central Hudson |  | New York State Solar Farm | CH-04022 | Kingston | Hurley | Ulster | 12443 | G | 2094 | Hurley Ave | N |  | 7.6 | [13 empty] | NM | N | 2 SMA AMERICA SB3800-TL | 2015-11-11 | 2015-11-20 | 7 | 2015-11-20 | [14 empty] | 2016-01-19 | 2016-01-26 |  | Y
Central Hudson |  | Aegis Energy Services, Inc. | CH-00638 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 6051 | Todd Hill | Y | CH-04901 | [8 empty] | 75 | [5 empty] | NA | N | ThermoPower 75 LE | 2015-12-22 | 2016-01-15 | 15 | 2016-01-15 | 2015-12-22 | 2016-01-15 | 15 | [11 empty] | 2016-02-25 | 2016-02-29 |  | Y
Central Hudson |  | Apex Solar Power | CH-00685 | Fishkill | Beacon | Dutchess | 12508 | G | 8085 | Tioronda | N |  | 3.8 | [13 empty] | NM | N | SOLAR EDGE SE3800A-US | 2015-11-11 | 2015-11-18 | 5 | 2015-11-18 | [14 empty] | 2015-12-31 | 2016-01-07 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Hudson Solar | CH-01252 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7058 | Rhinebeck | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE-7600A-US | 2015-11-11 | 2015-11-18 | 5 | 2015-11-18 | [14 empty] | 2016-01-18 | 2016-01-25 |  | Y
Central Hudson |  | Hudson Solar | CH-01983 | Newburgh | Wallkill | Ulster | 12589 | G | 5043 | East Walden | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE-6000 | 2015-11-11 | 2015-11-12 | 1 | 2015-11-12 | [14 empty] | 2016-05-04 | 2016-05-06 |  | Y
Central Hudson |  | Hudson Solar | CH-02108 | Poughkeepsie | Wappingrs Fls | Dutchess | 12590 | G | 6052 | Todd Hill | N |  | 10 | [13 empty] | NM | N | SOLAREDGE SE-10000A-US | 2015-11-11 | 2015-11-25 | 10 | 2015-11-25 | [14 empty] | 2015-12-31 | 2016-01-08 |  | Y
Central Hudson |  | Hudson Solar | CH-02125 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7061 | Milan | N |  | 10 | [13 empty] | NM | N | SOLAREDGE SE-10000A-US | 2015-11-11 | 2015-11-25 | 10 | 2015-11-25 | [14 empty] | 2015-12-22 | 2015-12-29 |  | Y
Central Hudson |  | SolarCity | CH-05034 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7054 | Rhinebeck | N |  | 11 | [13 empty] | NM | N | (1) ABB PVI-5000-OUTD-US-Z-A (1) ABB PVI-6000-OUTD-US-Z-A | 2015-11-11 | 2015-11-25 | 10 | 2015-11-25 | [14 empty] | 2015-12-15 | 2015-12-21 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06635 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6042 | Spackenkill | N |  | 3 | [13 empty] | NM | N | ABB PVI-3.0-OUTD-S | 2016-01-26 | 2016-02-02 | 5 | 2016-02-02 | [14 empty] | 2016-02-24 | 2016-03-01 |  | Y
Central Hudson |  | Apex Solar Power | CH-03095 | Catskill | Westerlo | Albany | 12193 | G | 1092 | Westerlo | N |  | 3 | [13 empty] | NM | N | SOLAREDGE SE3000A-US | 2015-11-12 | 2015-11-20 | 6 | 2015-11-20 | [14 empty] | 2015-12-28 | 2016-01-05 |  | Y
Central Hudson |  | NRG Home Solar | CH-04230 | Catskill | Catskill | Greene | 12414 | G | 2001 | North Catskill | N |  | 4.75 | [13 empty] | NM | N | 19 ENPHASE ENERGY M250 | 2015-11-12 | 2015-11-20 | 6 | 2015-11-20 | [14 empty] | 2016-01-12 | 2016-01-19 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00883 | Poughkeepsie | Lagrangevl | Dutchess | 12540 | G | 6055 | Todd Hill | N |  | 18.5 | [13 empty] | NM | N | (74) ENPHASE M250 60-2LL-S22 | 2015-11-24 | 2015-12-02 | 4 | 2015-12-02 | [14 empty] | 2016-09-23 | 2016-09-26 |  | Y
Central Hudson |  | Hudson Solar | CH-02438 | Kingston | Kingston | Ulster | 12401 | G | 112 | South Wall St | N | CH-00643 | 7.6 | [13 empty] | NM | N | SOLAREDGE SE-7600 | 2015-11-16 | 2015-11-16 | 0 | 2015-11-16 | [14 empty] | 2015-11-23 | 2015-12-01 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-05404 | Newburgh | New Windsor | Orange | 12553 | G | 4046 | Union Ave | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000-OUTD US | 2015-11-12 | 2015-11-12 | 0 | 2015-11-12 | [14 empty] | 2015-12-15 | 2015-12-15 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06121 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8093 | Fishkill Plains | N |  | 3.6 | [13 empty] | NM | N | ABB PVI-3.6-OUTD-S US | 2015-11-12 | 2015-11-12 | 0 | 2015-11-12 | [14 empty] | 2015-12-15 | 2015-12-15 |  | Y
Central Hudson |  | SolarCity | CH-06152 | Fishkill | Beacon | Dutchess | 12508 | G | 8087 | Tioronda | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2015-11-12 | 2015-11-12 | 0 | 2015-11-12 | [14 empty] | 2015-12-18 | 2015-12-28 |  | Y
Central Hudson |  | SolarCity | CH-06190 | Newburgh | Newburgh | Orange | 12550 | G | 4013 | West Balmville | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A-US | 2015-11-13 | 2015-11-13 | 0 | 2015-11-13 | [14 empty] | 2016-02-11 | 2016-02-19 |  | Y
Central Hudson |  | SolarCity | CH-06334 | Newburgh | Marlboro | Ulster | 12542 | G | 5002 | Marlboro | N |  | 6.6 | [13 empty] | NM | N | ABB PVI-3.0-OUTD-S-US-Z- ABB PVI-3.6-OUTD-S-US-Z- | 2015-11-12 | 2015-11-12 | 0 | 2015-11-12 | [14 empty] | 2016-01-11 | 2016-01-13 |  | Y
Central Hudson |  | SolarCity | CH-06831 | Fishkill | Poughkeepsie | Dutchess | 12603 | G | 8024 | Knapps Corners | N |  | 8 | [13 empty] | NM | N | ABB PVI-3.0-OUTD-S-US-Z- ABB PVI-5000-OUTD-US-Z-A | 2015-11-12 | 2015-11-12 | 0 | 2015-11-12 | [14 empty] | 2016-01-11 | 2016-01-13 |  | Y
Central Hudson |  | SolarCity | CH-06884 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8014 | Forgebrook | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2015-11-12 | 2015-11-12 | 0 | 2015-11-12 | [14 empty] | 2015-12-18 | 2015-12-21 |  | Y
Central Hudson |  | SolarCity | CH-06894 | Fishkill | Beacon | Dutchess | 12508 | G | 8016 | Forgebrook | N |  | 3 | [13 empty] | NM | N | ABB PVI-3.0-OUTD-S-US-Z- | 2015-11-12 | 2015-11-12 | 0 | 2015-11-12 | [14 empty] | 2015-12-15 | 2015-12-15 |  | Y
Central Hudson |  | SolarCity | CH-06913 | Fishkill | Hopewell Jct |  | 12533 | G | 8093 | Fishkill Plains | TBD |  | 3 | [13 empty] | NM | N | ABB PVI-3.0-OUTD-S-US-Z- | 2015-11-13 | 2015-11-13 | 0 | 2015-11-13 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | SolarCity | CH-07208 | Kingston | Rosendale | Ulster | 12472 | G | 3022 | High Falls | N |  | 7.2 | [13 empty] | NM | N | ABB PVI-4.2-OUTD-S-US-Z ABB PVI-3.0-OUTD-S-US-Z | 2015-11-12 | 2015-11-20 | 6 | 2015-11-20 | [14 empty] | 2015-12-31 | 2016-01-07 |  | Y
Central Hudson |  | SolarCity | CH-07407 | Fishkill | Cold Spg | Putnam | 10516 | G | 8063 | Merritt Park | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2015-11-12 | 2015-11-12 | 0 | 2015-11-12 | [14 empty] | 2016-01-12 | 2016-01-13 |  | Y
Central Hudson |  | SolarCity | CH-07568 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8096 | Fishkill Plains | N |  | 3 | [13 empty] | NM | N | ABB PVI-3.0-OUTD-S-US-Z- | 2015-12-08 | 2015-12-08 | 0 | 2015-12-08 | [14 empty] | 2016-02-16 | 2016-02-23 |  | Y
Central Hudson |  | SolarCity | CH-07588 | Newburgh | New Paltz | Ulster | 12561 | G | 5024 | Ohioville | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000-OUTD-US-Z-A | 2015-11-12 | 2015-11-13 | 1 | 2015-11-13 | [14 empty] | 2015-12-14 | 2015-12-14 |  | Y
Central Hudson |  | SolarCity | CH-07722 | Newburgh | Newburgh | Orange | 12550 | G | 4045 | Union Ave | N |  | 8.2 | [13 empty] | NM | N | FRONIUS PRIMO 8.2 | 2015-11-12 | 2015-11-13 | 1 | 2015-11-13 | [14 empty] | 2016-03-01 | 2016-03-08 |  | Y
Central Hudson |  | Sunrun Inc. | CH-08347 | Newburgh | New Windsor | Orange | 12553 | G | 4045 | Union Ave | N |  | 10.5 | [13 empty] | NM | N | ENPHASE ENERGY M250-60-2LL-S2X (42) | 2015-11-18 | 2015-11-24 | 4 | 2015-11-24 | [14 empty] | 2016-03-31 | 2016-04-07 |  | Y
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03122 | Newburgh | Walden | Orange | 12586 | G | 5043 | East Walden | N |  | 2000 | [13 empty] | CDG | N | (44) Huawei SUN2000-45KTL-US | 2015-12-16 | 2016-01-11 | 15 | 2016-01-11 | 2015-12-16 | 2016-01-11 | 15 | 2016-03-18 | 2016-05-03 | 2016-07-28 | 60 | 8268 | 256112 | 128956.75 | 2017-03-01 | 2017-08-24 | 2017-08-24 | 2019-02-19 | 2019-07-25 | 2019-07-31 | 2019-11-07 | Y |  | CESIR for 3 Projects, CH-03122. CH-03138, CH-03143 Combined. Only proceeding with CH-03122.
Central Hudson |  | NRG Home Solar | CH-04359 | Poughkeepsie | Tivoli |  | 12583 | G | 7051 | Rhinebeck | TBD |  | 3.01 | [13 empty] | NM | N | ENPHASE ENERGY 215 (14) | 2015-11-13 | 2015-11-20 | 5 | 2015-11-20 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | NRG Home Solar | CH-04409 | Fishkill | Fishkill |  | 12524 | G | 8062 | Merritt Park | TBD |  | 4 | [13 empty] | NM | N | ENPHASE M-250-60-2LL-S22 (16) | 2015-11-13 | 2015-11-13 | 0 | 2015-11-13 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | Apex Solar Power | CH-00705 | Kingston | Woodstock | Ulster | 12498 | G | 3014 | Woodstock | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE7600A-US | 2015-11-13 | 2015-11-23 | 6 | 2015-11-23 | [14 empty] | 2016-04-25 | 2016-04-25 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00872 | Newburgh | Newburgh |  | 12550 | G | 4015 | West Balmville | N |  | 7.1 | [13 empty] | NM | N | ENPHASE M215 60-2LL-S22 (33) | 2015-11-13 | 2015-11-13 | 0 | 2015-11-13 | [17 empty] | W
Central Hudson |  | SolarCity | CH-05064 | Newburgh | Newburgh | Orange | 12550 | G | 4022 | Coldenham | N |  | 10 | [13 empty] | NM | N | ABB PVI-5000-OUTD-US-Z-A (2) | 2015-12-08 | 2015-12-08 | 0 | 2015-12-08 | [14 empty] | 2015-12-22 | 2015-12-31 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-05702 | Kingston | Kingston | Ulster | 12401 | G | 1011 | Boulevard | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000-OUTD-US-Z-A | 2015-11-13 | 2015-11-23 | 6 | 2015-11-23 | [14 empty] | 2015-12-18 | 2015-12-29 |  | Y
Central Hudson |  | SolarCity | CH-06595 | Kingston | Saugerties | Ulster | 12477 | G | 1021 | East Kingston | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000-OUTD-US-Z-A | 2015-11-13 | 2015-11-23 | 6 | 2015-11-23 | [14 empty] | 2015-12-14 | 2015-12-21 |  | Y
Central Hudson |  | SolarCity | CH-06632 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6003 | Reynolds Hill | N |  | 6 | [13 empty] | NM | N | ABB PVI-3.0-OUTD-S-US-Z- (2) | 2015-11-13 | 2015-11-20 | 5 | 2015-11-20 | [14 empty] | 2015-12-15 | 2015-12-21 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07561 | Fishkill | Wappingers Falls | Dutchess | 12590 | G | 8043 | Myers Corners | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE7600A US | 2015-11-13 | 2015-11-13 | 0 | 2015-11-13 | [14 empty] | 2015-11-13 | 2015-11-13 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07615 | Newburgh | Washingtonvl | Orange | 10992 | G | 4097 | Bethlehem Rd | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000-OUTD-US-Z-A | 2015-11-13 | 2015-11-13 | 0 | 2015-11-13 | [14 empty] | 2015-12-31 | 2016-01-07 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08622 | Kingston | Kingston | Ulster | 12401 | G | 1021 | East Kingston | N |  | 2.15 | [13 empty] | NM | N | 10 ENPHASE M215 602LLS2XZC | 2015-11-13 | 2015-11-23 | 6 | 2015-11-23 | [14 empty] | 2016-07-19 | 2016-07-20 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08729 | Catskill | Freehold |  | 12431 | G | 2071 | Freehold | TBD |  | 5.59 | [13 empty] | NM | N | 26 ENPHASE M215 602LLS2XZC | 2015-11-13 | 2015-11-20 | 5 | 2015-11-20 | [17 empty] | W |  | Transformer upgrade required to accommodate PV installation.
Central Hudson |  | Kirchhoff Green Energy LLC | CH-03538 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6044 | Spackenkill | N |  | 12 | [13 empty] | NM | N | (2) ABB PVI 6000 | 2015-11-18 | 2015-11-19 | 1 | 2015-11-19 | [14 empty] | 2016-01-29 | 2016-02-05 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | New York State Solar Farm | CH-04101 | Newburgh | Gardiner |  | 12525 | G | 5034 | Galeville | TBD |  | 3 | [13 empty] | NM | N | SMA AMERICA SB3000TL | 2015-11-16 | 2015-11-16 | 0 | 2015-11-16 | [14 empty] | 2016-01-13 | 2016-01-15 |  | W
Central Hudson |  | Apex Solar Power | CH-00704 | Catskill | Greenvl | Greene | 12083 | G | 2061 | Freehold | N |  | 11.4 | [13 empty] | NM | N | SOLAREDGE SE11400 A-US | 2015-11-16 | 2015-11-24 | 6 | 2015-11-24 | [14 empty] | 2015-12-16 | 2015-12-23 |  | Y
Central Hudson |  | SolarCity | CH-05652 | Kingston | Accord | Ulster | 12404 | G | 3083 | Kerhonkson | N |  | 8.4 | [13 empty] | NM | N | 2 ABB PVI-4.2-OUTD-S-US | 2015-11-16 | 2015-11-23 | 5 | 2015-11-23 | [14 empty] | 2015-12-15 | 2015-12-22 |  | Y
Central Hudson |  | SolarCity | CH-06502 | Kingston | Kingston | Ulster | 12401 | G | 2013 | Lincoln Park | N |  | 3 | [13 empty] | NM | N | ABB PVI-3.0-OUTD-S US | 2015-11-16 | 2015-11-24 | 6 | 2015-11-24 | [14 empty] | 2015-12-15 | 2015-12-22 |  | Y
Central Hudson |  | SolarCity | CH-06586 | Kingston | Kingston | Ulster | 12401 | G | 2091 | Hurley Ave | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2015-11-16 | 2015-11-24 | 6 | 2015-11-24 | [14 empty] | 2015-12-15 | 2015-12-22 |  | Y
Central Hudson |  | SolarCity | CH-07022 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2015-11-16 | 2015-11-16 | 0 | 2015-11-16 | [14 empty] | 2015-12-14 | 2015-12-14 |  | Y
Central Hudson |  | SolarCity | CH-07036 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 9.2 | [13 empty] | NM | N | ABB PVI-4.2-OUTD-S US ABB PVI-5000-OUTD US | 2015-11-16 | 2015-11-16 | 0 | 2015-11-16 | [14 empty] | 2016-01-22 | 2016-01-26 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07685 | Newburgh | Newburgh | Orange | 12550 | G | 4011 | West Balmville | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000-OUTD | 2015-11-16 | 2015-11-16 | 0 | 2015-11-16 | [14 empty] | 2015-12-15 | 2015-12-17 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07720 | Newburgh | Walden | Orange | 12586 | G | 5042 | East Walden | N |  | 11 | [13 empty] | NM | N | ABB PVI-6000-OUTD US ABB PVI-5000-OUTD US | 2015-11-16 | 2015-11-19 | 3 | 2015-11-19 | [14 empty] | 2015-12-14 | 2015-12-17 |  | Y
Central Hudson |  | Self | CH-08867 | Catskill | Medusa | Albany | 12120 | G | 1092 | Westerlo | N |  | 0.76 | [13 empty] | NM | N | ENPHASE M190 (4) | 2015-11-16 | 2015-11-16 | 0 | 2015-11-16 | [14 empty] | 2020-08-31 | 2020-08-31 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-03504 | Newburgh | Cornwall-Hdsn | Orange | 12520 | G | 4043 | Union Ave | N |  | 6 | [13 empty] | NM | N | SMA AMERICA SB6000TL-US-22 | 2015-11-17 | 2015-11-18 | 1 | 2015-11-18 | [14 empty] | 2016-01-11 | 2016-01-13 |  | Y
Central Hudson |  | Hudson Solar | CH-01393 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7052 | Rhinebeck | N |  | 3.8 | [13 empty] | NM | N | SOLAREDGE SE-3800A-US-U | 2015-11-17 | 2015-11-24 | 5 | 2015-11-24 | [14 empty] | 2015-12-31 | 2016-01-08 |  | Y
Central Hudson |  | Hudson Solar | CH-01697 | Kingston | Kingston |  | 12401 | G | 2092 | Hurley Ave | TBD |  | 3 | [13 empty] | NM | N | SMA AMERICA SB3000 TL-US-22 | 2015-11-17 | 2015-11-24 | 5 | 2015-11-24 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | Hudson Solar | CH-01752 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 6075 | East Park | N |  | 10 | [13 empty] | NM | N | SolarEdge SE10000A-US | 2015-11-17 | 2015-12-01 | 8 | 2015-12-01 | [14 empty] | 2016-03-23 | 2016-03-31 |  | Y
Central Hudson |  | Hudson Solar | CH-01766 | Poughkeepsie | Staatsburg | Dutchess | 12580 | G | 7041 | Staatsburg | N |  | 10 | [13 empty] | NM | N | SOLAREDGE SE-10000A-US-U | 2015-11-17 | 2015-11-24 | 5 | 2015-11-24 | [14 empty] | 2017-02-16 | 2017-02-16 |  | Y
Central Hudson |  | Hudson Solar | CH-01804 | Poughkeepsie | Pleasant Vly |  | 12569 | G | 6051 | Todd Hill | TBD |  | 8 | [13 empty] | NM | N | (2) SMA AMERICA SB4000TL-US-22 | 2015-11-17 | 2015-12-01 | 8 | 2015-12-01 | [17 empty] | W
Central Hudson |  | Hudson Solar | CH-02020 | Kingston | Rosendale | Ulster | 12472 | G | 1011 | Boulevard | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE-7600 A-US-U | 2015-11-17 | 2015-11-24 | 5 | 2015-11-24 | [14 empty] | 2015-12-30 | 2016-01-07 |  | Y
Central Hudson |  | Hudson Solar | CH-02021 | Kingston | Hurley | Ulster | 12443 | G | 2093 | Hurley Ave | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE-7600A-US-U | 2015-11-17 | 2015-11-24 | 5 | 2015-11-24 | [14 empty] | 2016-07-29 | 2016-08-01 |  | Y
Central Hudson |  | Hudson Solar | CH-02155 | Poughkeepsie | Pine Plns | Dutchess | 12567 | G | 7091 | Pulvers Corners | N |  | 10 | [13 empty] | NM | N | SOLAREDGE SE-10000A-US-U | 2015-11-17 | 2015-11-24 | 5 | 2015-11-24 | [14 empty] | 2016-05-25 | 2016-06-02 |  | Y
Central Hudson |  | Hudson Solar | CH-02318 | Newburgh | New Paltz | Ulster | 12561 | G | 5024 | Ohioville | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE-7600 | 2015-11-17 | 2015-11-20 | 3 | 2015-11-20 | [14 empty] | 2016-02-03 | 2016-02-04 |  | Y |  | Customer already had net meter prior to application.
Central Hudson |  | Hudson Solar | CH-02328 | Newburgh | Wallkill | Ulster | 12589 | G | 5041 | East Walden | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE-7600 | 2015-11-19 | 2015-11-19 | 0 | 2015-11-19 | [14 empty] | 2015-12-30 | 2016-01-07 |  | Y
Central Hudson |  | SolarCity | CH-05678 | Kingston | Woodstock | Ulster | 12498 | G | 3012 | Woodstock | N |  | 5 | [13 empty] | NM | N | ABB PVI-5000-OUTD US | 2015-11-17 | 2015-11-24 | 5 | 2015-11-24 | [14 empty] | 2016-01-04 | 2016-01-11 |  | Y
Central Hudson |  | SolarCity | CH-06273 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000-OUTD-US | 2015-11-17 | 2015-11-17 | 0 | 2015-11-17 | [14 empty] | 2015-12-15 | 2015-12-15 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06420 | Newburgh | Montgomery | Orange | 12549 | G | 5073 | Montgomery | N |  | 8 | [13 empty] | NM | N | ABB PVI-5000-OUTD-US ABB PVI-3.0-OUTD-S-US | 2015-11-17 | 2015-11-17 | 0 | 2015-11-17 | [14 empty] | 2015-12-14 | 2015-12-14 |  | Y
Central Hudson |  | SolarCity | CH-07558 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8091 | Fishkill Plains | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000-OUTD US | 2015-11-17 | 2015-11-17 | 0 | 2015-11-17 | [14 empty] | 2015-12-15 | 2015-12-15 |  | Y
Central Hudson |  | Trinity Solar | CH-08458 | Newburgh | Wallkill | Ulster | 12589 | G | 5013 | Modena | N |  | 16 | [13 empty] | NM | N | SOLAR EDGE SE 7600A-US SOLAR EDGE SE 5000A-US | 2015-11-24 | 2015-12-01 | 3 | 2015-12-01 | [8 empty] | 350 | 350 |  |  |  |  | 2016-05-24 | 2016-06-08 |  | Y
Central Hudson |  | Apex Solar Power | CH-03098 | Poughkeepsie | Salt Pt | Dutchess | 12578 | G | 7011 | Hibernia | N |  | 10 | [13 empty] | NM | N | SOLAR EDGE SE10000A-US | 2015-11-18 | 2015-12-01 | 7 | 2015-12-01 | [14 empty] | 2016-03-04 | 2016-03-11 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-03423 | Newburgh | New Windsor | Orange | 12553 | G | 4044 | Union Ave | N |  | 5 | [13 empty] | NM | N | SMA AMERICA SB5000TL-US-22 | 2015-11-18 | 2015-11-23 | 3 | 2015-11-23 | [14 empty] | 2016-01-20 | 2016-01-26 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-03468 | Newburgh | Milton | Ulster | 12547 | G | 5003 | Marlboro | N |  | 7.6 | [13 empty] | NM | N | SMA AMERICA SB3800TL-US-22(2) | 2015-11-19 | 2015-11-19 | 0 | 2015-11-19 | [14 empty] | 2016-05-16 | 2016-05-23 |  | Y
Central Hudson |  | Apex Solar Power | CH-00674 | Catskill | Catskill | Greene | 12414 | G | 2001 | North Catskill | N |  | 20 | [13 empty] | NM | N | 2 SOLAREDGE SE10000A-US | 2015-11-18 | 2015-11-30 | 6 | 2015-11-30 | [14 empty] | 2016-01-15 | 2016-01-21 |  | Y
Central Hudson |  | SolarCity | CH-05060 | Newburgh | Highland | Ulster | 12528 | G | 5024 | Ohioville | N |  | 5 | [13 empty] | NM | N | ABB PVI-5000 | 2015-12-11 | 2015-12-14 | 1 | 2015-12-14 | [14 empty] | 2016-02-11 | 2016-02-19 |  | Y
Central Hudson |  | SolarCity | CH-05308 | Newburgh | Wallkill | Ulster | 12589 | G | 5043 | East Walden | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000-OUTD-US | 2015-11-18 | 2015-11-18 | 0 | 2015-11-18 | [14 empty] | 2015-12-15 | 2015-12-15 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06822 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8052 | North Chelsea | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2015-11-18 | 2015-11-18 | 0 | 2015-11-18 | [14 empty] | 2015-12-31 | 2016-01-07 |  | Y
Central Hudson |  | SolarCity | CH-06925 | Fishkill | Beacon | Dutchess | 12508 | G | 8013 | Forgebrook | N |  | 5 | [13 empty] | NM | N | ABB PVI-5000-OUTD-US | 2015-11-18 | 2015-11-18 | 0 | 2015-11-18 | [14 empty] | 2015-12-18 | 2015-12-28 |  | Y
Central Hudson |  | SolarCity | CH-07053 | Newburgh | Wallkill | Ulster | 12589 | G | 5012 | Modena | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2015-11-18 | 2015-11-18 | 0 | 2015-11-18 | [14 empty] | 2016-01-04 | 2016-01-11 |  | Y
Central Hudson |  | SolarCity | CH-07527 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6042 | Spackenkill | N |  | 4.2 | [13 empty] | NM | N | ABB PVI-4.2-OUTD-S | 2016-01-05 | 2016-01-12 | 5 | 2016-01-12 | [14 empty] | 2016-01-18 | 2016-01-25 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Sunrun Inc. | CH-08338 | Newburgh | Cornwall-Hdsn | Orange | 12520 | G | 4043 | Union Ave | N |  | 4.75 | [13 empty] | NM | N | ENPHASE ENERGY M250-60-2LL-S2X (19) | 2015-11-19 | 2015-11-19 | 0 | 2015-11-19 | [14 empty] | 2016-04-14 | 2016-04-14 |  | Y
Central Hudson |  | Sol Providers | CH-08913 | Poughkeepsie | Lagrangevl | Dutchess | 12540 | G | 6055 | Todd Hill | N |  | 18 | [13 empty] | NM | N | SMA 6000 TL (3) | 2015-11-18 | 2015-12-01 | 7 | 2015-12-01 | [14 empty] | 2015-12-15 | 2015-12-16 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | You Save Green | CH-09956 | Newburgh | Maybrook | Orange | 12543 | G | 5052 | Maybrook | N |  | 6 | [13 empty] | NM | N | SOLAR EDGE SE6000 | 2015-11-19 | 2015-11-19 | 0 | 2015-11-19 | [14 empty] | 2016-07-08 | 2016-07-13 |  | Y
Central Hudson |  | NRG Home Solar | CH-04237 | Catskill | Cairo | Greene | 12413 | G | 2041 | South Cairo | N |  | 6 | [13 empty] | NM | N | SOLAR EDGE SE6000A-US | 2015-11-19 | 2015-11-30 | 5 | 2015-11-30 | [14 empty] | 2016-01-13 | 2016-01-20 |  | Y
Central Hudson |  | NRG Home Solar | CH-04258 | Kingston | High Fls |  | 12440 | G | 3022 | High Falls | TBD |  | 4.75 | [13 empty] | NM | N | 19 ENPHASE M-250-60-2LL-S22 | 2015-11-19 | 2015-11-30 | 5 | 2015-11-30 | [17 empty] | W |  | 11/26 & 11/27/2015 Company Holiday. Customer already had net meter prior to application.
Central Hudson |  | NRG Home Solar | CH-04580 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8091 | Fishkill Plains | N |  | 7 | [13 empty] | NM | N | ENPHASE M-250-60-2LL-S22 (28) | 2015-11-19 | 2015-11-19 | 0 | 2015-11-19 | [14 empty] | 2016-02-17 | 2016-02-24 |  | Y
Central Hudson |  | NRG Home Solar | CH-04675 | Newburgh | Newburgh | Orange | 12550 | G | 4091 | Bethlehem Rd | N |  | 7.5 | [13 empty] | NM | N | Enphase m250 | 2015-11-19 | 2015-11-19 | 0 | 2015-11-19 | [14 empty] | 2016-01-29 | 2016-02-01 |  | Y
Central Hudson |  | NRG Home Solar | CH-04776 | Newburgh | Newburgh | Orange | 12550 | G | 4051 | Union Ave | N |  | 2.79 | [13 empty] | NM | N | ENPHASE M-215-60-2LL-S22 (13) | 2015-11-19 | 2015-11-19 | 0 | 2015-11-19 | [14 empty] | 2016-02-12 | 2016-02-19 |  | Y
Central Hudson |  | NRG Home Solar | CH-04831 | Newburgh | New Paltz |  | 12561 | G | 5011 | Modena | TBD |  | 10 | [13 empty] | NM | N | SOLAR EDGE SE10000A-US | 2015-11-19 | 2015-11-19 | 0 | 2015-11-19 | [15 empty] | 2016-07-06 |  | W |  | Customer already had net meter prior to application.
Central Hudson |  | Apex Solar Power | CH-00696 | Fishkill | Cold Spg | Putnam | 10516 | G | 8087 | Tioronda | N |  | 3.8 | [13 empty] | NM | N | SOLAR EDGE SE3800A-US | 2015-11-19 | 2015-11-19 | 0 | 2015-11-19 | [14 empty] | 2016-04-12 | 2016-04-14 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08673 | Kingston | Kingston | Ulster | 12401 | G | 1021 | East Kingston | N | CH-08673 | 6.67 | [13 empty] | NM | N | 31 ENPHASE M215 602LLS2XZC | 2015-11-19 | 2015-11-30 | 5 | 2015-11-30 | [14 empty] | 2016-06-23 | 2016-06-29 |  | Y
Central Hudson |  | Monolith Solar Associates LLC | CH-02644 | Catskill | Coeymans Hollow | Albany | 12046 | G | 1071 | Coxsackie | N |  | 12 | [13 empty] | NM | N | 2 SOLAR EDGE SE6000-US | 2015-11-20 | 2015-12-01 | 5 | 2015-12-01 | [8 empty] | 350 | 350 |  | 2016-02-01 | 2016-02-01 | 2016-02-11 | 2016-02-06 | 2016-04-21 |  | Y
Central Hudson |  | Sunrun Inc. | CH-08330 | Fishkill | Garrison | Putnam | 10524 | G | 8066 | Merritt Park | N | CH-08330 | 3 | [13 empty] | NM | N | ABB PVI-3.0-OUTD-S-US-A | 2015-11-24 | 2015-11-24 | 0 | 2015-11-24 | [14 empty] | 2015-12-21 | 2015-12-30 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08670 | Kingston | Saugerties | Ulster | 12477 | G | 3001 | Saugerties | N |  | 7.525 | [13 empty] | NM | N | 35 ENPHASE M125-602LLS2XZC | 2015-11-20 | 2015-12-01 | 5 | 2015-12-01 | [14 empty] | 2016-06-23 | 2016-06-29 |  | Y
Central Hudson |  | American Solar Partners | CH-03077 | Kingston | Lk Katrine | Ulster | 12449 | G | 2011 | Lincoln Park | N |  | 5 | [13 empty] | NM | N | SOLAR EDGE SE5000-US | 2015-11-23 | 2015-12-02 | 5 | 2015-12-02 | [14 empty] | 2015-12-16 | 2015-12-23 |  | Y
Central Hudson |  | New York State Solar Farm | CH-03940 | Newburgh | Newburgh | Orange | 12550 | G | 5004 | Marlboro | N |  | 5 | [13 empty] | NM | N | SMA AMERICA SB5000TL | 2015-11-24 | 2015-11-24 | 0 | 2015-11-24 | [14 empty] | 2015-12-18 | 2015-12-21 |  | Y
Central Hudson |  | New York State Solar Farm | CH-03975 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6042 | Spackenkill | N |  | 3 | [13 empty] | NM | N | SOLAREDGE SE3000-A-US | 2015-11-23 | 2015-12-02 | 5 | 2015-12-02 | [14 empty] | 2016-01-06 | 2016-01-13 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | New York State Solar Farm | CH-04064 | Fishkill | Beacon | Dutchess | 12508 | G | 8085 | Tioronda | N |  | 5 | [13 empty] | NM | N | SMA AMERICA SB5000TL | 2015-11-23 | 2015-11-24 | 1 | 2015-11-24 | [14 empty] | 2015-12-07 | 2015-12-07 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Apex Solar Power | CH-00682 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8043 | Myers Corners | N |  | 10 | [13 empty] | NM | N | SOLAR EDGE SE10000A-US | 2015-12-11 | 2015-12-28 | 9 | 2015-12-28 | [14 empty] | 2016-01-05 | 2016-01-12 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Monolith Solar Associates LLC | CH-02695 | Catskill | W Coxsackie |  | 12192 | G | 1083 | New Baltimore | TBD |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A-US | 2015-11-23 | 2015-12-02 | 5 | 2015-12-02 | [17 empty] | W
Central Hudson |  | SolarCity | CH-05016 | Kingston | Saugerties | Ulster | 12477 | G | 2015 | Lincoln Park | N |  | 10 | [13 empty] | NM | N | 2 ABB PVI-5000-OUTD-US-Z-A | 2015-11-23 | 2015-12-02 | 5 | 2015-12-02 | [8 empty] | 350 | 350 |  | 2015-12-23 | 2015-12-23 | 2016-02-03 | 2016-02-11 | 2016-02-19 |  | Y
Central Hudson |  | SolarCity | CH-05056 | Newburgh | New Paltz | Ulster | 12561 | G | 5024 | Ohioville | N |  | 3 | [13 empty] | NM | N | ABB PVI-3.0-OUTD-S-US-Z- | 2015-11-23 | 2015-11-24 | 1 | 2015-11-24 | [14 empty] | 2015-12-18 | 2015-12-28 |  | Y
Central Hudson |  | SolarCity | CH-05464 | Newburgh | Highland | Ulster | 12528 | G | 5083 | Highland | N |  | 8.4 | [13 empty] | NM | N | ABB PVI-4.2-OUTD-S-US-Z (2) | 2015-11-23 | 2015-12-02 | 5 | 2015-12-02 | [14 empty] | 2016-01-18 | 2016-01-25 |  | Y
Central Hudson |  | SolarCity | CH-05836 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6073 | East Park | N |  | 8 | [13 empty] | NM | N | ABB PVI-3.0-OUTD-S-US-Z- ABB PVI-5000-OUTD-US-Z-A | 2015-11-23 | 2015-12-02 | 5 | 2015-12-02 | [14 empty] | 2015-12-17 | 2015-12-22 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-05962 | Poughkeepsie | Tivoli | Dutchess | 12583 | G | 7062 | Milan | N |  | 3 | [13 empty] | NM | N | ABB PVI-3.0-OUTD-S-US-Z- | 2015-12-02 | 2015-12-08 | 4 | 2015-12-08 | [14 empty] | 2016-01-13 | 2016-01-20 |  | Y
Central Hudson |  | SolarCity | CH-06241 | Newburgh | Newburgh | Orange | 12550 | G | 4014 | West Balmville | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2015-11-23 | 2015-11-24 | 1 | 2015-11-24 | [14 empty] | 2016-01-04 | 2016-01-11 |  | Y
Central Hudson |  | SolarCity | CH-06278 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2015-11-23 | 2015-11-24 | 1 | 2015-11-24 | [14 empty] | 2015-12-09 | 2015-12-09 |  | Y
Central Hudson |  | SolarCity | CH-06828 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8052 | North Chelsea | N |  | 6 | [13 empty] | NM | N | ABB PVI-3.0-OUTD-S-US-Z- (2) | 2015-11-23 | 2015-11-24 | 1 | 2015-11-24 | [14 empty] | 2016-01-27 | 2016-01-28 |  | Y
Central Hudson |  | SolarCity | CH-06859 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8092 | Fishkill Plains | N |  | 3.6 | [13 empty] | NM | N | ABB PVI-3.6-OUTD-S | 2015-11-23 | 2015-11-24 | 1 | 2015-11-24 | [14 empty] | 2015-12-15 | 2015-12-15 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07617 | Newburgh | Campbell Hall | Orange | 10916 | G | 5052 | Maybrook | N |  | 11.4 | [13 empty] | NM | N | FRONIUS IG PLUS A 11.4 | 2015-11-23 | 2015-11-24 | 1 | 2015-11-24 | [14 empty] | 2016-01-04 | 2016-01-11 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08639 | Catskill | Catskill | Greene | 12414 | G | 2005 | North Catskill | N |  | 13.33 | [13 empty] | NM | N | 62 ENPHASE M215-602LLS2XZC | 2015-11-23 | 2015-12-02 | 5 | 2015-12-02 | [14 empty] | 2016-06-10 | 2016-06-10 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08669 | Kingston | Saugerties | Ulster | 12477 | G | 3004 | Saugerties | N |  | 10.32 | [13 empty] | NM | N | 48 ENPHASE M215-602LLS2XZC | 2015-11-23 | 2015-12-02 | 5 | 2015-12-02 | [14 empty] | 2016-06-15 | 2016-06-17 |  | Y
Central Hudson |  | Sol Providers | CH-08954 | Fishkill | Beacon |  | 12508 | G | 8013 | Forgebrook | N |  | 6.8 | [13 empty] | NM | N | SMA 3800TL SMA 3000TL | 2015-12-03 | 2015-12-04 | 1 | 2015-12-04 | [14 empty] | 2016-02-19 | 2016-02-26 |  | W |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SunDog Solar | CH-09145 | Poughkeepsie | Salt Pt | Dutchess | 12578 | G | 6074 | East Park | N |  | 21 | [13 empty] | NM | N | SMA SB6000TL US (3) SMA SB3000TL US (1) | 2015-12-11 | 2015-12-17 | 4 | 2015-12-17 | [14 empty] | 2016-01-05 | 2016-01-05 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Infinity Solar Systems | CH-03487 | Newburgh | Newburgh | Orange | 12550 | G | 4044 | Union Ave | N |  | 6 | [13 empty] | NM | N | SMA AMERICA SB6000TL-US-22 | 2015-11-24 | 2015-11-24 | 0 | 2015-11-24 | [14 empty] | 2016-01-11 | 2016-01-13 |  | Y
Central Hudson |  | New York State Solar Farm | CH-04075 | Fishkill | Beacon | Dutchess | 12508 | G | 8017 | Forgebrook | N |  | 3.8 | [13 empty] | NM | N | SMA AMERICA SB3800TL | 2015-11-25 | 2015-11-25 | 0 | 2015-11-25 | [14 empty] | 2015-12-07 | 2015-12-07 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | NRG Home Solar | CH-04267 | Kingston | Kingston |  | 12401 | G | 1022 | East Kingston | TBD |  | 3.25 | [13 empty] | NM | N | 13 ENPHASE M250 | 2015-11-24 | 2015-12-04 | 6 | 2015-12-04 | [17 empty] | W |  | Customer already had net meter prior to application. 11/26 & 11/27/2015 Company Holiday.
Central Hudson |  | NRG Home Solar | CH-04340 | Poughkeepsie | Poughkeepsie |  | 12603 | G | 6092 | Manchester | TBD |  | 5.59 | [13 empty] | NM | N | ENPHASE M215 (26) | 2015-12-03 | 2015-12-09 | 4 | 2015-12-09 | [17 empty] | W |  | Customer already had net meter prior to application. 11/26/15 & 11/27/15 Company Holidays.
Central Hudson |  | NRG Home Solar | CH-04494 | Newburgh | Newburgh | Orange | 12550 | G | 4095 | Bethlehem Rd | N |  | 10 | [13 empty] | NM | N | SOLAR EDGE SE10000A-US | 2015-11-24 | 2015-11-24 | 0 | 2015-11-24 | [14 empty] | 2016-02-25 | 2016-02-29 |  | Y
Central Hudson |  | SolarCity | CH-04962 | Kingston | Tillson | Ulster | 12486 | G | 3021 | High Falls | N |  | 12 | [13 empty] | NM | N | 2 ABB PVI-6000-OUTD-US-Z-A | 2015-11-24 | 2015-12-04 | 6 | 2015-12-04 | [14 empty] | 2015-12-31 | 2016-01-08 |  | Y
Central Hudson |  | SolarCity | CH-06145 | Fishkill | Beacon | Dutchess | 12508 | G | 8085 | Tioronda | N |  | 5 | [13 empty] | NM | N | ABB PVI-5000-OUTD-US-Z-A | 2015-11-24 | 2015-11-24 | 0 | 2015-11-24 | [14 empty] | 2015-12-31 | 2016-01-07 |  | Y
Central Hudson |  | SolarCity | CH-07441 | Newburgh | New Windsor | Orange | 12553 | G | 4045 | Union Ave | N |  | 3 | [13 empty] | NM | N | ABB PVI-3.0-OUTD-S-US-Z | 2015-11-24 | 2015-11-24 | 0 | 2015-11-24 | [14 empty] | 2016-04-05 | 2016-04-12 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08603 | Catskill | Catskill | Greene | 12414 | G | 2002 | North Catskill | N |  | 6.45 | [13 empty] | NM | N | 30 ENPHASE M215-602LLS2XZC | 2015-11-24 | 2015-12-04 | 6 | 2015-12-04 | [14 empty] | 2016-07-18 | 2016-07-19 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-03464 | Newburgh | Newburgh | Orange | 12550 | G | 4023 | Coldenham | N |  | 10 | [13 empty] | NM | N | SMA AMERICA SB5000TL-US-22(2) | 2015-11-25 | 2015-11-25 | 0 | 2015-11-25 | [14 empty] | 2016-03-28 | 2016-04-04 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03745 | Newburgh | New Paltz | Ulster | 12561 | G | 5031 | Galeville | N |  | 11.4 | [13 empty] | NM | N | SOLAREDGE 11400 A-US | 2015-11-25 | 2015-11-25 | 0 | 2015-11-25 | [14 empty] | 2016-01-22 | 2016-01-26 |  | Y
Central Hudson |  | New York State Solar Farm | CH-04012 | Newburgh | Clintondale | Ulster | 12515 | G | 5012 | Modena | N |  | 7.6 | [13 empty] | NM | N | SMA AMERICA SB3800TL (2) | 2015-11-25 | 2015-11-25 | 0 | 2015-11-25 | [14 empty] | 2015-12-11 | 2015-12-15 |  | Y
Central Hudson |  | New York State Solar Farm | CH-04091 | Newburgh | Highland | Ulster | 12528 | G | 5082 | Highland | N |  | 6.8 | [13 empty] | NM | N | SMA AMERICA SB3800TL SMA AMERICA SB3000TL | 2015-11-25 | 2015-12-03 | 4 | 2015-12-03 | [14 empty] | 2015-12-17 | 2015-12-21 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | 212 Solar Development, LLC | CH-00594 | Kingston | Kerhonkson |  | 12446 | G | 3071 | Honk Falls | TBD |  | 1980 | [13 empty] | RNM | N | (33) SUNGROW SG60KU-M | 2016-01-08 | 2016-01-29 | 15 | 2016-01-29 | 2016-01-08 | 2016-01-29 | 15 |  |  |  |  | 38500 | [9 empty] | W |  | 11/26/15 & 11/27/15 Company Holidays. CESIR determined necessary during preliminary review Section C, Step 4.
Central Hudson |  | 212 Solar Development, LLC | CH-00595 | Kingston | Kerhonkson |  | 12446 | G | 3071 | Honk Falls | TBD |  | 1980 | [13 empty] | RNM | N | (33) SUNGROW SG60KU-M | 2016-01-08 | 2016-01-29 | 15 | 2016-01-29 | 2016-01-08 | 2016-01-29 | 15 |  |  |  |  | 38500 | [9 empty] | W |  | 11/26/15 & 11/27/15 Company Holidays. CESIR determined necessary during preliminary review Section C, Step 4.
Central Hudson |  | 212 Solar Development, LLC | CH-00596 | Kingston | Kerhonkson |  | 12446 | G | 3071 | Honk Falls | TBD |  | 1980 | [13 empty] | RNM | N | (33) SUNGROW SG60KU-M | 2016-01-08 | 2016-01-29 | 15 | 2016-01-29 | 2016-01-08 | 2016-01-29 | 15 |  |  |  |  | 38500 | [9 empty] | W |  | 11/26/15 & 11/27/15 Company Holidays. CESIR determined necessary during preliminary review Section C, Step 4.
Central Hudson |  | 212 Solar Development, LLC | CH-00597 | Kingston | Kerhonkson |  | 12446 | G | 3071 | Honk Falls | TBD |  | 1980 | [13 empty] | RNM | N | (33) SUNGROW SG60KU-M | 2016-01-08 | 2016-01-29 | 15 | 2016-01-29 | 2016-01-08 | 2016-01-29 | 15 |  |  |  |  | 38500 | [9 empty] | W |  | 11/26/15 & 11/27/15 Company Holidays. CESIR determined necessary during preliminary review Section C, Step 4.
Central Hudson |  | SolarCity | CH-05129 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8091 | Fishkill Plains | N |  | 8.2 | [13 empty] | NM | N | FRONIUS PRIMO 8.2 | 2015-11-25 | 2015-11-25 | 0 | 2015-11-25 | [14 empty] | 2016-01-04 | 2016-01-11 |  | Y
Central Hudson |  | SolarCity | CH-06140 | Fishkill | Beacon | Dutchess | 12508 | G | 8017 | Forgebrook | N |  | 4.2 | [13 empty] | NM | N | ABB PVI-4.2-OUTD-S | 2015-11-25 | 2015-11-25 | 0 | 2015-11-25 | [14 empty] | 2015-12-31 | 2016-01-07 |  | Y
Central Hudson |  | SolarCity | CH-06244 | Newburgh | Newburgh | Orange | 12550 | G | 4051 | Union Ave | N |  | 3.6 | [13 empty] | NM | N | ABB PVI-3.6-OUTD-S-US-Z- | 2015-11-25 | 2015-11-25 | 0 | 2015-11-25 | [14 empty] | 2016-01-13 | 2016-01-15 |  | Y
Central Hudson |  | SolarCity | CH-06505 | Kingston | Kingston | Ulster | 12401 | G | 1003 | Jansen Ave | N |  | 3 | [13 empty] | NM | N | SOLAREDGE SE3000A-US-ZB-U | 2015-11-25 | 2015-12-04 | 5 | 2015-12-04 | [14 empty] | 2016-01-04 | 2016-01-15 |  | Y
Central Hudson |  | SolarCity | CH-07065 | Newburgh | Newburgh | Orange | 12550 | G | 5004 | Marlboro | N |  | 8.6 | [13 empty] | NM | N | ABB PVI-5000-OUTD-US-Z-A ABB PVI-3.6-OUTD-S-US-Z- | 2015-12-02 | 2015-12-16 | 10 | 2015-12-16 | [14 empty] | 2016-02-11 | 2016-02-19 |  | Y
Central Hudson |  | SolarCity | CH-07380 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8071 | Shenandoah | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000-OUTD | 2015-11-25 | 2015-11-25 | 0 | 2015-11-25 | [14 empty] | 2015-12-22 | 2015-12-31 |  | Y
Central Hudson |  | Sol Providers | CH-08926 | Poughkeepsie | Pleasant Valley | Dutchess | 12569 | G | 6051 | Todd Hill | N |  | 10 | [13 empty] | NM | N | SOLAREDGE SE 10000A | 2015-11-25 | 2015-12-03 | 4 | 2015-12-03 | [14 empty] | 2016-02-08 | 2016-02-08 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Sungevity Inc | CH-09462 | Fishkill | Cold Spg | Putnam | 10516 | G | 8087 | Tioronda | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000-OUTD-US-A | 2015-11-25 | 2015-11-25 | 0 | 2015-11-25 | [14 empty] | 2016-04-19 | 2016-04-20 |  | Y
Central Hudson |  | Sungevity Inc | CH-09531 | Poughkeepsie | Millbrook | Dutchess | 12545 | G | 7025 | Tinkertown | N |  | 13.6 | [13 empty] | NM | N | ABB PVI-6000-OUTD-US-A (1) ABB PVI-3.8-OUTD-S-US-A (2) | 2016-01-12 | 2016-01-26 | 10 | 2016-01-26 | [14 empty] | 2016-01-27 | 2016-02-03 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Lotus Energy Inc. | CH-03871 | Catskill | Catskill | Greene | 12414 | G | 2001 | North Catskill | N |  | 7.7 | [13 empty] | NM | N | SMA SB7700 TL-US-22 | 2015-11-30 | 2015-12-07 | 5 | 2015-12-07 | [14 empty] | 2015-12-21 | 2015-12-30 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | New York State Solar Farm | CH-03971 | Kingston | W Hurley | Ulster | 12491 | G | 3013 | Woodstock | N |  | 3.8 | [13 empty] | NM | N | SMA AMERICA SB3800 TL | 2015-11-30 | 2015-12-08 | 6 | 2015-12-08 | [14 empty] | 2016-02-01 | 2016-02-08 |  | Y
Central Hudson |  | Apex Solar Power | CH-00677 | Kingston | Woodstock | Ulster | 12498 | G | 3012 | Woodstock | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE6000A-US | 2015-11-30 | 2015-12-07 | 5 | 2015-12-07 | [14 empty] | 2016-02-12 | 2016-02-22 |  | Y
Central Hudson |  | Apex Solar Power | CH-00692 | Fishkill | Beacon | Dutchess | 12508 | G | 8015 | Forgebrook | N |  | 3.8 | [13 empty] | NM | N | SOLAR EDGE SE3800A-US | 2015-11-30 | 2015-11-30 | 0 | 2015-11-30 | [14 empty] | 2016-01-12 | 2016-01-13 |  | Y
Central Hudson |  | Apex Solar Power | CH-00713 | Kingston | Woodstock |  | 12498 | G | 3012 | Woodstock | TBD |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A-US | 2015-11-30 | 2015-12-07 | 5 | 2015-12-07 | [17 empty] | W
Central Hudson |  | SolarCity | CH-05917 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 6092 | Manchester | N |  | 9.6 | [13 empty] | NM | N | (1) ABB PVI-6000-OUTD-US (1) ABB PVI-3.6-OUTD-US | 2015-11-30 | 2015-12-07 | 5 | 2015-12-07 | [14 empty] | 2015-12-18 | 2015-12-31 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Trinity Solar | CH-08467 | Kingston | Kerhonkson | Ulster | 12446 | G | 3081 | Kerhonkson | N |  | 13 | [13 empty] | NM | N | SOLAREDGE SE10000A-US SOLAREDGE SE3000A-US | 2015-11-30 | 2015-12-07 | 5 | 2015-12-07 | [14 empty] | 2016-01-27 | 2016-02-03 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08743 | Kingston | Saugerties | Ulster | 12477 | G | 3004 | Saugerties | N | CH-08743 | 6.45 | [13 empty] | NM | N | 30 ENPHASE M215 602LLS2XZC | 2015-11-30 | 2015-12-08 | 6 | 2015-12-08 | [14 empty] | 2016-06-21 | 2016-06-24 |  | Y
Central Hudson |  | Sol Providers | CH-08949 | Poughkeepsie | Lagrangevl | Dutchess | 12540 | G | 6055 | Todd Hill | N |  | 10 | [13 empty] | NM | N | SOLAREDGE SE10000A | 2015-12-08 | 2015-12-11 | 3 | 2015-12-11 | [14 empty] | 2015-12-23 | 2016-01-04 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Sungevity Inc | CH-09362 | Newburgh | New Paltz | Ulster | 12561 | G | 5021 | Ohioville | N |  | 6.8 | [13 empty] | NM | N | ABB PVI-3.0-OUTD-S-US-A ABB PVI-3.8-OUTD-S-US-A | 2015-11-30 | 2015-12-01 | 1 | 2015-12-01 | [14 empty] | 2016-04-25 | 2016-04-27 |  | Y
Central Hudson |  | Lotus Energy Inc. | CH-03875 | Kingston | Lk Hill | Ulster | 12448 | G | 3012 | Woodstock | N |  | 6 | [13 empty] | NM | N | SMA SB6000 TL-US-22 | 2015-12-01 | 2015-12-08 | 5 | 2015-12-08 | [14 empty] | 2016-01-04 | 2016-01-11 |  | Y
Central Hudson |  | NRG Home Solar | CH-04429 | Fishkill | Stormvl | Dutchess | 12582 | G | 8093 | Fishkill Plains | N |  | 6 | [13 empty] | NM | N | SOLAR EDGE SE6000A-US | 2015-12-03 | 2015-12-03 | 0 | 2015-12-03 | [14 empty] | 2016-04-20 | 2016-04-22 |  | Y
Central Hudson |  | Hudson Solar | CH-02045 | Kingston | Kingston | Ulster | 12401 | G | 111 | South Wall St | N |  | 3.8 | [13 empty] | NM | N | SOLAREDGE SE-3800 A-US | 2015-12-01 | 2015-12-08 | 5 | 2015-12-08 | [14 empty] | 2015-12-31 | 2016-01-08 |  | Y
Central Hudson |  | SolarCity | CH-05348 | Newburgh | Wallkill | Ulster | 12589 | G | 5011 | Modena | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2015-12-14 | 2015-12-30 | 10 | 2015-12-30 | [14 empty] | 2016-01-05 | 2016-01-12 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-05559 | Catskill | Greenville | Greene | 12083 | G | 2061 | Freehold | N |  | 12 | [13 empty] | NM | N | 2 ABB PVI-6000-OUTD-US | 2015-12-01 | 2015-12-08 | 5 | 2015-12-08 | [14 empty] | 2015-12-15 | 2015-12-22 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-05584 | Catskill | Coxsackie |  | 12051 | G | 1076 | Coxsackie | TBD |  | 7.2 | [13 empty] | NM | N | ABB PVI-4.2-OUTD-S-US ABB PVI-3.0-OUTD-S-US | 2015-12-01 | 2015-12-08 | 5 | 2015-12-08 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | SolarCity | CH-05742 | Kingston | Saugerties | Ulster | 12477 | G | 3001 | Saugerties | N |  | 4.2 | [13 empty] | NM | N | ABB PVI-4.2-OUTD-S-US | 2015-12-01 | 2015-12-08 | 5 | 2015-12-08 | [14 empty] | 2015-12-30 | 2016-01-08 |  | Y
Central Hudson |  | SolarCity | CH-05927 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 7025 | Tinkertown | N |  | 12 | [13 empty] | NM | N | ABB PVI-6000-OUTD-US (2) | 2015-12-01 | 2015-12-08 | 5 | 2015-12-08 | [8 empty] | 350 | 350 |  | 2016-02-03 | 2016-02-03 | 2016-02-12 | 2016-03-08 | 2016-03-15 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06912 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8093 | Fishkill Plains | N |  | 3.6 | [13 empty] | NM | N | ABB PVI-3.6-OUTD-S-US | 2015-12-01 | 2015-12-01 | 0 | 2015-12-01 | [14 empty] | 2016-01-04 | 2016-01-11 |  | Y
Central Hudson |  | SolarCity | CH-07492 | Catskill | Oak Hill | Greene | 12460 | G | 1092 | Westerlo | N |  | 8.2 | [13 empty] | NM | N | FRONIUS 8.2 | 2015-12-01 | 2015-12-09 | 6 | 2015-12-09 | [14 empty] | 2016-01-22 | 2016-01-29 |  | Y
Central Hudson |  | SolarCity | CH-08056 | Catskill | Leeds |  | 12541 | G | 2071 | Freehold | TBD |  | 1960 | [13 empty] | RNM | N | (70) SOLECTRIA RENEWABLES PVI-28TL | 2015-12-21 | 2016-01-14 | 15 | 2016-01-14 | 2015-12-21 | 2016-01-14 | 15 |  |  |  |  | 33000 | [9 empty] | W |  | 12/24/15, 12/25/15 & 1/1/16 Company Holidays. CESIR determined necessary during preliminary review Section C, Step 4.
Central Hudson |  | SolarCity | CH-08057 | Poughkeepsie | Rhinebeck |  | 12572 | G | 7054 | Rhinebeck | TBD |  | 1960 | [13 empty] | RNM | N | (70) SOLECTRIA RENEWABLES PVI-28TL | 2015-12-21 | 2016-01-14 | 15 | 2016-01-14 | 2015-12-21 | 2016-01-14 | 15 |  |  |  |  | 30000 | [9 empty] | W |  | 12/24/15, 12/25/15 & 1/1/16 Company Holidays. CESIR determined necessary during preliminary review Section C, Step 4.
Central Hudson |  | SolarCity | CH-08058 | Newburgh | Walden |  | 12586 | G | 5043 | East Walden | TBD |  | 1960 | [13 empty] | RNM | N | (70) SOLECTRIA RENEWABLES PVI-28TL | 2015-12-16 | 2016-01-11 | 15 | 2016-01-11 | 2015-12-16 | 2016-01-11 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 12/24/15, 12/25/15 & 1/1/16 Company Holidays. CESIR determined necessary during preliminary review Section C, Step 4.
Central Hudson |  | SolarCity | CH-08059 | Catskill | Cairo |  | 12413 | G | 2043 | South Cairo | TBD |  | 1960 | [13 empty] | RNM | N | (70) SOLECTRIA RENEWABLES PVI-28TL | 2015-12-16 | 2016-01-11 | 15 | 2016-01-11 | 2015-12-16 | 2016-01-11 | 15 |  |  |  |  | 32000 | [9 empty] | W |  | 12/24/15, 12/25/15 & 1/1/16 Company Holidays. CESIR determined necessary during preliminary review Section C, Step 4.
Central Hudson |  | SolarCity | CH-08060 | Kingston | Saugerties |  | 12477 | G | 3003 | Saugerties | TBD |  | 1960 | [13 empty] | RNM | N | (70) SOLECTRIA RENEWABLES PVI-28TL | 2015-12-15 | 2016-01-08 | 15 | 2016-01-08 | 2015-12-15 | 2016-01-08 | 15 |  |  |  |  | 32000 | [9 empty] | W |  | 12/24/15, 12/25/15 & 1/1/16 Company Holidays. CESIR determined necessary during preliminary review Section C, Step 4.
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08665 | Kingston | Kingston | Ulster | 12401 | G | 1022 | East Kingston | N |  | 4.51 | [13 empty] | NM | N | 21 ENPHASE M215-60-2LL-S2X-ZC | 2015-12-01 | 2015-12-08 | 5 | 2015-12-08 | [14 empty] | 2016-06-27 | 2016-07-05 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03808 | Kingston | Esopus | Ulster | 12429 | G | 3041 | Sturgeon Pool | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE 7600A-US | 2015-12-02 | 2015-12-09 | 5 | 2015-12-09 | [14 empty] | 2016-08-03 | 2016-08-05 |  | Y
Central Hudson |  | New York State Solar Farm | CH-03928 | Newburgh | Wallkill | Ulster | 12589 | G | 5041 | East Walden | N |  | 7.6 | [13 empty] | NM | N | SMA AMERICA SB3800TL (2) | 2015-12-02 | 2015-12-02 | 0 | 2015-12-02 | [14 empty] | 2016-02-01 | 2016-02-01 |  | Y
Central Hudson |  | NRG Home Solar | CH-04107 | Kingston | Ellenvl | Ulster | 12428 | G | 3096 | Grimley Rd | N |  | 4.3 | [13 empty] | NM | N | 20 ENPHASE M-215-60-2LL-S22-IG | 2015-12-02 | 2015-12-09 | 5 | 2015-12-09 | [14 empty] | 2016-02-01 | 2016-02-08 |  | Y
Central Hudson |  | Apex Solar Power | CH-00676 | Kingston | Kingston | Ulster | 12401 | G | 3021 | High Falls | N | CH-00676 | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A-US | 2015-12-02 | 2015-12-09 | 5 | 2015-12-09 | [14 empty] | 2015-12-29 | 2016-01-15 |  | Y
Central Hudson |  | Hudson Solar | CH-01701 | Kingston | Kingston | Ulster | 12401 | G | 1022 | East Kingston | N |  | 3 | [13 empty] | NM | N | SMA AMERICA SB3000 TL-US-22 | 2015-12-02 | 2015-12-09 | 5 | 2015-12-09 | [14 empty] | 2016-01-18 | 2016-01-25 |  | Y
Central Hudson |  | Hudson Solar | CH-01755 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 7041 | Staatsburg | N |  | 6 | [13 empty] | NM | N | SolarEdge SE6000A | 2015-12-10 | 2015-12-10 | 0 | 2015-12-10 | [14 empty] | 2016-04-20 | 2016-04-27 |  | Y
Central Hudson |  | Hudson Solar | CH-02410 | Poughkeepsie | Tivoli | Dutchess | 12583 | G | 7062 | Milan | N | CH-02410 | 10 | [13 empty] | NM | N | SOLAREDGE SE-10000 | 2015-12-02 | 2015-12-08 | 4 | 2015-12-08 | [14 empty] | 2016-02-03 | 2016-02-09 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03561 | Kingston | Lk Katrine | Ulster | 12449 | G | 2011 | Lincoln Park | N |  | 90 | [13 empty] | RNM | N | (9) ABB PVI 10.0 | 2015-12-22 | 2016-01-15 | 15 | 2016-01-15 | 2015-12-22 | 2016-01-15 | 15 | [11 empty] | 2016-02-25 | 2016-03-08 |  | Y
Central Hudson |  | NRG Home Solar | CH-04247 | Catskill | Athens | Greene | 12015 | G | 2002 | North Catskill | N |  | 2.795 | [13 empty] | NM | N | (13) ENPHASE M-215-60-2LL-S22-IG | 2015-12-03 | 2015-12-10 | 5 | 2015-12-10 | [14 empty] | 2016-01-12 | 2016-01-22 |  | Y
Central Hudson |  | Apex Solar Power | CH-00662 | Newburgh | Newburgh | Orange | 12550 | G | 4023 | Coldenham | N |  | 7.6 | [13 empty] | NM | N | SOLAR EDGE SE7600A-US | 2016-02-29 | 2016-03-14 | 10 | 2016-03-14 | [14 empty] | 2016-03-23 | 2016-03-31 |  | Y
Central Hudson |  | Hudson Solar | CH-01577 | Newburgh | New Paltz | Ulster | 12561 | G | 5011 | Modena | N | CH-01577 | 12 | [13 empty] | NM | N | SMA AMERICA SB6000 TL-US-22 (2) | 2015-12-07 | 2015-12-07 | 0 | 2015-12-07 | [14 empty] | 2016-01-28 | 2016-01-29 |  | Y
Central Hudson |  | Hudson Solar | CH-02512 | Kingston | Hurley |  | 12443 | G | 2094 | Hurley Ave | TBD |  | 6 | [13 empty] | NM | N | SMA AMERICA SB6000 TL-US-22 | 2015-12-03 | 2015-12-10 | 5 | 2015-12-10 | [17 empty] | W
Central Hudson |  | SolarCity | CH-05226 | Newburgh | Wallkill | Ulster | 12589 | G | 5041 | East Walden | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2015-12-03 | 2015-12-03 | 0 | 2015-12-03 | [14 empty] | 2015-12-15 | 2015-12-22 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06336 | Newburgh | Marlboro | Ulster | 12542 | G | 5002 | Marlboro | N |  | 15.2 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 (2) | 2015-12-03 | 2015-12-03 | 0 | 2015-12-03 | [14 empty] | 2016-01-04 | 2016-01-11 |  | Y
Central Hudson |  | SolarCity | CH-06656 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6004 | Reynolds Hill | N |  | 8.2 | [13 empty] | NM | N | FRONIUS PRIMO 8.2 | 2015-12-03 | 2015-12-09 | 4 | 2015-12-09 | [14 empty] | 2016-06-22 | 2016-06-29 |  | Y
Central Hudson |  | SolarCity | CH-06834 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8046 | Myers Corners | N |  | 8.4 | [13 empty] | NM | N | ABB PVI-4.2-OUTD-S-US-Z (2) | 2015-12-03 | 2015-12-04 | 1 | 2015-12-04 | [14 empty] | 2016-01-20 | 2016-01-20 |  | Y
Central Hudson |  | SolarCity | CH-06993 | Newburgh | Newburgh | Orange | 12550 | G | 4023 | Coldenham | N |  | 7.2 | [13 empty] | NM | N | ABB PVI-4.2-OUTD-S-US-Z- ABB PVI-3.0-OUTD-S-US-Z- | 2015-12-03 | 2015-12-04 | 1 | 2015-12-04 | [14 empty] | 2016-01-19 | 2016-01-26 |  | Y
Central Hudson |  | SolarCity | CH-07060 | Newburgh | Newburgh | Orange | 12550 | G | 4011 | West Balmville | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000-OUTD-US-Z-A | 2015-12-03 | 2015-12-03 | 0 | 2015-12-03 | [14 empty] | 2015-12-22 | 2015-12-31 |  | Y
Central Hudson |  | SolarCity | CH-07285 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 6075 | East Park | N |  | 6.6 | [13 empty] | NM | N | ABB PVI-3.0-OUTD-S-US-Z- ABB PVI-3.6-OUTD-S-US-Z- | 2015-12-03 | 2015-12-09 | 4 | 2015-12-09 | [14 empty] | 2016-01-22 | 2016-01-28 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07350 | Fishkill | Poughkeepsie | Dutchess | 12601 | G | 8021 | Knapps Corners | N |  | 3.6 | [13 empty] | NM | N | ABB PVI-3.6-OUTD-S-US-Z | 2015-12-03 | 2015-12-04 | 1 | 2015-12-04 | [14 empty] | 2015-12-31 | 2016-01-11 |  | Y
Central Hudson |  | Self | CH-08880 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8022 | Knapps Corners | N |  | 22.8 | [13 empty] | NM | N | SOLAR EDGE SE11400A-US (2) | 2015-12-03 | 2015-12-07 | 2 | 2015-12-07 | [14 empty] | 2016-05-11 | 2016-05-12 |  | Y
Central Hudson |  | Lotus Energy Inc. | CH-03893 | Kingston | Bearsvl | Ulster | 12409 | G | 3012 | Woodstock | N | CH-03893 | 7.7 | [13 empty] | NM | N | SMA SB7700 TL-US-22 | 2015-12-04 | 2015-12-11 | 5 | 2015-12-11 | [14 empty] | 2016-01-07 | 2016-01-14 |  | Y
Central Hudson |  | SolarCity | CH-05812 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6091 | Manchester | N |  | 3 | [13 empty] | NM | N | ABB PVI-3.0-OUTD-S-US-Z- | 2015-12-04 | 2015-12-09 | 3 | 2015-12-09 | [14 empty] | 2016-01-05 | 2016-01-12 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06323 | Newburgh | Marlboro | Ulster | 12542 | G | 5001 | Marlboro | N |  | 12 | [13 empty] | NM | N | ABB PVI-6000-OUTD-US-Z-A (2) | 2015-12-04 | 2015-12-04 | 0 | 2015-12-04 | [14 empty] | 2015-12-23 | 2016-01-04 |  | Y
Central Hudson |  | SolarCity | CH-06645 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6042 | Spackenkill | N |  | 8.2 | [13 empty] | NM | N | FRONIUS PRIMO 8.2 | 2015-12-04 | 2015-12-09 | 3 | 2015-12-09 | [14 empty] | 2015-12-31 | 2016-01-08 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07243 | Kingston | Kingston | Ulster | 12401 | G | 1021 | East Kingston | N |  | 5 | [13 empty] | NM | N | ABB PVI-5000-OUTD-US-Z-A | 2015-12-04 | 2015-12-11 | 5 | 2015-12-11 | [14 empty] | 2015-12-15 | 2015-12-22 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07269 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6046 | Spackenkill | N |  | 8.2 | [13 empty] | NM | N | FRONIUS PRIMO 8.2 | 2015-12-04 | 2015-12-09 | 3 | 2015-12-09 | [14 empty] | 2015-12-18 | 2015-12-23 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Trinity Solar | CH-08455 | Newburgh | Marlboro | Ulster | 12542 | G | 5004 | Marlboro | N |  | 10 | [13 empty] | NM | N | SOLAR EDGE SE 10000A-US | 2015-12-04 | 2015-12-04 | 0 | 2015-12-04 | [14 empty] | 2016-01-11 | 2016-01-11 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08672 | Kingston | Kingston | Ulster | 12401 | G | 1021 | East Kingston | N |  | 4.95 | [13 empty] | NM | N | 23 ENPHASE M215-60-2LL2XZC | 2015-12-04 | 2015-12-11 | 5 | 2015-12-11 | [14 empty] | 2016-06-15 | 2016-06-17 |  | Y
Central Hudson |  | American Solar Partners | CH-03063 | Newburgh | New Paltz | Ulster | 12561 | G | 5022 | Ohioville | N |  | 5 | [13 empty] | NM | N | SOLAR EDGE SE5000 | 2015-12-07 | 2015-12-07 | 0 | 2015-12-07 | [14 empty] | 2016-02-10 | 2016-02-11 |  | Y
Central Hudson |  | Kirchhoff Green Energy LLC | CH-00260 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6056 | Todd Hill | N |  | 8 | [13 empty] | NM | N | (32) ENPHASE ENERGY M250 | 2015-12-07 | 2015-12-11 | 4 | 2015-12-11 | [14 empty] | 2016-06-06 | 2016-06-13 |  | Y
Central Hudson |  | New York State Solar Farm | CH-03957 | Poughkeepsie | Staatsburg | Dutchess | 12580 | G | 7011 | Hibernia | N |  | 11 | [13 empty] | NM | N | (1) SMA AMERICA SB 5000TL (1) SMA AMERICA SB 6000TL | 2015-12-07 | 2015-12-16 | 7 | 2015-12-16 | [14 empty] | 2016-01-19 | 2016-01-26 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | New York State Solar Farm | CH-03978 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6002 | Reynolds Hill | N |  | 5 | [13 empty] | NM | N | SMA AMERICA SB5000TL | 2015-12-07 | 2015-12-10 | 3 | 2015-12-10 | [14 empty] | 2016-01-27 | 2016-02-03 |  | Y
Central Hudson |  | New York State Solar Farm | CH-04051 | Newburgh | Gardiner | Ulster | 12525 | G | 5031 | Galeville | N |  | 6 | [13 empty] | NM | N | SMA AMERICA SB6000TL | 2015-12-22 | 2016-01-06 | 8 | 2016-01-06 | [14 empty] | 2016-01-06 | 2016-01-08 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | NRG Home Solar | CH-04532 | Kingston | Saugerties | Ulster | 12477 | G | 3004 | Saugerties | N |  | 2.79 | [13 empty] | NM | N | 13 ENPHASE M215 | 2015-12-07 | 2015-12-15 | 6 | 2015-12-15 | [14 empty] | 2016-02-09 | 2016-02-17 |  | Y
Central Hudson |  | American Energy Care | CH-00660 | Catskill | Westerlo | Albany | 12193 | G | 1091 | Westerlo | N |  | 3 | [13 empty] | NM | N | SMA SB3000TL-US-ZZ | 2015-12-07 | 2015-12-16 | 7 | 2015-12-16 | [14 empty] | 2016-02-25 | 2016-03-09 |  | Y
Central Hudson |  | Hudson Solar | CH-02048 | Kingston | Cragsmoor | Ulster | 12420 | G | 3078 | Greenfield Rd | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE-7600A-US-U | 2015-12-07 | 2015-12-16 | 7 | 2015-12-16 | [14 empty] | 2016-02-10 | 2016-02-18 |  | Y
Central Hudson |  | Natural Energy Solutions | CH-02765 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7054 | Rhinebeck | N |  | 15.2 | [13 empty] | NM | N | (2) SOLAREDGE SE7600A US | 2015-12-11 | 2015-12-11 | 0 | 2015-12-11 | [14 empty] | 2016-01-11 | 2016-01-18 |  | Y
Central Hudson |  | Novel Approaches | CH-02780 | Kingston | Napanoch | Ulster | 12458 | G | 3072 | Honk Falls | N |  | 22 | [13 empty] | NM | N | 2 SMA SB11000TL-US | 2015-12-07 | 2015-12-14 | 5 | 2015-12-14 | [14 empty] | 2015-12-28 | 2015-12-31 |  | Y
Central Hudson |  | Novel Approaches | CH-02785 | Kingston | Ellenvl | Ulster | 12428 | G | 3078 | Greenfield Rd | N |  | 18 | [13 empty] | NM | N | 2 SMA SB9000TL-US | 2015-12-07 | 2015-12-14 | 5 | 2015-12-14 | [14 empty] | 2015-12-17 | 2015-12-28 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-04959 | Newburgh | New Paltz | Ulster | 12561 | G | 5021 | Ohioville | N |  | 12 | [13 empty] | NM | N | ABB PVI-6000-OUTD US (2) | 2015-12-07 | 2015-12-07 | 0 | 2015-12-07 | [14 empty] | 2016-04-05 | 2016-04-08 |  | Y
Central Hudson |  | SolarCity | CH-05846 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 6073 | East Park | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000-OUTD-US | 2015-12-07 | 2015-12-09 | 2 | 2015-12-09 | [14 empty] | 2015-12-22 | 2015-12-29 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-05918 | Poughkeepsie | Lagrangevl | Dutchess | 12540 | G | 6055 | Todd Hill | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2015-12-07 | 2015-12-09 | 2 | 2015-12-09 | [14 empty] | 2016-01-05 | 2016-01-12 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06391 | Newburgh | Salisbury Mls | Orange | 12577 | G | 4095 | Bethlehem Rd | N |  | 10 | [13 empty] | NM | N | FRONIUS IG PLUS 10.0 | 2015-12-07 | 2015-12-07 | 0 | 2015-12-07 | [14 empty] | 2016-01-05 | 2016-01-12 |  | Y
Central Hudson |  | SolarCity | CH-07230 | Kingston | Kerhonkson | Ulster | 12446 | G | 3081 | Kerhonkson | N |  | 5 | [13 empty] | NM | N | ABB PVI-5000-OU-TD-US | 2015-12-07 | 2015-12-15 | 6 | 2015-12-15 | [14 empty] | 2015-12-31 | 2016-01-15 |  | Y
Central Hudson |  | Sungevity Inc | CH-09547 | Newburgh | Newburgh | Orange | 12550 | G | 4023 | Coldenham | N |  | 6 | [13 empty] | NM | N | ABB PVI-3.0-OUTD-S-US-A (2) | 2015-12-07 | 2015-12-07 | 0 | 2015-12-07 | [14 empty] | 2016-06-30 | 2016-07-06 |  | Y
Central Hudson |  | Kirchhoff Green Energy LLC | CH-00261 | Poughkeepsie | Wappingrs Fls | Dutchess | 12590 | G | 6052 | Todd Hill | N |  | 11.4 | [13 empty] | NM | N | FRONIUS USA UNI 11.4-1 | 2015-12-08 | 2015-12-14 | 4 | 2015-12-14 | [14 empty] | 2016-06-06 | 2016-06-13 |  | Y
Central Hudson |  | PosiGen Solar | CH-02900 | Newburgh | Wallkill | Ulster | 12589 | G | 5043 | East Walden | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE7600A-US | 2015-12-11 | 2015-12-14 | 1 | 2015-12-14 | [14 empty] | 2016-01-13 | 2016-01-13 |  | Y
Central Hudson |  | SolarCity | CH-07238 | Kingston | Kingston | Ulster | 12401 | G | 2016 | Lincoln Park | N |  | 8.2 | [13 empty] | NM | N | ABB PVI-6000-OUTD-US-Z-A ABB PVI-3.0-OUTD-US-Z-A | 2015-12-08 | 2015-12-16 | 6 | 2015-12-16 | [14 empty] | 2015-12-30 | 2016-01-07 |  | Y
Central Hudson |  | Sungevity Inc | CH-09336 | Newburgh | Highland |  | 12528 | G | 5082 | Highland | TBD |  | 3 | [13 empty] | NM | N | ABB PVI-3.0-OUTD-S-US-A | 2015-12-08 | 2015-12-14 | 4 | 2015-12-14 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | Sungevity Inc | CH-09407 | Kingston | Accord | Ulster | 12404 | G | 3024 | High Falls | N |  | 10 | [13 empty] | NM | N | 2 ABB PVI-5000-OUTD-US-A | 2015-12-08 | 2015-12-16 | 6 | 2015-12-16 | [14 empty] | 2016-04-05 | 2016-04-12 |  | Y
Central Hudson |  | Sungevity Inc | CH-09530 | Poughkeepsie | Staatsburg | Dutchess | 12580 | G | 7041 | Staatsburg | N |  | 7.6 | [13 empty] | NM | N | (2) ABB PVI-3.8-OUTD-S-US-A | 2015-12-08 | 2015-12-11 | 3 | 2015-12-11 | [14 empty] | 2015-12-29 | 2016-01-07 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03123 | Newburgh | New Paltz |  | 12561 | G | 5031 | Galeville | TBD |  | 1980 | [13 empty] | CDG | N | (44) Huawei SUN2000-45KTL-US | 2016-01-14 | 2016-02-04 | 15 | 2016-02-04 | 2016-01-14 | 2016-02-04 | 15 | 2016-03-30 | 2016-05-03 | 2016-07-28 | 60 | 32000 | [9 empty] | W
Central Hudson |  | New York State Solar Farm | CH-03995 | Newburgh | New Paltz | Ulster | 12561 | G | 5024 | Ohioville | N |  | 6 | [13 empty] | NM | N | SMA AMERICA SB6000TL | 2015-12-09 | 2015-12-09 | 0 | 2015-12-09 | [14 empty] | 2016-01-19 | 2016-01-20 |  | Y
Central Hudson |  | SolarCity | CH-07714 | Fishkill | Garrison | Putnam | 10524 | G | 8066 | Merritt Park | N |  | 8 | [13 empty] | NM | N | ABB PVI-5000-OUTD-US ABB PVI-3.0-OUTD-S-US | 2015-12-09 | 2015-12-09 | 0 | 2015-12-09 | [14 empty] | 2016-01-06 | 2016-01-13 |  | Y
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03124 | Kingston | Saugerties |  | 12477 | G | 3002 | Saugerties | TBD |  | 1980 | [13 empty] | CDG | N | (44) Huawei SUN2000-45KTL-US | 2016-01-07 | 2016-01-28 | 15 | 2016-01-28 | 2016-01-07 | 2016-01-28 | 15 | 2016-03-18 | 2016-05-03 | 2016-07-28 | 60 | 15000 | [9 empty] | W |  | CESIR for 3 projects combined with an aggregate CESIR Cost to Customer of $45,000 & Total Estimated Upgrade Costs of $5,398,663. 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Apex Solar Power | CH-00712 | Kingston | Woodstock |  | 12498 | G | 3013 | Woodstock | TBD |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A-US | 2015-12-10 | 2015-12-28 | 10 | 2015-12-28 | [17 empty] | W
Central Hudson |  | Monolith Solar Associates LLC | CH-02687 | Catskill | Ravena | Albany | 12143 | G | 1081 | New Baltimore | N |  | 7.6 | [13 empty] | NM | N | SOLAR EDGE SE7600A-US | 2015-12-17 | 2015-12-28 | 5 | 2015-12-28 | [14 empty] | 2016-02-02 | 2016-02-09 |  | Y
Central Hudson |  | Ross Solar Group | CH-02994 | Newburgh | Cornwall-Hdsn | Orange | 12520 | G | 4043 | Union Ave | N |  | 11 | [13 empty] | NM | N | SMA SB5000TL SMA SB67000TL | 2015-12-10 | 2015-12-17 | 5 | 2015-12-17 | [14 empty] | 2016-03-15 | 2016-03-22 |  | Y
Central Hudson |  | Trinity Solar | CH-08530 | Kingston | Woodstock | Ulster | 12498 | G | 3012 | Woodstock | N |  | 6 | [13 empty] | NM | N | SOLAR EDGE SE6000A-US | 2015-12-10 | 2015-12-17 | 5 | 2015-12-17 | [14 empty] | 2016-03-18 | 2016-03-28 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08648 | Catskill | Greenvl | Greene | 12083 | G | 1091 | Westerlo | N |  | 7.31 | [13 empty] | NM | N | 34 ENPHASE M215 602LLS2XZC | 2015-12-10 | 2015-12-17 | 5 | 2015-12-17 | [14 empty] | 2016-06-16 | 2016-06-20 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08650 | Catskill | Catskill | Greene | 12414 | G | 2003 | North Catskill | N |  | 3.01 | [13 empty] | NM | N | 14 ENPHASE M215-602LLS2XZC | 2015-12-10 | 2015-12-17 | 5 | 2015-12-17 | [14 empty] | 2016-06-08 | 2016-06-13 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08684 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7051 | Rhinebeck | N |  | 8.6 | [13 empty] | NM | N | (40) ENPHASE M215 602LLS2XZC | 2015-12-10 | 2015-12-16 | 4 | 2015-12-16 | [14 empty] | 2016-06-09 | 2016-06-16 |  | Y
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03125 | Newburgh | Montgomery |  | 12549 | G | 4021 | Coldenham | TBD |  | 2000 | [13 empty] | CDG | N | (2) SUNGROW SG 1000MX | 2016-01-07 | 2016-01-28 | 15 | 2016-01-28 | 2016-01-07 | 2016-01-28 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | CESIR determined necessary during preliminary review Section C, Step 4.
Central Hudson |  | Joule, LLC | CH-03126 | Newburgh | Walden | Orange | 12586 | G | 5041 | East Walden | N |  | 2000 | [13 empty] | CDG | N | Sungrow Power Supply SG3150UD-MV-US (600V) [SI1] (44) Huawei SUN2000-45KTL-US | 2016-01-14 | 2016-02-04 | 15 | 2016-02-04 | 2016-01-14 | 2016-02-04 | 15 | 2016-03-30 | 2016-05-03 | 2016-07-28 | 60 | 32000 | 442500 |  | 2017-06-23 | 2017-08-21 | 2017-08-21 | 2025-11-20 |  |  |  | N
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03127 | Kingston | Saugerties |  | 12477 | G | 3002 | Saugerties | TBD |  | 1980 | [13 empty] | CDG | N | (44) Huawei SUN2000-45KTL-US | 2016-01-07 | 2016-01-28 | 15 | 2016-01-28 | 2016-01-07 | 2016-01-28 | 15 | 2016-03-18 | 2016-05-03 | 2016-07-28 | 60 | 15000 | [9 empty] | W |  | CESIR for 3 projects combined with an aggregate CESIR Cost to Customer of $45,000 & Total Estimated Upgrade Costs of $5,398,663. 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Infinity Solar Systems | CH-03460 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8051 | North Chelsea | N |  | 7.7 | [13 empty] | NM | N | SMA AMERICA SB7700TL-US-22 | 2015-12-14 | 2015-12-30 | 10 | 2015-12-30 | [14 empty] | 2016-01-28 | 2016-01-29 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03641 | Newburgh | Milton |  | 12547 | G | 5003 | Marlboro | N | CH-03641 | 7.6 | [13 empty] | NM | N | SOLAREDGE 7600 A-US | 2015-12-14 | 2015-12-17 | 3 | 2015-12-17 | [14 empty] | 2015-12-17 | 2015-12-17 |  | W |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | New York State Solar Farm | CH-03976 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6042 | Spackenkill | N |  | 3.8 | [13 empty] | NM | N | SMA AMERICA SB3800TL | 2015-12-14 | 2015-12-29 | 9 | 2015-12-29 | [14 empty] | 2016-03-04 | 2016-03-11 |  | Y
Central Hudson |  | New York State Solar Farm | CH-04060 | Poughkeepsie | Staatsburg | Dutchess | 12580 | G | 7011 | Hibernia | N |  | 9 | [13 empty] | NM | N | (1) SMA AMERICA SB3000TL (1) SMA AMERICA SB6000TL | 2015-12-17 | 2016-01-05 | 10 | 2016-01-05 | [14 empty] | 2016-03-14 | 2016-03-21 |  | Y
Central Hudson |  | NRG Home Solar | CH-04167 | Kingston | Lk Katrine | Ulster | 12449 | G | 2016 | Lincoln Park | N |  | 4 | [13 empty] | NM | N | 16 ENPHASE M250 | 2015-12-14 | 2015-12-30 | 10 | 2015-12-30 | [14 empty] | 2016-02-17 | 2016-02-24 |  | Y
Central Hudson |  | NRG Home Solar | CH-04455 | Newburgh | Newburgh | Orange | 12550 | G | 4024 | Coldenham | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE 7600 | 2015-12-14 | 2015-12-30 | 10 | 2015-12-30 | [14 empty] | 2016-01-19 | 2016-01-26 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | NRG Home Solar | CH-04685 | Catskill | Catskill | Greene | 12414 | G | 2004 | North Catskill | N |  | 2.58 | [13 empty] | NM | N | 12 ENPHASE M215 | 2015-12-14 | 2015-12-30 | 10 | 2015-12-30 | [14 empty] | 2016-02-17 | 2016-02-24 |  | Y
Central Hudson |  | Hudson Solar | CH-01921 | Fishkill | Fishkill |  | 12524 | G | 8014 | Forgebrook | TBD |  | 6 | [13 empty] | NM | N | SOLAREDGE SE-6000 A-US-U | 2015-12-15 | 2015-12-31 | 10 | 2015-12-31 | [17 empty] | W
Central Hudson |  | Hudson Solar | CH-02334 | Kingston | Stone Ridge | Ulster | 12484 | G | 3023 | High Falls | N |  | 13.6 | [13 empty] | NM | N | SOLAREDGE SE-7600A-US-U SOLAREDGE SE-6000A-US-U | 2015-12-14 | 2015-12-30 | 10 | 2015-12-30 | [8 empty] | 350 | 350 |  | 2016-01-28 | 2016-01-28 | 2016-05-09 | 2016-05-13 | 2016-05-20 |  | Y
Central Hudson |  | Hudson Solar | CH-02371 | Poughkeepsie | Stanfordvl | Dutchess | 12581 | G | 7072 | Stanfordville | N |  | 3 | [13 empty] | NM | N | SOLAREDGE SE-3000A-US-U | 2015-12-14 | 2015-12-17 | 3 | 2015-12-17 | [14 empty] | 2016-01-14 | 2016-01-21 |  | Y
Central Hudson |  | SolarCity | CH-04944 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 6051 | Todd Hill | N |  | 4.2 | [13 empty] | NM | N | ABB PVI-4.2-OUTD-S US | 2015-12-14 | 2015-12-29 | 9 | 2015-12-29 | [14 empty] | 2016-01-12 | 2016-01-12 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-04968 | Newburgh | New Paltz | Ulster | 12561 | G | 5022 | Ohioville | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000-OUTD US | 2015-12-14 | 2015-12-30 | 10 | 2015-12-30 | [14 empty] | 2016-03-31 | 2016-04-07 |  | Y
Central Hudson |  | SolarCity | CH-05362 | Newburgh | Wallkill | Ulster | 12589 | G | 5011 | Modena | N |  | 9.6 | [13 empty] | NM | N | ABB PVI-6000-OUTD US ABB PVI-3.6-OUTD-S US | 2015-12-14 | 2015-12-30 | 10 | 2015-12-30 | [14 empty] | 2016-01-05 | 2016-01-12 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-05979 | Newburgh | Highland | Ulster | 12528 | G | 5081 | Highland | N |  | 3.6 | [13 empty] | NM | N | ABB PVI-3.6-OUTD-S US | 2015-12-14 | 2015-12-29 | 9 | 2015-12-29 | [14 empty] | 2016-01-04 | 2016-01-11 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06326 | Newburgh | Marlboro | Ulster | 12542 | G | 5001 | Marlboro | N |  | 9.2 | [13 empty] | NM | N | ABB PVI-4.2-OUTD-S-US-Z- ABB PVI-5000-OUTD-US-Z-A | 2015-12-14 | 2015-12-30 | 10 | 2015-12-30 | [14 empty] | 2016-01-12 | 2016-01-18 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06428 | Newburgh | Maybrook | Orange | 12543 | G | 4026 | Coldenham | N |  | 3 | [13 empty] | NM | N | ABB PVI-3.0-OUTD-S-US | 2015-12-14 | 2015-12-14 | 0 | 2015-12-14 | [14 empty] | 2015-12-31 | 2016-01-07 |  | Y
Central Hudson |  | SolarCity | CH-06465 | Catskill | Athens | Greene | 12015 | G | 1074 | Coxsackie | N |  | 9 | [13 empty] | NM | N | ABB PVI-6000-OUTD-US-Z-A ABB PVI-3.0-OUTD-US-Z-A | 2015-12-14 | 2016-01-13 | 19 | 2016-01-13 | [14 empty] | 2016-01-18 | 2016-01-25 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06493 | Kingston | Kingston | Ulster | 12401 | G | 2093 | Hurley Ave | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2015-12-14 | 2015-12-28 | 8 | 2015-12-28 | [14 empty] | 2016-01-11 | 2016-01-15 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07045 | Newburgh | New Windsor | Orange | 12553 | G | 4042 | Union Ave | N |  | 6 | [13 empty] | NM | N | ABB PVI-3.0-OUTD-S US (2) | 2015-12-14 | 2015-12-30 | 10 | 2015-12-30 | [14 empty] | 2016-01-12 | 2016-01-13 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07111 | Newburgh | Cornwall |  | 12518 | G | 4093 | Bethlehem Rd | TBD |  | 6.6 | [13 empty] | NM | N | ABB PVI-3.0-OUTD-S-US ABB PVI-3.6-OUTD-S-US | 2015-12-14 | 2015-12-30 | 10 | 2015-12-30 | [17 empty] | W |  | Customer already had net meter prior to application. 12/24/15 &12/25/15 Company Holiday.
Central Hudson |  | SolarCity | CH-07488 | Catskill | Catskill | Greene | 12414 | G | 2006 | North Catskill | N |  | 9.6 | [13 empty] | NM | N | ABB PVI-6000-OUTD-US ABB PVI-3.6-OUTD-US | 2015-12-14 | 2015-12-28 | 8 | 2015-12-28 | [8 empty] | 350 | 350 |  | 2016-01-21 | 2016-01-21 | 2016-01-27 | 2016-01-27 | 2016-02-09 |  | Y
Central Hudson |  | Trinity Solar | CH-08364 | Newburgh | Marlboro | Ulster | 12542 | G | 5004 | Marlboro | N |  | 5 | [13 empty] | NM | N | SOLAR EDGE SE5000A-US | 2015-12-14 | 2015-12-30 | 10 | 2015-12-30 | [14 empty] | 2016-04-28 | 2016-04-29 |  | Y
Central Hudson |  | Trinity Solar | CH-08384 | Catskill | Purling |  | 12470 | G | 2042 | South Cairo | TBD |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A-US | 2015-12-14 | 2015-12-30 | 10 | 2015-12-30 | [17 empty] | W |  | 12/24 & 12/25/2015 Company Holiday.
Central Hudson |  | Trinity Solar | CH-08488 | Poughkeepsie | Pleasant Vly |  | 12569 | G | 6057 | Todd Hill | TBD |  | 11.4 | [13 empty] | NM | N | SolarEdge SE11400A-US | 2015-12-14 | 2015-12-17 | 3 | 2015-12-17 | [17 empty] | W
Central Hudson |  | Trinity Solar | CH-08580 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 6 | [13 empty] | NM | N | SOLAR EDGE SE6000A-US | 2015-12-14 | 2015-12-30 | 10 | 2015-12-30 | [14 empty] | 2016-03-18 | 2016-03-18 |  | Y
Central Hudson |  | Trinity Solar | CH-08586 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6063 | Inwood Ave | N |  | 7.6 | [13 empty] | NM | N | SolarEdge SE7600A-US | 2015-12-18 | 2016-01-06 | 10 | 2016-01-06 | [14 empty] | 2016-02-05 | 2016-02-12 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-03405 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6052 | Todd Hill | N |  | 10 | [13 empty] | NM | N | (2) SMA AMERICA SB5000TL-US-22 | 2015-12-22 | 2015-12-22 | 0 | 2015-12-22 | [14 empty] | 2016-03-08 | 2016-03-15 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03661 | Kingston | High Fls | Ulster | 12440 | G | 3024 | High Falls | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE 7600 A-US | 2015-12-15 | 2015-12-31 | 10 | 2015-12-31 | [14 empty] | 2016-03-24 | 2016-04-01 |  | Y
Central Hudson |  | Lotus Energy Inc. | CH-03876 | Kingston | Woodstock | Ulster | 12498 | G | 3012 | Woodstock | N |  | 5 | [13 empty] | NM | N | SMA SB5000 TL-US-22 | 2015-12-15 | 2015-12-31 | 10 | 2015-12-31 | [14 empty] | 2016-01-20 | 2016-01-27 |  | Y
Central Hudson |  | NRG Home Solar | CH-04123 | Poughkeepsie | Pine Plns | Dutchess | 12567 | G | 7091 | Pulvers Corners | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE7600 | 2015-12-15 | 2015-12-29 | 8 | 2015-12-29 | [14 empty] | 2016-02-17 | 2016-02-24 |  | Y
Central Hudson |  | NRG Home Solar | CH-04244 | Catskill | Catskill | Greene | 12414 | G | 2003 | North Catskill | N |  | 4.3 | [13 empty] | NM | N | 20 ENPHASE M215 | 2015-12-15 | 2015-12-31 | 10 | 2015-12-31 | [14 empty] | 2016-02-01 | 2016-02-08 |  | Y
Central Hudson |  | NRG Home Solar | CH-04256 | Kingston | Kerhonkson | Ulster | 12446 | G | 3081 | Kerhonkson | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE 7600 | 2015-12-15 | 2015-12-31 | 10 | 2015-12-31 | [14 empty] | 2016-03-30 | 2016-04-06 |  | Y
Central Hudson |  | NRG Home Solar | CH-04315 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6002 | Reynolds Hill | N |  | 6 | [13 empty] | NM | N | SolarEdge SE6000A | 2015-12-23 | 2016-01-11 | 10 | 2016-01-11 | [14 empty] | 2016-07-29 | 2016-08-01 |  | Y
Central Hudson |  | NRG Home Solar | CH-04398 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8092 | Fishkill Plains | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE 7600 | 2015-12-23 | 2016-01-20 | 17 | 2016-01-20 | [14 empty] | 2016-02-24 | 2016-02-29 |  | Y
Central Hudson |  | NRG Home Solar | CH-04499 | Newburgh | Cornwall |  | 12518 | G | 4041 | Union Ave | TBD |  | 4.3 | [13 empty] | NM | N | ENPHASE M215 (20) | 2015-12-23 | 2016-01-07 | 8 | 2016-01-07 | [17 empty] | W |  | Customer already had net meter prior to application. 12/24/15, 12/25/15 & 1/1/16 Company Holidays.
Central Hudson |  | NRG Home Solar | CH-04529 | Kingston | Napanoch | Ulster | 12458 | G | 3071 | Honk Falls | N |  | 5.5 | [13 empty] | NM | N | 22 ENPHASE M250 | 2015-12-15 | 2015-12-30 | 9 | 2015-12-30 | [14 empty] | 2016-03-28 | 2016-04-04 |  | Y
Central Hudson |  | NRG Home Solar | CH-04646 | Newburgh | New Windsor | Orange | 12553 | G | 4046 | Union Ave | N |  | 4.73 | [13 empty] | NM | N | 22 ENPHASE M215 | 2015-12-15 | 2015-12-31 | 10 | 2015-12-31 | [14 empty] | 2016-02-01 | 2016-02-01 |  | Y
Central Hudson |  | NRG Home Solar | CH-04743 | Newburgh | Newburgh |  | 12550 | G | 4047 | Union Ave | TBD |  | 2.58 | [13 empty] | NM | N | ENPHASE M215 (12) | 2015-12-23 | 2016-01-07 | 8 | 2016-01-07 | [17 empty] | W |  | Customer already had net meter prior to application. 12/24/15, 12/25/15 & 1/1/16 Company Holidays.
Central Hudson |  | NRG Home Solar | CH-04800 | Fishkill | Beacon | Dutchess | 12508 | G | 8017 | Forgebrook | N |  | 3.87 | [13 empty] | NM | N | 18 ENPHASE M215 | 2015-12-15 | 2015-12-31 | 10 | 2015-12-31 | [14 empty] | 2016-05-17 | 2016-05-24 |  | Y
Central Hudson |  | BQ Energy, LLC | CH-00756 | Kingston | Kingston |  | 12401 | G | 2091 | Hurley Ave | TBD |  | 2000 | [13 empty] | CDG | Y | (80) Schneider Electric Conext CL2500NA | 2016-02-02 | 2016-02-24 | 15 | 2016-02-24 | 2016-02-02 | 2016-02-24 | 15 | 2017-03-03 | 2017-04-03 | 2017-06-28 | 60 | 10477.22 | 2008110 | [7 empty] | 2018-05-24 | W |  | CESIR for 2 projects combined with an aggregate CESIR Cost to Customer of $40,000.
Central Hudson |  | BQ Energy, LLC | CH-00757 | Kingston | Kingston |  | 12401 | G | 2091 | Hurley Ave | TBD |  | 2000 | [13 empty] | CDG | Y | (80) Schneider Electric Conext CL2500NA | 2016-02-02 | 2016-02-24 | 15 | 2016-02-24 | 2016-02-02 | 2016-02-24 | 15 | 2017-03-03 | 2017-04-03 | 2017-06-28 | 60 | 10477.22 | 2008110 | [7 empty] | 2018-05-24 | W |  | CESIR for 2 projects combined with an aggregate CESIR Cost to Customer of $40,000.
Central Hudson |  | SolarCity | CH-05050 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8093 | Fishkill Plains | N |  | 7.2 | [13 empty] | NM | N | ABB-PVI 3.6 OUTD-US-Z (2) | 2015-12-15 | 2015-12-31 | 10 | 2015-12-31 | [14 empty] | 2016-01-14 | 2016-01-14 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-05366 | Kingston | Accord | Ulster | 12404 | G | 3083 | Kerhonkson | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2015-12-15 | 2015-12-31 | 10 | 2015-12-31 | [14 empty] | 2016-02-02 | 2016-02-09 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-05498 | Catskill | Hunter | Greene | 12442 | E | 2389 | Vinegar Hill | N |  | 6 | [13 empty] | NM | N | ABB PVI 4.2 OUTD -SZ-A | 2015-12-15 | 2015-12-31 | 10 | 2015-12-31 | [14 empty] | 2016-02-17 | 2016-02-24 |  | Y
Central Hudson |  | SolarCity | CH-05574 | Catskill | Coxsackie | Greene | 12051 | G | 1074 | Coxsackie | N |  | 5 | [13 empty] | NM | N | ABB PVI-5000-OUTD US | 2015-12-15 | 2015-12-31 | 10 | 2015-12-31 | [14 empty] | 2016-01-14 | 2016-01-21 |  | Y
Central Hudson |  | SolarCity | CH-05691 | Kingston | Kingston | Ulster | 12401 | G | 1011 | Boulevard | N |  | 16.4 | [13 empty] | NM | N | 2 FRONIUS PRIMO 8.2 | 2015-12-15 | 2015-12-31 | 10 | 2015-12-31 | [14 empty] | 2016-02-17 | 2016-02-24 |  | Y
Central Hudson |  | SolarCity | CH-06014 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8091 | Fishkill Plains | N |  | 12 | [13 empty] | NM | N | ABB-PVI 6000 OUTD-US-Z (2) | 2015-12-15 | 2015-12-31 | 10 | 2015-12-31 | [14 empty] | 2016-01-12 | 2016-01-18 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06355 | Newburgh | Modena | Ulster | 12548 | G | 5013 | Modena | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000 OUTD-US | 2015-12-30 | 2016-01-07 | 5 | 2016-01-07 | [14 empty] | 2016-01-11 | 2016-01-13 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07092 | Newburgh | Modena | Ulster | 12548 | G | 5013 | Modena | N |  | 4.2 | [13 empty] | NM | N | ABB PVI-4.2-OUTD-S US | 2015-12-15 | 2015-12-31 | 10 | 2015-12-31 | [14 empty] | 2016-01-18 | 2016-01-25 |  | Y
Central Hudson |  | SolarCity | CH-07297 | Poughkeepsie | Lagrangevl | Dutchess | 12540 | G | 6053 | Todd Hill | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2015-12-28 | 2016-01-07 | 7 | 2016-01-07 | [14 empty] | 2016-01-13 | 2016-01-20 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Solar Alchemy | CH-08997 | Kingston | Kerhonkson | Ulster | 12446 | G | 3082 | Kerhonkson | Y |  | 4.5 | 4.5 | [12 empty] | NM | N | SCHNEIDER XW 45481XantrexXW4548 (DC) | 2015-12-15 | 2015-12-30 | 9 | 2015-12-30 | [14 empty] | 2015-12-30 | 2015-12-31 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-03493 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8023 | Knapps Corners | N |  | 6 | [13 empty] | NM | N | SMA AMERICA SB6000TL-US-22 | 2015-12-16 | 2016-01-04 | 10 | 2016-01-04 | [14 empty] | 2016-03-15 | 2016-03-22 |  | Y
Central Hudson |  | SolarCity | CH-04954 | Poughkeepsie | Clinton Corners | Dutchess | 12514 | G | 7013 | Hibernia | N |  | 9 | [13 empty] | NM | N | (1) ABB PVI-6000-OUTD-US-Z-A (1) ABB PVI-3.0-OUTD-US-Z-A | 2016-02-11 | 2016-02-19 | 5 | 2016-02-19 | [14 empty] | 2016-03-14 | 2016-03-21 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-05173 | Kingston | Kerhonkson | Ulster | 12446 | G | 3082 | Kerhonkson | N |  | 4.2 | [13 empty] | NM | N | ABB PVI-4.2 OUTD-US-Z | 2015-12-16 | 2016-01-04 | 10 | 2016-01-04 | [14 empty] | 2016-02-11 | 2016-02-19 |  | Y
Central Hudson |  | SolarCity | CH-05200 | Newburgh | Rock Tvrn | Orange | 12575 | G | 4097 | Bethlehem Rd | N |  | 6 | [13 empty] | NM | N | ABB PVI 6000 | 2016-01-07 | 2016-01-21 | 10 | 2016-01-21 | [14 empty] | 2016-01-26 | 2016-01-29 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-05209 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7055 | Rhinebeck | N |  | 3.8 | [13 empty] | NM | N | SolarEdge SE3800A-US-ZB-U | 2016-02-08 | 2016-02-23 | 10 | 2016-02-23 | [14 empty] | 2016-03-08 | 2016-03-11 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-05252 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6066 | Inwood Ave | N |  | 6.6 | [13 empty] | NM | N | (1) ABB PVI-3.6 OUTD-S-US (1) ABB PVI-3.0 OUTD-S-US | 2015-12-16 | 2016-01-04 | 10 | 2016-01-04 | [14 empty] | 2016-01-19 | 2016-01-26 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-05350 | Newburgh | Campbell Hall | Orange | 10916 | G | 5051 | Maybrook | N |  | 15.2 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 (2) | 2016-01-07 | 2016-01-21 | 10 | 2016-01-21 | [8 empty] | 350 | 350 |  | 2016-02-04 | 2016-02-04 | 2016-02-10 | 2016-02-11 | 2016-03-08 |  | Y
Central Hudson |  | SolarCity | CH-05442 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6052 | Todd Hill | N |  | 3.6 | [13 empty] | NM | N | ABB PVI-3.6-OUTD-S-US-Z | 2016-02-12 | 2016-02-29 | 10 | 2016-02-29 | [14 empty] | 2016-06-20 | 2016-06-27 |  | Y
Central Hudson |  | SolarCity | CH-05461 | Newburgh | Montgomery | Orange | 12549 | G | 5042 | East Walden | N |  | 10 | [13 empty] | NM | N | ABB PVI-5000 OUTD-US-Z (2) | 2016-01-11 | 2016-01-22 | 9 | 2016-01-22 | [14 empty] | 2016-02-11 | 2016-02-19 |  | Y
Central Hudson |  | SolarCity | CH-05521 | Catskill | Cairo | Greene | 12413 | G | 2043 | South Cairo | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000 US-ZB-U | 2015-12-16 | 2016-01-04 | 10 | 2016-01-04 | [14 empty] | 2016-01-04 | 2016-01-11 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-05523 | Catskill | Durham | Greene | 12422 | G | 1092 | Westerlo | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2015-12-16 | 2016-01-04 | 10 | 2016-01-04 | [14 empty] | 2016-01-06 | 2016-01-13 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-05660 | Kingston | Kingston | Ulster | 12401 | G | 1022 | East Kingston | N |  | 4.2 | [13 empty] | NM | N | ABB PVI-4.2OUTD-S-US | 2015-12-28 | 2016-01-12 | 10 | 2016-01-12 | [14 empty] | 2016-04-12 | 2016-04-15 |  | Y
Central Hudson |  | SolarCity | CH-05831 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6065 | Inwood Ave | N |  | 3 | [13 empty] | NM | N | ABB PVI-3.0 OUTD-US-Z | 2015-12-16 | 2016-01-04 | 10 | 2016-01-04 | [14 empty] | 2016-03-09 | 2016-03-16 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-05859 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 6074 | East Park | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2015-12-16 | 2016-01-04 | 10 | 2016-01-04 | [14 empty] | 2016-01-06 | 2016-01-13 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-05861 | Poughkeepsie | Salt Pt | Dutchess | 12578 | G | 7011 | Hibernia | N |  | 3.6 | [13 empty] | NM | N | ABB PVI-3.6 OUTD-US-Z | 2015-12-16 | 2016-01-04 | 10 | 2016-01-04 | [14 empty] | 2016-01-06 | 2016-01-13 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06148 | Fishkill | Beacon | Dutchess | 12508 | G | 8085 | Tioronda | N |  | 8.2 | [13 empty] | NM | N | FRONIUS PRIMO 8.2 | 2016-01-07 | 2016-01-21 | 10 | 2016-01-21 | [14 empty] | 2016-01-26 | 2016-01-28 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06173 | Newburgh | Highland | Ulster | 12528 | G | 5022 | Ohioville | N |  | 3 | [13 empty] | NM | N | ABB PVI 3.0 | 2016-01-14 | 2016-01-18 | 2 | 2016-01-18 | [14 empty] | 2016-01-20 | 2016-01-26 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06223 | Newburgh | Newburgh | Orange | 12550 | G | 4024 | Coldenham | N |  | 7.2 | [13 empty] | NM | N | ABB PVI-4.2-OUTD-S-US-Z- ABB PVI-3.0-OUTD-S-US-Z- | 2015-12-23 | 2016-01-07 | 8 | 2016-01-07 | [14 empty] | 2016-01-11 | 2016-01-15 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06274 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 5 | [13 empty] | NM | N | ABB PVI-5000 OUTD-US-Z | 2015-12-28 | 2016-01-07 | 7 | 2016-01-07 | [14 empty] | 2016-01-11 | 2016-01-15 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06358 | Newburgh | Wallkill | Ulster | 12589 | G | 5013 | Modena | N |  | 9.6 | [13 empty] | NM | N | ABB PVI-6000 OUTD-S-US ABB PVI-3.6 OUTD-S-US | 2015-12-30 | 2016-01-07 | 5 | 2016-01-07 | [14 empty] | 2016-03-22 | 2016-03-30 |  | Y
Central Hudson |  | SolarCity | CH-06378 | Newburgh | New Windsor | Orange | 12553 | G | 4095 | Bethlehem Rd | N |  | 15 | [13 empty] | NM | N | ABB PVI-6000 OUTD-S-US (2) ABB PVI-3.0 OUTD-S-US (1) | 2015-12-30 | 2016-01-07 | 5 | 2016-01-07 | [14 empty] | 2016-01-19 | 2016-01-20 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06423 | Newburgh | Maybrook | Orange | 12543 | G | 4026 | Coldenham | N |  | 3 | [13 empty] | NM | N | ABB PVI-3.0 OUTD-S-US | 2015-12-30 | 2016-01-07 | 5 | 2016-01-07 | [14 empty] | 2016-02-01 | 2016-02-01 |  | Y
Central Hudson |  | SolarCity | CH-06639 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6042 | Spackenkill | N | CH-06639 | 6 | [13 empty] | NM | N | (2) ABB PVI-3.0-OUTD-S-US-Z-A | 2016-02-09 | 2016-02-17 | 5 | 2016-02-17 | [14 empty] | 2016-03-02 | 2016-03-03 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06664 | Poughkeepsie | Hyde Park | Dutchess | 12538 | G | 6068 | Inwood Ave | N |  | 7.8 | [13 empty] | NM | N | (1) ABB PVI-4.2 OUTD-US-Z (1) ABB PVI-3.6 OUTD-S-US | 2015-12-16 | 2016-01-04 | 10 | 2016-01-04 | [14 empty] | 2016-02-29 | 2016-03-07 |  | Y
Central Hudson |  | SolarCity | CH-06681 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 6073 | East Park | N |  | 10 | [13 empty] | NM | N | (2) ABB PVI-5000-OUTD-US-Z-A | 2016-02-08 | 2016-02-23 | 10 | 2016-02-23 | [14 empty] | 2016-03-08 | 2016-03-15 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06755 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7056 | Rhinebeck | N |  | 9 | [13 empty] | NM | N | (1) ABB PVI-3.0 OUTD-S-US (1) ABB PVI-6000 OUTD-S-US | 2015-12-30 | 2016-01-07 | 5 | 2016-01-07 | [14 empty] | 2016-01-26 | 2016-02-02 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06763 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7053 | Rhinebeck | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000-OUTD-US-Z-A | 2016-02-12 | 2016-02-29 | 10 | 2016-02-29 | [14 empty] | 2016-03-23 | 2016-04-01 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06815 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8045 | Myers Corners | N |  | 4.2 | [13 empty] | NM | N | ABB PVI-4.2 OUTD-S-US | 2015-12-30 | 2016-01-07 | 5 | 2016-01-07 | [14 empty] | 2016-01-11 | 2016-01-13 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06923 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8055 | North Chelsea | N |  | 11.4 | [13 empty] | NM | N | SOLAREDGE SE11400A-US | 2016-01-28 | 2016-01-29 | 1 | 2016-01-29 | [14 empty] | 2016-02-04 | 2016-02-04 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06994 | Newburgh | Newburgh | Orange | 12550 | G | 4024 | Coldenham | N |  | 3 | [13 empty] | NM | N | ABB PVI-3.0 OUTD-S-US | 2015-12-16 | 2016-01-04 | 10 | 2016-01-04 | [14 empty] | 2016-01-13 | 2016-01-14 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07084 | Newburgh | Wallkill | Ulster | 12589 | G | 5043 | East Walden | N |  | 16.4 | [13 empty] | NM | N | FRONIUS PRIMO 8.2 (2) | 2015-12-30 | 2016-01-07 | 5 | 2016-01-07 | [14 empty] | 2016-04-07 | 2016-04-11 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07100 | Newburgh | Wallkill | Ulster | 12589 | G | 5042 | East Walden | N |  | 7.2 | [13 empty] | NM | N | ABB PVI-3.6 (2) | 2016-02-08 | 2016-02-08 | 0 | 2016-02-08 | [14 empty] | 2016-02-11 | 2016-02-19 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07102 | Newburgh | Wallkill | Ulster | 12589 | G | 5011 | Modena | N |  | 3.6 | [13 empty] | NM | N | ABB PV 3.6 | 2016-01-27 | 2016-01-29 | 2 | 2016-01-29 | [14 empty] | 2016-02-12 | 2016-02-22 |  | Y
Central Hudson |  | SolarCity | CH-07107 | Newburgh | Cornwall | Orange | 12518 | G | 4093 | Bethlehem Rd | N |  | 12 | [13 empty] | NM | N | ABB PVI-6000 OUTD-US-Z (2) | 2015-12-30 | 2016-01-07 | 5 | 2016-01-07 | [14 empty] | 2016-01-21 | 2016-01-21 |  | Y
Central Hudson |  | SolarCity | CH-07137 | Newburgh | Washingtonvl | Orange | 10992 | G | 4097 | Bethlehem Rd | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2016-01-27 | 2016-01-29 | 2 | 2016-01-29 | [14 empty] | 2016-02-25 | 2016-02-29 |  | Y
Central Hudson |  | SolarCity | CH-07144 | Newburgh | Montgomery | Orange | 12549 | G | 5073 | Montgomery | N |  | 5 | [13 empty] | NM | N | ABB PVI-5000 | 2015-12-16 | 2016-01-04 | 10 | 2016-01-04 | [14 empty] | 2016-02-23 | 2016-02-29 |  | Y
Central Hudson |  | SolarCity | CH-07235 | Kingston | Saugerties | Ulster | 12477 | G | 3001 | Saugerties | N | CH-07235 | 4.2 | [13 empty] | NM | N | ABB PVI-4.2 OUTD-US-Z | 2015-12-16 | 2016-01-04 | 10 | 2016-01-04 | [14 empty] | 2016-02-09 | 2016-02-16 |  | Y
Central Hudson |  | SolarCity | CH-07323 | Poughkeepsie | Millerton | Dutchess | 12546 | G | 7081 | Millerton | N |  | 3.8 | [13 empty] | NM | N | SolarEdge SE3800A-US | 2016-03-15 | 2016-03-22 | 5 | 2016-03-22 | [14 empty] | 2016-04-05 | 2016-04-06 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07444 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 3 | [13 empty] | NM | N | ABB PVI-3.0 OUTD-US-Z | 2015-12-16 | 2016-01-04 | 10 | 2016-01-04 | [14 empty] | 2016-01-11 | 2016-01-13 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07560 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8091 | Fishkill Plains | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2015-12-23 | 2016-01-07 | 8 | 2016-01-07 | [14 empty] | 2016-01-11 | 2016-01-13 |  | Y
Central Hudson |  | SolarCity | CH-07634 | Kingston | Port Ewen | Ulster | 12466 | G | 1024 | East Kingston | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000OUTD-US-Z | 2015-12-28 | 2016-01-12 | 10 | 2016-01-12 | [14 empty] | 2016-02-11 | 2016-02-19 |  | Y
Central Hudson |  | SolarCity | CH-07678 | Newburgh | Newburgh | Orange | 12550 | G | 4051 | Union Ave | N |  | 6 | [13 empty] | NM | N | ABB PVI 6000 | 2016-01-20 | 2016-01-29 | 7 | 2016-01-29 | [14 empty] | 2016-02-09 | 2016-02-10 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07703 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6002 | Reynolds Hill | N |  | 3 | [13 empty] | NM | N | ABB PVI-3.0 OUTD-US-Z | 2015-12-16 | 2016-01-04 | 10 | 2016-01-04 | [14 empty] | 2016-01-13 | 2016-01-21 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07710 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8051 | North Chelsea | N |  | 12 | [13 empty] | NM | N | ABB PVI 6.0 (2) | 2015-12-22 | 2016-01-06 | 8 | 2016-01-06 | [14 empty] | 2016-01-19 | 2016-01-20 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07739 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8046 | Myers Corners | N |  | 3 | [13 empty] | NM | N | ABB PVI-3.0 OUTD-US-Z | 2015-12-28 | 2016-01-07 | 7 | 2016-01-07 | [14 empty] | 2016-01-11 | 2016-01-15 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Trinity Solar | CH-08528 | Kingston | Ulster Pk | Ulster | 12487 | G | 1014 | Boulevard | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE7600A-US | 2015-12-16 | 2016-01-04 | 10 | 2016-01-04 | [14 empty] | 2016-05-27 | 2016-06-02 |  | Y
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03128 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6061 | Inwood Ave | N |  | 1980 | [13 empty] | CDG | N | 33 Sungrow Power Supply SG60KU (44) Huawei SUN2000-45KTL-US | 2016-01-07 | 2016-01-28 | 15 | 2016-01-28 | 2016-01-07 | 2016-01-28 | 15 | 2016-03-18 | 2016-05-03 | 2016-07-28 | 60 | 15971.01 | 411500 | 362078.44 | 2017-06-23 | 2017-08-24 | 2017-08-24 | 2019-02-07 | 2019-03-18 | 2019-03-18 | 2019-08-27 | Y | N | 3/7/19 - Requested as-built 3LD. 8/12/19 - Received as-built 3LD.
Central Hudson |  | Infinity Solar Systems | CH-03373 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 6074 | East Park | N |  | 10 | [13 empty] | NM | N | (2) SMA America SB5000TL-US-22 | 2015-12-17 | 2016-01-05 | 10 | 2016-01-05 | [14 empty] | 2016-01-18 | 2016-01-25 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Lighthouse Solar | CH-03840 | Fishkill | Wappingrs Falls |  | 12590 | G | 8014 | Forgebrook | TBD |  | 7.6 | [13 empty] | NM | N | SOLAREDGE 7600 A-US | 2015-12-28 | 2016-01-07 | 7 | 2016-01-07 | [17 empty] | W
Central Hudson |  | SolarCity | CH-04948 | Newburgh | Gardiner | Ulster | 12525 | G | 5031 | Galeville | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2016-03-01 | 2016-03-01 | 0 | 2016-03-01 | [14 empty] | 2016-03-23 | 2016-03-31 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-04971 | Newburgh | Marlboro | Ulster | 12542 | G | 5004 | Marlboro | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000-OUTD-US-Z-A | 2015-12-17 | 2016-02-24 | 45 | 2016-02-24 | [14 empty] | 2016-03-09 | 2016-03-09 |  | Y
Central Hudson |  | SolarCity | CH-05075 | Newburgh | Milton | Ulster | 12547 | G | 5083 | Highland | N |  | 12 | [13 empty] | NM | N | ABB PVI-6000 (2) | 2016-02-04 | 2016-02-04 | 0 | 2016-02-04 | [14 empty] | 2016-02-18 | 2016-02-25 |  | Y
Central Hudson |  | SolarCity | CH-05333 | Fishkill | Fishkill | Dutchess | 12524 | G | 8014 | Forgebrook | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2015-12-17 | 2016-01-05 | 10 | 2016-01-05 | [14 empty] | 2016-02-11 | 2016-02-19 |  | Y
Central Hudson |  | SolarCity | CH-05990 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8091 | Fishkill Plains | N |  | 3.6 | [13 empty] | NM | N | ABB PVI-3.6-OUTD-S-US-Z- | 2016-01-05 | 2016-01-18 | 9 | 2016-01-18 | [14 empty] | 2016-01-27 | 2016-02-02 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07295 | Poughkeepsie | Poughquag | Dutchess | 12570 | G | 6055 | Todd Hill | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000-OUTD-US-Z-A | 2016-02-10 | 2016-02-18 | 5 | 2016-02-18 | [14 empty] | 2016-03-03 | 2016-03-03 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Sungevity Inc | CH-09338 | Fishkill | Wappingrs Falls |  | 12590 | G | 8091 | Fishkill Plains | TBD |  | 7.6 | [13 empty] | NM | N | ABB PVI-3.8-OUTD-S-US-A (2) | 2016-01-21 | 2016-01-29 | 6 | 2016-01-29 | [17 empty] | W |  | 12/24/15 & 12/25/15 Company Holiday.
Central Hudson |  | Apex Solar Power | CH-00014 | Fishkill | Beacon | Dutchess | 12508 | G | 8015 | Forgebrook | N |  | 7.6 | [13 empty] | NM | N | SOLAR EDGE SE7600A-US | 2015-12-18 | 2016-01-06 | 10 | 2016-01-06 | [14 empty] | 2016-08-11 | 2016-08-16 |  | Y
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03129 | Kingston | Saugerties |  | 12477 | G | 1021 | East Kingston | TBD |  | 2000 | [13 empty] | CDG | N | (2) SUNGROW SG 1000MX | 2016-01-07 | 2016-01-28 | 15 | 2016-01-28 | 2016-01-07 | 2016-01-28 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | CESIR determined necessary during preliminary review Section C, Step 4.
Central Hudson |  | Apex Solar Power | CH-00709 | Fishkill | Beacon | Dutchess | 12508 | G | 8017 | Forgebrook | N |  | 7.6 | [13 empty] | NM | N | SOLAR EDGE SE7600A-US | 2015-12-18 | 2016-01-06 | 10 | 2016-01-06 | [14 empty] | 2016-04-07 | 2016-04-08 |  | Y
Central Hudson |  | SolarCity | CH-05431 | Newburgh | Rock Tvrn |  | 12575 | G | 4097 | Bethlehem Rd | TBD |  | 4.2 | [13 empty] | NM | N | ABB PVI-4.2-OUTD-S-US-Z | 2015-12-29 | 2016-01-07 | 6 | 2016-01-07 | [17 empty] | W |  | 12/24/15 & 12/25/15 Company Holiday.
Central Hudson |  | SolarCity | CH-06727 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6046 | Spackenkill | N |  | 8.2 | [13 empty] | NM | N | FRONIUS PRIMO 8.2 | 2015-12-28 | 2016-01-07 | 7 | 2016-01-07 | [14 empty] | 2016-03-01 | 2016-03-08 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07325 | Newburgh | Highland | Ulster | 12528 | G | 5081 | Highland | N |  | 10 | [13 empty] | NM | N | (2) ABB PVI-5000-OUTD-US-Z-A | 2016-02-18 | 2016-03-01 | 8 | 2016-03-01 | [14 empty] | 2016-03-04 | 2016-03-11 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Trinity Solar | CH-08409 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6043 | Spackenkill | N |  | 3.8 | [13 empty] | NM | N | SolarEdge SE3800A-US | 2015-12-18 | 2016-01-06 | 10 | 2016-01-06 | [14 empty] | 2016-02-05 | 2016-02-12 |  | Y
Central Hudson |  | Sol Providers | CH-08965 | Newburgh | Maybrook | Orange | 12543 | G | 5052 | Maybrook | N |  | 12.6 | [13 empty] | NM | N | SUNNYBOY 3800 TL (2) SUNNYBOY 5000 TL | 2015-12-29 | 2016-01-07 | 6 | 2016-01-07 | [14 empty] | 2016-02-08 | 2016-02-11 |  | Y
Central Hudson |  | Sungevity Inc | CH-09321 | Poughkeepsie | Lagrangevl | Dutchess | 12540 | G | 6057 | Todd Hill | N |  | 6 | [13 empty] | NM | N | (2) ABB PVI 3.0 OUT-S-US-A | 2015-12-18 | 2016-01-06 | 10 | 2016-01-06 | [14 empty] | 2016-02-02 | 2016-02-09 |  | Y
Central Hudson |  | Sungevity Inc | CH-09361 | Fishkill | Cold Spg | Putnam | 10516 | G | 8063 | Merritt Park | N |  | 3.8 | [13 empty] | NM | N | ABB PVI-3.8-OUTD-S-US-A | 2015-12-18 | 2016-01-06 | 10 | 2016-01-06 | [14 empty] | 2016-03-10 | 2016-03-17 |  | Y
Central Hudson |  | Apex Solar Power | CH-00018 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6093 | Manchester | N |  | 2.15 | [13 empty] | NM | N | (10) Enphase M215 | 2016-01-07 | 2016-01-14 | 5 | 2016-01-14 | [14 empty] | 2016-05-31 | 2016-06-07 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-03392 | Newburgh | Cornwall | Orange | 12518 | G | 4093 | Bethlehem Rd | N |  | 10 | [13 empty] | NM | N | SMA AMERICA SB5000TL-US-22 (2) | 2015-12-21 | 2016-01-07 | 10 | 2016-01-07 | [14 empty] | 2016-03-09 | 2016-03-16 |  | Y
Central Hudson |  | SolarCity | CH-05099 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7061 | Milan | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2016-04-19 | 2016-04-19 | 0 | 2016-04-19 | [14 empty] | 2016-04-21 | 2016-04-28 |  | Y
Central Hudson |  | SolarCity | CH-05135 | Newburgh | Marlboro | Ulster | 12542 | G | 5004 | Marlboro | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2015-12-30 | 2016-01-07 | 5 | 2016-01-07 | [14 empty] | 2016-03-01 | 2016-03-08 |  | Y
Central Hudson |  | SolarCity | CH-05188 | Newburgh | Walden | Orange | 12586 | G | 4026 | Coldenham | N |  | 7.6 | [13 empty] | NM | N | FRONIUS FRONIUS 7.6 | 2016-01-13 | 2016-01-22 | 7 | 2016-01-22 | [14 empty] | 2016-01-27 | 2016-01-29 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-05257 | Poughkeepsie | Millbrook | Dutchess | 12545 | G | 7025 | Tinkertown | N |  | 5 | [13 empty] | NM | N | ABB PVI-5000 OUTD-S-US | 2016-03-08 | 2016-03-15 | 5 | 2016-03-15 | [8 empty] | 350 | 350 |  | 2016-04-21 | 2016-04-21 | 2016-06-10 | 2016-06-10 | 2016-06-15 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-05314 | Newburgh | New Windsor | Orange | 12553 | G | 4097 | Bethlehem Rd | N |  | 12 | [13 empty] | NM | N | ABB PVI-6000OUTD-S-US (2) | 2016-01-14 | 2016-01-22 | 6 | 2016-01-22 | [14 empty] | 2016-01-27 | 2016-01-28 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-05397 | Newburgh | Wallkill | Ulster | 12589 | G | 5011 | Modena | N |  | 22.8 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 (3) | 2016-01-11 | 2016-01-22 | 9 | 2016-01-22 | [8 empty] | 350 | 350 |  | 2016-02-11 | 2016-02-11 | 2016-02-18 | 2016-03-03 | 2016-03-10 |  | Y
Central Hudson |  | SolarCity | CH-05519 | Catskill | Acra | Greene | 12405 | G | 2043 | South Cairo | N |  | 3.6 | [13 empty] | NM | N | ABB 3.6 OUTD-S-US | 2015-12-21 | 2016-01-04 | 7 | 2016-01-04 | [14 empty] | 2016-03-31 | 2016-04-07 |  | Y
Central Hudson |  | SolarCity | CH-05741 | Kingston | Saugerties | Ulster | 12477 | G | 3001 | Saugerties | N |  | 8.2 | [13 empty] | NM | N | FRONIUS PRIMO 8.2 | 2015-12-21 | 2016-01-07 | 10 | 2016-01-07 | [14 empty] | 2016-01-11 | 2016-01-18 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-05784 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6095 | Manchester | N |  | 5 | [13 empty] | NM | N | SolarEdge SE5000A-US-ZB-U | 2016-02-16 | 2016-02-23 | 5 | 2016-02-23 | [14 empty] | 2016-02-29 | 2016-03-07 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06138 | Fishkill | Beacon | Dutchess | 12508 | G | 8015 | Forgebrook | N |  | 5 | [13 empty] | NM | N | ABB PVI-5000 OUTD-S-US | 2015-12-30 | 2016-01-07 | 5 | 2016-01-07 | [14 empty] | 2016-02-11 | 2016-02-19 |  | Y
Central Hudson |  | SolarCity | CH-06202 | Newburgh | Walden | Orange | 12586 | G | 5041 | East Walden | N |  | 9.2 | [13 empty] | NM | N | ABB PVI-4.2 OUTD-S-US ABB PVI-5000 OUTD-US | 2015-12-30 | 2016-01-07 | 5 | 2016-01-07 | [14 empty] | 2016-02-24 | 2016-02-29 |  | Y
Central Hudson |  | SolarCity | CH-06220 | Newburgh | Newburgh | Orange | 12550 | G | 4024 | Coldenham | N |  | 5 | [13 empty] | NM | N | ABB PVE-5000 OUTD-US | 2016-01-08 | 2016-01-22 | 10 | 2016-01-22 | [14 empty] | 2016-02-11 | 2016-02-19 |  | Y
Central Hudson |  | SolarCity | CH-06480 | Kingston | Olive Brdg | Ulster | 12461 | G | 3024 | High Falls | N |  | 5 | [13 empty] | NM | N | ABB PVI-5000-OUTD-US-Z-A | 2015-12-21 | 2016-01-04 | 7 | 2016-01-04 | [14 empty] | 2016-01-18 | 2016-01-25 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06726 | Poughkeepsie | Lagrangevl | Dutchess | 12540 | G | 6055 | Todd Hill | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2015-12-21 | 2016-01-07 | 10 | 2016-01-07 | [14 empty] | 2016-01-21 | 2016-01-25 |  | Y
Central Hudson |  | SolarCity | CH-06874 | Fishkill | Fishkill | Dutchess | 12524 | G | 8065 | Merritt Park | N |  | 12 | [13 empty] | NM | N | ABB PVI-6000 OUTD-S-US (2) | 2016-01-08 | 2016-01-22 | 10 | 2016-01-22 | [14 empty] | 2016-03-17 | 2016-03-24 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06918 | Fishkill | Stormvl | Dutchess | 12582 | G | 8071 | Shenandoah | N |  | 10.2 | [13 empty] | NM | N | ABB PVI-3.0 OUTD-S-US (2) ABB PVI4.2 OUTD-S-US (1) | 2015-12-21 | 2016-01-06 | 9 | 2016-01-06 | [14 empty] | 2016-01-19 | 2016-01-20 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07204 | Kingston | Stone Ridge | Ulster | 12484 | G | 3023 | High Falls | N |  | 10.2 | [13 empty] | NM | N | ABB PVI-6000 OUTD-S-US ABB PVI-4.2 OUTD-S-US | 2015-12-21 | 2016-01-04 | 7 | 2016-01-04 | [14 empty] | 2016-04-06 | 2016-04-13 |  | Y
Central Hudson |  | SolarCity | CH-07353 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8093 | Fishkill Plains | N |  | 16.4 | [13 empty] | NM | N | FRONIUS PRIMO 8.2 (2) | 2015-12-30 | 2016-01-07 | 5 | 2016-01-07 | [14 empty] | 2016-03-17 | 2016-03-23 |  | Y
Central Hudson |  | SolarCity | CH-07454 | Newburgh | Marlboro | Ulster | 12542 | G | 5003 | Marlboro | N |  | 5 | [13 empty] | NM | N | ABB OUTD-S-US | 2015-12-30 | 2016-01-07 | 5 | 2016-01-07 | [14 empty] | 2016-01-25 | 2016-01-26 |  | Y
Central Hudson |  | SolarCity | CH-07598 | Newburgh | Newburgh | Orange | 12550 | G | 4047 | Union Ave | N |  | 3.6 | [13 empty] | NM | N | ABB PVI-3.6 OUTD-S-Z | 2015-12-30 | 2016-01-07 | 5 | 2016-01-07 | [14 empty] | 2016-03-30 | 2016-04-07 |  | Y
Central Hudson |  | SolarCity | CH-07846 | Catskill | Athens |  | 12015 | G | 2002 | North Catskill | TBD |  | 6 | [13 empty] | NM | N | ABB PVI-6000 OUTD-US-Z | 2015-12-21 | 2016-01-08 | 11 | 2016-01-08 | [17 empty] | W
Central Hudson |  | SolarCity | CH-07898 | Newburgh | New Paltz |  | 12561 | G | 5024 | Ohioville | TBD |  | 9.6 | [13 empty] | NM | N | ABB PVI-6000 OUTD-S-US ABB PVI-3.6 OUTD-S-US | 2015-12-30 | 2016-01-07 | 5 | 2016-01-07 | [17 empty] | W
Central Hudson |  | Solar Generation | CH-08266 | Kingston | High Fls | Ulster | 12440 | G | 3021 | High Falls | N |  | 5 | [13 empty] | NM | N | SOLAREDGE 5000A US | 2015-12-21 | 2016-01-07 | 10 | 2016-01-07 | [14 empty] | 2016-02-16 | 2016-02-23 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08735 | Catskill | Athens | Greene | 12015 | G | 2002 | North Catskill | N |  | 5.37 | [13 empty] | NM | N | 25 ENPHASE M215 602LLS2XZC | 2015-12-21 | 2016-01-04 | 7 | 2016-01-04 | [14 empty] | 2016-06-06 | 2016-06-07 |  | Y
Central Hudson |  | Self | CH-08870 | Kingston | Stone Ridge |  | 12484 | G | 3023 | High Falls | N |  | 3.87 | [13 empty] | NM | N | 18 ENPHASE M215-US | 2015-12-21 | 2016-01-07 | 10 | 2016-01-07 | [17 empty] | W
Central Hudson |  | RGS Energy | CH-03061 | Poughkeepsie | Poughkeepsie |  | 12603 | G | 6046 | Spackenkill | TBD |  | 7.095 | [13 empty] | NM | N | (33) ENPHASE M215-60-2LL-S22-IG | 2015-12-29 | 2016-01-07 | 6 | 2016-01-07 | [17 empty] | W
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03130 | Kingston | Ellenvl | Ulster | 12428 | G | 3097 | Grimley Rd | N |  | 2000 | [13 empty] | CDG | N | 1 SMA America (44) Huawei SUN2000-45KTL-US | 2016-01-07 | 2016-01-28 | 15 | 2016-01-28 | 2016-01-07 | 2016-01-28 | 15 | 2016-03-18 | 2016-05-03 | 2016-07-28 | 60 | 20000 | 872425 | 945657.71 | 2017-06-23 | 2017-11-02 | 2017-11-02 | 2019-12-27 | 2019-12-27 | 2019-12-27 | 2020-05-26 | Y |  | CESIR for 2 projects, CH-03130 and CH-03142 combined with an aggregate CESIR Cost to Customer of $40,000. Only proceeding with CH-03130.
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03131 | Kingston | Ellenville |  | 12428 | G | 3076 | Greenfield Rd | TBD |  | 2000 | [13 empty] | CDG | N | (2) SUNGROW SG 1000MX | 2016-01-07 | 2016-01-28 | 15 | 2016-01-28 | 2016-01-07 | 2016-01-28 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Infinity Solar Systems | CH-03485 | Fishkill | Beacon | Dutchess | 12508 | G | 8085 | Tioronda | N |  | 6 | [13 empty] | NM | N | SMA AMERICA SB6000TL-US-22 | 2015-12-31 | 2016-01-15 | 10 | 2016-01-15 | [14 empty] | 2016-03-01 | 2016-03-08 |  | Y
Central Hudson |  | Lotus Energy Inc. | CH-03859 | Kingston | Kerhonkson |  | 12446 | G | 3082 | Kerhonkson | TBD |  | 7.7 | [13 empty] | NM | N | SMA SB7700 TL-US-22 | 2015-12-22 | 2016-01-08 | 10 | 2016-01-08 | [17 empty] | W
Central Hudson |  | Lotus Energy Inc. | CH-03860 | Kingston | Rosendale | Ulster | 12472 | G | 3022 | High Falls | N | CH-03860 | 12 | [13 empty] | NM | N | SMA SB3800 TL-US-22 SMA SB7000 TL-US-22 | 2015-12-22 | 2016-01-08 | 10 | 2016-01-08 | [14 empty] | 2016-01-11 | 2016-01-18 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-05274 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8096 | Fishkill Plains | N |  | 12 | [13 empty] | NM | N | ABB PVI 6000 (2) | 2015-12-31 | 2016-01-18 | 11 | 2016-01-18 | [14 empty] | 2016-03-17 | 2016-03-24 |  | Y
Central Hudson |  | SolarCity | CH-06187 | Newburgh | Highland | Ulster | 12528 | G | 5083 | Highland | N |  | 5 | [13 empty] | NM | N | ABB PVI 5 | 2015-12-22 | 2016-01-06 | 8 | 2016-01-06 | [14 empty] | 2016-02-01 | 2016-02-01 |  | Y
Central Hudson |  | Sungevity Inc | CH-09471 | Newburgh | Wallkill | Ulster | 12589 | G | 5041 | East Walden | N |  | 15.8 | [13 empty] | NM | N | ABB PVI-6000-OUTD-US-A (2) ABB PVI-3.8-OUTD-S-US-A (1) | 2015-12-22 | 2016-01-08 | 10 | 2016-01-08 | [14 empty] | 2016-02-19 | 2016-02-26 |  | Y
Central Hudson |  | Sungevity Inc | CH-09526 | Fishkill | Poughkeepsie | Dutchess | 12603 | G | 8022 | Knapps Corners | N |  | 8 | [13 empty] | NM | N | (1) ABB PVI-3.8-OUTD-S-US-A (1) ABB PVI-4.2-OUTD-S-US-A | 2015-12-29 | 2016-01-07 | 6 | 2016-01-07 | [14 empty] | 2016-03-16 | 2016-03-23 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-03391 | Newburgh | Wallkill | Ulster | 12589 | G | 5033 | Galeville | N |  | 7.6 | [13 empty] | NM | N | SMA AMERICA SB3800TL-US-22 (2) | 2016-01-11 | 2016-01-25 | 10 | 2016-01-25 | [14 empty] | 2016-03-30 | 2016-04-06 |  | Y
Central Hudson |  | NRG Home Solar | CH-04147 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8092 | Fishkill Plains | N |  | 3.87 | [13 empty] | NM | N | ENPHASE M215 (18) | 2015-12-23 | 2016-01-06 | 7 | 2016-01-06 | [14 empty] | 2016-02-18 | 2016-02-25 |  | Y
Central Hudson |  | NRG Home Solar | CH-04215 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6061 | Inwood Ave | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE 7600 | 2015-12-23 | 2016-01-11 | 10 | 2016-01-11 | [14 empty] | 2016-06-06 | 2016-06-13 |  | Y
Central Hudson |  | NRG Home Solar | CH-04300 | Kingston | Kingston |  | 12401 | G | 2013 | Lincoln Park | TBD |  | 7.6 | [13 empty] | NM | N | ENPHASE 7600 | 2015-12-23 | 2016-01-11 | 10 | 2016-01-11 | [17 empty] | W |  | 12/24, 12/25/2015, and 1/1/2016 Company Holiday. Customer already had net meter prior to application.
Central Hudson |  | NRG Home Solar | CH-00504 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6042 | Spackenkill | N |  | 3.01 | [13 empty] | NM | N | (14) ENPHASE M215 | 2015-12-23 | 2016-01-11 | 10 | 2016-01-11 | [14 empty] | 2016-04-12 | 2016-04-14 |  | Y
Central Hudson |  | NRG Home Solar | CH-04583 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8091 | Fishkill Plains | N |  | 6 | [13 empty] | NM | N | SOLAREDGE 6000 | 2015-12-23 | 2016-01-06 | 7 | 2016-01-06 | [14 empty] | 2016-02-10 | 2016-02-11 |  | Y
Central Hudson |  | NRG Home Solar | CH-04620 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8093 | Fishkill Plains | N |  | 5.37 | [13 empty] | NM | N | ENPHASE M215 (25) | 2015-12-23 | 2016-01-06 | 7 | 2016-01-06 | [14 empty] | 2016-04-26 | 2016-04-28 |  | Y
Central Hudson |  | NRG Home Solar | CH-04722 | Fishkill | Fishkill |  | 12524 | G | 8065 | Merritt Park | TBD |  | 2.58 | [13 empty] | NM | N | ENPHASE M215 (12) | 2015-12-23 | 2016-01-06 | 7 | 2016-01-06 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | PosiGen Solar | CH-02927 | Catskill | Acra |  | 12405 | G | 2041 | South Cairo | TBD |  | 5.8 | [13 empty] | NM | N | 27 ENPHASE M215-60-2LL-S22-IG | 2015-12-23 | 2016-01-11 | 10 | 2016-01-11 | [17 empty] | W |  | 12/24, 12/25/2015, 1/1/2016 Company Holidays.
Central Hudson |  | Solar Generation | CH-08297 | Kingston | Saugerties | Ulster | 12477 | G | 3001 | Saugerties | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE 7600A US | 2015-12-23 | 2016-01-11 | 10 | 2016-01-11 | [14 empty] | 2016-02-05 | 2016-02-29 |  | Y
Central Hudson |  | Trinity Solar | CH-08457 | Newburgh | Gardiner | Ulster | 12525 | G | 5031 | Galeville | N | CH-08457 | 10 | [13 empty] | NM | N | SOLAR EDGE SE10000A-US | 2015-12-23 | 2016-01-08 | 9 | 2016-01-08 | [14 empty] | 2016-02-22 | 2016-02-26 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08728 | Catskill | Greenvl | Greene | 12083 | G | 2061 | Freehold | N | CH-08728 | 2.58 | [13 empty] | NM | N | 12 ENPHASE M215 602LLS2XZC | 2015-12-23 | 2016-01-11 | 10 | 2016-01-11 | [14 empty] | 2016-07-25 | 2016-07-26 |  | Y
Central Hudson |  | Sol Providers | CH-08950 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8046 | Myers Corners | N |  | 5 | [13 empty] | NM | N | SMA 5000 TL-US-22 | 2015-12-23 | 2016-01-06 | 7 | 2016-01-06 | [14 empty] | 2016-01-20 | 2016-01-26 |  | Y
Central Hudson |  | Sungevity Inc | CH-09614 | Newburgh | New Paltz | Ulster | 12561 | G | 5024 | Ohioville | N | CH-09466 | 3.8 | [13 empty] | NM | N | ABB PVI-3.8-OUTD-S-US-A | 2015-12-23 | 2016-01-06 | 7 | 2016-01-06 | [14 empty] | 2016-02-02 | 2016-02-02 |  | Y
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03132 | Kingston | High Fls |  | 12440 | G | 3024 | High Falls | TBD |  | 1980 | [13 empty] | CDG | N | (44) Huawei SUN2000-45KTL-US | 2016-01-07 | 2016-01-28 | 15 | 2016-01-28 | 2016-01-28 | 2016-01-28 | 0 | 2016-03-18 | 2016-05-03 | 2016-07-28 | 60 | 23396.28 | 204600 | 1468.39 | 2017-06-23 | 2017-09-11 | 2017-09-11 |  |  |  | 2019-04-09 | W |  | CESIR for 2 projects, CH-03132 and CH-03135 combined with an aggregate CESIR Cost to Customer of $40,000. Only proceeding with CH-03132.
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03133 | Kingston | Ellenville |  | 12428 | G | 3095 | Grimley Rd | TBD |  | 2000 | [13 empty] | CDG | N | (2) SUNGROW SG 1000MX | 2016-01-07 | 2016-01-28 | 15 | 2016-01-28 | 2016-01-07 | 2016-01-28 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03134 | Kingston | Kingston | Ulster | 12401 | G | 2016 | Lincoln Park | N |  | 1980 | [13 empty] | CDG | N | 33 Sungrow Power Supply SG60KU-M | 2016-01-07 | 2016-01-28 | 15 | 2016-01-28 | 2016-01-07 | 2016-01-28 | 15 | 2016-03-18 | 2016-05-03 | 2016-07-28 | 60 | 15571 | 117500 | 95355.24 | 2017-06-23 | 2017-08-17 | 2017-08-17 | 2018-10-22 | 2019-03-27 | 2019-03-28 | 2019-09-06 | Y |  | 3/27/19 - Requested as-built 3LD. 9/3/19 - Received as-built 3LD.
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03135 | Kingston | Accord |  | 12404 | G | 3024 | High Falls | TBD |  | 1980 | [13 empty] | CDG | N | (44) Huawei SUN2000-45KTL-US | 2016-01-07 | 2016-01-28 | 15 | 2016-01-28 | 2016-01-07 | 2016-01-28 | 15 | 2016-03-18 | 2016-05-03 | 2016-07-28 | 60 | 20000 | [8 empty] | 2017-10-12 | W |  | CESIR for 2 projects combined with an aggregate CESIR Cost to Customer of $40,000 & Total Estimated Upgrade Costs of $4,327,666.
Central Hudson |  | New York State Solar Farm | CH-03977 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6096 | Manchester | N |  | 12.7 | [13 empty] | NM | N | SMA AMERICA 7700SB SMA AMERICA 5000SB | 2015-12-28 | 2016-01-07 | 7 | 2016-01-07 | [14 empty] | 2016-02-10 | 2016-02-17 |  | Y
Central Hudson |  | New York State Solar Farm | CH-04092 | Kingston | Saugerties | Ulster | 12477 | G | 3002 | Saugerties | N |  | 7.6 | [13 empty] | NM | N | SMA AMERICA SB3800TL (2) | 2015-12-28 | 2016-01-12 | 10 | 2016-01-12 | [14 empty] | 2016-02-26 | 2016-03-04 |  | Y
Central Hudson |  | Hudson Solar | CH-01220 | Newburgh | Wallkill | Ulster | 12589 | G | 5043 | East Walden | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE-6000 A-US-U | 2015-12-28 | 2016-01-05 | 5 | 2016-01-05 | [14 empty] | 2016-03-02 | 2016-03-09 |  | Y
Central Hudson |  | Hudson Solar | CH-01978 | Newburgh | Wallkill | Ulster | 12589 | G | 5043 | East Walden | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE-5000 A-US-U | 2015-12-28 | 2016-01-05 | 5 | 2016-01-05 | [14 empty] | 2016-03-02 | 2016-03-09 |  | Y
Central Hudson |  | Hudson Solar | CH-02238 | Kingston | W Hurley | Ulster | 12491 | G | 3013 | Woodstock | N |  | 10 | [13 empty] | NM | N | SOLAREDGE SE-10000A-US-U | 2015-12-28 | 2016-01-12 | 10 | 2016-01-12 | [14 empty] | 2016-02-18 | 2016-02-25 |  | Y
Central Hudson |  | Hudson Solar | CH-02357 | Fishkill | Cold Spring | Putnam | 10516 | G | 8086 | Tioronda | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE-6000 A-US-U | 2015-12-28 | 2016-01-07 | 7 | 2016-01-07 | [14 empty] | 2016-02-26 | 2016-03-04 |  | Y
Central Hudson |  | Monolith Solar Associates LLC | CH-02685 | Catskill | Greenvl | Greene | 12083 | G | 1092 | Westerlo | N |  | 6 | [13 empty] | NM | N | SOLAR EDGE SE6000 | 2015-12-28 | 2016-01-12 | 10 | 2016-01-12 | [14 empty] | 2016-06-17 | 2016-06-21 |  | Y
Central Hudson |  | SolarCity | CH-05449 | Newburgh | Highland | Ulster | 12528 | G | 5083 | Highland | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2016-01-14 | 2016-01-28 | 10 | 2016-01-28 | [14 empty] | 2016-03-11 | 2016-03-18 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-05998 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8091 | Fishkill Plains | N |  | 6.6 | [13 empty] | NM | N | ABB PVI-3.6 OUTD-S-US ABB PVI-3.0 OUTD-S-US | 2016-01-22 | 2016-01-29 | 5 | 2016-01-29 | [14 empty] | 2016-02-11 | 2016-02-19 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07419 | Newburgh | Newburgh | Orange | 12550 | G | 4014 | West Balmville | N |  | 3 | [13 empty] | NM | N | ABB PVI-3.0 OUTD-S-US | 2015-12-28 | 2016-01-07 | 7 | 2016-01-07 | [14 empty] | 2016-02-10 | 2016-02-11 |  | Y
Central Hudson |  | SolarCity | CH-07664 | Fishkill | Fishkill | Dutchess | 12524 | G | 8065 | Merritt Park | N |  | 7.2 | [13 empty] | NM | N | ABB PVI-3.6 OUTD-S-US (2) | 2016-01-22 | 2016-01-29 | 5 | 2016-01-29 | [14 empty] | 2016-02-24 | 2016-02-29 |  | Y
Central Hudson |  | SolarCity | CH-07925 | Kingston | Kerhonkson |  | 12446 | G | 3082 | Kerhonkson | TBD |  | 1992 | [13 empty] | CDG | N | FRONIUS SYMO 24KW (83) | 2016-02-02 | 2016-02-24 | 15 | 2016-02-24 | 2016-02-02 | 2016-02-24 | 15 |  |  |  |  | 32000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Sol Providers | CH-08973 | Poughkeepsie | Poughkeepsie |  | 12603 | G | 6092 | Manchester | TBD |  | 11.4 | [13 empty] | NM | N | SOLAREDGE SE 11400A-US | 2015-12-28 | 2016-01-07 | 7 | 2016-01-07 | [17 empty] | W
Central Hudson |  | CEC Development, LLC | CH-03117 | Catskill | New Baltimore |  | 12124 | G | 1082 | New Baltimore | TBD |  | 1944 | [13 empty] | CDG | N | (64) SMA STP 30000TL-US (1) SMA STP 24000TL-US | 2016-02-09 | 2016-03-01 | 14 | 2016-03-01 | 2016-02-09 | 2016-03-01 | 14 |  |  |  |  | 32000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Lighthouse Solar | CH-03560 | Catskill | Palenville | Greene | 12463 | G | 2001 | North Catskill | N |  | 18 | [13 empty] | NM | N | 3 ABB PVI 6000 | 2015-12-29 | 2016-01-13 | 10 | 2016-01-13 | [14 empty] | 2016-03-23 | 2016-03-31 |  | Y
Central Hudson |  | NRG Home Solar | CH-04126 | Fishkill | Hopewell Jct |  | 12533 | G | 8094 | Fishkill Plains | TBD |  | 5.37 | [13 empty] | NM | N | ENPHASE M215 (25) | 2015-12-29 | 2016-01-07 | 6 | 2016-01-07 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | NRG Home Solar | CH-04245 | Catskill | Catskill |  | 12414 | G | 2003 | North Catskill | TBD |  | 5.59 | [13 empty] | NM | N | 26 ENPHASE M215 | 2015-12-29 | 2016-01-13 | 10 | 2016-01-13 | [17 empty] | W |  | 1/1/2016 Company Holiday. Customer already had net meter prior to application.
Central Hudson |  | NRG Home Solar | CH-04251 | Catskill | Ravena | Albany | 12143 | G | 1082 | New Baltimore | N |  | 10 | [13 empty] | NM | N | 1 SOLAREDGE SE10000 | 2015-12-29 | 2016-01-13 | 10 | 2016-01-13 | [14 empty] | 2016-02-09 | 2016-02-17 |  | Y
Central Hudson |  | NRG Home Solar | CH-04597 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8091 | Fishkill Plains | N |  | 10 | [13 empty] | NM | N | SOLAREDG SE1000 | 2016-01-11 | 2016-01-22 | 9 | 2016-01-22 | [14 empty] | 2016-02-04 | 2016-02-04 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | NRG Home Solar | CH-00540 | Fishkill | Beacon | Dutchess | 12508 | G | 8017 | Forgebrook | N |  | 3.22 | [13 empty] | NM | N | ENPHASE M215 (15) | 2015-12-29 | 2016-01-07 | 6 | 2016-01-07 | [14 empty] | 2016-05-31 | 2016-06-03 |  | Y
Central Hudson |  | SolarCity | CH-05246 | Kingston | Kerhonkson | Ulster | 12446 | G | 3081 | Kerhonkson | N |  | 6 | [13 empty] | NM | N | ABB PVI 6 | 2015-12-29 | 2016-01-13 | 10 | 2016-01-13 | [14 empty] | 2016-01-19 | 2016-01-26 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-05522 | Catskill | E Durham | Greene | 12423 | G | 2043 | South Cairo | N |  | 3 | [13 empty] | NM | N | ABB PVI 3.0 | 2015-12-29 | 2016-01-13 | 10 | 2016-01-13 | [14 empty] | 2016-06-08 | 2016-06-13 |  | Y
Central Hudson |  | SolarCity | CH-05756 | Kingston | Saugerties | Ulster | 12477 | G | 2015 | Lincoln Park | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2015-12-29 | 2016-01-13 | 10 | 2016-01-13 | [14 empty] | 2016-02-09 | 2016-02-16 |  | Y
Central Hudson |  | SolarCity | CH-06120 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8093 | Fishkill Plains | N |  | 8.4 | [13 empty] | NM | N | ABB PVI-4.2 OUTD-S-US (2) | 2015-12-29 | 2016-01-07 | 6 | 2016-01-07 | [14 empty] | 2016-01-26 | 2016-01-29 |  | Y
Central Hudson |  | SolarCity | CH-06712 | Poughkeepsie | Hopewell Jct | Dutchess | 12533 | G | 6052 | Todd Hill | N |  | 9.6 | [13 empty] | NM | N | ABB PVI-6000 OUTD-S-US ABB PVI-3.6 OUTD-S-US | 2015-12-29 | 2016-01-07 | 6 | 2016-01-07 | [14 empty] | 2016-07-28 | 2016-07-28 |  | Y
Central Hudson |  | SolarCity | CH-06910 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8093 | Fishkill Plains | N |  | 3 | [13 empty] | NM | N | ABB PVI-3.0 OUTD-S-US | 2015-12-29 | 2016-01-07 | 6 | 2016-01-07 | [14 empty] | 2016-01-11 | 2016-01-13 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07020 | Newburgh | New Windsor | Orange | 12553 | G | 4043 | Union Ave | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000 OUTD-S-US | 2016-01-13 | 2016-01-22 | 7 | 2016-01-22 | [14 empty] | 2016-03-01 | 2016-03-08 |  | Y
Central Hudson |  | SolarCity | CH-07375 | Fishkill | Fishkill | Dutchess | 12524 | G | 8055 | North Chelsea | N |  | 5 | [13 empty] | NM | N | ABB PVI-5000-OUTD-US-Z-A | 2015-12-29 | 2016-01-07 | 6 | 2016-01-07 | [14 empty] | 2016-01-19 | 2016-01-20 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07628 | Kingston | Accord |  | 12404 | G | 3081 | Kerhonkson | N |  | 8.4 | [13 empty] | NM | N | 2 ABB PVI 4.2 | 2015-12-29 | 2016-01-13 | 10 | 2016-01-13 | [14 empty] | 2016-01-19 | 2016-01-26 |  | W |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Lotus Energy Inc. | CH-03861 | Kingston | Rosendale | Ulster | 12472 | G | 3022 | High Falls | N |  | 5 | [13 empty] | NM | N | SMA SB5000 TL-US-22 | 2015-12-30 | 2016-01-14 | 10 | 2016-01-14 | [14 empty] | 2016-03-28 | 2016-04-04 |  | Y
Central Hudson |  | Lotus Energy Inc. | CH-03862 | Kingston | Rosendale | Ulster | 12472 | G | 3021 | High Falls | N |  | 10 | [13 empty] | NM | N | 2 SMA SB5000TL-US-22 | 2015-12-30 | 2016-01-14 | 10 | 2016-01-14 | [14 empty] | 2016-02-17 | 2016-02-24 |  | Y
Central Hudson |  | NRG Home Solar | CH-04187 | Kingston | Ellenvl | Ulster | 12428 | G | 3078 | Greenfield Rd | N |  | 4.73 | [13 empty] | NM | N | 22 ENPHASE M215 | 2015-12-30 | 2016-01-14 | 10 | 2016-01-14 | [14 empty] | 2016-02-29 | 2016-03-07 |  | Y
Central Hudson |  | NRG Home Solar | CH-04351 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6093 | Manchester | N |  | 3.87 | [13 empty] | NM | N | (18) ENPHASE M215 | 2015-12-30 | 2016-01-07 | 5 | 2016-01-07 | [14 empty] | 2016-04-26 | 2016-05-03 |  | Y
Central Hudson |  | NRG Home Solar | CH-04582 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8091 | Fishkill Plains | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE7600 | 2015-12-30 | 2016-01-07 | 5 | 2016-01-07 | [14 empty] | 2016-04-12 | 2016-04-14 |  | Y
Central Hudson |  | Hudson Solar | CH-01268 | Catskill | Coxsackie | Greene | 12051 | G | 1071 | Coxsackie | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE-5000A-US-U | 2015-12-30 | 2016-01-14 | 10 | 2016-01-14 | [14 empty] | 2016-04-18 | 2016-04-25 |  | Y
Central Hudson |  | Hudson Solar | CH-01352 | Newburgh | Newburgh | Orange | 12550 | G | 5004 | Marlboro | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE-7600 A-US-U | 2015-12-30 | 2016-01-07 | 5 | 2016-01-07 | [14 empty] | 2016-04-25 | 2016-04-27 |  | Y
Central Hudson |  | Hudson Solar | CH-01699 | Kingston | Kingston | Ulster | 12401 | G | 2093 | Hurley Ave | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE-7600 A-US-U | 2015-12-30 | 2016-01-14 | 10 | 2016-01-14 | [14 empty] | 2016-02-16 | 2016-02-23 |  | Y
Central Hudson |  | Hudson Solar | CH-01984 | Newburgh | Gardiner | Ulster | 12525 | G | 5011 | Modena | N |  | 10 | [13 empty] | NM | N | SOLAREDGE SE-10000 A-US-U | 2015-12-30 | 2016-01-08 | 6 | 2016-01-08 | [8 empty] | 350 | 350 |  | 2016-01-28 | 2016-01-28 | 2016-02-02 | 2016-03-23 | 2016-03-31 |  | Y
Central Hudson |  | Hudson Solar | CH-02023 | Kingston | Accord | Ulster | 12404 | G | 3024 | High Falls | N |  | 11.4 | [13 empty] | NM | N | SOLAREDGE SE-11400A-US-U | 2015-12-30 | 2016-01-14 | 10 | 2016-01-14 | [14 empty] | 2016-02-10 | 2016-02-18 |  | Y
Central Hudson |  | Hudson Solar | CH-02042 | Kingston | Kingston | Ulster | 12401 | G | 2093 | Hurley Ave | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE-5000 A-US-U | 2015-12-30 | 2016-01-14 | 10 | 2016-01-14 | [14 empty] | 2016-02-22 | 2016-02-29 |  | Y
Central Hudson |  | Hudson Solar | CH-02233 | Kingston | Kingston | Ulster | 12401 | G | 1022 | East Kingston | N |  | 10 | [13 empty] | NM | N | SOLAREDGE SE-10000A-US-U | 2015-12-30 | 2016-01-14 | 10 | 2016-01-14 | [14 empty] | 2016-01-28 | 2016-02-04 |  | Y
Central Hudson |  | Hudson Solar | CH-02496 | Newburgh | Montgomery | Orange | 12549 | G | 5054 | Maybrook | N | CH-01589 | 6 | [13 empty] | NM | N | SMA AMERICA SB6000 TL-US-22 | 2016-01-07 | 2016-01-21 | 10 | 2016-01-21 | [14 empty] | 2016-04-01 | 2016-04-07 |  | Y
Central Hudson |  | SolarCity | CH-04941 | Kingston | Saugerties | Ulster | 12477 | G | 2015 | Lincoln Park | N |  | 8.6 | [13 empty] | NM | N | ABB PVI-5000 OUTD-S-US ABB PVI-3.6 OUTD-S-US | 2015-12-30 | 2016-01-14 | 10 | 2016-01-14 | [14 empty] | 2016-06-15 | 2016-06-22 |  | Y
Central Hudson |  | SolarCity | CH-04988 | Catskill | Ravena | Albany | 12143 | G | 1082 | New Baltimore | N |  | 23.4 | [13 empty] | NM | N | FRONIUS PRIMO 8.2 FRONIUS PRIMO 7.6 x2 | 2015-12-30 | 2016-01-14 | 10 | 2016-01-14 | [14 empty] | 2016-01-28 | 2016-02-11 |  | Y
Central Hudson |  | SolarCity | CH-06065 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8094 | Fishkill Plains | N |  | 7.8 | [13 empty] | NM | N | ABB PVI-4.2 OUTD-S-US ABB PVI-3.6 OUTD-S-US | 2015-12-30 | 2016-01-15 | 11 | 2016-01-15 | [14 empty] | 2016-03-29 | 2016-04-05 |  | Y
Central Hudson |  | SolarCity | CH-06147 | Fishkill | Beacon |  | 12508 | G | 8085 | Tioronda | TBD |  | 3 | [13 empty] | NM | N | ABB PVI-3.0 OUTD-S-US | 2015-12-30 | 2016-01-15 | 11 | 2016-01-15 | [17 empty] | W |  | 1/1/16 Company Holiday.
Central Hudson |  | SolarCity | CH-06483 | Kingston | High Fls | Ulster | 12440 | G | 3022 | High Falls | N |  | 5 | [13 empty] | NM | N | ABB PVI-5000 OUTD-S-US | 2015-12-30 | 2016-01-14 | 10 | 2016-01-14 | [14 empty] | 2016-02-23 | 2016-03-01 |  | Y
Central Hudson |  | SolarCity | CH-06539 | Kingston | Kingston | Ulster | 12401 | G | 2092 | Hurley Ave | N |  | 4.2 | [13 empty] | NM | N | ABB PVI-4.2 OUTD-S-US | 2015-12-30 | 2016-01-14 | 10 | 2016-01-14 | [14 empty] | 2016-01-26 | 2016-02-02 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08636 | Kingston | Kingston | Ulster | 12401 | G | 1021 | East Kingston | N |  | 5.8 | [13 empty] | NM | N | 27 ENPHASE M215 602LLS2XZC | 2015-12-30 | 2016-01-14 | 10 | 2016-01-14 | [14 empty] | 2016-05-11 | 2016-05-17 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08804 | Kingston | Saugerties | Ulster | 12477 | G | 3003 | Saugerties | N |  | 6.88 | [13 empty] | NM | N | 32 ENPHASE M215 602LLS2XZC | 2015-12-30 | 2016-01-14 | 10 | 2016-01-14 | [14 empty] | 2016-06-13 | 2016-06-16 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08835 | Kingston | Kingston |  | 12401 | G | 1021 | East Kingston | TBD |  | 7.74 | [13 empty] | NM | N | 36 ENPHASE M215 602LLS2XZC | 2015-12-30 | 2016-01-14 | 10 | 2016-01-14 | [17 empty] | W
Central Hudson |  | You Save Green | CH-09965 | Newburgh | Campbell Hall | Orange | 10916 | G | 5052 | Maybrook | N |  | 9 | [13 empty] | NM | N | SOLAR EDGE SE6000A-US SOLAR EDGE SE3000A-US | 2016-01-08 | 2016-01-21 | 9 | 2016-01-21 | [14 empty] | 2016-06-01 | 2016-06-07 |  | Y
Central Hudson |  | Lotus Energy Inc. | CH-03842 | Kingston | High Fls | Ulster | 12440 | G | 3022 | High Falls | N |  | 7.7 | [13 empty] | NM | N | SMA SB7700 TL-US-22 | 2015-12-31 | 2016-01-15 | 10 | 2016-01-15 | [14 empty] | 2016-03-14 | 2016-03-21 |  | Y
Central Hudson |  | NRG Home Solar | CH-04296 | Kingston | Lk Katrine | Ulster | 12449 | G | 2011 | Lincoln Park | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000 | 2015-12-31 | 2016-01-15 | 10 | 2016-01-15 | [14 empty] | 2016-02-12 | 2016-02-22 |  | Y
Central Hudson |  | Monolith Solar Associates LLC | CH-02688 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7053 | Rhinebeck | N |  | 12 | [13 empty] | NM | N | SolarEdge SE6000A-US (2) | 2016-01-11 | 2016-01-18 | 5 | 2016-01-18 | [14 empty] | 2016-08-24 | 2016-08-25 |  | Y
Central Hudson |  | SolarCity | CH-05552 | Catskill | Freehold | Greene | 12431 | G | 2071 | Freehold | N |  | 22.8 | [13 empty] | NM | N | 3 FRONIUS PRIMO 7.6 | 2015-12-31 | 2016-01-15 | 10 | 2016-01-15 | [8 empty] | 350 | 350 |  | 2016-03-29 | 2016-03-29 | 2016-04-29 | 2016-04-29 | 2016-06-01 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07037 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 9 | [13 empty] | NM | N | ABB PVI-6000 OUTD-S-US ABB PVI-3.0 OUTD-S-US | 2016-01-13 | 2016-01-22 | 7 | 2016-01-22 | [14 empty] | 2016-02-11 | 2016-02-19 |  | Y
Central Hudson |  | SolarCity | CH-07821 | Fishkill | Hopewell Junction | Dutchess | 12533 | G | 8093 | Fishkill Plains | N | CH-06122 | 3 | [13 empty] | NM | N | ABB PVI-3.0 OUTD-S-US | 2016-02-03 | 2016-02-03 | 0 | 2016-02-03 | [14 empty] | 2017-03-22 | 2017-03-24 |  | Y
Central Hudson |  | SolarCity | CH-07908 | Newburgh | New Windsor |  | 12553 | G | 4042 | Union Ave | TBD |  | 3 | [13 empty] | NM | N | ABB PVI-3.0 OUTD-S-US | 2016-01-22 | 2016-01-29 | 5 | 2016-01-29 | [17 empty] | W
Central Hudson |  | Trinity Solar | CH-08415 | Poughkeepsie | Salt Pt | Dutchess | 12578 | G | 7011 | Hibernia | N |  | 5 | [13 empty] | NM | N | SOLAR EDGE SE5000A-US | 2016-01-11 | 2016-01-18 | 5 | 2016-01-18 | [14 empty] | 2016-04-15 | 2016-04-22 |  | Y
Central Hudson |  | EcoMen Solar | CH-03335 | Kingston | Cragsmoor | Ulster | 12420 | G | 3078 | Greenfield Rd | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE-5000-US | 2016-01-04 | 2016-01-18 | 10 | 2016-01-18 | [14 empty] | 2016-08-26 | 2016-08-26 |  | Y
Central Hudson |  | Kasselman Solar | CH-03509 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 7024 | Tinkertown | N |  | 7.5 | [13 empty] | NM | N | (30) Enphase M250 | 2016-01-12 | 2016-01-26 | 10 | 2016-01-26 | [14 empty] | 2016-02-26 | 2016-03-04 |  | Y
Central Hudson |  | SolarCity | CH-05590 | Catskill | Climax | Greene | 12042 | G | 1071 | Coxsackie | N |  | 4.2 | [13 empty] | NM | N | ABB PVI-4.2-OUTD-S US | 2016-01-04 | 2016-01-18 | 10 | 2016-01-18 | [14 empty] | 2016-02-24 | 2016-03-02 |  | Y
Central Hudson |  | SolarCity | CH-05738 | Kingston | Saugerties | Ulster | 12477 | G | 3001 | Saugerties | N |  | 6.6 | [13 empty] | NM | N | ABB PVI-3.6-OUTD-S US ABB PVI-3.0-OUTD-S US | 2016-01-04 | 2016-01-18 | 10 | 2016-01-18 | [14 empty] | 2016-06-23 | 2016-06-29 |  | Y
Central Hudson |  | SolarCity | CH-05928 | Poughkeepsie | Salt Pt | Dutchess | 12578 | G | 7011 | Hibernia | N |  | 8 | [13 empty] | NM | N | (1) ABB PVI-5000 OUTD-S-US (1) ABB PVI-3.0 OUTD-S-US | 2016-01-04 | 2016-01-18 | 10 | 2016-01-18 | [14 empty] | 2016-01-20 | 2016-01-26 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06662 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6068 | Inwood Ave | N |  | 10 | [13 empty] | NM | N | (2) ABB PVI-5000 OUTD-S-US | 2016-01-04 | 2016-01-18 | 10 | 2016-01-18 | [14 empty] | 2016-03-02 | 2016-03-09 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Trinity Solar | CH-08385 | Catskill | Cairo | Greene | 12413 | G | 2043 | South Cairo | N |  | 10 | [13 empty] | NM | N | SOLAR EDGE SE11400 A-US | 2016-01-04 | 2016-01-18 | 10 | 2016-01-18 | [14 empty] | 2016-03-28 | 2016-04-04 |  | Y
Central Hudson |  | Sure Energies Corp. | CH-09699 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8091 | Fishkill Plains | N |  | 11 | [13 empty] | NM | N | POWER ONE PVI5000 POWER ONE PVI6000 | 2016-01-15 | 2016-01-28 | 9 | 2016-01-28 | [14 empty] | 2016-03-28 | 2016-04-05 |  | Y
Central Hudson |  | SolarCity | CH-05824 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6064 | Inwood Ave | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000 OUTD-S-US | 2016-01-05 | 2016-01-12 | 5 | 2016-01-12 | [14 empty] | 2016-03-24 | 2016-04-01 |  | Y
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03136 | Kingston | Ellenville |  | 12428 | G | 3095 | Grimley Rd | TBD |  | 2000 | [13 empty] | CDG | N | SUNGROW SG 1000MX (2) | 2016-01-13 | 2016-01-28 | 11 | 2016-01-28 | 2016-01-13 | 2016-01-28 | 11 |  |  |  |  | 35000 | [9 empty] | W |  | CESIR determined necessary during preliminary review Section C, Step 4.
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03137 | Newburgh | Campbell Hall |  | 10916 | G | 5052 | Maybrook | TBD |  | 2000 | [13 empty] | CDG | N | SUNGROW SG 1000MX (2) | 2016-01-13 | 2016-02-03 | 15 | 2016-02-03 | 2016-01-13 | 2016-02-03 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03138 | Newburgh | Wallkill |  | 12589 | G | 5043 | East Walden | TBD |  | 1980 | [13 empty] | CDG | N | (44) Huawei SUN2000-45KTL-US | 2016-01-13 | 2016-02-03 | 15 | 2016-02-03 | 2016-01-13 | 2016-02-03 | 15 | 2016-03-18 | 2016-05-03 | 2016-07-28 | 60 | 20000 | [9 empty] | W |  | CESIR for 3 projects combined with an aggregate Total Estimated Upgrade Costs of $5,120,161. 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03139 | Newburgh | Campbell Hall |  | 10916 | G | 5052 | Maybrook | TBD |  | 2000 | [13 empty] | CDG | N | SUNGROW SG 1000MX (2) | 2016-01-13 | 2016-02-03 | 15 | 2016-02-03 | 2016-01-13 | 2016-02-03 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03140 | Kingston | Ellenville |  | 12428 | G | 3076 | Greenfield Rd | TBD |  | 2000 | [13 empty] | CDG | N | SUNGROW SG 1000MX (2) | 2016-01-13 | 2016-01-28 | 11 | 2016-01-28 | 2016-01-13 | 2016-01-28 | 11 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03141 | Kingston | Kingston | Ulster | 12401 | G | 2094 | Hurley Ave | N |  | 2000 | [13 empty] | CDG | N | (44) Huawei SUN2000-45KTL-US | 2016-01-13 | 2016-02-03 | 15 | 2016-02-03 | 2016-01-13 | 2016-02-03 | 15 | 2016-03-18 | 2016-05-03 | 2016-07-28 | 60 | 15662.59 | 204600 | 162620.17 | 2017-06-23 | 2017-10-09 | 2017-10-09 | 2019-12-10 | 2019-12-27 | 2019-12-27 | 2020-03-24 | Y
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03143 | Newburgh | Wallkill |  | 12589 | G | 5043 | East Walden | TBD |  | 1980 | [13 empty] | CDG | N | (44) Huawei SUN2000-45KTL-US | 2016-01-15 | 2016-02-03 | 13 | 2016-02-03 | 2016-01-15 | 2016-02-03 | 13 | 2016-03-18 | 2016-05-03 | 2016-07-28 | 60 | 20000 | [9 empty] | W |  | CESIR for 3 projects combined with an aggregate Total Estimated Upgrade Costs of $5,120,161.
Central Hudson |  | New York State Solar Farm | CH-04003 | Newburgh | Ardonia | Ulster | 12515 | G | 5012 | Modena | N |  | 7.6 | [13 empty] | NM | N | SMA AMERICA SB3800TL (2) | 2016-01-06 | 2016-01-20 | 10 | 2016-01-20 | [8 empty] | 350 | 350 |  | 2016-02-19 | 2016-02-19 | 2016-03-01 | 2016-02-29 | 2016-03-07 |  | Y
Central Hudson |  | New York State Solar Farm | CH-04024 | Kingston | Kingston | Ulster | 12401 | G | 1012 | Boulevard | N |  | 3.8 | [13 empty] | NM | N | SMA AMERICA SB3800 TL | 2016-01-06 | 2016-01-19 | 9 | 2016-01-19 | [14 empty] | 2016-04-07 | 2016-04-14 |  | Y
Central Hudson |  | New York State Solar Farm | CH-04034 | Newburgh | New Paltz | Ulster | 12561 | G | 5011 | Modena | N |  | 6 | [13 empty] | NM | N | SMA AMERICA SB6000TL | 2016-01-06 | 2016-01-20 | 10 | 2016-01-20 | [14 empty] | 2016-02-05 | 2016-02-08 |  | Y
Central Hudson |  | NRG Home Solar | CH-04229 | Kingston | Catskill | Greene | 12414 | G | 3004 | Saugerties | N |  | 3.22 | [13 empty] | NM | N | 15 ENPHASE M215 | 2016-01-06 | 2016-01-19 | 9 | 2016-01-19 | [14 empty] | 2016-03-24 | 2016-04-01 |  | Y
Central Hudson |  | NRG Home Solar | CH-04595 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8095 | Fishkill Plains | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE7600 | 2016-01-06 | 2016-01-20 | 10 | 2016-01-20 | [14 empty] | 2016-04-15 | 2016-04-19 |  | Y
Central Hudson |  | Monolith Solar Associates LLC | CH-02650 | Catskill | Catskill | Greene | 12414 | G | 2004 | North Catskill | N |  | 13.6 | [13 empty] | NM | N | SOLAREDGE SE7600-US SOLAREDGE SE6000-US | 2016-01-06 | 2016-01-19 | 9 | 2016-01-19 | [14 empty] | 2016-07-26 | 2016-07-26 |  | Y
Central Hudson |  | Paradise Energy Solutions LLC | CH-02834 | Poughkeepsie | Lagrangevl | Dutchess | 12540 | G | 6055 | Todd Hill | N |  | 3.8 | [13 empty] | NM | N | SolarEdge SE3800A-US | 2016-01-14 | 2016-01-28 | 10 | 2016-01-28 | [14 empty] | 2016-04-13 | 2016-04-15 |  | Y
Central Hudson |  | SolarCity | CH-05111 | Newburgh | Newburgh | Orange | 12550 | G | 4011 | West Balmville | N |  | 8 | [13 empty] | NM | N | ABB PVI-5000-OUTDUS ABB PVI-3.0-OUTD-SUS | 2016-01-06 | 2016-01-20 | 10 | 2016-01-20 | [14 empty] | 2016-01-25 | 2016-01-29 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06935 | Fishkill | Beacon | Dutchess | 12508 | G | 8085 | Tioronda | N |  | 4.2 | [13 empty] | NM | N | ABB PVI-4.2OUTD-S-US | 2016-01-22 | 2016-01-29 | 5 | 2016-01-29 | [14 empty] | 2016-02-12 | 2016-02-22 |  | Y
Central Hudson |  | Solar Generation | CH-08176 | Kingston | Mt Tremper | Ulster | 12457 | G | 3012 | Woodstock | N |  | 7.7 | [13 empty] | NM | N | SMA SB 7700 TL | 2016-01-06 | 2016-01-19 | 9 | 2016-01-19 | [14 empty] | 2016-07-05 | 2016-07-06 |  | Y
Central Hudson |  | Solar Generation | CH-08274 | Kingston | Woodstock | Ulster | 12498 | G | 3012 | Woodstock | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE 7600A US | 2016-01-06 | 2016-01-19 | 9 | 2016-01-19 | [14 empty] | 2016-04-06 | 2016-04-13 |  | Y
Central Hudson |  | Solar Generation | CH-08311 | Kingston | Woodstock |  | 12498 | G | 3014 | Woodstock | TBD |  | 5 | [13 empty] | NM | N | SOLAREDGE 5000A US | 2016-01-06 | 2016-01-19 | 9 | 2016-01-19 | [17 empty] | W
Central Hudson |  | STR Systems NY LLC | CH-08316 | Kingston | Stone Ridge | Ulster | 12494 | G | 3023 | High Falls | N |  | 5 | [13 empty] | NM | N | Fronius 5.0 | 2016-01-06 | 2016-01-06 | 0 | 2016-01-06 | [14 empty] | 2016-08-22 | 2016-08-22 |  | Y
Central Hudson |  | Sungevity Inc | CH-09516 | Kingston | New Paltz | Ulster | 12561 | G | 3041 | Sturgeon Pool | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000-OUTD-US-A | 2016-01-06 | 2016-01-19 | 9 | 2016-01-19 | [14 empty] | 2016-04-25 | 2016-04-25 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-03396 | Newburgh | Marlboro | Ulster | 12542 | G | 5004 | Marlboro | N |  | 11 | [13 empty] | NM | N | SMA AMERICA SB5000TL-US-22 SMA AMERICA SB6000TL-US-22 | 2016-01-07 | 2016-01-21 | 10 | 2016-01-21 | [14 empty] | 2016-03-01 | 2016-03-08 |  | Y
Central Hudson |  | NRG Home Solar | CH-00522 | Newburgh | Montgomery | Orange | 12549 | G | 5072 | Montgomery | N |  | 4.51 | [13 empty] | NM | N | ENPHASE M215 (21) | 2016-01-07 | 2016-01-22 | 11 | 2016-01-22 | [14 empty] | 2016-05-05 | 2016-05-12 |  | Y
Central Hudson |  | NRG Home Solar | CH-04513 | Kingston | Smith'S Landing | Greene | 12414 | G | 3004 | Saugerties | N |  | 3.87 | [13 empty] | NM | N | 18 ENPHADE M215 | 2016-01-07 | 2016-01-21 | 10 | 2016-01-21 | [14 empty] | 2016-02-17 | 2016-02-24 |  | Y
Central Hudson |  | Hudson Solar | CH-01557 | Fishkill | Fishkill | Dutchess | 12524 | G | 8062 | Merritt Park | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE-6000 A-US-U | 2016-01-07 | 2016-01-21 | 10 | 2016-01-21 | [14 empty] | 2016-02-12 | 2016-02-19 |  | Y
Central Hudson |  | Hudson Solar | CH-01925 | Fishkill | Fishkill | Dutchess | 12524 | G | 8016 | Forgebrook | N |  | 3.8 | [13 empty] | NM | N | SOLAREDGE SE-3800 A-US-U | 2016-01-07 | 2016-01-21 | 10 | 2016-01-21 | [14 empty] | 2016-04-08 | 2016-04-11 |  | Y
Central Hudson |  | Hudson Solar | CH-02446 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7053 | Rhinebeck | N | CH-02072 | 3 | [13 empty] | NM | N | SMA AMERICA SB3000TL-US-22 | 2016-01-07 | 2016-01-14 | 5 | 2016-01-14 | [14 empty] | 2016-03-18 | 2016-03-28 |  | Y
Central Hudson |  | Hudson Solar | CH-02483 | Newburgh | New Paltz | Ulster | 12561 | G | 5031 | Galeville | N | CH-01510 | 5 | [13 empty] | NM | N | SMA AMERICA SB5000 TL-US-22 | 2016-01-14 | 2016-01-22 | 6 | 2016-01-22 | [14 empty] | 2016-02-26 | 2016-03-04 |  | Y
Central Hudson |  | PosiGen Solar | CH-02873 | Catskill | Coeymans Hollow | Albany | 12046 | G | 1081 | New Baltimore | N |  | 5.16 | [13 empty] | NM | N | 24 ENPHASE M215-60-2LL-S22-IG | 2016-01-07 | 2016-01-21 | 10 | 2016-01-21 | [14 empty] | 2016-03-03 | 2016-03-10 |  | Y
Central Hudson |  | SolarCity | CH-06159 | Newburgh | New Paltz | Ulster | 12561 | G | 5031 | Galeville | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2016-01-19 | 2016-01-29 | 8 | 2016-01-29 | [14 empty] | 2016-03-29 | 2016-04-05 |  | Y
Central Hudson |  | SolarCity | CH-07237 | Kingston | Lk Katrine | Ulster | 12449 | G | 2016 | Lincoln Park | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2016-01-07 | 2016-01-21 | 10 | 2016-01-21 | [14 empty] | 2016-01-26 | 2016-02-02 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07753 | Kingston | Olive Brdg | Ulster | 12461 | G | 3024 | High Falls | N |  | 5 | [13 empty] | NM | N | ABB PVI 5000 | 2016-01-07 | 2016-01-21 | 10 | 2016-01-21 | [14 empty] | 2016-01-26 | 2016-02-02 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08737 | Kingston | Port Ewen | Ulster | 12466 | G | 1012 | Boulevard | N |  | 6.45 | [13 empty] | NM | N | 30 ENPHASE M215 602LLS2XZC | 2016-01-07 | 2016-01-21 | 10 | 2016-01-21 | [14 empty] | 2016-05-26 | 2016-05-31 |  | Y
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03142 | Kingston | Greenfield Park |  | 12435 | G | 3096 | Grimley Rd | TBD |  | 1980 | [13 empty] | CDG | N | (44) Huawei SUN2000-45KTL-US | 2016-01-13 | 2016-01-28 | 11 | 2016-01-28 | 2016-01-13 | 2016-01-28 | 11 | 2016-03-18 | 2016-05-03 | 2016-07-28 | 60 | 20000 | [9 empty] | W |  | CESIR for 2 projects combined with an aggregate CESIR Cost to Customer of $40,000 & Total Estimated Upgrade Costs of $2,915,500.
Central Hudson |  | NRG Home Solar | CH-04639 | Newburgh | Newburgh | Orange | 12550 | G | 4012 | West Balmville | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE 7600 | 2016-01-08 | 2016-01-22 | 10 | 2016-01-22 | [14 empty] | 2016-04-15 | 2016-04-19 |  | Y
Central Hudson |  | NRG Home Solar | CH-00546 | Newburgh | New Windsor | Orange | 12553 | G | 4093 | Bethlehem Rd | N |  | 4.94 | [13 empty] | NM | N | ENPHASE M215 (23) | 2016-01-08 | 2016-01-22 | 10 | 2016-01-22 | [14 empty] | 2016-05-12 | 2016-05-19 |  | Y
Central Hudson |  | Hudson Solar | CH-02383 | Kingston | Stone Ridge | Ulster | 12484 | G | 3023 | High Falls | Y | CH-02383 | 6.4 | [13 empty] | NM | N | SUNPOWER X21-345-X-AC (20) | 2016-01-08 | 2016-01-21 | 9 | 2016-01-21 | [14 empty] | 2016-07-14 | 2016-07-14 |  | Y
Central Hudson |  | SolarCity | CH-05538 | Catskill | Catskill | Greene | 12414 | G | 2005 | North Catskill | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2016-01-08 | 2016-01-21 | 9 | 2016-01-21 | [14 empty] | 2016-01-26 | 2016-02-02 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-05931 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 7024 | Tinkertown | N |  | 5 | [13 empty] | NM | N | ABB PVI 5000 | 2016-01-08 | 2016-01-15 | 5 | 2016-01-15 | [14 empty] | 2016-02-18 | 2016-02-25 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | New York State Solar Farm | CH-03945 | Fishkill | Beacon | Dutchess | 12508 | G | 8087 | Tioronda | N |  | 6 | [13 empty] | NM | N | SMA AMERICA SB6000TL | 2016-01-11 | 2016-01-22 | 9 | 2016-01-22 | [14 empty] | 2016-02-26 | 2016-03-04 |  | Y
Central Hudson |  | New York State Solar Farm | CH-03958 | Newburgh | Wallkill | Ulster | 12589 | G | 4011 | West Balmville | N |  | 8.8 | [13 empty] | NM | N | SMA AMERICASB3800TL SMA AMERICASB5000TL | 2016-01-11 | 2016-01-22 | 9 | 2016-01-22 | [14 empty] | 2016-03-14 | 2016-03-21 |  | Y
Central Hudson |  | New York State Solar Farm | CH-04086 | Fishkill | Beacon | Dutchess | 12508 | G | 8017 | Forgebrook | N |  | 1.75 | [13 empty] | NM | N | SUNPOWER X20-250-BLK-B-AC (7) | 2016-02-03 | 2016-02-03 | 0 | 2016-02-03 | [14 empty] | 2016-04-15 | 2016-04-22 |  | Y
Central Hudson |  | D&M Alternative Energy | CH-00814 | Catskill | Coxsackie | Greene | 12051 | G | 1076 | Coxsackie | N |  | 4 | [13 empty] | NM | N | ENPHASE M250 (16) | 2016-01-11 | 2016-01-25 | 10 | 2016-01-25 | [14 empty] | 2016-01-29 | 2016-02-02 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-05344 | Newburgh | New Windsor | Orange | 12553 | G | 4046 | Union Ave | N |  | 3.6 | [13 empty] | NM | N | ABB PVI-3.6OUTD-S-US | 2016-01-11 | 2016-01-22 | 9 | 2016-01-22 | [14 empty] | 2016-02-24 | 2016-02-29 |  | Y
Central Hudson |  | SolarCity | CH-05347 | Newburgh | Wallkill | Ulster | 12589 | G | 5042 | East Walden | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2016-01-11 | 2016-01-22 | 9 | 2016-01-22 | [14 empty] | 2016-02-26 | 2016-03-04 |  | Y
Central Hudson |  | SolarCity | CH-05551 | Catskill | Freehold | Greene | 12431 | G | 2071 | Freehold | N |  | 16 | [13 empty] | NM | N | FRONIUS IG PLUSA 10.0 ABB PVI-6000OUTD-S-US | 2016-01-11 | 2016-01-25 | 10 | 2016-01-25 | [8 empty] | 350 | 350 |  | 2016-03-16 | 2016-03-16 | 2016-03-22 | 2016-03-22 | 2016-04-21 |  | Y
Central Hudson |  | SolarCity | CH-05656 | Kingston | Kingston | Ulster | 12401 | G | 1003 | Jansen Ave | N |  | 3 | [13 empty] | NM | N | ABB PVI-3.0OUTD-S-US | 2016-01-11 | 2016-01-25 | 10 | 2016-01-25 | [14 empty] | 2016-02-24 | 2016-03-02 |  | Y
Central Hudson |  | SolarCity | CH-06456 | Catskill | Leeds | Greene | 12451 | G | 2005 | North Catskill | N |  | 3 | [13 empty] | NM | N | ABB PVI 3.0 | 2016-01-11 | 2016-01-25 | 10 | 2016-01-25 | [14 empty] | 2016-02-11 | 2016-02-19 |  | Y
Central Hudson |  | SolarCity | CH-07018 | Newburgh | New Windsor | Orange | 12553 | G | 4043 | Union Ave | N |  | 9.6 | [13 empty] | NM | N | ABB PVI-6000OUTD-S-US ABB PVI-3.6OUTD-S-US | 2016-01-11 | 2016-01-22 | 9 | 2016-01-22 | [14 empty] | 2016-02-04 | 2016-02-04 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07240 | Kingston | Lk Katrine | Ulster | 12449 | G | 2011 | Lincoln Park | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000OUTD-S-US | 2016-01-11 | 2016-01-25 | 10 | 2016-01-25 | [14 empty] | 2016-02-17 | 2016-02-24 |  | Y
Central Hudson |  | SolarCity | CH-07254 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6044 | Spackenkill | N |  | 3 | [13 empty] | NM | N | SOLAREDGE SE3000 | 2016-01-11 | 2016-01-18 | 5 | 2016-01-18 | [14 empty] | 2016-03-01 | 2016-03-08 |  | Y
Central Hudson |  | SolarCity | CH-07539 | Poughkeepsie | Lagrangevl | Dutchess | 12540 | G | 6057 | Todd Hill | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2016-01-11 | 2016-01-18 | 5 | 2016-01-18 | [14 empty] | 2016-03-29 | 2016-04-05 |  | Y
Central Hudson |  | SolarCity | CH-07540 | Poughkeepsie | Lagrangevl | Dutchess | 12540 | G | 6052 | Todd Hill | N |  | 8 | [13 empty] | NM | N | (1) ABB PVI 3.0 (1) ABB PVI 5000 | 2016-01-11 | 2016-01-18 | 5 | 2016-01-18 | [14 empty] | 2016-03-24 | 2016-04-01 |  | Y
Central Hudson |  | Solar Generation | CH-08100 | Kingston | Woodstock | Ulster | 12498 | G | 3014 | Woodstock | N | CH-08100 | 6 | [13 empty] | NM | N | SOLAREDGE SB 6000TL | 2016-01-11 | 2016-01-25 | 10 | 2016-01-25 | [14 empty] | 2016-05-02 | 2016-05-06 |  | Y
Central Hudson |  | Solar Generation | CH-08212 | Kingston | Stone Ridge | Ulster | 12484 | G | 3023 | High Falls | N |  | 15.4 | [13 empty] | NM | N | SMA SB7700TL (2) | 2016-01-11 | 2016-01-25 | 10 | 2016-01-25 | [14 empty] | 2016-07-12 | 2016-07-12 |  | Y
Central Hudson |  | Solar Generation | CH-08260 | Newburgh | Highland | Ulster | 12528 | G | 5081 | Highland | N |  | 10 | [13 empty] | NM | N | SOLAREDGE 10,000AUS | 2016-03-01 | 2016-03-15 | 10 | 2016-03-15 | [8 empty] | 350 | 350 |  | 2016-05-16 | 2016-05-16 | 2016-05-23 | 2016-06-21 | 2016-06-27 |  | Y
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03144 | Kingston | Ellenville |  | 12428 | G | 3095 | Grimley Rd | TBD |  | 2000 | [13 empty] | CDG | N | SUNGROW SG 1000MX (2) | 2016-01-19 | 2016-01-28 | 7 | 2016-01-28 | 2016-01-19 | 2016-01-28 | 7 |  |  |  |  | 35000 | [9 empty] | W |  | CESIR determined necessary during preliminary review Section C, Step 4.
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03145 | Poughkeepsie | Pleasant Valley |  | 12569 | G | 6051 | Todd Hill | TBD |  | 2000 | [13 empty] | CDG | N | (2) SUNGROW SG 1000MX | 2016-01-21 | 2016-02-11 | 15 | 2016-02-11 | 2016-01-21 | 2016-02-11 | 15 |  |  |  |  | 32000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Apex Solar Power | CH-00678 | Kingston | Woodstock | Ulster | 12498 | G | 3013 | Woodstock | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A-US | 2016-01-12 | 2016-01-26 | 10 | 2016-01-26 | [14 empty] | 2016-05-09 | 2016-05-16 |  | Y
Central Hudson |  | Hudson Solar | CH-01263 | Catskill | Catskill | Greene | 12414 | G | 2002 | North Catskill | N | CH-01263 | 11.4 | [13 empty] | NM | N | SOLAREDGE SE-11400A-US-U | 2016-01-12 | 2016-01-26 | 10 | 2016-01-26 | [8 empty] | 350 | 350 |  | 2016-02-22 | 2016-02-22 | 2016-06-08 | 2016-06-08 | 2016-06-09 |  | Y
Central Hudson |  | PosiGen Solar | CH-02907 | Catskill | Hannacroix | Greene | 12087 | G | 2061 | Freehold | N |  | 3.87 | [13 empty] | NM | N | 18 ENPHASE M215-60-2LL-S22-IG | 2016-01-12 | 2016-01-26 | 10 | 2016-01-26 | [14 empty] | 2016-02-18 | 2016-02-18 |  | Y
Central Hudson |  | SolarCity | CH-05420 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8094 | Fishkill Plains | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2016-01-12 | 2016-01-22 | 8 | 2016-01-22 | [14 empty] | 2016-02-01 | 2016-02-01 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06269 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 7.8 | [13 empty] | NM | N | ABB PVI-4.2OUTD-S-US ABB PVI-3.6OUTD-S-US | 2016-01-12 | 2016-01-22 | 8 | 2016-01-22 | [14 empty] | 2016-02-11 | 2016-03-08 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06418 | Newburgh | Montgomery | Orange | 12549 | G | 5073 | Montgomery | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000OUTD-US-Z | 2016-01-12 | 2016-01-22 | 8 | 2016-01-22 | [14 empty] | 2016-03-31 | 2016-04-06 |  | Y
Central Hudson |  | SolarCity | CH-07326 | Newburgh | Highland | Ulster | 12528 | G | 5083 | Highland | N |  | 5 | [13 empty] | NM | N | ABB PVI-5000 OUTD-US-Z | 2016-01-12 | 2016-01-26 | 10 | 2016-01-26 | [14 empty] | 2016-03-09 | 2016-03-16 |  | Y
Central Hudson |  | SolarCity | CH-07725 | Newburgh | Wallkill | Ulster | 12589 | G | 5041 | East Walden | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE7600 | 2016-01-12 | 2016-01-22 | 8 | 2016-01-22 | [14 empty] | 2016-03-21 | 2016-03-29 |  | Y
Central Hudson |  | You Save Green | CH-09963 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8014 | Forgebrook | N |  | 7.6 | [13 empty] | NM | N | SOLAR SE7600 | 2016-01-27 | 2016-02-02 | 4 | 2016-02-02 | [14 empty] | 2016-05-20 | 2016-05-25 |  | Y
Central Hudson |  | New York State Solar Farm | CH-04099 | Fishkill | Wappingrs Falls |  | 12590 | G | 8094 | Fishkill Plains | TBD |  | 14.8 | [13 empty] | NM | N | SMA AMERICA SB6000TL SMA AMERICA SB3800TL SMA AMERICA SB5000TL | 2016-01-20 | 2016-01-29 | 7 | 2016-01-29 | [17 empty] | W
Central Hudson |  | Apex Solar Power | CH-00715 | Poughkeepsie | Staatsburg |  | 12580 | G | 7041 | Staatsburg | TBD |  | 6 | [13 empty] | NM | N |  | 2015-11-11 | [17 empty] | 2015-12-21 |  |  | W
Central Hudson |  | SolarCity | CH-06858 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8092 | Fishkill Plains | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2016-01-13 | 2016-01-22 | 7 | 2016-01-22 | [14 empty] | 2016-03-29 | 2016-04-05 |  | Y
Central Hudson |  | SolarCity | CH-07897 | Fishkill | Cold Spg |  | 10516 | G | 8063 | Merritt Park | TBD |  | 3 | [13 empty] | NM | N | ABB PVI-3.0OUTD-S-US | 2016-01-22 | 2016-01-29 | 5 | 2016-01-29 | [17 empty] | W
Central Hudson |  | Infinity Solar Systems | CH-03450 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 7024 | Tinkertown | N |  | 17.7 | [13 empty] | NM | N | (1) SMA AMERICA SB7700TL US (2) SMA AMERICA SB5000TL US | 2016-01-14 | 2016-01-28 | 10 | 2016-01-28 | [14 empty] | 2016-02-17 | 2016-02-24 |  | Y
Central Hudson |  | NRG Home Solar | CH-00560 | Fishkill | Cold Spg | Putnam | 10516 | G | 8087 | Tioronda | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE 7600 | 2016-01-21 | 2016-01-29 | 6 | 2016-01-29 | [14 empty] | 2016-08-19 | 2016-08-19 |  | Y
Central Hudson |  | SolarCity | CH-05537 | Catskill | Catskill | Greene | 12414 | G | 2005 | North Catskill | N |  | 8.4 | [13 empty] | NM | N | 2 ABB PVI-4.2 OUTD-S-US | 2016-01-14 | 2016-01-28 | 10 | 2016-01-28 | [14 empty] | 2016-02-22 | 2016-02-29 |  | Y
Central Hudson |  | SolarCity | CH-06490 | Kingston | Tillson | Ulster | 12486 | G | 3021 | High Falls | N |  | 10.2 | [13 empty] | NM | N | ABB PVI-6000 OUTD-S-US ABB PVI-4.2 OUTD-S-US | 2016-01-14 | 2016-01-28 | 10 | 2016-01-28 | [14 empty] | 2016-02-16 | 2016-02-23 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08661 | Kingston | Ulster Pk | Ulster | 12487 | G | 1014 | Boulevard | N |  | 4.085 | [13 empty] | NM | N | 19 ENPHASE M215 602LLS2XZC | 2016-01-14 | 2016-01-28 | 10 | 2016-01-28 | [14 empty] | 2016-07-13 | 2016-07-19 |  | Y
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03146 | Kingston | Saugerties |  | 12477 | G | 3002 | Saugerties | TBD |  | 1980 | [13 empty] | CDG | Y | (44) Huawei SUN2000-45KTL-US | 2016-01-21 | 2016-01-28 | 5 | 2016-01-28 | 2016-01-21 | 2016-01-28 | 5 | 2016-03-18 | 2016-05-03 | 2016-07-28 | 60 | 15000 | 1291750 |  | 2017-11-08 | [6 empty] | W |  | CESIR for 3 projects combined with an aggregate CESIR Cost to Customer of $45,000 & Total Estimated Upgrade Costs of $5,398,663.
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03147 | Newburgh | New Paltz |  | 12561 | G | 5011 | Modena | TBD |  | 1980 | [13 empty] | CDG | N | (44) Huawei SUN2000-45KTL-US | 2016-01-29 | 2016-02-22 | 15 | 2016-02-22 | 2016-01-29 | 2016-02-22 | 15 | 2016-04-21 | 2016-05-03 | 2016-07-28 | 60 | 32000 | [9 empty] | W
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03148 | Kingston | Neversink |  | 12765 | G | 3091 | Neversink | TBD |  | 2000 | [13 empty] | CDG | N | SUNGROW SG 1000MX (2) | 2016-01-21 | 2016-02-11 | 15 | 2016-02-11 | 2016-01-21 | 2016-02-11 | 15 |  |  |  |  | 32000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03149 | Newburgh | New Paltz |  | 12561 | G | 5012 | Modena | TBD |  | 1980 | [13 empty] | CDG | N | 44 Huawei Sun2000-45kTL | 2016-01-21 | 2016-02-11 | 15 | 2016-02-11 | 2016-01-21 | 2016-02-11 | 15 | 2017-01-23 | 2017-02-06 | 2017-03-09 | 22 | 12500 | [8 empty] | 2017-03-09 | W |  | CESIR for 2 projects combined with an aggregate CESIR Cost to Customer of $25,000. 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03150 | Poughkeepsie | Hyde Park |  | 12538 | G | 7041 | Staatsburg | TBD |  | 2000 | [13 empty] | CDG | N | SUNGROW SG 1000MX (2) | 2016-01-21 | 2016-02-11 | 15 | 2016-02-11 | 2016-01-21 | 2016-02-11 | 15 |  |  |  |  | 32000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Lighthouse Solar | CH-03600 | Kingston | Accord | Ulster | 12404 | G | 3024 | High Falls | N |  | 10 | [13 empty] | NM | N | SOLAREDGE 10000A-US | 2016-01-15 | 2016-01-29 | 10 | 2016-01-29 | [14 empty] | 2016-02-12 | 2016-02-22 |  | Y
Central Hudson |  | NRG Home Solar | CH-00554 | Newburgh | Newburgh | Orange | 12550 | G | 4012 | West Balmville | N | CH-00554 | 4.51 | [13 empty] | NM | N | ENPHASE M215 (21) | 2016-01-15 | 2016-01-22 | 5 | 2016-01-22 | [14 empty] | 2016-05-05 | 2016-05-10 |  | Y
Central Hudson |  | Direct Energy Solar | CH-01058 | Newburgh | Highland | Ulster | 12528 | G | 5081 | Highland | N |  | 7.31 | [13 empty] | NM | N | (34) ENPHASE M215 60-2LL-S22 | 2016-01-15 | 2016-01-22 | 5 | 2016-01-22 | [14 empty] | 2016-05-27 | 2016-06-06 |  | Y
Central Hudson |  | Monolith Solar Associates LLC | CH-02648 | Catskill | Hannacroix |  | 12087 | G | 1083 | New Baltimore | TBD |  | 5 | [13 empty] | NM | N | SOLAREDGE SB5000A-US | 2016-01-15 | 2016-01-29 | 10 | 2016-01-29 | [17 empty] | W
Central Hudson |  | SolarCity | CH-05032 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7062 | Milan | N |  | 6 | [13 empty] | NM | N | ABB PVI 6000 | 2016-01-15 | 2016-01-22 | 5 | 2016-01-22 | [14 empty] | 2016-03-31 | 2016-04-07 |  | Y
Central Hudson |  | SolarCity | CH-05234 | Newburgh | New Paltz | Ulster | 12561 | G | 5031 | Galeville | N |  | 9 | [13 empty] | NM | N | ABB PVI6000 ABB PVI3.0 | 2016-01-15 | 2016-01-22 | 5 | 2016-01-22 | [14 empty] | 2016-02-24 | 2016-02-29 |  | Y
Central Hudson |  | SolarCity | CH-06110 | Fishkill | Fishkill | Dutchess | 12524 | G | 8055 | North Chelsea | N |  | 10.2 | [13 empty] | NM | N | ABB PVI 4.2 ABB PVI6000 | 2016-03-16 | 2016-03-31 | 10 | 2016-03-31 | [14 empty] | 2016-04-20 | 2016-04-25 |  | Y
Central Hudson |  | Kasselman Solar | CH-03534 | Catskill | Surprise | Greene | 12176 | G | 2061 | Freehold | N |  | 15 | [13 empty] | NM | N | ENPHASE M250 (60) | 2016-01-26 | 2016-02-09 | 10 | 2016-02-09 | [8 empty] | 350 | 350 |  | 2016-03-04 | 2016-03-04 | 2016-03-11 | 2016-06-09 | 2016-06-15 |  | Y
Central Hudson |  | Lotus Energy Inc. | CH-03884 | Kingston | Saugerties | Ulster | 12477 | G | 3003 | Saugerties | N |  | 7 | [13 empty] | NM | N | SMA SB7000TLUS-22 | 2016-02-10 | 2016-02-10 | 0 | 2016-02-10 | [14 empty] | 2016-03-21 | 2016-03-29 |  | Y
Central Hudson |  | NRG Home Solar | CH-00481 | Kingston | Saugerties | Ulster | 12477 | G | 3004 | Saugerties | N |  | 5.8 | [13 empty] | NM | N | 27 ENPHASE M215 | 2016-01-18 | 2016-02-01 | 10 | 2016-02-01 | [14 empty] | 2016-05-17 | 2016-05-24 |  | Y
Central Hudson |  | NRG Home Solar | CH-04180 | Newburgh | Wallkill | Ulster | 12589 | G | 4011 | West Balmville | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE7600A | 2016-01-18 | 2016-01-29 | 9 | 2016-01-29 | [14 empty] | 2016-04-15 | 2016-04-19 |  | Y
Central Hudson |  | NRG Home Solar | CH-04438 | Fishkill | Beacon | Dutchess | 12508 | G | 8087 | Tioronda | N |  | 3.65 | [13 empty] | NM | N | ENPHASE M215 (17) | 2016-01-25 | 2016-01-29 | 4 | 2016-01-29 | [14 empty] | 2016-03-31 | 2016-04-06 |  | Y
Central Hudson |  | NRG Home Solar | CH-00529 | Kingston | Saugerties | Ulster | 12477 | G | 3004 | Saugerties | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE7600A | 2016-01-18 | 2016-02-01 | 10 | 2016-02-01 | [14 empty] | 2016-04-29 | 2016-05-06 |  | Y
Central Hudson |  | NRG Home Solar | CH-00530 | Kingston | Saugerties | Ulster | 12477 | G | 2015 | Lincoln Park | N |  | 5.37 | [13 empty] | NM | N | 25 ENPHASE M215 | 2016-01-18 | 2016-02-01 | 10 | 2016-02-01 | [14 empty] | 2016-05-11 | 2016-05-12 |  | Y
Central Hudson |  | NRG Home Solar | CH-04770 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8096 | Fishkill Plains | N |  | 10 | [13 empty] | NM | N | SOLAR EDGE SE10000 | 2016-01-18 | 2016-01-29 | 9 | 2016-01-29 | [14 empty] | 2016-06-01 | 2016-06-03 |  | Y
Central Hudson |  | SolarCity | CH-05494 | Catskill | Hunter | Greene | 12442 | G | 2385 | Lawrenceville | N |  | 4.2 | [13 empty] | NM | N | ABB PVI 4.2 | 2016-01-18 | 2016-02-01 | 10 | 2016-02-01 | [14 empty] | 2016-02-04 | 2016-03-03 |  | Y
Central Hudson |  | SolarCity | CH-06034 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8052 | North Chelsea | N |  | 8.6 | [13 empty] | NM | N | ABB PVI-5000OUTD-S-US ABB PVI-3.6OUTD-S-US | 2016-01-18 | 2016-01-29 | 9 | 2016-01-29 | [14 empty] | 2016-04-12 | 2016-04-14 |  | Y
Central Hudson |  | SolarCity | CH-06398 | Newburgh | Cornwall | Orange | 12518 | G | 4094 | Bethlehem Rd | N |  | 3.6 | [13 empty] | NM | N | ABB PVI-3.6OUTD-S-US | 2016-01-18 | 2016-01-29 | 9 | 2016-01-29 | [14 empty] | 2016-02-11 | 2016-02-19 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06990 | Newburgh | Newburgh | Orange | 12550 | G | 4024 | Coldenham | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2016-03-16 | 2016-03-30 | 9 | 2016-03-30 | [14 empty] | 2016-03-31 | 2016-04-06 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07924 | Catskill | Cairo |  | 12413 | G | 2041 | South Cairo | TBD |  | 1992 | [13 empty] | CDG | N | FRONIUS PRIMO 24.0 (83) | 2016-05-05 | 2016-05-05 | 0 | 2016-05-05 | 2016-05-05 | 2016-05-26 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Infinity Solar Systems | CH-03455 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8043 | Myers Corners | N |  | 3.8 | [13 empty] | NM | N | SMA SB 3800 TL US | 2016-01-27 | 2016-01-29 | 2 | 2016-01-29 | [14 empty] | 2016-03-01 | 2016-03-08 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-03498 | Newburgh | Maybrook | Orange | 12543 | G | 4026 | Coldenham | N |  | 3.8 | [13 empty] | NM | N | SMA AMERICA SB3800T | 2016-02-01 | 2016-02-01 | 0 | 2016-02-01 | [14 empty] | 2016-03-11 | 2016-03-18 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03822 | Kingston | Stone Ridge | Ulster | 12484 | G | 3023 | High Falls | N | CH-03736 | 2 | [13 empty] | NM | N | ABB 2.0 OUTD-US | 2016-01-19 | 2016-02-02 | 10 | 2016-02-02 | [14 empty] | 2016-04-07 | 2016-04-14 |  | Y
Central Hudson |  | NRG Home Solar | CH-00497 | Catskill | Catskill | Greene | 12414 | G | 2004 | North Catskill | N |  | 4.085 | [13 empty] | NM | N | 19 ENPHASE M215-60-2LL-S22-IG | 2016-01-20 | 2016-02-03 | 10 | 2016-02-03 | [14 empty] | 2016-05-04 | 2016-05-11 |  | Y
Central Hudson |  | NRG Home Solar | CH-04845 | Newburgh | Cornwall |  | 12518 | G | 4041 | Union Ave | TBD |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A-US | 2016-01-20 | 2016-01-29 | 7 | 2016-01-29 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | Hudson Solar | CH-02166 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8045 | Myers Corners | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE-6000A-US-U | 2016-01-20 | 2016-01-29 | 7 | 2016-01-29 | [14 empty] | 2016-05-10 | 2016-05-16 |  | Y
Central Hudson |  | Hudson Solar | CH-02435 | Kingston | High Fls | Ulster | 12440 | G | 3024 | High Falls | N | CH-01282 | 3 | [13 empty] | NM | N | SMA AMERICA SB3000 TL-US-22 | 2016-01-20 | 2016-02-03 | 10 | 2016-02-03 | [14 empty] | 2016-03-23 | 2016-03-31 |  | Y
Central Hudson |  | SolarCity | CH-07064 | Newburgh | Newburgh | Orange | 12550 | G | 4011 | West Balmville | N |  | 3.6 | [13 empty] | NM | N | ABB PVI 3.6 | 2016-01-20 | 2016-01-29 | 7 | 2016-01-29 | [14 empty] | 2016-03-03 | 2016-03-10 |  | Y
Central Hudson |  | Solar Generation | CH-08145 | Kingston | Accord | Ulster | 12404 | G | 3024 | High Falls | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE 7600 A | 2016-01-20 | 2016-02-03 | 10 | 2016-02-03 | [14 empty] | 2016-05-27 | 2016-05-31 |  | Y
Central Hudson |  | Solar Generation | CH-08179 | Kingston | Willow | Ulster | 12495 | G | 3012 | Woodstock | N |  | 7.7 | [13 empty] | NM | N | SMA SB 7700TL | 2016-01-20 | 2016-02-03 | 10 | 2016-02-03 | [14 empty] | 2016-03-10 | 2016-03-17 |  | Y |  | Customer already had net meter prior to application.
Central Hudson |  | Trinity Solar | CH-08400 | Kingston | Tillson |  | 12486 | G | 3021 | High Falls | TBD |  | 3 | [13 empty] | NM | N | SOLAREDGE SE3000A-US | 2016-01-20 | 2016-02-03 | 10 | 2016-02-03 | [17 empty] | W
Central Hudson |  | Sungevity Inc | CH-09359 | Fishkill | Beacon | Dutchess | 12508 | G | 8017 | Forgebrook | N |  | 3 | [13 empty] | NM | N | ABB PVI-3.0-OUTD-S-US-A | 2016-01-28 | 2016-01-29 | 1 | 2016-01-29 | [14 empty] | 2016-04-11 | 2016-04-13 |  | Y
Central Hudson |  | Xzerta Energy Group, LLC | CH-09951 | Catskill | Athens |  | 12015 | G | 2002 | North Catskill | TBD |  | 2000 | [13 empty] | CDG | N | POWER ELECTRONICS FS751CU POWER ELECTRONICS FS1250CU | 2016-02-26 | 2016-03-18 | 15 | 2016-03-18 | 2016-02-26 | 2016-03-18 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03151 | Kingston | Napanoch |  | 12458 | G | 3072 | Honk Falls | TBD |  | 1980 | [13 empty] | CDG | N | (44) Huawei SUN2000-45KTL-US | 2016-01-27 | 2016-02-18 | 15 | 2016-02-18 | 2016-01-27 | 2016-02-18 | 15 | 2016-03-30 | 2016-05-03 | 2016-07-28 | 60 | 19191.61 | 689000 | 24223.4 | 2017-06-23 | 2017-08-29 | 2017-08-29 |  |  |  | 2019-04-04 | W
Central Hudson |  | Infinity Solar Systems | CH-03483 | Fishkill | Fishkill | Dutchess | 12524 | G | 8065 | Merritt Park | N |  | 7.6 | [13 empty] | NM | N | SMA 3.8TL (2) | 2016-01-21 | 2016-01-29 | 6 | 2016-01-29 | [14 empty] | 2016-02-16 | 2016-02-23 |  | Y
Central Hudson |  | NRG Home Solar | CH-04520 | Catskill | Coxsackie | Greene | 12051 | G | 1076 | Coxsackie | N |  | 6 | [13 empty] | NM | N | SOLAR EDGE SE6000A | 2016-01-21 | 2016-02-04 | 10 | 2016-02-04 | [14 empty] | 2016-03-29 | 2016-04-05 |  | Y
Central Hudson |  | NRG Home Solar | CH-00533 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 6075 | East Park | N |  | 4.3 | [13 empty] | NM | N | (20) ENPHASE M215 | 2016-01-28 | 2016-02-04 | 5 | 2016-02-04 | [14 empty] | 2016-05-17 | 2016-05-24 |  | Y
Central Hudson |  | Hudson Solar | CH-01257 | Catskill | Catskill | Greene | 12414 | G | 2004 | North Catskill | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE-7600A-US-U | 2016-01-21 | 2016-02-04 | 10 | 2016-02-04 | [14 empty] | 2016-03-14 | 2016-03-21 |  | Y
Central Hudson |  | Hudson Solar | CH-01906 | Poughkeepsie | Stanfordvl | Dutchess | 12581 | G | 7072 | Stanfordville | N | CH-01906 | 11.4 | [13 empty] | NM | N | SOLAREDGE SE-11400A-US-U | 2016-01-21 | 2016-02-04 | 10 | 2016-02-04 | [8 empty] | 350 | 350 |  | 2016-04-22 | 2016-04-22 | 2016-05-03 | 2016-05-03 | 2016-05-09 |  | Y
Central Hudson |  | Hudson Solar | CH-02316 | Newburgh | New Paltz | Ulster | 12561 | G | 5031 | Galeville | N |  | 10 | [13 empty] | NM | N | SOLAREDGE SE-10000A-US-U | 2016-01-21 | 2016-02-04 | 10 | 2016-02-04 | [8 empty] | 350 | 350 |  | 2016-02-19 | 2016-02-19 | 2016-03-09 | 2016-07-11 | 2016-07-14 |  | Y
Central Hudson |  | Hudson Solar | CH-02349 | Poughkeepsie | Rhinebeck |  | 12572 | G | 7052 | Rhinebeck | TBD |  | 10 | [13 empty] | NM | N | SOLAREDGE SE-10000 A-US-U | 2016-01-21 | 2016-01-28 | 5 | 2016-01-28 | [17 empty] | W
Central Hudson |  | Hudson Solar | CH-02445 | Kingston | Saugerties | Ulster | 12477 | G | 2016 | Lincoln Park | N | CH-02056 | 3 | [13 empty] | NM | N | SMA AMERICA SB3000 TL-US-22 | 2016-01-21 | 2016-02-04 | 10 | 2016-02-04 | [14 empty] | 2016-04-13 | 2016-04-19 |  | Y
Central Hudson |  | SolarCity | CH-04996 | Kingston | Kingston | Ulster | 12401 | G | 111 | South Wall St | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2016-01-21 | 2016-02-04 | 10 | 2016-02-04 | [14 empty] | 2016-02-11 | 2016-02-19 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-05504 | Catskill | Catskill | Greene | 12414 | G | 2042 | South Cairo | N |  | 8.2 | [13 empty] | NM | N | FRONIUS PRIMO 8.2 | 2016-01-21 | 2016-02-04 | 10 | 2016-02-04 | [14 empty] | 2016-02-09 | 2016-02-16 |  | Y
Central Hudson |  | Sungevity Inc | CH-09238 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6053 | Todd Hill | N |  | 6 | [13 empty] | NM | N | (2) ABB PVI-3.0-OUTD-US-A | 2016-01-21 | 2016-01-28 | 5 | 2016-01-28 | [14 empty] | 2016-03-17 | 2016-03-23 |  | Y
Central Hudson |  | Sungevity Inc | CH-09255 | Catskill | Palenvl | Greene | 12463 | G | 2001 | North Catskill | N |  | 6.8 | [13 empty] | NM | N | ABB PVI-3.0-OUTD-S-US-A ABB PVI-3.8-OUTD-S-US-A | 2016-01-21 | 2016-02-04 | 10 | 2016-02-04 | [14 empty] | 2016-04-06 | 2016-04-11 |  | Y
Central Hudson |  | Sungevity Inc | CH-09608 | Newburgh | New Paltz | Ulster | 12561 | G | 5031 | Galeville | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000-OUTD-US-A | 2016-01-28 | 2016-01-29 | 1 | 2016-01-29 | [14 empty] | 2016-06-02 | 2016-06-06 |  | Y
Central Hudson |  | Sungevity Inc | CH-09620 | Kingston | Boiceville |  | 12412 | G | 3011 | Woodstock | TBD |  | 4.2 | [13 empty] | NM | N | ABB PVI-4.2-OUTD-S-US-A | 2016-01-21 | 2016-02-04 | 10 | 2016-02-04 | [17 empty] | W
Central Hudson |  | NRG Home Solar | CH-00517 | Newburgh | Wallkill | Ulster | 12589 | G | 4011 | West Balmville | N |  | 10 | [13 empty] | NM | N | SOLAREDGE SE10000A-US | 2016-02-11 | 2016-02-26 | 10 | 2016-02-26 | [14 empty] | 2016-05-17 | 2016-05-24 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00882 | Newburgh | Wallkill |  | 12589 | G | 4011 | West Balmville | N |  | 7.5 | [13 empty] | NM | N | ENPHASE 250 (30) | 2016-01-22 | 2016-01-29 | 5 | 2016-01-29 | [17 empty] | W
Central Hudson |  | Hudson Solar | CH-01584 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7052 | Rhinebeck | N | CH-01584 | 45.6 | [13 empty] | NM | Y | (6) SOLAREDGE SE-7600A-US-U | 2016-04-05 | 2016-04-19 | 10 | 2016-04-19 | [8 empty] | 2725 | 1692.99 |  | 2016-05-20 | 2016-05-20 | 2016-09-02 | 2016-09-15 | 2016-09-19 |  | Y | Y
Central Hudson |  | SolarCity | CH-07021 | Newburgh | New Windsor | Orange | 12553 | G | 4054 | Union Ave | N |  | 6 | [13 empty] | NM | N | ABB PVI6000 | 2016-01-22 | 2016-01-29 | 5 | 2016-01-29 | [14 empty] | 2016-03-29 | 2016-04-05 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08651 | Catskill | Athens | Greene | 12015 | G | 2002 | North Catskill | N | CH-08651 | 2.15 | [13 empty] | NM | N | 10 ENPHASE M215 602LLS2XZC | 2016-01-22 | 2016-02-05 | 10 | 2016-02-05 | [8 empty] | 350 | 350 |  | 2016-12-14 | 2016-12-14 | 2016-12-21 | 2016-09-16 | 2016-09-19 |  | Y
Central Hudson |  | Sungevity Inc | CH-09316 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6065 | Inwood Ave | N |  | 3.8 | [13 empty] | NM | N | ABB PVI-3.8-OUTD-S-US-A | 2016-01-22 | 2016-02-04 | 9 | 2016-02-04 | [14 empty] | 2016-04-05 | 2016-04-08 |  | Y
Central Hudson |  | RGS Energy | CH-03056 | Fishkill | Beacon | Dutchess | 12508 | G | 8087 | Tioronda | N |  | 5 | [13 empty] | NM | N | ENPHASE M250-60-2LL-S22 (20) | 2016-01-25 | 2016-01-29 | 4 | 2016-01-29 | [14 empty] | 2016-12-02 | 2016-12-02 |  | Y
Central Hudson |  | Kasselman Solar | CH-03536 | Catskill | Greenville |  | 12083 | G | 1091 | Westerlo | TBD |  | 14 | [13 empty] | NM | N | 56 ENPHASE M250-US | 2016-01-25 | 2016-02-10 | 12 | 2016-02-10 | [17 empty] | W
Central Hudson |  | Lotus Energy Inc. | CH-03845 | Kingston | Bearsvl | Ulster | 12409 | G | 3012 | Woodstock | N |  | 7.7 | [13 empty] | NM | N | SMA SB7700 TL-US-22 | 2016-01-25 | 2016-02-10 | 12 | 2016-02-10 | [14 empty] | 2016-02-24 | 2016-03-02 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | New York State Solar Farm | CH-03937 | Newburgh | Marlboro | Ulster | 12542 | G | 5004 | Marlboro | N |  | 12 | [13 empty] | NM | N | SMA AMERICA SB6000TL (2) | 2016-01-25 | 2016-02-08 | 10 | 2016-02-08 | [8 empty] | 350 | 350 |  | 2016-02-19 | 2016-02-19 | 2016-03-03 | 2016-03-03 | 2016-03-10 |  | Y
Central Hudson |  | New York State Solar Farm | CH-03954 | Fishkill | Beacon | Dutchess | 12508 | G | 8017 | Forgebrook | N |  | 5 | [13 empty] | NM | N | SMA AMERICA SB5000TL | 2016-01-25 | 2016-01-29 | 4 | 2016-01-29 | [14 empty] | 2016-03-02 | 2016-03-09 |  | Y
Central Hudson |  | Apex Solar Power | CH-00711 | Kingston | Kingston |  | 12401 | G | 1012 | Boulevard | TBD |  | 3.44 | [13 empty] | NM | N | 16 ENPHASE M215 US | 2016-01-25 | 2016-02-10 | 12 | 2016-02-10 | [17 empty] | W
Central Hudson |  | SolarCity | CH-05582 | Catskill | Coxsackie | Greene | 12051 | G | 1076 | Coxsackie | N |  | 5 | [13 empty] | NM | N | ABB PVI-5000OUTD-US | 2016-01-25 | 2016-02-10 | 12 | 2016-02-10 | [14 empty] | 2016-03-29 | 2016-04-05 |  | Y
Central Hudson |  | SolarCity | CH-05679 | Kingston | W Hurley | Ulster | 12491 | G | 3013 | Woodstock | N |  | 3 | [13 empty] | NM | N | ABB PVI 3.0 | 2016-01-25 | 2016-02-10 | 12 | 2016-02-10 | [14 empty] | 2016-04-12 | 2016-04-15 |  | Y
Central Hudson |  | SolarCity | CH-05938 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6093 | Manchester | N |  | 3 | [13 empty] | NM | N | ABB PVI-3.0 OUTD-S-US | 2016-01-25 | 2016-02-01 | 5 | 2016-02-01 | [14 empty] | 2016-03-29 | 2016-04-05 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07394 | Fishkill | Beacon | Dutchess | 12508 | G | 8085 | Tioronda | N |  | 3.6 | [13 empty] | NM | N | ABB PVI-3.6OUTD-S-US | 2016-01-25 | 2016-01-29 | 4 | 2016-01-29 | [14 empty] | 2016-03-07 | 2016-03-14 |  | Y
Central Hudson |  | SolarCity | CH-07481 | Newburgh | New Windsor | Orange | 12553 | G | 4094 | Bethlehem Rd | N |  | 6.6 | [13 empty] | NM | N | ABB PVI-3.6OUTD-S-US ABB PVI-3.0OUTD-S-US | 2016-01-25 | 2016-01-29 | 4 | 2016-01-29 | [14 empty] | 2016-03-21 | 2016-03-29 |  | Y
Central Hudson |  | SolarCity | CH-07903 | Newburgh | Walden |  | 12586 | G | 5041 | East Walden | TBD |  | 8.2 | [13 empty] | NM | N | FRONIUS PRIMO 8.2 | 2016-01-25 | 2016-01-29 | 4 | 2016-01-29 | [17 empty] | W
Central Hudson |  | Sungevity Inc | CH-09481 | Newburgh | New Windsor | Orange | 12553 | G | 4044 | Union Ave | N |  | 3 | [13 empty] | NM | N | ABB PVI-3.0-OUTD-S-US-A | 2016-01-25 | 2016-01-29 | 4 | 2016-01-29 | [14 empty] | 2016-05-17 | 2016-05-24 |  | Y
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03152 | Poughkeepsie | Pleasant Valley |  | 12569 | G | 6057 | Todd Hill | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-03-30 | 2016-04-20 | 15 | 2016-04-20 | 2016-03-30 | 2016-04-20 | 15 |  |  |  |  | 35000 | [9 empty] | W
Central Hudson |  | Apex Solar Power | CH-00708 | Kingston | Lk Hill | Ulster | 12448 | G | 3012 | Woodstock | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE7600AUS | 2016-01-26 | 2016-02-09 | 10 | 2016-02-09 | [14 empty] | 2016-05-16 | 2016-05-23 |  | Y
Central Hudson |  | Monolith Solar Associates LLC | CH-02647 | Catskill | Hannacroix | Greene | 12087 | G | 1083 | New Baltimore | N |  | 8.8 | [13 empty] | NM | N | SOLAR EDGE SE5000A-US SOLAR EDGE SE3800A-US | 2016-01-26 | 2016-02-09 | 10 | 2016-02-09 | [14 empty] | 2016-05-16 | 2016-05-23 |  | Y
Central Hudson |  | Monolith Solar Associates LLC | CH-02693 | Catskill | Coxsackie |  | 12051 | G | 1076 | Coxsackie | TBD |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000AUS | 2016-01-26 | 2016-02-09 | 10 | 2016-02-09 | [17 empty] | W
Central Hudson |  | SolarCity | CH-06658 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6002 | Reynolds Hill | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000 OUTD-US-Z | 2016-01-26 | 2016-02-04 | 7 | 2016-02-04 | [14 empty] | 2016-02-11 | 2016-02-19 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06883 | Fishkill | Fishkill | Dutchess | 12524 | G | 8014 | Forgebrook | N |  | 7.8 | [13 empty] | NM | N | ABB PVI-4.2OUTD-S-US ABB PVI-3.6OUTD-S-US | 2016-01-26 | 2016-01-29 | 3 | 2016-01-29 | [14 empty] | 2016-03-31 | 2016-04-07 |  | Y
Central Hudson |  | Sunrun Inc. | CH-08353 | Newburgh | New Windsor | Orange | 12553 | G | 4095 | Bethlehem Rd | N |  | 6 | [13 empty] | NM | N | ENPHASEM250-60-2LL-S2X (24) | 2016-02-01 | 2016-02-01 | 0 | 2016-02-01 | [14 empty] | 2016-07-26 | 2016-07-28 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08630 | Kingston | Kingston | Ulster | 12401 | G | 2093 | Hurley Ave | N |  | 4.94 | [13 empty] | NM | N | ENPHASE M215602LLS2XZC (23) | 2016-01-26 | 2016-02-09 | 10 | 2016-02-09 | [14 empty] | 2016-05-23 | 2016-05-27 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08671 | Kingston | Woodstock |  | 12498 | G | 3014 | Woodstock | TBD |  | 4.94 | [13 empty] | NM | N | ENPHASE M215 (23) | 2016-01-26 | 2016-02-09 | 10 | 2016-02-09 | [17 empty] | W
Central Hudson |  | Lighthouse Solar | CH-03597 | Newburgh | Mountainvl | Orange | 10953 | G | 4095 | Bethlehem Rd | N |  | 30.8 | [13 empty] | RNM | N | SMA 7700TL-US (4) | 2016-01-27 | 2016-02-10 | 10 | 2016-02-10 | [8 empty] | 2750 | 1405.26 |  | 2016-02-19 | 2016-02-19 | 2016-03-03 | 2016-03-16 | 2016-03-23 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03602 | Kingston | Cragsmoor | Orange | 12566 | G | 3078 | Greenfield Rd | N |  | 5 | [13 empty] | NM | N | SOLAREDGE 5000A-US | 2016-01-27 | 2016-02-10 | 10 | 2016-02-10 | [14 empty] | 2016-04-07 | 2016-04-14 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03753 | Newburgh | New Paltz | Ulster | 12561 | G | 5011 | Modena | N |  | 10 | [13 empty] | NM | N | SOLAREDGE 10000A-US | 2016-01-27 | 2016-02-10 | 10 | 2016-02-10 | [8 empty] | 350 | 350 |  | 2016-02-26 | 2016-02-26 | 2016-03-07 | 2016-04-29 | 2016-05-05 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03784 | Newburgh | New Paltz | Ulster | 12561 | G | 5031 | Galeville | N |  | 10 | [13 empty] | NM | N | SOLAREDGE 10000A-US | 2016-01-27 | 2016-02-10 | 10 | 2016-02-10 | [8 empty] | 350 | 350 |  | 2016-05-12 | 2016-05-12 | 2016-05-23 | 2016-12-21 | 2016-12-21 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03839 | Fishkill | New Hamburg |  | 12590 | G | 8023 | Knapps Corners | TBD |  | 6 | [13 empty] | NM | N | SOLAREDGE 6000A-US | 2016-02-01 | 2016-02-01 | 0 | 2016-02-01 | [17 empty] | W
Central Hudson |  | NRG Home Solar | CH-04594 | Fishkill | Hopewell Jct |  | 12533 | G | 8096 | Fishkill Plains | TBD |  | 10 | [13 empty] | NM | N | SOLAREDGE SE10000A-US | 2016-01-27 | 2016-01-29 | 2 | 2016-01-29 | [17 empty] | W
Central Hudson |  | NRG Home Solar | CH-04746 | Newburgh | Milton | Ulster | 12547 | G | 5002 | Marlboro | N |  | 4.3 | [13 empty] | NM | N | ENPHASE M215-60-2LL-S22-IG (20) | 2016-01-27 | 2016-01-29 | 2 | 2016-01-29 | [14 empty] | 2016-04-15 | 2016-04-20 |  | Y
Central Hudson |  | Paradise Energy Solutions LLC | CH-02842 | Fishkill | Stormvl | Dutchess | 12582 | G | 8071 | Shenandoah | N |  | 7.5 | [13 empty] | NM | N | ENPHASE M250 (30) | 2016-02-04 | 2016-02-04 | 0 | 2016-02-04 | [14 empty] | 2016-04-21 | 2016-04-25 |  | Y
Central Hudson |  | SolarCity | CH-05813 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6003 | Reynolds Hill | N |  | 6 | [13 empty] | NM | N | ABB PVI 6.0 | 2016-01-27 | 2016-02-03 | 5 | 2016-02-03 | [14 empty] | 2016-03-08 | 2016-03-15 |  | Y
Central Hudson |  | SolarCity | CH-06254 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2016-01-27 | 2016-01-29 | 2 | 2016-01-29 | [14 empty] | 2016-06-03 | 2016-06-07 |  | Y
Central Hudson |  | SolarCity | CH-06541 | Kingston | Kingston | Ulster | 12401 | G | 2093 | Hurley Ave | N |  | 3 | [13 empty] | NM | N | ABB PVI 3.0 | 2016-01-27 | 2016-02-10 | 10 | 2016-02-10 | [14 empty] | 2016-03-29 | 2016-04-05 |  | Y
Central Hudson |  | Solar Generation | CH-08110 | Kingston | Glenford | Ulster | 12433 | G | 3013 | Woodstock | Y | CH-08110 | 7.6 | [13 empty] | NM | N | SOLAREDGE 7600A-US | 2016-01-27 | 2016-02-10 | 10 | 2016-02-10 | [14 empty] | 2016-03-31 | 2016-04-07 |  | Y
Central Hudson |  | Solar Generation | CH-08271 | Kingston | Shokan | Ulster | 12481 | G | 3011 | Woodstock | N |  | 10 | [13 empty] | NM | N | SOLAREDGE 10000A-US | 2016-01-27 | 2016-02-10 | 10 | 2016-02-10 | [14 empty] | 2016-06-09 | 2016-06-15 |  | Y
Central Hudson |  | Sol Providers | CH-08943 | Kingston | Rosendale | Ulster | 12472 | G | 3022 | High Falls | N |  | 5 | [13 empty] | NM | N | SMA 5000 TL | 2016-01-27 | 2016-02-10 | 10 | 2016-02-10 | [14 empty] | 2016-02-24 | 2016-03-02 |  | Y
Central Hudson |  | Sungevity Inc | CH-09444 | Newburgh | Highland | Ulster | 12528 | G | 5082 | Highland | N |  | 7.6 | [13 empty] | NM | N | (2) ABB PVI-3.8-OUTD-S-US-A | 2016-01-27 | 2016-02-03 | 5 | 2016-02-03 | [14 empty] | 2016-04-29 | 2016-05-06 |  | Y
Central Hudson |  | Sungevity Inc | CH-09492 | Newburgh | Marlboro | Ulster | 12542 | G | 5002 | Marlboro | N |  | 9.8 | [13 empty] | NM | N | ABB PVI-3.8-OUTD-S-US-A ABB PVI-6000-OUTD-US-A | 2016-02-02 | 2016-02-02 | 0 | 2016-02-02 | [14 empty] | 2016-03-17 | 2016-03-24 |  | Y
Central Hudson |  | Sungevity Inc | CH-09583 | Kingston | Kingston | Ulster | 12401 | G | 112 | South Wall St | N |  | 3.8 | [13 empty] | NM | N | ABB PVI-3.8-OUTD-S-US-A | 2016-01-27 | 2016-02-10 | 10 | 2016-02-10 | [14 empty] | 2016-04-05 | 2016-04-12 |  | Y
Central Hudson |  | Sungevity Inc | CH-09627 | Fishkill | Fishkill |  | 12524 | G | 8014 | Forgebrook | TBD |  | 4.2 | [13 empty] | NM | N | ABB PVI-4.2-OUTD-S-US-A | 2016-01-27 | 2016-01-29 | 2 | 2016-01-29 | [17 empty] | W
Central Hudson |  | Conscious Energy | CH-00810 | Newburgh | Gardiner | Ulster | 12525 | G | 5043 | East Walden | N | CH-00788 | 9 | [13 empty] | NM | N | SMA SB3000TL-US-22 SMA SB6000TL-US-22 | 2016-02-04 | 2016-03-15 | 27 | 2016-03-15 | [14 empty] | 2016-04-06 | 2016-04-13 |  | Y
Central Hudson |  | Monolith Solar Associates LLC | CH-02635 | Catskill | Climax | Greene | 12042 | G | 2061 | Freehold | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE7600A-US | 2016-01-28 | 2016-02-11 | 10 | 2016-02-11 | [14 empty] | 2016-04-07 | 2016-04-14 |  | Y
Central Hudson |  | SolarCity | CH-05138 | Newburgh | Montgomery | Orange | 12549 | G | 5042 | East Walden | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2016-03-15 | 2016-03-22 | 5 | 2016-03-22 | [14 empty] | 2016-04-07 | 2016-04-12 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-05700 | Kingston | Kingston | Ulster | 12401 | G | 111 | South Wall St | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000-OUTD-US | 2016-01-28 | 2016-02-11 | 10 | 2016-02-11 | [14 empty] | 2016-07-15 | 2016-07-15 |  | Y
Central Hudson |  | SolarCity | CH-06561 | Kingston | Ellenvl | Ulster | 12428 | G | 3076 | Greenfield Rd | N |  | 12 | [13 empty] | NM | N | 2 ABB PVI-6000-OUTD-US | 2016-01-28 | 2016-02-11 | 10 | 2016-02-11 | [14 empty] | 2016-06-23 | 2016-06-29 |  | Y
Central Hudson |  | SolarCity | CH-07075 | Newburgh | Marlboro | Ulster | 12542 | G | 5001 | Marlboro | N |  | 6 | [13 empty] | NM | N | ABB PVI6000 | 2016-03-09 | 2016-03-21 | 8 | 2016-03-21 | [14 empty] | 2016-03-24 | 2016-04-01 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07870 | Poughkeepsie | Poughkeepsie |  | 12603 | G | 6046 | Spackenkill | TBD |  | 3 | [13 empty] | NM | N | ABB PVI-3.0 OUTD-US-Z | 2016-01-28 | 2016-02-04 | 5 | 2016-02-04 | [17 empty] | W
Central Hudson |  | Apex Solar Power | CH-03091 | Catskill | Cornwallvl | Greene | 12418 | G | 2043 | South Cairo | N |  | 12 | [13 empty] | NM | N | 2 SOLAREDGE SE6000A-US | 2016-01-29 | 2016-02-12 | 10 | 2016-02-12 | [14 empty] | 2016-03-17 | 2016-03-23 |  | Y
Central Hudson |  | NRG Home Solar | CH-04189 | Newburgh | Wallkill |  | 12589 | G | 5033 | Galeville | TBD |  | 3.5 | [13 empty] | NM | N | ENPHASE M250-60-2LL-S22 (14) | 2016-01-29 | 2016-01-29 | 0 | 2016-01-29 | [17 empty] | W
Central Hudson |  | NRG Home Solar | CH-04257 | Kingston | Accord |  | 12404 | G | 3082 | Kerhonkson | TBD |  | 3.87 | [13 empty] | NM | N | 18 ENPHASE M215-60-2LL-S22-IG | 2016-01-29 | 2016-02-12 | 10 | 2016-02-12 | [17 empty] | W
Central Hudson |  | NRG Home Solar | CH-04606 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8045 | Myers Corners | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE7600A-US | 2016-01-29 | 2016-01-29 | 0 | 2016-01-29 | [14 empty] | 2016-04-20 | 2016-04-22 |  | Y
Central Hudson |  | NRG Home Solar | CH-00539 | Fishkill | Beacon | Dutchess | 12508 | G | 8017 | Forgebrook | N |  | 5.8 | [13 empty] | NM | N | ENPHASE M215-60-2LL-S22-IG (27) | 2016-01-29 | 2016-01-29 | 0 | 2016-01-29 | [14 empty] | 2016-05-04 | 2016-05-06 |  | Y
Central Hudson |  | NRG Home Solar | CH-00575 | Newburgh | New Windsor |  | 12553 | G | 4042 | Union Ave | TBD |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE7600A-US | 2016-01-29 | 2016-01-29 | 0 | 2016-01-29 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | SolarCity | CH-04985 | Catskill | Ravena | Albany | 12143 | G | 1081 | New Baltimore | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2016-01-29 | 2016-02-12 | 10 | 2016-02-12 | [14 empty] | 2016-04-26 | 2016-04-26 |  | Y
Central Hudson |  | SolarCity | CH-06511 | Kingston | Connelly | Ulster | 12417 | G | 1024 | East Kingston | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2016-01-29 | 2016-02-12 | 10 | 2016-02-12 | [14 empty] | 2016-03-01 | 2016-03-08 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-00205 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8045 | Myers Corners | N |  | 9.8 | [13 empty] | NM | N | SMA SB6000TL-22 SMA SB3800TL-US-22 | 2016-02-02 | 2016-02-02 | 0 | 2016-02-02 | [14 empty] | 2016-04-20 | 2016-04-25 |  | Y
Central Hudson |  | Solar Liberty Energy Systems | CH-04902 | Catskill | Prattsvl | Greene | 12468 | E | 2389 | Vinegar Hill | N |  | 5 | [13 empty] | NM | N | SOLAREDGESE5000A-US | 2016-02-01 | 2016-02-16 | 10 | 2016-02-16 | [8 empty] | 350 | 350 |  | 2016-03-02 | 2016-03-02 | 2016-10-17 | 2017-05-04 | 2017-05-05 |  | Y
Central Hudson |  | SolarCity | CH-05168 | Newburgh | Milton | Ulster | 12547 | G | 5083 | Highland | N |  | 6 | [13 empty] | NM | N | ABB PVI 6000 | 2016-02-01 | 2016-02-01 | 0 | 2016-02-01 | [14 empty] | 2016-02-11 | 2016-02-19 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-05835 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 6074 | East Park | N |  | 8.2 | [13 empty] | NM | N | FRONIUS PRIMO 8.2 | 2016-02-01 | 2016-02-08 | 5 | 2016-02-08 | [14 empty] | 2016-02-29 | 2016-03-07 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06987 | Newburgh | Newburgh |  | 12550 | G | 4024 | Coldenham | TBD |  | 6 | [13 empty] | NM | N | ABB PVI 6.0 | 2016-03-15 | 2016-03-29 | 9 | 2016-03-29 | [17 empty] | W
Central Hudson |  | SolarCity | CH-07158 | Newburgh | New Windsor | Orange | 12553 | G | 4094 | Bethlehem Rd | N |  | 12 | [13 empty] | NM | N | ABB PVI6.0 (2) | 2016-02-01 | 2016-02-01 | 0 | 2016-02-01 | [14 empty] | 2016-04-18 | 2016-04-18 |  | Y
Central Hudson |  | SolarCity | CH-07310 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 7024 | Tinkertown | N |  | 10 | [13 empty] | NM | N | (2) ABB PVI 5000 | 2016-02-01 | 2016-02-08 | 5 | 2016-02-08 | [14 empty] | 2016-03-29 | 2016-04-05 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Sungevity Inc | CH-09226 | Newburgh | Montgomery | Orange | 12549 | G | 5041 | East Walden | N |  | 3.8 | [13 empty] | NM | N | ABB PVI-3.8-OUTD-S-US-A | 2016-02-01 | 2016-02-01 | 0 | 2016-02-01 | [14 empty] | 2016-04-19 | 2016-04-21 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-03376 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8056 | North Chelsea | N |  | 9.8 | [13 empty] | NM | N | SMA SB6000TL-22 SMA SB3800TL-US-22 | 2016-02-02 | 2016-02-02 | 0 | 2016-02-02 | [14 empty] | 2016-02-23 | 2016-02-29 |  | Y
Central Hudson |  | Sunrun Inc. | CH-08354 | Newburgh | Newburgh | Orange | 12550 | G | 4023 | Coldenham | N |  | 2.75 | [13 empty] | NM | N | ENPHASE M250-60-2LL-S2X (11) | 2016-02-03 | 2016-02-03 | 0 | 2016-02-03 | [14 empty] | 2016-07-21 | 2016-07-26 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-03456 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8093 | Fishkill Plains | N |  | 9.8 | [13 empty] | NM | N | SMA SB6000TL-22 SMA SB3800TL-US-22 | 2016-02-03 | 2016-02-03 | 0 | 2016-02-03 | [14 empty] | 2016-04-20 | 2016-04-22 |  | Y
Central Hudson |  | Map Energy Solutions, LLC | CH-04849 | Poughkeepsie | Hyde Pk |  | 12538 | G | 7041 | Staatsburg | N |  | 1944 | [13 empty] | CDG | Y | 54 Chint Power Systems America CPS SCA36KTL-DO/US CPS SCA36KTL (54) | 2016-05-19 | 2016-06-09 | 14 | 2016-06-09 | 2016-05-19 | 2016-06-09 | 14 | 2017-05-16 | 2017-06-08 | 2017-09-01 | 60 | 22500 | 223474.5 | 84228.5 | 2017-11-30 | 2018-05-23 | 2018-05-23 |  |  |  | 2021-01-21 | W |  | There are 2 accounts at this location, CH-04849 and CH-04850 with an aggregate CESIR Cost to Customer of $45,000 & Estimated Project Upgrade Costs of $446,949.
Central Hudson |  | SolarCity | CH-06210 | Newburgh | Newburgh | Orange | 12550 | G | 4022 | Coldenham | N |  | 6 | [13 empty] | NM | N | ABB PVI 3.0 (2) | 2016-03-15 | 2016-03-29 | 9 | 2016-03-29 | [14 empty] | 2016-04-06 | 2016-04-11 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07542 | Poughkeepsie | Clinton Corners | Dutchess | 12514 | G | 7013 | Hibernia | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2016-02-03 | 2016-02-10 | 5 | 2016-02-10 | [14 empty] | 2016-02-25 | 2016-03-03 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08806 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7054 | Rhinebeck | N |  | 2.795 | [13 empty] | NM | N | (13) ENPHASE M215 | 2016-02-03 | 2016-02-10 | 5 | 2016-02-10 | [14 empty] | 2016-05-23 | 2016-05-27 |  | Y
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03153 | Catskill | Cairo |  | 12413 | G | 2041 | South Cairo | N |  | 1980 | [13 empty] | CDG | Y | 44 HUAWEI SUN2000-45KTL-US-1500 | 2016-03-04 | 2016-03-04 | 0 | 2016-03-04 | 2016-02-12 | 2016-03-04 | 14 | 2017-02-22 | 2017-02-22 | 2017-05-18 | 60 | 29223.92 | 569513 | 124.86 | 2017-10-30 | 2018-04-18 | 2018-04-18 |  |  |  | 2020-07-21 | W
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03154 | Catskill | Freehold | Greene | 12431 | G | 2061 | Freehold | N |  | 2000 | [13 empty] | CDG | N | 16 Chint Power Systems America CPS SCH125KTL-DO/US-600 (600V) (44) Huawei SUN2000-45KTL-US-1500 | 2016-02-10 | 2016-03-03 | 15 | 2016-03-03 | 2016-02-10 | 2016-03-03 | 15 | 2016-11-15 | 2016-11-15 | 2017-02-14 | 60 | 12500 | 326537.5 | 119160.75 | 2017-03-01 | 2017-08-24 | 2017-08-24 | 2021-06-22 | 2021-08-31 | 2021-08-31 | 2021-11-22 | Y |  | CESIR for 4 projects, CH-03154, CH-03228, CH-03172 and CH-03176. (totaling 8MW) combined with an aggregate CESIR Cost to Customer of $50,000. Only proceeding with CH-03154 and CH-03172.
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03155 | Poughkeepsie | Milan |  | 12571 | G | 7061 | Milan | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-02-12 | 2016-03-04 | 14 | 2016-03-04 | 2016-02-12 | 2016-03-04 | 14 |  |  |  |  | 32000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03156 | Catskill | Freehold |  | 12431 | G | 2061 | Freehold | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-02-10 | 2016-03-03 | 15 | 2016-03-03 | 2016-02-10 | 2016-03-03 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 2/15/16 Company Holiday. CESIR determined necessary during preliminary review Section C, Step 4.
Central Hudson |  | Kasselman Solar | CH-03517 | Catskill | Catskill | Greene | 12414 | G | 2003 | North Catskill | N |  | 6.16 | [13 empty] | NM | N | 22 ENPHASE S280 US | 2016-02-04 | 2016-02-19 | 10 | 2016-02-19 | [14 empty] | 2016-02-26 | 2016-03-04 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Solar Liberty Energy Systems | CH-04912 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 6057 | Todd Hill | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE 7600A-US | 2016-02-22 | 2016-03-07 | 10 | 2016-03-07 | [14 empty] | 2017-06-20 | 2017-06-21 |  | Y
Central Hudson |  | SolarCity | CH-05217 | Kingston | Kingston | Ulster | 12401 | G | 1022 | East Kingston | N |  | 3.6 | [13 empty] | NM | N | ABB PVI 3.6 | 2016-02-04 | 2016-02-19 | 10 | 2016-02-19 | [14 empty] | 2016-02-23 | 2016-03-01 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03157 | Catskill | W Coxsackie |  | 12192 | G | 1083 | New Baltimore | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-02-10 | 2016-03-03 | 15 | 2016-03-03 | 2016-02-10 | 2016-03-03 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 2/15/16 Company Holiday. CESIR determined necessary during preliminary review Section C, Step 4.
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03158 | Kingston | Ellenvl | Ulster | 12428 | G | 3097 | Grimley Rd | N |  | 2000 | [13 empty] | CDG | N | HUAWEI SUN2000-45KTL-US-1500 (44) | 2016-02-12 | 2016-03-04 | 14 | 2016-03-04 | 2016-02-12 | 2016-03-04 | 14 | 2016-07-26 | 2016-07-26 | 2016-10-19 | 60 | 16569.36 | 872425 | 945657.71 | 2017-03-08 | 2017-08-29 | 2017-08-29 | 2019-10-24 | 2019-10-29 | 2019-10-29 | 2020-05-26 | Y |  | Interconnection costs for 2 projects, CH-03130 and CH-03158 combined with an aggregate Estimated Upgrade Costs of $1,744,850.
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03159 | Catskill | Catskill |  | 12414 | G | 2006 | North Catskill | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-02-10 | 2016-03-03 | 15 | 2016-03-03 | 2016-02-10 | 2016-03-03 | 15 |  |  |  |  | 32000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03160 | Catskill | Catskill |  | 12414 | G | 2001 | North Catskill | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-02-16 | 2016-03-08 | 15 | 2016-03-08 | 2016-02-16 | 2016-03-08 | 15 |  |  |  |  | 32000 | [9 empty] | W
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03161 | Catskill | Greenville |  | 12083 | G | 2061 | Freehold | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-02-10 | 2016-03-03 | 15 | 2016-03-03 | 2016-02-10 | 2016-03-03 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 2/15/16 Company Holiday. CESIR determined necessary during preliminary review Section C, Step 4.
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03162 | Newburgh | Lloyd |  | 12528 | G | 5022 | Ohioville | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-02-16 | 2016-03-08 | 15 | 2016-03-08 | 2016-02-16 | 2016-03-08 | 15 |  |  |  |  | 32000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03163 | Poughkeepsie | Clinton Corners |  | 12514 | G | 7012 | Hibernia | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-02-10 | 2016-03-03 | 15 | 2016-03-03 | 2016-02-10 | 2016-03-03 | 15 |  |  |  |  | 34000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03164 | Catskill | Greenville |  | 12083 | G | 2061 | Freehold | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-02-16 | 2016-03-08 | 15 | 2016-03-08 | 2016-02-16 | 2016-03-08 | 15 |  |  |  |  | 42000 | [9 empty] | W |  | CESIR determined necessary during preliminary review Section C, Step 4.
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03165 | Catskill | Greenville |  | 12083 | G | 2061 | Freehold | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-02-10 | 2016-03-03 | 15 | 2016-03-03 | 2016-02-10 | 2016-03-03 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 2/15/16 Company Holiday. CESIR determined necessary during preliminary review Section C, Step 4.
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03166 | Catskill | Cairo |  | 12413 | G | 2041 | South Cairo | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-02-12 | 2016-03-04 | 14 | 2016-03-04 | 2016-02-12 | 2016-03-04 | 14 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03167 | TBD | Ellenville |  | 12428 | Tbd | TBD | Tbd | N |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-02-10 | 2016-03-03 | 15 | 2016-03-03 | 2016-02-10 | 2016-03-03 | 15 |  |  |  |  | 33000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03168 | Kingston | Accord |  | 12404 | G | 3024 | High Falls | TBD |  | 1980 | [13 empty] | CDG | N | 44 HUAWEI SUN2000-45KTL-US-1500 | 2016-02-16 | 2016-03-08 | 15 | 2016-03-08 | 2016-02-16 | 2016-03-08 | 15 | 2017-02-22 | 2017-02-22 | 2017-05-18 | 60 | 20852.9 | 3779523 | [7 empty] | 2018-05-24 | W
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03169 | Catskill | Athens |  | 12015 | G | 1074 | Coxsackie | TBD |  | 1980 | [13 empty] | CDG | N | (44) Huawei SUN2000-45KTL-US | 2016-02-10 | 2016-03-03 | 15 | 2016-03-03 | 2016-02-10 | 2016-03-03 | 15 | 2016-04-21 | 2016-05-03 | 2016-07-28 | 60 | 22834 | 403500 | 498.15 | 2017-06-23 | 2017-11-16 | 2017-11-16 |  |  |  | 2019-10-18 | W
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03170 | Kingston | Ellenville |  | 12428 | G | 3095 | Grimley Rd | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-02-16 | 2016-03-08 | 15 | 2016-03-08 | 2016-02-16 | 2016-03-08 | 15 |  |  |  |  | 32000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | NRG Home Solar | CH-04526 | Kingston | Kingston | Ulster | 12401 | G | 2093 | Hurley Ave | N |  | 4.73 | [13 empty] | NM | N | 22 ENPHASE M215-60-2LL-S22-IG | 2016-02-05 | 2016-02-22 | 10 | 2016-02-22 | [14 empty] | 2016-04-06 | 2016-04-13 |  | Y
Central Hudson |  | NRG Home Solar | CH-04629 | Newburgh | Newburgh | Orange | 12550 | G | 4051 | Union Ave | N |  | 3.87 | [13 empty] | NM | N | ENPHASE M215-60-2LL-S22-IG (18) | 2016-02-05 | 2016-02-08 | 1 | 2016-02-08 | [14 empty] | 2016-03-30 | 2016-04-06 |  | Y
Central Hudson |  | SolarCity | CH-07817 | Poughkeepsie | Pine Plns | Dutchess | 12567 | G | 7091 | Pulvers Corners | N | CH-05973 | 3 | [13 empty] | NM | N | ABB PVI-3.0 OUTD-S-US | 2016-02-05 | 2016-02-22 | 10 | 2016-02-22 | [14 empty] | 2016-02-24 | 2016-03-01 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07926 | Kingston | Accord |  | 12404 | G | 3024 | High Falls | TBD |  | 1992 | [13 empty] | CDG | N | (83) FRONIUS SYMO 24 | 2016-03-18 | 2016-04-11 | 15 | 2016-04-11 | 2016-03-18 | 2016-04-11 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | SolarCity | CH-07927 | Newburgh | Walden |  | 12586 | G | 5041 | East Walden | TBD |  | 1992 | [13 empty] | CDG | N | FRONIUS SYMO 24.3 (83) | 2016-03-18 | 2016-04-11 | 15 | 2016-04-11 | 2016-03-18 | 2016-04-11 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | SolarCity | CH-07928 | Poughkeepsie | Rhinebeck |  | 12572 | G | 7054 | Rhinebeck | TBD |  | 1992 | [13 empty] | CDG | N | (83) FRONIUS SYMO 24 | 2016-03-18 | 2016-04-11 | 15 | 2016-04-11 | 2016-03-18 | 2016-04-11 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | SolarCity | CH-07929 | Catskill | Freehold |  | 12431 | G | 2071 | Freehold | TBD |  | 1992 | [13 empty] | CDG | N | FRONIUS SYMO 24.3 (83) | 2016-03-18 | 2016-04-11 | 15 | 2016-04-11 | 2016-03-18 | 2016-04-11 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | SolarCity | CH-07930 | Catskill | Leeds |  | 12451 | G | 2071 | Freehold | TBD |  | 1992 | [13 empty] | CDG | N | (83) FRONIUS SYMO 24 | 2016-03-18 | 2016-04-11 | 15 | 2016-04-11 | 2016-03-18 | 2016-04-11 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | SolarCity | CH-07931 | Catskill | Cairo |  | 12413 | G | 2071 | Freehold | TBD |  | 1992 | [13 empty] | CDG | N | (83) FRONIUS SYMO 24 | 2016-03-18 | 2016-04-11 | 15 | 2016-04-11 | 2016-03-18 | 2016-04-11 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | SolarCity | CH-07932 | Catskill | Cairo |  | 12413 | G | 2043 | South Cairo | TBD |  | 1992 | [13 empty] | CDG | N | FRONIUS SYMO 24.3 (83) | 2016-03-18 | 2016-04-11 | 15 | 2016-04-11 | 2016-03-18 | 2016-04-11 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08792 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7051 | Rhinebeck | N |  | 6.02 | [13 empty] | NM | N | (28) ENPHASE M125 602LLS2XZC | 2016-02-05 | 2016-02-22 | 10 | 2016-02-22 | [14 empty] | 2016-04-14 | 2016-04-21 |  | Y
Central Hudson |  | Sungevity Inc | CH-09423 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6011 | Sand Dock | N | CH-09423 | 3.3 | [13 empty] | NM | N | ABB PVI-3.0-OUTD-S-US-A | 2016-02-05 | 2016-02-22 | 10 | 2016-02-22 | [14 empty] | 2016-04-18 | 2016-04-25 |  | Y
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03171 | Catskill | S Cairo |  | 12482 | G | 2042 | South Cairo | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-02-23 | 2016-03-15 | 15 | 2016-03-15 | 2016-02-23 | 2016-03-15 | 15 |  |  |  |  | 32000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03172 | Catskill | Greenvl |  | 12083 | G | 2061 | Freehold | N |  | 1980 | [13 empty] | CDG | N | (44) Huawei SUN2000-45KTL-US-1500 | 2016-02-16 | 2016-03-08 | 15 | 2016-03-08 | 2016-02-16 | 2016-03-08 | 15 | 2016-11-15 | 2016-11-15 | 2017-03-15 | 80 | 60314.65 | 380035 | 15611.1 | 2017-06-23 | 2017-09-12 | 2017-09-12 |  |  |  | 2022-06-14 | W |  | CESIR for 4 projects, CH-03154, CH-03228, CH-03172 and CH-03176. (totaling 8MW) combined with an aggregate CESIR Cost to Customer of $50,000. Only proceeding with CH-03154, and CH-03172.
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03173 | Catskill | Athens |  | 12015 | G | 2002 | North Catskill | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-02-16 | 2016-03-08 | 15 | 2016-03-08 | 2016-02-16 | 2016-03-08 | 15 |  |  |  |  | 32000 | [9 empty] | W
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03174 | Kingston | Greenfield Park |  | 12435 | G | 3096 | Grimley Rd | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-02-16 | 2016-03-08 | 15 | 2016-03-08 | 2016-02-16 | 2016-03-08 | 15 |  |  |  |  | 38000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03175 | Catskill | Cairo |  | 12413 | G | 2041 | South Cairo | TBD |  | 2000 | [13 empty] | CDG | N | SMA SG SC-2200-US | 2016-02-16 | 2016-03-08 | 15 | 2016-03-08 | 2016-02-16 | 2016-03-08 | 15 |  |  |  |  | 40000 | [9 empty] | W
Central Hudson |  | Kasselman Solar | CH-00243 | Kingston | Hurley | Ulster | 12443 | G | 2094 | Hurley Ave | N |  | 5.25 | [13 empty] | NM | N | 21 ENPHASE S280 US | 2016-02-08 | 2016-02-23 | 10 | 2016-02-23 | [14 empty] | 2016-03-17 | 2016-03-23 |  | Y
Central Hudson |  | NRG Home Solar | CH-04149 | Kingston | Kingston |  | 12401 | G | 2093 | Hurley Ave | TBD |  | 5.16 | [13 empty] | NM | N | 24 ENPHASE M215-60-2LL-S22-IG | 2016-02-08 | 2016-02-23 | 10 | 2016-02-23 | [17 empty] | W
Central Hudson |  | NRG Home Solar | CH-04632 | Newburgh | Newburgh |  | 12550 | G | 4013 | West Balmville | TBD |  | 3.87 | [13 empty] | NM | N | ENPHASE M215-60-2LL-S22-IG (18) | 2016-02-08 | 2016-02-23 | 10 | 2016-02-23 | [17 empty] | W
Central Hudson |  | Map Energy Solutions, LLC | CH-04850 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 7041 | Staatsburg | N |  | 1950 | [13 empty] | CDG | Y | 13 SMA America SHP 150-US-20 (600V) [SI1] CPS SCA36KTL (54) | 2016-05-19 | 2016-06-09 | 14 | 2016-06-09 | 2016-05-19 | 2016-06-09 | 14 | 2017-05-16 | 2017-06-08 | 2017-09-01 | 60 | 29600.1 | 307703 | 127136.9 | 2017-11-30 | 2018-05-23 | 2018-05-23 | 2021-12-02 | 2021-12-20 | 2021-12-21 | 2022-03-25 | Y | Y | There are 2 accounts at this location, CH-04849 and CH-04850 with an aggregate CESIR Cost to Customer of $45,000 & Estimated Project Upgrade Costs of $446,949.
Central Hudson |  | Omni Navitas Holdings LLC | CH-04851 | Poughkeepsie | Pine Plains |  | 12567 | G | 7091 | Pulvers Corners | TBD |  | 1944 | [13 empty] | CDG | N | CPS SCA36KTL (54) | 2016-05-19 | 2016-06-10 | 15 | 2016-06-10 | 2016-05-19 | 2016-06-10 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Omni Navitas Holdings LLC | CH-04852 | Poughkeepsie | Poughkeepsie |  | 12601 | G | 7024 | Tinkertown | TBD |  | 1944 | [13 empty] | CDG | N | CPS SCA36KTL (54) | 2016-05-19 | 2016-06-09 | 14 | 2016-06-09 | 2016-05-19 | 2016-06-09 | 14 |  |  |  |  | 35000 | [9 empty] | W
Central Hudson |  | Omni Navitas Holdings LLC | CH-04853 | Poughkeepsie | Pine Plains |  | 12567 | G | 7091 | Pulvers Corners | TBD |  | 1944 | [13 empty] | CDG | N | CPS SCA36KTL (54) | 2016-05-19 | 2016-06-09 | 14 | 2016-06-09 | 2016-05-19 | 2016-06-09 | 14 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Omni Navitas Holdings LLC | CH-04857 | Poughkeepsie | Clinton Corners |  | 12514 | G | 7071 | Stanfordville | TBD |  | 1036 | [13 empty] | CDG | N | CPS SCA36KTL (28) CPS SCA28KTL (1) | 2016-05-19 | 2016-06-09 | 14 | 2016-06-09 | 2016-05-19 | 2016-06-09 | 14 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Omni Navitas Holdings LLC | CH-04858 | Poughkeepsie | Pleasant Valley |  | 12569 | G | 6074 | East Park | TBD |  | 1800 | [13 empty] | CDG | N | CPS SCA36KTL (50) | 2016-05-19 | 2016-06-10 | 15 | 2016-06-10 | 2016-05-19 | 2016-06-10 | 15 |  |  |  |  | 32000 | [9 empty] | W
Central Hudson |  | Omni Navitas Holdings LLC | CH-04859 | Poughkeepsie | Pine Plains |  | 12567 | G | 7091 | Pulvers Corners | TBD |  | 1944 | [13 empty] | CDG | N | CPS SCA36KTL (54) | 2016-06-16 | 2016-07-07 | 14 | 2016-07-07 | 2016-06-16 | 2016-07-07 | 14 |  |  |  |  | 35000 | [9 empty] | W |  | 2/15/16 - Company Holiday.
Central Hudson |  | Omni Navitas Holdings LLC | CH-04860 | Poughkeepsie | Pleasant Valley |  | 12569 | G | 6074 | East Park | TBD |  | 1944 | [13 empty] | CDG | N | CPS SCA36KTL (54) | 2016-05-19 | 2016-06-10 | 15 | 2016-06-10 | 2016-05-19 | 2016-06-10 | 15 |  |  |  |  | 35000 | [9 empty] | W
Central Hudson |  | Hudson Solar | CH-01415 | Kingston | Kingston | Ulster | 12401 | G | 1024 | East Kingston | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE-7600A-US-U | 2016-02-08 | 2016-02-23 | 10 | 2016-02-23 | [14 empty] | 2016-03-18 | 2016-03-28 |  | Y
Central Hudson |  | Hudson Solar | CH-01675 | Kingston | Bloomington | Ulster | 12411 | G | 1011 | Boulevard | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE-7600A-US-U | 2016-02-08 | 2016-02-23 | 10 | 2016-02-23 | [14 empty] | 2016-04-18 | 2016-04-25 |  | Y
Central Hudson |  | Hudson Solar | CH-01730 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6046 | Spackenkill | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE-6000A-US-U | 2016-02-08 | 2016-02-23 | 10 | 2016-02-23 | [14 empty] | 2016-07-21 | 2016-07-21 |  | Y
Central Hudson |  | Hudson Solar | CH-01968 | Newburgh | Marlboro | Ulster | 12542 | G | 5004 | Marlboro | N |  | 11.4 | [13 empty] | NM | N | SOLAREDGE SE-11400A-US-U | 2016-02-08 | 2016-02-23 | 10 | 2016-02-23 | [14 empty] | 2016-03-23 | 2016-03-31 |  | Y
Central Hudson |  | Hudson Solar | CH-02011 | Catskill | E Durham | Greene | 12423 | G | 2071 | Freehold | N | CH-02011 | 5 | [13 empty] | NM | N | SOLAREDGE SE-5000A-US-U | 2016-02-08 | 2016-02-23 | 10 | 2016-02-23 | [14 empty] | 2016-03-31 | 2016-04-07 |  | Y
Central Hudson |  | Hudson Solar | CH-02187 | Newburgh | New Paltz | Ulster | 12561 | G | 5021 | Ohioville | N |  | 10 | [13 empty] | NM | N | SOLAREDGE SE-10000A-US-U | 2016-02-08 | 2016-02-23 | 10 | 2016-02-23 | [14 empty] | 2016-05-06 | 2016-05-10 |  | Y
Central Hudson |  | Hudson Solar | CH-02287 | Poughkeepsie | Tivoli | Dutchess | 12583 | G | 7051 | Rhinebeck | N | CH-02287 | 5 | [13 empty] | NM | N | SOLAREDGE SE-5000A-US-U | 2016-02-08 | 2016-02-23 | 10 | 2016-02-23 | [14 empty] | 2016-05-16 | 2016-05-23 |  | Y
Central Hudson |  | OE SOLAR 8, LLC | CH-02796 | Catskill | New Baltimore |  | 12192 | G | 1071 | Coxsackie | TBD |  | 2000 | [13 empty] | CDG | N | SGI 500XTM (4) | 2016-03-07 | 2016-03-29 | 15 | 2016-03-29 | 2016-03-07 | 2016-03-29 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | SolarCity | CH-05229 | Newburgh | Montgomery | Orange | 12549 | G | 5054 | Maybrook | N |  | 11 | [13 empty] | NM | N | ABB PVI6000 ABB PVI5000 | 2016-02-08 | 2016-02-08 | 0 | 2016-02-08 | [14 empty] | 2016-03-01 | 2016-03-08 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-05407 | Newburgh | Newburgh | Orange | 12550 | G | 4011 | West Balmville | N |  | 7.2 | [13 empty] | NM | N | ABB PVI 3.6 (2) | 2016-03-09 | 2016-03-21 | 8 | 2016-03-21 | [14 empty] | 2016-03-28 | 2016-04-04 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-05629 | Kingston | Tillson | Ulster | 12486 | G | 3021 | High Falls | N |  | 9.2 | [13 empty] | NM | N | ABB PVI-5000 OUTD-US ABB PVI-4.2 OUTD-US | 2016-02-08 | 2016-02-23 | 10 | 2016-02-23 | [14 empty] | 2016-03-04 | 2016-03-11 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06569 | Kingston | Saugerties | Ulster | 12477 | G | 3002 | Saugerties | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2016-02-08 | 2016-02-23 | 10 | 2016-02-23 | [14 empty] | 2016-03-01 | 2016-03-08 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06750 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6092 | Manchester | N |  | 6 | [13 empty] | NM | N | (2) ABB PVI 3.0 | 2016-02-19 | 2016-02-26 | 5 | 2016-02-26 | [14 empty] | 2016-04-13 | 2016-04-14 |  | Y
Central Hudson |  | SolarCity | CH-06978 | Newburgh | Walden | Orange | 12586 | G | 5041 | East Walden | N |  | 6 | [13 empty] | NM | N | ABB PVI 6000 | 2016-02-08 | 2016-02-23 | 10 | 2016-02-23 | [14 empty] | 2016-03-01 | 2016-03-08 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07202 | Kingston | Ulster Pk | Ulster | 12487 | G | 1014 | Boulevard | N |  | 3 | [13 empty] | NM | N | ABB PVI 3.0 | 2016-02-08 | 2016-02-23 | 10 | 2016-02-23 | [14 empty] | 2016-03-21 | 2016-04-01 |  | Y
Central Hudson |  | SolarCity | CH-07528 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6091 | Manchester | N |  | 5 | [13 empty] | NM | N | ABB PVI 5000 | 2016-03-08 | 2016-03-15 | 5 | 2016-03-15 | [14 empty] | 2016-03-16 | 2016-03-23 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07564 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8046 | Myers Corners | N |  | 3 | [13 empty] | NM | N | ABB PVI-3.0 | 2016-02-08 | 2016-02-23 | 10 | 2016-02-23 | [14 empty] | 2016-06-03 | 2016-06-07 |  | Y
Central Hudson |  | SolarCity | CH-07933 | Newburgh | New Paltz |  | 12561 | G | 5023 | Ohioville | TBD |  | 1992 | [13 empty] | CDG | N | FRONIUS SYMO 24.3 (83) | 2016-03-18 | 2016-04-11 | 15 | 2016-04-11 | 2016-03-18 | 2016-04-11 | 15 |  |  |  |  | 32000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | SolarCity | CH-07934 | Poughkeepsie | Rhinebeck |  | 12572 | G | 7053 | Rhinebeck | TBD |  | 1992 | [13 empty] | CDG | N | (83) FRONIUS SYMO 24 | 2016-03-18 | 2016-04-11 | 15 | 2016-04-11 | 2016-03-18 | 2016-04-11 | 15 |  |  |  |  | 32000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | SolarCity | CH-07935 | Kingston | Saugerties |  | 12477 | G | 3003 | Saugerties | TBD |  | 1992 | [13 empty] | CDG | N | (83) FRONIUS SYMO 24 | 2016-03-18 | 2016-04-11 | 15 | 2016-04-11 | 2016-03-18 | 2016-04-11 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | SolarCity | CH-07936 | Poughkeepsie | Rhinebeck |  | 12572 | G | 7056 | Rhinebeck | TBD |  | 1992 | [13 empty] | CDG | N | FRONIUS SYMO 24 (83) | 2016-03-18 | 2016-04-11 | 15 | 2016-04-11 | 2016-03-18 | 2016-04-11 | 15 |  |  |  |  | 32000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | SolarCity | CH-07937 | Fishkill | Wappingrs Falls |  | 12590 | G | 8092 | Fishkill Plains | TBD |  | 1992 | [13 empty] | CDG | N | (83) FRONIUS SYMO 24 | 2016-03-18 | 2016-04-11 | 15 | 2016-04-11 | 2016-03-18 | 2016-04-11 | 15 |  |  |  |  | 32000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | SolarCity | CH-07938 | Catskill | Catskill |  | 12414 | G | 2003 | North Catskill | TBD |  | 1992 | [13 empty] | CDG | N | FRONIUS SYMO 24.0 (83) | 2016-03-18 | 2016-04-11 | 15 | 2016-04-11 | 2016-03-18 | 2016-04-11 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | SolarCity | CH-07939 | Newburgh | Gardiner |  | 12525 | G | 5011 | Modena | TBD |  | 1992 | [13 empty] | CDG | N | (83) FRONIUS SYMO 24 | 2016-03-18 | 2016-04-11 | 15 | 2016-04-11 | 2016-03-18 | 2016-04-11 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | SolarCity | CH-07940 | Poughkeepsie | Red Hook |  | 12571 | G | 7061 | Milan | TBD |  | 1992 | [13 empty] | CDG | N | FRONIUS SYMO 24 (83) | 2016-03-18 | 2016-04-11 | 15 | 2016-04-11 | 2016-03-18 | 2016-04-11 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | SolarCity | CH-07941 | Poughkeepsie | Red Hook |  | 12571 | G | 7061 | Milan | TBD |  | 1992 | [13 empty] | CDG | N | (83) FRONIUS SYMO 24 | 2016-03-18 | 2016-04-11 | 15 | 2016-04-11 | 2016-03-18 | 2016-04-11 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | SolarCity | CH-07942 | Catskill | Ravena |  | 12143 | G | 1083 | New Baltimore | TBD |  | 1992 | [13 empty] | CDG | N | FRONIUS SYMO 24 (83) | 2016-03-18 | 2016-04-11 | 15 | 2016-04-11 | 2016-03-18 | 2016-04-11 | 15 |  |  |  |  | 40000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | SolarCity | CH-07943 | Catskill | Ravena |  | 12143 | G | 1083 | New Baltimore | TBD |  | 1992 | [13 empty] | CDG | N | (83) FRONIUS SYMO 24 | 2016-03-18 | 2016-04-11 | 15 | 2016-04-11 | 2016-03-18 | 2016-04-11 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | SolarCity | CH-07944 | Poughkeepsie | Rhinebeck |  | 12572 | G | 7053 | Rhinebeck | TBD |  | 1992 | [13 empty] | CDG | N | FRONIUS SYMO 24 (83) | 2016-03-18 | 2016-04-11 | 15 | 2016-04-11 | 2016-03-18 | 2016-04-11 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | SolarCity | CH-07945 | Kingston | Saugerties |  | 12477 | G | 3002 | Saugerties | TBD |  | 1992 | [13 empty] | CDG | N | (83) FRONIUS SYMO 24 | 2016-03-18 | 2016-04-08 | 14 | 2016-04-08 | 2016-03-18 | 2016-04-08 | 14 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | SolarCity | CH-07946 | Catskill | Athens |  | 12015 | G | 2002 | North Catskill | TBD |  | 1992 | [13 empty] | CDG | N | FRONIUS SYMO 24 (83) | 2016-03-18 | 2016-04-08 | 14 | 2016-04-08 | 2016-03-18 | 2016-04-08 | 14 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | SolarCity | CH-07947 | Catskill | Catskill |  | 12414 | G | 2001 | North Catskill | TBD |  | 1992 | [13 empty] | CDG | N | (83) FRONIUS SYMO 24 | 2016-03-28 | 2016-04-18 | 15 | 2016-04-18 | 2016-03-28 | 2016-04-18 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | SolarCity | CH-07948 | Kingston | Marbletown |  | 12440 | G | 3022 | High Falls | TBD |  | 1992 | [13 empty] | CDG | N | FRONIUS SYMO 24 (83) | 2016-03-18 | 2016-04-08 | 14 | 2016-04-08 | 2016-03-18 | 2016-04-08 | 14 |  |  |  |  | 32000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | SolarCity | CH-07949 | Catskill | New Baltimore |  | 12192 | G | 1083 | New Baltimore | TBD |  | 1992 | [13 empty] | CDG | N | (83) FRONIUS SYMO 24 | 2016-03-18 | 2016-04-08 | 14 | 2016-04-08 | 2016-03-18 | 2016-04-08 | 14 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | SolarCity | CH-07950 | Catskill | Hannacroix |  | 12087 | G | 1076 | Coxsackie | TBD |  | 1992 | [13 empty] | CDG | N | FRONIUS SYMO 24 (83) | 2016-03-18 | 2016-04-11 | 15 | 2016-04-11 | 2016-03-18 | 2016-04-11 | 15 |  |  |  |  | 40000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | SolarCity | CH-07951 | Catskill | Catskill |  | 12414 | G | 2004 | North Catskill | TBD |  | 1992 | [13 empty] | CDG | N | (83) FRONIUS SYMO 24 | 2016-03-18 | 2016-04-11 | 15 | 2016-04-11 | 2016-03-18 | 2016-04-11 | 15 |  |  |  |  | 32000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | SolarCity | CH-07952 | Poughkeepsie | Northeast |  | 12501 | G | 7095 | Smithfield | TBD |  | 1992 | [13 empty] | CDG | N | FRONIUS SYMO 24 (83) | 2016-03-18 | 2016-04-11 | 15 | 2016-04-11 | 2016-03-18 | 2016-04-11 | 15 |  |  |  |  | 32000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | SolarCity | CH-07953 | Poughkeepsie | Northeast |  | 12501 | G | 7095 | Smithfield | TBD |  | 1992 | [13 empty] | CDG | N | FRONIUS SYMO 24 (83) | 2016-03-21 | 2016-04-11 | 14 | 2016-04-11 | 2016-03-21 | 2016-04-11 | 14 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | SolarCity | CH-07954 | Poughkeepsie | Pine Plains |  | 12567 | G | 7092 | Pulvers Corners | TBD |  | 1992 | [13 empty] | CDG | N | (83) FRONIUS SYMO 24 | 2016-03-18 | 2016-04-11 | 15 | 2016-04-11 | 2016-03-18 | 2016-04-11 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | SolarCity | CH-07955 | Poughkeepsie | Pine Plains |  | 12567 | G | 7092 | Pulvers Corners | TBD |  | 1992 | [13 empty] | CDG | N | FRONIUS SYMO 24 (83) | 2016-03-18 | 2016-04-11 | 15 | 2016-04-11 | 2016-03-18 | 2016-04-11 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | SolarCity | CH-07956 | Poughkeepsie | Stanfordville |  | 12581 | G | 7072 | Stanfordville | TBD |  | 1992 | [13 empty] | CDG | N | (83) FRONIUS SYMO 24 | 2016-03-18 | 2016-04-11 | 15 | 2016-04-11 | 2016-03-18 | 2016-04-11 | 15 |  |  |  |  | 32000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | SolarCity | CH-07957 | Poughkeepsie | Washington |  | 12545 | G | 7012 | Hibernia | TBD |  | 1992 | [13 empty] | CDG | N | FRONIUS SYMO 24 (83) | 2016-03-18 | 2016-04-11 | 15 | 2016-04-11 | 2016-03-18 | 2016-04-11 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | SolarCity | CH-07958 | Catskill | Coxsackie |  | 12051 | G | 1076 | Coxsackie | TBD |  | 1992 | [13 empty] | CDG | N | (83) FRONIUS SYMO 24 | 2016-03-18 | 2016-04-11 | 15 | 2016-04-11 | 2016-03-18 | 2016-04-11 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | SolarCity | CH-07959 | Newburgh | Campbell Hall |  | 10916 | G | 5051 | Maybrook | TBD |  | 1992 | [13 empty] | CDG | N | FRONIUS SYMO 24 (83) | 2016-03-18 | 2016-04-11 | 15 | 2016-04-11 | 2016-03-18 | 2016-04-11 | 15 |  |  |  |  | 32000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | SolarCity | CH-07960 | Kingston | Stone Ridge |  | 12484 | G | 3021 | High Falls | TBD |  | 1992 | [13 empty] | CDG | N | (83) FRONIUS SYMO 24 | 2016-03-18 | 2016-04-11 | 15 | 2016-04-11 | 2016-03-18 | 2016-04-11 | 15 |  |  |  |  | 32000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | SolarCity | CH-07961 | Poughkeepsie | Rhinebeck |  | 12572 | G | 7053 | Rhinebeck | TBD |  | 1992 | [13 empty] | CDG | N | FRONIUS SYMO 24 (83) | 2016-03-18 | 2016-04-11 | 15 | 2016-04-11 | 2016-03-18 | 2016-04-11 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | SolarCity | CH-07962 | Kingston | Saugerties |  | 12477 | G | 2016 | Lincoln Park | TBD |  | 1992 | [13 empty] | CDG | N | FRONIUS SYMO 24 | 2016-03-18 | 2016-04-11 | 15 | 2016-04-11 | 2016-03-18 | 2016-04-11 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Sunrun Inc. | CH-08345 | Newburgh | Newburgh | Orange | 12550 | G | 4014 | West Balmville | N | CH-08345 | 4.2 | [13 empty] | NM | N | ABB PVI-4.2-OUTD-S-US-A | 2016-02-18 | 2016-03-03 | 10 | 2016-03-03 | [14 empty] | 2016-11-04 | 2016-11-11 |  | Y
Central Hudson |  | Trinity Solar | CH-08560 | Poughkeepsie | Lagrangevl | Dutchess | 12540 | G | 6055 | Todd Hill | N |  | 6 | [13 empty] | NM | N | SOLAR EDGE SE6000A-US | 2016-02-16 | 2016-02-23 | 5 | 2016-02-23 | [14 empty] | 2016-08-04 | 2016-08-05 |  | Y
Central Hudson |  | Trinity Solar | CH-08594 | Fishkill | Wappingrs Falls |  | 12590 | G | 8023 | Knapps Corners | TBD |  | 6 | [13 empty] | NM | N | SOLAR EDGE 6000A-US | 2016-02-23 | 2016-03-07 | 9 | 2016-03-07 | [17 empty] | W |  | 2/15/16 Company Holiday.
Central Hudson |  | Sungevity Inc | CH-09622 | Kingston | Ruby |  | 12475 | G | 2016 | Lincoln Park | TBD |  | 7.6 | [13 empty] | NM | N | 2 ABB PVI-3.8-OUTD-S-US-A | 2016-02-08 | 2016-02-23 | 10 | 2016-02-23 | [17 empty] | W
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03176 | Catskill | Greenville |  | 12083 | G | 2061 | Freehold | TBD |  | 1980 | [13 empty] | CDG | N | (44) Huawei SUN2000-45KTL-US-1500 | 2016-02-17 | 2016-03-09 | 15 | 2016-03-09 | 2016-02-17 | 2016-03-09 | 15 | 2016-11-15 | 2016-11-15 | 2017-03-15 | 80 | 12500 | 397571 | 2627.5 | 2017-06-23 | 2017-09-21 | 2017-09-21 |  |  |  | 2018-09-18 | W |  | CESIR for 4 projects (totaling 8MW) combined with an aggregate CESIR Cost to Customer of $50,000. Total Estimated Upgrade Costs of $1,285,304.
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03177 | Kingston | Grahamsville |  | 12740 | G | 3091 | Neversink | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-02-18 | 2016-03-10 | 15 | 2016-03-10 | 2016-02-18 | 2016-03-10 | 15 |  |  |  |  | 40000 | [9 empty] | W |  | 2/15/16 Company Holiday. CESIR determined necessary during preliminary review Section C, Step 4.
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03178 | Kingston | Saugerties |  | 12477 | G | 3002 | Saugerties | TBD |  | 2000 | [13 empty] | CDG | N | SMA SG 1000MX | 2016-02-17 | 2016-03-09 | 15 | 2016-03-09 | 2016-02-17 | 2016-03-09 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03179 | Catskill | Purling |  | 12470 | G | 2042 | South Cairo | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-02-23 | 2016-03-15 | 15 | 2016-03-15 | 2016-02-23 | 2016-03-15 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03180 | Catskill | Earlton |  | 12058 | G | 1071 | Coxsackie | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-02-17 | 2016-03-09 | 15 | 2016-03-09 | 2016-02-17 | 2016-03-09 | 15 |  |  |  |  | 32000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Active Solar Development | CH-00632 | Catskill | Rensselaervl | Albany | 12147 | G | 1092 | Westerlo | N |  | 8.8 | [13 empty] | NM | N | 2 FRONIUS PRIMO 3.8 US | 2016-02-09 | 2016-02-24 | 10 | 2016-02-24 | [8 empty] | 350 | 350 |  | 2016-03-10 | 2016-03-10 | 2016-03-17 | 2016-03-23 | 2016-03-31 |  | Y
Central Hudson |  | SolarCity | CH-05116 | Kingston | Ulster Pk | Ulster | 12487 | G | 1014 | Boulevard | N |  | 3 | [13 empty] | NM | N | ABB PVI-3.0US-ZB-U | 2016-02-09 | 2016-02-24 | 10 | 2016-02-24 | [14 empty] | 2016-03-10 | 2016-03-21 |  | Y
Central Hudson |  | SolarCity | CH-05599 | Catskill | Ravena | Albany | 12143 | G | 1081 | New Baltimore | N |  | 8.6 | [13 empty] | NM | N | ABB PVI-5000-OUTD US ABB PVI-3.6-OUTD US | 2016-02-09 | 2016-02-24 | 10 | 2016-02-24 | [14 empty] | 2016-03-31 | 2016-04-07 |  | Y
Central Hudson |  | SolarCity | CH-06191 | Newburgh | Newburgh | Orange | 12550 | G | 4051 | Union Ave | N |  | 3.6 | [13 empty] | NM | N | ABB PVI-3.6-OUTD-S US | 2016-02-09 | 2016-02-24 | 10 | 2016-02-24 | [14 empty] | 2016-04-28 | 2016-04-29 |  | Y
Central Hudson |  | Trinity Solar | CH-08449 | Newburgh | Newburgh |  | 12550 | G | 4051 | Union Ave | TBD |  | 7.6 | [13 empty] | NM | N | SOLAR EDGE 7600A-US | 2016-02-24 | 2016-03-09 | 10 | 2016-03-09 | [17 empty] | W
Central Hudson |  | Trinity Solar | CH-08489 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6051 | Todd Hill | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE7600A-US | 2016-02-25 | 2016-02-26 | 1 | 2016-02-26 | [14 empty] | 2016-04-04 | 2016-04-07 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03789 | Newburgh | New Paltz | Ulster | 12561 | G | 5024 | Ohioville | N |  | 10 | [13 empty] | NM | N | SOLAREDGE 10000A-US | 2016-02-18 | 2016-03-03 | 10 | 2016-03-03 | [14 empty] | 2016-04-14 | 2016-04-18 |  | Y
Central Hudson |  | Direct Energy Solar | CH-01012 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8096 | Fishkill Plains | N |  | 6.24 | [13 empty] | NM | N | ENPHASE M215 (29) | 2016-02-10 | 2016-02-25 | 10 | 2016-02-25 | [14 empty] | 2016-06-09 | 2016-06-14 |  | Y
Central Hudson |  | Monolith Solar Associates LLC | CH-02694 | Catskill | Coxsackie |  | 12051 | G | 1072 | Coxsackie | TBD |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A-US | 2016-02-10 | 2016-02-25 | 10 | 2016-02-25 | [17 empty] | W
Central Hudson |  | SolarCity | CH-07716 | Newburgh | New Paltz | Ulster | 12561 | G | 5023 | Ohioville | N |  | 11 | [13 empty] | NM | N | POWER-ONE PVI-6000 POWER-ONE PVI-5000 | 2016-02-10 | 2016-02-25 | 10 | 2016-02-25 | [14 empty] | 2016-03-21 | 2016-03-28 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Trinity Solar | CH-08375 | Newburgh | New Windsor | Orange | 12553 | G | 4097 | Bethlehem Rd | N |  | 7.6 | [13 empty] | NM | N | SOLAR EDGE7600A-US | 2016-02-25 | 2016-03-10 | 10 | 2016-03-10 | [14 empty] | 2016-04-19 | 2016-04-22 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08623 | Fishkill | Poughkeepsie |  | 12601 | G | 8022 | Knapps Corners | TBD |  | 7.74 | [13 empty] | NM | N | ENPHASE M215 (36) | 2016-02-10 | 2016-02-25 | 10 | 2016-02-25 | [17 empty] | W
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08753 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7051 | Rhinebeck | N |  | 3.225 | [13 empty] | NM | N | (15) ENPHASE M215 | 2016-02-10 | 2016-02-18 | 5 | 2016-02-18 | [14 empty] | 2016-04-14 | 2016-04-21 |  | Y
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03181 | Catskill | Palenville |  | 12463 | G | 2001 | North Catskill | TBD |  | 1980 | [13 empty] | CDG | N | 44 HUAWEI SUN2000-45KTL-US-1500 | 2016-02-17 | 2016-03-09 | 15 | 2016-03-09 | 2016-02-17 | 2016-03-09 | 15 | 2017-02-22 | 2017-02-22 | 2017-05-18 | 60 | 35000 | [9 empty] | W
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03182 | Kingston | Ellenville |  | 12428 | G | 3095 | Grimley Rd | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-02-17 | 2016-03-09 | 15 | 2016-03-09 | 2016-02-17 | 2016-03-09 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03183 | Catskill | Athens |  | 12015 | G | 1074 | Coxsackie | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-02-17 | 2016-03-09 | 15 | 2016-03-09 | 2016-02-17 | 2016-03-09 | 15 |  |  |  |  | 40000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03184 | Kingston | Ellenville |  | 12428 | G | 3078 | Greenfield Rd | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-02-17 | 2016-03-09 | 15 | 2016-03-09 | 2016-02-17 | 2016-03-09 | 15 |  |  |  |  | 32000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03185 | Catskill | Coxsackie |  | 10251 | G | 2002 | North Catskill | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-02-17 | 2016-03-09 | 15 | 2016-03-09 | 2016-02-17 | 2016-03-09 | 15 |  |  |  |  | 34000 | [9 empty] | W
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03186 | Poughkeepsie | Poughkeepsie |  | 12601 | G | 6068 | Inwood Ave | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-02-17 | 2016-03-09 | 15 | 2016-03-09 | 2016-02-17 | 2016-03-09 | 15 |  |  |  |  | 32000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03187 | Fishkill | Fishkill |  | 12524 | G | 8065 | Merritt Park | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-02-17 | 2016-03-09 | 15 | 2016-03-09 | 2016-02-17 | 2016-03-09 | 15 |  |  |  |  | 32000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Infinity Solar Systems | CH-00164 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6065 | Inwood Ave | N |  | 14.72 | [13 empty] | NM | N | (46) SUNPOWER SPR-E20-327 | 2016-05-09 | 2016-05-11 | 2 | 2016-05-11 | [14 empty] | 2016-07-13 | 2016-09-15 |  | Y
Central Hudson |  | NRG Home Solar | CH-00516 | Newburgh | Newburgh | Orange | 12550 | G | 4053 | Union Ave | N |  | 10 | [13 empty] | NM | N | SOLAREDGE SE10000A-US | 2016-02-11 | 2016-02-26 | 10 | 2016-02-26 | [14 empty] | 2016-06-01 | 2016-06-03 |  | Y
Central Hudson |  | Monolith Solar Associates LLC | CH-02697 | Catskill | Coeymans |  | 12143 | G | 1081 | New Baltimore | TBD |  | 240 | [13 empty] | RNM | N | SOLAR EDGE SE20KUS (12) | 2016-03-01 | 2016-03-22 | 15 | 2016-03-22 | 2016-03-01 | 2016-03-22 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | SolarCity | CH-04938 | Catskill | Coxsackie | Greene | 12051 | G | 1072 | Coxsackie | N |  | 5 | [13 empty] | NM | N | ABB PVI 5000 | 2016-02-11 | 2016-02-26 | 10 | 2016-02-26 | [14 empty] | 2016-03-11 | 2016-03-23 |  | Y
Central Hudson |  | SolarCity | CH-05339 | Newburgh | Clintondale | Ulster | 12515 | G | 5024 | Ohioville | N |  | 5 | [13 empty] | NM | N | ABB PVI-5000OUTD-US | 2016-02-11 | 2016-02-26 | 10 | 2016-02-26 | [14 empty] | 2016-05-11 | 2016-05-17 |  | Y
Central Hudson |  | SolarCity | CH-05602 | Catskill | New Baltimore | Greene | 12124 | G | 1083 | New Baltimore | N |  | 4.2 | [13 empty] | NM | N | ABB PVI-4.2 OUTD-S-US | 2016-02-11 | 2016-02-26 | 10 | 2016-02-26 | [14 empty] | 2016-03-21 | 2016-03-29 |  | Y
Central Hudson |  | SolarCity | CH-05694 | Kingston | Kingston | Ulster | 12401 | G | 2093 | Hurley Ave | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000 OUTD-US | 2016-02-11 | 2016-02-26 | 10 | 2016-02-26 | [14 empty] | 2016-04-12 | 2016-04-15 |  | Y
Central Hudson |  | SolarCity | CH-05929 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 7024 | Tinkertown | N |  | 10.2 | [13 empty] | NM | N | (1) ABB PVI 6000 (1) ABB PVI 4.2 | 2016-02-11 | 2016-02-19 | 5 | 2016-02-19 | [14 empty] | 2016-03-10 | 2016-03-17 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06413 | Newburgh | Montgomery | Orange | 12549 | G | 5073 | Montgomery | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2016-02-11 | 2016-02-26 | 10 | 2016-02-26 | [14 empty] | 2016-05-05 | 2016-05-10 |  | Y
Central Hudson |  | SolarCity | CH-06921 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8055 | North Chelsea | N |  | 10 | [13 empty] | NM | N | ABB PVI 5000 (2) | 2016-02-11 | 2016-02-26 | 10 | 2016-02-26 | [14 empty] | 2016-06-24 | 2016-07-01 |  | Y
Central Hudson |  | SolarCity | CH-06981 | Newburgh | Walden | Orange | 12586 | G | 5041 | East Walden | N |  | 9 | [13 empty] | NM | N | ABB PVI-6000 ABB PVI-3.0 | 2016-02-11 | 2016-02-26 | 10 | 2016-02-26 | [14 empty] | 2016-03-29 | 2016-04-05 |  | Y
Central Hudson |  | SolarCity | CH-07728 | Catskill | Palenvl | Greene | 12463 | G | 2001 | North Catskill | N |  | 4.2 | [13 empty] | NM | N | ABB PVI 4.2 | 2016-02-11 | 2016-02-26 | 10 | 2016-02-26 | [14 empty] | 2016-02-29 | 2016-03-07 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07860 | Kingston | Mount Tremper |  | 12457 | G | 3012 | Woodstock | TBD |  | 3 | [13 empty] | NM | N | ABB PVI 3.0 | 2016-02-11 | 2016-02-26 | 10 | 2016-02-26 | [17 empty] | W
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03188 | Catskill | Freehold |  | 12431 | G | 2071 | Freehold | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-02-17 | 2016-03-09 | 15 | 2016-03-09 | 2016-02-17 | 2016-03-09 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03189 | Newburgh | Gardiner |  | 12525 | G | 5033 | Galeville | TBD |  | 1980 | [13 empty] | CDG | N | (44) Huawei SUN2000-45KTL-US | 2016-02-17 | 2016-03-09 | 15 | 2016-03-09 | 2016-02-17 | 2016-03-09 | 15 | 2016-06-21 | 2016-06-21 | 2016-09-15 | 60 | 27858.05 | 152660 | 4700 | 2017-06-23 | 2017-12-19 | 2017-12-19 |  |  |  | 2018-09-18 | W
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03190 | Kingston | Saugerties |  | 12477 | G | 3014 | Woodstock | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-02-19 | 2016-03-11 | 15 | 2016-03-11 | 2016-02-19 | 2016-03-11 | 15 |  |  |  |  | 32000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Apex Solar Power | CH-00690 | Kingston | High Fls | Ulster | 12440 | G | 3024 | High Falls | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A-US | 2016-02-12 | 2016-02-29 | 10 | 2016-02-29 | [14 empty] | 2016-05-13 | 2016-05-20 |  | Y
Central Hudson |  | SolarCity | CH-05150 | Kingston | Saugerties | Ulster | 12477 | G | 3002 | Saugerties | N |  | 16.4 | [13 empty] | NM | N | 2 FRONIUS PRIMO 8.2 | 2016-02-12 | 2016-02-29 | 10 | 2016-02-29 | [14 empty] | 2016-03-21 | 2016-03-29 |  | Y
Central Hudson |  | SolarCity | CH-05508 | Catskill | S Cairo | Greene | 12482 | G | 2005 | North Catskill | N |  | 14.6 | [13 empty] | NM | N | ABB PVI-6.0 OUTD-S-US ABB PVI-5.0 OUTD-S-US ABB PVI-3.6 OUTD-S-US | 2016-02-12 | 2016-02-29 | 10 | 2016-02-29 | [14 empty] | 2016-03-03 | 2016-03-10 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06354 | Newburgh | Modena | Ulster | 12548 | G | 5012 | Modena | N |  | 4.2 | [13 empty] | NM | N | ABB PVI 4.2 | 2016-02-12 | 2016-02-29 | 10 | 2016-02-29 | [14 empty] | 2016-05-12 | 2016-05-17 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06840 | Fishkill | Stormvl | Dutchess | 12582 | G | 8095 | Fishkill Plains | N |  | 12 | [13 empty] | NM | N | ABB PVI 6000 (2) | 2016-02-12 | 2016-02-29 | 10 | 2016-02-29 | [14 empty] | 2016-03-24 | 2016-04-05 |  | Y
Central Hudson |  | SolarCity | CH-07439 | Newburgh | Newburgh | Orange | 12550 | G | 4046 | Union Ave | N |  | 3 | [13 empty] | NM | N | ABB PVI 3.0 | 2016-02-12 | 2016-02-29 | 10 | 2016-02-29 | [14 empty] | 2016-03-17 | 2016-03-24 |  | Y
Central Hudson |  | SolarCity | CH-07963 | Catskill | Coxsackie |  | 12051 | G | 1072 | Coxsackie | TBD |  | 1992 | [13 empty] | CDG | N | FRONIUS SYMO 24 (83) | 2016-04-27 | 2016-04-27 | 0 | 2016-04-27 | 2016-04-27 | 2016-05-18 | 15 |  |  |  |  | 32000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | SolarCity | CH-07964 | Poughkeepsie | Lagrange |  | 12603 | G | 6091 | Manchester | TBD |  | 1992 | [13 empty] | CDG | N | FRONIUS SYMO 24 (83) | 2016-03-18 | 2016-04-11 | 15 | 2016-04-11 | 2016-03-18 | 2016-04-11 | 15 |  |  |  |  | 32000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | SolarCity | CH-07965 | Newburgh | Newburgh |  | 12553 | G | 4047 | Union Ave | TBD |  | 1992 | [13 empty] | CDG | N | FRONIUS SYMO 24 (83) | 2016-03-18 | 2016-04-11 | 15 | 2016-04-11 | 2016-03-18 | 2016-04-11 | 15 |  |  |  |  | 32000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | SolarCity | CH-07966 | Poughkeepsie | Millerton |  | 12546 | G | 7081 | Millerton | TBD |  | 1992 | [13 empty] | CDG | N | FRONIUS SYMO 24 (83) | 2016-03-18 | 2016-04-11 | 15 | 2016-04-11 | 2016-03-18 | 2016-04-11 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | SolarCity | CH-07967 | Poughkeepsie | Rhinebeck |  | 12572 | G | 7053 | Rhinebeck | TBD |  | 1992 | [13 empty] | CDG | N | FRONIUS SYMO 24 (83) | 2016-03-18 | 2016-04-11 | 15 | 2016-04-11 | 2016-03-18 | 2016-04-11 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | SolarCity | CH-07968 | Catskill | Catskill |  | 12414 | G | 2001 | North Catskill | TBD |  | 1992 | [13 empty] | CDG | N | FRONIUS SYMO 24 (83) | 2016-03-21 | 2016-04-11 | 14 | 2016-04-11 | 2016-03-21 | 2016-04-11 | 14 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Apex Solar Power | CH-03084 | Fishkill | Fishkill | Dutchess | 12524 | G | 8055 | North Chelsea | N |  | 7.6 | [13 empty] | NM | N | SOLAR EDGE SE7600A-US | 2016-02-16 | 2016-02-29 | 9 | 2016-02-29 | [14 empty] | 2016-04-01 | 2016-04-07 |  | Y
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03191 | Newburgh | New Windsor |  | 12553 | G | 4091 | Bethlehem Rd | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-02-23 | 2016-03-15 | 15 | 2016-03-15 | 2016-02-23 | 2016-03-15 | 15 |  |  |  |  | 32000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03192 | Newburgh | New Windsor |  | 12553 | G | 4097 | Bethlehem Rd | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-02-23 | 2016-03-15 | 15 | 2016-03-15 | 2016-02-23 | 2016-03-15 | 15 |  |  |  |  | 32000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03193 | Newburgh | Walden |  | 12586 | G | 5041 | East Walden | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-02-23 | 2016-03-15 | 15 | 2016-03-15 | 2016-02-23 | 2016-03-15 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03194 | Poughkeepsie | Pine Plains |  | 12567 | G | 7091 | Pulvers Corners | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-02-23 | 2016-03-15 | 15 | 2016-03-15 | 2016-02-23 | 2016-03-15 | 15 |  |  |  |  | 32000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03195 | Newburgh | Walden |  | 12586 | G | 4026 | Coldenham | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-03-23 | 2016-04-13 | 14 | 2016-04-13 | 2016-03-23 | 2016-04-13 | 14 |  |  |  |  | 40000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03196 | Poughkeepsie | Millerton |  | 12546 | G | 7092 | Pulvers Corners | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-02-23 | 2016-03-15 | 15 | 2016-03-15 | 2016-02-23 | 2016-03-15 | 15 |  |  |  |  | 32000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03197 | Poughkeepsie | Poughkeepsie |  | 12601 | G | 7024 | Tinkertown | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-02-23 | 2016-03-15 | 15 | 2016-03-15 | 2016-02-23 | 2016-03-15 | 15 |  |  |  |  | 32000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03198 | Poughkeepsie | Rhinebeck |  | 12572 | G | 7061 | Milan | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-02-23 | 2016-03-15 | 15 | 2016-03-15 | 2016-02-23 | 2016-03-15 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | CESIR determined necessary during preliminary review Section C, Step 4.
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03199 | Poughkeepsie | Redhook |  | 12571 | G | 7062 | Milan | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-02-23 | 2016-03-15 | 15 | 2016-03-15 | 2016-02-23 | 2016-03-15 | 15 |  |  |  |  | 32000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | EnterSolar LLC | CH-03346 | Fishkill | Wappingrs Falls |  | 12590 | G | 8051 | North Chelsea | TBD |  | 1980 | [13 empty] | CDG | N | SOLECTRIA PVI 36TL (55) | 2016-03-14 | 2016-04-05 | 15 | 2016-04-05 | 2016-03-14 | 2016-04-05 | 15 |  |  |  |  | 32000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Infinity Solar Systems | CH-03427 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 10.8 | [13 empty] | NM | N | SMA SB7000TL-US-22 SMA SB3800TL-US-22 | 2016-02-16 | 2016-02-29 | 9 | 2016-02-29 | [14 empty] | 2016-06-22 | 2016-06-28 |  | Y
Central Hudson |  | Kasselman Solar | CH-03529 | Catskill | Catskill | Greene | 12414 | G | 2003 | North Catskill | N |  | 3.08 | [13 empty] | NM | N | 11 ENPHASE S280-US | 2016-02-16 | 2016-02-23 | 5 | 2016-02-23 | [14 empty] | 2016-04-14 | 2016-04-19 |  | Y
Central Hudson |  | Hudson Solar | CH-01359 | Kingston | Kingston | Ulster | 12401 | G | 1022 | East Kingston | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE-6000A-US-U | 2016-02-16 | 2016-03-01 | 10 | 2016-03-01 | [14 empty] | 2016-06-21 | 2016-06-24 |  | Y
Central Hudson |  | Hudson Solar | CH-01761 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 6074 | East Park | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE-7600A-US-U | 2016-02-16 | 2016-02-23 | 5 | 2016-02-23 | [14 empty] | 2016-03-30 | 2016-04-06 |  | Y
Central Hudson |  | Hudson Solar | CH-01988 | Newburgh | Newburgh | Orange | 12550 | G | 4094 | Bethlehem Rd | N |  | 10 | [13 empty] | NM | N | SOLAREDGE SE-10000A-US-U | 2016-02-16 | 2016-02-29 | 9 | 2016-02-29 | [14 empty] | 2016-03-31 | 2016-04-07 |  | Y
Central Hudson |  | Hudson Solar | CH-02010 | Catskill | West Kill | Greene | 12492 | E | 2389 | Vinegar Hill | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE-6000A-US-U | 2016-02-16 | 2016-03-01 | 10 | 2016-03-01 | [14 empty] | 2016-04-11 | 2016-04-15 |  | Y
Central Hudson |  | Hudson Solar | CH-02121 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7051 | Rhinebeck | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE-6000A-US-U | 2016-02-16 | 2016-03-01 | 10 | 2016-03-01 | [14 empty] | 2016-05-16 | 2016-05-23 |  | Y
Central Hudson |  | Mannino Electric | CH-02604 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8092 | Fishkill Plains | N |  | 10 | [13 empty] | NM | N | SOLAREDGE SE10A-US | 2016-02-16 | 2016-02-29 | 9 | 2016-02-29 | [14 empty] | 2016-06-03 | 2016-06-07 |  | Y
Central Hudson |  | Monolith Solar Associates LLC | CH-02656 | Catskill | Hannacroix | Greene | 12087 | G | 2061 | Freehold | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000 A-US | 2016-02-16 | 2016-03-01 | 10 | 2016-03-01 | [14 empty] | 2016-06-20 | 2016-06-23 |  | Y
Central Hudson |  | Murphy Solar Power | CH-02753 | Catskill | Palenvl | Greene | 12463 | G | 2001 | North Catskill | N |  | 8 | [13 empty] | NM | N | SMA 8000 US | 2016-02-16 | 2016-03-01 | 10 | 2016-03-01 | [14 empty] | 2016-06-15 | 2016-06-20 |  | Y
Central Hudson |  | Solar Liberty Energy Systems | CH-04903 | Catskill | Freehold | Greene | 12431 | G | 2071 | Freehold | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE7600A-US | 2016-02-16 | 2016-03-01 | 10 | 2016-03-01 | [14 empty] | 2016-07-20 | 2016-07-20 |  | Y
Central Hudson |  | SolarCity | CH-05572 | Catskill | Westerlo | Albany | 12193 | G | 1091 | Westerlo | N |  | 3 | [13 empty] | NM | N | ABB PVI 3.0 | 2016-02-16 | 2016-03-01 | 10 | 2016-03-01 | [14 empty] | 2016-03-21 | 2016-04-01 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-05690 | Kingston | Kingston | Ulster | 12401 | G | 1003 | Jansen Ave | N |  | 5 | [13 empty] | NM | N | ABB PVI-5000 OUTD-US | 2016-02-16 | 2016-03-01 | 10 | 2016-03-01 | [14 empty] | 2016-04-28 | 2016-04-28 |  | Y
Central Hudson |  | SolarCity | CH-05706 | Kingston | Kingston |  | 12401 | G | 2091 | Hurley Ave | TBD |  | 4.2 | [13 empty] | NM | N | ABB PVI-4.2 OUTD-S-US | 2016-02-16 | 2016-03-01 | 10 | 2016-03-01 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | SolarCity | CH-05781 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6046 | Spackenkill | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2016-02-16 | 2016-02-23 | 5 | 2016-02-23 | [14 empty] | 2016-04-12 | 2016-04-14 |  | Y
Central Hudson |  | SolarCity | CH-07969 | Poughkeepsie | Rhinebeck |  | 12572 | G | 7052 | Rhinebeck | TBD |  | 1992 | [13 empty] | CDG | N | (83) FRONIUS SYMO 24 | 2016-03-18 | 2016-04-11 | 15 | 2016-04-11 | 2016-03-18 | 2016-04-11 | 15 |  |  |  |  | 32000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | SolarCity | CH-07970 | Newburgh | Rock Tavern |  | 12575 | G | 4021 | Coldenham | TBD |  | 1992 | [13 empty] | CDG | N | (83) FRONIUS SYMO 24 | 2016-03-21 | 2016-04-12 | 15 | 2016-04-12 | 2016-03-21 | 2016-04-12 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Trinity Solar | CH-08454 | Newburgh | Wallkill | Ulster | 12589 | G | 5013 | Modena | N |  | 7.6 | [13 empty] | NM | N | SOLAR EDGE 7600A-US | 2016-03-10 | 2016-03-24 | 10 | 2016-03-24 | [14 empty] | 2016-05-12 | 2016-05-19 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08613 | Kingston | Kingston |  | 12401 | G | 1014 | Boulevard | TBD |  | 7.09 | [13 empty] | NM | N | 33 ENPHASE M215 602LLS2XZC | 2016-02-16 | 2016-03-01 | 10 | 2016-03-01 | [17 empty] | W
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08645 | Catskill | Freehold | Greene | 12431 | G | 2071 | Freehold | N |  | 12.255 | [13 empty] | NM | N | 57 ENPHASE M215 602LLS2XZC | 2016-02-16 | 2016-03-01 | 10 | 2016-03-01 | [14 empty] | 2016-07-27 | 2016-07-27 |  | Y
Central Hudson |  | Sol Providers | CH-08952 | Fishkill | Fishkill | Dutchess | 12524 | G | 8065 | Merritt Park | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE7000AUS | 2016-02-16 | 2016-02-29 | 9 | 2016-02-29 | [14 empty] | 2016-03-14 | 2016-03-21 |  | Y
Central Hudson |  | Sungevity Inc | CH-09625 | Poughkeepsie | Rhinebeck |  | 12572 | G | 7052 | Rhinebeck | TBD |  | 4.2 | [13 empty] | NM | N | ABB PVI-4.2-OUTD-S-US-A | 2016-02-16 | 2016-02-23 | 5 | 2016-02-23 | [17 empty] | W
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03200 | Kingston | Stone Ridge |  | 12484 | G | 3023 | High Falls | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-02-23 | 2016-03-15 | 15 | 2016-03-15 | 2016-02-23 | 2016-03-15 | 15 |  |  |  |  | 32000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Generate Capital | CH-03201 | Newburgh | Modena | Ulster | 12548 | G | 5012 | Modena | N |  | 1980 | [13 empty] | CDG | N | 44 Huawei Sun2000-45kTL | 2016-02-23 | 2016-03-15 | 15 | 2016-03-15 | 2016-02-23 | 2016-03-15 | 15 | 2017-01-23 | 2017-02-06 | 2017-05-03 | 60 | 24660.01 | 359913 | 143887.91 | 2017-06-23 | 2018-03-09 | 2018-03-09 | 2024-01-12 | 2024-01-12 | 2024-01-12 | 2024-04-15 | Y | N | CESIR for 2 projects, CH-03201 and CH-03149 combined with an aggregate CESIR Cost to Customer of $25,000. Only proceeding with CH-03201.
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03202 | Kingston | Kerhonkson |  | 12446 | G | 3081 | Kerhonkson | TBD |  | 1980 | [13 empty] | CDG | N | 44 HUAWEI SUN2000-45KTL US-1500 | 2016-02-23 | 2016-03-15 | 15 | 2016-03-15 | 2016-02-23 | 2016-03-15 | 15 | 2017-01-09 | 2017-01-09 | 2017-04-04 | 60 | 32135.2 | 710538 | 15956.84 | 2017-06-23 | 2017-10-02 | 2017-10-02 |  |  |  | 2019-04-05 | W
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03203 | Kingston | Saugerties |  | 12477 | G | 3002 | Saugerties | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-02-23 | 2016-03-15 | 15 | 2016-03-15 | 2016-02-23 | 2016-03-15 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | CESIR determined necessary during preliminary review Section C, Step 4.
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03204 | Kingston | Kingston |  | 12401 | G | 2094 | Hurley Ave | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-02-23 | 2016-03-15 | 15 | 2016-03-15 | 2016-02-23 | 2016-03-15 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | CESIR determined necessary during preliminary review Section C, Step 4.
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03205 | Kingston | Saugerties |  | 12477 | G | 3002 | Saugerties | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-02-23 | 2016-03-15 | 15 | 2016-03-15 | 2016-02-23 | 2016-03-15 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03206 | Kingston | Lake Kathrine |  | 12449 | G | 2015 | Lincoln Park | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-02-23 | 2016-03-15 | 15 | 2016-03-15 | 2016-02-23 | 2016-03-15 | 15 |  |  |  |  | 32000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03207 | Kingston | Ulster | Ulster | 12401 | G | 1011 | Boulevard | N |  | 2000 | [13 empty] | CDG | N | (44) Huawei SUN2000-45KTL-US1SMASC 2000-EV | 2016-02-23 | 2016-03-15 | 15 | 2016-03-15 | 2016-02-23 | 2016-03-15 | 15 | 2016-08-26 | 2016-10-14 | 2017-01-13 | 60 | 17730.18 | 238400 | 132829.67 | 2017-06-23 | 2017-08-29 | 2017-08-29 | 2021-11-18 | 2021-12-01 | 2021-12-01 | 2022-02-18 | Y | N
Central Hudson |  | SolarCity | CH-06322 | Newburgh | Marlboro | Ulster | 12542 | G | 5001 | Marlboro | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000OUTD-US | 2016-02-17 | 2016-02-29 | 8 | 2016-02-29 | [14 empty] | 2016-03-21 | 2016-03-29 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07267 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6046 | Spackenkill | N |  | 10 | [13 empty] | NM | N | (2) ABB PVI 5.0 | 2016-02-17 | 2016-02-24 | 5 | 2016-02-24 | [14 empty] | 2016-04-05 | 2016-04-08 |  | Y
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03208 | Newburgh | Newburgh |  | 12550 | G | 4015 | West Balmville | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-02-24 | 2016-03-16 | 15 | 2016-03-16 | 2016-02-24 | 2016-03-16 | 15 |  |  |  |  | 32000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03209 | Poughkeepsie | Ancramdale |  | 12503 | G | 7092 | Pulvers Corners | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-02-24 | 2016-03-16 | 15 | 2016-03-16 | 2016-02-24 | 2016-03-16 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03210 | Poughkeepsie | Ancramdale |  | 12503 | G | 7092 | Pulvers Corners | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-02-24 | 2016-03-16 | 15 | 2016-03-16 | 2016-02-24 | 2016-03-16 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03211 | Catskill | Coxsackie |  | 12192 | G | 1076 | Coxsackie | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-02-24 | 2016-03-16 | 15 | 2016-03-16 | 2016-02-24 | 2016-03-16 | 15 |  |  |  |  | 32000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03212 | Catskill | W Coxsackie |  | 12192 | G | 1081 | New Baltimore | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-02-24 | 2016-03-16 | 15 | 2016-03-16 | 2016-02-24 | 2016-03-16 | 15 |  |  |  |  | 32000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03213 | Catskill | W Coxsackie |  | 12192 | G | 1083 | New Baltimore | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-02-24 | 2016-03-03 | 6 | 2016-03-03 | 2016-02-24 | 2016-03-03 | 6 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03214 | Catskill | Freehold |  | 12431 | G | 2071 | Freehold | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-02-24 | 2016-03-16 | 15 | 2016-03-16 | 2016-02-24 | 2016-03-16 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Infinity Solar Systems | CH-03443 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6046 | Spackenkill | N |  | 9.8 | [13 empty] | NM | N | (1) SMA SB6000TL-22 (1) SMA SB3800TL-22 | 2016-02-26 | 2016-03-11 | 10 | 2016-03-11 | [14 empty] | 2016-05-09 | 2016-05-11 |  | Y
Central Hudson |  | NRG Home Solar | CH-04238 | Catskill | Acra | Greene | 12405 | G | 2041 | South Cairo | N |  | 5 | [13 empty] | NM | N | 20 ENPHASE M250 | 2016-02-18 | 2016-03-02 | 9 | 2016-03-02 | [14 empty] | 2016-04-19 | 2016-04-25 |  | Y
Central Hudson |  | SolarCity | CH-04942 | Kingston | Saugerties | Ulster | 12477 | G | 3001 | Saugerties | N |  | 7.8 | [13 empty] | NM | N | ABB PVI 4.2 ABB PVI 3.6 | 2016-02-18 | 2016-03-03 | 10 | 2016-03-03 | [14 empty] | 2016-03-04 | 2016-03-11 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07192 | Catskill | Westerlo | Albany | 12193 | G | 1091 | Westerlo | N |  | 5 | [13 empty] | NM | N | ABB PVI 5.0 | 2016-02-18 | 2016-03-02 | 9 | 2016-03-02 | [14 empty] | 2016-03-21 | 2016-03-29 |  | Y
Central Hudson |  | SolarCity | CH-07452 | Newburgh | Marlboro | Ulster | 12542 | G | 5004 | Marlboro | N |  | 8.2 | [13 empty] | NM | N | FRONIUS PRIMO 8.2 | 2016-02-18 | 2016-03-03 | 10 | 2016-03-03 | [14 empty] | 2016-03-31 | 2016-04-06 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07896 | Fishkill | Beacon |  | 12508 | G | 8051 | North Chelsea | TBD |  | 4.2 | [13 empty] | NM | N | ABB PVI-4.2OUTD-S-US | 2016-04-12 | 2016-04-18 | 4 | 2016-04-18 | [17 empty] | W
Central Hudson |  | Solar Generation | CH-08254 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7054 | Rhinebeck | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE 7600A US | 2016-02-29 | 2016-03-07 | 5 | 2016-03-07 | [14 empty] | 2016-04-13 | 2016-04-20 |  | Y
Central Hudson |  | Trinity Solar | CH-08442 | Fishkill | Beacon | Dutchess | 12508 | G | 8087 | Tioronda | N |  | 3 | [13 empty] | NM | N | SOLAR EDGE 3000A-US | 2016-02-26 | 2016-03-11 | 10 | 2016-03-11 | [14 empty] | 2016-05-24 | 2016-05-24 |  | Y
Central Hudson |  | Trinity Solar | CH-08452 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 5 | [13 empty] | NM | N | SOLAR EDGE 5000A-US | 2016-02-26 | 2016-03-11 | 10 | 2016-03-11 | [14 empty] | 2016-04-19 | 2016-04-21 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Trinity Solar | CH-08463 | Catskill | Coeymans Hollow | Albany | 12046 | G | 1081 | New Baltimore | N |  | 7.6 | [13 empty] | NM | N | SOLAR EDGE 7600A-US | 2016-02-18 | 2016-03-03 | 10 | 2016-03-03 | [14 empty] | 2016-05-17 | 2016-05-17 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08826 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7052 | Rhinebeck | N | CH-00800 | 3.44 | [13 empty] | NM | N | (16) ENPHASE M215 | 2016-03-21 | 2016-04-05 | 10 | 2016-04-05 | [14 empty] | 2016-06-21 | 2016-06-28 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08833 | Kingston | Port Ewen |  | 12466 | G | 1012 | Boulevard | TBD |  | 4.08 | [13 empty] | NM | N | 19 ENPHASE M215 602LLS2XZC | 2016-02-18 | 2016-03-03 | 10 | 2016-03-03 | [17 empty] | W
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03216 | Poughkeepsie | Salt Point |  | 12578 | G | 7011 | Hibernia | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-02-26 | 2016-03-17 | 14 | 2016-03-17 | 2016-02-26 | 2016-03-17 | 14 |  |  |  |  | 32000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03218 | Poughkeepsie | Millerton |  | 12546 | G | 7092 | Pulvers Corners | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-02-24 | 2016-03-16 | 15 | 2016-03-16 | 2016-02-24 | 2016-03-16 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | CESIR determined necessary during preliminary review Section C, Step 4.
Central Hudson |  | Apex Solar Power | CH-00716 | Fishkill | Cold Spg |  | 10516 | G | 8086 | Tioronda | TBD |  | 3.8 | [13 empty] | NM | N | SOLAR EDGE SE 3800A-US | 2016-02-19 | 2016-03-04 | 10 | 2016-03-04 | [17 empty] | W
Central Hudson |  | SolarCity | CH-04964 | Kingston | Saugerties | Ulster | 12477 | G | 3002 | Saugerties | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000 OUTD-US | 2016-02-19 | 2016-03-04 | 10 | 2016-03-04 | [14 empty] | 2016-03-21 | 2016-04-01 |  | Y
Central Hudson |  | SolarCity | CH-05351 | Catskill | Durham | Greene | 12422 | G | 1092 | Westerlo | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2016-02-19 | 2016-03-04 | 10 | 2016-03-04 | [14 empty] | 2016-03-15 | 2016-03-22 |  | Y
Central Hudson |  | SolarCity | CH-06041 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8046 | Myers Corners | N |  | 7.8 | [13 empty] | NM | N | ABB PVI 3.6 ABB PVI 4.2 | 2016-03-28 | 2016-04-06 | 7 | 2016-04-06 | [14 empty] | 2016-04-07 | 2016-04-11 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06343 | Newburgh | Gardiner | Ulster | 12525 | G | 5031 | Galeville | N |  | 7.8 | [13 empty] | NM | N | ABB PVI 4.2 ABB PVI 3.6 | 2016-02-19 | 2016-03-04 | 10 | 2016-03-04 | [14 empty] | 2016-03-15 | 2016-03-22 |  | Y
Central Hudson |  | SolarCity | CH-07676 | Newburgh | Newburgh | Orange | 12550 | G | 4054 | Union Ave | N |  | 3 | [13 empty] | NM | N | ABB PVI 3.0 | 2016-02-19 | 2016-03-04 | 10 | 2016-03-04 | [14 empty] | 2016-05-02 | 2016-05-06 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08659 | Kingston | Rosendale | Ulster | 12472 | G | 3022 | High Falls | N |  | 5.59 | [13 empty] | NM | N | 26 ENPHASE M215 602LLS2XZC | 2016-02-19 | 2016-03-04 | 10 | 2016-03-04 | [14 empty] | 2016-06-21 | 2016-06-24 |  | Y
Central Hudson |  | Sungevity Inc | CH-09468 | Newburgh | Highland | Ulster | 12528 | G | 5081 | Highland | N |  | 6 | [13 empty] | NM | N | ABB PVI-3.0-OUTD-S-US-A (2) | 2016-02-26 | 2016-03-11 | 10 | 2016-03-11 | [14 empty] | 2016-05-27 | 2016-06-01 |  | Y
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03215 | Newburgh | Newburgh |  | 12550 | G | 4024 | Coldenham | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-02-24 | 2016-03-16 | 15 | 2016-03-16 | 2016-02-24 | 2016-03-16 | 15 |  |  |  |  | 32000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03217 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6061 | Inwood Ave | Y |  | 2000 | 2000 | [12 empty] | CDG | Y | 1 Power Electronics FS2000K (600V) (44) Huawei SUN2000-45KTL-US-15001Power ElectronicsFS2000K | 2016-03-16 | 2016-03-16 | 0 | 2016-03-16 | 2016-02-24 | 2016-03-16 | 15 | 2016-11-08 | 2016-11-09 | 2017-02-08 | 60 | 22833.11 | 764750 | 110636.2 | 2017-11-01 | 2018-04-20 | 2018-04-20 | 2020-11-24 | 2021-01-08 | 2021-01-08 | 2021-03-23 | Y | Y
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03219 | Newburgh | Modena |  | 12548 | G | 5012 | Modena | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-02-24 | 2016-03-16 | 15 | 2016-03-16 | 2016-02-24 | 2016-03-16 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Green Street Power Partners, LLC | CH-03363 | Newburgh | Newburgh |  | 12550 | G | 5001 | Marlboro | TBD |  | 1740 | [13 empty] | CDG | N | SMA STP-30000TLUS-10 (58) | 2016-04-04 | 2016-04-25 | 15 | 2016-04-25 | 2016-04-04 | 2016-04-25 | 15 | 2016-11-22 | 2017-01-16 | 2017-04-10 | 59 | 20000 | [9 empty] | W |  | CESIR for 2 projects combined with an aggregate CESIR Cost to Customer of $40,000.
Central Hudson |  | New York State Solar Farm | CH-04054 | Newburgh | Cornwall-Hdsn | Orange | 12520 | G | 4043 | Union Ave | N |  | 7.7 | [13 empty] | NM | N | SMA AMERICA 7700SB | 2016-03-02 | 2016-03-16 | 10 | 2016-03-16 | [14 empty] | 2016-04-14 | 2016-04-18 |  | Y
Central Hudson |  | SolarCity | CH-05132 | Fishkill | Beacon | Dutchess | 12508 | G | 8085 | Tioronda | N |  | 11 | [13 empty] | NM | N | ABB PVI6000 ABB PVI5000 | 2016-02-22 | 2016-03-07 | 10 | 2016-03-07 | [14 empty] | 2016-06-23 | 2016-06-29 |  | Y
Central Hudson |  | SolarCity | CH-06189 | Newburgh | Newburgh | Orange | 12550 | G | 4054 | Union Ave | N |  | 3 | [13 empty] | NM | N | ABB PVI 3.0 | 2016-02-22 | 2016-03-07 | 10 | 2016-03-07 | [14 empty] | 2016-05-02 | 2016-05-06 |  | Y
Central Hudson |  | Trinity Solar | CH-08401 | Kingston | Kingston | Ulster | 12401 | G | 1022 | East Kingston | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SB6000A-US | 2016-02-22 | 2016-03-07 | 10 | 2016-03-07 | [14 empty] | 2016-08-05 | 2016-08-05 |  | Y
Central Hudson |  | Green Street Power Partners, LLC | CH-03364 | Newburgh | Newburgh |  | 12550 | G | 5001 | Marlboro | TBD |  | 1320 | [13 empty] | CDG | N | SMA STP-30000TLUS-10 (44) | 2016-04-04 | 2016-04-25 | 15 | 2016-04-25 | 2016-04-04 | 2016-04-25 | 15 | 2016-11-22 | 2017-01-16 | 2017-04-10 | 59 | 20000 | [9 empty] | W |  | CESIR for 2 projects combined with an aggregate CESIR Cost to Customer of $40,000.
Central Hudson |  | SolarCity | CH-05507 | Catskill | Leeds | Greene | 12451 | G | 2005 | North Catskill | N |  | 7.2 | [13 empty] | NM | N | ABB PVI-4.2 OUTD-S-US ABB PVI-3.0 OUTD-S-US | 2016-02-23 | 2016-03-08 | 10 | 2016-03-08 | [14 empty] | 2016-03-31 | 2016-04-07 |  | Y
Central Hudson |  | SolarCity | CH-06188 | Newburgh | Highland | Ulster | 12528 | G | 5081 | Highland | N |  | 3 | [13 empty] | NM | N | ABB PVI-3.0OUTD-S-US | 2016-03-29 | 2016-04-06 | 6 | 2016-04-06 | [14 empty] | 2016-04-11 | 2016-04-12 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06230 | Newburgh | Newburgh | Orange | 12550 | G | 4015 | West Balmville | N |  | 9 | [13 empty] | NM | N | ABB PVI-6000OUTD-US ABB PVI-3.0OUTD-US | 2016-02-23 | 2016-03-07 | 9 | 2016-03-07 | [14 empty] | 2016-03-21 | 2016-03-29 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Sunrun Inc. | CH-08348 | Newburgh | Milton | Ulster | 12547 | G | 5002 | Marlboro | N |  | 5.75 | [13 empty] | NM | N | ENPHASE M250-60-2LL-S2X (23) | 2016-02-23 | 2016-03-07 | 9 | 2016-03-07 | [14 empty] | 2016-04-19 | 2016-04-21 |  | Y
Central Hudson |  | Trinity Solar | CH-08377 | Kingston | Grahamsvl | Sullivan | 12740 | G | 3091 | Neversink | N |  | 10 | [13 empty] | NM | N | SOLAREDGE SB10000A-US | 2016-02-23 | 2016-03-08 | 10 | 2016-03-08 | [14 empty] | 2016-03-31 | 2016-04-07 |  | Y
Central Hudson |  | New York State Solar Farm | CH-04089 | Poughkeepsie | Lagrangevl | Dutchess | 12540 | G | 6053 | Todd Hill | N |  | 7.6 | [13 empty] | NM | N | (2) SMA AMERICA SB3800-TL | 2016-02-24 | 2016-03-09 | 10 | 2016-03-09 | [14 empty] | 2016-06-14 | 2016-06-21 |  | Y
Central Hudson |  | NRG Home Solar | CH-00523 | Newburgh | Maybrook | Orange | 12543 | G | 5052 | Maybrook | N |  | 3.22 | [13 empty] | NM | N | ENPHASE M215 (15) | 2016-02-24 | 2016-03-09 | 10 | 2016-03-09 | [14 empty] | 2016-05-05 | 2016-05-12 |  | Y
Central Hudson |  | SolarCity | CH-07241 | Kingston | Saugerties | Ulster | 12477 | G | 2015 | Lincoln Park | N |  | 3 | [13 empty] | NM | N | ABB PVI 3.0 | 2016-02-24 | 2016-03-09 | 10 | 2016-03-09 | [14 empty] | 2016-03-09 | 2016-03-16 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07971 | Catskill | Medusa |  | 12120 | G | 1092 | Westerlo | TBD |  | 1992 | [13 empty] | CDG | N | FRONIUS 24 (83) | 2016-03-18 | 2016-04-11 | 15 | 2016-04-11 | 2016-03-18 | 2016-04-11 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | SolarCity | CH-07972 | Poughkeepsie | Stanfordville |  | 12581 | G | 7072 | Stanfordville | TBD |  | 1992 | [13 empty] | CDG | N | FRONIUS 24 (83) | 2016-03-18 | 2016-04-11 | 15 | 2016-04-11 | 2016-03-18 | 2016-04-11 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | SolarCity | CH-07973 | Poughkeepsie | Salt Point |  | 12578 | G | 7011 | Hibernia | TBD |  | 1992 | [13 empty] | CDG | N | FRONIUS 24 (83) | 2016-03-21 | 2016-04-12 | 15 | 2016-04-12 | 2016-03-21 | 2016-04-12 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Trinity Solar | CH-08469 | Kingston | New Paltz | Ulster | 12561 | G | 3022 | High Falls | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A-US | 2016-02-24 | 2016-03-09 | 10 | 2016-03-09 | [14 empty] | 2016-03-28 | 2016-04-07 |  | Y
Central Hudson |  | Trinity Solar | CH-08478 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6095 | Manchester | N |  | 5 | [13 empty] | NM | N | SolarEdge SE5000A-US | 2016-02-24 | 2016-03-09 | 10 | 2016-03-09 | [14 empty] | 2016-04-14 | 2016-04-25 |  | Y
Central Hudson |  | SolarCity | CH-05033 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7051 | Rhinebeck | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2016-03-16 | 2016-03-23 | 5 | 2016-03-23 | [14 empty] | 2016-05-02 | 2016-05-06 |  | Y
Central Hudson |  | SolarCity | CH-05162 | Newburgh | Newburgh |  | 12550 | G | 406 | Montgomery St | TBD |  | 3 | [13 empty] | NM | N | SOLAREDGE SE3000A | 2016-02-25 | 2016-03-10 | 10 | 2016-03-10 | [17 empty] | W
Central Hudson |  | SolarCity | CH-05419 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8095 | Fishkill Plains | N |  | 15.2 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 (2) | 2016-04-01 | 2016-04-07 | 4 | 2016-04-07 | [14 empty] | 2016-05-04 | 2016-05-06 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-05603 | Catskill | Coeymans | Albany | 12045 | G | 1082 | New Baltimore | N |  | 3.6 | [13 empty] | NM | N | ABB PVI 3.6 | 2016-02-25 | 2016-03-10 | 10 | 2016-03-10 | [14 empty] | 2016-06-01 | 2016-06-02 |  | Y
Central Hudson |  | SolarCity | CH-06469 | Catskill | Coxsackie | Greene | 12051 | G | 1071 | Coxsackie | N |  | 6 | [13 empty] | NM | N | ABB PVI 6.0 | 2016-02-25 | 2016-03-10 | 10 | 2016-03-10 | [14 empty] | 2016-03-21 | 2016-03-29 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07364 | Fishkill | Fishkill | Dutchess | 12524 | G | 8094 | Fishkill Plains | N |  | 15.2 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 (2) | 2016-02-25 | 2016-03-10 | 10 | 2016-03-10 | [14 empty] | 2016-05-11 | 2016-05-17 |  | Y
Central Hudson |  | SolarCity | CH-07743 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8014 | Forgebrook | N |  | 3 | [13 empty] | NM | N | ABB PVI 3.0 | 2016-02-25 | 2016-03-10 | 10 | 2016-03-10 | [14 empty] | 2016-03-17 | 2016-03-24 |  | Y
Central Hudson |  | SolarCity | CH-07884 | Poughkeepsie | Red Hook |  | 12571 | G | 7056 | Rhinebeck | TBD |  | 5 | [13 empty] | NM | N | ABB PVI 5000 | 2016-02-25 | 2016-03-03 | 5 | 2016-03-03 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | SolarCity | CH-07974 | Poughkeepsie | Salt Point |  | 12578 | G | 7011 | Hibernia | TBD |  | 1992 | [13 empty] | CDG | N | (83) FRONIUS SYMO 24 | 2016-03-18 | 2016-04-11 | 15 | 2016-04-11 | 2016-03-18 | 2016-04-11 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | SolarCity | CH-07975 | Fishkill | Hopewelljunction |  | 12533 | G | 8072 | Shenandoah | TBD |  | 1992 | [13 empty] | CDG | N | (83) FRONIUS SYMO 24 | 2016-03-18 | 2016-04-08 | 14 | 2016-04-08 | 2016-03-18 | 2016-04-08 | 14 |  |  |  |  | 28000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | SolarCity | CH-07976 | Poughkeepsie | Millbrook |  | 12545 | G | 7025 | Tinkertown | TBD |  | 1992 | [13 empty] | CDG | N | (83) FRONIUS SYMO 24 | 2016-03-18 | 2016-04-11 | 15 | 2016-04-11 | 2016-03-18 | 2016-04-11 | 15 |  |  |  |  | 32000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | SolarCity | CH-07977 | Catskill | W Cairo |  | 12413 | G | 2042 | South Cairo | TBD |  | 1992 | [13 empty] | CDG | N | (83) FRONIUS SYMO 24 | 2016-03-18 | 2016-04-11 | 15 | 2016-04-11 | 2016-03-18 | 2016-04-11 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | SolarCity | CH-07978 | Kingston | Rochester |  | 12404 | G | 3024 | High Falls | TBD |  | 1992 | [13 empty] | CDG | N | (83) FRONIUS SYMO 24 | 2016-03-18 | 2016-04-11 | 15 | 2016-04-11 | 2016-03-18 | 2016-04-11 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | SolarCity | CH-07979 | Kingston | Marbletown |  | 12440 | G | 3023 | High Falls | TBD |  | 1992 | [13 empty] | CDG | N | (83) FRONIUS SYMO 24 | 2016-03-18 | 2016-04-11 | 15 | 2016-04-11 | 2016-03-18 | 2016-04-11 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | SolarCity | CH-07980 | Newburgh | New Paltz |  | 12561 | G | 5011 | Modena | TBD |  | 1992 | [13 empty] | CDG | N | (83) FRONIUS SYMO 24 | 2016-03-18 | 2016-04-11 | 15 | 2016-04-11 | 2016-03-18 | 2016-04-11 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | SolarCity | CH-07981 | Kingston | Marbletown |  | 12484 | G | 3024 | High Falls | TBD |  | 1992 | [13 empty] | CDG | N | (83) FRONIUS SYMO 24 | 2016-03-18 | 2016-04-11 | 15 | 2016-04-11 | 2016-03-18 | 2016-04-11 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | SolarCity | CH-07982 | Kingston | Hurley |  | 12443 | G | 2094 | Hurley Ave | TBD |  | 1992 | [13 empty] | CDG | N | (83) FRONIUS SYMO 24 | 2016-03-18 | 2016-04-11 | 15 | 2016-04-11 | 2016-03-18 | 2016-04-11 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | SolarCity | CH-07983 | Newburgh | Gardiner |  | 12525 | G | 5031 | Galeville | TBD |  | 1992 | [13 empty] | CDG | N | FRONIUS SYMO 24 (83) | 2016-03-18 | 2016-04-11 | 15 | 2016-04-11 | 2016-03-18 | 2016-04-11 | 15 |  |  |  |  | 40000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | SolarCity | CH-07985 | Newburgh | Walkill |  | 12589 | G | 5043 | East Walden | TBD |  | 1992 | [13 empty] | CDG | N | FRONIUS SYMO 24 (83) | 2016-03-18 | 2016-04-11 | 15 | 2016-04-11 | 2016-03-18 | 2016-04-11 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | SolarCity | CH-07986 | Newburgh | Walkill |  | 12589 | G | 5043 | East Walden | TBD |  | 1992 | [13 empty] | CDG | N | FRONIUS SYMO 24 (83) | 2016-03-18 | 2016-04-11 | 15 | 2016-04-11 | 2016-03-18 | 2016-04-11 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | SolarCity | CH-07987 | Newburgh | Walkill |  | 12589 | G | 5011 | Modena | TBD |  | 1992 | [13 empty] | CDG | N | FRONIUS SYMO 24 (83) | 2016-03-18 | 2016-04-11 | 15 | 2016-04-11 | 2016-03-18 | 2016-04-11 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | SolarCity | CH-07988 | Catskill | Durham |  | 12418 | G | 2043 | South Cairo | TBD |  | 1992 | [13 empty] | CDG | N | FRONIUS SYMO 24 (83) | 2016-03-18 | 2016-04-11 | 15 | 2016-04-11 | 2016-03-18 | 2016-04-11 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | SolarCity | CH-07989 | Catskill | Coxsackie |  | 12051 | G | 1076 | Coxsackie | TBD |  | 1992 | [13 empty] | CDG | N | FRONIUS SYMO 24 (83) | 2016-03-18 | 2016-04-11 | 15 | 2016-04-11 | 2016-03-18 | 2016-04-11 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | SolarCity | CH-07990 | Catskill | Lexington |  | 12452 | E | 2389 | Vinegar Hill | TBD |  | 1992 | [13 empty] | CDG | N | FRONIUS SYMO 24 (83) | 2016-03-18 | 2016-04-11 | 15 | 2016-04-11 | 2016-03-18 | 2016-04-11 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | SunBlue Energy | CH-09134 | Fishkill | Garrison | Putnam | 10524 | G | 8086 | Tioronda | N |  | 6 | [13 empty] | NM | N | SOLAR EDGE SE6000 | 2016-03-03 | 2016-03-17 | 10 | 2016-03-17 | [14 empty] | 2016-10-04 | 2016-10-04 |  | Y
Central Hudson |  | EnterSolar LLC | CH-03348 | Newburgh | Montgomery |  | 12575 | G | 4023 | Coldenham | TBD |  | 1980 | [13 empty] | CDG | N | SOLECTRIA PVI 36TL (55) | 2016-03-14 | 2016-04-05 | 15 | 2016-04-05 | 2016-03-14 | 2016-04-05 | 15 |  |  |  |  | 32000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Green Street Power Partners, LLC | CH-03361 | Kingston | Ellenville |  | 12428 | G | 3072 | Honk Falls | TBD |  | 1980 | [13 empty] | CDG | N | SMA STP-30000TLUS-10 (66) | 2016-04-04 | 2016-04-25 | 15 | 2016-04-25 | 2016-04-04 | 2016-04-25 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Green Street Power Partners, LLC | CH-03362 | Kingston | Ellenville |  | 12428 | G | 3072 | Honk Falls | TBD |  | 1980 | [13 empty] | CDG | N | SMA STP-30000TLUS-10 (66) | 2016-04-04 | 2016-04-25 | 15 | 2016-04-25 | 2016-04-04 | 2016-04-25 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | SolarCity | CH-06516 | Kingston | Kingston | Ulster | 12401 | G | 1024 | East Kingston | N |  | 12 | [13 empty] | NM | N | 2 Fronius Primo 6.0 | 2016-02-26 | 2016-03-10 | 9 | 2016-03-10 | [14 empty] | 2016-03-21 | 2016-03-29 |  | Y
Central Hudson |  | SolarCity | CH-07991 | Catskill | Durham |  | 12460 | G | 1092 | Westerlo | TBD |  | 1992 | [13 empty] | CDG | N | FRONIUS SYMO 24 (83) | 2016-04-01 | 2016-04-22 | 15 | 2016-04-22 | 2016-04-01 | 2016-04-22 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | SolarCity | CH-07992 | Catskill | Coxsackie |  | 12192 | G | 1076 | Coxsackie | TBD |  | 1992 | [13 empty] | CDG | N | (83) FRONIUS SYMO 24 | 2016-03-21 | 2016-04-11 | 14 | 2016-04-11 | 2016-03-21 | 2016-04-11 | 14 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | SolarCity | CH-07993 | Poughkeepsie | Millbrook |  | 12545 | G | 7012 | Hibernia | TBD |  | 1992 | [13 empty] | CDG | N | (83) FRONIUS SYMO 24 | 2016-03-18 | 2016-04-11 | 15 | 2016-04-11 | 2016-03-18 | 2016-04-11 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | SolarCity | CH-07994 | Kingston | Accord |  | 12404 | G | 3024 | High Falls | TBD |  | 1992 | [13 empty] | CDG | N | FRONIUS SYMO 24 | 2016-03-18 | 2016-04-11 | 15 | 2016-04-11 | 2016-03-18 | 2016-04-11 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | SolarCity | CH-07995 | Newburgh | Walkill |  | 12589 | G | 5034 | Galeville | TBD |  | 1992 | [13 empty] | CDG | N | (83) FRONIUS SYMO 24 | 2016-03-18 | 2016-04-11 | 15 | 2016-04-11 | 2016-03-18 | 2016-04-11 | 15 |  |  |  |  | 32000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | SolarCity | CH-07996 | Kingston | Ulster Park |  | 12487 | G | 1014 | Boulevard | TBD |  | 1992 | [13 empty] | CDG | N | (83) FRONIUS SYMO 24 | 2016-03-18 | 2016-04-11 | 15 | 2016-04-11 | 2016-03-18 | 2016-04-11 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | SolarCity | CH-07997 | Kingston | Marbletown |  | 12440 | G | 3023 | High Falls | TBD |  | 1992 | [13 empty] | CDG | N | (83) FRONIUS SYMO 24 | 2016-03-18 | 2016-04-11 | 15 | 2016-04-11 | 2016-03-18 | 2016-04-11 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | SolarCity | CH-07998 | Catskill | Jewett |  | 12444 | E | 2389 | Vinegar Hill | TBD |  | 1992 | [13 empty] | CDG | N | (83) FRONIUS SYMO 24 | 2016-03-18 | 2016-04-11 | 15 | 2016-04-11 | 2016-03-18 | 2016-04-11 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | SolarCity | CH-07999 | Newburgh | Gardiner |  | 12525 | G | 5031 | Galeville | TBD |  | 1992 | [13 empty] | CDG | N | (83) FRONIUS SYMO 24 | 2016-03-30 | 2016-04-20 | 15 | 2016-04-20 | 2016-03-30 | 2016-04-20 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08607 | Kingston | Kingston | Ulster | 12401 | G | 1021 | East Kingston | N |  | 10.32 | [13 empty] | NM | N | 48 ENPHASE M215 602LLS2XZC | 2016-02-26 | 2016-03-10 | 9 | 2016-03-10 | [14 empty] | 2016-07-29 | 2016-08-01 |  | Y
Central Hudson |  | Sungevity Inc | CH-09615 | Newburgh | New Windsor |  | 12553 | G | 4097 | Bethlehem Rd | TBD |  | 6.8 | [13 empty] | NM | N | ABB PVI-3.8-OUTD-S-US-A ABB PVI-3.0-OUTD-S-US-A | 2016-02-26 | 2016-03-11 | 10 | 2016-03-11 | [17 empty] | W
Central Hudson |  | Xzerta Energy Group, LLC | CH-09952 | Catskill | Athens |  | 12015 | G | 2006 | North Catskill | TBD |  | 2000 | [13 empty] | CDG | N | POWER ELECTRONICS FS0751CU POWER ELECTRONICS FS1250CU | 2016-03-14 | 2016-04-05 | 15 | 2016-04-05 | 2016-03-14 | 2016-04-05 | 15 |  |  |  |  | 32000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03220 | Newburgh | Montgomery |  | 12549 | G | 4026 | Coldenham | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-03-14 | 2016-04-05 | 15 | 2016-04-05 | 2016-03-14 | 2016-04-05 | 15 |  |  |  |  | 32000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03221 | Kingston | Kerhonkson |  | 12446 | G | 3082 | Kerhonkson | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-03-14 | 2016-04-05 | 15 | 2016-04-05 | 2016-03-14 | 2016-04-05 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03222 | TBD | Ellenville |  | 12428 | Tbd | TBD | Tbd | N |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-03-14 | 2016-04-05 | 15 | 2016-04-05 | 2016-03-14 | 2016-04-05 | 15 |  |  |  |  | 35000 | [9 empty] | W
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03223 | Catskill | Athens |  | 12015 | G | 2002 | North Catskill | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-03-14 | 2016-04-05 | 15 | 2016-04-05 | 2016-03-14 | 2016-04-05 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03224 | Catskill | Cairo |  | 12413 | G | 2041 | South Cairo | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-03-14 | 2016-04-05 | 15 | 2016-04-05 | 2016-03-14 | 2016-04-05 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03225 | Catskill | Cairo |  | 12413 | G | 2042 | South Cairo | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-03-14 | 2016-04-05 | 15 | 2016-04-05 | 2016-03-14 | 2016-04-05 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03226 | Catskill | Palenvl | Greene | 12463 | G | 2385 | Lawrenceville | N |  | 2000 | [13 empty] | CDG | N | SMA America (44) Huawei SUN2000-45KTL-US-1500 | 2016-03-14 | 2016-04-05 | 15 | 2016-04-05 | 2016-03-14 | 2016-04-05 | 15 | 2016-11-08 | 2017-01-06 | 2017-04-03 | 60 | 29496.62 | 575875 | 186589.35 | 2017-06-23 | 2017-10-09 | 2017-10-09 | 2019-12-19 | 2019-12-19 | 2019-12-20 | 2020-06-22 | Y
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03227 | Catskill | Catskill |  | 12414 | G | 2042 | South Cairo | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-03-14 | 2016-04-05 | 15 | 2016-04-05 | 2016-03-14 | 2016-04-05 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03228 | Catskill | Freehold |  | 12431 | G | 2061 | Freehold | TBD |  | 1980 | [13 empty] | CDG | N | (44) Huawei SUN2000-45KTL-US-1500 | 2016-03-14 | 2016-04-05 | 15 | 2016-04-05 | 2016-03-14 | 2016-04-05 | 15 | 2016-11-15 | 2016-11-15 | 2017-03-15 | 80 |  | 127463 |  | 2017-06-23 | 2017-09-12 | 2017-09-12 |  |  |  | 2019-04-01 | W |  | CESIR for 4 projects, CH-03154, CH-03228, CH-03172 and CH-03176. (totaling 8MW) combined with an aggregate CESIR Cost to Customer of $50,000. Only proceeding with CH-03154, CH-03228,and CH-03172.
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03229 | Newburgh | Modena |  | 12548 | G | 5012 | Modena | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-03-14 | 2016-04-05 | 15 | 2016-04-05 | 2016-03-14 | 2016-04-05 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03230 | Newburgh | Highland |  | 12528 | G | 5083 | Highland | TBD |  | 1980 | [13 empty] | CDG | N | (44) Huawei SUN2000-45KTL-US | 2016-03-14 | 2016-04-05 | 15 | 2016-04-05 | 2016-03-14 | 2016-04-05 | 15 | 2016-05-12 | 2016-05-12 | 2016-08-08 | 60 | 29288 | 57500 | 51.41 | 2017-06-23 | 2017-08-17 | 2017-08-17 |  |  |  | 2018-06-07 | W
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03231 | Poughkeepsie | Pleasant Valley |  | 12569 | G | 7024 | Tinkertown | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-03-14 | 2016-04-05 | 15 | 2016-04-05 | 2016-03-14 | 2016-04-05 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03232 | Poughkeepsie | Salt Point |  | 12578 | G | 7011 | Hibernia | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-03-14 | 2016-04-05 | 15 | 2016-04-05 | 2016-03-14 | 2016-04-05 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03233 | Catskill | Coxsackie |  | 12051 | G | 1076 | Coxsackie | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-03-14 | 2016-04-05 | 15 | 2016-04-05 | 2016-03-14 | 2016-04-05 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03234 | Catskill | Athens |  | 12015 | G | 2003 | North Catskill | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-03-14 | 2016-04-05 | 15 | 2016-04-05 | 2016-03-14 | 2016-04-05 | 15 |  |  |  |  | 32000 | [9 empty] | W
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03235 | Catskill | Freehold |  | 12431 | G | 2071 | Freehold | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-03-14 | 2016-04-05 | 15 | 2016-04-05 | 2016-03-14 | 2016-04-05 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03236 | Catskill | Catskill |  | 12414 | G | 2005 | North Catskill | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-03-14 | 2016-04-05 | 15 | 2016-04-05 | 2016-03-14 | 2016-04-05 | 15 |  |  |  |  | 32000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03237 | Newburgh | Wallkill |  | 12589 | G | 5041 | East Walden | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-03-14 | 2016-04-05 | 15 | 2016-04-05 | 2016-03-14 | 2016-04-05 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03238 | Newburgh | Wallkill |  | 12589 | G | 5042 | East Walden | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-03-14 | 2016-04-05 | 15 | 2016-04-05 | 2016-03-14 | 2016-04-05 | 15 |  |  |  |  | 32000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Infinity Solar Systems | CH-03404 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6056 | Todd Hill | N |  | 6 | [13 empty] | NM | N | SMA AMERICA SB6000TL-22 | 2016-02-29 | 2016-03-07 | 5 | 2016-03-07 | [14 empty] | 2016-04-27 | 2016-05-04 |  | Y
Central Hudson |  | Hollitronics Energy Solutions | CH-01204 | Catskill | Greenvl | Greene | 12083 | G | 2061 | Freehold | N |  | 6 | [13 empty] | NM | N | 12 ALTENERGY POWER SYSTEMS YC500-US | 2016-02-29 | 2016-03-11 | 9 | 2016-03-11 | [14 empty] | 2016-04-07 | 2016-04-14 |  | Y
Central Hudson |  | Kiewit-Shea Constructors | CH-02569 | Newburgh | Newburgh | Orange | 12550 | G | 5005 | Marlboro | N | [14 empty] | 1914 | NA | N | (2) Rockwell Powerflex 7000 | 2016-05-05 | 2016-05-05 | 0 | 2016-05-05 | 2016-05-05 | 2016-05-26 | 15 | 2016-06-27 | 2016-07-06 | 2016-09-16 | 51 | 2061.93 | [6 empty] | 2017-08-28 | 2017-09-05 | 2018-05-24 | Y
Central Hudson |  | SolarCity | CH-05121 | Newburgh | Milton | Ulster | 12547 | G | 5083 | Highland | N |  | 4.2 | [13 empty] | NM | N | ABB PVI 4.2 | 2016-02-29 | 2016-03-14 | 10 | 2016-03-14 | [14 empty] | 2016-04-19 | 2016-04-22 |  | Y
Central Hudson |  | SolarCity | CH-05441 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 6074 | East Park | N |  | 8.2 | [13 empty] | NM | N | FRONIUS PRIMO 8.2 | 2016-02-29 | 2016-03-07 | 5 | 2016-03-07 | [14 empty] | 2016-04-26 | 2016-05-03 |  | Y
Central Hudson |  | SolarCity | CH-06179 | Newburgh | New Paltz | Ulster | 12561 | G | 5024 | Ohioville | N |  | 3 | [13 empty] | NM | N | ABB PVI 3.0 | 2016-02-29 | 2016-03-14 | 10 | 2016-03-14 | [14 empty] | 2016-05-11 | 2016-05-17 |  | Y
Central Hudson |  | SolarCity | CH-07101 | Newburgh | Wallkill | Ulster | 12589 | G | 5043 | East Walden | N |  | 5 | [13 empty] | NM | N | ABB PVI 5000 | 2016-02-29 | 2016-03-14 | 10 | 2016-03-14 | [8 empty] | 350 | 350 |  | 2016-04-26 | 2016-04-26 | 2016-05-10 | 2016-05-10 | 2016-06-01 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03239 | Newburgh | Wallkill |  | 12589 | G | 5041 | East Walden | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-03-14 | 2016-04-05 | 15 | 2016-04-05 | 2016-03-14 | 2016-04-05 | 15 |  |  |  |  | 35000 | [9 empty] | W
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03240 | Newburgh | Wallkill |  | 12589 | G | 5041 | East Walden | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-03-14 | 2016-04-05 | 15 | 2016-04-05 | 2016-03-14 | 2016-04-05 | 15 |  |  |  |  | 35000 | [9 empty] | W
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03241 | Newburgh | Wallkill |  | 12589 | G | 5042 | East Walden | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-03-14 | 2016-04-05 | 15 | 2016-04-05 | 2016-03-14 | 2016-04-05 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03242 | Catskill | Athens |  | 12015 | G | 2002 | North Catskill | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-03-14 | 2016-04-05 | 15 | 2016-04-05 | 2016-03-14 | 2016-04-05 | 15 |  |  |  |  | 35000 | [9 empty] | W
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03243 | Catskill | Catskill |  | 12414 | G | 2042 | South Cairo | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-03-14 | 2016-04-05 | 15 | 2016-04-05 | 2016-03-14 | 2016-04-05 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03244 | Catskill | Freehold |  | 12431 | G | 2071 | Freehold | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-03-14 | 2016-04-05 | 15 | 2016-04-05 | 2016-03-14 | 2016-04-05 | 15 |  |  |  |  | 35000 | [9 empty] | W
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03245 | Catskill | Freehold |  | 12431 | G | 2061 | Freehold | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-03-14 | 2016-04-05 | 15 | 2016-04-05 | 2016-03-14 | 2016-04-05 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03246 | Newburgh | Modena |  | 12548 | G | 5012 | Modena | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-03-14 | 2016-04-05 | 15 | 2016-04-05 | 2016-03-14 | 2016-04-05 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03247 | Kingston | Kingston |  | 12401 | G | 3014 | Woodstock | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-03-14 | 2016-04-05 | 15 | 2016-04-05 | 2016-03-14 | 2016-04-05 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03248 | Kingston | Saugerties |  | 12477 | G | 2015 | Lincoln Park | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-03-14 | 2016-04-05 | 15 | 2016-04-05 | 2016-03-14 | 2016-04-05 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03249 | Catskill | Freehold |  | 12431 | G | 2071 | Freehold | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-03-14 | 2016-04-05 | 15 | 2016-04-05 | 2016-03-14 | 2016-04-05 | 15 |  |  |  |  | 35000 | [9 empty] | W
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03250 | Catskill | Greenville |  | 12083 | G | 2061 | Freehold | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-03-14 | 2016-04-05 | 15 | 2016-04-05 | 2016-03-14 | 2016-04-05 | 15 |  |  |  |  | 35000 | [9 empty] | W
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03251 | Newburgh | Milton |  | 12547 | G | 5002 | Marlboro | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-03-14 | 2016-04-05 | 15 | 2016-04-05 | 2016-03-14 | 2016-04-05 | 15 |  |  |  |  | 32000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03252 | Newburgh | Modena |  | 12548 | G | 5012 | Modena | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-03-14 | 2016-04-05 | 15 | 2016-04-05 | 2016-03-14 | 2016-04-05 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03253 | Catskill | W Coxsackie |  | 12192 | G | 1076 | Coxsackie | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-03-14 | 2016-04-05 | 15 | 2016-04-05 | 2016-03-14 | 2016-04-05 | 15 |  |  |  |  | 35000 | [9 empty] | W
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03254 | Catskill | Climax |  | 12042 | G | 1071 | Coxsackie | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-03-14 | 2016-04-05 | 15 | 2016-04-05 | 2016-03-14 | 2016-04-05 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03255 | Catskill | Purling |  | 12470 | G | 2042 | South Cairo | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-03-14 | 2016-04-05 | 15 | 2016-04-05 | 2016-03-14 | 2016-04-05 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Hudson Solar | CH-02168 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8046 | Myers Corners | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE-6000A-US-U | 2016-03-14 | 2016-03-24 | 8 | 2016-03-24 | [14 empty] | 2016-04-06 | 2016-04-11 |  | Y
Central Hudson |  | SolarCity | CH-07076 | Newburgh | Marlboro | Ulster | 12542 | G | 5003 | Marlboro | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2016-03-16 | 2016-03-31 | 10 | 2016-03-31 | [14 empty] | 2016-04-19 | 2016-04-22 |  | Y
Central Hudson |  | Sunrise Solar Solutions, LLC | CH-09644 | Newburgh | New Paltz | Ulster | 12561 | G | 5031 | Galeville | N |  | 7.84 | [13 empty] | NM | N | ENPHASE M280 (28) | 2016-05-04 | 2016-05-18 | 10 | 2016-05-18 | [14 empty] | 2016-10-03 | 2016-10-10 |  | Y
Central Hudson |  | New York State Solar Farm | CH-03986 | Poughkeepsie | Pine Plns | Dutchess | 12567 | G | 7091 | Pulvers Corners | N |  | 5 | [13 empty] | NM | N | SMA AMERICA SB5000 | 2016-03-10 | 2016-03-24 | 10 | 2016-03-24 | [14 empty] | 2016-03-24 | 2016-04-01 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | NRG Home Solar | CH-04676 | Newburgh | New Windsor | Orange | 12553 | G | 4095 | Bethlehem Rd | N |  | 10 | [13 empty] | NM | N | SOLAR EDGE SE10000A-US | 2016-03-02 | 2016-03-16 | 10 | 2016-03-16 | [14 empty] | 2016-04-19 | 2016-04-21 |  | Y
Central Hudson |  | NRG Home Solar | CH-04689 | Kingston | Kingston |  | 12401 | G | 2092 | Hurley Ave | TBD |  | 6 | [13 empty] | NM | N | SOLAR EDGE SE6000A-US | 2016-03-02 | 2016-03-11 | 7 | 2016-03-11 | [17 empty] | W
Central Hudson |  | NRG Home Solar | CH-04690 | Kingston | Kingston | Ulster | 12401 | G | 1013 | Boulevard | N |  | 3.22 | [13 empty] | NM | N | 15 ENPHASE M215-60-2LL-S22-IG | 2016-03-02 | 2016-03-11 | 7 | 2016-03-11 | [14 empty] | 2016-05-09 | 2016-05-11 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00863 | Kingston | New Paltz | Ulster | 12561 | G | 3041 | Sturgeon Pool | N |  | 6.02 | [13 empty] | NM | N | 28 ENPHASE M215 60-2LL-S22 | 2016-03-02 | 2016-03-11 | 7 | 2016-03-11 | [14 empty] | 2016-04-12 | 2016-04-15 |  | Y
Central Hudson |  | Direct Energy Solar | CH-01039 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6042 | Spackenkill | N |  | 7.5 | [13 empty] | NM | N | (30) ENPHASE M250 60-2LL-S22 | 2016-03-09 | 2016-03-16 | 5 | 2016-03-16 | [14 empty] | 2016-04-21 | 2016-04-28 |  | Y
Central Hudson |  | SolarCity | CH-08000 | Catskill | Cairo |  | 12413 | G | 2043 | South Cairo | TBD |  | 1992 | [13 empty] | CDG | N | (83) FRONIUS SYMO 24 | 2016-03-18 | 2016-04-11 | 15 | 2016-04-11 | 2016-03-18 | 2016-04-11 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | SolarCity | CH-08001 | Catskill | Durham |  | 12422 | G | 1092 | Westerlo | TBD |  | 1992 | [13 empty] | CDG | N | (83) FRONIUS SYMO 24 | 2016-03-18 | 2016-04-11 | 15 | 2016-04-11 | 2016-03-18 | 2016-04-11 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | SolarCity | CH-08002 | Catskill | Durham |  | 12422 | G | 1092 | Westerlo | TBD |  | 1992 | [13 empty] | CDG | N | (83) FRONIUS SYMO 24 | 2016-03-18 | 2016-04-11 | 15 | 2016-04-11 | 2016-03-18 | 2016-04-11 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | SolarCity | CH-08003 | Catskill | E Durham |  | 12423 | G | 1092 | Westerlo | TBD |  | 1992 | [13 empty] | CDG | N | (83) FRONIUS SYMO 24 | 2016-03-18 | 2016-04-11 | 15 | 2016-04-11 | 2016-03-18 | 2016-04-11 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | SolarCity | CH-08004 | Catskill | New Baltimore |  | 12124 | G | 2061 | Freehold | TBD |  | 1992 | [13 empty] | CDG | N | (83) FRONIUS SYMO 24 | 2016-03-18 | 2016-04-11 | 15 | 2016-04-11 | 2016-03-18 | 2016-04-11 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | SolarCity | CH-08005 | Catskill | New Baltimore |  | 12124 | G | 2061 | Freehold | TBD |  | 1992 | [13 empty] | CDG | N | (83) FRONIUS SYMO 24 | 2016-03-18 | 2016-04-11 | 15 | 2016-04-11 | 2016-03-18 | 2016-04-11 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | SolarCity | CH-08006 | Catskill | E Durham |  | 12423 | G | 2071 | Freehold | TBD |  | 1992 | [13 empty] | CDG | N | (83) FRONIUS SYMO 24 | 2016-03-18 | 2016-04-11 | 15 | 2016-04-11 | 2016-03-18 | 2016-04-11 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | SolarCity | CH-08007 | Catskill | Durham |  | 12460 | G | 1092 | Westerlo | TBD |  | 1992 | [13 empty] | CDG | N | (83) FRONIUS SYMO 24 | 2016-03-18 | 2016-04-11 | 15 | 2016-04-11 | 2016-03-18 | 2016-04-11 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | SolarCity | CH-08008 | Catskill | Oak Hill |  | 12460 | G | 1092 | Westerlo | TBD |  | 1992 | [13 empty] | CDG | N | (83) FRONIUS SYMO 24 | 2016-03-18 | 2016-04-11 | 15 | 2016-04-11 | 2016-03-18 | 2016-04-11 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | SolarCity | CH-08009 | Catskill | Greenville |  | 12083 | G | 2061 | Freehold | TBD |  | 1992 | [13 empty] | CDG | N | FRONIUS SYMO 24 (83) | 2016-03-18 | 2016-04-11 | 15 | 2016-04-11 | 2016-03-18 | 2016-04-11 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | SolarCity | CH-08010 | Catskill | Prattsville |  | 12468 | E | 2389 | Vinegar Hill | TBD |  | 1992 | [13 empty] | CDG | N | FRONIUS SYMO 24 (83) | 2016-03-18 | 2016-04-11 | 15 | 2016-04-11 | 2016-03-18 | 2016-04-11 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | SolarCity | CH-08011 | Poughkeepsie | Stanfordville |  | 12581 | G | 7072 | Stanfordville | TBD |  | 1992 | [13 empty] | CDG | N | FRONIUS SYMO 24 (83) | 2016-03-18 | 2016-04-11 | 15 | 2016-04-11 | 2016-03-18 | 2016-04-11 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | SolarCity | CH-08012 | Poughkeepsie | Northeast |  | 12546 | G | 7081 | Millerton | TBD |  | 1992 | [13 empty] | CDG | N | FRONIUS SYMO 24 (83) | 2016-03-18 | 2016-04-11 | 15 | 2016-04-11 | 2016-03-18 | 2016-04-11 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | SolarCity | CH-08013 | Poughkeepsie | Verbank |  | 12585 | G | 6057 | Todd Hill | TBD |  | 1992 | [13 empty] | CDG | N | FRONIUS SYMO 24 (83) | 2016-03-18 | 2016-04-11 | 15 | 2016-04-11 | 2016-03-18 | 2016-04-11 | 15 |  |  |  |  | 32000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | SolarCity | CH-08014 | Poughkeepsie | Northeast |  | 12546 | G | 7081 | Millerton | TBD |  | 1992 | [13 empty] | CDG | N | FRONIUS SYMO 24 (83) | 2016-03-18 | 2016-04-11 | 15 | 2016-04-11 | 2016-03-18 | 2016-04-11 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | SolarCity | CH-08015 | Poughkeepsie | Millerton |  | 12546 | G | 7081 | Millerton | TBD |  | 1992 | [13 empty] | CDG | N | FRONIUS SYMO 24 (83) | 2016-03-18 | 2016-04-11 | 15 | 2016-04-11 | 2016-03-18 | 2016-04-11 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | SolarCity | CH-08016 | Poughkeepsie | Lagrangeville |  | 12540 | G | 6053 | Todd Hill | TBD |  | 1992 | [13 empty] | CDG | N | FRONIUS SYMO 24 (83) | 2016-03-18 | 2016-04-11 | 15 | 2016-04-11 | 2016-03-18 | 2016-04-11 | 15 |  |  |  |  | 32000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | SolarCity | CH-08017 | Poughkeepsie | Union Vale |  | 12540 | G | 6055 | Todd Hill | TBD |  | 1992 | [13 empty] | CDG | N | FRONIUS SYMO 24 (83) | 2016-03-18 | 2016-04-11 | 15 | 2016-04-11 | 2016-03-18 | 2016-04-11 | 15 |  |  |  |  | 32000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08742 | Kingston | Kingston | Ulster | 12401 | G | 2091 | Hurley Ave | N |  | 6.235 | [13 empty] | NM | N | 29 ENPHASE M215 602LLS2XZC | 2016-03-02 | 2016-03-11 | 7 | 2016-03-11 | [14 empty] | 2016-07-13 | 2016-07-19 |  | Y
Central Hudson |  | NRG Home Solar | CH-00535 | Poughkeepsie | Pine Plns | Dutchess | 12567 | G | 7091 | Pulvers Corners | N |  | 3.22 | [13 empty] | NM | N | ENPHASE M215-60-2LL-S22-IG (15) | 2016-03-10 | 2016-03-24 | 10 | 2016-03-24 | [14 empty] | 2016-05-17 | 2016-05-24 |  | Y
Central Hudson |  | NRG Home Solar | CH-04815 | Poughkeepsie | Millbrook |  | 12545 | G | 7025 | Tinkertown | TBD |  | 10 | [13 empty] | NM | N | SOLAREDGE SE10000A-US | 2016-03-03 | 2016-03-17 | 10 | 2016-03-17 | [17 empty] | W
Central Hudson |  | SolarCity | CH-05304 | Newburgh | Marlboro | Ulster | 12542 | G | 5003 | Marlboro | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2016-03-03 | 2016-03-17 | 10 | 2016-03-17 | [14 empty] | 2016-04-19 | 2016-04-21 |  | Y
Central Hudson |  | SolarCity | CH-05467 | Newburgh | Rock Tvrn | Orange | 12575 | G | 4097 | Bethlehem Rd | N |  | 6 | [13 empty] | NM | N | ABB PVI 6000 | 2016-03-03 | 2016-03-17 | 10 | 2016-03-17 | [14 empty] | 2016-06-01 | 2016-06-03 |  | Y
Central Hudson |  | SolarCity | CH-05689 | Kingston | Kingston |  | 12401 | G | 112 | South Wall St | TBD |  | 3 | [13 empty] | NM | N | ABB PVI-3.0 OUTD-S-US | 2016-03-03 | 2016-03-14 | 7 | 2016-03-14 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | SolarCity | CH-05871 | Poughkeepsie | Staatsburg | Dutchess | 12580 | G | 7041 | Staatsburg | N |  | 3.6 | [13 empty] | NM | N | ABB PVI 3.6 | 2016-03-03 | 2016-03-17 | 10 | 2016-03-17 | [14 empty] | 2016-07-14 | 2016-07-14 |  | Y
Central Hudson |  | SolarCity | CH-06552 | Kingston | Kingston | Ulster | 12401 | G | 1022 | East Kingston | N |  | 3 | [13 empty] | NM | N | ABB PVI 3.0 | 2016-03-03 | 2016-03-15 | 8 | 2016-03-15 | [14 empty] | 2016-03-30 | 2016-04-06 |  | Y
Central Hudson |  | SolarCity | CH-06756 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7051 | Rhinebeck | N |  | 6 | [13 empty] | NM | N | ABB PVI 6000 | 2016-05-02 | 2016-05-02 | 0 | 2016-05-02 | [14 empty] | 2016-05-02 | 2016-05-09 |  | Y
Central Hudson |  | SolarCity | CH-06766 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7054 | Rhinebeck | N |  | 6.6 | [13 empty] | NM | N | ABB PV I3.6 ABB PVI 3.0 | 2016-03-03 | 2016-03-17 | 10 | 2016-03-17 | [14 empty] | 2016-10-03 | 2016-10-03 |  | Y
Central Hudson |  | SolarCity | CH-06836 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8046 | Myers Corners | N |  | 6 | [13 empty] | NM | N | ABB PVI 6.0 | 2016-03-03 | 2016-03-17 | 10 | 2016-03-17 | [14 empty] | 2016-04-13 | 2016-04-18 |  | Y
Central Hudson |  | SolarCity | CH-07187 | Catskill | Greenvl | Greene | 12083 | G | 2061 | Freehold | N |  | 10.2 | [13 empty] | NM | N | ABB PVI-6000 OUTD-US ABB PVI-4.2 OUTD-US | 2016-03-03 | 2016-03-14 | 7 | 2016-03-14 | [14 empty] | 2016-04-25 | 2016-04-25 |  | Y
Central Hudson |  | SolarCity | CH-07809 | Kingston | Lk Katrine | Ulster | 12449 | G | 2016 | Lincoln Park | N | CH-07246 | 3 | [13 empty] | NM | N | ABB PVI 3.0 | 2016-03-03 | 2016-03-15 | 8 | 2016-03-15 | [14 empty] | 2016-05-02 | 2016-05-06 |  | Y
Central Hudson |  | SolarCity | CH-08018 | Poughkeepsie | Pine Plains |  | 12567 | G | 7072 | Stanfordville | TBD |  | 1992 | [13 empty] | CDG | N | FRONIUS SYMO 24.0 (83) | 2016-03-18 | 2016-04-11 | 15 | 2016-04-11 | 2016-03-18 | 2016-04-11 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | SolarCity | CH-08019 | Poughkeepsie | Pleasant Valley |  | 12578 | G | 7011 | Hibernia | TBD |  | 1992 | [13 empty] | CDG | N | FRONIUS SYMO 24.0 (83) | 2016-03-24 | 2016-04-15 | 15 | 2016-04-15 | 2016-03-24 | 2016-04-15 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | SolarCity | CH-08020 | Poughkeepsie | Stanford |  | 12514 | G | 7071 | Stanfordville | TBD |  | 1992 | [13 empty] | CDG | N | FRONIUS SYMO 24.0 (83) | 2016-03-18 | 2016-04-11 | 15 | 2016-04-11 | 2016-03-18 | 2016-04-11 | 15 |  |  |  |  | 32000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | SolarCity | CH-08021 | Poughkeepsie | Millerton |  | 12540 | G | 7081 | Millerton | TBD |  | 1992 | [13 empty] | CDG | N | FRONIUS SYMO 24.0 (83) | 2016-04-27 | 2016-04-27 | 0 | 2016-04-27 | 2016-04-27 | 2016-05-18 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | SolarCity | CH-08023 | Poughkeepsie | Clinton |  | 12570 | G | 7012 | Hibernia | TBD |  | 1992 | [13 empty] | CDG | N | FRONIUS SYMO 24.0 (83) | 2016-03-18 | 2016-04-11 | 15 | 2016-04-11 | 2016-03-18 | 2016-04-11 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08784 | Kingston | Kingston |  | 12401 | G | 1011 | Boulevard | TBD |  | 8.17 | [13 empty] | NM | N | 38 ENPHASE M215 602LLS2XZC | 2016-03-03 | 2016-03-15 | 8 | 2016-03-15 | [17 empty] | W
Central Hudson |  | Sungevity Inc | CH-09611 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8052 | North Chelsea | N |  | 3 | [13 empty] | NM | N | ABB PVI-3.0-OUTD-S-US-A | 2016-03-23 | 2016-04-05 | 8 | 2016-04-05 | [14 empty] | 2016-05-02 | 2016-05-06 |  | Y
Central Hudson |  | Sungevity Inc | CH-09621 | Kingston | Woodbourne |  | 12788 | G | 3091 | Neversink | TBD |  | 7.6 | [13 empty] | NM | N | 2 ABB PVI-3.8-OUTD-S-US-A | 2016-03-03 | 2016-03-14 | 7 | 2016-03-14 | [17 empty] | W
Central Hudson |  | Lighthouse Solar | CH-03816 | Newburgh | New Paltz | Ulster | 12561 | G | 5031 | Galeville | N |  | 1.68 | [13 empty] | NM | N | ENPHASES28060-2LL-X (6) | 2016-03-11 | 2016-03-11 | 0 | 2016-03-11 | [14 empty] | 2016-04-14 | 2016-04-14 |  | Y
Central Hudson |  | NRG Home Solar | CH-04704 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 6074 | East Park | N |  | 3.22 | [13 empty] | NM | N | ENPHASE M215-60-2LL-S22-IG (15) | 2016-03-04 | 2016-03-18 | 10 | 2016-03-18 | [14 empty] | 2016-05-25 | 2016-06-01 |  | Y
Central Hudson |  | NRG Home Solar | CH-00568 | Poughkeepsie | Clinton Corners |  | 12514 | G | 7071 | Stanfordville | TBD |  | 4.3 | [13 empty] | NM | N | (20) ENPHASE M215-60-2LL-S22-IG | 2016-04-05 | 2016-04-05 | 0 | 2016-04-05 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | BQ Energy, LLC | CH-00758 | Fishkill | Beacon | Dutchess | 12508 | G | 8085 | Tioronda | N |  | 1975 | [13 empty] | RNM | N | 79 Huawei Technologies SUN2000-25KTL-US | 2016-03-18 | 2016-04-11 | 15 | 2016-04-11 | 2016-03-18 | 2016-04-11 | 15 | 2016-05-05 | 2016-04-25 | 2016-07-19 | 59 | 29999 | 58200 | 114652.29 |  | 2017-06-23 | 2017-06-23 | 2018-06-18 | 2018-06-27 | 2018-06-28 | 2022-10-31 | Y |  | Temporary partial final interconnection approval granted on 6/28/18.
Central Hudson |  | SolarCity | CH-05066 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 12 | [13 empty] | NM | N | ABB PVI 6000 ABB PVI 6000 | 2016-04-15 | 2016-04-29 | 10 | 2016-04-29 | [8 empty] | 350 | 350 |  | 2016-05-18 | 2016-05-18 | 2016-06-15 | 2016-07-27 | 2016-07-27 |  | Y
Central Hudson |  | SolarCity | CH-05735 | Kingston | Woodstock | Ulster | 12498 | G | 3003 | Saugerties | N |  | 10 | [13 empty] | NM | N | 2 ABB PVI 5000 | 2016-03-04 | 2016-03-17 | 9 | 2016-03-17 | [8 empty] | 350 | 350 |  | 2016-03-29 | 2016-03-29 | 2016-05-09 | 2016-06-03 | 2016-06-07 |  | Y
Central Hudson |  | SolarCity | CH-07027 | Newburgh | New Windsor | Orange | 12553 | G | 4046 | Union Ave | N |  | 5 | [13 empty] | NM | N | ABB PVI 5000 | 2016-03-16 | 2016-03-31 | 10 | 2016-03-31 | [14 empty] | 2016-04-28 | 2016-04-29 |  | Y
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03256 | Newburgh | Walkill |  | 12589 | G | 5043 | East Walden | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-03-18 | 2016-04-11 | 15 | 2016-04-11 | 2016-03-18 | 2016-04-11 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03257 | Catskill | Athens |  | 12414 | G | 2002 | North Catskill | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-03-14 | 2016-04-05 | 15 | 2016-04-05 | 2016-03-14 | 2016-04-05 | 15 |  |  |  |  | 35000 | [9 empty] | W
Central Hudson |  | Infinity Solar Systems | CH-00141 | Fishkill | Beacon | Dutchess | 12508 | G | 8085 | Tioronda | N | CH-00141 | 6 | [13 empty] | NM | N | SMA AMERICA SB6000TL-US | 2016-03-14 | 2016-03-24 | 8 | 2016-03-24 | [14 empty] | 2016-06-22 | 2016-06-28 |  | Y
Central Hudson |  | Lighthouse Solar | CH-00309 | Newburgh | New Windsor | Orange | 12553 | G | 4044 | Union Ave | N |  | 6 | [13 empty] | NM | N | SOLAREDGE 6000A-US | 2016-03-07 | 2016-03-21 | 10 | 2016-03-21 | [14 empty] | 2016-04-29 | 2016-05-05 |  | Y
Central Hudson |  | NRG Home Solar | CH-04433 | Fishkill | Beacon | Dutchess | 12508 | G | 8017 | Forgebrook | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE7600A-US | 2016-03-07 | 2016-03-21 | 10 | 2016-03-21 | [14 empty] | 2016-06-21 | 2016-06-27 |  | Y
Central Hudson |  | Community Energy Inc | CH-00778 | Kingston | Saugerties |  | 12477 | G | 3002 | Saugerties | TBD |  | 2000 | [13 empty] | CDG | N | SMA AMERICA 20000TL (100) | 2016-03-18 | 2016-04-11 | 15 | 2016-04-11 | 2016-03-18 | 2016-04-11 | 15 | 2017-05-16 | 2017-05-22 | 2017-06-01 | 7 | 35000 | [9 empty] | W
Central Hudson |  | SolarCity | CH-08024 | Newburgh | Newburgh |  | 12550 | G | 4092 | Bethlehem Rd | TBD |  | 1992 | [13 empty] | CDG | N | FRONIUS SYMO 24.0 (83) | 2016-03-24 | 2016-04-15 | 15 | 2016-04-15 | 2016-03-24 | 2016-04-15 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | SolarCity | CH-08025 | Newburgh | Campbell Hall |  | 10916 | G | 5051 | Maybrook | TBD |  | 1992 | [13 empty] | CDG | N | FRONIUS SYMO 24.0 (83) | 2016-03-18 | 2016-04-11 | 15 | 2016-04-11 | 2016-03-18 | 2016-04-11 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | SolarCity | CH-08026 | Poughkeepsie | Lagrangeville |  | 12540 | G | 6055 | Todd Hill | TBD |  | 1992 | [13 empty] | CDG | N | FRONIUS SYMO 24.0 (83) | 2016-03-18 | 2016-04-11 | 15 | 2016-04-11 | 2016-03-18 | 2016-04-11 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | SolarCity | CH-08027 | Kingston | Rochester |  | 12446 | G | 3082 | Kerhonkson | TBD |  | 1992 | [13 empty] | CDG | N | FRONIUS SYMO 24.0 (83) | 2016-03-18 | 2016-04-11 | 15 | 2016-04-11 | 2016-03-18 | 2016-04-11 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | SolarCity | CH-08028 | Poughkeepsie | Millerton |  | 12546 | G | 7081 | Millerton | TBD |  | 1992 | [13 empty] | CDG | N | FRONIUS SYMO 24.0 (83) | 2016-03-18 | 2016-04-11 | 15 | 2016-04-11 | 2016-03-18 | 2016-04-11 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | SolarCity | CH-08029 | Poughkeepsie | Millerton |  | 12546 | G | 7081 | Millerton | TBD |  | 1992 | [13 empty] | CDG | N | FRONIUS SYMO 24.0 (83) | 2016-03-24 | 2016-04-15 | 15 | 2016-04-15 | 2016-03-24 | 2016-04-15 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | SolarCity | CH-08030 | Poughkeepsie | Millerton |  | 12546 | G | 7081 | Millerton | TBD |  | 1992 | [13 empty] | CDG | N | FRONIUS SYMO 24.0 (83) | 2016-03-18 | 2016-04-11 | 15 | 2016-04-11 | 2016-03-18 | 2016-04-11 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | SolarCity | CH-08031 | Poughkeepsie | Pleasant Valley |  | 12569 | G | 6051 | Todd Hill | TBD |  | 1992 | [13 empty] | CDG | N | FRONIUS SYMO 24.0 (83) | 2016-03-18 | 2016-04-11 | 15 | 2016-04-11 | 2016-03-18 | 2016-04-11 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | SolarCity | CH-08032 | Poughkeepsie | Northeast |  | 12546 | G | 7081 | Millerton | TBD |  | 1992 | [13 empty] | CDG | N | FRONIUS SYMO 24.0 (83) | 2016-03-18 | 2016-04-11 | 15 | 2016-04-11 | 2016-03-18 | 2016-04-11 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | SolarCity | CH-08033 | Kingston | Kerhonkson |  | 12446 | G | 3081 | Kerhonkson | TBD |  | 1992 | [13 empty] | CDG | N | (83) FRONIUS SYMO 24 | 2016-03-18 | 2016-04-11 | 15 | 2016-04-11 | 2016-03-18 | 2016-04-11 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | SolarCity | CH-08034 | Kingston | Stone Ridge |  | 12484 | G | 3023 | High Falls | TBD |  | 1992 | [13 empty] | CDG | N | (83) FRONIUS SYMO 24 | 2016-03-18 | 2016-04-11 | 15 | 2016-04-11 | 2016-03-18 | 2016-04-11 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | SolarCity | CH-08035 | Kingston | Glasco |  | 12432 | G | 2015 | Lincoln Park | TBD |  | 1992 | [13 empty] | CDG | N | (83) FRONIUS SYMO 24 | 2016-03-18 | 2016-04-11 | 15 | 2016-04-11 | 2016-03-18 | 2016-04-11 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | SolarCity | CH-08036 | Kingston | Saugerties |  | 12477 | G | 2016 | Lincoln Park | TBD |  | 1992 | [13 empty] | CDG | N | FRONIUS SYMO 24.0 (83) | 2016-03-18 | 2016-04-11 | 15 | 2016-04-11 | 2016-03-18 | 2016-04-11 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03258 | Catskill | E Durham |  | 12423 | G | 2071 | Freehold | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-03-14 | 2016-04-05 | 15 | 2016-04-05 | 2016-03-14 | 2016-04-05 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03259 | Catskill | Earlton |  | 12058 | G | 1071 | Coxsackie | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-03-14 | 2016-04-05 | 15 | 2016-04-05 | 2016-03-14 | 2016-04-05 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03260 | Catskill | Coxsackie |  | 12051 | G | 1071 | Coxsackie | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-03-14 | 2016-04-05 | 15 | 2016-04-05 | 2016-03-14 | 2016-04-05 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03261 | Catskill | S Cairo |  | 12482 | G | 2042 | South Cairo | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-03-14 | 2016-04-05 | 15 | 2016-04-05 | 2016-03-14 | 2016-04-05 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03262 | Catskill | Greenville |  | 12083 | G | 2061 | Freehold | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-03-14 | 2016-04-05 | 15 | 2016-04-05 | 2016-03-14 | 2016-04-05 | 15 |  |  |  |  | 35000 | [9 empty] | W
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03263 | Catskill | Freehold |  | 12431 | G | 2061 | Freehold | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-03-14 | 2016-04-05 | 15 | 2016-04-05 | 2016-03-14 | 2016-04-05 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03264 | Catskill | Catskill |  | 12414 | G | 2002 | North Catskill | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-03-14 | 2016-04-05 | 15 | 2016-04-05 | 2016-03-14 | 2016-04-05 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03265 | Poughkeepsie | Poughkeepsie |  | 12601 | G | 6061 | Inwood Ave | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-03-14 | 2016-04-05 | 15 | 2016-04-05 | 2016-03-14 | 2016-04-05 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03266 | Catskill | W Coxsackie |  | 12192 | G | 1071 | Coxsackie | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-03-14 | 2016-04-05 | 15 | 2016-04-05 | 2016-03-14 | 2016-04-05 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03267 | Catskill | Earlton |  | 12058 | G | 1071 | Coxsackie | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-03-16 | 2016-04-07 | 15 | 2016-04-07 | 2016-03-16 | 2016-04-07 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | CESIR determined necessary during preliminary review Section C, Step 4.
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03268 | Kingston | Saugerties |  | 12477 | G | 3002 | Saugerties | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-03-14 | 2016-04-05 | 15 | 2016-04-05 | 2016-03-14 | 2016-04-05 | 15 |  |  |  |  | 35000 | [9 empty] | W
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03269 | Newburgh | Highland |  | 12528 | G | 5081 | Highland | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-03-14 | 2016-04-05 | 15 | 2016-04-05 | 2016-03-14 | 2016-04-05 | 15 |  |  |  |  | 32000 | [9 empty] | W
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03270 | Kingston | Kingston |  | 12401 | G | 2094 | Hurley Ave | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-03-16 | 2016-04-07 | 15 | 2016-04-07 | 2016-03-16 | 2016-04-07 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03271 | Kingston | Lake Katrine |  | 12449 | G | 2011 | Lincoln Park | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-03-14 | 2016-04-05 | 15 | 2016-04-05 | 2016-03-14 | 2016-04-05 | 15 |  |  |  |  | 32000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03272 | Catskill | Westerlo |  | 12193 | G | 2061 | Freehold | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-03-14 | 2016-04-05 | 15 | 2016-04-05 | 2016-03-14 | 2016-04-05 | 15 |  |  |  |  | 35000 | [9 empty] | W
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03273 | Catskill | Athens |  | 12015 | G | 1074 | Coxsackie | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-03-14 | 2016-04-05 | 15 | 2016-04-05 | 2016-03-14 | 2016-04-05 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03274 | Catskill | Westerlo |  | 12193 | G | 1091 | Westerlo | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-03-14 | 2016-04-05 | 15 | 2016-04-05 | 2016-03-14 | 2016-04-05 | 15 |  |  |  |  | 32000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03275 | Catskill | Coxsackie |  | 12051 | G | 1076 | Coxsackie | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-03-14 | 2016-04-05 | 15 | 2016-04-05 | 2016-03-14 | 2016-04-05 | 15 |  |  |  |  | 35000 | [9 empty] | W
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03276 | Catskill | Westerlo | Albany | 12193 | G | 1092 | Westerlo | N |  | 2000 | [13 empty] | CDG | Y | SMA America 44 Huawei Sun2000-45kTL | 2016-03-14 | 2016-04-05 | 15 | 2016-04-05 | 2016-03-14 | 2016-04-05 | 15 | 2017-01-30 | 2017-02-06 | 2017-05-03 | 60 | 29878.48 | 567913 | 106524.59 | 2017-08-16 | 2018-01-26 | 2018-01-26 | 2020-12-01 | 2020-12-30 | 2020-12-30 | 2021-03-15 | Y | Y
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03277 | Poughkeepsie | Red Hook |  | 12571 | G | 7061 | Milan | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-03-14 | 2016-04-05 | 15 | 2016-04-05 | 2016-03-14 | 2016-04-05 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03278 | Catskill | Prattsville |  | 12468 | E | 2389 | Vinegar Hill | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-03-14 | 2016-04-05 | 15 | 2016-04-05 | 2016-03-14 | 2016-04-05 | 15 |  |  |  |  | 35000 | [9 empty] | W
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03279 | Catskill | W Coxsackie |  | 12192 | G | 1083 | New Baltimore | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-03-14 | 2016-04-05 | 15 | 2016-04-05 | 2016-03-14 | 2016-04-05 | 15 |  |  |  |  | 35000 | [9 empty] | W
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03280 | Catskill | Hannacroix |  | 12087 | G | 1083 | New Baltimore | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-03-14 | 2016-04-05 | 15 | 2016-04-05 | 2016-03-14 | 2016-04-05 | 15 |  |  |  |  | 35000 | [9 empty] | W
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03281 | Catskill | Prattsville |  | 12468 | E | 2389 | Vinegar Hill | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-03-14 | 2016-04-05 | 15 | 2016-04-05 | 2016-03-14 | 2016-04-05 | 15 |  |  |  |  | 32000 | [9 empty] | W
Central Hudson |  | Empire Solar Solutions | CH-03341 | Newburgh | Gardiner |  | 12525 | G | 5031 | Galeville | TBD |  | 6 | [13 empty] | NM | N | SMA AMERICA 6000 | 2016-03-21 | 2016-04-04 | 9 | 2016-04-04 | [15 empty] | 2016-04-13 |  | W |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.Customer already had net meter prior to application.
Central Hudson |  | Green Street Power Partners, LLC | CH-03359 | Newburgh | Walden | Orange | 12586 | G | 5041 | East Walden | N |  | 10 | [13 empty] | NM | N | SMA SB5000TL-US (2) | 2016-03-08 | 2016-03-21 | 9 | 2016-03-21 | [14 empty] | 2016-07-18 | 2016-07-18 |  | Y
Central Hudson |  | SolarCity | CH-05535 | Catskill | Catskill | Greene | 12414 | G | 2004 | North Catskill | N |  | 5 | [13 empty] | NM | N | ABB PVI-5000-OUTD-US-Z-A | 2016-03-08 | 2016-03-17 | 7 | 2016-03-17 | [14 empty] | 2016-03-31 | 2016-04-07 |  | Y
Central Hudson |  | SolarCity | CH-07166 | Newburgh | New Windsor | Orange | 12553 | G | 4095 | Bethlehem Rd | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2016-03-08 | 2016-03-21 | 9 | 2016-03-21 | [14 empty] | 2016-04-01 | 2016-04-07 |  | Y
Central Hudson |  | SolarCity | CH-08037 | Kingston | Saugerties |  | 12477 | G | 3002 | Saugerties | TBD |  | 1992 | [13 empty] | CDG | N | FRONIUS SYMO 24.0 (83) | 2016-05-12 | 2016-06-03 | 15 | 2016-06-03 | 2016-06-03 | 2016-06-03 | 0 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | SolarCity | CH-08038 | Poughkeepsie | Verbank |  | 12585 | G | 6057 | Todd Hill | TBD |  | 1992 | [13 empty] | CDG | N | FRONIUS SYMO 24.0 (83) | 2016-05-12 | 2016-06-03 | 15 | 2016-06-03 | 2016-05-12 | 2016-06-03 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | SolarCity | CH-08039 | Poughkeepsie | Pleasant Valley |  | 12569 | G | 7011 | Hibernia | TBD |  | 1992 | [13 empty] | CDG | N | FRONIUS SYMO 24.0 (83) | 2016-05-12 | 2016-06-03 | 15 | 2016-06-03 | 2016-05-12 | 2016-06-03 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03282 | Catskill |  |  | 12192 | G | 1083 | New Baltimore | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US (Curtailing to 2MW) | 2016-09-27 | 2016-10-13 | 12 | 2016-10-13 | 2016-09-27 | 2016-10-13 | 12 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03283 | Catskill | Prattsville |  | 12468 | E | 2389 | Vinegar Hill | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-03-14 | 2016-04-05 | 15 | 2016-04-05 | 2016-03-14 | 2016-04-05 | 15 |  |  |  |  | 35000 | [9 empty] | W
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03284 | Kingston | Kerhonkson |  | 12446 | G | 3082 | Kerhonkson | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-03-14 | 2016-04-05 | 15 | 2016-04-05 | 2016-03-14 | 2016-04-05 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03285 | Catskill | Cairo |  | 12413 | G | 2071 | Freehold | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-03-14 | 2016-04-05 | 15 | 2016-04-05 | 2016-03-14 | 2016-04-05 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03286 | Catskill | Coxsackie |  | 12051 | G | 2002 | North Catskill | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-03-14 | 2016-04-05 | 15 | 2016-04-05 | 2016-03-14 | 2016-04-05 | 15 |  |  |  |  | 35000 | [9 empty] | W
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03287 | Catskill | Earlton |  | 12058 | G | 2006 | North Catskill | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-03-14 | 2016-04-05 | 15 | 2016-04-05 | 2016-03-14 | 2016-04-05 | 15 |  |  |  |  | 32000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03288 | Catskill | Coxsackie |  | 12051 | G | 1074 | Coxsackie | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-03-14 | 2016-04-05 | 15 | 2016-04-05 | 2016-03-14 | 2016-04-05 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03289 | Catskill | Climax |  | 12042 | G | 1071 | Coxsackie | TBD |  | 1980 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-03-14 | 2016-04-05 | 15 | 2016-04-05 | 2016-03-14 | 2016-04-05 | 15 |  |  |  |  | 35000 | [9 empty] | W
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03290 | Catskill | Climax |  | 12042 | G | 1071 | Coxsackie | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-03-14 | 2016-04-05 | 15 | 2016-04-05 | 2016-03-14 | 2016-04-05 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03291 | Catskill | Cairo |  | 12413 | G | 2043 | South Cairo | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-03-14 | 2016-04-05 | 15 | 2016-04-05 | 2016-03-14 | 2016-04-05 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03292 | Catskill | Earlton |  | 12058 | G | 2005 | North Catskill | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-03-14 | 2016-04-05 | 15 | 2016-04-05 | 2016-03-14 | 2016-04-05 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03293 | Catskill | Medusa |  | 12120 | G | 1092 | Westerlo | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-03-14 | 2016-04-05 | 15 | 2016-04-05 | 2016-03-14 | 2016-04-05 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03294 | Catskill | Greenville |  | 12083 | G | 2061 | Freehold | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-03-14 | 2016-04-05 | 15 | 2016-04-05 | 2016-03-14 | 2016-04-05 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03295 | Catskill | Round Top |  | 12473 | G | 2042 | South Cairo | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-03-14 | 2016-04-05 | 15 | 2016-04-05 | 2016-03-14 | 2016-04-05 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03296 | Catskill | Leeds |  | 12451 | G | 2005 | North Catskill | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-03-14 | 2016-04-05 | 15 | 2016-04-05 | 2016-03-14 | 2016-04-05 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03297 | Catskill | Cairo |  | 12413 | G | 2041 | South Cairo | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-03-14 | 2016-04-05 | 15 | 2016-04-05 | 2016-03-14 | 2016-04-05 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03298 | Catskill | Cairo |  | 12413 | G | 2043 | South Cairo | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-03-14 | 2016-04-05 | 15 | 2016-04-05 | 2016-03-14 | 2016-04-05 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03299 | Catskill | Cairo |  | 12413 | G | 2041 | South Cairo | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-03-14 | 2016-04-05 | 15 | 2016-04-05 | 2016-03-14 | 2016-04-05 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03300 | Catskill | Cairo |  | 12413 | G | 2041 | South Cairo | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-03-14 | 2016-04-05 | 15 | 2016-04-05 | 2016-03-14 | 2016-04-05 | 15 |  |  |  |  | 35000 | [9 empty] | W
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03301 | Catskill | Freehold |  | 12431 | G | 2071 | Freehold | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-03-14 | 2016-04-05 | 15 | 2016-04-05 | 2016-03-14 | 2016-04-05 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03302 | Catskill | Greenville |  | 12083 | G | 2061 | Freehold | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-03-14 | 2016-04-05 | 15 | 2016-04-05 | 2016-03-14 | 2016-04-05 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Green Street Power Partners, LLC | CH-03360 | Newburgh | Salisbury Mls |  | 12577 | G | 4095 | Bethlehem Rd | TBD |  | 12 | [13 empty] | NM | N | SMA SB6000TL-US 22 (2) | 2016-03-09 | 2016-03-21 | 8 | 2016-03-21 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | New York State Solar Farm | CH-03947 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8024 | Knapps Corners | N |  | 7.6 | [13 empty] | NM | N | SB-TL-3800 (2) | 2016-03-09 | 2016-03-21 | 8 | 2016-03-21 | [14 empty] | 2016-04-07 | 2016-04-07 |  | Y
Central Hudson |  | SolarCity | CH-06626 | Poughkeepsie | Poughkeepsie |  | 12601 | G | 6011 | Sand Dock | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2016-03-23 | 2016-04-06 | 9 | 2016-04-06 | [14 empty] | 2016-04-29 | 2016-05-06 |  | W
Central Hudson |  | SolarCity | CH-08040 | Newburgh | New Windsor |  | 12553 | G | 4046 | Union Ave | TBD |  | 1992 | [13 empty] | CDG | N | FRONIUS SYMO 24.0 (83) | 2016-05-12 | 2016-06-03 | 15 | 2016-06-03 | 2016-05-12 | 2016-06-03 | 15 |  |  |  |  | 32000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | SolarCity | CH-08041 | Newburgh | New Paltz |  | 12561 | G | 5023 | Ohioville | TBD |  | 1992 | [13 empty] | CDG | N | FRONIUS SYMO 24.0 (83) | 2016-05-12 | 2016-05-12 | 0 | 2016-05-12 | 2016-05-12 | 2016-06-03 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | SolarCity | CH-08042 | Catskill | Catskill |  | 12414 | G | 2003 | North Catskill | TBD |  | 1992 | [13 empty] | CDG | N | FRONIUS SYMO 24.0 (83) | 2016-05-12 | 2016-06-03 | 15 | 2016-06-03 | 2016-05-12 | 2016-06-03 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | SolarCity | CH-08043 | Fishkill | Fishkill |  | 12524 | G | 8063 | Merritt Park | TBD |  | 1992 | [13 empty] | CDG | N | FRONIUS SYMO 24.0 (83) | 2016-05-12 | 2016-06-03 | 15 | 2016-06-03 | 2016-05-12 | 2016-06-03 | 15 |  |  |  |  | 32000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | SolarCity | CH-08044 | Catskill | Athens |  | 12015 | G | 2003 | North Catskill | TBD |  | 1992 | [13 empty] | CDG | N | FRONIUS SYMO 24.0 (83) | 2016-05-12 | 2016-06-03 | 15 | 2016-06-03 | 2016-05-12 | 2016-06-03 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | SolarCity | CH-08046 | Poughkeepsie | Amenia |  | 12501 | G | 7095 | Smithfield | TBD |  | 1992 | [13 empty] | CDG | N | FRONIUS SYMO 24.0 (83) | 2016-05-12 | 2016-05-12 | 0 | 2016-05-12 | 2016-05-12 | 2016-06-03 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | SolarCity | CH-08047 | Poughkeepsie | Millerton |  | 12546 | G | 7095 | Smithfield | TBD |  | 1992 | [13 empty] | CDG | N | FRONIUS SYMO 24.0 (83) | 2016-05-12 | 2016-06-03 | 15 | 2016-06-03 | 2016-05-12 | 2016-06-03 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | SolarCity | CH-08048 | Poughkeepsie | Clinton Corners |  | 12514 | G | 7071 | Stanfordville | TBD |  | 1992 | [13 empty] | CDG | N | FRONIUS SYMO 24.0 (83) | 2016-05-12 | 2016-05-12 | 0 | 2016-05-12 | 2016-05-12 | 2016-06-03 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | SolarCity | CH-08049 | Poughkeepsie | Millbrook |  | 12545 | G | 7025 | Tinkertown | TBD |  | 1992 | [13 empty] | CDG | N | FRONIUS SYMO 24.0 (83) | 2016-05-12 | 2016-05-12 | 0 | 2016-05-12 | 2016-05-12 | 2016-06-03 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | SolarCity | CH-08050 | Poughkeepsie | Millbrook |  | 12545 | G | 7025 | Tinkertown | TBD |  | 1992 | [13 empty] | CDG | N | FRONIUS SYMO 24.0 (83) | 2016-05-12 | 2016-05-12 | 0 | 2016-05-12 | 2016-05-12 | 2016-06-03 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Trinity Solar | CH-08466 | Catskill | Ravena | Albany | 12143 | G | 1082 | New Baltimore | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A-US | 2016-03-09 | 2016-03-15 | 4 | 2016-03-15 | [14 empty] | 2016-03-09 | 2016-03-15 |  | Y
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03303 | Catskill | Catskill |  | 12414 | G | 2042 | South Cairo | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-03-14 | 2016-04-05 | 15 | 2016-04-05 | 2016-03-14 | 2016-04-05 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03304 | Catskill | Catskill |  | 12414 | G | 2001 | North Catskill | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-03-14 | 2016-04-05 | 15 | 2016-04-05 | 2016-03-14 | 2016-04-05 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03305 | Kingston | Woodbourne |  | 12788 | G | 3091 | Neversink | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-03-18 | 2016-04-11 | 15 | 2016-04-11 | 2016-03-18 | 2016-04-11 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03306 | Catskill | Leeds |  | 12451 | G | 2005 | North Catskill | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-03-18 | 2016-04-11 | 15 | 2016-04-11 | 2016-03-18 | 2016-04-11 | 15 |  |  |  |  | 35000 | [9 empty] | W
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03307 | Kingston | Ellenville |  | 12428 | G | 3076 | Greenfield Rd | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-03-18 | 2016-04-11 | 15 | 2016-04-11 | 2016-03-18 | 2016-04-11 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03308 | Newburgh | Wallkill |  | 12589 | G | 5043 | East Walden | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-03-18 | 2016-04-11 | 15 | 2016-04-11 | 2016-03-18 | 2016-04-11 | 15 |  |  |  |  | 35000 | [9 empty] | W
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03309 | Catskill | Round Top |  | 12473 | G | 2042 | South Cairo | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-03-18 | 2016-04-11 | 15 | 2016-04-11 | 2016-03-18 | 2016-04-11 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03310 | Catskill | Greenville |  | 12083 | G | 1091 | Westerlo | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-03-18 | 2016-04-11 | 15 | 2016-04-11 | 2016-03-18 | 2016-04-11 | 15 |  |  |  |  | 35000 | [9 empty] | W
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03311 | Catskill | Westerlo |  | 12193 | G | 1092 | Westerlo | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-03-18 | 2016-04-11 | 15 | 2016-04-11 | 2016-03-18 | 2016-04-11 | 15 |  |  |  |  | 35000 | [9 empty] | W
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03312 | Kingston | Saugerties |  | 12477 | G | 3002 | Saugerties | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-03-18 | 2016-04-11 | 15 | 2016-04-11 | 2016-03-18 | 2016-04-11 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Community Energy Inc | CH-00779 | Catskill | Greenville |  | 12083 | G | 2061 | Freehold | TBD |  | 2000 | [13 empty] | CDG | N | SMA AMERICA 20000TLUS (100) | 2016-03-18 | 2016-04-11 | 15 | 2016-04-11 | 2016-03-18 | 2016-04-11 | 15 |  |  |  |  | 35000 | [9 empty] | W
Central Hudson |  | Geo of Camden, LLC dba Solar Universe Camden | CH-01133 | Poughkeepsie | Lagrangevl | Dutchess | 12540 | G | 6057 | Todd Hill | N |  | 21 | [13 empty] | NM | N | (30) TenK LS700S | 2016-04-14 | 2016-04-27 | 9 | 2016-04-27 | [14 empty] | 2016-09-16 | 2016-09-16 |  | Y
Central Hudson |  | PosiGen Solar | CH-02875 | Catskill | Catskill | Greene | 12414 | G | 2003 | North Catskill | N |  | 3.87 | [13 empty] | NM | N | 18 ENPHASE M215-60-2LL-S22-IG | 2016-03-10 | 2016-03-18 | 6 | 2016-03-18 | [14 empty] | 2016-05-09 | 2016-05-20 |  | Y
Central Hudson |  | SolarCity | CH-04992 | Kingston | New Paltz | Ulster | 12561 | G | 3041 | Sturgeon Pool | N |  | 4.2 | [13 empty] | NM | N | ABB PVI-4.2 OUTD-S-US | 2016-03-10 | 2016-03-21 | 7 | 2016-03-21 | [14 empty] | 2016-04-05 | 2016-04-12 |  | Y
Central Hudson |  | SolarCity | CH-05607 | Catskill | Ravena | Albany | 12143 | G | 1081 | New Baltimore | N |  | 9 | [13 empty] | NM | N | ABB PVI-6.0 OUTD-S-US ABB PVI-3.0 OUTD-S-US | 2016-03-10 | 2016-03-21 | 7 | 2016-03-21 | [8 empty] | 350 | 350 |  | 2016-03-30 | 2016-03-30 | 2016-04-13 | 2016-04-13 | 2016-04-21 |  | Y
Central Hudson |  | SolarCity | CH-05910 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6092 | Manchester | N |  | 8.2 | [13 empty] | NM | N | Fronius Primo 8.2-1 208-240 | 2016-04-08 | 2016-04-22 | 10 | 2016-04-22 | [14 empty] | 2016-04-29 | 2016-05-06 |  | Y
Central Hudson |  | SolarCity | CH-06219 | Newburgh | Newburgh | Orange | 12550 | G | 4024 | Coldenham | N |  | 12 | [13 empty] | NM | N | PVI-6000-OUTD-US-Z-A (2) | 2016-03-10 | 2016-03-24 | 10 | 2016-03-24 | [14 empty] | 2016-05-23 | 2016-05-26 |  | Y
Central Hudson |  | SolarCity | CH-06279 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 12 | [13 empty] | NM | N | PVI-6000-OUTD-US-Z-A (2) | 2016-03-10 | 2016-03-24 | 10 | 2016-03-24 | [8 empty] | 350 | 350 |  | 2016-04-14 | 2016-04-14 | 2016-05-05 | 2016-05-05 | 2016-05-25 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06714 | Poughkeepsie | Lagrangevl | Dutchess | 12540 | G | 6053 | Todd Hill | N |  | 15.8 | [13 empty] | NM | N | Fronius Primo 7.6-1 Fronius Primo 8.2 | 2016-03-10 | 2016-03-24 | 10 | 2016-03-24 | [14 empty] | 2016-07-13 | 2016-07-13 |  | Y
Central Hudson |  | SolarCity | CH-07195 | Catskill | Coxsackie | Greene | 12051 | G | 1071 | Coxsackie | N |  | 8.2 | [13 empty] | NM | N | FRONIUS PRIMO 8.2 | 2016-03-10 | 2016-03-18 | 6 | 2016-03-18 | [8 empty] | 350 | 350 |  | 2016-03-29 | 2016-03-29 | 2016-04-21 | 2016-04-21 | 2016-04-27 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08750 | Poughkeepsie | Hyde Park |  | 12538 | G | 6073 | East Park | TBD |  | 3.01 | [13 empty] | NM | N | ENPHASE M215602LLS2XZC (14) | 2016-03-10 | 2016-03-24 | 10 | 2016-03-24 | [17 empty] | W
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08794 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7051 | Rhinebeck | N |  | 7.74 | [13 empty] | NM | N | ENPHASE M125602LLS2XZC (36) | 2016-03-18 | 2016-04-04 | 10 | 2016-04-04 | [14 empty] | 2016-07-25 | 2016-07-26 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08834 | Kingston | Kingston |  | 12401 | G | 1022 | East Kingston | TBD |  | 2.58 | [13 empty] | NM | N | 12 ENPHASE M215 602LLS2XZC | 2016-03-10 | 2016-03-18 | 6 | 2016-03-18 | [17 empty] | W
Central Hudson |  | Solar Alchemy | CH-08976 | Kingston | Accord | Ulster | 12404 | G | 3081 | Kerhonkson | N |  | 16 | [13 empty] | NM | N | 64 ENPHASE M250 | 2016-03-10 | 2016-03-21 | 7 | 2016-03-21 | [14 empty] | 2016-04-26 | 2016-04-27 |  | Y
Central Hudson |  | Community Energy Inc | CH-00780 | Newburgh | New Paltz |  | 12561 | G | 5031 | Galeville | TBD |  | 2000 | [13 empty] | CDG | N | SMA AMERICA 20000TLUS (100) | 2016-03-18 | 2016-04-11 | 15 | 2016-04-11 | 2016-03-18 | 2016-04-11 | 15 | 2016-12-05 | 2016-12-20 | 2017-03-20 | 60 | 35000 | [9 empty] | W
Central Hudson |  | Monolith Solar Associates LLC | CH-02655 | Catskill | Greenvl | Greene | 12083 | G | 2061 | Freehold | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE7600A-US | 2016-03-11 | 2016-03-28 | 10 | 2016-03-28 | [14 empty] | 2016-05-26 | 2016-05-31 |  | Y
Central Hudson |  | SolarCity | CH-06445 | Catskill | Durham | Greene | 12422 | G | 1092 | Westerlo | N |  | 5 | [13 empty] | NM | N | ABB PVI-5000 OUTD-US | 2016-03-11 | 2016-03-23 | 8 | 2016-03-23 | [14 empty] | 2016-04-01 | 2016-04-08 |  | Y
Central Hudson |  | Solar Generation | CH-08214 | Kingston | Ulster Pk | Ulster | 12487 | G | 3041 | Sturgeon Pool | N |  | 3.8 | [13 empty] | NM | N | SMA SB3800 TL | 2016-03-11 | 2016-03-23 | 8 | 2016-03-23 | [14 empty] | 2016-08-10 | 2016-08-15 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08807 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7054 | Rhinebeck | N |  | 6.02 | [13 empty] | NM | N | (28) ENPHASE M215 | 2016-03-11 | 2016-03-28 | 10 | 2016-03-28 | [14 empty] | 2016-07-08 | 2016-07-11 |  | Y
Central Hudson |  | Sol Providers | CH-08957 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6045 | Spackenkill | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE7600 | 2016-04-01 | 2016-04-07 | 4 | 2016-04-07 | [14 empty] | 2016-04-18 | 2016-04-25 |  | Y
Central Hudson |  | Solar Alchemy | CH-08992 | Kingston | Saugerties | Ulster | 12477 | G | 3001 | Saugerties | N |  | 4.25 | [13 empty] | NM | N | 17 ENPHASE M250 60-2LL-S2X | 2016-03-11 | 2016-03-23 | 8 | 2016-03-23 | [14 empty] | 2016-07-06 | 2016-07-08 |  | Y
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03313 | Newburgh | Campbell Hall |  | 10916 | G | 5051 | Maybrook | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-03-18 | 2016-04-11 | 15 | 2016-04-11 | 2016-03-18 | 2016-04-11 | 15 |  |  |  |  | 35000 | [9 empty] | W
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03314 | Newburgh | Wallkill |  | 12589 | G | 5011 | Modena | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-03-18 | 2016-04-11 | 15 | 2016-04-11 | 2016-03-18 | 2016-04-11 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03315 | Catskill | Catskill |  | 12414 | G | 2001 | North Catskill | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-03-18 | 2016-04-11 | 15 | 2016-04-11 | 2016-03-18 | 2016-04-11 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03316 | Catskill | Catskill |  | 12414 | G | 2042 | South Cairo | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-03-18 | 2016-04-11 | 15 | 2016-04-11 | 2016-03-18 | 2016-04-11 | 15 |  |  |  |  | 35000 | [9 empty] | W
Central Hudson |  | NRG Home Solar | CH-00476 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7062 | Milan | N |  | 6 | [13 empty] | NM | N | SOLAR EDGE SE6000A-US | 2016-03-14 | 2016-03-21 | 5 | 2016-03-21 | [14 empty] | 2016-06-02 | 2016-06-09 |  | Y
Central Hudson |  | NRG Home Solar | CH-04331 | Poughkeepsie | Salt Pt | Dutchess | 12578 | G | 7012 | Hibernia | N |  | 3.225 | [13 empty] | NM | N | (15) ENPHASE M215 | 2016-03-14 | 2016-03-21 | 5 | 2016-03-21 | [14 empty] | 2016-06-01 | 2016-06-07 |  | Y
Central Hudson |  | SolarCity | CH-05185 | Newburgh | Gardiner | Ulster | 12525 | G | 5031 | Galeville | N |  | 3 | [13 empty] | NM | N | ABB PVI-3.0-OUTD-S | 2016-03-14 | 2016-03-24 | 8 | 2016-03-24 | [14 empty] | 2016-03-28 | 2016-04-04 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-05561 | Catskill | Coeymans Hollow | Albany | 12046 | G | 1081 | New Baltimore | N |  | 4.2 | [13 empty] | NM | N | ABB PVI-4.2-OUTD-S US | 2016-03-14 | 2016-03-28 | 9 | 2016-03-28 | [14 empty] | 2016-07-14 | 2016-07-14 |  | Y
Central Hudson |  | SolarCity | CH-06198 | Newburgh | Newburgh | Orange | 12550 | G | 4014 | West Balmville | N |  | 12 | [13 empty] | NM | N | ABB PVI 6000 (2) | 2016-03-14 | 2016-03-24 | 8 | 2016-03-24 | [14 empty] | 2016-03-31 | 2016-04-07 |  | Y
Central Hudson |  | SolarCity | CH-06845 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8095 | Fishkill Plains | N |  | 9.2 | [13 empty] | NM | N | ABB PVI 4.2 ABB PVI 5.0 | 2016-03-28 | 2016-04-06 | 7 | 2016-04-06 | [14 empty] | 2016-06-03 | 2016-06-07 |  | Y
Central Hudson |  | SolarCity | CH-06939 | Fishkill | Beacon | Dutchess | 12508 | G | 8085 | Tioronda | N |  | 6.6 | [13 empty] | NM | N | ABB PVI 3.6 ABB PVI 3.0 | 2016-04-12 | 2016-04-18 | 4 | 2016-04-18 | [14 empty] | 2016-04-28 | 2016-05-05 |  | Y
Central Hudson |  | SolarCity | CH-07017 | Newburgh | New Windsor | Orange | 12553 | G | 4044 | Union Ave | N |  | 3.6 | [13 empty] | NM | N | ABB PVI-3 OUTD-S-US | 2016-03-14 | 2016-03-24 | 8 | 2016-03-24 | [14 empty] | 2016-07-27 | 2016-07-27 |  | Y
Central Hudson |  | SolarCity | CH-07424 | Newburgh | Newburgh | Orange | 12550 | G | 4023 | Coldenham | N |  | 6.6 | [13 empty] | NM | N | ABB PVI-3.6-OUTD-S ABB PVI-3.0-OUTD-S | 2016-03-14 | 2016-03-24 | 8 | 2016-03-24 | [14 empty] | 2016-07-25 | 2016-07-26 |  | Y
Central Hudson |  | SolarCity | CH-07567 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8093 | Fishkill Plains | N |  | 15.2 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 (2) | 2016-04-13 | 2016-04-19 | 4 | 2016-04-19 | [14 empty] | 2016-07-14 | 2016-07-15 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Infinity Solar Systems | CH-00139 | Newburgh | Washingtonvl | Orange | 10992 | G | 4097 | Bethlehem Rd | N |  | 8.8 | [13 empty] | NM | N | SMA AMERICA SB5000TL-US SMA AMERICA SB3800TL-US-22 | 2016-03-15 | 2016-03-29 | 9 | 2016-03-29 | [14 empty] | 2016-05-02 | 2016-05-06 |  | Y
Central Hudson |  | NRG Home Solar | CH-00519 | Newburgh | Newburgh | Orange | 12550 | G | 5001 | Marlboro | N | CH-00519 | 4.3 | [13 empty] | NM | N | ENPHASE M215 (20) | 2016-03-15 | 2016-03-24 | 7 | 2016-03-24 | [14 empty] | 2016-07-26 | 2016-07-27 |  | Y
Central Hudson |  | NRG Home Solar | CH-00551 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8091 | Fishkill Plains | N |  | 4.73 | [13 empty] | NM | N | ENPHASE M215 (22) | 2016-04-12 | 2016-04-18 | 4 | 2016-04-18 | [14 empty] | 2016-06-14 | 2016-06-15 |  | Y
Central Hudson |  | KG Solar & Renewable Energy, LLC | CH-02568 | Kingston | Kingston | Ulster | 12401 | G | 1022 | East Kingston | N |  | 3.87 | [13 empty] | NM | N | 18 ENPHASE M215 60 | 2016-03-15 | 2016-04-07 | 16 | 2016-04-07 | [14 empty] | 2016-09-27 | 2016-09-27 |  | Y
Central Hudson |  | SolarCity | CH-05887 | Poughkeepsie | Verbank | Dutchess | 12585 | G | 6057 | Todd Hill | N |  | 8 | [13 empty] | NM | N | (1) ABB PVI-5000 OUTD-US (1) ABB PVI-3.0 OUTD-US | 2016-05-24 | 2016-06-07 | 9 | 2016-06-07 | [14 empty] | 2016-06-09 | 2016-06-16 |  | Y
Central Hudson |  | Sungevity Inc | CH-09196 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6093 | Manchester | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000-OUTD-US-A | 2016-03-29 | 2016-04-05 | 5 | 2016-04-05 | [14 empty] | 2016-04-29 | 2016-05-06 |  | Y
Central Hudson |  | Sungevity Inc | CH-09578 | Newburgh | New Paltz | Ulster | 12561 | G | 5023 | Ohioville | N |  | 4.2 | [13 empty] | NM | N | ABB PVI-4.2-OUTD-S-US-A | 2016-04-14 | 2016-04-19 | 3 | 2016-04-19 | [14 empty] | 2016-05-17 | 2016-05-24 |  | Y
Central Hudson |  | Apex Solar Power | CH-00012 | Newburgh | Campbell Hall | Orange | 10916 | G | 5052 | Maybrook | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A-US | 2016-03-23 | 2016-04-05 | 8 | 2016-04-05 | [14 empty] | 2016-07-06 | 2016-07-11 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03627 | Newburgh | New Paltz | Ulster | 12561 | G | 5031 | Galeville | N |  | 15.2 | [13 empty] | NM | N | SOLAREDGE 7600 A-US (2) | 2016-03-23 | 2016-04-05 | 8 | 2016-04-05 | [14 empty] | 2016-04-25 | 2016-04-27 |  | Y
Central Hudson |  | New York State Solar Farm | CH-00419 | Kingston | Stone Ridge | Ulster | 12484 | G | 3023 | High Falls | N | CH-00419 | 6 | [13 empty] | NM | N | SMA AMERICA SB6000TL | 2016-03-16 | 2016-03-30 | 9 | 2016-03-30 | [14 empty] | 2016-08-04 | 2016-08-05 |  | Y
Central Hudson |  | SolarCity | CH-05554 | Catskill | Cairo | Greene | 12413 | G | 2071 | Freehold | N |  | 5 | [13 empty] | NM | N | ABB PVI 5000 | 2016-03-16 | 2016-03-30 | 9 | 2016-03-30 | [14 empty] | 2016-04-29 | 2016-04-29 |  | Y
Central Hudson |  | SolarCity | CH-07858 | Kingston | Woodstock |  | 12498 | G | 3013 | Woodstock | TBD |  | 3 | [13 empty] | NM | N | ABB PVI-3.0 OUTD-S-US | 2016-03-16 | 2016-03-30 | 9 | 2016-03-30 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | Trinity Solar | CH-08470 | Kingston | Rosendale | Ulster | 12472 | G | 1011 | Boulevard | N | CH-08470 | 3 | [13 empty] | NM | N | SOLAREDGE 3000A-US | 2016-03-16 | 2016-03-30 | 9 | 2016-03-30 | [14 empty] | 2017-11-01 | 2017-11-02 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08666 | Kingston | Kingston |  | 12401 | G | 2091 | Hurley Ave | TBD |  | 3.87 | [13 empty] | NM | N | 18 ENPASE 215 602LLS2XZC | 2016-03-16 | 2016-03-31 | 10 | 2016-03-31 | [17 empty] | W
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08734 | Catskill | Athens | Greene | 12015 | G | 2002 | North Catskill | N |  | 9.46 | [13 empty] | NM | N | 44 ENPHASE M215 602LLS2XZC | 2016-03-16 | 2016-03-30 | 9 | 2016-03-30 | [14 empty] | 2016-06-28 | 2016-07-05 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08839 | Fishkill | Wappingrs Fls |  | 12590 | G | 8046 | Myers Corners | TBD |  | 8.6 | [13 empty] | NM | N | ENPHASE M215 602LLS2XZC (40) | 2016-03-23 | 2016-04-05 | 8 | 2016-04-05 | [17 empty] | W
Central Hudson |  | Empire Solar Solutions | CH-00061 | Newburgh | Newburgh | Orange | 12550 | G | 5004 | Marlboro | N |  | 10 | [13 empty] | NM | N | SOLAREDGE 10.0 A | 2016-03-24 | 2016-04-05 | 7 | 2016-04-05 | [14 empty] | 2016-06-01 | 2016-06-03 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-00068 | Newburgh | Montgomery | Orange | 12549 | G | 5054 | Maybrook | N |  | 16.4 | [13 empty] | NM | N | FRONIUS 11.4 FRONIUS 5.0 | 2016-03-24 | 2016-04-05 | 7 | 2016-04-05 | [14 empty] | 2016-08-03 | 2016-08-04 |  | Y
Central Hudson |  | NRG Home Solar | CH-00484 | Newburgh | Plattekill | Ulster | 12568 | G | 5013 | Modena | N |  | 3.44 | [13 empty] | NM | N | ENPHASE M215-60-2LL-S22-IG (16) | 2016-03-24 | 2016-04-04 | 6 | 2016-04-04 | [14 empty] | 2016-06-14 | 2016-06-15 |  | Y
Central Hudson |  | SolarCity | CH-07506 | Kingston | Saugerties | Ulster | 12477 | G | 3004 | Saugerties | N |  | 3 | [13 empty] | NM | N | ABB PVI 3.0 | 2016-03-17 | 2016-04-01 | 10 | 2016-04-01 | [14 empty] | 2016-05-23 | 2016-05-27 |  | Y
Central Hudson |  | SolarCity | CH-07613 | Newburgh | New Paltz | Ulster | 12561 | G | 5011 | Modena | N |  | 15.2 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 (2) | 2016-03-17 | 2016-03-31 | 9 | 2016-03-31 | [14 empty] | 2016-04-08 | 2016-04-12 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07620 | Newburgh | Montgomery | Orange | 12549 | G | 4026 | Coldenham | N |  | 7.8 | [13 empty] | NM | N | ABB PVI 4.2 ABB PVI 3.6 | 2016-03-17 | 2016-03-31 | 9 | 2016-03-31 | [14 empty] | 2016-06-22 | 2016-06-28 |  | Y
Central Hudson |  | SolarCity | CH-07823 | Newburgh | Walden | Orange | 12586 | G | 5041 | East Walden | N | CH-06977 | 4.2 | [13 empty] | NM | N | ABB PVI-4.2-OUTD-S | 2016-04-11 | 2016-04-13 | 2 | 2016-04-13 | [14 empty] | 2016-04-18 | 2016-04-20 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08600 | Kingston | Saugerties | Ulster | 12477 | G | 3001 | Saugerties | N |  | 2.15 | [13 empty] | NM | N | 10 ENPHASE M215 602LLS2XZC | 2016-03-17 | 2016-04-04 | 11 | 2016-04-04 | [14 empty] | 2016-07-12 | 2016-07-13 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08825 | Kingston | Saugerties | Ulster | 12477 | G | 3001 | Saugerties | N | CH-08986 | 6.45 | [13 empty] | NM | N | 30 ENPHASE M215-60-2LL | 2016-03-17 | 2016-04-04 | 11 | 2016-04-04 | [14 empty] | 2016-06-13 | 2016-06-16 |  | Y
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03317 | Kingston | Napanoch |  | 12458 | G | 3076 | Greenfield Rd | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-03-30 | 2016-04-20 | 15 | 2016-04-20 | 2016-03-30 | 2016-04-20 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/25/16 Company Holiday.
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03318 | Catskill | Cairo |  | 12413 | G | 2042 | South Cairo | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-03-30 | 2016-04-20 | 15 | 2016-04-20 | 2016-03-30 | 2016-04-20 | 15 |  |  |  |  | 35000 | [9 empty] | W
Central Hudson |  | Infinity Solar Systems | CH-00152 | Fishkill | Fishkill | Dutchess | 12524 | G | 8094 | Fishkill Plains | N |  | 7 | [13 empty] | NM | N | SMA AMERICA SB7000TL-US-22 | 2016-03-18 | 2016-04-04 | 10 | 2016-04-04 | [14 empty] | 2016-05-09 | 2016-05-12 |  | Y
Central Hudson |  | NRG Home Solar | CH-00485 | Newburgh | Newburgh | Orange | 12550 | G | 4011 | West Balmville | N |  | 10 | [13 empty] | NM | N | SOLAR EDGE SE7600A | 2016-03-18 | 2016-04-04 | 10 | 2016-04-04 | [14 empty] | 2016-07-08 | 2016-07-13 |  | Y
Central Hudson |  | NRG Home Solar | CH-00567 | Kingston | Saugerties |  | 12477 | G | 2015 | Lincoln Park | TBD |  | 5.16 | [13 empty] | NM | N | 24 Enphase 215 | 2016-03-18 | 2016-04-04 | 10 | 2016-04-04 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | 129 Cream Street, LLC | CH-04862 | Poughkeepsie | Hyde Park | Dutchess | 12538 | G | 6073 | East Park | N |  | 3900 | [13 empty] | CDG | Y | 39 Chint Power Systems America CPS SCH100KTL-DO/US-600 (600V) (54) CHINT POWER CPSSCA36KTL | 2016-05-19 | 2016-06-09 | 14 | 2016-06-09 | 2016-05-19 | 2016-06-09 | 14 | 2017-05-16 | 2017-06-08 | 2017-09-01 | 60 | 20220.02 | 389752.5 | 280039.93 | 2017-11-30 | 2018-05-23 | 2018-05-23 | 2021-12-17 | 2021-12-21 | 2021-12-27 | 2022-03-25 | Y | Y | There are 2 accounts at this location, CH-04862 and CH-04863 with an aggregate CESIR Cost to Customer of $40,000 & Estimated Project Upgrade Costs of $483,753.
Central Hudson |  | Map Energy Solutions, LLC | CH-04863 | Poughkeepsie | Hyde Pk |  | 12538 | G | 6073 | East Park | N |  | 1944 | [13 empty] | CDG | Y | 54 Chint Power Systems America CPS SCA36KTL-DO/US (480V) [SI1] (54) CHINT POWER CPSSCA36KTL | 2016-05-19 | 2016-06-09 | 14 | 2016-06-09 | 2016-05-19 | 2016-06-09 | 14 | 2017-05-16 | 2017-06-08 | 2017-09-01 | 60 | 20000 | 241876.5 |  | 2017-11-30 | 2018-05-23 | 2018-05-23 |  |  |  |  | W |  | There are 2 accounts at this location, CH-04862 and CH-04863 with an aggregate CESIR Cost to Customer of $40,000 & Estimated Project Upgrade Costs of $483,753.
Central Hudson |  | Hudson Valley Wind Energy, LLC | CH-02546 | Poughkeepsie | Lagrangevl |  | 12540 | G | 6057 | Todd Hill | TBD |  | 450 | [13 empty] | NM | N | (15) SMA SunnyBoy TriPower 3000TL-US | 2016-05-04 | 2016-05-04 | 0 | 2016-05-04 | 2016-05-04 | 2016-05-25 | 15 | [5 empty] | 10100 | [8 empty] | W
Central Hudson |  | SolarCity | CH-05015 | Kingston | Saugerties | Ulster | 12477 | G | 3003 | Saugerties | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2016-03-18 | 2016-04-04 | 10 | 2016-04-04 | [14 empty] | 2016-04-07 | 2016-04-14 |  | Y
Central Hudson |  | SolarCity | CH-06156 | Newburgh | New Paltz |  | 12561 | G | 5023 | Ohioville | TBD |  | 600 | [13 empty] | NM | N | (25) FRONIUS SYMO 24.0-3 480 | 2016-06-15 | 2016-07-07 | 15 | 2016-07-07 | 2016-06-15 | 2016-07-07 | 15 |  |  |  |  | 35000 | [9 empty] | W
Central Hudson |  | SolarCity | CH-06295 | Newburgh | Plattekill | Ulster | 12568 | G | 5013 | Modena | N |  | 15.2 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 (2) | 2016-03-18 | 2016-04-04 | 10 | 2016-04-04 | [14 empty] | 2016-05-20 | 2016-05-25 |  | Y
Central Hudson |  | SolarCity | CH-08051 | Newburgh | New Paltz |  | 12561 | G | 5024 | Ohioville | TBD |  | 792 | [13 empty] | RNM | N | (33) FRONIUS SYMO 24.0-30480 | 2016-07-20 | 2016-08-10 | 15 | 2016-08-10 | 2016-07-20 | 2016-08-10 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | SolarCity | CH-08052 | Catskill | Cairo |  | 12413 | G | 2043 | South Cairo | TBD |  | 1992 | [13 empty] | CDG | N | (83) FRONIUS SYMO 24.0-3 | 2016-04-13 | 2016-05-04 | 15 | 2016-05-04 | 2016-04-13 | 2016-05-04 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08740 | Kingston | Hurley | Ulster | 12443 | G | 2093 | Hurley Ave | N |  | 5.16 | [13 empty] | NM | N | 24 Enphase M215 | 2016-03-18 | 2016-04-04 | 10 | 2016-04-04 | [14 empty] | 2017-01-03 | 2017-01-03 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08842 | Newburgh | New Paltz |  | 12561 | G | 5023 | Ohioville | TBD |  | 7.95 | [13 empty] | NM | N | ENPHASE M125 602LLS2XZC (37) | 2016-03-18 | 2016-04-04 | 10 | 2016-04-04 | [17 empty] | W
Central Hudson |  | Infinity Solar Systems | CH-00149 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8065 | Merritt Park | N |  | 6.4 | [13 empty] | NM | N | SUNPOWER SPR-E20-327 C-AC (20) | 2016-04-07 | 2016-04-14 | 5 | 2016-04-14 | [14 empty] | 2016-07-08 | 2016-07-08 |  | Y
Central Hudson |  | New York State Solar Farm | CH-00358 | Newburgh | Gardiner | Ulster | 12525 | G | 5043 | East Walden | N |  | 7.6 | [13 empty] | NM | N | SMA AMERICA SB TL (2) | 2016-03-21 | 2016-04-04 | 9 | 2016-04-04 | [14 empty] | 2016-04-28 | 2016-04-29 |  | Y
Central Hudson |  | Geo of Camden, LLC dba Solar Universe Camden | CH-01134 | Newburgh | Modena | Ulster | 12548 | G | 5012 | Modena | N |  | 5.16 | [13 empty] | NM | N | ENPHASE M215-60-2LL-S2X-IG (24) | 2016-03-30 | 2016-04-06 | 5 | 2016-04-06 | [14 empty] | 2016-04-27 | 2016-04-29 |  | Y
Central Hudson |  | SolarCity | CH-06582 | Kingston | Saugerties | Ulster | 12477 | G | 3001 | Saugerties | N |  | 5 | [13 empty] | NM | N | ABB PVI 5.0 | 2016-03-21 | 2016-04-05 | 10 | 2016-04-05 | [14 empty] | 2016-09-27 | 2016-09-28 |  | Y
Central Hudson |  | SolarCity | CH-07371 | Fishkill | Beacon | Dutchess | 12508 | G | 8015 | Forgebrook | N |  | 7.6 | [13 empty] | NM | N | 1 Fronius USA Fronius Primo 7.6-1 208-240 (208V) FRONIUS PRI 7.6 | 2016-03-21 | 2016-04-04 | 9 | 2016-04-04 | [14 empty] | 2018-02-07 | 2018-02-09 |  | Y
Central Hudson |  | SolarCity | CH-07538 | Poughkeepsie | Staatsburg | Dutchess | 12580 | G | 7042 | Staatsburg | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2016-03-21 | 2016-04-05 | 10 | 2016-04-05 | [14 empty] | 2016-08-24 | 2016-08-25 |  | Y
Central Hudson |  | SolarCity | CH-07842 | Catskill | Cairo |  | 12413 | G | 2043 | South Cairo | TBD |  | 3 | [13 empty] | NM | N | ABB PVI-3.0-OUTD-S-US | 2016-03-21 | 2016-04-05 | 10 | 2016-04-05 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08606 | Kingston | Kingston |  | 12401 | G | 1022 | East Kingston | TBD |  | 7.31 | [13 empty] | NM | N | 34 Enphase 215 | 2016-03-21 | 2016-04-05 | 10 | 2016-04-05 | [17 empty] | W
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08664 | Kingston | Kingston |  | 12401 | G | 1022 | East Kingston | TBD |  | 3.01 | [13 empty] | NM | N | 14 Enpase M215 | 2016-03-21 | 2016-04-05 | 10 | 2016-04-05 | [17 empty] | W
Central Hudson |  | Hudson Solar | CH-01458 | Newburgh | Wallkill | Ulster | 12589 | G | 5043 | East Walden | N |  | 10 | [13 empty] | NM | N | SOLAREDGE SE-10000 A-US-U | 2016-03-22 | 2016-04-04 | 8 | 2016-04-04 | [14 empty] | 2016-04-25 | 2016-04-27 |  | Y
Central Hudson |  | Hudson Solar | CH-02345 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7052 | Rhinebeck | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE-6000A-US-U | 2016-04-25 | 2016-04-25 | 0 | 2016-04-25 | [14 empty] | 2016-05-16 | 2016-05-23 |  | Y
Central Hudson |  | SolarCity | CH-06109 | Fishkill | Fishkill | Dutchess | 12524 | G | 8013 | Forgebrook | N |  | 11 | [13 empty] | NM | N | ABB PVI 6000 ABB PVI 5000 | 2016-04-15 | 2016-04-20 | 3 | 2016-04-20 | [14 empty] | 2016-06-28 | 2016-07-05 |  | Y
Central Hudson |  | SolarCity | CH-07314 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6097 | Manchester | N |  | 3 | [13 empty] | NM | N | SOLAREDGE SE 3000A | 2016-03-22 | 2016-04-05 | 9 | 2016-04-05 | [14 empty] | 2016-07-14 | 2016-07-14 |  | Y
Central Hudson |  | SolarCity | CH-07469 | Newburgh | Cornwall-Hdsn | Orange | 12520 | G | 4043 | Union Ave | N |  | 3 | [13 empty] | NM | N | ABB PVI 3.0 | 2016-03-22 | 2016-04-04 | 8 | 2016-04-04 | [14 empty] | 2016-09-22 | 2016-09-26 |  | Y
Central Hudson |  | Trinity Solar | CH-08527 | Catskill | Coxsackie | Greene | 12051 | G | 1072 | Coxsackie | N |  | 6 | [13 empty] | NM | N | SOLAREDGE 6000A-US | 2016-03-22 | 2016-04-06 | 10 | 2016-04-06 | [14 empty] | 2016-08-09 | 2016-08-10 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08693 | Fishkill | Wappingrs Fls |  | 12590 | G | 8092 | Fishkill Plains | TBD |  | 6.24 | [13 empty] | NM | N | ENPHASE M215 602LLS2XZC (29) | 2016-03-22 | 2016-04-04 | 8 | 2016-04-04 | [17 empty] | W
Central Hudson |  | Sungevity Inc | CH-09618 | Kingston | Stone Ridge |  | 12484 | G | 3023 | High Falls | TBD |  | 6.8 | [13 empty] | NM | N | ABB PVI-3.0-OUTD-S-US-A ABB PVI-3.8-OUTD-S-US-A | 2016-03-22 | 2016-04-06 | 10 | 2016-04-06 | [17 empty] | W
Central Hudson |  | New York State Solar Farm | CH-00391 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6096 | Manchester | N |  | 6.8 | [13 empty] | NM | N | SMA AMERICA SB TL 3.0 SMA AMERICA SB TL 3.8 | 2016-03-23 | 2016-04-05 | 8 | 2016-04-05 | [14 empty] | 2016-06-03 | 2016-06-10 |  | Y
Central Hudson |  | SolarCity | CH-05888 | Poughkeepsie | Lagrangevl | Dutchess | 12540 | G | 6057 | Todd Hill | N |  | 15.2 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 (2) | 2016-04-04 | 2016-04-18 | 10 | 2016-04-18 | [14 empty] | 2016-07-25 | 2016-07-26 |  | Y
Central Hudson |  | SolarCity | CH-06266 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 8 | [13 empty] | NM | N | ABB PVI 3.0 ABB PVI 5000 | 2016-03-23 | 2016-04-04 | 7 | 2016-04-04 | [14 empty] | 2016-04-06 | 2016-04-08 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07576 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8014 | Forgebrook | N |  | 6 | [13 empty] | NM | N | ABB PVI 3.0 (2) | 2016-03-23 | 2016-04-04 | 7 | 2016-04-04 | [14 empty] | 2016-04-06 | 2016-04-13 |  | Y
Central Hudson |  | SolarCity | CH-07851 | Kingston | Stone Ridge |  | 12484 | G | 3023 | High Falls | TBD |  | 6 | [13 empty] | NM | N | ABB PVI 6000 | 2016-03-23 | 2016-04-06 | 9 | 2016-04-06 | [17 empty] | W
Central Hudson |  | Trinity Solar | CH-08404 | Kingston | Grahamsvl | Sullivan | 12740 | G | 3091 | Neversink | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE 7600A-US | 2016-03-23 | 2016-04-06 | 9 | 2016-04-06 | [14 empty] | 2016-07-26 | 2016-07-26 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08635 | Kingston | Kingston | Ulster | 12401 | G | 1021 | East Kingston | N | CH-08635 | 5.8 | [13 empty] | NM | N | 27 ENPHASE M215 602LLS2XZC | 2016-03-23 | 2016-04-07 | 10 | 2016-04-07 | [14 empty] | 2016-08-02 | 2016-08-03 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08789 | Poughkeepsie | Staatsburg | Dutchess | 12580 | G | 7041 | Staatsburg | N |  | 5.16 | [13 empty] | NM | N | ENPHASE M215 602LLS2XZC (24) | 2016-04-01 | 2016-04-07 | 4 | 2016-04-07 | [14 empty] | 2016-11-09 | 2016-11-09 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08815 | Kingston | Kingston | Ulster | 12401 | G | 1024 | East Kingston | N |  | 8.17 | [13 empty] | NM | N | 38 ENPHASE M215 602LLS2XZC | 2016-03-23 | 2016-04-07 | 10 | 2016-04-07 | [14 empty] | 2016-10-10 | 2016-10-10 |  | Y
Central Hudson |  | Sungevity Inc | CH-09623 | Poughkeepsie | Poughkeepsie |  | 12603 | G | 6043 | Spackenkill | TBD |  | 3.8 | [13 empty] | NM | N | ABB PVI-3.8-OUTD-S-US-A | 2016-03-23 | 2016-04-06 | 9 | 2016-04-06 | [17 empty] | W
Central Hudson |  | Omni Navitas Holdings LLC | CH-04864 | Poughkeepsie | Gallatin |  | 12567 | G | 7085 | Ancram | TBD |  | 1944 | [13 empty] | CDG | N | CHINT POWER CPSSCA36KTL (54) | 2016-05-19 | 2016-06-09 | 14 | 2016-06-09 | 2016-05-19 | 2016-06-09 | 14 |  |  |  |  | 32000 | [9 empty] | W
Central Hudson |  | Omni Navitas Holdings LLC | CH-04865 | Poughkeepsie | Ancram |  | 12502 | G | 7091 | Pulvers Corners | TBD |  | 1944 | [13 empty] | CDG | N | CHINT POWER CPSSCA36KTL (54) | 2016-05-19 | 2016-06-10 | 15 | 2016-06-10 | 2016-05-19 | 2016-06-10 | 15 |  |  |  |  | 35000 | [9 empty] | W
Central Hudson |  | Hudson Solar | CH-01308 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7054 | Rhinebeck | N |  | 70 | [13 empty] | NM | N | (7) SOLAREDGE SE-10000A-US-U | 2016-04-28 | 2016-04-28 | 0 | 2016-04-28 | 2016-04-28 | 2016-05-19 | 15 | [5 empty] | 2775 | 1941.7174 |  | 2016-06-17 | 2016-06-17 | 2016-06-29 | 2016-06-30 | 2016-07-06 |  | Y
Central Hudson |  | Hudson Solar | CH-01546 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8092 | Fishkill Plains | N |  | 12 | [13 empty] | NM | N | SOLAREDGE SE-6000 A-US-U (2) | 2016-03-24 | 2016-04-06 | 8 | 2016-04-06 | [14 empty] | 2016-06-03 | 2016-06-07 |  | Y
Central Hudson |  | Hudson Solar | CH-01743 | Poughkeepsie | Staatsburg | Dutchess | 12580 | G | 7041 | Staatsburg | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE-6000 A-US-U | 2016-04-01 | 2016-04-06 | 3 | 2016-04-06 | [14 empty] | 2016-09-01 | 2016-09-01 |  | Y
Central Hudson |  | Hudson Solar | CH-02495 | Newburgh | Montgomery |  | 12549 | G | 5054 | Maybrook | TBD |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE-7600 A-US-U | 2016-03-24 | 2016-04-06 | 8 | 2016-04-06 | [17 empty] | W
Central Hudson |  | PosiGen Solar | CH-02922 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7062 | Milan | N |  | 5.16 | [13 empty] | NM | N | ENPHASE M215-60-2LL-S22-IG (24) | 2016-04-01 | 2016-04-07 | 4 | 2016-04-07 | [14 empty] | 2016-06-06 | 2016-06-13 |  | Y
Central Hudson |  | SolarCity | CH-05011 | Kingston | Kingston | Ulster | 12401 | G | 2016 | Lincoln Park | N |  | 8.6 | [13 empty] | NM | N | ABB PVI-5000 OUTD-US ABB PVI-3.6 OUTD-US | 2016-03-24 | 2016-04-08 | 10 | 2016-04-08 | [14 empty] | 2016-07-13 | 2016-07-14 |  | Y
Central Hudson |  | Trinity Solar | CH-08451 | Newburgh | Newburgh | Orange | 12550 | G | 4044 | Union Ave | N |  | 6 | [13 empty] | NM | N | SOLAREDGE 6000A-US | 2016-03-24 | 2016-04-06 | 8 | 2016-04-06 | [14 empty] | 2016-06-14 | 2016-06-15 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08748 | Kingston | Saugerties | Ulster | 12477 | G | 2015 | Lincoln Park | N |  | 7.74 | [13 empty] | NM | N | ENPHSE M215 602LLS2XZC (36) | 2016-03-24 | 2016-04-01 | 5 | 2016-04-01 | [14 empty] | 2016-07-07 | 2016-07-19 |  | Y
Central Hudson |  | Sungevity Inc | CH-09634 | Newburgh | Maybrook |  | 12543 | G | 5052 | Maybrook | TBD |  | 4.2 | [13 empty] | NM | N | ABB PVI-4.2-TL-OUTD | 2016-03-24 | 2016-04-06 | 8 | 2016-04-06 | [17 empty] | W
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03319 | Catskill | S Cairo |  | 12482 | G | 2005 | North Catskill | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-04-06 | 2016-04-27 | 15 | 2016-04-27 | 2016-04-06 | 2016-04-27 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Kasselman Solar | CH-03510 | Catskill | West Kill | Greene | 12492 | E | 2389 | Vinegar Hill | N |  | 11 | [13 empty] | NM | N | 44 Enphase M250 | 2016-03-28 | 2016-04-08 | 9 | 2016-04-08 | [14 empty] | 2016-06-17 | 2016-06-21 |  | Y
Central Hudson |  | New York State Solar Farm | CH-00456 | Newburgh | Clintondale | Ulster | 12515 | G | 5012 | Modena | N |  | 6.8 | [13 empty] | NM | N | SMA AMERICA SB TL 3000 SMA AMERICA SB TL 3800 | 2016-03-28 | 2016-04-06 | 7 | 2016-04-06 | [14 empty] | 2016-05-24 | 2016-05-31 |  | Y
Central Hudson |  | Dynamic Energy Solutions, LLC | CH-01085 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6045 | Spackenkill | N |  | 324 | [13 empty] | NM | N | CPS SCA36KTL (9) | 2016-05-23 | 2016-06-14 | 15 | 2016-06-14 | 2016-05-23 | 2016-06-14 | 15 | [5 empty] | 12150 | 12150 |  | 2016-09-12 | 2016-09-12 | 2017-07-15 | 2017-08-18 | 2017-08-18 |  | Y
Central Hudson |  | Hudson Solar | CH-02016 | Kingston | Stone Ridge | Ulster | 12484 | G | 3023 | High Falls | N |  | 8 | [13 empty] | NM | N | SOLAREDGE SE-5000 A-US-U SOLAREDGE SE-3000 A-US-U | 2016-03-28 | 2016-04-08 | 9 | 2016-04-08 | [14 empty] | 2016-06-01 | 2016-06-02 |  | Y
Central Hudson |  | PosiGen Solar | CH-02871 | Catskill | Climax | Greene | 12042 | G | 1071 | Coxsackie | N |  | 3.87 | [13 empty] | NM | N | 18 ENPHASE M215-60-2LL-S22-IG | 2016-03-28 | 2016-04-08 | 9 | 2016-04-08 | [14 empty] | 2016-06-07 | 2016-06-08 |  | Y
Central Hudson |  | SolarCity | CH-05017 | Kingston | Kingston | Ulster | 12401 | G | 2013 | Lincoln Park | N |  | 3 | [13 empty] | NM | N | ABB PVI-3.0-OUTD-S US | 2016-03-28 | 2016-04-08 | 9 | 2016-04-08 | [14 empty] | 2016-05-02 | 2016-05-10 |  | Y
Central Hudson |  | SolarCity | CH-05058 | Newburgh | Highland | Ulster | 12528 | G | 5022 | Ohioville | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2016-03-28 | 2016-04-06 | 7 | 2016-04-06 | [14 empty] | 2016-05-06 | 2016-05-10 |  | Y
Central Hudson |  | SolarCity | CH-05501 | Catskill | Leeds | Greene | 12451 | G | 2005 | North Catskill | N |  | 8.6 | [13 empty] | NM | N | ABB PVI-5000-OUTD US ABB PVI-3.6-OUTD-S US | 2016-06-29 | 2016-07-06 | 4 | 2016-07-06 | [14 empty] | 2016-07-07 | 2016-07-22 |  | Y
Central Hudson |  | SolarCity | CH-05634 | Kingston | High Fls | Ulster | 12440 | G | 3022 | High Falls | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE7600A | 2016-03-28 | 2016-04-08 | 9 | 2016-04-08 | [14 empty] | 2016-05-27 | 2016-05-31 |  | Y
Central Hudson |  | SolarCity | CH-05769 | Kingston | Kingston | Ulster | 12401 | G | 2013 | Lincoln Park | N |  | 3 | [13 empty] | NM | N | ABB PVI-3.0-OUTD-S US | 2016-03-28 | 2016-04-08 | 9 | 2016-04-08 | [14 empty] | 2016-05-02 | 2016-05-06 |  | Y
Central Hudson |  | SolarCity | CH-06081 | Fishkill | Fishkill | Dutchess | 12524 | G | 8094 | Fishkill Plains | N |  | 10 | [13 empty] | NM | N | ABB PVI-5000-OUTD US (2) | 2016-03-28 | 2016-04-06 | 7 | 2016-04-06 | [14 empty] | 2016-06-20 | 2016-06-21 |  | Y
Central Hudson |  | SolarCity | CH-06204 | Newburgh | Walden | Orange | 12586 | G | 5041 | East Walden | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2016-03-28 | 2016-04-06 | 7 | 2016-04-06 | [14 empty] | 2016-06-20 | 2016-06-21 |  | Y
Central Hudson |  | SolarCity | CH-06246 | Newburgh | New Windsor | Orange | 12553 | G | 4044 | Union Ave | N |  | 9.6 | [13 empty] | NM | N | ABB PVI 6000 ABB PVI 3.6 | 2016-03-28 | 2016-04-06 | 7 | 2016-04-06 | [14 empty] | 2016-05-02 | 2016-05-06 |  | Y
Central Hudson |  | SolarCity | CH-06991 | Newburgh | Newburgh | Orange | 12550 | G | 4023 | Coldenham | N |  | 3.6 | [13 empty] | NM | N | ABB PVI-3.6-OUTD-S US | 2016-03-28 | 2016-04-06 | 7 | 2016-04-06 | [14 empty] | 2017-01-05 | 2017-01-05 |  | Y
Central Hudson |  | SolarCity | CH-07146 | Newburgh | Montgomery | Orange | 12549 | G | 5073 | Montgomery | N |  | 3.6 | [13 empty] | NM | N | ABB PVI-3.6-OUTD-S | 2016-03-28 | 2016-04-06 | 7 | 2016-04-06 | [14 empty] | 2016-05-11 | 2016-05-17 |  | Y
Central Hudson |  | SolarCity | CH-07317 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7052 | Rhinebeck | N |  | 6.6 | [13 empty] | NM | N | (1) ABB PVI-3.0-OUTD-S (1) ABB PVI-3.6-OUTD-S | 2016-03-28 | 2016-04-04 | 5 | 2016-04-04 | [14 empty] | 2016-07-14 | 2016-07-14 |  | Y
Central Hudson |  | SolarCity | CH-07384 | Fishkill | Stormvl | Dutchess | 12582 | G | 8071 | Shenandoah | N |  | 3 | [13 empty] | NM | N | ABB PVI-3.0-OUTD-S US | 2016-03-28 | 2016-04-06 | 7 | 2016-04-06 | [14 empty] | 2016-05-11 | 2016-05-17 |  | Y
Central Hudson |  | SolarCity | CH-07670 | Newburgh | Gardiner | Ulster | 12525 | G | 5034 | Galeville | N |  | 3 | [13 empty] | NM | N | ABB PVI-3.0-OUTD-S US | 2016-03-28 | 2016-04-06 | 7 | 2016-04-06 | [14 empty] | 2016-05-02 | 2016-05-05 |  | Y
Central Hudson |  | SolarCity | CH-07856 | Kingston | Kingston |  | 12401 | G | 2017 | Lincoln Park | TBD |  | 5 | [13 empty] | NM | N | ABB PVI-5000-OUTD US | 2016-03-28 | 2016-04-08 | 9 | 2016-04-08 | [17 empty] | W
Central Hudson |  | Sunrun Inc. | CH-08343 | Newburgh | Newburgh |  | 12550 | G | 4011 | West Balmville | TBD |  | 3 | [13 empty] | NM | N | ENPHASE ENERGY M250-60-2LL-S2X (12) | 2016-03-28 | 2016-04-06 | 7 | 2016-04-06 | [17 empty] | W
Central Hudson |  | Trinity Solar | CH-08578 | Catskill | Catskill | Greene | 12414 | G | 2005 | North Catskill | N |  | 3.8 | [13 empty] | NM | N | SOLAREDGE SE3800A-US | 2016-03-28 | 2016-04-08 | 9 | 2016-04-08 | [14 empty] | 2016-07-26 | 2016-07-26 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-00174 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8046 | Myers Corners | N |  | 12 | [13 empty] | NM | N | SMA AMERICA SB6000TL-22 (2) | 2016-03-29 | 2016-04-06 | 6 | 2016-04-06 | [14 empty] | 2016-06-03 | 2016-06-09 |  | Y
Central Hudson |  | Murphy Solar Power | CH-02710 | Catskill | Greenvl | Greene | 12083 | G | 2061 | Freehold | N |  | 7 | [13 empty] | NM | N | SMA 7000US | 2016-08-01 | 2016-08-03 | 2 | 2016-08-03 | [14 empty] | 2016-08-24 | 2016-08-25 |  | Y
Central Hudson |  | SolarCity | CH-05511 | Catskill | Cairo | Greene | 12413 | G | 2041 | South Cairo | N |  | 3 | [13 empty] | NM | N | ABB PVI 3.0 | 2016-03-29 | 2016-04-08 | 8 | 2016-04-08 | [14 empty] | 2016-07-13 | 2016-07-13 |  | Y
Central Hudson |  | Trinity Solar | CH-08391 | Catskill | Greenvl | Greene | 12083 | G | 2061 | Freehold | N |  | 11.4 | [13 empty] | NM | N | SOLAREDGE SE11400A-US | 2016-03-29 | 2016-04-08 | 8 | 2016-04-08 | [14 empty] | 2016-05-17 | 2016-05-17 |  | Y
Central Hudson |  | Sungevity Inc | CH-09630 | Newburgh | Newburgh |  | 12550 | G | 4011 | West Balmville | TBD |  | 7.6 | [13 empty] | NM | N | ABB UNO-7.6-OUTD-S-US-A | 2016-03-29 | 2016-04-06 | 6 | 2016-04-06 | [17 empty] | W
Central Hudson |  | NRG Home Solar | CH-00549 | Catskill | Acra |  | 12405 | G | 2041 | South Cairo | N |  | 6.23 | [13 empty] | NM | N | 29 ENPHASE M215-60-2LL-S22-IG | 2016-03-30 | 2016-04-11 | 8 | 2016-04-11 | [14 empty] | 2016-04-19 | 2016-04-25 |  | W
Central Hudson |  | Omni Navitas Holdings LLC | CH-04866 | Poughkeepsie | Milan |  | 12571 | G | 7061 | Milan | TBD |  | 1920 | [13 empty] | CDG | N | SUNGROW SG60KU-M (32) | 2016-05-27 | 2016-06-20 | 15 | 2016-06-20 | 2016-05-27 | 2016-06-20 | 15 |  |  |  |  | 35000 | [9 empty] | W
Central Hudson |  | Omni Navitas Holdings LLC | CH-04867 | Poughkeepsie | Pine Plains |  | 12567 | G | 7091 | Pulvers Corners | TBD |  | 1920 | [13 empty] | CDG | N | SUNGROW SG60KU-M (32) | 2016-05-27 | 2016-06-20 | 15 | 2016-06-20 | 2016-05-27 | 2016-06-20 | 15 |  |  |  |  | 35000 | [9 empty] | W
Central Hudson |  | Omni Navitas Holdings LLC | CH-04868 | Poughkeepsie | Ancram |  | 12502 | G | 7091 | Pulvers Corners | TBD |  | 1944 | [13 empty] | CDG | N | CPS SCA36KTL (54) | 2016-05-20 | 2016-06-13 | 15 | 2016-06-13 | 2016-05-20 | 2016-06-13 | 15 |  |  |  |  | 35000 | [9 empty] | W
Central Hudson |  | Omni Navitas Holdings LLC | CH-04869 | Poughkeepsie | Pine Plains |  | 12567 | G | 7091 | Pulvers Corners | TBD |  | 1920 | [13 empty] | CDG | N | SUNGROW SG60KU-M (32) | 2016-05-27 | 2016-06-20 | 15 | 2016-06-20 | 2016-05-27 | 2016-06-20 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Omni Navitas Holdings LLC | CH-04870 | Poughkeepsie | Gallatin |  | 12567 | G | 7091 | Pulvers Corners | TBD |  | 1920 | [13 empty] | CDG | N | SUNGROW SG60KU-M (32) | 2016-05-27 | 2016-06-20 | 15 | 2016-06-20 | 2016-05-27 | 2016-06-20 | 15 |  |  |  |  | 35000 | [9 empty] | W
Central Hudson |  | Empire Solar Store | CH-01094 | Catskill | Palenvl | Greene | 12463 | G | 2001 | North Catskill | N |  | 7.7 | [13 empty] | NM | N | SMA AMERICA 7700 TLUS22 | 2016-03-30 | 2016-04-11 | 8 | 2016-04-11 | [14 empty] | 2016-07-26 | 2016-07-26 |  | Y
Central Hudson |  | SolarCity | CH-05844 | Poughkeepsie |  |  | 12538 | G | 6074 | East Park | TBD |  | 7.2 | [13 empty] | NM | N | ABB PVI 3.6 (2) | 2016-03-30 | 2016-05-25 | 40 | 2016-05-25 | [17 empty] | W
Central Hudson |  | SolarCity | CH-05868 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 7042 | Staatsburg | N |  | 7.2 | [13 empty] | NM | N | ABB PVI 3.0 ABB PVI 4.2 | 2016-03-30 | 2016-05-25 | 40 | 2016-05-25 | [14 empty] | 2016-07-14 | 2016-07-21 |  | Y
Central Hudson |  | SolarCity | CH-07418 | Newburgh | Newburgh | Orange | 12550 | G | 4051 | Union Ave | N |  | 8.6 | [13 empty] | NM | N | ABB PVI-5000 OUTD-US ABB PVI-3.6 OUTD-US | 2016-03-30 | 2016-04-06 | 5 | 2016-04-06 | [14 empty] | 2016-05-09 | 2016-05-12 |  | Y
Central Hudson |  | SolarCity | CH-07653 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 7024 | Tinkertown | N |  | 6 | [13 empty] | NM | N | ABB PVI 6000 | 2016-03-30 | 2016-05-25 | 40 | 2016-05-25 | [14 empty] | 2016-05-27 | 2016-06-06 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08638 | Catskill | Catskill | Greene | 12414 | G | 2001 | North Catskill | N | CH-08638 | 6.02 | [13 empty] | NM | N | 28 ENPHASE M215 602LLS2XZC | 2016-03-30 | 2016-04-11 | 8 | 2016-04-11 | [14 empty] | 2016-08-22 | 2016-08-22 |  | Y
Central Hudson |  | Sungevity Inc | CH-09509 | Newburgh | Maybrook | Orange | 12543 | G | 4026 | Coldenham | N |  | 5 | [13 empty] | NM | N | ABB PVI-5000-OUTD-U | 2016-03-30 | 2016-04-06 | 5 | 2016-04-06 | [14 empty] | 2016-05-31 | 2016-06-03 |  | Y
Central Hudson |  | Community Energy Inc | CH-00781 | Catskill | Greenville |  | 12083 | G | 2061 | Freehold | TBD |  | 2000 | [13 empty] | CDG | N | (100) SMA AMERICA 20000TL | 2016-04-06 | 2016-04-27 | 15 | 2016-04-27 | 2016-04-06 | 2016-04-27 | 15 |  |  |  |  | 35000 | [9 empty] | W
Central Hudson |  | Community Energy Inc | CH-00782 | Catskill | W Coxsackie |  | 12192 | G | 1071 | Coxsackie | TBD |  | 2000 | [13 empty] | CDG | N | (100) SMA AMERICA 20000TL | 2016-04-18 | 2016-04-18 | 0 | 2016-04-18 | 2016-04-18 | 2016-05-09 | 15 | 2017-05-22 | 2017-05-25 | 2017-08-21 | 60 | 35000 | [9 empty] | W
Central Hudson |  | Community Energy Inc | CH-00783 | Catskill | Greenville |  | 12083 | G | 2061 | Freehold | TBD |  | 2000 | [13 empty] | CDG | N | (100) SMA AMERICA 20000TL | 2016-04-18 | 2016-04-18 | 0 | 2016-04-18 | 2016-04-18 | 2016-05-09 | 15 |  |  |  |  | 35000 | [9 empty] | W
Central Hudson |  | Community Energy Inc | CH-00784 | Catskill | Freehold |  | 12431 | G | 2071 | Freehold | TBD |  | 2000 | [13 empty] | CDG | N | (100) SMA AMERICA 20000TL | 2016-04-18 | 2016-04-18 | 0 | 2016-04-18 | 2016-04-18 | 2016-05-09 | 15 |  |  |  |  | 35000 | [9 empty] | W
Central Hudson |  | Trinity Solar | CH-08381 | Catskill | Palenville |  | 12463 | G | 2001 | North Catskill | TBD |  | 13.6 | [13 empty] | NM | N | SOLAREDGE 7600A-US SOLAREDGE 6000A-US | 2016-03-31 | 2016-04-12 | 8 | 2016-04-12 | [17 empty] | W
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08788 | Kingston | Kingston | Ulster | 12401 | G | 2013 | Lincoln Park | N |  | 4.3 | [13 empty] | NM | N | 20 Enphase M215 | 2016-03-31 | 2016-04-12 | 8 | 2016-04-12 | [14 empty] | 2016-07-18 | 2016-07-21 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08843 | Newburgh | New Paltz |  | 12561 | G | 5023 | Ohioville | TBD |  | 4.51 | [13 empty] | NM | N | ENPHASE M215602LLS2XZC | 2016-03-31 | 2016-04-07 | 5 | 2016-04-07 | [17 empty] | W
Central Hudson |  | Sungevity Inc | CH-09205 | Newburgh | Montgomery | Orange | 12549 | G | 5072 | Montgomery | N |  | 3.8 | [13 empty] | NM | N | ABB PVI-3.8-OUTD-S-US-A | 2016-03-31 | 2016-04-07 | 5 | 2016-04-07 | [14 empty] | 2016-05-10 | 2016-05-16 |  | Y
Central Hudson |  | Sungevity Inc | CH-09219 | Newburgh | Milton | Ulster | 12547 | G | 5002 | Marlboro | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000-OUTD-US-A | 2016-03-31 | 2016-04-07 | 5 | 2016-04-07 | [14 empty] | 2016-05-11 | 2016-05-17 |  | Y
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03320 | Catskill | Greenville |  | 12083 | G | 1091 | Westerlo | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-04-06 | 2016-04-27 | 15 | 2016-04-27 | 2016-04-06 | 2016-04-27 | 15 |  |  |  |  | 35000 | [9 empty] | W
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03321 | Poughkeepsie | Millerton |  | 12546 | G | 7081 | Millerton | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-04-18 | 2016-05-09 | 15 | 2016-05-09 | 2016-04-18 | 2016-05-09 | 15 |  |  |  |  | 35000 | [9 empty] | W
Central Hudson |  | SolarCity | CH-05382 | Poughkeepsie | Pleasant Valley | Dutchess | 12569 | G | 6092 | Manchester | N |  | 6 | [13 empty] | NM | N | ABB PVI 6000 | 2016-04-01 | 2016-04-07 | 4 | 2016-04-07 | [14 empty] | 2016-04-11 | 2016-04-12 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-05471 | Fishkill | Fishkill | Dutchess | 12524 | G | 8014 | Forgebrook | N |  | 6 | [13 empty] | NM | N | ABB PVI 6000 | 2016-04-01 | 2016-04-07 | 4 | 2016-04-07 | [14 empty] | 2016-07-28 | 2016-08-01 |  | Y
Central Hudson |  | SolarCity | CH-06725 | Poughkeepsie | Lagrangevl | Dutchess | 12540 | G | 6052 | Todd Hill | Y | CH-06725 | 9 | [13 empty] | NM | N | ABB PVI 3.0 ABB PVI 6000 | 2016-05-05 | 2016-05-05 | 0 | 2016-05-05 | [14 empty] | 2016-05-27 | 2016-06-03 |  | Y
Central Hudson |  | Sunrun Inc. | CH-08352 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 6.6 | [13 empty] | NM | N | ABB PVI-3.0-OUTD-S-US-A ABB PVI-3.6-OUTD-S-US-A | 2016-04-07 | 2016-04-11 | 2 | 2016-04-11 | [14 empty] | 2016-06-14 | 2016-06-16 |  | Y
Central Hudson |  | Sun Mountain | CH-09122 | Kingston | Accord | Ulster | 12404 | G | 3083 | Kerhonkson | N |  | 6 | [13 empty] | NM | N | SMA AMERICA SB6000TL-US | 2016-04-01 | 2016-04-12 | 7 | 2016-04-12 | [14 empty] | 2016-06-06 | 2016-06-13 |  | Y
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03322 | Catskill | Medusa |  | 12120 | G | 1092 | Westerlo | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-04-27 | 2016-04-27 | 0 | 2016-04-27 | 2016-04-27 | 2016-05-18 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03323 | Catskill | Hunter |  | 12442 | E | 2389 | Vinegar Hill | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-05-31 | 2016-06-21 | 15 | 2016-06-21 | 2016-05-31 | 2016-06-21 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03324 | Kingston | Ellenville |  | 12428 | G | 3095 | Grimley Rd | TBD |  | 2000 | [13 empty] | CDG | N | SMA SC-2200-US | 2016-05-31 | 2016-06-21 | 15 | 2016-06-21 | 2016-05-31 | 2016-06-21 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | New York State Solar Farm | CH-00449 | Kingston | Saugerties | Ulster | 12477 | G | 3004 | Saugerties | N |  | 3.8 | [13 empty] | NM | N | SMA AMERICA SB3800 | 2016-04-04 | 2016-04-18 | 10 | 2016-04-18 | [14 empty] | 2016-05-23 | 2016-05-27 |  | Y
Central Hudson |  | Omni Navitas Holdings LLC | CH-04871 | Poughkeepsie | Pine Plains |  | 12567 | G | 7091 | Pulvers Corners | TBD |  | 1920 | [13 empty] | CDG | N | SUNGROW SG60KU-M (32) | 2016-05-27 | 2016-06-20 | 15 | 2016-06-20 | 2016-05-27 | 2016-06-20 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Omni Navitas Holdings LLC | CH-04873 | Poughkeepsie | Gallatin |  | 12567 | G | 7091 | Pulvers Corners | TBD |  | 1920 | [13 empty] | CDG | N | SUNGROW SG60KU-M (32) | 2016-05-27 | 2016-06-20 | 15 | 2016-06-20 | 2016-05-27 | 2016-06-20 | 15 |  |  |  |  | 35000 | [9 empty] | W
Central Hudson |  | Omni Navitas Holdings LLC | CH-04874 | Poughkeepsie | Pine Plains |  | 12567 | G | 7091 | Pulvers Corners | TBD |  | 1920 | [13 empty] | CDG | N | SUNGROW SG60KU-M (32) | 2016-05-27 | 2016-06-20 | 15 | 2016-06-20 | 2016-05-27 | 2016-06-20 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Omni Navitas Holdings LLC | CH-04875 | Poughkeepsie | Milan |  | 12571 | G | 7061 | Milan | TBD |  | 1920 | [13 empty] | CDG | N | SUNGROW SG60KU-M (32) | 2016-05-27 | 2016-06-20 | 15 | 2016-06-20 | 2016-05-27 | 2016-06-20 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Apex Solar Power | CH-00714 | Kingston | Kingston |  | 12401 | G | 2016 | Lincoln Park | TBD |  | 3.8 | [13 empty] | NM | N | SOLAREDGE SE3800A-US | 2016-04-04 | 2016-04-18 | 10 | 2016-04-18 | [17 empty] | W
Central Hudson |  | SolarCity | CH-05276 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8093 | Fishkill Plains | N |  | 9.2 | [13 empty] | NM | N | ABB PVI-4.2 OUTD-S-US ABB PVI-5000 OUTD-US | 2016-04-04 | 2016-04-07 | 3 | 2016-04-07 | [14 empty] | 2016-07-14 | 2016-07-15 |  | Y
Central Hudson |  | SolarCity | CH-05571 | Catskill | Westerlo | Albany | 12193 | G | 1091 | Westerlo | N |  | 10 | [13 empty] | NM | N | SOLAREDGE SE10000A | 2016-04-04 | 2016-04-18 | 10 | 2016-04-18 | [14 empty] | 2016-05-12 | 2016-06-01 |  | Y
Central Hudson |  | SolarCity | CH-05932 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6092 | Manchester | N |  | 3.8 | [13 empty] | NM | N | SOLAREDGE SE 3800A | 2016-04-04 | 2016-04-07 | 3 | 2016-04-07 | [14 empty] | 2016-06-20 | 2016-06-27 |  | Y
Central Hudson |  | SolarCity | CH-06321 | Newburgh | Marlboro | Ulster | 12542 | G | 5003 | Marlboro | N |  | 15.2 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 (2) | 2016-04-04 | 2016-04-07 | 3 | 2016-04-07 | [14 empty] | 2016-06-06 | 2016-06-08 |  | Y
Central Hudson |  | SolarCity | CH-07293 | Poughkeepsie | Staatsburg | Dutchess | 12580 | G | 7042 | Staatsburg | N |  | 9.2 | [13 empty] | NM | N | ABB PVI-5000OUTD-S-US ABB PVI-4.2 OUTD-S-US | 2016-05-03 | 2016-05-16 | 9 | 2016-05-16 | [14 empty] | 2016-07-07 | 2016-07-11 |  | Y
Central Hudson |  | SolarCity | CH-07422 | Newburgh | Newburgh | Orange | 12550 | G | 4024 | Coldenham | N |  | 3.6 | [13 empty] | NM | N | ABB PVI-3.6OUTD-S-US | 2016-04-04 | 2016-04-07 | 3 | 2016-04-07 | [14 empty] | 2016-10-03 | 2016-10-03 |  | Y
Central Hudson |  | US Energy Concierge, Inc. | CH-09733 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8096 | Fishkill Plains | N |  | 15.2 | [13 empty] | NM | N | SOLAREDGE SE7600A-US (2) | 2016-04-11 | 2016-04-15 | 4 | 2016-04-15 | [14 empty] | 2020-04-06 | 2020-04-06 |  | Y
Central Hudson |  | SolarCity | CH-06753 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6092 | Manchester | N |  | 3 | [13 empty] | NM | N | SOLAREDGE SE 3000A | 2016-04-05 | 2016-04-08 | 3 | 2016-04-08 | [14 empty] | 2016-07-11 | 2016-07-12 |  | Y
Central Hudson |  | SolarCity | CH-06898 | Fishkill | Fishkill | Dutchess | 12524 | G | 8014 | Forgebrook | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2016-04-05 | 2016-04-08 | 3 | 2016-04-08 | [14 empty] | 2016-04-28 | 2016-05-05 |  | Y
Central Hudson |  | SolarCity | CH-07360 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8092 | Fishkill Plains | N |  | 4.2 | [13 empty] | NM | N | ABB PVI-4.2 OUTD-S-US | 2016-04-05 | 2016-04-08 | 3 | 2016-04-08 | [14 empty] | 2016-04-26 | 2016-04-28 |  | Y
Central Hudson |  | SolarCity | CH-07456 | Newburgh | Milton | Ulster | 12547 | G | 5083 | Highland | N |  | 11 | [13 empty] | NM | N | ABB PVI 6000 ABB PVI 5000 | 2016-04-05 | 2016-04-08 | 3 | 2016-04-08 | [14 empty] | 2016-05-23 | 2016-05-27 |  | Y
Central Hudson |  | SolarCity | CH-07841 | Catskill | Catskill |  | 12414 | G | 2001 | North Catskill | TBD |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2016-04-05 | 2016-04-19 | 10 | 2016-04-19 | [17 empty] | W
Central Hudson |  | SolarCity | CH-07882 | Poughkeepsie | Lagrangevl |  | 12540 | G | 6052 | Todd Hill | TBD |  | 4.2 | [13 empty] | NM | N | ABB PVI 4.2 | 2016-04-05 | 2016-04-08 | 3 | 2016-04-08 | [17 empty] | W
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08615 | Fishkill | Beacon | Dutchess | 12508 | G | 8087 | Tioronda | N |  | 4.51 | [13 empty] | NM | N | ENPHASE M215 602LLS2XZC (21) | 2016-04-05 | 2016-04-08 | 3 | 2016-04-08 | [14 empty] | 2016-08-29 | 2016-08-29 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08634 | Newburgh | New Paltz | Ulster | 12561 | G | 5023 | Ohioville | N |  | 3.87 | [13 empty] | NM | N | ENPHASE M215 602LLS2XZC (18) | 2016-04-05 | 2016-04-08 | 3 | 2016-04-08 | [14 empty] | 2016-07-20 | 2016-07-21 |  | Y
Central Hudson |  | Solar Alchemy | CH-08993 | Kingston | Saugerties | Ulster | 12477 | G | 3001 | Saugerties | N |  | 2 | [13 empty] | NM | N | ENPHASE M250 60-2LL-S2X (8) | 2016-04-05 | 2016-04-19 | 10 | 2016-04-19 | [14 empty] | 2016-07-06 | 2016-07-08 |  | Y
Central Hudson |  | Solar Alchemy | CH-09003 | Kingston | Saugerties | Ulster | 12477 | G | 3001 | Saugerties | N |  | 3.5 | [13 empty] | NM | N | 14 ENPHASE M250 60-2LL-S2X | 2016-04-05 | 2016-04-19 | 10 | 2016-04-19 | [14 empty] | 2016-07-06 | 2016-07-08 |  | Y
Central Hudson |  | Sungevity Inc | CH-09249 | Newburgh | Campbell Hall | Orange | 10916 | G | 5051 | Maybrook | N |  | 6 | [13 empty] | NM | N | ABB PVI-3.0-OUTD-S-US-A (2) | 2016-04-05 | 2016-04-08 | 3 | 2016-04-08 | [14 empty] | 2016-05-31 | 2016-06-03 |  | Y
Central Hudson |  | Green Street Power Partners, LLC | CH-00114 | Newburgh | Walden |  | 12586 | G | 5041 | East Walden | TBD |  | 10 | [13 empty] | NM | N | SMA SB5000TL-US-22 (2) | 2016-04-06 | 2016-04-13 | 5 | 2016-04-13 | [17 empty] | W |  | Customer already had net meter prior to application.
Central Hudson |  | Infinity Solar Systems | CH-03445 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6094 | Manchester | N |  | 5 | [13 empty] | NM | N | SMA AMERICA SB5000TL-US | 2016-04-20 | 2016-04-27 | 5 | 2016-04-27 | [14 empty] | 2016-07-13 | 2016-07-13 |  | Y
Central Hudson |  | NRG Home Solar | CH-00520 | Newburgh | Wallkill | Ulster | 12589 | G | 5042 | East Walden | N |  | 4.3 | [13 empty] | NM | N | ENPHASE M215 (20) | 2016-04-06 | 2016-04-11 | 3 | 2016-04-11 | [14 empty] | 2016-06-20 | 2016-06-21 |  | Y
Central Hudson |  | SolarCity | CH-06243 | Newburgh | Newburgh | Orange | 12550 | G | 4051 | Union Ave | N |  | 8.4 | [13 empty] | NM | N | ABB PVI-4.2 OUTD-S-US (2) | 2016-04-06 | 2016-04-11 | 3 | 2016-04-11 | [14 empty] | 2016-07-26 | 2016-07-26 |  | Y
Central Hudson |  | Trinity Solar | CH-08461 | Catskill | Catskill | Greene | 12414 | G | 2006 | North Catskill | N |  | 10 | [13 empty] | NM | N | Solar Edge SE10000A-US | 2016-04-27 | 2016-04-28 | 1 | 2016-04-28 | [8 empty] | 350 | 350 |  | 2016-07-18 | 2016-07-18 | 2016-07-19 | 2016-07-28 | 2016-07-28 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-00056 | Newburgh | Highland | Ulster | 12528 | G | 5081 | Highland | N |  | 3.8 | [13 empty] | NM | N | SOLAREDGE 3800 A | 2016-04-14 | 2016-04-18 | 2 | 2016-04-18 | [14 empty] | 2016-05-06 | 2016-05-10 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-00222 | Fishkill | Wappingrs Fls |  | 12590 | G | 8092 | Fishkill Plains | TBD |  | 7.7 | [13 empty] | NM | N | SMA AMERICA SB7700TL-US-22 | 2016-04-07 | 2016-04-11 | 2 | 2016-04-11 | [17 empty] | W
Central Hudson |  | SolarCity | CH-07411 | Newburgh | New Paltz | Ulster | 12561 | G | 5024 | Ohioville | N |  | 9.2 | [13 empty] | NM | N | ABB PVI-5000 OUTD-US ABB PVI 4.2 OUTD-S-US | 2016-04-07 | 2016-04-11 | 2 | 2016-04-11 | [14 empty] | 2016-06-03 | 2016-06-07 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08785 | Kingston | Mount Marion | Ulster | 12456 | G | 2016 | Lincoln Park | N |  | 5.16 | [13 empty] | NM | N | 24 ENPHASE M215 602LLS2XZC | 2016-04-07 | 2016-04-21 | 10 | 2016-04-21 | [14 empty] | 2016-10-20 | 2016-10-20 |  | Y
Central Hudson |  | SolarCity | CH-05736 | Kingston | Saugerties | Ulster | 12477 | G | 3003 | Saugerties | N |  | 4.2 | [13 empty] | NM | N | ABB PVI 4.2 | 2016-04-08 | 2016-04-22 | 10 | 2016-04-22 | [14 empty] | 2016-06-20 | 2016-06-23 |  | Y
Central Hudson |  | SolarCity | CH-07040 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 15.2 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 (2) | 2016-04-08 | 2016-04-22 | 10 | 2016-04-22 | [8 empty] | 350 | 350 |  | 2016-05-09 | 2016-05-09 | 2016-05-05 | 2016-08-12 | 2016-08-16 |  | Y
Central Hudson |  | SolarCity | CH-07073 | Newburgh | Marlboro | Ulster | 12542 | G | 5003 | Marlboro | N |  | 9.6 | [13 empty] | NM | N | ABB PVI 3.6 ABB PVI 6.0 | 2016-04-08 | 2016-04-12 | 2 | 2016-04-12 | [14 empty] | 2016-08-17 | 2016-08-19 |  | Y
Central Hudson |  | SolarCity | CH-07309 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 7024 | Tinkertown | N |  | 12 | [13 empty] | NM | N | ABB PVI 6000 (2) | 2016-04-08 | 2016-04-12 | 2 | 2016-04-12 | [14 empty] | 2016-05-09 | 2016-05-11 |  | Y
Central Hudson |  | SolarCity | CH-07677 | Newburgh | New Windsor | Orange | 12553 | G | 4054 | Union Ave | N |  | 3 | [13 empty] | NM | N | ABB PVI 3.0 | 2016-04-08 | 2016-04-21 | 9 | 2016-04-21 | [14 empty] | 2016-07-15 | 2016-07-15 |  | Y
Central Hudson |  | Trinity Solar | CH-08423 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7054 | Rhinebeck | N |  | 6 | [13 empty] | NM | N | SOLAREDGE 6000A-US | 2016-04-08 | 2016-04-11 | 1 | 2016-04-11 | [14 empty] | 2016-11-15 | 2016-11-15 |  | Y
Central Hudson |  | Sunrise Solar Solutions, LLC | CH-09647 | Fishkill | Peekskill | Putnam | 10524 | G | 8066 | Merritt Park | N |  | 10.8 | [13 empty] | NM | N | ENPHASE M250 (45) | 2016-04-08 | 2016-04-13 | 3 | 2016-04-13 | [14 empty] | 2016-10-14 | 2016-10-14 |  | Y
Central Hudson |  | Hudson Solar | CH-02504 | Newburgh | Marlboro | Ulster | 12542 | G | 5003 | Marlboro | N | CH-01384 | 14.4 | [13 empty] | NM | N | SOLAREDGE SE14.4K US | 2016-04-18 | 2016-05-02 | 10 | 2016-05-02 | [14 empty] | 2016-07-18 | 2016-07-18 |  | Y
Central Hudson |  | SolarCity | CH-05557 | Catskill | Greenvl | Greene | 12083 | G | 2071 | Freehold | N |  | 3.6 | [13 empty] | NM | N | ABB PVI-3.6 OUTD-S-US | 2016-04-11 | 2016-04-15 | 4 | 2016-04-15 | [14 empty] | 2016-06-07 | 2016-06-08 |  | Y
Central Hudson |  | SolarCity | CH-05749 | Kingston | Kingston | Ulster | 12401 | G | 2016 | Lincoln Park | N |  | 3.6 | [13 empty] | NM | N | ABB PVI 3.6 | 2016-04-11 | 2016-04-15 | 4 | 2016-04-15 | [14 empty] | 2016-05-02 | 2016-05-06 |  | Y
Central Hudson |  | SolarCity | CH-06668 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6065 | Inwood Ave | N |  | 4.2 | [13 empty] | NM | N | ABB PVI-4.2 OUTD-S-US | 2016-04-11 | 2016-04-22 | 9 | 2016-04-22 | [14 empty] | 2016-04-28 | 2016-05-05 |  | Y
Central Hudson |  | SolarCity | CH-07920 | Newburgh | Montgomery |  | 12549 | G | 4021 | Coldenham | TBD |  | 6.6 | [13 empty] | NM | N | ABB PVI 3.6 ABB PVI 3.0 | 2016-04-11 | 2016-04-13 | 2 | 2016-04-13 | [17 empty] | W
Central Hudson |  | Sunrun Inc. | CH-08350 | Newburgh | Rock Tvrn | Orange | 12575 | G | 4097 | Bethlehem Rd | N |  | 7.6 | [13 empty] | NM | N | ABB UNO-7.6-TL-OUTD-S-US | 2016-05-26 | 2016-06-07 | 7 | 2016-06-07 | [14 empty] | 2016-06-22 | 2016-06-28 |  | Y
Central Hudson |  | Trinity Solar | CH-08380 | Newburgh | Newburgh | Orange | 12550 | G | 4011 | West Balmville | N |  | 11.4 | [13 empty] | NM | N | SOLAREDGE 11400A-US | 2016-04-11 | 2016-04-13 | 2 | 2016-04-13 | [14 empty] | 2016-07-13 | 2016-07-25 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08816 | Kingston | Kingston | Ulster | 12401 | G | 1021 | East Kingston | N |  | 7.52 | [13 empty] | NM | N | ENPHASE M215 602LLS2XZC (35) | 2016-04-11 | 2016-04-15 | 4 | 2016-04-15 | [14 empty] | 2016-10-13 | 2016-10-17 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-00163 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6045 | Spackenkill | N |  | 10.32 | [13 empty] | NM | N | 43 SUNPOWER SPR-E20-327 C-AC | 2016-04-12 | 2016-04-25 | 9 | 2016-04-25 | [14 empty] | 2016-06-20 | 2016-06-27 |  | Y
Central Hudson |  | NRG Home Solar | CH-00521 | Newburgh | Washingtonvl |  | 10992 | G | 4097 | Bethlehem Rd | TBD |  | 7.6 | [13 empty] | NM | N | SOLAR EDGE SE7600A | 2016-04-12 | 2016-04-15 | 3 | 2016-04-15 | [17 empty] | W
Central Hudson |  | PosiGen Solar | CH-02904 | Catskill | Catskill | Greene | 12414 | G | 2042 | South Cairo | N |  | 5.16 | [13 empty] | NM | N | ENPHASE M215-60-2LL-S22-IG (24) | 2016-04-12 | 2016-04-19 | 5 | 2016-04-19 | [14 empty] | 2016-06-10 | 2016-06-16 |  | Y
Central Hudson |  | SolarCity | CH-06376 | Newburgh | New Paltz | Ulster | 12561 | G | 5011 | Modena | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2016-04-12 | 2016-04-15 | 3 | 2016-04-15 | [14 empty] | 2016-04-19 | 2016-04-21 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08658 | Kingston | Cottekill | Ulster | 12419 | G | 3021 | High Falls | N | CH-08658 | 2.79 | [13 empty] | NM | N | ENPHASE M215 602LLS2XZC (13) | 2016-04-12 | 2016-04-15 | 3 | 2016-04-15 | [14 empty] | 2016-10-19 | 2016-10-19 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08717 | Newburgh | New Paltz | Ulster | 12561 | G | 5011 | Modena | N |  | 4.94 | [13 empty] | NM | N | ENPHASE M215 602LLS2XZC (23) | 2016-04-12 | 2016-04-14 | 2 | 2016-04-14 | [14 empty] | 2016-08-29 | 2016-08-29 |  | Y
Central Hudson |  | Con Edison Solutions | CH-00020 | Kingston | Saugerties | Ulster | 12477 | G | 3005 | Saugerties | N |  | 150 | [13 empty] | NM | N | 6 Yaskawa Solectria Solar PVI25TL-480-R {480V} [SI1] SOLECTRIA PVI28 (6) | 2016-10-31 | 2016-10-31 | 0 | 2016-10-31 | 2016-10-31 | 2016-11-21 | 15 | 2017-03-27 | 2017-06-15 | 2017-09-11 | 60 | 1500.96 | 21600 | 1903 |  | 2017-11-27 | 2017-11-27 | 2018-05-24 | 2019-05-20 | 2019-05-21 | 2019-08-06 | Y
Central Hudson |  | EnterSolar LLC | CH-00107 | Fishkill | Wappingrs Falls |  | 12590 | G | 8091 | Fishkill Plains | TBD |  | 1980 | [13 empty] | CDG | N | (55) SOLECTRIA RENEWABLES PVI 36TL | 2016-04-21 | 2016-04-21 | 0 | 2016-04-21 | 2016-04-21 | 2016-05-12 | 15 |  |  |  |  | 32000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | New York State Solar Farm | CH-00384 | Kingston | Saugerties | Ulster | 12477 | G | 3004 | Saugerties | N |  | 12 | [13 empty] | NM | N | SMA AMERICA SB6000TL (2) | 2016-04-13 | 2016-04-27 | 10 | 2016-04-27 | [8 empty] | 350 | 350 |  | 2016-05-09 | 2016-05-09 | 2016-06-06 | 2016-06-06 | 2016-06-07 |  | Y
Central Hudson |  | NRG Home Solar | CH-00477 | Newburgh | Newburgh |  | 12550 | G | 4011 | West Balmville | TBD |  | 3.23 | [13 empty] | NM | N | ENPHASE M215 (15) | 2016-04-13 | 2016-04-18 | 3 | 2016-04-18 | [17 empty] | W
Central Hudson |  | SolarCity | CH-06333 | Newburgh | Milton | Ulster | 12547 | G | 5002 | Marlboro | N |  | 5 | [13 empty] | NM | N | ABB PVI 5000 | 2016-04-13 | 2016-04-27 | 10 | 2016-04-27 | [14 empty] | 2016-05-02 | 2016-05-06 |  | Y
Central Hudson |  | SolarCity | CH-06366 | Newburgh | Wallkill | Ulster | 12589 | G | 5041 | East Walden | N |  | 3.6 | [13 empty] | NM | N | ABB PVI 3.6 | 2016-04-13 | 2016-04-18 | 3 | 2016-04-18 | [14 empty] | 2016-05-20 | 2016-05-25 |  | Y
Central Hudson |  | SolarCity | CH-06450 | Catskill | Preston Holw | Albany | 12469 | G | 1092 | Westerlo | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2016-04-13 | 2016-04-19 | 4 | 2016-04-19 | [14 empty] | 2016-05-11 | 2016-05-17 |  | Y
Central Hudson |  | SolarCity | CH-06489 | Kingston | Rosendale | Ulster | 12472 | G | 3022 | High Falls | N |  | 3.6 | [13 empty] | NM | N | ABB PVI 3.6 | 2016-04-13 | 2016-04-19 | 4 | 2016-04-19 | [14 empty] | 2016-05-18 | 2016-05-25 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08738 | Kingston | Port Ewen | Ulster | 12466 | G | 1012 | Boulevard | N |  | 9.675 | [13 empty] | NM | N | ENPHASE M215 (45) | 2016-04-13 | 2016-04-19 | 4 | 2016-04-19 | [14 empty] | 2016-08-05 | 2016-08-05 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08836 | Kingston | Saugerties |  | 12477 | G | 1021 | East Kingston | TBD |  | 9.24 | [13 empty] | NM | N | ENPHASE M215 (43) | 2016-04-13 | 2016-04-27 | 10 | 2016-04-27 | [8 empty] | 350 | 350 | [7 empty] | W |  | Customer already had net meter prior to application. Transformer upgrade required to accommodate PV installation.
Central Hudson |  | Empire Solar Solutions | CH-00036 | Kingston | Rosendale | Ulster | 12472 | G | 3021 | High Falls | N |  | 7.5 | [13 empty] | NM | N | FRONIUS 7.5 | 2016-04-21 | 2016-04-25 | 2 | 2016-04-25 | [14 empty] | 2016-06-14 | 2016-06-21 |  | Y
Central Hudson |  | New York State Solar Farm | CH-00475 | Newburgh | Rock Tvrn | Orange | 12575 | G | 4097 | Bethlehem Rd | N | CH-00374 | 1.19 | [13 empty] | NM | N | Sunpower 327AC (5) | 2016-04-20 | 2016-04-25 | 3 | 2016-04-25 | [14 empty] | 2016-06-22 | 2016-06-24 |  | Y
Central Hudson |  | NRG Home Solar | CH-00531 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6042 | Spackenkill | N |  | 4.95 | [13 empty] | NM | N | 23 ENPHASE M215 | 2016-04-14 | 2016-04-27 | 9 | 2016-04-27 | [14 empty] | 2016-07-11 | 2016-07-12 |  | Y
Central Hudson |  | SolarCity | CH-06128 | Fishkill | Stormvl | Dutchess | 12582 | G | 8071 | Shenandoah | N |  | 10 | [13 empty] | NM | N | FRONIUS IG PLUS 10.0 | 2016-04-14 | 2016-04-19 | 3 | 2016-04-19 | [14 empty] | 2016-05-18 | 2016-05-25 |  | Y
Central Hudson |  | SolarCity | CH-06484 | Kingston | Ulster Pk | Ulster | 12487 | G | 3041 | Sturgeon Pool | N |  | 8.2 | [13 empty] | NM | N | FRONIUS PRIMO 8.2 | 2016-04-14 | 2016-04-19 | 3 | 2016-04-19 | [14 empty] | 2016-05-18 | 2016-05-25 |  | Y
Central Hudson |  | SolarCity | CH-06892 | Fishkill | Beacon | Dutchess | 12508 | G | 8015 | Forgebrook | N |  | 3 | [13 empty] | NM | N | ABB PVI 3.0 | 2016-04-14 | 2016-04-19 | 3 | 2016-04-19 | [14 empty] | 2016-05-23 | 2016-05-27 |  | Y
Central Hudson |  | SolarCity | CH-07680 | Newburgh | Newburgh | Orange | 12550 | G | 4014 | West Balmville | N |  | 3 | [13 empty] | NM | N | ABB PVI 3.0 | 2016-04-14 | 2016-04-19 | 3 | 2016-04-19 | [14 empty] | 2016-07-14 | 2016-07-15 |  | Y
Central Hudson |  | Solar Generation | CH-08087 | Kingston | Woodstock | Ulster | 12498 | G | 3013 | Woodstock | N |  | 5 | [13 empty] | NM | N | SMA 5000 | 2016-06-22 | 2016-07-05 | 8 | 2016-07-05 | [14 empty] | 2016-09-19 | 2016-11-16 |  | Y |  | 7/13/16 - CH Rep at site to install net meter; customer initially refused net meter install. Net meter installed 11/11/16.
Central Hudson |  | Solar Generation | CH-08251 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7041 | Staatsburg | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE 7600A US | 2016-08-15 | 2016-08-15 | 0 | 2016-08-15 | [14 empty] | 2016-11-02 | 2016-11-02 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08667 | Kingston | Kingston |  | 12401 | G | 1022 | East Kingston | TBD |  | 1.72 | [13 empty] | NM | N | ENPHASE M215602LLS2XZC (8) | 2016-04-14 | 2016-04-19 | 3 | 2016-04-19 | [17 empty] | W
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08716 | Newburgh | New Paltz |  | 12561 | G | 5011 | Modena | TBD |  | 3.65 | [13 empty] | NM | N | ENPHASE M215 602LLS2XZC (17) | 2016-04-14 | 2016-04-18 | 2 | 2016-04-18 | [17 empty] | W
Central Hudson |  | Omni Navitas Holdings LLC | CH-04876 | Poughkeepsie | Gallatin |  | 12567 | G | 7085 | Ancram | TBD |  | 1944 | [13 empty] | CDG | N | CHINT POWER CPSSCA36KTL (54) | 2016-05-19 | 2016-06-09 | 14 | 2016-06-09 | 2016-05-19 | 2016-06-09 | 14 |  |  |  |  | 32000 | [9 empty] | W
Central Hudson |  | Omni Navitas Holdings LLC | CH-04877 | Poughkeepsie | Ancram |  | 12502 | G | 7085 | Ancram | TBD |  | 1944 | [13 empty] | CDG | N | CHINT POWER CPSSCA36KTL (54) | 2016-05-19 | 2016-06-09 | 14 | 2016-06-09 | 2016-05-19 | 2016-06-09 | 14 |  |  |  |  | 32000 | [9 empty] | W
Central Hudson |  | Omni Navitas Holdings LLC | CH-04878 | Poughkeepsie | Hyde Park |  | 12538 | G | 6061 | Inwood Ave | TBD |  | 1944 | [13 empty] | CDG | N | CHINT POWER CPSSCA36KTL (54) | 2016-05-19 | 2016-06-09 | 14 | 2016-06-09 | 2016-05-19 | 2016-06-09 | 14 |  |  |  |  | 35000 | [9 empty] | W
Central Hudson |  | Community Energy Inc | CH-00785 | Catskill | Earlton |  | 12058 | G | 2061 | Freehold | TBD |  | 2000 | [13 empty] | CDG | N | (100) SMA AMERICA 20000TL | 2016-04-27 | 2016-04-27 | 0 | 2016-04-27 | 2016-04-27 | 2016-05-18 | 15 |  |  |  |  | 35000 | [9 empty] | W
Central Hudson |  | Community Energy Inc | CH-00786 | Catskill | Greenville |  | 12083 | G | 2061 | Freehold | TBD |  | 2000 | [13 empty] | CDG | N | (100) SMA AMERICA 20000TL | 2016-05-04 | 2016-05-18 | 10 | 2016-05-18 | 2016-05-04 | 2016-05-25 | 15 |  |  |  |  | 35000 | [9 empty] | W
Central Hudson |  | Community Energy Inc | CH-00787 | Catskill | Westerlo |  | 12193 | G | 1091 | Westerlo | TBD |  | 2000 | [13 empty] | CDG | N | (100) SMA AMERICA 20000TL | 2016-04-27 | 2016-04-27 | 0 | 2016-04-27 | 2016-04-27 | 2016-05-18 | 15 |  |  |  |  | 35000 | [9 empty] | W
Central Hudson |  | Monolith Solar Associates LLC | CH-02674 | Catskill | Catskill | Greene | 12414 | G | 2042 | South Cairo | N |  | 7.6 | [13 empty] | NM | N | SOLAR EDGE SE7600A-US | 2016-05-11 | 2016-05-11 | 0 | 2016-05-11 | [14 empty] | 2016-05-26 | 2016-05-31 |  | Y
Central Hudson |  | SolarCity | CH-06206 | Newburgh | Walden | Orange | 12586 | G | 5041 | East Walden | N |  | 11.4 | [13 empty] | NM | N | FRONIUS IG PLUS 11.4 | 2016-04-22 | 2016-04-25 | 1 | 2016-04-25 | [14 empty] | 2016-06-08 | 2016-06-14 |  | Y
Central Hudson |  | SolarCity | CH-07355 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8096 | Fishkill Plains | N |  | 12 | [13 empty] | NM | N | ABB PVI 6.0 (2) | 2016-04-15 | 2016-04-20 | 3 | 2016-04-20 | [14 empty] | 2016-05-18 | 2016-05-25 |  | Y
Central Hudson |  | SolarCity | CH-07381 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8093 | Fishkill Plains | N |  | 12 | [13 empty] | NM | N | ABB PVI 6.0 (2) | 2016-04-15 | 2016-04-29 | 10 | 2016-04-29 | [14 empty] | 2016-07-13 | 2016-07-14 |  | Y
Central Hudson |  | SolarCity | CH-07803 | Catskill | W Coxsackie | Greene | 12192 | G | 1071 | Coxsackie | N | CH-05592 | 3 | [13 empty] | NM | N | ABB PVI 3.0 | 2016-04-15 | 2016-04-19 | 2 | 2016-04-19 | [14 empty] | 2016-07-14 | 2016-07-15 |  | Y
Central Hudson |  | SolarCity | CH-07843 | Catskill | Durham |  | 12422 | G | 1092 | Westerlo | TBD |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2016-04-15 | 2016-04-19 | 2 | 2016-04-19 | [17 empty] | W
Central Hudson |  | Solar Generation | CH-08262 | Kingston | Accord | Ulster | 12404 | G | 3082 | Kerhonkson | N |  | 15.2 | [13 empty] | NM | N | SOLAREDGE 7600A (2) | 2016-06-15 | 2016-06-29 | 10 | 2016-06-29 | [14 empty] | 2016-08-29 | 2016-08-29 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-00048 | Poughkeepsie | Stanfordvl | Dutchess | 12581 | G | 7072 | Stanfordville | N |  | 12 | [13 empty] | NM | N | 2 FRONIUS 6.0 | 2016-05-02 | 2016-05-02 | 0 | 2016-05-02 | [14 empty] | 2016-07-08 | 2016-07-11 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-00083 | Poughkeepsie | Pine Plns | Dutchess | 12567 | G | 7091 | Pulvers Corners | N |  | 7.7 | [13 empty] | NM | N | SMA AMERICA 7700TLUS22 | 2016-04-18 | 2016-04-29 | 9 | 2016-04-29 | [14 empty] | 2016-05-24 | 2016-06-01 |  | Y
Central Hudson |  | Direct Energy Solar | CH-01024 | Newburgh | Wallkill | Ulster | 12589 | G | 5043 | East Walden | N |  | 6.45 | [13 empty] | NM | N | ENPHASE M215 (30) | 2016-04-20 | 2016-04-21 | 1 | 2016-04-21 | [14 empty] | 2016-07-22 | 2016-07-25 |  | Y
Central Hudson |  | Hudson Solar | CH-01614 | Catskill | Catskill | Greene | 12414 | G | 2006 | North Catskill | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE-6000A-US-U | 2016-04-18 | 2016-04-19 | 1 | 2016-04-19 | [14 empty] | 2016-05-20 | 2016-05-25 |  | Y
Central Hudson |  | Hudson Solar | CH-01638 | Catskill | New Baltimore | Greene | 12124 | G | 1083 | New Baltimore | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE-6000A-US-U | 2016-04-18 | 2016-04-19 | 1 | 2016-04-19 | [14 empty] | 2016-06-13 | 2016-06-16 |  | Y
Central Hudson |  | Hudson Solar | CH-02280 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7051 | Rhinebeck | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE-5000A-US-U | 2016-05-02 | 2016-05-02 | 0 | 2016-05-02 | [14 empty] | 2016-05-16 | 2016-05-23 |  | Y
Central Hudson |  | SolarCity | CH-05412 | Newburgh | Newburgh | Orange | 12550 | G | 4011 | West Balmville | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000 OUTD-US | 2016-04-18 | 2016-04-20 | 2 | 2016-04-20 | [14 empty] | 2016-06-06 | 2016-06-08 |  | Y
Central Hudson |  | Trinity Solar | CH-08438 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8093 | Fishkill Plains | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE 7600A-US | 2016-04-22 | 2016-04-26 | 2 | 2016-04-26 | [14 empty] | 2016-06-02 | 2016-06-10 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08699 | Fishkill | Fishkill | Dutchess | 12524 | G | 8014 | Forgebrook | N |  | 11.39 | [13 empty] | NM | N | ENPHASE M215 602LLS2XZC (53) | 2016-04-18 | 2016-04-20 | 2 | 2016-04-20 | [14 empty] | 2016-07-28 | 2016-07-28 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08747 | Kingston | Kingston |  | 12401 | G | 2013 | Lincoln Park | TBD |  | 5.59 | [13 empty] | NM | N | ENPHASE M215602LLS2XZC (26) | 2016-04-18 | 2016-04-19 | 1 | 2016-04-19 | [17 empty] | W
Central Hudson |  | You Save Green | CH-09967 | Newburgh | Walden |  | 12586 | G | 5043 | East Walden | TBD |  | 1980 | [13 empty] | CDG | N | (55) Solectria PVI 36TL | 2016-04-29 | 2016-05-13 | 10 | 2016-05-13 | 2016-04-29 | 2016-05-20 | 15 |  |  |  |  | 35000 | [9 empty] | W
Central Hudson |  | Lighthouse Solar | CH-00296 | Newburgh | New Paltz | Ulster | 12561 | G | 5024 | Ohioville | N |  | 11.4 | [13 empty] | NM | N | SOLAREDGE 11400 A-US | 2016-04-21 | 2016-04-25 | 2 | 2016-04-25 | [14 empty] | 2016-05-16 | 2016-05-23 |  | Y
Central Hudson |  | Hudson Solar | CH-01824 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7055 | Rhinebeck | N |  | 5.76 | [13 empty] | NM | N | SUNPOWER SPR-E20-327-C-AC | 2016-05-03 | 2016-05-16 | 9 | 2016-05-16 | [14 empty] | 2016-06-20 | 2016-06-23 |  | Y
Central Hudson |  | SolarCity | CH-06537 | Kingston | Woodstock | Ulster | 12498 | G | 3012 | Woodstock | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2016-04-19 | 2016-04-25 | 4 | 2016-04-25 | [14 empty] | 2016-09-22 | 2016-09-28 |  | Y
Central Hudson |  | SolarCity | CH-07047 | Newburgh | New Windsor | Orange | 12553 | G | 4042 | Union Ave | N |  | 8.2 | [13 empty] | NM | N | FRONIUS PRIMO 8.2 | 2016-04-21 | 2016-04-25 | 2 | 2016-04-25 | [14 empty] | 2016-05-18 | 2016-05-25 |  | Y
Central Hudson |  | Trinity Solar | CH-08389 | Catskill | Greenville | Greene | 12083 | G | 2061 | Freehold | N |  | 7.6 | [13 empty] | NM | N | SOLAR EDGE SE76000A-US | 2016-04-19 | 2016-04-25 | 4 | 2016-04-25 | [14 empty] | 2016-07-14 | 2016-07-14 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08621 | Kingston | Hurley | Ulster | 12443 | G | 2094 | Hurley Ave | N |  | 10.75 | [13 empty] | NM | N | ENPHASE M215 602LLS2XZC (50) | 2016-04-19 | 2016-04-25 | 4 | 2016-04-25 | [14 empty] | 2016-12-30 | 2016-12-30 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08652 | Catskill | Catskill | Greene | 12414 | G | 2003 | North Catskill | N |  | 2.58 | [13 empty] | NM | N | ENPHASE M215602LLS2XZC (12) | 2016-04-19 | 2016-04-25 | 4 | 2016-04-25 | [14 empty] | 2016-08-08 | 2016-08-10 |  | Y
Central Hudson |  | Sungevity Inc | CH-09606 | Newburgh | Highland | Ulster | 12528 | G | 5082 | Highland | N |  | 3 | [13 empty] | NM | N | ABB PVI-3.0-OUTD-S-US-A | 2016-05-02 | 2016-05-02 | 0 | 2016-05-02 | [14 empty] | 2016-06-17 | 2016-06-24 |  | Y
Central Hudson |  | CEC Development, LLC | CH-03114 | Kingston | Saugerties |  | 12477 | G | 3003 | Saugerties | TBD |  | 1980 | [13 empty] | CDG | N | (55) SOLECTRIA PVI 36TL | 2016-06-02 | 2016-06-23 | 15 | 2016-06-23 | 2016-06-02 | 2016-06-23 | 15 | 2017-05-16 | 2017-05-22 | 2017-08-16 | 60 | 35000 | [9 empty] | W
Central Hudson |  | Matrix Development LLC | CH-03912 | Kingston | Saugerties |  | 12477 | G | 3014 | Woodstock | TBD |  | 1980 | [13 empty] | CDG | N | (55) SOLECTRIA PVI 36TL | 2016-06-02 | 2016-06-23 | 15 | 2016-06-23 | 2016-06-02 | 2016-06-23 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Matrix Development LLC | CH-03913 | Kingston | Saugerties |  | 12477 | G | 3014 | Woodstock | TBD |  | 1980 | [13 empty] | CDG | N | (55) SOLECTRIA PVI 36TL | 2016-06-02 | 2016-06-23 | 15 | 2016-06-23 | 2016-06-02 | 2016-06-23 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Matrix Development LLC | CH-03914 | Kingston | Saugerties |  | 12477 | G | 3002 | Saugerties | TBD |  | 1980 | [13 empty] | CDG | N | (55) SOLECTRIA PVI 36TL | 2016-06-02 | 2016-06-23 | 15 | 2016-06-23 | 2016-06-02 | 2016-06-23 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Matrix Development LLC | CH-03915 | Kingston | Saugerties |  | 12477 | G | 3002 | Saugerties | TBD |  | 1980 | [13 empty] | CDG | N | (55) SOLECTRIA PVI 36TL | 2016-06-02 | 2016-06-23 | 15 | 2016-06-23 | 2016-06-02 | 2016-06-23 | 15 |  |  |  |  | 35000 | [9 empty] | W
Central Hudson |  | Matrix Development LLC | CH-03916 | Kingston | Saugerties |  | 12477 | G | 3002 | Saugerties | TBD |  | 1980 | [13 empty] | CDG | N | (33) SOLECTRIA PVI 60TL | 2016-06-02 | 2016-06-23 | 15 | 2016-06-23 | 2016-06-02 | 2016-06-23 | 15 | 2017-07-14 | 2017-07-14 | 2017-10-09 | 60 | 17387.47 | 1001322 | [7 empty] | 2018-05-24 | W
Central Hudson |  | Matrix Development LLC | CH-03917 | Kingston | Saugerties |  | 12477 | G | 3005 | Saugerties | TBD |  | 1980 | [13 empty] | CDG | N | (55) SOLECTRIA PVI 36TL | 2016-06-02 | 2016-06-23 | 15 | 2016-06-23 | 2016-06-02 | 2016-06-23 | 15 |  |  |  |  | 32000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Matrix Development LLC | CH-03918 | Kingston | Saugerties |  | 12477 | G | 2016 | Lincoln Park | TBD |  | 2000 | [13 empty] | CDG | N | (55) SOLECTRIA PVI 36TL | 2016-06-02 | 2016-06-23 | 15 | 2016-06-23 | 2016-06-02 | 2016-06-23 | 15 |  |  |  |  | 22500 | [9 empty] | W
Central Hudson |  | Matrix Development LLC | CH-03919 | Kingston | Saugerties |  | 12477 | G | 2016 | Lincoln Park | TBD |  | 2000 | [13 empty] | CDG | N | (55) SOLECTRIA PVI 36TL | 2016-06-02 | 2016-06-23 | 15 | 2016-06-23 | 2016-06-02 | 2016-06-23 | 15 |  |  |  |  | 22500 | [9 empty] | W
Central Hudson |  | New York State Solar Farm | CH-00355 | Kingston | Kingston | Ulster | 12401 | G | 2016 | Lincoln Park | N |  | 8.56 | [13 empty] | NM | N | (36) Sunpower SPR-E20-327 | 2016-04-20 | 2016-04-25 | 3 | 2016-04-25 | [14 empty] | 2016-06-06 | 2016-06-07 |  | Y
Central Hudson |  | Omni Navitas Holdings LLC | CH-04880 | Poughkeepsie | Poughkeepsie |  | 12601 | G | 6092 | Manchester | TBD |  | 1944 | [13 empty] | CDG | N | (54) CHINT POWER CPSSCA36KTL | 2016-05-19 | 2016-06-09 | 14 | 2016-06-09 | 2016-05-19 | 2016-06-09 | 14 |  |  |  |  | 30000 | [9 empty] | W
Central Hudson |  | MC Solar Development, LLC | CH-02610 | Poughkeepsie | Pleasant Valley |  | 12569 | G | 7011 | Hibernia | TBD |  | 1980 | [13 empty] | CDG | N | (66) SMA STP-30000TL-US | 2016-06-21 | 2016-07-13 | 15 | 2016-07-13 | 2016-06-21 | 2016-07-13 | 15 |  |  |  |  | 35000 | [9 empty] | W
Central Hudson |  | MC Solar Development, LLC | CH-02611 | Catskill | Catskill |  | 12414 | G | 2001 | North Catskill | TBD |  | 1980 | [13 empty] | CDG | N | (66) SMA STP-30000TL-US | 2016-06-21 | 2016-07-12 | 14 | 2016-07-12 | 2016-06-21 | 2016-07-12 | 14 |  |  |  |  | 35000 | [9 empty] | W
Central Hudson |  | MC Solar Development, LLC | CH-02612 | Fishkill | Hopewell Junction |  | 12533 | G | 8072 | Shenandoah | TBD |  | 1980 | [13 empty] | CDG | N | (66) SMA STP-30000TL-US | 2016-06-21 | 2016-07-12 | 14 | 2016-07-12 | 2016-06-21 | 2016-07-12 | 14 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | OnForce Solar | CH-02815 | Fishkill | Wappinger |  | 12590 | G | 8056 | North Chelsea | TBD |  | 1980 | [13 empty] | CDG | N | (66) SMA SUNNY TRIPOWER 30000TL-US | 2016-06-03 | 2016-06-24 | 15 | 2016-06-24 | 2016-06-03 | 2016-06-24 | 15 | 2016-07-14 | 2016-07-14 | 2016-10-07 | 60 | 20000 | [9 empty] | W |  | CESIR for 2 projects combined with an aggregate CESIR Cost to Customer of $40,000 & Total Estimated Upgrade Costs of $278,875.
Central Hudson |  | OnForce Solar | CH-02816 | Fishkill | Wappinger |  | 12590 | G | 8056 | North Chelsea | TBD |  | 1980 | [13 empty] | CDG | N | (66) SMA SUNNY TRIPOWER 30000TL-US | 2016-06-03 | 2016-06-24 | 15 | 2016-06-24 | 2016-06-03 | 2016-06-24 | 15 | 2016-07-14 | 2016-07-14 | 2016-10-07 | 60 | 20000 | [9 empty] | W |  | CESIR for 2 projects combined with an aggregate CESIR Cost to Customer of $40,000 & Total Estimated Upgrade Costs of $278,875.
Central Hudson |  | SolarCity | CH-05232 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8091 | Fishkill Plains | N |  | 9 | [13 empty] | NM | N | ABB PVI 6000 ABB PVI 3.0 | 2016-04-20 | 2016-04-22 | 2 | 2016-04-22 | [14 empty] | 2016-06-03 | 2016-06-07 |  | Y
Central Hudson |  | SolarCity | CH-05711 | Kingston | Ellenvl | Ulster | 12428 | G | 3078 | Greenfield Rd | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2016-04-20 | 2016-04-25 | 3 | 2016-04-25 | [14 empty] | 2016-07-15 | 2016-07-15 |  | Y
Central Hudson |  | SolarCity | CH-06367 | Newburgh | Wallkill | Ulster | 12589 | G | 5042 | East Walden | N |  | 11 | [13 empty] | NM | N | ABB PVI 5000 ABB PVI 6000 | 2016-04-20 | 2016-04-29 | 7 | 2016-04-29 | [8 empty] | 350 | 350 |  | 2016-05-18 | 2016-05-18 | 2016-06-02 | 2016-09-30 | 2016-10-03 |  | Y
Central Hudson |  | SolarCity | CH-07663 | Fishkill | Poughkeepsie | Dutchess | 12601 | G | 8022 | Knapps Corners | N |  | 12 | [13 empty] | NM | N | ABB PVI-6000 OUTD-US (2) | 2016-04-20 | 2016-04-21 | 1 | 2016-04-21 | [14 empty] | 2016-05-23 | 2016-05-27 |  | Y
Central Hudson |  | SolarCity | CH-07824 | Newburgh | New Windsor |  | 12553 | G | 4052 | Union Ave | TBD |  | 3 | [13 empty] | NM | N | ABB PVI 3.0 | 2016-04-20 | 2016-04-21 | 1 | 2016-04-21 | [17 empty] | W
Central Hudson |  | SolarCity | CH-07891 | Fishkill | Hopewell Jct |  | 12533 | G | 8096 | Fishkill Plains | TBD |  | 6.6 | [13 empty] | NM | N | ABB PVI-3.0 OUTD-S-US ABB PVI-3.6 OUTD-S-US | 2016-04-20 | 2016-04-22 | 2 | 2016-04-22 | [17 empty] | W
Central Hudson |  | SolarCity | CH-08053 | Poughkeepsie | Poughkeepsie |  | 12603 | G | 6046 | Spackenkill | TBD |  | 456 | [13 empty] | RNM | N | FRONIUS SYMO 24.0 (19) | 2016-06-08 | 2016-06-29 | 15 | 2016-06-29 | 2016-06-08 | 2016-06-29 | 15 | 2016-08-30 | 2016-10-24 | 2017-01-23 | 60 | 21700 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | CEC Development, LLC | CH-03113 | Catskill | Greenville | Greene | 12083 | G | 1091 | Westerlo | N |  | 1975 | [13 empty] | CDG | Y | 15 Chint Power Systems America CPS SCH125KTL-DO/US-600 (600V) [SI1] 1 Chint Power Systems America CPS SCH100KTL-DO/US-600 (600V) | 2016-04-28 | 2016-04-28 | 0 | 2016-04-28 | 2016-04-28 | 2016-05-19 | 15 | 2017-07-14 | 2017-07-14 | 2017-10-09 | 60 | 28926.5 | 488974 | 154609.29 | 2018-01-12 | 2018-06-27 | 2018-06-27 | 2019-11-20 | 2020-01-16 | 2020-01-16 | 2020-04-13 | Y | Y
Central Hudson |  | Direct Energy Solar | CH-01002 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7051 | Rhinebeck | N |  | 6.88 | [13 empty] | NM | N | 32 ENPHASE M215 60-2LL-S22 | 2016-05-02 | 2016-05-02 | 0 | 2016-05-02 | [14 empty] | 2016-07-11 | 2016-07-13 |  | Y
Central Hudson |  | SolarCity | CH-04953 | Catskill | Ravena | Albany | 12143 | G | 1081 | New Baltimore | N |  | 3.6 | [13 empty] | NM | N | ABB PVI-3.6OUTD-S-US | 2016-04-21 | 2016-04-25 | 2 | 2016-04-25 | [14 empty] | 2016-08-24 | 2016-08-25 |  | Y
Central Hudson |  | SolarCity | CH-05424 | Newburgh | New Paltz | Ulster | 12561 | G | 5024 | Ohioville | N |  | 9.6 | [13 empty] | NM | N | ABB PVI-6000-OUTD-US-Z-A ABB PVI-3.6-OUTD-S-US-Z | 2016-04-21 | 2016-04-25 | 2 | 2016-04-25 | [14 empty] | 2016-06-03 | 2016-06-07 |  | Y
Central Hudson |  | SolarCity | CH-05513 | Catskill | Cairo | Greene | 12413 | G | 2041 | South Cairo | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2016-04-21 | 2016-04-25 | 2 | 2016-04-25 | [14 empty] | 2016-07-14 | 2016-07-14 |  | Y
Central Hudson |  | SolarCity | CH-05714 | Kingston | Saugerties | Ulster | 12477 | G | 3003 | Saugerties | N |  | 10 | [13 empty] | NM | N | FRONIUS IG-PLUS 10.0 | 2016-06-06 | 2016-06-16 | 8 | 2016-06-16 | [14 empty] | 2016-07-11 | 2016-07-11 |  | Y
Central Hudson |  | SolarCity | CH-05722 | Kingston | Saugerties | Ulster | 12477 | G | 3002 | Saugerties | N |  | 7.2 | [13 empty] | NM | N | ABB PVI-3.6OUTD-S-US (2) | 2016-04-21 | 2016-04-25 | 2 | 2016-04-25 | [14 empty] | 2016-05-23 | 2016-05-27 |  | Y
Central Hudson |  | SolarCity | CH-06559 | Kingston | Cragsmoor |  | 12420 | G | 3078 | Greenfield Rd | TBD |  | 3 | [13 empty] | NM | N | ABB PVI-3.0 OUTD-S-US | 2016-05-05 | 2016-05-17 | 8 | 2016-05-17 | [17 empty] | W
Central Hudson |  | SolarCity | CH-07636 | Kingston | Kingston | Ulster | 12401 | G | 112 | South Wall St | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000OUTD-US | 2016-04-21 | 2016-04-25 | 2 | 2016-04-25 | [14 empty] | 2016-06-01 | 2016-06-02 |  | Y
Central Hudson |  | Trinity Solar | CH-08508 | Fishkill | Fishkill | Dutchess | 12524 | G | 8094 | Fishkill Plains | N |  | 5 | [13 empty] | NM | N | SOLAREDGE 5000A-US | 2016-04-21 | 2016-04-25 | 2 | 2016-04-25 | [14 empty] | 2016-06-24 | 2016-06-24 |  | Y
Central Hudson |  | Trinity Solar | CH-08557 | Kingston | Saugerties | Ulster | 12477 | G | 3014 | Woodstock | N |  | 3.8 | [13 empty] | NM | N | SOLAR EDGE SE3800A-US | 2016-04-21 | 2016-04-25 | 2 | 2016-04-25 | [14 empty] | 2016-12-09 | 2016-12-09 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08727 | Catskill | Catskill | Greene | 12414 | G | 2004 | North Catskill | N |  | 3.22 | [13 empty] | NM | N | ENPHASE M215602LLS2XZC (15) | 2016-04-21 | 2016-04-25 | 2 | 2016-04-25 | [14 empty] | 2016-09-07 | 2016-09-14 |  | Y
Central Hudson |  | NRG Home Solar | CH-00570 | Fishkill | Wappingrs Fls |  | 12590 | G | 8091 | Fishkill Plains | TBD |  | 10 | [13 empty] | NM | N | SOLAR EDGE SE10000A-US | 2016-04-22 | 2016-04-27 | 3 | 2016-04-27 | [17 empty] | W
Central Hudson |  | Omni Navitas Holdings LLC | CH-04881 | Poughkeepsie | Pleasant Valley |  | 12569 | G | 7024 | Tinkertown | TBD |  | 1944 | [13 empty] | CDG | N | CHINT POWER CPSSCA36KTL (54) | 2016-06-16 | 2016-07-07 | 14 | 2016-07-07 | 2016-06-16 | 2016-07-07 | 14 |  |  |  |  | 35000 | [9 empty] | W
Central Hudson |  | Omni Navitas Holdings LLC | CH-04882 | Poughkeepsie | Pleasant Valley |  | 12569 | G | 6092 | Manchester | TBD |  | 1944 | [13 empty] | CDG | N | CHINT POWER CPSSCA36KTL (54) | 2016-05-19 | 2016-06-09 | 14 | 2016-06-09 | 2016-05-19 | 2016-06-09 | 14 |  |  |  |  | 32000 | [9 empty] | W
Central Hudson |  | Omni Navitas Holdings LLC | CH-04883 | Poughkeepsie | Clinton |  | 13323 | G | 7011 | Hibernia | TBD |  | 1920 | [13 empty] | CDG | N | SUNGROW SG60KU-M (32) | 2016-05-17 | 2016-06-08 | 15 | 2016-06-08 | 2016-05-17 | 2016-06-08 | 15 |  |  |  |  | 35000 | [9 empty] | W
Central Hudson |  | Omni Navitas Holdings LLC | CH-04884 | Catskill | Rensselaerville |  | 12469 | G | 1092 | Westerlo | TBD |  | 1944 | [13 empty] | CDG | N | CHINT POWER CPSSCA36KTL (54) | 2016-06-17 | 2016-07-08 | 14 | 2016-07-08 | 2016-06-17 | 2016-07-08 | 14 |  |  |  |  | 35000 | [9 empty] | W
Central Hudson |  | Omni Navitas Holdings LLC | CH-04885 | Newburgh | Walden |  | 12586 | G | 5041 | East Walden | TBD |  | 1944 | [13 empty] | CDG | N | CHINT POWER CPSSCA36KTL (54) | 2016-05-19 | 2016-06-09 | 14 | 2016-06-09 | 2016-05-19 | 2016-06-09 | 14 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Omni Navitas Holdings LLC | CH-04886 | Poughkeepsie | Pleasant Valley |  | 12569 | G | 7024 | Tinkertown | TBD |  | 1944 | [13 empty] | CDG | N | CHINT POWER CPSSCA36KTL (54) | 2016-05-19 | 2016-06-09 | 14 | 2016-06-09 | 2016-05-19 | 2016-06-09 | 14 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | SolarCity | CH-06341 | Newburgh | Wallkill | Ulster | 12589 | G | 5033 | Galeville | N |  | 5 | [13 empty] | NM | N | ABB PVI-5000 OUTD-US | 2016-04-22 | 2016-04-25 | 1 | 2016-04-25 | [14 empty] | 2016-05-18 | 2016-05-25 |  | Y
Central Hudson |  | SolarCity | CH-06811 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8044 | Myers Corners | N |  | 10.2 | [13 empty] | NM | N | ABB PVI 6000 ABB PVI 4.2 | 2016-04-22 | 2016-04-26 | 2 | 2016-04-26 | [14 empty] | 2016-07-28 | 2016-07-28 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08814 | Newburgh | New Paltz |  | 12561 | G | 5023 | Ohioville | TBD |  | 7.95 | [13 empty] | NM | N | ENPHASE M215 602LLS2XZC (37) | 2016-04-22 | 2016-04-25 | 1 | 2016-04-25 | [17 empty] | W
Central Hudson |  | NRG Home Solar | CH-00486 | Newburgh | Wallkill | Ulster | 12589 | G | 5013 | Modena | N |  | 4.08 | [13 empty] | NM | N | ENPHASE M215 (19) | 2016-04-25 | 2016-04-27 | 2 | 2016-04-27 | [14 empty] | 2016-09-09 | 2016-09-15 |  | Y
Central Hudson |  | Hudson Solar | CH-01367 | Newburgh | Gardiner | Ulster | 12525 | G | 5031 | Galeville | N |  | 10 | [13 empty] | NM | N | SOLAREDGE SE-10000 A-US-U | 2016-05-06 | 2016-05-06 | 0 | 2016-05-06 | [14 empty] | 2016-06-21 | 2016-06-28 |  | Y
Central Hudson |  | Hudson Solar | CH-01456 | Newburgh | Gardiner | Ulster | 12525 | G | 5031 | Galeville | N |  | 10 | [13 empty] | NM | N | SOLAREDGE SE-10000 A-US-U | 2016-05-06 | 2016-05-06 | 0 | 2016-05-06 | [14 empty] | 2016-06-21 | 2016-06-27 |  | Y
Central Hudson |  | Hudson Solar | CH-01667 | Kingston | Stone Ridge | Ulster | 12484 | G | 3023 | High Falls | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE-5000A-US-U | 2016-04-25 | 2016-04-25 | 0 | 2016-04-25 | [14 empty] | 2016-07-14 | 2016-07-14 |  | Y
Central Hudson |  | Hudson Solar | CH-01832 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7056 | Rhinebeck | N |  | 10 | [13 empty] | NM | N | SOLAREDGE SE-10000 A-US-U | 2016-05-05 | 2016-05-05 | 0 | 2016-05-05 | [8 empty] | 350 | 350 |  | 2016-06-06 | 2016-06-06 | 2016-06-21 | 2016-06-21 | 2016-06-29 |  | Y
Central Hudson |  | Hudson Solar | CH-02304 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8051 | North Chelsea | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE-7600 A-US-U | 2016-04-25 | 2016-04-27 | 2 | 2016-04-27 | [14 empty] | 2016-07-29 | 2016-08-01 |  | Y
Central Hudson |  | Hudson Solar | CH-02376 | Fishkill | Cold Spg | Putnam | 10516 | G | 8086 | Tioronda | N |  | 3.8 | [13 empty] | NM | N | SOLAREDGE SE-3800 A-US-U | 2016-04-25 | 2016-04-28 | 3 | 2016-04-28 | [14 empty] | 2016-07-15 | 2016-07-15 |  | Y
Central Hudson |  | Hudson Solar | CH-02459 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6092 | Manchester | N | CH-02115 | 3 | [13 empty] | NM | N | SMA AMERICA SB-3000 HFUS-30 | 2016-05-05 | 2016-05-05 | 0 | 2016-05-05 | [14 empty] | 2016-08-05 | 2016-08-05 |  | Y
Central Hudson |  | OE SOLAR 8, LLC | CH-02797 | Poughkeepsie | Rhinebeck |  | 12572 | G | 7054 | Rhinebeck | TBD |  | 2000 | [13 empty] | CDG | N | SOLECTRIA SGI 500XTM (4) | 2016-05-05 | 2016-05-17 | 8 | 2016-05-17 | 2016-05-05 | 2016-05-26 | 15 |  |  |  |  | 35000 | [9 empty] | W
Central Hudson |  | OE SOLAR 8, LLC | CH-02798 | Poughkeepsie | Rhinebeck |  | 12572 | G | 7054 | Rhinebeck | TBD |  | 2000 | [13 empty] | CDG | N | SOLECTRIA SGI 500XTM (4) | 2016-05-05 | 2016-05-17 | 8 | 2016-05-17 | 2016-05-05 | 2016-05-26 | 15 |  |  |  |  | 35000 | [9 empty] | W
Central Hudson |  | SolarCity | CH-07466 | Newburgh | Wallkill | Ulster | 12589 | G | 5011 | Modena | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2016-04-25 | 2016-04-27 | 2 | 2016-04-27 | [14 empty] | 2016-07-18 | 2016-07-18 |  | Y
Central Hudson |  | New York State Solar Farm | CH-00409 | Newburgh | Newburgh | Orange | 12550 | G | 4015 | West Balmville | N |  | 4.48 | [13 empty] | NM | N | SUNPOWER X22-360 C-AC (14) | 2016-05-04 | 2016-05-04 | 0 | 2016-05-04 | [14 empty] | 2016-06-03 | 2016-06-10 |  | Y
Central Hudson |  | RER Energy Group, LLC. | CH-04900 | Catskill |  |  | 12051 | G | 1074 | Coxsackie | TBD |  | 600 | [13 empty] | RNM | N | SUNGROW SG60KU-M (10) | 2016-06-09 | 2016-06-30 | 15 | 2016-06-30 | 2016-06-09 | 2016-06-30 | 15 | 2017-05-22 | 2017-06-29 | 2017-09-25 | 60 | 18971.02 | 494796 | [7 empty] | 2018-05-24 | W
Central Hudson |  | Murphy Solar Power | CH-02763 | Kingston | Ellenvl | Ulster | 12428 | G | 3078 | Greenfield Rd | N |  | 5 | [13 empty] | NM | N | SMA 5000TL-22 | 2016-04-26 | 2016-04-28 | 2 | 2016-04-28 | [14 empty] | 2016-06-15 | 2016-06-20 |  | Y
Central Hudson |  | OnForce Solar | CH-02817 | Fishkill |  |  | 12601 | G | 8024 | Knapps Corners | TBD |  | 1980 | [13 empty] | CDG | N | SUNNY TRIPOWER 30000 (66) | 2016-05-25 | 2016-06-16 | 15 | 2016-06-16 | 2016-05-25 | 2016-06-16 | 15 |  |  |  |  | 32000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | OnForce Solar | CH-02818 | Fishkill |  |  | 12601 | G | 8024 | Knapps Corners | TBD |  | 1980 | [13 empty] | CDG | N | SMA SUNNY TRIPOWER 30000 (66) | 2016-05-25 | 2016-06-16 | 15 | 2016-06-16 | 2016-05-25 | 2016-06-16 | 15 |  |  |  |  | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | SolarCity | CH-06167 | Newburgh | New Paltz | Ulster | 12561 | G | 5024 | Ohioville | N |  | 12 | [13 empty] | NM | N | ABB PVI-6000 OUTD-US (2) | 2016-05-10 | 2016-05-10 | 0 | 2016-05-10 | [8 empty] | 350 | 350 |  | 2016-05-26 | 2016-05-26 | 2016-06-16 | 2016-06-16 | 2016-06-20 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08796 | Newburgh | Highland |  | 12528 | G | 5022 | Ohioville | TBD |  | 10.96 | [13 empty] | NM | N | ENPHASE M215 602LLS2XZC (51) | 2016-04-26 | 2016-04-26 | 0 | 2016-04-26 | [17 empty] | W
Central Hudson |  | Lighthouse Solar | CH-00306 | Poughkeepsie | Salt Pt | Dutchess | 12578 | G | 7011 | Hibernia | N |  | 11.4 | [13 empty] | NM | N | SOLAREDGE SE11400 A-US | 2016-05-05 | 2016-05-05 | 0 | 2016-05-05 | [14 empty] | 2016-08-01 | 2016-08-01 |  | Y
Central Hudson |  | Hudson Solar | CH-02528 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7054 | Rhinebeck | N |  | 1725 | [13 empty] | CDG | Y | 13 Chint Power Systems America CPS SCH125KTL-DO/US-600 (600V) 1 Chint Power Systems America CPS SC100KT-O/xx-480 (480V) (52) SOLAREDGE SE33.3K US | 2016-06-07 | 2016-06-28 | 15 | 2016-06-28 | 2016-06-07 | 2016-06-28 | 15 | 2017-07-17 | 2017-07-14 | 2017-10-05 | 58 | 14462.15 | 316928 | 137478.4 | 2018-01-05 | 2019-06-28 | 2019-06-28 | 2019-12-20 | 2019-12-30 | 2019-12-31 | 2020-04-28 | Y | Y | 5/10/18 - Developer submitted a Moratorium Attestation Form ending 8/23/18, full payment due 2/15/19. 12/18/18 - Moratorium extended ending 3/4/19, full payment due 8/22/19.
Central Hudson |  | SolarCity | CH-06958 | Newburgh | New Paltz | Ulster | 12561 | G | 5031 | Galeville | N |  | 6 | [13 empty] | NM | N | ABB PVI 3.0 (2) | 2016-04-27 | 2016-04-29 | 2 | 2016-04-29 | [14 empty] | 2016-06-22 | 2016-06-28 |  | Y
Central Hudson |  | SolarCity | CH-07514 | Kingston | Saugerties | Ulster | 12477 | G | 2015 | Lincoln Park | N |  | 11 | [13 empty] | NM | N | ABB PVI6000 ABB PVI5000 | 2016-05-09 | 2016-05-23 | 10 | 2016-05-23 | [14 empty] | 2016-08-03 | 2016-08-05 |  | Y
Central Hudson |  | SolarCity | CH-07831 | Newburgh | Modena |  | 12548 | G | 5012 | Modena | TBD |  | 3.6 | [13 empty] | NM | N | ABB PVI-3.6 OUTD-S-US | 2016-07-13 | 2016-07-22 | 7 | 2016-07-22 | [14 empty] | 2016-08-11 | 2016-08-11 |  | W
Central Hudson |  | Green Street Power Partners, LLC | CH-03367 | Poughkeepsie | Millbrook |  | 12545 | G | 7012 | Hibernia | TBD |  | 480 | [13 empty] | RNM | N | SMA STP-30000TL-US (16) | 2016-09-27 | 2016-10-13 | 12 | 2016-10-13 | 2016-09-27 | 2016-10-13 | 12 |  |  |  |  | 35000 | [9 empty] | W
Central Hudson |  | SolarCity | CH-06119 | Fishkill | Hopewell Junction | Dutchess | 12533 | G | 8093 | Fishkill Plains | N |  | 15.8 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 FRONIUS PRIMO 8.2 | 2016-05-05 | 2016-05-05 | 0 | 2016-05-05 | [14 empty] | 2016-08-04 | 2016-08-05 |  | Y
Central Hudson |  | SolarCity | CH-06427 | Newburgh | Maybrook | Orange | 12543 | G | 4026 | Coldenham | N |  | 3.6 | [13 empty] | NM | N | ABB PVI-3.6 OUTD-S-US | 2016-05-04 | 2016-05-04 | 0 | 2016-05-04 | [14 empty] | 2016-08-31 | 2016-08-31 |  | Y
Central Hudson |  | SolarCity | CH-07618 | Newburgh | Campbell Hall | Orange | 10916 | G | 5051 | Maybrook | N |  | 9.6 | [13 empty] | NM | N | ABB PVI 6000 ABB PVI 3.6 | 2016-05-04 | 2016-05-04 | 0 | 2016-05-04 | [14 empty] | 2016-06-20 | 2016-06-21 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08662 | Kingston | Kerhonkson | Ulster | 12446 | G | 3081 | Kerhonkson | N |  | 5.37 | [13 empty] | NM | N | ENPHASE M215602LLS2XZC (25) | 2016-04-29 | 2016-04-29 | 0 | 2016-04-29 | [14 empty] | 2016-08-01 | 2016-08-02 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00993 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6045 | Spackenkill | N |  | 8.17 | [13 empty] | NM | N | 38 ENPHASE M215 60 | 2016-05-12 | 2016-05-12 | 0 | 2016-05-12 | [14 empty] | 2016-06-24 | 2016-07-01 |  | Y
Central Hudson |  | Direct Energy Solar | CH-01006 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7061 | Milan | N |  | 6.67 | [13 empty] | NM | N | 31 ENPHASE M215 60 | 2016-05-13 | 2016-05-13 | 0 | 2016-05-13 | [14 empty] | 2016-06-30 | 2016-07-08 |  | Y
Central Hudson |  | SolarCity | CH-05856 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 6074 | East Park | N | CH-05856 | 3.6 | [13 empty] | NM | N | ABB PVI-3.6 OUTD-S-US | 2016-05-12 | 2016-05-12 | 0 | 2016-05-12 | [14 empty] | 2016-09-08 | 2016-09-14 |  | Y
Central Hudson |  | SolarCity | CH-06069 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8094 | Fishkill Plains | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000 OUTD-US | 2016-05-16 | 2016-05-27 | 9 | 2016-05-27 | [14 empty] | 2016-06-01 | 2016-06-03 |  | Y
Central Hudson |  | SolarCity | CH-07085 | Newburgh | Wallkill | Ulster | 12589 | G | 5043 | East Walden | N |  | 15.2 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 (2) | 2016-05-12 | 2016-05-12 | 0 | 2016-05-12 | [14 empty] | 2016-07-14 | 2016-07-26 |  | Y
Central Hudson |  | SolarCity | CH-07396 | Fishkill | Beacon | Dutchess | 12508 | G | 8085 | Tioronda | N |  | 3.6 | [13 empty] | NM | N | ABB PVI-3.6 OUTD-S-US | 2016-05-10 | 2016-05-10 | 0 | 2016-05-10 | [14 empty] | 2016-07-28 | 2016-07-28 |  | Y
Central Hudson |  | Sunrun Inc. | CH-08323 | Newburgh | Newburgh | Orange | 12550 | G | 5001 | Marlboro | N |  | 7.6 | [13 empty] | NM | N | ABB UNO-7.6-TL-OUTD-S-US | 2016-05-13 | 2016-05-25 | 8 | 2016-05-25 | [14 empty] | 2016-06-21 | 2016-06-27 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08642 | Catskill | Catskill | Greene | 12414 | G | 2005 | North Catskill | N |  | 4.73 | [13 empty] | NM | N | ENPHASE M215602LLS2XZC (22) | 2016-05-13 | 2016-05-13 | 0 | 2016-05-13 | [14 empty] | 2017-01-19 | 2017-01-25 |  | Y
Central Hudson |  | American Solar Partners | CH-03078 | Catskill | Greenvl | Greene | 12083 | G | 2061 | Freehold | N |  | 3.8 | [13 empty] | NM | N | SOLAR EDGE SE3800 | 2016-05-18 | 2016-05-31 | 8 | 2016-05-31 | [14 empty] | 2016-09-21 | 2016-09-26 |  | Y
Central Hudson |  | New York State Solar Farm | CH-04004 | Newburgh | Newburgh | Orange | 12550 | G | 4011 | West Balmville | N |  | 3.8 | [13 empty] | NM | N | SMA AMERICA SB3800TL | 2016-05-02 | 2016-05-16 | 10 | 2016-05-16 | [14 empty] | 2016-06-16 | 2016-06-17 |  | Y
Central Hudson |  | NRG Home Solar | CH-00482 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6004 | Reynolds Hill | N |  | 2.8 | [13 empty] | NM | N | 13 ENPHASE M215 | 2016-05-12 | 2016-05-12 | 0 | 2016-05-12 | [14 empty] | 2016-09-01 | 2016-09-09 |  | Y
Central Hudson |  | Monolith Solar Associates LLC | CH-02646 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8065 | Merritt Park | N |  | 10 | [13 empty] | NM | N | SOLAREDGE SE5000A-US (2) | 2016-05-12 | 2016-05-12 | 0 | 2016-05-12 | [14 empty] | 2016-06-29 | 2016-07-05 |  | Y
Central Hudson |  | SolarCity | CH-05389 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8065 | Merritt Park | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE 7600A | 2016-05-12 | 2016-05-12 | 0 | 2016-05-12 | [14 empty] | 2016-07-07 | 2016-07-13 |  | Y
Central Hudson |  | SolarCity | CH-05447 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6092 | Manchester | N |  | 12 | [13 empty] | NM | N | 2 ABB PVI 6.0 | 2016-05-13 | 2016-05-13 | 0 | 2016-05-13 | [14 empty] | 2016-06-22 | 2016-06-29 |  | Y
Central Hudson |  | SolarCity | CH-05923 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6052 | Todd Hill | N |  | 3 | [13 empty] | NM | N | ABB PVI 3.0 | 2016-05-13 | 2016-05-13 | 0 | 2016-05-13 | [14 empty] | 2016-08-10 | 2016-08-15 |  | Y
Central Hudson |  | SolarCity | CH-06075 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8092 | Fishkill Plains | N |  | 3.6 | [13 empty] | NM | N | ABB PVI 3.6 | 2016-05-12 | 2016-05-12 | 0 | 2016-05-12 | [14 empty] | 2016-06-22 | 2016-06-28 |  | Y
Central Hudson |  | SolarCity | CH-06959 | Newburgh | New Paltz | Ulster | 12561 | G | 5031 | Galeville | N |  | 3.6 | [13 empty] | NM | N | ABB PVI-3.6 OUTD-S-US | 2016-05-12 | 2016-05-12 | 0 | 2016-05-12 | [14 empty] | 2016-06-22 | 2016-06-28 |  | Y
Central Hudson |  | SolarCity | CH-06971 | Newburgh | Newburgh | Orange | 12550 | G | 4013 | West Balmville | N |  | 15.8 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 FRONIUS PRIMO 8.2 | 2016-05-12 | 2016-05-12 | 0 | 2016-05-12 | [14 empty] | 2016-09-22 | 2016-09-26 |  | Y
Central Hudson |  | SolarCity | CH-07919 | Newburgh |  |  | 12549 | G | 5054 | Maybrook | TBD |  | 6 | [13 empty] | NM | N | ABB PVI 6000 | 2016-05-02 | 2016-05-16 | 10 | 2016-05-16 | [17 empty] | W
Central Hudson |  | Infinity Solar Systems | CH-00155 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8056 | North Chelsea | N |  | 8.32 | [13 empty] | NM | N | SUNPOWER SPR-E20-327 C-AC (26) | 2016-05-16 | 2016-05-27 | 9 | 2016-05-27 | [14 empty] | 2016-06-30 | 2016-07-08 |  | Y
Central Hudson |  | NRG Home Solar | CH-00479 | Catskill | Hannacroix | Greene | 12087 | G | 1083 | New Baltimore | N |  | 4.73 | [13 empty] | NM | N | ENPHASE M215 (22) | 2016-05-03 | 2016-05-16 | 9 | 2016-05-16 | [14 empty] | 2016-10-14 | 2016-10-14 |  | Y
Central Hudson |  | NRG Home Solar | CH-00509 | Poughkeepsie | Stanfordvl | Dutchess | 12581 | G | 7072 | Stanfordville | N |  | 3.01 | [13 empty] | NM | N | 14 Enphase M215 | 2016-05-03 | 2016-05-16 | 9 | 2016-05-16 | [14 empty] | 2016-08-31 | 2016-08-31 |  | Y
Central Hudson |  | Novel Approaches | CH-02794 | Kingston | Wawarsing | Ulster | 12489 | G | 3071 | Honk Falls | N | CH-02790 | 7 | [13 empty] | NM | N | SOLAR EDGE SE 11.4 SOLAR EDGE SE6000 SOLAR EDGE SE 7.6 | 2016-05-18 | 2016-05-31 | 8 | 2016-05-31 | [8 empty] | 350 | 350 |  |  |  |  | 2016-06-06 | 2016-06-08 |  | Y
Central Hudson |  | Paradise Energy Solutions LLC | CH-02830 | Catskill | Lanesvl | Greene | 12450 | E | 2387 | NYSEG | N | CH-02830 | 6 | [13 empty] | NM | N | SMA SB6.0-US | 2016-06-01 | 2016-06-15 | 10 | 2016-06-15 | [14 empty] | 2016-08-24 | 2016-08-25 |  | Y
Central Hudson |  | PosiGen Solar | CH-02864 | Catskill | Elka Pk | Greene | 12427 | G | 2385 | Lawrenceville | N |  | 8.39 | [13 empty] | NM | N | ENPHASE M215-60-2LL-S22-IG (39) | 2016-05-03 | 2016-05-16 | 9 | 2016-05-16 | [14 empty] | 2016-06-24 | 2016-07-01 |  | Y
Central Hudson |  | Ross Solar Group | CH-02991 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8093 | Fishkill Plains | N |  | 15.2 | [13 empty] | NM | N | SOLAREDGE SE7600-US (2) | 2016-05-16 | 2016-05-27 | 9 | 2016-05-27 | [14 empty] | 2016-07-21 | 2016-07-21 |  | Y
Central Hudson |  | SolarCity | CH-05387 | Newburgh | Highland | Ulster | 12528 | G | 5083 | Highland | N |  | 12 | [13 empty] | NM | N | ABB PVI 6000 ABB PVI 6000 | 2016-06-03 | 2016-06-17 | 10 | 2016-06-17 | [14 empty] | 2016-10-10 | 2016-10-13 |  | Y
Central Hudson |  | SolarCity | CH-05966 | Poughkeepsie | Ancram | Columbia | 12502 | G | 7085 | Ancram | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2016-05-03 | 2016-05-16 | 9 | 2016-05-16 | [14 empty] | 2016-05-23 | 2016-05-27 |  | Y
Central Hudson |  | SolarCity | CH-07699 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6042 | Spackenkill | N |  | 3.8 | [13 empty] | NM | N | SOLAREDGE SE3800A | 2016-05-03 | 2016-05-16 | 9 | 2016-05-16 | [14 empty] | 2016-08-29 | 2016-09-08 |  | Y
Central Hudson |  | SolarCity | CH-07752 | Catskill | Catskill | Greene | 12414 | G | 2003 | North Catskill | N |  | 10 | [13 empty] | NM | N | ABB PVI 5000 (2) | 2016-05-16 | 2016-05-16 | 0 | 2016-05-16 | [14 empty] | 2016-08-25 | 2016-08-26 |  | Y
Central Hudson |  | SolarCity | CH-07893 | Fishkill |  |  | 12524 | G | 8055 | North Chelsea | TBD |  | 11 | [13 empty] | NM | N | ABB PVI 6000 ABB PVI 5000 | 2016-05-03 | 2016-05-16 | 9 | 2016-05-16 | [17 empty] | W
Central Hudson |  | Trinity Solar | CH-08583 | Fishkill | Beacon | Dutchess | 12508 | G | 8017 | Forgebrook | N |  | 5 | [13 empty] | NM | N | SOLAREDGE 5000A-US | 2016-05-03 | 2016-05-16 | 9 | 2016-05-16 | [14 empty] | 2016-07-07 | 2016-07-21 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08700 | Fishkill |  |  | 12590 | G | 8056 | North Chelsea | TBD |  | 6.45 | [13 empty] | NM | N | ENPHASE M215 602LLS2XZC (30) | 2016-05-16 | 2016-05-27 | 9 | 2016-05-27 | [17 empty] | W
Central Hudson |  | Infinity Solar Systems | CH-00157 | Fishkill | Beacon | Dutchess | 12508 | G | 8085 | Tioronda | N |  | 6.4 | [13 empty] | NM | N | SUNPOWER SPR-E20-327 (20) | 2016-05-04 | 2016-05-17 | 9 | 2016-05-17 | [14 empty] | 2016-09-30 | 2016-10-06 |  | Y
Central Hudson |  | Lighthouse Solar | CH-00314 | Newburgh | Gardiner | Ulster | 12525 | G | 5031 | Galeville | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE 7600 A-US | 2016-05-17 | 2016-05-27 | 8 | 2016-05-27 | [14 empty] | 2016-06-01 | 2016-06-01 |  | Y
Central Hudson |  | New York State Solar Farm | CH-00392 | Poughkeepsie | Millbrook | Dutchess | 12545 | G | 6057 | Todd Hill | N |  | 11 | [13 empty] | NM | N | SMA AMERICA SB5000 SMA AMERICA SB6000 | 2016-05-04 | 2016-05-17 | 9 | 2016-05-17 | [14 empty] | 2016-07-12 | 2016-07-13 |  | Y
Central Hudson |  | PosiGen Solar | CH-02896 | Newburgh | Highland | Ulster | 12528 | G | 5082 | Highland | N |  | 3.87 | [13 empty] | NM | N | 18 ENPHASE M215-60-2LL-S22-IG | 2016-05-04 | 2016-05-17 | 9 | 2016-05-17 | [14 empty] | 2016-06-20 | 2016-06-27 |  | Y
Central Hudson |  | Pure Point Energy LLC | CH-02942 | Poughkeepsie | Staatsburg | Dutchess | 12580 | G | 7011 | Hibernia | N | CH-02942 | 10.8 | [13 empty] | NM | N | SMA SUNNYBOY 7700TL-US SMA SUNNYBOY 3800TL-US | 2016-05-04 | 2016-05-17 | 9 | 2016-05-17 | [14 empty] | 2016-12-13 | 2016-12-13 |  | Y
Central Hudson |  | SolarCity | CH-05425 | Newburgh |  |  | 12586 | G | 5041 | East Walden | TBD |  | 6 | [13 empty] | NM | N | ABB PVI 6000 | 2016-05-04 | 2016-05-16 | 8 | 2016-05-16 | [17 empty] | W
Central Hudson |  | SolarCity | CH-06042 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8046 | Myers Corners | N |  | 8 | [13 empty] | NM | N | ABB PVI 5000 ABB PVI 3.0 | 2016-05-04 | 2016-05-17 | 9 | 2016-05-17 | [14 empty] | 2016-07-14 | 2016-07-15 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06922 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8055 | North Chelsea | N |  | 15.8 | [13 empty] | NM | N | FRONIUS PRIMO 8.2 FRONIUS PRIMO 7.6 | 2016-05-04 | 2016-05-17 | 9 | 2016-05-17 | [14 empty] | 2016-08-24 | 2016-09-01 |  | Y
Central Hudson |  | SolarCity | CH-07661 | Fishkill | Poughkeepsie | Dutchess | 12603 | G | 8024 | Knapps Corners | N |  | 3.6 | [13 empty] | NM | N | ABB PVI 3.6 | 2016-05-04 | 2016-05-17 | 9 | 2016-05-17 | [14 empty] | 2016-06-22 | 2016-06-28 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08625 | Kingston |  |  | 12401 | G | 1021 | East Kingston | TBD |  | 5.16 | [13 empty] | NM | N | ENPHASE M215602LLS2XZC (24) | 2016-05-04 | 2016-05-18 | 10 | 2016-05-18 | [17 empty] | W
Central Hudson |  | SELF | CH-08893 | Newburgh | New Paltz | Ulster | 12561 | G | 5023 | Ohioville | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE7600A-US | 2016-05-04 | 2016-05-16 | 8 | 2016-05-16 | [14 empty] | 2017-12-13 | 2017-12-14 |  | Y
Central Hudson |  | Sol Providers | CH-08970 | Poughkeepsie | Clinton Corners | Dutchess | 12514 | G | 7013 | Hibernia | N | CH-08923 | 15.36 | [13 empty] | NM | N | 48 SUNPOWER E20 327 | 2016-05-04 | 2016-05-17 | 9 | 2016-05-17 | [14 empty] | 2016-06-30 | 2016-07-06 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-00075 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6062 | Inwood Ave | N |  | 6 | [13 empty] | NM | N | SOLAREDGE 6000AUS | 2016-05-05 | 2016-05-19 | 10 | 2016-05-19 | [14 empty] | 2016-06-08 | 2016-06-15 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-00175 | Fishkill | Stormvl | Dutchess | 12582 | G | 8093 | Fishkill Plains | N |  | 9.6 | [13 empty] | NM | N | SUNPOWER SPR-E20-327 C-AC (30) | 2016-05-05 | 2016-07-06 | 42 | 2016-07-06 | [14 empty] | 2016-09-14 | 2016-09-15 |  | Y
Central Hudson |  | Kasselman Solar | CH-00239 | Catskill | W Coxsackie | Greene | 12192 | G | 1071 | Coxsackie | N | CH-00239 | 5 | [13 empty] | NM | N | ENPHASE ENERGY M250 (20) | 2016-05-05 | 2016-05-27 | 16 | 2016-05-27 | [14 empty] | 2016-09-06 | 2016-09-06 |  | Y
Central Hudson |  | Lighthouse Solar | CH-00301 | Kingston | Cottekill | Ulster | 12419 | G | 3021 | High Falls | N |  | 6 | [13 empty] | NM | N | SOLAREDGE 6000 A-US | 2016-05-05 | 2016-05-19 | 10 | 2016-05-19 | [14 empty] | 2016-08-02 | 2016-08-03 |  | Y
Central Hudson |  | NRG Home Solar | CH-00478 | Poughkeepsie | Verbank |  | 12585 | G | 6057 | Todd Hill | TBD |  | 10 | [13 empty] | NM | N | SOLAR EDGE SE10000A-US | 2016-05-05 | 2016-05-19 | 10 | 2016-05-19 | [17 empty] | W
Central Hudson |  | Burke Electric and Solar | CH-00761 | Fishkill | Cold Spg | Putnam | 10516 | G | 8063 | Merritt Park | N |  | 10 | [13 empty] | NM | N | SOLAR EDGE SE10000A US | 2016-06-02 | 2016-06-15 | 9 | 2016-06-15 | [14 empty] | 2016-06-24 | 2016-06-27 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00940 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7054 | Rhinebeck | N |  | 6.02 | [13 empty] | NM | N | 28 ENPHASE M215 60-2LL-S22 | 2016-05-05 | 2016-05-19 | 10 | 2016-05-19 | [14 empty] | 2016-08-08 | 2016-08-10 |  | Y
Central Hudson |  | SolarCity | CH-05900 | Poughkeepsie | Clinton Corners | Dutchess | 12514 | G | 7013 | Hibernia | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2016-05-05 | 2016-05-19 | 10 | 2016-05-19 | [14 empty] | 2016-06-22 | 2016-06-29 |  | Y
Central Hudson |  | SolarCity | CH-06018 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8043 | Myers Corners | N |  | 6 | [13 empty] | NM | N | ABB PVI 6000 | 2016-05-05 | 2016-05-19 | 10 | 2016-05-19 | [14 empty] | 2016-07-28 | 2016-07-28 |  | Y
Central Hudson |  | SolarCity | CH-06302 | Newburgh | Newburgh | Orange | 12550 | G | 4015 | West Balmville | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE 7600A | 2016-05-05 | 2016-05-19 | 10 | 2016-05-19 | [14 empty] | 2016-06-23 | 2016-06-29 |  | Y
Central Hudson |  | SolarCity | CH-06468 | Catskill | W Coxsackie | Greene | 12192 | G | 1076 | Coxsackie | N |  | 7.2 | [13 empty] | NM | N | ABB PVI 3.6 (2) | 2016-05-05 | 2016-05-17 | 8 | 2016-05-17 | [14 empty] | 2016-06-01 | 2016-06-02 |  | Y
Central Hudson |  | SolarCity | CH-06749 | Poughkeepsie | Arlington | Dutchess | 12603 | G | 6092 | Manchester | N |  | 6 | [13 empty] | NM | N | ABB PVI 6000 | 2016-05-05 | 2016-05-19 | 10 | 2016-05-19 | [14 empty] | 2016-07-14 | 2016-07-14 |  | Y
Central Hudson |  | SolarCity | CH-07097 | Newburgh | Wallkill | Ulster | 12589 | G | 5013 | Modena | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE 7600A | 2016-05-05 | 2016-05-19 | 10 | 2016-05-19 | [14 empty] | 2016-08-04 | 2016-08-05 |  | Y
Central Hudson |  | Socore Energy | CH-08900 | Poughkeepsie |  |  | 12540 | G | 6055 | Todd Hill | TBD |  | 1980 | [13 empty] | RNM | N | (55) CHINT POWER INVERTER SCA36KTL-DO_US | 2016-06-24 | 2016-07-11 | 10 | 2016-07-11 | 2016-07-11 | 2016-07-29 | 14 | 2016-08-30 | 2016-10-20 | 2017-01-19 | 60 | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | Socore Energy | CH-08901 | Poughkeepsie |  |  | 12603 | G | 6092 | Manchester | TBD |  | 1476 | [13 empty] | RNM | N | (41) CHINT POWER INVERTER SCA36KTL-DO_US | 2016-06-24 | 2016-07-11 | 10 | 2016-07-11 | 2016-07-11 | 2016-07-29 | 14 | 2016-08-30 | 2016-10-20 | 2017-01-19 | 60 | 35000 | [9 empty] | W |  | 3/9/17 - Property Owner Consent not received; project withdrawn.
Central Hudson |  | NRG Home Solar | CH-00553 | Fishkill | Beacon | Dutchess | 12508 | G | 8017 | Forgebrook | N |  | 3.87 | [13 empty] | NM | N | ENPHASE M215 (18) | 2016-05-06 | 2016-05-20 | 10 | 2016-05-20 | [14 empty] | 2016-09-29 | 2016-10-03 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08783 | Kingston |  |  | 12401 | G | 2017 | Lincoln Park | TBD |  | 4.51 | [13 empty] | NM | N | ENPHASE M215 602LLS2XZC (21) | 2016-05-06 | 2016-05-20 | 10 | 2016-05-20 | [17 empty] | W
Central Hudson |  | Direct Energy Solar | CH-00848 | Poughkeepsie | Stanfordvl | Dutchess | 12581 | G | 7072 | Stanfordville | N |  | 12.9 | [13 empty] | NM | N | ENPHASE M215 (60) | 2016-06-16 | 2016-07-11 | 16 | 2016-07-11 | [14 empty] | 2016-09-15 | 2016-09-20 |  | Y
Central Hudson |  | SolarCity | CH-04995 | Kingston | Kingston | Ulster | 12401 | G | 1024 | East Kingston | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2016-05-09 | 2016-05-23 | 10 | 2016-05-23 | [14 empty] | 2016-06-20 | 2016-06-24 |  | Y
Central Hudson |  | SolarCity | CH-05078 | Newburgh | Milton | Ulster | 12547 | G | 5003 | Marlboro | N |  | 6 | [13 empty] | NM | N | ABB PVI-3.0 OUTD-S-US (2) | 2016-05-09 | 2016-05-23 | 10 | 2016-05-23 | [14 empty] | 2016-08-15 | 2016-08-18 |  | Y
Central Hudson |  | SolarCity | CH-05457 | Newburgh | Wallkill | Ulster | 12589 | G | 5041 | East Walden | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE 6000A | 2016-05-09 | 2016-05-23 | 10 | 2016-05-23 | [14 empty] | 2016-06-28 | 2016-07-07 |  | Y
Central Hudson |  | SolarCity | CH-06315 | Newburgh | Newburgh | Orange | 12550 | G | 5004 | Marlboro | N |  | 9 | [13 empty] | NM | N | ABB PVI-6000 OUTD-US ABB PVI-3.0 OUTD-S-US | 2016-05-09 | 2016-05-23 | 10 | 2016-05-23 | [14 empty] | 2016-05-27 | 2016-06-01 |  | Y
Central Hudson |  | SolarCity | CH-07172 | Newburgh | New Windsor | Orange | 12553 | G | 4094 | Bethlehem Rd | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2016-05-09 | 2016-05-23 | 10 | 2016-05-23 | [14 empty] | 2016-07-14 | 2016-07-15 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08739 | Kingston | West Shokan | Ulster | 12494 | G | 3011 | Woodstock | N | CH-08739 | 5.59 | [13 empty] | NM | N | ENPHASE M215 (26) | 2016-05-09 | 2016-05-23 | 10 | 2016-05-23 | [14 empty] | 2016-08-08 | 2016-08-10 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08832 | Kingston |  |  | 12401 | G | 2017 | Lincoln Park | TBD |  | 4.73 | [13 empty] | NM | N | ENPHASE M215 (22) | 2016-05-09 | 2016-05-23 | 10 | 2016-05-23 | [17 empty] | W
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08841 | Newburgh | New Paltz |  | 12561 | G | 5024 | Ohioville | TBD |  | 5.16 | [13 empty] | NM | N | ENPHASE M215602LLS2XZC (24) | 2016-05-11 | 2016-05-25 | 10 | 2016-05-25 | [17 empty] | W
Central Hudson |  | Sun Mountain | CH-09108 | Newburgh | New Paltz | Ulster | 12561 | G | 5031 | Galeville | N |  | 12 | [13 empty] | NM | N | SMA SB6000TL-US-22 (2) | 2016-05-19 | 2016-05-27 | 6 | 2016-05-27 | [14 empty] | 2016-07-19 | 2016-07-26 |  | Y
Central Hudson |  | SunDog Solar | CH-09167 | Kingston | Kingston | Ulster | 12401 | G | 2094 | Hurley Ave | N | CH-05012 | 5.6 | [13 empty] | NM | N | ENPHASE ENERGY S280-60-LL-5-US (20) | 2016-08-01 | 2016-08-15 | 10 | 2016-08-15 | [14 empty] | 2016-09-09 | 2016-09-13 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Sunrise Solar Solutions, LLC | CH-09651 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8072 | Shenandoah | N |  | 6.72 | [13 empty] | NM | N | (24) ENPHASE S280 | 2016-06-10 | 2016-06-20 | 6 | 2016-06-20 | [14 empty] | 2016-08-23 | 2016-08-24 |  | Y
Central Hudson |  | Green Street Power Partners, LLC | CH-00109 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7013 | Hibernia | N |  | 7.7 | [13 empty] | NM | N | SMA SB7700TL-US | 2016-05-25 | 2016-06-09 | 10 | 2016-06-09 | [14 empty] | 2016-09-21 | 2016-09-22 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00926 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6046 | Spackenkill | N |  | 4.73 | [13 empty] | NM | N | ENPHASE M215 60-2LL-S22 (22) | 2016-06-06 | 2016-06-20 | 10 | 2016-06-20 | [14 empty] | 2016-07-22 | 2016-07-25 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00941 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7054 | Rhinebeck | N |  | 7.74 | [13 empty] | NM | N | ENPHASE M215 60-2LL-S22 (36) | 2016-05-25 | 2016-06-09 | 10 | 2016-06-09 | [14 empty] | 2016-08-12 | 2016-08-16 |  | Y
Central Hudson |  | Direct Energy Solar | CH-01055 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6042 | Spackenkill | N |  | 4.73 | [13 empty] | NM | N | ENPHASE M215 60-2LL-S22 (22) | 2016-06-13 | 2016-06-27 | 10 | 2016-06-27 | [14 empty] | 2016-09-12 | 2016-09-14 |  | Y
Central Hudson |  | SolarCity | CH-06819 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8054 | North Chelsea | N |  | 3 | [13 empty] | NM | N | ABB PVI 3.0 | 2016-05-10 | 2016-05-24 | 10 | 2016-05-24 | [14 empty] | 2016-08-24 | 2016-08-25 |  | Y
Central Hudson |  | Sunrun Inc. | CH-08334 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 3.75 | [13 empty] | NM | N | ENPHASE ENERGY M250-60-2LL-S2X (15) | 2016-06-15 | 2016-06-15 | 0 | 2016-06-15 | [14 empty] | 2016-07-28 | 2016-07-28 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-00176 | Fishkill | Stormvl | Dutchess | 12582 | G | 8093 | Fishkill Plains | N |  | 11.2 | [13 empty] | NM | N | SUNPOWER SPR-E20-327 (35) | 2016-05-25 | 2016-06-07 | 8 | 2016-06-07 | [14 empty] | 2016-07-28 | 2016-08-01 |  | Y
Central Hudson |  | SolarCity | CH-06306 | Newburgh | Marlboro | Ulster | 12542 | G | 5004 | Marlboro | N |  | 12 | [13 empty] | NM | N | ABB PVI 6000 (2) | 2016-05-11 | 2016-05-25 | 10 | 2016-05-25 | [14 empty] | 2016-06-22 | 2016-06-28 |  | Y
Central Hudson |  | SolarCity | CH-06437 | Catskill | Palenvl | Greene | 12463 | G | 2001 | North Catskill | N |  | 3 | [13 empty] | NM | N | ABB PVI-3.0OUTD-S-US | 2016-07-28 | 2016-07-29 | 1 | 2016-07-29 | [14 empty] | 2016-08-02 | 2016-08-03 |  | Y
Central Hudson |  | SolarCity | CH-06661 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6068 | Inwood Ave | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2016-05-11 | 2016-05-25 | 10 | 2016-05-25 | [14 empty] | 2016-05-27 | 2016-06-03 |  | Y
Central Hudson |  | SolarCity | CH-07888 | Newburgh |  |  | 12525 | G | 5083 | Highland | TBD |  | 5 | [13 empty] | NM | N | ABB PVI-5000 OUTD-US | 2016-05-11 | 2016-05-25 | 10 | 2016-05-25 | [17 empty] | W
Central Hudson |  | Infinity Solar Systems | CH-00221 | Newburgh | Wallkill | Ulster | 12589 | G | 5041 | East Walden | N |  | 7 | [13 empty] | NM | N | SMA AMERICA SB7000TL-US-22 | 2016-07-28 | 2016-07-28 | 0 | 2016-07-28 | [14 empty] | 2016-08-09 | 2016-08-10 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Lighthouse Solar | CH-00325 | Kingston | Kingston | Ulster | 12401 | G | 1021 | East Kingston | N |  | 6 | [13 empty] | NM | N | SOLAREDGE 6000A-US | 2016-05-12 | 2016-05-25 | 9 | 2016-05-25 | [14 empty] | 2016-08-17 | 2016-08-19 |  | Y
Central Hudson |  | New York State Solar Farm | CH-00372 | Kingston | Hurley | Ulster | 12443 | G | 2094 | Hurley Ave | N |  | 6 | [13 empty] | NM | N | SMA AMERICA SB6000 | 2016-05-12 | 2016-05-25 | 9 | 2016-05-25 | [14 empty] | 2016-08-10 | 2016-08-18 |  | Y
Central Hudson |  | New York State Solar Farm | CH-04079 | Newburgh | Wallkill | Ulster | 12589 | G | 5043 | East Walden | N |  | 11 | [13 empty] | NM | N | SMA AMERICA 5000 SB TL SMA AMERICA 6000 SB TL | 2016-05-25 | 2016-06-07 | 8 | 2016-06-07 | [14 empty] | 2016-07-27 | 2016-07-27 |  | Y
Central Hudson |  | NRG Home Solar | CH-00566 | Kingston |  |  | 12401 | G | 2016 | Lincoln Park | TBD |  | 4.73 | [13 empty] | NM | N | ENPHASE M215 (22) | 2016-05-12 | 2016-05-25 | 9 | 2016-05-25 | [17 empty] | W
Central Hudson |  | PosiGen Solar | CH-02859 | Newburgh | Milton | Ulster | 12547 | G | 5083 | Highland | N | CH-02859 | 3.87 | [13 empty] | NM | N | ENPHASE M215-60-2LL-S22-IG (18) | 2016-05-12 | 2016-05-25 | 9 | 2016-05-25 | [14 empty] | 2016-09-23 | 2016-09-28 |  | Y
Central Hudson |  | SolarCity | CH-07545 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6051 | Todd Hill | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000-OUTD-US | 2016-05-12 | 2016-05-26 | 10 | 2016-05-26 | [14 empty] | 2016-12-06 | 2016-12-06 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08751 | Poughkeepsie | Staatsburg | Dutchess | 12580 | G | 7041 | Staatsburg | N |  | 7.95 | [13 empty] | NM | N | 37 ENPHASE M215 602LLS2XZC | 2016-05-12 | 2016-05-26 | 10 | 2016-05-26 | [14 empty] | 2017-01-17 | 2017-01-18 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08755 | Newburgh | Highland | Ulster | 12528 | G | 5082 | Highland | N |  | 5.18 | [13 empty] | NM | N | 24 ENPHASE M215 602LLS2XZC | 2016-05-12 | 2016-05-26 | 10 | 2016-05-26 | [14 empty] | 2016-12-15 | 2016-12-16 |  | Y
Central Hudson |  | Empire Solar Store | CH-01100 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 7024 | Tinkertown | N |  | 7.6 | [13 empty] | NM | N | Fronius 7.6 | 2016-05-13 | 2016-05-26 | 9 | 2016-05-26 | [14 empty] | 2016-06-20 | 2016-06-27 |  | Y
Central Hudson |  | SolarCity | CH-06181 | Newburgh | Clintondale | Ulster | 12515 | G | 5012 | Modena | N |  | 6.6 | [13 empty] | NM | N | ABB PVI 3.0 ABB PVI 3.6 | 2016-08-19 | 2016-08-19 | 0 | 2016-08-19 | [14 empty] | 2016-08-22 | 2016-08-30 |  | Y
Central Hudson |  | Sunrun Inc. | CH-08344 | Newburgh | Newburgh | Orange | 12550 | G | 4023 | Coldenham | N |  | 3 | [13 empty] | NM | N | ABB PVI-3.0-OUTD-S-US-A | 2016-05-26 | 2016-06-07 | 7 | 2016-06-07 | [14 empty] | 2016-07-27 | 2016-08-05 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08711 | Fishkill | Putnam Valley | Putnam | 10524 | G | 8066 | Merritt Park | N |  | 5.8 | [13 empty] | NM | N | ENPHASE M215 602LLS2XZC (27) | 2016-05-31 | 2016-05-31 | 0 | 2016-05-31 | [14 empty] | 2016-11-22 | 2016-11-22 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-00128 | Newburgh | Modena | Ulster | 12548 | G | 5013 | Modena | N |  | 9.6 | [13 empty] | NM | N | SUNPOWER SPR-E20-327 C-AC (30) | 2016-05-16 | 2016-05-26 | 8 | 2016-05-26 | [14 empty] | 2016-08-10 | 2016-08-15 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00953 | Fishkill | Fishkill | Dutchess | 12524 | G | 8094 | Fishkill Plains | N |  | 10.75 | [13 empty] | NM | N | ENPHASE M215 60 (50) | 2016-05-31 | 2016-06-14 | 10 | 2016-06-14 | [14 empty] | 2016-07-12 | 2016-07-19 |  | Y
Central Hudson |  | Hudson Solar | CH-02084 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 7041 | Staatsburg | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE-7600 A-US-U | 2016-06-06 | 2016-06-20 | 10 | 2016-06-20 | [14 empty] | 2016-09-08 | 2016-09-22 |  | Y
Central Hudson |  | Hudson Solar | CH-02095 | Poughkeepsie | Millbrook | Dutchess | 12545 | G | 6057 | Todd Hill | N |  | 9.6 | [13 empty] | NM | N | 30 SUNPOWER SPR-X21-345 C-AC | 2016-05-16 | 2016-05-27 | 9 | 2016-05-27 | [8 empty] | 350 | 350 |  | 2016-06-27 | 2016-06-27 | 2016-07-22 | 2016-06-14 | 2016-08-03 |  | Y
Central Hudson |  | Hudson Solar | CH-02364 | Kingston | Port Ewen | Ulster | 12466 | G | 1012 | Boulevard | N |  | 10 | [13 empty] | NM | N | SOLAREDGE SE-10000 A-US-U | 2016-06-06 | 2016-06-17 | 9 | 2016-06-17 | [14 empty] | 2016-06-17 | 2016-06-21 |  | Y
Central Hudson |  | Hudson Solar | CH-02375 | Fishkill | Beacon | Dutchess | 12508 | G | 8087 | Tioronda | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE-5000 A-US-U | 2016-06-06 | 2016-06-16 | 8 | 2016-06-16 | [14 empty] | 2016-08-17 | 2016-08-22 |  | Y
Central Hudson |  | Hudson Solar | CH-02380 | Newburgh | New Paltz | Ulster | 12561 | G | 5023 | Ohioville | N |  | 10 | [13 empty] | NM | N | SOLAREDGE SE-10000 A-US-U | 2016-06-13 | 2016-06-21 | 6 | 2016-06-21 | [14 empty] | 2016-06-21 | 2016-06-27 |  | Y
Central Hudson |  | Hudson Solar | CH-02387 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7054 | Rhinebeck | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE-6000 A-US-U | 2016-07-15 | 2016-07-18 | 1 | 2016-07-18 | [14 empty] | 2016-07-20 | 2016-07-20 |  | Y
Central Hudson |  | Hudson Solar | CH-02388 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8095 | Fishkill Plains | N |  | 11.4 | [13 empty] | NM | N | SOLAREDGE SE-11400 A-US-U | 2016-06-06 | 2016-06-16 | 8 | 2016-06-16 | [14 empty] | 2016-08-22 | 2016-08-22 |  | Y
Central Hudson |  | Hudson Solar | CH-02501 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8095 | Fishkill Plains | N | CH-02169 | 6 | [13 empty] | NM | N | SMA AMERICA SB-6.0 -1SP-US-40 | 2016-06-06 | 2016-06-16 | 8 | 2016-06-16 | [14 empty] | 2016-06-16 | 2016-06-22 |  | Y
Central Hudson |  | Murphy Solar Power | CH-02728 | Catskill | Catskill | Greene | 12414 | G | 2005 | North Catskill | N |  | 11 | [13 empty] | NM | N | SMA 11000TL-US | 2016-06-03 | 2016-06-16 | 9 | 2016-06-16 | [14 empty] | 2016-07-07 | 2016-07-07 |  | Y
Central Hudson |  | SolarCity | CH-05409 | Newburgh | Montgomery | Orange | 12549 | G | 5054 | Maybrook | N |  | 12 | [13 empty] | NM | N | ABB PVI-6000 OUTD-US (2) | 2016-05-31 | 2016-06-14 | 10 | 2016-06-14 | [14 empty] | 2016-06-23 | 2016-06-30 |  | Y
Central Hudson |  | Sunrun Inc. | CH-08355 | Newburgh | Newburgh | Orange | 12550 | G | 4014 | West Balmville | N |  | 3.75 | [13 empty] | NM | N | ENPHASE ENERGY M250-60-2LL-S2X (15) | 2016-05-16 | 2016-05-27 | 9 | 2016-05-27 | [14 empty] | 2016-09-07 | 2016-09-19 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08676 | Poughkeepsie |  |  | 12580 | G | 7041 | Staatsburg | TBD |  | 8.6 | [13 empty] | NM | N | 40 ENPHASE M215 602LLS2XZC | 2016-05-16 | 2016-05-27 | 9 | 2016-05-27 | [17 empty] | W
Central Hudson |  | Empire Solar Solutions | CH-00082 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7062 | Milan | N |  | 6 | [13 empty] | NM | N | Fronius 6.0 | 2016-05-17 | 2016-06-01 | 10 | 2016-06-01 | [14 empty] | 2016-07-08 | 2016-07-11 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-00200 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6092 | Manchester | N |  | 9 | [13 empty] | NM | N | SMA AMERICA SB6000TL-US-22 SMA AMERICA SB3000TL-US-22 | 2016-05-17 | 2016-06-01 | 10 | 2016-06-01 | [14 empty] | 2016-06-03 | 2016-06-09 |  | Y
Central Hudson |  | New York State Solar Farm | CH-00352 | Kingston | Napanoch | Ulster | 12458 | G | 3091 | Neversink | N |  | 48 | [13 empty] | RNM | N | SMA AMERICA 6000 SB-TL (8) | 2016-05-31 | 2016-06-14 | 10 | 2016-06-14 | [8 empty] | 2678 | 2055.74 |  | 2016-07-14 | 2016-07-14 | 2016-08-05 | 2016-09-23 | 2016-09-23 |  | Y
Central Hudson |  | SolarCity | CH-06476 | Catskill | Ravena | Albany | 12143 | G | 1081 | New Baltimore | N |  | 12 | [13 empty] | NM | N | ABB PVI-6000OUTD-US (2) | 2016-05-17 | 2016-05-31 | 9 | 2016-05-31 | [14 empty] | 2016-06-30 | 2016-07-01 |  | Y
Central Hudson |  | SolarCity | CH-06647 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6046 | Spackenkill | N |  | 9.6 | [13 empty] | NM | N | ABB PVI 6000 ABB PVI 3.6 | 2016-05-17 | 2016-06-01 | 10 | 2016-06-01 | [14 empty] | 2016-07-07 | 2016-07-14 |  | Y
Central Hudson |  | SolarCity | CH-06850 | Fishkill | Hopewell Junction | Dutchess | 12533 | G | 8096 | Fishkill Plains | N |  | 8 | [13 empty] | NM | N | ABB PVI-5000 OUTD-US ABB PVI-3.0 OUTD-S-US | 2016-05-17 | 2016-05-27 | 8 | 2016-05-27 | [14 empty] | 2016-07-14 | 2016-07-15 |  | Y
Central Hudson |  | SolarCity | CH-07305 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6055 | Todd Hill | N |  | 8.2 | [13 empty] | NM | N | FRONIUS PRIMO 8.2 | 2016-05-17 | 2016-06-01 | 10 | 2016-06-01 | [14 empty] | 2016-06-22 | 2016-06-29 |  | Y
Central Hudson |  | SolarCity | CH-07536 | Poughkeepsie | Salt Pt | Dutchess | 12578 | G | 7011 | Hibernia | N |  | 7.6 | [13 empty] | NM | N | Fronius Primo 7.6 | 2016-05-17 | 2016-06-01 | 10 | 2016-06-01 | [14 empty] | 2016-06-22 | 2016-07-07 |  | Y
Central Hudson |  | SolarCity | CH-07877 | Poughkeepsie |  |  | 12580 | G | 7041 | Staatsburg | TBD |  | 8.4 | [13 empty] | NM | N | 2 ABB PVI-4.2 OUTD-S-US | 2016-05-17 | 2016-05-31 | 9 | 2016-05-31 | [17 empty] | W
Central Hudson |  | Solar Generation | CH-08255 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7054 | Rhinebeck | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE 7600A US | 2016-06-10 | 2016-06-24 | 10 | 2016-06-24 | [14 empty] | 2016-09-06 | 2016-09-08 |  | Y
Central Hudson |  | Solar Generation | CH-08256 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7053 | Rhinebeck | N |  | 10 | [13 empty] | NM | N | SOLAREDGE 10000A US | 2016-05-17 | 2016-06-01 | 10 | 2016-06-01 | [14 empty] | 2016-10-04 | 2016-10-04 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08705 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8071 | Shenandoah | N |  | 6.24 | [13 empty] | NM | N | ENPHASE M215 602LLS2XZC (29) | 2016-05-17 | 2016-05-27 | 8 | 2016-05-27 | [14 empty] | 2016-09-29 | 2016-10-03 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08720 | Newburgh | Newburgh | Orange | 12550 | G | 4011 | West Balmville | N |  | 7.955 | [13 empty] | NM | N | ENPHASE M215 602LLS2XZC (37) | 2016-05-31 | 2016-06-14 | 10 | 2016-06-14 | [14 empty] | 2016-11-23 | 2016-11-28 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08721 | Newburgh | Newburgh | Orange | 12550 | G | 4012 | West Balmville | N |  | 8.17 | [13 empty] | NM | N | ENPHASE M215 602LLS2XZC (38) | 2016-05-17 | 2016-05-31 | 9 | 2016-05-31 | [14 empty] | 2016-12-02 | 2016-12-02 |  | Y
Central Hudson |  | Sol Providers | CH-08915 | Poughkeepsie | Pine Plns | Dutchess | 12567 | G | 7091 | Pulvers Corners | N |  | 13.44 | [13 empty] | NM | N | 56 SUNPOWER SPR E20-327 | 2016-05-17 | 2016-06-01 | 10 | 2016-06-01 | [14 empty] | 2016-08-15 | 2016-08-31 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-00057 | Newburgh | Newburgh | Orange | 12550 | G | 4014 | West Balmville | N |  | 7.6 | [13 empty] | NM | N | FRONIUS 7.6 | 2016-05-18 | 2016-05-31 | 8 | 2016-05-31 | [14 empty] | 2016-06-21 | 2016-06-27 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-00209 | Newburgh | Newburgh | Orange | 12550 | G | 4014 | West Balmville | N |  | 5.76 | [13 empty] | NM | N | SUNPOWER SPR-E20-327 C-AC (18) | 2016-06-01 | 2016-06-14 | 9 | 2016-06-14 | [14 empty] | 2016-08-30 | 2016-09-06 |  | Y
Central Hudson |  | New York State Solar Farm | CH-03953 | Newburgh | Modena | Ulster | 12548 | G | 5011 | Modena | N |  | 8 | [13 empty] | NM | N | SUNPOWER SPR-E20 327-C-AC (25) | 2016-05-18 | 2016-06-02 | 10 | 2016-06-02 | [8 empty] | 350 | 350 |  | 2016-06-20 | 2016-06-20 | 2016-07-13 | 2016-07-13 | 2016-07-15 |  | Y
Central Hudson |  | SolarCity | CH-05955 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7054 | Rhinebeck | N |  | 8.2 | [13 empty] | NM | N | FRONIUS PRIMO 8.2 | 2016-05-18 | 2016-06-02 | 10 | 2016-06-02 | [14 empty] | 2016-08-24 | 2016-08-31 |  | Y
Central Hudson |  | SolarCity | CH-06114 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8072 | Shenandoah | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000 OUTD-US | 2016-06-07 | 2016-06-17 | 8 | 2016-06-17 | [14 empty] | 2016-08-08 | 2016-08-10 |  | Y
Central Hudson |  | SolarCity | CH-06713 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 6057 | Todd Hill | N |  | 6.6 | [13 empty] | NM | N | DELTA SOLIVIA 6.6 | 2016-05-18 | 2016-06-02 | 10 | 2016-06-02 | [14 empty] | 2017-01-09 | 2017-01-09 |  | Y
Central Hudson |  | SolarCity | CH-06731 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 7025 | Tinkertown | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2016-05-18 | 2016-06-02 | 10 | 2016-06-02 | [14 empty] | 2016-07-14 | 2016-07-14 |  | Y
Central Hudson |  | Trinity Solar | CH-08534 | Poughkeepsie |  |  | 12603 | G | 6011 | Sand Dock | TBD |  | 6 | [13 empty] | NM | N | SOLAREDGE 6000A-US | 2016-05-18 | 2016-06-03 | 11 | 2016-06-03 | [17 empty] | W
Central Hudson |  | Infinity Solar Systems | CH-00198 | Newburgh | Montgomery | Orange | 12549 | G | 5073 | Montgomery | N |  | 7.04 | [13 empty] | NM | N | SUNPOWER SPR-E20-327 C-AC (22) | 2016-05-31 | 2016-06-14 | 10 | 2016-06-14 | [14 empty] | 2016-08-10 | 2016-08-15 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-00211 | Newburgh | Cornwall | Orange | 12518 | G | 4041 | Union Ave | N |  | 12.8 | [13 empty] | NM | N | SUNPOWER SPR-E20-327 C-AC (40) | 2016-05-19 | 2016-06-03 | 10 | 2016-06-03 | [14 empty] | 2016-07-19 | 2016-07-20 |  | Y
Central Hudson |  | NRG Home Solar | CH-00510 | Fishkill |  |  | 12533 | G | 8091 | Fishkill Plains | TBD |  | 4.08 | [13 empty] | NM | N | ENPHASE M215 (19) | 2016-05-19 | 2016-05-31 | 7 | 2016-05-31 | [17 empty] | W
Central Hudson |  | NRG Home Solar | CH-00536 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8056 | North Chelsea | N |  | 5.25 | [13 empty] | NM | N | ENPHASE M250 (21) | 2016-05-19 | 2016-05-31 | 7 | 2016-05-31 | [14 empty] | 2016-08-10 | 2016-08-15 |  | Y
Central Hudson |  | Monolith Solar Associates LLC | CH-02682 | Catskill | Coxsackie | Greene | 12051 | G | 1074 | Coxsackie | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE7600A-US | 2016-07-11 | 2016-07-11 | 0 | 2016-07-11 | [14 empty] | 2016-08-12 | 2016-08-22 |  | Y
Central Hudson |  | SolarCity | CH-05189 | Kingston | Bearsvl | Ulster | 12409 | G | 3012 | Woodstock | N |  | 3.6 | [13 empty] | NM | N | ABB PVI-3.6OUTD-S-US | 2016-05-19 | 2016-05-31 | 7 | 2016-05-31 | [14 empty] | 2016-09-14 | 2016-09-15 |  | Y
Central Hudson |  | SolarCity | CH-05303 | Newburgh | Newburgh | Orange | 12550 | G | 4011 | West Balmville | N |  | 9 | [13 empty] | NM | N | ABB PVI 3.0 ABB PVI 6000 | 2016-05-19 | 2016-05-27 | 6 | 2016-05-27 | [14 empty] | 2016-07-14 | 2016-07-15 |  | Y
Central Hudson |  | SolarCity | CH-06424 | Newburgh | Maybrook | Orange | 12543 | G | 4026 | Coldenham | N |  | 8.2 | [13 empty] | NM | N | Fronius Primo 8.2 | 2016-05-19 | 2016-05-27 | 6 | 2016-05-27 | [14 empty] | 2016-06-20 | 2016-06-21 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-00079 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 7024 | Tinkertown | N |  | 7.6 | [13 empty] | NM | N | SOLAR EDGE 7600A-US | 2016-05-20 | 2016-06-06 | 10 | 2016-06-06 | [14 empty] | 2016-09-14 | 2016-10-05 |  | Y
Central Hudson |  | Apex Solar Power | CH-00695 | Fishkill | Beacon | Dutchess | 12508 | G | 8087 | Tioronda | N |  | 10 | [13 empty] | NM | N | SOLAREDGE SE10000A-US | 2016-05-20 | 2016-06-02 | 8 | 2016-06-02 | [8 empty] | 350 | 350 |  | 2016-06-15 | 2016-06-15 | 2016-07-22 | 2016-07-28 | 2016-07-28 |  | Y
Central Hudson |  | Direct Energy Solar | CH-01013 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8071 | Shenandoah | N |  | 5.16 | [13 empty] | NM | N | ENPHASE ENERGY M215-60-2LL-S22 (24) | 2016-06-01 | 2016-06-14 | 9 | 2016-06-14 | [14 empty] | 2016-10-07 | 2016-10-10 |  | Y
Central Hudson |  | SolarCity | CH-05667 | Kingston | Kingston | Ulster | 12401 | G | 1024 | East Kingston | N |  | 6 | [13 empty] | NM | N | ABB PVI 6000 | 2016-08-11 | 2016-08-22 | 7 | 2016-08-22 | [14 empty] | 2016-08-24 | 2016-08-25 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06746 | Poughkeepsie |  |  | 12603 | G | 6092 | Manchester | TBD |  | 8.2 | [13 empty] | NM | N | FRONIUS PRIMO 8.2 | 2016-05-20 | 2016-06-06 | 10 | 2016-06-06 | [17 empty] | W
Central Hudson |  | SolarCity | CH-07589 | Newburgh | New Paltz | Ulster | 12561 | G | 5024 | Ohioville | N |  | 9.6 | [13 empty] | NM | N | ABB PVI 3.6 ABB PVI 6000 | 2016-05-20 | 2016-05-31 | 6 | 2016-05-31 | [14 empty] | 2016-08-15 | 2016-08-18 |  | Y
Central Hudson |  | Green Street Power Partners, LLC | CH-00117 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8094 | Fishkill Plains | N |  | 10 | [13 empty] | NM | N | SMA SB5000TL-US-22 (2) | 2016-05-23 | 2016-06-02 | 7 | 2016-06-02 | [14 empty] | 2016-09-16 | 2016-09-22 |  | Y
Central Hudson |  | New York State Solar Farm | CH-00429 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6092 | Manchester | N |  | 10.24 | [13 empty] | NM | N | 32 SUNPOWER SPR-E20 327-C-AC | 2016-05-23 | 2016-06-07 | 10 | 2016-06-07 | [14 empty] | 2016-07-14 | 2016-07-22 |  | Y
Central Hudson |  | SolarCity | CH-05665 | Kingston | Kingston | Ulster | 12401 | G | 1024 | East Kingston | N |  | 16 | [13 empty] | NM | N | SOLAREDGE SE6000A SOLAREDGE SE10000A | 2016-05-23 | 2016-06-06 | 9 | 2016-06-06 | [8 empty] | 350 | 350 |  | 2016-07-07 | 2016-07-07 | 2016-07-25 | 2016-07-28 | 2016-08-03 |  | Y
Central Hudson |  | SolarCity | CH-06856 | Fishkill | Hopewell Junction | Dutchess | 12533 | G | 8092 | Fishkill Plains | N |  | 6 | [13 empty] | NM | N | ABB PVI 3.0 (2) | 2016-05-23 | 2016-06-02 | 7 | 2016-06-02 | [14 empty] | 2016-06-20 | 2016-06-21 |  | Y
Central Hudson |  | SolarCity | CH-06938 | Fishkill | Beacon | Dutchess | 12508 | G | 8085 | Tioronda | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2016-05-23 | 2016-06-01 | 6 | 2016-06-01 | [14 empty] | 2016-06-23 | 2016-06-29 |  | Y
Central Hudson |  | SolarCity | CH-07875 | Poughkeepsie |  |  | 12538 | G | 6075 | East Park | TBD |  | 5 | [13 empty] | NM | N | ABB PVI-5000 OUTD-US | 2016-05-23 | 2016-05-27 | 4 | 2016-05-27 | [17 empty] | W
Central Hudson |  | Trinity Solar | CH-08575 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE 7600A-US | 2016-05-23 | 2016-06-03 | 8 | 2016-06-03 | [14 empty] | 2016-08-17 | 2016-08-19 |  | Y
Central Hudson |  | Hudson Solar | CH-02529 | Poughkeepsie | Rhinebeck |  | 12572 | G | 7054 | Rhinebeck | N |  | 166.5 | [13 empty] | CDG | N | SOLAREDGE SE33.3KUS (5) | 2016-06-13 | 2016-06-20 | 5 | 2016-06-20 | [17 empty] | W
Central Hudson |  | SolarCity | CH-07000 | Newburgh |  |  | 12550 | G | 4015 | West Balmville | TBD |  | 6 | [13 empty] | NM | N | ABB PVI-6000OUTD-US | 2016-05-24 | 2016-06-03 | 7 | 2016-06-03 | [17 empty] | W
Central Hudson |  | Solar Generation | CH-08078 | Kingston | Kerhonkson | Ulster | 12446 | G | 3082 | Kerhonkson | N |  | 6 | [13 empty] | NM | N | SMA SB 6000 | 2016-07-29 | 2016-07-29 | 0 | 2016-07-29 | [14 empty] | 2016-08-02 | 2016-08-04 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Infinity Solar Systems | CH-00145 | Newburgh | Marlboro | Ulster | 12542 | G | 5004 | Marlboro | N |  | 13.8 | [13 empty] | NM | N | SMA AMERICA SB5000TL-US (2) SMA AMERICA SB3800TL-US-22 | 2016-05-25 | 2016-06-07 | 8 | 2016-06-07 | [14 empty] | 2016-07-25 | 2016-07-28 |  | Y
Central Hudson |  | New York State Solar Farm | CH-00368 | Newburgh | New Paltz | Ulster | 12561 | G | 5021 | Ohioville | N |  | 8 | [13 empty] | NM | N | SMA AMERICA SB3000 SMA AMERICA SB5000 | 2016-05-25 | 2016-06-03 | 6 | 2016-06-03 | [14 empty] | 2016-08-01 | 2016-08-01 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00907 | Kingston | Claryvl | Sullivan | 12725 | G | 3091 | Neversink | N |  | 5.59 | [13 empty] | NM | N | ENPHASE M215 60-2LL-S22 (26) | 2016-06-17 | 2016-07-01 | 10 | 2016-07-01 | [14 empty] | 2016-07-22 | 2016-07-27 |  | Y
Central Hudson |  | SolarCity | CH-05181 | Newburgh | New Windsor | Orange | 12553 | G | 4097 | Bethlehem Rd | N | CH-05181 | 5 | [13 empty] | NM | N | ABB PVI-5000OUTD-US | 2016-05-25 | 2016-06-06 | 7 | 2016-06-06 | [14 empty] | 2016-06-28 | 2016-07-08 |  | Y
Central Hudson |  | SolarCity | CH-05443 | Newburgh | Modena | Ulster | 12548 | G | 5012 | Modena | N |  | 3.6 | [13 empty] | NM | N | ABB PVI-3.6OUTD-S-US | 2016-05-25 | 2016-06-06 | 7 | 2016-06-06 | [14 empty] | 2016-07-21 | 2016-07-26 |  | Y
Central Hudson |  | SolarCity | CH-06332 | Newburgh | Marlboro | Ulster | 12542 | G | 5004 | Marlboro | N |  | 7.2 | [13 empty] | NM | N | ABB PVI-3.0OUTD-S-US ABB PVI-4.2OUTD-S-US | 2016-06-13 | 2016-06-21 | 6 | 2016-06-21 | [14 empty] | 2016-09-02 | 2016-09-06 |  | Y
Central Hudson |  | SolarCity | CH-06525 | Kingston | Kingston | Ulster | 12401 | G | 1022 | East Kingston | N |  | 3 | [13 empty] | NM | N | ABB PVI-3.0 OUTD-S-US | 2016-06-13 | 2016-09-26 | 73 | 2016-09-26 | [14 empty] | 2016-09-28 | 2016-10-03 |  | Y
Central Hudson |  | SolarCity | CH-06698 | Poughkeepsie | Lagrangevl | Dutchess | 12540 | G | 6057 | Todd Hill | N |  | 12.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 ABB PVI-5000OUTD-US | 2016-05-25 | 2016-06-09 | 10 | 2016-06-09 | [14 empty] | 2016-08-08 | 2016-08-10 |  | Y
Central Hudson |  | SolarCity | CH-07352 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8043 | Myers Corners | N |  | 6.6 | [13 empty] | NM | N | ABB PVI-3.0 OUTD-S-US ABB PVI-3.6 OUTD-S-US | 2016-08-05 | 2016-08-17 | 8 | 2016-08-17 | [14 empty] | 2016-08-19 | 2016-08-22 |  | Y
Central Hudson |  | SolarCity | CH-07614 | Newburgh | Cornwall | Orange | 12518 | G | 4041 | Union Ave | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2016-05-25 | 2016-06-06 | 7 | 2016-06-06 | [14 empty] | 2016-07-28 | 2016-07-28 |  | Y
Central Hudson |  | SolarCity | CH-07741 | Fishkill | Hopewell Junction | Dutchess | 12533 | G | 8096 | Fishkill Plains | N |  | 5 | [13 empty] | NM | N | ABB PVI-5000OUTD-US | 2016-06-23 | 2016-07-06 | 8 | 2016-07-06 | [14 empty] | 2016-07-07 | 2016-07-11 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08637 | Catskill |  |  | 12414 | G | 2004 | North Catskill | TBD |  | 2.58 | [13 empty] | NM | N | ENPHASE M215 602LLS2XZC (12) | 2016-05-25 | 2016-06-02 | 5 | 2016-06-02 | [17 empty] | W
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08790 | Poughkeepsie |  |  | 12572 | G | 7042 | Staatsburg | TBD |  | 7.74 | [13 empty] | NM | N | 36 ENPHASE M215 602LLS2XZC | 2016-05-25 | 2016-06-09 | 10 | 2016-06-09 | [17 empty] | W
Central Hudson |  | Solar Alchemy | CH-08983 | Kingston | Bearsvl | Ulster | 12409 | G | 3012 | Woodstock | N | CH-08983 | 6 | [13 empty] | NM | N | ENPHASE M250 60-2LL-S2X (24) | 2016-06-03 | 2016-06-16 | 9 | 2016-06-16 | [14 empty] | 2016-08-19 | 2016-08-22 |  | Y
Central Hudson |  | Solar Alchemy | CH-09002 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7042 | Staatsburg | N | CH-09002 | 6 | [13 empty] | NM | N | 25 ENPHASE M250 60-2LL-S2X | 2016-05-25 | 2016-06-09 | 10 | 2016-06-09 | [14 empty] | 2016-08-19 | 2016-08-26 |  | Y
Central Hudson |  | Sungevity Inc | CH-09511 | Newburgh | New Windsor | Orange | 12553 | G | 4095 | Bethlehem Rd | N |  | 6.8 | [13 empty] | NM | N | ABB PVI-3.0-OUTD-S-US-A ABB PVI-3.8-OUTD-S-US-A | 2016-06-07 | 2016-06-17 | 8 | 2016-06-17 | [14 empty] | 2016-06-20 | 2016-06-24 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-00173 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8023 | Knapps Corners | N |  | 7.04 | [13 empty] | NM | N | SUNPOWER SPR-E20-327 (22) | 2016-06-07 | 2016-06-17 | 8 | 2016-06-17 | [14 empty] | 2016-10-12 | 2016-10-14 |  | Y
Central Hudson |  | SolarCity | CH-05768 | Kingston | Saugerties | Ulster | 12477 | G | 1021 | East Kingston | N |  | 12 | [13 empty] | NM | N | ABB PVI-6000OUTD-US (2) | 2016-05-26 | 2016-06-07 | 7 | 2016-06-07 | [8 empty] | 350 | 350 |  | 2016-07-13 | 2016-07-13 | 2016-07-25 | 2016-07-13 | 2016-08-05 |  | Y
Central Hudson |  | SolarCity | CH-06709 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 6057 | Todd Hill | N |  | 3.6 | [13 empty] | NM | N | ABB PVI-3.6 OUTD-S-US | 2016-05-26 | 2016-06-10 | 10 | 2016-06-10 | [14 empty] | 2016-06-23 | 2016-06-30 |  | Y
Central Hudson |  | Kasselman Solar | CH-00236 | Catskill | Westerlo | Albany | 12193 | G | 1091 | Westerlo | N | CH-00236 | 14 | [13 empty] | NM | N | ENPHASE M250 (56) | 2016-05-27 | 2016-06-09 | 8 | 2016-06-09 | [14 empty] | 2016-07-07 | 2016-07-08 |  | Y
Central Hudson |  | NRG Home Solar | CH-00537 | Fishkill | Fishkill | Dutchess | 12524 | G | 8094 | Fishkill Plains | N |  | 3.65 | [13 empty] | NM | N | ENPHASE M215 (17) | 2016-05-27 | 2016-06-08 | 7 | 2016-06-08 | [14 empty] | 2016-08-09 | 2016-08-19 |  | Y
Central Hudson |  | NRG Home Solar | CH-00552 | Fishkill |  |  | 12582 | G | 8071 | Shenandoah | TBD |  | 10 | [13 empty] | NM | N | SOLAR EDGE SE10000A-US | 2016-05-27 | 2016-06-08 | 7 | 2016-06-08 | [17 empty] | W
Central Hudson |  | PosiGen Solar | CH-02877 | Catskill | Ravena | Albany | 12143 | G | 1081 | New Baltimore | N |  | 5.16 | [13 empty] | NM | N | ENPHASE M215 (24) | 2016-05-27 | 2016-06-08 | 7 | 2016-06-08 | [14 empty] | 2016-06-20 | 2016-06-24 |  | Y
Central Hudson |  | SolarCity | CH-05828 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6066 | Inwood Ave | N |  | 3.8 | [13 empty] | NM | N | SOLAREDGE SE3800A | 2016-05-27 | 2016-06-13 | 10 | 2016-06-13 | [14 empty] | 2016-07-06 | 2016-07-11 |  | Y
Central Hudson |  | SolarCity | CH-06264 | Newburgh | New Windsor | Orange | 12553 | G | 4046 | Union Ave | N |  | 3.8 | [13 empty] | NM | N | SOLAREDGE SE 3800A | 2016-06-20 | 2016-07-05 | 10 | 2016-07-05 | [14 empty] | 2016-07-28 | 2016-08-01 |  | Y
Central Hudson |  | SolarCity | CH-06748 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6092 | Manchester | N | CH-06748 | 8 | [13 empty] | NM | N | ABB PVI 5000 ABB PVI 3.0 | 2016-05-27 | 2016-06-13 | 10 | 2016-06-13 | [14 empty] | 2016-08-09 | 2016-08-15 |  | Y
Central Hudson |  | SolarCity | CH-06929 | Fishkill | Beacon | Dutchess | 12508 | G | 8017 | Forgebrook | N |  | 3.6 | [13 empty] | NM | N | ABB PVI 3.6 | 2016-05-27 | 2016-06-07 | 6 | 2016-06-07 | [14 empty] | 2016-08-12 | 2016-08-22 |  | Y
Central Hudson |  | SolarCity | CH-07062 | Newburgh | Newburgh | Orange | 12550 | G | 4011 | West Balmville | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000 OUTD-US | 2016-07-07 | 2016-07-14 | 5 | 2016-07-14 | [14 empty] | 2016-07-15 | 2016-07-26 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07077 | Newburgh | Wallkill | Ulster | 12589 | G | 5033 | Galeville | N |  | 3 | [13 empty] | NM | N | ABB PVI 3.0 | 2016-05-27 | 2016-05-27 | 0 | 2016-05-27 | [14 empty] | 2016-07-18 | 2016-07-18 |  | Y
Central Hudson |  | SolarCity | CH-07347 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8052 | North Chelsea | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2016-05-27 | 2016-06-08 | 7 | 2016-06-08 | [14 empty] | 2016-08-30 | 2016-09-14 |  | Y
Central Hudson |  | Trinity Solar | CH-08393 | Catskill | Hannacroix | Greene | 12087 | G | 1071 | Coxsackie | N |  | 5 | [13 empty] | NM | N | SOLAR EDGE 5000A-US | 2016-05-27 | 2016-06-08 | 7 | 2016-06-08 | [14 empty] | 2016-11-02 | 2016-11-02 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00912 | Kingston | Saugerties | Ulster | 12477 | G | 3004 | Saugerties | N |  | 2.5 | [13 empty] | NM | N | ENPHASE M250 (10) | 2016-06-13 | 2016-06-23 | 8 | 2016-06-23 | [14 empty] | 2016-07-29 | 2016-08-01 |  | Y
Central Hudson |  | SolarCity | CH-05023 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 7011 | Hibernia | N |  | 11 | [13 empty] | NM | N | ABB PVI-6000 OUTD-US ABB PVI-5000 OUTD-US | 2016-05-31 | 2016-06-13 | 9 | 2016-06-13 | [14 empty] | 2016-10-10 | 2016-10-13 |  | Y
Central Hudson |  | SolarCity | CH-06267 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2016-05-31 | 2016-06-09 | 7 | 2016-06-09 | [14 empty] | 2016-06-23 | 2016-06-29 |  | Y
Central Hudson |  | SolarCity | CH-06364 | Newburgh | Wallkill | Ulster | 12589 | G | 5041 | East Walden | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2016-05-31 | 2016-06-09 | 7 | 2016-06-09 | [14 empty] | 2016-07-07 | 2016-07-11 |  | Y
Central Hudson |  | SolarCity | CH-06461 | Catskill | Greenvl | Greene | 12083 | G | 2061 | Freehold | N |  | 6 | [13 empty] | NM | N | ABB PVI6.0 | 2016-05-31 | 2016-06-13 | 9 | 2016-06-13 | [14 empty] | 2016-08-05 | 2016-08-09 |  | Y
Central Hudson |  | SolarCity | CH-06640 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6042 | Spackenkill | N |  | 3 | [13 empty] | NM | N | ABB PVI 3.0 | 2016-05-31 | 2016-06-14 | 10 | 2016-06-14 | [14 empty] | 2016-07-15 | 2016-07-15 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07153 | Newburgh | Maybrook | Orange | 12543 | G | 5052 | Maybrook | N |  | 3 | [13 empty] | NM | N | ABB PVI-3.0 OUTD-S-US | 2016-05-31 | 2016-06-14 | 10 | 2016-06-14 | [14 empty] | 2016-07-14 | 2016-07-22 |  | Y
Central Hudson |  | SolarCity | CH-07622 | Newburgh | New Windsor | Orange | 12553 | G | 4094 | Bethlehem Rd | N |  | 7.2 | [13 empty] | NM | N | ABB PVI-3.6 OUTD-S-US (2) | 2016-05-31 | 2016-06-08 | 6 | 2016-06-08 | [14 empty] | 2016-07-01 | 2016-07-07 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08677 | Poughkeepsie |  |  | 12538 | G | 6074 | East Park | TBD |  | 7.09 | [13 empty] | NM | N | 33 ENPHASE M215 602LLS2XZC | 2016-05-31 | 2016-06-13 | 9 | 2016-06-13 | [17 empty] | W
Central Hudson |  | Kasselman Solar | CH-03528 | Catskill | Greenvl | Greene | 12083 | G | 1091 | Westerlo | N |  | 9.75 | [13 empty] | NM | N | ENPHASE M-250 (39) | 2016-06-01 | 2016-06-15 | 10 | 2016-06-15 | [14 empty] | 2016-07-19 | 2016-07-25 |  | Y
Central Hudson |  | Lighthouse Solar | CH-00274 | Newburgh | New Paltz | Ulster | 12561 | G | 5011 | Modena | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE 7600 A-US | 2016-06-01 | 2016-06-14 | 9 | 2016-06-14 | [14 empty] | 2016-09-09 | 2016-09-15 |  | Y
Central Hudson |  | Lighthouse Solar | CH-00312 | Kingston | Hurley | Ulster | 12443 | G | 2093 | Hurley Ave | N |  | 10 | [13 empty] | NM | N | SOLAREDGE 10000A-US | 2016-06-01 | 2016-06-14 | 9 | 2016-06-14 | [14 empty] | 2016-08-02 | 2016-08-05 |  | Y
Central Hudson |  | New York State Solar Farm | CH-00383 | Kingston | Saugerties | Ulster | 12477 | G | 3003 | Saugerties | N |  | 11 | [13 empty] | NM | N | SMA AMERICA SB5000 SMA AMERICA SB6000 | 2016-06-01 | 2016-06-14 | 9 | 2016-06-14 | [14 empty] | 2016-06-28 | 2016-07-07 |  | Y
Central Hudson |  | New York State Solar Farm | CH-00420 | Kingston | Kingston | Ulster | 12401 | G | 1011 | Boulevard | N |  | 3.52 | [13 empty] | NM | N | SUNPOWER SPR-E20327-C-AC (11) | 2016-07-19 | 2016-07-21 | 2 | 2016-07-21 | [14 empty] | 2016-07-25 | 2016-07-27 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | New York State Solar Farm | CH-00461 | Kingston | Olive Brdg | Ulster | 12461 | G | 3082 | Kerhonkson | N |  | 5 | [13 empty] | NM | N | SMA AMERICA SB5000 | 2016-06-01 | 2016-06-13 | 8 | 2016-06-13 | [14 empty] | 2016-07-14 | 2016-07-22 |  | Y
Central Hudson |  | SolarCity | CH-05659 | Kingston | Kingston | Ulster | 12401 | G | 1022 | East Kingston | N |  | 3 | [13 empty] | NM | N | ABB PVI-3.0OUTD-S-US | 2016-08-10 | 2016-08-19 | 7 | 2016-08-19 | [14 empty] | 2016-08-22 | 2016-08-22 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08675 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6094 | Manchester | N |  | 3.01 | [13 empty] | NM | N | 14 ENPHASE M215 602LLS22IG | 2016-06-01 | 2016-06-15 | 10 | 2016-06-15 | [14 empty] | 2016-09-29 | 2016-10-03 |  | Y
Central Hudson |  | Sunrise Solar Solutions, LLC | CH-09652 | Kingston | High Fls | Ulster | 12440 | G | 3022 | High Falls | N | CH-09681 | 7.5 | [13 empty] | NM | N | ENPHASE M250 (30) | 2016-07-06 | 2016-07-06 | 0 | 2016-07-06 | [14 empty] | 2016-10-12 | 2016-10-12 |  | Y
Central Hudson |  | RGS Energy | CH-00004 | Poughkeepsie |  |  | 12603 | G | 6003 | Reynolds Hill | N |  | 4.5 | [13 empty] | NM | N | 18 ENPHASE M25M250-60-2LL-S22 | 2016-06-16 | 2016-06-16 | 0 | 2016-06-16 | [17 empty] | W
Central Hudson |  | Green Street Power Partners, LLC | CH-00112 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8092 | Fishkill Plains | N |  | 6.72 | [13 empty] | NM | N | SUNPOWER SPR E20 327+C-AC (21) | 2016-06-15 | 2016-06-27 | 8 | 2016-06-27 | [14 empty] | 2016-09-29 | 2016-09-30 |  | Y
Central Hudson |  | Green Street Power Partners, LLC | CH-00120 | Newburgh | Highland | Ulster | 12528 | G | 5081 | Highland | N |  | 6 | [13 empty] | NM | N | SMA SB6000TL-US-22 | 2016-06-02 | 2016-06-16 | 10 | 2016-06-16 | [14 empty] | 2016-08-16 | 2016-08-23 |  | Y
Central Hudson |  | PosiGen Solar | CH-02885 | Catskill | S Cairo | Greene | 12482 | G | 2005 | North Catskill | N |  | 5.16 | [13 empty] | NM | N | ENPHASE M215 (24) | 2016-06-02 | 2016-06-16 | 10 | 2016-06-16 | [14 empty] | 2016-07-18 | 2016-07-25 |  | Y
Central Hudson |  | SolarCity | CH-05044 | Newburgh | Highland | Ulster | 12528 | G | 5022 | Ohioville | N |  | 10.2 | [13 empty] | NM | N | ABB PVI-6000 OUTD-US ABB PVI-4.2 OUTD-US | 2016-06-02 | 2016-06-16 | 10 | 2016-06-16 | [14 empty] | 2016-08-24 | 2016-08-31 |  | Y
Central Hudson |  | SolarCity | CH-06177 | Newburgh | New Paltz | Ulster | 12561 | G | 5023 | Ohioville | N |  | 8.2 | [13 empty] | NM | N | FRONIUS PRIMO 8.2 | 2016-06-02 | 2016-06-14 | 8 | 2016-06-14 | [14 empty] | 2016-09-22 | 2016-09-23 |  | Y
Central Hudson |  | SolarCity | CH-06218 | Newburgh | Newburgh | Orange | 12550 | G | 4024 | Coldenham | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE 5000A | 2016-06-02 | 2016-06-14 | 8 | 2016-06-14 | [14 empty] | 2016-08-31 | 2016-09-30 |  | Y
Central Hudson |  | SolarCity | CH-06940 | Fishkill | Beacon | Dutchess | 12508 | G | 8085 | Tioronda | N |  | 3.6 | [13 empty] | NM | N | ABB PVI-3.6 OUTD-S-US | 2016-06-17 | 2016-06-28 | 7 | 2016-06-28 | [14 empty] | 2016-07-28 | 2016-07-28 |  | Y
Central Hudson |  | SolarCity | CH-07581 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8093 | Fishkill Plains | N |  | 12 | [13 empty] | NM | N | ABB PVI-6000 OUTD-S-US (2) | 2016-06-02 | 2016-06-15 | 9 | 2016-06-15 | [14 empty] | 2016-06-22 | 2016-06-28 |  | Y
Central Hudson |  | STR Systems NY LLC | CH-08318 | Newburgh | New Paltz | Ulster | 12561 | G | 5011 | Modena | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6-1 | 2016-06-02 | 2016-06-15 | 9 | 2016-06-15 | [14 empty] | 2016-07-28 | 2016-07-29 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08800 | Fishkill | Putnam Valley | Putnam | 10524 | G | 8066 | Merritt Park | N |  | 5.8 | [13 empty] | NM | N | ENPHASE M215 602LLS22IG (27) | 2016-07-05 | 2016-07-05 | 0 | 2016-07-05 | [14 empty] | 2016-11-11 | 2016-11-11 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-00050 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6092 | Manchester | N |  | 10 | [13 empty] | NM | N | SOLAR EDGE 10.00 | 2016-06-03 | 2016-06-17 | 10 | 2016-06-17 | [14 empty] | 2016-07-13 | 2016-07-13 |  | Y
Central Hudson |  | SolarCity | CH-05827 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6065 | Inwood Ave | N |  | 3 | [13 empty] | NM | N | ABB PVI 3.0 | 2016-06-03 | 2016-06-17 | 10 | 2016-06-17 | [14 empty] | 2016-08-15 | 2016-08-18 |  | Y
Central Hudson |  | SolarCity | CH-05981 | Newburgh | Highland | Ulster | 12528 | G | 5081 | Highland | N |  | 3 | [13 empty] | NM | N | ABB PVI 3.0 | 2016-06-03 | 2016-06-17 | 10 | 2016-06-17 | [14 empty] | 2016-08-04 | 2016-08-10 |  | Y
Central Hudson |  | SolarCity | CH-07872 | Poughkeepsie |  |  | 12603 | G | 6003 | Reynolds Hill | N |  | 3 | [13 empty] | NM | N | ABB PVI 3.0 | 2016-06-03 | 2016-06-17 | 10 | 2016-06-17 | [17 empty] | W
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08812 | Fishkill | Garrison | Putnam | 10524 | G | 8066 | Merritt Park | N |  | 4.94 | [13 empty] | NM | N | ENPHASE M215 602LLS22IG (23) | 2016-06-15 | 2016-06-27 | 8 | 2016-06-27 | [14 empty] | 2016-10-04 | 2016-10-04 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-00185 | Fishkill | Beacon | Dutchess | 12508 | G | 8087 | Tioronda | N |  | 3.8 | [13 empty] | NM | N | SMA AMERICA SB3800TL-US-22 | 2016-06-16 | 2016-06-29 | 9 | 2016-06-29 | [14 empty] | 2016-08-12 | 2016-08-16 |  | Y
Central Hudson |  | New York State Solar Farm | CH-00381 | Kingston | Saugerties | Ulster | 12477 | G | 3002 | Saugerties | N |  | 8 | [13 empty] | NM | N | SMA AMERICA SB TL 3000 SMA AMERICA SB TL 5000 | 2016-06-20 | 2016-07-05 | 10 | 2016-07-05 | [14 empty] | 2016-08-03 | 2016-08-03 |  | Y
Central Hudson |  | New York State Solar Farm | CH-00388 | Kingston | Saugerties | Ulster | 12477 | G | 3003 | Saugerties | N |  | 3.8 | [13 empty] | NM | N | SMA AMERICA SB 3800 TL | 2016-06-20 | 2016-07-05 | 10 | 2016-07-05 | [14 empty] | 2016-07-18 | 2016-07-22 |  | Y
Central Hudson |  | SolarCity | CH-05006 | Kingston | Saugerties | Ulster | 12477 | G | 3002 | Saugerties | N |  | 12 | [13 empty] | NM | N | ABB PVI 6000 (2) | 2016-06-06 | 2016-06-16 | 8 | 2016-06-16 | [14 empty] | 2016-07-14 | 2016-07-22 |  | Y
Central Hudson |  | SolarCity | CH-05326 | Poughkeepsie | Lagrangeville | Dutchess | 12540 | G | 6055 | Todd Hill | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE 7600A | 2016-06-06 | 2016-06-20 | 10 | 2016-06-20 | [14 empty] | 2016-07-14 | 2016-07-26 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06547 | Kingston | Kingston | Ulster | 12401 | G | 111 | South Wall St | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2016-06-06 | 2016-06-16 | 8 | 2016-06-16 | [14 empty] | 2016-07-07 | 2016-07-13 |  | Y
Central Hudson |  | Trinity Solar | CH-08398 | Catskill | Ravena | Albany | 12143 | G | 1082 | New Baltimore | N | CH-08398 | 10 | [13 empty] | NM | N | SOLAR EDGE | 2016-06-06 | 2016-06-17 | 9 | 2016-06-17 | [14 empty] | 2016-07-13 | 2016-07-22 |  | Y
Central Hudson |  | Trinity Solar | CH-08491 | Poughkeepsie |  |  | 12502 | G | 7085 | Ancram | TBD |  | 7.6 | [13 empty] | NM | N | SOLAREDGE 7600A-US | 2016-06-06 | 2016-06-20 | 10 | 2016-06-20 | [17 empty] | W
Central Hudson |  | Grid Alternatives Tri-State | CH-01176 | Kingston | Kingston | Ulster | 12401 | G | 2092 | Hurley Ave | N |  | 4.3 | [13 empty] | NM | N | ENPHASE ENERGY M215 (20) | 2016-07-15 | 2016-07-18 | 1 | 2016-07-18 | [14 empty] | 2016-08-18 | 2016-08-24 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Monolith Solar Associates LLC | CH-02686 | Catskill | Dormansvl | Albany | 12055 | G | 1091 | Westerlo | N | CH-02686 | 6 | [13 empty] | NM | N | SOLAR EDGE SE6000A-US | 2016-07-07 | 2016-07-08 | 1 | 2016-07-08 | [14 empty] | 2016-07-20 | 2016-07-25 |  | Y
Central Hudson |  | SolarCity | CH-05157 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8091 | Fishkill Plains | N | CH-05157 | 12 | [13 empty] | NM | N | ABB PVI 6000 (2) | 2016-06-07 | 2016-06-17 | 8 | 2016-06-17 | [14 empty] | 2016-07-14 | 2016-07-22 |  | Y
Central Hudson |  | SolarCity | CH-05693 | Kingston | Kingston | Ulster | 12401 | G | 2093 | Hurley Ave | N |  | 3 | [13 empty] | NM | N | ABB PVI 3.0 | 2016-06-07 | 2016-06-17 | 8 | 2016-06-17 | [14 empty] | 2016-11-10 | 2016-11-15 |  | Y
Central Hudson |  | SolarCity | CH-06229 | Newburgh | Newburgh | Orange | 12550 | G | 4015 | West Balmville | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2016-06-07 | 2016-06-17 | 8 | 2016-06-17 | [14 empty] | 2016-07-15 | 2016-07-15 |  | Y
Central Hudson |  | SolarCity | CH-07226 | Kingston | Kingston | Ulster | 12401 | G | 1022 | East Kingston | N |  | 5 | [13 empty] | NM | N | ABB PVI 5000 | 2016-06-07 | 2016-06-17 | 8 | 2016-06-17 | [14 empty] | 2016-08-31 | 2016-09-09 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08754 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7062 | Milan | N |  | 6.88 | [13 empty] | NM | N | 32 ENPHASE M215 602LLS22IG | 2016-06-07 | 2016-06-21 | 10 | 2016-06-21 | [14 empty] | 2016-07-29 | 2016-08-11 |  | Y
Central Hudson |  | Lotus Energy Inc. | CH-03866 | Kingston | Woodstock | Ulster | 12498 | G | 3014 | Woodstock | N |  | 20.4 | [13 empty] | NM | N | SMA SB7700 TL US-22 SMA SB5000 TL US-22 | 2016-06-24 | 2016-07-06 | 7 | 2016-07-06 | [8 empty] | 350 | 350 |  | 2016-07-18 | 2016-07-18 | 2016-07-29 | 2016-08-26 | 2016-08-26 |  | Y
Central Hudson |  | New York State Solar Farm | CH-00382 | Kingston | Saugerties | Ulster | 12477 | G | 3002 | Saugerties | N |  | 6.72 | [13 empty] | NM | N | SUNPOWER SPR-E20 327-C-AC (21) | 2016-06-08 | 2016-06-17 | 7 | 2016-06-17 | [14 empty] | 2016-07-22 | 2016-07-28 |  | Y
Central Hudson |  | New York State Solar Farm | CH-00427 | Poughkeepsie | Millbrook | Dutchess | 12545 | G | 7025 | Tinkertown | N |  | 9.52 | [13 empty] | NM | N | 40 SUNPOWER SPR-E20 327-C-AC | 2016-06-08 | 2016-06-22 | 10 | 2016-06-22 | [14 empty] | 2016-07-21 | 2016-07-22 |  | Y
Central Hudson |  | NRG Home Solar | CH-00571 | Fishkill |  |  | 12533 | G | 8095 | Fishkill Plains | TBD |  | 3 | [13 empty] | NM | N | ENPHASE M250 (12) | 2016-06-08 | 2016-06-17 | 7 | 2016-06-17 | [17 empty] | W
Central Hudson |  | SolarCity | CH-06448 | Catskill | Medusa | Albany | 12120 | G | 1092 | Westerlo | N |  | 6.6 | [13 empty] | NM | N | ABB PVI 3.0 ABB PVI 3.6 | 2016-06-08 | 2016-06-20 | 8 | 2016-06-20 | [14 empty] | 2016-07-14 | 2016-07-22 |  | Y
Central Hudson |  | SolarCity | CH-06652 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6091 | Manchester | N |  | 5 | [13 empty] | NM | N | ABB PVI 5000 | 2016-06-08 | 2016-06-21 | 9 | 2016-06-21 | [14 empty] | 2016-07-28 | 2016-07-28 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08752 | Poughkeepsie |  |  | 12571 | G | 7056 | Rhinebeck | TBD |  | 6.45 | [13 empty] | NM | N | 30 ENPHASE M215 602LLS22IG | 2016-06-08 | 2016-06-21 | 9 | 2016-06-21 | [17 empty] | W
Central Hudson |  | SolarCity | CH-05671 | Kingston | Port Ewen | Ulster | 12466 | G | 1012 | Boulevard | N |  | 10 | [13 empty] | NM | N | SOLAREDGE SE 10000A | 2016-06-09 | 2016-06-21 | 8 | 2016-06-21 | [14 empty] | 2016-12-09 | 2016-12-09 |  | Y
Central Hudson |  | SolarCity | CH-05745 | Kingston | Kingston | Ulster | 12401 | G | 2016 | Lincoln Park | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2016-07-12 | 2016-07-12 | 0 | 2016-07-12 | [14 empty] | 2016-08-24 | 2016-08-25 |  | Y
Central Hudson |  | Trinity Solar | CH-08376 | Newburgh | Campbell Hall | Orange | 10916 | G | 5051 | Maybrook | N |  | 11.4 | [13 empty] | NM | N | SOLAREDGE SE11400A-US | 2016-06-09 | 2016-06-20 | 7 | 2016-06-20 | [14 empty] | 2016-10-21 | 2016-10-21 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08837 | Poughkeepsie |  |  | 12572 | G | 7053 | Rhinebeck | TBD |  | 8.6 | [13 empty] | NM | N | 40 ENPHASE M215 602LLS22IG | 2016-06-23 | 2016-06-23 | 0 | 2016-06-23 | [17 empty] | W
Central Hudson |  | Lighthouse Solar | CH-00289 | Kingston | Saugerties | Ulster | 12477 | G | 3002 | Saugerties | N |  | 15.4 | [13 empty] | NM | N | SMA 7700 (2) | 2016-06-22 | 2016-07-05 | 8 | 2016-07-05 | [8 empty] | 350 | 350 |  | 2016-07-25 | 2016-07-25 | 2016-07-29 | 2016-08-26 | 2016-08-26 |  | Y
Central Hudson |  | Lighthouse Solar | CH-00308 | Newburgh | New Paltz | Ulster | 12561 | G | 5023 | Ohioville | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE 7600 A-US | 2016-07-06 | 2016-07-06 | 0 | 2016-07-06 | [14 empty] | 2016-08-30 | 2016-08-30 |  | Y
Central Hudson |  | NRG Home Solar | CH-00555 | Newburgh | Newburgh | Orange | 12550 | G | 4052 | Union Ave | N |  | 6.02 | [13 empty] | NM | N | ENPHASE M215 (28) | 2016-06-10 | 2016-06-22 | 8 | 2016-06-22 | [14 empty] | 2016-08-10 | 2016-08-15 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00864 | Newburgh | Wallkill | Ulster | 12589 | G | 5013 | Modena | N | CH-00864 | 6.24 | [13 empty] | NM | N | ENPHASE 215 (29) | 2016-06-22 | 2016-07-06 | 9 | 2016-07-06 | [14 empty] | 2016-10-03 | 2016-10-03 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00932 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 6074 | East Park | N |  | 8.6 | [13 empty] | NM | N | 40 ENPHASE M215 60-2LL-S22 | 2016-06-10 | 2016-06-24 | 10 | 2016-06-24 | [14 empty] | 2016-09-20 | 2016-09-22 |  | Y
Central Hudson |  | Direct Energy Solar | CH-01064 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7061 | Milan | N | CH-01064 | 4.085 | [13 empty] | NM | N | 19 ENPHASE M215 60-2LL-S22 | 2016-06-10 | 2016-06-24 | 10 | 2016-06-24 | [14 empty] | 2016-08-08 | 2016-08-15 |  | Y
Central Hudson |  | Hudson Solar | CH-01329 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7062 | Milan | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE-6000A-US-U | 2016-06-10 | 2016-06-24 | 10 | 2016-06-24 | [14 empty] | 2016-07-29 | 2016-08-01 |  | Y
Central Hudson |  | Hudson Solar | CH-01776 | Poughkeepsie | Millbrook | Dutchess | 12545 | G | 7025 | Tinkertown | N |  | 3 | [13 empty] | NM | N | SOLAREDGE SE-3000 A-US-U | 2016-06-10 | 2016-06-24 | 10 | 2016-06-24 | [14 empty] | 2016-07-26 | 2016-07-27 |  | Y
Central Hudson |  | Hudson Solar | CH-01835 | Poughkeepsie |  |  | 12571 | G | 7054 | Rhinebeck | TBD |  | 3 | [13 empty] | NM | N | SOLAREDGE SE-3000 A-US-U | 2016-06-10 | 2016-06-24 | 10 | 2016-06-24 | [17 empty] | W
Central Hudson |  | Hudson Solar | CH-01849 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7061 | Milan | N |  | 15.2 | [13 empty] | NM | N | 2 SOLAREDGE SE-7600A-US-U | 2016-06-10 | 2016-06-24 | 10 | 2016-06-24 | [14 empty] | 2016-12-08 | 2016-12-08 |  | Y
Central Hudson |  | Hudson Solar | CH-01869 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7055 | Rhinebeck | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE-6000A-US-U | 2016-06-10 | 2016-06-24 | 10 | 2016-06-24 | [14 empty] | 2016-07-27 | 2016-07-27 |  | Y
Central Hudson |  | Hudson Solar | CH-01933 | Fishkill | Stormvl | Dutchess | 12582 | G | 8093 | Fishkill Plains | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE-5000 A-US-U | 2016-06-10 | 2016-06-24 | 10 | 2016-06-24 | [14 empty] | 2016-07-11 | 2016-07-14 |  | Y
Central Hudson |  | Hudson Solar | CH-01966 | Newburgh | Newburgh | Orange | 12550 | G | 5004 | Marlboro | N |  | 11.4 | [13 empty] | NM | N | (1) SOLAREDGE SE-7600A-US-U (1) SOLAREDGE SE-3800A-US-U | 2016-06-10 | 2016-07-27 | 32 | 2016-07-27 | [14 empty] | 2016-09-06 | 2016-09-15 |  | Y
Central Hudson |  | Hudson Solar | CH-02189 | Newburgh | New Paltz | Ulster | 12561 | G | 5031 | Galeville | Y | CH-02189 | 15.2 | [13 empty] | NM | N | SOLAREDGE SE-7600 A-US-U | 2016-06-10 | 2016-06-20 | 6 | 2016-06-20 | [14 empty] | 2016-08-22 | 2016-09-01 |  | Y
Central Hudson |  | SolarCity | CH-05611 | Kingston | Accord | Ulster | 12404 | G | 3081 | Kerhonkson | N |  | 7.2 | [13 empty] | NM | N | ABB PVI3.0 ABB PVI4.2 | 2016-06-10 | 2016-06-21 | 7 | 2016-06-21 | [14 empty] | 2016-07-20 | 2016-07-22 |  | Y
Central Hudson |  | SolarCity | CH-05892 | Poughkeepsie | Hopewell Jct | Dutchess | 12533 | G | 6052 | Todd Hill | N |  | 4.2 | [13 empty] | NM | N | ABB PVI 4.2 | 2016-06-10 | 2016-06-24 | 10 | 2016-06-24 | [14 empty] | 2016-07-15 | 2016-07-27 |  | Y
Central Hudson |  | Solar Generation | CH-08136 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7061 | Milan | N |  | 19.2 | [13 empty] | NM | N | 36 SUNPOWER SB X22-360-C AC | 2016-06-10 | 2016-06-24 | 10 | 2016-06-24 | [14 empty] | 2017-11-15 | 2017-11-22 |  | Y
Central Hudson |  | New York State Solar Farm | CH-00385 | Kingston | Saugerties | Ulster | 12477 | G | 3004 | Saugerties | N |  | 7.6 | [13 empty] | NM | N | SMA AMERICA SB3800TL (2) | 2016-06-13 | 2016-06-24 | 9 | 2016-06-24 | [14 empty] | 2016-09-09 | 2016-09-15 |  | Y
Central Hudson |  | SolarCity | CH-05095 | Kingston | Saugerties | Ulster | 12477 | G | 3002 | Saugerties | N |  | 8.2 | [13 empty] | NM | N | FRONIUS PRIMO 8.2 | 2016-07-08 | 2016-07-08 | 0 | 2016-07-08 | [14 empty] | 2016-07-12 | 2016-07-21 |  | Y
Central Hudson |  | SolarCity | CH-06636 | Poughkeepsie | Poughkeepsie |  | 12603 | G | 6042 | Spackenkill | TBD |  | 10.2 | [13 empty] | NM | N | ABB PVI-6000-OUTD ABB PVI-4.2-OUTD-S | 2016-06-13 | 2016-06-27 | 10 | 2016-06-27 | [14 empty] | 2016-09-27 |  |  | W |  | 9/30/16 - CH Rep unable to install net meter due to no access. Appointment Required.
Central Hudson |  | SolarCity | CH-07074 | Newburgh | Marlboro | Ulster | 12542 | G | 5001 | Marlboro | N |  | 12 | [13 empty] | NM | N | ABB PVI 6000 (2) | 2016-06-13 | 2016-06-21 | 6 | 2016-06-21 | [14 empty] | 2016-07-15 | 2016-07-15 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07604 | Newburgh | Marlboro | Ulster | 12542 | G | 5004 | Marlboro | N |  | 5 | [13 empty] | NM | N | ABB PVI 5000 | 2016-06-13 | 2016-06-21 | 6 | 2016-06-21 | [14 empty] | 2016-07-18 | 2016-07-28 |  | Y
Central Hudson |  | SolarCity | CH-07646 | Poughkeepsie | Poughkeepsie |  | 12603 | G | 6042 | Spackenkill | N |  | 6 | [13 empty] | NM | N | ABB PVI 3.0 (2) | 2016-06-13 | 2016-06-27 | 10 | 2016-06-27 | [14 empty] | 2016-08-24 | 2016-08-30 |  | W
Central Hudson |  | SolarCity | CH-07682 | Newburgh | Newburgh | Orange | 12550 | G | 4051 | Union Ave | N |  | 5 | [13 empty] | NM | N | ABB PVI 5000 | 2016-06-13 | 2016-06-21 | 6 | 2016-06-21 | [14 empty] | 2016-08-24 | 2016-09-06 |  | Y
Central Hudson |  | Hudson Solar | CH-01233 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8096 | Fishkill Plains | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE-5000 A-US-U | 2016-06-14 | 2016-06-27 | 9 | 2016-06-27 | [14 empty] | 2016-09-19 | 2016-09-20 |  | Y
Central Hudson |  | Hudson Solar | CH-01281 | Kingston | High Fls | Ulster | 12440 | G | 3021 | High Falls | N |  | 10 | [13 empty] | NM | N | SOLAREDGE SE-10000 A-US-U | 2016-08-17 | 2016-08-17 | 0 | 2016-08-17 | [14 empty] | 2016-10-13 | 2016-10-18 |  | Y
Central Hudson |  | Hudson Solar | CH-01745 | Poughkeepsie | Staatsburg | Dutchess | 12580 | G | 7011 | Hibernia | N | CH-01745 | 7.6 | [13 empty] | NM | N | SOLAREDGE SE-7600 A-US-U | 2016-06-14 | 2016-06-28 | 10 | 2016-06-28 | [14 empty] | 2016-10-20 | 2016-10-25 |  | Y
Central Hudson |  | Hudson Solar | CH-01748 | Poughkeepsie | Clinton Corners | Dutchess | 12514 | G | 7013 | Hibernia | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE-7600 A-US-U | 2016-06-14 | 2016-06-28 | 10 | 2016-06-28 | [14 empty] | 2016-08-29 | 2016-08-29 |  | Y
Central Hudson |  | Hudson Solar | CH-01808 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6046 | Spackenkill | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE-7600 A-US-U | 2016-06-14 | 2016-06-28 | 10 | 2016-06-28 | [14 empty] | 2016-08-22 | 2016-08-22 |  | Y
Central Hudson |  | Hudson Solar | CH-02066 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6003 | Reynolds Hill | N |  | 3.8 | [13 empty] | NM | N | SOLAREDGE SE-3800 A-US-U | 2016-06-14 | 2016-06-28 | 10 | 2016-06-28 | [14 empty] | 2016-08-31 | 2016-08-31 |  | Y
Central Hudson |  | Hudson Solar | CH-02123 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7054 | Rhinebeck | N |  | 11.4 | [13 empty] | NM | N | SOLAREDGE SE-11400 A-US-U | 2016-06-14 | 2016-06-28 | 10 | 2016-06-28 | [14 empty] | 2016-08-31 | 2016-08-31 |  | Y
Central Hudson |  | Hudson Solar | CH-02272 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6096 | Manchester | N |  | 3.8 | [13 empty] | NM | N | SOLAREDGE SE-3800 A-US-U | 2016-06-14 | 2016-06-28 | 10 | 2016-06-28 | [14 empty] | 2016-09-02 | 2016-09-02 |  | Y
Central Hudson |  | SolarCity | CH-05789 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6044 | Spackenkill | N |  | 12 | [13 empty] | NM | N | ABB PVI 6000 (2) | 2016-06-14 | 2016-06-28 | 10 | 2016-06-28 | [14 empty] | 2016-09-22 | 2016-09-26 |  | Y
Central Hudson |  | Solar Generation | CH-08292 | Kingston | Hurley | Ulster | 12443 | G | 2094 | Hurley Ave | N |  | 3.8 | [13 empty] | NM | N | SOLAREDGE SB3800US | 2016-06-14 | 2016-06-24 | 8 | 2016-06-24 | [14 empty] | 2017-05-22 | 2017-05-23 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-03338 | Catskill | Tannersvl | Greene | 12485 | G | 2385 | Lawrenceville | N |  | 3 | [13 empty] | NM | N | SOLAREDGE 3000-US | 2016-06-29 | 2016-07-06 | 4 | 2016-07-06 | [14 empty] | 2016-07-08 | 2016-07-15 |  | Y
Central Hudson |  | Green Street Power Partners, LLC | CH-00110 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7062 | Milan | N |  | 15.36 | [13 empty] | NM | N | 48 SMA SPR 327-C-AC | 2016-06-15 | 2016-06-29 | 10 | 2016-06-29 | [14 empty] | 2016-09-09 | 2016-09-15 |  | Y
Central Hudson |  | Kasselman Solar | CH-00247 | Catskill | Greenvl | Greene | 12083 | G | 2061 | Freehold | N |  | 6 | [13 empty] | NM | N | ENPHASE ENERGY M-250 (24) | 2016-06-15 | 2016-06-29 | 10 | 2016-06-29 | [14 empty] | 2016-09-01 | 2016-09-08 |  | Y
Central Hudson |  | New York State Solar Farm | CH-00405 | Newburgh | New Paltz | Ulster | 12561 | G | 5023 | Ohioville | N |  | 6.8 | [13 empty] | NM | N | SMA AMERICA SB TL 3000 SMA AMERICA SB TL 3800 | 2016-06-15 | 2016-06-27 | 8 | 2016-06-27 | [14 empty] | 2016-08-24 | 2016-08-24 |  | Y
Central Hudson |  | Direct Energy Solar | CH-01062 | Kingston | Kingston | Ulster | 12401 | G | 2093 | Hurley Ave | N |  | 8.17 | [13 empty] | NM | N | ENPHASE M215 60-2LL-S22 (38) | 2016-06-29 | 2016-07-06 | 4 | 2016-07-06 | [14 empty] | 2016-09-13 | 2016-09-13 |  | Y
Central Hudson |  | Hudson Solar | CH-01820 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6092 | Manchester | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE-6000A-US-U | 2016-06-15 | 2016-06-29 | 10 | 2016-06-29 | [14 empty] | 2016-10-03 | 2016-10-03 |  | Y
Central Hudson |  | Hudson Solar | CH-02158 | Poughkeepsie | Stanfordvl | Dutchess | 12581 | G | 7072 | Stanfordville | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE-5000A-US-U | 2016-06-15 | 2016-06-29 | 10 | 2016-06-29 | [14 empty] | 2016-09-06 | 2016-09-06 |  | Y
Central Hudson |  | Hudson Solar | CH-02300 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8043 | Myers Corners | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE-7600 A-US-U | 2016-06-15 | 2016-06-27 | 8 | 2016-06-27 | [14 empty] | 2016-09-15 | 2016-09-15 |  | Y
Central Hudson |  | Hudson Solar | CH-02346 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7051 | Rhinebeck | N |  | 10 | [13 empty] | NM | N | SOLAREDGE SE-10000A-US-U | 2016-06-15 | 2016-06-29 | 10 | 2016-06-29 | [14 empty] | 2016-08-08 | 2016-08-10 |  | Y
Central Hudson |  | SolarCity | CH-07373 | Fishkill | Beacon | Dutchess | 12508 | G | 8015 | Forgebrook | N |  | 4.2 | [13 empty] | NM | N | ABB PVI 4.2 | 2016-06-15 | 2016-06-27 | 8 | 2016-06-27 | [14 empty] | 2016-08-10 | 2016-08-17 |  | Y
Central Hudson |  | Sunrun Inc. | CH-08356 | Newburgh | Newburgh | Orange | 12550 | G | 4015 | West Balmville | N |  | 3.8 | [13 empty] | NM | N | SOLAREDGE SE3800 | 2016-06-15 | 2016-06-27 | 8 | 2016-06-27 | [14 empty] | 2016-11-22 | 2016-11-22 |  | Y
Central Hudson |  | Trinity Solar | CH-08482 | Poughkeepsie |  |  | 12603 | G | 6003 | Reynolds Hill | TBD |  | 5 | [13 empty] | NM | N | SOLAREDGE 5000A-US | 2016-06-15 | 2016-06-29 | 10 | 2016-06-29 | [17 empty] | W
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08683 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7062 | Milan | N |  | 3.655 | [13 empty] | NM | N | 17 ENPHASE M215 602LLS22IG | 2016-06-15 | 2016-06-29 | 10 | 2016-06-29 | [14 empty] | 2016-09-07 | 2016-09-09 |  | Y
Central Hudson |  | SolarCity | CH-05826 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6065 | Inwood Ave | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2016-06-16 | 2016-06-30 | 10 | 2016-06-30 | [14 empty] | 2016-07-28 | 2016-07-28 |  | Y
Central Hudson |  | SolarCity | CH-07304 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 6051 | Todd Hill | N |  | 10.2 | [13 empty] | NM | N | ABB PVI 6000 ABB PVI 4.2 | 2016-06-16 | 2016-06-30 | 10 | 2016-06-30 | [14 empty] | 2016-07-05 | 2016-07-12 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07873 | Poughkeepsie |  |  | 12603 | G | 6046 | Spackenkill | TBD |  | 7.2 | [13 empty] | NM | N | ABB PVI-4.2 OUTD-S-US ABB PVI-3.0 OUTD-S-US | 2016-06-16 | 2016-06-30 | 10 | 2016-06-30 | [17 empty] | W
Central Hudson |  | SolarCity | CH-07918 | Newburgh |  |  | 10916 | G | 5052 | Maybrook | TBD |  | 12 | [13 empty] | NM | N | ABB PVI-6000 OUTD-US (2) | 2016-09-13 | 2016-09-19 | 4 | 2016-09-19 | [17 empty] | W
Central Hudson |  | Trinity Solar | CH-08396 | Catskill | Athens | Greene | 12015 | G | 1074 | Coxsackie | N |  | 3.8 | [13 empty] | NM | N | SOLAR EDGE 3800A-US | 2016-06-16 | 2016-06-30 | 10 | 2016-06-30 | [14 empty] | 2016-10-05 | 2016-10-06 |  | Y
Central Hudson |  | Trinity Solar | CH-08484 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6066 | Inwood Ave | N |  | 5 | [13 empty] | NM | N | SOLAR EDGE 5000A-US | 2016-06-16 | 2016-06-30 | 10 | 2016-06-30 | [14 empty] | 2016-09-08 | 2016-09-23 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-00051 | Poughkeepsie | Pine Plns | Dutchess | 12567 | G | 7091 | Pulvers Corners | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE 7600A US | 2016-06-17 | 2016-07-01 | 10 | 2016-07-01 | [14 empty] | 2016-09-20 | 2016-09-20 |  | Y
Central Hudson |  | Lighthouse Solar | CH-00266 | Kingston | High Fls | Ulster | 12440 | G | 3024 | High Falls | N |  | 5 | [13 empty] | NM | N | SOLAREDGE 5000 A-US | 2016-07-01 | 2016-07-07 | 3 | 2016-07-07 | [14 empty] | 2016-08-30 | 2016-09-02 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03581 | Newburgh | Esopus | Ulster | 12429 | G | 5084 | Highland | N |  | 11.4 | [13 empty] | NM | N | SOLAREDGE 11400 A-US | 2016-06-17 | 2016-07-01 | 10 | 2016-07-01 | [8 empty] | 350 | 350 |  | 2016-09-20 | 2016-09-20 | 2016-09-30 | 2016-09-30 | 2016-10-07 |  | Y
Central Hudson |  | Lighthouse Solar | CH-00286 | Kingston | Rosendale | Ulster | 12472 | G | 3022 | High Falls | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE 7600 A-US | 2016-06-17 | 2016-07-01 | 10 | 2016-07-01 | [14 empty] | 2017-01-16 | 2017-01-20 |  | Y
Central Hudson |  | PosiGen Solar | CH-02881 | Kingston | Lk Katrine | Ulster | 12449 | G | 2016 | Lincoln Park | N |  | 6.88 | [13 empty] | NM | N | ENPHASE ENERGY M215-60-2LL-S22-IG (32) | 2016-06-17 | 2016-06-30 | 9 | 2016-06-30 | [14 empty] | 2016-07-29 | 2016-08-01 |  | Y
Central Hudson |  | SolarCity | CH-06494 | Kingston | Hurley | Ulster | 12443 | G | 2093 | Hurley Ave | N |  | 3 | [13 empty] | NM | N | ABB PVI 3.0 | 2016-06-17 | 2016-06-21 | 2 | 2016-06-21 | [14 empty] | 2016-07-27 | 2016-08-03 |  | Y
Central Hudson |  | Sungevity Inc | CH-09475 | Newburgh | Newburgh | Orange | 12550 | G | 4023 | Coldenham | N |  | 6 | [13 empty] | NM | N | ABB PVI-3.0-OUTD-S-US-A (2) | 2016-06-17 | 2016-06-30 | 9 | 2016-06-30 | [14 empty] | 2016-07-27 | 2016-08-05 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-00085 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8044 | Myers Corners | N |  | 7.6 | [13 empty] | NM | N | SOLAR EDGE 7600AUS | 2016-06-20 | 2016-07-05 | 10 | 2016-07-05 | [14 empty] | 2016-08-29 | 2016-08-29 |  | Y
Central Hudson |  | New York State Solar Farm | CH-00408 | Newburgh | Highland | Ulster | 12528 | G | 5012 | Modena | N |  | 6 | [13 empty] | NM | N | SMA AMERICA SB 6000-TL | 2016-06-20 | 2016-07-05 | 10 | 2016-07-05 | [14 empty] | 2016-08-30 | 2016-09-07 |  | Y
Central Hudson |  | NRG Home Solar | CH-00508 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6092 | Manchester | N |  | 5.59 | [13 empty] | NM | N | (26) ENPHASE M215 | 2016-07-07 | 2016-07-12 | 3 | 2016-07-12 | [14 empty] | 2016-12-19 | 2016-12-19 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00910 | Kingston | Saugerties | Ulster | 12477 | G | 3002 | Saugerties | N |  | 7.1 | [13 empty] | NM | N | ENPHASE M215 60-2LL-S22 (33) | 2016-06-20 | 2016-07-05 | 10 | 2016-07-05 | [14 empty] | 2016-10-06 | 2016-10-10 |  | Y
Central Hudson |  | Mannino Electric | CH-02598 | Poughkeepsie | Lagrangevl | Dutchess | 12540 | G | 6055 | Todd Hill | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A-US | 2016-06-20 | 2016-07-01 | 9 | 2016-07-01 | [14 empty] | 2016-09-23 | 2016-09-23 |  | Y
Central Hudson |  | SolarCity | CH-05430 | Newburgh | New Windsor | Orange | 12553 | G | 4097 | Bethlehem Rd | N |  | 4.2 | [13 empty] | NM | N | ABB PVI-4.2 OUTD-S-US | 2016-06-20 | 2016-06-27 | 5 | 2016-06-27 | [14 empty] | 2016-08-23 | 2016-08-25 |  | Y
Central Hudson |  | SolarCity | CH-07900 | Newburgh |  |  | 12528 | G | 5081 | Highland | TBD |  | 6.6 | [13 empty] | NM | N | ABB PVI-3.6 ABB PVI-3.0 | 2016-07-26 | 2016-07-26 | 0 | 2016-07-26 | [17 empty] | W
Central Hudson |  | Trinity Solar | CH-08483 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 6062 | Inwood Ave | N |  | 11.4 | [13 empty] | NM | N | SOLAR EDGE 11400A-US | 2016-06-20 | 2016-07-01 | 9 | 2016-07-01 | [14 empty] | 2016-08-15 | 2016-08-23 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08678 | Poughkeepsie |  |  | 12601 | G | 6073 | East Park | TBD |  | 7.31 | [13 empty] | NM | N | 34 ENPHASE M215 602LLS22IG | 2016-06-20 | 2016-07-01 | 9 | 2016-07-01 | [17 empty] | W
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08827 | Kingston |  |  | 12449 | G | 2016 | Lincoln Park | TBD |  | 2.15 | [13 empty] | NM | N | ENPHASE M215 602LLS22IG (10) | 2016-06-20 | 2016-07-05 | 10 | 2016-07-05 | [17 empty] | W
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08838 | Poughkeepsie |  |  | 12571 | G | 7091 | Pulvers Corners | TBD |  | 4.3 | [13 empty] | NM | N | (20) ENPHASE M215 | 2016-06-20 | 2016-07-05 | 10 | 2016-07-05 | [17 empty] | W
Central Hudson |  | NRG Home Solar | CH-00518 | Newburgh | Newburgh | Orange | 12550 | G | 5004 | Marlboro | N |  | 5.59 | [13 empty] | NM | N | ENPHASE M215 (26) | 2016-06-21 | 2016-07-05 | 9 | 2016-07-05 | [14 empty] | 2016-09-14 | 2016-09-15 |  | Y
Central Hudson |  | Apex Solar Power | CH-00698 | Newburgh | Newburgh | Orange | 12550 | G | 4051 | Union Ave | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A-US | 2016-07-11 | 2016-07-20 | 7 | 2016-07-20 | [14 empty] | 2016-09-28 | 2016-10-11 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00915 | Kingston | Saugerties | Ulster | 12477 | G | 3003 | Saugerties | N |  | 5.81 | [13 empty] | NM | N | ENPHASE M215 60-2LL-S22 (27) | 2016-07-07 | 2016-07-07 | 0 | 2016-07-07 | [14 empty] | 2016-10-05 | 2016-10-17 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00925 | Kingston | Kingston | Ulster | 12401 | G | 1021 | East Kingston | N |  | 15.05 | [13 empty] | NM | N | ENPHASE M215 60-2LL-S22 (70) | 2016-06-21 | 2016-07-05 | 9 | 2016-07-05 | [14 empty] | 2016-08-23 | 2016-08-30 |  | Y
Central Hudson |  | SolarCity | CH-05677 | Kingston | W Hurley | Ulster | 12491 | G | 3013 | Woodstock | N |  | 7.2 | [13 empty] | NM | N | ABB PVI-3.6OUTD-S-US (2) | 2016-06-21 | 2016-07-05 | 9 | 2016-07-05 | [14 empty] | 2016-10-26 | 2016-11-01 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08680 | Poughkeepsie |  |  | 12580 | G | 7041 | Staatsburg | TBD |  | 1.72 | [13 empty] | NM | N | ENPHASE M215 602LLS22IG (8) | 2016-06-21 | 2016-07-06 | 10 | 2016-07-06 | [17 empty] | W
Central Hudson |  | New York State Solar Farm | CH-00413 | Newburgh | Wallkill | Ulster | 12589 | G | 5033 | Galeville | N |  | 7.6 | [13 empty] | NM | N | SMA AMERICA SB 3800TL (2) | 2016-06-22 | 2016-07-05 | 8 | 2016-07-05 | [14 empty] | 2016-07-21 | 2016-07-22 |  | Y
Central Hudson |  | SolarCity | CH-06165 | Newburgh | New Paltz | Ulster | 12561 | G | 5011 | Modena | N |  | 7.8 | [13 empty] | NM | N | ABB PVI 4.2 ABB PVI 3.6 | 2016-06-22 | 2016-07-05 | 8 | 2016-07-05 | [14 empty] | 2016-08-24 | 2016-08-24 |  | Y
Central Hudson |  | SolarCity | CH-06614 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6045 | Spackenkill | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2016-06-22 | 2016-07-07 | 10 | 2016-07-07 | [14 empty] | 2016-08-24 | 2016-08-25 |  | Y
Central Hudson |  | SolarCity | CH-07090 | Newburgh | Wallkill | Ulster | 12589 | G | 5041 | East Walden | N |  | 6 | [13 empty] | NM | N | ABB PVI 6000 | 2016-06-22 | 2016-07-05 | 8 | 2016-07-05 | [14 empty] | 2016-09-22 | 2016-09-22 |  | Y
Central Hudson |  | SolarCity | CH-07640 | Kingston | Kingston | Ulster | 12401 | G | 1022 | East Kingston | N |  | 5 | [13 empty] | NM | N | ABB PVI 5000 | 2016-07-26 | 2016-07-27 | 1 | 2016-07-27 | [14 empty] | 2016-10-18 | 2016-10-21 |  | Y
Central Hudson |  | SolarCity | CH-07880 | Poughkeepsie |  |  | 12540 | G | 6053 | Todd Hill | TBD |  | 6 | [13 empty] | NM | N | ABB PVI-6000OUTD-US | 2016-06-22 | 2016-07-07 | 10 | 2016-07-07 | [17 empty] | W
Central Hudson |  | Sunrise Solar Solutions, LLC | CH-09645 | Kingston | Kingston | Ulster | 12401 | G | 2012 | Lincoln Park | N |  | 166.5 | [13 empty] | CDG | N | SOLAREDGE SE33.3KUS (5) | 2016-07-22 | 2016-07-22 | 0 | 2016-07-22 | 2016-07-22 | 2016-08-09 | 12 | [11 empty] | 2016-11-01 | 2016-11-01 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-00197 | Newburgh | Montgomery | Orange | 12549 | G | 5073 | Montgomery | N |  | 11.52 | [13 empty] | NM | N | SUNPOWER SPR-E20-327 C-AC (36) | 2016-06-23 | 2016-07-05 | 7 | 2016-07-05 | [14 empty] | 2016-09-14 | 2016-09-15 |  | Y
Central Hudson |  | Lighthouse Solar | CH-00272 | Poughkeepsie | Stanfordvl | Dutchess | 12581 | G | 7072 | Stanfordville | N |  | 18 | [13 empty] | NM | N | SMA SB9000 TL-US (2) | 2016-07-07 | 2016-07-12 | 3 | 2016-07-12 | [14 empty] | 2016-11-04 | 2016-11-07 |  | Y
Central Hudson |  | PosiGen Solar | CH-02928 | Catskill |  |  | 12051 | G | 1076 | Coxsackie | TBD |  | 0.01 | [13 empty] | NM | N | ENPHASE ENERGY M215 (32) | 2016-06-23 | 2016-07-05 | 7 | 2016-07-05 | [17 empty] | W
Central Hudson |  | SolarCity | CH-07793 | Catskill | Hunter | Greene | 12442 | E | 2389 | Vinegar Hill | N |  | 3 | [13 empty] | NM | N | ABB PVI-3.0OUTD-S-US | 2016-08-03 | 2016-08-05 | 2 | 2016-08-05 | [14 empty] | 2016-10-18 | 2016-10-18 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Infinity Solar Systems | CH-00166 | Poughkeepsie | Staatsburg | Dutchess | 12580 | G | 7041 | Staatsburg | N |  | 5 | [13 empty] | NM | N | SMA AMERICA SB5000TL-US | 2016-06-24 | 2016-07-11 | 10 | 2016-07-11 | [14 empty] | 2016-08-30 | 2016-08-30 |  | Y
Central Hudson |  | SolarCity | CH-06247 | Newburgh | New Windsor | Orange | 12553 | G | 4044 | Union Ave | N |  | 4.2 | [13 empty] | NM | N | ABB PVI-4.2 OUTD-S-US | 2016-08-17 | 2016-08-22 | 3 | 2016-08-22 | [14 empty] | 2016-08-23 | 2016-08-23 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06485 | Kingston | Tillson | Ulster | 12486 | G | 3022 | High Falls | N |  | 12 | [13 empty] | NM | N | ABB PVI-6000OUTD-US (2) | 2016-06-24 | 2016-07-05 | 6 | 2016-07-05 | [14 empty] | 2016-08-04 | 2016-08-05 |  | Y
Central Hudson |  | SolarCity | CH-07342 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8043 | Myers Corners | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000 OUTD-US | 2016-08-10 | 2016-08-19 | 7 | 2016-08-19 | [14 empty] | 2016-09-22 | 2016-09-23 |  | Y
Central Hudson |  | SolarCity | CH-07437 | Newburgh | New Windsor | Orange | 12553 | G | 4044 | Union Ave | N |  | 12 | [13 empty] | NM | N | ABB PVI-6000 OUTD-US (2) | 2016-07-22 | 2016-07-29 | 5 | 2016-07-29 | [14 empty] | 2016-08-04 | 2016-08-11 |  | Y
Central Hudson |  | SolarCity | CH-07498 | Kingston | Kingston | Ulster | 12401 | G | 1011 | Boulevard | N |  | 3 | [13 empty] | NM | N | ABB PVI-3.0 OUTD-S-US | 2016-08-02 | 2016-08-05 | 3 | 2016-08-05 | [14 empty] | 2016-10-03 | 2016-10-04 |  | Y
Central Hudson |  | Trinity Solar | CH-08479 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6043 | Spackenkill | N |  | 5 | [13 empty] | NM | N | SOLAR EDGE SE5000A-US | 2016-06-24 | 2016-07-11 | 10 | 2016-07-11 | [14 empty] | 2016-12-28 | 2016-12-28 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08715 | Fishkill | Putnam Valley | Putnam | 10524 | G | 8066 | Merritt Park | N |  | 3.65 | [13 empty] | NM | N | ENPHASE M215 602LLS22IG (17) | 2016-07-15 | 2016-07-27 | 8 | 2016-07-27 | [14 empty] | 2016-11-22 | 2016-11-22 |  | Y
Central Hudson |  | Sungevity Inc | CH-09428 | Poughkeepsie | Lagrangevl | Dutchess | 12540 | G | 6057 | Todd Hill | N | CH-09428 | 4.2 | [13 empty] | NM | N | ABB PVI-4.2-OUTD-S-US-A | 2016-08-03 | 2016-08-15 | 8 | 2016-08-15 | [14 empty] | 2016-08-16 | 2016-08-24 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Solar Liberty Energy Systems | CH-04915 | Kingston |  |  | 12725 | G | 3091 | Neversink | TBD |  | 150 | [13 empty] | RNM | N | (6) Schneider Electric Context CL25000-NA | 2016-08-19 | 2016-08-24 | 3 | 2016-08-24 | 2016-08-24 | 2016-09-15 | 15 | [14 empty] | W
Central Hudson |  | Solar Liberty Energy Systems | CH-04916 | Kingston |  |  | 12725 | G | 3091 | Neversink | TBD |  | 350 | [13 empty] | CDG | N | (14) Schneider Electric Conext CL25000-NA | 2016-08-19 | 2016-08-24 | 3 | 2016-08-24 | 2016-08-24 | 2016-09-15 | 15 | [14 empty] | W
Central Hudson |  | SolarCity | CH-05295 | Newburgh | Wallkill | Ulster | 12589 | G | 4011 | West Balmville | N |  | 8.2 | [13 empty] | NM | N | FRONIUS PRIMO 8.2 | 2016-07-11 | 2016-07-19 | 6 | 2016-07-19 | [14 empty] | 2016-09-12 | 2016-09-28 |  | Y
Central Hudson |  | SolarCity | CH-06163 | Newburgh | New Paltz | Ulster | 12561 | G | 5011 | Modena | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2016-07-19 | 2016-07-28 | 7 | 2016-07-28 | [14 empty] | 2016-08-01 | 2016-08-01 |  | Y
Central Hudson |  | SolarCity | CH-06932 | Fishkill | Beacon | Dutchess | 12508 | G | 8017 | Forgebrook | N |  | 3 | [13 empty] | NM | N | ABB PVI-3.0 OUTD-S-US | 2016-07-27 | 2016-08-02 | 4 | 2016-08-02 | [14 empty] | 2016-08-09 | 2016-08-10 |  | Y
Central Hudson |  | SolarCity | CH-07428 | Newburgh | Newburgh | Orange | 12550 | G | 4012 | West Balmville | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2016-08-19 | 2016-08-23 | 2 | 2016-08-23 | [14 empty] | 2016-08-24 | 2016-08-31 |  | Y
Central Hudson |  | SolarCity | CH-07878 | Poughkeepsie |  |  | 12540 | G | 6057 | Todd Hill | TBD |  | 5 | [13 empty] | NM | N | ABB PVI-5000 OUTD-S-US | 2016-08-03 | 2016-08-15 | 8 | 2016-08-15 | [17 empty] | W
Central Hudson |  | US Energy Concierge, Inc. | CH-09750 | Newburgh | Rock Tvrn | Orange | 12575 | G | 4097 | Bethlehem Rd | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A-US | 2016-07-12 | 2016-07-20 | 6 | 2016-07-20 | [14 empty] | 2016-09-28 | 2016-09-28 |  | Y
Central Hudson |  | Apex Solar Power | CH-00013 | Kingston | Kerhonkson | Ulster | 12446 | G | 3071 | Honk Falls | N |  | 10 | [13 empty] | NM | N | SOLAREDGE SE10000A-US | 2016-07-06 | 2016-07-13 | 5 | 2016-07-13 | [8 empty] | 350 | 350 |  | 2016-07-15 | 2016-07-15 | 2016-08-02 | 2016-11-01 | 2016-11-02 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-00167 | Poughkeepsie | Lagrangevl | Dutchess | 12540 | G | 6057 | Todd Hill | N |  | 7.04 | [13 empty] | NM | N | SUNPOWER SPR-E20-327C-AC (22) | 2016-06-28 | 2016-07-11 | 8 | 2016-07-11 | [14 empty] | 2016-08-30 | 2016-09-07 |  | Y
Central Hudson |  | SolarCity | CH-07435 | Newburgh | Newburgh | Orange | 12550 | G | 4044 | Union Ave | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000 OUTD-US | 2016-11-09 | 2016-11-09 | 0 | 2016-11-09 | [14 empty] | 2016-11-17 | 2016-11-18 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08685 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7051 | Rhinebeck | N |  | 5.59 | [13 empty] | NM | N | ENPHASE M215602LLS22IG (26) | 2016-06-28 | 2016-07-11 | 8 | 2016-07-11 | [14 empty] | 2016-10-31 | 2016-11-14 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08787 | Kingston | Lk Katrine | Ulster | 12449 | G | 2016 | Lincoln Park | N |  | 7.955 | [13 empty] | NM | N | ENPHASE M215 602LLS22IG (37) | 2016-06-28 | 2016-07-06 | 5 | 2016-07-06 | [14 empty] | 2016-09-07 | 2016-09-09 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08805 | Kingston | Saugerties | Ulster | 12477 | G | 3001 | Saugerties | N |  | 10.53 | [13 empty] | NM | N | ENPHASE M215 602LLS22IG (49) | 2016-06-28 | 2016-07-06 | 5 | 2016-07-06 | [14 empty] | 2016-09-29 | 2016-10-06 |  | Y
Central Hudson |  | SolarCity | CH-05358 | Newburgh | Newburgh | Orange | 12550 | G | 4045 | Union Ave | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000 OUTD-US | 2016-09-19 | 2016-09-20 | 1 | 2016-09-20 | [14 empty] | 2016-09-27 | 2016-10-03 |  | Y
Central Hudson |  | SolarCity | CH-05820 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6061 | Inwood Ave | N |  | 4.2 | [13 empty] | NM | N | ABB PVI-4.2 OUTD-S-US | 2016-07-27 | 2016-08-01 | 3 | 2016-08-01 | [14 empty] | 2016-08-29 | 2016-09-06 |  | Y
Central Hudson |  | SolarCity | CH-06047 | Fishkill | Stormvl | Dutchess | 12582 | G | 8095 | Fishkill Plains | N |  | 8.2 | [13 empty] | NM | N | FRONIUS PRIMO 8.2 | 2016-08-23 | 2016-08-24 | 1 | 2016-08-24 | [14 empty] | 2016-08-29 | 2016-09-01 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08802 | Fishkill | Putnam Valley | Putnam | 10524 | G | 8066 | Merritt Park | N |  | 4.3 | [13 empty] | NM | N | ENPHASE M215 602LLS22IG (20) | 2016-07-26 | 2016-08-01 | 4 | 2016-08-01 | [14 empty] | 2017-01-30 | 2017-01-31 |  | Y
Central Hudson |  | NRG Home Solar | CH-00547 | Newburgh | Cornwall | Orange | 12518 | G | 4041 | Union Ave | N |  | 4.73 | [13 empty] | NM | N | ENPHASE M215 (22) | 2016-07-14 | 2016-07-26 | 8 | 2016-07-26 | [14 empty] | 2016-09-06 | 2016-09-15 |  | Y
Central Hudson |  | Direct Energy Solar | CH-01030 | Kingston | Hurley | Ulster | 12443 | G | 2094 | Hurley Ave | N |  | 7.5 | [13 empty] | NM | N | ENPHASEM250-60-2LL-S22 (30) | 2016-07-07 | 2016-07-07 | 0 | 2016-07-07 | [14 empty] | 2016-08-30 | 2016-08-31 |  | Y
Central Hudson |  | Hudson Solar | CH-01455 | Fishkill | Fishkill | Dutchess | 12524 | G | 8065 | Merritt Park | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE-7600A-US-U | 2016-07-22 | 2016-07-29 | 5 | 2016-07-29 | [14 empty] | 2016-10-03 | 2016-10-03 |  | Y
Central Hudson |  | Hudson Solar | CH-01989 | Newburgh | Montgomery | Orange | 12549 | G | 5072 | Montgomery | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE-5000 A-US-U | 2016-07-13 | 2016-07-22 | 7 | 2016-07-22 | [14 empty] | 2016-09-27 | 2016-10-11 |  | Y
Central Hudson |  | SolarCity | CH-05692 | Kingston | Kingston | Ulster | 12401 | G | 2093 | Hurley Ave | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2016-07-28 | 2016-07-29 | 1 | 2016-07-29 | [14 empty] | 2016-08-16 | 2016-08-22 |  | Y
Central Hudson |  | SolarCity | CH-05737 | Kingston | Saugerties | Ulster | 12477 | G | 3001 | Saugerties | N |  | 3 | [13 empty] | NM | N | ABB PVI-3.0 OUTD-S-US | 2016-09-02 | 2016-09-15 | 8 | 2016-09-15 | [14 empty] | 2016-11-03 | 2016-11-21 |  | Y
Central Hudson |  | SolarCity | CH-07510 | Kingston | Saugerties | Ulster | 12477 | G | 3001 | Saugerties | N |  | 3 | [13 empty] | NM | N | ABB PVI 3.0 | 2016-06-30 | 2016-07-06 | 3 | 2016-07-06 | [14 empty] | 2016-07-12 | 2016-07-21 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08631 | Fishkill | Putnam Valley | Putnam | 10524 | G | 8066 | Merritt Park | N |  | 4.73 | [13 empty] | NM | N | ENPHASE M215 602LLS22IG (22) | 2016-07-14 | 2016-07-26 | 8 | 2016-07-26 | [14 empty] | 2016-10-04 | 2016-10-04 |  | Y
Central Hudson |  | Hudson Solar | CH-01566 | Fishkill | Beacon | Dutchess | 12508 | G | 8017 | Forgebrook | N |  | 3 | [13 empty] | NM | N | SOLAREDGE SE-3000A-US-U | 2016-08-01 | 2016-08-01 | 0 | 2016-08-01 | [14 empty] | 2016-10-06 | 2016-10-14 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08714 | Fishkill | Garrison | Putnam | 10524 | G | 8066 | Merritt Park | N |  | 3.65 | [13 empty] | NM | N | ENPHASE M215 602LLS22IG (17) | 2016-07-18 | 2016-07-28 | 8 | 2016-07-28 | [14 empty] | 2016-10-04 | 2016-10-04 |  | Y
Central Hudson |  | Sol Providers | CH-08902 | Poughkeepsie | Millbrook | Dutchess | 12545 | G | 7012 | Hibernia | N |  | 13.44 | [13 empty] | RNM | N | SUNPOWER E20 327 (42) | 2016-07-18 | 2016-07-18 | 0 | 2016-07-18 | [14 empty] | 2016-07-21 | 2016-07-26 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Empire Solar Solutions | CH-00092 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 7024 | Tinkertown | N |  | 5 | [13 empty] | NM | N | SOLAREDGE 5000-AUS | 2016-08-04 | 2016-08-04 | 0 | 2016-08-04 | [14 empty] | 2016-08-05 | 2016-08-10 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-05361 | Newburgh | Wallkill | Ulster | 12589 | G | 5043 | East Walden | N |  | 7.5 | [13 empty] | NM | N | FRONIUS IB PLUS A 7.5 | 2016-11-03 | 2016-11-03 | 0 | 2016-11-03 | [14 empty] | 2016-11-29 | 2016-11-29 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-05704 | Kingston | Kingston | Ulster | 12401 | G | 2091 | Hurley Ave | N |  | 3.6 | [13 empty] | NM | N | ABB PVI-3.6 OUTD-S-US | 2016-07-27 | 2016-07-29 | 2 | 2016-07-29 | [14 empty] | 2016-09-14 | 2016-09-15 |  | Y
Central Hudson |  | SolarCity | CH-06655 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6003 | Reynolds Hill | N |  | 3 | [13 empty] | NM | N | SOLAREDGE SE3000A | 2016-08-25 | 2016-08-26 | 1 | 2016-08-26 | [14 empty] | 2016-11-10 | 2016-11-10 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07776 | Catskill | Cairo | Greene | 12413 | G | 2043 | South Cairo | N |  | 6.6 | [13 empty] | NM | N | ABB PVI-3.0OUTD-S-US ABB PVI-3.6OUTD-S-US | 2016-08-02 | 2016-08-05 | 3 | 2016-08-05 | [14 empty] | 2016-10-05 | 2016-10-10 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-00047 | Poughkeepsie | Millbrook | Dutchess | 12545 | G | 7012 | Hibernia | N |  | 3.8 | [13 empty] | NM | N | SOLAREDGE 3800AUS | 2016-10-21 | 2016-11-02 | 8 | 2016-11-02 | [14 empty] | 2016-11-02 | 2016-11-02 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Empire Solar Solutions | CH-00078 | Poughkeepsie | Salt Pt | Dutchess | 12578 | G | 7011 | Hibernia | N |  | 10 | [13 empty] | NM | N | SOLAREDGE 10000AUS | 2016-07-06 | 2016-07-12 | 4 | 2016-07-12 | [14 empty] | 2016-08-03 | 2016-08-10 |  | Y
Central Hudson |  | Lighthouse Solar | CH-00300 | Kingston | Kerhonkson | Ulster | 12446 | G | 3082 | Kerhonkson | N | CH-00300 | 7.6 | [13 empty] | NM | N | SOLAREDGE 7600 A-US | 2016-07-06 | 2016-07-07 | 1 | 2016-07-07 | [14 empty] | 2016-09-08 | 2016-09-08 |  | Y
Central Hudson |  | Lighthouse Solar | CH-00302 | Kingston | Hurley | Ulster | 12443 | G | 2094 | Hurley Ave | N |  | 6 | [13 empty] | NM | N | SOLAREDGE 6000A | 2016-07-06 | 2016-07-07 | 1 | 2016-07-07 | [14 empty] | 2016-10-14 | 2016-10-19 |  | Y
Central Hudson |  | Lighthouse Solar | CH-00326 | Kingston | Saugerties | Ulster | 12477 | G | 3002 | Saugerties | N |  | 6 | [13 empty] | NM | N | SOLAREDGE 6000 A-US | 2016-07-06 | 2016-07-07 | 1 | 2016-07-07 | [14 empty] | 2016-09-21 | 2016-09-28 |  | Y
Central Hudson |  | NRG Home Solar | CH-00543 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 5.16 | [13 empty] | NM | N | ENPHASE M215 (24) | 2016-07-26 | 2016-08-01 | 4 | 2016-08-01 | [14 empty] | 2016-09-08 | 2016-09-22 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00936 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7051 | Rhinebeck | N |  | 6.75 | [13 empty] | NM | N | ENPHASE M250 S22 (27) | 2016-07-06 | 2016-07-12 | 4 | 2016-07-12 | [14 empty] | 2016-10-06 | 2016-10-10 |  | Y
Central Hudson |  | Trinity Solar | CH-08512 | Newburgh | Newburgh | Orange | 12550 | G | 410 | Montgomery St | N |  | 3.8 | [13 empty] | NM | N | SOLAR EDGE SE3800A-US | 2016-07-06 | 2016-07-14 | 6 | 2016-07-14 | [14 empty] | 2016-09-26 | 2016-10-03 |  | Y
Central Hudson |  | Green Street Power Partners, LLC | CH-00111 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 6075 | East Park | N |  | 3 | [13 empty] | NM | N | SMA SB3000TL-US | 2016-08-08 | 2016-08-18 | 8 | 2016-08-18 | [14 empty] | 2016-09-21 | 2016-09-22 |  | Y
Central Hudson |  | Lighthouse Solar | CH-00303 | Kingston | Port Ewen | Ulster | 12466 | G | 1012 | Boulevard | N |  | 3 | [13 empty] | NM | N | SOLAREDGE SE3000 A-US | 2016-07-07 | 2016-07-08 | 1 | 2016-07-08 | [14 empty] | 2016-10-17 | 2016-10-17 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03737 | Kingston | Saugerties | Ulster | 12477 | G | 3001 | Saugerties | N |  | 6 | [13 empty] | NM | N | SOLAREDGE 6000A-US | 2016-07-07 | 2016-07-07 | 0 | 2016-07-07 | [14 empty] | 2016-08-30 | 2016-08-30 |  | Y
Central Hudson |  | Lighthouse Solar | CH-00307 | Newburgh | Highland | Ulster | 12528 | G | 5084 | Highland | N |  | 5 | [13 empty] | NM | N | SOLAREDGE 5000A-US | 2016-07-07 | 2016-07-12 | 3 | 2016-07-12 | [14 empty] | 2016-09-01 | 2016-09-14 |  | Y
Central Hudson |  | Lighthouse Solar | CH-00311 | Kingston | Shokan | Ulster | 12481 | G | 3011 | Woodstock | N |  | 5 | [13 empty] | NM | N | SOLAREDGE 5000 A-US | 2016-07-07 | 2016-07-08 | 1 | 2016-07-08 | [14 empty] | 2016-10-31 | 2016-10-31 |  | Y
Central Hudson |  | Lighthouse Solar | CH-00320 | Kingston | Saugerties | Ulster | 12477 | G | 3003 | Saugerties | N |  | 3 | [13 empty] | NM | N | SOLAREDGE 3000A-US | 2016-07-07 | 2016-07-08 | 1 | 2016-07-08 | [14 empty] | 2016-09-08 | 2016-09-09 |  | Y
Central Hudson |  | Kool-Temp | CH-02576 | Catskill | Greenville | Greene | 12083 | G | 2061 | Freehold | N |  | 3.8 | [13 empty] | NM | N | FRONIUS PRIMO 3.8 | 2016-07-12 | 2016-07-12 | 0 | 2016-07-12 | [14 empty] | 2016-08-10 | 2016-08-15 |  | Y
Central Hudson |  | SolarCity | CH-05062 | Newburgh | Wallkill | Ulster | 12589 | G | 5041 | East Walden | N |  | 6 | [13 empty] | NM | N | ABB PVI 6000 | 2016-10-25 | 2016-10-25 | 0 | 2016-10-25 | [14 empty] | 2016-12-05 | 2016-12-13 |  | Y
Central Hudson |  | Viking Solar Inc | CH-09938 | Catskill | Westerlo | Albany | 12193 | G | 1091 | Westerlo | N |  | 7.2 | [13 empty] | NM | N | OUTBACK GVFX 3648 (2) | 2016-07-29 | 2016-08-09 | 7 | 2016-08-09 | [14 empty] | 2016-08-08 | 2016-08-15 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Apex Solar Power | CH-00691 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7061 | Milan | N | CH-00691 | 3 | [13 empty] | NM | N | SOLAREDGE SE3000A-US | 2016-07-12 | 2016-07-12 | 0 | 2016-07-12 | [14 empty] | 2016-08-16 | 2016-08-18 |  | Y
Central Hudson |  | SolarCity | CH-05242 | Kingston | Kerhonkson | Ulster | 12446 | G | 3081 | Kerhonkson | N |  | 6 | [13 empty] | NM | N | ABB PVI 6000 | 2016-07-21 | 2016-07-25 | 2 | 2016-07-25 | [14 empty] | 2016-10-17 | 2016-10-19 |  | Y
Central Hudson |  | SolarCity | CH-07251 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6046 | Spackenkill | N |  | 6 | [13 empty] | NM | N | ABB PVI 6000 | 2016-07-15 | 2016-07-15 | 0 | 2016-07-15 | [14 empty] | 2016-07-28 | 2016-07-28 |  | Y
Central Hudson |  | SolarCity | CH-07760 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6065 | Inwood Ave | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2016-07-25 | 2016-07-26 | 1 | 2016-07-26 | [14 empty] | 2016-11-15 | 2016-11-15 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08682 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7056 | Rhinebeck | N |  | 6.23 | [13 empty] | NM | N | ENPHASE M215602LLS22IG (29) | 2016-07-08 | 2016-07-12 | 2 | 2016-07-12 | [14 empty] | 2016-10-13 | 2016-10-18 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08712 | Fishkill | Putnam Valley | Putnam | 10524 | G | 8066 | Merritt Park | N |  | 4.94 | [13 empty] | NM | N | ENPHASE M215 602LLS22IG (23) | 2016-07-08 | 2016-07-19 | 7 | 2016-07-19 | [14 empty] | 2016-10-04 | 2016-10-04 |  | Y
Central Hudson |  | Kasselman Solar | CH-00257 | Catskill | Ravena | Albany | 12143 | G | 1081 | New Baltimore | N | CH-03523 | 3.36 | [13 empty] | NM | N | ENPHASE ENERGY S280 (12) | 2016-07-14 | 2016-07-14 | 0 | 2016-07-14 | [14 empty] | 2016-09-30 | 2016-10-03 |  | Y
Central Hudson |  | NRG Home Solar | CH-00487 | Kingston | Saugerties | Ulster | 12477 | G | 3004 | Saugerties | N |  | 6.02 | [13 empty] | NM | N | ENPHASE M215 (28) | 2016-07-13 | 2016-07-13 | 0 | 2016-07-13 | [14 empty] | 2016-10-11 | 2016-10-14 |  | Y
Central Hudson |  | Murphy Solar Power | CH-02742 | Catskill | Earlton | Greene | 12058 | G | 2071 | Freehold | N |  | 3.8 | [13 empty] | NM | N | Fronius Primo 3800 | 2016-09-06 | 2016-09-06 | 0 | 2016-09-06 | [14 empty] | 2016-09-30 | 2016-10-04 |  | Y
Central Hudson |  | SolarCity | CH-05416 | Kingston | Kingston | Ulster | 12401 | G | 1024 | East Kingston | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000OUTD-US | 2016-09-06 | 2016-09-06 | 0 | 2016-09-06 | [14 empty] | 2016-09-07 | 2016-09-16 |  | Y
Central Hudson |  | SolarCity | CH-05971 | Poughkeepsie | Millerton | Dutchess | 12546 | G | 7081 | Millerton | N |  | 5 | [13 empty] | NM | N | ABB PVI-5000 OUTD-US | 2016-08-02 | 2016-08-05 | 3 | 2016-08-05 | [14 empty] | 2016-08-24 | 2016-08-25 |  | Y
Central Hudson |  | SolarCity | CH-07032 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 7.2 | [13 empty] | NM | N | ABB PVI-3.6OUTD-S-US (2) | 2016-08-23 | 2016-08-24 | 1 | 2016-08-24 | [14 empty] | 2016-08-29 | 2016-09-07 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07194 | Catskill | W Coxsackie | Greene | 12192 | G | 1071 | Coxsackie | N |  | 17.6 | [13 empty] | NM | N | SOLAREDGE SE10000A SOLAREDGE SE7600A | 2016-07-26 | 2016-07-26 | 0 | 2016-07-26 | [8 empty] | 350 | 350 |  | 2016-08-18 | 2016-08-18 | 2016-08-26 | 2016-08-26 | 2016-09-20 |  | Y
Central Hudson |  | SolarCity | CH-07302 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6056 | Todd Hill | N |  | 3.6 | [13 empty] | NM | N | ABB PVI-3.6OUTD-S-US | 2016-08-02 | 2016-08-05 | 3 | 2016-08-05 | [14 empty] | 2016-08-24 | 2016-08-31 |  | Y
Central Hudson |  | SolarCity | CH-07399 | Fishkill | Beacon | Dutchess | 12508 | G | 8017 | Forgebrook | N |  | 4.2 | [13 empty] | NM | N | ABB PVI-4.2OUTD-S-US | 2016-08-02 | 2016-08-05 | 3 | 2016-08-05 | [14 empty] | 2016-08-12 | 2016-08-16 |  | Y
Central Hudson |  | SolarCity | CH-07688 | Newburgh | Maybrook | Orange | 12543 | G | 4026 | Coldenham | N |  | 5 | [13 empty] | NM | N | ABB PVI-5000OUTD-US | 2016-08-10 | 2016-08-19 | 7 | 2016-08-19 | [14 empty] | 2016-09-12 | 2016-09-13 |  | Y
Central Hudson |  | Sunrun Inc. | CH-08337 | Newburgh | Newburgh | Orange | 12550 | G | 5001 | Marlboro | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000-OUTD-US-A | 2016-08-05 | 2016-08-17 | 8 | 2016-08-17 | [14 empty] | 2016-09-21 | 2016-09-22 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-00199 | Newburgh | New Windsor | Orange | 12553 | G | 4095 | Bethlehem Rd | N |  | 5.12 | [13 empty] | NM | N | SUNPOWER SPR-E20-327 (16) | 2016-07-12 | 2016-07-20 | 6 | 2016-07-20 | [14 empty] | 2016-09-28 | 2016-10-03 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-00223 | Newburgh |  |  | 12553 | G | 4094 | Bethlehem Rd | TBD |  | 11.2 | [13 empty] | NM | N | SUNPOWER SPR-E20-327 (35) | 2016-08-02 | 2016-08-02 | 0 | 2016-08-02 | [17 empty] | W
Central Hudson |  | New York State Solar Farm | CH-00373 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8095 | Fishkill Plains | N |  | 10.7 | [13 empty] | NM | N | SMA AMERICASB3000TL SMA AMERICASB7700TL | 2016-07-12 | 2016-07-20 | 6 | 2016-07-20 | [14 empty] | 2016-08-18 | 2016-08-19 |  | Y
Central Hudson |  | PosiGen Solar | CH-02911 | Poughkeepsie | Clinton Corners | Dutchess | 12514 | G | 7071 | Stanfordville | N |  | 6.88 | [13 empty] | NM | N | ENPHASE M215-60-2LL-S22-IG (32) | 2016-07-13 | 2016-07-13 | 0 | 2016-07-13 | [14 empty] | 2016-07-27 | 2016-07-27 |  | Y
Central Hudson |  | Solar Liberty Energy Systems | CH-04922 | Catskill | Coxsackie | Greene | 12051 | G | 1071 | Coxsackie | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE 7600US | 2016-07-13 | 2016-07-14 | 1 | 2016-07-14 | [14 empty] | 2016-08-23 | 2016-08-26 |  | Y
Central Hudson |  | SolarCity | CH-05838 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 6074 | East Park | N |  | 7.2 | [13 empty] | NM | N | ABB PVI-4.2 OUTD-S-US ABB PVI-3.0 OUTD-S-US | 2016-08-25 | 2016-08-26 | 1 | 2016-08-26 | [14 empty] | 2016-10-18 | 2016-10-18 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06249 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 3.6 | [13 empty] | NM | N | ABB PVI-3.6 OUTD-S-US | 2016-08-23 | 2016-08-24 | 1 | 2016-08-24 | [14 empty] | 2016-08-29 | 2016-08-29 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07393 | Fishkill | Beacon | Dutchess | 12508 | G | 8017 | Forgebrook | N |  | 3 | [13 empty] | NM | N | ABB PVI-3.0OUTD-S-US | 2016-08-17 | 2016-08-22 | 3 | 2016-08-22 | [14 empty] | 2016-08-24 | 2016-09-01 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07431 | Newburgh | Newburgh | Orange | 12550 | G | 4051 | Union Ave | N |  | 8.2 | [13 empty] | NM | N | FRONIUS PRIMO 8.2 | 2016-08-25 | 2016-08-26 | 1 | 2016-08-26 | [14 empty] | 2016-08-30 | 2016-09-06 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Empire Solar Solutions | CH-00096 | Newburgh | New Windsor | Orange | 12553 | G | 4095 | Bethlehem Rd | N |  | 5 | [13 empty] | NM | N | SOLAREDGE 5000-AUS | 2016-07-13 | 2016-07-25 | 8 | 2016-07-25 | [14 empty] | 2016-08-25 | 2016-08-26 |  | Y
Central Hudson |  | Lighthouse Solar | CH-00291 | Kingston | Woodstock | Ulster | 12498 | G | 3014 | Woodstock | N |  | 6 | [13 empty] | NM | N | SOLAREDGE 6000A-US | 2016-07-13 | 2016-07-13 | 0 | 2016-07-13 | [14 empty] | 2016-10-07 | 2016-10-10 |  | Y
Central Hudson |  | Lighthouse Solar | CH-00298 | Newburgh | Campbell Hall | Orange | 10916 | G | 5051 | Maybrook | N |  | 37.5 | [13 empty] | NM | N | FRONIUS PRIMO12.5-1 (3) | 2016-07-26 | 2016-08-09 | 10 | 2016-08-09 | [8 empty] | 2996.87 | 2007.05 |  | 2016-09-15 | 2016-09-15 | 2016-11-29 | 2016-12-14 | 2016-12-16 |  | Y
Central Hudson |  | Lighthouse Solar | CH-00299 | Newburgh | Campbell Hall | Orange | 10916 | G | 5051 | Maybrook | N |  | 37.5 | [13 empty] | NM | N | FRONIUS PRIMO 12.5-1 (3) | 2016-07-26 | 2016-08-09 | 10 | 2016-08-09 | [8 empty] | 2996.87 | 2007.04 |  | 2016-09-15 | 2016-09-15 | 2016-11-29 | 2016-12-14 | 2016-12-16 |  | Y
Central Hudson |  | Lighthouse Solar | CH-00305 | Kingston | Malden-Hdsn | Ulster | 12453 | G | 3004 | Saugerties | N |  | 3 | [13 empty] | NM | N | SOLAREDGE 3000A-US | 2016-07-14 | 2016-07-15 | 1 | 2016-07-15 | [14 empty] | 2016-09-14 | 2016-09-15 |  | Y
Central Hudson |  | Lighthouse Solar | CH-00323 | Kingston | Kingston | Ulster | 12401 | G | 2094 | Hurley Ave | N |  | 3 | [13 empty] | NM | N | SOLAREDGE 3000A-US | 2016-07-13 | 2016-07-13 | 0 | 2016-07-13 | [14 empty] | 2016-09-19 | 2016-10-05 |  | Y
Central Hudson |  | New York State Solar Farm | CH-00396 | Poughkeepsie | Stanfordvl | Dutchess | 12581 | G | 7072 | Stanfordville | N |  | 7.68 | [13 empty] | NM | N | SUNPOWER SPR-E20 327-C-AC (24) | 2016-07-13 | 2016-07-13 | 0 | 2016-07-13 | [14 empty] | 2016-08-26 | 2016-08-26 |  | Y
Central Hudson |  | New York State Solar Farm | CH-00411 | Newburgh | Marlboro | Ulster | 12542 | G | 5004 | Marlboro | N |  | 10.24 | [13 empty] | NM | N | SUNPOWER SPR-E20327-C-AC (32) | 2016-07-13 | 2016-07-25 | 8 | 2016-07-25 | [14 empty] | 2016-08-23 | 2016-08-24 |  | Y
Central Hudson |  | New York State Solar Farm | CH-00417 | Catskill | Catskill | Greene | 12414 | G | 2001 | North Catskill | N |  | 9.6 | [13 empty] | NM | N | SUNPOWER SPR-E20 327-C-AC (30) | 2016-07-13 | 2016-07-13 | 0 | 2016-07-13 | [14 empty] | 2016-09-26 | 2016-10-06 |  | Y
Central Hudson |  | NRG Home Solar | CH-00493 | Newburgh | Walden | Orange | 12586 | G | 5041 | East Walden | N |  | 3.87 | [13 empty] | NM | N | ENPHASE M215 (18) | 2016-07-13 | 2016-07-22 | 7 | 2016-07-22 | [14 empty] | 2016-10-14 | 2016-10-21 |  | Y
Central Hudson |  | NRG Home Solar | CH-00545 | Newburgh | Marlboro | Ulster | 12542 | G | 5002 | Marlboro | N |  | 6.88 | [13 empty] | NM | N | ENPHASE M215 (32) | 2016-07-13 | 2016-07-25 | 8 | 2016-07-25 | [14 empty] | 2016-10-14 | 2016-10-17 |  | Y
Central Hudson |  | Solar Generation | CH-08276 | Kingston | Saugerties | Ulster | 12477 | G | 3001 | Saugerties | N |  | 10 | [13 empty] | NM | N | SMA SB 7000 SMA SB 3000 | 2016-07-18 | 2016-07-21 | 3 | 2016-07-21 | [14 empty] | 2016-08-01 | 2016-08-02 |  | Y
Central Hudson |  | Hudson Solar | CH-02182 | Fishkill | Cold Spg | Putnam | 10516 | G | 8087 | Tioronda | N |  | 3.8 | [13 empty] | NM | N | SOLAREDGE SE-3800A-US-U | 2016-07-14 | 2016-07-26 | 8 | 2016-07-26 | [14 empty] | 2016-10-06 | 2016-10-10 |  | Y
Central Hudson |  | Hudson Solar | CH-02206 | Newburgh | Marlboro | Ulster | 12542 | G | 5003 | Marlboro | N | CH-02206 | 6 | [13 empty] | NM | N | SOLAREDGE SE-6000A-US-U | 2016-07-14 | 2016-07-26 | 8 | 2016-07-26 | [14 empty] | 2016-09-30 | 2016-10-03 |  | Y
Central Hudson |  | Hudson Solar | CH-02221 | Newburgh | Montgomery | Orange | 12549 | G | 5073 | Montgomery | N | CH-02221 | 10 | [13 empty] | NM | N | SOLAREDGE SE-10000A-US-U | 2016-07-14 | 2016-07-26 | 8 | 2016-07-26 | [14 empty] | 2016-09-23 | 2016-09-26 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08710 | Fishkill | Putnam Valley | Putnam | 10524 | G | 8066 | Merritt Park | N |  | 6.66 | [13 empty] | NM | N | ENPHASE M215 602LLS22IG (31) | 2016-07-14 | 2016-07-26 | 8 | 2016-07-26 | [14 empty] | 2017-01-03 | 2017-01-03 |  | Y
Central Hudson |  | You Save Green | CH-09966 | Newburgh | New Windsor | Orange | 12553 | G | 4095 | Bethlehem Rd | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE STOREDGE SE7600A | 2016-08-05 | 2016-08-17 | 8 | 2016-08-17 | [14 empty] | 2016-10-14 | 2016-10-17 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-00170 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8091 | Fishkill Plains | N |  | 11.84 | [13 empty] | NM | N | SUNPOWER SPR-E20-327 C-AC (37) | 2016-07-15 | 2016-07-27 | 8 | 2016-07-27 | [14 empty] | 2016-09-22 | 2016-09-26 |  | Y
Central Hudson |  | Lighthouse Solar | CH-00269 | Kingston | Glenford | Ulster | 12433 | G | 3013 | Woodstock | N |  | 5 | [13 empty] | NM | N | SOLAREDGE 5000A-US | 2016-07-15 | 2016-07-18 | 1 | 2016-07-18 | [14 empty] | 2016-09-02 | 2016-09-15 |  | Y
Central Hudson |  | Hudson Solar | CH-01331 | Poughkeepsie | Tivoli | Dutchess | 12583 | G | 7062 | Milan | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE-7600A-US-U | 2016-07-15 | 2016-07-18 | 1 | 2016-07-18 | [14 empty] | 2016-10-31 | 2016-11-04 |  | Y
Central Hudson |  | Hudson Solar | CH-01496 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7055 | Rhinebeck | N |  | 3.8 | [13 empty] | NM | N | SOLAREDGE SE-3800A-US-U | 2016-07-15 | 2016-07-15 | 0 | 2016-07-15 | [14 empty] | 2016-10-05 | 2016-10-07 |  | Y
Central Hudson |  | Hudson Solar | CH-01867 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7062 | Milan | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE-5000A-US-U | 2016-07-15 | 2016-07-15 | 0 | 2016-07-15 | [14 empty] | 2016-09-26 | 2016-09-28 |  | Y
Central Hudson |  | Hudson Solar | CH-02222 | Newburgh | Montgomery | Orange | 12549 | G | 5073 | Montgomery | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE-6000 A-US-U | 2016-08-04 | 2016-08-16 | 8 | 2016-08-16 | [14 empty] | 2016-09-23 | 2016-10-04 |  | Y
Central Hudson |  | Trinity Solar | CH-08435 | Fishkill | Beacon | Dutchess | 12508 | G | 8013 | Forgebrook | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A-US | 2016-07-15 | 2016-07-27 | 8 | 2016-07-27 | [14 empty] | 2016-09-13 | 2016-09-13 |  | Y
Central Hudson |  | Sungevity Inc | CH-09260 | Catskill | Greenvl | Greene | 12083 | G | 2061 | Freehold | N |  | 3 | [13 empty] | NM | N | ABB PVI-3.0-OUTD-S-US-A | 2016-07-20 | 2016-07-25 | 3 | 2016-07-25 | [14 empty] | 2016-09-19 | 2016-09-19 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-03336 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7062 | Milan | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE 7600A US | 2016-07-18 | 2016-07-21 | 3 | 2016-07-21 | [14 empty] | 2016-08-09 | 2016-08-10 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00884 | Catskill |  |  | 12414 | G | 2001 | North Catskill | TBD |  | 5.16 | [13 empty] | NM | N | ENPHASE M215 60-2LL-S22 (24) | 2016-07-18 | 2016-07-21 | 3 | 2016-07-21 | [17 empty] | W
Central Hudson |  | SolarCity | CH-07531 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 6074 | East Park | N | CH-07531 | 6 | [13 empty] | NM | N | ABB PPVI-6000OUTD-S-US | 2016-07-26 | 2016-07-26 | 0 | 2016-07-26 | [14 empty] | 2016-08-24 | 2016-08-25 |  | Y
Central Hudson |  | Trinity Solar | CH-08420 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6093 | Manchester | N |  | 5 | [13 empty] | NM | N | SOLAR EDGE SE5000A-US | 2016-07-18 | 2016-07-26 | 6 | 2016-07-26 | [14 empty] | 2016-09-09 | 2016-09-13 |  | Y
Central Hudson |  | Trinity Solar | CH-08577 | Catskill |  |  | 12418 | G | 2043 | South Cairo | TBD |  | 7.6 | [13 empty] | NM | N | SOLAR EDGE SE7600A-US | 2016-07-18 | 2016-07-26 | 6 | 2016-07-26 | [17 empty] | W
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08668 | Kingston | Saugerties | Ulster | 12477 | G | 3004 | Saugerties | N | CH-22963 | 4.73 | [13 empty] | NM | N | ENPHASE M215 602LLS22IG (25) | 2016-07-18 | 2016-08-01 | 10 | 2016-08-01 | [14 empty] | 2016-10-10 | 2016-10-14 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08770 | Fishkill | Garrison | Putnam | 10524 | G | 8066 | Merritt Park | N |  | 4.73 | [13 empty] | NM | N | ENPHASE M215 602LLS22IG (22) | 2016-07-18 | 2016-07-28 | 8 | 2016-07-28 | [14 empty] | 2016-10-05 | 2016-10-06 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-00100 | Newburgh | New Paltz | Ulster | 12561 | G | 5023 | Ohioville | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE 7600AUS | 2016-07-19 | 2016-07-28 | 7 | 2016-07-28 | [8 empty] | 350 | 350 |  | 2016-08-15 | 2016-08-15 | 2016-09-05 | 2016-08-09 | 2016-09-14 |  | Y
Central Hudson |  | New York State Solar Farm | CH-00434 | Newburgh | New Paltz | Ulster | 12561 | G | 5024 | Ohioville | N |  | 6 | [13 empty] | NM | N | SMA AMERICA SB6000TL | 2016-08-03 | 2016-08-15 | 8 | 2016-08-15 | [14 empty] | 2016-08-30 | 2016-08-30 |  | Y
Central Hudson |  | Monolith Solar Associates LLC | CH-02643 | Catskill | Coeymans Hollow | Albany | 12046 | G | 1071 | Coxsackie | N |  | 7.6 | [13 empty] | NM | N | SOLAR EDGE SE7600-A-US | 2016-07-26 | 2016-07-26 | 0 | 2016-07-26 | [14 empty] | 2016-10-03 | 2016-10-03 |  | Y
Central Hudson |  | SolarCity | CH-05212 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8092 | Fishkill Plains | N |  | 6 | [13 empty] | NM | N | ABB PVI 6000 | 2016-07-29 | 2016-08-04 | 4 | 2016-08-04 | [14 empty] | 2016-08-31 | 2016-08-31 |  | Y
Central Hudson |  | SolarCity | CH-07500 | Kingston | Kingston | Ulster | 12401 | G | 2017 | Lincoln Park | N |  | 7.6 | [13 empty] | NM | N | FRONIUS 7.6 | 2016-07-19 | 2016-07-21 | 2 | 2016-07-21 | [14 empty] | 2016-07-25 | 2016-07-25 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | New York State Solar Farm | CH-03987 | Newburgh | Highland | Ulster | 12528 | G | 5022 | Ohioville | N |  | 3.8 | [13 empty] | NM | N | SMA AMERICA 3.80 | 2016-07-26 | 2016-07-27 | 1 | 2016-07-27 | [14 empty] | 2016-09-08 | 2016-09-09 |  | Y
Central Hudson |  | New York State Solar Farm | CH-00437 | Newburgh | Newburgh | Orange | 12550 | G | 4015 | West Balmville | N |  | 7.68 | [13 empty] | NM | N | SUNPOWER SPR-E20 327-C-AC (24) | 2016-07-20 | 2016-07-28 | 6 | 2016-07-28 | [14 empty] | 2016-09-19 | 2016-09-26 |  | Y
Central Hudson |  | Burke Electric and Solar | CH-00767 | Kingston |  |  | 12487 | G | 1014 | Boulevard | TBD |  | 999 | [13 empty] | CDG | N | SOLAREDGE SE33.3KUS (30) | 2016-10-24 | 2016-11-07 | 10 | 2016-11-07 | 2016-11-07 | 2016-11-29 | 14 |  |  |  |  | 32000 | [9 empty] | W
Central Hudson |  | Direct Energy Solar | CH-01032 | Kingston | Hurley | Ulster | 12443 | G | 2094 | Hurley Ave | N |  | 13.33 | [13 empty] | NM | N | ENPHASE M215 (62) | 2016-07-20 | 2016-07-25 | 3 | 2016-07-25 | [14 empty] | 2016-09-26 | 2016-09-28 |  | Y
Central Hudson |  | SolarCity | CH-06444 | Catskill | Cairo | Greene | 12413 | G | 2043 | South Cairo | N |  | 6 | [13 empty] | NM | N | ABB PVI 6000 | 2016-07-20 | 2016-07-22 | 2 | 2016-07-22 | [8 empty] | 350 | 350 |  | 2016-08-18 | 2016-08-18 | 2016-08-23 | 2016-08-29 | 2016-08-29 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08674 | Kingston | Lk Katrine | Ulster | 12449 | G | 2016 | Lincoln Park | N |  | 13.54 | [13 empty] | NM | N | ENPHASE M215 602LLS22IG (63) | 2016-07-20 | 2016-07-22 | 2 | 2016-07-22 | [14 empty] | 2016-12-07 | 2016-12-07 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-00184 | Fishkill | Beacon | Dutchess | 12508 | G | 8017 | Forgebrook | N |  | 3.84 | [13 empty] | NM | N | SUNPOWER SPR-X21-335-BLK (12) | 2016-07-21 | 2016-07-29 | 6 | 2016-07-29 | [14 empty] | 2016-10-14 | 2016-10-19 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-00224 | Newburgh |  |  | 12553 | G | 4094 | Bethlehem Rd | TBD |  | 10.24 | [13 empty] | NM | N | SUNPOWER SPR-X21-335-BLK (32) | 2016-07-29 | 2016-07-29 | 0 | 2016-07-29 | [17 empty] | W
Central Hudson |  | NRG Home Solar | CH-00528 | Kingston | Kingston | Ulster | 12401 | G | 1003 | Jansen Ave | N |  | 3.87 | [13 empty] | NM | N | ENPHASE M215 (18) | 2016-07-21 | 2016-07-25 | 2 | 2016-07-25 | [14 empty] | 2017-01-23 | 2017-01-27 |  | Y
Central Hudson |  | SolarCity | CH-05175 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8052 | North Chelsea | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2016-08-01 | 2016-08-05 | 4 | 2016-08-05 | [14 empty] | 2016-08-24 | 2016-08-25 |  | Y
Central Hudson |  | SolarCity | CH-06521 | Kingston | Ulster Pk | Ulster | 12487 | G | 1014 | Boulevard | N |  | 12 | [13 empty] | NM | N | ABB PVI 6000 (2) | 2016-07-21 | 2016-07-25 | 2 | 2016-07-25 | [14 empty] | 2016-08-31 | 2016-08-31 |  | Y
Central Hudson |  | SolarCity | CH-07662 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8046 | Myers Corners | N |  | 4.2 | [13 empty] | NM | N | ABB PVI 4.2 | 2016-07-29 | 2016-08-02 | 2 | 2016-08-02 | [14 empty] | 2016-08-10 | 2016-08-15 |  | Y
Central Hudson |  | Solar Alchemy | CH-08984 | Kingston | Kerhonkson | Ulster | 12446 | G | 3083 | Kerhonkson | N |  | 12.32 | [13 empty] | NM | N | ENPHASE S28060-LL-5-US (44) | 2016-10-06 | 2016-10-07 | 1 | 2016-10-07 | [14 empty] | 2016-11-15 | 2016-11-15 |  | Y
Central Hudson |  | Solar Alchemy | CH-08987 | Fishkill | Fishkill | Dutchess | 12524 | G | 8065 | Merritt Park | N |  | 9 | [13 empty] | NM | N | ENPHASE M250 60-2LL-S24 (36) | 2016-07-29 | 2016-08-04 | 4 | 2016-08-04 | [14 empty] | 2016-09-20 | 2016-09-22 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-00081 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7053 | Rhinebeck | N |  | 3.8 | [13 empty] | NM | N | SOLAREDGE 3800A US | 2016-07-22 | 2016-07-26 | 2 | 2016-07-26 | [14 empty] | 2016-08-03 | 2016-08-05 |  | Y
Central Hudson |  | Hudson Solar | CH-02070 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6062 | Inwood Ave | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE-5000A-US | 2016-07-22 | 2016-07-26 | 2 | 2016-07-26 | [14 empty] | 2016-10-13 | 2016-10-17 |  | Y
Central Hudson |  | Hudson Solar | CH-02362 | Kingston | High Fls | Ulster | 12440 | G | 3022 | High Falls | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE-7600 A-US | 2016-07-22 | 2016-07-26 | 2 | 2016-07-26 | [14 empty] | 2016-10-07 | 2016-10-14 |  | Y
Central Hudson |  | Sunrun Inc. | CH-08326 | Newburgh | Rock Tavern | Orange | 12575 | G | 4097 | Bethlehem Rd | N |  | 9.6 | [13 empty] | NM | N | ABB PVI-3.6-OUTD-S-US-A ABB PVI-6000-OUTD-US-A | 2016-08-11 | 2016-08-19 | 6 | 2016-08-19 | [14 empty] | 2016-09-22 | 2016-09-22 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08686 | Poughkeepsie |  |  | 12572 | G | 7056 | Rhinebeck | TBD |  | 3.44 | [13 empty] | NM | N | ENPHASE M215 602LLS22IG (16) | 2016-07-22 | 2016-07-26 | 2 | 2016-07-26 | [17 empty] | W
Central Hudson |  | American Solar Partners | CH-00005 | Newburgh | Wallkill | Ulster | 12589 | G | 5042 | East Walden | N |  | 10 | [13 empty] | NM | N | SOLAREDGE SE10000 | 2016-10-20 | 2016-11-02 | 9 | 2016-11-02 | [8 empty] | 350 | 350 |  | 2016-11-28 | 2016-11-28 | 2016-12-01 | 2016-12-15 | 2016-12-15 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-00190 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 7.68 | [13 empty] | NM | N | SUNPOWER SPR-E20-327 (24) | 2016-07-25 | 2016-07-29 | 4 | 2016-07-29 | [14 empty] | 2016-09-14 | 2016-09-15 |  | Y
Central Hudson |  | NRG Home Solar | CH-00502 | Kingston | Sundown | Sullivan | 12740 | G | 3091 | Neversink | N |  | 4.3 | [13 empty] | NM | N | ENPHASE M215 (20) | 2016-07-26 | 2016-07-26 | 0 | 2016-07-26 | [14 empty] | 2017-01-09 | 2017-01-09 |  | Y
Central Hudson |  | CKH Indusries | CH-00771 | Newburgh | Newburgh | Orange | 12550 | G | 4023 | Coldenham | N |  | 3.6 | [13 empty] | NM | N | ABB PVI 3.6 | 2016-09-07 | 2016-09-08 | 1 | 2016-09-08 | [14 empty] | 2016-12-28 | 2016-12-28 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00967 | Newburgh | Walden | Orange | 12586 | G | 5041 | East Walden | N |  | 6.25 | [13 empty] | NM | N | ENPHASE M250 60-2LL-S22 (25) | 2016-08-05 | 2016-08-17 | 8 | 2016-08-17 | [14 empty] | 2017-01-03 | 2017-01-03 |  | Y
Central Hudson |  | SolarCity | CH-05475 | Fishkill | Beacon | Dutchess | 12508 | G | 8015 | Forgebrook | N |  | 8.2 | [13 empty] | NM | N | FRONIUS PRIMO 8.2 | 2016-08-01 | 2016-08-05 | 4 | 2016-08-05 | [14 empty] | 2016-09-22 | 2016-09-26 |  | Y
Central Hudson |  | Trinity Solar | CH-08519 | Newburgh | New Windsor | Orange | 12553 | G | 4095 | Bethlehem Rd | N |  | 10 | [13 empty] | NM | N | SOLAREDGE SE10000A-US | 2016-07-25 | 2016-07-29 | 4 | 2016-07-29 | [14 empty] | 2016-09-26 | 2016-09-28 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08768 | Fishkill | Putnam Valley | Putnam | 10524 | G | 8066 | Merritt Park | N |  | 6.45 | [13 empty] | NM | N | ENPHASE M215 602LLS22IG (30) | 2016-07-25 | 2016-07-29 | 4 | 2016-07-29 | [14 empty] | 2016-12-08 | 2016-12-08 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-00129 | Newburgh | Montgomery | Orange | 12549 | G | 5073 | Montgomery | N |  | 16 | [13 empty] | NM | N | SUNPOWER SPR-E20-327 (50) | 2016-08-02 | 2016-08-05 | 3 | 2016-08-05 | [14 empty] | 2016-11-01 | 2016-11-01 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-00132 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6092 | Manchester | N |  | 5.12 | [13 empty] | NM | N | SUNPOWER SPR-E20-327C-AC (16) | 2016-07-26 | 2016-07-27 | 1 | 2016-07-27 | [14 empty] | 2016-10-12 | 2016-10-19 |  | Y
Central Hudson |  | Kasselman Solar | CH-00245 | Catskill | Catskill | Greene | 12414 | G | 2001 | North Catskill | N |  | 9 | [13 empty] | NM | N | (36) Enphase Energy M250 | 2016-08-22 | 2016-08-26 | 4 | 2016-08-26 | [14 empty] | 2016-09-01 | 2016-09-01 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | NRG Home Solar | CH-00541 | Newburgh |  |  | 12561 | G | 5011 | Modena | TBD |  | 6.45 | [13 empty] | NM | N | ENPHASE M215 (30) | 2016-07-26 | 2016-08-01 | 4 | 2016-08-01 | [17 empty] | W
Central Hudson |  | Direct Energy Solar | CH-01017 | Fishkill | Beacon | Dutchess | 12508 | G | 8017 | Forgebrook | N |  | 6.02 | [13 empty] | NM | N | ENPHASE 215 (28) | 2016-07-26 | 2016-08-01 | 4 | 2016-08-01 | [14 empty] | 2016-10-03 | 2016-10-18 |  | Y
Central Hudson |  | Monolith Solar Associates LLC | CH-02649 | Catskill | Hannacroix | Greene | 12087 | G | 1083 | New Baltimore | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A-US | 2016-10-03 | 2016-10-05 | 2 | 2016-10-05 | [14 empty] | 2016-10-14 | 2016-10-17 |  | Y
Central Hudson |  | Sunrun Inc. | CH-08339 | Newburgh | Washingtonvl | Orange | 10992 | G | 4097 | Bethlehem Rd | N |  | 7.6 | [13 empty] | NM | N | ABB UNO-7.6-TL-OUTD-S-US | 2016-08-09 | 2016-08-18 | 7 | 2016-08-18 | [14 empty] | 2016-10-05 | 2016-10-06 |  | Y
Central Hudson |  | Sol Providers | CH-08945 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6044 | Spackenkill | N |  | 7.04 | [13 empty] | NM | N | SUNPOWER 335-BLK-C- (22) | 2016-07-28 | 2016-07-29 | 1 | 2016-07-29 | [14 empty] | 2016-08-23 | 2016-08-24 |  | Y
Central Hudson |  | Lighthouse Solar | CH-00288 | Kingston | Woodstock | Ulster | 12498 | G | 3014 | Woodstock | N |  | 11.4 | [13 empty] | NM | N | SOLAREDGE 11400A-US | 2016-07-27 | 2016-07-28 | 1 | 2016-07-28 | [14 empty] | 2016-09-21 | 2016-09-22 |  | Y
Central Hudson |  | New York State Solar Farm | CH-00458 | Newburgh | Clintondale | Ulster | 12515 | G | 5012 | Modena | N |  | 20.16 | [13 empty] | NM | N | SUNPOWER SPR-E20 327-C-AC (63) | 2016-07-27 | 2016-08-10 | 10 | 2016-08-10 | [8 empty] | 350 | 350 |  | 2016-09-08 | 2016-09-08 | 2016-10-06 | 2016-10-06 | 2016-10-06 |  | Y
Central Hudson |  | NRG Home Solar | CH-00564 | Kingston |  |  | 12466 | G | 1012 | Boulevard | TBD |  | 4.08 | [13 empty] | NM | N | ENPHASE M215 (19) | 2016-07-27 | 2016-07-29 | 2 | 2016-07-29 | [17 empty] | W
Central Hudson |  | Direct Energy Solar | CH-00899 | Kingston | Kingston | Ulster | 12401 | G | 111 | South Wall St | N |  | 4.3 | [13 empty] | NM | N | ENPHASE M215 60-2LL-S22 (20) | 2016-08-01 | 2016-08-03 | 2 | 2016-08-03 | [14 empty] | 2016-10-14 | 2016-10-27 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00937 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7062 | Milan | N |  | 6.67 | [13 empty] | NM | N | ENPHASE M215 (31) | 2016-07-27 | 2016-08-01 | 3 | 2016-08-01 | [14 empty] | 2016-11-04 | 2016-11-04 |  | Y
Central Hudson |  | Direct Energy Solar | CH-01049 | Kingston | Kingston | Ulster | 12401 | G | 3023 | High Falls | N |  | 9.25 | [13 empty] | NM | N | ENPHASE M21560-2LL-S22 (43) | 2016-07-27 | 2016-07-28 | 1 | 2016-07-28 | [14 empty] | 2016-09-09 | 2016-09-14 |  | Y
Central Hudson |  | Hudson Solar | CH-01382 | Newburgh | Montgomery | Orange | 12549 | G | 5071 | Montgomery | N |  | 3 | [13 empty] | NM | N | SOLAREDGE SE-3000A US-U | 2016-08-04 | 2016-08-16 | 8 | 2016-08-16 | [14 empty] | 2016-10-07 | 2016-10-10 |  | Y
Central Hudson |  | Hudson Solar | CH-01729 | Kingston | Kingston | Ulster | 12401 | G | 2013 | Lincoln Park | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE-6000AUS-U | 2016-07-27 | 2016-07-29 | 2 | 2016-07-29 | [8 empty] | 350 | 350 |  | 2016-08-11 | 2016-08-11 | 2016-09-07 | 2016-10-07 | 2016-10-14 |  | Y
Central Hudson |  | Green Street Power Partners, LLC | CH-00113 | Fishkill | Beacon | Dutchess | 12508 | G | 8015 | Forgebrook | N |  | 5 | [13 empty] | NM | N | SMA SB5000TL-US-22 | 2016-08-08 | 2016-08-18 | 8 | 2016-08-18 | [14 empty] | 2016-08-30 | 2016-08-31 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-00183 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8055 | North Chelsea | N |  | 10.88 | [13 empty] | NM | N | SUNPOWER SPR-E20-327 C-AC (34) | 2016-07-28 | 2016-08-02 | 3 | 2016-08-02 | [14 empty] | 2016-10-19 | 2016-10-25 |  | Y
Central Hudson |  | Lighthouse Solar | CH-00293 | Fishkill | Beacon | Dutchess | 12508 | G | 8087 | Tioronda | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE 7600 A-US | 2016-08-02 | 2016-08-05 | 3 | 2016-08-05 | [14 empty] | 2016-10-10 | 2016-10-13 |  | Y
Central Hudson |  | SolarCity | CH-05408 | Newburgh | Campbell Hall | Orange | 10916 | G | 5052 | Maybrook | N |  | 3.6 | [13 empty] | NM | N | ABB PVI-3.6 OUTD-S-US | 2016-08-10 | 2016-08-19 | 7 | 2016-08-19 | [14 empty] | 2016-09-01 | 2016-09-01 |  | Y
Central Hudson |  | SolarCity | CH-05613 | Kingston | Accord | Ulster | 12404 | G | 3081 | Kerhonkson | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2016-07-28 | 2016-07-29 | 1 | 2016-07-29 | [14 empty] | 2016-10-03 | 2016-10-04 |  | Y
Central Hudson |  | Sol Providers | CH-08942 | Catskill | Palenvl | Greene | 12463 | G | 2001 | North Catskill | N | CH-08942 | 5.12 | [13 empty] | NM | N | SUNPOWER E20 327-C-AC (16) | 2016-07-28 | 2016-07-29 | 1 | 2016-07-29 | [14 empty] | 2016-08-30 | 2016-09-06 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-00090 | Newburgh | Cornwall-Hdsn | Orange | 12520 | G | 4043 | Union Ave | N |  | 15.2 | [13 empty] | NM | N | SOLAREDGE 7600A (2) | 2016-08-04 | 2016-08-16 | 8 | 2016-08-16 | [14 empty] | 2016-09-28 | 2016-10-04 |  | Y
Central Hudson |  | Kirchhoff Green Energy LLC | CH-00262 | Poughkeepsie |  |  | 12603 | G | 6043 | Spackenkill | TBD |  | 15 | [13 empty] | NM | N | FRONIUS USA 7.5 | 2016-08-04 | 2016-08-16 | 8 | 2016-08-16 | [17 empty] | W
Central Hudson |  | Lighthouse Solar | CH-00329 | Kingston |  |  | 12477 | G | 3002 | Saugerties | TBD |  | 100 | [13 empty] | NM | N | SOLECTRIA PVI 100KW | 2016-10-12 | 2016-10-24 | 8 | 2016-10-24 | 2016-10-24 | 2016-11-08 | 11 |  |  |  |  | 35000 | [9 empty] | W
Central Hudson |  | Murphy Solar Power | CH-02747 | Catskill | Freehold | Greene | 12431 | G | 2071 | Freehold | N |  | 11 | [13 empty] | NM | N | SMA 11000TL-US | 2016-09-07 | 2016-09-08 | 1 | 2016-09-08 | [14 empty] | 2016-09-30 | 2016-10-03 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | PosiGen Solar | CH-02876 | Catskill | Climax | Greene | 12042 | G | 1071 | Coxsackie | N |  | 6.88 | [13 empty] | NM | N | ENPHASE M215-60-2LL-S22-IG (32) | 2016-08-09 | 2016-08-18 | 7 | 2016-08-18 | [14 empty] | 2016-08-29 | 2016-08-29 |  | Y
Central Hudson |  | SolarCity | CH-05490 | Catskill | Palenvl | Greene | 12463 | G | 2042 | South Cairo | N |  | 9 | [13 empty] | NM | N | ABB PVI3.0 ABB PVI6000 | 2016-07-29 | 2016-08-03 | 3 | 2016-08-03 | [14 empty] | 2016-10-14 | 2016-10-17 |  | Y
Central Hudson |  | SolarCity | CH-05960 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7056 | Rhinebeck | N |  | 5 | [13 empty] | NM | N | ABB PVI 5000 | 2016-07-29 | 2016-08-03 | 3 | 2016-08-03 | [14 empty] | 2016-10-04 | 2016-10-13 |  | Y
Central Hudson |  | SolarCity | CH-06126 | Fishkill | Stormvl | Dutchess | 12582 | G | 8071 | Shenandoah | N |  | 5 | [13 empty] | NM | N | ABB PVI 5000 | 2016-07-29 | 2016-08-04 | 4 | 2016-08-04 | [14 empty] | 2016-10-12 | 2016-10-17 |  | Y
Central Hudson |  | SolarCity | CH-07224 | Kingston | Kingston | Ulster | 12401 | G | 2093 | Hurley Ave | N |  | 11.4 | [13 empty] | NM | N | SOLAREDGE SE11400A | 2016-08-01 | 2016-08-04 | 3 | 2016-08-04 | [14 empty] | 2016-10-14 | 2016-10-19 |  | Y
Central Hudson |  | SolarCity | CH-07835 | Newburgh | Maybrook | Orange | 12543 | G | 5052 | Maybrook | N | CH-07154 | 3 | [13 empty] | NM | N | ABB PVI 3.0 | 2016-08-11 | 2016-08-22 | 7 | 2016-08-22 | [14 empty] | 2016-09-22 | 2016-09-22 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08660 | Kingston | Hurley | Ulster | 12443 | G | 2093 | Hurley Ave | N | CH-08660 | 5.8 | [13 empty] | NM | N | ENPHASE M215 602LLS22IG (27) | 2016-07-29 | 2016-08-03 | 3 | 2016-08-03 | [14 empty] | 2016-12-08 | 2016-12-08 |  | Y
Central Hudson |  | Direct Energy Solar | CH-01065 | Poughkeepsie | Tivoli | Dutchess | 12583 | G | 7062 | Milan | N |  | 3.65 | [13 empty] | NM | N | ENPHASE M215 (17) | 2016-08-01 | 2016-08-17 | 12 | 2016-08-17 | [14 empty] | 2016-10-25 | 2016-10-28 |  | Y
Central Hudson |  | SolarCity | CH-06234 | Newburgh | Newburgh | Orange | 12550 | G | 4012 | West Balmville | N |  | 5 | [13 empty] | NM | N | ABB PVI 5000 | 2016-08-01 | 2016-08-05 | 4 | 2016-08-05 | [14 empty] | 2016-10-18 | 2016-10-18 |  | Y
Central Hudson |  | SolarCity | CH-06475 | Catskill | Ravena | Albany | 12143 | G | 1083 | New Baltimore | N |  | 5 | [13 empty] | NM | N | ABB PVI 5000 | 2016-08-01 | 2016-08-04 | 3 | 2016-08-04 | [14 empty] | 2016-10-04 | 2016-10-04 |  | Y
Central Hudson |  | Sunrun Inc. | CH-08335 | Newburgh | Newburgh | Orange | 12550 | G | 4011 | West Balmville | N |  | 4.2 | [13 empty] | NM | N | ABB PVI-4.2-OUTD-S-US-A | 2016-09-14 | 2016-09-19 | 3 | 2016-09-19 | [14 empty] | 2016-11-28 | 2016-11-28 |  | Y
Central Hudson |  | Trinity Solar | CH-08403 | Kingston | Ellenvl | Ulster | 12428 | G | 3076 | Greenfield Rd | N |  | 3 | [13 empty] | NM | N | SOLAREDGE SE3800A-US | 2016-08-01 | 2016-08-04 | 3 | 2016-08-04 | [14 empty] | 2016-10-28 | 2016-10-28 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-00022 | Kingston | Stone Ridge | Ulster | 12484 | G | 3023 | High Falls | N |  | 5 | [13 empty] | NM | N | SOLAREDGE 5000AUS | 2016-08-05 | 2016-08-17 | 8 | 2016-08-17 | [14 empty] | 2016-08-29 | 2016-09-07 |  | Y
Central Hudson |  | New York State Solar Farm | CH-00402 | Newburgh | New Paltz | Ulster | 12561 | G | 5031 | Galeville | N |  | 5 | [13 empty] | NM | N | SMA AMERICA SB 5000 | 2016-08-02 | 2016-08-05 | 3 | 2016-08-05 | [14 empty] | 2016-09-22 | 2016-09-26 |  | Y
Central Hudson |  | Apex Solar Power | CH-00683 | Fishkill | Beacon | Dutchess | 12508 | G | 8017 | Forgebrook | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A-US | 2016-08-02 | 2016-08-05 | 3 | 2016-08-05 | [14 empty] | 2016-12-30 | 2016-12-30 |  | Y
Central Hudson |  | Ross Solar Group | CH-02993 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8095 | Fishkill Plains | N |  | 15.4 | [13 empty] | NM | N | SMA SB7700TL-US-22 (2) | 2016-08-08 | 2016-08-18 | 8 | 2016-08-18 | [14 empty] | 2016-12-06 | 2016-12-06 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08840 | Fishkill |  |  | 10524 | G | 8066 | Merritt Park | TBD |  | 6.23 | [13 empty] | NM | N | ENPHASE M215 602LLS22IG (29) | 2016-08-02 | 2016-08-05 | 3 | 2016-08-05 | [17 empty] | W
Central Hudson |  | Empire Solar Solutions | CH-00063 | Newburgh | Gardiner | Ulster | 12525 | G | 5031 | Galeville | N |  | 6 | [13 empty] | NM | N | SMA AMERICA 6000 | 2016-08-03 | 2016-08-03 | 0 | 2016-08-03 | [14 empty] | 2016-08-03 | 2016-08-03 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | New York State Solar Farm | CH-00387 | Kingston | Saugerties | Ulster | 12477 | G | 3003 | Saugerties | N |  | 6 | [13 empty] | NM | N | SMA AMERICA SB6000TL | 2016-08-03 | 2016-08-09 | 4 | 2016-08-09 | [14 empty] | 2016-09-01 | 2016-09-02 |  | Y
Central Hudson |  | New York State Solar Farm | CH-00400 | Newburgh | New Paltz | Ulster | 12561 | G | 5031 | Galeville | N |  | 11.2 | [13 empty] | NM | N | SUNPOWER SPR-E20 327-C-AC (35) | 2016-08-03 | 2016-08-15 | 8 | 2016-08-15 | [14 empty] | 2016-09-29 | 2016-10-04 |  | Y
Central Hudson |  | Hudson Solar | CH-01802 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 6051 | Todd Hill | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE-5000 A-US | 2016-08-17 | 2016-08-22 | 3 | 2016-08-22 | [14 empty] | 2016-10-19 | 2016-10-19 |  | Y
Central Hudson |  | Hudson Solar | CH-02309 | Fishkill | Beacon | Dutchess | 12508 | G | 8017 | Forgebrook | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE-6000 | 2016-08-03 | 2016-08-15 | 8 | 2016-08-15 | [14 empty] | 2016-11-14 | 2016-11-17 |  | Y
Central Hudson |  | Hudson Solar | CH-02320 | Newburgh | Newburgh | Orange | 12550 | G | 4053 | Union Ave | N |  | 3.8 | [13 empty] | NM | N | SOLAREDGE SE-3800 A-US | 2016-08-03 | 2016-08-05 | 2 | 2016-08-05 | [14 empty] | 2016-11-17 | 2016-12-06 |  | Y
Central Hudson |  | Hudson Solar | CH-02506 | Poughkeepsie |  |  | 12571 | G | 7062 | Milan | TBD |  | 6 | [13 empty] | NM | N | SOLAREDGE SE-6000 US-U | 2016-08-16 | 2016-08-23 | 5 | 2016-08-23 | [17 empty] | W
Central Hudson |  | Monolith Solar Associates LLC | CH-02689 | Catskill |  |  | 12058 | G | 1071 | Coxsackie | TBD |  | 9 | [13 empty] | NM | N | SOLAREDGE SE6000 SOLAREDGE SE3000 | 2016-08-03 | 2016-08-05 | 2 | 2016-08-05 | [17 empty] | W
Central Hudson |  | PosiGen Solar | CH-02884 | Catskill | Catskill | Greene | 12414 | G | 2004 | North Catskill | N |  | 6.88 | [13 empty] | NM | N | ENPHASE M215-60-2LL-S22-IG (32) | 2016-08-03 | 2016-08-05 | 2 | 2016-08-05 | [14 empty] | 2016-08-18 | 2016-08-19 |  | Y
Central Hudson |  | PosiGen Solar | CH-02899 | Newburgh | Newburgh | Orange | 12550 | G | 4011 | West Balmville | N |  | 6.88 | [13 empty] | NM | N | ENPHASE M215-60-2LL-S22-IG (32) | 2016-08-03 | 2016-08-15 | 8 | 2016-08-15 | [14 empty] | 2016-12-09 | 2016-12-09 |  | Y
Central Hudson |  | SolarCity | CH-05506 | Catskill | Catskill | Greene | 12414 | G | 2042 | South Cairo | N |  | 12 | [13 empty] | NM | N | ABB PVI-6000OUTD-US (2) | 2016-08-10 | 2016-08-19 | 7 | 2016-08-19 | [14 empty] | 2016-08-29 | 2016-09-07 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06549 | Kingston | Hurley | Ulster | 12443 | G | 2093 | Hurley Ave | N |  | 6 | [13 empty] | NM | N | ABB PVI-3.0 OUTD-S-US (2) | 2016-08-25 | 2016-08-26 | 1 | 2016-08-26 | [14 empty] | 2016-11-01 | 2016-11-02 |  | Y
Central Hudson |  | Hudson Solar | CH-01834 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7056 | Rhinebeck | N |  | 11.4 | [13 empty] | NM | N | SOLAREDGE SE-11400 | 2016-08-17 | 2016-08-22 | 3 | 2016-08-22 | [14 empty] | 2016-10-24 | 2016-10-31 |  | W
Central Hudson |  | Hudson Solar | CH-02152 | Poughkeepsie | Tivoli | Dutchess | 12583 | G | 7062 | Milan | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE-5000 A-US | 2016-08-17 | 2016-08-22 | 3 | 2016-08-22 | [14 empty] | 2017-01-16 | 2017-01-16 |  | Y
Central Hudson |  | SolarCity | CH-04970 | Newburgh | Newburgh | Orange | 12550 | G | 4022 | Coldenham | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2016-08-04 | 2016-08-16 | 8 | 2016-08-16 | [14 empty] | 2016-08-24 | 2016-08-24 |  | Y
Central Hudson |  | SolarCity | CH-05243 | Newburgh | Highland | Ulster | 12528 | G | 5022 | Ohioville | N |  | 6 | [13 empty] | NM | N | ABB PVI6000 | 2016-08-17 | 2016-08-23 | 4 | 2016-08-23 | [14 empty] | 2016-09-02 | 2016-09-12 |  | Y
Central Hudson |  | SolarCity | CH-05625 | Kingston | Ulster Pk | Ulster | 12487 | G | 3041 | Sturgeon Pool | N |  | 3.6 | [13 empty] | NM | N | ABB PVI 3.6 | 2016-08-04 | 2016-08-16 | 8 | 2016-08-16 | [14 empty] | 2016-10-14 | 2016-10-17 |  | Y
Central Hudson |  | SolarCity | CH-07292 | Poughkeepsie | Salt Pt | Dutchess | 12578 | G | 7011 | Hibernia | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2016-08-26 | 2016-08-26 | 0 | 2016-08-26 | [14 empty] | 2016-08-31 | 2016-09-06 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07390 | Fishkill | Beacon | Dutchess | 12508 | G | 8017 | Forgebrook | N |  | 3 | [13 empty] | NM | N | ABB PVI-3.0 OUTD-S-US | 2016-08-04 | 2016-08-16 | 8 | 2016-08-16 | [14 empty] | 2016-08-24 | 2016-08-24 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07460 | Newburgh | Walden | Orange | 12586 | G | 5043 | East Walden | N |  | 3 | [13 empty] | NM | N | ABB PVI 3.0 | 2016-08-04 | 2016-08-16 | 8 | 2016-08-16 | [14 empty] | 2016-08-24 | 2016-08-24 |  | Y
Central Hudson |  | SolarCity | CH-07777 | Kingston | Woodstock | Ulster | 12498 | G | 3012 | Woodstock | N |  | 5 | [13 empty] | NM | N | ABB PVI 5000 | 2016-08-30 | 2016-08-30 | 0 | 2016-08-30 | [14 empty] | 2016-10-03 | 2016-10-14 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08831 | Kingston |  |  | 12443 | G | 2093 | Hurley Ave | TBD |  | 9.03 | [13 empty] | NM | N | ENPHASE M215 602LLS22IG (42) | 2016-08-04 | 2016-08-16 | 8 | 2016-08-16 | [17 empty] | W
Central Hudson |  | Malcarne Contracting | CH-00347 | Kingston | Shokan | Ulster | 12481 | G | 3011 | Woodstock | N |  | 7 | [13 empty] | NM | N | SOLAREDGE 7000 | 2016-08-18 | 2016-08-23 | 3 | 2016-08-23 | [14 empty] | 2016-10-06 | 2016-10-14 |  | Y
Central Hudson |  | Hudson Solar | CH-02190 | Newburgh |  |  | 12561 | G | 5031 | Galeville | TBD |  | 29.7 | [13 empty] | NM | N | SMA AMERICA SB11000TL-US-12 (2) SMA AMERICA SB7700TL-US-22 | 2016-08-05 | 2016-08-05 | 0 | 2016-08-05 | [17 empty] | W
Central Hudson |  | Hudson Solar | CH-02254 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6046 | Spackenkill | N |  | 8.32 | [13 empty] | NM | N | SUNPOWER SPR-X21-345 C-AC (26) | 2016-08-17 | 2016-08-22 | 3 | 2016-08-22 | [14 empty] | 2016-10-13 | 2016-10-14 |  | Y
Central Hudson |  | Hudson Solar | CH-02396 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6043 | Spackenkill | N |  | 10 | [13 empty] | NM | N | SOLAREDGE SE-10000 A-US | 2016-08-17 | 2016-08-23 | 4 | 2016-08-23 | [14 empty] | 2016-10-25 | 2016-11-01 |  | Y
Central Hudson |  | SolarCity | CH-05752 | Kingston | Saugerties | Ulster | 12477 | G | 3005 | Saugerties | N |  | 8.6 | [13 empty] | NM | N | ABB PVI 5000 ABB PVI 3.6 | 2016-08-23 | 2016-08-24 | 1 | 2016-08-24 | [14 empty] | 2016-08-29 | 2016-08-29 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06169 | Newburgh | New Paltz | Ulster | 12561 | G | 5024 | Ohioville | N |  | 12 | [13 empty] | NM | N | ABB PVI 6000 (2) | 2016-08-05 | 2016-08-17 | 8 | 2016-08-17 | [14 empty] | 2016-08-24 | 2016-08-30 |  | Y
Central Hudson |  | Sungevity Inc | CH-09239 | Newburgh | Newburgh | Orange | 12550 | G | 4023 | Coldenham | N |  | 3.8 | [13 empty] | NM | N | ABB PVI-3.8-OUTD-S-US-A | 2016-08-25 | 2016-08-25 | 0 | 2016-08-25 | [14 empty] | 2016-09-09 | 2016-09-13 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-00060 | Newburgh | New Windsor | Orange | 12553 | G | 4046 | Union Ave | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE 7600A | 2016-08-08 | 2016-08-18 | 8 | 2016-08-18 | [14 empty] | 2016-08-30 | 2016-08-30 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-00135 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6073 | East Park | N |  | 11.2 | [13 empty] | NM | N | SUNPOWER SPR-X21-335-BLK C-AC (35) | 2016-08-08 | 2016-08-18 | 8 | 2016-08-18 | [14 empty] | 2016-11-08 | 2016-11-14 |  | Y
Central Hudson |  | NRG Home Solar | CH-00538 | Fishkill | Fishkill | Dutchess | 12524 | G | 8013 | Forgebrook | N |  | 2.15 | [13 empty] | NM | N | ENPHASE M-215 (10) | 2016-08-18 | 2016-08-23 | 3 | 2016-08-23 | [14 empty] | 2016-12-19 | 2016-12-22 |  | Y
Central Hudson |  | Hudson Solar | CH-01363 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 7024 | Tinkertown | N |  | 19 | [13 empty] | NM | N | SOLAREDGE SE-11400 SOLAREDGE SE7600 | 2016-08-08 | 2016-08-18 | 8 | 2016-08-18 | [14 empty] | 2016-12-30 | 2017-01-05 |  | Y
Central Hudson |  | Hudson Solar | CH-02127 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7061 | Milan | N |  | 11.4 | [13 empty] | NM | N | SOLAREDGE SE-11400 | 2016-08-18 | 2016-08-26 | 6 | 2016-08-26 | [8 empty] | 350 | 350 |  | 2016-09-19 | 2016-09-19 | 2016-09-23 | 2016-10-25 | 2016-10-25 |  | Y
Central Hudson |  | Hudson Solar | CH-02385 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6051 | Todd Hill | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE-6000 | 2016-08-08 | 2016-08-18 | 8 | 2016-08-18 | [14 empty] | 2016-10-11 | 2016-10-14 |  | Y
Central Hudson |  | Solar Liberty Energy Systems | CH-04913 | Newburgh | New Paltz | Ulster | 12561 | G | 5025 | Ohioville | Y | CH-00621 | 100 | [13 empty] | NM | N | SMA Sunny Tripower 20.0kW (5) | 2016-11-07 | 2016-11-07 | 0 | 2016-11-07 | 2016-11-07 | 2016-11-09 | 2 | [11 empty] | 2017-03-28 | 2017-03-28 |  | Y
Central Hudson |  | SolarCity | CH-05364 | Newburgh | Montgomery | Orange | 12549 | G | 5073 | Montgomery | N |  | 5 | [13 empty] | NM | N | ABB PVI 5000 | 2016-08-08 | 2016-08-18 | 8 | 2016-08-18 | [14 empty] | 2016-08-31 | 2016-09-06 |  | Y
Central Hudson |  | SolarCity | CH-05470 | Newburgh | Highland | Ulster | 12528 | G | 5083 | Highland | N |  | 3.6 | [13 empty] | NM | N | ABB PVI-3.6-OUTD-S | 2016-08-08 | 2016-08-18 | 8 | 2016-08-18 | [14 empty] | 2016-10-14 | 2016-10-17 |  | Y
Central Hudson |  | SolarCity | CH-05823 | Poughkeepsie | Hyde Park | Dutchess | 12538 | G | 6068 | Inwood Ave | N |  | 4.2 | [13 empty] | NM | N | ABB PVI 4.2 | 2016-08-30 | 2016-08-30 | 0 | 2016-08-30 | [14 empty] | 2016-11-03 | 2016-11-09 |  | Y
Central Hudson |  | SolarCity | CH-06401 | Newburgh | New Windsor | Orange | 12553 | G | 4097 | Bethlehem Rd | N |  | 8.4 | [13 empty] | NM | N | ABB PVI-4.2-OUTD-S (2) | 2016-08-22 | 2016-08-23 | 1 | 2016-08-23 | [14 empty] | 2016-10-03 | 2016-10-03 |  | Y
Central Hudson |  | SolarCity | CH-06506 | Kingston | Kingston | Ulster | 12401 | G | 1003 | Jansen Ave | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A | 2016-08-08 | 2016-08-18 | 8 | 2016-08-18 | [14 empty] | 2016-10-18 | 2016-10-21 |  | Y
Central Hudson |  | SolarCity | CH-06960 | Newburgh | New Paltz | Ulster | 12561 | G | 5021 | Ohioville | N |  | 8.2 | [13 empty] | NM | N | FRONIUS PRIMO 8.2 | 2016-08-08 | 2016-08-18 | 8 | 2016-08-18 | [14 empty] | 2016-10-14 | 2016-10-17 |  | Y
Central Hudson |  | SolarCity | CH-07211 | Kingston | Accord | Ulster | 12404 | G | 3024 | High Falls | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A | 2016-08-08 | 2016-08-18 | 8 | 2016-08-18 | [14 empty] | 2016-10-18 | 2016-10-25 |  | Y
Central Hudson |  | SolarCity | CH-07443 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 6 | [13 empty] | NM | N | ABB PVI 6000 | 2016-08-08 | 2016-08-17 | 7 | 2016-08-17 | [14 empty] | 2016-11-01 | 2016-11-02 |  | W
Central Hudson |  | Solar Generation | CH-08156 | Kingston | Hurley | Ulster | 12443 | G | 2094 | Hurley Ave | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SB7600 | 2016-08-18 | 2016-08-23 | 3 | 2016-08-23 | [14 empty] | 2016-10-13 | 2016-10-14 |  | Y
Central Hudson |  | NRG Home Solar | CH-00512 | Fishkill | Beacon | Dutchess | 12508 | G | 8017 | Forgebrook | N |  | 3.44 | [13 empty] | NM | N | ENPHASE M-215 (16) | 2016-08-09 | 2016-08-18 | 7 | 2016-08-18 | [14 empty] | 2016-09-16 | 2016-09-19 |  | Y
Central Hudson |  | Monolith Solar Associates LLC | CH-02657 | Catskill | Westerlo | Albany | 12193 | G | 1091 | Westerlo | N |  | 11.4 | [13 empty] | NM | N | SOLAREDGE SE7600A-US SOLAREDGE SE3800A-US | 2016-08-19 | 2016-08-23 | 2 | 2016-08-23 | [14 empty] | 2016-10-25 | 2016-11-01 |  | Y
Central Hudson |  | SolarCity | CH-07692 | Kingston | Stone Ridge | Ulster | 12484 | G | 3023 | High Falls | N | CH-07692 | 5 | [13 empty] | NM | N | ABB PVI-5000 OUTD-US | 2016-08-09 | 2016-08-18 | 7 | 2016-08-18 | [14 empty] | 2016-11-10 | 2016-11-15 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-00041 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 6074 | East Park | N |  | 10 | [13 empty] | NM | N | SOLAREDGE 10000A | 2016-08-10 | 2016-08-19 | 7 | 2016-08-19 | [14 empty] | 2017-02-01 | 2017-02-01 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-00140 | Newburgh | Milton | Ulster | 12547 | G | 5083 | Highland | N |  | 13.44 | [13 empty] | NM | N | SUNPOWER SPR-E20-327 C-AC (42) | 2016-08-10 | 2016-08-19 | 7 | 2016-08-19 | [14 empty] | 2016-10-05 | 2016-10-06 |  | Y
Central Hudson |  | NRG Home Solar | CH-00506 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6065 | Inwood Ave | N |  | 2.58 | [13 empty] | NM | N | ENPHASE M-215 (12) | 2016-08-19 | 2016-08-23 | 2 | 2016-08-23 | [14 empty] | 2016-10-11 | 2016-10-14 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00837 | Kingston | Stone Ridge | Ulster | 12484 | G | 3023 | High Falls | N |  | 8.25 | [13 empty] | NM | N | ENPHASE M250 60-2LL-S22 (33) | 2016-08-10 | 2016-08-19 | 7 | 2016-08-19 | [14 empty] | 2016-10-26 | 2016-11-01 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00909 | Kingston | Saugerties | Ulster | 12477 | G | 3002 | Saugerties | N |  | 3.75 | [13 empty] | NM | N | ENPHASE M250 60-2LL-S22 (15) | 2016-08-30 | 2016-08-30 | 0 | 2016-08-30 | [14 empty] | 2016-09-16 | 2016-09-19 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00917 | Kingston | Saugerties | Ulster | 12477 | G | 3001 | Saugerties | N |  | 3.02 | [13 empty] | NM | N | ENPHASE M215 (14) | 2016-08-29 | 2016-08-29 | 0 | 2016-08-29 | [14 empty] | 2016-09-23 | 2016-10-05 |  | Y
Central Hudson |  | Direct Energy Solar | CH-01005 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7061 | Milan | N |  | 9.03 | [13 empty] | NM | N | ENPHASE M215 60-2LL-S22 (42) | 2016-08-10 | 2016-08-19 | 7 | 2016-08-19 | [8 empty] | 350 | 350 |  | 2016-09-12 | 2016-09-12 | 2016-09-21 | 2016-09-29 | 2016-10-03 |  | Y
Central Hudson |  | Hudson Solar | CH-01544 | Catskill | Catskill | Greene | 12414 | G | 2006 | North Catskill | N |  | 10 | [13 empty] | NM | N | SOLAREDGE SE-10000 | 2016-08-10 | 2016-08-19 | 7 | 2016-08-19 | [14 empty] | 2016-11-17 | 2016-11-23 |  | Y
Central Hudson |  | Hudson Solar | CH-02283 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7054 | Rhinebeck | N |  | 10 | [13 empty] | NM | N | SOLAREDGE SE-10000 | 2016-08-19 | 2016-08-23 | 2 | 2016-08-23 | [14 empty] | 2016-10-17 | 2016-10-17 |  | Y
Central Hudson |  | Monolith Solar Associates LLC | CH-02639 | Catskill | Preston Holw | Albany | 12469 | G | 1092 | Westerlo | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE7600-A-US | 2016-08-22 | 2016-08-24 | 2 | 2016-08-24 | [14 empty] | 2016-10-31 | 2016-11-01 |  | Y
Central Hudson |  | PosiGen Solar | CH-02908 | Catskill | Coxsackie | Greene | 12051 | G | 1076 | Coxsackie | N |  | 6.88 | [13 empty] | NM | N | ENPHASE M215-60-2LL-S22-IG (32) | 2016-08-25 | 2016-08-25 | 0 | 2016-08-25 | [14 empty] | 2016-09-06 | 2016-09-16 |  | Y
Central Hudson |  | PosiGen Solar | CH-02916 | Fishkill | Poughkeepsie | Dutchess | 12603 | G | 8022 | Knapps Corners | N |  | 3.87 | [13 empty] | NM | N | ENPHASE M215-60-2LL-S22-IG (18) | 2016-08-10 | 2016-08-19 | 7 | 2016-08-19 | [14 empty] | 2016-11-17 | 2016-11-23 |  | Y
Central Hudson |  | SolarCity | CH-06512 | Kingston | Kingston | Ulster | 12401 | G | 1022 | East Kingston | N |  | 3 | [13 empty] | NM | N | SOLAREDGE SE3000A | 2016-09-08 | 2016-09-08 | 0 | 2016-09-08 | [14 empty] | 2016-09-15 | 2016-09-15 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | You Save Green | CH-09962 | Kingston | Cragsmoor | Ulster | 12420 | G | 3078 | Greenfield Rd | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000 | 2016-08-24 | 2016-08-26 | 2 | 2016-08-26 | [14 empty] | 2017-08-31 | 2017-08-31 |  | Y
Central Hudson |  | Solar Liberty Energy Systems | CH-04914 | Newburgh | New Paltz | Ulster | 12561 | G | 5025 | Ohioville | Y | CH-00621 | 100 | 100 | [12 empty] | NM | N | 2 Princeton Power Systems GTIB-480-100X-YYYYYYYY-Z-G1.2 (480V) Princeton Power GTIB 480-1001Princeton PowerGTIB 100 | 2016-11-22 | 2016-11-22 | 0 | 2016-11-22 | 2016-11-22 | 2016-11-23 | 1 | [11 empty] | 2018-04-05 | 2018-04-05 |  | Y
Central Hudson |  | Trinity Solar | CH-08363 | Kingston | Ulster Pk | Ulster | 12487 | G | 3041 | Sturgeon Pool | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE7600A-US | 2016-08-11 | 2016-08-22 | 7 | 2016-08-22 | [14 empty] | 2016-10-27 | 2016-10-27 |  | Y
Central Hudson |  | US Energy Concierge, Inc. | CH-09744 | Fishkill | Wappingers Falls | Dutchess | 12590 | G | 8051 | North Chelsea | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE7600A-US | 2016-08-23 | 2016-08-24 | 1 | 2016-08-24 | [14 empty] | 2016-10-10 | 2016-10-17 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-00043 | Poughkeepsie | Salt Pt | Dutchess | 12578 | G | 7011 | Hibernia | N |  | 6 | [13 empty] | NM | N | SOLAREDGE 6000A | 2016-08-12 | 2016-08-22 | 6 | 2016-08-22 | [14 empty] | 2016-11-09 | 2016-11-09 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-00095 | Fishkill | Wappingers Falls | Dutchess | 12590 | G | 8051 | North Chelsea | N |  | 10 | [13 empty] | NM | N | SOLAREDGE 10000A | 2016-08-12 | 2016-08-22 | 6 | 2016-08-22 | [14 empty] | 2016-09-28 | 2016-10-03 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-00189 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 6.4 | [13 empty] | NM | N | SUNPOWER SPR-E20-327 C-AC (20) | 2016-08-12 | 2016-08-22 | 6 | 2016-08-22 | [14 empty] | 2016-10-24 | 2016-10-27 |  | Y
Central Hudson |  | PosiGen Solar | CH-02923 | Catskill | Westerlo | Albany | 12193 | G | 1091 | Westerlo | N |  | 3.87 | [13 empty] | NM | N | ENPHASE M215-60-2LL-S22-IG (18) | 2016-08-12 | 2016-08-22 | 6 | 2016-08-22 | [14 empty] | 2016-09-06 | 2016-10-06 |  | Y
Central Hudson |  | SolarCity | CH-05318 | Catskill | Athens | Greene | 12015 | G | 1074 | Coxsackie | N |  | 5 | [13 empty] | NM | N | ABB PVI-5000 OUTD-US | 2016-08-12 | 2016-08-22 | 6 | 2016-08-22 | [14 empty] | 2016-08-29 | 2016-09-02 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-05937 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6093 | Manchester | N |  | 3.8 | [13 empty] | NM | N | SOLAREDGE SE3800 A-US | 2016-08-26 | 2016-08-26 | 0 | 2016-08-26 | [14 empty] | 2016-10-14 | 2016-10-17 |  | Y
Central Hudson |  | SolarCity | CH-06050 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8095 | Fishkill Plains | N | CH-06050 | 8.2 | [13 empty] | NM | N | FRONIUS PRIMO 8.2 | 2016-08-12 | 2016-08-22 | 6 | 2016-08-22 | [14 empty] | 2016-10-03 | 2016-10-04 |  | Y
Central Hudson |  | SolarCity | CH-06285 | Newburgh | New Windsor | Orange | 12553 | G | 4042 | Union Ave | N |  | 6 | [13 empty] | NM | N | ABB PVI 6000 | 2016-08-12 | 2016-08-22 | 6 | 2016-08-22 | [14 empty] | 2016-10-04 | 2016-10-04 |  | Y
Central Hudson |  | SolarCity | CH-07397 | Fishkill | Beacon | Dutchess | 12508 | G | 8085 | Tioronda | N |  | 4.2 | [13 empty] | NM | N | ABB PVI 4.2 | 2016-08-12 | 2016-08-22 | 6 | 2016-08-22 | [14 empty] | 2016-10-04 | 2016-10-04 |  | Y
Central Hudson |  | SolarCity | CH-06835 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8046 | Myers Corners | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000-OUTD | 2016-09-06 | 2016-09-06 | 0 | 2016-09-06 | [14 empty] | 2016-09-07 | 2016-09-16 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07143 | Newburgh | Montgomery | Orange | 12549 | G | 5073 | Montgomery | N |  | 3 | [13 empty] | NM | N | ABB PVI 3.0 | 2016-08-15 | 2016-08-22 | 5 | 2016-08-22 | [14 empty] | 2016-11-10 | 2016-11-10 |  | Y
Central Hudson |  | SolarCity | CH-07798 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7062 | Milan | N |  | 4.2 | [13 empty] | NM | N | ABB PVI 4.2 | 2016-08-15 | 2016-08-22 | 5 | 2016-08-22 | [14 empty] | 2016-11-15 | 2016-11-23 |  | Y
Central Hudson |  | New York State Solar Farm | CH-00414 | Newburgh | Wallkill | Ulster | 12589 | G | 5043 | East Walden | N |  | 7.6 | [13 empty] | NM | N | SMA AMERICA SB 3800 (2) | 2016-08-16 | 2016-08-23 | 5 | 2016-08-23 | [14 empty] | 2016-09-29 | 2016-10-03 |  | Y
Central Hudson |  | New York State Solar Farm | CH-00426 | Kingston | Saugerties | Ulster | 12477 | G | 3001 | Saugerties | N |  | 5 | [13 empty] | NM | N | SMA AMERICA SB5000 | 2016-08-16 | 2016-08-22 | 4 | 2016-08-22 | [14 empty] | 2017-01-05 | 2017-01-05 |  | Y
Central Hudson |  | New York State Solar Farm | CH-00470 | Kingston | Saugerties | Ulster | 12477 | G | 3001 | Saugerties | N |  | 4.48 | [13 empty] | NM | N | SUNPOWER SPR-X21 345-C-AC (14) | 2016-08-16 | 2016-08-22 | 4 | 2016-08-22 | [14 empty] | 2016-09-27 | 2016-09-28 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00991 | Kingston | Saugerties | Ulster | 12477 | G | 3003 | Saugerties | N |  | 6.02 | [13 empty] | NM | N | ENPHASE M215-60-2LL-S22-IG (28) | 2016-08-16 | 2016-08-22 | 4 | 2016-08-22 | [14 empty] | 2016-11-18 | 2016-11-22 |  | Y
Central Hudson |  | Direct Energy Solar | CH-01001 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7062 | Milan | N |  | 6.24 | [13 empty] | NM | N | ENPHASE M215 (29) | 2016-08-22 | 2016-08-23 | 1 | 2016-08-23 | [14 empty] | 2016-09-16 | 2016-09-19 |  | Y
Central Hudson |  | Sunrun Inc. | CH-08357 | Newburgh | Newburgh | Orange | 12550 | G | 4024 | Coldenham | N | CH-08357 | 3.8 | [13 empty] | NM | N | SOLAREDGE SE3800 | 2016-09-27 | 2016-10-04 | 5 | 2016-10-04 | [14 empty] | 2016-12-28 | 2016-12-28 |  | Y
Central Hudson |  | New York State Solar Farm | CH-00418 | Catskill | Athens | Greene | 12015 | G | 2002 | North Catskill | N |  | 9.6 | [13 empty] | NM | N | SUNPOWER SPR-E20 327-C-AC (30) | 2016-08-17 | 2016-08-23 | 4 | 2016-08-23 | [14 empty] | 2016-09-29 | 2016-10-14 |  | Y
Central Hudson |  | New York State Solar Farm | CH-00454 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8092 | Fishkill Plains | N |  | 11 | [13 empty] | NM | N | SMA AMERICA SB TL 5000 SMA AMERICA SB TL 6000 | 2016-08-17 | 2016-08-22 | 3 | 2016-08-22 | [14 empty] | 2016-10-10 | 2016-10-13 |  | Y
Central Hudson |  | NRG Home Solar | CH-00527 | Kingston | Port Ewen | Ulster | 12466 | G | 1012 | Boulevard | N |  | 5.37 | [13 empty] | NM | N | ENPHASE M-215 (25) | 2016-08-17 | 2016-08-23 | 4 | 2016-08-23 | [14 empty] | 2016-10-04 | 2016-10-04 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00988 | Kingston | Saugerties | Ulster | 12477 | G | 3004 | Saugerties | N |  | 6.88 | [13 empty] | NM | N | ENPHASE 215 (32) | 2016-08-23 | 2016-08-24 | 1 | 2016-08-24 | [14 empty] | 2017-01-03 | 2017-01-03 |  | Y
Central Hudson |  | Direct Energy Solar | CH-01053 | Kingston | Saugerties |  | 12477 | G | 3003 | Saugerties | N |  | 4.3 | [13 empty] | NM | N | ENPHASE 215 (20) | 2016-08-17 | 2016-08-23 | 4 | 2016-08-23 | [17 empty] | W
Central Hudson |  | SolarCity | CH-05330 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8023 | Knapps Corners | N |  | 5 | [13 empty] | NM | N | ABB PVI 5 | 2016-08-17 | 2016-08-22 | 3 | 2016-08-22 | [14 empty] | 2016-11-15 | 2016-11-15 |  | Y
Central Hudson |  | SolarCity | CH-05472 | Kingston | Kingston | Ulster | 12401 | G | 1022 | East Kingston | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2016-08-17 | 2016-08-23 | 4 | 2016-08-23 | [14 empty] | 2016-09-15 | 2016-09-15 |  | Y
Central Hudson |  | SolarCity | CH-06579 | Kingston | Saugerties | Ulster | 12477 | G | 3001 | Saugerties | N |  | 9 | [13 empty] | NM | N | ABB PVI-6000-OUTD ABB PVI-3.0-OUTD-S | 2016-08-17 | 2016-08-23 | 4 | 2016-08-23 | [14 empty] | 2016-10-18 | 2016-10-18 |  | Y
Central Hudson |  | SolarCity | CH-06783 | Newburgh | Highland | Ulster | 12528 | G | 5081 | Highland | N |  | 5 | [13 empty] | NM | N | ABB PVI 5000 | 2016-08-17 | 2016-08-22 | 3 | 2016-08-22 | [14 empty] | 2016-10-12 | 2016-10-17 |  | Y
Central Hudson |  | Trinity Solar | CH-08365 | Kingston |  |  | 12481 | G | 3011 | Woodstock | TBD |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A-US | 2016-08-17 | 2016-08-23 | 4 | 2016-08-23 | [17 empty] | W
Central Hudson |  | New York State Solar Farm | CH-00361 | Newburgh | Highland | Ulster | 12528 | G | 5081 | Highland | N |  | 7.68 | [13 empty] | NM | N | SUNPOWER 327-C-AC (24) | 2016-08-18 | 2016-08-24 | 4 | 2016-08-24 | [14 empty] | 2016-10-05 | 2016-10-18 |  | Y
Central Hudson |  | New York State Solar Farm | CH-00386 | Kingston | Saugerties | Ulster | 12477 | G | 3002 | Saugerties | N |  | 6 | [13 empty] | NM | N | SMA AMERICA SB3000 (2) | 2016-08-25 | 2016-08-29 | 2 | 2016-08-29 | [14 empty] | 2016-10-31 | 2016-10-31 |  | Y
Central Hudson |  | New York State Solar Farm | CH-00424 | Kingston | Saugerties | Ulster | 12477 | G | 3002 | Saugerties | N |  | 6 | [13 empty] | NM | N | SMA AMERICA SB6000 | 2016-08-18 | 2016-08-23 | 3 | 2016-08-23 | [14 empty] | 2016-10-10 | 2016-10-13 |  | Y
Central Hudson |  | NRG Home Solar | CH-00501 | Kingston | Kingston | Ulster | 12401 | G | 1022 | East Kingston | N |  | 4.3 | [13 empty] | NM | N | ENPHASE M-215 (20) | 2016-08-18 | 2016-08-23 | 3 | 2016-08-23 | [14 empty] | 2017-01-10 | 2017-01-10 |  | Y
Central Hudson |  | NRG Home Solar | CH-00559 | Fishkill | Beacon | Dutchess | 12508 | G | 8017 | Forgebrook | N |  | 3.22 | [13 empty] | NM | N | ENPHASE M-215 (15) | 2016-08-18 | 2016-08-23 | 3 | 2016-08-23 | [14 empty] | 2016-10-10 | 2016-10-13 |  | Y
Central Hudson |  | NRG Home Solar | CH-00572 | Fishkill |  |  | 12527 | G | 8015 | Forgebrook | TBD |  | 3.01 | [13 empty] | NM | N | ENPHASE M215 (14) | 2016-08-18 | 2016-08-23 | 3 | 2016-08-23 | [17 empty] | W
Central Hudson |  | SolarCity | CH-05375 | Kingston | Lk Katrine | Ulster | 12449 | G | 2011 | Lincoln Park | N |  | 3 | [13 empty] | NM | N | SOLAREDGE SE 3000A | 2016-08-18 | 2016-08-23 | 3 | 2016-08-23 | [14 empty] | 2016-09-22 | 2016-09-23 |  | Y
Central Hudson |  | SolarCity | CH-07112 | Newburgh | Cornwall | Orange | 12518 | G | 4041 | Union Ave | N |  | 15.2 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 (2) | 2016-08-31 | 2016-08-31 | 0 | 2016-08-31 | [14 empty] | 2016-09-08 | 2016-10-11 |  | Y
Central Hudson |  | Sunrun Inc. | CH-08332 | Newburgh | New Windsor | Orange | 12553 | G | 4044 | Union Ave | N |  | 7.8 | [13 empty] | NM | N | ABB PVI-3.6-OUTD-S-US-A ABB PVI-4.2-OUTD-S-US-A | 2016-08-18 | 2016-08-23 | 3 | 2016-08-23 | [14 empty] | 2016-10-07 | 2016-10-10 |  | Y
Central Hudson |  | Lighthouse Solar | CH-00284 | Kingston | Hurley | Ulster | 12443 | G | 2094 | Hurley Ave | N |  | 6 | [13 empty] | NM | N | SOLAREDGE 7600 A-US | 2016-08-19 | 2016-08-23 | 2 | 2016-08-23 | [14 empty] | 2016-11-04 | 2016-11-04 |  | Y
Central Hudson |  | Lighthouse Solar | CH-00304 | Kingston | W Hurley | Ulster | 12491 | G | 3013 | Woodstock | N |  | 5 | [13 empty] | NM | N | SOLAREDGE 5000 A-US | 2016-08-19 | 2016-08-23 | 2 | 2016-08-23 | [14 empty] | 2017-02-02 | 2017-02-02 |  | Y
Central Hudson |  | NRG Home Solar | CH-00490 | Poughkeepsie | Poughquag | Dutchess | 12570 | G | 6055 | Todd Hill | N |  | 5.59 | [13 empty] | NM | N | ENPHASE M-215 (26) | 2016-08-19 | 2016-08-23 | 2 | 2016-08-23 | [14 empty] | 2016-12-19 | 2016-12-22 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00944 | Poughkeepsie | Tivoli | Dutchess | 12583 | G | 7062 | Milan | N |  | 14 | [13 empty] | NM | N | ENPHASE M250 60-2LL-S22 (56) | 2016-08-19 | 2016-08-23 | 2 | 2016-08-23 | [14 empty] | 2016-11-10 | 2016-11-15 |  | Y
Central Hudson |  | PosiGen Solar | CH-02889 | Catskill | Coxsackie | Greene | 12051 | G | 1072 | Coxsackie | N |  | 6.88 | [13 empty] | NM | N | ENPHASE M215-60-2LL-S22-IG (32) | 2016-08-19 | 2016-08-24 | 3 | 2016-08-24 | [14 empty] | 2016-09-09 | 2016-09-14 |  | Y
Central Hudson |  | SolarCity | CH-06410 | Newburgh | Campbell Hall | Orange | 10916 | G | 5051 | Maybrook | N | CH-06410 | 3 | [13 empty] | NM | N | ABB PVI-3.0 OUTD-S-US | 2016-08-19 | 2016-08-23 | 2 | 2016-08-23 | [14 empty] | 2016-10-18 | 2016-11-01 |  | Y
Central Hudson |  | SolarCity | CH-07783 | Fishkill | Beacon | Dutchess | 12508 | G | 8016 | Forgebrook | N |  | 12 | [13 empty] | NM | N | ABB PVI 6000 (2) | 2016-08-19 | 2016-08-23 | 2 | 2016-08-23 | [14 empty] | 2016-11-01 | 2016-11-01 |  | Y
Central Hudson |  | Trinity Solar | CH-08472 | Kingston | Hurley | Ulster | 12443 | G | 2094 | Hurley Ave | N |  | 10 | [13 empty] | NM | N | SOLAREDGE SE1000A-US | 2016-08-23 | 2016-08-24 | 1 | 2016-08-24 | [14 empty] | 2016-11-09 | 2016-11-09 |  | Y
Central Hudson |  | Trinity Solar | CH-08596 | Newburgh |  |  | 12550 | G | 4014 | West Balmville | TBD |  | 10 | [13 empty] | NM | N | SOLAREDGE SE1000A-US | 2016-08-19 | 2016-08-23 | 2 | 2016-08-23 | [17 empty] | W
Central Hudson |  | NRG Home Solar | CH-00569 | Poughkeepsie |  |  | 12603 | G | 6092 | Manchester | TBD |  | 3.87 | [13 empty] | NM | N | ENPHASE M-215 (18) | 2016-08-24 | 2016-08-25 | 1 | 2016-08-25 | [17 empty] | W
Central Hudson |  | Direct Energy Solar | CH-01071 | Kingston | Kingston | Ulster | 12401 | G | 2016 | Lincoln Park | N |  | 2.58 | [13 empty] | NM | N | ENPHASE M215 (12) | 2016-08-22 | 2016-08-23 | 1 | 2016-08-23 | [14 empty] | 2016-11-16 | 2016-11-23 |  | Y
Central Hudson |  | PosiGen Solar | CH-02892 | Kingston | Port Ewen | Ulster | 12466 | G | 1012 | Boulevard | N |  | 3.87 | [13 empty] | NM | N | ENPHASE M215-60-2LL-S22-IG (18) | 2016-08-26 | 2016-08-26 | 0 | 2016-08-26 | [14 empty] | 2016-09-06 | 2016-09-06 |  | Y
Central Hudson |  | SolarCity | CH-05664 | Kingston | Kingston | Ulster | 12401 | G | 1024 | East Kingston | N |  | 10.2 | [13 empty] | NM | N | ABB PVI 6000 ABB PVI 4.2 | 2016-08-22 | 2016-08-24 | 2 | 2016-08-24 | [14 empty] | 2016-10-14 | 2016-10-17 |  | Y
Central Hudson |  | SolarCity | CH-07161 | Newburgh | New Windsor | Orange | 12553 | G | 4095 | Bethlehem Rd | N |  | 6 | [13 empty] | NM | N | ABB PVI 6000 | 2016-08-22 | 2016-08-23 | 1 | 2016-08-23 | [14 empty] | 2016-11-15 | 2016-11-22 |  | Y
Central Hudson |  | Trinity Solar | CH-08513 | Newburgh | Walden | Orange | 12586 | G | 5041 | East Walden | N |  | 6 | [13 empty] | NM | N | SOLAR EDGE SE6000A-US | 2016-08-25 | 2016-08-26 | 1 | 2016-08-26 | [14 empty] | 2016-11-30 | 2016-11-30 |  | Y
Central Hudson |  | Hudson Solar | CH-02530 | Poughkeepsie |  |  | 12572 | G | 7053 | Rhinebeck | TBD |  | 97 | [13 empty] | NM | N | (5) SOLAREDGE SE11400A-US (4) SOLAREDGE SE10000A -US | 2016-10-05 | 2016-10-18 | 9 | 2016-10-18 | 2016-10-18 | 2016-11-04 | 13 |  |  |  |  | 28000 | [9 empty] | W
Central Hudson |  | PosiGen Solar | CH-02915 | Kingston | Kerhonkson |  | 12446 | G | 3082 | Kerhonkson | N |  | 5.16 | [13 empty] | NM | N | ENPHASE M215-60-2LL-S22-IG (24) | 2016-08-23 | 2016-08-24 | 1 | 2016-08-24 | [17 empty] | W
Central Hudson |  | SolarCity | CH-06806 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8043 | Myers Corners | N |  | 5 | [13 empty] | NM | N | ABB PVI-5000 | 2016-08-23 | 2016-08-24 | 1 | 2016-08-24 | [14 empty] | 2016-10-18 | 2016-10-25 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08610 | Kingston |  |  | 12481 | G | 3011 | Woodstock | TBD |  | 12.68 | [13 empty] | NM | N | ENPHASE M215 (59) | 2016-08-25 | 2016-08-26 | 1 | 2016-08-26 | [17 empty] | W
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08611 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7061 | Milan | N |  | 3.01 | [13 empty] | NM | N | ENPHASE M215 (14) | 2016-08-23 | 2016-08-24 | 1 | 2016-08-24 | [14 empty] | 2016-12-16 | 2016-12-19 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08616 | Fishkill | Putnam Valley | Putnam | 10524 | G | 8066 | Merritt Park | N |  | 5.59 | [13 empty] | NM | N | ENPHASE M215 (26) | 2016-08-23 | 2016-08-24 | 1 | 2016-08-24 | [14 empty] | 2016-11-08 | 2016-11-08 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08640 | Catskill | Purling | Greene | 12470 | G | 2041 | South Cairo | N |  | 6.45 | [13 empty] | NM | N | ENPHASE M215 (30) | 2016-08-23 | 2016-08-24 | 1 | 2016-08-24 | [14 empty] | 2016-12-19 | 2016-12-29 |  | Y
Central Hudson |  | Sun Mountain | CH-09092 | Kingston | Kerhonkson | Ulster | 12446 | G | 3082 | Kerhonkson | N |  | 6 | [13 empty] | NM | N | SMA AMERICA 6.0-US | 2016-08-29 | 2016-08-30 | 1 | 2016-08-30 | [14 empty] | 2016-12-01 | 2016-12-02 |  | Y
Central Hudson |  | NRG Home Solar | CH-00500 | Kingston | Accord | Ulster | 12404 | G | 3024 | High Falls | N |  | 13.11 | [13 empty] | NM | N | ENPHASE M-215 (61) | 2016-08-24 | 2016-08-25 | 1 | 2016-08-25 | [14 empty] | 2016-12-12 | 2016-12-12 |  | Y
Central Hudson |  | Hudson Solar | CH-01301 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7042 | Staatsburg | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE-7600A-US | 2016-08-25 | 2016-08-25 | 0 | 2016-08-25 | [14 empty] | 2017-02-22 | 2017-03-02 |  | Y
Central Hudson |  | Hudson Solar | CH-01452 | Newburgh | Montgomery | Orange | 12549 | G | 5054 | Maybrook | N |  | 10 | [13 empty] | NM | N | SOLAREDGE SE-10000A-US | 2016-08-25 | 2016-08-25 | 0 | 2016-08-25 | [14 empty] | 2016-10-06 | 2016-10-21 |  | Y
Central Hudson |  | PosiGen Solar | CH-02918 | Newburgh | Newburgh | Orange | 12550 | G | 4024 | Coldenham | N |  | 5.16 | [13 empty] | NM | N | ENPHASE M215-60-2LL-S22-IG (24) | 2016-08-24 | 2016-08-26 | 2 | 2016-08-26 | [14 empty] | 2016-11-29 | 2016-11-29 |  | Y
Central Hudson |  | SolarCity | CH-06723 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 6051 | Todd Hill | N |  | 4.2 | [13 empty] | NM | N | ABB PVI-4.2 OUTD-S-US | 2016-09-06 | 2016-09-15 | 7 | 2016-09-15 | [14 empty] | 2016-09-16 | 2016-09-19 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Infinity Solar Systems | CH-00178 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8092 | Fishkill Plains | N |  | 8.32 | [13 empty] | NM | N | SUNPOWER SPR-E20-327 C-AC (26) | 2016-08-25 | 2016-08-26 | 1 | 2016-08-26 | [14 empty] | 2016-11-17 | 2016-11-18 |  | Y
Central Hudson |  | NRG Home Solar | CH-00499 | Kingston | Tillson | Ulster | 12486 | G | 3021 | High Falls | N |  | 3.65 | [13 empty] | NM | N | ENPHASE M-215 (17) | 2016-08-25 | 2016-08-26 | 1 | 2016-08-26 | [14 empty] | 2016-09-20 | 2016-09-20 |  | Y
Central Hudson |  | NRG Home Solar | CH-00574 | Newburgh |  |  | 12553 | G | 4046 | Union Ave | TBD |  | 4.94 | [13 empty] | NM | N | ENPHASE M-215 (23) | 2016-08-29 | 2016-08-29 | 0 | 2016-08-29 | [17 empty] | W
Central Hudson |  | Direct Energy Solar | CH-00943 | Poughkeepsie | Tivoli | Dutchess | 12583 | G | 7062 | Milan | N |  | 6.45 | [13 empty] | NM | N | ENPHASE M215 60-2LL-S22 (30) | 2016-08-25 | 2016-08-26 | 1 | 2016-08-26 | [14 empty] | 2016-10-18 | 2016-10-18 |  | Y
Central Hudson |  | PosiGen Solar | CH-02863 | Fishkill |  |  | 12533 | G | 8095 | Fishkill Plains | TBD |  | 3.87 | [13 empty] | NM | N | ENPHASE M215-60-2LL-S22-IG (18) | 2016-09-12 | 2016-09-16 | 4 | 2016-09-16 | [17 empty] | W
Central Hudson |  | SolarCity | CH-05279 | Fishkill | Beacon | Dutchess | 12508 | G | 8087 | Tioronda | N |  | 3 | [13 empty] | NM | N | ABB PVI-3.0 OUTD-S-US | 2016-08-25 | 2016-08-26 | 1 | 2016-08-26 | [14 empty] | 2016-10-14 | 2016-10-19 |  | Y
Central Hudson |  | SolarCity | CH-05713 | Kingston | Saugerties | Ulster | 12477 | G | 3003 | Saugerties | N |  | 4.2 | [13 empty] | NM | N | ABB PVI 4.2 | 2016-08-25 | 2016-08-26 | 1 | 2016-08-26 | [14 empty] | 2016-12-20 | 2016-12-22 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08819 | Kingston |  |  | 12401 | G | 2013 | Lincoln Park | TBD |  | 7.95 | [13 empty] | NM | N | ENPHASE M215 602LLS22IG | 2016-08-25 | 2016-08-26 | 1 | 2016-08-26 | [17 empty] | W
Central Hudson |  | NRG Home Solar | CH-00556 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 6074 | East Park | N |  | 10.32 | [13 empty] | NM | N | ENPHASE M-215 (48) | 2016-08-26 | 2016-08-26 | 0 | 2016-08-26 | [8 empty] | 350 | 350 |  | 2016-10-26 | 2016-10-26 | 2017-01-06 | 2017-03-03 | 2017-03-03 |  | Y
Central Hudson |  | PosiGen Solar | CH-02880 | Kingston | Kerhonkson | Ulster | 12446 | G | 3083 | Kerhonkson | N |  | 3.87 | [13 empty] | NM | N | ENPHASE M215-60-2LL-S22-IG (18) | 2016-08-26 | 2016-08-26 | 0 | 2016-08-26 | [14 empty] | 2016-09-21 | 2016-09-22 |  | Y
Central Hudson |  | PosiGen Solar | CH-02888 | Catskill | Earlton |  | 12058 | G | 1071 | Coxsackie | N |  | 3.87 | [13 empty] | NM | N | ENPHASE M215-60-2LL-S22-IG | 2016-08-26 | 2016-08-26 | 0 | 2016-08-26 | [17 empty] | W
Central Hudson |  | PosiGen Solar | CH-02903 | Catskill |  |  | 12427 | G | 2385 | Lawrenceville | TBD |  | 6.88 | [13 empty] | NM | N | ENPHASE M215-60-2LL-S22-IG (32) | 2016-08-26 | 2016-08-26 | 0 | 2016-08-26 | [17 empty] | W
Central Hudson |  | PosiGen Solar | CH-02906 | Catskill | Cornwallvl | Greene | 12418 | G | 2043 | South Cairo | N |  | 5.16 | [13 empty] | NM | N | ENPHASE M215-60-2LL-S22-IG (24) | 2016-08-26 | 2016-08-26 | 0 | 2016-08-26 | [14 empty] | 2016-09-27 | 2016-09-28 |  | Y
Central Hudson |  | PosiGen Solar | CH-02909 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6065 | Inwood Ave | N |  | 5.16 | [13 empty] | NM | N | ENPHASE M215 (24) | 2016-08-26 | 2016-08-26 | 0 | 2016-08-26 | [14 empty] | 2016-10-07 | 2016-10-14 |  | Y
Central Hudson |  | SolarCity | CH-05000 | Kingston | Kingston | Ulster | 12401 | G | 2013 | Lincoln Park | N |  | 13 | [13 empty] | NM | N | FRONIUS IG PLUS 10.0 ABB PVI-3.0 OUTD-US | 2016-09-02 | 2016-09-15 | 8 | 2016-09-15 | [14 empty] | 2016-10-20 | 2016-10-20 |  | Y
Central Hudson |  | SolarCity | CH-05787 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6045 | Spackenkill | N |  | 11.8 | [13 empty] | NM | N | DELTA SOLIVIA 5.2 DELTA SOLIVIA 6.6 | 2016-08-26 | 2016-08-26 | 0 | 2016-08-26 | [14 empty] | 2016-10-14 | 2016-10-17 |  | Y
Central Hudson |  | SolarCity | CH-05909 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6096 | Manchester | N |  | 3 | [13 empty] | NM | N | ABB PVI 3.0 | 2016-08-26 | 2016-08-26 | 0 | 2016-08-26 | [14 empty] | 2016-10-28 | 2016-10-31 |  | Y
Central Hudson |  | SolarCity | CH-06688 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 7041 | Staatsburg | N |  | 10.2 | [13 empty] | NM | N | ABB PVI 6000 ABB PVI 4.2 | 2016-08-26 | 2016-08-26 | 0 | 2016-08-26 | [14 empty] | 2016-12-06 | 2016-12-06 |  | Y
Central Hudson |  | SolarCity | CH-07775 | Newburgh | Montgomery | Orange | 12549 | G | 5072 | Montgomery | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2016-09-06 | 2016-09-06 | 0 | 2016-09-06 | [14 empty] | 2016-10-18 | 2016-10-31 |  | Y
Central Hudson |  | Trinity Solar | CH-08382 | Catskill |  |  | 12444 | E | 2389 | Vinegar Hill | TBD |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE7600A-US | 2016-08-29 | 2016-08-29 | 0 | 2016-08-29 | [17 empty] | W
Central Hudson |  | Sungevity Inc | CH-09241 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6092 | Manchester | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE 7600A-US | 2016-08-29 | 2016-08-29 | 0 | 2016-08-29 | [14 empty] | 2016-10-11 | 2016-10-14 |  | Y
Central Hudson |  | New York State Solar Farm | CH-03927 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 6051 | Todd Hill | N |  | 7.04 | [13 empty] | NM | N | SUNPOWER SPR-E20327-C-AC (22) | 2016-08-29 | 2016-09-13 | 10 | 2016-09-13 | [14 empty] | 2016-10-18 | 2016-11-02 |  | Y
Central Hudson |  | New York State Solar Farm | CH-00398 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8046 | Myers Corners | N |  | 4.16 | [13 empty] | NM | N | SUNPOWER SPR-E20 327-C-AC (13) | 2016-08-29 | 2016-08-29 | 0 | 2016-08-29 | [14 empty] | 2016-10-24 | 2016-11-07 |  | Y
Central Hudson |  | New York State Solar Farm | CH-00460 | Newburgh | Wallkill | Ulster | 12589 | G | 5043 | East Walden | N |  | 6.08 | [13 empty] | NM | N | SUNPOWER SPR-E20327-C-AC (19) | 2016-08-29 | 2016-08-30 | 1 | 2016-08-30 | [14 empty] | 2016-10-13 | 2016-10-21 |  | Y
Central Hudson |  | SolarCity | CH-07470 | Newburgh | Rock Tvrn | Orange | 12575 | G | 4097 | Bethlehem Rd | N |  | 6 | [13 empty] | NM | N | ABB PVI-6000OUTD-US | 2016-09-06 | 2016-09-06 | 0 | 2016-09-06 | [14 empty] | 2016-09-07 | 2016-09-09 |  | Y
Central Hudson |  | SolarCity | CH-07827 | Newburgh | Newburgh | Orange | 12550 | G | 5004 | Marlboro | N | CH-05070 | 3.6 | [13 empty] | NM | N | ABB PVI-3.6 OUTD-US | 2016-09-02 | 2016-09-02 | 0 | 2016-09-02 | [14 empty] | 2016-10-03 | 2016-10-04 |  | Y
Central Hudson |  | Trinity Solar | CH-08439 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8093 | Fishkill Plains | N |  | 7.6 | [13 empty] | NM | N | SOLAR EDGE SE7600 | 2016-08-29 | 2016-08-29 | 0 | 2016-08-29 | [14 empty] | 2017-03-16 | 2017-03-17 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-00053 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8023 | Knapps Corners | N | CH-00053 | 11.4 | [13 empty] | NM | N | SOLAREDGE 11400A | 2016-08-30 | 2016-08-30 | 0 | 2016-08-30 | [14 empty] | 2016-09-29 | 2016-10-06 |  | Y
Central Hudson |  | American Energy Care | CH-00659 | Catskill | Westerlo | Albany | 12193 | G | 1091 | Westerlo | N |  | 7.6 | [13 empty] | NM | N | SolarEdge SE7600A | 2016-09-08 | 2016-09-22 | 10 | 2016-09-22 | [14 empty] | 2017-01-13 | 2017-01-13 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00918 | Kingston | Saugerties | Ulster | 12477 | G | 3001 | Saugerties | N |  | 5.25 | [13 empty] | NM | N | ENPHASE M250 2LL-S22 (21) | 2016-09-12 | 2016-09-16 | 4 | 2016-09-16 | [14 empty] | 2016-11-30 | 2016-11-30 |  | Y
Central Hudson |  | SolarCity | CH-05223 | Newburgh | Newburgh | Orange | 12550 | G | 4012 | West Balmville | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2016-08-30 | 2016-08-30 | 0 | 2016-08-30 | [14 empty] | 2016-10-14 | 2016-10-21 |  | Y
Central Hudson |  | SolarCity | CH-05415 | Kingston | Kingston | Ulster | 12401 | G | 3021 | High Falls | N |  | 7.2 | [13 empty] | NM | N | ABB PVI 4.2 ABB PVI 3.0 | 2016-08-30 | 2016-08-30 | 0 | 2016-08-30 | [14 empty] | 2017-10-09 | 2017-10-09 |  | Y
Central Hudson |  | SolarCity | CH-05740 | Kingston | Saugerties | Ulster | 12477 | G | 3001 | Saugerties | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A | 2016-09-02 | 2016-09-02 | 0 | 2016-09-02 | [14 empty] | 2016-10-14 | 2016-10-19 |  | Y
Central Hudson |  | SolarCity | CH-06999 | Newburgh | Newburgh | Orange | 12550 | G | 5041 | East Walden | N |  | 8 | [13 empty] | NM | N | ABB PVI 5000 ABB PVI 3.0 | 2016-09-07 | 2016-09-08 | 1 | 2016-09-08 | [14 empty] | 2016-10-14 | 2016-10-17 |  | Y
Central Hudson |  | SolarCity | CH-07162 | Newburgh | New Windsor | Orange | 12553 | G | 4095 | Bethlehem Rd | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2016-08-30 | 2016-08-30 | 0 | 2016-08-30 | [14 empty] | 2016-11-09 | 2016-11-14 |  | Y
Central Hudson |  | SolarCity | CH-07868 | Kingston |  |  | 12401 | G | 1021 | East Kingston | TBD |  | 5 | [13 empty] | NM | N | ABB PVI-5000 OUTD-US | 2016-09-02 | 2016-09-02 | 0 | 2016-09-02 | [17 empty] | W
Central Hudson |  | Trinity Solar | CH-08374 | Newburgh | Newburgh | Orange | 12550 | G | 4023 | Coldenham | N |  | 10 | [13 empty] | NM | N | SOLAR EDGE SE 10000 | 2016-08-30 | 2016-08-30 | 0 | 2016-08-30 | [14 empty] | 2017-03-01 | 2017-03-06 |  | Y
Central Hudson |  | Sungevity Inc | CH-09616 | Catskill |  |  | 12427 | G | 2385 | Lawrenceville | TBD |  | 5 | [13 empty] | NM | N | SOLAREDGE SE 5000A-US | 2016-08-30 | 2016-08-30 | 0 | 2016-08-30 | [17 empty] | W
Central Hudson |  | Malcarne Contracting | CH-03910 | Poughkeepsie | Ancram | Columbia | 12502 | G | 7085 | Ancram | N |  | 3 | [13 empty] | NM | N | SOLAREDGE SE3000A | 2016-08-31 | 2016-08-31 | 0 | 2016-08-31 | [14 empty] | 2016-10-24 | 2016-10-24 |  | Y
Central Hudson |  | NRG Home Solar | CH-00561 | Newburgh | Marlboro | Ulster | 12542 | G | 5004 | Marlboro | N |  | 6.02 | [13 empty] | NM | N | ENPHASE M-215 (28) | 2016-08-31 | 2016-08-31 | 0 | 2016-08-31 | [14 empty] | 2016-11-28 | 2016-11-28 |  | Y
Central Hudson |  | Direct Energy Solar | CH-01052 | Kingston | Napanoch | Ulster | 12458 | G | 3071 | Honk Falls | N |  | 6.45 | [13 empty] | NM | N | ENPHASE M215 60-2LL-S22 (30) | 2016-08-31 | 2016-08-31 | 0 | 2016-08-31 | [14 empty] | 2016-10-04 | 2016-10-11 |  | Y
Central Hudson |  | Hudson Valley Wind Energy, LLC | CH-02542 | Kingston | Kingston | Ulster | 12401 | G | 1003 | Jansen Ave | N |  | 22.8 | [13 empty] | NM | N | (2) Fronius Primo 11.4-1 | 2016-09-21 | 2016-10-05 | 10 | 2016-10-05 | [14 empty] | 2016-12-28 | 2016-12-28 |  | Y
Central Hudson |  | Hudson Valley Wind Energy, LLC | CH-02544 | Kingston | Kingston | Ulster | 12401 | G | 1003 | Jansen Ave | N |  | 40 | [13 empty] | RNM | N | (4) Fronius Primo 10.0-1 | 2016-10-06 | 2016-10-20 | 10 | 2016-10-20 | [8 empty] | 4771 | 4239.2873 |  | 2016-12-02 | 2016-12-02 | 2016-12-21 | 2016-12-28 | 2016-12-28 |  | Y
Central Hudson |  | SolarCity | CH-06520 | Kingston |  |  | 12466 | G | 1024 | East Kingston | TBD |  | 6 | [13 empty] | NM | N | ABB PVI 6000 | 2016-08-31 | 2016-08-31 | 0 | 2016-08-31 | [17 empty] | W
Central Hudson |  | SolarCity | CH-07217 | Kingston | Port Ewen | Ulster | 12466 | G | 1012 | Boulevard | N |  | 3.6 | [13 empty] | NM | N | ABB PVI 3.6 | 2016-08-31 | 2016-08-31 | 0 | 2016-08-31 | [14 empty] | 2016-12-08 | 2016-12-08 |  | Y
Central Hudson |  | Sunrun Inc. | CH-08324 | Newburgh | Cornwall | Orange | 12518 | G | 4093 | Bethlehem Rd | N |  | 3 | [13 empty] | NM | N | ABB PVI-3.0-OUTD-S-US-A | 2016-09-01 | 2016-09-01 | 0 | 2016-09-01 | [14 empty] | 2016-11-03 | 2016-11-03 |  | Y
Central Hudson |  | Trinity Solar | CH-08424 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7062 | Milan | N |  | 5 | [13 empty] | NM | N | SOLAR EDGE SE5000A | 2016-08-31 | 2016-08-31 | 0 | 2016-08-31 | [14 empty] | 2016-11-10 | 2016-11-10 |  | Y
Central Hudson |  | Kasselman Solar | CH-00255 | Catskill | Greenvl | Greene | 12083 | G | 2061 | Freehold | N | CH-05563 | 5.5 | [13 empty] | NM | N | ENPHASE M250 (22) | 2016-09-06 | 2016-09-06 | 0 | 2016-09-06 | [14 empty] | 2016-09-22 | 2016-09-26 |  | Y
Central Hudson |  | SolarCity | CH-05676 | Kingston | W Hurley | Ulster | 12491 | G | 3013 | Woodstock | N |  | 5 | [13 empty] | NM | N | ABB PVI 5000 | 2016-09-01 | 2016-09-01 | 0 | 2016-09-01 | [14 empty] | 2016-11-03 | 2016-11-09 |  | Y
Central Hudson |  | SolarCity | CH-06560 | Kingston | Ellenvl | Ulster | 12428 | G | 3095 | Grimley Rd | N |  | 23.4 | [13 empty] | NM | N | FRONIUS PRIMO 8.2 FRONIUS PRIMO 7.6 (2) | 2016-09-01 | 2016-09-01 | 0 | 2016-09-01 | [8 empty] | 350 | 350 |  | 2016-10-21 | 2016-10-21 | 2016-11-09 | 2016-12-01 | 2016-12-02 |  | Y
Central Hudson |  | SolarCity | CH-07695 | Kingston | Ulster Park | Ulster | 12487 | G | 1014 | Boulevard | N |  | 8.4 | [13 empty] | NM | N | ABB PVI 4.2 (2) | 2016-09-01 | 2016-09-01 | 0 | 2016-09-01 | [14 empty] | 2017-01-04 | 2017-01-04 |  | Y
Central Hudson |  | Trinity Solar | CH-08514 | Newburgh | Newburgh | Orange | 12550 | G | 4044 | Union Ave | N |  | 6 | [13 empty] | NM | N | SOLAR EDGE SE6000A-US | 2016-09-01 | 2016-09-16 | 10 | 2016-09-16 | [14 empty] | 2017-08-18 | 2017-08-18 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00914 | Kingston | Saugerties | Ulster | 12477 | G | 3014 | Woodstock | N |  | 4.94 | [13 empty] | NM | N | ENPHASE 215 (23) | 2016-09-06 | 2016-09-06 | 0 | 2016-09-06 | [14 empty] | 2016-10-10 | 2016-10-13 |  | Y
Central Hudson |  | Murphy Solar Power | CH-02723 | Catskill | E Durham | Greene | 12423 | G | 2043 | South Cairo | N |  | 5 | [13 empty] | NM | N | FRONIUS PRIMO 5000 | 2016-09-02 | 2016-09-02 | 0 | 2016-09-02 | [14 empty] | 2016-10-13 | 2016-10-18 |  | Y
Central Hudson |  | SolarCity | CH-05126 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6096 | Manchester | N |  | 10.2 | [13 empty] | NM | N | ABB PVI 6000 ABB PVI 4.2 | 2016-09-02 | 2016-09-02 | 0 | 2016-09-02 | [14 empty] | 2016-11-10 | 2016-11-23 |  | Y
Central Hudson |  | SolarCity | CH-05284 | Newburgh | New Paltz | Ulster | 12561 | G | 5024 | Ohioville | N |  | 6 | [13 empty] | NM | N | ABB PVI 6000 | 2016-09-02 | 2016-09-02 | 0 | 2016-09-02 | [14 empty] | 2016-10-17 | 2016-10-18 |  | Y
Central Hudson |  | SolarCity | CH-05570 | Catskill | Westerlo | Albany | 12193 | G | 1091 | Westerlo | N |  | 8.2 | [13 empty] | NM | N | FRONIUS PRIMO 8.2 | 2016-09-02 | 2016-09-02 | 0 | 2016-09-02 | [14 empty] | 2016-11-10 | 2016-11-15 |  | Y
Central Hudson |  | SolarCity | CH-05646 | Kingston | Hurley | Ulster | 12443 | G | 2093 | Hurley Ave | N |  | 12 | [13 empty] | NM | N | ABB PVI 6000 (2) | 2016-09-02 | 2016-09-15 | 8 | 2016-09-15 | [14 empty] | 2016-10-18 | 2016-10-18 |  | Y
Central Hudson |  | SolarCity | CH-05761 | Kingston | Kingston | Ulster | 12401 | G | 1021 | East Kingston | N |  | 8.2 | [13 empty] | NM | N | FRONIUS PRIMO 8.2 | 2016-09-09 | 2016-09-16 | 5 | 2016-09-16 | [14 empty] | 2016-10-17 | 2016-10-18 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06441 | Catskill | Jewett | Greene | 12444 | E | 2389 | Vinegar Hill | N |  | 5.2 | [13 empty] | NM | N | DELTA SOLIVIA 5.2 | 2016-09-02 | 2016-09-02 | 0 | 2016-09-02 | [14 empty] | 2016-11-09 | 2016-11-09 |  | Y
Central Hudson |  | SolarCity | CH-06791 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8091 | Fishkill Plains | N |  | 10 | [13 empty] | NM | N | ABB PVI 5000 (2) | 2016-09-02 | 2016-09-02 | 0 | 2016-09-02 | [14 empty] | 2016-10-14 | 2016-11-02 |  | Y
Central Hudson |  | SolarCity | CH-07201 | Kingston | Stone Ridge | Ulster | 12484 | G | 3023 | High Falls | N |  | 3.8 | [13 empty] | NM | N | SOLAREDGE SE3800A | 2016-09-15 | 2016-09-19 | 2 | 2016-09-19 | [14 empty] | 2016-11-03 | 2016-11-03 |  | Y
Central Hudson |  | SolarCity | CH-07621 | Newburgh | Maybrook | Orange | 12543 | G | 4026 | Coldenham | N |  | 4.2 | [13 empty] | NM | N | ABB PVI 4.2 | 2016-09-02 | 2016-09-02 | 0 | 2016-09-02 | [14 empty] | 2016-11-10 | 2016-11-10 |  | Y
Central Hudson |  | SolarCity | CH-07799 | Catskill | Purling | Greene | 12470 | G | 2042 | South Cairo | N | CH-05510 | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2016-09-07 | 2016-09-08 | 1 | 2016-09-08 | [14 empty] | 2016-11-02 | 2016-11-02 |  | Y
Central Hudson |  | Solar Generation | CH-08104 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7051 | Rhinebeck | N |  | 6 | [13 empty] | NM | N | SOLAREDGE 6000A | 2016-09-02 | 2016-09-02 | 0 | 2016-09-02 | [14 empty] | 2016-09-30 | 2016-10-03 |  | Y
Central Hudson |  | Solar Generation | CH-08120 | Catskill | Lexington | Greene | 12452 | E | 2389 | Vinegar Hill | N |  | 11.5 | [13 empty] | NM | N | SMA 7700TL SMA 3800TL | 2016-09-06 | 2016-09-08 | 2 | 2016-09-08 | [14 empty] | 2017-01-24 | 2017-01-24 |  | Y
Central Hudson |  | Solar Generation | CH-08122 | Kingston | W Hurley | Ulster | 12491 | G | 2094 | Hurley Ave | Y | CH-08122 | 10.6 | [13 empty] | NM | N | SOLAREDGE 7600A SOLAREDGE 3000A | 2016-09-02 | 2016-09-02 | 0 | 2016-09-02 | [14 empty] | 2016-11-01 | 2016-11-02 |  | Y
Central Hudson |  | NRG Home Solar | CH-04783 | Kingston | Kingston | Ulster | 12401 | G | 1013 | Boulevard | N |  | 3.65 | [13 empty] | NM | N | ENPHASE M-215 (17) | 2016-09-06 | 2016-09-06 | 0 | 2016-09-06 | [14 empty] | 2016-11-29 | 2016-12-07 |  | Y
Central Hudson |  | D&M Alternative Energy | CH-00817 | Catskill | Coxsackie | Greene | 12051 | G | 1072 | Coxsackie | N |  | 3.8 | [13 empty] | NM | N | FRONIUS PRIMO 3.8 | 2016-09-16 | 2016-09-20 | 2 | 2016-09-20 | [14 empty] | 2016-11-10 | 2016-11-10 |  | Y
Central Hudson |  | PosiGen Solar | CH-02895 | Poughkeepsie | Poughquag |  | 12570 | G | 6055 | Todd Hill | N |  | 3.87 | [13 empty] | NM | N | ENPHASE M215 (18) | 2016-09-06 | 2016-09-06 | 0 | 2016-09-06 | [17 empty] | W
Central Hudson |  | SolarCity | CH-05872 | Poughkeepsie | Millbrook | Dutchess | 12545 | G | 7025 | Tinkertown | N |  | 15.2 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 (2) | 2016-09-06 | 2016-09-08 | 2 | 2016-09-08 | [14 empty] | 2017-02-02 | 2017-02-10 |  | Y
Central Hudson |  | SolarCity | CH-06049 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8093 | Fishkill Plains | N |  | 16.4 | [13 empty] | NM | N | FRONIUS PRIMO 8.2 (2) | 2016-09-06 | 2016-09-08 | 2 | 2016-09-08 | [14 empty] | 2016-12-01 | 2016-12-01 |  | Y
Central Hudson |  | SolarCity | CH-06183 | Newburgh | Highland | Ulster | 12528 | G | 5024 | Ohioville | N |  | 6 | [13 empty] | NM | N | ABB PVI 6000 | 2016-09-06 | 2016-09-08 | 2 | 2016-09-08 | [14 empty] | 2017-01-25 | 2017-02-21 |  | Y
Central Hudson |  | SolarCity | CH-06338 | Newburgh | Gardiner | Ulster | 12525 | G | 5011 | Modena | N |  | 3 | [13 empty] | NM | N | ABB PVI 3.0 | 2016-09-06 | 2016-09-08 | 2 | 2016-09-08 | [14 empty] | 2016-11-03 | 2016-11-03 |  | Y
Central Hudson |  | SolarCity | CH-06565 | Kingston | Napanoch | Ulster | 12458 | G | 3091 | Neversink | N |  | 3.8 | [13 empty] | NM | N | DELTA SOLIVIA 3.8 | 2016-10-03 | 2016-10-05 | 2 | 2016-10-05 | [14 empty] | 2016-12-22 | 2016-12-22 |  | Y
Central Hudson |  | SolarCity | CH-06666 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6002 | Reynolds Hill | N |  | 6 | [13 empty] | NM | N | ABB PVI 6000 | 2016-09-06 | 2016-09-08 | 2 | 2016-09-08 | [14 empty] | 2016-11-10 | 2016-11-15 |  | Y
Central Hudson |  | SolarCity | CH-06680 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6073 | East Park | N |  | 11 | [13 empty] | NM | N | ABB PVI 6000 ABB PVI 5000 | 2016-09-06 | 2016-09-08 | 2 | 2016-09-08 | [14 empty] | 2016-11-16 | 2016-11-16 |  | Y
Central Hudson |  | SolarCity | CH-06736 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6002 | Reynolds Hill | N |  | 5 | [13 empty] | NM | N | ABB PVI 5000 | 2016-09-06 | 2016-09-15 | 7 | 2016-09-15 | [14 empty] | 2016-11-09 | 2016-11-09 |  | Y
Central Hudson |  | SolarCity | CH-06937 | Fishkill | Beacon | Dutchess | 12508 | G | 8085 | Tioronda | N |  | 5 | [13 empty] | NM | N | ABB PVI 5000 | 2016-09-06 | 2016-09-08 | 2 | 2016-09-08 | [14 empty] | 2016-12-02 | 2016-12-02 |  | Y
Central Hudson |  | SolarCity | CH-07335 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8091 | Fishkill Plains | N |  | 3 | [13 empty] | NM | N | ABB PVI-3.0 | 2016-09-21 | 2016-09-26 | 3 | 2016-09-26 | [14 empty] | 2016-09-29 | 2016-11-02 |  | Y
Central Hudson |  | Solar Generation | CH-08275 | Kingston | Woodstock | Ulster | 12498 | G | 3014 | Woodstock | N | CH-08275 | 6 | [13 empty] | NM | N | SOLAREDGE 6000AUS | 2016-09-06 | 2016-09-06 | 0 | 2016-09-06 | [14 empty] | 2016-10-13 | 2016-10-14 |  | Y
Central Hudson |  | Sunrun Inc. | CH-08327 | Fishkill | Poughkeepsie | Dutchess | 12603 | G | 8024 | Knapps Corners | N |  | 7.6 | [13 empty] | NM | N | ABB UNO-7.6-TL-OUTD-S-US | 2016-09-13 | 2016-09-16 | 3 | 2016-09-16 | [14 empty] | 2016-12-08 | 2016-12-08 |  | Y
Central Hudson |  | Trinity Solar | CH-08406 | Kingston | Kingston | Ulster | 12401 | G | 1021 | East Kingston | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE7600A | 2016-09-06 | 2016-09-20 | 10 | 2016-09-20 | [14 empty] | 2017-05-23 | 2017-05-23 |  | Y
Central Hudson |  | Green Street Power Partners, LLC | CH-00115 | Kingston | Ulster Pk | Ulster | 12487 | G | 1014 | Boulevard | N |  | 7.7 | [13 empty] | NM | N | SMA SB7700TL-US | 2016-09-07 | 2016-09-08 | 1 | 2016-09-08 | [14 empty] | 2016-10-10 | 2016-10-13 |  | Y
Central Hudson |  | NRG Home Solar | CH-00565 | Kingston |  |  | 12477 | G | 3003 | Saugerties | TBD |  | 4.51 | [13 empty] | NM | N | ENPHASE M-215 (21) | 2016-09-07 | 2016-09-08 | 1 | 2016-09-08 | [17 empty] | W
Central Hudson |  | OnForce Solar | CH-02819 | Poughkeepsie |  |  | 12540 | G | 6055 | Todd Hill | TBD |  | 1650 | [13 empty] | CDG | N | (55) SMA STP 30000TL-US | 2016-11-03 | 2016-11-03 | 0 | 2016-11-03 | 2016-11-03 | 2016-11-28 | 15 |  |  |  |  | 35000 | [9 empty] | W
Central Hudson |  | OnForce Solar | CH-02820 | Poughkeepsie |  |  | 12540 | G | 6055 | Todd Hill | TBD |  | 1620 | [13 empty] | CDG | N | (54) SMA STP 30000TL-US | 2016-11-03 | 2016-11-03 | 0 | 2016-11-03 | 2016-11-03 | 2016-11-28 | 15 |  |  |  |  | 35000 | [9 empty] | W
Central Hudson |  | OnForce Solar | CH-02821 | Poughkeepsie |  |  | 12540 | G | 6055 | Todd Hill | TBD |  | 1740 | [13 empty] | CDG | N | (58) SMA STP 30000TL-US | 2016-11-03 | 2016-11-03 | 0 | 2016-11-03 | 2016-11-03 | 2016-11-28 | 15 |  |  |  |  | 35000 | [9 empty] | W
Central Hudson |  | SolarCity | CH-05764 | Kingston | Kingston | Ulster | 12401 | G | 1021 | East Kingston | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A | 2016-09-16 | 2016-09-20 | 2 | 2016-09-20 | [14 empty] | 2017-01-19 | 2017-01-19 |  | Y
Central Hudson |  | SolarCity | CH-06305 | Newburgh | Wallkill | Ulster | 12589 | G | 4011 | West Balmville | N |  | 6 | [13 empty] | NM | N | ABB PVI 6000 | 2016-09-07 | 2016-09-15 | 6 | 2016-09-15 | [14 empty] | 2016-11-03 | 2016-11-09 |  | Y
Central Hudson |  | SolarCity | CH-06395 | Newburgh | Cornwall-Hdsn | Orange | 12520 | G | 4043 | Union Ave | N |  | 6 | [13 empty] | NM | N | ABB PVI 3.0 (2) | 2016-09-07 | 2016-09-08 | 1 | 2016-09-08 | [14 empty] | 2016-12-01 | 2016-12-13 |  | Y
Central Hudson |  | SolarCity | CH-07113 | Newburgh | New Windsor | Orange | 12553 | G | 4094 | Bethlehem Rd | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2016-09-07 | 2016-09-15 | 6 | 2016-09-15 | [14 empty] | 2016-12-22 | 2017-01-05 |  | Y
Central Hudson |  | SolarCity | CH-07273 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6094 | Manchester | N |  | 3 | [13 empty] | NM | N | ABB PVI 3.0 | 2016-09-07 | 2016-09-15 | 6 | 2016-09-15 | [14 empty] | 2016-10-18 | 2016-10-21 |  | Y
Central Hudson |  | SolarCity | CH-07320 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7053 | Rhinebeck | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2016-09-07 | 2016-09-15 | 6 | 2016-09-15 | [14 empty] | 2016-10-03 | 2016-10-04 |  | Y
Central Hudson |  | Sunrun Inc. | CH-08329 | Fishkill | Cold Spg | Putnam | 10516 | G | 8087 | Tioronda | N |  | 3.6 | [13 empty] | NM | N | ABB PVI-3.6-OUTD-S-US-A | 2016-09-07 | 2016-09-08 | 1 | 2016-09-08 | [14 empty] | 2016-10-21 | 2016-10-21 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-00196 | Newburgh | Rock Tvrn | Orange | 12575 | G | 4097 | Bethlehem Rd | N |  | 6.4 | [13 empty] | NM | N | SUNPOWER SPR-X21-335-BLK C-AC (20) | 2016-09-08 | 2016-09-15 | 5 | 2016-09-15 | [14 empty] | 2016-11-29 | 2016-11-29 |  | Y
Central Hudson |  | Ace Solar LLC | CH-00630 | Catskill | Elka Pk | Greene | 12427 | G | 2385 | Lawrenceville | N |  | 10 | [13 empty] | NM | N | (2) FRONIUS 5.0 | 2016-09-09 | 2016-09-19 | 6 | 2016-09-19 | [14 empty] | 2017-09-07 | 2017-09-07 |  | Y
Central Hudson |  | Apex Solar Power | CH-00686 | Fishkill | Cold Spg | Putnam | 10516 | G | 8087 | Tioronda | N |  | 3.8 | [13 empty] | NM | N | SOLAREDGE SE3800A-US | 2016-09-12 | 2016-09-16 | 4 | 2016-09-16 | [14 empty] | 2017-02-21 | 2017-02-21 |  | Y
Central Hudson |  | PosiGen Solar | CH-02893 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6011 | Sand Dock | N |  | 3.8 | [13 empty] | NM | N | SOLAREDGE SE 3800A-US | 2016-09-08 | 2016-09-09 | 1 | 2016-09-09 | [14 empty] | 2016-11-11 | 2016-11-11 |  | Y
Central Hudson |  | SolarCity | CH-05921 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6056 | Todd Hill | N |  | 5 | [13 empty] | NM | N | ABB PVI-5000 OUTD-US | 2016-09-21 | 2016-09-26 | 3 | 2016-09-26 | [14 empty] | 2016-10-19 | 2016-10-19 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06294 | Newburgh | Highland | Ulster | 12528 | G | 5013 | Modena | N |  | 10.6 | [13 empty] | NM | N | ABB PVI 3.6 FRONIUS PRIMO 7.6 | 2016-09-08 | 2016-09-15 | 5 | 2016-09-15 | [14 empty] | 2016-11-10 | 2016-11-10 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06823 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8023 | Knapps Corners | N |  | 8.6 | [13 empty] | NM | N | ABB PVI 5000 ABB PVI 3.6 | 2016-09-08 | 2016-09-09 | 1 | 2016-09-09 | [14 empty] | 2016-11-11 | 2016-11-11 |  | Y
Central Hudson |  | SolarCity | CH-07477 | Newburgh | Maybrook | Orange | 12543 | G | 5052 | Maybrook | N | CH-19256 | 3.6 | [13 empty] | NM | N | ABBPVI-3.6OUTD-S-US | 2016-09-19 | 2016-09-20 | 1 | 2016-09-20 | [14 empty] | 2016-09-28 | 2016-10-11 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08786 | Kingston |  |  | 12477 | G | 2016 | Lincoln Park | TBD |  | 14.4 | [13 empty] | NM | N | ENPHASE M215 (67) | 2016-09-08 | 2016-09-08 | 0 | 2016-09-08 | [17 empty] | W
Central Hudson |  | Sun Mountain | CH-09098 | Kingston | Kingston | Ulster | 12401 | G | 2094 | Hurley Ave | N | CH-09098 | 5 | [13 empty] | NM | N | SMA AMERICA SB5.0 | 2016-09-20 | 2016-09-26 | 4 | 2016-09-26 | [14 empty] | 2016-12-08 | 2016-12-08 |  | Y
Central Hudson |  | PosiGen Solar | CH-02860 | Catskill | Cornwallvl | Greene | 12418 | G | 2043 | South Cairo | N |  | 5.16 | [13 empty] | NM | N | ENPHASE M215 (24) | 2016-09-09 | 2016-09-22 | 9 | 2016-09-22 | [14 empty] | 2016-09-30 | 2016-10-06 |  | Y
Central Hudson |  | Solar Liberty Energy Systems | CH-04904 | Kingston | Saugerties | Ulster | 12477 | G | 3001 | Saugerties | N |  | 15.2 | [13 empty] | NM | N | SOLAREDGE TECH A US | 2016-09-09 | 2016-09-16 | 5 | 2016-09-16 | [14 empty] | 2016-11-18 | 2016-12-02 |  | Y
Central Hudson |  | SolarCity | CH-05038 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7062 | Milan | N |  | 8.2 | [13 empty] | NM | N | FRONIUS PRIMO 8.2 | 2016-09-09 | 2016-09-16 | 5 | 2016-09-16 | [14 empty] | 2016-10-03 | 2016-10-04 |  | Y
Central Hudson |  | Tesla | CH-05136 | Newburgh | New Windsor | Orange | 12553 | G | 4095 | Bethlehem Rd | N |  | 7.6 | [13 empty] | NM | N | 1 Fronius International Fronius Primo 7.6-1 208-240 (208V) [SI1] | 2016-09-09 | 2016-09-16 | 5 | 2016-09-16 | [14 empty] | 2018-10-09 | 2018-10-10 |  | Y
Central Hudson |  | Lighthouse Solar | CH-00313 | Newburgh | New Paltz | Ulster | 12561 | G | 5021 | Ohioville | N |  | 10 | [13 empty] | NM | N | SOLAREDGE 10000 A-US | 2016-09-12 | 2016-09-16 | 4 | 2016-09-16 | [14 empty] | 2016-12-16 | 2016-12-16 |  | Y
Central Hudson |  | New York State Solar Farm | CH-03931 | Newburgh | Wallkill | Ulster | 12589 | G | 5043 | East Walden | N |  | 6.72 | [13 empty] | NM | N | (21) SUNPOWER SPR-X22 360-C-AC | 2016-09-19 | 2016-09-26 | 5 | 2016-09-26 | [14 empty] | 2016-10-24 | 2016-10-27 |  | Y
Central Hudson |  | New York State Solar Farm | CH-00442 | Newburgh | Gardiner | Ulster | 12525 | G | 5031 | Galeville | N | CH-00442 | 3.52 | [13 empty] | NM | N | SUNPOWER SPR-E20 327-C-AC (11) | 2016-09-19 | 2016-09-26 | 5 | 2016-09-26 | [14 empty] | 2016-10-27 | 2016-10-27 |  | Y
Central Hudson |  | Direct Energy Solar | CH-01004 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7061 | Milan | N |  | 12.5 | [13 empty] | NM | N | (50) E M250 60-2LL-S2 | 2016-09-21 | 2016-09-26 | 3 | 2016-09-26 | [14 empty] | 2016-10-25 | 2016-10-25 |  | Y
Central Hudson |  | Direct Energy Solar | CH-01028 | Catskill | Haines Fls | Greene | 12436 | G | 2385 | Lawrenceville | N |  | 5 | [13 empty] | NM | N | (20) ENPHASE M250 60-2LL-S22 | 2016-10-10 | 2016-10-11 | 1 | 2016-10-11 | [14 empty] | 2017-03-17 | 2017-03-21 |  | Y
Central Hudson |  | PosiGen Solar | CH-02866 | Catskill | Elka Pk | Greene | 12427 | G | 2385 | Lawrenceville | N |  | 3.8 | [13 empty] | NM | N | SOLAR EDGE SE3800 | 2016-09-12 | 2016-09-22 | 8 | 2016-09-22 | [14 empty] | 2016-11-08 | 2016-11-15 |  | Y
Central Hudson |  | SolarCity | CH-05195 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8093 | Fishkill Plains | N |  | 12 | [13 empty] | NM | N | ABB PVI 6000 | 2016-09-12 | 2016-09-16 | 4 | 2016-09-16 | [14 empty] | 2016-10-14 | 2016-11-02 |  | Y
Central Hudson |  | SolarCity | CH-05645 | Kingston | Hurley | Ulster | 12443 | G | 2093 | Hurley Ave | N |  | 15.2 | [13 empty] | NM | N | (2) FRONIUS PRIMO 7.6 | 2016-09-12 | 2016-09-16 | 4 | 2016-09-16 | [14 empty] | 2016-11-10 | 2016-11-10 |  | Y
Central Hudson |  | SolarCity | CH-06426 | Newburgh | Maybrook | Orange | 12543 | G | 4026 | Coldenham | N |  | 3.6 | [13 empty] | NM | N | ABB PVI 3.6 | 2016-09-12 | 2016-09-16 | 4 | 2016-09-16 | [14 empty] | 2016-10-17 | 2016-11-02 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06517 | Kingston | Kingston | Ulster | 12401 | G | 1024 | East Kingston | N |  | 6 | [13 empty] | NM | N | ABB PVI 6000 | 2016-11-03 | 2016-11-03 | 0 | 2016-11-03 | [14 empty] | 2016-11-14 | 2016-11-17 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07168 | Newburgh | New Windsor | Orange | 12553 | G | 4095 | Bethlehem Rd | N |  | 3.6 | [13 empty] | NM | N | ABB PVI 3.6 | 2016-09-12 | 2016-09-16 | 4 | 2016-09-16 | [14 empty] | 2016-10-13 | 2016-10-17 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-00093 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7052 | Rhinebeck | N |  | 6 | [13 empty] | NM | N | SOLAREDGE 6000A US | 2016-09-13 | 2016-10-03 | 14 | 2016-10-03 | [14 empty] | 2016-10-21 | 2016-10-21 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-00202 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8092 | Fishkill Plains | N |  | 8.32 | [13 empty] | NM | N | (26) SUNPOWER SPR-E20-327 C-AC | 2016-09-13 | 2016-09-26 | 9 | 2016-09-26 | [14 empty] | 2016-11-03 | 2016-11-03 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-00210 | Newburgh | Newburgh | Orange | 12550 | G | 5004 | Marlboro | N |  | 7.04 | [13 empty] | NM | N | (22) SUNPOWER SPR-E20-327 C-AC | 2016-09-13 | 2016-09-16 | 3 | 2016-09-16 | [14 empty] | 2016-10-14 | 2016-10-17 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03738 | Poughkeepsie | Staatsburg | Dutchess | 12580 | G | 7011 | Hibernia | N |  | 11.4 | [13 empty] | NM | N | SOLAREDGE 11400 A-US | 2016-09-13 | 2016-09-19 | 4 | 2016-09-19 | [14 empty] | 2016-11-02 | 2016-11-07 |  | Y
Central Hudson |  | Lighthouse Solar | CH-00327 | Kingston | Cottekill | Ulster | 12419 | G | 3021 | High Falls | N | CH-09059 | 5 | [13 empty] | NM | N | SOLAREDGE 5000 A-US | 2016-09-13 | 2016-09-19 | 4 | 2016-09-19 | [14 empty] | 2016-10-13 | 2016-10-14 |  | Y
Central Hudson |  | New York State Solar Farm | CH-00366 | Kingston | Saugerties | Ulster | 12477 | G | 2015 | Lincoln Park | N | CH-00366 | 12 | [13 empty] | NM | N | (2) SMA AMERICA SB TL | 2016-09-13 | 2016-09-16 | 3 | 2016-09-16 | [14 empty] | 2016-11-14 | 2016-11-16 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00829 | Poughkeepsie |  |  | 12571 | G | 7062 | Milan | TBD |  | 10.32 | [13 empty] | NM | N | (48) ENPHASE M215 60-2LL-S22 | 2016-09-23 | 2016-10-03 | 6 | 2016-10-03 | [14 empty] | 2017-01-10 | 2017-01-17 |  | W
Central Hudson |  | Direct Energy Solar | CH-00947 | Poughkeepsie | Pine Plns | Dutchess | 12567 | G | 7091 | Pulvers Corners | N |  | 5.25 | [13 empty] | NM | N | (21) ENPHASE M250 60-2LL-S22 | 2016-09-13 | 2016-09-16 | 3 | 2016-09-16 | [14 empty] | 2016-11-14 | 2016-11-14 |  | Y
Central Hudson |  | PosiGen Solar | CH-02926 | Newburgh |  |  | 12550 | G | 4053 | Union Ave | TBD |  | 5 | [13 empty] | NM | N | SOLAREDGE SE 5000A-US | 2016-09-13 | 2016-09-22 | 7 | 2016-09-22 | [17 empty] | W
Central Hudson |  | SolarCity | CH-05657 | Kingston | Kingston | Ulster | 12401 | G | 2017 | Lincoln Park | N |  | 6 | [13 empty] | NM | N | ABB PVI 6000 | 2016-09-13 | 2016-09-16 | 3 | 2016-09-16 | [14 empty] | 2016-12-21 | 2016-12-28 |  | Y
Central Hudson |  | SolarCity | CH-06098 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8045 | Myers Corners | N |  | 4.2 | [13 empty] | NM | N | ABB PVI 4.2 | 2016-09-13 | 2016-09-16 | 3 | 2016-09-16 | [14 empty] | 2016-11-29 | 2016-11-29 |  | Y
Central Hudson |  | SolarCity | CH-06989 | Newburgh | Newburgh | Orange | 12550 | G | 4024 | Coldenham | N |  | 5 | [13 empty] | NM | N | ABB PVI 5000 | 2016-09-13 | 2016-09-16 | 3 | 2016-09-16 | [14 empty] | 2017-02-02 | 2017-02-02 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08681 | Poughkeepsie | Verbank | Dutchess | 12585 | G | 6057 | Todd Hill | N | CH-08681 | 3.44 | [13 empty] | NM | N | (16) ENPHASE M215 602LLS22IG | 2016-12-08 | 2016-12-21 | 9 | 2016-12-21 | [14 empty] | 2017-04-12 | 2017-04-19 |  | Y
Central Hudson |  | Sungevity Inc | CH-09533 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6092 | Manchester | N |  | 10 | [13 empty] | NM | N | SOLAREDGE TECH. SE 10000 | 2016-10-11 | 2016-10-12 | 1 | 2016-10-12 | [14 empty] | 2016-10-26 | 2016-10-31 |  | Y
Central Hudson |  | NRG Home Solar | CH-00557 | Fishkill | Glenham | Dutchess | 12527 | G | 8015 | Forgebrook | N |  | 5.59 | [13 empty] | NM | N | ENPHASE M-215 (26) | 2016-09-20 | 2016-09-26 | 4 | 2016-09-26 | [14 empty] | 2017-01-16 | 2017-01-16 |  | Y
Central Hudson |  | Hudson Solar | CH-01875 | Poughkeepsie | Tivoli | Dutchess | 12583 | G | 7062 | Milan | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE-6000 A-US | 2016-09-19 | 2016-09-26 | 5 | 2016-09-26 | [14 empty] | 2016-12-27 | 2016-12-27 |  | Y
Central Hudson |  | Hudson Solar | CH-01876 | Poughkeepsie | Tivoli | Dutchess | 12583 | G | 7062 | Milan | N |  | 10 | [13 empty] | NM | N | SOLAREDGE SE-10000 A-US | 2016-09-20 | 2016-09-26 | 4 | 2016-09-26 | [14 empty] | 2016-11-01 | 2016-11-04 |  | Y
Central Hudson |  | Monolith Solar Associates LLC | CH-02683 | Catskill | Coxsackie | Greene | 12051 | G | 1076 | Coxsackie | N |  | 10 | [13 empty] | NM | N | SOLAREDGE SE10000 | 2016-10-18 | 2016-10-18 | 0 | 2016-10-18 | [8 empty] | 350 | 350 |  | 2016-11-09 | 2016-11-09 | 2016-12-09 | 2016-12-19 | 2016-12-27 |  | Y
Central Hudson |  | SolarCity | CH-07159 | Newburgh | New Windsor | Orange | 12553 | G | 4095 | Bethlehem Rd | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2016-10-07 | 2016-10-07 | 0 | 2016-10-07 | [14 empty] | 2016-10-11 | 2016-10-14 |  | Y
Central Hudson |  | SolarCity | CH-07508 | Kingston | Saugerties | Ulster | 12477 | G | 3003 | Saugerties | N |  | 5 | [13 empty] | NM | N | ABB PVI-5000 OUTD-US | 2016-10-07 | 2016-10-07 | 0 | 2016-10-07 | [14 empty] | 2016-12-08 | 2016-12-08 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Solar Alchemy | CH-08989 | Kingston | Stone Ridge | Ulster | 12484 | G | 3023 | High Falls | N |  | 10.5 | [13 empty] | NM | N | (42) ENPHASE ENERGY M250 60-2LL | 2016-09-21 | 2016-09-26 | 3 | 2016-09-26 | [8 empty] | 350 | 350 |  | 2016-10-17 | 2016-10-17 | 2016-11-11 | 2016-11-15 | 2016-11-15 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Empire Solar Solutions | CH-00072 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6046 | Spackenkill | N |  | 11.4 | [13 empty] | NM | N | SOLAREDGE 11400A US | 2016-09-15 | 2016-09-19 | 2 | 2016-09-19 | [14 empty] | 2016-10-27 | 2016-11-01 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-00138 | Newburgh | New Windsor | Orange | 12553 | G | 4094 | Bethlehem Rd | N |  | 14.08 | [13 empty] | NM | N | (44) SUNPOWER SPR-E20-327 C-AC | 2016-09-21 | 2016-09-26 | 3 | 2016-09-26 | [14 empty] | 2016-10-24 | 2016-10-24 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00832 | Kingston | Kingston | Ulster | 12401 | G | 2013 | Lincoln Park | N |  | 4.73 | [13 empty] | NM | N | (22) ENPHASE M215 60-2LL-S22 | 2016-09-15 | 2016-09-20 | 3 | 2016-09-20 | [14 empty] | 2017-01-11 | 2017-01-11 |  | Y
Central Hudson |  | Direct Energy Solar | CH-01027 | Newburgh | Campbell Hall | Orange | 10916 | G | 5051 | Maybrook | N |  | 8.25 | [13 empty] | NM | N | (33) ENPHASE M250 60 | 2016-09-21 | 2016-09-26 | 3 | 2016-09-26 | [14 empty] | 2017-01-06 | 2017-01-06 |  | Y
Central Hudson |  | Hudson Solar | CH-02284 | Poughkeepsie | Tivoli | Dutchess | 12583 | G | 7062 | Milan | N |  | 3.8 | [13 empty] | NM | N | SOLAREDGE SE-3800 A-US | 2016-09-15 | 2016-09-19 | 2 | 2016-09-19 | [14 empty] | 2016-10-10 | 2016-10-13 |  | Y
Central Hudson |  | SolarCity | CH-05089 | Newburgh | Campbell Hall | Orange | 10916 | G | 5052 | Maybrook | N |  | 9.2 | [13 empty] | NM | N | ABB PVI-4.2 OUTD-S-US ABB PVI-5000 OUTD-US | 2016-09-15 | 2016-09-19 | 2 | 2016-09-19 | [14 empty] | 2016-12-15 | 2016-12-15 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08713 | Fishkill | Putnam Valley | Putnam | 10524 | G | 8066 | Merritt Park | N |  | 4.73 | [13 empty] | NM | N | (22) ENPHASE M215 602LLS22IG | 2016-09-15 | 2016-09-19 | 2 | 2016-09-19 | [14 empty] | 2016-12-05 | 2016-12-05 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-00066 | Newburgh | Campbell Hall | Orange | 10916 | G | 5051 | Maybrook | N |  | 12.6 | [13 empty] | NM | N | SOLAREDGE 7600A US SOLAREDGE 5000A US | 2016-09-28 | 2016-10-04 | 4 | 2016-10-04 | [14 empty] | 2017-06-07 | 2017-06-08 |  | Y
Central Hudson |  | Lotus Energy Inc. | CH-03886 | Fishkill | Putnam Valley | Putnam | 10524 | G | 8086 | Tioronda | N |  | 23.1 | [13 empty] | NM | N | (3) SMA 7700 TL-US-22 | 2016-09-27 | 2016-09-30 | 3 | 2016-09-30 | [14 empty] | 2016-11-08 | 2016-11-23 |  | Y
Central Hudson |  | SolarCity | CH-07732 | Kingston | Kingston | Ulster | 12401 | G | 2017 | Lincoln Park | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2016-09-16 | 2016-09-20 | 2 | 2016-09-20 | [14 empty] | 2016-11-09 | 2016-11-09 |  | Y
Central Hudson |  | Sol Providers | CH-08960 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 7024 | Tinkertown | N |  | 6.4 | [13 empty] | NM | N | (20) SUNPOWER E20 327C-AC | 2016-09-16 | 2016-09-26 | 6 | 2016-09-26 | [14 empty] | 2016-10-04 | 2016-10-04 |  | Y
Central Hudson |  | Hudson Solar | CH-01846 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7051 | Rhinebeck | N |  | 11.4 | [13 empty] | NM | N | SOLAREDGE SE-11400 A-US | 2016-09-27 | 2016-10-11 | 10 | 2016-10-11 | [14 empty] | 2016-12-07 | 2016-12-07 |  | Y
Central Hudson |  | Hudson Solar | CH-02382 | Newburgh | Maybrook | Orange | 12543 | G | 5052 | Maybrook | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE-5000 US-U | 2016-09-27 | 2016-10-04 | 5 | 2016-10-04 | [14 empty] | 2016-12-14 | 2016-12-19 |  | Y
Central Hudson |  | PosiGen Solar | CH-02868 | Catskill | Leeds |  | 12451 | G | 2005 | North Catskill | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A | 2016-10-05 | 2016-10-06 | 1 | 2016-10-06 | [17 empty] | W
Central Hudson |  | PosiGen Solar | CH-02912 | Fishkill | Cold Spg |  | 10516 | G | 8087 | Tioronda | N |  | 3.8 | [13 empty] | NM | N | SOLAREDGE SE3800A-US | 2016-09-26 | 2016-10-03 | 5 | 2016-10-03 | [17 empty] | W
Central Hudson |  | SolarCity | CH-07632 | Kingston | Hurley | Ulster | 12443 | G | 2093 | Hurley Ave | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2016-09-19 | 2016-09-20 | 1 | 2016-09-20 | [14 empty] | 2016-11-30 | 2016-11-30 |  | Y
Central Hudson |  | New York State Solar Farm | CH-00450 | Kingston | Saugerties | Ulster | 12477 | G | 3003 | Saugerties | N |  | 6.8 | [13 empty] | NM | N | SMA AMERICA SB-3000-TL-US-22 SMA AMERICAN SB-3800-TL-US-22 | 2016-09-26 | 2016-10-03 | 5 | 2016-10-03 | [14 empty] | 2016-11-18 | 2016-12-06 |  | Y
Central Hudson |  | PosiGen Solar | CH-02913 | Fishkill | Cold Spg |  | 10516 | G | 8087 | Tioronda | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE7600A-US | 2016-09-20 | 2016-09-26 | 4 | 2016-09-26 | [17 empty] | W
Central Hudson |  | SolarCity | CH-06507 | Kingston | Kingston | Ulster | 12401 | G | 2017 | Lincoln Park | N |  | 4.2 | [13 empty] | NM | N | ABB PVI 4.2 | 2016-09-20 | 2016-09-28 | 6 | 2016-09-28 | [14 empty] | 2016-11-02 | 2016-11-02 |  | Y
Central Hudson |  | SolarCity | CH-07274 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6065 | Inwood Ave | N |  | 3.8 | [13 empty] | NM | N | DELTA SOLIVIA 3.8 | 2016-09-20 | 2016-09-26 | 4 | 2016-09-26 | [14 empty] | 2016-12-22 | 2016-12-22 |  | Y
Central Hudson |  | SolarCity | CH-07337 | Fishkill |  |  | 12590 | G | 8091 | Fishkill Plains | TBD |  | 19 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 FRONIUS PRIMO 11.4 | 2016-10-18 | 2016-10-21 | 3 | 2016-10-21 | [17 empty] | W
Central Hudson |  | SolarCity | CH-07523 | Poughkeepsie |  |  | 12603 | G | 6043 | Spackenkill | TBD |  | 3 | [13 empty] | NM | N | ABB PVI 3.0 | 2016-09-20 | 2016-09-26 | 4 | 2016-09-26 | [17 empty] | W
Central Hudson |  | New York State Solar Farm | CH-00406 | Newburgh | Walden | Orange | 12586 | G | 5042 | East Walden | N |  | 7.68 | [13 empty] | NM | N | (24) SUNPOWER SPR-E20 327-C-AC | 2016-09-26 | 2016-10-03 | 5 | 2016-10-03 | [14 empty] | 2016-11-07 | 2016-11-08 |  | Y
Central Hudson |  | New York State Solar Farm | CH-00416 | Newburgh | Maybrook | Orange | 12543 | G | 5052 | Maybrook | N |  | 9.6 | [13 empty] | NM | N | (30) SUNPOWER SPR-E20 327-C-AC | 2016-09-21 | 2016-09-26 | 3 | 2016-09-26 | [14 empty] | 2016-10-20 | 2016-10-20 |  | Y
Central Hudson |  | NRG Home Solar | CH-00480 | Kingston | Kerhonkson | Ulster | 12446 | G | 3081 | Kerhonkson | N |  | 6.66 | [13 empty] | NM | N | (31) ENPHASE M-215 240 | 2016-09-21 | 2016-09-26 | 3 | 2016-09-26 | [14 empty] | 2017-01-04 | 2017-01-04 |  | Y
Central Hudson |  | SolarCity | CH-05870 | Poughkeepsie | Staatsburg | Dutchess | 12580 | G | 7042 | Staatsburg | N |  | 10.4 | [13 empty] | NM | N | (2) DELTA SOLIVIA 5.2 | 2016-09-21 | 2016-09-26 | 3 | 2016-09-26 | [14 empty] | 2016-12-15 | 2016-12-15 |  | Y
Central Hudson |  | SolarCity | CH-06544 | Kingston | Kingston | Ulster | 12401 | G | 2093 | Hurley Ave | N |  | 15.8 | [13 empty] | NM | N | FRONIUS PRIMO 8.2 FRONIUS PRIMO 7.6 | 2016-09-21 | 2016-09-26 | 3 | 2016-09-26 | [14 empty] | 2017-06-01 | 2017-06-06 |  | Y
Central Hudson |  | SolarCity | CH-07526 | Poughkeepsie |  |  | 12603 | G | 6096 | Manchester | TBD |  | 3 | [13 empty] | NM | N | ABB PVI 3.0 | 2016-09-21 | 2016-09-26 | 3 | 2016-09-26 | [14 empty] | 2017-01-10 | 2017-01-10 |  | W
Central Hudson |  | SolarCity | CH-07721 | Newburgh | Walden | Orange | 12586 | G | 5041 | East Walden | N |  | 3.6 | [13 empty] | NM | N | ABB PVI 3.6 | 2016-09-21 | 2016-09-26 | 3 | 2016-09-26 | [14 empty] | 2016-10-25 | 2016-10-31 |  | Y
Central Hudson |  | Trinity Solar | CH-08407 | Kingston | Kingston | Ulster | 12401 | G | 2017 | Lincoln Park | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE7600A -US | 2016-09-21 | 2016-09-30 | 7 | 2016-09-30 | [14 empty] | 2017-01-05 | 2017-01-09 |  | Y
Central Hudson |  | Trinity Solar | CH-08568 | Newburgh | Newburgh | Orange | 12550 | G | 4047 | Union Ave | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A -US | 2016-09-30 | 2016-10-05 | 3 | 2016-10-05 | [14 empty] | 2016-11-08 | 2016-11-11 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08741 | Kingston |  |  | 12401 | G | 2091 | Hurley Ave | TBD |  | 4.73 | [13 empty] | NM | N | (22) ENPHASE M215 602LLS22IG | 2016-09-21 | 2016-09-26 | 3 | 2016-09-26 | [17 empty] | W
Central Hudson |  | Infinity Solar Systems | CH-00148 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8092 | Fishkill Plains | N |  | 5.76 | [13 empty] | NM | N | (18) SUNPOWER SPR-E20-327 C-AC | 2016-09-22 | 2016-09-26 | 2 | 2016-09-26 | [14 empty] | 2016-12-29 | 2016-12-29 |  | Y
Central Hudson |  | American Energy Care | CH-00657 | Catskill | Coxsackie | Greene | 12051 | G | 1071 | Coxsackie | N |  | 15.2 | [13 empty] | NM | N | 2 SOLAREDGE SE7600A-US | 2016-09-30 | 2016-10-06 | 4 | 2016-10-06 | [14 empty] | 2017-01-13 | 2017-01-13 |  | Y
Central Hudson |  | Autonomous Energies LLC | CH-00744 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7061 | Milan | N |  | 4.25 | [13 empty] | NM | N | (17) ENPHASE M-250 250 | 2016-10-07 | 2016-10-07 | 0 | 2016-10-07 | [14 empty] | 2016-12-06 | 2016-12-06 |  | Y
Central Hudson |  | PosiGen Solar | CH-02887 | Catskill | Cornwallvl | Greene | 12418 | G | 2043 | South Cairo | N |  | 3.8 | [13 empty] | NM | N | SOLAREDGE TECHNOLOGI SE3800A -US | 2016-10-03 | 2016-10-05 | 2 | 2016-10-05 | [14 empty] | 2016-12-19 | 2016-12-19 |  | Y
Central Hudson |  | SolarCity | CH-05390 | Newburgh | Newburgh | Orange | 12550 | G | 4024 | Coldenham | N | CH-05390 | 6.6 | [13 empty] | NM | N | ABB PVI 3.6 ABB PVI 3.0 | 2016-09-22 | 2016-10-03 | 7 | 2016-10-03 | [14 empty] | 2016-11-09 | 2016-11-09 |  | Y
Central Hudson |  | SolarCity | CH-06104 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8014 | Forgebrook | N |  | 5.2 | [13 empty] | NM | N | DELTA SOLIVIA 5.2 | 2016-09-22 | 2016-10-03 | 7 | 2016-10-03 | [14 empty] | 2016-11-10 | 2016-11-10 |  | Y
Central Hudson |  | Solar Generation | CH-08196 | Kingston | Saugerties | Ulster | 12477 | G | 1021 | East Kingston | N |  | 7.68 | [13 empty] | NM | N | (24) SUNPOWER 327-C AC | 2016-10-07 | 2016-10-07 | 0 | 2016-10-07 | [14 empty] | 2016-11-22 | 2016-11-22 |  | Y
Central Hudson |  | Solar Generation | CH-08200 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6092 | Manchester | N |  | 9.8 | [13 empty] | NM | N | SOLAREDGE 3800 A SOLAREDGE 6000 A | 2016-10-03 | 2016-10-06 | 3 | 2016-10-06 | [14 empty] | 2016-11-30 | 2016-11-30 |  | Y
Central Hudson |  | Sunrun Inc. | CH-08331 | Newburgh | Newburgh | Orange | 12550 | G | 4012 | West Balmville | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE TECHNOLOGI SE 7600A-US | 2016-10-03 | 2016-10-06 | 3 | 2016-10-06 | [14 empty] | 2016-12-02 | 2016-12-07 |  | Y
Central Hudson |  | Sustainable Energy Developments, Inc. | CH-09703 | Kingston |  |  | 12777 | G | 3005 | Saugerties | TBD |  | 2000 | [13 empty] | CDG | N | (66) SMA Tri-power 30000TL-US & (1) SMA Tri-power 20000TL-US | 2016-11-18 | 2016-11-18 | 0 | 2016-11-18 | 2016-11-18 | 2016-12-06 | 10 |  |  |  |  | 32000 | [9 empty] | W
Central Hudson |  | SolarCity | CH-07430 | Newburgh | Newburgh | Orange | 12550 | G | 4051 | Union Ave | N |  | 6 | [13 empty] | NM | N | ABB PVI 6000 | 2016-09-23 | 2016-09-30 | 5 | 2016-09-30 | [14 empty] | 2017-02-22 | 2017-03-01 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08803 | Fishkill | Putnam Valley | Putnam | 10524 | G | 8066 | Merritt Park | N |  | 3.44 | [13 empty] | NM | N | (16) ENPHASE M215 602LLS22IG | 2016-09-23 | 2016-10-05 | 8 | 2016-10-05 | [14 empty] | 2017-02-23 | 2017-02-23 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-00058 | Newburgh | Newburgh | Orange | 12550 | G | 4024 | Coldenham | N |  | 22.8 | [13 empty] | NM | N | SOLAREDGE 11400A US (2) | 2016-09-26 | 2016-10-03 | 5 | 2016-10-03 | [8 empty] | 350 | 350 |  | 2016-12-06 | 2016-12-06 | 2016-12-14 | 2016-12-14 | 2016-12-14 |  | Y
Central Hudson |  | New York State Solar Farm | CH-00451 | Poughkeepsie | Lagrangevl | Dutchess | 12540 | G | 6057 | Todd Hill | N |  | 16 | [13 empty] | NM | N | SUNPOWER SPR-E20 327-C-AC (50) | 2016-09-26 | 2016-10-03 | 5 | 2016-10-03 | [8 empty] | 350 | 350 |  | 2016-10-17 | 2016-10-17 | 2016-12-06 | 2016-12-08 | 2016-12-08 |  | Y
Central Hudson |  | Direct Energy Solar | CH-01048 | Kingston | Accord | Ulster | 12404 | G | 3082 | Kerhonkson | N |  | 4.2 | [13 empty] | NM | N | ENPHASE M215 60-2LL-S22 (20) | 2016-09-29 | 2016-10-03 | 2 | 2016-10-03 | [14 empty] | 2016-11-16 | 2016-11-16 |  | Y
Central Hudson |  | PosiGen Solar | CH-02910 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6056 | Todd Hill | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE 5000A-US - | 2016-09-26 | 2016-10-10 | 10 | 2016-10-10 | [14 empty] | 2016-11-02 | 2016-11-02 |  | Y
Central Hudson |  | SolarCity | CH-06097 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8045 | Myers Corners | N |  | 5 | [13 empty] | NM | N | ABB PVI-5000 OUTD-US | 2016-09-26 | 2016-09-26 | 0 | 2016-09-26 | [14 empty] | 2016-11-03 | 2016-11-03 |  | Y
Central Hudson |  | Trinity Solar | CH-08497 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8094 | Fishkill Plains | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE7600A -US | 2016-09-26 | 2016-09-30 | 4 | 2016-09-30 | [14 empty] | 2017-02-08 | 2017-02-08 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-00039 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6044 | Spackenkill | N |  | 11.4 | [13 empty] | NM | N | SOLAREDGE 11400A US | 2016-09-27 | 2016-09-30 | 3 | 2016-09-30 | [14 empty] | 2016-10-26 | 2016-10-27 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-00080 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 7025 | Tinkertown | N |  | 5 | [13 empty] | NM | N | SOLAREDGE 5000A US | 2016-09-27 | 2016-10-04 | 5 | 2016-10-04 | [14 empty] | 2016-10-10 | 2016-10-13 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Endless Mtn Solar Services | CH-01110 | Catskill | Hunter | Greene | 12442 | E | 2081 | Hunter | N |  | 3.22 | [13 empty] | NM | N | ENPHASE M215- (15) | 2016-09-30 | 2016-10-04 | 2 | 2016-10-04 | [14 empty] | 2016-12-20 | 2016-12-20 |  | Y
Central Hudson |  | Monolith Solar Associates LLC | CH-02645 | Catskill | Coxsackie | Greene | 12051 | G | 1071 | Coxsackie | N |  | 11.4 | [13 empty] | NM | N | SOLAREDGE SE7600A SOLAREDGE SE3800A | 2016-09-27 | 2016-10-04 | 5 | 2016-10-04 | [14 empty] | 2016-12-14 | 2016-12-14 |  | Y
Central Hudson |  | New York State Solar Farm | CH-00365 | Fishkill | Beacon | Dutchess | 12508 | G | 8015 | Forgebrook | N |  | 4.16 | [13 empty] | NM | N | SUNPOWER SPR-X22 360-C-AC (13) | 2016-10-05 | 2016-10-06 | 1 | 2016-10-06 | [14 empty] | 2016-11-30 | 2016-11-30 |  | Y
Central Hudson |  | New York State Solar Farm | CH-00423 | Kingston | Saugerties | Ulster | 12477 | G | 3003 | Saugerties | N |  | 6.4 | [13 empty] | NM | N | SUNPOWER SPR-E20 327-C-AC (20) | 2016-09-28 | 2016-10-04 | 4 | 2016-10-04 | [14 empty] | 2016-11-14 | 2016-11-18 |  | Y
Central Hudson |  | Hudson Solar | CH-01552 | Poughkeepsie | Clinton Corners | Dutchess | 12514 | G | 7013 | Hibernia | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE-6000 A-US | 2016-09-28 | 2016-10-04 | 4 | 2016-10-04 | [14 empty] | 2017-01-20 | 2017-01-20 |  | Y
Central Hudson |  | Monolith Solar Associates LLC | CH-02678 | Catskill | Medusa | Greene | 12083 | G | 2061 | Freehold | N |  | 10 | [13 empty] | NM | N | SOLAREDGE SE5000 A-US (2) | 2016-09-28 | 2016-10-05 | 5 | 2016-10-05 | [14 empty] | 2016-12-12 | 2016-12-13 |  | Y
Central Hudson |  | PosiGen Solar | CH-02865 | Kingston | Tillson | Ulster | 12486 | G | 3021 | High Falls | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE 5000A-US | 2016-09-28 | 2016-10-04 | 4 | 2016-10-04 | [14 empty] | 2016-11-01 | 2016-11-01 |  | Y
Central Hudson |  | PosiGen Solar | CH-02883 | Newburgh | Wallkill | Ulster | 12589 | G | 5013 | Modena | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE7600A-US | 2016-09-28 | 2016-10-04 | 4 | 2016-10-04 | [14 empty] | 2016-11-11 | 2016-11-11 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-00059 | Newburgh | Newburgh | Orange | 12550 | G | 4014 | West Balmville | N |  | 6 | [13 empty] | NM | N | SOLAREDGE 6000A US | 2016-10-04 | 2016-10-06 | 2 | 2016-10-06 | [14 empty] | 2016-10-28 | 2016-11-07 |  | Y
Central Hudson |  | New York State Solar Farm | CH-00463 | Kingston | Ellenvl | Ulster | 12428 | G | 3076 | Greenfield Rd | N |  | 5.76 | [13 empty] | NM | N | SUNPOWER SPR-X22 360-C-AC 18 | 2016-10-05 | 2016-10-06 | 1 | 2016-10-06 | [14 empty] | 2016-11-08 | 2016-11-14 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00840 | Kingston | Saugerties | Ulster | 12477 | G | 3002 | Saugerties | N |  | 4.3 | [13 empty] | NM | N | ENPHASE M215 60-2LL-S22 (20) | 2016-10-04 | 2016-10-06 | 2 | 2016-10-06 | [14 empty] | 2017-01-25 | 2017-01-27 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00906 | Kingston | Claryvl | Sullivan | 12725 | G | 3091 | Neversink | N |  | 2.58 | [13 empty] | NM | N | ENPHASE M215 60-2LL-S22 (12) | 2016-09-29 | 2016-10-04 | 3 | 2016-10-04 | [14 empty] | 2016-11-02 | 2016-11-02 |  | Y
Central Hudson |  | SolarCity | CH-06976 | Newburgh | Newburgh | Orange | 12550 | G | 4014 | West Balmville | N |  | 7.6 | [13 empty] | NM | N | DELTA SOLIVIA 7.6TL | 2016-09-29 | 2016-10-04 | 3 | 2016-10-04 | [14 empty] | 2016-12-28 | 2016-12-28 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-03339 | Newburgh |  |  | 12575 | G | 4097 | Bethlehem Rd | TBD |  | 1.07 | [13 empty] | NM | N | 5 ENPHASE M125 A | 2016-10-10 | 2016-10-11 | 1 | 2016-10-11 | [17 empty] | W
Central Hudson |  | Empire Solar Solutions | CH-00103 | Newburgh |  |  | 12575 | G | 4097 | Bethlehem Rd | TBD |  | 6 | [13 empty] | NM | N | SOLAREDGE 6000A US | 2016-09-30 | 2016-10-07 | 5 | 2016-10-07 | [17 empty] | W
Central Hudson |  | Kasselman Solar | CH-00227 | Catskill | Athens | Greene | 12015 | G | 2002 | North Catskill | N |  | 7 | [13 empty] | NM | N | (28) Enphase M250 | 2016-10-14 | 2016-10-14 | 0 | 2016-10-14 | [14 empty] | 2016-10-26 | 2016-10-27 |  | Y
Central Hudson |  | NRG Home Solar | CH-00489 | Poughkeepsie |  |  | 12538 | G | 6074 | East Park | TBD |  | 4.3 | [13 empty] | NM | N | ENPHASE 215 240 (20) | 2016-10-11 | 2016-10-11 | 0 | 2016-10-11 | [17 empty] | W
Central Hudson |  | NRG Home Solar | CH-00550 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6073 | East Park | N |  | 13.97 | [13 empty] | NM | N | ENPHASE M215 240 (65) | 2016-10-11 | 2016-10-11 | 0 | 2016-10-11 | [14 empty] | 2016-12-19 | 2016-12-22 |  | Y
Central Hudson |  | Apex Solar Power | CH-00693 | Fishkill | Beacon | Dutchess | 12508 | G | 8085 | Tioronda | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A-US | 2016-10-11 | 2016-10-11 | 0 | 2016-10-11 | [14 empty] | 2017-01-04 | 2017-01-09 |  | Y
Central Hudson |  | Hudson Solar | CH-02531 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7052 | Rhinebeck | N |  | 160 | [13 empty] | CDG | N | 2 Chint Power Systems America CPS SCA50KTL-DO/US-480 (480V) 1 Chint Power Systems America CPS SCA60KTL-DO/US-480 (480V) (5) SolarEdge SE33.3k-US | 2016-10-19 | 2016-10-20 | 1 | 2016-10-20 | 2016-10-20 | 2016-11-10 | 15 | [11 empty] | 2020-12-08 | 2020-12-09 |  | Y
Central Hudson |  | Hudson Solar | CH-02532 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7052 | Rhinebeck | N |  | 160 | [13 empty] | CDG | N | 2 Chint Power Systems America CPS SCA50KTL-DO/US-480 (480V) 1 Chint Power Systems America CPS SCA60KTL-DO/US-480 (480V) (5) SolarEdge SE33.3k-US | 2016-10-19 | 2016-10-20 | 1 | 2016-10-20 | 2016-10-20 | 2016-11-10 | 15 | [11 empty] | 2020-12-08 | 2020-12-09 |  | Y
Central Hudson |  | Roeser Engineering DBA | CH-02989 | Poughkeepsie | Lagrangevl | Dutchess | 12540 | G | 6053 | Todd Hill | N |  | 22.5 | [13 empty] | NM | N | (90) Enphase M250-60-2LL-S22 | 2016-10-25 | 2016-11-07 | 9 | 2016-11-07 | [14 empty] | 2016-11-21 | 2016-11-22 |  | Y
Central Hudson |  | SolarCity | CH-05105 | Kingston | Hurley | Ulster | 12443 | G | 2094 | Hurley Ave | N |  | 5.2 | [13 empty] | NM | N | DELTA SOLIVIA 5.2 | 2016-09-30 | 2016-10-05 | 3 | 2016-10-05 | [14 empty] | 2016-11-28 | 2016-12-06 |  | Y
Central Hudson |  | SolarCity | CH-05169 | Newburgh | Milton | Ulster | 12547 | G | 5002 | Marlboro | N |  | 10.4 | [13 empty] | NM | N | DELTA SOLIVIA 5.29 (2) | 2016-09-30 | 2016-10-14 | 10 | 2016-10-14 | [14 empty] | 2016-11-10 | 2016-11-10 |  | Y
Central Hudson |  | SolarCity | CH-06826 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8052 | North Chelsea | N |  | 7.6 | [13 empty] | NM | N | DELTA SOLIVIA 7.6 | 2016-09-30 | 2016-10-05 | 3 | 2016-10-05 | [14 empty] | 2016-12-09 | 2016-12-09 |  | Y
Central Hudson |  | SolarCity | CH-07555 | Poughkeepsie | Millerton | Dutchess | 12546 | G | 7081 | Millerton | N |  | 6 | [13 empty] | NM | N | ABB PVI 6000 | 2016-11-14 | 2016-11-14 | 0 | 2016-11-14 | [14 empty] | 2016-12-01 | 2016-12-02 |  | Y
Central Hudson |  | SolarCity | CH-07679 | Newburgh | Newburgh | Orange | 12550 | G | 4023 | Coldenham | N |  | 7.6 | [13 empty] | NM | N | DELTA SOLIVIA 7.6 | 2016-09-30 | 2016-10-05 | 3 | 2016-10-05 | [14 empty] | 2017-01-05 | 2017-01-05 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-00077 | Poughkeepsie |  |  | 12540 | G | 6052 | Todd Hill | TBD |  | 5 | [13 empty] | NM | N | SOLAREDGE 5000A | 2016-10-03 | 2016-10-06 | 3 | 2016-10-06 | [17 empty] | W
Central Hudson |  | New York State Solar Farm | CH-00389 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6045 | Spackenkill | N |  | 16.32 | [13 empty] | NM | N | SUNPOWER SPR-X22360-C-AC (51) | 2016-10-10 | 2016-10-11 | 1 | 2016-10-11 | [14 empty] | 2017-01-13 | 2017-01-13 |  | Y
Central Hudson |  | New York State Solar Farm | CH-00421 | Kingston | Accord | Ulster | 12404 | G | 3024 | High Falls | N |  | 24 | [13 empty] | NM | N | SMA AMERICA 6000 SB TL(4) | 2016-10-03 | 2016-10-17 | 10 | 2016-10-17 | [8 empty] | 350 | 350 |  | 2016-12-12 | 2016-12-12 | 2017-04-11 | 2017-04-08 | 2017-04-11 |  | Y
Central Hudson |  | New York State Solar Farm | CH-00422 | Kingston | Accord | Ulster | 12404 | G | 3024 | High Falls | N |  | 18 | [13 empty] | NM | N | 3 SMA AMERICA SB 6000 TL | 2016-10-17 | 2016-10-17 | 0 | 2016-10-17 | [8 empty] | 350 | 350 |  | 2016-12-05 | 2016-12-05 | 2017-04-11 | 2017-04-08 | 2017-04-11 |  | Y
Central Hudson |  | Hudson Solar | CH-01862 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7061 | Milan | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE-6000A-US | 2016-10-03 | 2016-10-12 | 7 | 2016-10-12 | [14 empty] | 2016-11-07 | 2016-11-07 |  | Y
Central Hudson |  | SolarCity | CH-04999 | Kingston | Kingston | Ulster | 12401 | G | 1022 | East Kingston | N |  | 3.8 | [13 empty] | NM | N | DELTA SOLIVIA 3.8 | 2016-12-16 | 2016-12-16 | 0 | 2016-12-16 | [14 empty] | 2017-05-24 | 2017-05-24 |  | Y
Central Hudson |  | SolarCity | CH-05699 | Kingston | Kingston | Ulster | 12401 | G | 111 | South Wall St | N |  | 5.2 | [13 empty] | NM | N | DELTA SOLIVIA 5.2 | 2016-10-03 | 2016-10-13 | 8 | 2016-10-13 | [14 empty] | 2016-12-12 | 2016-12-12 |  | Y
Central Hudson |  | SolarCity | CH-05724 | Kingston | West Camp | Ulster | 12490 | G | 3004 | Saugerties | N |  | 3.8 | [13 empty] | NM | N | DELTA SOLIVIA 3.8 | 2016-10-03 | 2016-10-05 | 2 | 2016-10-05 | [14 empty] | 2016-11-22 | 2016-11-22 |  | Y
Central Hudson |  | SolarCity | CH-06272 | Newburgh | Newburgh | Orange | 12550 | G | 4052 | Union Ave | N |  | 6.6 | [13 empty] | NM | N | DELTA SOLIVIA 6.6 | 2016-10-03 | 2016-10-06 | 3 | 2016-10-06 | [14 empty] | 2017-01-04 | 2017-02-07 |  | Y
Central Hudson |  | SolarCity | CH-06390 | Newburgh |  |  | 12577 | G | 4095 | Bethlehem Rd | TBD |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2016-10-03 | 2016-10-14 | 9 | 2016-10-14 | [17 empty] | W
Central Hudson |  | SolarCity | CH-07184 | Catskill | Catskill | Greene | 12414 | G | 2005 | North Catskill | N |  | 5.2 | [13 empty] | NM | N | DELTA SOLIVIA 5.2 | 2016-10-03 | 2016-10-06 | 3 | 2016-10-06 | [14 empty] | 2017-02-03 | 2017-02-03 |  | Y
Central Hudson |  | SolarCity | CH-07768 | Kingston | Kingston | Ulster | 12401 | G | 1022 | East Kingston | N |  | 5.2 | [13 empty] | NM | N | DELTA SOLIVIA 5.2 | 2016-10-03 | 2016-10-05 | 2 | 2016-10-05 | [14 empty] | 2017-04-21 | 2017-04-21 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-00168 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6092 | Manchester | N |  | 7.04 | [13 empty] | NM | N | 22 SUNPOWER SPR-X21-335-BLK C-AC | 2016-10-04 | 2016-10-06 | 2 | 2016-10-06 | [14 empty] | 2017-01-04 | 2017-01-06 |  | Y
Central Hudson |  | Apex Solar Power | CH-00702 | Poughkeepsie |  |  | 12580 | G | 7041 | Staatsburg | TBD |  | 15.2 | [13 empty] | NM | N | SOLAREDGE SE7600A-US (2) | 2016-10-04 | 2016-10-12 | 6 | 2016-10-12 | [8 empty] | 350 | 350 | [7 empty] | W
Central Hudson |  | SolarCity | CH-05174 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 6074 | East Park | N |  | 9 | [13 empty] | NM | N | ABB PVI 6000 ABB PVI 3000 | 2016-10-04 | 2016-10-06 | 2 | 2016-10-06 | [14 empty] | 2016-11-01 | 2016-11-01 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-05532 | Catskill | Rensselaervl | Albany | 12147 | G | 1092 | Westerlo | N |  | 3 | [13 empty] | NM | N | ABB PVI 3.0 | 2016-10-04 | 2016-10-06 | 2 | 2016-10-06 | [14 empty] | 2017-04-17 | 2017-04-24 |  | Y
Central Hudson |  | SolarCity | CH-06784 | Newburgh | Highland |  | 12528 | G | 5081 | Highland | TBD |  | 15.2 | [13 empty] | NM | N | 2 DELTA SOLIVIA 7.6 | 2016-10-12 | 2016-10-12 | 0 | 2016-10-12 | [17 empty] | W
Central Hudson |  | Trinity Solar | CH-08537 | Poughkeepsie |  |  | 12603 | G | 6097 | Manchester | TBD |  | 10 | [13 empty] | NM | N | SOLAREDGE SE10000A-US | 2016-10-05 | 2016-10-06 | 1 | 2016-10-06 | [17 empty] | W
Central Hudson |  | Trinity Solar | CH-08558 | Poughkeepsie |  |  | 12603 | G | 6045 | Spackenkill | TBD |  | 13.8 | [13 empty] | NM | N | SOLAREDGE SE10000A-US SOLAREDGE SE3800A-US | 2016-10-05 | 2016-10-06 | 1 | 2016-10-06 | [17 empty] | W
Central Hudson |  | Lighthouse Solar | CH-03783 | Newburgh | New Paltz | Ulster | 12561 | G | 5031 | Galeville | N |  | 11.4 | [13 empty] | NM | N | SOLAREDGE SE11400A-US | 2016-10-07 | 2016-10-07 | 0 | 2016-10-07 | [14 empty] | 2016-11-14 | 2016-11-18 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08718 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 8.815 | [13 empty] | NM | N | 41 ENPHASE m215-602LLS22IG | 2016-10-25 | 2016-10-25 | 0 | 2016-10-25 | [14 empty] | 2017-01-03 | 2017-01-03 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-00219 | Newburgh | Maybrook | Orange | 12543 | G | 4026 | Coldenham | N |  | 7.36 | [13 empty] | NM | N | 23 SUNPOWER SPR--X22-360 C-AC | 2016-10-11 | 2016-10-12 | 1 | 2016-10-12 | [14 empty] | 2016-12-13 | 2016-12-13 |  | Y
Central Hudson |  | Grid Alternatives Tri-State | CH-01174 | Kingston | Kingston | Ulster | 12401 | G | 1013 | Boulevard | N |  | 3 | [13 empty] | NM | N | SMA SB300TL | 2016-10-11 | 2016-10-14 | 3 | 2016-10-14 | [14 empty] | 2017-03-20 | 2017-03-23 |  | Y
Central Hudson |  | SolarCity | CH-05381 | Poughkeepsie | Clinton Corners | Dutchess | 12514 | G | 7071 | Stanfordville | N |  | 10.4 | [13 empty] | NM | N | 2 DELTA SOLIVIA 5.2 TL | 2016-10-07 | 2016-10-07 | 0 | 2016-10-07 | [14 empty] | 2017-01-26 | 2017-01-26 |  | Y
Central Hudson |  | SolarCity | CH-06492 | Kingston | Hurley | Ulster | 12443 | G | 2093 | Hurley Ave | N |  | 7.6 | [13 empty] | NM | N | DELTA SOLIVIA TL 7.6 | 2016-11-02 | 2016-11-02 | 0 | 2016-11-02 | [14 empty] | 2016-11-28 | 2016-11-28 |  | Y
Central Hudson |  | Sungevity Inc | CH-09294 | Kingston | Ellenvl | Ulster | 12428 | G | 3078 | Greenfield Rd | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A-US | 2016-10-07 | 2016-10-07 | 0 | 2016-10-07 | [14 empty] | 2016-11-21 | 2016-11-21 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-00040 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 6073 | East Park | N |  | 15.2 | [13 empty] | NM | N | 2 SOLAREDGE 7600A-US | 2016-10-10 | 2016-10-11 | 1 | 2016-10-11 | [14 empty] | 2016-11-09 | 2016-11-09 |  | Y
Central Hudson |  | Lighthouse Solar | CH-00328 | Kingston |  |  | 12477 | G | 3002 | Saugerties | TBD |  | 100 | [13 empty] | NM | N | SOLECTRIA PVI 100KW | 2016-10-19 | 2016-10-24 | 3 | 2016-10-24 | 2016-10-24 | 2016-11-08 | 11 |  |  |  |  | 35000 | [9 empty] | W
Central Hudson |  | New York State Solar Farm | CH-00401 | Newburgh | New Paltz | Ulster | 12561 | G | 5031 | Galeville | N |  | 8 | [13 empty] | NM | N | 25 SUNPOWER SPR-E20 327-C-AC | 2016-10-10 | 2016-10-11 | 1 | 2016-10-11 | [14 empty] | 2016-12-02 | 2016-12-02 |  | Y
Central Hudson |  | PosiGen Solar | CH-02870 | Catskill |  |  | 12418 | G | 2043 | South Cairo | TBD |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000-US | 2016-10-10 | 2016-10-11 | 1 | 2016-10-11 | [17 empty] | W
Central Hudson |  | SolarCity | CH-05338 | Newburgh | New Paltz | Ulster | 12561 | G | 5023 | Ohioville | N |  | 5.2 | [13 empty] | NM | N | DELTA SOLIVIA TL 5.2 | 2016-10-11 | 2016-10-12 | 1 | 2016-10-12 | [14 empty] | 2017-02-02 | 2017-02-10 |  | Y
Central Hudson |  | SolarCity | CH-07049 | Newburgh | New Windsor | Orange | 12553 | G | 4046 | Union Ave | N |  | 10.4 | [13 empty] | NM | N | 2 DELTA SOLIVIA 5.2 TL | 2016-10-20 | 2016-10-20 | 0 | 2016-10-20 | [14 empty] | 2016-12-12 | 2017-01-17 |  | Y
Central Hudson |  | Trinity Solar | CH-08422 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7054 | Rhinebeck | N |  | 3 | [13 empty] | NM | N | SOLAREDGE SE3000-US | 2016-10-10 | 2016-10-11 | 1 | 2016-10-11 | [14 empty] | 2016-12-05 | 2016-12-05 |  | Y
Central Hudson |  | SolarCity | CH-05755 | Kingston | Saugerties | Ulster | 12477 | G | 2016 | Lincoln Park | N |  | 15.6 | [13 empty] | NM | N | DELTA SOLIVIA 6.6 TL DELTA SOLIVIA 5.2 TL DELTA SOLIVIA 3.8 TL | 2016-10-11 | 2016-10-25 | 10 | 2016-10-25 | [14 empty] | 2016-12-07 | 2016-12-07 |  | Y
Central Hudson |  | SolarCity | CH-05760 | Kingston | Kingston | Ulster | 12401 | G | 2016 | Lincoln Park | N |  | 5.2 | [13 empty] | NM | N | DELTA SOLIVIA 5.2 TL | 2016-11-01 | 2016-11-01 | 0 | 2016-11-01 | [14 empty] | 2017-02-09 | 2017-02-13 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-05772 | Kingston | Lk Katrine | Ulster | 12449 | G | 2016 | Lincoln Park | N |  | 10.4 | [13 empty] | NM | N | 2 DELTA SOLIVIA 5.2 TL | 2016-10-11 | 2016-10-25 | 10 | 2016-10-25 | [14 empty] | 2017-01-17 | 2017-01-17 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06071 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8092 | Fishkill Plains | N |  | 3.6 | [13 empty] | NM | N | ABB PVI 3.6 OUTD-S-US | 2016-10-11 | 2016-10-11 | 0 | 2016-10-11 | [14 empty] | 2016-11-22 | 2016-11-22 |  | Y
Central Hudson |  | SolarCity | CH-06452 | Catskill | Rensselaervl | Albany | 12147 | G | 1092 | Westerlo | N |  | 3 | [13 empty] | NM | N | ABB PVI 3.0-OUTD-S-US | 2016-10-11 | 2016-10-11 | 0 | 2016-10-11 | [14 empty] | 2017-06-19 | 2017-06-20 |  | Y
Central Hudson |  | SolarCity | CH-06954 | Fishkill | Putnam Valley | Putnam | 10524 | G | 8066 | Merritt Park | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2016-11-08 | 2016-11-08 | 0 | 2016-11-08 | [14 empty] | 2016-11-14 | 2016-11-14 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07600 | Newburgh | New Windsor | Orange | 12553 | G | 4044 | Union Ave | N |  | 3 | [13 empty] | NM | N | ABB PVI 3.0 OUTD-S-US | 2016-11-01 | 2016-11-01 | 0 | 2016-11-01 | [14 empty] | 2016-11-10 | 2016-11-10 |  | Y
Central Hudson |  | SolarCity | CH-07687 | Newburgh |  |  | 12549 | G | 4021 | Coldenham | TBD |  | 6.6 | [13 empty] | NM | N | DELTA SOLIVIA 6.6 | 2016-11-01 | 2016-11-01 | 0 | 2016-11-01 | [17 empty] | W
Central Hudson |  | Sungevity Inc | CH-09591 | Newburgh | Clintondale | Ulster | 12515 | G | 5081 | Highland | N |  | 3.8 | [13 empty] | NM | N | SOLAREDGE SE3800-US | 2016-10-11 | 2016-10-25 | 10 | 2016-10-25 | [14 empty] | 2016-12-13 | 2016-12-13 |  | Y
Central Hudson |  | Kasselman Solar | CH-00241 | Catskill | W Coxsackie | Greene | 12192 | G | 1076 | Coxsackie | N |  | 12.25 | [13 empty] | NM | N | 59 ENPHAASE M250 | 2016-10-19 | 2016-10-19 | 0 | 2016-10-19 | [14 empty] | 2016-10-26 | 2016-10-26 |  | Y
Central Hudson |  | New York State Solar Farm | CH-00441 | Newburgh | Marlboro | Ulster | 12542 | G | 5003 | Marlboro | N |  | 8 | [13 empty] | NM | N | 25 SUNPOWER SPR-E20 327-C-AC | 2016-10-17 | 2016-10-17 | 0 | 2016-10-17 | [14 empty] | 2016-11-28 | 2016-11-28 |  | Y
Central Hudson |  | NRG Home Solar | CH-00558 | Kingston | Tillson | Ulster | 12486 | G | 3022 | High Falls | N |  | 4.3 | [13 empty] | NM | N | 20 ENPHASE M215 240 | 2016-10-13 | 2016-10-14 | 1 | 2016-10-14 | [14 empty] | 2016-12-22 | 2016-12-22 |  | Y
Central Hudson |  | American Energy Care | CH-00658 | Poughkeepsie | Red Hook |  | 12571 | G | 7056 | Rhinebeck | N |  | 10 | [13 empty] | NM | N | SOLAREDGE SE10000A-US | 2016-10-13 | 2016-10-13 | 0 | 2016-10-13 | [17 empty] | W
Central Hudson |  | Grid Alternatives Tri-State | CH-01175 | Kingston | Kingston | Ulster | 12401 | G | 1022 | East Kingston | N |  | 3.01 | [13 empty] | NM | N | 14 ENPHASE M215-60-2LL-S2X-IG | 2016-10-13 | 2016-10-13 | 0 | 2016-10-13 | [14 empty] | 2017-05-19 | 2017-05-19 |  | Y
Central Hudson |  | Grid Alternatives Tri-State | CH-01177 | Kingston | Kingston | Ulster | 12401 | G | 1024 | East Kingston | N |  | 3.8 | [13 empty] | NM | N | SMA SB3800TL-US-22 | 2016-10-13 | 2016-10-18 | 3 | 2016-10-18 | [14 empty] | 2017-04-25 | 2017-04-25 |  | Y
Central Hudson |  | Hudson Solar | CH-01757 | Poughkeepsie | Staatsburg | Dutchess | 12580 | G | 7041 | Staatsburg | N | CH-01757 | 10 | [13 empty] | NM | N | SOLAREDGE SE 10000 A-US | 2016-10-14 | 2016-10-18 | 2 | 2016-10-18 | [14 empty] | 2016-11-28 | 2016-12-06 |  | Y
Central Hudson |  | SolarCity | CH-07009 | Newburgh | Newburgh | Orange | 12550 | G | 4047 | Union Ave | N |  | 3 | [13 empty] | NM | N | SOLAREDGE SE 3000A | 2016-10-12 | 2016-10-12 | 0 | 2016-10-12 | [14 empty] | 2016-12-09 | 2016-12-09 |  | Y
Central Hudson |  | SolarCity | CH-07278 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6065 | Inwood Ave | N |  | 5 | [13 empty] | NM | N | ABB PVI 5000 OUTD-US | 2016-10-12 | 2016-10-13 | 1 | 2016-10-13 | [14 empty] | 2017-01-19 | 2017-01-24 |  | Y
Central Hudson |  | Trinity Solar | CH-08589 | Catskill | Hunter | Greene | 12442 | E | 2081 | Hunter | N | CH-09658 | 3.8 | [13 empty] | NM | N | SOLAREDGE SE3800A-US | 2016-10-25 | 2016-10-25 | 0 | 2016-10-25 | [14 empty] | 2016-12-28 | 2016-12-28 |  | Y
Central Hudson |  | Direct Energy Solar | CH-01066 | Kingston | Saugerties | Ulster | 12477 | G | 3003 | Saugerties | N |  | 6.45 | [13 empty] | NM | N | 30 ENPHASE 215 | 2016-10-13 | 2016-10-13 | 0 | 2016-10-13 | [14 empty] | 2017-01-19 | 2017-01-23 |  | Y
Central Hudson |  | Hudson Solar | CH-01395 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8095 | Fishkill Plains | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE-6000 A-US | 2016-10-13 | 2016-10-13 | 0 | 2016-10-13 | [14 empty] | 2016-11-17 | 2016-11-18 |  | Y
Central Hudson |  | Hudson Solar | CH-01507 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8072 | Shenandoah | N |  | 11.4 | [13 empty] | NM | N | SOLAREDGE SE-11400 A-US | 2016-10-14 | 2016-10-14 | 0 | 2016-10-14 | [14 empty] | 2016-11-14 | 2016-11-18 |  | Y
Central Hudson |  | Hudson Solar | CH-02112 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 7024 | Tinkertown | N |  | 3 | [13 empty] | NM | N | SOLAREDGE SE-3000 A-US | 2016-10-18 | 2016-10-19 | 1 | 2016-10-19 | [14 empty] | 2016-12-15 | 2016-12-22 |  | Y
Central Hudson |  | Murphy Solar Power | CH-02760 | Kingston | Ellenvl | Ulster | 12428 | G | 3076 | Greenfield Rd | N |  | 5 | [13 empty] | NM | N | FRONIUS PRIMO 5000 | 2016-10-17 | 2016-10-17 | 0 | 2016-10-17 | [14 empty] | 2016-12-08 | 2016-12-12 |  | Y
Central Hudson |  | PosiGen Solar | CH-02901 | Newburgh | Modena | Ulster | 12548 | G | 5012 | Modena | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE7600S-US | 2016-10-13 | 2016-10-13 | 0 | 2016-10-13 | [14 empty] | 2016-11-14 | 2016-11-18 |  | Y
Central Hudson |  | Lighthouse Solar | CH-00297 | Newburgh | New Paltz | Ulster | 12561 | G | 5024 | Ohioville | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE 7600 A-US | 2016-10-17 | 2016-10-17 | 0 | 2016-10-17 | [14 empty] | 2016-11-15 | 2016-11-15 |  | Y
Central Hudson |  | Autonomous Energies LLC | CH-00748 | Kingston | Bloomington | Ulster | 12412 | G | 3012 | Woodstock | N |  | 8.8 | [13 empty] | NM | N | SMA 3.8 US-40 SMA 5.0 US-40 | 2016-10-14 | 2016-10-14 | 0 | 2016-10-14 | [14 empty] | 2017-02-06 | 2017-02-06 |  | Y
Central Hudson |  | Hudson Solar | CH-01779 | Poughkeepsie | Lagrangevl | Dutchess | 12540 | G | 6053 | Todd Hill | N |  | 16 | [13 empty] | NM | N | SOLAREDGE SE-6000 A-US SOLAREDGE SE-10000 A-US | 2016-10-14 | 2016-10-14 | 0 | 2016-10-14 | [14 empty] | 2016-12-08 | 2016-12-08 |  | Y
Central Hudson |  | Sun Mountain | CH-09109 | Newburgh | New Paltz | Ulster | 12561 | G | 5011 | Modena | N |  | 6 | [13 empty] | NM | N | SMA AMERICA 6.0 -US | 2016-10-14 | 2016-10-18 | 2 | 2016-10-18 | [14 empty] | 2016-12-20 | 2016-12-20 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Solar Generation | CH-08164 | Kingston | Woodstock | Ulster | 12498 | G | 3012 | Woodstock | N |  | 6 | [13 empty] | NM | N | SOLAREDGE 6000A | 2016-10-18 | 2016-10-18 | 0 | 2016-10-18 | [14 empty] | 2017-01-11 | 2017-01-11 |  | Y
Central Hudson |  | Solar Generation | CH-08204 | Kingston | Accord | Ulster | 12404 | G | 3024 | High Falls | N | CH-08204 | 5 | [13 empty] | NM | N | SMA SB 5.0 A | 2016-10-19 | 2016-10-19 | 0 | 2016-10-19 | [14 empty] | 2017-01-10 | 2017-01-10 |  | Y
Central Hudson |  | Solar Generation | CH-08226 | Kingston | Woodstock | Ulster | 12498 | G | 3012 | Woodstock | N |  | 10 | [13 empty] | NM | N | SMA SB 7.0 US SMA SB 3.0 US | 2016-10-18 | 2016-10-18 | 0 | 2016-10-18 | [8 empty] | 350 | 350 |  | 2016-12-08 | 2016-12-08 | 2017-01-27 | 2017-01-27 | 2017-02-02 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08766 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8071 | Shenandoah | N |  | 10.32 | [13 empty] | NM | N | 48 ENPHASE M215 | 2016-10-18 | 2016-10-18 | 0 | 2016-10-18 | [14 empty] | 2017-01-04 | 2017-01-04 |  | Y
Central Hudson |  | New York State Solar Farm | CH-00452 | Poughkeepsie | Poughkeepsie |  | 12603 | G | 6052 | Todd Hill | TBD |  | 12 | [13 empty] | NM | N | 2 SMA America SB6000TL-US-12 (240V) 2 SMA AMERICA SB TL | 2016-10-19 | 2016-10-31 | 8 | 2016-10-31 | [14 empty] | 2018-02-20 | 2018-02-20 |  | W
Central Hudson |  | PosiGen Solar | CH-02898 | Fishkill | Fishkill |  | 12524 | G | 8011 | Forgebrook | N |  | 3.8 | [13 empty] | NM | N | SOLARDEDGE SE3800A-US | 2016-10-19 | 2016-10-19 | 0 | 2016-10-19 | [17 empty] | W
Central Hudson |  | SolarCity | CH-06317 | Newburgh | Newburgh | Orange | 12550 | G | 5001 | Marlboro | N |  | 5.2 | [13 empty] | NM | N | DELTA SOLIVIA 5.2 | 2016-10-28 | 2016-10-28 | 0 | 2016-10-28 | [14 empty] | 2017-02-02 | 2017-02-02 |  | Y
Central Hudson |  | SolarCity | CH-06868 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8092 | Fishkill Plains | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2016-10-28 | 2016-10-28 | 0 | 2016-10-28 | [14 empty] | 2017-03-20 | 2017-03-23 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07505 | Kingston | West Camp | Ulster | 12490 | G | 3004 | Saugerties | N |  | 3.8 | [13 empty] | NM | N | DELTA SOLIVIA 3.8 TL | 2016-10-28 | 2016-10-28 | 0 | 2016-10-28 | [14 empty] | 2016-11-22 | 2016-11-22 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07534 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 6074 | East Park | N |  | 6.6 | [13 empty] | NM | N | DELTA SOLIVIA 6.6 | 2016-10-28 | 2016-10-28 | 0 | 2016-10-28 | [14 empty] | 2017-03-28 | 2017-03-28 |  | Y
Central Hudson |  | SolarCity | CH-07755 | Kingston | Kingston | Ulster | 12401 | G | 2017 | Lincoln Park | N |  | 3.8 | [13 empty] | NM | N | DELTA SOLIVIA 3.8 TL | 2016-10-28 | 2016-10-28 | 0 | 2016-10-28 | [14 empty] | 2016-12-02 | 2016-12-02 |  | Y
Central Hudson |  | SolarCity | CH-07766 | Newburgh | Clintondale | Ulster | 12515 | G | 5024 | Ohioville | N |  | 7.6 | [13 empty] | NM | N | DELTA SOLIVIA 7.6 TL | 2016-12-15 | 2016-12-15 | 0 | 2016-12-15 | [14 empty] | 2016-12-19 | 2016-12-22 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Trinity Solar | CH-08399 | Catskill | Ravena | Albany | 12143 | G | 1081 | New Baltimore | N |  | 5 | [13 empty] | NM | N | SOLDAREDGE SE5000 | 2016-10-19 | 2016-10-25 | 4 | 2016-10-25 | [8 empty] | 350 | 350 |  | 2017-01-23 | 2017-01-23 | 2017-02-23 | 2017-02-23 | 2017-02-24 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08706 | Fishkill | Beacon | Dutchess | 12508 | G | 8087 | Tioronda | N |  | 8.6 | [13 empty] | NM | N | 40 ENPHASE M215 | 2016-10-19 | 2016-10-19 | 0 | 2016-10-19 | [14 empty] | 2017-05-10 | 2017-05-10 |  | Y
Central Hudson |  | RGS Energy | CH-00003 | Poughkeepsie | Lagrangevl | Dutchess | 12540 | G | 6055 | Todd Hill | N | CH-03033 | 2.5 | [13 empty] | NM | N | 10 ENPHASE M250-60-2LL-S22 | 2016-10-27 | 2016-10-27 | 0 | 2016-10-27 | [14 empty] | 2017-02-07 | 2017-02-07 |  | Y
Central Hudson |  | Lotus Energy Inc. | CH-00332 | Catskill | Catskill | Greene | 12414 | G | 2042 | South Cairo | N |  | 7.68 | [13 empty] | NM | N | 24 SUNPOWER SPR327-C-AC | 2016-11-04 | 2016-11-04 | 0 | 2016-11-04 | [14 empty] | 2016-12-20 | 2016-12-20 |  | Y
Central Hudson |  | Malcarne Contracting | CH-00351 | Poughkeepsie | Staatsburg | Dutchess | 12580 | G | 7041 | Staatsburg | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE7600A US | 2016-10-20 | 2016-10-20 | 0 | 2016-10-20 | [14 empty] | 2016-12-14 | 2016-12-28 |  | Y
Central Hudson |  | NRG Home Solar | CH-00532 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6094 | Manchester | N |  | 4.08 | [13 empty] | NM | N | 19 ENPHASE M15 | 2016-10-21 | 2016-10-21 | 0 | 2016-10-21 | [14 empty] | 2017-02-07 | 2017-02-13 |  | Y
Central Hudson |  | Sol Providers | CH-08966 | Poughkeepsie | Poughkeepsie |  | 12601 | G | 6066 | Inwood Ave | N |  | 6.4 | [13 empty] | NM | N | 20 SUNPOWER X21 335 BLK-C-AC | 2016-10-24 | 2016-10-24 | 0 | 2016-10-24 | [14 empty] | 2016-11-18 | 2016-11-30 |  | W
Central Hudson |  | Infinity Solar Systems | CH-00134 | Newburgh | Marlboro | Ulster | 12542 | G | 5003 | Marlboro | N |  | 9.6 | [13 empty] | NM | N | 30 SUNPOWER SPR-E20-327-C-AC | 2016-10-21 | 2016-10-24 | 1 | 2016-10-24 | [14 empty] | 2016-12-01 | 2016-12-01 |  | Y
Central Hudson |  | Hudson Solar | CH-01319 | Poughkeepsie | Red Hook |  | 12571 | G | 7054 | Rhinebeck | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE-7600 A-US | 2016-10-21 | 2016-10-24 | 1 | 2016-10-24 | [17 empty] | W
Central Hudson |  | Hudson Solar | CH-01756 | Poughkeepsie | Staatsburg | Dutchess | 12580 | G | 7041 | Staatsburg | N |  | 6.08 | [13 empty] | NM | N | 19 SUNPOWER SPR-X22-360-C-AC | 2016-10-21 | 2016-10-21 | 0 | 2016-10-21 | [14 empty] | 2017-02-02 | 2017-02-02 |  | Y
Central Hudson |  | Hudson Solar | CH-01859 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7061 | Milan | N |  | 11.4 | [13 empty] | NM | N | SOLAREDGE SE-11400 A-US | 2016-10-21 | 2016-10-24 | 1 | 2016-10-24 | [14 empty] | 2016-12-30 | 2016-12-30 |  | Y
Central Hudson |  | Hudson Solar | CH-02279 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7061 | Milan | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE7600 A-US | 2016-10-21 | 2016-10-24 | 1 | 2016-10-24 | [14 empty] | 2016-12-19 | 2016-12-27 |  | Y
Central Hudson |  | Hudson Solar | CH-02391 | Newburgh | Newburgh | Orange | 12550 | G | 4014 | West Balmville | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE-6000 A-US | 2016-10-21 | 2016-10-24 | 1 | 2016-10-24 | [14 empty] | 2017-01-23 | 2017-01-23 |  | Y
Central Hudson |  | SolarCity | CH-07141 | Newburgh | Campbell Hall | Orange | 10916 | G | 5052 | Maybrook | N |  | 11.8 | [13 empty] | NM | N | DELTA SOLIVIA 5.2 TL DELTA SOLIVIA 6.6 TL | 2016-11-08 | 2016-11-08 | 0 | 2016-11-08 | [8 empty] | 350 | 350 |  | 2016-12-13 | 2016-12-13 | 2016-12-16 | 2017-02-02 | 2017-02-02 |  | Y
Central Hudson |  | Trinity Solar | CH-08367 | Poughkeepsie | Verbank | Dutchess | 12585 | G | 6057 | Todd Hill | N |  | 3.8 | [13 empty] | NM | N | SOLAREDGE SE 3800 A-US | 2016-10-21 | 2016-10-24 | 1 | 2016-10-24 | [14 empty] | 2017-01-19 | 2017-01-19 |  | Y
Central Hudson |  | SolarCity | CH-05059 | Newburgh | New Paltz | Ulster | 12561 | G | 5024 | Ohioville | N |  | 10.4 | [13 empty] | NM | N | 2 DELTA SOLIVIA 5.2 TL | 2016-10-24 | 2016-10-24 | 0 | 2016-10-24 | [14 empty] | 2017-01-23 | 2017-01-23 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-05148 | Newburgh | Newburgh | Orange | 12550 | G | 4023 | Coldenham | N |  | 5.2 | [13 empty] | NM | N | DELTA SOLIVIA 5.2 | 2016-12-16 | 2016-12-16 | 0 | 2016-12-16 | [14 empty] | 2017-01-25 | 2017-01-25 |  | Y
Central Hudson |  | SolarCity | CH-05256 | Poughkeepsie | Dover Plains | Dutchess | 12522 | G | 7025 | Tinkertown | N |  | 7.5 | [13 empty] | NM | N | FRONIUS IG PLUS A 7.5 | 2016-10-24 | 2016-10-24 | 0 | 2016-10-24 | [14 empty] | 2016-10-26 | 2016-10-27 |  | Y
Central Hudson |  | SolarCity | CH-05372 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 7024 | Tinkertown | N |  | 7.6 | [13 empty] | NM | N | DELTA SOLIVIA 7.6 | 2016-10-27 | 2016-10-27 | 0 | 2016-10-27 | [14 empty] | 2016-12-16 | 2016-12-22 |  | Y
Central Hudson |  | SolarCity | CH-05829 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6065 | Inwood Ave | N |  | 10.4 | [13 empty] | NM | N | 2 DELTA SOLIVIA 5.2 | 2016-10-25 | 2016-10-25 | 0 | 2016-10-25 | [14 empty] | 2016-11-16 | 2016-11-22 |  | Y
Central Hudson |  | SolarCity | CH-06518 | Kingston | Port Ewen | Ulster | 12466 | G | 1024 | East Kingston | N |  | 15.8 | [13 empty] | NM | N | FRONIUS PRIMO 8.2 FRONIUS PRIMO 7.6 | 2016-10-24 | 2016-11-07 | 10 | 2016-11-07 | [14 empty] | 2016-12-30 | 2016-12-30 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07033 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 12.8 | [13 empty] | NM | N | DELTA SOLIVIA 5.2 TL DELTA SOLIVIA 7.6 | 2016-11-02 | 2016-11-02 | 0 | 2016-11-02 | [14 empty] | 2017-01-25 | 2017-01-30 |  | Y
Central Hudson |  | SolarCity | CH-07345 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8045 | Myers Corners | N |  | 8.2 | [13 empty] | NM | N | FRONIUS PRIMO 8.2 | 2016-10-24 | 2016-10-24 | 0 | 2016-10-24 | [14 empty] | 2016-12-29 | 2016-12-29 |  | Y
Central Hudson |  | SolarCity | CH-07652 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6051 | Todd Hill | N |  | 10.2 | [13 empty] | NM | N | ABB PVI-6000 OUTD-US ABB PVI-4.2 OUTD-S-US | 2016-11-01 | 2016-11-02 | 1 | 2016-11-02 | [14 empty] | 2016-12-20 | 2016-12-20 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Empire Solar Solutions | CH-00049 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6046 | Spackenkill | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE 7600A-US | 2016-10-25 | 2016-10-25 | 0 | 2016-10-25 | [14 empty] | 2016-11-30 | 2016-12-07 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-00101 | Fishkill | Hopewell Junction | Dutchess | 12533 | G | 8072 | Shenandoah | N |  | 15.2 | [13 empty] | NM | N | 2 SOLAREDGE 7600A-US | 2016-10-25 | 2016-10-25 | 0 | 2016-10-25 | [8 empty] | 350 | 350 |  | 2016-12-28 | 2016-12-28 | 2017-01-11 | 2017-01-11 | 2017-01-13 |  | Y
Central Hudson |  | SolarCity | CH-05224 | Newburgh | Newburgh | Orange | 12550 | G | 5004 | Marlboro | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE 6000A | 2016-10-27 | 2016-10-27 | 0 | 2016-10-27 | [14 empty] | 2017-01-25 | 2017-01-25 |  | Y
Central Hudson |  | SolarCity | CH-05365 | Newburgh | New Windsor | Orange | 12553 | G | 4094 | Bethlehem Rd | N |  | 5.2 | [13 empty] | NM | N | DELTA SOLIVIA 5.2TL | 2016-10-27 | 2016-10-27 | 0 | 2016-10-27 | [14 empty] | 2017-02-03 | 2017-02-03 |  | Y
Central Hudson |  | SolarCity | CH-06503 | Kingston | Kingston | Ulster | 12401 | G | 2017 | Lincoln Park | N |  | 8.6 | [13 empty] | NM | N | ABB PVI 3.6 ABB PVI 5000 | 2016-10-25 | 2016-10-25 | 0 | 2016-10-25 | [14 empty] | 2016-10-28 | 2016-11-03 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06514 | Kingston | Port Ewen | Ulster | 12466 | G | 1012 | Boulevard | N |  | 10.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 ABB PVI 3.0 | 2016-11-02 | 2016-11-02 | 0 | 2016-11-02 | [14 empty] | 2017-01-23 | 2017-01-23 |  | Y
Central Hudson |  | SolarCity | CH-06604 | Kingston | Lake Katrine | Ulster | 12449 | G | 2016 | Lincoln Park | N |  | 11.4 | [13 empty] | NM | N | DELTA SOLIVIA 7.6 TL DELTA SOLIVIA 3.8 TL | 2016-10-25 | 2016-10-25 | 0 | 2016-10-25 | [14 empty] | 2017-02-06 | 2017-02-06 |  | Y
Central Hudson |  | SolarCity | CH-07212 | Kingston | Kingston | Ulster | 12401 | G | 2013 | Lincoln Park | N |  | 7.6 | [13 empty] | NM | N | DELTA SOLIVIA 7.6 | 2016-10-25 | 2016-10-25 | 0 | 2016-10-25 | [14 empty] | 2017-07-13 | 2017-07-13 |  | Y
Central Hudson |  | SolarCity | CH-07649 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6065 | Inwood Ave | N |  | 10.4 | [13 empty] | NM | N | 2 DELTA SOLIVIA 5.2 | 2016-10-27 | 2016-10-27 | 0 | 2016-10-27 | [14 empty] | 2017-02-22 | 2017-02-27 |  | Y
Central Hudson |  | Trinity Solar | CH-08525 | Catskill |  |  | 12418 | G | 2043 | South Cairo | TBD |  | 7.6 | [13 empty] | NM | N | SOLAREDGE 7600 A US | 2016-10-25 | 2016-10-26 | 1 | 2016-10-26 | [17 empty] | W
Central Hudson |  | Trinity Solar | CH-08567 | Newburgh | Newburgh | Orange | 12550 | G | 4012 | West Balmville | N | CH-08567 | 6 | [13 empty] | NM | N | SOLAREDGE SE600A-US | 2016-10-25 | 2016-10-25 | 0 | 2016-10-25 | [14 empty] | 2016-12-28 | 2016-12-28 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-00188 | Newburgh | New Windsor | Orange | 12553 | G | 4046 | Union Ave | N |  | 7.68 | [13 empty] | NM | N | 24 SUNPOWERSPR-E20-327 C-AC | 2016-10-26 | 2016-10-27 | 1 | 2016-10-27 | [14 empty] | 2017-01-19 | 2017-01-19 |  | Y
Central Hudson |  | New York State Solar Farm | CH-00395 | Poughkeepsie | Pine Plns | Dutchess | 12567 | G | 7091 | Pulvers Corners | N |  | 15.04 | [13 empty] | NM | N | 47 SUNPOWER SP 345-C-AC | 2016-11-02 | 2016-11-02 | 0 | 2016-11-02 | [14 empty] | 2016-12-22 | 2016-12-27 |  | Y
Central Hudson |  | NRG Home Solar | CH-00511 | Fishkill |  |  | 12508 | G | 8015 | Forgebrook | TBD |  | 3.65 | [13 empty] | NM | N | 17 ENPHASE M215 240 | 2016-10-26 | 2016-10-27 | 1 | 2016-10-27 | [17 empty] | W
Central Hudson |  | Hudson Solar | CH-02140 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7062 | Milan | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE-6000 A-US | 2016-10-26 | 2016-10-27 | 1 | 2016-10-27 | [14 empty] | 2016-10-27 | 2016-10-27 |  | Y
Central Hudson |  | PosiGen Solar | CH-02878 | Catskill |  |  | 12143 | G | 1082 | New Baltimore | TBD |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A-US | 2016-10-26 | 2016-10-27 | 1 | 2016-10-27 | [17 empty] | W
Central Hudson |  | SolarCity | CH-05139 | Kingston | Saugerties | Ulster | 12477 | G | 3001 | Saugerties | N |  | 5.2 | [13 empty] | NM | N | DELTA SOLIVIA 5.2 TL | 2016-11-22 | 2016-11-22 | 0 | 2016-11-22 | [14 empty] | 2017-01-20 | 2017-01-20 |  | Y
Central Hudson |  | SolarCity | CH-06368 | Newburgh | Wallkill | Ulster | 12589 | G | 5042 | East Walden | N |  | 7.6 | [13 empty] | NM | N | DELTA SOLIVIA 7.6 | 2016-11-14 | 2016-11-14 | 0 | 2016-11-14 | [14 empty] | 2016-11-29 | 2016-11-29 |  | Y
Central Hudson |  | SolarCity | CH-06574 | Kingston | Saugerties | Ulster | 12477 | G | 3004 | Saugerties | N |  | 10 | [13 empty] | NM | N | SOLAREDGE SE 10000A | 2016-10-26 | 2016-10-26 | 0 | 2016-10-26 | [14 empty] | 2017-01-24 | 2017-02-02 |  | Y
Central Hudson |  | SolarCity | CH-07284 | Poughkeepsie |  |  | 12601 | G | 6073 | East Park | TBD |  | 7.6 | [13 empty] | NM | N | DELTA SOLIVIA 7.6TL | 2016-10-26 | 2016-10-26 | 0 | 2016-10-26 | [17 empty] | W
Central Hudson |  | SolarCity | CH-07294 | Poughkeepsie | Staatsburg |  | 12580 | G | 7042 | Staatsburg | TBD |  | 10.4 | [13 empty] | NM | N | DELTA SOLIVIA 5.2 (2) | 2016-11-02 | 2016-11-02 | 0 | 2016-11-02 | [17 empty] | W
Central Hudson |  | SolarCity | CH-07426 | Newburgh | Newburgh | Orange | 12550 | G | 4023 | Coldenham | N |  | 5.2 | [13 empty] | NM | N | DELTA SOLIVIA 5.2TL | 2016-10-26 | 2016-10-26 | 0 | 2016-10-26 | [14 empty] | 2017-01-10 | 2017-01-16 |  | Y
Central Hudson |  | Trinity Solar | CH-08593 | Poughkeepsie |  |  | 12601 | G | 6011 | Sand Dock | TBD |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000-US | 2016-10-27 | 2016-10-27 | 0 | 2016-10-27 | [17 empty] | W
Central Hudson |  | Empire Solar Solutions | CH-00024 | Newburgh | New Paltz | Ulster | 12561 | G | 5023 | Ohioville | N |  | 10 | [13 empty] | NM | N | SOLAREDGE 10000A-US | 2016-10-31 | 2016-10-31 | 0 | 2016-10-31 | [14 empty] | 2016-12-16 | 2016-12-22 |  | Y
Central Hudson |  | PosiGen Solar | CH-02867 | Catskill | Catskill | Greene | 12414 | G | 2042 | South Cairo | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE 5000A-US | 2016-10-27 | 2016-10-27 | 0 | 2016-10-27 | [14 empty] | 2017-04-20 | 2017-04-21 |  | Y
Central Hudson |  | SolarCity | CH-06197 | Newburgh | Newburgh | Orange | 12550 | G | 4014 | West Balmville | N |  | 5.2 | [13 empty] | NM | N | DELTA SOLIVIA 5.2 | 2016-10-27 | 2016-10-27 | 0 | 2016-10-27 | [14 empty] | 2016-12-12 | 2016-12-12 |  | Y
Central Hudson |  | Trinity Solar | CH-08383 | Catskill |  |  | 12414 | G | 2005 | North Catskill | TBD |  | 10 | [13 empty] | NM | N | 1 SOLAREDGE SE10000A-US | 2016-10-27 | 2016-11-02 | 4 | 2016-11-02 | [17 empty] | W
Central Hudson |  | Trinity Solar | CH-08555 | Newburgh | Maybrook | Orange | 12543 | G | 4026 | Coldenham | N |  | 3 | [13 empty] | NM | N | SOLAREDGE SE3000A-US | 2016-10-28 | 2016-10-28 | 0 | 2016-10-28 | [14 empty] | 2017-02-03 | 2017-02-06 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-00216 | Newburgh | Newburgh | Orange | 12550 | G | 4014 | West Balmville | N |  | 4.16 | [13 empty] | NM | N | 13 SUNPOWER SPR-E20-327-C-AC | 2016-10-28 | 2016-10-28 | 0 | 2016-10-28 | [14 empty] | 2017-01-31 | 2017-01-31 |  | Y
Central Hudson |  | Kirchhoff Green Energy LLC | CH-00259 | Poughkeepsie | Millbrook | Dutchess | 12545 | G | 7012 | Hibernia | N |  | 49 | [13 empty] | NM | N | 7 SMA AMERICA 7.0 | 2016-11-08 | 2016-11-22 | 10 | 2016-11-22 | [14 empty] | 2017-05-24 | 2017-05-31 |  | Y
Central Hudson |  | SolarCity | CH-05167 | Newburgh | Newburgh | Orange | 12550 | G | 5004 | Marlboro | N |  | 7.6 | [13 empty] | NM | N | DELTA SOLIVIA 7.6 | 2016-10-28 | 2016-10-28 | 0 | 2016-10-28 | [14 empty] | 2016-12-06 | 2016-12-13 |  | Y
Central Hudson |  | SolarCity | CH-05451 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8071 | Shenandoah | N |  | 7.6 | [13 empty] | NM | N | DELTA SOLIVIA 7.6 | 2016-11-02 | 2016-11-02 | 0 | 2016-11-02 | [14 empty] | 2016-11-10 | 2016-11-14 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-05792 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6011 | Sand Dock | N |  | 7.6 | [13 empty] | NM | N | Delta Solivia 7.6TL | 2016-10-28 | 2016-10-28 | 0 | 2016-10-28 | [14 empty] | 2017-03-02 | 2017-03-02 |  | Y
Central Hudson |  | SolarCity | CH-05843 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 6073 | East Park | N |  | 14.2 | [13 empty] | NM | N | DELTA SOLIVIA 6.6 DELTA SOLIVIA 7.6 | 2016-11-01 | 2016-11-01 | 0 | 2016-11-01 | [14 empty] | 2017-05-23 | 2017-05-23 |  | Y
Central Hudson |  | SolarCity | CH-06581 | Kingston | Saugerties | Ulster | 12477 | G | 3001 | Saugerties | N |  | 14.4 | [13 empty] | NM | N | SOLAREDGE SE 3000A-US SOLAREDGE SE 114000A-US | 2016-10-28 | 2016-10-28 | 0 | 2016-10-28 | [14 empty] | 2016-12-19 | 2016-12-19 |  | Y
Central Hudson |  | SolarCity | CH-06920 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8055 | North Chelsea | N |  | 11.4 | [13 empty] | NM | N | DELTA SOLIVIA 7.6 TL DELTA SOLIVIA 3.8 TL | 2016-10-28 | 2016-10-28 | 0 | 2016-10-28 | [14 empty] | 2017-01-25 | 2017-01-30 |  | Y
Central Hudson |  | SolarCity | CH-07448 | Newburgh | Wallkill | Ulster | 12589 | G | 5041 | East Walden | N |  | 3 | [13 empty] | NM | N | ABB PVI 3.0 OUTD-S-US | 2016-10-28 | 2016-10-28 | 0 | 2016-10-28 | [14 empty] | 2016-11-10 | 2016-11-15 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07658 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8023 | Knapps Corners | N |  | 6 | [13 empty] | NM | N | ABB PVI 6000 OUTD US | 2016-11-02 | 2016-11-02 | 0 | 2016-11-02 | [14 empty] | 2016-11-10 | 2016-11-10 |  | Y
Central Hudson |  | SolarCity | CH-07814 | Poughkeepsie | Lagrangevl | Dutchess | 12540 | G | 6057 | Todd Hill | N | CH-05874 | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2017-01-24 | 2017-01-24 | 0 | 2017-01-24 | [14 empty] | 2017-02-24 | 2017-02-24 |  | Y
Central Hudson |  | Trinity Solar | CH-08419 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 7024 | Tinkertown | N |  | 10 | [13 empty] | NM | N | SOLAREDGE SE10000A-US | 2016-10-28 | 2016-11-10 | 9 | 2016-11-10 | [14 empty] | 2017-01-30 | 2017-02-06 |  | Y
Central Hudson |  | New York State Solar Farm | CH-00465 | Kingston | Saugerties | Ulster | 12477 | G | 3002 | Saugerties | N | CH-00465 | 6.08 | [13 empty] | NM | N | 19 SUNPOWER SPR-X21 345-C-AC | 2016-10-31 | 2016-10-31 | 0 | 2016-10-31 | [14 empty] | 2016-12-09 | 2016-12-09 |  | Y
Central Hudson |  | New York State Solar Farm | CH-00472 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 6075 | East Park | N | CH-02083 | 2.88 | [13 empty] | NM | N | 9 SUNPOWER SPR-E20 327-C-AC | 2016-10-31 | 2016-10-31 | 0 | 2016-10-31 | [14 empty] | 2017-01-13 | 2017-01-13 |  | Y
Central Hudson |  | NRG Home Solar | CH-00514 | Fishkill |  |  | 12508 | G | 8018 | Forgebrook | N |  | 3.44 | [13 empty] | NM | N | 16 ENPHASE M215 | 2016-11-01 | 2016-11-01 | 0 | 2016-11-01 | [17 empty] | W
Central Hudson |  | Direct Energy Solar | CH-01009 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7054 | Rhinebeck | N |  | 4.5 | [13 empty] | NM | N | 18 ENPHASE M250 | 2016-10-31 | 2016-10-31 | 0 | 2016-10-31 | [14 empty] | 2017-07-26 | 2017-07-26 |  | Y
Central Hudson |  | Hudson Solar | CH-02390 | Fishkill |  |  | 10516 | G | 8086 | Tioronda | TBD |  | 7.6 | [13 empty] | NM | N | 1 SOLAREDGE SE-7600A-US | 2016-11-15 | 2016-11-15 | 0 | 2016-11-15 | [17 empty] | W
Central Hudson |  | Novel Approaches | CH-02781 | Kingston | Greenfield Pk | Ulster | 12435 | G | 3096 | Grimley Rd | N | CH-02781 | 12.5 | [13 empty] | NM | N | FRONIUS 12.5 | 2016-11-01 | 2016-11-01 | 0 | 2016-11-01 | [14 empty] | 2016-11-28 | 2016-11-28 |  | Y
Central Hudson |  | PosiGen Solar | CH-02861 | Catskill | Ravena |  | 12143 | G | 1081 | New Baltimore | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE 5000A-US | 2016-10-31 | 2016-10-31 | 0 | 2016-10-31 | [14 empty] | 2016-11-17 | 2016-11-23 |  | W
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08771 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 5.59 | [13 empty] | NM | N | 26 ENPHASE M215 | 2016-10-31 | 2016-10-31 | 0 | 2016-10-31 | [14 empty] | 2017-08-11 | 2017-08-17 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08772 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 4.945 | [13 empty] | NM | N | 23 ENPHASE M215 | 2016-10-31 | 2016-10-31 | 0 | 2016-10-31 | [14 empty] | 2017-03-02 | 2017-03-02 |  | Y
Central Hudson |  | Solar Maximum LLC, dba RevoluSun | CH-09032 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8071 | Shenandoah | N |  | 9.92 | [13 empty] | NM | N | 31 SUNPOWER X21-345-C-AC | 2016-11-01 | 2016-11-07 | 4 | 2016-11-07 | [14 empty] | 2016-12-20 | 2016-12-20 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-03340 | Newburgh | Campbell Hall | Orange | 10916 | G | 5051 | Maybrook | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A US | 2016-11-01 | 2016-11-01 | 0 | 2016-11-01 | [14 empty] | 2017-05-17 | 2017-05-31 |  | Y
Central Hudson |  | SolarCity | CH-07174 | Newburgh | New Windsor | Orange | 12553 | G | 4094 | Bethlehem Rd | N | CH-07174 | 8.2 | [13 empty] | NM | N | FRONIUS PRIMO 8.2 | 2016-11-11 | 2016-11-11 | 0 | 2016-11-11 | [14 empty] | 2016-11-15 | 2016-11-22 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07395 | Fishkill | Beacon | Dutchess | 12508 | G | 8085 | Tioronda | N |  | 5 | [13 empty] | NM | N | Solar Edge SE5000 | 2016-11-01 | 2016-11-01 | 0 | 2016-11-01 | [14 empty] | 2016-12-28 | 2016-12-28 |  | Y
Central Hudson |  | New York State Solar Farm | CH-00432 | Fishkill | Beacon | Dutchess | 12508 | G | 8017 | Forgebrook | N |  | 5.44 | [13 empty] | NM | N | 17 SUNPOWER SPR-X21 345-C-AC | 2016-11-02 | 2016-11-02 | 0 | 2016-11-02 | [14 empty] | 2016-11-30 | 2016-11-30 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00945 | Poughkeepsie | Tivoli | Dutchess | 12583 | G | 7062 | Milan | N |  | 9 | [13 empty] | NM | N | 36 ENPHASE M250 | 2016-11-02 | 2016-11-16 | 10 | 2016-11-16 | [14 empty] | 2017-01-19 | 2017-01-23 |  | Y
Central Hudson |  | PosiGen Solar | CH-02897 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8092 | Fishkill Plains | N |  | 3.8 | [13 empty] | NM | N | SOLAREDGE SE3800A-US | 2016-11-02 | 2016-11-02 | 0 | 2016-11-02 | [14 empty] | 2017-04-21 | 2017-04-21 |  | Y
Central Hudson |  | Sungevity Inc | CH-09469 | Newburgh | Newburgh | Orange | 12550 | G | 4012 | West Balmville | N |  | 3.8 | [13 empty] | NM | N | SOLAREDGE SE 3800A-US | 2016-11-04 | 2016-11-04 | 0 | 2016-11-04 | [14 empty] | 2017-05-08 | 2017-06-19 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-00160 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 8.96 | [13 empty] | NM | N | 28 SUNPOWER SPR-E20-327 C-AC | 2016-11-04 | 2016-11-04 | 0 | 2016-11-04 | [14 empty] | 2017-01-19 | 2017-01-27 |  | Y
Central Hudson |  | Grid Alternatives Tri-State | CH-01179 | Kingston | Kingston | Ulster | 12401 | G | 1022 | East Kingston | N |  | 3.375 | [13 empty] | NM | N | 15 SUNPOWER SPR-20E-WHT-U-ACPV | 2016-11-18 | 2016-11-18 | 0 | 2016-11-18 | [14 empty] | 2017-07-26 | 2017-07-26 |  | Y
Central Hudson |  | Hudson Solar | CH-01827 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7056 | Rhinebeck | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE-5000A-US | 2016-11-08 | 2016-11-08 | 0 | 2016-11-08 | [14 empty] | 2017-07-19 | 2017-07-20 |  | Y
Central Hudson |  | Paradise Energy Solutions LLC | CH-02829 | Catskill | Palenvl | Greene | 12463 | G | 2001 | North Catskill | N |  | 11.4 | [13 empty] | NM | N | SOLAREDGE 11400A-US | 2016-11-04 | 2016-11-08 | 2 | 2016-11-08 | [14 empty] | 2016-12-01 | 2016-12-02 |  | Y
Central Hudson |  | PosiGen Solar | CH-02894 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6065 | Inwood Ave | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A-US | 2016-11-04 | 2016-11-04 | 0 | 2016-11-04 | [14 empty] | 2016-12-07 | 2016-12-08 |  | Y
Central Hudson |  | PosiGen Solar | CH-02905 | Catskill | Cairo | Greene | 12413 | G | 2005 | North Catskill | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A-US | 2016-11-04 | 2016-11-04 | 0 | 2016-11-04 | [14 empty] | 2017-04-21 | 2017-04-21 |  | Y
Central Hudson |  | SolarCity | CH-05275 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8092 | Fishkill Plains | N |  | 10.4 | [13 empty] | NM | N | 2 DELTA SOLIVIA 5.2 | 2016-12-08 | 2016-12-08 | 0 | 2016-12-08 | [14 empty] | 2016-12-19 | 2017-01-04 |  | Y
Central Hudson |  | SolarCity | CH-06139 | Fishkill | Beacon | Dutchess | 12508 | G | 8015 | Forgebrook | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000 | 2016-11-16 | 2016-11-17 | 1 | 2016-11-17 | [14 empty] | 2017-02-10 | 2017-02-13 |  | Y
Central Hudson |  | SolarCity | CH-07778 | Kingston | Kingston | Ulster | 12401 | G | 3013 | Woodstock | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2016-11-16 | 2016-11-16 | 0 | 2016-11-16 | [14 empty] | 2016-12-08 | 2016-12-08 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03325 | Kingston | Ulster |  | 12401 | G | 1011 | Boulevard | N | CH-03325 | [14 empty] | CDG | Y | HUAWEI SUN2000-45KTL-US-150 (44) | 2016-12-30 | 2016-12-30 | 0 | 2016-12-30 | 2016-12-30 | 2017-01-20 | 14 | 2017-03-08 | 2017-04-17 | 2017-07-12 | 60 | 40000 |  |  | 2017-10-18 | 2018-04-13 | 2018-04-13 |  |  |  |  | W |  | There are 2 accounts at this location with an aggregate CESIR Cost to Customer of $40,000 & Estimated Project Upgrade Costs of $595,571. 6/6/18 - Received request to combine with Project CH-03326; current deadlines suspended. 5/15/19 - Developer decision to combine received. CH-03325 & CH-03326 consolidated to one 3.96 MW project,
Central Hudson |  | Infinity Solar Systems | CH-00153 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8052 | North Chelsea | N |  | 9.6 | [13 empty] | NM | N | 30 SUNPOWER SPR-E20-327 C-AC | 2016-11-07 | 2016-11-07 | 0 | 2016-11-07 | [14 empty] | 2017-01-18 | 2017-01-18 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-00206 | Fishkill | Beacon | Dutchess | 12508 | G | 8085 | Tioronda | N |  | 5.76 | [13 empty] | NM | N | 18 SUNPOWER SPR-X21-335-BLK C-AC | 2016-11-07 | 2016-11-07 | 0 | 2016-11-07 | [14 empty] | 2016-12-08 | 2016-12-08 |  | Y
Central Hudson |  | Grid Alternatives Tri-State | CH-01178 | Kingston | Kingston | Ulster | 12401 | G | 2093 | Hurley Ave | N |  | 4 | [13 empty] | NM | N | SMA AMERICA SB4000 | 2016-11-07 | 2016-11-21 | 10 | 2016-11-21 | [14 empty] | 2017-04-25 | 2017-04-27 |  | Y
Central Hudson |  | SolarCity | CH-05013 | Kingston | Kingston | Ulster | 12401 | G | 2094 | Hurley Ave | N |  | 15.2 | [13 empty] | NM | N | 2 DELTA SOLIVIA 7.6 | 2016-11-07 | 2016-11-08 | 1 | 2016-11-08 | [14 empty] | 2017-02-03 | 2017-02-03 |  | Y
Central Hudson |  | SolarCity | CH-06508 | Kingston |  |  | 12401 | G | 2017 | Lincoln Park | TBD |  | 3.8 | [13 empty] | NM | N | DELTA SOLIVIA 3.8 | 2016-11-08 | 2016-11-08 | 0 | 2016-11-08 | [17 empty] | W
Central Hudson |  | SolarCity | CH-06522 | Kingston | Port Ewen | Ulster | 12466 | G | 1012 | Boulevard | N |  | 7.6 | [13 empty] | NM | N | DELTA SOLIVIA 7.6 | 2016-11-15 | 2016-11-15 | 0 | 2016-11-15 | [14 empty] | 2016-12-21 | 2016-12-28 |  | Y
Central Hudson |  | SolarCity | CH-06536 | Kingston | Woodstock | Ulster | 12498 | G | 3013 | Woodstock | Y |  | 7.6 | 7.6 | [12 empty] | NM | N | SOLAREDGE STOREDGE 7.6 SE7600A-US1SolarEdge TechnologiesSE7600-USS | 2016-11-07 | 2016-11-15 | 6 | 2016-11-15 | [14 empty] | 2017-06-12 | 2017-06-19 |  | Y
Central Hudson |  | SolarCity | CH-06621 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6045 | Spackenkill | N |  | 7.6 | [13 empty] | NM | N | DELTA SOLIVIA 7.6 | 2016-11-07 | 2016-11-07 | 0 | 2016-11-07 | [14 empty] | 2016-12-06 | 2016-12-06 |  | Y
Central Hudson |  | SolarCity | CH-06624 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6011 | Sand Dock | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE 6000a | 2016-11-07 | 2016-11-21 | 10 | 2016-11-21 | [14 empty] | 2017-01-25 | 2017-01-25 |  | Y
Central Hudson |  | Trinity Solar | CH-08587 | Newburgh | Milton | Ulster | 12547 | G | 5083 | Highland | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE7600A-US | 2016-11-07 | 2016-11-08 | 1 | 2016-11-08 | [14 empty] | 2017-01-25 | 2017-02-03 |  | Y
Central Hudson |  | Sol Providers | CH-08934 | Newburgh | Newburgh | Orange | 12550 | G | 4047 | Union Ave | N |  | 15.7 | [13 empty] | RNM | N | 73 ENPHASE M215 | 2016-11-07 | 2016-11-07 | 0 | 2016-11-07 | [14 empty] | 2016-11-30 | 2016-12-06 |  | W
Central Hudson |  | Solar Flair | CH-09023 | Catskill | Catskill | Greene | 12414 | G | 2004 | North Catskill | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE7600A-US | 2016-12-07 | 2016-12-07 | 0 | 2016-12-07 | [14 empty] | 2017-02-07 | 2017-02-07 |  | Y
Central Hudson |  | Taconic Renewable energy Solutions | CH-09707 | Fishkill | Cold Spg | Putnam | 10516 | G | 8087 | Tioronda | N | CH-09707 | 9.75 | [13 empty] | NM | N | 39 NEPHASE M250 | 2016-11-07 | 2016-11-08 | 1 | 2016-11-08 | [14 empty] | 2017-06-06 | 2017-06-08 |  | Y
Central Hudson |  | New York State Solar Farm | CH-00394 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7061 | Milan | N |  | 7.04 | [13 empty] | NM | N | 22 Sunpower spr-x22-360-c-ac | 2016-11-08 | 2016-11-08 | 0 | 2016-11-08 | [14 empty] | 2016-12-09 | 2016-12-09 |  | Y
Central Hudson |  | New York State Solar Farm | CH-00404 | Newburgh | New Paltz | Ulster | 12561 | G | 5022 | Ohioville | N |  | 6.4 | [13 empty] | NM | N | 20 SUNPOWER SPR-E20 327-C-AC | 2016-11-08 | 2016-11-09 | 1 | 2016-11-09 | [14 empty] | 2016-12-07 | 2016-12-07 |  | Y
Central Hudson |  | New York State Solar Farm | CH-00407 | Newburgh | Wallkill | Ulster | 12589 | G | 5012 | Modena | N |  | 16.96 | [13 empty] | NM | N | 53 SUNPOWER SPR-E20 327-C-AC | 2016-11-08 | 2016-11-22 | 10 | 2016-11-22 | [8 empty] | 350 | 350 |  |  |  |  | 2016-12-15 | 2016-12-27 |  | Y
Central Hudson |  | SolarCity | CH-05427 | Newburgh | Newburgh | Orange | 12550 | G | 4011 | West Balmville | N |  | 7.6 | [13 empty] | NM | N | FRONIUS PRIMO 7.6 | 2016-11-08 | 2016-11-08 | 0 | 2016-11-08 | [14 empty] | 2016-11-16 | 2016-11-28 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-05837 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6073 | East Park | N |  | 7.6 | [13 empty] | NM | N | DELTA SOLIVIA 7.6 | 2016-11-08 | 2016-11-08 | 0 | 2016-11-08 | [14 empty] | 2017-02-16 | 2017-02-16 |  | Y
Central Hudson |  | SolarCity | CH-05842 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 6073 | East Park | N |  | 11.4 | [13 empty] | NM | N | DELTA SOLIVIA 7.6 DELTA SOLIVIA 3.8 | 2016-11-08 | 2016-11-08 | 0 | 2016-11-08 | [14 empty] | 2017-06-01 | 2017-06-06 |  | Y
Central Hudson |  | SolarCity | CH-07280 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6061 | Inwood Ave | N |  | 3.8 | [13 empty] | NM | N | DELTA SOLIVIA 3.8 | 2016-11-08 | 2016-11-08 | 0 | 2016-11-08 | [14 empty] | 2016-12-16 | 2016-12-16 |  | Y
Central Hudson |  | SolarCity | CH-07696 | Kingston | Port Ewen | Ulster | 12466 | G | 1012 | Boulevard | N |  | 3.8 | [13 empty] | NM | N | DELTA SOLIVIA 3.8 | 2016-11-08 | 2016-11-08 | 0 | 2016-11-08 | [14 empty] | 2017-03-29 | 2017-03-30 |  | Y
Central Hudson |  | Trinity Solar | CH-08412 | Poughkeepsie |  |  | 12601 | G | 6062 | Inwood Ave | TBD |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE7600A-US | 2016-11-08 | 2016-11-08 | 0 | 2016-11-08 | [17 empty] | W
Central Hudson |  | Trinity Solar | CH-08431 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8045 | Myers Corners | N |  | 3.8 | [13 empty] | NM | N | SOLAREDGE SE3800A-US | 2016-11-08 | 2016-11-09 | 1 | 2016-11-09 | [14 empty] | 2017-02-03 | 2017-02-10 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08730 | Catskill |  |  | 12431 | G | 2061 | Freehold | TBD |  | 6.23 | [13 empty] | NM | N | 29 ENPHASE M215 | 2016-11-11 | 2016-11-11 | 0 | 2016-11-11 | [17 empty] | W
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08769 | Fishkill | Putnam Valley | Putnam | 10524 | G | 8066 | Merritt Park | N |  | 6.23 | [13 empty] | NM | N | 29 ENPHASE M215 | 2016-11-08 | 2016-11-08 | 0 | 2016-11-08 | [14 empty] | 2017-02-02 | 2017-02-02 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08823 | Catskill | Athens | Greene | 12015 | G | 2002 | North Catskill | N | CH-08651 | 3.225 | [13 empty] | NM | N | 15 ENPHASE M215 | 2016-11-08 | 2016-11-11 | 3 | 2016-11-11 | [8 empty] | 350 | 350 |  | 2016-12-13 | 2016-12-13 | 2016-12-21 | 2017-02-07 | 2017-02-07 |  | Y
Central Hudson |  | American Solar Partners | CH-00009 | Kingston | Kerhonkson | Ulster | 12446 | G | 3082 | Kerhonkson | N |  | 10 | [13 empty] | NM | N | SOLAREDGE SE10000 | 2016-11-09 | 2016-11-10 | 1 | 2016-11-10 | [8 empty] | 350 | 350 |  | 2016-11-28 | 2016-11-28 | 2016-12-30 | 2017-02-21 | 2017-02-24 |  | Y
Central Hudson |  | New York State Solar Farm | CH-00428 | Poughkeepsie | Lagrangevl | Dutchess | 12540 | G | 6057 | Todd Hill | N |  | 24 | [13 empty] | NM | N | 75 SUNPOWER SPR-X21 345-C-AC | 2016-11-09 | 2016-11-23 | 10 | 2016-11-23 | [14 empty] | 2017-01-03 | 2017-01-03 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00827 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7062 | Milan | N |  | 12.25 | [13 empty] | NM | N | 49 ENPHASE M250 | 2016-11-09 | 2016-11-10 | 1 | 2016-11-10 | [14 empty] | 2017-01-03 | 2017-01-03 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00841 | Kingston | Stone Ridge | Ulster | 12484 | G | 3024 | High Falls | N |  | 6.88 | [13 empty] | NM | N | 32 ENPHASE M215 | 2016-11-11 | 2016-11-11 | 0 | 2016-11-11 | [14 empty] | 2017-01-06 | 2017-01-12 |  | Y
Central Hudson |  | Trinity Solar | CH-08379 | Newburgh | Cornwall | Orange | 12518 | G | 4041 | Union Ave | N |  | 3 | [13 empty] | NM | N | SOLAREDGE SE3000A-US | 2016-11-09 | 2016-11-09 | 0 | 2016-11-09 | [14 empty] | 2017-01-24 | 2017-02-03 |  | Y
Central Hudson |  | Trinity Solar | CH-08408 | Kingston |  |  | 12401 | G | 2013 | Lincoln Park | TBD |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE7600A-US | 2016-11-10 | 2016-11-11 | 1 | 2016-11-11 | [17 empty] | W
Central Hudson |  | Infinity Solar Systems | CH-00124 | Fishkill | Holmes | Dutchess | 12531 | G | 8071 | Shenandoah | N |  | 14.72 | [13 empty] | NM | N | 46 SUNPOWER SPR-X21-335-BLK-C-AC | 2016-11-10 | 2016-11-11 | 1 | 2016-11-11 | [14 empty] | 2017-01-31 | 2017-01-31 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-00180 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8094 | Fishkill Plains | N |  | 8 | [13 empty] | NM | N | SMA America SB8000TL-US | 2016-11-10 | 2016-11-11 | 1 | 2016-11-11 | [14 empty] | 2016-11-14 | 2016-11-14 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Infinity Solar Systems | CH-00215 | Newburgh | Newburgh | Orange | 12550 | G | 4013 | West Balmville | N |  | 12.8 | [13 empty] | NM | N | 40 SUNPOWER SPR-E20-327-C-AC | 2017-01-18 | 2017-01-23 | 3 | 2017-01-23 | [14 empty] | 2017-01-23 | 2017-01-23 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-05939 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6093 | Manchester | N |  | 7.6 | [13 empty] | NM | N | DELTA SOLIVIA 7.6 | 2016-11-10 | 2016-11-11 | 1 | 2016-11-11 | [14 empty] | 2016-12-12 | 2016-12-12 |  | Y
Central Hudson |  | SolarCity | CH-07103 | Newburgh |  |  | 12525 | G | 5011 | Modena | TBD |  | 15.2 | [13 empty] | NM | N | 2 DELTA SOLIVIA 7.6 | 2016-11-10 | 2016-11-10 | 0 | 2016-11-10 | [17 empty] | W
Central Hudson |  | SolarCity | CH-07266 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6093 | Manchester | N |  | 11.4 | [13 empty] | NM | N | DELTA SOLIVIA 7.6 DELTA SOLIVIA 3.8 | 2016-11-10 | 2016-11-11 | 1 | 2016-11-11 | [14 empty] | 2017-02-02 | 2017-02-02 |  | Y
Central Hudson |  | Trinity Solar | CH-08371 | Newburgh | Rock Tvrn | Orange | 12575 | G | 4097 | Bethlehem Rd | N |  | 10 | [13 empty] | NM | N | SOLAREDGE SE 10000A-US | 2016-11-11 | 2016-11-11 | 0 | 2016-11-11 | [14 empty] | 2016-12-27 | 2016-12-27 |  | Y
Central Hudson |  | Trinity Solar | CH-08581 | Newburgh | Campbell Hall | Orange | 10916 | G | 5052 | Maybrook | N |  | 10 | [13 empty] | NM | N | SOLAREDE SE10000A-US | 2016-11-11 | 2016-11-11 | 0 | 2016-11-11 | [14 empty] | 2017-02-06 | 2017-03-06 |  | Y
Central Hudson |  | Lighthouse Solar | CH-00280 | Fishkill | Wappingrs Fls |  | 12590 | G | 8043 | Myers Corners | N |  | 30 | [13 empty] | NM | N | 3 SOLAREDGE 10000A-US | 2016-11-17 | 2016-11-18 | 1 | 2016-11-18 | [8 empty] | 1930 | [8 empty] | W
Central Hudson |  | Direct Energy Solar | CH-01057 | Poughkeepsie | Stanfordvl | Dutchess | 12581 | G | 7072 | Stanfordville | N |  | 10.75 | [13 empty] | NM | N | 50 ENPHASE M215 | 2016-11-11 | 2016-11-11 | 0 | 2016-11-11 | [14 empty] | 2016-12-16 | 2016-12-27 |  | Y
Central Hudson |  | Lam Development | CH-02581 | Poughkeepsie |  |  | 12538 | G | 6074 | East Park | TBD |  | 2000 | [13 empty] | CDG | N | SMA TRIPOWER 30000TL-US (66) SMA TRIPOWER 20000TL-US (1) | 2016-11-15 | 2016-11-18 | 3 | 2016-11-18 | 2016-11-18 | 2016-12-06 | 10 | 2016-12-15 | 2016-12-16 | 2017-03-16 | 60 | 35000 | [9 empty] | W
Central Hudson |  | SolarCity | CH-05493 | Catskill | Hunter | Greene | 12442 | E | 2081 | Hunter | N |  | 3.8 | [13 empty] | NM | N | DELTA SOLIVIA 3.8 | 2016-11-11 | 2016-11-11 | 0 | 2016-11-11 | [14 empty] | 2017-03-22 | 2017-03-24 |  | Y
Central Hudson |  | SolarCity | CH-05766 | Kingston | Kingston | Ulster | 12401 | G | 1021 | East Kingston | N |  | 11.4 | [13 empty] | NM | N | SOLAREDGE SE 11400A | 2016-11-11 | 2016-11-11 | 0 | 2016-11-11 | [14 empty] | 2017-02-27 | 2017-02-27 |  | Y
Central Hudson |  | SolarCity | CH-05992 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8091 | Fishkill Plains | N |  | 3.6 | [13 empty] | NM | N | ABB PVI 3.6 OUTD-S-US | 2016-11-11 | 2016-11-11 | 0 | 2016-11-11 | [14 empty] | 2016-11-23 | 2016-11-30 |  | Y
Central Hudson |  | SolarCity | CH-07275 | Poughkeepsie |  |  | 12601 | G | 6065 | Inwood Ave | TBD |  | 8 | [13 empty] | NM | N | ABB PVI 5000 OUTD-US ABB PVI 3.0 OUTD-S-US | 2016-11-11 | 2016-11-11 | 0 | 2016-11-11 | [17 empty] | W
Central Hudson |  | SolarCity | CH-07548 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 7024 | Tinkertown | N |  | 3 | [13 empty] | NM | N | ABB PVI 3.0 | 2016-11-15 | 2016-11-15 | 0 | 2016-11-15 | [14 empty] | 2016-12-02 | 2016-12-07 |  | Y
Central Hudson |  | New York State Solar Farm | CH-00375 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6052 | Todd Hill | N |  | 4.16 | [13 empty] | NM | N | 13 SUNPOWER SPR-X22 | 2016-11-15 | 2016-11-15 | 0 | 2016-11-15 | [14 empty] | 2016-12-14 | 2016-12-29 |  | Y
Central Hudson |  | Hudson Solar | CH-02105 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 6051 | Todd Hill | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE7600A-US | 2016-11-14 | 2016-11-14 | 0 | 2016-11-14 | [14 empty] | 2017-02-22 | 2017-02-28 |  | Y
Central Hudson |  | SolarCity | CH-05473 | Kingston | Saugerties | Ulster | 12477 | G | 3001 | Saugerties | N |  | 22.8 | [13 empty] | NM | N | 3 DELTA SOLIVIA 7.6 | 2016-11-14 | 2016-11-30 | 10 | 2016-11-30 | [8 empty] | 350 | 350 |  | 2016-12-22 | 2016-12-22 | 2017-01-04 | 2017-01-04 | 2017-01-06 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-05935 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 7024 | Tinkertown | N |  | 11.4 | [13 empty] | NM | N | SOLAREDGE SE11400A | 2016-11-14 | 2016-11-15 | 1 | 2016-11-15 | [14 empty] | 2017-03-13 | 2017-03-20 |  | Y
Central Hudson |  | SolarCity | CH-06670 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6065 | Inwood Ave | N |  | 11.4 | [13 empty] | NM | N | DELTA SOLIVIA 3.8 DELTA SOLIVIA 7.6 | 2016-11-14 | 2016-11-15 | 1 | 2016-11-15 | [14 empty] | 2017-01-25 | 2017-01-30 |  | Y
Central Hudson |  | SolarCity | CH-06762 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7061 | Milan | N |  | 10 | [13 empty] | NM | N | SOLAREDGE SE 10000A | 2016-11-14 | 2016-11-15 | 1 | 2016-11-15 | [14 empty] | 2017-03-07 | 2017-03-10 |  | Y
Central Hudson |  | SolarCity | CH-07140 | Newburgh | Washingtonvl | Orange | 10992 | G | 4097 | Bethlehem Rd | N |  | 12 | [13 empty] | NM | N | 2 ABB PVI-6000 | 2016-11-22 | 2016-11-22 | 0 | 2016-11-22 | [14 empty] | 2016-12-07 | 2016-12-07 |  | Y
Central Hudson |  | SolarCity | CH-07603 | Newburgh | Newburgh | Orange | 12550 | G | 4015 | West Balmville | N |  | 5 | [13 empty] | NM | N | ABB PVI-5000OUTD-US | 2016-11-14 | 2016-11-14 | 0 | 2016-11-14 | [14 empty] | 2016-11-17 | 2016-11-23 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08688 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8043 | Myers Corners | N |  | 7.525 | [13 empty] | NM | N | 35 ENPHASE M215 | 2016-11-14 | 2016-11-14 | 0 | 2016-11-14 | [14 empty] | 2017-04-05 | 2017-04-06 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08780 | Catskill | Greenvl | Greene | 12083 | G | 2061 | Freehold | N |  | 9.245 | [13 empty] | NM | N | 48 ENPHASE M215 | 2016-11-14 | 2016-11-17 | 3 | 2016-11-17 | [8 empty] | 350 | 350 |  | 2016-12-01 | 2016-12-01 | 2016-12-07 | 2017-03-07 | 2017-03-10 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08798 | Fishkill |  |  | 12533 | G | 8093 | Fishkill Plains | TBD |  | 13.76 | [13 empty] | NM | N | 64 ENPHASE M215 | 2016-11-14 | 2016-11-14 | 0 | 2016-11-14 | [17 empty] | W
Central Hudson |  | US Energy Concierge, Inc. | CH-09740 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8096 | Fishkill Plains | N |  | 3.8 | [13 empty] | NM | N | SOLAREDGE SE3800A-US | 2016-11-16 | 2016-11-16 | 0 | 2016-11-16 | [14 empty] | 2017-06-12 | 2017-06-15 |  | Y
Central Hudson |  | US Energy Concierge, Inc. | CH-09749 | Fishkill | Putnam Valley | Putnam | 10524 | G | 8066 | Merritt Park | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A-US | 2016-11-14 | 2016-11-14 | 0 | 2016-11-14 | [14 empty] | 2017-01-09 | 2017-01-16 |  | Y
Central Hudson |  | Cypress Creek Renewables, LLC | CH-03326 | Kingston | Ulster |  | 12401 | G | 1011 | Boulevard | TBD |  | 1980 | [13 empty] | CDG | Y | 44 HUAWEI SUN2000-45KTL-US-150 | 2016-12-02 | 2016-12-02 | 0 | 2016-12-02 | 2016-12-02 | 2016-12-22 | 14 | 2017-03-08 | 2017-04-17 | 2017-07-12 | 60 | 20000 | 297785.5 |  | 2017-10-18 | 2018-04-13 | 2018-04-13 |  |  |  |  | W |  | There are 2 accounts at this location with an aggregate CESIR Cost to Customer of $40,000 & Estimated Project Upgrade Costs of $595,571. 6/6/18 - Received request to combine with Project CH-03325; current deadlines suspended.
Central Hudson |  | Infinity Solar Systems | CH-00142 | Newburgh | Rock Tvrn | Orange | 12575 | G | 4097 | Bethlehem Rd | N |  | 12.8 | [13 empty] | NM | N | 40 SUNPOWER SPR-X21-335-BLK | 2016-11-15 | 2016-11-16 | 1 | 2016-11-16 | [14 empty] | 2017-01-25 | 2017-01-31 |  | Y
Central Hudson |  | SolarCity | CH-05171 | Newburgh | New Windsor | Orange | 12553 | G | 4095 | Bethlehem Rd | N |  | 13.8 | [13 empty] | NM | N | SOLAREDGE SE3800 SOLAREDGE SE10000 | 2016-11-15 | 2016-11-16 | 1 | 2016-11-16 | [14 empty] | 2017-01-10 | 2017-01-10 |  | Y
Central Hudson |  | SolarCity | CH-06422 | Newburgh | Maybrook | Orange | 12543 | G | 4026 | Coldenham | N |  | 3.8 | [13 empty] | NM | N | SOLAREDGE SE 3800A | 2016-11-15 | 2016-11-15 | 0 | 2016-11-15 | [14 empty] | 2016-12-21 | 2016-12-21 |  | Y
Central Hudson |  | Trinity Solar | CH-08464 | Catskill | Westerlo | Albany | 12193 | G | 1091 | Westerlo | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE 7600A-US | 2016-11-17 | 2016-11-17 | 0 | 2016-11-17 | [14 empty] | 2017-01-25 | 2017-01-25 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08732 | Catskill | E Durham | Greene | 12423 | G | 2071 | Freehold | N | CH-08732 | 8.6 | [13 empty] | NM | N | 40 ENPHASE M215 | 2016-11-16 | 2016-11-16 | 0 | 2016-11-16 | [14 empty] | 2017-03-14 | 2017-03-21 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08813 | Fishkill | Garrison | Putnam | 10524 | G | 8066 | Merritt Park | N |  | 4.3 | [13 empty] | NM | N | 20 ENPHASE 215 | 2016-11-15 | 2016-11-15 | 0 | 2016-11-15 | [14 empty] | 2017-02-17 | 2017-02-17 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-00034 | Kingston | Accord | Ulster | 12404 | G | 3081 | Kerhonkson | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE7600A-US | 2016-11-16 | 2016-11-17 | 1 | 2016-11-17 | [14 empty] | 2016-12-07 | 2016-12-07 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-00042 | Poughkeepsie | Staatsburg | Dutchess | 12580 | G | 7041 | Staatsburg | N |  | 12 | [13 empty] | NM | N | 2 SOLAREDGE SE 6000A-US | 2016-11-16 | 2016-11-16 | 0 | 2016-11-16 | [14 empty] | 2017-01-18 | 2017-02-01 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-00062 | Newburgh | Newburgh | Orange | 12550 | G | 5001 | Marlboro | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE7600A-US | 2016-11-16 | 2016-11-16 | 0 | 2016-11-16 | [14 empty] | 2016-12-16 | 2016-12-16 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-00125 | Poughkeepsie |  |  | 12603 | G | 6056 | Todd Hill | TBD |  | 11.2 | [13 empty] | NM | N | 35 SUNPOWER SPR-X21-335-BLK | 2016-11-16 | 2016-11-16 | 0 | 2016-11-16 | [17 empty] | W
Central Hudson |  | SolarCity | CH-06764 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7054 | Rhinebeck | N |  | 22.8 | [13 empty] | NM | N | 3 DELTA SOLIVIA 7.6 | 2016-11-21 | 2016-12-02 | 7 | 2016-12-02 | [8 empty] | 350 | 350 |  | 2017-02-17 | 2017-02-17 | 2017-02-28 | 2017-04-21 | 2017-04-26 |  | Y
Central Hudson |  | Trinity Solar | CH-08521 | Newburgh | Goshen | Orange | 10924 | G | 5051 | Maybrook | N | CH-08521 | 10 | [13 empty] | NM | N | SOLAREDGE SE10000A-US | 2016-11-16 | 2016-11-16 | 0 | 2016-11-16 | [14 empty] | 2017-02-17 | 2017-02-17 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-00064 | Newburgh | Modena | Ulster | 12548 | G | 5012 | Modena | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE7600A-US | 2016-11-18 | 2016-11-18 | 0 | 2016-11-18 | [14 empty] | 2016-11-22 | 2016-11-22 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | New York State Solar Farm | CH-00448 | Kingston | Saugerties | Ulster | 12477 | G | 3004 | Saugerties | N |  | 6.08 | [13 empty] | NM | N | 19 SUNPOWER SPR-E20-327-C-AC | 2016-11-28 | 2016-11-29 | 1 | 2016-11-29 | [14 empty] | 2016-12-13 | 2016-12-13 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | NRG Home Solar | CH-00492 | Newburgh | New Windsor | Orange | 12553 | G | 4044 | Union Ave | N |  | 3.44 | [13 empty] | NM | N | 16 ENPHASE M215 | 2016-11-21 | 2016-11-21 | 0 | 2016-11-21 | [14 empty] | 2017-01-16 | 2017-01-16 |  | Y
Central Hudson |  | Hudson Solar | CH-02119 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7062 | Milan | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE7600A-US | 2016-11-17 | 2016-11-18 | 1 | 2016-11-18 | [14 empty] | 2017-02-10 | 2017-02-22 |  | Y
Central Hudson |  | PosiGen Solar | CH-02925 | Catskill |  |  | 12143 | G | 1082 | New Baltimore | TBD |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A-US | 2016-11-17 | 2016-11-17 | 0 | 2016-11-17 | [14 empty] | 2016-12-09 | 2016-12-09 |  | W
Central Hudson |  | SolarCity | CH-04978 | Catskill | Round Top | Greene | 12473 | G | 2042 | South Cairo | N |  | 13.2 | [13 empty] | NM | N | 2 Delta Solivia 6.6 | 2016-11-17 | 2016-11-29 | 6 | 2016-11-29 | [8 empty] | 350 | 350 |  | 2016-12-16 | 2016-12-16 | 2016-12-22 | 2017-02-15 | 2017-02-21 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-05765 | Kingston | Kingston | Ulster | 12401 | G | 1021 | East Kingston | N |  | 8.8 | [13 empty] | NM | N | SOLAREDGE SE3800A-US SOLAREDGE SE5000A-US | 2016-11-17 | 2016-11-17 | 0 | 2016-11-17 | [14 empty] | 2017-01-25 | 2017-01-25 |  | Y
Central Hudson |  | SolarCity | CH-07584 | Fishkill | Beacon | Dutchess | 12508 | G | 8015 | Forgebrook | N |  | 15.2 | [13 empty] | NM | N | 2 DELTA SOLIVIA 7.6 | 2016-11-17 | 2016-11-17 | 0 | 2016-11-17 | [14 empty] | 2017-02-02 | 2017-02-10 |  | Y
Central Hudson |  | Sol Providers | CH-08910 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8093 | Fishkill Plains | N |  | 14.4 | [13 empty] | NM | N | 45 SUNPOWER SPR-E20-327C-AC | 2016-11-17 | 2016-11-17 | 0 | 2016-11-17 | [14 empty] | 2016-12-27 | 2016-12-27 |  | Y
Central Hudson |  | NRG Home Solar | CH-00526 | Kingston | Kingston |  | 12401 | G | 2013 | Lincoln Park | N |  | 3.23 | [13 empty] | NM | N | 15 ENPHASE M215 | 2016-11-18 | 2016-11-18 | 0 | 2016-11-18 | [14 empty] | 2017-01-23 | 2017-01-23 |  | W
Central Hudson |  | Hudson Solar | CH-01538 | Newburgh | Highland | Ulster | 12528 | G | 5082 | Highland | N | CH-01538 | 15 | [13 empty] | NM | N | SOLAREDGE SE10000A-Us SOLAREDGE SE5000A-US | 2016-11-18 | 2016-12-02 | 8 | 2016-12-02 | [14 empty] | 2017-01-26 | 2017-02-01 |  | Y
Central Hudson |  | Hudson Solar | CH-02312 | Fishkill | Cold Spg | Putnam | 10516 | G | 8087 | Tioronda | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE50000A-US | 2016-11-18 | 2016-11-18 | 0 | 2016-11-18 | [14 empty] | 2017-01-27 | 2017-01-30 |  | Y
Central Hudson |  | SolarCity | CH-05754 | Kingston | Lk Katrine | Ulster | 12449 | G | 2011 | Lincoln Park | N |  | 15.2 | [13 empty] | NM | N | 2 DELTA SOLIVIA 7.6 | 2016-12-01 | 2016-12-02 | 1 | 2016-12-02 | [14 empty] | 2017-02-17 | 2017-02-17 |  | Y
Central Hudson |  | SolarCity | CH-07429 | Newburgh | Newburgh | Orange | 12550 | G | 4014 | West Balmville | N |  | 5.2 | [13 empty] | NM | N | DELTA SOLIVIA 5.2 | 2016-11-29 | 2016-11-29 | 0 | 2016-11-29 | [14 empty] | 2017-02-17 | 2017-03-01 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07637 | Kingston | Kingston | Ulster | 12401 | G | 1013 | Boulevard | N |  | 3 | [13 empty] | NM | N | ABB PVI 3.0 | 2016-11-18 | 2016-11-18 | 0 | 2016-11-18 | [14 empty] | 2016-11-23 | 2016-11-28 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-00070 | Kingston | Kingston | Ulster | 12401 | G | 1011 | Boulevard | N |  | 5 | [13 empty] | NM | N | SOLAREDGE 5000A | 2016-11-21 | 2016-11-23 | 2 | 2016-11-23 | [14 empty] | 2016-12-29 | 2016-12-29 |  | Y
Central Hudson |  | Hudson Solar | CH-02139 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7054 | Rhinebeck | N |  | 11.4 | [13 empty] | NM | N | SOLAREDGE SE11400 | 2016-11-21 | 2016-12-07 | 10 | 2016-12-07 | [14 empty] | 2017-03-03 | 2017-03-06 |  | Y
Central Hudson |  | SolarCity | CH-05696 | Kingston | Kingston | Ulster | 12401 | G | 1011 | Boulevard | N |  | 7.6 | [13 empty] | NM | N | DELTA SOLIVIA 7.6 | 2016-11-30 | 2016-11-30 | 0 | 2016-11-30 | [14 empty] | 2017-01-25 | 2017-01-30 |  | Y
Central Hudson |  | SolarCity | CH-06588 | Kingston | Lk Katrine | Ulster | 12449 | G | 2011 | Lincoln Park | N |  | 15.2 | [13 empty] | NM | N | 2 DELTA SOLIVIA 7.6 | 2016-11-21 | 2016-11-23 | 2 | 2016-11-23 | [14 empty] | 2017-01-25 | 2017-01-25 |  | Y
Central Hudson |  | SolarCity | CH-07025 | Newburgh | New Windsor | Orange | 12553 | G | 4046 | Union Ave | N |  | 5 | [13 empty] | NM | N | ABB PVI-5000 | 2016-11-21 | 2016-11-21 | 0 | 2016-11-21 | [14 empty] | 2016-11-28 | 2016-12-06 |  | Y
Central Hudson |  | SolarCity | CH-07585 | Fishkill | Beacon | Dutchess | 12508 | G | 8015 | Forgebrook | N |  | 3.8 | [13 empty] | NM | N | DELTA SOLIVIA 3.8 | 2016-11-30 | 2016-11-30 | 0 | 2016-11-30 | [14 empty] | 2017-01-25 | 2017-01-25 |  | Y
Central Hudson |  | Trinity Solar | CH-08574 | Fishkill | Beacon | Dutchess | 12508 | G | 8087 | Tioronda | N |  | 3.8 | [13 empty] | NM | N | SOLAREDGE SE3800A-US | 2016-11-21 | 2016-11-28 | 3 | 2016-11-28 | [14 empty] | 2017-01-25 | 2017-01-31 |  | Y
Central Hudson |  | Apex Solar Power | CH-00010 | Fishkill | Beacon | Dutchess | 12508 | G | 8015 | Forgebrook | N |  | 45 | [13 empty] | NM | N | 5 SOLAREDGE SE9000A-US | 2016-11-28 | 2016-11-29 | 1 | 2016-11-29 | [14 empty] | 2017-06-21 | 2017-07-05 |  | Y
Central Hudson |  | Kasselman Solar | CH-00225 | Catskill | Jewett | Greene | 12444 | E | 2081 | Hunter | N |  | 8.75 | [13 empty] | NM | N | 35 ENPHASE M250 | 2016-11-22 | 2016-11-28 | 2 | 2016-11-28 | [14 empty] | 2017-01-17 | 2017-01-17 |  | Y
Central Hudson |  | Kasselman Solar | CH-00232 | Catskill | Hunter | Greene | 12442 | E | 2081 | Hunter | N | CH-00232 | 6 | [13 empty] | NM | N | 24 ENPHASE M250 | 2016-12-06 | 2016-12-20 | 10 | 2016-12-20 | [14 empty] | 2016-12-06 | 2017-01-17 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL. 12/9/16 - Unable to install net meter due to access issue; appointment required. 1/17/17 - Net Meter Installed.
Central Hudson |  | Lotus Energy Inc. | CH-00343 | Catskill | Catskill | Greene | 12414 | G | 2004 | North Catskill | N |  | 3.2 | [13 empty] | NM | N | 10 SUNPOWER E20-327-C-AC | 2016-11-23 | 2016-11-29 | 2 | 2016-11-29 | [14 empty] | 2016-12-16 | 2016-12-19 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00919 | Kingston | Saugerties | Ulster | 12477 | G | 3001 | Saugerties | N |  | 10 | [13 empty] | NM | N | 40 ENPHASE M250 | 2016-11-22 | 2016-11-28 | 2 | 2016-11-28 | [14 empty] | 2016-12-27 | 2016-12-27 |  | Y
Central Hudson |  | Grid Alternatives Tri-State | CH-01180 | Kingston | Kingston | Ulster | 12401 | G | 2092 | Hurley Ave | N |  | 3 | [13 empty] | NM | N | SMA AMERICA SB300 | 2016-11-22 | 2016-11-28 | 2 | 2016-11-28 | [14 empty] | 2017-04-25 | 2017-04-27 |  | Y
Central Hudson |  | Grid Alternatives Tri-State | CH-01181 | Kingston | Kingston | Ulster | 12401 | G | 1024 | East Kingston | N |  | 3 | [13 empty] | NM | N | SMA AMERICA SB3000 | 2016-11-22 | 2016-11-28 | 2 | 2016-11-28 | [14 empty] | 2017-05-05 | 2017-05-05 |  | Y
Central Hudson |  | Hudson Solar | CH-01323 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7061 | Milan | N |  | 8.8 | [13 empty] | NM | N | SMA AMERICA SB3800 SMA AMERICA SB5000 | 2016-11-22 | 2016-11-30 | 4 | 2016-11-30 | [14 empty] | 2017-02-10 | 2017-02-23 |  | Y
Central Hudson |  | SolarCity | CH-06473 | Catskill | W Coxsackie | Greene | 12192 | G | 1076 | Coxsackie | N |  | 10.4 | [13 empty] | NM | N | 2 DELTA SOLIVIA 5.2 | 2016-12-01 | 2016-12-02 | 1 | 2016-12-02 | [14 empty] | 2016-12-09 | 2016-12-09 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Trinity Solar | CH-08471 | Kingston | Port Ewen | Ulster | 12466 | G | 1012 | Boulevard | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A-US | 2016-11-22 | 2016-11-28 | 2 | 2016-11-28 | [14 empty] | 2017-04-03 | 2017-04-04 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08626 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8045 | Myers Corners | N |  | 5.8 | [13 empty] | NM | N | 27 ENPHASE M215 | 2016-11-28 | 2016-11-29 | 1 | 2016-11-29 | [14 empty] | 2017-03-17 | 2017-03-23 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-00025 | Newburgh | Wallkill | Ulster | 12589 | G | 5043 | East Walden | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE7600A-US | 2016-11-23 | 2016-11-29 | 2 | 2016-11-29 | [14 empty] | 2016-12-22 | 2017-01-05 |  | Y
Central Hudson |  | SolarCity | CH-05757 | Kingston | Kingston | Ulster | 12401 | G | 1021 | East Kingston | Y |  | 7.6 | 7.6 | [12 empty] | NM | N | SOLAREDGE 76001SolarEdge TechnologiesSE7600-USS | 2017-04-18 | 2017-04-24 | 4 | 2017-04-24 | [14 empty] | 2017-09-29 | 2017-09-29 |  | Y
Central Hudson |  | Solar Generation | CH-08086 | Kingston | Ulster Pk | Ulster | 12487 | G | 1014 | Boulevard | N |  | 10.6 | [13 empty] | NM | N | SOLAREDGE SE7600A SOLAREDGE SE3000A | 2016-11-23 | 2016-11-29 | 2 | 2016-11-29 | [8 empty] | 350 | 350 |  | 2017-02-28 | 2017-02-28 | 2017-04-11 | 2017-03-13 | 2017-03-15 |  | Y
Central Hudson |  | Solar Generation | CH-08261 | Catskill | Leeds | Greene | 12451 | G | 2005 | North Catskill | N |  | 7.7 | [13 empty] | NM | N | SMA SB7.7 | 2016-11-23 | 2016-11-28 | 1 | 2016-11-28 | [14 empty] | 2017-01-23 | 2017-01-23 |  | Y
Central Hudson |  | NRG Home Solar | CH-00515 | Newburgh | Newburgh | Orange | 12550 | G | 4054 | Union Ave | N |  | 6.23 | [13 empty] | NM | N | 29 ENPHASE M215 | 2016-11-30 | 2016-11-30 | 0 | 2016-11-30 | [14 empty] | 2017-04-13 | 2017-06-01 |  | Y
Central Hudson |  | Hudson Solar | CH-01843 | Poughkeepsie | Milan |  | 12571 | G | 7061 | Milan | TBD |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000 | 2016-11-28 | 2016-11-29 | 1 | 2016-11-29 | [17 empty] | W
Central Hudson |  | SolarCity | CH-06207 | Newburgh | Walden | Orange | 12586 | G | 5041 | East Walden | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE 7600 | 2016-11-29 | 2016-11-29 | 0 | 2016-11-29 | [14 empty] | 2017-02-22 | 2017-02-22 |  | Y
Central Hudson |  | Trinity Solar | CH-08421 | Poughkeepsie |  |  | 12571 | G | 7051 | Rhinebeck | TBD |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A-US | 2016-11-30 | 2016-11-30 | 0 | 2016-11-30 | [17 empty] | W
Central Hudson |  | Trinity Solar | CH-08579 | Kingston |  |  | 12446 | G | 3082 | Kerhonkson | TBD |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A-US | 2016-11-28 | 2016-11-30 | 2 | 2016-11-30 | [17 empty] | W
Central Hudson |  | Empire Solar Solutions | CH-00074 | Poughkeepsie |  |  | 12601 | G | 6002 | Reynolds Hill | N |  | 2.5 | [13 empty] | NM | N | 10 ENPHASE M250 | 2016-11-30 | 2016-11-30 | 0 | 2016-11-30 | [17 empty] | W
Central Hudson |  | Infinity Solar Systems | CH-00156 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8051 | North Chelsea | N |  | 8.32 | [13 empty] | NM | N | 26 SUNPOWER SPR-X21-335-BLK | 2016-11-30 | 2016-11-30 | 0 | 2016-11-30 | [14 empty] | 2017-03-15 | 2017-03-17 |  | Y
Central Hudson |  | NRG Home Solar | CH-00488 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6046 | Spackenkill | N |  | 7.31 | [13 empty] | NM | N | 34 ENPHASE M215 | 2016-11-29 | 2016-11-30 | 1 | 2016-11-30 | [14 empty] | 2017-04-17 | 2017-04-17 |  | Y
Central Hudson |  | NRG Home Solar | CH-00503 | Kingston | Saugerties | Ulster | 12477 | G | 3001 | Saugerties | N |  | 6.02 | [13 empty] | NM | N | 28 ENPHASE M215 | 2016-11-29 | 2016-11-30 | 1 | 2016-11-30 | [14 empty] | 2017-02-21 | 2017-02-21 |  | Y
Central Hudson |  | SolarCity | CH-05466 | Newburgh | Wallkill | Ulster | 12589 | G | 5013 | Modena | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A-US | 2016-11-29 | 2016-11-30 | 1 | 2016-11-30 | [14 empty] | 2017-02-22 | 2017-03-24 |  | Y
Central Hudson |  | Sungevity Inc | CH-09517 | Kingston |  |  | 12484 | G | 3023 | High Falls | TBD |  | 3 | [13 empty] | NM | N | SOLAREDGE SE3000A-US | 2016-12-07 | 2016-12-07 | 0 | 2016-12-07 | [17 empty] | W
Central Hudson |  | Green Street Power Partners, LLC | CH-00118 | Newburgh | New Paltz | Ulster | 12561 | G | 5031 | Galeville | N |  | 5.76 | [13 empty] | NM | N | 18 SUNPOWER SPR E20 327-C-AC | 2016-11-30 | 2016-11-30 | 0 | 2016-11-30 | [14 empty] | 2017-01-18 | 2017-01-18 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Infinity Solar Systems | CH-00204 | Fishkill | Fishkill | Dutchess | 12524 | G | 8094 | Fishkill Plains | N |  | 7.68 | [13 empty] | NM | N | 24 SUNPOWER SPR-E20-327 | 2016-11-30 | 2016-12-02 | 2 | 2016-12-02 | [14 empty] | 2017-01-24 | 2017-01-24 |  | Y
Central Hudson |  | Lighthouse Solar | CH-00285 | Kingston | Kingston | Ulster | 12401 | G | 3023 | High Falls | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE 7600 | 2016-12-05 | 2016-12-05 | 0 | 2016-12-05 | [14 empty] | 2017-02-07 | 2017-02-07 |  | Y
Central Hudson |  | Lighthouse Solar | CH-00318 | Newburgh | Marlboro | Ulster | 12542 | G | 5001 | Marlboro | N |  | 6 | [13 empty] | NM | N | SOLAREDGE 6000 | 2016-11-30 | 2016-12-02 | 2 | 2016-12-02 | [14 empty] | 2017-01-23 | 2017-01-23 |  | Y
Central Hudson |  | SolarCity | CH-05594 | Catskill | W Coxsackie | Greene | 12192 | G | 1083 | New Baltimore | N |  | 5.2 | [13 empty] | NM | N | DELTA SOLIVIA 5.2 | 2016-11-30 | 2016-12-02 | 2 | 2016-12-02 | [14 empty] | 2017-02-03 | 2017-02-03 |  | Y
Central Hudson |  | SolarCity | CH-07252 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6045 | Spackenkill | N |  | 7.6 | [13 empty] | NM | N | DELTA SOLIVIA 7.6 | 2016-11-30 | 2016-12-02 | 2 | 2016-12-02 | [14 empty] | 2017-01-10 | 2017-01-10 |  | Y
Central Hudson |  | Solar Generation | CH-08291 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6052 | Todd Hill | N |  | 6 | [13 empty] | NM | N | 24 ENPHASE M250 | 2016-12-05 | 2016-12-05 | 0 | 2016-12-05 | [14 empty] | 2017-02-09 | 2017-02-13 |  | Y
Central Hudson |  | Kasselman Solar | CH-00233 | Catskill | Leeds | Greene | 12451 | G | 2005 | North Catskill | N |  | 5.75 | [13 empty] | NM | N | 23 ENPHASE M250 | 2016-12-01 | 2016-12-05 | 2 | 2016-12-05 | [14 empty] | 2017-01-06 | 2017-01-06 |  | Y
Central Hudson |  | SolarCity | CH-06238 | Newburgh | Newburgh | Orange | 12550 | G | 4014 | West Balmville | N |  | 3 | [13 empty] | NM | N | ABB PVI 3.0 | 2017-02-23 | 2017-02-23 | 0 | 2017-02-23 | [14 empty] | 2017-06-02 | 2017-06-08 |  | Y
Central Hudson |  | SolarCity | CH-06622 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6011 | Sand Dock | N |  | 6.6 | [13 empty] | NM | N | DELTA SOLIVIA 6.6TL | 2016-12-01 | 2016-12-02 | 1 | 2016-12-02 | [14 empty] | 2017-03-01 | 2017-03-01 |  | Y
Central Hudson |  | SolarCity | CH-06633 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6094 | Manchester | N |  | 3.8 | [13 empty] | NM | N | SOLAREDGE SE3800A | 2016-12-01 | 2016-12-02 | 1 | 2016-12-02 | [14 empty] | 2016-12-16 | 2016-12-22 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07008 | Newburgh | Newburgh | Orange | 12550 | G | 4051 | Union Ave | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000 | 2016-12-01 | 2016-12-02 | 1 | 2016-12-02 | [14 empty] | 2017-02-15 | 2017-03-03 |  | Y
Central Hudson |  | SolarCity | CH-07099 | Newburgh | Wallkill | Ulster | 12589 | G | 5043 | East Walden | N |  | 5 | [13 empty] | NM | N | ABB PVI-5000 OUTD-US | 2017-03-28 | 2017-03-29 | 1 | 2017-03-29 | [14 empty] | 2017-03-30 | 2017-03-30 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Trinity Solar | CH-08541 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8092 | Fishkill Plains | N |  | 3.8 | [13 empty] | NM | N | SOLAREDGE SE3800A-US | 2016-12-01 | 2016-12-06 | 3 | 2016-12-06 | [14 empty] | 2017-03-16 | 2017-03-21 |  | Y
Central Hudson |  | Solar Alchemy | CH-08990 | Kingston | Ellenvl | Ulster | 12428 | G | 3078 | Greenfield Rd | N |  | 12.25 | [13 empty] | NM | N | 49 ENPHASE ENERGY M250 | 2016-12-09 | 2016-12-09 | 0 | 2016-12-09 | [14 empty] | 2017-02-15 | 2017-02-15 |  | Y
Central Hudson |  | East Light Partners PBC | CH-03332 | Fishkill | Fishkill | Dutchess | 12524 | G | 8093 | Fishkill Plains | N |  | 1980 | [13 empty] | CDG | Y | 33 SUNGROW SG-60KU-M | 2016-12-12 | 2016-12-28 | 10 | 2016-12-28 | 2016-12-28 | 2017-01-19 | 15 | 2017-04-03 | 2017-04-04 | 2017-06-29 | 60 | 27846.21 | 139303 | 84433.31 | 2017-08-28 | 2018-02-23 | 2018-02-23 | 2019-12-13 | 2019-12-31 | 2019-12-31 | 2020-03-26 | Y | Y
Central Hudson |  | Empire Solar Solutions | CH-00029 | Newburgh | Washingtonvl | Orange | 10992 | G | 4097 | Bethlehem Rd | N | CH-00029 | 3 | [13 empty] | NM | N | 12 ENPHASE M250 | 2016-12-05 | 2016-12-05 | 0 | 2016-12-05 | [14 empty] | 2016-12-28 | 2016-12-28 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-00038 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6046 | Spackenkill | N |  | 2.75 | [13 empty] | NM | N | 11 ENPHASE M250 | 2016-12-02 | 2016-12-05 | 1 | 2016-12-05 | [14 empty] | 2016-12-29 | 2017-01-03 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-00084 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8091 | Fishkill Plains | N |  | 11.4 | [13 empty] | NM | N | SOLAREDGE 11400AUS | 2016-12-02 | 2016-12-02 | 0 | 2016-12-02 | [14 empty] | 2016-12-30 | 2016-12-30 |  | Y
Central Hudson |  | Solar Landscape, LLC | CH-03349 | Newburgh | New Windsor | Orange | 12553 | G | 4046 | Union Ave | N |  | 1980 | [13 empty] | CDG | Y | 33 Yaskawa Solectria Solar PVI60kW-240 | 2016-12-07 | 2016-12-21 | 10 | 2016-12-21 | 2016-12-21 | 2017-01-16 | 15 | 2017-03-03 | 2017-03-06 | 2017-05-31 | 60 | 9048.88 | 167392.5 | 106797.64 | 2017-06-27 | 2017-12-08 | 2017-12-08 | 2019-05-07 | 2019-08-29 | 2019-08-29 | 2019-11-22 | Y | Y | CESIR for 2 projects, CH-03349 and CH-03350 combined with an aggregate CESIR Cost to Customer of $40,000.
Central Hudson |  | Infinity Solar Systems | CH-00159 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 10.24 | [13 empty] | NM | N | 32 SUNPWOER SPR-X21-335-BLK | 2016-12-02 | 2016-12-05 | 1 | 2016-12-05 | [14 empty] | 2017-01-31 | 2017-02-01 |  | Y
Central Hudson |  | Kasselman Solar | CH-00246 | Catskill | Westerlo | Albany | 12193 | G | 1092 | Westerlo | N |  | 8 | [13 empty] | NM | N | 32 ENPHASE M250 | 2016-12-02 | 2016-12-05 | 1 | 2016-12-05 | [14 empty] | 2017-04-17 | 2017-05-01 |  | Y
Central Hudson |  | Direct Energy Solar | CH-01043 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7053 | Rhinebeck | N |  | 6 | [13 empty] | NM | N | 24 ENPHASE M250 | 2016-12-02 | 2016-12-15 | 9 | 2016-12-15 | [14 empty] | 2017-01-19 | 2017-01-19 |  | Y
Central Hudson |  | SolarCity | CH-07290 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 7041 | Staatsburg | N |  | 7.6 | [13 empty] | NM | N | DELTA SOLIVIA 7.6 TL | 2016-12-02 | 2016-12-02 | 0 | 2016-12-02 | [14 empty] | 2017-02-16 | 2017-02-16 |  | Y
Central Hudson |  | Monolith Solar Associates LLC | CH-02664 | Catskill | W Coxsackie | Greene | 12192 | G | 1071 | Coxsackie | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A-UA | 2016-12-05 | 2016-12-05 | 0 | 2016-12-05 | [14 empty] | 2017-01-20 | 2017-01-20 |  | Y
Central Hudson |  | SolarCity | CH-07668 | Fishkill | Beacon | Dutchess | 12508 | G | 8085 | Tioronda | N |  | 3 | [13 empty] | NM | N | SOLAREDGE SE 3000A-US | 2016-12-05 | 2016-12-06 | 1 | 2016-12-06 | [14 empty] | 2016-12-30 | 2016-12-30 |  | Y
Central Hudson |  | SolarCity | CH-07792 | Newburgh | Cornwall | Orange | 12518 | G | 4041 | Union Ave | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE 5000A | 2016-12-05 | 2016-12-05 | 0 | 2016-12-05 | [14 empty] | 2016-12-21 | 2016-12-21 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Trinity Solar | CH-08386 | Catskill |  |  | 12405 | G | 2041 | South Cairo | TBD |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A-US | 2016-12-05 | 2016-12-05 | 0 | 2016-12-05 | [17 empty] | W
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08749 | Poughkeepsie |  |  | 12601 | G | 6065 | Inwood Ave | TBD |  | 3.87 | [13 empty] | NM | N | 18 ENPHASE M215 | 2016-12-05 | 2016-12-05 | 0 | 2016-12-05 | [17 empty] | W
Central Hudson |  | American Solar Partners | CH-00007 | Newburgh | New Paltz | Ulster | 12561 | G | 5031 | Galeville | N |  | 3 | [13 empty] | NM | N | SOLAREDGE SE3000 | 2016-12-06 | 2016-12-06 | 0 | 2016-12-06 | [14 empty] | 2017-07-10 | 2017-07-11 |  | Y
Central Hudson |  | Green Street Power Partners, LLC | CH-00108 | Newburgh | Milton | Ulster | 12547 | G | 5002 | Marlboro | N |  | 7.7 | [13 empty] | NM | N | SMA SB7700TL | 2016-12-06 | 2016-12-07 | 1 | 2016-12-07 | [14 empty] | 2017-06-01 | 2017-06-06 |  | Y
Central Hudson |  | Direct Energy Solar | CH-01051 | Kingston | Grahamsvl | Sullivan | 12740 | G | 3091 | Neversink | N |  | 7.5 | [13 empty] | NM | N | 30 ENPHASE M250 | 2016-12-06 | 2016-12-06 | 0 | 2016-12-06 | [14 empty] | 2017-01-20 | 2017-01-23 |  | Y
Central Hudson |  | SolarCity | CH-04926 | Catskill |  |  | 12469 | G | 1092 | Westerlo | TBD |  | 6.6 | [13 empty] | NM | N | DELTA SOLIVIA 6.6 | 2017-08-30 | 2017-08-30 | 0 | 2017-08-30 | [14 empty] | 2017-09-21 | 2017-09-27 |  | W
Central Hudson |  | SolarCity | CH-05989 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8091 | Fishkill Plains | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000 | 2016-12-06 | 2016-12-06 | 0 | 2016-12-06 | [14 empty] | 2017-01-25 | 2017-01-31 |  | Y
Central Hudson |  | SolarCity | CH-06118 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8071 | Shenandoah | N |  | 10 | [13 empty] | NM | N | SOLAREDGE SE10000 | 2016-12-06 | 2016-12-06 | 0 | 2016-12-06 | [14 empty] | 2017-01-25 | 2017-01-31 |  | Y
Central Hudson |  | SolarCity | CH-06261 | Newburgh | New Windsor | Orange | 12553 | G | 4045 | Union Ave | N |  | 5.2 | [13 empty] | NM | N | DELTA SOLIVIA 5.2 | 2016-12-06 | 2016-12-06 | 0 | 2016-12-06 | [14 empty] | 2017-01-25 | 2017-01-25 |  | Y
Central Hudson |  | SolarCity | CH-06449 | Catskill | Preston Holw | Albany | 12469 | G | 1092 | Westerlo | N |  | 6.6 | [13 empty] | NM | N | DELTA SOLIVIA 6.6 | 2017-08-30 | 2017-08-30 | 0 | 2017-08-30 | [14 empty] | 2017-09-21 | 2017-09-27 |  | Y
Central Hudson |  | SolarCity | CH-06777 | Poughkeepsie |  |  | 12571 | G | 7091 | Pulvers Corners | TBD |  | 10.4 | [13 empty] | NM | N | DELTA SOLIVIA 6.6 DELTA SOLIVIA 3.8 | 2016-12-06 | 2016-12-07 | 1 | 2016-12-07 | [17 empty] | W
Central Hudson |  | SolarCity | CH-07059 | Newburgh | Newburgh | Orange | 12550 | G | 4015 | West Balmville | N |  | 5.2 | [13 empty] | NM | N | DELTA SOLIVIA 5.2 | 2016-12-06 | 2016-12-06 | 0 | 2016-12-06 | [14 empty] | 2017-01-25 | 2017-01-25 |  | Y
Central Hudson |  | SolarCity | CH-07609 | Newburgh | Wallkill | Ulster | 12589 | G | 5043 | East Walden | N |  | 3.8 | [13 empty] | NM | N | DELTA SOLIVIA 3.8 | 2016-12-06 | 2016-12-06 | 0 | 2016-12-06 | [14 empty] | 2017-01-10 | 2017-01-10 |  | Y
Central Hudson |  | SolarCity | CH-07651 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 7011 | Hibernia | N |  | 3.8 | [13 empty] | NM | N | DELTA SOLIVIA 3.8 | 2016-12-06 | 2016-12-08 | 2 | 2016-12-08 | [14 empty] | 2017-01-25 | 2017-01-31 |  | Y
Central Hudson |  | Solar Generation | CH-08080 | Kingston | Olive Brdg | Ulster | 12461 | G | 3082 | Kerhonkson | N |  | 16 | [13 empty] | NM | N | 50 SUNPOWER X21-335 | 2017-01-19 | 2017-01-20 | 1 | 2017-01-20 | [14 empty] | 2017-02-23 | 2017-02-23 |  | Y
Central Hudson |  | Trinity Solar | CH-08446 | Newburgh |  |  | 12561 | G | 5024 | Ohioville | TBD |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A-US | 2016-12-06 | 2016-12-06 | 0 | 2016-12-06 | [17 empty] | W
Central Hudson |  | Solar Landscape, LLC | CH-03350 | Newburgh | New Windsor | Orange | 12553 | G | 4046 | Union Ave | N |  | 1980 | [13 empty] | CDG | Y | 33 Yaskawa Solectria Solar PVI60kW-240 | 2016-12-07 | 2016-12-21 | 10 | 2016-12-21 | 2016-12-21 | 2017-01-16 | 15 | 2017-03-03 | 2017-03-06 | 2017-05-31 | 60 | 9048.89 | 167392.5 | 106797.62 | 2017-06-27 | 2017-12-08 | 2017-12-08 | 2019-05-07 | 2019-08-29 | 2019-08-29 | 2019-11-22 | Y | Y | CESIR for 2 projects, CH-03349 and CH-03350 combined with an aggregate CESIR Cost to Customer of $40,000.
Central Hudson |  | SolarCity | CH-07440 | Newburgh | Newburgh | Orange | 12550 | G | 4045 | Union Ave | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000 | 2016-12-07 | 2016-12-07 | 0 | 2016-12-07 | [14 empty] | 2017-02-03 | 2017-03-10 |  | Y
Central Hudson |  | SolarCity | CH-07765 | Newburgh |  |  | 12561 | G | 5024 | Ohioville | TBD |  | 7.6 | [13 empty] | NM | N | DELTA SOLIVIA 7.6 | 2016-12-07 | 2016-12-21 | 10 | 2016-12-21 | [8 empty] | 350 | 350 | [7 empty] | W
Central Hudson |  | Solar Generation | CH-08081 | Kingston | Accord | Ulster | 12404 | G | 3024 | High Falls | N |  | 6 | [13 empty] | NM | N | SMA SB6 | 2016-12-07 | 2016-12-07 | 0 | 2016-12-07 | [14 empty] | 2017-02-02 | 2017-02-02 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08797 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8092 | Fishkill Plains | N |  | 5.8 | [13 empty] | NM | N | 27 ENPHASE M215 | 2016-12-07 | 2016-12-07 | 0 | 2016-12-07 | [14 empty] | 2017-02-08 | 2017-02-08 |  | Y
Central Hudson |  | SolarCity | CH-06546 | Kingston |  |  | 12443 | G | 2094 | Hurley Ave | TBD |  | 6.6 | [13 empty] | NM | N | DELTA SOLIVIA 6.6 | 2016-12-08 | 2016-12-08 | 0 | 2016-12-08 | [17 empty] | W
Central Hudson |  | SolarCity | CH-07046 | Newburgh | New Windsor | Orange | 12553 | G | 4042 | Union Ave | N |  | 7.6 | [13 empty] | NM | N | DELTA SOLIVIA 7.6 | 2016-12-08 | 2016-12-08 | 0 | 2016-12-08 | [14 empty] | 2017-01-25 | 2017-01-27 |  | Y
Central Hudson |  | SolarCity | CH-07259 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6042 | Spackenkill | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A | 2016-12-08 | 2016-12-08 | 0 | 2016-12-08 | [14 empty] | 2017-01-30 | 2017-01-31 |  | Y
Central Hudson |  | SolarCity | CH-07307 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6046 | Spackenkill | N |  | 7.6 | [13 empty] | NM | N | DELTA SOLIVIA 7.6 | 2016-12-08 | 2016-12-08 | 0 | 2016-12-08 | [14 empty] | 2017-03-29 | 2017-03-30 |  | Y
Central Hudson |  | Sungevity Inc | CH-09247 | Newburgh |  |  | 12528 | G | 5083 | Highland | TBD |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE7600 | 2016-12-08 | 2016-12-08 | 0 | 2016-12-08 | [17 empty] | W
Central Hudson |  | SolarCity | CH-06132 | Fishkill | Holmes | Dutchess | 12531 | G | 8071 | Shenandoah | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge se10000 | 2016-12-09 | 2016-12-09 | 0 | 2016-12-09 | [14 empty] | 2017-01-31 | 2017-01-31 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08602 | Catskill | Catskill | Greene | 12414 | G | 2005 | North Catskill | N |  | 10.32 | [13 empty] | NM | N | 48 ENPHASE M215 | 2016-12-15 | 2016-12-15 | 0 | 2016-12-15 | [14 empty] | 2017-02-09 | 2017-02-14 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-00137 | Newburgh | Milton | Ulster | 12547 | G | 5083 | Highland | N |  | 8.96 | [13 empty] | NM | N | 28 SUNPOWER SPR-X21-335-BLK | 2016-12-12 | 2016-12-12 | 0 | 2016-12-12 | [14 empty] | 2017-03-16 | 2017-03-21 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-00208 | Newburgh | Newburgh | Orange | 12550 | G | 4012 | West Balmville | N |  | 6.4 | [13 empty] | NM | N | 20 SUNPOWER SPR | 2016-12-12 | 2016-12-12 | 0 | 2016-12-12 | [14 empty] | 2017-03-02 | 2017-03-21 |  | Y
Central Hudson |  | Enlighten Power Solutions | CH-01118 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7051 | Rhinebeck | N |  | 5 | [13 empty] | NM | N | ENPHASE M250-60-2LL (20) | 2016-12-15 | 2016-12-15 | 0 | 2016-12-15 | [14 empty] | 2016-12-28 | 2016-12-28 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Hudson Solar | CH-01894 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7061 | Milan | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE7600 | 2016-12-12 | 2016-12-12 | 0 | 2016-12-12 | [14 empty] | 2017-03-02 | 2017-03-02 |  | Y
Central Hudson |  | SolarCity | CH-06160 | Newburgh | New Paltz | Ulster | 12561 | G | 5031 | Galeville | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE 7.6 | 2017-01-03 | 2017-01-04 | 1 | 2017-01-04 | [14 empty] | 2017-02-03 | 2017-02-03 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06906 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8071 | Shenandoah | N |  | 7.6 | [13 empty] | NM | N | DELTA SOLIVIA 7.6 | 2016-12-12 | 2016-12-12 | 0 | 2016-12-12 | [14 empty] | 2017-02-15 | 2017-02-23 |  | Y
Central Hudson |  | SolarCity | CH-07385 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8055 | North Chelsea | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE 7.6 | 2017-01-04 | 2017-01-04 | 0 | 2017-01-04 | [14 empty] | 2018-03-06 | 2018-03-08 |  | Y
Central Hudson |  | SolarCity | CH-07591 | Newburgh | New Windsor |  | 12553 | G | 4044 | Union Ave | N |  | 3.8 | [13 empty] | NM | N | SOLAREDGE SE 3800A | 2017-02-24 | 2017-02-27 | 1 | 2017-02-27 | [17 empty] | W
Central Hudson |  | Apex Solar Power | CH-00015 | Catskill | Westerlo | Albany | 12193 | G | 1091 | Westerlo | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A-US | 2016-12-15 | 2016-12-15 | 0 | 2016-12-15 | [14 empty] | 2017-01-20 | 2017-01-20 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-00055 | Newburgh | New Paltz | Ulster | 12561 | G | 5024 | Ohioville | N |  | 11.4 | [13 empty] | NM | N | SOLAREDGE SE 11400 | 2016-12-13 | 2016-12-14 | 1 | 2016-12-14 | [14 empty] | 2017-02-13 | 2017-02-13 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-00105 | Fishkill |  |  | 12582 | G | 8071 | Shenandoah | TBD |  | 11.4 | [13 empty] | NM | N | SOLAREDGE 11400A | 2016-12-14 | 2016-12-14 | 0 | 2016-12-14 | [17 empty] | W
Central Hudson |  | Infinity Solar Systems | CH-00203 | Fishkill | Fishkill | Dutchess | 12524 | G | 8094 | Fishkill Plains | N |  | 6.4 | [13 empty] | NM | N | SUNPOWER SPR-X21-335-BLK (20) | 2016-12-13 | 2016-12-13 | 0 | 2016-12-13 | [14 empty] | 2017-02-08 | 2017-02-08 |  | Y
Central Hudson |  | New York State Solar Farm | CH-00443 | Newburgh | Wallkill | Ulster | 12589 | G | 5041 | East Walden | N |  | 4.16 | [13 empty] | NM | N | sunpower x22-360-C-AC (13) | 2016-12-13 | 2016-12-13 | 0 | 2016-12-13 | [14 empty] | 2016-12-28 | 2017-01-03 |  | Y
Central Hudson |  | American Energy Care | CH-00654 | Catskill | Round Top | Greene | 12473 | G | 2042 | South Cairo | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000 | 2016-12-22 | 2016-12-22 | 0 | 2016-12-22 | [14 empty] | 2017-02-27 | 2017-02-27 |  | Y
Central Hudson |  | Direct Energy Solar | CH-01021 | Newburgh | New Windsor | Orange | 12553 | G | 4046 | Union Ave | N |  | 10.32 | [13 empty] | NM | N | 48 ENPHASE M215 | 2016-12-14 | 2016-12-30 | 10 | 2016-12-30 | [14 empty] | 2017-03-31 | 2017-03-31 |  | Y
Central Hudson |  | Paradise Energy Solutions LLC | CH-02850 | Newburgh | Wallkill | Ulster | 12589 | G | 5043 | East Walden | N |  | 31.4 | [13 empty] | NM | N | SOLAREDGE SE 114000 2 SOLAREDGE SE 10000 | 2016-12-16 | 2016-12-16 | 0 | 2016-12-16 | [14 empty] | 2017-02-21 | 2017-02-21 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08726 | Catskill | E Durham | Greene | 12423 | G | 1092 | Westerlo | N |  | 11.61 | [13 empty] | NM | N | ENPHASE M215 602LLS22IG (54) | 2016-12-13 | 2016-12-13 | 0 | 2016-12-13 | [14 empty] | 2017-05-09 | 2017-05-09 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-00091 | Poughkeepsie | Lagrangevl | Dutchess | 12540 | G | 6057 | Todd Hill | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE 7600 | 2016-12-14 | 2016-12-14 | 0 | 2016-12-14 | [14 empty] | 2017-05-25 | 2017-06-01 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-00097 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6068 | Inwood Ave | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE 7600A | 2017-01-26 | 2017-01-26 | 0 | 2017-01-26 | [14 empty] | 2017-02-14 | 2017-02-21 |  | Y
Central Hudson |  | New York State Solar Farm | CH-00440 | Newburgh | Marlboro | Ulster | 12542 | G | 5003 | Marlboro | N |  | 7.36 | [13 empty] | NM | N | 23 SUNPOWER SPR-X21 | 2016-12-14 | 2016-12-14 | 0 | 2016-12-14 | [14 empty] | 2016-12-27 | 2016-12-30 |  | Y
Central Hudson |  | SolarCity | CH-06458 | Catskill | Greenvl | Greene | 12083 | G | 2061 | Freehold | N |  | 6.6 | [13 empty] | NM | N | DELTA SOLIVIA 6.6 | 2016-12-29 | 2016-12-30 | 1 | 2016-12-30 | [8 empty] | 350 | 350 |  | 2017-02-28 | 2017-02-28 | 2017-03-06 | 2017-03-06 | 2017-03-10 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Empire Solar Solutions | CH-00089 | Newburgh | Wallkill | Ulster | 12589 | G | 4011 | West Balmville | N |  | 11.4 | [13 empty] | NM | N | SOLAREDGE 11400A | 2017-01-25 | 2017-01-25 | 0 | 2017-01-25 | [8 empty] | 350 | 350 |  | 2017-02-21 | 2017-02-21 | 2017-03-01 | 2017-05-15 | 2017-05-15 |  | Y
Central Hudson |  | SolarCity | CH-06847 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8096 | Fishkill Plains | N |  | 11.4 | [13 empty] | NM | N | SOLAREDGE SE 11400A | 2016-12-15 | 2016-12-15 | 0 | 2016-12-15 | [14 empty] | 2017-01-17 | 2017-01-25 |  | Y
Central Hudson |  | SolarCity | CH-07026 | Newburgh | Newburgh | Orange | 12550 | G | 4045 | Union Ave | N |  | 5.2 | [13 empty] | NM | N | DELTA SOLIVIA 5.2 | 2016-12-30 | 2016-12-30 | 0 | 2016-12-30 | [14 empty] | 2017-01-25 | 2017-02-02 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08725 | Catskill |  |  | 12423 | G | 2043 | South Cairo | TBD |  | 17.41 | [13 empty] | NM | N | 81 ENPHASE M215 | 2016-12-19 | 2016-12-19 | 0 | 2016-12-19 | [17 empty] | W
Central Hudson |  | Empire Solar Solutions | CH-00028 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8072 | Shenandoah | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE 7600A | 2016-12-19 | 2016-12-19 | 0 | 2016-12-19 | [14 empty] | 2017-03-16 | 2017-03-17 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-00045 | Poughkeepsie | Staatsburg | Dutchess | 12580 | G | 7042 | Staatsburg | N |  | 17.6 | [13 empty] | NM | N | SOLAREDGE 10000A SOLAREDGE 7600A | 2016-12-19 | 2016-12-19 | 0 | 2016-12-19 | [14 empty] | 2017-02-16 | 2017-02-16 |  | Y
Central Hudson |  | NRG Home Solar | CH-00563 | Kingston | Mount Marion | Ulster | 12456 | G | 2016 | Lincoln Park | N |  | 3.01 | [13 empty] | NM | N | 14 ENPHASE M215 | 2016-12-16 | 2016-12-16 | 0 | 2016-12-16 | [14 empty] | 2017-03-09 | 2017-03-10 |  | Y
Central Hudson |  | Hudson Solar | CH-02487 | Newburgh | Newburgh | Orange | 12550 | G | 4045 | Union Ave | N | CH-01351 | 5.12 | [13 empty] | NM | N | 16 SUNPOWER E320-327 | 2016-12-19 | 2016-12-19 | 0 | 2016-12-19 | [14 empty] | 2017-05-25 | 2017-06-02 |  | Y
Central Hudson |  | Hudson Solar | CH-02518 | Poughkeepsie |  |  | 12581 | G | 7072 | Stanfordville | TBD |  | 65.2 | [13 empty] | NM | N | 5 SOLAREDGE SE10000 2 SOL 7600 | 2017-01-06 | 2017-01-06 | 0 | 2017-01-06 | 2017-01-06 | 2017-01-27 | 15 |  |  |  |  | 18000 | 2500 | 3892.41 | [7 empty] | W
Central Hudson |  | SolarCity | CH-06003 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8091 | Fishkill Plains | N |  | 15.2 | [13 empty] | NM | N | 2 DELTA SOLIVIA 7.6 | 2016-12-16 | 2016-12-16 | 0 | 2016-12-16 | [14 empty] | 2017-01-25 | 2017-01-31 |  | Y
Central Hudson |  | SolarCity | CH-07644 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6011 | Sand Dock | N |  | 10 | [13 empty] | NM | N | SOLAREDGE SE 10000A | 2016-12-16 | 2016-12-16 | 0 | 2016-12-16 | [14 empty] | 2017-07-27 | 2017-08-03 |  | Y
Central Hudson |  | NRG Home Solar | CH-00548 | Newburgh | Rock Tvrn | Orange | 12575 | G | 4097 | Bethlehem Rd | N |  | 7.52 | [13 empty] | NM | N | 35 ENPHASE M215 | 2016-12-19 | 2016-12-19 | 0 | 2016-12-19 | [14 empty] | 2017-04-06 | 2017-04-10 |  | Y
Central Hudson |  | NRG Home Solar | CH-00573 | Fishkill |  |  | 12508 | G | 8018 | Forgebrook | N |  | 4.3 | [13 empty] | NM | N | 20 ENPHASE M215 | 2016-12-19 | 2016-12-19 | 0 | 2016-12-19 | [17 empty] | W
Central Hudson |  | Roberts Contracting Inc | CH-02988 | Newburgh | New Paltz | Ulster | 12561 | G | 5011 | Modena | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE7600A | 2016-12-19 | 2016-12-19 | 0 | 2016-12-19 | [14 empty] | 2017-04-25 | 2017-04-25 |  | W
Central Hudson |  | STR Systems NY LLC | CH-08319 | Poughkeepsie | Hyde Park | Dutchess | 12538 | G | 6075 | East Park | N |  | 11.4 | [13 empty] | NM | N | SOLAREDGE SE11400A | 2016-12-19 | 2016-12-19 | 0 | 2016-12-19 | [14 empty] | 2017-04-07 | 2017-04-13 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08694 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8092 | Fishkill Plains | N |  | 5.59 | [13 empty] | NM | N | 26 ENPHASE M215 | 2016-12-22 | 2016-12-22 | 0 | 2016-12-22 | [14 empty] | 2017-03-20 | 2017-03-23 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-00073 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6011 | Sand Dock | N |  | 6 | [13 empty] | NM | N | SOLAREDGE 6000A | 2016-12-20 | 2016-12-20 | 0 | 2016-12-20 | [14 empty] | 2017-02-07 | 2017-02-13 |  | Y
Central Hudson |  | Lighthouse Solar | CH-00290 | Kingston | Saugerties | Ulster | 12477 | G | 3003 | Saugerties | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE 7600 | 2016-12-20 | 2016-12-21 | 1 | 2016-12-21 | [14 empty] | 2017-01-23 | 2017-01-27 |  | Y
Central Hudson |  | Lighthouse Solar | CH-00321 | Newburgh | New Paltz |  | 12561 | G | 5031 | Galeville | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE 7600 | 2016-12-21 | 2016-12-22 | 1 | 2016-12-22 | [14 empty] | 2017-06-16 | 2017-06-20 |  | W
Central Hudson |  | SolarCity | CH-04965 | Kingston | Saugerties | Ulster | 12477 | G | 3001 | Saugerties | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000 | 2017-02-24 | 2017-02-24 | 0 | 2017-02-24 | [14 empty] | 2017-02-28 | 2017-03-03 |  | Y
Central Hudson |  | SolarCity | CH-06596 | Kingston | Kingston | Ulster | 12401 | G | 1021 | East Kingston | N |  | 5.2 | [13 empty] | NM | N | DELTA SOLIVIA 5.2 | 2016-12-20 | 2016-12-20 | 0 | 2016-12-20 | [14 empty] | 2017-02-13 | 2017-02-13 |  | Y
Central Hudson |  | SolarCity | CH-07400 | Fishkill |  |  | 12508 | G | 8018 | Forgebrook | N |  | 7.6 | [13 empty] | NM | N | DELTA SOLIVIA 7.6 | 2016-12-20 | 2016-12-21 | 1 | 2016-12-21 | [17 empty] | W
Central Hudson |  | SolarCity | CH-07681 | Newburgh | Newburgh | Orange | 12550 | G | 4051 | Union Ave | N |  | 5.2 | [13 empty] | NM | N | DELTA SOLIVIA 5.2 | 2016-12-20 | 2016-12-21 | 1 | 2016-12-21 | [14 empty] | 2017-02-06 | 2017-03-31 |  | Y
Central Hudson |  | SolarCity | CH-07822 | Newburgh | Newburgh | Orange | 12550 | G | 4014 | West Balmville | N | CH-06974 | 3.8 | [13 empty] | NM | N | DELTA 3.8 | 2017-01-03 | 2017-01-04 | 1 | 2017-01-04 | [14 empty] | 2017-01-25 | 2017-01-25 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08779 | Catskill | Durham | Greene | 12422 | G | 1092 | Westerlo | N | CH-08779 | 4.08 | [13 empty] | NM | N | 19 ENPHASE M215 | 2016-12-20 | 2016-12-21 | 1 | 2016-12-21 | [14 empty] | 2017-05-31 | 2017-06-05 |  | Y
Central Hudson |  | Lighthouse Solar | CH-00271 | Kingston | Accord | Ulster | 12404 | G | 3081 | Kerhonkson | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE 7600A | 2016-12-21 | 2016-12-22 | 1 | 2016-12-22 | [14 empty] | 2017-07-12 | 2017-07-12 |  | Y
Central Hudson |  | Lighthouse Solar | CH-00276 | Newburgh | Gardiner | Ulster | 12525 | G | 5011 | Modena | N |  | 22.8 | [13 empty] | NM | N | SOLAREDGE SE11400 | 2016-12-22 | 2016-12-27 | 1 | 2016-12-27 | [8 empty] | 350 | 350 |  | 2017-03-02 | 2017-03-02 | 2017-03-08 | 2017-09-07 | 2017-09-08 |  | Y
Central Hudson |  | NRG Home Solar | CH-00494 | Newburgh | Marlboro | Ulster | 12542 | G | 5003 | Marlboro | N |  | 6.665 | [13 empty] | NM | N | 31 ENPHASE M215 | 2016-12-21 | 2016-12-22 | 1 | 2016-12-22 | [14 empty] | 2017-02-21 | 2017-02-21 |  | Y
Central Hudson |  | SolarCity | CH-05106 | Kingston | Saugerties | Ulster | 12477 | G | 2015 | Lincoln Park | N |  | 5.2 | [13 empty] | NM | N | DELTA SOLIVIA 5.2 | 2017-01-09 | 2017-01-09 | 0 | 2017-01-09 | [14 empty] | 2017-01-10 | 2017-01-10 |  | Y
Central Hudson |  | SolarCity | CH-05251 | Kingston | Saugerties | Ulster | 12477 | G | 2015 | Lincoln Park | N |  | 11.8 | [13 empty] | NM | N | DELTA SOLIVIA 5.2 DELTA SOLIVIA 6.6 | 2016-12-21 | 2016-12-22 | 1 | 2016-12-22 | [14 empty] | 2017-03-20 | 2017-03-23 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06414 | Newburgh | Montgomery | Orange | 12549 | G | 5073 | Montgomery | N |  | 3.8 | [13 empty] | NM | N | DELTA SOLIVIA 3.8 | 2016-12-21 | 2016-12-22 | 1 | 2016-12-22 | [14 empty] | 2017-04-05 | 2017-04-12 |  | Y
Central Hudson |  | SolarCity | CH-06611 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6046 | Spackenkill | N |  | 6.6 | [13 empty] | NM | N | DELTA SOLIVIA 6.6 | 2016-12-21 | 2016-12-22 | 1 | 2016-12-22 | [14 empty] | 2017-02-27 | 2017-02-27 |  | Y
Central Hudson |  | SolarCity | CH-06861 | Fishkill | Wappingers Falls | Dutchess | 12590 | G | 8092 | Fishkill Plains | N |  | 11.4 | [13 empty] | NM | N | 1 DELTA SOLIVIA 7.6 1 DELTA SOLIVIA 3.8 | 2016-12-21 | 2016-12-27 | 2 | 2016-12-27 | [14 empty] | 2017-05-24 | 2017-05-24 |  | Y
Central Hudson |  | SolarCity | CH-07331 | Newburgh | Highland | Ulster | 12528 | G | 5084 | Highland | N |  | 3.8 | [13 empty] | NM | N | Solar Edge SE3800A | 2016-12-21 | 2016-12-22 | 1 | 2016-12-22 | [14 empty] | 2017-04-05 | 2017-04-06 |  | Y
Central Hudson |  | SolarCity | CH-07665 | Fishkill | Fishkill | Dutchess | 12524 | G | 8014 | Forgebrook | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE 7.6 | 2016-12-21 | 2016-12-22 | 1 | 2016-12-22 | [14 empty] | 2017-02-02 | 2017-02-03 |  | Y
Central Hudson |  | SolarCity | CH-07779 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6008 | Reynolds Hill | N |  | 3.8 | [13 empty] | NM | N | DELTA SOLIVIA 3.8 | 2017-01-06 | 2017-01-06 | 0 | 2017-01-06 | [14 empty] | 2017-03-22 | 2017-03-24 |  | Y
Central Hudson |  | Trinity Solar | CH-08445 | Newburgh | New Paltz | Ulster | 12561 | G | 5031 | Galeville | N |  | 3.8 | [13 empty] | NM | N | SOLAREDGE SE3800A | 2016-12-21 | 2016-12-29 | 4 | 2016-12-29 | [14 empty] | 2017-02-17 | 2017-02-17 |  | Y
Central Hudson |  | Trinity Solar | CH-08524 | Catskill | Catskill | Greene | 12414 | G | 2001 | North Catskill | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000 | 2016-12-21 | 2016-12-27 | 2 | 2016-12-27 | [14 empty] | 2017-02-15 | 2017-02-21 |  | Y
Central Hudson |  | Hudson Solar | CH-01760 | Poughkeepsie |  |  | 12580 | G | 7011 | Hibernia | TBD |  | 13.6 | [13 empty] | NM | N | SOLAREDGE SE7600 SOLAREDGE SE6000 | 2016-12-27 | 2016-12-27 | 0 | 2016-12-27 | [17 empty] | W
Central Hudson |  | Hudson Solar | CH-01903 | Poughkeepsie | Stanfordville | Dutchess | 12581 | G | 7072 | Stanfordville | N |  | 15.2 | [13 empty] | NM | N | 2 SOLAREDGE SE 7600 | 2017-02-17 | 2017-02-17 | 0 | 2017-02-17 | [8 empty] | 350 | 350 |  | 2017-03-03 | 2017-03-03 | 2017-04-19 | 2017-08-09 | 2017-08-09 |  | Y
Central Hudson |  | Hudson Solar | CH-02415 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 6074 | East Park | N |  | 10 | [13 empty] | NM | N | SOLAREDGE SE10000 | 2016-12-22 | 2016-12-27 | 1 | 2016-12-27 | [8 empty] | 350 | 350 |  | 2017-01-12 | 2017-01-12 | 2017-01-26 | 2018-02-20 | 2018-03-07 |  | Y |  | Storm Restoration due to 3/2/18 Heavy Wet Snow and Damaging Wind Storm.
Central Hudson |  | Hudson Solar | CH-02500 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8046 | Myers Corners | N | CH-01913 | 3.2 | [13 empty] | NM | N | 10 SUNPOWER X21-345 | 2017-01-12 | 2017-01-12 | 0 | 2017-01-12 | [14 empty] | 2017-02-06 | 2017-02-06 |  | Y
Central Hudson |  | Trinity Solar | CH-08477 | Kingston | Saugerties | Ulster | 12477 | G | 3003 | Saugerties | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000 | 2016-12-22 | 2016-12-27 | 1 | 2016-12-27 | [14 empty] | 2017-03-16 | 2017-03-20 |  | Y
Central Hudson |  | Trinity Solar | CH-08507 | Fishkill | Fishkill | Dutchess | 12524 | G | 8094 | Fishkill Plains | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A-US | 2016-12-22 | 2016-12-27 | 1 | 2016-12-27 | [14 empty] | 2017-01-30 | 2017-02-03 |  | Y
Central Hudson |  | Trinity Solar | CH-08536 | Poughkeepsie | Lagrangevl | Dutchess | 12540 | G | 6053 | Todd Hill | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A | 2016-12-22 | 2016-12-27 | 1 | 2016-12-27 | [14 empty] | 2017-08-23 | 2017-08-24 |  | Y
Central Hudson |  | Trinity Solar | CH-08542 | Fishkill | Fishkill | Dutchess | 12524 | G | 8094 | Fishkill Plains | N |  | 6.8 | [13 empty] | NM | N | SOLAREDGE SE3800 SOLAREDGE SE3000 | 2016-12-22 | 2016-12-27 | 1 | 2016-12-27 | [14 empty] | 2017-01-30 | 2017-01-31 |  | Y
Central Hudson |  | Trinity Solar | CH-08571 | Catskill | Climax | Greene | 12042 | G | 1071 | Coxsackie | N |  | 12 | [13 empty] | NM | N | 2 SOLAREDGE SE6000A | 2016-12-22 | 2016-12-27 | 1 | 2016-12-27 | [14 empty] | 2017-03-28 | 2017-03-29 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08761 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8094 | Fishkill Plains | N |  | 10.53 | [13 empty] | NM | N | 49 ENPHASE M215 | 2016-12-22 | 2016-12-27 | 1 | 2016-12-27 | [8 empty] | 350 | 350 |  | 2017-03-13 | 2017-03-13 | 2017-04-21 | 2017-05-09 | 2017-05-15 |  | Y
Central Hudson |  | Lighthouse Solar | CH-00295 | Newburgh | New Paltz | Ulster | 12561 | G | 5031 | Galeville | N |  | 6 | [13 empty] | NM | N | SOLAREDGE 6000A | 2016-12-27 | 2016-12-27 | 0 | 2016-12-27 | [14 empty] | 2017-12-07 | 2017-12-07 |  | Y
Central Hudson |  | NRG Home Solar | CH-00496 | Newburgh | Wallkill | Ulster | 12589 | G | 5041 | East Walden | N |  | 5.59 | [13 empty] | NM | N | 26 ENPHASE M215 | 2016-12-27 | 2016-12-27 | 0 | 2016-12-27 | [14 empty] | 2017-03-01 | 2017-03-06 |  | Y
Central Hudson |  | NRG Home Solar | CH-00505 | Poughkeepsie |  |  | 12601 | G | 6061 | Inwood Ave | TBD |  | 5.16 | [13 empty] | NM | N | 24 ENPHASE M215 | 2016-12-27 | 2016-12-27 | 0 | 2016-12-27 | [17 empty] | W
Central Hudson |  | Hudson Solar | CH-01539 | Newburgh | New Paltz | Ulster | 12561 | G | 5031 | Galeville | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE7600 | 2017-01-25 | 2017-01-25 | 0 | 2017-01-25 | [8 empty] | 350 | 350 |  | 2017-02-07 | 2017-02-07 | 2017-07-17 | 2017-07-25 | 2017-07-25 |  | Y
Central Hudson |  | Hudson Solar | CH-02064 | Poughkeepsie | Poughkeepsie |  | 12601 | G | 6011 | Sand Dock | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE7600 | 2016-12-27 | 2016-12-27 | 0 | 2016-12-27 | [17 empty] | W
Central Hudson |  | SolarCity | CH-07063 | Newburgh | Newburgh | Orange | 12550 | G | 4011 | West Balmville | N |  | 10 | [13 empty] | NM | N | SOLAREDGE SE10000 | 2016-12-27 | 2016-12-27 | 0 | 2016-12-27 | [14 empty] | 2017-03-03 | 2017-03-10 |  | Y
Central Hudson |  | SolarCity | CH-07128 | Newburgh | Rock Tvrn | Orange | 12575 | G | 4097 | Bethlehem Rd | N |  | 10 | [13 empty] | NM | N | SOLAREDGE 10000 | 2016-12-27 | 2016-12-29 | 2 | 2016-12-29 | [14 empty] | 2017-01-19 | 2017-01-19 |  | Y
Central Hudson |  | SolarCity | CH-07517 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6046 | Spackenkill | N |  | 7.6 | [13 empty] | NM | N | DELTA SOLIVIA 7.6 | 2016-12-27 | 2016-12-27 | 0 | 2016-12-27 | [14 empty] | 2017-01-05 | 2017-01-12 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-00088 | Fishkill | Stormvl | Dutchess | 12582 | G | 8071 | Shenandoah | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000 | 2016-12-29 | 2016-12-29 | 0 | 2016-12-29 | [14 empty] | 2017-01-30 | 2017-01-31 |  | Y
Central Hudson |  | NRG Home Solar | CH-00534 | Poughkeepsie | Poughquag | Dutchess | 12570 | G | 6055 | Todd Hill | N |  | 3.22 | [13 empty] | NM | N | 15 ENPHASE M215 | 2016-12-28 | 2016-12-29 | 1 | 2016-12-29 | [14 empty] | 2017-03-03 | 2017-03-03 |  | Y
Central Hudson |  | Kool-Temp | CH-02572 | Catskill | Earlton | Greene | 12058 | G | 2006 | North Catskill | N |  | 20 | [13 empty] | NM | N | 2 FRONIUS PRIMO 10 | 2017-01-03 | 2017-01-03 | 0 | 2017-01-03 | [14 empty] | 2017-01-16 | 2017-01-16 |  | Y
Central Hudson |  | SolarCity | CH-05951 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7054 | Rhinebeck | N |  | 6.6 | [13 empty] | NM | N | DELTA SOLIVIA 6.6 | 2016-12-29 | 2016-12-29 | 0 | 2016-12-29 | [14 empty] | 2017-02-15 | 2017-02-21 |  | Y
Central Hudson |  | SolarCity | CH-06268 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 5.2 | [13 empty] | NM | N | DELTA SOLIVIA 5.2 | 2016-12-28 | 2016-12-29 | 1 | 2016-12-29 | [14 empty] | 2017-01-25 | 2017-01-25 |  | Y
Central Hudson |  | SolarCity | CH-07114 | Newburgh | New Windsor | Orange | 12553 | G | 4093 | Bethlehem Rd | N |  | 11.4 | [13 empty] | NM | N | SOLAREDGE SE11400 | 2017-01-16 | 2017-01-16 | 0 | 2017-01-16 | [8 empty] | 350 | 350 |  | 2017-03-17 | 2017-03-17 | 2017-03-22 | 2017-04-17 | 2017-04-17 |  | Y
Central Hudson |  | Trinity Solar | CH-08447 | Newburgh | New Paltz | Ulster | 12561 | G | 5023 | Ohioville | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000 | 2016-12-28 | 2016-12-30 | 2 | 2016-12-30 | [14 empty] | 2017-01-25 | 2017-01-25 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Solar Alchemy | CH-08978 | Kingston | Olive Brdg | Ulster | 12461 | G | 3024 | High Falls | N |  | 6.75 | [13 empty] | NM | N | 27 ENPHASE M250 | 2017-01-03 | 2017-01-03 | 0 | 2017-01-03 | [14 empty] | 2017-04-24 | 2017-04-25 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-00087 | Fishkill | Stormvl | Dutchess | 12582 | G | 8071 | Shenandoah | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE7600 | 2016-12-29 | 2016-12-29 | 0 | 2016-12-29 | [14 empty] | 2017-01-30 | 2017-01-31 |  | Y
Central Hudson |  | NRG Home Solar | CH-00491 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8091 | Fishkill Plains | N |  | 6.02 | [13 empty] | NM | N | 28 ENPHASE M215 | 2016-12-29 | 2016-12-29 | 0 | 2016-12-29 | [14 empty] | 2017-04-05 | 2017-04-06 |  | Y
Central Hudson |  | NRG Home Solar | CH-00542 | Newburgh |  |  | 12550 | G | 4014 | West Balmville | TBD |  | 3.01 | [13 empty] | NM | N | 14 ENPHASE M215 | 2016-12-29 | 2016-12-30 | 1 | 2016-12-30 | [17 empty] | W
Central Hudson |  | Monolith Solar Associates LLC | CH-02692 | Catskill | S Cairo | Greene | 12482 | G | 2005 | North Catskill | N | CH-02684 | 3 | [13 empty] | NM | N | SOLAREDGE SE3000 | 2016-12-30 | 2017-01-03 | 1 | 2017-01-03 | [14 empty] | 2017-02-07 | 2017-02-07 |  | Y
Central Hudson |  | SolarCity | CH-07249 | Kingston | Saugerties | Ulster | 12477 | G | 2015 | Lincoln Park | N |  | 5.2 | [13 empty] | NM | N | DELTA SOLIVIA 5.2 | 2016-12-29 | 2016-12-29 | 0 | 2016-12-29 | [14 empty] | 2017-01-19 | 2017-01-27 |  | Y
Central Hudson |  | Sungevity Inc | CH-09474 | Newburgh |  |  | 12550 | G | 4024 | Coldenham | TBD |  | 3.8 | [13 empty] | NM | N | SOLAREDGE SE3800 | 2017-01-04 | 2017-01-04 | 0 | 2017-01-04 | [17 empty] | W
Central Hudson |  | Trinity Solar | CH-08485 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6063 | Inwood Ave | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE7600 | 2016-12-30 | 2017-01-03 | 1 | 2017-01-03 | [14 empty] | 2017-03-16 | 2017-03-21 |  | Y
Central Hudson |  | American Solar Partners | CH-00008 | Newburgh | Cornwall | Orange | 12518 | G | 4041 | Union Ave | N |  | 10 | [13 empty] | NM | N | SOLAREDGE SE10000 | 2017-01-03 | 2017-01-03 | 0 | 2017-01-03 | [14 empty] | 2017-10-12 | 2017-10-13 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-00076 | Poughkeepsie | Lagrangeville | Dutchess | 12540 | G | 6055 | Todd Hill | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE7600 | 2017-01-03 | 2017-01-03 | 0 | 2017-01-03 | [8 empty] | 350 | 350 |  | 2017-01-27 | 2017-01-27 | 2017-02-06 | 2017-02-08 | 2017-02-08 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-00099 | Newburgh | New Paltz | Ulster | 12561 | G | 5031 | Galeville | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE7600 | 2017-01-03 | 2017-01-03 | 0 | 2017-01-03 | [14 empty] | 2017-02-27 | 2017-02-28 |  | Y
Central Hudson |  | Lotus Energy Inc. | CH-00341 | Poughkeepsie | Tivoli | Dutchess | 12583 | G | 7054 | Rhinebeck | N |  | 7.68 | [13 empty] | NM | N | 24 SUNPOWER SPR-X21-335 | 2017-01-03 | 2017-01-03 | 0 | 2017-01-03 | [14 empty] | 2017-02-03 | 2017-02-13 |  | Y
Central Hudson |  | SolarCity | CH-04984 | Catskill | Athens | Greene | 12015 | G | 1074 | Coxsackie | N |  | 16 | [13 empty] | NM | N | SOLAREDGE SE10000 SOLAREDGE SE6000 | 2017-01-03 | 2017-01-04 | 1 | 2017-01-04 | [14 empty] | 2017-01-25 | 2017-01-31 |  | Y
Central Hudson |  | SolarCity | CH-05130 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8024 | Knapps Corners | N |  | 6.6 | [13 empty] | NM | N | DELTA SOLIVA 6.6 | 2017-01-19 | 2017-01-19 | 0 | 2017-01-19 | [14 empty] | 2017-02-28 | 2017-03-03 |  | Y
Central Hudson |  | SolarCity | CH-05236 | Catskill | Freehold | Greene | 12431 | G | 2071 | Freehold | N |  | 10.4 | [13 empty] | NM | N | 2 DELTA SOLIVIA 5.2 | 2017-01-03 | 2017-01-03 | 0 | 2017-01-03 | [14 empty] | 2017-02-22 | 2017-02-27 |  | Y
Central Hudson |  | SolarCity | CH-07794 | Kingston | Ellenvl | Ulster | 12428 | G | 3078 | Greenfield Rd | N |  | 5.2 | [13 empty] | NM | N | DELTA SOLIVIA 5.2 | 2017-01-30 | 2017-01-30 | 0 | 2017-01-30 | [14 empty] | 2017-03-23 | 2017-03-24 |  | Y
Central Hudson |  | Trinity Solar | CH-08460 | Catskill | Oak Hill | Greene | 12460 | G | 1092 | Westerlo | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000 | 2017-01-03 | 2017-01-04 | 1 | 2017-01-04 | [14 empty] | 2017-01-25 | 2017-01-31 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-00201 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8043 | Myers Corners | N |  | 6 | [13 empty] | NM | N | SMA AMERICA SB6000 | 2017-01-04 | 2017-01-05 | 1 | 2017-01-05 | [14 empty] | 2017-03-02 | 2017-03-10 |  | Y
Central Hudson |  | New York State Solar Farm | CH-00369 | Newburgh | Gardiner | Ulster | 12525 | G | 5031 | Galeville | N |  | 23.04 | [13 empty] | NM | N | 72 SUNPOWER SPR-X21 345-C-AC | 2017-01-23 | 2017-01-23 | 0 | 2017-01-23 | [8 empty] | 350 | 350 |  | 2017-02-02 | 2017-02-02 | 2017-02-08 | 2017-02-06 | 2017-02-10 |  | Y
Central Hudson |  | American Energy Care | CH-00655 | Catskill | Berne | Albany | 12023 | G | 1092 | Westerlo | N |  | 10 | [13 empty] | NM | N | SOLAREDGE SE10000 | 2017-01-05 | 2017-01-05 | 0 | 2017-01-05 | [14 empty] | 2017-03-06 | 2017-03-10 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00949 | Poughkeepsie | Pine Plns | Dutchess | 12567 | G | 7091 | Pulvers Corners | N |  | 5 | [13 empty] | NM | N | 20 ENPHASE M250 | 2017-01-04 | 2017-01-05 | 1 | 2017-01-05 | [14 empty] | 2017-04-18 | 2017-04-18 |  | Y
Central Hudson |  | Direct Energy Solar | CH-01036 | Kingston | Saugerties | Ulster | 12477 | G | 3003 | Saugerties | N |  | 9.46 | [13 empty] | NM | N | 44 ENPHASE M215 | 2017-01-04 | 2017-01-05 | 1 | 2017-01-05 | [14 empty] | 2017-04-06 | 2017-04-10 |  | Y
Central Hudson |  | SolarCity | CH-05317 | Newburgh | Montgomery | Orange | 12549 | G | 5042 | East Walden | N |  | 15.2 | [13 empty] | NM | N | 2 DELTA SOLIVIA 7.6 | 2017-01-04 | 2017-01-04 | 0 | 2017-01-04 | [14 empty] | 2017-02-02 | 2017-03-03 |  | Y
Central Hudson |  | SolarCity | CH-06948 | Fishkill | Beacon | Dutchess | 12508 | G | 8087 | Tioronda | N |  | 3 | [13 empty] | NM | N | SOLAREDGE SE3000 | 2017-01-04 | 2017-01-04 | 0 | 2017-01-04 | [14 empty] | 2017-01-19 | 2017-01-19 |  | Y
Central Hudson |  | SolarCity | CH-07276 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6065 | Inwood Ave | N |  | 5.2 | [13 empty] | NM | N | DELTA SOLVIA 5.2 | 2017-01-04 | 2017-01-04 | 0 | 2017-01-04 | [14 empty] | 2017-03-17 | 2017-03-21 |  | Y
Central Hudson |  | SolarCity | CH-07736 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 6073 | East Park | N |  | 6.6 | [13 empty] | NM | N | DELTA SOLIVIA 6.6 | 2017-01-04 | 2017-01-05 | 1 | 2017-01-05 | [14 empty] | 2017-02-27 | 2017-03-13 |  | Y
Central Hudson |  | Trinity Solar | CH-08584 | Kingston |  |  | 12435 | G | 3096 | Grimley Rd | TBD |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE7600 | 2017-01-04 | 2017-01-05 | 1 | 2017-01-05 | [17 empty] | W
Central Hudson |  | You Save Green | CH-09968 | Newburgh |  |  | 12589 | G | 4011 | West Balmville | TBD |  | 1980 | [13 empty] | RNM | N | 33 SUNGROW SG-60KU-M | 2017-02-10 | 2017-02-14 | 2 | 2017-02-14 | 2017-02-14 | 2017-03-03 | 12 |  |  |  |  | 35000 | [9 empty] | W
Central Hudson |  | Infinity Solar Systems | CH-00179 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8092 | Fishkill Plains | N |  | 4 | [13 empty] | NM | N | 16 ENPHASE M250 | 2017-01-05 | 2017-01-06 | 1 | 2017-01-06 | [14 empty] | 2017-03-30 | 2017-04-12 |  | Y
Central Hudson |  | Lotus Energy Inc. | CH-00340 | Kingston | Saugerties | Ulster | 12477 | G | 3014 | Woodstock | N |  | 14.72 | [13 empty] | NM | N | (46) SUNPOWER SPR-X21-335 | 2017-01-06 | 2017-01-20 | 10 | 2017-01-20 | [8 empty] | 350 | 350 |  | 2017-02-03 | 2017-02-03 | 2017-04-17 | 2017-04-17 | 2017-04-18 |  | Y
Central Hudson |  | New York State Solar Farm | CH-00430 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8095 | Fishkill Plains | N |  | 13.12 | [13 empty] | NM | N | 41 SUNPOWER SPR-E20 327-C-AC | 2017-01-18 | 2017-01-18 | 0 | 2017-01-18 | [14 empty] | 2017-03-01 | 2017-03-01 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00828 | Newburgh | New Paltz | Ulster | 12561 | G | 5023 | Ohioville | N |  | 11.61 | [13 empty] | NM | N | 54 ENPHASE M215 | 2017-01-05 | 2017-01-06 | 1 | 2017-01-06 | [14 empty] | 2017-02-02 | 2017-02-10 |  | Y
Central Hudson |  | SolarCity | CH-07013 | Newburgh | Newburgh | Orange | 12550 | G | 4051 | Union Ave | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A | 2017-01-05 | 2017-01-06 | 1 | 2017-01-06 | [14 empty] | 2017-01-25 | 2017-02-06 |  | Y
Central Hudson |  | SolarCity | CH-07367 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8014 | Forgebrook | N |  | 7.6 | [13 empty] | NM | N | DELTA SOLIVIA 7.6 | 2017-01-06 | 2017-01-06 | 0 | 2017-01-06 | [14 empty] | 2017-02-28 | 2017-02-28 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08698 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8045 | Myers Corners | N |  | 5.37 | [13 empty] | NM | N | 25 ENPHASE M215 | 2017-01-20 | 2017-01-20 | 0 | 2017-01-20 | [14 empty] | 2017-05-19 | 2017-05-19 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-00218 | Newburgh | Salisbury Mls | Orange | 12577 | G | 4097 | Bethlehem Rd | N |  | 5.76 | [13 empty] | NM | N | 18 SUNPOWER SPR-X21-335-BLK | 2017-01-09 | 2017-01-10 | 1 | 2017-01-10 | [14 empty] | 2017-03-16 | 2017-04-07 |  | Y
Central Hudson |  | Solar Liberty Energy Systems | CH-04909 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8046 | Myers Corners | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE 7.6 | 2017-01-11 | 2017-01-12 | 1 | 2017-01-12 | [14 empty] | 2017-05-23 | 2017-05-24 |  | Y
Central Hudson |  | Trinity Solar | CH-08441 | Fishkill | Stormvl | Dutchess | 12582 | G | 8071 | Shenandoah | N |  | 10 | [13 empty] | NM | N | SOLAREDGE SE10000 | 2017-01-09 | 2017-01-09 | 0 | 2017-01-09 | [14 empty] | 2017-05-01 | 2017-05-02 |  | Y
Central Hudson |  | NRG Home Solar | CH-00507 | Poughkeepsie | Hyde Pk |  | 12538 | G | 6074 | East Park | N |  | 6.02 | [13 empty] | NM | N | 28 ENPHASE M215 | 2017-01-10 | 2017-01-10 | 0 | 2017-01-10 | [17 empty] | W
Central Hudson |  | Mannino Electric | CH-02608 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7054 | Rhinebeck | N |  | 3 | [13 empty] | NM | N | SOLAREDGE SE3000A | 2017-01-10 | 2017-01-10 | 0 | 2017-01-10 | [14 empty] | 2017-03-23 | 2017-03-24 |  | Y
Central Hudson |  | SolarCity | CH-05225 | Newburgh |  |  | 12550 | G | 5004 | Marlboro | TBD |  | 7.6 | [13 empty] | NM | N | DELTA SOLIVIA 7.6 | 2017-01-10 | 2017-01-10 | 0 | 2017-01-10 | [17 empty] | W
Central Hudson |  | SolarCity | CH-05746 | Kingston | Kingston | Ulster | 12401 | G | 2016 | Lincoln Park | N |  | 3.8 | [13 empty] | NM | N | SOLAREDGE SE3800A-US | 2017-01-10 | 2017-01-10 | 0 | 2017-01-10 | [14 empty] | 2017-03-13 | 2017-03-13 |  | Y
Central Hudson |  | SolarCity | CH-06141 | Fishkill | Beacon | Dutchess | 12508 | G | 8017 | Forgebrook | N |  | 6.6 | [13 empty] | NM | N | DELTA SOLIVIA 6.6 | 2017-01-10 | 2017-01-10 | 0 | 2017-01-10 | [14 empty] | 2017-02-22 | 2017-02-22 |  | Y
Central Hudson |  | SolarCity | CH-07451 | Newburgh | Newburgh | Orange | 12550 | G | 4012 | West Balmville | N |  | 9 | [13 empty] | NM | N | DELTA SOLIVIA 5.2 DELTA SOLIVIA 3.8 | 2017-01-10 | 2017-01-10 | 0 | 2017-01-10 | [14 empty] | 2017-03-29 | 2017-03-30 |  | Y
Central Hudson |  | Solar Maximum LLC, dba RevoluSun | CH-09033 | Newburgh | Campbell Hall | Orange | 10916 | G | 5052 | Maybrook | N |  | 11.52 | [13 empty] | NM | N | 36 SUNPOWER SPR X22 | 2017-01-13 | 2017-01-13 | 0 | 2017-01-13 | [14 empty] | 2017-03-21 | 2017-03-29 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00983 | Kingston | Tillson | Ulster | 12486 | G | 3022 | High Falls | N |  | 14.5 | [13 empty] | NM | N | 58 ENPHASE M250 | 2017-01-11 | 2017-01-12 | 1 | 2017-01-12 | [14 empty] | 2017-02-02 | 2017-02-08 |  | Y
Central Hudson |  | Hudson Solar | CH-02167 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8052 | North Chelsea | N |  | 8 | [13 empty] | NM | N | SOALREDGE SE5000 SOLAREDGE SE3000 | 2017-01-11 | 2017-01-12 | 1 | 2017-01-12 | [14 empty] | 2017-03-30 | 2017-03-30 |  | Y
Central Hudson |  | Trinity Solar | CH-08410 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6003 | Reynolds Hill | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000 | 2017-01-11 | 2017-01-12 | 1 | 2017-01-12 | [14 empty] | 2017-03-16 | 2017-03-22 |  | Y
Central Hudson |  | Trinity Solar | CH-08475 | Kingston | Napanoch | Ulster | 12458 | G | 3091 | Neversink | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE7600A | 2017-01-11 | 2017-01-26 | 11 | 2017-01-26 | [14 empty] | 2017-02-22 | 2017-02-22 |  | Y
Central Hudson |  | Hudson Solar | CH-01275 | Newburgh | West Park | Ulster | 12493 | G | 5084 | Highland | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE7600 | 2017-01-12 | 2017-01-13 | 1 | 2017-01-13 | [14 empty] | 2017-05-31 | 2017-06-06 |  | Y
Central Hudson |  | Hudson Solar | CH-01490 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7052 | Rhinebeck | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000 | 2017-01-12 | 2017-01-12 | 0 | 2017-01-12 | [14 empty] | 2017-03-06 | 2017-03-10 |  | Y
Central Hudson |  | Hudson Solar | CH-01581 | Fishkill | Beacon | Dutchess | 12508 | G | 8017 | Forgebrook | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000 | 2017-01-12 | 2017-01-13 | 1 | 2017-01-13 | [14 empty] | 2017-03-17 | 2017-03-21 |  | Y
Central Hudson |  | Hudson Solar | CH-01784 | Poughkeepsie | Lagrangeville | Dutchess | 12540 | G | 6053 | Todd Hill | N |  | 3.8 | [13 empty] | NM | N | SOLAREDGE SE3800 | 2017-01-12 | 2017-01-12 | 0 | 2017-01-12 | [14 empty] | 2017-03-03 | 2017-03-10 |  | Y
Central Hudson |  | Hudson Solar | CH-02476 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8092 | Fishkill Plains | N | CH-01915 | 7.4 | [13 empty] | NM | N | 23 SunPower SPR-E20-327-C-AC (208V) | 2017-01-12 | 2017-01-12 | 0 | 2017-01-12 | [14 empty] | 2017-12-19 | 2017-12-19 |  | Y
Central Hudson |  | SolarCity | CH-05663 | Kingston | Kingston | Ulster | 12401 | G | 1024 | East Kingston | N |  | 5.2 | [13 empty] | NM | N | DELTA 5.2 | 2017-02-14 | 2017-02-14 | 0 | 2017-02-14 | [14 empty] | 2017-02-24 | 2017-03-01 |  | Y
Central Hudson |  | SolarCity | CH-06011 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8091 | Fishkill Plains | N |  | 10.4 | [13 empty] | NM | N | DELTA SOLIVIA 3.8 DELTA SOLIVIA 6.6 | 2017-01-12 | 2017-01-13 | 1 | 2017-01-13 | [14 empty] | 2017-02-15 | 2017-02-15 |  | Y
Central Hudson |  | SolarCity | CH-06282 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 7.6 | [13 empty] | NM | N | DELTA SOLIVIA 7.6 | 2017-01-12 | 2017-01-12 | 0 | 2017-01-12 | [14 empty] | 2017-02-09 | 2017-02-13 |  | Y
Central Hudson |  | SolarCity | CH-06309 | Newburgh | Newburgh | Orange | 12550 | G | 4011 | West Balmville | N |  | 9 | [13 empty] | NM | N | DELTA SOLIVIA 3.8 DELTA SOLIVIA 5.2 | 2017-01-12 | 2017-01-12 | 0 | 2017-01-12 | [14 empty] | 2017-11-27 | 2017-11-27 |  | Y
Central Hudson |  | SolarCity | CH-07582 | Fishkill | Stormvl |  | 12582 | G | 8071 | Shenandoah | N |  | 7.6 | [13 empty] | NM | N | DELTA SOLIVIA 7.6 | 2017-01-12 | 2017-01-12 | 0 | 2017-01-12 | [14 empty] | 2017-02-03 | 2017-02-10 |  | W |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07748 | Newburgh |  |  | 12553 | G | 4044 | Union Ave | TBD |  | 5.2 | [13 empty] | NM | N | DELTA SOLIVIA 5.2 | 2017-01-12 | 2017-01-13 | 1 | 2017-01-13 | [14 empty] | 2017-03-30 | 2017-03-30 |  | W
Central Hudson |  | SolarCity | CH-05107 | Poughkeepsie | Millerton | Dutchess | 12546 | G | 7081 | Millerton | N |  | 5.2 | [13 empty] | NM | N | DELTA SOLIVIA 5.2 | 2017-05-11 | 2017-05-12 | 1 | 2017-05-12 | [14 empty] | 2017-07-11 | 2017-07-20 |  | Y
Central Hudson |  | New York State Solar Farm | CH-00399 | Fishkill | Beacon | Dutchess | 12508 | G | 8087 | Tioronda | N |  | 8.96 | [13 empty] | NM | N | 28 SUNPOWER SPR-X22 360-C-AC | 2017-01-23 | 2017-01-23 | 0 | 2017-01-23 | [14 empty] | 2017-03-09 | 2017-03-10 |  | Y
Central Hudson |  | SolarCity | CH-05377 | Newburgh | Highland | Ulster | 12528 | G | 5084 | Highland | N |  | 5.2 | [13 empty] | NM | N | DELTA SOLIVIA 5.2 | 2017-01-23 | 2017-01-23 | 0 | 2017-01-23 | [14 empty] | 2017-03-03 | 2017-03-10 |  | Y
Central Hudson |  | SolarCity | CH-06548 | Kingston | Kingston | Ulster | 12401 | G | 1013 | Boulevard | N |  | 3 | [13 empty] | NM | N | SOLAREDGE SE3000A | 2017-01-16 | 2017-01-16 | 0 | 2017-01-16 | [14 empty] | 2017-01-25 | 2017-01-31 |  | Y
Central Hudson |  | SolarCity | CH-07007 | Newburgh | Newburgh | Orange | 12550 | G | 4014 | West Balmville | N |  | 6.6 | [13 empty] | NM | N | DELTA SOLIVIA 6.6 | 2017-01-23 | 2017-01-23 | 0 | 2017-01-23 | [14 empty] | 2017-03-16 | 2017-03-21 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-00035 | Kingston | Kerhonkson | Ulster | 12446 | G | 3082 | Kerhonkson | N |  | 15.2 | [13 empty] | NM | N | (2) SOLAREDGE SE7600 | 2017-01-17 | 2017-01-17 | 0 | 2017-01-17 | [8 empty] | 350 | 350 |  | 2017-01-30 | 2017-01-30 | 2017-04-13 | 2017-04-13 | 2017-04-17 |  | Y
Central Hudson |  | Solar Liberty Energy Systems | CH-04910 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8092 | Fishkill Plains | N |  | 10 | [13 empty] | NM | N | SOLAREDGE 10000 | 2017-01-18 | 2017-01-19 | 1 | 2017-01-19 | [14 empty] | 2017-06-26 | 2017-06-26 |  | Y
Central Hudson |  | SolarCity | CH-06625 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6011 | Sand Dock | N |  | 6.6 | [13 empty] | NM | N | DELTA SOLIVIA 6.6 | 2017-01-17 | 2017-01-18 | 1 | 2017-01-18 | [14 empty] | 2017-03-13 | 2017-03-15 |  | Y
Central Hudson |  | SolarCity | CH-07106 | Newburgh |  |  | 10930 | G | 4093 | Bethlehem Rd | TBD |  | 6.6 | [13 empty] | NM | N | DELTA SOLIVIA 6.6 | 2017-01-23 | 2017-01-23 | 0 | 2017-01-23 | [17 empty] | W
Central Hudson |  | Solar Generation | CH-08294 | Kingston | Saugerties | Ulster | 12477 | G | 3003 | Saugerties | N | CH-08294 | 6.72 | [13 empty] | NM | N | 21 SUNPOWER X22-360-C | 2017-01-17 | 2017-01-17 | 0 | 2017-01-17 | [14 empty] | 2017-03-07 | 2017-03-10 |  | Y
Central Hudson |  | Hudson Solar | CH-02505 | Newburgh | Marlboro | Ulster | 12542 | G | 5003 | Marlboro | N | CH-01384 | 4.55 | [13 empty] | NM | N | SMA AMERICA SB-5000 | 2017-01-27 | 2017-02-07 | 7 | 2017-02-07 | [14 empty] | 2017-03-31 | 2017-04-04 |  | Y
Central Hudson |  | Murphy Solar Power | CH-02739 | Catskill | Freehold | Greene | 12431 | G | 2061 | Freehold | N |  | 5 | [13 empty] | NM | N | SMA 5000 SB | 2017-01-18 | 2017-01-18 | 0 | 2017-01-18 | [17 empty] | W
Central Hudson |  | SolarCity | CH-05051 | Fishkill | Hopewell Junction | Dutchess | 12533 | G | 8093 | Fishkill Plains | N |  | 7.6 | [13 empty] | NM | N | DELTA SOLIVIA 7.6 | 2017-01-18 | 2017-01-18 | 0 | 2017-01-18 | [14 empty] | 2017-02-17 | 2017-02-17 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-05076 | Newburgh | Milton | Ulster | 12547 | G | 5083 | Highland | N |  | 10.4 | [13 empty] | NM | N | 2 DELTA SOLIVIA 5.2 | 2017-01-18 | 2017-01-18 | 0 | 2017-01-18 | [8 empty] | 350 | 350 |  | 2017-02-17 | 2017-02-17 | 2017-03-06 | 2017-03-06 | 2017-03-10 |  | Y
Central Hudson |  | SolarCity | CH-05698 | Kingston | Kingston | Ulster | 12401 | G | 1013 | Boulevard | N |  | 3 | [13 empty] | NM | N | SOLAREDGE SE3000 | 2017-01-18 | 2017-01-19 | 1 | 2017-01-19 | [14 empty] | 2017-03-13 | 2017-03-13 |  | Y
Central Hudson |  | SolarCity | CH-05729 | Kingston | Saugerties | Ulster | 12477 | G | 3004 | Saugerties | N |  | 10.4 | [13 empty] | NM | N | 2 DELTA SOLIVIA 5.2 | 2017-01-18 | 2017-01-18 | 0 | 2017-01-18 | [14 empty] | 2017-02-09 | 2017-02-13 |  | Y
Central Hudson |  | SolarCity | CH-06262 | Newburgh | New Windsor | Orange | 12553 | G | 4045 | Union Ave | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A | 2017-01-18 | 2017-01-18 | 0 | 2017-01-18 | [14 empty] | 2017-02-27 | 2017-03-10 |  | Y
Central Hudson |  | SolarCity | CH-06293 | Newburgh | Plattekill | Ulster | 12568 | G | 5013 | Modena | N |  | 6.6 | [13 empty] | NM | N | DELTA SOLIVIA 6.6 | 2017-01-18 | 2017-02-01 | 10 | 2017-02-01 | [14 empty] | 2017-05-24 | 2017-05-25 |  | Y
Central Hudson |  | SolarCity | CH-07029 | Newburgh | Newburgh | Orange | 12550 | G | 4052 | Union Ave | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000 | 2017-01-18 | 2017-01-18 | 0 | 2017-01-18 | [14 empty] | 2017-02-22 | 2017-02-22 |  | Y
Central Hudson |  | Solar Generation | CH-08063 | Kingston | Kerhonkson | Ulster | 12446 | G | 3082 | Kerhonkson | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A | 2017-01-18 | 2017-01-19 | 1 | 2017-01-19 | [14 empty] | 2017-01-23 | 2017-01-31 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Hudson Solar | CH-02052 | Kingston | Saugerties | Ulster | 12477 | G | 3003 | Saugerties | N |  | 11.4 | [13 empty] | NM | N | SOLAREDGE SE11400 | 2017-01-19 | 2017-01-20 | 1 | 2017-01-20 | [14 empty] | 2017-03-20 | 2017-03-23 |  | Y
Central Hudson |  | Paradise Energy Solutions LLC | CH-02827 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6097 | Manchester | N |  | 109.9 | [13 empty] | NM | N | 3 SOLAREDGE 33.3K SOLAREDGE 10K3SolaredgeSE33.3KUS1SolaredgeSE 10000A-US (277V) | 2017-03-03 | 2017-03-06 | 1 | 2017-03-06 | 2017-03-06 | 2017-03-27 | 15 | [11 empty] | 2018-01-29 | 2018-01-29 |  | Y
Central Hudson |  | SolarCity | CH-05128 | Newburgh | Highland | Ulster | 12528 | G | 5083 | Highland | N |  | 6.6 | [13 empty] | NM | N | DELTA SOLIVIA 6.6 | 2017-01-19 | 2017-01-20 | 1 | 2017-01-20 | [14 empty] | 2017-02-28 | 2017-03-03 |  | Y
Central Hudson |  | SolarCity | CH-07611 | Newburgh | Wallkill | Ulster | 12589 | G | 5012 | Modena | N |  | 7.6 | [13 empty] | NM | N | DELTA SOLIVIA 7.6 | 2017-01-20 | 2017-01-20 | 0 | 2017-01-20 | [14 empty] | 2017-03-28 | 2017-03-28 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-00195 | Newburgh | Rock Tvrn | Orange | 12575 | G | 4097 | Bethlehem Rd | N |  | 8.32 | [13 empty] | NM | N | 26 SUNPOWER SPR-E20-327 | 2017-01-23 | 2017-01-23 | 0 | 2017-01-23 | [14 empty] | 2017-03-02 | 2017-03-28 |  | Y
Central Hudson |  | SolarCity | CH-04960 | Newburgh | Campbell Hall | Orange | 10916 | G | 5051 | Maybrook | N |  | 6.6 | [13 empty] | NM | N | DELTA SOLIVIA 6.6 | 2017-01-23 | 2017-01-23 | 0 | 2017-01-23 | [14 empty] | 2017-04-21 | 2017-05-01 |  | Y
Central Hudson |  | SolarCity | CH-05855 | Poughkeepsie | Staatsburg | Dutchess | 12580 | G | 7041 | Staatsburg | N |  | 11.4 | [13 empty] | NM | N | DELTA SOLIVIA 3.8 DELTA SOLIVIA 7.6 | 2017-01-23 | 2017-01-23 | 0 | 2017-01-23 | [14 empty] | 2017-02-14 | 2017-02-17 |  | Y
Central Hudson |  | SolarCity | CH-06211 | Newburgh | Newburgh | Orange | 12550 | G | 4022 | Coldenham | N |  | 13.2 | [13 empty] | NM | N | 2 DELTA SOLIVIA 6.6 | 2017-01-23 | 2017-01-23 | 0 | 2017-01-23 | [8 empty] | 350 | 350 |  | 2017-02-17 | 2017-02-17 | 2017-02-24 | 2017-04-10 | 2017-04-10 |  | Y
Central Hudson |  | SolarCity | CH-06651 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6091 | Manchester | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE 5000 | 2017-01-23 | 2017-01-24 | 1 | 2017-01-24 | [14 empty] | 2017-03-28 | 2017-03-31 |  | Y
Central Hudson |  | SolarCity | CH-07409 | Newburgh | New Paltz | Ulster | 12561 | G | 5021 | Ohioville | N | CH-07409 | 6.6 | [13 empty] | NM | N | DELTA SOLIVIA 6.6 | 2017-01-23 | 2017-01-23 | 0 | 2017-01-23 | [14 empty] | 2017-02-24 | 2017-02-24 |  | Y
Central Hudson |  | SolarCity | CH-07521 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6011 | Sand Dock | N |  | 6.6 | [13 empty] | NM | N | DELTA SOLIVIA 6.6 | 2017-01-23 | 2017-01-24 | 1 | 2017-01-24 | [14 empty] | 2017-03-17 | 2017-03-23 |  | Y
Central Hudson |  | Trinity Solar | CH-08535 | Poughkeepsie | Staatsburg | Dutchess | 12580 | G | 7041 | Staatsburg | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A | 2017-01-23 | 2017-01-23 | 0 | 2017-01-23 | [14 empty] | 2017-04-03 | 2017-04-04 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08719 | Newburgh | New Windsor | Orange | 12553 | G | 4043 | Union Ave | N |  | 7.52 | [13 empty] | NM | N | 35 ENPHASE M215 | 2017-01-23 | 2017-01-23 | 0 | 2017-01-23 | [14 empty] | 2017-06-06 | 2017-06-08 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-00151 | Fishkill | Fishkill | Dutchess | 12524 | G | 8094 | Fishkill Plains | N |  | 3 | [13 empty] | NM | N | 12 ENPHASE M250 | 2017-01-25 | 2017-01-25 | 0 | 2017-01-25 | [14 empty] | 2017-04-28 | 2017-04-28 |  | Y
Central Hudson |  | SolarCity | CH-07704 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6073 | East Park | N |  | 6.6 | [13 empty] | NM | N | DELTA SOLIVIA 6.6 | 2017-01-24 | 2017-01-24 | 0 | 2017-01-24 | [14 empty] | 2017-03-07 | 2017-03-10 |  | Y
Central Hudson |  | SolarCity | CH-07796 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6008 | Reynolds Hill | N |  | 3.8 | [13 empty] | NM | N | DELTA SOLIVIA 3.8 | 2017-01-24 | 2017-01-24 | 0 | 2017-01-24 | [14 empty] | 2017-03-21 | 2017-03-24 |  | Y
Central Hudson |  | Trinity Solar | CH-08556 | Kingston | Ellenvl | Ulster | 12428 | G | 3076 | Greenfield Rd | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE7600 | 2017-01-24 | 2017-01-24 | 0 | 2017-01-24 | [14 empty] | 2017-03-16 | 2017-03-21 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08609 | Fishkill |  |  | 12590 | G | 8043 | Myers Corners | TBD |  | 9.24 | [13 empty] | NM | N | 43 ENPHASE M215 | 2017-01-24 | 2017-01-24 | 0 | 2017-01-24 | [17 empty] | W
Central Hudson |  | Hudson Solar | CH-01643 | Catskill | Greenvl | Greene | 12083 | G | 1091 | Westerlo | N |  | 60 | [13 empty] | NM | N | 6 SOLAREDGE SE10000 | 2017-01-26 | 2017-02-07 | 8 | 2017-02-07 | [8 empty] | 10000 | 3401.46 |  | 2017-02-27 | 2017-02-27 | 2017-04-07 | 2017-07-06 | 2017-07-10 |  | Y
Central Hudson |  | SolarCity | CH-05206 | Newburgh | Newburgh | Orange | 12550 | G | 4051 | Union Ave | N |  | 6.6 | [13 empty] | NM | N | DELTA SOLIVIA 6.6 | 2017-02-15 | 2017-02-15 | 0 | 2017-02-15 | [14 empty] | 2017-04-13 | 2017-04-13 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08759 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8043 | Myers Corners | N |  | 7.95 | [13 empty] | NM | N | 37 ENPHASE M215 | 2017-01-25 | 2017-01-25 | 0 | 2017-01-25 | [14 empty] | 2017-06-06 | 2017-06-08 |  | Y
Central Hudson |  | Solar Generation | CH-08123 | Kingston | Stone Ridge | Ulster | 12484 | G | 3023 | High Falls | N |  | 6 | [13 empty] | NM | N | SOLAREDGE 6000A | 2017-01-26 | 2017-01-26 | 0 | 2017-01-26 | [14 empty] | 2017-03-28 | 2017-03-28 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08687 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8043 | Myers Corners | N |  | 4.73 | [13 empty] | NM | N | 22 ENPHASE M215 | 2017-01-26 | 2017-01-27 | 1 | 2017-01-27 | [14 empty] | 2017-06-07 | 2017-06-08 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08701 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8072 | Shenandoah | N |  | 8.17 | [13 empty] | NM | N | 38 ENPHASE M215 | 2017-01-26 | 2017-01-26 | 0 | 2017-01-26 | [14 empty] | 2017-06-01 | 2017-06-07 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-00165 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 6073 | East Park | N |  | 4.25 | [13 empty] | NM | N | 17 ENPHASE M250 | 2017-01-27 | 2017-01-27 | 0 | 2017-01-27 | [14 empty] | 2017-03-30 | 2017-04-07 |  | Y
Central Hudson |  | Lighthouse Solar | CH-00278 | Newburgh | New Paltz | Ulster | 12561 | G | 5024 | Ohioville | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE 7600 | 2017-01-27 | 2017-01-27 | 0 | 2017-01-27 | [14 empty] | 2017-02-10 | 2017-02-22 |  | Y
Central Hudson |  | SolarCity | CH-07316 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6092 | Manchester | N |  | 7.6 | [13 empty] | NM | N | DELTA SOLIVIA 7.6 | 2017-01-27 | 2017-01-27 | 0 | 2017-01-27 | [14 empty] | 2017-03-24 | 2017-03-27 |  | Y
Central Hudson |  | SolarCity | CH-05970 | Poughkeepsie | Ancramdale | Columbia | 12503 | G | 7085 | Ancram | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000 | 2017-01-30 | 2017-01-30 | 0 | 2017-01-30 | [14 empty] | 2017-04-25 | 2017-05-01 |  | Y
Central Hudson |  | SolarCity | CH-06186 | Newburgh | Clintondale | Ulster | 12515 | G | 5012 | Modena | N |  | 6.6 | [13 empty] | NM | N | DELTA SOLIVIA 6.6 | 2017-01-30 | 2017-01-30 | 0 | 2017-01-30 | [14 empty] | 2017-04-19 | 2017-04-19 |  | Y
Central Hudson |  | SolarCity | CH-06807 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8043 | Myers Corners | N |  | 3.8 | [13 empty] | NM | N | DELTA SOLIVIA 3.8 | 2017-01-30 | 2017-01-30 | 0 | 2017-01-30 | [14 empty] | 2017-04-17 | 2017-04-17 |  | Y
Central Hudson |  | Sungevity Inc | CH-09482 | Newburgh |  |  | 12550 | G | 4052 | Union Ave | TBD |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000 | 2017-01-30 | 2017-01-30 | 0 | 2017-01-30 | [17 empty] | W
Central Hudson |  | Green Street Power Partners, LLC | CH-00119 | Newburgh | Mountainvl | Orange | 12518 | G | 4041 | Union Ave | N |  | 8.32 | [13 empty] | NM | N | 26 SUNPOWER SPR X21 345 C-AC | 2017-01-31 | 2017-01-31 | 0 | 2017-01-31 | [14 empty] | 2017-03-24 | 2017-03-27 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Infinity Solar Systems | CH-00126 | Newburgh | Newburgh | Orange | 12550 | G | 4023 | Coldenham | N |  | 4 | [13 empty] | NM | N | 16 ENPHASE M250 | 2017-02-01 | 2017-02-06 | 3 | 2017-02-06 | [14 empty] | 2017-04-13 | 2017-04-17 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-00194 | Newburgh | Wallkill | Ulster | 12589 | G | 5011 | Modena | N |  | 10 | [13 empty] | NM | N | 40 ENPHASE M250 | 2017-01-31 | 2017-02-06 | 4 | 2017-02-06 | [14 empty] | 2017-05-03 | 2017-05-03 |  | Y
Central Hudson |  | Revolution Solar | CH-02984 | Catskill |  |  | 12083 | G | 2061 | Freehold | TBD |  | 2.5 | [13 empty] | NM | N | 10 ENPHASE M250 | 2017-01-31 | 2017-01-31 | 0 | 2017-01-31 | [17 empty] | W
Central Hudson |  | SolarCity | CH-05240 | Kingston | Olive Brdg | Ulster | 12461 | G | 3082 | Kerhonkson | N |  | 5.2 | [13 empty] | NM | N | DELTA 5.2 | 2017-01-31 | 2017-02-01 | 1 | 2017-02-01 | [14 empty] | 2017-04-13 | 2017-04-13 |  | Y
Central Hudson |  | SolarCity | CH-06930 | Fishkill | Beacon | Dutchess | 12508 | G | 8017 | Forgebrook | N |  | 5.2 | [13 empty] | NM | N | DELTA SOLIVIA 5.2 | 2017-01-31 | 2017-01-31 | 0 | 2017-01-31 | [14 empty] | 2017-02-16 | 2017-02-24 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Trinity Solar | CH-08563 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8044 | Myers Corners | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000 | 2017-01-31 | 2017-02-01 | 1 | 2017-02-01 | [14 empty] | 2017-04-17 | 2017-04-17 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08608 | Poughkeepsie |  |  | 12571 | G | 7061 | Milan | TBD |  | 2.58 | [13 empty] | NM | N | 12 ENPASE M215 | 2017-01-31 | 2017-01-31 | 0 | 2017-01-31 | [17 empty] | W
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08809 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8094 | Fishkill Plains | N |  | 9.03 | [13 empty] | NM | N | 41 ENPHASE M215 | 2017-02-03 | 2017-02-03 | 0 | 2017-02-03 | [14 empty] | 2017-05-09 | 2017-05-09 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-00171 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8094 | Fishkill Plains | N |  | 6.4 | [13 empty] | NM | N | 20 SUNPOWER SPR-X21-335-BLK | 2017-02-02 | 2017-02-02 | 0 | 2017-02-02 | [14 empty] | 2017-05-17 | 2017-05-18 |  | Y
Central Hudson |  | Kasselman Solar | CH-00240 | Catskill |  |  | 12042 | G | 1071 | Coxsackie | TBD |  | 4 | [13 empty] | NM | N | 16 ENPHASE M250 | 2017-02-02 | 2017-02-02 | 0 | 2017-02-02 | [17 empty] | W
Central Hudson |  | Hudson Solar | CH-01369 | Catskill | Preston Holw | Albany | 12469 | G | 1092 | Westerlo | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600A-US (240V) | 2017-02-02 | 2017-02-07 | 3 | 2017-02-07 | [14 empty] | 2018-01-24 | 2018-02-01 |  | Y
Central Hudson |  | Hudson Solar | CH-01713 | Kingston | Saugerties | Ulster | 12477 | G | 3003 | Saugerties | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE7600 | 2017-02-02 | 2017-02-03 | 1 | 2017-02-03 | [14 empty] | 2017-05-22 | 2017-05-22 |  | Y
Central Hudson |  | NRG Home Solar | CH-00498 | Kingston | Stone Ridge |  | 12484 | G | 3023 | High Falls | N |  | 3 | [13 empty] | NM | N | 12 ENPHASE M250 | 2017-02-06 | 2017-02-06 | 0 | 2017-02-06 | [17 empty] | W
Central Hudson |  | SolarCity | CH-06125 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8071 | Shenandoah | N |  | 10 | [13 empty] | NM | N | SOLAREDGE SE10000 | 2017-02-22 | 2017-02-22 | 0 | 2017-02-22 | [8 empty] | 350 | 350 |  | 2017-03-23 | 2017-03-23 | 2017-04-10 | 2017-04-10 | 2017-04-12 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | New York State Solar Farm | CH-00357 | Newburgh | Marlboro | Ulster | 12542 | G | 5004 | Marlboro | N |  | 8.96 | [13 empty] | NM | N | 28 SUNPOWER SPR-X22 360-C-AC | 2017-02-06 | 2017-02-06 | 0 | 2017-02-06 | [14 empty] | 2017-03-24 | 2017-03-24 |  | Y
Central Hudson |  | NRG Home Solar | CH-00525 | Kingston | Hurley |  | 12443 | G | 2094 | Hurley Ave | N |  | 14.25 | [13 empty] | NM | N | 57 ENPHASE M250 | 2017-02-06 | 2017-02-06 | 0 | 2017-02-06 | [17 empty] | W
Central Hudson |  | SolarCity | CH-06248 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 5.2 | [13 empty] | NM | N | DELTA SOLIVIA 5.2 | 2017-02-06 | 2017-02-06 | 0 | 2017-02-06 | [14 empty] | 2017-04-17 | 2017-04-25 |  | Y
Central Hudson |  | SolarCity | CH-06411 | Newburgh | Montgomery | Orange | 12549 | G | 5073 | Montgomery | N |  | 6 | [13 empty] | NM | N | Solar Edge SE6000A | 2017-02-06 | 2017-02-06 | 0 | 2017-02-06 | [14 empty] | 2017-03-20 | 2017-03-23 |  | Y
Central Hudson |  | SolarCity | CH-06527 | Kingston | Kingston | Ulster | 12401 | G | 1022 | East Kingston | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000 | 2017-02-06 | 2017-02-07 | 1 | 2017-02-07 | [14 empty] | 2017-02-28 | 2017-02-28 |  | Y
Central Hudson |  | SolarCity | CH-07155 | Newburgh | Maybrook | Orange | 12543 | G | 5052 | Maybrook | N |  | 9 | [13 empty] | NM | N | SOLAREDGE SE6 SOLAREDGE SE3 | 2017-02-06 | 2017-02-06 | 0 | 2017-02-06 | [14 empty] | 2017-03-14 | 2017-03-17 |  | Y
Central Hudson |  | Trinity Solar | CH-08518 | Newburgh | New Windsor | Orange | 12553 | G | 4095 | Bethlehem Rd | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE7600 | 2017-02-06 | 2017-02-06 | 0 | 2017-02-06 | [14 empty] | 2017-03-23 | 2017-03-24 |  | Y
Central Hudson |  | Trinity Solar | CH-08544 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8072 | Shenandoah | N |  | 3 | [13 empty] | NM | N | SOLAREDGE SE3000 | 2017-02-06 | 2017-02-06 | 0 | 2017-02-06 | [14 empty] | 2017-05-16 | 2017-05-19 |  | Y
Central Hudson |  | Trinity Solar | CH-08595 | Fishkill |  |  | 12533 | G | 8093 | Fishkill Plains | TBD |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000 | 2017-02-06 | 2017-02-06 | 0 | 2017-02-06 | [17 empty] | W
Central Hudson |  | SolarCity | CH-06037 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8046 | Myers Corners | N |  | 7.6 | [13 empty] | NM | N | DELTA SOLIVIA 7.6 | 2017-02-07 | 2017-02-07 | 0 | 2017-02-07 | [14 empty] | 2017-04-24 | 2017-04-24 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-06572 | Kingston | Saugerties | Ulster | 12477 | G | 3002 | Saugerties | N |  | 10.4 | [13 empty] | NM | N | DELTA SOLIVIA 3.8 DELTA SOLIVIA 6.6 | 2017-02-07 | 2017-02-07 | 0 | 2017-02-07 | [14 empty] | 2017-03-24 | 2017-03-27 |  | Y
Central Hudson |  | SolarCity | CH-06833 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8046 | Myers Corners | N |  | 11.4 | [13 empty] | NM | N | DELTA SOLIVIA 3.8 DELTA SOLIVIA 7.6 | 2017-02-09 | 2017-02-13 | 2 | 2017-02-13 | [14 empty] | 2017-02-28 | 2017-03-03 |  | Y
Central Hudson |  | SolarCity | CH-07207 | Kingston | High Fls | Ulster | 12440 | G | 3022 | High Falls | N |  | 6.6 | [13 empty] | NM | N | DELTA SOLIVIA 6.6 | 2017-02-07 | 2017-02-07 | 0 | 2017-02-07 | [14 empty] | 2017-03-24 | 2017-03-24 |  | Y
Central Hudson |  | SolarCity | CH-07511 | Kingston | Kingston | Ulster | 12401 | G | 2091 | Hurley Ave | N |  | 10.4 | [13 empty] | NM | N | DELTA SOLIVIA 6.6 DELTA SOLIVIA 3.8 | 2017-02-07 | 2017-02-07 | 0 | 2017-02-07 | [14 empty] | 2017-05-04 | 2017-05-05 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08757 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8043 | Myers Corners | N |  | 6.66 | [13 empty] | NM | N | 31 ENPHASE M215 | 2017-02-07 | 2017-02-07 | 0 | 2017-02-07 | [14 empty] | 2017-06-07 | 2017-06-08 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08818 | Fishkill |  |  | 12590 | G | 8043 | Myers Corners | TBD |  | 3.44 | [13 empty] | NM | N | 16 ENPHASE M215 | 2017-02-08 | 2017-02-08 | 0 | 2017-02-08 | [17 empty] | W
Central Hudson |  | Sungevity Inc | CH-09374 | Newburgh | Newburgh | Orange | 12550 | G | 4051 | Union Ave | N |  | 3.8 | [13 empty] | NM | N | SOLAREDGE SE3800 | 2017-02-08 | 2017-02-08 | 0 | 2017-02-08 | [14 empty] | 2017-05-26 | 2017-06-01 |  | Y
Central Hudson |  | SolarCity | CH-07383 | Fishkill | Stormvl | Dutchess | 12582 | G | 8071 | Shenandoah | N |  | 12.8 | [13 empty] | NM | N | DELTA SOLIVIA 7.6 DELTA SOLIVIA 5.2 | 2017-02-09 | 2017-02-13 | 2 | 2017-02-13 | [14 empty] | 2017-03-13 | 2017-03-24 |  | Y
Central Hudson |  | Sologistics | CH-08312 | Catskill | West Kill | Greene | 12492 | E | 2389 | Vinegar Hill | N |  | 14.4 | [13 empty] | NM | N | 45 SUNPOWER E20-327-C-AC | 2017-02-09 | 2017-02-24 | 10 | 2017-02-24 | [8 empty] | 350 | 350 |  | 2017-04-26 | 2017-04-26 | 2017-05-02 | 2017-05-02 | 2017-05-04 |  | Y
Central Hudson |  | Sologistics | CH-08314 | Catskill | West Kill | Greene | 12492 | E | 2389 | Vinegar Hill | N |  | 27.52 | [13 empty] | NM | N | 86 SUNPOWER X21-345-C-AC | 2017-02-09 | 2017-02-24 | 10 | 2017-02-24 | [14 empty] | 2017-04-18 | 2017-04-18 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-00193 | Newburgh | Marlboro | Ulster | 12542 | G | 5001 | Marlboro | N |  | 5.5 | [13 empty] | NM | N | 22 ENPHASE M250 | 2017-02-10 | 2017-02-13 | 1 | 2017-02-13 | [14 empty] | 2017-03-30 | 2017-04-07 |  | Y
Central Hudson |  | New York State Solar Farm | CH-00362 | Newburgh | New Windsor | Orange | 12553 | G | 4091 | Bethlehem Rd | N |  | 9.6 | [13 empty] | NM | N | 30 SUNPOWERR SPR-E20-327 | 2017-02-10 | 2017-02-13 | 1 | 2017-02-13 | [14 empty] | 2017-03-03 | 2017-03-28 |  | Y
Central Hudson |  | SolarCity | CH-06820 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8054 | North Chelsea | N |  | 5 | [13 empty] | NM | N | Solar Edge SE5000 | 2017-02-10 | 2017-02-13 | 1 | 2017-02-13 | [14 empty] | 2017-03-28 | 2017-03-28 |  | Y
Central Hudson |  | Apex Solar Power | CH-00011 | Poughkeepsie | Millbrook | Dutchess | 12545 | G | 7025 | Tinkertown | N |  | 7.6 | [13 empty] | NM | N | PIKA X7600 | 2017-02-15 | 2017-02-15 | 0 | 2017-02-15 | [14 empty] | 2017-05-08 | 2017-05-09 |  | Y
Central Hudson |  | New York State Solar Farm | CH-00360 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8093 | Fishkill Plains | N |  | 6.4 | [13 empty] | NM | N | 20 SUNPOWER SPR-X22-360 | 2017-02-13 | 2017-02-14 | 1 | 2017-02-14 | [14 empty] | 2017-03-01 | 2017-03-06 |  | Y
Central Hudson |  | Nexamp Solar | CH-04102 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8054 | North Chelsea | N |  | 1995.4 | [13 empty] | CDG | Y | INGETEAM 1165 INGETEAM 830 | 2017-03-28 | 2017-03-29 | 1 | 2017-03-29 | 2017-03-29 | 2017-04-13 | 11 | 2017-05-05 | 2017-05-31 | 2017-09-01 | 66 | 32315.15 | 223953 | 105162.13 | 2017-09-20 | 2017-03-08 | 2017-03-08 | 2019-07-09 | 2019-07-31 | 2019-07-31 | 2019-10-24 | Y | Y | 8/8/17 - CESIR placed on hold due to the delay in obtaining corrected documents from the applicant. The CESIR recommenced on 8/23/17 when updated documentation was received.
Central Hudson |  | SolarCity | CH-06283 | Newburgh | Newburgh | Orange | 12550 | G | 4052 | Union Ave | N |  | 9 | [13 empty] | NM | N | DELTA SOLIVIA 5.2 DELTA SOLIVIA 3.8 | 2017-02-13 | 2017-02-14 | 1 | 2017-02-14 | [14 empty] | 2017-05-24 | 2017-05-24 |  | Y
Central Hudson |  | SolarCity | CH-06797 | Fishkill |  |  | 12590 | G | 8091 | Fishkill Plains | TBD |  | 6.6 | [13 empty] | NM | N | DELTA SOLIVIA 6.6 | 2017-02-13 | 2017-02-17 | 4 | 2017-02-17 | [17 empty] | W
Central Hudson |  | SolarCity | CH-07357 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8095 | Fishkill Plains | N | CH-07357 | 6.6 | [13 empty] | NM | N | DELTA SOLIVIA 6.6 | 2017-03-08 | 2017-03-13 | 3 | 2017-03-13 | [14 empty] | 2017-08-18 | 2017-08-18 |  | Y
Central Hudson |  | SolarCity | CH-07723 | Newburgh | New Windsor | Orange | 12553 | G | 4045 | Union Ave | Y |  | 6.6 | 5 | [12 empty] | NM | N | 1 Delta Electronics SOLIVIA 6.6 NA G4 TL (208V) 1TeslaAC Powerwall 2.0 | 2017-05-23 | 2017-06-05 | 8 | 2017-06-05 | [14 empty] | 2018-01-19 | 2018-01-19 |  | Y
Central Hudson |  | Hudson Solar | CH-02053 | Kingston | Saugerties | Ulster | 12477 | G | 3001 | Saugerties | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000 | 2017-02-14 | 2017-02-14 | 0 | 2017-02-14 | [14 empty] | 2017-04-07 | 2017-04-10 |  | Y
Central Hudson |  | Trinity Solar | CH-08450 | Newburgh | Newburgh | Orange | 12550 | G | 4053 | Union Ave | N |  | 11.4 | [13 empty] | NM | N | SOLAREDGE SE11400 | 2017-02-14 | 2017-02-14 | 0 | 2017-02-14 | [14 empty] | 2017-03-16 | 2017-03-17 |  | Y
Central Hudson |  | Malcarne Contracting | CH-00349 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 6062 | Inwood Ave | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000 | 2017-02-16 | 2017-02-16 | 0 | 2017-02-16 | [14 empty] | 2017-03-24 | 2017-03-31 |  | Y
Central Hudson |  | SolarCity | CH-05282 | Newburgh | New Paltz | Ulster | 12561 | G | 5031 | Galeville | N |  | 5.2 | [13 empty] | NM | N | DELTA SOLIVIA 5.2 | 2017-02-15 | 2017-02-15 | 0 | 2017-02-15 | [14 empty] | 2017-04-12 | 2017-04-18 |  | Y
Central Hudson |  | SolarCity | CH-06660 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6065 | Inwood Ave | N |  | 10.4 | [13 empty] | NM | N | 2 DELTA SOLIVIA 5.2 | 2017-02-15 | 2017-02-15 | 0 | 2017-02-15 | [14 empty] | 2017-03-03 | 2017-03-03 |  | Y
Central Hudson |  | SolarCity | CH-07415 | Newburgh | Newburgh | Orange | 12550 | G | 4051 | Union Ave | N |  | 5.2 | [13 empty] | NM | N | DELTA SOLIVIA 5.2 | 2017-02-15 | 2017-02-15 | 0 | 2017-02-15 | [14 empty] | 2017-04-12 | 2017-04-17 |  | Y
Central Hudson |  | Trinity Solar | CH-08487 | Poughkeepsie | Staatsburg | Dutchess | 12580 | G | 7042 | Staatsburg | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A | 2017-02-15 | 2017-02-16 | 1 | 2017-02-16 | [14 empty] | 2017-05-19 | 2017-06-01 |  | Y
Central Hudson |  | Trinity Solar | CH-08503 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8092 | Fishkill Plains | N |  | 10 | [13 empty] | NM | N | SOLAREDGE SE10000 | 2017-02-15 | 2017-02-16 | 1 | 2017-02-16 | [14 empty] | 2017-04-25 | 2017-05-04 |  | Y
Central Hudson |  | Trinity Solar | CH-08532 | Kingston | Kerhonkson | Ulster | 12446 | G | 3083 | Kerhonkson | N |  | 3.8 | [13 empty] | NM | N | SOLAREDGE SE3800A | 2017-02-15 | 2017-02-16 | 1 | 2017-02-16 | [14 empty] | 2017-04-12 | 2017-04-12 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08722 | Catskill |  |  | 12477 | G | 2001 | North Catskill | TBD |  | 15.26 | [13 empty] | NM | N | 71 ENPHASE M215 | 2017-02-15 | 2017-02-15 | 0 | 2017-02-15 | [17 empty] | W
Central Hudson |  | Sustainable Energy Developments, Inc. | CH-09704 | Kingston |  |  | 12777 | G | 3006 | Saugerties | TBD |  | 2000 | [13 empty] | CDG | N | (66) SMA Tri-power 30000TL-US (1) SMA Tri-power 20000TL-US | 2017-02-15 | 2017-03-02 | 10 | 2017-03-02 | 2017-03-02 | 2017-03-23 | 15 |  |  |  |  | 35000 | [9 empty] | W
Central Hudson |  | SolarCity | CH-06663 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 6068 | Inwood Ave | N |  | 6.6 | [13 empty] | NM | N | DELTA SOLIVIA 6.6 | 2017-02-16 | 2017-02-17 | 1 | 2017-02-17 | [14 empty] | 2017-05-02 | 2017-05-02 |  | Y
Central Hudson |  | SolarCity | CH-07094 | Newburgh |  |  | 12561 | G | 5012 | Modena | TBD |  | 13.2 | [13 empty] | NM | N | 2 DELTA SOLIVIA 6.6 | 2017-02-21 | 2017-02-22 | 1 | 2017-02-22 | [17 empty] | W
Central Hudson |  | SolarCity | CH-06589 | Kingston | Lk Katrine | Ulster | 12449 | G | 2011 | Lincoln Park | N |  | 5.2 | [13 empty] | NM | N | DELTA SOLIVIA 5.2 | 2017-02-17 | 2017-02-17 | 0 | 2017-02-17 | [14 empty] | 2017-04-13 | 2017-04-13 |  | Y
Central Hudson |  | Solar Generation | CH-08129 | Kingston | Woodstock | Ulster | 12498 | G | 3014 | Woodstock | N |  | 12 | [13 empty] | NM | N | 2 SOLAREDGE 6000A | 2017-02-22 | 2017-02-22 | 0 | 2017-02-22 | [14 empty] | 2017-04-11 | 2017-04-12 |  | Y
Central Hudson |  | Solar Generation | CH-08208 | Kingston | W Hurley | Ulster | 12491 | G | 2094 | Hurley Ave | N |  | 15.4 | [13 empty] | NM | N | 2 SMA SB7.7 | 2017-05-23 | 2017-06-01 | 6 | 2017-06-01 | [8 empty] | 350 | 350 |  | 2017-06-07 | 2017-06-07 | 2017-07-06 | 2017-07-21 | 2017-07-21 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08627 | Fishkill | Beacon | Dutchess | 12508 | G | 8087 | Tioronda | N |  | 3.87 | [13 empty] | NM | N | 18 ENPHASE M215 | 2017-02-17 | 2017-02-17 | 0 | 2017-02-17 | [14 empty] | 2017-12-06 | 2017-12-07 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08633 | Fishkill | Beacon | Dutchess | 12508 | G | 8087 | Tioronda | N |  | 3.87 | [13 empty] | NM | N | 18 ENPHASE M215 | 2017-02-24 | 2017-02-24 | 0 | 2017-02-24 | [14 empty] | 2017-12-06 | 2017-12-07 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-00102 | Fishkill | Fishkill | Dutchess | 12524 | G | 8063 | Merritt Park | N |  | 11.4 | [13 empty] | NM | N | SOLAREDGE 11400A | 2017-02-22 | 2017-02-22 | 0 | 2017-02-22 | [14 empty] | 2017-06-02 | 2017-06-07 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-00212 | Newburgh | Campbell Hall | Orange | 10916 | G | 5052 | Maybrook | N |  | 4.5 | [13 empty] | NM | N | 18 ENPHASE ENERGY M250 | 2017-02-22 | 2017-02-22 | 0 | 2017-02-22 | [14 empty] | 2017-06-08 | 2017-06-13 |  | Y
Central Hudson |  | Kasselman Solar | CH-00235 | Catskill | Surprise |  | 12176 | G | 2061 | Freehold | TBD |  | 9 | [13 empty] | NM | N | 36 ENPHASE M250 | 2017-02-21 | 2017-02-23 | 2 | 2017-02-23 | [8 empty] | 350 | 350 | [7 empty] | W
Central Hudson |  | Hudson Solar | CH-01314 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 7024 | Tinkertown | N |  | 10 | [13 empty] | NM | N | SOLAREDGE SE10000 | 2017-02-21 | 2017-02-21 | 0 | 2017-02-21 | [14 empty] | 2017-04-25 | 2017-04-25 |  | Y
Central Hudson |  | Hudson Solar | CH-01413 | Newburgh | Gardiner | Ulster | 12525 | G | 5031 | Galeville | N |  | 11.4 | [13 empty] | NM | N | SOLAREDGE SE11400 | 2017-02-27 | 2017-02-27 | 0 | 2017-02-27 | [14 empty] | 2017-04-07 | 2017-04-12 |  | Y
Central Hudson |  | Hudson Solar | CH-02372 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8093 | Fishkill Plains | N |  | 10 | [13 empty] | NM | N | SOLAREDGE SE10000 | 2017-02-21 | 2017-02-21 | 0 | 2017-02-21 | [8 empty] | 350 | 350 |  | 2017-03-03 | 2017-03-03 | 2017-04-18 | 2017-07-28 | 2017-07-28 |  | Y
Central Hudson |  | Hudson Solar | CH-02494 | Newburgh | Montgomery | Orange | 12549 | G | 5073 | Montgomery | N | CH-02221 | 6 | [13 empty] | NM | N | SOLAREDGE SE6000 | 2017-02-21 | 2017-02-21 | 0 | 2017-02-21 | [8 empty] | 350 | 350 |  | 2017-03-03 | 2017-03-03 | 2017-03-16 | 2017-03-30 | 2017-05-01 |  | Y
Central Hudson |  | Hudson Solar | CH-02534 | Poughkeepsie | Rhinebeck |  | 12572 | G | 7053 | Rhinebeck | N |  | 432.9 | [13 empty] | CDG | N | 13 SOLAREDGE SE33.3 | 2017-02-27 | 2017-03-01 | 2 | 2017-03-01 | 2017-03-01 | 2017-03-22 | 15 | [14 empty] | W
Central Hudson |  | SolarCity | CH-07048 | Newburgh | New Windsor | Orange | 12553 | G | 4046 | Union Ave | N |  | 10.4 | [13 empty] | NM | N | DELTA SOLIVIA 3.8 DELTA SOLIVIA 6.6 | 2017-02-21 | 2017-02-21 | 0 | 2017-02-21 | [14 empty] | 2017-06-30 | 2017-06-30 |  | Y
Central Hudson |  | SUNEAST DEVELOPMENT LLC | CH-09078 | Catskill | Coxsackie | Greene | 12051 | G | 1076 | Coxsackie | N |  | 4998 | [13 empty] | CDG | Y | 3 EATON power XPERT SOLAR 1670 | 2017-04-20 | 2017-04-26 | 4 | 2017-04-26 | 2017-04-26 | 2017-05-17 | 15 | 2017-08-07 | 2017-10-27 | 2018-02-26 | 80 | 18043.19 | 1511895 | 515212.21 | 2018-04-23 | 2019-07-01 | 2019-07-01 | 2022-06-24 | 2022-10-03 | 2022-10-10 | 2023-01-11 | Y | Y | 9/5/18 - Developer submitted a Moratorium Attestation Form.
Central Hudson |  | SUNEAST DEVELOPMENT LLC | CH-09168 | Catskill | Athens | Greene | 12414 | G | 2006 | North Catskill | N |  | 4998 | [13 empty] | CDG | Y | 3 EATON POWER XPERT SOLAR 1670 | 2017-04-20 | 2017-04-26 | 4 | 2017-04-26 | 2017-04-26 | 2017-05-17 | 15 | 2017-08-07 | 2017-10-27 | 2018-02-26 | 80 | 35500 | 634813 |  | 2018-04-23 | 2018-10-09 | 2018-10-09 |  |  |  |  | N | Y | CESIR deadline extended 40 Business Days; due 3/26/18.
Central Hudson |  | American Energy Care | CH-00653 | Catskill | Hannacroix | Greene | 12087 | G | 1083 | New Baltimore | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE7600 | 2017-02-22 | 2017-02-22 | 0 | 2017-02-22 | [14 empty] | 2017-04-28 | 2017-05-04 |  | Y
Central Hudson |  | Solar Generation | CH-08112 | Kingston | Kerhonkson | Ulster | 12446 | G | 3082 | Kerhonkson | N |  | 6 | [13 empty] | NM | N | SOLAREDGE 6000A | 2017-02-22 | 2017-02-23 | 1 | 2017-02-23 | [14 empty] | 2017-04-11 | 2017-04-19 |  | Y
Central Hudson |  | Hudson Solar | CH-01807 | Poughkeepsie | Lagrangevl | Dutchess | 12540 | G | 6052 | Todd Hill | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000 | 2017-02-23 | 2017-02-24 | 1 | 2017-02-24 | [14 empty] | 2017-05-04 | 2017-05-17 |  | Y
Central Hudson |  | Hudson Solar | CH-02060 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6044 | Spackenkill | N |  | 7.6 | [13 empty] | NM | N | SOALREDGE SE7600 | 2017-02-23 | 2017-02-24 | 1 | 2017-02-24 | [14 empty] | 2017-06-14 | 2017-06-20 |  | Y
Central Hudson |  | SolarCity | CH-06556 | Kingston | Ellenvl | Ulster | 12428 | G | 3095 | Grimley Rd | Y | CH-06556 | 11.4 | [13 empty] | NM | N | DELTA SOLIVIA 7.6 DELTA SOLIVIA 3.8 | 2017-02-23 | 2017-02-23 | 0 | 2017-02-23 | [14 empty] | 2017-03-24 | 2017-03-24 |  | Y
Central Hudson |  | Sunrun Inc. | CH-08349 | Newburgh | New Windsor | Orange | 12553 | G | 4095 | Bethlehem Rd | N |  | 10 | [13 empty] | NM | N | SOLAREDGE SE10000 | 2017-02-24 | 2017-02-27 | 1 | 2017-02-27 | [14 empty] | 2017-04-26 | 2017-05-02 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08695 | Fishkill |  |  | 12533 | G | 8094 | Fishkill Plains | TBD |  | 4.51 | [13 empty] | NM | N | 21 ENPHASE M215 | 2017-02-23 | 2017-02-23 | 0 | 2017-02-23 | [17 empty] | W
Central Hudson |  | Solar Liberty Energy Systems | CH-04905 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6095 | Manchester | N | CH-04905 | 6 | [13 empty] | NM | N | SOLAREDGE 6000A | 2017-02-27 | 2017-02-27 | 0 | 2017-02-27 | [14 empty] | 2017-08-07 | 2017-08-07 |  | Y
Central Hudson |  | SolarCity | CH-06824 | Fishkill | Wappingers Falls | Dutchess | 12590 | G | 8023 | Knapps Corners | N |  | 7.6 | [13 empty] | NM | N | DELTA SOLIVIA 7.6 | 2017-02-24 | 2017-02-28 | 2 | 2017-02-28 | [14 empty] | 2017-03-01 | 2017-03-06 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07570 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8092 | Fishkill Plains | N |  | 7.6 | [13 empty] | NM | N | DELTA SOLIVIA 7.6 | 2017-02-24 | 2017-02-27 | 1 | 2017-02-27 | [14 empty] | 2017-04-18 | 2017-04-18 |  | Y
Central Hudson |  | SolarCity | CH-07602 | Newburgh | Wallkill | Ulster | 12589 | G | 4011 | West Balmville | N |  | 10 | [13 empty] | NM | N | SOLAREDGE SE10000A | 2017-02-24 | 2017-02-24 | 0 | 2017-02-24 | [14 empty] | 2017-04-20 | 2017-04-27 |  | Y
Central Hudson |  | SolarCity | CH-07791 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 3 | [13 empty] | NM | N | ABB PVI 3.0 | 2017-02-27 | 2017-02-27 | 0 | 2017-02-27 | [14 empty] | 2017-04-12 | 2017-04-12 |  | Y
Central Hudson |  | Trinity Solar | CH-08437 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8072 | Shenandoah | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000 | 2017-02-24 | 2017-02-24 | 0 | 2017-02-24 | [14 empty] | 2017-04-10 | 2017-04-10 |  | Y
Central Hudson |  | Trinity Solar | CH-08440 | Fishkill |  |  | 12533 | G | 8093 | Fishkill Plains | TBD |  | 3.8 | [13 empty] | NM | N | SOLAREDGE SE3800 | 2017-02-24 | 2017-02-24 | 0 | 2017-02-24 | [17 empty] | W
Central Hudson |  | Trinity Solar | CH-08474 | Kingston |  |  | 12428 | G | 3076 | Greenfield Rd | TBD |  | 3.8 | [13 empty] | NM | N | SOLAREDGE SE3800 | 2017-02-24 | 2017-03-01 | 3 | 2017-03-01 | [17 empty] | W
Central Hudson |  | Trinity Solar | CH-08564 | Fishkill | Fishkill | Dutchess | 12524 | G | 8065 | Merritt Park | N | CH-08564 | 3.8 | [13 empty] | NM | N | SOLAREDGE SE.3800 | 2017-02-24 | 2017-02-24 | 0 | 2017-02-24 | [14 empty] | 2017-04-17 | 2017-04-17 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00939 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7061 | Milan | N |  | 9 | [13 empty] | NM | N | 36 ENPHASE M250 | 2017-02-27 | 2017-02-28 | 1 | 2017-02-28 | [14 empty] | 2017-03-29 | 2017-03-30 |  | Y
Central Hudson |  | SolarCity | CH-05345 | Newburgh | Newburgh | Orange | 12550 | G | 4011 | West Balmville | N |  | 12.8 | [13 empty] | NM | N | DELTA SOLIVIA 5.2 DELTA SOLIVIA 7.6 | 2017-02-27 | 2017-02-27 | 0 | 2017-02-27 | [14 empty] | 2017-06-16 | 2017-06-22 |  | Y
Central Hudson |  | SolarCity | CH-05383 | Newburgh | Highland | Ulster | 12528 | G | 5081 | Highland | N |  | 5.2 | [13 empty] | NM | N | DELTA SOLIVIA 5.2 | 2017-02-27 | 2017-02-28 | 1 | 2017-02-28 | [14 empty] | 2017-05-31 | 2017-06-07 |  | Y
Central Hudson |  | SolarCity | CH-07478 | Newburgh | New Windsor | Orange | 12553 | G | 4095 | Bethlehem Rd | N |  | 11.4 | [13 empty] | NM | N | SOLAREDGE SE11400 | 2017-02-27 | 2017-02-27 | 0 | 2017-02-27 | [14 empty] | 2017-03-29 | 2017-03-31 |  | Y
Central Hudson |  | Kasselman Solar | CH-00237 | Catskill | Westerlo | Albany | 12193 | G | 1091 | Westerlo | N |  | 5.1 | [13 empty] | NM | N | 22 Enphase Energy IQ6-60-x-US (240V) [SI1] | 2017-04-24 | 2017-04-24 | 0 | 2017-04-24 | [14 empty] | 2018-06-01 | 2018-06-04 |  | Y
Central Hudson |  | Hudson Solar | CH-01799 | Poughkeepsie | Stanfordvl | Dutchess | 12581 | G | 7072 | Stanfordville | N |  | 50 | [13 empty] | NM | N | 5 SOLAREDGE SE7600 2 SOLAREDGE SE6000 | 2017-02-28 | 2017-03-14 | 10 | 2017-03-14 | [8 empty] | 2500 | 3892.41 |  | 2017-03-27 | 2017-03-27 | 2017-05-08 | 2017-06-12 | 2017-06-19 |  | Y
Central Hudson |  | SolarCity | CH-06653 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6091 | Manchester | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE500A | 2017-02-28 | 2017-02-28 | 0 | 2017-02-28 | [14 empty] | 2017-04-26 | 2017-04-26 |  | Y
Central Hudson |  | SolarCity | CH-06946 | Fishkill | Beacon | Dutchess | 12508 | G | 8015 | Forgebrook | N |  | 3 | [13 empty] | NM | N | ABB PVI 3.0 | 2017-02-28 | 2017-02-28 | 0 | 2017-02-28 | [14 empty] | 2017-05-09 | 2017-05-09 |  | Y
Central Hudson |  | SolarCity | CH-07165 | Newburgh | New Windsor | Orange | 12553 | G | 4094 | Bethlehem Rd | N |  | 11.4 | [13 empty] | NM | N | SOLAREDGE SE11400 | 2017-02-28 | 2017-02-28 | 0 | 2017-02-28 | [14 empty] | 2017-04-13 | 2017-04-13 |  | Y
Central Hudson |  | SolarCity | CH-07178 | Newburgh | New Windsor | Orange | 12553 | G | 4095 | Bethlehem Rd | N |  | 7.6 | [13 empty] | NM | N | DELTA SOLIVIA 7.6 | 2017-03-02 | 2017-03-02 | 0 | 2017-03-02 | [14 empty] | 2017-04-12 | 2017-04-19 |  | Y
Central Hudson |  | SolarCity | CH-07724 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 5.2 | [13 empty] | NM | N | DELTA SOLIVIA 5.2 | 2017-02-28 | 2017-02-28 | 0 | 2017-02-28 | [14 empty] | 2017-03-27 | 2017-03-28 |  | Y
Central Hudson |  | Trinity Solar | CH-08418 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6055 | Todd Hill | N |  | 11.4 | [13 empty] | NM | N | SOLAREDGE SE11400A | 2017-02-28 | 2017-03-13 | 9 | 2017-03-13 | [14 empty] | 2017-04-27 | 2017-04-27 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08731 | Catskill | E Durham | Greene | 12423 | G | 2071 | Freehold | N |  | 3.22 | [13 empty] | NM | N | 15 ENPHASE M215 | 2017-02-28 | 2017-02-28 | 0 | 2017-02-28 | [14 empty] | 2017-06-06 | 2017-06-08 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-00130 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8096 | Fishkill Plains | N |  | 13.76 | [13 empty] | NM | N | 43 SUNPOWER SPR-X22-360 | 2017-03-01 | 2017-03-01 | 0 | 2017-03-01 | [14 empty] | 2017-05-03 | 2017-05-03 |  | Y
Central Hudson |  | SolarCity | CH-05392 | Newburgh | Newburgh | Orange | 12550 | G | 4023 | Coldenham | N |  | 5.2 | [13 empty] | NM | N | DELTA SOLIVIA 5.2 | 2017-03-17 | 2017-03-22 | 3 | 2017-03-22 | [14 empty] | 2017-03-24 | 2017-03-31 |  | Y
Central Hudson |  | Apex Solar Power | CH-00707 | Newburgh | New Paltz | Ulster | 12561 | G | 5021 | Ohioville | N | CH-00707 | 6 | [13 empty] | NM | N | SOLAREDGE SE6000 | 2017-03-02 | 2017-03-03 | 1 | 2017-03-03 | [14 empty] | 2017-06-13 | 2017-06-20 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00920 | Kingston | Saugerties | Ulster | 12477 | G | 3001 | Saugerties | N |  | 6.75 | [13 empty] | NM | N | 27 ENPHASE M250 | 2017-03-02 | 2017-03-03 | 1 | 2017-03-03 | [14 empty] | 2017-03-29 | 2017-03-30 |  | Y
Central Hudson |  | Solar Liberty Energy Systems | CH-04906 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6003 | Reynolds Hill | N |  | 3 | [13 empty] | NM | N | SOLAREDGE SE3000 | 2017-03-03 | 2017-03-07 | 2 | 2017-03-07 | [14 empty] | 2017-08-09 | 2017-08-15 |  | Y
Central Hudson |  | Solar Liberty Energy Systems | CH-04908 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8052 | North Chelsea | N |  | 5 | [13 empty] | NM | N | SOLAREDGE 5 | 2017-03-02 | 2017-03-02 | 0 | 2017-03-02 | [14 empty] | 2017-08-04 | 2017-08-04 |  | Y
Central Hudson |  | SolarCity | CH-06107 | Fishkill | Beacon | Dutchess | 12508 | G | 8013 | Forgebrook | N |  | 6 | [13 empty] | NM | N | ABB PVI 6000 | 2017-03-02 | 2017-03-02 | 0 | 2017-03-02 | [14 empty] | 2017-04-17 | 2017-04-17 |  | Y
Central Hudson |  | SolarCity | CH-07002 | Newburgh | Newburgh | Orange | 12550 | G | 4012 | West Balmville | N |  | 6.6 | [13 empty] | NM | N | DELTA SOLIVIA 6.6 | 2017-03-02 | 2017-03-02 | 0 | 2017-03-02 | [14 empty] | 2017-04-12 | 2017-04-12 |  | Y
Central Hudson |  | SolarCity | CH-08054 | Kingston |  |  | 12428 | G | 3076 | Greenfield Rd | TBD |  | 1992 | [13 empty] | CDG | N | 83 FRONIUS SYMO | 2017-04-12 | 2017-04-21 | 6 | 2017-04-21 | 2017-04-21 | 2017-05-12 | 15 |  |  |  |  | 35000 | [9 empty] | W
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08707 | Fishkill |  |  | 12508 | G | 8085 | Tioronda | TBD |  | 4.08 | [13 empty] | NM | N | 19 ENPHASE M215 | 2017-03-02 | 2017-03-03 | 1 | 2017-03-03 | [17 empty] | W
Central Hudson |  | Siemens Industry | CH-08898 | Poughkeepsie | Pine Plains | Dutchess | 12567 | G | 7091 | Pulvers Corners | N |  | 360 | [13 empty] | NM | N | 6 ABB TRIO-TM-60.0-US-480 (480V) [SI1] 8 TRIO 50 TL | 2017-03-13 | 2017-03-16 | 3 | 2017-03-16 | 2017-03-16 | 2017-04-06 | 15 | [11 empty] | 2019-06-26 | 2019-06-26 |  | Y
Central Hudson |  | Hudson Solar | CH-01403 | Poughkeepsie | Tivoli | Dutchess | 12583 | G | 7062 | Milan | N |  | 11.4 | [13 empty] | NM | N | SOLAREDGE SE11400 | 2017-03-27 | 2017-03-28 | 1 | 2017-03-28 | [14 empty] | 2017-05-08 | 2017-05-24 |  | Y
Central Hudson |  | Hudson Solar | CH-02261 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 7041 | Staatsburg | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE7600 | 2017-03-03 | 2017-03-07 | 2 | 2017-03-07 | [14 empty] | 2017-05-23 | 2017-05-31 |  | Y
Central Hudson |  | SolarCity | CH-06691 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 6074 | East Park | N |  | 11.4 | [13 empty] | NM | N | SOLAREDGE SE11400 | 2017-03-23 | 2017-03-24 | 1 | 2017-03-24 | [14 empty] | 2017-05-05 | 2017-05-05 |  | Y
Central Hudson |  | SolarCity | CH-07657 | Fishkill |  |  | 12590 | G | 8091 | Fishkill Plains | TBD |  | 6.6 | [13 empty] | NM | N | DELTA SOLIVIA 6.6 | 2017-03-03 | 2017-03-10 | 5 | 2017-03-10 | [17 empty] | W
Central Hudson |  | Empire Solar Solutions | CH-00023 | Kingston | Kingston | Ulster | 12401 | G | 2016 | Lincoln Park | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE 7600AUS | 2017-03-07 | 2017-03-10 | 3 | 2017-03-10 | [14 empty] | 2017-04-17 | 2017-04-25 |  | Y
Central Hudson |  | New York State Solar Farm | CH-00436 | Newburgh | Walden | Orange | 12586 | G | 5043 | East Walden | N |  | 10.88 | [13 empty] | NM | N | 34 Sunpower X21 345 | 2017-03-06 | 2017-03-07 | 1 | 2017-03-07 | [14 empty] | 2017-04-05 | 2017-04-06 |  | Y
Central Hudson |  | SolarCity | CH-05300 | Newburgh | Newburgh | Orange | 12550 | G | 4011 | West Balmville | N |  | 11.8 | [13 empty] | NM | N | DELTA SOLIVIA 5.2 DELTA SOLIVIA 6.6 | 2017-03-06 | 2017-03-10 | 4 | 2017-03-10 | [8 empty] | 350 | 350 |  | 2017-05-04 | 2017-05-04 | 2017-05-06 | 2017-05-24 | 2017-05-24 |  | Y
Central Hudson |  | SolarCity | CH-07229 | Kingston | Ellenville | Ulster | 12428 | G | 3095 | Grimley Rd | N |  | 5.2 | [13 empty] | NM | N | DELTA SOLIVIA 5.2 | 2017-03-06 | 2017-03-20 | 10 | 2017-03-20 | [14 empty] | 2017-04-12 | 2017-04-19 |  | Y
Central Hudson |  | SolarCity | CH-07328 | Newburgh | Highland | Ulster | 12528 | G | 5081 | Highland | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE7600 | 2017-03-14 | 2017-03-21 | 5 | 2017-03-21 | [14 empty] | 2017-04-20 | 2017-04-20 |  | Y
Central Hudson |  | SolarCity | CH-07358 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8092 | Fishkill Plains | N |  | 6.6 | [13 empty] | NM | N | DELTA SOLIVIA 6.6TL | 2017-03-06 | 2017-03-07 | 1 | 2017-03-07 | [14 empty] | 2017-04-21 | 2017-04-26 |  | Y
Central Hudson |  | SolarCity | CH-07749 | Newburgh | Plattekill | Ulster | 12568 | G | 5013 | Modena | N |  | 3.8 | [13 empty] | NM | N | DELTA SOLIVIA 3.8TL | 2017-03-06 | 2017-03-10 | 4 | 2017-03-10 | [14 empty] | 2017-03-13 | 2017-03-15 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07767 | Newburgh | Newburgh | Orange | 12550 | G | 4012 | West Balmville | N |  | 3 | [13 empty] | NM | N | ABB PVI-3.0OUTD-S-US | 2017-03-06 | 2017-03-07 | 1 | 2017-03-07 | [14 empty] | 2017-05-08 | 2017-05-08 |  | Y
Central Hudson |  | Solar Generation | CH-08147 | Kingston | Accord | Ulster | 12404 | G | 3024 | High Falls | N |  | 18 | [13 empty] | NM | N | 3 SMA SB6.0 | 2017-03-21 | 2017-03-24 | 3 | 2017-03-24 | [8 empty] | 350 | 350 |  | 2017-04-06 | 2017-04-06 | 2017-04-25 | 2017-05-03 | 2017-05-09 |  | Y
Central Hudson |  | Hudson Solar | CH-02198 | Newburgh | New Paltz | Ulster | 12561 | G | 5023 | Ohioville | N |  | 12.6 | [13 empty] | NM | N | SOLAREDGE SE7600 SOLAREDGE SE5000 | 2017-03-07 | 2017-03-10 | 3 | 2017-03-10 | [14 empty] | 2017-06-02 | 2017-06-06 |  | Y
Central Hudson |  | Hudson Solar | CH-02448 | Poughkeepsie |  |  | 12538 | G | 6074 | East Park | TBD |  | 16.4 | [13 empty] | NM | N | SOLAREDGE SE11400 SOLAREDGE SE5000 | 2017-03-07 | 2017-03-10 | 3 | 2017-03-10 | [17 empty] | W
Central Hudson |  | SolarCity | CH-05398 | Newburgh | Salisbury Mls | Orange | 12577 | G | 4097 | Bethlehem Rd | N |  | 6.6 | [13 empty] | NM | N | DELTA SOLIVIA 6.6 | 2017-03-07 | 2017-03-08 | 1 | 2017-03-08 | [14 empty] | 2017-04-05 | 2017-04-10 |  | Y
Central Hudson |  | SolarCity | CH-06245 | Newburgh | Newburgh | Orange | 12550 | G | 4051 | Union Ave | Y |  | 6 | 6 | [12 empty] | NM | N | DELTA H61TeslaH6 Hybrid Inverter | 2017-05-16 | 2017-05-17 | 1 | 2017-05-17 | [14 empty] | 2017-07-19 | 2017-07-19 |  | Y
Central Hudson |  | SolarCity | CH-06796 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8091 | Fishkill Plains | N |  | 11.4 | [13 empty] | NM | N | DELTA SOLIVIA 7.6 DELTA SOLIVIA 3.8 | 2017-03-07 | 2017-03-08 | 1 | 2017-03-08 | [14 empty] | 2017-04-12 | 2017-04-12 |  | Y
Central Hudson |  | SolarCity | CH-06919 | Fishkill | Stormvl | Dutchess | 12582 | G | 8071 | Shenandoah | N |  | 7.6 | [13 empty] | NM | N | DELTA SOLIVIA 7.6 | 2017-03-07 | 2017-03-08 | 1 | 2017-03-08 | [14 empty] | 2017-04-28 | 2017-04-28 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08646 | Catskill |  |  | 12083 | G | 2071 | Freehold | TBD |  | 4.3 | [13 empty] | NM | N | 20 ENPHASE M215 | 2017-03-07 | 2017-03-10 | 3 | 2017-03-10 | [17 empty] | W
Central Hudson |  | Mountain Gardens, LLC | CH-03351 | Newburgh | Newburgh | Orange | 12550 | G | 4024 | Coldenham | N |  | 3960 | [13 empty] | CDG | Y | 20 Yaskawa Solectria Solar XGI 1500 200/200-480 (480V) [SI1] 33 SOLECTRIA 60TL | 2017-03-13 | 2017-03-21 | 6 | 2017-03-21 | 2017-03-21 | 2017-04-10 | 14 | 2017-06-09 | 2017-06-09 | 2017-09-05 | 60 | 20000 | 269540 |  | 2017-12-04 | 2019-03-15 | 2019-03-15 | 2025-10-17 |  |  |  | N | N | CESIR for 2 projects combined with an aggregate CESIR Cost to customer of $40,000 & Estimated Project Upgrade Costs of $379,265. 6/6/18 - Received request to combine with Project CH-03352; current deadlines suspended. CH-03351 and CH-03352 consolidated to one 3.96 MW project. Combined application number is CH-03351. Post Combination Cost $269,540
Central Hudson |  | EnterSolar LLC | CH-03352 | Newburgh | Newburgh |  | 12550 | G | 4024 | Coldenham | TBD |  | 1980 | [13 empty] | CDG | Y | 33 SOLECTRIA 60TL | 2017-03-13 | 2017-03-21 | 6 | 2017-03-21 | 2017-03-21 | 2017-04-10 | 14 | 2017-06-09 | 2017-06-09 | 2017-09-05 | 60 | 20000 | 189632.5 |  | 2017-12-04 | [6 empty] | W |  | CESIR for 2 projects combined with an aggregate CESIR Cost to customer of $40,000 & Estimated Project Upgrade Costs of $379,265. 6/6/18 - Received request to combine with Project CH-03351; current deadlines suspended.CH-03351 and CH-03352 consolidated to one 3.96 MW project. Combined application number is CH-03351. Post Combination Cost $269,540
Central Hudson |  | SolarCity | CH-05048 | Fishkill |  |  | 12590 | G | 8044 | Myers Corners | TBD |  | 120 | [13 empty] | NM | N | 5 FRONIUS SYMO 24-3 480 | 2017-03-30 | 2017-04-13 | 10 | 2017-04-13 | 2017-04-13 | 2017-05-05 | 15 | 2017-06-26 | 2017-07-14 |  |  | 233.53 | [8 empty] | 2018-06-07 | W |  | Due to the delay obtaining the corrected documents, the CESIR study was put on hold as of 10/2/17. The CESIR will recommence once we receive the requested documents.
Central Hudson |  | SolarCity | CH-07643 | Kingston | Kingston | Ulster | 12401 | G | 1021 | East Kingston | N |  | 7.6 | [13 empty] | NM | N | DELTA SOLIVIA 7.6 | 2017-03-08 | 2017-03-16 | 6 | 2017-03-16 | [14 empty] | 2017-06-27 | 2017-06-27 |  | Y
Central Hudson |  | Trinity Solar | CH-08387 | Catskill |  |  | 12418 | G | 2043 | South Cairo | TBD |  | 3 | [13 empty] | NM | N | SOLAREDGE SE3000 | 2017-03-21 | 2017-03-28 | 5 | 2017-03-28 | [17 empty] | W
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08647 | Catskill |  |  | 12423 | G | 2061 | Freehold | TBD |  | 3.22 | [13 empty] | NM | N | 15 ENPHASE M215 | 2017-06-02 | 2017-07-03 | 21 | 2017-07-03 | [17 empty] | W
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08697 | Fishkill | Fishkill | Dutchess | 12524 | G | 8094 | Fishkill Plains | N |  | 3.44 | [13 empty] | NM | N | 16 ENPHASE M215 | 2017-03-13 | 2017-03-17 | 4 | 2017-03-17 | [14 empty] | 2017-05-09 | 2017-05-15 |  | Y
Central Hudson |  | Xzerta Energy Group, LLC | CH-09953 | Kingston |  |  | 12788 | G | 3091 | Neversink | TBD |  | 2000 | [13 empty] | CDG | N | Power electronics FS2000CU15 | 2017-04-24 | 2017-05-05 | 9 | 2017-05-05 | 2017-05-05 | 2017-05-26 | 15 | [14 empty] | W
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08708 | Fishkill | Beacon | Dutchess | 12508 | G | 8087 | Tioronda | N |  | 6.02 | [13 empty] | NM | N | 28 ENPHASE M215 | 2017-03-09 | 2017-03-15 | 4 | 2017-03-15 | [14 empty] | 2017-08-01 | 2017-08-01 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08709 | Fishkill | Beacon | Dutchess | 12508 | G | 8087 | Tioronda | N |  | 3.44 | [13 empty] | NM | N | 16 ENPHASE M215 | 2017-03-09 | 2017-03-15 | 4 | 2017-03-15 | [14 empty] | 2017-07-25 | 2017-07-25 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08764 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8071 | Shenandoah | N |  | 5.59 | [13 empty] | NM | N | 26 ENPHASE M215 | 2017-03-09 | 2017-03-15 | 4 | 2017-03-15 | [14 empty] | 2017-05-24 | 2017-05-24 |  | Y
Central Hudson |  | SolarCity | CH-05335 | Fishkill | Beacon | Dutchess | 12508 | G | 8015 | Forgebrook | N |  | 3.8 | [13 empty] | NM | N | DELTA SOLIVIA 3.8 | 2017-03-10 | 2017-03-15 | 3 | 2017-03-15 | [14 empty] | 2017-03-16 | 2017-03-21 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | SolarCity | CH-07434 | Newburgh | Newburgh | Orange | 12550 | G | 4051 | Union Ave | N |  | 3 | [13 empty] | NM | N | ABB PVI 3.0 | 2017-03-10 | 2017-03-15 | 3 | 2017-03-15 | [14 empty] | 2017-04-18 | 2017-04-26 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08618 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8091 | Fishkill Plains | N |  | 7.74 | [13 empty] | NM | N | 36 ENPHASE M215 | 2017-03-16 | 2017-03-22 | 4 | 2017-03-22 | [14 empty] | 2017-06-05 | 2017-06-09 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08696 | Fishkill | Fishkill | Dutchess | 12524 | G | 8094 | Fishkill Plains | N | CH-08696 | 4.3 | [13 empty] | NM | N | 26 ENPHASE M215 | 2017-03-10 | 2017-03-15 | 3 | 2017-03-15 | [14 empty] | 2017-07-25 | 2017-07-25 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08821 | Newburgh | Newburgh | Orange | 12550 | G | 4024 | Coldenham | N |  | 3.655 | [13 empty] | NM | N | 18 ENPHASE M215 | 2017-03-16 | 2017-03-22 | 4 | 2017-03-22 | [14 empty] | 2017-09-14 | 2017-09-15 |  | Y
Central Hudson |  | New York State Solar Farm | CH-00415 | Newburgh | Modena | Ulster | 12548 | G | 5013 | Modena | N |  | 9.28 | [13 empty] | NM | N | 29 SUNPOWER SPR X22 360 | 2017-03-13 | 2017-03-27 | 10 | 2017-03-27 | [14 empty] | 2017-05-30 | 2017-06-01 |  | Y
Central Hudson |  | US Energy Concierge, Inc. | CH-09748 | Fishkill | Beacon | Dutchess | 12508 | G | 8017 | Forgebrook | N |  | 11.4 | [13 empty] | NM | N | PIKA ENERGY X7601 SOLAREDGE SE3800 | 2017-03-21 | 2017-03-28 | 5 | 2017-03-28 | [14 empty] | 2017-05-11 | 2017-05-18 |  | Y
Central Hudson |  | New York State Solar Farm | CH-00397 | Newburgh | Highland | Ulster | 12528 | G | 5022 | Ohioville | N |  | 5.12 | [13 empty] | NM | N | 16 SUNPOWER SPR X21 345 | 2017-03-14 | 2017-03-17 | 3 | 2017-03-17 | [14 empty] | 2017-07-13 | 2017-07-17 |  | Y
Central Hudson |  | SolarCity | CH-05215 | Kingston | Kingston | Ulster | 12401 | G | 1021 | East Kingston | N | CH-05215 | 6 | [13 empty] | NM | N | ABB PVI-6000 | 2017-03-14 | 2017-03-28 | 10 | 2017-03-28 | [14 empty] | 2017-04-19 | 2017-04-19 |  | Y
Central Hudson |  | SolarCity | CH-06870 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8094 | Fishkill Plains | N |  | 10 | [13 empty] | NM | N | SOLAREDGE SE10000 | 2017-03-28 | 2017-03-29 | 1 | 2017-03-29 | [14 empty] | 2017-09-01 | 2017-09-01 |  | Y
Central Hudson |  | SolarCity | CH-07160 | Newburgh | New Windsor | Orange | 12553 | G | 4095 | Bethlehem Rd | N |  | 6.6 | [13 empty] | NM | N | DELTA SOLIVIA 6.6 | 2017-03-14 | 2017-03-17 | 3 | 2017-03-17 | [14 empty] | 2017-04-20 | 2017-05-02 |  | Y
Central Hudson |  | Trinity Solar | CH-08444 | Fishkill | Garrison | Putnam | 10524 | G | 8066 | Merritt Park | N |  | 6 | [13 empty] | NM | N | SOLAREDGHE SE6000A | 2017-03-14 | 2017-03-27 | 9 | 2017-03-27 | [14 empty] | 2017-06-08 | 2017-06-13 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08756 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8091 | Fishkill Plains | N |  | 7.31 | [13 empty] | NM | N | 34 ENPHASE M215 | 2017-03-14 | 2017-03-21 | 5 | 2017-03-21 | [14 empty] | 2017-05-09 | 2017-05-09 |  | Y
Central Hudson |  | SolarCity | CH-07179 | Newburgh | New Windsor | Orange | 12553 | G | 4095 | Bethlehem Rd | N |  | 15.8 | [13 empty] | NM | N | DELTA SOLIVIA 7.6 DELTA SOLIVIA 5.2 | 2017-03-27 | 2017-03-28 | 1 | 2017-03-28 | [14 empty] | 2017-07-13 | 2017-07-13 |  | Y
Central Hudson |  | New York State Solar Farm | CH-00377 | Newburgh | Highland | Ulster | 12528 | G | 5081 | Highland | N |  | 5.76 | [13 empty] | NM | N | 18 SUNPOWER SPR320 345 | 2017-03-16 | 2017-03-22 | 4 | 2017-03-22 | [14 empty] | 2017-04-20 | 2017-04-20 |  | Y
Central Hudson |  | New York State Solar Farm | CH-00435 | Newburgh | Newburgh | Orange | 12550 | G | 402 | Montgomery St | N |  | 7.68 | [13 empty] | NM | N | 24 SUNPOWER SPRX21 345 | 2017-03-16 | 2017-03-22 | 4 | 2017-03-22 | [14 empty] | 2017-05-08 | 2017-05-24 |  | Y
Central Hudson |  | SolarCity | CH-06094 | Fishkill | Fishkill | Dutchess | 12524 | G | 8011 | Forgebrook | N |  | 11.4 | [13 empty] | NM | N | SOLAREDGE SE11400 | 2017-03-16 | 2017-03-22 | 4 | 2017-03-22 | [14 empty] | 2017-05-04 | 2017-05-05 |  | Y
Central Hudson |  | SolarCity | CH-06800 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8091 | Fishkill Plains | N |  | 6.6 | [13 empty] | NM | N | DELTA SOLIVIA 6.6 | 2017-03-16 | 2017-03-22 | 4 | 2017-03-22 | [14 empty] | 2017-05-23 | 2017-05-23 |  | Y
Central Hudson |  | SolarCity | CH-07127 | Newburgh | New Windsor | Orange | 12553 | G | 4097 | Bethlehem Rd | N |  | 7.6 | [13 empty] | NM | N | DELTA SOLIVIA 7.6 | 2017-03-16 | 2017-03-22 | 4 | 2017-03-22 | [14 empty] | 2017-04-12 | 2017-04-12 |  | Y
Central Hudson |  | Apex Solar Power | CH-00017 | Kingston | Claryvl | Sullivan | 12725 | G | 3091 | Neversink | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE7600 | 2017-03-27 | 2017-03-28 | 1 | 2017-03-28 | [14 empty] | 2017-05-01 | 2017-05-01 |  | Y
Central Hudson |  | SolarCity | CH-06695 | Poughkeepsie | Salt Pt | Dutchess | 12578 | G | 7011 | Hibernia | N |  | 13.2 | [13 empty] | NM | N | 2 DELTA SOLVIAI 6.6 | 2017-03-17 | 2017-03-22 | 3 | 2017-03-22 | [14 empty] | 2017-05-09 | 2017-05-15 |  | Y
Central Hudson |  | SolarCity | CH-07546 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6051 | Todd Hill | N |  | 10 | [13 empty] | NM | N | SOLAREDGE SE10000A | 2017-03-17 | 2017-03-22 | 3 | 2017-03-22 | [14 empty] | 2017-10-10 | 2017-10-10 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08612 | Fishkill | Beacon | Dutchess | 12508 | G | 8087 | Tioronda | N |  | 7.31 | [13 empty] | NM | N | 34 ENPHASE M215 | 2017-03-17 | 2017-03-22 | 3 | 2017-03-22 | [14 empty] | 2017-08-24 | 2017-08-24 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08736 | Catskill | W Coxsackie | Greene | 12192 | G | 1076 | Coxsackie | N |  | 8.81 | [13 empty] | NM | N | 41 ENPHASE M215 | 2017-03-17 | 2017-03-22 | 3 | 2017-03-22 | [14 empty] | 2017-05-11 | 2017-05-18 |  | Y
Central Hudson |  | US Energy Concierge, Inc. | CH-09734 | Fishkill | Garrison | Putnam | 10524 | G | 8066 | Merritt Park | N |  | 10 | [13 empty] | NM | N | SOLAREDGE SE10000 | 2017-03-27 | 2017-03-28 | 1 | 2017-03-28 | [8 empty] | 350 | 350 |  | 2017-06-02 | 2017-06-02 | 2017-07-27 | 2017-07-28 | 2017-07-28 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-00147 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8094 | Fishkill Plains | N |  | 7.36 | [13 empty] | NM | N | 23 SUNPOWER SPR X21 345 | 2017-03-20 | 2017-03-27 | 5 | 2017-03-27 | [14 empty] | 2017-06-12 | 2017-06-15 |  | Y
Central Hudson |  | Apex Solar Power | CH-00701 | Kingston | Saugerties | Ulster | 12477 | G | 2015 | Lincoln Park | N |  | 10 | [13 empty] | NM | N | SOLAREDGE SE10000 | 2017-03-27 | 2017-03-28 | 1 | 2017-03-28 | [14 empty] | 2017-04-26 | 2017-04-26 |  | Y
Central Hudson |  | SolarCity | CH-05205 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8094 | Fishkill Plains | N |  | 10 | [13 empty] | NM | N | SOLAREDGE SE10000 | 2017-03-20 | 2017-03-23 | 3 | 2017-03-23 | [14 empty] | 2017-05-02 | 2017-05-02 |  | Y
Central Hudson |  | SolarCity | CH-05825 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6065 | Inwood Ave | N |  | 3.6 | [13 empty] | NM | N | ABB PVI 3.6 | 2017-03-28 | 2017-03-29 | 1 | 2017-03-29 | [14 empty] | 2017-04-28 | 2017-05-01 |  | Y
Central Hudson |  | SolarCity | CH-06067 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8092 | Fishkill Plains | N |  | 3.6 | [13 empty] | NM | N | ABB PVI 3.6 | 2017-03-20 | 2017-03-23 | 3 | 2017-03-23 | [14 empty] | 2017-05-04 | 2017-05-05 |  | Y
Central Hudson |  | Trinity Solar | CH-08370 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8045 | Myers Corners | N |  | 10 | [13 empty] | NM | N | SOLAREDGE SE10000 | 2017-03-20 | 2017-03-28 | 6 | 2017-03-28 | [14 empty] | 2017-09-05 | 2017-09-12 |  | Y
Central Hudson |  | Trinity Solar | CH-08511 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8093 | Fishkill Plains | N |  | 16.4 | [13 empty] | NM | N | SOLAREDGE SE11400 SOLAREDGE SE5000 | 2017-03-28 | 2017-03-29 | 1 | 2017-03-29 | [14 empty] | 2017-05-05 | 2017-05-05 |  | Y
Central Hudson |  | Trinity Solar | CH-08565 | Fishkill | Beacon | Dutchess | 12508 | G | 8013 | Forgebrook | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A | 2017-03-20 | 2017-03-28 | 6 | 2017-03-28 | [14 empty] | 2017-06-13 | 2017-06-22 |  | Y
Central Hudson |  | SunDog Solar | CH-09166 | Catskill | Hensonvl | Greene | 12439 | E | 2081 | Hunter | N | CH-09139 | 5 | [13 empty] | NM | N | SOLAREDGE SE5000 | 2017-03-31 | 2017-04-05 | 3 | 2017-04-05 | [14 empty] | 2017-05-23 | 2017-05-23 |  | Y
Central Hudson |  | Sungevity Inc | CH-09513 | Newburgh |  |  | 12553 | G | 4095 | Bethlehem Rd | TBD |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE7600 | 2017-03-24 | 2017-03-27 | 1 | 2017-03-27 | [17 empty] | W
Central Hudson |  | Empire Solar Solutions | CH-00104 | Newburgh | Newburgh | Orange | 12550 | G | 4051 | Union Ave | N |  | 5 | [13 empty] | NM | N | SOLAREDGE 5000 | 2017-06-27 | 2017-06-28 | 1 | 2017-06-28 | [14 empty] | 2017-07-14 | 2017-07-20 |  | Y
Central Hudson |  | SolarCity | CH-06675 | Poughkeepsie | Staatsburg | Dutchess | 12580 | G | 7011 | Hibernia | N |  | 3 | [13 empty] | NM | N | ABB PVI 3 | 2017-03-29 | 2017-03-30 | 1 | 2017-03-30 | [14 empty] | 2017-04-19 | 2017-04-19 |  | Y
Central Hudson |  | SolarCity | CH-07120 | Newburgh | Cornwall-Hdsn | Orange | 12520 | G | 4043 | Union Ave | N |  | 10 | [13 empty] | NM | N | SOLAREDGE SE10000 | 2017-03-21 | 2017-03-24 | 3 | 2017-03-24 | [14 empty] | 2017-05-17 | 2017-05-18 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-00150 | Fishkill | Fishkill | Dutchess | 12524 | G | 8094 | Fishkill Plains | N |  | 6.4 | [13 empty] | NM | N | 20 SUNPOWER SPR X21 345 | 2017-03-22 | 2017-03-24 | 2 | 2017-03-24 | [14 empty] | 2017-05-17 | 2017-05-18 |  | Y
Central Hudson |  | Active Solar Development | CH-00633 | Kingston | Kingston | Ulster | 12401 | G | 1021 | East Kingston | N |  | 360 | [13 empty] | RNM | N | 8 SUNGROW 60KU | 2017-04-13 | 2017-04-21 | 5 | 2017-04-21 | 2017-04-21 | 2017-05-12 | 15 | [5 empty] | 31529.5 | 17504.95 |  | 2017-07-13 | 2017-07-13 | 2017-12-29 | 2018-12-20 | 2018-12-20 | 2019-03-20 | Y
Central Hudson |  | Hudson Solar | CH-02517 | Poughkeepsie |  |  | 12585 | G | 6057 | Todd Hill | TBD |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE7600 | 2017-03-22 | 2017-03-24 | 2 | 2017-03-24 | [17 empty] | W
Central Hudson |  | SolarCity | CH-06078 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8092 | Fishkill Plains | N |  | 7.6 | [13 empty] | NM | N | DELTA SOLIVIA 7.6 | 2017-03-22 | 2017-03-24 | 2 | 2017-03-24 | [14 empty] | 2017-05-26 | 2017-06-01 |  | Y
Central Hudson |  | SolarCity | CH-06538 | Kingston | Woodstock | Ulster | 12498 | G | 3012 | Woodstock | N |  | 5.2 | [13 empty] | NM | N | DELTA SOLIVIA 5.2 | 2017-03-22 | 2017-03-24 | 2 | 2017-03-24 | [14 empty] | 2017-04-25 | 2017-04-25 |  | Y
Central Hudson |  | SolarCity | CH-07348 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8046 | Myers Corners | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A | 2017-03-22 | 2017-03-24 | 2 | 2017-03-24 | [14 empty] | 2017-10-12 | 2017-10-18 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08703 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8071 | Shenandoah | N |  | 12.68 | [13 empty] | NM | N | 59 ENPHASE M215 | 2017-04-27 | 2017-04-28 | 1 | 2017-04-28 | [14 empty] | 2017-12-11 | 2017-12-11 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08810 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8072 | Shenandoah | N |  | 4.73 | [13 empty] | NM | N | 22 ENPHASE M215 | 2017-03-22 | 2017-03-24 | 2 | 2017-03-24 | [14 empty] | 2017-06-13 | 2017-06-20 |  | Y
Central Hudson |  | Hudson Solar | CH-01259 | Catskill | Tannersvl | Greene | 12485 | G | 2385 | Lawrenceville | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE7600 | 2017-03-23 | 2017-03-24 | 1 | 2017-03-24 | [14 empty] | 2017-05-17 | 2017-05-24 |  | Y
Central Hudson |  | Hudson Solar | CH-02535 | Poughkeepsie |  |  | 12572 | G | 7054 | Rhinebeck | TBD |  | 66.6 | [13 empty] | CDG | N | 2 SOLAREDGE SE33.3 | 2017-04-05 | 2017-04-17 | 7 | 2017-04-17 | 2017-04-17 | 2017-05-08 | 15 | [14 empty] | W
Central Hudson |  | SolarCity | CH-05452 | Fishkill |  |  | 12524 | G | 8055 | North Chelsea | TBD |  | 7.6 | [13 empty] | NM | N | DELTA SOLIVIA 7.6 | 2017-03-23 | 2017-03-24 | 1 | 2017-03-24 | [17 empty] | W
Central Hudson |  | Trinity Solar | CH-08495 | Fishkill |  |  | 12533 | G | 8091 | Fishkill Plains | TBD |  | 3.8 | [13 empty] | NM | N | SOLAREDGE SE3800 | 2017-03-29 | 2017-03-30 | 1 | 2017-03-30 | [17 empty] | W
Central Hudson |  | Trinity Solar | CH-08548 | Fishkill | Putnam Valley | Putnam | 10524 | G | 8066 | Merritt Park | N |  | 13.8 | [13 empty] | NM | N | SOLAREDGE SE 10000 SOLAREDGE SE3800 | 2017-03-23 | 2017-03-28 | 3 | 2017-03-28 | [14 empty] | 2017-06-02 | 2017-06-12 |  | Y
Central Hudson |  | Trinity Solar | CH-08550 | Newburgh | Newburgh | Orange | 12550 | G | 4047 | Union Ave | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000 | 2017-03-23 | 2017-03-28 | 3 | 2017-03-28 | [14 empty] | 2017-05-02 | 2017-05-08 |  | Y
Central Hudson |  | Sunrise Solar Solutions, LLC | CH-09648 | Poughkeepsie | Millbrook | Dutchess | 12545 | G | 7025 | Tinkertown | N |  | 66.6 | [13 empty] | NM | N | 2 SOLAREDGE 33.3 | 2017-05-08 | 2017-05-08 | 0 | 2017-05-08 | 2017-05-08 | 2017-05-26 | 14 | [14 empty] | W
Central Hudson |  | Infinity Solar Systems | CH-00220 | Fishkill | Fishkill | Dutchess | 12524 | G | 8094 | Fishkill Plains | N |  | 8.32 | [13 empty] | NM | N | 26 SUNPOWER SPR X21 345 | 2017-03-24 | 2017-03-27 | 1 | 2017-03-27 | [14 empty] | 2017-05-09 | 2017-05-09 |  | Y
Central Hudson |  | Hudson Solar | CH-01865 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7062 | Milan | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000 | 2017-03-24 | 2017-03-27 | 1 | 2017-03-27 | [14 empty] | 2017-06-06 | 2017-06-08 |  | Y
Central Hudson |  | SolarCity | CH-05948 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7054 | Rhinebeck | N |  | 6 | [13 empty] | NM | N | ABB PVI 6000 | 2017-03-27 | 2017-03-28 | 1 | 2017-03-28 | [14 empty] | 2017-05-04 | 2017-05-05 |  | Y
Central Hudson |  | SolarCity | CH-06667 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6065 | Inwood Ave | N |  | 6.6 | [13 empty] | NM | N | DELTA SOLIVIA 6.6 | 2017-03-27 | 2017-03-28 | 1 | 2017-03-28 | [14 empty] | 2017-05-15 | 2017-05-15 |  | Y
Central Hudson |  | SolarCity | CH-07453 | Newburgh | Marlboro | Ulster | 12542 | G | 5004 | Marlboro | N |  | 13.2 | [13 empty] | NM | N | 2 DELTA SOLIVIA 6.6 | 2017-03-27 | 2017-03-28 | 1 | 2017-03-28 | [14 empty] | 2017-04-28 | 2017-05-04 |  | Y
Central Hudson |  | SolarCity | CH-07479 | Newburgh | New Windsor | Orange | 12553 | G | 4095 | Bethlehem Rd | N |  | 6.6 | [13 empty] | NM | N | DELTA SOLIVIA 6.6 | 2017-03-27 | 2017-03-28 | 1 | 2017-03-28 | [14 empty] | 2017-04-24 | 2017-04-25 |  | Y
Central Hudson |  | SolarCity | CH-07840 | Fishkill |  |  | 12508 | G | 8018 | Forgebrook | N |  | 5.2 | [13 empty] | NM | N | DELTA SOLIVIA 5.2 | 2017-03-27 | 2017-04-10 | 10 | 2017-04-10 | [17 empty] | W
Central Hudson |  | Trinity Solar | CH-08559 | Poughkeepsie | Lagrangevl | Dutchess | 12540 | G | 6055 | Todd Hill | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A | 2017-03-27 | 2017-03-28 | 1 | 2017-03-28 | [14 empty] | 2017-05-30 | 2017-06-06 |  | Y
Central Hudson |  | Trinity Solar | CH-08416 | Poughkeepsie | Lagrangevl | Dutchess | 12540 | G | 6057 | Todd Hill | N |  | 10 | [13 empty] | NM | N | SOLAREDGE SE10000 | 2017-04-11 | 2017-04-19 | 5 | 2017-04-19 | [14 empty] | 2017-05-30 | 2017-06-01 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08723 | Catskill |  |  | 12451 | G | 2005 | North Catskill | TBD |  | 2.58 | [13 empty] | NM | N | 12 ENPHASE M215 | 2017-03-28 | 2017-03-29 | 1 | 2017-03-29 | [17 empty] | W
Central Hudson |  | Solar Alchemy | CH-09007 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7042 | Staatsburg | N | CH-09002 | 3.25 | [13 empty] | NM | N | 14 ENPHASE M250 | 2017-03-30 | 2017-03-31 | 1 | 2017-03-31 | [8 empty] | 350 | 350 |  | 2017-04-10 | 2017-04-10 | 2017-05-11 | 2017-06-07 | 2017-06-08 |  | Y
Central Hudson |  | Lotus Energy Inc. | CH-00339 | Kingston | Stone Ridge | Ulster | 12484 | G | 3023 | High Falls | N |  | 7.7 | [13 empty] | NM | N | SMA SB7700 | 2017-03-29 | 2017-03-30 | 1 | 2017-03-30 | [14 empty] | 2017-05-12 | 2017-05-15 |  | Y
Central Hudson |  | Lotus Energy Inc. | CH-00342 | Newburgh | Newburgh | Orange | 12550 | G | 5001 | Marlboro | N |  | 4.8 | [13 empty] | NM | N | 15 SUNPOWER SPR-X22-335-C-AC | 2017-03-29 | 2017-03-30 | 1 | 2017-03-30 | [14 empty] | 2017-11-22 | 2017-11-27 |  | Y
Central Hudson |  | SolarCity | CH-06669 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6062 | Inwood Ave | N |  | 3 | [13 empty] | NM | N | ABB PVI 3 | 2017-03-29 | 2017-03-30 | 1 | 2017-03-30 | [14 empty] | 2017-07-11 | 2017-07-11 |  | Y
Central Hudson |  | Solitude Solar, LLC | CH-09076 | Catskill |  |  | 12485 | G | 2385 | Lawrenceville | TBD |  | 1980 | [13 empty] | CDG | N | 66 SMA 30000TL | 2017-05-01 | 2017-05-15 | 10 | 2017-05-15 | 2017-05-15 | 2017-06-05 | 14 | [14 empty] | W
Central Hudson |  | Sunrise Solar Solutions, LLC | CH-09654 | Poughkeepsie | Millbrook | Dutchess | 12545 | G | 7025 | Tinkertown | N |  | 60 | [13 empty] | CDG | N | 1 Sungrow Power Supply SG60KU-M 2 SOLAREDGE 33.3 | 2017-05-08 | 2017-05-08 | 0 | 2017-05-08 | 2017-05-08 | 2017-05-26 | 14 | [14 empty] | W
Central Hudson |  | Sunrise Solar Solutions, LLC | CH-09655 | Poughkeepsie | Millbrook | Dutchess | 12545 | G | 7025 | Tinkertown | N |  | 540 | [13 empty] | RNM | N | 9 Sungrow Power Supply SG60KU 17 SOLAREDGE 33.3 | 2017-05-08 | 2017-05-08 | 0 | 2017-05-08 | 2017-05-08 | 2017-05-26 | 14 | [11 empty] | 2019-12-20 | 2019-12-20 |  | Y
Central Hudson |  | Apex Solar Power | CH-00016 | Catskill | Westerlo | Albany | 12193 | G | 1091 | Westerlo | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000 | 2017-04-03 | 2017-04-05 | 2 | 2017-04-05 | [14 empty] | 2017-05-12 | 2017-05-12 |  | Y
Central Hudson |  | SolarCity | CH-05686 | Kingston | West Shokan | Ulster | 12494 | G | 3011 | Woodstock | N |  | 3.8 | [13 empty] | NM | N | DELTA SOLIVIA 3.8 | 2017-03-30 | 2017-03-31 | 1 | 2017-03-31 | [14 empty] | 2017-04-05 | 2017-04-06 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08629 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8071 | Shenandoah | N |  | 5.16 | [13 empty] | NM | N | 24 ENPHASE M215 | 2017-03-30 | 2017-03-31 | 1 | 2017-03-31 | [14 empty] | 2017-11-09 | 2017-11-14 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-00032 | Newburgh | Marlboro | Ulster | 12542 | G | 5004 | Marlboro | N |  | 12 | [13 empty] | NM | N | 2 SOLAREDGE 6000 | 2017-04-05 | 2017-04-06 | 1 | 2017-04-06 | [14 empty] | 2017-04-25 | 2017-04-27 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00980 | Kingston | Kerhonkson | Ulster | 12446 | G | 3081 | Kerhonkson | N |  | 7 | [13 empty] | NM | N | 28 ENPHASE M250 | 2017-03-31 | 2017-04-04 | 2 | 2017-04-04 | [14 empty] | 2017-04-18 | 2017-04-18 |  | Y
Central Hudson |  | District Sun | CH-01081 | Kingston |  |  | 12446 | G | 3071 | Honk Falls | TBD |  | 148 | [13 empty] | CDG | N | 2 CPS 60KTL US-480 1 CPS 28KTLY US-480 | 2017-05-03 | 2017-05-15 | 8 | 2017-05-15 | 2017-05-15 | 2017-06-05 | 14 | [14 empty] | W
Central Hudson |  | SolarCity | CH-05851 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 6074 | East Park | N |  | 6.6 | [13 empty] | NM | N | DELTA SOLIVIA 6.6 | 2017-03-31 | 2017-04-04 | 2 | 2017-04-04 | [14 empty] | 2017-05-04 | 2017-05-05 |  | Y
Central Hudson |  | SolarCity | CH-06231 | Newburgh | Newburgh | Orange | 12550 | G | 4015 | West Balmville | N |  | 10.4 | [13 empty] | NM | N | 2 DELTA SOLIVIA 5.2 | 2017-03-31 | 2017-04-04 | 2 | 2017-04-04 | [14 empty] | 2017-06-13 | 2017-06-20 |  | Y
Central Hudson |  | SolarCity | CH-06240 | Newburgh | Newburgh | Orange | 12550 | G | 4014 | West Balmville | N |  | 7.6 | [13 empty] | NM | N | DELTA SOLIVIA 7.6 | 2017-04-18 | 2017-04-24 | 4 | 2017-04-24 | [14 empty] | 2018-03-06 | 2018-03-13 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-00054 | Fishkill | Stormvl | Dutchess | 12582 | G | 8071 | Shenandoah | N |  | 22.8 | [13 empty] | NM | N | 2 SOLAREDGE 11400 | 2017-04-05 | 2017-04-06 | 1 | 2017-04-06 | [8 empty] | 350 | 350 |  | 2017-06-09 | 2017-06-09 | 2017-09-12 | 2017-10-09 | 2017-10-09 |  | Y
Central Hudson |  | Kasselman Solar | CH-00226 | Catskill | Surprise | Greene | 12176 | G | 2061 | Freehold | N |  | 6.75 | [13 empty] | NM | N | 27 ENPHASE M250 | 2017-04-26 | 2017-04-27 | 1 | 2017-04-27 | [14 empty] | 2017-05-11 | 2017-05-15 |  | Y
Central Hudson |  | New York State Solar Farm | CH-00363 | Newburgh | Highland | Ulster | 12528 | G | 5083 | Highland | N |  | 19.52 | [13 empty] | NM | N | 61 SUNPOWER SPR E20 327 | 2017-04-18 | 2017-04-24 | 4 | 2017-04-24 | [14 empty] | 2017-04-26 | 2017-04-26 |  | Y
Central Hudson |  | New York State Solar Farm | CH-00453 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8023 | Knapps Corners | N |  | 5.12 | [13 empty] | NM | N | 16 SUNPOWER SPR X22 360 | 2017-04-03 | 2017-04-05 | 2 | 2017-04-05 | [14 empty] | 2017-04-26 | 2017-05-05 |  | Y
Central Hudson |  | SolarCity | CH-05445 | Kingston | Ulster Pk | Ulster | 12487 | G | 1014 | Boulevard | N |  | 6.6 | [13 empty] | NM | N | DELTA SOLIVIA 6.6 | 2017-04-03 | 2017-04-05 | 2 | 2017-04-05 | [14 empty] | 2017-05-09 | 2017-05-15 |  | Y
Central Hudson |  | SolarCity | CH-06105 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8056 | North Chelsea | N |  | 9 | [13 empty] | NM | N | DELTA SOLIVIA 5.2 DELTA SOLIVIA 3.8 | 2017-04-24 | 2017-04-26 | 2 | 2017-04-26 | [14 empty] | 2017-05-09 | 2017-05-15 |  | Y
Central Hudson |  | SolarCity | CH-07406 | Fishkill | Putnam Valley | Putnam | 10524 | G | 8066 | Merritt Park | N |  | 5.2 | [13 empty] | NM | N | DELTA SOLIVIA 5.2 | 2017-04-13 | 2017-04-19 | 3 | 2017-04-19 | [14 empty] | 2017-05-09 | 2017-05-15 |  | Y
Central Hudson |  | SolarCity | CH-07610 | Newburgh | Wallkill | Ulster | 12589 | G | 5041 | East Walden | N |  | 11.4 | [13 empty] | NM | N | DELTA SOLIVIA 7.6 DELTA SOLIVIA 3.8 | 2017-04-03 | 2017-04-12 | 7 | 2017-04-12 | [8 empty] | 350 | 350 |  | 2017-06-05 | 2017-06-05 | 2017-07-17 | 2017-07-17 | 2017-07-18 |  | Y
Central Hudson |  | SolarCity | CH-07734 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6011 | Sand Dock | N |  | 5.2 | [13 empty] | NM | N | DELTA SOLIVIA 5.2 | 2017-04-03 | 2017-04-05 | 2 | 2017-04-05 | [14 empty] | 2017-05-22 | 2017-05-31 |  | Y
Central Hudson |  | Trinity Solar | CH-08492 | Poughkeepsie | Pine Plns | Dutchess | 12567 | G | 7091 | Pulvers Corners | N |  | 13 | [13 empty] | NM | N | SOLAREDGE SE10000 SOLAREDGE SE3000 | 2017-04-03 | 2017-04-12 | 7 | 2017-04-12 | [14 empty] | 2017-06-21 | 2017-06-28 |  | Y
Central Hudson |  | Trinity Solar | CH-08582 | Catskill |  |  | 12436 | G | 2385 | Lawrenceville | TBD |  | 3 | [13 empty] | NM | N | SOLAREDGE SE3000 | 2017-04-03 | 2017-04-12 | 7 | 2017-04-12 | [17 empty] | W
Central Hudson |  | Solar Generation | CH-09986 | Kingston | Ulster Park |  | 12487 | G | 3041 | Sturgeon Pool | N |  | 6 | [13 empty] | NM | N |  | 2017-04-11 | [18 empty] | 2017-04-11 |  | W
Central Hudson |  | New York State Solar Farm | CH-00390 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6003 | Reynolds Hill | N |  | 8 | [13 empty] | NM | N | 25 SUNPOWER SPR X22 360 | 2017-04-06 | 2017-04-10 | 2 | 2017-04-10 | [14 empty] | 2017-06-08 | 2017-06-13 |  | Y
Central Hudson |  | Hudson Solar | CH-01847 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7051 | Rhinebeck | N |  | 10 | [13 empty] | NM | N | SOLAREDGE SE10000 | 2017-04-04 | 2017-04-06 | 2 | 2017-04-06 | [14 empty] | 2017-05-25 | 2017-05-26 |  | Y
Central Hudson |  | SolarCity | CH-06237 | Newburgh | Newburgh | Orange | 12550 | G | 4014 | West Balmville | N |  | 7.6 | [13 empty] | NM | N | DELTA SOLIVIA 7.6 | 2017-04-04 | 2017-04-06 | 2 | 2017-04-06 | [14 empty] | 2017-09-05 | 2017-09-06 |  | Y
Central Hudson |  | EnterSolar LLC | CH-03353 | Fishkill |  |  | 12590 | G | 8043 | Myers Corners | TBD |  | 1980 | [13 empty] | CDG | N | 33 YASKAWA SOLECTRIA PVI 60TL | 2017-04-17 | 2017-04-21 | 4 | 2017-04-21 | 2017-04-21 | 2017-05-12 | 15 |  |  |  |  | 20000 | [9 empty] | W
Central Hudson |  | EnterSolar LLC | CH-03354 | Fishkill |  |  | 12590 | G | 8043 | Myers Corners | TBD |  | 1980 | [13 empty] | CDG | N | 33 YASKAWA SOLECTRIA PVI 60TL | 2017-04-17 | 2017-04-21 | 4 | 2017-04-21 | 2017-04-21 | 2017-05-12 | 15 |  |  |  |  | 20000 | [9 empty] | W
Central Hudson |  | Kasselman Solar | CH-00230 | Newburgh | Wallkill |  | 12589 | G | 5013 | Modena | TBD |  | 7 | [13 empty] | NM | N | 28 ENPHASE M250 | 2017-04-26 | 2017-04-27 | 1 | 2017-04-27 | [17 empty] | W
Central Hudson |  | SolarCity | CH-07834 | Newburgh | Montgomery | Orange | 12549 | G | 5073 | Montgomery | Y | CH-07751 | 6 | 6 | [12 empty] | NM | N | SOLARCITY DELTA H61TeslaH6 Hybrid Inverter | 2017-05-25 | 2017-06-07 | 8 | 2017-06-07 | [14 empty] | 2017-09-22 | 2017-09-27 |  | Y
Central Hudson |  | Lighthouse Solar | CH-00268 | Kingston | W Hurley | Ulster | 12491 | G | 3014 | Woodstock | N |  | 3.8 | [13 empty] | NM | N | SOLAREDGE 3.8 | 2017-04-20 | 2017-04-24 | 2 | 2017-04-24 | [14 empty] | 2017-07-14 | 2017-07-14 |  | Y
Central Hudson |  | New York State Solar Farm | CH-00438 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N | CH-00438 | 2.88 | [13 empty] | NM | N | 9 SUNPOWER SPR X21 345 | 2017-04-06 | 2017-04-10 | 2 | 2017-04-10 | [14 empty] | 2017-04-19 | 2017-04-28 |  | Y
Central Hudson |  | New York State Solar Farm | CH-00444 | Newburgh | Wallkill | Ulster | 12589 | G | 5041 | East Walden | N |  | 5.76 | [13 empty] | NM | N | 18 SUNPOWER SPR X22 360 | 2017-04-06 | 2017-04-10 | 2 | 2017-04-10 | [14 empty] | 2017-05-22 | 2017-05-22 |  | Y
Central Hudson |  | New York State Solar Farm | CH-00447 | Kingston | Kerhonkson | Ulster | 12446 | G | 3081 | Kerhonkson | N |  | 6.4 | [13 empty] | NM | N | 20 SUNPOWER SPR E20 327 | 2017-04-06 | 2017-04-10 | 2 | 2017-04-10 | [14 empty] | 2017-06-20 | 2017-06-21 |  | Y
Central Hudson |  | New York State Solar Farm | CH-00455 | Newburgh | Newburgh | Orange | 12550 | G | 4014 | West Balmville | N |  | 6.08 | [13 empty] | NM | N | 19 SUNPOWER SPR E20 327 | 2017-04-24 | 2017-04-26 | 2 | 2017-04-26 | [14 empty] | 2017-05-02 | 2017-05-09 |  | Y
Central Hudson |  | New York State Solar Farm | CH-00467 | Newburgh | Newburgh | Orange | 12550 | G | 410 | Montgomery St | N |  | 10.24 | [13 empty] | NM | N | 32 SUNPOWER SPR X21 345 | 2017-04-06 | 2017-04-10 | 2 | 2017-04-10 | [14 empty] | 2017-08-29 | 2017-08-30 |  | Y
Central Hudson |  | Hudson Solar | CH-01423 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8091 | Fishkill Plains | N |  | 20 | [13 empty] | NM | N | 2SolaredgeSE 10000A-US (277V) | 2017-04-06 | 2017-04-10 | 2 | 2017-04-10 | [14 empty] | 2018-06-15 | 2018-06-28 |  | Y
Central Hudson |  | SolarCity | CH-05342 | Newburgh | Newburgh | Orange | 12550 | G | 4054 | Union Ave | N |  | 3 | [13 empty] | NM | N | ABB 3.0 | 2017-04-06 | 2017-04-10 | 2 | 2017-04-10 | [14 empty] | 2017-05-23 | 2017-05-31 |  | Y
Central Hudson |  | SolarCity | CH-05363 | Newburgh | Highland Mls | Orange | 10930 | G | 4093 | Bethlehem Rd | N |  | 13.2 | [13 empty] | NM | N | 2 DELTA SOLIVIA 6.6 | 2017-04-06 | 2017-04-11 | 3 | 2017-04-11 | [14 empty] | 2017-07-10 | 2017-07-17 |  | Y
Central Hudson |  | SolarCity | CH-06287 | Newburgh | New Windsor | Orange | 12553 | G | 4046 | Union Ave | N |  | 10.4 | [13 empty] | NM | N | DELTA SOLIVIA 6.6 DELTA SOLIVIA 3.8 | 2017-04-06 | 2017-04-10 | 2 | 2017-04-10 | [14 empty] | 2017-05-23 | 2017-05-24 |  | Y
Central Hudson |  | SolarCity | CH-06917 | Fishkill | Stormvl | Dutchess | 12582 | G | 8093 | Fishkill Plains | N |  | 11.4 | [13 empty] | NM | N | DELTA SOLIVIA 7.6 DELTA SOLVIIA 3.8 | 2017-04-06 | 2017-04-10 | 2 | 2017-04-10 | [14 empty] | 2017-06-19 | 2017-06-20 |  | Y
Central Hudson |  | SolarCity | CH-07015 | Newburgh | Newburgh | Orange | 12550 | G | 4054 | Union Ave | N |  | 3 | [13 empty] | NM | N | ABB PVI 3.0 | 2017-04-06 | 2017-04-10 | 2 | 2017-04-10 | [14 empty] | 2017-05-23 | 2017-05-31 |  | Y
Central Hudson |  | SolarCity | CH-07220 | Kingston | Woodstock | Ulster | 12498 | G | 3013 | Woodstock | N |  | 10.4 | [13 empty] | NM | N | 2 DELTA SOLIVIA 5.2 | 2017-04-06 | 2017-04-10 | 2 | 2017-04-10 | [14 empty] | 2017-05-31 | 2017-06-01 |  | Y
Central Hudson |  | SolarCity | CH-07401 | Fishkill | Beacon | Dutchess | 12508 | G | 8085 | Tioronda | N |  | 3.8 | [13 empty] | NM | N | SOLAREDGE SE3800 | 2017-04-06 | 2017-04-10 | 2 | 2017-04-10 | [14 empty] | 2017-06-20 | 2017-06-21 |  | Y
Central Hudson |  | SolarCity | CH-07593 | Newburgh | Newburgh | Orange | 12550 | G | 4013 | West Balmville | N |  | 3.6 | [13 empty] | NM | N | ABB PVI 3.6 | 2017-04-06 | 2017-04-10 | 2 | 2017-04-10 | [14 empty] | 2017-05-24 | 2017-06-01 |  | Y
Central Hudson |  | Trinity Solar | CH-08547 | Fishkill | Putnam Valley | Putnam | 10524 | G | 8066 | Merritt Park | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE7600 | 2017-04-06 | 2017-04-12 | 4 | 2017-04-12 | [14 empty] | 2017-08-07 | 2017-08-07 |  | Y
Central Hudson |  | Trinity Solar | CH-08572 | Kingston | Kingston | Ulster | 12401 | G | 1024 | East Kingston | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000 | 2017-04-06 | 2017-04-12 | 4 | 2017-04-12 | [14 empty] | 2017-09-20 | 2017-09-20 |  | Y
Central Hudson |  | 212 Solar Development, LLC | CH-00598 | Kingston | Kerhonkson | Ulster | 12446 | G | 3081 | Kerhonkson | N |  | 4000 | [13 empty] | CDG | Y | SUNGROW SG125HV (32) | 2017-05-02 | 2017-05-02 | 0 | 2017-05-02 | 2017-05-02 | 2017-05-22 | 14 | 2017-07-17 | 2017-08-28 | 2017-11-21 | 60 | 32656.31 | 448616 | 318030.04 | 2017-12-14 | 2018-06-04 | 2018-06-04 | 2019-08-14 | 2019-10-04 | 2019-10-04 | 2020-01-03 | Y | Y | CH-00598, and CH-00599 consolidated to one 4 MW project. Combined application number is CH-00598.
Central Hudson |  | 212 Solar Development, LLC | CH-00599 | Kingston | Kerhonkson |  | 12446 | G | 3081 | Kerhonkson | TBD |  | 2000 | [13 empty] | CDG | Y | SUNGROW SG125HV (16) | 2017-05-02 | 2017-05-02 | 0 | 2017-05-02 | 2017-05-02 | 2017-05-22 | 14 | 2017-07-17 | 2017-08-28 | 2017-11-21 | 60 | 22500 | 226099.5 |  | 2017-12-14 | 2018-06-04 | 2018-06-04 |  |  |  |  | W
Central Hudson |  | SolarCity | CH-06463 | Catskill | Alcove | Albany | 12007 | G | 1081 | New Baltimore | N |  | 4.2 | [13 empty] | NM | N | ABB PVI 4.2 | 2017-04-07 | 2017-04-10 | 1 | 2017-04-10 | [14 empty] | 2017-05-22 | 2017-06-08 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08762 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8071 | Shenandoah | N |  | 9.89 | [13 empty] | NM | N | 46 ENPHASE M215 | 2017-04-07 | 2017-04-10 | 1 | 2017-04-10 | [14 empty] | 2017-07-25 | 2017-08-03 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08820 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8094 | Fishkill Plains | N |  | 7.31 | [13 empty] | NM | N | 34 ENPHASE M215 | 2017-04-07 | 2017-04-10 | 1 | 2017-04-10 | [14 empty] | 2017-07-25 | 2017-08-03 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-00172 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8094 | Fishkill Plains | N |  | 14.5 | [13 empty] | NM | N | 58 ENPHASE M250 | 2017-04-10 | 2017-04-18 | 5 | 2017-04-18 | [14 empty] | 2017-06-22 | 2017-06-22 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-00182 | Fishkill |  |  | 12533 | G | 8071 | Shenandoah | TBD |  | 8 | [13 empty] | NM | N | 25 SUNPOWER SPR X21 345 | 2017-04-10 | 2017-04-18 | 5 | 2017-04-18 | [17 empty] | W
Central Hudson |  | Lotus Energy Inc. | CH-00334 | Fishkill | Putnam Valley | Putnam | 10524 | G | 8086 | Tioronda | N |  | 15 | [13 empty] | NM | N | SMA STP 15000 | 2017-05-03 | 2017-05-04 | 1 | 2017-05-04 | [14 empty] | 2017-09-20 | 2017-09-20 |  | Y
Central Hudson |  | Monolith Solar Associates LLC | CH-02680 | Catskill | Westerlo | Albany | 12193 | G | 1091 | Westerlo | N |  | 9.8 | [13 empty] | NM | N | SOLAREDGE SE6000 SOLAREDGE SE3800 | 2017-04-10 | 2017-04-17 | 4 | 2017-04-17 | [14 empty] | 2017-05-11 | 2017-05-15 |  | Y
Central Hudson |  | Revolution Solar | CH-02983 | Catskill | Greenvl | Greene | 12083 | G | 2061 | Freehold | N |  | 2.5 | [13 empty] | NM | N | 10 ENPHASE M250 | 2017-05-08 | 2017-05-08 | 0 | 2017-05-08 | [14 empty] | 2017-07-13 | 2017-07-13 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-00217 | Newburgh |  |  | 12553 | G | 4052 | Union Ave | TBD |  | 5.12 | [13 empty] | NM | N | 16 SUNPOWER SPR X21 345 | 2017-04-11 | 2017-04-18 | 4 | 2017-04-18 | [17 empty] | W
Central Hudson |  | Borrego Solar | CH-00600 | Kingston | Accord | Ulster | 12404 | G | 3024 | High Falls | N |  | 4000 | [13 empty] | CDG | Y | SUNGROW SG125HV | 2017-04-28 | 2017-05-10 | 8 | 2017-05-10 | 2017-05-10 | 2017-05-31 | 14 | 2017-07-17 | 2017-08-28 | 2017-11-21 | 60 | 25169.77 | 448620 | 358620.6 | 2018-02-12 | 2018-11-28 | 2018-11-28 | 2019-12-06 | 2019-12-23 | 2019-12-23 | 2020-03-20 | Y | Y | 11/2/18 - Combined Project Review Complete. CH-00600 & CH-00601 consolidated to one 4MW project, CH-00600. Full upgrade payment due 2/1/19.
Central Hudson |  | 212 Solar Development, LLC | CH-00601 | Kingston | Accord |  | 12404 | G | 3024 | High Falls | TBD |  | 2000 | [13 empty] | CDG | Y | SUNGROW SG125HV (16) | 2017-04-28 | 2017-05-10 | 8 | 2017-05-10 | 2017-05-10 | 2017-05-31 | 14 | 2017-07-17 | 2017-08-28 | 2017-11-21 | 60 | 22500 |  |  | 2018-02-12 | [6 empty] | W |  | 5/1/18 - Received request to combine with Project CH-00600; current deadlines suspended.
Central Hudson |  | 212 Solar Development, LLC | CH-00602 | Kingston |  |  | 12404 | G | 3024 | High Falls | TBD |  | 1980 | [13 empty] | CDG | N | 30 SUNGROW SG60KU | 2017-04-28 | 2017-05-10 | 8 | 2017-05-10 | 2017-05-10 | 2017-05-31 | 14 |  |  |  |  | 16666.66 | [9 empty] | W
Central Hudson |  | 212 Solar Development, LLC | CH-00603 | Fishkill |  |  | 12582 | G | 8093 | Fishkill Plains | TBD |  | 1980 | [13 empty] | CDG | N | 30 SUNGROW SG60KU | 2017-04-28 | 2017-05-12 | 10 | 2017-05-12 | 2017-05-12 | 2017-06-02 | 14 |  |  |  |  | 13750 | [9 empty] | W
Central Hudson |  | 212 Solar Development, LLC | CH-00604 | Fishkill |  |  | 12582 | G | 8093 | Fishkill Plains | TBD |  | 1980 | [13 empty] | CDG | N | 30 SUNGROW SG60KU | 2017-04-28 | 2017-05-12 | 10 | 2017-05-12 | 2017-05-12 | 2017-06-02 | 14 |  |  |  |  | 13750 | [9 empty] | W
Central Hudson |  | 212 Solar Development, LLC | CH-00605 | Fishkill |  |  | 12582 | G | 8093 | Fishkill Plains | TBD |  | 1980 | [13 empty] | CDG | N | 30 SUNGROW SG60KU | 2017-04-28 | 2017-05-12 | 10 | 2017-05-12 | 2017-05-12 | 2017-06-02 | 14 |  |  |  |  | 13750 | [9 empty] | W
Central Hudson |  | 212 Solar Development, LLC | CH-00606 | Fishkill |  |  | 12582 | G | 8093 | Fishkill Plains | TBD |  | 1980 | [13 empty] | CDG | N | 30 SUNGROW SG60KU | 2017-04-28 | 2017-05-12 | 10 | 2017-05-12 | 2017-05-12 | 2017-06-02 | 14 |  |  |  |  | 13750 | [9 empty] | W
Central Hudson |  | Collegiate Builders | CH-00777 | Kingston | Willow | Ulster | 12495 | G | 3012 | Woodstock | N |  | 10 | [13 empty] | NM | N | SOLAREDGE SE10000 | 2017-07-11 | 2017-07-12 | 1 | 2017-07-12 | [14 empty] | 2017-08-23 | 2017-08-24 |  | Y
Central Hudson |  | SolarCity | CH-06161 | Newburgh | New Paltz | Ulster | 12561 | G | 5031 | Galeville | N |  | 6.6 | [13 empty] | NM | N | DELTA SOLVIIA 6.6 | 2017-04-11 | 2017-04-18 | 4 | 2017-04-18 | [14 empty] | 2017-05-31 | 2017-06-01 |  | Y
Central Hudson |  | SolarCity | CH-06575 | Kingston | Saugerties | Ulster | 12477 | G | 3004 | Saugerties | N |  | 9 | [13 empty] | NM | N | DELTA SOLIVIA 3.8 DELTA SOLIVIA 5.2 | 2017-04-11 | 2017-04-18 | 4 | 2017-04-18 | [14 empty] | 2017-04-19 | 2017-04-19 |  | Y
Central Hudson |  | SolarCity | CH-06899 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8072 | Shenandoah | N |  | 5.2 | [13 empty] | NM | N | DELTA SOLIVIA 5.2 | 2017-04-11 | 2017-04-18 | 4 | 2017-04-18 | [14 empty] | 2017-05-22 | 2017-05-22 |  | Y
Central Hudson |  | SolarCity | CH-07818 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8092 | Fishkill Plains | N | CH-06066 | 3 | [13 empty] | NM | N | SOLAREDGE SE 3000 | 2017-04-11 | 2017-04-18 | 4 | 2017-04-18 | [14 empty] | 2017-05-01 | 2017-05-01 |  | Y
Central Hudson |  | Sunrun Inc. | CH-08321 | Newburgh | Newburgh | Orange | 12550 | G | 4013 | West Balmville | N |  | 5 | [13 empty] | NM | N | 1 SOLAREDGE SE5000 | 2017-04-18 | 2017-04-24 | 4 | 2017-04-24 | [14 empty] | 2017-05-12 | 2017-05-18 |  | Y
Central Hudson |  | Sunrun Inc. | CH-08325 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8072 | Shenandoah | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE 7600 | 2017-04-19 | 2017-04-24 | 3 | 2017-04-24 | [14 empty] | 2017-08-07 | 2017-08-09 |  | Y
Central Hudson |  | Trinity Solar | CH-08531 | Kingston | Bloomington | Ulster | 12411 | G | 1011 | Boulevard | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A | 2017-04-11 | 2017-04-25 | 9 | 2017-04-25 | [14 empty] | 2017-07-11 | 2017-07-11 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-00181 | Fishkill | Fishkill | Dutchess | 12524 | G | 8094 | Fishkill Plains | N |  | 8.96 | [13 empty] | NM | N | 28 SUNPOWER SPR X21 345 | 2017-04-12 | 2017-04-19 | 4 | 2017-04-19 | [14 empty] | 2017-06-20 | 2017-06-22 |  | Y
Central Hudson |  | SolarCity | CH-06711 | Poughkeepsie | Lagrangevl | Dutchess | 12540 | G | 6055 | Todd Hill | N |  | 7.6 | [13 empty] | NM | N | DELTA SOLIVIA 7.6 | 2017-04-12 | 2017-04-19 | 4 | 2017-04-19 | [14 empty] | 2017-05-09 | 2017-05-09 |  | Y
Central Hudson |  | SolarCity | CH-07689 | Newburgh | Maybrook | Orange | 12543 | G | 4026 | Coldenham | N |  | 3 | [13 empty] | NM | N | ABB PVI 3 | 2017-04-13 | 2017-04-19 | 3 | 2017-04-19 | [14 empty] | 2017-05-24 | 2017-06-14 |  | Y
Central Hudson |  | Solar Generation | CH-08132 | Kingston | Woodstock | Ulster | 12498 | G | 3013 | Woodstock | N |  | 21 | [13 empty] | NM | N | 3 SMA SB 7.0 | 2017-04-19 | 2017-04-24 | 3 | 2017-04-24 | [8 empty] | 350 | 350 |  | 2017-05-05 | 2017-05-05 | 2017-05-30 | 2017-05-31 | 2017-06-06 |  | Y
Central Hudson |  | Con Edison Solutions | CH-03120 | Poughkeepsie |  |  | 12540 | G | 6055 | Todd Hill | TBD |  | 840 | [13 empty] | CDG | N | 14 CHINT POWER SYSTEMS 60KTL | 2017-05-16 | 2017-05-31 | 10 | 2017-05-31 | 2017-05-31 | 2017-06-21 | 15 | 2017-07-13 | 2017-08-17 | 2017-11-01 | 53 | 13958.41 | 337630 | [7 empty] | 2018-05-24 | W
Central Hudson |  | Empire Solar Solutions | CH-00052 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8043 | Myers Corners | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE 7600 | 2017-04-17 | 2017-04-19 | 2 | 2017-04-19 | [14 empty] | 2017-05-17 | 2017-05-18 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-00094 | Fishkill |  |  | 12533 | G | 8096 | Fishkill Plains | TBD |  | 21.4 | [13 empty] | NM | N | SOLAREDGE SE11400 SOLAREDGE 10000 | 2017-04-17 | 2017-04-19 | 2 | 2017-04-19 | [17 empty] | W
Central Hudson |  | New York State Solar Farm | CH-00410 | Newburgh | Marlboro | Ulster | 12542 | G | 5004 | Marlboro | N |  | 10.56 | [13 empty] | NM | N | 33 SUNPOWER SPR X21 345 | 2017-04-26 | 2017-04-27 | 1 | 2017-04-27 | [14 empty] | 2017-07-13 | 2017-07-13 |  | Y
Central Hudson |  | American Energy Care | CH-00652 | Catskill | Earlton | Greene | 12058 | G | 1071 | Coxsackie | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE 7600 | 2017-05-22 | 2017-05-25 | 3 | 2017-05-25 | [14 empty] | 2017-06-07 | 2017-06-13 |  | Y
Central Hudson |  | Hudson Solar | CH-02111 | Poughkeepsie |  |  | 12569 | G | 7023 | Tinkertown | TBD |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000 A-US-U | 2017-04-17 | 2017-04-19 | 2 | 2017-04-19 | [14 empty] | 2017-06-14 | 2017-06-20 |  | W
Central Hudson |  | SolarCity | CH-05707 | Kingston | Kingston | Ulster | 12401 | G | 1014 | Boulevard | N |  | 3 | [13 empty] | NM | N | ABB PVI 3 | 2017-04-17 | 2017-04-19 | 2 | 2017-04-19 | [14 empty] | 2017-05-01 | 2017-05-02 |  | Y
Central Hudson |  | SolarCity | CH-07067 | Newburgh | Newburgh | Orange | 12550 | G | 5004 | Marlboro | N |  | 9 | [13 empty] | NM | N | DELTA SOLIVIA 5.2TL DELTA SOLIVIA 3.8TL | 2017-05-17 | 2017-05-17 | 0 | 2017-05-17 | [14 empty] | 2017-06-26 | 2017-07-07 |  | Y
Central Hudson |  | SolarCity | CH-07786 | Kingston | Tillson | Ulster | 12486 | G | 3021 | High Falls | Y |  | 5 | 5 | [12 empty] | NM | N | 1 SolarEdge Technologies SE5000 (240V) 1TeslaAC Powerwall 2.0 | 2017-06-12 | 2017-06-20 | 6 | 2017-06-20 | [14 empty] | 2018-02-09 | 2018-02-09 |  | Y
Central Hudson |  | Trinity Solar | CH-08388 | Catskill | Oak Hill | Greene | 12460 | G | 1092 | Westerlo | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A-US | 2017-04-17 | 2017-05-01 | 10 | 2017-05-01 | [14 empty] | 2017-08-23 | 2017-08-23 |  | Y
Central Hudson |  | Trinity Solar | CH-08413 | Poughkeepsie |  |  | 12538 | G | 6075 | East Park | TBD |  | 3.8 | [13 empty] | NM | N | SOLAREDGE SE3800A-US | 2017-04-17 | 2017-05-01 | 10 | 2017-05-01 | [17 empty] | W
Central Hudson |  | Trinity Solar | CH-08459 | Newburgh |  |  | 10916 | G | 5052 | Maybrook | TBD |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A-US | 2017-04-17 | 2017-05-01 | 10 | 2017-05-01 | [17 empty] | W
Central Hudson |  | Trinity Solar | CH-08476 | Kingston | Saugerties | Ulster | 12477 | G | 3001 | Saugerties | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A-US | 2017-04-17 | 2017-05-01 | 10 | 2017-05-01 | [14 empty] | 2017-05-15 | 2017-05-18 |  | Y
Central Hudson |  | Trinity Solar | CH-08498 | Fishkill |  |  | 12533 | G | 8096 | Fishkill Plains | TBD |  | 10 | [13 empty] | NM | N | SOLAREDGE SE10000A-US | 2017-04-17 | 2017-05-01 | 10 | 2017-05-01 | [17 empty] | W
Central Hudson |  | Trinity Solar | CH-08510 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8093 | Fishkill Plains | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A-US | 2017-04-17 | 2017-05-01 | 10 | 2017-05-01 | [14 empty] | 2017-06-15 | 2017-06-20 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08763 | Fishkill |  |  | 12533 | G | 8072 | Shenandoah | TBD |  | 6.66 | [13 empty] | NM | N | 31 ENPHASE M215 | 2017-04-17 | 2017-04-19 | 2 | 2017-04-19 | [17 empty] | W
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08822 | Catskill |  |  | 12413 | G | 2042 | South Cairo | TBD |  | 3.44 | [13 empty] | NM | N | 16 ENPHASE M215 | 2017-04-17 | 2017-04-19 | 2 | 2017-04-19 | [17 empty] | W
Central Hudson |  | Infinity Solar Systems | CH-00207 | Fishkill | Beacon |  | 12508 | G | 8087 | Tioronda | N |  | 3.2 | [13 empty] | NM | N | SUNPOWER SPR-X21-345 (10) | 2017-04-18 | 2017-04-24 | 4 | 2017-04-24 | [14 empty] | 2017-06-14 | 2017-06-20 |  | W
Central Hudson |  | Lighthouse Solar | CH-00292 | Kingston | Kingston |  | 12401 | G | 2016 | Lincoln Park | N |  | 11.4 | [13 empty] | NM | N | SOLAREDGE 11400 A-US | 2017-04-18 | 2017-04-24 | 4 | 2017-04-24 | [17 empty] | W
Central Hudson |  | Nexamp | CH-04103 | Newburgh | Milton | Ulster | 12547 | G | 5083 | Highland | N |  | 2000 | [13 empty] | CDG | Y | 40 ABB TRIO 50 | 2017-05-18 | 2017-05-18 | 0 | 2017-05-18 | 2017-05-18 | 2017-06-09 | 15 | 2017-07-17 | 2017-07-24 | 2017-10-17 | 60 | 27528.97 | 298022 | 134892.05 | 2017-11-15 | 2018-05-08 | 2018-05-08 | 2020-12-04 | 2021-03-30 | 2021-03-31 | 2021-06-04 | Y | Y
Central Hudson |  | Hudson Solar | CH-02323 | Newburgh | Milton | Ulster | 12547 | G | 5002 | Marlboro | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE7600A-US-U | 2017-04-19 | 2017-04-24 | 3 | 2017-04-24 | [14 empty] | 2017-10-16 | 2017-10-20 |  | Y
Central Hudson |  | Solar Liberty Energy Systems | CH-04917 | Kingston | Claryvl | Sullivan | 12725 | G | 3091 | Neversink | N |  | 200 | [13 empty] | RC | Y | 4SMASunny Tripower Core1-US | 2017-04-25 | 2017-05-05 | 8 | 2017-05-05 | 2017-05-05 | 2017-05-26 | 15 | 2017-06-26 | 2017-07-06 | 2017-09-29 | 60 | 21478.76 | 62613 | 24345.73 | 2018-01-19 | 2018-07-05 | 2018-07-05 | 2019-04-02 | 2019-07-18 | 2019-07-18 | 2019-10-11 | Y | Y
Central Hudson |  | Solar Liberty Energy Systems | CH-04918 | Kingston | Denning |  | 12725 | G | 3091 | Neversink | TBD |  | 150.2 | [13 empty] | RNM | N | 3 SMA America STP50-US-40 | 2017-04-25 | 2017-05-05 | 8 | 2017-05-05 | 2017-05-05 | 2017-05-26 | 15 | 2017-06-26 | 2017-07-06 | 2017-09-29 | 60 | 11000 | 62613 | [7 empty] | 2018-02-16 | W
Central Hudson |  | SolarCity | CH-06142 | Fishkill | Beacon | Dutchess | 12508 | G | 8017 | Forgebrook | N |  | 9 | [13 empty] | NM | N | DELTA SOLIVIA 5.2 TL DELTA SOLIVIA 3.8 TL | 2017-04-19 | 2017-04-24 | 3 | 2017-04-24 | [14 empty] | 2017-09-05 | 2017-09-05 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-00187 | Newburgh | Newburgh | Orange | 12550 | G | 4012 | West Balmville | N |  | 4.48 | [13 empty] | NM | N | SUNPOWER SPR-X21-345 C-AC (14) | 2017-04-20 | 2017-04-24 | 2 | 2017-04-24 | [14 empty] | 2017-08-08 | 2017-08-09 |  | Y
Central Hudson |  | Hudson Solar | CH-01324 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7061 | Milan | N |  | 7.68 | [13 empty] | NM | N | SMA AMERICA SB7.7 | 2017-04-26 | 2017-04-27 | 1 | 2017-04-27 | [14 empty] | 2017-06-14 | 2017-06-20 |  | Y
Central Hudson |  | Hudson Solar | CH-01716 | Kingston | Saugerties | Ulster | 12477 | G | 3001 | Saugerties | N | CH-01716 | 11.84 | [13 empty] | NM | N | SUNPOWER X22-360 C-AC (37) | 2017-05-01 | 2017-05-02 | 1 | 2017-05-02 | [14 empty] | 2017-06-08 | 2017-06-13 |  | Y
Central Hudson |  | Hudson Solar | CH-02305 | Fishkill | Cold Spg | Putnam | 10516 | G | 8063 | Merritt Park | N | CH-02305 | 6.4 | [13 empty] | NM | N | SUN X21-345 C-AC (20) | 2017-04-25 | 2017-04-26 | 1 | 2017-04-26 | [14 empty] | 2017-07-11 | 2017-07-13 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08643 | Catskill | Earlton | Greene | 12058 | G | 1071 | Coxsackie | N |  | 4.3 | [13 empty] | NM | N | ENPHASE 602LLS22IG M215 (20) | 2017-04-20 | 2017-04-24 | 2 | 2017-04-24 | [14 empty] | 2017-08-22 | 2017-08-22 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-00169 | Newburgh | Highland | Ulster | 12528 | G | 5084 | Highland | N |  | 5.12 | [13 empty] | NM | N | SUNPOWER SPR-X21-345 C-AC (16) | 2017-04-21 | 2017-04-25 | 2 | 2017-04-25 | [14 empty] | 2017-06-06 | 2017-06-07 |  | Y
Central Hudson |  | SolarCity | CH-06803 | Fishkill | Wappingers Falls | Dutchess | 12590 | G | 8094 | Fishkill Plains | N |  | 5.2 | [13 empty] | NM | N | DELTA SOLIVIA 5.2 | 2017-04-21 | 2017-04-26 | 3 | 2017-04-26 | [14 empty] | 2017-05-02 | 2017-05-02 |  | Y
Central Hudson |  | SolarCity | CH-07819 | Fishkill |  |  | 12524 | G | 8055 | North Chelsea | TBD |  | 3 | [13 empty] | NM | N | ABB PVI 3 | 2017-04-21 | 2017-04-25 | 2 | 2017-04-25 | [17 empty] | W
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08765 | Fishkill |  |  | 12533 | G | 8071 | Shenandoah | TBD |  | 6.02 | [13 empty] | NM | N | ENPHASE M215 602LLS22IG (28) | 2017-04-21 | 2017-04-25 | 2 | 2017-04-25 | [17 empty] | W
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08811 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8094 | Fishkill Plains | N |  | 6.45 | [13 empty] | NM | N | ENPHASE M215 602LLS22IG (30) | 2017-04-21 | 2017-04-25 | 2 | 2017-04-25 | [14 empty] | 2017-11-15 | 2017-11-20 |  | Y
Central Hudson |  | Kasselman Solar | CH-00256 | Catskill | Westerlo | Albany | 12193 | G | 1091 | Westerlo | N | CH-03507 | 2 | [13 empty] | NM | N | ENPHASE M250 (8) | 2017-05-02 | 2017-05-03 | 1 | 2017-05-03 | [14 empty] | 2017-05-11 | 2017-05-11 |  | Y
Central Hudson |  | New York State Solar Farm | CH-00376 | Poughkeepsie | Stanfordvl | Dutchess | 12581 | G | 7071 | Stanfordville | N |  | 11.84 | [13 empty] | NM | N | 37 SUNPOWER SPR X21 345 | 2017-04-24 | 2017-04-26 | 2 | 2017-04-26 | [14 empty] | 2017-05-15 | 2017-05-15 |  | Y
Central Hudson |  | Direct Energy Solar | CH-01067 | Kingston | Kingston | Ulster | 12401 | G | 1021 | East Kingston | N |  | 5 | [13 empty] | NM | N | 20 ENPHASE M250 | 2017-04-24 | 2017-04-26 | 2 | 2017-04-26 | [14 empty] | 2017-05-15 | 2017-05-18 |  | Y
Central Hudson |  | SolarCity | CH-07191 | Catskill | Westerlo | Albany | 12193 | G | 1091 | Westerlo | N |  | 14.2 | [13 empty] | NM | N | DELTA SOLIVIA 6.6TL DELTA SOLIVIA 7.6TL | 2017-04-24 | 2017-05-02 | 6 | 2017-05-02 | [8 empty] | 350 | 350 |  | 2017-07-10 | 2017-07-10 | 2017-07-28 | 2017-08-01 | 2017-08-01 |  | Y
Central Hudson |  | SolarCity | CH-07387 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8055 | North Chelsea | N |  | 11.8 | [13 empty] | NM | N | DELTA SOLIVIA 5.2TL DELTA SOLIVIA 6.6TL | 2017-05-02 | 2017-05-03 | 1 | 2017-05-03 | [8 empty] | 350 | 350 |  | 2017-06-05 | 2017-06-05 | 2017-08-09 | 2017-08-18 | 2017-08-18 |  | Y
Central Hudson |  | SolarCity | CH-07495 | Kingston | Tillson | Ulster | 12486 | G | 3022 | High Falls | N |  | 5 | [13 empty] | NM | N | ABB PVI-5.0OUTD-S-US | 2017-04-24 | 2017-04-26 | 2 | 2017-04-26 | [14 empty] | 2017-05-24 | 2017-06-07 |  | Y
Central Hudson |  | Trinity Solar | CH-08414 | Poughkeepsie | Staatsburg | Dutchess | 12580 | G | 7041 | Staatsburg | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE7600A-US | 2017-04-24 | 2017-05-01 | 5 | 2017-05-01 | [14 empty] | 2017-08-01 | 2017-08-01 |  | Y
Central Hudson |  | Trinity Solar | CH-08529 | Kingston | High Fls | Ulster | 12440 | G | 3024 | High Falls | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A-US | 2017-05-04 | 2017-05-04 | 0 | 2017-05-04 | [14 empty] | 2017-09-21 | 2017-09-25 |  | Y
Central Hudson |  | Trinity Solar | CH-08539 | Fishkill | Poughkeepsie | Dutchess | 12601 | G | 8024 | Knapps Corners | N |  | 13 | [13 empty] | NM | N | SOLAREDGE SE3000A-US SOLAREDGE SE10000A-US | 2017-04-24 | 2017-05-01 | 5 | 2017-05-01 | [14 empty] | 2017-09-08 | 2017-09-08 |  | Y
Central Hudson |  | Trinity Solar | CH-08540 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8095 | Fishkill Plains | N |  | 10 | [13 empty] | NM | N | SOLAREDGE SE10000A-US | 2017-04-24 | 2017-05-01 | 5 | 2017-05-01 | [14 empty] | 2017-09-20 | 2017-09-25 |  | Y
Central Hudson |  | Trinity Solar | CH-08545 | Fishkill |  |  | 12533 | G | 8093 | Fishkill Plains | TBD |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A-US | 2017-04-24 | 2017-05-01 | 5 | 2017-05-01 | [17 empty] | W
Central Hudson |  | Infinity Solar Systems | CH-00146 | Newburgh | New Windsor | Orange | 12553 | G | 4046 | Union Ave | N |  | 16 | [13 empty] | NM | N | 50 SUNPOWER SPR X21 345 | 2017-04-25 | 2017-04-26 | 1 | 2017-04-26 | [14 empty] | 2017-06-29 | 2017-06-29 |  | Y
Central Hudson |  | Lotus Energy Inc. | CH-00338 | Kingston | Kerhonkson | Ulster | 12446 | G | 3081 | Kerhonkson | N |  | 15.36 | [13 empty] | NM | N | SMA SB7700 SMA SB7700 | 2017-04-27 | 2017-04-27 | 0 | 2017-04-27 | [14 empty] | 2017-05-24 | 2017-05-25 |  | Y
Central Hudson |  | SolarCity | CH-06911 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8093 | Fishkill Plains | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000 | 2017-04-25 | 2017-04-26 | 1 | 2017-04-26 | [14 empty] | 2017-06-19 | 2017-06-20 |  | Y
Central Hudson |  | SolarCity | CH-06947 | Fishkill | Beacon | Dutchess | 12508 | G | 8015 | Forgebrook | N |  | 6 | [13 empty] | NM | N | 2 ABB PVI 3 | 2017-04-25 | 2017-04-26 | 1 | 2017-04-26 | [14 empty] | 2017-06-19 | 2017-06-22 |  | Y
Central Hudson |  | Kasselman Solar | CH-00229 | Newburgh | Highland | Ulster | 12528 | G | 5083 | Highland | N | CH-00229 | 7.25 | [13 empty] | NM | N | ENPHASE M250 (29) | 2017-04-26 | 2017-05-09 | 9 | 2017-05-09 | [14 empty] | 2017-06-07 | 2017-06-08 |  | Y
Central Hudson |  | Kasselman Solar | CH-00234 | Catskill | Acra | Greene | 12405 | G | 2041 | South Cairo | N | CH-00234 | 6.5 | [13 empty] | NM | N | ENPHASE M250 (26) | 2017-04-26 | 2017-05-01 | 3 | 2017-05-01 | [14 empty] | 2017-05-22 | 2017-05-22 |  | Y
Central Hudson |  | New York State Solar Farm | CH-00412 | Newburgh | Gardiner | Ulster | 12525 | G | 5034 | Galeville | N | CH-00412 | 5 | [13 empty] | NM | N | SMA AMERICA SB 5 | 2017-05-02 | 2017-05-03 | 1 | 2017-05-03 | [14 empty] | 2017-06-14 | 2017-06-20 |  | Y
Central Hudson |  | SolarCity | CH-05216 | Kingston | Accord | Ulster | 12404 | G | 3024 | High Falls | Y |  | 9.8 | 9.8 | [12 empty] | NM | N | DELTA SOLIVIA 3.8 SOLARCITY DELTA H61TeslaH6 Hybrid Inverter | 2017-05-12 | 2017-05-12 | 0 | 2017-05-12 | [14 empty] | 2017-09-11 | 2017-09-11 |  | Y
Central Hudson |  | SolarCity | CH-05606 | Catskill | Ravena | Albany | 12143 | G | 1081 | New Baltimore | N |  | 5.2 | [13 empty] | NM | N | DELTA SOLIVIA 5.2 | 2017-05-03 | 2017-05-04 | 1 | 2017-05-04 | [14 empty] | 2017-08-11 | 2017-08-14 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08641 | Catskill | Acra | Greene | 12405 | G | 2041 | South Cairo | N |  | 5.59 | [13 empty] | NM | N | 26 ENPHASE M215 | 2017-04-26 | 2017-04-27 | 1 | 2017-04-27 | [14 empty] | 2017-09-05 | 2017-09-05 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08778 | Catskill |  |  | 12405 | G | 2041 | South Cairo | TBD |  | 7.52 | [13 empty] | NM | N | 35 ENPHASE M215 | 2017-04-26 | 2017-05-02 | 4 | 2017-05-02 | [17 empty] | W
Central Hudson |  | Solar Alchemy | CH-08995 | Newburgh | Highland | Ulster | 12528 | G | 5082 | Highland | N |  | 11.2 | [13 empty] | NM | N | 40 ENPHASE S280 | 2017-04-27 | 2017-04-28 | 1 | 2017-04-28 | [14 empty] | 2017-10-04 | 2017-10-18 |  | Y
Central Hudson |  | Hudson Solar | CH-01630 | Catskill | Westerlo | Albany | 12193 | G | 1091 | Westerlo | Y |  | 6.8 | 6.8 | [12 empty] | NM | N | SCNEIDER ELECTRIC XW+68482XantrexXW4548 (DC) | 2017-05-15 | 2017-05-15 | 0 | 2017-05-15 | [14 empty] | 2017-09-26 | 2017-10-10 |  | Y
Central Hudson |  | Hudson Solar | CH-01789 | Poughkeepsie | Clinton Corners | Dutchess | 12514 | G | 7013 | Hibernia | N |  | 16 | [13 empty] | NM | N | SUNPOWER X22-360C-AC (50) | 2017-04-27 | 2017-04-28 | 1 | 2017-04-28 | [8 empty] | 350 | 350 |  | 2017-05-17 | 2017-05-17 | 2017-07-19 | 2017-07-05 | 2017-07-19 |  | Y
Central Hudson |  | Hudson Solar | CH-02226 | Catskill | Ravena | Albany | 12143 | G | 1081 | New Baltimore | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A-US-U | 2017-04-27 | 2017-04-28 | 1 | 2017-04-28 | [14 empty] | 2017-06-22 | 2017-06-22 |  | Y
Central Hudson |  | Hudson Solar | CH-02229 | Kingston | Stone Ridge | Ulster | 12484 | G | 3023 | High Falls | N |  | 12.6 | [13 empty] | NM | N | SOLAREDGE SE7600A-US-U SOLAREDGE SE5000A-US-U | 2017-04-27 | 2017-04-28 | 1 | 2017-04-28 | [14 empty] | 2017-08-17 | 2017-08-18 |  | Y
Central Hudson |  | Hudson Solar | CH-02470 | Poughkeepsie | Millerton | Dutchess | 12546 | G | 7081 | Millerton | N | CH-01089 | 3.8 | [13 empty] | NM | N | SOLAREDGE SE3800H-US | 2017-04-27 | 2017-04-28 | 1 | 2017-04-28 | [14 empty] | 2017-06-21 | 2017-06-21 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08692 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8095 | Fishkill Plains | N |  | 8.17 | [13 empty] | NM | N | ENPHASE M215 602LLS22IG (38) | 2017-04-27 | 2017-04-28 | 1 | 2017-04-28 | [14 empty] | 2017-11-09 | 2017-11-14 |  | Y
Central Hudson |  | Self | CH-08887 | Newburgh | New Paltz | Ulster | 12561 | G | 5023 | Ohioville | N |  | 6 | [13 empty] | NM | N | SMA SB 6 | 2017-04-27 | 2017-05-03 | 4 | 2017-05-03 | [17 empty] | W
Central Hudson |  | Infinity Solar Systems | CH-00158 | Fishkill | Beacon | Dutchess | 12508 | G | 8087 | Tioronda | N |  | 5.12 | [13 empty] | NM | N | SUNPOWER SPR-X21-345C-AC (16) | 2017-04-28 | 2017-05-01 | 1 | 2017-05-01 | [14 empty] | 2017-07-11 | 2017-07-11 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-00161 | Newburgh | Campbell Hall | Orange | 10916 | G | 5052 | Maybrook | N |  | 9.6 | [13 empty] | NM | N | 30 SUNPOWER SPR X21 345 | 2017-04-28 | 2017-05-02 | 2 | 2017-05-02 | [14 empty] | 2017-07-11 | 2017-08-01 |  | Y
Central Hudson |  | 212 Solar Development, LLC | CH-00607 | Newburgh |  |  | 12553 | G | 4092 | Bethlehem Rd | TBD |  | 1980 | [13 empty] | CDG | N | 30 SUNGROW SG60KU | 2017-05-03 | 2017-05-17 | 10 | 2017-05-17 | 2017-05-17 | 2017-06-08 | 15 | [14 empty] | W
Central Hudson |  | 212 Solar Development, LLC | CH-00608 | Newburgh |  |  | 12553 | G | 4092 | Bethlehem Rd | TBD |  | 1980 | [13 empty] | CDG | N | 30 SUNGROW SG60KU | 2017-05-03 | 2017-05-17 | 10 | 2017-05-17 | 2017-05-17 | 2017-06-08 | 15 | [14 empty] | W
Central Hudson |  | SolarCity | CH-06963 | Newburgh | New Paltz | Ulster | 12561 | G | 5022 | Ohioville | N |  | 7.6 | [13 empty] | NM | N | DELTA SOLIVIA 7.6 | 2017-04-28 | 2017-05-01 | 1 | 2017-05-01 | [14 empty] | 2017-10-17 | 2017-10-19 |  | Y
Central Hudson |  | Trinity Solar | CH-08486 | Poughkeepsie |  |  | 12538 | G | 6075 | East Park | TBD |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A-US | 2017-04-28 | 2017-05-02 | 2 | 2017-05-02 | [17 empty] | W
Central Hudson |  | Trinity Solar | CH-08499 | Fishkill |  |  | 12533 | G | 8094 | Fishkill Plains | TBD |  | 5 | [13 empty] | NM | N | SOLAREDGE 5000A-US | 2017-04-28 | 2017-05-02 | 2 | 2017-05-02 | [17 empty] | W
Central Hudson |  | Trinity Solar | CH-08526 | Catskill | Preston Holw | Albany | 12469 | G | 1092 | Westerlo | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE7600A | 2017-04-28 | 2017-05-02 | 2 | 2017-05-02 | [14 empty] | 2017-09-20 | 2017-10-13 |  | Y |  | 9/29/17 - CH Rep was unable to install net meter due to dog. Scheduled appt & installed meter on 10/12/17.
Central Hudson |  | Trinity Solar | CH-08561 | Poughkeepsie |  |  | 12514 | G | 7071 | Stanfordville | TBD |  | 7.6 | [13 empty] | NM | N | SOLAREDGE 7600A-US | 2017-04-28 | 2017-05-02 | 2 | 2017-05-02 | [17 empty] | W
Central Hudson |  | SolarCity | CH-07315 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6097 | Manchester | N |  | 10.4 | [13 empty] | NM | N | 2 DELTA SOLIVIA 5.2 | 2017-05-01 | 2017-05-02 | 1 | 2017-05-02 | [14 empty] | 2018-03-26 | 2018-03-28 |  | Y
Central Hudson |  | SolarCity | CH-07624 | Catskill | Cairo | Greene | 12413 | G | 2041 | South Cairo | N |  | 10.4 | [13 empty] | NM | N | 2 DELTA SOLIVIA 5.2 | 2017-05-01 | 2017-05-02 | 1 | 2017-05-02 | [14 empty] | 2017-11-29 | 2017-11-29 |  | Y
Central Hudson |  | SolarCity | CH-07684 | Newburgh | Newburgh | Orange | 12550 | G | 4051 | Union Ave | N |  | 12.8 | [13 empty] | NM | N | DELTA SOLIVIA 5.2 DELTA SOLIVIA 7.6 | 2017-05-01 | 2017-05-02 | 1 | 2017-05-02 | [14 empty] | 2017-09-06 | 2017-09-06 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-00086 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8024 | Knapps Corners | N |  | 6 | [13 empty] | NM | N | SOLAREDGE 6000 | 2017-05-02 | 2017-05-03 | 1 | 2017-05-03 | [14 empty] | 2017-07-13 | 2017-07-13 |  | Y
Central Hudson |  | Direct Energy Solar | CH-00916 | Kingston | Woodstock | Ulster | 12498 | G | 3014 | Woodstock | N |  | 11.5 | [13 empty] | NM | N | 46 ENPHASE M250 | 2017-05-02 | 2017-05-03 | 1 | 2017-05-03 | [14 empty] | 2017-07-10 | 2017-07-20 |  | Y
Central Hudson |  | Hudson Solar | CH-02014 | Catskill | Freehold | Greene | 12431 | G | 2071 | Freehold | N |  | 17.6 | [13 empty] | NM | N | SOLAREDGE SE7600 SOLAREDGE SE10000 | 2017-05-02 | 2017-05-03 | 1 | 2017-05-03 | [14 empty] | 2017-07-10 | 2017-07-10 |  | Y
Central Hudson |  | SolarCity | CH-05053 | Fishkill | Cold Spg | Putnam | 10516 | G | 8087 | Tioronda | N |  | 13.2 | [13 empty] | NM | N | 2 DELTA SOLIVIA 6.6 | 2017-05-02 | 2017-05-03 | 1 | 2017-05-03 | [14 empty] | 2017-08-04 | 2017-08-04 |  | Y
Central Hudson |  | SolarCity | CH-06000 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8091 | Fishkill Plains | N |  | 15.2 | [13 empty] | NM | N | DELTA SOLIVIA 7.6 DELTA SOLIVIA 7.6 | 2017-05-02 | 2017-05-03 | 1 | 2017-05-03 | [14 empty] | 2017-09-05 | 2017-09-05 |  | Y
Central Hudson |  | Solar Generation | CH-08287 | Kingston | Kingston | Ulster | 12401 | G | 2093 | Hurley Ave | N |  | 7 | [13 empty] | NM | N | SMA SB 7000 | 2017-06-02 | 2017-06-14 | 8 | 2017-06-14 | [14 empty] | 2017-06-20 | 2017-06-21 |  | Y
Central Hudson |  | Sunrun Inc. | CH-08351 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 7.6 | [13 empty] | NM | N | ABB UNO 7.6 | 2017-05-04 | 2017-05-04 | 0 | 2017-05-04 | [14 empty] | 2017-07-19 | 2017-07-20 |  | Y
Central Hudson |  | Apex Solar Power | CH-00019 | Poughkeepsie | Ancram | Columbia | 12502 | G | 7085 | Ancram | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000 | 2017-05-03 | 2017-05-04 | 1 | 2017-05-04 | [14 empty] | 2017-06-12 | 2017-06-20 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-00027 | Newburgh | Cornwall-Hdsn | Orange | 12520 | G | 4043 | Union Ave | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE7600 | 2017-07-31 | 2017-07-31 | 0 | 2017-07-31 | [14 empty] | 2017-08-07 | 2017-08-09 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-00031 | Newburgh | Cornwall-Hdsn | Orange | 12520 | G | 4043 | Union Ave | N |  | 10 | [13 empty] | NM | N | SOLAREDGE SE10000 | 2017-07-31 | 2017-07-31 | 0 | 2017-07-31 | [14 empty] | 2017-08-04 | 2017-08-04 |  | Y
Central Hudson |  | New York State Solar Farm | CH-00354 | Kingston | Stone Ridge | Ulster | 12484 | G | 3023 | High Falls | Y | CH-00354 | 3.2 | [13 empty] | NM | N | 10 SUNPOWER SPR E20 327 | 2017-05-03 | 2017-05-04 | 1 | 2017-05-04 | [14 empty] | 2017-06-26 | 2017-07-05 |  | Y
Central Hudson |  | Hudson Solar | CH-01954 | Newburgh | New Paltz | Ulster | 12561 | G | 5023 | Ohioville | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000 | 2017-05-03 | 2017-05-04 | 1 | 2017-05-04 | [14 empty] | 2017-07-11 | 2017-07-11 |  | Y
Central Hudson |  | SolarCity | CH-05096 | Kingston | Saugerties | Ulster | 12477 | G | 3002 | Saugerties | N |  | 6.6 | [13 empty] | NM | N | DELTA SOLIVIA 6.6 | 2017-05-03 | 2017-05-04 | 1 | 2017-05-04 | [14 empty] | 2017-06-22 | 2017-06-29 |  | Y
Central Hudson |  | Taconic Renewable energy Solutions | CH-09706 | Newburgh | Gardiner | Ulster | 12525 | G | 5011 | Modena | N | CH-09706 | 14.16 | [13 empty] | NM | N | 59 ENPHASE M250 | 2017-05-08 | 2017-05-08 | 0 | 2017-05-08 | [14 empty] | 2017-06-13 | 2017-06-22 |  | Y
Central Hudson |  | SolarCity | CH-06637 | Poughkeepsie |  |  | 12603 | G | 6042 | Spackenkill | TBD |  | 5.2 | [13 empty] | NM | N | DELTA SOLIVIA 5.2 | 2017-05-04 | 2017-05-04 | 0 | 2017-05-04 | [17 empty] | W
Central Hudson |  | Solar Generation | CH-08215 | Kingston | Kingston | Ulster | 12401 | G | 3021 | High Falls | N |  | 3.2 | [13 empty] | NM | N | 10 SUNPOWER 360 | 2017-05-09 | 2017-05-10 | 1 | 2017-05-10 | [14 empty] | 2017-06-01 | 2017-06-06 |  | Y
Central Hudson |  | STR Systems NY LLC | CH-08317 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6093 | Manchester | N |  | 28.8 | [13 empty] | NM | N | 2 SOLAREDGE SE14.42SolaredgeSE14.4KUS (208V) | 2017-05-10 | 2017-05-11 | 1 | 2017-05-11 | [14 empty] | 2018-05-10 | 2018-05-17 |  | Y
Central Hudson |  | Kasselman Solar | CH-00231 | Catskill | Greenvl | Greene | 12083 | G | 2061 | Freehold | N |  | 9.25 | [13 empty] | NM | N | 37 ENPHASE M250 | 2017-05-11 | 2017-05-12 | 1 | 2017-05-12 | [14 empty] | 2017-06-01 | 2017-06-05 |  | Y
Central Hudson |  | SolarCity | CH-06650 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6097 | Manchester | N |  | 3.6 | [13 empty] | NM | N | ABB PVI 3.6 | 2017-05-05 | 2017-05-08 | 1 | 2017-05-08 | [14 empty] | 2017-06-02 | 2017-06-12 |  | Y
Central Hudson |  | SolarCity | CH-07398 | Fishkill | Beacon | Dutchess | 12508 | G | 8017 | Forgebrook | N |  | 6 | [13 empty] | NM | N | ABB PVI 6000 | 2017-05-05 | 2017-05-05 | 0 | 2017-05-05 | [14 empty] | 2017-10-26 | 2017-10-30 |  | Y
Central Hudson |  | High Peaks Solar, LLC | CH-00121 | Catskill | Cornwallvl | Greene | 12418 | G | 1092 | Westerlo | N |  | 7 | [13 empty] | NM | N | SMA SUNNY BOY 7000TLUS22 | 2017-05-08 | 2017-05-08 | 0 | 2017-05-08 | [14 empty] | 2017-07-10 | 2017-07-10 |  | Y
Central Hudson |  | SolarCity | CH-05708 | Kingston | Kingston | Ulster | 12401 | G | 1014 | Boulevard | N |  | 3.8 | [13 empty] | NM | N | DELTA SOLIVIA 3.8TL | 2017-05-19 | 2017-05-19 | 0 | 2017-05-19 | [14 empty] | 2017-05-23 | 2017-05-31 |  | Y
Central Hudson |  | SolarCity | CH-05949 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7054 | Rhinebeck | N |  | 5.2 | [13 empty] | NM | N | DELTA SOLIVIA 5.2TL | 2017-05-08 | 2017-05-09 | 1 | 2017-05-09 | [14 empty] | 2017-06-20 | 2017-06-21 |  | Y
Central Hudson |  | SolarCity | CH-06601 | Kingston | Kingston | Ulster | 12401 | G | 2017 | Lincoln Park | N |  | 10.4 | [13 empty] | NM | N | DELTA SOLIVIA 5.2 TL (2) | 2017-05-08 | 2017-05-09 | 1 | 2017-05-09 | [14 empty] | 2017-06-20 | 2017-06-23 |  | Y
Central Hudson |  | SolarCity | CH-06694 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 6074 | East Park | N |  | 10.4 | [13 empty] | NM | N | DELTA SOLIVIA 5.2 TL (2) | 2017-05-08 | 2017-05-08 | 0 | 2017-05-08 | [14 empty] | 2017-06-30 | 2017-06-30 |  | Y
Central Hudson |  | SolarCity | CH-07272 | Poughkeepsie |  |  | 12601 | G | 6002 | Reynolds Hill | TBD |  | 3 | [13 empty] | NM | N | ABB PVI 3.0 | 2017-05-08 | 2017-05-08 | 0 | 2017-05-08 | [17 empty] | W
Central Hudson |  | Kasselman Solar | CH-00238 | Catskill | Coxsackie | Greene | 12051 | G | 1076 | Coxsackie | N |  | 8 | [13 empty] | NM | N | ENPHASE ENERGY M250 (32) | 2017-05-09 | 2017-05-22 | 9 | 2017-05-22 | [14 empty] | 2017-12-05 | 2017-12-06 |  | Y
Central Hudson |  | 212 Solar Development, LLC | CH-00618 | Newburgh |  |  | 12525 | G | 5011 | Modena | TBD |  | 2000 | [13 empty] | CDG | N | SUNGROW SG125HV | 2017-09-07 | 2017-09-21 | 10 | 2017-09-21 | 2017-09-21 | 2017-10-06 | 11 |  |  |  |  | 39000 | [9 empty] | W
Central Hudson |  | Solar Alchemy | CH-09005 | Kingston | Kerhonkson | Ulster | 12446 | G | 3081 | Kerhonkson | N | CH-09005 | 4.48 | [13 empty] | NM | Y | ENPHASE ENERGYS28060-LL-2US (16) | 2017-05-10 | 2017-05-10 | 0 | 2017-05-10 | [14 empty] | 2017-06-30 | 2017-07-17 |  | Y | Y
Central Hudson |  | Empire Solar Solutions | CH-00033 | Newburgh | Newburgh | Orange | 12550 | G | 4011 | West Balmville | N |  | 11.4 | [13 empty] | NM | N | SOLAREDGE 11400A-US | 2017-05-10 | 2017-05-11 | 1 | 2017-05-11 | [14 empty] | 2017-05-30 | 2017-06-15 |  | Y
Central Hudson |  | New York State Solar Farm | CH-00445 | Newburgh | New Windsor | Orange | 12553 | G | 4094 | Bethlehem Rd | N |  | 18.56 | [13 empty] | NM | N | SUNPOWER SPR-X21 345-C-AC (58) | 2017-05-10 | 2017-05-10 | 0 | 2017-05-10 | [14 empty] | 2017-06-21 | 2017-07-05 |  | Y
Central Hudson |  | Hudson Solar | CH-02473 | Fishkill |  |  | 12590 | G | 8091 | Fishkill Plains | TBD |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A-US-U | 2017-05-10 | 2017-05-10 | 0 | 2017-05-10 | [17 empty] | W
Central Hudson |  | SolarCity | CH-07650 | Poughkeepsie | Staatsburg | Dutchess | 12580 | G | 7041 | Staatsburg | N | CH-07650 | 5.2 | [13 empty] | NM | N | ABB PVI-4.2OUTD-S-US | 2017-05-10 | 2017-05-10 | 0 | 2017-05-10 | [14 empty] | 2017-07-17 | 2017-07-21 |  | Y
Central Hudson |  | Hudson Solar | CH-02339 | Kingston | Saugerties | Ulster | 12477 | G | 3003 | Saugerties | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A-US | 2017-05-11 | 2017-05-12 | 1 | 2017-05-12 | [14 empty] | 2017-07-05 | 2017-07-05 |  | Y
Central Hudson |  | SolarCity | CH-05437 | Fishkill | Beacon | Dutchess | 12508 | G | 8015 | Forgebrook | N |  | 6.6 | [13 empty] | NM | N | DELTA SOLIVIA 6.6TL | 2017-05-15 | 2017-05-15 | 0 | 2017-05-15 | [14 empty] | 2017-09-15 | 2017-09-25 |  | Y
Central Hudson |  | SolarCity | CH-05444 | Newburgh | Mountainvl | Orange | 10953 | G | 4093 | Bethlehem Rd | N |  | 7.6 | [13 empty] | NM | N | DELTA SOLIVIA 7.6TL | 2017-05-11 | 2017-05-12 | 1 | 2017-05-12 | [14 empty] | 2017-06-19 | 2017-06-20 |  | Y
Central Hudson |  | SolarCity | CH-07268 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6046 | Spackenkill | N |  | 17 | [13 empty] | NM | N | DELTA SOLIVIA 5.2 (2) DELTA SOLIVIA 6.6 (1) | 2017-05-11 | 2017-05-12 | 1 | 2017-05-12 | [14 empty] | 2017-06-27 | 2017-06-27 |  | Y
Central Hudson |  | Con Edison Solutions | CH-03121 | Newburgh |  |  | 12589 | G | 5011 | Modena | TBD |  | 1992 | [13 empty] | CDG | N | CHINT SCA60KTL (32) CHINT SCA36KTL (2) | 2017-06-15 | 2017-06-15 | 0 | 2017-06-15 | 2017-06-15 | 2017-07-05 | 13 | 2017-07-28 | 2017-08-22 | 2017-11-15 | 60 | 19513.29 | 4032199 | [7 empty] | 2018-05-24 | W
Central Hudson |  | Monolith Solar Associates LLC | CH-02658 | Catskill | Athens | Greene | 12015 | G | 1074 | Coxsackie | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000AUS | 2017-05-12 | 2017-05-23 | 7 | 2017-05-23 | [14 empty] | 2017-07-13 | 2017-07-13 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08620 | Fishkill |  |  | 12590 | G | 8091 | Fishkill Plains | TBD |  | 4.3 | [13 empty] | NM | N | ENPHASE M215 602LLS22IG (20) | 2017-05-12 | 2017-05-12 | 0 | 2017-05-12 | [17 empty] | W
Central Hudson |  | CEC Development, LLC | CH-03115 | Catskill | Medusa | Albany | 12120 | G | 1092 | Westerlo | N |  | 2000 | [13 empty] | CDG | Y | 16 Chint Power Systems America CPS SCH125KTL-DO/US-600 (600V) SOLECTRIA PVI 60TL (33) SOLECTRIA PVI 20TL (1) | 2017-06-26 | 2017-06-26 | 0 | 2017-06-26 | 2017-06-26 | 2017-07-10 | 9 | 2017-09-12 | 2017-11-09 | 2018-02-08 | 60 | 28363.23 | 541813 | 160215.94 | 2018-05-07 | 2018-12-21 | 2018-12-21 | 2020-03-26 | 2020-06-24 | 2020-06-26 | 2020-09-21 | Y | Y | 12/10/18 - Effective grounding study complete.
Central Hudson |  | Murphy Solar Power | CH-02734 | Catskill | Catskill | Greene | 12414 | G | 2006 | North Catskill | N |  | 6 | [13 empty] | NM | N | SMA 3000 US (2) | 2017-06-05 | 2017-06-16 | 9 | 2017-06-16 | [14 empty] | 2017-07-18 | 2017-07-18 |  | Y
Central Hudson |  | SolarCity | CH-06166 | Newburgh | New Paltz | Ulster | 12561 | G | 5011 | Modena | N |  | 15.6 | [13 empty] | NM | N | DELTA SOLIVIA 5.2TL (3) | 2017-05-22 | 2017-05-25 | 3 | 2017-05-25 | [8 empty] | 350 | 350 |  | 2017-06-29 | 2017-06-29 | 2017-07-07 | 2017-08-01 | 2017-08-01 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08799 | Fishkill |  |  | 12582 | G | 8093 | Fishkill Plains | TBD |  | 9.03 | [13 empty] | NM | N | ENPHASE M215 602LLS22IG (42) | 2017-05-15 | 2017-05-15 | 0 | 2017-05-15 | [17 empty] | W
Central Hudson |  | New York State Solar Farm | CH-00353 | Newburgh | New Paltz | Ulster | 12561 | G | 5021 | Ohioville | N |  | 43.2 | [13 empty] | NM | N | SOLAREDGE SE14.4 SE US | 2017-05-31 | 2017-06-13 | 9 | 2017-06-13 | [8 empty] | 4000 | 3075.27 |  | 2017-07-17 | 2017-07-17 | 2017-08-03 | 2017-08-08 | 2017-08-08 |  | Y
Central Hudson |  | Apex Solar Power | CH-00706 | Kingston | Kingston | Ulster | 12401 | G | 2093 | Hurley Ave | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE 5000 | 2017-05-17 | 2017-05-17 | 0 | 2017-05-17 | [14 empty] | 2017-09-07 | 2017-09-08 |  | Y
Central Hudson |  | SolarCity | CH-06258 | Newburgh | New Windsor | Orange | 12553 | G | 4045 | Union Ave | N |  | 5.2 | [13 empty] | NM | N | DELTA SOLIVIA 5.2TL | 2017-05-16 | 2017-05-17 | 1 | 2017-05-17 | [14 empty] | 2017-06-26 | 2017-06-26 |  | Y
Central Hudson |  | Lotus Energy Inc. | CH-00333 | Catskill | Athens | Greene | 12015 | G | 2002 | North Catskill | N |  | 4.8 | [13 empty] | NM | N | SUNPOWER SPR-X22-360-C-AC (15) | 2017-05-17 | 2017-05-19 | 2 | 2017-05-19 | [14 empty] | 2017-06-21 | 2017-06-22 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08690 | Fishkill | Stormvl | Dutchess | 12582 | G | 8095 | Fishkill Plains | N |  | 3.22 | [13 empty] | NM | N | ENPHASE M215 602LLS22IG (15) | 2017-05-17 | 2017-05-19 | 2 | 2017-05-19 | [14 empty] | 2017-09-07 | 2017-09-08 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08691 | Fishkill |  |  | 12582 | G | 8093 | Fishkill Plains | TBD |  | 5.59 | [13 empty] | NM | N | ENPHASE M215 602LLS22IG (26) | 2017-05-17 | 2017-05-19 | 2 | 2017-05-19 | [17 empty] | W
Central Hudson |  | Empire Solar Solutions | CH-00069 | Kingston | Kerhonkson | Ulster | 12446 | G | 3082 | Kerhonkson | N |  | 3 | [13 empty] | NM | N | SOLAREDGE 3000A-US | 2017-05-18 | 2017-05-19 | 1 | 2017-05-19 | [14 empty] | 2017-06-01 | 2017-06-01 |  | Y
Central Hudson |  | SolarCity | CH-05262 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 7023 | Tinkertown | Y |  | 11.2 | 11.2 | [12 empty] | NM | N | DELTA SOLIVIA 5.2 TL DELTA H61TeslaH6 Hybrid Inverter | 2017-05-19 | 2017-05-19 | 0 | 2017-05-19 | [14 empty] | 2017-08-18 | 2017-08-18 |  | Y
Central Hudson |  | SolarCity | CH-06155 | Fishkill | Putnam Valley | Putnam | 10524 | G | 8066 | Merritt Park | N |  | 4.2 | [13 empty] | NM | N | ABB PVI 4.2 | 2017-05-18 | 2017-05-18 | 0 | 2017-05-18 | [14 empty] | 2017-07-11 | 2017-07-11 |  | Y
Central Hudson |  | Trinity Solar | CH-08397 | Catskill | Ravena | Albany | 12143 | G | 1081 | New Baltimore | N |  | 3.8 | [13 empty] | NM | N | SOLAREDGE SE3800A | 2017-05-18 | 2017-05-23 | 3 | 2017-05-23 | [14 empty] | 2017-07-17 | 2017-07-17 |  | Y
Central Hudson |  | Trinity Solar | CH-08546 | Fishkill |  |  | 12582 | G | 8071 | Shenandoah | TBD |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE76000A | 2017-05-18 | 2017-05-23 | 3 | 2017-05-23 | [17 empty] | W
Central Hudson |  | Trinity Solar | CH-08573 | Fishkill | Fishkill | Dutchess | 12524 | G | 8094 | Fishkill Plains | N |  | 5 | [13 empty] | NM | N | SOLAREDGESE5000A | 2017-05-19 | 2017-05-25 | 4 | 2017-05-25 | [8 empty] | 350 | 350 |  | 2017-08-18 | 2017-08-18 | 2017-09-13 | 2017-09-29 | 2017-09-29 |  | Y
Central Hudson |  | Malcarne Contracting | CH-00345 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 7041 | Staatsburg | N |  | 3 | [13 empty] | NM | N | SOLAREDGE 3000 | 2017-05-26 | 2017-06-07 | 7 | 2017-06-07 | [14 empty] | 2017-09-05 | 2017-09-05 |  | Y
Central Hudson |  | Malcarne Contracting | CH-00350 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 7041 | Staatsburg | N |  | 10 | [13 empty] | NM | N | SOLAREDGE 5000 (2) | 2017-05-26 | 2017-06-07 | 7 | 2017-06-07 | [8 empty] | 350 | 350 |  | 2017-06-29 | 2017-06-29 | 2017-08-29 | 2017-08-08 | 2017-08-09 |  | Y
Central Hudson |  | Hudson Solar | CH-02099 | Poughkeepsie | Salt Pt | Dutchess | 12578 | G | 7012 | Hibernia | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE7600 A-US-U | 2017-05-19 | 2017-05-26 | 5 | 2017-05-26 | [14 empty] | 2017-08-02 | 2017-08-02 |  | Y
Central Hudson |  | Hudson Solar | CH-02419 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6094 | Manchester | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE7600A-US-U | 2017-05-19 | 2017-05-23 | 2 | 2017-05-23 | [14 empty] | 2017-09-15 | 2017-09-29 |  | Y
Central Hudson |  | SolarCity | CH-06084 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8065 | Merritt Park | N |  | 11.4 | [13 empty] | NM | N | DELTA SOLIVIA 3.8TL DELTA SOLIVIA 7.6TL | 2017-08-25 | 2017-08-25 | 0 | 2017-08-25 | [14 empty] | 2017-09-07 | 2017-09-08 |  | Y
Central Hudson |  | SolarCity | CH-06705 | Poughkeepsie | Poughquag | Dutchess | 12570 | G | 6055 | Todd Hill | N |  | 10.4 | [13 empty] | NM | N | DELTA SOLIVIA 5.2TL (2) | 2017-05-22 | 2017-05-25 | 3 | 2017-05-25 | [14 empty] | 2017-07-05 | 2017-08-17 |  | Y
Central Hudson |  | SolarCity | CH-06719 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6056 | Todd Hill | N |  | 10.4 | [13 empty] | NM | N | DELTA SOLIVIA 5.2TL (2) | 2017-05-22 | 2017-05-25 | 3 | 2017-05-25 | [14 empty] | 2017-07-03 | 2017-07-03 |  | Y
Central Hudson |  | Trinity Solar | CH-08369 | Kingston |  |  | 12491 | G | 3013 | Woodstock | TBD |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE7600A | 2017-05-22 | 2017-06-01 | 7 | 2017-06-01 | [17 empty] | W
Central Hudson |  | Trinity Solar | CH-08436 | Fishkill | Fishkill | Dutchess | 12524 | G | 8014 | Forgebrook | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE7600A | 2017-05-22 | 2017-06-01 | 7 | 2017-06-01 | [14 empty] | 2017-10-31 | 2017-11-01 |  | Y
Central Hudson |  | Trinity Solar | CH-08493 | Poughkeepsie | Stanfordvl | Dutchess | 12581 | G | 7072 | Stanfordville | N |  | 10 | [13 empty] | NM | N | SOLAREDGE SE10000A | 2017-05-22 | 2017-06-01 | 7 | 2017-06-01 | [14 empty] | 2017-09-20 | 2017-10-02 |  | Y
Central Hudson |  | Trinity Solar | CH-08566 | Newburgh | Newburgh | Orange | 12550 | G | 4024 | Coldenham | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A | 2017-05-22 | 2017-06-01 | 7 | 2017-06-01 | [14 empty] | 2017-09-20 | 2017-09-25 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08624 | Kingston |  |  | 12453 | G | 3002 | Saugerties | TBD |  | 7.74 | [13 empty] | NM | N | ENPHASE M215 602LLS22IG (36) | 2017-05-22 | 2017-05-25 | 3 | 2017-05-25 | [17 empty] | W
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08824 | Kingston | Hurley | Ulster | 12443 | G | 2093 | Hurley Ave | N | CH-08660 | 2.58 | [13 empty] | NM | N | ENPHASE M215 (12) | 2017-05-22 | 2017-05-25 | 3 | 2017-05-25 | [14 empty] | 2017-11-29 | 2017-11-29 |  | Y
Central Hudson |  | Solar Flair | CH-09024 | Kingston | Saugerties | Ulster | 12477 | G | 2015 | Lincoln Park | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A=US | 2017-05-22 | 2017-06-01 | 7 | 2017-06-01 | [14 empty] | 2018-01-04 | 2018-01-04 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-00026 | Newburgh | Highland Mls | Orange | 10930 | G | 4041 | Union Ave | N |  | 16 | [13 empty] | NM | N | SOLAREDGE 10000 SOLAREDGE 6000 | 2017-05-23 | 2017-06-05 | 8 | 2017-06-05 | [14 empty] | 2017-06-20 | 2017-06-21 |  | Y
Central Hudson |  | Lighthouse Solar | CH-00273 | Newburgh | New Paltz | Ulster | 12561 | G | 5011 | Modena | N |  | 11.4 | [13 empty] | NM | N | SOLAREDGE 11400A-US | 2017-06-05 | 2017-06-15 | 8 | 2017-06-15 | [14 empty] | 2017-07-25 | 2017-07-25 |  | Y
Central Hudson |  | Lighthouse Solar | CH-00294 | Newburgh | New Paltz | Ulster | 12561 | G | 5021 | Ohioville | N |  | 6 | [13 empty] | NM | N | SOLAREDGE 6000A-US | 2017-05-23 | 2017-06-05 | 8 | 2017-06-05 | [14 empty] | 2017-08-10 | 2017-08-11 |  | Y
Central Hudson |  | Lighthouse Solar | CH-00310 | Kingston | Accord | Ulster | 12404 | G | 3024 | High Falls | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE 7600A-US | 2017-06-05 | 2017-06-15 | 8 | 2017-06-15 | [14 empty] | 2017-10-05 | 2017-10-05 |  | Y
Central Hudson |  | Lighthouse Solar | CH-00324 | Kingston | Stone Ridge | Ulster | 12484 | G | 3023 | High Falls | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE 6000 A-US | 2017-05-23 | 2017-06-05 | 8 | 2017-06-05 | [14 empty] | 2017-08-04 | 2017-08-09 |  | Y
Central Hudson |  | Direct Energy Solar | CH-01060 | Newburgh | Newburgh | Orange | 12550 | G | 4011 | West Balmville | N |  | 8.25 | [13 empty] | NM | N | ENPHASE M250 (33) | 2017-06-22 | 2017-06-22 | 0 | 2017-06-22 | [14 empty] | 2017-09-27 | 2017-09-27 |  | Y
Central Hudson |  | SolarCity | CH-05376 | Newburgh | Highland | Ulster | 12528 | G | 5081 | Highland | N |  | 20 | [13 empty] | NM | N | SOLAREDGE SE10000A (2) | 2017-05-23 | 2017-05-25 | 2 | 2017-05-25 | [14 empty] | 2017-07-06 | 2017-07-07 |  | Y
Central Hudson |  | SolarCity | CH-05734 | Kingston | Saugerties | Ulster | 12477 | G | 3003 | Saugerties | N |  | 14.2 | [13 empty] | NM | N | DELTA SOLIVIA 3.8TL (2) DELTA SOLIVIA 6.6TL | 2017-05-23 | 2017-05-25 | 2 | 2017-05-25 | [14 empty] | 2017-06-29 | 2017-06-29 |  | Y
Central Hudson |  | SolarCity | CH-06900 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8094 | Fishkill Plains | N |  | 9 | [13 empty] | NM | N | DELTA SOLIVIA5.2TL DELTA SOLIVIA5.2TL | 2017-05-23 | 2017-05-25 | 2 | 2017-05-25 | [14 empty] | 2017-09-14 | 2017-09-25 |  | Y
Central Hudson |  | SolarCity | CH-07701 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6008 | Reynolds Hill | N |  | 3.8 | [13 empty] | NM | N | SOLAREDGE SE3800A | 2017-05-23 | 2017-05-25 | 2 | 2017-05-25 | [14 empty] | 2017-08-16 | 2017-08-17 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08795 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7054 | Rhinebeck | N |  | 5.8 | [13 empty] | NM | N | ENPHASE M215 (27) | 2017-05-23 | 2017-05-25 | 2 | 2017-05-25 | [14 empty] | 2017-11-09 | 2017-11-21 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08808 | Poughkeepsie |  |  | 12571 | G | 7054 | Rhinebeck | TBD |  | 2.36 | [13 empty] | NM | N | ENPHASE M215 (11) | 2017-05-23 | 2017-05-25 | 2 | 2017-05-25 | [17 empty] | W
Central Hudson |  | Empire Solar Solutions | CH-00037 | Kingston | Saugerties | Ulster | 12477 | G | 3002 | Saugerties | N |  | 5 | [13 empty] | NM | N | SOLAREDGE 5000A-US | 2017-05-24 | 2017-06-06 | 8 | 2017-06-06 | [8 empty] | 350 | 350 |  | 2017-06-09 | 2017-06-09 | 2017-07-17 | 2017-07-25 | 2017-07-25 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-00191 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 7.04 | [13 empty] | NM | N | SUNPOWER SPR-X21-345 | 2017-05-24 | 2017-06-06 | 8 | 2017-06-06 | [14 empty] | 2017-07-07 | 2017-07-10 |  | Y
Central Hudson |  | New York State Solar Farm | CH-00431 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8096 | Fishkill Plains | N |  | 7.04 | [13 empty] | NM | N | SUNPOWER SPR-X21 345-C-AC (22) | 2017-05-24 | 2017-06-06 | 8 | 2017-06-06 | [14 empty] | 2017-06-21 | 2017-06-28 |  | Y
Central Hudson |  | New York State Solar Farm | CH-00439 | Newburgh | Newburgh | Orange | 12550 | G | 5001 | Marlboro | N |  | 8.96 | [13 empty] | NM | N | SUNPOWER SPR-X22 360-C-AC (28) | 2017-05-24 | 2017-06-06 | 8 | 2017-06-06 | [14 empty] | 2017-07-24 | 2017-07-24 |  | Y
Central Hudson |  | Trinity Solar | CH-08394 | Catskill | Coxsackie | Greene | 12051 | G | 1076 | Coxsackie | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE7600A | 2017-05-24 | 2017-06-06 | 8 | 2017-06-06 | [14 empty] | 2017-10-09 | 2017-10-09 |  | Y
Central Hudson |  | Trinity Solar | CH-08473 | Kingston | Kingston | Ulster | 12401 | G | 1014 | Boulevard | N |  | 3.8 | [13 empty] | NM | N | SOLAREDGE SE6000A | 2017-05-24 | 2017-06-06 | 8 | 2017-06-06 | [14 empty] | 2017-10-31 | 2017-11-01 |  | Y
Central Hudson |  | Trinity Solar | CH-08500 | Fishkill |  |  | 12533 | G | 8092 | Fishkill Plains | TBD |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE7600A | 2017-05-24 | 2017-06-06 | 8 | 2017-06-06 | [17 empty] | W
Central Hudson |  | SolarCity | CH-06545 | Kingston | Hurley | Ulster | 12443 | G | 2094 | Hurley Ave | N |  | 18 | [13 empty] | NM | N | DELTA SOLIVIA7.6TL (1) DELTA SOLIVIA5.2TL (2) | 2017-05-25 | 2017-06-06 | 7 | 2017-06-06 | [14 empty] | 2017-08-24 | 2017-08-24 |  | W
Central Hudson |  | SolarCity | CH-07215 | Kingston | Port Ewen | Ulster | 12466 | G | 1012 | Boulevard | N |  | 10 | [13 empty] | NM | N | SOLAREDGE SE10000A | 2017-06-09 | 2017-06-20 | 7 | 2017-06-20 | [14 empty] | 2017-06-22 | 2017-06-22 |  | Y
Central Hudson |  | Solar Generation | CH-08286 | Kingston | Woodstock | Ulster | 12498 | G | 3014 | Woodstock | N | CH-08286 | 7.6 | [13 empty] | NM | N | SOLAREDGE 3800 (2) | 2017-06-20 | 2017-06-20 | 0 | 2017-06-20 | [14 empty] | 2017-06-26 | 2017-06-26 |  | Y
Central Hudson |  | American Energy Care | CH-00656 | Catskill | Athens | Greene | 12015 | G | 2002 | North Catskill | N |  | 13.6 | [13 empty] | NM | N | SOLAREDGE SE7600A SOLAREDGE SE6000A | 2017-06-07 | 2017-06-21 | 10 | 2017-06-21 | [14 empty] | 2017-06-27 | 2017-07-05 |  | Y
Central Hudson |  | Lam Development | CH-02583 | Newburgh |  |  | 12539 | G | 5043 | East Walden | TBD |  | 2000 | [13 empty] | CDG | N | SMA TRIPOWER 30000 (66) SMA TRIPOWER 20000 (1) | 2017-06-13 | 2017-06-22 | 7 | 2017-06-22 | 2017-06-22 | 2017-07-10 | 11 | [14 empty] | W
Central Hudson |  | SolarCity | CH-07359 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8094 | Fishkill Plains | N |  | 7.6 | [13 empty] | NM | N | DELTA SOLIVIA 7.6TL | 2017-06-13 | 2017-06-21 | 6 | 2017-06-21 | [14 empty] | 2017-10-18 | 2017-10-23 |  | Y
Central Hudson |  | Tesla | CH-08362 | Newburgh |  |  | 12550 | G | 5001 | Marlboro | TBD |  | 1320 | [13 empty] | RNM | N | FRONIUS SYMO 24.0-3 (55) | 2017-07-14 | 2017-07-28 | 10 | 2017-07-28 | 2017-07-28 | 2017-08-18 | 15 | 2017-10-23 | 2017-11-17 | 2018-02-16 | 60 | 39000 | 156036 | [8 empty] | W
Central Hudson |  | CEC Development, LLC | CH-03116 | Newburgh | Walden | Orange | 12586 | G | 5041 | East Walden | N |  | 2000 | [13 empty] | CDG | Y | 16 Chint Power Systems America 1 Yaskawa Solectria Solar XGI 1500-150/166 (600V) SOLECTRIA PVI 60TL (33) SOLECTRIA PVI 20TL (1) | 2017-06-19 | 2017-06-19 | 0 | 2017-06-19 | 2017-06-19 | 2017-07-10 | 14 | 2017-09-12 | 2017-11-09 | 2018-02-08 | 60 | 17424.62 | 276895 | 136383.92 | 2018-05-07 | 2018-12-21 | 2018-12-21 | 2020-02-18 | 2020-06-30 | 2020-06-30 | 2020-09-23 | Y | Y | 12/10/18 - Effective grounding study complete.
Central Hudson |  | Empire Solar Solutions | CH-00098 | Newburgh | Highland | Ulster | 12528 | G | 5082 | Highland | N |  | 14.4 | [13 empty] | NM | N | SOLAREDGE 7600 A-US SOLAREDGE 5000 A-US | 2017-05-31 | 2017-06-13 | 9 | 2017-06-13 | [8 empty] | 350 | 350 |  | 2017-06-29 | 2017-06-29 | 2017-08-02 | 2017-08-03 | 2017-08-03 |  | Y |  | PV SYSTEM BUILT PRIOR TO CONSTRUCTION APPROVAL.
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08689 | Fishkill | Stormvl | Dutchess | 12582 | G | 8093 | Fishkill Plains | N |  | 8.17 | [13 empty] | NM | N | ENPHASE M215 602LLS22IG (38) | 2017-05-31 | 2017-06-08 | 6 | 2017-06-08 | [14 empty] | 2017-09-20 | 2017-09-20 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-00162 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6046 | Spackenkill | N |  | 5.76 | [13 empty] | NM | N | SUNPOWER SPR-X21-345 C-AC (18) | 2017-06-13 | 2017-06-21 | 6 | 2017-06-21 | [14 empty] | 2017-07-25 | 2017-07-25 |  | Y
Central Hudson |  | SolarCity | CH-05108 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8091 | Fishkill Plains | N |  | 10.4 | [13 empty] | NM | N | DELTA SOLIVIA 5.2TL (2) | 2017-06-14 | 2017-06-16 | 2 | 2017-06-16 | [14 empty] | 2017-10-16 | 2017-10-20 |  | Y
Central Hudson |  | SolarCity | CH-05474 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8095 | Fishkill Plains | N |  | 3.6 | [13 empty] | NM | N | ABB PVI 3.6 | 2017-06-01 | 2017-06-13 | 8 | 2017-06-13 | [14 empty] | 2017-07-12 | 2017-07-17 |  | Y
Central Hudson |  | SolarCity | CH-05986 | Newburgh | Highland | Ulster | 12528 | G | 5084 | Highland | N |  | 14.2 | [13 empty] | NM | N | DELTA SOLIVIA 6.6TL DELTA SOLIVIA 7.6TL | 2017-06-14 | 2017-07-27 | 30 | 2017-07-27 | [14 empty] | 2017-08-17 | 2017-08-17 |  | Y
Central Hudson |  | SolarCity | CH-06628 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6044 | Spackenkill | N |  | 9 | [13 empty] | NM | N | DELTA SOLIVIA 3.8TL DELTA SOLIVIA 5.2TL | 2017-06-14 | 2017-06-16 | 2 | 2017-06-16 | [14 empty] | 2017-08-16 | 2017-08-17 |  | Y
Central Hudson |  | SolarCity | CH-07467 | Newburgh | Cornwall | Orange | 12518 | G | 4041 | Union Ave | N |  | 17 | [13 empty] | NM | N | DELTA SOLIVIA 7.6TL (2) | 2017-06-27 | 2017-06-27 | 0 | 2017-06-27 | [14 empty] | 2017-09-22 | 2017-09-26 |  | Y
Central Hudson |  | SolarCity | CH-07769 | Kingston | Kingston | Ulster | 12401 | G | 2016 | Lincoln Park | N |  | 5 | [13 empty] | NM | N | ABB PVI 5000 | 2017-06-01 | 2017-06-09 | 6 | 2017-06-09 | [14 empty] | 2017-08-24 | 2017-08-24 |  | Y
Central Hudson |  | Trinity Solar | CH-08405 | Kingston | Saugerties | Ulster | 12477 | G | 2016 | Lincoln Park | N |  | 6 | [13 empty] | NM | N | SolarEdge SE6000A-US | 2017-06-01 | 2017-06-09 | 6 | 2017-06-09 | [14 empty] | 2017-09-01 | 2017-09-01 |  | Y
Central Hudson |  | Trinity Solar | CH-08448 | Newburgh | Newburgh | Orange | 12550 | G | 4012 | West Balmville | N |  | 10 | [13 empty] | NM | N | SolarEdge 10000A-US | 2017-06-01 | 2017-06-09 | 6 | 2017-06-09 | [14 empty] | 2017-09-27 | 2017-10-03 |  | W
Central Hudson |  | Trinity Solar | CH-08494 | Fishkill |  |  | 12590 | G | 8091 | Fishkill Plains | TBD |  | 7.6 | [13 empty] | NM | N | SolarEdge SE7600A-US | 2017-06-01 | 2017-06-13 | 8 | 2017-06-13 | [17 empty] | W
Central Hudson |  | Trinity Solar | CH-08505 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8092 | Fishkill Plains | N |  | 10 | [13 empty] | NM | N | SolarEdge SE10000A-US | 2017-06-01 | 2017-06-13 | 8 | 2017-06-13 | [14 empty] | 2017-09-27 | 2017-10-03 |  | Y
Central Hudson |  | Trinity Solar | CH-08533 | Kingston |  |  | 12477 | G | 3001 | Saugerties | TBD |  | 5 | [13 empty] | NM | N | SolarEdge SE5000A-US | 2017-06-01 | 2017-06-09 | 6 | 2017-06-09 | [17 empty] | W
Central Hudson |  | Trinity Solar | CH-08569 | Newburgh | Wallkill | Ulster | 12589 | G | 5033 | Galeville | N |  | 13.6 | [13 empty] | NM | N | SolarEdge SE11400A-US | 2017-06-01 | 2017-06-09 | 6 | 2017-06-09 | [8 empty] | 350 | 350 |  |  |  |  | 2017-11-29 | 2017-11-30 |  | Y
Central Hudson |  | Lighthouse Solar | CH-00330 | Newburgh | New Paltz | Ulster | 12561 | G | 5021 | Ohioville | N | CH-03754 | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A-US | 2017-06-13 | 2017-06-21 | 6 | 2017-06-21 | [14 empty] | 2017-08-04 | 2017-08-04 |  | Y
Central Hudson |  | PlugPV, LLC. | CH-00576 | Catskill | West Kill | Greene | 12492 | E | 2389 | Vinegar Hill | N |  | 7.6 | [13 empty] | NM | N | SolarEdge SE7600A-US | 2017-06-16 | 2017-06-21 | 3 | 2017-06-21 | [14 empty] | 2017-07-27 | 2017-07-27 |  | Y
Central Hudson |  | SolarCity | CH-05109 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8043 | Myers Corners | N |  | 11.8 | [13 empty] | NM | N | DELTA SOLIVIA 5.2TL DELTA SOLIVIA 6.6TL | 2017-06-27 | 2017-06-27 | 0 | 2017-06-27 | [14 empty] | 2017-07-24 | 2017-07-24 |  | Y
Central Hudson |  | SolarCity | CH-07163 | Newburgh | New Windsor | Orange | 12553 | G | 4095 | Bethlehem Rd | N |  | 3 | [13 empty] | NM | N | ABB PVI-3.0 OUTD-S-US | 2017-06-02 | 2017-06-13 | 7 | 2017-06-13 | [14 empty] | 2017-09-05 | 2017-09-06 |  | Y
Central Hudson |  | Kasselman Solar | CH-00242 | Kingston | Rosendale | Ulster | 12472 | G | 3021 | High Falls | N |  | 8 | [13 empty] | NM | N | Enphase Energy M250 (32) | 2017-06-05 | 2017-06-16 | 9 | 2017-06-16 | [14 empty] | 2017-07-05 | 2017-07-18 |  | Y
Central Hudson |  | New York State Solar Farm | CH-00378 | Kingston | Stone Ridge | Ulster | 12484 | G | 3023 | High Falls | N |  | 11.52 | [13 empty] | NM | N | SunPower SPR-X21 345-C-AC (36) | 2017-06-05 | 2017-06-15 | 8 | 2017-06-15 | [14 empty] | 2017-06-21 | 2017-06-21 |  | Y
Central Hudson |  | Empire Solar Store | CH-01103 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6094 | Manchester | N |  | 7.6 | [13 empty] | NM | N | SolarEdge SE7600A-US | 2017-06-06 | 2017-06-13 | 5 | 2017-06-13 | [14 empty] | 2017-07-13 | 2017-07-13 |  | Y
Central Hudson |  | Hudson Solar | CH-01574 | Newburgh | Wallkill | Ulster | 12589 | G | 5013 | Modena | N |  | 6 | [13 empty] | NM | N | SolarEdge SE6000 A-US | 2017-06-06 | 2017-06-13 | 5 | 2017-06-13 | [14 empty] | 2017-07-17 | 2017-07-21 |  | Y
Central Hudson |  | Hudson Solar | CH-01635 | Catskill | Coxsackie | Greene | 12051 | G | 1072 | Coxsackie | N | CH-01635 | 5.76 | [13 empty] | NM | N | 18 SPR E20-327-C-AC | 2017-06-21 | 2017-06-22 | 1 | 2017-06-22 | [14 empty] | 2017-08-23 | 2017-08-23 |  | Y
Central Hudson |  | Hudson Solar | CH-02412 | Newburgh | Gardiner | Ulster | 12525 | G | 5031 | Galeville | N |  | 10 | [13 empty] | NM | N | SolarEdge SE10000 A-US | 2017-06-06 | 2017-06-20 | 10 | 2017-06-20 | [8 empty] | 350 | 350 |  | 2017-12-08 | 2017-12-08 | 2017-12-19 | 2017-12-19 | 2017-12-19 |  | Y
Central Hudson |  | Solar Generation | CH-08085 | Kingston |  |  | 12404 | G | 3024 | High Falls | N |  | 15.2 | [13 empty] | NM | N | SolarEdge SE7600 A-US (2) | 2017-07-06 | 2017-07-06 | 0 | 2017-07-06 | [8 empty] | 350 | 350 |  | 2017-07-21 | 2017-07-21 | 2017-08-21 | 2017-09-07 | 2017-09-07 |  | W
Central Hudson |  | Solar Generation | CH-08296 | Kingston | Stone Ridge | Ulster | 12484 | G | 3023 | High Falls | N |  | 10.8 | [13 empty] | NM | N | SMA SB7000 TL-US SMA SB3800 TL-US | 2017-06-20 | 2017-06-20 | 0 | 2017-06-20 | [14 empty] | 2017-07-19 | 2017-07-20 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-00127 | Newburgh | Wallkill | Ulster | 12589 | G | 4011 | West Balmville | N |  | 4.48 | [13 empty] | NM | N | SunPower SPR-X21-345 C-AC (14) | 2017-06-08 | 2017-06-20 | 8 | 2017-06-20 | [14 empty] | 2017-07-25 | 2017-07-25 |  | Y
Central Hudson |  | Empire Solar Store | CH-01101 | Newburgh | Newburgh | Orange | 12550 | G | 4012 | West Balmville | N |  | 5 | [13 empty] | NM | N | SolarEdge SE5000A-US | 2017-06-08 | 2017-06-14 | 4 | 2017-06-14 | [14 empty] | 2017-07-10 | 2017-07-18 |  | Y
Central Hudson |  | SolarCity | CH-07151 | Newburgh | Maybrook | Orange | 12543 | G | 4026 | Coldenham | N |  | 5.2 | [13 empty] | NM | N | Delta Solivia 5.2 TL | 2017-06-08 | 2017-06-14 | 4 | 2017-06-14 | [14 empty] | 2017-06-22 | 2017-07-17 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08745 | Kingston | Saugerties | Ulster | 12477 | G | 3001 | Saugerties | N |  | 6.66 | [13 empty] | NM | N | Enphase M215 602LLS22IG (31) | 2017-06-08 | 2017-06-14 | 4 | 2017-06-14 | [14 empty] | 2017-12-26 | 2017-12-26 |  | Y
Central Hudson |  | SolarCity | CH-05329 | Poughkeepsie | Pine Plns | Dutchess | 12567 | G | 7091 | Pulvers Corners | N |  | 7.6 | [13 empty] | NM | N | Delta Solivia 7.6TL | 2017-06-22 | 2017-06-22 | 0 | 2017-06-22 | [14 empty] | 2017-07-17 | 2017-07-20 |  | Y
Central Hudson |  | SolarCity | CH-06429 | Newburgh | Maybrook | Orange | 12543 | G | 4026 | Coldenham | N |  | 5.2 | [13 empty] | NM | N | ABB PVI 5.2 | 2017-06-22 | 2017-06-22 | 0 | 2017-06-22 | [14 empty] | 2017-08-14 | 2017-08-14 |  | Y
Central Hudson |  | Solar Generation | CH-08194 | Kingston | Kingston | Ulster | 12401 | G | 2016 | Lincoln Park | N |  | 5 | [13 empty] | NM | N | SolarEdge SE5000A-US | 2017-06-20 | 2017-06-21 | 1 | 2017-06-21 | [14 empty] | 2017-07-05 | 2017-07-05 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08649 | Catskill | Westerlo | Albany | 12193 | G | 1091 | Westerlo | N |  | 6.23 | [13 empty] | NM | N | Enphase M215 602LLS22IG (29) | 2017-06-09 | 2017-06-14 | 3 | 2017-06-14 | [14 empty] | 2017-08-23 | 2017-08-23 |  | Y
Central Hudson |  | Lotus Energy Inc. | CH-00337 | Kingston | Rosendale | Ulster | 12472 | G | 3021 | High Falls | N |  | 6 | [13 empty] | NM | N | SMA SB 6000TL-US-22 | 2017-06-12 | 2017-06-14 | 2 | 2017-06-14 | [14 empty] | 2017-07-20 | 2017-07-20 |  | Y
Central Hudson |  | SolarCity | CH-07370 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8056 | North Chelsea | N |  | 20.4 | [13 empty] | NM | N | Delta Solivia 7.6TL (2) Delta Solivia 5.2TL | 2017-07-13 | 2017-07-13 | 0 | 2017-07-13 | [8 empty] | 350 | 350 |  | 2017-07-28 | 2017-07-28 | 2017-08-09 | 2017-09-14 | 2017-09-14 |  | Y
Central Hudson |  | SolarCity | CH-07712 | Fishkill | Glenham | Dutchess | 12527 | G | 8013 | Forgebrook | N |  | 3 | [13 empty] | NM | N | ABB PVI-3.0-OUTD-S | 2017-06-21 | 2017-06-22 | 1 | 2017-06-22 | [14 empty] | 2017-08-15 | 2017-08-17 |  | Y
Central Hudson |  | Kasselman Solar | CH-00252 | Catskill | Westerlo | Albany | 12193 | G | 1091 | Westerlo | N |  | 7 | [13 empty] | NM | N | Enphase Energy M250 (28) | 2017-06-21 | 2017-06-22 | 1 | 2017-06-22 | [14 empty] | 2017-07-19 | 2017-07-20 |  | Y
Central Hudson |  | Empire Solar Store | CH-01096 | Poughkeepsie | Lagrangevl | Dutchess | 12540 | G | 6057 | Todd Hill | N |  | 10 | [13 empty] | NM | N | SOLAREDGE 10000 A-US | 2017-06-14 | 2017-06-16 | 2 | 2017-06-16 | [14 empty] | 2017-06-27 | 2017-06-27 |  | Y
Central Hudson |  | SolarCity | CH-05199 | Newburgh | New Windsor | Orange | 12553 | G | 4094 | Bethlehem Rd | N |  | 4.2 | [13 empty] | NM | N | ABB PVI 4.2 | 2017-06-14 | 2017-06-16 | 2 | 2017-06-16 | [14 empty] | 2017-08-28 | 2017-08-28 |  | Y
Central Hudson |  | SolarCity | CH-06447 | Catskill |  |  | 12193 | G | 1092 | Westerlo | TBD |  | 9 | [13 empty] | NM | N | Delta Solivia 5.2TL Delta Solivia 3.8TL | 2017-06-27 | 2017-06-27 | 0 | 2017-06-27 | [17 empty] | W
Central Hudson |  | SolarCity | CH-07271 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6004 | Reynolds Hill | N |  | 10.4 | [13 empty] | NM | N | 2 DELTA SOLIVIA 5.2 | 2017-06-14 | 2017-06-16 | 2 | 2017-06-16 | [14 empty] | 2017-09-14 | 2017-09-14 |  | Y
Central Hudson |  | Hudson Solar | CH-02041 | Kingston | Kingston | Ulster | 12401 | G | 2093 | Hurley Ave | N |  | 3 | [13 empty] | NM | N | SOLAREDGE SE3000 H-US | 2017-06-21 | 2017-06-21 | 0 | 2017-06-21 | [14 empty] | 2017-08-17 | 2017-08-18 |  | Y
Central Hudson |  | SolarCity | CH-07145 | Newburgh | Montgomery | Orange | 12549 | G | 5073 | Montgomery | N |  | 4.2 | [13 empty] | NM | N | ABB PVI-4.2 OUTD-S-US | 2017-06-15 | 2017-06-19 | 2 | 2017-06-19 | [14 empty] | 2017-09-05 | 2017-09-05 |  | Y
Central Hudson |  | SolarCity | CH-07551 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6092 | Manchester | N |  | 6.6 | [13 empty] | NM | N | DELTA SOLIVIA 6.6 | 2017-06-15 | 2017-06-19 | 2 | 2017-06-19 | [14 empty] | 2017-08-29 | 2017-08-29 |  | Y
Central Hudson |  | Trinity Solar | CH-08395 | Catskill | Athens | Greene | 12015 | G | 2002 | North Catskill | N |  | 3 | [13 empty] | NM | N | SolarEdge SE3000A-US | 2017-06-21 | 2017-06-22 | 1 | 2017-06-22 | [14 empty] | 2017-11-27 | 2017-11-30 |  | Y
Central Hudson |  | Trinity Solar | CH-08515 | Newburgh |  |  | 12553 | G | 4054 | Union Ave | TBD |  | 10 | [13 empty] | NM | N | SOLAREDGE SE10000A US | 2017-06-15 | 2017-06-16 | 1 | 2017-06-16 | [17 empty] | W
Central Hudson |  | Trinity Solar | CH-08570 | Newburgh | Maybrook | Orange | 12543 | G | 5052 | Maybrook | N |  | 7.6 | [13 empty] | NM | N | SolarEdge SE7600A-US | 2017-06-15 | 2017-06-16 | 1 | 2017-06-16 | [14 empty] | 2017-10-03 | 2017-10-06 |  | Y
Central Hudson |  | Trinity Solar | CH-08588 | Kingston |  |  | 12401 | G | 1024 | East Kingston | TBD |  | 4.2 | [13 empty] | NM | N | ABB PVI-4.2 OUTD-S-US | 2017-06-15 | 2017-06-16 | 1 | 2017-06-16 | [17 empty] | W
Central Hudson |  | Empire Solar Store | CH-01093 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 10 | [13 empty] | NM | N | SOLAREDGE 10000 A-US | 2017-07-31 | 2017-07-31 | 0 | 2017-07-31 | [14 empty] | 2017-08-30 | 2017-08-31 |  | Y
Central Hudson |  | Hudson Solar | CH-01216 | Fishkill | Cold Spg | Putnam | 10516 | G | 8066 | Merritt Park | N |  | 15.1 | [13 empty] | NM | N | 2 SolarEdge Technologies SE 7600A-US (208V) | 2017-06-16 | 2017-06-22 | 4 | 2017-06-22 | [14 empty] | 2018-05-07 | 2018-05-24 |  | Y |  | Storm Restoration due to 5/15/18 Damaging Winds and Rains including Tornados and Macroburst.
Central Hudson |  | Lam Development | CH-02584 | Kingston |  |  | 12404 | G | 3081 | Kerhonkson | TBD |  | 2000 | [13 empty] | CDG | N | SMA TRIPOWER 30000 (66) SMA TRIPOWER 20000 (1) | 2017-06-23 | 2017-07-07 | 9 | 2017-07-07 | 2017-07-07 | 2017-07-17 | 6 | [14 empty] | W
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08744 | Kingston |  |  | 12477 | G | 3004 | Saugerties | TBD |  | 3.44 | [13 empty] | NM | N | ENPHASE M215 602LLS22IG (16) | 2017-06-16 | 2017-06-19 | 1 | 2017-06-19 | [17 empty] | W
Central Hudson |  | SolarCity | CH-05207 | Newburgh | New Windsor | Orange | 12553 | G | 4092 | Bethlehem Rd | N |  | 6.6 | [13 empty] | NM | N | DELTA SOLIVIA 6.6TL | 2017-06-22 | 2017-06-22 | 0 | 2017-06-22 | [14 empty] | 2017-09-05 | 2017-09-06 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-03411 | Fishkill | Beacon | Dutchess | 12508 | G | 8087 | Tioronda | N |  | 5.12 | [13 empty] | NM | N | SUNPOWER SPR-X21-345 C-AC (16) | 2017-06-20 | 2017-06-23 | 3 | 2017-06-23 | [14 empty] | 2017-08-07 | 2017-08-09 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-00177 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8091 | Fishkill Plains | N |  | 11.2 | [13 empty] | NM | N | SUNPOWER SPR-X21-345 C-AC (35) | 2017-06-20 | 2017-06-20 | 0 | 2017-06-20 | [14 empty] | 2017-08-22 | 2017-08-22 |  | Y
Central Hudson |  | Hudson Solar | CH-02205 | Newburgh | Marlboro | Ulster | 12542 | G | 5003 | Marlboro | N |  | 7.6 | [13 empty] | NM | N | SolarEdge SE7600 A-US-U | 2017-06-20 | 2017-06-21 | 1 | 2017-06-21 | [14 empty] | 2017-09-13 | 2017-09-14 |  | Y
Central Hudson |  | SolarCity | CH-07816 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7053 | Rhinebeck | N | CH-04945 | 6.6 | [13 empty] | NM | N | DELTA SOLIVIA 6.6TL | 2017-06-22 | 2017-06-22 | 0 | 2017-06-22 | [14 empty] | 2017-09-13 | 2017-09-15 |  | Y
Central Hudson |  | Solar Generation | CH-08066 | Kingston | Mt Tremper | Ulster | 12457 | G | 3012 | Woodstock | Y | CH-08066 | 7.6 | [13 empty] | NM | N | SOLAREDGE 7600A-US | 2017-06-21 | 2017-06-23 | 2 | 2017-06-23 | [14 empty] | 2017-12-04 | 2017-12-04 |  | Y
Central Hudson |  | Trinity Solar | CH-08434 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8056 | North Chelsea | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A US | 2017-06-21 | 2017-06-22 | 1 | 2017-06-22 | [14 empty] | 2017-10-11 | 2017-10-11 |  | Y
Central Hudson |  | Trinity Solar | CH-08509 | Fishkill | Beacon | Dutchess | 12508 | G | 8016 | Forgebrook | N |  | 3.8 | [13 empty] | NM | N | SOLAREDGE SE3800A US | 2017-06-21 | 2017-06-22 | 1 | 2017-06-22 | [14 empty] | 2017-10-20 | 2017-10-25 |  | Y
Central Hudson |  | Trinity Solar | CH-08552 | Newburgh | Gardiner | Ulster | 12525 | G | 5031 | Galeville | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A US | 2017-06-22 | 2017-06-22 | 0 | 2017-06-22 | [14 empty] | 2018-11-14 | 2018-11-15 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08702 | Fishkill |  |  | 12533 | G | 8071 | Shenandoah | TBD |  | 2.365 | [13 empty] | NM | N | ENPHASE M215 602LLS22IG (11) | 2017-06-21 | 2017-06-22 | 1 | 2017-06-22 | [17 empty] | W
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08724 | Catskill | Acra | Greene | 12405 | G | 2043 | South Cairo | N |  | 6.45 | [13 empty] | NM | N | ENPHASE M215 602LLS22IG (30) | 2017-08-14 | 2017-08-14 | 0 | 2017-08-14 | [14 empty] | 2017-09-22 | 2017-09-26 |  | Y
Central Hudson |  | Hudson Solar | CH-02378 | Fishkill | Cold Spg | Putnam | 10516 | G | 8087 | Tioronda | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE6000 A-US-U | 2017-06-22 | 2017-06-22 | 0 | 2017-06-22 | [14 empty] | 2017-10-09 | 2017-10-09 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-00131 | Newburgh | New Windsor | Orange | 12553 | G | 4095 | Bethlehem Rd | N |  | 9.92 | [13 empty] | NM | N | SUNPOWER SPR-X22-360 C-AC (31) | 2017-06-23 | 2017-06-23 | 0 | 2017-06-23 | [14 empty] | 2017-09-05 | 2017-09-06 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-00136 | Newburgh | Rock Tavern | Orange | 12575 | G | 4097 | Bethlehem Rd | N |  | 7.36 | [13 empty] | NM | N | SUNPOWER SPR-X21-335-BLK C-AC (23) | 2017-06-23 | 2017-06-23 | 0 | 2017-06-23 | [14 empty] | 2017-08-24 | 2017-08-24 |  | Y
Central Hudson |  | Lighthouse Solar | CH-00319 | Newburgh | Wallkill |  | 12589 | G | 5011 | Modena | N |  | 11.4 | [13 empty] | NM | N | SOLAREDGE 11400 A-US | 2017-06-27 | 2017-06-27 | 0 | 2017-06-27 | [17 empty] | W
Central Hudson |  | Apex Solar Power | CH-00675 | Kingston |  |  | 12401 | G | 3021 | High Falls | TBD |  | 16 | [13 empty] | NM | N | SolarEdge SE6000A-US SolarEdge SE10000A-US | 2017-07-12 | 2017-07-12 | 0 | 2017-07-12 | [8 empty] | 350 | 350 |  | 2017-07-20 | 2017-07-20 | 2017-07-26 |  |  |  | W
Central Hudson |  | Trinity Solar | CH-08426 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8091 | Fishkill Plains | N |  | 20 | [13 empty] | NM | N | SolarEdge SE10000A-US (2) | 2017-07-18 | 2017-07-18 | 0 | 2017-07-18 | [8 empty] | 350 | 350 |  | 2017-08-07 | 2017-08-07 | 2017-09-27 | 2017-10-12 | 2017-10-13 |  | Y
Central Hudson |  | Trinity Solar | CH-08433 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8092 | Fishkill Plains | N |  | 11.4 | [13 empty] | NM | N | SOLAREDGE SE11400A US | 2017-06-26 | 2017-06-26 | 0 | 2017-06-26 | [14 empty] | 2017-10-20 | 2017-10-27 |  | Y
Central Hudson |  | Trinity Solar | CH-08480 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6044 | Spackenkill | N |  | 10 | [13 empty] | NM | N | SOLAREDGE SOLAREDGE US | 2017-06-26 | 2017-06-26 | 0 | 2017-06-26 | [14 empty] | 2017-09-20 | 2017-09-25 |  | Y
Central Hudson |  | Trinity Solar | CH-08562 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8094 | Fishkill Plains | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A-US | 2017-06-26 | 2017-06-26 | 0 | 2017-06-26 | [14 empty] | 2017-11-17 | 2017-11-17 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-00144 | Fishkill | Beacon | Dutchess | 12508 | G | 8015 | Forgebrook | N |  | 3.84 | [13 empty] | NM | N | SUNPOWER SPR-X21-345 C-AC (12) | 2017-06-27 | 2017-06-27 | 0 | 2017-06-27 | [14 empty] | 2017-10-10 | 2017-10-10 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-00154 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8056 | North Chelsea | N |  | 11.52 | [13 empty] | NM | N | SUNPOWER SPR-X21-345 C-AC (36) | 2017-06-27 | 2017-06-27 | 0 | 2017-06-27 | [8 empty] | 350 | 350 |  | 2017-08-31 | 2017-08-31 | 2017-09-27 | 2017-09-29 | 2017-09-29 |  | Y
Central Hudson |  | SolarCity | CH-06024 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8045 | Myers Corners | N |  | 7.6 | [13 empty] | NM | N | DELTA SOLIVIA 7.6TL | 2017-06-29 | 2017-06-29 | 0 | 2017-06-29 | [14 empty] | 2017-07-05 | 2017-07-18 |  | Y
Central Hudson |  | SolarCity | CH-07519 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6046 | Spackenkill | N |  | 3.8 | [13 empty] | NM | N | DELTA SOLIVIA 3.8TL | 2017-06-29 | 2017-06-29 | 0 | 2017-06-29 | [14 empty] | 2017-06-30 | 2017-06-30 |  | Y
Central Hudson |  | SolarCity | CH-07735 | Poughkeepsie |  |  | 12601 | G | 6003 | Reynolds Hill | TBD |  | 3.8 | [13 empty] | NM | N | SOLAREDGE SE 3800A | 2017-06-29 | 2017-06-29 | 0 | 2017-06-29 | [17 empty] | W
Central Hudson |  | Apex Solar Power | CH-00703 | Newburgh | Highland | Ulster | 12528 | G | 5022 | Ohioville | N |  | 6 | [13 empty] | NM | N | SOLAR EDGE SE 6000 | 2017-06-28 | 2017-06-29 | 1 | 2017-06-29 | [14 empty] | 2017-08-22 | 2017-08-23 |  | Y
Central Hudson |  | Hudson Solar | CH-02335 | Kingston | High Fls | Ulster | 12440 | G | 3022 | High Falls | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE7600 A-US-U | 2017-06-28 | 2017-06-28 | 0 | 2017-06-28 | [14 empty] | 2017-10-04 | 2017-10-18 |  | Y
Central Hudson |  | SolarCity | CH-06116 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8072 | Shenandoah | N |  | 3 | [13 empty] | NM | N | ABB PVI-3.0 OUTD-S-US | 2017-06-28 | 2017-06-29 | 1 | 2017-06-29 | [14 empty] | 2017-09-14 | 2017-09-14 |  | Y
Central Hudson |  | SolarCity | CH-06928 | Fishkill | Beacon | Dutchess | 12508 | G | 8017 | Forgebrook | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A-US | 2017-07-03 | 2017-07-03 | 0 | 2017-07-03 | [14 empty] | 2017-08-21 | 2017-08-21 |  | Y
Central Hudson |  | Seed Solar | CH-08859 | Catskill | Ravena | Albany | 12143 | G | 1083 | New Baltimore | N |  | 6.25 | [13 empty] | NM | N | ENPHASE M250 240V (25) | 2017-06-28 | 2017-06-28 | 0 | 2017-06-28 | [14 empty] | 2017-08-15 | 2017-08-18 |  | Y
Central Hudson |  | Lighthouse Solar | CH-00270 | Kingston | Kerhonkson | Ulster | 12446 | G | 3083 | Kerhonkson | N |  | 5.04 | [13 empty] | NM | N | ENPHASE S280 60-LL-2-US (18) | 2017-07-13 | 2017-07-13 | 0 | 2017-07-13 | [14 empty] | 2017-10-20 | 2017-10-25 |  | Y
Central Hudson |  | New York State Solar Farm | CH-00403 | Newburgh | Gardiner | Ulster | 12525 | G | 5031 | Galeville | N |  | 14.4 | [13 empty] | NM | N | SUNPOWER SPR-X21 345-C-AC (45) | 2017-06-29 | 2017-07-10 | 6 | 2017-07-10 | [8 empty] | 350 | 350 |  | 2017-07-20 | 2017-07-20 | 2017-08-02 | 2017-08-02 | 2017-08-07 |  | Y
Central Hudson |  | Borrego Solar Systems, Inc. | CH-00609 | Catskill | Greenville | Greene | 12083 | G | 1093 | Westerlo | N |  | 5000 | [13 empty] | CDG | Y | 40 - Sungrow SG125HV - 125 kW inverters | 2017-07-13 | 2017-07-17 | 2 | 2017-07-17 | 2017-07-17 | 2017-08-03 | 13 | 2017-09-21 | 2017-09-22 | 2017-12-19 | 60 | 20814.7 | 1848564 | 1437852.13 | 2018-01-05 | 2018-06-20 | 2018-06-20 | 2020-02-13 | 2020-03-09 | 2020-03-10 | 2020-06-04 | Y | Y | CH-00609, CH-00610, CH-00611, CH-00612, and CH-00613 consolidated to two 5 MW projects. Combined application numbers are CH-00609 and CH-00610.
Central Hudson |  | Borrego Solar Systems, Inc. | CH-00610 | Catskill | Greenvl | Greene | 12083 | G | 1093 | Westerlo | N |  | 5000 | [13 empty] | CDG | Y | 40 - Sungrow SG125HV - 125 kW inverters | 2017-07-13 | 2017-07-17 | 2 | 2017-07-17 | 2017-07-17 | 2017-08-03 | 13 | 2017-09-21 | 2017-09-22 | 2017-12-19 | 60 | 20814.69 | 1848564 | 1437852.13 | 2018-01-05 | 2018-06-20 | 2018-06-20 | 2020-02-14 | 2020-03-09 | 2020-03-10 | 2020-06-04 | Y | Y | CH-00609, CH-00610, CH-00611, CH-00612, and CH-00613 consolidated to two 5 MW projects. Combined application numbers are CH-00609 and CH-00610.
Central Hudson |  | Borrego Solar Systems, Inc. | CH-00611 | Catskill | Greenvl |  | 12083 | G | 1091 | Westerlo | TBD |  | 2000 | [13 empty] | CDG | Y | 16 - Sungrow SG125HV - 125 kW inverters | 2017-07-13 | 2017-07-17 | 2 | 2017-07-17 | 2017-07-17 | 2017-08-03 | 13 | 2017-09-21 | 2017-09-22 | 2017-12-19 | 60 | 12000 |  |  | 2018-01-05 | 2018-06-20 | 2018-06-20 |  |  |  |  | W |  | CH-00609 to CH-00613 consolidated to two 5 MW projects, existing application numbers are CH-00609 and CH-00610.
Central Hudson |  | Borrego Solar Systems, Inc. | CH-00612 | Catskill | Greenvl |  | 12083 | G | 1091 | Westerlo | TBD |  | 2000 | [13 empty] | CDG | Y | 16 - Sungrow SG125HV - 125 kW inverters | 2017-07-13 | 2017-07-17 | 2 | 2017-07-17 | 2017-07-17 | 2017-08-03 | 13 | 2017-09-21 | 2017-09-22 | 2017-12-19 | 60 | 12000 |  |  | 2018-01-05 | 2018-06-20 | 2018-06-20 |  |  |  |  | W |  | CH-00609 to CH-00613 consolidated to two 5 MW projects, existing application numbers are CH-00609 and CH-00610.
Central Hudson |  | Borrego Solar Systems, Inc. | CH-00613 | Catskill | Greenvl |  | 12083 | G | 1091 | Westerlo | TBD |  | 2000 | [13 empty] | CDG | Y | 16 - Sungrow SG125HV - 125kW | 2017-07-13 | 2017-07-17 | 2 | 2017-07-17 | 2017-07-17 | 2017-08-03 | 13 | 2017-09-21 | 2017-09-22 | 2017-12-19 | 60 | 12000 |  |  | 2018-01-05 | 2018-06-20 | 2018-06-20 |  |  |  |  | W |  | CH-00609 to CH-00613 consolidated to two 5 MW projects, existing application numbers are CH-00609 and CH-00610.
Central Hudson |  | Hudson Solar | CH-01421 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7053 | Rhinebeck | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600 SOLAREDGE SE7600 A-US-U | 2017-06-29 | 2017-07-06 | 4 | 2017-07-06 | [14 empty] | 2017-11-01 | 2017-11-07 |  | Y
Central Hudson |  | Hudson Solar | CH-02477 | Fishkill | Beacon | Dutchess | 12508 | G | 8015 | Forgebrook | N | CH-01923 | 3.8 | [13 empty] | NM | N | SOLAREDGE SE3800 H-US | 2017-07-17 | 2017-07-17 | 0 | 2017-07-17 | [14 empty] | 2017-10-02 | 2017-10-06 |  | Y
Central Hudson |  | Lam Development | CH-02585 | Poughkeepsie |  |  | 12514 | G | 7071 | Stanfordville | TBD |  | 2000 | [13 empty] | CDG | N | SMA TRIPOWER 30000 TL-US-10 (66) SMA TRIPOWER 20000 TL-US-10 (1) | 2017-06-29 | 2017-07-13 | 9 | 2017-07-13 | 2017-07-13 | 2017-08-03 | 15 | [14 empty] | W
Central Hudson |  | Solar Generation | CH-08245 | Kingston | Kingston | Ulster | 12401 | G | 2091 | Hurley Ave | N |  | 11.52 | [13 empty] | NM | N | SUNPOWER X22-360 X22-360 (36) | 2017-06-30 | 2017-06-30 | 0 | 2017-06-30 | [8 empty] | 350 | 350 |  | 2017-07-21 | 2017-07-21 | 2017-07-26 | 2017-09-05 | 2017-09-05 |  | Y
Central Hudson |  | SolarCity | CH-06814 | Fishkill |  |  | 12590 | G | 8044 | Myers Corners | TBD |  | 4.2 | [13 empty] | NM | N | ABB PVI-4.2 OUTD-S-US | 2017-07-11 | 2017-07-12 | 1 | 2017-07-12 | [17 empty] | W
Central Hudson |  | SolarCity | CH-07587 | Fishkill | Beacon | Dutchess | 12508 | G | 8017 | Forgebrook | N |  | 3.6 | [13 empty] | NM | N | ABB PVI-3.6 OUTD-S-US | 2017-07-03 | 2017-07-06 | 2 | 2017-07-06 | [14 empty] | 2017-09-13 | 2017-09-14 |  | Y
Central Hudson |  | SolarCity | CH-07758 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6003 | Reynolds Hill | N |  | 3 | [13 empty] | NM | N | SOLAREDGE SE 3000A-US | 2017-07-10 | 2017-07-12 | 2 | 2017-07-12 | [14 empty] | 2017-08-14 | 2017-08-15 |  | Y
Central Hudson |  | SunBlue Energy | CH-09132 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8071 | Shenandoah | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE7600 US | 2017-07-17 | 2017-07-18 | 1 | 2017-07-18 | [14 empty] | 2017-08-04 | 2017-08-23 |  | Y
Central Hudson |  | New York State Solar Farm | CH-00425 | Kingston | Saugerties | Ulster | 12477 | G | 3004 | Saugerties | N |  | 4.48 | [13 empty] | NM | N | SUNPOWER SPR-X21 345-C-AC (14) | 2017-07-05 | 2017-07-06 | 1 | 2017-07-06 | [14 empty] | 2017-09-05 | 2017-09-05 |  | Y
Central Hudson |  | New York State Solar Farm | CH-00466 | Poughkeepsie | Hopewell Jct | Dutchess | 12533 | G | 6052 | Todd Hill | N |  | 13.44 | [13 empty] | NM | N | SUNPOWER SPR-X22 360-C-AC (42) | 2017-07-05 | 2017-07-07 | 2 | 2017-07-07 | [8 empty] | 350 | 350 |  | 2017-07-27 | 2017-07-27 | 2017-08-03 | 2017-08-14 | 2017-08-14 |  | Y
Central Hudson |  | New York State Solar Farm | CH-00469 | Newburgh | Montgomery | Orange | 12549 | G | 5073 | Montgomery | N |  | 8.96 | [13 empty] | NM | N | SUNPOWER SPR-X21 345-C-AC (28) | 2017-07-05 | 2017-07-07 | 2 | 2017-07-07 | [14 empty] | 2017-08-09 | 2017-08-17 |  | Y
Central Hudson |  | Trinity Solar | CH-08429 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8091 | Fishkill Plains | N |  | 10 | [13 empty] | NM | N | SOLAREDGE SE10000A US | 2017-07-05 | 2017-07-07 | 2 | 2017-07-07 | [14 empty] | 2017-10-31 | 2017-11-01 |  | Y
Central Hudson |  | Trinity Solar | CH-08468 | Kingston | Ulster Pk | Ulster | 12487 | G | 1023 | East Kingston | N |  | 13.6 | [13 empty] | NM | N | SOLAREDGE SE3000A US | 2017-07-07 | 2017-07-27 | 14 | 2017-07-27 | [14 empty] | 2017-10-10 | 2017-10-24 |  | Y
Central Hudson |  | Trinity Solar | CH-08516 | Newburgh |  |  | 12553 | G | 4046 | Union Ave | TBD |  | 3.8 | [13 empty] | NM | N | SOLAREDGE SE3800A US | 2017-07-05 | 2017-07-07 | 2 | 2017-07-07 | [17 empty] | W
Central Hudson |  | Infinity Solar Systems | CH-00143 | Newburgh | Newburgh | Orange | 12550 | G | 4011 | West Balmville | N |  | 8.6 | [13 empty] | NM | N | 27 SunPower SPR-X21-345-C-AC (208V) SUNPOWER SPR-X21-345 C-AC (27) | 2017-07-06 | 2017-07-07 | 1 | 2017-07-07 | [14 empty] | 2018-01-26 | 2018-02-02 |  | Y
Central Hudson |  | Lighthouse Solar | CH-00283 | Kingston | Accord | Ulster | 12404 | G | 3081 | Kerhonkson | N |  | 10 | [13 empty] | NM | N | SOLAREDGE SE10000 A-U | 2017-07-07 | 2017-07-10 | 1 | 2017-07-10 | [8 empty] | 350 | 350 |  | 2017-07-14 | 2017-07-14 | 2017-07-21 | 2017-07-21 | 2017-07-21 |  | Y
Central Hudson |  | Lotus Energy Inc. | CH-00335 | Catskill | Surprise | Greene | 12176 | G | 2061 | Freehold | N |  | 11.52 | [13 empty] | NM | N | SUNPOWER SPR-X21-345-C-AC (36) | 2017-07-06 | 2017-07-07 | 1 | 2017-07-07 | [14 empty] | 2017-08-03 | 2017-08-03 |  | Y
Central Hudson |  | Empire Solar Store | CH-01104 | Poughkeepsie | Clinton Corners | Dutchess | 12514 | G | 7071 | Stanfordville | N |  | 10 | [13 empty] | NM | N | SOLAREDGE 10000 A-US | 2017-07-18 | 2017-07-18 | 0 | 2017-07-18 | [14 empty] | 2017-10-11 | 2017-10-11 |  | Y
Central Hudson |  | SolarCity | CH-05178 | Newburgh | New Windsor | Orange | 12553 | G | 4042 | Union Ave | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE 6000A | 2017-07-06 | 2017-07-07 | 1 | 2017-07-07 | [14 empty] | 2017-09-06 | 2017-09-06 |  | Y
Central Hudson |  | Trinity Solar | CH-08425 | Fishkill |  |  | 12590 | G | 8091 | Fishkill Plains | TBD |  | 15.2 | [13 empty] | NM | N | SOLAREDGE SE7600A US (2) | 2017-07-06 | 2017-07-07 | 1 | 2017-07-07 | [17 empty] | W
Central Hudson |  | Trinity Solar | CH-08481 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6042 | Spackenkill | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A SE6000A US | 2017-07-06 | 2017-07-07 | 1 | 2017-07-07 | [14 empty] | 2017-11-01 | 2017-11-07 |  | Y
Central Hudson |  | Trinity Solar | CH-08520 | Newburgh | New Windsor | Orange | 12553 | G | 4095 | Bethlehem Rd | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A US | 2017-07-06 | 2017-07-07 | 1 | 2017-07-07 | [14 empty] | 2017-11-20 | 2017-11-21 |  | Y
Central Hudson |  | Trinity Solar | CH-08576 | Newburgh | Cornwall-Hdsn | Orange | 12520 | G | 4043 | Union Ave | N |  | 6 | [13 empty] | NM | N | SolarEdge SE6000A US | 2017-07-06 | 2017-07-07 | 1 | 2017-07-07 | [14 empty] | 2017-10-10 | 2017-10-10 |  | Y
Central Hudson |  | Hudson Solar | CH-02449 | Poughkeepsie | Staatsburg | Dutchess | 12580 | G | 7041 | Staatsburg | N | CH-02087 | 4.16 | [13 empty] | NM | N | SUNPOWER X21-335 C-AC (13) | 2017-07-17 | 2017-07-17 | 0 | 2017-07-17 | [8 empty] | 350 | 350 |  | 2017-08-07 | 2017-08-07 | 2017-08-22 | 2017-10-02 | 2017-10-06 |  | Y
Central Hudson |  | Kasselman Solar | CH-00228 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6092 | Manchester | N |  | 7.5 | [13 empty] | NM | N | ENPHASE ENERGY M250 (30) | 2017-07-10 | 2017-07-10 | 0 | 2017-07-10 | [14 empty] | 2017-09-15 | 2017-09-20 |  | Y
Central Hudson |  | Kasselman Solar | CH-00249 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8091 | Fishkill Plains | N |  | 9.8 | [13 empty] | NM | N | ENPHASE ENERGY S280 (35) | 2017-07-10 | 2017-07-12 | 2 | 2017-07-12 | [14 empty] | 2017-08-14 | 2017-08-17 |  | Y
Central Hudson |  | Kasselman Solar | CH-03531 | Fishkill | Hopewell Jct |  | 12533 | G | 8071 | Shenandoah | N |  | 15.5 | [13 empty] | NM | N | ENPHASE ENERGY M250 (62) | 2017-07-10 | 2017-07-21 | 9 | 2017-07-21 | [14 empty] | 2017-08-28 | 2017-08-29 |  | W
Central Hudson |  | Empire Solar Store | CH-01102 | Newburgh | Wallkill | Ulster | 12589 | G | 4011 | West Balmville | N |  | 7.6 | [13 empty] | NM | N | SolarEdge SE7600A-US | 2017-07-10 | 2017-07-12 | 2 | 2017-07-12 | [14 empty] | 2017-07-13 | 2017-07-13 |  | Y
Central Hudson |  | Solar Generation | CH-08201 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8096 | Fishkill Plains | N |  | 11.52 | [13 empty] | NM | N | SUNPOWERX22-360-C-AC (36) | 2017-07-12 | 2017-07-13 | 1 | 2017-07-13 | [14 empty] | 2017-08-17 | 2017-08-18 |  | Y
Central Hudson |  | Empire Solar Store | CH-01098 | Newburgh | Marlboro | Ulster | 12542 | G | 5003 | Marlboro | N | CH-01098 | 11.4 | [13 empty] | NM | N | SOLAREDGE 11400 A-US | 2017-07-11 | 2017-07-12 | 1 | 2017-07-12 | [14 empty] | 2017-07-12 | 2017-07-12 |  | Y
Central Hudson |  | Solar Spectrum LLC | CH-04924 | Fishkill | Beacon | Dutchess | 12508 | G | 8085 | Tioronda | N |  | 5 | [13 empty] | NM | N | SOLAREDGE TECHNOLOGI SE 5000A-US (240V) 240V | 2017-07-11 | 2017-07-12 | 1 | 2017-07-12 | [14 empty] | 2017-08-30 | 2017-08-30 |  | Y
Central Hudson |  | SolarCity | CH-06689 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 7041 | Staatsburg | N |  | 9.6 | [13 empty] | NM | N | ABB PVI-6000-OUTD-US ABB PVI-3.6-OUTD-US | 2017-07-17 | 2017-07-18 | 1 | 2017-07-18 | [14 empty] | 2017-11-02 | 2017-11-07 |  | Y
Central Hudson |  | Trinity Solar | CH-08543 | Fishkill |  |  | 12524 | G | 8011 | Forgebrook | TBD |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE7600A | 2017-07-11 | 2017-07-12 | 1 | 2017-07-12 | [17 empty] | W
Central Hudson |  | Empire Solar Store | CH-01099 | Kingston | Saugerties | Ulster | 12477 | G | 1021 | East Kingston | N |  | 12 | [13 empty] | NM | N | SOLAREDGE 6000 A-US (2) | 2017-07-12 | 2017-07-13 | 1 | 2017-07-13 | [8 empty] | 350 | 350 |  | 2017-08-29 | 2017-08-29 | 2017-10-04 | 2017-10-05 | 2017-10-05 |  | Y
Central Hudson |  | Solar Spectrum LLC | CH-04923 | Fishkill | Poughkeepsie | Dutchess | 12603 | G | 8022 | Knapps Corners | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE 6000A-US (240V) 240V | 2017-07-18 | 2017-07-20 | 2 | 2017-07-20 | [8 empty] | 350 | 350 |  | 2017-08-04 | 2017-08-04 | 2017-10-27 | 2017-09-15 | 2017-09-15 |  | Y
Central Hudson |  | Trinity Solar | CH-08501 | Fishkill |  |  | 12533 | G | 8094 | Fishkill Plains | TBD |  | 11.4 | [13 empty] | NM | N | SOLAREDGE SE11400A US | 2017-07-12 | 2017-07-13 | 1 | 2017-07-13 | [17 empty] | W
Central Hudson |  | Infinity Solar Systems | CH-03501 | Newburgh | Maybrook | Orange | 12543 | G | 4026 | Coldenham | N |  | 8 | [13 empty] | NM | N | SUNPOWER SPR-X21-345 C-AC (25) | 2017-07-13 | 2017-07-14 | 1 | 2017-07-14 | [14 empty] | 2017-09-22 | 2017-09-29 |  | Y
Central Hudson |  | Kasselman Solar | CH-00254 | Kingston | Saugerties |  | 12477 | G | 2015 | Lincoln Park | TBD |  | 4 | [13 empty] | NM | N | ENPHASE ENERGY M250 (16) | 2017-07-13 | 2017-07-13 | 0 | 2017-07-13 | [17 empty] | W
Central Hudson |  | SolarCity | CH-07377 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8072 | Shenandoah | N |  | 5 | [13 empty] | NM | N | SolarEdge SE5000A-US | 2017-07-13 | 2017-07-13 | 0 | 2017-07-13 | [14 empty] | 2017-08-16 | 2017-08-18 |  | Y
Central Hudson |  | Empire Solar Store | CH-01105 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 6051 | Todd Hill | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE 7600 A-US | 2017-07-14 | 2017-07-14 | 0 | 2017-07-14 | [14 empty] | 2017-08-07 | 2017-08-09 |  | Y
Central Hudson |  | Hudson Solar | CH-01641 | Catskill | Ravena | Albany | 12143 | G | 1082 | New Baltimore | N |  | 10 | [13 empty] | NM | N | SOLAREDGE SE10000 A-US-U | 2017-07-14 | 2017-07-20 | 4 | 2017-07-20 | [14 empty] | 2017-10-09 | 2017-10-09 |  | Y
Central Hudson |  | SolarCity | CH-05090 | Newburgh | Campbell Hall | Orange | 10916 | G | 5051 | Maybrook | N |  | 4.2 | [13 empty] | NM | N | ABB PVI-4.2 OUTD-S-US | 2017-07-14 | 2017-07-18 | 2 | 2017-07-18 | [14 empty] | 2017-08-10 | 2017-08-14 |  | Y
Central Hudson |  | SolarCity | CH-05210 | Poughkeepsie | Verbank | Dutchess | 12585 | G | 6057 | Todd Hill | N |  | 9 | [13 empty] | NM | N | DELTA SOLIVIA 3.8TL DELTA SOLIVIA 5.2TL | 2017-07-14 | 2017-07-14 | 0 | 2017-07-14 | [14 empty] | 2017-07-24 | 2017-07-24 |  | Y
Central Hudson |  | CEC Development, LLC | CH-03355 | Catskill | Cairo |  | 12413 | G | 2041 | South Cairo | TBD |  | 1980 | [13 empty] | CDG | Y | Solectria PVI-60TL (33) | 2017-08-01 | 2017-08-14 | 9 | 2017-08-14 | 2017-08-14 | 2017-08-25 | 9 | 2017-11-10 | 2017-11-14 | 2018-02-13 | 60 | 28030.06 | 552198 | 1207.5 | 2018-05-07 | [5 empty] | 2019-03-28 | W |  | Effective grounding study in progress.
Central Hudson |  | Direct Energy Solar | CH-00930 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 7011 | Hibernia | N |  | 11.2 | [13 empty] | NM | N | ENPHASE IQ6+ 72-2-US (40) | 2017-07-17 | 2017-07-18 | 1 | 2017-07-18 | [14 empty] | 2017-09-20 | 2017-10-10 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08773 | Newburgh | New Windsor | Orange | 12553 | G | 4097 | Bethlehem Rd | N | CH-23740 | 7.74 | [13 empty] | NM | N | ENPHASE M215 602LLS22IG (36) | 2017-07-17 | 2017-07-17 | 0 | 2017-07-17 | [14 empty] | 2018-01-12 | 2018-01-12 |  | Y
Central Hudson |  | Salisbury Mills Association | CH-09732 | Newburgh | Salisbury Mls | Orange | 12577 | G | 4095 | Bethlehem Rd | N | [11 empty] | 750 |  |  |  | CDG | Y | GENERAL ELECTRIC T1 | 2017-07-17 | 2017-07-31 | 10 | 2017-07-31 | [14 empty] | 2018-03-16 | 1987-09-15 |  | Y | N | March 2018 - Account readover to new customer.
Central Hudson |  | Infinity Solar Systems | CH-00186 | Newburgh | Newburgh | Orange | 12550 | G | 4023 | Coldenham | N |  | 5.44 | [13 empty] | NM | N | SUNPOWER SPR-X21-335-BLK C-AC (17) | 2017-07-18 | 2017-07-20 | 2 | 2017-07-20 | [14 empty] | 2017-09-26 | 2017-10-02 |  | Y
Central Hudson |  | Direct Energy Solar | CH-01044 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7062 | Milan | N |  | 10.32 | [13 empty] | NM | N | ENPHASE M215 60-2LL-S22 (48) | 2017-07-18 | 2017-07-20 | 2 | 2017-07-20 | [14 empty] | 2017-07-31 | 2017-08-03 |  | Y
Central Hudson |  | Hudson Solar | CH-01459 | Kingston | Ulster Pk |  | 12487 | G | 3041 | Sturgeon Pool | TBD |  | 30 | [13 empty] | NM | N | SOLAREDGE SE10000 A-US-U (3) | 2017-07-18 | 2017-08-01 | 10 | 2017-08-01 | [8 empty] | 1100 | [8 empty] | W
Central Hudson |  | SolarCity | CH-06021 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8043 | Myers Corners | Y |  | 7.6 | 5 | [12 empty] | NM | N | 1 SolarEdge Technologies SE 7600A-US (208V) 1TeslaAC Powerwall 2.0 | 2017-07-24 | 2017-07-26 | 2 | 2017-07-26 | [14 empty] | 2018-01-22 | 2018-01-23 |  | Y
Central Hudson |  | New York State Solar Farm | CH-00370 | Newburgh | Newburgh | Orange | 12550 | G | 410 | Montgomery St | N |  | 2.56 | [13 empty] | NM | N | SUNPOWER X21 AC (8) | 2017-07-19 | 2017-07-26 | 5 | 2017-07-26 | [14 empty] | 2017-10-04 | 2017-10-13 |  | Y
Central Hudson |  | Autonomous Energies LLC | CH-00752 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7055 | Rhinebeck | N |  | 7.7 | [13 empty] | NM | N | SMA 7.7 US-40 | 2017-07-20 | 2017-07-20 | 0 | 2017-07-20 | [14 empty] | 2017-12-15 | 2017-12-26 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08679 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 6073 | East Park | N |  | 7.74 | [13 empty] | NM | N | ENPHASE M215 602LLS22IG (36) | 2017-07-19 | 2017-07-19 | 0 | 2017-07-19 | [14 empty] | 2018-01-08 | 2018-01-12 |  | Y
Central Hudson |  | EnterSolar LLC | CH-03356 | Kingston |  |  | 12477 | G | 3002 | Saugerties | TBD |  | 1980 | [13 empty] | CDG | N | SOLECTRIA PVI 60TL (33) | 2017-08-17 | 2017-08-17 | 0 | 2017-08-17 | 2017-08-17 | 2017-08-30 | 9 |  |  |  |  | 39000 | [9 empty] | W
Central Hudson |  | Lotus Energy Inc. | CH-00336 | Catskill | Catskill | Greene | 12414 | G | 2003 | North Catskill | N |  | 5 | [13 empty] | NM | N | SMA SB 5000TL-US-22 | 2017-07-20 | 2017-07-26 | 4 | 2017-07-26 | [14 empty] | 2017-08-22 | 2017-08-23 |  | Y
Central Hudson |  | Solar Liberty Energy Systems | CH-04911 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6042 | Spackenkill | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE 7600A-US (208V) | 2017-07-21 | 2017-07-21 | 0 | 2017-07-21 | [14 empty] | 2018-05-02 | 2018-05-03 |  | Y
Central Hudson |  | High Peaks Solar, LLC | CH-00122 | Catskill | Coeymans Hollow | Albany | 12046 | G | 1081 | New Baltimore | N |  | 6 | [13 empty] | NM | N | ENPHASE ENERGY M250-60-2LL S22 (24) | 2017-07-26 | 2017-07-26 | 0 | 2017-07-26 | [14 empty] | 2017-09-25 | 2017-10-03 |  | Y
Central Hudson |  | Trinity Solar | CH-08453 | Newburgh | Clintondale | Ulster | 12515 | G | 5012 | Modena | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A US | 2017-09-07 | 2017-09-07 | 0 | 2017-09-07 | [14 empty] | 2017-10-20 | 2017-10-25 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-00213 | Newburgh | Campbell Hall | Orange | 10916 | G | 5052 | Maybrook | N |  | 15.68 | [13 empty] | NM | N | SUNPOWER SPR-X21-345 C-AC (49) | 2017-07-25 | 2017-07-26 | 1 | 2017-07-26 | [8 empty] | 350 | 350 |  | 2017-09-27 | 2017-09-27 | 2017-11-28 | 2017-10-23 | 2017-11-28 |  | Y
Central Hudson |  | SolarCity | CH-06260 | Newburgh |  |  | 12553 | G | 4046 | Union Ave | TBD |  | 10.4 | [13 empty] | NM | N | DELTA SOLIVIA 6.6 TL DELTA SOLIVIA 3.8 TL | 2017-08-03 | 2017-08-03 | 0 | 2017-08-03 | [17 empty] | W
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08775 | Newburgh | Montgomery | Orange | 12549 | G | 5072 | Montgomery | N |  | 3.65 | [13 empty] | NM | N | ENPHASE M215 602LLS22IG (17) | 2017-07-26 | 2017-07-26 | 0 | 2017-07-26 | [14 empty] | 2017-11-07 | 2017-11-09 |  | Y
Central Hudson |  | Kasselman Solar | CH-03535 | Catskill | Westerlo | Albany | 12193 | G | 1091 | Westerlo | N | CH-00236 | 3 | [13 empty] | NM | N | ENPHASE M250 (12) | 2017-07-27 | 2017-07-27 | 0 | 2017-07-27 | [14 empty] | 2017-08-23 | 2017-08-24 |  | Y
Central Hudson |  | Malcarne Contracting | CH-00346 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7061 | Milan | N |  | 3 | [13 empty] | NM | N | SOLAREDGE SE3000H US-240 | 2017-07-27 | 2017-07-27 | 0 | 2017-07-27 | [14 empty] | 2017-09-16 | 2017-09-20 |  | Y
Central Hudson |  | Hudson Solar | CH-01313 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 7024 | Tinkertown | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000 A-US-U | 2017-07-27 | 2017-07-27 | 0 | 2017-07-27 | [14 empty] | 2017-07-27 | 2017-08-14 |  | Y
Central Hudson |  | SolarCity | CH-07509 | Kingston | Saugerties | Ulster | 12477 | G | 3001 | Saugerties | N |  | 3 | [13 empty] | NM | N | ABB PVI-3.0 OUTD-US | 2017-07-27 | 2017-07-28 | 1 | 2017-07-28 | [14 empty] | 2017-09-13 | 2017-09-14 |  | Y
Central Hudson |  | SolarCity | CH-07787 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6094 | Manchester | N |  | 3.8 | [13 empty] | NM | N | SOLAREDGE SE 3800A | 2017-07-27 | 2017-07-27 | 0 | 2017-07-27 | [14 empty] | 2017-10-25 | 2017-10-27 |  | Y
Central Hudson |  | Solar Generation | CH-08148 | Kingston | W Hurley | Ulster | 12491 | G | 2094 | Hurley Ave | N |  | 5.44 | [13 empty] | NM | N | SUNPOWER X22-360 AC (17) | 2017-07-27 | 2017-07-27 | 0 | 2017-07-27 | [14 empty] | 2017-08-29 | 2017-08-29 |  | Y
Central Hudson |  | Lighthouse Solar | CH-03666 | Kingston | Napanoch | Ulster | 12458 | G | 3072 | Honk Falls | N |  | 10 | [13 empty] | NM | N | SOLAREDGE SE10000 A-US | 2017-07-28 | 2017-08-03 | 4 | 2017-08-03 | [14 empty] | 2017-09-21 | 2017-09-25 |  | Y
Central Hudson |  | Lighthouse Solar | CH-00315 | Newburgh | New Paltz | Ulster | 12561 | G | 5011 | Modena | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE7600 A-US | 2017-08-02 | 2017-08-02 | 0 | 2017-08-02 | [14 empty] | 2017-10-03 | 2017-10-06 |  | Y
Central Hudson |  | Solar Generation | CH-08210 | Kingston | W Hurley | Ulster | 12491 | G | 2094 | Hurley Ave | N |  | 15.4 | [13 empty] | NM | N | SMA AMERICA SB7700 (2) | 2017-08-11 | 2017-08-11 | 0 | 2017-08-11 | [8 empty] | 350 | 350 |  | 2017-09-05 | 2017-09-05 | 2017-10-04 | 2017-10-05 | 2017-10-05 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08599 | Catskill | Cairo | Greene | 12413 | G | 2071 | Freehold | N |  | 7.955 | [13 empty] | NM | N | ENPHASE M215 602LLS22IG (37) | 2017-07-28 | 2017-07-28 | 0 | 2017-07-28 | [14 empty] | 2017-10-23 | 2017-10-27 |  | Y
Central Hudson |  | Empire Solar Store | CH-01097 | Fishkill | Cold Spg | Putnam | 10516 | G | 8063 | Merritt Park | N |  | 10 | [13 empty] | NM | N | SOLAREDGE 10000 A-US | 2017-08-17 | 2017-08-17 | 0 | 2017-08-17 | [14 empty] | 2017-10-16 | 2017-10-18 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-00214 | Fishkill | Beacon | Dutchess | 12508 | G | 8017 | Forgebrook | N |  | 3.8 | [13 empty] | NM | N | SUNPOWER SPR-X21-335-BLK C-AC (14) | 2017-08-03 | 2017-08-03 | 0 | 2017-08-03 | [14 empty] | 2017-10-16 | 2017-10-18 |  | Y
Central Hudson |  | Hudson Solar | CH-01656 | Kingston | Stone Ridge | Ulster | 12484 | G | 3023 | High Falls | N |  | 6.4 | [13 empty] | NM | N | SUNPOWER E320-327 C-AC (20) | 2017-08-01 | 2017-08-01 | 0 | 2017-08-01 | [14 empty] | 2017-10-04 | 2017-10-06 |  | Y
Central Hudson |  | Hudson Solar | CH-02039 | Kingston | Mt Tremper | Ulster | 12457 | G | 3012 | Woodstock | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000H-US | 2017-08-14 | 2017-08-14 | 0 | 2017-08-14 | [14 empty] | 2017-10-11 | 2017-10-12 |  | Y
Central Hudson |  | Hudson Solar | CH-02065 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6044 | Spackenkill | N | CH-02065 | 9.6 | [13 empty] | NM | N | SUNPOWER E320-327 C-AC (30) | 2017-08-03 | 2017-08-03 | 0 | 2017-08-03 | [14 empty] | 2017-10-13 | 2017-10-20 |  | Y
Central Hudson |  | Hudson Solar | CH-02319 | Newburgh | Newburgh | Orange | 12550 | G | 4023 | Coldenham | N |  | 13.44 | [13 empty] | NM | N | SUNPOWER E320-327 C-AC (42) | 2017-08-01 | 2017-08-01 | 0 | 2017-08-01 | [14 empty] | 2017-10-18 | 2017-10-23 |  | Y
Central Hudson |  | Solar Generation | CH-08074 | Newburgh | Highland | Ulster | 12528 | G | 5084 | Highland | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE7600 H US | 2017-08-07 | 2017-08-07 | 0 | 2017-08-07 | [14 empty] | 2017-10-03 | 2017-10-18 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08663 | Kingston |  |  | 12401 | G | 2013 | Lincoln Park | TBD |  | 4.73 | [13 empty] | NM | N | ENPHASE M215 602LLS22IG (22) | 2017-08-01 | 2017-08-01 | 0 | 2017-08-01 | [17 empty] | W
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08774 | Newburgh |  |  | 10940 | G | 5051 | Maybrook | TBD |  | 7.31 | [13 empty] | NM | N | ENPHASE M215 602LLS22IG (34) | 2017-08-01 | 2017-08-01 | 0 | 2017-08-01 | [17 empty] | W
Central Hudson |  | Hudson Solar | CH-01691 | Kingston | West Shokan | Ulster | 12494 | G | 3011 | Woodstock | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE7600 A-US-U | 2017-08-02 | 2017-08-02 | 0 | 2017-08-02 | [14 empty] | 2017-10-05 | 2017-10-05 |  | Y
Central Hudson |  | SolarCity | CH-06215 | Newburgh | Newburgh | Orange | 12550 | G | 4024 | Coldenham | N |  | 5.2 | [13 empty] | NM | N | DELTA SOLIVIA 5.2 TL | 2017-08-02 | 2017-08-02 | 0 | 2017-08-02 | [14 empty] | 2017-10-02 | 2017-10-02 |  | Y
Central Hudson |  | Trinity Solar | CH-08402 | Kingston | Kingston | Ulster | 12401 | G | 2093 | Hurley Ave | N |  | 10 | [13 empty] | NM | N | SOLAREDGE SE10000AUS | 2017-08-02 | 2017-08-02 | 0 | 2017-08-02 | [8 empty] | 350 | 350 |  |  |  |  | 2017-11-22 | 2017-11-27 |  | Y
Central Hudson |  | Trinity Solar | CH-08427 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8091 | Fishkill Plains | N |  | 7.6 | [13 empty] | NM | N | 1 SOLAREDGE SE7600A US | 2017-08-02 | 2017-08-02 | 0 | 2017-08-02 | [14 empty] | 2017-11-06 | 2017-11-09 |  | Y
Central Hudson |  | Trinity Solar | CH-08496 | Fishkill |  |  | 12590 | G | 8043 | Myers Corners | TBD |  | 11.4 | [13 empty] | NM | N | 1 SOLAREDGE SE11400A US | 2017-08-02 | 2017-08-02 | 0 | 2017-08-02 | [17 empty] | W
Central Hudson |  | Trinity Solar | CH-08504 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8092 | Fishkill Plains | N |  | 10 | [13 empty] | NM | N | SOLAREDGE SE10000A US | 2017-08-02 | 2017-08-02 | 0 | 2017-08-02 | [14 empty] | 2018-01-02 | 2018-01-04 |  | Y
Central Hudson |  | Trinity Solar | CH-08506 | Fishkill | Fishkill | Dutchess | 12524 | G | 8094 | Fishkill Plains | N |  | 7.6 | [13 empty] | NM | N | 1 SOLAREDGE SE3800A US | 2017-08-02 | 2017-08-02 | 0 | 2017-08-02 | [14 empty] | 2017-12-20 | 2017-12-26 |  | Y
Central Hudson |  | Trinity Solar | CH-08517 | Newburgh | Wallkill | Ulster | 12589 | G | 5043 | East Walden | N |  | 3.8 | [13 empty] | NM | N | 1 SOLAREDGE SE3800HUS | 2017-09-06 | 2017-09-06 | 0 | 2017-09-06 | [14 empty] | 2017-11-20 | 2017-11-21 |  | Y
Central Hudson |  | Trinity Solar | CH-08522 | Newburgh | Montgomery | Orange | 12549 | G | 5073 | Montgomery | N |  | 6 | [13 empty] | NM | N | 1 SOLAREDGE 6000A US | 2017-09-06 | 2017-09-06 | 0 | 2017-09-06 | [14 empty] | 2017-11-07 | 2017-11-09 |  | Y
Central Hudson |  | Trinity Solar | CH-08551 | Newburgh | Newburgh | Orange | 12550 | G | 4047 | Union Ave | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A US | 2017-08-02 | 2017-08-02 | 0 | 2017-08-02 | [14 empty] | 2017-10-25 | 2017-10-30 |  | Y
Central Hudson |  | Lighthouse Solar | CH-00275 | Kingston | Accord | Ulster | 12404 | G | 3024 | High Falls | N |  | 10 | [13 empty] | NM | N | SOLAREDGE SE10000A-US | 2017-08-03 | 2017-08-03 | 0 | 2017-08-03 | [14 empty] | 2017-10-10 | 2017-10-18 |  | Y
Central Hudson |  | New York State Solar Farm | CH-00474 | Newburgh | Clintondale | Ulster | 12515 | G | 5012 | Modena | N | CH-00457 | 3.84 | [13 empty] | NM | N | 12 SUNPOWER SPR-E20 327-C-AC | 2017-08-11 | 2017-08-11 | 0 | 2017-08-11 | [14 empty] | 2017-09-08 | 2017-09-14 |  | Y
Central Hudson |  | NEXAMP SOLAR LLC | CH-04104 | Poughkeepsie | Hyde Park | Dutchess | 12601 | G | 6068 | Inwood Ave | N |  | 2000 | [13 empty] | CDG | Y | 1 SMA America SC 2500-EV-US (550V) [SI1] 1Schneider ElectricConext SmartGen CS 2000 | 2017-11-03 | 2017-11-03 | 0 | 2017-11-03 | 2017-11-03 | 2017-11-22 | 13 | 2018-02-06 | 2018-02-07 | 2018-05-04 | 60 | 16774.74 | 281367 | 150826.41 | 2018-08-01 | 2019-01-29 | 2019-01-29 | 2020-12-04 | 2020-12-29 | 2020-12-29 | 2021-03-11 | Y | Y
Central Hudson |  | SolarCity | CH-05411 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 6051 | Todd Hill | N |  | 11.8 | [13 empty] | NM | N | 1 DELTA SOLIVIA 6.6 TL 1 DELTA SOLIVIA 5.2TL | 2017-08-03 | 2017-08-11 | 6 | 2017-08-11 | [14 empty] | 2017-09-25 | 2017-10-02 |  | Y
Central Hudson |  | Sumintra | CH-08320 | Catskill | Westerlo | Albany | 12193 | G | 1091 | Westerlo | N |  | 15.36 | [13 empty] | NM | N | SMA SB7.7-1SP-US-40 (2) | 2017-08-11 | 2017-08-11 | 0 | 2017-08-11 | [8 empty] | 350 | 350 |  | 2017-08-30 | 2017-08-30 | 2017-12-29 | 2018-03-26 | 2018-03-28 |  | Y
Central Hudson |  | High Peaks Solar, LLC | CH-00123 | Catskill | Elka Pk | Greene | 12427 | G | 2385 | Lawrenceville | N |  | 5 | [13 empty] | NM | N | SMA SB3800TLUS-22 | 2017-08-14 | 2017-08-14 | 0 | 2017-08-14 | [14 empty] | 2017-11-01 | 2017-11-01 |  | Y
Central Hudson |  | Lighthouse Solar | CH-00331 | Newburgh | Marlboro | Ulster | 12542 | G | 5004 | Marlboro | N | CH-03805 | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A-US | 2017-08-14 | 2017-08-14 | 0 | 2017-08-14 | [8 empty] | 350 | 350 |  |  |  |  | 2017-11-02 | 2017-11-03 |  | Y
Central Hudson |  | SolarCity | CH-07044 | Newburgh | Newburgh | Orange | 12550 | G | 4042 | Union Ave | N |  | 3.6 | [13 empty] | NM | N | ABB PVI 3.6 | 2017-08-04 | 2017-08-04 | 0 | 2017-08-04 | [14 empty] | 2017-10-09 | 2017-10-09 |  | Y
Central Hudson |  | EcoMen Solar | CH-00021 | Newburgh | Wallkill | Ulster | 12589 | G | 5041 | East Walden | N |  | 18.56 | [13 empty] | NM | N | 58 SUNPOWER 345AC | 2017-08-17 | 2017-08-17 | 0 | 2017-08-17 | [14 empty] | 2018-03-28 | 2018-03-28 |  | Y
Central Hudson |  | Lotus Energy Inc. | CH-00344 | Kingston | Kingston | Ulster | 12401 | G | 1013 | Boulevard | N |  | 5.76 | [13 empty] | NM | N | 18 SUNPOWER SPR-X21-345-C-AC 1 | 2017-08-14 | 2017-08-14 | 0 | 2017-08-14 | [14 empty] | 2017-09-05 | 2017-09-05 |  | Y
Central Hudson |  | SolarCity | CH-06216 | Newburgh | Newburgh | Orange | 12550 | G | 4024 | Coldenham | N |  | 6.6 | [13 empty] | NM | N | DELTA SOLIVIA 6.6 TL | 2017-08-18 | 2017-08-18 | 0 | 2017-08-18 | [14 empty] | 2017-10-04 | 2017-10-04 |  | Y
Central Hudson |  | US ENERGY CONCIERGE, INC. | CH-09746 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6096 | Manchester | N |  | 7.6 | [13 empty] | NM | N | SOLAREDGE SE7600H US | 2017-08-07 | 2017-08-07 | 0 | 2017-08-07 | [14 empty] | 2017-10-19 | 2017-10-23 |  | Y
Central Hudson |  | RGS Energy | CH-00002 | Kingston | High Fls | Ulster | 12440 | G | 3024 | High Falls | N | CH-00796 | 5 | [13 empty] | NM | N | SMA SB5.0-1SP-US-40 | 2017-08-14 | 2017-08-14 | 0 | 2017-08-14 | [14 empty] | 2017-12-27 | 2017-12-27 |  | Y
Central Hudson |  | 212 Solar Development, LLC | CH-00614 | Poughkeepsie |  |  | 12603 | G | 6092 | Manchester | TBD |  | 2000 | [13 empty] | CDG | N | SUNGROW SG125HV (16) | 2017-09-07 | 2017-09-21 | 10 | 2017-09-21 | 2017-10-05 | 2017-10-06 | 1 |  |  |  |  | 38000 | [9 empty] | W
Central Hudson |  | 212 Solar Development, LLC | CH-00615 | Poughkeepsie |  |  | 12603 | G | 6092 | Manchester | TBD |  | 2000 | [13 empty] | CDG | N | SUNGROW SG125HV (16) | 2017-09-07 | 2017-09-21 | 10 | 2017-09-21 | 2017-09-21 | 2017-10-06 | 11 |  |  |  |  | 34000 | [9 empty] | W
Central Hudson |  | SolarCity | CH-06499 | Kingston | Accord | Ulster | 12404 | G | 3024 | High Falls | N |  | 3 | [13 empty] | NM | N | ABB PVI 3.0 | 2017-08-08 | 2017-08-08 | 0 | 2017-08-08 | [14 empty] | 2017-10-16 | 2017-10-18 |  | Y
Central Hudson |  | Solar Generation | CH-08205 | Kingston | Accord | Ulster | 12404 | G | 3024 | High Falls | N |  | 23 | [13 empty] | NM | N | 72 SunPower SPR-X22-360-C-AC (240V) | 2017-08-08 | 2017-08-08 | 0 | 2017-08-08 | [8 empty] | 350 | 350 |  | 2017-09-05 | 2017-09-05 | 2018-01-25 | 2018-04-16 | 2018-04-18 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08628 | Newburgh | Modena | Ulster | 12548 | G | 5012 | Modena | N |  | 4.73 | [13 empty] | NM | N | 22 ENPHASE M215 60-2LL-S22 | 2017-08-08 | 2017-08-08 | 0 | 2017-08-08 | [14 empty] | 2017-10-02 | 2017-10-20 |  | Y
Central Hudson |  | New York State Solar Farm | CH-00359 | Newburgh | Highland | Ulster | 12528 | G | 5081 | Highland | N |  | 11.73 | [13 empty] | NM | N | 34 SUNPOWER C-AC 345 | 2017-08-09 | 2017-08-09 | 0 | 2017-08-09 | [14 empty] | 2017-08-31 | 2017-09-05 |  | Y
Central Hudson |  | Kasselman Solar | CH-00250 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8092 | Fishkill Plains | N |  | 6.16 | [13 empty] | NM | N | 22 ENPHASE ENERGY S280 | 2017-08-14 | 2017-08-14 | 0 | 2017-08-14 | [14 empty] | 2017-09-15 | 2017-09-15 |  | Y
Central Hudson |  | SolarCity | CH-05042 | Newburgh | Highland | Ulster | 12528 | G | 5082 | Highland | N |  | 4.2 | [13 empty] | NM | N | ABB PVI-4.2 OUTD-S-US | 2017-08-10 | 2017-08-10 | 0 | 2017-08-10 | [14 empty] | 2018-01-05 | 2018-01-16 |  | Y
Central Hudson |  | SolarCity | CH-05495 | Catskill | Hensonvl | Greene | 12439 | E | 2081 | Hunter | N |  | 4.2 | [13 empty] | NM | N | ABB PVI-4.2 OUTD-S-US | 2017-08-08 | 2017-08-10 | 2 | 2017-08-10 | [14 empty] | 2017-10-20 | 2017-10-25 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08760 | Fishkill |  |  | 12533 | G | 8094 | Fishkill Plains | TBD |  | 11.39 | [13 empty] | NM | N | 53 ENPHASE M215 602LLS22IG | 2017-08-10 | 2017-08-10 | 0 | 2017-08-10 | [17 empty] | W
Central Hudson |  | HUDSON SOLAR | CH-10046 | Newburgh | Newburgh | Orange | 12550 | G | 4023 | Coldenham | N |  | 8.3 | [13 empty] | NM | N | 26 SunPower SPR-E20-327-C-AC (240V) | 2017-09-25 | 2017-10-04 | 7 | 2017-10-04 | [14 empty] | 2017-12-20 | 2017-12-27 |  | Y
Central Hudson |  | Hudson Solar | CH-02061 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6011 | Sand Dock | N | CH-02061 | 14.08 | [13 empty] | NM | N | 44 SUNPOWER E320-327 C-AC | 2017-08-11 | 2017-08-11 | 0 | 2017-08-11 | [14 empty] | 2017-11-22 | 2017-12-08 |  | Y
Central Hudson |  | New York State Solar Farm | CH-00380 | Kingston | Napanoch | Ulster | 12458 | G | 3072 | Honk Falls | N |  | 7.59 | [13 empty] | NM | N | 22 SUNPOWER X21C-AC | 2017-08-14 | 2017-08-14 | 0 | 2017-08-14 | [14 empty] | 2017-10-26 | 2017-10-26 |  | Y
Central Hudson |  | New York State Solar Farm | CH-00433 | Newburgh | New Paltz | Ulster | 12561 | G | 5031 | Galeville | N |  | 12.76 | [13 empty] | NM | N | (37) SUNPOWER X21C-AC | 2017-08-15 | 2017-08-15 | 0 | 2017-08-15 | [14 empty] | 2017-09-27 | 2017-09-27 |  | Y
Central Hudson |  | SolarCity | CH-06768 | Poughkeepsie |  |  | 12571 | G | 7051 | Rhinebeck | TBD |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A | 2017-08-14 | 2017-08-14 | 0 | 2017-08-14 | [17 empty] | W
Central Hudson |  | US ENERGY CONCIERGE, INC. | CH-09738 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7062 | Milan | N |  | 15.2 | [13 empty] | NM | N | 2 PIKA ENERGY X7602 | 2017-08-18 | 2017-08-18 | 0 | 2017-08-18 | [14 empty] | 2017-12-14 | 2017-12-15 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-00044 | Poughkeepsie | Staatsburg | Dutchess | 12580 | G | 7041 | Staatsburg | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE 10000A-US (277V) | 2017-08-15 | 2017-08-15 | 0 | 2017-08-15 | [8 empty] | 350 | 350 |  | 2017-08-24 | 2017-08-24 | 2018-04-10 | 2018-04-03 | 2018-04-05 |  | Y
Central Hudson |  | INFINITY SOLAR SYSTEMS | CH-00133 | Newburgh | Marlboro | Ulster | 12542 | G | 5003 | Marlboro | N |  | 6.08 | [13 empty] | NM | N | 19 SUNPOWERSPR-X21-345C-AC | 2017-08-15 | 2017-08-17 | 2 | 2017-08-17 | [14 empty] | 2017-10-17 | 2017-10-24 |  | Y
Central Hudson |  | Lighthouse Solar | CH-00267 | Kingston | Accord | Ulster | 12404 | G | 3024 | High Falls | N |  | 20 | [13 empty] | NM | N | 2 SOLAREDGE SE10000A-US | 2017-08-15 | 2017-08-15 | 0 | 2017-08-15 | [8 empty] | 350 | 350 |  | 2017-08-24 | 2017-08-24 | 2017-10-05 | 2017-09-15 | 2017-10-13 |  | Y
Central Hudson |  | Lighthouse Solar | CH-00281 | Kingston | Kerhonkson | Ulster | 12446 | G | 3082 | Kerhonkson | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A-US | 2017-08-15 | 2017-08-15 | 0 | 2017-08-15 | [14 empty] | 2017-10-05 | 2017-10-05 |  | Y
Central Hudson |  | 212 Solar Development, LLC | CH-00616 | Catskill |  |  | 12444 | E | 2389 | Vinegar Hill | TBD |  | 2000 | [13 empty] | CDG | N | SUNGROW SG125 HV (16) | 2017-09-07 | 2017-09-21 | 10 | 2017-09-21 | 2017-09-21 | 2017-10-06 | 11 |  |  |  |  | 34000 | [9 empty] | W
Central Hudson |  | 212 Solar Development, LLC | CH-00617 | Catskill |  |  | 12444 | E | 2389 | Vinegar Hill | TBD |  | 2000 | [13 empty] | CDG | N | SUNGROW SG125 HV (16) | 2017-09-07 | 2017-09-21 | 10 | 2017-09-21 | 2017-09-21 | 2017-10-06 | 11 |  |  |  |  | 38000 | [9 empty] | W
Central Hudson |  | Trinity Solar | CH-08502 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8092 | Fishkill Plains | N | CH-08502 | 7.6 | [13 empty] | NM | N | 1 SOLAREDGE SE7600A US | 2017-08-15 | 2017-08-15 | 0 | 2017-08-15 | [14 empty] | 2017-10-31 | 2017-11-01 |  | Y
Central Hudson |  | Hudson Solar | CH-02148 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7054 | Rhinebeck | N |  | 9.6 | [13 empty] | NM | N | 30 SUNPOWER X22-360C-AC | 2017-08-16 | 2017-08-16 | 0 | 2017-08-16 | [14 empty] | 2017-10-24 | 2017-10-24 |  | Y
Central Hudson |  | SolarCity | CH-05328 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 6051 | Todd Hill | N |  | 6.6 | [13 empty] | NM | N | DELTA SOLIVIA 6.6 TL | 2017-08-17 | 2017-08-17 | 0 | 2017-08-17 | [14 empty] | 2017-11-14 | 2017-11-16 |  | Y
Central Hudson |  | SolarCity | CH-05379 | Kingston | Olive Brdg | Ulster | 12461 | G | 3024 | High Falls | N |  | 5 | [13 empty] | NM | N | SOLAREDGE SE5000A-US | 2017-08-17 | 2017-08-17 | 0 | 2017-08-17 | [14 empty] | 2017-09-28 | 2017-10-04 |  | Y
Central Hudson |  | SolarCity | CH-06417 | Newburgh |  |  | 12549 | G | 5072 | Montgomery | TBD |  | 6.6 | [13 empty] | NM | N | DELTA SOLIVIA 6.6 TL | 2017-08-17 | 2017-08-17 | 0 | 2017-08-17 | [17 empty] | W
Central Hudson |  | SolarCity | CH-07244 | Kingston | Kingston | Ulster | 12401 | G | 2013 | Lincoln Park | N |  | 4.2 | [13 empty] | NM | N | ABB PVI-4.2-OUTD-S US | 2017-08-17 | 2017-08-17 | 0 | 2017-08-17 | [14 empty] | 2017-10-17 | 2017-10-19 |  | Y
Central Hudson |  | Solar Generation | CH-08301 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7056 | Rhinebeck | N |  | 9 | [13 empty] | NM | N | 1 SOLAREDGE 6000-H 1 SOLAREDGE 3000-H | 2017-08-17 | 2017-08-17 | 0 | 2017-08-17 | [14 empty] | 2017-10-23 | 2017-10-26 |  | Y
Central Hudson |  | Sologistics | CH-08313 | Fishkill | Beacon | Dutchess | 12508 | G | 8018 | Forgebrook | N |  | 5.12 | [13 empty] | NM | N | 16 SUNPOWER X21-345-C-AC | 2017-08-17 | 2017-08-17 | 0 | 2017-08-17 | [14 empty] | 2018-01-02 | 2018-01-08 |  | Y
Central Hudson |  | Trinity Solar | CH-08591 | Fishkill | Wappingers Falls | Dutchess | 12590 | G | 8091 | Fishkill Plains | N | CH-06007 | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE 7600A-US (208V) SOLAREDGE SE7600A-US | 2017-09-15 | 2017-09-29 | 10 | 2017-09-29 | [8 empty] | 350 | 350 |  |  |  |  | 2017-11-29 | 2017-11-30 |  | Y
Central Hudson |  | Kasselman Solar | CH-00248 | Poughkeepsie | Millbrook |  | 12545 | G | 7012 | Hibernia | TBD |  | 4.25 | [13 empty] | NM | N | 17 ENPHASE ENERGY S250 | 2017-08-18 | 2017-08-18 | 0 | 2017-08-18 | [17 empty] | W
Central Hudson |  | Kasselman Solar | CH-00251 | Fishkill |  |  | 12508 | G | 8087 | Tioronda | TBD |  | 7 | [13 empty] | NM | N | 25 ENPHASE ENERGY S280 | 2017-08-18 | 2017-08-18 | 0 | 2017-08-18 | [17 empty] | W
Central Hudson |  | Kasselman Solar | CH-00253 | Kingston | Stone Ridge | Ulster | 12484 | G | 3024 | High Falls | N |  | 6.16 | [13 empty] | NM | N | 22 ENPHASE ENERGY S280 | 2017-08-18 | 2017-08-18 | 0 | 2017-08-18 | [14 empty] | 2017-09-20 | 2017-09-26 |  | Y
Central Hudson |  | SOLARCITY | CH-05184 | Newburgh | New Windsor | Orange | 12553 | G | 4046 | Union Ave | Y |  | 5 | 5 | [12 empty] | NM | N | 1 SolarEdge Technologies SE5000 (208V) SOLAREDGE SE5000A-US1TeslaAC Powerwall 2.0 | 2017-08-18 | 2017-08-18 | 0 | 2017-08-18 | [14 empty] | 2018-01-30 | 2018-01-30 |  | Y
Central Hudson |  | Tesla | CH-07253 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6045 | Spackenkill | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000x (240V) [SI1] SOLAREDGE SE 5000A-US | 2017-08-18 | 2017-08-18 | 0 | 2017-08-18 | [14 empty] | 2019-01-08 | 2019-01-09 |  | Y
Central Hudson |  | SolarCity | CH-07762 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 6092 | Manchester | N |  | 9 | [13 empty] | NM | N | DELTA SOLIVIA 5.2 DELTA SOLIVIA 3.8 | 2017-08-22 | 2017-08-22 | 0 | 2017-08-22 | [14 empty] | 2017-10-19 | 2017-10-30 |  | Y
Central Hudson |  | SolarCity | CH-05186 | Newburgh | Salisbury Mls | Orange | 12577 | G | 4095 | Bethlehem Rd | N |  | 12 | [13 empty] | NM | N | 2 SOLAREDGE SE6000A-US | 2017-08-23 | 2017-08-23 | 0 | 2017-08-23 | [14 empty] | 2017-10-16 | 2017-10-24 |  | Y
Central Hudson |  | Green Street Power Partners, LLC | CH-00116 | Fishkill | Hopewell Jct |  | 12533 | G | 8095 | Fishkill Plains | N |  | 11.52 | [13 empty] | NM | N | 36 SUNPOWERSPR-E20-327-C-AC | 2017-08-29 | 2017-08-29 | 0 | 2017-08-29 | [17 empty] | W
Central Hudson |  | INFINITY SOLAR SYSTEMS | CH-00192 | Newburgh | Newburgh | Orange | 12550 | G | 5004 | Marlboro | N |  | 5.44 | [13 empty] | NM | N | 17 SUNPOWER SPR-X21-345 C-AC | 2017-08-28 | 2017-08-28 | 0 | 2017-08-28 | [14 empty] | 2017-10-10 | 2017-11-02 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-00046 | Poughkeepsie | Clinton Corners | Dutchess | 12514 | G | 7071 | Stanfordville | N |  | 7.6 | [13 empty] | NM | N | 1 SOLAREDGE 7600 A-US | 2017-08-29 | 2017-08-29 | 0 | 2017-08-29 | [14 empty] | 2017-10-11 | 2017-10-11 |  | Y
Central Hudson |  | Lighthouse Solar | CH-00317 | Newburgh | New Paltz | Ulster | 12561 | G | 5023 | Ohioville | N |  | 6 | [13 empty] | NM | N | 1 SOLAREDGE 6000 A-US | 2017-08-30 | 2017-08-30 | 0 | 2017-08-30 | [14 empty] | 2017-10-09 | 2017-10-09 |  | Y
Central Hudson |  | Trinity Solar | CH-08430 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8091 | Fishkill Plains | N |  | 7.6 | [13 empty] | NM | N | 1 SOLAREDGE SE7600A-US | 2017-08-29 | 2017-08-29 | 0 | 2017-08-29 | [14 empty] | 2018-01-09 | 2018-01-10 |  | Y
Central Hudson |  | Trinity Solar | CH-08443 | Fishkill | Beacon | Dutchess | 12508 | G | 8017 | Forgebrook | N |  | 3 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3000 (240V) | 2017-09-06 | 2017-09-06 | 0 | 2017-09-06 | [14 empty] | 2018-04-10 | 2018-04-12 |  | Y
Central Hudson |  | Trinity Solar | CH-08456 | Newburgh | Marlboro | Ulster | 12542 | G | 5001 | Marlboro | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US | 2017-09-06 | 2017-09-06 | 0 | 2017-09-06 | [14 empty] | 2018-01-22 | 2018-01-24 |  | Y
Central Hudson |  | Trinity Solar | CH-08538 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8045 | Myers Corners | N |  | 10 | [13 empty] | NM | N | 1 SOLAREDGE SE1000A-US | 2017-08-29 | 2017-08-29 | 0 | 2017-08-29 | [14 empty] | 2017-12-20 | 2017-12-26 |  | Y
Central Hudson |  | Trinity Solar | CH-08554 | Newburgh | Montgomery | Orange | 12549 | G | 5073 | Montgomery | N |  | 3.8 | [13 empty] | NM | N | 1 SOLAREDGE SE3800H-US | 2017-09-06 | 2017-09-06 | 0 | 2017-09-06 | [14 empty] | 2018-01-23 | 2018-01-24 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-00065 | Newburgh | Rock Tvrn | Orange | 12575 | G | 4097 | Bethlehem Rd | N |  | 13.6 | [13 empty] | NM | N | 1 SOLAREDGE 6000 A-US 1 SOLAREDGE 7600 A-US | 2017-08-30 | 2017-08-30 | 0 | 2017-08-30 | [8 empty] | 350 | 350 |  | 2017-09-11 | 2017-09-11 | 2017-10-05 | 2017-10-19 | 2017-10-24 |  | Y
Central Hudson |  | New York State Solar Farm | CH-00371 | Newburgh | Gardiner | Ulster | 12525 | G | 5011 | Modena | N |  | 7.68 | [13 empty] | NM | N | 24 SUNPOWER C-AC | 2017-08-30 | 2017-08-30 | 0 | 2017-08-30 | [14 empty] | 2017-10-03 | 2017-10-06 |  | Y
Central Hudson |  | New York State Solar Farm | CH-00393 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6092 | Manchester | N |  | 5.44 | [13 empty] | NM | N | 17 SUNPOWER C-AC 360 | 2017-08-30 | 2017-08-30 | 0 | 2017-08-30 | [14 empty] | 2017-09-28 | 2017-10-03 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08617 | Newburgh | New Windsor | Orange | 12553 | G | 4095 | Bethlehem Rd | N |  | 5.52 | [13 empty] | NM | N | 24 ENPHASE IQ6 602US | 2017-08-30 | 2017-08-30 | 0 | 2017-08-30 | [14 empty] | 2017-12-15 | 2018-01-10 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08777 | Newburgh | New Windsor | Orange | 12553 | G | 4095 | Bethlehem Rd | N |  | 4.6 | [13 empty] | NM | N | 20 ENPHASE IQ6 602US | 2017-09-01 | 2017-09-01 | 0 | 2017-09-01 | [14 empty] | 2018-01-18 | 2018-01-18 |  | Y
Central Hudson |  | New York State Solar Farm | CH-00364 | Poughkeepsie | Clinton Corners | Dutchess | 12514 | G | 7071 | Stanfordville | N |  | 11.52 | [13 empty] | NM | N | 36 SUNPOWER C-AC | 2017-08-31 | 2017-08-31 | 0 | 2017-08-31 | [14 empty] | 2017-09-27 | 2017-10-03 |  | Y
Central Hudson |  | Hudson Solar | CH-02124 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7061 | Milan | N |  | 8 | [13 empty] | NM | N | SUNPOWER E320-327 C-AC (25) | 2017-08-31 | 2017-08-31 | 0 | 2017-08-31 | [14 empty] | 2017-10-31 | 2017-11-06 |  | Y
Central Hudson |  | SolarCity | CH-05608 | Catskill | Purling |  | 12470 | G | 2041 | South Cairo | TBD |  | 3.8 | [13 empty] | NM | N | 1 DELTA SOLIVIA 3.8TL | 2017-09-06 | 2017-09-06 | 0 | 2017-09-06 | [17 empty] | W
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08776 | Newburgh | New Windsor | Orange | 12553 | G | 4094 | Bethlehem Rd | N |  | 5.06 | [13 empty] | NM | N | 22 ENPHASE IQ6 602US | 2017-09-01 | 2017-09-01 | 0 | 2017-09-01 | [14 empty] | 2017-12-12 | 2017-12-15 |  | Y
Central Hudson |  | Solar Generation | CH-08167 | Kingston | Woodstock | Ulster | 12498 | G | 3013 | Woodstock | N |  | 6 | [13 empty] | NM | N | 1 SMA AMERICA SB6000 TL | 2017-09-05 | 2017-09-05 | 0 | 2017-09-05 | [14 empty] | 2018-04-02 | 2018-04-03 |  | Y
Central Hudson |  | SolarCity | CH-06318 | Newburgh | Newburgh | Orange | 12550 | G | 5001 | Marlboro | Y |  | 7.6 | 5 | [12 empty] | NM | N | 1 Delta Electronics SOLIVIA 7.6 NA G4 TL (240V) 1TeslaAC Powerwall 2.0 | 2018-01-10 | 2018-01-10 | 0 | 2018-01-10 | [14 empty] | 2018-01-18 | 2018-01-18 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08619 | Newburgh | Cornwall-Hdsn | Orange | 12520 | G | 4043 | Union Ave | N |  | 5.5 | [13 empty] | NM | N | 24 Enphase Energy IQ6-60-X-US (240V) | 2017-09-07 | 2017-09-07 | 0 | 2017-09-07 | [14 empty] | 2018-08-14 | 2018-08-15 |  | Y
Central Hudson |  | PlugPV, LLC. | CH-04898 | Kingston | Shokan | Ulster | 12481 | G | 3011 | Woodstock | N |  | 7.6 | [13 empty] | NM | N | 1 SOLAREDGE 7600A US | 2017-09-08 | 2017-09-08 | 0 | 2017-09-08 | [14 empty] | 2017-12-27 | 2018-01-02 |  | Y
Central Hudson |  | Hudson Solar | CH-02153 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7062 | Milan | N | CH-02153 | 10.88 | [13 empty] | NM | N | 34 SUNPOWER E320-327 C-AC | 2017-09-08 | 2017-09-08 | 0 | 2017-09-08 | [14 empty] | 2017-10-31 | 2017-11-27 |  | Y
Central Hudson |  | Lam Development | CH-02587 | Kingston |  |  | 12428 | G | 3095 | Grimley Rd | TBD |  | 2000 | [13 empty] | NM | N | SMA TRIPOWER 30000 TL-US-10 (66) SMA TRIPOWER 20000 TL-US-10 (1) | 2017-09-08 | 2017-09-22 | 10 | 2017-09-22 | 2017-09-22 | 2017-10-12 | 14 |  |  |  |  | 37000 | [9 empty] | W
Central Hudson |  | Lam Development | CH-02588 | Kingston |  |  | 12428 | G | 3076 | Greenfield Rd | TBD |  | 2000 | [13 empty] | NM | N | SMA TRIPOWER 30000 TL-US-10 (66) SMA TRIPOWER 20000 TL-US-10 (1) | 2017-09-08 | 2017-09-22 | 10 | 2017-09-22 | 2017-09-22 | 2017-10-12 | 14 |  |  |  |  | 37000 | [9 empty] | W
Central Hudson |  | Lam Development | CH-02589 | Catskill |  |  | 12428 | G | 1071 | Coxsackie | TBD |  | 2000 | [13 empty] | NM | N | SMA TRIPOWER 30000 TL-US-10 (66) SMA TRIPOWER 20000 TL-US-10 (1) | 2017-09-08 | 2017-09-22 | 10 | 2017-09-22 | 2017-09-22 | 2017-10-12 | 14 |  |  |  |  | 39000 | [9 empty] | W
Central Hudson |  | Lam Development | CH-02590 | Catskill |  |  | 12428 | G | 1081 | New Baltimore | TBD |  | 2000 | [13 empty] | NM | N | SMA TRIPOWER 30000 TL-US-10 (66) SMA TRIPOWER 20000 TL-US-10 (1) | 2017-09-08 | 2017-09-22 | 10 | 2017-09-22 | 2017-09-22 | 2017-10-12 | 14 |  |  |  |  | 37000 | [9 empty] | W
Central Hudson |  | Kasselman Solar | CH-03532 | Kingston | Hurley | Ulster | 12443 | G | 2094 | Hurley Ave | N |  | 5.6 | [13 empty] | NM | N | 20 ENPHASE ENERGY IQ6+ US | 2017-09-11 | 2017-09-11 | 0 | 2017-09-11 | [14 empty] | 2017-10-02 | 2017-10-02 |  | Y
Central Hudson |  | Kasselman Solar | CH-03533 | Fishkill | Beacon | Dutchess | 12508 | G | 8015 | Forgebrook | N | CH-03533 | 6.21 | [13 empty] | NM | N | 27 ENPHASE ENERGY IQ6-60-2 US | 2017-09-11 | 2017-09-11 | 0 | 2017-09-11 | [14 empty] | 2017-10-18 | 2017-10-20 |  | Y
Central Hudson |  | Solar Generation | CH-08113 | Kingston | Accord | Ulster | 12404 | G | 3081 | Kerhonkson | N |  | 22.8 | [13 empty] | NM | N | 3 SOLAREDGE 7600A US | 2017-09-11 | 2017-09-11 | 0 | 2017-09-11 | [8 empty] | 350 | 350 |  |  |  |  | 2017-10-06 | 2017-10-20 |  | Y
Central Hudson |  | Solar Generation | CH-08131 | Kingston | Shokan | Ulster | 12481 | G | 3011 | Woodstock | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE 7600A-US (208V) 1 SolarEdge 7600 | 2017-09-14 | 2017-09-28 | 10 | 2017-09-28 | [14 empty] | 2017-12-20 | 2017-12-27 |  | Y
Central Hudson |  | Trinity Solar | CH-08373 | Fishkill | Fishkill | Dutchess | 12524 | G | 8013 | Forgebrook | N | CH-08373 | 3 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3000H-US (240V) 1 SOLAREDGE 3800H US | 2017-09-14 | 2017-09-28 | 10 | 2017-09-28 | [14 empty] | 2018-01-19 | 2018-01-24 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-00030 | Newburgh | Washingtonvl | Orange | 10992 | G | 4097 | Bethlehem Rd | N |  | 12 | [13 empty] | NM | N | 2 SOLAREDGE 6000A-US | 2017-09-12 | 2017-09-12 | 0 | 2017-09-12 | [14 empty] | 2017-10-11 | 2017-10-13 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-00071 | Kingston | Grahamsvl | Sullivan | 12740 | G | 3091 | Neversink | N |  | 6 | [13 empty] | NM | N | 1 SOLAREDGE 6000A-US | 2017-09-12 | 2017-09-12 | 0 | 2017-09-12 | [14 empty] | 2017-10-19 | 2017-10-23 |  | Y
Central Hudson |  | Lighthouse Solar | CH-00265 | Kingston | Accord | Ulster | 12404 | G | 3083 | Kerhonkson | N |  | 10 | [13 empty] | NM | N | 1 SOLAREDGE SE10000 A-US | 2017-09-12 | 2017-09-12 | 0 | 2017-09-12 | [14 empty] | 2017-10-25 | 2017-11-02 |  | Y
Central Hudson |  | Lighthouse Solar | CH-00322 | Newburgh | New Paltz | Ulster | 12561 | G | 5023 | Ohioville | N |  | 6 | [13 empty] | NM | N | 1 SOLAREDGE SE6000 A-US | 2017-09-12 | 2017-09-12 | 0 | 2017-09-12 | [14 empty] | 2017-11-08 | 2017-11-09 |  | Y
Central Hudson |  | Trinity Solar | CH-08465 | Catskill | Coeymans | Albany | 12045 | G | 1082 | New Baltimore | N | CH-08465 | 10 | [13 empty] | NM | N | 1 SOLAREDGE SE1000A US | 2017-09-12 | 2017-09-12 | 0 | 2017-09-12 | [14 empty] | 2018-01-02 | 2018-01-08 |  | Y
Central Hudson |  | Lighthouse Solar | CH-00316 | Newburgh | Highland | Ulster | 12528 | G | 5022 | Ohioville | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE 10000A-US (277V) 1 SOLAREDGE SE10000 A-US | 2017-09-13 | 2017-09-27 | 10 | 2017-09-27 | [8 empty] | 350 | 350 |  | 2017-10-17 | 2017-10-17 | 2017-10-26 | 2017-11-20 | 2017-11-21 |  | Y
Central Hudson |  | New York State Solar Farm | CH-00471 | Newburgh | Newburgh | Orange | 12550 | G | 4053 | Union Ave | N |  | 4.8 | [13 empty] | NM | N | 16 SUNPOWER X21 AC | 2017-09-13 | 2017-09-13 | 0 | 2017-09-13 | [14 empty] | 2017-11-14 | 2017-11-16 |  | Y
Central Hudson |  | Solar Generation | CH-08105 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7052 | Rhinebeck | N |  | 18 | [13 empty] | NM | N | 3 SMA America SB6000US-11 (208V) | 2017-09-13 | 2017-09-13 | 0 | 2017-09-13 | [14 empty] | 2018-08-27 | 2018-09-06 |  | Y
Central Hudson |  | Lighthouse Solar | CH-00287 | Kingston | High Fls | Ulster | 12440 | G | 3024 | High Falls | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE 7600A-US (208V) | 2017-09-14 | 2017-09-28 | 10 | 2017-09-28 | [14 empty] | 2017-10-17 | 2017-10-20 |  | Y
Central Hudson |  | Hudson Solar | CH-01256 | Newburgh | New Windsor | Orange | 12553 | G | 4095 | Bethlehem Rd | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE11400A-US (240V) [SI1] 1 SOLAREDGE SE11400A-US-U | 2017-09-14 | 2017-09-28 | 10 | 2017-09-28 | [14 empty] | 2017-11-21 | 2017-12-01 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-08632 | Newburgh | Rock Tvrn | Orange | 12575 | G | 4097 | Bethlehem Rd | N |  | 9.2 | [13 empty] | NM | N | 40 Enphase Energy IQ6-60-x-US (240V) [SI1] 40 ENPHASE IQ6 602US | 2017-09-14 | 2017-09-28 | 10 | 2017-09-28 | [14 empty] | 2017-10-27 | 2018-04-13 |  | Y |  | 10/26/17 - CH rep unable to install net meter due to unsafe conditions. Customer to make repairs, then call for net meter install. Customer repairs complete 4/11 Meter installed 4/13
Central Hudson |  | New York State Solar Farm | CH-00367 | Fishkill | Cold Spg | Putnam | 10516 | G | 8063 | Merritt Park | N |  | 12.48 | [13 empty] | NM | N | 16 SUNPOWER X21 AC | 2017-09-15 | 2017-09-15 | 0 | 2017-09-15 | [14 empty] | 2017-11-02 | 2017-11-07 |  | Y
Central Hudson |  | SolarCity | CH-06808 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8043 | Myers Corners | N |  | 9 | [13 empty] | NM | N | 1 Delta Electronics SOLIVIA 5.2 NA G4 TL (208V) 1 Delta Electronics SOLIVIA 3.8 NA G4 TL (240V) | 2017-09-15 | 2017-09-29 | 10 | 2017-09-29 | [14 empty] | 2017-11-03 | 2017-11-07 |  | Y
Central Hudson |  | SolarCity | CH-07301 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6056 | Todd Hill | N |  | 7.6 | [13 empty] | NM | N | 1 Delta Electronics SOLIVIA 7.6 NA G4 TL (240V) 1 DELTA SOLIVIA 7.6 TL | 2017-09-15 | 2017-09-29 | 10 | 2017-09-29 | [14 empty] | 2017-10-05 | 2017-10-09 |  | Y
Central Hudson |  | HUDSON SOLAR | CH-10009 | Kingston | Ulster Pk | Ulster | 12487 | G | 1012 | Boulevard | N |  | 7.7 | [13 empty] | NM | N | 12 SunPower SPR-X21-335-C-AC (240V) 12 SunPower SPR-X22-360-C-AC (240V) | 2017-09-15 | 2017-09-28 | 9 | 2017-09-28 | [14 empty] | 2017-11-09 | 2017-11-13 |  | Y
Central Hudson |  | HUDSON SOLAR | CH-10010 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6063 | Inwood Ave | N |  | 6.1 | [13 empty] | NM | N | 19 SunPower SPR-E20-327-C-AC (240V) | 2017-09-15 | 2017-09-28 | 9 | 2017-09-28 | [14 empty] | 2018-06-27 | 2018-06-27 |  | Y
Central Hudson |  | Lighthouse Solar | CH-10011 | Fishkill | Cold Spg | Putnam | 10516 | G | 8087 | Tioronda | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000 (240V) | 2017-09-15 | 2017-09-28 | 9 | 2017-09-28 | [14 empty] | 2017-12-26 | 2017-12-26 |  | Y
Central Hudson |  | HUDSON SOLAR | CH-10012 | Kingston | Stone Ridge | Ulster | 12484 | G | 3023 | High Falls | N |  | 8.3 | [13 empty] | NM | N | 26 SunPower SPR-E20-327-C-AC (208V) | 2017-09-15 | 2017-09-28 | 9 | 2017-09-28 | [14 empty] | 2017-11-21 | 2017-11-22 |  | Y
Central Hudson |  | HUDSON SOLAR | CH-10013 | Kingston | Kingston | Ulster | 12401 | G | 2094 | Hurley Ave | N |  | 4.5 | [13 empty] | NM | N | 14 SunPower SPR-E20-327-C-AC (208V) | 2017-09-15 | 2017-09-28 | 9 | 2017-09-28 | [14 empty] | 2017-11-01 | 2017-11-02 |  | Y
Central Hudson |  | Solar Generation | CH-10017 | Kingston | Kerhonkson | Ulster | 12446 | G | 3082 | Kerhonkson | Y | CH-10017 | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600A-US (240V) | 2017-09-18 | 2017-10-02 | 10 | 2017-10-02 | [14 empty] | 2018-01-16 | 2018-01-23 |  | Y
Central Hudson |  | Solar Generation | CH-08097 | Kingston | Saugerties | Ulster | 12477 | G | 3004 | Saugerties | N |  | 7.7 | [13 empty] | NM | N | 24 SunPower SPR-X22-360-C-AC (240V) 24 SUNPOWER X22-360 C-AC | 2017-09-19 | 2017-10-02 | 9 | 2017-10-02 | [14 empty] | 2018-02-20 | 2018-02-22 |  | Y
Central Hudson |  | New York State Solar Farm | CH-10027 | Newburgh | New Windsor | Orange | 12553 | G | 4046 | Union Ave | N |  | 8.3 | [13 empty] | NM | N | 26 SunPower SPR-X21-345-C-AC (240V) | 2017-09-20 | 2017-10-03 | 9 | 2017-10-03 | [14 empty] | 2017-10-17 | 2017-10-19 |  | Y
Central Hudson |  | Lotus Energy Inc. | CH-10029 | Kingston | Kingston | Ulster | 12401 | G | 1024 | East Kingston | N |  | 3.8 | [13 empty] | NM | N | 12 SunPower SPR-X22-360-C-AC (208V) | 2017-09-21 | 2017-10-03 | 8 | 2017-10-03 | [14 empty] | 2017-10-11 | 2017-10-12 |  | Y
Central Hudson |  | HUDSON SOLAR | CH-10031 | Kingston | High Fls | Ulster | 12440 | G | 3022 | High Falls | N |  | 7.4 | [13 empty] | NM | N | 23 SunPower SPR-E20-327-C-AC (240V) | 2017-09-21 | 2017-10-03 | 8 | 2017-10-03 | [14 empty] | 2017-12-12 | 2017-12-14 |  | Y
Central Hudson |  | HUDSON SOLAR | CH-10032 | Kingston | High Fls | Ulster | 12440 | G | 3024 | High Falls | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE 7600A-US (208V) | 2017-09-21 | 2017-10-03 | 8 | 2017-10-03 | [14 empty] | 2017-11-29 | 2017-11-30 |  | Y
Central Hudson |  | Hudson Solar | CH-10033 | Kingston | Accord |  | 12404 | G | 3024 | High Falls | TBD |  | 5.8 | [13 empty] | NM | N | 18 SunPower SPR-E20-327-C-AC (240V) | 2017-09-21 | 2017-10-03 | 8 | 2017-10-03 | [17 empty] | W
Central Hudson |  | Kasselman Solar | CH-10034 | Kingston | Cottekill | Ulster | 12419 | G | 3021 | High Falls | N |  | 7 | [13 empty] | NM | N | 25 Enphase Energy IQ6PLUS-72-x-US (240V) [SI1] | 2017-09-21 | 2017-10-03 | 8 | 2017-10-03 | [14 empty] | 2017-11-10 | 2017-11-16 |  | Y
Central Hudson |  | Solar Generation | CH-10035 | Kingston | Woodstock | Ulster | 12498 | G | 3014 | Woodstock | N |  | 12.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600A-US (240V) 1 SolarEdge Technologies SE5000 (240V) | 2017-09-21 | 2017-10-03 | 8 | 2017-10-03 | [8 empty] | 350 | 350 |  | 2017-10-09 | 2017-10-09 | 2017-12-21 | 2018-02-02 | 2018-02-07 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-10016 | Fishkill | Fishkill | Dutchess | 12524 | G | 8014 | Forgebrook | N |  | 8 | [13 empty] | NM | N | 25 SunPower SPR-X21-345-C-AC (240V) | 2017-09-22 | 2017-09-29 | 5 | 2017-09-29 | [14 empty] | 2017-09-22 | 2017-09-29 |  | Y
Central Hudson |  | HUDSON SOLAR | CH-10038 | Catskill | Catskill | Greene | 12414 | G | 2002 | North Catskill | N | CH-01263 | 7.7 | [13 empty] | NM | N | 24 SunPower SPR-E20-327-C-AC (240V) | 2017-09-22 | 2017-10-04 | 8 | 2017-10-04 | [14 empty] | 2018-01-31 | 2018-02-01 |  | Y
Central Hudson |  | HUDSON SOLAR | CH-10041 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7053 | Rhinebeck | N |  | 9.6 | [13 empty] | NM | N | 30 SunPower SPR-E20-327-C-AC (240V) | 2017-09-22 | 2017-10-04 | 8 | 2017-10-04 | [14 empty] | 2017-12-20 | 2017-12-20 |  | Y
Central Hudson |  | HUDSON SOLAR | CH-10042 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8051 | North Chelsea | N |  | 9.6 | [13 empty] | NM | N | 30 SunPower SPR-E20-327-C-AC (240V) | 2017-09-22 | 2017-10-04 | 8 | 2017-10-04 | [14 empty] | 2017-11-29 | 2017-11-29 |  | Y
Central Hudson |  | HUDSON SOLAR | CH-10043 | Kingston | Kerhonkson | Ulster | 12446 | G | 3081 | Kerhonkson | N |  | 6.7 | [13 empty] | NM | N | 21 SunPower SPR-E20-327-C-AC (240V) | 2017-09-22 | 2017-10-04 | 8 | 2017-10-04 | [14 empty] | 2017-12-13 | 2017-12-14 |  | Y
Central Hudson |  | Kasselman Solar | CH-10045 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7054 | Rhinebeck | N |  | 3.6 | [13 empty] | NM | N | 13 Enphase Energy IQ6PLUS-72-x-US (240V) [SI1] | 2017-09-22 | 2017-10-04 | 8 | 2017-10-04 | [14 empty] | 2017-11-08 | 2017-11-13 |  | Y
Central Hudson |  | New York State Solar Farm | CH-10051 | Kingston | Claryvl | Sullivan | 12725 | G | 3091 | Neversink | N |  | 5.8 | [13 empty] | NM | N | 18 SunPower SPR-X21-345-C-AC (240V) | 2017-09-25 | 2017-10-05 | 8 | 2017-10-05 | [8 empty] | 350 | 350 |  | 2017-10-12 | 2017-10-12 | 2017-11-15 | 2017-11-15 | 2017-11-16 |  | Y
Central Hudson |  | New York State Solar Farm | CH-10052 | Newburgh | Marlboro | Ulster | 12542 | G | 5001 | Marlboro | N |  | 6.4 | [13 empty] | NM | N | 20 SunPower SPR-X21-345-C-AC (240V) | 2017-09-25 | 2017-10-05 | 8 | 2017-10-05 | [14 empty] | 2017-11-22 | 2017-11-27 |  | Y
Central Hudson |  | Lighthouse Solar | CH-10053 | Fishkill | Cold Spg | Putnam | 10516 | G | 8086 | Tioronda | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000 (240V) | 2017-09-28 | 2017-10-05 | 5 | 2017-10-05 | [14 empty] | 2017-11-13 | 2017-11-14 |  | Y
Central Hudson |  | New York State Solar Farm | CH-00356 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6008 | Reynolds Hill | N |  | 6.1 | [13 empty] | NM | N | 19 SunPower SPR-X21-345-C-AC (240V) | 2017-09-19 | 2017-10-02 | 9 | 2017-10-02 | [14 empty] | 2018-02-14 | 2018-02-22 |  | Y
Central Hudson |  | New York State Solar Farm | CH-00464 | Kingston | Kerhonkson | Ulster | 12446 | G | 3083 | Kerhonkson | N |  | 5.4 | [13 empty] | NM | N | 17 SunPower SPR-X22-360-C-AC (240V) 16 SUNPOWER X21 AC | 2017-09-19 | 2017-10-02 | 9 | 2017-10-02 | [14 empty] | 2017-10-26 | 2017-10-30 |  | Y
Central Hudson |  | Lighthouse Solar | CH-10022 | Newburgh | Newburgh |  | 12550 | G | 5001 | Marlboro | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000 (240V) | 2017-10-02 | 2017-10-09 | 5 | 2017-10-09 | [17 empty] | W
Central Hudson |  | Lighthouse Solar | CH-10023 | Kingston | Kingston | Ulster | 12401 | G | 2093 | Hurley Ave | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US | 2017-10-02 | 2017-10-09 | 5 | 2017-10-09 | [14 empty] | 2017-11-27 | 2017-11-27 |  | Y
Central Hudson |  | Lotus Energy Inc. | CH-10019 | Newburgh | Newburgh | Orange | 12550 | G | 4012 | West Balmville | N |  | 13.1 | [13 empty] | NM | N | 41 SunPower SPR-X22-360-D-AC (240V) [SI1] | 2017-10-02 | 2017-10-09 | 5 | 2017-10-09 | [14 empty] | 2017-10-23 | 2017-10-26 |  | Y
Central Hudson |  | New York State Solar Farm | CH-10026 | Kingston | Stone Ridge | Ulster | 12484 | G | 3024 | High Falls | N |  | 3.2 | [13 empty] | NM | N | 10 SunPower SPR-X21-345-C-AC (240V) | 2017-10-02 | 2017-10-09 | 5 | 2017-10-09 | [14 empty] | 2017-11-30 | 2017-12-01 |  | Y
Central Hudson |  | Lighthouse Solar | CH-00277 | Kingston | Kingston | Ulster | 12401 | G | 3023 | High Falls | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE 11400A-US (240V) | 2017-09-20 | 2017-10-03 | 9 | 2017-10-03 | [14 empty] | 2017-10-25 | 2017-10-27 |  | Y
Central Hudson |  | HUDSON SOLAR | CH-01472 | Kingston | Stone Ridge |  | 12484 | G | 3023 | High Falls | TBD |  | 5.8 | [13 empty] | NM | N | 18 SunPower SPR-E20-327-C-AC (240V) | 2017-09-19 | 2017-10-03 | 10 | 2017-10-03 | [17 empty] | W
Central Hudson |  | Hudson Solar | CH-02040 | Kingston | Kingston | Ulster | 12401 | G | 1011 | Boulevard | N |  | 4.2 | [13 empty] | NM | N | 13 SunPower SPR-E20-327-C-AC (240V) | 2017-09-19 | 2017-10-03 | 10 | 2017-10-03 | [14 empty] | 2017-12-20 | 2017-12-26 |  | Y
Central Hudson |  | Hudson Solar | CH-02338 | Kingston | Saugerties | Ulster | 12477 | G | 3001 | Saugerties | N |  | 3.5 | [13 empty] | NM | N | 11 SunPower SPR-E20-327-C-AC (240V) | 2017-09-19 | 2017-10-03 | 10 | 2017-10-03 | [14 empty] | 2017-11-02 | 2017-11-07 |  | Y
Central Hudson |  | Hudson Solar | CH-02466 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7062 | Milan | N | CH-01534 | 3.5 | [13 empty] | NM | N | 11 SunPower SPR-X21-335-BLK-C-AC (240V) | 2017-09-19 | 2017-10-03 | 10 | 2017-10-03 | [14 empty] | 2017-12-04 | 2017-12-04 |  | Y
Central Hudson |  | SolarCity | CH-05622 | Kingston | High Fls | Ulster | 12440 | G | 3022 | High Falls | N |  | 10.4 | [13 empty] | NM | N | 2 Delta Electronics SOLIVIA 5.2 NA G4 TL (240V) | 2017-09-19 | 2017-10-03 | 10 | 2017-10-03 | [14 empty] | 2017-12-04 | 2017-12-05 |  | Y
Central Hudson |  | SolarCity | CH-07117 | Newburgh | New Windsor | Orange | 12553 | G | 4095 | Bethlehem Rd | N |  | 5.2 | [13 empty] | NM | N | 1 Delta Electronics SOLIVIA 5.2 NA G4 TL (240V) | 2017-09-25 | 2017-10-03 | 6 | 2017-10-03 | [14 empty] | 2017-10-05 | 2017-10-06 |  | Y
Central Hudson |  | Green Street Power Partners, LLC | CH-10028 | Kingston | Saugerties |  | 12477 | G | 3003 | Saugerties | TBD |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000 (240V) | 2017-10-03 | 2017-10-09 | 4 | 2017-10-09 | [8 empty] | 350 | 350 | [7 empty] | W
Central Hudson |  | HUDSON SOLAR | CH-10030 | Poughkeepsie | Ancramdale | Columbia | 12503 | G | 7092 | Pulvers Corners | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000H-US (208V) | 2017-09-21 | 2017-10-03 | 8 | 2017-10-03 | [14 empty] | 2017-12-19 | 2017-12-26 |  | Y
Central Hudson |  | New York State Solar Farm | CH-00379 | Kingston | Kingston | Ulster | 12401 | G | 1022 | East Kingston | N | CH-00379 | 3.8 | [13 empty] | NM | N | 12 SunPower SPR-E20-327-C-AC (240V) | 2017-09-22 | 2017-10-04 | 8 | 2017-10-04 | [14 empty] | 2017-11-06 | 2017-11-08 |  | Y
Central Hudson |  | New York State Solar Farm | CH-00446 | Newburgh | Montgomery | Orange | 12549 | G | 5073 | Montgomery | N |  | 8.3 | [13 empty] | NM | N | 26 SunPower SPR-X22-360-C-AC (240V) | 2017-09-22 | 2017-10-04 | 8 | 2017-10-04 | [14 empty] | 2017-10-20 | 2017-10-25 |  | Y
Central Hudson |  | New York State Solar Farm | CH-00468 | Newburgh | Milton | Ulster | 12547 | G | 5003 | Marlboro | N |  | 8.6 | [13 empty] | NM | N | 27 SunPower SPR-X21-345-C-AC (240V) | 2017-09-22 | 2017-10-04 | 8 | 2017-10-04 | [14 empty] | 2017-11-13 | 2017-11-27 |  | Y
Central Hudson |  | HUDSON SOLAR | CH-02536 | Kingston | Kingston |  | 12402 | G | 2091 | Hurley Ave | TBD |  | 1198.8 | [13 empty] | CDG | N | 36 SolarEdge Technologies SE33.3KUS SOLAREDGE SE33300US (36) | 2017-10-04 | 2017-10-18 | 10 | 2017-10-18 | 2017-10-18 | 2017-11-06 | 13 |  |  |  |  | 37000 | [9 empty] | W
Central Hudson |  | HUDSON SOLAR | CH-02537 | Kingston | Rhinebeck |  | 12572 | G | 3002 | Saugerties | TBD |  | 1332 | [13 empty] | CDG | N | 40 SolarEdge Technologies SE33.3KUS SOLAREDGE SE33300 US (40) | 2017-10-04 | 2017-10-18 | 10 | 2017-10-18 | 2017-10-18 | 2017-11-06 | 13 |  |  |  |  | 39000 | [9 empty] | W
Central Hudson |  | Sunrun Inc. | CH-08341 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8092 | Fishkill Plains | N |  | 3 | [13 empty] | NM | N | 1 ABB PVI-3.0-OUTD-S-US-A (240V) [SI1] | 2017-09-22 | 2017-10-04 | 8 | 2017-10-04 | [14 empty] | 2017-12-19 | 2017-12-19 |  | Y
Central Hudson |  | Trinity Solar | CH-10036 | Fishkill | Beacon |  | 12508 | G | 8018 | Forgebrook | N |  | 3.7 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3800H-US | 2017-10-04 | 2017-10-04 | 0 | 2017-10-04 | [17 empty] | W
Central Hudson |  | Robert Moss | CH-10047 | Catskill | Hunter | Greene | 12442 | E | 2081 | Hunter | N |  | 6 | [13 empty] | NM | N | 1 SMA America SB6000TL-US-22 (240V) | 2017-10-16 | 2017-10-26 | 8 | 2017-10-26 | [14 empty] | 2018-03-16 | 2018-03-19 |  | Y
Central Hudson |  | Solar Generation | CH-10064 | Catskill | Cairo | Greene | 12413 | G | 2043 | South Cairo | N |  | 9.8 | [13 empty] | NM | N | 1 SMA America SB6000TL-US (240V) 1 SMA America SB3800TL-US-22 (240V) | 2017-10-04 | 2017-10-11 | 5 | 2017-10-11 | [14 empty] | 2018-01-02 | 2018-01-08 |  | Y
Central Hudson |  | Lighthouse Solar | CH-00279 | Newburgh | Gardiner | Ulster | 12525 | G | 5011 | Modena | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE 11400A-US (240V) | 2017-09-25 | 2017-10-05 | 8 | 2017-10-05 | [14 empty] | 2017-11-15 | 2017-11-20 |  | Y
Central Hudson |  | Lighthouse Solar | CH-00282 | Kingston | Kerhonkson | Ulster | 12446 | G | 3082 | Kerhonkson | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE 10000A-US (277V) | 2017-09-25 | 2017-10-05 | 8 | 2017-10-05 | [8 empty] | 350 | 350 |  | 2017-10-10 | 2017-10-10 | 2017-11-27 | 2017-11-27 | 2017-11-27 |  | Y
Central Hudson |  | SolarCity | CH-07366 | Fishkill | Fishkill | Dutchess | 12524 | G | 8094 | Fishkill Plains | N |  | 11.8 | [13 empty] | NM | N | 1 Delta Electronics SOLIVIA 6.6 NA G4 TL (240V) 1 Delta Electronics SOLIVIA 5.2 NA G4 TL (208V) 1 DELTA SOLIVIA 6.6 TL 1 DELTA SOLIVIA 5.2 TL | 2017-09-26 | 2017-10-05 | 7 | 2017-10-05 | [14 empty] | 2017-11-14 | 2017-11-21 |  | Y
Central Hudson |  | SolarCity | CH-09976 | Kingston | Kingston | Ulster | 12401 | G | 1011 | Boulevard | Y | CH-09976 | 10.4 | 10 | [12 empty] | NM | N | 1 Delta Electronics SOLIVIA 6.6 NA G4 TL (208V) 1 Delta Electronics SOLIVIA 3.8 NA G4 TL (240V) 2TeslaAC Powerwall 2.0 | 2017-09-25 | 2017-10-05 | 8 | 2017-10-05 | [14 empty] | 2018-01-25 | 2018-01-25 |  | Y
Central Hudson |  | New York State Solar Farm | CH-10049 | Catskill | Haines Fls | Greene | 12436 | G | 2385 | Lawrenceville | N |  | 4.8 | [13 empty] | NM | N | 15 SunPower SPR-E20-327-C-AC (240V) | 2017-09-25 | 2017-10-05 | 8 | 2017-10-05 | [14 empty] | 2017-12-11 | 2017-12-11 |  | Y
Central Hudson |  | RED HOOK SOLAR | CH-10037 | Poughkeepsie | Tivoli | Dutchess | 12583 | G | 7062 | Milan | N |  | 7.8 | [13 empty] | NM | N | 1 SMA America SB7.7-1SP-US-40 (240V) | 2017-10-05 | 2017-10-05 | 0 | 2017-10-05 | [14 empty] | 2017-10-16 | 2017-10-16 |  | Y
Central Hudson |  | Malcarne Contracting | CH-00348 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6044 | Spackenkill | N |  | 15.2 | [13 empty] | NM | N | 2 SolarEdge Technologies SE7600A-US (240V) [SI1] Incorrect inverter listed on page two of three line diagram | 2017-10-02 | 2017-10-09 | 5 | 2017-10-09 | [8 empty] | 350 | 350 |  |  |  |  | 2017-11-30 | 2017-12-01 |  | Y
Central Hudson |  | New York State Solar Farm | CH-00473 | Newburgh | Highland | Ulster | 12528 | G | 5024 | Ohioville | Y | CH-02982 | 2.9 | 2.9 | [12 empty] | NM | N | 9 SunPower SPR-X21-335-BLK-C-AC (240V) 9 SUNPOWER C-AC1SonnenSONNEN Eco 61SonnenECO 6 | 2017-10-09 | 2017-10-09 | 0 | 2017-10-09 | [8 empty] | 350 | 350 |  | 2017-10-12 | 2017-10-12 | 2017-10-17 | 2018-01-26 | 2018-01-26 |  | Y
Central Hudson |  | HUDSON SOLAR | CH-02344 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 7024 | Tinkertown | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600A-US (240V) 1 SOLAREDGE SE7600A-USS2 | 2017-10-03 | 2017-10-09 | 4 | 2017-10-09 | [14 empty] | 2017-11-21 | 2017-11-22 |  | Y
Central Hudson |  | SolarCity | CH-06115 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8072 | Shenandoah | Y |  | 7.6 | 5 | [12 empty] | NM | N | 1 Delta Electronics SOLIVIA 7.6 NA G4 TL (240V) 1TeslaAC Powerwall 2.0 | 2017-09-27 | 2017-10-09 | 8 | 2017-10-09 | [14 empty] | 2018-02-05 | 2018-02-05 |  | Y
Central Hudson |  | You Save Green | CH-09964 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600A-US (240V) [SI1] 1 SOLAREDGE SE 10000A | 2017-10-03 | 2017-10-09 | 4 | 2017-10-09 | [14 empty] | 2017-11-09 | 2017-11-14 |  | Y
Central Hudson |  | Hudson Solar | CH-10015 | Kingston | High Fls | Ulster | 12440 | G | 3022 | High Falls | N |  | 7.6 | [13 empty] | NM | N | 1solaredgese7600a-uss2 | 2017-09-29 | 2017-10-09 | 6 | 2017-10-09 | [14 empty] | 2017-11-28 | 2017-12-06 |  | Y
Central Hudson |  | SolarCity | CH-10059 | Catskill | Athens | Greene | 12015 | G | 1074 | Coxsackie | N |  | 3 | [13 empty] | NM | N | 1 ABB PVI-3.0-OUTD-S-US-Z-A (240V) [SI1] | 2017-10-10 | 2017-10-18 | 6 | 2017-10-18 | [14 empty] | 2017-12-01 | 2017-12-01 |  | Y
Central Hudson |  | New York State Solar Farm | CH-10056 | Newburgh | Marlboro | Ulster | 12542 | G | 5004 | Marlboro | N |  | 8.6 | [13 empty] | NM | N | 27 SunPower SPR-E20-327-C-AC (240V) | 2017-10-09 | 2017-10-11 | 2 | 2017-10-11 | [14 empty] | 2017-12-18 | 2017-12-18 |  | Y
Central Hudson |  | New York State Solar Farm | CH-10058 | Kingston | Saugerties | Ulster | 12477 | G | 3004 | Saugerties | N |  | 5.4 | [13 empty] | NM | N | 17 SunPower SPR-E20-327-C-AC (240V) | 2017-10-09 | 2017-10-12 | 3 | 2017-10-12 | [14 empty] | 2017-12-18 | 2017-12-26 |  | Y
Central Hudson |  | New York State Solar Farm | CH-10057 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6043 | Spackenkill | N |  | 19.2 | [13 empty] | NM | N | 60 SunPower SPR-X21-345-C-AC (240V) | 2017-10-09 | 2017-10-11 | 2 | 2017-10-11 | [14 empty] | 2017-12-04 | 2017-12-11 |  | Y
Central Hudson |  | Wallkill Hydro | CH-10060 | Newburgh | Wallkill | Dutchess | 12533 | G | 5043 | East Walden | N | [11 empty] | 490 |  |  |  | CDG | Y | Reliance Electric Company Duty Master A-C Induction Generator XE 449T PReliance Electric CompanyDuty Master A-C Induction 490 | 2017-10-10 | 2017-10-10 | 0 | 2017-10-10 | 2017-10-10 | 2017-10-10 | 0 | [11 empty] | 2017-10-10 | 1986-10-23 |  | Y | N | October 2017 - Account readover to new customer.
Central Hudson |  | Hudson Solar | CH-10062 | Poughkeepsie | Poughkeepsie |  | 12601 | G | 6073 | East Park | N |  | 5.8 | [13 empty] | NM | N | 18 SunPower SPR-E20-327-C-AC (240V) | 2017-10-10 | 2017-10-18 | 6 | 2017-10-18 | [17 empty] | W
Central Hudson |  | New York State Solar Farm | CH-00462 | Kingston | Ellenvl | Ulster | 12428 | G | 396 | Clinton Ave | N |  | 14.4 | [13 empty] | NM | N | 45 SunPower SPR-X21-345-C-AC (240V) 16 SUNPOWER X21 AC | 2017-10-06 | 2017-10-11 | 3 | 2017-10-11 | [8 empty] | 350 | 350 |  | 2017-12-11 | 2017-12-11 | 2018-01-26 | 2018-01-26 | 2018-01-26 |  | Y
Central Hudson |  | BQ Energy, LLC | CH-10014 | Newburgh | W Park |  | 12590 | G | 5084 | Highland | N |  | 2000 | [13 empty] | CDG | N | 80 Huawei Technologies SUN2000-25KTL-US | 2017-12-28 | 2018-01-08 | 6 | 2018-01-08 | 2018-01-08 | 2018-01-29 | 15 | 2018-02-16 | 2018-03-26 | 2018-06-28 | 66 | 21684.05 | 1752332 |  | 2019-02-20 | [5 empty] | 2019-09-03 | W | Y | 5/31/18 - CESIR placed on hold due to awaiting documentation from applicant. The CESIR recommenced on 6/8/18 when updated documentation was received. 10/31/18 - 1/28/19 Detailed Voltage Flicker Study.
Central Hudson |  | Infinity Solar Systems | CH-10018 | Newburgh | New Windsor | Orange | 12553 | G | 4046 | Union Ave | N |  | 13.4 | [13 empty] | NM | N | 42 SunPower SPR-X22-360-C-AC (240V) | 2017-10-09 | 2017-10-11 | 2 | 2017-10-11 | [14 empty] | 2017-10-31 | 2017-10-31 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-10050 | Newburgh | Maybrook | Orange | 12543 | G | 4026 | Coldenham | N |  | 8 | [13 empty] | NM | N | 25 SunPower SPR-X21-345-C-AC (240V) | 2017-10-11 | 2017-10-20 | 7 | 2017-10-20 | [14 empty] | 2017-11-03 | 2017-11-13 |  | Y
Central Hudson |  | New York State Solar Farm | CH-10065 | Newburgh | New Paltz | Ulster | 12561 | G | 5024 | Ohioville | N |  | 12.5 | [13 empty] | NM | N | 39 SunPower SPR-E20-327-C-AC (240V) | 2017-10-11 | 2017-10-20 | 7 | 2017-10-20 | [14 empty] | 2017-11-08 | 2017-11-10 |  | Y
Central Hudson |  | HUDSON SOLAR | CH-10040 | Kingston | Boicevl | Ulster | 12412 | G | 3011 | Woodstock | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600A-US (208V) [SI1] | 2017-10-11 | 2017-10-19 | 6 | 2017-10-19 | [14 empty] | 2017-12-08 | 2017-12-08 |  | Y
Central Hudson |  | Tri-State Solar Services | CH-10055 | Newburgh | Newburgh | Orange | 12550 | G | 4053 | Union Ave | N |  | 3 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3000 (240V) | 2017-10-20 | 2017-10-30 | 6 | 2017-10-30 | [14 empty] | 2018-09-27 | 2018-09-27 |  | Y
Central Hudson |  | Novel Approaches | CH-10048 | Kingston | Greenfield Pk | Ulster | 12435 | G | 3096 | Grimley Rd | N | CH-02781 | 12.5 | [13 empty] | NM | N | 1 Fronius USA Fronius Primo 12.5-1 (240V) | 2017-10-12 | 2017-10-12 | 0 | 2017-10-12 | [8 empty] | 350 | 350 |  |  |  |  | 2017-11-22 | 2017-11-22 |  | Y
Central Hudson |  | New York State Solar Farm | CH-10066 | Poughkeepsie | Tivoli | Dutchess | 12583 | G | 7062 | Milan | N |  | 6.4 | [13 empty] | NM | N | 20 SunPower SPR-E20-327-C-AC (240V) | 2017-10-13 | 2017-10-25 | 8 | 2017-10-25 | [14 empty] | 2017-12-14 | 2018-01-03 |  | Y
Central Hudson |  | New York State Solar Farm | CH-10067 | Poughkeepsie | Lagrangevl | Dutchess | 12540 | G | 6053 | Todd Hill | N |  | 32 | [13 empty] | NM | N | 100 SunPower SPR-E20-327-C-AC (240V) | 2017-11-28 | 2017-12-04 | 4 | 2017-12-04 | [8 empty] | 3500 | 2013.71 |  | 2017-12-08 | 2017-12-08 | 2017-12-31 | 2018-01-15 | 2018-01-15 | 2018-09-14 | Y
Central Hudson |  | Delaware River Solar | CH-09954 | Kingston | Neversink |  | 12788 | G | 3091 | Neversink | TBD |  | 1980 | [13 empty] | CDG | N | Ingecon Sun PowerMax 1245TL U B48066smaSunny Tripower 30000TL-US | 2017-10-27 | 2017-11-06 | 6 | 2017-11-06 | 2017-11-06 | 2017-11-22 | 12 | 2018-02-05 | 2018-02-06 | 2018-05-03 | 60 | 10440.57 | 2572911 | [7 empty] | 2018-09-28 | W
Central Hudson |  | Delaware River Solar | CH-09955 | Kingston | Neversink |  | 12788 | G | 3091 | Neversink | TBD |  | 1980 | [13 empty] | CDG | N | 66smaSunny Tripower 30000TL-US | 2017-10-27 | 2017-11-06 | 6 | 2017-11-06 | 2017-11-06 | 2017-11-22 | 12 | 2018-02-05 | 2018-02-06 | 2018-05-03 | 60 | 10440.57 | 2572911 | [7 empty] | 2018-09-28 | W
Central Hudson |  | Trinity Solar | CH-10068 | Kingston | Kingston | Ulster | 12401 | G | 2093 | Hurley Ave | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE 11400A-US (240V) | 2017-11-07 | 2017-11-15 | 6 | 2017-11-15 | [14 empty] | 2018-01-02 | 2018-01-03 |  | Y
Central Hudson |  | Trinity Solar | CH-10069 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7051 | Rhinebeck | N |  | 3 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3000H-US | 2017-10-26 | 2017-11-07 | 8 | 2017-11-07 | [14 empty] | 2018-02-08 | 2018-02-08 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-10070 | Newburgh | New Windsor | Orange | 12553 | G | 4094 | Bethlehem Rd | N |  | 11.2 | [13 empty] | NM | N | 35 SunPower SPR-X21-335-BLK-C-AC (240V) | 2017-10-16 | 2017-10-26 | 8 | 2017-10-26 | [14 empty] | 2018-01-29 | 2018-02-01 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-10073 | Newburgh | New Windsor | Orange | 12553 | G | 4095 | Bethlehem Rd | N |  | 6.2 | [13 empty] | NM | N | 16 Enphase Energy IQ6-60-X-US (240V) 11 Enphase Energy IQ6-60-X-US (240V) | 2017-10-27 | 2017-10-27 | 0 | 2017-10-27 | [14 empty] | 2017-11-22 | 2017-12-08 |  | Y
Central Hudson |  | Solitude Solar, LLC | CH-10072 | Catskill | Tannersville |  | 12485 | G | 2385 | Lawrenceville | TBD |  | 1980.7 | [13 empty] | CDG | N | 66 SMA America STP30000TL-US-10 | 2017-12-12 | 2017-12-27 | 9 | 2017-12-27 | 2017-12-27 | 2018-01-18 | 15 |  |  |  |  | 37000 | [9 empty] | W
Central Hudson |  | Trinity Solar | CH-10054 | Kingston | Kingston |  | 12401 | G | 2093 | Hurley Ave | TBD |  | 3 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3000H-US | 2017-10-10 | 2017-10-18 | 6 | 2017-10-18 | [17 empty] | W
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-10025 | Newburgh | Middletown | Orange | 10940 | G | 5051 | Maybrook | N |  | 6.9 | [13 empty] | NM | N | 30 Enphase Energy IQ6-60-X-US (240V) | 2017-10-09 | 2017-10-18 | 7 | 2017-10-18 | [14 empty] | 2018-01-04 | 2018-01-04 |  | Y
Central Hudson |  | Trinity Solar | CH-10024 | Kingston | Shokan | Ulster | 12481 | G | 3011 | Woodstock | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US | 2017-10-10 | 2017-10-18 | 6 | 2017-10-18 | [14 empty] | 2017-10-31 | 2017-11-01 |  | Y
Central Hudson |  | Trinity Solar | CH-10075 | Newburgh | Newburgh | Orange | 12550 | G | 5004 | Marlboro | N |  | 3.8 | [13 empty] | NM | N | 1SolaredgeSE3800H-US | 2017-11-01 | 2017-11-09 | 6 | 2017-11-09 | [14 empty] | 2017-12-20 | 2017-12-20 |  | Y
Central Hudson |  | SolarCity | CH-10077 | Catskill | Catskill | Greene | 12414 | G | 2003 | North Catskill | Y | CH-10077 | 7.6 | 5 | [12 empty] | NM | N | 1 Delta Electronics SOLIVIA 7.6 NA G4 TL (240V) 1TeslaAC Powerwall 2.0 | 2018-02-14 | 2018-02-23 | 6 | 2018-02-23 | [14 empty] | 2018-03-13 | 2018-03-13 |  | Y |  | Storm Restoration due to 3/2/18 Heavy Wet Snow and Damaging Wind Storm.
Central Hudson |  | Solitude Solar, LLC | CH-10071 | Catskill | Westerlo |  | 12193 | G | 1091 | Westerlo | TBD |  | 1980.7 | [13 empty] | CDG | N | 66 SMA America STP30000TL-US-10 | 2018-01-16 | 2018-01-30 | 10 | 2018-01-30 | 2018-01-30 | 2018-02-21 | 15 | [14 empty] | W
Central Hudson |  | Conscious Energy | CH-10074 | Kingston | Kingston | Ulster | 12401 | G | 2094 | Hurley Ave | N |  | 7.7 | [13 empty] | NM | N | 1 SMA America SB7700TL-US-22 (240V) | 2017-10-27 | 2017-11-10 | 10 | 2017-11-10 | [14 empty] | 2018-08-22 | 2018-08-23 |  | Y
Central Hudson |  | Self | CH-08890 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8046 | Myers Corners | N |  | 6 | [13 empty] | NM | N | SOLAREDGE SE6000A (1) | 2017-10-20 | 2017-10-20 | 0 | 2017-10-20 | [14 empty] | 2017-10-31 | 2017-11-01 |  | Y
Central Hudson |  | Trinity Solar | CH-10021 | Fishkill | Beacon | Dutchess | 12508 | G | 8087 | Tioronda | N |  | 3 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3000H-US | 2017-10-11 | 2017-10-19 | 6 | 2017-10-19 | [14 empty] | 2018-01-02 | 2018-01-04 |  | Y
Central Hudson |  | SolarCity | CH-10080 | Newburgh | New Windsor | Orange | 12553 | G | 4042 | Union Ave | N |  | 7.6 | [13 empty] | NM | N | Delta Solivia 7.6 TL | 2017-10-19 | 2017-10-30 | 7 | 2017-10-30 | [14 empty] | 2018-01-12 | 2018-01-23 |  | Y
Central Hudson |  | Hudson Solar | CH-10078 | Catskill | Westerlo | Albany | 12193 | G | 1092 | Westerlo | N |  | 6.4 | [13 empty] | NM | N | 20 SunPower SPR-E20-327-C-AC (240V) | 2017-10-19 | 2017-10-27 | 6 | 2017-10-27 | [14 empty] | 2018-01-16 | 2018-01-19 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-10079 | Newburgh | Rock Tvrn | Orange | 12575 | G | 4097 | Bethlehem Rd | N |  | 9.6 | [13 empty] | NM | N | 30 SunPower SPR-X21-345-C-AC (240V) | 2017-10-19 | 2017-10-30 | 7 | 2017-10-30 | [14 empty] | 2017-12-06 | 2017-12-06 |  | Y
Central Hudson |  | New York State Solar Farm | CH-10083 | Newburgh | Marlboro | Ulster | 12542 | G | 5004 | Marlboro | N |  | 9.6 | [13 empty] | NM | N | 30 SunPower SPR-X21-345-C-AC (240V) | 2017-10-19 | 2017-10-30 | 7 | 2017-10-30 | [14 empty] | 2017-12-18 | 2017-12-18 |  | Y
Central Hudson |  | Hudson Solar | CH-10082 | Newburgh | New Paltz | Ulster | 12561 | G | 5031 | Galeville | N |  | 29.7 | [13 empty] | RNM | N | 2SMASB11000TL-US-12 (240V)1SMASB7700TL-US-22 (240V) | 2017-10-06 | 2017-10-19 | 9 | 2017-10-19 | [14 empty] | 2017-10-19 | 2017-10-24 |  | Y
Central Hudson |  | Kasselman Solar | CH-10020 | Catskill | Surprise | Greene | 12176 | G | 2061 | Freehold | N |  | 13.4 | [13 empty] | NM | N | 56 Enphase Energy M250-72-2LL-S2x (240V) | 2017-10-11 | 2017-10-20 | 7 | 2017-10-20 | [8 empty] | 350 | 350 |  | 2017-11-10 | 2017-11-10 | 2017-11-28 | 2017-12-05 | 2017-12-05 |  | Y
Central Hudson |  | New York State Solar Farm | CH-10086 | Kingston | Saugerties | Ulster | 12477 | G | 3004 | Saugerties | N |  | 7 | [13 empty] | NM | N | 22 SunPower SPR-E20-327-C-AC (240V) | 2017-10-20 | 2017-11-01 | 8 | 2017-11-01 | [14 empty] | 2018-03-14 | 2018-03-14 |  | Y
Central Hudson |  | Hudson Solar | CH-10084 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7061 | Milan | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US | 2017-10-20 | 2017-10-30 | 6 | 2017-10-30 | [14 empty] | 2017-12-26 | 2017-12-26 |  | Y
Central Hudson |  | Apex Solar Power | CH-10085 | Newburgh | Newburgh |  | 12550 | G | 402 | Montgomery St | N | CH-10085 | 3.8 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3800 (240V) | 2017-10-20 | 2017-10-30 | 6 | 2017-10-30 | [14 empty] | 2018-02-02 | 2018-02-09 |  | W
Central Hudson |  | Hudson Solar | CH-02538 | Kingston | High Fls | Ulster | 12440 | G | 3024 | High Falls | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600A-US (240V) [SI1] 1 SOLAREDGE SE7600 A-US-U | 2017-10-10 | 2017-10-24 | 10 | 2017-10-24 | [14 empty] | 2017-11-28 | 2017-12-06 |  | Y
Central Hudson |  | Con Edison Solutions | CH-09988 | Kingston | Kingston | Ulster | 12401 | G | 2094 | Hurley Ave | N |  | 3000 | [13 empty] | CDG | Y | 24 Kaco KACO blueplanet 125 TL3 M1 WM OD IIP0 (600V) [SI1] 16KacoBlue Planet 125 TL3 | 2017-11-06 | 2017-11-07 | 1 | 2017-11-07 | 2017-11-07 | 2017-11-30 | 15 | 2018-02-16 | 2018-03-15 | 2018-06-21 | 68 | 20628.86 | 322646.25 | 216486.08 | 2018-09-18 | 2019-03-11 | 2019-03-11 | 2020-12-11 | 2021-03-22 | 2021-03-22 | 2021-06-04 | Y | Y | 5/25/18 - CESIR placed on hold due to change in grounding bank design. The CESIR recommenced on 6/7/18 when updated documentation was received.
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-10088 | Newburgh | New Windsor | Orange | 12553 | G | 4095 | Bethlehem Rd | N |  | 6.7 | [13 empty] | NM | N | 10 Enphase Energy IQ6-60-X-US (240V) 4 Enphase Energy IQ6-60-X-US (240V) 15 Enphase Energy IQ6-60-X-US (240V) | 2017-10-23 | 2017-10-30 | 5 | 2017-10-30 | [14 empty] | 2018-01-08 | 2018-01-12 |  | Y
Central Hudson |  | Kasselman Solar | CH-10089 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6096 | Manchester | N |  | 2.8 | [13 empty] | NM | N | 10 Enphase Energy IQ6PLUS-72-x-US (240V) [SI1] | 2017-10-23 | 2017-10-31 | 6 | 2017-10-31 | [14 empty] | 2017-12-19 | 2017-12-19 |  | Y
Central Hudson |  | SolarCIty | CH-10091 | Kingston | Kerhonkson | Ulster | 12446 | G | 3083 | Kerhonkson | Y | CH-08892 |  | 5 | [12 empty] | NM | N | 1TeslaAC Powerwall 2.0 | 2018-03-27 | 2018-04-03 | 4 | 2018-04-03 | [8 empty] | 350 | 350 |  | 2018-05-08 | 2018-05-08 | 2018-07-19 | 2018-12-12 | 2018-12-12 |  | Y
Central Hudson |  | Lighthouse Solar | CH-10081 | Kingston | Kingston | Ulster | 12401 | G | 1013 | Boulevard | N |  | 299.7 | [13 empty] | NM | Y | 9 SolarEdge Technologies SE33.3KUS | 2018-03-22 | 2018-04-03 | 7 | 2018-04-03 | 2018-04-03 | 2018-04-23 | 14 | [11 empty] | 2020-07-02 | 2020-07-02 |  | Y | Y
Central Hudson |  | Infinity Solar Systems | CH-10090 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6008 | Reynolds Hill | N |  | 7.7 | [13 empty] | NM | N | 24 SunPower SPR-X21-345-C-AC (240V) | 2017-10-23 | 2017-10-31 | 6 | 2017-10-31 | [14 empty] | 2017-11-02 | 2017-11-07 |  | Y
Central Hudson |  | STANDARD SOLAR, INC. | CH-10087 | Catskill | Westerlo |  | 12193 | G | 1091 | Westerlo | TBD |  | 2000 | [13 empty] | CDG | N | 30 Chint Power Systems America CPS SCA60KTL-DO/US-480 4 Chint Power Systems America CPS SCA50KTL-DO/US-480 | 2017-10-23 | 2017-10-27 | 4 | 2017-10-27 | 2017-10-27 | 2017-11-06 | 6 |  |  |  |  | 39000 | [9 empty] | W
Central Hudson |  | High Peaks Solar, LLC | CH-10094 | Catskill | Jewett | Greene | 12444 | E | 2389 | Vinegar Hill | N | CH-10094 | 6.5 | [13 empty] | NM | N | 27 Enphase Energy M250-60-2LL-S2X (-ZC) (-NA) (240V) | 2017-11-01 | 2017-11-09 | 6 | 2017-11-09 | [14 empty] | 2017-11-30 | 2017-11-30 |  | Y
Central Hudson |  | New York State Solar Farm | CH-10093 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7054 | Rhinebeck | N |  | 4.5 | [13 empty] | NM | N | 14 SunPower SPR-E20-327-C-AC (240V) | 2017-10-24 | 2017-10-31 | 5 | 2017-10-31 | [14 empty] | 2018-01-26 | 2018-02-01 |  | Y
Central Hudson |  | Lighthouse Solar | CH-10098 | Kingston | Stone Ridge | Ulster | 12484 | G | 3023 | High Falls | N |  | 22.8 | [13 empty] | NM | N | 2 SolarEdge Technologies SE 11400A-US (240V) | 2017-10-25 | 2017-11-02 | 6 | 2017-11-02 | [8 empty] | 350 | 350 |  | 2017-11-06 | 2017-11-06 | 2017-12-21 | 2017-12-14 | 2017-12-14 |  | Y
Central Hudson |  | Sunrun Inc. | CH-10097 | Newburgh | New Windsor | Orange | 12553 | G | 4044 | Union Ave | N |  | 6 | [13 empty] | NM | N | 1 ABB PVI-6000-OUTD-US-A (240V) | 2017-10-24 | 2017-10-31 | 5 | 2017-10-31 | [14 empty] | 2017-11-30 | 2017-12-01 |  | Y
Central Hudson |  | New York State Solar Farm | CH-10095 | Newburgh | Highland | Ulster | 12528 | G | 5081 | Highland | N |  | 3.2 | [13 empty] | NM | N | 10 SunPower SPR-X22-360-C-AC (240V) | 2017-10-25 | 2017-11-02 | 6 | 2017-11-02 | [14 empty] | 2017-12-18 | 2017-12-18 |  | Y
Central Hudson |  | New York State Solar Farm | CH-10096 | Newburgh | Newburgh | Orange | 12550 | G | 4045 | Union Ave | N |  | 7.7 | [13 empty] | NM | N | 24 SunPower SPR-X21-345-C-AC (240V) | 2017-11-02 | 2017-11-13 | 7 | 2017-11-13 | [14 empty] | 2017-12-04 | 2017-12-06 |  | Y
Central Hudson |  | You Save Green | CH-10099 | Newburgh | New Paltz | Ulster | 12561 | G | 5023 | Ohioville | N |  | 10 | [13 empty] | NM | N | 1SolaredgeSE 10000A-US (240V) | 2017-11-03 | 2017-11-03 | 0 | 2017-11-03 | [14 empty] | 2017-12-01 | 2017-12-01 |  | Y
Central Hudson |  | Tesla | CH-10100 | Kingston | Stone Ridge | Ulster | 12484 | G | 3023 | High Falls | Y |  | 5.2 | 5 | [12 empty] | NM | N | 1 Delta Electronics SOLIVIA 5.2 NA G4 TL (240V) 1TeslaAC Powerwall 2.0 | 2018-03-02 | 2018-03-05 | 1 | 2018-03-05 | [14 empty] | 2018-03-06 | 2018-03-13 |  | Y
Central Hudson |  | Matrix Development LLC | CH-10063 | Poughkeepsie | Hyde Park |  | 12538 | G | 7042 | Staatsburg | TBD |  | 1980 | [13 empty] | CDG | N | 33 Solectria Renewables PVI 60TL-480 | 2017-11-15 | 2017-12-01 | 10 | 2017-12-01 | 2017-12-01 | 2017-12-20 | 13 |  |  |  |  | 41000 | [9 empty] | W
Central Hudson |  | EnterSolar LLC | CH-10061 | Poughkeepsie | Hyde Park |  | 12538 | G | 7042 | Staatsburg | TBD |  | 1980 | [13 empty] | CDG | N | 33 Solectria Renewables PVI 60TL-480 | 2017-11-15 | 2017-12-01 | 10 | 2017-12-01 | 2017-12-01 | 2017-12-20 | 13 |  |  |  |  | 37000 | [9 empty] | W
Central Hudson |  | INFINITY SOLAR SYSTEMS | CH-10107 | Newburgh | Newburgh | Orange | 12550 | G | 4013 | West Balmville | N |  | 9 | [13 empty] | NM | N | 28 SunPower SPR-X21-345-C-AC (240V) | 2017-10-30 | 2017-11-07 | 6 | 2017-11-07 | [14 empty] | 2018-01-12 | 2018-01-18 |  | Y
Central Hudson |  | Trinity Solar | CH-10109 | Newburgh | Newburgh | Orange | 12550 | G | 5004 | Marlboro | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US | 2017-10-31 | 2017-11-08 | 6 | 2017-11-08 | [14 empty] | 2018-01-23 | 2018-01-24 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-10111 | Newburgh | Newburgh | Orange | 12550 | G | 4023 | Coldenham | N |  | 6.9 | [13 empty] | NM | N | 3 Enphase Energy IQ6-60-X-US (240V) 3 Enphase Energy IQ6-60-X-US (240V) 4 Enphase Energy IQ6-60-X-US (240V) 20 Enphase Energy IQ6-60-X-US (240V) | 2017-11-01 | 2017-11-09 | 6 | 2017-11-09 | [14 empty] | 2018-01-12 | 2018-01-12 |  | Y
Central Hudson |  | SELF | CH-10110 | Kingston | Olive Brdg | Ulster | 12461 | G | 3024 | High Falls | N |  | 2.8 | [13 empty] | NM | N | 1XantraxGT2.8-NA-240/208 (208V) | 2017-11-10 | 2017-11-21 | 7 | 2017-11-21 | [14 empty] | 2017-12-29 | 2017-12-29 |  | Y
Central Hudson |  | SolarCity | CH-10115 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 7025 | Tinkertown | N |  | 6 | [13 empty] | NM | N | 1 ABB PVI-3.0-OUTD-S-US-Z-A (240V) 1 ABB PVI-3.0-OUTD-S-US-Z-A (240V) | 2017-11-01 | 2017-11-09 | 6 | 2017-11-09 | [14 empty] | 2017-11-21 | 2017-11-22 |  | Y
Central Hudson |  | SolarCity | CH-10114 | Newburgh | Newburgh |  | 12550 | G | 4011 | West Balmville | TBD |  | 10.4 | [13 empty] | NM | N | 2 Delta Electronics SOLIVIA 5.2 NA G4 TL (240V) | 2017-11-01 | 2017-11-09 | 6 | 2017-11-09 | [8 empty] | 350 | 350 | [7 empty] | W
Central Hudson |  | SolarCity | CH-10113 | Kingston | Napanoch |  | 12458 | G | 3071 | Honk Falls | N |  | 3 | [13 empty] | NM | N | 1 ABB PVI-3.0-OUTD-S-US-Z-A (240V) | 2017-11-01 | 2017-11-09 | 6 | 2017-11-09 | [14 empty] | 2018-02-16 | 2018-02-20 |  | W
Central Hudson |  | New York State Solar Farm | CH-10112 | Newburgh | New Paltz | Ulster | 12561 | G | 5031 | Galeville | N |  | 4.5 | [13 empty] | NM | N | 14 SunPower SPR-E20-327-C-AC (240V) | 2017-11-01 | 2017-11-09 | 6 | 2017-11-09 | [14 empty] | 2017-12-11 | 2017-12-11 |  | Y
Central Hudson |  | Solar Plus a division of US Energy Concierge, Inc. | CH-10116 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7056 | Rhinebeck | N |  | 15.2 | [13 empty] | NM | N | 2 Pika Energy X7602 | 2017-11-01 | 2017-11-09 | 6 | 2017-11-09 | [8 empty] | 350 | 350 |  | 2017-11-14 | 2017-11-14 | 2017-11-23 | 2017-12-14 | 2017-12-14 |  | Y
Central Hudson |  | Kasselman Solar | CH-10119 | Kingston | Kerhonkson | Ulster | 12446 | G | 3082 | Kerhonkson | N |  | 3.4 | [13 empty] | NM | N | 12 Enphase Energy IQ6PLUS-72-x-US (240V) [SI1] | 2017-11-02 | 2017-11-13 | 7 | 2017-11-13 | [14 empty] | 2017-12-13 | 2017-12-18 |  | Y
Central Hudson |  | Hudson Valley Wind & Solar, LLC | CH-10106 | Kingston | Lk Katrine | Ulster | 12449 | G | 2015 | Lincoln Park | N |  | 166.5 | [13 empty] | NM | N | 5 SolarEdge Technologies SE33.3KUS | 2017-11-06 | 2017-11-17 | 9 | 2017-11-17 | 2017-11-17 | 2017-12-07 | 12 | [11 empty] | 2018-04-13 | 2018-04-17 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-10120 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7061 | Milan | N | CH-10120 | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE 11400A-US (240V) | 2017-11-06 | 2017-11-15 | 7 | 2017-11-15 | [14 empty] | 2018-03-19 | 2018-03-26 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-10125 | Newburgh | New Windsor | Orange | 12553 | G | 4092 | Bethlehem Rd | N |  | 7.6 | [13 empty] | NM | N | 23 Enphase Energy IQ6-60-X-US (240V) 10 Enphase Energy IQ6-60-X-US (240V) | 2017-11-07 | 2017-11-15 | 6 | 2017-11-15 | [14 empty] | 2017-12-26 | 2017-12-26 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-10123 | Newburgh | Campbell Hall | Orange | 10916 | G | 5052 | Maybrook | N |  | 9.9 | [13 empty] | NM | N | 1 SolarEdge Technologies SE 10000A-US (240V) | 2017-11-07 | 2017-11-15 | 6 | 2017-11-15 | [14 empty] | 2017-12-05 | 2017-12-05 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-10122 | Newburgh | Campbell Hall | Orange | 10916 | G | 5054 | Maybrook | N |  | 12 | [13 empty] | NM | N | 2SMASB6.0-1SP-US-40 (240V) | 2017-11-07 | 2017-11-15 | 6 | 2017-11-15 | [14 empty] | 2018-04-03 | 2018-04-03 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-10121 | Newburgh | New Windsor | Orange | 12553 | G | 4046 | Union Ave | N |  | 13.1 | [13 empty] | NM | N | 41 SunPower SPR-X22-360-C-AC (240V) | 2017-11-07 | 2017-11-15 | 6 | 2017-11-15 | [14 empty] | 2018-01-26 | 2018-01-26 |  | Y
Central Hudson |  | SolarCity DBA Tesla | CH-10126 | Newburgh | Campbell Hall | Orange | 10916 | G | 5051 | Maybrook | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000x (240V) | 2017-11-07 | 2017-11-15 | 6 | 2017-11-15 | [14 empty] | 2018-05-22 | 2018-05-25 |  | Y
Central Hudson |  | Kasselman Solar | CH-10128 | Catskill | Preston Holw | Albany | 12469 | G | 1092 | Westerlo | N |  | 5.8 | [13 empty] | NM | N | 25 Enphase Energy IQ6-60-X-US (240V) | 2017-11-08 | 2017-11-17 | 7 | 2017-11-17 | [14 empty] | 2017-12-29 | 2017-12-29 |  | Y
Central Hudson |  | New York State Solar Farm | CH-10129 | Newburgh | Wallkill | Ulster | 12589 | G | 4011 | West Balmville | N |  | 9.3 | [13 empty] | NM | N | 29 SunPower SPR-X22-360-C-AC (240V) | 2017-11-08 | 2017-11-22 | 10 | 2017-11-22 | [14 empty] | 2018-03-01 | 2018-03-16 |  | Y
Central Hudson |  | Apex Solar Power | CH-10127 | Newburgh | Newburgh | Orange | 12550 | G | 4013 | West Balmville | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600A-US (240V) | 2017-11-07 | 2017-11-16 | 7 | 2017-11-16 | [14 empty] | 2018-01-24 | 2018-01-24 |  | Y
Central Hudson |  | Lighthouse Solar | CH-10134 | Kingston | Stone Ridge | Ulster | 12484 | G | 3023 | High Falls | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE 11400A-US (240V) | 2017-11-09 | 2017-11-20 | 7 | 2017-11-20 | [14 empty] | 2017-12-27 | 2018-01-02 |  | Y
Central Hudson |  | SolarCity DBA Tesla | CH-10133 | Kingston | Kingston | Ulster | 12401 | G | 1022 | East Kingston | N |  | 3 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3000 (240V) | 2017-11-09 | 2017-11-20 | 7 | 2017-11-20 | [14 empty] | 2018-02-05 | 2018-02-07 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-10130 | Fishkill | Beacon | Dutchess | 12508 | G | 8017 | Forgebrook | N |  | 3 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3000 (240V) | 2017-11-09 | 2017-11-20 | 7 | 2017-11-20 | [14 empty] | 2017-12-28 | 2017-12-29 |  | Y
Central Hudson |  | Lighthouse Solar | CH-10136 | Newburgh | New Paltz | Ulster | 12561 | G | 5023 | Ohioville | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US | 2017-11-20 | 2017-11-21 | 1 | 2017-11-21 | [14 empty] | 2017-12-07 | 2017-12-13 |  | Y
Central Hudson |  | INFINITY SOLAR SYSTEMS | CH-10137 | Fishkill | Beacon | Dutchess | 12508 | G | 8017 | Forgebrook | N |  | 8.3 | [13 empty] | NM | N | 26 SunPower SPR-X22-360-C-AC (240V) | 2017-11-10 | 2017-11-20 | 6 | 2017-11-20 | [14 empty] | 2017-12-26 | 2017-12-29 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-10138 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6011 | Sand Dock | N |  | 5.4 | [13 empty] | NM | N | 17 SunPower SPR-X21-345-C-AC (240V) | 2017-11-10 | 2017-11-20 | 6 | 2017-11-20 | [14 empty] | 2018-01-02 | 2018-01-03 |  | Y
Central Hudson |  | New York State Solar Farm | CH-10139 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 15.4 | [13 empty] | NM | N | 48 SunPower SPR-X22-360-C-AC (240V) | 2017-11-10 | 2017-11-21 | 7 | 2017-11-21 | [14 empty] | 2018-02-20 | 2018-02-20 |  | Y
Central Hudson |  | Trinity Solar | CH-10118 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8094 | Fishkill Plains | N |  | 9.9 | [13 empty] | NM | N | 1 SolarEdge Technologies SE 10000A-US (240V) | 2017-11-13 | 2017-11-21 | 6 | 2017-11-21 | [14 empty] | 2017-12-20 | 2017-12-26 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-10145 | Catskill | Westerlo | Albany | 12193 | G | 1091 | Westerlo | N |  | 13.8 | [13 empty] | NM | N | 36 Enphase Energy IQ6-60-X-US (240V) 24 Enphase Energy IQ6-60-X-US (240V) | 2017-11-13 | 2017-11-21 | 6 | 2017-11-21 | [14 empty] | 2018-01-16 | 2018-01-19 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-10141 | Newburgh | Newburgh | Orange | 12550 | G | 4012 | West Balmville | N |  | 6.4 | [13 empty] | NM | N | 20 SunPower SPR-X21-345-C-AC (240V) | 2017-11-13 | 2017-11-21 | 6 | 2017-11-21 | [14 empty] | 2018-02-12 | 2018-02-15 |  | Y
Central Hudson |  | Kasselman Solar | CH-10140 | Fishkill | Beacon | Dutchess | 12508 | G | 8087 | Tioronda | N |  | 5.6 | [13 empty] | NM | N | 20 Enphase Energy IQ6PLUS-72-X-US (240V) | 2017-11-13 | 2017-11-21 | 6 | 2017-11-21 | [14 empty] | 2017-12-11 | 2017-12-18 |  | Y
Central Hudson |  | Trinity Solar | CH-10142 | Newburgh | Wallkill | Ulster | 12589 | G | 5013 | Modena | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600A-US (240V) | 2017-11-13 | 2017-11-21 | 6 | 2017-11-21 | [14 empty] | 2018-01-02 | 2018-01-02 |  | Y
Central Hudson |  | Solar City | CH-10144 | Kingston | Tillson | Ulster | 12486 | G | 3022 | High Falls | Y | CH-10144 | 6.6 | [13 empty] | NM | N | 1 Delta Electronics SOLIVIA 6.6 NA G4 TL (240V) | 2017-11-13 | 2017-11-21 | 6 | 2017-11-21 | [14 empty] | 2018-04-12 | 2018-04-12 |  | Y
Central Hudson |  | New York State Solar Farm | CH-10143 | Newburgh | Wallkill | Ulster | 12589 | G | 5012 | Modena | N |  | 8 | [13 empty] | NM | N | 25 SunPower SPR-E20-327-C-AC (240V) | 2017-11-13 | 2017-11-21 | 6 | 2017-11-21 | [14 empty] | 2018-01-10 | 2018-01-11 |  | Y
Central Hudson |  | US Energy Concierge, Inc. | CH-10146 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8072 | Shenandoah | N |  | 5 | [13 empty] | NM | N | 1SolaredgeSE5000H-US (240V) | 2017-11-21 | 2017-11-22 | 1 | 2017-11-22 | [14 empty] | 2018-02-28 | 2018-03-01 |  | Y
Central Hudson |  | Solar Generation | CH-10149 | Kingston | Accord | Ulster | 12404 | G | 3024 | High Falls | N |  | 15.2 | [13 empty] | NM | N | 2 SolarEdge Technologies SE7600A-US (240V) | 2017-11-14 | 2017-11-21 | 5 | 2017-11-21 | [14 empty] | 2017-11-30 | 2017-11-30 |  | Y
Central Hudson |  | Vanguard Energy/Sol Providers | CH-10148 | Newburgh | Newburgh | Orange | 12550 | G | 4047 | Union Ave | N |  | 7.3 | [13 empty] | NM | N | 34 Enphase Energy M215-60-2LL-S2x-IG (240V) | 2017-11-22 | 2017-11-22 | 0 | 2017-11-22 | [14 empty] | 2018-01-02 | 2018-01-02 |  | W
Central Hudson |  | SolarCity DBA Tesla | CH-10153 | Fishkill | Fishkill | Dutchess | 12524 | G | 8014 | Forgebrook | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000x (240V) | 2017-11-15 | 2017-11-21 | 4 | 2017-11-21 | [14 empty] | 2018-01-05 | 2018-01-08 |  | Y
Central Hudson |  | New York State Solar Farm | CH-10150 | Fishkill | Beacon | Dutchess | 12508 | G | 8017 | Forgebrook | N |  | 2.9 | [13 empty] | NM | N | 9 SunPower SPR-X22-360-C-AC (240V) | 2017-11-15 | 2017-11-21 | 4 | 2017-11-21 | [14 empty] | 2017-12-11 | 2017-12-11 |  | Y
Central Hudson |  | Solar Generation | CH-10152 | Kingston | Lk Hill | Ulster | 12448 | G | 3012 | Woodstock | N |  | 7.7 | [13 empty] | NM | N | 1 SMA America SB7700TL-US-22 (240V) | 2017-11-22 | 2017-11-27 | 1 | 2017-11-27 | [14 empty] | 2018-01-05 | 2018-01-12 |  | Y
Central Hudson |  | NSE | CH-10155 | Catskill | Athens |  | 12015 | G | 2002 | North Catskill | TBD |  | 2000 | [13 empty] | RNM | N | 40 Chint Power Systems America CPS SCA50KTL-DO/US-480 (480V) | 2018-04-09 | 2018-04-17 | 6 | 2018-04-17 | 2018-04-17 | 2018-05-08 | 15 |  |  |  |  | 14766.67 | [9 empty] | W |  | This project is part of a combined CESIR with CH-10156 and CH-10157 for a total CESIR Cost of $44,300 for all three projects.
Central Hudson |  | New York State Solar Farm | CH-10154 | Newburgh | Highland Mls | Orange | 10930 | G | 4041 | Union Ave | N |  | 10.6 | [13 empty] | NM | N | 33 SunPower SPR-X22-360-C-AC (240V) | 2017-11-15 | 2017-11-16 | 1 | 2017-11-16 | [8 empty] | 350 | 350 |  | 2017-11-17 | 2017-11-17 | 2017-12-04 | 2017-11-27 | 2017-12-04 |  | Y
Central Hudson |  | NSE | CH-10156 | Catskill | Athens |  | 12015 | G | 2002 | North Catskill | TBD |  | 2000 | [13 empty] | CDG | N | 40 Chint Power Systems America CPS SCA50KTL-DO/US-480 (480V) | 2018-04-09 | 2018-04-17 | 6 | 2018-04-17 | 2018-04-17 | 2018-05-08 | 15 |  |  |  |  | 14766.67 | [9 empty] | W |  | This project is part of a combined CESIR with CH-10155 and CH-10157 for a total CESIR Cost of $44,300 for all three projects.
Central Hudson |  | NSE | CH-10157 | Catskill | Athens |  | 12015 | G | 2002 | North Catskill | TBD |  | 2000 | [13 empty] | RNM | N | 40 Chint Power Systems America CPS SCA50KTL-DO/US-480 (480V) [SI1] | 2018-04-09 | 2018-04-17 | 6 | 2018-04-17 | 2018-04-17 | 2018-05-08 | 15 |  |  |  |  | 14766.66 | [9 empty] | W |  | This project is part of a combined CESIR with CH-10155 and CH-10156 for a total CESIR Cost of $44,300 for all three projects.
Central Hudson |  | Lighthouse Solar | CH-10158 | Kingston | Saugerties | Ulster | 12477 | G | 3002 | Saugerties | N |  | 9.9 | [13 empty] | NM | N | 1 SolarEdge Technologies SE 10000A-US (240V) | 2017-11-17 | 2017-11-21 | 2 | 2017-11-21 | [14 empty] | 2018-04-25 | 2018-05-02 |  | Y
Central Hudson |  | New York State Solar Farm | CH-10161 | Kingston | Kingston | Ulster | 12401 | G | 1012 | Boulevard | N |  | 9 | [13 empty] | NM | N | 28 SunPower SPR-X21-345-C-AC (240V) | 2017-11-17 | 2017-11-21 | 2 | 2017-11-21 | [14 empty] | 2018-02-26 | 2018-02-28 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-10160 | Newburgh | New Windsor | Orange | 12553 | G | 4095 | Bethlehem Rd | N |  | 7.1 | [13 empty] | NM | N | 31 Enphase Energy IQ6-60-X-US (240V) | 2017-11-17 | 2017-11-21 | 2 | 2017-11-21 | [14 empty] | 2018-01-18 | 2018-01-23 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-10159 | Kingston | Krumvl | Ulster | 12461 | G | 3024 | High Falls | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000 (240V) | 2017-12-15 | 2017-12-18 | 1 | 2017-12-18 | [14 empty] | 2017-12-26 | 2017-12-26 |  | Y
Central Hudson |  | Trinity Solar | CH-10131 | Poughkeepsie | Millbrook | Dutchess | 12545 | G | 7025 | Tinkertown | N |  | 3 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3000H-US | 2017-11-20 | 2017-11-21 | 1 | 2017-11-21 | [14 empty] | 2017-12-18 | 2018-01-03 |  | Y
Central Hudson |  | Trinity Solar | CH-10132 | Kingston | Saugerties | Ulster | 12477 | G | 2015 | Lincoln Park | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000 (240V) | 2017-11-20 | 2017-11-21 | 1 | 2017-11-21 | [14 empty] | 2018-01-10 | 2018-01-11 |  | Y
Central Hudson |  | New York Power Solutions | CH-10168 | Poughkeepsie | Wingdale | Dutchess | 12594 | G | 6055 | Todd Hill | N | CH-10168 | 7.4 | [13 empty] | NM | N | 32 Enphase Energy IQ6-60-X-US (240V) | 2017-11-27 | 2017-11-27 | 0 | 2017-11-27 | [14 empty] | 2018-04-25 | 2018-04-26 |  | Y
Central Hudson |  | New York State Solar Farm | CH-10163 | Newburgh | New Paltz | Ulster | 12561 | G | 5023 | Ohioville | N |  | 5.1 | [13 empty] | NM | N | 16 SunPower SPR-E20-327-C-AC (240V) | 2017-11-21 | 2017-11-21 | 0 | 2017-11-21 | [14 empty] | 2018-02-23 | 2018-02-26 |  | Y
Central Hudson |  | Autonomous Energies LLC | CH-10162 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6046 | Spackenkill | N |  | 10.9 | [13 empty] | NM | N | 39 Enphase Energy IQ6PLUS-72-ACM-US (240V) | 2017-11-27 | 2017-11-27 | 0 | 2017-11-27 | [14 empty] | 2017-12-06 | 2017-12-06 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-10164 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8092 | Fishkill Plains | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600A-US (240V) | 2017-11-20 | 2017-11-21 | 1 | 2017-11-21 | [14 empty] | 2018-02-26 | 2018-02-26 |  | Y
Central Hudson |  | New York State Solar Farm | CH-10165 | Newburgh | Gardiner |  | 12525 | G | 5031 | Galeville | N |  | 266.4 | [13 empty] | CDG | Y | 8 SolarEdge Technologies SE33.3KUS (480V) | 2018-05-09 | 2018-05-21 | 8 | 2018-05-21 | 2018-05-21 | 2018-06-11 | 14 | 2018-10-23 | 2018-11-27 | 2018-12-13 | 12 | 219.32 | [8 empty] | 2022-02-25 | W
Central Hudson |  | Hudson Solar | CH-10167 | Kingston | Kingston |  | 12402 | G | 2092 | Hurley Ave | TBD |  | 1198.8 | [13 empty] | CDG | N | 36 SolarEdge Technologies SE33.3KUS | 2017-11-20 | 2017-12-06 | 10 | 2017-12-06 | 2017-12-06 | [16 empty] | W
Central Hudson |  | Lighthouse Solar | CH-10147 | Kingston | Stone Ridge | Ulster | 12484 | G | 3024 | High Falls | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US | 2017-11-21 | 2017-11-27 | 2 | 2017-11-27 | [8 empty] | 350 | 350 |  | 2017-11-28 | 2017-11-28 | 2017-12-21 | 2017-12-26 | 2017-12-26 |  | Y
Central Hudson |  | Trinity Solar | CH-10169 | Newburgh | Cornwall | Orange | 12518 | G | 4041 | Union Ave | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US | 2017-11-21 | 2017-11-22 | 1 | 2017-11-22 | [14 empty] | 2018-02-07 | 2018-02-07 |  | Y
Central Hudson |  | Lighthouse Solar | CH-10151 | Kingston | Accord | Ulster | 12404 | G | 3081 | Kerhonkson | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US | 2017-11-22 | 2017-11-22 | 0 | 2017-11-22 | [14 empty] | 2017-12-13 | 2017-12-13 |  | Y
Central Hudson |  | SolarCity DBA Tesla | CH-10172 | Fishkill | Beacon | Dutchess | 12508 | G | 8017 | Forgebrook | N |  | 5.2 | [13 empty] | NM | N | 1 Delta Electronics SOLIVIA 5.2 NA G4 TL (240V) | 2017-11-22 | 2017-11-27 | 1 | 2017-11-27 | [14 empty] | 2017-11-30 | 2017-12-06 |  | Y
Central Hudson |  | Trinity Solar | CH-10170 | Kingston | Saugerties | Ulster | 12477 | G | 3001 | Saugerties | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US | 2017-11-22 | 2017-11-27 | 1 | 2017-11-27 | [14 empty] | 2018-02-01 | 2018-02-02 |  | Y
Central Hudson |  | Trinity Solar | CH-10171 | Kingston | Kingston |  | 12401 | G | 3021 | High Falls | TBD |  | 9.9 | [13 empty] | NM | N | 1 SolarEdge Technologies SE 10000A-US (240V) | 2017-11-22 | 2017-11-27 | 1 | 2017-11-27 | [17 empty] | W
Central Hudson |  | Infinity Solar Systems | CH-10173 | Newburgh | Highland | Ulster | 12528 | G | 5083 | Highland | N |  | 9.9 | [13 empty] | NM | N | 31 SunPower SPR-X21-345-C-AC (240V) | 2017-11-27 | 2017-11-27 | 0 | 2017-11-27 | [14 empty] | 2018-01-16 | 2018-01-26 |  | Y
Central Hudson |  | Monolith Solar Associates LLC | CH-10177 | Kingston | Kingston |  | 12401 | G | 1022 | East Kingston | N |  | 150 | [13 empty] | RNM | Y | 5 SMA America STP30000TL-US-10 | 2018-01-05 | 2018-01-09 | 2 | 2018-01-09 | 2018-01-09 | 2018-01-30 | 15 | [14 empty] | W
Central Hudson |  | Monolith Solar Associates LLC | CH-10176 | Kingston | Kingston |  | 12401 | G | 1022 | East Kingston | N |  | 75 | [13 empty] | RNM | Y | 2 SMA America STP30000TL-US-10 1 SMA America STP15000TL-US-10 [SI1] | 2018-01-05 | 2018-01-09 | 2 | 2018-01-09 | 2018-01-09 | 2018-01-30 | 15 | [14 empty] | W
Central Hudson |  | Monolith Solar Associates LLC | CH-10174 | Newburgh | Highland |  | 12528 | G | 5084 | Highland | N |  | 150 | [13 empty] | RNM | Y | 5 SMA America STP30000TL-US-10 | 2018-01-05 | 2018-01-09 | 2 | 2018-01-09 | 2018-01-09 | 2018-01-30 | 15 | [14 empty] | W
Central Hudson |  | Monolith Solar Associates LLC | CH-10175 | Newburgh | Highland |  | 12528 | G | 5084 | Highland | N |  | 75 | [13 empty] | RNM | Y | 2 SMA America STP30000TL-US-10 1 SMA America STP15000TL-US-10 | 2018-01-08 | 2018-01-09 | 1 | 2018-01-09 | 2018-01-09 | 2018-01-30 | 15 | [14 empty] | W
Central Hudson |  | SolarCity DBA Tesla | CH-10180 | Newburgh | Newburgh | Orange | 12550 | G | 4052 | Union Ave | N |  | 11.4 | [13 empty] | NM | N | 1 Delta Electronics SOLIVIA 7.6 NA G4 TL (240V) 1 Delta Electronics SOLIVIA 3.8 NA G4 TL (240V) | 2017-11-29 | 2017-11-29 | 0 | 2017-11-29 | [14 empty] | 2017-12-18 | 2017-12-27 |  | Y
Central Hudson |  | Novel Approaches | CH-10178 | Kingston | Grahamsvl | Sullivan | 12740 | G | 3095 | Grimley Rd | N |  | 7.7 | [13 empty] | NM | N | 1 SMA America SB7700TL-US-22 (240V) | 2017-12-01 | 2017-12-01 | 0 | 2017-12-01 | [14 empty] | 2017-12-20 | 2018-02-27 |  | Y |  | 12/27/17 - CH rep unable to install net meter due to damaged meter pan. Customer to replace, then call for net meter install. 2/20/18 - Customer advised repairs are complete; net meter was installed.
Central Hudson |  | SolarCity DBA Tesla | CH-10181 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7013 | Hibernia | Y |  | 3.6 | 5 | [12 empty] | NM | N | 1 ABB PVI-3.6-OUTD-S-US-Z-A (240V) [SI1] 1TeslaAC Powerwall 2.0 | 2018-01-08 | 2018-01-09 | 1 | 2018-01-09 | [14 empty] | 2018-02-01 | 2018-02-01 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-10183 | Newburgh | Wallkill | Ulster | 12589 | G | 5043 | East Walden | N |  | 8.7 | [13 empty] | NM | N | 18 Enphase Energy IQ6-60-X-US (240V) 20 Enphase Energy IQ6-60-X-US (240V) | 2017-11-30 | 2017-12-01 | 1 | 2017-12-01 | [14 empty] | 2018-05-03 | 2018-05-09 |  | Y
Central Hudson |  | Kasselman Solar | CH-10184 | Catskill | Coxsackie | Greene | 12051 | G | 1071 | Coxsackie | N | CH-03520 | 5.5 | [13 empty] | NM | N | 24 Enphase Energy IQ6-60-X-US (240V) | 2017-12-01 | 2017-12-04 | 1 | 2017-12-04 | [14 empty] | 2017-12-26 | 2017-12-26 |  | Y
Central Hudson |  | Trinity Solar | CH-10182 | Kingston | Saugerties | Ulster | 12477 | G | 3001 | Saugerties | N |  | 9.9 | [13 empty] | NM | N | 1 SolarEdge Technologies SE 10000A-US (240V) | 2017-11-30 | 2017-12-01 | 1 | 2017-12-01 | [14 empty] | 2018-01-30 | 2018-02-01 |  | Y
Central Hudson |  | SolarCity DBA Tesla | CH-10185 | Fishkill | Beacon | Dutchess | 12508 | G | 8087 | Tioronda | Y |  | 6 | 5 | [12 empty] | NM | N | 1 SolarEdge Technologies SE6000x (240V) 1TeslaAC Powerwall 2.0 | 2018-05-18 | 2018-05-29 | 6 | 2018-05-29 | [14 empty] | 2018-07-17 | 2018-07-17 |  | Y
Central Hudson |  | Kasselman Solar | CH-10186 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6043 | Spackenkill | N |  | 6.4 | [13 empty] | NM | N | 28 Enphase Energy IQ6-60-x-US (240V) [SI1] | 2017-12-04 | 2017-12-04 | 0 | 2017-12-04 | [14 empty] | 2018-01-15 | 2018-01-15 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-10188 | Newburgh | Salisbury Mls | Orange | 12577 | G | 4097 | Bethlehem Rd | N |  | 5.5 | [13 empty] | NM | N | 22 Enphase Energy IQ6-60-X-US (240V) 2 Enphase Energy IQ6-60-X-US (240V) | 2017-12-06 | 2017-12-06 | 0 | 2017-12-06 | [14 empty] | 2018-02-01 | 2018-02-01 |  | Y
Central Hudson |  | Natural Energy Solutions | CH-10189 | Poughkeepsie | Milan | Dutchess | 12571 | G | 7062 | Milan | N |  |  |  | 2.4 | [11 empty] | NM | N | (1) Skystream 3.7 - Inverter Rating (kW) 2.4Skystream 3.7Skystream 3.7 | 2018-01-31 | 2018-01-31 | 0 | 2018-01-31 | [14 empty] | 2020-10-05 | 2020-10-05 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-10190 | Fishkill | Beacon | Dutchess | 12508 | G | 8087 | Tioronda | N |  | 4.4 | [13 empty] | NM | N | 19 Enphase Energy IQ6-60-X-US (240V) | 2017-12-05 | 2017-12-06 | 1 | 2017-12-06 | [14 empty] | 2018-02-26 | 2018-02-26 |  | Y
Central Hudson |  | New York State Solar Farm | CH-10192 | Newburgh | Gardiner | Ulster | 12525 | G | 5011 | Modena | N |  | 7.7 | [13 empty] | NM | N | 24 SunPower SPR-E20-327-C-AC (240V) | 2017-12-05 | 2017-12-07 | 2 | 2017-12-07 | [14 empty] | 2018-02-21 | 2018-02-22 |  | Y
Central Hudson |  | Kasselman Solar | CH-10191 | Poughkeepsie | Rhinebeck |  | 12572 | G | 7042 | Staatsburg | TBD |  | 6.4 | [13 empty] | NM | N | 23 Enphase Energy IQ6PLUS-72-X-US (240V) | 2017-12-05 | 2017-12-06 | 1 | 2017-12-06 | [17 empty] | W
Central Hudson |  | Kasselman Solar | CH-10193 | Catskill | Earlton |  | 12058 | G | 1071 | Coxsackie | TBD |  | 6.4 | [13 empty] | NM | N | 23 Enphase Energy IQ6PLUS-72-X-US (240V) | 2017-12-05 | 2017-12-06 | 1 | 2017-12-06 | [17 empty] | W
Central Hudson |  | New York State Solar Farm | CH-10194 | Catskill | Catskill | Greene | 12414 | G | 2001 | North Catskill | N | CH-10194 | 9 | [13 empty] | NM | N | 28 SunPower SPR-E20-327-C-AC (240V) | 2017-12-07 | 2017-12-14 | 5 | 2017-12-14 | [14 empty] | 2018-02-26 | 2018-03-01 |  | Y
Central Hudson |  | SunBlue Energy | CH-10195 | Fishkill | Garrison | Putnam | 10524 | G | 8066 | Merritt Park | N |  | 9.9 | [13 empty] | NM | N | 1 SolarEdge Technologies SE 10000A-US (240V) | 2017-12-07 | 2017-12-07 | 0 | 2017-12-07 | [14 empty] | 2018-02-02 | 2018-02-07 |  | Y
Central Hudson |  | New York State Solar Farm | CH-10196 | Kingston | High Fls | Ulster | 12440 | G | 3024 | High Falls | N |  | 5.1 | [13 empty] | NM | N | 16 SunPower SPR-X22-360-C-AC (240V) | 2017-12-08 | 2017-12-11 | 1 | 2017-12-11 | [14 empty] | 2018-02-26 | 2018-02-28 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-10200 | Newburgh | Cornwall-Hdsn | Orange | 12520 | G | 4043 | Union Ave | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000 (240V) | 2017-12-12 | 2017-12-12 | 0 | 2017-12-12 | [14 empty] | 2017-12-12 | 2017-12-14 |  | Y
Central Hudson |  | SolarCity DBA Tesla | CH-10204 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7013 | Hibernia | N |  | 7.6 | [13 empty] | NM | N | 1 Delta Electronics SOLIVIA 7.6 NA G4 TL (240V) [SI1] | 2017-12-12 | 2017-12-13 | 1 | 2017-12-13 | [14 empty] | 2018-01-02 | 2018-02-27 |  | Y |  | 1/19/18 - CH rep unable to install net meter due to unsafe conditions. Customer to make repairs, then call for net meter install. 2/21/18 - Customer advised repairs are complete; net meter was installed.
Central Hudson |  | SolarCity DBA Tesla | CH-10202 | Newburgh | Newburgh | Orange | 12550 | G | 5041 | East Walden | N |  | 10.4 | [13 empty] | NM | N | 1 Delta Electronics SOLIVIA 6.6 NA G4 TL (240V) [SI1] 1 Delta Electronics SOLIVIA 3.8 NA G4 TL (240V) [SI1] | 2017-12-13 | 2017-12-14 | 1 | 2017-12-14 | [8 empty] | 350 | 350 |  | 2018-02-13 | 2018-02-13 | 2018-03-01 | 2018-03-01 | 2018-03-01 |  | Y
Central Hudson |  | SunDog Solar | CH-10203 | Poughkeepsie | Ancram | Columbia | 12502 | G | 7085 | Ancram | N |  | 4.6 | [13 empty] | NM | N | 20 Enphase Energy IQ6-60-x-US (240V) [SI1] | 2018-01-24 | 2018-01-26 | 2 | 2018-01-26 | [14 empty] | 2018-07-31 | 2018-08-24 |  | Y |  | 8/1/18 - CH Rep unable to install net meter; appointment required. Scheduled appt & installed meter on 8/23/18.
Central Hudson |  | New York State Solar Farm | CH-10198 | Newburgh | Wallkill | Ulster | 12589 | G | 5033 | Galeville | N |  | 5.1 | [13 empty] | NM | N | 16 SunPower SPR-E20-327-D-AC (208V) | 2017-12-12 | 2017-12-12 | 0 | 2017-12-12 | [14 empty] | 2018-03-12 | 2018-03-13 |  | Y
Central Hudson |  | Vanguard Energy/Sol Providers | CH-10201 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 6092 | Manchester | N |  | 20 | [13 empty] | NM | N | 2SolaredgeSE 10000A-US (240V) | 2017-12-12 | 2017-12-12 | 0 | 2017-12-12 | [14 empty] | 2017-12-21 | 2018-01-02 |  | Y
Central Hudson |  | Kasselman Solar | CH-10199 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 7011 | Hibernia | N |  | 7.6 | [13 empty] | NM | N | 27 Enphase Energy IQ6PLUS-72-X-US (240V) | 2017-12-12 | 2017-12-12 | 0 | 2017-12-12 | [14 empty] | 2018-01-23 | 2018-01-24 |  | Y
Central Hudson |  | SunDog Solar | CH-10205 | Kingston | Kingston | Ulster | 12401 | G | 3021 | High Falls | N |  | 5.6 | [13 empty] | NM | N | 20 Enphase Energy IQ6PLUS-72-x-US (240V) [SI1] | 2018-01-24 | 2018-01-26 | 2 | 2018-01-26 | [14 empty] | 2018-03-21 | 2018-03-22 |  | Y
Central Hudson |  | Sunrun Inc. | CH-10206 | Fishkill | Hopewell Jct |  | 12533 | G | 8094 | Fishkill Plains | TBD |  | 6 | [13 empty] | NM | N | 1 ABB PVI-6000-OUTD-US-A (240V) | 2017-12-14 | 2017-12-14 | 0 | 2017-12-14 | [17 empty] | W
Central Hudson |  | New York State Solar Farm | CH-10207 | Fishkill | Stormvl | Dutchess | 12582 | G | 8093 | Fishkill Plains | N |  | 15.4 | [13 empty] | NM | N | 48 SunPower SPR-X22-360-C-AC (240V) | 2017-12-14 | 2017-12-14 | 0 | 2017-12-14 | [14 empty] | 2018-02-20 | 2018-02-20 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-10210 | Newburgh | Newburgh | Orange | 12550 | G | 4012 | West Balmville | N |  | 3.4 | [13 empty] | NM | N | 15 Enphase Energy IQ6-60-X-US (240V) | 2017-12-15 | 2017-12-18 | 1 | 2017-12-18 | [14 empty] | 2018-02-26 | 2018-03-15 |  | Y |  | Storm Restoration due to 3/2/18 Heavy Wet Snow and Damaging Wind Storm.
Central Hudson |  | Infinity Solar Systems | CH-10208 | Newburgh | Newburgh | Orange | 12550 | G | 4024 | Coldenham | N |  | 7 | [13 empty] | NM | N | 22 SunPower SPR-X22-360-C-AC (240V) | 2017-12-15 | 2017-12-18 | 1 | 2017-12-18 | [14 empty] | 2018-01-29 | 2018-01-29 |  | Y
Central Hudson |  | Lotus Energy Inc. | CH-10209 | Fishkill | Beacon | Dutchess | 12508 | G | 8015 | Forgebrook | N |  | 9.6 | [13 empty] | NM | N | 30 SunPower SPR-E20-327-D-AC (240V) | 2017-12-15 | 2017-12-18 | 1 | 2017-12-18 | [14 empty] | 2018-01-22 | 2018-01-25 |  | Y
Central Hudson |  | Hudson Solar | CH-10211 | Kingston | Stone Ridge | Ulster | 12484 | G | 3023 | High Falls | N |  | 6.4 | [13 empty] | NM | N | 20 SunPower SPR-E20-327-D-AC (240V) | 2017-12-18 | 2017-12-18 | 0 | 2017-12-18 | [14 empty] | 2017-12-27 | 2017-12-29 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-10213 | Kingston | Kingston |  | 12401 | G | 3023 | High Falls | TBD |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600A-US (240V) | 2017-12-18 | 2017-12-18 | 0 | 2017-12-18 | [17 empty] | W
Central Hudson |  | Hudson Solar | CH-10212 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7062 | Milan | N | CH-01863 | 1.9 | [13 empty] | NM | N | 8 SunPower SPR-X20-250-BLK-B-AC (240V) | 2017-12-18 | 2017-12-18 | 0 | 2017-12-18 | [8 empty] | 350 | 350 |  | 2018-01-12 | 2018-01-12 | 2018-01-23 | 2018-02-06 | 2018-02-07 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-10215 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000 (240V) | 2017-12-19 | 2017-12-19 | 0 | 2017-12-19 | [14 empty] | 2018-01-19 | 2018-01-19 |  | Y
Central Hudson |  | Seed Solar | CH-10214 | Kingston | Hurley | Ulster | 12443 | G | 2094 | Hurley Ave | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US | 2017-12-19 | 2017-12-19 | 0 | 2017-12-19 | [14 empty] | 2018-01-15 | 2018-01-19 |  | Y
Central Hudson |  | New York State Solar Farm | CH-10217 | Fishkill | Cold Spg | Putnam | 10516 | G | 8063 | Merritt Park | N |  | 6.7 | [13 empty] | NM | N | 21 SunPower SPR-E20-327-D-AC (240V) | 2017-12-19 | 2017-12-19 | 0 | 2017-12-19 | [14 empty] | 2018-03-23 | 2018-03-26 |  | Y
Central Hudson |  | SolarCity DBA Tesla | CH-10216 | Kingston | Kingston | Ulster | 12401 | G | 2013 | Lincoln Park | N |  | 4.2 | [13 empty] | NM | N | 1 ABB PVI-4.2-OUTD-S-US-Z-A (240V) | 2017-12-19 | 2017-12-19 | 0 | 2017-12-19 | [14 empty] | 2018-01-09 | 2018-01-19 |  | Y
Central Hudson |  | Tri-State Solar Services | CH-10218 | Newburgh | Wallkill | Ulster | 12589 | G | 5033 | Galeville | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000 (240V) | 2017-12-20 | 2017-12-20 | 0 | 2017-12-20 | [14 empty] | 2018-03-19 | 2018-03-20 |  | Y
Central Hudson |  | Tri-State Solar Services | CH-10219 | Newburgh | Marlboro | Ulster | 12542 | G | 5003 | Marlboro | N |  | 9.9 | [13 empty] | NM | N | 1 SolarEdge Technologies SE 10000A-US (240V) | 2017-12-20 | 2017-12-20 | 0 | 2017-12-20 | [8 empty] | 350 | 350 |  | 2018-05-14 | 2018-05-14 | 2018-06-15 | 2018-06-22 | 2018-06-22 |  | Y
Central Hudson |  | STR Systems NY LLC | CH-10220 | Poughkeepsie | Poughkeepsie |  | 12601 | G | 6065 | Inwood Ave | N |  | 5.2 | [13 empty] | RNM | N | 1 Solectria Renewables PVI 5200TL (240V) | 2017-12-26 | 2018-01-02 | 4 | 2018-01-02 | [17 empty] | W
Central Hudson |  | New York State Solar Farm | CH-10221 | Kingston | Accord | Ulster | 12404 | G | 3024 | High Falls | N |  | 6.4 | [13 empty] | NM | N | 20 SunPower SPR-X22-360-D-AC (240V) [SI1] | 2017-12-26 | 2017-12-26 | 0 | 2017-12-26 | [14 empty] | 2018-03-13 | 2018-03-14 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-10223 | Newburgh | Walden | Orange | 12586 | G | 5043 | East Walden | N |  | 3.7 | [13 empty] | NM | N | 16 Enphase Energy IQ6-60-X-US (240V) | 2017-12-26 | 2017-12-26 | 0 | 2017-12-26 | [14 empty] | 2018-07-05 | 2018-07-05 |  | Y
Central Hudson |  | Kasselman Solar | CH-10222 | Kingston | Kingston | Ulster | 12401 | G | 1022 | East Kingston | N |  | 6.4 | [13 empty] | NM | N | 28 Enphase Energy IQ6-60-X-US (240V) | 2017-12-26 | 2017-12-26 | 0 | 2017-12-26 | [14 empty] | 2018-03-12 | 2018-03-14 |  | Y
Central Hudson |  | Trinity Solar | CH-10224 | Kingston | Kingston | Ulster | 12401 | G | 1021 | East Kingston | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US | 2017-12-28 | 2017-12-29 | 1 | 2017-12-29 | [14 empty] | 2018-01-22 | 2018-01-24 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-10225 | Newburgh | New Windsor | Orange | 12553 | G | 4095 | Bethlehem Rd | N |  | 8 | [13 empty] | NM | N | 25 SunPower SPR-X22-360-C-AC (240V) | 2018-01-10 | 2018-01-11 | 1 | 2018-01-11 | [14 empty] | 2018-03-06 | 2018-03-13 |  | Y
Central Hudson |  | Lighthouse Solar | CH-10226 | Kingston | Kingston | Ulster | 12401 | G | 3023 | High Falls | N |  | 9.9 | [13 empty] | NM | N | 1 SolarEdge Technologies SE 10000A-US (240V) | 2017-12-28 | 2018-01-04 | 4 | 2018-01-04 | [14 empty] | 2018-02-27 | 2018-03-01 |  | Y
Central Hudson |  | Matrix Development LLC | CH-10229 | Newburgh | Rock Tavern |  | 12575 | G | 4026 | Coldenham | TBD |  | 1980 | [13 empty] | CDG | N | 55 Huawei Technologies SUN2000-36KTL-US | 2018-02-15 | 2018-02-27 | 7 | 2018-02-27 | 2018-02-27 | 2018-03-20 | 15 | 2018-04-30 |  |  |  | 12000 | [9 empty] | W |  | There are 4 accounts at this location with an aggregate CESIR Cost to Customer of $48,000.
Central Hudson |  | Matrix Development LLC | CH-10228 | Newburgh | Rock Tavern |  | 12575 | G | 4026 | Coldenham | TBD |  | 1980 | [13 empty] | CDG | N | 55 Huawei Technologies SUN2000-36KTL-US | 2018-02-15 | 2018-02-27 | 7 | 2018-02-27 | 2018-02-27 | 2018-03-20 | 15 | 2018-04-30 |  |  |  | 12000 | [9 empty] | W |  | There are 4 accounts at this location with an aggregate CESIR Cost to Customer of $48,000.
Central Hudson |  | Borrego Solar Systems, Inc. | CH-10227 | Newburgh | Rock Tavern | Orange | 12575 | G | 4026 | Coldenham | N |  | 4950 | [13 empty] | CDG | Y | 33 SMA America SHP 150-US-20 (600V) | 2018-02-15 | 2018-02-27 | 7 | 2018-02-27 | 2018-02-27 | 2018-03-20 | 15 | 2018-04-30 | 2018-09-10 | 2018-12-05 | 60 | 24067.93 | 218615 | 201478.25 | 2019-01-28 | 2019-05-15 | 2019-05-15 | 2021-11-17 | 2021-12-27 | 2021-12-30 | 2022-03-31 | Y | Y | There are 4 accounts at this location with an aggregate CESIR Cost to Customer of $48,000.
Central Hudson |  | PlugPV, LLC. | CH-10231 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8096 | Fishkill Plains | N |  | 9.9 | [13 empty] | NM | N | 1 SolarEdge Technologies SE 10000A-US (240V) | 2018-01-04 | 2018-01-09 | 3 | 2018-01-09 | [14 empty] | 2018-02-28 | 2018-03-07 |  | Y
Central Hudson |  | Lighthouse Solar | CH-10230 | Kingston | W Shokan | Ulster | 12494 | G | 3011 | Woodstock | N |  | 15.2 | [13 empty] | NM | N | 2 SolarEdge Technologies SE7600H-US | 2018-01-03 | 2018-01-04 | 1 | 2018-01-04 | [8 empty] | 350 | 350 |  | 2018-01-12 | 2018-01-12 | 2018-04-10 | 2018-04-12 | 2018-04-12 |  | Y
Central Hudson |  | Sunrun Inc. | CH-10232 | Fishkill | Beacon | Dutchess | 12508 | G | 8085 | Tioronda | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US | 2018-01-09 | 2018-01-10 | 1 | 2018-01-10 | [14 empty] | 2018-02-02 | 2018-02-05 |  | Y
Central Hudson |  | SolarCity DBA Tesla | CH-10233 | Catskill | Athens | Greene | 12015 | G | 1074 | Coxsackie | N |  | 7.6 | [13 empty] | NM | N | 1 Delta Electronics SOLIVIA 7.6 NA G4 TL (240V) [SI1] | 2018-01-05 | 2018-01-09 | 2 | 2018-01-09 | [14 empty] | 2018-01-18 | 2018-01-24 |  | Y
Central Hudson |  | Sunrun Inc. | CH-10234 | Newburgh | Rock Tvrn | Orange | 12575 | G | 4097 | Bethlehem Rd | N | CH-10234 | 12.6 | [13 empty] | NM | N | 1SolaredgeSE7600H-US1SolaredgeSE5000H-US (240V) | 2018-01-09 | 2018-01-10 | 1 | 2018-01-10 | [8 empty] | 350 | 350 |  | 2018-01-29 | 2018-01-29 | 2018-02-06 | 2018-02-07 | 2018-02-07 |  | Y
Central Hudson |  | SolarCity DBA Tesla | CH-10235 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 3 | [13 empty] | NM | N | 1 ABB PVI-3.0-OUTD-S-US-A (240V) | 2018-01-09 | 2018-01-11 | 2 | 2018-01-11 | [14 empty] | 2018-02-02 | 2018-02-05 |  | Y
Central Hudson |  | SolarCity DBA Tesla | CH-10237 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8092 | Fishkill Plains | Y |  | 11.4 | 5 | [12 empty] | NM | N | 1 Delta Electronics SOLIVIA 3.8 NA G4 TL (240V) [SI1] 1 Delta Electronics SOLIVIA 7.6 NA G4 TL (240V) [SI1] 1TeslaAC Powerwall 2.0 | 2018-01-10 | 2018-01-11 | 1 | 2018-01-11 | [14 empty] | 2018-02-15 | 2018-02-15 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-10236 | Newburgh | New Windsor | Orange | 12553 | G | 4094 | Bethlehem Rd | N |  | 13.4 | [13 empty] | NM | N | 42 SunPower SPR-X22-360-C-AC (240V) | 2018-01-10 | 2018-01-11 | 1 | 2018-01-11 | [14 empty] | 2018-03-19 | 2018-03-26 |  | Y
Central Hudson |  | Hudson Solar | CH-10238 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6043 | Spackenkill | N |  | 9 | [13 empty] | NM | N | 28 SunPower SPR-E20-327-D-AC (240V) | 2018-01-11 | 2018-01-11 | 0 | 2018-01-11 | [14 empty] | 2018-03-08 | 2018-03-08 |  | Y
Central Hudson |  | SolarCity DBA Tesla | CH-10242 | Kingston | Napanoch | Ulster | 12458 | G | 3091 | Neversink | N |  | 7.6 | [13 empty] | NM | N | 1 Delta Electronics SOLIVIA 7.6 NA G4 TL (240V) | 2018-01-19 | 2018-01-19 | 0 | 2018-01-19 | [14 empty] | 2018-02-06 | 2018-02-23 |  | Y
Central Hudson |  | SolarCity DBA Tesla | CH-10240 | Kingston | Accord | Ulster | 12404 | G | 3082 | Kerhonkson | N |  | 15.2 | [13 empty] | NM | N | 2 Delta Electronics SOLIVIA 7.6 NA G4 TL (240V) | 2018-01-12 | 2018-01-12 | 0 | 2018-01-12 | [8 empty] | 350 | 350 |  | 2018-02-13 | 2018-02-13 | 2018-05-15 | 2018-05-25 | 2018-05-29 |  | Y
Central Hudson |  | Hudson Solar | CH-10239 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7053 | Rhinebeck | N |  | 43.2 | [13 empty] | NM | Y | 3SolaredgeSE14.4KUS | 2018-01-26 | 2018-02-08 | 9 | 2018-02-08 | [14 empty] | 2019-01-04 | 2019-01-04 |  | Y | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-10241 | Poughkeepsie | Hyde Pk |  | 12538 | G | 6074 | East Park | TBD |  | 9 | [13 empty] | NM | N | 21 Enphase Energy IQ6-60-X-US (240V) 18 Enphase Energy IQ6-60-X-US (240V) | 2018-03-13 | 2018-03-15 | 2 | 2018-03-15 | [11 empty] | 2018-06-01 | 2018-06-01 |  |  |  |  | W
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-10244 | Newburgh | Campbell Hall | Orange | 10916 | G | 5052 | Maybrook | N |  | 13.3 | [13 empty] | NM | N | 58 Enphase Energy IQ6-60-X-US (240V) | 2018-01-15 | 2018-01-16 | 1 | 2018-01-16 | [14 empty] | 2018-03-20 | 2018-03-22 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-10245 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 7024 | Tinkertown | N |  | 8.3 | [13 empty] | NM | N | 13 Enphase Energy IQ6-60-X-US (240V) 11 Enphase Energy IQ6-60-X-US (240V) 12 Enphase Energy IQ6-60-X-US (240V) | 2018-01-15 | 2018-01-16 | 1 | 2018-01-16 | [14 empty] | 2018-05-08 | 2018-05-09 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-10246 | Newburgh | Mountainvl | Orange | 10953 | G | 4093 | Bethlehem Rd | N |  | 4.4 | [13 empty] | NM | N | 6 Enphase Energy IQ6-60-X-US (240V) 3 Enphase Energy IQ6-60-X-US (240V) 8 Enphase Energy IQ6-60-X-US (240V) 2 Enphase Energy IQ6-60-X-US (240V) | 2018-01-15 | 2018-01-16 | 1 | 2018-01-16 | [14 empty] | 2018-08-01 | 2018-08-02 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-10243 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 6073 | East Park | N |  | 10.4 | [13 empty] | NM | N | 10 Enphase Energy IQ6-60-X-US (240V) 6 Enphase Energy IQ6-60-X-US (240V) 4 Enphase Energy IQ6-60-X-US (240V) 6 Enphase Energy IQ6-60-X-US (240V) 4 Enphase Energy IQ6-60-X-US (240V) 7 Enphase Energy IQ6-60-X-US (240V) 5 Enphase Energy IQ6-60-X-US (240V) 3 Enphase Energy IQ6-60-X-US (240V) | 2018-01-16 | 2018-01-16 | 0 | 2018-01-16 | [14 empty] | 2018-05-11 | 2018-05-22 |  | Y
Central Hudson |  | Hudson Solar | CH-10247 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7051 | Rhinebeck | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE 10000A-US (277V) | 2018-01-16 | 2018-01-30 | 10 | 2018-01-30 | [14 empty] | 2018-03-20 | 2018-04-10 |  | Y
Central Hudson |  | Hudson Solar | CH-10248 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6092 | Manchester | N |  | 6.7 | [13 empty] | NM | N | 21 SunPower SPR-X21-345-C-AC (240V) | 2018-01-19 | 2018-01-19 | 0 | 2018-01-19 | [14 empty] | 2018-03-08 | 2018-03-19 |  | Y
Central Hudson |  | SolarCity DBA Tesla | CH-10250 | Newburgh | Marlboro | Ulster | 12542 | G | 5004 | Marlboro | N |  | 6 | [13 empty] | NM | N | 1 ABB PVI-6000-OUTD-US-Z-A (240V) | 2018-01-18 | 2018-01-18 | 0 | 2018-01-18 | [14 empty] | 2018-03-12 | 2018-03-14 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-10249 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6092 | Manchester | N |  | 11.5 | [13 empty] | NM | N | 36 SunPower SPR-X22-360-C-AC (240V) | 2018-01-17 | 2018-01-18 | 1 | 2018-01-18 | [14 empty] | 2018-03-27 | 2018-03-29 |  | Y
Central Hudson |  | New York State Solar Farm | CH-10255 | Newburgh | Newburgh | Orange | 12550 | G | 4052 | Union Ave | N |  | 8.3 | [13 empty] | NM | N | 26 SunPower SPR-X21-345-D-AC (240V) | 2018-01-18 | 2018-01-19 | 1 | 2018-01-19 | [14 empty] | 2018-03-12 | 2018-03-14 |  | Y
Central Hudson |  | Solar Generation | CH-10253 | Kingston | Woodstock | Ulster | 12498 | G | 2016 | Lincoln Park | N | CH-10253 | 4.5 | [13 empty] | NM | N | 14 SunPower SPR-X22-360-C-AC (240V) | 2018-01-18 | 2018-01-19 | 1 | 2018-01-19 | [14 empty] | 2018-03-05 | 2018-03-05 |  | Y
Central Hudson |  | SolarCity DBA Tesla | CH-10254 | Kingston | Kingston | Ulster | 12401 | G | 3023 | High Falls | Y |  | 3.6 | 5 | [12 empty] | NM | N | 1 ABB PVI-3.6-OUTD-S-US-Z-A (240V) [SI1] 1TeslaAC Powerwall 2.0 | 2018-01-24 | 2018-01-24 | 0 | 2018-01-24 | [14 empty] | 2018-09-12 | 2018-09-24 |  | Y
Central Hudson |  | Hudson Solar | CH-10252 | Poughkeepsie | Tivoli | Dutchess | 12583 | G | 7062 | Milan | N | CH-23086 | 5.44 | [13 empty] | NM | N | 17 SunPower SPR-E20-327-D-AC (240V) [SI1] | 2018-01-18 | 2018-01-19 | 1 | 2018-01-19 | [14 empty] | 2018-03-06 | 2018-03-06 |  | Y
Central Hudson |  | Hudson Solar | CH-10251 | Poughkeepsie | Pine Plns |  | 12567 | G | 7091 | Pulvers Corners | N | CH-10251 | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600A-US (240V) | 2018-01-19 | 2018-01-19 | 0 | 2018-01-19 | [14 empty] | 2018-04-10 | 2018-04-12 |  | W
Central Hudson |  | Kasselman Solar | CH-10256 | Catskill | Catskill | Greene | 12414 | G | 2005 | North Catskill | N | CH-03513 | 1.2 | [13 empty] | NM | N | 5 Enphase Energy IQ6-60-X-US (240V) | 2018-01-19 | 2018-01-19 | 0 | 2018-01-19 | [14 empty] | 2018-02-20 | 2018-02-22 |  | Y
Central Hudson |  | Solar Generation | CH-10258 | Kingston | Kerhonkson | Ulster | 12446 | G | 3083 | Kerhonkson | N |  | 15.2 | [13 empty] | NM | N | 2 SolarEdge Technologies SE7600A-US (240V) | 2018-01-22 | 2018-01-26 | 4 | 2018-01-26 | [8 empty] | 350 | 350 |  | 2018-02-06 | 2018-02-06 | 2018-02-12 | 2018-02-12 | 2018-02-16 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-10257 | Kingston | Malden-Hdsn | Ulster | 12453 | G | 3004 | Saugerties | N |  | 13.3 | [13 empty] | NM | N | 15 Enphase Energy IQ6-60-X-US (240V) 21 Enphase Energy IQ6-60-X-US (240V) 10 Enphase Energy IQ6-60-X-US (240V) 12 Enphase Energy IQ6-60-X-US (240V) | 2018-01-22 | 2018-01-22 | 0 | 2018-01-22 | [14 empty] | 2018-07-05 | 2018-07-05 |  | Y
Central Hudson |  | Lighthouse Solar | CH-10259 | Kingston | Kingston | Ulster | 12401 | G | 1003 | Jansen Ave | N |  | 40 | [13 empty] | NM | N | 2SolaredgeSE-20KUS | 2018-06-21 | 2018-06-26 | 3 | 2018-06-26 | [14 empty] | 2018-08-23 | 2018-08-24 |  | Y
Central Hudson |  | SolarCity DBA Tesla | CH-10261 | Newburgh | Maybrook | Orange | 12543 | G | 5052 | Maybrook | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600A-US (240V) | 2018-01-30 | 2018-02-02 | 3 | 2018-02-02 | [14 empty] | 2018-02-09 | 2018-02-12 |  | Y
Central Hudson |  | Hudson Solar | CH-10260 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7053 | Rhinebeck | N |  | 21.4 | [13 empty] | NM | N | 67 SunPower SPR-E20-327-D-AC (240V) | 2018-01-24 | 2018-01-24 | 0 | 2018-01-24 | [14 empty] | 2018-06-27 | 2018-06-28 |  | Y
Central Hudson |  | Solar Generation | CH-10263 | Kingston | Kingston | Ulster | 12401 | G | 1022 | East Kingston | N |  | 5 | [13 empty] | NM | N | 1SolaredgeSE5000H-US (240V) | 2018-01-26 | 2018-01-26 | 0 | 2018-01-26 | [14 empty] | 2018-03-09 | 2018-03-13 |  | Y
Central Hudson |  | New York State Solar Farm | CH-10262 | Newburgh | New Paltz | Ulster | 12561 | G | 5031 | Galeville | N |  | 10.2 | [13 empty] | NM | N | 32 SunPower SPR-X21-345-D-AC (240V) | 2018-01-25 | 2018-01-26 | 1 | 2018-01-26 | [14 empty] | 2018-03-23 | 2018-04-10 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-10264 | Kingston | Olive Brdg | Ulster | 12461 | G | 3024 | High Falls | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600A-US (240V) | 2018-03-19 | 2018-03-26 | 5 | 2018-03-26 | [14 empty] | 2018-03-28 | 2018-04-02 |  | Y
Central Hudson |  | Hudson Solar | CH-10265 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7054 | Rhinebeck | N |  | 5.8 | [13 empty] | NM | N | 18 SunPower SPR-E20-327-D-AC (240V) | 2018-01-29 | 2018-01-29 | 0 | 2018-01-29 | [14 empty] | 2018-02-28 | 2018-02-28 |  | Y
Central Hudson |  | Hudson Solar | CH-10266 | Newburgh | Newburgh | Orange | 12550 | G | 5001 | Marlboro | N |  | 9.6 | [13 empty] | NM | N | 30 SunPower SPR-E20-327-D-AC (240V) | 2018-01-30 | 2018-02-05 | 4 | 2018-02-05 | [14 empty] | 2018-03-06 | 2018-04-05 |  | Y
Central Hudson |  | Sunrun Inc. | CH-10267 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8043 | Myers Corners | N |  | 11 | [13 empty] | NM | N | 1 ABB PVI-6000-OUTD-US-A (240V) 1 ABB PVI-5000-OUTD-US-A (240V) | 2018-01-26 | 2018-01-29 | 1 | 2018-01-29 | [8 empty] | 350 | 350 |  | 2018-02-01 | 2018-02-01 | 2018-02-05 | 2018-03-19 | 2018-03-20 |  | Y
Central Hudson |  | SolarCity | CH-07808 | Kingston | High Fls | Ulster | 12440 | G | 3024 | High Falls | N | CH-05649 | 6 | [13 empty] | NM | N | 2 SolarEdge Technologies SE3000 (240V) | 2018-02-09 | 2018-02-09 | 0 | 2018-02-09 | [14 empty] | 2018-02-20 | 2018-02-22 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-10270 | Fishkill | Hopewell Junction | Dutchess | 12533 | G | 8072 | Shenandoah | N |  | 7.1 | [13 empty] | NM | N | 6 Enphase Energy IQ6-60-X-US (240V) 16 Enphase Energy IQ6-60-X-US (240V) 9 Enphase Energy IQ6-60-X-US (240V) | 2018-01-29 | 2018-01-29 | 0 | 2018-01-29 | [14 empty] | 2018-04-26 | 2018-04-27 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-10278 | Newburgh | Newburgh |  | 12550 | G | 4054 | Union Ave | N |  | 6.1 | [13 empty] | NM | N | 19 SunPower SPR-X22-360-C-AC (240V) | 2018-01-30 | 2018-02-01 | 2 | 2018-02-01 | [17 empty] | W
Central Hudson |  | Wiltshire Renewable Energy Systems | CH-10277 | Kingston | Cementon | Greene | 12414 | G | 3002 | Saugerties | N |  | 6 | [13 empty] | NM | N | 1 SMA America SB6.0-1SP-US-40 (240V) | 2018-02-13 | 2018-02-13 | 0 | 2018-02-13 | [14 empty] | 2018-04-23 | 2018-04-23 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-10269 | Fishkill | Beacon | Dutchess | 12508 | G | 8085 | Tioronda | N |  | 8.3 | [13 empty] | NM | N | 26 SunPower SPR-X22-360-C-AC (240V) | 2018-01-29 | 2018-01-29 | 0 | 2018-01-29 | [14 empty] | 2018-05-04 | 2018-05-04 |  | Y
Central Hudson |  | Solar Generation | CH-10268 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7062 | Milan | N |  | 7.7 | [13 empty] | NM | N | 24 SunPower SPR-X22-360-D-AC (240V) | 2018-01-29 | 2018-02-01 | 3 | 2018-02-01 | [14 empty] | 2018-03-05 | 2018-03-06 |  | Y
Central Hudson |  | Independent Solar (Cypress Creek Renewables, LLC) | CH-10272 | Newburgh | Milton |  | 12547 | G | 5083 | Highland | Y |  | 3000 | 3000 | [12 empty] | CDG | Y | 1Power ElectronicsFS3001k1Power ElectronicsFS3001K | 2019-03-13 | 2019-03-27 | 10 | 2019-03-27 | 2019-03-27 | 2019-04-17 | 15 | 2019-06-18 | 2019-09-03 | 2019-11-25 | 59 | 12820.25 | 281642.5 |  | 2020-04-07 | [5 empty] | 2020-12-16 | W | Y
Central Hudson |  | Cypress Creek Renewables | CH-10273 | Catskill | Greenville |  | 12083 | G | 1091 | Westerlo | TBD |  | 2000 | [13 empty] | CDG | N | 1Power ElectronicsFS2001K | 2019-04-23 | 2019-05-03 | 8 | 2019-05-03 | 2019-05-03 | 2019-05-23 | 14 |  |  |  |  | 17500 | [9 empty] | W
Central Hudson |  | Kowalski Solar (Cypress Creek Renewables, LLC) | CH-10275 | Catskill | Cairo |  | 12413 | G | 2042 | South Cairo | TBD |  | 5000 | [13 empty] | CDG | N | 2 SMA America SC 2500-EV-US (550V) [SI1] | 2018-06-22 | 2018-06-26 | 2 | 2018-06-26 | 2018-06-26 | 2018-07-18 | 15 | [14 empty] | W
Central Hudson |  | SolarCity DBA Tesla | CH-10281 | Kingston | Saugerties | Ulster | 12477 | G | 3001 | Saugerties | N |  | 6.6 | [13 empty] | NM | N | 1 Delta Electronics SOLIVIA 6.6 NA G4 TL (240V) [SI1] | 2018-01-30 | 2018-02-02 | 3 | 2018-02-02 | [14 empty] | 2018-02-05 | 2018-02-07 |  | Y
Central Hudson |  | SolarCity DBA Tesla | CH-10280 | Poughkeepsie | Tivoli | Dutchess | 12583 | G | 7062 | Milan | Y |  | 3.3 | 5 | [12 empty] | NM | N | 1 ABB UNO-DM-3.3-TL-PLUS-US-SZ-RA (240V) [SI1] 1TeslaAC Powerwall 2.0 | 2018-01-30 | 2018-02-02 | 3 | 2018-02-02 | [14 empty] | 2018-08-03 | 2018-08-08 |  | Y
Central Hudson |  | SolarCity DBA Tesla | CH-10279 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 6073 | East Park | Y | CH-05847 |  | 15 | [12 empty] | NM | N | 3TeslaAC Powerwall 2.0 | 2018-01-30 | 2018-02-01 | 2 | 2018-02-01 | [14 empty] | 2018-03-13 | 2018-03-13 |  | Y |  | Storm Restoration due to 3/2/18 Heavy Wet Snow and Damaging Wind Storm.
Central Hudson |  | Infinity Solar Systems | CH-10282 | Newburgh | New Windsor |  | 12553 | G | 4095 | Bethlehem Rd | N |  | 12.8 | [13 empty] | NM | N | 40 SunPower SPR-X22-360-C-AC (240V) | 2018-01-31 | 2018-02-02 | 2 | 2018-02-02 | [17 empty] | W
Central Hudson |  | Infinity Solar Systems | CH-10283 | Newburgh | Cornwall | Orange | 12518 | G | 4093 | Bethlehem Rd | N |  | 8 | [13 empty] | NM | N | 25 SunPower SPR-X22-360-C-AC (240V) | 2018-02-07 | 2018-02-07 | 0 | 2018-02-07 | [14 empty] | 2018-03-06 | 2018-03-07 |  | Y
Central Hudson |  | Sunrun Inc. | CH-10284 | Newburgh | Montgomery | Orange | 12549 | G | 5073 | Montgomery | N |  | 8.6 | [13 empty] | NM | N | 1 ABB UNO-8.6-TL-OUTD-S-US-A (240 V) | 2018-02-05 | 2018-02-06 | 1 | 2018-02-06 | [14 empty] | 2018-03-06 | 2018-04-13 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-10285 | Fishkill | Glenham | Dutchess | 12527 | G | 8013 | Forgebrook | N |  | 3.8 | [13 empty] | NM | N | 12 SunPower SPR-X22-360-C-AC (240V) | 2018-02-15 | 2018-02-15 | 0 | 2018-02-15 | [14 empty] | 2018-09-25 | 2018-09-26 |  | Y
Central Hudson |  | Tesla | CH-10294 | Newburgh | Highland | Ulster | 12528 | G | 5081 | Highland | N |  | 6 | [13 empty] | NM | N | 2 ABB PVI-3.0-OUTD-S-US (240 V) | 2018-03-15 | 2018-03-26 | 7 | 2018-03-26 | [14 empty] | 2018-04-02 | 2018-04-06 |  | Y
Central Hudson |  | SolarCity DBA Tesla | CH-10288 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8045 | Myers Corners | N | CH-10288 | 3.6 | [13 empty] | NM | N | 1 ABB PVI-3.6-OUTD-S-US-Z (240 V) | 2018-02-02 | 2018-02-05 | 1 | 2018-02-05 | [14 empty] | 2018-03-07 | 2018-03-07 |  | Y
Central Hudson |  | Tesla | CH-10289 | Kingston | Kingston | Ulster | 12401 | G | 3021 | High Falls | N |  | 3.6 | [13 empty] | NM | N | 1 ABB PVI-3.6-OUTD-US (240 V) | 2018-03-15 | 2018-03-23 | 6 | 2018-03-23 | [14 empty] | 2018-03-23 | 2018-04-10 |  | Y
Central Hudson |  | SolarCity DBA Tesla | CH-10291 | Newburgh | Newburgh | Orange | 12550 | G | 4094 | Bethlehem Rd | N |  | 5.2 | [13 empty] | NM | N | 1 Delta Electronics SOLIVIA 5.2 NA G4 TL (240V) [SI1] | 2018-03-14 | 2018-03-21 | 5 | 2018-03-21 | [14 empty] | 2018-03-21 | 2018-03-22 |  | Y
Central Hudson |  | Tesla | CH-10293 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8046 | Myers Corners | N |  | 3.8 | [13 empty] | NM | N | 1 Delta Electronics SOLIVIA 3.8 NA G4 TL (240V) [SI1] | 2018-02-02 | 2018-02-05 | 1 | 2018-02-05 | [14 empty] | 2018-02-23 | 2018-02-26 |  | Y
Central Hudson |  | SolarCity DBA Tesla | CH-10290 | Fishkill | Beacon | Dutchess | 12508 | G | 8087 | Tioronda | Y |  | 3.6 | 5 | [12 empty] | NM | N | 1 ABB PVI-3.6-OUTD-S-US-Z-M-A (240V) [SI1] 1TeslaAC Powerwall 2.0 | 2018-04-16 | 2018-04-18 | 2 | 2018-04-18 | [14 empty] | 2018-04-26 | 2018-05-02 |  | Y
Central Hudson |  | SolarCity DBA Tesla | CH-10292 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8094 | Fishkill Plains | N |  | 5.2 | [13 empty] | NM | N | 1 Delta Electronics SOLIVIA 5.2 NA G4 TL (240V) [SI1] | 2018-04-10 | 2018-04-16 | 4 | 2018-04-16 | [14 empty] | 2018-04-17 | 2018-04-19 |  | Y
Central Hudson |  | Kasselman Solar | CH-10287 | Kingston | New Paltz | Ulster | 12561 | G | 3022 | High Falls | N |  | 4.6 | [13 empty] | NM | N | 20 Enphase Energy IQ6-60-X-US (240V) | 2018-02-02 | 2018-02-05 | 1 | 2018-02-05 | [14 empty] | 2018-02-28 | 2018-03-13 |  | Y
Central Hudson |  | Tesla | CH-10296 | Kingston | Woodstock | Ulster | 12498 | G | 3014 | Woodstock | N |  | 13.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600A-US (240V) 1 SolarEdge Technologies SE6000 (240V) | 2018-02-05 | 2018-02-06 | 1 | 2018-02-06 | [14 empty] | 2018-05-08 | 2018-05-15 |  | Y
Central Hudson |  | Tesla | CH-10299 | Newburgh | Newburgh | Orange | 12550 | G | 4013 | West Balmville | Y |  | 5 | 5 | [12 empty] | NM | N | 1 ABB PVI-5000-OUTD-US-Z-A (240V) 1TeslaAC Powerwall 2.0 | 2018-02-08 | 2018-02-08 | 0 | 2018-02-08 | [14 empty] | 2018-03-12 | 2018-03-15 |  | Y
Central Hudson |  | Tesla | CH-10300 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8093 | Fishkill Plains | N |  | 4.2 | [13 empty] | NM | N | 1 ABB PVI-4.2-OUTD-S-US-Z-A (240V) [SI1] | 2018-02-08 | 2018-02-08 | 0 | 2018-02-08 | [14 empty] | 2018-02-12 | 2018-02-12 |  | Y
Central Hudson |  | Tesla | CH-10301 | Newburgh | New Windsor | Orange | 12553 | G | 4094 | Bethlehem Rd | N |  | 3.6 | [13 empty] | NM | N | 1 ABB PVI-3.6-OUTD-S-US-Z-A (240V) [SI1] | 2018-03-14 | 2018-03-21 | 5 | 2018-03-21 | [14 empty] | 2018-03-21 | 2018-03-28 |  | Y
Central Hudson |  | Tesla | CH-10304 | Newburgh | New Windsor | Orange | 12553 | G | 4095 | Bethlehem Rd | N |  | 3.6 | [13 empty] | NM | N | 1 ABB PVI-3.6-OUTD-S-US-Z-A (240V) [SI1] | 2018-02-08 | 2018-02-08 | 0 | 2018-02-08 | [14 empty] | 2018-02-16 | 2018-02-28 |  | Y
Central Hudson |  | Tesla | CH-10303 | Newburgh | Maybrook | Orange | 12543 | G | 5052 | Maybrook | N |  | 13.2 | [13 empty] | NM | N | 2 Delta Electronics SOLIVIA 6.6 NA G4 TL (240V) [SI1] | 2018-02-05 | 2018-02-06 | 1 | 2018-02-06 | [14 empty] | 2018-03-12 | 2018-03-14 |  | Y
Central Hudson |  | Tesla | CH-10305 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 6074 | East Park | Y |  | 11.8 | 10 | [12 empty] | NM | N | 1 Delta Electronics SOLIVIA 6.6 NA G4 TL (240V) [SI1] 1 Delta Electronics SOLIVIA 5.2 NA G4 TL (240V) [SI1] 2TeslaAC Powerwall 2.0 | 2018-02-13 | 2018-02-13 | 0 | 2018-02-13 | [14 empty] | 2018-03-23 | 2018-03-26 |  | Y
Central Hudson |  | SolarCity DBA Tesla | CH-10297 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8071 | Shenandoah | N |  | 9 | [13 empty] | NM | N | 1 Delta Electronics SOLIVIA 3.8 NA G4 TL (240V) [SI1] 1 Delta Electronics SOLIVIA 5.2 NA G4 TL (240V) [SI1] | 2018-02-05 | 2018-02-06 | 1 | 2018-02-06 | [14 empty] | 2018-03-23 | 2018-04-06 |  | Y
Central Hudson |  | Tesla | CH-10302 | Newburgh | Newburgh | Orange | 12550 | G | 406 | Montgomery St | N |  | 6.6 | [13 empty] | NM | N | 1 Delta Electronics SOLIVIA 6.6 NA G4 TL (240V) | 2018-04-03 | 2018-04-03 | 0 | 2018-04-03 | [14 empty] | 2018-04-24 | 2018-04-30 |  | Y
Central Hudson |  | Tesla | CH-10298 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7053 | Rhinebeck | N |  | 14.2 | [13 empty] | NM | N | 1 Delta Electronics SOLIVIA 6.6 NA G4 TL (208V) 1 Delta Electronics SOLIVIA 7.6 NA G4 TL (240V) | 2018-02-08 | 2018-02-08 | 0 | 2018-02-08 | [14 empty] | 2018-04-13 | 2018-04-17 |  | Y
Central Hudson |  | Monolith Solar Associates LLC | CH-10295 | Catskill | Coxsackie |  | 12051 | G | 1071 | Coxsackie | TBD |  | 120 | [13 empty] | CDG | Y | 4 SMA America STP30000TL-US-10 | 2018-02-20 | 2018-03-01 | 7 | 2018-03-01 | 2018-03-01 | 2018-03-21 | 14 | [14 empty] | W
Central Hudson |  | SolarCity DBA Tesla | CH-10307 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7062 | Milan | Y | CH-07554 |  | 5 | [12 empty] | NM | N | 1TeslaAC Powerwall 2.0 | 2018-02-15 | 2018-02-23 | 5 | 2018-02-23 | [14 empty] | 2018-10-01 | 2018-10-01 |  | Y
Central Hudson |  | SolarCity DBA Tesla | CH-10306 | Newburgh | Newburgh | Orange | 12550 | G | 4022 | Coldenham | N |  | 20.4 | [13 empty] | NM | N | 2 Delta Electronics SOLIVIA 7.6 NA G4 TL (240V) [SI1] 1 Delta Electronics SOLIVIA 5.2 NA G4 TL (240V) [SI1] | 2018-02-06 | 2018-02-07 | 1 | 2018-02-07 | [8 empty] | 350 | 350 |  | 2018-02-13 | 2018-02-13 | 2018-03-01 | 2018-03-12 | 2018-03-14 |  | Y
Central Hudson |  | SolarCity DBA Tesla | CH-10309 | Catskill | Ravena | Albany | 12143 | G | 1081 | New Baltimore | N |  | 5.2 | [13 empty] | NM | N | 1 Delta Electronics SOLIVIA 5.2 NA G4 TL (240V) | 2018-03-14 | 2018-03-21 | 5 | 2018-03-21 | [14 empty] | 2018-03-21 | 2018-03-28 |  | Y
Central Hudson |  | Sunrun Inc. | CH-10310 | Newburgh | Newburgh | Orange | 12550 | G | 4012 | West Balmville | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US | 2018-02-07 | 2018-02-08 | 1 | 2018-02-08 | [14 empty] | 2018-03-20 | 2018-03-22 |  | Y
Central Hudson |  | Hudson Solar | CH-10311 | Kingston | Kingston | Ulster | 12401 | G | 2091 | Hurley Ave | N | CH-10311 | 366.3 | [13 empty] | CDG | Y | 11 SolarEdge Technologies SE33.3KUS | 2018-02-08 | 2018-02-22 | 9 | 2018-02-22 | 2018-02-22 | 2018-03-12 | 12 | [11 empty] | 2019-02-21 | 2019-02-27 |  | Y | Y
Central Hudson |  | SolarCity | CH-07188 | Catskill | Freehold | Greene | 12431 | G | 2061 | Freehold | Y |  | 5 | 10 | [12 empty] | NM | N | 1 ABB PVI-5000-OUTD-US (240V) 2TeslaAC Powerwall 2.0 | 2018-02-14 | 2018-02-23 | 6 | 2018-02-23 | [8 empty] | 350 | 350 |  | 2018-03-07 | 2018-03-07 | 2018-06-18 | 2018-07-23 | 2018-07-24 |  | Y
Central Hudson |  | New York State Solar Farm | CH-10312 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8092 | Fishkill Plains | N |  | 10.6 | [13 empty] | NM | N | 33 SunPower SPR-E20-327-D-AC (240V) | 2018-02-09 | 2018-02-09 | 0 | 2018-02-09 | [14 empty] | 2018-03-28 | 2018-04-06 |  | Y
Central Hudson |  | SolarCity | CH-07780 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6068 | Inwood Ave | Y | CH-07780 | 6 | 10 | [12 empty] | NM | N | 1 SolarEdge Technologies SE6000 (240V) 2TeslaAC Powerwall 2.0 | 2018-02-14 | 2018-02-23 | 6 | 2018-02-23 | [14 empty] | 2018-03-01 | 2018-03-13 |  | Y |  | Storm Restoration due to 3/2/18 Heavy Wet Snow and Damaging Wind Storm.
Central Hudson |  | Empire State Land Holdings, LLC | CH-08360 | Catskill | Hannacroix | Greene | 12087 | G | 1072 | Coxsackie | N |  | 5000 | [13 empty] | CDG | N | 2 TMEIC PVH-L2500GR | 2018-04-20 | 2018-05-04 | 10 | 2018-05-04 | 2018-05-04 | 2018-05-25 | 15 | 2018-07-16 | 2018-11-19 | 2019-02-19 | 60 | 37100 | 691945 |  | 2019-06-27 | 2019-12-20 | 2019-12-20 |  |  |  |  | N |  | Customer requested to be removed from the Value Stack compensation as they will be participating in the NYISO Market.
Central Hudson |  | SolarCity DBA Tesla | CH-10313 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8096 | Fishkill Plains | Y |  | 5.2 | 5 | [12 empty] | NM | N | 1 Delta Electronics SOLIVIA 5.2 NA G4 TL (240V) 1TeslaAC Powerwall 2.0 | 2018-02-14 | 2018-02-23 | 6 | 2018-02-23 | [14 empty] | 2018-07-26 | 2018-07-30 |  | Y
Central Hudson |  | Kasselman Solar | CH-10314 | Catskill | Hunter | Greene | 12442 | E | 2081 | Hunter | N |  | 6.2 | [13 empty] | NM | N | 27 Enphase Energy IQ6-60-X-US (240V) | 2018-02-12 | 2018-02-12 | 0 | 2018-02-12 | [14 empty] | 2018-03-20 | 2018-03-20 |  | Y
Central Hudson |  | SELF | CH-10315 | Catskill | Cairo | Greene | 12413 | G | 2043 | South Cairo | N |  | 3.8 | [13 empty] | NM | N | 1 ABB PVI-3.8-OUTD-S-US-A (240V) | 2018-02-12 | 2018-02-12 | 0 | 2018-02-12 | [14 empty] | 2018-02-28 | 2018-02-28 |  | Y
Central Hudson |  | American Energy Care | CH-10316 | Catskill | Oak Hill | Greene | 12460 | G | 1092 | Westerlo | N |  | 9.9 | [13 empty] | NM | N | 1 SolarEdge Technologies SE 10000A-US (240V) | 2018-02-13 | 2018-02-13 | 0 | 2018-02-13 | [8 empty] | 350 | 350 |  | 2018-02-26 | 2018-02-26 | 2018-03-20 | 2018-04-02 | 2018-04-04 |  | Y
Central Hudson |  | SolarCity DBA Tesla | CH-10317 | Newburgh | Modena | Ulster | 12548 | G | 5012 | Modena | N |  | 3.6 | [13 empty] | NM | N | 1 ABB PVI-3.6-OUTD-S-US-Z-A (240V) [SI1] | 2018-03-07 | 2018-03-08 | 1 | 2018-03-08 | [14 empty] | 2018-03-08 | 2018-03-16 |  | Y
Central Hudson |  | Sunrun Inc. | CH-10318 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6044 | Spackenkill | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE 10000A-US (277V) | 2018-02-13 | 2018-02-15 | 2 | 2018-02-15 | [14 empty] | 2018-04-12 | 2018-04-12 |  | Y
Central Hudson |  | SolarCity DBA Tesla | CH-10321 | Newburgh | New Windsor | Orange | 12553 | G | 4046 | Union Ave | Y |  | 11.8 | 5 | [12 empty] | NM | N | 1 Delta Electronics SOLIVIA 6.6 NA G4 TL (240V) [SI1] 1 Delta Electronics SOLIVIA 5.2 NA G4 TL (240V) [SI1] 1TeslaAC Powerwall 2.0 | 2018-02-14 | 2018-02-22 | 5 | 2018-02-22 | [14 empty] | 2018-04-02 | 2018-04-03 |  | Y
Central Hudson |  | Hudson Solar | CH-10319 | Catskill | Coxsackie |  | 12051 | G | 1076 | Coxsackie | N | CH-01358 | 10.9 | [13 empty] | RNM | Y | 34 SunPower SPR-X22-360-D-AC (240V) [SI1] | 2018-03-14 | 2018-03-28 | 10 | 2018-03-28 | [8 empty] | 3750 | 2521.54 |  | 2018-04-26 | 2018-04-26 | 2018-06-12 | 2018-06-22 | 2018-06-26 | 2018-07-24 | W | Y
Central Hudson |  | Solar Generation | CH-10323 | Catskill | Tannersville | Greene | 12485 | G | 2385 | Lawrenceville | N |  | 9 | [13 empty] | NM | N | 28 SunPower SPR-X21-335-BLK-C-AC (240V) | 2018-02-15 | 2018-02-23 | 5 | 2018-02-23 | [14 empty] | 2018-05-03 | 2018-05-04 |  | Y
Central Hudson |  | Solar Generation | CH-10324 | Kingston | High Fls | Ulster | 12440 | G | 3022 | High Falls | N |  | 5 | [13 empty] | NM | N | 1 SMA America SB5000TL-US-22 (240V) | 2018-02-15 | 2018-02-26 | 6 | 2018-02-26 | [14 empty] | 2018-04-16 | 2018-04-18 |  | Y
Central Hudson |  | Solar Generation | CH-10322 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7051 | Rhinebeck | N |  | 7.7 | [13 empty] | NM | N | 24 SunPower SPR-X21-335-C-AC (240V) | 2018-03-05 | 2018-03-13 | 6 | 2018-03-13 | [14 empty] | 2018-03-28 | 2018-03-29 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-10330 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8091 | Fishkill Plains | N |  | 19.1 | [13 empty] | NM | N | 41 Enphase Energy IQ6-60-X-US (240V) 42 Enphase Energy IQ6-60-X-US (240V) | 2018-02-20 | 2018-02-28 | 6 | 2018-02-28 | [14 empty] | 2019-03-19 | 2019-03-20 |  | Y
Central Hudson |  | Sunrun Inc. | CH-10326 | Newburgh | Maybrook | Orange | 12543 | G | 5052 | Maybrook | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US | 2018-02-20 | 2018-02-26 | 4 | 2018-02-26 | [14 empty] | 2018-03-20 | 2018-04-06 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-10327 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8072 | Shenandoah | N |  | 12.4 | [13 empty] | NM | N | 24 Enphase Energy IQ6-60-X-US (240V) 10 Enphase Energy IQ6-60-X-US (240V) 20 Enphase Energy IQ6-60-X-US (240V) | 2018-02-20 | 2018-02-26 | 4 | 2018-02-26 | [14 empty] | 2018-05-16 | 2018-05-17 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-10325 | Newburgh | New Windsor | Orange | 12553 | G | 4095 | Bethlehem Rd | N |  | 12.5 | [13 empty] | NM | N | 39 SunPower SPR-X22-360-C-AC (240V) | 2018-02-20 | 2018-02-26 | 4 | 2018-02-26 | [8 empty] | 350 | 350 |  | 2018-02-27 | 2018-02-27 | 2018-03-20 | 2018-04-17 | 2018-04-18 |  | Y
Central Hudson |  | Hudson Solar | CH-10329 | Kingston | Kingston | Ulster | 12401 | G | 1014 | Boulevard | N |  | 6.4 | [13 empty] | NM | N | 20 SunPower SPR-E20-327-D-AC (240V) | 2018-02-20 | 2018-02-28 | 6 | 2018-02-28 | [14 empty] | 2018-04-06 | 2018-04-12 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-10328 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6096 | Manchester | N |  | 6.9 | [13 empty] | NM | N | 30 Enphase Energy IQ6-60-X-US (240V) | 2018-02-20 | 2018-02-26 | 4 | 2018-02-26 | [14 empty] | 2018-05-23 | 2018-06-26 |  | Y |  | 5/29/18 - Meter could not be changed due to being behind a locked gate, appointment needed. 6/22/18 - Meter change scheduled and completed.
Central Hudson |  | Hudson Solar | CH-10331 | Kingston | Accord | Ulster | 12404 | G | 3081 | Kerhonkson | N |  | 7.7 | [13 empty] | NM | N | 24 SunPower SPR-E20-327-D-AC (240V) | 2018-02-20 | 2018-02-28 | 6 | 2018-02-28 | [14 empty] | 2018-05-31 | 2018-06-04 |  | Y
Central Hudson |  | Lighthouse Solar | CH-10333 | Kingston | Saugerties | Ulster | 12477 | G | 3004 | Saugerties | N |  | 5 | [13 empty] | NM | N | 1SolaredgeSE5000H-US (240V) | 2018-02-28 | 2018-03-06 | 4 | 2018-03-06 | [14 empty] | 2018-04-24 | 2018-04-25 |  | Y
Central Hudson |  | Hudson Solar | CH-10332 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 7025 | Tinkertown | N |  | 10.9 | [13 empty] | NM | N | 34 SunPower SPR-E20-327-D-AC (240V) | 2018-02-21 | 2018-02-28 | 5 | 2018-02-28 | [14 empty] | 2018-04-20 | 2018-04-23 |  | Y
Central Hudson |  | SolarCity DBA Tesla | CH-10335 | Kingston | Saugerties | Ulster | 12477 | G | 3004 | Saugerties | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600A-US (240V) [SI1] | 2018-02-22 | 2018-03-02 | 6 | 2018-03-02 | [14 empty] | 2018-03-15 | 2018-03-19 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-10334 | Kingston | Rosendale | Ulster | 12472 | G | 1011 | Boulevard | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600A-US (240V) | 2018-03-14 | 2018-03-21 | 5 | 2018-03-21 | [14 empty] | 2018-04-03 | 2018-04-05 |  | Y
Central Hudson |  | Solarcity DBA Tesla | CH-10336 | Fishkill | Beacon | Dutchess | 12508 | G | 8016 | Forgebrook | Y | CH-10336 | 3.8 | [13 empty] | NM | N | 1SolaredgeSE3800H-US (240V) [SI1] | 2018-02-22 | 2018-03-02 | 6 | 2018-03-02 | [14 empty] | 2018-06-27 | 2018-06-28 |  | Y
Central Hudson |  | Trinity Solar | CH-10338 | Newburgh | New Windsor | Orange | 12553 | G | 4094 | Bethlehem Rd | N |  | 9.9 | [13 empty] | NM | N | 1 SolarEdge Technologies SE 10000A-US (240V) | 2018-04-11 | 2018-04-17 | 4 | 2018-04-17 | [14 empty] | 2018-04-25 | 2018-04-25 |  | Y
Central Hudson |  | High Peaks Solar, LLC | CH-10337 | Poughkeepsie | Millerton | Dutchess | 12546 | G | 7081 | Millerton | N |  | 3 | [13 empty] | NM | N | 1 SMA America SB3.0-1SP-US-40 (240V) | 2018-03-06 | 2018-03-06 | 0 | 2018-03-06 | [14 empty] | 2018-03-13 | 2018-03-14 |  | Y
Central Hudson |  | Matrix Development LLC | CH-10339 | Newburgh | Rock Tavern |  | 12575 | G | 4026 | Coldenham | TBD |  | 1980 | [13 empty] | CDG | N | 55 Huawei Technologies SUN2000-36KTL-US | 2018-03-07 | 2018-03-20 | 9 | 2018-03-20 | 2018-03-20 | 2018-04-10 | 14 | 2018-04-30 |  |  |  | 12000 | [9 empty] | W |  | There are 4 accounts at this location with an aggregate CESIR Cost to Customer of $48,000.
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-10340 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6065 | Inwood Ave | N |  | 4.6 | [13 empty] | NM | N | 8 Enphase Energy IQ6-60-X-US (240V) 12 Enphase Energy IQ6-60-X-US (240V) | 2018-02-26 | 2018-03-08 | 8 | 2018-03-08 | [14 empty] | 2018-07-25 | 2018-07-25 |  | Y
Central Hudson |  | SolarCity DBA Tesla | CH-10345 | Newburgh | New Windsor | Orange | 12553 | G | 4045 | Union Ave | N |  | 4.2 | [13 empty] | NM | N | 1 ABB PVI-4.2-OUTD-S-US-Z-A (240V) | 2018-02-27 | 2018-03-05 | 4 | 2018-03-05 | [14 empty] | 2018-04-16 | 2018-04-18 |  | Y
Central Hudson |  | East Light Partners PBC | CH-10341 | Kingston | Saugerties | Ulster | 12477 | G | 3014 | Woodstock | N |  | 2440 | [13 empty] | CDG | Y | 39 Chint Power Systems America CPS SCA60KTL-DO/US-480 (480V) 2 Chint Power Systems America CPS SCA50KTL-DO/US-480 (480V) [SI1] | 2018-04-02 | 2018-04-16 | 10 | 2018-04-16 | 2018-04-16 | 2018-05-07 | 15 | 2018-06-07 | 2018-06-21 | 2018-09-17 | 60 | 16616.14 | 313106 | 172618.12 | 2019-01-24 | 2019-07-16 | 2019-07-16 | 2019-12-30 | 2020-02-27 | 2020-02-27 | 2020-05-22 | Y | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-10342 | Newburgh | Newburgh | Orange | 12550 | G | 4024 | Coldenham | N |  | 11.5 | [13 empty] | NM | N | 50 Enphase Energy IQ6-60-X-US (240V) | 2018-02-27 | 2018-03-05 | 4 | 2018-03-05 | [14 empty] | 2018-06-08 | 2018-06-20 |  | Y
Central Hudson |  | Lumens Holdings 3 LLC. | CH-10344 | Kingston | Kerhonkson |  | 12446 | G | 3082 | Kerhonkson | TBD |  | 1980 | [13 empty] | CDG | N | 33 Sungrow Power Supply SG60KU-M | 2018-07-31 | 2018-08-06 | 4 | 2018-08-06 | 2018-08-06 | 2018-08-24 | 14 | 2018-10-29 | 2018-11-05 | 2019-02-04 | 60 | 16026.27 | 332241 | [7 empty] | 2019-08-09 | W
Central Hudson |  | Omni Industria NY LLC | CH-10347 | Catskill | Athens |  | 12015 | G | 1074 | Coxsackie | TBD |  | 1980 | [13 empty] | CDG | N | 33 Sungrow Power Supply SG60KU-M | 2018-08-09 | 2018-08-21 | 8 | 2018-08-21 | 2018-08-21 | 2018-09-11 | 14 |  |  |  |  | 37100 | [9 empty] | W
Central Hudson |  | Tesla | CH-10350 | Catskill | Haines Falls | Greene | 12436 | G | 2385 | Lawrenceville | N |  | 7.2 | [13 empty] | NM | N | 1 ABB PVI-4.2-OUTD-S-US-Z-A (240V) 1 ABB PVI-3.0-OUTD-S-US-Z-A (240V) | 2018-03-13 | 2018-03-16 | 3 | 2018-03-16 | [14 empty] | 2018-04-04 | 2018-04-05 |  | Y
Central Hudson |  | SolarCity DBA Tesla Energy | CH-10348 | Kingston | W Shokan | Ulster | 12494 | G | 3011 | Woodstock | N |  |  | 10 | [12 empty] | NM | N | 2TeslaAC Powerwall 2.0 | 2019-01-08 | 2019-01-09 | 1 | 2019-01-09 | [14 empty] | 2019-04-24 | 2019-04-26 |  | Y |  | 4/24/19 - Received signed letter from applicant to opt-out of Value Stack compensation.
Central Hudson |  | Infinity Solar Systems | CH-10349 | Newburgh | New Windsor | Orange | 12553 | G | 4092 | Bethlehem Rd | N |  | 9 | [13 empty] | NM | N | 28 SunPower SPR-X22-360-C-AC (240V) | 2018-02-28 | 2018-03-06 | 4 | 2018-03-06 | [14 empty] | 2018-05-08 | 2018-05-25 |  | Y |  | Storm Restoration due to 5/15/18 Damaging Winds and Rains including Tornados and Macroburst.
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-10354 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8095 | Fishkill Plains | N |  | 9.2 | [13 empty] | NM | N | 40 Enphase Energy IQ6-60-X-US (240V) | 2018-03-01 | 2018-03-02 | 1 | 2018-03-02 | [14 empty] | 2018-05-07 | 2018-05-08 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-10352 | Newburgh | Newburgh | Orange | 12550 | G | 4014 | West Balmville | N | CH-10352 | 5.5 | [13 empty] | NM | N | 24 Enphase Energy IQ6-60-X-US (240V) | 2018-03-01 | 2018-03-06 | 3 | 2018-03-06 | [14 empty] | 2018-04-26 | 2018-04-30 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-10351 | Fishkill | Hopewell Jct |  | 12533 | G | 8093 | Fishkill Plains | N |  | 20.2 | [13 empty] | NM | N | 88 Enphase Energy IQ6-60-X-US (240V) | 2018-03-01 | 2018-03-06 | 3 | 2018-03-06 | [17 empty] | W
Central Hudson |  | New York State Solar Farm | CH-10353 | Kingston | Shokan | Ulster | 12481 | G | 3011 | Woodstock | N |  | 14.4 | [13 empty] | NM | N | 45 SunPower SPR-X22-360-D-AC (240V) [SI1] | 2018-03-06 | 2018-03-06 | 0 | 2018-03-06 | [14 empty] | 2018-03-23 | 2018-04-06 |  | Y
Central Hudson |  | Solar Generation | CH-10355 | Kingston | Kingston | Ulster | 12401 | G | 2092 | Hurley Ave | N |  | 43.2 | [13 empty] | RC | Y | 3SolaredgeSE14.4KUS (208V) | 2018-04-11 | 2018-04-17 | 4 | 2018-04-17 | [14 empty] | 2018-05-25 | 2018-05-25 |  | Y | Y
Central Hudson |  | SolarCity DBA Tesla | CH-10358 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8045 | Myers Corners | N |  | 16.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000 (240V) 1 SolarEdge Technologies SE 11400A-US (240V) | 2018-03-02 | 2018-03-06 | 2 | 2018-03-06 | [14 empty] | 2018-03-12 | 2018-03-14 |  | Y
Central Hudson |  | SolarCity DBA Tesla | CH-10359 | Poughkeepsie | Pleasant Vly |  | 12569 | G | 7011 | Hibernia | TBD |  | 7.6 | [13 empty] | NM | N | 1 Delta Electronics SOLIVIA 7.6 NA G4 TL (240V) [SI1] | 2018-03-02 | 2018-03-06 | 2 | 2018-03-06 | [17 empty] | W
Central Hudson |  | SolarCity DBA Tesla | CH-10360 | Newburgh | Maybrook | Orange | 12543 | G | 4026 | Coldenham | N |  | 3.6 | [13 empty] | NM | N | 1 ABB PVI-3.6-OUTD-S-US-Z-A (240V) [SI1] | 2018-03-02 | 2018-03-06 | 2 | 2018-03-06 | [14 empty] | 2018-06-04 | 2018-06-05 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-10356 | Poughkeepsie | Wappingrs Fls | Dutchess | 12590 | G | 6052 | Todd Hill | N |  | 7.8 | [13 empty] | NM | N | 34 Enphase Energy IQ6-60-X-US (240V) | 2018-03-02 | 2018-03-06 | 2 | 2018-03-06 | [14 empty] | 2018-05-07 | 2018-05-08 |  | Y
Central Hudson |  | SolarCity DBA Tesla | CH-10363 | Kingston | Saugerties |  | 12477 | G | 3003 | Saugerties | Y | CH-10363 |  | 5 | [12 empty] | NM | N | 1TeslaAC PowerWall | 2018-03-05 | 2018-03-08 | 3 | 2018-03-08 | [14 empty] | 2018-08-09 | 2018-08-15 |  | W
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-10361 | Poughkeepsie | Staatsburg | Dutchess | 12580 | G | 7041 | Staatsburg | N |  | 3.4 | [13 empty] | NM | N | 15 Enphase Energy IQ6-60-X-US (240V) | 2018-03-05 | 2018-03-06 | 1 | 2018-03-06 | [14 empty] | 2018-07-30 | 2018-07-30 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-10362 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8071 | Shenandoah | N |  | 12.6 | [13 empty] | NM | N | 12 Enphase Energy IQ6-60-X-US (240V) 16 Enphase Energy IQ6-60-X-US (240V) 12 Enphase Energy IQ6-60-X-US (240V) 15 Enphase Energy IQ6-60-X-US (240V) | 2018-03-05 | 2018-03-06 | 1 | 2018-03-06 | [14 empty] | 2018-05-01 | 2018-05-07 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-10364 | Poughkeepsie | Poughkeepsie |  | 12603 | G | 6061 | Inwood Ave | N |  | 4.4 | [13 empty] | NM | N | 19 Enphase Energy IQ6-60-X-US (240V) | 2018-03-06 | 2018-03-06 | 0 | 2018-03-06 | [17 empty] | W
Central Hudson |  | SolarCity DBA Tesla | CH-10373 | Kingston | High Fls | Ulster | 12440 | G | 3024 | High Falls | Y |  | 3.6 | 5 | [12 empty] | NM | N | 1 ABB PVI-3.6-OUTD-S-US-Z-A (240V) 1TeslaAC Powerwall 2.0 | 2018-04-06 | 2018-04-13 | 5 | 2018-04-13 | [14 empty] | 2018-04-26 | 2018-04-27 |  | Y
Central Hudson |  | SolarCity DBA Tesla | CH-10374 | Newburgh | Cornwall-Hdsn | Orange | 12520 | G | 4043 | Union Ave | N |  | 4.2 | [13 empty] | NM | N | 1 ABB PVI-4.2-OUTD-S-US-Z-A (240V) [SI1] | 2018-03-08 | 2018-03-08 | 0 | 2018-03-08 | [14 empty] | 2018-03-28 | 2018-04-04 |  | Y
Central Hudson |  | SolarCity DBA Tesla | CH-10370 | Newburgh | Middletown | Orange | 10941 | G | 5051 | Maybrook | N |  | 10.4 | [13 empty] | NM | N | 1 Delta Electronics SOLIVIA 5.2 NA G4 TL (240V) 1 Delta Electronics SOLIVIA 5.2 NA G4 TL (240V) [SI1] | 2018-03-06 | 2018-03-08 | 2 | 2018-03-08 | [14 empty] | 2018-05-23 | 2018-05-25 |  | Y
Central Hudson |  | SolarCity DBA Tesla | CH-10375 | Poughkeepsie | Hyde Pk |  | 12538 | G | 6074 | East Park | TBD |  | 6.6 | [13 empty] | NM | N | 1 Delta Electronics SOLIVIA 6.6 NA G4 TL (240V) [SI1] 1TeslaAC PowerWall | 2018-03-06 | 2018-03-08 | 2 | 2018-03-08 | [17 empty] | W
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-10365 | Kingston | Ulster Pk | Ulster | 12487 | G | 1023 | East Kingston | N |  | 3.7 | [13 empty] | NM | N | 16 Enphase Energy IQ6-60-X-US (240V) | 2018-03-06 | 2018-03-06 | 0 | 2018-03-06 | [14 empty] | 2018-05-10 | 2018-05-14 |  | Y
Central Hudson |  | Tesla | CH-10368 | Fishkill | Beacon | Dutchess | 12508 | G | 8085 | Tioronda | N |  | 3 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3000H-US (240V) [SI1] | 2018-03-06 | 2018-03-06 | 0 | 2018-03-06 | [14 empty] | 2018-06-25 | 2018-06-25 |  | Y
Central Hudson |  | Sunrun Inc. | CH-10366 | Newburgh | Montgomery | Orange | 12549 | G | 5073 | Montgomery | N |  | 7.8 | [13 empty] | NM | N | 1 ABB PVI-3.6-OUTD-S-US-A (240V) 1 ABB PVI-4.2-OUTD-S-US-A (240V) | 2018-03-06 | 2018-03-06 | 0 | 2018-03-06 | [14 empty] | 2018-05-09 | 2018-05-10 |  | Y
Central Hudson |  | Tesla | CH-10367 | Fishkill | Stormvl |  | 12582 | G | 8071 | Shenandoah | Y |  | 7.6 | 10 | [12 empty] | NM | N | 1 SolarEdge Technologies SE7600A-US (240V) 2TeslaAC PowerWall | 2018-03-06 | 2018-03-06 | 0 | 2018-03-06 | [17 empty] | W
Central Hudson |  | Solar Generation | CH-10369 | Kingston | Saugerties | Ulster | 12477 | G | 3003 | Saugerties | N |  | 20.8 | [13 empty] | NM | N | 65 SunPower SPR-X22-360-D-AC (240V) | 2018-03-23 | 2018-03-29 | 4 | 2018-03-29 | [14 empty] | 2018-07-18 | 2018-07-26 |  | Y
Central Hudson |  | Tri-State Solar Services | CH-10376 | Newburgh | Marlboro | Ulster | 12542 | G | 5003 | Marlboro | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600A-US (240V) | 2018-03-09 | 2018-03-09 | 0 | 2018-03-09 | [14 empty] | 2018-03-29 | 2018-04-06 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-10377 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8051 | North Chelsea | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000 (240V) | 2018-03-07 | 2018-03-08 | 1 | 2018-03-08 | [8 empty] | 350 | 350 |  | 2018-03-21 | 2018-03-21 | 2018-05-04 | 2018-05-11 | 2018-05-14 |  | Y
Central Hudson |  | Kasselman Solar | CH-10379 | Poughkeepsie | Stanfordvl | Dutchess | 12581 | G | 7072 | Stanfordville | N |  | 4.8 | [13 empty] | NM | N | 17 Enphase Energy IQ6PLUS-72-X-US (240V) | 2018-03-07 | 2018-03-08 | 1 | 2018-03-08 | [14 empty] | 2018-03-20 | 2018-03-22 |  | Y
Central Hudson |  | Kasselman Solar | CH-10378 | Kingston | Kingston | Ulster | 12401 | G | 2094 | Hurley Ave | N |  | 5 | [13 empty] | NM | N | 18 Enphase Energy IQ6PLUS-72-X-US (240V) | 2018-03-07 | 2018-03-08 | 1 | 2018-03-08 | [14 empty] | 2018-04-11 | 2018-04-16 |  | Y
Central Hudson |  | Empire Solar Store | CH-10380 | Catskill | Catskill | Greene | 12414 | G | 2005 | North Catskill | N |  | 6 | [13 empty] | RC | Y | 1 SolarEdge Technologies SE6000H-US (240V) | 2018-03-29 | 2018-04-04 | 3 | 2018-04-04 | [14 empty] | 2018-05-08 | 2018-05-15 |  | Y | N
Central Hudson |  | Trinity Solar | CH-10381 | Newburgh | Newburgh | Orange | 12550 | G | 402 | Montgomery St | N |  | 6.4 | [13 empty] | NM | N | 28 Enphase Energy IQ6-60-X-US (240V) | 2018-04-04 | 2018-04-05 | 1 | 2018-04-05 | [14 empty] | 2018-07-12 | 2018-07-13 |  | Y
Central Hudson |  | New York State Solar Farm | CH-10383 | Newburgh | Milton | Ulster | 12547 | G | 5083 | Highland | N |  | 5.1 | [13 empty] | NM | N | 16 SunPower SPR-E20-327-D-AC (240V) | 2018-03-08 | 2018-03-09 | 1 | 2018-03-09 | [14 empty] | 2018-03-29 | 2018-04-03 |  | Y
Central Hudson |  | New York State Solar Farm | CH-10382 | Newburgh | Newburgh | Orange | 12550 | G | 5004 | Marlboro | N | CH-10382 | 6.4 | [13 empty] | NM | N | 20 SunPower SPR-E20-327-D-AC (240V) [SI1] | 2018-03-08 | 2018-03-09 | 1 | 2018-03-09 | [14 empty] | 2018-06-18 | 2018-06-29 |  | Y
Central Hudson |  | Kasselman Solar | CH-10384 | Newburgh | Highland | Ulster | 12528 | G | 5083 | Highland | N | CH-00229 | 6.7 | [13 empty] | NM | N | 29 Enphase Energy IQ6-60-X-US (240V) | 2018-03-09 | 2018-03-23 | 10 | 2018-03-23 | [8 empty] | 350 | 350 |  | 2018-03-28 | 2018-03-28 | 2018-03-29 | 2018-04-27 | 2018-04-30 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-10388 | Newburgh | New Windsor | Orange | 12553 | G | 4046 | Union Ave | N |  | 7.4 | [13 empty] | NM | N | 32 Enphase Energy IQ6-60-X-US (240V) | 2018-03-13 | 2018-03-15 | 2 | 2018-03-15 | [14 empty] | 2018-10-16 | 2018-10-17 |  | Y
Central Hudson |  | Lumens Holdings 3 LLC. | CH-10343 | Catskill | Coeymans Hollow |  | 12046 | G | 1081 | New Baltimore | TBD |  | 1980 | [13 empty] | CDG | N | 33 Sungrow Power Supply SG60KU-M | 2018-06-05 | 2018-06-14 | 7 | 2018-06-14 | 2018-06-14 | 2018-07-03 | 13 | 2018-08-27 | 2018-10-31 | 2019-01-30 | 60 | 25943.01 | 728709 | [7 empty] | 2019-08-09 | W
Central Hudson |  | Consolidated Edison Solutions, Inc. | CH-10387 | Kingston | Kingston |  | 12401 | G | 2094 | Hurley Ave | N |  | 1000 | [13 empty] | CDG | Y | 24KacoBlue Planet 125 TL3 | 2018-11-26 | 2018-12-04 | 6 | 2018-12-04 | 2018-12-04 | 2018-12-19 | 11 | 2019-01-04 | 2019-02-15 | 2019-07-01 | 93 | 19837.52 | 292646.25 | 292646.25 | 2019-08-22 | 2020-01-03 | 2020-01-03 |  |  |  | 2021-01-29 | W |  | 5/7/19 - System configuration changed, Utility and Developer mutually agreed to extend the CESIR deadline to 7/1/19.
Central Hudson |  | Solitude Solar, LLC | CH-10385 | Catskill | Tannersvl |  | 12485 | G | 2385 | Lawrenceville | TBD |  | 1800 | [13 empty] | CDG | N | 30 Chint Power Systems America CPS SCA60KTL-DO/US-480 (480V) | 2018-04-20 | 2018-05-02 | 8 | 2018-05-02 | 2018-05-02 | 2018-05-23 | 15 | 2018-06-08 | 2018-07-27 | 2018-11-02 | 69 | 19159.37 | 315025 |  | 2019-02-20 | 2019-05-24 | 2019-05-24 |  |  |  | 2019-09-06 | W | Y | 10/12/18 - Utility and Customer came to a mutual agreement to extend the CESIR deadline from 10/22/18 to 11/2/18, as permitted in Section 6 of the NYSSIR.
Central Hudson |  | Empire Solar Solutions | CH-10392 | Poughkeepsie | Millbrook | Dutchess | 12545 | G | 7012 | Hibernia | N |  | 3 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3000 (240V) | 2018-03-14 | 2018-03-21 | 5 | 2018-03-21 | [14 empty] | 2018-03-29 | 2018-04-03 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-10391 | Fishkill | Fishkill | Dutchess | 12524 | G | 8094 | Fishkill Plains | N |  | 7.1 | [13 empty] | NM | N | 31 Enphase Energy IQ6-60-X-US (240V) | 2018-03-14 | 2018-03-21 | 5 | 2018-03-21 | [14 empty] | 2018-06-01 | 2018-06-07 |  | Y
Central Hudson |  | High Peaks Solar, LLC | CH-10390 | Catskill | Jewett | Greene | 12444 | E | 2389 | Vinegar Hill | N | CH-10094 | 3.4 | [13 empty] | NM | N | 14 Enphase Energy M250-60-2LL-S2X (-ZC) (-NA) (240V) | 2018-03-14 | 2018-03-20 | 4 | 2018-03-20 | [14 empty] | 2018-06-18 | 2018-06-19 |  | Y
Central Hudson |  | Apex Solar Power | CH-10389 | Newburgh | New Paltz | Ulster | 12561 | G | 5021 | Ohioville | N | CH-10389 | 3.8 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3800 (240V) | 2018-03-14 | 2018-03-20 | 4 | 2018-03-20 | [14 empty] | 2018-05-25 | 2018-05-29 |  | Y
Central Hudson |  | SolarCity DBA Tesla | CH-10398 | Newburgh | Newburgh | Orange | 12550 | G | 4014 | West Balmville | N |  | 5.2 | [13 empty] | NM | N | 1 Delta Electronics SOLIVIA 5.2 NA G4 TL (240V) [SI1] | 2018-03-15 | 2018-03-23 | 6 | 2018-03-23 | [14 empty] | 2018-03-23 | 2018-04-10 |  | Y
Central Hudson |  | SolarCity DBA Tesla | CH-10397 | Kingston | Ellenvl | Ulster | 12428 | G | 3095 | Grimley Rd | Y | CH-06556 |  | 5 | [12 empty] | NM | N | 1TeslaAC Powerwall 2.0 | 2018-03-15 | 2018-03-26 | 7 | 2018-03-26 | [14 empty] | 2018-06-08 | 2018-06-08 |  | Y
Central Hudson |  | Solar Spectrum LLC | CH-10393 | Poughkeepsie | Hyde Pk |  | 12538 | G | 6073 | East Park | TBD |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000 (240V) | 2018-04-04 | 2018-04-04 | 0 | 2018-04-04 | [17 empty] | W
Central Hudson |  | Solar Generation | CH-10394 | Catskill | Shandaken | Ulster | 12480 | E | 2387 | NYSEG | N | CH-08139 | 4 | [13 empty] | NM | N | 1 SMA America SB7.7-1SP-US-40 (240V) | 2018-03-29 | 2018-04-04 | 3 | 2018-04-04 | [14 empty] | 2018-08-21 | 2018-08-21 |  | Y
Central Hudson |  | Empire Solar Store | CH-10400 | Kingston | Saugerties | Ulster | 12477 | G | 3003 | Saugerties | N |  | 3.8 | [13 empty] | NM | N | 1 SMA America SB3.8-1SP-US-40 (240V) | 2018-03-16 | 2018-03-26 | 6 | 2018-03-26 | [14 empty] | 2018-04-20 | 2018-04-24 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-10403 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8045 | Myers Corners | N |  | 7.8 | [13 empty] | NM | N | 28 Enphase Energy IQ6-60-X-US (240V) 6 Enphase Energy IQ6-60-X-US (240V) | 2018-03-19 | 2018-03-28 | 7 | 2018-03-28 | [14 empty] | 2018-08-02 | 2018-08-02 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-10402 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8091 | Fishkill Plains | N |  | 4.8 | [13 empty] | NM | N | 21 Enphase Energy IQ6-60-X-US (240V) | 2018-03-19 | 2018-03-26 | 5 | 2018-03-26 | [14 empty] | 2018-05-15 | 2018-05-15 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-10405 | Kingston | Hurley | Ulster | 12443 | G | 2094 | Hurley Ave | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600A-US (240V) | 2018-03-29 | 2018-04-04 | 3 | 2018-04-04 | [14 empty] | 2018-04-04 | 2018-04-05 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-10404 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6065 | Inwood Ave | N |  | 3.2 | [13 empty] | NM | N | 14 Enphase Energy IQ6-60-X-US (240V) | 2018-05-17 | 2018-05-18 | 1 | 2018-05-18 | [14 empty] | 2018-07-25 | 2018-07-25 |  | Y
Central Hudson |  | Kasselman Solar | CH-10401 | Catskill | Earlton | Greene | 12058 | G | 2005 | North Catskill | N |  | 3.2 | [13 empty] | NM | N | 14 Enphase Energy IQ6-60-X-US (240V) | 2018-03-19 | 2018-03-26 | 5 | 2018-03-26 | [14 empty] | 2018-04-02 | 2018-04-03 |  | Y
Central Hudson |  | Solar Alchemy, Inc. | CH-10406 | Kingston | Olive Brdg | Ulster | 12461 | G | 2094 | Hurley Ave | N |  | 110.7 | [13 empty] | NM | N | 1 Fronius USA Fronius Primo 15.0-1 (240V) 1 Fronius USA Fronius Primo 12.5-1 (240V) 1 Fronius USA Fronius Primo 12.5-1 (240V) 1 Fronius USA Fronius Primo 12.5-1 (240V) 1 Fronius USA Fronius Primo 12.5-1 (240V) 1 Fronius USA Fronius Symo 12.5-3 480 (480V) 1 Fronius USA Fronius Primo 8.2-1 208-240 (240V) 1 Fronius USA Fronius Primo 12.5-1 (240V) 1 Fronius USA Fronius Symo 12.5-3 480 (480V) | 2018-08-22 | 2018-08-27 | 3 | 2018-08-27 | 2018-08-27 | 2018-09-18 | 15 | [5 empty] | 5750 | 3714.75 |  | 2018-10-02 | 2018-10-02 | 2018-12-04 | 2019-01-03 | 2019-01-03 | 2019-01-03 | Y
Central Hudson |  | Empire Solar Solutions | CH-10409 | Catskill | Catskill | Greene | 12414 | G | 2001 | North Catskill | N |  | 7.7 | [13 empty] | NM | N | 1 SMA America SB7700TL-US-22 (240V) | 2018-03-21 | 2018-03-29 | 6 | 2018-03-29 | [14 empty] | 2018-06-05 | 2018-06-07 |  | Y
Central Hudson |  | EnterSolar LLC | CH-10407 | Kingston | Kerhonkson |  | 12446 | G | 3082 | Kerhonkson | TBD |  | 5000 | [13 empty] | CDG | N | 76Yaskawa Solectria SolarXGI 1000-65 (480V)1Yaskawa Solectria SolarXGI 1000-60 (480V) | 2018-07-26 | 2018-08-06 | 7 | 2018-08-06 | 2018-08-06 | 2018-08-24 | 14 |  |  |  |  | 37100 | [9 empty] | W
Central Hudson |  | New York State Solar Farm | CH-10408 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6052 | Todd Hill | N |  | 12 | [13 empty] | NM | N | 2 SMA America SB6000TL-US (240V) | 2018-03-21 | 2018-03-21 | 0 | 2018-03-21 | [14 empty] | 2018-03-21 | 2018-03-21 |  | Y
Central Hudson |  | SolarCity | CH-05196 | Fishkill | Garrison | Putnam | 10524 | G | 8066 | Merritt Park | Y |  | 5.2 | 5 | [12 empty] | NM | N | 1 Delta Electronics SOLIVIA 5.2 NA G4 TL (240V) 1 DELTA SOLIVIA 5.2 TL1TeslaAC Powerwall 2.0 | 2018-06-25 | 2018-06-25 | 0 | 2018-06-25 | [14 empty] | 2018-08-08 | 2018-08-13 |  | Y
Central Hudson |  | Lighthouse Solar | CH-10411 | Kingston | Kerhonkson | Ulster | 12446 | G | 3082 | Kerhonkson | N |  | 22.8 | [13 empty] | NM | N | 2 SolarEdge Technologies SE 11400A-US (240V) | 2018-03-22 | 2018-03-29 | 5 | 2018-03-29 | [8 empty] | 350 | 350 |  | 2018-04-02 | 2018-04-02 | 2018-05-30 | 2018-05-31 | 2018-05-31 |  | Y
Central Hudson |  | Tesla | CH-10412 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6045 | Spackenkill | N |  | 5 | [13 empty] | NM | N | 1 ABB PVI-5000-OUTD-S-US-Z-A (240 V) | 2018-03-22 | 2018-03-29 | 5 | 2018-03-29 | [14 empty] | 2018-05-23 | 2018-05-25 |  | Y
Central Hudson |  | Hudson Solar | CH-10410 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 6074 | East Park | N |  | 7.6 | [13 empty] | NM | N | 1SolarEdgeSE7600A-USS2 | 2018-03-29 | 2018-04-04 | 3 | 2018-04-04 | [14 empty] | 2018-05-14 | 2018-05-15 |  | Y
Central Hudson |  | Squan Solar | CH-10413 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6044 | Spackenkill | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE 11400A-US (240V) | 2018-04-18 | 2018-04-18 | 0 | 2018-04-18 | [14 empty] | 2018-04-18 | 2018-04-26 |  | Y
Central Hudson |  | WINDSOR MACHINERY INC | CH-09989 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8023 | Knapps Corners | N | CH-09989 | [10 empty] | 282 |  |  |  | CDG | Y | 282 | 2018-04-12 | 2018-04-19 | 5 | 2018-04-19 | [14 empty] | 1988-12-02 | 1988-12-02 |  | Y | N | April 2018 - Account transferred from IPP to CDG.
Central Hudson |  | WINDSOR MACHINERY INC | CH-10005 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8023 | Knapps Corners | N | CH-09989 | [10 empty] | 2200 |  |  |  | CDG | Y | (2) 1100 kW generators at .77 PF2200 | 2018-04-12 | 2018-04-19 | 5 | 2018-04-19 | [14 empty] | 1988-12-02 | 1988-12-02 |  | Y | N | April 2018 - Account transferred from IPP to CDG.
Central Hudson |  | GenPro Energy Solutions, LLC | CH-10414 | Kingston | Rosendale | Ulster | 12472 | G | 3021 | High Falls | N |  | 150 | [13 empty] | NM | N | 3 Chint Power Systems America CPS SCA50KTL-DO/US-480 | 2018-04-03 | 2018-04-16 | 9 | 2018-04-16 | 2018-04-16 | 2018-05-07 | 15 | [11 empty] | 2021-12-08 | 2021-12-08 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-10419 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8092 | Fishkill Plains | N |  | 4.8 | [13 empty] | NM | N | 15 SunPower SPR-X22-360-C-AC (240V) | 2018-03-26 | 2018-03-29 | 3 | 2018-03-29 | [14 empty] | 2018-07-03 | 2018-07-05 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-10415 | Newburgh | Cornwall | Orange | 12518 | G | 4041 | Union Ave | N |  | 5.4 | [13 empty] | NM | N | 17 SunPower SPR-X22-360-C-AC (240V) | 2018-03-26 | 2018-04-03 | 5 | 2018-04-03 | [14 empty] | 2018-05-14 | 2018-05-25 |  | Y
Central Hudson |  | New York State Solar Farm | CH-10418 | Newburgh | Wallkill | Ulster | 12589 | G | 5043 | East Walden | N |  | 9 | [13 empty] | NM | N | 28 SunPower SPR-E20-327-D-AC (240V) | 2018-03-26 | 2018-03-29 | 3 | 2018-03-29 | [14 empty] | 2018-03-29 | 2018-04-03 |  | Y
Central Hudson |  | Tesla | CH-10417 | Kingston | W Hurley | Ulster | 12491 | G | 2094 | Hurley Ave | Y | CH-08122 |  | 15 | [12 empty] | NM | N | 3TeslaAC Powerwall 2.0 | 2018-04-02 | 2018-04-04 | 2 | 2018-04-04 | [14 empty] | 2019-05-06 | 2019-05-09 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-10416 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 7025 | Tinkertown | N |  | 12.2 | [13 empty] | NM | N | 18 Enphase Energy IQ6-60-X-US (240V) 10 Enphase Energy IQ6-60-X-US (240V) 25 Enphase Energy IQ6-60-X-US (240V) | 2018-03-26 | 2018-03-29 | 3 | 2018-03-29 | [8 empty] | 350 | 350 |  | 2018-04-02 | 2018-04-02 | 2018-04-06 | 2018-07-12 | 2018-07-20 |  | Y
Central Hudson |  | New York State Solar Farm | CH-10420 | Newburgh | New Paltz | Ulster | 12561 | G | 5031 | Galeville | N |  | 6.7 | [13 empty] | NM | N | 21 SunPower SPR-X22-360-D-AC (240V) | 2018-03-26 | 2018-03-29 | 3 | 2018-03-29 | [14 empty] | 2018-04-23 | 2018-04-23 |  | Y
Central Hudson |  | SolarCity DBA Tesla | CH-10427 | Newburgh | Highland Mls | Orange | 10930 | G | 4041 | Union Ave | N |  | 6.6 | [13 empty] | NM | N | 1 Delta Electronics SOLIVIA 6.6 NA G4 TL (240V) | 2018-04-11 | 2018-04-17 | 4 | 2018-04-17 | [14 empty] | 2018-04-24 | 2018-04-27 |  | Y
Central Hudson |  | New York State Solar Farm | CH-10424 | Newburgh | Modena | Ulster | 12548 | G | 5012 | Modena | N |  | 6.1 | [13 empty] | NM | N | 19 SunPower SPR-E20-327-D-AC (240V) | 2018-03-27 | 2018-03-29 | 2 | 2018-03-29 | [14 empty] | 2018-04-23 | 2018-04-23 |  | Y
Central Hudson |  | New York State Solar Farm | CH-10423 | Newburgh | Milton | Ulster | 12547 | G | 5003 | Marlboro | N |  | 9 | [13 empty] | NM | N | 28 SunPower SPR-X22-360-D-AC (240V) | 2018-03-27 | 2018-03-29 | 2 | 2018-03-29 | [14 empty] | 2018-05-04 | 2018-05-07 |  | Y
Central Hudson |  | New York State Solar Farm | CH-10422 | Newburgh | New Paltz | Ulster | 12561 | G | 5024 | Ohioville | N |  | 11.2 | [13 empty] | NM | N | 35 SunPower SPR-E20-327-D-AC (240V) | 2018-04-12 | 2018-04-12 | 0 | 2018-04-12 | [14 empty] | 2018-04-13 | 2018-04-17 |  | Y
Central Hudson |  | New York State Solar Farm | CH-10421 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8095 | Fishkill Plains | N |  | 19.5 | [13 empty] | NM | N | 61 SunPower SPR-X21-345-D-AC (240V) [SI1] | 2018-03-27 | 2018-03-29 | 2 | 2018-03-29 | [14 empty] | 2018-05-08 | 2018-05-09 |  | Y
Central Hudson |  | Tesla | CH-10431 | Newburgh | Wallkill | Ulster | 12589 | G | 5013 | Modena | N |  | 6 | [13 empty] | NM | N | 1 ABB PVI-6000-OUTD-US-Z-A (240V) [SI1] | 2018-03-28 | 2018-04-04 | 4 | 2018-04-04 | [14 empty] | 2018-05-18 | 2018-05-21 |  | Y
Central Hudson |  | Hudson Solar | CH-10428 | Poughkeepsie | Millerton | Dutchess | 12546 | G | 7081 | Millerton | N | CH-02352 | 3.2 | [13 empty] | NM | N | 10 SunPower SPR-X21-335-BLK-D-AC (240V) [SI1] | 2018-03-28 | 2018-04-05 | 5 | 2018-04-05 | [14 empty] | 2018-05-16 | 2018-05-16 |  | Y
Central Hudson |  | Hudson Solar | CH-10429 | Newburgh | New Paltz | Ulster | 12561 | G | 5023 | Ohioville | N | CH-10429 | 3.5 | [13 empty] | NM | N | 11 SunPower SPR-E20-327-D-AC (240V) [SI1] | 2018-03-28 | 2018-04-03 | 3 | 2018-04-03 | [14 empty] | 2018-04-12 | 2018-04-12 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-10430 | Kingston | Saugerties | Ulster | 12477 | G | 3001 | Saugerties | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000 (240V) | 2018-04-05 | 2018-04-06 | 1 | 2018-04-06 | [14 empty] | 2018-04-06 | 2018-04-10 |  | Y
Central Hudson |  | Autonomous Energies LLC | CH-10432 | Catskill | Catskill | Greene | 12414 | G | 2042 | South Cairo | N |  | 30.8 | [13 empty] | NM | N | 4 SMA America SB7700TL-US-22 (240V) | 2018-04-20 | 2018-04-20 | 0 | 2018-04-20 | [14 empty] | 2018-07-12 | 2018-07-12 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-10434 | Fishkill | Fishkill | Dutchess | 12524 | G | 8051 | North Chelsea | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600A-US (240V) | 2018-04-05 | 2018-04-06 | 1 | 2018-04-06 | [14 empty] | 2018-04-06 | 2018-04-12 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-10433 | Fishkill | Beacon | Dutchess | 12508 | G | 8087 | Tioronda | N |  | 4.8 | [13 empty] | NM | N | 15 SunPower SPR-X22-360-C-AC (240V) | 2018-03-29 | 2018-04-04 | 3 | 2018-04-04 | [14 empty] | 2018-06-04 | 2018-06-06 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-10435 | Newburgh | New Windsor | Orange | 12553 | G | 4044 | Union Ave | N |  | 14.4 | [13 empty] | NM | N | 45 SunPower SPR-X22-360-C-AC (240V) | 2018-04-04 | 2018-04-12 | 6 | 2018-04-12 | [14 empty] | 2018-06-26 | 2018-07-06 |  | Y
Central Hudson |  | Lumens Holdings 3 LLC. | CH-10436 | Catskill | Durham |  | 12413 | G | 2043 | South Cairo | TBD |  | 5000 | [13 empty] | CDG | N | 40 Sungrow Power Supply SG125HV (600V) | 2018-06-18 | 2018-06-26 | 6 | 2018-06-26 | 2018-06-26 | 2018-07-18 | 15 | 2018-08-27 | 2018-10-31 | 2019-01-30 | 60 | 26353.25 | 436040 | [7 empty] | 2019-08-09 | W
Central Hudson |  | PlugPV, LLC. | CH-10438 | Kingston | Saugerties | Ulster | 12477 | G | 3003 | Saugerties | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600A-US (240V) [SI1] | 2018-04-02 | 2018-04-04 | 2 | 2018-04-04 | [14 empty] | 2018-04-19 | 2018-04-19 |  | Y
Central Hudson |  | Seed Solar | CH-10437 | Kingston | Hurley | Ulster | 12443 | G | 2093 | Hurley Ave | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2018-04-02 | 2018-04-04 | 2 | 2018-04-04 | [14 empty] | 2018-05-14 | 2018-05-14 |  | Y
Central Hudson |  | New York State Solar Farm | CH-10440 | Newburgh | Wallkill | Ulster | 12589 | G | 5013 | Modena | N |  | 8.3 | [13 empty] | NM | N | 26 SunPower SPR-X22-360-D-AC (240V) | 2018-04-03 | 2018-04-04 | 1 | 2018-04-04 | [14 empty] | 2018-04-16 | 2018-04-18 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-10442 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8044 | Myers Corners | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000 (240V) | 2018-04-03 | 2018-04-12 | 7 | 2018-04-12 | [14 empty] | 2018-04-30 | 2018-05-04 |  | Y
Central Hudson |  | New York State Solar Farm | CH-10439 | Newburgh | Newburgh | Orange | 12550 | G | 4011 | West Balmville | N |  | 10.9 | [13 empty] | NM | N | 34 SunPower SPR-X22-360-D-AC (240V) | 2018-04-04 | 2018-04-04 | 0 | 2018-04-04 | [14 empty] | 2018-05-11 | 2018-05-14 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-10441 | Fishkill | Poughkeepsie | Dutchess | 12603 | G | 8022 | Knapps Corners | N |  | 9 | [13 empty] | NM | N | 27 Enphase Energy IQ6-60-X-US (240V) 12 Enphase Energy IQ6-60-X-US (240V) | 2018-05-10 | 2018-05-21 | 7 | 2018-05-21 | [14 empty] | 2018-07-27 | 2018-07-27 |  | Y
Central Hudson |  | New York State Solar Farm | CH-10443 | Newburgh | Highland | Ulster | 12528 | G | 5022 | Ohioville | N |  | 9.6 | [13 empty] | NM | N | 30 SunPower SPR-E20-327-D-AC (240V) | 2018-04-04 | 2018-04-04 | 0 | 2018-04-04 | [14 empty] | 2018-04-04 | 2018-04-06 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-10445 | Newburgh | New Windsor | Orange | 12553 | G | 4046 | Union Ave | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000 (240V) | 2018-04-05 | 2018-04-06 | 1 | 2018-04-06 | [14 empty] | 2018-04-11 | 2018-04-12 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-10444 | Fishkill | Beacon | Dutchess | 12508 | G | 8015 | Forgebrook | N |  | 3.8 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3800 (240V) | 2018-04-09 | 2018-04-16 | 5 | 2018-04-16 | [14 empty] | 2018-06-26 | 2018-06-26 |  | Y
Central Hudson |  | Sunrun Inc. | CH-10446 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8094 | Fishkill Plains | N |  | 16 | [13 empty] | NM | N | 1 SolarEdge Technologies SE 10000A-US (240V) 1 SolarEdge Technologies SE6000H-US (240V) | 2018-04-05 | 2018-04-06 | 1 | 2018-04-06 | [8 empty] | 350 | 350 |  | 2018-04-16 | 2018-04-16 | 2018-05-04 | 2018-06-07 | 2018-06-08 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-10447 | Newburgh | Milton | Ulster | 12547 | G | 5083 | Highland | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000 (240V) | 2018-04-05 | 2018-04-12 | 5 | 2018-04-12 | [14 empty] | 2018-06-25 | 2018-06-25 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-10448 | Kingston | Woodstock |  | 12498 | G | 3014 | Woodstock | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600A-US (240V) | 2018-04-05 | 2018-04-12 | 5 | 2018-04-12 | [17 empty] | W
Central Hudson |  | Empire Solar Solutions | CH-10450 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 7041 | Staatsburg | N |  | 3 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3000 (240V) | 2018-04-16 | 2018-04-18 | 2 | 2018-04-18 | [14 empty] | 2018-06-06 | 2018-06-06 |  | Y
Central Hudson |  | SolarCity DBA Tesla | CH-10453 | Fishkill | Beacon | Dutchess | 12508 | G | 8087 | Tioronda | N |  | 5 | [13 empty] | NM | N | 1 ABB PVI-5000-OUTD-US-Z-A (240V) | 2018-04-17 | 2018-04-19 | 2 | 2018-04-19 | [14 empty] | 2018-04-23 | 2018-04-26 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-10449 | Kingston | Hurley | Ulster | 12443 | G | 2094 | Hurley Ave | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000 (240V) | 2018-04-06 | 2018-04-13 | 5 | 2018-04-13 | [14 empty] | 2018-04-25 | 2018-04-30 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-10451 | Newburgh | Newburgh | Orange | 12550 | G | 4022 | Coldenham | N | CH-10451 | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000 (240V) | 2018-04-06 | 2018-04-16 | 6 | 2018-04-16 | [14 empty] | 2018-06-08 | 2018-06-11 |  | Y
Central Hudson |  | Kasselman Solar | CH-10452 | Kingston | Kingston | Ulster | 12401 | G | 1022 | East Kingston | N |  | 5.5 | [13 empty] | NM | N | 24 Enphase Energy IQ6-60-X-US (240V) | 2018-04-06 | 2018-04-16 | 6 | 2018-04-16 | [14 empty] | 2018-05-14 | 2018-05-18 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-10456 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8092 | Fishkill Plains | N |  | 5.8 | [13 empty] | NM | N | 19 Enphase Energy IQ6-60-X-US (240V) 6 Enphase Energy IQ6-60-X-US (240V) | 2018-04-09 | 2018-04-16 | 5 | 2018-04-16 | [14 empty] | 2018-05-14 | 2018-05-14 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-10454 | Newburgh | Newburgh | Orange | 12550 | G | 4013 | West Balmville | N |  | 5.4 | [13 empty] | NM | N | 17 SunPower SPR-X22-360-C-AC (240V) | 2018-04-09 | 2018-04-16 | 5 | 2018-04-16 | [14 empty] | 2018-07-23 | 2018-07-26 |  | Y
Central Hudson |  | Hudson Solar | CH-10455 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6097 | Manchester | N |  | 25.6 | [13 empty] | NM | N | 80 SunPower SPR-E20-327-D-AC (240V) | 2018-04-20 | 2018-04-20 | 0 | 2018-04-20 | [14 empty] | 2018-11-13 | 2018-11-13 |  | Y
Central Hudson |  | Tesla | CH-10458 | Catskill | Catskill | Greene | 12414 | G | 2006 | North Catskill | N |  | 7.6 | [13 empty] | NM | N | 1 Delta Electronics SOLIVIA 7.6 NA G4 TL (240V) | 2018-04-10 | 2018-04-16 | 4 | 2018-04-16 | [14 empty] | 2018-04-27 | 2018-05-03 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-10457 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8091 | Fishkill Plains | N |  | 12.6 | [13 empty] | NM | N | 55 Enphase Energy IQ6-60-X-US (240V) | 2018-04-09 | 2018-04-16 | 5 | 2018-04-16 | [14 empty] | 2018-07-05 | 2018-07-05 |  | Y
Central Hudson |  | SolarCity DBA Tesla | CH-10459 | Kingston | Saugerties | Ulster | 12477 | G | 3014 | Woodstock | N |  |  | 5 | [12 empty] | NA | N | 1TeslaAC Powerwall 2.0 | 2018-04-10 | 2018-04-18 | 6 | 2018-04-18 | [14 empty] | 2018-10-18 | 2018-10-18 |  | Y
Central Hudson |  | SolarCity DBA Tesla | CH-10467 | Fishkill | Wappingers Falls | Dutchess | 12590 | G | 8045 | Myers Corners | N |  | 3.6 | [13 empty] | NM | N | 1 ABB PVI-3.6-OUTD-S-US-Z-A (240V) | 2018-04-11 | 2018-04-17 | 4 | 2018-04-17 | [14 empty] | 2018-04-25 | 2018-04-27 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-10461 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8071 | Shenandoah | N |  | 7.6 | [13 empty] | NM | N | 33 Enphase Energy IQ6-60-X-US (240V) | 2018-04-11 | 2018-04-17 | 4 | 2018-04-17 | [14 empty] | 2018-05-24 | 2018-05-30 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-10462 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6046 | Spackenkill | N |  | 10.1 | [13 empty] | NM | N | 4 Enphase Energy IQ6-60-X-US (240V) 14 Enphase Energy IQ6-60-X-US (240V) 16 Enphase Energy IQ6-60-X-US (240V) 10 Enphase Energy IQ6-60-X-US (240V) | 2018-04-11 | 2018-04-17 | 4 | 2018-04-17 | [14 empty] | 2018-11-07 | 2018-11-13 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-10466 | Kingston | Mt Tremper | Ulster | 12457 | G | 3012 | Woodstock | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600A-US (240V) | 2018-04-11 | 2018-04-17 | 4 | 2018-04-17 | [14 empty] | 2018-05-17 | 2018-05-17 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-10464 | Fishkill | Wappingrs Fls |  | 12590 | G | 8045 | Myers Corners | N |  | 6.9 | [13 empty] | NM | N | 3 Enphase Energy IQ6-60-X-US (240V) 6 Enphase Energy IQ6-60-X-US (240V) 21 Enphase Energy IQ6-60-X-US (240V) | 2018-04-11 | 2018-04-17 | 4 | 2018-04-17 | [17 empty] | W
Central Hudson |  | New York State Solar Farm | CH-10470 | Poughkeepsie | Lagrangevl | Dutchess | 12540 | G | 6057 | Todd Hill | N |  | 8 | [13 empty] | NM | N | 25 SunPower SPR-X22-360-D-AC (240V) [SI1] | 2018-04-11 | 2018-04-17 | 4 | 2018-04-17 | [14 empty] | 2018-07-03 | 2018-07-05 |  | Y
Central Hudson |  | New York State Solar Farm | CH-10469 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 6051 | Todd Hill | N |  | 7 | [13 empty] | NM | N | 22 SunPower SPR-X22-360-D-AC (240V) | 2018-04-11 | 2018-04-17 | 4 | 2018-04-17 | [14 empty] | 2018-05-18 | 2018-05-21 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-10463 | Newburgh | Rock Tvrn | Orange | 12575 | G | 4097 | Bethlehem Rd | N |  | 12.8 | [13 empty] | NM | N | 40 SunPower SPR-X22-360-C-AC (240V) | 2018-04-11 | 2018-04-17 | 4 | 2018-04-17 | [14 empty] | 2018-06-29 | 2018-07-02 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-10465 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8094 | Fishkill Plains | N |  | 9 | [13 empty] | NM | N | 7 Enphase Energy IQ6-60-X-US (240V) 6 Enphase Energy IQ6-60-X-US (240V) 9 Enphase Energy IQ6-60-X-US (240V) 9 Enphase Energy IQ6-60-X-US (240V) 8 Enphase Energy IQ6-60-X-US (240V) | 2018-04-17 | 2018-04-17 | 0 | 2018-04-17 | [14 empty] | 2018-06-04 | 2018-06-07 |  | Y
Central Hudson |  | Lotus Energy Inc. | CH-10468 | Kingston | Esopus | Ulster | 12429 | G | 3041 | Sturgeon Pool | N |  | 7.7 | [13 empty] | NM | N | 24 SunPower SPR-E20-327-D-AC (240V) | 2018-04-11 | 2018-04-17 | 4 | 2018-04-17 | [14 empty] | 2018-04-27 | 2018-05-02 |  | Y
Central Hudson |  | Lighthouse Solar | CH-10460 | Newburgh | Highland | Ulster | 12528 | G | 5081 | Highland | N |  | 57.6 | [13 empty] | NM | N | 4SolaredgeSE14.4KUS (208V) | 2018-04-18 | 2018-05-02 | 10 | 2018-05-02 | 2018-05-02 | 2018-05-23 | 15 | [11 empty] | 2018-11-27 | 2018-11-27 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-10472 | Kingston | W Shokan | Ulster | 12494 | G | 3011 | Woodstock | N | CH-08739 | 6.7 | [13 empty] | NM | N | 10 Enphase Energy IQ6-60-X-US (240V) 10 Enphase Energy IQ6-60-X-US (240V) 9 Enphase Energy IQ6-60-X-US (240V) | 2018-05-07 | 2018-05-11 | 4 | 2018-05-11 | [14 empty] | 2018-07-17 | 2018-07-18 |  | Y
Central Hudson |  | New York State Solar Farm | CH-10473 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6003 | Reynolds Hill | N |  | 6.7 | [13 empty] | NM | N | 21 SunPower SPR-E20-327-D-AC (240V) | 2018-04-13 | 2018-04-18 | 3 | 2018-04-18 | [14 empty] | 2018-06-18 | 2018-06-28 |  | Y
Central Hudson |  | Tesla | CH-10474 | Kingston | Tillson | Ulster | 12486 | G | 3022 | High Falls | Y | CH-10144 |  | 5 | [12 empty] | NM | N | 1TeslaAC Powerwall 2.0 | 2018-04-13 | 2018-04-18 | 3 | 2018-04-18 | [8 empty] | 350 | 350 |  | 2018-04-25 | 2018-04-25 | 2018-06-04 | 2018-06-12 | 2018-06-13 |  | Y
Central Hudson |  | General Electric International, Inc | CH-10476 | Newburgh | Montgomery |  | 12549 | G | 4021 | Coldenham | TBD |  | 1755 | [13 empty] | RNM | N | 39 Huawei Technologies SUN2000-45KTL-US-HV-D0 | 2018-09-07 | 2018-09-10 | 1 | 2018-09-10 | 2018-09-10 | 2018-10-01 | 15 |  |  |  |  | 20000 | [9 empty] | W
Central Hudson |  | Tesla | CH-10475 | Newburgh | Highland | Ulster | 12528 | G | 5083 | Highland | N |  | 9 | [13 empty] | NM | N | 1 Delta Electronics SOLIVIA 3.8 NA G4 TL (240V) 1 Delta Electronics SOLIVIA 5.2 NA G4 TL (240V) | 2018-04-16 | 2018-04-18 | 2 | 2018-04-18 | [14 empty] | 2018-06-20 | 2018-06-26 |  | Y
Central Hudson |  | Green Power Solutions | CH-01169 | Poughkeepsie | Rhinebeck |  | 12572 | G | 7053 | Rhinebeck | Y |  | 3.1 | 3.1 | [12 empty] | NM | N | 1 Fronius USA Galvo 3.1-1 208-240 (240V) 1SonnenECO 61SonnenECO 6 | 2018-04-16 | 2018-04-17 | 1 | 2018-04-17 | [17 empty] | W
Central Hudson |  | Tesla | CH-10479 | Kingston | W Shokan | Ulster | 12494 | G | 3011 | Woodstock | Y | CH-08088 |  | 5 | [12 empty] | NM | N | 1TeslaAC Powerwall 2.0 | 2018-04-17 | 2018-04-19 | 2 | 2018-04-19 | [14 empty] | 2019-06-17 | 2019-06-18 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-10481 | Catskill | Earlton | Greene | 12058 | G | 2006 | North Catskill | N |  | 7.7 | [13 empty] | NM | N | 1SMASB7.7-1SP-US-40 (240V) [SI1] | 2018-04-17 | 2018-04-19 | 2 | 2018-04-19 | [14 empty] | 2018-09-24 | 2018-09-26 |  | Y
Central Hudson |  | Paradise Energy Solutions LLC | CH-10480 | Catskill | Lanesvl | Greene | 12450 | E | 2387 | NYSEG | N | CH-02830 | 6 | [13 empty] | NM | N | 1 SMA America SB6.0-1SP-US-40 (240V) | 2018-04-24 | 2018-04-24 | 0 | 2018-04-24 | [14 empty] | 2018-09-04 | 2018-09-05 |  | Y
Central Hudson |  | New York State Solar Farm | CH-10478 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6011 | Sand Dock | N |  | 6.4 | [13 empty] | NM | N | 20 SunPower SPR-X22-360-D-AC (240V) | 2018-04-17 | 2018-04-18 | 1 | 2018-04-18 | [14 empty] | 2018-06-29 | 2018-07-02 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-10477 | Poughkeepsie | Millerton | Dutchess | 12546 | G | 7081 | Millerton | N |  | 15.2 | [13 empty] | NM | N | 2 SolarEdge Technologies SE7600 (240V) | 2018-04-17 | 2018-04-18 | 1 | 2018-04-18 | [14 empty] | 2018-05-15 | 2018-05-18 |  | Y
Central Hudson |  | New York State Solar Farm | CH-10484 | Fishkill | Cold Spg | Putnam | 10516 | G | 8087 | Tioronda | N | CH-10484 | 6.7 | [13 empty] | NM | N | 21 SunPower SPR-E20-327-D-AC (240V) | 2018-04-20 | 2018-04-20 | 0 | 2018-04-20 | [14 empty] | 2018-05-29 | 2018-05-29 |  | Y
Central Hudson |  | Apex Solar Power | CH-10483 | Newburgh | Walden | Orange | 12586 | G | 5043 | East Walden | N |  | 9.9 | [13 empty] | NM | N | 1 SolarEdge Technologies SE 10000A-US (240V) | 2018-04-19 | 2018-04-19 | 0 | 2018-04-19 | [14 empty] | 2018-05-30 | 2018-05-30 |  | Y
Central Hudson |  | SolarCity DBA Tesla | CH-10486 | Kingston | Ellenvl | Ulster | 12428 | G | 3078 | Greenfield Rd | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2018-04-20 | 2018-04-24 | 2 | 2018-04-24 | [14 empty] | 2018-05-07 | 2018-05-08 |  | Y
Central Hudson |  | Hudson Solar | CH-10485 | Poughkeepsie | Salt Pt |  | 12578 | G | 7012 | Hibernia | N |  | 9.6 | [13 empty] | NM | N | 30 SunPower SPR-X20-327-D-AC (240V) [SI1] | 2018-04-20 | 2018-04-20 | 0 | 2018-04-20 | [8 empty] | 350 | 350 |  | 2018-04-23 | 2018-04-23 | 2018-05-07 |  |  |  | W
Central Hudson |  | Tesla | CH-10488 | Kingston | Kingston | Ulster | 12401 | G | 2016 | Lincoln Park | N |  | 9 | [13 empty] | NM | N | 1 Delta Electronics SOLIVIA 5.2 NA G4 TL (240V) 1 Delta Electronics SOLIVIA 3.8 NA G4 TL (240V) [SI1] | 2018-04-23 | 2018-04-24 | 1 | 2018-04-24 | [14 empty] | 2018-05-02 | 2018-05-03 |  | Y
Central Hudson |  | SolarCity DBA Tesla | CH-10487 | Kingston | Glenford | Ulster | 12433 | G | 3013 | Woodstock | Y | CH-08110 |  | 5 | [12 empty] | NM | N | 1TeslaAC Powerwall 2.0 | 2018-05-07 | 2018-05-10 | 3 | 2018-05-10 | [14 empty] | 2018-09-04 | 2018-09-05 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-10489 | Poughkeepsie | Rhinebeck |  | 12572 | G | 7055 | Rhinebeck | N |  | 10 | [13 empty] | NM | N | 1SolaredgeSE 10000A-US (240V) | 2018-04-25 | 2018-04-26 | 1 | 2018-04-26 | [17 empty] | W
Central Hudson |  | Solar Generation | CH-10491 | Kingston | Samsonvl | Ulster | 12461 | G | 3082 | Kerhonkson | N | CH-08143 | 12 | [13 empty] | NM | N | 2 SMA America SB6000US (240V) | 2018-04-24 | 2018-04-26 | 2 | 2018-04-26 | [14 empty] | 2018-05-25 | 2018-05-29 |  | Y
Central Hudson |  | Solar Generation | CH-10490 | Kingston | Lk Katrine | Ulster | 12449 | G | 2011 | Lincoln Park | N |  | 19.2 | [13 empty] | NM | N | 60 SunPower SPR-X22-360-D-AC (240V) [SI1] | 2018-04-24 | 2018-04-26 | 2 | 2018-04-26 | [8 empty] | 350 | 350 |  | 2018-04-26 | 2018-04-26 | 2018-06-04 | 2018-07-24 | 2018-07-31 |  | Y
Central Hudson |  | Monolith Solar Associates LLC | CH-10492 | Catskill | Coxsackie |  | 12051 | G | 1071 | Coxsackie | N |  | 150 | [13 empty] | CDG | Y | 5 SMA America STP30000TL-US-10 (480V) | 2018-05-09 | 2018-05-21 | 8 | 2018-05-21 | 2018-05-21 | 2018-06-11 | 14 | [14 empty] | W
Central Hudson |  | SELF | CH-10496 | Kingston | Saugerties | Ulster | 12477 | G | 1021 | East Kingston | N |  | 1 | [13 empty] | NM | N | 4 Enphase Energy | 2018-04-25 | 2018-04-26 | 1 | 2018-04-26 | [14 empty] | 2018-05-04 | 2018-05-04 |  | Y
Central Hudson |  | Tesla | CH-10498 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 6051 | Todd Hill | N |  | 10.4 | [13 empty] | NM | N | 2 Delta Electronics SOLIVIA 5.2 NA G4 TL (240V) | 2018-05-22 | 2018-05-29 | 4 | 2018-05-29 | [14 empty] | 2018-07-10 | 2018-07-11 |  | Y
Central Hudson |  | Sunrun Inc. | CH-10497 | Newburgh | Maybrook | Orange | 12543 | G | 4026 | Coldenham | N |  | 4.2 | [13 empty] | NM | N | 1 ABB PVI-4.2-OUTD-S-US-A (240V) | 2018-04-25 | 2018-04-26 | 1 | 2018-04-26 | [14 empty] | 2018-05-21 | 2018-05-25 |  | Y
Central Hudson |  | Kasselman Solar | CH-10493 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8051 | North Chelsea | N | CH-10493 | 7.84 | [13 empty] | NM | N | 28 Enphase Energy IQ6PLUS-72-x-US (240V) [SI1] | 2018-04-25 | 2018-04-26 | 1 | 2018-04-26 | [14 empty] | 2018-08-01 | 2018-08-10 |  | Y
Central Hudson |  | Kasselman Solar | CH-10494 | Catskill | Greenvl | Greene | 12083 | G | 2061 | Freehold | N |  | 10.1 | [13 empty] | NM | N | 36 Enphase Energy IQ6PLUS-72-X-US (240V) | 2018-04-25 | 2018-04-26 | 1 | 2018-04-26 | [14 empty] | 2018-06-01 | 2018-06-04 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-10495 | Newburgh | Newburgh |  | 12550 | G | 4024 | Coldenham | N |  | 11.5 | [13 empty] | NM | N | 36 SunPower SPR-X22-360-C-AC (240V) | 2018-04-25 | 2018-04-26 | 1 | 2018-04-26 | [17 empty] | W
Central Hudson |  | Lumens Holdings 3 LLC. | CH-10499 | Poughkeepsie | Poughkeepsie |  | 12601 | G | 7024 | Tinkertown | TBD |  | 1980 | [13 empty] | CDG | N | 33 Sungrow Power Supply SG60KU-M | 2018-06-08 | 2018-06-18 | 6 | 2018-06-18 | 2018-06-18 | 2018-07-10 | 15 | 2018-08-27 | 2018-10-31 | 2019-01-30 | 60 | 16154.96 | 360624 | [7 empty] | 2019-08-09 | W
Central Hudson |  | Lumens Holdings 3 LLC. | CH-10500 | Catskill | Cairo |  | 12413 | G | 2071 | Freehold | N |  | 1980 | [13 empty] | CDG | N | 33 Sungrow Power Supply SG60KU-M | 2018-09-26 | 2018-10-03 | 5 | 2018-10-03 | 2018-10-03 | 2018-10-22 | 13 | 2018-12-12 | 2019-01-30 | 2019-04-26 | 60 | 18415.63 | 443769 | [7 empty] | 2019-09-27 | W
Central Hudson |  | Lumens Holdings 3 LLC. | CH-10501 | Fishkill | East Fishkill |  | 12582 | G | 8093 | Fishkill Plains | TBD |  | 1980 | [13 empty] | CDG | N | 33 Sungrow Power Supply SG60KU-M | 2018-07-25 | 2018-08-06 | 8 | 2018-08-06 | 2018-08-06 | 2018-08-24 | 14 | 2018-10-26 | 2018-11-05 | 2019-02-04 | 60 | 27309.56 | 502423 | [7 empty] | 2019-08-09 | W
Central Hudson |  | Lumens Holdings 3 LLC. | CH-10502 | Catskill | Catskill |  | 12414 | G | 2001 | North Catskill | TBD |  | 1980 | [13 empty] | CDG | N | 33 Sungrow Power Supply SG60KU-M | 2018-06-04 | 2018-06-14 | 8 | 2018-06-14 | 2018-06-14 | 2018-07-05 | 14 | 2018-08-27 | 2018-10-31 | 2019-01-30 | 60 | 26352.64 | 476749 | [7 empty] | 2019-08-09 | W
Central Hudson |  | Lumens Holdings 3 LLC. | CH-10503 | Newburgh | Gardiner |  | 12561 | G | 5031 | Galeville | TBD |  | 1980 | [13 empty] | CDG | N | 33 Sungrow Power Supply SG60KU-M | 2018-05-30 | 2018-06-07 | 6 | 2018-06-07 | 2018-06-07 | 2018-06-28 | 15 | 2018-08-27 | 2018-10-31 | 2019-01-30 | 60 | 9878 | 161390 | [7 empty] | 2019-08-09 | W
Central Hudson |  | Trinity Solar | CH-10504 | Newburgh | Montgomery | Orange | 12549 | G | 5073 | Montgomery | N |  | 10 | [13 empty] | NM | N | 1SolaredgeSE10000A-US (240V) [SI1] | 2018-04-26 | 2018-04-27 | 1 | 2018-04-27 | [14 empty] | 2018-07-10 | 2018-07-10 |  | Y
Central Hudson |  | Tesla | CH-10509 | Fishkill | Fishkill | Dutchess | 12524 | G | 8094 | Fishkill Plains | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000H-US (208V) | 2018-04-27 | 2018-04-30 | 1 | 2018-04-30 | [14 empty] | 2018-05-17 | 2018-05-17 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-10505 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6046 | Spackenkill | N |  | 7.82 | [13 empty] | NM | N | 12 Enphase Energy IQ6-60-X-US (240V) 14 Enphase Energy IQ6-60-X-US (240V) 8 Enphase Energy IQ6-60-X-US (240V) | 2018-04-27 | 2018-04-30 | 1 | 2018-04-30 | [14 empty] | 2019-09-09 | 2019-09-13 |  | Y
Central Hudson |  | High Peaks Solar, LLC | CH-10506 | Catskill | Greenvl | Greene | 12083 | G | 1091 | Westerlo | N |  | 7.4 | [13 empty] | NM | N | 32 Enphase Energy IQ6-60-X-US (240V) | 2018-05-01 | 2018-05-03 | 2 | 2018-05-03 | [14 empty] | 2018-09-26 | 2018-09-27 |  | Y
Central Hudson |  | Lighthouse Solar | CH-10508 | Newburgh | Gardiner |  | 12525 | G | 5011 | Modena | N |  | 25 | [13 empty] | NM | N | 2SolaredgeSE 10000A-US (240V)1SolaredgeSE5000H-US (240V) | 2018-05-18 | 2018-05-18 | 0 | 2018-05-18 | [17 empty] | W
Central Hudson |  | Lumens Holdings 3 LLC | CH-10507 | Newburgh | Gardiner |  | 12561 | G | 5031 | Galeville | TBD |  | 1980 | [13 empty] | CDG | N | 33 Sungrow Power Supply SG60KU-M | 2018-05-30 | 2018-06-07 | 6 | 2018-06-07 | 2018-06-07 | 2018-06-28 | 15 | 2018-08-27 | 2018-10-31 | 2019-01-30 | 60 | 9878 | 161390 | [7 empty] | 2019-08-09 | W
Central Hudson |  | Solar Liberty Energy Systems | CH-10510 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6095 | Manchester | N | CH-04905 | 3 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3000 (240V) | 2018-05-22 | 2018-05-29 | 4 | 2018-05-29 | [14 empty] | 2018-06-19 | 2018-06-19 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-10511 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8044 | Myers Corners | N | CH-10511 | 3.2 | [13 empty] | NM | N | 14 Enphase Energy IQ6-60-X-US (240V) | 2018-04-30 | 2018-05-03 | 3 | 2018-05-03 | [14 empty] | 2018-06-20 | 2018-06-21 |  | Y
Central Hudson |  | SolarCity DBA Tesla | CH-10516 | Newburgh | Newburgh | Orange | 12550 | G | 4023 | Coldenham | N |  | 6 | [13 empty] | NM | N | 1 ABB PVI-6000-OUTD-US-Z-A (240V) | 2018-05-01 | 2018-05-03 | 2 | 2018-05-03 | [14 empty] | 2018-12-11 | 2018-12-12 |  | Y
Central Hudson |  | SolarCity DBA Tesla | CH-10515 | Newburgh | Marlboro | Ulster | 12542 | G | 5001 | Marlboro | N |  | 6 | [13 empty] | NM | N | 1 ABB PVI-6000-OUTD-US-Z-A (240V) | 2018-05-07 | 2018-05-10 | 3 | 2018-05-10 | [14 empty] | 2018-06-18 | 2018-06-20 |  | Y
Central Hudson |  | Hudson Solar | CH-10513 | Kingston | Saugerties | Ulster | 12477 | G | 3003 | Saugerties | N |  | 9.9 | [13 empty] | NM | N | 9 SunPower SPR-E20-327-D-AC (240V) 22 SunPower SPR-E20-327-D-AC (240V) | 2018-05-16 | 2018-05-25 | 7 | 2018-05-25 | [8 empty] | 350 | 350 |  | 2018-06-04 | 2018-06-04 | 2018-06-29 | 2018-07-03 | 2018-07-13 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-10514 | Newburgh | Newburgh | Orange | 12550 | G | 4023 | Coldenham | N |  | 5.8 | [13 empty] | NM | N | 18 SunPower SPR-X22-360-D-AC (240V) | 2018-05-01 | 2018-05-03 | 2 | 2018-05-03 | [14 empty] | 2018-07-13 | 2018-07-17 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-10521 | Fishkill | Hughsonvl | Dutchess | 12537 | G | 8052 | North Chelsea | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000 (240V) | 2018-05-02 | 2018-05-03 | 1 | 2018-05-03 | [14 empty] | 2018-06-15 | 2018-06-28 |  | Y
Central Hudson |  | SolarCity DBA Tesla | CH-10518 | Kingston | Shady | Ulster | 12409 | G | 3012 | Woodstock | Y | CH-10518 | 5.2 | [13 empty] | NM | N | 1 Delta Electronics SOLIVIA 5.2 NA G4 TL (240V) | 2018-05-07 | 2018-05-10 | 3 | 2018-05-10 | [14 empty] | 2018-05-10 | 2018-05-15 |  | Y
Central Hudson |  | Hudson Solar | CH-10517 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 6051 | Todd Hill | N |  | 6.4 | [13 empty] | NM | N | 20 SunPower SPR-E20-327-D-AC (240V) [SI1] | 2018-05-02 | 2018-05-03 | 1 | 2018-05-03 | [14 empty] | 2018-10-01 | 2018-10-01 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-10520 | Poughkeepsie | Lagrangevl |  | 12540 | G | 6057 | Todd Hill | TBD |  | 7.7 | [13 empty] | NM | N | 24 SunPower SPR-X22-360-D-AC (240V) | 2018-05-03 | 2018-05-04 | 1 | 2018-05-04 | [17 empty] | W
Central Hudson |  | Infinity Solar Systems | CH-10519 | Newburgh | Rock Tvrn | Orange | 12575 | G | 4097 | Bethlehem Rd | N |  | 8.3 | [13 empty] | NM | N | 26 SunPower SPR-X22-360-D-AC (240V) | 2018-05-02 | 2018-05-03 | 1 | 2018-05-03 | [14 empty] | 2018-07-13 | 2018-07-17 |  | Y
Central Hudson |  | Lighthouse Solar | CH-10522 | Kingston | Kerhonkson | Ulster | 12446 | G | 3082 | Kerhonkson | N |  | 20 | [13 empty] | NM | N | 2SolaredgeSE 10000A-US (240V) | 2018-05-04 | 2018-05-04 | 0 | 2018-05-04 | [14 empty] | 2018-05-18 | 2018-05-29 |  | Y
Central Hudson |  | SolarCity DBA Tesla | CH-10525 | Fishkill | Cold Spg | Putnam | 10516 | G | 8063 | Merritt Park | N |  | 7.6 | [13 empty] | NM | N | 1 Delta Electronics SOLIVIA 7.6 NA G4 TL (240V) | 2018-05-18 | 2018-05-18 | 0 | 2018-05-18 | [14 empty] | 2018-10-03 | 2018-10-04 |  | Y
Central Hudson |  | New York State Solar Farm | CH-10524 | Newburgh | Wallkill | Ulster | 12589 | G | 5043 | East Walden | N |  | 9 | [13 empty] | NM | N | 28 SunPower SPR-X22-360-D-AC (240V) [SI1] | 2018-05-18 | 2018-05-29 | 6 | 2018-05-29 | [14 empty] | 2018-06-05 | 2018-06-14 |  | Y
Central Hudson |  | New York State Solar Farm | CH-10523 | Newburgh | Milton | Ulster | 12547 | G | 5083 | Highland | N |  | 6.4 | [13 empty] | NM | N | 20 SunPower SPR-E20-327-D-AC (240V) | 2018-05-04 | 2018-05-04 | 0 | 2018-05-04 | [14 empty] | 2018-05-16 | 2018-05-17 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-10526 | Kingston | Kerhonkson |  | 12446 | G | 3083 | Kerhonkson | N |  | 1.8 | [13 empty] | NM | N | 2 Enphase Energy IQ6-60-X-US (240V) 6 Enphase Energy IQ6-60-X-US (240V) | 2018-05-08 | 2018-05-09 | 1 | 2018-05-09 | [17 empty] | W
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-10527 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8071 | Shenandoah | N |  | 7.1 | [13 empty] | NM | N | 31 Enphase Energy IQ6-60-X-US (240V) | 2018-05-04 | 2018-05-10 | 4 | 2018-05-10 | [14 empty] | 2018-06-29 | 2018-06-29 |  | Y
Central Hudson |  | Hudson Solar | CH-10529 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 6074 | East Park | N |  | 5.1 | [13 empty] | NM | N | 16 SunPower SPR-E20-327-D-AC (240V) | 2018-05-25 | 2018-05-29 | 1 | 2018-05-29 | [14 empty] | 2018-06-27 | 2018-07-03 |  | Y
Central Hudson |  | New York State Solar Farm | CH-10528 | Poughkeepsie | Clinton Corners | Dutchess | 12514 | G | 7013 | Hibernia | N | CH-10528 | 8.82 | [13 empty] | NM | N | 28 SunPower SPR-X21-350-BLK-D-AC (240V) | 2018-05-07 | 2018-05-10 | 3 | 2018-05-10 | [14 empty] | 2018-05-29 | 2018-05-30 |  | Y
Central Hudson |  | Kasselman Solar | CH-10531 | Kingston | Saugerties | Ulster | 12477 | G | 3014 | Woodstock | N |  | 6.2 | [13 empty] | NM | N | 27 Enphase Energy IQ6-60-X-US (240V) | 2018-05-08 | 2018-05-14 | 4 | 2018-05-14 | [14 empty] | 2018-05-21 | 2018-05-25 |  | Y
Central Hudson |  | Solar Image, LLC | CH-10533 | Newburgh | Wallkill | Ulster | 12589 | G | 5041 | East Walden | N |  | 5 | [13 empty] | NM | N | 1 SMA America SB5000US-11 (240V) | 2018-05-16 | 2018-05-16 | 0 | 2018-05-16 | [14 empty] | 2018-05-21 | 2018-05-29 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-10532 | Poughkeepsie | Poughkeepsie |  | 12603 | G | 6093 | Manchester | TBD |  | 5.8 | [13 empty] | NM | N | 18 SunPower SPR-X22-360-D-AC (240V) | 2018-05-08 | 2018-05-21 | 9 | 2018-05-21 | [17 empty] | W
Central Hudson |  | Lighthouse Solar | CH-10534 | Fishkill | Cold Spg | Putnam | 10516 | G | 8063 | Merritt Park | N |  | 3.8 | [13 empty] | NM | N | 1SolaredgeSE3800H-US (240V) | 2018-05-08 | 2018-05-14 | 4 | 2018-05-14 | [14 empty] | 2018-10-03 | 2018-10-08 |  | Y
Central Hudson |  | New York State Solar Farm | CH-10535 | Fishkill | Beacon | Dutchess | 12508 | G | 8085 | Tioronda | N |  | 5.4 | [13 empty] | NM | N | 17 SunPower SPR-X22-360-D-AC (240V) | 2018-05-09 | 2018-05-14 | 3 | 2018-05-14 | [14 empty] | 2018-06-29 | 2018-07-02 |  | Y
Central Hudson |  | Lighthouse Solar | CH-10536 | Kingston | Kingston | Ulster | 12401 | G | 1014 | Boulevard | N |  | 10 | [13 empty] | NM | N | 1SolaredgeSE 10000A-US (240V) | 2018-05-09 | 2018-05-14 | 3 | 2018-05-14 | [14 empty] | 2018-06-22 | 2018-06-25 |  | Y
Central Hudson |  | Green Street Power Partners, LLC | CH-10425 | Newburgh | New Windsor | Orange | 12553 | G | 4097 | Bethlehem Rd | N |  | 3000 | [13 empty] | CDG | Y | 35SungrowSungrow SG125-HV | 2019-01-16 | 2019-01-30 | 10 | 2019-01-30 | 2019-01-30 | 2019-02-21 | 15 | 2019-04-30 | 2019-05-08 | 2019-08-15 | 69 | 3546.69 | 368809 | 528934.03 | 2019-12-26 | 2020-09-10 | 2020-09-10 | 2021-12-21 | 2022-07-22 | 2022-07-26 | 2022-10-26 | Y | Y | CESIR placed on hold due to awaiting documentation from applicant, new due date 8/15/19.
Central Hudson |  | Green Street Power Partners, LLC | CH-10426 | Newburgh | New Windsor | Orange | 12553 | G | 4097 | Bethlehem Rd | N |  | 4125 | [13 empty] | CDG | Y | 33 Sungrow Power Supply SG125HV (600V) 40SungrowSungrow SG125-HV | 2019-01-02 | 2019-01-16 | 10 | 2019-01-16 | 2019-01-16 | 2019-02-04 | 13 | 2019-02-21 | 2019-05-08 | 2019-08-15 | 69 | 16246.68 | 368808 | 431986.21 | 2019-12-26 | 2020-09-09 | 2020-09-09 | 2021-12-21 | 2022-07-22 | 2022-07-26 | 2022-10-26 | Y | Y | CESIR placed on hold due to awaiting documentation from applicant, new due date 8/15/19.
Central Hudson |  | Empire Solar Solutions | CH-10537 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8024 | Knapps Corners | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000 (240V) | 2018-05-10 | 2018-05-14 | 2 | 2018-05-14 | [14 empty] | 2018-06-15 | 2018-06-18 |  | Y
Central Hudson |  | New York State Solar Farm | CH-10538 | Newburgh | Walden | Orange | 12586 | G | 4026 | Coldenham | N |  | 8.6 | [13 empty] | NM | N | 27 SunPower SPR-E20-327-D-AC (240V) | 2018-05-10 | 2018-05-14 | 2 | 2018-05-14 | [14 empty] | 2018-07-09 | 2018-07-09 |  | Y
Central Hudson |  | SolarCity DBA Tesla | CH-10539 | Poughkeepsie | Ancramdale | Columbia | 12503 | G | 7092 | Pulvers Corners | N |  | 3.6 | [13 empty] | NM | N | 1 ABB PVI-3.6-OUTD-S-US-Z-A (240V) | 2018-05-11 | 2018-05-14 | 1 | 2018-05-14 | [14 empty] | 2018-07-06 | 2018-07-06 |  | Y
Central Hudson |  | SolarCity DBA Tesla | CH-10540 | Newburgh | Campbell Hall | Orange | 10916 | G | 5051 | Maybrook | N |  | 6.6 | [13 empty] | NM | N | 1 Delta Electronics SOLIVIA 6.6 NA G4 TL (240V) | 2018-05-21 | 2018-05-29 | 5 | 2018-05-29 | [14 empty] | 2018-07-10 | 2018-07-11 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-10541 | Kingston | Ulster Pk | Ulster | 12487 | G | 1023 | East Kingston | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600A-US (240V) | 2018-05-15 | 2018-05-15 | 0 | 2018-05-15 | [14 empty] | 2018-05-15 | 2018-05-18 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-10542 | Newburgh | Newburgh | Orange | 12550 | G | 4051 | Union Ave | N |  | 5.4 | [13 empty] | NM | N | 17 SunPower SPR-X22-360-C-AC (240V) | 2018-05-14 | 2018-05-14 | 0 | 2018-05-14 | [14 empty] | 2018-08-02 | 2018-08-06 |  | Y
Central Hudson |  | murphysolarandcentralair | CH-10544 | Catskill | Athens | Greene | 12015 | G | 2002 | North Catskill | N |  | 7.6 | [13 empty] | NM | N | 1 Fronius International Fronius Primo 7.6-1 208-240 (208V) [SI1] | 2018-05-14 | 2018-05-14 | 0 | 2018-05-14 | [14 empty] | 2018-07-26 | 2018-07-26 |  | Y
Central Hudson |  | Sunrun Inc. | CH-10546 | Newburgh | Montgomery | Orange | 12549 | G | 5073 | Montgomery | N |  | 10 | [13 empty] | NM | N | 1SolaredgeSE10000A-US (240V) [SI1] | 2018-05-15 | 2018-05-15 | 0 | 2018-05-15 | [8 empty] | 350 | 350 |  | 2018-05-29 | 2018-05-29 | 2018-06-11 | 2018-07-26 | 2018-08-03 |  | Y
Central Hudson |  | Solar Generation | CH-10543 | Kingston | Woodstock | Ulster | 12498 | G | 3013 | Woodstock | N |  | 6.4 | [13 empty] | NM | N | 20 SunPower SPR-X22-360-D-AC (240V) [SI1] | 2018-05-14 | 2018-05-14 | 0 | 2018-05-14 | [14 empty] | 2018-07-30 | 2018-07-30 |  | Y
Central Hudson |  | CVE North America, Inc. | CH-10545 | Kingston | Kerhonkson |  | 12446 | G | 3071 | Honk Falls | N |  | 5000 | [13 empty] | CDG | N | 40 Sungrow Power Supply SG125HV (600V) | 2018-06-27 | 2018-07-10 | 8 | 2018-07-10 | 2018-07-10 | 2018-07-31 | 15 | 2018-08-23 | 2018-10-12 | 2019-01-11 | 60 | 28329.97 | 220739 | 1804.5 | 2019-03-19 | [5 empty] | 2019-12-05 | W
Central Hudson |  | murphysolarandcentralair | CH-10554 | Catskill | Athens | Greene | 12015 | G | 2002 | North Catskill | N |  | 7.6 | [13 empty] | NM | N | 1 Fronius International Fronius Primo 7.6-1 208-240 (240V) [SI1] | 2018-05-15 | 2018-05-16 | 1 | 2018-05-16 | [14 empty] | 2018-07-26 | 2018-07-26 |  | Y
Central Hudson |  | PlugPV, LLC. | CH-10547 | Kingston | Saugerties | Ulster | 12477 | G | 2015 | Lincoln Park | N |  | 10 | [13 empty] | NM | N | 1SolaredgeSE 10000A-US (240V) | 2018-05-15 | 2018-05-15 | 0 | 2018-05-15 | [14 empty] | 2018-06-20 | 2018-06-21 |  | Y
Central Hudson |  | Tesla | CH-10553 | Kingston | Olive Brdg | Ulster | 12461 | G | 3024 | High Falls | Y |  | 3.6 | 5 | [12 empty] | NM | N | 1 ABB PVI-3.6-OUTD-US (240 V) 1TeslaAC Powerwall 2.0 | 2018-05-17 | 2018-05-25 | 6 | 2018-05-25 | [8 empty] | 350 | 350 |  | 2018-06-01 | 2018-06-01 | 2018-08-15 | 2018-08-24 | 2018-08-29 |  | Y
Central Hudson |  | Tesla | CH-10551 | Poughkeepsie | Lagrangevl | Dutchess | 12540 | G | 6052 | Todd Hill | Y | CH-06725 |  | 10 | [12 empty] | NM | N | 2TeslaAC Powerwall 2.0 | 2018-05-15 | 2018-05-15 | 0 | 2018-05-15 | [14 empty] | 2019-04-05 | 2019-04-05 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-10550 | Newburgh | Newburgh | Orange | 12550 | G | 4011 | West Balmville | N |  | 9.3 | [13 empty] | NM | N | 29 SunPower SPR-X22-360-D-AC (240V) | 2018-05-15 | 2018-05-15 | 0 | 2018-05-15 | [14 empty] | 2018-07-23 | 2018-07-26 |  | Y
Central Hudson |  | PlugPV, LLC. | CH-10548 | Kingston | Saugerties | Ulster | 12477 | G | 3002 | Saugerties | N |  | 10 | [13 empty] | NM | N | 1SolaredgeSE 10000A-US (240V) | 2018-05-15 | 2018-05-15 | 0 | 2018-05-15 | [14 empty] | 2018-06-25 | 2018-06-25 |  | Y
Central Hudson |  | Tesla | CH-10552 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6045 | Spackenkill | Y | CH-10552 | 3.3 | [13 empty] | NM | N | 1 ABB UNO-DM-3.3-TL-PLUS-US-SZ-RA (240V) [SI1] | 2018-05-15 | 2018-05-15 | 0 | 2018-05-15 | [14 empty] | 2018-06-20 | 2018-06-20 |  | Y
Central Hudson |  | SELF | CH-10549 | Kingston | Bearsvl | Ulster | 12409 | G | 3012 | Woodstock | Y |  | 3.3 | 3.3 | [12 empty] | NM | N | 1 Xantrex Technology SW4024 (120V) 1XantrexSW4024 (DC) | 2018-05-15 | 2018-05-15 | 0 | 2018-05-15 | [14 empty] | 2018-05-24 | 2018-05-25 |  | Y
Central Hudson |  | New York State Solar Farm | CH-10558 | Newburgh | Gardiner | Ulster | 12525 | G | 5031 | Galeville | N | CH-00442 | 2.9 | [13 empty] | NM | N | 9 SunPower SPR-E20-327-D-AC (240V) | 2018-05-16 | 2018-05-25 | 7 | 2018-05-25 | [14 empty] | 2018-06-14 | 2018-06-14 |  | Y
Central Hudson |  | Kasselman Solar | CH-10555 | Catskill | Hunter | Greene | 12442 | E | 2081 | Hunter | N |  | 6.4 | [13 empty] | NM | N | 28 Enphase Energy IQ6-60-X-US (240V) | 2018-05-16 | 2018-05-16 | 0 | 2018-05-16 | [14 empty] | 2018-11-15 | 2018-11-19 |  | Y
Central Hudson |  | Tesla | CH-10557 | Newburgh | New Paltz | Ulster | 12561 | G | 5011 | Modena | N |  | 6.6 | [13 empty] | NM | N | 1 Delta Electronics SOLIVIA 6.6 NA G4 TL (240V) | 2018-05-16 | 2018-05-16 | 0 | 2018-05-16 | [14 empty] | 2018-05-29 | 2018-05-30 |  | Y
Central Hudson |  | Tesla | CH-10556 | Kingston | Willow | Ulster | 12495 | G | 3012 | Woodstock | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) [SI1] | 2018-05-16 | 2018-05-16 | 0 | 2018-05-16 | [14 empty] | 2018-07-11 | 2018-07-18 |  | Y
Central Hudson |  | New York State Solar Farm | CH-10559 | Newburgh | Modena | Ulster | 12548 | G | 5012 | Modena | N |  | 55.4 | [13 empty] | NM | N | 3 SolarEdge Technologies SE 11400A-US (240V) 2 SolarEdge Technologies SE7600A-US (240V) 1 SolarEdge Technologies SE6000 (240V) | 2018-05-31 | 2018-06-13 | 9 | 2018-06-13 | 2018-06-13 | 2018-07-05 | 15 | [5 empty] | 3755 | 2073.81 |  | 2018-07-13 | 2018-07-13 | 2018-09-05 | 2018-10-03 | 2018-10-03 | 2018-10-03 | Y
Central Hudson |  | PlugPV, LLC. | CH-10561 | Kingston | Saugerties | Ulster | 12477 | G | 3002 | Saugerties | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600A-US (240V) | 2018-05-17 | 2018-05-18 | 1 | 2018-05-18 | [14 empty] | 2018-05-18 | 2018-05-25 |  | Y
Central Hudson |  | Tesla | CH-10565 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8091 | Fishkill Plains | N | CH-10565 | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE 11400A-US (240V) | 2018-05-17 | 2018-05-18 | 1 | 2018-05-18 | [14 empty] | 2018-05-21 | 2018-05-25 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-10562 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6043 | Spackenkill | N |  | 17.7 | [13 empty] | NM | N | 4 Enphase Energy IQ6-60-X-US (240V) 3 Enphase Energy IQ6-60-X-US (240V) 31 Enphase Energy IQ6-60-X-US (240V) 9 Enphase Energy IQ6-60-X-US (240V) 30 Enphase Energy IQ6-60-X-US (240V) | 2018-05-17 | 2018-05-18 | 1 | 2018-05-18 | [14 empty] | 2018-08-14 | 2018-08-24 |  | Y
Central Hudson |  | Tri-State Solar Services | CH-10563 | Newburgh | Montgomery | Orange | 12549 | G | 5054 | Maybrook | N |  | 10 | [13 empty] | NM | N | 1SolaredgeSE 10000A-US (240V) | 2018-06-08 | 2018-06-15 | 5 | 2018-06-15 | [14 empty] | 2018-06-22 | 2018-06-27 |  | Y
Central Hudson |  | PlugPV, LLC. | CH-10560 | Catskill | Coxsackie | Greene | 12051 | G | 1076 | Coxsackie | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600A-US (240V) | 2018-05-17 | 2018-05-18 | 1 | 2018-05-18 | [14 empty] | 2018-07-24 | 2018-07-24 |  | Y
Central Hudson |  | PlugPV, LLC. | CH-10564 | Kingston | Kingston | Ulster | 12401 | G | 1021 | East Kingston | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600 (240V) | 2018-05-17 | 2018-05-18 | 1 | 2018-05-18 | [14 empty] | 2018-07-20 | 2018-07-20 |  | Y
Central Hudson |  | SolarCity DBA Tesla | CH-10570 | Newburgh | New Paltz | Ulster | 12561 | G | 5023 | Ohioville | N |  | 3.6 | [13 empty] | NM | N | 1 ABB PVI-3.6-OUTD-S-US-Z-A (240V) | 2018-05-22 | 2018-05-29 | 4 | 2018-05-29 | [14 empty] | 2018-07-10 | 2018-07-11 |  | Y
Central Hudson |  | PlugPV, LLC. | CH-10567 | Kingston | Saugerties | Ulster | 12477 | G | 3002 | Saugerties | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600A-US (240V) | 2018-05-18 | 2018-05-18 | 0 | 2018-05-18 | [14 empty] | 2018-06-05 | 2018-06-15 |  | Y
Central Hudson |  | Kasselman Solar | CH-10566 | Poughkeepsie | Lagrangevl | Dutchess | 12540 | G | 6052 | Todd Hill | N |  | 11 | [13 empty] | NM | N | 48 Enphase Energy IQ6-60-X-US (240V) | 2018-05-18 | 2018-05-18 | 0 | 2018-05-18 | [14 empty] | 2018-06-20 | 2018-07-03 |  | Y
Central Hudson |  | Tesla | CH-10573 | Fishkill | Fishkill | Dutchess | 12524 | G | 8062 | Merritt Park | N |  | 3 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3000H-US (240V) [SI1] | 2018-05-18 | 2018-05-29 | 6 | 2018-05-29 | [14 empty] | 2018-06-20 | 2018-06-20 |  | Y
Central Hudson |  | New York State Solar Farm | CH-10571 | Newburgh | Highland | Ulster | 12528 | G | 5083 | Highland | N |  | 13.1 | [13 empty] | NM | N | 41 SunPower SPR-E20-327-D-AC (240V) | 2018-05-18 | 2018-05-29 | 6 | 2018-05-29 | [14 empty] | 2018-06-11 | 2018-06-11 |  | Y
Central Hudson |  | New York State Solar Farm | CH-10572 | Newburgh | Newburgh | Orange | 12550 | G | 5041 | East Walden | N |  | 10.9 | [13 empty] | NM | N | 34 SunPower SPR-X22-360-D-AC (240V) | 2018-05-18 | 2018-05-29 | 6 | 2018-05-29 | [14 empty] | 2018-06-11 | 2018-06-11 |  | Y
Central Hudson |  | murphysolarandcentralair | CH-10574 | Catskill | Acra | Greene | 12405 | G | 2041 | South Cairo | N |  | 3 | [13 empty] | NM | N | 1 SMA America SB3000US (240V) | 2018-05-21 | 2018-05-29 | 5 | 2018-05-29 | [14 empty] | 2018-07-26 | 2018-07-26 |  | Y
Central Hudson |  | Kasselman Solar | CH-10575 | Kingston | Kingston | Ulster | 12401 | G | 1012 | Boulevard | N |  | 3.7 | [13 empty] | NM | N | 16 Enphase Energy IQ6-60-X-US (240V) | 2018-05-21 | 2018-05-29 | 5 | 2018-05-29 | [14 empty] | 2018-07-18 | 2018-07-23 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-10576 | Fishkill | Stormvl | Dutchess | 12582 | G | 8071 | Shenandoah | N |  | 12.4 | [13 empty] | NM | N | 27 Enphase Energy IQ6-60-X-US (240V) 27 Enphase Energy IQ6-60-X-US (240V) | 2018-05-21 | 2018-05-29 | 5 | 2018-05-29 | [14 empty] | 2018-08-13 | 2018-08-14 |  | Y
Central Hudson |  | Trinity Solar | CH-10577 | Kingston | Stone Ridge | Ulster | 12484 | G | 3023 | High Falls | N | CH-10577 | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2018-06-13 | 2018-06-14 | 1 | 2018-06-14 | [14 empty] | 2018-08-28 | 2018-08-31 |  | Y
Central Hudson |  | Tesla | CH-10581 | Newburgh | Highland | Ulster | 12528 | G | 5083 | Highland | N |  | 5 | [13 empty] | NM | N | 1 ABB PVI-5000-OUTD-US-Z-A (240V) | 2018-05-22 | 2018-05-29 | 4 | 2018-05-29 | [14 empty] | 2018-06-18 | 2018-06-19 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-10578 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8094 | Fishkill Plains | N |  | 5.5 | [13 empty] | NM | N | 24 Enphase Energy IQ6-60-X-US (240V) | 2018-05-22 | 2018-05-29 | 4 | 2018-05-29 | [14 empty] | 2018-09-12 | 2018-09-13 |  | Y
Central Hudson |  | Novel Approaches | CH-10579 | Kingston | Grahamsvl | Sullivan | 12740 | G | 3091 | Neversink | N |  | 37.5 | [13 empty] | NM | N | 2 Fronius USA Fronius Primo 12.5-1 (240V) 1 Fronius USA Fronius Primo 12.5-1 (240V) | 2018-10-16 | 2018-10-17 | 1 | 2018-10-17 | [14 empty] | 2018-10-31 | 2018-10-31 |  | Y
Central Hudson |  | Freedom Solar, LLC | CH-10580 | Kingston | Ellenvl | Ulster | 12428 | G | 3078 | Greenfield Rd | N |  | 10.5 | [13 empty] | NM | N | 21 Altenergy Power System YC500A (240V) | 2018-06-12 | 2018-06-14 | 2 | 2018-06-14 | [14 empty] | 2018-07-10 | 2018-07-11 |  | Y
Central Hudson |  | SolarCity DBA Tesla | CH-10582 | Fishkill | Stormvl | Dutchess | 12582 | G | 8071 | Shenandoah | N |  | 11.4 | [13 empty] | NM | N | 1 Delta Electronics SOLIVIA 7.6 NA G4 TL (240V) 1 Delta Electronics SOLIVIA 3.8 NA G4 TL (240V) | 2018-05-23 | 2018-05-29 | 3 | 2018-05-29 | [14 empty] | 2018-05-29 | 2018-06-05 |  | Y
Central Hudson |  | Lotus Energy Inc. | CH-10583 | Catskill | Haines Fls | Greene | 12436 | G | 2385 | Lawrenceville | N |  | 3.8 | [13 empty] | NM | N | 12 SunPower SPR-X20-327-D-AC (240V) | 2018-05-23 | 2018-05-29 | 3 | 2018-05-29 | [14 empty] | 2018-06-04 | 2018-06-05 |  | Y
Central Hudson |  | Tesla | CH-10584 | Newburgh | Highland | Ulster | 12528 | G | 5022 | Ohioville | Y | CH-10584 | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2018-06-01 | 2018-06-04 | 1 | 2018-06-04 | [14 empty] | 2018-08-03 | 2018-08-03 |  | Y
Central Hudson |  | New York State Solar Farm | CH-10585 | Kingston | Kingston | Ulster | 12401 | G | 3023 | High Falls | N |  | 5.1 | [13 empty] | NM | N | 16 SunPower SPR-E20-327-D-AC (240V) | 2018-05-23 | 2018-05-29 | 3 | 2018-05-29 | [14 empty] | 2018-06-05 | 2018-06-06 |  | Y
Central Hudson |  | Tesla | CH-10590 | Poughkeepsie | Salt Pt | Dutchess | 12578 | G | 7011 | Hibernia | Y | CH-05254 |  | 5 | [12 empty] | NM | N | 1TeslaAC Powerwall 2.0 | 2018-05-29 | 2018-05-29 | 0 | 2018-05-29 | [8 empty] | 350 | 350 |  | 2018-06-04 | 2018-06-04 | 2018-08-02 | 2018-10-10 | 2018-10-11 |  | Y
Central Hudson |  | Environomics.co | CH-10482 | Newburgh | Wallkill |  | 12589 | G | 5043 | East Walden | N |  | 4400 | [13 empty] | CDG | N | 2 SMA America SC-2200-US (385V) | 2018-08-24 | 2018-08-31 | 5 | 2018-08-31 | 2018-08-31 | 2018-09-18 | 11 | 2018-11-30 | 2019-02-12 | 2019-05-09 | 60 | 18236.72 | 5532611.25 | [7 empty] | 2019-09-27 | W
Central Hudson |  | Sunrun Inc. | CH-10589 | Newburgh | Cornwall-Hdsn | Orange | 12520 | G | 4043 | Union Ave | N |  | 5 | [13 empty] | NM | N | 1SolaredgeSE5000H-US (240V) | 2018-05-24 | 2018-05-29 | 2 | 2018-05-29 | [14 empty] | 2018-06-15 | 2018-06-18 |  | Y
Central Hudson |  | Tesla | CH-10588 | Kingston | Olive Brdg | Ulster | 12461 | G | 3082 | Kerhonkson | N |  | 5.2 | [13 empty] | NM | N | 1 Delta Electronics SOLIVIA 5.2 NA G4 TL (240V) | 2018-05-24 | 2018-05-29 | 2 | 2018-05-29 | [14 empty] | 2018-06-20 | 2018-06-22 |  | Y
Central Hudson |  | Tesla | CH-10587 | Newburgh | New Windsor | Orange | 12553 | G | 4042 | Union Ave | N |  | 17.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000A-US (240V) [SI1] 1 SolarEdge Technologies SE7600H-US (240V) | 2018-05-24 | 2018-05-29 | 2 | 2018-05-29 | [8 empty] | 350 | 350 |  | 2018-06-04 | 2018-06-04 | 2018-06-15 | 2018-09-10 | 2018-09-11 |  | Y
Central Hudson |  | Hudson Solar | CH-10586 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6092 | Manchester | N |  | 8 | [13 empty] | NM | N | 25 SunPower SPR-E20-327-D-AC (240V) | 2018-05-24 | 2018-05-29 | 2 | 2018-05-29 | [14 empty] | 2018-07-03 | 2018-07-06 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-10592 | Fishkill | Stormvl | Dutchess | 12582 | G | 8071 | Shenandoah | N |  | 17 | [13 empty] | NM | N | 25 Enphase Energy IQ6-60-X-US (240V) 12 Enphase Energy IQ6-60-X-US (240V) 28 Enphase Energy IQ6-60-X-US (240V) 9 Enphase Energy IQ6-60-X-US (240V) | 2018-05-25 | 2018-05-29 | 1 | 2018-05-29 | [8 empty] | 350 | 350 |  | 2018-06-28 | 2018-06-28 | 2018-07-10 | 2018-08-10 | 2018-08-15 |  | Y
Central Hudson |  | Kasselman Solar | CH-10591 | Catskill | Hannacroix | Greene | 12087 | G | 1071 | Coxsackie | N |  | 8.1 | [13 empty] | NM | N | 29 Enphase Energy IQ6PLUS-72-X-US (240V) | 2018-05-25 | 2018-05-29 | 1 | 2018-05-29 | [14 empty] | 2018-07-10 | 2018-07-12 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-10593 | Kingston | W Hurley | Ulster | 12491 | G | 3013 | Woodstock | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000 (240V) | 2018-05-25 | 2018-05-29 | 1 | 2018-05-29 | [14 empty] | 2018-06-08 | 2018-06-13 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-10594 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8092 | Fishkill Plains | N |  | 14.3 | [13 empty] | NM | N | 62 Enphase Energy IQ6-60-X-US (240V) | 2018-07-05 | 2018-07-05 | 0 | 2018-07-05 | [14 empty] | 2018-09-24 | 2018-09-24 |  | Y
Central Hudson |  | SunDog Solar | CH-10596 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6095 | Manchester | N |  | 27.6 | [13 empty] | NM | N | 120 Enphase Energy IQ6-60-X-US (208V) | 2018-07-10 | 2018-07-17 | 5 | 2018-07-17 | [14 empty] | 2018-11-27 | 2018-11-28 |  | Y
Central Hudson |  | Apex Solar Power | CH-10595 | Newburgh | Newburgh | Orange | 12550 | G | 4023 | Coldenham | N |  | 10 | [13 empty] | NM | N | 1SolaredgeSE 10000A-US (240V) | 2018-05-29 | 2018-05-29 | 0 | 2018-05-29 | [14 empty] | 2018-08-29 | 2018-08-30 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-10601 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8091 | Fishkill Plains | N |  | 8.3 | [13 empty] | NM | N | 36 Enphase Energy IQ6-60-X-US (240V) | 2018-05-31 | 2018-05-31 | 0 | 2018-05-31 | [8 empty] | 350 | 350 |  | 2018-06-05 | 2018-06-05 | 2018-06-26 | 2018-11-27 | 2018-11-29 |  | Y
Central Hudson |  | SolarCity DBA Tesla | CH-10599 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 6075 | East Park | N |  | 5.2 | [13 empty] | NM | N | 1 Delta Electronics SOLIVIA 5.2 NA G4 TL (240V) | 2018-06-04 | 2018-06-05 | 1 | 2018-06-05 | [14 empty] | 2018-08-17 | 2018-08-29 |  | Y
Central Hudson |  | Monolith Solar Associates LLC | CH-10597 | Poughkeepsie | Stanfordvl | Dutchess | 12581 | G | 7072 | Stanfordville | N |  | 47.6 | [13 empty] | NM | N | 4SolaredgeSE-10000A1SolaredgeSE-7600H | 2018-06-20 | 2018-06-26 | 4 | 2018-06-26 | [14 empty] | 2018-09-17 | 2018-09-19 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-10600 | Kingston | Kingston | Ulster | 12401 | G | 2013 | Lincoln Park | N |  | 9.9 | [13 empty] | NM | N | 7 Enphase Energy IQ6-60-X-US (240V) 24 Enphase Energy IQ6-60-X-US (240V) 6 Enphase Energy IQ6-60-X-US (240V) 6 Enphase Energy IQ6-60-X-US (240V) | 2018-07-16 | 2018-07-20 | 4 | 2018-07-20 | [14 empty] | 2018-08-29 | 2018-08-31 |  | Y
Central Hudson |  | Sunrun Inc. | CH-10598 | Newburgh | Newburgh |  | 12550 | G | 5001 | Marlboro | TBD |  | 7.6 | [13 empty] | NM | N | 1 Ningbo Ginlong Technologies Solis-1P7.6K-4G-US | 2018-05-30 | 2018-05-31 | 1 | 2018-05-31 | [17 empty] | W
Central Hudson |  | SolarCity DBA Tesla | CH-10603 | Newburgh | New Windsor | Orange | 12553 | G | 4095 | Bethlehem Rd | Y |  | 6 | 5 | [12 empty] | NM | N | 1 ABB PVI-6000-OUTD-US-Z-A (240V) 1TeslaAC Powerwall 2.0 | 2018-07-10 | 2018-07-18 | 6 | 2018-07-18 | [14 empty] | 2018-10-16 | 2018-10-22 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-10602 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8044 | Myers Corners | N |  | 2.8 | [13 empty] | NM | N | 12 Enphase Energy IQ6-60-X-US (240V) | 2018-07-05 | 2018-07-05 | 0 | 2018-07-05 | [14 empty] | 2018-09-17 | 2018-09-18 |  | Y
Central Hudson |  | Environomics.co | CH-10530 | Catskill | Tannersvl |  | 12485 | G | 2385 | Lawrenceville | N |  | 5000 | [13 empty] | CDG | N | 2 SMA America SC 2500-EV-US (550V) [SI1] 2SMASC-2500-EV | 2018-09-12 | 2018-09-18 | 4 | 2018-09-18 | 2018-09-18 | 2018-10-09 | 15 | 2018-12-06 | 2019-02-27 | 2019-06-07 | 70 | 16433.58 | 666712.5 | [7 empty] | 2019-11-05 | W |  | 4/17/19 - Updated documents requested to proceed with CESIR. 5/1/19, updated documents received. Utility and Developer have mutually agreed to extend the CESIR deadline to 6/7/19.
Central Hudson |  | Solar Liberty Energy Systems | CH-10605 | Poughkeepsie | Lagrange | Dutchess | 12569 | G | 6051 | Todd Hill | N |  | 1572 | [13 empty] | RC | Y | 13 SMA America SHP 150-US-20 (600V) | 2018-06-29 | 2018-07-16 | 10 | 2018-07-16 | 2018-07-16 | 2018-08-06 | 15 | 2018-09-17 | 2018-11-27 | 2019-02-04 | 46 | 15940.54 | 174108 | 114270.67 | 2019-04-24 | 2019-10-09 | 2019-10-09 | 2021-12-02 | 2021-12-15 | 2021-12-15 | 2022-03-24 | Y | Y
Central Hudson |  | Tesla | CH-10604 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8052 | North Chelsea | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE 10000A-US (277V) | 2018-06-01 | 2018-06-04 | 1 | 2018-06-04 | [14 empty] | 2018-06-18 | 2018-06-18 |  | Y
Central Hudson |  | Tesla | CH-10608 | Newburgh | Montgomery | Orange | 12549 | G | 5073 | Montgomery | N |  | 3 | [13 empty] | NM | N | 1 ABB UNO-DM-3.3-TL-PLUS-US-SB-RA (240V) [SI1] | 2018-06-14 | 2018-06-18 | 2 | 2018-06-18 | [14 empty] | 2018-09-21 | 2018-09-21 |  | Y
Central Hudson |  | PlugPV, LLC. | CH-10606 | Kingston | Kingston | Ulster | 12401 | G | 1021 | East Kingston | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600 (240V) | 2018-06-04 | 2018-06-05 | 1 | 2018-06-05 | [14 empty] | 2018-07-17 | 2018-07-18 |  | Y
Central Hudson |  | Seed Solar | CH-10607 | Kingston | Saugerties |  | 12477 | G | 3003 | Saugerties | N | CH-10607 | 12 | [13 empty] | RNM | N | 2 SolarEdge Technologies SE6000 (240V) | 2018-06-18 | 2018-06-25 | 5 | 2018-06-25 | [8 empty] | 350 | 350 |  | 2018-07-05 | 2018-07-05 | 2018-08-09 | 2018-08-09 | 2018-08-09 |  | W | Y
Central Hudson |  | Sunrun Inc. | CH-10612 | Newburgh | New Windsor | Orange | 12553 | G | 4045 | Union Ave | N |  | 6 | [13 empty] | NM | N | 1 Ningbo Ginlong Technologies Solis-1P6K-4G-US | 2018-06-05 | 2018-06-07 | 2 | 2018-06-07 | [14 empty] | 2018-07-18 | 2018-07-23 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-10610 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6096 | Manchester | N |  | 7.6 | [13 empty] | NM | N | 12 Enphase Energy IQ6-60-X-US (240V) 7 Enphase Energy IQ6-60-X-US (240V) 14 Enphase Energy IQ6-60-X-US (240V) | 2018-06-05 | 2018-06-07 | 2 | 2018-06-07 | [14 empty] | 2018-08-14 | 2018-08-16 |  | Y
Central Hudson |  | Tesla | CH-10609 | Fishkill | Beacon | Dutchess | 12508 | G | 8087 | Tioronda | N |  | 4.2 | [13 empty] | NM | N | 1 ABB PVI-4.2-OUTD-S-US-Z-A (240V) | 2018-06-05 | 2018-06-07 | 2 | 2018-06-07 | [14 empty] | 2018-09-25 | 2018-09-26 |  | Y
Central Hudson |  | New York State Solar Farm | CH-10611 | Fishkill | Fishkill | Dutchess | 12524 | G | 8011 | Forgebrook | N |  | 24.96 | [13 empty] | NM | N | 78 SunPower SPR-X22-360-D-AC (240V) | 2018-06-05 | 2018-06-11 | 4 | 2018-06-11 | [8 empty] | 350 | 350 |  | 2018-06-21 | 2018-06-21 | 2018-06-26 | 2018-10-10 | 2018-10-11 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-10615 | Kingston | Kerhonkson | Ulster | 12446 | G | 3083 | Kerhonkson | N |  | 4.6 | [13 empty] | NM | N | 6 Enphase Energy IQ6-60-X-US (240V) 14 Enphase Energy IQ6-60-X-US (240V) | 2018-06-06 | 2018-06-07 | 1 | 2018-06-07 | [14 empty] | 2018-12-04 | 2018-12-05 |  | Y
Central Hudson |  | SolarCity DBA Tesla | CH-10613 | Catskill | Westerlo | Albany | 12193 | G | 1091 | Westerlo | N |  | 11.8 | [13 empty] | NM | N | 1 Delta Electronics SOLIVIA 6.6 NA G4 TL (240V) 1 Delta Electronics SOLIVIA 5.2 NA G4 TL (240V) | 2018-07-12 | 2018-07-18 | 4 | 2018-07-18 | [8 empty] | 350 | 350 |  | 2018-08-08 | 2018-08-08 | 2018-08-22 | 2018-10-05 | 2018-10-08 |  | Y
Central Hudson |  | Solar Generation | CH-10614 | Kingston | Woodstock | Ulster | 12498 | G | 3012 | Woodstock | N |  | 13.1 | [13 empty] | NM | N | 41 SunPower SPR-X22-360-D-AC (240V) [SI1] | 2018-06-06 | 2018-06-07 | 1 | 2018-06-07 | [14 empty] | 2018-09-06 | 2018-09-07 |  | Y
Central Hudson |  | SolarCity DBA Tesla | CH-10616 | Newburgh | Campbell Hall | Orange | 10916 | G | 5051 | Maybrook | N |  | 6.6 | [13 empty] | NM | N | 1 Delta Electronics SOLIVIA 6.6 NA G4 TL (240V) | 2018-06-06 | 2018-06-07 | 1 | 2018-06-07 | [14 empty] | 2018-09-26 | 2018-09-27 |  | Y
Central Hudson |  | Hudson Solar | CH-10617 | Newburgh | Wallkill | Ulster | 12589 | G | 5041 | East Walden | N | CH-10617 | 7.68 | [13 empty] | NM | N | 24 SunPower SPR-E20-327-D-AC (240V) | 2018-06-06 | 2018-06-07 | 1 | 2018-06-07 | [14 empty] | 2018-07-11 | 2018-07-17 |  | Y
Central Hudson |  | Tesla | CH-10622 | Kingston | Saugerties | Ulster | 12477 | G | 3003 | Saugerties | N |  | 3.6 | [13 empty] | NM | N | 1 ABB PVI-3.6-OUTD-S-US-A (240V) | 2018-06-07 | 2018-06-13 | 4 | 2018-06-13 | [14 empty] | 2018-06-13 | 2018-06-25 |  | Y
Central Hudson |  | Squan Solar | CH-10618 | Poughkeepsie | Pleasant Vly |  | 12569 | G | 6057 | Todd Hill | TBD |  | 13.4 | [13 empty] | NM | N | 56 Enphase Energy M250-60-2LL-S2X (-ZC) (-NA) (240V) | 2018-06-07 | 2018-06-08 | 1 | 2018-06-08 | [8 empty] | 350 | 350 | [7 empty] | W
Central Hudson |  | Kasselman Solar | CH-10621 | Catskill | Medusa | Albany | 12120 | G | 1092 | Westerlo | N |  | 7.4 | [13 empty] | NM | N | 32 Enphase Energy IQ6-60-X-US (240V) | 2018-06-07 | 2018-06-13 | 4 | 2018-06-13 | [14 empty] | 2018-06-20 | 2018-06-22 |  | Y
Central Hudson |  | PlugPV, LLC. | CH-10620 | Catskill | New Baltimore | Greene | 12124 | G | 1083 | New Baltimore | N | CH-10620 | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) [SI1] | 2018-06-07 | 2018-06-12 | 3 | 2018-06-12 | [14 empty] | 2018-08-13 | 2018-08-15 |  | Y
Central Hudson |  | Tesla | CH-10619 | Newburgh | Newburgh | Orange | 12550 | G | 4055 | Union Ave | N |  | 10.4 | [13 empty] | NM | N | 2 Delta Electronics SOLIVIA 5.2 NA G4 TL (240V) | 2018-06-01 | 2018-06-11 | 6 | 2018-06-11 | [14 empty] | 2018-07-11 | 2018-07-17 |  | Y
Central Hudson |  | Tesla | CH-10625 | Catskill | Athens | Greene | 12015 | G | 1074 | Coxsackie | Y |  | 7.6 | 5 | [12 empty] | NM | N | 1 Delta Electronics SOLIVIA 7.6 NA G4 TL (240V) 1TeslaAC Powerwall 2.0 | 2018-06-19 | 2018-06-19 | 0 | 2018-06-19 | [14 empty] | 2019-04-11 | 2019-04-11 |  | Y
Central Hudson |  | Trinity Solar | CH-10624 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8091 | Fishkill Plains | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2018-06-08 | 2018-06-13 | 3 | 2018-06-13 | [14 empty] | 2018-09-27 | 2018-09-27 |  | Y
Central Hudson |  | Tesla | CH-10626 | Newburgh | New Windsor | Orange | 12553 | G | 4044 | Union Ave | N |  | 5.2 | [13 empty] | NM | N | 1 Delta Electronics SOLIVIA 5.2 NA G4 TL (208V) | 2018-06-08 | 2018-06-08 | 0 | 2018-06-08 | [14 empty] | 2018-06-08 | 2018-06-08 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-10628 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8092 | Fishkill Plains | N |  | 11.7 | [13 empty] | NM | N | 8 Enphase Energy IQ6-60-X-US (240V) 12 Enphase Energy IQ6-60-X-US (240V) 8 Enphase Energy IQ6-60-X-US (240V) 12 Enphase Energy IQ6-60-X-US (240V) 11 Enphase Energy IQ6-60-X-US (240V) | 2018-07-05 | 2018-07-06 | 1 | 2018-07-06 | [14 empty] | 2018-11-05 | 2018-11-08 |  | Y
Central Hudson |  | Integrity Solar Solutions | CH-10629 | Newburgh | Rock Tvrn | Orange | 12575 | G | 4097 | Bethlehem Rd | N |  | 10 | [13 empty] | NM | N | 1SolaredgeSE 10000A-US (240V) | 2018-06-11 | 2018-06-13 | 2 | 2018-06-13 | [14 empty] | 2018-06-22 | 2018-06-22 |  | Y
Central Hudson |  | New York State Solar Farm | CH-10630 | Kingston | Kingston | Ulster | 12401 | G | 1011 | Boulevard | N |  | 6.4 | [13 empty] | NM | N | 20 SunPower SPR-E20-327-D-AC (240V) | 2018-06-11 | 2018-06-13 | 2 | 2018-06-13 | [14 empty] | 2018-06-27 | 2018-06-27 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-10627 | Newburgh | Newburgh | Orange | 12550 | G | 5004 | Marlboro | N |  | 17.9 | [13 empty] | NM | N | 9 Enphase Energy IQ6-60-X-US (240V) 2 Enphase Energy IQ6-60-X-US (240V) 15 Enphase Energy IQ6-60-X-US (240V) 23 Enphase Energy IQ6-60-X-US (240V) 2 Enphase Energy IQ6-60-X-US (240V) 2 Enphase Energy IQ6-60-X-US (240V) 2 Enphase Energy IQ6-60-X-US (240V) 12 Enphase Energy IQ6-60-X-US (240V) 11 Enphase Energy IQ6-60-X-US (240V) | 2018-06-11 | 2018-06-13 | 2 | 2018-06-13 | [14 empty] | 2018-08-13 | 2018-08-14 |  | Y
Central Hudson |  | Sunrise Electrical Services, LLC. | CH-10634 | Newburgh | Newburgh |  | 12550 | G | 4045 | Union Ave | N |  | 40 | [13 empty] | NM | N | 2 SMA America STP20000TL-US-10 (480V) | 2019-02-21 | 2019-03-07 | 10 | 2019-03-07 | [17 empty] | W
Central Hudson |  | Sunrise Electrical Services, LLC. | CH-10632 | Newburgh | Newburgh | Orange | 12550 | G | 4054 | Union Ave | N |  | 100 | [13 empty] | NM | N | 2 SMA America STP50-US-40 (480V) | 2019-01-21 | 2019-01-31 | 8 | 2019-01-31 | 2019-01-31 | 2019-02-22 | 15 | [11 empty] | 2021-08-27 | 2021-08-27 |  | Y
Central Hudson |  | Sunrise Electrical Services, LLC. | CH-10635 | Newburgh | Newburgh |  | 12550 | G | 4054 | Union Ave | N |  | 45 | [13 empty] | NM | N | 3 SMA America STP15000TL-US-10 (480V) | 2019-02-21 | 2019-03-07 | 10 | 2019-03-07 | [17 empty] | W
Central Hudson |  | Sunrise Electrical Services, LLC. | CH-10636 | Newburgh | Newburgh | Orange | 12550 | G | 4015 | West Balmville | N |  | 63.3 | [13 empty] | NM | N | 2 SMA America STP 33-US-41 (480V) | 2019-01-21 | 2019-01-31 | 8 | 2019-01-31 | 2019-01-31 | 2019-02-22 | 15 | [11 empty] | 2022-08-11 | 2022-08-11 |  | Y
Central Hudson |  | Sunrise Electrical Services, LLC. | CH-10637 | Newburgh | Newburgh | Orange | 12550 | G | 4011 | West Balmville | N |  | 66.6 | [13 empty] | NM | N | 2 SMA America STP 33-US-41 (480V) | 2019-01-21 | 2019-01-31 | 8 | 2019-01-31 | 2019-01-31 | 2019-02-22 | 15 | [11 empty] | 2021-07-29 | 2021-07-30 |  | Y
Central Hudson |  | Sunrise Electrical Services, LLC. | CH-10638 | Newburgh | Newburgh | Orange | 12550 | G | 4051 | Union Ave | N |  | 33.3 | [13 empty] | NM | N | 1 SMA America STP 33-US-41 (480V) | 2019-03-20 | 2019-04-02 | 9 | 2019-04-02 | [14 empty] | 2021-07-15 | 2021-07-22 |  | Y
Central Hudson |  | Sunrise Electrical Services, LLC. | CH-10639 | Newburgh | Newburgh | Orange | 12550 | G | WN | West Balmville | N |  | 400 | [13 empty] | NM | N | 8 SMA America STP 50-US-41 (480V) | 2019-04-03 | 2019-04-16 | 9 | 2019-04-16 | 2019-04-16 | 2019-05-08 | 15 | [11 empty] | 2020-11-24 | 2020-11-24 |  | Y
Central Hudson |  | Sunrise Electrical Services, LLC. | CH-10640 | Newburgh | Newburgh | Orange | 12550 | G | 402 | Montgomery St | N |  | 50 | [13 empty] | NM | N | 1 SMA America STP50-US-40 (480V) | 2018-12-17 | 2019-01-03 | 10 | 2019-01-03 | [14 empty] | 2021-08-02 | 2021-08-02 |  | Y
Central Hudson |  | Sunrise Electrical Services, LLC. | CH-10641 | Newburgh | Newburgh | Orange | 12550 | G | 403 | Montgomery St | N |  | 50 | [13 empty] | NM | N | 1 SMA America STP50-US-40 (480V) [SI1] | 2018-12-17 | 2019-01-03 | 10 | 2019-01-03 | [14 empty] | 2021-06-30 | 2021-06-30 |  | Y
Central Hudson |  | Tesla | CH-10631 | Catskill | Catskill | Greene | 12414 | G | 2042 | South Cairo | N |  | 10.4 | [13 empty] | NM | N | 2 Delta Electronics SOLIVIA 5.2 NA G4 TL (240V) [SI1] | 2018-06-12 | 2018-06-14 | 2 | 2018-06-14 | [14 empty] | 2018-09-26 | 2018-09-27 |  | Y
Central Hudson |  | Tri-State Solar Services | CH-10623 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8071 | Shenandoah | N |  | 15 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000A-US (240V) [SI1] 1 SolarEdge Technologies SE5000x (240V) [SI1] | 2018-06-13 | 2018-06-14 | 1 | 2018-06-14 | [8 empty] | 350 | 350 |  | 2018-08-10 | 2018-08-10 | 2018-08-15 | 2018-10-15 | 2018-10-15 |  | Y
Central Hudson |  | New York State Solar Farm | CH-10633 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6093 | Manchester | N | CH-10633 | 5.1 | [13 empty] | NM | N | 16 SunPower SPR-E20-327-D-AC (240V) | 2018-06-13 | 2018-06-19 | 4 | 2018-06-19 | [14 empty] | 2018-06-29 | 2018-07-02 |  | Y
Central Hudson |  | Tesla | CH-10642 | Catskill | Earlton | Greene | 12058 | G | 2005 | North Catskill | N |  | 10.4 | [13 empty] | NM | N | 1 Delta Electronics SOLIVIA 5.2 NA G4 TL (240V) 1 Delta Electronics SOLIVIA 5.2 NA G4 TL (240V) | 2018-06-12 | 2018-06-13 | 1 | 2018-06-13 | [14 empty] | 2018-09-11 | 2018-09-13 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-10643 | Newburgh | New Paltz | Ulster | 12561 | G | 5031 | Galeville | N |  | 15.2 | [13 empty] | NM | N | 2 SolarEdge Technologies SE7600A-US (240V) | 2018-06-12 | 2018-06-14 | 2 | 2018-06-14 | [8 empty] | 350 | 350 |  | 2018-06-18 | 2018-06-18 | 2018-06-28 | 2018-07-02 | 2018-07-02 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-10648 | Fishkill | Stormvl | Dutchess | 12582 | G | 8071 | Shenandoah | N |  | 9.4 | [13 empty] | NM | N | 8 Enphase Energy IQ6-60-X-US (240V) 30 Enphase Energy IQ6-60-X-US (240V) 3 Enphase Energy IQ6-60-X-US (240V) | 2018-06-13 | 2018-06-14 | 1 | 2018-06-14 | [14 empty] | 2018-07-25 | 2018-08-03 |  | Y
Central Hudson |  | Sunrun Inc. | CH-10646 | Newburgh | Milton | Ulster | 12547 | G | 5083 | Highland | N |  | 6 | [13 empty] | NM | N | 1 Ningbo Ginlong Technologies Solis-1P6K-4G-US | 2018-06-13 | 2018-06-14 | 1 | 2018-06-14 | [14 empty] | 2018-06-29 | 2018-07-02 |  | Y
Central Hudson |  | Sunrun Inc. | CH-10647 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8045 | Myers Corners | N |  | 10 | [13 empty] | NM | N | 1 Ningbo Ginlong Technologies Solis-1P10K-4G-US | 2018-06-13 | 2018-06-14 | 1 | 2018-06-14 | [14 empty] | 2018-07-03 | 2018-07-03 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-10649 | Newburgh | Newburgh | Orange | 12550 | G | 4011 | West Balmville | N |  | 12.2 | [13 empty] | NM | N | 53 Enphase Energy IQ6-60-X-US (240V) | 2018-06-13 | 2018-06-14 | 1 | 2018-06-14 | [14 empty] | 2019-04-29 | 2019-04-30 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-10645 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6046 | Spackenkill | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE 11400A-US (240V) | 2018-06-13 | 2018-06-14 | 1 | 2018-06-14 | [14 empty] | 2018-06-15 | 2018-06-18 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-10644 | Kingston | Kingston | Ulster | 12401 | G | 3021 | High Falls | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600A-US (240V) | 2018-06-13 | 2018-06-14 | 1 | 2018-06-14 | [14 empty] | 2018-07-09 | 2018-07-16 |  | Y
Central Hudson |  | Tesla | CH-10653 | Kingston | Accord | Ulster | 12404 | G | 3024 | High Falls | N |  | 4.2 | [13 empty] | NM | N | 1 ABB PVI-4.2-OUTD-S-US-Z-A (240V) | 2018-06-14 | 2018-06-18 | 2 | 2018-06-18 | [14 empty] | 2018-06-18 | 2018-06-18 |  | Y
Central Hudson |  | Lotus Energy Inc. | CH-10650 | Kingston | Stone Ridge | Ulster | 12484 | G | 3023 | High Falls | N | CH-09042 | 5.1 | [13 empty] | NM | N | 16 SunPower SPR-E20-327-D-AC (240V) | 2018-06-14 | 2018-06-14 | 0 | 2018-06-14 | [14 empty] | 2018-06-20 | 2018-06-20 |  | Y
Central Hudson |  | Tri-State Solar Services | CH-10655 | Fishkill | Hopewell Junction | Dutchess | 12533 | G | 8072 | Shenandoah | N |  | 17.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600A-US (240V) 1 SolarEdge Technologies SE 10000A-US (240V) | 2018-06-14 | 2018-06-18 | 2 | 2018-06-18 | [14 empty] | 2018-07-26 | 2018-07-26 |  | Y
Central Hudson |  | New York State Solar Farm | CH-10651 | Poughkeepsie | Lagrangevl | Dutchess | 12540 | G | 6052 | Todd Hill | N | CH-10651 | 10.9 | [13 empty] | NM | N | 34 SunPower SPR-X22-360-D-AC (240V) | 2018-06-14 | 2018-06-18 | 2 | 2018-06-18 | [14 empty] | 2018-06-26 | 2018-06-26 |  | Y
Central Hudson |  | SolarCity DBA Tesla | CH-10654 | Kingston | Bearsvl | Ulster | 12409 | G | 3012 | Woodstock | N |  |  | 5 | [12 empty] | NA | N | 1TeslaAC Powerwall 2.0 | 2018-06-14 | 2018-06-18 | 2 | 2018-06-18 | [14 empty] | 2019-04-22 | 2019-04-23 |  | Y
Central Hudson |  | Tesla | CH-10652 | Newburgh | New Windsor | Orange | 12553 | G | 4094 | Bethlehem Rd | N |  | 3.3 | [13 empty] | NM | N | 1 ABB UNO-DM-3.3-TL-PLUS-US-SZ-RA (240V) [SI1] | 2018-06-14 | 2018-06-18 | 2 | 2018-06-18 | [14 empty] | 2018-08-22 | 2018-08-24 |  | Y
Central Hudson |  | Kasselman Solar | CH-10658 | Kingston | Kingston | Ulster | 12401 | G | 2016 | Lincoln Park | N |  | 4.6 | [13 empty] | NM | N | 20 Enphase Energy IQ6-60-X-US (240V) | 2018-06-15 | 2018-06-18 | 1 | 2018-06-18 | [14 empty] | 2018-07-02 | 2018-07-02 |  | Y
Central Hudson |  | Tesla | CH-10656 | Catskill | Catskill | Greene | 12414 | G | 2005 | North Catskill | N |  | 7.6 | [13 empty] | NM | N | 1 Delta Electronics SOLIVIA 7.6 NA G4 TL (240V) [SI1] | 2018-06-15 | 2018-06-18 | 1 | 2018-06-18 | [14 empty] | 2018-11-05 | 2018-11-06 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-10659 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8095 | Fishkill Plains | N |  | 15.2 | [13 empty] | NM | N | 2 SolarEdge Technologies SE7600A-US (240V) | 2018-06-15 | 2018-06-18 | 1 | 2018-06-18 | [14 empty] | 2018-06-21 | 2018-06-22 |  | Y
Central Hudson |  | New York State Solar Farm | CH-10657 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8093 | Fishkill Plains | N |  | 9 | [13 empty] | NM | N | 28 SunPower SPR-E20-327-D-AC (240V) | 2018-06-15 | 2018-06-18 | 1 | 2018-06-18 | [14 empty] | 2018-07-13 | 2018-07-16 |  | Y
Central Hudson |  | Tesla | CH-10660 | Kingston | Olive Brdg | Ulster | 12461 | G | 3082 | Kerhonkson | N | CH-10660 | 7.6 | [13 empty] | NM | N | 1 Delta Electronics SOLIVIA 7.6 NA G4 TL (240V) | 2018-06-18 | 2018-06-18 | 0 | 2018-06-18 | [14 empty] | 2018-07-11 | 2018-07-13 |  | Y
Central Hudson |  | Natural Energy Solutions | CH-10661 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7062 | Milan | N |  | 10 | [13 empty] | NM | N | 1SolaredgeSE10000A-US (240V) [SI1] | 2018-06-22 | 2018-06-22 | 0 | 2018-06-22 | [14 empty] | 2018-09-14 | 2018-09-17 |  | Y
Central Hudson |  | SolarCity DBA Tesla | CH-10667 | Kingston | Woodstock | Ulster | 12498 | G | 3012 | Woodstock | Y |  | 4.2 | 5 | [12 empty] | NM | N | 1 ABB PVI-4.2-OUTD-S-US-Z-A (240V) 1TeslaAC Powerwall 2.0 | 2018-06-19 | 2018-06-20 | 1 | 2018-06-20 | [8 empty] | 350 | 350 |  | 2018-06-29 | 2018-06-29 | 2018-08-13 | 2018-10-05 | 2018-10-08 |  | Y
Central Hudson |  | Tesla | CH-10665 | Catskill | Tannersvl | Greene | 12485 | G | 2385 | Lawrenceville | N |  | 14.2 | [13 empty] | NM | N | 2 Delta Electronics SOLIVIA 5.2 NA G4 TL (240V) 1 Delta Electronics SOLIVIA 3.8 NA G4 TL (240V) | 2018-06-19 | 2018-06-19 | 0 | 2018-06-19 | [14 empty] | 2018-09-24 | 2018-09-24 |  | Y
Central Hudson |  | New York State Solar Farm | CH-10664 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6011 | Sand Dock | N |  | 4.2 | [13 empty] | NM | N | 13 SunPower SPR-E20-327-D-AC (240V) | 2018-06-19 | 2018-06-19 | 0 | 2018-06-19 | [14 empty] | 2018-06-25 | 2018-06-28 |  | Y
Central Hudson |  | Hudson Solar | CH-10663 | Kingston | Kingston | Ulster | 12401 | G | 1011 | Boulevard | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600A-US (240V) [SI1] | 2018-06-20 | 2018-06-20 | 0 | 2018-06-20 | [14 empty] | 2018-07-09 | 2018-07-12 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-10662 | Poughkeepsie | Clinton Corners | Dutchess | 12514 | G | 7013 | Hibernia | N |  | 14.7 | [13 empty] | NM | N | 64 Enphase Energy IQ6-60-x-US (240V) [SI1] | 2018-06-19 | 2018-06-19 | 0 | 2018-06-19 | [14 empty] | 2018-12-05 | 2018-12-06 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-10666 | Newburgh | Newburgh | Orange | 12550 | G | 4023 | Coldenham | N |  | 5.4 | [13 empty] | NM | N | 17 SunPower SPR-X21-345-D-AC (240V) | 2018-06-19 | 2018-06-19 | 0 | 2018-06-19 | [8 empty] | 350 | 350 |  | 2018-06-20 | 2018-06-20 | 2018-06-29 | 2018-09-06 | 2018-09-07 |  | Y
Central Hudson |  | New York State Solar Farm | CH-10668 | Kingston | Kingston | Ulster | 12401 | G | 1024 | East Kingston | N |  | 9.3 | [13 empty] | NM | N | 29 SunPower SPR-E20-327-D-AC (240V) | 2018-06-19 | 2018-06-20 | 1 | 2018-06-20 | [14 empty] | 2018-07-10 | 2018-07-11 |  | Y
Central Hudson |  | Trinity Solar | CH-10670 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 7011 | Hibernia | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2018-06-20 | 2018-06-20 | 0 | 2018-06-20 | [14 empty] | 2018-08-02 | 2018-08-02 |  | Y
Central Hudson |  | Solar Liberty Energy Systems | CH-10669 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6095 | Manchester | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2018-06-29 | 2018-07-03 | 2 | 2018-07-03 | [14 empty] | 2018-09-28 | 2018-10-01 |  | Y
Central Hudson |  | New York State Solar Farm | CH-10671 | Newburgh | Milton | Ulster | 12547 | G | 5083 | Highland | N |  | 5.8 | [13 empty] | NM | N | 18 SunPower SPR-E20-327-D-AC (240V) | 2018-06-21 | 2018-06-21 | 0 | 2018-06-21 | [14 empty] | 2018-06-29 | 2018-07-09 |  | Y
Central Hudson |  | Intelligent Green Solutions | CH-10675 | Kingston | Saugerties | Ulster | 12477 | G | 3002 | Saugerties | N |  | 11.2 | [13 empty] | NM | N | 12 Enphase Energy IQ6PLUS-72-X-US (240V) 28 Enphase Energy IQ6PLUS-72-X-US (240V) | 2018-06-21 | 2018-06-21 | 0 | 2018-06-21 | [8 empty] | 350 | 350 |  | 2018-06-22 | 2018-06-22 | 2018-08-09 | 2018-08-23 | 2018-08-24 |  | Y
Central Hudson |  | Tesla | CH-10672 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 6 | [13 empty] | NM | N | 1 ABB PVI-6000-OUTD-US-Z-A (240V) | 2018-06-21 | 2018-06-21 | 0 | 2018-06-21 | [14 empty] | 2018-07-09 | 2018-07-09 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-10673 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6073 | East Park | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600A-US (240V) | 2018-06-22 | 2018-06-25 | 1 | 2018-06-25 | [14 empty] | 2018-06-25 | 2018-06-28 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-10674 | Newburgh | Wallkill | Ulster | 12589 | G | 5042 | East Walden | N |  | 9.3 | [13 empty] | NM | N | 29 SunPower SPR-X22-360-D-AC (240V) | 2018-06-21 | 2018-06-21 | 0 | 2018-06-21 | [14 empty] | 2018-09-20 | 2018-09-26 |  | Y
Central Hudson |  | SolarCity DBA Tesla | CH-10677 | Newburgh | Cornwall-Hdsn |  | 12520 | G | 4043 | Union Ave | N |  | 5.2 | [13 empty] | NM | N | 1 Delta Electronics SOLIVIA 5.2 NA G4 TL (240V) | 2018-06-27 | 2018-06-28 | 1 | 2018-06-28 | [17 empty] | W
Central Hudson |  | SolarCity DBA Tesla | CH-10678 | Catskill | Cornwallvl | Greene | 12418 | G | 2043 | South Cairo | N |  | 15.6 | [13 empty] | NM | N | 1 Delta Electronics SOLIVIA 5.2 NA G4 TL (240V) 1 Delta Electronics SOLIVIA 5.2 NA G4 TL (240V) 1 Delta Electronics SOLIVIA 5.2 NA G4 TL (240V) | 2018-06-29 | 2018-07-03 | 2 | 2018-07-03 | [8 empty] | 350 | 350 |  | 2018-08-08 | 2018-08-08 | 2018-08-25 | 2018-12-18 | 2018-12-21 |  | Y
Central Hudson |  | Kasselman Solar | CH-10679 | Catskill | Cairo | Greene | 12413 | G | 2041 | South Cairo | N |  | 4.6 | [13 empty] | NM | N | 20 Enphase Energy IQ6-60-X-US (240V) | 2018-07-18 | 2018-07-23 | 3 | 2018-07-23 | [14 empty] | 2019-05-03 | 2019-05-08 |  | Y
Central Hudson |  | Apex Solar Power | CH-10676 | Kingston | Woodstock | Ulster | 12498 | G | 3012 | Woodstock | N |  | 10 | [13 empty] | NM | N | 1SolaredgeSE 10000A-US (240V) | 2018-06-22 | 2018-06-22 | 0 | 2018-06-22 | [14 empty] | 2018-08-16 | 2018-08-21 |  | Y
Central Hudson |  | New York State Solar Farm | CH-10681 | Newburgh | Newburgh | Orange | 12550 | G | 5041 | East Walden | N |  | 7 | [13 empty] | NM | N | 22 SunPower SPR-E20-327-D-AC (240V) | 2018-06-25 | 2018-06-26 | 1 | 2018-06-26 | [14 empty] | 2018-08-10 | 2018-08-13 |  | Y
Central Hudson |  | SunCommon | CH-10682 | Kingston | Saugerties |  | 12477 | G | 3002 | Saugerties | TBD |  | 1332 | [13 empty] | CDG | N | 40 SolarEdge Technologies SE33.3KUS (480V) | 2018-07-11 | 2018-07-17 | 4 | 2018-07-17 | 2018-07-17 | 2018-08-07 | 15 |  |  |  |  | 37100 | [9 empty] | W
Central Hudson |  | SolarCity DBA Tesla | CH-10683 | Kingston | Kingston | Ulster | 12401 | G | 1011 | Boulevard | N | CH-10683 | 9 | [13 empty] | NM | N | 1 Delta Electronics SOLIVIA 3.8 NA G4 TL (240V) 1 Delta Electronics SOLIVIA 5.2 NA G4 TL (240V) | 2018-06-25 | 2018-06-27 | 2 | 2018-06-27 | [14 empty] | 2018-08-31 | 2018-09-04 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-10684 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6066 | Inwood Ave | N |  | 7 | [13 empty] | NM | N | 22 SunPower SPR-X21-345-C-AC (240V) | 2018-06-26 | 2018-06-27 | 1 | 2018-06-27 | [14 empty] | 2018-09-26 | 2018-10-03 |  | Y
Central Hudson |  | Paradise Energy Solutions LLC | CH-10686 | Newburgh | New Windsor | Orange | 12553 | G | 4046 | Union Ave | N |  | 100.8 | [13 empty] | NM | Y | 7 SolarEdge Technologies SE14.4KUS (208V) [SI1] | 2018-08-20 | 2018-08-24 | 4 | 2018-08-24 | 2018-08-24 | 2018-09-17 | 15 | [5 empty] | 3200 | 3347.25 |  | 2018-09-20 | 2018-09-20 | 2018-10-11 | 2018-12-11 | 2018-12-11 | 2018-12-11 | Y | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-10687 | Kingston | Kingston | Ulster | 12401 | G | 111 | South Wall St | N |  | 5.52 | [13 empty] | NM | N | 24 Enphase Energy IQ6-60-X-US (240V) | 2018-06-26 | 2018-07-02 | 4 | 2018-07-02 | [14 empty] | 2020-01-03 | 2020-01-07 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-10688 | Newburgh | Newburgh | Orange | 12550 | G | 4024 | Coldenham | N |  | 5.1 | [13 empty] | NM | N | 16 SunPower SPR-X21-345-D-AC (240V) | 2018-06-26 | 2018-06-28 | 2 | 2018-06-28 | [14 empty] | 2018-08-27 | 2018-08-27 |  | Y
Central Hudson |  | Hudson Solar | CH-10685 | Kingston | Kingston | Ulster | 12401 | G | 2093 | Hurley Ave | N |  | 6.4 | [13 empty] | NM | N | 3 SunPower SPR-E20-327-D-AC (240V) 9 SunPower SPR-E20-327-D-AC (240V) 8 SunPower SPR-E20-327-D-AC (240V) [SI1] | 2018-06-27 | 2018-07-02 | 3 | 2018-07-02 | [14 empty] | 2018-07-19 | 2018-07-24 |  | Y
Central Hudson |  | New York State Solar Farm | CH-10691 | Newburgh | Highland | Ulster | 12528 | G | 5084 | Highland | N | CH-10691 | 8.3 | [13 empty] | NM | N | 26 SunPower SPR-E20-327-D-AC (240V) | 2018-06-27 | 2018-06-28 | 1 | 2018-06-28 | [14 empty] | 2018-07-05 | 2018-07-05 |  | Y
Central Hudson |  | New York State Solar Farm | CH-10690 | Fishkill | Fishkill | Dutchess | 12524 | G | 8055 | North Chelsea | N | CH-10690 | 7 | [13 empty] | NM | N | 22 SunPower SPR-E20-327-D-AC (240V) | 2018-06-27 | 2018-06-28 | 1 | 2018-06-28 | [14 empty] | 2018-08-10 | 2018-08-13 |  | Y
Central Hudson |  | PlugPV, LLC. | CH-10689 | Kingston | Kingston | Ulster | 12401 | G | 2012 | Lincoln Park | N |  | 10 | [13 empty] | NM | N | 1SolaredgeSE 10000A-US (240V) | 2018-06-27 | 2018-06-28 | 1 | 2018-06-28 | [14 empty] | 2018-09-11 | 2018-09-12 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-10692 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8023 | Knapps Corners | N | CH-00053 | 3 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3000 (240V) | 2018-09-04 | 2018-09-05 | 1 | 2018-09-05 | [14 empty] | 2018-11-01 | 2018-11-02 |  | Y
Central Hudson |  | Tesla | CH-10694 | Catskill | Hunter | Greene | 12442 | E | 2081 | Hunter | N |  | 3.3 | [13 empty] | NM | N | 1 ABB UNO-DM-3.3-TL-PLUS-US-SZ-RA (240V) [SI1] | 2018-06-28 | 2018-07-03 | 3 | 2018-07-03 | [14 empty] | 2018-08-16 | 2018-08-21 |  | Y
Central Hudson |  | Tesla | CH-10695 | Catskill | Ravena | Albany | 12143 | G | 1082 | New Baltimore | N |  | 7.6 | [13 empty] | NM | N | 1 Delta Electronics SOLIVIA 7.6 NA G4 TL (240V) [SI1] | 2018-06-28 | 2018-07-03 | 3 | 2018-07-03 | [14 empty] | 2019-01-29 | 2019-02-05 |  | Y
Central Hudson |  | Tesla | CH-10693 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7061 | Milan | Y |  | 5.2 | 5 | [12 empty] | NM | N | 1 Delta Electronics SOLIVIA 5.2 NA G4 TL (240V) [SI1] 1TeslaAC Powerwall 2.0 | 2018-06-28 | 2018-07-02 | 2 | 2018-07-02 | [8 empty] | 350 | 350 |  | 2018-07-11 | 2018-07-11 | 2018-08-20 | 2018-11-05 | 2018-11-08 |  | Y
Central Hudson |  | SolarCity DBA Tesla | CH-10697 | Newburgh | Maybrook | Orange | 12543 | G | 5052 | Maybrook | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2018-07-31 | 2018-08-01 | 1 | 2018-08-01 | [14 empty] | 2018-09-26 | 2018-09-27 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-10696 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6063 | Inwood Ave | N |  | 9.3 | [13 empty] | NM | N | 29 SunPower SPR-X22-360-D-AC (240V) | 2018-07-03 | 2018-07-03 | 0 | 2018-07-03 | [14 empty] | 2018-10-31 | 2018-11-02 |  | Y
Central Hudson |  | Sunrun Inc. | CH-10702 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8095 | Fishkill Plains | N |  | 7.6 | [13 empty] | NM | N | 1 Ningbo Ginlong Technologies Solis-1P7.6K-4G-US | 2018-06-29 | 2018-07-03 | 2 | 2018-07-03 | [14 empty] | 2018-07-26 | 2018-07-27 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-10701 | Newburgh | Rock Tvrn | Orange | 12575 | G | 4097 | Bethlehem Rd | N |  | 7.8 | [13 empty] | NM | N | 28 Enphase Energy IQ6PLUS-72-X-US (240V) | 2018-06-29 | 2018-07-03 | 2 | 2018-07-03 | [14 empty] | 2018-10-01 | 2018-10-01 |  | Y
Central Hudson |  | Sunrise Solar Solutions, LLC | CH-10700 | Fishkill | Garrison | Putnam | 10524 | G | 8086 | Tioronda | Y | CH-10700 | 11.8 | [13 empty] | NM | N | 37 SunPower SPR-X22-360-C-AC (240V) | 2018-07-25 | 2018-07-25 | 0 | 2018-07-25 | [14 empty] | 2018-10-31 | 2018-11-01 |  | Y
Central Hudson |  | New York State Solar Farm | CH-10699 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8095 | Fishkill Plains | N |  | 14.4 | [13 empty] | NM | N | 45 SunPower SPR-X22-360-D-AC (240V) | 2018-06-29 | 2018-07-03 | 2 | 2018-07-03 | [14 empty] | 2018-07-18 | 2018-07-18 |  | Y
Central Hudson |  | Hudson Solar | CH-10703 | Kingston | Malden-Hdsn | Ulster | 12453 | G | 3004 | Saugerties | N |  | 9.6 | [13 empty] | NM | N | 30 SunPower SPR-X21-335-BLK-D-AC (240V) [SI1] | 2018-07-17 | 2018-07-20 | 3 | 2018-07-20 | [14 empty] | 2018-08-08 | 2018-08-08 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-10704 | Newburgh | Cornwall-Hdsn | Orange | 12520 | G | 4043 | Union Ave | N |  | 3 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3000 (240V) | 2018-07-03 | 2018-07-05 | 1 | 2018-07-05 | [14 empty] | 2018-07-18 | 2018-07-20 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-10705 | Newburgh | Cornwall | Orange | 12518 | G | 4041 | Union Ave | N |  | 5.8 | [13 empty] | NM | N | 18 Enphase Energy IQ6-60-X-US (240V) 7 Enphase Energy IQ6-60-X-US (240V) | 2018-07-03 | 2018-07-05 | 1 | 2018-07-05 | [14 empty] | 2018-10-18 | 2018-10-22 |  | Y
Central Hudson |  | Tesla | CH-10708 | Kingston | Mt Tremper |  | 12457 | G | 3012 | Woodstock | Y | CH-08066 |  | 5 | [12 empty] | NM | N | 1TeslaPowerwall | 2018-07-05 | 2018-07-05 | 0 | 2018-07-05 | [17 empty] | W
Central Hudson |  | Infinity Solar Systems | CH-10706 | Newburgh | Cornwall | Orange | 12518 | G | 4094 | Bethlehem Rd | N |  | 6.2 | [13 empty] | NM | N | 27 Enphase Energy IQ6-60-X-US (240V) | 2018-07-31 | 2018-07-31 | 0 | 2018-07-31 | [14 empty] | 2018-08-17 | 2018-08-24 |  | Y
Central Hudson |  | SolarCity DBA Tesla | CH-10707 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8056 | North Chelsea | N |  | 12.8 | [13 empty] | NM | N | 1 Delta Electronics SOLIVIA 7.6 NA G4 TL (240V) 1 Delta Electronics SOLIVIA 5.2 NA G4 TL (240V) | 2018-07-03 | 2018-07-05 | 1 | 2018-07-05 | [14 empty] | 2018-09-11 | 2018-09-12 |  | Y
Central Hudson |  | Apex Solar Power | CH-10709 | Kingston | W Shokan | Ulster | 12494 | G | 3011 | Woodstock | N |  | 9 | [13 empty] | NM | N | 1 SolarEdge Technologies SE9K (208V) | 2018-07-05 | 2018-07-05 | 0 | 2018-07-05 | [14 empty] | 2018-08-23 | 2018-09-04 |  | Y
Central Hudson |  | SolarCity DBA Tesla | CH-10710 | Newburgh | Wallkill | Ulster | 12589 | G | 5041 | East Walden | N |  | 12.8 | [13 empty] | NM | N | 1 Delta Electronics SOLIVIA 7.6 NA G4 TL (240V) 1 Delta Electronics SOLIVIA 5.2 NA G4 TL (240V) | 2018-07-06 | 2018-07-06 | 0 | 2018-07-06 | [14 empty] | 2018-07-23 | 2018-07-23 |  | Y
Central Hudson |  | Monolith Solar Associates LLC | CH-10711 | Fishkill | East Fishkill |  | 12533 | G | 8072 | Shenandoah | TBD |  | 498 | [13 empty] | RNM | N | 15 SMA America STP30000TL-US-10 (480V) 2 SMA America STP24000TL-US-10 (480V) | 2018-10-03 | 2018-10-09 | 4 | 2018-10-09 | 2018-10-09 | 2018-10-25 | 12 | [14 empty] | W
Central Hudson |  | Solar Image, LLC | CH-10712 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 5 | [13 empty] | NM | N | 1 SMA America SBS5.0-US-10 (240V) [SI1] | 2018-07-19 | 2018-07-24 | 3 | 2018-07-24 | [14 empty] | 2018-08-16 | 2018-08-16 |  | Y
Central Hudson |  | Hudson Valley Wind & Solar, LLC | CH-10715 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7061 | Milan | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2018-07-31 | 2018-07-31 | 0 | 2018-07-31 | [14 empty] | 2018-08-29 | 2018-08-30 |  | Y
Central Hudson |  | Hudson Valley Wind & Solar, LLC | CH-10714 | Poughkeepsie | Milan | Dutchess | 12571 | G | 7061 | Milan | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) [SI1] | 2018-07-31 | 2018-07-31 | 0 | 2018-07-31 | [14 empty] | 2018-10-16 | 2018-10-22 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-10713 | Fishkill | Poughkeepsie | Dutchess | 12603 | G | 8024 | Knapps Corners | N |  | 15.2 | [13 empty] | NM | N | 2 SolarEdge Technologies SE7600A-US (240V) | 2018-07-10 | 2018-07-10 | 0 | 2018-07-10 | [14 empty] | 2018-07-20 | 2018-07-20 |  | Y
Central Hudson |  | SolarCity DBA Tesla | CH-10717 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8046 | Myers Corners | N |  | 12.8 | [13 empty] | NM | N | 1 Delta Electronics SOLIVIA 7.6 NA G4 TL (240V) 1 Delta Electronics SOLIVIA 5.2 NA G4 TL (240V) | 2018-07-10 | 2018-07-18 | 6 | 2018-07-18 | [14 empty] | 2018-08-17 | 2018-08-21 |  | Y
Central Hudson |  | Florenton River LLC dba SunBlue Energy | CH-10716 | Poughkeepsie | Clinton Corners | Dutchess | 12514 | G | 7011 | Hibernia | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE 11400A-US (240V) | 2018-07-17 | 2018-07-18 | 1 | 2018-07-18 | [14 empty] | 2018-10-08 | 2018-10-10 |  | Y
Central Hudson |  | Lighthouse Solar | CH-10719 | Kingston | W Hurley | Ulster | 12491 | G | 2094 | Hurley Ave | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000 (240V) | 2018-07-18 | 2018-07-23 | 3 | 2018-07-23 | [14 empty] | 2018-09-10 | 2018-09-13 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-10718 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8094 | Fishkill Plains | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600A-US (240V) | 2018-07-11 | 2018-07-18 | 5 | 2018-07-18 | [14 empty] | 2018-07-20 | 2018-07-20 |  | Y
Central Hudson |  | New York State Solar Farm | CH-10720 | Newburgh | New Paltz | Ulster | 12561 | G | 5011 | Modena | N | CH-23807 | 9 | [13 empty] | NM | N | 28 SunPower SPR-E20-327-D-AC (240V) | 2018-07-11 | 2018-07-23 | 8 | 2018-07-23 | [14 empty] | 2018-07-23 | 2018-07-26 |  | Y
Central Hudson |  | Energy Venture Management Inc | CH-10722 | Kingston | Rosendale |  | 12472 | G | 3021 | High Falls | TBD |  | 1100 | [13 empty] | NM | N | 11 Chint Power Systems America CPS SCH100KTL-DO/US-600 (600V) | 2018-10-12 | 2018-10-15 | 1 | 2018-10-15 | 2018-10-15 | 2018-11-05 | 15 |  |  |  |  | 36000 | [9 empty] | W
Central Hudson |  | New York State Solar Farm | CH-10723 | Poughkeepsie | Verbank | Dutchess | 12585 | G | 6057 | Todd Hill | N |  | 11.2 | [13 empty] | NM | N | 35 SunPower SPR-E20-327-D-AC (240V) | 2018-07-12 | 2018-07-18 | 4 | 2018-07-18 | [14 empty] | 2018-08-07 | 2018-08-14 |  | Y
Central Hudson |  | New York State Solar Farm | CH-10724 | Poughkeepsie | Verbank | Dutchess | 12585 | G | 6057 | Todd Hill | N |  | 3.2 | [13 empty] | NM | N | 10 SunPower SPR-E20-327-D-AC (240V) | 2018-07-12 | 2018-07-18 | 4 | 2018-07-18 | [14 empty] | 2018-08-09 | 2018-08-13 |  | Y
Central Hudson |  | Kasselman Solar | CH-10726 | Kingston | Saugerties | Ulster | 12477 | G | 3003 | Saugerties | N |  | 10.1 | [13 empty] | NM | N | 36 Enphase Energy IQ6PLUS-72-X-US (240V) | 2018-07-13 | 2018-07-23 | 6 | 2018-07-23 | [14 empty] | 2018-08-03 | 2018-08-08 |  | Y
Central Hudson |  | Kasselman Solar | CH-10731 | Catskill | Westerlo | Albany | 12193 | G | 1091 | Westerlo | N |  | 6.4 | [13 empty] | NM | N | 28 Enphase Energy IQ6-60-X-US (240V) | 2018-07-16 | 2018-07-23 | 5 | 2018-07-23 | [14 empty] | 2018-07-25 | 2018-07-26 |  | Y
Central Hudson |  | Kasselman Solar | CH-10728 | Kingston | Ulster Pk |  | 12487 | G | 1023 | East Kingston | N |  | 4.6 | [13 empty] | NM | N | 20 Enphase Energy IQ6-60-X-US (240V) | 2018-07-16 | 2018-07-23 | 5 | 2018-07-23 | [17 empty] | W
Central Hudson |  | Tesla | CH-10729 | Kingston | Kingston | Ulster | 12401 | G | 2093 | Hurley Ave | N |  | 12.8 | [13 empty] | NM | N | 1 Delta Electronics SOLIVIA 5.2 NA G4 TL (240V) 1 Delta Electronics SOLIVIA 7.6 NA G4 TL (240V) | 2018-07-16 | 2018-07-23 | 5 | 2018-07-23 | [14 empty] | 2018-09-13 | 2018-09-14 |  | Y
Central Hudson |  | Kasselman Solar | CH-10730 | Catskill | Prattsvl | Greene | 12468 | E | 2389 | Vinegar Hill | N |  | 4.5 | [13 empty] | NM | N | 16 Enphase Energy IQ6PLUS-72-X-US (240V) | 2018-07-16 | 2018-07-23 | 5 | 2018-07-23 | [14 empty] | 2018-09-06 | 2018-09-07 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-10732 | Fishkill | Beacon | Dutchess | 12508 | G | 8087 | Tioronda | N |  | 3 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3000 (240V) | 2018-07-16 | 2018-07-23 | 5 | 2018-07-23 | [14 empty] | 2018-07-24 | 2018-07-24 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-10733 | Fishkill | Wappingrs Fls |  | 12590 | G | 8043 | Myers Corners | N |  | 2.8 | [13 empty] | NM | N | 12 Enphase Energy IQ6-60-X-US (240V) | 2018-07-17 | 2018-07-23 | 4 | 2018-07-23 | [17 empty] | W
Central Hudson |  | Kasselman Solar | CH-10734 | Fishkill | Fishkill | Dutchess | 12524 | G | 8014 | Forgebrook | N |  | 6.2 | [13 empty] | NM | N | 27 Enphase Energy IQ6-60-X-US (240V) | 2018-07-17 | 2018-07-23 | 4 | 2018-07-23 | [14 empty] | 2018-08-15 | 2018-08-16 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-10735 | Kingston | Kingston | Ulster | 12401 | G | 1022 | East Kingston | N |  | 5.5 | [13 empty] | NM | N | 21 Enphase Energy IQ6-60-X-US (240V) 3 Enphase Energy IQ6-60-X-US (240V) | 2018-07-17 | 2018-07-23 | 4 | 2018-07-23 | [14 empty] | 2019-01-02 | 2019-01-04 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-10737 | Kingston | Ellenvl | Ulster | 12428 | G | 396 | Clinton Ave | N |  | 3.8 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3800 (240V) | 2018-07-18 | 2018-07-23 | 3 | 2018-07-23 | [14 empty] | 2018-07-30 | 2018-08-06 |  | Y
Central Hudson |  | New York State Solar Farm | CH-10736 | Newburgh | Cornwall-Hdsn | Orange | 12520 | G | 4043 | Union Ave | N |  | 6.7 | [13 empty] | NM | N | 21 SunPower SPR-E20-327-D-AC (240V) | 2018-07-18 | 2018-07-23 | 3 | 2018-07-23 | [14 empty] | 2018-08-21 | 2018-08-22 |  | Y
Central Hudson |  | Solar Alchemy, Inc. | CH-10738 | Kingston | Kingston | Ulster | 12401 | G | 2094 | Hurley Ave | N |  | 15 | [13 empty] | NM | N | 1 Fronius USA Fronius Primo 15.0-1 (240V) | 2018-07-18 | 2018-07-23 | 3 | 2018-07-23 | [14 empty] | 2018-09-07 | 2018-09-10 |  | Y
Central Hudson |  | SolarCity DBA Tesla | CH-10741 | Catskill | Freehold | Greene | 12431 | G | 2061 | Freehold | N |  | 10.4 | [13 empty] | NM | N | 2 Delta Electronics SOLIVIA 5.2 NA G4 TL (240V) | 2018-07-19 | 2018-07-23 | 2 | 2018-07-23 | [14 empty] | 2018-12-21 | 2018-12-28 |  | Y
Central Hudson |  | Sunrun Inc. | CH-10743 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6011 | Sand Dock | N |  | 9.9 | [13 empty] | NM | N | 1 SolarEdge Technologies SE 10000A-US (240V) | 2018-07-19 | 2018-07-23 | 2 | 2018-07-23 | [14 empty] | 2018-09-28 | 2018-10-01 |  | Y
Central Hudson |  | PlugPV, LLC. | CH-10740 | Kingston | Saugerties | Ulster | 12477 | G | 3001 | Saugerties | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE 10000A-US (240V) | 2018-07-19 | 2018-07-23 | 2 | 2018-07-23 | [14 empty] | 2018-11-20 | 2018-11-20 |  | Y
Central Hudson |  | Albany Solar Solutions LLC | CH-10742 | Newburgh | Highland | Ulster | 12528 | G | 5022 | Ohioville | N |  | 9.9 | [13 empty] | NM | N | 18 Altenergy Power System YC600 (240V) | 2018-08-06 | 2018-08-09 | 3 | 2018-08-09 | [14 empty] | 2018-10-22 | 2018-10-25 |  | Y
Central Hudson |  | Environomics.co | CH-10512 | Kingston | Saugerties |  | 12477 | G | 3014 | Woodstock | N |  | 5000 | [13 empty] | CDG | N | 2 SMA America SC 2500-EV-US (550V) [SI1] 2SMASC-2500-EV | 2018-09-14 | 2018-09-24 | 6 | 2018-09-24 | 2018-09-24 | 2018-10-15 | 15 | 2018-12-10 | 2019-02-12 | 2019-05-09 | 60 | 17023.66 | 2144881.25 | [7 empty] | 2019-09-27 | W
Central Hudson |  | Sunrun Inc. | CH-10748 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8043 | Myers Corners | N |  | 6 | [13 empty] | NM | N | 1 Ningbo Ginlong Technologies Solis-1P6K-4G-US | 2018-08-29 | 2018-08-30 | 1 | 2018-08-30 | [14 empty] | 2018-09-17 | 2018-09-18 |  | Y
Central Hudson |  | Sunrun Inc. | CH-10747 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6011 | Sand Dock | N |  | 5 | [13 empty] | NM | N | 1 Ningbo Ginlong Technologies Solis-1P5K-4G-US (240V) | 2018-07-20 | 2018-07-24 | 2 | 2018-07-24 | [14 empty] | 2018-08-28 | 2018-08-29 |  | Y
Central Hudson |  | Sunrun Inc. | CH-10746 | Newburgh | New Windsor | Orange | 12553 | G | 4094 | Bethlehem Rd | N | CH-08322 | 7 | [13 empty] | NM | N | 1 Ningbo Ginlong Technologies Solis-1P4K-4G-US (240V) 1 Ningbo Ginlong Technologies Solis-1P3K-4G-US (240V) | 2018-07-20 | 2018-07-25 | 3 | 2018-07-25 | [14 empty] | 2018-08-21 | 2018-08-24 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-10745 | Fishkill | Garrison | Putnam | 10524 | G | 8066 | Merritt Park | N |  | 8.05 | [13 empty] | NM | N | 7 Enphase Energy IQ6-60-X-US (240V) 28 Enphase Energy IQ6-60-X-US (240V) | 2018-07-31 | 2018-07-31 | 0 | 2018-07-31 | [14 empty] | 2018-11-09 | 2018-11-12 |  | Y
Central Hudson |  | New York State Solar Farm | CH-10744 | Newburgh | Gardiner | Ulster | 12525 | G | 5031 | Galeville | N |  | 7.68 | [13 empty] | NM | N | 24 SunPower SPR-X22-360-D-AC (240V) | 2018-07-20 | 2018-07-23 | 1 | 2018-07-23 | [14 empty] | 2018-08-20 | 2018-08-21 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-10756 | Fishkill | Fishkill | Dutchess | 12524 | G | 8011 | Forgebrook | N |  | 3.4 | [13 empty] | NM | N | 15 Enphase Energy IQ6-60-X-US (240V) | 2018-08-01 | 2018-08-01 | 0 | 2018-08-01 | [14 empty] | 2018-11-26 | 2018-12-03 |  | Y
Central Hudson |  | sunpower | CH-10753 | Fishkill | Beacon | Dutchess | 12508 | G | 8017 | Forgebrook | N |  | 5.4 | [13 empty] | NM | N | 17 SunPower SPR-X22-360-D-AC (240V) | 2018-08-10 | 2018-08-14 | 2 | 2018-08-14 | [14 empty] | 2018-11-15 | 2018-11-15 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-10751 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8056 | North Chelsea | N |  | 8.3 | [13 empty] | NM | N | 26 SunPower SPR-X22-360-D-AC (240V) | 2018-07-23 | 2018-07-24 | 1 | 2018-07-24 | [14 empty] | 2018-09-27 | 2018-09-27 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-10755 | Fishkill | Wappingrs Fls |  | 12590 | G | 8045 | Myers Corners | TBD |  | 14.7 | [13 empty] | NM | N | 8 Enphase Energy IQ6-60-X-US (240V) 15 Enphase Energy IQ6-60-X-US (240V) 8 Enphase Energy IQ6-60-X-US (240V) 33 Enphase Energy IQ6-60-X-US (240V) | 2018-07-23 | 2018-07-25 | 2 | 2018-07-25 | [17 empty] | W
Central Hudson |  | SolarCity DBA Tesla | CH-10749 | Newburgh | Maybrook | Orange | 12543 | G | 4026 | Coldenham | N |  | 3.8 | [13 empty] | NM | N | 1 Delta Electronics SOLIVIA 3.8 NA G4 TL (240V) | 2018-07-23 | 2018-07-25 | 2 | 2018-07-25 | [14 empty] | 2018-08-27 | 2018-08-27 |  | Y
Central Hudson |  | Lotus Energy Inc. | CH-10754 | Catskill | Catskill | Greene | 12414 | G | 2001 | North Catskill | N | CH-10194 | 2.6 | [13 empty] | NM | N | 8 SunPower SPR-E20-327-D-AC (240V) | 2018-07-25 | 2018-07-25 | 0 | 2018-07-25 | [14 empty] | 2018-08-13 | 2018-08-14 |  | Y
Central Hudson |  | Sunpower | CH-10752 | Newburgh | New Windsor | Orange | 12553 | G | 4095 | Bethlehem Rd | N |  | 5.12 | [13 empty] | NM | N | 16 SunPower SPR-X22-360-D-AC (240V) | 2018-08-14 | 2018-08-14 | 0 | 2018-08-14 | [14 empty] | 2018-11-15 | 2018-11-15 |  | Y
Central Hudson |  | New York State Solar Farm | CH-10750 | Newburgh | Highland | Ulster | 12528 | G | 5084 | Highland | N | CH-10750 | 5.8 | [13 empty] | NM | N | 18 SunPower SPR-E20-327-D-AC (240V) | 2018-07-23 | 2018-07-24 | 1 | 2018-07-24 | [14 empty] | 2018-09-14 | 2018-09-17 |  | Y
Central Hudson |  | Sunrun Inc. | CH-10760 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6011 | Sand Dock | N |  | 9 | [13 empty] | NM | N | 1 Ningbo Ginlong Technologies Solis-1P9K-4G-US | 2018-07-24 | 2018-07-25 | 1 | 2018-07-25 | [14 empty] | 2018-08-30 | 2018-08-31 |  | Y
Central Hudson |  | PlugPV, LLC. | CH-10759 | Kingston | Woodstock | Ulster | 12498 | G | 3012 | Woodstock | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000 (240V) | 2018-10-04 | 2018-10-04 | 0 | 2018-10-04 | [14 empty] | 2018-10-26 | 2018-10-29 |  | Y
Central Hudson |  | New York State Solar Farm | CH-10757 | Newburgh | New Windsor | Orange | 12553 | G | 4094 | Bethlehem Rd | N |  | 7 | [13 empty] | NM | N | 22 SunPower SPR-X21-350-BLK-D-AC (240V) | 2018-07-24 | 2018-07-25 | 1 | 2018-07-25 | [14 empty] | 2018-10-10 | 2018-10-11 |  | Y
Central Hudson |  | New York State Solar Farm | CH-10758 | Newburgh | Highland Mls | Orange | 10930 | G | 4041 | Union Ave | N |  | 10.56 | [13 empty] | NM | N | 33 SunPower SPR-X22-360-D-AC (240V) | 2018-07-24 | 2018-07-25 | 1 | 2018-07-25 | [14 empty] | 2018-09-17 | 2018-09-18 |  | Y
Central Hudson |  | National Solar Technologies | CH-10764 | Newburgh | Highland | Ulster | 12528 | G | 5084 | Highland | N |  | 12.6 | [13 empty] | NM | N | 45 Enphase Energy IQ6PLUS-72-x-US (208V) [SI1] | 2018-08-06 | 2018-08-09 | 3 | 2018-08-09 | [14 empty] | 2019-08-02 | 2019-08-02 |  | Y
Central Hudson |  | National Solar Technologies | CH-10765 | Kingston | Cragsmoor | Ulster | 12420 | G | 3078 | Greenfield Rd | N |  | 17.4 | [13 empty] | NM | N | 62 Enphase Energy IQ6PLUS-72-X-US (240V) | 2018-07-26 | 2018-07-26 | 0 | 2018-07-26 | [14 empty] | 2018-12-04 | 2018-12-05 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-10762 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 6073 | East Park | N |  | 7.6 | [13 empty] | NM | N | 33 Enphase Energy IQ6-60-X-US (240V) | 2018-07-25 | 2018-07-26 | 1 | 2018-07-26 | [14 empty] | 2018-11-08 | 2018-11-08 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-10763 | Fishkill | Fishkill |  | 12524 | G | 8062 | Merritt Park | N |  | 9.7 | [13 empty] | NM | N | 16 Enphase Energy IQ6-60-X-US (240V) 15 Enphase Energy IQ6-60-X-US (240V) 5 Enphase Energy IQ6-60-X-US (240V) 4 Enphase Energy IQ6-60-X-US (240V) 2 Enphase Energy IQ6-60-X-US (240V) | 2018-07-25 | 2018-07-26 | 1 | 2018-07-26 | [17 empty] | W
Central Hudson |  | Monolith Solar Associates LLC | CH-10761 | Catskill | Coeymans | Albany | 12045 | G | 1082 | New Baltimore | N |  | 10.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) 1 SolarEdge Technologies SE3000H-US (240V) | 2018-07-25 | 2018-07-25 | 0 | 2018-07-25 | [14 empty] | 2018-12-18 | 2018-12-21 |  | Y
Central Hudson |  | Sunrun Inc. | CH-10766 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6011 | Sand Dock | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2018-08-29 | 2018-08-29 | 0 | 2018-08-29 | [14 empty] | 2018-10-05 | 2018-10-08 |  | Y
Central Hudson |  | Sunrun Inc. | CH-10767 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6011 | Sand Dock | N |  | 5 | [13 empty] | NM | N | 1 SMA America SB5.0-1SP-US-40 (240V) | 2018-08-29 | 2018-08-29 | 0 | 2018-08-29 | [14 empty] | 2018-09-17 | 2018-09-18 |  | Y
Central Hudson |  | SolarCity DBA Tesla | CH-10768 | Poughkeepsie | Millerton | Dutchess | 12546 | G | 7081 | Millerton | N | CH-10768 | 5 | [13 empty] | NM | N | 1 ABB PVI-5000-OUTD-S-US-Z-A (240 V) | 2018-07-26 | 2018-07-26 | 0 | 2018-07-26 | [14 empty] | 2018-08-06 | 2018-08-10 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-10769 | Newburgh | Marlboro | Ulster | 12542 | G | 5003 | Marlboro | N |  | 12.48 | [13 empty] | NM | N | 39 SunPower SPR-X22-360-D-AC (240V) | 2018-07-26 | 2018-07-26 | 0 | 2018-07-26 | [14 empty] | 2018-09-19 | 2018-09-21 |  | Y
Central Hudson |  | Tesla | CH-10770 | Fishkill | Stormvl | Dutchess | 12582 | G | 8071 | Shenandoah | N |  | 6 | [13 empty] | NM | N | 1 ABB PVI-6000-OUTD-US-Z-A (240V) | 2018-07-27 | 2018-07-30 | 1 | 2018-07-30 | [14 empty] | 2018-09-06 | 2018-09-17 |  | Y
Central Hudson |  | New York State Solar Farm | CH-10771 | Kingston | Woodstock | Ulster | 12498 | G | 3014 | Woodstock | N |  | 20 | [13 empty] | NM | N | 2 SolarEdge Technologies SE 10000A-US (240V) | 2018-07-31 | 2018-07-31 | 0 | 2018-07-31 | [14 empty] | 2018-11-09 | 2018-11-16 |  | Y
Central Hudson |  | New York State Solar Farm | CH-10772 | Newburgh | Newburgh | Orange | 12550 | G | 5001 | Marlboro | N |  | 9.6 | [13 empty] | NM | N | 30 SunPower SPR-X22-360-D-AC (240V) | 2018-07-27 | 2018-07-30 | 1 | 2018-07-30 | [14 empty] | 2018-12-27 | 2018-12-28 |  | Y |  | 9/26/18 - Meter pan damaged, meter cannot be replaced. 12/21 - Contractor notified Central Hudson that repairs have been made. 12/27 - Meter change complete.
Central Hudson |  | Empire Solar Solutions | CH-10773 | Kingston | Hurley |  | 12443 | G | 2094 | Hurley Ave | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600A-US (240V) | 2018-07-27 | 2018-07-30 | 1 | 2018-07-30 | [14 empty] | 2018-08-01 | 2018-08-01 |  | W
Central Hudson |  | Infinity Solar Systems | CH-10774 | Newburgh | Newburgh | Orange | 12550 | G | 4023 | Coldenham | N |  | 7.36 | [13 empty] | NM | N | 23 SunPower SPR-X22-360-D-AC (240V) | 2018-07-30 | 2018-07-30 | 0 | 2018-07-30 | [14 empty] | 2018-11-14 | 2018-11-14 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-10775 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8092 | Fishkill Plains | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600A-US (240V) | 2018-07-30 | 2018-07-31 | 1 | 2018-07-31 | [14 empty] | 2018-08-03 | 2018-08-07 |  | Y
Central Hudson |  | Solar Generation | CH-10776 | Kingston | Stone Ridge | Ulster | 12484 | G | 3024 | High Falls | N |  | 3.5 | [13 empty] | NM | N | 7 SunPower SPR-X21-345-D-AC (240V) [SI1] 4 SunPower SPR-X21-345-D-AC (240V) | 2018-08-01 | 2018-08-01 | 0 | 2018-08-01 | [14 empty] | 2018-09-04 | 2018-09-06 |  | Y
Central Hudson |  | SolarCity DBA Tesla | CH-10778 | Kingston | Lk Hill | Ulster | 12448 | G | 3012 | Woodstock | Y | CH-10778 | 7.6 | [13 empty] | NM | N | 1 Delta Electronics SOLIVIA 7.6 NA G4 TL (240V) | 2018-07-31 | 2018-07-31 | 0 | 2018-07-31 | [14 empty] | 2018-10-30 | 2018-11-02 |  | Y
Central Hudson |  | PlugPV, LLC. | CH-10777 | Kingston | Saugerties | Ulster | 12477 | G | 3001 | Saugerties | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000 (240V) | 2018-08-02 | 2018-08-02 | 0 | 2018-08-02 | [14 empty] | 2018-11-13 | 2018-11-14 |  | Y
Central Hudson |  | Sunrun Inc. | CH-10780 | Poughkeepsie | Pleasant Vly |  | 12569 | G | 7011 | Hibernia | N |  | 5 | [13 empty] | NM | N | 1 Ningbo Ginlong Technologies Solis-1P5K-4G-US (240V) | 2018-08-29 | 2018-08-29 | 0 | 2018-08-29 | [14 empty] | 2019-03-14 | 2019-03-14 |  | W
Central Hudson |  | Sunrun Inc. | CH-10779 | Poughkeepsie | Pleasant Vly |  | 12569 | G | 7011 | Hibernia | N |  | 25 | [13 empty] | NM | N | 1 Ningbo Ginlong Technologies Solis-1P10K-4G-US 1 Ningbo Ginlong Technologies Solis-1P5K-4G-US (240V) 1 Ningbo Ginlong Technologies Solis-10K-US (480V) | 2018-08-29 | 2018-08-29 | 0 | 2018-08-29 | [14 empty] | 2019-03-14 | 2019-03-14 |  | W
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-10782 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 6051 | Todd Hill | N |  | 2.5 | [13 empty] | NM | N | 11 Enphase Energy IQ6-60-X-US (240V) | 2018-08-08 | 2018-08-13 | 3 | 2018-08-13 | [14 empty] | 2018-10-05 | 2018-10-08 |  | Y
Central Hudson |  | Tesla | CH-10781 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8095 | Fishkill Plains | N |  | 5 | [13 empty] | NM | N | 1 ABB PVI-5000-OUTD-US-Z-A (240V) | 2018-08-01 | 2018-08-01 | 0 | 2018-08-01 | [14 empty] | 2018-10-03 | 2018-10-08 |  | Y
Central Hudson |  | New York State Solar Farm | CH-10784 | Kingston | Saugerties | Ulster | 12477 | G | 2015 | Lincoln Park | N |  | 3.8 | [13 empty] | NM | N | 12 SunPower SPR-E20-327-D-AC (240V) | 2018-08-02 | 2018-08-03 | 1 | 2018-08-03 | [14 empty] | 2018-08-10 | 2018-08-13 |  | Y
Central Hudson |  | Tesla | CH-10783 | Catskill | Palenville | Greene | 12463 | G | 2042 | South Cairo | N |  | 4.2 | [13 empty] | NM | N | 1 ABB PVI-4.2-OUTD-S-US-Z-A (240V) | 2018-08-02 | 2018-08-02 | 0 | 2018-08-02 | [14 empty] | 2018-08-13 | 2018-08-14 |  | Y
Central Hudson |  | RER Energy Group, LLC. | CH-10786 | Catskill | Coxsackie | Greene | 12051 | G | 1074 | Coxsackie | N |  | 600 | [13 empty] | RC | Y | 10 Sungrow Power Supply SG 60KU-M (480V) [SI1] | 2018-09-25 | 2018-09-25 | 0 | 2018-09-25 | 2018-09-25 | 2018-10-16 | 15 | [5 empty] | 422811 | 130928.14 | 2019-01-22 | 2019-06-14 | 2019-06-14 | 2019-11-20 | 2020-09-03 | 2020-09-03 | 2020-11-25 | Y | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-10787 | Newburgh | Highland | Ulster | 12528 | G | 5084 | Highland | N |  | 11.5 | [13 empty] | NM | N | 30 Enphase Energy IQ6-60-X-US (240V) 20 Enphase Energy IQ6-60-X-US (240V) | 2018-08-08 | 2018-08-13 | 3 | 2018-08-13 | [14 empty] | 2018-12-04 | 2018-12-06 |  | Y
Central Hudson |  | Tri-State Solar Services | CH-10785 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8014 | Forgebrook | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000A-US (240V) [SI1] | 2018-08-08 | 2018-08-08 | 0 | 2018-08-08 | [14 empty] | 2019-02-07 | 2019-02-08 |  | Y
Central Hudson |  | Hudson Solar | CH-10788 | Catskill | Medusa | Albany | 12120 | G | 1092 | Westerlo | N |  | 5.1 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000H-US (240V) | 2018-08-14 | 2018-08-15 | 1 | 2018-08-15 | [8 empty] | 350 | 350 |  | 2018-08-16 | 2018-08-16 | 2018-09-02 | 2018-09-12 | 2018-09-14 |  | Y
Central Hudson |  | Tesla | CH-10789 | Poughkeepsie | Hyde Park | Dutchess | 12538 | G | 7042 | Staatsburg | Y | CH-10789 | 9 | [13 empty] | NM | N | 1 Delta Electronics SOLIVIA 3.8 NA G4 TL (240V) 1 Delta Electronics SOLIVIA 5.2 NA G4 TL (240V) | 2018-08-06 | 2018-08-09 | 3 | 2018-08-09 | [14 empty] | 2018-10-25 | 2018-10-26 |  | Y
Central Hudson |  | Sun Mountain | CH-10791 | Kingston | High Fls | Ulster | 12440 | G | 3024 | High Falls | Y |  | 6.8 | 6.8 | [12 empty] | NM | N | 1 Schneider Electric Solar Inverters USA XW+6848-NA 1Schneider ElectricConext XW+ 6848 NA | 2018-10-11 | 2018-10-24 | 9 | 2018-10-24 | [14 empty] | 2018-12-19 | 2018-12-19 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-10790 | Newburgh | Cornwall | Orange | 12518 | G | 4041 | Union Ave | N |  | 12.8 | [13 empty] | NM | N | 40 SunPower SPR-X22-360-D-AC (240V) | 2018-08-06 | 2018-08-09 | 3 | 2018-08-09 | [14 empty] | 2018-10-31 | 2018-11-02 |  | Y
Central Hudson |  | Tesla | CH-10793 | Newburgh | Newburgh | Orange | 12550 | G | 5041 | East Walden | Y | CH-10793 | 7.6 | [13 empty] | NM | N | 1 Delta Electronics SOLIVIA 7.6 NA G4 TL (240V) | 2018-08-24 | 2018-08-27 | 1 | 2018-08-27 | [14 empty] | 2018-10-23 | 2018-10-29 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-10792 | Fishkill | Fishkill | Dutchess | 12524 | G | 8063 | Merritt Park | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000 (240V) | 2018-08-07 | 2018-08-09 | 2 | 2018-08-09 | [14 empty] | 2018-08-16 | 2018-08-16 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-10794 | Kingston | Kingston | Ulster | 12401 | G | 2093 | Hurley Ave | N |  | 7.13 | [13 empty] | NM | N | 31 Enphase Energy IQ6-60-X-US (240V) | 2018-08-07 | 2018-08-09 | 2 | 2018-08-09 | [14 empty] | 2018-11-07 | 2018-11-09 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-10795 | Kingston | Cottekill | Ulster | 12419 | G | 3021 | High Falls | N | CH-08658 | 1.84 | [13 empty] | NM | N | 8 Enphase Energy IQ6-60-X-US (240V) | 2018-08-15 | 2018-08-16 | 1 | 2018-08-16 | [14 empty] | 2019-04-15 | 2019-04-16 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-10796 | Newburgh | New Paltz | Ulster | 12561 | G | 5012 | Modena | N |  | 9.89 | [13 empty] | NM | N | 39 Enphase Energy IQ6-60-X-US (240V) 2 Enphase Energy IQ6-60-X-US (240V) 2 Enphase Energy IQ6-60-X-US (240V) | 2018-08-08 | 2018-08-13 | 3 | 2018-08-13 | [14 empty] | 2018-11-30 | 2018-12-04 |  | Y
Central Hudson |  | SolarCity DBA Tesla | CH-10798 | Kingston | Kingston | Ulster | 12401 | G | 1014 | Boulevard | N |  | 7.6 | [13 empty] | NM | N | 1 Delta Electronics SOLIVIA 7.6 NA G4 TL (240V) | 2018-08-09 | 2018-08-14 | 3 | 2018-08-14 | [14 empty] | 2018-09-28 | 2018-10-02 |  | Y
Central Hudson |  | SolarCity DBA Tesla | CH-10799 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6043 | Spackenkill | N |  | 5 | [13 empty] | NM | N | 1 ABB PVI-5000-OUTD-US-Z-A (240V) | 2018-08-09 | 2018-08-14 | 3 | 2018-08-14 | [14 empty] | 2018-09-12 | 2018-09-12 |  | Y
Central Hudson |  | Solar Generation | CH-10797 | Kingston | Woodstock | Ulster | 12498 | G | 3012 | Woodstock | N |  | 5.8 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2018-08-09 | 2018-08-14 | 3 | 2018-08-14 | [14 empty] | 2018-11-21 | 2018-11-21 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-10802 | Newburgh | New Paltz | Ulster | 12561 | G | 5024 | Ohioville | N |  | 14.5 | [13 empty] | NM | N | 32 Enphase Energy IQ6-60-X-US (240V) 31 Enphase Energy IQ6-60-X-US (240V) | 2018-08-10 | 2018-08-14 | 2 | 2018-08-14 | [8 empty] | 350 | 350 |  | 2018-10-24 | 2018-10-24 | 2019-02-05 | 2019-01-20 | 2019-02-07 |  | Y
Central Hudson |  | Lighthouse Solar | CH-10800 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6045 | Spackenkill | N |  | 5.8 | [13 empty] | NM | N | 20 Enphase Energy IQ7PLUS-72-x-US (240V) | 2018-08-23 | 2018-08-27 | 2 | 2018-08-27 | [14 empty] | 2018-10-29 | 2018-10-29 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-10801 | Fishkill | Beacon | Dutchess | 12508 | G | 8085 | Tioronda | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000 (240V) | 2018-08-10 | 2018-08-16 | 4 | 2018-08-16 | [14 empty] | 2018-08-22 | 2018-08-28 |  | Y
Central Hudson |  | Kasselman Solar | CH-10803 | Kingston | Kingston |  | 12401 | G | 2094 | Hurley Ave | N |  | 4.8 | [13 empty] | NM | N | 20 Enphase Energy IQ6-60-X-US (240V) | 2018-08-13 | 2018-08-14 | 1 | 2018-08-14 | [17 empty] | W
Central Hudson |  | Kasselman Solar | CH-10804 | Catskill | Lexington | Greene | 12452 | E | 2389 | Vinegar Hill | N |  | 6 | [13 empty] | NM | N | 26 Enphase Energy IQ6-60-X-US (240V) | 2018-08-14 | 2018-08-14 | 0 | 2018-08-14 | [14 empty] | 2018-09-17 | 2018-09-18 |  | Y
Central Hudson |  | Tesla | CH-10807 | Kingston | Stone Ridge | Ulster | 12484 | G | 3023 | High Falls | N |  | 3.3 | [13 empty] | NM | N | 1 ABB UNO-DM-3.3-TL-PLUS-US-SZ-RA (240V) [SI1] | 2018-08-14 | 2018-08-14 | 0 | 2018-08-14 | [14 empty] | 2018-09-10 | 2018-09-13 |  | Y
Central Hudson |  | New York State Solar Farm | CH-10806 | Newburgh | Highland | Ulster | 12528 | G | 5022 | Ohioville | N |  | 24.96 | [13 empty] | NM | N | 78 SunPower SPR-E20-327-D-AC (240V) | 2018-08-14 | 2018-08-16 | 2 | 2018-08-16 | [8 empty] | 350 | 350 |  | 2018-08-17 | 2018-08-17 | 2018-08-31 | 2018-10-05 | 2018-10-05 |  | Y
Central Hudson |  | Hudson Valley Wind & Solar, LLC | CH-10805 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7053 | Rhinebeck | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2018-09-10 | 2018-09-11 | 1 | 2018-09-11 | [14 empty] | 2019-02-07 | 2019-02-14 |  | Y
Central Hudson |  | Lotus Energy Inc. | CH-10809 | Poughkeepsie | Ancram | Columbia | 12502 | G | 7091 | Pulvers Corners | N |  | 6.4 | [13 empty] | NM | N | 20 SunPower SPR-X21-350-BLK-D-AC (240V) | 2018-08-15 | 2018-08-15 | 0 | 2018-08-15 | [14 empty] | 2018-08-22 | 2018-08-24 |  | Y
Central Hudson |  | Vivint Solar Delveloper, LLC | CH-10810 | Newburgh | New Windsor | Orange | 12553 | G | 4044 | Union Ave | N |  | 4.6 | [13 empty] | NM | N | 20 Enphase Energy IQ6-60-X-US (240V) | 2018-08-16 | 2018-08-16 | 0 | 2018-08-16 | [14 empty] | 2018-10-26 | 2018-10-31 |  | Y
Central Hudson |  | SunCommon | CH-10808 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7053 | Rhinebeck | N |  | 15.04 | [13 empty] | NM | N | 11 SunPower SPR-E20-327-D-AC (240V) [SI1] 36 SunPower SPR-E20-327-D-AC (240V) [SI1] | 2018-08-15 | 2018-08-15 | 0 | 2018-08-15 | [8 empty] | 350 | 350 |  | 2018-08-16 | 2018-08-16 | 2018-08-20 | 2018-08-24 | 2018-08-29 |  | Y
Central Hudson |  | Sunrun Inc. | CH-10812 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6011 | Sand Dock | N |  | 11 | [13 empty] | NM | N | 1 SMA America SB6.0-1SP-US-40 (240V) 1 SMA America SB5.0-1SP-US-40 (240V) | 2018-08-17 | 2018-08-21 | 2 | 2018-08-21 | [14 empty] | 2018-10-05 | 2018-10-08 |  | Y
Central Hudson |  | SolarCity DBA Tesla Energy | CH-10811 | Catskill | Leeds | Greene | 12451 | G | 2005 | North Catskill | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) [SI1] | 2018-08-27 | 2018-08-29 | 2 | 2018-08-29 | [14 empty] | 2018-10-12 | 2018-10-15 |  | Y
Central Hudson |  | Seed Solar | CH-10813 | Kingston | Saugerties |  | 12477 | G | 3003 | Saugerties | N | CH-10607 | 3.2 | [13 empty] | RNM | N | 2 SolarEdge Technologies SE7600H-US (240V) | 2018-08-20 | 2018-08-21 | 1 | 2018-08-21 | [8 empty] | 350 | 350 |  | 2018-08-22 | 2018-08-22 | 2018-10-26 | 2018-11-02 | 2018-11-07 |  | W | Y
Central Hudson |  | B&W Group Inc. | CH-10814 | Kingston | Woodstock |  | 12498 | G | 3013 | Woodstock | TBD |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2018-08-20 | 2018-08-24 | 4 | 2018-08-24 | [17 empty] | W
Central Hudson |  | Lighthouse Solar | CH-10816 | Newburgh | New Paltz | Ulster | 12561 | G | 5031 | Galeville | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2018-08-23 | 2018-08-27 | 2 | 2018-08-27 | [14 empty] | 2018-11-30 | 2018-12-04 |  | Y
Central Hudson |  | Sunrun Inc. | CH-10817 | Newburgh | Newburgh | Orange | 12550 | G | 4024 | Coldenham | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000x (240V) [SI1] | 2018-08-20 | 2018-08-23 | 3 | 2018-08-23 | [14 empty] | 2018-09-06 | 2018-09-10 |  | Y
Central Hudson |  | New York State Solar Farm | CH-10815 | Newburgh | Maybrook | Orange | 12543 | G | 4026 | Coldenham | N |  | 7 | [13 empty] | NM | N | 22 SunPower SPR-E20-327-D-AC (240V) | 2018-08-20 | 2018-08-22 | 2 | 2018-08-22 | [14 empty] | 2018-10-10 | 2018-10-19 |  | Y
Central Hudson |  | Solar Image, LLC | CH-10818 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 5 | [13 empty] | NM | N | 1 SMA America SB5000US (240V) | 2018-08-23 | 2018-08-27 | 2 | 2018-08-27 | [14 empty] | 2018-08-29 | 2018-08-30 |  | Y
Central Hudson |  | Kasselman Solar | CH-10819 | Catskill | Ravena | Albany | 12143 | G | 1082 | New Baltimore | N |  | 37.2 | [13 empty] | NM | N | 155 Enphase Energy IQ7-60-x-US (240V) | 2019-01-17 | 2019-01-30 | 9 | 2019-01-30 | [14 empty] | 2019-12-02 | 2019-12-05 |  | Y
Central Hudson |  | City of Kingston Parks & Rec Dept | CH-10821 | Kingston | Kingston | Ulster | 12401 | G | 2093 | Hurley Ave | N |  | 4.8 | [13 empty] | NM | N | 20 Enphase Energy M250-60-2LL-S2X (-ZC) (-NA) (240V) | 2018-08-23 | 2018-08-27 | 2 | 2018-08-27 | [14 empty] | 2018-10-12 | 2018-10-15 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-10823 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6011 | Sand Dock | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000x (240V) [SI1] | 2018-08-22 | 2018-08-23 | 1 | 2018-08-23 | [14 empty] | 2018-09-19 | 2018-09-21 |  | Y
Central Hudson |  | Sunrun Inc. | CH-10824 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8065 | Merritt Park | N |  | 8 | [13 empty] | NM | N | 1 SMA America SB5.0-1SP-US-40 (240V) 1 SMA America SB3.0-1SP-US-40 (240V) | 2018-08-29 | 2018-08-30 | 1 | 2018-08-30 | [14 empty] | 2018-09-17 | 2018-09-18 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-10822 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8052 | North Chelsea | N |  | 10 | [13 empty] | NM | N | 2 SMA America SB5.0-1SP-US-40 (240V) | 2018-08-22 | 2018-08-23 | 1 | 2018-08-23 | [14 empty] | 2018-09-24 | 2018-09-26 |  | Y
Central Hudson |  | New York State Solar Farm | CH-10827 | Kingston | Kingston | Ulster | 12401 | G | 1013 | Boulevard | N |  | 7.7 | [13 empty] | NM | N | 24 SunPower SPR-E20-327-D-AC (240V) | 2018-08-23 | 2018-08-27 | 2 | 2018-08-27 | [14 empty] | 2018-12-13 | 2018-12-14 |  | Y
Central Hudson |  | New York State Solar Farm | CH-10826 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 6057 | Todd Hill | N |  | 11.5 | [13 empty] | NM | N | 36 SunPower SPR-E20-327-D-AC (240V) | 2018-08-23 | 2018-08-27 | 2 | 2018-08-27 | [14 empty] | 2018-12-05 | 2018-12-14 |  | Y
Central Hudson |  | New York State Solar Farm | CH-10830 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8014 | Forgebrook | N |  | 6.4 | [13 empty] | NM | N | 20 SunPower SPR-X22-360-D-AC (240V) | 2018-08-27 | 2018-08-29 | 2 | 2018-08-29 | [14 empty] | 2018-09-07 | 2018-09-10 |  | Y
Central Hudson |  | New York State Solar Farm | CH-10828 | Kingston | Woodstock | Ulster | 12498 | G | 3012 | Woodstock | N |  | 10.88 | [13 empty] | NM | N | 34 SunPower SPR-X22-360-D-AC (240V) | 2018-08-27 | 2018-08-29 | 2 | 2018-08-29 | [14 empty] | 2018-10-22 | 2018-10-24 |  | Y
Central Hudson |  | New York State Solar Farm | CH-10829 | Newburgh | Highland | Ulster | 12528 | G | 5083 | Highland | N |  | 6.1 | [13 empty] | NM | N | 19 SunPower SPR-E20-327-D-AC (240V) | 2018-08-23 | 2018-08-27 | 2 | 2018-08-27 | [14 empty] | 2018-11-15 | 2018-11-19 |  | Y
Central Hudson |  | Lighthouse Solar | CH-10833 | Kingston | Stone Ridge | Ulster | 12484 | G | 3023 | High Falls | N |  | 20 | [13 empty] | NM | N | 2 SolarEdge Technologies SE 10000A-US (240V) | 2018-08-27 | 2018-08-29 | 2 | 2018-08-29 | [8 empty] | 350 | 350 |  | 2018-08-30 | 2018-08-30 | 2018-10-11 | 2018-10-11 | 2018-10-12 |  | Y
Central Hudson |  | PlugPV, LLC. | CH-10831 | Kingston | Ulster Pk | Ulster | 12487 | G | 1023 | East Kingston | N | CH-10831 | 3.8 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3800H-US (240V) | 2018-08-29 | 2018-08-30 | 1 | 2018-08-30 | [14 empty] | 2018-11-15 | 2018-11-20 |  | Y
Central Hudson |  | Tesla Energy | CH-10832 | Catskill | Lexington | Greene | 12452 | E | 2389 | Vinegar Hill | N |  | 3 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3000H-US (240V) | 2018-08-24 | 2018-08-27 | 1 | 2018-08-27 | [14 empty] | 2019-01-24 | 2019-01-30 |  | Y
Central Hudson |  | PlugPV, LLC | CH-10834 | Kingston | Kingston | Ulster | 12401 | G | 2017 | Lincoln Park | N |  | 3 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3000 (240V) | 2018-08-27 | 2018-08-27 | 0 | 2018-08-27 | [14 empty] | 2018-11-30 | 2018-12-04 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-10839 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6046 | Spackenkill | N |  | 3 | [13 empty] | NM | N | 1 SMA America SB3.0-1SP-US-40 (240V) | 2018-08-28 | 2018-08-29 | 1 | 2018-08-29 | [14 empty] | 2018-12-11 | 2018-12-12 |  | Y
Central Hudson |  | Apex Solar Power | CH-10836 | Fishkill | Beacon | Dutchess | 12508 | G | 8087 | Tioronda | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000 (240V) | 2018-08-28 | 2018-08-29 | 1 | 2018-08-29 | [14 empty] | 2018-09-13 | 2018-09-14 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-10840 | Newburgh | Wallkill | Ulster | 12589 | G | 5041 | East Walden | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600A-US (240V) | 2018-09-04 | 2018-09-05 | 1 | 2018-09-05 | [14 empty] | 2018-09-06 | 2018-09-14 |  | Y
Central Hudson |  | SolarCity DBA Tesla Energy | CH-10842 | Newburgh | Newburgh | Orange | 12550 | G | 5001 | Marlboro | N |  | 7.6 | [13 empty] | NM | N | 1 Delta Electronics SOLIVIA 7.6 NA G4 TL (240V) | 2018-08-29 | 2018-08-30 | 1 | 2018-08-30 | [14 empty] | 2018-12-13 | 2018-12-17 |  | Y
Central Hudson |  | Solar Image | CH-10841 | Newburgh | Salisbury Mls | Orange | 12577 | G | 4097 | Bethlehem Rd | N |  | 5 | [13 empty] | NM | N | 1 SMA America SB5000US-11 (240V) | 2018-09-04 | 2018-09-05 | 1 | 2018-09-05 | [14 empty] | 2018-09-18 | 2018-09-25 |  | Y
Central Hudson |  | SunCommon | CH-10844 | Poughkeepsie | Pleasant Valley | Dutchess | 12569 | G | 7011 | Hibernia | N |  | 7.68 | [13 empty] | NM | N | 24 SunPower SPR-X22-360-C-AC (240V) | 2018-08-29 | 2018-08-30 | 1 | 2018-08-30 | [14 empty] | 2018-10-01 | 2018-10-11 |  | Y
Central Hudson |  | Tesla | CH-10845 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6093 | Manchester | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) [SI1] | 2018-08-30 | 2018-08-30 | 0 | 2018-08-30 | [14 empty] | 2018-09-10 | 2018-09-11 |  | Y
Central Hudson |  | New York State Solar Farm | CH-10846 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6092 | Manchester | N |  | 8 | [13 empty] | NM | N | 25 SunPower SPR-X21-350-BLK-D-AC (240V) | 2018-08-30 | 2018-08-30 | 0 | 2018-08-30 | [14 empty] | 2018-11-30 | 2018-12-04 |  | Y
Central Hudson |  | SolarCity DBA Tesla Energy | CH-10847 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 7042 | Staatsburg | N | CH-10847 | 7.6 | [13 empty] | NM | N | 1 Delta Electronics SOLIVIA 7.6 NA G4 TL (240V) | 2018-09-17 | 2018-09-17 | 0 | 2018-09-17 | [14 empty] | 2018-09-21 | 2018-09-25 |  | Y
Central Hudson |  | SolarCity DBA Tesla Energy | CH-10849 | Newburgh | Campbell Hall | Orange | 10916 | G | 5052 | Maybrook | N | CH-10849 | 7.6 | [13 empty] | NM | N | 1 Delta Electronics SOLIVIA 7.6 NA G4 TL (240V) | 2018-08-31 | 2018-09-04 | 1 | 2018-09-04 | [14 empty] | 2018-09-06 | 2018-09-17 |  | Y
Central Hudson |  | SunCommon | CH-10848 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7052 | Rhinebeck | Y | CH-01770 | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600A-US (240V) [SI1] | 2018-09-07 | 2018-09-11 | 2 | 2018-09-11 | [14 empty] | 2018-09-27 | 2018-09-27 |  | Y
Central Hudson |  | SolarCity | CH-10850 | Kingston | Kingston | Ulster | 12401 | G | 2092 | Hurley Ave | N |  | 5 | [13 empty] | NM | N | 1 ABB PVI-5000-OUTD-US-Z-A (240V) | 2018-09-04 | 2018-09-05 | 1 | 2018-09-05 | [14 empty] | 2018-09-11 | 2018-09-14 |  | Y
Central Hudson |  | SolarCity DBA Tesla | CH-10852 | Catskill | Prattsvl | Greene | 12468 | E | 2389 | Vinegar Hill | N |  | 3.3 | [13 empty] | NM | N | 1 ABB UNO-DM-3.3-TL-PLUS-US-SZ-RA (240V) [SI1] | 2018-09-04 | 2018-09-05 | 1 | 2018-09-05 | [14 empty] | 2018-10-05 | 2018-10-09 |  | Y
Central Hudson |  | Trinity Solar | CH-10853 | Newburgh | Campbell Hall | Orange | 10916 | G | 5051 | Maybrook | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE 10000A-US (240V) | 2018-09-18 | 2018-09-24 | 4 | 2018-09-24 | [14 empty] | 2019-01-07 | 2019-01-10 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-10851 | Poughkeepsie | Millbrook | Dutchess | 12545 | G | 7012 | Hibernia | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE 10000A-US (240V) | 2018-09-06 | 2018-09-11 | 3 | 2018-09-11 | [14 empty] | 2018-09-12 | 2018-09-13 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-10862 | Poughkeepsie | Poughkeepsie |  | 12601 | G | 6011 | Sand Dock | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2018-09-05 | 2018-09-17 | 8 | 2018-09-17 | [17 empty] | W
Central Hudson |  | Conscious Energy Inc. | CH-10854 | Kingston | Kingston | Ulster | 12401 | G | 2094 | Hurley Ave | N |  | 15 | [13 empty] | NM | N | 3 SMA America SB5000US-11 (240V) | 2018-09-05 | 2018-09-06 | 1 | 2018-09-06 | [8 empty] | 350 | 350 |  | 2018-09-18 | 2018-09-18 | 2018-10-26 | 2019-03-04 | 2019-03-08 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-10861 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8043 | Myers Corners | N |  | 7 | [13 empty] | NM | N | 1 SMA America SB7.0-1SP-US-40 (240V) | 2018-09-05 | 2018-09-07 | 2 | 2018-09-07 | [14 empty] | 2018-09-24 | 2018-09-26 |  | Y
Central Hudson |  | New York State Solar Farm | CH-10855 | Fishkill | Beacon | Dutchess | 12508 | G | 8017 | Forgebrook | N |  | 5.12 | [13 empty] | NM | N | 16 SunPower SPR-E20-327-D-AC (240V) | 2018-09-05 | 2018-09-06 | 1 | 2018-09-06 | [14 empty] | 2018-10-15 | 2018-10-16 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-10858 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6046 | Spackenkill | N |  | 10.8 | [13 empty] | NM | N | 1 SMA America SB7.7-1SP-US-40 (240V) 1 SMA America SB3.0-1SP-US-40 (240V) | 2018-09-19 | 2018-09-25 | 4 | 2018-09-25 | [8 empty] | 350 | 350 |  | 2018-09-26 | 2018-09-26 | 2018-10-19 | 2018-11-19 | 2018-11-19 |  | Y
Central Hudson |  | New York State Solar Farm | CH-10856 | Newburgh | Gardiner | Ulster | 12525 | G | 5011 | Modena | N |  | 5.76 | [13 empty] | NM | N | 18 SunPower SPR-E20-327-D-AC (240V) | 2018-09-06 | 2018-09-06 | 0 | 2018-09-06 | [14 empty] | 2018-10-24 | 2018-10-25 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-10859 | Newburgh | Newburgh | Orange | 12550 | G | 4023 | Coldenham | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000 (240V) | 2018-09-05 | 2018-09-07 | 2 | 2018-09-07 | [14 empty] | 2018-10-04 | 2018-10-08 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-10860 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6046 | Spackenkill | N |  | 7 | [13 empty] | NM | N | 1 SMA America SB7.0-1SP-US-40 (240V) | 2018-09-05 | 2018-09-07 | 2 | 2018-09-07 | [14 empty] | 2018-10-08 | 2018-10-15 |  | Y
Central Hudson |  | New York State Solar Farm | CH-10857 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7054 | Rhinebeck | N |  | 13.44 | [13 empty] | NM | N | 42 SunPower SPR-X21-350-BLK-D-AC (240V) | 2018-09-05 | 2018-09-07 | 2 | 2018-09-07 | [14 empty] | 2019-05-23 | 2019-05-28 |  | Y
Central Hudson |  | Solar Generation | CH-10863 | Kingston | Willow | Ulster | 12495 | G | 3012 | Woodstock | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600A-US (240V) | 2018-10-15 | 2018-10-16 | 1 | 2018-10-16 | [14 empty] | 2018-10-25 | 2018-10-30 |  | Y
Central Hudson |  | Saturn Power Corporation | CH-10864 | Catskill | Lexington |  | 12485 | E | 2389 | Vinegar Hill | TBD |  | 3000 | [13 empty] | CDG | N | 30 Huawei Technologies SUN2000-100KTL-USH0 (800V) | 2018-10-12 | 2018-10-15 | 1 | 2018-10-15 | 2018-10-15 | 2018-11-05 | 15 | [14 empty] | W
Central Hudson |  | Tesla Energy Operations | CH-10865 | Fishkill | Cold Spg | Putnam | 10516 | G | 8063 | Merritt Park | N |  | 11.4 | [13 empty] | NM | N | 1 Delta Electronics SOLIVIA 7.6 NA G4 TL (240V) 1 Delta Electronics SOLIVIA 3.8 NA G4 TL (240V) | 2018-09-07 | 2018-09-11 | 2 | 2018-09-11 | [14 empty] | 2018-10-19 | 2018-10-22 |  | Y
Central Hudson |  | Tesla | CH-10866 | Newburgh | New Paltz | Ulster | 12561 | G | 5024 | Ohioville | N | CH-10866 | 19 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) 1 SolarEdge Technologies SE 11400A-US (240V) | 2018-09-10 | 2018-09-11 | 1 | 2018-09-11 | [8 empty] | 350 | 350 |  | 2018-09-18 | 2018-09-18 | 2018-12-08 | 2018-12-12 | 2018-12-14 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-10870 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6093 | Manchester | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000 (240V) | 2018-09-11 | 2018-09-18 | 5 | 2018-09-18 | [14 empty] | 2018-11-28 | 2018-12-04 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-10867 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7054 | Rhinebeck | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE 11400A-US (240V) | 2018-09-11 | 2018-09-11 | 0 | 2018-09-11 | [14 empty] | 2018-10-02 | 2018-10-04 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-10869 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6046 | Spackenkill | N |  | 7 | [13 empty] | NM | N | 1 SMA America SB7.0-1SP-US-40 (240V) | 2018-09-11 | 2018-09-18 | 5 | 2018-09-18 | [14 empty] | 2018-10-29 | 2018-10-29 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-10868 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6046 | Spackenkill | N |  | 14.7 | [13 empty] | NM | N | 1 SMA America SB7.7-1SP-US-40 (240V) 1 SMA America SB7.0-1SP-US-40 (240V) | 2018-09-21 | 2018-09-24 | 1 | 2018-09-24 | [14 empty] | 2018-10-12 | 2018-10-15 |  | Y
Central Hudson |  | New York State Solar Farm | CH-10871 | Newburgh | Gardiner | Ulster | 12525 | G | 5033 | Galeville | N |  | 9.6 | [13 empty] | NM | N | 30 SunPower SPR-X22-360-D-AC (240V) | 2018-09-12 | 2018-09-13 | 1 | 2018-09-13 | [14 empty] | 2018-10-31 | 2018-11-01 |  | Y
Central Hudson |  | Empire Solar Solutuions | CH-10872 | Newburgh | Marlboro | Ulster | 12542 | G | 5003 | Marlboro | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600A-US (240V) | 2018-09-13 | 2018-09-13 | 0 | 2018-09-13 | [14 empty] | 2018-09-20 | 2018-09-21 |  | Y
Central Hudson |  | Vivint Solar Developer, LLC | CH-10876 | Newburgh | Highland | Ulster | 12528 | G | 5081 | Highland | N |  | 11.73 | [13 empty] | NM | N | 27 Enphase Energy IQ6-60-X-US (240V) 12 Enphase Energy IQ6-60-X-US (240V) 6 Enphase Energy IQ6-60-X-US (240V) 6 Enphase Energy IQ6-60-X-US (240V) | 2018-09-13 | 2018-09-14 | 1 | 2018-09-14 | [14 empty] | 2018-12-14 | 2018-12-19 |  | Y
Central Hudson |  | Lighthouse Solar | CH-10873 | Kingston | Kingston | Ulster | 12401 | G | 3021 | High Falls | N |  | 5.23 | [13 empty] | NM | N | 18 Enphase Energy IQ7PLUS-72-x-US (240V) | 2018-09-20 | 2018-09-24 | 2 | 2018-09-24 | [14 empty] | 2018-10-16 | 2018-10-16 |  | Y
Central Hudson |  | New York State Solar Farm | CH-10874 | Newburgh | Newburgh | Orange | 12550 | G | 4013 | West Balmville | N |  | 9.6 | [13 empty] | NM | N | 30 SunPower SPR-E20-327-D-AC (240V) | 2018-09-13 | 2018-09-13 | 0 | 2018-09-13 | [14 empty] | 2019-04-24 | 2019-04-26 |  | Y
Central Hudson |  | New York State Solar Farm | CH-10875 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6045 | Spackenkill | N |  | 10.56 | [13 empty] | NM | N | 33 SunPower SPR-E20-327-D-AC (240V) | 2018-09-13 | 2018-09-13 | 0 | 2018-09-13 | [14 empty] | 2018-12-17 | 2018-12-18 |  | Y
Central Hudson |  | SolarCity DBA Tesla Energy | CH-10878 | Kingston | West Camp | Ulster | 12490 | G | 3004 | Saugerties | N |  | 10 | [13 empty] | NM | N | 2 SolarEdge Technologies SE5000 (240V) | 2018-09-20 | 2018-09-24 | 2 | 2018-09-24 | [14 empty] | 2018-10-09 | 2018-10-17 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-10877 | Newburgh | New Windsor | Orange | 12553 | G | 4042 | Union Ave | N |  | 6.08 | [13 empty] | NM | N | 19 SunPower SPR-X22-360-D-AC (240V) | 2018-09-14 | 2018-09-14 | 0 | 2018-09-14 | [14 empty] | 2018-10-26 | 2018-10-31 |  | Y
Central Hudson |  | YSG Solar | CH-10879 | Newburgh | Wallkill | Ulster | 12589 | G | 5041 | East Walden | N |  | 20 | [13 empty] | NM | N | 2 SolarEdge Technologies SE10000H-US (240V) | 2018-09-24 | 2018-09-24 | 0 | 2018-09-24 | [14 empty] | 2018-10-24 | 2018-10-25 |  | Y
Central Hudson |  | Solar Generation | CH-10880 | Kingston | Woodstock | Ulster | 12498 | G | 3013 | Woodstock | N | CH-08172 | 5 | [13 empty] | NM | N | 1 SMA America SB5000US (240V) | 2018-09-17 | 2018-09-20 | 3 | 2018-09-20 | [14 empty] | 2018-10-19 | 2018-10-22 |  | Y
Central Hudson |  | SolarCity DBA Tesla Energy | CH-10882 | Catskill | Cairo | Greene | 12413 | G | 2041 | South Cairo | N |  | 7.6 | [13 empty] | NM | N | 1 Delta Electronics SOLIVIA 7.6 NA G4 TL (240V) | 2018-10-01 | 2018-10-01 | 0 | 2018-10-01 | [14 empty] | 2018-12-21 | 2018-12-26 |  | Y
Central Hudson |  | Vivint Solar Developer, LLC | CH-10881 | Poughkeepsie | Poughkeepsie |  | 12603 | G | 6097 | Manchester | N |  | 6.21 | [13 empty] | NM | N | 27 Enphase Energy IQ6-60-X-US (240V) | 2018-09-18 | 2018-09-25 | 5 | 2018-09-25 | [17 empty] | W
Central Hudson |  | SolarCity DBA Tesla Energy | CH-10884 | Newburgh | New Windsor | Orange | 12553 | G | 4045 | Union Ave | N |  | 3 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3000H-US (240V) [SI1] | 2018-09-18 | 2018-09-25 | 5 | 2018-09-25 | [14 empty] | 2018-10-24 | 2018-10-25 |  | Y
Central Hudson |  | American Solar Partners | CH-10885 | Newburgh | Newburgh | Orange | 12550 | G | 4023 | Coldenham | N |  | 3.8 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3800H-US (240V) | 2018-10-11 | 2018-10-15 | 2 | 2018-10-15 | [14 empty] | 2019-01-22 | 2019-01-28 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-10886 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6046 | Spackenkill | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2018-09-18 | 2018-09-25 | 5 | 2018-09-25 | [14 empty] | 2018-11-12 | 2018-11-14 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-10888 | Newburgh | Montgomery | Orange | 12549 | G | 5073 | Montgomery | N |  | 15.2 | [13 empty] | NM | N | 1 SolarEdge Technologies SE 11400A-US (240V) 1 SolarEdge Technologies SE3800x (240V) [SI1] | 2018-09-28 | 2018-10-01 | 1 | 2018-10-01 | [14 empty] | 2018-10-09 | 2018-10-10 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-10887 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6046 | Spackenkill | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2018-09-18 | 2018-09-25 | 5 | 2018-09-25 | [14 empty] | 2018-11-01 | 2018-11-15 |  | Y
Central Hudson |  | Vivint Solar Developer, LLC | CH-10889 | Fishkill | Wappingers Falls |  | 12590 | G | 8045 | Myers Corners | N |  | 4.14 | [13 empty] | NM | N | 18 Enphase Energy IQ6-60-X-US (240V) | 2018-09-19 | 2018-09-25 | 4 | 2018-09-25 | [17 empty] | W
Central Hudson |  | Empire Solar Solutions | CH-10890 | Kingston | Kingston | Ulster | 12401 | G | 1021 | East Kingston | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600A-US (240V) | 2018-10-02 | 2018-10-04 | 2 | 2018-10-04 | [14 empty] | 2018-10-04 | 2018-10-09 |  | Y
Central Hudson |  | SolarCity DBA Tesla Energy | CH-10896 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 7.6 | [13 empty] | NM | N | 1 Delta Electronics SOLIVIA 7.6 NA G4 TL (240V) | 2018-09-20 | 2018-09-25 | 3 | 2018-09-25 | [14 empty] | 2018-12-10 | 2018-12-14 |  | Y
Central Hudson |  | SunCommon | CH-10891 | Fishkill | Beacon | Dutchess | 12508 | G | 8015 | Forgebrook | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2018-09-20 | 2018-09-25 | 3 | 2018-09-25 | [14 empty] | 2018-10-02 | 2018-10-08 |  | Y
Central Hudson |  | SunCommon | CH-10892 | Fishkill | Garrison | Putnam | 10524 | G | 8066 | Merritt Park | N |  | 3 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3000x (240V) [SI1] | 2018-09-25 | 2018-09-26 | 1 | 2018-09-26 | [14 empty] | 2018-10-31 | 2018-11-01 |  | Y
Central Hudson |  | Kasselman Solar | CH-10894 | Newburgh | New Paltz | Ulster | 12561 | G | 5012 | Modena | N |  | 6.96 | [13 empty] | NM | N | 29 Enphase Energy IQ7-60-x-US (240V) | 2018-09-24 | 2018-09-25 | 1 | 2018-09-25 | [14 empty] | 2018-10-08 | 2018-10-23 |  | Y
Central Hudson |  | Kasselman Solar | CH-10895 | Catskill | Lexington | Greene | 12452 | E | 2389 | Vinegar Hill | N |  | 6.72 | [13 empty] | NM | N | 28 Enphase Energy IQ7-60-x-US (240V) | 2018-09-20 | 2018-09-25 | 3 | 2018-09-25 | [14 empty] | 2018-11-05 | 2018-11-08 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-10901 | Newburgh | Highland | Ulster | 12528 | G | 5024 | Ohioville | N |  | 7.1 | [13 empty] | NM | N | 1 SMA America SB7.0-1SP-US-40 (240V) | 2018-09-21 | 2018-09-25 | 2 | 2018-09-25 | [14 empty] | 2018-10-15 | 2018-10-19 |  | Y
Central Hudson |  | Borrego Solar Systems, Inc | CH-10900 | Catskill | Westerlo |  | 12083 | G | 1093 | Westerlo | TBD |  |  | 5000 | [12 empty] | CDG | N | 2Power ElectronicsHEMK PCS, FS2000K and FS3000K | 2018-11-26 | 2018-11-28 | 2 | 2018-11-28 | 2018-11-28 | 2018-12-18 | 14 | 2019-01-09 | 2019-04-16 | 2019-06-11 | 38 | 1897.88 | 3697128 | [7 empty] | 2019-09-06 | W |  | ESS application intended to be combined with PV application CH-00609. PV plus ESS total export will be limited to 5 MW-AC. Project following ESS + PV Interim Guidelines Tier 3. 3/25/19 - CESIR placed on hold due to awaiting documentation from applicant.
Central Hudson |  | Borrego Solar Systems, Inc | CH-10899 | Catskill | Westerlo |  | 12083 | G | 1093 | Westerlo | TBD |  |  | 5000 | [12 empty] | CDG | N | 2Power ElectronicsHEMK PCS, FS2000K and FS3000K | 2018-11-26 | 2018-11-28 | 2 | 2018-11-28 | 2018-11-28 | 2018-12-18 | 14 | 2019-01-09 | 2019-04-16 | 2019-06-11 | 38 | 1897.87 | 3697128 | [7 empty] | 2019-09-06 | W |  | ESS application intended to be combined with PV application CH-00610. PV plus ESS total export will be limited to 5 MW-AC. Project following ESS + PV Interim Guidelines Tier 3. 3/25/19 - CESIR placed on hold due to awaiting documentation from applicant.
Central Hudson |  | Borrego Solar Systems, Inc. | CH-10898 | Kingston | Accord |  | 12404 | G | 3024 | High Falls | TBD |  |  | 4000 | [12 empty] | CDG | N | 2Power ElectronicsHEMK PCS, FS2000K | 2018-11-26 | 2018-11-28 | 2 | 2018-11-28 | 2018-11-28 | 2018-12-18 | 14 | 2019-01-09 | 2019-02-21 | 2019-05-17 | 60 | 3809.83 | 18934 | [7 empty] | 2019-09-06 | W |  | ESS application intended to be combined with PV application CH-00600. PV plus ESS total export will be limited to 4 MW-AC. Project following ESS + PV Interim Guidelines Tier 3.
Central Hudson |  | Borrego Solar Systems, Inc | CH-10897 | Kingston | Kerhonkson |  | 12446 | G | 3081 | Kerhonkson | TBD |  |  | 3960 | [12 empty] | CDG | N | 2Power ElectronicsFP1980KW AC | 2018-11-15 | 2018-11-28 | 7 | 2018-11-28 | 2018-11-28 | 2018-12-18 | 14 | 2019-01-09 | [12 empty] | 2019-05-30 | W |  | ESS application intended to be combined with PV application CH-00598. PV plus ESS total export will be limited to 4 MW-AC. Project following ESS + PV Interim Guidelines Tier 3.
Central Hudson |  | Sunrun Installation Services, Inc. | CH-10907 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6046 | Spackenkill | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE 11400A-US (240V) | 2018-09-24 | 2018-09-25 | 1 | 2018-09-25 | [14 empty] | 2018-11-06 | 2018-11-13 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-10904 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6046 | Spackenkill | N |  | 16 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) 1 SolarEdge Technologies SE6000H-US (240V) [SI1] | 2018-09-24 | 2018-09-25 | 1 | 2018-09-25 | [14 empty] | 2018-10-29 | 2018-11-05 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-10906 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6046 | Spackenkill | N |  | 12.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) 1 SolarEdge Technologies SE5000H-US (240V) | 2018-09-24 | 2018-09-25 | 1 | 2018-09-25 | [14 empty] | 2018-11-01 | 2018-11-07 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-10903 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6046 | Spackenkill | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE 11400A-US (240V) | 2018-09-24 | 2018-09-25 | 1 | 2018-09-25 | [14 empty] | 2018-11-28 | 2018-12-07 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-10905 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6046 | Spackenkill | N |  | 5 | [13 empty] | NM | N | 1 SMA America SB5.0-1SP-US-40 (240V) | 2018-09-24 | 2018-09-25 | 1 | 2018-09-25 | [14 empty] | 2018-10-18 | 2018-10-24 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-10908 | Kingston | Accord | Ulster | 12404 | G | 3024 | High Falls | N |  | 3 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3000 (240V) | 2018-09-24 | 2018-09-25 | 1 | 2018-09-25 | [14 empty] | 2018-10-22 | 2018-10-23 |  | Y
Central Hudson |  | Lotus Solar | CH-10910 | Catskill | Athens | Greene | 12015 | G | 2002 | North Catskill | N | CH-10910 | 9.6 | [13 empty] | NM | N | 30 SunPower SPR-E20-327-D-AC (240V) | 2018-09-24 | 2018-09-25 | 1 | 2018-09-25 | [14 empty] | 2018-09-26 | 2018-09-27 |  | Y
Central Hudson |  | Apex Solar Power | CH-10909 | Kingston | Ulster Pk | Ulster | 12487 | G | 1023 | East Kingston | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000H-US (240V) | 2018-09-24 | 2018-09-25 | 1 | 2018-09-25 | [14 empty] | 2018-11-08 | 2018-11-13 |  | Y
Central Hudson |  | SolarCity DBA Tesla Energy | CH-10914 | Catskill | Cairo | Greene | 12413 | G | 2041 | South Cairo | N |  | 3 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3000H-US (240V) | 2018-09-25 | 2018-09-26 | 1 | 2018-09-26 | [14 empty] | 2018-10-31 | 2018-11-01 |  | Y
Central Hudson |  | PlugPV, LLC | CH-10912 | Kingston | Woodstock | Ulster | 12498 | G | 3014 | Woodstock | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600A-US (240V) | 2018-10-04 | 2018-10-04 | 0 | 2018-10-04 | [14 empty] | 2018-10-26 | 2018-10-26 |  | Y
Central Hudson |  | PlugPV, LLC | CH-10911 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8045 | Myers Corners | N |  | 17.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE 10000A-US (240V) 1 SolarEdge Technologies SE7600A-US (240V) | 2018-10-04 | 2018-10-04 | 0 | 2018-10-04 | [14 empty] | 2018-12-18 | 2018-12-18 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-10913 | Kingston | High Fls |  | 12440 | G | 3022 | High Falls | N |  | 10.08 | [13 empty] | NM | N | 36 Enphase Energy IQ6PLUS-72-X-US (240V) | 2018-09-25 | 2018-09-26 | 1 | 2018-09-26 | [8 empty] | 350 | 350 |  | 2018-09-27 | 2018-09-27 | 2018-10-31 |  |  |  | W
Central Hudson |  | Empire Solar Solutions | CH-10923 | Kingston | High Fls | Ulster | 12440 | G | 3024 | High Falls | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000 (240V) | 2018-10-02 | 2018-10-04 | 2 | 2018-10-04 | [14 empty] | 2018-11-21 | 2018-11-21 |  | Y
Central Hudson |  | SolarCity DBA Tesla Energy | CH-10921 | Newburgh | Cornwall | Orange | 12518 | G | 4094 | Bethlehem Rd | Y |  | 7.6 | 5 | [12 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) 1TeslaAC Powerwall 2.0 | 2018-12-21 | 2019-01-04 | 7 | 2019-01-04 | [14 empty] | 2019-01-08 | 2019-01-11 |  | Y
Central Hudson |  | Vivint Solar Developer, LLC | CH-10920 | Fishkill | Hopewell Jct |  | 12533 | G | 8071 | Shenandoah | N |  | 16.33 | [13 empty] | NM | N | 71 Enphase Energy IQ6-60-X-US (240V) | 2018-09-27 | 2018-10-01 | 2 | 2018-10-01 | [17 empty] | W
Central Hudson |  | PlugPV, LLC. | CH-10919 | Kingston | Hurley | Ulster | 12443 | G | 2093 | Hurley Ave | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE 11400A-US (240V) | 2018-09-27 | 2018-10-01 | 2 | 2018-10-01 | [14 empty] | 2018-11-20 | 2018-11-28 |  | Y
Central Hudson |  | SunCommon | CH-10915 | Kingston | Saugerties | Ulster | 12477 | G | 1021 | East Kingston | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2018-10-01 | 2018-10-01 | 0 | 2018-10-01 | [14 empty] | 2018-11-01 | 2018-11-07 |  | Y
Central Hudson |  | Vivint Solar Developer, LLC | CH-10917 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6068 | Inwood Ave | N |  | 6.44 | [13 empty] | NM | N | 28 Enphase Energy IQ6-60-x-US (240V) [SI1] | 2018-09-27 | 2018-10-01 | 2 | 2018-10-01 | [14 empty] | 2019-01-14 | 2019-01-21 |  | Y
Central Hudson |  | New York State Solar Farm | CH-10922 | Newburgh | Newburgh | Orange | 12550 | G | 4023 | Coldenham | Y | CH-10922 | 9.92 | [13 empty] | NM | N | 31 SunPower SPR-X22-360-D-AC (240V) | 2018-09-27 | 2018-10-01 | 2 | 2018-10-01 | [14 empty] | 2019-04-16 | 2019-04-17 |  | Y
Central Hudson |  | Apex Solar Power | CH-10916 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6093 | Manchester | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2018-10-15 | 2018-10-17 | 2 | 2018-10-17 | [14 empty] | 2018-11-20 | 2018-11-29 |  | Y
Central Hudson |  | PlugPV, LLC. | CH-10918 | Kingston | Saugerties | Ulster | 12477 | G | 2015 | Lincoln Park | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE 10000A-US (240V) | 2018-10-01 | 2018-10-01 | 0 | 2018-10-01 | [14 empty] | 2018-10-25 | 2018-10-30 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-10925 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 6051 | Todd Hill | N |  | 10.7 | [13 empty] | NM | N | 1 SMA America SB7.7-1SP-US-40 (240V) 1 SMA America SB3.0-1SP-US-40 (240V) | 2018-09-28 | 2018-10-01 | 1 | 2018-10-01 | [14 empty] | 2018-11-28 | 2018-12-06 |  | Y
Central Hudson |  | New York State Solar Farm | CH-10924 | Fishkill | Wappingers Falls | Dutchess | 12590 | G | 8091 | Fishkill Plains | N |  | 9.6 | [13 empty] | NM | N | 30 SunPower SPR-X22-360-D-AC (240V) | 2018-09-28 | 2018-10-01 | 1 | 2018-10-01 | [14 empty] | 2019-02-07 | 2019-02-08 |  | Y
Central Hudson |  | Albany Solar Solutions LLC | CH-10926 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8072 | Shenandoah | N |  | 4.2 | [13 empty] | NM | N | 7 Altenergy Power System YC600 (240V) [SI1] | 2018-10-01 | 2018-10-01 | 0 | 2018-10-01 | [14 empty] | 2018-12-31 | 2018-12-31 |  | Y
Central Hudson |  | SunCommon | CH-10928 | Kingston | Saugerties | Ulster | 12477 | G | 1021 | East Kingston | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2018-10-01 | 2018-10-01 | 0 | 2018-10-01 | [14 empty] | 2019-01-07 | 2019-01-08 |  | Y
Central Hudson |  | SunCommon | CH-10927 | Poughkeepsie | Staatsburg | Dutchess | 12580 | G | 7041 | Staatsburg | N |  | 20 | [13 empty] | NM | N | 2 SolarEdge Technologies SE 10000A-US (277V) | 2018-10-01 | 2018-10-01 | 0 | 2018-10-01 | [8 empty] | 350 | 350 |  | 2018-10-03 | 2018-10-03 | 2018-10-17 | 2019-01-08 | 2019-01-11 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-10929 | Newburgh | Campbell Hall | Orange | 10916 | G | 5052 | Maybrook | N |  | 8.96 | [13 empty] | NM | N | 28 SunPower SPR-X22-360-D-AC (240V) | 2018-10-01 | 2018-10-01 | 0 | 2018-10-01 | [14 empty] | 2019-01-21 | 2019-01-25 |  | Y
Central Hudson |  | Lighthouse Solar | CH-10930 | Kingston | Stone Ridge | Ulster | 12484 | G | 3023 | High Falls | N |  | 3.84 | [13 empty] | NM | N | 12 Enphase Energy IQ6PLUS-72-X-US (240V) | 2018-10-02 | 2018-10-02 | 0 | 2018-10-02 | [14 empty] | 2018-11-19 | 2018-11-20 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-10933 | Newburgh | Highland | Ulster | 12528 | G | 5081 | Highland | N |  | 7.7 | [13 empty] | NM | N | 1 SMA America SB7.7-1SP-US-40 (240V) | 2018-10-03 | 2018-10-04 | 1 | 2018-10-04 | [14 empty] | 2019-01-08 | 2019-01-09 |  | Y
Central Hudson |  | Kasselman Solar | CH-10935 | Catskill | Acra | Greene | 12405 | G | 2041 | South Cairo | N | CH-00234 | 0.5 | [13 empty] | NM | N | 2 Enphase Energy M250-60-2LL-S2X (-ZC) (-NA) (240V) | 2018-10-03 | 2018-10-04 | 1 | 2018-10-04 | [14 empty] | 2018-10-18 | 2018-10-22 |  | Y
Central Hudson |  | SunCommon | CH-10934 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8091 | Fishkill Plains | N |  | 10.88 | [13 empty] | NM | N | 34 SunPower SPR-X21-335-BLK-D-AC (240V) | 2018-10-03 | 2018-10-04 | 1 | 2018-10-04 | [14 empty] | 2018-12-07 | 2018-12-07 |  | Y
Central Hudson |  | SunCommon | CH-10931 | Poughkeepsie | Clinton Cors | Dutchess | 12514 | G | 7071 | Stanfordville | N |  | 8 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000H-US (208V) 1 SolarEdge Technologies SE3000H-US (240V) | 2018-10-03 | 2018-10-04 | 1 | 2018-10-04 | [8 empty] | 350 | 350 |  | 2018-10-05 | 2018-10-05 | 2018-10-17 | 2018-10-24 | 2018-10-25 |  | Y
Central Hudson |  | New York State Solar Farm | CH-10932 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6068 | Inwood Ave | N |  | 10.88 | [13 empty] | NM | N | 34 SunPower SPR-E20-327-D-AC (240V) | 2018-10-03 | 2018-10-04 | 1 | 2018-10-04 | [14 empty] | 2019-01-07 | 2019-01-08 |  | Y
Central Hudson |  | SolarCity DBA Tesla Energy | CH-10937 | Poughkeepsie | Hyde Park | Dutchess | 12538 | G | 6075 | East Park | N |  | 7.6 | [13 empty] | NM | N | 1 Delta Electronics SOLIVIA 7.6 NA G4 TL (240V) | 2018-10-04 | 2018-10-04 | 0 | 2018-10-04 | [14 empty] | 2018-10-09 | 2018-10-10 |  | Y
Central Hudson |  | Green Hybrid Energy Solutions Inc. | CH-10936 | Fishkill | Holmes | Dutchess | 12531 | G | 8071 | Shenandoah | N | CH-01147 | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2018-10-05 | 2018-10-05 | 0 | 2018-10-05 | [8 empty] | 350 | 350 |  | 2019-01-11 | 2019-01-11 | 2019-01-18 | 2019-01-24 | 2019-01-28 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-10938 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6093 | Manchester | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000 (240V) | 2018-10-04 | 2018-10-05 | 1 | 2018-10-05 | [14 empty] | 2018-10-15 | 2018-10-16 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-10940 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6011 | Sand Dock | N |  | 3.8 | [13 empty] | NM | N | 1 SMA America SB3.8-1SP-US-40 (240V) | 2018-10-05 | 2018-10-08 | 1 | 2018-10-08 | [14 empty] | 2018-11-16 | 2018-11-19 |  | Y
Central Hudson |  | SolarCity DBA Tesla Energy | CH-10939 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 6074 | East Park | N | CH-07531 | 3.3 | [13 empty] | NM | N | 1 ABB UNO-DM-3.3-TL-PLUS-US-SZ-RA (240V) [SI1] | 2018-10-05 | 2018-10-08 | 1 | 2018-10-08 | [14 empty] | 2019-11-18 | 2019-11-19 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-10941 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6011 | Sand Dock | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2018-10-05 | 2018-10-08 | 1 | 2018-10-08 | [14 empty] | 2019-05-15 | 2019-05-17 |  | Y
Central Hudson |  | Kasselman Solar | CH-10837 | Catskill | W Coxsackie | Greene | 12192 | G | 1076 | Coxsackie | N |  | 33.3 | [13 empty] | NM | N | 1 SolarEdge Technologies SE33.3KUS (480V) | 2018-12-13 | 2018-12-17 | 2 | 2018-12-17 | [14 empty] | 2019-01-11 | 2019-01-11 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-10943 | Newburgh | Newburgh | Orange | 12550 | G | 5041 | East Walden | N |  | 7 | [13 empty] | NM | N | 1 SMA America SB7.0-1SP-US-40 (240V) | 2018-10-08 | 2018-10-11 | 3 | 2018-10-11 | [14 empty] | 2018-12-28 | 2019-01-03 |  | Y
Central Hudson |  | PlugPV, LLC | CH-10942 | Kingston | Mt Marion | Ulster | 12456 | G | 2016 | Lincoln Park | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2018-10-08 | 2018-10-11 | 3 | 2018-10-11 | [14 empty] | 2018-12-27 | 2018-12-27 |  | Y
Central Hudson |  | murphy solar and central air | CH-10947 | Catskill | Athens | Greene | 12015 | G | 1074 | Coxsackie | N |  | 10 | [13 empty] | NM | N | 1 SMA America SB10000TL-US (240V) | 2018-10-09 | 2018-10-15 | 4 | 2018-10-15 | [14 empty] | 2019-09-12 | 2019-09-16 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-10946 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8096 | Fishkill Plains | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600A-US (240V) | 2018-10-09 | 2018-10-15 | 4 | 2018-10-15 | [14 empty] | 2018-11-06 | 2018-11-08 |  | Y
Central Hudson |  | New York State Solar Farm | CH-10944 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8072 | Shenandoah | N |  | 10.464 | [13 empty] | NM | N | 32 SunPower SPR-E20-327-D-AC (240V) | 2018-10-09 | 2018-10-12 | 3 | 2018-10-12 | [14 empty] | 2018-11-20 | 2018-11-20 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-10945 | Newburgh | Walden | Orange | 12586 | G | 4026 | Coldenham | N |  | 8.64 | [13 empty] | NM | N | 27 SunPower SPR-X22-360-D-AC (240V) | 2018-10-09 | 2018-10-15 | 4 | 2018-10-15 | [14 empty] | 2018-12-11 | 2018-12-12 |  | Y
Central Hudson |  | Vivint Solar Developer, LLC | CH-10952 | Kingston | Cottekill |  | 12419 | G | 3021 | High Falls | N |  | 4.4 | [13 empty] | NM | N | 19 Enphase Energy IQ6-60-x-US (240V) [SI1] | 2018-10-10 | 2018-10-15 | 3 | 2018-10-15 | [17 empty] | W
Central Hudson |  | PlugPV, LLC | CH-10950 | Kingston | Mt Marion | Ulster | 12456 | G | 2016 | Lincoln Park | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000 (240V) | 2018-10-10 | 2018-10-15 | 3 | 2018-10-15 | [14 empty] | 2018-11-30 | 2018-11-30 |  | Y
Central Hudson |  | PlugPV, LLC | CH-10949 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6061 | Inwood Ave | N |  | 3.8 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3800 (240V) | 2018-10-10 | 2018-10-15 | 3 | 2018-10-15 | [14 empty] | 2018-11-14 | 2018-11-15 |  | Y
Central Hudson |  | Tesla Energy Operations | CH-10951 | Fishkill | Fishkill | Dutchess | 12524 | G | 8051 | North Chelsea | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000 (240V) | 2018-11-29 | 2018-11-30 | 1 | 2018-11-30 | [14 empty] | 2018-12-06 | 2018-12-07 |  | Y
Central Hudson |  | Apex Solar Power | CH-10948 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6093 | Manchester | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2018-10-10 | 2018-10-15 | 3 | 2018-10-15 | [14 empty] | 2018-11-20 | 2018-11-29 |  | Y
Central Hudson |  | New York State Solar Farm | CH-10954 | Fishkill | Wappingrs Fls |  | 12590 | G | 8092 | Fishkill Plains | N |  | 8 | [13 empty] | NM | N | 25 SunPower SPR-E20-327-D-AC (240V) | 2018-10-11 | 2018-10-15 | 2 | 2018-10-15 | [17 empty] | W
Central Hudson |  | Kasselman Solar | CH-10953 | Catskill | Athens | Greene | 12015 | G | 2002 | North Catskill | N |  | 4.8 | [13 empty] | NM | N | 16 Enphase Energy IQ7-60-x-US (240V) | 2018-11-08 | 2018-11-09 | 1 | 2018-11-09 | [14 empty] | 2018-12-18 | 2018-12-21 |  | Y
Central Hudson |  | Solar Generation | CH-10956 | Kingston | Saugerties | Ulster | 12477 | G | 3002 | Saugerties | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2018-10-16 | 2018-10-16 | 0 | 2018-10-16 | [14 empty] | 2018-11-21 | 2018-11-28 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-10955 | Fishkill | Fishkill | Dutchess | 12524 | G | 8065 | Merritt Park | N |  | 14.4 | [13 empty] | NM | N | 45 SunPower SPR-X22-360-D-AC (240V) | 2018-10-11 | 2018-10-16 | 3 | 2018-10-16 | [14 empty] | 2019-01-07 | 2019-01-11 |  | Y
Central Hudson |  | Solar Generation | CH-10957 | Kingston | Kingston | Ulster | 12401 | G | 2017 | Lincoln Park | N | CH-10957 | 28.8 | [13 empty] | NM | N | 2 SolarEdge Technologies SE14.4KUS (208V) | 2018-11-15 | 2018-11-19 | 2 | 2018-11-19 | [14 empty] | 2019-01-31 | 2019-01-31 |  | Y
Central Hudson |  | Solar Generation Projects, LLC | CH-10902 | Catskill | Hannacroix | Greene | 12087 | G | 1083 | New Baltimore | N |  | 600 | [13 empty] | CDG | Y | 6 Chint Power Systems America CPS SCH100KTL-DO/US-600 (600V) | 2018-12-20 | 2019-01-08 | 10 | 2019-01-08 | 2019-01-08 | 2019-01-28 | 14 | [5 empty] | 310642.5 | 94833.32 |  | 2019-08-14 | 2019-08-14 | 2020-11-03 | 2020-12-07 | 2020-12-07 | 2021-02-25 | Y | Y
Central Hudson |  | Solar Generation | CH-10958 | Kingston | Kingston | Ulster | 12401 | G | 1013 | Boulevard | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2018-10-29 | 2018-11-06 | 6 | 2018-11-06 | [14 empty] | 2018-11-16 | 2018-11-19 |  | Y
Central Hudson |  | PlugPV, LLC. | CH-10960 | Newburgh | Newburgh | Orange | 12550 | G | 5001 | Marlboro | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2018-10-16 | 2018-10-16 | 0 | 2018-10-16 | [14 empty] | 2018-11-20 | 2018-11-20 |  | Y
Central Hudson |  | Kasselman Solar | CH-10959 | Catskill | Jewett |  | 12444 | E | 2389 | Vinegar Hill | N |  | 6.96 | [13 empty] | NM | N | 29 Enphase Energy IQ7-60-x-US (240V) | 2018-10-15 | 2018-10-16 | 1 | 2018-10-16 | [17 empty] | W
Central Hudson |  | New York State Solar Farm | CH-10962 | Newburgh | Highland | Ulster | 12528 | G | 5082 | Highland | N |  | 9.6 | [13 empty] | NM | N | 30 SunPower SPR-X22-360-D-AC (240V) | 2018-10-15 | 2018-10-16 | 1 | 2018-10-16 | [14 empty] | 2019-02-14 | 2019-02-21 |  | Y
Central Hudson |  | Solar Generation Projects, LLC | CH-10961 | Kingston | Saugerties | Ulster | 12477 | G | 3002 | Saugerties | N |  | 600 | [13 empty] | CDG | Y | 6 Chint Power Systems America CPS SCH100KTL-DO/US-600 (600V) | 2018-12-05 | 2018-12-14 | 7 | 2018-12-14 | 2018-12-14 | 2019-01-08 | 14 | 2019-01-31 | 2019-04-01 | 2019-06-26 | 60 | 11423.64 | 120900 | 126439.79 | 2019-07-01 | 2019-07-03 | 2019-07-03 | 2020-01-29 | 2020-02-21 | 2020-02-28 | 2020-05-26 | Y | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-10963 | Newburgh | Washingtonvl | Orange | 10992 | G | 4097 | Bethlehem Rd | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2018-10-16 | 2018-10-17 | 1 | 2018-10-17 | [8 empty] | 350 | 350 |  | 2018-11-02 | 2018-11-02 | 2019-01-14 | 2019-01-14 | 2019-01-21 |  | Y
Central Hudson |  | PlugPV, LLC. | CH-10965 | Poughkeepsie | Lagrangevl | Dutchess | 12540 | G | 6052 | Todd Hill | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) [SI1] | 2018-10-26 | 2018-11-06 | 7 | 2018-11-06 | [14 empty] | 2018-12-27 | 2018-12-31 |  | Y
Central Hudson |  | PlugPV, LLC. | CH-10966 | Newburgh | New Windsor | Orange | 12553 | G | 4046 | Union Ave | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE11400H-US (240V) | 2018-10-17 | 2018-10-17 | 0 | 2018-10-17 | [14 empty] | 2018-12-11 | 2018-12-18 |  | Y
Central Hudson |  | Kasselman Solar | CH-10969 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6064 | Inwood Ave | N |  | 6.24 | [13 empty] | NM | N | 26 Enphase Energy IQ7-60-x-US (240V) | 2018-10-17 | 2018-10-22 | 3 | 2018-10-22 | [14 empty] | 2018-11-27 | 2018-11-29 |  | Y
Central Hudson |  | SolarCity DBA Tesla Energy | CH-10968 | Kingston | Saugerties | Ulster | 12477 | G | 3002 | Saugerties | N |  | 8.2 | [13 empty] | NM | N | 1 Fronius USA Fronius Primo 8.2-1 208-240 (240V) | 2019-02-14 | 2019-02-22 | 5 | 2019-02-22 | [14 empty] | 2019-02-26 | 2019-03-08 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-10971 | Newburgh | Wallkill |  | 12589 | G | 5041 | East Walden | TBD |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2019-01-25 | 2019-01-31 | 4 | 2019-01-31 | [17 empty] | W
Central Hudson |  | Empire Solar Solutions | CH-10964 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8092 | Fishkill Plains | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000 (240V) | 2018-10-17 | 2018-10-17 | 0 | 2018-10-17 | [14 empty] | 2018-10-23 | 2018-10-25 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-10967 | Newburgh | Newburgh | Orange | 12550 | G | 4042 | Union Ave | N |  | 5.44 | [13 empty] | NM | N | 17 SunPower SPR-X22-360-D-AC (240V) | 2018-10-17 | 2018-10-22 | 3 | 2018-10-22 | [14 empty] | 2018-11-15 | 2018-11-15 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-10970 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6011 | Sand Dock | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2018-10-17 | 2018-10-22 | 3 | 2018-10-22 | [14 empty] | 2019-01-04 | 2019-01-10 |  | Y
Central Hudson |  | Lighthouse Solar | CH-10973 | Kingston | Accord | Ulster | 12404 | G | 3024 | High Falls | N |  | 7.83 | [13 empty] | NM | N | 27 Enphase Energy IQ7PLUS-72-x-US (240V) | 2018-10-29 | 2018-10-30 | 1 | 2018-10-30 | [14 empty] | 2018-11-19 | 2018-11-21 |  | Y
Central Hudson |  | American Solar Partners | CH-10976 | Newburgh | Campbell Hall | Orange | 10916 | G | 5052 | Maybrook | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (208V) | 2018-10-22 | 2018-10-23 | 1 | 2018-10-23 | [14 empty] | 2019-01-09 | 2019-01-11 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-10974 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6003 | Reynolds Hill | N |  | 3.8 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3800 (240V) | 2018-10-23 | 2018-10-23 | 0 | 2018-10-23 | [14 empty] | 2018-11-16 | 2018-11-19 |  | Y
Central Hudson |  | Solar Generation | CH-10975 | Newburgh | New Paltz | Ulster | 12561 | G | 5031 | Galeville | N |  | 15.2 | [13 empty] | NM | N | 2 Pika Energy X7602 (240V) | 2018-10-29 | 2018-11-06 | 6 | 2018-11-06 | [14 empty] | 2019-05-29 | 2019-05-31 |  | Y
Central Hudson |  | Lighthouse Solar | CH-10977 | Newburgh | New Paltz | Ulster | 12561 | G | 5031 | Galeville | N |  | 13.34 | [13 empty] | NM | N | 46 Enphase Energy IQ7PLUS-72-x-US (240V) | 2018-10-22 | 2018-10-23 | 1 | 2018-10-23 | [8 empty] | 350 | 350 |  | 2018-10-25 | 2018-10-25 | 2018-12-08 | 2018-12-10 | 2018-12-10 |  | Y
Central Hudson |  | New York State Solar Farm | CH-10978 | Fishkill | Beacon | Dutchess | 12508 | G | 8087 | Tioronda | N |  | 3.8 | [13 empty] | NM | N | 12 SunPower SPR-X22-360-D-AC (240V) | 2018-10-19 | 2018-10-22 | 1 | 2018-10-22 | [14 empty] | 2019-01-15 | 2019-01-21 |  | Y
Central Hudson |  | PlugPV, LLC | CH-10979 | Catskill | Coxsackie | Greene | 12051 | G | 1074 | Coxsackie | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600 (240V) | 2018-10-22 | 2018-10-22 | 0 | 2018-10-22 | [14 empty] | 2018-11-28 | 2018-11-30 |  | Y
Central Hudson |  | Lighthouse Solar | CH-10982 | Kingston | Kerhonkson | Ulster | 12446 | G | 3082 | Kerhonkson | N |  | 11.02 | [13 empty] | NM | N | 38 Enphase Energy IQ7PLUS-72-x-US (240V) | 2018-10-23 | 2018-10-23 | 0 | 2018-10-23 | [8 empty] | 350 | 350 |  | 2018-10-25 | 2018-10-25 | 2018-12-04 | 2018-12-05 | 2018-12-06 |  | Y
Central Hudson |  | SunCommon | CH-10981 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 6074 | East Park | N | CH-02080 | 4.8 | [13 empty] | NM | N | 15 SunPower SPR-X21-345-D-AC (240V) [SI1] | 2018-10-29 | 2018-10-30 | 1 | 2018-10-30 | [14 empty] | 2018-12-18 | 2018-12-18 |  | Y
Central Hudson |  | SunCommon | CH-10980 | Poughkeepsie | Millerton | Dutchess | 12546 | G | 7095 | Smithfield | N |  | 24.32 | [13 empty] | NM | N | 76 SunPower SPR-X22-360-C-AC (240V) | 2018-10-23 | 2018-10-23 | 0 | 2018-10-23 | [8 empty] | 350 | 350 |  | 2018-10-30 | 2018-10-30 | 2018-12-18 | 2018-12-18 | 2018-12-21 |  | Y
Central Hudson |  | Vivint Solar Developer, LLC | CH-10985 | Kingston | Ellenville | Ulster | 12428 | G | 3078 | Greenfield Rd | N |  | 3.19 | [13 empty] | NM | N | 17 Enphase Energy IQ6-60-X-US (240V) | 2018-10-25 | 2018-10-26 | 1 | 2018-10-26 | [14 empty] | 2019-03-13 | 2019-03-14 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-10983 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6046 | Spackenkill | N |  | 3.8 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3800 (240V) | 2018-10-22 | 2018-10-23 | 1 | 2018-10-23 | [14 empty] | 2018-12-21 | 2018-12-28 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-10984 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6046 | Spackenkill | N |  | 3.8 | [13 empty] | NM | N | 1 SMA America SB3.8-1SP-US-40 (240V) | 2018-10-22 | 2018-10-23 | 1 | 2018-10-23 | [14 empty] | 2018-12-18 | 2018-12-21 |  | Y
Central Hudson |  | New York State Solar Farm | CH-10989 | Kingston | Accord | Ulster | 12404 | G | 3024 | High Falls | N |  | 4.16 | [13 empty] | NM | N | 13 SunPower SPR-E20-327-D-AC (240V) | 2018-10-24 | 2018-10-26 | 2 | 2018-10-26 | [14 empty] | 2019-04-11 | 2019-04-12 |  | Y
Central Hudson |  | SolarCity DBA Tesla Energy | CH-10987 | Kingston | Saugerties | Ulster | 12477 | G | 3003 | Saugerties | N |  | 5.2 | [13 empty] | NM | N | 1 Delta Electronics SOLIVIA 5.2 NA G4 TL (240V) | 2018-10-23 | 2018-10-23 | 0 | 2018-10-23 | [14 empty] | 2018-12-12 | 2018-12-14 |  | Y
Central Hudson |  | Kasselman Solar | CH-10986 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8072 | Shenandoah | N |  | 6.7 | [13 empty] | NM | N | 28 Enphase Energy IQ7-60-x-US (240V) | 2018-10-23 | 2018-10-23 | 0 | 2018-10-23 | [14 empty] | 2018-11-09 | 2018-11-12 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-10988 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6011 | Sand Dock | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2018-10-24 | 2018-10-26 | 2 | 2018-10-26 | [14 empty] | 2019-01-04 | 2019-01-10 |  | Y
Central Hudson |  | Costanza Solar, LLC | CH-10991 | Catskill | Westerlo |  | 12193 | G | 1092 | Westerlo | TBD |  |  | 1980 | [12 empty] | CDG | N | 1Power ElectronicsFS2001K | 2019-01-14 | 2019-01-25 | 9 | 2019-01-25 | [17 empty] | W |  | ESS application intended be combined with PV application CH-03276.
Central Hudson |  | Empire Solar Solutions | CH-10990 | Fishkill | Beacon | Dutchess | 12508 | G | 8018 | Forgebrook | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000 (240V) | 2018-10-25 | 2018-10-26 | 1 | 2018-10-26 | [14 empty] | 2018-11-05 | 2018-11-08 |  | Y
Central Hudson |  | Murphy Solar and Central Air | CH-10992 | Catskill | Catskill | Greene | 12414 | G | 2003 | North Catskill | N |  | 10 | [13 empty] | NM | N | 1 SMA America SB10000TL-US (240V) | 2018-10-25 | 2018-10-30 | 3 | 2018-10-30 | [8 empty] | 350 | 350 |  | 2018-11-13 | 2018-11-13 | 2018-11-20 | 2019-05-13 | 2019-05-15 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-10996 | Fishkill | Poughkeepsie | Dutchess | 12601 | G | 8021 | Knapps Corners | N |  | 5 | [13 empty] | NM | N | 1 SMA America SB5.0-1SP-US-40 (240V) | 2018-10-25 | 2018-10-26 | 1 | 2018-10-26 | [14 empty] | 2018-11-15 | 2018-11-20 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-10994 | Newburgh | Rock Tvrn | Orange | 12575 | G | 4097 | Bethlehem Rd | N |  | 4.48 | [13 empty] | NM | N | 14 SunPower SPR-E20-327-C-AC (240V) | 2018-10-25 | 2018-10-26 | 1 | 2018-10-26 | [14 empty] | 2018-12-17 | 2018-12-18 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-10995 | Newburgh | Newburgh | Orange | 12550 | G | 4015 | West Balmville | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000 (240V) | 2018-10-25 | 2018-10-26 | 1 | 2018-10-26 | [14 empty] | 2018-11-08 | 2018-11-09 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-10997 | Newburgh | Wallkill | Ulster | 12589 | G | 5041 | East Walden | N |  | 15.2 | [13 empty] | NM | N | 1 SolarEdge Technologies SE11400H-US (240V) 1 SolarEdge Technologies SE3800x (240V) [SI1] | 2018-10-25 | 2018-10-26 | 1 | 2018-10-26 | [8 empty] | 350 | 350 |  | 2018-11-02 | 2018-11-02 | 2018-11-14 | 2018-11-28 | 2018-12-04 |  | Y
Central Hudson |  | Kasselman Solar | CH-11000 | Kingston | Saugerties | Ulster | 12477 | G | 3004 | Saugerties | N |  | 5.28 | [13 empty] | NM | N | 22 Enphase Energy IQ7-60-x-US (240V) | 2018-10-26 | 2018-10-26 | 0 | 2018-10-26 | [14 empty] | 2018-12-19 | 2018-12-21 |  | Y
Central Hudson |  | Vivint Solar Developer, LLC | CH-10999 | Newburgh | Modena | Ulster | 12548 | G | 5012 | Modena | N |  | 3.68 | [13 empty] | NM | N | 16 Enphase Energy IQ6-60-X-US (240V) | 2018-10-31 | 2018-11-08 | 6 | 2018-11-08 | [14 empty] | 2019-02-04 | 2019-02-07 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-11001 | Poughkeepsie | Millerton | Dutchess | 12546 | G | 7081 | Millerton | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600A-US (240V) [SI1] | 2018-10-26 | 2018-10-30 | 2 | 2018-10-30 | [14 empty] | 2018-11-05 | 2018-11-08 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-11002 | Kingston | Woodstock | Ulster | 12498 | G | 3012 | Woodstock | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE 10000A-US (240V) | 2018-10-26 | 2018-10-29 | 1 | 2018-10-29 | [14 empty] | 2018-11-05 | 2018-11-08 |  | Y
Central Hudson |  | New York State Solar Farm | CH-11004 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7054 | Rhinebeck | N |  | 36.8 | [13 empty] | NM | N | 115 SunPower SPR-X21-350-BLK-D-AC (240V) | 2018-11-06 | 2018-11-19 | 9 | 2018-11-19 | [8 empty] | 3000 | 1229.08 |  | 2018-11-29 | 2018-11-29 | 2018-12-19 | 2019-01-10 | 2019-01-10 | 2019-01-10 | Y
Central Hudson |  | New York State Solar Farm | CH-11005 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7054 | Rhinebeck | N |  | 11.2 | [13 empty] | NM | N | 35 SunPower SPR-X21-350-BLK-D-AC (240V) | 2018-10-26 | 2018-11-06 | 7 | 2018-11-06 | [14 empty] | 2019-01-10 | 2019-01-10 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-11003 | Poughkeepsie | Salt Pt | Dutchess | 12578 | G | 7011 | Hibernia | N |  | 3.8 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3800 (240V) | 2018-10-26 | 2018-10-29 | 1 | 2018-10-29 | [14 empty] | 2018-11-05 | 2018-11-08 |  | Y
Central Hudson |  | Vivint Solar Developer, LLC | CH-10998 | Newburgh | Wallkill | Ulster | 12589 | G | 5013 | Modena | N |  | 6.21 | [13 empty] | NM | N | 27 Enphase Energy IQ6-60-x-US (240V) [SI1] | 2019-01-02 | 2019-01-07 | 3 | 2019-01-07 | [14 empty] | 2020-03-02 | 2020-03-06 |  | Y
Central Hudson |  | New York State Solar Farm | CH-11006 | Poughkeepsie | Staatsburg | Dutchess | 12580 | G | 7013 | Hibernia | N |  | 11.2 | [13 empty] | NM | N | 35 SunPower SPR-X22-360-D-AC (240V) | 2018-10-29 | 2018-10-30 | 1 | 2018-10-30 | [14 empty] | 2019-03-18 | 2019-04-02 |  | Y
Central Hudson |  | Solar Generation | CH-11009 | Kingston | Kingston | Ulster | 12401 | G | 2016 | Lincoln Park | N | CH-08102 | 13.35 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600A-US (240V) 1 SolarEdge Technologies SE5000H-US (240V) | 2018-10-29 | 2018-11-06 | 6 | 2018-11-06 | [14 empty] | 2019-01-03 | 2019-01-11 |  | Y
Central Hudson |  | New York State Solar Farm | CH-11010 | Newburgh | Newburgh | Orange | 12550 | G | 5001 | Marlboro | N |  | 6.72 | [13 empty] | NM | N | 21 SunPower SPR-E20-327-D-AC (240V) | 2018-10-29 | 2018-11-06 | 6 | 2018-11-06 | [14 empty] | 2018-12-17 | 2018-12-18 |  | Y
Central Hudson |  | PlugPV, LLC | CH-11008 | Catskill | Catskill | Greene | 12414 | G | 2003 | North Catskill | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000 (240V) | 2018-10-29 | 2018-10-30 | 1 | 2018-10-30 | [14 empty] | 2018-12-07 | 2018-12-11 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-11012 | Kingston | Saugerties | Ulster | 12477 | G | 3001 | Saugerties | N |  | 7.1 | [13 empty] | NM | N | 1 SMA America SB7.0-1SP-US-40 (240V) | 2018-10-30 | 2018-11-08 | 7 | 2018-11-08 | [14 empty] | 2018-12-12 | 2018-12-14 |  | Y
Central Hudson |  | Solar Liberty Energy Systems, Inc. | CH-11014 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6095 | Manchester | N |  | 6.4 | [13 empty] | NM | N | 20 SunPower SPR-X22-360-C-AC (240V) | 2018-11-15 | 2018-11-16 | 1 | 2018-11-16 | [14 empty] | 2019-01-31 | 2019-01-31 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-11016 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6046 | Spackenkill | N |  | 7.1 | [13 empty] | NM | N | 1 SMA America SB7.0-1SP-US-40 (240V) | 2018-10-31 | 2018-11-08 | 6 | 2018-11-08 | [14 empty] | 2018-12-28 | 2019-01-08 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-11017 | Newburgh | Cornwall | Orange | 12518 | G | 4041 | Union Ave | N |  | 6 | [13 empty] | NM | N | 22 Enphase Energy IQ7X-96-x-US (240V) | 2018-11-12 | 2018-11-13 | 1 | 2018-11-13 | [14 empty] | 2019-02-06 | 2019-02-07 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-11015 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6046 | Spackenkill | N |  | 10.1 | [13 empty] | NM | N | 2 SMA America SB5.0-1SP-US-40 (240V) | 2018-10-31 | 2018-11-08 | 6 | 2018-11-08 | [14 empty] | 2018-12-13 | 2018-12-17 |  | Y
Central Hudson |  | Kasselman Solar | CH-11019 | Fishkill | Stormvl | Dutchess | 12582 | G | 8071 | Shenandoah | N |  | 11.04 | [13 empty] | NM | N | 46 Enphase Energy IQ7-60-x-US (240V) | 2018-11-01 | 2018-11-08 | 5 | 2018-11-08 | [14 empty] | 2019-01-10 | 2019-01-11 |  | Y
Central Hudson |  | Kasselman Solar | CH-11018 | Catskill | E Durham | Greene | 12423 | G | 1092 | Westerlo | N |  | 9.6 | [13 empty] | NM | N | 32 Enphase Energy IQ7-60-x-US (240V) | 2018-11-01 | 2018-11-08 | 5 | 2018-11-08 | [14 empty] | 2018-11-15 | 2018-11-19 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-11024 | Newburgh | New Windsor | Orange | 12553 | G | 4044 | Union Ave | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000 (240V) | 2018-11-02 | 2018-11-08 | 4 | 2018-11-08 | [14 empty] | 2018-11-14 | 2018-11-15 |  | Y
Central Hudson |  | Kasselman Solar | CH-11020 | Poughkeepsie | Lagrangevl |  | 12540 | G | 6055 | Todd Hill | TBD |  | 5.76 | [13 empty] | NM | N | 18 Enphase Energy IQ7-60-x-US (240V) | 2018-11-02 | 2018-11-08 | 4 | 2018-11-08 | [17 empty] | W
Central Hudson |  | Kasselman Solar | CH-11021 | Poughkeepsie | Lagrangevl |  | 12540 | G | 6055 | Todd Hill | TBD |  | 0.48 | [13 empty] | NM | N | 2 Enphase Energy IQ7-60-x-US (240V) | 2018-11-02 | 2018-11-08 | 4 | 2018-11-08 | [17 empty] | W
Central Hudson |  | Kasselman Solar | CH-11022 | Poughkeepsie | Lagrangevl |  | 12540 | G | 6055 | Todd Hill | TBD |  | 2.56 | [13 empty] | NM | N | 8 Enphase Energy IQ7-60-x-US (240V) | 2018-11-02 | 2018-11-08 | 4 | 2018-11-08 | [17 empty] | W
Central Hudson |  | Infinity Solar Systems | CH-11025 | Newburgh | New Windsor | Orange | 12553 | G | 4094 | Bethlehem Rd | N |  | 14.58 | [13 empty] | NM | N | 66 Enphase Energy IQ6-60-X-US (240V) | 2018-11-05 | 2018-11-08 | 3 | 2018-11-08 | [8 empty] | 350 | 350 |  | 2018-11-09 | 2018-11-09 | 2019-01-09 | 2019-01-11 | 2019-01-11 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-11027 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6046 | Spackenkill | N |  | 7.8 | [13 empty] | NM | N | 1 SMA America SB7.7-1SP-US-40 (240V) | 2018-11-05 | 2018-11-08 | 3 | 2018-11-08 | [8 empty] | 350 | 350 |  | 2018-11-26 | 2018-11-26 | 2018-12-28 | 2018-12-21 | 2018-12-28 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-11026 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6011 | Sand Dock | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE11400H-US (240V) | 2018-11-05 | 2018-11-08 | 3 | 2018-11-08 | [8 empty] | 350 | 350 |  | 2018-11-26 | 2018-11-26 | 2018-11-28 | 2019-01-16 | 2019-01-22 |  | Y
Central Hudson |  | PlugPV, LLC | CH-11028 | Catskill | Catskill | Greene | 12414 | G | 2005 | North Catskill | N | CH-11028 | 3 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3000H-US (240V) | 2018-12-06 | 2018-12-07 | 1 | 2018-12-07 | [14 empty] | 2018-12-27 | 2018-12-27 |  | Y
Central Hudson |  | New York State Solar Farm | CH-11035 | Fishkill | Garrison | Putnam | 10524 | G | 8086 | Tioronda | N | CH-11035 | 5.76 | [13 empty] | NM | N | 18 SunPower SPR-E20-327-D-AC (240V) | 2018-11-06 | 2018-11-09 | 3 | 2018-11-09 | [14 empty] | 2018-11-19 | 2018-11-19 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-11032 | Poughkeepsie | Staatsburg | Dutchess | 12580 | G | 7041 | Staatsburg | N |  | 3 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3000 (240V) | 2018-11-06 | 2018-11-09 | 3 | 2018-11-09 | [14 empty] | 2018-11-12 | 2018-11-12 |  | Y
Central Hudson |  | New York State Solar Farm | CH-11034 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7062 | Milan | N |  | 3.84 | [13 empty] | NM | N | 12 SunPower SPR-X22-360-D-AC (208V) | 2018-11-06 | 2018-11-09 | 3 | 2018-11-09 | [14 empty] | 2018-12-21 | 2018-12-26 |  | Y
Central Hudson |  | Lighthouse Solar | CH-11031 | Poughkeepsie | Stanfordvl | Dutchess | 12581 | G | 7072 | Stanfordville | N |  | 45.6 | [13 empty] | RC | Y | 4 SolarEdge Technologies SE11400H-US (240V) | 2018-11-13 | 2018-11-29 | 10 | 2018-11-29 | [8 empty] | 3200 | 1426.52 |  | 2018-12-03 | 2018-12-03 | 2019-02-22 | 2019-06-14 | 2019-06-21 | 2019-06-21 | Y | Y
Central Hudson |  | Infinity Solar Systems | CH-11030 | Newburgh | New Windsor | Orange | 12553 | G | 4094 | Bethlehem Rd | N |  | 9.6 | [13 empty] | NM | N | 30 SunPower SPR-X22-360-D-AC (240V) | 2018-11-06 | 2018-11-09 | 3 | 2018-11-09 | [14 empty] | 2019-01-21 | 2019-01-25 |  | Y
Central Hudson |  | Empire Solar Soltuions | CH-11029 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6051 | Todd Hill | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE 11400A-US (240V) | 2018-11-06 | 2018-11-09 | 3 | 2018-11-09 | [8 empty] | 350 | 350 |  | 2018-11-12 | 2018-11-12 | 2018-11-28 | 2018-11-30 | 2018-12-04 |  | Y
Central Hudson |  | SunCommon | CH-11033 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 7011 | Hibernia | N |  | 10.88 | [13 empty] | NM | N | 34 SunPower SPR-X21-345-D-AC (240V) [SI1] | 2018-11-06 | 2018-11-09 | 3 | 2018-11-09 | [14 empty] | 2018-12-06 | 2018-12-07 |  | Y
Central Hudson |  | Vivint Solar Developer, LLC | CH-11040 | Poughkeepsie | Lagrangevl | Dutchess | 12540 | G | 6055 | Todd Hill | N |  | 6.44 | [13 empty] | NM | N | 28 Enphase Energy IQ6-60-X-US (240V) | 2019-01-02 | 2019-01-07 | 3 | 2019-01-07 | [14 empty] | 2019-11-20 | 2019-11-20 |  | Y
Central Hudson |  | Vivint Solar Developer, LLC | CH-11038 | Newburgh | Cornwall | Orange | 12518 | G | 4093 | Bethlehem Rd | N |  | 16.79 | [13 empty] | NM | N | 73 Enphase Energy IQ6-60-X-US (240V) | 2018-11-12 | 2018-11-13 | 1 | 2018-11-13 | [14 empty] | 2019-05-14 | 2019-05-16 |  | Y
Central Hudson |  | SunCommon | CH-11039 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 7041 | Staatsburg | Y | CH-11039 | 13.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) 1 SolarEdge Technologies SE6000H-US (240V) | 2018-11-07 | 2018-11-09 | 2 | 2018-11-09 | [14 empty] | 2019-05-03 | 2019-05-07 |  | Y
Central Hudson |  | SunCommon | CH-11037 | Kingston | Kingston | Ulster | 12401 | G | 2012 | Lincoln Park | N |  | 6.72 | [13 empty] | NM | N | 21 SunPower SPR-X22-360-D-AC (240V) [SI1] | 2018-11-07 | 2018-11-09 | 2 | 2018-11-09 | [14 empty] | 2018-12-17 | 2018-12-18 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-11036 | Newburgh | Walden | Orange | 12586 | G | 5042 | East Walden | N |  | 9.28 | [13 empty] | NM | N | 29 SunPower SPR-X22-360-D-AC (240V) | 2018-11-07 | 2018-11-09 | 2 | 2018-11-09 | [14 empty] | 2019-01-16 | 2019-01-28 |  | Y
Central Hudson |  | PlugPV, LLC | CH-11043 | Kingston | Kingston | Ulster | 12401 | G | 2013 | Lincoln Park | N |  | 3.8 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3800x (240V) [SI1] | 2018-11-30 | 2018-12-06 | 4 | 2018-12-06 | [14 empty] | 2018-12-11 | 2018-12-12 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-11042 | Kingston | Kingston | Ulster | 12401 | G | 2093 | Hurley Ave | N |  | 10.56 | [13 empty] | NM | N | 33 SunPower SPR-X21-345-C-AC (240V) | 2018-11-08 | 2018-11-09 | 1 | 2018-11-09 | [8 empty] | 350 | 350 |  | 2018-11-12 | 2018-11-12 | 2018-12-07 | 2019-01-02 | 2019-01-03 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-11041 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8024 | Knapps Corners | N |  | 7.68 | [13 empty] | NM | N | 24 Enphase Energy IQ7X-96-x-US (240V) | 2018-11-08 | 2018-11-09 | 1 | 2018-11-09 | [14 empty] | 2019-02-06 | 2019-02-07 |  | Y
Central Hudson |  | Apex Solar Power | CH-11044 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 6073 | East Park | N |  | 13 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3000H-US (240V) 1 SolarEdge Technologies SE10000H-US (240V) | 2018-11-09 | 2018-11-13 | 2 | 2018-11-13 | [14 empty] | 2019-02-12 | 2019-02-13 |  | Y
Central Hudson |  | SolarCity DBA Tesla Energy | CH-11048 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8095 | Fishkill Plains | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE 10000A-US (240V) | 2018-11-09 | 2018-11-13 | 2 | 2018-11-13 | [14 empty] | 2018-11-15 | 2018-11-19 |  | Y
Central Hudson |  | SolarCity DBA Tesla Energy | CH-11049 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 7.6 | [13 empty] | NM | N | 1 Delta Electronics SOLIVIA 7.6 NA G4 TL (240V) | 2018-11-09 | 2018-11-13 | 2 | 2018-11-13 | [14 empty] | 2018-12-13 | 2018-12-17 |  | Y
Central Hudson |  | New York State Solar Farm | CH-11046 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6046 | Spackenkill | N |  | 3.84 | [13 empty] | NM | N | 12 SunPower SPR-X22-360-D-AC (240V) | 2018-11-09 | 2018-11-13 | 2 | 2018-11-13 | [14 empty] | 2018-12-18 | 2018-12-21 |  | Y
Central Hudson |  | Kasselman Solar | CH-11047 | Poughkeepsie | Clinton Cors |  | 12514 | G | 7071 | Stanfordville | N |  | 8.4 | [13 empty] | NM | N | 30 Enphase Energy IQ7PLUS-72-x-US (240V) | 2018-11-09 | 2018-11-13 | 2 | 2018-11-13 | [17 empty] | W
Central Hudson |  | Kasselman Solar | CH-11045 | Catskill | Catskill | Greene | 12414 | G | 2006 | North Catskill | N |  | 2.52 | [13 empty] | NM | N | 9 Enphase Energy IQ7PLUS-72-x-US (240V) | 2018-11-09 | 2018-11-13 | 2 | 2018-11-13 | [14 empty] | 2018-12-20 | 2018-12-21 |  | Y
Central Hudson |  | murphy solar and central air | CH-11050 | Catskill | E Durham | Greene | 12423 | G | 2043 | South Cairo | N |  | 5 | [13 empty] | NM | N | 1 SMA America SB5000US-11 (240V) | 2018-11-12 | 2018-11-13 | 1 | 2018-11-13 | [14 empty] | 2019-05-13 | 2019-05-15 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-11051 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8094 | Fishkill Plains | N |  | 15.2 | [13 empty] | NM | N | 2 SolarEdge Technologies SE7600A-US (240V) | 2018-11-12 | 2018-11-15 | 3 | 2018-11-15 | [14 empty] | 2018-12-14 | 2018-12-14 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-11052 | Poughkeepsie | Poughkeepsie |  | 12603 | G | 6046 | Spackenkill | N |  | 3 | [13 empty] | NM | N | 1 SMA America SB3.0-1SP-US-40 (240V) | 2018-11-12 | 2018-11-15 | 3 | 2018-11-15 | [17 empty] | W
Central Hudson |  | Kasselman Solar | CH-11053 | Kingston | Saugerties | Ulster | 12477 | G | 3004 | Saugerties | N |  | 10.8 | [13 empty] | NM | N | 45 Enphase Energy IQ7-60-x-US (240V) | 2018-11-13 | 2018-11-16 | 3 | 2018-11-16 | [14 empty] | 2018-12-03 | 2018-12-11 |  | Y
Central Hudson |  | Tesla Energy Operations, Inc. | CH-11061 | Kingston | Hurley | Ulster | 12443 | G | 2094 | Hurley Ave | Y |  | 3.8 | 10 | [12 empty] | NM | N | 1 ABB UNO-DM-3.8-TL-PLUS-US-SZ-RA (240V) 2TeslaAC Powerwall 2.0 | 2019-01-16 | 2019-01-28 | 8 | 2019-01-28 | [8 empty] | 350 | 350 |  | 2019-02-01 | 2019-02-01 | 2019-03-27 | 2019-04-04 | 2019-04-05 |  | Y
Central Hudson |  | New York State Solar Farm | CH-11057 | Newburgh | Montgomery | Orange | 12549 | G | 5073 | Montgomery | N |  | 4.48 | [13 empty] | NM | N | 14 SunPower SPR-X22-360-D-AC (240V) | 2018-11-14 | 2018-11-16 | 2 | 2018-11-16 | [14 empty] | 2019-01-17 | 2019-01-23 |  | Y
Central Hudson |  | Kasselman Solar | CH-11060 | Kingston | Kingston | Ulster | 12401 | G | 112 | South Wall St | N |  | 3.84 | [13 empty] | NM | N | 16 Enphase Energy IQ7-60-x-US (240V) | 2018-11-14 | 2018-11-16 | 2 | 2018-11-16 | [14 empty] | 2018-12-05 | 2018-12-06 |  | Y
Central Hudson |  | SunCommon | CH-11055 | Kingston | W Shokan | Ulster | 12494 | G | 3011 | Woodstock | N |  | 5.44 | [13 empty] | NM | N | 10 SunPower SPR-X22-360-D-AC (240V) [SI1] 7 SunPower SPR-E20-327-C-AC (240V) | 2018-11-14 | 2018-11-16 | 2 | 2018-11-16 | [8 empty] | 350 | 350 |  | 2018-11-21 | 2018-11-21 | 2018-12-05 | 2018-12-28 | 2018-12-28 |  | Y
Central Hudson |  | SunCommon | CH-11058 | Catskill | Jewett | Greene | 12444 | E | 2081 | Hunter | N |  | 9.9 | [13 empty] | NM | N | 31 SunPower SPR-X22-360-D-AC (240V) [SI1] | 2018-11-14 | 2018-11-16 | 2 | 2018-11-16 | [14 empty] | 2019-01-28 | 2019-01-28 |  | Y
Central Hudson |  | SunCommon | CH-11056 | Catskill | E Durham | Greene | 12423 | G | 2071 | Freehold | N | CH-02011 | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000H-US (240V) | 2018-11-16 | 2018-11-19 | 1 | 2018-11-19 | [14 empty] | 2019-01-10 | 2019-01-11 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-11054 | Kingston | Olive Brdg | Ulster | 12461 | G | 3024 | High Falls | N |  | 3 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3000 (240V) | 2018-11-13 | 2018-11-16 | 3 | 2018-11-16 | [14 empty] | 2019-10-02 | 2019-10-07 |  | Y
Central Hudson |  | New York State Solar Farm | CH-11059 | Poughkeepsie | Lagrangevl | Dutchess | 12540 | G | 6055 | Todd Hill | N |  | 7.04 | [13 empty] | NM | N | 22 SunPower SPR-X22-360-D-AC (240V) | 2018-11-14 | 2018-11-16 | 2 | 2018-11-16 | [14 empty] | 2018-12-21 | 2018-12-26 |  | Y
Central Hudson |  | Cypress Creek Renewables | CH-11064 | Kingston | Ellenville |  | 12428 | G | 3096 | Grimley Rd | TBD |  |  | 1980 | [12 empty] | CDG | N | 1Power ElectronicsFS2001K | 2019-01-09 | 2019-01-23 | 10 | 2019-01-23 | [17 empty] | W |  | ESS application intended to be combined with PV application CH-03130. Project following ESS + PV Interim Guidelines Tier 2.
Central Hudson |  | Cypress Creek Renewables | CH-11065 | Poughkeepsie | Poughkeepsie |  | 12601 | G | 6061 | Inwood Ave | Y |  |  | 2000 | [12 empty] | CDG | Y | 1Power ElectronicsFS2001K | 2019-01-09 | 2019-01-23 | 10 | 2019-01-23 | [17 empty] | W |  | ESS application intended to be combined with PV application CH-03217. PV plus ESS total export will be limited to 1980 kW-AC. Project following ESS + PV Interim Guidelines Tier 2.
Central Hudson |  | PlugPV, LLC. | CH-11067 | Newburgh | Newburgh | Orange | 12550 | G | 4012 | West Balmville | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2018-11-14 | 2018-11-16 | 2 | 2018-11-16 | [14 empty] | 2018-11-19 | 2018-11-20 |  | Y
Central Hudson |  | New York State Solar Farm | CH-11070 | Kingston | Ellenvl | Ulster | 12428 | G | 396 | Clinton Ave | N |  | 3.52 | [13 empty] | NM | N | 11 SunPower SPR-X22-360-D-AC (240V) | 2018-11-15 | 2018-11-16 | 1 | 2018-11-16 | [14 empty] | 2018-12-05 | 2018-12-10 |  | Y
Central Hudson |  | Lighthouse Solar | CH-11069 | Kingston | Accord | Ulster | 12404 | G | 3082 | Kerhonkson | N |  | 5.8 | [13 empty] | NM | N | 20 Enphase Energy IQ6PLUS-72-X-US (240V) | 2018-11-14 | 2018-11-16 | 2 | 2018-11-16 | [14 empty] | 2018-12-13 | 2018-12-14 |  | Y
Central Hudson |  | PlugPV, LLC | CH-11066 | Newburgh | Campbell Hall | Orange | 10916 | G | 5052 | Maybrook | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE 10000A-US (240V) | 2018-11-14 | 2018-11-16 | 2 | 2018-11-16 | [14 empty] | 2019-01-29 | 2019-01-31 |  | Y
Central Hudson |  | Cypress Creek Renewables | CH-11071 | Catskill | Palenville |  | 12463 | G | 2385 | Lawrenceville | TBD |  |  | 1980 | [12 empty] | CDG | N | 1Power ElectronicsFS2001K | 2019-01-11 | 2019-01-11 | 0 | 2019-01-11 | [17 empty] | W |  | ESS application intended to be combined with PV application CH-03226. PV plus ESS total export will be limited to 1980 kW-AC.
Central Hudson |  | Infinity Solar Systems | CH-11068 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8091 | Fishkill Plains | N |  | 8.96 | [13 empty] | NM | N | 28 SunPower SPR-X22-360-D-AC (240V) | 2018-11-14 | 2018-11-16 | 2 | 2018-11-16 | [14 empty] | 2018-12-28 | 2018-12-28 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-11072 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6011 | Sand Dock | N |  | 3 | [13 empty] | NM | N | 1 SMA America SB3.0-1SP-US-40 (240V) | 2018-11-15 | 2018-11-16 | 1 | 2018-11-16 | [14 empty] | 2019-02-11 | 2019-02-12 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-11074 | Fishkill | Poughkeepsie | Dutchess | 12603 | G | 8022 | Knapps Corners | N |  | 7.1 | [13 empty] | NM | N | 1 SMA America SB7.0-1SP-US-40 (240V) | 2018-11-15 | 2018-11-16 | 1 | 2018-11-16 | [14 empty] | 2018-12-28 | 2018-12-28 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-11073 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6092 | Manchester | N |  | 12.8 | [13 empty] | NM | N | 1 SMA America SB7.7-1SP-US-40 (240V) 1 SMA America SB5.0-1SP-US-40 (240V) | 2018-11-15 | 2018-11-16 | 1 | 2018-11-16 | [14 empty] | 2019-01-28 | 2019-02-06 |  | Y
Central Hudson |  | Kasselman Solar | CH-11075 | Catskill | Catskill | Greene | 12414 | G | 2042 | South Cairo | N | CH-11075 | 4.8 | [13 empty] | NM | N | 20 Enphase Energy IQ7-60-x-US (240V) | 2018-11-16 | 2018-11-16 | 0 | 2018-11-16 | [14 empty] | 2018-12-03 | 2018-12-04 |  | Y
Central Hudson |  | PlugPV | CH-11077 | Poughkeepsie | Hyde Pk |  | 12538 | G | 6073 | East Park | TBD |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE 10000A-US (240V) | 2018-11-16 | 2018-11-19 | 1 | 2018-11-19 | [17 empty] | W
Central Hudson |  | Solar Generation | CH-11076 | Kingston | Cottekill | Ulster | 12419 | G | 3021 | High Falls | N |  | 3.8 | [13 empty] | NM | N | 1 SMA America SB3800US (240V) | 2018-11-19 | 2018-11-19 | 0 | 2018-11-19 | [14 empty] | 2019-01-16 | 2019-01-22 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-11078 | Poughkeepsie | Pine Plns | Dutchess | 12567 | G | 7091 | Pulvers Corners | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600A-US (240V) | 2018-11-16 | 2018-11-19 | 1 | 2018-11-19 | [14 empty] | 2019-01-24 | 2019-01-28 |  | Y
Central Hudson |  | US Energy Concierge, Inc | CH-11080 | Fishkill | Garrison | Putnam | 10524 | G | 8066 | Merritt Park | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2018-11-19 | 2018-11-20 | 1 | 2018-11-20 | [14 empty] | 2018-12-26 | 2018-12-26 |  | Y
Central Hudson |  | US Energy Concierge, Inc. | CH-11079 | Fishkill | Cold Spg | Putnam | 10516 | G | 8087 | Tioronda | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2018-11-19 | 2018-11-20 | 1 | 2018-11-20 | [14 empty] | 2018-12-26 | 2018-12-26 |  | Y
Central Hudson |  | New York State Solar Farm | CH-11084 | Newburgh | Marlboro | Ulster | 12542 | G | 5004 | Marlboro | N |  | 8.96 | [13 empty] | NM | N | 28 SunPower SPR-X21-350-BLK-D-AC (240V) | 2018-11-19 | 2018-11-20 | 1 | 2018-11-20 | [14 empty] | 2019-01-02 | 2019-01-03 |  | Y
Central Hudson |  | New York State Solar Farm | CH-11083 | Newburgh | Newburgh | Orange | 12550 | G | 5004 | Marlboro | N |  | 11.52 | [13 empty] | NM | N | 36 SunPower SPR-E20-327-D-AC (240V) | 2018-11-19 | 2018-11-20 | 1 | 2018-11-20 | [14 empty] | 2018-12-28 | 2019-01-09 |  | Y
Central Hudson |  | SunCommon | CH-11082 | Kingston | Kingston | Ulster | 12401 | G | 1022 | East Kingston | N |  | 3.8 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3800H-US (240V) [SI1] | 2018-11-19 | 2018-11-20 | 1 | 2018-11-20 | [14 empty] | 2019-01-07 | 2019-01-08 |  | Y
Central Hudson |  | Solar Generation | CH-11085 | Kingston | Kingston | Ulster | 12401 | G | 2017 | Lincoln Park | N | CH-10957 | 14.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE14.4KUS (208V) | 2019-01-03 | 2019-01-11 | 6 | 2019-01-11 | [14 empty] | 2019-03-29 | 2019-03-29 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-11086 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6046 | Spackenkill | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2018-11-20 | 2018-11-20 | 0 | 2018-11-20 | [14 empty] | 2019-02-13 | 2019-02-15 |  | Y
Central Hudson |  | Vivint Solar Developer, LLC | CH-11090 | Fishkill | Wappingrs Fls |  | 12590 | G | 8092 | Fishkill Plains | TBD |  | 13.11 | [13 empty] | NM | N | 57 Enphase Energy IQ6-60-X-US (240V) | 2018-12-07 | 2018-12-10 | 1 | 2018-12-10 | [17 empty] | W
Central Hudson |  | Vivint Solar Developer, LLC | CH-11091 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8092 | Fishkill Plains | N |  | 5.52 | [13 empty] | NM | N | 24 Enphase Energy IQ6-60-X-US (240V) | 2018-12-07 | 2018-12-10 | 1 | 2018-12-10 | [14 empty] | 2019-02-01 | 2019-02-05 |  | Y
Central Hudson |  | Coldbrook Power, LLC | CH-11089 | Newburgh | Walden |  | 12586 | G | 5042 | East Walden | TBD |  | 4400 | [13 empty] | CDG | N | 2 SMA America SC-2200-US (385V) | 2018-12-03 | 2018-12-13 | 8 | 2018-12-13 | 2018-12-13 | 2019-01-08 | 15 | [14 empty] | W
Central Hudson |  | New York State Solar Farm | CH-11087 | Fishkill | Garrison | Putnam | 10524 | G | 8066 | Merritt Park | N |  | 9.6 | [13 empty] | NM | N | 30 SunPower SPR-X21-350-BLK-D-AC (240V) | 2018-11-21 | 2018-11-21 | 0 | 2018-11-21 | [14 empty] | 2019-01-21 | 2019-01-28 |  | Y
Central Hudson |  | New York State Solar Farm | CH-11088 | Kingston | Ellenvl | Ulster | 12428 | G | 3076 | Greenfield Rd | N |  | 11.2 | [13 empty] | NM | N | 35 SunPower SPR-X22-360-D-AC (240V) | 2018-11-21 | 2018-11-21 | 0 | 2018-11-21 | [14 empty] | 2019-02-19 | 2019-02-25 |  | Y
Central Hudson |  | KilaWatt Consulting | CH-11092 | Poughkeepsie | Millerton |  | 12546 | G | 7081 | Millerton | Y |  | 15 | 15 | [12 empty] | NM | N | 3Outback Power SystemsSkybox1KilaWatt Consulting20kWh Li-Ion | 2019-01-02 | 2019-01-11 | 7 | 2019-01-11 | [8 empty] | 350 | 350 |  | 2019-01-15 | 2019-01-15 | 2019-02-08 | 2019-12-02 | 2019-12-03 |  | W
Central Hudson |  | Apex Roofing, LLC | CH-11094 | Poughkeepsie | Pleasant Valley | Dutchess | 12569 | G | 6057 | Todd Hill | N |  | 20 | [13 empty] | NM | N | 2 SolarEdge Technologies SE10000H-US (240V) | 2018-12-03 | 2018-12-06 | 3 | 2018-12-06 | [14 empty] | 2018-12-26 | 2018-12-27 |  | Y
Central Hudson |  | Trinity Solar | CH-11093 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8071 | Shenandoah | N |  | 3.8 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3800H-US (240V) | 2018-11-26 | 2018-11-28 | 2 | 2018-11-28 | [14 empty] | 2019-01-23 | 2019-01-28 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-11099 | Kingston | Hurley | Ulster | 12443 | G | 2094 | Hurley Ave | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000 (240V) | 2018-11-27 | 2018-11-30 | 3 | 2018-11-30 | [14 empty] | 2018-12-11 | 2018-12-12 |  | Y
Central Hudson |  | New York State Solar Farm | CH-11096 | Kingston | Port Ewen | Ulster | 12466 | G | 1024 | East Kingston | N |  | 3.2 | [13 empty] | NM | N | 10 SunPower SPR-X22-360-D-AC (240V) | 2018-11-27 | 2018-11-28 | 1 | 2018-11-28 | [14 empty] | 2019-02-27 | 2019-03-04 |  | Y
Central Hudson |  | SunCommon | CH-11095 | Catskill | Durham | Greene | 12422 | G | 1092 | Westerlo | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2018-11-27 | 2018-11-30 | 3 | 2018-11-30 | [14 empty] | 2019-01-04 | 2019-01-08 |  | Y
Central Hudson |  | PlugPV, LLC | CH-11098 | Newburgh | Rock Tvrn | Orange | 12575 | G | 4097 | Bethlehem Rd | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2018-12-06 | 2018-12-07 | 1 | 2018-12-07 | [14 empty] | 2019-01-10 | 2019-01-16 |  | Y
Central Hudson |  | Mannino Electric, Inc. / Incline Solar | CH-11097 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6043 | Spackenkill | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2018-11-27 | 2018-11-30 | 3 | 2018-11-30 | [14 empty] | 2018-12-17 | 2018-12-21 |  | Y
Central Hudson |  | Lighthouse Solar | CH-11100 | Fishkill | Garrison | Putnam | 10524 | G | 8066 | Merritt Park | N |  | 7.54 | [13 empty] | NM | N | 26 Enphase Energy IQ7PLUS-72-x-US (240V) | 2018-11-28 | 2018-11-30 | 2 | 2018-11-30 | [8 empty] | 350 | 350 |  | 2018-12-10 | 2018-12-10 | 2018-12-27 | 2019-01-09 | 2019-01-11 |  | Y
Central Hudson |  | Cypress Creek Renewables | CH-11101 | Kingston | Kingston |  | 12401 | G | 2094 | Hurley Ave | TBD |  |  | 1980 | [12 empty] | CDG | N | 1Power ElectronicsFS2001K | 2019-01-09 | 2019-01-09 | 0 | 2019-01-09 | [17 empty] | W |  | ESS application intended to be combined with PV application CH-03141. Project following ESS + PV Interim Guidelines Tier 2.
Central Hudson |  | DG New York CS LLC | CH-11108 | Catskill | Hannacroix |  | 12087 | G | 1083 | New Baltimore | Y |  | 5000 | 5000 | [12 empty] | CDG | Y | 2Power ElectronicsFREEMAQ PCSK FP2650K2Power ElectronicsFREEMAQ PCSK FP2650K | 2019-06-18 | 2019-07-02 | 10 | 2019-07-02 | 2019-07-02 | 2019-07-24 | 15 | 2019-08-12 | 2019-10-23 | 2020-01-22 | 60 | 12503.06 | 13207242.5 | [7 empty] | 2020-06-22 | W
Central Hudson |  | Empire Solar Solutions | CH-11106 | Newburgh | New Paltz | Ulster | 12561 | G | 5031 | Galeville | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600A-US (240V) | 2018-11-29 | 2018-12-05 | 4 | 2018-12-05 | [14 empty] | 2018-12-12 | 2018-12-14 |  | Y
Central Hudson |  | CES Danbury Solar LLC | CH-11109 | Poughkeepsie | Ancramdale |  | 12503 | G | 7085 | Ancram | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2019-01-22 | 2019-01-28 | 4 | 2019-01-28 | [17 empty] | W
Central Hudson |  | Paradise Energy Solutions LLC | CH-11105 | Kingston | W Hurley | Ulster | 12491 | G | 2094 | Hurley Ave | Y | CH-09716 | 3 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000H-US (240V) | 2018-12-18 | 2018-12-27 | 5 | 2018-12-27 | [14 empty] | 2019-02-04 | 2019-02-11 |  | Y
Central Hudson |  | New York State Solar Farm | CH-11102 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6011 | Sand Dock | N |  | 12.8 | [13 empty] | NM | N | 40 SunPower SPR-X22-360-D-AC (240V) | 2018-11-29 | 2018-11-30 | 1 | 2018-11-30 | [8 empty] | 350 | 350 |  | 2019-01-02 | 2019-01-02 | 2019-01-11 | 2019-02-20 | 2019-02-22 |  | Y
Central Hudson |  | New York State Solar Farm | CH-11104 | Newburgh | Newburgh | Orange | 12550 | G | 410 | Montgomery St | N |  | 8 | [13 empty] | NM | N | 25 SunPower SPR-X22-360-D-AC (240V) | 2018-11-29 | 2018-12-03 | 2 | 2018-12-03 | [14 empty] | 2019-06-28 | 2019-07-03 |  | Y
Central Hudson |  | New York State Solar Farm | CH-11103 | Newburgh | Cornwall | Orange | 12518 | G | 4041 | Union Ave | N |  | 13.44 | [13 empty] | NM | N | 42 SunPower SPR-X22-360-D-AC (240V) | 2018-11-29 | 2018-11-30 | 1 | 2018-11-30 | [14 empty] | 2019-02-01 | 2019-02-05 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-11107 | Newburgh | Cornwall-Hdsn | Orange | 12520 | G | 4043 | Union Ave | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE 10000A-US (240V) | 2018-11-29 | 2018-12-06 | 5 | 2018-12-06 | [14 empty] | 2019-01-29 | 2019-01-31 |  | Y
Central Hudson |  | Landau Solar, LLC | CH-11110 | Kingston | Ulster |  | 12401 | G | 1011 | Boulevard | N |  |  | 1980 | [12 empty] | CDG | N | 1Power ElectronicsFS2001K | 2019-01-24 | 2019-02-01 | 6 | 2019-02-01 | [17 empty] | W |  | ESS application intended to be combined with PV application CH-03207. System must be limited to 1980kW AC. Project following ESS + PV Interim Guidelines Tier 2.
Central Hudson |  | Cypress Creek Renewables, LLC | CH-11111 | Kingston | Kingston | Ulster | 12401 | G | 1011 | Boulevard | Y | CH-03325 | 4000 | 4000 | [12 empty] | CDG | Y | SMA America 2Power ElectronicsFS2001K2Power ElectronicsFS2001K | 2019-01-11 | 2019-01-25 | 10 | 2019-01-25 | [7 empty] | 30108.51 | 482555 | 132091.12 | 2017-10-18 | 2018-04-13 | 2018-04-13 | 2021-11-18 | 2021-12-30 | 2021-12-30 | 2022-04-07 | Y | Y | ESS application intended to be combined with PV application CH-03325. System must be limited to 3960kW AC. Project following ESS + PV Interim Guidelines Tier 2.
Central Hudson |  | SunCommon | CH-11112 | Newburgh | Clintondale | Ulster | 12515 | G | 5024 | Ohioville | N |  | 6.4 | [13 empty] | NM | N | 20 SunPower SPR-X22-360-D-AC (240V) [SI1] | 2018-11-30 | 2018-12-06 | 4 | 2018-12-06 | [14 empty] | 2019-03-18 | 2019-03-26 |  | Y
Central Hudson |  | MAP Energy Solutions LLC | CH-10993 | Poughkeepsie | Staatsburg |  | 12580 | G | 7041 | Staatsburg | TBD |  | 5000 | [13 empty] | CDG | N | 100 Huawei Technologies SUN2000-45KTL-US-HV-D0 | 2019-02-28 | 2019-03-14 | 10 | 2019-03-14 | 2019-03-14 | 2019-04-03 | 14 |  |  |  |  | 17500 | [9 empty] | W
Central Hudson |  | PlugPV, LLC | CH-11113 | Catskill | Athens | Greene | 12015 | G | 1074 | Coxsackie | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600A-US (240V) | 2018-12-03 | 2018-12-06 | 3 | 2018-12-06 | [14 empty] | 2019-01-07 | 2019-01-08 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-11114 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8092 | Fishkill Plains | N | CH-11114 | 4.48 | [13 empty] | NM | N | 14 SunPower SPR-X22-360-D-AC (240V) | 2018-12-03 | 2018-12-06 | 3 | 2018-12-06 | [14 empty] | 2019-02-25 | 2019-02-27 |  | Y
Central Hudson |  | Vivint Solar Developer, LLC | CH-11115 | Newburgh | Modena | Ulster | 12548 | G | 5011 | Modena | N |  | 6.72 | [13 empty] | NM | N | 28 Enphase Energy IQ6-60-X-US (240V) | 2018-12-07 | 2018-12-10 | 1 | 2018-12-10 | [14 empty] | 2019-12-17 | 2019-12-18 |  | Y
Central Hudson |  | Cypress Creek Renewables | CH-11117 | Catskill | Cairo |  | 12413 | G | 2041 | South Cairo | N |  |  | 1980 | [12 empty] | CDG | Y | 1Power ElectronicsFS2001K | 2019-01-14 | 2019-01-25 | 9 | 2019-01-25 | [17 empty] | W |  | ESS application intended to be combined with PV application CH-03153. Project following ESS + PV Interim Guidelines Tier 2.
Central Hudson |  | Infinity Solar Systems | CH-11116 | Kingston | Kingston | Ulster | 12401 | G | 2013 | Lincoln Park | N |  | 3.2 | [13 empty] | NM | N | 10 Enphase Energy IQ7X-96-x-US (240V) | 2018-12-04 | 2018-12-06 | 2 | 2018-12-06 | [14 empty] | 2019-02-27 | 2019-03-04 |  | Y
Central Hudson |  | PlugPV, LLC. | CH-11119 | Kingston | Kingston | Ulster | 12401 | G | 2012 | Lincoln Park | N |  | 13.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) 1 SolarEdge Technologies SE6000H-US (240V) | 2018-12-05 | 2018-12-06 | 1 | 2018-12-06 | [14 empty] | 2018-12-27 | 2018-12-27 |  | Y
Central Hudson |  | PlugPV, LLC | CH-11120 | Kingston | Ruby | Ulster | 12475 | G | 2016 | Lincoln Park | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2018-12-27 | 2018-12-27 | 0 | 2018-12-27 | [14 empty] | 2019-01-10 | 2019-01-16 |  | Y
Central Hudson |  | Tesla Energy Operations, Inc. | CH-11118 | Kingston | Saugerties | Ulster | 12477 | G | 3003 | Saugerties | Y | CH-11118 | 7.6 | 5 | [12 empty] | NM | N | 1 Delta Electronics SOLIVIA 7.6 NA G4 TL (240V) 1TeslaAC Powerwall 2.0 | 2018-12-05 | 2018-12-13 | 6 | 2018-12-13 | [14 empty] | 2019-01-23 | 2019-01-28 |  | Y
Central Hudson |  | Vivint Solar Developer, LLC | CH-11121 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8091 | Fishkill Plains | N |  | 10.35 | [13 empty] | NM | N | 45 Enphase Energy IQ6-60-x-US (240V) [SI1] | 2018-12-05 | 2018-12-07 | 2 | 2018-12-07 | [14 empty] | 2019-03-27 | 2019-03-27 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-11123 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6042 | Spackenkill | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000x (240V) [SI1] | 2018-12-06 | 2018-12-07 | 1 | 2018-12-07 | [14 empty] | 2018-12-13 | 2018-12-14 |  | Y
Central Hudson |  | Apex Solar Power | CH-11122 | Kingston | Ulster Pk | Ulster | 12487 | G | 1023 | East Kingston | N |  | 13.8 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3800H-US (240V) 1 SolarEdge Technologies SE10000H-US (240V) | 2018-12-06 | 2018-12-07 | 1 | 2018-12-07 | [8 empty] | 350 | 350 |  | 2018-12-10 | 2018-12-10 | 2018-12-20 | 2019-03-19 | 2019-03-20 |  | Y
Central Hudson |  | Solar Alchemy, Inc. | CH-11124 | Kingston | Kerhonkson | Ulster | 12446 | G | 3081 | Kerhonkson | N | CH-09005 | 12.5 | [13 empty] | NM | Y | 1 Fronius USA Fronius Symo 12.5-3 480 (480V) | 2019-04-01 | 2019-04-10 | 7 | 2019-04-10 | [14 empty] | 2019-06-28 | 2019-07-02 |  | Y | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-11126 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6091 | Manchester | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2018-12-07 | 2018-12-10 | 1 | 2018-12-10 | [14 empty] | 2019-01-28 | 2019-01-31 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-11125 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6046 | Spackenkill | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2018-12-07 | 2018-12-10 | 1 | 2018-12-10 | [14 empty] | 2019-02-19 | 2019-02-22 |  | Y
Central Hudson |  | East Light Partners | CH-11131 | Kingston | Saugerties |  | 12477 | G | 2016 | Lincoln Park | N |  | 3000 | [13 empty] | CDG | N | 24 Sungrow Power Supply SG125HV (600V) | 2019-05-08 | 2019-05-21 | 9 | 2019-05-21 | 2019-05-21 | 2019-06-12 | 15 | 2019-06-24 | 2019-08-12 | 2019-11-05 | 60 | 10179.28 | 5964591.25 | [7 empty] | 2020-02-11 | W
Central Hudson |  | Lighthouse Solar | CH-11132 | Kingston | Kerhonkson | Ulster | 12446 | G | 3081 | Kerhonkson | N | CH-11132 | 8.99 | [13 empty] | NM | N | 31 Enphase Energy IQ7PLUS-72-x-US (240V) | 2018-12-10 | 2018-12-10 | 0 | 2018-12-10 | [14 empty] | 2018-12-14 | 2018-12-14 |  | Y
Central Hudson |  | Kasselman Solar | CH-11130 | Kingston | Ellenvl |  | 12428 | G | 396 | Clinton Ave | N |  | 4.8 | [13 empty] | NM | N | 20 Enphase Energy IQ7-60-x-US (240V) | 2018-12-10 | 2018-12-10 | 0 | 2018-12-10 | [17 empty] | W
Central Hudson |  | Lotus Energy | CH-11127 | Kingston | Tillson | Ulster | 12486 | G | 3021 | High Falls | N |  | 3.52 | [13 empty] | NM | N | 11 SunPower SPR-X22-360-D-AC (240V) | 2018-12-17 | 2018-12-21 | 4 | 2018-12-21 | [14 empty] | 2019-01-15 | 2019-01-21 |  | Y
Central Hudson |  | Lotus Energy | CH-11128 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7052 | Rhinebeck | N |  | 7.68 | [13 empty] | NM | N | 24 SunPower SPR-X22-360-D-AC (240V) | 2018-12-13 | 2018-12-17 | 2 | 2018-12-17 | [14 empty] | 2019-01-02 | 2019-01-04 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-11134 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6046 | Spackenkill | N |  | 13.6 | [13 empty] | NM | N | 1 SMA America SB7.7-1SP-US-40 (240V) 1 SMA America SB6.0-1SP-US-40 (240V) | 2018-12-10 | 2018-12-12 | 2 | 2018-12-12 | [14 empty] | 2019-01-08 | 2019-01-11 |  | Y
Central Hudson |  | Lotus Solar | CH-11129 | Catskill | Jewett | Greene | 12444 | E | 2389 | Vinegar Hill | N |  | 9.6 | [13 empty] | NM | N | 30 SunPower SPR-X22-360-D-AC (240V) | 2018-12-19 | 2018-12-27 | 4 | 2018-12-27 | [14 empty] | 2019-01-02 | 2019-01-04 |  | Y
Central Hudson |  | YSG Solar | CH-11133 | Newburgh | Milton | Ulster | 12547 | G | 5002 | Marlboro | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2019-01-02 | 2019-01-07 | 3 | 2019-01-07 | [14 empty] | 2019-02-27 | 2019-03-04 |  | Y
Central Hudson |  | New York State Solar Farm | CH-11136 | Fishkill | Beacon | Dutchess | 12508 | G | 8087 | Tioronda | N |  | 7.68 | [13 empty] | NM | N | 24 SunPower SPR-E20-327-D-AC (240V) | 2018-12-11 | 2018-12-12 | 1 | 2018-12-12 | [14 empty] | 2018-12-31 | 2019-01-08 |  | Y
Central Hudson |  | SunCommon | CH-11135 | Kingston | Saugerties | Ulster | 12477 | G | 1021 | East Kingston | N | CH-11135 | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2018-12-11 | 2018-12-12 | 1 | 2018-12-12 | [14 empty] | 2019-02-06 | 2019-02-07 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-11137 | Poughkeepsie | Millbrook | Dutchess | 12545 | G | 7072 | Stanfordville | N | CH-11137 | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000x (240V) [SI1] | 2018-12-27 | 2019-01-09 | 8 | 2019-01-09 | [14 empty] | 2019-01-09 | 2019-01-11 |  | Y
Central Hudson |  | Lighthouse Solar | CH-11142 | Kingston | Olivebridge | Ulster | 12461 | G | 3082 | Kerhonkson | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2018-12-12 | 2018-12-17 | 3 | 2018-12-17 | [14 empty] | 2019-05-14 | 2019-05-20 |  | Y
Central Hudson |  | Kasselman Solar | CH-11138 | Poughkeepsie | Millbrook | Dutchess | 12545 | G | 7025 | Tinkertown | N |  | 8.4 | [13 empty] | NM | N | 29 Enphase Energy IQ7PLUS-72-x-US (240V) | 2018-12-12 | 2018-12-12 | 0 | 2018-12-12 | [14 empty] | 2019-01-03 | 2019-01-07 |  | Y
Central Hudson |  | Borrego Solar Systems, Inc | CH-11141 | Newburgh | Campbell Hall |  | 10916 | G | 5051 | Maybrook | TBD |  | 5000 | 5000 | [12 empty] | CDG | N | 1Power ElectronicsHEMK FS3000K1Power ElectronicsHEMK FS2000K2Power ElectronicsHEMK FS3000K/HEMK FS2000K | 2019-02-05 | 2019-02-20 | 10 | 2019-02-20 | 2019-02-20 | 2019-03-13 | 15 | [14 empty] | W
Central Hudson |  | Sunrun Installation Services, Inc. | CH-11143 | Newburgh | Clintondale | Ulster | 12515 | G | 5024 | Ohioville | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000H-US (240V) | 2018-12-12 | 2018-12-17 | 3 | 2018-12-17 | [14 empty] | 2019-06-03 | 2019-06-05 |  | Y
Central Hudson |  | Empire Solar | CH-11139 | Poughkeepsie | Millbrook | Dutchess | 12545 | G | 7072 | Stanfordville | N | CH-11137 | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000 (240V) | 2018-12-27 | 2019-01-09 | 8 | 2019-01-09 | [14 empty] | 2019-01-09 | 2019-01-11 |  | Y
Central Hudson |  | Kasselman Solar | CH-11144 | Kingston | Saugerties | Ulster | 12477 | G | 3001 | Saugerties | N |  | 10.15 | [13 empty] | NM | N | 35 Enphase Energy IQ7PLUS-72-x-US (240V) | 2018-12-13 | 2018-12-17 | 2 | 2018-12-17 | [14 empty] | 2018-12-17 | 2018-12-21 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-11145 | Newburgh | Esopus | Ulster | 12429 | G | 5084 | Highland | N | CH-23678 | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE 10000A-US (240V) | 2018-12-13 | 2018-12-17 | 2 | 2018-12-17 | [8 empty] | 350 | 350 |  | 2018-12-26 | 2018-12-26 | 2019-02-21 | 2019-03-04 | 2019-03-08 |  | Y
Central Hudson |  | New York State Solar Farm | CH-11147 | Newburgh | New Paltz | Ulster | 12561 | G | 5031 | Galeville | N |  | 9.28 | [13 empty] | NM | N | 29 SunPower SPR-X22-360-D-AC (240V) | 2018-12-14 | 2018-12-17 | 1 | 2018-12-17 | [14 empty] | 2019-01-22 | 2019-01-28 |  | Y
Central Hudson |  | PlugPV | CH-11148 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 6075 | East Park | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2018-12-18 | 2018-12-21 | 3 | 2018-12-21 | [14 empty] | 2019-02-01 | 2019-02-06 |  | Y
Central Hudson |  | Solar Generation | CH-11149 | Kingston | Kingston | Ulster | 12401 | G | 2094 | Hurley Ave | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600A-US (240V) | 2018-12-17 | 2018-12-19 | 2 | 2018-12-19 | [8 empty] | 350 | 350 |  | 2018-12-21 | 2018-12-21 | 2019-02-21 | 2019-02-28 | 2019-03-05 |  | Y
Central Hudson |  | solar image, llc | CH-11150 | Newburgh | Campbell Hall | Orange | 10916 | G | 5051 | Maybrook | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2018-12-21 | 2018-12-27 | 2 | 2018-12-27 | [14 empty] | 2019-01-11 | 2019-01-11 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-11153 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6044 | Spackenkill | N |  | 9.6 | [13 empty] | NM | N | 30 SunPower SPR-X22-360-D-AC (240V) | 2018-12-21 | 2018-12-27 | 2 | 2018-12-27 | [8 empty] | 350 | 350 |  | 2018-12-28 | 2018-12-28 | 2019-01-11 | 2019-04-11 | 2019-04-12 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-11162 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6011 | Sand Dock | N |  | 14.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE11400H-US (240V) 1 SolarEdge Technologies SE3000H-US (240V) | 2018-12-18 | 2018-12-21 | 3 | 2018-12-21 | [14 empty] | 2019-02-01 | 2019-02-04 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-11161 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6003 | Reynolds Hill | N |  | 7 | [13 empty] | NM | N | 1 SMA America SB7.0-1SP-US-40 (240V) | 2018-12-18 | 2018-12-21 | 3 | 2018-12-21 | [14 empty] | 2019-02-01 | 2019-02-04 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-11160 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6046 | Spackenkill | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2018-12-18 | 2018-12-21 | 3 | 2018-12-21 | [14 empty] | 2019-02-14 | 2019-02-15 |  | Y
Central Hudson |  | Trinity Solar | CH-11156 | Newburgh | Wallkill | Ulster | 12589 | G | 5013 | Modena | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE 10000A-US (240V) | 2018-12-18 | 2018-12-21 | 3 | 2018-12-21 | [14 empty] | 2019-02-06 | 2019-02-08 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-11157 | Poughkeepsie | Poughkeepsie |  | 12603 | G | 6046 | Spackenkill | N |  | 7.7 | [13 empty] | NM | N | 1 SMA America SB7.7-1SP-US-40 (240V) | 2018-12-18 | 2018-12-21 | 3 | 2018-12-21 | [17 empty] | W
Central Hudson |  | Hudson Valley Wind & Solar, LLC | CH-11155 | Poughkeepsie | Pine Plns | Dutchess | 12567 | G | 7091 | Pulvers Corners | N |  | 23.5 | [13 empty] | NM | N | 81 Enphase Energy IQ7PLUS-72-x-US (240V) | 2018-12-18 | 2018-12-21 | 3 | 2018-12-21 | [8 empty] | 350 | 350 |  | 2019-01-31 | 2019-01-31 | 2019-02-14 | 2019-11-18 | 2019-11-20 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-11154 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6046 | Spackenkill | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE 10000A-US (240V) | 2018-12-18 | 2018-12-21 | 3 | 2018-12-21 | [14 empty] | 2019-01-21 | 2019-01-25 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-11158 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6091 | Manchester | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2018-12-18 | 2018-12-21 | 3 | 2018-12-21 | [14 empty] | 2019-02-22 | 2019-02-25 |  | Y
Central Hudson |  | Hudson Valley Wind & Solar, LLC | CH-11159 | Poughkeepsie | Pine Plns | Dutchess | 12567 | G | 7091 | Pulvers Corners | N |  | 23.5 | [13 empty] | NM | N | 81 Enphase Energy IQ7PLUS-72-x-ACM-US (240V) | 2018-12-27 | 2018-12-27 | 0 | 2018-12-27 | [14 empty] | 2019-09-19 | 2019-09-19 |  | Y
Central Hudson |  | Kasselman Solar | CH-11165 | Newburgh | New Paltz | Ulster | 12561 | G | 5023 | Ohioville | N |  | 7.44 | [13 empty] | NM | N | 31 Enphase Energy IQ7-60-x-US (240V) | 2018-12-19 | 2018-12-26 | 3 | 2018-12-26 | [14 empty] | 2019-01-03 | 2019-01-07 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-11167 | Fishkill | Beacon | Dutchess | 12508 | G | 8017 | Forgebrook | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600A-US (240V) | 2018-12-19 | 2018-12-27 | 4 | 2018-12-27 | [14 empty] | 2018-12-27 | 2019-01-03 |  | Y
Central Hudson |  | Trinity Solar | CH-11166 | Newburgh | Goshen | Orange | 10924 | G | 5051 | Maybrook | N |  | 3.8 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3800H-US (240V) | 2018-12-19 | 2018-12-27 | 4 | 2018-12-27 | [14 empty] | 2019-06-11 | 2019-06-14 |  | Y
Central Hudson |  | Apex Roofing, LLC | CH-11164 | Poughkeepsie | Staatsburg | Dutchess | 12580 | G | 7041 | Staatsburg | N | CH-03898 | 15.2 | [13 empty] | NM | N | 2 SolarEdge Technologies SE7600H-US (240V) | 2019-01-14 | 2019-01-23 | 7 | 2019-01-23 | [8 empty] | 350 | 350 |  | 2019-01-25 | 2019-01-25 | 2019-01-29 | 2019-02-07 | 2019-02-08 |  | Y
Central Hudson |  | Kasselman Solar | CH-11163 | Poughkeepsie | Lagrangevl |  | 12540 | G | 6055 | Todd Hill | TBD |  | 8.64 | [13 empty] | NM | N | 36 Enphase Energy IQ7-60-x-US (240V) | 2019-01-03 | 2019-01-07 | 2 | 2019-01-07 | [14 empty] | 2019-01-14 | 2019-01-21 |  | W
Central Hudson |  | YSG Solar | CH-11169 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 3.8 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3800 (240V) | 2019-01-02 | 2019-01-04 | 2 | 2019-01-04 | [14 empty] | 2019-01-29 | 2019-01-31 |  | W
Central Hudson |  | MOMENTUM SOLAR | CH-11170 | Poughkeepsie | Lagrangeville | Dutchess | 12540 | G | 6057 | Todd Hill | N |  | 7.2 | [13 empty] | NM | N | 30 Enphase Energy IQ7-60-x-US (240V) | 2018-12-27 | 2018-12-27 | 0 | 2018-12-27 | [14 empty] | 2019-02-14 | 2019-02-15 |  | Y
Central Hudson |  | MOMENTUM SOLAR | CH-11168 | Newburgh | Newburgh | Orange | 12550 | G | 4024 | Coldenham | N |  | 6.7 | [13 empty] | NM | N | 28 Enphase Energy IQ7-60-x-US (240V) | 2018-12-27 | 2018-12-27 | 0 | 2018-12-27 | [14 empty] | 2019-02-14 | 2019-02-15 |  | Y
Central Hudson |  | Kasselman Solar | CH-11171 | Fishkill | Beacon | Dutchess | 12508 | G | 8017 | Forgebrook | N | CH-11171 | 4.8 | [13 empty] | NM | N | 20 Enphase Energy IQ7-60-x-US (240V) | 2018-12-21 | 2018-12-27 | 2 | 2018-12-27 | [14 empty] | 2019-01-03 | 2019-01-04 |  | Y
Central Hudson |  | PlugPV, LLC | CH-11172 | Kingston | Lk Katrine | Ulster | 12449 | G | 2016 | Lincoln Park | N |  | 17.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) 1 SolarEdge Technologies SE7600H-US (240V) | 2019-01-04 | 2019-01-09 | 3 | 2019-01-09 | [14 empty] | 2019-03-25 | 2019-03-26 |  | Y
Central Hudson |  | Tesla Energy Operations, Inc | CH-11173 | Kingston | Olive Brdg | Ulster | 12461 | G | 3024 | High Falls | Y |  | 3.8 | 5 | [12 empty] | NM | N | 1 SolarEdge Technologies SE6000 (240V) 1TeslaAC Powerwall 2.0 | 2019-02-22 | 2019-02-28 | 4 | 2019-02-28 | [14 empty] | 2019-03-25 | 2019-03-26 |  | Y
Central Hudson |  | SolarCity DBA Tesla Energy | CH-11175 | Poughkeepsie | Hyde Park | Dutchess | 12538 | G | 7042 | Staatsburg | Y | CH-10789 |  | 10 | [12 empty] | NM | N | 2TeslaAC Powerwall 2.0 | 2019-03-27 | 2019-04-04 | 6 | 2019-04-04 | [14 empty] | 2019-04-15 | 2019-04-16 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-11174 | Poughkeepsie | Lagrangeville | Dutchess | 12540 | G | 6055 | Todd Hill | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE 10000A-US (240V) | 2019-01-02 | 2019-01-04 | 2 | 2019-01-04 | [14 empty] | 2019-01-08 | 2019-01-09 |  | Y
Central Hudson |  | Kasselman Solar | CH-11177 | Catskill | Jewett | Greene | 12444 | E | 2389 | Vinegar Hill | N |  | 9.28 | [13 empty] | NM | N | 32 Enphase Energy IQ7PLUS-72-x-US (240V) | 2019-01-03 | 2019-01-07 | 2 | 2019-01-07 | [14 empty] | 2019-01-07 | 2019-01-09 |  | Y
Central Hudson |  | Kasselman Solar | CH-11176 | Fishkill | Wappingrs Fls |  | 12590 | G | 8052 | North Chelsea | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000H-US (240V) | 2019-01-07 | 2019-01-09 | 2 | 2019-01-09 | [17 empty] | W
Central Hudson |  | Kasselman Solar | CH-11178 | Catskill | Earlton | Greene | 12058 | G | 2071 | Freehold | N |  | 9.28 | [13 empty] | NM | N | 32 Enphase Energy IQ7PLUS-72-x-US (240V) | 2019-01-04 | 2019-01-09 | 3 | 2019-01-09 | [14 empty] | 2019-01-11 | 2019-01-16 |  | Y
Central Hudson |  | PLugPV, LLC | CH-11179 | Kingston | Kingston | Ulster | 12401 | G | 1021 | East Kingston | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2019-01-04 | 2019-01-09 | 3 | 2019-01-09 | [14 empty] | 2019-03-05 | 2019-03-08 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-11180 | Fishkill | Beacon | Dutchess | 12508 | G | 8087 | Tioronda | N |  | 3.2 | [13 empty] | NM | N | 10 SunPower SPR-X22-360-D-AC (240V) | 2019-01-07 | 2019-01-09 | 2 | 2019-01-09 | [14 empty] | 2019-03-13 | 2019-03-14 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-11182 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6065 | Inwood Ave | N |  | 15.2 | [13 empty] | NM | N | 2 SolarEdge Technologies SE7600A-US (240V) | 2019-01-07 | 2019-01-09 | 2 | 2019-01-09 | [8 empty] | 350 | 350 |  | 2019-01-10 | 2019-01-10 | 2019-01-29 | 2019-02-15 | 2019-02-19 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-11181 | Kingston | Ellenvl | Ulster | 12428 | G | 3095 | Grimley Rd | N |  | 5.44 | [13 empty] | NM | N | 17 SunPower SPR-X22-360-D-AC (240V) | 2019-01-07 | 2019-01-09 | 2 | 2019-01-09 | [14 empty] | 2019-02-28 | 2019-03-29 |  | Y |  | 3/4/19 - No access to meter; will reschedule meter set. 3/29/19 - Net meter installed.
Central Hudson |  | Trinity Solar | CH-11183 | Fishkill | Wappingers Falls | Dutchess | 12590 | G | 8092 | Fishkill Plains | N |  | 15.2 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) 1 SolarEdge Technologies SE7600H-US (240V) | 2019-01-10 | 2019-01-11 | 1 | 2019-01-11 | [14 empty] | 2019-03-21 | 2019-03-28 |  | Y
Central Hudson |  | Intelligent Green Solutions LLC | CH-11184 | Newburgh | New Paltz | Ulster | 12561 | G | 5031 | Galeville | N |  | 20 | [13 empty] | NM | N | 2 SolarEdge Technologies SE10000H-US (240V) | 2019-01-08 | 2019-01-09 | 1 | 2019-01-09 | [8 empty] | 350 | 350 |  | 2019-01-10 | 2019-01-10 | 2019-02-19 | 2019-02-25 | 2019-02-28 |  | Y
Central Hudson |  | PlugPV, LLC | CH-11186 | Kingston | Saugerties | Ulster | 12477 | G | 3002 | Saugerties | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2019-01-09 | 2019-01-11 | 2 | 2019-01-11 | [14 empty] | 2019-01-29 | 2019-01-31 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-11187 | Poughkeepsie | Poughkeepsie |  | 12603 | G | 6046 | Spackenkill | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE 11400A-US (240V) | 2019-01-09 | 2019-01-11 | 2 | 2019-01-11 | [14 empty] | 2019-04-24 | 2019-04-26 |  | W
Central Hudson |  | Infinity Solar Systems | CH-11185 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8024 | Knapps Corners | N |  | 5.12 | [13 empty] | NM | N | 16 SunPower SPR-X22-360-D-AC (240V) | 2019-01-09 | 2019-01-09 | 0 | 2019-01-09 | [14 empty] | 2019-04-01 | 2019-04-03 |  | Y
Central Hudson |  | Apex Solar Power | CH-11188 | Fishkill | Fishkill | Dutchess | 12524 | G | 8062 | Merritt Park | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2019-01-10 | 2019-01-11 | 1 | 2019-01-11 | [14 empty] | 2019-03-12 | 2019-03-19 |  | Y
Central Hudson |  | Vivint Solar Developer, LLC | CH-11189 | Poughkeepsie | Hyde Pk |  | 12538 | G | 6074 | East Park | N |  | 7.13 | [13 empty] | NM | N | 31 Enphase Energy IQ6-60-X-US (240V) | 2019-01-11 | 2019-01-21 | 6 | 2019-01-21 | [17 empty] | W
Central Hudson |  | Tesla Energy Operations, Inc. | CH-11190 | Newburgh | Walden | Orange | 12586 | G | 5042 | East Walden | Y |  | 9 | 10 | [12 empty] | NM | N | 1 Delta Electronics SOLIVIA 3.8 NA G4 TL (240V) 1 Delta Electronics SOLIVIA 5.2 NA G4 TL (240V) 2TeslaAC Powerwall 2.0 | 2019-01-14 | 2019-01-23 | 7 | 2019-01-23 | [14 empty] | 2019-02-06 | 2019-02-11 |  | Y
Central Hudson |  | PlugPV, LLC | CH-11191 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6093 | Manchester | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE 11400A-US (240V) | 2019-01-14 | 2019-01-25 | 9 | 2019-01-25 | [14 empty] | 2019-02-28 | 2019-03-05 |  | Y
Central Hudson |  | tri-state solar services llc | CH-11194 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8071 | Shenandoah | N |  | 13.1 | [13 empty] | NM | N | 37 Enphase Energy IQ6PLUS-72-X-US (240V) | 2019-01-14 | 2019-01-25 | 9 | 2019-01-25 | [14 empty] | 2019-02-11 | 2019-02-12 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-11192 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6093 | Manchester | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600A-US (240V) | 2019-01-14 | 2019-01-25 | 9 | 2019-01-25 | [14 empty] | 2019-02-13 | 2019-02-15 |  | Y
Central Hudson |  | Tri-State Solar Services | CH-11195 | Kingston | Napanoch | Ulster | 12458 | G | 3091 | Neversink | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600A-US (240V) | 2019-01-14 | 2019-01-25 | 9 | 2019-01-25 | [14 empty] | 2019-02-15 | 2019-02-15 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-11199 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6011 | Sand Dock | N |  | 5 | [13 empty] | NM | N | 1 SMA America SB5.0-1SP-US-40 (240V) | 2019-01-15 | 2019-01-28 | 9 | 2019-01-28 | [14 empty] | 2019-02-28 | 2019-03-14 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-11197 | Kingston | Saugerties | Ulster | 12477 | G | 3001 | Saugerties | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE11400H-US (240V) | 2019-01-15 | 2019-01-28 | 9 | 2019-01-28 | [14 empty] | 2019-04-12 | 2019-04-18 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-11198 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6046 | Spackenkill | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2019-01-15 | 2019-01-28 | 9 | 2019-01-28 | [14 empty] | 2019-02-19 | 2019-02-22 |  | Y
Central Hudson |  | SunCommon | CH-11196 | Newburgh | Milton | Ulster | 12547 | G | 5083 | Highland | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2019-01-28 | 2019-02-01 | 4 | 2019-02-01 | [14 empty] | 2019-02-11 | 2019-02-12 |  | Y
Central Hudson |  | Solar Generation | CH-11200 | Kingston | Woodstock | Ulster | 12498 | G | 3013 | Woodstock | N | CH-08171 | 12 | [13 empty] | NM | N | 2 SMA America SB6000US (240V) | 2019-01-30 | 2019-02-07 | 6 | 2019-02-07 | [8 empty] | 350 | 350 |  | 2019-02-12 | 2019-02-12 | 2019-04-03 | 2019-04-05 | 2019-04-05 |  | Y
Central Hudson |  | NY Solar 1001 LLC | CH-11152 | Kingston | Saugerties |  | 12477 | G | 3002 | Saugerties | N |  | 5000 | [13 empty] | CDG | N | 100 Huawei Technologies SUN2000-45KTL-US-HV-D0 | 2019-03-04 | 2019-03-15 | 9 | 2019-03-15 | 2019-03-15 | 2019-04-05 | 15 | 2019-05-29 | 2019-06-26 | 2019-10-16 | 78 | 10615.62 | 2983146.25 | [7 empty] | 2020-03-11 | W |  | 9/4/19 - Due to applicant changes to system design; CESIR deadline mutually extended to 10/18/19.
Central Hudson |  | Sunrun Installation Services, Inc. | CH-11203 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6046 | Spackenkill | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2019-01-16 | 2019-01-28 | 8 | 2019-01-28 | [14 empty] | 2019-02-19 | 2019-02-22 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-11202 | Poughkeepsie | Poughkeepsie |  | 12601 | G | 6011 | Sand Dock | N |  | 10.8 | [13 empty] | NM | N | 1 SMA America SB7.7-1SP-US-40 (240V) 1 SMA America SB3.0-1SP-US-40 (240V) | 2019-01-16 | 2019-01-28 | 8 | 2019-01-28 | [17 empty] | W
Central Hudson |  | SunCommon | CH-11201 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7055 | Rhinebeck | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000 (240V) | 2019-01-16 | 2019-01-28 | 8 | 2019-01-28 | [14 empty] | 2019-09-04 | 2019-09-11 |  | Y
Central Hudson |  | YSG Solar | CH-11205 | Kingston | Kingston | Ulster | 12401 | G | 1012 | Boulevard | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2019-01-17 | 2019-01-28 | 7 | 2019-01-28 | [14 empty] | 2019-04-26 | 2019-04-29 |  | Y
Central Hudson |  | CVE North America, Inc | CH-11204 | Kingston | Kerhonkson |  | 12446 | G | 3071 | Honk Falls | N |  |  | 5000 | [12 empty] | CDG | N | 40SungrowSG125HV | 2019-05-02 | 2019-05-16 | 10 | 2019-05-16 | [16 empty] | 2019-10-04 | W |  | ESS application intended be combined with PV application CH-10545. Project following ESS + PV Interim Guidelines Tier 1.
Central Hudson |  | Integrity Solar Solutions | CH-11206 | Poughkeepsie | Stanfordville | Dutchess | 12581 | G | 7072 | Stanfordville | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) 1 SolarEdge Technologies SE10000H-US (240V) [SI1] | 2019-01-18 | 2019-01-28 | 6 | 2019-01-28 | [8 empty] | 350 | 350 |  | 2019-02-19 | 2019-02-19 | 2019-02-28 | 2019-03-04 | 2019-03-08 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-11209 | Newburgh | Wallkill | Ulster | 12589 | G | 5041 | East Walden | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE 11400A-US (240V) | 2019-01-18 | 2019-01-28 | 6 | 2019-01-28 | [14 empty] | 2019-01-29 | 2019-01-31 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-11208 | Poughkeepsie | Poughkeepsie |  | 12601 | G | 6011 | Sand Dock | TBD |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE11400H-US (240V) | 2019-01-30 | 2019-02-07 | 6 | 2019-02-07 | [8 empty] | 350 | 350 |  | 2019-02-19 | 2019-02-19 | 2019-03-20 |  |  |  | W
Central Hudson |  | Foremost Electric Inc. | CH-11207 | Fishkill | Beacon | Dutchess | 12508 | G | 8085 | Tioronda | N |  | 66.6 | [13 empty] | RC | Y | 1 SolarEdge Technologies SE66.6KUS (480V) | 2019-05-10 | 2019-05-24 | 10 | 2019-05-24 | 2019-05-24 | 2019-06-17 | 15 | [5 empty] | 8832.15 | 7012.56 |  | 2019-08-30 | 2019-08-30 | 2021-12-31 | 2025-04-29 | 2025-04-29 | 2025-06-02 | Y | Y
Central Hudson |  | MOMENTUM SOLAR | CH-11211 | Kingston | Kerhonkson |  | 12446 | G | 3082 | Kerhonkson | N |  | 6.5 | [13 empty] | NM | N | 27 Enphase Energy IQ7-60-x-US (240V) | 2019-02-07 | 2019-02-13 | 4 | 2019-02-13 | [17 empty] | W
Central Hudson |  | Sunrun Installation Services, Inc. | CH-11212 | Kingston | Saugerties | Ulster | 12477 | G | 2015 | Lincoln Park | N |  | 5 | [13 empty] | NM | N | 1 SMA America SB5.0-1SP-US-40 (240V) | 2019-01-22 | 2019-01-28 | 4 | 2019-01-28 | [14 empty] | 2019-03-14 | 2019-03-19 |  | Y
Central Hudson |  | Lighthouse Solar | CH-11210 | Poughkeepsie | Lagrangevl | Dutchess | 12540 | G | 6053 | Todd Hill | N |  | 9.28 | [13 empty] | NM | N | 32 Enphase Energy IQ7PLUS-72-x-US (240V) [SI1] | 2019-01-22 | 2019-01-28 | 4 | 2019-01-28 | [14 empty] | 2019-03-27 | 2019-03-28 |  | Y
Central Hudson |  | Apex Solar Power | CH-11215 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 7023 | Tinkertown | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2019-01-23 | 2019-01-28 | 3 | 2019-01-28 | [8 empty] | 350 | 350 |  | 2019-01-30 | 2019-01-30 | 2019-02-22 | 2019-03-18 | 2019-03-19 |  | Y
Central Hudson |  | Standard Solar | CH-11219 | Kingston | Esopus |  | 12487 | G | 1023 | East Kingston | N |  | 733.3 | [13 empty] | RNM | Y | 7 SolarEdge Technologies SE100KUS (480V) 1 SolarEdge Technologies SE33.3KUS (480V) | 2019-03-12 | 2019-03-26 | 10 | 2019-03-26 | 2019-03-26 | 2019-04-16 | 15 | 2019-06-05 | 2019-06-14 | 2019-09-10 | 60 | 9901.5 | 145957.5 | 8698.68 | 2019-12-05 | [5 empty] | 2020-11-25 | W
Central Hudson |  | PlugPV LLC | CH-11216 | Newburgh | Montgomery | Orange | 12549 | G | 5073 | Montgomery | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2019-01-24 | 2019-01-28 | 2 | 2019-01-28 | [14 empty] | 2019-03-12 | 2019-03-14 |  | Y
Central Hudson |  | Nexamp Solar LLC | CH-11217 | Fishkill | Wappinger Falls |  | 12590 | G | 8056 | North Chelsea | Y |  |  | 2000 | [12 empty] | CDG | Y | 2INGECON SUN STORAGE1170TL U B450 | 2019-11-25 | 2019-12-10 | 9 | 2019-12-10 | [7 empty] | 6500 | [9 empty] | W |  | ESS application intended be combined with PV application CH-04102. Project following ESS + PV Interim Guidelines Tier 3.
Central Hudson |  | SunCommon | CH-11220 | Fishkill | Stormvl | Dutchess | 12582 | G | 8071 | Shenandoah | N |  | 5.44 | [13 empty] | NM | N | 17 SunPower SPR-E20-327-D-AC (240V) | 2019-01-25 | 2019-01-28 | 1 | 2019-01-28 | [14 empty] | 2019-02-15 | 2019-02-25 |  | Y
Central Hudson |  | General Electric International, Inc | CH-11223 | Newburgh | Montgomery | Orange | 12549 | G | 5073 | Montgomery | N |  | 315 | [13 empty] | RC | Y | 7 Huawei Technologies SUN2000-45KTL-US-HV-D0 | 2019-03-28 | 2019-04-05 | 6 | 2019-04-05 | 2019-04-05 | 2019-04-29 | 15 | [14 empty] | W
Central Hudson |  | New York State Solar Farm | CH-11222 | Newburgh | Highland Mls | Orange | 10930 | G | 4041 | Union Ave | N |  | 16.96 | [13 empty] | NM | N | 53 SunPower SPR-E20-327-D-AC (240V) | 2019-01-28 | 2019-02-01 | 4 | 2019-02-01 | [8 empty] | 350 | 350 |  | 2019-02-04 | 2019-02-04 | 2019-02-21 | 2019-02-22 | 2019-02-25 |  | Y
Central Hudson |  | SolarCity DBA Tesla Energy | CH-11225 | Newburgh | Cornwall | Orange | 12518 | G | 4041 | Union Ave | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2019-01-29 | 2019-02-07 | 7 | 2019-02-07 | [14 empty] | 2019-03-08 | 2019-03-08 |  | Y
Central Hudson |  | MOMENTUM SOLAR | CH-11226 | Fishkill | Hopewell Junction | Dutchess | 12533 | G | 8092 | Fishkill Plains | N |  | 6 | [13 empty] | NM | N | 25 Enphase Energy IQ7-60-x-US (240V) | 2019-01-29 | 2019-02-07 | 7 | 2019-02-07 | [14 empty] | 2019-02-15 | 2019-02-21 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-11229 | Newburgh | Campbell Hall | Orange | 10916 | G | 5051 | Maybrook | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE11400H-US (240V) | 2019-01-30 | 2019-02-07 | 6 | 2019-02-07 | [14 empty] | 2019-05-07 | 2019-05-10 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-11228 | Newburgh | Highland | Ulster | 12528 | G | 5084 | Highland | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2019-01-30 | 2019-02-07 | 6 | 2019-02-07 | [14 empty] | 2019-03-18 | 2019-03-19 |  | Y
Central Hudson |  | Red Hook Solar | CH-11227 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7053 | Rhinebeck | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2019-01-30 | 2019-02-07 | 6 | 2019-02-07 | [14 empty] | 2019-04-05 | 2019-04-09 |  | Y
Central Hudson |  | East Light Partners | CH-11232 | Kingston | Saugerties |  | 12477 | G | 3014 | Woodstock | N |  |  | 2200 | [12 empty] | CDG | N | 1Power ElectronicsFP2180C Battery Inverter | 2019-07-29 | 2019-08-06 | 6 | 2019-08-06 |  |  |  | 2019-08-21 | 2019-09-03 |  |  | 1932.8 | [8 empty] | 2020-04-17 | W |  | ESS application intended be combined with PV application CH-10341. Project following ESS + PV Interim Guidelines Tier 3. 11/26/19 - Due to applicant changes to system design; CESIR deadline mutually extended to 1/28/20.
Central Hudson |  | Vitol Solar I LLC | CH-11233 | Fishkill | Hopewell Junction |  | 12533 | G | 8093 | Fishkill Plains | N |  |  | 1200 | [12 empty] | CDG | Y | 1Power ElectronicsFP1245C Battery Inverter | 2019-07-29 | 2019-08-06 | 6 | 2019-08-06 |  |  |  | 2019-08-21 | 2019-09-03 | 2019-11-26 | 60 | 3235.59 | 208437.5 | [7 empty] | 2020-06-01 | W |  | ESS application intended be combined with PV application CH-03332. Project following ESS + PV Interim Guidelines Tier 3.
Central Hudson |  | Lighthouse Solar | CH-11230 | Newburgh | New Paltz | Ulster | 12561 | G | 5021 | Ohioville | N |  | 8.12 | [13 empty] | NM | N | 28 Enphase Energy IQ7PLUS-72-x-US (240V) [SI1] | 2019-01-31 | 2019-02-08 | 6 | 2019-02-08 | [14 empty] | 2019-04-04 | 2019-04-05 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-11235 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8051 | North Chelsea | N |  | 20 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (208V) [SI1] 1 SolarEdge Technologies SE10000H-US (240V) | 2019-02-08 | 2019-02-15 | 5 | 2019-02-15 | [8 empty] | 350 | 350 |  | 2019-02-27 | 2019-02-27 | 2019-03-08 | 2019-03-21 | 2019-03-26 |  | Y
Central Hudson |  | Kasselman Solar | CH-11236 | Poughkeepsie | Lagrangevl | Dutchess | 12540 | G | 6055 | Todd Hill | N |  | 2.23 | [13 empty] | NM | N | 8 Enphase Energy IQ7-60-x-US (240V) | 2019-02-01 | 2019-02-12 | 7 | 2019-02-12 | [14 empty] | 2019-02-27 | 2019-03-05 |  | Y
Central Hudson |  | Albany Solar Solutions LLC | CH-11238 | Catskill | Medusa | Albany | 12120 | G | 1092 | Westerlo | N |  | 8.64 | [13 empty] | NM | N | 12 Chilicon Power CP-720-60/72/96-208/240-MC4 (240V) [SI1] | 2019-02-19 | 2019-03-05 | 10 | 2019-03-05 | [14 empty] | 2019-04-04 | 2019-04-29 |  | Y
Central Hudson |  | SunCommon | CH-11239 | Poughkeepsie | Tivoli | Dutchess | 12583 | G | 7062 | Milan | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2019-02-04 | 2019-02-08 | 4 | 2019-02-08 | [14 empty] | 2019-04-16 | 2019-04-17 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-11242 | Newburgh | Cornwall | Orange | 12518 | G | 4041 | Union Ave | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2019-02-04 | 2019-02-08 | 4 | 2019-02-08 | [8 empty] | 350 | 350 |  | 2019-02-19 | 2019-02-19 | 2019-04-05 | 2019-04-10 | 2019-04-11 |  | Y
Central Hudson |  | Kasselman Solar | CH-11241 | Poughkeepsie | Lagrangevl | Dutchess | 12540 | G | 6055 | Todd Hill | N |  | 1.92 | [13 empty] | NM | N | 8 Enphase Energy IQ7-60-x-US (240V) | 2019-02-04 | 2019-02-12 | 6 | 2019-02-12 | [14 empty] | 2019-02-27 | 2019-03-05 |  | Y
Central Hudson |  | Kasselman Solar | CH-11240 | Poughkeepsie | Lagrangevl | Dutchess | 12540 | G | 6055 | Todd Hill | N |  | 1.92 | [13 empty] | NM | N | 8 Enphase Energy IQ7-60-x-US (240V) | 2019-02-14 | 2019-02-22 | 5 | 2019-02-22 | [14 empty] | 2019-02-27 | 2019-03-05 |  | Y
Central Hudson |  | New York State Solar Farm | CH-11246 | Newburgh | Newburgh | Orange | 12550 | G | 4011 | West Balmville | N |  | 12.48 | [13 empty] | NM | N | 39 SunPower SPR-X22-360-D-AC (240V) | 2019-02-05 | 2019-02-08 | 3 | 2019-02-08 | [8 empty] | 350 | 350 |  | 2019-03-01 | 2019-03-01 | 2019-03-14 | 2019-04-24 | 2019-04-26 |  | Y
Central Hudson |  | Consolidated Edison Solutions, Inc. | CH-11245 | Kingston | Marbletown |  | 12401 | G | 2094 | Hurley Ave | Y |  |  | 2340 | [12 empty] | CDG | Y | 2IngeconPower Sun 2340 DUAL 1170TL U B540 | 2019-04-23 | 2019-05-03 | 8 | 2019-05-03 | 2019-05-03 | 2019-05-24 | 15 | 2019-06-10 | 2019-09-11 | 2019-12-06 | 60 | 3781.52 | 9467.5 | [7 empty] | 2020-06-01 | W |  | ESS application intended be combined with PV applications CH-09988 and CH-10387. Project following ESS + PV Interim Guidelines Tier 3.
Central Hudson |  | New York State Solar Farm | CH-11243 | Newburgh | New Paltz | Ulster | 12561 | G | 5023 | Ohioville | N |  | 9.92 | [13 empty] | NM | N | 31 SunPower SPR-E20-327-D-AC (240V) | 2019-02-05 | 2019-02-08 | 3 | 2019-02-08 | [14 empty] | 2019-03-04 | 2019-03-08 |  | Y
Central Hudson |  | Red Hook Solar | CH-11244 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7056 | Rhinebeck | N |  | 6 | [13 empty] | NM | N | 1 SMA America SB6.0-1SP-US-40 (240V) | 2019-02-14 | 2019-02-22 | 5 | 2019-02-22 | [14 empty] | 2019-03-07 | 2019-03-11 |  | Y
Central Hudson |  | Vivint Solar Developer, LLC | CH-11250 | Poughkeepsie | Poughkeepsie |  | 12601 | G | 6068 | Inwood Ave | TBD |  | 9.43 | [13 empty] | NM | N | 41 Enphase Energy IQ6-60-X-US (240V) | 2019-02-06 | 2019-02-11 | 3 | 2019-02-11 | [17 empty] | W
Central Hudson |  | SRE Solar Origination 1, LLC | CH-11248 | Kingston | Saugerties |  | 12477 | G | 3002 | Saugerties | Y |  | 3000 | 3000 | [12 empty] | CDG | N | 1 Power Electronics FS3000CU15 (690V) 1Power ElectronicsFS3000K | 2019-04-10 | 2019-04-22 | 7 | 2019-04-22 | 2019-04-22 | 2019-05-10 | 14 | 2019-06-03 | 2019-06-17 | 2019-09-11 | 60 | 11737.82 | 4943146.25 | [7 empty] | 2020-04-17 | W
Central Hudson |  | Sunrun Installation Services, Inc. | CH-11249 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6011 | Sand Dock | N |  | 3.8 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3800H-US (240V) [SI1] | 2019-02-06 | 2019-02-11 | 3 | 2019-02-11 | [14 empty] | 2019-04-23 | 2019-04-26 |  | Y
Central Hudson |  | Solar Image, LLC | CH-11247 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6094 | Manchester | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2019-02-06 | 2019-02-11 | 3 | 2019-02-11 | [14 empty] | 2019-02-19 | 2019-02-22 |  | Y
Central Hudson |  | Vivint Solar Developer, LLC | CH-11254 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8043 | Myers Corners | N |  | 4.14 | [13 empty] | NM | N | 18 Enphase Energy IQ6-60-X-US (240V) | 2019-02-07 | 2019-02-11 | 2 | 2019-02-11 | [14 empty] | 2019-05-16 | 2019-05-21 |  | Y
Central Hudson |  | murphy solar and central air | CH-11251 | Catskill | Coxsackie | Greene | 12051 | G | 1076 | Coxsackie | N |  | 5 | [13 empty] | NM | N | 1 SMA America SB5.0-1TP-US-40 (240V) | 2019-02-07 | 2019-02-11 | 2 | 2019-02-11 | [14 empty] | 2019-05-13 | 2019-05-15 |  | Y
Central Hudson |  | New York State Solar Farm | CH-11255 | Newburgh | Campbell Hall | Orange | 10916 | G | 5051 | Maybrook | N |  | 7.68 | [13 empty] | NM | N | 24 SunPower SPR-E20-327-D-AC (240V) | 2019-02-07 | 2019-02-11 | 2 | 2019-02-11 | [14 empty] | 2019-04-29 | 2019-05-06 |  | Y
Central Hudson |  | PlugPV LLC | CH-11253 | Catskill | Ravena | Albany | 12143 | G | 1081 | New Baltimore | N |  | 3.8 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3800H-US (240V) | 2019-02-07 | 2019-02-11 | 2 | 2019-02-11 | [14 empty] | 2019-03-14 | 2019-03-19 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-11252 | Newburgh | New Windsor | Orange | 12553 | G | 4094 | Bethlehem Rd | N | CH-11252 | 5.44 | [13 empty] | NM | N | 17 SunPower SPR-X22-360-D-AC (240V) | 2019-02-07 | 2019-02-21 | 9 | 2019-02-21 | [14 empty] | 2019-03-07 | 2019-03-12 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-11259 | Newburgh | New Windsor | Orange | 12553 | G | 4097 | Bethlehem Rd | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE11400H-US (240V) | 2019-02-08 | 2019-02-15 | 5 | 2019-02-15 | [14 empty] | 2019-03-18 | 2019-03-19 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-11258 | Fishkill | Poughkeepsie | Dutchess | 12603 | G | 8022 | Knapps Corners | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2019-02-08 | 2019-02-15 | 5 | 2019-02-15 | [14 empty] | 2019-05-17 | 2019-05-21 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-11256 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8091 | Fishkill Plains | N |  | 10.88 | [13 empty] | NM | N | 34 SunPower SPR-X22-360-D-AC (240V) | 2019-02-08 | 2019-02-13 | 3 | 2019-02-13 | [14 empty] | 2019-07-09 | 2019-07-11 |  | Y |  | 5/13/19 - Rep unable to install net meter due to unsafe conditions; customer to make repairs. Repairs completed on 7/9/19. Meter changed 7/10/19.
Central Hudson |  | Sunrun Installation Services, Inc. | CH-11257 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6011 | Sand Dock | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE11400H-US (240V) | 2019-02-08 | 2019-02-25 | 10 | 2019-02-25 | [14 empty] | 2019-04-08 | 2019-04-11 |  | Y
Central Hudson |  | SunCommon | CH-11260 | Newburgh | New Paltz | Ulster | 12561 | G | 5023 | Ohioville | N |  | 199.8 | [13 empty] | NM | N | 6 SolarEdge Technologies SE33.3KUS (480V) | 2019-04-26 | 2019-05-03 | 5 | 2019-05-03 | 2019-05-03 | 2019-05-24 | 15 | [11 empty] | 2021-05-19 | 2021-05-26 |  | Y | Y
Central Hudson |  | Vivint Solar Developer, LLC | CH-11262 | Fishkill | Beacon |  | 12508 | G | 8018 | Forgebrook | N |  | 8.51 | [13 empty] | NM | N | 37 Enphase Energy IQ6-60-X-US (240V) | 2019-03-28 | 2019-04-04 | 5 | 2019-04-04 | [17 empty] | W
Central Hudson |  | New York State Solar Farm | CH-11261 | Kingston | Kingston | Ulster | 12401 | G | 1021 | East Kingston | N |  | 6.4 | [13 empty] | NM | N | 20 SunPower SPR-E20-327-D-AC (240V) | 2019-02-11 | 2019-02-19 | 5 | 2019-02-19 | [14 empty] | 2019-03-04 | 2019-03-05 |  | Y
Central Hudson |  | PlugPV, LLC | CH-11264 | Kingston | Saugerties | Ulster | 12477 | G | 3003 | Saugerties | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000H-US (240V) | 2019-02-13 | 2019-02-25 | 7 | 2019-02-25 | [14 empty] | 2019-02-27 | 2019-03-08 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-11270 | Kingston | Kingston | Ulster | 12401 | G | 1013 | Boulevard | N |  | 3.8 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3800x (240V) [SI1] | 2019-02-13 | 2019-02-19 | 3 | 2019-02-19 | [14 empty] | 2019-05-15 | 2019-05-17 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-11268 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6003 | Reynolds Hill | N |  | 11 | [13 empty] | NM | N | 1 SMA America SB5.0-1SP-US-40 (240V) 1 SMA America SB6.0-1SP-US-40 (240V) | 2019-02-13 | 2019-02-27 | 9 | 2019-02-27 | [14 empty] | 2019-04-22 | 2019-04-23 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-11269 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6052 | Todd Hill | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE 11400A-US (240V) | 2019-02-13 | 2019-02-22 | 6 | 2019-02-22 | [14 empty] | 2019-03-21 | 2019-03-26 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-11265 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8094 | Fishkill Plains | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600A-US (240V) | 2019-02-12 | 2019-02-19 | 4 | 2019-02-19 | [14 empty] | 2019-12-23 | 2019-12-26 |  | Y
Central Hudson |  | Solar Generation Projects, LLC | CH-11266 | Kingston | Saugerties |  | 12401 | G | 3002 | Saugerties | N |  | 2000 | [13 empty] | CDG | N | 16SungrowSG125HV | 2019-05-06 | 2019-05-17 | 9 | 2019-05-17 | 2019-05-17 | 2019-06-10 | 15 |  |  |  |  | 18500 | [9 empty] | W
Central Hudson |  | IPPsolar LLC | CH-11267 | Fishkill | Wappinger |  | 12590 | G | 8056 | North Chelsea | N |  | 1600 | [13 empty] | CDG | N | 16 SolarEdge Technologies SE100KUS (480V) | 2019-05-14 | 2019-05-28 | 9 | 2019-05-28 | 2019-05-28 | 2019-06-18 | 15 |  |  |  |  | 17500 | [9 empty] | W
Central Hudson |  | Vivint Solar Developer, LLC | CH-11274 | Fishkill | Garrison | Putnam | 10524 | G | 8066 | Merritt Park | N |  | 5.29 | [13 empty] | NM | N | 23 Enphase Energy IQ6-60-X-US (240V) | 2019-02-13 | 2019-02-22 | 6 | 2019-02-22 | [14 empty] | 2019-05-14 | 2019-05-16 |  | Y
Central Hudson |  | SolarCity DBA Tesla | CH-11275 | Newburgh | Highland | Ulster | 12528 | G | 5022 | Ohioville | Y | CH-10584 |  | 15 | [12 empty] | NM | N | 3TeslaAC Powerwall 2.0 | 2019-02-13 | 2019-02-22 | 6 | 2019-02-22 | [14 empty] | 2019-04-12 | 2019-04-15 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-11276 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6046 | Spackenkill | N |  | 10 | [13 empty] | NM | N | 2 SMA America SB5.0-1SP-US-40 (240V) | 2019-02-13 | 2019-02-22 | 6 | 2019-02-22 | [14 empty] | 2019-03-28 | 2019-04-01 |  | Y
Central Hudson |  | Solar Generation Projects, LLC | CH-11272 | Catskill | Hannacroix | Greene | 12087 | G | 1072 | Coxsackie | N |  | 1750 | [13 empty] | CDG | Y | 14 Chint Power Systems America CPS SCH125KTL-DO/US-600 (600V) | 2019-05-14 | 2019-05-28 | 9 | 2019-05-28 | 2019-05-28 | 2019-06-18 | 15 | 2019-10-18 | 2019-12-26 | 2020-03-23 | 60 | 10798.31 | 184413.75 | 213608.92 | 2020-06-12 | 2020-12-03 | 2020-12-03 | 2022-09-23 | 2022-09-21 | 2022-09-28 | 2022-12-22 | Y | Y
Central Hudson |  | Kasselman Solar | CH-11271 | Poughkeepsie | Lagrangevl | Dutchess | 12540 | G | 6055 | Todd Hill | N |  | 0.48 | [13 empty] | NM | N | 2 Enphase Energy IQ7-60-x-US (240V) | 2019-02-13 | 2019-02-22 | 6 | 2019-02-22 | [14 empty] | 2019-02-27 | 2019-03-05 |  | Y
Central Hudson |  | Solar Generation Projects, LLC | CH-11273 | Catskill | Hannacroix | Greene | 12087 | G | 1076 | Coxsackie | N |  | 2125 | [13 empty] | CDG | Y | 17 Chint Power Systems America CPS SCH125KTL-DO/US-600 (600V) | 2019-05-14 | 2019-05-28 | 9 | 2019-05-28 | 2019-05-28 | 2019-06-18 | 15 | 2019-10-17 | 2019-12-26 | 2020-03-23 | 60 | 12151.15 | 183163.75 | 185541.67 | 2020-06-17 | 2020-12-09 | 2020-12-09 | 2022-08-23 | 2022-09-12 | 2022-09-19 | 2022-12-22 | Y | Y
Central Hudson |  | Lighthouse Solar | CH-11278 | Kingston | Accord | Ulster | 12404 | G | 3082 | Kerhonkson | N |  | 20 | [13 empty] | NM | N | 2 SolarEdge Technologies SE10000H-US (240V) | 2019-02-14 | 2019-02-26 | 7 | 2019-02-26 | [14 empty] | 2019-05-08 | 2019-05-15 |  | Y
Central Hudson |  | Solar Generation Projects, LLC | CH-11277 | Catskill | Hannacroix | Greene | 12087 | G | 1083 | New Baltimore | N |  | 1750 | [13 empty] | CDG | Y | 14 Chint Power Systems America CPS SCH125KTL-DO/US-600 (600V) | 2019-04-10 | 2019-04-22 | 7 | 2019-04-22 | 2019-04-22 | 2019-05-13 | 15 | 2019-08-14 | 2019-12-30 | 2020-03-25 | 60 | 10683.08 | 277585 | 252597.22 | 2020-06-17 | 2020-12-09 | 2020-12-09 | 2022-07-29 | 2022-08-19 | 2022-08-22 | 2022-12-15 | Y | Y
Central Hudson |  | Infinity Solar Systems | CH-11279 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8072 | Shenandoah | N |  | 19.2 | [13 empty] | NM | N | 60 SunPower SPR-X22-360-D-AC (240V) | 2019-02-15 | 2019-02-25 | 5 | 2019-02-25 | [8 empty] | 350 | 350 |  | 2019-02-27 | 2019-02-27 | 2019-03-08 | 2019-04-01 | 2019-04-03 |  | Y
Central Hudson |  | New York State Solar Farm | CH-11283 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8092 | Fishkill Plains | N |  | 14.72 | [13 empty] | NM | N | 46 SunPower SPR-X22-360-D-AC (240V) | 2019-02-19 | 2019-02-26 | 5 | 2019-02-26 | [14 empty] | 2019-05-07 | 2019-05-10 |  | Y
Central Hudson |  | PlugPV LLC | CH-11281 | Poughkeepsie | Clinton Cors | Dutchess | 12514 | G | 7013 | Hibernia | N | CH-05899 | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2019-03-05 | 2019-03-08 | 3 | 2019-03-08 | [14 empty] | 2019-03-26 | 2019-03-26 |  | Y
Central Hudson |  | New York State Solar Farm | CH-11282 | Kingston | Kingston | Ulster | 12401 | G | 2015 | Lincoln Park | N |  | 33.3 | [13 empty] | NM | N | 1 SMA America STP 33-US-41 (480V) | 2019-02-19 | 2019-02-27 | 6 | 2019-02-27 | [14 empty] | 2020-03-04 | 2020-03-05 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-11280 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6011 | Sand Dock | N |  | 5.6 | [13 empty] | NM | N | 19 Enphase Energy IQ7PLUS-72-x-US (240V) | 2019-02-19 | 2019-02-25 | 4 | 2019-02-25 | [14 empty] | 2019-04-25 | 2019-04-29 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-11284 | Poughkeepsie | Lagrangevl | Dutchess | 12540 | G | 6053 | Todd Hill | N |  | 7 | [13 empty] | NM | N | 1 SMA America SB7.0-1SP-US-40 (240V) | 2019-02-19 | 2019-02-26 | 5 | 2019-02-26 | [14 empty] | 2019-03-21 | 2019-03-26 |  | Y
Central Hudson |  | SunCommon | CH-11288 | Newburgh | Wallkill | Ulster | 12589 | G | 4011 | West Balmville | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE11400H-US (240V) | 2019-02-20 | 2019-02-28 | 6 | 2019-02-28 | [14 empty] | 2019-05-01 | 2019-05-03 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-11286 | Fishkill | Beacon | Dutchess | 12508 | G | 8015 | Forgebrook | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE 11400A-US (240V) | 2019-02-20 | 2019-02-26 | 4 | 2019-02-26 | [14 empty] | 2019-02-28 | 2019-03-05 |  | Y
Central Hudson |  | PlugPV LLC | CH-11285 | Kingston | Saugerties | Ulster | 12477 | G | 3001 | Saugerties | N |  | 3.8 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3800H-US (240V) | 2019-02-20 | 2019-02-25 | 3 | 2019-02-25 | [14 empty] | 2019-06-04 | 2019-06-06 |  | Y
Central Hudson |  | Conscious Energy Inc | CH-11289 | Kingston | Woodstock | Ulster | 12498 | G | 3012 | Woodstock | N |  | 10 | [13 empty] | NM | N | 2 SMA America SB5000TL-US-22 (240V) | 2019-02-20 | 2019-02-26 | 4 | 2019-02-26 | [14 empty] | 2019-09-09 | 2019-09-13 |  | Y
Central Hudson |  | Tri-State Solar Services | CH-11287 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6002 | Reynolds Hill | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE 10000A-US (240V) | 2019-02-26 | 2019-03-08 | 8 | 2019-03-08 | [14 empty] | 2019-05-31 | 2019-06-14 |  | Y
Central Hudson |  | MOMENTUM SOLAR | CH-11290 | Newburgh | Campbell Hall | Orange | 10916 | G | 5051 | Maybrook | N |  | 12.5 | [13 empty] | NM | N | 52 Enphase Energy IQ7-60-x-US (240V) | 2019-02-21 | 2019-02-26 | 3 | 2019-02-26 | [8 empty] | 350 | 350 |  | 2019-03-15 | 2019-03-15 | 2019-04-09 | 2019-04-17 | 2019-04-18 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-11291 | Newburgh | Newburgh |  | 12550 | G | 4015 | West Balmville | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600A-US (240V) | 2019-03-07 | 2019-03-12 | 3 | 2019-03-12 | [14 empty] | 2019-04-03 | 2019-04-05 |  | W
Central Hudson |  | Sunrun Installation Services, Inc. | CH-11292 | Newburgh | Newburgh | Orange | 12550 | G | 4023 | Coldenham | N |  | 7 | [13 empty] | NM | N | 1 SMA America SB7.0-1SP-US-40 (240V) | 2019-02-21 | 2019-02-28 | 5 | 2019-02-28 | [14 empty] | 2019-03-21 | 2019-03-26 |  | Y
Central Hudson |  | New York State Solar Farm | CH-11293 | Newburgh | Newburgh | Orange | 12550 | G | 4023 | Coldenham | Y | CH-10922 |  | 15 | [12 empty] | NM | N | 3TeslaAC Powerwall 2.0 | 2019-02-22 | 2019-03-08 | 10 | 2019-03-08 | [14 empty] | 2019-05-09 | 2019-05-09 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-11295 | Kingston | Greenfield Park |  | 12435 | G | 3078 | Greenfield Rd | N |  | 15.2 | [13 empty] | NM | N | 2 SolarEdge Technologies SE7600A-US (240V) | 2019-02-25 | 2019-02-28 | 3 | 2019-02-28 | [8 empty] | 350 | 350 |  | 2019-03-04 | 2019-03-04 | 2019-04-12 | 2019-04-23 | 2019-04-26 |  | W
Central Hudson |  | SunCommon | CH-11294 | Poughkeepsie | Millbrook | Dutchess | 12545 | G | 7025 | Tinkertown | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2019-02-28 | 2019-03-08 | 6 | 2019-03-08 | [14 empty] | 2019-06-18 | 2019-06-26 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-11299 | Newburgh | New Windsor | Orange | 12553 | G | 4046 | Union Ave | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE11400H-US (240V) | 2019-02-26 | 2019-03-08 | 8 | 2019-03-08 | [14 empty] | 2019-04-08 | 2019-04-09 |  | Y
Central Hudson |  | SunCommon | CH-11296 | Kingston | Rifton | Ulster | 12471 | G | 3041 | Sturgeon Pool | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2019-02-28 | 2019-03-08 | 6 | 2019-03-08 | [14 empty] | 2019-03-22 | 2019-03-26 |  | Y
Central Hudson |  | PlugPV LLC | CH-11297 | Fishkill | Hopewell Jct |  | 12533 | G | 8095 | Fishkill Plains | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2019-02-26 | 2019-02-28 | 2 | 2019-02-28 | [17 empty] | W
Central Hudson |  | Solar Generation | CH-11300 | Poughkeepsie | Millerton | Dutchess | 12546 | G | 7081 | Millerton | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2019-02-26 | 2019-03-08 | 8 | 2019-03-08 | [14 empty] | 2019-05-28 | 2019-05-31 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-11298 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8094 | Fishkill Plains | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000H-US (240V) | 2019-02-26 | 2019-03-08 | 8 | 2019-03-08 | [14 empty] | 2019-04-12 | 2019-04-22 |  | Y
Central Hudson |  | Tesla Energy Operation | CH-11302 | Newburgh | Clintondale | Ulster | 12515 | G | 5081 | Highland | Y |  | 7.6 | 5 | [12 empty] | NM | N | 1 Delta Electronics SOLIVIA 7.6 NA G4 TL (240V) 1TeslaAC Powerwall 2.0 | 2019-02-28 | 2019-03-08 | 6 | 2019-03-08 | [14 empty] | 2019-04-01 | 2019-04-03 |  | Y
Central Hudson |  | PlugPV LLC | CH-11301 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8091 | Fishkill Plains | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2019-03-08 | 2019-03-11 | 1 | 2019-03-11 | [14 empty] | 2019-03-18 | 2019-03-19 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-11303 | Fishkill | Fishkill | Dutchess | 12524 | G | 8055 | North Chelsea | N |  | 6.4 | [13 empty] | NM | N | 20 SunPower SPR-X22-360-D-AC (240V) | 2019-02-28 | 2019-03-08 | 6 | 2019-03-08 | [14 empty] | 2019-05-07 | 2019-05-13 |  | Y
Central Hudson |  | Suncommon | CH-11306 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7056 | Rhinebeck | N | Ch-11306 | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2019-02-28 | 2019-03-08 | 6 | 2019-03-08 | [14 empty] | 2019-04-01 | 2019-04-03 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-11304 | Kingston | Stone Ridge | Ulster | 12484 | G | 3023 | High Falls | N |  | 6.49 | [13 empty] | NM | N | 22 Enphase Energy IQ7PLUS-72-x-US (240V) | 2019-02-28 | 2019-03-08 | 6 | 2019-03-08 | [14 empty] | 2019-05-07 | 2019-05-10 |  | Y
Central Hudson |  | Suncommon | CH-11305 | Kingston | Saugerties | Ulster | 12477 | G | 3001 | Saugerties | N | CH-01716 | 2.24 | [13 empty] | NM | N | 7 SunPower SPR-X22-360-D-AC (240V) [SI1] | 2019-03-12 | 2019-03-19 | 5 | 2019-03-19 | [14 empty] | 2019-03-25 | 2019-03-26 |  | Y
Central Hudson |  | New York State Solar Farm | CH-11307 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6068 | Inwood Ave | N |  | 6.08 | [13 empty] | NM | N | 19 SunPower SPR-X22-360-E-AC (240V) | 2019-03-01 | 2019-03-08 | 5 | 2019-03-08 | [14 empty] | 2019-03-29 | 2019-04-04 |  | Y
Central Hudson |  | New York State Solar Farm | CH-11311 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7054 | Rhinebeck | N |  | 9.6 | [13 empty] | NM | N | 30 SunPower SPR-X22-360-D-AC (240V) | 2019-03-01 | 2019-03-08 | 5 | 2019-03-08 | [14 empty] | 2019-03-08 | 2019-03-12 |  | Y
Central Hudson |  | SunCommon | CH-11312 | Fishkill | Hopewell Junction | Dutchess | 12533 | G | 8092 | Fishkill Plains | N | CH-02172 | 2.56 | [13 empty] | NM | N | 8 SunPower SPR-X20-327-D-AC (240V) | 2019-03-01 | 2019-03-08 | 5 | 2019-03-08 | [14 empty] | 2019-04-03 | 2019-04-04 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-11309 | Newburgh | Newburgh | Orange | 12550 | G | 4022 | Coldenham | N | CH-10451 | 1.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600A-US (240V) | 2019-03-11 | 2019-03-12 | 1 | 2019-03-12 | [14 empty] | 2019-03-14 | 2019-03-19 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-11310 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7061 | Milan | N | CH-10120 | 0.6 | [13 empty] | NM | N | 2 SolarEdge Technologies SE6000 (240V) | 2019-03-11 | 2019-03-12 | 1 | 2019-03-12 | [14 empty] | 2019-04-09 | 2019-04-09 |  | Y
Central Hudson |  | SolarCity DBA Tesla Energy | CH-11316 | Fishkill | Garrison | Putnam | 10524 | G | 8086 | Tioronda | Y | CH-10700 |  | 10 | [12 empty] | NM | N | 2TeslaAC Powerwall 2.0 | 2019-03-15 | 2019-03-20 | 3 | 2019-03-20 | [14 empty] | 2019-07-11 | 2019-07-15 |  | Y
Central Hudson |  | PlugPV LLC | CH-11313 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6091 | Manchester | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2019-03-04 | 2019-03-08 | 4 | 2019-03-08 | [14 empty] | 2019-04-01 | 2019-04-03 |  | Y
Central Hudson |  | PlugPV LLC | CH-11314 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 6074 | East Park | N |  | 15.2 | [13 empty] | NM | N | 2 SolarEdge Technologies SE7600H-US (240V) | 2019-03-18 | 2019-03-20 | 2 | 2019-03-20 | [8 empty] | 350 | 350 |  | 2019-03-21 | 2019-03-21 | 2019-04-10 | 2019-04-10 | 2019-04-16 |  | Y
Central Hudson |  | New York State Solar Farm | CH-11315 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 6068 | Inwood Ave | N |  | 11.52 | [13 empty] | NM | N | 36 SunPower SPR-E20-327-D-AC (240V) | 2019-03-04 | 2019-03-08 | 4 | 2019-03-08 | [8 empty] | 350 | 350 |  | 2019-03-15 | 2019-03-15 | 2019-03-20 | 2019-03-29 | 2019-04-04 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-11317 | Poughkeepsie | Pine Plains | Dutchess | 12567 | G | 7091 | Pulvers Corners | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE 10000A-US (240V) | 2019-03-05 | 2019-03-11 | 4 | 2019-03-11 | [14 empty] | 2019-03-14 | 2019-03-29 |  | Y
Central Hudson |  | Vivint Solar Developer, LLC | CH-11318 | Newburgh | Highland | Ulster | 12528 | G | 5083 | Highland | N |  | 3.91 | [13 empty] | NM | N | 17 Enphase Energy IQ6-60-X-US (240V) | 2019-03-06 | 2019-03-11 | 3 | 2019-03-11 | [14 empty] | 2019-06-12 | 2019-06-12 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-11321 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6046 | Spackenkill | N |  | 7 | [13 empty] | NM | N | 1 SMA America SB7.0-1SP-US-40 (240V) [SI1] | 2019-03-07 | 2019-03-14 | 5 | 2019-03-14 | [14 empty] | 2019-04-30 | 2019-05-02 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-11322 | Newburgh | Newburgh | Orange | 12550 | G | 4023 | Coldenham | N |  | 8.8 | [13 empty] | NM | N | 1 SMA America SB5.0-1SP-US-40 (240V) 1 SMA America SB3.8-1SP-US-40 (240V) | 2019-03-07 | 2019-03-11 | 2 | 2019-03-11 | [14 empty] | 2019-04-08 | 2019-04-09 |  | Y
Central Hudson |  | New York State Solar Farm | CH-11320 | Kingston | Rosendale | Ulster | 12472 | G | 3022 | High Falls | N |  | 6.4 | [13 empty] | NM | N | 20 SunPower SPR-E20-327-D-AC (240V) | 2019-03-07 | 2019-03-11 | 2 | 2019-03-11 | [14 empty] | 2019-03-18 | 2019-03-22 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-11319 | Newburgh | Marlboro | Ulster | 12542 | G | 5001 | Marlboro | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE 10000A-US (240V) | 2019-03-07 | 2019-03-11 | 2 | 2019-03-11 | [14 empty] | 2019-12-10 | 2019-12-10 |  | Y
Central Hudson |  | Tri-State Solar | CH-11324 | Fishkill | Hopewell Junction | Dutchess | 12533 | G | 8071 | Shenandoah | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE 10000A-US (240V) | 2019-04-22 | 2019-04-26 | 4 | 2019-04-26 | [14 empty] | 2019-05-14 | 2019-05-16 |  | Y
Central Hudson |  | MOMENTUM SOLAR | CH-11326 | Poughkeepsie | Millbrook | Dutchess | 12545 | G | 6057 | Todd Hill | N |  | 6.7 | [13 empty] | NM | N | 29 Enphase Energy IQ6-60-X-US (240V) | 2019-03-08 | 2019-03-11 | 1 | 2019-03-11 | [14 empty] | 2019-03-18 | 2019-03-22 |  | Y
Central Hudson |  | Tesla Energy Operations, Inc. | CH-11325 | Kingston | Kerhonkson | Ulster | 12446 | G | 3082 | Kerhonkson | Y | CH-10017 |  | 15 | [12 empty] | NM | N | 3TeslaAC Powerwall 2.0 | 2019-04-17 | 2019-04-26 | 6 | 2019-04-26 | [14 empty] | 2019-07-22 | 2019-07-25 |  | Y
Central Hudson |  | Tesla Energy Operations, Inc. | CH-11323 | Fishkill | Beacon | Dutchess | 12508 | G | 8016 | Forgebrook | Y | CH-10336 |  | 5 | [12 empty] | NM | N | 1TeslaAC Powerwall 2.0 | 2019-04-05 | 2019-04-16 | 7 | 2019-04-16 | [14 empty] | 2019-04-22 | 2019-04-23 |  | Y
Central Hudson |  | New York State Solar Farm | CH-11327 | Kingston | Kerhonkson | Ulster | 12446 | G | 3082 | Kerhonkson | N |  | 7.68 | [13 empty] | NM | N | 24 SunPower SPR-E20-327-D-AC (240V) | 2019-03-11 | 2019-03-11 | 0 | 2019-03-11 | [14 empty] | 2019-03-26 | 2019-03-26 |  | Y
Central Hudson |  | SunCommon | CH-11329 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7052 | Rhinebeck | Y | CH-01770 |  | 5 | [12 empty] | NM | N | 1TeslaAC Powerwall 2.0 | 2019-04-30 | 2019-05-14 | 10 | 2019-05-14 | [14 empty] | 2019-06-25 | 2019-06-25 |  | Y
Central Hudson |  | ForeFront Power | CH-11328 | Newburgh | Windsor |  | 12553 | G | 4091 | Bethlehem Rd | N |  | 1260 | [13 empty] | NM | N | 21 Yaskawa Solectria Solar PVI 60TL-480 (480V) | 2019-06-21 | 2019-07-08 | 10 | 2019-07-08 | 2019-07-08 | 2019-07-29 | 15 |  |  |  |  | 17500 | [9 empty] | W
Central Hudson |  | Infinity Solar Systems | CH-11330 | Newburgh | Montgomery | Orange | 12549 | G | 5073 | Montgomery | N |  | 5.9 | [13 empty] | NM | N | 20 Enphase Energy IQ7PLUS-72-x-US (240V) | 2019-03-12 | 2019-03-14 | 2 | 2019-03-14 | [14 empty] | 2019-05-06 | 2019-05-10 |  | Y
Central Hudson |  | SolarCity DBA Tesla Energy | CH-11336 | Fishkill | Hopewell Junction | Dutchess | 12533 | G | 8072 | Shenandoah | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000 (240V) | 2019-03-12 | 2019-03-19 | 5 | 2019-03-19 | [14 empty] | 2019-04-03 | 2019-04-04 |  | Y
Central Hudson |  | SolarCity DBA Tesla Energy | CH-11337 | Fishkill | Fishkill | Dutchess | 12524 | G | 8014 | Forgebrook | N |  | 7.6 | [13 empty] | NM | N | 1 Delta Electronics SOLIVIA 7.6 NA G4 TL (240V) | 2019-03-22 | 2019-04-01 | 6 | 2019-04-01 | [14 empty] | 2019-04-01 | 2019-04-03 |  | Y
Central Hudson |  | SunCommon | CH-11334 | Kingston | Napanoch | Ulster | 12458 | G | 3072 | Honk Falls | Y | CH-01711 | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2019-03-21 | 2019-03-28 | 5 | 2019-03-28 | [8 empty] | 350 | 350 |  | 2019-03-29 | 2019-03-29 | 2019-04-30 | 2019-04-30 | 2019-05-02 |  | Y
Central Hudson |  | SunBug Solar | CH-11333 | Poughkeepsie | Ancramdale | Columbia | 12503 | G | 7092 | Pulvers Corners | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2019-03-12 | 2019-03-14 | 2 | 2019-03-14 | [14 empty] | 2019-05-13 | 2019-05-15 |  | Y
Central Hudson |  | PlugPV LLC | CH-11331 | Newburgh | New Windsor | Orange | 12553 | G | 4095 | Bethlehem Rd | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2019-03-12 | 2019-03-14 | 2 | 2019-03-14 | [14 empty] | 2019-04-30 | 2019-05-02 |  | Y
Central Hudson |  | Solar Generation | CH-11335 | Kingston | Woodstock | Ulster | 12498 | G | 3013 | Woodstock | N |  | 7.7 | [13 empty] | NM | N | 1 SMA America SB7700TL-US-22 (240V) | 2019-03-20 | 2019-03-21 | 1 | 2019-03-21 | [14 empty] | 2019-05-28 | 2019-05-31 |  | Y
Central Hudson |  | IPPsolar Integration LLC | CH-11338 | Newburgh | Newburgh |  | 12550 | G | 4011 | West Balmville | TBD |  | 5000 | [13 empty] | CDG | N | 50 SolarEdge Technologies SE100KUS (480V) | 2019-05-02 | 2019-05-15 | 9 | 2019-05-15 | 2019-05-15 | 2019-06-06 | 15 |  |  |  |  | 17500 | [9 empty] | W
Central Hudson |  | Kasselman Solar | CH-11339 | Catskill | Palenville | Greene | 12463 | G | 2001 | North Catskill | N |  | 3.84 | [13 empty] | NM | N | 16 Enphase Energy IQ7-60-x-US (240V) | 2019-03-14 | 2019-03-20 | 4 | 2019-03-20 | [14 empty] | 2019-04-11 | 2019-04-16 |  | Y
Central Hudson |  | Ameresco | CH-11341 | Fishkill | East Fishkill | Dutchess | 12533 | G | 8096 | Fishkill Plains | N |  | 4980 | [13 empty] | RC | Y | 30 Yaskawa Solectria Solar XGI 1500-166/166 (600V) | 2019-05-17 | 2019-05-31 | 9 | 2019-05-31 | 2019-05-31 | 2019-06-21 | 15 | 2019-07-08 | 2019-07-29 | 2019-10-22 | 60 | 13312.03 | 255671.25 | 206831.77 | 2020-02-26 | 2020-08-14 | 2020-08-14 | 2022-03-21 | 2022-03-30 | 2022-03-30 | 2022-06-14 | Y | N
Central Hudson |  | PlugPV LLC | CH-11340 | Fishkill | Stormville | Dutchess | 12582 | G | 8093 | Fishkill Plains | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2019-03-14 | 2019-03-20 | 4 | 2019-03-20 | [14 empty] | 2019-04-26 | 2019-04-29 |  | Y
Central Hudson |  | Suncommon | CH-11342 | Catskill | Catskill | Greene | 12414 | G | 2006 | North Catskill | N | CH-01616 | 1 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000H-US (240V) | 2019-03-20 | 2019-03-20 | 0 | 2019-03-20 | [14 empty] | 2019-04-23 | 2019-04-25 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-11343 | Newburgh | New Paltz | Ulster | 12561 | G | 5022 | Ohioville | N |  | 15.2 | [13 empty] | NM | N | 2 SolarEdge Technologies SE7600A-US (240V) | 2019-03-28 | 2019-04-04 | 5 | 2019-04-04 | [8 empty] | 350 | 350 |  | 2019-04-05 | 2019-04-05 | 2019-04-25 | 2019-04-26 | 2019-04-29 |  | Y
Central Hudson |  | New York State Solar Farm | CH-11346 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8043 | Myers Corners | N |  | 7.04 | [13 empty] | NM | N | 22 SunPower SPR-X22-370-E-AC (240V) | 2019-03-19 | 2019-03-20 | 1 | 2019-03-20 | [14 empty] | 2019-04-11 | 2019-04-16 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-11344 | Newburgh | Newburgh |  | 12550 | G | 4053 | Union Ave | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000 (240V) | 2019-03-19 | 2019-03-20 | 1 | 2019-03-20 | [14 empty] | 2019-05-14 | 2019-05-16 |  | W
Central Hudson |  | SolarCity DBA Tesla | CH-11345 | Kingston | Kingston |  | 12401 | G | 3023 | High Falls | N |  | 5.2 | [13 empty] | NM | N | 1 Delta Electronics SOLIVIA 5.2 NA G4 TL (240V) | 2019-03-21 | 2019-03-28 | 5 | 2019-03-28 | [17 empty] | W
Central Hudson |  | Infinity Solar Systems | CH-11347 | Fishkill | Fishkill | Dutchess | 12524 | G | 8014 | Forgebrook | N |  | 13.63 | [13 empty] | NM | N | 47 Enphase Energy IQ7PLUS-72-x-US (240V) | 2019-03-19 | 2019-03-20 | 1 | 2019-03-20 | [14 empty] | 2019-05-09 | 2019-05-16 |  | Y
Central Hudson |  | Vivint Solar Developer, LLC | CH-11348 | Catskill | W Coxsackie | Greene | 12192 | G | 1071 | Coxsackie | N |  | 6.44 | [13 empty] | NM | N | 28 Enphase Energy IQ6-60-X-US (240V) | 2019-03-20 | 2019-03-20 | 0 | 2019-03-20 | [14 empty] | 2019-06-18 | 2019-06-19 |  | Y
Central Hudson |  | Solar Image | CH-11352 | Newburgh | Campbell Hall | Orange | 10916 | G | 5052 | Maybrook | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2019-03-20 | 2019-03-21 | 1 | 2019-03-21 | [14 empty] | 2019-04-15 | 2019-04-15 |  | Y
Central Hudson |  | SolarCity DBA Tesla | CH-11350 | Kingston | Saugerties | Ulster | 12477 | G | 3002 | Saugerties | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000H-US (208V) | 2019-03-20 | 2019-03-21 | 1 | 2019-03-21 | [14 empty] | 2019-06-13 | 2019-06-17 |  | Y
Central Hudson |  | SolarCity DBA Tesla | CH-11349 | Kingston | Saugerties | Ulster | 12477 | G | 3002 | Saugerties | Y |  | 3 | 5 | [12 empty] | NM | N | 1 SolarEdge Technologies SE3000H-US (240V) 1TeslaAC Powerwall 2.0 | 2019-03-20 | 2019-03-20 | 0 | 2019-03-20 | [14 empty] | 2019-06-13 | 2019-06-18 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-11351 | Fishkill | Wappingers Falls | Dutchess | 12590 | G | 8043 | Myers Corners | N |  | 3.6 | [13 empty] | NM | N | 15 Enphase Energy IQ7-60-x-US (240V) | 2019-03-20 | 2019-03-20 | 0 | 2019-03-20 | [14 empty] | 2019-05-10 | 2019-05-14 |  | Y
Central Hudson |  | PlugPV LLC | CH-11356 | Kingston | Kingston | Ulster | 12401 | G | 1021 | East Kingston | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2019-03-21 | 2019-03-29 | 6 | 2019-03-29 | [14 empty] | 2019-04-09 | 2019-04-11 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-11355 | Poughkeepsie | Poughkeepsie |  | 12603 | G | 6046 | Spackenkill | TBD |  | 17.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE11400H-US (240V) 1 SolarEdge Technologies SE6000H-US (240V) | 2019-03-29 | 2019-04-04 | 4 | 2019-04-04 | [17 empty] | W
Central Hudson |  | Empire Solar Solutions | CH-11353 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6046 | Spackenkill | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600A-US (240V) | 2019-03-21 | 2019-03-26 | 3 | 2019-03-26 | [14 empty] | 2019-04-25 | 2019-04-29 |  | Y
Central Hudson |  | Tri-State Solar | CH-11354 | Fishkill | Wappinger | Dutchess | 12590 | G | 8091 | Fishkill Plains | N |  | 12 | [13 empty] | NM | N | 2 SolarEdge Technologies SE6000 (240V) | 2019-05-20 | 2019-05-23 | 3 | 2019-05-23 | [14 empty] | 2019-07-15 | 2019-07-18 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-11359 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6093 | Manchester | N |  | 3.8 | [13 empty] | NM | N | 1 SMA America SB3.8-1SP-US-40 (240V) | 2019-03-22 | 2019-04-01 | 6 | 2019-04-01 | [14 empty] | 2019-04-12 | 2019-04-16 |  | Y
Central Hudson |  | Suncommon | CH-11357 | Kingston | Saugerties | Ulster | 12477 | G | 2015 | Lincoln Park | N | CH-02249 | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000H-US (240V) | 2019-03-22 | 2019-03-29 | 5 | 2019-03-29 | [14 empty] | 2019-04-16 | 2019-04-17 |  | Y
Central Hudson |  | Maybrook Solar, LLC | CH-11358 | Newburgh | Campbell Hall | Orange | 10916 | G | 5051 | Maybrook | N |  | 5000 | [13 empty] | CDG | Y | 40 Sungrow Power Supply SG125HV (600V) 5SungrowSC1000KU5SungrowSC1000KU | 2019-05-29 | 2019-06-11 | 9 | 2019-06-11 | 2019-06-11 | 2019-07-01 | 14 | 2019-07-31 | 2019-08-06 | 2019-10-30 | 60 | 11401.51 | 1251646.25 | 649581.3 | 2020-03-12 | 2020-09-09 | 2020-09-09 | 2022-11-28 | 2022-12-28 | 2022-12-28 | 2023-03-20 | Y | Y
Central Hudson |  | SolarCity DBA Tesla Energy | CH-11360 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 5.2 | [13 empty] | NM | N | 1 Delta Electronics SOLIVIA 5.2 NA G4 TL (240V) | 2019-03-22 | 2019-04-01 | 6 | 2019-04-01 | [14 empty] | 2019-04-30 | 2019-05-02 |  | Y
Central Hudson |  | PlugPV LLC | CH-11363 | Newburgh | Salisbury Mls | Orange | 12577 | G | 4097 | Bethlehem Rd | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2019-03-25 | 2019-04-03 | 7 | 2019-04-03 | [14 empty] | 2019-05-10 | 2019-05-17 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-11361 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6092 | Manchester | N |  | 5.9 | [13 empty] | NM | N | 20 Enphase Energy IQ7PLUS-72-x-US (240V) | 2019-03-25 | 2019-04-01 | 5 | 2019-04-01 | [14 empty] | 2019-05-07 | 2019-05-14 |  | Y
Central Hudson |  | MOMENTUM SOLAR | CH-11366 | Poughkeepsie | Lagrangevl | Dutchess | 12540 | G | 6055 | Todd Hill | N |  | 5.5 | [13 empty] | NM | N | 24 Enphase Energy IQ6-60-X-US (240V) | 2019-04-29 | 2019-05-06 | 5 | 2019-05-06 | [14 empty] | 2019-05-16 | 2019-05-28 |  | Y
Central Hudson |  | PlugPV LLC | CH-11365 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6095 | Manchester | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2019-03-25 | 2019-04-03 | 7 | 2019-04-03 | [14 empty] | 2019-05-02 | 2019-05-10 |  | Y
Central Hudson |  | New York State Solar Farm | CH-11362 | Newburgh | New Windsor | Orange | 12553 | G | 4095 | Bethlehem Rd | N |  | 12.16 | [13 empty] | NM | N | 38 SunPower SPR-E20-327-D-AC (240V) | 2019-03-25 | 2019-04-01 | 5 | 2019-04-01 | [14 empty] | 2019-04-16 | 2019-04-18 |  | Y
Central Hudson |  | New York State Solar Farm | CH-11364 | Poughkeepsie | Salt Pt | Dutchess | 12578 | G | 7012 | Hibernia | Y |  | 6.08 | 5 | [12 empty] | NM | N | 19 SunPower SPR-X21-350-BLK-D-AC (240V) 1TeslaAC Powerwall 2.0 | 2019-04-12 | 2019-04-18 | 4 | 2019-04-18 | [14 empty] | 2019-05-22 | 2019-05-22 |  | Y
Central Hudson |  | CES Danbury Solar LLC | CH-11369 | Fishkill | Fishkill | Dutchess | 12524 | G | 8014 | Forgebrook | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2019-03-26 | 2019-04-03 | 6 | 2019-04-03 | [14 empty] | 2019-09-18 | 2019-09-19 |  | Y
Central Hudson |  | Trinity Solar | CH-11367 | Kingston | Kingston | Ulster | 12401 | G | 1011 | Boulevard | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE11400H-US (240V) | 2019-04-05 | 2019-04-12 | 5 | 2019-04-12 | [14 empty] | 2019-04-26 | 2019-05-02 |  | Y
Central Hudson |  | Tri-State Solar Services | CH-11372 | Newburgh | Newburgh | Orange | 12550 | G | 4015 | West Balmville | N |  | 15.2 | [13 empty] | NM | N | 2 SolarEdge Technologies SE 7600A-US (277V) | 2019-05-16 | 2019-05-20 | 2 | 2019-05-20 | [14 empty] | 2019-07-15 | 2019-07-18 |  | Y
Central Hudson |  | Solar Liberty Energy Systems, Inc. | CH-11373 | Newburgh | New Windsor |  | 12553 | G | 4091 | Bethlehem Rd | N |  | 2100 | [13 empty] | RNM | Y | 42 SMA America STP50-US-40 (480V) [SI1] | 2019-05-09 | 2019-05-22 | 9 | 2019-05-22 | 2019-05-22 | 2019-06-13 | 15 | 2019-06-28 | 2019-07-30 | 2019-10-23 | 60 | 10785.03 | 374895 | [7 empty] | 2020-06-01 | W
Central Hudson |  | Lotus Solar | CH-11371 | Kingston | Ulster Park | Ulster | 12487 | G | 1023 | East Kingston | N |  | 15.4 | [13 empty] | RC | Y | 2 SMA America SB7.7-1SP-US-40 (240V) | 2019-04-04 | 2019-04-10 | 4 | 2019-04-10 | [14 empty] | 2019-06-19 | 2019-06-21 |  | Y | Y
Central Hudson |  | PlugPV LLC | CH-11370 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 7024 | Tinkertown | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2019-03-27 | 2019-04-03 | 5 | 2019-04-03 | [14 empty] | 2019-04-30 | 2019-05-02 |  | Y
Central Hudson |  | SolarCity DBA Tesla Energy | CH-11377 | Kingston | Kerhonkson | Ulster | 12446 | G | 3082 | Kerhonkson | Y |  | 3.8 | 10 | [12 empty] | NM | N | 1 Delta Electronics SOLIVIA 3.8 NA G4 TL (240V) 2TeslaAC Powerwall 2.0 | 2019-03-28 | 2019-04-04 | 5 | 2019-04-04 | [14 empty] | 2019-04-15 | 2019-04-16 |  | Y
Central Hudson |  | New York State Solar Farm | CH-11375 | Newburgh | Montgomery | Orange | 12549 | G | 5073 | Montgomery | N |  | 9.28 | [13 empty] | NM | N | 29 SunPower SPR-X22-370-E-AC (240V) | 2019-03-28 | 2019-04-03 | 4 | 2019-04-03 | [8 empty] | 350 | 350 |  | 2019-04-08 | 2019-04-08 | 2019-04-17 | 2019-05-16 | 2019-05-21 |  | Y
Central Hudson |  | New York State Solar Farm | CH-11379 | Newburgh | Newburgh | Orange | 12550 | G | 5004 | Marlboro | N | CH-10382 | 3.84 | [13 empty] | NM | N | 12 SunPower SPR-E20-327-D-AC (240V) | 2019-04-05 | 2019-04-12 | 5 | 2019-04-12 | [14 empty] | 2019-05-15 | 2019-05-17 |  | Y
Central Hudson |  | Kasselman Solar | CH-11378 | Poughkeepsie | Stanfordvl | Dutchess | 12581 | G | 7072 | Stanfordville | N | CH-02293 | 12.96 | [13 empty] | NM | N | 54 Enphase Energy IQ7-60-x-US (240V) | 2019-04-26 | 2019-05-03 | 5 | 2019-05-03 | [14 empty] | 2019-05-10 | 2019-05-15 |  | Y
Central Hudson |  | Tesla Energy Operations | CH-11376 | Poughkeepsie | Clinton Cors | Dutchess | 12514 | G | 7071 | Stanfordville | Y |  | 7.6 | 10 | [12 empty] | NM | N | 1 SolarEdge Technologies SE7600 (240V) 2TeslaAC Powerwall 2.0 | 2019-04-03 | 2019-04-10 | 5 | 2019-04-10 | [14 empty] | 2019-04-22 | 2019-04-23 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-11374 | Newburgh | Newburgh | Orange | 12550 | G | 4044 | Union Ave | N |  | 16.8 | [13 empty] | NM | N | 58 Enphase Energy IQ7PLUS-72-x-US (240V) | 2019-03-28 | 2019-04-03 | 4 | 2019-04-03 | [14 empty] | 2019-05-21 | 2019-05-23 |  | Y
Central Hudson |  | SolarCity DBA Tesla Energy | CH-11382 | Newburgh | Newburgh | Orange | 12550 | G | 5001 | Marlboro | Y |  | 12.8 | 5 | [12 empty] | NM | N | 1 Delta Electronics SOLIVIA 7.6 NA G4 TL (240V) 1 Delta Electronics SOLIVIA 5.2 NA G4 TL (240V) 1TeslaAC Powerwall 2.0 | 2019-03-29 | 2019-04-04 | 4 | 2019-04-04 | [14 empty] | 2019-04-08 | 2019-04-11 |  | Y
Central Hudson |  | Solar Generation | CH-11381 | Kingston | Olive Brdg | Ulster | 12461 | G | 3024 | High Falls | N |  | 3.8 | [13 empty] | NM | N | 1 SMA America SB3800TL-US-22 (240V) | 2019-04-04 | 2019-04-10 | 4 | 2019-04-10 | [14 empty] | 2019-04-11 | 2019-04-12 |  | Y
Central Hudson |  | Solar Generation | CH-11380 | Kingston | Saugerties | Ulster | 12477 | G | 3003 | Saugerties | N | CH-08294 | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2019-03-29 | 2019-04-04 | 4 | 2019-04-04 | [8 empty] | 350 | 350 |  | 2019-04-08 | 2019-04-08 | 2019-06-06 | 2019-06-13 | 2019-06-17 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-11388 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6093 | Manchester | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE11400H-US (240V) | 2019-04-01 | 2019-04-09 | 6 | 2019-04-09 | [14 empty] | 2019-04-30 | 2019-05-02 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-11383 | Fishkill | Beacon | Dutchess | 12508 | G | 8015 | Forgebrook | N |  | 5 | [13 empty] | NM | N | 20 Enphase Energy IQ7-60-x-US (240V) | 2019-04-01 | 2019-04-05 | 4 | 2019-04-05 | [14 empty] | 2019-05-23 | 2019-05-28 |  | Y
Central Hudson |  | Kasselman Solar | CH-11384 | Poughkeepsie | Stanfordvl | Dutchess | 12581 | G | 7072 | Stanfordville | N |  | 18 | [13 empty] | NM | N | 75 Enphase Energy IQ7-60-x-US (240V) | 2019-04-09 | 2019-04-15 | 4 | 2019-04-15 | [14 empty] | 2019-04-29 | 2019-04-30 |  | Y
Central Hudson |  | Vivint Solar Developer, LLC | CH-11386 | Poughkeepsie | Pleasant Valley | Dutchess | 12569 | G | 6057 | Todd Hill | N |  | 18.4 | [13 empty] | NM | N | 80 Enphase Energy IQ6-60-X-US (240V) | 2019-04-18 | 2019-05-01 | 8 | 2019-05-01 | [14 empty] | 2019-10-31 | 2019-11-19 |  | Y
Central Hudson |  | Lighthouse Solar | CH-11387 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7056 | Rhinebeck | N |  | 6.96 | [13 empty] | NM | N | 24 Enphase Energy IQ7PLUS-72-x-US (240V) [SI1] | 2019-04-01 | 2019-04-09 | 6 | 2019-04-09 | [14 empty] | 2019-05-02 | 2019-05-03 |  | Y
Central Hudson |  | Bright Planet Solar | CH-11385 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6091 | Manchester | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000H-US (240V) | 2019-04-16 | 2019-04-23 | 4 | 2019-04-23 | [8 empty] | 350 | 350 |  | 2019-05-07 | 2019-05-07 | 2019-07-16 | 2019-08-20 | 2019-08-22 |  | Y
Central Hudson |  | Vivint Solar Developer, LLC | CH-11392 | Poughkeepsie | Poughkeepsie |  | 12601 | G | 6073 | East Park | N |  | 11.73 | [13 empty] | NM | N | 51 Enphase Energy IQ6-60-X-US (240V) | 2019-05-16 | 2019-05-20 | 2 | 2019-05-20 | [17 empty] | W
Central Hudson |  | Infinity Solar Systems | CH-11391 | Kingston | Kingston | Ulster | 12401 | G | 1021 | East Kingston | N |  | 13 | [13 empty] | NM | N | 52 Enphase Energy IQ7-60-x-US (240V) | 2019-04-02 | 2019-04-09 | 5 | 2019-04-09 | [14 empty] | 2019-06-14 | 2019-06-19 |  | Y
Central Hudson |  | Tesla Energy Operations, Inc. | CH-11390 | Kingston | Kingston |  | 12401 | G | 2016 | Lincoln Park | Y | CH-05748 |  | 10 | [12 empty] | NM | N | 2TeslaAC PowerWall 2.0 | 2019-04-02 | 2019-04-10 | 6 | 2019-04-10 | [17 empty] | W
Central Hudson |  | Vivint Solar Developer, LLC | CH-11394 | Poughkeepsie | Newburgh |  | 12550 | G | 7091 | Pulvers Corners | N |  | 5.75 | [13 empty] | NM | N | 25 Enphase Energy IQ6-60-X-US (240V) | 2019-04-03 | 2019-04-10 | 5 | 2019-04-10 | [17 empty] | W
Central Hudson |  | Albany Solar Solutions LLC | CH-11393 | Newburgh | Milton | Ulster | 12547 | G | 5002 | Marlboro | N |  | 14.4 | [13 empty] | NM | N | 20 Chilicon Power CP-720-60/72/96-208/240-MC4 (240V) [SI1] | 2019-04-22 | 2019-04-26 | 4 | 2019-04-26 | [14 empty] | 2019-05-01 | 2019-05-03 |  | Y
Central Hudson |  | Suncommon | CH-11395 | Poughkeepsie | Stanfordvl | Dutchess | 12581 | G | 7071 | Stanfordville | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2019-04-03 | 2019-04-10 | 5 | 2019-04-10 | [14 empty] | 2019-05-20 | 2019-05-28 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-11396 | Newburgh | Newburgh |  | 12550 | G | 4051 | Union Ave | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE 10000A-US (240V) | 2019-04-04 | 2019-04-10 | 4 | 2019-04-10 | [14 empty] | 2019-04-16 | 2019-04-18 |  | W
Central Hudson |  | Tri-State Solar Services | CH-11397 | Kingston | Ellenvl | Ulster | 12428 | G | 3078 | Greenfield Rd | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2019-05-02 | 2019-05-07 | 3 | 2019-05-07 | [14 empty] | 2019-05-21 | 2019-05-29 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-11400 | Newburgh | Newburgh |  | 12550 | G | 4052 | Union Ave | N |  | 5 | [13 empty] | NM | N | 1 SMA America SB5.0-1SP-US-40 (240V) [SI1] | 2019-04-08 | 2019-04-15 | 5 | 2019-04-15 | [17 empty] | W
Central Hudson |  | Trinity Solar | CH-11399 | Kingston | Ellenvl | Ulster | 12428 | G | 3078 | Greenfield Rd | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2019-04-08 | 2019-04-15 | 5 | 2019-04-15 | [14 empty] | 2019-08-23 | 2019-08-29 |  | Y
Central Hudson |  | PlugPV LLC | CH-11398 | Newburgh | New Windsor | Orange | 12553 | G | 4095 | Bethlehem Rd | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE11400H-US (240V) [SI1] | 2019-04-17 | 2019-04-26 | 6 | 2019-04-26 | [14 empty] | 2019-05-29 | 2019-05-31 |  | Y
Central Hudson |  | PlugPV LLC | CH-11403 | Kingston | Kingston | Ulster | 12401 | G | 2016 | Lincoln Park | N |  | 21.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE11400H-US (240V) 1 SolarEdge Technologies SE10000H-US (240V) | 2019-04-16 | 2019-04-23 | 4 | 2019-04-23 | [8 empty] | 350 | 350 |  | 2019-05-16 | 2019-05-16 | 2019-06-06 | 2019-06-12 | 2019-06-12 |  | Y
Central Hudson |  | PlugPV LLC | CH-11404 | Newburgh | New Windsor | Orange | 12553 | G | 4095 | Bethlehem Rd | N | CH-23113 | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2019-04-09 | 2019-04-16 | 5 | 2019-04-16 | [14 empty] | 2019-05-17 | 2019-05-21 |  | Y
Central Hudson |  | Greene Correctional Coxsackie NY Solar LLC (Ameresco Inc.) | CH-11402 | Catskill | Coxsackie | Greene | 12051 | G | 1071 | Coxsackie | N |  | 4980 | [13 empty] | RC | Y | 30 Yaskawa Solectria Solar XGI 1500-166/166 (600V) | 2019-05-21 | 2019-06-04 | 9 | 2019-06-04 | 2019-06-04 | 2019-06-25 | 15 | 2019-07-08 | 2019-07-29 | 2019-10-22 | 60 | 13482.2 | 222857.5 | 139523.52 | 2020-03-04 | 2020-07-07 | 2020-07-07 | 2022-08-31 | 2022-10-05 | 2022-10-12 | 2023-01-12 | Y | Y
Central Hudson |  | Kasselman Solar | CH-11401 | Kingston | Saugerties | Ulster | 12477 | G | 3003 | Saugerties | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2019-04-09 | 2019-04-15 | 4 | 2019-04-15 | [14 empty] | 2019-07-15 | 2019-07-18 |  | Y
Central Hudson |  | New York State Solar Farm | CH-11405 | Newburgh | Montgomery | Orange | 12549 | G | 5073 | Montgomery | N |  | 10.88 | [13 empty] | NM | N | 34 SunPower SPR-X22-360-E-AC (240V) | 2019-04-09 | 2019-04-16 | 5 | 2019-04-16 | [14 empty] | 2019-05-15 | 2019-05-17 |  | Y
Central Hudson |  | New York State Solar Farm | CH-11406 | Poughkeepsie | Lagrangeville | Dutchess | 12540 | G | 6053 | Todd Hill | N |  | 9.6 | [13 empty] | NM | N | 30 SunPower SPR-E20-327-E-AC (240V) | 2019-04-09 | 2019-04-15 | 4 | 2019-04-15 | [8 empty] | 350 | 350 |  | 2019-04-23 | 2019-04-23 | 2019-05-06 | 2019-05-17 | 2019-05-21 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-11410 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6046 | Spackenkill | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2019-04-17 | 2019-04-26 | 6 | 2019-04-26 | [14 empty] | 2019-05-09 | 2019-05-13 |  | Y
Central Hudson |  | Eastern Correctional Napanoch NY Solar LLC (Ameresco Inc) | CH-11407 | Kingston | Wawarsing | Ulster | 12458 | G | 3072 | Honk Falls | N |  | 4980 | [13 empty] | RC | Y | 30 Yaskawa Solectria Solar XGI 1500-166/166 (600V) | 2019-05-22 | 2019-06-04 | 8 | 2019-06-04 | 2019-06-04 | 2019-06-25 | 15 | 2019-07-08 | 2019-07-29 | 2019-10-22 | 60 | 13143.53 | 286983.75 | 191980.08 | 2020-03-04 | 2020-07-07 | 2020-07-07 | 2021-04-09 | 2021-10-25 | 2021-10-26 | 2022-02-03 | Y | Y
Central Hudson |  | Shawangunk Correctional Wallkill NY Solar LLC (Ameresco Inc) | CH-11409 | Newburgh | Wallkill |  | 12589 | G | 5043 | East Walden | N |  | 4980 | [13 empty] | RNM | N | 30 Yaskawa Solectria Solar XGI 1500-166/166 (600V) | 2019-05-22 | 2019-06-06 | 10 | 2019-06-06 | 2019-06-06 | 2019-06-27 | 15 | 2019-07-12 | 2019-07-17 | 2019-10-10 | 60 | 10949.11 | 5808945 | [7 empty] | 2020-04-17 | W
Central Hudson |  | Infinity Solar Systems | CH-11412 | Newburgh | Newburgh | Orange | 12550 | G | 4023 | Coldenham | N |  | 2.65 | [13 empty] | NM | N | 9 Enphase Energy IQ7PLUS-72-x-US (240V) | 2019-04-11 | 2019-04-18 | 5 | 2019-04-18 | [14 empty] | 2019-05-06 | 2019-05-09 |  | Y
Central Hudson |  | Sunrun inc | CH-11414 | Kingston | Kingston | Ulster | 12401 | G | 1022 | East Kingston | N |  | 3 | [13 empty] | NM | N | 1 SMA America SB3.0-1SP-US-40 (240V) [SI1] | 2019-04-11 | 2019-04-18 | 5 | 2019-04-18 | [14 empty] | 2019-07-05 | 2019-07-09 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-11411 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6093 | Manchester | N |  | 4.425 | [13 empty] | NM | N | 15 Enphase Energy IQ7PLUS-72-x-US (240V) | 2019-04-11 | 2019-04-18 | 5 | 2019-04-18 | [14 empty] | 2019-06-28 | 2019-07-02 |  | Y
Central Hudson |  | SRE Solar Origination 1, LLC | CH-11413 | Catskill | Selkirk |  | 12158 | G | 1082 | New Baltimore | Y |  | 4600 | 4600 | [12 empty] | CDG | Y | 2Power ElectronicsHEMK FS2300K2Power ElectronicsHEMK FS2300K | 2019-05-14 | 2019-05-28 | 9 | 2019-05-28 | 2019-05-28 | 2019-06-18 | 15 | 2019-07-11 | 2019-07-19 | 2019-10-14 | 60 | 14912.11 | 1464773.75 |  | 2020-02-24 | [5 empty] | 2021-01-29 | W | Y | 9/3/20 - 75% payment deadline extended to 11/10/2020 due to moratorium being submitted.
Central Hudson |  | Kasselman Solar | CH-11415 | Kingston | Kerhonkson | Ulster | 12446 | G | 3081 | Kerhonkson | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000H-US (240V) | 2019-04-12 | 2019-04-18 | 4 | 2019-04-18 | [14 empty] | 2019-04-22 | 2019-04-23 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-11416 | Newburgh | Newburgh | Orange | 12550 | G | 4047 | Union Ave | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000 (240V) | 2019-04-12 | 2019-04-26 | 9 | 2019-04-26 | [14 empty] | 2019-05-14 | 2019-05-16 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-11418 | Fishkill | Hopewell Junction | Dutchess | 12533 | G | 8096 | Fishkill Plains | N |  | 5.31 | [13 empty] | NM | N | 18 Enphase Energy IQ7PLUS-72-x-US (240V) | 2019-04-12 | 2019-04-26 | 9 | 2019-04-26 | [14 empty] | 2019-05-23 | 2019-05-28 |  | Y
Central Hudson |  | Lighthouse Solar | CH-11422 | Kingston | Stone Ridge | Ulster | 12484 | G | 3024 | High Falls | N |  | 12.18 | [13 empty] | NM | N | 42 Enphase Energy IQ7PLUS-72-x-US (240V) [SI1] | 2019-04-22 | 2019-04-26 | 4 | 2019-04-26 | [14 empty] | 2019-07-16 | 2019-07-18 |  | Y
Central Hudson |  | Sunrun Inc | CH-11420 | Newburgh | Marlboro | Ulster | 12542 | G | 5004 | Marlboro | N | CH-09203 | 3 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3000H-US (240V) | 2019-04-12 | 2019-04-18 | 4 | 2019-04-18 | [14 empty] | 2019-05-07 | 2019-05-10 |  | Y
Central Hudson |  | Solar Generation Projects, LLC | CH-11417 | Kingston | Kingston |  | 12401 | G | 2094 | Hurley Ave | N |  | 136.5 | [13 empty] | CDG | Y | 1 SMA America STP24000TL-US-10 (480V) [SI1] 1 SMA America STP 50-US-41 (480V) 1 SMA America STP 62-US-41 (480V) | 2019-08-08 | 2019-08-12 | 2 | 2019-08-12 | 2019-08-12 | 2019-09-03 | 15 | [14 empty] | W
Central Hudson |  | Sunrun Installation Services, Inc. | CH-11421 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6065 | Inwood Ave | N |  | 5 | [13 empty] | NM | N | 1 SMA America SB5.0-1SP-US-40 (240V) [SI1] | 2019-04-12 | 2019-04-18 | 4 | 2019-04-18 | [14 empty] | 2019-06-03 | 2019-06-06 |  | Y
Central Hudson |  | SRE Solar Origination 1, LLC | CH-11419 | Kingston | Ulster Park |  | 12401 | G | 1021 | East Kingston | Y |  | 3450 | 3450 | [12 empty] | CDG | Y | 1Power ElectronicsHEMK FS3450K1Power ElectronicsHEMK FS3450K | 2019-05-14 | 2019-05-28 | 9 | 2019-05-28 | 2019-05-28 | 2019-06-18 | 15 | 2019-07-11 | 2019-09-30 | 2019-10-18 | 14 | 10351.91 | 4897795 | [7 empty] | 2020-05-18 | W |  | 9/17/19 - CESIR placed on hold due to the delay in obtaining documents from the applicant. The CESIR recommenced on 9/30/19.
Central Hudson |  | PlugPV LLC | CH-11424 | Poughkeepsie | Hyde Pk |  | 12538 | G | 6075 | East Park | N |  | 6.3 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2019-04-15 | 2019-04-23 | 5 | 2019-04-23 | [17 empty] | W
Central Hudson |  | PlugPV LLC | CH-11423 | Poughkeepsie | Lagrangevl | Dutchess | 12540 | G | 6053 | Todd Hill | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2019-04-15 | 2019-04-23 | 5 | 2019-04-23 | [14 empty] | 2019-05-10 | 2019-05-14 |  | Y
Central Hudson |  | PlugPV LLC | CH-11425 | Newburgh | Wallkill | Ulster | 12589 | G | 5043 | East Walden | N |  | 12.09 | [13 empty] | NM | N | 1 SolarEdge Technologies SE11400H-US (240V) | 2019-04-16 | 2019-04-23 | 4 | 2019-04-23 | [14 empty] | 2019-07-09 | 2019-07-11 |  | Y
Central Hudson |  | Solitude Solar, LLC | CH-11427 | Catskill | Westerlo |  | 12193 | G | 1091 | Westerlo | N |  | 1980 | [13 empty] | CDG | N | 66 SMA America STP30000TL-US-10 (480V) | 2019-08-21 | 2019-09-03 | 8 | 2019-09-03 | 2019-09-03 | 2019-09-24 | 15 |  |  |  |  | 17500 | [9 empty] | W
Central Hudson |  | Kasselman Solar | CH-11428 | Kingston | Stone Ridge | Ulster | 12484 | G | 3023 | High Falls | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE11400H-US (240V) | 2019-04-16 | 2019-04-23 | 4 | 2019-04-23 | [14 empty] | 2019-04-26 | 2019-05-02 |  | Y
Central Hudson |  | Consolidated Edison Solutions, Inc. | CH-11430 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6043 | Spackenkill | N |  | 224 | [13 empty] | NM | N | 16 Yaskawa Solectria Solar PVI 14TL-208 | 2019-05-02 | 2019-05-15 | 9 | 2019-05-15 | 2019-05-15 | 2019-06-06 | 15 | [11 empty] | 2020-12-09 | 2020-12-09 |  | Y
Central Hudson |  | Solar Generation | CH-11431 | Kingston | Kingston |  | 12401 | G | 2094 | Hurley Ave | N |  | 30 | [13 empty] | NM | N | 3 SolarEdge Technologies SE10000H-US (240V) | 2019-05-23 | 2019-06-07 | 10 | 2019-06-07 | [8 empty] | 2500 | [8 empty] | W
Central Hudson |  | Tesla Energy Operations, Inc. | CH-11429 | Kingston | Shady | Ulster | 12409 | G | 3012 | Woodstock | Y | CH-10518 |  | 10 | [12 empty] | NM | N | 2TeslaAC Powerwall 2.0 | 2019-04-17 | 2019-04-26 | 6 | 2019-04-26 | [14 empty] | 2019-05-02 | 2019-05-03 |  | Y
Central Hudson |  | Suncommon | CH-11432 | Kingston | Kingston | Ulster | 12401 | G | 2091 | Hurley Ave | N | CH-10311 | 499.5 | [13 empty] | CDG | Y | 15 SolarEdge Technologies SE33.3KUS (480V) | 2019-05-31 | 2019-06-11 | 7 | 2019-06-11 | 2019-06-11 | 2019-07-01 | 14 | [5 empty] | 100125 | 80083.78 | 2019-10-15 | 2020-05-19 | 2020-05-19 | 2020-10-02 | 2020-11-04 | 2020-11-12 | 2021-02-01 | Y | Y
Central Hudson |  | Empire Solar Solutions | CH-11435 | Newburgh | Newburgh | Orange | 12550 | G | 4047 | Union Ave | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600A-US (240V) | 2019-04-12 | 2019-04-18 | 4 | 2019-04-18 | [14 empty] | 2019-05-14 | 2019-05-16 |  | Y
Central Hudson |  | Solar Image | CH-11434 | Poughkeepsie | Staatsburg | Dutchess | 12580 | G | 7041 | Staatsburg | N | CH-11434 | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2019-05-07 | 2019-05-10 | 3 | 2019-05-10 | [14 empty] | 2019-05-17 | 2019-05-21 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-11433 | Newburgh | Campbell Hall | Orange | 10916 | G | 5051 | Maybrook | N |  | 8.5 | [13 empty] | NM | N | 34 Enphase Energy IQ7-60-x-US (240V) | 2019-04-18 | 2019-04-26 | 5 | 2019-04-26 | [14 empty] | 2019-06-14 | 2019-06-19 |  | Y
Central Hudson |  | Dimension NY 1 | CH-11436 | Catskill | Cairo |  | 12413 | G | 2042 | South Cairo | Y |  | 3850 | 3697.5 | [12 empty] | CDG | N | 5TeslaMegapack5TeslaMegapack | 2019-07-23 | 2019-07-30 | 5 | 2019-07-30 | 2019-07-30 | 2019-08-19 | 14 |  |  |  |  | 17500 | [9 empty] | W
Central Hudson |  | Consolidated Edison Solutions, Inc. | CH-11441 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6044 | Spackenkill | N |  | 137 | [13 empty] | NM | N | 1 Chint Power Systems America CPS SCA50KTL-DO/US-480 (480V) [SI1] 1 Chint Power Systems America CPS SCA36KTL-DO/US (480V) [SI1] 1 Chint Power Systems America CPS SCA28KTL-DO/US-480 (480V) 1 Chint Power Systems America CPS SCA23KTL-DO/US-480 (480V) | 2019-05-08 | 2019-05-22 | 10 | 2019-05-22 | 2019-05-22 | 2019-06-13 | 15 | [11 empty] | 2020-11-12 | 2020-11-30 |  | Y
Central Hudson |  | Consolidated Edison Solutions, Inc. | CH-11439 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6011 | Sand Dock | N |  | 84 | [13 empty] | NM | N | 6 Chint Power Systems America CPS SC14KTL-DO/xx-208 (208V) | 2019-05-03 | 2019-05-16 | 9 | 2019-05-16 | 2019-05-16 | 2019-06-07 | 15 | [11 empty] | 2020-11-12 | 2020-11-13 |  | Y
Central Hudson |  | New York State Solar Farm | CH-11438 | Kingston | New Paltz | Ulster | 12561 | G | 3022 | High Falls | N |  | 21.12 | [13 empty] | NM | N | 66 SunPower SPR-X22-360-E-AC (240V) | 2019-04-22 | 2019-04-26 | 4 | 2019-04-26 | [8 empty] | 350 | 350 |  | 2019-05-14 | 2019-05-14 | 2019-06-06 | 2019-06-12 | 2019-06-12 |  | Y
Central Hudson |  | Trinity Solar | CH-11440 | Kingston | Kerhonkson | Ulster | 12446 | G | 3082 | Kerhonkson | N |  | 12.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) 1 SolarEdge Technologies SE5000H-US (240V) | 2019-04-22 | 2019-04-26 | 4 | 2019-04-26 | [14 empty] | 2019-06-21 | 2019-06-28 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-11444 | Poughkeepsie | Poughkeepsie |  | 12603 | G | 6096 | Manchester | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000 (240V) | 2019-04-22 | 2019-04-30 | 6 | 2019-04-30 | [14 empty] | 2019-05-13 | 2019-05-15 |  | W
Central Hudson |  | Empire Solar Solutions | CH-11437 | Poughkeepsie | Stanfordvl | Dutchess | 12581 | G | 7071 | Stanfordville | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000 (240V) | 2019-04-22 | 2019-04-26 | 4 | 2019-04-26 | [14 empty] | 2019-06-12 | 2019-06-12 |  | Y
Central Hudson |  | Lighthouse Solar | CH-11443 | Newburgh | Gardiner | Ulster | 12525 | G | 5011 | Modena | N |  | 9.28 | [13 empty] | NM | N | 32 Enphase Energy IQ7PLUS-72-x-US (240V) [SI1] | 2019-04-22 | 2019-04-30 | 6 | 2019-04-30 | [14 empty] | 2019-06-12 | 2019-06-12 |  | Y
Central Hudson |  | Kasselman Solar | CH-11442 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6042 | Spackenkill | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2019-04-30 | 2019-05-06 | 4 | 2019-05-06 | [14 empty] | 2019-07-29 | 2019-08-02 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-11446 | Newburgh | Newburgh | Orange | 12550 | G | 4015 | West Balmville | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE 10000A-US (240V) | 2019-04-23 | 2019-04-30 | 5 | 2019-04-30 | [14 empty] | 2019-05-06 | 2019-05-09 |  | Y
Central Hudson |  | Consolidated Edison Solutions, Inc. | CH-11449 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6044 | Spackenkill | N |  | 112 | [13 empty] | NM | N | 8 Chint Power Systems America CPS SC14KTL-DO/xx-208 (208V) | 2019-04-23 | 2019-05-07 | 10 | 2019-05-07 | 2019-05-07 | 2019-05-29 | 15 | [11 empty] | 2020-11-12 | 2020-11-13 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-11447 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6046 | Spackenkill | N | CH-11447 | 7.6 | [13 empty] | NM | N | 1 SMA America SB3.8-1SP-US-40 (240V) [SI1] 1 SMA America SB3.8-1SP-US-40 (240V) [SI1] | 2019-04-23 | 2019-04-30 | 5 | 2019-04-30 | [14 empty] | 2019-05-15 | 2019-05-28 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-11448 | Poughkeepsie | Poughkeepsie |  | 12603 | G | 6093 | Manchester | N |  | 7 | [13 empty] | NM | N | 1 SMA America SB7.0-1SP-US-40 (240V) | 2019-04-23 | 2019-04-30 | 5 | 2019-04-30 | [17 empty] | W
Central Hudson |  | Kasselman Solar | CH-11445 | Catskill | Athens | Greene | 12015 | G | 2002 | North Catskill | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2019-05-06 | 2019-05-10 | 4 | 2019-05-10 | [14 empty] | 2019-06-28 | 2019-07-03 |  | Y
Central Hudson |  | New York State Solar Farm | CH-11452 | Fishkill | Garrison | Putnam | 10524 | G | 8086 | Tioronda | N |  | 14.8 | [13 empty] | NM | N | 47 SunPower SPR-E20-327-E-AC (240V) | 2019-04-24 | 2019-05-02 | 6 | 2019-05-02 | [14 empty] | 2019-05-31 | 2019-06-04 |  | Y
Central Hudson |  | PlugPV LLC | CH-11453 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6095 | Manchester | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000H-US (240V) | 2019-04-24 | 2019-05-02 | 6 | 2019-05-02 | [14 empty] | 2019-05-22 | 2019-05-22 |  | Y
Central Hudson |  | New York State Solar Farm | CH-11451 | Newburgh | New Paltz | Ulster | 12561 | G | 5024 | Ohioville | N |  | 6.4 | [13 empty] | NM | N | 20 SunPower SPR-X22-360-E-AC (240V) | 2019-04-24 | 2019-05-02 | 6 | 2019-05-02 | [14 empty] | 2019-05-15 | 2019-05-17 |  | Y
Central Hudson |  | New York State Solar Farm | CH-11456 | Fishkill | Nelsonvl | Putnam | 10516 | G | 8087 | Tioronda | N | CH-10484 | 3.84 | [13 empty] | NM | N | 12 SunPower SPR-E20-327-D-AC (240V) | 2019-04-25 | 2019-05-02 | 5 | 2019-05-02 | [14 empty] | 2019-05-29 | 2019-05-31 |  | Y
Central Hudson |  | PlugPV LLC | CH-11454 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8091 | Fishkill Plains | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2019-04-25 | 2019-05-02 | 5 | 2019-05-02 | [14 empty] | 2019-06-10 | 2019-06-11 |  | Y
Central Hudson |  | PlugPV LLC | CH-11455 | Newburgh | Salisbury Mls | Orange | 12577 | G | 4097 | Bethlehem Rd | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2019-04-25 | 2019-05-02 | 5 | 2019-05-02 | [14 empty] | 2019-06-10 | 2019-06-11 |  | Y
Central Hudson |  | PlugPV LLC | CH-11459 | Kingston | Lk Katrine | Ulster | 12449 | G | 2016 | Lincoln Park | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2019-04-26 | 2019-05-03 | 5 | 2019-05-03 | [14 empty] | 2019-05-23 | 2019-05-28 |  | Y
Central Hudson |  | Kasselman Solar | CH-11457 | Catskill | W Coxsackie | Greene | 12192 | G | 1071 | Coxsackie | N | CH-00239 | 1 | [13 empty] | NM | N | 4 Enphase Energy M250-72-2LL-S2x (240V) | 2019-04-26 | 2019-05-03 | 5 | 2019-05-03 | [14 empty] | 2019-06-03 | 2019-06-05 |  | Y
Central Hudson |  | Kasselman Solar | CH-11458 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6092 | Manchester | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2019-04-26 | 2019-05-03 | 5 | 2019-05-03 | [14 empty] | 2019-06-03 | 2019-06-04 |  | Y
Central Hudson |  | Bright Planet Solar | CH-11462 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8023 | Knapps Corners | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2019-06-24 | 2019-06-25 | 1 | 2019-06-25 | [14 empty] | 2019-08-05 | 2019-08-12 |  | Y
Central Hudson |  | Bright Planet Solar | CH-11466 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6093 | Manchester | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2019-06-11 | 2019-06-11 | 0 | 2019-06-11 | [14 empty] | 2019-11-13 | 2019-11-14 |  | Y
Central Hudson |  | Suncommon | CH-11460 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7061 | Milan | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000 (240V) | 2019-05-03 | 2019-05-10 | 5 | 2019-05-10 | [14 empty] | 2019-06-05 | 2019-06-19 |  | Y
Central Hudson |  | Bright Planet Solar | CH-11464 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6045 | Spackenkill | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2019-05-24 | 2019-05-28 | 1 | 2019-05-28 | [14 empty] | 2019-06-05 | 2019-06-10 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-11468 | Poughkeepsie | Rhinebeck |  | 12572 | G | 7052 | Rhinebeck | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000 (240V) | 2019-04-30 | 2019-05-06 | 4 | 2019-05-06 | [14 empty] | 2019-05-08 | 2019-05-13 |  | W
Central Hudson |  | Sunrun Installation Services, Inc. | CH-11470 | Fishkill | Fishkill | Dutchess | 12524 | G | 8063 | Merritt Park | N |  | 6 | [13 empty] | NM | N | 1 SMA America SB6.0-1SP-US-40 (240V) | 2019-04-30 | 2019-05-13 | 9 | 2019-05-13 | [14 empty] | 2019-05-21 | 2019-05-21 |  | Y
Central Hudson |  | Solar Image | CH-11467 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6045 | Spackenkill | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2019-04-30 | 2019-05-06 | 4 | 2019-05-06 | [14 empty] | 2019-05-15 | 2019-05-17 |  | W
Central Hudson |  | Tri-State Solar Services | CH-11471 | Fishkill | Beacon | Dutchess | 12508 | G | 8085 | Tioronda | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2019-05-16 | 2019-05-22 | 4 | 2019-05-22 | [14 empty] | 2020-02-04 | 2020-02-04 |  | Y
Central Hudson |  | Bright Planet Solar | CH-11472 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6094 | Manchester | N |  | 3.8 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3800H-US (240V) [SI1] | 2019-12-04 | 2019-12-06 | 2 | 2019-12-06 | [14 empty] | 2019-12-06 | 2019-12-06 |  | Y
Central Hudson |  | Bright Planet Solar | CH-11473 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8046 | Myers Corners | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2019-05-29 | 2019-06-03 | 3 | 2019-06-03 | [14 empty] | 2019-10-28 | 2019-10-30 |  | Y
Central Hudson |  | Sunrun, INC | CH-11475 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7052 | Rhinebeck | N |  | 20.735 | [13 empty] | NM | N | 1 SolarEdge Technologies SE 11400A-US (240V) 1 SolarEdge Technologies SE10000H-US (240V) | 2019-05-01 | 2019-05-06 | 3 | 2019-05-06 | [14 empty] | 2019-05-29 | 2019-06-17 |  | Y
Central Hudson |  | New York State Solar Farm | CH-11474 | Newburgh | New Windsor | Orange | 12553 | G | 4095 | Bethlehem Rd | N |  | 8.96 | [13 empty] | NM | N | 28 SunPower SPR-X22-370-E-AC (240V) | 2019-05-01 | 2019-05-08 | 5 | 2019-05-08 | [14 empty] | 2019-05-20 | 2019-05-23 |  | Y
Central Hudson |  | PlugPV LLC | CH-11476 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6092 | Manchester | N |  | 8.19 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2019-05-02 | 2019-05-06 | 2 | 2019-05-06 | [14 empty] | 2019-05-28 | 2019-06-10 |  | Y
Central Hudson |  | Suncommon | CH-11477 | Kingston | Napanoch | Ulster | 12458 | G | 3072 | Honk Falls | Y | CH-01711 |  | 10 | [12 empty] | NM | N | 2TeslaAC Powerwall 2.0 | 2019-05-02 | 2019-05-15 | 9 | 2019-05-15 | [14 empty] | 2019-07-09 | 2019-07-10 |  | Y
Central Hudson |  | New York State Solar Farm | CH-11481 | Newburgh | Marlboro | Ulster | 12542 | G | 5004 | Marlboro | N |  | 15.04 | [13 empty] | NM | N | 47 SunPower SPR-X22-360-E-AC (240V) | 2019-05-02 | 2019-05-07 | 3 | 2019-05-07 | [8 empty] | 350 | 350 |  | 2019-05-14 | 2019-05-14 | 2019-05-23 | 2019-06-17 | 2019-06-19 |  | Y
Central Hudson |  | New York State Solar Farm | CH-11480 | Kingston | Ellenville | Ulster | 12428 | G | 3078 | Greenfield Rd | N |  | 7.245 | [13 empty] | NM | N | 23 SunPower SPR-X22-370-E-AC (240V) | 2019-05-02 | 2019-05-07 | 3 | 2019-05-07 | [14 empty] | 2019-08-08 | 2019-08-13 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-11478 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8043 | Myers Corners | N |  | 4.25 | [13 empty] | NM | N | 17 Enphase Energy IQ7-60-x-US (240V) | 2019-05-02 | 2019-05-07 | 3 | 2019-05-07 | [14 empty] | 2019-06-26 | 2019-06-28 |  | Y
Central Hudson |  | Bright Planet Solar | CH-11479 | Poughkeepsie | Poughkeepsie |  | 12603 | G | 6093 | Manchester | N |  | 15.2 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) 1 SolarEdge Technologies SE7600H-US (240V) | 2019-05-29 | 2019-06-03 | 3 | 2019-06-03 | [17 empty] | W
Central Hudson |  | Sunrun Installation Services, Inc. | CH-11485 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8094 | Fishkill Plains | N |  | 3.8 | [13 empty] | NM | N | 1 SMA America SB3.8-1SP-US-40 (240V) | 2019-05-03 | 2019-05-10 | 5 | 2019-05-10 | [14 empty] | 2019-06-12 | 2019-06-17 |  | Y
Central Hudson |  | PlugPV LLC | CH-11482 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6093 | Manchester | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000H-US (240V) | 2019-05-03 | 2019-05-10 | 5 | 2019-05-10 | [14 empty] | 2019-06-17 | 2019-06-25 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-11483 | Kingston | Shokan |  | 12481 | G | 3011 | Woodstock | N |  | 3 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3000 (240V) | 2019-05-03 | 2019-05-10 | 5 | 2019-05-10 | [14 empty] | 2019-05-15 | 2019-05-17 |  | W
Central Hudson |  | Bright Planet Solar | CH-11486 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6094 | Manchester | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2019-05-10 | 2019-05-20 | 6 | 2019-05-20 | [14 empty] | 2019-10-16 | 2019-10-17 |  | Y
Central Hudson |  | Vivint Solar Developer, LLC | CH-11487 | Catskill | Athens |  | 12015 | G | 2002 | North Catskill | N | CH-08604 | 4.83 | [13 empty] | NM | N | 21 Enphase Energy IQ6-60-X-US (240V) | 2019-05-16 | 2019-05-20 | 2 | 2019-05-20 | [8 empty] | 350 | [8 empty] | W
Central Hudson |  | SolarCity DBA Tesla Energy | CH-11489 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6092 | Manchester | Y |  | 12.8 | 10 | [12 empty] | NM | N | 1 Delta Electronics SOLIVIA 7.6 NA G4 TL (240V) [SI1] 1 Delta Electronics SOLIVIA 5.2 NA G4 TL (240V) [SI1] 2TeslaAC Powerwall 2.0 | 2019-05-07 | 2019-05-21 | 10 | 2019-05-21 | [14 empty] | 2019-08-02 | 2019-08-16 |  | Y
Central Hudson |  | New York State Solar Farm | CH-11492 | Kingston | Kingston | Ulster | 12401 | G | 1022 | East Kingston | N | CH-00379 | 1.28 | [13 empty] | NM | N | 4 SunPower SPR-E20-327-E-AC (240V) | 2019-05-07 | 2019-05-16 | 7 | 2019-05-16 | [14 empty] | 2019-07-12 | 2019-07-15 |  | Y
Central Hudson |  | New York State Solar Farm | CH-11491 | Fishkill | Beacon | Dutchess | 12508 | G | 8087 | Tioronda | N |  | 4.48 | [13 empty] | NM | N | 14 SunPower SPR-E20-327-E-AC (240V) | 2019-05-07 | 2019-05-13 | 4 | 2019-05-13 | [14 empty] | 2019-07-10 | 2019-07-18 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-11488 | Newburgh | Maybrook | Orange | 12543 | G | 5052 | Maybrook | N |  | 4.25 | [13 empty] | NM | N | 17 Enphase Energy IQ7-60-x-US (240V) | 2019-05-07 | 2019-05-10 | 3 | 2019-05-10 | [14 empty] | 2019-05-29 | 2019-05-31 |  | Y
Central Hudson |  | Suncommon | CH-11490 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7051 | Rhinebeck | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2019-05-07 | 2019-05-10 | 3 | 2019-05-10 | [14 empty] | 2019-06-12 | 2019-06-12 |  | Y
Central Hudson |  | Vivint Solar Developer, LLC | CH-11495 | Newburgh | Newburgh | Orange | 12550 | G | 4014 | West Balmville | N |  | 5.06 | [13 empty] | NM | N | 22 Enphase Energy IQ6-60-X-US (240V) | 2019-05-08 | 2019-05-16 | 6 | 2019-05-16 | [14 empty] | 2019-11-11 | 2019-11-11 |  | Y |  | 6/19/19 - Unable to install net meter; customer to have electrician fix hazard. 11/05/19 - Hazard fixed; net meter installed.
Central Hudson |  | PlugPV LLC | CH-11493 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8091 | Fishkill Plains | N |  | 19 | [13 empty] | NM | N | 1 SolarEdge Technologies SE11400H-US (240V) 1 SolarEdge Technologies SE7600H-US (240V) | 2019-05-16 | 2019-05-20 | 2 | 2019-05-20 | [14 empty] | 2019-06-28 | 2019-07-02 |  | Y
Central Hudson |  | Common Energy | CH-11502 | Poughkeepsie | Lagrangeville | Dutchess | 12540 | G | 6055 | Todd Hill | N |  | 1656.2 | [13 empty] | CDG | Y | 7 Sungrow Power Supply SG125HV (600V) 7 Sungrow Power Supply SG125HV (600V) | 2019-05-23 | 2019-06-07 | 10 | 2019-06-07 | 2019-06-07 | 2019-06-28 | 15 | 2019-08-05 | 2019-09-17 | 2019-12-12 | 60 | 13045.76 | 263482.5 | 232642.2 | 2020-03-03 | 2020-08-24 | 2020-08-24 | 2021-06-24 | 2021-08-27 | 2021-08-27 | 2022-03-24 | Y | Y
Central Hudson |  | Infinity Solar Systems | CH-11497 | Newburgh | Newburgh | Orange | 12550 | G | 4095 | Bethlehem Rd | N |  | 11 | [13 empty] | NM | N | 44 Enphase Energy IQ7-60-x-US (240V) | 2019-05-09 | 2019-05-17 | 6 | 2019-05-17 | [14 empty] | 2019-07-12 | 2019-07-15 |  | Y
Central Hudson |  | PlugPV LLC | CH-11501 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6093 | Manchester | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2019-05-09 | 2019-05-17 | 6 | 2019-05-17 | [14 empty] | 2019-06-07 | 2019-06-11 |  | Y
Central Hudson |  | PlugPV LLC | CH-11496 | Kingston | Kingston | Ulster | 12401 | G | 1021 | East Kingston | N |  | 12 | [13 empty] | NM | N | 2 SolarEdge Technologies SE6000H-US (240V) | 2019-05-17 | 2019-05-20 | 1 | 2019-05-20 | [14 empty] | 2019-06-19 | 2019-06-21 |  | Y
Central Hudson |  | Vivint Solar Developer, LLC | CH-11503 | Kingston | Kingston | Ulster | 12401 | G | 1021 | East Kingston | N | CH-08635 | 2.3 | [13 empty] | NM | N | 10 Enphase Energy IQ6-60-X-US (240V) | 2019-05-21 | 2019-05-23 | 2 | 2019-05-23 | [14 empty] | 2019-06-28 | 2019-07-03 |  | Y
Central Hudson |  | Kasselman Solar | CH-11498 | Catskill | Athens, | Greene | 12015 | G | 2002 | North Catskill | N |  | 6.48 | [13 empty] | NM | N | 27 Enphase Energy IQ7-60-x-US (240V) | 2019-05-09 | 2019-05-20 | 7 | 2019-05-20 | [14 empty] | 2019-06-10 | 2019-06-12 |  | Y
Central Hudson |  | Kasselman Solar | CH-11499 | Catskill | Coxsackie | Greene | 12051 | G | 1076 | Coxsackie | N |  | 15.2 | [13 empty] | NM | N | 2 SolarEdge Technologies SE7600A-US (240V) | 2019-05-20 | 2019-05-28 | 5 | 2019-05-28 | [14 empty] | 2019-08-14 | 2019-08-21 |  | Y
Central Hudson |  | PlugPV, LLC | CH-11500 | Newburgh | New Paltz | Ulster | 12561 | G | 5021 | Ohioville | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2019-05-09 | 2019-05-17 | 6 | 2019-05-17 | [14 empty] | 2019-06-12 | 2019-06-12 |  | Y
Central Hudson |  | New York State Solar Farm | CH-11506 | Fishkill | Garrison | Putnam | 10524 | G | 8086 | Tioronda | N | CH-11035 | 1.28 | [13 empty] | NM | N | 4 SunPower SPR-E20-327-E-AC (240V) | 2019-05-10 | 2019-05-17 | 5 | 2019-05-17 | [14 empty] | 2019-06-03 | 2019-06-04 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-11505 | Kingston | Saugerties | Ulster | 12477 | G | 3014 | Woodstock | N |  | 7.68 | [13 empty] | NM | N | 32 Enphase Energy IQ7-60-x-US (240V) | 2019-05-10 | 2019-05-17 | 5 | 2019-05-17 | [14 empty] | 2019-08-06 | 2019-08-06 |  | Y
Central Hudson |  | New York State Solar Farm | CH-11507 | Newburgh | New Paltz | Ulster | 12561 | G | 5023 | Ohioville | N |  | 6.4 | [13 empty] | NM | N | 20 SunPower SPR-X22-360-E-AC (240V) | 2019-05-10 | 2019-05-20 | 6 | 2019-05-20 | [8 empty] | 350 | 350 |  | 2019-06-04 | 2019-06-04 | 2019-06-11 | 2019-06-17 | 2019-06-19 |  | Y
Central Hudson |  | Kasselman Solar | CH-11504 | Kingston | Shokan | Ulster | 12481 | G | 3011 | Woodstock | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2019-05-10 | 2019-05-20 | 6 | 2019-05-20 | [14 empty] | 2019-06-26 | 2019-07-02 |  | Y
Central Hudson |  | Suncommon | CH-11511 | Poughkeepsie | Staatsburg | Dutchess | 12580 | G | 7041 | Staatsburg | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2019-05-15 | 2019-05-20 | 3 | 2019-05-20 | [14 empty] | 2019-06-13 | 2019-06-17 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-11510 | Newburgh | Newburgh |  | 12550 | G | 4015 | West Balmville | N |  | 15.2 | [13 empty] | NM | N | 2 SolarEdge Technologies SE7600A-US (240V) | 2019-05-13 | 2019-05-20 | 5 | 2019-05-20 | [14 empty] | 2019-05-20 | 2019-05-31 |  | W
Central Hudson |  | Empire Solar Solutions | CH-11513 | Kingston | Lk Katrine | Ulster | 12449 | G | 2016 | Lincoln Park | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000 (240V) | 2019-05-13 | 2019-05-20 | 5 | 2019-05-20 | [14 empty] | 2019-05-20 | 2019-05-22 |  | Y
Central Hudson |  | PlugPV LLC | CH-11508 | Newburgh | Wallkill |  | 12589 | G | 4011 | West Balmville | TBD |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2019-05-13 | 2019-05-20 | 5 | 2019-05-20 | [17 empty] | W
Central Hudson |  | Suncommon | CH-11512 | Poughkeepsie | Pine Plns | Dutchess | 12567 | G | 7091 | Pulvers Corners | N | CH-02295 | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000 (240V) | 2019-05-13 | 2019-05-20 | 5 | 2019-05-20 | [14 empty] | 2019-06-26 | 2019-06-28 |  | Y
Central Hudson |  | PlugPV, LLC | CH-11514 | Newburgh | New Paltz | Ulster | 12561 | G | 5021 | Ohioville | N |  | 13.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) 1 SolarEdge Technologies SE7600H-US (240V) | 2019-05-13 | 2019-05-20 | 5 | 2019-05-20 | [14 empty] | 2019-06-12 | 2019-06-12 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-11509 | Kingston | Ellenvl | Ulster | 12428 | G | 3078 | Greenfield Rd | N |  | 10 | [13 empty] | NM | N | 40 Enphase Energy IQ7-60-x-US (240V) | 2019-05-13 | 2019-05-20 | 5 | 2019-05-20 | [14 empty] | 2019-06-28 | 2019-07-08 |  | Y
Central Hudson |  | AEC Solar | CH-11515 | Newburgh | Gardiner | Ulster | 12525 | G | 5031 | Galeville | N |  | 6.42 | [13 empty] | NM | N | 20 SunPower SPR-X22-360-D-AC (240V) [SI1] | 2019-05-21 | 2019-05-23 | 2 | 2019-05-23 | [14 empty] | 2019-09-10 | 2019-09-10 |  | Y
Central Hudson |  | PlugPV LLC | CH-11516 | Newburgh | Highland | Ulster | 12528 | G | 5083 | Highland | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2019-05-20 | 2019-05-23 | 3 | 2019-05-23 | [14 empty] | 2019-07-02 | 2019-07-08 |  | Y
Central Hudson |  | Sunrun, Inc. | CH-11523 | Newburgh | Newburgh | Orange | 12550 | G | 4023 | Coldenham | N |  | 8 | [13 empty] | NM | N | 1 Ningbo Ginlong Technologies Solis-1P4K-4G-US (240V) 1 Ningbo Ginlong Technologies Solis-1P4K-4G-US (240V) | 2019-05-15 | 2019-05-20 | 3 | 2019-05-20 | [14 empty] | 2019-06-21 | 2019-06-25 |  | Y
Central Hudson |  | Suncommon | CH-11522 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 7041 | Staatsburg | Y | CH-11039 |  | 10 | [12 empty] | NM | N | 2TeslaAC Powerwall 2.0 | 2019-05-15 | 2019-05-20 | 3 | 2019-05-20 | [14 empty] | 2019-06-05 | 2019-06-05 |  | Y
Central Hudson |  | Bright Planet Solar | CH-11517 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8052 | North Chelsea | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2019-05-15 | 2019-05-20 | 3 | 2019-05-20 | [14 empty] | 2019-09-11 | 2019-09-16 |  | Y
Central Hudson |  | New York State Solar Farm | CH-11521 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8094 | Fishkill Plains | N |  | 7.04 | [13 empty] | NM | N | 22 SunPower SPR-X22-360-E-AC (240V) | 2019-05-15 | 2019-05-20 | 3 | 2019-05-20 | [14 empty] | 2019-06-06 | 2019-06-10 |  | Y
Central Hudson |  | Solar Generation | CH-11518 | Kingston | Kingston | Ulster | 12401 | G | 2094 | Hurley Ave | N |  | 9 | [13 empty] | NM | N | 28 SunPower SPR-X22-360-C-AC (240V) | 2019-05-15 | 2019-05-20 | 3 | 2019-05-20 | [14 empty] | 2019-06-19 | 2019-06-21 |  | Y
Central Hudson |  | Solar Generation | CH-11519 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7061 | Milan | N |  | 7.6 | [13 empty] | NM | N | 1 Pika Energy X7602 (240V) | 2019-05-15 | 2019-05-22 | 5 | 2019-05-22 | [14 empty] | 2019-07-29 | 2019-08-05 |  | Y
Central Hudson |  | SRE Solar Origination 1, LLC | CH-11520 | Kingston | Stone Ridge |  | 12484 | G | 3024 | High Falls | N |  | 1500 | [13 empty] | CDG | Y | 1Power ElectronicsHEMK FS2000K | 2019-06-04 | 2019-06-17 | 9 | 2019-06-17 | 2019-06-17 | 2019-07-09 | 15 | 2019-07-30 | 2019-08-12 | 2019-11-05 | 60 | 14533.17 | 294613.75 |  | 2020-03-19 | [5 empty] | 2020-11-05 | W | Y
Central Hudson |  | Trinity Solar | CH-11525 | Newburgh | Rock Tvrn | Orange | 12575 | G | 4097 | Bethlehem Rd | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000H-US (240V) | 2019-05-16 | 2019-05-20 | 2 | 2019-05-20 | [14 empty] | 2019-06-26 | 2019-06-28 |  | Y
Central Hudson |  | Apex Solar Power | CH-11526 | Catskill | Ravena | Albany | 12143 | G | 1082 | New Baltimore | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000H-US (240V) | 2019-05-20 | 2019-05-23 | 3 | 2019-05-23 | [14 empty] | 2019-06-18 | 2019-06-24 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-11524 | Newburgh | New Windsor | Orange | 12553 | G | 4094 | Bethlehem Rd | N |  | 8.9 | [13 empty] | NM | N | 37 Enphase Energy IQ7-60-x-US (240V) | 2019-05-16 | 2019-05-20 | 2 | 2019-05-20 | [14 empty] | 2019-06-05 | 2019-06-10 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-11527 | Fishkill | Beacon | Dutchess | 12508 | G | 8087 | Tioronda | N | CH-23242 | 3 | [13 empty] | NM | N | 12 Enphase Energy IQ7-60-x-US (240V) | 2019-05-16 | 2019-05-20 | 2 | 2019-05-20 | [14 empty] | 2019-06-11 | 2019-06-11 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-11528 | Newburgh | Newburgh |  | 12550 | G | 4023 | Coldenham | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000 (240V) | 2019-05-17 | 2019-05-20 | 1 | 2019-05-20 | [14 empty] | 2019-05-30 | 2019-05-31 |  | W
Central Hudson |  | National Solar Group | CH-11469 | Kingston | Saugerties |  | 12477 | G | 3002 | Saugerties | N |  | 5000 | [13 empty] | CDG | N | 40 Sungrow Power Supply SG125HV (600V) [SI1] | 2019-06-11 | 2019-06-20 | 7 | 2019-06-20 | 2019-06-20 | 2019-07-12 | 15 | [14 empty] | W
Central Hudson |  | US Energy Concierge, Inc. | CH-11531 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8056 | North Chelsea | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2019-06-03 | 2019-06-04 | 1 | 2019-06-04 | [14 empty] | 2019-10-09 | 2019-10-10 |  | Y
Central Hudson |  | US Energy Concierge, Inc. | CH-11530 | Fishkill | Garrison | Putnam | 10524 | G | 8086 | Tioronda | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2019-06-03 | 2019-06-05 | 2 | 2019-06-05 | [14 empty] | 2019-10-12 | 2019-10-14 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-11529 | Newburgh | New Windsor | Orange | 12553 | G | 4095 | Bethlehem Rd | N |  | 4.5 | [13 empty] | NM | N | 18 Enphase Energy IQ7-60-x-US (240V) | 2019-05-17 | 2019-05-20 | 1 | 2019-05-20 | [14 empty] | 2019-07-12 | 2019-07-15 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-11536 | Newburgh | Newburgh | Orange | 12550 | G | 4011 | West Balmville | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE 11400A-US (240V) | 2019-05-20 | 2019-05-23 | 3 | 2019-05-23 | [14 empty] | 2019-06-21 | 2019-06-25 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-11535 | Newburgh | Maybrook | Orange | 12543 | G | 4026 | Coldenham | N |  | 3.8 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3800 (240V) | 2019-05-20 | 2019-05-23 | 3 | 2019-05-23 | [14 empty] | 2019-07-11 | 2019-07-15 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-11532 | Fishkill | Beacon |  | 12508 | G | 8085 | Tioronda | N |  | 4 | [13 empty] | NM | N | 16 Enphase Energy IQ7-60-x-US (240V) | 2019-05-20 | 2019-05-22 | 2 | 2019-05-22 | [17 empty] | W
Central Hudson |  | Empire Solar Solutions | CH-11534 | Kingston | Accord | Ulster | 12404 | G | 3082 | Kerhonkson | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600A-US (240V) | 2019-05-20 | 2019-05-23 | 3 | 2019-05-23 | [14 empty] | 2019-06-18 | 2019-06-24 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-11533 | Newburgh | Montgomery | Orange | 12549 | G | 5073 | Montgomery | N |  | 5.5 | [13 empty] | NM | N | 22 Enphase Energy IQ7-60-x-US (240V) | 2019-05-20 | 2019-05-22 | 2 | 2019-05-22 | [14 empty] | 2019-07-03 | 2019-07-05 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-11537 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8043 | Myers Corners | N |  | 5.75 | [13 empty] | NM | N | 23 Enphase Energy IQ7-60-x-US (240V) | 2019-05-21 | 2019-05-23 | 2 | 2019-05-23 | [14 empty] | 2019-06-26 | 2019-06-28 |  | Y
Central Hudson |  | PlugPV LLC | CH-11539 | Newburgh | Rock Tvrn | Orange | 12575 | G | 4097 | Bethlehem Rd | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000H-US (240V) | 2019-05-22 | 2019-05-23 | 1 | 2019-05-23 | [14 empty] | 2019-07-02 | 2019-07-05 |  | Y
Central Hudson |  | SolarCity DBA Tesla Energy | CH-11542 | Catskill | Saugerties | Ulster | 12477 | G | 2001 | North Catskill | N |  | 3.8 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3800H-US (240V) [SI1] | 2019-05-23 | 2019-05-28 | 2 | 2019-05-28 | [14 empty] | 2019-05-30 | 2019-05-31 |  | Y
Central Hudson |  | Solar Generation | CH-11540 | Newburgh | Cornwall | Orange | 12518 | G | 4041 | Union Ave | N | CH-09666 | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2019-05-23 | 2019-05-28 | 2 | 2019-05-28 | [17 empty] | W
Central Hudson |  | Empire Solar Solutions | CH-11541 | Kingston | Shokan | Ulster | 12481 | G | 3011 | Woodstock | N |  | 15.2 | [13 empty] | NM | N | 2 SolarEdge Technologies SE7600A-US (240V) | 2019-05-23 | 2019-05-28 | 2 | 2019-05-28 | [14 empty] | 2019-06-19 | 2019-06-21 |  | Y
Central Hudson |  | Bright Planet Solar | CH-11543 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6093 | Manchester | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE11400H-US (240V) | 2019-05-24 | 2019-05-28 | 1 | 2019-05-28 | [14 empty] | 2019-09-24 | 2019-09-24 |  | Y
Central Hudson |  | American Solar Partners | CH-11544 | Newburgh | Newburgh |  | 12550 | G | 4024 | Coldenham | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2019-06-03 | 2019-06-05 | 2 | 2019-06-05 | [17 empty] | W
Central Hudson |  | Sunrun Installation Services, Inc. | CH-11548 | Newburgh | Cornwall-Hdsn | Orange | 12520 | G | 4043 | Union Ave | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000H-US (240V) | 2019-05-28 | 2019-06-03 | 4 | 2019-06-03 | [14 empty] | 2019-06-18 | 2019-06-19 |  | Y
Central Hudson |  | Solar Generation | CH-11546 | Newburgh | Cornwall |  | 12518 | G | 4041 | Union Ave | N |  | 11.04 | [13 empty] | NM | N | 46 SunPower SPR-240E-WHT-U-ACPV (240V) | 2019-05-28 | 2019-05-29 | 1 | 2019-05-29 | [17 empty] | W
Central Hudson |  | Suncommon | CH-11545 | Poughkeepsie | Staatsburg | Dutchess | 12580 | G | 7041 | Staatsburg | N | CH-01757 | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000 (240V) | 2019-06-05 | 2019-06-11 | 4 | 2019-06-11 | [14 empty] | 2019-07-15 | 2019-07-18 |  | Y
Central Hudson |  | Lighthouse Solar | CH-11547 | Kingston | Accord | Ulster | 12404 | G | 3082 | Kerhonkson | N |  | 18.85 | [13 empty] | NM | N | 35 Enphase Energy IQ7PLUS-72-x-ACM-US (240V) [SI1] 30 Enphase Energy IQ7PLUS-72-x-US (240V) [SI1] | 2019-05-28 | 2019-05-29 | 1 | 2019-05-29 | [14 empty] | 2019-08-20 | 2019-08-22 |  | Y
Central Hudson |  | Bright Planet Solar | CH-11552 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6011 | Sand Dock | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2019-05-29 | 2019-06-03 | 3 | 2019-06-03 | [14 empty] | 2019-11-06 | 2019-11-07 |  | Y
Central Hudson |  | PlugPV LLC | CH-11550 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6051 | Todd Hill | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2019-05-29 | 2019-06-03 | 3 | 2019-06-03 | [14 empty] | 2019-06-24 | 2019-06-25 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-11549 | Kingston | Accord | Ulster | 12404 | G | 3024 | High Falls | N |  | 3.8 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3800 (240V) | 2019-05-29 | 2019-06-03 | 3 | 2019-06-03 | [14 empty] | 2019-07-09 | 2019-07-11 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-11551 | Kingston | Kingston | Ulster | 12401 | G | 1003 | Jansen Ave | N |  | 5.22 | [13 empty] | NM | N | 18 Enphase Energy IQ7PLUS-72-x-US (240V) | 2019-05-29 | 2019-06-03 | 3 | 2019-06-03 | [14 empty] | 2019-08-27 | 2019-09-04 |  | Y
Central Hudson |  | PlugPV LLC | CH-11553 | Poughkeepsie | Pleasant Valley | Dutchess | 12569 | G | 6051 | Todd Hill | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2019-05-30 | 2019-06-03 | 2 | 2019-06-03 | [14 empty] | 2019-06-26 | 2019-06-28 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-11554 | Fishkill | Stormvl | Dutchess | 12582 | G | 8095 | Fishkill Plains | N |  | 8.555 | [13 empty] | NM | N | 29 Enphase Energy IQ7PLUS-72-x-US (240V) | 2019-05-30 | 2019-06-03 | 2 | 2019-06-03 | [14 empty] | 2019-07-15 | 2019-07-18 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-11556 | Poughkeepsie | Millerton | Dutchess | 12546 | G | 7081 | Millerton | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000 (240V) | 2019-05-31 | 2019-06-04 | 2 | 2019-06-04 | [14 empty] | 2019-06-26 | 2019-06-28 |  | Y
Central Hudson |  | Suncommon | CH-11555 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7058 | Rhinebeck | N |  | 36 | [13 empty] | NM | N | 1 Delta Electronics M36U_XXX (480V) | 2019-08-28 | 2019-09-12 | 10 | 2019-09-12 | [14 empty] | 2021-09-20 | 2021-09-27 |  | Y
Central Hudson |  | Lighthouse Solar | CH-11558 | Fishkill | Cold Spg | Putnam | 10516 | G | 8087 | Tioronda | N |  | 13.05 | [13 empty] | NM | N | 45 Enphase Energy IQ7PLUS-72-x-US (240V) [SI1] | 2019-06-04 | 2019-06-10 | 4 | 2019-06-10 | [14 empty] | 2019-08-19 | 2019-08-22 |  | Y
Central Hudson |  | Green Hybrid Energy Solutions, Inc. | CH-11559 | Fishkill | Hopewell Junction | Dutchess | 12533 | G | 8093 | Fishkill Plains | N |  | 15.2 | [13 empty] | NM | N | 2 SolarEdge Technologies SE7600H-US (240V) | 2019-05-31 | 2019-06-04 | 2 | 2019-06-04 | [14 empty] | 2019-08-01 | 2019-08-06 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-11557 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 6074 | East Park | N |  | 3.8 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3800 (240V) | 2019-05-31 | 2019-06-04 | 2 | 2019-06-04 | [14 empty] | 2019-07-03 | 2019-07-05 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-11564 | Kingston | Woodstock | Ulster | 12498 | G | 3013 | Woodstock | N |  | 3.7 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3800H-US (240V) | 2019-06-03 | 2019-06-05 | 2 | 2019-06-05 | [14 empty] | 2019-07-09 | 2019-07-10 |  | Y
Central Hudson |  | Solar Generation | CH-11562 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7054 | Rhinebeck | N |  | 10 | [13 empty] | NM | N | 2 SMA America SB5000US (240V) 1SolarEdgeSE10000H-US | 2019-06-03 | 2019-06-17 | 10 | 2019-06-17 | [8 empty] | 350 | 350 |  | 2019-07-19 | 2019-07-19 | 2019-08-07 | 2019-11-26 | 2019-11-27 |  | Y
Central Hudson |  | Solar Generation | CH-11561 | Kingston | Bearsvl | Ulster | 12409 | G | 3012 | Woodstock | N | CH-11561 | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2019-06-03 | 2019-06-05 | 2 | 2019-06-05 | [14 empty] | 2019-11-01 | 2019-11-08 |  | Y
Central Hudson |  | Solar Generation | CH-11560 | Kingston | Woodstock | Ulster | 12498 | G | 3014 | Woodstock | N |  | 7.7 | [13 empty] | NM | N | 1 SMA America SB7700TL-US-22 (240V) | 2019-06-03 | 2019-06-04 | 1 | 2019-06-04 | [14 empty] | 2019-10-15 | 2019-10-15 |  | Y
Central Hudson |  | PlugPV LLC | CH-11563 | Catskill | Greenvl | Greene | 12083 | G | 2061 | Freehold | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE11400H-US (240V) | 2019-06-03 | 2019-06-05 | 2 | 2019-06-05 | [14 empty] | 2019-07-09 | 2019-07-11 |  | Y
Central Hudson |  | Kasselman Solar | CH-11567 | Catskill | Tannersvl | Greene | 12485 | G | 2385 | Lawrenceville | N |  | 3.8 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3800H-US (240V) | 2019-06-04 | 2019-06-10 | 4 | 2019-06-10 | [14 empty] | 2019-07-09 | 2019-07-15 |  | Y
Central Hudson |  | New York State Solar Farm | CH-11569 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6068 | Inwood Ave | N |  | 10.24 | [13 empty] | NM | N | 32 SunPower SPR-X22-370-E-AC (240V) | 2019-06-10 | 2019-06-11 | 1 | 2019-06-11 | [14 empty] | 2019-07-12 | 2019-07-15 |  | Y
Central Hudson |  | Vivint Solar Developer, LLC | CH-11568 | Fishkill | Fishkill | Dutchess | 12524 | G | 8094 | Fishkill Plains | N |  | 8.74 | [13 empty] | NM | N | 38 Enphase Energy IQ6-60-X-US (240V) | 2019-06-10 | 2019-06-11 | 1 | 2019-06-11 | [14 empty] | 2019-09-20 | 2019-09-20 |  | Y
Central Hudson |  | SRE Solar Origination 2, LLC | CH-11565 | Kingston | Ulster Park |  | 12487 | G | 2016 | Lincoln Park | N |  | 2000 | [13 empty] | CDG | Y | 1Power ElectronicsHEMK F2000K | 2019-06-04 | 2019-06-17 | 9 | 2019-06-17 | 2019-06-17 | 2019-07-09 | 15 | 2019-07-30 | 2019-08-13 | 2019-11-06 | 60 | 9548.87 | 2809791.25 | [7 empty] | 2020-06-03 | W
Central Hudson |  | Infinity Solar Systems | CH-11566 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8092 | Fishkill Plains | N |  | 7.2 | [13 empty] | NM | N | 30 Enphase Energy IQ7-60-x-US (240V) | 2019-06-04 | 2019-06-06 | 2 | 2019-06-06 | [14 empty] | 2020-01-06 | 2020-01-07 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-11570 | Newburgh | Highland | Ulster | 12528 | G | 5083 | Highland | N |  | 6.38 | [13 empty] | NM | N | 22 Enphase Energy IQ7PLUS-72-x-US (240V) | 2019-06-05 | 2019-06-10 | 3 | 2019-06-10 | [14 empty] | 2019-08-07 | 2019-08-12 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-11574 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 6074 | East Park | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2019-07-12 | 2019-07-23 | 7 | 2019-07-23 | [14 empty] | 2019-09-18 | 2019-09-19 |  | Y
Central Hudson |  | New York State Solar Farm | CH-11573 | Newburgh | Marlboro | Ulster | 12542 | G | 5001 | Marlboro | N |  | 9.6 | [13 empty] | NM | N | 30 SunPower SPR-X22-360-E-AC (240V) | 2019-06-05 | 2019-06-11 | 4 | 2019-06-11 | [8 empty] | 350 | 350 |  | 2019-06-14 | 2019-06-14 | 2019-06-27 | 2019-07-01 | 2019-07-03 |  | Y
Central Hudson |  | Solar Generation | CH-11571 | Kingston | Glenford | Ulster | 12433 | G | 3013 | Woodstock | N |  | 15.2 | [13 empty] | NM | N | 2 SolarEdge Technologies SE7600H-US (240V) | 2019-06-10 | 2019-06-11 | 1 | 2019-06-11 | [8 empty] | 350 | 350 |  | 2019-06-17 | 2019-06-17 | 2019-08-14 | 2020-04-08 | 2020-04-13 |  | Y
Central Hudson |  | Suncommon | CH-11572 | Newburgh | New Paltz | Ulster | 12561 | G | 5031 | Galeville | Y | CH-02189 |  | 15 | [12 empty] | NM | N | 3TeslaAC Powerwall 2.0 | 2019-06-05 | 2019-06-11 | 4 | 2019-06-11 | [14 empty] | 2019-11-18 | 2019-11-18 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-11575 | Newburgh | Campbell Hall | Orange | 10916 | G | 5052 | Maybrook | N | CH-11575 | 8.7 | [13 empty] | NM | N | 30 Enphase Energy IQ7PLUS-72-x-US (240V) | 2019-06-06 | 2019-06-11 | 3 | 2019-06-11 | [14 empty] | 2019-07-12 | 2019-07-15 |  | Y
Central Hudson |  | PlugPV LLC | CH-11577 | Fishkill | Fishkill | Dutchess | 12524 | G | 8016 | Forgebrook | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2019-06-07 | 2019-06-11 | 2 | 2019-06-11 | [14 empty] | 2019-07-30 | 2019-08-05 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-11579 | Poughkeepsie | Tivoli | Dutchess | 12583 | G | 7062 | Milan | N |  | 6 | [13 empty] | NM | N | 1 Ningbo Ginlong Technologies Solis-1P6K-4G-US | 2019-06-07 | 2019-06-11 | 2 | 2019-06-11 | [14 empty] | 2019-06-28 | 2019-07-03 |  | Y
Central Hudson |  | PlugPV LLC | CH-11576 | Poughkeepsie | Lagrangevl | Dutchess | 12540 | G | 6055 | Todd Hill | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2019-06-07 | 2019-06-11 | 2 | 2019-06-11 | [14 empty] | 2019-07-30 | 2019-08-12 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-11578 | Newburgh | Montgomery | Orange | 12549 | G | 5072 | Montgomery | N |  | 7.6 | [13 empty] | NM | N | 1 Ningbo Ginlong Technologies Solis-1P7.6K-4G-US | 2019-06-07 | 2019-06-11 | 2 | 2019-06-11 | [14 empty] | 2019-08-20 | 2019-08-22 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-11581 | Kingston | Rosendale | Ulster | 12472 | G | 3022 | High Falls | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE 10000A-US (240V) | 2019-06-10 | 2019-06-11 | 1 | 2019-06-11 | [14 empty] | 2019-07-26 | 2019-08-02 |  | Y
Central Hudson |  | Trinity Solar | CH-11580 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8046 | Myers Corners | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2019-06-10 | 2019-06-11 | 1 | 2019-06-11 | [14 empty] | 2019-07-18 | 2019-07-23 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-11582 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N | CH-11582 | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600A-US (240V) [SI1] | 2019-06-10 | 2019-06-11 | 1 | 2019-06-11 | [14 empty] | 2019-06-13 | 2019-06-19 |  | Y
Central Hudson |  | MOMENTUM SOLAR | CH-11583 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8095 | Fishkill Plains | N |  | 7.2 | [13 empty] | NM | N | 25 Enphase Energy IQ7PLUS-72-x-US (240V) | 2019-06-11 | 2019-06-11 | 0 | 2019-06-11 | [14 empty] | 2019-07-03 | 2019-07-15 |  | Y
Central Hudson |  | Bright Planet Solar | CH-11584 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6011 | Sand Dock | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2019-08-20 | 2019-09-04 | 10 | 2019-09-04 | [14 empty] | 2019-12-23 | 2020-01-02 |  | Y
Central Hudson |  | PlugPV LLC | CH-11586 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8092 | Fishkill Plains | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2019-06-12 | 2019-06-17 | 3 | 2019-06-17 | [14 empty] | 2019-07-16 | 2019-07-18 |  | Y
Central Hudson |  | Suncommon | CH-11587 | Kingston | Stone Ridge | Ulster | 12484 | G | 3023 | High Falls | Y | CH-02383 |  | 5 | [12 empty] | NM | N | 1TeslaAC Powerwall 2.0 | 2019-06-12 | 2019-06-18 | 4 | 2019-06-18 | [14 empty] | 2019-10-29 | 2019-11-06 |  | Y
Central Hudson |  | PlugPV LLC | CH-11585 | Poughkeepsie | Clinton Cors | Dutchess | 12514 | G | 7071 | Stanfordville | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000H-US (240V) | 2019-06-17 | 2019-06-20 | 3 | 2019-06-20 | [14 empty] | 2019-07-16 | 2019-07-18 |  | Y
Central Hudson |  | PlugPV LLC | CH-11588 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8094 | Fishkill Plains | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2019-06-12 | 2019-06-18 | 4 | 2019-06-18 | [14 empty] | 2019-07-29 | 2019-08-02 |  | Y
Central Hudson |  | Tesla Energy Operations | CH-11589 | Kingston | Accord | Ulster | 12404 | G | 3081 | Kerhonkson | N |  | 7.6 | [13 empty] | NM | N | 1 Delta Electronics SOLIVIA 7.6 NA G4 TL (240V) | 2019-06-12 | 2019-06-18 | 4 | 2019-06-18 | [14 empty] | 2019-08-09 | 2019-08-14 |  | Y
Central Hudson |  | Kasselman Solar | CH-11590 | Fishkill | Beacon | Dutchess | 12508 | G | 8017 | Forgebrook | N | CH-11171 | 0.96 | [13 empty] | NM | N | 4 Enphase Energy IQ7-60-x-US (240V) | 2019-07-01 | 2019-07-05 | 3 | 2019-07-05 | [14 empty] | 2019-08-06 | 2019-08-09 |  | Y
Central Hudson |  | New York State Solar Farm | CH-11595 | Newburgh | Newburgh | Orange | 12550 | G | 4011 | West Balmville | N |  | 5.44 | [13 empty] | NM | N | 17 SunPower SPR-X21-350-BLK-E-AC (240V) | 2019-06-14 | 2019-06-19 | 3 | 2019-06-19 | [14 empty] | 2019-10-11 | 2019-10-15 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-11593 | Newburgh | New Windsor | Orange | 12553 | G | 4094 | Bethlehem Rd | N |  | 4.8 | [13 empty] | NM | N | 20 Enphase Energy IQ7-60-x-US (240V) | 2019-06-14 | 2019-06-18 | 2 | 2019-06-18 | [14 empty] | 2019-08-07 | 2019-08-12 |  | Y
Central Hudson |  | PlugPV LLC | CH-11594 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8096 | Fishkill Plains | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE11400H-US (240V) | 2019-06-18 | 2019-06-20 | 2 | 2019-06-20 | [14 empty] | 2019-07-29 | 2019-08-02 |  | Y
Central Hudson |  | Tesla Energy Operations | CH-11591 | Newburgh | Newburgh | Orange | 12550 | G | 5041 | East Walden | Y | CH-10793 |  | 5 | [12 empty] | NM | N | 1TeslaAC Powerwall 2.0 | 2019-06-18 | 2019-06-21 | 3 | 2019-06-21 | [14 empty] | 2019-07-11 | 2019-07-15 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-11592 | Catskill | Catskill | Greene | 12414 | G | 2004 | North Catskill | N |  | 3 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3000 (240V) | 2019-06-14 | 2019-06-18 | 2 | 2019-06-18 | [14 empty] | 2019-08-21 | 2019-08-22 |  | Y
Central Hudson |  | Tesla Energy Operations, Inc | CH-11599 | Newburgh | Mountainvl | Orange | 10953 | G | 4095 | Bethlehem Rd | Y | CH-05085 |  | 15 | [12 empty] | NM | N | 3TeslaAC Powerwall 2.0 | 2019-07-01 | 2019-07-05 | 3 | 2019-07-05 | [14 empty] | 2020-04-13 | 2020-04-13 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-11598 | Newburgh | Newburgh | Orange | 12550 | G | 4023 | Coldenham | N |  | 5.52 | [13 empty] | NM | N | 23 Enphase Energy IQ7-60-x-US (240V) | 2019-06-17 | 2019-06-20 | 3 | 2019-06-20 | [14 empty] | 2019-08-06 | 2019-08-06 |  | Y
Central Hudson |  | plugPV LLC | CH-11596 | Newburgh | Washingtonvl | Orange | 10992 | G | 4097 | Bethlehem Rd | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2019-06-17 | 2019-06-19 | 2 | 2019-06-19 | [14 empty] | 2019-07-30 | 2019-08-02 |  | Y
Central Hudson |  | Hudson Valley Wind & Solar LLC | CH-11597 | Poughkeepsie | Pine Plains | Dutchess | 12567 | G | 7091 | Pulvers Corners | N |  |  |  | 12 | [11 empty] | NM | N | 1Bergey Wind PowerPSII12 | 2019-09-26 | 2019-09-27 | 1 | 2019-09-27 | [14 empty] | 2019-12-04 | 2019-12-04 |  | Y
Central Hudson |  | Bright Planet Solar | CH-11616 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6045 | Spackenkill | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3800H-US (240V) | 2019-06-18 | 2019-06-20 | 2 | 2019-06-20 | [14 empty] | 2019-11-20 | 2019-11-21 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-11614 | Newburgh | Campbell Hall | Orange | 10916 | G | 5051 | Maybrook | N |  | 12.6 | [13 empty] | NM | N | 1 Ningbo Ginlong Technologies Solis-1P7.6K-4G-US 1 Ningbo Ginlong Technologies Solis-1P5K-4G-US (240V) | 2019-06-18 | 2019-06-20 | 2 | 2019-06-20 | [14 empty] | 2019-08-27 | 2019-09-04 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-11608 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8043 | Myers Corners | N |  | 5.52 | [13 empty] | NM | N | 23 Enphase Energy IQ7-60-x-US (240V) | 2019-06-18 | 2019-06-20 | 2 | 2019-06-20 | [14 empty] | 2019-08-07 | 2019-08-12 |  | Y
Central Hudson |  | PlugPV LLC | CH-11607 | Catskill | Leeds | Greene | 12451 | G | 2005 | North Catskill | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2019-06-18 | 2019-06-20 | 2 | 2019-06-20 | [14 empty] | 2019-07-19 | 2019-07-25 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-11606 | Poughkeepsie | Pleasant Valley | Dutchess | 12569 | G | 7025 | Tinkertown | N |  | 3.84 | [13 empty] | NM | N | 16 Enphase Energy IQ7-60-x-US (240V) | 2019-06-18 | 2019-06-20 | 2 | 2019-06-20 | [14 empty] | 2019-08-07 | 2019-08-12 |  | Y
Central Hudson |  | Solar Generation | CH-11611 | Kingston | Woodstock | Ulster | 12498 | G | 3014 | Woodstock | N |  | 7.6 | [13 empty] | NM | N | 1 Pika Energy X7602 (240V) | 2019-06-18 | 2019-07-01 | 9 | 2019-07-01 | [14 empty] | 2019-07-11 | 2019-07-15 |  | Y
Central Hudson |  | Apex Solar Power | CH-11610 | Newburgh | New Paltz | Ulster | 12561 | G | 5011 | Modena | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2019-06-18 | 2019-06-20 | 2 | 2019-06-20 | [14 empty] | 2019-07-17 | 2019-07-23 |  | Y
Central Hudson |  | Apex Solar Power | CH-11609 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8072 | Shenandoah | N |  | 12.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) 1 SolarEdge Technologies SE5000H-US (240V) | 2019-06-20 | 2019-06-24 | 2 | 2019-06-24 | [8 empty] | 350 | 350 |  | 2019-07-16 | 2019-07-16 | 2019-09-05 | 2019-11-19 | 2019-11-19 |  | Y
Central Hudson |  | Red Hook Solar Corp | CH-11612 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7056 | Rhinebeck | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) [SI1] | 2019-06-18 | 2019-06-20 | 2 | 2019-06-20 | [14 empty] | 2019-07-31 | 2019-08-05 |  | Y
Central Hudson |  | Integrity Solar Solutions | CH-11615 | Newburgh | Newburgh | Orange | 12550 | G | 5041 | East Walden | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2019-06-18 | 2019-06-25 | 5 | 2019-06-25 | [14 empty] | 2019-08-09 | 2019-08-14 |  | Y
Central Hudson |  | Bright Planet Solar | CH-11617 | Poughkeepsie | Poughkeepsie |  | 12601 | G | 6011 | Sand Dock | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) [SI1] | 2019-06-19 | 2019-06-21 | 2 | 2019-06-21 | [17 empty] | W
Central Hudson |  | Bright Planet Solar | CH-11618 | Fishkill | Wappingrs Fls |  | 12590 | G | 8023 | Knapps Corners | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) [SI1] | 2019-06-19 | 2019-06-24 | 3 | 2019-06-24 | [17 empty] | W
Central Hudson |  | Sunrun, Inc. | CH-11620 | Newburgh | Milton | Ulster | 12547 | G | 5083 | Highland | N |  | 3.8 | [13 empty] | NM | N | 1 SMA America SB3.8-1SP-US-40 (240V) | 2019-06-20 | 2019-06-24 | 2 | 2019-06-24 | [14 empty] | 2019-07-09 | 2019-07-10 |  | Y
Central Hudson |  | Suncommon | CH-11619 | Poughkeepsie | Milan | Dutchess | 12571 | G | 7062 | Milan | N |  | 20 | [13 empty] | NM | N | 2 SolarEdge Technologies SE10000H-US (240V) | 2019-06-20 | 2019-07-01 | 7 | 2019-07-01 | [8 empty] | 350 | 350 |  | 2019-07-05 | 2019-07-05 | 2019-08-05 | 2019-08-12 | 2019-08-15 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-11621 | Newburgh | Cornwall | Orange | 12518 | G | 4094 | Bethlehem Rd | N |  | 5.5 | [13 empty] | NM | N | 22 Enphase Energy IQ7-60-x-US (240V) | 2019-06-21 | 2019-06-25 | 2 | 2019-06-25 | [14 empty] | 2019-09-06 | 2019-09-13 |  | Y
Central Hudson |  | Tesla Energy Operations | CH-11622 | Kingston | Lk Hill | Ulster | 12448 | G | 3012 | Woodstock | Y | CH-10778 |  | 10 | [12 empty] | NM | N | 2TeslaAC Powerwall 2.0 | 2019-06-26 | 2019-07-05 | 6 | 2019-07-05 | [14 empty] | 2019-08-16 | 2019-08-22 |  | Y
Central Hudson |  | US Energy Concierge, Inc | CH-11623 | Fishkill | Cold Spg | Putnam | 10516 | G | 8087 | Tioronda | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000 (240V) | 2019-06-24 | 2019-06-25 | 1 | 2019-06-25 | [14 empty] | 2019-11-17 | 2019-11-18 |  | Y
Central Hudson |  | Self | CH-11624 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 7024 | Tinkertown | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2019-06-24 | 2019-06-25 | 1 | 2019-06-25 | [14 empty] | 2019-08-19 | 2019-09-03 |  | Y
Central Hudson |  | Lighthouse Solar | CH-11626 | Kingston | Kerhonkson | Ulster | 12446 | G | 3082 | Kerhonkson | N |  | 16.53 | [13 empty] | NM | N | 57 Enphase Energy IQ7PLUS-72-x-US (240V) [SI1] | 2019-06-25 | 2019-06-25 | 0 | 2019-06-25 | [14 empty] | 2019-09-09 | 2019-09-13 |  | Y
Central Hudson |  | Vivint Solar Developer, LLC | CH-11625 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6094 | Manchester | N |  | 13.92 | [13 empty] | NM | N | 58 Enphase Energy IQ7-60-x-US (240V) | 2019-06-24 | 2019-06-25 | 1 | 2019-06-25 | [14 empty] | 2020-06-10 | 2020-06-10 |  | Y
Central Hudson |  | New York State Solar Farm | CH-11627 | Kingston | Stone Ridge | Ulster | 12484 | G | 3023 | High Falls | Y | CH-00354 | 3.2 | 5 | [12 empty] | NM | N | 10 SunPower SPR-E20-327-E-AC (240V) 1TeslaAC Powerwall 2.0 | 2019-06-25 | 2019-06-25 | 0 | 2019-06-25 | [14 empty] | 2019-08-23 | 2019-08-30 |  | Y
Central Hudson |  | Kasselman Solar | CH-11628 | Catskill | Hunter | Greene | 12442 | E | 2081 | Hunter | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE11400H-US (240V) | 2019-06-25 | 2019-06-28 | 3 | 2019-06-28 | [14 empty] | 2019-09-03 | 2019-09-10 |  | Y
Central Hudson |  | YSG Community Solar LLC | CH-11630 | Catskill | Hunter |  | 12442 | G | 2385 | Lawrenceville | N |  | 1100 | [13 empty] | CDG | Y | 50 Sungrow Power Supply SG60KU-M | 2019-07-12 | 2019-07-25 | 9 | 2019-07-25 | 2019-07-25 | 2019-08-15 | 15 | 2019-10-09 | 2019-11-21 | 2020-02-21 | 60 | 12250 | 191024.38 | [8 empty] | W
Central Hudson |  | YSG Community Solar, LLC | CH-11629 | Catskill | Hunter |  | 12442 | G | 2385 | Lawrenceville | N |  | 2125 | [13 empty] | CDG | Y | 14 Chint Power Systems America CPS SCH125KTL-DO/US-600 (600V) | 2019-07-12 | 2019-07-25 | 9 | 2019-07-25 | 2019-07-25 | 2019-08-15 | 15 | 2019-10-09 | 2019-11-21 | 2020-02-21 | 60 | 15626.77 | 282048.75 |  | 2020-09-23 | [5 empty] | 2022-02-07 | W | Y | 10/15/20 - Developer submitted a Moratorium Attestation Form ending 5/26/21, full payment due 11/15/21.
Central Hudson |  | Tri-State Solar Services | CH-11633 | Newburgh | Rock Tvrn | Orange | 12575 | G | 4097 | Bethlehem Rd | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000 (240V) | 2019-07-16 | 2019-07-16 | 0 | 2019-07-16 | [14 empty] | 2019-08-29 | 2019-09-06 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-11634 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8091 | Fishkill Plains | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600A-US (240V) | 2019-06-26 | 2019-07-05 | 6 | 2019-07-05 | [14 empty] | 2019-07-10 | 2019-07-11 |  | Y
Central Hudson |  | Suncommon | CH-11632 | Kingston | Ulster Park | Ulster | 12487 | G | 3041 | Sturgeon Pool | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2019-06-26 | 2019-07-05 | 6 | 2019-07-05 | [14 empty] | 2019-08-07 | 2019-08-19 |  | Y
Central Hudson |  | SolarCity DBA Tesla Energy | CH-11631 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6045 | Spackenkill | Y | CH-10552 |  | 10 | [12 empty] | NM | N | 2TeslaAC Powerwall 2.0 | 2019-07-01 | 2019-07-05 | 3 | 2019-07-05 | [14 empty] | 2019-07-08 | 2019-07-10 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-11637 | Newburgh | Clintondale | Ulster | 12515 | G | 5012 | Modena | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE 11400A-US (240V) | 2019-06-27 | 2019-07-05 | 5 | 2019-07-05 | [8 empty] | 350 | 350 |  | 2019-07-10 | 2019-07-10 | 2019-07-31 | 2019-08-06 | 2019-08-09 |  | Y
Central Hudson |  | New York State Solar Farm | CH-11636 | Catskill | Catskill | Greene | 12414 | G | 2005 | North Catskill | N |  | 9.6 | [13 empty] | NM | N | 30 SunPower SPR-X22-360-E-AC (240V) | 2019-06-27 | 2019-07-05 | 5 | 2019-07-05 | [14 empty] | 2019-07-24 | 2019-07-30 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-11635 | Fishkill | Glenham | Dutchess | 12527 | G | 8013 | Forgebrook | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE 11400A-US (240V) | 2019-06-27 | 2019-07-05 | 5 | 2019-07-05 | [8 empty] | 350 | 350 |  | 2019-07-10 | 2019-07-10 | 2019-07-11 | 2019-07-18 | 2019-07-23 |  | Y
Central Hudson |  | Solar Generation | CH-11638 | Kingston | Sundown | Sullivan | 12740 | G | 3091 | Neversink | N |  | 6 | [13 empty] | NM | N | 1 SMA America SB6000US (240V) | 2019-06-28 | 2019-07-05 | 4 | 2019-07-05 | [14 empty] | 2019-07-24 | 2019-07-26 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-11639 | Fishkill | Beacon | Dutchess | 12508 | G | 8085 | Tioronda | N |  | 3.6 | [13 empty] | NM | N | 1 Ningbo Ginlong Technologies Solis-1P3.6K-4G-US (240V) | 2019-06-28 | 2019-07-05 | 4 | 2019-07-05 | [14 empty] | 2019-09-03 | 2019-09-10 |  | Y
Central Hudson |  | Common Energy | CH-11645 | Poughkeepsie | Stanfordville | Dutchess | 12581 | G | 7072 | Stanfordville | N |  | 5000 | [13 empty] | CDG | Y | 2 SMA America SC 2500-EV-US (550V) [SI1] | 2019-07-19 | 2019-07-29 | 6 | 2019-07-29 | 2019-07-29 | 2019-08-19 | 15 | 2019-09-13 | 2019-09-25 | 2019-12-20 | 60 | 12891.51 | 181710 | 101904.53 | 2020-03-03 | 2020-08-24 | 2020-08-24 | 2021-07-26 | 2021-08-31 | 2021-08-31 | 2021-11-19 | Y | Y
Central Hudson |  | Bright Planet Solar | CH-11640 | Newburgh | Newburgh |  | 12550 | G | 4022 | Coldenham | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2019-07-11 | 2019-07-16 | 3 | 2019-07-16 | [17 empty] | W
Central Hudson |  | Bright Planet Solar | CH-11643 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6093 | Manchester | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000H-US (240V) | 2019-07-02 | 2019-07-05 | 2 | 2019-07-05 | [14 empty] | 2019-11-06 | 2019-11-20 |  | Y
Central Hudson |  | Tesla Energy | CH-11641 | Kingston | Kingston | Ulster | 12401 | G | 1021 | East Kingston | N | CH-05215 | 3.8 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3800 (240V) | 2019-07-23 | 2019-08-02 | 8 | 2019-08-02 | [14 empty] | 2019-11-04 | 2019-11-04 |  | Y
Central Hudson |  | New York State Solar Farm | CH-11642 | Kingston | Kingston |  | 12401 | G | 2015 | Lincoln Park | N |  | 60 | [13 empty] | NM | N | 2 SolarEdge Technologies SE30KUS (480V) | 2019-09-25 | 2019-10-09 | 10 | 2019-10-09 | 2019-10-09 | 2019-10-30 | 15 | [14 empty] | W
Central Hudson |  | Suncommon | CH-11648 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8093 | Fishkill Plains | N | CH-01931 | 12.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE11400H-US (240V) 3 SunPower SPR-X21-335-BLK-C-AC (240V) | 2019-07-12 | 2019-07-16 | 2 | 2019-07-16 | [14 empty] | 2019-08-06 | 2019-08-09 |  | Y
Central Hudson |  | Suncommon | CH-11647 | Kingston | Ulster Pk |  | 12487 | G | 1023 | East Kingston | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2019-07-11 | 2019-07-16 | 3 | 2019-07-16 | [17 empty] | W
Central Hudson |  | Suncommon | CH-11646 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7062 | Milan | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE11400H-US (240V) | 2019-08-06 | 2019-08-19 | 9 | 2019-08-19 | [14 empty] | 2019-10-18 | 2019-10-24 |  | Y
Central Hudson |  | Kasselman Solar | CH-11649 | Newburgh | New Paltz | Ulster | 12561 | G | 5023 | Ohioville | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE11400H-US (240V) | 2019-07-17 | 2019-07-19 | 2 | 2019-07-19 | [14 empty] | 2019-08-05 | 2019-08-06 |  | Y
Central Hudson |  | New York State Solar Farm | CH-11650 | Kingston | Accord | Ulster | 12404 | G | 3081 | Kerhonkson | N |  | 15.68 | [13 empty] | NM | N | 49 SunPower SPR-X22-360-E-AC (240V) | 2019-07-12 | 2019-07-16 | 2 | 2019-07-16 | [14 empty] | 2019-08-02 | 2019-08-07 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-11651 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8072 | Shenandoah | N |  | 10 | [13 empty] | NM | N | 1 Ningbo Ginlong Technologies Solis-1P10K-4G-US | 2019-07-29 | 2019-08-07 | 7 | 2019-08-07 | [14 empty] | 2019-09-03 | 2019-09-10 |  | Y
Central Hudson |  | PlugPV LLC | CH-11655 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8096 | Fishkill Plains | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2019-07-08 | 2019-07-15 | 5 | 2019-07-15 | [14 empty] | 2019-08-06 | 2019-08-09 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-11653 | Newburgh | New Windsor |  | 12553 | G | 4052 | Union Ave | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000A-US (240V) [SI1] | 2019-07-08 | 2019-07-15 | 5 | 2019-07-15 | [14 empty] | 2019-07-19 | 2019-07-24 |  | W
Central Hudson |  | Suncommon | CH-11658 | Kingston | Kingston | Ulster | 12401 | G | 3023 | High Falls | N |  | 22.8 | [13 empty] | NM | N | 2 SolarEdge Technologies SE11400H-US (240V) | 2019-07-17 | 2019-07-19 | 2 | 2019-07-19 | [8 empty] | 350 | 350 |  | 2019-07-25 | 2019-07-25 | 2019-10-22 | 2019-11-26 | 2019-11-26 |  | Y
Central Hudson |  | Kasselman Solar | CH-11654 | Fishkill | Beacon | Dutchess | 12508 | G | 8085 | Tioronda | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2019-07-17 | 2019-07-19 | 2 | 2019-07-19 | [14 empty] | 2019-08-12 | 2019-08-26 |  | Y
Central Hudson |  | Suncommon | CH-11652 | Fishkill | Cold Spg | Putnam | 10516 | G | 8087 | Tioronda | N |  | 20 | [13 empty] | NM | N | 2 SolarEdge Technologies SE10000H-US (240V) | 2019-07-15 | 2019-07-16 | 1 | 2019-07-16 | [14 empty] | 2019-12-09 | 2019-12-13 |  | Y
Central Hudson |  | Bright Planet Solar | CH-11656 | Poughkeepsie | Red Hook |  | 12571 | G | 7061 | Milan | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2019-07-16 | 2019-07-17 | 1 | 2019-07-17 | [17 empty] | W
Central Hudson |  | Infinity Solar Systems | CH-11657 | Newburgh | Montgomery | Orange | 12549 | G | 5072 | Montgomery | N |  | 6.25 | [13 empty] | NM | N | 25 Enphase Energy IQ7-60-x-US (240V) | 2019-07-16 | 2019-07-17 | 1 | 2019-07-17 | [14 empty] | 2019-08-28 | 2019-09-05 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-11661 | Catskill | Hannacroix | Greene | 12087 | G | 2002 | North Catskill | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE 11400A-US (240V) | 2019-07-09 | 2019-07-15 | 4 | 2019-07-15 | [14 empty] | 2019-07-23 | 2019-07-26 |  | Y
Central Hudson |  | EnterSolar | CH-11660 | Newburgh | Montgomery | Orange | 12549 | G | 5054 | Maybrook | N |  | 5000 | [13 empty] | CDG | Y | 41 SolarEdge Technologies SE120KUS (480V) [SI1] 1 SolarEdge Technologies SE80KUS (480V) [SI1] | 2019-08-08 | 2019-08-14 | 4 | 2019-08-14 | 2019-08-14 | 2019-09-05 | 15 | 2019-09-16 | 2019-12-30 | 2020-03-25 | 60 | 23956.74 | 296536.7 | 214000.72 | 2020-04-01 | 2020-09-18 | 2020-09-18 | 2023-05-22 | 2023-05-24 | 2023-05-26 | 2023-09-18 | Y | Y
Central Hudson |  | Infinity Solar Systems | CH-11659 | Newburgh | New Windsor | Orange | 12553 | G | 4046 | Union Ave | N |  | 4.5 | [13 empty] | NM | N | 18 Enphase Energy IQ7-60-x-US (240V) | 2019-07-16 | 2019-07-17 | 1 | 2019-07-17 | [14 empty] | 2019-08-29 | 2019-09-06 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-11665 | Poughkeepsie | Salt Pt |  | 12578 | G | 7025 | Tinkertown | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600A-US (240V) | 2019-07-17 | 2019-07-19 | 2 | 2019-07-19 | [14 empty] | 2019-07-19 | 2019-07-24 |  | W
Central Hudson |  | Apex Roofing, LLC | CH-11664 | Catskill | Athens | Greene | 12015 | G | 2002 | North Catskill | N |  | 9.92 | [13 empty] | NM | N | 31 SunPower SPR-X22-360-E-AC (208V) | 2019-07-18 | 2019-07-19 | 1 | 2019-07-19 | [8 empty] | 350 | 350 |  | 2019-07-23 | 2019-07-23 | 2019-09-09 | 2019-09-27 | 2019-09-27 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-11666 | Newburgh | Newburgh | Orange | 12550 | G | 4023 | Coldenham | N | CH-11666 | 5 | [13 empty] | NM | N | 1 Ningbo Ginlong Technologies Solis-1P5K-4G-US (240V) | 2019-07-29 | 2019-08-07 | 7 | 2019-08-07 | [14 empty] | 2019-08-22 | 2019-08-28 |  | Y
Central Hudson |  | Tesla Energy | CH-11662 | Kingston | Stone Ridge | Ulster | 12484 | G | 3023 | High Falls | Y |  | 12.8 | 10 | [12 empty] | NM | N | 1 Delta Electronics SOLIVIA 5.2 NA G4 TL (240V) [SI1] 1 Delta Electronics SOLIVIA 7.6 NA G4 TL (240V) [SI1] 2TeslaAC Powerwall 2.0 | 2019-07-16 | 2019-07-17 | 1 | 2019-07-17 | [14 empty] | 2019-09-26 | 2019-09-26 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-11667 | Newburgh | Newburgh | Orange | 12550 | G | 4015 | West Balmville | N |  | 8 | [13 empty] | NM | N | 32 Enphase Energy IQ7-60-x-US (240V) | 2019-07-16 | 2019-07-17 | 1 | 2019-07-17 | [14 empty] | 2019-10-09 | 2019-10-09 |  | Y
Central Hudson |  | Tesla Energy | CH-11663 | Kingston | Shady | Ulster | 12409 | G | 3012 | Woodstock | Y | CH-20958 |  | 20 | [12 empty] | NM | N | 4TeslaAC Powerwall 2.0 | 2019-07-16 | 2019-07-17 | 1 | 2019-07-17 | [14 empty] | 2019-09-26 | 2019-09-26 |  | Y
Central Hudson |  | Vivint Solar Developer, LLC | CH-11669 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8092 | Fishkill Plains | N |  | 6.96 | [13 empty] | NM | N | 29 Enphase Energy IQ7-60-x-US (240V) | 2019-07-11 | 2019-07-16 | 3 | 2019-07-16 | [14 empty] | 2020-09-23 | 2020-09-23 |  | Y
Central Hudson |  | Vivint Solar Developer, LLC | CH-11671 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 6051 | Todd Hill | N |  | 13.8 | [13 empty] | NM | N | 60 Enphase Energy IQ6-60-X-US (240V) | 2019-08-09 | 2019-08-22 | 9 | 2019-08-22 | [14 empty] | 2019-08-28 | 2019-09-16 |  | Y
Central Hudson |  | Apex Solar Power | CH-11668 | Kingston | Saugerties | Ulster | 12477 | G | 3003 | Saugerties | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2019-07-17 | 2019-07-19 | 2 | 2019-07-19 | [8 empty] | 350 | 350 |  | 2019-08-01 | 2019-08-01 | 2019-09-27 | 2019-10-22 | 2019-10-24 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-11670 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6043 | Spackenkill | N |  | 2.88 | [13 empty] | NM | N | 12 Enphase Energy IQ7-60-x-US (240V) | 2019-07-18 | 2019-07-19 | 1 | 2019-07-19 | [14 empty] | 2019-08-14 | 2019-08-28 |  | Y
Central Hudson |  | Lumens Holdings 3 LLC | CH-11600 | Kingston | Kerhonkson |  | 12446 | G | 3082 | Kerhonkson | N |  | 1980 | [13 empty] | CDG | Y | 33 Sungrow Power Supply SG60KU-M (480V) [SI1] | 2019-07-26 | 2019-08-01 | 4 | 2019-08-01 | 2019-08-01 | 2019-08-22 | 15 | [5 empty] | 296047.5 | 2218.76 | 2019-11-25 | 2020-09-09 | 2020-09-09 |  |  |  | 2021-09-15 | W
Central Hudson |  | Lumens Holdings 3 LLC | CH-11601 | Catskill | Coeymans Hollow |  | 12046 | G | 1081 | New Baltimore | N |  | 1980 | [13 empty] | CDG | Y | 33 Sungrow Power Supply SG60KU-M (480V) [SI1] | 2019-07-26 | 2019-08-01 | 4 | 2019-08-01 | 2019-08-01 | 2019-08-22 | 15 | 2019-10-03 | 2019-10-30 | 2020-01-29 | 60 | 13400.97 | 18199537.5 | [7 empty] | 2020-07-22 | W
Central Hudson |  | Lumens Holdings 3 LLC | CH-11602 | Fishkill | East Fishkill |  | 12582 | G | 8093 | Fishkill Plains | N |  | 1300 | [13 empty] | CDG | Y | 22 Sungrow Power Supply SG60KU-M (480V) [SI1] | 2019-07-26 | 2019-08-01 | 4 | 2019-08-01 | 2019-08-01 | 2019-08-22 | 15 | [5 empty] | 502610 |  | 2019-11-25 | [5 empty] | 2020-12-16 | W
Central Hudson |  | Lumens Holdings 3 LLC | CH-11603 | Catskill | Catskill |  | 12414 | G | 2001 | North Catskill | N |  | 1980 | [13 empty] | CDG | Y | 33 Sungrow Power Supply SG60KU-M (480V) [SI1] | 2019-07-26 | 2019-08-01 | 4 | 2019-08-01 | 2019-08-01 | 2019-08-22 | 15 | [5 empty] | 465926.25 |  | 2019-11-15 | [5 empty] | 2020-12-16 | W | Y
Central Hudson |  | Lumens Holdings 3 LLC | CH-11604 | Newburgh | Gardiner | Ulster | 12561 | G | 5031 | Galeville | N |  | 2000 | [13 empty] | CDG | Y | 16 Chint Power Systems America CPS SCH125KTL-DO/US-600 (600V) | 2019-07-26 | 2019-08-01 | 4 | 2019-08-01 | 2019-08-01 | 2019-08-22 | 15 | 2019-10-03 | 2019-10-22 | 2020-01-21 | 60 | 17500 | 212575 |  | 2020-05-18 | 2020-11-04 | 2020-11-04 | 2025-07-25 | 2025-10-31 | 2025-10-31 |  | Y | Y
Central Hudson |  | Lumens Holdings 3 LLC | CH-11605 | Catskill | Durham |  | 12413 | G | 2043 | South Cairo | N |  | 5000 | [13 empty] | CDG | Y | 40 Sungrow Power Supply SG125HV (600V) | 2019-07-26 | 2019-08-01 | 4 | 2019-08-01 | 2019-08-01 | 2019-08-22 | 15 | 2019-10-03 | 2019-10-30 | 2020-01-29 | 60 | 11446.27 | 7310056.25 | [7 empty] | 2020-07-22 | W
Central Hudson |  | PlugPC LLC | CH-11674 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 6057 | Todd Hill | N |  | 3.8 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3800H-US (240V) | 2019-07-12 | 2019-07-16 | 2 | 2019-07-16 | [14 empty] | 2019-08-19 | 2019-08-22 |  | Y
Central Hudson |  | Tesla Energy | CH-11673 | Kingston | Kingston | Ulster | 12401 | G | 112 | South Wall St | N |  | 5.2 | [13 empty] | NM | N | 1 Delta Electronics SOLIVIA 5.2 NA G4 TL (240V) | 2019-07-17 | 2019-07-19 | 2 | 2019-07-19 | [14 empty] | 2019-10-16 | 2019-10-16 |  | Y
Central Hudson |  | PlugPV LLC | CH-11675 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6052 | Todd Hill | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE11400H-US (240V) | 2019-07-22 | 2019-08-05 | 10 | 2019-08-05 | [14 empty] | 2019-08-26 | 2019-08-30 |  | Y
Central Hudson |  | Suncommon | CH-11676 | Poughkeepsie | Red Hook | Dutchess | 12583 | G | 7062 | Milan | N |  | 40 | [13 empty] | NM | N | 4 SolarEdge Technologies SE10000H-US (240V) | 2019-07-29 | 2019-08-07 | 7 | 2019-08-07 | [8 empty] | 2500 | 1036.99 |  | 2019-08-13 | 2019-08-13 | 2019-10-07 | 2019-10-21 | 2019-10-28 | 2019-11-04 | Y
Central Hudson |  | New York State Solar Farm | CH-11677 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6056 | Todd Hill | N | CH-11677 | 7.36 | [13 empty] | NM | N | 23 SunPower SPR-X22-360-E-AC (240V) | 2019-07-15 | 2019-07-16 | 1 | 2019-07-16 | [14 empty] | 2019-08-16 | 2019-08-22 |  | Y
Central Hudson |  | Sunrun, Inc. | CH-11684 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 6073 | East Park | N |  | 6 | [13 empty] | NM | N | 1 Ningbo Ginlong Technologies Solis-1P6K-4G-US | 2019-08-26 | 2019-09-10 | 10 | 2019-09-10 | [14 empty] | 2019-09-27 | 2019-10-04 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-11686 | Kingston | Kingston | Ulster | 12401 | G | 2016 | Lincoln Park | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2019-08-05 | 2019-08-14 | 7 | 2019-08-14 | [14 empty] | 2019-08-23 | 2019-08-30 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-11678 | Newburgh | Marlboro |  | 12542 | G | 5001 | Marlboro | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE 10000A-US (240V) | 2019-07-16 | 2019-07-17 | 1 | 2019-07-17 | [8 empty] | 350 | 350 |  | 2019-07-19 | 2019-07-19 | 2019-08-13 | 2019-08-14 | 2019-08-21 |  | W
Central Hudson |  | Sunrun Installation Services, Inc. | CH-11685 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8056 | North Chelsea | N |  | 16.6 | [13 empty] | NM | N | 1 Ningbo Ginlong Technologies Solis-1P9K-4G-US 1 Ningbo Ginlong Technologies Solis-1P7.6K-4G-US | 2019-08-05 | 2019-08-16 | 9 | 2019-08-16 | [14 empty] | 2019-08-22 | 2019-08-29 |  | Y
Central Hudson |  | Solar Generation Projects LLC | CH-11683 | Newburgh | Highland |  | 12528 | G | 5084 | Highland | N |  | 750 | [13 empty] | RC | Y | 6 Sungrow Power Supply SG125HV (600V) | 2019-09-03 | 2019-09-16 | 9 | 2019-09-16 | 2019-09-16 | 2019-10-07 | 15 | [5 empty] | 219613.75 | 11511.92 | 2020-05-28 | 2020-11-17 | 2020-11-17 |  |  |  | 2022-06-13 | W | Y
Central Hudson |  | Empire Solar Solutions | CH-11679 | Fishkill | Hopewell Jct |  | 12533 | G | 8096 | Fishkill Plains | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE 10000A-US (240V) | 2019-07-16 | 2019-07-17 | 1 | 2019-07-17 | [14 empty] | 2019-07-19 | 2019-07-24 |  | W
Central Hudson |  | Empire Solar Solutions | CH-11680 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8043 | Myers Corners | N |  | 15.2 | [13 empty] | NM | N | 2 SolarEdge Technologies SE7600A-US (240V) | 2019-07-16 | 2019-07-17 | 1 | 2019-07-17 | [14 empty] | 2019-07-25 | 2019-07-26 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-11681 | Fishkill | Wappingrs Fls |  | 12590 | G | 8052 | North Chelsea | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000 (240V) | 2019-07-16 | 2019-07-17 | 1 | 2019-07-17 | [14 empty] | 2019-08-14 | 2019-08-21 |  | W
Central Hudson |  | Solar Generation | CH-11682 | Kingston | Willow | Ulster | 12495 | G | 3012 | Woodstock | N |  | 3.8 | [13 empty] | NM | N | 1SolarEdge3800H-US | 2019-07-16 | 2019-07-17 | 1 | 2019-07-17 | [14 empty] | 2019-07-29 | 2019-08-02 |  | Y
Central Hudson |  | Lighthouse Solar | CH-11689 | Newburgh | New Paltz | Ulster | 12561 | G | 5031 | Galeville | N |  | 10.44 | [13 empty] | NM | N | 36 Enphase Energy IQ7PLUS-72-x-US (240V) [SI1] | 2019-07-25 | 2019-08-06 | 8 | 2019-08-06 | [14 empty] | 2019-10-02 | 2019-10-07 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-11687 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6042 | Spackenkill | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000 (240V) | 2019-07-17 | 2019-07-19 | 2 | 2019-07-19 | [14 empty] | 2019-09-06 | 2019-09-13 |  | Y
Central Hudson |  | New York State Solar Farm | CH-11690 | Newburgh | Montgomery | Orange | 12549 | G | 5073 | Montgomery | N |  | 7.245 | [13 empty] | NM | N | 23 SunPower SPR-E20-327-E-AC (240V) | 2019-07-17 | 2019-07-19 | 2 | 2019-07-19 | [14 empty] | 2019-08-21 | 2019-08-22 |  | Y
Central Hudson |  | Lighthouse Solar | CH-11688 | Newburgh | New Paltz | Ulster | 12561 | G | 5023 | Ohioville | N |  | 7.54 | [13 empty] | NM | N | 14 Enphase Energy IQ7PLUS-72-x-US (240V) [SI1] 12 Enphase Energy IQ7PLUS-72-x-US (240V) [SI1] | 2019-07-17 | 2019-07-19 | 2 | 2019-07-19 | [14 empty] | 2019-08-27 | 2019-09-04 |  | Y
Central Hudson |  | Suncommon | CH-11692 | Poughkeepsie | Stanfordvl | Dutchess | 12581 | G | 7072 | Stanfordville | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2019-07-18 | 2019-07-19 | 1 | 2019-07-19 | [14 empty] | 2019-09-13 | 2019-09-18 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-11694 | Newburgh | New Windsor | Orange | 12553 | G | 4095 | Bethlehem Rd | N |  | 12 | [13 empty] | NM | N | 2 SolarEdge Technologies SE6000 (240V) | 2019-07-18 | 2019-07-19 | 1 | 2019-07-19 | [14 empty] | 2019-07-19 | 2019-07-24 |  | Y
Central Hudson |  | murphy solar and central air | CH-11696 | Catskill | Coxsackie | Greene | 12051 | G | 1076 | Coxsackie | N |  | 5 | [13 empty] | NM | N | 1 SMA America SB5000US-11 (240V) | 2019-07-18 | 2019-07-19 | 1 | 2019-07-19 | [14 empty] | 2019-09-20 | 2019-09-20 |  | Y
Central Hudson |  | Bright Planet Solar | CH-11695 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6003 | Reynolds Hill | N |  | 16 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) 1 SolarEdge Technologies SE6000H-US (240V) | 2019-08-20 | 2019-09-04 | 10 | 2019-09-04 | [14 empty] | 2019-11-11 | 2019-11-14 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-11691 | Newburgh | New Windsor | Orange | 12553 | G | 4094 | Bethlehem Rd | N |  | 8.64 | [13 empty] | NM | N | 36 Enphase Energy IQ7-60-x-US (240V) | 2019-07-18 | 2019-07-19 | 1 | 2019-07-19 | [14 empty] | 2019-09-16 | 2019-09-18 |  | Y
Central Hudson |  | Solar Generation | CH-11693 | Kingston | Woodstock |  | 12498 | G | 3013 | Woodstock | N |  | 10.6 | [13 empty] | NM | N | 1 Pika Energy X7602 (240V) 1 SolarEdge Technologies SE3000H-US (240V) | 2019-08-15 | 2019-08-28 | 9 | 2019-08-28 | [17 empty] | W
Central Hudson |  | Sunrun Installation Services, Inc. | CH-11701 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8072 | Shenandoah | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2019-07-19 | 2019-07-30 | 7 | 2019-07-30 | [14 empty] | 2019-08-30 | 2019-09-09 |  | Y
Central Hudson |  | Trinity Solar | CH-11700 | Newburgh | New Windsor | Orange | 12553 | G | 4045 | Union Ave | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2019-07-19 | 2019-07-26 | 5 | 2019-07-26 | [14 empty] | 2019-08-15 | 2019-08-22 |  | Y
Central Hudson |  | Kasselman Solar | CH-11697 | Fishkill | Fishkill | Dutchess | 12524 | G | 8062 | Merritt Park | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2019-07-19 | 2019-07-24 | 3 | 2019-07-24 | [14 empty] | 2019-08-19 | 2019-08-22 |  | Y
Central Hudson |  | PlugPV LLC | CH-11699 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 7024 | Tinkertown | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2019-07-19 | 2019-07-26 | 5 | 2019-07-26 | [14 empty] | 2019-08-19 | 2019-09-03 |  | Y
Central Hudson |  | Suncommon | CH-11698 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6044 | Spackenkill | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000H-US (240V) | 2019-07-19 | 2019-07-24 | 3 | 2019-07-24 | [14 empty] | 2019-08-07 | 2019-08-13 |  | Y
Central Hudson |  | PlugPV LLC | CH-11703 | Newburgh | Newburgh | Orange | 12550 | G | 4022 | Coldenham | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000H-US (240V) | 2019-07-22 | 2019-08-02 | 9 | 2019-08-02 | [8 empty] | 350 | 350 |  | 2019-10-24 | 2019-10-24 | 2019-12-17 | 2020-01-17 | 2020-01-17 |  | Y
Central Hudson |  | Suncommon | CH-11702 | Catskill | Saugerties | Ulster | 12477 | G | 2001 | North Catskill | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2019-07-22 | 2019-08-02 | 9 | 2019-08-02 | [14 empty] | 2019-08-20 | 2019-08-28 |  | Y
Central Hudson |  | PlugPV LLC | CH-11704 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6061 | Inwood Ave | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2019-08-05 | 2019-08-14 | 7 | 2019-08-14 | [14 empty] | 2019-08-19 | 2019-08-30 |  | Y
Central Hudson |  | Kasselman Solar | CH-11706 | Kingston | Saugerties | Ulster | 12477 | G | 3001 | Saugerties | N |  | 3 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3000H-US (240V) | 2019-07-23 | 2019-08-02 | 8 | 2019-08-02 | [14 empty] | 2019-08-26 | 2019-09-03 |  | Y
Central Hudson |  | Kasselman Solar | CH-11705 | Catskill | Athens | Greene | 12015 | G | 2002 | North Catskill | N | CH-03518 | 1.44 | [13 empty] | NM | N | 6 Enphase Energy M250-72-2LL-S2x (240V) | 2019-08-05 | 2019-08-14 | 7 | 2019-08-14 | [14 empty] | 2019-10-08 | 2019-10-09 |  | Y
Central Hudson |  | PlugPV LLC | CH-11707 | Kingston | Saugerties | Ulster | 12477 | G | 3001 | Saugerties | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2019-08-06 | 2019-08-16 | 8 | 2019-08-16 | [14 empty] | 2019-08-19 | 2019-08-22 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-11710 | Fishkill | Wappingrs Fls |  | 12590 | G | 8045 | Myers Corners | N |  | 3 | [13 empty] | NM | N | 1 Ningbo Ginlong Technologies Solis-1P3K-4G-US (240V) | 2019-07-25 | 2019-08-06 | 8 | 2019-08-06 | [17 empty] | W
Central Hudson |  | Sunrun Installation Services, Inc. | CH-11709 | Fishkill | Beacon | Dutchess | 12508 | G | 8085 | Tioronda | N |  | 10 | [13 empty] | NM | N | 1 Ningbo Ginlong Technologies Solis-1P10K-4G-US | 2019-07-25 | 2019-08-06 | 8 | 2019-08-06 | [14 empty] | 2019-09-11 | 2019-09-16 |  | Y
Central Hudson |  | Lighthouse Solar | CH-11708 | Kingston | Kingston | Ulster | 12401 | G | 1022 | East Kingston | N |  | 6.96 | [13 empty] | NM | N | 24 Enphase Energy IQ7PLUS-72-x-US (240V) [SI1] | 2019-07-25 | 2019-08-06 | 8 | 2019-08-06 | [14 empty] | 2019-09-25 | 2019-09-25 |  | Y
Central Hudson |  | YSG Solar | CH-11713 | Poughkeepsie | Millerton | Dutchess | 12546 | G | 7081 | Millerton | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000 (240V) | 2019-08-20 | 2019-09-04 | 10 | 2019-09-04 | [14 empty] | 2019-11-12 | 2019-11-15 |  | Y
Central Hudson |  | Solar Generation Projects LLC | CH-11712 | Kingston | Stone Ridge | Ulster | 12484 | G | 3023 | High Falls | N |  | 300 | [13 empty] | CDG | Y | 3 Chint Power Systems America CPS SCH100KTL-DO/US-600 (600V) | 2019-09-03 | 2019-09-16 | 9 | 2019-09-16 | 2019-09-16 | 2019-10-07 | 15 | [5 empty] | 69266.25 | 61272.82 | 2020-05-13 | 2020-10-30 | 2020-10-30 | 2022-01-17 | 2022-03-01 | 2022-03-07 | 2022-05-16 | Y | Y
Central Hudson |  | Suncommon | CH-11711 | Kingston | Kingston | Ulster | 12401 | G | 1011 | Boulevard | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2019-07-29 | 2019-08-07 | 7 | 2019-08-07 | [14 empty] | 2019-08-20 | 2019-08-22 |  | Y
Central Hudson |  | Sunrun Inc | CH-11715 | Fishkill | Beacon | Dutchess | 12508 | G | 8015 | Forgebrook | N | CH-11715 | 4 | [13 empty] | NM | N | 1 Ningbo Ginlong Technologies Solis-1P4K-4G-US (240V) | 2019-08-13 | 2019-08-22 | 7 | 2019-08-22 | [14 empty] | 2019-10-04 | 2019-10-08 |  | Y
Central Hudson |  | Red Hook Solar | CH-11722 | Kingston | Saugerties | Ulster | 12477 | G | 3002 | Saugerties | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2019-08-19 | 2019-09-03 | 10 | 2019-09-03 | [8 empty] | 350 | 350 |  | 2019-09-05 | 2019-09-05 | 2019-10-14 | 2019-10-16 | 2019-10-18 |  | Y
Central Hudson |  | Solar Generation | CH-11721 | Kingston | Woodstock | Ulster | 12498 | G | 3014 | Woodstock | N |  | 13.68 | [13 empty] | NM | N | 1 SMA America SB7700TL-US-22 (240V) 1 SolarEdge Technologies SE6000H-US (240V) | 2019-07-31 | 2019-08-12 | 8 | 2019-08-12 | [14 empty] | 2019-08-16 | 2019-08-22 |  | Y
Central Hudson |  | Albany Solar Solutions LLC | CH-11716 | Kingston | Shokan | Ulster | 12481 | G | 3011 | Woodstock | N |  | 12.96 | [13 empty] | NM | N | 18 Chilicon Power CP-720-60/72/96-208/240-MC4 (240V) [SI1] | 2019-09-03 | 2019-09-17 | 10 | 2019-09-17 | [8 empty] | 350 | 350 |  | 2019-09-18 | 2019-09-18 | 2019-11-04 | 2019-11-07 | 2019-11-11 |  | Y
Central Hudson |  | Albany Solar Solutions LLC | CH-11717 | Poughkeepsie | Millerton | Dutchess | 12546 | G | 7081 | Millerton | N |  | 15.84 | [13 empty] | NM | N | 22 Chilicon Power CP-720-60/72/96-208/240-MC4 (240V) [SI1] | 2019-11-06 | 2019-11-14 | 6 | 2019-11-14 | [8 empty] | 350 | 350 |  | 2019-11-18 | 2019-11-18 | 2019-12-12 | 2020-05-12 | 2020-05-12 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-11719 | Poughkeepsie | Poughkeepsie |  | 12601 | G | 6096 | Manchester | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE 11400A-US (240V) | 2019-07-31 | 2019-08-12 | 8 | 2019-08-12 | [14 empty] | 2019-09-03 | 2019-09-10 |  | W
Central Hudson |  | Kasselman Solar | CH-11718 | Catskill | Jewett | Greene | 12444 | E | 2081 | Hunter | N | CH-00232 | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2019-07-31 | 2019-08-12 | 8 | 2019-08-12 | [8 empty] | 350 | 350 |  | 2019-08-20 | 2019-08-20 | 2019-08-28 | 2019-10-25 | 2019-10-25 |  | Y
Central Hudson |  | Solar Generation | CH-11720 | Kingston | Woodstock | Ulster | 12498 | G | 3014 | Woodstock | N |  | 11.2 | [13 empty] | NM | N | 35 SunPower SPR-X22-360-C-AC (240V) | 2019-07-31 | 2019-08-12 | 8 | 2019-08-12 | [14 empty] | 2019-09-19 | 2019-09-19 |  | Y
Central Hudson |  | MOMENTUM SOLAR | CH-11728 | Newburgh | Cornwall | Orange | 12518 | G | 4093 | Bethlehem Rd | N |  | 2.88 | [13 empty] | NM | N | 12 Enphase Energy IQ7-60-x-US (240V) | 2019-08-01 | 2019-08-13 | 8 | 2019-08-13 | [14 empty] | 2019-10-07 | 2019-10-08 |  | Y
Central Hudson |  | Solar Liberty Energy Systems Inc. | CH-11727 | Catskill | Hannacroix | Greene | 12087 | G | 1083 | New Baltimore | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE11400H-US (240V) | 2019-08-01 | 2019-08-13 | 8 | 2019-08-13 | [8 empty] | 350 | 350 |  | 2019-08-19 | 2019-08-19 | 2019-08-26 | 2019-12-23 | 2019-12-26 |  | Y
Central Hudson |  | PlugPV LLC | CH-11724 | Kingston | Saugerties | Ulster | 12477 | G | 3001 | Saugerties | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2019-08-01 | 2019-08-13 | 8 | 2019-08-13 | [14 empty] | 2019-09-09 | 2019-09-13 |  | Y
Central Hudson |  | Lighthouse Solar | CH-11723 | Kingston | Woodstock | Ulster | 12498 | G | 3012 | Woodstock | N |  | 6.96 | [13 empty] | NM | N | 24EnphaseIQ7Plus-72-X-US | 2019-08-01 | 2019-08-13 | 8 | 2019-08-13 | [14 empty] | 2019-09-05 | 2019-09-12 |  | Y
Central Hudson |  | PlugPV LLC | CH-11725 | Newburgh | Campbell Hall | Orange | 10916 | G | 5051 | Maybrook | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2019-08-01 | 2019-08-13 | 8 | 2019-08-13 | [14 empty] | 2019-09-16 | 2019-09-18 |  | Y
Central Hudson |  | Suncommon | CH-11726 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7053 | Rhinebeck | N |  | 10.24 | [13 empty] | NM | N | 32 SunPower SPR-E20-327-D-AC (240V) [SI1] | 2019-08-01 | 2019-08-13 | 8 | 2019-08-13 | [14 empty] | 2019-11-19 | 2019-11-22 |  | Y
Central Hudson |  | murphy solar and central air | CH-11729 | Catskill | Coxsackie | Greene | 12051 | G | 1076 | Coxsackie | N |  | 5 | [13 empty] | NM | N | 1 Fronius USA IG Plus 5.0-1 UNI (240V) | 2019-09-25 | 2019-09-25 | 0 | 2019-09-25 | [14 empty] | 2019-10-08 | 2019-10-09 |  | Y
Central Hudson |  | Nexamp | CH-11730 | Catskill | Cairo | Greene | 12413 | G | 2041 | South Cairo | N |  | 1975 | [13 empty] | CDG | Y | 15 Chint Power Systems America CPS SCH125KTL-DO/US-600 (600V) 1 Chint Power Systems America CPS SCH100KTL-DO/US-600 (600V) | 2019-08-14 | 2019-08-14 | 0 | 2019-08-14 | 2019-08-14 | 2019-09-05 | 15 | 2019-09-23 | 2019-10-25 | 2020-01-24 | 60 | 5703.73 | 339958.23 | 200737.31 | 2020-03-02 | 2020-09-10 | 2020-09-10 | 2023-05-19 | 2023-06-29 | 2023-06-30 | 2023-09-26 | Y | Y
Central Hudson |  | Sunrun Inc | CH-11732 | Fishkill | Hopewell Jct |  | 12533 | G | 8091 | Fishkill Plains | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2019-08-16 | 2019-08-28 | 8 | 2019-08-28 | [17 empty] | W
Central Hudson |  | Kasselman Solar | CH-11731 | Kingston | Olive Brdg | Ulster | 12461 | G | 3082 | Kerhonkson | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2019-08-14 | 2019-08-22 | 6 | 2019-08-22 | [8 empty] | 350 | 350 |  | 2019-08-27 | 2019-08-27 | 2019-10-15 | 2019-10-18 | 2019-10-18 |  | Y
Central Hudson |  | YSG Solar LLC | CH-11736 | Newburgh | Newburgh | Orange | 12550 | G | 4051 | Union Ave | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE11400H-US (240V) | 2019-09-03 | 2019-09-16 | 9 | 2019-09-16 | [8 empty] | 350 | 350 |  | 2019-10-03 | 2019-10-03 | 2020-03-18 | 2020-04-24 | 2020-04-24 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-11739 | Newburgh | Newburgh | Orange | 12550 | G | 4023 | Coldenham | N |  | 5 | [13 empty] | NM | N | 1 Ningbo Ginlong Technologies Solis-1P5K-4G-US (240V) | 2019-08-06 | 2019-08-19 | 9 | 2019-08-19 | [14 empty] | 2019-09-27 | 2019-10-02 |  | Y
Central Hudson |  | Monolith Solar Associates LLC | CH-11734 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7052 | Rhinebeck | N |  | 10 | [13 empty] | NM | N | 2 SolarEdge Technologies SE5000H-US (208V) | 2019-09-03 | 2019-09-16 | 9 | 2019-09-16 | [8 empty] | 350 | 350 |  | 2019-09-18 | 2019-09-18 | 2019-09-30 | 2019-10-23 | 2019-10-25 |  | Y
Central Hudson |  | Sunrun Inc | CH-11737 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 6057 | Todd Hill | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2019-08-06 | 2019-08-19 | 9 | 2019-08-19 | [14 empty] | 2020-03-30 | 2020-03-30 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-11735 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6095 | Manchester | N |  | 6.96 | [13 empty] | NM | N | 29 Enphase Energy IQ7-60-x-US (240V) | 2019-08-16 | 2019-08-28 | 8 | 2019-08-28 | [14 empty] | 2019-11-01 | 2019-11-01 |  | Y
Central Hudson |  | Sunrun Inc | CH-11738 | Newburgh | New Windsor | Orange | 12553 | G | 4044 | Union Ave | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2019-08-06 | 2019-08-19 | 9 | 2019-08-19 | [14 empty] | 2019-09-10 | 2019-09-16 |  | Y
Central Hudson |  | Solar Alchemy, Inc. | CH-11742 | Kingston | Stone Ridge | Ulster | 12484 | G | 3023 | High Falls | N |  | 9.6 | [13 empty] | NM | N | 40 Enphase Energy IQ7-60-x-US (240V) | 2019-08-21 | 2019-09-05 | 10 | 2019-09-05 | [14 empty] | 2020-03-24 | 2020-03-24 |  | Y
Central Hudson |  | Solar Alchemy, Inc. | CH-11741 | Kingston | Stone Ridge | Ulster | 12484 | G | 3023 | High Falls | N |  | 4.08 | [13 empty] | NM | N | 17 Enphase Energy IQ7-60-x-US (240V) | 2019-08-21 | 2019-09-05 | 10 | 2019-09-05 | [14 empty] | 2019-12-13 | 2019-12-13 |  | Y
Central Hudson |  | Solar Alchemy, Inc. | CH-11740 | Kingston | Bearsvl | Ulster | 12409 | G | 3012 | Woodstock | N | CH-08983 | 3.3 | [13 empty] | NM | N | 13 Enphase Energy IQ7-60-x-US (240V) | 2019-09-19 | 2019-09-20 | 1 | 2019-09-20 | [14 empty] | 2019-09-26 | 2019-09-26 |  | Y
Central Hudson |  | BQ Energy Development | CH-11750 | Poughkeepsie | Milan | Dutchess | 12571 | G | 7061 | Milan | N |  | 1375 | [13 empty] | CDG | Y | 11 SMA America SHP 125-US-20 (480V) | 2019-08-20 | 2019-09-03 | 9 | 2019-09-03 | 2019-09-03 | 2019-09-24 | 15 | 2019-11-26 | 2020-01-30 | 2020-05-11 | 70 | 20682.06 | 216037.5 | 203240.05 | 2020-09-18 | 2021-03-17 | 2021-03-17 | 2024-12-17 | 2025-02-05 | 2025-02-06 | 2025-05-02 | Y | Y | 4/27/2020 - Utility and Developer mutually agreed to extend the CESIR deadline to 05/11/2020.
Central Hudson |  | Suncommon | CH-11749 | Kingston | Ulster Pk | Ulster | 12487 | G | 1023 | East Kingston | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE11400H-US (240V) | 2019-08-08 | 2019-08-22 | 10 | 2019-08-22 | [14 empty] | 2019-09-20 | 2019-09-24 |  | Y
Central Hudson |  | PlugPV LLC | CH-11744 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 7025 | Tinkertown | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE11400H-US (240V) | 2019-08-23 | 2019-09-09 | 10 | 2019-09-09 | [14 empty] | 2019-09-10 | 2019-09-16 |  | Y
Central Hudson |  | Tesla Energy | CH-11748 | Catskill | Hunter | Greene | 12442 | E | 2081 | Hunter | Y |  | 3.8 | 5 | [12 empty] | NM | N | 1 SolarEdge Technologies SE3800x (240V) [SI1] 1TeslaAC Powerwall 2.0 | 2019-08-22 | 2019-09-06 | 10 | 2019-09-06 | [14 empty] | 2019-11-12 | 2019-11-14 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-11747 | Poughkeepsie | Poughkeepsie |  | 12601 | G | 6011 | Sand Dock | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000 (240V) | 2019-08-08 | 2019-08-22 | 10 | 2019-08-22 | [14 empty] | 2019-08-23 | 2019-08-29 |  | W
Central Hudson |  | PlugPV LLC | CH-11743 | Newburgh | Highland | Ulster | 12528 | G | 5084 | Highland | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2019-08-08 | 2019-08-22 | 10 | 2019-08-22 | [14 empty] | 2019-09-09 | 2019-09-13 |  | Y
Central Hudson |  | PlugPV LLC | CH-11745 | Newburgh | Salisbury Mls | Orange | 12577 | G | 4097 | Bethlehem Rd | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2019-08-08 | 2019-08-22 | 10 | 2019-08-22 | [14 empty] | 2019-09-06 | 2019-09-13 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-11746 | Kingston | Kingston |  | 12401 | G | 1022 | East Kingston | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000 (240V) | 2019-08-08 | 2019-08-22 | 10 | 2019-08-22 | [14 empty] | 2019-08-22 | 2019-08-28 |  | W
Central Hudson |  | New York State Solar Farm | CH-11752 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N | CH-00438 | 1.89 | [13 empty] | NM | N | 6 SunPower SPR-X21-345-E-AC (240V) | 2019-08-09 | 2019-08-22 | 9 | 2019-08-22 | [14 empty] | 2019-08-23 | 2019-08-30 |  | Y
Central Hudson |  | Apex Solar Power | CH-11751 | Poughkeepsie | Staatsburg | Dutchess | 12580 | G | 7041 | Staatsburg | N |  | 15 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) 1 SolarEdge Technologies SE5000H-US (240V) | 2019-08-09 | 2019-08-23 | 10 | 2019-08-23 | [8 empty] | 350 | 350 |  | 2019-09-14 | 2019-09-14 | 2019-09-13 | 2019-09-23 | 2019-09-25 |  | Y
Central Hudson |  | Sunrun Installation Service, Inc. | CH-11754 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8045 | Myers Corners | N |  | 9 | [13 empty] | NM | N | 1 Ningbo Ginlong Technologies Solis-1P9K-4G-US | 2019-08-26 | 2019-09-10 | 10 | 2019-09-10 | [14 empty] | 2019-10-18 | 2019-10-18 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-11753 | Kingston | Kingston |  | 12401 | G | 1013 | Boulevard | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600A-US (240V) | 2019-08-12 | 2019-08-22 | 8 | 2019-08-22 | [14 empty] | 2019-08-30 | 2019-09-09 |  | W
Central Hudson |  | Solar Generation | CH-11755 | Kingston | Mt Tremper | Ulster | 12457 | G | 3012 | Woodstock | N |  | 15.2 | [13 empty] | NM | N | 2 SolarEdge Technologies SE7600H-US (240V) | 2019-08-13 | 2019-08-22 | 7 | 2019-08-22 | [14 empty] | 2019-09-25 | 2019-10-02 |  | Y
Central Hudson |  | Suncommon | CH-11756 | Kingston | Cottekill | Ulster | 12419 | G | 3021 | High Falls | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2019-08-13 | 2019-08-22 | 7 | 2019-08-22 | [14 empty] | 2019-10-03 | 2019-10-08 |  | Y
Central Hudson |  | New York State Solar Farm | CH-11757 | Fishkill | Nelsonvl | Putnam | 10516 | G | 8087 | Tioronda | N |  | 7.56 | [13 empty] | NM | N | 24 SunPower SPR-X22-360-E-AC (240V) | 2019-08-14 | 2019-08-22 | 6 | 2019-08-22 | [14 empty] | 2019-10-11 | 2019-10-11 |  | Y
Central Hudson |  | Sunrun Inc | CH-11762 | Kingston | Rifton | Ulster | 12471 | G | 3041 | Sturgeon Pool | N |  | 9 | [13 empty] | NM | N | 1 Ningbo Ginlong Technologies Solis-1P9K-4G-US | 2019-08-14 | 2019-08-22 | 6 | 2019-08-22 | [14 empty] | 2019-09-11 | 2019-09-17 |  | Y
Central Hudson |  | Sunrun Installation Service, Inc. | CH-11763 | Fishkill | Hopewell Jct |  | 12533 | G | 8072 | Shenandoah | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE11400H-US (240V) 1 SolarEdge Technologies SE3000H-US (240V) | 2019-10-18 | 2019-10-28 | 6 | 2019-10-28 | [17 empty] | W
Central Hudson |  | Empire Solar Solutions | CH-11760 | Kingston | Kingston |  | 12401 | G | 1022 | East Kingston | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE 10000A-US (240V) | 2019-08-15 | 2019-08-28 | 9 | 2019-08-28 | [14 empty] | 2019-09-10 | 2019-09-16 |  | W
Central Hudson |  | Kasselman Solar | CH-11759 | Catskill | Ravena | Albany | 12143 | G | 1081 | New Baltimore | N | CH-03522 | 3 | [13 empty] | NM | N | 12 Enphase Energy M250-72-2LL-S2x (240V) | 2019-08-14 | 2019-08-22 | 6 | 2019-08-22 | [14 empty] | 2019-09-23 | 2019-09-23 |  | Y
Central Hudson |  | Tesla Energy | CH-11761 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6044 | Spackenkill | N |  | 10.4 | [13 empty] | NM | N | 2 Delta Electronics SOLIVIA 5.2 NA G4 TL (240V) [SI1] | 2019-08-26 | 2019-09-10 | 10 | 2019-09-10 | [14 empty] | 2019-11-05 | 2019-11-05 |  | Y
Central Hudson |  | New York State Solar Farm | CH-11758 | Poughkeepsie | Millerton | Dutchess | 12546 | G | 7081 | Millerton | N |  | 8.505 | [13 empty] | NM | N | 27 SunPower SPR-E20-327-E-AC (240V) | 2019-08-14 | 2019-08-22 | 6 | 2019-08-22 | [14 empty] | 2020-01-07 | 2020-01-13 |  | Y
Central Hudson |  | Lighthouse Solar | CH-11765 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 6074 | East Park | N |  | 3.77 | [13 empty] | NM | N | 13 Enphase Energy IQ7PLUS-72-x-US (240V) [SI1] | 2019-08-15 | 2019-08-28 | 9 | 2019-08-28 | [14 empty] | 2019-11-12 | 2019-11-13 |  | Y
Central Hudson |  | 1st Light Energy Inc. | CH-11764 | Newburgh | New Windsor |  | 12553 | G | 4095 | Bethlehem Rd | N |  | 6.8 | [13 empty] | NM | N | 1 SMA America SB3.8-1SP-US-40 (240V) [SI1] 1 SMA America SB3.0-1SP-US-40 (240V) [SI1] | 2019-10-01 | 2019-10-09 | 6 | 2019-10-09 | [17 empty] | W
Central Hudson |  | PlugPV | CH-11768 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8096 | Fishkill Plains | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2019-08-15 | 2019-08-28 | 9 | 2019-08-28 | [14 empty] | 2019-09-16 | 2019-09-18 |  | Y
Central Hudson |  | MOMENTUM SOLAR | CH-11769 | Newburgh | New Windsor | Orange | 12553 | G | 4044 | Union Ave | N |  | 5.04 | [13 empty] | NM | N | 21 Enphase Energy IQ7-60-x-US (240V) | 2019-08-28 | 2019-09-12 | 10 | 2019-09-12 | [17 empty] | W
Central Hudson |  | Suncommon | CH-11770 | Newburgh | New Paltz | Ulster | 12561 | G | 5023 | Ohioville | N | CH-10429 | 2.24 | [13 empty] | NM | N | 7 SunPower SPR-E20-327-D-AC (240V) [SI1] | 2019-09-03 | 2019-09-16 | 9 | 2019-09-16 | [14 empty] | 2019-10-09 | 2019-10-09 |  | Y
Central Hudson |  | Sunrun Installation Service, Inc. | CH-11771 | Fishkill | Cold Spg | Putnam | 10516 | G | 8063 | Merritt Park | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000H-US (208V) | 2019-08-15 | 2019-08-28 | 9 | 2019-08-28 | [14 empty] | 2019-09-30 | 2019-10-07 |  | Y
Central Hudson |  | Sunrun Installation Service, Inc. | CH-11772 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8071 | Shenandoah | N |  | 6 | [13 empty] | NM | N | 1 Ningbo Ginlong Technologies Solis-1P6K-4G-US | 2019-08-15 | 2019-08-28 | 9 | 2019-08-28 | [14 empty] | 2019-09-30 | 2019-10-07 |  | Y
Central Hudson |  | New York State Solar Farm | CH-11766 | Newburgh | Gardiner | Ulster | 12525 | G | 5031 | Galeville | Y | CH-11766 | 11.34 | 10 | [12 empty] | NM | N | 36 SunPower SPR-X21-350-BLK-E-AC (240V) 2TeslaAC Powerwall 2.0 | 2019-08-15 | 2019-08-28 | 9 | 2019-08-28 | [14 empty] | 2019-10-08 | 2019-10-09 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-11767 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6096 | Manchester | N |  | 2.64 | [13 empty] | NM | N | 11 Enphase Energy IQ7-60-x-US (240V) | 2019-08-28 | 2019-09-12 | 10 | 2019-09-12 | [14 empty] | 2019-10-09 | 2019-10-09 |  | Y
Central Hudson |  | Sunrun | CH-11777 | Newburgh | Marlboro | Ulster | 12542 | G | 5004 | Marlboro | N |  | 6 | [13 empty] | NM | N | 1 Ningbo Ginlong Technologies Solis-1P6K2-4G-US (240V) | 2019-08-16 | 2019-08-28 | 8 | 2019-08-28 | [14 empty] | 2019-09-18 | 2019-09-19 |  | Y
Central Hudson |  | New York State Solar Farm | CH-11776 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 6075 | East Park | N |  | 3.84 | [13 empty] | NM | N | 12 SunPower SPR-X22-360-E-AC (240V) | 2019-08-16 | 2019-08-28 | 8 | 2019-08-28 | [14 empty] | 2019-08-29 | 2019-09-06 |  | Y
Central Hudson |  | Tesla Energy | CH-11773 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8051 | North Chelsea | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE11400H-US (240V) [SI1] | 2019-08-29 | 2019-09-13 | 10 | 2019-09-13 | [14 empty] | 2019-09-26 | 2019-09-26 |  | Y
Central Hudson |  | Trinity Solar | CH-11775 | Newburgh | Wallkill | Ulster | 12589 | G | 5042 | East Walden | N |  | 3 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3000H-US (240V) | 2019-08-16 | 2019-08-28 | 8 | 2019-08-28 | [14 empty] | 2019-11-08 | 2019-11-11 |  | Y
Central Hudson |  | Trinity Solar | CH-11774 | Newburgh | Newburgh | Orange | 12550 | G | 5001 | Marlboro | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2019-09-25 | 2019-09-26 | 1 | 2019-09-26 | [14 empty] | 2019-11-08 | 2019-11-11 |  | Y
Central Hudson |  | Lighthouse Solar | CH-11778 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 6075 | East Park | N |  | 11.89 | [13 empty] | NM | N | 41 Enphase Energy IQ7PLUS-72-x-US (240V) | 2019-08-16 | 2019-08-30 | 10 | 2019-08-30 | [14 empty] | 2019-10-31 | 2019-11-01 |  | Y
Central Hudson |  | PlugPV LLC | CH-11779 | Newburgh | Campbell Hall | Orange | 10916 | G | 5051 | Maybrook | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2019-08-19 | 2019-09-03 | 10 | 2019-09-03 | [14 empty] | 2019-09-16 | 2019-09-18 |  | Y
Central Hudson |  | Suncommon | CH-11780 | Poughkeepsie | Tivoli | Dutchess | 12583 | G | 7054 | Rhinebeck | N | CH-11780 | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2019-09-03 | 2019-09-16 | 9 | 2019-09-16 | [14 empty] | 2019-10-18 | 2019-10-25 |  | Y
Central Hudson |  | New York State Solar Farm | CH-11782 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 7041 | Staatsburg | N |  | 7.56 | [13 empty] | NM | N | 24 SunPower SPR-X22-360-E-AC (240V) | 2019-08-20 | 2019-09-04 | 10 | 2019-09-04 | [14 empty] | 2019-09-06 | 2019-09-13 |  | Y
Central Hudson |  | Apex Solar Power | CH-11781 | Newburgh | New Paltz | Ulster | 12561 | G | 5023 | Ohioville | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2019-08-20 | 2019-09-04 | 10 | 2019-09-04 | [14 empty] | 2019-09-13 | 2019-09-18 |  | Y
Central Hudson |  | Lighthouse Solar | CH-11784 | Newburgh | New Paltz | Ulster | 12561 | G | 5031 | Galeville | N |  | 6.96 | [13 empty] | NM | N | 24 Enphase Energy IQ7PLUS-72-x-US (240V) | 2019-09-05 | 2019-09-05 | 0 | 2019-09-05 | [14 empty] | 2019-09-13 | 2019-09-18 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-11783 | Newburgh | Newburgh |  | 12550 | G | 4022 | Coldenham | N |  | 12 | [13 empty] | NM | N | 2 SolarEdge Technologies SE6000 (240V) | 2019-08-21 | 2019-09-05 | 10 | 2019-09-05 | [14 empty] | 2019-09-05 | 2019-09-12 |  | W
Central Hudson |  | PlugPV LLC | CH-11785 | Kingston | Port Ewen | Ulster | 12466 | G | 1012 | Boulevard | N |  | 9.8 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) 1 SolarEdge Technologies SE3800H-US (240V) | 2019-09-06 | 2019-09-18 | 8 | 2019-09-18 | [14 empty] | 2019-09-23 | 2019-09-27 |  | Y
Central Hudson |  | PlugPV LLC | CH-11788 | Poughkeepsie | Poughkeepsie |  | 12603 | G | 6093 | Manchester | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2019-08-22 | 2019-09-06 | 10 | 2019-09-06 | [17 empty] | W
Central Hudson |  | Kasselman Solar | CH-11786 | Catskill | Berne | Albany | 12023 | G | 1092 | Westerlo | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE11400H-US (240V) | 2019-08-22 | 2019-09-06 | 10 | 2019-09-06 | [14 empty] | 2019-09-11 | 2019-09-16 |  | Y
Central Hudson |  | Hudson River Renewables | CH-11787 | Kingston | High Fls | Ulster | 12440 | G | 3024 | High Falls | N |  | 7.68 | [13 empty] | NM | N | 1 SMA America SB7700TL-US-22 (240V) | 2019-08-22 | 2019-09-06 | 10 | 2019-09-06 | [14 empty] | 2019-09-12 | 2019-09-25 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-11792 | Kingston | Kingston |  | 12401 | G | 1012 | Boulevard | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE 10000A-US (240V) | 2019-08-23 | 2019-09-09 | 10 | 2019-09-09 | [14 empty] | 2019-11-04 | 2019-11-04 |  | W
Central Hudson |  | Empire Solar Solutions | CH-11789 | Kingston | Hurley |  | 12443 | G | 2094 | Hurley Ave | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600A-US (240V) | 2019-09-16 | 2019-09-20 | 4 | 2019-09-20 | [14 empty] | 2019-09-23 | 2019-09-25 |  | W
Central Hudson |  | Sunrun Installation Service, Inc. | CH-11794 | Fishkill | Wappingrs Fls |  | 12590 | G | 8046 | Myers Corners | N |  | 6 | [13 empty] | NM | N | 1 Ningbo Ginlong Technologies Solis-1P6K-4G-US | 2019-08-23 | 2019-09-09 | 10 | 2019-09-09 | [17 empty] | W
Central Hudson |  | Empire Solar Solutions | CH-11790 | Fishkill | Beacon |  | 12508 | G | 8085 | Tioronda | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000 (240V) | 2019-08-23 | 2019-09-09 | 10 | 2019-09-09 | [14 empty] | 2019-09-09 | 2019-09-13 |  | W
Central Hudson |  | New York State Solar Farm | CH-11791 | Newburgh | Highland | Ulster | 12528 | G | 5083 | Highland | N |  | 3.141 | [13 empty] | NM | N | 9 SunPower SPR-A400-G-AC (240V) | 2019-08-23 | 2019-09-09 | 10 | 2019-09-09 | [14 empty] | 2019-09-20 | 2019-09-23 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-11793 | Fishkill | Fishkill |  | 12524 | G | 8012 | Forgebrook | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600A-US (240V) | 2019-08-23 | 2019-09-09 | 10 | 2019-09-09 | [14 empty] | 2019-09-09 | 2019-09-13 |  | W
Central Hudson |  | Empire Solar Solutions | CH-11795 | Kingston | Kingston |  | 12401 | G | 1022 | East Kingston | N |  | 3 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3000 (240V) | 2019-08-26 | 2019-09-10 | 10 | 2019-09-10 | [14 empty] | 2019-09-10 | 2019-09-16 |  | W
Central Hudson |  | New York State Solar Farm | CH-11796 | Fishkill | Garrison | Putnam | 10524 | G | 8086 | Tioronda | N |  | 7.56 | [13 empty] | NM | N | 24 SunPower SPR-X22-360-E-AC (240V) | 2019-09-11 | 2019-09-19 | 6 | 2019-09-19 | [14 empty] | 2019-09-20 | 2019-09-23 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-11797 | Newburgh | Marlboro | Ulster | 12542 | G | 5004 | Marlboro | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE 11400A-US (240V) | 2019-08-26 | 2019-09-10 | 10 | 2019-09-10 | [8 empty] | 350 | 350 |  | 2019-09-12 | 2019-09-12 | 2019-11-06 | 2019-11-06 | 2019-11-07 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-11801 | Newburgh | Highland | Ulster | 12528 | G | 5022 | Ohioville | N |  | 5.22 | [13 empty] | NM | N | 18 Enphase Energy IQ7PLUS-72-x-US (240V) | 2019-08-27 | 2019-09-11 | 10 | 2019-09-11 | [14 empty] | 2019-12-03 | 2019-12-10 |  | Y
Central Hudson |  | Solar Image | CH-11799 | Newburgh | Campbell Hall | Orange | 10916 | G | 5051 | Maybrook | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2019-08-27 | 2019-09-11 | 10 | 2019-09-11 | [14 empty] | 2019-09-23 | 2019-09-23 |  | Y
Central Hudson |  | Tesla Energy Operations | CH-11798 | Newburgh | New Paltz | Ulster | 12561 | G | 5031 | Galeville | Y | CH-06957 |  | 10 | [12 empty] | NM | N | 2TeslaAC Powerwall 2.0 | 2019-09-13 | 2019-09-20 | 5 | 2019-09-20 | [14 empty] | 2020-09-01 | 2020-09-01 |  | Y
Central Hudson |  | Solar Generation | CH-11800 | Kingston | Mt Tremper | Ulster | 12457 | G | 3012 | Woodstock | N | CH-08175 | 3 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3000H-US (240V) | 2019-08-27 | 2019-09-11 | 10 | 2019-09-11 | [14 empty] | 2020-02-18 | 2020-02-18 |  | Y
Central Hudson |  | Bright Planet Solar | CH-11808 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6094 | Manchester | N |  | 3.8 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3800H-US (240V) [SI1] | 2019-09-24 | 2019-09-25 | 1 | 2019-09-25 | [14 empty] | 2019-12-04 | 2019-12-10 |  | Y
Central Hudson |  | Vivint Solar Developer, LLC | CH-11809 | Fishkill | Beacon | Dutchess | 12508 | G | 8015 | Forgebrook | N |  | 9.2 | [13 empty] | NM | N | 40 Enphase Energy IQ6-60-X-US (240V) | 2019-08-28 | 2019-09-12 | 10 | 2019-09-12 | [14 empty] | 2019-10-15 | 2019-10-16 |  | Y
Central Hudson |  | Sky Solar Inc. | CH-11802 | Fishkill | Wappinger |  | 12590 | G | 8091 | Fishkill Plains | N |  | 2500 | [13 empty] | CDG | Y | 20 Sungrow Power Supply SG125HV (600V) | 2019-10-15 | 2019-10-28 | 9 | 2019-10-28 | 2019-10-28 | 2019-11-18 | 15 | 2019-12-20 | 2020-02-07 | 2020-05-05 | 60 | 10154.2 | 1556544.17 | [7 empty] | 2020-12-04 | W
Central Hudson |  | Sky Solar Inc. | CH-11804 | Fishkill | Wappinger |  | 12590 | G | 8091 | Fishkill Plains | N |  | 4000 | [13 empty] | CDG | Y | 32 Sungrow Power Supply SG125HV (600V) | 2019-10-15 | 2019-10-28 | 9 | 2019-10-28 | 2019-10-28 | 2019-11-18 | 15 | 2019-12-20 | 2020-02-07 | 2020-05-05 | 60 | 10154.2 | 1556544.16 | [7 empty] | 2020-12-04 | W
Central Hudson |  | Sky Solar Inc. | CH-11803 | Fishkill | Wappinger |  | 12590 | G | 8091 | Fishkill Plains | N |  | 4000 | [13 empty] | CDG | Y | 32 Sungrow Power Supply SG125HV (600V) | 2019-10-15 | 2019-10-28 | 9 | 2019-10-28 | 2019-10-28 | 2019-11-18 | 15 | 2019-12-20 | 2020-02-07 | 2020-05-05 | 60 | 10154.2 | 1556544.17 | [7 empty] | 2020-12-04 | W
Central Hudson |  | Suncommon | CH-11806 | Fishkill | Garrison | Putnam | 10524 | G | 8086 | Tioronda | N |  | 22.8 | [13 empty] | NM | N | 2 SolarEdge Technologies SE11400H-US (240V) | 2019-08-28 | 2019-09-12 | 10 | 2019-09-12 | [8 empty] | 350 | 350 |  | 2019-09-19 | 2019-09-19 | 2019-10-27 | 2019-11-11 | 2019-11-12 |  | Y
Central Hudson |  | Suncommon | CH-11807 | Catskill | Catskill |  | 12414 | G | 2004 | North Catskill | N |  | 20 | [13 empty] | NM | N | 2 SolarEdge Technologies SE10000H-US (240V) | 2019-08-28 | 2019-09-12 | 10 | 2019-09-12 | [11 empty] | 2019-09-19 | 2019-09-19 | 2020-12-10 |  |  |  | W
Central Hudson |  | Suncommon | CH-11805 | Catskill | Lexington | Greene | 12452 | E | 2389 | Vinegar Hill | N |  | 3.8 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3800H-US (240V) | 2019-09-23 | 2019-09-23 | 0 | 2019-09-23 | [14 empty] | 2019-10-04 | 2019-10-08 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-11813 | Newburgh | Montgomery |  | 12549 | G | 5054 | Maybrook | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE 11400A-US (240V) | 2019-08-29 | 2019-09-13 | 10 | 2019-09-13 | [14 empty] | 2019-09-13 | 2019-09-18 |  | W
Central Hudson |  | New York State Solar Farm | CH-11811 | Newburgh | Montgomery | Orange | 12549 | G | 5071 | Montgomery | N |  | 7.68 | [13 empty] | NM | N | 24 SunPower SPR-X22-360-E-AC (240V) | 2019-09-13 | 2019-09-19 | 4 | 2019-09-19 | [14 empty] | 2019-09-25 | 2019-09-25 |  | Y
Central Hudson |  | Tesla Energy Operations | CH-11810 | Kingston | Mt Tremper | Ulster | 12457 | G | 3012 | Woodstock | Y |  | 3.8 | 5 | [12 empty] | NM | N | 1 SolarEdge Technologies SE3800H-US (240V) [SI1] 1TeslaAC Powerwall 2.0 | 2019-10-15 | 2019-10-24 | 7 | 2019-10-24 | [14 empty] | 2020-02-07 | 2020-02-10 |  | Y
Central Hudson |  | Tesla Energy Operations | CH-11812 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6056 | Todd Hill | Y |  | 12.6 | 10 | [12 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) [SI1] 1 SolarEdge Technologies SE5000H-US (208V) [SI1] 2TeslaAC Powerwall 2.0 | 2019-08-29 | 2019-09-13 | 10 | 2019-09-13 | [14 empty] | 2019-10-11 | 2019-10-15 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-11816 | Newburgh | Newburgh | Orange | 12550 | G | 4022 | Coldenham | N |  | 4.6 | [13 empty] | NM | N | 1 Ningbo Ginlong Technologies Solis-1P4.6K-4G-US (240V) | 2019-08-30 | 2019-09-13 | 9 | 2019-09-13 | [14 empty] | 2019-12-10 | 2019-12-10 |  | Y
Central Hudson |  | PlugPV LLC | CH-11815 | Kingston | Kerhonkson | Ulster | 12446 | G | 3082 | Kerhonkson | Y | CH-00300 | 5 | 5 | [12 empty] | NM | N | 1 SolarEdge Technologies SE5000H-US (240V) 1TeslaAC Powerwall 2.0 | 2019-10-25 | 2019-10-25 | 0 | 2019-10-25 | [14 empty] | 2020-03-12 | 2020-03-17 |  | Y
Central Hudson |  | PlugPV LLC | CH-11814 | Catskill | Athens | Greene | 12015 | G | 1074 | Coxsackie | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2019-08-30 | 2019-09-13 | 9 | 2019-09-13 | [14 empty] | 2019-10-08 | 2019-10-11 |  | Y
Central Hudson |  | Sunrun Installation Service, Inc. | CH-11817 | Newburgh | Newburgh | Orange | 12550 | G | 4023 | Coldenham | N |  | 7.6 | [13 empty] | NM | N | 1 Ningbo Ginlong Technologies Solis-1P7.6K-4G-US | 2019-09-25 | 2019-09-26 | 1 | 2019-09-26 | [14 empty] | 2020-01-09 | 2020-01-09 |  | Y
Central Hudson |  | Apex Solar, LLC | CH-11819 | Newburgh | New Windsor | Orange | 12553 | G | 4046 | Union Ave | N |  | 7.329 | [13 empty] | NM | N | 21SunPowerSPR-A-400-G-AC | 2019-09-16 | 2019-09-20 | 4 | 2019-09-20 | [14 empty] | 2020-02-11 | 2020-02-12 |  | Y
Central Hudson |  | Sunrun Installation Service, Inc. | CH-11820 | Kingston | Kingston |  | 12401 | G | 1022 | East Kingston | N |  | 3 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3000H-US (240V) | 2019-09-03 | 2019-09-16 | 9 | 2019-09-16 | [17 empty] | W
Central Hudson |  | New York State Solar Farm | CH-11821 | Newburgh | New Windsor | Orange | 12553 | G | 4094 | Bethlehem Rd | N |  | 7.245 | [13 empty] | NM | N | 23 SunPower SPR-X22-360-E-AC (240V) | 2019-09-04 | 2019-09-16 | 8 | 2019-09-16 | [14 empty] | 2019-10-08 | 2019-10-14 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-11822 | Poughkeepsie | Poughkeepsie |  | 12603 | G | 6043 | Spackenkill | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600A-US (240V) | 2019-09-05 | 2019-09-16 | 7 | 2019-09-16 | [14 empty] | 2019-09-18 | 2019-09-19 |  | W
Central Hudson |  | Apex Solar Power, LLC | CH-11823 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6092 | Manchester | N |  | 7.88 | [13 empty] | NM | N | 25 SunPower SPR-X22-360-E-AC (240V) | 2019-09-16 | 2019-09-20 | 4 | 2019-09-20 | [14 empty] | 2020-02-20 | 2020-02-26 |  | Y
Central Hudson |  | PlugPV LLC | CH-11826 | Newburgh | Milton | Ulster | 12547 | G | 5003 | Marlboro | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2019-09-05 | 2019-09-16 | 7 | 2019-09-16 | [8 empty] | 350 | 350 |  | 2019-09-18 | 2019-09-18 | 2019-10-30 | 2019-11-11 | 2019-11-12 |  | Y
Central Hudson |  | New York State Solar Farm | CH-11824 | Kingston | Stone Ridge | Ulster | 12484 | G | 3023 | High Falls | N |  | 8.82 | [13 empty] | NM | N | 28 SunPower SPR-E19-320-E-AC (240V) | 2019-09-05 | 2019-09-16 | 7 | 2019-09-16 | [8 empty] | 350 | 350 |  | 2019-09-23 | 2019-09-23 | 2019-11-04 | 2019-11-15 | 2019-11-19 |  | Y
Central Hudson |  | Solar Generation | CH-11827 | Kingston | Woodstock | Ulster | 12498 | G | 3013 | Woodstock | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000H-US (240V) | 2019-09-05 | 2019-09-16 | 7 | 2019-09-16 | [14 empty] | 2019-10-02 | 2019-10-07 |  | Y
Central Hudson |  | New York State Solar Farm | CH-11825 | Poughkeepsie | Clinton Cors | Dutchess | 12514 | G | 7013 | Hibernia | N | CH-10528 | 3.15 | [13 empty] | NM | N | 10 SunPower SPR-X21-350-BLK-E-AC (240V) | 2019-09-05 | 2019-09-16 | 7 | 2019-09-16 | [14 empty] | 2019-10-07 | 2019-10-08 |  | Y
Central Hudson |  | Sunrun Inc | CH-11835 | Newburgh | Newburgh | Orange | 12550 | G | 5001 | Marlboro | N |  | 12 | [13 empty] | NM | N | 1 Ningbo Ginlong Technologies Solis-1P9K-4G-US 1 Ningbo Ginlong Technologies Solis-1P3K-4G-US (240V) [SI1] | 2019-09-26 | 2019-09-26 | 0 | 2019-09-26 | [14 empty] | 2019-10-25 | 2019-10-31 |  | Y
Central Hudson |  | Sunrun Installation Service, Inc. | CH-11834 | Newburgh | Newburgh | Orange | 12550 | G | 4023 | Coldenham | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2019-09-26 | 2019-09-26 | 0 | 2019-09-26 | [14 empty] | 2019-11-27 | 2019-12-06 |  | Y
Central Hudson |  | PlugPV LLC | CH-11831 | Newburgh | Marlboro | Ulster | 12542 | G | 5003 | Marlboro | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2019-09-23 | 2019-09-23 | 0 | 2019-09-23 | [14 empty] | 2019-10-07 | 2019-10-08 |  | Y
Central Hudson |  | PlugPV LLC | CH-11832 | Newburgh | Newburgh | Orange | 12550 | G | 4027 | Coldenham | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2019-09-06 | 2019-09-17 | 7 | 2019-09-17 | [14 empty] | 2019-11-19 | 2019-11-22 |  | Y
Central Hudson |  | Trinity Solar | CH-11833 | Fishkill | Beacon | Dutchess | 12508 | G | 8087 | Tioronda | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2019-09-25 | 2019-09-26 | 1 | 2019-09-26 | [14 empty] | 2019-11-08 | 2019-11-11 |  | Y
Central Hudson |  | Suncommon | CH-11829 | Poughkeepsie | Poughkeepsie |  | 12603 | G | 6092 | Manchester | N |  | 15.2 | [13 empty] | NM | N | 2 SolarEdge Technologies SE7600H-US (240V) | 2019-09-06 | 2019-09-17 | 7 | 2019-09-17 | [8 empty] | 350 | 350 |  | 2019-09-19 | 2019-09-19 | 2019-09-30 |  |  |  | W
Central Hudson |  | Suncommon | CH-11838 | Newburgh | Wallkill | Ulster | 12589 | G | 5041 | East Walden | N | CH-10617 | 6.4 | [13 empty] | NM | N | 20 SunPower SPR-X21-345-D-AC (240V) | 2019-09-20 | 2019-09-20 | 0 | 2019-09-20 | [8 empty] | 350 | 350 |  | 2019-09-30 | 2019-09-30 | 2019-11-26 | 2019-12-03 | 2019-12-03 |  | Y
Central Hudson |  | New York State Solar Farm | CH-11839 | Newburgh | Clintondale | Ulster | 12515 | G | 5012 | Modena | N |  | 6.93 | [13 empty] | NM | N | 22 SunPower SPR-E20-327-E-AC (240V) | 2019-09-18 | 2019-09-20 | 2 | 2019-09-20 | [14 empty] | 2019-10-07 | 2019-10-08 |  | Y
Central Hudson |  | Suncommon | CH-11828 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 6074 | East Park | N |  | 10.56 | [13 empty] | NM | N | 33 SunPower SPR-X21-345-D-AC (240V) | 2019-09-23 | 2019-09-23 | 0 | 2019-09-23 | [14 empty] | 2020-01-07 | 2020-01-07 |  | Y
Central Hudson |  | Suncommon | CH-11830 | Newburgh | New Paltz | Ulster | 12561 | G | 5011 | Modena | Y | CH-01557 |  | 10 | [12 empty] | NM | N | 2TeslaAC Powerwall 2.0 | 2019-09-06 | 2019-09-17 | 7 | 2019-09-17 | [14 empty] | 2019-12-03 | 2019-12-03 |  | Y
Central Hudson |  | Sunrun Installation Service, Inc. | CH-11836 | Newburgh | Newburgh | Orange | 12550 | G | 4042 | Union Ave | N |  | 4.6 | [13 empty] | NM | N | 1 Ningbo Ginlong Technologies Solis-1P4.6K-4G-US (240V) | 2019-09-06 | 2019-09-17 | 7 | 2019-09-17 | [14 empty] | 2019-11-04 | 2019-11-08 |  | Y
Central Hudson |  | Lighthouse Solar | CH-11837 | Newburgh | New Paltz | Ulster | 12561 | G | 5011 | Modena | N |  | 15.37 | [13 empty] | NM | N | 53 Enphase Energy IQ7PLUS-72-x-US (240V) | 2019-09-06 | 2019-09-17 | 7 | 2019-09-17 | [8 empty] | 350 | 350 |  | 2019-09-19 | 2019-09-19 | 2019-11-08 | 2019-11-18 | 2019-11-18 |  | Y
Central Hudson |  | Solar Generation | CH-11841 | Kingston | Hurley | Ulster | 12443 | G | 2093 | Hurley Ave | N |  | 7.6 | [13 empty] | NM | N | 1 Pika Energy X7602 (240V) | 2019-09-24 | 2019-09-24 | 0 | 2019-09-24 | [14 empty] | 2019-09-25 | 2019-10-02 |  | Y
Central Hudson |  | Sunrun Installation Service, Inc. | CH-11845 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6046 | Spackenkill | N |  | 4 | [13 empty] | NM | N | 1 Ningbo Ginlong Technologies Solis-1P4K-4G-US (240V) | 2019-09-19 | 2019-09-20 | 1 | 2019-09-20 | [14 empty] | 2019-10-09 | 2019-10-11 |  | Y
Central Hudson |  | NY Solar 1001 LLC | CH-11844 | Newburgh | Walkill |  | 12589 | G | 5043 | East Walden | N |  | 4500 | [13 empty] | CDG | Y | 45Chint Power Systems AmericaCPS SCH100KTL-DO/US-600 | 2019-12-23 | 2020-01-09 | 10 | 2020-01-09 | 2020-01-09 | 2020-01-27 | 12 | 2020-03-03 | 2020-03-26 | 2020-06-22 | 60 | 12657.51 | 1983092.5 | [7 empty] | 2020-12-18 | W
Central Hudson |  | Lighthouse Solar | CH-11840 | Newburgh | New Paltz | Ulster | 12561 | G | 5011 | Modena | N |  | 11.02 | [13 empty] | NM | N | 38 Enphase Energy IQ7PLUS-72-x-US (240V) | 2019-09-16 | 2019-09-20 | 4 | 2019-09-20 | [14 empty] | 2019-11-20 | 2019-11-20 |  | Y
Central Hudson |  | New York State Solar Farm | CH-11842 | Poughkeepsie | Staatsburg | Dutchess | 12580 | G | 7041 | Staatsburg | N |  | 6.93 | [13 empty] | NM | N | 22 SunPower SPR-X22-360-E-AC (240V) | 2019-09-19 | 2019-09-20 | 1 | 2019-09-20 | [14 empty] | 2019-10-11 | 2019-10-17 |  | Y
Central Hudson |  | Sunrun Installation Service, Inc. | CH-11843 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8091 | Fishkill Plains | Y |  | 7.6 | 7.6 | [12 empty] | NM | N | 1 SolarEdge Technologies SE7600A-US (208V) [SI1] 1SolarEdge TechnologiesSE7600A-US | 2019-10-17 | 2019-10-28 | 7 | 2019-10-28 | [14 empty] | 2020-02-12 | 2020-02-13 |  | Y
Central Hudson |  | Tesla Energy Operations | CH-11846 | Kingston | Ellenvl | Ulster | 12428 | G | 3076 | Greenfield Rd | Y |  | 17.6 | 10 | [12 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) [SI1] 1 SolarEdge Technologies SE10000H-US (240V) 2TeslaAC Powerwall 2.0 | 2019-09-19 | 2019-09-20 | 1 | 2019-09-20 | [14 empty] | 2019-12-20 | 2019-12-26 |  | Y
Central Hudson |  | Suncommon | CH-11849 | Kingston | Saugerties | Ulster | 12477 | G | 3001 | Saugerties | N | CH-01716 | 4.8 | [13 empty] | NM | N | 15 SunPower SPR-X22-360-D-AC (240V) | 2019-09-10 | 2019-09-19 | 7 | 2019-09-19 | [14 empty] | 2020-02-05 | 2020-02-06 |  | Y
Central Hudson |  | New York State Solar Farm | CH-11851 | Fishkill | Beacon | Dutchess | 12508 | G | 8017 | Forgebrook | N |  | 7.245 | [13 empty] | NM | N | 23 SunPower SPR-X22-360-E-AC (240V) | 2019-09-19 | 2019-09-20 | 1 | 2019-09-20 | [14 empty] | 2019-10-21 | 2019-10-23 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-11847 | Newburgh | New Windsor |  | 12553 | G | 4043 | Union Ave | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE 10000A-US (240V) | 2019-09-10 | 2019-09-19 | 7 | 2019-09-19 | [14 empty] | 2019-09-19 | 2019-09-19 |  | W
Central Hudson |  | New York State Solar Farm | CH-11848 | Kingston | Grahamsvl | Sullivan | 12740 | G | 3091 | Neversink | N |  | 7.245 | [13 empty] | NM | N | 23 SunPower SPR-X21-350-BLK-E-AC (240V) | 2019-09-19 | 2019-09-20 | 1 | 2019-09-20 | [14 empty] | 2019-10-02 | 2019-10-07 |  | Y
Central Hudson |  | YSG Solar Installers LLC | CH-11850 | Kingston | Ulster Pk | Ulster | 12487 | G | 3041 | Sturgeon Pool | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE 10000A-US (240V) | 2019-09-26 | 2019-09-26 | 0 | 2019-09-26 | [14 empty] | 2020-03-20 | 2020-03-20 |  | Y
Central Hudson |  | PlugPV LLC | CH-11853 | Newburgh | Newburgh | Orange | 12550 | G | 4013 | West Balmville | N |  | 16 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) 1 SolarEdge Technologies SE6000H-US (240V) | 2019-09-23 | 2019-09-23 | 0 | 2019-09-23 | [14 empty] | 2019-10-22 | 2019-10-24 |  | Y
Central Hudson |  | Sunrun Installation Service, Inc. | CH-11854 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8043 | Myers Corners | N |  | 7.6 | [13 empty] | NM | N | 1 Ningbo Ginlong Technologies Solis-1P7.6K-4G-US | 2019-09-11 | 2019-09-19 | 6 | 2019-09-19 | [14 empty] | 2019-10-22 | 2019-10-24 |  | Y
Central Hudson |  | Solar Generation | CH-11852 | Kingston | Woodstock | Ulster | 12498 | G | 3012 | Woodstock | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2019-09-19 | 2019-09-20 | 1 | 2019-09-20 | [14 empty] | 2019-12-17 | 2019-12-19 |  | Y
Central Hudson |  | Kasselman Solar | CH-11855 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8023 | Knapps Corners | N | CH-11855 | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000H-US (240V) | 2019-09-12 | 2019-09-19 | 5 | 2019-09-19 | [14 empty] | 2019-09-19 | 2019-09-19 |  | Y
Central Hudson |  | Sunrun Installation Service, Inc. | CH-11856 | Poughkeepsie | Hyde Park | Dutchess | 12538 | G | 6073 | East Park | N | CH-11856 | 3.6 | [13 empty] | NM | N | 1 Ningbo Ginlong Technologies Solis-1P3.6K-4G-US (240V) | 2019-09-24 | 2019-09-25 | 1 | 2019-09-25 | [14 empty] | 2019-10-14 | 2019-10-17 |  | Y
Central Hudson |  | Suncommon | CH-11857 | Kingston | Saugerties | Ulster | 12477 | G | 2016 | Lincoln Park | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2019-09-12 | 2019-09-19 | 5 | 2019-09-19 | [14 empty] | 2019-12-04 | 2019-12-16 |  | Y
Central Hudson |  | Self | CH-11858 | Newburgh | Wallkill | Ulster | 12589 | G | 5041 | East Walden | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2019-09-12 | 2019-09-19 | 5 | 2019-09-19 | [14 empty] | 2019-10-23 | 2019-10-23 |  | Y
Central Hudson |  | Apex Solar Power, LLC | CH-11859 | Fishkill | Fishkill | Dutchess | 12524 | G | 8094 | Fishkill Plains | N |  | 10.47 | [13 empty] | NM | N | 30SunPowerSPR-A-400-G-AC | 2019-09-12 | 2019-09-19 | 5 | 2019-09-19 | [14 empty] | 2020-02-06 | 2020-02-06 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-11860 | Newburgh | Maybrook |  | 12543 | G | 5052 | Maybrook | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000 (240V) | 2019-09-13 | 2019-09-19 | 4 | 2019-09-19 | [14 empty] | 2019-10-25 | 2019-10-29 |  | W
Central Hudson |  | Sun Mountain | CH-11861 | Kingston | Stone Ridge | Ulster | 12484 | G | 3024 | High Falls | N |  | 10.7 | [13 empty] | NM | N | 1 SMA America SB7.7-1SP-US-40 (240V) 1 SMA America SB3.0-1SP-US-40 (240V) [SI1] | 2019-09-27 | 2019-10-03 | 4 | 2019-10-03 | [8 empty] | 350 | 350 |  | 2019-10-08 | 2019-10-08 | 2019-12-12 | 2019-12-30 | 2019-12-30 |  | Y
Central Hudson |  | Vivint Solar Developer, LLC | CH-11862 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8091 | Fishkill Plains | N |  | 13.11 | [13 empty] | NM | N | 57 Enphase Energy IQ6-60-X-US (240V) | 2019-09-16 | 2019-09-20 | 4 | 2019-09-20 | [17 empty] | W
Central Hudson |  | Lighthouse Solar | CH-11864 | Newburgh | Highland | Ulster | 12528 | G | 5084 | Highland | N |  | 4.06 | [13 empty] | NM | N | 14 Enphase Energy IQ7PLUS-72-x-US (240V) | 2019-09-26 | 2019-09-26 | 0 | 2019-09-26 | [14 empty] | 2019-10-31 | 2019-11-01 |  | Y
Central Hudson |  | Sunrun Installation Service, Inc. | CH-11865 | Newburgh | Newburgh | Orange | 12550 | G | 4044 | Union Ave | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000H-US (240V) | 2019-09-16 | 2019-09-20 | 4 | 2019-09-20 | [14 empty] | 2019-11-13 | 2019-11-14 |  | Y
Central Hudson |  | Kasselman Solar | CH-11863 | Kingston | Saugerties | Ulster | 12477 | G | 3002 | Saugerties | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2019-09-16 | 2019-09-20 | 4 | 2019-09-20 | [14 empty] | 2019-09-23 | 2019-09-23 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-11866 | Newburgh | Cornwall |  | 12518 | G | 4041 | Union Ave | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000 (240V) | 2019-09-16 | 2019-09-20 | 4 | 2019-09-20 | [14 empty] | 2019-11-04 | 2019-11-04 |  | W
Central Hudson |  | Kasselman Solar | CH-11867 | Kingston | Kerhonkson | Ulster | 12446 | G | 3083 | Kerhonkson | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2019-09-16 | 2019-09-20 | 4 | 2019-09-20 | [14 empty] | 2019-10-18 | 2019-10-18 |  | Y
Central Hudson |  | Kasselman Solar | CH-11869 | Poughkeepsie | Poughquag | Dutchess | 12570 | G | 6055 | Todd Hill | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE11400H-US (240V) | 2019-09-20 | 2019-09-20 | 0 | 2019-09-20 | [8 empty] | 350 | 350 |  | 2019-09-24 | 2019-09-24 | 2019-09-30 | 2019-12-19 | 2019-12-20 |  | Y
Central Hudson |  | Kasselman Solar | CH-11868 | Kingston | High Fls | Ulster | 12440 | G | 3022 | High Falls | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2019-09-20 | 2019-09-20 | 0 | 2019-09-20 | [8 empty] | 350 | 350 |  | 2019-09-24 | 2019-09-24 | 2019-11-04 | 2019-11-06 | 2019-11-08 |  | Y
Central Hudson |  | Kasselman Solar | CH-11871 | Kingston | Kingston | Ulster | 12401 | G | 111 | South Wall St | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000H-US (240V) | 2019-09-18 | 2019-09-20 | 2 | 2019-09-20 | [14 empty] | 2019-10-08 | 2019-10-09 |  | Y
Central Hudson |  | Kasselman Solar | CH-11870 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8051 | North Chelsea | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2019-09-20 | 2019-09-20 | 0 | 2019-09-20 | [14 empty] | 2019-10-29 | 2019-11-04 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-11872 | Newburgh | Rock Tvrn | Orange | 12575 | G | 4097 | Bethlehem Rd | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600A-US (240V) | 2019-09-18 | 2019-09-20 | 2 | 2019-09-20 | [8 empty] | 350 | 350 |  | 2019-09-24 | 2019-09-24 | 2019-11-25 | 2019-11-26 | 2019-11-26 |  | Y
Central Hudson |  | Vivint Solar Developer, LLC | CH-11878 | Newburgh | Campbell Hall | Orange | 10916 | G | 5052 | Maybrook | N | CH-11878 | 2.99 | [13 empty] | NM | N | 13 Enphase Energy IQ6-60-X-US (240V) | 2019-10-17 | 2019-10-28 | 7 | 2019-10-28 | [14 empty] | 2020-01-24 | 2020-01-27 |  | Y
Central Hudson |  | Suncommon | CH-11875 | Catskill | Preston Holw | Albany | 12469 | G | 1092 | Westerlo | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2019-09-19 | 2019-09-20 | 1 | 2019-09-20 | [14 empty] | 2019-11-18 | 2019-11-19 |  | Y
Central Hudson |  | Sunrun Installation Service, Inc. | CH-11877 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6046 | Spackenkill | N |  | 7.6 | [13 empty] | NM | N | 1 Ningbo Ginlong Technologies Solis-1P7.6K-4G-US | 2019-09-19 | 2019-09-20 | 1 | 2019-09-20 | [14 empty] | 2019-10-22 | 2019-10-24 |  | Y
Central Hudson |  | Kasselman Solar | CH-11876 | Poughkeepsie | Lagrangevl | Dutchess | 12540 | G | 6055 | Todd Hill | N | CH-11241 | 2.9 | [13 empty] | NM | N | 10 Enphase Energy IQ7PLUS-72-x-US (240V) | 2019-09-20 | 2019-09-20 | 0 | 2019-09-20 | [14 empty] | 2020-09-14 | 2020-09-14 |  | Y
Central Hudson |  | Sunrun Installation Service, Inc. | CH-11880 | Newburgh | New Windsor | Orange | 12553 | G | 4046 | Union Ave | N |  | 6 | [13 empty] | NM | N | 1 Ningbo Ginlong Technologies Solis-1P6K-4G-US | 2019-09-30 | 2019-10-08 | 6 | 2019-10-08 | [14 empty] | 2019-11-18 | 2019-11-22 |  | Y
Central Hudson |  | Sunrun Installation Service, Inc. | CH-11879 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8091 | Fishkill Plains | N |  | 17.6 | [13 empty] | NM | N | 1 Ningbo Ginlong Technologies Solis-1P10K-4G-US 1 Ningbo Ginlong Technologies Solis-1P7.6K-4G-US | 2019-09-20 | 2019-09-20 | 0 | 2019-09-20 | [8 empty] | 350 | 350 |  | 2019-10-08 | 2019-10-08 | 2019-12-30 | 2020-01-08 | 2020-01-09 |  | Y
Central Hudson |  | Sunrun Installation Service, Inc. | CH-11881 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8045 | Myers Corners | N |  | 6 | [13 empty] | NM | N | 1 Ningbo Ginlong Technologies Solis-1P6K-4G-US | 2019-09-24 | 2019-09-25 | 1 | 2019-09-25 | [14 empty] | 2019-10-10 | 2019-10-15 |  | Y
Central Hudson |  | Apex Roofing, LLC dba Seamless Solar | CH-11883 | Newburgh | New Windsor | Orange | 12553 | G | 4044 | Union Ave | N |  | 25 | [13 empty] | NM | N | 2 SolarEdge Technologies SE10000H-US (240V) 1 SolarEdge Technologies SE5000H-US (240V) | 2019-10-29 | 2019-10-29 | 0 | 2019-10-29 | [14 empty] | 2020-03-30 | 2020-03-30 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-11882 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6043 | Spackenkill | N |  | 3.36 | [13 empty] | NM | N | 14 Enphase Energy IQ7-60-x-US (240V) | 2019-09-24 | 2019-09-24 | 0 | 2019-09-24 | [14 empty] | 2019-11-06 | 2019-11-07 |  | Y
Central Hudson |  | New York State Solar Farm | CH-11884 | Catskill | Berne | Albany | 12023 | G | 1092 | Westerlo | N | CH-11884 | 5.04 | [13 empty] | NM | N | 16 SunPower SPR-X22-360-E-AC (240V) | 2019-09-23 | 2019-09-23 | 0 | 2019-09-23 | [14 empty] | 2019-11-11 | 2019-11-13 |  | Y
Central Hudson |  | Tesla Energy Operations, Inc. | CH-11885 | Newburgh | Maybrook | Orange | 12543 | G | 5052 | Maybrook | N |  | 5.2 | [13 empty] | NM | N | 1 Delta Electronics SOLIVIA 5.2 NA G4 TL (240V) | 2019-09-30 | 2019-10-04 | 4 | 2019-10-04 | [14 empty] | 2019-12-20 | 2019-12-20 |  | Y
Central Hudson |  | Autonomous Energies | CH-11886 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7062 | Milan | N | CH-11886 | 5 | [13 empty] | NM | N | 1 SMA America SB5.0-1SP-US-41 (240V) [SI1] | 2019-09-24 | 2019-09-24 | 0 | 2019-09-24 | [14 empty] | 2019-11-05 | 2019-11-05 |  | W
Central Hudson |  | Kasselman Solar | CH-11887 | Kingston | Saugerties | Ulster | 12477 | G | 3002 | Saugerties | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2019-09-24 | 2019-09-24 | 0 | 2019-09-24 | [14 empty] | 2019-09-24 | 2019-09-25 |  | Y
Central Hudson |  | PlugPV LLC | CH-11889 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8072 | Shenandoah | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2019-09-24 | 2019-09-25 | 1 | 2019-09-25 | [14 empty] | 2019-10-22 | 2019-10-24 |  | Y
Central Hudson |  | PlugPV LLC | CH-11888 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6042 | Spackenkill | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2019-09-24 | 2019-09-25 | 1 | 2019-09-25 | [14 empty] | 2019-12-04 | 2019-12-16 |  | Y
Central Hudson |  | Trinity Solar | CH-11892 | Newburgh | Newburgh | Orange | 12550 | G | 4012 | West Balmville | N | CH-08567 | 3.8 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3800H-US (240V) | 2019-09-25 | 2019-09-26 | 1 | 2019-09-26 | [14 empty] | 2020-03-06 | 2020-03-12 |  | Y
Central Hudson |  | New York State Solar Farm | CH-11890 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6096 | Manchester | N |  | 6.98 | [13 empty] | NM | N | 20 SunPower SPR-A400-G-AC (240V) | 2019-09-25 | 2019-09-26 | 1 | 2019-09-26 | [14 empty] | 2019-10-31 | 2019-11-01 |  | Y
Central Hudson |  | Solar Generation | CH-11891 | Kingston | Woodstock | Ulster | 12498 | G | 3012 | Woodstock | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000H-US (240V) | 2019-09-25 | 2019-09-26 | 1 | 2019-09-26 | [14 empty] | 2019-10-09 | 2019-10-10 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-11894 | Newburgh | Marlboro | Ulster | 12542 | G | 5003 | Marlboro | N | CH-01098 | 3 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3000 (240V) | 2019-09-25 | 2019-09-26 | 1 | 2019-09-26 | [14 empty] | 2019-10-03 | 2019-10-08 |  | Y
Central Hudson |  | EnterSolar | CH-11899 | Newburgh | Newburgh | Orange | 12550 | G | 4027 | Coldenham | N |  | 4200 | [13 empty] | CDG | Y | 70 Yaskawa Solectria Solar PVI 60TL-480 (480V) | 2019-09-27 | 2019-10-11 | 10 | 2019-10-11 | 2019-10-11 | 2019-10-31 | 14 | 2019-11-14 | 2019-12-06 | 2020-03-05 | 60 | 10666.29 | 387361.25 | 148144.71 | 2020-04-01 | 2020-09-23 | 2020-09-23 | 2021-09-22 | 2021-11-30 | 2021-11-30 | 2022-03-04 | Y | Y
Central Hudson |  | Sunrun Installation Service, Inc. | CH-11897 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6046 | Spackenkill | N |  | 6 | [13 empty] | NM | N | 1 Ningbo Ginlong Technologies Solis-1P6K-4G-US | 2019-09-30 | 2019-10-08 | 6 | 2019-10-08 | [14 empty] | 2019-10-30 | 2019-11-11 |  | Y
Central Hudson |  | Sunrun Installation Service, Inc. | CH-11898 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7053 | Rhinebeck | N |  | 13 | [13 empty] | NM | N | 1 Ningbo Ginlong Technologies Solis-1P10K-4G-US 1 Ningbo Ginlong Technologies Solis-1P3K-4G-US (240V) | 2019-10-07 | 2019-10-17 | 8 | 2019-10-17 | [8 empty] | 350 | 350 |  | 2019-10-22 | 2019-10-22 | 2019-12-04 | 2019-12-27 | 2020-01-02 |  | Y
Central Hudson |  | PlugPV LLC | CH-11895 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7053 | Rhinebeck | N |  | 22 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) 1 SolarEdge Technologies SE6000H-US (240V) 1 SolarEdge Technologies SE6000H-US (240V) | 2019-09-27 | 2019-09-27 | 0 | 2019-09-27 | [8 empty] | 350 | 350 |  | 2019-10-01 | 2019-10-01 | 2019-12-25 | 2019-12-10 | 2019-12-12 |  | Y
Central Hudson |  | Sunrun Installation Service, Inc. | CH-11896 | Kingston | Woodstock | Ulster | 12498 | G | 3014 | Woodstock | N |  | 7.6 | [13 empty] | NM | N | 1 Ningbo Ginlong Technologies Solis-1P7.6K-4G-US | 2019-09-27 | 2019-09-27 | 0 | 2019-09-27 | [14 empty] | 2020-01-08 | 2020-01-09 |  | Y
Central Hudson |  | New York State Solar Farm | CH-11900 | Kingston | Tillson | Ulster | 12486 | G | 3021 | High Falls | N |  | 9.135 | [13 empty] | NM | N | 29 SunPower SPR-E19-320-E-AC (240V) | 2019-09-30 | 2019-10-01 | 1 | 2019-10-01 | [14 empty] | 2019-11-15 | 2019-11-15 |  | Y
Central Hudson |  | Solar Generation | CH-11903 | Kingston | Cottekill | Ulster | 12419 | G | 3021 | High Falls | N |  | 1.44 | [13 empty] | NM | N | 6 Enphase Energy IQ7-60-x-US (240V) | 2019-09-30 | 2019-10-03 | 3 | 2019-10-03 | [14 empty] | 2019-10-31 | 2019-11-01 |  | Y
Central Hudson |  | Solar Generation | CH-11902 | Kingston | Cottekill | Ulster | 12419 | G | 3021 | High Falls | N |  | 3.6 | [13 empty] | NM | N | 15 Enphase Energy IQ7-60-x-US (240V) | 2019-09-30 | 2019-10-03 | 3 | 2019-10-03 | [14 empty] | 2019-11-04 | 2019-11-04 |  | Y
Central Hudson |  | Lighthouse Solar | CH-11901 | Kingston | Kerhonkson | Ulster | 12446 | G | 3082 | Kerhonkson | N |  | 4.93 | [13 empty] | NM | N | 17 Enphase Energy IQ7PLUS-72-x-US (240V) | 2019-09-30 | 2019-10-03 | 3 | 2019-10-03 | [14 empty] | 2019-11-01 | 2019-11-01 |  | Y
Central Hudson |  | Trinity Solar | CH-11904 | Newburgh | Gardiner | Ulster | 12525 | G | 5031 | Galeville | N | CH-08457 | 3 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3000H-US (240V) | 2019-10-11 | 2019-10-17 | 4 | 2019-10-17 | [14 empty] | 2019-11-15 | 2019-11-15 |  | Y
Central Hudson |  | Kasselman Solar | CH-11905 | Poughkeepsie | Lagrangevl | Dutchess | 12540 | G | 6057 | Todd Hill | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE11400H-US (240V) | 2019-09-30 | 2019-10-04 | 4 | 2019-10-04 | [14 empty] | 2019-11-12 | 2019-11-13 |  | Y
Central Hudson |  | Suncommon | CH-11907 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7061 | Milan | Y |  | 7.6 | 5 | [12 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) 1TeslaAC Powerwall 2.0 | 2019-10-14 | 2019-10-22 | 6 | 2019-10-22 | [14 empty] | 2019-11-19 | 2019-11-22 |  | Y
Central Hudson |  | New York State Solar Farm | CH-11909 | Newburgh | Highland | Ulster | 12528 | G | 5022 | Ohioville | N |  | 11.168 | [13 empty] | NM | N | 32 SunPower SPR-A400-G-AC (240V) | 2019-10-09 | 2019-10-14 | 3 | 2019-10-14 | [14 empty] | 2019-10-21 | 2019-10-23 |  | Y
Central Hudson |  | PlugPV LLC | CH-11908 | Newburgh | New Windsor | Orange | 12553 | G | 4095 | Bethlehem Rd | N |  | 13.8 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) 1 SolarEdge Technologies SE3800H-US (240V) | 2019-10-01 | 2019-10-09 | 6 | 2019-10-09 | [14 empty] | 2019-12-10 | 2019-12-10 |  | Y
Central Hudson |  | Lighthouse Solar | CH-11906 | Kingston | Rosendale | Ulster | 12472 | G | 3021 | High Falls | N | CH-11906 | 5.51 | [13 empty] | NM | N | 19 Enphase Energy IQ7PLUS-72-x-US (240V) | 2019-10-16 | 2019-10-25 | 7 | 2019-10-25 | [14 empty] | 2019-11-12 | 2019-11-14 |  | Y
Central Hudson |  | Lighthouse Solar | CH-11911 | Kingston | Rosendale | Ulster | 12472 | G | 3022 | High Falls | N |  | 6.09 | [13 empty] | NM | N | 21 Enphase Energy IQ7PLUS-72-x-US (240V) | 2019-10-01 | 2019-10-09 | 6 | 2019-10-09 | [14 empty] | 2019-11-21 | 2019-11-21 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-11910 | Poughkeepsie | Poughkeepsie |  | 12603 | G | 6043 | Spackenkill | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000 (240V) | 2019-10-01 | 2019-10-09 | 6 | 2019-10-09 | [14 empty] | 2019-10-17 | 2019-10-17 |  | W
Central Hudson |  | PlugPV LLC | CH-11913 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8043 | Myers Corners | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2019-10-02 | 2019-10-09 | 5 | 2019-10-09 | [14 empty] | 2019-11-08 | 2019-11-13 |  | Y
Central Hudson |  | New York State Solar Farm | CH-11912 | Kingston | Kingston | Ulster | 12401 | G | 111 | South Wall St | N |  | 5.04 | [13 empty] | NM | N | 16 SunPower SPR-E19-320-E-AC (240V) | 2019-10-02 | 2019-10-09 | 5 | 2019-10-09 | [14 empty] | 2019-11-15 | 2019-11-15 |  | Y
Central Hudson |  | PlugPV LLC | CH-11915 | Newburgh | Gardiner | Ulster | 12525 | G | 5031 | Galeville | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2019-10-02 | 2019-10-10 | 6 | 2019-10-10 | [14 empty] | 2019-11-22 | 2019-12-04 |  | Y
Central Hudson |  | Suncommon | CH-11918 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7041 | Staatsburg | N | CH-11918 | 20 | [13 empty] | NM | N | 2 SolarEdge Technologies SE10000H-US (240V) | 2019-10-02 | 2019-10-10 | 6 | 2019-10-10 | [14 empty] | 2020-02-26 | 2020-03-05 |  | Y
Central Hudson |  | Suncommon | CH-11917 | Poughkeepsie | Milerton | Dutchess | 12546 | G | 7092 | Pulvers Corners | N |  | 22.8 | [13 empty] | NM | N | 2 SolarEdge Technologies SE11400H-US (240V) | 2019-12-02 | 2019-12-02 | 0 | 2019-12-02 | [14 empty] | 2020-09-10 | 2020-09-10 |  | Y
Central Hudson |  | Suncommon | CH-11916 | Poughkeepsie | Staatsburg |  | 12580 | G | 7041 | Staatsburg | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2019-10-02 | 2019-10-16 | 10 | 2019-10-16 | [17 empty] | W
Central Hudson |  | Suncommon | CH-11919 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7053 | Rhinebeck | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2019-10-11 | 2019-10-17 | 4 | 2019-10-17 | [14 empty] | 2019-12-04 | 2019-12-06 |  | Y
Central Hudson |  | PlugPV LLC | CH-11914 | Newburgh | Wallkill | Ulster | 12589 | G | 4011 | West Balmville | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2019-10-02 | 2019-10-10 | 6 | 2019-10-10 | [14 empty] | 2019-11-22 | 2019-12-02 |  | Y
Central Hudson |  | Suncommon | CH-11924 | Catskill | W Coxsackie | Greene | 12192 | G | 1083 | New Baltimore | N | CH-11924 | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2019-10-03 | 2019-10-11 | 6 | 2019-10-11 | [14 empty] | 2020-02-18 | 2020-02-18 |  | Y
Central Hudson |  | Empire Solar solutions | CH-11925 | Poughkeepsie | Poughkeepsie |  | 12603 | G | 6096 | Manchester | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000 (240V) | 2019-10-11 | 2019-10-17 | 4 | 2019-10-17 | [14 empty] | 2019-10-31 | 2019-11-01 |  | W
Central Hudson |  | Empire Solar Solutions | CH-11923 | Newburgh | New Paltz |  | 12561 | G | 5031 | Galeville | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE 11400A-US (240V) | 2019-10-03 | 2019-10-11 | 6 | 2019-10-11 | [14 empty] | 2019-10-31 | 2019-11-01 |  | W
Central Hudson |  | Empire Solar Solutions | CH-11921 | Newburgh | Cornwall |  | 12518 | G | 4041 | Union Ave | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600A-US (240V) | 2019-10-03 | 2019-10-10 | 5 | 2019-10-10 | [14 empty] | 2019-10-16 | 2019-10-17 |  | W
Central Hudson |  | Empire Solar Solutions | CH-11922 | Kingston | Olive Brdg |  | 12461 | G | 3024 | High Falls | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000 (240V) | 2019-10-03 | 2019-10-11 | 6 | 2019-10-11 | [17 empty] | W
Central Hudson |  | Suncommon | CH-11920 | Poughkeepsie | Rhinebeck |  | 12572 | G | 7053 | Rhinebeck | N |  | 22.8 | [13 empty] | NM | N | 2 SolarEdge Technologies SE11400H-US (240V) | 2019-10-31 | 2019-11-12 | 8 | 2019-11-12 | [17 empty] | W
Central Hudson |  | Lighthouse Solar | CH-11928 | Newburgh | Gardiner | Ulster | 12525 | G | 5031 | Galeville | N | CH-03686 | 6.96 | [13 empty] | NM | N | 24 Enphase Energy IQ7PLUS-72-x-US (240V) | 2019-10-04 | 2019-10-14 | 6 | 2019-10-14 | [14 empty] | 2019-11-06 | 2019-11-07 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-11927 | Poughkeepsie | Poughkeepsie |  | 12601 | G | 6065 | Inwood Ave | N | CH-11927 | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000 (240V) | 2019-10-04 | 2019-10-11 | 5 | 2019-10-11 | [14 empty] | 2019-10-31 | 2019-11-01 |  | W
Central Hudson |  | Empire Solar Solutions LLC | CH-11926 | Kingston | Kerhonkson |  | 12446 | G | 3082 | Kerhonkson | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600A-US (240V) | 2019-10-04 | 2019-10-11 | 5 | 2019-10-11 | [14 empty] | 2019-10-31 | 2019-11-01 |  | W
Central Hudson |  | Solar Generation | CH-11929 | Kingston | Kingston |  | 12401 | G | 1024 | East Kingston | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2019-10-04 | 2019-10-14 | 6 | 2019-10-14 | [17 empty] | W
Central Hudson |  | Lumens Holdings 3 LLC | CH-11873 | Catskill | Cairo | Greene | 12413 | G | 2071 | Freehold | N |  | 2000 | [13 empty] | CDG | Y | 16 Chint Power Systems America CPS SCH125KTL-DO/US-600 (600V) | 2019-10-08 | 2019-10-21 | 9 | 2019-10-21 | 2019-10-21 | 2019-11-08 | 14 | [5 empty] | 292831 |  | 2020-05-26 | 2020-11-12 | 2020-11-12 | 2025-06-18 | 2025-11-07 | 2025-11-12 |  | Y | Y
Central Hudson |  | Infinity Solar Systems | CH-11930 | Fishkill | Stormvl | Dutchess | 12582 | G | 8071 | Shenandoah | N |  | 8.64 | [13 empty] | NM | N | 36 Enphase Energy IQ7-60-x-US (240V) | 2019-10-07 | 2019-10-14 | 5 | 2019-10-14 | [14 empty] | 2019-12-19 | 2019-12-19 |  | Y
Central Hudson |  | Lighthouse Solar | CH-11934 | Newburgh | New Paltz | Ulster | 12561 | G | 5031 | Galeville | N |  | 9.86 | [13 empty] | NM | N | 34 Enphase Energy IQ7PLUS-72-x-US (240V) | 2019-10-07 | 2019-10-14 | 5 | 2019-10-14 | [14 empty] | 2019-12-03 | 2019-12-03 |  | Y
Central Hudson |  | PlugPV LLC | CH-11933 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8043 | Myers Corners | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000H-US (240V) | 2019-10-07 | 2019-10-14 | 5 | 2019-10-14 | [14 empty] | 2019-12-23 | 2019-12-23 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-11931 | Kingston | High Fls |  | 12440 | G | 3022 | High Falls | N |  | 3 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3000 (240V) | 2019-10-07 | 2019-10-14 | 5 | 2019-10-14 | [14 empty] | 2019-10-31 | 2019-11-01 |  | W
Central Hudson |  | Solar Generation | CH-11932 | Kingston | W Hurley | Ulster | 12491 | G | 2094 | Hurley Ave | N | CH-08149 | 1.44 | [13 empty] | NM | N | 6 Enphase Energy IQ7-60-x-US (240V) | 2019-10-31 | 2019-11-05 | 3 | 2019-11-05 | [14 empty] | 2019-11-11 | 2019-11-13 |  | Y
Central Hudson |  | Sunrun Installation Service, Inc. | CH-11936 | Newburgh | Newburgh | Orange | 12550 | G | 4015 | West Balmville | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2019-10-08 | 2019-10-14 | 4 | 2019-10-14 | [14 empty] | 2019-12-26 | 2019-12-26 |  | Y
Central Hudson |  | Suncommon | CH-11935 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7051 | Rhinebeck | N |  | 13.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) 1 SolarEdge Technologies SE6000H-US (240V) | 2019-10-14 | 2019-10-23 | 7 | 2019-10-23 | [14 empty] | 2020-02-06 | 2020-02-10 |  | Y
Central Hudson |  | Bright Planet Solar | CH-11941 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8054 | North Chelsea | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) [SI1] | 2019-10-09 | 2019-10-15 | 4 | 2019-10-15 | [14 empty] | 2020-06-19 | 2020-06-19 |  | Y
Central Hudson |  | Bright Planet Solar | CH-11940 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6008 | Reynolds Hill | N |  | 3.8 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3800 (240V) | 2019-11-25 | 2019-11-25 | 0 | 2019-11-25 | [14 empty] | 2019-11-27 | 2019-12-06 |  | Y
Central Hudson |  | New York State Solar Farm | CH-11937 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8043 | Myers Corners | N |  | 13.2 | [13 empty] | NM | N | 42 SunPower SPR-X22-360-E-AC (240V) | 2019-10-09 | 2019-10-22 | 9 | 2019-10-22 | [14 empty] | 2020-09-21 | 2020-09-21 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-11939 | Kingston | Grahamsvl |  | 12740 | G | 391 | Neversink | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE 10000A-US (240V) | 2019-10-09 | 2019-10-14 | 3 | 2019-10-14 | [14 empty] | 2019-10-15 | 2019-10-17 |  | W
Central Hudson |  | US Energy Concierge, Inc. | CH-11943 | Fishkill | Garrison | Putnam | 10524 | G | 8066 | Merritt Park | N |  | 21.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE 10000A-US (240V) 1 SolarEdge Technologies SE 11400A-US (240V) | 2019-10-25 | 2019-11-04 | 6 | 2019-11-04 | [14 empty] | 2019-12-23 | 2019-12-26 |  | Y
Central Hudson |  | Solar Generation | CH-11942 | Kingston | Woodstock | Ulster | 12498 | G | 3012 | Woodstock | N |  | 3.84 | [13 empty] | NM | N | 16 Enphase Energy IQ7-60-x-US (240V) | 2019-10-09 | 2019-10-15 | 4 | 2019-10-15 | [14 empty] | 2020-03-13 | 2020-03-18 |  | Y
Central Hudson |  | Solar Generation | CH-11938 | Kingston | Kingston | Ulster | 12401 | G | 3021 | High Falls | N |  | 9.67 | [13 empty] | NM | N | 1 Pika Energy X7602 (240V) 7 Enphase Energy IQ7PLUS-72-x-US (240V) [SI1] | 2019-10-16 | 2019-10-25 | 7 | 2019-10-25 | [14 empty] | 2019-11-26 | 2019-11-26 |  | Y
Central Hudson |  | Sunrun Inc | CH-11947 | Fishkill | Wappingrs Fls |  | 12590 | G | 8094 | Fishkill Plains | N |  | 16.6 | [13 empty] | NM | N | 1 Ningbo Ginlong Technologies Solis-1P9K-4G-US 1 Ningbo Ginlong Technologies Solis-1P7.6K-4G-US | 2019-10-10 | 2019-10-18 | 6 | 2019-10-18 | [8 empty] | 350 | [8 empty] | W
Central Hudson |  | PlugPV LLC | CH-11945 | Newburgh | Newburgh | Orange | 12550 | G | 4013 | West Balmville | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000H-US (240V) | 2019-10-10 | 2019-10-17 | 5 | 2019-10-17 | [14 empty] | 2020-02-12 | 2020-02-14 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-11948 | Kingston | Kerhonkson | Ulster | 12446 | G | 3082 | Kerhonkson | N |  | 3.8 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3800 (240V) | 2019-10-17 | 2019-10-17 | 0 | 2019-10-17 | [14 empty] | 2019-11-19 | 2019-11-19 |  | Y
Central Hudson |  | Suncommon | CH-11950 | Kingston | Kingston | Ulster | 12401 | G | 1013 | Boulevard | Y |  | 20 | 15 | [12 empty] | NM | N | 2 SolarEdge Technologies SE10000H-US (240V) 3TeslaAC Powerwall 2.0 | 2020-02-10 | 2020-02-25 | 10 | 2020-02-25 | [14 empty] | 2021-05-26 | 2021-05-26 |  | Y
Central Hudson |  | New York State Solar Farm | CH-11949 | Kingston | Saugerties | Ulster | 12477 | G | 3004 | Saugerties | N |  | 5.6 | [13 empty] | NM | N | 16 SunPower SPR-A400-G-AC (240V) | 2019-10-11 | 2019-10-17 | 4 | 2019-10-17 | [14 empty] | 2019-11-27 | 2019-11-27 |  | Y
Central Hudson |  | Suncommon | CH-11951 | Catskill | Prattsville | Greene | 12468 | E | 2389 | Vinegar Hill | Y |  | 3.8 | 5 | [12 empty] | NM | N | 1 SolarEdge Technologies SE3800H-US (240V) 1TeslaAC Powerwall 2.0 | 2019-10-30 | 2019-11-05 | 4 | 2019-11-05 | [14 empty] | 2019-12-16 | 2019-12-18 |  | Y
Central Hudson |  | PlugPV LLC | CH-11953 | Newburgh | Wallkill | Ulster | 12589 | G | 5043 | East Walden | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2019-10-17 | 2019-10-28 | 7 | 2019-10-28 | [14 empty] | 2019-11-19 | 2019-11-22 |  | Y
Central Hudson |  | Apex Solar Power | CH-11952 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8072 | Shenandoah | N |  | 13.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) 1 SolarEdge Technologies SE6000H-US (240V) | 2019-10-17 | 2019-10-28 | 7 | 2019-10-28 | [14 empty] | 2019-11-20 | 2019-11-25 |  | Y
Central Hudson |  | New York State Solar Farm | CH-11955 | Poughkeepsie | Millbrook | Dutchess | 12545 | G | 7025 | Tinkertown | N |  | 6.3 | [13 empty] | NM | N | 18 SunPower SPR-A400-G-AC (240V) | 2019-10-14 | 2019-10-22 | 6 | 2019-10-22 | [14 empty] | 2019-11-27 | 2019-12-02 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-11957 | Newburgh | Newburgh | Orange | 12550 | G | 4015 | West Balmville | N |  | 5.28 | [13 empty] | NM | N | 22 Enphase Energy IQ7-60-x-US (240V) | 2019-10-14 | 2019-10-24 | 8 | 2019-10-24 | [14 empty] | 2020-01-20 | 2020-01-21 |  | Y
Central Hudson |  | Suncommon | CH-11958 | Kingston | Kingston | Ulster | 12401 | G | 2091 | Hurley Ave | N |  | 86.4 | [13 empty] | NM | N | 2 SolarEdge Technologies SE43.2KUS (208V) | 2019-10-30 | 2019-11-04 | 3 | 2019-11-04 | 2019-11-04 | 2019-11-25 | 15 | [11 empty] | 2021-01-05 | 2021-01-05 |  | Y
Central Hudson |  | Solar Generation | CH-11960 | Kingston | Boicevl | Ulster | 12412 | G | 3011 | Woodstock | N |  | 12 | [13 empty] | NM | N | 2 SMA America SB6000US (240V) | 2019-10-22 | 2019-10-30 | 6 | 2019-10-30 | [14 empty] | 2019-12-16 | 2019-12-16 |  | Y
Central Hudson |  | Suncommon | CH-11956 | Newburgh | Highland | Ulster | 12528 | G | 5081 | Highland | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2019-10-18 | 2019-10-29 | 7 | 2019-10-29 | [14 empty] | 2020-01-17 | 2020-01-17 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-11965 | Newburgh | Plattekill |  | 12568 | G | 5041 | East Walden | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE 10000A-US (240V) | 2019-10-15 | 2019-10-24 | 7 | 2019-10-24 | [14 empty] | 2019-10-29 | 2019-10-30 |  | W
Central Hudson |  | PlugPV LLC | CH-11963 | Newburgh | Wallkill | Ulster | 12589 | G | 5043 | East Walden | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2019-10-15 | 2019-10-24 | 7 | 2019-10-24 | [14 empty] | 2019-11-22 | 2019-11-25 |  | Y
Central Hudson |  | AEC Solar Energy Corp. | CH-11964 | Catskill | Earlton | Greene | 12058 | G | 1071 | Coxsackie | N |  | 15.8 | [13 empty] | NM | N | 50 SunPower SPR-E20-327-E-AC (240V) | 2019-10-24 | 2019-10-31 | 5 | 2019-10-31 | [8 empty] | 350 | 350 |  | 2020-06-11 | 2020-06-11 | 2020-06-25 | 2020-06-30 | 2020-06-30 |  | Y
Central Hudson |  | Self | CH-11962 | Fishkill | Wappingers Falls | Dutchess | 12590 | G | 8052 | North Chelsea | N |  | 3.8 | [13 empty] | NM | N | 1 SMA America SB3.8-1SP-US-40 (240V) [SI1] | 2019-10-24 | 2019-11-01 | 6 | 2019-11-01 | [14 empty] | 2020-01-07 | 2020-01-07 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-11961 | Catskill | W Coxsackie | Greene | 12192 | G | 1083 | New Baltimore | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE 10000A-US (240V) | 2019-10-15 | 2019-10-23 | 6 | 2019-10-23 | [14 empty] | 2019-11-04 | 2019-11-08 |  | Y
Central Hudson |  | Autonomous Energies | CH-11966 | Catskill | W Kill | Greene | 12492 | E | 2389 | Vinegar Hill | N |  | 12 | [13 empty] | NM | N | 2 SMA America SB6.0-1SP-US-41 (240V) [SI1] | 2019-10-15 | 2019-10-24 | 7 | 2019-10-24 | [14 empty] | 2019-11-21 | 2019-11-21 |  | Y
Central Hudson |  | Sunrun Installation Service, Inc. | CH-11971 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6011 | Sand Dock | N |  | 9 | [13 empty] | NM | N | 1 Ningbo Ginlong Technologies Solis-1P9K-4G-US | 2019-10-16 | 2019-10-28 | 8 | 2019-10-28 | [14 empty] | 2019-11-14 | 2019-11-19 |  | Y
Central Hudson |  | Sunrun Installation Service, Inc. | CH-11969 | Newburgh | Newburgh |  | 12550 | G | 410 | Montgomery St | N |  | 3 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3000H-US (240V) | 2019-10-16 | 2019-10-28 | 8 | 2019-10-28 | [17 empty] | W
Central Hudson |  | Solar Generation | CH-11967 | Kingston | Olivebridge | Ulster | 12461 | G | 3024 | High Falls | N |  | 8.8 | [13 empty] | NM | N | 1 Pika Energy X7602 (240V) 5 Enphase Energy IQ7-60-x-US (240V) [SI1] | 2019-10-28 | 2019-11-04 | 5 | 2019-11-04 | [14 empty] | 2020-07-30 | 2020-07-30 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-11968 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6043 | Spackenkill | N |  | 17.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600A-US (240V) 1 SolarEdge Technologies SE10000H-US (240V) | 2019-10-16 | 2019-10-25 | 7 | 2019-10-25 | [14 empty] | 2019-12-18 | 2019-12-18 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-11972 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6046 | Spackenkill | N |  | 22.8 | [13 empty] | NM | N | 2 SolarEdge Technologies SE 11400A-US (240V) | 2019-10-17 | 2019-10-28 | 7 | 2019-10-28 | [8 empty] | 350 | 350 |  | 2019-10-30 | 2019-10-30 | 2019-12-13 | 2019-12-31 | 2019-12-31 |  | Y
Central Hudson |  | New York State Solar Farm | CH-11973 | Fishkill | Beacon | Dutchess | 12508 | G | 8015 | Forgebrook | N |  | 9.1 | [13 empty] | NM | N | 26 SunPower SPR-A400-G-AC (240V) | 2019-10-17 | 2019-10-28 | 7 | 2019-10-28 | [14 empty] | 2019-10-29 | 2019-11-05 |  | Y
Central Hudson |  | Self | CH-11979 | Kingston | St Remy | Ulster | 12401 | G | 3041 | Sturgeon Pool | N |  | 10 | [13 empty] | NM | N | 1 Ningbo Ginlong Technologies Solis-1P10K-4G-US | 2019-10-18 | 2019-10-28 | 6 | 2019-10-28 | [14 empty] | 2020-05-15 | 2020-05-15 |  | Y
Central Hudson |  | Suncommon | CH-11977 | Poughkeepsie | Lagrangevl |  | 12540 | G | 6053 | Todd Hill | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE11400H-US (240V) | 2019-10-18 | 2019-10-29 | 7 | 2019-10-29 | [17 empty] | W
Central Hudson |  | Infinity Solar Systems | CH-11976 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8092 | Fishkill Plains | N |  | 6.72 | [13 empty] | NM | N | 28 Enphase Energy IQ7-60-x-US (240V) | 2019-10-29 | 2019-10-29 | 0 | 2019-10-29 | [14 empty] | 2019-11-21 | 2019-11-25 |  | Y
Central Hudson |  | Hudson Valley Wind & Solar, LLC | CH-11980 | Kingston | Stone Ridge | Ulster | 12484 | G | 3023 | High Falls | N |  | 10.56 | [13 empty] | NM | N | 44 Enphase Energy IQ7-60-x-US (240V) | 2019-11-22 | 2019-11-25 | 1 | 2019-11-25 | [14 empty] | 2020-03-17 | 2020-03-20 |  | Y
Central Hudson |  | Suncommon | CH-11978 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7053 | Rhinebeck | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE11400H-US (240V) | 2019-10-18 | 2019-10-29 | 7 | 2019-10-29 | [14 empty] | 2020-01-31 | 2020-02-03 |  | Y
Central Hudson |  | Vivint Solar Developer, LLC | CH-11984 | Catskill | W Coxsackie |  | 12192 | G | 1076 | Coxsackie | N | CH-08736 | 5.98 | [13 empty] | NM | N | 26 Enphase Energy IQ6-60-X-US (240V) | 2020-01-14 | 2020-01-14 | 0 | 2020-01-14 | [8 empty] | 350 | [8 empty] | W
Central Hudson |  | Empire Solar Solutions | CH-11983 | Newburgh | New Windsor |  | 12553 | G | 4045 | Union Ave | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600A-US (240V) | 2019-10-21 | 2019-10-30 | 7 | 2019-10-30 | [14 empty] | 2019-10-31 | 2019-11-01 |  | W
Central Hudson |  | Solar Liberty Energy Systems, Inc. | CH-11982 | Kingston | Kingston | Ulster | 12401 | G | 3021 | High Falls | N |  | 15.2 | [13 empty] | NM | N | 2 SolarEdge Technologies SE7600H-US (240V) | 2019-10-30 | 2019-11-05 | 4 | 2019-11-05 | [8 empty] | 350 | 350 |  | 2019-11-07 | 2019-11-07 | 2020-01-24 | 2020-02-10 | 2020-02-12 |  | Y
Central Hudson |  | Solar Liberty Energy Systems, Inc. | CH-11981 | Kingston | Kingston | Ulster | 12401 | G | 3021 | High Falls | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2019-11-05 | 2019-11-05 | 0 | 2019-11-05 | [14 empty] | 2020-02-10 | 2020-02-12 |  | Y
Central Hudson |  | MOMENTUM SOLAR | CH-11987 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8051 | North Chelsea | N |  | 2.88 | [13 empty] | NM | N | 12 Enphase Energy IQ7-60-x-US (240V) | 2019-10-30 | 2019-10-30 | 0 | 2019-10-30 | [14 empty] | 2020-01-23 | 2020-01-27 |  | Y
Central Hudson |  | New York State Solar Farm | CH-11985 | Kingston | High Fls | Ulster | 12440 | G | 3022 | High Falls | N |  | 7.678 | [13 empty] | NM | N | 22 SunPower SPR-A400-G-AC (240V) | 2019-10-31 | 2019-11-04 | 2 | 2019-11-04 | [14 empty] | 2019-11-06 | 2019-11-07 |  | Y
Central Hudson |  | Trinity Solar | CH-11988 | Newburgh | Campbell Hall | Orange | 10916 | G | 5051 | Maybrook | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2019-10-22 | 2019-10-30 | 6 | 2019-10-30 | [14 empty] | 2020-04-20 | 2020-04-21 |  | Y
Central Hudson |  | New York State Solar Farm | CH-11989 | Newburgh | Gardiner | Ulster | 12525 | G | 5031 | Galeville | N |  | 7.678 | [13 empty] | NM | N | 22 SunPower SPR-A400-G-AC (240V) | 2019-10-22 | 2019-10-30 | 6 | 2019-10-30 | [14 empty] | 2019-11-27 | 2019-12-10 |  | Y |  | 11/22/19 - CH Rep unable to install net meter; appointment required. Scheduled appt & installed meter on 12/9/19.
Central Hudson |  | Empire Solar Solutions | CH-11993 | Kingston | Grahamsvl | Sullivan | 12740 | G | 3091 | Neversink | N |  | 3 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3000 (240V) | 2019-10-23 | 2019-10-31 | 6 | 2019-10-31 | [14 empty] | 2019-11-04 | 2019-11-08 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-11992 | Poughkeepsie | Poughkeepsie |  | 12603 | G | 6003 | Reynolds Hill | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE 10000A-US (240V) | 2019-10-23 | 2019-10-31 | 6 | 2019-10-31 | [14 empty] | 2019-10-31 | 2019-11-01 |  | W
Central Hudson |  | Sunrun Installation Service, Inc. | CH-11994 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8072 | Shenandoah | Y |  | 15.2 | 15.2 | [12 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) 1 SolarEdge Technologies SE7600A-US (208V) [SI1] 1SolarEdge TechnologiesSE7600A-US | 2019-11-14 | 2019-11-21 | 5 | 2019-11-21 | [14 empty] | 2020-01-30 | 2020-01-31 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-11991 | Catskill | Greenvl | Greene | 12083 | G | 1092 | Westerlo | N |  | 3.8 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3800 (240V) | 2019-10-23 | 2019-10-30 | 5 | 2019-10-30 | [14 empty] | 2019-12-04 | 2019-12-04 |  | Y
Central Hudson |  | hudson Valley Wind & Solar LLC | CH-11990 | Poughkeepsie | Millerton | Dutchess | 12546 | G | 7095 | Smithfield | N |  | 6 | [13 empty] | NM | N | 1 SMA America SB6000TL-US (240V) | 2019-11-21 | 2019-11-22 | 1 | 2019-11-22 | [14 empty] | 2020-01-24 | 2020-01-27 |  | W
Central Hudson |  | Kasselman Solar | CH-11995 | Newburgh | Newburgh | Orange | 12550 | G | 4013 | West Balmville | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2019-10-31 | 2019-10-31 | 0 | 2019-10-31 | [14 empty] | 2019-12-23 | 2020-01-02 |  | Y
Central Hudson |  | Hudson Valley Wind & Solar, LLC | CH-11997 | Poughkeepsie | Millbrook | Dutchess | 12545 | G | 7012 | Hibernia | N |  | 6 | [13 empty] | NM | N | 1 SMA America SB6.0-1SP-US-40 (240V) [SI1] | 2019-11-14 | 2019-11-21 | 5 | 2019-11-21 | [14 empty] | 2020-06-22 | 2020-06-22 |  | Y
Central Hudson |  | Hudson River Renewables | CH-11998 | Poughkeepsie | Wassaic | Dutchess | 12592 | G | 7012 | Hibernia | N | CH-11998 | 12 | [13 empty] | NM | N | 2 SMA America SB6.0-1SP-US-40 (240V) | 2019-11-18 | 2019-11-21 | 3 | 2019-11-21 | [14 empty] | 2020-01-22 | 2020-01-27 |  | Y
Central Hudson |  | Sunrun Installation Service, Inc. | CH-12006 | Kingston | Kingston | Ulster | 12401 | G | 1022 | East Kingston | N |  | 3.6 | [13 empty] | NM | N | 1 Ningbo Ginlong Technologies Solis-1P3.6K-4G-US (240V) | 2019-10-25 | 2019-11-04 | 6 | 2019-11-04 | [14 empty] | 2020-01-02 | 2020-01-03 |  | Y
Central Hudson |  | Sunrun Installation Service, Inc. | CH-12005 | Fishkill | Hopewell Jct |  | 12533 | G | 8095 | Fishkill Plains | N |  | 4 | [13 empty] | NM | N | 1 Ningbo Ginlong Technologies Solis-1P4K-4G-US (240V) | 2019-11-04 | 2019-11-11 | 5 | 2019-11-11 | [17 empty] | W
Central Hudson |  | Solar Generation | CH-12000 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7051 | Rhinebeck | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2019-11-08 | 2019-11-14 | 4 | 2019-11-14 | [14 empty] | 2020-01-10 | 2020-01-10 |  | Y
Central Hudson |  | Sunrun Installation Service, Inc. | CH-12003 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6094 | Manchester | N |  | 3.8 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3800H-US (240V) | 2019-11-04 | 2019-11-11 | 5 | 2019-11-11 | [14 empty] | 2019-12-03 | 2019-12-10 |  | Y
Central Hudson |  | self | CH-12002 | Poughkeepsie | Poughquag | Dutchess | 12570 | G | 6055 | Todd Hill | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) [SI1] | 2019-11-04 | 2019-11-11 | 5 | 2019-11-11 | [14 empty] | 2020-01-06 | 2020-01-07 |  | Y
Central Hudson |  | Solar Generation | CH-11999 | Kingston | New Paltz | Ulster | 12561 | G | 3041 | Sturgeon Pool | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2019-10-25 | 2019-11-07 | 9 | 2019-11-07 | [14 empty] | 2020-01-08 | 2020-01-08 |  | Y
Central Hudson |  | Sunrun Inc | CH-12004 | Fishkill | Wappingers Fall | Dutchess | 12590 | G | 8092 | Fishkill Plains | N |  | 4.8 | [13 empty] | NM | N | 1 Delta Electronics M5-TL-US (240V) [SI1] | 2019-11-04 | 2019-11-11 | 5 | 2019-11-11 | [14 empty] | 2019-11-27 | 2019-12-02 |  | Y
Central Hudson |  | Suncommon | CH-12001 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 6074 | East Park | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2019-10-25 | 2019-11-08 | 10 | 2019-11-08 | [14 empty] | 2020-02-03 | 2020-02-05 |  | Y
Central Hudson |  | Solar Generation | CH-12007 | Newburgh | Pine Bush | Orange | 12566 | G | NYSEG9 | NYSEG | N |  | 21.5 | [13 empty] | NM | N | 74 Enphase Energy IQ7PLUS-72-x-US (240V) | 2019-10-28 | 2019-11-04 | 5 | 2019-11-04 | [14 empty] | 2020-06-29 | 2020-06-29 |  | Y
Central Hudson |  | Kasselman Solar | CH-12010 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8043 | Myers Corners | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2019-10-29 | 2019-11-04 | 4 | 2019-11-04 | [14 empty] | 2019-11-05 | 2019-11-05 |  | Y
Central Hudson |  | Trinity Solar | CH-12011 | Newburgh | Newburgh | Orange | 12550 | G | 4053 | Union Ave | N |  | 3.8 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3800H-US (240V) | 2019-11-05 | 2019-11-05 | 0 | 2019-11-05 | [14 empty] | 2019-12-19 | 2019-12-30 |  | Y
Central Hudson |  | PlugPV LLC | CH-12009 | Newburgh | New Paltz | Ulster | 12561 | G | 5021 | Ohioville | N | CH-00958 | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2019-11-12 | 2019-11-15 | 3 | 2019-11-15 | [14 empty] | 2019-12-23 | 2019-12-23 |  | Y
Central Hudson |  | Sunrun Inc | CH-12012 | Catskill | Palenvl | Greene | 12463 | G | 2001 | North Catskill | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE11400H-US (240V) | 2019-11-05 | 2019-11-05 | 0 | 2019-11-05 | [14 empty] | 2020-01-21 | 2020-01-28 |  | Y
Central Hudson |  | Kasselman Solar | CH-12008 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8043 | Myers Corners | N |  | 8.99 | [13 empty] | NM | N | 31 Enphase Energy IQ7PLUS-72-x-US (240V) | 2019-11-18 | 2019-11-21 | 3 | 2019-11-21 | [14 empty] | 2019-12-04 | 2019-12-04 |  | Y
Central Hudson |  | Kasselman Solar | CH-12018 | Kingston | Saugerties | Ulster | 12477 | G | 3002 | Saugerties | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3800H-US (240V) 1 SolarEdge Technologies SE3800 (240V) | 2019-10-30 | 2019-11-05 | 4 | 2019-11-05 | [14 empty] | 2019-12-05 | 2019-12-10 |  | Y
Central Hudson |  | AEC Solar Energy Corp. | CH-12015 | Newburgh | New Paltz | Ulster | 12561 | G | 5021 | Ohioville | N |  | 13.96 | [13 empty] | NM | N | 40 SunPower SPR-A400-G-AC (240V) [SI1] | 2019-10-30 | 2019-11-05 | 4 | 2019-11-05 | [14 empty] | 2020-02-07 | 2020-02-10 |  | Y
Central Hudson |  | Kasselman Solar | CH-12017 | Catskill | Durham | Greene | 12422 | G | 1092 | Westerlo | N |  | 3.8 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3800H-US (240V) | 2019-10-31 | 2019-10-31 | 0 | 2019-10-31 | [14 empty] | 2019-11-20 | 2019-11-25 |  | Y
Central Hudson |  | Kasselman Solar | CH-12016 | Poughkeepsie | Clinton Cors | Dutchess | 12514 | G | 7071 | Stanfordville | N | CH-12016 | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2019-10-30 | 2019-11-05 | 4 | 2019-11-05 | [14 empty] | 2019-11-12 | 2019-11-13 |  | Y
Central Hudson |  | ETM Solar Works | CH-12021 | Catskill | Coxsackie | Greene | 12051 | G | 1074 | Coxsackie | N | CH-02660 | 5 | [13 empty] | NM | N | 1 SMA America SB5.0-1TP-US-40 (240V) [SI1] | 2019-11-21 | 2019-11-22 | 1 | 2019-11-22 | [14 empty] | 2020-12-11 | 2020-12-11 |  | Y
Central Hudson |  | PlugPV LLC | CH-12019 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 7041 | Staatsburg | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2019-10-31 | 2019-11-11 | 7 | 2019-11-11 | [14 empty] | 2019-12-23 | 2019-12-23 |  | Y
Central Hudson |  | PlugPV LLC | CH-12020 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8071 | Shenandoah | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2019-11-05 | 2019-11-05 | 0 | 2019-11-05 | [14 empty] | 2020-01-02 | 2020-01-02 |  | Y
Central Hudson |  | Kasselman Solar | CH-12023 | Kingston | Saugerties | Ulster | 12477 | G | 3002 | Saugerties | N |  | 17.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600A-US (240V) 1 SolarEdge Technologies SE10000H-US (240V) | 2019-11-11 | 2019-11-15 | 4 | 2019-11-15 | [8 empty] | 350 | 350 |  | 2019-11-22 | 2019-11-22 | 2020-03-02 | 2020-03-25 | 2020-03-25 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-12022 | Fishkill | Fishkill | Dutchess | 12524 | G | 8065 | Merritt Park | N |  | 8.64 | [13 empty] | NM | N | 36 Enphase Energy IQ7-60-x-US (240V) | 2019-11-01 | 2019-11-11 | 6 | 2019-11-11 | [14 empty] | 2020-01-20 | 2020-01-20 |  | Y
Central Hudson |  | Suncommon | CH-12031 | Fishkill | Beacon | Dutchess | 12508 | G | 8087 | Tioronda | N |  | 3.8 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3800H-US (240V) | 2019-11-04 | 2019-11-11 | 5 | 2019-11-11 | [14 empty] | 2020-01-17 | 2020-01-21 |  | Y
Central Hudson |  | Suncommon | CH-12028 | Kingston | Saugerties | Ulster | 12477 | G | 3002 | Saugerties | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2019-11-04 | 2019-11-11 | 5 | 2019-11-11 | [14 empty] | 2020-02-03 | 2020-02-04 |  | Y
Central Hudson |  | Kasselman Solar | CH-12025 | Catskill | Catskill | Greene | 12414 | G | 2006 | North Catskill | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2019-11-20 | 2019-11-22 | 2 | 2019-11-22 | [14 empty] | 2019-12-12 | 2019-12-12 |  | Y
Central Hudson |  | Sunrun Inc | CH-12030 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8043 | Myers Corners | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000H-US (240V) | 2019-11-14 | 2019-11-21 | 5 | 2019-11-21 | [14 empty] | 2020-03-03 | 2020-03-10 |  | Y
Central Hudson |  | New York State Solar Farm | CH-12027 | Kingston | Saugerties |  | 12477 | G | 3003 | Saugerties | N |  | 10.71 | [13 empty] | NM | N | 34 SunPower SPR-E19-320-E-AC (240V) | 2019-11-04 | 2019-11-11 | 5 | 2019-11-11 | [8 empty] | 350 | [8 empty] | W
Central Hudson |  | New York State Solar Farm | CH-12026 | Kingston | Tillson | Ulster | 12486 | G | 3021 | High Falls | N |  | 4.886 | [13 empty] | NM | N | 14 SunPower SPR-A400-G-AC (240V) | 2019-11-04 | 2019-11-11 | 5 | 2019-11-11 | [14 empty] | 2019-12-12 | 2019-12-12 |  | Y
Central Hudson |  | Sunrun Inc | CH-12029 | Newburgh | Wallkill | Ulster | 12589 | G | 5043 | East Walden | N |  | 7.68 | [13 empty] | NM | N | 1 Delta Electronics M8-TL-US (240V) [SI1] | 2019-11-04 | 2019-11-11 | 5 | 2019-11-11 | [8 empty] | 350 | 350 |  | 2019-12-03 | 2019-12-03 | 2019-12-23 | 2019-12-30 | 2019-12-31 |  | Y
Central Hudson |  | Solar Image | CH-12033 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 6068 | Inwood Ave | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2019-11-21 | 2019-12-09 | 10 | 2019-12-09 | [14 empty] | 2019-12-10 | 2019-12-11 |  | Y
Central Hudson |  | US Energy Concierge, Inc | CH-12034 | Fishkill | Stormvl | Dutchess | 12582 | G | 8071 | Shenandoah | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2019-11-04 | 2019-11-13 | 7 | 2019-11-13 | [14 empty] | 2019-12-24 | 2019-12-26 |  | Y
Central Hudson |  | Vivint Solar Developer, LLC | CH-12039 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8072 | Shenandoah | N |  | 12.72 | [13 empty] | NM | N | 53 Enphase Energy IQ7-60-x-US (240V) | 2019-11-05 | 2019-11-13 | 6 | 2019-11-13 | [14 empty] | 2020-03-25 | 2020-03-30 |  | Y
Central Hudson |  | Solar Generation | CH-12042 | Kingston | Woodstock | Ulster | 12498 | G | 3012 | Woodstock | N |  | 12.18 | [13 empty] | NM | N | 42 Enphase Energy IQ7PLUS-72-x-US (240V) | 2019-11-13 | 2019-11-19 | 4 | 2019-11-19 | [14 empty] | 2019-11-27 | 2019-11-27 |  | Y
Central Hudson |  | PlugPV LLC | CH-12038 | Newburgh | Wallkill | Ulster | 12589 | G | 5043 | East Walden | N | CH-09881 | 3.8 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3800H-US (240V) | 2019-12-19 | 2019-12-20 | 1 | 2019-12-20 | [14 empty] | 2019-12-31 | 2019-12-31 |  | Y
Central Hudson |  | New York State Solar Farm | CH-12040 | Kingston | Kingston | Ulster | 12401 | G | 1022 | East Kingston | N |  | 10.08 | [13 empty] | NM | N | 32 SunPower SPR-E19-320-E-AC (240V) | 2019-11-05 | 2019-11-13 | 6 | 2019-11-13 | [14 empty] | 2020-01-09 | 2020-01-13 |  | Y
Central Hudson |  | New York State Solar Farm | CH-12041 | Newburgh | Wallkill | Ulster | 12589 | G | 5033 | Galeville | N |  | 5.235 | [13 empty] | NM | N | 15 SunPower SPR-A400-G-AC (240V) | 2019-11-05 | 2019-11-13 | 6 | 2019-11-13 | [14 empty] | 2019-11-27 | 2019-12-02 |  | Y
Central Hudson |  | Sunrun Inc | CH-12044 | Fishkill | Fishkill | Dutchess | 12524 | G | 8014 | Forgebrook | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2019-11-05 | 2019-11-13 | 6 | 2019-11-13 | [14 empty] | 2019-11-25 | 2019-12-04 |  | Y
Central Hudson |  | Kasselman Solar | CH-12035 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6046 | Spackenkill | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2019-11-05 | 2019-11-13 | 6 | 2019-11-13 | [14 empty] | 2019-12-31 | 2019-12-31 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12037 | Poughkeepsie | Millerton | Dutchess | 12546 | G | 7095 | Smithfield | N |  | 15.2 | [13 empty] | NM | N | 2 SolarEdge Technologies SE7600A-US (240V) | 2019-11-13 | 2019-11-15 | 2 | 2019-11-15 | [14 empty] | 2020-02-20 | 2020-02-26 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12036 | Poughkeepsie | Millerton | Dutchess | 12546 | G | 7095 | Smithfield | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000 (240V) | 2019-11-05 | 2019-11-13 | 6 | 2019-11-13 | [14 empty] | 2020-02-20 | 2020-02-26 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-12043 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8095 | Fishkill Plains | N |  | 7.245 | [13 empty] | NM | N | 23 Enphase Energy IQ7X-96-x-US (240V) | 2019-12-02 | 2019-12-02 | 0 | 2019-12-02 | [14 empty] | 2019-12-19 | 2019-12-23 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12048 | Poughkeepsie | Lagrangevl | Dutchess | 12540 | G | 6055 | Todd Hill | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE 11400A-US (240V) | 2019-11-07 | 2019-11-19 | 8 | 2019-11-19 | [14 empty] | 2019-12-16 | 2019-12-16 |  | Y
Central Hudson |  | Kasselman Solar | CH-12047 | Kingston | W Shokan | Ulster | 12494 | G | 3011 | Woodstock | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2019-11-15 | 2019-11-21 | 4 | 2019-11-21 | [14 empty] | 2019-12-04 | 2019-12-04 |  | Y
Central Hudson |  | Kasselman Solar | CH-12046 | Newburgh | Highland | Ulster | 12528 | G | 5022 | Ohioville | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000H-US (240V) | 2019-11-07 | 2019-11-14 | 5 | 2019-11-14 | [14 empty] | 2019-12-03 | 2019-12-03 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12049 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8045 | Myers Corners | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600A-US (240V) | 2019-11-21 | 2019-11-22 | 1 | 2019-11-22 | [14 empty] | 2019-12-02 | 2019-12-02 |  | Y
Central Hudson |  | MOMENTUM SOLAR | CH-12055 | Newburgh | Walden |  | 12586 | G | 5042 | East Walden | N |  | 12.96 | [13 empty] | NM | N | 54 Enphase Energy IQ7-60-x-US (240V) | 2019-11-08 | 2019-11-14 | 4 | 2019-11-14 | [8 empty] | 350 | 350 |  | 2019-11-22 | 2019-11-22 | 2019-12-19 |  |  |  | W
Central Hudson |  | American Solar Partners | CH-12054 | Newburgh | Rock Tvrn |  | 12575 | G | 4097 | Bethlehem Rd | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2019-11-22 | 2019-11-25 | 1 | 2019-11-25 | [14 empty] | 2020-03-10 | 2020-03-17 |  | W
Central Hudson |  | Empire Solar Solutions | CH-12053 | Poughkeepsie | Clinton Cors | Dutchess | 12514 | G | 7013 | Hibernia | N |  | 23.8 | [13 empty] | NM | N | 1 SolarEdge Technologies SE 10000A-US (240V) 1 SolarEdge Technologies SE 10000A-US (240V) 1 SolarEdge Technologies SE3800 (240V) | 2019-11-22 | 2019-11-25 | 1 | 2019-11-25 | [8 empty] | 350 | 350 |  | 2019-11-27 | 2019-11-27 | 2019-12-16 | 2020-01-07 | 2020-01-07 |  | Y
Central Hudson |  | New York State Solar Farm | CH-12058 | Catskill | Tannersvl | Greene | 12485 | G | 2385 | Lawrenceville | N |  | 8.505 | [13 empty] | NM | N | 27 SunPower SPR-E19-320-E-AC (240V) | 2019-11-11 | 2019-11-14 | 3 | 2019-11-14 | [14 empty] | 2019-12-31 | 2020-01-07 |  | Y
Central Hudson |  | Suncommon | CH-12061 | Fishkill | Garrison | Putnam | 10524 | G | 8066 | Merritt Park | N |  | 22.8 | [13 empty] | NM | N | 2 SolarEdge Technologies SE11400H-US (240V) | 2020-02-18 | 2020-02-19 | 1 | 2020-02-19 | [14 empty] | 2021-01-11 | 2021-01-11 |  | Y
Central Hudson |  | Suncommon | CH-12059 | Kingston | Shokan | Ulster | 12481 | G | 3011 | Woodstock | N |  | 12 | [13 empty] | NM | N | 2 SolarEdge Technologies SE6000H-US (240V) | 2019-11-15 | 2019-11-21 | 4 | 2019-11-21 | [14 empty] | 2020-01-21 | 2020-01-28 |  | Y
Central Hudson |  | AEC Solar Energy Corp. | CH-12060 | Catskill | Westerlo | Albany | 12193 | G | 1091 | Westerlo | N |  | 6.93 | [13 empty] | NM | N | 22 SunPower SPR-E20-327-E-AC (240V) [SI1] | 2019-11-15 | 2019-11-21 | 4 | 2019-11-21 | [14 empty] | 2020-01-29 | 2020-01-29 |  | Y
Central Hudson |  | PlugPV LLC | CH-12063 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6043 | Spackenkill | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2019-11-11 | 2019-11-15 | 4 | 2019-11-15 | [14 empty] | 2019-12-13 | 2019-12-26 |  | Y
Central Hudson |  | PlugPV LLC | CH-12062 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7052 | Rhinebeck | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2019-11-11 | 2019-11-15 | 4 | 2019-11-15 | [14 empty] | 2020-01-29 | 2020-01-29 |  | Y
Central Hudson |  | Sunrun Inc | CH-12074 | Kingston | Saugerties | Ulster | 12477 | G | 3004 | Saugerties | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2019-11-19 | 2019-11-21 | 2 | 2019-11-21 | [14 empty] | 2020-03-31 | 2020-04-01 |  | Y
Central Hudson |  | Tesla Energy | CH-12072 | Fishkill | Cold Spg | Putnam | 10516 | G | 8087 | Tioronda | N |  | 3.8 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3800H-US (240V) [SI1] | 2019-11-20 | 2019-11-22 | 2 | 2019-11-22 | [14 empty] | 2020-01-17 | 2020-01-17 |  | Y
Central Hudson |  | Common Energy | CH-12073 | Kingston | Saugerties | Ulster | 12477 | G | 3005 | Saugerties | N |  | 1900 | [13 empty] | CDG | Y | 8 Sungrow Power Supply SG125HV (600V) 8 Sungrow Power Supply SG125HV (600V) | 2019-11-12 | 2019-11-20 | 6 | 2019-11-20 | 2019-11-20 | 2019-11-21 | 1 | 2019-12-05 | 2020-01-07 | 2020-04-01 | 60 | 14112.68 | 318075 | 183287.19 | 2020-04-21 | 2020-10-06 | 2020-10-06 | 2021-05-06 | 2021-06-17 | 2021-06-17 | 2022-03-24 | Y | Y
Central Hudson |  | US Energy Concierge, Inc | CH-12070 | Fishkill | Garrison | Putnam | 10524 | G | 8066 | Merritt Park | N |  | 3.8 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3800H-US (240V) [SI1] | 2019-11-25 | 2019-11-25 | 0 | 2019-11-25 | [14 empty] | 2019-12-31 | 2019-12-31 |  | Y
Central Hudson |  | New York State Solar Farm | CH-12065 | Newburgh | Marlboro | Ulster | 12542 | G | 5004 | Marlboro | N |  | 11.168 | [13 empty] | NM | N | 32 SunPower SPR-A400-G-AC (240V) | 2019-11-12 | 2019-11-15 | 3 | 2019-11-15 | [14 empty] | 2019-12-04 | 2019-12-04 |  | Y
Central Hudson |  | New York State Solar Farm | CH-12066 | Poughkeepsie | Stanfordville | Dutchess | 12581 | G | 7061 | Milan | N |  | 5.235 | [13 empty] | NM | N | 15 SunPower SPR-A400-G-AC (240V) | 2019-11-22 | 2019-11-25 | 1 | 2019-11-25 | [14 empty] | 2019-12-04 | 2019-12-12 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12069 | Kingston | Olive Brdg | Ulster | 12461 | G | 3024 | High Falls | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000 (240V) | 2019-11-12 | 2019-11-15 | 3 | 2019-11-15 | [14 empty] | 2019-12-10 | 2019-12-10 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12068 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6064 | Inwood Ave | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000 (240V) | 2019-11-12 | 2019-11-15 | 3 | 2019-11-15 | [14 empty] | 2019-12-11 | 2019-12-11 |  | Y
Central Hudson |  | Suncommon | CH-12082 | Poughkeepsie | Rhinebeck |  | 12572 | G | 7053 | Rhinebeck | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE11400H-US (240V) | 2019-11-19 | 2019-11-21 | 2 | 2019-11-21 | [17 empty] | W
Central Hudson |  | Empire Solar Solutions | CH-12085 | Newburgh | Goshen | Orange | 10924 | G | 5051 | Maybrook | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE 11400A-US (240V) | 2019-11-13 | 2019-11-19 | 4 | 2019-11-19 | [8 empty] | 350 | 350 |  | 2019-11-21 | 2019-11-21 | 2019-12-19 | 2020-01-20 | 2020-01-20 |  | Y
Central Hudson |  | PlugPV LLC | CH-12083 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6003 | Reynolds Hill | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2019-11-13 | 2019-11-19 | 4 | 2019-11-19 | [14 empty] | 2020-03-16 | 2020-03-20 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-12078 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 7024 | Tinkertown | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2019-11-13 | 2019-11-19 | 4 | 2019-11-19 | [14 empty] | 2019-12-10 | 2019-12-11 |  | Y
Central Hudson |  | Sunrun Installation Service, Inc. | CH-12080 | Newburgh | Newburgh | Orange | 12550 | G | 5001 | Marlboro | N |  | 7.6 | [13 empty] | NM | N | 1 Ningbo Ginlong Technologies Solis-1P7.6K-4G-US | 2019-11-13 | 2019-11-19 | 4 | 2019-11-19 | [14 empty] | 2020-02-06 | 2020-02-18 |  | Y
Central Hudson |  | Tri-State Solar Services | CH-12084 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2019-11-19 | 2019-11-21 | 2 | 2019-11-21 | [14 empty] | 2019-12-10 | 2019-12-10 |  | Y
Central Hudson |  | PlugPV, LLC | CH-12077 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8092 | Fishkill Plains | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2019-11-13 | 2019-11-15 | 2 | 2019-11-15 | [14 empty] | 2019-12-27 | 2020-01-03 |  | Y
Central Hudson |  | Tesla Energy | CH-12075 | Newburgh | New Windsor | Orange | 12553 | G | 4095 | Bethlehem Rd | Y |  | 10 | 10 | [12 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) [SI1] 2TeslaAC Powerwall 2.0 | 2019-11-21 | 2019-11-22 | 1 | 2019-11-22 | [8 empty] | 350 | 350 |  | 2020-01-14 | 2020-01-14 | 2020-01-24 | 2020-02-06 | 2020-02-12 |  | Y
Central Hudson |  | Kasselman Solar | CH-12076 | Poughkeepsie | Pine Plns | Dutchess | 12567 | G | 7092 | Pulvers Corners | N |  | 8.88 | [13 empty] | NM | N | 37 Enphase Energy IQ7-60-x-US (240V) | 2019-11-18 | 2019-11-21 | 3 | 2019-11-21 | [14 empty] | 2019-12-27 | 2019-12-27 |  | Y
Central Hudson |  | Suncommon | CH-12081 | Fishkill | Cold Spg | Putnam | 10516 | G | 8087 | Tioronda | N |  | 3.8 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3800H-US (240V) | 2019-11-22 | 2019-11-25 | 1 | 2019-11-25 | [14 empty] | 2020-03-20 | 2020-04-03 |  | Y
Central Hudson |  | Solar Generation | CH-12086 | Kingston | Shokan | Ulster | 12481 | G | 3011 | Woodstock | N |  | 5.8 | [13 empty] | NM | N | 20 Enphase Energy IQ7PLUS-72-x-US (240V) [SI1] | 2019-11-21 | 2019-11-22 | 1 | 2019-11-22 | [8 empty] | 350 | 350 |  | 2019-12-05 | 2019-12-05 | 2020-01-24 | 2020-12-21 | 2020-12-21 |  | Y
Central Hudson |  | Suncommon | CH-12087 | Catskill | Purling | Greene | 12470 | G | 2042 | South Cairo | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000H-US (240V) | 2019-11-14 | 2019-11-21 | 5 | 2019-11-21 | [14 empty] | 2020-02-25 | 2020-03-02 |  | Y
Central Hudson |  | Sunrun Inc | CH-12090 | Poughkeepsie | Poughkeepsie |  | 12601 | G | 6011 | Sand Dock | N |  | 3 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3000H-US (240V) | 2019-11-21 | 2019-12-04 | 7 | 2019-12-04 | [17 empty] | W
Central Hudson |  | Trinity Solar | CH-12089 | Newburgh | Montgomery | Orange | 12549 | G | 4026 | Coldenham | N | CH-12089 | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000H-US (240V) | 2019-11-21 | 2019-11-22 | 1 | 2019-11-22 | [14 empty] | 2020-01-20 | 2020-01-22 |  | Y
Central Hudson |  | Solar Generation | CH-12088 | Kingston | Woodstock | Ulster | 12498 | G | 3014 | Woodstock | N | CH-12088 | 5.76 | [13 empty] | NM | N | 24 Enphase Energy IQ7-60-x-US (240V) | 2019-11-14 | 2019-11-21 | 5 | 2019-11-21 | [14 empty] | 2020-01-08 | 2020-01-09 |  | Y
Central Hudson |  | Vivint Solar Developer, LLC | CH-12093 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 5.29 | [13 empty] | NM | N | 23 Enphase Energy IQ6-60-X-US (240V) | 2019-11-21 | 2019-11-25 | 2 | 2019-11-25 | [14 empty] | 2020-03-26 | 2020-03-26 |  | Y
Central Hudson |  | New York State Solar Farm | CH-12096 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7052 | Rhinebeck | N |  | 7.56 | [13 empty] | NM | N | 24 SunPower SPR-X22-360-E-AC (240V) | 2019-11-15 | 2019-11-21 | 4 | 2019-11-21 | [14 empty] | 2019-11-26 | 2019-11-27 |  | Y
Central Hudson |  | Kasselman Solar | CH-12099 | Kingston | Saugerties | Ulster | 12477 | G | 3003 | Saugerties | N |  | 5.76 | [13 empty] | NM | N | 24 Enphase Energy IQ7-60-x-US (240V) | 2019-11-21 | 2019-11-25 | 2 | 2019-11-25 | [14 empty] | 2019-12-05 | 2019-12-12 |  | Y
Central Hudson |  | Kasselman Solar | CH-12097 | Catskill | Greenvl |  | 12083 | G | 2061 | Freehold | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2019-11-18 | 2019-11-21 | 3 | 2019-11-21 | [17 empty] | W
Central Hudson |  | SRE Solar Origination 2, LLC | CH-12101 | Newburgh | Gardiner |  | 12525 | G | 5033 | Galeville | N |  | 2875 | [13 empty] | CDG | Y | 23SolectriaXGI 1500-125/125 | 2020-01-07 | 2020-01-10 | 3 | 2020-01-10 | 2020-01-10 | 2020-01-30 | 14 |  |  |  |  | 17000 | [9 empty] | W
Central Hudson |  | Solar Generation Projects, LLC | CH-12100 | Kingston | Saugerties | Ulster | 12477 | G | 3004 | Saugerties | N |  | 250 | [13 empty] | CDG | Y | 2 SMA America SHP 125-US-20 (480V) | 2020-03-16 | 2020-03-30 | 10 | 2020-03-30 | 2020-03-30 | 2020-04-21 | 15 | [11 empty] | 2021-06-28 | 2021-06-28 |  | Y | Y
Central Hudson |  | PlugPV, LLC | CH-12098 | Newburgh | Montgomery | Orange | 12549 | G | 5073 | Montgomery | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2019-11-18 | 2019-11-21 | 3 | 2019-11-21 | [8 empty] | 350 | 350 |  | 2019-11-25 | 2019-11-25 | 2019-12-19 | 2020-01-24 | 2020-01-27 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12103 | Kingston | Saugerties | Ulster | 12477 | G | 2015 | Lincoln Park | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000 (240V) | 2019-11-19 | 2019-11-21 | 2 | 2019-11-21 | [14 empty] | 2019-12-30 | 2019-12-30 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12102 | Newburgh | Montgomery | Orange | 12549 | G | 5073 | Montgomery | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE 11400A-US (240V) | 2019-11-19 | 2019-11-21 | 2 | 2019-11-21 | [14 empty] | 2019-12-18 | 2019-12-18 |  | Y
Central Hudson |  | MOMENTUM SOLAR | CH-12105 | Fishkill | Carmel | Putnam | 10512 | G | 8071 | Shenandoah | N |  | 27.84 | [13 empty] | NM | Y | 96 Enphase Energy IQ7PLUS-72-x-US (240V) | 2019-11-19 | 2019-12-05 | 10 | 2019-12-05 | [8 empty] | 995 | 1108.14 |  | 2019-12-13 | 2019-12-13 | 2020-01-30 | 2020-03-04 | 2020-03-11 | 2020-05-06 | Y | N
Central Hudson |  | Suncommon | CH-12104 | Kingston | Kingston | Ulster | 12401 | G | 2092 | Hurley Ave | N |  | 312.5 | [13 empty] | CDG | Y | 5 SMA America STP 62-US-41 (480V) | 2019-12-11 | 2019-12-26 | 9 | 2019-12-26 | 2019-12-26 | 2020-01-13 | 11 | [5 empty] | 135275 | 86523.25 | 2020-07-27 | 2020-09-25 | 2020-09-25 | 2021-09-24 | 2021-11-16 | 2021-11-17 | 2022-02-11 | Y | Y
Central Hudson |  | Empire Solar Solutions | CH-12108 | Kingston | Kerhonkson | Ulster | 12446 | G | 3082 | Kerhonkson | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000 (240V) | 2019-11-20 | 2019-11-22 | 2 | 2019-11-22 | [14 empty] | 2019-11-26 | 2019-11-26 |  | Y
Central Hudson |  | PlugPV LLC | CH-12107 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8072 | Shenandoah | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE11400H-US (240V) | 2019-12-10 | 2019-12-11 | 1 | 2019-12-11 | [14 empty] | 2020-01-07 | 2020-01-09 |  | Y
Central Hudson |  | PlugPV LLC | CH-12106 | Kingston | Ulster Pk | Ulster | 12487 | G | 1023 | East Kingston | N | CH-10831 | 3 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3000H-US (240V) | 2019-11-25 | 2019-11-25 | 0 | 2019-11-25 | [8 empty] | 350 | 350 |  | 2019-12-02 | 2019-12-02 | 2020-01-20 | 2020-01-28 | 2020-01-29 |  | Y
Central Hudson |  | Solar Generation | CH-12109 | Kingston | Stone Ridge | Ulster | 12484 | G | 3024 | High Falls | N |  | 7.6 | [13 empty] | NM | N | 1 Pika Energy X7602 (240V) | 2019-11-25 | 2019-11-25 | 0 | 2019-11-25 | [14 empty] | 2020-02-18 | 2020-02-18 |  | Y
Central Hudson |  | Sunrun Installation Service, Inc. | CH-12114 | Fishkill | Beacon | Dutchess | 12508 | G | 8015 | Forgebrook | N | CH-12114 | 3.84 | [13 empty] | NM | N | 1 Delta Electronics M4-TL-US (240V) [SI1] | 2019-12-03 | 2019-12-03 | 0 | 2019-12-03 | [14 empty] | 2020-03-03 | 2020-03-10 |  | Y
Central Hudson |  | Solar Generation | CH-12110 | Kingston | Hurley | Ulster | 12443 | G | 2094 | Hurley Ave | N |  | 10 | [13 empty] | NM | N | 2 SMA America SB5000US (240V) | 2019-11-21 | 2019-11-22 | 1 | 2019-11-22 | [14 empty] | 2020-07-23 | 2020-07-23 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12112 | Kingston | Hurley | Ulster | 12443 | G | 2094 | Hurley Ave | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000 (240V) | 2019-11-21 | 2019-11-25 | 2 | 2019-11-25 | [14 empty] | 2019-12-06 | 2019-12-09 |  | Y
Central Hudson |  | Kasselman Solar | CH-12113 | Catskill | Jewett | Greene | 12444 | E | 2081 | Hunter | Y |  | 3.8 | 3.8 | [12 empty] | NM | N | 1 SolarEdge Technologies SE3800 (240V) 1SolarEdge TechnologiesSE7600A-US | 2019-11-21 | 2019-11-25 | 2 | 2019-11-25 | [14 empty] | 2020-02-04 | 2020-02-11 |  | Y
Central Hudson |  | PlugPV LLC | CH-12111 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6068 | Inwood Ave | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2019-11-25 | 2019-11-25 | 0 | 2019-11-25 | [14 empty] | 2020-01-10 | 2020-01-17 |  | Y
Central Hudson |  | Apex Roofing dba Seamless Solar | CH-12117 | Newburgh | Newburgh | Orange | 12550 | G | 4011 | West Balmville | N |  | 10.88 | [13 empty] | NM | N | 34 SunPower SPR-X21-335-D-AC (240V) | 2019-12-05 | 2019-12-06 | 1 | 2019-12-06 | [14 empty] | 2020-01-06 | 2020-01-08 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-12116 | Kingston | High Fls |  | 12440 | G | 3022 | High Falls | N |  | 8.4 | [13 empty] | NM | N | 35 Enphase Energy IQ7-60-x-US (240V) | 2019-11-22 | 2019-11-25 | 1 | 2019-11-25 | [17 empty] | W
Central Hudson |  | Empire Solar Solutions | CH-12119 | Fishkill | Beacon | Dutchess | 12508 | G | 8087 | Tioronda | N |  | 3 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3000 (240V) | 2019-11-22 | 2019-11-25 | 1 | 2019-11-25 | [14 empty] | 2019-12-04 | 2019-12-04 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12118 | Fishkill | Beacon | Dutchess | 12508 | G | 8087 | Tioronda | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000 (240V) | 2019-11-22 | 2019-11-25 | 1 | 2019-11-25 | [14 empty] | 2019-12-02 | 2019-12-06 |  | Y
Central Hudson |  | Tesla Energy | CH-12115 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8092 | Fishkill Plains | Y |  | 10 | 10 | [12 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) 2TeslaAC Powerwall 2.0 | 2019-11-22 | 2019-11-25 | 1 | 2019-11-25 | [14 empty] | 2020-01-08 | 2020-01-08 |  | Y
Central Hudson |  | Kasselman Solar | CH-12120 | Kingston | Accord | Ulster | 12404 | G | 3081 | Kerhonkson | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2019-11-22 | 2019-11-25 | 1 | 2019-11-25 | [14 empty] | 2019-12-03 | 2019-12-12 |  | Y
Central Hudson |  | New York State Solar Farm | CH-12122 | Kingston | Saugerties | Ulster | 12477 | G | 3003 | Saugerties | N |  | 12.6 | [13 empty] | NM | N | 40 SunPower SPR-E19-320-E-AC (240V) | 2019-11-25 | 2019-11-25 | 0 | 2019-11-25 | [14 empty] | 2019-12-23 | 2019-12-23 |  | Y
Central Hudson |  | New York State Solar Farm | CH-12121 | Newburgh | Walden | Orange | 12586 | G | 5042 | East Walden | N |  | 13.23 | [13 empty] | NM | N | 42 SunPower SPR-E19-320-E-AC (240V) | 2019-12-04 | 2019-12-06 | 2 | 2019-12-06 | [14 empty] | 2020-01-14 | 2020-01-14 |  | Y
Central Hudson |  | Ramapo Communication Corp. | CH-12124 | Newburgh | Newburgh | Orange | 12550 | G | 4092 | Bethlehem Rd | N |  |  | 210 | [12 empty] | NA | N | 1Tesla1134768-31-A | 2020-03-23 | 2020-04-06 | 10 | 2020-04-06 | 2020-04-06 | 2020-04-28 | 15 | [11 empty] | 2021-04-08 | 2021-04-15 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12123 | Newburgh | Newburgh | Orange | 12550 | G | 5004 | Marlboro | N |  | 22.8 | [13 empty] | NM | N | 2 SolarEdge Technologies SE 11400A-US (240V) | 2019-11-25 | 2019-12-09 | 8 | 2019-12-09 | [14 empty] | 2020-02-04 | 2020-02-04 |  | Y
Central Hudson |  | PlugPV LLC | CH-12126 | Kingston | Cottekill | Ulster | 12419 | G | 3021 | High Falls | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2019-11-26 | 2019-11-27 | 1 | 2019-11-27 | [14 empty] | 2020-01-21 | 2020-02-03 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12125 | Newburgh | Clintondale | Ulster | 12515 | G | 5024 | Ohioville | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000 (240V) | 2019-11-26 | 2019-11-27 | 1 | 2019-11-27 | [14 empty] | 2019-12-10 | 2019-12-10 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12129 | Newburgh | Newburgh | Orange | 12550 | G | 4011 | West Balmville | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE 10000A-US (240V) | 2019-11-27 | 2019-12-02 | 1 | 2019-12-02 | [14 empty] | 2020-01-10 | 2020-01-10 |  | Y
Central Hudson |  | murphy solar and central air | CH-12127 | Kingston | Boicevl | Ulster | 12412 | G | 3011 | Woodstock | N |  | 6 | [13 empty] | NM | N | 1 SMA America SB6000U (240V) | 2020-01-02 | 2020-01-03 | 1 | 2020-01-03 | [14 empty] | 2020-04-13 | 2020-04-13 |  | Y
Central Hudson |  | New York State Solar Farm | CH-12128 | Newburgh | Walden | Orange | 12586 | G | 5042 | East Walden | N |  | 1.89 | [13 empty] | NM | N | 6 SunPower SPR-E19-320-E-AC (240V) | 2019-12-04 | 2019-12-06 | 2 | 2019-12-06 | [14 empty] | 2020-01-14 | 2020-01-14 |  | Y
Central Hudson |  | Tesla Energy | CH-12131 | Poughkeepsie | Poughquag | Dutchess | 12570 | G | 6055 | Todd Hill | Y | CH-01484 |  | 10 | [12 empty] | NM | N | 2TeslaAC Powerwall 2.0 | 2019-12-30 | 2019-12-30 | 0 | 2019-12-30 | [14 empty] | 2020-03-31 | 2020-03-31 |  | Y
Central Hudson |  | Solitude Solar, LLC | CH-12130 | Catskill | Westerlo |  | 12193 | G | 1091 | Westerlo | N |  | 4000 | [13 empty] | CDG | Y | 32 Chint Power Systems America CPS SCH125KTL-DO/US-600 (600V) | 2020-01-02 | 2020-01-10 | 6 | 2020-01-10 | 2020-01-10 | 2020-01-30 | 14 | [14 empty] | W
Central Hudson |  | Kasselman Solar | CH-11893 | Catskill | Round Top | Greene | 12473 | G | 2042 | South Cairo | N |  | 57 | [13 empty] | NM | N | 5 SolarEdge Technologies SE11400H-US (240V) | 2020-02-07 | 2020-02-24 | 10 | 2020-02-24 | 2020-02-24 | 2020-03-11 | 12 | [5 empty] | 1300 | 1861.81 |  | 2020-03-24 | 2020-03-24 | 2020-03-31 | 2021-07-20 | 2021-07-26 | 2021-08-30 | Y
Central Hudson |  | Kasselman Solar | CH-12134 | Kingston | Glenford | Ulster | 12433 | G | 3012 | Woodstock | N |  | 22.8 | [13 empty] | NM | N | 2 SolarEdge Technologies SE11400H-US (240V) | 2019-12-02 | 2019-12-03 | 1 | 2019-12-03 | [8 empty] | 350 | 350 |  | 2019-12-10 | 2019-12-10 | 2020-01-24 | 2020-02-12 | 2020-02-12 |  | Y | Y
Central Hudson |  | Lighthouse Solar | CH-12135 | Kingston | Stone Ridge | Ulster | 12484 | G | 3024 | High Falls | N |  | 22.62 | [13 empty] | NM | N | 78 Enphase Energy IQ7PLUS-72-x-US (240V) | 2019-12-02 | 2019-12-02 | 0 | 2019-12-02 | [8 empty] | 350 | 350 |  | 2019-12-05 | 2019-12-05 | 2020-01-22 | 2020-02-04 | 2020-02-04 |  | Y
Central Hudson |  | Lighthouse Solar | CH-12136 | Kingston | Stone Ridge | Ulster | 12484 | G | 3024 | High Falls | N |  | 12.18 | [13 empty] | NM | N | 42 Enphase Energy IQ7PLUS-72-x-US (240V) | 2019-12-02 | 2019-12-02 | 0 | 2019-12-02 | [8 empty] | 350 | 350 |  | 2019-12-05 | 2019-12-05 | 2020-01-22 | 2020-02-04 | 2020-02-04 |  | Y
Central Hudson |  | Albany Solar Solutions LLC | CH-12140 | Catskill | Jewett | Greene | 12444 | E | 2081 | Hunter | N |  | 8.64 | [13 empty] | NM | N | 12 Chilicon Power CP-720-60/72/96-208/240-MC4 (240V) [SI1] | 2019-12-04 | 2019-12-05 | 1 | 2019-12-05 | [14 empty] | 2019-12-16 | 2019-12-16 |  | Y
Central Hudson |  | Albany Solar Solutions | CH-12141 | Poughkeepsie | Millbrook | Dutchess | 12545 | G | 7012 | Hibernia | N |  | 12.96 | [13 empty] | NM | N | 18 Chilicon Power CP-720-60/72/96-208/240-MC4 (240V) [SI1] | 2019-12-04 | 2019-12-06 | 2 | 2019-12-06 | [14 empty] | 2019-12-30 | 2019-12-31 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12137 | Kingston | Glenford | Ulster | 12433 | G | 3013 | Woodstock | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE 10000A-US (240V) | 2019-12-04 | 2019-12-18 | 10 | 2019-12-18 | [14 empty] | 2019-12-23 | 2019-12-27 |  | Y
Central Hudson |  | Sunrun Inc | CH-12139 | Newburgh | Newburgh | Orange | 12550 | G | 4012 | West Balmville | N |  | 8 | [13 empty] | NM | N | 1 Delta Electronics M8-TL-US (240V) [SI1] | 2020-01-30 | 2020-02-05 | 4 | 2020-02-05 | [14 empty] | 2020-02-18 | 2020-02-19 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12138 | Catskill | Preston Holw | Albany | 12469 | G | 1092 | Westerlo | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE 11400A-US (240V) | 2019-12-04 | 2019-12-06 | 2 | 2019-12-06 | [14 empty] | 2020-01-20 | 2020-01-20 |  | Y
Central Hudson |  | Bright Planet Solar | CH-12146 | Poughkeepsie | Poughkeepsie |  | 12601 | G | 6002 | Reynolds Hill | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2019-12-05 | 2019-12-06 | 1 | 2019-12-06 | [17 empty] | W
Central Hudson |  | New York State Solar Farm | CH-12148 | Kingston | Ulster Pk | Ulster | 12487 | G | 1014 | Boulevard | N |  | 8.82 | [13 empty] | NM | N | 28 SunPower SPR-X22-360-E-AC (240V) | 2019-12-05 | 2019-12-06 | 1 | 2019-12-06 | [14 empty] | 2019-12-18 | 2019-12-18 |  | Y
Central Hudson |  | Solar Generation | CH-12143 | Kingston | Ulster Pk | Ulster | 12487 | G | 3041 | Sturgeon Pool | N |  | 7.7 | [13 empty] | NM | N | 1 SMA America SB7700TL-US-22 (240V) | 2019-12-05 | 2019-12-06 | 1 | 2019-12-06 | [14 empty] | 2020-11-02 | 2020-11-02 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12142 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6045 | Spackenkill | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600A-US (240V) | 2019-12-05 | 2019-12-06 | 1 | 2019-12-06 | [14 empty] | 2020-02-10 | 2020-02-10 |  | Y
Central Hudson |  | Solar Generation | CH-12144 | Kingston | Saugerties | Ulster | 12477 | G | 3003 | Saugerties | N |  | 15.3 | [13 empty] | NM | N | 1 Pika Energy X7602 (240V) 1 SMA America SB7700TL-US-22 (240V) | 2019-12-13 | 2019-12-30 | 9 | 2019-12-30 | [8 empty] | 350 | 350 |  | 2020-01-08 | 2020-01-08 | 2019-12-13 | 2020-02-10 | 2020-02-18 |  | Y
Central Hudson |  | Solar Generation | CH-12145 | Kingston | Woodstock | Ulster | 12498 | G | 2016 | Lincoln Park | N | CH-10253 | 1.74 | [13 empty] | NM | N | 6 Enphase Energy IQ7PLUS-72-x-US (240V) | 2019-12-13 | 2019-12-16 | 1 | 2019-12-16 | [14 empty] | 2020-01-08 | 2020-01-09 |  | Y
Central Hudson |  | PlugPV, LLC | CH-12147 | Newburgh | Montgomery | Orange | 12549 | G | 5073 | Montgomery | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2019-12-06 | 2019-12-09 | 1 | 2019-12-09 | [14 empty] | 2020-01-02 | 2020-01-03 |  | Y
Central Hudson |  | GRID Alternatives | CH-11975 | Poughkeepsie | Millbrook |  | 12545 | G | 7025 | Tinkertown | N |  | 1950 | [13 empty] | CDG | Y | 13 SMA America SHP 150-US-20 (600V) | 2020-02-12 | 2020-02-26 | 9 | 2020-02-26 | 2020-02-26 | 2020-03-16 | 13 |  |  |  |  | 15000 | [9 empty] | W
Central Hudson |  | New York State Solar Farm | CH-12149 | Kingston | Kingston | Ulster | 12401 | G | 1011 | Boulevard | N |  | 6.93 | [13 empty] | NM | N | 22 SunPower SPR-E20-327-E-AC (240V) | 2019-12-06 | 2019-12-10 | 2 | 2019-12-10 | [14 empty] | 2019-12-12 | 2019-12-13 |  | Y
Central Hudson |  | Tesla Energy | CH-12150 | Fishkill | Beacon | Dutchess | 12508 | G | 8087 | Tioronda | Y |  | 7.6 | 5 | [12 empty] | NM | N | 1 Delta Electronics SOLIVIA 7.6 NA G4 TL (240V) 1TeslaAC Powerwall 2.0 | 2019-12-11 | 2019-12-12 | 1 | 2019-12-12 | [14 empty] | 2020-02-13 | 2020-02-14 |  | Y
Central Hudson |  | murphy solar and central air | CH-12151 | Catskill | Round Top | Greene | 12473 | G | 2042 | South Cairo | N |  | 7 | [13 empty] | NM | N | 1 SMA America SB7000US (240V) | 2020-01-14 | 2020-01-14 | 0 | 2020-01-14 | [14 empty] | 2020-05-18 | 2020-05-18 |  | Y
Central Hudson |  | MOMENTUM SOLAR | CH-12156 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 6074 | East Park | N |  | 5.51 | [13 empty] | NM | N | 19 Enphase Energy IQ7PLUS-72-x-US (240V) | 2019-12-11 | 2019-12-12 | 1 | 2019-12-12 | [14 empty] | 2020-03-06 | 2020-03-12 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12155 | Newburgh | Wallkill | Ulster | 12589 | G | 5041 | East Walden | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE 10000A-US (240V) | 2019-12-09 | 2019-12-11 | 2 | 2019-12-11 | [14 empty] | 2020-02-03 | 2020-02-04 |  | Y
Central Hudson |  | Suncommon | CH-12153 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 7011 | Hibernia | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000H-US (240V) | 2019-12-11 | 2019-12-11 | 0 | 2019-12-11 | [14 empty] | 2020-10-06 | 2020-10-06 |  | Y
Central Hudson |  | New York State Solar Farm | CH-12157 | Kingston | Bearsvl | Ulster | 12409 | G | 3012 | Woodstock | N | CH-12157 | 20.475 | [13 empty] | NM | N | 65 SunPower SPR-X22-360-E-AC (240V) | 2019-12-09 | 2019-12-11 | 2 | 2019-12-11 | [8 empty] | 350 | 350 |  | 2019-12-30 | 2019-12-30 | 2020-01-29 | 2020-03-30 | 2020-03-31 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-12152 | Newburgh | Newburgh |  | 12550 | G | 5004 | Marlboro | N |  | 4.56 | [13 empty] | NM | N | 19 Enphase Energy IQ7-60-x-US (240V) | 2019-12-11 | 2019-12-11 | 0 | 2019-12-11 | [17 empty] | W
Central Hudson |  | New York State Solar Farm | CH-12154 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7052 | Rhinebeck | N |  | 8.376 | [13 empty] | NM | N | 24 SunPower SPR-A400-G-AC (240V) | 2019-12-09 | 2019-12-11 | 2 | 2019-12-11 | [14 empty] | 2019-12-19 | 2019-12-20 |  | Y
Central Hudson |  | Solar Image | CH-12160 | Newburgh | Campbell Hall | Orange | 10916 | G | 5052 | Maybrook | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2019-12-12 | 2019-12-12 | 0 | 2019-12-12 | [14 empty] | 2020-01-13 | 2020-01-15 |  | Y
Central Hudson |  | New York State Solar Farm | CH-12159 | Newburgh | New Windsor | Orange | 12553 | G | 4095 | Bethlehem Rd | N |  | 12.6 | [13 empty] | NM | N | 40 SunPower SPR-E19-320-E-AC (240V) | 2019-12-10 | 2019-12-19 | 7 | 2019-12-19 | [14 empty] | 2020-01-24 | 2020-01-27 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12158 | Catskill | Climax | Greene | 12042 | G | 2061 | Freehold | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2019-12-12 | 2019-12-12 | 0 | 2019-12-12 | [8 empty] | 350 | 350 |  | 2020-01-20 | 2020-01-20 | 2020-01-27 | 2020-02-14 | 2020-02-14 |  | Y
Central Hudson |  | Sunrun Inc | CH-12163 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6063 | Inwood Ave | N |  | 15.36 | [13 empty] | NM | N | 1 Delta Electronics M8-TL-US (240V) [SI1] 1 Delta Electronics M8-TL-US (240V) [SI1] | 2019-12-12 | 2019-12-12 | 0 | 2019-12-12 | [14 empty] | 2020-09-23 | 2020-09-23 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12161 | Newburgh | Wallkill | Ulster | 12589 | G | 5013 | Modena | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE 10000A-US (240V) | 2019-12-11 | 2019-12-12 | 1 | 2019-12-12 | [14 empty] | 2019-12-23 | 2019-12-23 |  | Y
Central Hudson |  | Suncommon | CH-12162 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7051 | Rhinebeck | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2019-12-13 | 2019-12-16 | 1 | 2019-12-16 | [14 empty] | 2020-03-23 | 2020-03-23 |  | Y
Central Hudson |  | 103 Sparling Road LLC | CH-12164 | Kingston | Saugerties | Ulster | 12477 | G | 3004 | Saugerties | N |  | 3450 | [13 empty] | CDG | Y | 23 SMA America SHP 150-US-20 (600V) 35Chint Power Systems AmericaCPS SCH100KTL-DO/US-600 | 2019-12-11 | 2019-12-26 | 9 | 2019-12-26 | 2019-12-26 | 2020-01-15 | 13 | 2020-02-13 | 2020-03-02 | 2020-05-27 | 60 | 19784.85 | 501268.75 | 392743.71 | 2020-06-11 | 2020-12-03 | 2020-12-03 | 2022-03-25 | 2022-06-28 | 2022-06-28 | 2022-11-23 | Y | Y
Central Hudson |  | PlugPV LLC | CH-12166 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2019-12-12 | 2019-12-12 | 0 | 2019-12-12 | [14 empty] | 2020-02-19 | 2020-02-19 |  | Y
Central Hudson |  | Kasselman Solar | CH-12165 | Newburgh | Newburgh | Orange | 12550 | G | 4011 | West Balmville | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000H-US (240V) | 2019-12-12 | 2019-12-12 | 0 | 2019-12-12 | [14 empty] | 2020-02-03 | 2020-02-10 |  | Y
Central Hudson |  | Bright Planet Solar | CH-12169 | Fishkill | Fishkill |  | 12524 | G | 8011 | Forgebrook | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2019-12-13 | 2019-12-13 | 0 | 2019-12-13 | [17 empty] | W
Central Hudson |  | Sunrun Inc | CH-12170 | Newburgh | Modena | Ulster | 12548 | G | 5012 | Modena | N |  | 3.84 | [13 empty] | NM | N | 1 Delta Electronics M4-TL-US (240V) [SI1] | 2019-12-13 | 2019-12-17 | 2 | 2019-12-17 | [14 empty] | 2020-01-21 | 2020-01-23 |  | Y
Central Hudson |  | PlugPV LLC | CH-12167 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8051 | North Chelsea | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2019-12-20 | 2019-12-20 | 0 | 2019-12-20 | [14 empty] | 2020-02-14 | 2020-02-14 |  | Y
Central Hudson |  | PlugPV LLC | CH-12168 | Catskill | Westerlo | Albany | 12193 | G | 1091 | Westerlo | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000H-US (240V) | 2019-12-17 | 2019-12-18 | 1 | 2019-12-18 | [14 empty] | 2020-06-02 | 2020-06-02 |  | Y
Central Hudson |  | Tesla Energy Operations | CH-12173 | Newburgh | Salisbury Mls | Orange | 12577 | G | 4097 | Bethlehem Rd | Y |  | 7.6 | 10 | [12 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) [SI1] 2TeslaAC Powerwall 2.0 | 2019-12-19 | 2019-12-20 | 1 | 2019-12-20 | [14 empty] | 2020-03-09 | 2020-03-16 |  | Y
Central Hudson |  | Kasselman Solar | CH-12171 | Catskill | S Cairo | Greene | 12482 | G | 2005 | North Catskill | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2019-12-16 | 2019-12-17 | 1 | 2019-12-17 | [14 empty] | 2020-01-29 | 2020-02-03 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12172 | Kingston | Saugerties | Ulster | 12477 | G | 3004 | Saugerties | N |  | 15.2 | [13 empty] | NM | N | 2 SolarEdge Technologies SE7600A-US (240V) | 2019-12-16 | 2019-12-17 | 1 | 2019-12-17 | [14 empty] | 2020-01-14 | 2020-01-14 |  | Y
Central Hudson |  | Sky Solar Inc. | CH-12095 | Newburgh | Highland |  | 12528 | G | 5081 | Highland | N |  | 4000 | [13 empty] | CDG | Y | 32 Sungrow Power Supply SG125HV (600V) | 2020-01-06 | 2020-01-10 | 4 | 2020-01-10 | 2020-01-10 | 2020-01-30 | 14 |  |  |  |  | 17000 | [9 empty] | W
Central Hudson |  | Sunrun Inc | CH-12178 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7051 | Rhinebeck | N |  | 2.64 | [13 empty] | NM | N | 11 Enphase Energy IQ7-60-x-US (240V) | 2019-12-17 | 2020-01-02 | 9 | 2020-01-02 | [14 empty] | 2020-02-06 | 2020-02-10 |  | Y
Central Hudson |  | Trinity Solar | CH-12177 | Newburgh | Newburgh | Orange | 12550 | G | 4051 | Union Ave | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2019-12-17 | 2019-12-20 | 3 | 2019-12-20 | [14 empty] | 2020-02-11 | 2020-02-14 |  | Y
Central Hudson |  | Kasselman Solar | CH-12176 | Catskill | Freehold | Greene | 12431 | G | 2071 | Freehold | Y | CH-12176 | 7.6 | 7.6 | [12 empty] | NM | N | 1 SolarEdge Technologies SE7600A-US (240V) 1SolarEdge TechnologiesSE7600A-US | 2019-12-17 | 2019-12-18 | 1 | 2019-12-18 | [14 empty] | 2020-02-04 | 2020-02-11 |  | Y
Central Hudson |  | Solar Generation | CH-12175 | Kingston | W Hurley | Ulster | 12491 | G | 3013 | Woodstock | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2019-12-17 | 2019-12-18 | 1 | 2019-12-18 | [14 empty] | 2020-02-27 | 2020-03-05 |  | Y
Central Hudson |  | New York State Solar Farm | CH-12180 | Poughkeepsie | Clinton Cors | Dutchess | 12514 | G | 7071 | Stanfordville | N |  | 11.97 | [13 empty] | NM | N | 38 SunPower SPR-X22-360-E-AC (240V) | 2019-12-17 | 2019-12-20 | 3 | 2019-12-20 | [14 empty] | 2020-01-20 | 2020-01-21 |  | Y
Central Hudson |  | Hudson River Renewables | CH-12179 | Kingston | Shady | Ulster | 12409 | G | 3012 | Woodstock | N | CH-03864 | 3.8 | [13 empty] | NM | N | 1 SMA America SB3.8-1SP-US-41 (240V) [SI1] | 2019-12-23 | 2019-12-27 | 2 | 2019-12-27 | [14 empty] | 2020-05-07 | 2020-05-07 |  | Y
Central Hudson |  | Suncommon | CH-12182 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7053 | Rhinebeck | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2019-12-18 | 2019-12-20 | 2 | 2019-12-20 | [14 empty] | 2020-02-28 | 2020-03-06 |  | Y
Central Hudson |  | New York State Solar Farm | CH-12181 | Newburgh | New Paltz | Ulster | 12561 | G | 5021 | Ohioville | N |  | 11.655 | [13 empty] | NM | N | 37 SunPower SPR-E19-320-E-AC (240V) | 2019-12-18 | 2019-12-20 | 2 | 2019-12-20 | [14 empty] | 2019-12-23 | 2019-12-27 |  | Y
Central Hudson |  | Sunrun Inc | CH-12184 | Newburgh | Marlboro | Ulster | 12542 | G | 5004 | Marlboro | N |  | 6 | [13 empty] | NM | N | 1 Delta Electronics M6-TL-US (240V) [SI1] | 2020-01-02 | 2020-01-03 | 1 | 2020-01-03 | [14 empty] | 2020-01-30 | 2020-01-31 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12183 | Kingston | Woodstock | Ulster | 12498 | G | 3013 | Woodstock | N |  | 12 | [13 empty] | NM | N | 2 SolarEdge Technologies SE6000 (240V) | 2019-12-19 | 2019-12-20 | 1 | 2019-12-20 | [14 empty] | 2020-02-28 | 2020-03-06 |  | Y
Central Hudson |  | Suncommon | CH-12186 | Poughkeepsie | Rhinebeck |  | 12572 | G | 7055 | Rhinebeck | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2019-12-26 | 2019-12-27 | 1 | 2019-12-27 | [17 empty] | W
Central Hudson |  | Apex Solar Power, LLC | CH-12189 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8072 | Shenandoah | N |  | 12.56 | [13 empty] | NM | N | 36 Enphase Energy IQ7AS-66-ACM-US-x (240V) | 2019-12-23 | 2019-12-26 | 1 | 2019-12-26 | [14 empty] | 2020-02-24 | 2020-03-02 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12187 | Fishkill | Wappingers Falls | Dutchess | 12590 | G | 8092 | Fishkill Plains | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000 (240V) | 2019-12-23 | 2019-12-23 | 0 | 2019-12-23 | [14 empty] | 2020-02-17 | 2020-02-18 |  | Y
Central Hudson |  | Kilawatt Consulting LLC | CH-12188 | Poughkeepsie | Millerton |  | 12546 | G | 7081 | Millerton | Y |  | 7.2 | 7.2 | [12 empty] | NM | N | 1 OutBack Power Technologies GS8048A (240V) [SI1] 1OutbackRadian A-series GS8048A | 2020-01-03 | 2020-01-17 | 10 | 2020-01-17 | [17 empty] | W
Central Hudson |  | Empire Solar Solutions | CH-12190 | Fishkill | Stormvl | Dutchess | 12582 | G | 8071 | Shenandoah | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE 10000A-US (240V) | 2019-12-27 | 2019-12-27 | 0 | 2019-12-27 | [14 empty] | 2020-01-21 | 2020-01-22 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12191 | Newburgh | Newburgh | Orange | 12550 | G | 4011 | West Balmville | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE 10000A-US (240V) | 2019-12-26 | 2019-12-27 | 1 | 2019-12-27 | [14 empty] | 2020-01-16 | 2020-01-17 |  | Y
Central Hudson |  | Tesla Energy Operations | CH-12192 | Newburgh | Wallkill | Ulster | 12589 | G | 5041 | East Walden | Y |  | 11.4 | 15 | [12 empty] | NM | N | 1 Delta Electronics SOLIVIA 7.6 NA G4 TL (240V) [SI1] 1 Delta Electronics SOLIVIA 3.8 NA G4 TL (240V) [SI1] 3TeslaAC Powerwall 2.0 | 2020-01-30 | 2020-02-03 | 2 | 2020-02-03 | [8 empty] | 350 | 350 |  | 2020-02-13 | 2020-02-13 | 2020-03-18 | 2020-03-20 | 2020-03-20 |  | Y
Central Hudson |  | Sunrun Inc | CH-12195 | Fishkill | Fishkill | Dutchess | 12524 | G | 8094 | Fishkill Plains | N |  | 3.77 | [13 empty] | NM | N | 13 Enphase Energy IQ7PLUS-72-x-US (240V) | 2020-01-06 | 2020-01-07 | 1 | 2020-01-07 | [14 empty] | 2020-01-23 | 2020-01-27 |  | Y
Central Hudson |  | Apex Solar Power, LLC | CH-12193 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8051 | North Chelsea | N |  | 6.98 | [13 empty] | NM | N | 20 Enphase Energy IQ7AS-66-ACM-US-x (240V) | 2019-12-30 | 2019-12-30 | 0 | 2019-12-30 | [14 empty] | 2020-03-02 | 2020-03-02 |  | Y
Central Hudson |  | Vivint Solar Developer, LLC | CH-12196 | Catskill | Greenvl |  | 12083 | G | 2061 | Freehold | N | CH-08728 | 2.3 | [13 empty] | NM | N | 10 Enphase Energy IQ6-60-X-US (240V) | 2020-01-21 | 2020-01-21 | 0 | 2020-01-21 | [17 empty] | W
Central Hudson |  | Tesla Energy | CH-12197 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6095 | Manchester | Y |  | 7.6 | 5 | [12 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) 1TeslaAC Powerwall 2.0 | 2020-01-06 | 2020-01-07 | 1 | 2020-01-07 | [14 empty] | 2020-02-28 | 2020-03-06 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-12198 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8046 | Myers Corners | N |  | 3.84 | [13 empty] | NM | N | 16 Enphase Energy IQ7-60-x-US (240V) | 2020-01-03 | 2020-01-03 | 0 | 2020-01-03 | [14 empty] | 2020-08-26 | 2020-08-26 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12199 | Newburgh | Cornwall | Orange | 12518 | G | 4041 | Union Ave | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600A-US (240V) | 2020-01-02 | 2020-01-03 | 1 | 2020-01-03 | [14 empty] | 2020-06-29 | 2020-06-29 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12200 | Newburgh | Cornwall | Orange | 12518 | G | 4041 | Union Ave | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE 10000A-US (240V) | 2020-01-02 | 2020-01-03 | 1 | 2020-01-03 | [14 empty] | 2020-06-30 | 2020-06-30 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12203 | Newburgh | Plattekill | Ulster | 12568 | G | 5041 | East Walden | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE11400H-US (240V) | 2020-02-06 | 2020-02-07 | 1 | 2020-02-07 | [14 empty] | 2020-06-26 | 2020-06-26 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12204 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6043 | Spackenkill | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000 (240V) | 2020-02-06 | 2020-02-07 | 1 | 2020-02-07 | [14 empty] | 2020-06-29 | 2020-06-29 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12201 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6011 | Sand Dock | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000 (240V) | 2020-02-06 | 2020-02-07 | 1 | 2020-02-07 | [14 empty] | 2020-06-29 | 2020-06-29 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12202 | Newburgh | New Windsor | Orange | 12553 | G | 4043 | Union Ave | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE 11400A-US (240V) | 2020-02-06 | 2020-02-07 | 1 | 2020-02-07 | [14 empty] | 2020-06-29 | 2020-06-29 |  | Y
Central Hudson |  | New York State Solar Farm | CH-12206 | Poughkeepsie | Millerton | Dutchess | 12546 | G | 7081 | Millerton | N |  | 9.772 | [13 empty] | NM | N | 28 SunPower SPR-A400-G-AC (240V) | 2020-01-02 | 2020-01-03 | 1 | 2020-01-03 | [14 empty] | 2020-02-03 | 2020-02-04 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12205 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6065 | Inwood Ave | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600A-US (240V) | 2020-02-06 | 2020-02-07 | 1 | 2020-02-07 | [14 empty] | 2020-06-29 | 2020-06-29 |  | Y
Central Hudson |  | Highland Gardens LLC | CH-12211 | Newburgh | Newburgh | Orange | 12550 | G | 4024 | Coldenham | N |  | 499.9 | [13 empty] | CDG | Y | 4 SolarEdge Technologies SE100KUS (480V) [SI1] 3 SolarEdge Technologies SE33.3KUS (480V) | 2020-02-24 | 2020-03-06 | 9 | 2020-03-06 | 2020-03-06 | 2020-03-25 | 13 | 2020-04-27 | 2020-05-19 | 2020-08-13 | 60 | 17000 | 78105 |  | 2020-12-23 | 2021-06-21 | 2021-06-21 |  |  |  |  | N | Y
Central Hudson |  | Infinity Solar Systems | CH-12208 | Newburgh | Campbell Hall | Orange | 10916 | G | 5052 | Maybrook | N |  | 7.44 | [13 empty] | NM | N | 31 Enphase Energy IQ7-60-x-US (240V) | 2020-01-03 | 2020-01-03 | 0 | 2020-01-03 | [14 empty] | 2020-02-24 | 2020-03-02 |  | Y
Central Hudson |  | Solar Generation | CH-12207 | Kingston | Woodstock | Ulster | 12498 | G | 3012 | Woodstock | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2020-01-03 | 2020-01-03 | 0 | 2020-01-03 | [14 empty] | 2020-03-18 | 2020-03-20 |  | Y
Central Hudson |  | Seed Solar | CH-12209 | Kingston | Saugerties | Ulster | 12477 | G | 3003 | Saugerties | N |  | 15.2 | [13 empty] | NM | N | 2 SolarEdge Technologies SE7600H-US (240V) | 2020-01-08 | 2020-01-08 | 0 | 2020-01-08 | [14 empty] | 2020-01-22 | 2020-01-27 |  | Y
Central Hudson |  | Kasselman Solar | CH-12210 | Newburgh | Wallkill | Ulster | 12589 | G | 5043 | East Walden | N |  | 13 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3000H-US (240V) 1 SolarEdge Technologies SE10000H-US (240V) | 2020-01-03 | 2020-01-06 | 1 | 2020-01-06 | [14 empty] | 2020-02-19 | 2020-02-21 |  | Y
Central Hudson |  | New York State Solar Farm | CH-12212 | Catskill | Athens | Greene | 12015 | G | 1074 | Coxsackie | N |  | 6.98 | [13 empty] | NM | N | 20 SunPower SPR-A400-G-AC (240V) | 2020-01-06 | 2020-01-06 | 0 | 2020-01-06 | [14 empty] | 2020-02-10 | 2020-02-18 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12214 | Fishkill | Beacon | Dutchess | 12508 | G | 8015 | Forgebrook | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000 (240V) | 2020-01-07 | 2020-01-07 | 0 | 2020-01-07 | [14 empty] | 2020-01-24 | 2020-01-27 |  | Y
Central Hudson |  | Solar Generation | CH-12215 | Kingston | Lk Hill | Ulster | 12448 | G | 3012 | Woodstock | N |  | 7.7 | [13 empty] | NM | N | 1 SMA America SB7700TL-US-22 (240V) | 2020-01-06 | 2020-01-07 | 1 | 2020-01-07 | [14 empty] | 2020-03-02 | 2020-03-06 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-12216 | Newburgh | New Windsor |  | 12553 | G | 4052 | Union Ave | N |  | 4.6 | [13 empty] | NM | N | 1 Ningbo Ginlong Technologies Solis-1P4.6K-4G-US (240V) | 2020-01-06 | 2020-01-07 | 1 | 2020-01-07 | [17 empty] | W
Central Hudson |  | Suncommon | CH-12213 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7053 | Rhinebeck | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2020-01-06 | 2020-01-07 | 1 | 2020-01-07 | [14 empty] | 2020-10-06 | 2020-10-06 |  | Y
Central Hudson |  | Solar Generation | CH-12219 | Kingston | W Hurley | Ulster | 12491 | G | 2094 | Hurley Ave | N |  | 10 | [13 empty] | NM | N | 2 SMA America SB5000US (240V) | 2020-01-07 | 2020-01-07 | 0 | 2020-01-07 | [14 empty] | 2020-04-14 | 2020-04-21 |  | Y
Central Hudson |  | Sunrun Inc | CH-12218 | Newburgh | Newburgh | Orange | 12550 | G | 4015 | West Balmville | N | CH-12218 | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000H-US (240V) | 2020-01-07 | 2020-01-07 | 0 | 2020-01-07 | [14 empty] | 2020-02-20 | 2020-02-26 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12217 | Kingston | Hurley | Ulster | 12443 | G | 2094 | Hurley Ave | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE 11400A-US (240V) | 2020-01-07 | 2020-01-07 | 0 | 2020-01-07 | [14 empty] | 2020-01-16 | 2020-01-16 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12220 | Newburgh | Newburgh | Orange | 12550 | G | 4051 | Union Ave | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600 (240V) | 2020-01-08 | 2020-01-08 | 0 | 2020-01-08 | [14 empty] | 2020-01-21 | 2020-02-04 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-12222 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8052 | North Chelsea | N |  | 13.44 | [13 empty] | NM | N | 1 Delta Electronics M4-TL-US (240V) [SI1] 1 Delta Electronics M10-TL-US (240V) [SI1] | 2020-01-08 | 2020-01-09 | 1 | 2020-01-09 | [14 empty] | 2020-02-20 | 2020-02-27 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-12221 | Newburgh | New Windsor |  | 12553 | G | 4094 | Bethlehem Rd | N |  | 5.04 | [13 empty] | NM | N | 21 Enphase Energy IQ7-60-x-US (240V) | 2020-01-08 | 2020-01-09 | 1 | 2020-01-09 | [17 empty] | W
Central Hudson |  | Sunrun Inc | CH-12223 | Kingston | Kingston | Ulster | 12401 | G | 1021 | East Kingston | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2020-01-09 | 2020-01-10 | 1 | 2020-01-10 | [14 empty] | 2020-05-04 | 2020-05-04 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-12224 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6095 | Manchester | N |  | 2.88 | [13 empty] | NM | N | 12 Enphase Energy IQ7-60-x-US (240V) | 2020-01-10 | 2020-01-13 | 1 | 2020-01-13 | [14 empty] | 2020-05-15 | 2020-05-15 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-12225 | Newburgh | Newburgh | Orange | 12550 | G | 4023 | Coldenham | N | CH-12225 | 6.48 | [13 empty] | NM | N | 27 Enphase Energy IQ7-60-x-US (240V) | 2020-01-13 | 2020-01-13 | 0 | 2020-01-13 | [14 empty] | 2020-02-25 | 2020-03-03 |  | Y
Central Hudson |  | ConEd Solutions | CH-12229 | Kingston | Saugerties | Ulster | 12477 | G | 3005 | Saugerties | N |  | 168 | [13 empty] | NM | N | 6 Yaskawa Solectria Solar PVI 28TL-480 | 2020-01-31 | 2020-02-14 | 10 | 2020-02-14 | 2020-02-14 | 2020-03-05 | 13 | 2020-03-30 | 2020-04-30 | 2020-07-27 | 60 | [9 empty] | 2025-08-21 | W
Central Hudson |  | Empire Solar Solutions | CH-12228 | Catskill | Catskill | Greene | 12414 | G | 2005 | North Catskill | N |  | 4.93 | [13 empty] | NM | N | 17 Enphase Energy IQ7PLUS-72-x-US-& (240V) [SI1] | 2020-01-13 | 2020-01-14 | 1 | 2020-01-14 | [14 empty] | 2020-05-11 | 2020-05-11 |  | Y
Central Hudson |  | Solar Generation | CH-12226 | Kingston | Mt Tremper | Ulster | 12457 | G | 3012 | Woodstock | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2020-01-13 | 2020-01-13 | 0 | 2020-01-13 | [14 empty] | 2020-07-31 | 2020-07-31 |  | Y
Central Hudson |  | New York State Solar Farm | CH-12230 | Kingston | Kingston | Ulster | 12401 | G | 111 | South Wall St | N |  | 5.67 | [13 empty] | NM | N | 18 SunPower SPR-E19-320-E-AC (240V) | 2020-01-13 | 2020-01-14 | 1 | 2020-01-14 | [14 empty] | 2020-02-04 | 2020-02-04 |  | Y
Central Hudson |  | Solar Generation | CH-12227 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7061 | Milan | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2020-01-13 | 2020-01-13 | 0 | 2020-01-13 | [14 empty] | 2020-03-13 | 2020-03-18 |  | Y
Central Hudson |  | Clove Solar, LLC | CH-12091 | Poughkeepsie | Union Vale |  | 12540 | G | 6055 | Todd Hill | N |  | 5000 | 5000 | [12 empty] | CDG | Y | 1Power ElectronicsFS2125K1Power ElectronicsFS3190K1Power ElectronicsFS2125K - FS3190K | 2020-03-03 | 2020-03-16 | 9 | 2020-03-16 | 2020-03-16 | 2020-04-06 | 15 | 2020-05-19 | 2020-06-01 | 2020-08-25 | 60 | 19518.47 | 4748252.5 | [7 empty] | 2021-03-15 | W
Central Hudson |  | Gertrude Solar, LLC | CH-12092 | Newburgh | New Paltz |  | 12561 | G | 5024 | Ohioville | N |  | 5000 | 5000 | [12 empty] | CDG | Y | 1Power ElectronicsFS2125K1Power ElectronicsFS3190K2Power ElectronicsFS2125K - FS3190K | 2020-03-03 | 2020-03-16 | 9 | 2020-03-16 | 2020-03-16 | 2020-04-03 | 14 | 2020-05-19 | 2020-06-01 | 2020-08-25 | 60 | 18894.17 | 638805 | [7 empty] | 2021-03-29 | W
Central Hudson |  | AEC Solar Energy Corp. | CH-12232 | Newburgh | New Paltz | Ulster | 12561 | G | 5023 | Ohioville | N |  | 5.985 | [13 empty] | NM | N | 19 SunPower SPR-E20-327-E-AC (240V) [SI1] | 2020-01-16 | 2020-01-16 | 0 | 2020-01-16 | [14 empty] | 2020-03-04 | 2020-03-11 |  | Y
Central Hudson |  | Conscious Energy Inc | CH-12233 | Kingston | Kingston | Ulster | 12401 | G | 2094 | Hurley Ave | N |  | 12 | [13 empty] | NM | N | 2 SMA America SB6000TL-US-12 (240V) | 2020-01-22 | 2020-01-28 | 4 | 2020-01-28 | [8 empty] | 350 | 350 |  | 2020-02-05 | 2020-02-05 | 2020-03-02 | 2020-05-01 | 2020-05-01 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-12234 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6092 | Manchester | N |  | 4.08 | [13 empty] | NM | N | 17 Enphase Energy IQ7-60-x-US (240V) | 2020-01-15 | 2020-01-16 | 1 | 2020-01-16 | [14 empty] | 2020-07-06 | 2020-07-06 |  | Y
Central Hudson |  | PlugPV LLC | CH-12235 | Catskill | Coxsackie | Greene | 12051 | G | 1076 | Coxsackie | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000H-US (240V) | 2020-01-15 | 2020-01-16 | 1 | 2020-01-16 | [14 empty] | 2020-02-25 | 2020-03-02 |  | Y
Central Hudson |  | Kasselman Solar | CH-12238 | Catskill | Coxsackie | Greene | 12051 | G | 1076 | Coxsackie | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2020-01-16 | 2020-01-17 | 1 | 2020-01-17 | [14 empty] | 2020-02-03 | 2020-02-10 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-12236 | Newburgh | New Windsor | Orange | 12553 | G | 4044 | Union Ave | N |  | 7.54 | [13 empty] | NM | N | 26 Enphase Energy IQ7PLUS-72-x-US (240V) | 2020-01-16 | 2020-01-16 | 0 | 2020-01-16 | [14 empty] | 2020-06-30 | 2020-06-30 |  | Y
Central Hudson |  | Suncommon | CH-12237 | Poughkeepsie | Pine Plns | Dutchess | 12567 | G | 7091 | Pulvers Corners | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2020-01-16 | 2020-01-16 | 0 | 2020-01-16 | [14 empty] | 2020-03-24 | 2020-03-26 |  | Y
Central Hudson |  | Integrity Solar Solutions | CH-12239 | Newburgh | Newburgh | Orange | 12550 | G | 4014 | West Balmville | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2020-01-17 | 2020-01-17 | 0 | 2020-01-17 | [14 empty] | 2020-02-14 | 2020-02-14 |  | Y
Central Hudson |  | PlugPV LLC | CH-12242 | Newburgh | Montgomery | Orange | 12549 | G | 5073 | Montgomery | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2020-01-21 | 2020-01-27 | 4 | 2020-01-27 | [14 empty] | 2020-03-03 | 2020-03-10 |  | Y
Central Hudson |  | AEC Solar Energy Corp. | CH-12240 | Catskill | Jewett | Greene | 12444 | E | 2389 | Vinegar Hill | N |  | 10.08 | [13 empty] | NM | N | 32 SunPower SPR-E20-327-E-AC (240V) | 2020-01-20 | 2020-01-20 | 0 | 2020-01-20 | [8 empty] | 350 | 350 |  | 2020-02-18 | 2020-02-18 | 2020-07-09 | 2020-08-26 | 2020-08-26 |  | Y
Central Hudson |  | Solar Spectrum LLC | CH-12241 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8071 | Shenandoah | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2020-01-28 | 2020-01-28 | 0 | 2020-01-28 | [14 empty] | 2020-10-07 | 2020-10-07 |  | Y
Central Hudson |  | Sunrun Installation Service, Inc. | CH-12247 | Kingston | New Paltz | Ulster | 12561 | G | 1023 | East Kingston | N |  | 8.64 | [13 empty] | NM | N | 1 Delta Electronics M5-TL-US (240V) [SI1] 1 Delta Electronics M4-TL-US (240V) [SI1] | 2020-02-12 | 2020-02-14 | 2 | 2020-02-14 | [14 empty] | 2020-04-08 | 2020-04-08 |  | Y
Central Hudson |  | Distributed Asset Solutions, LLC | CH-12244 | Newburgh | Wallkill | Ulster | 12589 | G | 5042 | East Walden | N |  | 4995 | [13 empty] | CDG | Y | 27 Ginlong Technologies Solis-185K-EHV-5G-US-PLUS (600V) [SI1] SOLIS185K-EHV-5G-US-PLUS | 2020-04-23 | 2020-05-07 | 10 | 2020-05-07 | 2020-05-07 | 2020-05-29 | 15 | 2020-06-30 | 2020-08-28 | 2020-11-23 | 60 | 15000 | 323955 |  | 2021-04-06 | 2021-09-24 | 2021-09-24 | 2025-08-29 |  |  |  | N | Y
Central Hudson |  | Sunrun Inc | CH-12246 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6094 | Manchester | Y |  | 3.8 | 3.8 | [12 empty] | NM | N | 1 SolarEdge Technologies SE3800 (240V) 1SolarEdge TechnologiesSE3800H-US | 2020-02-12 | 2020-02-12 | 0 | 2020-02-12 | [14 empty] | 2020-03-10 | 2020-03-18 |  | Y
Central Hudson |  | Trinity Solar | CH-12245 | Newburgh | Campbell Hall | Orange | 10916 | G | 5052 | Maybrook | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2020-01-21 | 2020-01-27 | 4 | 2020-01-27 | [14 empty] | 2020-03-10 | 2020-03-17 |  | Y
Central Hudson |  | Lighthouse Solar | CH-12243 | Kingston | Kingston | Ulster | 12401 | G | 2094 | Hurley Ave | N |  | 19.43 | [13 empty] | NM | N | 67 Enphase Energy IQ7PLUS-72-x-US (240V) | 2020-02-04 | 2020-02-05 | 1 | 2020-02-05 | [14 empty] | 2020-03-17 | 2020-03-20 |  | Y | Y
Central Hudson |  | Empire Solar Solutions | CH-12248 | Kingston | Kerhonkson | Ulster | 12446 | G | 3082 | Kerhonkson | N |  | 12 | [13 empty] | NM | N | 2 SolarEdge Technologies SE6000 (240V) | 2020-02-04 | 2020-02-05 | 1 | 2020-02-05 | [14 empty] | 2020-02-10 | 2020-02-10 |  | Y
Central Hudson |  | New York State Solar Farm | CH-12251 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6043 | Spackenkill | N |  | 8.82 | [13 empty] | NM | N | 28 SunPower SPR-E19-320-E-AC (240V) | 2020-01-23 | 2020-01-28 | 3 | 2020-01-28 | [14 empty] | 2020-06-29 | 2020-06-29 |  | Y
Central Hudson |  | Sunrun Installation Service, Inc. | CH-12250 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6065 | Inwood Ave | N |  | 5.52 | [13 empty] | NM | N | 23 Enphase Energy IQ7-60-x-US (240V) | 2020-01-23 | 2020-01-28 | 3 | 2020-01-28 | [14 empty] | 2020-02-06 | 2020-02-12 |  | Y
Central Hudson |  | New York State Solar Farm | CH-12249 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7053 | Rhinebeck | N |  | 6.98 | [13 empty] | NM | N | 20 SunPower SPR-A400-G-AC (240V) | 2020-01-23 | 2020-01-28 | 3 | 2020-01-28 | [14 empty] | 2020-03-16 | 2020-03-20 |  | Y
Central Hudson |  | Sunrun Inc | CH-12252 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6051 | Todd Hill | N |  | 11 | [13 empty] | NM | N | 1 Delta Electronics M6-TL-US (240V) [SI1] 1 Delta Electronics M5-TL-US (208V) [SI1] | 2020-01-24 | 2020-01-28 | 2 | 2020-01-28 | [14 empty] | 2020-02-17 | 2020-02-18 |  | Y
Central Hudson |  | PlugPV LLC | CH-12253 | Newburgh | Milton | Ulster | 12547 | G | 5002 | Marlboro | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2020-01-24 | 2020-01-28 | 2 | 2020-01-28 | [14 empty] | 2020-03-17 | 2020-03-20 |  | Y
Central Hudson |  | Suncommon | CH-12254 | Poughkeepsie | Stanfordvl | Dutchess | 12581 | G | 7072 | Stanfordville | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2020-01-27 | 2020-01-28 | 1 | 2020-01-28 | [14 empty] | 2020-03-05 | 2020-03-12 |  | Y
Central Hudson |  | PlugPV, LLC | CH-12256 | Kingston | Port Ewen | Ulster | 12466 | G | 1012 | Boulevard | N |  | 28.8 | [13 empty] | RC | Y | 2 SolarEdge Technologies SE14.4KUS (208V) | 2020-02-07 | 2020-02-14 | 5 | 2020-02-14 | [14 empty] | 2020-04-07 | 2020-04-07 |  | Y | Y
Central Hudson |  | PlugPV LLC | CH-12255 | Newburgh | Newburgh | Orange | 12550 | G | 5041 | East Walden | N | CH-12255 | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2020-01-28 | 2020-01-28 | 0 | 2020-01-28 | [14 empty] | 2020-07-31 | 2020-07-31 |  | Y
Central Hudson |  | Kasselman Solar | CH-12257 | Catskill | Westerlo | Albany | 12193 | G | 1092 | Westerlo | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000H-US (240V) | 2020-01-28 | 2020-01-28 | 0 | 2020-01-28 | [14 empty] | 2020-12-11 | 2020-12-11 |  | Y
Central Hudson |  | Sunrun Inc | CH-12262 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 8 | [13 empty] | NM | N | 1 Delta Electronics M8-TL-US (240V) [SI1] | 2020-01-29 | 2020-02-10 | 8 | 2020-02-10 | [14 empty] | 2020-03-25 | 2020-03-25 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-12261 | Newburgh | Marlboro | Ulster | 12542 | G | 5004 | Marlboro | N |  | 5.76 | [13 empty] | NM | N | 24 Enphase Energy IQ7-60-x-US (240V) | 2020-01-29 | 2020-01-29 | 0 | 2020-01-29 | [14 empty] | 2020-03-03 | 2020-03-10 |  | Y
Central Hudson |  | PlugPV LLC | CH-12264 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6011 | Sand Dock | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2020-03-18 | 2020-03-25 | 5 | 2020-03-25 | [14 empty] | 2020-07-21 | 2020-07-21 |  | Y
Central Hudson |  | PlugPV LLC | CH-12263 | Newburgh | Wallkill | Ulster | 12589 | G | 4011 | West Balmville | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2020-03-09 | 2020-03-20 | 9 | 2020-03-20 | [14 empty] | 2020-03-30 | 2020-04-01 |  | Y
Central Hudson |  | Tri-State Solar Services | CH-12265 | Newburgh | Montgomery | Orange | 12549 | G | 5073 | Montgomery | N |  | 11.6 | [13 empty] | NM | N | 40 Enphase Energy IQ7PLUS-72-x-US (240V) [SI1] | 2020-01-30 | 2020-02-03 | 2 | 2020-02-03 | [14 empty] | 2020-09-01 | 2020-09-01 |  | Y
Central Hudson |  | Natural Energy Solutions LLC | CH-12266 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7051 | Rhinebeck | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2020-01-30 | 2020-02-05 | 4 | 2020-02-05 | [14 empty] | 2020-10-23 | 2020-10-23 |  | Y
Central Hudson |  | Kasselman Solar | CH-12267 | Catskill | Coxsackie | Greene | 12051 | G | 1071 | Coxsackie | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2020-01-31 | 2020-02-05 | 3 | 2020-02-05 | [14 empty] | 2020-03-09 | 2020-03-16 |  | Y
Central Hudson |  | Solar Generation | CH-12269 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7062 | Milan | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2020-02-05 | 2020-02-05 | 0 | 2020-02-05 | [14 empty] | 2020-07-09 | 2020-07-09 |  | Y
Central Hudson |  | PlugPV LLC | CH-12268 | Newburgh | Wallkill | Ulster | 12589 | G | 5043 | East Walden | N |  | 19 | [13 empty] | NM | N | 1 SolarEdge Technologies SE11400H-US (240V) 1 SolarEdge Technologies SE7600H-US (240V) | 2020-02-03 | 2020-02-05 | 2 | 2020-02-05 | [8 empty] | 350 | 350 |  | 2020-02-07 | 2020-02-07 | 2020-03-11 | 2020-03-27 | 2020-03-27 |  | Y
Central Hudson |  | Solar Generation | CH-12271 | Kingston | Woodstock |  | 12498 | G | 3013 | Woodstock | N |  | 25 | [13 empty] | NM | N | 2 SolarEdge Technologies SE10000H-US (240V) 1 SolarEdge Technologies SE5000H-US (240V) | 2020-02-05 | 2020-02-05 | 0 | 2020-02-05 | [17 empty] | W
Central Hudson |  | New York State Solar Farm | CH-12270 | Kingston | Accord | Ulster | 12404 | G | 3024 | High Falls | N |  | 9.135 | [13 empty] | NM | N | 29 SunPower SPR-E19-320-E-AC (240V) | 2020-02-03 | 2020-02-05 | 2 | 2020-02-05 | [14 empty] | 2020-02-26 | 2020-03-04 |  | Y
Central Hudson |  | Ameresco | CH-12275 | Fishkill | Fishkill | Dutchess | 12524 | G | 8094 | Fishkill Plains | N |  | 266.6 | [13 empty] | NM | Y | 2 SolarEdge Technologies SE100KUS (480V) 1 SolarEdge Technologies SE66.6KUS (480V) | 2020-03-05 | 2020-03-19 | 10 | 2020-03-19 | 2020-04-22 | 2020-05-13 | 15 | [5 empty] | 36400 | 38379.73 |  | 2020-08-07 | 2020-08-07 | 2023-04-10 | 2025-02-11 | 2025-02-11 | 2025-05-02 | Y | Y
Central Hudson |  | Ameresco | CH-12279 | Fishkill | Wappingers Falls | Dutchess | 12590 | G | 8052 | North Chelsea | N |  | 66.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE66.6KUS (480V) | 2020-04-22 | 2020-05-06 | 10 | 2020-05-06 | 2020-05-06 | 2020-05-28 | 15 | [11 empty] | 2022-03-15 | 2022-03-15 |  | Y
Central Hudson |  | Ameresco | CH-12278 | Fishkill | Wappingers Falls | Dutchess | 12590 | G | 8044 | Myers Corners | N |  | 499.9 | [13 empty] | NM | N | 4 SolarEdge Technologies SE100KUS (480V) 1 SolarEdge Technologies SE66.6KUS (480V) 1 SolarEdge Technologies SE33.3KUS (480V) [SI1] | 2020-03-05 | 2020-03-19 | 10 | 2020-03-19 | 2020-04-22 | 2020-05-13 | 15 | [11 empty] | 2024-06-12 | 2024-06-12 |  | Y
Central Hudson |  | Ameresco | CH-12276 | Fishkill | Wappingers Falls | Dutchess | 12533 | G | 8091 | Fishkill Plains | N |  | 333.3 | [13 empty] | NM | N | 3 SolarEdge Technologies SE100KUS (480V) 1 SolarEdge Technologies SE33.3KUS (480V) | 2020-04-01 | 2020-04-16 | 10 | 2020-04-16 | 2020-04-16 | 2020-05-07 | 15 | [11 empty] | 2023-04-26 | 2023-04-26 |  | Y
Central Hudson |  | Ameresco | CH-12277 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6046 | Spackenkill | N |  | 66.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE66.6KUS (480V) | 2020-04-22 | 2020-05-06 | 10 | 2020-05-06 | 2020-05-06 | 2020-05-28 | 15 | [11 empty] | 2022-02-11 | 2022-02-23 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12272 | Newburgh | New Paltz | Ulster | 12561 | G | 5021 | Ohioville | N |  | 13.34 | [13 empty] | NM | N | 46 Enphase Energy IQ7PLUS-72-x-US-& (240V) [SI1] | 2020-02-04 | 2020-02-05 | 1 | 2020-02-05 | [8 empty] | 350 | 350 |  | 2020-02-07 | 2020-02-07 | 2020-03-11 | 2020-04-06 | 2020-04-06 |  | Y
Central Hudson |  | PlugPV, LLC | CH-12273 | Newburgh | Newburgh | Orange | 12550 | G | 4014 | West Balmville | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000H-US (240V) | 2020-02-04 | 2020-02-05 | 1 | 2020-02-05 | [14 empty] | 2020-03-30 | 2020-04-02 |  | Y
Central Hudson |  | Solar Generation | CH-12274 | Kingston | Kerhonkson | Ulster | 12446 | G | 3082 | Kerhonkson | N |  | 8.7 | [13 empty] | NM | N | 30 Enphase Energy IQ7PLUS-72-x-US (240V) | 2020-02-04 | 2020-02-05 | 1 | 2020-02-05 | [14 empty] | 2020-10-19 | 2020-10-19 |  | Y
Central Hudson |  | PlugPV LLC | CH-12280 | Poughkeepsie | Poughkeepsie |  | 12601 | G | 6011 | Sand Dock | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000H-US (240V) | 2020-02-06 | 2020-02-06 | 0 | 2020-02-06 | [17 empty] | W
Central Hudson |  | Solar Generation | CH-12281 | Kingston | Cottekill | Ulster | 12419 | G | 3021 | High Falls | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2020-02-06 | 2020-02-21 | 10 | 2020-02-21 | [14 empty] | 2020-07-30 | 2020-07-30 |  | Y
Central Hudson |  | Kasselman Solar | CH-12282 | Catskill | Ravena | Albany | 12143 | G | 1081 | New Baltimore | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2020-02-06 | 2020-02-06 | 0 | 2020-02-06 | [14 empty] | 2020-03-11 | 2020-03-17 |  | Y
Central Hudson |  | Suncommon | CH-12185 | Poughkeepsie | Amenia | Dutchess | 12501 | G | 7095 | Smithfield | N |  | 57 | [13 empty] | NM | Y | 5 SolarEdge Technologies SE11400H-US (240V) | 2020-02-07 | 2020-02-24 | 10 | 2020-02-24 | 2020-02-24 | 2020-03-16 | 15 | [11 empty] | 2020-06-17 | 2020-06-24 |  | Y | Y
Central Hudson |  | Kasselman Solar | CH-12283 | Poughkeepsie | Millerton | Dutchess | 12546 | G | 7081 | Millerton | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000H-US (240V) | 2020-02-07 | 2020-02-10 | 1 | 2020-02-10 | [14 empty] | 2020-03-02 | 2020-03-06 |  | Y
Central Hudson |  | Suncommon | CH-12284 | Kingston | Hurley | Ulster | 12443 | G | 2094 | Hurley Ave | N |  | 15.2 | [13 empty] | NM | N | 2 SolarEdge Technologies SE7600H-US (240V) | 2020-02-07 | 2020-02-10 | 1 | 2020-02-10 | [8 empty] | 350 | 350 |  | 2020-02-20 | 2020-02-20 | 2020-03-02 | 2020-03-20 | 2020-04-01 |  | Y
Central Hudson |  | New York State Solar Farm | CH-12285 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7061 | Milan | N | CH-12285 | 8.82 | [13 empty] | NM | N | 28 SunPower SPR-E20-327-E-AC (240V) | 2020-02-10 | 2020-02-10 | 0 | 2020-02-10 | [14 empty] | 2020-04-01 | 2020-04-03 |  | Y
Central Hudson |  | Tesla Energy | CH-12286 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8096 | Fishkill Plains | Y |  | 11.4 | 20 | [12 empty] | NM | N | 1 SolarEdge Technologies SE11400H-US (240V) 4TeslaAC Powerwall 2.0 | 2020-02-18 | 2020-02-18 | 0 | 2020-02-18 | [14 empty] | 2020-09-09 | 2020-09-09 |  | Y
Central Hudson |  | Solar Image, LLC | CH-12287 | Fishkill | Beacon | Dutchess | 12508 | G | 8018 | Forgebrook | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) [SI1] | 2020-02-10 | 2020-02-19 | 6 | 2020-02-19 | [14 empty] | 2020-03-16 | 2020-03-20 |  | Y
Central Hudson |  | Solar Image, LLC | CH-12288 | Fishkill | Beacon | Dutchess | 12508 | G | 8017 | Forgebrook | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2020-02-10 | 2020-02-19 | 6 | 2020-02-19 | [8 empty] | 350 | 350 |  | 2020-03-12 | 2020-03-12 | 2020-06-18 | 2020-08-10 | 2020-08-10 |  | Y
Central Hudson |  | Solar Generation | CH-12290 | Kingston | Shokan | Ulster | 12481 | G | 3011 | Woodstock | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2020-02-11 | 2020-02-12 | 1 | 2020-02-12 | [14 empty] | 2020-03-27 | 2020-03-27 |  | Y
Central Hudson |  | Solar Image, LLC | CH-12289 | Newburgh | Newburgh | Orange | 12550 | G | 4011 | West Balmville | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2020-02-11 | 2020-02-13 | 2 | 2020-02-13 | [14 empty] | 2020-05-06 | 2020-05-06 |  | Y
Central Hudson |  | Apex Solar Power | CH-12291 | Kingston | Saugerties | Ulster | 12477 | G | 2016 | Lincoln Park | N | CH-12291 | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE11400H-US (240V) | 2020-02-11 | 2020-02-12 | 1 | 2020-02-12 | [14 empty] | 2020-03-20 | 2020-03-20 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-12292 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 4.32 | [13 empty] | NM | N | 18 Enphase Energy IQ7-60-x-US (240V) | 2020-02-12 | 2020-02-12 | 0 | 2020-02-12 | [14 empty] | 2020-06-22 | 2020-06-22 |  | Y
Central Hudson |  | Suncommon | CH-12293 | Kingston | Boicevl | Ulster | 12412 | G | 3011 | Woodstock | Y |  | 10 | 10 | [12 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) 2TeslaPowerwall 2 | 2020-02-14 | 2020-02-14 | 0 | 2020-02-14 | [14 empty] | 2020-03-24 | 2020-03-26 |  | Y
Central Hudson |  | PlugPV LLC | CH-12295 | Kingston | Saugerties | Ulster | 12477 | G | 2016 | Lincoln Park | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2020-02-13 | 2020-02-14 | 1 | 2020-02-14 | [14 empty] | 2020-03-12 | 2020-03-18 |  | Y
Central Hudson |  | Tesla Energy Operations, Inc. | CH-12297 | Fishkill | Cold Spg | Putnam | 10516 | G | 8063 | Merritt Park | Y |  | 11.4 | 15 | [12 empty] | NM | N | 1 SolarEdge Technologies SE11400A-US (240V) [SI1] 3TeslaAC Powerwall 2.0 | 2020-02-13 | 2020-02-14 | 1 | 2020-02-14 | [17 empty] | W
Central Hudson |  | Empire Solar Solutions | CH-12296 | Catskill | Freehold | Greene | 12431 | G | 2071 | Freehold | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE 10000A-US (240V) | 2020-02-13 | 2020-02-14 | 1 | 2020-02-14 | [14 empty] | 2020-03-11 | 2020-03-17 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-12298 | Newburgh | Maybrook | Orange | 12543 | G | 5052 | Maybrook | N |  | 2.64 | [13 empty] | NM | N | 11 Enphase Energy IQ7-60-x-US (240V) | 2020-02-14 | 2020-02-14 | 0 | 2020-02-14 | [14 empty] | 2020-06-26 | 2020-06-26 |  | Y
Central Hudson |  | Watershed Solar Development, LLC | CH-12299 | Catskill | Catskill |  | 12414 | G | 2001 | North Catskill | N |  | 5000 | [13 empty] | CDG | Y | 1Power ElectronicsHEMK FS3000K1Power ElectronicsHEMK FS2000K | 2020-03-09 | 2020-03-23 | 10 | 2020-03-23 | 2020-03-23 | 2020-04-13 | 14 | 2020-05-07 | 2020-06-12 | 2020-09-08 | 60 | 20148.79 | 5825465 | [7 empty] | 2021-04-14 | W
Central Hudson |  | New York State Solar Farm | CH-12300 | Kingston | Stone Ridge | Ulster | 12484 | G | 3023 | High Falls | N |  | 16 | [13 empty] | NM | N | 50 SunPower SPR-X22-360-E-AC (240V) | 2020-02-19 | 2020-02-19 | 0 | 2020-02-19 | [14 empty] | 2020-03-20 | 2020-03-20 |  | Y
Central Hudson |  | PlugPV LLC | CH-12304 | Newburgh | Newburgh | Orange | 12550 | G | 5004 | Marlboro | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2020-02-18 | 2020-02-19 | 1 | 2020-02-19 | [14 empty] | 2020-06-08 | 2020-06-08 |  | Y
Central Hudson |  | PlugPV LLC | CH-12301 | Newburgh | New Windsor | Orange | 12553 | G | 4094 | Bethlehem Rd | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE11400H-US (240V) | 2020-02-18 | 2020-02-18 | 0 | 2020-02-18 | [8 empty] | 350 | 350 |  | 2020-02-21 | 2020-02-21 | 2020-03-12 | 2020-03-23 | 2020-03-26 |  | Y
Central Hudson |  | PlugPV LLC | CH-12302 | Fishkill | Stormvl | Dutchess | 12582 | G | 8071 | Shenandoah | N |  | 12.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) 1 SolarEdge Technologies SE5000H-US (240V) | 2020-02-18 | 2020-02-19 | 1 | 2020-02-19 | [14 empty] | 2020-04-03 | 2020-04-03 |  | Y
Central Hudson |  | PlugPV LLC | CH-12303 | Newburgh | Marlboro | Ulster | 12542 | G | 5004 | Marlboro | N |  | 13.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) 1 SolarEdge Technologies SE6000H-US (240V) | 2020-02-18 | 2020-03-02 | 9 | 2020-03-02 | [14 empty] | 2020-03-27 | 2020-04-01 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12305 | Fishkill | Holmes | Dutchess | 12531 | G | 8071 | Shenandoah | N |  | 6.96 | [13 empty] | NM | N | 24 Enphase Energy IQ7PLUS-72-x-US (240V) | 2020-02-18 | 2020-02-19 | 1 | 2020-02-19 | [14 empty] | 2020-04-24 | 2020-04-24 |  | Y
Central Hudson |  | Sunrun Inc | CH-12311 | Fishkill | Beacon | Dutchess | 12508 | G | 8015 | Forgebrook | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2020-02-18 | 2020-02-19 | 1 | 2020-02-19 | [14 empty] | 2020-05-04 | 2020-05-04 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12312 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 6057 | Todd Hill | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000 (240V) | 2020-02-18 | 2020-03-02 | 9 | 2020-03-02 | [14 empty] | 2020-03-02 | 2020-03-06 |  | Y
Central Hudson |  | Sunrun Inc | CH-12310 | Newburgh | New Windsor | Orange | 12553 | G | 4045 | Union Ave | N |  | 9.36 | [13 empty] | NM | N | 39 Enphase Energy IQ7-60-x-US (240V) | 2020-02-18 | 2020-02-19 | 1 | 2020-02-19 | [14 empty] | 2020-08-06 | 2020-08-06 |  | Y
Central Hudson |  | PlugPv LLC | CH-12306 | Kingston | Accord | Ulster | 12404 | G | 3081 | Kerhonkson | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2020-03-05 | 2020-03-17 | 8 | 2020-03-17 | [14 empty] | 2020-06-15 | 2020-06-15 |  | Y
Central Hudson |  | Suncommon | CH-12307 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8095 | Fishkill Plains | Y | CH-02171 |  | 5 | [12 empty] | NM | N | 1TeslaPowerwall 2 | 2020-03-02 | 2020-03-16 | 10 | 2020-03-16 | [14 empty] | 2020-10-01 | 2020-10-01 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-12308 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8072 | Shenandoah | N |  | 5.22 | [13 empty] | NM | N | 18 Enphase Energy IQ7PLUS-72-x-US (240V) | 2020-02-19 | 2020-02-19 | 0 | 2020-02-19 | [14 empty] | 2020-03-11 | 2020-03-25 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-12309 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6093 | Manchester | N |  | 4.32 | [13 empty] | NM | N | 18 Enphase Energy IQ7-60-x-US (240V) | 2020-02-18 | 2020-02-19 | 1 | 2020-02-19 | [14 empty] | 2020-06-24 | 2020-06-24 |  | Y
Central Hudson |  | Sunrun Inc | CH-12319 | Kingston | Saugerties | Ulster | 12477 | G | 3002 | Saugerties | N |  | 5.52 | [13 empty] | NM | N | 23 Enphase Energy IQ7-60-x-US (240V) | 2020-03-05 | 2020-03-17 | 8 | 2020-03-17 | [14 empty] | 2020-10-19 | 2020-10-19 |  | Y
Central Hudson |  | Sunrun Inc | CH-12318 | Newburgh | New Windsor | Orange | 12553 | G | 4046 | Union Ave | N |  | 7.92 | [13 empty] | NM | N | 33 Enphase Energy IQ7-60-x-US (240V) | 2020-02-19 | 2020-03-04 | 10 | 2020-03-04 | [14 empty] | 2020-09-04 | 2020-09-04 |  | Y
Central Hudson |  | PlugPV, LLC | CH-12315 | Newburgh | Newburgh |  | 12550 | G | 5004 | Marlboro | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2020-02-19 | 2020-02-19 | 0 | 2020-02-19 | [17 empty] | W
Central Hudson |  | Infinity Solar Systems | CH-12313 | Newburgh | Newburgh | Orange | 12550 | G | 4054 | Union Ave | N |  | 5.04 | [13 empty] | NM | N | 21 Enphase Energy IQ7-60-x-US (240V) | 2020-02-19 | 2020-02-19 | 0 | 2020-02-19 | [14 empty] | 2020-07-29 | 2020-07-29 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-12314 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8072 | Shenandoah | N |  | 19.2 | [13 empty] | NM | N | 80 Enphase Energy IQ7-60-x-US (240V) | 2020-02-19 | 2020-02-19 | 0 | 2020-02-19 | [8 empty] | 350 | 350 |  | 2020-02-21 | 2020-02-21 | 2020-10-06 | 2020-10-19 | 2020-10-19 |  | Y
Central Hudson |  | 875 Broadway | CH-12317 | Fishkill | Stormvl | Dutchess | 12582 | G | 8093 | Fishkill Plains | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2020-02-19 | 2020-02-19 | 0 | 2020-02-19 | [14 empty] | 2020-06-15 | 2020-06-15 |  | Y
Central Hudson |  | PlugPV, LLC | CH-12316 | Newburgh | Milton | Ulster | 12547 | G | 5002 | Marlboro | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000H-US (240V) | 2020-02-19 | 2020-02-19 | 0 | 2020-02-19 | [8 empty] | 350 | 350 |  | 2020-02-21 | 2020-02-21 | 2020-03-11 | 2020-03-12 | 2020-03-17 |  | Y
Central Hudson |  | Suncommon | CH-12320 | Fishkill | Garrison | Putnam | 10524 | G | 8086 | Tioronda | Y | CH-12320 | 10 | 10 | [12 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) 2TeslaPowerwall 2 | 2020-03-18 | 2020-03-27 | 7 | 2020-03-27 | [14 empty] | 2020-06-15 | 2020-06-15 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12321 | Kingston | Ellenvl | Ulster | 12428 | G | 3078 | Greenfield Rd | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE 11400A-US (240V) | 2020-02-20 | 2020-03-05 | 10 | 2020-03-05 | [8 empty] | 350 | 350 |  | 2020-03-09 | 2020-03-09 | 2020-06-09 | 2020-06-26 | 2020-06-26 |  | Y
Central Hudson |  | Apex Solar Power | CH-12325 | Kingston | New Paltz | Ulster | 12561 | G | 3021 | High Falls | Y |  | 7.6 | 10 | [12 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) 2TeslaPowerwall 2 | 2020-03-19 | 2020-03-26 | 5 | 2020-03-26 | [14 empty] | 2020-10-28 | 2020-10-28 |  | Y
Central Hudson |  | Sunrun Inc | CH-12326 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8091 | Fishkill Plains | N |  | 7.68 | [13 empty] | NM | N | 2 Delta Electronics M4-TL-US (240V) [SI1] | 2020-03-23 | 2020-03-26 | 3 | 2020-03-26 | [14 empty] | 2020-04-02 | 2020-04-06 |  | Y
Central Hudson |  | PlugPV LLC | CH-12322 | Kingston | Kingston | Ulster | 12401 | G | 1022 | East Kingston | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2020-02-21 | 2020-03-06 | 10 | 2020-03-06 | [14 empty] | 2020-06-15 | 2020-06-15 |  | Y
Central Hudson |  | PlugPV LLC | CH-12324 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8092 | Fishkill Plains | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2020-02-21 | 2020-03-06 | 10 | 2020-03-06 | [14 empty] | 2020-03-27 | 2020-03-27 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12323 | Kingston | High Fls | Ulster | 12440 | G | 3024 | High Falls | N |  | 3.8 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3800A-US (240V) [SI1] | 2020-03-06 | 2020-03-18 | 8 | 2020-03-18 | [14 empty] | 2020-04-01 | 2020-04-02 |  | Y
Central Hudson |  | Apex Solar Power | CH-12328 | Newburgh | Newburgh | Orange | 12550 | G | 402 | Montgomery St | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000H-US (240V) | 2020-03-17 | 2020-03-24 | 5 | 2020-03-24 | [14 empty] | 2020-10-29 | 2020-10-29 |  | Y
Central Hudson |  | American Energy Care / AEC Solar | CH-12327 | Catskill | Coxsackie | Greene | 12051 | G | 1074 | Coxsackie | N |  | 6.3 | [13 empty] | NM | N | 20 SunPower SPR-X21-350-BLK-E-AC (240V) | 2020-02-24 | 2020-03-06 | 9 | 2020-03-06 | [14 empty] | 2020-06-19 | 2020-06-19 |  | Y
Central Hudson |  | American Energy Care / AEC Solar | CH-12330 | Catskill | Palenvl | Greene | 12463 | G | 2001 | North Catskill | N |  | 10.82 | [13 empty] | NM | N | 31 SunPower SPR-A400-G-AC (240V) | 2020-02-25 | 2020-03-10 | 10 | 2020-03-10 | [14 empty] | 2020-06-10 | 2020-06-10 |  | Y
Central Hudson |  | New York State Solar Farm | CH-12331 | Kingston | Kingston | Ulster | 12401 | G | 1013 | Boulevard | N |  | 4.725 | [13 empty] | NM | N | 15 SunPower SPR-X21-350-BLK-E-AC (240V) | 2020-02-25 | 2020-03-10 | 10 | 2020-03-10 | [14 empty] | 2020-03-17 | 2020-03-20 |  | Y
Central Hudson |  | Suncommon | CH-12329 | Kingston | Kingston | Ulster | 12401 | G | 1022 | East Kingston | N |  | 3 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3000H-US (240V) | 2020-02-25 | 2020-03-10 | 10 | 2020-03-10 | [14 empty] | 2020-03-24 | 2020-03-24 |  | Y
Central Hudson |  | PlugPV LLC | CH-12332 | Newburgh | New Windsor | Orange | 12553 | G | 4095 | Bethlehem Rd | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2020-02-26 | 2020-03-11 | 10 | 2020-03-11 | [14 empty] | 2020-06-10 | 2020-06-10 |  | Y
Central Hudson |  | PlugPV LLC | CH-12333 | Poughkeepsie | Millbrook | Dutchess | 12545 | G | 7025 | Tinkertown | N |  | 12 | [13 empty] | NM | N | 2 SolarEdge Technologies SE6000H-US (240V) | 2020-02-26 | 2020-03-11 | 10 | 2020-03-11 | [14 empty] | 2020-06-17 | 2020-06-17 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12334 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8092 | Fishkill Plains | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2020-02-26 | 2020-03-11 | 10 | 2020-03-11 | [14 empty] | 2020-03-19 | 2020-03-20 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12336 | Kingston | Kingston | Ulster | 12401 | G | 2017 | Lincoln Park | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000 (240V) | 2020-02-28 | 2020-03-12 | 9 | 2020-03-12 | [14 empty] | 2020-03-30 | 2020-03-30 |  | Y
Central Hudson |  | Kasselman Solar | CH-12335 | Catskill | Ravena | Albany | 12143 | G | 1081 | New Baltimore | N |  | 3.8 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3800H-US (240V) | 2020-02-28 | 2020-03-12 | 9 | 2020-03-12 | [14 empty] | 2020-03-12 | 2020-03-17 |  | Y
Central Hudson |  | Sky Solar Inc. | CH-12337 | Fishkill | Fishkill |  | 12524 | G | 8065 | Merritt Park | N |  | 4000 | [13 empty] | CDG | Y | 32 Sungrow Power Supply SG125HV (600V) | 2020-05-26 | 2020-06-08 | 9 | 2020-06-08 | 2020-06-08 | 2020-06-29 | 15 | [14 empty] | W
Central Hudson |  | New York State Solar Farm | CH-12338 | Poughkeepsie | Millbrook | Dutchess | 12545 | G | 7012 | Hibernia | N |  | 8.376 | [13 empty] | NM | N | 24 SunPower SPR-A415-G-AC (240V) | 2020-03-02 | 2020-03-16 | 10 | 2020-03-16 | [14 empty] | 2020-07-13 | 2020-07-13 |  | Y
Central Hudson |  | New York State Solar Farm | CH-12342 | Poughkeepsie | Staatsburg | Dutchess | 12580 | G | 7042 | Staatsburg | N |  | 18 | [13 empty] | NM | N | 3 SMA America SB6.0-1TP-US-41 (240V) [SI1] | 2020-03-02 | 2020-03-16 | 10 | 2020-03-16 | [14 empty] | 2020-07-09 | 2020-07-09 |  | Y
Central Hudson |  | Suncommon | CH-12341 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7053 | Rhinebeck | N |  | 15.2 | [13 empty] | NM | N | 2 SolarEdge Technologies SE7600H-US (240V) | 2020-03-02 | 2020-03-16 | 10 | 2020-03-16 | [8 empty] | 350 | 350 |  | 2020-06-11 | 2020-06-11 | 2020-07-01 | 2020-12-01 | 2020-12-01 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-12339 | Newburgh | Newburgh | Orange | 12550 | G | 4022 | Coldenham | N |  | 12 | [13 empty] | NM | N | 50 Enphase Energy IQ7-60-x-US (240V) | 2020-03-16 | 2020-03-24 | 6 | 2020-03-24 | [14 empty] | 2020-03-27 | 2020-03-27 |  | Y
Central Hudson |  | Solar Generation | CH-12340 | Kingston | Stone Ridge |  | 12484 | G | 3024 | High Falls | N |  | 5 | [13 empty] | NM | N | 1 SMA America SB5.0-1SP-US-40 (240V) [SI1] | 2020-03-26 | 2020-03-27 | 1 | 2020-03-27 | [17 empty] | W
Central Hudson |  | Sunrun Inc | CH-12345 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8072 | Shenandoah | N |  | 7.68 | [13 empty] | NM | N | 1 Delta Electronics M8-TL-US (240V) [SI1] | 2020-03-25 | 2020-03-27 | 2 | 2020-03-27 | [14 empty] | 2020-04-03 | 2020-04-07 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12344 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6046 | Spackenkill | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE11400H-US (240V) | 2020-03-16 | 2020-03-24 | 6 | 2020-03-24 | [14 empty] | 2020-03-26 | 2020-03-27 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12343 | Poughkeepsie | Staatsburg | Dutchess | 12580 | G | 7011 | Hibernia | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2020-03-16 | 2020-03-24 | 6 | 2020-03-24 | [14 empty] | 2020-03-30 | 2020-03-30 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-12347 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8095 | Fishkill Plains | N |  | 14.4 | [13 empty] | NM | N | 60 Enphase Energy IQ7-60-x-US (240V) | 2020-03-24 | 2020-03-27 | 3 | 2020-03-27 | [14 empty] | 2020-06-23 | 2020-06-23 |  | Y
Central Hudson |  | PlugPV LLC | CH-12346 | Poughkeepsie | Salt Point | Dutchess | 12578 | G | 7011 | Hibernia | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE11400H-US (240V) | 2020-03-04 | 2020-03-16 | 8 | 2020-03-16 | [14 empty] | 2020-03-30 | 2020-03-30 |  | Y
Central Hudson |  | Tesla Energy | CH-12348 | Catskill | Coxsackie | Greene | 12051 | G | 1071 | Coxsackie | Y |  | 3.8 | 5 | [12 empty] | NM | N | 1 SolarEdge Technologies SE3800H-US (240V) 1TeslaAC Powerwall 2.0 | 2020-03-31 | 2020-03-31 | 0 | 2020-03-31 | [14 empty] | 2020-11-04 | 2020-11-04 |  | Y
Central Hudson |  | Tesla Energy | CH-12349 | Newburgh | Modena | Ulster | 12548 | G | 5013 | Modena | Y |  | 7.68 | 10 | [12 empty] | NM | N | 1 Delta Electronics M8-TL-US (240V) [SI1] 2TeslaAC Powerwall 2.0 | 2020-03-31 | 2020-03-31 | 0 | 2020-03-31 | [17 empty] | W
Central Hudson |  | Suncommon | CH-12350 | Catskill | Coxsackie | Greene | 12051 | G | 1074 | Coxsackie | N |  | 54.24 | [13 empty] | NM | N | 2 SMA America SB6000US (240V) 1 SMA America SB4000US (240V) 32 SunPower SPR-X22-360-D-AC (240V) 4 SunPower SPR-7000m (240V) | 2020-07-23 | 2020-08-05 | 9 | 2020-08-05 | 2020-08-05 | 2020-08-25 | 14 | [11 empty] | 2020-09-29 | 2020-10-05 |  | Y
Central Hudson |  | Kasselman Solar | CH-12352 | Kingston | Kingston | Ulster | 12401 | G | 2013 | Lincoln Park | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000H-US (240V) | 2020-03-31 | 2020-03-31 | 0 | 2020-03-31 | [14 empty] | 2020-03-31 | 2020-04-03 |  | Y
Central Hudson |  | SunPower Direct (NY) | CH-12356 | Fishkill | Fishkill | Dutchess | 12524 | G | 8051 | North Chelsea | N |  | 7.329 | [13 empty] | NM | N | 21 SunPower SPR-A400-G-AC (240V) [SI1] | 2020-03-19 | 2020-03-26 | 5 | 2020-03-26 | [14 empty] | 2020-10-14 | 2020-10-14 |  | Y
Central Hudson |  | Solar Generation | CH-12351 | Kingston | Saugerties | Ulster | 12477 | G | 3003 | Saugerties | N | CH-08295 | 7.68 | [13 empty] | NM | N | 1SMA AmericaSB7700-1SP-US-40 | 2020-03-26 | 2020-03-27 | 1 | 2020-03-27 | [8 empty] | 350 | 350 |  | 2020-04-01 | 2020-04-01 | 2020-06-18 | 2020-07-09 | 2020-07-09 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12353 | Kingston | Kingston | Ulster | 12401 | G | 1024 | East Kingston | N |  | 21.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE11400H-US (240V) 1 SolarEdge Technologies SE10000H-US (240V) | 2020-03-18 | 2020-03-31 | 9 | 2020-03-31 | [8 empty] | 350 | 350 |  | 2020-04-08 | 2020-04-08 | 2020-06-25 | 2020-07-07 | 2020-07-07 |  | Y
Central Hudson |  | PlugPV LLC | CH-12355 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8094 | Fishkill Plains | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2020-03-06 | 2020-03-18 | 8 | 2020-03-18 | [14 empty] | 2020-06-15 | 2020-06-15 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12357 | Fishkill | Fishkill | Dutchess | 12524 | G | 8066 | Merritt Park | N |  | 22.8 | [13 empty] | NM | N | 2 SolarEdge Technologies SE 11400A-US (240V) | 2020-03-23 | 2020-03-26 | 3 | 2020-03-26 | [8 empty] | 350 | 350 |  | 2020-04-01 | 2020-04-01 | 2020-05-26 | 2020-06-05 | 2020-06-05 |  | Y
Central Hudson |  | Sky Solar Inc. | CH-12358 | Fishkill | Wappinger Falls |  | 12590 | G | 8092 | Fishkill Plains | N |  | 4000 | [13 empty] | CDG | Y | 32 Sungrow Power Supply SG125HV (600V) | 2020-05-26 | 2020-06-08 | 9 | 2020-06-08 | 2020-06-08 | 2020-06-26 | 14 | [14 empty] | W
Central Hudson |  | Sunrun Inc | CH-12364 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8091 | Fishkill Plains | N |  | 7.68 | [13 empty] | NM | N | 32 Enphase Energy IQ7-60-x-ACM-US (240V) | 2020-03-11 | 2020-03-23 | 8 | 2020-03-23 | [14 empty] | 2020-08-17 | 2020-08-17 |  | Y
Central Hudson |  | Tri-State Solar Services | CH-12359 | Fishkill | Cold Spg | Putnam | 10516 | G | 8063 | Merritt Park | N |  | 9.28 | [13 empty] | NM | N | 32 Enphase Energy IQ7PLUS-72-x-US (240V) [SI1] | 2020-04-24 | 2020-04-27 | 1 | 2020-04-27 | [14 empty] | 2020-07-15 | 2020-07-15 |  | Y
Central Hudson |  | PlugPV, LLC | CH-12360 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6055 | Todd Hill | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000H-US (240V) | 2020-03-11 | 2020-03-23 | 8 | 2020-03-23 | [14 empty] | 2020-06-10 | 2020-06-10 |  | Y
Central Hudson |  | Sunrun Inc | CH-12365 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8043 | Myers Corners | N |  | 7.68 | [13 empty] | NM | N | 2 Delta Electronics M4-TL-US (240V) [SI1] | 2020-03-11 | 2020-03-23 | 8 | 2020-03-23 | [14 empty] | 2020-07-14 | 2020-07-14 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12366 | Kingston | W Hurley | Ulster | 12491 | G | 3013 | Woodstock | N |  | 3.8 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3800H-US (240V) | 2020-03-23 | 2020-03-26 | 3 | 2020-03-26 | [14 empty] | 2020-04-03 | 2020-04-03 |  | Y
Central Hudson |  | Ameresco | CH-12363 | Fishkill | Wappingers Falls | Dutchess | 12590 | G | 8091 | Fishkill Plains | N |  | 100 | [13 empty] | NM | N | 1 SolarEdge Technologies SE100KUS (480V) | 2020-04-28 | 2020-05-12 | 10 | 2020-05-12 | 2020-05-12 | 2020-05-29 | 12 | [5 empty] | 2815 | 8431.4 |  | 2020-07-21 | 2020-07-21 | 2022-04-12 | 2023-03-08 | 2023-03-08 | 2023-04-20 | Y
Central Hudson |  | Lighthouse Solar | CH-12361 | Kingston | Cragsmoor | Ulster | 12420 | G | 3078 | Greenfield Rd | N |  | 7.54 | [13 empty] | NM | N | 26 Enphase Energy IQ7PLUS-72-x-US (240V) | 2020-03-23 | 2020-03-26 | 3 | 2020-03-26 | [14 empty] | 2020-07-17 | 2020-07-17 |  | Y
Central Hudson |  | Kasselman Solar | CH-12362 | Newburgh | New Paltz | Ulster | 12561 | G | 5024 | Ohioville | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000H-US (240V) | 2020-03-23 | 2020-03-26 | 3 | 2020-03-26 | [14 empty] | 2020-03-27 | 2020-03-27 |  | Y
Central Hudson |  | Lighthouse Solar | CH-12367 | Newburgh | New Paltz | Ulster | 12561 | G | 5021 | Ohioville | N |  | 12.18 | [13 empty] | NM | N | 42 Enphase Energy IQ7PLUS-72-x-US (240V) | 2020-03-11 | 2020-03-23 | 8 | 2020-03-23 | [17 empty] | W
Central Hudson |  | Suncommon | CH-12368 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 6057 | Todd Hill | N | CH-01788 | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000H-US (240V) | 2020-03-23 | 2020-03-27 | 4 | 2020-03-27 | [14 empty] | 2020-04-01 | 2020-04-02 |  | Y
Central Hudson |  | New York State Solar Farm | CH-12370 | Newburgh | Wallkill | Ulster | 12589 | G | 5033 | Galeville | N |  | 10.395 | [13 empty] | NM | N | 33 SunPower SPR-X22-360-E-AC (240V) | 2020-03-16 | 2020-03-24 | 6 | 2020-03-24 | [8 empty] | 350 | 350 |  | 2020-03-31 | 2020-03-31 | 2020-04-29 | 2020-06-03 | 2020-06-03 |  | Y
Central Hudson |  | New York State Solar Farm | CH-12369 | Newburgh | Highland | Ulster | 12528 | G | 5084 | Highland | N | CH-10750 | 1.89 | [13 empty] | NM | N | 6 SunPower SPR-E20-327-E-AC (240V) | 2020-03-16 | 2020-03-24 | 6 | 2020-03-24 | [14 empty] | 2020-06-02 | 2020-06-02 |  | Y
Central Hudson |  | New York State Solar Farm | CH-12371 | Newburgh | Gardiner | Ulster | 12525 | G | 5043 | East Walden | N |  | 11.34 | [13 empty] | NM | N | 36 SunPower SPR-X22-360-E-AC (240V) | 2020-03-16 | 2020-03-24 | 6 | 2020-03-24 | [8 empty] | 350 | 350 |  | 2020-03-31 | 2020-03-31 | 2020-04-22 |  |  |  | W
Central Hudson |  | Suncommon | CH-12372 | Kingston | Glasco | Ulster | 12432 | G | 2015 | Lincoln Park | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2020-03-16 | 2020-03-24 | 6 | 2020-03-24 | [14 empty] | 2020-04-13 | 2020-04-13 |  | Y
Central Hudson |  | New York State Solar Farm | CH-12373 | Newburgh | New Windsor | Orange | 12553 | G | 4097 | Bethlehem Rd | N |  | 9.765 | [13 empty] | NM | N | 31 SunPower SPR-E19-320-E-AC (240V) | 2020-03-16 | 2020-03-24 | 6 | 2020-03-24 | [14 empty] | 2020-06-05 | 2020-06-05 |  | Y
Central Hudson |  | self | CH-12375 | Newburgh | Newburgh | Orange | 12550 | G | 4011 | West Balmville | N |  | 10.44 | [13 empty] | NM | N | 36 Enphase Energy IQ7PLUS-72-x-US (240V) [SI1] | 2020-03-16 | 2020-03-24 | 6 | 2020-03-24 | [14 empty] | 2020-07-20 | 2020-07-20 |  | Y
Central Hudson |  | New York State Solar Farm | CH-12374 | Fishkill | Nelsonvl | Putnam | 10516 | G | 8087 | Tioronda | N | CH-12374 | 4.48 | [13 empty] | NM | N | 14 SunPower SPR-E20-327-E-AC (240V) | 2020-03-16 | 2020-03-24 | 6 | 2020-03-24 | [14 empty] | 2020-05-06 | 2020-05-06 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12376 | Kingston | Saugerties | Ulster | 12477 | G | 3003 | Saugerties | N |  | 3.8 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3800H-US (240V) | 2020-03-16 | 2020-03-24 | 6 | 2020-03-24 | [14 empty] | 2020-04-03 | 2020-04-03 |  | Y
Central Hudson |  | Solar Image | CH-12379 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6042 | Spackenkill | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) [SI1] | 2020-03-17 | 2020-03-24 | 5 | 2020-03-24 | [14 empty] | 2020-03-30 | 2020-03-30 |  | Y
Central Hudson |  | murphy solar and central air | CH-12378 | Catskill | Catskill | Greene | 12414 | G | 2001 | North Catskill | N |  | 7 | [13 empty] | NM | N | 1 SMA America SB7000TL-US-22 (240V) | 2020-03-25 | 2020-03-27 | 2 | 2020-03-27 | [14 empty] | 2020-04-27 | 2020-04-27 |  | Y
Central Hudson |  | Lighthouse Solar | CH-12377 | Newburgh | New Paltz | Ulster | 12561 | G | 5031 | Galeville | N | CH-03628 | 9.8 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) 1 SolarEdge Technologies SE3800H-US (240V) | 2020-03-17 | 2020-03-24 | 5 | 2020-03-24 | [8 empty] | 350 | 350 |  | 2020-03-26 | 2020-03-26 | 2020-04-22 | 2020-08-18 | 2020-08-18 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12381 | Newburgh | Montgomery | Orange | 12549 | G | 5054 | Maybrook | N |  | 12 | [13 empty] | NM | N | 2 SolarEdge Technologies SE6000 (240V) | 2020-03-18 | 2020-03-25 | 5 | 2020-03-25 | [14 empty] | 2020-06-29 | 2020-06-29 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12382 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6094 | Manchester | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000 (240V) | 2020-03-18 | 2020-03-25 | 5 | 2020-03-25 | [14 empty] | 2020-06-29 | 2020-06-29 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12383 | Newburgh | New Paltz | Ulster | 12561 | G | 5031 | Galeville | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE 10000A-US (240V) | 2020-03-18 | 2020-03-25 | 5 | 2020-03-25 | [14 empty] | 2020-07-01 | 2020-07-01 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12384 | Kingston | High Fls | Ulster | 12440 | G | 3022 | High Falls | N |  | 3.8 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3800A-US (240V) [SI1] | 2020-03-18 | 2020-03-25 | 5 | 2020-03-25 | [14 empty] | 2020-06-29 | 2020-06-29 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12385 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8052 | North Chelsea | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000 (240V) | 2020-03-18 | 2020-03-25 | 5 | 2020-03-25 | [14 empty] | 2020-06-11 | 2020-06-11 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12386 | Kingston | Kerhonkson | Ulster | 12446 | G | 3082 | Kerhonkson | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE 10000A-US (240V) | 2020-03-18 | 2020-03-25 | 5 | 2020-03-25 | [14 empty] | 2020-06-29 | 2020-06-29 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12387 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE 11400A-US (240V) | 2020-03-18 | 2020-03-25 | 5 | 2020-03-25 | [14 empty] | 2020-06-29 | 2020-06-29 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12388 | Kingston | Greenfield Park | Ulster | 12435 | G | 3078 | Greenfield Rd | N |  | 17.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) 1 SolarEdge Technologies SE7600H-US (240V) | 2020-03-18 | 2020-03-25 | 5 | 2020-03-25 | [14 empty] | 2020-06-29 | 2020-06-29 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12389 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7052 | Rhinebeck | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000 (240V) | 2020-03-18 | 2020-03-25 | 5 | 2020-03-25 | [14 empty] | 2020-07-01 | 2020-07-01 |  | Y
Central Hudson |  | Suncommon | CH-12390 | Catskill | Hunter | Greene | 12442 | E | 2081 | Hunter | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2020-03-18 | 2020-03-25 | 5 | 2020-03-25 | [14 empty] | 2020-06-24 | 2020-06-24 |  | Y
Central Hudson |  | Kasselman Solar | CH-12391 | Catskill | Greenvl | Greene | 12083 | G | 2061 | Freehold | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000H-US (240V) | 2020-03-18 | 2020-03-25 | 5 | 2020-03-25 | [14 empty] | 2020-03-26 | 2020-04-02 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12380 | Newburgh | Wallkill | Ulster | 12589 | G | 5041 | East Walden | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2020-03-18 | 2020-03-25 | 5 | 2020-03-25 | [14 empty] | 2020-04-27 | 2020-04-27 |  | Y
Central Hudson |  | Vivint Solar Developer, LLC | CH-12396 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7052 | Rhinebeck | N | CH-00800 | 2.88 | [13 empty] | NM | N | 12 Enphase Energy IQ7-60-x-US-& (240V) [SI1] | 2020-03-19 | 2020-03-26 | 5 | 2020-03-26 | [14 empty] | 2020-08-27 | 2020-08-27 |  | Y
Central Hudson |  | Vivint Solar Developer, LLC | CH-12395 | Kingston | Kingston | Ulster | 12401 | G | 1021 | East Kingston | N | CH-08673 | 1.68 | [13 empty] | NM | N | 7 Enphase Energy IQ7-60-x-US (240V) | 2020-03-19 | 2020-03-26 | 5 | 2020-03-26 | [17 empty] | W
Central Hudson |  | PlugPV LLC | CH-12393 | Newburgh | Newburgh | Orange | 12550 | G | 4022 | Coldenham | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000H-US (240V) | 2020-03-19 | 2020-03-26 | 5 | 2020-03-26 | [14 empty] | 2020-07-14 | 2020-07-14 |  | Y
Central Hudson |  | Ameresco | CH-12394 | Fishkill | Hopewell Junction | Dutchess | 12533 | G | 8093 | Fishkill Plains | N |  | 266.6 | [13 empty] | NM | N | 2 SolarEdge Technologies SE100KUS (480V) 1 SolarEdge Technologies SE66.6KUS (480V) | 2020-04-28 | 2020-05-12 | 10 | 2020-05-12 | 2020-05-12 | 2020-06-03 | 15 | [5 empty] | 7850 | 21972.02 |  | 2020-07-21 | 2020-07-21 | 2023-04-10 | 2023-06-16 | 2023-06-16 | 2023-08-01 | Y
Central Hudson |  | Tesla Energy | CH-12392 | Catskill | Catskill | Greene | 12414 | G | 2003 | North Catskill | Y | CH-10077 | 3.8 | 5 | [12 empty] | NM | N | 1 SolarEdge Technologies SE3800H-US (240V) 1TeslaAC Powerwall 2.0 | 2020-04-02 | 2020-04-02 | 0 | 2020-04-02 | [14 empty] | 2020-09-18 | 2020-09-18 |  | Y
Central Hudson |  | Sunrun Installation Service, Inc. | CH-12397 | Kingston | Kingston | Ulster | 12401 | G | 2017 | Lincoln Park | N |  | 4.8 | [13 empty] | NM | N | 1 Delta Electronics M5-TL-US (240V) [SI1] | 2020-04-06 | 2020-04-07 | 1 | 2020-04-07 | [14 empty] | 2020-07-09 | 2020-07-09 |  | Y
Central Hudson |  | New York State Solar Farm | CH-12398 | Kingston | Ellenvl | Ulster | 12428 | G | 3095 | Grimley Rd | N |  | 9.45 | [13 empty] | NM | N | 30 SunPower SPR-E20-327-E-AC (240V) | 2020-03-23 | 2020-03-26 | 3 | 2020-03-26 | [14 empty] | 2020-08-11 | 2020-08-11 |  | Y
Central Hudson |  | SRE Solar Origination 2, LLC | CH-12399 | Kingston | Kingston |  | 12401 | G | 2091 | Hurley Ave | N |  | 3250 | [13 empty] | CDG | Y | 26 Chint Power Systems America CPS SCH125KTL-DO/US-600 (600V) | 2020-04-17 | 2020-04-30 | 9 | 2020-04-30 | 2020-04-30 | 2020-05-21 | 15 | [14 empty] | W
Central Hudson |  | PlugPV LLC | CH-12400 | Newburgh | Campbell Hall | Orange | 10916 | G | 5052 | Maybrook | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2020-03-24 | 2020-03-27 | 3 | 2020-03-27 | [14 empty] | 2020-06-17 | 2020-06-17 |  | Y
Central Hudson |  | Kasselman Solar | CH-12401 | Fishkill | Fishkill |  | 12524 | G | 8055 | North Chelsea | N |  | 10.73 | [13 empty] | NM | N | 37 Enphase Energy IQ7PLUS-72-x-US (240V) | 2020-03-27 | 2020-03-27 | 0 | 2020-03-27 | [17 empty] | W
Central Hudson |  | Nexamp Solar, LLC | CH-12402 | Newburgh | Highland |  | 12547 | G | 5081 | Highland | N |  | 1250 | [13 empty] | CDG | Y | 10 SMA America SHP 125-US-20 (480V) | 2020-05-07 | 2020-05-21 | 10 | 2020-05-21 | 2020-05-21 | 2020-06-10 | 13 | 2020-08-04 | 2020-09-29 | 2020-12-23 | 59 | 21937.18 | 248586.3 | 1520 | 2021-02-12 | [5 empty] | 2021-08-25 | W | Y
Central Hudson |  | Vivint Solar Developer, LLC | CH-12403 | Kingston | Saugerties | Ulster | 12477 | G | 3004 | Saugerties | N | CH-08743 | 3.36 | [13 empty] | NM | N | 14 Enphase Energy IQ7-60-x-US (240V) | 2020-03-30 | 2020-03-30 | 0 | 2020-03-30 | [14 empty] | 2020-12-16 | 2020-12-16 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-12404 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8094 | Fishkill Plains | N |  | 6.24 | [13 empty] | NM | N | 26 Enphase Energy IQ7-60-x-US (240V) | 2020-03-30 | 2020-03-30 | 0 | 2020-03-30 | [14 empty] | 2020-07-09 | 2020-07-09 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-12405 | Kingston | Saugerties | Ulster | 12477 | G | 3003 | Saugerties | N |  | 14.88 | [13 empty] | NM | N | 62 Enphase Energy IQ7-60-x-US (240V) | 2020-03-30 | 2020-03-30 | 0 | 2020-03-30 | [14 empty] | 2020-07-07 | 2020-07-07 |  | Y
Central Hudson |  | PlugPV LLC | CH-12408 | Newburgh | Newburgh | Orange | 12550 | G | 4011 | West Balmville | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2020-03-31 | 2020-03-31 | 0 | 2020-03-31 | [14 empty] | 2020-07-27 | 2020-07-27 |  | Y
Central Hudson |  | Suncommon | CH-12407 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6092 | Manchester | N |  | 3.8 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3800H-US (240V) | 2020-03-31 | 2020-03-31 | 0 | 2020-03-31 | [14 empty] | 2020-07-22 | 2020-07-22 |  | Y
Central Hudson |  | Apex Solar Power, LLC | CH-12406 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6092 | Manchester | N |  | 9.765 | [13 empty] | NM | N | 31 SunPower SPR-E20-327-E-AC (240V) [SI1] | 2020-04-03 | 2020-04-03 | 0 | 2020-04-03 | [8 empty] | 350 | 350 |  | 2020-04-16 | 2020-04-16 | 2020-06-03 | 2020-09-01 | 2020-09-01 |  | Y
Central Hudson |  | PlugPV LLC | CH-12409 | Newburgh | New Windsor | Orange | 12553 | G | 4097 | Bethlehem Rd | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2020-04-01 | 2020-04-01 | 0 | 2020-04-01 | [14 empty] | 2020-08-03 | 2020-08-03 |  | Y
Central Hudson |  | PlugPV LLC | CH-12410 | Kingston | Mt Marion | Ulster | 12456 | G | 2016 | Lincoln Park | N |  | 3.8 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3800H-US (240V) | 2020-04-01 | 2020-04-01 | 0 | 2020-04-01 | [14 empty] | 2020-06-26 | 2020-06-26 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12411 | Kingston | Kingston | Ulster | 12401 | G | 1024 | East Kingston | N |  | 13.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) 1 SolarEdge Technologies SE6000H-US (240V) | 2020-04-01 | 2020-04-02 | 1 | 2020-04-02 | [8 empty] | 350 | 350 |  | 2020-04-08 | 2020-04-08 | 2020-06-25 | 2020-07-07 | 2020-07-07 |  | Y
Central Hudson |  | Suncommon | CH-12413 | Kingston | Shokan | Ulster | 12481 | G | 3011 | Woodstock | N |  | 12.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) 1 SolarEdge Technologies SE5000H-US (240V) | 2020-04-02 | 2020-04-03 | 1 | 2020-04-03 | [14 empty] | 2020-07-21 | 2020-07-21 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12412 | Kingston | Kingston | Ulster | 12401 | G | 1022 | East Kingston | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2020-04-02 | 2020-04-02 | 0 | 2020-04-02 | [14 empty] | 2020-07-14 | 2020-07-14 |  | Y
Central Hudson |  | Sunrun Inc | CH-12418 | Newburgh | Wallkill | Ulster | 12589 | G | 5013 | Modena | N |  | 4.32 | [13 empty] | NM | N | 18 Enphase Energy IQ7-60-x-US (240V) | 2020-04-06 | 2020-04-07 | 1 | 2020-04-07 | [14 empty] | 2020-08-17 | 2020-08-17 |  | Y
Central Hudson |  | Michael GWiliam | CH-12417 | Newburgh | Milton | Ulster | 12547 | G | 5083 | Highland | N |  | 10.8 | [13 empty] | NM | N | 15 Chilicon Power CP-720-60/72/96-208/240-MC4 (208V) [SI1] | 2020-04-06 | 2020-04-15 | 6 | 2020-04-15 | [14 empty] | 2021-01-27 | 2021-01-27 |  | Y
Central Hudson |  | PlugPV LLC | CH-12414 | Newburgh | Newburgh | Orange | 12550 | G | 4011 | West Balmville | N | CH-12414 | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2020-04-06 | 2020-04-06 | 0 | 2020-04-06 | [14 empty] | 2020-08-03 | 2020-08-03 |  | Y
Central Hudson |  | PlugPV LLC | CH-12415 | Kingston | Port Ewen | Ulster | 12466 | G | 1024 | East Kingston | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2020-04-06 | 2020-04-06 | 0 | 2020-04-06 | [14 empty] | 2020-06-19 | 2020-06-19 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12416 | Newburgh | New Windsor | Orange | 12553 | G | 4054 | Union Ave | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2020-04-06 | 2020-04-06 | 0 | 2020-04-06 | [14 empty] | 2020-04-30 | 2020-04-30 |  | Y
Central Hudson |  | PlugPV LLC | CH-12420 | Newburgh | Newburgh | Orange | 12550 | G | 5004 | Marlboro | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000H-US (240V) | 2020-04-07 | 2020-04-07 | 0 | 2020-04-07 | [17 empty] | W
Central Hudson |  | PlugPV LLC | CH-12421 | Poughkeepsie | Clinton Cors | Dutchess | 12514 | G | 7071 | Stanfordville | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000H-US (240V) | 2020-04-07 | 2020-04-07 | 0 | 2020-04-07 | [14 empty] | 2020-07-06 | 2020-07-06 |  | Y
Central Hudson |  | Kasselman Solar | CH-12419 | Catskill | Catskill | Greene | 12414 | G | 2042 | South Cairo | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2020-04-07 | 2020-04-07 | 0 | 2020-04-07 | [14 empty] | 2020-07-09 | 2020-07-09 |  | Y
Central Hudson |  | Sunrun Installation Service, Inc. | CH-12422 | Newburgh | Wallkill | Ulster | 12589 | G | 4011 | West Balmville | N |  | 6.24 | [13 empty] | NM | N | 26 Enphase Energy IQ7-60-x-US (240V) | 2020-04-08 | 2020-04-08 | 0 | 2020-04-08 | [14 empty] | 2020-09-08 | 2020-09-08 |  | Y
Central Hudson |  | New York State Solar Farm | CH-12425 | Kingston | High Fls | Ulster | 12440 | G | 3024 | High Falls | N |  | 3.78 | [13 empty] | NM | N | 12 SunPower SPR-E19-320-E-AC (240V) | 2020-04-22 | 2020-04-23 | 1 | 2020-04-23 | [14 empty] | 2020-07-15 | 2020-07-15 |  | Y
Central Hudson |  | Suncommon | CH-12424 | Kingston | Kingston | Ulster | 12401 | G | 2093 | Hurley Ave | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2020-04-09 | 2020-04-09 | 0 | 2020-04-09 | [14 empty] | 2020-08-18 | 2020-08-18 |  | Y
Central Hudson |  | Autonomous Energies | CH-12426 | Catskill | Catskill | Greene | 12414 | G | 2001 | North Catskill | N |  | 27.26 | [13 empty] | NM | Y | 94 Enphase Energy IQ7PLUS-72-x-US (240V) | 2020-04-09 | 2020-04-17 | 5 | 2020-04-17 | [14 empty] | 2020-10-12 | 2020-10-12 |  | Y | Y
Central Hudson |  | Tesla Energy Operations Inc | CH-12430 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7052 | Rhinebeck | N |  | 15.36 | [13 empty] | NM | N | 2 Delta Electronics M8-TL-US (240V) [SI1] | 2020-05-27 | 2020-05-28 | 1 | 2020-05-28 | [17 empty] | W
Central Hudson |  | Sunrun Installation Service, Inc. | CH-12428 | Newburgh | Highland | Ulster | 12528 | G | 5081 | Highland | N |  | 4.8 | [13 empty] | NM | N | 1 Delta Electronics M5-TL-US (240V) [SI1] | 2020-05-11 | 2020-05-15 | 4 | 2020-05-15 | [14 empty] | 2020-11-23 | 2020-11-23 |  | Y
Central Hudson |  | Sunrun Installation Service, Inc. | CH-12429 | Newburgh | New Windsor | Orange | 12553 | G | 4094 | Bethlehem Rd | N |  | 8.4 | [13 empty] | NM | N | 35 Enphase Energy IQ7-60-x-US-& (240V) [SI1] | 2020-05-11 | 2020-05-12 | 1 | 2020-05-12 | [14 empty] | 2020-09-16 | 2020-09-16 |  | Y
Central Hudson |  | Kasselman Solar | CH-12427 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6043 | Spackenkill | N |  | 3.8 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3800H-US (240V) | 2020-04-22 | 2020-05-06 | 10 | 2020-05-06 | [14 empty] | 2020-06-25 | 2020-06-25 |  | Y
Central Hudson |  | Sunrun Installation Service, Inc. | CH-12431 | Newburgh | Highland | Ulster | 12528 | G | 5082 | Highland | N |  | 4.8 | [13 empty] | NM | N | 20 Enphase Energy IQ7-60-x-US (240V) | 2020-05-13 | 2020-05-13 | 0 | 2020-05-13 | [14 empty] | 2020-07-23 | 2020-07-23 |  | Y
Central Hudson |  | Sunrun Inc | CH-12433 | Fishkill | Fishkill | Dutchess | 12524 | G | 8094 | Fishkill Plains | N |  | 4.8 | [13 empty] | NM | N | 20 Enphase Energy IQ7-60-x-US (240V) | 2020-05-11 | 2020-05-12 | 1 | 2020-05-12 | [14 empty] | 2020-09-14 | 2020-09-14 |  | Y
Central Hudson |  | Sunrun Installation Service, Inc. | CH-12432 | Fishkill | Wappingrs Fls |  | 12590 | G | 8043 | Myers Corners | N |  | 12 | [13 empty] | NM | N | 50 Enphase Energy IQ7-60-x-US (240V) | 2020-06-01 | 2020-06-02 | 1 | 2020-06-02 | [17 empty] | W
Central Hudson |  | Suncommon | CH-12434 | Kingston | Lk Hill | Ulster | 12448 | G | 3012 | Woodstock | N | CH-01684 | 3 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3000H-US (240V) | 2020-04-14 | 2020-04-21 | 5 | 2020-04-21 | [14 empty] | 2020-07-16 | 2020-07-16 |  | Y
Central Hudson |  | Sunrun Installation Service, Inc. | CH-12435 | Newburgh | Highland | Ulster | 12528 | G | 5081 | Highland | N |  | 10.6 | [13 empty] | NM | N | 1 Delta Electronics M5-TL-US (240V) [SI1] 1 Delta Electronics M6-TL-US (240V) [SI1] | 2020-06-03 | 2020-06-04 | 1 | 2020-06-04 | [8 empty] | 350 | 350 |  | 2020-06-23 | 2020-06-23 | 2020-07-09 | 2020-10-12 | 2020-10-12 |  | Y
Central Hudson |  | Sunrun Installation Service, Inc. | CH-12436 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6066 | Inwood Ave | N |  | 2.64 | [13 empty] | NM | N | 11 Enphase Energy IQ7-60-x-US (240V) | 2020-05-12 | 2020-05-13 | 1 | 2020-05-13 | [14 empty] | 2020-08-19 | 2020-08-19 |  | Y
Central Hudson |  | New York State Solar Farm | CH-12438 | Newburgh | Marlboro | Ulster | 12542 | G | 5001 | Marlboro | N |  | 6.3 | [13 empty] | NM | N | 20 SunPower SPR-X21-335-BLK-E-AC (240V) | 2020-04-22 | 2020-04-23 | 1 | 2020-04-23 | [14 empty] | 2020-07-30 | 2020-07-30 |  | Y
Central Hudson |  | New York State Solar Farm | CH-12437 | Kingston | Kingston | Ulster | 12401 | G | 1011 | Boulevard | N | CH-12437 | 24.57 | [13 empty] | NM | N | 78 SunPower SPR-X22-360-E-AC (240V) | 2020-04-22 | 2020-04-23 | 1 | 2020-04-23 | [8 empty] | 350 | 350 |  | 2020-05-15 | 2020-05-15 | 2020-07-09 | 2020-07-13 | 2020-07-13 |  | Y
Central Hudson |  | Tesla | CH-12439 | Kingston | Lk Katrine |  | 12449 | G | 2011 | Lincoln Park | Y |  | 11.4 | 5 | [12 empty] | NM | N | 1 SolarEdge Technologies SE11400A-US (240V) [SI1] 1TeslaAC Powerwall 2.0 | 2020-04-29 | 2020-04-29 | 0 | 2020-04-29 | [17 empty] | W
Central Hudson |  | murphy solar and central air | CH-12440 | Catskill | Palenvl | Greene | 12463 | G | 2001 | North Catskill | N |  | 3 | [13 empty] | NM | N | 1 SMA America SB3000TL-US-22 (240V) | 2020-04-20 | 2020-04-22 | 2 | 2020-04-22 | [17 empty] | N
Central Hudson |  | Sunrun Installation Service, Inc. | CH-12442 | Newburgh | New Windsor | Orange | 12553 | G | 4042 | Union Ave | N |  | 2.88 | [13 empty] | NM | N | 12 Enphase Energy IQ7-60-x-US-& (240V) [SI1] | 2020-04-23 | 2020-04-24 | 1 | 2020-04-24 | [14 empty] | 2021-02-08 | 2021-02-08 |  | Y
Central Hudson |  | Suncommon | CH-12441 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7041 | Staatsburg | Y | CH-11918 |  | 15 | [12 empty] | NM | N | 3TeslaPowerwall 2.0 | 2020-04-29 | 2020-04-29 | 0 | 2020-04-29 | [14 empty] | 2020-06-30 | 2020-06-30 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-12443 | Poughkeepsie | Wappingrs Fls | Dutchess | 12590 | G | 6046 | Spackenkill | N |  | 8.12 | [13 empty] | NM | N | 28 Enphase Energy IQ7PLUS-72-x-US (240V) | 2020-04-23 | 2020-04-24 | 1 | 2020-04-24 | [14 empty] | 2020-07-23 | 2020-07-23 |  | Y
Central Hudson |  | Tesla Energy Operations, Inc. | CH-12444 | Kingston | Woodstock | Ulster | 12498 | G | 3013 | Woodstock | Y | CH-04525 |  | 5 | [12 empty] | NM | N | 1TeslaAC Powerwall 2.0 | 2020-04-24 | 2020-04-27 | 1 | 2020-04-27 | [14 empty] | 2020-05-01 | 2020-05-01 |  | Y
Central Hudson |  | Stella Solar | CH-12448 | Catskill | Westerlo |  | 12193 | G | 1092 | Westerlo | N |  | 2497.5 | [13 empty] | CDG | Y | 15 ABB PVS-166-TL-POWER-MODULE-1-US (800V) [SI1] | 2020-05-15 | 2020-05-27 | 7 | 2020-05-27 | 2020-05-27 | 2020-06-17 | 15 | 2020-07-01 | 2020-08-17 | 2020-11-10 | 60 | 19250.71 | 22497195 | [7 empty] | 2021-04-27 | W
Central Hudson |  | Green Hybrid Energy Soltions Inc. | CH-12447 | Newburgh | Milton | Ulster | 12547 | G | 5003 | Marlboro | N | CH-02566 | 16.48 | [13 empty] | NM | N | 30 Enphase Energy IQ7-60-x-US-& (240V) [SI1] 32 Enphase Energy IQ7PLUS-72-x-US (240V) | 2020-04-27 | 2020-04-27 | 0 | 2020-04-27 | [14 empty] | 2021-09-22 | 2021-09-22 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12446 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8096 | Fishkill Plains | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2020-04-27 | 2020-04-27 | 0 | 2020-04-27 | [14 empty] | 2020-06-05 | 2020-06-05 |  | Y
Central Hudson |  | Suncommon | CH-12449 | Poughkeepsie | Staatsburg | Dutchess | 12580 | G | 7041 | Staatsburg | Y |  | 7.6 | 5 | [12 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) 1TeslaPowerwall 2.0 | 2020-04-29 | 2020-04-29 | 0 | 2020-04-29 | [14 empty] | 2020-09-01 | 2020-09-01 |  | Y
Central Hudson |  | Sunrun Installation Service, Inc. | CH-12450 | Kingston | Saugerties | Ulster | 12477 | G | 2016 | Lincoln Park | N |  | 2.64 | [13 empty] | NM | N | 11 Enphase Energy IQ7-60-x-US (240V) | 2020-04-29 | 2020-04-29 | 0 | 2020-04-29 | [14 empty] | 2020-07-16 | 2020-07-16 |  | Y
Central Hudson |  | Sunrun Installation Service, Inc. | CH-12451 | Newburgh | New Windsor | Orange | 12553 | G | 4092 | Bethlehem Rd | N |  | 3.84 | [13 empty] | NM | N | 16 Enphase Energy IQ7-60-x-US (240V) | 2020-04-29 | 2020-04-29 | 0 | 2020-04-29 | [14 empty] | 2020-09-11 | 2020-09-11 |  | Y
Central Hudson |  | New York State Solar Farm | CH-12452 | Poughkeepsie | Millbrook | Dutchess | 12545 | G | 7025 | Tinkertown | Y |  | 4.9 | 5 | [12 empty] | NM | N | 14 SunPower SPR-A415-G-AC (240V) 1TESLATESLA POWERWALL 2 | 2020-05-26 | 2020-05-27 | 1 | 2020-05-27 | [14 empty] | 2020-09-14 | 2020-09-14 |  | Y
Central Hudson |  | Suncommon | CH-12453 | Fishkill | Cold Spg | Putnam | 10516 | G | 8063 | Merritt Park | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2020-05-07 | 2020-05-13 | 4 | 2020-05-13 | [14 empty] | 2020-09-14 | 2020-09-14 |  | Y
Central Hudson |  | Sunrun Installation Service, Inc. | CH-12456 | Kingston | Kingston | Ulster | 12401 | G | 112 | South Wall St | N |  | 7.92 | [13 empty] | NM | N | 33 Enphase Energy IQ7-60-x-US-& (240V) [SI1] | 2020-05-04 | 2020-05-05 | 1 | 2020-05-05 | [14 empty] | 2020-09-16 | 2020-09-16 |  | Y
Central Hudson |  | Sunrun Installation Service, Inc. | CH-12457 | Kingston | Saugerties | Ulster | 12477 | G | 3005 | Saugerties | N |  | 4.8 | [13 empty] | NM | N | 20 Enphase Energy IQ7-60-x-ACM-US (240V) | 2020-05-04 | 2020-05-05 | 1 | 2020-05-05 | [14 empty] | 2020-09-16 | 2020-09-16 |  | Y
Central Hudson |  | Sunrun Installation Service, Inc. | CH-12455 | Catskill | Haines Fls |  | 12436 | G | 2385 | Lawrenceville | N |  | 9.6 | [13 empty] | NM | N | 40 Enphase Energy IQ7-60-x-US (240V) | 2020-05-04 | 2020-05-04 | 0 | 2020-05-04 | [17 empty] | W
Central Hudson |  | Autonomous Energies | CH-12454 | Kingston | Port Ewen | Ulster | 12466 | G | 1024 | East Kingston | N |  | 10.8 | [13 empty] | NM | N | 7 Chilicon Power CP-720-60/72/96-208/240-MC4 (240V) [SI1] 8 Chilicon Power CP-720-60/72/96-208/240-MC4 (240V) [SI1] | 2020-05-04 | 2020-05-05 | 1 | 2020-05-05 | [14 empty] | 2020-05-21 | 2020-05-21 |  | Y
Central Hudson |  | Sunrun Installation Service, Inc. | CH-12461 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8091 | Fishkill Plains | N |  | 3.84 | [13 empty] | NM | N | 16 Enphase Energy IQ7-60-x-US-& (240V) [SI1] | 2020-05-05 | 2020-05-06 | 1 | 2020-05-06 | [14 empty] | 2020-09-18 | 2020-09-18 |  | Y
Central Hudson |  | PlugPV LLC | CH-12460 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8091 | Fishkill Plains | N |  | 20 | [13 empty] | NM | N | 2 SolarEdge Technologies SE10000H-US (240V) | 2020-05-05 | 2020-05-06 | 1 | 2020-05-06 | [14 empty] | 2020-08-26 | 2020-08-26 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12459 | Kingston | Kerhonkson | Ulster | 12446 | G | 3082 | Kerhonkson | N | CH-12459 | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2020-05-05 | 2020-05-05 | 0 | 2020-05-05 | [14 empty] | 2020-05-21 | 2020-05-21 |  | Y
Central Hudson |  | Suncommon | CH-12463 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7051 | Rhinebeck | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2020-05-06 | 2020-05-07 | 1 | 2020-05-07 | [14 empty] | 2020-08-03 | 2020-08-03 |  | Y
Central Hudson |  | Suncommon | CH-12462 | Poughkeepsie | Tivoli | Dutchess | 12583 | G | 7062 | Milan | N |  | 3 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3000H-US (240V) | 2020-05-06 | 2020-05-06 | 0 | 2020-05-06 | [14 empty] | 2020-07-06 | 2020-07-06 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12464 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 7041 | Staatsburg | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2020-05-07 | 2020-05-07 | 0 | 2020-05-07 | [14 empty] | 2020-05-21 | 2020-05-21 |  | Y
Central Hudson |  | Novel approaches Solar applications | CH-12465 | Newburgh | Montgomery | Orange | 12549 | G | 5073 | Montgomery | N |  | 25 | [13 empty] | NM | N | 2 Fronius USA Fronius Primo 12.5-1 (240V) | 2020-05-07 | 2020-05-07 | 0 | 2020-05-07 | [14 empty] | 2020-10-14 | 2020-10-14 |  | Y
Central Hudson |  | New York State Solar Farm | CH-12467 | Catskill | Catskill | Greene | 12414 | G | 2042 | South Cairo | N |  | 13.545 | [13 empty] | NM | N | 43 SunPower SPR-E19-320-E-AC (240V) | 2020-05-07 | 2020-05-08 | 1 | 2020-05-08 | [8 empty] | 350 | 350 |  | 2020-05-15 | 2020-05-15 | 2020-05-22 | 2020-07-16 | 2020-07-16 |  | Y
Central Hudson |  | Tesla Energy | CH-12466 | Kingston | Kingston |  | 12401 | G | 2093 | Hurley Ave | Y |  | 3.8 | 10 | [12 empty] | NM | N | 1 SolarEdge Technologies SE3800H-US (240V) 2TeslaAC Powerwall 2.0 | 2020-05-07 | 2020-05-08 | 1 | 2020-05-08 | [17 empty] | W
Central Hudson |  | Novel approaches Solar applications | CH-12468 | Kingston | Ellenville | Ulster | 12428 | G | 3076 | Greenfield Rd | N |  | 30 | [13 empty] | NM | N | 2 Fronius USA Fronius Primo 15.0-1 (240V) | 2020-05-26 | 2020-05-27 | 1 | 2020-05-27 | [8 empty] | 1128.75 | 1590.01 |  | 2020-07-06 | 2020-07-06 | 2020-08-26 | 2021-05-24 | 2021-05-24 | 2021-05-25 | Y
Central Hudson |  | Trinity Solarr | CH-12469 | Fishkill | Fishkill | Dutchess | 12524 | G | 8014 | Forgebrook | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2020-05-08 | 2020-05-08 | 0 | 2020-05-08 | [14 empty] | 2020-09-14 | 2020-09-14 |  | Y
Central Hudson |  | Kasselman Solar | CH-12473 | Poughkeepsie | Wappingrs Fls | Dutchess | 12590 | G | 6052 | Todd Hill | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2020-05-11 | 2020-05-12 | 1 | 2020-05-12 | [14 empty] | 2020-08-03 | 2020-08-03 |  | Y
Central Hudson |  | Sunrun Installation Service, Inc. | CH-12472 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6044 | Spackenkill | N |  | 6.72 | [13 empty] | NM | N | 28 Enphase Energy IQ7-60-x-US-& (240V) [SI1] | 2020-05-11 | 2020-05-11 | 0 | 2020-05-11 | [14 empty] | 2020-07-09 | 2020-07-09 |  | Y
Central Hudson |  | SunPower Direct (NY) | CH-12471 | Newburgh | Newburgh | Orange | 12550 | G | 5004 | Marlboro | N |  | 9.45 | [13 empty] | NM | N | 30 Enphase Energy IQ7XS-96-x-ACM-US-y (240V) [SI1] | 2020-05-11 | 2020-05-11 | 0 | 2020-05-11 | [14 empty] | 2020-10-12 | 2020-10-12 |  | Y
Central Hudson |  | Suncommon | CH-12470 | Poughkeepsie | Pine Plns | Dutchess | 12567 | G | 7091 | Pulvers Corners | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2020-05-11 | 2020-05-12 | 1 | 2020-05-12 | [8 empty] | 350 | 350 |  | 2020-06-24 | 2020-06-24 | 2020-07-01 | 2020-07-17 | 2020-07-17 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-12474 | Fishkill | Fishkill | Dutchess | 12524 | G | 8014 | Forgebrook | N |  | 7.68 | [13 empty] | NM | N | 32 Enphase Energy IQ7-60-x-US (240V) | 2020-05-11 | 2020-05-12 | 1 | 2020-05-12 | [14 empty] | 2020-07-21 | 2020-07-21 |  | Y
Central Hudson |  | Tesla Energy | CH-12475 | Catskill | Elka Pk | Greene | 12427 | G | 2385 | Lawrenceville | Y |  | 7.6 | 10 | [12 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) [SI1] 2TeslaAC Powerwall 2.0 | 2020-05-13 | 2020-05-13 | 0 | 2020-05-13 | [17 empty] | W
Central Hudson |  | Tesla Energy Operations, Inc. | CH-12476 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8043 | Myers Corners | Y | CH-06805 |  | 5 | [12 empty] | NM | N | 1TeslaAC Powerwall 2.0 | 2020-05-18 | 2020-05-18 | 0 | 2020-05-18 | [14 empty] | 2023-03-07 | 2023-03-13 |  | Y
Central Hudson |  | Suncommon | CH-12477 | Kingston | Kingston | Ulster | 12401 | G | 1011 | Boulevard | Y | CH-01698 |  | 5 | [12 empty] | NM | N | 1TeslaPowerwall 2.0 | 2020-05-18 | 2020-05-18 | 0 | 2020-05-18 | [14 empty] | 2020-07-21 | 2020-07-21 |  | Y
Central Hudson |  | Sunrun Installation Service, Inc. | CH-12481 | Newburgh | Campbell Hall | Orange | 10916 | G | 5051 | Maybrook | N |  | 10.56 | [13 empty] | NM | N | 44 Enphase Energy IQ7-60-x-US (240V) | 2020-05-13 | 2020-05-14 | 1 | 2020-05-14 | [14 empty] | 2020-08-06 | 2020-08-06 |  | Y
Central Hudson |  | Suncommon | CH-12478 | Poughkeepsie | Clinton Cors | Dutchess | 12514 | G | 7071 | Stanfordville | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE11400H-US (240V) | 2020-05-13 | 2020-05-13 | 0 | 2020-05-13 | [14 empty] | 2020-08-26 | 2020-08-26 |  | Y
Central Hudson |  | Kasselman Solar | CH-12480 | Catskill | Catskill | Greene | 12414 | G | 2001 | North Catskill | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2020-05-13 | 2020-05-14 | 1 | 2020-05-14 | [17 empty] | W
Central Hudson |  | Kasselman Solar | CH-12482 | Fishkill | Beacon | Dutchess | 12508 | G | 8016 | Forgebrook | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2020-05-13 | 2020-05-15 | 2 | 2020-05-15 | [14 empty] | 2020-08-03 | 2020-08-03 |  | Y
Central Hudson |  | Sunrun Installation Service, Inc. | CH-12483 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 6.72 | [13 empty] | NM | N | 28 Enphase Energy IQ7-60-x-US (240V) | 2020-05-14 | 2020-05-15 | 1 | 2020-05-15 | [14 empty] | 2020-10-22 | 2020-10-22 |  | Y
Central Hudson |  | Sunrun Installation Service, Inc. | CH-12485 | Poughkeepsie | Poughkeepsie |  | 12601 | G | 6011 | Sand Dock | N |  | 4.8 | [13 empty] | NM | N | 1 Delta Electronics M5-TL-US (208V) [SI1] | 2020-05-15 | 2020-05-18 | 1 | 2020-05-18 | [17 empty] | W
Central Hudson |  | Suncommon | CH-12484 | Fishkill | Cold Spg | Putnam | 10516 | G | 8063 | Merritt Park | Y |  | 5 | 5 | [12 empty] | NM | N | 1 SolarEdge Technologies SE5000H-US (240V) 1TeslaPowerwall 2 | 2020-05-21 | 2020-05-22 | 1 | 2020-05-22 | [14 empty] | 2020-09-21 | 2020-09-21 |  | Y
Central Hudson |  | New York State Solar Farm | CH-12487 | Fishkill | Beacon | Dutchess | 12508 | G | 8085 | Tioronda | N |  | 7.56 | [13 empty] | NM | N | 24 SunPower SPR-E20-327-E-AC (240V) | 2020-05-18 | 2020-05-18 | 0 | 2020-05-18 | [14 empty] | 2020-06-18 | 2020-06-18 |  | Y
Central Hudson |  | New York State Solar Farm | CH-12486 | Newburgh | Wallkill | Ulster | 12589 | G | 5043 | East Walden | N |  | 6.615 | [13 empty] | NM | N | 21 SunPower SPR-E19-320-E-AC (240V) | 2020-05-18 | 2020-05-18 | 0 | 2020-05-18 | [14 empty] | 2020-07-20 | 2020-07-20 |  | Y
Central Hudson |  | Kasselman Solar | CH-12488 | Catskill | Haines Fls | Greene | 12436 | G | 2385 | Lawrenceville | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2020-05-18 | 2020-05-18 | 0 | 2020-05-18 | [17 empty] | W
Central Hudson |  | Sunrun Installation Service, Inc. | CH-12489 | Kingston | Port Ewen | Ulster | 12466 | G | 1024 | East Kingston | N |  | 2.16 | [13 empty] | NM | N | 9 Enphase Energy IQ7-60-x-US (240V) | 2020-05-18 | 2020-05-19 | 1 | 2020-05-19 | [14 empty] | 2020-10-19 | 2020-10-19 |  | Y
Central Hudson |  | Suncommon | CH-12490 | Kingston | Port Ewen | Ulster | 12466 | G | 1014 | Boulevard | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2020-05-22 | 2020-05-26 | 1 | 2020-05-26 | [14 empty] | 2020-09-03 | 2020-09-03 |  | Y
Central Hudson |  | Sunrun Installation Service, Inc. | CH-12491 | Kingston | Woodstock | Ulster | 12498 | G | 3003 | Saugerties | N |  | 7.44 | [13 empty] | NM | N | 31 Enphase Energy IQ7-60-x-US (240V) | 2020-05-20 | 2020-05-21 | 1 | 2020-05-21 | [14 empty] | 2020-09-16 | 2020-09-16 |  | Y
Central Hudson |  | Trinity Solar | CH-12493 | Kingston | Stone Ridge | Ulster | 12484 | G | 3023 | High Falls | N |  | 3.8 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3800H-US (240V) [SI1] | 2020-05-21 | 2020-05-22 | 1 | 2020-05-22 | [14 empty] | 2020-08-26 | 2020-08-26 |  | Y
Central Hudson |  | Hudson River Renewables LLC | CH-12492 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7053 | Rhinebeck | N |  | 15.08 | [13 empty] | NM | N | 52 Enphase Energy IQ7PLUS-72-x-US (240V) | 2020-06-02 | 2020-06-03 | 1 | 2020-06-03 | [8 empty] | 350 | 350 |  | 2020-06-05 | 2020-06-05 | 2020-06-29 | 2020-07-01 | 2020-07-01 |  | Y
Central Hudson |  | Sunrun Installation Service, Inc. | CH-12495 | Catskill | Tannersvl | Greene | 12485 | G | 2385 | Lawrenceville | N |  | 4.56 | [13 empty] | NM | N | 19 Enphase Energy IQ7-60-x-US (240V) | 2020-05-21 | 2020-05-26 | 2 | 2020-05-26 | [14 empty] | 2020-09-17 | 2020-09-17 |  | Y
Central Hudson |  | Kasselman Solar | CH-12494 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8093 | Fishkill Plains | N | CH-12494 | 6.48 | [13 empty] | NM | N | 27 Enphase Energy IQ7-60-x-US (240V) | 2020-05-27 | 2020-05-28 | 1 | 2020-05-28 | [14 empty] | 2020-07-29 | 2020-07-29 |  | Y
Central Hudson |  | New York State Solar Farm | CH-12498 | Newburgh | Gardiner | Ulster | 12525 | G | 5011 | Modena | N |  | 15.75 | [13 empty] | NM | N | 50 SunPower SPR-E20-327-E-AC (240V) | 2020-05-22 | 2020-05-27 | 2 | 2020-05-27 | [8 empty] | 350 | 350 |  | 2020-06-09 | 2020-06-09 | 2020-06-18 | 2020-07-02 | 2020-07-02 |  | Y
Central Hudson |  | Kasselman Solar | CH-12497 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8046 | Myers Corners | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2020-05-22 | 2020-05-27 | 2 | 2020-05-27 | [14 empty] | 2020-08-03 | 2020-08-03 |  | Y
Central Hudson |  | New York State Solar Farm | CH-12500 | Newburgh | Highland | Ulster | 12528 | G | 5083 | Highland | N |  | 17.45 | [13 empty] | NM | N | 50 SunPower SPR-A400-G-AC (240V) | 2020-05-26 | 2020-05-28 | 2 | 2020-05-28 | [14 empty] | 2020-07-30 | 2020-07-30 |  | Y
Central Hudson |  | Suncommon | CH-12499 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6096 | Manchester | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000H-US (240V) | 2020-05-28 | 2020-05-29 | 1 | 2020-05-29 | [14 empty] | 2020-09-16 | 2020-09-16 |  | Y
Central Hudson |  | Lighthouse Solar | CH-12501 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7052 | Rhinebeck | N |  | 9 | [13 empty] | NM | N | 1 SolarEdge Technologies SE9KUS (208V) [SI1] | 2020-06-02 | 2020-06-12 | 8 | 2020-06-12 | [14 empty] | 2020-08-11 | 2020-08-11 |  | Y
Central Hudson |  | Sunrun Installation Service, Inc. | CH-12503 | Kingston | Kingston | Ulster | 12401 | G | 1022 | East Kingston | N |  | 4.8 | [13 empty] | NM | N | 20 Enphase Energy IQ7-60-x-US (240V) | 2020-05-27 | 2020-05-29 | 2 | 2020-05-29 | [14 empty] | 2020-09-14 | 2020-09-14 |  | Y
Central Hudson |  | MOMENTUM SOLAR | CH-12502 | Newburgh | Newburgh |  | 12550 | G | 4053 | Union Ave | N |  | 2.9 | [13 empty] | NM | N | 12 Enphase Energy IQ7-60-x-US (240V) | 2020-05-27 | 2020-05-29 | 2 | 2020-05-29 | [17 empty] | W
Central Hudson |  | Infinity Solar Systems | CH-12507 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 6051 | Todd Hill | N |  | 14.16 | [13 empty] | NM | N | 59 Enphase Energy IQ7-60-x-US (240V) | 2020-05-28 | 2020-06-01 | 2 | 2020-06-01 | [8 empty] | 350 | 350 |  | 2020-06-02 | 2020-06-02 | 2020-07-30 | 2020-08-14 | 2020-08-14 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-12505 | Newburgh | Newburgh | Orange | 12550 | G | 4023 | Coldenham | N |  | 6 | [13 empty] | NM | N | 25 Enphase Energy IQ7-60-x-US (240V) | 2020-05-28 | 2020-05-29 | 1 | 2020-05-29 | [14 empty] | 2020-08-31 | 2020-08-31 |  | Y
Central Hudson |  | Suncommon | CH-12504 | Kingston | Olive Brdg | Ulster | 12461 | G | 3024 | High Falls | N | CH-12504 | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2020-05-28 | 2020-05-29 | 1 | 2020-05-29 | [14 empty] | 2021-01-06 | 2021-01-06 |  | Y
Central Hudson |  | Sunrun Installation Service, Inc. | CH-12506 | Newburgh | Newburgh | Orange | 12550 | G | 4012 | West Balmville | N |  | 6.96 | [13 empty] | NM | N | 29 Enphase Energy IQ7-60-x-US (240V) | 2020-05-29 | 2020-06-01 | 1 | 2020-06-01 | [14 empty] | 2020-09-21 | 2020-09-21 |  | Y
Central Hudson |  | Solar Generation | CH-12509 | Newburgh | Newburgh |  | 12550 | G | 5001 | Marlboro | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) 1 SolarEdge Technologies SE3800H-US (240V) | 2020-06-03 | 2020-06-03 | 0 | 2020-06-03 | [14 empty] | 2020-07-23 | 2020-07-23 |  | W
Central Hudson |  | Solar Generation | CH-12510 | Kingston | Accord | Ulster | 12404 | G | 3024 | High Falls | N | CH-12510 | 6.3 | [13 empty] | NM | N | 20 Enphase Energy IQ7X-96-x-US (240V) [SI1] | 2020-06-02 | 2020-06-03 | 1 | 2020-06-03 | [14 empty] | 2020-07-30 | 2020-07-30 |  | Y
Central Hudson |  | Solar Generation | CH-12511 | Kingston | Accord | Ulster | 12404 | G | 3024 | High Falls | N |  | 15.2 | [13 empty] | NM | N | 2 SolarEdge Technologies SE7600H-US (240V) | 2020-06-03 | 2020-06-04 | 1 | 2020-06-04 | [14 empty] | 2020-08-26 | 2020-08-26 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-12514 | Newburgh | Newburgh | Orange | 12550 | G | 4045 | Union Ave | N |  | 5.76 | [13 empty] | NM | N | 24 Enphase Energy IQ7-60-x-US (240V) | 2020-05-29 | 2020-06-02 | 2 | 2020-06-02 | [14 empty] | 2020-06-26 | 2020-06-26 |  | Y
Central Hudson |  | PlugPV LLC | CH-12508 | Newburgh | Newburgh | Orange | 12550 | G | 4022 | Coldenham | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2020-05-29 | 2020-06-01 | 1 | 2020-06-01 | [8 empty] | 350 | 350 |  | 2020-06-03 | 2020-06-03 | 2020-07-20 | 2020-08-11 | 2020-08-11 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-12513 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6044 | Spackenkill | N | CH-12513 | 8.4 | [13 empty] | NM | N | 35 Enphase Energy IQ7-60-x-US (240V) | 2020-06-01 | 2020-06-02 | 1 | 2020-06-02 | [14 empty] | 2020-08-03 | 2020-08-03 |  | Y
Central Hudson |  | Suncommon | CH-12512 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7052 | Rhinebeck | N |  | 15.2 | [13 empty] | NM | N | 2 SolarEdge Technologies SE7600H-US (240V) | 2020-05-29 | 2020-06-01 | 1 | 2020-06-01 | [8 empty] | 350 | 350 |  | 2020-06-15 | 2020-06-15 | 2020-07-01 | 2020-11-23 | 2020-11-23 |  | Y
Central Hudson |  | IPPsolar Integration LLC | CH-12515 | Poughkeepsie | Pleasant Valley | Dutchess | 12569 | G | 7024 | Tinkertown | N |  | 5000 | [13 empty] | CDG | Y | 40 SMA America SHP 125-US-21 (480V) [SI1] | 2020-07-31 | 2020-08-14 | 10 | 2020-08-14 | 2020-08-14 | 2020-09-04 | 15 | 2020-12-02 | 2021-04-09 | 2021-07-06 | 60 | 17000 | 201470.8 |  | 2021-07-22 | 2022-01-12 | 2022-01-12 | 2025-11-14 |  |  |  | N | Y
Central Hudson |  | Sunrun Installation Service, Inc. | CH-12518 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6093 | Manchester | N |  | 2.64 | [13 empty] | NM | N | 11 Enphase Energy IQ7-60-x-US (240V) | 2020-06-01 | 2020-06-03 | 2 | 2020-06-03 | [14 empty] | 2020-08-13 | 2020-08-13 |  | Y
Central Hudson |  | Vivint Solar Developer, LLC | CH-12516 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8054 | North Chelsea | N |  | 3.84 | [13 empty] | NM | N | 16 Enphase Energy IQ7-60-x-US (240V) | 2020-06-04 | 2020-06-05 | 1 | 2020-06-05 | [14 empty] | 2020-12-02 | 2020-12-02 |  | Y
Central Hudson |  | Suncommon | CH-12517 | Kingston | Accord | Ulster | 12404 | G | 3024 | High Falls | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2020-06-01 | 2020-06-03 | 2 | 2020-06-03 | [14 empty] | 2020-10-07 | 2020-10-07 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-12519 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8072 | Shenandoah | N |  | 7.2 | [13 empty] | NM | N | 30 Enphase Energy IQ7-60-x-US (240V) | 2020-06-02 | 2020-06-03 | 1 | 2020-06-03 | [8 empty] | 350 | 350 |  | 2020-06-05 | 2020-06-05 | 2020-06-19 | 2020-10-20 | 2020-10-20 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12520 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6011 | Sand Dock | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2020-06-02 | 2020-06-03 | 1 | 2020-06-03 | [14 empty] | 2020-07-01 | 2020-07-01 |  | Y
Central Hudson |  | Hudson River Renewables LLC | CH-12521 | Kingston | Saugerties | Ulster | 12477 | G | 3002 | Saugerties | Y |  | 9.6 | 9.6 | [12 empty] | NM | N | 1 Sol-Ark Sol-Ark-12K-P (240V) 1Sol-ArkSol-Ark 12K | 2020-06-12 | 2020-06-23 | 7 | 2020-06-23 | [8 empty] | 350 | 350 |  | 2020-07-01 | 2020-07-01 | 2020-09-29 | 2020-10-14 | 2020-10-14 |  | Y
Central Hudson |  | Solar Generation | CH-12524 | Kingston | High Fls | Ulster | 12440 | G | 3022 | High Falls | N |  | 4.64 | [13 empty] | NM | N | 16 Enphase Energy IQ7PLUS-72-x-US-& (240V) [SI1] 1GeneracPWRCell APKE0014 | 2020-06-16 | 2020-06-16 | 0 | 2020-06-16 | [14 empty] | 2020-09-15 | 2020-09-15 |  | Y
Central Hudson |  | Kasselman Solar | CH-12522 | Catskill | Greenvl | Greene | 12083 | G | 2061 | Freehold | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2020-06-03 | 2020-06-04 | 1 | 2020-06-04 | [14 empty] | 2020-08-18 | 2020-08-18 |  | Y
Central Hudson |  | Lighthouse Solar | CH-12523 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7061 | Milan | N |  | 8.7 | [13 empty] | NM | N | 30 Enphase Energy IQ7PLUS-72-x-US (240V) | 2020-06-04 | 2020-06-04 | 0 | 2020-06-04 | [14 empty] | 2020-11-20 | 2020-11-20 |  | Y
Central Hudson |  | Vanguard Energy Partners, LLC | CH-12527 | Catskill | Catskill |  | 12414 | G | 2001 | North Catskill | N |  | 5000 | [13 empty] | CDG | Y | 40 Chint Power Systems America CPS SCH125KTL-DO/US-600 (600V) | 2020-07-17 | 2020-07-31 | 10 | 2020-07-31 | 2020-07-31 | 2020-08-21 | 15 | 2020-09-15 | [12 empty] | 2020-11-09 | W
Central Hudson |  | SolarPlus | CH-12525 | Fishkill | Fishkill | Dutchess | 12524 | G | 8092 | Fishkill Plains | N | CH-00834 | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) [SI1] | 2020-06-05 | 2020-06-08 | 1 | 2020-06-08 | [14 empty] | 2020-07-02 | 2020-07-02 |  | Y
Central Hudson |  | PlugPV LLC | CH-12526 | Fishkill | Beacon | Dutchess | 12508 | G | 8087 | Tioronda | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000H-US (240V) | 2020-06-04 | 2020-06-08 | 2 | 2020-06-08 | [14 empty] | 2020-08-17 | 2020-08-17 |  | Y
Central Hudson |  | AEC Solar Energy Corp | CH-12533 | Poughkeepsie | Staatsburg | Dutchess | 12580 | G | 7041 | Staatsburg | N |  | 8.5 | [13 empty] | NM | N | 27 SunPower SPR-E20-327-E-AC (240V) | 2020-06-05 | 2020-06-08 | 1 | 2020-06-08 | [14 empty] | 2020-08-12 | 2020-08-12 |  | Y
Central Hudson |  | Lighthouse Solar | CH-12530 | Newburgh | New Paltz | Ulster | 12561 | G | 5031 | Galeville | Y | CH-03573 | 7.6 | 7.6 | [12 empty] | NM | N | 1 Generac Power Systems X7602 (240V) 1GeneracGenerac x7602 | 2020-06-15 | 2020-06-15 | 0 | 2020-06-15 | [14 empty] | 2021-03-11 | 2021-03-11 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-12528 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8091 | Fishkill Plains | N |  | 8.64 | [13 empty] | NM | N | 36 Enphase Energy IQ7-60-x-US (240V) | 2020-06-05 | 2020-06-08 | 1 | 2020-06-08 | [14 empty] | 2020-08-18 | 2020-08-18 |  | Y
Central Hudson |  | Sunrun Installaion Services, Inc. | CH-12531 | Kingston | Olive Brdg | Ulster | 12461 | G | 3024 | High Falls | N |  | 3.6 | [13 empty] | NM | N | 15 Enphase Energy IQ7-60-x-US (240V) | 2020-06-05 | 2020-06-08 | 1 | 2020-06-08 | [14 empty] | 2020-09-16 | 2020-09-16 |  | Y
Central Hudson |  | Lighthouse Solar | CH-12529 | Newburgh | New Paltz | Ulster | 12561 | G | 5024 | Ohioville | N |  | 17.4 | [13 empty] | NM | N | 60 Enphase Energy IQ7PLUS-72-x-US (208V) | 2020-06-08 | 2020-06-11 | 3 | 2020-06-11 | [14 empty] | 2020-08-12 | 2020-08-12 |  | Y
Central Hudson |  | American Energy Care / AEC Solar | CH-12532 | Poughkeepsie | Hyde Park |  | 12538 | G | 6074 | East Park | N |  | 25.515 | [13 empty] | NM | Y | 81 SunPower SPR-E20-327-E-AC (240V) | 2020-06-05 | 2020-06-19 | 10 | 2020-06-19 | [8 empty] | 1550 | [8 empty] | W
Central Hudson |  | MOMENTUM SOLAR | CH-12534 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8071 | Shenandoah | N |  | 3.84 | [13 empty] | NM | N | 16 Enphase Energy IQ7-60-x-US (240V) | 2020-06-05 | 2020-06-08 | 1 | 2020-06-08 | [14 empty] | 2020-11-13 | 2020-11-13 |  | Y
Central Hudson |  | Lighthouse Solar | CH-12535 | Newburgh | Highland | Ulster | 12528 | G | 5022 | Ohioville | N |  | 25 | [13 empty] | NM | N | 2 SolarEdge Technologies SE10000H-US (240V) 1 SolarEdge Technologies SE5000H-US (240V) | 2020-06-09 | 2020-06-10 | 1 | 2020-06-10 | [8 empty] | 350 | 350 |  | 2020-06-15 | 2020-06-15 | 2020-07-09 | 2020-09-21 | 2020-09-21 |  | Y
Central Hudson |  | New York State Solar Farm | CH-12536 | Kingston | Hurley | Ulster | 12443 | G | 2093 | Hurley Ave | N |  | 5.67 | [13 empty] | NM | N | 18 SunPower SPR-E19-320-E-AC (240V) | 2020-06-08 | 2020-06-18 | 8 | 2020-06-18 | [14 empty] | 2020-08-26 | 2020-08-26 |  | Y
Central Hudson |  | Sky Solar Inc. | CH-12537 | Newburgh | Montgomery |  | 12549 | G | 4026 | Coldenham | N |  | 4000 | [13 empty] | CDG | Y | 32 Sungrow Power Supply SG125HV (600V) | 2020-07-06 | 2020-07-20 | 10 | 2020-07-20 | 2020-07-20 | 2020-08-10 | 15 | [14 empty] | W
Central Hudson |  | Trinity Solar | CH-12538 | Newburgh | Newburgh | Orange | 12550 | G | 4014 | West Balmville | N |  | 3 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3000H-US (240V) | 2020-06-10 | 2020-06-10 | 0 | 2020-06-10 | [14 empty] | 2020-09-17 | 2020-09-17 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-12539 | Newburgh | New Windsor | Orange | 12553 | G | 4047 | Union Ave | N |  | 7.68 | [13 empty] | NM | N | 32 Enphase Energy IQ7-60-x-US (240V) | 2020-06-11 | 2020-06-11 | 0 | 2020-06-11 | [14 empty] | 2020-09-04 | 2020-09-04 |  | Y
Central Hudson |  | Suncommon | CH-12540 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7053 | Rhinebeck | N |  | 22.8 | [13 empty] | NM | N | 2 SolarEdge Technologies SE11400H-US (240V) | 2020-06-10 | 2020-06-19 | 7 | 2020-06-19 | [14 empty] | 2020-06-24 | 2020-06-24 |  | Y
Central Hudson |  | Kasselman Solar | CH-12541 | Poughkeepsie | Hyde Park | Dutchess | 12538 | G | 6074 | East Park | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2020-06-12 | 2020-06-12 | 0 | 2020-06-12 | [14 empty] | 2020-07-06 | 2020-07-06 |  | Y
Central Hudson |  | Lighthouse Solar | CH-12542 | Kingston | Kingston | Ulster | 12401 | G | 2016 | Lincoln Park | N |  | 6 | [13 empty] | NM | N | 1 SMA America SB6.0-1SP-US-40 (240V) [SI1] | 2020-06-15 | 2020-06-16 | 1 | 2020-06-16 | [14 empty] | 2020-07-21 | 2020-07-21 |  | Y
Central Hudson |  | Solar Generation | CH-12543 | Catskill | W Kill | Greene | 12492 | E | 2389 | Vinegar Hill | N |  | 8.8 | [13 empty] | NM | N | 1 SMA America SB5.0-1SP-US-40 (240V) [SI1] 1 SMA America SB3.8-1SP-US-40 (240V) [SI1] | 2020-06-16 | 2020-06-16 | 0 | 2020-06-16 | [14 empty] | 2020-09-04 | 2020-09-04 |  | Y
Central Hudson |  | Tesla Inc | CH-12545 | Fishkill | Garrison | Putnam | 10524 | G | 8066 | Merritt Park | Y | CH-07746 |  | 10 | [12 empty] | NM | N | 2TeslaAC Powerwall 2.0 | 2020-06-16 | 2020-06-22 | 4 | 2020-06-22 | [14 empty] | 2020-12-03 | 2020-12-03 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12546 | Poughkeepsie | Milan | Dutchess | 12571 | G | 7061 | Milan | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2020-06-16 | 2020-06-18 | 2 | 2020-06-18 | [14 empty] | 2020-07-09 | 2020-07-09 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12544 | Newburgh | New Windsor | Orange | 12553 | G | 4094 | Bethlehem Rd | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2020-06-16 | 2020-06-16 | 0 | 2020-06-16 | [14 empty] | 2020-06-23 | 2020-06-23 |  | Y
Central Hudson |  | Tesla | CH-12548 | Fishkill | Wappingrs Fls |  | 12590 | G | 8023 | Knapps Corners | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) [SI1] | 2020-06-17 | 2020-06-22 | 3 | 2020-06-22 | [17 empty] | W
Central Hudson |  | Infinity Solar Systems | CH-12547 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 6.24 | [13 empty] | NM | N | 26 Enphase Energy IQ7-60-x-US (240V) | 2020-06-17 | 2020-06-23 | 4 | 2020-06-23 | [14 empty] | 2020-10-15 | 2020-10-15 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12549 | Newburgh | Newburgh | Orange | 12550 | G | 4014 | West Balmville | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2020-06-17 | 2020-06-22 | 3 | 2020-06-22 | [14 empty] | 2020-07-14 | 2020-07-14 |  | Y
Central Hudson |  | Suncommon | CH-12550 | Catskill | Purling | Greene | 12470 | G | 2042 | South Cairo | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2020-06-18 | 2020-06-24 | 4 | 2020-06-24 | [14 empty] | 2020-08-03 | 2020-08-03 |  | Y
Central Hudson |  | Sunrun Installation Service, Inc. | CH-12552 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6044 | Spackenkill | N |  | 7.68 | [13 empty] | NM | N | 1 Delta Electronics M8-TL-US (240V) [SI1] | 2020-07-10 | 2020-07-22 | 8 | 2020-07-22 | [14 empty] | 2021-01-19 | 2021-01-19 |  | Y
Central Hudson |  | Borrego Solar Systems, Inc. | CH-12553 | Newburgh | Gardiner |  | 12561 | G | 5012 | Modena | N |  | 5000 | [13 empty] | CDG | Y | 40 Chint Power Systems America CPS SCH125KTL-DO/US-600 (600V) | 2020-08-13 | 2020-08-25 | 8 | 2020-08-25 | 2020-08-25 | 2020-09-16 | 15 | 2020-11-02 | 2020-11-20 | 2021-02-22 | 60 | 19008.68 | 4121759.85 | [7 empty] | 2021-04-16 | W
Central Hudson |  | Suncommon | CH-12551 | Poughkeepsie | Stanfordvl | Dutchess | 12581 | G | 7072 | Stanfordville | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2020-06-25 | 2020-07-07 | 7 | 2020-07-07 | [14 empty] | 2020-11-13 | 2020-11-13 |  | Y
Central Hudson |  | Suncommon | CH-12554 | Kingston | Kerhonkson | Ulster | 12446 | G | 3082 | Kerhonkson | N | CH-12554 | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2020-06-22 | 2020-07-07 | 10 | 2020-07-07 | [14 empty] | 2020-09-24 | 2020-09-24 |  | Y
Central Hudson |  | New York State Solar Farm | CH-12559 | Newburgh | Gardiner | Ulster | 12525 | G | 5031 | Galeville | N |  | 4.41 | [13 empty] | NM | N | 14 SunPower SPR-E19-320-E-AC (240V) | 2020-06-23 | 2020-07-01 | 6 | 2020-07-01 | [14 empty] | 2020-07-21 | 2020-07-21 |  | Y
Central Hudson |  | Sunrun Installaion Services, Inc. | CH-12560 | Kingston | Lk Katrine | Ulster | 12449 | G | 2011 | Lincoln Park | N |  | 4.8 | [13 empty] | NM | N | 1 Delta Electronics M5-TL-US (240V) [SI1] | 2020-07-10 | 2020-07-22 | 8 | 2020-07-22 | [14 empty] | 2020-10-13 | 2020-10-13 |  | Y
Central Hudson |  | Suncommon | CH-12556 | Kingston | Napanoch |  | 12458 | G | 3072 | Honk Falls | Y | CH-01711 | 7.6 | 5 | [12 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) 1TeslaPowerwall 2 | 2020-07-06 | 2020-07-16 | 8 | 2020-07-16 | [8 empty] | 350 | 350 |  | 2020-07-22 | 2020-07-22 | 2020-11-10 | 2020-11-17 | 2020-11-17 |  | W
Central Hudson |  | Suncommon | CH-12555 | Newburgh | Highland | Ulster | 12528 | G | 5083 | Highland | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE11400H-US (240V) | 2020-06-23 | 2020-06-25 | 2 | 2020-06-25 | [14 empty] | 2020-10-27 | 2020-10-27 |  | Y
Central Hudson |  | Kasselman Solar | CH-12558 | Poughkeepsie | Lagrangevl | Dutchess | 12540 | G | 6055 | Todd Hill | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE11400H-US (240V) | 2020-06-23 | 2020-07-01 | 6 | 2020-07-01 | [14 empty] | 2020-09-01 | 2020-09-01 |  | Y
Central Hudson |  | Kasselman Solar | CH-12557 | Kingston | Kingston | Ulster | 12401 | G | 1011 | Boulevard | N |  | 3.8 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3800H-US (240V) | 2020-06-23 | 2020-07-01 | 6 | 2020-07-01 | [14 empty] | 2020-08-17 | 2020-08-17 |  | Y
Central Hudson |  | Tesla | CH-12564 | Newburgh | New Windsor | Orange | 12553 | G | 4043 | Union Ave | Y |  | 15.2 | 20 | [12 empty] | NM | N | 2 SolarEdge Technologies SE7600H-US (240V) 4TeslaAC Powerwall 2.0 | 2020-07-02 | 2020-07-15 | 8 | 2020-07-15 | [8 empty] | 350 | 350 |  | 2020-10-16 | 2020-10-16 | 2020-11-18 | 2020-12-16 | 2020-12-16 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-12562 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8095 | Fishkill Plains | N |  | 10.8 | [13 empty] | NM | N | 45 Enphase Energy IQ7-60-x-US (240V) | 2020-07-02 | 2020-07-15 | 8 | 2020-07-15 | [14 empty] | 2020-09-29 | 2020-09-29 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-12561 | Fishkill | Beacon | Dutchess | 12508 | G | 8015 | Forgebrook | N |  | 5.76 | [13 empty] | NM | N | 24 Enphase Energy IQ7-60-x-US (240V) | 2020-06-24 | 2020-07-01 | 5 | 2020-07-01 | [14 empty] | 2020-09-14 | 2020-09-14 |  | Y
Central Hudson |  | Lighthouse Solar | CH-12563 | Newburgh | New Paltz | Ulster | 12561 | G | 5011 | Modena | N |  | 6.96 | [13 empty] | NM | N | 24 Enphase Energy IQ7PLUS-72-x-US-& (240V) [SI1] | 2020-06-24 | 2020-07-02 | 6 | 2020-07-02 | [14 empty] | 2020-09-04 | 2020-09-04 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12566 | Kingston | Grahamsvl | Sullivan | 12740 | G | 3091 | Neversink | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE 11400A-US (240V) | 2020-07-09 | 2020-07-21 | 8 | 2020-07-21 | [14 empty] | 2020-07-31 | 2020-07-31 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12575 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8096 | Fishkill Plains | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE 11400A-US (240V) | 2020-07-23 | 2020-08-04 | 8 | 2020-08-04 | [14 empty] | 2020-12-18 | 2020-12-18 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12578 | Newburgh | Newburgh | Orange | 12550 | G | 4053 | Union Ave | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000 (240V) | 2020-07-14 | 2020-07-24 | 8 | 2020-07-24 | [14 empty] | 2020-11-06 | 2020-11-06 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12574 | Poughkeepsie | Millbrook | Dutchess | 12545 | G | 7072 | Stanfordville | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000x (240V) [SI1] | 2020-07-23 | 2020-08-04 | 8 | 2020-08-04 | [17 empty] | W
Central Hudson |  | Empire Solar Solutions | CH-12573 | Poughkeepsie | Millbrook | Dutchess | 12545 | G | 7072 | Stanfordville | N |  | 3.8 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3800A-US (240V) [SI1] | 2020-07-23 | 2020-08-04 | 8 | 2020-08-04 | [17 empty] | W
Central Hudson |  | Empire Solar Solutions | CH-12570 | Kingston | Shokan | Ulster | 12481 | G | 3011 | Woodstock | N |  | 3.8 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3800A-US (240V) [SI1] | 2020-07-14 | 2020-07-27 | 9 | 2020-07-27 | [14 empty] | 2020-10-28 | 2020-10-28 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12569 | Newburgh | Newburgh | Orange | 12550 | G | 4023 | Coldenham | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600A-US (240V) | 2020-07-14 | 2020-07-24 | 8 | 2020-07-24 | [14 empty] | 2020-07-31 | 2020-07-31 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12572 | Newburgh | Newburgh | Orange | 12550 | G | 4022 | Coldenham | N |  | 15.2 | [13 empty] | NM | N | 2 SolarEdge Technologies SE7600A-US (240V) | 2020-07-14 | 2020-07-24 | 8 | 2020-07-24 | [14 empty] | 2020-08-31 | 2020-08-31 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12579 | Newburgh | Maybrook | Orange | 12543 | G | 5052 | Maybrook | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000x (240V) [SI1] | 2020-07-23 | 2020-08-04 | 8 | 2020-08-04 | [14 empty] | 2020-09-14 | 2020-09-14 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12577 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6003 | Reynolds Hill | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE 11400A-US (240V) | 2020-07-23 | 2020-08-04 | 8 | 2020-08-04 | [14 empty] | 2020-08-26 | 2020-08-26 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12571 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6043 | Spackenkill | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE 10000A-US (240V) | 2020-07-14 | 2020-07-27 | 9 | 2020-07-27 | [14 empty] | 2020-08-26 | 2020-08-26 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12576 | Fishkill | Fishkill | Dutchess | 12524 | G | 8012 | Forgebrook | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE 10000A-US (240V) | 2020-07-23 | 2020-08-04 | 8 | 2020-08-04 | [14 empty] | 2020-08-14 | 2020-08-14 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12568 | Kingston | Hurley | Ulster | 12443 | G | 2094 | Hurley Ave | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE 10000A-US (240V) | 2020-07-09 | 2020-07-22 | 9 | 2020-07-22 | [14 empty] | 2020-08-05 | 2020-08-05 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12567 | Newburgh | Marlboro | Ulster | 12542 | G | 5001 | Marlboro | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE 11400A-US (240V) | 2020-07-14 | 2020-07-24 | 8 | 2020-07-24 | [14 empty] | 2020-08-05 | 2020-08-05 |  | Y
Central Hudson |  | Sunrise Solar Solutions LLC | CH-12565 | Fishkill | Beacon | Dutchess | 12508 | G | 8085 | Tioronda | N |  | 10.88 | [13 empty] | NM | N | 34 SunPower SPR-X20-327-BLK-E-AC (240V) | 2020-06-25 | 2020-07-07 | 7 | 2020-07-07 | [14 empty] | 2020-09-21 | 2020-09-21 |  | Y
Central Hudson |  | Sunrun Installaion Services, Inc. | CH-12580 | Newburgh | Clintondale | Ulster | 12515 | G | 5012 | Modena | N |  | 16.08 | [13 empty] | NM | N | 67 Enphase Energy IQ7-60-x-US (240V) | 2020-06-26 | 2020-07-08 | 7 | 2020-07-08 | [8 empty] | 350 | 350 |  | 2020-07-31 | 2020-07-31 | 2020-08-21 | 2020-10-07 | 2020-10-07 |  | Y
Central Hudson |  | PlugPV LLC | CH-12581 | Newburgh | Marlboro | Ulster | 12542 | G | 5004 | Marlboro | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2020-07-08 | 2020-07-08 | 0 | 2020-07-08 | [14 empty] | 2020-08-05 | 2020-08-05 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12582 | Newburgh | Newburgh | Orange | 12550 | G | 4015 | West Balmville | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE 10000A-US (240V) | 2020-07-14 | 2020-07-24 | 8 | 2020-07-24 | [14 empty] | 2020-07-31 | 2020-07-31 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12583 | Kingston | Kingston | Ulster | 12401 | G | 1012 | Boulevard | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE 11400A-US (240V) | 2020-06-29 | 2020-07-09 | 7 | 2020-07-09 | [14 empty] | 2020-07-16 | 2020-07-16 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12584 | Fishkill | Beacon | Dutchess | 12508 | G | 8085 | Tioronda | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600A-US (240V) | 2020-08-04 | 2020-08-04 | 0 | 2020-08-04 | [14 empty] | 2020-08-14 | 2020-08-14 |  | Y
Central Hudson |  | Sunrun Installation Service, Inc. | CH-12587 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 5.52 | [13 empty] | NM | N | 23 Enphase Energy IQ7-60-x-US (240V) | 2020-06-29 | 2020-07-08 | 6 | 2020-07-08 | [14 empty] | 2020-09-15 | 2020-09-15 |  | Y
Central Hudson |  | Solar Generation | CH-12586 | Kingston | Saugerties | Ulster | 12477 | G | 3014 | Woodstock | N |  | 23.04 | [13 empty] | RC | Y | 3 SMA America SB7.7-1SP-US-40 (240V) | 2020-08-04 | 2020-08-13 | 7 | 2020-08-13 | [8 empty] | 350 | 350 |  | 2020-08-18 | 2020-08-18 | 2020-09-09 | 2020-09-17 | 2020-09-17 |  | Y | Y
Central Hudson |  | Sunrun Installaion Services, Inc. | CH-12588 | Kingston | Boicevl | Ulster | 12412 | G | 3011 | Woodstock | Y |  | 3.36 | 5 | [12 empty] | NM | N | 14 Enphase Energy IQ7-60-x-US (240V) 1TeslaAC Powerwall 2.0 | 2020-07-13 | 2020-07-23 | 8 | 2020-07-23 | [14 empty] | 2021-02-02 | 2021-02-02 |  | Y
Central Hudson |  | Sun Mountain | CH-12585 | Kingston | High Fls | Ulster | 12440 | G | 3022 | High Falls | N | CH-02363 | 12 | [13 empty] | NM | N | 2 SMA America SB6.0-1SP-US-41 (240V) [SI1] | 2020-08-18 | 2020-08-18 | 0 | 2020-08-18 | [14 empty] | 2020-09-24 | 2020-09-24 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-12589 | Newburgh | Wallkill | Ulster | 12589 | G | 4011 | West Balmville | N |  | 7.68 | [13 empty] | NM | N | 32 Enphase Energy IQ7-60-x-US (240V) | 2020-06-30 | 2020-07-13 | 8 | 2020-07-13 | [17 empty] | W
Central Hudson |  | Integrity Solar Solutions | CH-12591 | Newburgh | Newburgh | Orange | 12550 | G | 4022 | Coldenham | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2020-06-30 | 2020-07-13 | 8 | 2020-07-13 | [14 empty] | 2020-08-17 | 2020-08-17 |  | Y
Central Hudson |  | Gottschalk Solutions, LLC | CH-12592 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6005 | Reynolds Hill | N |  | 20 | [13 empty] | NM | N | 2 SolarEdge Technologies SE10000H-US (240V) | 2020-06-30 | 2020-07-13 | 8 | 2020-07-13 | [8 empty] | 350 | 350 |  | 2020-07-16 | 2020-07-16 | 2020-09-09 | 2020-09-14 | 2020-09-14 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12594 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8052 | North Chelsea | N |  | 22.8 | [13 empty] | NM | N | 2 SolarEdge Technologies SE11400H-US (240V) | 2020-07-13 | 2020-07-23 | 8 | 2020-07-23 | [8 empty] | 350 | 350 |  | 2020-07-27 | 2020-07-27 | 2020-09-17 | 2020-09-29 | 2020-09-29 |  | Y
Central Hudson |  | Trinity Solar | CH-12596 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2020-07-01 | 2020-07-14 | 8 | 2020-07-14 | [14 empty] | 2020-08-26 | 2020-08-26 |  | Y
Central Hudson |  | Sunrun Installaion Services, Inc. | CH-12595 | Kingston | Saugerties | Ulster | 12477 | G | 3001 | Saugerties | N |  | 7.44 | [13 empty] | NM | N | 31 Enphase Energy IQ7-60-x-US (240V) | 2020-07-28 | 2020-08-07 | 8 | 2020-08-07 | [14 empty] | 2020-09-21 | 2020-09-21 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12593 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8052 | North Chelsea | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000H-US (240V) | 2020-07-16 | 2020-07-29 | 9 | 2020-07-29 | [14 empty] | 2020-09-29 | 2020-09-29 |  | Y
Central Hudson |  | New York State Solar Farm | CH-12597 | Newburgh | Marlboro | Ulster | 12542 | G | 5003 | Marlboro | N | CH-04041 | 1.575 | [13 empty] | NM | N | 5 SunPower SPR-E20-327-E-AC (240V) | 2020-07-15 | 2020-07-27 | 8 | 2020-07-27 | [14 empty] | 2020-09-10 | 2020-09-10 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12599 | Newburgh | Marlboro | Ulster | 12542 | G | 5003 | Marlboro | N |  | 9.9 | [13 empty] | NM | N | 34 Enphase Energy IQ7PLUS-72-x-US (240V) | 2020-07-02 | 2020-07-15 | 8 | 2020-07-15 | [8 empty] | 350 | 350 |  | 2020-07-17 | 2020-07-17 | 2020-08-21 | 2020-09-10 | 2020-09-10 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12598 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8046 | Myers Corners | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2020-07-02 | 2020-07-15 | 8 | 2020-07-15 | [14 empty] | 2020-07-21 | 2020-07-21 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12600 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7013 | Hibernia | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2020-07-02 | 2020-07-15 | 8 | 2020-07-15 | [14 empty] | 2020-07-24 | 2020-07-24 |  | Y
Central Hudson |  | murphy solar and central air | CH-12601 | Catskill | Athens | Greene | 12015 | G | 1074 | Coxsackie | N |  | 9 | [13 empty] | NM | N | 1 SMA America SB9000TL-US (240V) | 2020-07-22 | 2020-07-22 | 0 | 2020-07-22 | [14 empty] | 2020-08-12 | 2020-08-12 |  | Y
Central Hudson |  | Bright Planet Solar | CH-12603 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6011 | Sand Dock | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) [SI1] | 2020-09-03 | 2020-09-09 | 3 | 2020-09-09 | [14 empty] | 2022-06-13 | 2022-06-17 |  | Y
Central Hudson |  | Tesla | CH-12602 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7041 | Staatsburg | Y |  | 7.6 | 10 | [12 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) [SI1] 2TeslaAC Powerwall 2.0 | 2020-07-06 | 2020-07-14 | 6 | 2020-07-14 | [14 empty] | 2020-09-25 | 2020-09-25 |  | Y
Central Hudson |  | AEC Solar Energy Corp | CH-12609 | Fishkill | Fishkill | Dutchess | 12524 | G | 8065 | Merritt Park | N |  | 9.45 | [13 empty] | NM | N | 30 SunPower SPR-E20-327-E-AC (240V) | 2020-07-07 | 2020-07-20 | 9 | 2020-07-20 | [14 empty] | 2020-08-14 | 2020-08-14 |  | Y
Central Hudson |  | American Energy Care / AEC Solar | CH-12608 | Poughkeepsie | Staatsburg | Dutchess | 12580 | G | 7041 | Staatsburg | N |  | 5.985 | [13 empty] | NM | N | 19 SunPower SPR-X20-327-E-AC (240V) [SI1] | 2020-07-27 | 2020-08-05 | 7 | 2020-08-05 | [14 empty] | 2020-08-14 | 2020-08-14 |  | Y
Central Hudson |  | American Energy Care / AEC Solar | CH-12604 | Kingston | Napanoch | Ulster | 12458 | G | 3072 | Honk Falls | N |  | 9.135 | [13 empty] | NM | N | 29 SunPower SPR-E20-327-E-AC (240V) [SI1] | 2020-08-03 | 2020-08-13 | 8 | 2020-08-13 | [14 empty] | 2020-09-23 | 2020-09-23 |  | Y
Central Hudson |  | C2 Energy Development, LLC | CH-12610 | Newburgh | Campbell Hall |  | 10916 | G | 5052 | Maybrook | N |  | 5000 | [13 empty] | CDG | Y | 40 Chint Power Systems America CPS SCH125KTL-DO/US-600 (600V) | 2020-09-21 | 2020-09-24 | 3 | 2020-09-24 | 2020-09-24 | 2020-10-15 | 15 | 2020-12-21 | 2021-05-05 | 2021-07-30 | 60 | 17684.01 | 3623096.85 | [7 empty] | 2021-11-15 | W
Central Hudson |  | Empire Solar Solutions | CH-12606 | Fishkill | Fishkill | Dutchess | 12524 | G | 8014 | Forgebrook | N |  | 3 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3000H-US (240V) | 2020-07-07 | 2020-07-17 | 8 | 2020-07-17 | [14 empty] | 2020-08-12 | 2020-08-12 |  | Y
Central Hudson |  | Tesla | CH-12605 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8095 | Fishkill Plains | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) [SI1] | 2020-07-07 | 2020-07-17 | 8 | 2020-07-17 | [14 empty] | 2020-11-06 | 2020-11-06 |  | Y
Central Hudson |  | Tesla | CH-12607 | Catskill | Catskill | Greene | 12414 | G | 2001 | North Catskill | Y |  | 10 | 15 | [12 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) [SI1] 3TeslaAC Powerwall 2.0 | 2020-07-07 | 2020-07-20 | 9 | 2020-07-20 | [14 empty] | 2020-12-22 | 2020-12-22 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12612 | Catskill | Cairo | Greene | 12413 | G | 2042 | South Cairo | N |  | 1.74 | [13 empty] | NM | N | 6 Enphase Energy IQ7PLUS-72-x-US (240V) | 2020-07-21 | 2020-07-21 | 0 | 2020-07-21 | [14 empty] | 2020-07-23 | 2020-07-23 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12611 | Catskill | Cairo | Greene | 12413 | G | 2042 | South Cairo | N |  | 7 | [13 empty] | NM | N | 24 Enphase Energy IQ7PLUS-72-x-US (240V) | 2020-07-21 | 2020-07-21 | 0 | 2020-07-21 | [14 empty] | 2020-07-23 | 2020-07-23 |  | Y
Central Hudson |  | Solar Generation | CH-12613 | Catskill | Prattsvl | Greene | 12468 | E | 2389 | Vinegar Hill | N |  | 5 | [13 empty] | NM | N | 1 SMA America SB5.0-1SP-US-40 (208V) [SI1] | 2020-07-08 | 2020-07-21 | 9 | 2020-07-21 | [14 empty] | 2020-08-27 | 2020-08-27 |  | Y
Central Hudson |  | Trinity Solar | CH-12615 | Newburgh | Campbell Hall | Orange | 10916 | G | 5051 | Maybrook | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE11400H-US (240V) | 2020-07-09 | 2020-07-22 | 9 | 2020-07-22 | [8 empty] | 350 | 350 |  | 2020-08-07 | 2020-08-07 | 2020-09-04 | 2020-11-17 | 2020-11-17 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-12614 | Newburgh | Highland | Ulster | 12528 | G | 5082 | Highland | N |  | 9.84 | [13 empty] | NM | N | 41 Enphase Energy IQ7-60-x-US (240V) | 2020-07-09 | 2020-07-22 | 9 | 2020-07-22 | [14 empty] | 2020-10-12 | 2020-10-12 |  | Y
Central Hudson |  | Kool Temp Heating & Cooling Inc | CH-12617 | Catskill | E Durham | Greene | 12423 | G | 2071 | Freehold | N |  | 30 | [13 empty] | NM | N | 2 Fronius USA Fronius Primo 15.0-1 (240V) | 2020-08-25 | 2020-09-09 | 10 | 2020-09-09 | [8 empty] | 1450 | 923.56 |  | 2020-09-14 | 2020-09-14 | 2020-09-18 | 2021-04-08 | 2021-04-08 | 2021-05-24 | Y
Central Hudson |  | Sunrun Installaion Services, Inc. | CH-12621 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8093 | Fishkill Plains | N |  | 13.2 | [13 empty] | NM | N | 55 Enphase Energy IQ7-60-x-US (240V) | 2020-07-13 | 2020-07-24 | 9 | 2020-07-24 | [14 empty] | 2021-05-25 | 2021-05-25 |  | Y
Central Hudson |  | Sunrun Installaion Services, Inc. | CH-12620 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6046 | Spackenkill | N |  | 6.72 | [13 empty] | NM | N | 28 Enphase Energy IQ7-60-x-US (240V) | 2020-07-13 | 2020-07-24 | 9 | 2020-07-24 | [14 empty] | 2020-09-16 | 2020-09-16 |  | Y
Central Hudson |  | Sunrun Installaion Services, Inc. | CH-12619 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7053 | Rhinebeck | N |  | 4.8 | [13 empty] | NM | N | 20 Enphase Energy IQ7-60-x-US (240V) | 2020-07-13 | 2020-07-23 | 8 | 2020-07-23 | [14 empty] | 2020-09-16 | 2020-09-16 |  | Y
Central Hudson |  | PlugPV LLC | CH-12618 | Catskill | Westerlo | Albany | 12193 | G | 1091 | Westerlo | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2020-07-13 | 2020-07-23 | 8 | 2020-07-23 | [8 empty] | 350 | 350 |  | 2020-07-29 | 2020-07-29 | 2020-08-03 | 2020-09-08 | 2020-09-08 |  | Y
Central Hudson |  | Vanguard Energy Partners, LLC | CH-12623 | Catskill | Catskill |  | 12414 | G | 2001 | North Catskill | N |  | 5000 | [13 empty] | CDG | Y | 40 Chint Power Systems America CPS SCH125KTL-DO/US-600 (600V) | 2020-11-16 | 2020-11-20 | 4 | 2020-11-20 | 2020-11-20 | 2020-12-14 | 14 | [14 empty] | W
Central Hudson |  | Empire Solar Solututions | CH-12622 | Fishkill | Fishkill | Dutchess | 12524 | G | 8055 | North Chelsea | N |  | 6.09 | [13 empty] | NM | N | 21 Enphase Energy IQ7PLUS-72-x-US (240V) | 2020-07-27 | 2020-07-27 | 0 | 2020-07-27 | [14 empty] | 2020-10-09 | 2020-10-09 |  | Y
Central Hudson |  | PlugPV LLC | CH-12626 | Fishkill | Fishkill | Dutchess | 12524 | G | 8016 | Forgebrook | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000H-US (240V) | 2020-07-28 | 2020-08-07 | 8 | 2020-08-07 | [14 empty] | 2020-08-12 | 2020-08-12 |  | Y
Central Hudson |  | Solar Generation | CH-12628 | Kingston | Hurley | Ulster | 12443 | G | 2094 | Hurley Ave | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2020-07-29 | 2020-08-10 | 8 | 2020-08-10 | [14 empty] | 2020-08-27 | 2020-08-27 |  | Y
Central Hudson |  | PlugPV LLC | CH-12624 | Catskill | Westerlo | Albany | 12193 | G | 1091 | Westerlo | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000H-US (240V) | 2020-07-15 | 2020-07-28 | 9 | 2020-07-28 | [14 empty] | 2020-08-03 | 2020-08-03 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-12625 | Newburgh | Newburgh | Orange | 12550 | G | 4022 | Coldenham | N |  | 5.52 | [13 empty] | NM | N | 23 Enphase Energy IQ7-60-x-US (240V) | 2020-07-15 | 2020-07-28 | 9 | 2020-07-28 | [14 empty] | 2020-09-29 | 2020-09-29 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12629 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8092 | Fishkill Plains | N |  | 11.6 | [13 empty] | NM | N | 40 Enphase Energy IQ7PLUS-72-x-US (240V) | 2020-07-27 | 2020-08-05 | 7 | 2020-08-05 | [14 empty] | 2020-08-27 | 2020-08-27 |  | Y
Central Hudson |  | Solar Generation | CH-12627 | Kingston | Kingston | Ulster | 12401 | G | 2013 | Lincoln Park | N |  | 7.68 | [13 empty] | NM | N | 1 SMA America SB7.7-1SP-US-40 (240V) [SI1] | 2020-07-15 | 2020-07-28 | 9 | 2020-07-28 | [14 empty] | 2020-08-27 | 2020-08-27 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12630 | Newburgh | Wallkill | Ulster | 12589 | G | 4011 | West Balmville | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2020-07-29 | 2020-08-10 | 8 | 2020-08-10 | [17 empty] | W
Central Hudson |  | Sunrun Installation Service, Inc. | CH-12639 | Newburgh | Milton | Ulster | 12547 | G | 5083 | Highland | N |  | 3.6 | [13 empty] | NM | N | 15 Enphase Energy IQ7-60-x-US (240V) | 2020-07-17 | 2020-07-29 | 8 | 2020-07-29 | [14 empty] | 2020-11-23 | 2020-11-23 |  | Y
Central Hudson |  | Kasselman Solar | CH-12631 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8052 | North Chelsea | N |  | 3.8 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3800H-US (240V) | 2020-07-17 | 2020-07-29 | 8 | 2020-07-29 | [14 empty] | 2020-08-05 | 2020-08-05 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12633 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6046 | Spackenkill | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2020-07-17 | 2020-07-29 | 8 | 2020-07-29 | [8 empty] | 350 | 350 |  | 2020-07-31 | 2020-07-31 | 2020-10-05 | 2020-10-09 | 2020-10-09 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-12634 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6002 | Reynolds Hill | N |  | 5.04 | [13 empty] | NM | N | 21 Enphase Energy IQ7-60-x-US (240V) | 2020-07-17 | 2020-07-29 | 8 | 2020-07-29 | [14 empty] | 2020-12-03 | 2020-12-03 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-12638 | Poughkeepsie | Salt Pt | Dutchess | 12578 | G | 7011 | Hibernia | N |  | 9.12 | [13 empty] | NM | N | 38 Enphase Energy IQ7-60-x-US (240V) | 2020-07-17 | 2020-07-31 | 10 | 2020-07-31 | [14 empty] | 2020-09-25 | 2020-09-25 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-12637 | Kingston | Kingston | Ulster | 12401 | G | 1024 | East Kingston | N |  | 5.28 | [13 empty] | NM | N | 22 Enphase Energy IQ7-60-x-US (240V) | 2020-07-17 | 2020-07-29 | 8 | 2020-07-29 | [14 empty] | 2020-09-23 | 2020-09-23 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-12636 | Kingston | Kingston | Ulster | 12401 | G | 2093 | Hurley Ave | N |  | 6 | [13 empty] | NM | N | 25 Enphase Energy IQ7-60-x-US (240V) | 2020-08-25 | 2020-09-01 | 5 | 2020-09-01 | [14 empty] | 2020-10-02 | 2020-10-02 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-12635 | Newburgh | Newburgh | Orange | 12550 | G | 4023 | Coldenham | Y |  | 4.8 | 5 | [12 empty] | NM | N | 20 Enphase Energy IQ7-60-x-US (240V) 1TeslaAC Powerwall 2.0 | 2020-08-25 | 2020-09-01 | 5 | 2020-09-01 | [14 empty] | 2021-11-17 | 2021-11-17 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12632 | Kingston | Saugerties | Ulster | 12477 | G | 2016 | Lincoln Park | N |  | 6.38 | [13 empty] | NM | N | 22 Enphase Energy IQ7PLUS-72-x-US (240V) | 2020-07-29 | 2020-08-10 | 8 | 2020-08-10 | [14 empty] | 2020-09-18 | 2020-09-18 |  | Y
Central Hudson |  | American Energy Care / AEC Solar | CH-12640 | Kingston | Accord | Ulster | 12404 | G | 3024 | High Falls | N |  | 15.75 | [13 empty] | NM | N | 50 Enphase Energy IQ7XS-96-x-ACM-US-y (240V) [SI1] | 2020-07-29 | 2020-08-11 | 9 | 2020-08-11 | [14 empty] | 2020-08-20 | 2020-08-20 |  | Y
Central Hudson |  | PlugPV LLC | CH-12643 | Kingston | Port Ewen | Ulster | 12466 | G | 1012 | Boulevard | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2020-07-20 | 2020-07-31 | 9 | 2020-07-31 | [14 empty] | 2020-08-18 | 2020-08-18 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12641 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6093 | Manchester | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2020-07-20 | 2020-08-03 | 10 | 2020-08-03 | [14 empty] | 2020-08-06 | 2020-08-06 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-12645 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6046 | Spackenkill | Y |  | 7.2 | 5 | [12 empty] | NM | N | 30 Enphase Energy IQ7-60-x-US (240V) 1TeslaAC Powerwall 2.0 | 2020-08-25 | 2020-09-01 | 5 | 2020-09-01 | [14 empty] | 2021-01-19 | 2021-01-19 |  | Y
Central Hudson |  | New York State Solar Farm | CH-12646 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 7024 | Tinkertown | N |  | 21.42 | [13 empty] | NM | N | 22 SunPower SPR-E19-320-E-AC (240V) 26 SunPower SPR-E19-320-E-AC (240V) 9 SunPower SPR-E19-320-BLK-E-AC (240V) [SI1] 6 SunPower SPR-E19-320-E-AC (240V) 5 SunPower SPR-E19-320-E-AC (240V) | 2020-07-20 | 2020-07-31 | 9 | 2020-07-31 | [14 empty] | 2020-08-14 | 2020-08-14 |  | Y
Central Hudson |  | Solar Generation | CH-12642 | Kingston | Woodstock | Ulster | 12498 | G | 3014 | Woodstock | N |  | 14 | [13 empty] | NM | N | 2 SMA America SB7.0-1SP-US-40 (240V) | 2020-07-20 | 2020-07-31 | 9 | 2020-07-31 | [8 empty] | 350 | 350 |  | 2020-08-04 | 2020-08-04 | 2020-10-09 | 2020-11-13 | 2020-11-13 |  | Y |  | 10/12/2020- CH Rep not able to access meter. Customer to contact CH when ready for net meter install.
Central Hudson |  | Empire Solar Solutions | CH-12648 | Poughkeepsie | Ancramdale | Columbia | 12503 | G | 7085 | Ancram | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE11400H-US (240V) | 2020-07-20 | 2020-07-31 | 9 | 2020-07-31 | [8 empty] | 350 | 350 |  | 2020-08-04 | 2020-08-04 | 2020-09-28 | 2020-09-29 | 2020-09-29 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12647 | Poughkeepsie | Ancramdale | Columbia | 12503 | G | 7085 | Ancram | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE11400H-US (240V) | 2020-07-20 | 2020-07-31 | 9 | 2020-07-31 | [14 empty] | 2020-09-29 | 2020-09-29 |  | Y
Central Hudson |  | Trinity Solar | CH-12644 | Newburgh | New Windsor | Orange | 12553 | G | 4094 | Bethlehem Rd | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2020-07-20 | 2020-07-31 | 9 | 2020-07-31 | [14 empty] | 2020-08-31 | 2020-08-31 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12651 | Newburgh | Newburgh | Orange | 12550 | G | 5004 | Marlboro | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2020-08-03 | 2020-08-12 | 7 | 2020-08-12 | [14 empty] | 2020-09-08 | 2020-09-08 |  | Y
Central Hudson |  | New York State Solar Farm | CH-12652 | Newburgh | Wallkill | Ulster | 12589 | G | 5033 | Galeville | N |  | 14.658 | [13 empty] | NM | N | 42 SunPower SPR-A415-G-AC (240V) [SI1] | 2020-07-21 | 2020-07-31 | 8 | 2020-07-31 | [14 empty] | 2020-08-19 | 2020-08-19 |  | Y
Central Hudson |  | PlugPV LLC | CH-12650 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8024 | Knapps Corners | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2020-07-21 | 2020-07-31 | 8 | 2020-07-31 | [14 empty] | 2020-09-29 | 2020-09-29 |  | Y
Central Hudson |  | New York State Solar Farm | CH-12649 | Catskill | Purling | Greene | 12470 | G | 2041 | South Cairo | N |  | 12.915 | [13 empty] | NM | N | 41 SunPower SPR-E20-327-E-AC (240V) | 2020-08-03 | 2020-08-11 | 6 | 2020-08-11 | [14 empty] | 2020-08-14 | 2020-08-14 |  | Y
Central Hudson |  | Suncommon | CH-12654 | Poughkeepsie | Pine Plains | Dutchess | 12546 | G | 7092 | Pulvers Corners | N |  | 15.2 | [13 empty] | NM | N | 2 SolarEdge Technologies SE7600H-US (240V) | 2020-07-21 | 2020-08-03 | 9 | 2020-08-03 | [14 empty] | 2020-09-10 | 2020-09-10 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-12653 | Newburgh | Campbell Hall | Orange | 10916 | G | 5052 | Maybrook | N |  | 5.76 | [13 empty] | NM | N | 24 Enphase Energy IQ7-60-x-US (240V) | 2020-07-21 | 2020-08-03 | 9 | 2020-08-03 | [14 empty] | 2020-12-23 | 2020-12-23 |  | Y
Central Hudson |  | Hudson River Renewables LLC | CH-12656 | Poughkeepsie | Staatsburg | Dutchess | 12580 | G | 7011 | Hibernia | N |  | 15.08 | [13 empty] | NM | N | 52 Enphase Energy IQ7PLUS-72-x-US (240V) | 2020-07-22 | 2020-08-03 | 8 | 2020-08-03 | [14 empty] | 2020-09-16 | 2020-09-16 |  | Y
Central Hudson |  | Lighthouse Solar | CH-12657 | Newburgh | New Paltz | Ulster | 12561 | G | 5023 | Ohioville | N |  | 7.25 | [13 empty] | NM | N | 25 Enphase Energy IQ7PLUS-72-x-US (240V) | 2020-07-22 | 2020-08-03 | 8 | 2020-08-03 | [14 empty] | 2020-09-29 | 2020-09-29 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12659 | Kingston | Hurley | Ulster | 12443 | G | 2093 | Hurley Ave | N |  | 10.44 | [13 empty] | NM | N | 36 Enphase Energy IQ7PLUS-72-x-US (240V) | 2020-07-23 | 2020-08-03 | 7 | 2020-08-03 | [14 empty] | 2020-09-15 | 2020-09-15 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12658 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8071 | Shenandoah | N |  | 11.6 | [13 empty] | NM | N | 40 Enphase Energy IQ7PLUS-72-x-US (240V) | 2020-07-23 | 2020-08-04 | 8 | 2020-08-04 | [8 empty] | 350 | 350 |  | 2020-08-07 | 2020-08-07 | 2020-10-06 | 2020-10-20 | 2020-10-20 |  | Y
Central Hudson |  | New York State Solar Farm | CH-12660 | Newburgh | New Paltz | Ulster | 12561 | G | 5031 | Galeville | N | CH-02606 | 3.15 | [13 empty] | NM | N | 10 SunPower SPR-X22-360-E-AC (240V) | 2020-08-17 | 2020-08-26 | 7 | 2020-08-26 | [14 empty] | 2020-08-27 | 2020-08-27 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12662 | Newburgh | Highland |  | 12528 | G | 5081 | Highland | N |  | 6.67 | [13 empty] | NM | N | 23 Enphase Energy IQ7PLUS-72-x-US (240V) | 2020-08-05 | 2020-08-14 | 7 | 2020-08-14 | [17 empty] | W
Central Hudson |  | Kasselman Solar | CH-12661 | Kingston | Accord | Ulster | 12404 | G | 3081 | Kerhonkson | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2020-08-05 | 2020-08-14 | 7 | 2020-08-14 | [14 empty] | 2020-10-06 | 2020-10-06 |  | Y
Central Hudson |  | Suncommon | CH-12663 | Newburgh | Gardiner | Ulster | 12525 | G | 5034 | Galeville | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2020-08-05 | 2020-08-19 | 10 | 2020-08-19 | [14 empty] | 2021-01-15 | 2021-01-15 |  | Y
Central Hudson |  | New York State Solar Farm | CH-12664 | Newburgh | Montgomery | Orange | 12549 | G | 5073 | Montgomery | N |  | 5.04 | [13 empty] | NM | N | 16 SunPower SPR-E19-320-E-AC (240V) | 2020-08-07 | 2020-08-17 | 6 | 2020-08-17 | [14 empty] | 2021-07-16 | 2021-07-16 |  | Y
Central Hudson |  | New York State Solar Farm | CH-12666 | Newburgh | Walden | Orange | 12586 | G | 5041 | East Walden | N |  | 17.01 | [13 empty] | NM | N | 54 SunPower SPR-E20-327-E-AC (240V) | 2020-07-27 | 2020-08-05 | 7 | 2020-08-05 | [14 empty] | 2020-09-10 | 2020-09-10 |  | Y
Central Hudson |  | New York State Solar Farm | CH-12665 | Fishkill | Fishkill | Dutchess | 12524 | G | 8055 | North Chelsea | N | CH-10690 | 1.89 | [13 empty] | NM | N | 6 SunPower SPR-E20-327-E-AC (240V) | 2020-07-27 | 2020-08-05 | 7 | 2020-08-05 | [14 empty] | 2020-08-27 | 2020-08-27 |  | Y
Central Hudson |  | Sunrun Inc | CH-12672 | Fishkill | Nelsonville | Putnam | 10516 | G | 8087 | Tioronda | N |  | 6.48 | [13 empty] | NM | N | 27 Enphase Energy IQ7-60-x-US (240V) | 2020-07-27 | 2020-08-06 | 8 | 2020-08-06 | [14 empty] | 2021-01-19 | 2021-01-19 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-12671 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6061 | Inwood Ave | N |  | 5.04 | [13 empty] | NM | N | 21 Enphase Energy IQ7-60-x-US (240V) | 2020-07-27 | 2020-08-06 | 8 | 2020-08-06 | [14 empty] | 2021-01-12 | 2021-01-12 |  | Y
Central Hudson |  | PlugPV LLC | CH-12668 | Catskill | Westerlo | Albany | 12193 | G | 1091 | Westerlo | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE11400H-US (240V) | 2020-07-27 | 2020-08-05 | 7 | 2020-08-05 | [14 empty] | 2020-09-03 | 2020-09-03 |  | Y
Central Hudson |  | Kasselman Solar | CH-12669 | Catskill | W Kill |  | 12492 | E | 2389 | Vinegar Hill | N |  | 7.25 | [13 empty] | NM | N | 25 Enphase Energy IQ7PLUS-72-x-US (240V) | 2020-07-27 | 2020-08-05 | 7 | 2020-08-05 | [17 empty] | W
Central Hudson |  | Sunrun Installaion Services, Inc. | CH-12678 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6093 | Manchester | N |  | 3.84 | [13 empty] | NM | N | 16 Enphase Energy IQ7-60-x-US (240V) | 2020-07-28 | 2020-08-07 | 8 | 2020-08-07 | [14 empty] | 2021-01-08 | 2021-01-08 |  | Y
Central Hudson |  | PlugPV LLC | CH-12676 | Fishkill | Garrison | Putnam | 10524 | G | 8066 | Merritt Park | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2020-08-10 | 2020-08-18 | 6 | 2020-08-18 | [14 empty] | 2020-12-10 | 2020-12-10 |  | Y
Central Hudson |  | PlugPV LLC | CH-12673 | Catskill | Athens | Greene | 12015 | G | 2002 | North Catskill | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2020-08-10 | 2020-08-18 | 6 | 2020-08-18 | [14 empty] | 2020-09-24 | 2020-09-24 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-12674 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 4.93 | [13 empty] | NM | N | 17 Enphase Energy IQ7PLUS-72-x-US (240V) | 2020-07-28 | 2020-08-07 | 8 | 2020-08-07 | [14 empty] | 2020-09-23 | 2020-09-23 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-12677 | Kingston | Kingston | Ulster | 12401 | G | 3021 | High Falls | N |  | 3.6 | [13 empty] | NM | N | 15 Enphase Energy IQ7-60-x-US-& (240V) [SI1] | 2020-07-28 | 2020-08-07 | 8 | 2020-08-07 | [14 empty] | 2021-01-04 | 2021-01-04 |  | Y
Central Hudson |  | PlugPV LLC | CH-12675 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8091 | Fishkill Plains | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2020-07-28 | 2020-08-07 | 8 | 2020-08-07 | [14 empty] | 2020-09-03 | 2020-09-03 |  | Y
Central Hudson |  | Kasselman Solar | CH-12679 | Catskill | Athens | Greene | 12015 | G | 2002 | North Catskill | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2020-08-10 | 2020-08-18 | 6 | 2020-08-18 | [17 empty] | W
Central Hudson |  | New York State Solar Farm | CH-12682 | Kingston | W Shokan | Ulster | 12494 | G | 3011 | Woodstock | N |  | 5.04 | [13 empty] | NM | N | 16 SunPower SPR-X22-360-E-AC (240V) | 2020-07-29 | 2020-08-11 | 9 | 2020-08-11 | [14 empty] | 2020-09-01 | 2020-09-01 |  | Y
Central Hudson |  | Suncommon | CH-12680 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8056 | North Chelsea | N |  | 3.8 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3800H-US (240V) | 2020-07-29 | 2020-08-10 | 8 | 2020-08-10 | [14 empty] | 2020-09-24 | 2020-09-24 |  | Y
Central Hudson |  | Suncommon | CH-12681 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7052 | Rhinebeck | N |  | 25 | [13 empty] | NM | N | 2 SolarEdge Technologies SE10000H-US (240V) 1 SolarEdge Technologies SE5000H-US (240V) | 2020-08-12 | 2020-08-19 | 5 | 2020-08-19 | [8 empty] | 350 | 350 |  | 2020-08-27 | 2020-08-27 | 2020-11-03 | 2020-12-14 | 2020-12-14 |  | Y
Central Hudson |  | Kasselman Solar | CH-12683 | Catskill | Greenvl | Greene | 12083 | G | 2071 | Freehold | N |  | 3 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3000H-US (240V) | 2020-07-30 | 2020-08-11 | 8 | 2020-08-11 | [14 empty] | 2020-09-01 | 2020-09-01 |  | Y
Central Hudson |  | New York State Solar Farm | CH-12684 | Kingston | Bloomington | Ulster | 12411 | G | 1011 | Boulevard | Y |  | 8.82 | 10 | [12 empty] | NM | N | 28 SunPower SPR-E20-327-E-AC (240V) 2TESLATESLA POWERWALL 2 | 2020-08-11 | 2020-08-19 | 6 | 2020-08-19 | [14 empty] | 2020-10-01 | 2020-10-01 |  | Y
Central Hudson |  | New York State Solar Farm | CH-12686 | Newburgh | Gardiner | Ulster | 12525 | G | 5011 | Modena | N |  | 24.57 | [13 empty] | NM | N | 78 SunPower SPR-X21-335-E-AC (240V) | 2020-07-30 | 2020-08-11 | 8 | 2020-08-11 | [14 empty] | 2020-08-14 | 2020-08-14 |  | Y
Central Hudson |  | Kasselman Solar | CH-12690 | Newburgh | New Windsor | Orange | 12553 | G | 4045 | Union Ave | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000H-US (240V) | 2020-07-31 | 2020-08-11 | 7 | 2020-08-11 | [14 empty] | 2020-10-22 | 2020-10-22 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-12694 | Newburgh | New Windsor | Orange | 12553 | G | 4044 | Union Ave | Y |  | 2.64 | 5 | [12 empty] | NM | N | 11 Enphase Energy IQ7-60-x-US-& (240V) [SI1] 1TeslaPowerwall2AC | 2020-08-25 | 2020-09-01 | 5 | 2020-09-01 | [14 empty] | 2020-11-17 | 2020-11-17 |  | Y
Central Hudson |  | New York State Solar Farm | CH-12688 | Newburgh | Highland | Ulster | 12528 | G | 5081 | Highland | N |  | 4.41 | [13 empty] | NM | N | 14 SunPower SPR-E20-327-E-AC (240V) | 2020-07-31 | 2020-08-12 | 8 | 2020-08-12 | [14 empty] | 2020-08-20 | 2020-08-20 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-12687 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8072 | Shenandoah | N |  | 5.76 | [13 empty] | NM | N | 24 Enphase Energy IQ7-60-x-US (240V) | 2020-07-31 | 2020-08-12 | 8 | 2020-08-12 | [14 empty] | 2020-09-16 | 2020-09-16 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12689 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6068 | Inwood Ave | N |  | 14.21 | [13 empty] | NM | N | 49 Enphase Energy IQ7PLUS-72-x-US (240V) | 2020-07-31 | 2020-08-12 | 8 | 2020-08-12 | [14 empty] | 2020-08-27 | 2020-08-27 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12692 | Newburgh | Newburgh | Orange | 12550 | G | 4015 | West Balmville | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2020-07-31 | 2020-08-11 | 7 | 2020-08-11 | [14 empty] | 2020-09-23 | 2020-09-23 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12691 | Newburgh | Newburgh | Orange | 12550 | G | 4015 | West Balmville | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2020-07-31 | 2020-08-11 | 7 | 2020-08-11 | [14 empty] | 2020-09-23 | 2020-09-23 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12697 | Kingston | Kerhonkson | Ulster | 12446 | G | 3083 | Kerhonkson | N | CH-12697 | 5.8 | [13 empty] | NM | N | 20 Enphase Energy IQ7PLUS-72-x-US (240V) | 2020-08-13 | 2020-08-20 | 5 | 2020-08-20 | [14 empty] | 2020-10-15 | 2020-10-15 |  | Y
Central Hudson |  | Apex Solar Power | CH-12696 | Kingston | Kingston | Ulster | 12401 | G | 2094 | Hurley Ave | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2020-08-03 | 2020-08-12 | 7 | 2020-08-12 | [8 empty] | 350 | 350 |  | 2020-10-08 | 2020-10-08 | 2021-01-06 | 2021-04-16 | 2021-04-16 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-12701 | Newburgh | New Windsor | Orange | 12553 | G | 4093 | Bethlehem Rd | N | CH-12701 | 5.8 | [13 empty] | NM | N | 20 Enphase Energy IQ7PLUS-72-x-US-& (240V) [SI1] | 2020-08-03 | 2020-08-13 | 8 | 2020-08-13 | [14 empty] | 2020-12-03 | 2020-12-03 |  | Y
Central Hudson |  | PlugPV LLC | CH-12699 | Newburgh | New Paltz | Ulster | 12561 | G | 5024 | Ohioville | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2020-08-03 | 2020-08-12 | 7 | 2020-08-12 | [14 empty] | 2020-09-24 | 2020-09-24 |  | Y
Central Hudson |  | New York State Solar Farm | CH-12695 | Kingston | Ulster Pk | Ulster | 12487 | G | 3041 | Sturgeon Pool | N |  | 11.34 | [13 empty] | NM | N | 36 SunPower SPR-E19-320-E-AC (240V) | 2020-08-03 | 2020-08-13 | 8 | 2020-08-13 | [14 empty] | 2020-08-18 | 2020-08-24 |  | Y
Central Hudson |  | Solar Generation | CH-12700 | Kingston | Woodstock | Ulster | 12498 | G | 3014 | Woodstock | N |  | 7.6 | [13 empty] | NM | N | 1GeneracPWRCell APKE00014 | 2020-08-24 | 2020-08-31 | 5 | 2020-08-31 | [14 empty] | 2020-09-10 | 2020-09-10 |  | Y
Central Hudson |  | Tesla | CH-12698 | Newburgh | New Windsor | Orange | 12553 | G | 4094 | Bethlehem Rd | Y |  | 10 | 15 | [12 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) [SI1] 3TeslaAC Powerwall 2.0 | 2020-08-25 | 2020-09-01 | 5 | 2020-09-01 | [14 empty] | 2021-02-08 | 2021-02-08 |  | Y
Central Hudson |  | Solar Generation | CH-12702 | Poughkeepsie | Clinton Cors | Dutchess | 12514 | G | 7071 | Stanfordville | N | CH-12702 | 8.19 | [13 empty] | NM | N | 26 Enphase Energy IQ7X-96-x-US (240V) | 2020-08-14 | 2020-08-28 | 10 | 2020-08-28 | [14 empty] | 2020-09-29 | 2020-09-29 |  | Y
Central Hudson |  | PlugPV LLC | CH-12703 | Newburgh | Rock Tavern | Orange | 12575 | G | 4022 | Coldenham | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2020-08-03 | 2020-08-12 | 7 | 2020-08-12 | [14 empty] | 2020-10-06 | 2020-10-06 |  | Y
Central Hudson |  | AEC Solar Energy Corp | CH-12711 | Catskill | Round Top | Greene | 12473 | G | 2042 | South Cairo | N |  | 3.78 | [13 empty] | NM | N | 12 Enphase Energy IQ7XS-96-y-ACM-z (240V) | 2020-08-13 | 2020-08-20 | 5 | 2020-08-20 | [14 empty] | 2020-09-09 | 2020-09-09 |  | Y
Central Hudson |  | Tesla | CH-12706 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6092 | Manchester | Y |  | 10 | 15 | [12 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) [SI1] 3TeslaAC Powerwall 2.0 | 2020-09-28 | 2020-09-30 | 2 | 2020-09-30 | [14 empty] | 2020-11-13 | 2020-11-13 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-12705 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6011 | Sand Dock | N |  | 4.56 | [13 empty] | NM | N | 19 Enphase Energy IQ7-60-x-US (240V) | 2020-08-04 | 2020-08-13 | 7 | 2020-08-13 | [14 empty] | 2020-10-19 | 2020-10-19 |  | Y
Central Hudson |  | Solar Generation | CH-12707 | Kingston | Bloomington | Ulster | 12411 | G | 1011 | Boulevard | N | CH-08216 | 8.82 | [13 empty] | NM | N | 28 Enphase Energy IQ7X-96-x-US (240V) | 2020-09-02 | 2020-09-09 | 4 | 2020-09-09 | [8 empty] | 350 | 350 |  | 2020-09-11 | 2020-09-11 | 2020-09-21 | 2020-10-08 | 2020-10-08 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12709 | Newburgh | Newburgh | Orange | 12550 | G | 5004 | Marlboro | N |  | 1.16 | [13 empty] | NM | N | 4 Enphase Energy IQ7PLUS-72-x-US (240V) | 2020-08-04 | 2020-08-13 | 7 | 2020-08-13 | [14 empty] | 2020-12-02 | 2020-12-02 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12710 | Newburgh | Newburgh | Orange | 12550 | G | 5004 | Marlboro | N |  | 8.12 | [13 empty] | NM | N | 28 Enphase Energy IQ7PLUS-72-x-US (240V) | 2020-08-04 | 2020-08-13 | 7 | 2020-08-13 | [8 empty] | 350 | 350 |  | 2020-10-16 | 2020-10-16 | 2020-11-24 | 2020-12-02 | 2020-12-02 |  | Y
Central Hudson |  | ETM Solar Works | CH-12712 | Catskill | Coxsackie | Greene | 12051 | G | 1074 | Coxsackie | N |  | 6 | [13 empty] | NM | N | 1 SMA America SB6.0-1SP-US-40 (240V) [SI1] | 2020-08-17 | 2020-08-26 | 7 | 2020-08-26 | [14 empty] | 2020-12-14 | 2020-12-14 |  | Y
Central Hudson |  |  | CH-12616 | Kingston | Saugerties |  | 12477 | G | 3006 | Saugerties | N |  | 5000 | [13 empty] | CDG | Y | 40 Chint Power Systems America CPS SCH125KTL-DO/US-600 (600V) | 2020-09-08 | 2020-09-15 | 5 | 2020-09-15 | 2020-09-15 | 2020-10-02 | 13 | 2020-10-22 | 2020-12-14 | 2021-03-11 | 59 | 19235.67 | 320293.4 | [7 empty] | 2021-08-23 | W
Central Hudson |  | Solar Generation | CH-12713 | Kingston | Boicevl | Ulster | 12412 | G | 3011 | Woodstock | N |  | 15.2 | [13 empty] | NM | N | 2 SolarEdge Technologies SE7600H-US (240V) | 2020-08-14 | 2020-08-26 | 8 | 2020-08-26 | [8 empty] | 350 | 350 |  | 2020-08-28 | 2020-08-28 | 2020-09-28 | 2020-10-21 | 2020-10-21 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12714 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8043 | Myers Corners | N |  | 13.92 | [13 empty] | NM | N | 48 Enphase Energy IQ7PLUS-72-x-US (240V) | 2020-08-05 | 2020-08-14 | 7 | 2020-08-14 | [14 empty] | 2020-08-19 | 2020-08-19 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12715 | Newburgh | Walden | Orange | 12586 | G | 5043 | East Walden | N |  | 5.8 | [13 empty] | NM | N | 20 Enphase Energy IQ7PLUS-72-x-US (240V) | 2020-08-05 | 2020-08-14 | 7 | 2020-08-14 | [14 empty] | 2020-08-19 | 2020-08-24 |  | Y
Central Hudson |  | Suncommon | CH-12718 | Newburgh | New Windsor | Orange | 12553 | G | 4044 | Union Ave | N |  | 3 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3000H-US (240V) | 2020-08-06 | 2020-08-14 | 6 | 2020-08-14 | [14 empty] | 2020-10-14 | 2020-10-14 |  | Y
Central Hudson |  | Suncommon | CH-12723 | Catskill | Westerlo | Albany | 12193 | G | 1092 | Westerlo | N | CH-12723 | 20 | [13 empty] | NM | N | 2 SolarEdge Technologies SE10000H-US (240V) | 2020-08-19 | 2020-08-27 | 6 | 2020-08-27 | [14 empty] | 2021-01-15 | 2021-01-15 |  | Y
Central Hudson |  | Suncommon | CH-12717 | Kingston | Kingston | Ulster | 12401 | G | 1014 | Boulevard | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2020-08-06 | 2020-08-17 | 7 | 2020-08-17 | [14 empty] | 2020-10-14 | 2020-10-14 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12719 | Newburgh | Marlboro | Ulster | 12542 | G | 5003 | Marlboro | N |  | 6.96 | [13 empty] | NM | N | 24 Enphase Energy IQ7PLUS-72-x-US (240V) | 2020-08-06 | 2020-08-14 | 6 | 2020-08-14 | [14 empty] | 2020-09-28 | 2020-09-28 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12716 | Newburgh | Newburgh |  | 12550 | G | 4022 | Coldenham | N |  | 8.41 | [13 empty] | NM | N | 29 Enphase Energy IQ7PLUS-72-x-US (240V) | 2020-08-06 | 2020-08-17 | 7 | 2020-08-17 | [17 empty] | W
Central Hudson |  | Empire Solar Solutions | CH-12722 | Kingston | Stone Ridge | Ulster | 12484 | G | 3024 | High Falls | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000H-US (240V) | 2020-08-17 | 2020-08-26 | 7 | 2020-08-26 | [14 empty] | 2020-10-06 | 2020-10-06 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12721 | Kingston | Stone Ridge | Ulster | 12484 | G | 3024 | High Falls | N |  | 3 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3000H-US (240V) | 2020-08-17 | 2020-08-26 | 7 | 2020-08-26 | [14 empty] | 2020-10-07 | 2020-10-07 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12720 | Fishkill | Beacon | Dutchess | 12508 | G | 8016 | Forgebrook | N |  | 4.64 | [13 empty] | NM | N | 16 Enphase Energy IQ7PLUS-72-x-US (240V) | 2020-08-06 | 2020-08-17 | 7 | 2020-08-17 | [14 empty] | 2020-08-31 | 2020-08-31 |  | Y
Central Hudson |  | Borrego Solar Systems, Inc | CH-12724 | Newburgh | New Windsor |  | 12553 | G | 4097 | Bethlehem Rd | N |  | 5000 | [13 empty] | CDG | Y | 40ChintCPS CH125KTL-DO/US 600 | 2020-09-23 | 2020-09-24 | 1 | 2020-09-24 | 2020-09-24 | 2020-10-14 | 14 | [14 empty] | W
Central Hudson |  | Empire Solar Solutions | CH-12727 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6096 | Manchester | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600A-US (240V) | 2020-08-07 | 2020-08-17 | 6 | 2020-08-17 | [14 empty] | 2020-08-26 | 2020-08-26 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12728 | Newburgh | Newburgh | Orange | 12550 | G | 4015 | West Balmville | N |  | 16 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000x (240V) [SI1] 1 SolarEdge Technologies SE 10000A-US (240V) | 2020-08-07 | 2020-08-17 | 6 | 2020-08-17 | [14 empty] | 2020-09-01 | 2020-09-01 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12734 | Kingston | Kingston | Ulster | 12401 | G | 1022 | East Kingston | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000x (240V) [SI1] | 2020-08-17 | 2020-08-17 | 0 | 2020-08-17 | [14 empty] | 2020-09-16 | 2020-09-16 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12732 | Kingston | Kingston | Ulster | 12401 | G | 1022 | East Kingston | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE 11400A-US (240V) | 2020-08-07 | 2020-08-17 | 6 | 2020-08-17 | [14 empty] | 2020-09-01 | 2020-09-01 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12731 | Kingston | Kingston | Ulster | 12401 | G | 1022 | East Kingston | N |  | 3.8 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3800A-US (240V) [SI1] | 2020-08-07 | 2020-08-17 | 6 | 2020-08-17 | [14 empty] | 2020-08-31 | 2020-09-01 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12730 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6094 | Manchester | N |  | 12 | [13 empty] | NM | N | 2 SolarEdge Technologies SE6000x (240V) [SI1] | 2020-08-07 | 2020-08-17 | 6 | 2020-08-17 | [14 empty] | 2020-09-14 | 2020-09-14 |  | Y
Central Hudson |  | PlugPV LLC | CH-12729 | Catskill | Coeymans Holw | Albany | 12046 | G | 1081 | New Baltimore | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2020-08-07 | 2020-08-17 | 6 | 2020-08-17 | [14 empty] | 2020-09-29 | 2020-09-29 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12733 | Fishkill | Beacon | Dutchess | 12508 | G | 8015 | Forgebrook | N |  | 3.48 | [13 empty] | NM | N | 12 Enphase Energy IQ7PLUS-72-x-US (240V) | 2020-08-07 | 2020-08-18 | 7 | 2020-08-18 | [14 empty] | 2020-09-03 | 2020-09-03 |  | Y
Central Hudson |  | PlugPV LLC | CH-12725 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6092 | Manchester | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000H-US (240V) | 2020-08-07 | 2020-08-17 | 6 | 2020-08-17 | [14 empty] | 2020-09-01 | 2020-09-01 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12726 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7054 | Rhinebeck | N |  | 4.06 | [13 empty] | NM | N | 14 Enphase Energy IQ7PLUS-72-x-US (240V) | 2020-08-07 | 2020-08-17 | 6 | 2020-08-17 | [14 empty] | 2020-08-26 | 2020-08-26 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12736 | Kingston | Ulster Pk | Ulster | 12487 | G | 3041 | Sturgeon Pool | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE11400H-US (240V) | 2020-08-07 | 2020-08-17 | 6 | 2020-08-17 | [8 empty] | 350 | 350 |  | 2020-08-25 | 2020-08-25 | 2020-09-21 | 2020-10-12 | 2020-10-12 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12735 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8043 | Myers Corners | N |  | 5.8 | [13 empty] | NM | N | 20 Enphase Energy IQ7PLUS-72-x-US (240V) | 2020-08-07 | 2020-08-17 | 6 | 2020-08-17 | [14 empty] | 2020-09-03 | 2020-09-03 |  | Y
Central Hudson |  | AEC Solar | CH-12745 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8091 | Fishkill Plains | N | CH-01910 | 3.15 | [13 empty] | NM | N | 10 Enphase Energy IQ7XS-96-x-ACM-US-y (240V) [SI1] | 2020-08-18 | 2020-08-27 | 7 | 2020-08-27 | [14 empty] | 2020-09-23 | 2020-09-23 |  | Y
Central Hudson |  | Sunrun Inc | CH-12742 | Fishkill | Fishkill | Dutchess | 12524 | G | 8055 | North Chelsea | N |  | 6.96 | [13 empty] | NM | N | 24 Enphase Energy IQ7PLUS-72-x-US (240V) | 2020-08-20 | 2020-08-27 | 5 | 2020-08-27 | [14 empty] | 2020-09-29 | 2020-09-29 |  | Y
Central Hudson |  | Lighthouse Solar | CH-12737 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 6051 | Todd Hill | N |  | 6.38 | [13 empty] | NM | N | 22 Enphase Energy IQ7PLUS-72-x-US (240V) | 2020-08-10 | 2020-08-18 | 6 | 2020-08-18 | [14 empty] | 2020-10-12 | 2020-10-12 |  | Y
Central Hudson |  | Suncommon | CH-12741 | Newburgh | Newburgh | Orange | 12550 | G | 4011 | West Balmville | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2020-08-10 | 2020-08-18 | 6 | 2020-08-18 | [14 empty] | 2020-12-07 | 2020-12-07 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-12743 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 6074 | East Park | N |  | 13.92 | [13 empty] | NM | N | 58 Enphase Energy IQ7-60-x-US (240V) | 2020-08-10 | 2020-08-18 | 6 | 2020-08-18 | [14 empty] | 2021-01-15 | 2021-01-15 |  | Y
Central Hudson |  | Kasselman Solar | CH-12744 | Kingston | Kingston | Ulster | 12401 | G | 1011 | Boulevard | N |  | 2.03 | [13 empty] | NM | N | 7 Enphase Energy IQ7PLUS-72-x-US (240V) | 2020-08-10 | 2020-08-18 | 6 | 2020-08-18 | [14 empty] | 2020-09-14 | 2020-09-14 |  | Y
Central Hudson |  | Suncommon | CH-12739 | Poughkeepsie | Clinton Cors | Dutchess | 12514 | G | 7013 | Hibernia | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2020-08-10 | 2020-08-18 | 6 | 2020-08-18 | [14 empty] | 2020-12-03 | 2020-12-03 |  | Y
Central Hudson |  | New York State Solar Farm | CH-12740 | Newburgh | New Windsor | Orange | 12553 | G | 4045 | Union Ave | N |  | 6.93 | [13 empty] | NM | N | 22 SunPower SPR-E19-320-E-AC (240V) | 2020-08-10 | 2020-08-18 | 6 | 2020-08-18 | [14 empty] | 2020-08-26 | 2020-08-26 |  | Y
Central Hudson |  | Suncommon | CH-12738 | Kingston | Saugerties | Ulster | 12477 | G | 3003 | Saugerties | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2020-08-10 | 2020-08-18 | 6 | 2020-08-18 | [8 empty] | 350 | 350 |  | 2020-08-20 | 2020-08-20 | 2020-09-10 | 2020-11-04 | 2020-11-04 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-12753 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6092 | Manchester | N |  | 13.2 | [13 empty] | NM | N | 55 Enphase Energy IQ7-60-x-US (240V) | 2020-08-11 | 2020-08-18 | 5 | 2020-08-18 | [14 empty] | 2020-10-09 | 2020-10-09 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-12752 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8091 | Fishkill Plains | N |  | 13.2 | [13 empty] | NM | N | 55 Enphase Energy IQ7-60-x-US (240V) | 2020-08-11 | 2020-08-18 | 5 | 2020-08-18 | [14 empty] | 2021-02-12 | 2021-02-12 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-12751 | Newburgh | Wallkill | Ulster | 12589 | G | 5013 | Modena | Y |  | 8.41 | 10 | [12 empty] | NM | N | 29 Enphase Energy IQ7PLUS-72-x-US (240V) 2TeslaPowerwall2AC | 2020-08-25 | 2020-09-01 | 5 | 2020-09-01 | [14 empty] | 2021-01-26 | 2021-01-26 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-12750 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8023 | Knapps Corners | Y |  | 12 | 10 | [12 empty] | NM | N | 50 Enphase Energy IQ7-60-x-US-& (240V) [SI1] 2TeslaPowerwall2AC | 2020-08-25 | 2020-09-01 | 5 | 2020-09-01 | [14 empty] | 2021-01-04 | 2021-01-04 |  | Y
Central Hudson |  | New York State Solar Farm | CH-12746 | Newburgh | Montgomery | Orange | 12549 | G | 5073 | Montgomery | N |  | 6.3 | [13 empty] | NM | N | 20 SunPower SPR-E19-320-E-AC (240V) | 2020-08-11 | 2020-08-18 | 5 | 2020-08-18 | [14 empty] | 2021-07-15 | 2021-07-15 |  | Y
Central Hudson |  | Suncommon | CH-12747 | Poughkeepsie | Millerton | Dutchess | 12546 | G | 7081 | Millerton | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2020-08-11 | 2020-08-18 | 5 | 2020-08-18 | [14 empty] | 2020-11-02 | 2020-11-02 |  | Y
Central Hudson |  | PlugPV LLC | CH-12749 | Kingston | Saugerties | Ulster | 12477 | G | 3002 | Saugerties | N |  | 15.2 | [13 empty] | NM | N | 2 SolarEdge Technologies SE7600H-US (240V) | 2020-08-11 | 2020-08-18 | 5 | 2020-08-18 | [14 empty] | 2020-09-21 | 2020-09-21 |  | Y
Central Hudson |  | PlugPV LLC | CH-12748 | Newburgh | Newburgh | Orange | 12550 | G | 4013 | West Balmville | N |  | 3.8 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3800H-US (240V) | 2020-08-11 | 2020-08-18 | 5 | 2020-08-18 | [14 empty] | 2020-11-02 | 2020-11-02 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12759 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6046 | Spackenkill | N |  | 12 | [13 empty] | NM | N | 2 SolarEdge Technologies SE6000x (240V) [SI1] | 2020-08-19 | 2020-08-27 | 6 | 2020-08-27 | [14 empty] | 2020-10-28 | 2020-10-28 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12760 | Poughkeepsie | Salt Pt | Dutchess | 12578 | G | 7025 | Tinkertown | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE 10000A-US (240V) | 2020-08-12 | 2020-08-19 | 5 | 2020-08-19 | [14 empty] | 2020-10-19 | 2020-10-19 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12761 | Kingston | Kingston | Ulster | 12401 | G | 1013 | Boulevard | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE 10000A-US (240V) | 2020-08-12 | 2020-08-19 | 5 | 2020-08-19 | [14 empty] | 2020-09-16 | 2020-09-16 |  | Y
Central Hudson |  | Suncommon | CH-12757 | Poughkeepsie | Lagrangevl | Dutchess | 12540 | G | 6053 | Todd Hill | N |  | 15 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) 1 SolarEdge Technologies SE5000H-US (240V) | 2020-08-12 | 2020-08-19 | 5 | 2020-08-19 | [14 empty] | 2020-12-01 | 2020-12-01 |  | Y |  | 11/18/2020 - Meter inaccessible; Customer to call when accessible. 11/30/2020 - Meter Changed.
Central Hudson |  | Suncommon | CH-12756 | Poughkeepsie | Clinton Cors | Dutchess | 12514 | G | 7013 | Hibernia | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2020-08-12 | 2020-08-19 | 5 | 2020-08-19 | [14 empty] | 2020-12-14 | 2020-12-17 |  | Y
Central Hudson |  | Suncommon | CH-12755 | Poughkeepsie | Clinton Cors | Dutchess | 12514 | G | 7013 | Hibernia | N |  | 30.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) 2 SolarEdge Technologies SE11400H-US (240V) | 2020-08-12 | 2020-08-20 | 6 | 2020-08-20 | [8 empty] | 1550 | 1140.34 |  | 2020-09-14 | 2020-09-14 | 2020-11-05 | 2020-12-31 | 2020-12-31 | 2021-01-04 | Y
Central Hudson |  | Suncommon | CH-12758 | Newburgh | Marlboro | Ulster | 12542 | G | 5003 | Marlboro | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2020-08-12 | 2020-08-19 | 5 | 2020-08-19 | [14 empty] | 2020-11-23 | 2020-11-23 |  | Y
Central Hudson |  | PlugPV LLC | CH-12754 | Kingston | Kingston | Ulster | 12401 | G | 2013 | Lincoln Park | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE11400H-US (240V) | 2020-08-12 | 2020-08-19 | 5 | 2020-08-19 | [14 empty] | 2020-10-06 | 2020-10-06 |  | Y
Central Hudson |  | AEC Solar | CH-12765 | Fishkill | Wappingers Falls | Dutchess | 12590 | G | 8051 | North Chelsea | N |  | 16.065 | [13 empty] | NM | N | 51 Enphase Energy IQ7XS-96-x-ACM-US-y (240V) [SI1] | 2020-08-20 | 2020-08-27 | 5 | 2020-08-27 | [14 empty] | 2020-09-23 | 2020-09-23 |  | Y
Central Hudson |  | Suncommon | CH-12763 | Kingston | W Hurley | Ulster | 12491 | G | 2094 | Hurley Ave | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000H-US (240V) | 2020-08-13 | 2020-08-20 | 5 | 2020-08-20 | [14 empty] | 2020-11-02 | 2020-11-02 |  | Y
Central Hudson |  | BQ Energy Development, LLC | CH-12764 | Newburgh | West Park | Ulster | 12493 | G | 5084 | Highland | N |  | 2000 | [13 empty] | CDG | Y | 19 SMA America SHP 125-US-20 (480V) 19SMA AmericaSUNNY HIGHPOWER PEAK3 125-US-20 | 2020-08-19 | 2020-09-02 | 10 | 2020-09-02 | 2020-09-02 | 2020-09-09 | 4 | 2020-09-29 | 2020-11-12 | 2021-02-04 | 55 | 3131.52 | 365322.8 | 218203.78 | 2021-02-09 | 2021-07-30 | 2021-07-30 | 2025-03-17 | 2025-04-01 | 2025-04-01 | 2025-09-11 | Y | Y
Central Hudson |  | Kasselman Solar | CH-12762 | Kingston | Ashokan | Ulster | 12481 | G | 3011 | Woodstock | N |  | 8.12 | [13 empty] | NM | N | 28 Enphase Energy IQ7PLUS-72-x-US (240V) | 2020-08-13 | 2020-08-20 | 5 | 2020-08-20 | [14 empty] | 2021-02-05 | 2021-02-05 |  | Y
Central Hudson |  | PlugPV, LLC | CH-12766 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7013 | Hibernia | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE11400H-US (240V) | 2020-08-14 | 2020-08-20 | 4 | 2020-08-20 | [14 empty] | 2020-09-25 | 2020-09-25 |  | Y
Central Hudson |  | AEC Solar Energy Corp | CH-12767 | Kingston | Lk Katrine | Ulster | 12449 | G | 1021 | East Kingston | N |  | 14.085 | [13 empty] | NM | N | 47 SunPower SPR-X20-327-E-AC (240V) | 2020-08-21 | 2020-08-31 | 6 | 2020-08-31 | [8 empty] | 350 | 350 |  | 2020-09-03 | 2020-09-03 | 2020-09-21 | 2020-10-14 | 2020-10-14 |  | Y
Central Hudson |  | 1st Light Energy Inc. | CH-12768 | Kingston | Saugerties | Ulster | 12477 | G | 3002 | Saugerties | N |  | 33.3 | [13 empty] | RC | Y | 1 SMA America STP 33-US-41 (480V) | 2020-09-18 | 2020-09-24 | 4 | 2020-09-24 | [14 empty] | 2021-05-18 | 2021-05-18 |  | Y | Y
Central Hudson |  | New York State Solar Farm | CH-12769 | Newburgh | Highland | Ulster | 12528 | G | 5081 | Highland | N |  | 4.886 | [13 empty] | NM | N | 14 SunPower SPR-A415-G-AC (240V) | 2020-08-17 | 2020-08-26 | 7 | 2020-08-26 | [14 empty] | 2020-09-03 | 2020-09-03 |  | Y
Central Hudson |  | New York State Solar Farm | CH-12771 | Kingston | Kingston | Ulster | 12401 | G | 1024 | East Kingston | N |  | 8.19 | [13 empty] | NM | N | 26 SunPower SPR-E19-320-E-AC (240V) | 2020-08-18 | 2020-08-27 | 7 | 2020-08-27 | [14 empty] | 2020-09-09 | 2020-09-09 |  | Y
Central Hudson |  | New York State Solar Farm | CH-12770 | Kingston | Olive Brdg | Ulster | 12461 | G | 3024 | High Falls | N |  | 8.19 | [13 empty] | NM | N | 26 SunPower SPR-E19-320-E-AC (240V) | 2020-08-26 | 2020-08-26 | 0 | 2020-08-26 | [14 empty] | 2020-09-03 | 2020-09-03 |  | Y
Central Hudson |  | Sunrun Inc | CH-12777 | Newburgh | New Windsor | Orange | 12553 | G | 4044 | Union Ave | N |  | 3.12 | [13 empty] | NM | N | 13 Enphase Energy IQ7-60-x-US (240V) | 2020-09-01 | 2020-09-08 | 4 | 2020-09-08 | [14 empty] | 2020-09-25 | 2020-09-25 |  | Y
Central Hudson |  | Sunrun Inc | CH-12776 | Newburgh | Newburgh | Orange | 12550 | G | 4013 | West Balmville | N |  | 4.8 | [13 empty] | NM | N | 20 Enphase Energy IQ7-60-x-US (240V) | 2020-09-01 | 2020-09-08 | 4 | 2020-09-08 | [14 empty] | 2020-12-14 | 2020-12-14 |  | Y
Central Hudson |  | Suncommon | CH-12774 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 6057 | Todd Hill | N | CH-02267 | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2020-08-28 | 2020-09-03 | 4 | 2020-09-03 | [14 empty] | 2021-01-11 | 2021-01-11 |  | Y
Central Hudson |  | Suncommon | CH-12773 | Kingston | Accord | Ulster | 12404 | G | 3081 | Kerhonkson | N | CH-12773 | 9.92 | [13 empty] | NM | N | 31 LG Electronics Solar Cell Division LG375A1C-V5 (240V) [SI1] | 2020-08-27 | 2020-09-02 | 4 | 2020-09-02 | [14 empty] | 2020-11-13 | 2020-11-13 |  | Y
Central Hudson |  | Suncommon | CH-12772 | Poughkeepsie | Staatsburg | Dutchess | 12580 | G | 7041 | Staatsburg | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2020-08-18 | 2020-08-27 | 7 | 2020-08-27 | [8 empty] | 350 | 350 |  | 2020-09-08 | 2020-09-08 | 2020-10-14 | 2021-02-12 | 2021-02-12 |  | Y
Central Hudson |  | New York State Solar Farm | CH-12780 | Newburgh | Montgomery | Orange | 12549 | G | 5073 | Montgomery | N |  | 3.465 | [13 empty] | NM | N | 11 SunPower SPR-E19-320-E-AC (240V) | 2020-08-19 | 2020-08-27 | 6 | 2020-08-27 | [14 empty] | 2021-07-16 | 2021-07-16 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-12779 | Newburgh | New Windsor | Orange | 12553 | G | 4043 | Union Ave | N |  | 8.16 | [13 empty] | NM | N | 34 Enphase Energy IQ7-60-x-US (240V) | 2020-08-19 | 2020-08-27 | 6 | 2020-08-27 | [14 empty] | 2020-12-04 | 2020-12-04 |  | Y
Central Hudson |  | New York State Solar Farm | CH-12781 | Kingston | Boicevl | Ulster | 12412 | G | 3011 | Woodstock | N |  | 5.584 | [13 empty] | NM | N | 16 SunPower SPR-A415-G-AC (240V) | 2020-08-19 | 2020-08-27 | 6 | 2020-08-27 | [14 empty] | 2020-09-10 | 2020-09-10 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-12778 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6001 | Reynolds Hill | N |  | 12 | [13 empty] | NM | N | 50 Enphase Energy IQ7-60-x-US (240V) | 2020-08-19 | 2020-08-27 | 6 | 2020-08-27 | [14 empty] | 2021-04-12 | 2021-04-12 |  | Y
Central Hudson |  | AEC Solar Energy Corp | CH-12782 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 6074 | East Park | N |  | 23.94 | [13 empty] | NM | N | 76 SunPower SPR-E20-327-E-AC (240V) | 2020-08-27 | 2020-09-02 | 4 | 2020-09-02 | [8 empty] | 350 | 350 |  | 2020-09-10 | 2020-09-10 | 2020-11-09 | 2020-12-23 | 2020-12-23 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12783 | Newburgh | Cornwall | Orange | 12518 | G | 4043 | Union Ave | N |  | 10.44 | [13 empty] | NM | N | 36 Enphase Energy IQ7PLUS-72-x-US (240V) | 2020-08-20 | 2020-08-27 | 5 | 2020-08-27 | [14 empty] | 2020-11-02 | 2020-11-02 |  | Y
Central Hudson |  | New York State Solar Farm | CH-12784 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6042 | Spackenkill | N |  | 10.121 | [13 empty] | NM | N | 29 SunPower SPR-A415-G-AC (240V) | 2020-08-20 | 2020-08-28 | 6 | 2020-08-28 | [14 empty] | 2020-09-23 | 2020-09-23 |  | Y
Central Hudson |  | New York State Solar Farm | CH-12785 | Newburgh | Highland | Ulster | 12528 | G | 5084 | Highland | N |  | 8.725 | [13 empty] | NM | N | 25 SunPower SPR-A415-G-AC (240V) | 2020-08-20 | 2020-08-28 | 6 | 2020-08-28 | [14 empty] | 2020-10-01 | 2020-10-01 |  | Y
Central Hudson |  | Kasselman Solar | CH-12787 | Poughkeepsie | Lagrangevl | Dutchess | 12540 | G | 6053 | Todd Hill | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE11400H-US (240V) | 2020-08-21 | 2020-08-31 | 6 | 2020-08-31 | [8 empty] | 350 | 350 |  | 2020-09-02 | 2020-09-02 | 2020-10-14 | 2020-12-03 | 2020-12-03 |  | Y
Central Hudson |  | Sunrun Installation Service, Inc. | CH-12786 | Catskill | Tannersvl | Greene | 12485 | G | 2385 | Lawrenceville | N |  | 23.1 | [13 empty] | NM | N | 2 Delta Electronics M10-TL-US (240V) [SI1] 1 Delta Electronics M4-TL-US (240V) [SI1] | 2020-10-07 | 2020-10-08 | 1 | 2020-10-08 | [8 empty] | 350 | 350 |  | 2020-10-26 | 2020-10-26 | 2020-12-29 | 2021-02-12 | 2021-02-12 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-12791 | Newburgh | Wallkill | Ulster | 12589 | G | 5013 | Modena | N |  | 7.68 | [13 empty] | NM | N | 1 Delta Electronics M8-TL-US (240V) [SI1] | 2020-08-24 | 2020-08-31 | 5 | 2020-08-31 | [14 empty] | 2020-10-07 | 2020-10-07 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12789 | Newburgh | Newburgh |  | 12550 | G | 4012 | West Balmville | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2020-08-24 | 2020-08-31 | 5 | 2020-08-31 | [17 empty] | W
Central Hudson |  | New York State Solar Farm | CH-12788 | Kingston | Grahamsvl | Sullivan | 12740 | G | 3091 | Neversink | N |  | 4.725 | [13 empty] | NM | N | 15 SunPower SPR-E19-320-E-AC (240V) | 2020-08-24 | 2020-08-31 | 5 | 2020-08-31 | [14 empty] | 2020-09-14 | 2020-09-14 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12790 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 7041 | Staatsburg | N |  | 8.12 | [13 empty] | NM | N | 28 Enphase Energy IQ7PLUS-72-x-US (240V) | 2020-08-24 | 2020-08-31 | 5 | 2020-08-31 | [14 empty] | 2020-09-14 | 2020-09-14 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12792 | Fishkill | Wappingrs Fls |  | 12590 | G | 8014 | Forgebrook | N |  | 3.48 | [13 empty] | NM | N | 12 Enphase Energy IQ7PLUS-72-x-US (208V) | 2020-08-25 | 2020-08-31 | 4 | 2020-08-31 | [17 empty] | W
Central Hudson |  | Empire Solar Solutions | CH-12793 | Newburgh | Cornwall-Hdsn | Orange | 12520 | G | 4043 | Union Ave | N |  | 6.38 | [13 empty] | NM | N | 22 Enphase Energy IQ7PLUS-72-x-US (240V) | 2020-08-25 | 2020-09-01 | 5 | 2020-09-01 | [14 empty] | 2020-10-07 | 2020-10-07 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12794 | Newburgh | New Windsor | Orange | 12553 | G | 4046 | Union Ave | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE 10000A-US (240V) | 2020-08-25 | 2020-08-31 | 4 | 2020-08-31 | [14 empty] | 2020-09-14 | 2020-09-14 |  | Y
Central Hudson |  | PlugPV LLC | CH-12798 | Kingston | Kingston | Ulster | 12401 | G | 2092 | Hurley Ave | N |  | 3.8 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3800H-US (240V) [SI1] | 2020-08-26 | 2020-09-02 | 5 | 2020-09-02 | [14 empty] | 2020-10-08 | 2020-10-08 |  | Y
Central Hudson |  | Solar Generation | CH-12796 | Kingston | W Hurley | Ulster | 12491 | G | 2094 | Hurley Ave | N |  | 7.6 | [13 empty] | NM | N | 2 SMA America SB3.8-1SP-US-40 (240V) [SI1] | 2020-09-02 | 2020-09-09 | 4 | 2020-09-09 | [14 empty] | 2020-11-16 | 2020-11-16 |  | Y
Central Hudson |  | Suncommon | CH-12797 | Poughkeepsie | Lagrangevl | Dutchess | 12540 | G | 6055 | Todd Hill | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE11400H-US (240V) | 2020-08-26 | 2020-09-01 | 4 | 2020-09-01 | [14 empty] | 2020-10-28 | 2020-10-28 |  | Y
Central Hudson |  | Solar Generation | CH-12795 | Newburgh | Gardiner | Ulster | 12525 | G | 5034 | Galeville | N |  | 10.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3000H-US (240V) 1 Generac Power Systems X7602 (240V) | 2020-09-09 | 2020-09-09 | 0 | 2020-09-09 | [14 empty] | 2020-09-25 | 2020-09-25 |  | Y
Central Hudson |  | Borrego Solar Systems, Inc | CH-12799 | Newburgh | Plattekill |  | 12589 | G | 5013 | Modena | N |  | 4000 | [13 empty] | CDG | Y | 2 Power Electronics FS2125K (600V) [SI1] 40ChintCPS SCH125KTL-DO/US-600 | 2020-09-23 | 2020-09-24 | 1 | 2020-09-24 | 2020-09-24 | 2020-10-15 | 15 | 2020-12-28 | 2021-05-17 | 2021-08-11 | 60 | 20158.23 | 5781252.4 | [7 empty] | 2022-02-25 | W
Central Hudson |  | Borrego Solar Systems, Inc | CH-12800 | Newburgh | Plattekill |  | 12589 | G | 5013 | Modena | N |  | 5000 | [13 empty] | CDG | Y | 40ChintCPS SCH125KTL-DO/US-600 | 2020-09-23 | 2020-09-24 | 1 | 2020-09-24 | 2020-09-24 | 2020-10-15 | 15 | [14 empty] | W
Central Hudson |  | New York State Solar Farm | CH-12801 | Kingston | Woodstock | Ulster | 12498 | G | 3012 | Woodstock | N |  | 7.56 | [13 empty] | NM | N | 24 SunPower SPR-X21-335-BLK-E-AC (240V) | 2020-08-27 | 2020-09-02 | 4 | 2020-09-02 | [14 empty] | 2021-01-04 | 2021-01-04 |  | Y
Central Hudson |  | AEC Solar Energy Corp. | CH-12802 | Kingston | Kingston | Ulster | 12401 | G | 2094 | Hurley Ave | N | CH-09098 | 7.56 | [13 empty] | NM | N | 24 SunPower SPR-E20-327-E-AC (208V) | 2020-09-02 | 2020-09-09 | 4 | 2020-09-09 | [8 empty] | 350 | 350 |  | 2020-09-29 | 2020-09-29 | 2020-10-21 | 2020-11-20 | 2020-11-20 |  | Y
Central Hudson |  | Lighthouse Solar | CH-12804 | Newburgh | Gardiner | Ulster | 12525 | G | 5031 | Galeville | N |  | 11.6 | [13 empty] | NM | N | 40 Enphase Energy IQ7PLUS-72-x-US (240V) | 2020-08-28 | 2020-09-03 | 4 | 2020-09-03 | [14 empty] | 2021-01-06 | 2021-01-06 |  | Y
Central Hudson |  | PlugPV, LLC | CH-12805 | Newburgh | Milton | Ulster | 12547 | G | 5003 | Marlboro | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE11400H-US (240V) | 2020-08-28 | 2020-09-03 | 4 | 2020-09-03 | [14 empty] | 2020-10-23 | 2020-10-23 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-12807 | Kingston | Kingston |  | 12401 | G | 1021 | East Kingston | N |  | 6.24 | [13 empty] | NM | N | 26 Enphase Energy IQ7-60-x-US (240V) | 2020-08-28 | 2020-09-03 | 4 | 2020-09-03 | [17 empty] | W
Central Hudson |  | Lighthouse Solar | CH-12803 | Fishkill | Fishkill | Dutchess | 12524 | G | 8055 | North Chelsea | N |  | 8.99 | [13 empty] | NM | N | 31 Enphase Energy IQ7PLUS-72-x-ACM-US (240V) | 2020-08-28 | 2020-09-03 | 4 | 2020-09-03 | [14 empty] | 2020-10-29 | 2020-10-29 |  | Y
Central Hudson |  | Borrego Solar Systems, Inc | CH-12806 | Newburgh | New Paltz |  | 12561 | G | 5024 | Ohioville | N |  | 5000 | [13 empty] | CDG | Y | 40ChintCPS SCH125KTL-DO/US-600 | 2020-09-25 | 2020-09-29 | 2 | 2020-09-29 | 2020-09-29 | 2020-10-19 | 14 | 2020-11-30 | [12 empty] | 2021-03-26 | W
Central Hudson |  | New York State Solar Farm | CH-12808 | Kingston | Saugerties | Ulster | 12477 | G | 2015 | Lincoln Park | N | CH-00366 | 7 | [13 empty] | NM | N | 1 SMA America SB7000TL-US (240V) | 2020-09-08 | 2020-09-11 | 3 | 2020-09-11 | [14 empty] | 2020-09-28 | 2020-09-28 |  | Y
Central Hudson |  | PlugPV LLC | CH-12810 | Kingston | Saugerties | Ulster | 12477 | G | 2015 | Lincoln Park | N | CH-12810 | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000H-US (240V) | 2020-08-31 | 2020-09-04 | 4 | 2020-09-04 | [14 empty] | 2020-10-29 | 2020-10-29 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12809 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 9.86 | [13 empty] | NM | N | 34 Enphase Energy IQ7PLUS-72-x-US (240V) | 2020-08-31 | 2020-09-04 | 4 | 2020-09-04 | [14 empty] | 2020-09-25 | 2020-09-25 |  | Y
Central Hudson |  | W4 Construction Group LLC. | CH-12811 | Newburgh | New Windsor | Orange | 12553 | G | 4091 | Bethlehem Rd | N | CH-08855 | 82 | [13 empty] | NM | N | 1 Yaskawa Solectria Solar PVI 82 kW-480 (480V) | 2021-11-24 | 2021-12-03 | 5 | 2021-12-03 | 2021-12-03 | 2021-12-27 | 14 | [14 empty] | W
Central Hudson |  | Gottschalk Solutions | CH-12813 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8096 | Fishkill Plains | Y |  | 11.4 | 11.4 | [12 empty] | NM | N | 1 SolarEdge Technologies SE7600A-US (240V) 1 SolarEdge Technologies SE3800A-US (240V) [SI1] 1Solar Edge StoredgeSE7600A-US | 2020-09-28 | 2020-09-30 | 2 | 2020-09-30 | [14 empty] | 2020-10-02 | 2020-10-02 |  | Y
Central Hudson |  | Suncommon | CH-12814 | Poughkeepsie | Lagrangevl | Dutchess | 12540 | G | 6055 | Todd Hill | Y | CH-03033 |  | 5 | [12 empty] | NM | N | 1TeslaPowerwall 2 | 2020-09-08 | 2020-09-11 | 3 | 2020-09-11 | [14 empty] | 2020-12-03 | 2020-12-03 |  | Y
Central Hudson |  | Integrity Solar Solutions | CH-12815 | Newburgh | Washingtonvl | Orange | 10992 | G | 4097 | Bethlehem Rd | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2020-09-02 | 2020-09-09 | 4 | 2020-09-09 | [8 empty] | 350 | 350 |  | 2020-10-08 | 2020-10-08 | 2020-11-16 | 2020-11-20 | 2020-11-20 |  | Y
Central Hudson |  | ReneSolar Power Holdings LLC | CH-12816 | Catskill | Cairo | Greene | 12413 | G | 2043 | South Cairo | N |  | 1900 | [13 empty] | CDG | Y | 16 SMA America SHP 125-US-20 (480V) 19ABBPVS-175-TL US10ABBPVS-166-TL US | 2020-10-05 | 2020-10-15 | 8 | 2020-10-15 | 2020-10-30 | 2020-11-05 | 4 | 2020-12-01 | 2021-03-19 | 2021-06-15 | 60 | 20925.06 | 342775.9 | 4295.34 | 2021-10-27 | 2022-04-20 | 2022-04-20 |  |  |  | 2022-12-22 | W | Y
Central Hudson |  | Empire Solar Solutions | CH-12818 | Fishkill | Fishkill | Dutchess | 12524 | G | 8016 | Forgebrook | N |  | 9.28 | [13 empty] | NM | N | 32 Enphase Energy IQ7PLUS-72-x-US (240V) | 2020-09-03 | 2020-09-09 | 3 | 2020-09-09 | [14 empty] | 2020-09-24 | 2020-09-24 |  | Y
Central Hudson |  | Tesla | CH-12817 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 6075 | East Park | N |  | 15.2 | [13 empty] | NM | N | 2 SolarEdge Technologies SE7600H-US (240V) | 2020-09-03 | 2020-09-09 | 3 | 2020-09-09 | [8 empty] | 350 | 350 |  | 2020-09-21 | 2020-09-21 | 2020-10-14 | 2020-10-23 | 2020-10-23 |  | Y
Central Hudson |  | Suncommon | CH-12822 | Fishkill | Garrison | Putnam | 10524 | G | 8066 | Merritt Park | N |  | 15.2 | [13 empty] | NM | N | 2 SolarEdge Technologies SE7600H-US (240V) | 2020-09-04 | 2020-09-10 | 3 | 2020-09-10 | [14 empty] | 2021-04-08 | 2021-04-08 |  | Y
Central Hudson |  | Vivint Solar Developer, LLC | CH-12821 | Newburgh | New Windsor | Orange | 12553 | G | 4095 | Bethlehem Rd | N |  | 7.2 | [13 empty] | NM | N | 30 Enphase Energy IQ7-60-x-US (240V) | 2020-09-11 | 2020-09-14 | 1 | 2020-09-14 | [14 empty] | 2021-03-01 | 2021-03-01 |  | Y
Central Hudson |  | YSG Solar | CH-12823 | Newburgh | Montgomery | Orange | 12549 | G | 5073 | Montgomery | N |  | 6 | [13 empty] | NM | N | 1 SMA America SB6.0-1SP-US-40 (240V) [SI1] | 2020-09-11 | 2020-09-14 | 1 | 2020-09-14 | [14 empty] | 2021-02-02 | 2021-02-02 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12819 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8092 | Fishkill Plains | N |  | 14.79 | [13 empty] | NM | N | 51 Enphase Energy IQ7PLUS-72-x-US (240V) | 2020-09-04 | 2020-09-10 | 3 | 2020-09-10 | [14 empty] | 2020-10-20 | 2020-10-20 |  | Y
Central Hudson |  | Solar Generation | CH-12820 | Kingston | Shokan | Ulster | 12481 | G | 3011 | Woodstock | N |  | 13.23 | [13 empty] | NM | N | 42 Enphase Energy IQ7X-96-x-US (240V) | 2020-09-04 | 2020-09-10 | 3 | 2020-09-10 | [14 empty] | 2020-10-29 | 2020-10-29 |  | Y
Central Hudson |  | Suncommon | CH-12824 | Fishkill | Garrison | Putnam | 10524 | G | 8066 | Merritt Park | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000H-US (240V) | 2020-09-04 | 2020-09-10 | 3 | 2020-09-10 | [14 empty] | 2021-03-01 | 2021-03-01 |  | Y
Central Hudson |  | Kasselman Solar | CH-12831 | Fishkill | Hopewell Jct |  | 12533 | G | 8072 | Shenandoah | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2020-09-08 | 2020-09-11 | 3 | 2020-09-11 | [17 empty] | W
Central Hudson |  | Kasselman Solar | CH-12827 | Kingston | Mt Tremper | Ulster | 12457 | G | 3012 | Woodstock | Y |  | 7.6 | 7.6 | [12 empty] | NM | N | 1 SolarEdge Technologies SE7600A-US (240V) 1SolarEdgeSE 7.6A | 2020-11-24 | 2020-12-04 | 6 | 2020-12-04 | [14 empty] | 2021-04-21 | 2021-04-21 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-12832 | Newburgh | New Windsor | Orange | 12553 | G | 4094 | Bethlehem Rd | N |  | 11.76 | [13 empty] | NM | N | 49 Enphase Energy IQ7-60-x-US (240V) | 2020-09-08 | 2020-09-11 | 3 | 2020-09-11 | [14 empty] | 2020-12-04 | 2020-12-04 |  | Y
Central Hudson |  | AEC Solar Energy Corp | CH-12826 | Newburgh | Gardiner | Ulster | 12525 | G | 5031 | Galeville | N |  | 19.53 | [13 empty] | NM | N | 62 SunPower SPR-E20-327-E-AC (240V) | 2020-09-08 | 2020-09-11 | 3 | 2020-09-11 | [17 empty] | W
Central Hudson |  | AEC Solar Energy Corp | CH-12825 | Newburgh | Walden | Orange | 12586 | G | 5043 | East Walden | N |  | 19.22 | [13 empty] | NM | N | 61 SunPower SPR-E20-327-E-AC (240V) | 2020-09-08 | 2020-09-11 | 3 | 2020-09-11 | [17 empty] | W
Central Hudson |  | AEC Solar Energy Corp | CH-12829 | Catskill | S Cairo | Greene | 12482 | G | 2005 | North Catskill | N |  | 7.68 | [13 empty] | NM | N | 22 SunPower SPR-A400-G-AC (240V) [SI1] | 2020-09-08 | 2020-09-11 | 3 | 2020-09-11 | [14 empty] | 2020-11-09 | 2020-11-09 |  | Y
Central Hudson |  | Upstate Electrical | CH-12828 | Newburgh | New Windsor | Orange | 12553 | G | 4042 | Union Ave | N |  | 30.74 | [13 empty] | NM | N | 106 Enphase Energy IQ7PLUS-72-x-US (208V) | 2020-09-24 | 2020-10-05 | 7 | 2020-10-05 | [14 empty] | 2021-09-23 | 2021-09-30 |  | Y
Central Hudson |  | Hudson Valley wind & Solar LLC | CH-12830 | Poughkeepsie | Ancram | Columbia | 12502 | G | 7091 | Pulvers Corners | N |  | 12.5 | [13 empty] | NM | N | 1 Fronius USA Fronius Primo 12.5-1 (240V) | 2020-09-08 | 2020-09-11 | 3 | 2020-09-11 | [8 empty] | 350 | 350 |  | 2020-09-25 | 2020-09-25 | 2020-11-06 | 2021-01-18 | 2021-01-18 |  | Y
Central Hudson |  | New Leaf Solar LLC | CH-12833 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8096 | Fishkill Plains | N |  | 22.8 | [13 empty] | NM | N | 2 SolarEdge Technologies SE11400H-US (240V) | 2020-09-11 | 2020-09-14 | 1 | 2020-09-14 | [8 empty] | 350 | 350 |  | 2020-09-16 | 2020-09-16 | 2020-09-23 | 2020-11-23 | 2020-11-23 |  | Y
Central Hudson |  | Sunrun Installation Service, Inc. | CH-12838 | Newburgh | Highland | Ulster | 12528 | G | 5081 | Highland | N |  | 9.36 | [13 empty] | NM | N | 39 Enphase Energy IQ7-60-x-US (240V) | 2020-09-09 | 2020-09-14 | 3 | 2020-09-14 | [14 empty] | 2020-10-30 | 2020-10-30 |  | Y
Central Hudson |  | New York State Solar Farm | CH-12840 | Kingston | Stone Ridge | Ulster | 12484 | G | 3023 | High Falls | N | CH-12840 | 5.58 | [13 empty] | NM | N | 16 SunPower SPR-A415-G-AC (240V) | 2020-09-08 | 2020-09-11 | 3 | 2020-09-11 | [14 empty] | 2021-07-23 | 2021-07-23 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-12837 | Kingston | Saugerties | Ulster | 12477 | G | 3002 | Saugerties | N |  | 17.52 | [13 empty] | NM | N | 73 Enphase Energy IQ7-60-x-US (240V) | 2020-09-09 | 2020-09-14 | 3 | 2020-09-14 | [8 empty] | 350 | 350 |  | 2020-11-03 | 2020-11-03 | 2020-12-30 | 2021-01-11 | 2021-01-11 |  | Y
Central Hudson |  | Sunrun Installation Service, Inc. | CH-12836 | Newburgh | Newburgh | Orange | 12550 | G | 4023 | Coldenham | N |  | 4.32 | [13 empty] | NM | N | 18 Enphase Energy IQ7-60-x-US (240V) | 2020-09-09 | 2020-09-15 | 4 | 2020-09-15 | [14 empty] | 2021-01-08 | 2021-01-08 |  | Y
Central Hudson |  | AEC Solar Energy Corp | CH-12834 | Poughkeepsie | Staatsburg | Dutchess | 12580 | G | 7041 | Staatsburg | N |  | 15.12 | [13 empty] | NM | N | 48 SunPower SPR-E20-327-E-AC (240V) | 2020-09-14 | 2020-09-16 | 2 | 2020-09-16 | [14 empty] | 2021-01-11 | 2021-01-11 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12835 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6092 | Manchester | N |  | 5.22 | [13 empty] | NM | N | 18 Enphase Energy IQ7PLUS-72-x-US (240V) | 2020-09-09 | 2020-09-14 | 3 | 2020-09-14 | [14 empty] | 2020-10-30 | 2020-10-30 |  | Y
Central Hudson |  | Lighthouse Solar | CH-12839 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8072 | Shenandoah | Y |  | 6.46 | 8.96 | [12 empty] | NM | N | 34Enphase EnergyIQ7PD-72-2-US28Enphase EnergyEnphase IQ8 | 2020-09-11 | 2020-09-15 | 2 | 2020-09-15 | [14 empty] | 2021-08-30 | 2021-08-30 |  | Y
Central Hudson |  | Apex Solar Power | CH-12842 | Newburgh | New Windsor | Orange | 12553 | G | 4094 | Bethlehem Rd | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2020-10-02 | 2020-10-02 | 0 | 2020-10-02 | [14 empty] | 2021-03-24 | 2021-03-24 |  | Y
Central Hudson |  | Kasselman Solar | CH-12841 | Fishkill | Fishkill | Dutchess | 12524 | G | 8014 | Forgebrook | N |  | 5.8 | [13 empty] | NM | N | 20 Enphase Energy IQ7PLUS-72-x-US (240V) | 2020-09-09 | 2020-09-14 | 3 | 2020-09-14 | [14 empty] | 2020-10-15 | 2020-10-15 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-12843 | Poughkeepsie | Poughkeepsie |  | 12603 | G | 6093 | Manchester | N |  | 10.8 | [13 empty] | NM | N | 45 Enphase Energy IQ7-60-x-US (240V) | 2020-09-10 | 2020-09-14 | 2 | 2020-09-14 | [17 empty] | W
Central Hudson |  | PlugPV LLC | CH-12848 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6011 | Sand Dock | N |  | 15.2 | [13 empty] | NM | N | 2 SolarEdge Technologies SE7600H-US (240V) | 2020-09-16 | 2020-09-17 | 1 | 2020-09-17 | [8 empty] | 350 | 350 |  | 2020-09-23 | 2020-09-23 | 2020-11-15 | 2020-12-21 | 2020-12-21 |  | Y
Central Hudson |  | AEC Solar Energy Corp | CH-12847 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8045 | Myers Corners | N |  | 9.13 | [13 empty] | NM | N | 29 SunPower SPR-E20-327-E-AC (240V) | 2020-09-11 | 2020-09-15 | 2 | 2020-09-15 | [14 empty] | 2021-02-02 | 2021-02-02 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-12844 | Poughkeepsie | Poughkeepsie |  | 12601 | G | 6064 | Inwood Ave | N |  | 5.52 | [13 empty] | NM | N | 23 Enphase Energy IQ7-60-x-US (240V) | 2020-09-11 | 2020-09-15 | 2 | 2020-09-15 | [17 empty] | W
Central Hudson |  | New York State Solar Farm | CH-12846 | Kingston | Saugerties | Ulster | 12477 | G | 3003 | Saugerties | N |  | 6.28 | [13 empty] | NM | N | 18 SunPower SPR-A415-G-AC (240V) | 2020-09-11 | 2020-09-15 | 2 | 2020-09-15 | [14 empty] | 2020-09-25 | 2020-09-25 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-12845 | Newburgh | Goshen | Orange | 10924 | G | 5051 | Maybrook | N |  | 8.7 | [13 empty] | NM | N | 30 Enphase Energy IQ7PLUS-72-x-US (240V) | 2020-09-11 | 2020-09-15 | 2 | 2020-09-15 | [14 empty] | 2021-01-07 | 2021-01-07 |  | Y
Central Hudson |  | New York State Solar Farm | CH-12850 | Kingston | Woodstock | Ulster | 12498 | G | 3014 | Woodstock | N |  | 10.08 | [13 empty] | NM | N | 32 SunPower SPR-X22-360-E-AC (240V) | 2020-09-14 | 2020-09-16 | 2 | 2020-09-16 | [14 empty] | 2020-10-12 | 2020-10-12 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-12849 | Fishkill | Fishkill | Dutchess | 12524 | G | 8012 | Forgebrook | N |  | 6.3 | [13 empty] | NM | N | 20 Enphase Energy IQ7X-96-x-US (240V) | 2020-09-14 | 2020-09-16 | 2 | 2020-09-16 | [14 empty] | 2020-12-10 | 2020-12-10 |  | Y
Central Hudson |  | New York State Solar Farm | CH-12851 | Newburgh | Montgomery | Orange | 12549 | G | 4026 | Coldenham | N |  | 4.886 | [13 empty] | NM | N | 14 SunPower SPR-A420-G-AC (240V) | 2020-09-14 | 2020-09-16 | 2 | 2020-09-16 | [14 empty] | 2020-10-14 | 2020-10-14 |  | Y
Central Hudson |  | PlugPV, LLC | CH-12854 | Newburgh | Marlboro | Ulster | 12542 | G | 5004 | Marlboro | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2020-09-15 | 2020-09-16 | 1 | 2020-09-16 | [14 empty] | 2020-12-08 | 2020-12-08 |  | Y
Central Hudson |  | Solar Generation | CH-12855 | Kingston | Kingston | Ulster | 12401 | G | 1022 | East Kingston | N |  | 6 | [13 empty] | NM | N | 1SolarEdge TechologySE6000 | 2020-09-17 | 2020-09-18 | 1 | 2020-09-18 | [14 empty] | 2020-10-28 | 2020-10-28 |  | Y
Central Hudson |  | New York State Solar Farm | CH-12853 | Fishkill | Fishkill | Dutchess | 12524 | G | 8094 | Fishkill Plains | N |  | 3.465 | [13 empty] | NM | N | 11 SunPower SPR-E20-327-E-AC (240V) | 2020-09-15 | 2020-09-22 | 5 | 2020-09-22 | [14 empty] | 2020-10-07 | 2020-10-07 |  | Y
Central Hudson |  | Kasselman Solar | CH-12852 | Catskill | Coeymans Holw | Albany | 12046 | G | 1081 | New Baltimore | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2020-09-15 | 2020-09-16 | 1 | 2020-09-16 | [14 empty] | 2020-11-20 | 2020-11-20 |  | Y
Central Hudson |  | Suncommon | CH-12858 | Kingston | Kingston | Ulster | 12401 | G | 1022 | East Kingston | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2020-09-16 | 2020-09-17 | 1 | 2020-09-17 | [14 empty] | 2020-10-23 | 2020-10-23 |  | Y
Central Hudson |  | Suncommon | CH-12859 | Kingston | Kingston | Ulster | 12401 | G | 2012 | Lincoln Park | N |  | 43.2 | [13 empty] | NM | N | 1 SolarEdge Technologies SE43.2KUS (208V) | 2020-11-03 | 2020-11-05 | 2 | 2020-11-05 | [14 empty] | 2022-08-30 | 2022-08-31 |  | Y
Central Hudson |  | Kasselman Solar | CH-12861 | Catskill | Greenvl | Greene | 12083 | G | 1091 | Westerlo | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2020-09-16 | 2020-09-17 | 1 | 2020-09-17 | [14 empty] | 2020-12-03 | 2020-12-03 |  | Y
Central Hudson |  | Suncommon | CH-12860 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6011 | Sand Dock | N | CH-02061 | 1.28 | [13 empty] | NM | N | 4 SunPower SPR-E20-327-C-AC (240V) | 2020-09-17 | 2020-09-18 | 1 | 2020-09-18 | [14 empty] | 2020-12-18 | 2020-12-18 |  | Y
Central Hudson |  | PlugPV, LLC | CH-12857 | Newburgh | Milton | Ulster | 12547 | G | 5083 | Highland | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2020-09-16 | 2020-09-17 | 1 | 2020-09-17 | [14 empty] | 2020-11-06 | 2020-11-06 |  | Y
Central Hudson |  | Lighthouse Solar | CH-12856 | Fishkill | Cold Spg | Putnam | 10516 | G | 8063 | Merritt Park | N |  | 4.64 | [13 empty] | NM | N | 16 Enphase Energy IQ7PLUS-72-x-US (240V) | 2020-09-16 | 2020-09-17 | 1 | 2020-09-17 | [14 empty] | 2021-07-23 | 2021-07-23 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-12863 | Poughkeepsie | Poughkeepsie |  | 12603 | G | 6093 | Manchester | N |  | 4.8 | [13 empty] | NM | N | 20 Enphase Energy IQ7-60-x-US (240V) | 2020-09-17 | 2020-09-18 | 1 | 2020-09-18 | [17 empty] | W
Central Hudson |  | Infinity Solar Systems | CH-12864 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6094 | Manchester | N |  | 7.2 | [13 empty] | NM | N | 30 Enphase Energy IQ7-60-x-US (240V) | 2020-09-17 | 2020-09-18 | 1 | 2020-09-18 | [14 empty] | 2021-03-09 | 2021-03-09 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-12862 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8093 | Fishkill Plains | N |  | 10.44 | [13 empty] | NM | N | 36 Enphase Energy IQ7PLUS-72-x-US (240V) | 2020-09-17 | 2020-09-18 | 1 | 2020-09-18 | [14 empty] | 2020-12-10 | 2020-12-10 |  | Y
Central Hudson |  | PlugPV, LLC | CH-12865 | Newburgh | Newburgh | Orange | 12550 | G | 4051 | Union Ave | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2020-09-18 | 2020-09-18 | 0 | 2020-09-18 | [14 empty] | 2021-03-02 | 2021-03-02 |  | Y
Central Hudson |  | Trinity Solar | CH-12868 | Newburgh | Salisbury Mls | Orange | 12577 | G | 4097 | Bethlehem Rd | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2020-09-21 | 2020-09-21 | 0 | 2020-09-21 | [14 empty] | 2020-11-25 | 2020-11-25 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12867 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8095 | Fishkill Plains | N |  | 6.67 | [13 empty] | NM | N | 23 Enphase Energy IQ7PLUS-72-x-ACM-US (240V) | 2020-09-23 | 2020-09-23 | 0 | 2020-09-23 | [14 empty] | 2020-12-08 | 2020-12-08 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12866 | Kingston | Grahamsvl |  | 12740 | G | 3091 | Neversink | N |  | 12 | [13 empty] | NM | N | 2 SolarEdge Technologies SE6000H-US (240V) | 2020-09-21 | 2020-09-22 | 1 | 2020-09-22 | [8 empty] | 350 | 350 |  | 2020-09-24 | 2020-09-24 | 2021-01-13 |  |  |  | W
Central Hudson |  | Lighthouse Solar | CH-12869 | Kingston | High Fls | Ulster | 12440 | G | 3024 | High Falls | N |  | 21.17 | [13 empty] | NM | N | 73 Enphase Energy IQ7PLUS-72-x-ACM-US (240V) | 2020-09-21 | 2020-10-02 | 9 | 2020-10-02 | [14 empty] | 2020-10-19 | 2020-10-19 |  | Y
Central Hudson |  | Lighthouse Solar | CH-12870 | Kingston | Kerhonkson | Ulster | 12446 | G | 3081 | Kerhonkson | N |  | 6.38 | [13 empty] | NM | N | 22 Enphase Energy IQ7PLUS-72-x-US (240V) | 2020-09-21 | 2020-10-02 | 9 | 2020-10-02 | [14 empty] | 2020-11-05 | 2020-11-05 |  | Y
Central Hudson |  | Lighthouse Solar | CH-12873 | Kingston | Olive Brdg | Ulster | 12461 | G | 3082 | Kerhonkson | N |  | 5.22 | [13 empty] | NM | N | 18 Enphase Energy IQ7PLUS-72-x-US (240V) | 2020-09-21 | 2020-09-22 | 1 | 2020-09-22 | [14 empty] | 2020-12-15 | 2020-12-15 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-12871 | Poughkeepsie | Wappingrs Fls | Dutchess | 12590 | G | 6052 | Todd Hill | N |  | 12.76 | [13 empty] | NM | N | 44 Enphase Energy IQ7PLUS-72-x-US (240V) | 2020-09-21 | 2020-09-21 | 0 | 2020-09-21 | [14 empty] | 2020-12-10 | 2020-12-10 |  | Y
Central Hudson |  | Autonomous Energies LLC | CH-12872 | Kingston | Ulster Pk | Ulster | 12487 | G | 1023 | East Kingston | N |  | 11.89 | [13 empty] | NM | N | 41 Enphase Energy IQ7PLUS-72-x-US (240V) | 2020-09-21 | 2020-09-22 | 1 | 2020-09-22 | [14 empty] | 2020-12-14 | 2020-12-14 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-12878 | Kingston | Kingston | Ulster | 12401 | G | 2017 | Lincoln Park | N |  | 6.24 | [13 empty] | NM | N | 26 Enphase Energy IQ7-60-x-US-& (240V) [SI1] | 2020-09-22 | 2020-09-24 | 2 | 2020-09-24 | [14 empty] | 2020-11-04 | 2020-11-04 |  | Y
Central Hudson |  | Sunrun Installation Service, Inc. | CH-12877 | Poughkeepsie | Millbrook | Dutchess | 12545 | G | 7025 | Tinkertown | Y |  | 9.6 | 5 | [12 empty] | NM | N | 40 Enphase Energy IQ7-60-x-US (240V) 1TeslaAC Powerwall 2.0 | 2020-09-22 | 2020-09-23 | 1 | 2020-09-23 | [14 empty] | 2021-01-25 | 2021-01-25 |  | Y
Central Hudson |  | Solar Generation | CH-12875 | Kingston | Glenford | Ulster | 12433 | G | 3013 | Woodstock | N |  | 3.8 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3800H-US (240V) | 2020-09-22 | 2020-09-23 | 1 | 2020-09-23 | [14 empty] | 2020-11-23 | 2020-11-23 |  | Y
Central Hudson |  | Hudson River Renewables LLC | CH-12874 | Poughkeepsie | Wassaic | Dutchess | 12592 | G | 7012 | Hibernia | N | CH-11998 | 7.68 | [13 empty] | NM | N | 1 SMA America SB7.7-1TP-US-41 (240V) [SI1] | 2020-09-22 | 2020-09-23 | 1 | 2020-09-23 | [14 empty] | 2020-11-02 | 2020-11-02 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-12879 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N | CH-04648 | 3.84 | [13 empty] | NM | N | 16 Enphase Energy IQ7-60-x-US (240V) | 2020-09-22 | 2020-09-23 | 1 | 2020-09-23 | [14 empty] | 2020-11-20 | 2020-11-20 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12881 | Kingston | Napanoch | Ulster | 12458 | G | 3071 | Honk Falls | N |  | 8.7 | [13 empty] | NM | N | 30 Enphase Energy IQ7PLUS-72-x-US (240V) | 2020-09-23 | 2020-09-24 | 1 | 2020-09-24 | [14 empty] | 2020-10-20 | 2020-10-20 |  | Y
Central Hudson |  | PlugPV, LLC | CH-12880 | Poughkeepsie | Wappingrs Fls | Dutchess | 12590 | G | 6052 | Todd Hill | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE11400H-US (240V) | 2020-09-25 | 2020-09-28 | 1 | 2020-09-28 | [14 empty] | 2020-11-09 | 2020-11-09 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12883 | Kingston | Grahamsvl | Sullivan | 12740 | G | 3091 | Neversink | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE11400H-US (240V) | 2020-09-23 | 2020-09-24 | 1 | 2020-09-24 | [14 empty] | 2021-05-03 | 2021-05-03 |  | Y
Central Hudson |  | Lighthouse Solar | CH-12884 | Newburgh | New Paltz | Ulster | 12561 | G | 5023 | Ohioville | N | CH-12884 | 6.38 | [13 empty] | NM | N | 22 Enphase Energy IQ7PLUS-72-x-US (240V) | 2020-09-24 | 2020-09-28 | 2 | 2020-09-28 | [14 empty] | 2021-03-24 | 2021-03-24 |  | Y
Central Hudson |  | Lighthouse Solar | CH-12886 | Newburgh | New Paltz | Ulster | 12561 | G | 5031 | Galeville | N |  | 24.94 | [13 empty] | NM | N | 86 Enphase Energy IQ7PLUS-72-x-US (240V) | 2020-09-25 | 2020-09-28 | 1 | 2020-09-28 | [8 empty] | 350 | 350 |  | 2020-10-02 | 2020-10-02 | 2020-10-14 | 2020-12-11 | 2020-12-11 |  | Y
Central Hudson |  | New York State Solar Farm | CH-12885 | Newburgh | New Windsor |  | 12553 | G | 4052 | Union Ave | N |  | 11.025 | [13 empty] | NM | N | 35 SunPower SPR-E20-327-E-AC (240V) | 2020-09-25 | 2020-09-28 | 1 | 2020-09-28 | [17 empty] | W
Central Hudson |  | New York State Solar Farm | CH-12888 | Kingston | Kingston | Ulster | 12401 | G | 2015 | Lincoln Park | N |  | 62.5 | [13 empty] | NM | N | 1 SMA America STP 62-US-41 (480V) | 2020-09-30 | 2020-10-05 | 3 | 2020-10-05 | [14 empty] | 2020-10-08 | 2020-10-15 |  | Y
Central Hudson |  | Lighthouse Solar | CH-12887 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 7011 | Hibernia | N |  | 10.44 | [13 empty] | NM | N | 36 Enphase Energy IQ7PLUS-72-x-US (240V) | 2020-09-25 | 2020-09-28 | 1 | 2020-09-28 | [8 empty] | 350 | 350 |  | 2020-10-02 | 2020-10-02 | 2020-10-14 | 2020-12-17 | 2020-12-17 |  | Y
Central Hudson |  | PlugPV, LLC | CH-12889 | Fishkill | Stormvl | Dutchess | 12582 | G | 8093 | Fishkill Plains | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2020-09-28 | 2020-09-29 | 1 | 2020-09-29 | [14 empty] | 2020-11-12 | 2020-11-12 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-12891 | Newburgh | New Windsor | Orange | 12553 | G | 4054 | Union Ave | N |  | 4.56 | [13 empty] | NM | N | 19 Enphase Energy IQ7-60-x-US (240V) | 2020-10-12 | 2020-10-13 | 1 | 2020-10-13 | [14 empty] | 2021-07-01 | 2021-07-01 |  | Y
Central Hudson |  | PlugPV LLC | CH-12892 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7062 | Milan | Y |  | 7.6 | 5 | [12 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) [SI1] 1TeslaAC Powerwall 2 | 2020-10-12 | 2020-10-12 | 0 | 2020-10-12 | [8 empty] | 350 | 350 |  | 2020-10-14 | 2020-10-14 | 2021-01-18 | 2021-02-23 | 2021-02-23 |  | Y
Central Hudson |  | PlugPV, LLC | CH-12893 | Fishkill | New Hamburg | Dutchess | 12590 | G | 8023 | Knapps Corners | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2020-09-30 | 2020-09-30 | 0 | 2020-09-30 | [14 empty] | 2020-12-23 | 2020-12-23 |  | Y
Central Hudson |  | Suncommon | CH-12897 | Poughkeepsie | Rhinebeck |  | 12572 | G | 7041 | Staatsburg | N |  | 20 | [13 empty] | NM | N | 2 SolarEdge Technologies SE10000H-US (240V) | 2020-10-01 | 2020-10-01 | 0 | 2020-10-01 | [8 empty] | 350 | 350 |  | 2020-10-09 | 2020-10-09 | 2021-01-15 |  |  |  | W
Central Hudson |  | Trinity Solar | CH-12900 | Fishkill | Beacon | Dutchess | 12508 | G | 8017 | Forgebrook | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000H-US (240V) | 2020-10-02 | 2020-10-06 | 2 | 2020-10-06 | [14 empty] | 2021-01-11 | 2021-01-11 |  | Y
Central Hudson |  | New York State Solar Farm | CH-12902 | Newburgh | Maybrook | Orange | 12543 | G | 5052 | Maybrook | Y |  | 5.67 | 5 | [12 empty] | NM | N | 18 SunPower SPR-E19-320-E-AC (240V) 1TESLATESLA POWERWALL 2 | 2020-10-01 | 2020-10-02 | 1 | 2020-10-02 | [14 empty] | 2020-10-14 | 2020-10-14 |  | Y
Central Hudson |  | Lighthouse Solar | CH-12894 | Newburgh | New Paltz | Ulster | 12561 | G | 5024 | Ohioville | Y |  | 7.6 | 7.6 | [12 empty] | NM | N | 1 Generac Power Systems X7602 (240V) 1Generac7.6 kW X7602 (240v) | 2020-10-01 | 2020-10-01 | 0 | 2020-10-01 | [14 empty] | 2021-01-14 | 2021-01-14 |  | Y
Central Hudson |  | Solar Generation | CH-12898 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7052 | Rhinebeck | N |  | 8.82 | [13 empty] | NM | N | 28 Enphase Energy IQ7X-96-x-US (240V) | 2020-10-01 | 2020-10-06 | 3 | 2020-10-06 | [8 empty] | 350 | 350 |  | 2020-10-08 | 2020-10-08 | 2020-11-05 | 2020-12-11 | 2020-12-11 |  | Y
Central Hudson |  | PlugPV, LLC | CH-12895 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6093 | Manchester | N | CH-12895 | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2020-10-01 | 2020-10-01 | 0 | 2020-10-01 | [14 empty] | 2020-12-04 | 2020-12-04 |  | Y
Central Hudson |  | Solar Generation | CH-12896 | Kingston | Tillson | Ulster | 12486 | G | 3022 | High Falls | N |  | 12 | [13 empty] | NM | N | 2 SolarEdge Technologies SE6000H-US (240V) | 2020-10-05 | 2020-10-06 | 1 | 2020-10-06 | [14 empty] | 2020-11-25 | 2020-11-25 |  | Y
Central Hudson |  | Solar Generation | CH-12899 | Newburgh | Marlboro | Ulster | 12542 | G | 5004 | Marlboro | N |  | 18 | [13 empty] | NM | N | 3 SMA America SB6.0-1SP-US-40 (240V) [SI1] | 2020-10-01 | 2020-10-02 | 1 | 2020-10-02 | [14 empty] | 2021-01-25 | 2021-01-25 |  | Y
Central Hudson |  | Borrego Solar Systems, Inc | CH-12903 | Catskill | Athens |  | 12015 | G | 2002 | North Catskill | N |  | 5000 | [13 empty] | CDG | Y | 40ChintCPS SCH125KTL-DO/US-600 | 2020-10-02 | 2020-10-15 | 9 | 2020-10-15 | 2020-10-30 | 2020-11-05 | 4 | 2021-02-01 | 2021-03-02 | 2021-05-26 | 60 | 12881.63 | 7698616.35 | [7 empty] | 2021-08-23 | W
Central Hudson |  | New York State Solar Farm | CH-12904 | Newburgh | Gardiner | Ulster | 12525 | G | 5031 | Galeville | Y | CH-11766 |  | 5 | [12 empty] | NM | N | 1TESLATESLA POWERWALL 2 | 2020-10-02 | 2020-10-06 | 2 | 2020-10-06 | [17 empty] | W
Central Hudson |  | Empire Solar Solutions | CH-12905 | Newburgh | Gardiner | Ulster | 12525 | G | 5011 | Modena | N |  | 8.12 | [13 empty] | NM | N | 28 Enphase Energy IQ7PLUS-72-x-US (240V) | 2020-10-02 | 2020-10-06 | 2 | 2020-10-06 | [14 empty] | 2020-10-20 | 2020-10-20 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-12906 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8043 | Myers Corners | Y |  | 7.68 | 5 | [12 empty] | NM | N | 1 Delta Electronics M8-TL-US (240V) [SI1] 1TeslaAC Powerwall 2.0 | 2020-10-16 | 2020-10-20 | 2 | 2020-10-20 | [14 empty] | 2021-01-11 | 2021-01-11 |  | Y
Central Hudson |  | Solar Generation | CH-12908 | Kingston | Saugerties |  | 12477 | G | 3004 | Saugerties | N |  | 250 | [13 empty] | RNM | Y | 2 SMA America SHP 125-US-20 (480V) | 2020-11-05 | 2020-11-16 | 7 | 2020-11-16 | 2020-11-23 | 2020-12-09 | 10 | [5 empty] | 30121.95 | [8 empty] | W
Central Hudson |  | Sunrun Installation Service, Inc. | CH-12910 | Kingston | Ellenvl | Ulster | 12428 | G | 3078 | Greenfield Rd | N |  | 4.1 | [13 empty] | NM | N | 17 Enphase Energy IQ7-60-x-US (240V) | 2020-10-05 | 2020-10-06 | 1 | 2020-10-06 | [14 empty] | 2020-11-10 | 2020-11-10 |  | Y
Central Hudson |  | Solar Generation Projects, LLC | CH-12907 | Kingston | Kingston | Ulster | 12477 | G | 2016 | Lincoln Park | N |  | 5000 | [13 empty] | CDG | Y | 40 Chint Power Systems America CPS SCH125KTL-DO/US-600 (600V) [SI1] | 2020-10-28 | 2020-11-11 | 10 | 2020-11-11 | 2020-11-11 | 2020-12-04 | 15 | 2021-02-05 | 2021-03-18 | 2021-06-14 | 60 | 20861.49 | 248601.25 | 227812.49 | 2021-06-28 | 2022-01-05 | 2022-01-05 | 2023-12-28 | 2024-01-11 | 2024-01-11 | 2024-04-15 | Y | Y
Central Hudson |  | Lighthouse Solar | CH-12912 | Newburgh | New Paltz |  | 12561 | G | 5023 | Ohioville | N |  | 7.54 | [13 empty] | NM | N | 26 Enphase Energy IQ7PLUS-72-x-US (240V) | 2020-10-06 | 2020-10-07 | 1 | 2020-10-07 | [17 empty] | W
Central Hudson |  | SunCommon | CH-12913 | Newburgh | Newburgh | Orange | 12550 | G | 4011 | West Balmville | N |  | 25 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) 1 SolarEdge Technologies SE10000H-US (240V) 1 SolarEdge Technologies SE5000H-US (240V) | 2020-10-19 | 2020-10-23 | 4 | 2020-10-23 | [14 empty] | 2021-09-22 | 2021-09-22 |  | Y
Central Hudson |  | Solar Generation Projects, LLC | CH-12911 | Newburgh | Gardiner |  | 12525 | G | 5011 | Modena | N |  | 5000 | [13 empty] | CDG | Y | 40 Sungrow Power Supply SG125HV (600V) | 2020-10-28 | 2020-11-11 | 10 | 2020-11-11 | 2020-11-11 | 2020-12-04 | 15 | [14 empty] | W
Central Hudson |  | Sunrun Installation Services, Inc. | CH-12917 | Kingston | Kingston | Ulster | 12401 | G | 111 | South Wall St | N |  | 5.04 | [13 empty] | NM | N | 21 Enphase Energy IQ7-60-x-US (240V) | 2020-10-07 | 2020-10-08 | 1 | 2020-10-08 | [14 empty] | 2021-01-14 | 2021-01-14 |  | Y
Central Hudson |  | Suncommon | CH-12915 | Poughkeepsie | Millbrook | Dutchess | 12545 | G | 7012 | Hibernia | Y |  | 10.6 | 5 | [12 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) 1 SolarEdge Technologies SE3000H-US (240V) 1TeslaPowerwall 2 | 2020-10-07 | 2020-10-08 | 1 | 2020-10-08 | [14 empty] | 2020-12-04 | 2020-12-04 |  | Y
Central Hudson |  | Solar Generation | CH-12914 | Kingston | Willow | Ulster | 12495 | G | 3012 | Woodstock | N |  | 3.77 | [13 empty] | NM | N | 13 Enphase Energy IQ7PLUS-72-x-US (240V) | 2020-10-07 | 2020-10-07 | 0 | 2020-10-07 | [14 empty] | 2020-11-10 | 2020-11-10 |  | Y
Central Hudson |  | Autonomous Energies LLC | CH-12916 | Catskill | Cairo | Greene | 12413 | G | 2043 | South Cairo | N |  | 5.8 | [13 empty] | NM | N | 20 Enphase Energy IQ7PLUS-72-x-ACM-US-y (240V) [SI1] | 2020-10-07 | 2020-10-08 | 1 | 2020-10-08 | [14 empty] | 2020-12-29 | 2020-12-29 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-12920 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6065 | Inwood Ave | N |  | 5.28 | [13 empty] | NM | N | 22 Enphase Energy IQ7-60-x-US-& (240V) [SI1] | 2020-10-08 | 2020-10-09 | 1 | 2020-10-09 | [14 empty] | 2020-12-23 | 2020-12-23 |  | Y
Central Hudson |  | PlugPV, LLC. | CH-12921 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8092 | Fishkill Plains | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000H-US (240V) | 2020-10-08 | 2020-10-09 | 1 | 2020-10-09 | [14 empty] | 2020-12-10 | 2020-12-10 |  | Y
Central Hudson |  | PlugPV LLC | CH-12918 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6096 | Manchester | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE11400H-US (240V) | 2020-10-08 | 2020-10-08 | 0 | 2020-10-08 | [14 empty] | 2020-11-20 | 2020-11-20 |  | Y
Central Hudson |  | Lighthouse Solar | CH-12919 | Newburgh | New Paltz | Ulster | 12561 | G | 5031 | Galeville | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2020-10-08 | 2020-10-08 | 0 | 2020-10-08 | [14 empty] | 2020-11-25 | 2020-11-25 |  | Y
Central Hudson |  | New York State Solar Farm | CH-12924 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 6092 | Manchester | N |  | 4.095 | [13 empty] | NM | N | 13 SunPower SPR-X22-360-E-AC (240V) | 2020-10-09 | 2020-10-12 | 1 | 2020-10-12 | [14 empty] | 2020-11-02 | 2020-11-02 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12922 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 6051 | Todd Hill | N |  | 7.25 | [13 empty] | NM | N | 25 Enphase Energy IQ7PLUS-72-x-US (240V) | 2020-10-09 | 2020-10-12 | 1 | 2020-10-12 | [14 empty] | 2020-10-21 | 2020-10-21 |  | Y
Central Hudson |  | PlugPV, LLC. | CH-12923 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6044 | Spackenkill | N |  | 12 | [13 empty] | NM | N | 2 SolarEdge Technologies SE6000H-US (240V) | 2020-10-09 | 2020-10-12 | 1 | 2020-10-12 | [14 empty] | 2020-12-23 | 2020-12-23 |  | Y
Central Hudson |  | Self | CH-12925 | Catskill | Oak Hl | Greene | 12460 | G | 1092 | Westerlo | N |  | 6 | [13 empty] | NM | N | 1 SMA America SB6000US (240V) | 2020-10-16 | 2020-10-20 | 2 | 2020-10-20 | [14 empty] | 2020-10-30 | 2020-10-30 |  | Y
Central Hudson |  | Kasselman Solar | CH-12926 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2020-10-13 | 2020-10-13 | 0 | 2020-10-13 | [14 empty] | 2020-10-23 | 2020-10-23 |  | Y
Central Hudson |  | Solar Generation | CH-12927 | Kingston | Kingston | Ulster | 12401 | G | 2013 | Lincoln Park | N |  | 8.19 | [13 empty] | NM | N | 26 Enphase Energy IQ7X-96-x-US (240V) | 2020-10-13 | 2020-10-13 | 0 | 2020-10-13 | [14 empty] | 2020-12-01 | 2020-12-01 |  | Y
Central Hudson |  | Solar Generation | CH-12928 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6003 | Reynolds Hill | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2020-10-13 | 2020-10-13 | 0 | 2020-10-13 | [14 empty] | 2020-12-10 | 2020-12-10 |  | Y
Central Hudson |  | Sundog | CH-12929 | Poughkeepsie | Millerton | Dutchess | 12546 | G | 7095 | Smithfield | N | CH-12929 | 6.28 | [13 empty] | NM | N | 18 Enphase Energy IQ7A-72-x-US-& (240V) [SI1] | 2020-10-19 | 2020-10-21 | 2 | 2020-10-21 | [14 empty] | 2020-12-16 | 2020-12-16 |  | Y
Central Hudson |  | PlugPV, LLC. | CH-12930 | Poughkeepsie | Lagrangevl | Dutchess | 12540 | G | 6053 | Todd Hill | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2020-10-19 | 2020-10-21 | 2 | 2020-10-21 | [14 empty] | 2020-11-25 | 2020-11-25 |  | Y
Central Hudson |  | Kasselman Solar | CH-12939 | Catskill | Cairo | Greene | 12413 | G | 1092 | Westerlo | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2020-10-15 | 2020-10-20 | 3 | 2020-10-20 | [8 empty] | 350 | 350 |  | 2020-10-29 | 2020-10-29 | 2020-11-23 | 2020-12-07 | 2020-12-07 |  | Y
Central Hudson |  | Sunrun Installation Service, Inc. | CH-12935 | Fishkill | Garrison | Putnam | 10524 | G | 8066 | Merritt Park | N |  | 3.36 | [13 empty] | NM | N | 14 Enphase Energy IQ7-60-x-US (240V) | 2020-10-15 | 2020-10-16 | 1 | 2020-10-16 | [14 empty] | 2020-11-25 | 2020-11-25 |  | Y
Central Hudson |  | US Energy Concierge, Inc. | CH-12931 | Fishkill | Garrison | Putnam | 10524 | G | 8086 | Tioronda | N |  | 3.8 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3800H-US (240V) | 2020-10-21 | 2020-10-22 | 1 | 2020-10-22 | [14 empty] | 2020-12-22 | 2020-12-22 |  | Y
Central Hudson |  | Sunrun Installation Service, Inc. | CH-12936 | Newburgh | New Windsor | Orange | 12553 | G | 4044 | Union Ave | N |  | 4.8 | [13 empty] | NM | N | 20 Enphase Energy IQ7-60-x-US (240V) | 2020-10-15 | 2020-10-16 | 1 | 2020-10-16 | [14 empty] | 2021-05-17 | 2021-05-17 |  | Y
Central Hudson |  | Kasselman Solar | CH-12932 | Catskill | S Westerlo | Greene | 12083 | G | 1091 | Westerlo | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2020-10-16 | 2020-10-16 | 0 | 2020-10-16 | [14 empty] | 2020-11-05 | 2020-11-05 |  | Y
Central Hudson |  | Kasselman Solar | CH-12933 | Catskill | S Westerlo | Greene | 12083 | G | 1091 | Westerlo | N |  | 3.8 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3800H-US (240V) [SI1] | 2020-10-15 | 2020-10-16 | 1 | 2020-10-16 | [8 empty] | 350 | 350 |  | 2020-11-17 | 2020-11-17 | 2020-12-02 | 2020-12-14 | 2020-12-14 |  | Y
Central Hudson |  | Trinity Solar | CH-12938 | Newburgh | Goshen | Orange | 10924 | G | 5051 | Maybrook | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2020-10-15 | 2020-10-16 | 1 | 2020-10-16 | [14 empty] | 2021-02-24 | 2021-02-24 |  | Y
Central Hudson |  | Tesla | CH-12934 | Newburgh | Newburgh | Orange | 12550 | G | 4011 | West Balmville | N |  | 15.2 | [13 empty] | NM | N | 2 SolarEdge Technologies SE7600H-US (240V) | 2020-10-15 | 2020-10-16 | 1 | 2020-10-16 | [14 empty] | 2021-03-16 | 2021-03-16 |  | Y
Central Hudson |  | PlugPV, LLC | CH-12937 | Newburgh | New Windsor | Orange | 12553 | G | 4094 | Bethlehem Rd | N |  | 15.2 | [13 empty] | NM | N | 2 SolarEdge Technologies SE7600H-US (240V) | 2020-10-15 | 2020-10-16 | 1 | 2020-10-16 | [14 empty] | 2021-01-12 | 2021-01-12 |  | Y
Central Hudson |  | PlugPV, LLC | CH-12940 | Catskill | W Coxsackie | Greene | 12192 | G | 1076 | Coxsackie | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2020-10-15 | 2020-10-16 | 1 | 2020-10-16 | [14 empty] | 2020-12-04 | 2020-12-04 |  | Y
Central Hudson |  | American Solar Partners | CH-12943 | Catskill | Catskill | Greene | 12414 | G | 2003 | North Catskill | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000H-US (240V) | 2020-10-20 | 2020-10-20 | 0 | 2020-10-20 | [14 empty] | 2021-02-17 | 2021-02-17 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12942 | Fishkill | Beacon | Dutchess | 12508 | G | 8085 | Tioronda | N |  | 7.25 | [13 empty] | NM | N | 25 Enphase Energy IQ7PLUS-72-x-US (240V) | 2020-10-16 | 2020-10-19 | 1 | 2020-10-19 | [14 empty] | 2021-07-29 | 2021-07-29 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12944 | Fishkill | Fishkill | Dutchess | 12524 | G | 8011 | Forgebrook | N |  | 11.02 | [13 empty] | NM | N | 38 Enphase Energy IQ7PLUS-72-x-US (240V) | 2020-10-16 | 2020-10-20 | 2 | 2020-10-20 | [14 empty] | 2020-11-06 | 2020-11-06 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12945 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6046 | Spackenkill | N |  | 6.96 | [13 empty] | NM | N | 24 Enphase Energy IQ7PLUS-72-x-US (240V) | 2020-10-16 | 2020-10-20 | 2 | 2020-10-20 | [14 empty] | 2020-11-06 | 2020-11-06 |  | Y
Central Hudson |  | Sunrun Installation Service, Inc. | CH-12941 | Kingston | Olive Brdg | Ulster | 12461 | G | 3024 | High Falls | Y |  | 5.51 | 10 | [12 empty] | NM | N | 19 Enphase Energy IQ7PLUS-72-x-US (240V) 2TESLAPowerwall 2 AC | 2020-10-16 | 2020-10-19 | 1 | 2020-10-19 | [14 empty] | 2021-01-26 | 2021-01-26 |  | Y
Central Hudson |  | SunCommon | CH-12950 | Kingston | Kingston | Ulster | 12401 | G | 2092 | Hurley Ave | Y |  | 17.6 | 15 | [12 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) 1 SolarEdge Technologies SE7600H-US (240V) 3TeslaAC Powerwall 2 | 2020-10-19 | 2020-10-22 | 3 | 2020-10-22 | [14 empty] | 2021-07-19 | 2021-07-19 |  | Y
Central Hudson |  | SunCommon | CH-12947 | Fishkill | Garrison | Putnam | 10524 | G | 8086 | Tioronda | Y | CH-12320 |  | 10 | [12 empty] | NM | N | 2TeslaPowerwall 2 | 2020-10-23 | 2020-10-23 | 0 | 2020-10-23 | [14 empty] | 2021-01-07 | 2021-01-07 |  | Y
Central Hudson |  | Tesla | CH-12949 | Fishkill | Cold Spg | Putnam | 10516 | G | 8087 | Tioronda | Y |  | 11.4 | 10 | [12 empty] | NM | N | 1 SolarEdge Technologies SE11400H-US (240V) 2TeslaAC Powerwall 2.0 | 2020-10-19 | 2020-10-21 | 2 | 2020-10-21 | [14 empty] | 2021-03-02 | 2021-03-02 |  | Y
Central Hudson |  | Tesla | CH-12948 | Kingston | Saugerties | Ulster | 12477 | G | 3003 | Saugerties | Y | CH-16557 | 15.2 | 20 | [12 empty] | NM | N | 2 SolarEdge Technologies SE7600H-US (240V) [SI1] 4TeslaAC Powerwall 2.0 | 2020-10-19 | 2020-10-20 | 1 | 2020-10-20 | [8 empty] | 350 | 350 |  | 2021-03-10 | 2021-03-10 | 2021-05-08 | 2021-07-23 | 2021-07-23 |  | Y
Central Hudson |  | Lighthouse Solar | CH-12951 | Newburgh | New Paltz | Ulster | 12561 | G | 5023 | Ohioville | N |  | 4.64 | [13 empty] | NM | N | 16 Enphase Energy IQ7PLUS-72-x-US (240V) | 2020-10-20 | 2020-10-26 | 4 | 2020-10-26 | [14 empty] | 2020-12-03 | 2020-12-03 |  | Y
Central Hudson |  | PlugPV LLC | CH-12953 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 6092 | Manchester | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE11400H-US (240V) | 2020-10-21 | 2020-10-22 | 1 | 2020-10-22 | [14 empty] | 2020-12-10 | 2020-12-10 |  | Y
Central Hudson |  | PlugPV, LLC. | CH-12952 | Poughkeepsie | Staatsburg | Dutchess | 12580 | G | 7041 | Staatsburg | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2020-10-21 | 2020-10-22 | 1 | 2020-10-22 | [8 empty] | 350 | 350 |  | 2020-10-26 | 2020-10-26 | 2021-01-18 | 2021-01-20 | 2021-01-20 |  | Y
Central Hudson |  | New York State Solar Farm | CH-12954 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8096 | Fishkill Plains | N |  | 10.71 | [13 empty] | NM | N | 34 SunPower SPR-E19-320-E-AC (240V) | 2020-10-21 | 2020-10-22 | 1 | 2020-10-22 | [14 empty] | 2020-11-12 | 2020-11-12 |  | Y
Central Hudson |  | New York State Solar Farm | CH-12959 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8072 | Shenandoah | N |  | 4.725 | [13 empty] | NM | N | 15 SunPower SPR-E20-327-E-AC (240V) | 2020-10-22 | 2020-10-23 | 1 | 2020-10-23 | [14 empty] | 2021-03-22 | 2021-03-22 |  | Y
Central Hudson |  | New York State Solar Farm | CH-12955 | Poughkeepsie | Salt Pt | Dutchess | 12578 | G | 7025 | Tinkertown | N |  | 6.62 | [13 empty] | NM | N | 21 SunPower SPR-E19-320-E-AC (240V) | 2020-10-22 | 2020-10-23 | 1 | 2020-10-23 | [14 empty] | 2020-11-04 | 2020-11-04 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12956 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N | CH-11582 | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2020-10-22 | 2020-10-22 | 0 | 2020-10-22 | [14 empty] | 2020-12-08 | 2020-12-08 |  | Y
Central Hudson |  | Rav Electric | CH-12957 | Poughkeepsie | Millerton | Dutchess | 12546 | G | 7081 | Millerton | N |  | 6 | [13 empty] | NM | N | 1 SMA America SB6.0-1SP-US-41 (240V) [SI1] | 2020-10-27 | 2020-10-28 | 1 | 2020-10-28 | [14 empty] | 2021-01-14 | 2021-01-14 |  | Y
Central Hudson |  | Tesla | CH-12958 | Kingston | Kingston | Ulster | 12401 | G | 2093 | Hurley Ave | Y |  | 7.6 | 10 | [12 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) 2TeslaAC Powerwall 2.0 | 2020-10-22 | 2020-10-23 | 1 | 2020-10-23 | [14 empty] | 2020-10-27 | 2020-10-27 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-12963 | Kingston | Kerhonkson | Ulster | 12446 | G | 3083 | Kerhonkson | N |  | 6.48 | [13 empty] | NM | N | 27 Enphase Energy IQ7-60-x-US (240V) | 2020-10-23 | 2020-10-26 | 1 | 2020-10-26 | [14 empty] | 2021-02-02 | 2021-02-02 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-12964 | Newburgh | Maybrook | Orange | 12543 | G | 4026 | Coldenham | N |  | 4.8 | [13 empty] | NM | N | 20 Enphase Energy IQ7-60-x-US (240V) | 2020-11-09 | 2020-11-10 | 1 | 2020-11-10 | [14 empty] | 2020-12-02 | 2020-12-02 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-12961 | Newburgh | Maybrook | Orange | 12543 | G | 4026 | Coldenham | N |  | 7.25 | [13 empty] | NM | N | 25 Enphase Energy IQ7PLUS-72-x-US (240V) | 2020-10-23 | 2020-10-23 | 0 | 2020-10-23 | [14 empty] | 2021-01-07 | 2021-01-07 |  | Y
Central Hudson |  | Sunrun Installation Service, Inc. | CH-12962 | Kingston | Accord | Ulster | 12404 | G | 3024 | High Falls | N |  | 5.28 | [13 empty] | NM | N | 22 Enphase Energy IQ7-60-x-US (240V) | 2020-10-23 | 2020-10-26 | 1 | 2020-10-26 | [14 empty] | 2021-02-12 | 2021-02-12 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-12960 | Fishkill | Fishkill | Dutchess | 12524 | G | 8094 | Fishkill Plains | N |  | 5.22 | [13 empty] | NM | N | 18 Enphase Energy IQ7PLUS-72-x-US (240V) | 2020-10-23 | 2020-10-23 | 0 | 2020-10-23 | [14 empty] | 2020-12-10 | 2020-12-10 |  | Y
Central Hudson |  | SunCommon | CH-12967 | Kingston | Saugerties | Ulster | 12477 | G | 3001 | Saugerties | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2020-10-26 | 2020-10-28 | 2 | 2020-10-28 | [14 empty] | 2020-12-23 | 2020-12-23 |  | Y
Central Hudson |  | PlugPV, LLC | CH-12965 | Poughkeepsie | Wappingrs Fls | Dutchess | 12590 | G | 6052 | Todd Hill | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2020-10-26 | 2020-10-26 | 0 | 2020-10-26 | [14 empty] | 2021-06-28 | 2021-06-28 |  | Y
Central Hudson |  | PlugPV LLC | CH-12966 | Newburgh | New Windsor | Orange | 12553 | G | 4097 | Bethlehem Rd | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2020-10-26 | 2020-10-26 | 0 | 2020-10-26 | [14 empty] | 2020-12-17 | 2020-12-17 |  | Y
Central Hudson |  | Independent Solar, LLC | CH-12970 | Newburgh | Milton |  | 12547 | G | 5083 | Highland | N |  | 3300 | [13 empty] | CDG | Y | 1 Power Electronics FS3190K (600V) [SI1] | 2020-11-19 | 2020-11-30 | 5 | 2020-11-30 | 2020-11-30 | 2020-12-21 | 15 |  |  |  |  | 19000 | [9 empty] | W
Central Hudson |  | Infinity Solar Systems | CH-12968 | Newburgh | New Windsor |  | 12553 | G | 4046 | Union Ave | N |  | 6.72 | [13 empty] | NM | N | 28 Enphase Energy IQ7-60-x-US (240V) | 2020-10-27 | 2020-10-28 | 1 | 2020-10-28 | [17 empty] | W
Central Hudson |  | Lighthouse Solar | CH-12969 | Poughkeepsie | Ancramdale |  | 12503 | G | 7092 | Pulvers Corners | Y |  | 7.6 | 7.6 | [12 empty] | NM | N | 1 Generac Power Systems X7602 (240V) 1Generac7.6 kW X7602 (240v) | 2020-10-28 | 2020-10-29 | 1 | 2020-10-29 | [17 empty] | W
Central Hudson |  | Trinity Solar | CH-12973 | Newburgh | Newburgh | Orange | 12550 | G | 4011 | West Balmville | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2020-10-29 | 2020-11-02 | 2 | 2020-11-02 | [14 empty] | 2020-12-31 | 2020-12-31 |  | Y
Central Hudson |  | Hudson River Solar | CH-12971 | Kingston | Glenford | Ulster | 12433 | G | 3013 | Woodstock | Y |  | 9 | 9 | [12 empty] | NM | N | 1 Sol-Ark Sol-Ark-12K-P (240V) 1Sol-ArkSol-Ark 12K-P (240V) | 2020-11-02 | 2020-11-03 | 1 | 2020-11-03 | [14 empty] | 2021-03-02 | 2021-03-02 |  | Y
Central Hudson |  | Kasselman Solar | CH-12972 | Catskill | Athens | Greene | 12015 | G | 2002 | North Catskill | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE11400H-US (240V) | 2020-10-29 | 2020-11-02 | 2 | 2020-11-02 | [14 empty] | 2020-12-21 | 2020-12-21 |  | Y
Central Hudson |  | PlugPV, LLC | CH-12974 | Kingston | Saugerties | Ulster | 12477 | G | 2015 | Lincoln Park | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2020-10-28 | 2020-10-29 | 1 | 2020-10-29 | [14 empty] | 2020-12-18 | 2020-12-18 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12976 | Newburgh | Cornwall | Orange | 12518 | G | 4094 | Bethlehem Rd | N |  | 5.22 | [13 empty] | NM | N | 18 Enphase Energy IQ7PLUS-72-x-US (240V) | 2020-10-29 | 2020-11-02 | 2 | 2020-11-02 | [14 empty] | 2020-11-17 | 2020-11-17 |  | Y
Central Hudson |  | Kasselman Solar | CH-12975 | Catskill | S Westerlo | Greene | 12083 | G | 1091 | Westerlo | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2020-11-03 | 2020-11-04 | 1 | 2020-11-04 | [14 empty] | 2020-12-03 | 2020-12-03 |  | Y
Central Hudson |  | New York State Solar Farm | CH-12977 | Poughkeepsie | Lagrangevl | Dutchess | 12540 | G | 6053 | Todd Hill | N | CH-12977 | 11.34 | [13 empty] | NM | N | 36 SunPower SPR-E19-320-E-AC (240V) | 2020-10-30 | 2020-11-02 | 1 | 2020-11-02 | [14 empty] | 2020-11-20 | 2020-11-20 |  | Y
Central Hudson |  | PlugPV, LLC. | CH-12978 | Newburgh | New Windsor | Orange | 12553 | G | 4094 | Bethlehem Rd | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2020-10-30 | 2020-11-02 | 1 | 2020-11-02 | [14 empty] | 2020-12-10 | 2020-12-10 |  | Y
Central Hudson |  | New York State Solar Farm | CH-12979 | Kingston | Ellenvl | Ulster | 12428 | G | 3078 | Greenfield Rd | N | CH-12979 | 7.56 | [13 empty] | NM | N | 24 SunPower SPR-E20-327-D-AC (240V) | 2020-10-30 | 2020-11-02 | 1 | 2020-11-02 | [14 empty] | 2020-12-14 | 2020-12-14 |  | Y
Central Hudson |  | Solar Generation | CH-12982 | Kingston | Ellenville | Ulster | 12428 | G | 396 | Clinton Ave | N |  | 19.53 | [13 empty] | RC | Y | 62 Enphase Energy IQ7X-96-x-US (240V) | 2020-11-04 | 2020-11-12 | 6 | 2020-11-12 | [14 empty] | 2021-03-05 | 2021-03-05 |  | Y | Y
Central Hudson |  | Solar Generation | CH-12984 | Kingston | Kingston | Ulster | 12401 | G | 122 | Converse St | N |  | 14.18 | [13 empty] | RC | Y | 45 Enphase Energy IQ7X-96-x-US (240V) | 2020-11-04 | 2020-11-05 | 1 | 2020-11-05 | [14 empty] | 2021-03-12 | 2021-03-12 |  | Y | Y | 3/8/21 - CH rep had no access to install net meter. 3/12/21 - Appt scheduled; net meter installed.
Central Hudson |  | Solar Generation | CH-12983 | Newburgh | New Paltz | Ulster | 12561 | G | 5021 | Ohioville | N |  | 6.93 | [13 empty] | NM | N | 22 Enphase Energy IQ7X-96-x-US (240V) | 2020-11-04 | 2020-11-05 | 1 | 2020-11-05 | [14 empty] | 2021-02-24 | 2021-02-24 |  | Y
Central Hudson |  | PlugPV LLC | CH-12980 | Poughkeepsie | Poughquag | Dutchess | 12570 | G | 6055 | Todd Hill | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2020-11-02 | 2020-11-02 | 0 | 2020-11-02 | [14 empty] | 2020-12-31 | 2020-12-31 |  | Y
Central Hudson |  | PlugPV LLC | CH-12981 | Newburgh | New Windsor | Orange | 12553 | G | 4097 | Bethlehem Rd | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE11400H-US (240V) | 2020-11-02 | 2020-11-02 | 0 | 2020-11-02 | [14 empty] | 2020-12-23 | 2020-12-23 |  | Y
Central Hudson |  | SunCommon | CH-12989 | Fishkill | Beacon | Dutchess | 12508 | G | 8018 | Forgebrook | N |  | 3.8 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3800H-US (240V) | 2020-11-03 | 2020-11-05 | 2 | 2020-11-05 | [14 empty] | 2021-01-25 | 2021-01-25 |  | Y
Central Hudson |  | Trinity Solar | CH-12985 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6063 | Inwood Ave | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2020-11-03 | 2020-11-03 | 0 | 2020-11-03 | [14 empty] | 2021-03-10 | 2021-03-10 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12987 | Newburgh | New Windsor | Orange | 12553 | G | 4095 | Bethlehem Rd | N |  | 6.38 | [13 empty] | NM | N | 22 Enphase Energy IQ7PLUS-72-x-US (240V) | 2020-11-03 | 2020-11-05 | 2 | 2020-11-05 | [14 empty] | 2020-12-01 | 2020-12-01 |  | Y
Central Hudson |  | New York State Solar Farm | CH-12986 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N | CH-12986 | 7.56 | [13 empty] | NM | N | 24 SunPower SPR-E19-320-E-AC (240V) | 2020-11-03 | 2020-11-05 | 2 | 2020-11-05 | [14 empty] | 2020-11-23 | 2020-11-23 |  | Y
Central Hudson |  | Solar Generation | CH-12988 | Kingston | W Camp | Ulster | 12490 | G | 3004 | Saugerties | N |  | 3.78 | [13 empty] | NM | N | 12 Enphase Energy IQ7X-96-x-US (240V) | 2020-11-03 | 2020-11-05 | 2 | 2020-11-05 | [14 empty] | 2020-12-02 | 2020-12-02 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12990 | Kingston | Kingston | Ulster | 12401 | G | 2013 | Lincoln Park | N |  | 5.22 | [13 empty] | NM | N | 18 Enphase Energy IQ7PLUS-72-x-US (240V) | 2020-11-03 | 2020-11-05 | 2 | 2020-11-05 | [14 empty] | 2020-12-10 | 2020-12-10 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-12993 | Fishkill | Fishkill | Dutchess | 12524 | G | 8013 | Forgebrook | N |  | 9.6 | [13 empty] | NM | N | 40 Enphase Energy IQ7-60-x-US (240V) | 2020-11-04 | 2020-11-05 | 1 | 2020-11-05 | [14 empty] | 2020-12-03 | 2020-12-03 |  | Y
Central Hudson |  | Kasselman Solar | CH-12991 | Catskill | Preston Holw | Albany | 12469 | G | 1092 | Westerlo | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2020-11-13 | 2020-11-18 | 3 | 2020-11-18 | [14 empty] | 2020-11-23 | 2020-11-23 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-12992 | Newburgh | Marlboro | Ulster | 12542 | G | 5004 | Marlboro | N |  | 7.83 | [13 empty] | NM | N | 27 Enphase Energy IQ7PLUS-72-x-US (240V) | 2020-11-04 | 2020-11-05 | 1 | 2020-11-05 | [14 empty] | 2020-12-03 | 2020-12-03 |  | Y
Central Hudson |  | AEC Solar Energy Corp | CH-12994 | Fishkill | Garrison | Putnam | 10524 | G | 8066 | Merritt Park | Y |  | 7.6 | 7.6 | [12 empty] | NM | N | 1 Generac Power Systems X7602 (240V) 1Generac PWRCELLX7602 | 2020-11-30 | 2020-12-04 | 4 | 2020-12-04 | [14 empty] | 2021-04-08 | 2021-04-08 |  | Y
Central Hudson |  | Tesla | CH-12995 | Newburgh | Salisbury Mls | Orange | 12577 | G | 4097 | Bethlehem Rd | Y |  | 11.4 | 15 | [12 empty] | NM | N | 1 SolarEdge Technologies SE11400H-US (240V) 3TeslaAC Powerwall 2.0 | 2020-11-09 | 2020-11-10 | 1 | 2020-11-10 | [8 empty] | 350 | 350 |  | 2020-11-24 | 2020-11-24 | 2021-02-05 | 2021-02-25 | 2021-02-25 |  | Y
Central Hudson |  | SunCommon | CH-12996 | Kingston | Claryvl | Sullivan | 12725 | G | 3091 | Neversink | N |  | 26 | [13 empty] | NM | N | 2 SolarEdge Technologies SE10000H-US (240V) 1 SolarEdge Technologies SE6000H-US (240V) | 2020-12-21 | 2020-12-23 | 2 | 2020-12-23 | [8 empty] | 1447.39 | 1916.27 |  | 2020-12-30 | 2020-12-30 | 2021-02-03 | 2021-07-01 | 2021-07-01 | 2021-07-12 | Y
Central Hudson |  | PlugPV, LLC. | CH-12997 | Newburgh | New Windsor | Orange | 12553 | G | 4097 | Bethlehem Rd | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2020-11-06 | 2020-11-09 | 1 | 2020-11-09 | [14 empty] | 2020-12-31 | 2020-12-31 |  | Y
Central Hudson |  | Solar Liberty Energy Systems, Inc. | CH-12998 | Catskill | Lexington | Greene | 12452 | E | 2389 | Vinegar Hill | N |  | 10.4 | [13 empty] | NM | N | 33 Enphase Energy IQ7X-96-x-US (240V) | 2020-11-09 | 2020-11-10 | 1 | 2020-11-10 | [14 empty] | 2021-02-23 | 2021-02-23 |  | Y
Central Hudson |  | EDF Renewables Distributed Solutions Inc. | CH-13003 | Kingston | Rosendale | Ulster | 12486 | G | 3042 | Sturgeon Pool | N |  | 5000 | [13 empty] | CDG | Y | 40 Chint Power Systems America CPS SCH125KTL-DO/US-600 (600V) [SI1] | 2021-01-22 | 2021-02-05 | 10 | 2021-02-05 | 2021-02-05 | 2021-02-26 | 14 | 2021-04-26 | 2021-07-12 | 2021-10-05 | 60 | 20000 | 133078 |  | 2022-03-08 | 2022-06-03 | 2022-06-03 |  |  |  |  | N | Y
Central Hudson |  | PlugPV, LLC | CH-13001 | Newburgh | Rock Tvrn | Orange | 12575 | G | 4097 | Bethlehem Rd | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2020-11-10 | 2020-11-13 | 3 | 2020-11-13 | [8 empty] | 350 | 350 |  | 2020-11-18 | 2020-11-18 | 2021-02-03 | 2021-02-08 | 2021-02-08 |  | Y
Central Hudson |  | KASSELMAN SOLAR | CH-13000 | Kingston | Saugerties | Ulster | 12477 | G | 3002 | Saugerties | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000H-US (208V) | 2020-11-10 | 2020-11-12 | 2 | 2020-11-12 | [14 empty] | 2020-12-29 | 2020-12-29 |  | Y
Central Hudson |  | Solar Generation | CH-12999 | Kingston | Grahamsvl | Sullivan | 12740 | G | 3091 | Neversink | N |  | 7.6 | [13 empty] | NM | N | 1 Generac Power Systems X7602 (240V) | 2020-11-09 | 2020-11-10 | 1 | 2020-11-10 | [14 empty] | 2021-01-26 | 2021-01-26 |  | Y
Central Hudson |  | Viking Solar | CH-13004 | Catskill | Greenvl | Greene | 12083 | G | 1091 | Westerlo | N | CH-13004 | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000H-US (208V) | 2020-11-09 | 2020-11-11 | 2 | 2020-11-11 | [14 empty] | 2021-11-17 | 2021-11-17 |  | Y
Central Hudson |  | KASSELMAN SOLAR | CH-13002 | Kingston | Greenfield Pk | Ulster | 12435 | G | 3096 | Grimley Rd | N |  | 5.8 | [13 empty] | NM | N | 20 Enphase Energy IQ7PLUS-72-x-US (240V) | 2020-11-09 | 2020-11-11 | 2 | 2020-11-11 | [14 empty] | 2020-12-31 | 2020-12-31 |  | Y
Central Hudson |  | SunCommon | CH-13007 | Poughkeepsie | Verbank | Dutchess | 12585 | G | 6057 | Todd Hill | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2020-11-10 | 2020-11-12 | 2 | 2020-11-12 | [14 empty] | 2021-01-28 | 2021-01-28 |  | Y
Central Hudson |  | Kasselman Solar | CH-13008 | Poughkeepsie | Staatsburg | Dutchess | 12580 | G | 7011 | Hibernia | N |  | 7.6 | [13 empty] | NM | N | 2 SolarEdge Technologies SE3800H-US (240V) | 2020-11-12 | 2020-11-17 | 3 | 2020-11-17 | [14 empty] | 2020-12-03 | 2020-12-03 |  | Y
Central Hudson |  | KASSELMAN SOLAR | CH-13009 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6044 | Spackenkill | N |  | 8.41 | [13 empty] | NM | N | 12 Enphase Energy IQ7PLUS-72-x-US (240V) 17 Enphase Energy IQ7PLUS-72-x-US (240V) | 2020-11-10 | 2020-11-12 | 2 | 2020-11-12 | [14 empty] | 2020-11-25 | 2020-11-25 |  | Y
Central Hudson |  | New York State Solar Farm | CH-13010 | Catskill | Greenvl | Greene | 12083 | G | 2061 | Freehold | N | CH-13010 | 11.025 | [13 empty] | NM | N | 35 SunPower SPR-X22-360-E-AC (240V) | 2020-11-10 | 2020-11-12 | 2 | 2020-11-12 | [8 empty] | 350 | 350 |  | 2020-11-20 | 2020-11-20 | 2020-12-18 | 2020-12-22 | 2020-12-22 |  | Y
Central Hudson |  | Lighthouse Solar | CH-13006 | Newburgh | Newburgh | Orange | 12550 | G | 4011 | West Balmville | Y |  | 7.6 | 7.6 | [12 empty] | NM | N | 1 Generac Power Systems X7602 (240V) 1Generac7.6 kW X7602 (240v) | 2020-11-12 | 2020-11-17 | 3 | 2020-11-17 | [8 empty] | 350 | 350 |  | 2020-11-20 | 2020-11-20 | 2021-01-15 | 2021-04-14 | 2021-04-14 |  | Y
Central Hudson |  | Hudson River Renewables LLC | CH-13013 | Poughkeepsie | Millerton | Dutchess | 12546 | G | 7081 | Millerton | Y |  | 9.6 | 8 | [12 empty] | NM | N | 1 Sol-Ark Sol-Ark-12K-P (240V) 1Sol-ArkSol-Ark 12K-P (240V) | 2020-12-03 | 2020-12-07 | 2 | 2020-12-07 | [14 empty] | 2021-03-03 | 2021-03-03 |  | Y
Central Hudson |  | PlugPV LLC | CH-13014 | Newburgh | Marlboro | Ulster | 12542 | G | 5004 | Marlboro | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2020-11-11 | 2020-11-13 | 2 | 2020-11-13 | [8 empty] | 350 | 350 |  | 2020-11-17 | 2020-11-17 | 2021-01-13 | 2021-01-25 | 2021-01-25 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-13018 | Newburgh | Newburgh | Orange | 12550 | G | 4015 | West Balmville | N |  | 7.54 | [13 empty] | NM | N | 26 Enphase Energy IQ7PLUS-72-x-US (240V) | 2020-11-17 | 2020-11-19 | 2 | 2020-11-19 | [14 empty] | 2020-12-14 | 2020-12-14 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-13017 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8046 | Myers Corners | N |  | 4.35 | [13 empty] | NM | N | 15 Enphase Energy IQ7PLUS-72-x-US (240V) | 2020-11-11 | 2020-11-13 | 2 | 2020-11-13 | [14 empty] | 2020-11-23 | 2020-11-23 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-13021 | Fishkill | Fishkill | Dutchess | 12524 | G | 8094 | Fishkill Plains | N |  | 9.9 | [13 empty] | NM | N | 34 Enphase Energy IQ7PLUS-72-x-US (240V) | 2020-11-11 | 2020-11-16 | 3 | 2020-11-16 | [14 empty] | 2020-12-03 | 2020-12-03 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-13016 | Fishkill | Hopewell Jct |  | 12533 | G | 8096 | Fishkill Plains | N |  | 5.22 | [13 empty] | NM | N | 18 Enphase Energy IQ7PLUS-72-x-US (240V) | 2020-11-11 | 2020-11-16 | 3 | 2020-11-16 | [17 empty] | W
Central Hudson |  | PlugPV LLC | CH-13015 | Kingston | Olive Brdg | Ulster | 12461 | G | 3024 | High Falls | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE11400H-US (240V) | 2020-11-11 | 2020-11-13 | 2 | 2020-11-13 | [14 empty] | 2020-12-29 | 2020-12-29 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-13019 | Kingston | Kingston | Ulster | 12401 | G | 1022 | East Kingston | N |  | 2.9 | [13 empty] | NM | N | 10 Enphase Energy IQ7PLUS-72-x-US (240V) | 2020-11-11 | 2020-11-16 | 3 | 2020-11-16 | [14 empty] | 2021-03-02 | 2021-03-02 |  | Y
Central Hudson |  | New York State Solar Farm | CH-13020 | Newburgh | New Paltz | Ulster | 12561 | G | 5024 | Ohioville | N |  | 13.262 | [13 empty] | NM | N | 38 SunPower SPR-A415-G-AC (240V) | 2020-11-11 | 2020-11-16 | 3 | 2020-11-16 | [14 empty] | 2020-12-02 | 2020-12-02 |  | Y
Central Hudson |  | Tesla Energy Operations, Inc. | CH-13022 | Kingston | Lk Katrine | Ulster | 12449 | G | 2011 | Lincoln Park | Y |  | 11.4 | 10 | [12 empty] | NM | N | 1 SolarEdge Technologies SE11400H-US (240V) 2TeslaAC Powerwall 2.0 | 2020-11-23 | 2020-11-30 | 3 | 2020-11-30 | [14 empty] | 2020-12-17 | 2020-12-17 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-13025 | Newburgh | New Windsor |  | 12553 | G | 4054 | Union Ave | Y |  | 4.32 | 5 | [12 empty] | NM | N | 18 Enphase Energy IQ7-60-x-US (240V) 1TeslaAC Powerwall 2.0 | 2020-11-12 | 2020-11-17 | 3 | 2020-11-17 | [17 empty] | W
Central Hudson |  | Solar Generation | CH-13028 | Kingston | Woodstock | Ulster | 12498 | G | 3012 | Woodstock | N |  | 5.36 | [13 empty] | NM | N | 17 Enphase Energy IQ7X-96-x-US (240V) | 2020-11-24 | 2020-11-25 | 1 | 2020-11-25 | [14 empty] | 2020-12-11 | 2020-12-11 |  | Y
Central Hudson |  | KASSELMAN SOLAR | CH-13023 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 6068 | Inwood Ave | N |  | 6.96 | [13 empty] | NM | N | 24 Enphase Energy IQ7PLUS-72-x-US (240V) | 2020-11-24 | 2020-11-25 | 1 | 2020-11-25 | [14 empty] | 2020-12-28 | 2020-12-28 |  | Y
Central Hudson |  | PlugPV | CH-13024 | Newburgh | Milton | Ulster | 12547 | G | 5003 | Marlboro | Y |  | 10 | 5 | [12 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) 1TeslaPowerwall 2 | 2020-11-17 | 2020-11-19 | 2 | 2020-11-19 | [14 empty] | 2020-12-18 | 2020-12-18 |  | Y
Central Hudson |  | New York State Solar Farm | CH-13026 | Newburgh | Highland | Ulster | 12528 | G | 5012 | Modena | N |  | 4.54 | [13 empty] | NM | N | 13 SunPower SPR-A420-G-AC (240V) | 2020-11-12 | 2020-11-17 | 3 | 2020-11-17 | [14 empty] | 2020-12-16 | 2020-12-16 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-13027 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6091 | Manchester | N |  | 7.2 | [13 empty] | NM | N | 15 Enphase Energy IQ7-60-x-US-& (240V) [SI1] 15 Enphase Energy IQ7-60-x-US-& (240V) [SI1] | 2020-11-12 | 2020-11-17 | 3 | 2020-11-17 | [14 empty] | 2020-12-23 | 2020-12-23 |  | Y
Central Hudson |  | Kasselman Solar | CH-13036 | Catskill | Westerlo | Albany | 12193 | G | 1091 | Westerlo | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2020-11-18 | 2020-11-20 | 2 | 2020-11-20 | [14 empty] | 2020-12-03 | 2020-12-03 |  | Y
Central Hudson |  | SunCommon | CH-13037 | Kingston | Woodstock | Ulster | 12498 | G | 3013 | Woodstock | Y |  | 7.6 | 5 | [12 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) 1TeslaPowerwall 2 | 2020-11-18 | 2020-11-20 | 2 | 2020-11-20 | [14 empty] | 2021-02-18 | 2021-02-18 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-13032 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6046 | Spackenkill | N | CH-13032 | 6.72 | [13 empty] | NM | N | 28 Enphase Energy IQ7-60-x-US (208V) | 2020-11-20 | 2020-11-24 | 2 | 2020-11-24 | [14 empty] | 2020-12-10 | 2020-12-10 |  | Y
Central Hudson |  | PlugPV, LLC | CH-13035 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6044 | Spackenkill | N |  | 15.2 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) 1 SolarEdge Technologies SE7600H-US (240V) | 2020-11-13 | 2020-11-18 | 3 | 2020-11-18 | [14 empty] | 2021-06-09 | 2021-06-09 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-13031 | Newburgh | Walden | Orange | 12586 | G | 5041 | East Walden | N |  | 5.52 | [13 empty] | NM | N | 10 Enphase Energy IQ7-60-x-US (240V) 13 Enphase Energy IQ7-60-x-US (240V) | 2020-12-01 | 2020-12-07 | 4 | 2020-12-07 | [14 empty] | 2021-01-07 | 2021-01-07 |  | Y
Central Hudson |  | PlugPV | CH-13034 | Poughkeepsie | Lagrangevl | Dutchess | 12540 | G | 6055 | Todd Hill | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2020-11-18 | 2020-11-18 | 0 | 2020-11-18 | [14 empty] | 2020-12-31 | 2020-12-31 |  | Y
Central Hudson |  | US Energy Concierge, Inc. | CH-13030 | Fishkill | Beacon | Dutchess | 12508 | G | 8016 | Forgebrook | N |  | 3.8 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3800H-US (240V) | 2020-11-16 | 2020-11-19 | 3 | 2020-11-19 | [14 empty] | 2020-12-17 | 2020-12-17 |  | Y
Central Hudson |  | US Energy Concierge, Inc. | CH-13029 | Fishkill | Nelsonvl | Putnam | 10516 | G | 8087 | Tioronda | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2020-11-13 | 2020-11-18 | 3 | 2020-11-18 | [14 empty] | 2020-12-23 | 2020-12-23 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-13033 | Newburgh | Rock Tavern | Orange | 12575 | G | 4097 | Bethlehem Rd | N |  | 8.41 | [13 empty] | NM | N | 13 Enphase Energy IQ7PLUS-72-x-US (240V) 10 Enphase Energy IQ7PLUS-72-x-US (240V) 6 Enphase Energy IQ7PLUS-72-x-US (240V) | 2020-11-20 | 2020-11-24 | 2 | 2020-11-24 | [14 empty] | 2020-12-08 | 2020-12-08 |  | Y
Central Hudson |  | SunCommon | CH-13040 | Fishkill | Cold Spg | Putnam | 10516 | G | 8087 | Tioronda | N |  | 17.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) 1 SolarEdge Technologies SE7600H-US (240V) | 2020-11-16 | 2020-11-18 | 2 | 2020-11-18 | [14 empty] | 2022-09-23 | 2022-10-11 |  | Y
Central Hudson |  | SunCommon | CH-13039 | Newburgh | Highland | Ulster | 12528 | G | 5022 | Ohioville | N | CH-13039 | 13.8 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) 1 SolarEdge Technologies SE3800H-US (240V) | 2020-11-16 | 2020-11-18 | 2 | 2020-11-18 | [8 empty] | 350 | 350 |  | 2020-12-31 | 2020-12-31 | 2021-03-09 | 2021-03-22 | 2021-03-22 |  | Y
Central Hudson |  | Vivint Solar Developer, LLC | CH-13038 | Newburgh | Newburgh | Orange | 12550 | G | 4024 | Coldenham | N |  | 3.8 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3800H-US (240V) | 2020-12-09 | 2020-12-09 | 0 | 2020-12-09 | [14 empty] | 2021-06-22 | 2021-06-22 |  | Y
Central Hudson |  | Trinity Solar | CH-13042 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8093 | Fishkill Plains | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000H-US (240V) | 2020-11-16 | 2020-11-19 | 3 | 2020-11-19 | [14 empty] | 2021-01-11 | 2021-01-11 |  | Y
Central Hudson |  | Lighthouse Solar | CH-13044 | Fishkill | Garrison | Putnam | 10524 | G | 8086 | Tioronda | N |  | 15.37 | [13 empty] | NM | N | 53 Enphase Energy IQ7PLUS-72-x-US (240V) | 2020-11-30 | 2020-12-04 | 4 | 2020-12-04 | [14 empty] | 2022-02-07 | 2022-02-11 |  | Y
Central Hudson |  | SunCommon | CH-13041 | Poughkeepsie | Pine Plns | Dutchess | 12567 | G | 7091 | Pulvers Corners | N |  | 20 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) 1 SolarEdge Technologies SE10000H-US (240V) | 2020-11-16 | 2020-11-18 | 2 | 2020-11-18 | [14 empty] | 2021-04-28 | 2021-04-28 |  | Y
Central Hudson |  | New York State Solar Farm | CH-13043 | Poughkeepsie | Staatsburg | Dutchess | 12580 | G | 7041 | Staatsburg | N |  | 10.08 | [13 empty] | NM | N | 32 SunPower SPR-X22-360-E-AC (240V) | 2020-11-16 | 2020-11-19 | 3 | 2020-11-19 | [14 empty] | 2020-12-29 | 2020-12-29 |  | Y
Central Hudson |  | SunCommon | CH-13046 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7051 | Rhinebeck | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2020-11-16 | 2020-11-19 | 3 | 2020-11-19 | [14 empty] | 2021-01-15 | 2021-01-15 |  | Y
Central Hudson |  | SunCommon | CH-13047 | Poughkeepsie | Ancram | Columbia | 12502 | G | 7085 | Ancram | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000H-US (240V) | 2020-11-16 | 2020-11-19 | 3 | 2020-11-19 | [14 empty] | 2021-04-12 | 2021-04-12 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-13045 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8096 | Fishkill Plains | N |  | 16 | [13 empty] | NM | N | 55 Enphase Energy IQ7PLUS-72-x-US (240V) | 2020-11-16 | 2020-11-19 | 3 | 2020-11-19 | [14 empty] | 2020-12-21 | 2020-12-21 |  | Y
Central Hudson |  | KASSELMAN SOLAR | CH-13048 | Catskill | Catskill | Greene | 12414 | G | 2042 | South Cairo | N | CH-11075 | 3 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3000H-US (240V) | 2020-11-16 | 2020-11-19 | 3 | 2020-11-19 | [14 empty] | 2021-01-06 | 2021-01-06 |  | Y
Central Hudson |  | Apex Solar Power | CH-13051 | Newburgh | New Paltz | Ulster | 12561 | G | 5031 | Galeville | N | CH-13051 | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2020-11-17 | 2020-11-20 | 3 | 2020-11-20 | [14 empty] | 2021-01-04 | 2021-01-04 |  | Y
Central Hudson |  | New York State Solar Farm | CH-13050 | Newburgh | Marlboro | Ulster | 12542 | G | 5003 | Marlboro | N |  | 8.82 | [13 empty] | NM | N | 28 SunPower SPR-E20-327-E-AC (240V) | 2020-11-17 | 2020-11-19 | 2 | 2020-11-19 | [14 empty] | 2020-12-09 | 2020-12-10 |  | Y
Central Hudson |  | KASSELMAN SOLAR | CH-13049 | Newburgh | Esopus | Ulster | 12429 | G | 5084 | Highland | N |  | 4.35 | [13 empty] | NM | N | 15 Enphase Energy IQ7PLUS-72-x-US (240V) | 2020-11-17 | 2020-11-19 | 2 | 2020-11-19 | [14 empty] | 2021-01-08 | 2021-01-08 |  | Y
Central Hudson |  | SunCommon | CH-13054 | Poughkeepsie | Clinton Cors | Dutchess | 12514 | G | 7071 | Stanfordville | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2020-11-18 | 2020-11-20 | 2 | 2020-11-20 | [14 empty] | 2021-01-11 | 2021-01-11 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-13058 | Fishkill | Stormvl | Dutchess | 12582 | G | 8093 | Fishkill Plains | Y |  | 14.6 | 5 | [12 empty] | NM | N | 61 Enphase Energy IQ7-60-x-US (240V) 1TeslaAC Powerwall 2.0 | 2020-12-18 | 2020-12-21 | 1 | 2020-12-21 | [14 empty] | 2021-03-05 | 2021-03-05 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-13057 | Newburgh | Newburgh | Orange | 12550 | G | 4052 | Union Ave | N |  | 4.32 | [13 empty] | NM | N | 18 Enphase Energy IQ7-60-x-US (240V) | 2020-12-09 | 2020-12-11 | 2 | 2020-12-11 | [14 empty] | 2021-01-07 | 2021-01-07 |  | Y
Central Hudson |  | 64 Solar LLC | CH-13055 | Newburgh | Newburgh |  | 12550 | G | 4022 | Coldenham | N |  | 660 | [13 empty] | CDG | Y | 11 Chint Power Systems America CPS SCA60KTL-DO/US-480 (480V) | 2020-12-17 | 2021-01-05 | 10 | 2021-01-05 | 2021-01-05 | 2021-01-25 | 14 | [5 empty] | 151444.65 | [8 empty] | W
Central Hudson |  | Sunrun Installation Service, Inc. | CH-13052 | Newburgh | Washingtonvl | Orange | 10992 | G | 4097 | Bethlehem Rd | Y | CH-13052 | 9.1 | 10 | [12 empty] | NM | N | 38 Enphase Energy IQ7-60-x-US (240V) 2TESLAPowerwall 2 AC | 2021-01-04 | 2021-01-05 | 1 | 2021-01-05 | [14 empty] | 2021-04-20 | 2021-04-20 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-13053 | Kingston | Connelly | Ulster | 12417 | G | 1024 | East Kingston | N |  | 4.06 | [13 empty] | NM | N | 14 Enphase Energy IQ7PLUS-72-x-US (240V) | 2020-11-18 | 2020-11-20 | 2 | 2020-11-20 | [14 empty] | 2021-02-10 | 2021-02-10 |  | Y |  | 2/9/21 - CH Rep on site to change meter, No access. Customer notified.
Central Hudson |  | PlugPV | CH-13056 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6097 | Manchester | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2020-11-20 | 2020-11-24 | 2 | 2020-11-24 | [14 empty] | 2021-01-26 | 2021-01-26 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-13063 | Newburgh | Highland |  | 12528 | G | 5082 | Highland | N |  | 15.2 | [13 empty] | NM | N | 2 SolarEdge Technologies SE7600H-US (240V) | 2020-11-20 | 2020-11-24 | 2 | 2020-11-24 | [17 empty] | W
Central Hudson |  | Empire Solar Solutions | CH-13062 | Newburgh | Highland | Ulster | 12528 | G | 5082 | Highland | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2020-11-24 | 2020-11-25 | 1 | 2020-11-25 | [14 empty] | 2021-09-24 | 2021-10-01 |  | Y
Central Hudson |  | D & M Alternative Energy LLC | CH-13065 | Catskill | Coxsackie | Greene | 12051 | G | 1072 | Coxsackie | N |  | 5.28 | [13 empty] | NM | N | 22 Enphase Energy IQ7-60-x-US (240V) | 2020-11-20 | 2020-11-24 | 2 | 2020-11-24 | [14 empty] | 2021-01-22 | 2021-01-22 |  | Y
Central Hudson |  | Sunrun Installation Service, Inc. | CH-13069 | Newburgh | New Windsor | Orange | 12553 | G | 4042 | Union Ave | N |  | 10.6 | [13 empty] | NM | N | 44 Enphase Energy IQ7-60-x-US (240V) | 2020-11-20 | 2020-11-24 | 2 | 2020-11-24 | [14 empty] | 2021-01-18 | 2021-01-18 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-13061 | Newburgh | Wallkill | Ulster | 12589 | G | 5041 | East Walden | N | CH-13061 | 9.28 | [13 empty] | NM | N | 9 Enphase Energy IQ7PLUS-72-x-US (240V) 10 Enphase Energy IQ7PLUS-72-x-US (240V) 13 Enphase Energy IQ7PLUS-72-x-US (240V) | 2020-11-20 | 2020-11-24 | 2 | 2020-11-24 | [8 empty] | 350 | 350 |  | 2021-01-25 | 2021-01-25 | 2021-02-06 | 2021-02-17 | 2021-02-17 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-13060 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6094 | Manchester | N |  | 7.83 | [13 empty] | NM | N | 10 Enphase Energy IQ7PLUS-72-x-US (240V) 10 Enphase Energy IQ7PLUS-72-x-US (240V) 7 Enphase Energy IQ7PLUS-72-x-US (240V) | 2020-11-20 | 2020-11-24 | 2 | 2020-11-24 | [14 empty] | 2021-01-26 | 2021-01-26 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-13059 | Newburgh | Washingtonvl | Orange | 10992 | G | 5052 | Maybrook | N |  | 8.7 | [13 empty] | NM | N | 10 Enphase Energy IQ7PLUS-72-x-US (240V) 10 Enphase Energy IQ7PLUS-72-x-US (240V) 10 Enphase Energy IQ7PLUS-72-x-US (240V) | 2020-11-19 | 2020-11-23 | 2 | 2020-11-23 | [14 empty] | 2021-02-12 | 2021-02-12 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-13064 | Fishkill | Garrison | Putnam | 10524 | G | 8066 | Merritt Park | N |  | 9.28 | [13 empty] | NM | N | 10 Enphase Energy IQ7PLUS-72-x-US (240V) 12 Enphase Energy IQ7PLUS-72-x-US (240V) 10 Enphase Energy IQ7PLUS-72-x-US (240V) | 2020-11-24 | 2020-11-25 | 1 | 2020-11-25 | [14 empty] | 2021-03-29 | 2021-03-29 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-13068 | Newburgh | New Paltz | Ulster | 12561 | G | 5022 | Ohioville | N |  | 8.7 | [13 empty] | NM | N | 10 Enphase Energy IQ7PLUS-72-x-ACM-US (240V) 10 Enphase Energy IQ7PLUS-72-x-US (240V) 10 Enphase Energy IQ7PLUS-72-x-US (240V) | 2020-11-20 | 2020-11-24 | 2 | 2020-11-24 | [14 empty] | 2021-01-22 | 2021-01-22 |  | Y
Central Hudson |  | Solar Generation | CH-13067 | Kingston | Accord | Ulster | 12404 | G | 3024 | High Falls | N |  | 14.2 | [13 empty] | NM | N | 45 Enphase Energy IQ7X-96-x-US (240V) | 2020-11-24 | 2020-11-25 | 1 | 2020-11-25 | [8 empty] | 350 | 350 |  | 2020-12-01 | 2020-12-01 | 2021-02-17 | 2021-09-02 | 2021-09-02 |  | Y
Central Hudson |  | New York State Solar Farm | CH-13072 | Newburgh | New Paltz | Ulster | 12561 | G | 5021 | Ohioville | N |  | 9.765 | [13 empty] | NM | N | 31 SunPower SPR-E19-320-E-AC (240V) | 2020-11-20 | 2020-11-25 | 3 | 2020-11-25 | [14 empty] | 2020-12-10 | 2020-12-10 |  | Y
Central Hudson |  | SunBlue Energy | CH-13071 | Fishkill | Cold Spg | Putnam | 10516 | G | 8063 | Merritt Park | N |  | 24.4 | [13 empty] | NM | N | 84 Enphase Energy IQ7PLUS-72-x-US (240V) | 2020-11-30 | 2020-12-04 | 4 | 2020-12-04 | [8 empty] | 350 | 350 |  | 2020-12-09 | 2020-12-09 | 2020-12-10 | 2021-06-09 | 2021-06-09 |  | Y
Central Hudson |  | KASSELMAN SOLAR | CH-13070 | Newburgh | New Paltz | Ulster | 12561 | G | 5024 | Ohioville | N |  | 8.7 | [13 empty] | NM | N | 30 Enphase Energy IQ7PLUS-72-x-US (240V) | 2020-11-20 | 2020-11-24 | 2 | 2020-11-24 | [17 empty] | W
Central Hudson |  | Infinity Solar Systems | CH-13075 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6094 | Manchester | N |  | 3.19 | [13 empty] | NM | N | 11 Enphase Energy IQ7PLUS-72-x-US (240V) | 2020-11-23 | 2020-11-30 | 3 | 2020-11-30 | [14 empty] | 2021-04-08 | 2021-04-08 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-13073 | Newburgh | New Paltz | Ulster | 12561 | G | 5024 | Ohioville | N | CH-13073 | 15.66 | [13 empty] | NM | N | 32 Enphase Energy IQ7PLUS-72-x-US (240V) 22 Enphase Energy IQ7PLUS-72-x-US (240V) | 2020-12-07 | 2020-12-10 | 3 | 2020-12-10 | [14 empty] | 2021-02-03 | 2021-02-03 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-13074 | Newburgh | Middletown | Orange | 10941 | G | 5051 | Maybrook | N |  | 6.09 | [13 empty] | NM | N | 21 Enphase Energy IQ7PLUS-72-x-US (240V) | 2020-11-23 | 2020-11-30 | 3 | 2020-11-30 | [14 empty] | 2020-12-21 | 2020-12-21 |  | Y
Central Hudson |  | PlugPV LLC | CH-13076 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6092 | Manchester | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2020-11-23 | 2020-11-30 | 3 | 2020-11-30 | [14 empty] | 2021-06-15 | 2021-06-15 |  | Y
Central Hudson |  | SunPower Direct (NY) | CH-13080 | Newburgh | Newburgh | Orange | 12550 | G | 4023 | Coldenham | N |  | 9.074 | [13 empty] | NM | N | 26 SunPower SPR-A410-G-AC (240V) [SI1] | 2020-12-02 | 2020-12-07 | 3 | 2020-12-07 | [14 empty] | 2021-02-26 | 2021-02-26 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-13078 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 4.93 | [13 empty] | NM | N | 17 Enphase Energy IQ7PLUS-72-x-US (240V) | 2020-11-23 | 2020-11-30 | 3 | 2020-11-30 | [14 empty] | 2021-01-07 | 2021-01-07 |  | Y
Central Hudson |  | Tesla Energy Operations, Inc. | CH-13079 | Newburgh | New Windsor | Orange | 12553 | G | 4094 | Bethlehem Rd | Y |  | 15.2 | 15 | [12 empty] | NM | N | 2 SolarEdge Technologies SE7600H-US (240V) 3TeslaAC Powerwall | 2020-11-30 | 2020-12-07 | 5 | 2020-12-07 | [14 empty] | 2021-04-22 | 2021-04-22 |  | Y
Central Hudson |  | Omni Navitas Holdings LLC | CH-12946 | Catskill | Catskill |  | 12414 | G | 2001 | North Catskill | N |  | 1980 | [13 empty] | CDG | Y | 33 Sungrow Power Supply SG60KU-M (480V) [SI1] | 2020-12-11 | 2020-12-15 | 2 | 2020-12-15 | 2020-12-15 | 2021-01-07 | 14 | [5 empty] | 405652.15 | [8 empty] | W
Central Hudson |  | PlugPV, LLC | CH-13083 | Newburgh | New Windsor | Orange | 12553 | G | 4097 | Bethlehem Rd | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2020-11-25 | 2020-12-01 | 2 | 2020-12-01 | [14 empty] | 2021-01-06 | 2021-01-06 |  | Y
Central Hudson |  | KASSELMAN SOLAR | CH-13082 | Catskill | Catskill | Greene | 12414 | G | 2001 | North Catskill | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000H-US (208V) | 2020-11-25 | 2020-12-01 | 2 | 2020-12-01 | [14 empty] | 2020-12-16 | 2020-12-16 |  | Y
Central Hudson |  | KASSELMAN SOLAR | CH-13081 | Newburgh | Esopus | Ulster | 12429 | G | 5084 | Highland | N |  | 8.7 | [13 empty] | NM | N | 30 Enphase Energy IQ7PLUS-72-x-US (240V) | 2020-11-25 | 2020-12-01 | 2 | 2020-12-01 | [14 empty] | 2020-12-31 | 2020-12-31 |  | Y
Central Hudson |  | SunCommon | CH-13084 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7055 | Rhinebeck | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2020-11-25 | 2020-12-01 | 2 | 2020-12-01 | [14 empty] | 2020-12-08 | 2020-12-08 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-13086 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 5.28 | [13 empty] | NM | N | 22 Enphase Energy IQ7-60-x-US (240V) | 2020-11-30 | 2020-12-01 | 1 | 2020-12-01 | [14 empty] | 2021-02-05 | 2021-02-05 |  | Y
Central Hudson |  | New York State Solar Farm | CH-13085 | Kingston | W Hurley | Ulster | 12491 | G | 3013 | Woodstock | N |  | 10.71 | [13 empty] | NM | N | 34 SunPower SPR-X22-360-E-AC (240V) | 2020-11-30 | 2020-12-01 | 1 | 2020-12-01 | [14 empty] | 2020-12-29 | 2020-12-29 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-13087 | Newburgh | Milton | Ulster | 12547 | G | 5083 | Highland | N |  | 5.28 | [13 empty] | NM | N | 22 Enphase Energy IQ7-60-x-US (240V) | 2020-12-10 | 2020-12-14 | 2 | 2020-12-14 | [14 empty] | 2021-01-22 | 2021-01-22 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-13091 | Newburgh | Newburgh | Orange | 12550 | G | 4054 | Union Ave | N |  | 5.76 | [13 empty] | NM | N | 24 Enphase Energy IQ7-60-x-US (240V) | 2020-12-01 | 2020-12-07 | 4 | 2020-12-07 | [14 empty] | 2021-02-18 | 2021-02-18 |  | Y
Central Hudson |  | SunCommon | CH-13092 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7052 | Rhinebeck | Y |  | 4.72 | 5 | [12 empty] | NM | N | 16 Enphase Energy IQ7PLUS-72-x-US (240V) 1TeslaPowerwall 2 | 2020-12-08 | 2020-12-11 | 3 | 2020-12-11 | [14 empty] | 2021-02-16 | 2021-02-16 |  | Y
Central Hudson |  | KASSELMAN SOLAR | CH-13089 | Kingston | Accord | Ulster | 12404 | G | 3082 | Kerhonkson | N |  | 7.25 | [13 empty] | NM | N | 25 Enphase Energy IQ7PLUS-72-x-US (240V) | 2020-12-01 | 2020-12-07 | 4 | 2020-12-07 | [14 empty] | 2021-01-14 | 2021-01-14 |  | Y
Central Hudson |  | New York State Solar Farm | CH-13088 | Kingston | Kingston | Ulster | 12401 | G | 1022 | East Kingston | N |  | 5.04 | [13 empty] | NM | N | 16 SunPower SPR-E19-320-E-AC (240V) | 2020-11-30 | 2020-12-07 | 5 | 2020-12-07 | [14 empty] | 2021-01-11 | 2021-01-11 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-13090 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 7024 | Tinkertown | N |  | 9.86 | [13 empty] | NM | N | 13 Enphase Energy IQ7PLUS-72-x-US (240V) 13 Enphase Energy IQ7PLUS-72-x-US (240V) 8 Enphase Energy IQ7PLUS-72-x-US (240V) | 2020-12-01 | 2020-12-09 | 6 | 2020-12-09 | [14 empty] | 2021-04-08 | 2021-04-08 |  | Y
Central Hudson |  | AEC Solar Energy Corp | CH-13093 | Catskill | Catskill | Greene | 12414 | G | 2003 | North Catskill | N |  | 9.4 | [13 empty] | NM | N | 30 Enphase Energy IQ7XS-96-x-ACM-US-y-z-& (240V) [SI1] | 2020-12-07 | 2020-12-07 | 0 | 2020-12-07 | [8 empty] | 350 | 350 |  | 2020-12-15 | 2020-12-15 | 2020-12-23 | 2021-02-02 | 2021-02-02 |  | Y
Central Hudson |  | PlugPV LLC | CH-13094 | Poughkeepsie | Lagrangevl | Dutchess | 12540 | G | 6057 | Todd Hill | N |  | 20 | [13 empty] | NM | N | 2 SolarEdge Technologies SE10000H-US (240V) | 2020-12-02 | 2020-12-07 | 3 | 2020-12-07 | [8 empty] | 350 | 350 |  | 2020-12-09 | 2020-12-09 | 2021-01-12 | 2021-02-22 | 2021-02-22 |  | Y
Central Hudson |  | AEC Solar Energy Corp | CH-13099 | Fishkill | Poughkeepsie | Dutchess | 12601 | G | 8021 | Knapps Corners | N |  | 6.631 | [13 empty] | NM | N | 19 SunPower SPR-A415-G-AC (240V) | 2020-12-10 | 2020-12-14 | 2 | 2020-12-14 | [14 empty] | 2021-02-02 | 2021-02-02 |  | Y
Central Hudson |  | Lighthouse Solar | CH-13097 | Newburgh | Highland |  | 12528 | G | 5081 | Highland | N |  | 6.38 | [13 empty] | NM | N | 22 Enphase Energy IQ7PLUS-72-x-US (240V) | 2020-12-14 | 2020-12-14 | 0 | 2020-12-14 | [17 empty] | W
Central Hudson |  | New York State Solar Farm | CH-13096 | Newburgh | Newburgh | Orange | 12550 | G | 4023 | Coldenham | N |  | 6.93 | [13 empty] | NM | N | 22 SunPower SPR-E19-320-E-AC (240V) | 2020-12-04 | 2020-12-15 | 7 | 2020-12-15 | [14 empty] | 2021-02-08 | 2021-02-08 |  | Y
Central Hudson |  | Lighthouse Solar | CH-13100 | Kingston | Saugerties | Ulster | 12477 | G | 3014 | Woodstock | Y |  | 7.6 | 7.6 | [12 empty] | NM | N | 1 Generac Power Systems X7602 (240V) 1Generac7.6 kW X7602 (240v) | 2020-12-10 | 2020-12-11 | 1 | 2020-12-11 | [14 empty] | 2021-03-18 | 2021-03-18 |  | Y
Central Hudson |  | PlugPV, LLC. | CH-13098 | Poughkeepsie | Staatsburg | Dutchess | 12580 | G | 7042 | Staatsburg | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000H-US (240V) | 2020-12-04 | 2020-12-09 | 3 | 2020-12-09 | [14 empty] | 2021-01-20 | 2021-01-20 |  | Y
Central Hudson |  | Tesla | CH-13095 | Catskill | W Kill | Greene | 12492 | E | 2389 | Vinegar Hill | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2020-12-04 | 2020-12-09 | 3 | 2020-12-09 | [14 empty] | 2020-12-14 | 2020-12-14 |  | Y
Central Hudson |  | American Solar Partners | CH-13101 | Newburgh | Marlboro | Ulster | 12542 | G | 5003 | Marlboro | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000H-US (208V) | 2020-12-04 | 2020-12-10 | 4 | 2020-12-10 | [14 empty] | 2021-02-17 | 2021-02-17 |  | Y
Central Hudson |  | Apex Roofing LLC | CH-13106 | Poughkeepsie | Rhinecliff | Dutchess | 12574 | G | 7055 | Rhinebeck | N | CH-13106 | 16.38 | [13 empty] | NM | N | 52 Enphase Energy IQ7XS-96-y-ACM-z (240V) | 2020-12-07 | 2020-12-10 | 3 | 2020-12-10 | [14 empty] | 2021-01-20 | 2021-01-20 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-13103 | Newburgh | Campbell Hall | Orange | 10916 | G | 5052 | Maybrook | N |  | 7.54 | [13 empty] | NM | N | 26 Enphase Energy IQ7PLUS-72-x-US (240V) | 2020-12-07 | 2020-12-10 | 3 | 2020-12-10 | [14 empty] | 2021-01-29 | 2021-01-29 |  | Y
Central Hudson |  | Tesla | CH-13102 | Kingston | Kerhonkson | Ulster | 12446 | G | 3083 | Kerhonkson | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2020-12-07 | 2020-12-10 | 3 | 2020-12-10 | [14 empty] | 2020-12-14 | 2020-12-14 |  | Y
Central Hudson |  | New York State Solar Farm | CH-13104 | Fishkill | Fishkill | Dutchess | 12524 | G | 8012 | Forgebrook | N | CH-13104 | 6.3 | [13 empty] | NM | N | 20 SunPower SPR-E19-320-E-AC (240V) | 2020-12-07 | 2020-12-10 | 3 | 2020-12-10 | [14 empty] | 2021-01-18 | 2021-01-18 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-13105 | Poughkeepsie | Lagrangevl | Dutchess | 12540 | G | 6055 | Todd Hill | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) [SI1] | 2020-12-07 | 2020-12-10 | 3 | 2020-12-10 | [8 empty] | 350 | 350 |  | 2020-12-14 | 2020-12-14 | 2021-01-12 | 2021-07-14 | 2021-07-14 |  | Y
Central Hudson |  | Sunrun Installation Service, Inc. | CH-13109 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8092 | Fishkill Plains | Y |  | 10.15 | 5 | [12 empty] | NM | N | 24 Enphase Energy IQ7PLUS-72-x-US (240V) 11 Enphase Energy IQ7PLUS-72-x-US (240V) 1TESLAPowerwall 2 AC | 2020-12-08 | 2020-12-11 | 3 | 2020-12-11 | [14 empty] | 2021-05-07 | 2021-05-07 |  | Y
Central Hudson |  | Gottschalk Solutions, LLC | CH-13108 | Poughkeepsie | Lagrangeville | Dutchess | 12540 | G | 6052 | Todd Hill | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2020-12-08 | 2020-12-10 | 2 | 2020-12-10 | [14 empty] | 2020-12-29 | 2020-12-29 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-13107 | Kingston | Cragsmoor |  | 12420 | G | 3078 | Greenfield Rd | N |  | 15.2 | [13 empty] | NM | N | 2 SolarEdge Technologies SE7600H-US (240V) | 2020-12-08 | 2020-12-10 | 2 | 2020-12-10 | [8 empty] | 350 | 350 |  | 2020-12-14 | 2020-12-14 | 2021-03-11 |  |  |  | W
Central Hudson |  | KASSELMAN SOLAR | CH-13112 | Catskill | Athens | Greene | 12015 | G | 1074 | Coxsackie | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2020-12-09 | 2020-12-11 | 2 | 2020-12-11 | [14 empty] | 2021-02-05 | 2021-02-05 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-13116 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6002 | Reynolds Hill | N |  | 3.84 | [13 empty] | NM | N | 16 Enphase Energy IQ7-60-x-US (240V) | 2020-12-09 | 2020-12-11 | 2 | 2020-12-11 | [14 empty] | 2021-09-14 | 2021-09-21 |  | Y
Central Hudson |  | PlugPV LLC | CH-13114 | Newburgh | Newburgh | Orange | 12550 | G | 4023 | Coldenham | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2020-12-09 | 2020-12-11 | 2 | 2020-12-11 | [14 empty] | 2021-01-26 | 2021-01-26 |  | Y
Central Hudson |  | New York State Solar Farm | CH-13118 | Newburgh | New Paltz | Ulster | 12561 | G | 5024 | Ohioville | N |  | 6.282 | [13 empty] | NM | N | 18 SunPower SPR-A400-G-AC (240V) | 2020-12-09 | 2020-12-11 | 2 | 2020-12-11 | [14 empty] | 2020-12-31 | 2020-12-31 |  | Y
Central Hudson |  | PlugPV LLC | CH-13113 | Newburgh | Newburgh | Orange | 12550 | G | 4011 | West Balmville | N |  | 15.2 | [13 empty] | NM | N | 2 SolarEdge Technologies SE7600H-US (240V) | 2020-12-09 | 2020-12-11 | 2 | 2020-12-11 | [14 empty] | 2021-02-10 | 2021-02-10 |  | Y
Central Hudson |  | Lighthouse Solar | CH-13111 | Newburgh | Highland | Ulster | 12528 | G | 5083 | Highland | N |  | 10.4 | [13 empty] | NM | N | 36 Enphase Energy IQ7PLUS-72-x-US (240V) | 2020-12-09 | 2020-12-11 | 2 | 2020-12-11 | [14 empty] | 2021-01-27 | 2021-01-27 |  | Y
Central Hudson |  | Lighthouse Solar | CH-13110 | Kingston | Kerhonkson | Ulster | 12446 | G | 3081 | Kerhonkson | N | CH-11132 | 8.7 | [13 empty] | NM | N | 30 Enphase Energy IQ7PLUS-72-x-US (240V) | 2020-12-29 | 2021-01-04 | 3 | 2021-01-04 | [14 empty] | 2021-01-26 | 2021-01-26 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-13115 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6062 | Inwood Ave | N |  | 13.05 | [13 empty] | NM | N | 45 Enphase Energy IQ7PLUS-72-x-US (240V) | 2020-12-09 | 2020-12-11 | 2 | 2020-12-11 | [14 empty] | 2021-01-21 | 2021-01-21 |  | Y
Central Hudson |  | Tesla | CH-13117 | Fishkill | Poughkeepsie | Dutchess | 12601 | G | 8021 | Knapps Corners | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2020-12-09 | 2020-12-11 | 2 | 2020-12-11 | [14 empty] | 2021-01-05 | 2021-01-05 |  | Y
Central Hudson |  | SunCommon | CH-13119 | Kingston | Hurley | Ulster | 12443 | G | 2094 | Hurley Ave | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2020-12-10 | 2020-12-11 | 1 | 2020-12-11 | [14 empty] | 2021-01-11 | 2021-01-11 |  | Y
Central Hudson |  | New York State Solar Farm | CH-13121 | Fishkill | Garrison | Putnam | 10524 | G | 8066 | Merritt Park | N |  | 6.3 | [13 empty] | NM | N | 20 SunPower SPR-E19-320-E-AC (240V) | 2020-12-14 | 2020-12-14 | 0 | 2020-12-14 | [14 empty] | 2021-02-12 | 2021-02-12 |  | Y
Central Hudson |  | Tesla | CH-13120 | Kingston | Saugerties | Ulster | 12477 | G | 3004 | Saugerties | Y |  | 7.6 | 10 | [12 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) 2TeslaAC Powerwall 2.0 | 2020-12-10 | 2020-12-11 | 1 | 2020-12-11 | [14 empty] | 2020-12-15 | 2020-12-15 |  | Y
Central Hudson |  | IPPsolar Intergration LLC | CH-13122 | Kingston | Ulster |  | 12401 | G | 2014 | Lincoln Park | N |  | 5000 | [13 empty] | CDG | Y | 50 SMA America STP50-US-40 (480V) [SI1] 50 SMA America STP50-US-40 (480V) [SI1] | 2021-01-08 | 2021-01-22 | 10 | 2021-01-22 | 2021-01-22 | 2021-02-12 | 15 |  |  |  |  | 17500 | [9 empty] | W
Central Hudson |  | PLUGPV | CH-13123 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6097 | Manchester | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2020-12-11 | 2020-12-14 | 1 | 2020-12-14 | [14 empty] | 2021-03-09 | 2021-03-09 |  | Y
Central Hudson |  | Tesla | CH-13124 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8051 | North Chelsea | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2020-12-22 | 2020-12-23 | 1 | 2020-12-23 | [14 empty] | 2021-01-29 | 2021-01-29 |  | Y
Central Hudson |  | Tesla Energy Operations, Inc. | CH-13129 | Fishkill | Beacon | Dutchess | 12508 | G | 8018 | Forgebrook | N |  | 7.68 | [13 empty] | NM | N | 1 Delta Electronics M8-TL-US (240V) [SI1] | 2020-12-14 | 2020-12-15 | 1 | 2020-12-15 | [14 empty] | 2020-12-28 | 2020-12-28 |  | Y
Central Hudson |  | Tesla | CH-13128 | Newburgh | New Windsor | Orange | 12553 | G | 4097 | Bethlehem Rd | N | CH-05181 | 3.8 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3800H-US (240V) | 2020-12-14 | 2020-12-15 | 1 | 2020-12-15 | [14 empty] | 2021-02-16 | 2021-02-16 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-13125 | Newburgh | Newburgh | Orange | 12550 | G | 5004 | Marlboro | N |  | 8.64 | [13 empty] | NM | N | 36 Enphase Energy IQ7-60-x-US (240V) | 2020-12-11 | 2020-12-14 | 1 | 2020-12-14 | [14 empty] | 2021-02-12 | 2021-02-12 |  | Y
Central Hudson |  | PlugPV LLC | CH-13127 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6097 | Manchester | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2020-12-14 | 2020-12-15 | 1 | 2020-12-15 | [14 empty] | 2021-02-19 | 2021-02-19 |  | Y
Central Hudson |  | PlugPV LLC | CH-13126 | Newburgh | Gardiner | Ulster | 12525 | G | 5033 | Galeville | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000H-US (240V) | 2020-12-14 | 2020-12-14 | 0 | 2020-12-14 | [14 empty] | 2021-02-16 | 2021-02-16 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-13130 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8091 | Fishkill Plains | N |  | 15.6 | [13 empty] | NM | N | 20 Enphase Energy IQ7-60-x-US (240V) 15 Enphase Energy IQ7-60-x-US (240V) 30 Enphase Energy IQ7-60-x-US (240V) | 2020-12-15 | 2020-12-16 | 1 | 2020-12-16 | [8 empty] | 350 | 350 |  | 2021-01-08 | 2021-01-08 | 2021-01-14 | 2021-03-09 | 2021-03-09 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-13134 | Newburgh | Newburgh | Orange | 12550 | G | 4023 | Coldenham | N |  | 11.31 | [13 empty] | NM | N | 39 Enphase Energy IQ7PLUS-72-x-US (240V) | 2020-12-15 | 2020-12-16 | 1 | 2020-12-16 | [14 empty] | 2021-01-07 | 2021-01-07 |  | Y
Central Hudson |  | Seed Solar | CH-13132 | Kingston | Woodstock | Ulster | 12498 | G | 3014 | Woodstock | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000H-US (240V) | 2021-01-13 | 2021-01-14 | 1 | 2021-01-14 | [14 empty] | 2021-04-09 | 2021-04-09 |  | Y
Central Hudson |  | Seed Solar | CH-13131 | Kingston | Woodstock | Ulster | 12498 | G | 3014 | Woodstock | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2021-01-13 | 2021-01-14 | 1 | 2021-01-14 | [14 empty] | 2021-04-05 | 2021-04-05 |  | Y
Central Hudson |  | Trinity Solar | CH-13133 | Kingston | Saugerties | Ulster | 12477 | G | 3001 | Saugerties | N |  | 3.8 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3800H-US (240V) | 2020-12-15 | 2020-12-15 | 0 | 2020-12-15 | [14 empty] | 2021-01-21 | 2021-01-21 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-13137 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6093 | Manchester | N |  | 13.05 | [13 empty] | NM | N | 45 Enphase Energy IQ7PLUS-72-x-US (240V) | 2020-12-16 | 2020-12-17 | 1 | 2020-12-17 | [14 empty] | 2020-12-23 | 2020-12-23 |  | Y
Central Hudson |  | SunCommon | CH-13135 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7053 | Rhinebeck | N |  | 11.02 | [13 empty] | NM | N | 38 Enphase Energy IQ7PLUS-72-x-US (240V) | 2020-12-16 | 2020-12-17 | 1 | 2020-12-17 | [8 empty] | 350 | 350 |  | 2021-01-15 | 2021-01-15 | 2021-02-04 | 2021-02-08 | 2021-02-08 |  | Y
Central Hudson |  | SunCommon | CH-13136 | Kingston | Woodstock | Ulster | 12498 | G | 3014 | Woodstock | Y |  | 7.6 | 10 | [12 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) 2TeslaPowerwall | 2020-12-17 | 2020-12-17 | 0 | 2020-12-17 | [14 empty] | 2021-05-04 | 2021-05-04 |  | Y
Central Hudson |  | SunCommon | CH-13138 | Catskill | Catskill | Greene | 12414 | G | 2004 | North Catskill | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE11400H-US (240V) | 2021-01-25 | 2021-02-04 | 8 | 2021-02-04 | [14 empty] | 2021-06-07 | 2021-06-07 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-13145 | Kingston | Saugerties | Ulster | 12477 | G | 3001 | Saugerties | N |  | 6.72 | [13 empty] | NM | N | 28 Enphase Energy IQ7-60-x-US (240V) | 2020-12-17 | 2020-12-18 | 1 | 2020-12-18 | [14 empty] | 2021-01-08 | 2021-01-08 |  | Y
Central Hudson |  | New York State Solar Farm | CH-13141 | Kingston | Napanoch | Ulster | 12458 | G | 3072 | Honk Falls | N | CH-13141 | 11.025 | [13 empty] | NM | N | 35 SunPower SPR-E20-327-E-AC (240V) | 2020-12-17 | 2020-12-17 | 0 | 2020-12-17 | [8 empty] | 350 | 350 |  | 2021-02-03 | 2021-02-03 | 2021-03-12 | 2021-03-19 | 2021-03-19 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-13142 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8096 | Fishkill Plains | Y |  | 7.6 | 7.6 | [12 empty] | NM | N | 1 Generac Power Systems X7602 (240V) 1GeneracPWRCell X7602 | 2020-12-18 | 2020-12-21 | 1 | 2020-12-21 | [14 empty] | 2021-02-17 | 2021-02-17 |  | Y
Central Hudson |  | Tesla Energy Operations, Inc. | CH-13144 | Newburgh | Wallkill | Ulster | 12589 | G | 5013 | Modena | Y |  | 7.68 | 10 | [12 empty] | NM | N | 1 Delta Electronics M8-TL-US (240V) [SI1] 2TeslaAC Powerwall 2.0 | 2020-12-17 | 2020-12-18 | 1 | 2020-12-18 | [14 empty] | 2020-12-31 | 2020-12-31 |  | Y
Central Hudson |  | Tesla | CH-13139 | Newburgh | New Windsor | Orange | 12553 | G | 4094 | Bethlehem Rd | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2020-12-17 | 2020-12-17 | 0 | 2020-12-17 | [14 empty] | 2021-01-08 | 2021-01-08 |  | Y
Central Hudson |  | New York State Solar Farm | CH-13140 | Newburgh | Plattekill | Ulster | 12568 | G | 5012 | Modena | N |  | 6.98 | [13 empty] | NM | N | 20 SunPower SPR-A420-G-AC (240V) | 2020-12-17 | 2020-12-17 | 0 | 2020-12-17 | [14 empty] | 2021-01-20 | 2021-01-20 |  | Y
Central Hudson |  | Tesla | CH-13143 | Catskill | Acra | Greene | 12405 | G | 2041 | South Cairo | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2020-12-17 | 2020-12-17 | 0 | 2020-12-17 | [14 empty] | 2021-01-28 | 2021-01-28 |  | Y
Central Hudson |  | Tesla Energy Operations, Inc. | CH-13149 | Newburgh | Gardiner | Ulster | 12525 | G | 5031 | Galeville | Y |  | 11.52 | 15 | [12 empty] | NM | N | 1 Delta Electronics M4-TL-US (240V) [SI1] 1 Delta Electronics M8-TL-US (240V) [SI1] 3TeslaAC Powerwall 2.0 | 2020-12-18 | 2020-12-21 | 1 | 2020-12-21 | [8 empty] | 350 | 350 |  | 2021-02-11 | 2021-02-11 | 2021-02-23 | 2021-03-29 | 2021-03-29 |  | Y
Central Hudson |  | Solar Generation | CH-13148 | Kingston | Bearsvl | Ulster | 12409 | G | 3012 | Woodstock | N |  | 9.135 | [13 empty] | NM | N | 29 Enphase Energy IQ7X-96-x-US (240V) | 2020-12-18 | 2020-12-18 | 0 | 2020-12-18 | [8 empty] | 350 | 350 |  | 2020-12-23 | 2020-12-23 | 2021-02-20 | 2021-03-11 | 2021-03-11 |  | Y
Central Hudson |  | PlugPV LLC | CH-13150 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6043 | Spackenkill | N |  | 3.8 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3800H-US (240V) | 2020-12-18 | 2020-12-21 | 1 | 2020-12-21 | [14 empty] | 2021-03-31 | 2021-03-31 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-13154 | Fishkill | Wappingers Falls | Dutchess | 12590 | G | 8052 | North Chelsea | Y |  | 10.56 | 5 | [12 empty] | NM | N | 1 Delta Electronics E6-TL-US (240V) [SI1] 1 Delta Electronics M5-TL-US (240V) [SI1] 1Delta ElectronicsE6-TL-US | 2020-12-22 | 2020-12-29 | 3 | 2020-12-29 | [14 empty] | 2021-03-29 | 2021-03-29 |  | Y
Central Hudson |  | Lighthouse Solar | CH-13146 | Fishkill | Stormvl | Dutchess | 12582 | G | 8093 | Fishkill Plains | N |  | 7.2 | [13 empty] | NM | N | 25 Enphase Energy IQ7PLUS-72-x-US (240V) | 2020-12-18 | 2020-12-18 | 0 | 2020-12-18 | [14 empty] | 2021-03-03 | 2021-03-03 |  | Y
Central Hudson |  | Tesla Energy Operations, Inc. | CH-13147 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8023 | Knapps Corners | N |  | 22.8 | [13 empty] | NM | N | 2 SolarEdge Technologies SE11400H-US (240V) | 2020-12-18 | 2020-12-18 | 0 | 2020-12-18 | [8 empty] | 350 | 350 |  | 2020-12-31 | 2020-12-31 | 2021-01-07 | 2021-01-14 | 2021-01-14 |  | Y
Central Hudson |  | Lighthouse Solar | CH-13151 | Kingston | Rosendale | Ulster | 12472 | G | 3021 | High Falls | N |  | 6.96 | [13 empty] | NM | N | 24 Enphase Energy IQ7PLUS-72-x-US (240V) | 2020-12-18 | 2020-12-21 | 1 | 2020-12-21 | [14 empty] | 2021-02-03 | 2021-02-03 |  | Y
Central Hudson |  | Borrego Solar Systems, Inc | CH-13152 | Newburgh | New Paltz |  | 12561 | G | 5024 | Ohioville | Y |  | 5000 | [13 empty] | CDG | Y | 40Chint Power SystemsCPS SCA125KTL-DO/US-600 | 2021-02-17 | 2021-02-25 | 6 | 2021-02-25 | 2021-02-25 | 2021-03-12 | 11 | [14 empty] | W
Central Hudson |  | Borrego Solar Systems, Inc | CH-13153 | Kingston | Saugerties |  | 12477 | G | 3003 | Saugerties | N |  | 5000 | [13 empty] | CDG | Y | 40Chint Power SystemsCPS SCA125KTL-DO/US-600 | 2021-02-17 | 2021-02-25 | 6 | 2021-02-25 | 2021-02-25 | 2021-03-16 | 13 |  |  |  |  | 18000 | [9 empty] | W
Central Hudson |  | Empire Solar Solutions | CH-13157 | Newburgh | Cornwall | Orange | 12518 | G | 4041 | Union Ave | N |  | 6.09 | [13 empty] | NM | N | 21 Enphase Energy IQ7PLUS-72-x-US (240V) | 2020-12-21 | 2020-12-21 | 0 | 2020-12-21 | [14 empty] | 2021-01-06 | 2021-01-06 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-13156 | Newburgh | Newburgh | Orange | 12550 | G | 4011 | West Balmville | N |  | 7.25 | [13 empty] | NM | N | 25 Enphase Energy IQ7PLUS-72-x-US (240V) | 2020-12-21 | 2020-12-21 | 0 | 2020-12-21 | [17 empty] | W
Central Hudson |  | New York State Solar Farm | CH-13159 | Fishkill | Beacon | Dutchess | 12508 | G | 8013 | Forgebrook | N |  | 15 | [13 empty] | NM | Y | 3 SolarEdge Technologies SE5000H-US (240V) | 2021-01-12 | 2021-01-14 | 2 | 2021-01-14 | [14 empty] | 2021-03-12 | 2021-03-12 |  | Y | Y
Central Hudson |  | PlugPV, LLC. | CH-13158 | Newburgh | Newburgh | Orange | 12550 | G | 5001 | Marlboro | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE11400H-US (240V) | 2020-12-21 | 2020-12-21 | 0 | 2020-12-21 | [14 empty] | 2021-01-28 | 2021-01-28 |  | Y
Central Hudson |  | Gottschalk Solutions, LLC | CH-13160 | Newburgh | Walden | Orange | 12586 | G | 5041 | East Walden | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2020-12-31 | 2021-01-04 | 1 | 2021-01-04 | [14 empty] | 2021-01-20 | 2021-01-20 |  | Y
Central Hudson |  | Tesla | CH-13155 | Poughkeepsie | Staatsburg | Dutchess | 12580 | G | 7041 | Staatsburg | Y |  | 3.8 | 5 | [12 empty] | NM | N | 1 SolarEdge Technologies SE3800H-US (240V) 1TeslaAC Powerwall | 2020-12-21 | 2020-12-21 | 0 | 2020-12-21 | [14 empty] | 2021-02-02 | 2021-02-02 |  | Y
Central Hudson |  | SunCommon | CH-13162 | Catskill | Purling | Greene | 12470 | G | 2042 | South Cairo | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2020-12-23 | 2020-12-29 | 2 | 2020-12-29 | [14 empty] | 2021-05-14 | 2021-05-14 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-13169 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 7024 | Tinkertown | Y |  | 7.68 | 7.68 | [12 empty] | NM | N | 1 Delta Electronics E8-TL-US (240V) [SI1] 1Delta ElectronicsE8-TL-US | 2020-12-29 | 2021-01-04 | 3 | 2021-01-04 | [14 empty] | 2021-03-01 | 2021-03-01 |  | Y
Central Hudson |  | SunCommon | CH-13161 | Kingston | Woodstock | Ulster | 12498 | G | 3012 | Woodstock | Y | CH-13161 | 7.6 | 5 | [12 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) 1TeslaPowerwall | 2020-12-22 | 2020-12-23 | 1 | 2020-12-23 | [14 empty] | 2021-03-26 | 2021-03-26 |  | Y
Central Hudson |  | Tesla | CH-13165 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8043 | Myers Corners | Y |  | 7.6 | 10 | [12 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) 2TeslaAC Powerwall 2.0 | 2020-12-22 | 2020-12-23 | 1 | 2020-12-23 | [14 empty] | 2021-01-12 | 2021-01-12 |  | Y
Central Hudson |  | Tesla | CH-13163 | Fishkill | Garrison | Putnam | 10524 | G | 8086 | Tioronda | Y |  | 13.8 | 15 | [12 empty] | NM | N | 1 SolarEdge Technologies SE3800H-US (240V) [SI1] 1 SolarEdge Technologies SE10000H-US (240V) 3TeslaAC Powerwall 2.0 | 2020-12-22 | 2020-12-23 | 1 | 2020-12-23 | [14 empty] | 2021-07-08 | 2021-07-08 |  | Y
Central Hudson |  | Hudson River Renewables LLC | CH-13166 | Catskill | Catskill | Greene | 12414 | G | 2001 | North Catskill | Y |  | 9 | 9 | [12 empty] | NM | N | 1 Sol-Ark Sol-Ark-12K-P (240V) 1Sol-ArkSol-Ark 12K-P (240V) | 2020-12-23 | 2020-12-29 | 2 | 2020-12-29 | [14 empty] | 2021-03-29 | 2021-03-29 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-13167 | Newburgh | Newburgh | Orange | 12550 | G | 4012 | West Balmville | N |  | 15.2 | [13 empty] | NM | N | 2 SolarEdge Technologies SE7600H-US (240V) | 2020-12-22 | 2020-12-29 | 3 | 2020-12-29 | [14 empty] | 2020-12-31 | 2020-12-31 |  | Y
Central Hudson |  | New York State Solar Farm | CH-13168 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 7041 | Staatsburg | N |  | 11.866 | [13 empty] | NM | N | 34 SunPower SPR-A400-G-AC (240V) | 2020-12-22 | 2020-12-29 | 3 | 2020-12-29 | [14 empty] | 2021-02-12 | 2021-02-12 |  | Y
Central Hudson |  | Tesla | CH-13175 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6092 | Manchester | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2020-12-23 | 2020-12-29 | 2 | 2020-12-29 | [14 empty] | 2021-01-06 | 2021-01-06 |  | Y
Central Hudson |  | PlugPV LLC | CH-13171 | Catskill | Palenvl | Greene | 12463 | G | 2001 | North Catskill | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000H-US (240V) | 2020-12-23 | 2020-12-29 | 2 | 2020-12-29 | [14 empty] | 2021-01-25 | 2021-01-25 |  | Y
Central Hudson |  | Solar Generation | CH-13174 | Kingston | Woodstock | Ulster | 12498 | G | 3014 | Woodstock | N |  | 7.6 | [13 empty] | NM | N | 1 Generac Power Systems X7602 (240V) | 2021-01-13 | 2021-01-14 | 1 | 2021-01-14 | [14 empty] | 2021-02-25 | 2021-02-25 |  | Y
Central Hudson |  | Solar Generation | CH-13173 | Catskill | Palenvl | Greene | 12463 | G | 2001 | North Catskill | N |  | 7.6 | [13 empty] | NM | N | 1 Generac Power Systems X7602 (240V) | 2020-12-23 | 2020-12-29 | 2 | 2020-12-29 | [14 empty] | 2021-03-16 | 2021-03-16 |  | Y
Central Hudson |  | Solar Generation | CH-13172 | Catskill | Palenville | Greene | 12463 | G | 2001 | North Catskill | N |  | 24 | [13 empty] | NM | N | 2 Fronius USA Fronius Symo 12.0-3 208-240 (208V) | 2021-01-07 | 2021-01-07 | 0 | 2021-01-07 | [14 empty] | 2021-03-19 | 2021-03-19 |  | Y
Central Hudson |  | PlugPV LLC | CH-13177 | Newburgh | Newburgh | Orange | 12550 | G | 5004 | Marlboro | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE11400H-US (240V) | 2020-12-23 | 2020-12-29 | 2 | 2020-12-29 | [14 empty] | 2021-02-24 | 2021-02-24 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-13170 | Kingston | New Paltz |  | 12561 | G | 3041 | Sturgeon Pool | Y |  | 7.6 | 7.6 | [12 empty] | NM | N | 1 Generac Power Systems X7602 (240V) 1GeneracPWRCell X7602 | 2020-12-23 | 2020-12-29 | 2 | 2020-12-29 | [17 empty] | W
Central Hudson |  | KASSELMAN SOLAR | CH-13176 | Catskill | Jewett | Greene | 12444 | E | 2389 | Vinegar Hill | N |  | 3.8 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3800H-US (240V) 1SolarEdgeSE3800H-US | 2021-01-07 | 2021-01-07 | 0 | 2021-01-07 | [14 empty] | 2021-02-26 | 2021-02-26 |  | Y
Central Hudson |  | PlugPV | CH-13178 | Poughkeepsie | Millbrook | Dutchess | 12545 | G | 7025 | Tinkertown | N |  | 15 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000H-US (240V) [SI1] 1 SolarEdge Technologies SE10000H-US (240V) | 2020-12-28 | 2020-12-30 | 2 | 2020-12-30 | [14 empty] | 2021-01-29 | 2021-01-29 |  | Y
Central Hudson |  | PlugPV, LLC. | CH-13179 | Poughkeepsie | Lagrangevl | Dutchess | 12540 | G | 6053 | Todd Hill | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2020-12-28 | 2020-12-30 | 2 | 2020-12-30 | [14 empty] | 2021-02-17 | 2021-02-17 |  | Y
Central Hudson |  | Solar Alchemy, Inc. | CH-13182 | Kingston | Kerhonkson |  | 12446 | G | 3082 | Kerhonkson | Y |  | 8 | 8 | [12 empty] | NM | N | 1 OutBack Power Technologies GS8048A 1Outback PowerGS8048A FlexPower Radian | 2021-01-19 | 2021-01-19 | 0 | 2021-01-19 | [17 empty] | W
Central Hudson |  | Empire Solar Solutions | CH-13180 | Kingston | New Paltz | Ulster | 12561 | G | 3022 | High Falls | N |  | 5.22 | [13 empty] | NM | N | 18 Enphase Energy IQ7PLUS-72-x-US (240V) | 2020-12-28 | 2020-12-30 | 2 | 2020-12-30 | [14 empty] | 2021-01-15 | 2021-01-15 |  | Y
Central Hudson |  | Tesla | CH-13185 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8092 | Fishkill Plains | N |  | 20 | [13 empty] | NM | N | 2 SolarEdge Technologies SE10000H-US (240V) | 2020-12-28 | 2020-12-31 | 3 | 2020-12-31 | [14 empty] | 2021-01-28 | 2021-01-28 |  | Y
Central Hudson |  | New York State Solar Farm, Inc. | CH-13184 | Newburgh | New Windsor | Orange | 12553 | G | 4097 | Bethlehem Rd | N |  | 105 | [13 empty] | RC | Y | 15 SMA America SB7.0-1SP-US-41 (240V) [SI1] | 2021-02-19 | 2021-02-26 | 5 | 2021-02-26 | 2021-02-26 | 2021-03-19 | 15 | [5 empty] | 2939.34 | 3775.17 |  | 2021-06-08 | 2021-06-08 | 2021-09-16 | 2021-09-30 | 2021-09-30 | 2021-10-01 | Y | Y
Central Hudson |  | PlugPV LLC | CH-13183 | Fishkill | Stormvl | Dutchess | 12582 | G | 8093 | Fishkill Plains | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2020-12-28 | 2020-12-30 | 2 | 2020-12-30 | [14 empty] | 2021-02-10 | 2021-02-10 |  | Y
Central Hudson |  | Suncommon | CH-13186 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 6062 | Inwood Ave | Y | CH-01739 |  | 5 | [12 empty] | NM | N | 1TeslaPowerwall 2 | 2020-12-29 | 2020-12-31 | 2 | 2020-12-31 | [14 empty] | 2021-02-10 | 2021-02-10 |  | Y
Central Hudson |  | Trinity Solar | CH-13187 | Newburgh | Newburgh | Orange | 12550 | G | 4023 | Coldenham | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000H-US (240V) | 2020-12-29 | 2020-12-31 | 2 | 2020-12-31 | [14 empty] | 2021-01-27 | 2021-01-27 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-13189 | Newburgh | New Windsor | Orange | 12553 | G | 4095 | Bethlehem Rd | Y |  | 7.68 | 7.68 | [12 empty] | NM | N | 1 Delta Electronics E8-TL-US (240V) [SI1] 1Delta ElectronicsE8-TL-US | 2021-01-04 | 2021-01-05 | 1 | 2021-01-05 | [14 empty] | 2021-03-01 | 2021-03-01 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-13188 | Fishkill | Nelsonvl | Putnam | 10516 | G | 8087 | Tioronda | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE11400H-US (240V) | 2020-12-29 | 2020-12-31 | 2 | 2020-12-31 | [14 empty] | 2021-03-01 | 2021-03-01 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-13191 | Newburgh | Montgomery | Orange | 12549 | G | 5073 | Montgomery | N |  | 6.96 | [13 empty] | NM | N | 29 Enphase Energy IQ7-60-x-US (240V) | 2020-12-29 | 2021-01-04 | 3 | 2021-01-04 | [14 empty] | 2021-02-18 | 2021-02-18 |  | Y
Central Hudson |  | PlugPV LLC | CH-13190 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2020-12-29 | 2021-01-04 | 3 | 2021-01-04 | [14 empty] | 2021-01-29 | 2021-01-29 |  | Y
Central Hudson |  | CBH Electric | CH-13192 | Catskill | Durham | Greene | 12422 | G | 1092 | Westerlo | N |  | 24 | [13 empty] | NM | N | 3 SMA America SB8000TL-US-12 (240V) | 2021-01-05 | 2021-01-06 | 1 | 2021-01-06 | [8 empty] | 350 | 350 |  | 2021-01-08 | 2021-01-08 | 2021-01-14 | 2024-04-12 | 2024-04-15 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-13193 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6056 | Todd Hill | N | CH-13193 | 8.7 | [13 empty] | NM | N | 30 Enphase Energy IQ7PLUS-72-x-US (240V) | 2020-12-31 | 2021-01-04 | 1 | 2021-01-04 | [14 empty] | 2021-02-25 | 2021-02-25 |  | Y
Central Hudson |  | KASSELMAN SOLAR | CH-13194 | Catskill | Westerlo | Albany | 12193 | G | 1092 | Westerlo | N | CH-13194 | 11.4 | [13 empty] | NM | Y | 1 SolarEdge Technologies SE11400H-US (240V) | 2021-01-04 | 2021-01-05 | 1 | 2021-01-05 | [14 empty] | 2021-01-11 | 2021-01-11 |  | Y | Y
Central Hudson |  | Solar Generation | CH-13199 | Kingston | Woodstock | Ulster | 12498 | G | 3013 | Woodstock | N |  | 23.04 | [13 empty] | NM | N | 3 SMA America SB7700TL-US-22 (240V) | 2021-01-07 | 2021-01-08 | 1 | 2021-01-08 | [14 empty] | 2021-04-21 | 2021-04-21 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-13197 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6052 | Todd Hill | N |  | 6.96 | [13 empty] | NM | N | 24 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-01-04 | 2021-01-05 | 1 | 2021-01-05 | [14 empty] | 2021-02-22 | 2021-02-22 |  | Y
Central Hudson |  | SunCommon | CH-13196 | Kingston | Woodstock | Ulster | 12498 | G | 3012 | Woodstock | N |  | 12 | [13 empty] | NM | N | 2SolarEdgeSE6000H-US | 2021-01-27 | 2021-01-27 | 0 | 2021-01-27 | [14 empty] | 2021-05-28 | 2021-05-28 |  | Y
Central Hudson |  | KASSELMAN SOLAR | CH-13195 | Catskill | Coeymans Holw | Albany | 12046 | G | 1081 | New Baltimore | N |  | 9 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3000H-US (240V) 1 SolarEdge Technologies SE6000H-US (240V) | 2021-01-04 | 2021-01-05 | 1 | 2021-01-05 | [14 empty] | 2021-01-21 | 2021-01-21 |  | Y
Central Hudson |  | PlugPV LLC | CH-13198 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6046 | Spackenkill | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2021-01-04 | 2021-01-05 | 1 | 2021-01-05 | [14 empty] | 2021-03-30 | 2021-03-30 |  | Y
Central Hudson |  | Sunrun Installation Service, Inc. | CH-13201 | Newburgh | Newburgh | Orange | 12550 | G | 5041 | East Walden | N |  | 11.31 | [13 empty] | NM | N | 39 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-01-05 | 2021-01-06 | 1 | 2021-01-06 | [14 empty] | 2021-03-25 | 2021-03-25 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-13204 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8072 | Shenandoah | Y |  | 16.32 | 5.76 | [12 empty] | NM | N | 1 Delta Electronics E6-TL-US (240V) [SI1] 1 Delta Electronics M6-TL-US (240V) [SI1] 1 Delta Electronics M5-TL-US (240V) [SI1] 1Delta ElectronicsE6-TL-US | 2021-01-14 | 2021-01-15 | 1 | 2021-01-15 | [14 empty] | 2021-03-11 | 2021-03-11 |  | Y
Central Hudson |  | SunCommon | CH-13202 | Kingston | Olive Brdg | Ulster | 12461 | G | 3024 | High Falls | Y | CH-01649 |  | 5 | [12 empty] | NM | N | 1TeslaPowerwall | 2021-01-05 | 2021-01-06 | 1 | 2021-01-06 | [14 empty] | 2021-03-10 | 2021-03-10 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-13203 | Poughkeepsie | Hyde Pk |  | 12538 | G | 6073 | East Park | Y | CH-11856 | 3.84 | 3.84 | [12 empty] | NM | N | 1 Delta Electronics E4-TL-US (240V) [SI1] 1Delta ElectronicsE4-TL-US | 2021-01-14 | 2021-01-15 | 1 | 2021-01-15 | [17 empty] | W
Central Hudson |  | Empire Solar Solutions | CH-13200 | Newburgh | Wallkill | Ulster | 12589 | G | 4011 | West Balmville | N |  | 8.41 | [13 empty] | NM | N | 29 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-01-05 | 2021-01-06 | 1 | 2021-01-06 | [14 empty] | 2021-02-04 | 2021-02-04 |  | Y
Central Hudson |  | Trinity Solar | CH-13205 | Newburgh | Newburgh | Orange | 12550 | G | 4023 | Coldenham | N |  | 3 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3000H-US (240V) | 2021-01-06 | 2021-01-06 | 0 | 2021-01-06 | [14 empty] | 2021-02-08 | 2021-02-08 |  | Y
Central Hudson |  | PlugPV LLC | CH-13206 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6068 | Inwood Ave | N |  | 3.8 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3800H-US (240V) | 2021-01-06 | 2021-01-06 | 0 | 2021-01-06 | [14 empty] | 2021-03-10 | 2021-03-10 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-13207 | Poughkeepsie | Rhinebeck |  | 12572 | G | 7053 | Rhinebeck | N |  | 20.3 | [13 empty] | NM | N | 70 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-01-12 | 2021-01-12 | 0 | 2021-01-12 | [17 empty] | W
Central Hudson |  | Apex Solar Power | CH-13208 | Catskill | W Coxsackie | Greene | 12192 | G | 1076 | Coxsackie | N |  | 6.8 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3800H-US (240V) 1 SolarEdge Technologies SE3000H-US (240V) | 2021-02-10 | 2021-02-10 | 0 | 2021-02-10 | [14 empty] | 2021-12-28 | 2021-12-28 |  | Y
Central Hudson |  | PlugPV, LLC | CH-13209 | Newburgh | Marlboro | Ulster | 12542 | G | 5004 | Marlboro | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) [SI1] | 2021-01-07 | 2021-01-07 | 0 | 2021-01-07 | [14 empty] | 2021-02-18 | 2021-02-18 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-13217 | Newburgh | Highland | Ulster | 12528 | G | 5084 | Highland | N |  | 2.88 | [13 empty] | NM | N | 12 Enphase Energy IQ7-60-x-US (240V) | 2021-01-08 | 2021-01-11 | 1 | 2021-01-11 | [14 empty] | 2021-02-10 | 2021-02-10 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-13216 | Poughkeepsie | Salt Pt | Dutchess | 12578 | G | 7011 | Hibernia | N |  | 6.38 | [13 empty] | NM | N | 22 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-01-08 | 2021-01-11 | 1 | 2021-01-11 | [14 empty] | 2021-05-10 | 2021-05-10 |  | Y
Central Hudson |  | PlugPV LLC | CH-13210 | Newburgh | Wallkill | Ulster | 12589 | G | 5042 | East Walden | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2021-01-08 | 2021-01-08 | 0 | 2021-01-08 | [14 empty] | 2021-03-05 | 2021-03-05 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-13215 | Newburgh | New Windsor | Orange | 12553 | G | 4054 | Union Ave | N |  | 10.32 | [13 empty] | NM | N | 43 Enphase Energy IQ7-60-x-US (240V) | 2021-01-08 | 2021-01-11 | 1 | 2021-01-11 | [14 empty] | 2021-02-23 | 2021-02-23 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-13211 | Fishkill | Poughkeepsie | Dutchess | 12603 | G | 8024 | Knapps Corners | N |  | 10.44 | [13 empty] | NM | N | 36 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-01-08 | 2021-01-08 | 0 | 2021-01-08 | [14 empty] | 2021-03-19 | 2021-03-19 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-13214 | Newburgh | Walden | Orange | 12586 | G | 5041 | East Walden | N |  | 8.4 | [13 empty] | NM | N | 29 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-01-08 | 2021-01-11 | 1 | 2021-01-11 | [14 empty] | 2021-02-05 | 2021-02-05 |  | Y
Central Hudson |  | Solar Generation | CH-13212 | Kingston | Bloomington | Ulster | 12411 | G | 1011 | Boulevard | N |  | 7.6 | [13 empty] | NM | N | 1 Generac Power Systems X7602 (240V) | 2021-01-08 | 2021-01-08 | 0 | 2021-01-08 | [14 empty] | 2021-03-16 | 2021-03-16 |  | Y
Central Hudson |  | KASSELMAN SOLAR | CH-13219 | Catskill | Catskill |  | 12414 | G | 2042 | South Cairo | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2021-01-11 | 2021-01-12 | 1 | 2021-01-12 | [14 empty] | 2021-01-20 | 2021-01-20 |  | W
Central Hudson |  | Empire Solar Solutions | CH-13220 | Newburgh | New Windsor | Orange | 12553 | G | 4046 | Union Ave | N |  | 10.15 | [13 empty] | NM | N | 35 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-01-11 | 2021-01-12 | 1 | 2021-01-12 | [14 empty] | 2021-01-29 | 2021-01-29 |  | Y
Central Hudson |  | New York State Solar Farm | CH-13218 | Kingston | Kerhonkson | Ulster | 12446 | G | 3082 | Kerhonkson | Y |  | 6.631 | 5 | [12 empty] | NM | N | 19 SunPower SPR-A420-G-AC (240V) 1TESLATESLA POWERWALL 2 | 2021-01-11 | 2021-01-12 | 1 | 2021-01-12 | [14 empty] | 2021-03-10 | 2021-03-10 |  | Y
Central Hudson |  | PlugPV LLC | CH-13221 | Fishkill | Stormvl | Dutchess | 12582 | G | 8093 | Fishkill Plains | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2021-01-11 | 2021-01-12 | 1 | 2021-01-12 | [14 empty] | 2021-03-10 | 2021-03-10 |  | Y
Central Hudson |  | PlugPV LLC | CH-13222 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6043 | Spackenkill | N |  | 12 | [13 empty] | NM | N | 2 SolarEdge Technologies SE6000H-US (240V) | 2021-01-11 | 2021-01-12 | 1 | 2021-01-12 | [14 empty] | 2021-03-05 | 2021-03-05 |  | Y
Central Hudson |  | Sunrun Inc | CH-13225 | Newburgh | Newburgh | Orange | 12550 | G | 4023 | Coldenham | Y |  | 5.28 | 5 | [12 empty] | NM | N | 22 Enphase Energy IQ7-60-x-US (240V) 1TESLAPowerwall 2 AC | 2021-01-14 | 2021-01-15 | 1 | 2021-01-15 | [14 empty] | 2021-03-11 | 2021-03-11 |  | Y
Central Hudson |  | Lighthouse Solar | CH-13223 | Kingston | Saugerties | Ulster | 12477 | G | 3014 | Woodstock | Y |  | 7.6 | 7.6 | [12 empty] | NM | N | 1 Generac Power Systems X7602 (240V) 1Generac7.6kW X7602 (240v) | 2021-01-12 | 2021-01-12 | 0 | 2021-01-12 | [14 empty] | 2021-03-17 | 2021-03-17 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-13224 | Catskill | Catskill | Greene | 12414 | G | 2003 | North Catskill | N |  | 10.44 | [13 empty] | NM | N | 36 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-01-12 | 2021-01-13 | 1 | 2021-01-13 | [14 empty] | 2021-03-17 | 2021-03-17 |  | Y
Central Hudson |  | Tesla | CH-13257 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6092 | Manchester | N |  | 15.36 | [13 empty] | NM | N | 2 Delta Electronics M8-TL-US (240V) [SI1] | 2021-01-20 | 2021-01-20 | 0 | 2021-01-20 | [14 empty] | 2021-02-12 | 2021-02-12 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-13266 | Kingston | Boicevl |  | 12412 | G | 3011 | Woodstock | Y |  | 5.76 | 5.76 | [12 empty] | NM | N | 1 Delta Electronics E6-TL-US (240V) [SI1] 1Delta ElectronicsE6-TL-US | 2021-01-14 | 2021-01-15 | 1 | 2021-01-15 | [17 empty] | W
Central Hudson |  | New York Power Solutions | CH-13251 | Fishkill | Stormvl | Dutchess | 12582 | G | 8071 | Shenandoah | N |  | 7.54 | [13 empty] | NM | N | 26 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-01-13 | 2021-01-14 | 1 | 2021-01-14 | [14 empty] | 2021-03-23 | 2021-03-23 |  | Y
Central Hudson |  | PlugPV, LLC | CH-13258 | Newburgh | Newburgh | Orange | 12550 | G | 4044 | Union Ave | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2021-01-13 | 2021-01-14 | 1 | 2021-01-14 | [14 empty] | 2021-05-28 | 2021-05-28 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-13246 | Newburgh | New Windsor | Orange | 12553 | G | 4046 | Union Ave | N |  | 6.38 | [13 empty] | NM | N | 22 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-01-13 | 2021-01-14 | 1 | 2021-01-14 | [8 empty] | 350 | 350 |  | 2021-01-18 | 2021-01-18 | 2021-02-04 | 2021-06-16 | 2021-06-16 |  | Y
Central Hudson |  | SunCommon | CH-13290 | Kingston | Bearsvl | Ulster | 12409 | G | 3012 | Woodstock | N |  | 20 | [13 empty] | NM | N | 2 SolarEdge Technologies SE10000H-US (240V) | 2021-01-15 | 2021-01-15 | 0 | 2021-01-15 | [14 empty] | 2021-04-27 | 2021-04-27 |  | Y
Central Hudson |  | SunCommon | CH-13282 | Newburgh | New Paltz | Ulster | 12561 | G | 5031 | Galeville | Y |  | 11.52 | 5 | [12 empty] | NM | N | 1 Delta Electronics M4-TL-US (240V) [SI1] 1 Delta Electronics M8-TL-US (240V) [SI1] 1TeslaPowerwall 2 | 2021-01-14 | 2021-01-15 | 1 | 2021-01-15 | [14 empty] | 2021-04-12 | 2021-04-12 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-13296 | Newburgh | Newburgh | Orange | 12550 | G | 4044 | Union Ave | N |  | 7.68 | [13 empty] | NM | N | 32 Enphase Energy IQ7-60-x-US (240V) | 2021-01-14 | 2021-01-25 | 7 | 2021-01-25 | [14 empty] | 2021-04-22 | 2021-04-22 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-13297 | Newburgh | Cornwall | Orange | 12518 | G | 4094 | Bethlehem Rd | N |  | 7.83 | [13 empty] | NM | N | 27 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-01-14 | 2021-01-15 | 1 | 2021-01-15 | [14 empty] | 2021-02-19 | 2021-02-19 |  | Y
Central Hudson |  | Tesla | CH-13283 | Newburgh | Newburgh | Orange | 12550 | G | 4022 | Coldenham | N |  | 3.8 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3800H-US (240V) [SI1] | 2021-01-14 | 2021-01-14 | 0 | 2021-01-14 | [14 empty] | 2021-02-25 | 2021-02-25 |  | Y
Central Hudson |  | Tesla Energy Operations, Inc. | CH-13303 | Catskill | Rensselaervl | Albany | 12147 | G | 1092 | Westerlo | Y |  | 11.52 | 10 | [12 empty] | NM | N | 1 Delta Electronics M8-TL-US (240V) [SI1] 1 Delta Electronics M4-TL-US (240V) [SI1] 2TeslaAC Powerwall 2.0 | 2021-01-15 | 2021-01-15 | 0 | 2021-01-15 | [14 empty] | 2021-02-05 | 2021-02-05 |  | Y
Central Hudson |  | New York State Solar Farm | CH-13305 | Newburgh | New Paltz | Ulster | 12561 | G | 5011 | Modena | N |  | 23 | [13 empty] | NM | N | 73 SunPower SPR-E20-327-E-AC (240V) | 2021-01-15 | 2021-01-18 | 1 | 2021-01-18 | [8 empty] | 350 | 350 |  | 2021-01-29 | 2021-01-29 | 2021-03-04 | 2021-03-19 | 2021-03-19 |  | Y
Central Hudson |  | New York State Solar Farm | CH-13301 | Kingston | Stone Ridge | Ulster | 12484 | G | 3023 | High Falls | N |  | 12.6 | [13 empty] | NM | N | 40 SunPower SPR-E20-327-E-AC (240V) | 2021-01-15 | 2021-01-15 | 0 | 2021-01-15 | [14 empty] | 2021-05-06 | 2021-05-06 |  | Y
Central Hudson |  | New York State Solar Farm | CH-13307 | Newburgh | Wallkill | Ulster | 12589 | G | 5043 | East Walden | Y |  | 7.33 | 10 | [12 empty] | NM | N | 21 SunPower SPR-A420-G-AC (240V) 2TESLATESLA POWERWALL 2 | 2021-01-18 | 2021-01-18 | 0 | 2021-01-18 | [14 empty] | 2021-03-05 | 2021-03-05 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-13311 | Fishkill | Cold Spg | Putnam | 10516 | G | 8087 | Tioronda | N |  | 11.6 | [13 empty] | NM | N | 40 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-01-18 | 2021-01-19 | 1 | 2021-01-19 | [14 empty] | 2022-01-18 | 2022-01-25 |  | Y
Central Hudson |  | PlugPV, LLC | CH-13312 | Kingston | Grahamsvl |  | 12740 | G | 3091 | Neversink | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2021-01-18 | 2021-01-19 | 1 | 2021-01-19 | [17 empty] | W
Central Hudson |  | PlugPV LLC | CH-13310 | Newburgh | Newburgh | Orange | 12550 | G | 4014 | West Balmville | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2021-01-18 | 2021-01-18 | 0 | 2021-01-18 | [14 empty] | 2021-04-07 | 2021-04-07 |  | Y
Central Hudson |  | PlugPV LLC | CH-13309 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2021-01-18 | 2021-01-18 | 0 | 2021-01-18 | [14 empty] | 2021-03-09 | 2021-03-09 |  | Y
Central Hudson |  | Gottschalk Solutions | CH-13308 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 7024 | Tinkertown | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) [SI1] | 2021-01-18 | 2021-01-29 | 9 | 2021-01-29 | [14 empty] | 2021-02-16 | 2021-02-16 |  | Y
Central Hudson |  | SunCommon | CH-13316 | Kingston | Hurley | Ulster | 12443 | G | 2094 | Hurley Ave | N |  | 7.54 | [13 empty] | NM | N | 26 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-01-19 | 2021-01-20 | 1 | 2021-01-20 | [14 empty] | 2021-03-05 | 2021-03-05 |  | Y
Central Hudson |  | SunCommon | CH-13313 | Fishkill | Beacon | Dutchess | 12508 | G | 8087 | Tioronda | N |  | 4.06 | [13 empty] | NM | N | 14 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-01-19 | 2021-01-19 | 0 | 2021-01-19 | [14 empty] | 2021-03-26 | 2021-03-26 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-13318 | Newburgh | New Windsor | Orange | 12553 | G | 4044 | Union Ave | N |  | 8.12 | [13 empty] | NM | N | 28 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-01-19 | 2021-01-20 | 1 | 2021-01-20 | [14 empty] | 2021-07-06 | 2021-07-06 |  | Y
Central Hudson |  | Solar Generation | CH-13320 | Kingston | Hurley | Ulster | 12443 | G | 2094 | Hurley Ave | N |  | 15.2 | [13 empty] | NM | N | 2 SolarEdge Technologies SE7600H-US (240V) | 2021-01-22 | 2021-01-25 | 1 | 2021-01-25 | [8 empty] | 350 | 350 |  | 2021-01-27 | 2021-01-27 | 2021-03-19 | 2021-03-25 | 2021-03-25 |  | Y
Central Hudson |  | PlugPV LLC | CH-13319 | Newburgh | Rock Tvrn | Orange | 12575 | G | 4097 | Bethlehem Rd | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE11400H-US (240V) | 2021-01-20 | 2021-02-01 | 8 | 2021-02-01 | [14 empty] | 2021-03-16 | 2021-03-16 |  | Y
Central Hudson |  | SunPower Direct (NY) | CH-13321 | Kingston | Kingston |  | 12401 | G | 2017 | Lincoln Park | N |  | 5.584 | [13 empty] | NM | N | 16 Enphase Energy IQ7AS-66-x-ACM-US-y-z-& (240V) [SI1] | 2021-01-20 | 2021-01-21 | 1 | 2021-01-21 | [17 empty] | W
Central Hudson |  | Sunrun Installation Services, Inc. | CH-13323 | Kingston | W Hurley | Ulster | 12491 | G | 2094 | Hurley Ave | N |  | 8.64 | [13 empty] | NM | N | 36 Enphase Energy IQ7-60-x-US (240V) | 2021-01-21 | 2021-01-22 | 1 | 2021-01-22 | [14 empty] | 2021-04-14 | 2021-04-14 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-13322 | Kingston | Grahamsvl | Sullivan | 12740 | G | 3091 | Neversink | N |  | 13.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) 1 SolarEdge Technologies SE6000H-US (240V) | 2021-01-21 | 2021-01-21 | 0 | 2021-01-21 | [14 empty] | 2021-01-21 | 2021-01-21 |  | Y
Central Hudson |  | KASSELMAN SOLAR | CH-13324 | Catskill | Ravena | Albany | 12143 | G | 1081 | New Baltimore | N | CH-23079 | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000H-US {240V} [SI1] | 2021-01-22 | 2021-01-26 | 2 | 2021-01-26 | [14 empty] | 2021-02-04 | 2021-02-04 |  | Y
Central Hudson |  | Lighthouse Solar | CH-13325 | Poughkeepsie | Pine Plns | Dutchess | 12567 | G | 7091 | Pulvers Corners | Y |  | 13.34 | 11.52 | [12 empty] | NM | N | 46 Enphase Energy IQ7PLUS-72-x-US (240V) 3EnphaseEncharge 10 | 2021-01-25 | 2021-01-25 | 0 | 2021-01-25 | [14 empty] | 2021-03-22 | 2021-03-22 |  | Y
Central Hudson |  | PlugPV, LLC | CH-13326 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8092 | Fishkill Plains | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2021-01-22 | 2021-01-28 | 4 | 2021-01-28 | [14 empty] | 2021-04-12 | 2021-04-12 |  | Y
Central Hudson |  | KASSELMAN SOLAR | CH-13331 | Catskill | Athens | Greene | 12015 | G | 1074 | Coxsackie | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE11400H-US (240V) | 2021-01-25 | 2021-01-26 | 1 | 2021-01-26 | [14 empty] | 2021-02-05 | 2021-02-05 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-13327 | Newburgh | Montgomery | Orange | 12549 | G | 5072 | Montgomery | N |  | 8.12 | [13 empty] | NM | N | 28 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-01-25 | 2021-01-25 | 0 | 2021-01-25 | [14 empty] | 2021-03-19 | 2021-03-19 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-13332 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6056 | Todd Hill | N |  | 8.16 | [13 empty] | NM | N | 12 Enphase Energy IQ7-60-x-US (240V) 22 Enphase Energy IQ7-60-x-US (240V) | 2021-01-25 | 2021-01-26 | 1 | 2021-01-26 | [8 empty] | 350 | 350 |  | 2021-01-28 | 2021-01-28 | 2021-02-08 | 2021-05-20 | 2021-05-20 |  | Y
Central Hudson |  | New York State Solar Farm | CH-13328 | Newburgh | New Paltz | Ulster | 12561 | G | 5031 | Galeville | N |  | 43.2 | [13 empty] | NM | N | 1 SolarEdge Technologies SE43.2KUS (208V) | 2021-01-29 | 2021-02-01 | 1 | 2021-02-01 | [14 empty] | 2021-05-26 | 2021-05-26 |  | Y
Central Hudson |  | Solar Generation | CH-13329 | Kingston | Woodstock | Ulster | 12498 | G | 3013 | Woodstock | N |  | 4.06 | [13 empty] | NM | N | 14 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-01-26 | 2021-01-26 | 0 | 2021-01-26 | [14 empty] | 2021-03-16 | 2021-03-16 |  | Y
Central Hudson |  | SunCommon | CH-13337 | Kingston | Glenford | Ulster | 12433 | G | 3013 | Woodstock | N |  | 3.19 | [13 empty] | NM | N | 11 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-01-26 | 2021-01-27 | 1 | 2021-01-27 | [17 empty] | W
Central Hudson |  | Solar Liberty Energy Systems, Inc. | CH-13336 | Kingston | Grahamsvl | Sullivan | 12740 | G | 3091 | Neversink | N |  | 3.84 | [13 empty] | NM | N | 12 SunPower SPR-X22-360-E-AC (240V) | 2021-01-27 | 2021-01-27 | 0 | 2021-01-27 | [14 empty] | 2021-05-18 | 2021-05-18 |  | Y
Central Hudson |  | Lighthouse Solar | CH-13333 | Newburgh | New Paltz | Ulster | 12561 | G | 5031 | Galeville | N |  | 7.83 | [13 empty] | NM | N | 27 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-01-27 | 2021-01-27 | 0 | 2021-01-27 | [14 empty] | 2021-04-08 | 2021-04-08 |  | Y
Central Hudson |  | New York State Solar Farm | CH-13334 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7062 | Milan | N |  | 7.88 | [13 empty] | NM | N | 25 SunPower SPR-X22-360-E-AC (240V) | 2021-01-26 | 2021-01-26 | 0 | 2021-01-26 | [14 empty] | 2021-03-16 | 2021-03-16 |  | Y
Central Hudson |  | Intelligent Green Solutions LLC | CH-13338 | Catskill | Middleburg | Albany | 12122 | G | 1092 | Westerlo | Y |  | 7.6 | 7.6 | [12 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) 1SolarEdge TechnologiesSE7600A-US | 2021-01-29 | 2021-01-29 | 0 | 2021-01-29 | [14 empty] | 2021-04-13 | 2021-04-13 |  | Y
Central Hudson |  | PlugPV LLC | CH-13341 | Newburgh | Montgomery | Orange | 12549 | G | 5073 | Montgomery | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2021-01-27 | 2021-01-28 | 1 | 2021-01-28 | [14 empty] | 2021-03-10 | 2021-03-10 |  | Y
Central Hudson |  | Red Hook Solar Corp | CH-13340 | Kingston | Kingston | Ulster | 12401 | G | 1013 | Boulevard | N |  | 3.48 | [13 empty] | NM | N | 12 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-03-09 | 2021-03-09 | 0 | 2021-03-09 | [14 empty] | 2021-06-22 | 2021-06-22 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-13343 | Newburgh | Newburgh | Orange | 12550 | G | 4011 | West Balmville | N |  | 6.96 | [13 empty] | NM | N | 24 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-01-28 | 2021-01-28 | 0 | 2021-01-28 | [14 empty] | 2021-02-16 | 2021-02-16 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-13342 | Newburgh | Newburgh | Orange | 12550 | G | 4015 | West Balmville | N |  | 6.48 | [13 empty] | NM | N | 27 Enphase Energy IQ7-60-x-US (240V) | 2021-01-28 | 2021-01-28 | 0 | 2021-01-28 | [14 empty] | 2021-04-19 | 2021-04-19 |  | Y
Central Hudson |  | Tesla | CH-13345 | Newburgh | Marlboro | Ulster | 12542 | G | 5003 | Marlboro | Y | CH-02206 | 7.68 | 10 | [12 empty] | NM | N | 1 Delta Electronics M8-TL-US (240V) [SI1] 2TeslaAc Powerwall | 2021-03-31 | 2021-03-31 | 0 | 2021-03-31 | [8 empty] | 350 | 350 |  | 2021-05-07 | 2021-05-07 | 2021-06-11 | 2021-12-17 | 2021-12-21 |  | Y
Central Hudson |  | Tesla | CH-13346 | Newburgh | Cornwall | Orange | 12518 | G | 4041 | Union Ave | Y |  | 7.68 | 10 | [12 empty] | NM | N | 1 Delta Electronics M8-TL-US (240V) [SI1] 2TeslaAc Powerwall 2.0 | 2021-02-03 | 2021-02-04 | 1 | 2021-02-04 | [14 empty] | 2021-02-24 | 2021-02-24 |  | Y
Central Hudson |  | SunCommon | CH-13349 | Kingston | Saugerties | Ulster | 12477 | G | 3002 | Saugerties | Y |  | 5.51 | 5 | [12 empty] | NM | N | 19 Enphase Energy IQ7PLUS-72-x-US-& (240V) [SI1] 1TeslaPowerwall | 2021-02-01 | 2021-02-01 | 0 | 2021-02-01 | [14 empty] | 2021-03-16 | 2021-03-16 |  | Y
Central Hudson |  | New York State Solar Farm | CH-13351 | Newburgh | New Paltz | Ulster | 12561 | G | 5031 | Galeville | N |  | 43.2 | [13 empty] | NM | N | 1 SolarEdge Technologies SE43.2KUS (208V) | 2021-02-16 | 2021-03-02 | 10 | 2021-03-02 | [8 empty] | 2077.36 | 2478.41 |  | 2021-04-14 | 2021-04-14 | 2021-04-22 | 2021-09-29 | 2021-10-01 | 2021-10-06 | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-13352 | Newburgh | Salisbury Mls | Orange | 12577 | G | 4097 | Bethlehem Rd | N |  | 8.16 | [13 empty] | NM | N | 34 Enphase Energy IQ7-60-x-US (240V) | 2021-02-11 | 2021-02-11 | 0 | 2021-02-11 | [14 empty] | 2021-03-15 | 2021-03-15 |  | Y
Central Hudson |  | Lighthouse Solar | CH-13350 | Newburgh | New Paltz | Ulster | 12561 | G | 5031 | Galeville | Y |  | 7.6 | 7.6 | [12 empty] | NM | N | 1 Generac Power Systems X7602 (240V) 1Generac7.6kW X7602 (240v) | 2021-02-01 | 2021-02-01 | 0 | 2021-02-01 | [14 empty] | 2021-04-16 | 2021-04-16 |  | Y
Central Hudson |  | Gottschalk Solutions, LLC | CH-13382 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7053 | Rhinebeck | Y |  | 15.2 | 15.2 | [12 empty] | NM | N | 2 SolarEdge Technologies SE7600H-US (240V) 2SolarEdgeSE7600H | 2021-02-05 | 2021-02-05 | 0 | 2021-02-05 | [14 empty] | 2021-09-22 | 2021-09-22 |  | Y
Central Hudson |  | SunPower Direct (NY) | CH-13386 | Newburgh | Highland Mls | Orange | 10930 | G | 4041 | Union Ave | N |  | 8.03 | [13 empty] | NM | N | 23 Enphase Energy IQ7AS-66-x-ACM-US-y-z-& (240V) [SI1] | 2021-02-03 | 2021-02-04 | 1 | 2021-02-04 | [14 empty] | 2021-03-25 | 2021-03-25 |  | Y
Central Hudson |  | PlugPV, LLC | CH-13385 | Kingston | Mt Marion | Ulster | 12456 | G | 2016 | Lincoln Park | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2021-02-03 | 2021-02-03 | 0 | 2021-02-03 | [14 empty] | 2021-04-15 | 2021-04-15 |  | Y
Central Hudson |  | Solar LIberty Energy Systems, Inc. | CH-13390 | Kingston | Saugerties | Ulster | 14221 | G | 3002 | Saugerties | N |  | 2250 | [13 empty] | CDG | Y | 18 Chint Power Systems America CPS SCH125KTL-DO/US-600 (600V) | 2021-02-22 | 2021-02-26 | 4 | 2021-02-26 | 2021-02-26 | 2021-03-18 | 14 | 2021-05-03 | 2021-05-19 | 2021-08-12 | 59 | 20707.26 | 4500038.55 | [7 empty] | 2022-09-08 | W
Central Hudson |  | Sunrun Installation Services, Inc. | CH-13396 | Kingston | St Remy | Ulster | 12401 | G | 3041 | Sturgeon Pool | N |  | 6 | [13 empty] | NM | N | 25 Enphase Energy IQ7-60-x-US (240V) | 2021-02-04 | 2021-02-05 | 1 | 2021-02-05 | [14 empty] | 2021-04-20 | 2021-04-20 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-13392 | Newburgh | Newburgh | Orange | 12550 | G | 4013 | West Balmville | N |  | 3.48 | [13 empty] | NM | N | 12 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-02-04 | 2021-02-04 | 0 | 2021-02-04 | [14 empty] | 2021-07-01 | 2021-07-01 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-13393 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 6075 | East Park | N |  | 7.25 | [13 empty] | NM | N | 25 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-02-04 | 2021-02-05 | 1 | 2021-02-05 | [14 empty] | 2021-04-08 | 2021-04-08 |  | Y
Central Hudson |  | KASSELMAN SOLAR | CH-13387 | Catskill | Coxsackie | Greene | 12051 | G | 1074 | Coxsackie | N |  | 3.8 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3800H-US (240V) | 2021-02-04 | 2021-02-04 | 0 | 2021-02-04 | [8 empty] | 350 | 350 |  | 2021-02-08 | 2021-02-08 | 2021-02-18 | 2021-03-10 | 2021-03-10 |  | Y
Central Hudson |  | Solar Generation | CH-13394 | Kingston | Woodstock | Ulster | 12498 | G | 3003 | Saugerties | N |  | 21.11 | [13 empty] | NM | N | 67EnphaseIQ7X-96-2-US | 2021-02-04 | 2021-02-04 | 0 | 2021-02-04 | [8 empty] | 350 | 350 |  | 2021-02-10 | 2021-02-10 | 2021-03-25 | 2021-03-29 | 2021-03-29 |  | Y
Central Hudson |  | PlugPV, LLC | CH-13398 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6093 | Manchester | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2021-02-05 | 2021-02-05 | 0 | 2021-02-05 | [14 empty] | 2021-03-26 | 2021-03-26 |  | Y
Central Hudson |  | New York State Solar Farm | CH-13400 | Newburgh | Campbell Hall | Orange | 10916 | G | 5051 | Maybrook | N | CH-13400 | 10.82 | [13 empty] | NM | N | 31 SunPower SPR-A400-BLK-G-AC (240V) [SI1] | 2021-02-05 | 2021-02-05 | 0 | 2021-02-05 | [14 empty] | 2021-04-12 | 2021-04-12 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-13399 | Kingston | Boicevl | Ulster | 12412 | G | 3011 | Woodstock | N |  | 7.54 | [13 empty] | NM | N | 26 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-02-05 | 2021-02-05 | 0 | 2021-02-05 | [14 empty] | 2021-02-23 | 2021-02-23 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-13408 | Newburgh | New Windsor | Orange | 12553 | G | 4043 | Union Ave | N |  | 6.72 | [13 empty] | NM | N | 28 Enphase Energy IQ7-60-x-US (240V) | 2021-02-08 | 2021-02-09 | 1 | 2021-02-09 | [14 empty] | 2021-03-11 | 2021-03-11 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-13411 | Fishkill | Garrison | Putnam | 10524 | G | 8066 | Merritt Park | Y |  | 5.76 | 5.76 | [12 empty] | NM | N | 1 Delta Electronics E6-TL-US (240V) [SI1] 1Delta ElectronicsE6-TL-US | 2021-02-08 | 2021-02-09 | 1 | 2021-02-09 | [14 empty] | 2021-06-02 | 2021-06-02 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-13405 | Kingston | Kingston | Ulster | 12401 | G | 1003 | Jansen Ave | N |  | 11.31 | [13 empty] | NM | N | 39 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-02-08 | 2021-02-08 | 0 | 2021-02-08 | [14 empty] | 2021-03-30 | 2021-03-30 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-13410 | Newburgh | New Windsor | Orange | 12553 | G | 4045 | Union Ave | N |  | 7.44 | [13 empty] | NM | N | 31 Enphase Energy IQ7-60-x-US (240V) | 2021-02-08 | 2021-02-09 | 1 | 2021-02-09 | [14 empty] | 2021-05-18 | 2021-05-18 |  | Y
Central Hudson |  | Montante Solar | CH-13407 | Newburgh | Montgomery | Orange | 12549 | G | 4021 | Coldenham | N |  | 480 | [13 empty] | NM | Y | 8 Chint Power Systems America CPS SCA60KTL-DO/US-480 (480V) | 2021-04-08 | 2021-04-12 | 2 | 2021-04-12 | 2021-04-12 | 2021-04-29 | 13 | [11 empty] | 2021-12-16 | 2021-12-16 |  | Y | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-13409 | Newburgh | New Windsor |  | 12553 | G | 4094 | Bethlehem Rd | Y |  | 5.76 | 5.76 | [12 empty] | NM | N | 1 Delta Electronics E6-TL-US (240V) [SI1] 1Delta ElectronicsE6-TL-US | 2021-02-08 | 2021-02-09 | 1 | 2021-02-09 | [17 empty] | W
Central Hudson |  | Empire Solar Solutions | CH-13404 | Kingston | New Paltz | Ulster | 12561 | G | 3041 | Sturgeon Pool | N |  | 11.9 | [13 empty] | NM | N | 41 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-02-08 | 2021-02-08 | 0 | 2021-02-08 | [14 empty] | 2021-03-17 | 2021-03-17 |  | Y
Central Hudson |  | Tesla | CH-13406 | Kingston | Kingston | Ulster | 12401 | G | 2016 | Lincoln Park | Y |  | 7.6 | 15 | [12 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) 3TeslaAc Powerwall 2.0 | 2021-02-08 | 2021-02-08 | 0 | 2021-02-08 | [14 empty] | 2021-08-13 | 2021-08-13 |  | Y
Central Hudson |  | SunCommon | CH-13418 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7052 | Rhinebeck | Y | CH-01361 |  | 5 | [12 empty] | NM | N | 1TeslaPowerwall 2 | 2021-02-10 | 2021-02-10 | 0 | 2021-02-10 | [8 empty] | 350 | 350 |  | 2021-02-19 | 2021-02-19 | 2021-03-11 | 2021-04-08 | 2021-04-08 |  | Y
Central Hudson |  | SunCommon | CH-13420 | Poughkeepsie | Clinton Cors | Dutchess | 12514 | G | 7071 | Stanfordville | Y |  | 5.22 | 5 | [12 empty] | NM | N | 18 Enphase Energy IQ7PLUS-72-x-ACM-US (240V) 1TeslaPowerwall 2 | 2021-02-09 | 2021-02-10 | 1 | 2021-02-10 | [14 empty] | 2021-03-12 | 2021-03-12 |  | Y
Central Hudson |  | Tesla | CH-13413 | Kingston | Accord | Ulster | 12404 | G | 3024 | High Falls | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2021-02-09 | 2021-02-09 | 0 | 2021-02-09 | [17 empty] | W
Central Hudson |  | Tesla | CH-13412 | Poughkeepsie | Stanfordvl |  | 12581 | G | 7072 | Stanfordville | N |  |  | 10 | [12 empty] | NA | N | 2TeslaAc Powerwall 2.0 | 2021-02-12 | 2021-03-01 | 10 | 2021-03-01 | [8 empty] | 350 | 350 |  | 2021-03-10 | 2021-03-10 | 2021-04-05 |  |  |  | W
Central Hudson |  | Sunrun Installation Services, Inc. | CH-13416 | Kingston | Saugerties | Ulster | 12477 | G | 3001 | Saugerties | Y |  | 7.68 | 7.68 | [12 empty] | NM | N | 1 Delta Electronics E8-TL-US (240V) [SI1] 1Delta ElectronicsE8-TL-US | 2021-02-09 | 2021-02-10 | 1 | 2021-02-10 | [8 empty] | 350 | 350 |  | 2021-04-21 | 2021-04-21 | 2021-05-08 | 2021-05-24 | 2021-05-24 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-13421 | Poughkeepsie | Hyde Park | Dutchess | 12538 | G | 6073 | East Park | Y | CH-11856 | 5.76 | 5.76 | [12 empty] | NM | N | 1 Delta Electronics E6-TL-US (240V) [SI1] 1Delta ElectronicsE6-TL-US | 2021-02-18 | 2021-02-18 | 0 | 2021-02-18 | [14 empty] | 2021-03-19 | 2021-03-19 |  | Y
Central Hudson |  | Hudson Valley Wind & Solar LLC | CH-13426 | Poughkeepsie | Milan | Dutchess | 12571 | G | 7061 | Milan | Y |  | 22.8 | 22.8 | [12 empty] | NM | N | 3 SolarEdge Technologies SE7600H-US (240V) [SI1] 3SolarEdgeSE7600H-US | 2021-03-23 | 2021-04-05 | 8 | 2021-04-05 | [8 empty] | 350 | 350 |  | 2021-04-28 | 2021-04-28 | 2021-05-18 | 2021-08-26 | 2021-08-26 |  | Y
Central Hudson |  | PlugPV LLC | CH-13424 | Newburgh | Newburgh | Orange | 12550 | G | 4052 | Union Ave | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000H-US (240V) | 2021-02-24 | 2021-02-24 | 0 | 2021-02-24 | [14 empty] | 2021-03-29 | 2021-03-29 |  | Y
Central Hudson |  | Tesla | CH-13422 | Poughkeepsie | Millbrook | Dutchess | 12545 | G | 7012 | Hibernia | Y |  | 7.6 | 15 | [12 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) 3TeslaAc Powerwall 2.0 | 2021-02-11 | 2021-02-11 | 0 | 2021-02-11 | [14 empty] | 2021-10-13 | 2021-10-13 |  | Y
Central Hudson |  | KASSELMAN SOLAR | CH-13427 | Catskill | Freehold | Greene | 12431 | G | 2071 | Freehold | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2021-02-10 | 2021-02-11 | 1 | 2021-02-11 | [14 empty] | 2021-03-31 | 2021-03-31 |  | Y
Central Hudson |  | Solar Generation | CH-13429 | Newburgh | Newburgh | Orange | 12550 | G | 5001 | Marlboro | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) 1 SolarEdge Technologies SE3800H-US (240V) | 2021-02-10 | 2021-02-11 | 1 | 2021-02-11 | [14 empty] | 2021-02-12 | 2021-02-12 |  | Y
Central Hudson |  | Solar Generation | CH-13428 | Newburgh | Gardiner | Ulster | 12525 | G | 5031 | Galeville | N |  | 7.68 | [13 empty] | NM | N | 1 SMA America SB7700TL-US-22 (240V) | 2021-02-10 | 2021-02-11 | 1 | 2021-02-11 | [14 empty] | 2021-03-16 | 2021-03-16 |  | Y
Central Hudson |  | Lightstar Renewables LLC | CH-13430 | Fishkill | Wappingers Falls | Dutchess | 12590 | G | 8043 | Myers Corners | N |  | 2100 | [13 empty] | CDG | Y | 8 Chint Power Systems America CPS SCH275KTL-DO/US-800 (800V) [SI1] | 2021-06-01 | 2021-06-08 | 5 | 2021-06-08 | 2021-06-08 | 2021-06-29 | 15 | 2021-07-13 | 2021-07-30 | 2021-10-25 | 60 | 20000 | 283117.35 |  | 2022-03-08 | 2022-08-12 | 2022-08-12 |  |  |  |  | N | Y
Central Hudson |  | Tesla | CH-13459 | Newburgh | New Paltz | Ulster | 12561 | G | 5023 | Ohioville | N |  |  | 10 | [12 empty] | NA | N | 2TeslaAc Powerwall 2.0 | 2021-02-12 | 2021-03-01 | 10 | 2021-03-01 | [14 empty] | 2022-01-05 | 2022-01-05 |  | Y
Central Hudson |  | Tesla | CH-13439 | Newburgh | Highland | Ulster | 12528 | G | 5083 | Highland | Y |  | 7.6 | 10 | [12 empty] | NM | N | 1 Tesla 1538000-xx-y (240V) [SI1] 2TeslaAc Powerwall 2.0 | 2021-02-12 | 2021-02-16 | 1 | 2021-02-16 | [14 empty] | 2021-06-01 | 2021-06-01 |  | Y
Central Hudson |  | Tesla | CH-13466 | Poughkeepsie | Tivoli | Dutchess | 12583 | G | 7062 | Milan | N | CH-13466 |  | 15 | [12 empty] | NM | N | 3TeslaAc Powerwall 2.0 | 2021-02-12 | 2021-03-01 | 10 | 2021-03-01 | [8 empty] | 350 | 350 |  | 2021-03-10 | 2021-03-10 | 2021-03-29 | 2022-02-02 | 2022-02-09 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-13462 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 7.25 | [13 empty] | NM | N | 25 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-02-11 | 2021-02-11 | 0 | 2021-02-11 | [14 empty] | 2021-03-31 | 2021-03-31 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-13463 | Newburgh | Newburgh | Orange | 12550 | G | 4022 | Coldenham | N |  | 5.22 | [13 empty] | NM | N | 18 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-02-11 | 2021-02-11 | 0 | 2021-02-11 | [14 empty] | 2021-03-08 | 2021-03-08 |  | Y
Central Hudson |  | Lightstar Renewables LLC | CH-13467 | Newburgh | New Windsor | Orange | 12553 | G | 4091 | Bethlehem Rd | N |  | 4200 | [13 empty] | CDG | Y | 16 Chint Power Systems America CPS SCH275KTL-DO/US-800 (800V) [SI1] | 2021-03-18 | 2021-04-01 | 10 | 2021-04-01 | 2021-04-01 | 2021-04-23 | 15 | 2021-05-07 | 2021-06-14 | 2021-09-07 | 59 | 19000 | 125570.8 |  | 2022-01-03 | 2022-06-13 | 2022-06-13 |  |  |  |  | N | Y
Central Hudson |  | PlugPV LLC | CH-13477 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6091 | Manchester | N |  | 15.2 | [13 empty] | NM | N | 2 SolarEdge Technologies SE7600H-US (240V) | 2021-02-12 | 2021-02-12 | 0 | 2021-02-12 | [17 empty] | W
Central Hudson |  | PlugPV, LLC | CH-13474 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8091 | Fishkill Plains | Y |  | 10 | 10 | [12 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) 2TeslaPowerwall 2 | 2021-02-16 | 2021-02-16 | 0 | 2021-02-16 | [14 empty] | 2022-07-13 | 2022-07-13 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-13478 | Poughkeepsie | Wappingrs Fls | Dutchess | 12590 | G | 6052 | Todd Hill | N |  | 10.15 | [13 empty] | NM | N | 13 Enphase Energy IQ7PLUS-72-x-US (240V) 22 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-02-12 | 2021-02-16 | 1 | 2021-02-16 | [14 empty] | 2021-05-20 | 2021-05-20 |  | Y
Central Hudson |  | Lightstar Renewables, LLC | CH-13472 | Newburgh | Walden |  | 12586 | G | 5042 | East Walden | N |  | 600 | [13 empty] | CDG | Y | 6 Chint Power Systems America CPS SCH100KTL-DO/US-600 (600V) | 2021-03-18 | 2021-04-01 | 10 | 2021-04-01 | 2021-04-01 | 2021-04-22 | 14 | [14 empty] | W
Central Hudson |  | Lightstar Renewables, LLC | CH-13473 | Newburgh | Walden | Orange | 12586 | G | 5042 | East Walden | N |  | 2550 | [13 empty] | CDG | Y | 10 Chint Power Systems America CPS SCH275KTL-DO/US-800 (800V) [SI1] | 2021-03-18 | 2021-04-01 | 10 | 2021-04-01 | 2021-04-01 | 2021-04-22 | 14 | 2021-06-18 | 2021-07-26 | 2021-10-19 | 60 | 19000 | 216434.6 |  | 2022-03-01 | 2022-08-12 | 2022-08-12 | 2025-08-28 |  |  |  | N | Y
Central Hudson |  | Gottschalk Solutions | CH-13480 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6095 | Manchester | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2021-02-12 | 2021-02-16 | 1 | 2021-02-16 | [14 empty] | 2021-03-24 | 2021-03-24 |  | Y
Central Hudson |  | Trinity Solar | CH-13481 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8096 | Fishkill Plains | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2021-02-16 | 2021-02-16 | 0 | 2021-02-16 | [14 empty] | 2021-04-15 | 2021-04-15 |  | Y
Central Hudson |  | Empire Solar Solution | CH-13488 | Newburgh | Newburgh | Orange | 12550 | G | 4022 | Coldenham | N |  | 8.41 | [13 empty] | NM | N | 29 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-02-16 | 2021-02-17 | 1 | 2021-02-17 | [14 empty] | 2021-03-10 | 2021-03-10 |  | Y
Central Hudson |  | PlugPV, LLC | CH-13487 | Poughkeepsie | Staatsburg |  | 12580 | G | 7041 | Staatsburg | Y |  | 11.4 | 5 | [12 empty] | NM | N | 1 SolarEdge Technologies SE3800H-US (240V) [SI1] 1 SolarEdge Technologies SE7600H-US (240V) [SI1] 1TeslaPowerwall | 2021-02-22 | 2021-02-23 | 1 | 2021-02-23 | [17 empty] | W
Central Hudson |  | Solar Generation | CH-13486 | Kingston | Kingston | Ulster | 12401 | G | 2094 | Hurley Ave | N |  | 8.19 | [13 empty] | NM | N | 26 Enphase Energy IQ7X-96-x-US (240V) | 2021-02-23 | 2021-02-23 | 0 | 2021-02-23 | [14 empty] | 2021-04-06 | 2021-04-06 |  | Y
Central Hudson |  | GenPro Energy Solutions | CH-12423 | Kingston | Rosendale | Ulster | 12472 | G | 3021 | High Falls | N |  | 1100 | [13 empty] | RC | Y | 8 Chint Power Systems America CPS SCH125KTL-DO/US-600 (600V) 1 Chint Power Systems America CPS SCH100KTL-DO/US-600 (600V) | 2021-07-15 | 2021-07-26 | 7 | 2021-07-26 | 2021-07-26 | 2021-08-10 | 11 | 2021-09-10 | 2021-10-20 | 2022-01-19 | 60 | 18440.11 | 125569.65 | 131500.28 | 2022-05-02 | 2022-10-20 | 2022-10-20 | 2023-08-28 | 2023-08-29 | 2023-09-01 | 2023-11-14 | Y | Y
Central Hudson |  | PlugPV, LLC | CH-13489 | Newburgh | Highland | Ulster | 12528 | G | 5081 | Highland | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE11400H-US (240V) | 2021-02-17 | 2021-02-17 | 0 | 2021-02-17 | [14 empty] | 2021-04-21 | 2021-04-21 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-13492 | Kingston | Kingston | Ulster | 12401 | G | 1024 | East Kingston | N |  | 5.04 | [13 empty] | NM | N | 21 Enphase Energy IQ7-60-x-US (240V) | 2021-02-18 | 2021-02-19 | 1 | 2021-02-19 | [14 empty] | 2021-04-06 | 2021-04-06 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-13491 | Newburgh | Cornwall | Orange | 12518 | G | 4041 | Union Ave | N | CH-13491 | 6.72 | [13 empty] | NM | N | 28 Enphase Energy IQ7-60-x-US (240V) | 2021-02-18 | 2021-02-18 | 0 | 2021-02-18 | [14 empty] | 2021-05-18 | 2021-05-18 |  | Y
Central Hudson |  | Empire Solar Solutiond | CH-13490 | Poughkeepsie | Dover Plns | Dutchess | 12522 | G | NYSEG | NYSEG | N |  | 11.31 | [13 empty] | NM | N | 39 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-02-18 | 2021-03-03 | 9 | 2021-03-03 | [14 empty] | 2021-03-29 | 2021-03-29 |  | Y
Central Hudson |  | murphy solar and central air | CH-13494 | Catskill | Athens | Greene | 12015 | G | 1074 | Coxsackie | N |  | 7 | [13 empty] | NM | N | 1 SMA America SB7000TL-US (240V) | 2021-03-01 | 2021-03-03 | 2 | 2021-03-03 | [14 empty] | 2021-04-14 | 2021-04-14 |  | Y
Central Hudson |  | Tesla | CH-13496 | Newburgh | Highland | Ulster | 12528 | G | 5083 | Highland | Y | CH-05190 |  | 10 | [12 empty] | NM | N | 2TeslaAc Powerwall 2.0 | 2021-03-03 | 2021-03-04 | 1 | 2021-03-04 | [14 empty] | 2022-04-06 | 2022-04-08 |  | Y
Central Hudson |  | Hudson River Renewables LLC | CH-13499 | Kingston | Olivebridge | Ulster | 12461 | G | 3082 | Kerhonkson | Y |  | 9 | 9 | [12 empty] | NM | N | 1 Sol-Ark Sol-Ark-12K-P (240V) 1Sol-ArkSol-Ark 12K-P (240V) | 2021-02-24 | 2021-02-24 | 0 | 2021-02-24 | [14 empty] | 2021-04-05 | 2021-04-05 |  | Y
Central Hudson |  | Tesla | CH-13497 | Kingston | Saugerties | Ulster | 12477 | G | 3014 | Woodstock | N |  | 11.52 | [13 empty] | NM | N | 1 Delta Electronics M8-TL-US (240V) [SI1] 1 Delta Electronics M4-TL-US (240V) [SI1] | 2021-02-22 | 2021-02-22 | 0 | 2021-02-22 | [17 empty] | W
Central Hudson |  | Tesla Energy Operations, Inc. | CH-13498 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 6051 | Todd Hill | Y |  | 15.2 | 20 | [12 empty] | NM | N | 2 Tesla 1538000-xx-y (240V) [SI1] 4TeslaAC Powerwall 2.0 | 2021-02-24 | 2021-02-24 | 0 | 2021-02-24 | [8 empty] | 350 | 350 |  | 2021-03-05 | 2021-03-05 | 2021-03-15 | 2023-01-25 | 2023-01-31 |  | Y
Central Hudson |  | PlugPV, LLC | CH-13500 | Newburgh | Marlboro | Ulster | 12542 | G | 5001 | Marlboro | N | CH-13500 | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000H-US (240V) [SI1] | 2021-02-22 | 2021-02-23 | 1 | 2021-02-23 | [14 empty] | 2021-04-12 | 2021-04-12 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-13503 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6003 | Reynolds Hill | N |  | 2.61 | [13 empty] | NM | N | 9 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-02-23 | 2021-02-24 | 1 | 2021-02-24 | [14 empty] | 2021-03-23 | 2021-03-23 |  | Y
Central Hudson |  | Solar Generation | CH-13501 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7055 | Rhinebeck | N |  | 12.76 | [13 empty] | NM | N | 44 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-02-23 | 2021-02-23 | 0 | 2021-02-23 | [8 empty] | 350 | 350 |  | 2021-03-01 | 2021-03-01 | 2021-03-17 | 2021-06-16 | 2021-06-16 |  | Y
Central Hudson |  | SunCommon | CH-13502 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7062 | Milan | N | CH-02153 | 6.86 | [13 empty] | NM | N | 7 SunPower SPR-E20-327-C-AC (240V) 16 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-02-23 | 2021-02-23 | 0 | 2021-02-23 | [14 empty] | 2021-03-26 | 2021-03-26 |  | Y
Central Hudson |  | Tesla | CH-13511 | Fishkill | Cold Spg |  | 10516 | G | 8087 | Tioronda | Y |  | 3.8 | 5 | [12 empty] | NM | N | 1 SolarEdge Technologies SE3800H-US (240V) [SI1] 1TeslaAc Powerwall 2.0 | 2021-02-24 | 2021-02-25 | 1 | 2021-02-25 | [17 empty] | W
Central Hudson |  | Solar Generation | CH-13512 | Poughkeepsie | Pine Plns | Dutchess | 12567 | G | 7091 | Pulvers Corners | N |  | 12.47 | [13 empty] | NM | N | 43 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-02-25 | 2021-02-25 | 0 | 2021-02-25 | [8 empty] | 350 | 350 |  | 2021-03-01 | 2021-03-01 | 2021-03-22 | 2022-03-15 | 2022-03-21 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-13513 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 6051 | Todd Hill | N |  | 8.99 | [13 empty] | NM | N | 31 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-02-26 | 2021-02-26 | 0 | 2021-02-26 | [14 empty] | 2021-05-24 | 2021-05-24 |  | Y
Central Hudson |  | PlugPV LLC | CH-13515 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 6057 | Todd Hill | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000H-US (240V) | 2021-02-26 | 2021-02-26 | 0 | 2021-02-26 | [17 empty] | W
Central Hudson |  | PlugPV LLC | CH-13514 | Kingston | Kingston | Ulster | 12401 | G | 1021 | East Kingston | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000H-US (240V) | 2021-02-26 | 2021-02-26 | 0 | 2021-02-26 | [14 empty] | 2021-04-27 | 2021-04-27 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-13519 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 3.48 | [13 empty] | NM | N | 12 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-03-01 | 2021-03-01 | 0 | 2021-03-01 | [14 empty] | 2021-04-01 | 2021-04-01 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-13516 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8095 | Fishkill Plains | N |  | 7.68 | [13 empty] | NM | N | 1 Delta Electronics M8-TL-US (240V) [SI1] | 2021-03-03 | 2021-03-04 | 1 | 2021-03-04 | [17 empty] | W
Central Hudson |  | Sunrun Installation Services, Inc. | CH-13518 | Kingston | Kingston | Ulster | 12401 | G | 1021 | East Kingston | N |  | 7.68 | [13 empty] | NM | N | 1 Delta Electronics M8-TL-US (240V) [SI1] | 2021-03-01 | 2021-03-01 | 0 | 2021-03-01 | [14 empty] | 2021-05-21 | 2021-05-21 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-13517 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8091 | Fishkill Plains | Y | CH-23126 | 6 | 5 | [12 empty] | NM | N | 25 Enphase Energy IQ7-60-x-US (240V) 1TeslaAC Powerwall 2.0 | 2021-03-02 | 2021-03-03 | 1 | 2021-03-03 | [14 empty] | 2021-05-25 | 2021-05-25 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-13520 | Newburgh | Cornwall | Orange | 12518 | G | 4043 | Union Ave | Y |  | 3.19 | 10.24 | [12 empty] | NM | N | 11 Enphase Energy IQ7PLUS-72-x-US (240V) 8ENPHASEIQ 8X-BAT | 2021-03-24 | 2021-03-24 | 0 | 2021-03-24 | [14 empty] | 2021-08-02 | 2021-08-02 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-13521 | Newburgh | Newburgh | Orange | 12550 | G | 4012 | West Balmville | N |  | 7.54 | [13 empty] | NM | N | 26 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-03-01 | 2021-03-01 | 0 | 2021-03-01 | [14 empty] | 2021-03-26 | 2021-03-26 |  | Y
Central Hudson |  | Solar Generation | CH-13522 | Kingston | Saugerties | Ulster | 12477 | G | 3014 | Woodstock | N |  | 12.2 | [13 empty] | NM | N | 35 Enphase Energy IQ7A-72-x-US-& (240V) [SI1] | 2021-03-05 | 2021-03-05 | 0 | 2021-03-05 | [14 empty] | 2021-04-16 | 2021-04-16 |  | Y
Central Hudson |  | KASSELMAN SOLAR | CH-13528 | Catskill | Saugerties | Ulster | 12477 | G | 2001 | North Catskill | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2021-03-03 | 2021-03-03 | 0 | 2021-03-03 | [14 empty] | 2021-03-17 | 2021-03-17 |  | W
Central Hudson |  | PlugPV, LLC | CH-13524 | Newburgh | Cornwall | Orange | 12518 | G | 4041 | Union Ave | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) [SI1] | 2021-03-03 | 2021-03-03 | 0 | 2021-03-03 | [14 empty] | 2021-04-12 | 2021-04-12 |  | Y
Central Hudson |  | New York State Solar Farm | CH-13526 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6056 | Todd Hill | N | CH-11677 | 2.52 | [13 empty] | NM | N | 8 SunPower SPR-X22-360-E-AC (240V) | 2021-03-02 | 2021-03-03 | 1 | 2021-03-03 | [14 empty] | 2021-03-22 | 2021-03-22 |  | Y
Central Hudson |  | New York State Solar Farm | CH-13525 | Kingston | Saugerties | Ulster | 12477 | G | 3003 | Saugerties | Y |  | 7.88 | 5 | [12 empty] | NM | N | 25 SunPower SPR-X22-360-E-AC (240V) 1TESLATESLA POWERWALL 2 | 2021-03-02 | 2021-03-03 | 1 | 2021-03-03 | [14 empty] | 2021-04-13 | 2021-04-13 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-13529 | Newburgh | Newburgh | Orange | 12550 | G | 5004 | Marlboro | N |  | 6.96 | [13 empty] | NM | N | 29 Enphase Energy IQ7-60-x-US (240V) | 2021-03-03 | 2021-03-08 | 3 | 2021-03-08 | [14 empty] | 2021-10-08 | 2021-10-15 |  | Y
Central Hudson |  | PlugPV LLC | CH-13534 | Fishkill | Fishkill | Dutchess | 12524 | G | 8094 | Fishkill Plains | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000H-US (240V) | 2021-03-04 | 2021-03-08 | 2 | 2021-03-08 | [17 empty] | W
Central Hudson |  | Borrego Solar Systems, Inc | CH-13535 | Poughkeepsie | Staatsburg | Dutchess | 12580 | G | 7041 | Staatsburg | N |  | 4400 | [13 empty] | CDG | Y | 1Power ElectronicsHEMK FS2125K1Power ElectronicsHEMK FS3190K | 2021-05-17 | 2021-06-01 | 10 | 2021-06-01 | 2021-06-01 | 2021-06-07 | 4 | 2021-07-30 | 2021-10-08 | 2022-01-04 | 57 | 21937.27 | 210024.5 | 2858.95 | 2022-05-11 | [5 empty] | 2023-01-27 | W | Y
Central Hudson |  | Apex Roofing LLC | CH-13533 | Poughkeepsie | Rhinecliff | Dutchess | 12574 | G | 7055 | Rhinebeck | N | CH-13106 | 6.4 | [13 empty] | NM | N | 20 SunPower SPR-X21-350-BLK-D-AC (240V) | 2021-03-04 | 2021-03-05 | 1 | 2021-03-05 | [8 empty] | 350 | 350 |  | 2021-03-09 | 2021-03-09 | 2021-03-15 | 2021-03-26 | 2021-03-26 |  | Y
Central Hudson |  | Tesla | CH-13531 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 6051 | Todd Hill | Y | CH-13531 | 7.6 | 5 | [12 empty] | NM | N | 1 Tesla 1538000-xx-y (240V) [SI1] 1TeslaAc Powerwall 2.0 | 2021-03-04 | 2021-03-08 | 2 | 2021-03-08 | [14 empty] | 2021-10-28 | 2021-11-04 |  | Y
Central Hudson |  | Vivint Solar Developer, LLC | CH-13544 | Fishkill | Wappingers Falls | Dutchess | 12590 | G | 8054 | North Chelsea | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2021-05-03 | 2021-05-10 | 5 | 2021-05-10 | [14 empty] | 2021-11-22 | 2021-11-23 |  | Y
Central Hudson |  | Accord Power Inc. | CH-13542 | Catskill | Catskill |  | 12414 | G | 2042 | South Cairo | N |  | 5000 | [13 empty] | CDG | Y | 2 Sungrow Power Supply SG2500U (550V) | 2021-04-20 | 2021-05-04 | 10 | 2021-05-04 | 2021-05-04 | 2021-05-24 | 14 | 2021-06-10 | 2021-07-26 | 2021-10-19 | 60 | 21990.1 | 6808497.95 | [7 empty] | 2022-03-22 | W
Central Hudson |  | SunCommon | CH-13536 | Kingston | Port Ewen | Ulster | 12466 | G | 1012 | Boulevard | N |  | 3.77 | [13 empty] | NM | N | 13 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-03-05 | 2021-03-08 | 1 | 2021-03-08 | [14 empty] | 2021-03-26 | 2021-03-26 |  | Y
Central Hudson |  | PlugPV, LLC | CH-13537 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6056 | Todd Hill | N |  | 15.2 | [13 empty] | NM | N | 2 SolarEdge Technologies SE7600H-US (240V) | 2021-03-10 | 2021-03-10 | 0 | 2021-03-10 | [14 empty] | 2021-05-14 | 2021-05-14 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-13543 | Newburgh | Wallkill | Ulster | 12589 | G | 5041 | East Walden | N |  | 8.99 | [13 empty] | NM | N | 31 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-03-08 | 2021-03-08 | 0 | 2021-03-08 | [14 empty] | 2021-03-30 | 2021-03-30 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-13541 | Newburgh | Wallkill | Ulster | 12589 | G | 5043 | East Walden | N |  | 9.28 | [13 empty] | NM | N | 32 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-03-05 | 2021-03-08 | 1 | 2021-03-08 | [14 empty] | 2021-07-06 | 2021-07-06 |  | Y
Central Hudson |  | BW Solar Holding Inc | CH-13538 | Catskill | Ravena |  | 12143 | G | 1081 | New Baltimore | N |  | 5000 | [13 empty] | CDG | Y | 40 Sungrow Power Supply SG125HV (600V) | 2021-04-09 | 2021-04-19 | 6 | 2021-04-19 | 2021-04-19 | 2021-05-07 | 14 |  |  |  |  | 20000 | [9 empty] | W
Central Hudson |  | BW Solar Holding Inc | CH-13539 | Catskill | Ravena |  | 12143 | G | 1081 | New Baltimore | N |  | 5000 | [13 empty] | CDG | Y | 40 Sungrow Power Supply SG125HV (600V) | 2021-04-07 | 2021-04-12 | 3 | 2021-04-12 | 2021-04-12 | 2021-04-22 | 8 | [14 empty] | W
Central Hudson |  | BW Solar Holding Inc | CH-13540 | Catskill | Ravena |  | 12143 | G | 1081 | New Baltimore | N |  | 5000 | [13 empty] | CDG | Y | 40 Sungrow Power Supply SG125HV (600V) | 2021-04-08 | 2021-04-12 | 2 | 2021-04-12 | 2021-04-12 | 2021-04-30 | 14 | [14 empty] | W
Central Hudson |  | PlugPV LLC | CH-13546 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6096 | Manchester | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE11400H-US (240V) | 2021-03-08 | 2021-03-08 | 0 | 2021-03-08 | [14 empty] | 2021-05-19 | 2021-05-19 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-13545 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 6073 | East Park | N |  | 4.35 | [13 empty] | NM | N | 15 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-03-08 | 2021-03-08 | 0 | 2021-03-08 | [14 empty] | 2021-04-07 | 2021-04-07 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-13547 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6097 | Manchester | N |  | 6.38 | [13 empty] | NM | N | 22 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-03-08 | 2021-03-09 | 1 | 2021-03-09 | [14 empty] | 2021-05-17 | 2021-05-17 |  | Y
Central Hudson |  | SunCommon | CH-13548 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7041 | Staatsburg | N |  | 30 | [13 empty] | NM | Y | 3SolarEdgeSE10000H-US | 2021-04-12 | 2021-04-22 | 8 | 2021-04-22 | [14 empty] | 2022-03-09 | 2022-03-17 |  | Y | Y
Central Hudson |  | PlugPV, LLC | CH-13551 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8096 | Fishkill Plains | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE11400H-US (240V) [SI1] | 2021-03-09 | 2021-03-09 | 0 | 2021-03-09 | [14 empty] | 2021-05-04 | 2021-05-04 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-13552 | Kingston | Ulster Pk | Ulster | 12487 | G | 1014 | Boulevard | N |  | 6.67 | [13 empty] | NM | N | 23 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-03-09 | 2021-03-10 | 1 | 2021-03-10 | [14 empty] | 2021-05-17 | 2021-05-17 |  | Y
Central Hudson |  | SunCommon | CH-13550 | Poughkeepsie | Clinton Cors | Dutchess | 12514 | G | 7071 | Stanfordville | N |  | 10.44 | [13 empty] | NM | N | 36 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-03-09 | 2021-03-09 | 0 | 2021-03-09 | [14 empty] | 2021-05-06 | 2021-05-06 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-13558 | Newburgh | New Windsor | Orange | 12553 | G | 4054 | Union Ave | N |  | 6.96 | [13 empty] | NM | N | 24 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-03-10 | 2021-03-11 | 1 | 2021-03-11 | [14 empty] | 2021-05-25 | 2021-05-25 |  | Y
Central Hudson |  | PlugPV LLC | CH-13554 | Fishkill | Beacon | Dutchess | 12508 | G | 8085 | Tioronda | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2021-03-12 | 2021-03-12 | 0 | 2021-03-12 | [14 empty] | 2021-04-29 | 2021-04-29 |  | Y
Central Hudson |  | Lighthouse Solar | CH-13557 | Kingston | Saugerties | Ulster | 12477 | G | 3014 | Woodstock | N |  | 6.09 | [13 empty] | NM | N | 21 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-03-10 | 2021-03-10 | 0 | 2021-03-10 | [14 empty] | 2021-04-08 | 2021-04-08 |  | Y
Central Hudson |  | Trinity Solar | CH-13553 | Newburgh | Montgomery | Orange | 12549 | G | 5073 | Montgomery | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2021-03-10 | 2021-03-10 | 0 | 2021-03-10 | [14 empty] | 2021-09-23 | 2021-09-30 |  | Y
Central Hudson |  | IPPsolar Intergration LLC | CH-13556 | Kingston | Ulster | Ulster | 12401 | G | 1021 | East Kingston | N |  | 5000 | [13 empty] | CDG | Y | 100 SMA America STP50-US-40 (480V) [SI1] | 2021-06-01 | 2021-06-10 | 7 | 2021-06-10 | 2021-06-10 | 2021-07-01 | 15 | 2021-10-04 | 2021-12-27 | 2022-03-23 | 60 | 12886.21 | 1045031.45 | [7 empty] | 2022-10-31 | W
Central Hudson |  | Stella Solar | CH-13504 | Catskill | Freehold | Greene | 12431 | G | 2071 | Freehold | N |  | 499.5 | [13 empty] | RC | Y | 3 ABB PVS-166-TL-POWER-MODULE-2-US (800V) [SI1] | 2021-04-13 | 2021-04-23 | 8 | 2021-04-23 | 2021-04-23 | 2021-04-28 | 3 | [5 empty] | 68740.1 |  | 2022-01-05 | [5 empty] | 2022-08-05 | W | Y
Central Hudson |  | KASSELMAN SOLAR | CH-13560 | Poughkeepsie | Stanfordvl | Dutchess | 12581 | G | 7072 | Stanfordville | N | CH-13560 | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2021-09-30 | 2021-10-13 | 9 | 2021-10-13 | [14 empty] | 2021-10-13 | 2021-10-18 |  | Y
Central Hudson |  | New York Power Solutions | CH-13559 | Newburgh | Walden | Orange | 12586 | G | 5041 | East Walden | N |  | 9.28 | [13 empty] | NM | N | 32 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-03-18 | 2021-03-18 | 0 | 2021-03-18 | [14 empty] | 2021-05-04 | 2021-05-04 |  | Y
Central Hudson |  | PlugPV LLC | CH-13561 | Poughkeepsie | Poughkeepsie |  | 12603 | G | 6095 | Manchester | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2021-03-12 | 2021-03-15 | 1 | 2021-03-15 | [17 empty] | W
Central Hudson |  | New York State Solar Farm | CH-13562 | Kingston | Hurley | Ulster | 12443 | G | 2093 | Hurley Ave | N |  | 6.3 | [13 empty] | NM | N | 20 SunPower SPR-E20-327-E-AC (240V) | 2021-03-15 | 2021-03-15 | 0 | 2021-03-15 | [14 empty] | 2021-04-12 | 2021-04-12 |  | Y
Central Hudson |  | New York State Solar Farm | CH-13563 | Kingston | Shady | Ulster | 12409 | G | 3012 | Woodstock | N |  | 18 | [13 empty] | NM | N | 3 SMA America SB6.0-1SP-US-41 (240V) [SI1] | 2021-03-15 | 2021-03-15 | 0 | 2021-03-15 | [8 empty] | 350 | 350 |  | 2021-03-23 | 2021-03-23 | 2021-04-05 | 2021-09-27 | 2021-10-01 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-13568 | Newburgh | Newburgh | Orange | 12550 | G | 4051 | Union Ave | Y |  | 8.64 | 3.84 | [12 empty] | NM | N | 1 Delta Electronics M5-TL-US (240V) [SI1] 1 Delta Electronics E4-TL-US (240V) [SI1] 1Delta ElectronicsE4-TL-US | 2021-03-18 | 2021-03-18 | 0 | 2021-03-18 | [14 empty] | 2022-06-01 | 2022-06-03 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-13565 | Newburgh | New Windsor | Orange | 12553 | G | 4044 | Union Ave | N |  | 8.12 | [13 empty] | NM | N | 28 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-03-15 | 2021-03-16 | 1 | 2021-03-16 | [14 empty] | 2021-05-17 | 2021-05-17 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-13567 | Kingston | Kingston | Ulster | 12401 | G | 111 | South Wall St | N |  | 5.22 | [13 empty] | NM | N | 18 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-03-15 | 2021-03-15 | 0 | 2021-03-15 | [17 empty] | W
Central Hudson |  | Sunrun Installation Services, Inc. | CH-13566 | Poughkeepsie | Clinton Cors | Dutchess | 12514 | G | 7013 | Hibernia | N | CH-09326 | 3.84 | [13 empty] | NM | N | 1 Delta Electronics M4-TL-US (240V) [SI1] | 2021-03-15 | 2021-03-15 | 0 | 2021-03-15 | [14 empty] | 2021-06-11 | 2021-06-11 |  | Y
Central Hudson |  | Lighthouse Solar | CH-13564 | Newburgh | New Paltz | Ulster | 12561 | G | 5031 | Galeville | Y |  | 22.8 | 22.8 | [12 empty] | NM | N | 3 Generac Power Systems X7602 (240V) 3Generac7.6kW X7602 (240v) | 2021-03-15 | 2021-03-16 | 1 | 2021-03-16 | [8 empty] | 350 | 350 |  | 2021-03-18 | 2021-03-18 | 2021-05-17 | 2021-05-20 | 2021-05-20 |  | Y
Central Hudson |  | PlugPV LLC | CH-13569 | Fishkill | Beacon | Dutchess | 12508 | G | 8017 | Forgebrook | N |  | 3.8 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3800H-US (240V) | 2021-03-15 | 2021-03-15 | 0 | 2021-03-15 | [14 empty] | 2021-05-19 | 2021-05-19 |  | Y
Central Hudson |  | Tesla | CH-13573 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8092 | Fishkill Plains | Y |  | 11.4 | 15 | [12 empty] | NM | N | 1 Tesla 1538000-xx-y (240V) [SI1] 1 Tesla 1534000-xx-y (240V) [SI1] 3TeslaAc Powerwall 2.0 | 2021-03-15 | 2021-03-16 | 1 | 2021-03-16 | [14 empty] | 2021-07-29 | 2021-07-29 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-13570 | Fishkill | Nelsonvl | Putnam | 10516 | G | 8087 | Tioronda | N |  | 5.8 | [13 empty] | NM | N | 20 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-03-17 | 2021-03-17 | 0 | 2021-03-17 | [14 empty] | 2021-06-24 | 2021-06-24 |  | Y
Central Hudson |  | Tesla | CH-13571 | Kingston | Stone Ridge |  | 12484 | G | 3023 | High Falls | Y |  | 15.38 | 20 | [12 empty] | NM | N | 2 Delta Electronics M8-TL-US (240V) [SI1] 4TeslaAc Powerwall 2.0 | 2021-03-15 | 2021-03-16 | 1 | 2021-03-16 | [17 empty] | W
Central Hudson |  | Empire Solar Solutions | CH-13574 | Catskill | Cairo | Greene | 12413 | G | 2041 | South Cairo | N |  | 6.38 | [13 empty] | NM | N | 22 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-03-16 | 2021-03-16 | 0 | 2021-03-16 | [14 empty] | 2021-04-09 | 2021-04-09 |  | Y
Central Hudson |  | SunCommon | CH-13576 | Newburgh | Marlboro | Ulster | 12542 | G | 5003 | Marlboro | N |  | 15.08 | [13 empty] | NM | N | 13 Enphase Energy IQ7PLUS-72-x-US (240V) 13 Enphase Energy IQ7PLUS-72-x-US (240V) 13 Enphase Energy IQ7PLUS-72-x-US (240V) 13 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-03-16 | 2021-03-16 | 0 | 2021-03-16 | [17 empty] | W
Central Hudson |  | Lighthouse Solar | CH-13575 | Fishkill | Cold Spg |  | 10516 | G | 8063 | Merritt Park | N |  | 11.6 | [13 empty] | NM | N | 40 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-03-16 | 2021-03-26 | 8 | 2021-03-26 | [17 empty] | W
Central Hudson |  | PlugPV LLC | CH-13578 | Poughkeepsie | Lagrangevl | Dutchess | 12540 | G | 6055 | Todd Hill | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2021-03-17 | 2021-03-17 | 0 | 2021-03-17 | [14 empty] | 2021-04-26 | 2021-04-26 |  | Y
Central Hudson |  | AEC Solar Energy Corp | CH-13579 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7061 | Milan | N | CH-03057 | 8.82 | [13 empty] | NM | N | 28 Enphase Energy IQ7XS-96-x-ACM-US-y-z-& (240V) [SI1] | 2021-04-01 | 2021-04-06 | 2 | 2021-04-06 | [8 empty] | 350 | 350 |  | 2021-04-09 | 2021-04-09 | 2021-05-21 | 2021-06-11 | 2021-06-11 |  | Y
Central Hudson |  | AEC Solar Energy Corp | CH-13577 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7053 | Rhinebeck | Y |  | 7.6 | 7.6 | [12 empty] | NM | N | 1 Generac Power Systems X7602 (240V) 1Generacx7602 | 2021-03-18 | 2021-03-18 | 0 | 2021-03-18 | [14 empty] | 2021-05-10 | 2021-05-10 |  | Y
Central Hudson |  | HARVEST POWER LLC | CH-13580 | Kingston | Boiceville | Ulster | 12412 | G | 3011 | Woodstock | N |  | 300 | [13 empty] | NM | Y | 6 Chint Power Systems America CPS SCA50KTL-DO/US-480 (480V) | 2021-04-14 | 2021-04-27 | 9 | 2021-04-27 | 2021-04-27 | 2021-05-18 | 15 | [11 empty] | 2022-04-05 | 2022-04-05 |  | Y | Y
Central Hudson |  | New York State Solar Farm | CH-13584 | Kingston | Napanoch | Ulster | 12458 | G | 3072 | Honk Falls | N |  | 15.75 | [13 empty] | NM | N | 50 SunPower SPR-E20-327-E-AC (240V) | 2021-03-18 | 2021-03-18 | 0 | 2021-03-18 | [8 empty] | 350 | 350 |  | 2021-03-23 | 2021-03-23 | 2021-04-07 | 2021-04-28 | 2021-04-28 |  | Y
Central Hudson |  | PlugPV, LLC | CH-13581 | Newburgh | Newburgh | Orange | 12550 | G | 5004 | Marlboro | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) [SI1] | 2021-03-18 | 2021-03-18 | 0 | 2021-03-18 | [14 empty] | 2021-05-07 | 2021-05-07 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-13582 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8072 | Shenandoah | N |  | 5.8 | [13 empty] | NM | N | 20 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-03-18 | 2021-03-18 | 0 | 2021-03-18 | [14 empty] | 2021-04-23 | 2021-04-23 |  | Y
Central Hudson |  | PlugPV, LLC | CH-13583 | Newburgh | Marlboro | Ulster | 12542 | G | 5004 | Marlboro | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) [SI1] | 2021-03-18 | 2021-03-18 | 0 | 2021-03-18 | [14 empty] | 2021-04-23 | 2021-04-23 |  | Y
Central Hudson |  | PlugPV, LLC | CH-13585 | Kingston | Grahamsvl | Sullivan | 12740 | G | 3091 | Neversink | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE11400H-US (240V) | 2021-03-18 | 2021-03-18 | 0 | 2021-03-18 | [14 empty] | 2021-03-22 | 2021-03-22 |  | Y
Central Hudson |  | Tesla | CH-13586 | Kingston | Cottekill | Ulster | 12419 | G | 3021 | High Falls | Y |  | 7.6 | 10 | [12 empty] | NM | N | 1 Tesla 1538000-xx-y (240V) [SI1] 2TeslaAc Powerwall 2.0 | 2021-03-19 | 2021-03-19 | 0 | 2021-03-19 | [14 empty] | 2021-07-29 | 2021-07-29 |  | Y
Central Hudson |  | murphy solar and central air | CH-13587 | Catskill | Hunter | Greene | 12442 | E | 2081 | Hunter | N |  | 7 | [13 empty] | NM | N | 1 SMA America SB7000TL-US-22 (240V) | 2021-03-22 | 2021-03-22 | 0 | 2021-03-22 | [14 empty] | 2021-06-04 | 2021-06-04 |  | Y
Central Hudson |  | Hudson River Solar | CH-13588 | Catskill | Catskill | Greene | 12414 | G | 2001 | North Catskill | Y |  | 9 | 8 | [12 empty] | NM | N | 1 Sol-Ark Sol-Ark-12K-P (240V) 1Sol-ArkSol-Ark 12K-P (240V) | 2021-03-22 | 2021-03-22 | 0 | 2021-03-22 | [14 empty] | 2021-06-02 | 2021-06-02 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-13589 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8095 | Fishkill Plains | N |  | 5.8 | [13 empty] | NM | N | 4 Enphase Energy IQ7PLUS-72-x-US (240V) 16 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-03-22 | 2021-03-22 | 0 | 2021-03-22 | [14 empty] | 2021-06-23 | 2021-06-23 |  | Y
Central Hudson |  | SunCommon | CH-13591 | Newburgh | Newburgh | Orange | 12550 | G | 4013 | West Balmville | N |  | 15.95 | [13 empty] | NM | N | 15 Enphase Energy IQ7PLUS-72-x-US (240V) 40 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-03-22 | 2021-03-23 | 1 | 2021-03-23 | [14 empty] | 2021-06-03 | 2021-06-03 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-13590 | Newburgh | Newburgh | Orange | 12550 | G | 4054 | Union Ave | N |  | 4.93 | [13 empty] | NM | N | 17 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-03-22 | 2021-03-22 | 0 | 2021-03-22 | [14 empty] | 2021-05-18 | 2021-05-18 |  | Y
Central Hudson |  | PlugPV LLC | CH-13594 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6073 | East Park | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2021-03-24 | 2021-03-24 | 0 | 2021-03-24 | [14 empty] | 2021-05-03 | 2021-05-03 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-13593 | Catskill | Coxsackie | Greene | 12051 | G | 1071 | Coxsackie | N |  | 5.8 | [13 empty] | NM | N | 20 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-03-24 | 2021-03-24 | 0 | 2021-03-24 | [14 empty] | 2021-04-12 | 2021-04-12 |  | Y
Central Hudson |  | PlugPV LLC | CH-13595 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8023 | Knapps Corners | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2021-03-24 | 2021-03-24 | 0 | 2021-03-24 | [14 empty] | 2021-04-30 | 2021-04-30 |  | Y
Central Hudson |  | Lighthouse Solar | CH-13592 | Newburgh | Highland | Ulster | 12528 | G | 5024 | Ohioville | N |  | 10.73 | [13 empty] | NM | N | 37 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-03-24 | 2021-03-24 | 0 | 2021-03-24 | [14 empty] | 2021-04-22 | 2021-04-22 |  | Y
Central Hudson |  | SunCommon | CH-13598 | Poughkeepsie | Ancramdale | Columbia | 12503 | G | 7092 | Pulvers Corners | N |  | 15.4 | [13 empty] | NM | N | 2 SMA America SB7.7-1TP-US-40 (240V) | 2021-03-25 | 2021-03-25 | 0 | 2021-03-25 | [8 empty] | 350 | 350 |  | 2021-04-01 | 2021-04-01 | 2021-05-21 | 2021-07-26 | 2021-07-26 |  | Y
Central Hudson |  | Tesla Energy Operations, Inc. | CH-13602 | Kingston | Grahamsvl | Sullivan | 12740 | G | 3091 | Neversink | Y |  | 7.6 | 5 | [12 empty] | NM | N | 1 Tesla 1538000-xx-y (240V) [SI1] 1TeslaAC Powerwall 2.0 | 2021-03-26 | 2021-03-26 | 0 | 2021-03-26 | [14 empty] | 2021-07-30 | 2021-07-30 |  | Y
Central Hudson |  | SunCommon | CH-13601 | Newburgh | New Paltz | Ulster | 12561 | G | 5023 | Ohioville | N |  | 11.4 | [13 empty] | NM | N | 1 Tesla 1534000-xx-y (240V) [SI1] 1 Tesla 1538000-xx-y (240V) [SI1] | 2021-04-05 | 2021-04-06 | 1 | 2021-04-06 | [14 empty] | 2021-07-15 | 2021-07-15 |  | Y
Central Hudson |  | Red Hook Solar | CH-13597 | Kingston | Kingston | Ulster | 12401 | G | 1013 | Boulevard | N |  | 2.32 | [13 empty] | NM | N | 8 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-04-06 | 2021-04-08 | 2 | 2021-04-08 | [14 empty] | 2021-06-22 | 2021-06-22 |  | Y
Central Hudson |  | SunCommon | CH-13599 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7054 | Rhinebeck | N |  | 76.8 | [13 empty] | NM | Y | 10 SMA America SB7.7-1SP-US-41 (240V) [SI1] | 2021-04-27 | 2021-05-05 | 6 | 2021-05-05 | 2021-05-05 | 2021-05-26 | 15 | [5 empty] | 2324.04 | 2385.12 |  | 2021-06-21 | 2021-06-21 | 2021-09-20 | 2021-10-29 | 2021-10-29 | 2022-01-28 | Y | Y
Central Hudson |  | New York Power Solutions | CH-13600 | Newburgh | New Windsor | Orange | 12553 | G | 4046 | Union Ave | N |  | 6.24 | [13 empty] | NM | N | 26 Enphase Energy IQ7-60-x-US (240V) | 2021-03-25 | 2021-03-25 | 0 | 2021-03-25 | [14 empty] | 2021-05-10 | 2021-05-10 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-13605 | Newburgh | Montgomery | Orange | 12549 | G | 5073 | Montgomery | N |  | 6.96 | [13 empty] | NM | N | 24 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-03-26 | 2021-03-29 | 1 | 2021-03-29 | [14 empty] | 2021-04-16 | 2021-04-16 |  | Y
Central Hudson |  | MOMENTUM SOLAR | CH-13603 | Newburgh | Montgomery | Orange | 12549 | G | 5072 | Montgomery | N |  | 6.38 | [13 empty] | NM | N | 22 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-03-26 | 2021-03-26 | 0 | 2021-03-26 | [14 empty] | 2021-06-04 | 2021-06-04 |  | Y
Central Hudson |  | New York Power Solutions | CH-13604 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8096 | Fishkill Plains | N |  | 5.28 | [13 empty] | NM | N | 22 Enphase Energy IQ7-60-x-US (240V) | 2021-03-26 | 2021-03-26 | 0 | 2021-03-26 | [14 empty] | 2021-06-09 | 2021-06-09 |  | Y
Central Hudson |  | Green Hybrid Energy Solutions | CH-13612 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8093 | Fishkill Plains | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2021-03-29 | 2021-03-30 | 1 | 2021-03-30 | [14 empty] | 2022-12-06 | 2022-12-08 |  | Y
Central Hudson |  | Green Hybrid Energy Solutions | CH-13611 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8093 | Fishkill Plains | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2021-03-29 | 2021-03-30 | 1 | 2021-03-30 | [14 empty] | 2022-12-06 | 2022-12-08 |  | Y
Central Hudson |  | Green Hybrid Energy Solutions | CH-13608 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8093 | Fishkill Plains | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2021-03-29 | 2021-03-29 | 0 | 2021-03-29 | [14 empty] | 2022-12-01 | 2022-12-05 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-13606 | Newburgh | Newburgh | Orange | 12550 | G | 4011 | West Balmville | N |  | 14.5 | [13 empty] | NM | N | 50 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-03-29 | 2021-03-29 | 0 | 2021-03-29 | [8 empty] | 350 | 350 |  | 2021-03-31 | 2021-03-31 | 2021-04-20 | 2021-05-07 | 2021-05-07 |  | Y
Central Hudson |  | PlugPV, LLC | CH-13609 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) [SI1] | 2021-03-29 | 2021-03-29 | 0 | 2021-03-29 | [14 empty] | 2021-05-06 | 2021-05-06 |  | Y
Central Hudson |  | PlugPV, LLC | CH-13610 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) [SI1] | 2021-03-29 | 2021-03-29 | 0 | 2021-03-29 | [14 empty] | 2021-06-02 | 2021-06-02 |  | Y |  | 5/15/21 - CH rep had no access to install net meter. 6/2/21 - Net meter installed.
Central Hudson |  | Solar Generation | CH-13607 | Newburgh | Wallkill | Ulster | 12589 | G | 5030 | Galeville | N |  | 20.16 | [13 empty] | NM | N | 64 Enphase Energy IQ7X-96-x-US (240V) | 2021-03-29 | 2021-03-29 | 0 | 2021-03-29 | [8 empty] | 350 | 350 |  | 2021-03-31 | 2021-03-31 | 2021-04-27 | 2021-05-07 | 2021-05-07 |  | Y
Central Hudson |  | PlugPV, LLC | CH-13613 | Fishkill | Fishkill | Dutchess | 12524 | G | 8016 | Forgebrook | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) [SI1] | 2021-03-29 | 2021-03-30 | 1 | 2021-03-30 | [14 empty] | 2021-06-04 | 2021-06-04 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-13617 | Newburgh | Newburgh | Orange | 12550 | G | 4011 | West Balmville | N |  | 9.6 | [13 empty] | NM | N | 2 Delta Electronics M5-TL-US (240V) [SI1] | 2021-03-30 | 2021-03-31 | 1 | 2021-03-31 | [14 empty] | 2021-05-25 | 2021-05-25 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-13621 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6061 | Inwood Ave | N |  | 4.8 | [13 empty] | NM | N | 1 Delta Electronics M5-TL-US (240V) [SI1] | 2021-03-30 | 2021-03-31 | 1 | 2021-03-31 | [14 empty] | 2021-05-03 | 2021-05-03 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-13616 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6061 | Inwood Ave | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2021-03-30 | 2021-03-30 | 0 | 2021-03-30 | [14 empty] | 2021-05-21 | 2021-05-21 |  | Y
Central Hudson |  | Trinity Solar | CH-13618 | Newburgh | Montgomery | Orange | 12549 | G | 5072 | Montgomery | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2021-03-31 | 2021-03-31 | 0 | 2021-03-31 | [14 empty] | 2021-05-06 | 2021-05-06 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-13615 | Newburgh | Wallkill | Ulster | 12589 | G | 4011 | West Balmville | N |  | 12.47 | [13 empty] | NM | N | 43 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-03-30 | 2021-03-30 | 0 | 2021-03-30 | [14 empty] | 2021-04-28 | 2021-04-28 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-13619 | Newburgh | Newburgh | Orange | 12550 | G | 4014 | West Balmville | N | CH-13619 | 5.76 | [13 empty] | NM | N | 1 Delta Electronics M6-TL-US (240V) [SI1] | 2021-03-30 | 2021-03-31 | 1 | 2021-03-31 | [14 empty] | 2021-05-18 | 2021-05-18 |  | Y
Central Hudson |  | Trinity Solar | CH-13614 | Newburgh | Montgomery | Orange | 12549 | G | 5073 | Montgomery | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE11400H-US (240V) | 2021-03-30 | 2021-03-30 | 0 | 2021-03-30 | [8 empty] | 350 | 350 |  | 2021-04-08 | 2021-04-08 | 2021-04-20 | 2021-06-28 | 2021-06-28 |  | Y
Central Hudson |  | PlugPV, LLC | CH-13620 | Newburgh | Cornwall | Orange | 12518 | G | 4094 | Bethlehem Rd | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) [SI1] | 2021-03-30 | 2021-03-31 | 1 | 2021-03-31 | [14 empty] | 2021-07-28 | 2021-07-28 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-13624 | Newburgh | Newburgh | Orange | 12550 | G | 4012 | West Balmville | N |  | 10.15 | [13 empty] | NM | N | 35 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-03-31 | 2021-03-31 | 0 | 2021-03-31 | [14 empty] | 2021-04-20 | 2021-04-20 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-13631 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 7025 | Tinkertown | Y |  | 7.68 | 5 | [12 empty] | NM | N | 1 Delta Electronics E8-TL-US (240V) [SI1] 1Delta ElectronicsE8-TL-US | 2021-03-31 | 2021-04-01 | 1 | 2021-04-01 | [17 empty] | W
Central Hudson |  | Sunrun Installation Services, Inc. | CH-13630 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6003 | Reynolds Hill | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2021-04-01 | 2021-04-01 | 0 | 2021-04-01 | [14 empty] | 2021-06-25 | 2021-06-25 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-13629 | Kingston | Greenfield Pk | Ulster | 12435 | G | 3096 | Grimley Rd | Y |  | 17.28 | 5 | [12 empty] | NM | N | 1 Delta Electronics E6-TL-US (240V) [SI1] 1 Delta Electronics M4-TL-US (240V) [SI1] 1 Delta Electronics M8-TL-US (240V) [SI1] 1Delta ElectronicsE6-TL-US | 2021-04-06 | 2021-04-08 | 2 | 2021-04-08 | [8 empty] | 350 | 350 |  | 2021-04-21 | 2021-04-21 | 2021-05-07 | 2021-11-05 | 2021-11-05 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-13628 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 7011 | Hibernia | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2021-03-31 | 2021-04-01 | 1 | 2021-04-01 | [14 empty] | 2021-07-08 | 2021-07-08 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-13627 | Kingston | Saugerties | Ulster | 12477 | G | 3002 | Saugerties | N |  | 11.6 | [13 empty] | NM | N | 40 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-04-06 | 2021-04-08 | 2 | 2021-04-08 | [14 empty] | 2021-09-09 | 2021-10-05 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-13626 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 6075 | East Park | Y |  | 3.84 | 3.84 | [12 empty] | NM | N | 1 Delta Electronics M4-TL-US (240V) [SI1] 1Delta ElectronicsE6-TL-US | 2021-03-31 | 2021-04-01 | 1 | 2021-04-01 | [14 empty] | 2021-12-15 | 2021-12-15 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-13625 | Newburgh | New Windsor | Orange | 12553 | G | 4097 | Bethlehem Rd | Y | CH-13625 | 5.76 | 5 | [12 empty] | NM | N | 1 Delta Electronics M6-TL-US (240V) [SI1] 1TeslaAC Powerwall 2.0 | 2021-04-05 | 2021-04-07 | 2 | 2021-04-07 | [8 empty] | 350 | 350 |  | 2021-04-21 | 2021-04-21 | 2021-08-06 | 2021-12-17 | 2021-12-21 |  | Y
Central Hudson |  | Trinity Solar | CH-13622 | Newburgh | Newburgh | Orange | 12550 | G | 4023 | Coldenham | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000H-US (240V) | 2021-03-30 | 2021-03-31 | 1 | 2021-03-31 | [14 empty] | 2021-05-26 | 2021-05-26 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-13623 | Newburgh | Newburgh | Orange | 12550 | G | 4015 | West Balmville | N |  | 4.64 | [13 empty] | NM | N | 16 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-03-31 | 2021-03-31 | 0 | 2021-03-31 | [14 empty] | 2021-04-28 | 2021-04-28 |  | Y
Central Hudson |  | Gottschalk Solutions | CH-13639 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7055 | Rhinebeck | N |  | 38 | [13 empty] | NM | N | 3 SolarEdge Technologies SE11400H-US (240V) 1 SolarEdge Technologies SE3800H-US (240V) | 2021-05-03 | 2021-05-10 | 5 | 2021-05-10 | [8 empty] | 7760 | 1958.98 |  | 2021-08-03 | 2021-08-03 | 2021-09-21 | 2022-06-06 | 2022-06-06 | 2022-06-23 | Y | N
Central Hudson |  | KASSELMAN SOLAR | CH-13638 | Kingston | Kerhonkson | Ulster | 12446 | G | 3082 | Kerhonkson | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000H-US (208V) | 2021-04-13 | 2021-04-14 | 1 | 2021-04-14 | [14 empty] | 2021-05-19 | 2021-05-19 |  | Y
Central Hudson |  | KASSELMAN SOLAR | CH-13637 | Fishkill | Cold Spg | Putnam | 10516 | G | 8087 | Tioronda | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2021-04-09 | 2021-04-12 | 1 | 2021-04-12 | [14 empty] | 2021-04-28 | 2021-04-28 |  | Y
Central Hudson |  | KASSELMAN SOLAR | CH-13636 | Kingston | Stone Ridge | Ulster | 12484 | G | 3023 | High Falls | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2021-04-12 | 2021-04-13 | 1 | 2021-04-13 | [8 empty] | 350 | 350 |  | 2021-04-15 | 2021-04-15 | 2021-04-16 | 2021-04-28 | 2021-04-28 |  | Y
Central Hudson |  | SunCommon | CH-13632 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7052 | Rhinebeck | N | CH-00648 | 4.64 | [13 empty] | NM | N | 16 Enphase Energy IQ7PLUS-72-2-US (240V) [SI1] | 2021-04-26 | 2021-04-30 | 4 | 2021-04-30 | [14 empty] | 2021-06-11 | 2021-06-11 |  | Y
Central Hudson |  | PlugPV, LLC | CH-13635 | Newburgh | Cornwall | Orange | 12518 | G | 4094 | Bethlehem Rd | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) [SI1] | 2021-04-01 | 2021-04-01 | 0 | 2021-04-01 | [14 empty] | 2021-07-29 | 2021-07-29 |  | Y
Central Hudson |  | Solar Generation | CH-13633 | Kingston | Kingston | Ulster | 12401 | G | 1024 | East Kingston | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2021-03-31 | 2021-04-01 | 1 | 2021-04-01 | [14 empty] | 2021-06-04 | 2021-06-04 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-13634 | Kingston | Kingston | Ulster | 12401 | G | 1021 | East Kingston | N |  | 7.54 | [13 empty] | NM | N | 26 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-04-01 | 2021-04-01 | 0 | 2021-04-01 | [14 empty] | 2021-04-30 | 2021-04-30 |  | Y
Central Hudson |  | Solar Alchemy, Inc. | CH-13642 | Kingston | Kerhonkson | Ulster | 12446 | G | 3082 | Kerhonkson | Y |  | 8 | 8 | [12 empty] | NM | N | 1 OutBack Power Technologies GS8048A 1Outback PowerGS8048A / Flex Power Radian | 2021-05-11 | 2021-05-19 | 6 | 2021-05-19 | [8 empty] | 350 | 350 |  | 2021-07-21 | 2021-07-21 | 2021-08-24 | 2021-09-20 | 2021-09-27 |  | Y
Central Hudson |  | SunCommon | CH-13640 | Kingston | Napanoch | Ulster | 12458 | G | 3072 | Honk Falls | Y |  | 7.6 | 5 | [12 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) 1TeslaPowerwall | 2021-04-05 | 2021-04-07 | 2 | 2021-04-07 | [14 empty] | 2021-04-14 | 2021-04-14 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-13641 | Newburgh | Washingtonvl | Orange | 10992 | G | 4097 | Bethlehem Rd | N | CH-13641 | 9.57 | [13 empty] | NM | N | 33 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-04-05 | 2021-04-07 | 2 | 2021-04-07 | [14 empty] | 2021-07-23 | 2021-07-23 |  | Y
Central Hudson |  | Lighthouse Solar | CH-13643 | Kingston | Stone Ridge | Ulster | 12484 | G | 3023 | High Falls | N |  | 6.09 | [13 empty] | NM | N | 21 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-04-05 | 2021-04-07 | 2 | 2021-04-07 | [14 empty] | 2021-06-25 | 2021-06-25 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-13645 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6002 | Reynolds Hill | N |  | 10.73 | [13 empty] | NM | N | 37 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-04-05 | 2021-04-08 | 3 | 2021-04-08 | [14 empty] | 2021-05-07 | 2021-05-07 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-13644 | Kingston | Kingston | Ulster | 12401 | G | 3021 | High Falls | N |  | 6.96 | [13 empty] | NM | N | 24 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-04-05 | 2021-04-07 | 2 | 2021-04-07 | [14 empty] | 2021-07-13 | 2021-07-13 |  | Y
Central Hudson |  | SunCommon | CH-13647 | Newburgh | New Paltz | Ulster | 12561 | G | 5031 | Galeville | Y | CH-00628 |  | 10 | [12 empty] | NM | N | 1TeslaPowerwall 2 | 2021-04-08 | 2021-04-12 | 2 | 2021-04-12 | [14 empty] | 2022-05-23 | 2022-05-25 |  | Y
Central Hudson |  | Solar Generation | CH-13648 | Kingston | Stone Ridge | Ulster | 12484 | G | 3023 | High Falls | N |  | 14.49 | [13 empty] | NM | N | 46 Enphase Energy IQ7X-96-x-US (240V) | 2021-04-08 | 2021-04-12 | 2 | 2021-04-12 | [14 empty] | 2021-06-09 | 2021-06-09 |  | Y
Central Hudson |  | Solar Generation | CH-13649 | Kingston | Stone Ridge | Ulster | 12484 | G | 3023 | High Falls | N |  | 2.84 | [13 empty] | NM | N | 9 Enphase Energy IQ7X-96-x-US (240V) | 2021-04-06 | 2021-04-08 | 2 | 2021-04-08 | [14 empty] | 2021-06-22 | 2021-06-22 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-13646 | Poughkeepsie | Salt Pt | Dutchess | 12578 | G | 7011 | Hibernia | N | CH-13646 | 12.47 | [13 empty] | NM | N | 43 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-04-13 | 2021-04-14 | 1 | 2021-04-14 | [8 empty] | 350 | 350 |  | 2021-04-16 | 2021-04-16 | 2021-05-11 | 2021-06-23 | 2021-06-23 |  | Y
Central Hudson |  | KASSELMAN SOLAR | CH-13650 | Kingston | Olive Brdg | Ulster | 12461 | G | 3024 | High Falls | N |  | 6.67 | [13 empty] | NM | N | 23 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-04-07 | 2021-04-09 | 2 | 2021-04-09 | [14 empty] | 2021-05-27 | 2021-05-27 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-13653 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6052 | Todd Hill | N |  | 10.73 | [13 empty] | NM | N | 37 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-04-07 | 2021-04-09 | 2 | 2021-04-09 | [14 empty] | 2021-04-29 | 2021-04-29 |  | Y
Central Hudson |  | New York State Solar Farm | CH-13655 | Kingston | Tillson | Ulster | 12486 | G | 3022 | High Falls | N |  | 20.475 | [13 empty] | NM | N | 65 SunPower SPR-E20-327-E-AC (240V) | 2021-04-07 | 2021-04-09 | 2 | 2021-04-09 | [14 empty] | 2021-04-27 | 2021-04-27 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-13652 | Kingston | Kingston | Ulster | 12401 | G | 2093 | Hurley Ave | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2021-04-07 | 2021-04-09 | 2 | 2021-04-09 | [17 empty] | W
Central Hudson |  | SunCommon | CH-13651 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7041 | Staatsburg | N |  | 20 | [13 empty] | NM | N | 2 SolarEdge Technologies SE10000H-US (240V) | 2021-04-07 | 2021-04-09 | 2 | 2021-04-09 | [14 empty] | 2021-04-22 | 2021-04-22 |  | Y
Central Hudson |  | Nexamp Solar,LLC | CH-13656 | Catskill | Cairo | Greene | 12413 | G | 2043 | South Cairo | N |  | 5000 | [13 empty] | CDG | Y | 2 SMA America SC 4000 UP-US 600V 3850A (600V) [SI1] | 2021-05-20 | 2021-06-03 | 9 | 2021-06-03 | 2021-06-03 | 2021-06-23 | 14 | 2021-09-22 | 2021-11-15 | 2022-02-14 | 60 | 19265.27 | 8511753.75 | [7 empty] | 2022-08-22 | W
Central Hudson |  | Lighthouse Solar | CH-13658 | Poughkeepsie | Lagrangevl | Dutchess | 12540 | G | 6053 | Todd Hill | N |  | 12.18 | [13 empty] | NM | N | 42 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-04-08 | 2021-04-09 | 1 | 2021-04-09 | [14 empty] | 2021-05-25 | 2021-05-25 |  | Y
Central Hudson |  | Trinity Solar | CH-13659 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000H-US (240V) | 2021-04-23 | 2021-04-27 | 2 | 2021-04-27 | [14 empty] | 2021-07-29 | 2021-07-29 |  | Y
Central Hudson |  | SunCommon | CH-13657 | Kingston | Boicevl | Ulster | 12412 | G | 3011 | Woodstock | Y | CH-10040 |  | 5 | [12 empty] | NM | N | 1TeslaPowerwall 2 | 2021-05-04 | 2021-05-11 | 5 | 2021-05-11 | [14 empty] | 2021-07-23 | 2021-07-23 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-13660 | Fishkill | Beacon | Dutchess | 12508 | G | 8015 | Forgebrook | N |  | 4.35 | [13 empty] | NM | N | 15 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-04-09 | 2021-04-12 | 1 | 2021-04-12 | [14 empty] | 2021-09-07 | 2021-09-14 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-13661 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 7024 | Tinkertown | N |  | 10.73 | [13 empty] | NM | N | 37 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-04-12 | 2021-04-12 | 0 | 2021-04-12 | [14 empty] | 2021-05-21 | 2021-05-21 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-13665 | Newburgh | Goshen | Orange | 10924 | G | 5051 | Maybrook | N |  | 6.24 | [13 empty] | NM | N | 26 Enphase Energy IQ7-60-x-US (240V) | 2021-04-12 | 2021-04-13 | 1 | 2021-04-13 | [14 empty] | 2021-05-25 | 2021-05-25 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-13666 | Newburgh | Newburgh | Orange | 12550 | G | 4045 | Union Ave | N |  | 6.96 | [13 empty] | NM | N | 24 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-04-12 | 2021-04-13 | 1 | 2021-04-13 | [14 empty] | 2021-09-20 | 2021-09-27 |  | Y
Central Hudson |  | New York State Solar Farm | CH-13663 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6092 | Manchester | N |  | 6.3 | [13 empty] | NM | N | 20 SunPower SPR-X22-360-E-AC (240V) | 2021-04-15 | 2021-04-19 | 2 | 2021-04-19 | [14 empty] | 2021-05-18 | 2021-05-18 |  | Y
Central Hudson |  | New York State Solar Farm | CH-13662 | Kingston | Accord | Ulster | 12404 | G | 3081 | Kerhonkson | N |  | 6.615 | [13 empty] | NM | N | 21 SunPower SPR-X22-360-E-AC (240V) | 2021-04-12 | 2021-04-13 | 1 | 2021-04-13 | [14 empty] | 2021-04-22 | 2021-04-22 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-13667 | Fishkill | Wappingrs Fls |  | 12590 | G | 8022 | Knapps Corners | N |  | 5.76 | [13 empty] | NM | N | 1 Delta Electronics M6-TL-US (240V) [SI1] | 2021-05-06 | 2021-05-12 | 4 | 2021-05-12 | [17 empty] | W
Central Hudson |  | Sunrun Installation Services, Inc. | CH-13664 | Kingston | Kingston | Ulster | 12401 | G | 1024 | East Kingston | N |  | 5.76 | [13 empty] | NM | N | 1 Delta Electronics M6-TL-US (240V) [SI1] | 2021-04-12 | 2021-04-13 | 1 | 2021-04-13 | [14 empty] | 2021-07-23 | 2021-07-23 |  | Y
Central Hudson |  | PlugPV LLC | CH-13668 | Kingston | Port Ewen | Ulster | 12466 | G | 1023 | East Kingston | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2021-04-12 | 2021-04-13 | 1 | 2021-04-13 | [14 empty] | 2021-05-28 | 2021-05-28 |  | Y
Central Hudson |  | New York State Solar Farm | CH-13670 | Newburgh | New Paltz | Ulster | 12561 | G | 5011 | Modena | Y |  | 36.65 | 30 | [12 empty] | NM | N | 105 SunPower SPR-A420-G-AC (240V) [SI1] 6TESLATESLA POWERWALL 2 | 2021-05-18 | 2021-06-02 | 10 | 2021-06-02 | [14 empty] | 2021-11-09 | 2021-11-17 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-13675 | Poughkeepsie | Poughquag | Dutchess | 12570 | G | 6055 | Todd Hill | N |  | 9.57 | [13 empty] | NM | N | 33 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-04-13 | 2021-04-14 | 1 | 2021-04-14 | [14 empty] | 2021-06-15 | 2021-06-15 |  | Y
Central Hudson |  | PlugPV, LLC | CH-13671 | Fishkill | Beacon | Dutchess | 12508 | G | 8017 | Forgebrook | N |  | 12 | [13 empty] | NM | N | 2 SolarEdge Technologies SE6000H-US (240V) | 2021-04-13 | 2021-04-14 | 1 | 2021-04-14 | [14 empty] | 2021-06-16 | 2021-06-16 |  | Y
Central Hudson |  | SunPower Direct (NY) | CH-13674 | Newburgh | Newburgh | Orange | 12550 | G | 4022 | Coldenham | N |  | 11.34 | [13 empty] | NM | N | 36 Enphase Energy IQ7XS-96-x-US-& (240V) [SI1] | 2021-04-19 | 2021-04-21 | 2 | 2021-04-21 | [14 empty] | 2021-08-05 | 2021-08-05 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-13673 | Newburgh | Wallkill | Ulster | 12589 | G | 5043 | East Walden | N |  | 6.67 | [13 empty] | NM | N | 23 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-04-13 | 2021-04-14 | 1 | 2021-04-14 | [14 empty] | 2021-07-30 | 2021-07-30 |  | Y
Central Hudson |  | New York State Solar Farm | CH-13669 | Newburgh | Highland | Ulster | 12528 | G | 5082 | Highland | N |  | 11.34 | [13 empty] | NM | N | 36 SunPower SPR-X22-360-E-AC (240V) | 2021-04-13 | 2021-04-14 | 1 | 2021-04-14 | [8 empty] | 350 | 350 |  | 2021-04-20 | 2021-04-20 | 2021-05-12 | 2021-05-26 | 2021-05-26 |  | Y
Central Hudson |  | KASSELMAN SOLAR | CH-13672 | Catskill | Catskill | Greene | 12414 | G | 2042 | South Cairo | N |  | 7.6 | [13 empty] | RC | Y | 1 SolarEdge Technologies SE7600H-US (240V) | 2021-04-13 | 2021-04-14 | 1 | 2021-04-14 | [14 empty] | 2021-05-17 | 2021-05-17 |  | W | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-13678 | Catskill | Palenvl | Greene | 12463 | G | 2001 | North Catskill | N |  | 15.36 | [13 empty] | NM | N | 1 Delta Electronics M6-TL-US (240V) [SI1] 1 Delta Electronics M10-TL-US (240V) [SI1] | 2021-04-14 | 2021-04-16 | 2 | 2021-04-16 | [14 empty] | 2021-07-28 | 2021-07-28 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-13677 | Fishkill | Garrison | Putnam | 10524 | G | 8066 | Merritt Park | N |  | 18.27 | [13 empty] | NM | N | 48 Enphase Energy IQ7PLUS-72-x-US (240V) 15 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-04-14 | 2021-04-16 | 2 | 2021-04-16 | [14 empty] | 2021-07-01 | 2021-07-01 |  | Y
Central Hudson |  | LastMile Energy, LLC | CH-13676 | Newburgh | Walden |  | 12586 | G | 5041 | East Walden | N |  | 4950 | [13 empty] | CDG | Y | 33 SMA America SHP 150-US-20 (600V) | 2021-06-15 | 2021-06-21 | 4 | 2021-06-21 | 2021-06-21 | 2021-07-13 | 15 |  |  |  |  | 19500 | [9 empty] | W
Central Hudson |  | Trinity Solar | CH-13679 | Newburgh | Newburgh | Orange | 12550 | G | 4023 | Coldenham | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000H-US (240V) | 2021-04-19 | 2021-04-21 | 2 | 2021-04-21 | [14 empty] | 2021-06-21 | 2021-06-21 |  | Y
Central Hudson |  | Solar Generation | CH-13685 | Kingston | Kerhonkson | Ulster | 12446 | G | 3082 | Kerhonkson | N |  | 17.64 | [13 empty] | NM | N | 56 Enphase Energy IQ7X-96-x-US-& (240V) [SI1] 56EnphaseIQ7X-96-2-US | 2021-04-15 | 2021-04-20 | 3 | 2021-04-20 | [14 empty] | 2021-05-28 | 2021-05-28 |  | Y
Central Hudson |  | Solar Generation | CH-13680 | Kingston | Port Ewen | Ulster | 12466 | G | 1012 | Boulevard | N |  | 3.15 | [13 empty] | NM | N | 10 Enphase Energy IQ7X-96-x-US (240V) | 2021-04-15 | 2021-04-19 | 2 | 2021-04-19 | [14 empty] | 2021-05-03 | 2021-05-03 |  | Y
Central Hudson |  | PlugPV LLC | CH-13682 | Newburgh | New Windsor | Orange | 12553 | G | 4094 | Bethlehem Rd | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2021-04-15 | 2021-04-19 | 2 | 2021-04-19 | [14 empty] | 2021-06-04 | 2021-06-04 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-13684 | Fishkill | Beacon |  | 12508 | G | 8015 | Forgebrook | N |  | 4.56 | [13 empty] | NM | N | 5 Enphase Energy IQ7-60-x-US (240V) 6 Enphase Energy IQ7-60-x-US (240V) 8 Enphase Energy IQ7-60-x-ACM-US (240V) | 2021-04-15 | 2021-04-19 | 2 | 2021-04-19 | [17 empty] | W
Central Hudson |  | Trinity Solar | CH-13683 | Newburgh | Newburgh | Orange | 12550 | G | 4011 | West Balmville | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2021-04-15 | 2021-04-19 | 2 | 2021-04-19 | [14 empty] | 2021-05-25 | 2021-05-25 |  | Y
Central Hudson |  | Solar Generation | CH-13681 | Kingston | Hurley | Ulster | 12443 | G | 2093 | Hurley Ave | N |  | 5000 | [13 empty] | CDG | Y | 40 Sungrow Power Supply SG125HV (600V) | 2021-07-27 | 2021-07-28 | 1 | 2021-07-28 | 2021-07-28 | 2021-08-18 | 15 | 2022-01-05 | 2022-02-11 | 2022-05-09 | 59 | 13665.95 | 1081230 | [7 empty] | 2022-12-20 | W
Central Hudson |  | Suncommon | CH-13686 | Kingston | Glenford | Ulster | 12433 | G | 3013 | Woodstock | N |  | 13.34 | [13 empty] | NM | N | 46 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-04-15 | 2021-04-20 | 3 | 2021-04-20 | [14 empty] | 2021-07-19 | 2021-07-19 |  | Y
Central Hudson |  | New York State Solar Farm | CH-13688 | Newburgh | Newburgh | Orange | 12550 | G | 5004 | Marlboro | N |  | 5.24 | [13 empty] | NM | N | 15 SunPower SPR-A420-G-AC (240V) | 2021-04-16 | 2021-04-20 | 2 | 2021-04-20 | [14 empty] | 2021-05-18 | 2021-05-18 |  | Y
Central Hudson |  | Trinity Solar | CH-13687 | Newburgh | Newburgh | Orange | 12550 | G | 4022 | Coldenham | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2021-04-16 | 2021-04-20 | 2 | 2021-04-20 | [14 empty] | 2021-06-16 | 2021-06-16 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-13690 | Newburgh | Newburgh | Orange | 12550 | G | 4054 | Union Ave | N |  | 3.48 | [13 empty] | NM | N | 12 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-04-22 | 2021-04-23 | 1 | 2021-04-23 | [14 empty] | 2021-09-14 | 2021-09-21 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-13689 | Newburgh | New Windsor | Orange | 12553 | G | 4046 | Union Ave | N |  | 12.76 | [13 empty] | NM | N | 28 Enphase Energy IQ7PLUS-72-x-US (240V) 16 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-04-16 | 2021-04-20 | 2 | 2021-04-20 | [14 empty] | 2021-06-23 | 2021-06-23 |  | Y
Central Hudson |  | New York State Solar Farm | CH-13691 | Newburgh | New Windsor | Orange | 12553 | G | 4097 | Bethlehem Rd | N |  | 9.45 | [13 empty] | NM | N | 30 SunPower SPR-E20-327-E-AC (240V) | 2021-04-19 | 2021-04-21 | 2 | 2021-04-21 | [14 empty] | 2021-05-18 | 2021-05-18 |  | Y
Central Hudson |  | New York State Solar Farm | CH-13692 | Catskill | Ravena | Albany | 12143 | G | 1082 | New Baltimore | N |  | 10.08 | [13 empty] | NM | N | 32 SunPower SPR-X22-360-E-AC (240V) | 2021-04-19 | 2021-04-21 | 2 | 2021-04-21 | [14 empty] | 2021-06-09 | 2021-06-09 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-13694 | Kingston | Olive Brdg |  | 12461 | G | 3024 | High Falls | Y |  | 7.6 | 7.6 | [12 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) 1SolarEdge TechnologiesSE7600H-USS3 | 2021-04-29 | 2021-05-04 | 3 | 2021-05-04 | [17 empty] | W
Central Hudson |  | Infinity Solar Systems | CH-13693 | Fishkill | Fishkill | Dutchess | 12524 | G | 8012 | Forgebrook | N |  | 4.64 | [13 empty] | NM | N | 16 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-04-26 | 2021-04-30 | 4 | 2021-04-30 | [14 empty] | 2021-06-24 | 2021-06-24 |  | Y
Central Hudson |  | KASSELMAN SOLAR | CH-13696 | Catskill | Durham | Greene | 12422 | G | 1092 | Westerlo | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2021-04-20 | 2021-04-22 | 2 | 2021-04-22 | [14 empty] | 2021-05-21 | 2021-05-21 |  | Y
Central Hudson |  | Apex Solar Power | CH-13695 | Poughkeepsie | Milan | Dutchess | 12571 | G | 7061 | Milan | N | CH-00691 | 3.8 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3800H-US (240V) | 2021-04-20 | 2021-04-22 | 2 | 2021-04-22 | [14 empty] | 2021-11-16 | 2021-11-22 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-13698 | Newburgh | Middletown | Orange | 10940 | G | 5051 | Maybrook | N |  | 11.52 | [13 empty] | NM | N | 2 Delta Electronics M6-TL-US (240V) [SI1] | 2021-04-20 | 2021-04-22 | 2 | 2021-04-22 | [8 empty] | 350 | 350 |  | 2021-07-07 | 2021-07-07 | 2021-07-16 | 2021-09-27 | 2021-10-04 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-13697 | Newburgh | New Windsor | Orange | 12553 | G | 4094 | Bethlehem Rd | N |  | 4.06 | [13 empty] | NM | N | 14 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-04-20 | 2021-04-22 | 2 | 2021-04-22 | [14 empty] | 2021-08-25 | 2021-08-25 |  | Y
Central Hudson |  | PlugPV LLC | CH-13700 | Fishkill | Wappingrs Fls |  | 12590 | G | 8043 | Myers Corners | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2021-04-21 | 2021-04-23 | 2 | 2021-04-23 | [17 empty] | W
Central Hudson |  | Kasselman Solar | CH-13701 | Kingston | Kingston | Ulster | 12401 | G | 2093 | Hurley Ave | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2021-04-21 | 2021-04-23 | 2 | 2021-04-23 | [14 empty] | 2021-05-19 | 2021-05-19 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-13703 | Newburgh | New Windsor | Orange | 12553 | G | 4043 | Union Ave | N |  | 12.18 | [13 empty] | NM | N | 42 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-04-21 | 2021-04-23 | 2 | 2021-04-23 | [14 empty] | 2021-05-17 | 2021-05-17 |  | Y
Central Hudson |  | PlugPV, LLC | CH-13699 | Newburgh | Newburgh | Orange | 12550 | G | 4023 | Coldenham | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2021-04-21 | 2021-04-22 | 1 | 2021-04-22 | [14 empty] | 2021-08-30 | 2021-09-14 |  | Y
Central Hudson |  | AEC Solar Energy Corp | CH-13702 | Kingston | Ulster Pk | Ulster | 12487 | G | 1023 | East Kingston | N |  | 9.45 | [13 empty] | NM | N | 30 Enphase Energy IQ7XS-96-x-ACM-US-y-z-& (240V) [SI1] | 2021-04-21 | 2021-04-23 | 2 | 2021-04-23 | [14 empty] | 2021-07-01 | 2021-07-01 |  | Y
Central Hudson |  | Kasselman Solar | CH-13706 | Kingston | Kingston | Ulster | 12401 | G | 111 | South Wall St | N |  | 4.06 | [13 empty] | NM | N | 14 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-04-26 | 2021-04-30 | 4 | 2021-04-30 | [14 empty] | 2021-05-26 | 2021-05-26 |  | Y
Central Hudson |  | Trinity Solar | CH-13705 | Newburgh | Newburgh | Orange | 12550 | G | 4023 | Coldenham | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2021-04-22 | 2021-04-26 | 2 | 2021-04-26 | [14 empty] | 2021-06-21 | 2021-06-21 |  | Y
Central Hudson |  | SunCommon | CH-13708 | Poughkeepsie | Millerton | Dutchess | 12546 | G | 7081 | Millerton | N |  | 13.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) 1 SolarEdge Technologies SE7600H-US (240V) | 2021-04-22 | 2021-04-26 | 2 | 2021-04-26 | [14 empty] | 2021-05-17 | 2021-05-17 |  | Y
Central Hudson |  | PlugPV LLC | CH-13710 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2021-04-23 | 2021-04-27 | 2 | 2021-04-27 | [14 empty] | 2021-06-02 | 2021-06-02 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-13715 | Newburgh | Newburgh | Orange | 12550 | G | 4023 | Coldenham | N |  | 7.68 | [13 empty] | NM | N | 1 Delta Electronics M8-TL-US (240V) [SI1] | 2021-04-23 | 2021-04-29 | 4 | 2021-04-29 | [17 empty] | W
Central Hudson |  | Sunrun Installation Services, Inc. | CH-13714 | Newburgh | Newburgh | Orange | 12550 | G | 5001 | Marlboro | Y | CH-13714 | 3.8 | 3.8 | [12 empty] | NM | N | 1 SolarEdge Technologies SE3800H-US (240V) [SI1] 1SolarEdge TechnologiesSE3800H-USM3 | 2021-05-24 | 2021-06-01 | 5 | 2021-06-01 | [14 empty] | 2021-11-19 | 2021-11-19 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-13712 | Kingston | St Remy | Ulster | 12401 | G | 3041 | Sturgeon Pool | N |  | 13.05 | [13 empty] | NM | N | 45 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-04-23 | 2021-04-29 | 4 | 2021-04-29 | [14 empty] | 2021-06-28 | 2021-06-28 |  | Y
Central Hudson |  | Trinity Solar | CH-13711 | Newburgh | Newburgh | Orange | 12550 | G | 4023 | Coldenham | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2021-04-23 | 2021-04-28 | 3 | 2021-04-28 | [14 empty] | 2021-06-21 | 2021-06-21 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-13713 | Newburgh | Campbell Hall | Orange | 10916 | G | 5051 | Maybrook | N |  | 17.28 | [13 empty] | NM | N | 1 Delta Electronics M10-TL-US (240V) [SI1] 1 Delta Electronics M8-TL-US (240V) [SI1] | 2021-04-23 | 2021-05-03 | 6 | 2021-05-03 | [8 empty] | 350 | 350 |  | 2021-06-22 | 2021-06-22 | 2021-07-16 | 2021-09-14 | 2021-09-21 |  | Y
Central Hudson |  | Solar Generation | CH-13709 | Kingston | Glenford | Ulster | 12433 | G | 3013 | Woodstock | N |  | 7.6 | [13 empty] | NM | N | 1 Generac Power Systems X7602 (240V) | 2021-04-29 | 2021-05-04 | 3 | 2021-05-04 | [14 empty] | 2021-06-21 | 2021-06-21 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-13717 | Newburgh | Newburgh | Orange | 12550 | G | 4023 | Coldenham | N |  | 6.96 | [13 empty] | NM | N | 24 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-04-26 | 2021-04-30 | 4 | 2021-04-30 | [14 empty] | 2021-10-13 | 2021-10-18 |  | Y
Central Hudson |  | SunCommon | CH-13718 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7061 | Milan | N |  | 8.12 | [13 empty] | NM | N | 28 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-04-26 | 2021-04-30 | 4 | 2021-04-30 | [14 empty] | 2021-06-08 | 2021-06-08 |  | Y
Central Hudson |  | PlugPV, LLC | CH-13719 | Newburgh | Rock Tvrn | Orange | 12575 | G | 4097 | Bethlehem Rd | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2021-04-26 | 2021-04-30 | 4 | 2021-04-30 | [14 empty] | 2021-06-21 | 2021-06-21 |  | Y
Central Hudson |  | New York State Solar Farm | CH-13724 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8052 | North Chelsea | N |  | 10.08 | [13 empty] | NM | N | 32 SunPower SPR-X22-360-E-AC (240V) | 2021-04-27 | 2021-05-03 | 4 | 2021-05-03 | [14 empty] | 2021-05-18 | 2021-05-18 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-13722 | Poughkeepsie | Staatsburg | Dutchess | 12580 | G | 7041 | Staatsburg | N |  | 5.8 | [13 empty] | NM | N | 20 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-04-27 | 2021-05-03 | 4 | 2021-05-03 | [14 empty] | 2021-06-11 | 2021-06-11 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-13720 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6096 | Manchester | N |  | 9.57 | [13 empty] | NM | N | 33 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-04-27 | 2021-05-03 | 4 | 2021-05-03 | [14 empty] | 2021-07-01 | 2021-07-01 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-13723 | Fishkill | Beacon | Dutchess | 12508 | G | 8087 | Tioronda | N |  | 6.96 | [13 empty] | NM | N | 24 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-05-04 | 2021-05-11 | 5 | 2021-05-11 | [14 empty] | 2021-07-01 | 2021-07-01 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-13721 | Poughkeepsie | Millerton | Dutchess | 12546 | G | 7081 | Millerton | N | CH-13721 | 9.86 | [13 empty] | NM | N | 34 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-04-27 | 2021-05-03 | 4 | 2021-05-03 | [14 empty] | 2021-05-27 | 2021-05-27 |  | Y
Central Hudson |  | Lighthouse Solar | CH-13725 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6052 | Todd Hill | N |  | 9.28 | [13 empty] | NM | N | 32 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-04-28 | 2021-05-04 | 4 | 2021-05-04 | [14 empty] | 2021-07-06 | 2021-07-06 |  | Y
Central Hudson |  | PlugPV, LLC. | CH-13727 | Newburgh | Rock Tvrn | Orange | 12575 | G | 4097 | Bethlehem Rd | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2021-04-28 | 2021-05-04 | 4 | 2021-05-04 | [14 empty] | 2021-06-16 | 2021-06-16 |  | Y
Central Hudson |  | OurGeneration LLC | CH-13726 | Poughkeepsie | Rhinebeck |  | 12572 | G | 7053 | Rhinebeck | N |  | 5000 | [13 empty] | CDG | Y | 40 Chint Power Systems America CPS SCH125KTL-DO/US-600 (600V) | 2021-05-18 | 2021-06-02 | 10 | 2021-06-02 | 2021-06-02 | 2021-06-21 | 13 |  |  |  |  | 19000 | [9 empty] | W
Central Hudson |  | PlugPV, LLC | CH-13729 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6068 | Inwood Ave | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2021-04-29 | 2021-05-04 | 3 | 2021-05-04 | [14 empty] | 2021-06-21 | 2021-06-21 |  | Y
Central Hudson |  | PlugPV, LLC. | CH-13728 | Newburgh | Rock Tvrn | Orange | 12575 | G | 4097 | Bethlehem Rd | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2021-05-13 | 2021-05-20 | 5 | 2021-05-20 | [14 empty] | 2021-06-18 | 2021-06-18 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-13730 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8052 | North Chelsea | N |  | 7.68 | [13 empty] | NM | N | 1 Delta Electronics M8-TL-US (240V) [SI1] | 2021-04-29 | 2021-05-04 | 3 | 2021-05-04 | [14 empty] | 2021-08-05 | 2021-08-05 |  | Y
Central Hudson |  | SunCommon | CH-13731 | Kingston | Kingston | Ulster | 12401 | G | 2093 | Hurley Ave | Y |  | 13.05 | 5 | [12 empty] | NM | N | 45 Enphase Energy IQ7PLUS-72-x-US (240V) 1TeslaPowerwall | 2021-04-30 | 2021-05-07 | 5 | 2021-05-07 | [14 empty] | 2021-06-14 | 2021-06-14 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-13736 | Newburgh | Marlboro | Ulster | 12542 | G | 5003 | Marlboro | N |  | 7.68 | [13 empty] | NM | N | 1 Delta Electronics M8-TL-US (240V) [SI1] | 2021-04-30 | 2021-05-07 | 5 | 2021-05-07 | [14 empty] | 2021-12-17 | 2021-12-21 |  | Y
Central Hudson |  | New York Power Solutions | CH-13733 | Newburgh | Marlboro | Ulster | 12542 | G | 5004 | Marlboro | N |  | 11.6 | [13 empty] | NM | N | 40 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-04-30 | 2021-05-07 | 5 | 2021-05-07 | [14 empty] | 2021-07-02 | 2021-07-02 |  | Y
Central Hudson |  | New York Power Solutions.com | CH-13735 | Newburgh | Newburgh | Orange | 12550 | G | 4022 | Coldenham | N |  | 4.93 | [13 empty] | NM | N | 17 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-04-30 | 2021-05-07 | 5 | 2021-05-07 | [14 empty] | 2021-06-21 | 2021-06-21 |  | Y
Central Hudson |  | PlugPV, LLC | CH-13732 | Newburgh | Washingtonvl | Orange | 10992 | G | 4097 | Bethlehem Rd | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2021-04-30 | 2021-05-07 | 5 | 2021-05-07 | [14 empty] | 2021-06-11 | 2021-06-11 |  | Y
Central Hudson |  | SunCommon | CH-13734 | Poughkeepsie | Pine Plns | Dutchess | 12567 | G | 7091 | Pulvers Corners | Y |  | 8.41 | 10 | [12 empty] | NM | N | 19 Enphase Energy IQ7PLUS-72-x-US (240V) 6 Enphase Energy IQ7PLUS-72-x-US (240V) 4 Enphase Energy IQ7PLUS-72-x-US (240V) 2TeslaPowerwall 2 | 2021-04-30 | 2021-05-07 | 5 | 2021-05-07 | [14 empty] | 2021-07-06 | 2021-07-06 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-13737 | Poughkeepsie | Poughkeepsie |  | 12603 | G | 6045 | Spackenkill | N |  | 13.34 | [13 empty] | NM | N | 23 Enphase Energy IQ7PLUS-72-x-ACM-US (240V) 23 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-05-07 | 2021-05-17 | 6 | 2021-05-17 | [17 empty] | W
Central Hudson |  | Empire Solar Solutions | CH-13744 | Poughkeepsie | Salt Pt | Dutchess | 12578 | G | 7011 | Hibernia | N |  | 3.19 | [13 empty] | NM | N | 11 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-05-03 | 2021-05-10 | 5 | 2021-05-10 | [14 empty] | 2021-07-29 | 2021-07-29 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-13739 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7013 | Hibernia | N |  | 13.34 | [13 empty] | NM | N | 46 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-05-03 | 2021-05-10 | 5 | 2021-05-10 | [14 empty] | 2021-07-09 | 2021-07-09 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-13745 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6046 | Spackenkill | N |  | 11.6 | [13 empty] | NM | N | 40 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-05-03 | 2021-05-10 | 5 | 2021-05-10 | [14 empty] | 2021-07-23 | 2021-07-23 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-13743 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6094 | Manchester | N |  | 6.96 | [13 empty] | NM | N | 24 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-05-03 | 2021-05-10 | 5 | 2021-05-10 | [14 empty] | 2021-07-01 | 2021-07-01 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-13740 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6097 | Manchester | N |  | 10.44 | [13 empty] | NM | N | 36 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-05-03 | 2021-05-10 | 5 | 2021-05-10 | [14 empty] | 2021-07-26 | 2021-07-26 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-13742 | Newburgh | Newburgh | Orange | 12550 | G | 4015 | West Balmville | N |  | 11.6 | [13 empty] | NM | N | 40 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-05-03 | 2021-05-10 | 5 | 2021-05-10 | [14 empty] | 2021-10-12 | 2021-10-18 |  | Y
Central Hudson |  | AEC Solar Energy Corp | CH-13741 | Catskill | Westerlo | Albany | 12193 | G | 1091 | Westerlo | N |  | 7.6 | [13 empty] | NM | N | 1 Generac Power Systems X7602 (240V) | 2021-05-10 | 2021-05-18 | 6 | 2021-05-18 | [14 empty] | 2021-06-10 | 2021-06-10 |  | Y
Central Hudson |  | New York Power Solutions | CH-13738 | Newburgh | Campbell Hall | Orange | 10916 | G | 5052 | Maybrook | N |  | 8.7 | [13 empty] | NM | N | 30 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-05-03 | 2021-05-10 | 5 | 2021-05-10 | [14 empty] | 2021-08-12 | 2021-08-12 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-13753 | Kingston | Kingston | Ulster | 12401 | G | 2017 | Lincoln Park | N |  | 11.6 | [13 empty] | NM | N | 40 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-05-04 | 2021-05-12 | 6 | 2021-05-12 | [14 empty] | 2021-07-06 | 2021-07-06 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-13752 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6096 | Manchester | N |  | 6.09 | [13 empty] | NM | N | 21 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-05-04 | 2021-05-12 | 6 | 2021-05-12 | [14 empty] | 2021-08-09 | 2021-08-09 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-13751 | Newburgh | Newburgh | Orange | 12550 | G | 4051 | Union Ave | N |  | 5.51 | [13 empty] | NM | N | 19 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-05-04 | 2021-05-11 | 5 | 2021-05-11 | [14 empty] | 2021-08-06 | 2021-08-06 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-13750 | Newburgh | New Windsor | Orange | 12553 | G | 4097 | Bethlehem Rd | N |  | 10.44 | [13 empty] | NM | N | 36 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-05-04 | 2021-05-11 | 5 | 2021-05-11 | [14 empty] | 2021-05-28 | 2021-05-28 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-13749 | Kingston | Spring Glen | Ulster | 12483 | G | 3078 | Greenfield Rd | N |  | 6.67 | [13 empty] | NM | N | 23 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-05-04 | 2021-05-11 | 5 | 2021-05-11 | [14 empty] | 2021-07-23 | 2021-07-23 |  | Y
Central Hudson |  | KASSELMAN SOLAR | CH-13755 | Catskill | Athens | Greene | 12015 | G | 2002 | North Catskill | N |  | 19 | [13 empty] | NM | N | 1 SolarEdge Technologies SE11400H-US (240V) 1 SolarEdge Technologies SE7600H-US (240V) | 2021-05-04 | 2021-05-12 | 6 | 2021-05-12 | [8 empty] | 350 | 350 |  | 2021-05-14 | 2021-05-14 | 2021-05-27 | 2021-06-03 | 2021-06-03 |  | Y
Central Hudson |  | Aries Power | CH-13746 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7054 | Rhinebeck | N |  | 15.01 | [13 empty] | NM | N | 43 Enphase Energy IQ7A-72-x-ACM-US-y-z-& (240V) [SI1] | 2021-05-14 | 2021-05-21 | 5 | 2021-05-21 | [14 empty] | 2021-07-28 | 2021-07-28 |  | Y
Central Hudson |  | Overland Contracting, Inc. | CH-13747 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8044 | Myers Corners | N |  | 14.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE14.4KUS (208V) | 2021-06-09 | 2021-06-17 | 6 | 2021-06-17 | [14 empty] | 2023-05-09 | 2023-05-11 |  | Y
Central Hudson |  | PlugPV, LLC. | CH-13748 | Newburgh | Rock Tvrn | Orange | 12575 | G | 4097 | Bethlehem Rd | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2021-05-04 | 2021-05-11 | 5 | 2021-05-11 | [14 empty] | 2021-06-10 | 2021-06-10 |  | Y
Central Hudson |  | PlugPV, LLC. | CH-13754 | Newburgh | Washingtonvl | Orange | 10992 | G | 4097 | Bethlehem Rd | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2021-05-26 | 2021-06-03 | 5 | 2021-06-03 | [14 empty] | 2021-06-18 | 2021-06-18 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-13757 | Fishkill | Hughsonvl | Dutchess | 12537 | G | 8052 | North Chelsea | N |  | 6.67 | [13 empty] | NM | N | 23 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-05-05 | 2021-05-12 | 5 | 2021-05-12 | [14 empty] | 2021-07-14 | 2021-07-14 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-13756 | Newburgh | Highland | Ulster | 12528 | G | 5081 | Highland | Y |  | 5.76 | 5 | [12 empty] | NM | N | 1 Delta Electronics E6-TL-US (240V) [SI1] 1Delta ElectronicsE6-TL-US | 2021-05-05 | 2021-05-12 | 5 | 2021-05-12 | [14 empty] | 2021-07-12 | 2021-07-12 |  | Y
Central Hudson |  | PlugPV, LLC | CH-13758 | Newburgh | New Windsor | Orange | 12553 | G | 4095 | Bethlehem Rd | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2021-05-05 | 2021-05-12 | 5 | 2021-05-12 | [14 empty] | 2021-07-26 | 2021-07-26 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-13767 | Kingston | Saugerties | Ulster | 12477 | G | 3003 | Saugerties | Y |  | 6.38 | 3.84 | [12 empty] | NM | N | 22 Enphase Energy IQ7PLUS-72-x-US (240V) 1ENPHASEENCHARGE 10 | 2021-05-26 | 2021-06-02 | 4 | 2021-06-02 | [14 empty] | 2021-09-07 | 2021-09-14 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-13763 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 7025 | Tinkertown | Y |  | 3.84 | 3.84 | [12 empty] | NM | N | 1 Delta Electronics E4-TL-US (240V) [SI1] 1Delta ElectronicsE4-TL-US | 2021-05-06 | 2021-05-13 | 5 | 2021-05-13 | [14 empty] | 2021-11-04 | 2021-11-11 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-13762 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | Y |  | 6 | 6 | [12 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) 1SolarEdge TechnologiesSE6000H-USS3 | 2021-05-06 | 2021-05-13 | 5 | 2021-05-13 | [14 empty] | 2021-07-21 | 2021-07-21 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-13761 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6043 | Spackenkill | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2021-05-06 | 2021-05-13 | 5 | 2021-05-13 | [14 empty] | 2021-09-08 | 2021-09-08 |  | Y
Central Hudson |  | PlugPV, LLC. | CH-13760 | Kingston | Port Ewen | Ulster | 12466 | G | 1012 | Boulevard | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2021-05-13 | 2021-05-20 | 5 | 2021-05-20 | [14 empty] | 2021-06-02 | 2021-06-02 |  | Y
Central Hudson |  | Solar Generation | CH-13768 | Kingston | Woodstock | Ulster | 12498 | G | 3012 | Woodstock | N |  | 6.3 | [13 empty] | NM | N | 20 Enphase Energy IQ7X-96-x-US (240V) | 2021-05-06 | 2021-05-14 | 6 | 2021-05-14 | [14 empty] | 2021-07-28 | 2021-07-28 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-13764 | Kingston | Woodstock | Ulster | 12498 | G | 3014 | Woodstock | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3800H-US (240V) 1 SolarEdge Technologies SE7600H-US (240V) | 2021-05-06 | 2021-05-13 | 5 | 2021-05-13 | [14 empty] | 2021-08-18 | 2021-08-18 |  | Y
Central Hudson |  | Homeowner | CH-13759 | Newburgh | Highland | Ulster | 12528 | G | 5024 | Ohioville | N |  | 6.576 | [13 empty] | NM | N | 12 Altenergy Power System YC600 (240V) | 2021-05-20 | 2021-05-21 | 1 | 2021-05-21 | [14 empty] | 2021-07-28 | 2021-07-28 |  | Y
Central Hudson |  | New York State Solar Farm | CH-13770 | Newburgh | Esopus | Ulster | 12429 | G | 5084 | Highland | Y |  | 11.34 | 10 | [12 empty] | NM | N | 36 SunPower SPR-E20-327-E-AC (240V) 2TESLATESLA POWERWALL | 2021-05-06 | 2021-05-14 | 6 | 2021-05-14 | [14 empty] | 2021-06-11 | 2021-06-11 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-13765 | Catskill | Catskill | Greene | 12414 | G | 2001 | North Catskill | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) [SI1] | 2021-05-21 | 2021-05-28 | 5 | 2021-05-28 | [14 empty] | 2021-12-20 | 2021-12-20 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-13769 | Kingston | Saugerties | Ulster | 12477 | G | 2015 | Lincoln Park | N |  | 7.68 | [13 empty] | NM | N | 1 Delta Electronics M8-TL-US (240V) [SI1] | 2021-05-06 | 2021-05-14 | 6 | 2021-05-14 | [14 empty] | 2021-08-26 | 2021-08-26 |  | Y
Central Hudson |  | SunCommon | CH-13775 | Poughkeepsie | Millbrook | Dutchess | 12545 | G | 7025 | Tinkertown | N |  | 7.83 | [13 empty] | NM | N | 15 Enphase Energy IQ7PLUS-72-x-US (240V) 12 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-05-19 | 2021-05-26 | 5 | 2021-05-26 | [14 empty] | 2021-06-16 | 2021-06-16 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-13771 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8095 | Fishkill Plains | N |  | 8.99 | [13 empty] | NM | N | 31 Enphase Energy IQ8PLUS-72-2-US (240V) [SI1] | 2021-05-17 | 2021-05-24 | 5 | 2021-05-24 | [14 empty] | 2022-10-12 | 2022-10-17 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-13773 | Newburgh | Cornwall | Orange | 12518 | G | 4094 | Bethlehem Rd | N |  | 6.38 | [13 empty] | NM | N | 22 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-05-07 | 2021-05-17 | 6 | 2021-05-17 | [14 empty] | 2021-07-09 | 2021-07-09 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-13772 | Newburgh | Newburgh | Orange | 12550 | G | 4051 | Union Ave | N |  | 2.9 | [13 empty] | NM | N | 10 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-05-07 | 2021-05-17 | 6 | 2021-05-17 | [14 empty] | 2021-07-21 | 2021-07-21 |  | Y
Central Hudson |  | New York State Solar Farm | CH-13774 | Newburgh | New Paltz | Ulster | 12561 | G | 5023 | Ohioville | N |  | 41.4 | [13 empty] | NM | N | 5 SMA America SB7.7-1TP-US-41 (240V) [SI1] 1 SMA America SB3.0-1SP-US-41 (240V) [SI1] | 2021-05-07 | 2021-05-18 | 7 | 2021-05-18 | [14 empty] | 2021-10-18 | 2021-10-18 |  | Y
Central Hudson |  | SunCommon | CH-13776 | Newburgh | Cornwall | Orange | 12518 | G | 4041 | Union Ave | N | CH-13776 | 7.25 | [13 empty] | NM | N | 25 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-05-18 | 2021-05-24 | 4 | 2021-05-24 | [14 empty] | 2021-07-23 | 2021-07-23 |  | Y
Central Hudson |  | New York State Solar Farm | CH-13777 | Kingston | Saugerties | Ulster | 12477 | G | 3004 | Saugerties | N |  | 7.25 | [13 empty] | NM | N | 23 SunPower SPR-X22-360-E-AC (240V) | 2021-05-10 | 2021-05-18 | 6 | 2021-05-18 | [14 empty] | 2021-05-28 | 2021-05-28 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-13778 | Kingston | Stone Ridge | Ulster | 12484 | G | 3023 | High Falls | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2021-05-21 | 2021-05-28 | 5 | 2021-05-28 | [17 empty] | W
Central Hudson |  | New York State Solar Farm | CH-13780 | Fishkill | Beacon | Dutchess | 12508 | G | 8018 | Forgebrook | N |  | 9 | [13 empty] | NM | N | 3 SolarEdge Technologies SE3000H-US (240V) | 2021-06-29 | 2021-07-12 | 8 | 2021-07-12 | [14 empty] | 2021-10-06 | 2021-10-06 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-13781 | Newburgh | Newburgh | Orange | 12550 | G | 4013 | West Balmville | N |  | 3.48 | [13 empty] | NM | N | 6 Enphase Energy IQ7PLUS-72-x-US-& (240V) [SI1] 6 Enphase Energy IQ7PLUS-72-x-US-& (240V) [SI1] | 2021-05-20 | 2021-05-27 | 5 | 2021-05-27 | [14 empty] | 2022-01-18 | 2022-01-25 |  | Y
Central Hudson |  | Solar Generation | CH-13779 | Kingston | Kingston | Ulster | 12401 | G | 2013 | Lincoln Park | N |  | 5.8 | [13 empty] | NM | N | 20 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-05-11 | 2021-05-19 | 6 | 2021-05-19 | [14 empty] | 2021-06-23 | 2021-06-23 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-13783 | Fishkill | Beacon | Dutchess | 12508 | G | 8017 | Forgebrook | N |  | 4.06 | [13 empty] | NM | N | 14 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-05-11 | 2021-05-19 | 6 | 2021-05-19 | [14 empty] | 2021-09-09 | 2021-09-16 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-13782 | Fishkill | Beacon | Dutchess | 12508 | G | 8017 | Forgebrook | N |  | 3.48 | [13 empty] | NM | N | 12 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-05-11 | 2021-05-19 | 6 | 2021-05-19 | [14 empty] | 2021-08-09 | 2021-08-09 |  | Y
Central Hudson |  | Trinity Solar | CH-13785 | Newburgh | Newburgh | Orange | 12550 | G | 4022 | Coldenham | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2021-05-12 | 2021-05-19 | 5 | 2021-05-19 | [14 empty] | 2021-09-20 | 2021-10-05 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-13784 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 11.02 | [13 empty] | NM | N | 38 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-05-12 | 2021-05-19 | 5 | 2021-05-19 | [14 empty] | 2021-06-08 | 2021-06-08 |  | Y
Central Hudson |  | Kasselman Solar | CH-13786 | Poughkeepsie | Ancramdale | Columbia | 12503 | G | 7085 | Ancram | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2021-06-03 | 2021-06-11 | 6 | 2021-06-11 | [14 empty] | 2021-07-29 | 2021-07-29 |  | Y
Central Hudson |  | New York State Solar Farm | CH-13787 | Newburgh | Wallkill | Ulster | 12589 | G | 5043 | East Walden | N |  | 9.77 | [13 empty] | NM | N | 31 SunPower SPR-X22-360-E-AC (240V) | 2021-05-13 | 2021-05-20 | 5 | 2021-05-20 | [8 empty] | 350 | 350 |  | 2021-06-08 | 2021-06-08 | 2021-07-19 | 2021-07-26 | 2021-07-26 |  | Y
Central Hudson |  | CS Energy | CH-13791 | Catskill | Catskill | Greene | 12414 | G | 2001 | North Catskill | N |  | 1700 | [13 empty] | CDG | Y | 12 Chint Power Systems America CPS SCH125KTL-DO/US-600 (600V) [SI1] 2 Chint Power Systems America CPS SCH100KTL-DO/US-600 (600V) [SI1] | 2021-05-28 | 2021-06-07 | 5 | 2021-06-07 | 2021-06-18 | 2021-06-21 | 1 | 2021-08-16 | 2021-09-15 | 2021-12-10 | 60 | 12175 | 249298.15 |  | 2022-04-21 | 2022-10-12 | 2022-10-12 |  |  |  |  | N | Y
Central Hudson |  | CS Energy | CH-13792 | Catskill | Catskill |  | 12414 | G | 2001 | North Catskill | N |  | 5000 | [13 empty] | CDG | Y | 2SungrowSG 3150U | 2021-05-28 | 2021-06-07 | 5 | 2021-06-07 | 2021-06-18 | 2021-06-28 | 6 | 2021-08-16 | 2021-09-15 | 2021-12-10 | 60 | 12175 | 249298.15 | [7 empty] | 2022-05-13 | W
Central Hudson |  | Infinity Solar Systems | CH-13790 | Poughkeepsie | Poughkeepsie |  | 12603 | G | 6044 | Spackenkill | N |  | 9.36 | [13 empty] | NM | N | 26 Enphase Energy IQ7-60-x-US (240V) 13 Enphase Energy IQ7-60-x-US (240V) | 2021-05-21 | 2021-05-27 | 4 | 2021-05-27 | [17 empty] | W
Central Hudson |  | Sunrun Installation Services, Inc. | CH-13788 | Fishkill | Garrison | Putnam | 10524 | G | 8066 | Merritt Park | N |  | 7.68 | [13 empty] | NM | N | 1 Delta Electronics M8-TL-US (240V) [SI1] | 2021-05-13 | 2021-05-20 | 5 | 2021-05-20 | [8 empty] | 350 | 350 |  | 2021-06-10 | 2021-06-10 | 2021-07-22 | 2021-09-23 | 2021-09-30 |  | Y
Central Hudson |  | Trinity Solar | CH-13789 | Newburgh | Washingtonvl | Orange | 10992 | G | 4097 | Bethlehem Rd | N |  | 13.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) 1 SolarEdge Technologies SE7600H-US (240V) | 2021-05-20 | 2021-05-20 | 0 | 2021-05-20 | [14 empty] | 2021-11-01 | 2021-11-08 |  | Y
Central Hudson |  | AEC Solar Energy Corp | CH-13798 | Kingston | Stone Ridge | Ulster | 12484 | G | 3023 | High Falls | Y |  | 9 | 9 | [12 empty] | NM | N | 1 Sol-Ark Sol-Ark-12K-P (240V) 1Sol-ARk12K-P | 2021-05-21 | 2021-05-28 | 5 | 2021-05-28 | [17 empty] | W
Central Hudson |  | Sunrun Installation Services, Inc. | CH-13796 | Kingston | Glenford | Ulster | 12433 | G | 3013 | Woodstock | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2021-05-21 | 2021-05-28 | 5 | 2021-05-28 | [14 empty] | 2021-08-18 | 2021-08-18 |  | Y
Central Hudson |  | Kasselman Solar | CH-13793 | Catskill | Cairo | Greene | 12413 | G | 2071 | Freehold | N | CH-13793 | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE11400H-US (240V) | 2021-05-21 | 2021-05-28 | 5 | 2021-05-28 | [14 empty] | 2021-06-14 | 2021-06-14 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-13797 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6002 | Reynolds Hill | N |  | 3.84 | [13 empty] | NM | N | 1 Delta Electronics M4-TL-US (240V) [SI1] | 2021-05-14 | 2021-05-21 | 5 | 2021-05-21 | [14 empty] | 2021-08-13 | 2021-08-13 |  | Y |  | 8/5/21 - No access to meter; customer contacted for appointment. 8/13 /21 - Meter Changed.
Central Hudson |  | SunPower Direct (NY) | CH-13794 | Newburgh | Newburgh | Orange | 12550 | G | 4013 | West Balmville | N |  | 4.54 | [13 empty] | NM | N | 13 Enphase Energy IQ7AS-66-x-ACM-US-y-z-& (240V) [SI1] | 2021-05-14 | 2021-05-21 | 5 | 2021-05-21 | [14 empty] | 2021-09-07 | 2021-09-14 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-13795 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6073 | East Park | N |  | 12.47 | [13 empty] | NM | N | 14 Enphase Energy IQ7PLUS-72-x-US (240V) 29 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-05-14 | 2021-05-21 | 5 | 2021-05-21 | [14 empty] | 2021-08-02 | 2021-08-02 |  | Y
Central Hudson |  | Lighthouse Solar | CH-13799 | Newburgh | Highland | Ulster | 12528 | G | 5024 | Ohioville | N |  | 20.01 | [13 empty] | NM | N | 69 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-05-17 | 2021-05-24 | 5 | 2021-05-24 | [14 empty] | 2021-07-22 | 2021-07-22 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-13803 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6011 | Sand Dock | N |  | 8.41 | [13 empty] | NM | N | 29 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-05-17 | 2021-05-24 | 5 | 2021-05-24 | [14 empty] | 2021-06-28 | 2021-06-28 |  | Y
Central Hudson |  | Solar Generation | CH-13804 | Catskill | Elka Pk | Greene | 12427 | G | 2385 | Lawrenceville | N |  | 10.44 | [13 empty] | NM | N | 36 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-05-17 | 2021-05-24 | 5 | 2021-05-24 | [8 empty] | 350 | 350 |  | 2021-06-03 | 2021-06-03 | 2021-06-10 | 2021-07-01 | 2021-07-01 |  | Y
Central Hudson |  | Kasselman Solar | CH-13800 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6043 | Spackenkill | N |  | 6.96 | [13 empty] | NM | N | 24 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-05-17 | 2021-05-24 | 5 | 2021-05-24 | [14 empty] | 2021-06-04 | 2021-06-04 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-13801 | Fishkill | Fishkill | Dutchess | 12524 | G | 8011 | Forgebrook | Y |  | 7.54 | 5 | [12 empty] | NM | N | 26 Enphase Energy IQ7PLUS-72-x-US-& (240V) [SI1] 1TeslaAC Powerwall 2.0 | 2021-05-24 | 2021-06-01 | 5 | 2021-06-01 | [8 empty] | 350 | 350 |  | 2021-06-23 | 2021-06-23 | 2021-07-22 | 2021-09-08 | 2021-09-08 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-13805 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8092 | Fishkill Plains | N | CH-11566 | 1.44 | [13 empty] | NM | N | 6 Enphase Energy IQ7-60-x-US (240V) | 2021-06-08 | 2021-06-15 | 5 | 2021-06-15 | [14 empty] | 2022-03-28 | 2022-03-29 |  | Y
Central Hudson |  | PlugPV, LLC | CH-13810 | Newburgh | Newburgh | Orange | 12550 | G | 4022 | Coldenham | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2021-05-18 | 2021-05-25 | 5 | 2021-05-25 | [14 empty] | 2021-09-10 | 2021-09-17 |  | Y
Central Hudson |  | PlugPV, LLC. | CH-13809 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6093 | Manchester | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2021-06-08 | 2021-06-15 | 5 | 2021-06-15 | [14 empty] | 2021-08-18 | 2021-08-18 |  | Y
Central Hudson |  | Kasselman Solar | CH-13808 | Catskill | Hunter | Greene | 12442 | E | 2389 | Vinegar Hill | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE11400H-US (240V) | 2021-05-25 | 2021-05-25 | 0 | 2021-05-25 | [14 empty] | 2021-09-13 | 2021-09-20 |  | Y
Central Hudson |  | Kasselman Solar | CH-13807 | Kingston | Ulster Pk | Ulster | 12487 | G | 1023 | East Kingston | N |  | 4.64 | [13 empty] | NM | N | 16 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-05-18 | 2021-05-25 | 5 | 2021-05-25 | [14 empty] | 2021-06-23 | 2021-06-23 |  | Y
Central Hudson |  | PLUGPV, LLC | CH-13811 | Newburgh | Milton | Ulster | 12547 | G | 5083 | Highland | N | CH-13811 | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE11400H-US (240V) | 2021-05-25 | 2021-05-25 | 0 | 2021-05-25 | [14 empty] | 2021-06-22 | 2021-06-22 |  | Y
Central Hudson |  | PLUGPV | CH-13806 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6095 | Manchester | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2021-05-25 | 2021-05-25 | 0 | 2021-05-25 | [14 empty] | 2021-06-03 | 2021-06-03 |  | Y
Central Hudson |  | SunCommon | CH-13812 | Kingston | Hurley | Ulster | 12443 | G | 2094 | Hurley Ave | N |  | 115.2 | [13 empty] | NM | N | 2 SolarEdge Technologies SE43.2KUS (208V) 2 SolarEdge Technologies SE14.4KUS (208V) | 2021-07-21 | 2021-07-22 | 1 | 2021-07-22 | 2021-07-22 | 2021-08-11 | 14 | [11 empty] | 2023-06-22 | 2023-06-22 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-13813 | Newburgh | Cornwall | Orange | 12518 | G | 4043 | Union Ave | N |  | 4.06 | [13 empty] | NM | N | 14 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-05-19 | 2021-05-25 | 4 | 2021-05-25 | [14 empty] | 2021-07-23 | 2021-07-23 |  | Y
Central Hudson |  | New York Power Solutions | CH-13814 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6003 | Reynolds Hill | N |  | 6.48 | [13 empty] | NM | N | 27 Enphase Energy IQ7-60-x-US (240V) | 2021-05-19 | 2021-05-25 | 4 | 2021-05-25 | [14 empty] | 2021-08-09 | 2021-08-09 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-13815 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8095 | Fishkill Plains | N |  | 19.43 | [13 empty] | NM | N | 67 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-05-19 | 2021-05-26 | 5 | 2021-05-26 | [14 empty] | 2021-08-13 | 2021-08-13 |  | Y
Central Hudson |  | BPI Brightpower | CH-13821 | Fishkill | Poughkeepsie | Dutchess | 12601 | G | 8021 | Knapps Corners | N |  | 3600 | [13 empty] | CDG | Y | 60 Chint Power Systems America CPS SCA60KTL-DO/US-480 (480V) | 2022-06-07 | 2022-06-08 | 1 | 2022-06-08 | 2022-06-08 | 2022-06-28 | 14 |  |  |  |  | 19500 | [9 empty] | W
Central Hudson |  | Sunrun Installation Services, Inc. | CH-13820 | Newburgh | Newburgh | Orange | 12550 | G | 4051 | Union Ave | N |  | 4.8 | [13 empty] | NM | N | 1 Delta Electronics M5-TL-US (240V) [SI1] | 2021-05-20 | 2021-05-27 | 5 | 2021-05-27 | [14 empty] | 2021-08-02 | 2021-08-02 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-13818 | Newburgh | Highland | Ulster | 12528 | G | 5081 | Highland | N |  | 17.98 | [13 empty] | NM | N | 62 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-05-20 | 2021-05-27 | 5 | 2021-05-27 | [14 empty] | 2021-10-13 | 2021-10-13 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-13819 | Newburgh | New Paltz | Ulster | 12561 | G | 5024 | Ohioville | N |  | 11.02 | [13 empty] | NM | N | 38 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-05-20 | 2021-05-27 | 5 | 2021-05-27 | [14 empty] | 2021-07-09 | 2021-07-09 |  | Y
Central Hudson |  | PlugPV | CH-13816 | Newburgh | Marlboro | Ulster | 12542 | G | 5002 | Marlboro | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2021-05-20 | 2021-05-26 | 4 | 2021-05-26 | [14 empty] | 2021-06-22 | 2021-06-22 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-13817 | Fishkill | Holmes | Dutchess | 12531 | G | 8071 | Shenandoah | N |  | 21.46 | [13 empty] | NM | N | 74 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-05-20 | 2021-05-27 | 5 | 2021-05-27 | [14 empty] | 2021-08-09 | 2021-08-09 |  | Y
Central Hudson |  | Solar Alchemy, Inc. | CH-13826 | Kingston | Olive Brdg | Ulster | 12461 | G | 3082 | Kerhonkson | Y |  | 7.6 | 7.6 | [12 empty] | NM | N | 1 Generac Power Systems X7602 (240V) 1GeneracPWR-Cell 7.6 kW | 2021-07-29 | 2021-08-06 | 6 | 2021-08-06 | [14 empty] | 2021-09-07 | 2021-09-14 |  | Y
Central Hudson |  | Kasselman Solar, LLC | CH-13824 | Catskill | Acra | Greene | 12405 | G | 2041 | South Cairo | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000H-US (240V) | 2021-05-28 | 2021-06-02 | 2 | 2021-06-02 | [14 empty] | 2021-07-26 | 2021-07-26 |  | Y
Central Hudson |  | Kasselman Solar | CH-13825 | Kingston | Ellenvl | Ulster | 12428 | G | 3076 | Greenfield Rd | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2021-06-01 | 2021-06-08 | 5 | 2021-06-08 | [14 empty] | 2021-07-13 | 2021-07-13 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-13822 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 5.22 | [13 empty] | NM | N | 18 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-05-21 | 2021-05-27 | 4 | 2021-05-27 | [14 empty] | 2021-08-11 | 2021-08-11 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-13823 | Newburgh | Cornwall-Hdsn | Orange | 12520 | G | 4043 | Union Ave | N |  | 7.25 | [13 empty] | NM | N | 25 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-05-21 | 2021-05-27 | 4 | 2021-05-27 | [14 empty] | 2021-07-09 | 2021-07-09 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-13827 | Newburgh | Newburgh | Orange | 12550 | G | 4012 | West Balmville | N |  | 5.8 | [13 empty] | NM | N | 20 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-05-21 | 2021-05-28 | 5 | 2021-05-28 | [14 empty] | 2021-08-09 | 2021-08-09 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-13832 | Poughkeepsie | Wappingrs Fls | Dutchess | 12590 | G | 6052 | Todd Hill | N |  | 11.52 | [13 empty] | NM | N | 2 Delta Electronics M6-TL-US (240V) [SI1] | 2021-05-24 | 2021-06-01 | 5 | 2021-06-01 | [14 empty] | 2021-12-03 | 2021-12-06 |  | Y
Central Hudson |  | New York State Solar Farm | CH-13831 | Fishkill | Fishkill | Dutchess | 12524 | G | 8094 | Fishkill Plains | N |  | 5.67 | [13 empty] | NM | N | 18 SunPower SPR-X22-360-E-AC (240V) | 2021-05-24 | 2021-06-01 | 5 | 2021-06-01 | [14 empty] | 2021-06-11 | 2021-06-11 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-13829 | Kingston | Tillson | Ulster | 12486 | G | 3022 | High Falls | N |  | 4.64 | [13 empty] | NM | N | 16 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-05-24 | 2021-06-01 | 5 | 2021-06-01 | [14 empty] | 2021-08-18 | 2021-08-18 |  | Y
Central Hudson |  | SunCommon | CH-13828 | Kingston | High Fls | Ulster | 12440 | G | 3022 | High Falls | Y |  | 6.38 | 10 | [12 empty] | NM | N | 22 Enphase Energy IQ7PLUS-72-x-US (240V) 2TeslaPowerwall | 2021-05-24 | 2021-06-01 | 5 | 2021-06-01 | [14 empty] | 2021-09-02 | 2021-09-10 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-13830 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6094 | Manchester | N |  | 2.61 | [13 empty] | NM | N | 3 Enphase Energy IQ7PLUS-72-x-US (240V) 6 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-05-24 | 2021-06-01 | 5 | 2021-06-01 | [14 empty] | 2021-08-06 | 2021-08-06 |  | Y
Central Hudson |  | Kasselman Solar | CH-13839 | Catskill | Freehold | Greene | 12431 | G | 2071 | Freehold | Y | CH-12176 | 7.6 | 7.6 | [12 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) 1Solar EdgeSE7600H | 2021-07-06 | 2021-07-14 | 6 | 2021-07-14 | [8 empty] | 350 |  |  | 2021-07-22 | 2021-07-22 | 2021-07-29 |  |  |  | N
Central Hudson |  | SunCommon | CH-13834 | Newburgh | New Paltz | Ulster | 12561 | G | 5031 | Galeville | Y | CH-01945 |  | 5 | [12 empty] | NM | N | 1TeslaPowerwall 2 | 2021-05-25 | 2021-06-02 | 5 | 2021-06-02 | [14 empty] | 2021-08-24 | 2021-08-31 |  | Y
Central Hudson |  | SunCommon | CH-13835 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7052 | Rhinebeck | N | CH-13835 | 8.12 | [13 empty] | NM | N | 28 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-05-25 | 2021-06-02 | 5 | 2021-06-02 | [14 empty] | 2021-07-02 | 2021-07-02 |  | Y
Central Hudson |  | PLUGPV, LLC | CH-13833 | Newburgh | Highland | Ulster | 12528 | G | 5083 | Highland | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2021-05-25 | 2021-06-02 | 5 | 2021-06-02 | [14 empty] | 2021-07-07 | 2021-07-07 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-13837 | Newburgh | Washingtonvl | Orange | 10992 | G | 4097 | Bethlehem Rd | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3800H-US (240V) [SI1] 1 SolarEdge Technologies SE7600H-US (240V) [SI1] | 2021-05-25 | 2021-06-03 | 6 | 2021-06-03 | [8 empty] | 350 | 350 |  | 2021-06-23 | 2021-06-23 | 2021-08-19 | 2021-09-13 | 2021-09-20 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-13836 | Kingston | Kerhonkson | Ulster | 12446 | G | 3082 | Kerhonkson | Y |  | 9.6 | 10 | [12 empty] | NM | N | 1 Delta Electronics M10-4-TL-US (240V) [SI1] 2TeslaAC Powerwall 2.0 | 2021-05-25 | 2021-06-03 | 6 | 2021-06-03 | [8 empty] | 350 | 350 |  | 2022-01-19 | 2022-01-19 | 2022-03-03 | 2022-03-04 | 2022-03-07 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-13838 | Kingston | Kingston | Ulster | 12401 | G | 112 | South Wall St | N |  | 7.68 | [13 empty] | NM | N | 1 Delta Electronics M8-TL-US (240V) [SI1] | 2021-05-25 | 2021-06-02 | 5 | 2021-06-02 | [14 empty] | 2021-09-03 | 2021-09-13 |  | Y
Central Hudson |  | PlugPV LLC | CH-13840 | Fishkill | Beacon | Dutchess | 12508 | G | 8087 | Tioronda | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2021-05-26 | 2021-06-03 | 5 | 2021-06-03 | [14 empty] | 2021-08-18 | 2021-08-18 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-13845 | Newburgh | Newburgh | Orange | 12550 | G | 4011 | West Balmville | N |  | 15.95 | [13 empty] | NM | N | 55 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-05-26 | 2021-06-04 | 6 | 2021-06-04 | [14 empty] | 2021-09-16 | 2021-09-16 |  | Y
Central Hudson |  | PlugPV, LLC. | CH-13841 | Newburgh | New Windsor | Orange | 12553 | G | 4095 | Bethlehem Rd | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE11400H-US (240V) | 2021-05-26 | 2021-06-03 | 5 | 2021-06-03 | [8 empty] | 350 | 350 |  | 2021-06-07 | 2021-06-07 | 2021-08-09 | 2021-08-19 | 2021-08-25 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-13844 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6003 | Reynolds Hill | N |  | 3.48 | [13 empty] | NM | N | 12 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-05-26 | 2021-06-04 | 6 | 2021-06-04 | [17 empty] | W
Central Hudson |  | Gottschalk Solutions | CH-13846 | Newburgh | New Windsor | Orange | 12553 | G | 4092 | Bethlehem Rd | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2021-05-26 | 2021-06-04 | 6 | 2021-06-04 | [14 empty] | 2021-06-08 | 2021-06-08 |  | Y
Central Hudson |  | Apex Solar Power, LLC | CH-13842 | Newburgh | Highland | Ulster | 12528 | G | 5083 | Highland | N |  | 7.33 | [13 empty] | NM | N | 21 Enphase Energy IQ7AS-66-x-ACM-US-y-z-& (240V) [SI1] | 2021-05-26 | 2021-06-03 | 5 | 2021-06-03 | [14 empty] | 2021-10-13 | 2021-10-13 |  | Y
Central Hudson |  | PlugPV LLC | CH-13843 | Kingston | W Camp | Ulster | 12490 | G | 3004 | Saugerties | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2021-05-26 | 2021-06-04 | 6 | 2021-06-04 | [14 empty] | 2021-08-05 | 2021-08-05 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-13847 | Fishkill | Fishkill | Dutchess | 12524 | G | 8094 | Fishkill Plains | N |  | 5.51 | [13 empty] | NM | N | 19 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-05-27 | 2021-06-04 | 5 | 2021-06-04 | [14 empty] | 2021-08-26 | 2021-09-10 |  | Y
Central Hudson |  | Mannino Electric | CH-13848 | Kingston | High Fls | Ulster | 12440 | G | 3024 | High Falls | N |  | 22.8 | [13 empty] | NM | N | 3 SolarEdge Technologies SE7600H-US (240V) [SI1] | 2021-07-13 | 2021-07-22 | 7 | 2021-07-22 | [14 empty] | 2022-02-08 | 2022-02-17 |  | Y
Central Hudson |  | SunCommon | CH-13850 | Kingston | Woodstock | Ulster | 12498 | G | 3012 | Woodstock | N | CH-13850 | 13.92 | [13 empty] | NM | N | 48 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-05-28 | 2021-06-07 | 5 | 2021-06-07 | [14 empty] | 2021-07-22 | 2021-07-22 |  | Y
Central Hudson |  | SunCommon | CH-13849 | Poughkeepsie | Tivoli | Dutchess | 12583 | G | 7062 | Milan | N |  | 10.44 | [13 empty] | NM | N | 36 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-05-28 | 2021-06-07 | 5 | 2021-06-07 | [14 empty] | 2021-07-07 | 2021-07-07 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-13851 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6044 | Spackenkill | N |  | 11.52 | [13 empty] | NM | N | 1 Delta Electronics M8-TL-US (240V) [SI1] 1 Delta Electronics M4-TL-US (240V) [SI1] | 2021-06-01 | 2021-06-08 | 5 | 2021-06-08 | [14 empty] | 2021-07-26 | 2021-07-26 |  | Y
Central Hudson |  | Kasselman Solar | CH-13856 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6096 | Manchester | N |  | 16.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE11400H-US (240V) 1 SolarEdge Technologies SE5000H-US (240V) | 2021-06-22 | 2021-07-02 | 8 | 2021-07-02 | [14 empty] | 2021-07-19 | 2021-07-19 |  | Y
Central Hudson |  | New York State Solar Farm | CH-13858 | Kingston | Kingston | Ulster | 12401 | G | 2013 | Lincoln Park | N |  | 8.19 | [13 empty] | NM | N | 26 SunPower SPR-X22-360-E-AC (240V) | 2021-06-01 | 2021-06-09 | 6 | 2021-06-09 | [14 empty] | 2021-07-01 | 2021-07-01 |  | Y
Central Hudson |  | PlugPV, LLC. | CH-13855 | Newburgh | Newburgh | Orange | 12550 | G | 4047 | Union Ave | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2021-06-01 | 2021-06-08 | 5 | 2021-06-08 | [14 empty] | 2021-07-15 | 2021-07-15 |  | Y
Central Hudson |  | Kasselman Solar | CH-13857 | Catskill | Tannersvl | Greene | 12485 | G | 2385 | Lawrenceville | Y |  | 7.6 | 7.6 | [12 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) 1SolarEdgeSE7600H | 2021-09-16 | 2021-09-29 | 9 | 2021-09-29 | [14 empty] | 2021-12-01 | 2021-12-07 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-13853 | Kingston | Kingston | Ulster | 12401 | G | 1003 | Jansen Ave | N |  | 4.64 | [13 empty] | NM | N | 16 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-06-01 | 2021-06-08 | 5 | 2021-06-08 | [14 empty] | 2021-09-03 | 2021-09-13 |  | Y
Central Hudson |  | Lighthouse Solar | CH-13854 | Newburgh | New Paltz |  | 12561 | G | 5023 | Ohioville | N |  | 10.73 | [13 empty] | NM | N | 37 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-06-01 | 2021-06-08 | 5 | 2021-06-08 | [17 empty] | W
Central Hudson |  | Lighthouse Solar | CH-13852 | Newburgh | Highland | Ulster | 12528 | G | 5022 | Ohioville | N |  | 4.35 | [13 empty] | NM | N | 15 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-06-01 | 2021-06-08 | 5 | 2021-06-08 | [14 empty] | 2021-07-12 | 2021-07-12 |  | Y
Central Hudson |  | Trinity Solar | CH-13860 | Newburgh | Newburgh | Orange | 12550 | G | 4011 | West Balmville | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2021-07-01 | 2021-07-01 | 0 | 2021-07-01 | [14 empty] | 2021-08-05 | 2021-08-05 |  | Y
Central Hudson |  | Solar Generation | CH-13859 | Kingston | Saugerties | Ulster | 12477 | G | 3003 | Saugerties | N |  | 4.06 | [13 empty] | NM | N | 14 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-06-02 | 2021-06-10 | 6 | 2021-06-10 | [14 empty] | 2021-07-23 | 2021-07-23 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-13861 | Fishkill | Beacon | Dutchess | 12508 | G | 8017 | Forgebrook | N |  | 19.72 | [13 empty] | NM | N | 68 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-06-02 | 2021-06-10 | 6 | 2021-06-10 | [8 empty] | 350 | 350 |  | 2021-06-14 | 2021-06-14 | 2021-07-22 | 2021-07-30 | 2021-07-30 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-13869 | Kingston | Lk Hill | Ulster | 12448 | G | 3012 | Woodstock | Y |  | 15.36 | 5 | [12 empty] | NM | N | 2 Delta Electronics M8-TL-US (240V) [SI1] 1TeslaAC Powerwall 2.0 | 2021-06-03 | 2021-06-14 | 7 | 2021-06-14 | [8 empty] | 350 | 350 |  | 2021-09-07 | 2021-09-07 | 2021-10-15 | 2021-11-19 | 2021-11-19 |  | Y
Central Hudson |  | New York State Solar Farm | CH-13867 | Newburgh | New Paltz | Ulster | 12561 | G | 5011 | Modena | N |  | 17.64 | [13 empty] | NM | N | 56 SunPower SPR-X22-360-E-AC (240V) | 2021-06-03 | 2021-06-11 | 6 | 2021-06-11 | [14 empty] | 2021-06-28 | 2021-06-28 |  | Y
Central Hudson |  | Trinity Solar | CH-13863 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8055 | North Chelsea | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2021-06-03 | 2021-06-10 | 5 | 2021-06-10 | [14 empty] | 2021-09-28 | 2021-10-05 |  | Y
Central Hudson |  | AEC Solar Energy Corp | CH-13865 | Catskill | Ravena | Albany | 12143 | G | 1081 | New Baltimore | N |  | 10.4 | [13 empty] | NM | N | 33 Enphase Energy IQ7XS-96-ACM-US (240V) [SI1] | 2021-06-10 | 2021-06-22 | 8 | 2021-06-22 | [14 empty] | 2021-09-17 | 2021-09-24 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-13864 | Kingston | Kingston | Ulster | 12401 | G | 2013 | Lincoln Park | N |  | 3.77 | [13 empty] | NM | N | 13 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-06-03 | 2021-06-11 | 6 | 2021-06-11 | [14 empty] | 2021-09-09 | 2021-09-15 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-13868 | Kingston | Port Ewen | Ulster | 12466 | G | 1012 | Boulevard | N |  | 9.6 | [13 empty] | NM | N | 2 Delta Electronics M5-TL-US (240V) [SI1] | 2021-06-03 | 2021-06-11 | 6 | 2021-06-11 | [14 empty] | 2021-09-14 | 2021-09-21 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-13866 | Poughkeepsie | Milan | Dutchess | 12571 | G | 7062 | Milan | N |  | 3.48 | [13 empty] | NM | N | 12 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-06-03 | 2021-06-11 | 6 | 2021-06-11 | [14 empty] | 2021-07-06 | 2021-07-06 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-13870 | Kingston | Saugerties | Ulster | 12477 | G | 3004 | Saugerties | N |  | 7.68 | [13 empty] | NM | N | 1 Delta Electronics M8-TL-US (240V) [SI1] | 2021-07-06 | 2021-07-15 | 7 | 2021-07-15 | [14 empty] | 2021-07-26 | 2021-07-26 |  | Y
Central Hudson |  | SunCommon | CH-13876 | Poughkeepsie | Tivoli | Dutchess | 12583 | G | 7062 | Milan | N |  | 15.84 | [13 empty] | NM | N | 1 SMA America SB6.0-1SP-US-41 (240V) [SI1] 1 SMA America SB6.0-1SP-US-41 (240V) [SI1] 1 SMA America SB3.8-1SP-US-41 (240V) [SI1] | 2021-06-15 | 2021-06-25 | 8 | 2021-06-25 | [14 empty] | 2021-08-05 | 2021-08-05 |  | Y
Central Hudson |  | PlugPV | CH-13871 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6003 | Reynolds Hill | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000H-US (240V) | 2021-06-04 | 2021-06-11 | 5 | 2021-06-11 | [14 empty] | 2021-11-02 | 2021-11-22 |  | Y |  | 11/4/21 - No access to meter; need appointment.
Central Hudson |  | PLUGPV, LLC | CH-13873 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6046 | Spackenkill | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2021-06-14 | 2021-06-22 | 6 | 2021-06-22 | [17 empty] | W
Central Hudson |  | New York State Solar Farm | CH-13874 | Newburgh | Wallkill | Ulster | 12589 | G | 5033 | Galeville | N |  | 14.18 | [13 empty] | NM | N | 45 SunPower SPR-E20-327-E-AC (240V) | 2021-06-02 | 2021-06-14 | 8 | 2021-06-14 | [14 empty] | 2021-07-19 | 2021-07-19 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-13878 | Newburgh | Marlboro | Ulster | 12542 | G | 5002 | Marlboro | N |  | 7.68 | [13 empty] | NM | N | 1 Delta Electronics M8-TL-US (240V) [SI1] | 2021-06-04 | 2021-06-14 | 6 | 2021-06-14 | [14 empty] | 2022-01-04 | 2022-01-04 |  | Y
Central Hudson |  | Kasselman Solar | CH-13875 | Newburgh | Wallkill | Ulster | 12589 | G | 5043 | East Walden | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000H-US (208V) | 2021-06-04 | 2021-06-14 | 6 | 2021-06-14 | [14 empty] | 2021-07-27 | 2021-07-27 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-13872 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6066 | Inwood Ave | N | CH-12436 | 3.84 | [13 empty] | NM | N | 1 Delta Electronics M4-TL-US (240V) [SI1] | 2021-08-31 | 2021-09-15 | 10 | 2021-09-15 | [14 empty] | 2021-09-24 | 2021-10-01 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-13877 | Kingston | W Hurley | Ulster | 12491 | G | 3013 | Woodstock | N |  | 3.8 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3800H-US (240V) | 2021-06-04 | 2021-06-14 | 6 | 2021-06-14 | [14 empty] | 2021-10-27 | 2021-10-27 |  | Y
Central Hudson |  | Kasselman Solar | CH-13880 | Catskill | Hannacroix | Greene | 12087 | G | 1071 | Coxsackie | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2021-06-28 | 2021-07-08 | 7 | 2021-07-08 | [14 empty] | 2021-07-22 | 2021-07-22 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-13882 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6094 | Manchester | N |  | 2.9 | [13 empty] | NM | N | 10 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-06-07 | 2021-06-15 | 6 | 2021-06-15 | [14 empty] | 2021-08-18 | 2021-08-18 |  | Y
Central Hudson |  | SunCommon | CH-13881 | Catskill | Lexington | Greene | 12452 | E | 2389 | Vinegar Hill | N | CH-11805 | 5.51 | [13 empty] | NM | N | 19 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-06-15 | 2021-06-25 | 8 | 2021-06-25 | [14 empty] | 2021-07-16 | 2021-07-16 |  | Y
Central Hudson |  | PlugPV LLC | CH-13879 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8094 | Fishkill Plains | N |  | 15.2 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) 1 SolarEdge Technologies SE7600H-US (240V) | 2021-06-07 | 2021-06-15 | 6 | 2021-06-15 | [14 empty] | 2021-09-27 | 2021-10-04 |  | Y
Central Hudson |  | New Leaf Solar LLC | CH-13889 | Poughkeepsie | Millbrook | Dutchess | 12545 | G | 7012 | Hibernia | N |  | 22.8 | [13 empty] | NM | N | 1 SolarEdge Technologies SE11400H-US (240V) 1 SolarEdge Technologies SE11400H-US (240V) | 2021-09-15 | 2021-09-29 | 10 | 2021-09-29 | [8 empty] | 350 | 350 |  | 2021-09-30 | 2021-09-30 | 2021-11-09 | 2021-11-22 | 2021-11-23 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-13888 | Kingston | Ellenvl | Ulster | 12428 | G | 3076 | Greenfield Rd | Y |  | 3.8 | 3.8 | [12 empty] | NM | N | 1 SolarEdge Technologies SE3800H-US (240V) [SI1] 1SolarEdge TechnologiesSE3800H-USM3 | 2021-07-06 | 2021-07-15 | 7 | 2021-07-15 | [14 empty] | 2021-10-27 | 2021-10-27 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-13885 | Newburgh | Wallkill | Ulster | 12589 | G | 4011 | West Balmville | N |  | 15.08 | [13 empty] | NM | N | 52 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-06-08 | 2021-06-16 | 6 | 2021-06-16 | [8 empty] | 350 | 350 |  | 2021-06-18 | 2021-06-18 | 2021-07-16 | 2021-09-01 | 2021-09-01 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-13884 | Kingston | Kingston | Ulster | 12401 | G | 1003 | Jansen Ave | N |  | 5.8 | [13 empty] | NM | N | 20 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-06-08 | 2021-06-16 | 6 | 2021-06-16 | [14 empty] | 2021-09-01 | 2021-09-09 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-13883 | Newburgh | Newburgh | Orange | 12550 | G | 4013 | West Balmville | N |  | 13.63 | [13 empty] | NM | N | 47 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-06-08 | 2021-06-16 | 6 | 2021-06-16 | [14 empty] | 2021-10-13 | 2021-10-13 |  | Y
Central Hudson |  | Solar Generation | CH-13886 | Kingston | Grahamsvl | Sullivan | 12740 | G | 3091 | Neversink | N |  | 5.99 | [13 empty] | NM | N | 19 Enphase Energy IQ7X-96-x-US (240V) | 2021-06-08 | 2021-06-16 | 6 | 2021-06-16 | [14 empty] | 2021-08-30 | 2021-10-08 |  | Y |  | 9/7/21 - Unable to access meter. 10/7/21 - Meter installed.
Central Hudson |  | PlugPV, LLC | CH-13887 | Newburgh | Salisbury Mls | Orange | 12577 | G | 4095 | Bethlehem Rd | N |  | 20 | [13 empty] | NM | N | 2 SolarEdge Technologies SE10000H-US (240V) | 2021-06-08 | 2021-06-16 | 6 | 2021-06-16 | [14 empty] | 2021-08-30 | 2021-09-10 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-13891 | Newburgh | Newburgh | Orange | 12550 | G | 4055 | Union Ave | N |  | 9.8 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) 1 SolarEdge Technologies SE3800H-US (240V) [SI1] | 2021-06-09 | 2021-06-17 | 6 | 2021-06-17 | [14 empty] | 2021-10-05 | 2021-10-18 |  | Y
Central Hudson |  | PlugPV, LLC | CH-13895 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6097 | Manchester | N |  | 15.2 | [13 empty] | NM | N | 2 SolarEdge Technologies SE7600H-US (240V) | 2021-06-09 | 2021-06-17 | 6 | 2021-06-17 | [14 empty] | 2021-08-25 | 2021-08-25 |  | Y
Central Hudson |  | New York State Solar Farm | CH-13892 | Fishkill | Beacon | Dutchess | 12508 | G | 8087 | Tioronda | N |  | 5.67 | [13 empty] | NM | N | 18 SunPower SPR-X22-360-E-AC (240V) | 2021-06-09 | 2021-06-17 | 6 | 2021-06-17 | [14 empty] | 2021-07-23 | 2021-07-23 |  | Y
Central Hudson |  | SunCommon | CH-13893 | Newburgh | Marlboro | Ulster | 12542 | G | 5003 | Marlboro | N | CH-13893 | 8.99 | [13 empty] | NM | N | 31 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-06-09 | 2021-06-18 | 7 | 2021-06-18 | [14 empty] | 2021-09-28 | 2021-10-05 |  | Y
Central Hudson |  | PlugPV LLC | CH-13890 | Poughkeepsie | Verbank | Dutchess | 12585 | G | 6057 | Todd Hill | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2021-06-09 | 2021-06-17 | 6 | 2021-06-17 | [14 empty] | 2021-08-17 | 2021-08-17 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-13894 | Newburgh | Marlboro | Ulster | 12542 | G | 5004 | Marlboro | Y |  | 5.76 | 5.76 | [12 empty] | NM | N | 1 Delta Electronics E6-TL-US (240V) [SI1] 1Delta ElectronicsE6-TL-US | 2021-07-06 | 2021-07-15 | 7 | 2021-07-15 | [14 empty] | 2021-11-19 | 2021-11-19 |  | Y
Central Hudson |  | Solar Generation | CH-13897 | Kingston | Saugerties | Ulster | 12477 | G | 3003 | Saugerties | N |  | 11.03 | [13 empty] | NM | N | 35 Enphase Energy IQ7X-96-x-US (240V) | 2021-06-10 | 2021-06-21 | 7 | 2021-06-21 | [14 empty] | 2021-07-01 | 2021-07-01 |  | Y
Central Hudson |  | PlugPV LLC | CH-13896 | Newburgh | Campbell Hall | Orange | 10916 | G | 5051 | Maybrook | Y | CH-04512 |  | 10 | [12 empty] | NM | N | 2TeslaAC Powerwall 2 | 2021-06-24 | 2021-07-07 | 8 | 2021-07-07 | [8 empty] | 350 | 350 |  | 2021-07-14 | 2021-07-14 | 2021-10-13 | 2022-01-11 | 2022-01-11 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-13898 | Catskill | Purling | Greene | 12470 | G | 2042 | South Cairo | N |  | 6.96 | [13 empty] | NM | N | 24 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-06-11 | 2021-06-21 | 6 | 2021-06-21 | [14 empty] | 2021-08-18 | 2021-08-18 |  | Y
Central Hudson |  | LSE Sculptor LLC | CH-13899 | Newburgh | New Windsor | Orange | 12553 | G | 4091 | Bethlehem Rd | N |  | 2490 | [13 empty] | CDG | Y | 15 Yaskawa Solectria Solar XGI 1500-166/166 (600V) | 2021-07-12 | 2021-07-21 | 7 | 2021-07-21 | 2021-07-21 | 2021-07-28 | 5 | 2021-08-19 | 2021-09-29 | 2021-12-28 | 60 | 12690.44 | 453453.05 | 461828.24 | 2022-05-04 | 2022-10-24 | 2022-10-24 | 2025-06-06 | 2025-06-24 | 2025-06-26 | 2025-09-25 | Y | Y
Central Hudson |  | Empire Solar Solutions | CH-13906 | Newburgh | Marlboro | Ulster | 12542 | G | 5004 | Marlboro | N | CH-13906 | 10.15 | [13 empty] | NM | N | 35 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-06-14 | 2021-06-23 | 7 | 2021-06-23 | [14 empty] | 2021-07-30 | 2021-07-30 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-13903 | Newburgh | New Windsor | Orange | 12553 | G | 4045 | Union Ave | N |  | 4.8 | [13 empty] | NM | N | 1 Delta Electronics M5-TL-US (240V) [SI1] | 2021-06-14 | 2021-06-23 | 7 | 2021-06-23 | [14 empty] | 2021-09-14 | 2021-09-21 |  | Y
Central Hudson |  | PlugPV LLC | CH-13900 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 6074 | East Park | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2021-06-14 | 2021-06-21 | 5 | 2021-06-21 | [14 empty] | 2021-07-28 | 2021-07-28 |  | Y
Central Hudson |  | Tri-State Solar Services | CH-13901 | Newburgh | Newburgh | Orange | 12550 | G | 4015 | West Balmville | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2021-06-23 | 2021-07-06 | 8 | 2021-07-06 | [14 empty] | 2021-07-28 | 2021-07-28 |  | Y
Central Hudson |  | Solar Generation | CH-13902 | Kingston | Mt Tremper | Ulster | 12457 | G | 3012 | Woodstock | N |  | 7.6 | [13 empty] | NM | N | 1 Generac Power Systems X7602 (240V) | 2021-06-14 | 2021-06-22 | 6 | 2021-06-22 | [14 empty] | 2021-08-27 | 2021-08-27 |  | Y
Central Hudson |  | Kasselman Solar | CH-13907 | Poughkeepsie | Millerton | Dutchess | 12546 | G | 7081 | Millerton | N |  | 11.4 | [13 empty] | NM | Y | 1 SolarEdge Technologies SE11400H-US (240V) | 2021-06-23 | 2021-07-06 | 8 | 2021-07-06 | [8 empty] | 350 | 350 |  | 2021-07-19 | 2021-07-19 | 2021-07-26 | 2021-08-10 | 2021-09-17 |  | W | Y
Central Hudson |  | SunCommon | CH-13905 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7053 | Rhinebeck | N |  | 8.12 | [13 empty] | NM | N | 28 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-06-14 | 2021-06-23 | 7 | 2021-06-23 | [14 empty] | 2021-07-27 | 2021-07-27 |  | Y
Central Hudson |  | Sundog | CH-13904 | Poughkeepsie | Millerton | Dutchess | 12546 | G | 7095 | Smithfield | N | CH-12929 | 4.19 | [13 empty] | NM | N | 12 Enphase Energy IQ7A-72-2-US (240V) [SI1] | 2021-06-14 | 2021-06-23 | 7 | 2021-06-23 | [14 empty] | 2022-06-07 | 2022-06-09 |  | Y
Central Hudson |  | Suncommon | CH-13910 | Kingston | Ellenvl | Ulster | 12428 | G | 3076 | Greenfield Rd | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000H-US (240V) | 2021-06-15 | 2021-06-24 | 7 | 2021-06-24 | [14 empty] | 2021-08-17 | 2021-08-23 |  | Y
Central Hudson |  | New York State Solar Farm | CH-13912 | Fishkill | Garrison | Putnam | 10524 | G | 8086 | Tioronda | N |  | 100 | [13 empty] | NM | Y | 2 SMA America STP 50-US-41 (480V) | 2021-07-30 | 2021-08-06 | 5 | 2021-08-06 | 2021-08-06 | 2021-08-25 | 13 | [11 empty] | 2021-12-29 | 2021-12-29 |  | Y | Y
Central Hudson |  | PlugPV LLC | CH-13913 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2021-06-15 | 2021-06-25 | 8 | 2021-06-25 | [14 empty] | 2021-08-04 | 2021-08-27 |  | Y |  | 8/9/21 - No access to meter; need appointment. 8/25/21 - Net meter set.
Central Hudson |  | New York State Solar Farm | CH-13911 | Kingston | Bearsvl | Ulster | 12409 | G | 3012 | Woodstock | Y | CH-12157 |  | 10 | [12 empty] | NM | N | 2TESLATESLA POWERWALL 2 | 2021-06-15 | 2021-06-25 | 8 | 2021-06-25 | [17 empty] | W
Central Hudson |  | Sunrun Installation Services, Inc. | CH-13909 | Newburgh | Wallkill | Ulster | 12589 | G | 5033 | Galeville | N |  | 13.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) [SI1] 1 SolarEdge Technologies SE7600H-US (240V) [SI1] | 2021-06-15 | 2021-06-24 | 7 | 2021-06-24 | [14 empty] | 2022-01-19 | 2022-01-26 |  | Y
Central Hudson |  | Solar Generation | CH-13908 | Kingston | Saugerties | Ulster | 12477 | G | 3003 | Saugerties | N | CH-02932 | 13.05 | [13 empty] | NM | N | 45 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-07-29 | 2021-08-06 | 6 | 2021-08-06 | [14 empty] | 2021-09-10 | 2021-09-17 |  | Y
Central Hudson |  | PlugPV LLC | CH-13914 | Catskill | Prattsvl | Greene | 12468 | E | 2389 | Vinegar Hill | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE11400H-US (240V) | 2021-06-28 | 2021-07-08 | 7 | 2021-07-08 | [14 empty] | 2021-09-27 | 2021-10-04 |  | Y
Central Hudson |  | PlugPV, LLC | CH-13915 | Newburgh | Newburgh | Orange | 12550 | G | 4023 | Coldenham | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2021-06-25 | 2021-06-25 | 0 | 2021-06-25 | [14 empty] | 2021-08-25 | 2021-09-15 |  | Y
Central Hudson |  | Solar Generation | CH-13917 | Kingston | Saugerties | Ulster | 12477 | G | 3003 | Saugerties | N |  | 10 | [13 empty] | NM | N | 2 SMA America SB5.0-1SP-US-40 (240V) [SI1] | 2021-07-28 | 2021-08-03 | 4 | 2021-08-03 | [8 empty] | 350 | 350 |  | 2021-08-05 | 2021-08-05 | 2021-11-01 | 2021-09-30 | 2021-10-08 |  | Y
Central Hudson |  | Kasselman Solar | CH-13918 | Catskill | Cairo | Greene | 12413 | G | 2043 | South Cairo | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2021-06-28 | 2021-07-07 | 6 | 2021-07-07 | [14 empty] | 2021-07-26 | 2021-07-26 |  | Y
Central Hudson |  | SunCommon | CH-13916 | Newburgh | Wallkill | Ulster | 12589 | G | 5033 | Galeville | N | CH-13916 | 10.68 | [13 empty] | NM | N | 1 SMA America SB3.0-1SP-US-41 (240V) [SI1] 1 SMA America SB7.7-1SP-US-41 (240V) [SI1] | 2021-06-16 | 2021-06-28 | 8 | 2021-06-28 | [14 empty] | 2021-08-18 | 2021-08-18 |  | Y
Central Hudson |  | Solar Generation | CH-13919 | Newburgh | Gardiner | Ulster | 12525 | G | 5011 | Modena | N |  | 5.235 | [13 empty] | NM | N | 15 Enphase Energy IQ8A-72-2-US (240V) [SI1] | 2021-06-16 | 2021-06-28 | 8 | 2021-06-28 | [14 empty] | 2023-03-20 | 2023-03-24 |  | Y
Central Hudson |  | Tesla Energy Operations, Inc. | CH-13922 | Fishkill | Beacon | Dutchess | 12508 | G | 8017 | Forgebrook | N |  | 7.6 | [13 empty] | NM | N | 1 Tesla 1538000-xx-y (240V) [SI1] | 2021-06-30 | 2021-07-12 | 7 | 2021-07-12 | [14 empty] | 2021-08-18 | 2021-08-18 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-13920 | Kingston | Kingston | Ulster | 12401 | G | 2013 | Lincoln Park | N |  | 4.06 | [13 empty] | NM | N | 14 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-06-17 | 2021-06-28 | 7 | 2021-06-28 | [14 empty] | 2021-09-02 | 2021-09-02 |  | Y
Central Hudson |  | New York State Solar Farm | CH-13921 | Newburgh | New Paltz | Ulster | 12561 | G | 5012 | Modena | N |  | 6.62 | [13 empty] | NM | N | 21 SunPower SPR-E20-327-E-AC (240V) | 2021-06-17 | 2021-06-28 | 7 | 2021-06-28 | [14 empty] | 2021-07-07 | 2021-07-07 |  | Y
Central Hudson |  | Solar Generation | CH-13924 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7052 | Rhinebeck | N |  | 15.08 | [13 empty] | NM | N | 52 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-06-17 | 2021-07-01 | 10 | 2021-07-01 | [14 empty] | 2022-03-29 | 2022-03-29 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-13926 | Kingston | Kingston | Ulster | 12401 | G | 1003 | Jansen Ave | Y |  | 3.84 | 3.84 | [12 empty] | NM | N | 1 Delta Electronics E4-TL-US (240V) [SI1] 1Delta ElectronicsE4-TL-US | 2021-06-17 | 2021-06-30 | 9 | 2021-06-30 | [14 empty] | 2022-01-18 | 2022-01-25 |  | Y
Central Hudson |  | PlugPV LLC | CH-13923 | Newburgh | Wallkill | Ulster | 12589 | G | 5043 | East Walden | N |  | 12 | [13 empty] | NM | N | 2 SolarEdge Technologies SE6000H-US (240V) | 2021-06-17 | 2021-06-30 | 9 | 2021-06-30 | [14 empty] | 2021-10-21 | 2021-10-28 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-13927 | Newburgh | New Windsor | Orange | 12553 | G | 4094 | Bethlehem Rd | Y |  | 7.68 | 7.68 | [12 empty] | NM | N | 1 Delta Electronics E8-TL-US (240V) [SI1] 1Delta ElectronicsE8-TL-US | 2021-07-01 | 2021-07-13 | 7 | 2021-07-13 | [14 empty] | 2021-08-18 | 2021-08-18 |  | Y
Central Hudson |  | YSG Solar | CH-13862 | Catskill | Greenville |  | 12083 | G | 2061 | Freehold | N |  | 1000 | [13 empty] | CDG | Y | 8 Sungrow Power Supply SG125HV (600V) | 2021-07-15 | 2021-07-26 | 7 | 2021-07-26 | 2021-07-26 | 2021-08-16 | 15 |  |  |  |  | 20500 | [9 empty] | W
Central Hudson |  | SunCommon | CH-13929 | Fishkill | Beacon | Dutchess | 12508 | G | 8087 | Tioronda | N |  | 7.25 | [13 empty] | NM | N | 25 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-07-01 | 2021-07-01 | 0 | 2021-07-01 | [14 empty] | 2021-08-11 | 2021-08-11 |  | Y
Central Hudson |  | Solexus LLC | CH-13928 | Newburgh | New Windsor | Orange | 12553 | G | 4047 | Union Ave | N |  | 1625 | [13 empty] | CDG | Y | 13 Yaskawa Solectria Solar XGI 1500-125/150-UL (600V) [SI1] | 2021-07-21 | 2021-07-26 | 3 | 2021-07-26 | 2021-07-26 | 2021-08-16 | 15 | 2021-09-30 | 2021-10-18 | 2022-01-17 | 60 | 20000 | 131181.65 |  | 2022-05-25 | 2022-11-10 | 2022-11-10 |  |  |  |  | N | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-13936 | Kingston | Saugerties | Ulster | 12477 | G | 2015 | Lincoln Park | N |  | 3.77 | [13 empty] | NM | N | 13 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-06-21 | 2021-07-02 | 9 | 2021-07-02 | [14 empty] | 2021-08-05 | 2021-08-05 |  | Y
Central Hudson |  | New York State Solar Farm | CH-13932 | Kingston | Stone Ridge | Ulster | 12484 | G | 3023 | High Falls | N | CH-00419 | 5.67 | [13 empty] | NM | N | 18 SunPower SPR-E20-327-E-AC (240V) | 2021-06-21 | 2021-07-01 | 8 | 2021-07-01 | [14 empty] | 2021-11-03 | 2021-11-03 |  | Y
Central Hudson |  | Solar Generation | CH-13931 | Kingston | Woodstock | Ulster | 12498 | G | 3013 | Woodstock | N | CH-09103 | 8.12 | [13 empty] | NM | N | 28 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-07-19 | 2021-07-27 | 6 | 2021-07-27 | [14 empty] | 2021-09-10 | 2021-09-17 |  | Y
Central Hudson |  | SunCommon | CH-13933 | Newburgh | Highland | Ulster | 12528 | G | 5024 | Ohioville | N |  | 8.99 | [13 empty] | NM | N | 31 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-07-01 | 2021-07-01 | 0 | 2021-07-01 | [14 empty] | 2021-08-05 | 2021-08-05 |  | Y
Central Hudson |  | PlugPV LLC | CH-13930 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6091 | Manchester | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2021-06-21 | 2021-07-01 | 8 | 2021-07-01 | [14 empty] | 2021-07-26 | 2021-07-26 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-13935 | Fishkill | Beacon | Dutchess | 12508 | G | 8085 | Tioronda | N |  | 6.96 | [13 empty] | NM | N | 24 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-06-21 | 2021-07-02 | 9 | 2021-07-02 | [14 empty] | 2021-09-07 | 2021-09-15 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-13938 | Newburgh | New Windsor | Orange | 12553 | G | 4054 | Union Ave | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2021-06-22 | 2021-07-02 | 8 | 2021-07-02 | [14 empty] | 2021-11-12 | 2021-11-19 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-13940 | Kingston | Kingston | Ulster | 12401 | G | 1014 | Boulevard | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2021-06-22 | 2021-07-02 | 8 | 2021-07-02 | [14 empty] | 2021-10-22 | 2021-11-12 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-13937 | Newburgh | Newburgh | Orange | 12550 | G | 4015 | West Balmville | N |  | 9.6 | [13 empty] | NM | N | 1 Delta Electronics M10-TL-US (240V) [SI1] | 2021-06-22 | 2021-07-02 | 8 | 2021-07-02 | [14 empty] | 2021-09-27 | 2021-10-04 |  | Y
Central Hudson |  | Kool Temp Heating & Cooling Inc | CH-13942 | Catskill | Ravena | Albany | 12143 | G | 1081 | New Baltimore | N |  | 7.25 | [13 empty] | NM | N | 25 Enphase Energy IQ7PLUS-72-x-ACM-US (240V) | 2021-07-19 | 2021-07-27 | 6 | 2021-07-27 | [14 empty] | 2021-08-16 | 2021-08-16 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-13941 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6046 | Spackenkill | N |  | 5.51 | [13 empty] | NM | N | 19 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-07-06 | 2021-07-15 | 7 | 2021-07-15 | [14 empty] | 2021-09-08 | 2021-09-08 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-13939 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8091 | Fishkill Plains | N |  | 5.51 | [13 empty] | NM | N | 19 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-06-22 | 2021-07-02 | 8 | 2021-07-02 | [14 empty] | 2021-09-07 | 2021-09-14 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-13943 | Newburgh | Newburgh | Orange | 12550 | G | 4022 | Coldenham | Y |  | 6 | 5 | [12 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) 1TeslaAC Powerwall 2.0 | 2021-07-06 | 2021-07-15 | 7 | 2021-07-15 | [8 empty] | 350 | 350 |  | 2021-10-18 | 2021-10-18 | 2021-12-06 | 2021-12-06 | 2021-12-13 |  | Y
Central Hudson |  | PlugPV LLC | CH-13944 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6043 | Spackenkill | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE11400H-US (240V) | 2021-06-23 | 2021-07-06 | 8 | 2021-07-06 | [14 empty] | 2021-08-04 | 2021-08-18 |  | Y
Central Hudson |  | New York State Solar Farm | CH-13945 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8094 | Fishkill Plains | N |  | 8.82 | [13 empty] | NM | N | 28 SunPower SPR-X22-360-E-AC (240V) | 2021-06-23 | 2021-07-06 | 8 | 2021-07-06 | [14 empty] | 2021-09-16 | 2021-09-23 |  | Y
Central Hudson |  | New York State Solar Farm, Inc. | CH-13950 | Newburgh | Gardiner | Ulster | 12525 | G | 5031 | Galeville | N | CH-13149 | 12.6 | [13 empty] | NM | N | 40 SunPower SPR-X22-360-E-AC (240V) | 2021-06-24 | 2021-07-07 | 8 | 2021-07-07 | [8 empty] | 350 | 350 |  | 2021-07-14 | 2021-07-14 | 2022-01-28 | 2021-10-11 | 2021-10-15 |  | Y
Central Hudson |  | PlugPV LLC | CH-13946 | Catskill | Westerlo | Albany | 12193 | G | 1091 | Westerlo | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2021-07-15 | 2021-07-26 | 7 | 2021-07-26 | [14 empty] | 2021-12-15 | 2021-12-21 |  | Y
Central Hudson |  | Lighthouse Solar | CH-13947 | Newburgh | Milton | Ulster | 12547 | G | 5003 | Marlboro | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2021-07-08 | 2021-07-19 | 7 | 2021-07-19 | [14 empty] | 2021-07-28 | 2021-07-28 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-13948 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6046 | Spackenkill | N |  | 13.92 | [13 empty] | NM | N | 48 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-06-24 | 2021-07-07 | 8 | 2021-07-07 | [14 empty] | 2021-09-01 | 2021-09-17 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-13949 | Newburgh | Maybrook | Orange | 12543 | G | 4026 | Coldenham | N |  | 5.76 | [13 empty] | NM | N | 1 Delta Electronics M6-TL-US (240V) [SI1] | 2021-06-24 | 2021-07-07 | 8 | 2021-07-07 | [14 empty] | 2021-11-04 | 2021-11-09 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-13952 | Newburgh | New Windsor | Orange | 12553 | G | 4044 | Union Ave | N |  | 5.22 | [13 empty] | NM | N | 18 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-06-25 | 2021-07-07 | 7 | 2021-07-07 | [14 empty] | 2021-09-10 | 2021-09-17 |  | Y
Central Hudson |  | PlugPV, LLC. | CH-13953 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6092 | Manchester | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE11400H-US (240V) | 2021-07-07 | 2021-07-16 | 7 | 2021-07-16 | [14 empty] | 2021-08-25 | 2021-08-25 |  | Y
Central Hudson |  | PLUGPV, LLC | CH-13951 | Newburgh | Wallkill | Ulster | 12589 | G | 5013 | Modena | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2021-06-25 | 2021-07-07 | 7 | 2021-07-07 | [14 empty] | 2021-08-18 | 2021-08-18 |  | Y
Central Hudson |  | SunPower Direct (NY) | CH-13957 | Newburgh | Wallkill | Ulster | 12589 | G | 5041 | East Walden | N |  | 12.91 | [13 empty] | NM | N | 37 Enphase Energy IQ7AS-66-ACM-US (240V) [SI1] | 2021-06-28 | 2021-07-08 | 7 | 2021-07-08 | [8 empty] | 350 | 350 |  | 2021-09-10 | 2021-09-10 | 2021-09-21 | 2021-09-24 | 2021-10-01 |  | Y
Central Hudson |  | PlugPV LLC | CH-13956 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6046 | Spackenkill | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2021-06-28 | 2021-07-07 | 6 | 2021-07-07 | [14 empty] | 2021-09-03 | 2021-09-13 |  | Y
Central Hudson |  | Novel Approaches | CH-13960 | Kingston | Grahamsvl | Sullivan | 12740 | G | 3091 | Neversink | N |  | 8.2 | [13 empty] | NM | N | 1 Fronius USA Fronius Primo 8.2-1 208-240 (240V) 1SMASB7700TL-US | 2021-07-08 | 2021-07-20 | 8 | 2021-07-20 | [14 empty] | 2021-08-16 | 2021-08-16 |  | Y
Central Hudson |  | SunCommon | CH-13959 | Kingston | Kingston | Ulster | 12401 | G | 2017 | Lincoln Park | N |  | 4.35 | [13 empty] | NM | N | 12 Enphase Energy IQ7PLUS-72-x-US (240V) 3 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-06-28 | 2021-07-08 | 7 | 2021-07-08 | [14 empty] | 2021-07-29 | 2021-07-29 |  | Y
Central Hudson |  | SunCommon | CH-13958 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8071 | Shenandoah | N |  | 11.02 | [13 empty] | NM | N | 38 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-07-08 | 2021-07-20 | 8 | 2021-07-20 | [14 empty] | 2021-08-30 | 2021-09-15 |  | Y
Central Hudson |  | PlugPV, LLC. | CH-13954 | Newburgh | Newburgh |  | 12550 | G | 5041 | East Walden | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE11400H-US (240V) | 2021-07-14 | 2021-07-23 | 7 | 2021-07-23 | [8 empty] | 350 | 350 |  | 2021-07-27 | 2021-07-27 | 2021-08-10 |  |  |  | W
Central Hudson |  | Sunrun Installation Services, Inc. | CH-13955 | Newburgh | New Windsor | Orange | 12553 | G | 4094 | Bethlehem Rd | Y |  | 7.6 | 3.8 | [12 empty] | NM | N | 2 SolarEdge Technologies SE3800H-US (240V) [SI1] 1SolarEdge TechnologiesSE3800H-USM3 | 2021-08-31 | 2021-09-15 | 10 | 2021-09-15 | [14 empty] | 2021-12-07 | 2021-12-14 |  | Y
Central Hudson |  | PlugPV, LLC | CH-13970 | Newburgh | Newburgh | Orange | 12550 | G | 4023 | Coldenham | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2021-06-29 | 2021-07-12 | 8 | 2021-07-12 | [14 empty] | 2021-08-25 | 2021-09-15 |  | Y
Central Hudson |  | IPPsolar Integration LLC | CH-13963 | Kingston | Ulster | Ulster | 12449 | G | 2091 | Hurley Ave | N |  | 5000 | [13 empty] | S-SFA | Y | 40 Sungrow Power Supply SG125HV (600V) [SI1] | 2021-07-20 | 2021-07-26 | 4 | 2021-07-26 | 2021-07-26 | 2021-08-13 | 14 | 2021-09-16 | 2021-10-11 | 2022-01-10 | 60 | 18500 | 255290.8 |  | 2022-05-04 | 2022-10-21 | 2022-10-21 |  |  |  |  | N | Y
Central Hudson |  | Trinity Solar | CH-13968 | Newburgh | New Windsor | Orange | 12553 | G | 4044 | Union Ave | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2021-06-29 | 2021-07-09 | 7 | 2021-07-09 | [14 empty] | 2021-08-26 | 2021-08-26 |  | Y
Central Hudson |  | Trinity Solar | CH-13965 | Newburgh | Newburgh | Orange | 12550 | G | 4011 | West Balmville | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2021-06-29 | 2021-07-09 | 7 | 2021-07-09 | [14 empty] | 2021-08-19 | 2021-08-25 |  | Y
Central Hudson |  | SunPower Direct (NY) | CH-13962 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8052 | North Chelsea | N |  | 9.42 | [13 empty] | NM | N | 27 Enphase Energy IQ7AS-66-ACM-US (240V) [SI1] | 2021-06-29 | 2021-07-09 | 7 | 2021-07-09 | [17 empty] | W
Central Hudson |  | SunCommon | CH-13967 | Catskill | Tannersvl | Greene | 12485 | G | 2385 | Lawrenceville | N |  | 7.54 | [13 empty] | NM | N | 26 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-07-13 | 2021-07-23 | 8 | 2021-07-23 | [14 empty] | 2021-08-27 | 2021-08-27 |  | Y
Central Hudson |  | SunCommon | CH-13966 | Catskill | Round Top | Greene | 12473 | G | 2042 | South Cairo | N |  | 21 | [13 empty] | NM | N | 3 SMA America SB7.0-1SP-US-41 (240V) [SI1] | 2021-06-29 | 2021-07-09 | 7 | 2021-07-09 | [8 empty] | 350 | 350 |  | 2021-08-02 | 2021-08-02 | 2021-08-04 | 2021-12-07 | 2021-12-14 |  | Y
Central Hudson |  | PLUGPV, LLC | CH-13969 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6068 | Inwood Ave | N |  | 13.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) 1 SolarEdge Technologies SE6000H-US (240V) | 2021-06-29 | 2021-07-09 | 7 | 2021-07-09 | [14 empty] | 2021-08-31 | 2021-09-08 |  | Y
Central Hudson |  | Kasselman Solar | CH-13961 | Kingston | Stone Ridge | Ulster | 12484 | G | 3023 | High Falls | N |  | 4.64 | [13 empty] | NM | N | 16 Enphase Energy IQ7PLUS-72-2-US (240V) [SI1] | 2021-06-29 | 2021-07-09 | 7 | 2021-07-09 | [14 empty] | 2021-08-18 | 2021-08-18 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-13964 | Fishkill | Fishkill | Dutchess | 12524 | G | 8011 | Forgebrook | N |  | 3.84 | [13 empty] | NM | N | 1 Delta Electronics M4-TL-US (240V) [SI1] | 2021-06-29 | 2021-07-12 | 8 | 2021-07-12 | [14 empty] | 2022-03-25 | 2022-03-28 |  | Y
Central Hudson |  | SunCommon | CH-13973 | Kingston | Saugerties |  | 12477 | G | 3003 | Saugerties | N |  | 7.68 | [13 empty] | NM | N | 1 SMA America SB7.7-1SP-US-41 (240V) [SI1] | 2021-06-30 | 2021-07-12 | 7 | 2021-07-12 | [17 empty] | W
Central Hudson |  | Kasselman Solar | CH-13971 | Kingston | High Fls | Ulster | 12440 | G | 3021 | High Falls | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000H-US (240V) | 2021-08-06 | 2021-08-13 | 5 | 2021-08-13 | [14 empty] | 2021-08-24 | 2021-09-10 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-13972 | Kingston | W Hurley | Ulster | 12491 | G | 3013 | Woodstock | N |  | 12.18 | [13 empty] | NM | N | 42 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-06-30 | 2021-07-12 | 7 | 2021-07-12 | [14 empty] | 2021-08-18 | 2021-08-18 |  | Y
Central Hudson |  | Kasselman Solar | CH-13974 | Kingston | Willow | Ulster | 12495 | G | 3012 | Woodstock | N |  | 8.7 | [13 empty] | NM | N | 30 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-09-30 | 2021-10-13 | 9 | 2021-10-13 | [14 empty] | 2021-10-13 | 2021-10-19 |  | Y
Central Hudson |  | PLUGPV LLC, | CH-13979 | Newburgh | Wallkill | Ulster | 12589 | G | 5012 | Modena | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2021-07-01 | 2021-07-13 | 7 | 2021-07-13 | [14 empty] | 2021-09-01 | 2021-09-01 |  | Y
Central Hudson |  | PLUGPV, LLC | CH-13981 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6055 | Todd Hill | N |  | 17.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) 1 SolarEdge Technologies SE7600H-US (240V) | 2021-07-13 | 2021-07-22 | 7 | 2021-07-22 | [14 empty] | 2021-09-09 | 2021-09-16 |  | Y
Central Hudson |  | Kasselman Solar | CH-13977 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8092 | Fishkill Plains | N |  | 4.06 | [13 empty] | NM | N | 14 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-07-01 | 2021-07-13 | 7 | 2021-07-13 | [14 empty] | 2021-08-11 | 2021-08-11 |  | Y
Central Hudson |  | Kasselman Solar | CH-13976 | Catskill | Jewett | Greene | 12444 | E | 2389 | Vinegar Hill | Y |  | 7.6 | 7.6 | [12 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) [SI1] 1SolarEdge TechnologiesSE 7600H-US | 2021-08-05 | 2021-08-13 | 6 | 2021-08-13 | [8 empty] | 350 | 350 |  | 2021-08-17 | 2021-08-17 | 2021-08-24 | 2021-10-13 | 2021-10-13 |  | Y
Central Hudson |  | Kasselman Solar | CH-13975 | Catskill | S Cairo | Greene | 12482 | G | 2042 | South Cairo | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE11400H-US (240V) | 2021-07-01 | 2021-07-13 | 7 | 2021-07-13 | [14 empty] | 2021-12-07 | 2021-12-07 |  | Y
Central Hudson |  | PlugPV, LLC. | CH-13980 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6051 | Todd Hill | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE11400H-US (240V) | 2021-07-01 | 2021-07-13 | 7 | 2021-07-13 | [14 empty] | 2021-08-25 | 2021-08-25 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-13982 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8096 | Fishkill Plains | Y |  | 15.36 | 5.76 | [12 empty] | NM | N | 1 Delta Electronics E6-TL-US (240V) [SI1] 1 Delta Electronics M10-TL-US (240V) [SI1] 1Delta ElectronicsE6-TL-US | 2021-08-25 | 2021-09-09 | 10 | 2021-09-09 | [8 empty] | 350 | 350 |  | 2022-01-05 | 2022-01-05 | 2022-02-17 | 2022-03-10 | 2022-03-14 |  | Y
Central Hudson |  | PlugPV, LLC | CH-13985 | Kingston | Grahamsvl | Sullivan | 12740 | G | 3091 | Neversink | N |  | 20 | [13 empty] | NM | N | 2 SolarEdge Technologies SE10000H-US (240V) | 2021-07-14 | 2021-07-23 | 7 | 2021-07-23 | [8 empty] | 350 | 350 |  | 2021-07-27 | 2021-07-27 | 2021-08-25 | 2021-09-09 | 2021-09-16 |  | Y
Central Hudson |  | Novel Approaches | CH-13986 | Kingston | Grahamsvl | Sullivan | 12740 | G | 3091 | Neversink | N |  | 8.2 | [13 empty] | NM | N | 1 Fronius USA Fronius Primo 8.2-1 208-240 (240V) | 2021-07-15 | 2021-07-22 | 5 | 2021-07-22 | [14 empty] | 2021-08-18 | 2021-08-23 |  | Y
Central Hudson |  | SunCommon | CH-13983 | Newburgh | New Paltz | Ulster | 12561 | G | 5011 | Modena | N | CH-01577 | 6 | [13 empty] | NM | N | 1 SMA America SB6.0-1SP-US-41 (240V) [SI1] | 2021-07-02 | 2021-07-14 | 7 | 2021-07-14 | [8 empty] | 350 | 350 |  | 2021-08-02 | 2021-08-02 | 2021-08-10 | 2021-08-27 | 2021-08-27 |  | Y
Central Hudson |  | AEC Solar Energy Corp. | CH-13984 | Kingston | Saugerties | Ulster | 12477 | G | 3003 | Saugerties | N |  | 11.97 | [13 empty] | NM | N | 38 Enphase Energy IQ7XS-96-ACM-US (240V) [SI1] | 2021-07-02 | 2021-07-14 | 7 | 2021-07-14 | [14 empty] | 2021-09-28 | 2021-10-05 |  | Y
Central Hudson |  | Autonomous Energies LLC | CH-13987 | Kingston | Lk Katrine | Ulster | 12449 | G | 1021 | East Kingston | N |  | 9.28 | [13 empty] | NM | N | 14 Enphase Energy IQ7PLUS-72-x-ACM-US (240V) 12 Enphase Energy IQ7PLUS-72-x-ACM-US (240V) 6 Enphase Energy IQ7PLUS-72-x-ACM-US (240V) | 2021-07-06 | 2021-07-15 | 7 | 2021-07-15 | [14 empty] | 2021-09-09 | 2021-09-16 |  | Y
Central Hudson |  | KASSELMAN SOLAR | CH-13992 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7061 | Milan | Y |  | 15.2 | 15.2 | [12 empty] | NM | N | 2 SolarEdge Technologies SE7600H-US (240V) 2SolaredgeSE7600H-US | 2021-08-25 | 2021-09-09 | 10 | 2021-09-09 | [14 empty] | 2021-09-20 | 2021-09-27 |  | Y
Central Hudson |  | SunPower Direct (NY) | CH-13993 | Newburgh | New Windsor | Orange | 12553 | G | 4043 | Union Ave | N |  | 4.89 | [13 empty] | NM | N | 14 Enphase Energy IQ7AS-66-ACM-US-x (240V) | 2021-07-06 | 2021-07-15 | 7 | 2021-07-15 | [14 empty] | 2021-09-24 | 2021-10-01 |  | Y
Central Hudson |  | Kasselman Solar | CH-13991 | Catskill | Catskill | Greene | 12414 | G | 2001 | North Catskill | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2021-07-15 | 2021-07-26 | 7 | 2021-07-26 | [8 empty] | 350 | 350 |  | 2021-07-28 | 2021-07-28 | 2021-07-29 | 2021-08-17 | 2021-08-17 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-13989 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8094 | Fishkill Plains | N |  | 6.09 | [13 empty] | NM | N | 21 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-07-06 | 2021-07-14 | 6 | 2021-07-14 | [14 empty] | 2021-09-27 | 2021-10-04 |  | Y
Central Hudson |  | SunCommon | CH-13996 | Kingston | Woodstock | Ulster | 12498 | G | 3013 | Woodstock | N |  | 14.79 | [13 empty] | NM | N | 36 Enphase Energy IQ7PLUS-72-x-US (240V) 15 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-07-06 | 2021-07-15 | 7 | 2021-07-15 | [8 empty] | 350 | 350 |  | 2021-07-23 | 2021-07-23 | 2021-10-22 | 2021-10-12 | 2021-10-18 |  | Y
Central Hudson |  | Kasselman Solar | CH-13990 | Catskill | Freehold | Greene | 12431 | G | 2071 | Freehold | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2021-07-06 | 2021-07-15 | 7 | 2021-07-15 | [14 empty] | 2021-09-27 | 2021-10-04 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-13988 | Newburgh | Newburgh | Orange | 12550 | G | 4045 | Union Ave | N |  | 13.44 | [13 empty] | NM | N | 1 Delta Electronics M10-TL-US (240V) [SI1] 1 Delta Electronics M4-TL-US (240V) [SI1] | 2021-07-06 | 2021-07-14 | 6 | 2021-07-14 | [14 empty] | 2021-09-14 | 2021-09-21 |  | Y
Central Hudson |  | SunCommon | CH-13994 | Fishkill | Beacon | Dutchess | 12508 | G | 8017 | Forgebrook | N |  | 4.06 | [13 empty] | NM | N | 14 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-07-06 | 2021-07-15 | 7 | 2021-07-15 | [14 empty] | 2021-07-29 | 2021-07-29 |  | Y
Central Hudson |  | Hudson Valley Wind & Solar LLC | CH-13995 | Poughkeepsie | Stanfordvl | Dutchess | 12581 | G | 7071 | Stanfordville | Y |  | 15.2 | 15.2 | [12 empty] | NM | N | 2SolarEdgeSE7600H-US2SolarEdgeStoreEdge SE7600H-US | 2021-07-29 | 2021-08-06 | 6 | 2021-08-06 | [14 empty] | 2021-12-03 | 2021-12-06 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-14001 | Newburgh | Newburgh | Orange | 12550 | G | 4045 | Union Ave | N |  | 12.18 | [13 empty] | NM | N | 42 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-07-07 | 2021-07-16 | 7 | 2021-07-16 | [14 empty] | 2021-08-13 | 2021-08-13 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-14000 | Newburgh | Wallkill | Ulster | 12589 | G | 5043 | East Walden | N |  | 10.44 | [13 empty] | NM | N | 36 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-07-07 | 2021-07-19 | 8 | 2021-07-19 | [14 empty] | 2021-09-10 | 2021-09-17 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-13999 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6095 | Manchester | N |  | 6.09 | [13 empty] | NM | N | 21 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-07-07 | 2021-07-16 | 7 | 2021-07-16 | [14 empty] | 2021-11-04 | 2021-11-09 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-13998 | Newburgh | Newburgh | Orange | 12550 | G | 4051 | Union Ave | N |  | 11.02 | [13 empty] | NM | N | 38 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-07-07 | 2021-07-16 | 7 | 2021-07-16 | [14 empty] | 2021-08-18 | 2021-09-07 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-13997 | Fishkill | Hopewell Jct |  | 12533 | G | 8094 | Fishkill Plains | N |  | 11.89 | [13 empty] | NM | N | 41 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-07-07 | 2021-07-16 | 7 | 2021-07-16 | [17 empty] | W
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14004 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8072 | Shenandoah | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) [SI1] | 2021-07-08 | 2021-07-21 | 9 | 2021-07-21 | [14 empty] | 2021-08-18 | 2021-08-18 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14003 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6003 | Reynolds Hill | Y |  | 3.8 | 3.8 | [12 empty] | NM | N | 1 SolarEdge Technologies SE3800H-US (240V) [SI1] 1SolarEdge TechnologiesSE3800H-USM3 | 2021-07-08 | 2021-07-21 | 9 | 2021-07-21 | [17 empty] | W
Central Hudson |  | Lighthouse Solar | CH-14002 | Fishkill | Cold Spg | Putnam | 10516 | G | 8063 | Merritt Park | Y |  | 15.2 | 7.6 | [12 empty] | NM | N | 2 Generac Power Systems X7602 (240V) 1Generac7.6kW X7602 (240v) | 2021-07-21 | 2021-07-28 | 5 | 2021-07-28 | [14 empty] | 2021-08-23 | 2021-08-31 |  | Y
Central Hudson |  | Surf Clean Energy | CH-14010 | Newburgh | Newburgh | Orange | 12550 | G | 4051 | Union Ave | N |  | 3.8 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3800H-US (240V) | 2021-09-21 | 2021-09-21 | 0 | 2021-09-21 | [14 empty] | 2022-04-14 | 2022-04-21 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-14006 | Fishkill | Beacon | Dutchess | 12508 | G | 8015 | Forgebrook | N |  | 12.47 | [13 empty] | NM | N | 43 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-07-21 | 2021-07-21 | 0 | 2021-07-21 | [14 empty] | 2021-09-09 | 2021-09-16 |  | Y
Central Hudson |  | New Leaf Solar LLC | CH-14008 | Catskill | Greenvl | Greene | 12083 | G | 1091 | Westerlo | N | CH-03019 | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE11400H-US (240V) | 2021-08-31 | 2021-09-15 | 10 | 2021-09-15 | [8 empty] | 350 | 350 |  | 2021-09-16 | 2021-09-16 | 2021-11-08 | 2021-12-29 | 2021-12-29 |  | Y
Central Hudson |  | New Leaf Solar LLC | CH-14012 | Catskill | Medusa | Albany | 12120 | G | 1092 | Westerlo | N |  | 3.84 | [13 empty] | NM | N | 1 SMA America SB3.8-1SP-US-41 (240V) [SI1] | 2021-07-26 | 2021-07-30 | 4 | 2021-07-30 | [14 empty] | 2021-12-29 | 2021-12-29 |  | Y
Central Hudson |  | SunCommon | CH-14009 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 6074 | East Park | N |  | 7.6 | [13 empty] | NM | N | 1 Tesla 1538000-xx-y (240V) [SI1] | 2021-07-29 | 2021-08-09 | 7 | 2021-08-09 | [14 empty] | 2021-08-30 | 2021-09-07 |  | Y
Central Hudson |  | New York Power Solutions | CH-14005 | Newburgh | Newburgh | Orange | 12550 | G | 4022 | Coldenham | N |  | 6.96 | [13 empty] | NM | N | 24 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-07-21 | 2021-07-28 | 5 | 2021-07-28 | [14 empty] | 2021-08-13 | 2021-08-30 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14007 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2021-07-09 | 2021-07-21 | 8 | 2021-07-21 | [14 empty] | 2021-09-14 | 2021-09-21 |  | Y
Central Hudson |  | PlugPV, LLC. | CH-14011 | Poughkeepsie | Lagrangeville | Dutchess | 12540 | G | 6053 | Todd Hill | N |  | 13.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) 1 SolarEdge Technologies SE6000H-US (240V) | 2021-07-21 | 2021-07-29 | 6 | 2021-07-29 | [14 empty] | 2021-08-30 | 2021-09-07 |  | Y
Central Hudson |  | PlugPV LLC | CH-14014 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 6074 | East Park | N |  | 15.2 | [13 empty] | NM | N | 2 SolarEdge Technologies SE7600H-US (240V) | 2021-07-12 | 2021-07-22 | 8 | 2021-07-22 | [14 empty] | 2022-09-29 | 2022-10-04 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-14013 | Newburgh | Campbell Hall | Orange | 10916 | G | 5052 | Maybrook | N | CH-14013 | 9.57 | [13 empty] | NM | N | 33 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-07-12 | 2021-07-22 | 8 | 2021-07-22 | [14 empty] | 2021-08-18 | 2021-08-18 |  | Y
Central Hudson |  | Kasselman Solar | CH-14015 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8072 | Shenandoah | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2021-07-13 | 2021-07-22 | 7 | 2021-07-22 | [14 empty] | 2021-08-27 | 2021-08-27 |  | Y
Central Hudson |  | Tesla Energy Operations, Inc. | CH-14017 | Fishkill | Fishkill | Dutchess | 12524 | G | 8065 | Merritt Park | N |  | 7.6 | [13 empty] | NM | N | 1 Tesla 1538000-xx-y (240V) [SI1] | 2021-08-02 | 2021-08-09 | 5 | 2021-08-09 | [14 empty] | 2021-08-18 | 2021-08-18 |  | Y
Central Hudson |  | Aries Power | CH-14016 | Newburgh | New Paltz | Ulster | 12561 | G | 5023 | Ohioville | N |  | 13.63 | [13 empty] | NM | N | 47 Enphase Energy IQ7A-72-2-US (208V) [SI1] | 2021-09-07 | 2021-09-21 | 10 | 2021-09-21 | [14 empty] | 2022-03-07 | 2022-03-11 |  | Y
Central Hudson |  | SunCommon | CH-14019 | Catskill | Lanesvl | Greene | 12450 | E | 2387 | NYSEG | N |  | 13.68 | [13 empty] | NM | N | 1 SMA America SB6.0-1SP-US-41 (240V) [SI1] 1 SMA America SB7.7-1SP-US-41 (240V) [SI1] | 2021-07-14 | 2021-07-23 | 7 | 2021-07-23 | [14 empty] | 2022-06-13 | 2022-06-17 |  | Y
Central Hudson |  | PlugPV LLC | CH-14018 | Fishkill | Beacon | Dutchess | 12508 | G | 8085 | Tioronda | N |  | 17.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) 1 SolarEdge Technologies SE7600H-US (240V) | 2021-07-14 | 2021-07-23 | 7 | 2021-07-23 | [14 empty] | 2021-10-13 | 2021-10-18 |  | Y
Central Hudson |  | Solar Generation | CH-14021 | Kingston | Shokan | Ulster | 12481 | G | 3011 | Woodstock | N |  | 18.85 | [13 empty] | NM | N | 65 Enphase Energy IQ8PLUS-72-M-US (240V) [SI1] | 2021-07-23 | 2021-07-30 | 5 | 2021-07-30 | [14 empty] | 2023-02-10 | 2023-02-13 |  | Y
Central Hudson |  | SunCommon | CH-14020 | Poughkeepsie | Pine Plns | Dutchess | 12567 | G | 7095 | Smithfield | N |  | 24.77 | [13 empty] | NM | N | 13 Enphase Energy IQ7PLUS-72-2-US (240V) [SI1] 3 SMA America SB7.0-1SP-US-41 (240V) [SI1] | 2021-07-14 | 2021-07-23 | 7 | 2021-07-23 | [8 empty] | 350 | 350 |  | 2021-08-02 | 2021-08-02 | 2022-01-28 | 2022-03-03 | 2022-03-04 |  | Y
Central Hudson |  | Lodestar Energy LLC | CH-14023 | Catskill | Coxsackie |  | 12051 | G | 1076 | Coxsackie | N |  | 5000 | [13 empty] | RC | Y | 20 Sungrow Power Supply SG250HX-US (800V) [SI1] | 2021-08-05 | 2021-08-09 | 2 | 2021-08-09 | 2021-08-09 | 2021-08-26 | 13 |  |  |  |  | 20500 | [9 empty] | W
Central Hudson |  | Kasselman Solar | CH-14022 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6046 | Spackenkill | N | CH-14022 | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000H-US (208V) | 2021-07-15 | 2021-07-26 | 7 | 2021-07-26 | [14 empty] | 2021-08-11 | 2021-08-11 |  | Y
Central Hudson |  | PlugPV LLC | CH-14026 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8095 | Fishkill Plains | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2021-07-16 | 2021-07-26 | 6 | 2021-07-26 | [14 empty] | 2021-09-08 | 2021-09-15 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14027 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6046 | Spackenkill | Y |  | 6 | 6 | [12 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) 1SolarEdge TechnologiesSE6000H-USS3 | 2021-07-16 | 2021-07-26 | 6 | 2021-07-26 | [14 empty] | 2021-12-01 | 2021-12-07 |  | Y
Central Hudson |  | Novel approaches Solar applications | CH-14024 | Kingston | Grahamsvl | Sullivan | 12740 | G | 3091 | Neversink | N |  | 12.5 | [13 empty] | NM | N | 1Fronius12.5-1 | 2021-07-26 | 2021-08-03 | 6 | 2021-08-03 | [17 empty] | W
Central Hudson |  | Empire Solar Solutions | CH-14025 | Newburgh | Newburgh | Orange | 12550 | G | 4051 | Union Ave | N |  | 8.12 | [13 empty] | NM | N | 28 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-07-16 | 2021-07-26 | 6 | 2021-07-26 | [14 empty] | 2021-10-12 | 2021-10-18 |  | Y
Central Hudson |  | Kasselman Solar, LLC | CH-14032 | Poughkeepsie | Staatsburg | Dutchess | 12580 | G | 7042 | Staatsburg | N | CH-01575 | 18.846 | [13 empty] | NM | N | 54 Enphase Energy IQ7A-72-2-US (240V) [SI1] | 2021-12-30 | 2022-01-06 | 4 | 2022-01-06 | [14 empty] | 2022-01-11 | 2022-01-11 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14030 | Newburgh | Campbell Hall | Orange | 10916 | G | 5051 | Maybrook | N | CH-04681 | 6.96 | [13 empty] | NM | N | 24 Enphase Energy IQ7PLUS-72-2-US (240V) [SI1] | 2021-07-19 | 2021-07-27 | 6 | 2021-07-27 | [14 empty] | 2022-02-16 | 2022-02-22 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14029 | Fishkill | Stormvl | Dutchess | 12582 | G | 8071 | Shenandoah | Y |  | 10.56 | 10.56 | [12 empty] | NM | N | 1 Delta Electronics E6-TL-US (240V) [SI1] 1 Delta Electronics M5-TL-US (240V) [SI1] 1Delta ElectronicsE6-TL-US | 2021-08-02 | 2021-08-10 | 6 | 2021-08-10 | [17 empty] | W
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14028 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8093 | Fishkill Plains | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2021-07-19 | 2021-07-27 | 6 | 2021-07-27 | [14 empty] | 2021-09-23 | 2021-09-30 |  | Y
Central Hudson |  | PlugPV, LLC | CH-14031 | Catskill | Catskill | Greene | 12414 | G | 2001 | North Catskill | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2021-07-19 | 2021-07-27 | 6 | 2021-07-27 | [14 empty] | 2021-10-04 | 2021-10-08 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-14036 | Fishkill | Beacon | Dutchess | 12508 | G | 8017 | Forgebrook | N |  | 4.06 | [13 empty] | NM | N | 14 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-07-20 | 2021-07-28 | 6 | 2021-07-28 | [14 empty] | 2021-09-08 | 2021-09-08 |  | Y
Central Hudson |  | Trinity Solar Systems | CH-14035 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000H-US (240V) | 2021-07-20 | 2021-07-28 | 6 | 2021-07-28 | [14 empty] | 2021-09-13 | 2021-09-20 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14034 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8072 | Shenandoah | N |  | 11.52 | [13 empty] | NM | N | 2 Delta Electronics M6-TL-US (240V) [SI1] | 2021-07-20 | 2021-07-28 | 6 | 2021-07-28 | [14 empty] | 2021-11-12 | 2021-11-18 |  | Y
Central Hudson |  | PlugPV LLC | CH-14033 | Newburgh | Wallkill | Ulster | 12589 | G | 5041 | East Walden | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2021-07-20 | 2021-07-27 | 5 | 2021-07-27 | [14 empty] | 2021-08-27 | 2021-09-10 |  | Y
Central Hudson |  | New York State Solar Farm | CH-14037 | Newburgh | Newburgh |  | 12550 | G | 5004 | Marlboro | N |  | 4.73 | [13 empty] | NM | N | 15 SunPower SPR-E20-327-E-AC (240V) | 2021-07-20 | 2021-07-27 | 5 | 2021-07-27 | [17 empty] | W
Central Hudson |  | Kasselman Solar | CH-14038 | Fishkill | Garrison | Putnam | 10524 | G | 8086 | Tioronda | N |  | 13.8 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) 1 SolarEdge Technologies SE3800H-US (240V) | 2021-09-15 | 2021-09-29 | 10 | 2021-09-29 | [8 empty] | 350 | 350 |  | 2021-10-18 | 2021-10-18 | 2021-12-06 | 2021-12-06 | 2021-12-10 |  | Y
Central Hudson |  | Trinity Solar | CH-14040 | Newburgh | Newburgh | Orange | 12550 | G | 5004 | Marlboro | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2021-07-21 | 2021-07-29 | 6 | 2021-07-29 | [14 empty] | 2021-10-19 | 2021-10-25 |  | Y
Central Hudson |  | SunCommon | CH-14039 | Catskill | Haines Fls | Greene | 12436 | G | 2385 | Lawrenceville | Y |  | 11.4 | 10 | [12 empty] | NM | N | 1 Tesla 1538000-xx-y (240V) [SI1] 1 Tesla 1534000-xx-y (240V) [SI1] 2TeslaPowerwall | 2021-08-13 | 2021-08-17 | 2 | 2021-08-17 | [14 empty] | 2021-10-13 | 2021-10-13 |  | Y
Central Hudson |  | Lighthouse Solar | CH-14044 | Kingston | Kerhonkson | Ulster | 12446 | G | 3082 | Kerhonkson | N |  | 15.71 | [13 empty] | NM | N | 45 Enphase Energy IQ7A-72-2-US (240V) [SI1] | 2021-08-04 | 2021-08-16 | 8 | 2021-08-16 | [8 empty] | 350 | 350 |  | 2021-08-18 | 2021-08-18 | 2021-08-26 | 2021-10-26 | 2021-11-01 |  | Y
Central Hudson |  | Solar Generation | CH-14043 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6051 | Todd Hill | N |  | 7.25 | [13 empty] | NM | N | 25 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-07-22 | 2021-07-29 | 5 | 2021-07-29 | [14 empty] | 2021-09-08 | 2021-09-15 |  | Y
Central Hudson |  | PlugPV LLC | CH-14042 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 7011 | Hibernia | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2021-07-22 | 2021-07-29 | 5 | 2021-07-29 | [14 empty] | 2021-09-10 | 2021-09-28 |  | Y
Central Hudson |  | New York State Solar Farm | CH-14045 | Newburgh | Gardiner | Ulster | 12525 | G | 5011 | Modena | N |  | 12.29 | [13 empty] | NM | N | 39 SunPower SPR-X22-360-E-AC (240V) | 2021-07-22 | 2021-07-29 | 5 | 2021-07-29 | [14 empty] | 2021-09-29 | 2021-09-29 |  | Y
Central Hudson |  | Hudson River Renewables LLC | CH-14048 | Fishkill | Beacon | Dutchess | 12508 | G | 8085 | Tioronda | Y |  | 9.6 | 9.6 | [12 empty] | NM | N | 1 Sol-Ark Sol-Ark-12K-P (240V) [SI1] 1Sol-ArkSol-Ark 12K-P (240V) | 2021-08-10 | 2021-08-16 | 4 | 2021-08-16 | [14 empty] | 2021-12-21 | 2021-12-22 |  | Y
Central Hudson |  | New York State Solar Farm | CH-14049 | Poughkeepsie | Staatsburg | Dutchess | 12580 | G | 7041 | Staatsburg | N |  | 3.78 | [13 empty] | NM | N | 12 Enphase Energy IQ7XS-96-E-ACM-US (240V) [SI1] | 2021-07-23 | 2021-07-30 | 5 | 2021-07-30 | [14 empty] | 2021-10-11 | 2021-10-15 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14046 | Newburgh | Newburgh | Orange | 12550 | G | 4044 | Union Ave | N |  | 7.68 | [13 empty] | NM | N | 1 Delta Electronics M8-TL-US (240V) [SI1] | 2021-07-23 | 2021-07-30 | 5 | 2021-07-30 | [14 empty] | 2022-07-15 | 2022-07-18 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-14047 | Newburgh | Newburgh | Orange | 12550 | G | 4013 | West Balmville | N |  | 18.56 | [13 empty] | NM | N | 64 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-07-23 | 2021-07-30 | 5 | 2021-07-30 | [14 empty] | 2021-11-02 | 2021-11-08 |  | Y
Central Hudson |  | Kasselman Solar | CH-14052 | Kingston | Kingston | Ulster | 12401 | G | 1014 | Boulevard | N |  | 6.67 | [13 empty] | NM | N | 23 Enphase Energy IQ7A-72-2-US (240V) [SI1] | 2021-08-26 | 2021-08-26 | 0 | 2021-08-26 | [14 empty] | 2021-10-13 | 2021-10-18 |  | Y
Central Hudson |  | Kasselman Solar | CH-14053 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6042 | Spackenkill | N |  | 10.47 | [13 empty] | NM | N | 30 Enphase Energy IQ7A-72-E-ACM-US (240V) [SI1] | 2021-08-12 | 2021-08-17 | 3 | 2021-08-17 | [14 empty] | 2021-11-26 | 2021-12-06 |  | Y
Central Hudson |  | SunCommon | CH-14056 | Newburgh | Gardiner | Ulster | 12525 | G | 5034 | Galeville | Y | CH-01971 | 12.18 | 5 | [12 empty] | NM | N | 42 Enphase Energy IQ7PLUS-72-x-US (240V) 1TeslaPowerwall | 2021-07-26 | 2021-08-03 | 6 | 2021-08-03 | [8 empty] | 350 | 350 |  | 2021-08-16 | 2021-08-16 | 2021-09-23 | 2021-09-28 | 2021-10-05 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-14057 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 5.22 | [13 empty] | NM | N | 18 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-07-26 | 2021-08-02 | 5 | 2021-08-02 | [14 empty] | 2021-10-06 | 2021-10-06 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-14058 | Newburgh | Washingtonvl | Orange | 10992 | G | 4097 | Bethlehem Rd | N |  | 4.64 | [13 empty] | NM | N | 16 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-07-26 | 2021-08-02 | 5 | 2021-08-02 | [14 empty] | 2021-09-24 | 2021-10-01 |  | Y
Central Hudson |  | Solar Generation | CH-14060 | Catskill | Palenvl | Greene | 12463 | G | 2001 | North Catskill | N |  | 6.96 | [13 empty] | NM | N | 24 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-07-26 | 2021-08-03 | 6 | 2021-08-03 | [14 empty] | 2021-10-13 | 2021-10-18 |  | Y
Central Hudson |  | Solar Generation | CH-14050 | Kingston | Saugerties | Ulster | 12477 | G | 2015 | Lincoln Park | N |  | 9.28 | [13 empty] | NM | N | 32 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-07-26 | 2021-07-30 | 4 | 2021-07-30 | [14 empty] | 2021-09-17 | 2021-09-30 |  | Y
Central Hudson |  | PlugPV, LLC | CH-14054 | Kingston | Grahamsvl | Sullivan | 12740 | G | 3091 | Neversink | N |  | 3 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3000H-US (240V) | 2021-08-02 | 2021-08-10 | 6 | 2021-08-10 | [14 empty] | 2021-09-28 | 2021-10-05 |  | Y
Central Hudson |  | New York Power Solutions | CH-14051 | Fishkill | Beacon | Dutchess | 12508 | G | 8017 | Forgebrook | N |  | 7.83 | [13 empty] | NM | N | 27 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-08-19 | 2021-09-02 | 10 | 2021-09-02 | [14 empty] | 2021-12-14 | 2021-12-21 |  | Y
Central Hudson |  | Solar Generation | CH-14059 | Kingston | Shady | Ulster | 12409 | G | 3012 | Woodstock | N |  | 10.44 | [13 empty] | NM | N | 36 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-07-26 | 2021-08-03 | 6 | 2021-08-03 | [8 empty] | 350 | 350 |  | 2021-08-05 | 2021-08-05 | 2021-10-15 | 2022-07-14 | 2022-07-27 |  | Y
Central Hudson |  | PlugPV LLC | CH-14055 | Catskill | Catskill | Greene | 12414 | G | 2005 | North Catskill | Y | CH-11028 |  | 5 | [12 empty] | NM | N | 1TeslaPowerwall | 2021-10-21 | 2021-11-04 | 10 | 2021-11-04 | [14 empty] | 2022-06-23 | 2022-06-29 |  | Y
Central Hudson |  | Sunrun Installation Service, Inc. | CH-14063 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6095 | Manchester | N |  | 9.8 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) [SI1] 1 SolarEdge Technologies SE3800H-US (240V) | 2021-07-27 | 2021-08-03 | 5 | 2021-08-03 | [14 empty] | 2021-10-08 | 2021-10-15 |  | Y
Central Hudson |  | PlugPV LLC | CH-14061 | Newburgh | Milton | Ulster | 12547 | G | 5003 | Marlboro | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2021-07-27 | 2021-08-03 | 5 | 2021-08-03 | [14 empty] | 2021-09-20 | 2021-09-27 |  | Y
Central Hudson |  | Gottschalk Solutions | CH-14062 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6092 | Manchester | N |  | 13.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) 1 SolarEdge Technologies SE6000H-US (240V) | 2021-07-27 | 2021-08-03 | 5 | 2021-08-03 | [14 empty] | 2021-09-14 | 2021-09-21 |  | Y
Central Hudson |  | SunCommon | CH-14065 | Newburgh | New Paltz | Ulster | 12561 | G | 5031 | Galeville | Y |  | 12.76 | 10 | [12 empty] | NM | N | 44 Enphase Energy IQ7PLUS-72-x-US (240V) 2TeslaPowerwall | 2021-09-17 | 2021-10-01 | 10 | 2021-10-01 | [14 empty] | 2021-11-15 | 2021-11-22 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14064 | Poughkeepsie | Lagrangevl | Dutchess | 12540 | G | 6053 | Todd Hill | N |  | 9.8 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3800H-US (240V) 1 SolarEdge Technologies SE6000H-US (240V) | 2021-07-28 | 2021-08-06 | 7 | 2021-08-06 | [14 empty] | 2021-09-24 | 2021-10-01 |  | Y
Central Hudson |  | NY Solar 1001 LLC | CH-14069 | Newburgh | Walden | Orange | 12586 | G | 5041 | East Walden | N |  | 3625 | [13 empty] | CDG | Y | 29 Chint Power Systems America CPS SCH125KTL-DO/US-600 (600V) | 2021-10-05 | 2021-10-19 | 10 | 2021-10-19 | 2021-10-19 | 2021-10-26 | 5 | 2021-11-16 | 2022-01-18 | 2022-04-13 | 60 | 15351.7 | 169423.75 | 692.64 | 2022-08-12 | [5 empty] | 2023-04-17 | W | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14067 | Kingston | Ellenvl |  | 12428 | G | 3076 | Greenfield Rd | N |  | 3.8 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3800H-US (240V) | 2021-07-29 | 2021-08-04 | 4 | 2021-08-04 | [17 empty] | W
Central Hudson |  | Tesla Energy Operations | CH-14068 | Kingston | Saugerties | Ulster | 12477 | G | 3003 | Saugerties | Y | CH-11118 | 3.8 | [13 empty] | NM | N | 1 Tesla 1534000-xx-y (240V) [SI1] | 2021-10-06 | 2021-10-19 | 9 | 2021-10-19 | [14 empty] | 2021-11-17 | 2021-11-17 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14066 | Fishkill | Stormvl | Dutchess | 12582 | G | 8071 | Shenandoah | N |  | 9.6 | [13 empty] | NM | N | 1 Delta Electronics M10-TL-US (240V) [SI1] | 2021-07-29 | 2021-08-06 | 6 | 2021-08-06 | [14 empty] | 2021-11-05 | 2021-11-09 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-14070 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 4.35 | [13 empty] | NM | N | 15 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-07-29 | 2021-08-09 | 7 | 2021-08-09 | [14 empty] | 2021-09-14 | 2021-09-21 |  | Y
Central Hudson |  | Tesla Energy Operations, Inc. | CH-14071 | Kingston | Stone Ridge | Ulster | 12484 | G | 3023 | High Falls | Y | CH-10100 | 3.8 | 5 | [12 empty] | NM | N | 1 Tesla 1534000-xx-y (240V) [SI1] 1TeslaAC powerwall 2.0 | 2021-10-01 | 2021-10-13 | 8 | 2021-10-13 | [14 empty] | 2021-12-06 | 2021-12-13 |  | Y
Central Hudson |  | Lighthouse Solar | CH-14075 | Newburgh | Wallkill | Ulster | 12589 | G | 5033 | Galeville | N |  | 21.46 | [13 empty] | NM | N | 74 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-08-02 | 2021-08-10 | 6 | 2021-08-10 | [14 empty] | 2021-10-04 | 2021-10-08 |  | Y
Central Hudson |  | SunCommon | CH-14073 | Fishkill | Beacon | Dutchess | 12508 | G | 8087 | Tioronda | N |  | 4.06 | [13 empty] | NM | N | 14 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-08-02 | 2021-08-10 | 6 | 2021-08-10 | [14 empty] | 2021-11-12 | 2021-11-19 |  | Y
Central Hudson |  | SunCommon | CH-14072 | Kingston | Tillson | Ulster | 12486 | G | 3042 | Sturgeon Pool | N |  | 9.28 | [13 empty] | NM | N | 32 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-08-02 | 2021-08-10 | 6 | 2021-08-10 | [8 empty] | 350 | 350 |  | 2021-08-23 | 2021-08-23 | 2021-10-15 | 2021-10-11 | 2021-10-15 |  | Y
Central Hudson |  | PlugPV, LLC. | CH-14074 | Kingston | Malden On Hudson | Ulster | 12453 | G | 3004 | Saugerties | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2021-08-02 | 2021-08-10 | 6 | 2021-08-10 | [14 empty] | 2021-08-30 | 2021-09-07 |  | Y
Central Hudson |  | SolarCity dba Tesla Energy Operations, Inc. | CH-14076 | Newburgh | Newburgh | Orange | 12550 | G | 5004 | Marlboro | N |  | 7.6 | [13 empty] | NM | N | 1 Tesla 1538000-xx-y (240V) [SI1] | 2021-08-03 | 2021-08-10 | 5 | 2021-08-10 | [14 empty] | 2021-08-19 | 2021-08-25 |  | Y
Central Hudson |  | Solar Generation | CH-14077 | Kingston | Woodstock | Ulster | 12498 | G | 3012 | Woodstock | N |  | 14 | [13 empty] | NM | N | 2 SMA America SB7.0-1SP-US-40 (240V) [SI1] | 2021-08-03 | 2021-08-10 | 5 | 2021-08-10 | [14 empty] | 2021-10-28 | 2021-11-04 |  | Y
Central Hudson |  | New York Power Soluitons | CH-14078 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8092 | Fishkill Plains | N |  | 11.02 | [13 empty] | NM | N | 38 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-08-03 | 2021-08-10 | 5 | 2021-08-10 | [14 empty] | 2021-11-29 | 2021-11-30 |  | Y
Central Hudson |  | PlugPV, LLC | CH-14081 | Poughkeepsie | Pleasant Vly | Dutchess | 12569 | G | 7024 | Tinkertown | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE11400H-US (240V) | 2021-08-11 | 2021-08-17 | 4 | 2021-08-17 | [14 empty] | 2021-09-10 | 2021-09-28 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-14080 | Poughkeepsie | Lagrangevl | Dutchess | 12540 | G | 6055 | Todd Hill | N |  | 9.28 | [13 empty] | NM | N | 32 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-08-04 | 2021-08-10 | 4 | 2021-08-10 | [14 empty] | 2021-10-25 | 2021-11-01 |  | Y
Central Hudson |  | SunPower Direct (NY) | CH-14079 | Poughkeepsie | Lagrangevl | Dutchess | 12540 | G | 6053 | Todd Hill | N |  | 7.68 | [13 empty] | NM | N | 22 Enphase Energy IQ7AS-66-ACM-US (240V) [SI1] | 2021-08-04 | 2021-08-10 | 4 | 2021-08-10 | [14 empty] | 2021-09-24 | 2021-10-01 |  | Y
Central Hudson |  | New York State Solar Farm | CH-14085 | Kingston | Woodstock | Ulster | 12498 | G | 3012 | Woodstock | N | CH-12801 | 2.21 | [13 empty] | NM | N | 7 SunPower SPR-X21-350-BLK-E-AC (240V) | 2021-08-05 | 2021-08-12 | 5 | 2021-08-12 | [14 empty] | 2021-12-06 | 2021-12-10 |  | Y
Central Hudson |  | New York State Solar Farm | CH-14082 | Newburgh | Highland | Ulster | 12528 | G | 5082 | Highland | N |  | 9.765 | [13 empty] | NM | N | 31 SunPower SPR-X22-360-E-AC (240V) | 2021-08-05 | 2021-08-11 | 4 | 2021-08-11 | [14 empty] | 2021-10-20 | 2021-11-08 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14083 | Newburgh | Newburgh | Orange | 12550 | G | 4022 | Coldenham | N |  | 9.8 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3800H-US (240V) 1 SolarEdge Technologies SE6000H-US (240V) | 2021-08-05 | 2021-08-12 | 5 | 2021-08-12 | [14 empty] | 2021-09-24 | 2021-10-01 |  | Y
Central Hudson |  | PlugPV, LLC. | CH-14084 | Newburgh | Newburgh | Orange | 12550 | G | 5001 | Marlboro | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2021-08-05 | 2021-08-12 | 5 | 2021-08-12 | [14 empty] | 2021-09-27 | 2021-10-04 |  | Y
Central Hudson |  | PlugPV, LLC. | CH-14086 | Newburgh | New Windsor | Orange | 12553 | G | 4046 | Union Ave | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000H-US (208V) [SI1] | 2021-08-06 | 2021-08-13 | 5 | 2021-08-13 | [14 empty] | 2021-09-17 | 2021-09-24 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14087 | Newburgh | Newburgh | Orange | 12550 | G | 410 | Montgomery St | N |  | 3.84 | [13 empty] | NM | N | 1 Delta Electronics M4-TL-US (240V) [SI1] | 2021-08-09 | 2021-08-13 | 4 | 2021-08-13 | [14 empty] | 2021-09-14 | 2021-09-30 |  | Y
Central Hudson |  | Lighthouse Solar | CH-14088 | Kingston | Cottekill | Ulster | 12419 | G | 3021 | High Falls | N |  | 15.08 | [13 empty] | NM | N | 52 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-08-09 | 2021-08-13 | 4 | 2021-08-13 | [14 empty] | 2021-10-14 | 2021-10-19 |  | Y
Central Hudson |  | Trinity Solar Systems | CH-14091 | Newburgh | Newburgh | Orange | 12550 | G | 4014 | West Balmville | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000H-US (240V) | 2021-08-09 | 2021-08-13 | 4 | 2021-08-13 | [14 empty] | 2021-10-13 | 2021-10-13 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-14092 | Newburgh | New Windsor | Orange | 12553 | G | 4044 | Union Ave | N |  | 8.64 | [13 empty] | NM | N | 36 Enphase Energy IQ7-60-x-US (240V) | 2021-08-09 | 2021-08-13 | 4 | 2021-08-13 | [14 empty] | 2021-10-05 | 2021-10-12 |  | Y
Central Hudson |  | PlugPV, LLC | CH-14090 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6042 | Spackenkill | N |  | 20 | [13 empty] | NM | N | 2 SolarEdge Technologies SE10000H-US (240V) | 2021-08-09 | 2021-08-13 | 4 | 2021-08-13 | [17 empty] | W
Central Hudson |  | Infinity Solar Systems | CH-14089 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6043 | Spackenkill | N |  | 4.08 | [13 empty] | NM | N | 17 Enphase Energy IQ7-60-x-US (240V) | 2021-08-09 | 2021-08-13 | 4 | 2021-08-13 | [14 empty] | 2021-10-13 | 2021-10-18 |  | Y
Central Hudson |  | City Winery Hudson Valley LLC | CH-13704 | Newburgh | Montgomery | Orange | 12549 | G | 5071 | Montgomery | N | [11 empty] | 336.5 |  |  |  | NM | N | GEN#1 Primeline, GEN#2 Lincoln ElectricGEN #1 RC 444TTDS7946AN W, GEN #2 SM1346A1336.5 | 2021-10-14 | 2021-10-28 | 10 | 2021-10-28 | 2021-10-28 | 2021-11-17 | 14 | [5 empty] | 85100 |  |  | 2022-07-14 | 2022-07-14 |  |  |  |  | N
Central Hudson |  | None | CH-14095 | Catskill | E Durham | Greene | 12423 | G | 2071 | Freehold | N | CH-14095 | 16.696 | [13 empty] | NM | N | 8 Altenergy Power System QS1 (240V) 1 Altenergy Power System YC600 (240V) 4 Altenergy Power System QS1 (240V) 1 Altenergy Power System YC600 (240V) 1 Altenergy Power System QS1 (240V) | 2021-08-30 | 2021-09-14 | 10 | 2021-09-14 | [14 empty] | 2021-11-24 | 2021-11-24 |  | Y
Central Hudson |  | murphy solar and central air | CH-14094 | Catskill | Catskill | Greene | 12414 | G | 2003 | North Catskill | N |  | 5 | [13 empty] | NM | N | 1 SMA America SB5.0-1SP-US-41 (240V) [SI1] | 2021-08-10 | 2021-08-16 | 4 | 2021-08-16 | [14 empty] | 2021-12-29 | 2021-12-29 |  | Y
Central Hudson |  | PLUGPV, LLC | CH-14093 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6066 | Inwood Ave | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2021-08-10 | 2021-08-16 | 4 | 2021-08-16 | [14 empty] | 2021-11-22 | 2021-11-23 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-14098 | Newburgh | Highland | Ulster | 12528 | G | 5082 | Highland | N |  | 17.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) 1 SolarEdge Technologies SE7600H-US (240V) | 2021-08-16 | 2021-08-25 | 7 | 2021-08-25 | [8 empty] | 350 | 350 |  | 2021-08-27 | 2021-08-27 | 2021-10-13 | 2021-10-05 | 2021-10-12 |  | Y
Central Hudson |  | PLUGPV, LLC | CH-14101 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8043 | Myers Corners | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2021-08-11 | 2021-08-16 | 3 | 2021-08-16 | [14 empty] | 2021-08-18 | 2021-08-18 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-14096 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6003 | Reynolds Hill | N |  | 11.28 | [13 empty] | NM | N | 47 Enphase Energy IQ7-60-x-US (240V) | 2021-08-11 | 2021-08-17 | 4 | 2021-08-17 | [14 empty] | 2021-10-26 | 2021-11-01 |  | Y
Central Hudson |  | PlugPV, LLC. | CH-14103 | Newburgh | Newburgh | Orange | 12550 | G | 4023 | Coldenham | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2021-08-11 | 2021-08-17 | 4 | 2021-08-17 | [14 empty] | 2021-09-27 | 2021-10-04 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14099 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6095 | Manchester | N |  | 4.8 | [13 empty] | NM | N | 1 Delta Electronics M5-TL-US (240V) [SI1] | 2021-08-11 | 2021-08-16 | 3 | 2021-08-16 | [14 empty] | 2021-10-28 | 2021-11-04 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14097 | Kingston | Stone Ridge | Ulster | 12484 | G | 3023 | High Falls | N |  | 7.68 | [13 empty] | NM | N | 1 Delta Electronics M8-TL-US (240V) [SI1] | 2021-08-11 | 2021-08-17 | 4 | 2021-08-17 | [14 empty] | 2021-11-03 | 2021-11-09 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-14100 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8095 | Fishkill Plains | N |  | 11.02 | [13 empty] | NM | N | 38 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-08-11 | 2021-08-16 | 3 | 2021-08-16 | [14 empty] | 2021-11-17 | 2021-11-22 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-14102 | Newburgh | New Windsor | Orange | 12553 | G | 4045 | Union Ave | N |  | 6.09 | [13 empty] | NM | N | 21 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-08-27 | 2021-08-27 | 0 | 2021-08-27 | [14 empty] | 2021-12-08 | 2021-12-14 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14104 | Newburgh | New Windsor | Orange | 12553 | G | 4042 | Union Ave | Y |  | 7.6 | 3.8 | [12 empty] | NM | N | 2 SolarEdge Technologies SE3800H-US (240V) [SI1] 2SolarEdge TechnologiesSE3800H-USM3 | 2021-08-12 | 2021-08-17 | 3 | 2021-08-17 | [14 empty] | 2022-04-28 | 2022-05-05 |  | Y
Central Hudson |  | Lighthouse Solar | CH-14105 | Poughkeepsie | Lagrangeville | Dutchess | 12540 | G | 6055 | Todd Hill | N |  | 10.82 | [13 empty] | NM | N | 31 Enphase Energy IQ7A-72-2-US (240V) [SI1] | 2021-08-12 | 2021-08-17 | 3 | 2021-08-17 | [8 empty] | 350 | 350 |  | 2021-08-20 | 2021-08-20 | 2021-10-07 | 2021-11-16 | 2021-12-01 |  | Y
Central Hudson |  | Goodwill Road NY LLC | CH-14106 | Newburgh | Montgomery | Orange | 12549 | G | 4026 | Coldenham | N |  | 4298 | [13 empty] | CDG | Y | 35 Chint Power Systems America CPS SCH125KTL-DO/US-600 (600V) | 2021-08-30 | 2021-09-08 | 6 | 2021-09-08 | 2021-09-08 | 2021-09-16 | 6 | 2021-10-12 | 2021-11-15 | 2022-02-14 | 60 | 19300 | 200942.95 |  | 2022-06-13 | 2022-11-22 | 2022-11-22 |  |  |  |  | N | Y
Central Hudson |  | SunCommon | CH-14107 | Kingston | Cottekill | Ulster | 12419 | G | 3021 | High Falls | Y | CH-01671 | 6.96 | [13 empty] | NM | N | 24 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-09-23 | 2021-09-23 | 0 | 2021-09-23 | [14 empty] | 2021-10-22 | 2021-10-28 |  | Y
Central Hudson |  | Lighthouse Solar | CH-14108 | Newburgh | Highland |  | 12528 | G | 5024 | Ohioville | N |  | 9.28 | [13 empty] | NM | N | 32 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-08-13 | 2021-08-18 | 3 | 2021-08-18 | [8 empty] | 350 | [8 empty] | W
Central Hudson |  | PurePoint Energy, LLC | CH-14112 | Poughkeepsie | Pine Plns | Dutchess | 12567 | G | 7091 | Pulvers Corners | N |  | 12.564 | [13 empty] | NM | N | 36 SunPower SPR-A420-G-AC (240V) 2TeslaPowerwall2 | 2021-10-05 | 2021-10-18 | 9 | 2021-10-18 | [14 empty] | 2022-10-27 | 2022-10-28 |  | Y
Central Hudson |  | Kasselman Solar, LLC | CH-14114 | Kingston | Kingston | Ulster | 12401 | G | 1014 | Boulevard | N |  | 6.98 | [13 empty] | NM | N | 20 Enphase Energy IQ7A-72-2-US (240V) [SI1] | 2021-09-10 | 2021-09-10 | 0 | 2021-09-10 | [14 empty] | 2021-10-13 | 2021-10-18 |  | Y
Central Hudson |  | PLUGPV, LLC | CH-14113 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6096 | Manchester | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2021-09-01 | 2021-09-09 | 5 | 2021-09-09 | [14 empty] | 2021-10-22 | 2021-11-01 |  | Y
Central Hudson |  | Kasselman Solar, LLC | CH-14116 | Catskill | Saugerties | Ulster | 12477 | G | 2001 | North Catskill | Y |  | 7.6 | 7.6 | [12 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) 1Solar EdgeSE7600H-US | 2023-04-06 | 2023-04-17 | 6 | 2023-04-17 | [14 empty] | 2023-04-17 | 2023-04-18 |  | Y
Central Hudson |  | PlugPV, LLC | CH-14109 | Catskill | Coxsackie | Greene | 12051 | G | 1076 | Coxsackie | N |  | 17.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) 1 SolarEdge Technologies SE7600H-US (240V) | 2021-09-10 | 2021-09-24 | 10 | 2021-09-24 | [8 empty] | 350 | 350 |  | 2021-09-30 | 2021-09-30 | 2021-11-08 | 2022-02-18 | 2022-02-25 |  | Y
Central Hudson |  | New York State Solar Farm | CH-14117 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8095 | Fishkill Plains | N |  | 9.45 | [13 empty] | NM | N | 30 SunPower SPR-X22-360-E-AC (240V) | 2021-08-27 | 2021-08-27 | 0 | 2021-08-27 | [14 empty] | 2021-09-17 | 2021-09-24 |  | Y
Central Hudson |  | New York State Solar Farm | CH-14110 | Kingston | Kingston | Ulster | 12401 | G | 1021 | East Kingston | N |  | 16.38 | [13 empty] | NM | N | 52 SunPower SPR-X22-360-E-AC (240V) | 2021-08-16 | 2021-08-25 | 7 | 2021-08-25 | [14 empty] | 2021-11-03 | 2021-11-03 |  | Y
Central Hudson |  | Apex Solar Power | CH-14111 | Newburgh | Highland | Ulster | 12528 | G | 5084 | Highland | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2021-08-16 | 2021-08-25 | 7 | 2021-08-25 | [14 empty] | 2021-10-28 | 2021-11-04 |  | Y
Central Hudson |  | Integrity Solar Solutions | CH-14115 | Newburgh | Newburgh | Orange | 12550 | G | 4013 | West Balmville | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE11400H-US (240V) | 2021-09-09 | 2021-09-09 | 0 | 2021-09-09 | [14 empty] | 2021-09-16 | 2021-09-23 |  | Y
Central Hudson |  | PlugPV, LLC | CH-14118 | Newburgh | Campbell Hall | Orange | 10916 | G | 5051 | Maybrook | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2021-08-27 | 2021-09-13 | 10 | 2021-09-13 | [14 empty] | 2021-09-27 | 2021-10-04 |  | Y
Central Hudson |  | Trinity Solar | CH-14122 | Fishkill | Beacon | Dutchess | 12508 | G | 8017 | Forgebrook | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE11400H-US (240V) | 2021-08-30 | 2021-09-14 | 10 | 2021-09-14 | [14 empty] | 2021-11-09 | 2021-12-20 |  | Y
Central Hudson |  | Lodestar Energy LLC | CH-14120 | Catskill | New Baltimore | Greene | 12042 | G | 2061 | Freehold | N |  | 3500 | [13 empty] | RC | Y | 14 Sungrow Power Supply SG250HX-US (800V) [SI1] | 2021-09-07 | 2021-09-10 | 3 | 2021-09-10 | 2021-09-10 | 2021-09-30 | 14 | 2021-10-14 | 2021-11-03 | 2022-02-01 | 59 | 12572.06 | 9771926.05 | [7 empty] | 2022-08-22 | W
Central Hudson |  | Infinity Solar Systems | CH-14119 | Newburgh | Montgomery | Orange | 12549 | G | 5072 | Montgomery | N |  | 10.8 | [13 empty] | NM | N | 45 Enphase Energy IQ7-60-x-US (240V) | 2021-09-07 | 2021-09-21 | 10 | 2021-09-21 | [14 empty] | 2021-11-08 | 2021-11-12 |  | Y
Central Hudson |  | PlugPV, LLC. | CH-14121 | Newburgh | Newburgh | Orange | 12550 | G | 5001 | Marlboro | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2021-08-27 | 2021-08-27 | 0 | 2021-08-27 | [14 empty] | 2021-10-12 | 2021-10-18 |  | Y
Central Hudson |  | Autonomous Energies LLC | CH-14123 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7051 | Rhinebeck | N |  | 6.38 | [13 empty] | NM | N | 22 Enphase Energy IQ7PLUS-72-x-ACM-US (240V) | 2021-08-27 | 2021-08-27 | 0 | 2021-08-27 | [14 empty] | 2021-09-16 | 2021-09-23 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14125 | Fishkill | Hopewell Jct | Dutchess | 12533 | G | 8095 | Fishkill Plains | N | CH-14125 | 7.68 | [13 empty] | NM | N | 2 Delta Electronics M4-TL-US (240V) [SI1] | 2021-10-20 | 2021-11-03 | 10 | 2021-11-03 | [14 empty] | 2022-05-12 | 2022-05-17 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14124 | Kingston | Saugerties | Ulster | 12477 | G | 1021 | East Kingston | N |  | 3.8 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3800H-US (240V) | 2021-09-15 | 2021-09-15 | 0 | 2021-09-15 | [14 empty] | 2021-10-21 | 2021-10-28 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-14126 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6043 | Spackenkill | N |  | 17.98 | [13 empty] | NM | N | 62 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-09-07 | 2021-09-21 | 10 | 2021-09-21 | [14 empty] | 2021-10-27 | 2021-11-08 |  | Y
Central Hudson |  | Solar Generation | CH-14128 | Kingston | Woodstock | Ulster | 12498 | G | 3012 | Woodstock | N | CH-08274 | 2.9 | [13 empty] | NM | N | 10 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-09-15 | 2021-09-15 | 0 | 2021-09-15 | [14 empty] | 2021-10-26 | 2021-11-01 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-14129 | Newburgh | New Windsor | Orange | 12553 | G | 4054 | Union Ave | N |  | 8.88 | [13 empty] | NM | N | 37 Enphase Energy IQ7-60-x-US (240V) | 2021-09-01 | 2021-09-01 | 0 | 2021-09-01 | [14 empty] | 2021-10-18 | 2021-10-25 |  | Y
Central Hudson |  | SunCommon | CH-14127 | Kingston | Stone Ridge | Ulster | 12484 | G | 3023 | High Falls | Y |  | 14.68 | 5 | [12 empty] | NM | N | 1 SMA America SB7.7-1SP-US-41 (240V) [SI1] 1 SMA America SB7.0-1SP-US-41 (240V) [SI1] 2TeslaPowerwall 2 | 2021-09-17 | 2021-10-01 | 10 | 2021-10-01 | [8 empty] | 350 | 350 |  | 2021-10-12 | 2021-10-12 | 2021-11-10 | 2021-12-01 | 2021-12-01 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14130 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 6068 | Inwood Ave | N | CH-14130 | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2021-09-01 | 2021-09-01 | 0 | 2021-09-01 | [14 empty] | 2021-10-04 | 2021-10-08 |  | Y
Central Hudson |  | Solar Generation | CH-14133 | Kingston | Kingston | Ulster | 12401 | G | 2094 | Hurley Ave | N |  | 6 | [13 empty] | NM | N | 1 SMA America SB6000US (240V) | 2021-09-01 | 2021-09-01 | 0 | 2021-09-01 | [14 empty] | 2021-09-17 | 2021-09-24 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14132 | Kingston | Ellenvl | Ulster | 12428 | G | 3078 | Greenfield Rd | Y |  | 6 | 5 | [12 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) 1TeslaAC Powerwall 2.0 | 2021-11-29 | 2021-12-13 | 10 | 2021-12-13 | [14 empty] | 2022-06-02 | 2022-06-06 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14131 | Newburgh | New Windsor | Orange | 12553 | G | 4097 | Bethlehem Rd | Y |  | 4.8 | 10 | [12 empty] | NM | N | 1 Delta Electronics M5-TL-US (240V) [SI1] 2TeslaAC Powerwall 2.0 | 2021-10-20 | 2021-11-03 | 10 | 2021-11-03 | [14 empty] | 2021-12-08 | 2021-12-14 |  | Y
Central Hudson |  | SolarCity dba Tesla Energy Operations, Inc. | CH-14134 | Kingston | W Shokan | Ulster | 12494 | G | 3011 | Woodstock | Y |  | 19 | 5 | [12 empty] | NM | N | 2 Tesla 1538000-xx-y (240V) - may be a component of Powerwall+ (185000-XX-Y) [SI1] 1 Tesla 1534000-xx-y (240V) [SI1] 1TeslaAC Powerwall 2.0 | 2021-10-15 | 2021-10-15 | 0 | 2021-10-15 | [8 empty] | 350 | 350 |  | 2021-10-15 | 2021-10-15 | 2021-10-29 | 2021-11-23 | 2021-11-30 |  | Y
Central Hudson |  | PlugPV, LLC. | CH-14135 | Newburgh | Newburgh | Orange | 12550 | G | 5001 | Marlboro | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2021-09-02 | 2021-09-02 | 0 | 2021-09-02 | [14 empty] | 2021-09-27 | 2021-10-04 |  | Y
Central Hudson |  | SunCommon | CH-14140 | Poughkeepsie | Staatsburg | Dutchess | 12580 | G | 7041 | Staatsburg | N |  | 12.76 | [13 empty] | NM | N | 44 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-09-08 | 2021-09-22 | 10 | 2021-09-22 | [14 empty] | 2021-12-06 | 2021-12-10 |  | Y
Central Hudson |  | SunCommon | CH-14144 | Newburgh | Mountainvl | Orange | 10953 | G | 4095 | Bethlehem Rd | Y | CH-00821 |  | 5 | [12 empty] | NM | N | 1TeslaPowerwall 2 | 2021-09-21 | 2021-10-05 | 10 | 2021-10-05 | [14 empty] | 2022-09-19 | 2022-09-23 |  | Y
Central Hudson |  | SunCommon | CH-14139 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7052 | Rhinebeck | N |  | 98.8 | [13 empty] | NM | Y | 8 SolarEdge Technologies SE11400H-US (240V) 1 SolarEdge Technologies SE7600H-US (240V) | 2021-09-09 | 2021-09-15 | 4 | 2021-09-15 | 2021-09-15 | 2021-10-05 | 14 | [5 empty] | 7434.86 | 4746.66 |  | 2021-10-22 | 2021-10-22 | 2022-01-04 | 2022-04-29 | 2022-04-29 | 2022-06-01 | Y | N
Central Hudson |  | Solar Generation Projects, LLC | CH-14137 | Kingston | Marbletown | Ulster | 12401 | G | 2093 | Hurley Ave | N |  | 4500 | [13 empty] | CDG | Y | 36 Sungrow Power Supply SG125HV (600V) | 2021-08-23 | 2021-09-03 | 9 | 2021-09-03 | 2021-09-03 | 2021-09-20 | 10 | 2022-01-05 | 2022-02-02 | 2022-04-27 | 58 | 18967.88 | 5057029.55 | [7 empty] | 2022-12-01 | W
Central Hudson |  | Solar Generation Projects, LLC | CH-14136 | Kingston | Marbletown |  | 12401 | G | 2093 | Hurley Ave | N |  | 3500 | [13 empty] | CDG | Y | 28 Sungrow Power Supply SG125HV (600V) | 2021-08-23 | 2021-09-03 | 9 | 2021-09-03 | 2021-09-03 | 2021-09-20 | 10 |  |  |  |  | 22000 | [9 empty] | W
Central Hudson |  | PlugPV, LLC. | CH-14143 | Newburgh | Marlboro | Ulster | 12542 | G | 5001 | Marlboro | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2021-09-03 | 2021-09-03 | 0 | 2021-09-03 | [14 empty] | 2021-09-27 | 2021-10-04 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14145 | Fishkill | Beacon | Dutchess | 12508 | G | 8085 | Tioronda | N |  | 3.84 | [13 empty] | NM | N | 1 Delta Electronics M4-TL-US (240V) [SI1] | 2021-09-13 | 2021-09-27 | 10 | 2021-09-27 | [17 empty] | W
Central Hudson |  | Infinity Solar Systems | CH-14138 | Newburgh | Marlboro | Ulster | 12542 | G | 5002 | Marlboro | N |  | 8.12 | [13 empty] | NM | N | 28 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-09-02 | 2021-09-02 | 0 | 2021-09-02 | [14 empty] | 2021-10-11 | 2021-10-15 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-14146 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8051 | North Chelsea | N |  | 3.84 | [13 empty] | NM | N | 16 Enphase Energy IQ7-60-x-US (240V) | 2021-09-07 | 2021-09-21 | 10 | 2021-09-21 | [14 empty] | 2021-10-13 | 2021-10-13 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-14142 | Fishkill | Castle Pt | Dutchess | 12511 | G | 8051 | North Chelsea | N |  | 4.8 | [13 empty] | NM | N | 20 Enphase Energy IQ7-60-x-US (240V) | 2021-09-07 | 2021-09-21 | 10 | 2021-09-21 | [14 empty] | 2021-10-18 | 2021-10-25 |  | Y
Central Hudson |  | Solar Generation | CH-14141 | Kingston | Kingston | Ulster | 12401 | G | 1022 | East Kingston | N |  | 3.2 | [13 empty] | NM | N | 11 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-09-03 | 2021-09-03 | 0 | 2021-09-03 | [14 empty] | 2022-01-31 | 2022-02-04 |  | Y
Central Hudson |  | Conscious Energy Inc | CH-14147 | Kingston | Kingston | Ulster | 12401 | G | 3NTWK | Converse St | N |  | 4.5 | [13 empty] | NM | N | 5 Altenergy Power System YC1000-3-480 (480V) | 2021-10-18 | 2021-11-01 | 10 | 2021-11-01 | [14 empty] | 2022-10-18 | 2022-10-25 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-14148 | Newburgh | Newburgh | Orange | 12550 | G | 5001 | Marlboro | N |  | 14.21 | [13 empty] | NM | N | 49 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-09-07 | 2021-09-07 | 0 | 2021-09-07 | [14 empty] | 2021-10-06 | 2021-10-06 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14150 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8051 | North Chelsea | N |  | 4.8 | [13 empty] | NM | N | 1 Delta Electronics M5-TL-US (240V) [SI1] | 2021-10-13 | 2021-10-27 | 10 | 2021-10-27 | [14 empty] | 2021-12-06 | 2021-12-10 |  | Y
Central Hudson |  | Solar Energy Systems | CH-14154 | Kingston | Kingston | Ulster | 12401 | G | 1003 | Jansen Ave | N |  | 250 | [13 empty] | RNM | Y | 2 SMA America SHP 125-US-20 (480V) | 2021-10-12 | 2021-10-26 | 10 | 2021-10-26 | 2021-10-26 | 2021-11-02 | 5 | [5 empty] | 10405.5 |  | 2022-05-04 | 2022-10-26 | 2022-10-26 |  |  |  |  | N | Y
Central Hudson |  | PlugPV, LLC | CH-14152 | Kingston | Grahamsvl | Sullivan | 12740 | G | 3091 | Neversink | N |  | 15.2 | [13 empty] | NM | N | 2 SolarEdge Technologies SE7600H-US (240V) | 2021-09-08 | 2021-09-08 | 0 | 2021-09-08 | [8 empty] | 350 | 350 |  | 2021-09-10 | 2021-09-10 | 2021-11-10 | 2022-01-05 | 2022-01-28 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14155 | Kingston | Saugerties | Ulster | 12477 | G | 3001 | Saugerties | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2021-09-08 | 2021-09-08 | 0 | 2021-09-08 | [14 empty] | 2021-12-14 | 2021-12-27 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14151 | Newburgh | New Windsor | Orange | 12553 | G | 4044 | Union Ave | Y | CH-10097 | 3.84 | 5 | [12 empty] | NM | N | 1 Delta Electronics M4-TL-US (240V) [SI1] 1TeslaAC Powerwall 2.0 | 2021-10-20 | 2021-11-03 | 10 | 2021-11-03 | [14 empty] | 2021-12-01 | 2021-12-07 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14153 | Newburgh | Newburgh | Orange | 12550 | G | 5001 | Marlboro | N |  | 4.8 | [13 empty] | NM | N | 1 Delta Electronics M5-TL-US (240V) [SI1] | 2021-09-21 | 2021-10-05 | 10 | 2021-10-05 | [14 empty] | 2021-12-06 | 2021-12-10 |  | Y
Central Hudson |  | Hudson River Solar | CH-14160 | Poughkeepsie | Ancramdale | Columbia | 12503 | G | 7085 | Ancram | Y |  | 9 | 9 | [12 empty] | NM | N | 1 Sol-Ark Sol-Ark-12K-P (240V) 2Sol-ArkSol-Ark 12K-P (240V) | 2021-09-23 | 2021-10-07 | 10 | 2021-10-07 | [14 empty] | 2021-11-21 | 2021-11-30 |  | Y
Central Hudson |  | Kasselman Solar | CH-14158 | Poughkeepsie | Verbank | Dutchess | 12585 | G | 6057 | Todd Hill | N |  | 6.631 | [13 empty] | NM | N | 19 Enphase Energy IQ7A-72-2-US (208V) [SI1] | 2021-09-13 | 2021-09-27 | 10 | 2021-09-27 | [14 empty] | 2021-09-27 | 2021-10-04 |  | Y
Central Hudson |  | Kasselman Solar, LLC | CH-14157 | Kingston | Saugerties | Ulster | 12477 | G | 3002 | Saugerties | N |  | 12.215 | [13 empty] | NM | N | 35 Enphase Energy IQ7A-72-2-US (240V) [SI1] | 2021-09-13 | 2021-09-27 | 10 | 2021-09-27 | [14 empty] | 2021-10-19 | 2021-10-25 |  | Y
Central Hudson |  | SolarCity dba Tesla Energy Operations, Inc. | CH-14156 | Kingston | W Camp | Ulster | 12490 | G | 3004 | Saugerties | Y |  | 7.6 | 10 | [12 empty] | NM | N | 1 Tesla 1538000-xx-y (240V) - may be a component of Powerwall+ (185000-XX-Y) [SI1] 2TeslaAC Powerwall 2.0 | 2021-10-18 | 2021-11-01 | 10 | 2021-11-01 | [14 empty] | 2021-12-08 | 2021-12-08 |  | Y
Central Hudson |  | SolarCity dba Tesla Energy Operations, Inc. | CH-14165 | Kingston | Saugerties | Ulster | 12477 | G | 3004 | Saugerties | N |  | 15.2 | [13 empty] | NM | N | 1 Tesla 1538000-xx-y (240V) - may be a component of Powerwall+ (185000-XX-Y) [SI1] 1 Tesla 1538000-xx-y (240V) - may be a component of Powerwall+ (185000-XX-Y) [SI1] | 2021-09-23 | 2021-10-06 | 9 | 2021-10-06 | [8 empty] | 350 | 350 |  | 2021-10-26 | 2021-10-26 | 2021-12-08 | 2021-12-10 | 2021-12-21 |  | Y
Central Hudson |  | SunPower Direct (NY) | CH-14164 | Poughkeepsie | Lagrangevl | Dutchess | 12540 | G | 6053 | Todd Hill | N |  | 5.584 | [13 empty] | NM | N | 16 SunPower SPR-A400-G-AC (240V) | 2021-09-10 | 2021-09-24 | 10 | 2021-09-24 | [14 empty] | 2021-10-15 | 2021-10-19 |  | Y
Central Hudson |  | Trinity Solar Systems | CH-14162 | Newburgh | Walden | Orange | 12586 | G | 4023 | Coldenham | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2021-09-09 | 2021-09-09 | 0 | 2021-09-09 | [14 empty] | 2021-11-01 | 2021-11-08 |  | Y
Central Hudson |  | SolarCity dba Tesla Energy Operations, Inc. | CH-14166 | Newburgh | New Windsor | Orange | 12553 | G | 4095 | Bethlehem Rd | N |  | 11.4 | [13 empty] | NM | N | 1 Tesla 1534000-xx-y (240V) [SI1] 1 Tesla 1538000-xx-y (240V) - may be a component of Powerwall+ (185000-XX-Y) [SI1] | 2021-09-23 | 2021-10-06 | 9 | 2021-10-06 | [14 empty] | 2021-10-11 | 2021-10-15 |  | Y
Central Hudson |  | PlugPV, LLC. | CH-14163 | Newburgh | Newburgh | Orange | 12550 | G | 5001 | Marlboro | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2021-09-09 | 2021-09-09 | 0 | 2021-09-09 | [14 empty] | 2021-10-12 | 2021-10-18 |  | Y
Central Hudson |  | SolarCity dba Tesla Energy Operations, Inc. | CH-14168 | Newburgh | Montgomery | Orange | 12549 | G | 5054 | Maybrook | Y |  | 15.2 | 20 | [12 empty] | NM | N | 2 Tesla 1538000-xx-y (240V) - may be a component of Powerwall+ (185000-XX-Y) [SI1] 4TeslaAC Powerwall 2.0 | 2022-01-31 | 2022-02-11 | 9 | 2022-02-11 | [14 empty] | 2022-02-17 | 2022-02-23 |  | Y
Central Hudson |  | Trinity Solar Systems | CH-14161 | Newburgh | Walden | Orange | 12586 | G | 5041 | East Walden | N |  | 13.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) 1 SolarEdge Technologies SE6000H-US (240V) | 2021-09-09 | 2021-09-09 | 0 | 2021-09-09 | [14 empty] | 2022-07-27 | 2022-07-27 |  | Y
Central Hudson |  | SolarCity dba Tesla Energy Operations, Inc. | CH-14169 | Newburgh | Montgomery | Orange | 12549 | G | 5073 | Montgomery | Y |  | 7.6 | 7.6 | [12 empty] | NM | N | 1 Tesla 1538000-xx-y (240V) - may be a component of Powerwall+ (185000-XX-Y) [SI1] 1TeslaAC Powerwall 2.0 | 2021-10-21 | 2021-11-04 | 10 | 2021-11-04 | [14 empty] | 2021-11-16 | 2021-11-23 |  | Y
Central Hudson |  | Solar Generation | CH-14167 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7013 | Hibernia | N |  | 5.8 | [13 empty] | NM | N | 20 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-09-10 | 2021-09-24 | 10 | 2021-09-24 | [14 empty] | 2022-03-15 | 2022-03-18 |  | Y
Central Hudson |  | SunCommon | CH-14170 | Kingston | Kingston | Ulster | 12401 | G | 112 | South Wall St | N |  | 43.2 | [13 empty] | NM | N | 1 SolarEdge Technologies SE43.2KUS (208V) | 2021-11-04 | 2021-11-17 | 9 | 2021-11-17 | [14 empty] | 2021-12-06 | 2021-12-14 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-14173 | Kingston | Saugerties | Ulster | 12477 | G | 3002 | Saugerties | N |  | 8.12 | [13 empty] | NM | N | 28 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-08-27 | 2021-09-13 | 10 | 2021-09-13 | [14 empty] | 2021-11-17 | 2021-11-17 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-14172 | Newburgh | New Windsor | Orange | 12553 | G | 4044 | Union Ave | N |  | 7.25 | [13 empty] | NM | N | 25 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-08-27 | 2021-09-13 | 10 | 2021-09-13 | [14 empty] | 2021-10-12 | 2021-10-18 |  | Y
Central Hudson |  | PlugPV, LLC. | CH-14171 | Newburgh | Rock Tvrn | Orange | 12575 | G | 4097 | Bethlehem Rd | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE11400H-US (240V) | 2021-08-27 | 2021-09-13 | 10 | 2021-09-13 | [14 empty] | 2021-10-21 | 2021-10-28 |  | Y
Central Hudson |  | PlugPV LLC | CH-14176 | Newburgh | Highland | Ulster | 12528 | G | 5082 | Highland | N |  | 12 | [13 empty] | NM | N | 2 SolarEdge Technologies SE6000H-US (240V) | 2021-08-30 | 2021-09-14 | 10 | 2021-09-14 | [14 empty] | 2021-10-14 | 2021-10-19 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14177 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8022 | Knapps Corners | Y | CH-14177 | 5.76 | 5 | [12 empty] | NM | N | 1 Delta Electronics M6-TL-US (240V) [SI1] 1TeslaAC Powerwall 2.0 | 2021-10-19 | 2021-11-02 | 10 | 2021-11-02 | [14 empty] | 2022-05-18 | 2022-05-19 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-14175 | Newburgh | Modena | Ulster | 12548 | G | 5013 | Modena | N |  | 7.83 | [13 empty] | NM | N | 27 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-08-30 | 2021-09-14 | 10 | 2021-09-14 | [8 empty] | 350 | 350 |  | 2021-09-15 | 2021-09-15 | 2021-10-08 | 2021-11-09 | 2021-11-16 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-14178 | Newburgh | New Windsor | Orange | 12553 | G | 4054 | Union Ave | N |  | 5.51 | [13 empty] | NM | N | 19 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-08-30 | 2021-09-14 | 10 | 2021-09-14 | [14 empty] | 2021-10-28 | 2021-11-04 |  | Y
Central Hudson |  | PLUGPV, LLC | CH-14184 | Catskill | Catskill | Greene | 12414 | G | 2001 | North Catskill | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2021-09-15 | 2021-09-15 | 0 | 2021-09-15 | [8 empty] | 350 | 350 |  | 2021-09-21 | 2021-09-21 | 2021-11-08 | 2022-05-04 | 2022-05-10 |  | Y
Central Hudson |  | PlugPV, LLC. | CH-14180 | Newburgh | Newburgh | Orange | 12550 | G | 4022 | Coldenham | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE11400H-US (240V) | 2021-09-15 | 2021-09-15 | 0 | 2021-09-15 | [8 empty] | 350 | 350 |  | 2021-09-15 | 2021-09-15 | 2021-12-06 | 2021-12-20 | 2021-12-20 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14179 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6091 | Manchester | N |  | 7.7 | [13 empty] | NM | N | 1 Delta Electronics M8-TL-US (240V) [SI1] | 2021-09-15 | 2021-09-15 | 0 | 2021-09-15 | [14 empty] | 2021-11-05 | 2021-11-09 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14185 | Kingston | Ellenvl | Ulster | 12428 | G | 3078 | Greenfield Rd | Y |  | 7.6 | 7.6 | [12 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) 1SolarEdge TechnologiesSE7600H-USS3 | 2021-08-31 | 2021-09-15 | 10 | 2021-09-15 | [14 empty] | 2022-01-04 | 2022-01-04 |  | Y
Central Hudson |  | SunCommon | CH-14186 | Newburgh | Wallkill | Ulster | 12589 | G | 5033 | Galeville | Y | CH-13916 |  | 5 | [12 empty] | NM | N | 1TeslaPowerwall 2.0 | 2021-09-17 | 2021-10-01 | 10 | 2021-10-01 | [14 empty] | 2021-11-15 | 2021-11-22 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-14181 | Newburgh | New Windsor | Orange | 12553 | G | 4045 | Union Ave | N |  | 7.54 | [13 empty] | NM | N | 26 Enphase Energy IQ6PLUS-72-2-US (240V) [SI1] | 2021-09-15 | 2021-09-15 | 0 | 2021-09-15 | [14 empty] | 2021-10-14 | 2021-10-19 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14182 | Poughkeepsie | Hyde Park | Dutchess | 12538 | G | 6074 | East Park | N |  | 7.7 | [13 empty] | NM | N | 1 Delta Electronics M8-TL-US (240V) [SI1] | 2021-08-31 | 2021-09-15 | 10 | 2021-09-15 | [14 empty] | 2021-12-06 | 2021-12-10 |  | Y
Central Hudson |  | PlugPV LLC | CH-14183 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6052 | Todd Hill | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE11400H-US (240V) | 2021-08-31 | 2021-09-15 | 10 | 2021-09-15 | [14 empty] | 2021-10-19 | 2021-10-25 |  | Y
Central Hudson |  | Hudson River Solar | CH-14189 | Catskill | Freehold | Greene | 12431 | G | 2061 | Freehold | Y | CH-14189 | 8.4 | 3.4 | [12 empty] | NM | N | 1 SMA America SB5.0-1SP-US-41 (240V) [SI1] 1 Schneider Electric Solar Inverters USA XW4024-120/240-60 (120V) 1SchneiderCONEXT SW4024 | 2021-10-29 | 2021-11-11 | 9 | 2021-11-11 | [14 empty] | 2021-12-28 | 2021-12-28 |  | W
Central Hudson |  | Apex Roofing, LLC | CH-14187 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6051 | Todd Hill | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE11400H-US (240V) | 2021-09-17 | 2021-10-01 | 10 | 2021-10-01 | [14 empty] | 2021-11-02 | 2021-11-08 |  | Y
Central Hudson |  | Suncommon | CH-14188 | Newburgh | New Paltz | Ulster | 12561 | G | 5031 | Galeville | N | CH-01938 | 9 | [13 empty] | NM | N | 1 SMA America SB3.0-1SP-US-41 (240V) [SI1] 1 SMA America SB6.0-1SP-US-41 (240V) [SI1] | 2021-09-16 | 2021-09-29 | 9 | 2021-09-29 | [14 empty] | 2022-11-17 | 2022-11-28 |  | Y
Central Hudson |  | SunCommon | CH-14191 | Kingston | Saugerties | Ulster | 12477 | G | 1021 | East Kingston | Y | CH-11135 |  | 5 | [12 empty] | NM | N | 1TeslaPowerwall 2 | 2021-09-17 | 2021-10-01 | 10 | 2021-10-01 | [14 empty] | 2021-10-22 | 2021-10-28 |  | Y
Central Hudson |  | Trinity Solar Systems | CH-14190 | Newburgh | Walden | Orange | 12586 | G | 5073 | Montgomery | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2021-09-02 | 2021-09-17 | 10 | 2021-09-17 | [14 empty] | 2021-11-09 | 2021-11-15 |  | Y
Central Hudson |  | PlugPV, LLC. | CH-14193 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6092 | Manchester | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2021-09-03 | 2021-09-20 | 10 | 2021-09-20 | [8 empty] | 350 | 350 |  | 2021-09-20 | 2021-09-20 | 2021-10-13 | 2021-10-21 | 2021-10-28 |  | Y
Central Hudson |  | PlugPV, LLC. | CH-14194 | Newburgh | Campbell Hall | Orange | 10916 | G | 5052 | Maybrook | N |  | 12 | [13 empty] | NM | N | 2 SolarEdge Technologies SE6000H-US (240V) | 2021-09-03 | 2021-09-20 | 10 | 2021-09-20 | [14 empty] | 2021-10-08 | 2021-10-15 |  | Y
Central Hudson |  | PlugPV, LLC | CH-14198 | Poughkeepsie | Wappingrs Fls | Dutchess | 12590 | G | 6052 | Todd Hill | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2021-09-07 | 2021-09-21 | 10 | 2021-09-21 | [14 empty] | 2021-10-15 | 2021-10-19 |  | Y
Central Hudson |  | PlugPV, LLC | CH-14197 | Newburgh | Montgomery | Orange | 12549 | G | 5073 | Montgomery | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2021-09-21 | 2021-10-05 | 10 | 2021-10-05 | [14 empty] | 2021-10-28 | 2021-11-04 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-14196 | Catskill | Coxsackie |  | 12051 | G | 1071 | Coxsackie | N |  | 13.34 | [13 empty] | NM | N | 46 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-09-07 | 2021-09-21 | 10 | 2021-09-21 | [8 empty] | 350 | 350 |  | 2021-09-21 | 2021-09-21 | 2021-11-08 |  |  |  | W
Central Hudson |  | Empire Solar Solutions | CH-14195 | Fishkill | Wappingrs Fls | Dutchess | 12590 | G | 8043 | Myers Corners | N |  | 11.89 | [13 empty] | NM | N | 41 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-09-07 | 2021-09-21 | 10 | 2021-09-21 | [17 empty] | W
Central Hudson |  | SunCommon | CH-14201 | Kingston | Rifton | Ulster | 12471 | G | 3041 | Sturgeon Pool | N |  | 6.98 | [13 empty] | NM | N | 20 Enphase Energy IQ7A-72-2-US (240V) [SI1] | 2021-09-22 | 2021-10-06 | 10 | 2021-10-06 | [14 empty] | 2021-11-03 | 2021-11-29 |  | Y
Central Hudson |  | US Energy Concierge, Inc. | CH-14199 | Fishkill | Fishkill | Dutchess | 12524 | G | 8065 | Merritt Park | N |  | 6.96 | [13 empty] | NM | N | 24 Enphase Energy IQ7PLUS-72-2-US (240V) [SI1] | 2021-09-27 | 2021-10-06 | 7 | 2021-10-06 | [14 empty] | 2021-11-21 | 2021-11-23 |  | Y
Central Hudson |  | PlugPV, LLC. | CH-14200 | Fishkill | Hopewell Jct | Orange | 12553 | G | 8091 | Fishkill Plains | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2021-09-24 | 2021-10-06 | 8 | 2021-10-06 | [14 empty] | 2021-11-09 | 2021-11-15 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-14203 | Fishkill | Wappingers Falls | Dutchess | 12590 | G | 8094 | Fishkill Plains | N |  | 16.82 | [13 empty] | NM | N | 58 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-09-09 | 2021-09-22 | 9 | 2021-09-22 | [8 empty] | 350 | 350 |  | 2021-09-22 | 2021-09-22 | 2022-02-17 | 2021-11-18 | 2021-11-22 |  | Y
Central Hudson |  | SunCommon | CH-14202 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7061 | Milan | N |  | 4.06 | [13 empty] | NM | N | 14 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-09-09 | 2021-09-22 | 9 | 2021-09-22 | [14 empty] | 2021-10-13 | 2021-10-13 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-14204 | Poughkeepsie | Hyde Park | Dutchess | 12538 | G | 6074 | East Park | N |  | 16.82 | [13 empty] | NM | N | 58 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-09-09 | 2021-09-23 | 10 | 2021-09-23 | [14 empty] | 2021-11-09 | 2021-11-15 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-14205 | Poughkeepsie | Rhinecliff | Dutchess | 12574 | G | 7055 | Rhinebeck | N |  | 5.51 | [13 empty] | NM | N | 19 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-09-09 | 2021-09-23 | 10 | 2021-09-23 | [14 empty] | 2022-01-14 | 2022-01-21 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-14206 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6002 | Reynolds Hill | N |  | 4.35 | [13 empty] | NM | N | 15 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-09-09 | 2021-09-23 | 10 | 2021-09-23 | [14 empty] | 2021-12-30 | 2021-12-30 |  | Y
Central Hudson |  | NY Solar 1001 LLC | CH-14210 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7054 | Rhinebeck | N |  | 2750 | [13 empty] | CDG | Y | 22 Chint Power Systems America CPS SCH125KTL-DO/US-600 (600V) | 2021-10-12 | 2021-10-26 | 10 | 2021-10-26 | 2021-10-26 | 2021-11-15 | 14 | 2022-03-30 | 2022-04-18 | 2022-07-13 | 60 | 20297.31 | 155120.05 |  | 2022-11-17 | [5 empty] | 2023-06-06 | W | Y
Central Hudson |  | Infinity Solar Systems | CH-14207 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6093 | Manchester | Y |  | 4.8 | 2.56 | [12 empty] | NM | N | 20 Enphase Energy IQ7-60-x-US (240V) 2EnphaseENCHARGE 3 | 2021-09-27 | 2021-10-11 | 10 | 2021-10-11 | [14 empty] | 2021-10-11 | 2021-10-18 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-14208 | Fishkill | Fishkill | Dutchess | 12524 | G | 8094 | Fishkill Plains | N |  | 8.99 | [13 empty] | NM | N | 31 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-09-10 | 2021-09-24 | 10 | 2021-09-24 | [14 empty] | 2021-11-17 | 2021-11-17 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-14209 | Fishkill | Hopewell Junctio | Dutchess | 12533 | G | 8095 | Fishkill Plains | N |  | 8.4 | [13 empty] | NM | N | 35 Enphase Energy IQ7-60-x-US (240V) | 2021-09-10 | 2021-09-24 | 10 | 2021-09-24 | [14 empty] | 2021-12-02 | 2021-12-10 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-14211 | Catskill | Coxsackie | Greene | 12051 | G | 1076 | Coxsackie | N |  | 9.28 | [13 empty] | NM | N | 32 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-09-10 | 2021-09-24 | 10 | 2021-09-24 | [14 empty] | 2022-04-20 | 2022-04-25 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14215 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7056 | Rhinebeck | N |  | 7.68 | [13 empty] | NM | N | 1 Delta Electronics M8-TL-US (240V) [SI1] | 2021-09-13 | 2021-09-27 | 10 | 2021-09-27 | [14 empty] | 2021-10-18 | 2021-10-27 |  | Y
Central Hudson |  | Apex Roofing LLC | CH-14212 | Newburgh | Newburgh | Orange | 12550 | G | 4015 | West Balmville | N |  | 25 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000H-US (240V) 2 SolarEdge Technologies SE10000H-US (240V) | 2021-10-28 | 2021-11-10 | 9 | 2021-11-10 | [8 empty] | 350 | 350 |  | 2022-01-05 | 2022-01-05 | 2022-03-03 | 2022-04-11 | 2022-04-19 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-14219 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6042 | Spackenkill | N |  | 10.44 | [13 empty] | NM | N | 36 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-09-13 | 2021-09-27 | 10 | 2021-09-27 | [14 empty] | 2021-10-14 | 2021-10-19 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-14218 | Poughkeepsie | Hyde Park | Dutchess | 12538 | G | 6073 | East Park | N |  | 8.12 | [13 empty] | NM | N | 28 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-09-13 | 2021-09-27 | 10 | 2021-09-27 | [14 empty] | 2021-11-19 | 2021-12-01 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-14217 | Catskill | Jewett |  | 12444 | E | 2081 | Hunter | N |  | 12.76 | [13 empty] | NM | N | 44 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-09-27 | 2021-09-27 | 0 | 2021-09-27 | [17 empty] | W
Central Hudson |  | Kasselman Solar | CH-14214 | Kingston | Grahamsville | Sullivan | 12740 | G | 3091 | Neversink | N |  | 8.725 | [13 empty] | NM | N | 25 Enphase Energy IQ7AS-66-2-US (208V) [SI1] | 2021-10-11 | 2021-10-20 | 7 | 2021-10-20 | [14 empty] | 2021-10-27 | 2021-10-27 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-14213 | Fishkill | Wappingers Falls | Dutchess | 12590 | G | 8052 | North Chelsea | Y |  | 8.41 | 7.68 | [12 empty] | NM | N | 29 Enphase Energy IQ7PLUS-72-x-US (240V) 2EnphaseEncharge 10 | 2021-10-18 | 2021-10-27 | 7 | 2021-10-27 | [14 empty] | 2021-12-01 | 2021-12-01 |  | Y
Central Hudson |  | PlugPV LLC | CH-14216 | Fishkill | Wappingers Falls | Dutchess | 12590 | G | 8014 | Forgebrook | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2021-09-13 | 2021-09-27 | 10 | 2021-09-27 | [14 empty] | 2021-11-17 | 2021-11-22 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-14221 | Poughkeepsie | Hyde Pk | Dutchess | 12538 | G | 6068 | Inwood Ave | N |  | 13.92 | [13 empty] | NM | N | 48 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-11-02 | 2021-11-16 | 10 | 2021-11-16 | [14 empty] | 2021-11-23 | 2021-12-22 |  | Y
Central Hudson |  | Solar Generation | CH-14223 | Catskill | Coxsackie | Greene | 12051 | G | 1074 | Coxsackie | N |  | 11.48 | [13 empty] | NM | N | 1 SMA America SB7.7-1SP-US-40 (240V) 1 SMA America SB3.8-1SP-US-40 (240V) | 2021-09-14 | 2021-09-28 | 10 | 2021-09-28 | [14 empty] | 2021-11-24 | 2021-11-30 |  | Y
Central Hudson |  | SunCommon | CH-14222 | Catskill | Jewett | Greene | 12444 | E | 2389 | Vinegar Hill | N | CH-14222 | 7 | [13 empty] | NM | N | 1 SMA America SB7.0-1SP-US-41 (240V) [SI1] | 2021-09-14 | 2021-09-28 | 10 | 2021-09-28 | [14 empty] | 2021-10-22 | 2021-10-28 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-14220 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7053 | Rhinebeck | N |  | 10.15 | [13 empty] | NM | N | 35 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-09-28 | 2021-10-11 | 9 | 2021-10-11 | [8 empty] | 350 | 350 |  | 2021-10-11 | 2021-10-11 | 2021-10-14 | 2021-11-17 | 2021-11-17 |  | Y
Central Hudson |  | SunCommon | CH-14224 | Kingston | Accord | Ulster | 12404 | G | 3082 | Kerhonkson | N |  | 15.2 | [13 empty] | NM | N | 2 Tesla 1538000-xx-y (240V) - may be a component of Powerwall+ (185000-XX-Y) [SI1] | 2021-09-15 | 2021-09-29 | 10 | 2021-09-29 | [14 empty] | 2021-11-15 | 2021-12-10 |  | Y
Central Hudson |  | SunCommon | CH-14225 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7054 | Rhinebeck | N |  | 11.89 | [13 empty] | NM | N | 19 Enphase Energy IQ7PLUS-72-2-US (240V) [SI1] 14 Enphase Energy IQ7PLUS-72-2-US (240V) [SI1] 2 Enphase Energy IQ7PLUS-72-2-US (240V) [SI1] 3 Enphase Energy IQ7PLUS-72-2-US (240V) [SI1] 3 Enphase Energy IQ7PLUS-72-2-US (240V) [SI1] | 2021-09-15 | 2021-09-29 | 10 | 2021-09-29 | [14 empty] | 2021-10-11 | 2021-10-15 |  | Y
Central Hudson |  | Kasselman Solar | CH-14227 | Catskill | Rensselaervle | Albany | 12147 | G | 1092 | Westerlo | N |  | 6.28 | [13 empty] | NM | N | 18 Enphase Energy IQ7A-72-2-US (240V) [SI1] | 2021-11-16 | 2021-12-02 | 10 | 2021-12-02 | [14 empty] | 2021-12-07 | 2021-12-08 |  | Y
Central Hudson |  | Kasselman Solar | CH-14226 | Kingston | Port Ewen | Ulster | 12466 | G | 1024 | East Kingston | N |  | 6.98 | [13 empty] | NM | N | 20 Enphase Energy IQ7A-72-2-US (208V) [SI1] | 2021-09-16 | 2021-09-29 | 9 | 2021-09-29 | [14 empty] | 2021-10-06 | 2021-11-05 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-14228 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 7.92 | [13 empty] | NM | N | 33 Enphase Energy IQ7-60-x-US (240V) | 2021-09-29 | 2021-10-13 | 10 | 2021-10-13 | [14 empty] | 2021-11-02 | 2021-11-08 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-14229 | Kingston | Kingston | Ulster | 12401 | G | 3021 | High Falls | N |  | 9.28 | [13 empty] | NM | N | 32 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-09-17 | 2021-10-01 | 10 | 2021-10-01 | [14 empty] | 2021-11-17 | 2021-11-17 |  | Y
Central Hudson |  | Solar Generation | CH-14230 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6095 | Manchester | N |  | 6.38 | [13 empty] | NM | N | 22 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-09-17 | 2021-10-01 | 10 | 2021-10-01 | [14 empty] | 2021-11-03 | 2021-11-03 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-14231 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6064 | Inwood Ave | N |  | 8.41 | [13 empty] | NM | N | 29 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-09-17 | 2021-10-01 | 10 | 2021-10-01 | [17 empty] | W
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14232 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6091 | Manchester | N |  | 7.7 | [13 empty] | NM | N | 1 Delta Electronics M8-TL-US (240V) [SI1] | 2021-11-05 | 2021-11-19 | 10 | 2021-11-19 | [14 empty] | 2021-12-08 | 2021-12-16 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-14238 | Newburgh | Newburgh | Orange | 12550 | G | 4095 | Bethlehem Rd | N |  | 10.73 | [13 empty] | NM | N | 37 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-09-20 | 2021-10-04 | 10 | 2021-10-04 | [14 empty] | 2021-10-22 | 2021-10-28 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-14240 | Newburgh | Newburgh | Orange | 12550 | G | 4011 | West Balmville | N |  | 8.4 | [13 empty] | NM | N | 35 Enphase Energy IQ7-60-x-US (240V) | 2021-10-04 | 2021-10-18 | 10 | 2021-10-18 | [14 empty] | 2021-11-02 | 2021-11-08 |  | Y
Central Hudson |  | PlugPV, LLC | CH-14241 | Kingston | Napanoch | Ulster | 12458 | G | 3091 | Neversink | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2021-09-20 | 2021-10-04 | 10 | 2021-10-04 | [8 empty] | 350 | 350 |  | 2021-10-08 | 2021-10-08 | 2021-11-15 | 2022-02-14 | 2022-02-18 |  | Y
Central Hudson |  | Trinity Solar Systems | CH-14236 | Newburgh | Newburgh | Orange | 12550 | G | 4012 | West Balmville | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000H-US (240V) | 2021-09-20 | 2021-10-04 | 10 | 2021-10-04 | [14 empty] | 2021-11-09 | 2021-11-15 |  | Y
Central Hudson |  | New York Power Solutions | CH-14233 | Fishkill | Fishkill | Dutchess | 12524 | G | 8014 | Forgebrook | N |  | 17.69 | [13 empty] | NM | N | 61 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-09-20 | 2021-10-04 | 10 | 2021-10-04 | [8 empty] | 350 | 350 |  | 2021-10-07 | 2021-10-07 | 2021-10-15 | 2021-12-10 | 2021-12-20 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14234 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6046 | Spackenkill | N |  | 5.76 | [13 empty] | NM | N | 1 Delta Electronics M6-TL-US (240V) [SI1] | 2021-09-20 | 2021-10-04 | 10 | 2021-10-04 | [14 empty] | 2022-02-11 | 2022-02-17 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14235 | Newburgh | Rock Tavern | Orange | 12575 | G | 4097 | Bethlehem Rd | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2021-09-20 | 2021-10-04 | 10 | 2021-10-04 | [14 empty] | 2022-02-02 | 2022-02-08 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-14239 | Newburgh | Newburgh | Orange | 12550 | G | 4053 | Union Ave | N |  | 4.35 | [13 empty] | NM | N | 15 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-09-20 | 2021-10-04 | 10 | 2021-10-04 | [14 empty] | 2021-12-08 | 2021-12-16 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14237 | Newburgh | New Windsor | Orange | 12553 | G | 4095 | Bethlehem Rd | N |  | 11.52 | [13 empty] | NM | N | 1 Delta Electronics M4-TL-US (240V) [SI1] 1 Delta Electronics M8-TL-US (240V) [SI1] | 2021-09-20 | 2021-10-04 | 10 | 2021-10-04 | [14 empty] | 2021-11-02 | 2021-11-08 |  | Y
Central Hudson |  | SunCommon | CH-14245 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7061 | Milan | N |  | 7.6 | [13 empty] | NM | N | 1 Tesla 1538000-xx-y (240V) - may be a component of Powerwall+ (185000-XX-Y) [SI1] | 2021-09-21 | 2021-10-05 | 10 | 2021-10-05 | [14 empty] | 2021-12-02 | 2021-12-07 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-14246 | Fishkill | Hopewell Junctio | Dutchess | 12533 | G | 8096 | Fishkill Plains | N |  | 9.86 | [13 empty] | NM | N | 34 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-09-21 | 2021-10-05 | 10 | 2021-10-05 | [14 empty] | 2021-11-18 | 2021-11-22 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14244 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6073 | East Park | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) [SI1] | 2021-09-21 | 2021-10-05 | 10 | 2021-10-05 | [17 empty] | W
Central Hudson |  | Kasselman Solar | CH-14249 | Catskill | Westerlo | Albany | 12193 | G | 1091 | Westerlo | N |  | 6.282 | [13 empty] | NM | N | 18 Enphase Energy IQ7A-72-2-US (240V) [SI1] | 2021-10-06 | 2021-10-19 | 9 | 2021-10-19 | [14 empty] | 2021-10-25 | 2021-11-01 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14243 | Fishkill | Wappingers Falls | Dutchess | 12590 | G | 8092 | Fishkill Plains | Y |  | 9.8 | 10 | [12 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) 1 SolarEdge Technologies SE3800H-US (240V) 2TeslaPowerwall 2 AC | 2021-11-29 | 2021-12-13 | 10 | 2021-12-13 | [14 empty] | 2021-12-20 | 2021-12-20 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14242 | Kingston | Kingston | Ulster | 12401 | G | 2094 | Hurley Ave | N |  | 5.76 | [13 empty] | NM | N | 1 Delta Electronics M6-TL-US (240V) [SI1] | 2021-09-21 | 2021-10-05 | 10 | 2021-10-05 | [14 empty] | 2022-01-11 | 2022-01-11 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14250 | Kingston | High Falls | Ulster | 12440 | G | 3022 | High Falls | N |  | 4.8 | [13 empty] | NM | N | 1 Delta Electronics M5-TL-US (240V) [SI1] | 2021-09-22 | 2021-10-06 | 10 | 2021-10-06 | [14 empty] | 2022-07-05 | 2022-07-08 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14252 | Newburgh | Campbell Hall | Orange | 10916 | G | 5051 | Maybrook | N |  | 7.68 | [13 empty] | NM | N | 1 Delta Electronics M8-TL-US (240V) [SI1] | 2021-09-22 | 2021-10-06 | 10 | 2021-10-06 | [14 empty] | 2021-11-08 | 2021-11-12 |  | Y
Central Hudson |  | Integrity Solar Solutions | CH-14251 | Newburgh | Newburgh | Orange | 12550 | G | 5001 | Marlboro | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE11400H-US (240V) | 2021-09-22 | 2021-10-06 | 10 | 2021-10-06 | [14 empty] | 2021-10-13 | 2021-10-19 |  | Y
Central Hudson |  | PlugPV, LLC | CH-14258 | Kingston | Grahamsville | Sullivan | 12740 | G | 3091 | Neversink | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2021-09-23 | 2021-10-06 | 9 | 2021-10-06 | [14 empty] | 2021-11-08 | 2021-11-12 |  | Y
Central Hudson |  | Solar Liberty Energy Systems, Inc. | CH-14257 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7062 | Milan | N |  | 200 | [13 empty] | RC | Y | 8 Chint Power Systems America CPS SCA25KTL-DO/US-208 (208V) [SI1] | 2021-12-15 | 2022-01-03 | 10 | 2022-01-03 | 2022-01-03 | 2022-01-21 | 14 | [11 empty] | 2024-09-16 | 2024-09-16 |  | Y | Y
Central Hudson |  | Solar Liberty Energy Systems, Inc. | CH-14256 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7051 | Rhinebeck | N |  | 200 | [13 empty] | RC | Y | 8 Chint Power Systems America CPS SCA25KTL-DO/US-208 (208V) [SI1] | 2022-01-03 | 2022-01-14 | 9 | 2022-01-14 | 2022-01-14 | 2022-02-04 | 15 | [11 empty] | 2024-09-05 | 2024-09-05 |  | Y | Y
Central Hudson |  | SOLAR LIBERTY ENERGY SYSTEMS | CH-14255 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7051 | Rhinebeck | N |  | 60 | [13 empty] | RC | Y | 1 Chint Power Systems America CPS SCA60KTL-DO/US-480 (480V) [SI1] | 2021-12-15 | 2022-01-03 | 10 | 2022-01-03 | 2022-01-03 | 2022-01-21 | 14 | [11 empty] | 2024-09-12 | 2024-09-12 |  | Y | Y
Central Hudson |  | Carson Power LLC | CH-14253 | Poughkeepsie | Stanfordville |  | 11937 | G | 7072 | Stanfordville | N |  | 5000 | [13 empty] | CDG | Y | 2SMASC2660UP-US | 2021-10-13 | 2021-10-26 | 9 | 2021-10-26 | 2021-10-26 | 2021-11-02 | 5 |  |  |  |  | 20800 | [9 empty] | W
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14259 | Newburgh | New Windsor | Orange | 12553 | G | 4094 | Bethlehem Rd | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2021-09-23 | 2021-10-06 | 9 | 2021-10-06 | [14 empty] | 2021-12-06 | 2021-12-09 |  | Y
Central Hudson |  | Lighthouse Solar | CH-14260 | Kingston | Saugerties | Ulster | 12477 | G | 3014 | Woodstock | N |  | 9.8 | [13 empty] | NM | N | 28 Enphase Energy IQ7A-72-2-US (240V) [SI1] | 2021-09-24 | 2021-10-06 | 8 | 2021-10-06 | [14 empty] | 2021-11-29 | 2021-11-30 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-14263 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6042 | Spackenkill | N |  | 3.48 | [13 empty] | NM | N | 12 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-09-27 | 2021-10-06 | 7 | 2021-10-06 | [14 empty] | 2021-10-15 | 2021-10-19 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14262 | Newburgh | Newburgh | Orange | 12550 | G | 4012 | West Balmville | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2021-09-27 | 2021-10-06 | 7 | 2021-10-06 | [14 empty] | 2022-06-02 | 2022-06-06 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14261 | Poughkeepsie | Stanfordville | Dutchess | 12581 | G | 7072 | Stanfordville | Y |  | 7.68 | 7.68 | [12 empty] | NM | N | 1 Delta Electronics E4-TL-US (240V) [SI1] 1 Delta Electronics M4-TL-US (240V) [SI1] 2Delta ElectronicsE4-TL-US, M4-TL-US | 2021-10-22 | 2021-11-04 | 9 | 2021-11-04 | [14 empty] | 2022-04-26 | 2022-05-03 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14273 | Fishkill | Fishkill | Dutchess | 12524 | G | 8094 | Fishkill Plains | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2021-09-28 | 2021-10-11 | 9 | 2021-10-11 | [14 empty] | 2021-11-08 | 2021-11-12 |  | Y
Central Hudson |  | JAFFER ELECTRIC INC | CH-14264 | Kingston | Kingston | Ulster | 12401 | G | 2092 | Hurley Ave | N |  | 20 | [13 empty] | NM | N | 2 Fronius International Fronius Primo 10.0-1 208-240 (208V) [SI1] | 2021-10-19 | 2021-11-02 | 10 | 2021-11-02 | [14 empty] | 2022-03-03 | 2022-03-07 |  | Y
Central Hudson |  | SunCommon | CH-14275 | Kingston | Woodstock | Ulster | 12498 | G | 3013 | Woodstock | Y |  | 7 | 5 | [12 empty] | NM | N | 1 SMA America SB7.0-1SP-US-41 (240V) [SI1] 1TeslaPowerwall 2 | 2021-10-20 | 2021-11-03 | 10 | 2021-11-03 | [14 empty] | 2021-11-16 | 2021-12-06 |  | Y
Central Hudson |  | SunCommon | CH-14274 | Kingston | Bearsville | Ulster | 12409 | G | 3012 | Woodstock | Y | CH-08229 | 12 | 10 | [12 empty] | NM | N | 1 SMA America SB7.0-1SP-US-41 (240V) [SI1] 1 SMA America SB5.0-1SP-US-41 (240V) [SI1] 2TeslaPowerwall 2 | 2021-10-21 | 2021-11-03 | 9 | 2021-11-03 | [14 empty] | 2021-12-06 | 2021-12-13 |  | Y
Central Hudson |  | New York State Solar Farm | CH-14265 | Newburgh | Wallkill | Ulster | 12589 | G | 5043 | East Walden | N |  | 6.93 | [13 empty] | NM | N | 22 SunPower SPR-X22-360-E-AC (240V) | 2021-09-27 | 2021-10-11 | 10 | 2021-10-11 | [14 empty] | 2021-10-18 | 2021-10-22 |  | Y
Central Hudson |  | Solar Generation | CH-14266 | Kingston | Saugerties | Ulster | 12477 | G | 3003 | Saugerties | N |  | 23.04 | [13 empty] | NM | N | 3 SMA America SB7700TL-US-22 (240V) | 2021-09-28 | 2021-10-11 | 9 | 2021-10-11 | [8 empty] | 350 | 350 |  | 2021-10-11 | 2021-10-11 | 2021-12-20 | 2021-12-20 | 2021-12-22 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14270 | Newburgh | Wallkill | Ulster | 12589 | G | 5043 | East Walden | Y |  | 6 | 6 | [12 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) 1SolarEdge TechnologiesSE6000H-USS3 | 2021-09-28 | 2021-10-12 | 10 | 2021-10-12 | [14 empty] | 2022-06-24 | 2022-06-30 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14272 | Poughkeepsie | Hyde Park | Dutchess | 12538 | G | 6075 | East Park | N |  | 7.68 | [13 empty] | NM | N | 1 Delta Electronics M8-TL-US (240V) [SI1] | 2021-09-28 | 2021-10-11 | 9 | 2021-10-11 | [14 empty] | 2021-12-01 | 2021-12-07 |  | Y
Central Hudson |  | Solar Generation | CH-14269 | Kingston | Kerhonkson | Ulster | 12446 | G | 3082 | Kerhonkson | N |  | 23.04 | [13 empty] | NM | N | 3 SMA America SB7700TL-US-22 (240V) | 2021-09-28 | 2021-10-11 | 9 | 2021-10-11 | [8 empty] | 350 | 350 |  | 2021-10-11 | 2021-10-11 | 2021-11-10 | 2022-01-24 | 2022-02-15 |  | Y
Central Hudson |  | Solar Generation | CH-14268 | Kingston | Kingston | Ulster | 12401 | G | 2016 | Lincoln Park | N |  | 17.8 | [13 empty] | NM | N | 51 Enphase Energy IQ7A-72-2-US (240V) [SI1] | 2021-09-28 | 2021-10-11 | 9 | 2021-10-11 | [14 empty] | 2021-12-29 | 2021-12-29 |  | Y
Central Hudson |  | Solar Generation | CH-14267 | Kingston | Kingston | Ulster | 12401 | G | 2016 | Lincoln Park | N |  | 13.96 | [13 empty] | NM | N | 40 Enphase Energy IQ7A-72-2-US (240V) [SI1] | 2021-09-28 | 2021-10-11 | 9 | 2021-10-11 | [8 empty] | 350 | 350 |  | 2021-10-11 | 2021-10-11 | 2021-12-16 | 2021-12-29 | 2021-12-29 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-14271 | Kingston | Claryville | Sullivan | 12725 | G | 3091 | Neversink | N |  | 17.98 | [13 empty] | NM | N | 62 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-09-28 | 2021-10-12 | 10 | 2021-10-12 | [8 empty] | 350 | 350 |  | 2021-10-12 | 2021-10-12 | 2021-11-24 | 2021-12-07 | 2021-12-14 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14276 | Newburgh | Goshen | Orange | 10924 | G | 5051 | Maybrook | N |  | 3.8 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3800H-US (240V) [SI1] | 2021-09-29 | 2021-10-13 | 10 | 2021-10-13 | [14 empty] | 2022-07-21 | 2022-07-26 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14277 | Kingston | High Falls | Ulster | 12440 | G | 3022 | High Falls | Y |  | 3.8 | 5 | [12 empty] | NM | N | 1 SolarEdge Technologies SE3800H-US (240V) 1TeslaAC Powerwall 2.0 | 2021-11-03 | 2021-11-17 | 10 | 2021-11-17 | [17 empty] | W
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14281 | Kingston | Boiceville | Ulster | 12412 | G | 3011 | Woodstock | Y |  | 3.84 | 5 | [12 empty] | NM | N | 1 Delta Electronics M4-TL-US (240V) [SI1] 1TeslaAC Powerwall 2.0 | 2021-10-20 | 2021-11-03 | 10 | 2021-11-03 | [17 empty] | W
Central Hudson |  | Empire Solar Solutions | CH-14280 | Newburgh | New Windsor | Orange | 12553 | G | 4046 | Union Ave | N |  | 10.15 | [13 empty] | NM | N | 35 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-10-01 | 2021-10-13 | 8 | 2021-10-13 | [14 empty] | 2021-11-18 | 2021-11-22 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-14278 | Fishkill | Garrison | Putnam | 10524 | G | 8066 | Merritt Park | N |  | 10.08 | [13 empty] | NM | N | 42 Enphase Energy IQ7-60-x-US (240V) | 2021-10-01 | 2021-10-13 | 8 | 2021-10-13 | [14 empty] | 2021-11-30 | 2021-12-07 |  | Y
Central Hudson |  | murphy solar and central air | CH-14288 | Catskill | Coxsackie | Greene | 12051 | G | 1074 | Coxsackie | N |  | 14 | [13 empty] | NM | N | 2 SMA America SB7000TL-US (240V) | 2021-10-04 | 2021-10-18 | 10 | 2021-10-18 | [17 empty] | N
Central Hudson |  | murphy solar and central air | CH-14287 | Newburgh | Newburgh | Orange | 12550 | G | 4011 | West Balmville | N |  | 7 | [13 empty] | NM | N | 1 SMA America SB7000TL-US-12 (240V) | 2021-10-04 | 2021-10-18 | 10 | 2021-10-18 | [14 empty] | 2022-11-15 | 2022-11-18 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14283 | Fishkill | Fishkill | Dutchess | 12524 | G | 8094 | Fishkill Plains | Y |  | 5.76 | 5.76 | [12 empty] | NM | N | 1 Delta Electronics E6-TL-US (240V) [SI1] 1Delta ElectronicsE6-TL-US | 2021-10-20 | 2021-11-03 | 10 | 2021-11-03 | [14 empty] | 2021-12-06 | 2021-12-13 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14282 | Newburgh | Campbell Hall | Orange | 10916 | G | 5051 | Maybrook | N |  | 7.68 | [13 empty] | NM | N | 1 Delta Electronics M8-TL-US (240V) [SI1] | 2021-10-04 | 2021-10-15 | 9 | 2021-10-15 | [14 empty] | 2022-09-09 | 2022-09-14 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-14284 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6096 | Manchester | N |  | 7.25 | [13 empty] | NM | N | 25 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-10-04 | 2021-10-18 | 10 | 2021-10-18 | [14 empty] | 2021-11-29 | 2021-11-30 |  | Y
Central Hudson |  | PlugPV LLC | CH-14286 | Poughkeepsie | Hyde Park | Dutchess | 12538 | G | 6073 | East Park | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000H-US (240V) | 2021-10-04 | 2021-10-18 | 10 | 2021-10-18 | [14 empty] | 2022-01-31 | 2022-02-03 |  | Y
Central Hudson |  | PlugPV, LLC | CH-14285 | Newburgh | Highland | Ulster | 12528 | G | 5081 | Highland | N |  | 16 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) 1 SolarEdge Technologies SE6000H-US (240V) | 2021-10-04 | 2021-10-18 | 10 | 2021-10-18 | [14 empty] | 2022-03-24 | 2022-03-25 |  | Y
Central Hudson |  | US Energy Concierge, Inc. | CH-14289 | Fishkill | Garrison | Putnam | 10524 | G | 8086 | Tioronda | N |  | 3 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3000H-US (240V) | 2021-10-18 | 2021-10-27 | 7 | 2021-10-27 | [14 empty] | 2021-12-20 | 2021-12-22 |  | Y
Central Hudson |  | PlugPV | CH-14293 | Newburgh | Newburgh | Orange | 12550 | G | 4024 | Coldenham | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2021-10-06 | 2021-10-19 | 9 | 2021-10-19 | [14 empty] | 2021-12-02 | 2021-12-20 |  | Y
Central Hudson |  | PlugPV, LLC | CH-14294 | Fishkill | Wappingers Falls | Dutchess | 12590 | G | 8023 | Knapps Corners | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2021-10-06 | 2021-10-19 | 9 | 2021-10-19 | [14 empty] | 2021-11-05 | 2021-11-09 |  | Y
Central Hudson |  | Kasselman Solar | CH-14291 | Catskill | Rensselaervle | Albany | 12147 | G | 1092 | Westerlo | N |  | 4.9 | [13 empty] | NM | N | 14 Enphase Energy IQ7A-72-2-US (240V) [SI1] | 2021-10-19 | 2021-10-27 | 6 | 2021-10-27 | [14 empty] | 2021-11-17 | 2021-11-17 |  | Y
Central Hudson |  | Lighthouse Solar | CH-14292 | Newburgh | Gardiner | Ulster | 12525 | G | 5033 | Galeville | N |  | 11.517 | [13 empty] | NM | N | 33 Enphase Energy IQ7A-72-2-US (240V) [SI1] | 2021-10-06 | 2021-10-19 | 9 | 2021-10-19 | [14 empty] | 2021-12-03 | 2021-12-10 |  | Y
Central Hudson |  | PlugPV, LLC | CH-14295 | Kingston | Kingston | Ulster | 12401 | G | 1022 | East Kingston | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000H-US (240V) | 2021-10-06 | 2021-10-19 | 9 | 2021-10-19 | [14 empty] | 2021-11-23 | 2021-11-30 |  | Y
Central Hudson |  | Kasselman Solar | CH-14290 | Kingston | Kingston | Ulster | 12401 | G | 1013 | Boulevard | N |  | 6.3 | [13 empty] | NM | N | 18 Enphase Energy IQ7A-72-2-US (240V) [SI1] | 2021-10-19 | 2021-10-27 | 6 | 2021-10-27 | [14 empty] | 2021-10-29 | 2021-11-05 |  | Y
Central Hudson |  | SunPower Direct (NY) | CH-14298 | Newburgh | Wallkill | Ulster | 12589 | G | 5041 | East Walden | N |  | 10.47 | [13 empty] | NM | N | 30 Enphase Energy IQ7AS-66-ACM-US (240V) [SI1] | 2021-10-07 | 2021-10-20 | 9 | 2021-10-20 | [14 empty] | 2021-11-17 | 2021-11-22 |  | Y
Central Hudson |  | PlugPV, LLC. | CH-14297 | Newburgh | New Windsor | Orange | 12553 | G | 4095 | Bethlehem Rd | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000H-US (208V) | 2021-10-07 | 2021-10-20 | 9 | 2021-10-20 | [14 empty] | 2021-11-10 | 2021-11-10 |  | Y
Central Hudson |  | Kasselman Solar | CH-14296 | Catskill | Athens | Greene | 12015 | G | 1074 | Coxsackie | N |  | 7.6 | [13 empty] | NM | N | 20 SolarEdge Technologies SE7600H-US (240V) | 2021-10-07 | 2021-10-19 | 8 | 2021-10-19 | [14 empty] | 2021-11-23 | 2021-12-06 |  | Y
Central Hudson |  | Kasselman Solar | CH-14299 | Catskill | Round Top | Greene | 12473 | G | 2042 | South Cairo | N |  | 10.47 | [13 empty] | NM | N | 30 Enphase Energy IQ7A-72-2-US (240V) [SI1] | 2021-10-07 | 2021-10-20 | 9 | 2021-10-20 | [14 empty] | 2021-10-25 | 2021-11-01 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-14301 | Poughkeepsie | Pine Plains | Dutchess | 12567 | G | 7091 | Pulvers Corners | N |  | 8.41 | [13 empty] | NM | N | 29 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-10-07 | 2021-10-20 | 9 | 2021-10-20 | [14 empty] | 2021-11-17 | 2021-11-17 |  | Y
Central Hudson |  | Kasselman Solar | CH-14300 | Fishkill | Hopewell Junctio | Dutchess | 12533 | G | 8096 | Fishkill Plains | N |  | 4.9 | [13 empty] | NM | N | 14 Enphase Energy IQ7A-72-2-US (240V) [SI1] | 2021-10-07 | 2021-10-20 | 9 | 2021-10-20 | [14 empty] | 2021-11-12 | 2021-11-19 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14302 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6097 | Manchester | N |  | 3.84 | [13 empty] | NM | N | 1 Delta Electronics M4-TL-US (240V) [SI1] | 2021-10-20 | 2021-11-03 | 10 | 2021-11-03 | [14 empty] | 2022-01-04 | 2022-01-04 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-14303 | Newburgh | Newburgh | Orange | 12550 | G | 4022 | Coldenham | N |  | 12.72 | [13 empty] | NM | N | 53 Enphase Energy IQ7-60-x-US (240V) | 2021-10-08 | 2021-10-20 | 8 | 2021-10-20 | [14 empty] | 2022-01-18 | 2022-01-25 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-14307 | Fishkill | Wappingers Falls | Dutchess | 12590 | G | 8091 | Fishkill Plains | N |  | 5.28 | [13 empty] | NM | N | 22 Enphase Energy IQ7-60-x-US (240V) | 2021-10-11 | 2021-10-20 | 7 | 2021-10-20 | [17 empty] | W
Central Hudson |  | Suncommon | CH-14305 | Kingston | Grahamsville | Sullivan | 12740 | G | 3095 | Grimley Rd | N |  | 6 | [13 empty] | NM | N | 1 SMA America SB6.0-1SP-US-41 (240V) [SI1] | 2021-10-11 | 2021-10-20 | 7 | 2021-10-20 | [14 empty] | 2021-12-21 | 2021-12-21 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-14306 | Newburgh | Newburgh | Orange | 12550 | G | 5001 | Marlboro | Y |  | 6.67 | 7.68 | [12 empty] | NM | N | 23 Enphase Energy IQ7PLUS-72-x-US (240V) 2EnphaseEncharge 10 | 2021-10-20 | 2021-11-03 | 10 | 2021-11-03 | [14 empty] | 2022-02-17 | 2022-02-23 |  | Y
Central Hudson |  | SunPower Direct (NY) | CH-14304 | Newburgh | Washingtonvle | Orange | 10992 | G | 5052 | Maybrook | N |  | 9.45 | [13 empty] | NM | N | 30 Enphase Energy IQ7XS-96-ACM-US (240V) [SI1] | 2021-10-11 | 2021-10-20 | 7 | 2021-10-20 | [14 empty] | 2022-02-24 | 2022-03-01 |  | Y
Central Hudson |  | PlugPV, LLC. | CH-14309 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6096 | Manchester | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2021-10-11 | 2021-10-20 | 7 | 2021-10-20 | [14 empty] | 2021-11-24 | 2021-12-16 |  | Y
Central Hudson |  | SunCommon | CH-14308 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7053 | Rhinebeck | N |  | 3.48 | [13 empty] | NM | N | 12 Enphase Energy IQ7PLUS-72-2-US (240V) [SI1] | 2021-10-12 | 2021-10-20 | 6 | 2021-10-20 | [14 empty] | 2021-11-29 | 2021-12-16 |  | Y
Central Hudson |  | Moxie Solar | CH-14316 | Newburgh | New Paltz | Ulster | 12561 | G | 5011 | Modena | N |  | 8.12 | [13 empty] | NM | N | 28 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-10-27 | 2021-11-09 | 9 | 2021-11-09 | [17 empty] | W
Central Hudson |  | SunCommon | CH-14315 | Kingston | W Hurley | Ulster | 12491 | G | 2094 | Hurley Ave | Y |  | 7.68 | 5 | [12 empty] | NM | N | 1 SMA America SB7700TL-US-22 (240V) 1TeslaGateway 2 | 2021-10-27 | 2021-11-09 | 9 | 2021-11-09 | [14 empty] | 2022-02-10 | 2022-02-18 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-14311 | Kingston | Shokan | Ulster | 12481 | G | 3011 | Woodstock | N |  | 5.8 | [13 empty] | NM | N | 20 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-10-13 | 2021-10-20 | 5 | 2021-10-20 | [14 empty] | 2021-12-22 | 2021-12-22 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-14312 | Kingston | Kingston | Ulster | 12401 | G | 111 | South Wall St | N |  | 3.77 | [13 empty] | NM | N | 13 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-10-13 | 2021-10-20 | 5 | 2021-10-20 | [14 empty] | 2022-01-04 | 2022-01-04 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-14310 | Poughkeepsie | Hyde Park | Dutchess | 12538 | G | 6074 | East Park | N |  | 17.7 | [13 empty] | NM | N | 61 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-10-13 | 2021-10-20 | 5 | 2021-10-20 | [14 empty] | 2022-01-11 | 2022-01-11 |  | Y
Central Hudson |  | SunCommon | CH-14314 | Poughkeepsie | Rhinecliff | Dutchess | 12574 | G | 7055 | Rhinebeck | Y |  | 4.13 | 5 | [12 empty] | NM | N | 14 Enphase Energy IQ7PLUS-72-2-US (240V) [SI1] 1TeslaGateway 2.0 | 2021-11-11 | 2021-11-24 | 9 | 2021-11-24 | [14 empty] | 2022-02-01 | 2022-02-07 |  | Y
Central Hudson |  | Carson Power LLC | CH-14313 | Poughkeepsie | Red Hook | Dutchess | 12572 | G | 7054 | Rhinebeck | N |  | 5000 | [13 empty] | CDG | Y | 2SMASC2660UP-US | 2021-10-27 | 2021-11-10 | 10 | 2021-11-10 | 2021-11-10 | 2021-12-02 | 14 | 2022-02-08 | 2022-03-11 | 2022-06-07 | 60 | 12527.66 | 200445 | 3166.59 | 2022-10-12 | 2023-04-10 | 2023-04-10 |  |  |  | 2023-11-13 | W | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14317 | Newburgh | Newburgh | Orange | 12550 | G | 4051 | Union Ave | N |  | 9.6 | [13 empty] | NM | N | 1 Delta Electronics M10-TL-US (240V) [SI1] | 2021-10-14 | 2021-10-27 | 9 | 2021-10-27 | [14 empty] | 2022-01-26 | 2022-02-01 |  | Y
Central Hudson |  | Trinity Solar | CH-14318 | Newburgh | Campbell Hall | Orange | 10916 | G | 5052 | Maybrook | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2021-10-27 | 2021-11-09 | 9 | 2021-11-09 | [14 empty] | 2021-12-08 | 2021-12-16 |  | Y
Central Hudson |  | PlugPV LLC | CH-14319 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6046 | Spackenkill | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2021-10-18 | 2021-10-27 | 7 | 2021-10-27 | [14 empty] | 2021-11-29 | 2021-11-30 |  | Y
Central Hudson |  | Lighthouse Solar | CH-14320 | Kingston | Accord | Ulster | 12404 | G | 3024 | High Falls | N | CH-02227 | 8.725 | [13 empty] | NM | N | 25 Enphase Energy IQ7A-72-2-US (240V) [SI1] | 2021-10-27 | 2021-11-10 | 10 | 2021-11-10 | [14 empty] | 2021-12-29 | 2021-12-29 |  | Y
Central Hudson |  | Carson Power LLC | CH-14321 | Poughkeepsie | Pine Plains | Dutchess | 12567 | G | 7395 | Pulvers Corners | N |  | 5000 | [13 empty] | S-SFA | Y | 20 Yaskawa Solectria Solar XGI 1500 250/250-600 (600V) [SI1] 2SMASC2660UP-US | 2021-11-01 | 2021-11-11 | 8 | 2021-11-11 | 2021-11-11 | 2021-11-22 | 7 | 2022-02-08 | 2022-03-11 | 2022-06-07 | 60 | 12800 | 319870.2 |  | 2022-10-12 | 2023-04-10 | 2023-04-10 |  |  |  |  | N | Y
Central Hudson |  | Empire Solar Solutions | CH-14323 | Newburgh | New Windsor | Orange | 12553 | G | 4095 | Bethlehem Rd | N | CH-14323 | 11.9 | [13 empty] | NM | N | 41 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-10-18 | 2021-10-27 | 7 | 2021-10-27 | [14 empty] | 2021-12-28 | 2021-12-28 |  | Y
Central Hudson |  | Carson Power LLC | CH-14322 | Poughkeepsie | Pine Plains | Dutchess | 12567 | G | 7395 | Pulvers Corners | N |  | 5000 | [13 empty] | S-SFA | Y | 20 Yaskawa Solectria Solar XGI 1500 250/250-600 (600V) [SI1] 2SMASC2660UP-US | 2021-11-01 | 2021-11-11 | 8 | 2021-11-11 | 2021-11-11 | 2021-11-22 | 7 | 2022-02-28 | 2022-03-11 | 2022-06-07 | 60 | 12800 | 319870.2 |  | 2022-10-12 | 2023-04-10 | 2023-04-10 |  |  |  |  | N | Y
Central Hudson |  | PlugPV LLC | CH-14279 | Newburgh | Marlboro | Ulster | 12542 | G | 5003 | Marlboro | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE11400H-US (240V) | 2021-10-19 | 2021-10-27 | 6 | 2021-10-27 | [8 empty] | 350 | 350 |  | 2021-10-29 | 2021-10-29 | 2021-11-10 | 2021-11-17 | 2021-11-22 |  | Y
Central Hudson |  | SunCommon | CH-14325 | Newburgh | New Paltz | Ulster | 12561 | G | 5031 | Galeville | Y | CH-13282 |  | 5 | [12 empty] | NM | N | 1TeslaPowerwall 2 | 2021-11-03 | 2021-11-17 | 10 | 2021-11-17 | [14 empty] | 2022-01-11 | 2022-01-11 |  | Y
Central Hudson |  | Bailey's Gap Solar | CH-14328 | Newburgh | Highland | Ulster | 12528 | G | 5081 | Highland | N |  | 1350 | [13 empty] | S-SFA | Y | 6 Yaskawa Solectria Solar XGI 1500 225-600 (600V) [SI1] | 2022-02-14 | 2022-03-01 | 10 | 2022-03-01 | 2022-03-01 | 2022-03-22 | 15 | 2022-03-30 | 2022-04-12 | 2022-07-08 | 60 | 20200 | 328375.6 |  | 2022-09-09 | 2023-03-06 | 2023-03-06 |  |  |  |  | N | Y
Central Hudson |  | New York State Solar Farm | CH-14332 | Newburgh | Highland | Ulster | 12528 | G | 5081 | Highland | N |  | 5.67 | [13 empty] | NM | N | 18 SunPower SPR-E20-327-E-AC (240V) | 2021-10-19 | 2021-11-02 | 10 | 2021-11-02 | [14 empty] | 2021-11-03 | 2021-11-09 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14329 | Fishkill | Fishkill | Dutchess | 12524 | G | 8094 | Fishkill Plains | N |  | 8.64 | [13 empty] | NM | N | 1 Delta Electronics M4-TL-US (240V) [SI1] 1 Delta Electronics M5-TL-US (240V) [SI1] | 2021-10-19 | 2021-11-01 | 9 | 2021-11-01 | [14 empty] | 2022-02-08 | 2022-02-14 |  | Y
Central Hudson |  | PlugPV LLC | CH-14324 | Fishkill | Wappingers Falls | Dutchess | 12590 | G | 8055 | North Chelsea | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2021-10-19 | 2021-10-27 | 6 | 2021-10-27 | [14 empty] | 2021-12-20 | 2021-12-20 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14326 | Poughkeepsie | Pleasant Valley | Dutchess | 12569 | G | 7024 | Tinkertown | N | CH-09210 | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000 (240V) | 2021-12-06 | 2021-12-15 | 7 | 2021-12-15 | [17 empty] | W
Central Hudson |  | Kasselman Solar, LLC | CH-14327 | Newburgh | New Paltz | Ulster | 12561 | G | 5021 | Ohioville | N |  | 6.38 | [13 empty] | NM | N | 22 Enphase Energy IQ7A-72-2-US (240V) [SI1] | 2021-10-19 | 2021-11-01 | 9 | 2021-11-01 | [14 empty] | 2021-11-04 | 2021-12-01 |  | Y
Central Hudson |  | PlugPV, LLC | CH-14333 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6046 | Spackenkill | N |  | 15.2 | 10 | [12 empty] | NM | N | 2 SolarEdge Technologies SE7600H-US (240V) 2TeslaPowerwall 2 | 2021-10-19 | 2021-11-02 | 10 | 2021-11-02 | [14 empty] | 2021-12-29 | 2021-12-29 |  | Y
Central Hudson |  | Maybrook Solar 1 LLC | CH-14330 | Newburgh | Montgomery | Orange | 12549 | G | 5054 | Maybrook | N |  | 3450 | [13 empty] | CDG | Y | 14 Yaskawa Solectria Solar XGI 1500 250/250-600 (600V) [SI1] 2SMASC2660UP-US | 2021-11-02 | 2021-11-15 | 9 | 2021-11-15 | 2021-11-15 | 2021-12-08 | 15 | 2022-02-07 | 2022-03-17 | 2022-06-13 | 60 | 12500 | 105081.25 |  | 2022-10-18 | 2023-04-13 | 2023-04-13 | 2025-11-26 |  |  |  | N | Y
Central Hudson |  | Maybrook Solar 2 LLC | CH-14331 | Newburgh | Montgomery | Orange | 12549 | G | 5054 | Maybrook | N |  | 3450 | [13 empty] | CDG | Y | 14 Yaskawa Solectria Solar XGI 1500 250/250-600 (600V) [SI1] 2SMASC2660UP-US | 2021-11-02 | 2021-11-15 | 9 | 2021-11-15 | 2021-11-15 | 2021-12-08 | 15 | 2022-02-07 | 2022-03-17 | 2022-06-13 | 60 | 12500 | 178876.75 |  | 2022-10-18 | 2023-04-13 | 2023-04-13 | 2025-11-14 |  |  |  | N | Y
Central Hudson |  | SOLANTA CORP | CH-14337 | Poughkeepsie | Lagrangeville | Dutchess | 12540 | G | 6053 | Todd Hill | N |  | 7.748 | [13 empty] | NM | N | 6 Altenergy Power System QS1 (240V) 1 Altenergy Power System YC600 (240V) | 2021-11-03 | 2021-11-17 | 10 | 2021-11-17 | [14 empty] | 2022-11-03 | 2022-11-10 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14335 | Fishkill | Beacon | Dutchess | 12508 | G | 8017 | Forgebrook | Y |  | 6 | 5 | [12 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) 1TeslaAC Powerwall 2 | 2021-11-08 | 2021-11-22 | 10 | 2021-11-22 | [14 empty] | 2022-05-19 | 2022-05-20 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-14340 | Kingston | Kingston | Ulster | 12401 | G | 2091 | Hurley Ave | N |  | 8.12 | [13 empty] | NM | N | 28 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-10-20 | 2021-11-03 | 10 | 2021-11-03 | [14 empty] | 2021-11-22 | 2021-11-23 |  | Y
Central Hudson |  | Big Shine Energy | CH-14338 | Newburgh | Newburgh | Orange | 12550 | G | 4051 | Union Ave | N |  | 487.5 | [13 empty] | NM | Y | 7 SMA America STP 62-US-41 (480V) 1 SMA America STP 50-US-41 (480V) | 2021-11-22 | 2021-11-29 | 3 | 2021-11-29 | 2021-11-29 | 2021-12-14 | 11 | [11 empty] | 2022-11-03 | 2022-11-04 |  | Y | Y
Central Hudson |  | New York State Solar Farm | CH-14344 | Poughkeepsie | Lagrangeville | Dutchess | 12540 | G | 6055 | Todd Hill | N |  | 6.98 | [13 empty] | NM | N | 20 SunPower SPR-A420-G-AC (240V) [SI1] | 2021-10-20 | 2021-11-03 | 10 | 2021-11-03 | [14 empty] | 2021-11-09 | 2021-11-15 |  | Y
Central Hudson |  | SunCommon | CH-14343 | Newburgh | Gardiner | Ulster | 12525 | G | 5031 | Galeville | N |  | 7 | [13 empty] | NM | N | 1 SMA America SB7.0-1SP-US-41 (240V) [SI1] | 2021-10-20 | 2021-11-03 | 10 | 2021-11-03 | [14 empty] | 2021-12-20 | 2021-12-20 |  | Y
Central Hudson |  | PlugPV LLC | CH-14336 | Newburgh | Newburgh | Orange | 12550 | G | 4043 | Union Ave | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2021-10-20 | 2021-11-03 | 10 | 2021-11-03 | [14 empty] | 2021-11-24 | 2021-11-30 |  | Y
Central Hudson |  | Kool Temp Heating & Cooling Inc | CH-14334 | Catskill | Palenville | Greene | 12463 | G | 2001 | North Catskill | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2021-11-03 | 2021-11-17 | 10 | 2021-11-17 | [14 empty] | 2021-12-29 | 2021-12-29 |  | Y
Central Hudson |  | SunCommon | CH-14339 | Kingston | Hurley | Ulster | 12443 | G | 2094 | Hurley Ave | N |  | 10.44 | [13 empty] | NM | N | 36 Enphase Energy IQ7PLUS-72-2-US (240V) [SI1] | 2021-11-05 | 2021-11-19 | 10 | 2021-11-19 | [14 empty] | 2021-12-20 | 2021-12-22 |  | Y
Central Hudson |  | SunCommon | CH-14341 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6043 | Spackenkill | N |  | 7.25 | [13 empty] | NM | N | 25 Enphase Energy IQ7PLUS-72-2-US (240V) [SI1] | 2021-10-20 | 2021-11-03 | 10 | 2021-11-03 | [14 empty] | 2022-02-09 | 2022-02-22 |  | Y
Central Hudson |  | Trinity Solar Systems | CH-14342 | Newburgh | Newburgh | Orange | 12550 | G | 4012 | West Balmville | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2021-10-20 | 2021-11-03 | 10 | 2021-11-03 | [14 empty] | 2021-12-16 | 2021-12-21 |  | Y
Central Hudson |  | SunCommon | CH-14345 | Poughkeepsie | Staatsburg | Dutchess | 12580 | G | 7011 | Hibernia | N |  | 6.09 | [13 empty] | NM | N | 21 Enphase Energy IQ8PLUS-72-2-US (240V) [SI1] | 2021-10-21 | 2021-11-03 | 9 | 2021-11-03 | [14 empty] | 2021-11-15 | 2021-11-22 |  | Y
Central Hudson |  | SunCommon | CH-14346 | Poughkeepsie | Milan | Dutchess | 12571 | G | 7061 | Milan | Y | CH-03675 |  | 5 | [12 empty] | NM | N | 1TeslaTesla Powerwall 2 | 2021-10-21 | 2021-11-04 | 10 | 2021-11-04 | [14 empty] | 2021-11-24 | 2021-11-24 |  | Y
Central Hudson |  | PlugPV LLC | CH-14349 | Kingston | West Camp | Ulster | 12490 | G | 3004 | Saugerties | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2021-11-03 | 2021-11-17 | 10 | 2021-11-17 | [14 empty] | 2021-12-20 | 2021-12-20 |  | Y
Central Hudson |  | PlugPV LLC | CH-14347 | Poughkeepsie | Pleasant Valley | Dutchess | 12569 | G | 6051 | Todd Hill | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE11400H-US (240V) | 2021-10-21 | 2021-11-03 | 9 | 2021-11-03 | [14 empty] | 2021-11-29 | 2021-12-06 |  | Y
Central Hudson |  | SunCommon | CH-14348 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7053 | Rhinebeck | N |  | 18.27 | [13 empty] | NM | N | 63 Enphase Energy IQ7PLUS-72-2-US (240V) [SI1] | 2021-11-03 | 2021-11-17 | 10 | 2021-11-17 | [14 empty] | 2021-11-24 | 2021-12-14 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14350 | Kingston | Ellenville | Ulster | 12428 | G | 3078 | Greenfield Rd | Y |  | 7.68 | 5 | [12 empty] | NM | N | 1 Delta Electronics M8-TL-US (240V) [SI1] 1TeslaAC Powerwall 2.0 | 2021-10-21 | 2021-11-04 | 10 | 2021-11-04 | [17 empty] | W
Central Hudson |  | Empire Solar Solutions | CH-14351 | Newburgh | New Windsor | Orange | 12553 | G | 4093 | Bethlehem Rd | N |  | 6.4 | [13 empty] | NM | N | 22 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-10-21 | 2021-11-03 | 9 | 2021-11-03 | [14 empty] | 2021-12-21 | 2021-12-22 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-14353 | Catskill | Freehold | Greene | 12431 | G | 2071 | Freehold | N |  | 16.24 | [13 empty] | NM | N | 56 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-10-22 | 2021-11-05 | 10 | 2021-11-05 | [14 empty] | 2022-04-25 | 2022-04-28 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-14352 | Newburgh | New Windsor | Orange | 12553 | G | 4044 | Union Ave | N |  | 6 | [13 empty] | NM | N | 25 Enphase Energy IQ7-60-x-US (240V) | 2021-11-04 | 2021-11-17 | 9 | 2021-11-17 | [14 empty] | 2022-02-07 | 2022-02-11 |  | Y
Central Hudson |  | SunCommon | CH-14354 | Kingston | Hurley | Ulster | 12443 | G | 2094 | Hurley Ave | N |  | 9.28 | [13 empty] | NM | N | 32 Enphase Energy IQ7PLUS-72-2-US (240V) [SI1] | 2021-10-22 | 2021-11-04 | 9 | 2021-11-04 | [14 empty] | 2021-12-20 | 2021-12-20 |  | Y
Central Hudson |  | Kasselman Solar, LLC | CH-14355 | Catskill | Coxsackie | Greene | 12051 | G | 1072 | Coxsackie | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) [SI1] | 2021-11-04 | 2021-11-17 | 9 | 2021-11-17 | [14 empty] | 2021-12-01 | 2021-12-07 |  | Y
Central Hudson |  | Kasselman Solar, LLC | CH-14356 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6056 | Todd Hill | N |  | 4.188 | [13 empty] | NM | N | 12 Enphase Energy IQ7A-72-2-US (240V) [SI1] | 2021-11-04 | 2021-11-17 | 9 | 2021-11-17 | [14 empty] | 2021-11-30 | 2021-12-07 |  | Y
Central Hudson |  | PlugPV, LLC. | CH-14357 | Newburgh | Newburgh | Orange | 12550 | G | 4014 | West Balmville | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2021-11-04 | 2021-11-17 | 9 | 2021-11-17 | [14 empty] | 2021-12-20 | 2021-12-20 |  | Y
Central Hudson |  | PlugPV, LLC. | CH-14358 | Newburgh | New Windsor | Orange | 12553 | G | 4054 | Union Ave | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2021-10-22 | 2021-11-04 | 9 | 2021-11-04 | [14 empty] | 2021-12-15 | 2021-12-21 |  | Y
Central Hudson |  | New York State Solar Farm | CH-14359 | Newburgh | Newburgh | Orange | 12550 | G | 4013 | West Balmville | N |  | 11.34 | [13 empty] | NM | N | 36 SunPower SPR-X22-360-E-AC (240V) | 2021-10-25 | 2021-11-08 | 10 | 2021-11-08 | [14 empty] | 2021-11-29 | 2021-12-06 |  | Y
Central Hudson |  | Kasselman Solar | CH-14362 | Poughkeepsie | Hopewell Junctio | Dutchess | 12533 | G | 6052 | Todd Hill | N |  | 11.866 | [13 empty] | NM | N | 34 Enphase Energy IQ7A-72-2-US (240V) [SI1] | 2021-11-08 | 2021-11-22 | 10 | 2021-11-22 | [17 empty] | W
Central Hudson |  | Sunrise Power Solutions | CH-14364 | Newburgh | Newburgh | Orange | 12550 | G | 4051 | Union Ave | N |  | 83.3 | [13 empty] | NM | N | 1 SMA America STP 33-US-41 (480V) 1 SMA America STP 50-US-41 (480V) | 2022-01-31 | 2022-02-02 | 2 | 2022-02-02 | 2022-02-02 | 2022-02-23 | 14 | [11 empty] | 2022-08-11 | 2022-08-11 |  | Y
Central Hudson |  | PlugPV, LLC | CH-14368 | Poughkeepsie | Hyde Park | Dutchess | 12538 | G | 6068 | Inwood Ave | N | CH-14368 | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2021-11-08 | 2021-11-22 | 10 | 2021-11-22 | [14 empty] | 2021-12-15 | 2021-12-21 |  | Y
Central Hudson |  | PlugPV, LLC | CH-14367 | Kingston | Tillson | Ulster | 12486 | G | 3022 | High Falls | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE11400H-US (240V) | 2021-10-25 | 2021-11-08 | 10 | 2021-11-08 | [14 empty] | 2021-11-22 | 2021-12-10 |  | Y
Central Hudson |  | Suncommon | CH-14361 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7055 | Rhinebeck | Y | CH-14361 | 16.752 | 10 | [12 empty] | NM | N | 48 Enphase Energy IQ7A-72-2-US (240V) [SI1] 2TeslaPowerwall 2 | 2021-11-08 | 2021-11-22 | 10 | 2021-11-22 | [14 empty] | 2021-12-16 | 2021-12-16 |  | Y
Central Hudson |  | PlugPV LLC | CH-14360 | Newburgh | Highland | Ulster | 12528 | G | 5083 | Highland | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2021-11-08 | 2021-11-22 | 10 | 2021-11-22 | [14 empty] | 2021-12-15 | 2021-12-21 |  | Y
Central Hudson |  | Trinity Solar Systems | CH-14363 | Newburgh | Newburgh | Orange | 12550 | G | 4023 | Coldenham | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000H-US (240V) | 2021-11-09 | 2021-11-23 | 10 | 2021-11-23 | [14 empty] | 2022-01-17 | 2022-01-24 |  | Y
Central Hudson |  | SunCommon | CH-14365 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7053 | Rhinebeck | Y | CH-04945 | 6.09 | 5 | [12 empty] | NM | N | 21 Enphase Energy IQ7PLUS-72-2-US (240V) [SI1] 1TeslaTesla Powerwall 2 | 2021-11-08 | 2021-11-22 | 10 | 2021-11-22 | [14 empty] | 2022-01-28 | 2022-02-04 |  | Y
Central Hudson |  | Kasselman Solar, LLC | CH-14366 | Newburgh | Newburgh | Orange | 12550 | G | 4014 | West Balmville | N |  | 10.121 | [13 empty] | NM | N | 29 Enphase Energy IQ7A-72-2-US (240V) [SI1] | 2021-11-08 | 2021-11-22 | 10 | 2021-11-22 | [14 empty] | 2022-04-19 | 2022-04-21 |  | Y
Central Hudson |  | New York State Solar Farm | CH-14373 | Newburgh | Walden | Orange | 12586 | G | 5041 | East Walden | N |  | 14.49 | [13 empty] | NM | N | 46 SunPower SPR-X22-360-E-AC (240V) | 2021-10-26 | 2021-11-08 | 9 | 2021-11-08 | [14 empty] | 2021-12-10 | 2021-12-21 |  | Y
Central Hudson |  | SunCommon | CH-14371 | Poughkeepsie | Staatsburg | Dutchess | 12580 | G | 7042 | Staatsburg | N | CH-01481 | 13 | [13 empty] | NM | N | 1 SMA America SB6.0-1TP-US-41 (240V) [SI1] 1 SMA America SB7.0-1TP-US-41 (240V) [SI1] | 2021-11-22 | 2021-12-08 | 10 | 2021-12-08 | [14 empty] | 2022-05-17 | 2022-05-19 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14370 | Newburgh | Highland | Ulster | 12528 | G | 5081 | Highland | N |  | 9.6 | [13 empty] | NM | N | 2 Delta Electronics M5-TL-US (240V) [SI1] | 2021-10-26 | 2021-11-08 | 9 | 2021-11-08 | [14 empty] | 2022-02-23 | 2022-02-28 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14369 | Kingston | Kingston | Ulster | 12401 | G | 2094 | Hurley Ave | N | CH-14369 | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2021-10-26 | 2021-11-08 | 9 | 2021-11-08 | [14 empty] | 2022-03-25 | 2022-03-28 |  | Y
Central Hudson |  | SunCommon | CH-14372 | Kingston | Woodstock | Ulster | 12498 | G | 3012 | Woodstock | N |  | 22.62 | [13 empty] | NM | N | 78 Enphase Energy IQ7PLUS-72-2-US (240V) [SI1] | 2021-11-22 | 2021-12-08 | 10 | 2021-12-08 | [14 empty] | 2024-05-13 | 2024-05-15 |  | Y
Central Hudson |  | New York Power Solutions | CH-14374 | Newburgh | Newburgh | Orange | 12550 | G | 5001 | Marlboro | N |  | 13.2 | [13 empty] | NM | N | 55 Enphase Energy IQ7-60-2-US (240V) [SI1] | 2021-10-26 | 2021-11-09 | 10 | 2021-11-09 | [14 empty] | 2021-12-13 | 2021-12-21 |  | Y
Central Hudson |  | MOMENTUM SOLAR | CH-14378 | Newburgh | New Windsor | Orange | 12553 | G | 4095 | Bethlehem Rd | N |  | 3.36 | [13 empty] | NM | N | 14 Enphase Energy IQ7-60-2-US (240V) [SI1] | 2021-11-09 | 2021-11-09 | 0 | 2021-11-09 | [14 empty] | 2022-01-13 | 2022-01-20 |  | Y
Central Hudson |  | Sunrise Power Solutions | CH-14377 | Newburgh | New Windsor | Orange | 12553 | G | 4054 | Union Ave | N |  | 116.6 | [13 empty] | NM | N | 2 SMA America STP 33-US-41 (480V) 1 SMA America STP 50-US-41 (480V) | 2021-12-22 | 2022-01-10 | 10 | 2022-01-10 | 2022-01-10 | 2022-01-31 | 15 | [11 empty] | 2022-10-12 | 2022-10-12 |  | Y
Central Hudson |  | Sunrise Power Solutions | CH-14376 | Newburgh | New Windsor | Orange | 12553 | G | 4042 | Union Ave | N |  | 145.8 | [13 empty] | NM | N | 1 SMA America STP 62-US-41 (480V) 1 SMA America STP 50-US-41 (480V) 1 SMA America STP 33-US-41 (480V) | 2022-01-10 | 2022-01-19 | 7 | 2022-01-19 | 2022-01-19 | 2022-02-09 | 15 | [11 empty] | 2022-08-11 | 2022-08-11 |  | Y
Central Hudson |  | Kasselman Solar, LLC | CH-14375 | Newburgh | Salisbury Mls | Orange | 12577 | G | 4095 | Bethlehem Rd | N |  | 6.631 | [13 empty] | NM | N | 19 Enphase Energy IQ7A-72-2-US (240V) [SI1] | 2021-10-27 | 2021-11-09 | 9 | 2021-11-09 | [14 empty] | 2021-12-15 | 2021-12-21 |  | Y
Central Hudson |  | Gottschalk Solutions | CH-14379 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6011 | Sand Dock | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2021-10-27 | 2021-11-10 | 10 | 2021-11-10 | [14 empty] | 2021-12-06 | 2021-12-10 |  | Y
Central Hudson |  | SunCommon | CH-14384 | Newburgh | New Paltz | Ulster | 12561 | G | 5024 | Ohioville | Y | CH-01515 |  | 10 | [12 empty] | NM | N | 2TeslaPowerwall 2 | 2021-10-28 | 2021-11-11 | 10 | 2021-11-11 | [14 empty] | 2022-01-11 | 2022-01-11 |  | Y
Central Hudson |  | Novel approaches Solar applications | CH-14381 | Kingston | Napanoch | Ulster | 12458 | G | 3071 | Honk Falls | N | CH-09181 | 12.5 | [13 empty] | NM | N | 1 Fronius USA Fronius Primo 12.5-1 (240V) | 2021-11-29 | 2021-12-08 | 7 | 2021-12-08 | [14 empty] | 2021-12-16 | 2021-12-21 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14382 | Fishkill | Stormville | Dutchess | 12582 | G | 8071 | Shenandoah | N |  | 9.8 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) 1 SolarEdge Technologies SE3800H-US (240V) | 2021-10-28 | 2021-11-10 | 9 | 2021-11-10 | [14 empty] | 2022-02-08 | 2022-02-14 |  | Y
Central Hudson |  | Kasselman Solar, LLC | CH-14383 | Catskill | Westerlo | Albany | 12193 | G | 1092 | Westerlo | Y | CH-13194 | 15.2 | [13 empty] | NM | Y | 2 SolarEdge Technologies SE7600H-US (240V) | 2021-12-20 | 2022-01-04 | 8 | 2022-01-04 | [8 empty] | 1881 | 1062.25 |  | 2022-01-13 | 2022-01-13 | 2022-03-04 | 2022-03-21 | 2022-03-23 | 2022-03-25 | Y | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14380 | Newburgh | Montgomery | Orange | 12549 | G | 5071 | Montgomery | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2021-10-28 | 2021-11-10 | 9 | 2021-11-10 | [14 empty] | 2022-02-23 | 2022-02-28 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-14387 | Newburgh | Newburgh | Orange | 12550 | G | 5004 | Marlboro | N |  | 6.09 | [13 empty] | NM | N | 21 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-10-29 | 2021-11-10 | 8 | 2021-11-10 | [14 empty] | 2021-12-28 | 2021-12-28 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14386 | Newburgh | Newburgh | Orange | 12550 | G | 4012 | West Balmville | N |  | 9.6 | [13 empty] | NM | N | 1 Delta Electronics M6-TL-US (240V) [SI1] 1 Delta Electronics M4-TL-US (240V) [SI1] | 2021-10-29 | 2021-11-10 | 8 | 2021-11-10 | [14 empty] | 2022-04-12 | 2022-04-19 |  | Y
Central Hudson |  | New York State Solar Farm | CH-14388 | Fishkill | Cold Spring | Putnam | 10516 | G | 8087 | Tioronda | N |  | 4.095 | [13 empty] | NM | N | 13 SunPower SPR-X21-350-BLK-E-AC (240V) | 2021-10-28 | 2021-11-10 | 9 | 2021-11-10 | [14 empty] | 2021-12-30 | 2021-12-30 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14390 | Newburgh | Montgomery | Orange | 12549 | G | 5073 | Montgomery | Y |  | 9.8 | 10 | [12 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) 1 SolarEdge Technologies SE3800H-US (240V) 2TeslaAC Powerwall 2.0 | 2021-10-29 | 2021-11-11 | 9 | 2021-11-11 | [14 empty] | 2022-02-03 | 2022-02-09 |  | Y
Central Hudson |  | PlugPV LLC | CH-14385 | Fishkill | Hopewell Junctio | Dutchess | 12533 | G | 8096 | Fishkill Plains | N |  | 12 | [13 empty] | NM | N | 2 SolarEdge Technologies SE6000H-US (240V) | 2021-12-09 | 2021-12-20 | 7 | 2021-12-20 | [14 empty] | 2021-12-21 | 2021-12-22 |  | Y
Central Hudson |  | Lighthouse Solar | CH-14389 | Poughkeepsie | Pleasant Valley | Dutchess | 12569 | G | 6057 | Todd Hill | N |  | 10.5 | [13 empty] | NM | N | 30 Enphase Energy IQ7A-72-2-US (240V) [SI1] | 2021-10-29 | 2021-11-10 | 8 | 2021-11-10 | [14 empty] | 2021-12-03 | 2021-12-10 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-14391 | Poughkeepsie | Poughquag | Dutchess | 12570 | G | 6055 | Todd Hill | N |  | 11.28 | [13 empty] | NM | N | 47 Enphase Energy IQ7-60-x-US (240V) | 2021-10-29 | 2021-11-11 | 9 | 2021-11-11 | [14 empty] | 2022-01-11 | 2022-01-11 |  | Y
Central Hudson |  | Seed Solar | CH-14397 | Catskill | Berne | Albany | 12023 | G | 1091 | Westerlo | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE11400H-US (240V) | 2021-11-24 | 2021-12-08 | 8 | 2021-12-08 | [14 empty] | 2021-12-15 | 2021-12-21 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14395 | Newburgh | New Paltz | Ulster | 12561 | G | 5023 | Ohioville | N |  | 9.8 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3800H-US (240V) 1 SolarEdge Technologies SE6000H-US (240V) | 2021-11-01 | 2021-11-11 | 8 | 2021-11-11 | [14 empty] | 2022-01-14 | 2022-01-21 |  | Y
Central Hudson |  | PlugPV LLC | CH-14393 | Kingston | Kingston | Ulster | 12401 | G | 1021 | East Kingston | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000H-US (240V) | 2021-11-11 | 2021-11-24 | 9 | 2021-11-24 | [14 empty] | 2021-12-30 | 2021-12-30 |  | Y
Central Hudson |  | New York State Solar Farm | CH-14400 | Catskill | Hannacroix | Greene | 12087 | G | 2061 | Freehold | N |  | 9.765 | [13 empty] | NM | N | 31 SunPower SPR-E20-327-E-AC (240V) | 2021-11-01 | 2021-11-11 | 8 | 2021-11-11 | [14 empty] | 2021-12-20 | 2021-12-20 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14396 | Newburgh | Newburgh | Orange | 12550 | G | 4053 | Union Ave | N |  | 3.8 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3800 (240V) | 2021-11-01 | 2021-11-11 | 8 | 2021-11-11 | [14 empty] | 2022-06-08 | 2022-06-13 |  | Y
Central Hudson |  | PlugPV LLC | CH-14394 | Poughkeepsie | Pleasant Valley | Dutchess | 12569 | G | 6051 | Todd Hill | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2021-11-12 | 2021-11-24 | 8 | 2021-11-24 | [14 empty] | 2021-12-22 | 2021-12-22 |  | Y
Central Hudson |  | New York State Solar Farm | CH-14398 | Kingston | Grahamsville | Sullivan | 12740 | G | 3091 | Neversink | N |  | 12.6 | [13 empty] | NM | N | 40 SunPower SPR-E20-327-E-AC (240V) | 2021-11-01 | 2021-11-11 | 8 | 2021-11-11 | [14 empty] | 2021-12-15 | 2021-12-15 |  | Y
Central Hudson |  | Solar Generation Projects, LLC | CH-14399 | Kingston | Saugerties | Ulster | 12477 | G | 3001 | Saugerties | N | [11 empty] | 666 |  |  |  | CDG | Y | G&EMModel SG198WL18666 | 2022-01-10 | 2022-01-21 | 9 | 2022-01-21 | 2022-01-21 | 2022-02-10 | 14 | 2022-03-28 | 2022-06-10 | 2022-08-23 | 51 | 3460.62 | 150161.25 | 370.68 | 2023-01-03 | [5 empty] | 2023-09-21 | W | Y
Central Hudson |  | New York State Solar Farm | CH-14405 | Fishkill | Beacon | Dutchess | 12508 | G | 8087 | Tioronda | N |  | 6.98 | [13 empty] | NM | N | 20 SunPower SPR-A420-G-AC (240V) | 2021-11-02 | 2021-11-16 | 10 | 2021-11-16 | [14 empty] | 2022-01-28 | 2022-02-02 |  | Y
Central Hudson |  | Kasselman Solar, LLC | CH-14401 | Catskill | Tannersville | Greene | 12485 | G | 2385 | Lawrenceville | N |  | 10.47 | [13 empty] | NM | N | 30 Enphase Energy IQ7A-72-2-US (240V) [SI1] | 2021-11-16 | 2021-12-01 | 9 | 2021-12-01 | [14 empty] | 2021-12-02 | 2021-12-07 |  | Y
Central Hudson |  | Lighthouse Solar | CH-14402 | Poughkeepsie | Wappingers Falls | Dutchess | 12590 | G | 6052 | Todd Hill | N |  | 13.6 | [13 empty] | NM | N | 39 Enphase Energy IQ7A-72-2-US (240V) [SI1] | 2021-11-02 | 2021-11-16 | 10 | 2021-11-16 | [14 empty] | 2021-12-07 | 2021-12-14 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-14403 | Newburgh | Maybrook | Orange | 12543 | G | 5052 | Maybrook | N |  | 5.8 | [13 empty] | NM | N | 20 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-11-02 | 2021-11-16 | 10 | 2021-11-16 | [14 empty] | 2022-01-17 | 2022-01-24 |  | Y
Central Hudson |  | SunPower Direct (NY) | CH-14404 | Newburgh | Highland | Ulster | 12528 | G | 5082 | Highland | N |  | 3.49 | [13 empty] | NM | N | 10 Enphase Energy IQ7AS-66-ACM-US (240V) [SI1] | 2021-11-02 | 2021-11-16 | 10 | 2021-11-16 | [14 empty] | 2022-07-18 | 2022-07-19 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-14412 | Newburgh | Newburgh | Orange | 12550 | G | 4051 | Union Ave | N |  | 3.84 | [13 empty] | NM | N | 16 Enphase Energy IQ7-60-x-US (240V) | 2021-11-03 | 2021-11-17 | 10 | 2021-11-17 | [14 empty] | 2021-12-08 | 2021-12-14 |  | Y
Central Hudson |  | MOMENTUM SOLAR | CH-14406 | Newburgh | Newburgh | Orange | 12550 | G | 410 | Montgomery St | N |  | 7.25 | [13 empty] | NM | N | 25 Enphase Energy IQ7PLUS-72-2-US (240V) [SI1] | 2021-11-03 | 2021-11-17 | 10 | 2021-11-17 | [14 empty] | 2022-04-19 | 2022-04-25 |  | Y
Central Hudson |  | MOMENTUM SOLAR | CH-14408 | Newburgh | Newburgh | Orange | 12550 | G | 410 | Montgomery St | N |  | 4.06 | [13 empty] | NM | N | 14 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-11-03 | 2021-11-17 | 10 | 2021-11-17 | [14 empty] | 2022-04-19 | 2022-04-25 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14410 | Newburgh | Newburgh | Orange | 12550 | G | 4014 | West Balmville | N | CH-14410 | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2021-11-03 | 2021-11-17 | 10 | 2021-11-17 | [14 empty] | 2022-03-07 | 2022-03-11 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-14414 | Newburgh | Highland |  | 12528 | G | 5012 | Modena | N |  | 10.44 | [13 empty] | NM | N | 36 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-11-03 | 2021-11-17 | 10 | 2021-11-17 | [17 empty] | W
Central Hudson |  | New York State Solar Farm | CH-14416 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6092 | Manchester | Y | CH-10846 | 4.725 | 15 | [12 empty] | NM | N | 15 SunPower SPR-X21-350-BLK-E-AC (240V) 3TESLATESLA POWERWALL 2 | 2021-11-03 | 2021-11-17 | 10 | 2021-11-17 | [14 empty] | 2021-12-22 | 2021-12-22 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-14413 | Newburgh | Newburgh | Orange | 12550 | G | 4023 | Coldenham | N | CH-14413 | 5.22 | [13 empty] | NM | N | 18 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-11-03 | 2021-11-17 | 10 | 2021-11-17 | [14 empty] | 2022-02-02 | 2022-02-07 |  | Y
Central Hudson |  | New York State Solar Farm | CH-14407 | Poughkeepsie | Stanfordville | Dutchess | 12581 | G | 7072 | Stanfordville | N |  | 2.792 | [13 empty] | NM | N | 8 SunPower SPR-A400-BLK-G-AC (240V) [SI1] | 2021-11-03 | 2021-11-17 | 10 | 2021-11-17 | [14 empty] | 2021-12-03 | 2021-12-10 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-14411 | Kingston | Saugerties | Ulster | 12477 | G | 3001 | Saugerties | N |  | 8.99 | [13 empty] | NM | N | 31 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-11-03 | 2021-11-17 | 10 | 2021-11-17 | [14 empty] | 2022-01-11 | 2022-01-11 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-14409 | Newburgh | Montgomery | Orange | 12549 | G | 5071 | Montgomery | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2021-11-03 | 2021-11-17 | 10 | 2021-11-17 | [14 empty] | 2021-12-30 | 2021-12-30 |  | Y
Central Hudson |  | Kasselman Solar, LLC | CH-14415 | Kingston | Bloomington | Ulster | 12411 | G | 1011 | Boulevard | N |  | 4.537 | [13 empty] | NM | N | 13 Enphase Energy IQ7A-72-2-US (240V) [SI1] | 2021-11-03 | 2021-11-17 | 10 | 2021-11-17 | [14 empty] | 2021-11-29 | 2021-12-10 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-14424 | Fishkill | Wappingers Falls | Dutchess | 12590 | G | 8052 | North Chelsea | N |  | 6.09 | [13 empty] | NM | N | 21 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-11-04 | 2021-11-17 | 9 | 2021-11-17 | [14 empty] | 2021-11-23 | 2021-11-30 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14421 | Fishkill | Poughkeepsie | Dutchess | 12603 | G | 8024 | Knapps Corners | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2021-11-04 | 2021-11-17 | 9 | 2021-11-17 | [14 empty] | 2022-02-11 | 2022-02-17 |  | Y
Central Hudson |  | SunPower Direct (NY) | CH-14419 | Fishkill | Beacon | Dutchess | 12508 | G | 8087 | Tioronda | N |  | 5.584 | [13 empty] | NM | N | 16 SunPower SPR-A420-G-AC (240V) | 2021-11-17 | 2021-12-01 | 8 | 2021-12-01 | [14 empty] | 2022-02-07 | 2022-02-14 |  | Y
Central Hudson |  | PlugPV LLC | CH-14420 | Fishkill | Poughkeepsie | Dutchess | 12601 | G | 8021 | Knapps Corners | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000H-US (240V) | 2021-11-04 | 2021-11-17 | 9 | 2021-11-17 | [17 empty] | W
Central Hudson |  | Empire Solar Solutions | CH-14418 | Newburgh | Milton | Ulster | 12547 | G | 5083 | Highland | N |  | 12.76 | [13 empty] | NM | N | 44 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-11-04 | 2021-11-17 | 9 | 2021-11-17 | [14 empty] | 2022-01-06 | 2022-01-06 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14417 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6003 | Reynolds Hill | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2021-11-04 | 2021-11-17 | 9 | 2021-11-17 | [14 empty] | 2022-06-28 | 2022-07-05 |  | Y
Central Hudson |  | New York State Solar Farm | CH-14423 | Newburgh | Newburgh | Orange | 12550 | G | 4013 | West Balmville | N |  | 9.135 | [13 empty] | NM | N | 29 SunPower SPR-X22-360-E-AC (240V) | 2021-11-04 | 2021-11-17 | 9 | 2021-11-17 | [14 empty] | 2021-12-01 | 2021-12-07 |  | Y
Central Hudson |  | Lighthouse Solar | CH-14422 | Kingston | Olivebridge | Ulster | 12461 | G | 2094 | Hurley Ave | Y |  | 8.376 | 6.4 | [12 empty] | NM | N | 24 Enphase Energy IQ7A-72-2-US (240V) [SI1] 1EnphaseEncharge 102EnphaseEncharge 3 | 2021-12-02 | 2021-12-03 | 1 | 2021-12-03 | [14 empty] | 2021-12-20 | 2021-12-22 |  | Y
Central Hudson |  | PLUGPV LLC | CH-14427 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6096 | Manchester | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2021-11-16 | 2021-12-01 | 9 | 2021-12-01 | [14 empty] | 2021-12-20 | 2021-12-20 |  | Y
Central Hudson |  | Kasselman Solar | CH-14425 | Catskill | Catskill | Greene | 12414 | G | 2001 | North Catskill | N |  | 5.24 | [13 empty] | NM | N | 15 Enphase Energy IQ7A-72-2-US (240V) [SI1] | 2021-11-05 | 2021-11-17 | 8 | 2021-11-17 | [14 empty] | 2021-12-28 | 2021-12-28 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-14426 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6097 | Manchester | N |  | 8.88 | [13 empty] | NM | N | 37 Enphase Energy IQ7-60-x-US (240V) | 2021-11-05 | 2021-11-17 | 8 | 2021-11-17 | [14 empty] | 2021-12-29 | 2021-12-29 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-14428 | Fishkill | Wappingers Falls | Dutchess | 12590 | G | 8052 | North Chelsea | N |  | 2.9 | [13 empty] | NM | N | 10 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-11-05 | 2021-11-19 | 10 | 2021-11-19 | [14 empty] | 2021-12-29 | 2021-12-29 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14431 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6043 | Spackenkill | N |  | 9.6 | [13 empty] | NM | N | 1 Delta Electronics M10-TL-US (240V) [SI1] | 2021-11-08 | 2021-11-22 | 10 | 2021-11-22 | [14 empty] | 2022-02-22 | 2022-02-28 |  | Y
Central Hudson |  | Solar Generation | CH-14429 | Kingston | Woodstock | Ulster | 12498 | G | 3014 | Woodstock | N | CH-08286 | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2022-02-16 | 2022-03-01 | 8 | 2022-03-01 | [14 empty] | 2022-03-24 | 2022-03-25 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14435 | Newburgh | Newburgh | Orange | 12550 | G | 4042 | Union Ave | N |  | 3.8 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3800H-US (240V) | 2021-11-08 | 2021-11-22 | 10 | 2021-11-22 | [14 empty] | 2022-01-04 | 2022-01-04 |  | Y
Central Hudson |  | PlugPV LLC | CH-14430 | Poughkeepsie | Wappingers Falls | Dutchess | 12590 | G | 6052 | Todd Hill | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2021-11-22 | 2021-12-08 | 10 | 2021-12-08 | [14 empty] | 2022-01-13 | 2022-01-20 |  | Y
Central Hudson |  | PlugPV, LLC. | CH-14432 | Newburgh | Newburgh | Orange | 12550 | G | 4045 | Union Ave | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2021-11-08 | 2021-11-22 | 10 | 2021-11-22 | [14 empty] | 2021-12-28 | 2021-12-28 |  | Y
Central Hudson |  | PlugPV, LLC. | CH-14436 | Newburgh | Newburgh | Orange | 12550 | G | 4045 | Union Ave | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2021-11-08 | 2021-11-22 | 10 | 2021-11-22 | [14 empty] | 2021-12-20 | 2021-12-22 |  | Y
Central Hudson |  | PlugPV, LLC. | CH-14433 | Newburgh | Newburgh | Orange | 12550 | G | 4045 | Union Ave | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2021-11-08 | 2021-11-22 | 10 | 2021-11-22 | [14 empty] | 2021-12-30 | 2021-12-30 |  | Y
Central Hudson |  | PLUGPV LLC | CH-14434 | Kingston | Kingston | Ulster | 12401 | G | 1003 | Jansen Ave | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000H-US (240V) | 2021-11-22 | 2021-12-08 | 10 | 2021-12-08 | [14 empty] | 2021-12-20 | 2021-12-22 |  | Y
Central Hudson |  | MOMENTUM SOLAR | CH-14443 | Newburgh | Newburgh | Orange | 12550 | G | 4011 | West Balmville | N |  | 17.28 | [13 empty] | NM | N | 72 Enphase Energy IQ7-60-x-US (240V) | 2021-11-09 | 2021-11-22 | 9 | 2021-11-22 | [14 empty] | 2022-01-13 | 2022-01-28 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14441 | Poughkeepsie | Hyde Park | Dutchess | 12538 | G | 6068 | Inwood Ave | N |  | 7.68 | [13 empty] | NM | N | 1 Delta Electronics M8-TL-US (240V) [SI1] | 2021-11-09 | 2021-11-23 | 10 | 2021-11-23 | [14 empty] | 2022-01-05 | 2022-01-05 |  | Y
Central Hudson |  | PlugPV LLC | CH-14444 | Kingston | Grahamsville | Sullivan | 12740 | G | 3091 | Neversink | N |  | 3.8 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3800H-US (240V) | 2021-11-09 | 2021-11-22 | 9 | 2021-11-22 | [14 empty] | 2021-12-28 | 2021-12-28 |  | Y
Central Hudson |  | SunCommon | CH-14439 | Poughkeepsie | Tivoli | Dutchess | 12583 | G | 7062 | Milan | Y | CH-13466 | 10 | [13 empty] | NM | N | 1 SMA America SB5.0-1SP-US-41 (240V) [SI1] 1 SMA America SB5.0-1SP-US-41 (240V) [SI1] | 2022-03-04 | 2022-03-16 | 8 | 2022-03-16 | [14 empty] | 2022-05-09 | 2022-05-09 |  | Y
Central Hudson |  | SunCommon | CH-14440 | Catskill | Cairo | Greene | 12413 | G | 2041 | South Cairo | Y |  | 5.22 | 5 | [12 empty] | NM | N | 18 Enphase Energy IQ7PLUS-72-2-US (240V) [SI1] 1TeslaPowerwall 2 | 2021-11-09 | 2021-11-22 | 9 | 2021-11-22 | [14 empty] | 2022-01-04 | 2022-01-04 |  | Y
Central Hudson |  | PlugPV, LLC. | CH-14438 | Newburgh | Newburgh | Orange | 12550 | G | 4045 | Union Ave | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2021-11-09 | 2021-11-22 | 9 | 2021-11-22 | [14 empty] | 2021-12-20 | 2021-12-22 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14437 | Newburgh | Clintondale | Ulster | 12515 | G | 5081 | Highland | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) [SI1] | 2021-11-09 | 2021-11-22 | 9 | 2021-11-22 | [14 empty] | 2022-04-05 | 2022-04-08 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-14442 | Newburgh | Wallkill | Ulster | 12589 | G | 5041 | East Walden | N |  | 7.54 | [13 empty] | NM | N | 26 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-11-09 | 2021-11-22 | 9 | 2021-11-22 | [14 empty] | 2021-12-15 | 2021-12-15 |  | Y
Central Hudson |  | Gottschalk Solutions | CH-14447 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6046 | Spackenkill | N |  | 13.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) 1 SolarEdge Technologies SE6000H-US (240V) | 2021-11-10 | 2021-11-24 | 10 | 2021-11-24 | [14 empty] | 2021-12-22 | 2021-12-22 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14448 | Kingston | Kingston | Ulster | 12401 | G | 2092 | Hurley Ave | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2021-11-10 | 2021-11-24 | 10 | 2021-11-24 | [14 empty] | 2022-02-16 | 2022-02-22 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-14446 | Kingston | Kingston | Ulster | 12401 | G | 2013 | Lincoln Park | N |  | 7.2 | [13 empty] | NM | N | 30 Enphase Energy IQ7-60-x-US (240V) | 2021-11-10 | 2021-11-24 | 10 | 2021-11-24 | [14 empty] | 2022-03-07 | 2022-03-08 |  | Y
Central Hudson |  | PlugPV LLC | CH-14449 | Newburgh | New Windsor | Orange | 12553 | G | 4095 | Bethlehem Rd | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2021-11-24 | 2021-12-08 | 8 | 2021-12-08 | [14 empty] | 2021-12-29 | 2021-12-29 |  | Y
Central Hudson |  | SunCommon | CH-14450 | Kingston | Stone Ridge | Ulster | 12484 | G | 3023 | High Falls | Y | CH-07692 |  | 10 | [12 empty] | NM | N | 2TeslaPowerwall 2 | 2021-11-24 | 2021-12-08 | 8 | 2021-12-08 | [14 empty] | 2022-01-12 | 2022-01-19 |  | Y
Central Hudson |  | Kasselman Solar, LLC | CH-14452 | Poughkeepsie | Salt Point | Dutchess | 12578 | G | 7011 | Hibernia | Y |  | 6 | 6 | [12 empty] | NM | N | 1 SolarEdge Technologies SE6000x (240V) [SI1] 1SolarEdgeSE6000H-US (PRISM) | 2021-11-24 | 2021-12-08 | 8 | 2021-12-08 | [14 empty] | 2021-12-15 | 2021-12-21 |  | Y
Central Hudson |  | Solar Generation | CH-14451 | Catskill | Coxsackie | Greene | 12051 | G | 1072 | Coxsackie | N |  | 5.8 | [13 empty] | NM | N | 20 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-11-11 | 2021-11-24 | 9 | 2021-11-24 | [14 empty] | 2021-12-28 | 2021-12-28 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-14455 | Fishkill | Beacon | Dutchess | 12508 | G | 8013 | Forgebrook | N |  | 6.72 | [13 empty] | NM | N | 28 Enphase Energy IQ7-60-x-US (240V) | 2021-11-12 | 2021-11-24 | 8 | 2021-11-24 | [14 empty] | 2022-01-12 | 2022-01-19 |  | Y
Central Hudson |  | Kasselman Solar, LLC | CH-14457 | Fishkill | Beacon | Dutchess | 12508 | G | 8087 | Tioronda | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) [SI1] | 2021-11-12 | 2021-11-24 | 8 | 2021-11-24 | [14 empty] | 2023-09-28 | 2023-09-29 |  | Y
Central Hudson |  | New York State Solar Farm | CH-14453 | Catskill | Leeds | Greene | 12451 | G | 2006 | North Catskill | N |  | 9.074 | [13 empty] | NM | N | 26 SunPower SPR-A400-G-AC (240V) [SI1] | 2021-11-24 | 2021-11-24 | 0 | 2021-11-24 | [14 empty] | 2022-01-28 | 2022-02-16 |  | Y
Central Hudson |  | PlugPV LLC | CH-14454 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6092 | Manchester | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) 1TeslaPowerwall 2 | 2021-12-03 | 2021-12-15 | 8 | 2021-12-15 | [17 empty] | W
Central Hudson |  | PlugPV, LLC. | CH-14456 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6056 | Todd Hill | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2021-11-12 | 2021-11-24 | 8 | 2021-11-24 | [14 empty] | 2022-01-20 | 2022-01-27 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-14458 | Fishkill | Fishkill | Dutchess | 12524 | G | 8012 | Forgebrook | Y | CH-12849 | 1.89 | [13 empty] | NM | N | 6 Enphase Energy IQ7X-96-x-US (240V) | 2021-11-24 | 2021-12-08 | 8 | 2021-12-08 | [14 empty] | 2022-02-17 | 2022-02-23 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-14459 | Fishkill | Beacon | Dutchess | 12508 | G | 8015 | Forgebrook | N |  | 3.36 | [13 empty] | NM | N | 14 Enphase Energy IQ7-60-x-US (240V) | 2021-11-12 | 2021-11-24 | 8 | 2021-11-24 | [14 empty] | 2022-03-25 | 2022-03-28 |  | Y
Central Hudson |  | Kasselman Solar, LLC | CH-14460 | Fishkill | Hopewell Junctio | Dutchess | 12533 | G | 8071 | Shenandoah | N | CH-03531 | 15.12 | [13 empty] | NM | N | 63 Enphase Energy IQ7-60-x-US (240V) | 2021-11-29 | 2021-12-13 | 10 | 2021-12-13 | [14 empty] | 2022-02-09 | 2022-02-15 |  | Y
Central Hudson |  | New York State Solar Farm | CH-14461 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6056 | Todd Hill | N |  | 10.395 | [13 empty] | NM | N | 33 SunPower SPR-X22-360-E-AC (240V) | 2021-11-15 | 2021-12-01 | 10 | 2021-12-01 | [14 empty] | 2021-12-03 | 2021-12-10 |  | Y
Central Hudson |  | SunPower Direct (NY) | CH-14468 | Newburgh | Montgomery | Orange | 12549 | G | 5072 | Montgomery | N |  | 7.678 | [13 empty] | NM | N | 22 SunPower SPR-A410-G-AC (240V) | 2021-12-09 | 2021-12-20 | 7 | 2021-12-20 | [14 empty] | 2022-01-27 | 2022-02-02 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-14470 | Newburgh | Campbell Hall | Orange | 10916 | G | 5051 | Maybrook | N |  | 6.67 | [13 empty] | NM | N | 23 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-11-15 | 2021-12-01 | 10 | 2021-12-01 | [14 empty] | 2021-12-02 | 2021-12-16 |  | Y
Central Hudson |  | Hudson River Solar | CH-14467 | Catskill | Cairo | Greene | 12413 | G | 2041 | South Cairo | N |  | 23.04 | [13 empty] | NM | N | 3 SMA America SB7.7-1SP-US-41 (240V) [SI1] | 2021-11-15 | 2021-12-01 | 10 | 2021-12-01 | [14 empty] | 2021-12-30 | 2021-12-30 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14464 | Kingston | Kingston | Ulster | 12401 | G | 122 | Converse St | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2021-12-02 | 2021-12-15 | 9 | 2021-12-15 | [14 empty] | 2022-05-13 | 2022-05-16 |  | Y
Central Hudson |  | Solar Generation | CH-14466 | Kingston | Woodstock | Ulster | 12498 | G | 3014 | Woodstock | N |  | 7.25 | [13 empty] | NM | N | 25 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-11-15 | 2021-12-01 | 10 | 2021-12-01 | [14 empty] | 2022-02-02 | 2022-02-09 |  | Y
Central Hudson |  | PLUGPV LLC | CH-14462 | Fishkill | Wappingers Falls | Dutchess | 12590 | G | 8091 | Fishkill Plains | N |  | 12 | [13 empty] | NM | N | 2 SolarEdge Technologies SE6000H-US (240V) | 2021-11-30 | 2021-12-14 | 10 | 2021-12-14 | [14 empty] | 2022-01-31 | 2022-02-04 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14463 | Kingston | Ellenville | Ulster | 12428 | G | 3076 | Greenfield Rd | Y |  | 5.76 | 5.76 | [12 empty] | NM | N | 1 Delta Electronics E6-TL-US (240V) [SI1] 1Delta ElectronicsE6-TL-US | 2021-12-01 | 2021-12-15 | 10 | 2021-12-15 | [14 empty] | 2022-04-01 | 2022-04-06 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14465 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7052 | Rhinebeck | Y |  | 6 | 6 | [12 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) 1SolarEdge TechnologiesSE6000H-USS3 | 2021-12-17 | 2021-12-30 | 7 | 2021-12-30 | [14 empty] | 2022-03-23 | 2022-04-01 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-14469 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6003 | Reynolds Hill | N |  | 7.83 | [13 empty] | NM | N | 27 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-11-15 | 2021-12-01 | 10 | 2021-12-01 | [14 empty] | 2022-03-21 | 2022-03-23 |  | Y
Central Hudson |  | SunCommon | CH-14472 | Catskill | Acra | Greene | 12405 | G | 2041 | South Cairo | N |  | 40 | [13 empty] | RC | Y | 4 SolarEdge Technologies SE10000H-US (240V) | 2021-12-02 | 2021-12-15 | 9 | 2021-12-15 | [8 empty] | 1690 | 1915.61 |  | 2022-01-05 | 2022-01-05 | 2022-03-04 | 2022-03-24 | 2022-03-25 | 2022-03-28 | Y | Y
Central Hudson |  | Paradise Energy Solutions | CH-14471 | Poughkeepsie | Tivoli | Dutchess | 12583 | G | 7054 | Rhinebeck | N | CH-02828 | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) [SI1] | 2021-12-01 | 2021-12-09 | 6 | 2021-12-09 | [14 empty] | 2022-01-26 | 2022-02-01 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-14473 | Newburgh | Newburgh | Orange | 12550 | G | 403 | Montgomery St | N |  | 3.84 | [13 empty] | NM | N | 16 Enphase Energy IQ7-60-x-US (240V) | 2021-11-16 | 2021-12-01 | 9 | 2021-12-01 | [14 empty] | 2022-11-21 | 2022-11-28 |  | Y
Central Hudson |  | MOMENTUM SOLAR | CH-14474 | Newburgh | Newburgh | Orange | 12550 | G | 4015 | West Balmville | N |  | 7.25 | [13 empty] | NM | N | 25 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-11-16 | 2021-12-01 | 9 | 2021-12-01 | [17 empty] | W
Central Hudson |  | MOMENTUM SOLAR | CH-14475 | Newburgh | Newburgh | Orange | 12550 | G | 4015 | West Balmville | N |  | 1.74 | [13 empty] | NM | N | 6 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-11-16 | 2021-12-01 | 9 | 2021-12-01 | [17 empty] | W
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14477 | Fishkill | Hopewell Junctio |  | 12533 | G | 8091 | Fishkill Plains | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2021-11-17 | 2021-12-01 | 8 | 2021-12-01 | [17 empty] | W
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14476 | Poughkeepsie | Pleasant Valley | Dutchess | 12569 | G | 6051 | Todd Hill | N | CH-12507 | 3.84 | [13 empty] | NM | N | 1 Delta Electronics M4-TL-US (240V) [SI1] | 2021-11-17 | 2021-12-01 | 8 | 2021-12-01 | [17 empty] | W
Central Hudson |  | PlugPV, LLC. | CH-14481 | Newburgh | Walden | Orange | 12586 | G | 5041 | East Walden | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2021-11-17 | 2021-12-01 | 8 | 2021-12-01 | [14 empty] | 2022-02-09 | 2022-02-25 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-14480 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 5.22 | [13 empty] | NM | N | 18 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-11-17 | 2021-12-01 | 8 | 2021-12-01 | [14 empty] | 2022-01-13 | 2022-01-13 |  | Y
Central Hudson |  | Delaware River Solar | CH-14478 | Kingston | Neversink |  | 12765 | G | 3091 | Neversink | N |  | 5000 | [13 empty] | CDG | Y | 2SungrowSG 3425 UD-MV | 2022-01-11 | 2022-01-21 | 8 | 2022-01-21 | 2022-01-21 | 2022-01-31 | 6 |  |  |  |  | 19070 | [9 empty] | W
Central Hudson |  | Delaware River Solar | CH-14479 | Kingston | Neversink | Sullivan | 12765 | G | 3091 | Neversink | N |  | 3900 | [13 empty] | CDG | Y | 2SungrowSG 3425 UD-MV | 2022-01-11 | 2022-01-21 | 8 | 2022-01-21 | 2022-01-21 | 2022-02-11 | 15 | 2022-05-04 | 2022-08-22 | 2022-11-15 | 60 | 21250.02 | 1835443.7 | [7 empty] | 2023-06-07 | W | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14487 | Newburgh | New Windsor | Orange | 12553 | G | 4046 | Union Ave | N |  | 3.84 | [13 empty] | NM | N | 1 Delta Electronics M4-TL-US (240V) [SI1] | 2021-11-18 | 2021-12-01 | 7 | 2021-12-01 | [14 empty] | 2022-05-05 | 2022-05-10 |  | Y
Central Hudson |  | SunPower Direct (NY) | CH-14485 | Fishkill | Cold Spring | Putnam | 10516 | G | 8063 | Merritt Park | N |  | 2.835 | [13 empty] | NM | N | 9 Enphase Energy IQ7XS-96-ACM-US (240V) [SI1] | 2021-12-13 | 2021-12-21 | 6 | 2021-12-21 | [14 empty] | 2022-08-22 | 2022-08-24 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14483 | Kingston | Kingston | Ulster | 12401 | G | 1014 | Boulevard | N |  | 3.84 | [13 empty] | NM | N | 1 Delta Electronics M4-TL-US (240V) [SI1] | 2021-12-02 | 2021-12-15 | 9 | 2021-12-15 | [14 empty] | 2022-01-24 | 2022-01-31 |  | Y
Central Hudson |  | New York State Solar Farm | CH-14486 | Newburgh | New Windsor | Orange | 12553 | G | 4095 | Bethlehem Rd | N |  | 7.56 | [13 empty] | NM | N | 24 SunPower SPR-X22-360-E-AC (240V) | 2021-11-18 | 2021-12-01 | 7 | 2021-12-01 | [14 empty] | 2022-01-18 | 2022-01-26 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-14484 | Newburgh | New Windsor | Orange | 12553 | G | 4094 | Bethlehem Rd | N |  | 9.28 | [13 empty] | NM | N | 32 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-11-18 | 2021-12-01 | 7 | 2021-12-01 | [14 empty] | 2021-12-30 | 2021-12-30 |  | Y
Central Hudson |  | Suncommon | CH-14488 | Kingston | Saugerties | Ulster | 12477 | G | 3003 | Saugerties | Y | CH-14873 | 7.68 | 5 | [12 empty] | NM | N | 1 SMA America SB7.7-1SP-US-41 (240V) [SI1] 1TeslaPowerwall 2 | 2021-11-18 | 2021-12-01 | 7 | 2021-12-01 | [14 empty] | 2021-12-03 | 2021-12-16 |  | Y
Central Hudson |  | MOMENTUM SOLAR | CH-14491 | Fishkill | Beacon | Dutchess | 12508 | G | 8017 | Forgebrook | N |  | 3.6 | [13 empty] | NM | N | 15 Enphase Energy IQ7-60-x-US (240V) | 2021-11-19 | 2021-12-07 | 10 | 2021-12-07 | [14 empty] | 2022-01-13 | 2022-01-20 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-14495 | Newburgh | New Windsor | Orange | 12553 | G | 4095 | Bethlehem Rd | N |  | 7.54 | [13 empty] | NM | N | 26 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-11-19 | 2021-12-07 | 10 | 2021-12-07 | [14 empty] | 2022-02-18 | 2022-02-25 |  | Y
Central Hudson |  | PlugPV LLC | CH-14490 | Poughkeepsie | Salt Point | Dutchess | 12578 | G | 7011 | Hibernia | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2021-11-19 | 2021-12-07 | 10 | 2021-12-07 | [14 empty] | 2022-01-11 | 2022-01-11 |  | Y
Central Hudson |  | SunCommon | CH-14496 | Catskill | Athens | Greene | 12015 | G | 2006 | North Catskill | N |  | 12 | [13 empty] | NM | N | 1 SMA America SB6.0-1SP-US-41 (240V) [SI1] 1 SMA America SB6.0-1SP-US-41 (240V) [SI1] | 2021-11-19 | 2021-12-07 | 10 | 2021-12-07 | [14 empty] | 2022-01-27 | 2022-02-15 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-14494 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6073 | East Park | N |  | 3.6 | [13 empty] | NM | N | 15 Enphase Energy IQ7-60-x-US (240V) | 2021-12-06 | 2021-12-15 | 7 | 2021-12-15 | [14 empty] | 2022-02-02 | 2022-02-10 |  | Y
Central Hudson |  | PlugPV, LLC | CH-14493 | Newburgh | New Windsor | Orange | 12553 | G | 4054 | Union Ave | Y |  | 7.6 | 5 | [12 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) 1TeslaPowerwall 2 | 2021-12-07 | 2021-12-20 | 9 | 2021-12-20 | [14 empty] | 2022-07-20 | 2022-07-21 |  | Y
Central Hudson |  | PlugPV, LLC. | CH-14492 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6092 | Manchester | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2021-11-19 | 2021-12-07 | 10 | 2021-12-07 | [14 empty] | 2022-01-04 | 2022-01-04 |  | Y
Central Hudson |  | PlugPV, LLC. | CH-14498 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6044 | Spackenkill | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2021-11-19 | 2021-12-07 | 10 | 2021-12-07 | [14 empty] | 2021-12-20 | 2021-12-22 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-14497 | Newburgh | New Windsor | Orange | 12553 | G | 4094 | Bethlehem Rd | N |  | 11.02 | [13 empty] | NM | N | 38 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-11-19 | 2021-12-07 | 10 | 2021-12-07 | [14 empty] | 2021-12-30 | 2021-12-30 |  | Y
Central Hudson |  | New york Power Solutions | CH-14499 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6002 | Reynolds Hill | N |  | 8.12 | [13 empty] | NM | N | 28 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-12-07 | 2021-12-20 | 9 | 2021-12-20 | [14 empty] | 2022-04-04 | 2022-04-06 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-14504 | Poughkeepsie | Hyde Park | Dutchess | 12538 | G | 6073 | East Park | N |  | 5.76 | [13 empty] | NM | N | 24 Enphase Energy IQ7-60-x-US (240V) | 2021-12-07 | 2021-12-20 | 9 | 2021-12-20 | [14 empty] | 2022-02-22 | 2022-02-28 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-14501 | Poughkeepsie | Lagrangeville | Dutchess | 12540 | G | 6052 | Todd Hill | N |  | 9.36 | [13 empty] | NM | N | 39 Enphase Energy IQ7-60-x-US (240V) | 2021-11-22 | 2021-12-08 | 10 | 2021-12-08 | [17 empty] | W
Central Hudson |  | PlugPV LLC | CH-14500 | Kingston | Kingston | Ulster | 12401 | G | 1011 | Boulevard | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000H-US (240V) | 2021-11-22 | 2021-12-08 | 10 | 2021-12-08 | [17 empty] | W
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14505 | Catskill | Haines Falls | Greene | 12436 | G | 2385 | Lawrenceville | N |  | 3.8 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3800H-US (240V) | 2021-11-22 | 2021-12-08 | 10 | 2021-12-08 | [14 empty] | 2022-08-30 | 2022-09-02 |  | Y
Central Hudson |  | PlugPV, LLC. | CH-14502 | Newburgh | Newburgh | Orange | 12550 | G | 4012 | West Balmville | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE11400H-US (240V) | 2021-11-22 | 2021-12-08 | 10 | 2021-12-08 | [14 empty] | 2022-01-06 | 2022-01-06 |  | Y
Central Hudson |  | PlugPV, LLC | CH-14503 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6046 | Spackenkill | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2021-12-07 | 2021-12-20 | 9 | 2021-12-20 | [14 empty] | 2021-12-29 | 2021-12-29 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-14506 | Newburgh | Newburgh | Orange | 12550 | G | 4022 | Coldenham | N |  | 10.44 | [13 empty] | NM | N | 36 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-11-22 | 2021-12-08 | 10 | 2021-12-08 | [14 empty] | 2022-01-11 | 2022-01-11 |  | Y
Central Hudson |  | PlugPV, LLC. | CH-14507 | Newburgh | Newburgh | Orange | 12550 | G | 4044 | Union Ave | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2021-11-22 | 2021-12-08 | 10 | 2021-12-08 | [14 empty] | 2021-12-16 | 2021-12-21 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14508 | Fishkill | Beacon | Dutchess | 12508 | G | 8085 | Tioronda | Y |  | 4.8 | 5 | [12 empty] | NM | N | 1 Delta Electronics M5-TL-US (240V) [SI1] 1TeslaAC Powerwall 2.0 | 2021-11-23 | 2021-12-08 | 9 | 2021-12-08 | [14 empty] | 2022-06-22 | 2022-06-29 |  | Y
Central Hudson |  | PlugPV, LLC. | CH-14513 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6097 | Manchester | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2021-11-23 | 2021-12-08 | 9 | 2021-12-08 | [14 empty] | 2021-12-30 | 2021-12-30 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-14510 | Kingston | Kingston | Ulster | 12401 | G | 2016 | Lincoln Park | N |  | 6.67 | [13 empty] | NM | N | 23 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-11-23 | 2021-12-08 | 9 | 2021-12-08 | [14 empty] | 2022-02-02 | 2022-02-08 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-14509 | Newburgh | Modena | Ulster | 12548 | G | 5012 | Modena | N |  | 7.54 | [13 empty] | NM | N | 26 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-11-23 | 2021-12-08 | 9 | 2021-12-08 | [14 empty] | 2022-01-19 | 2022-01-26 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-14515 | Newburgh | Cornwall Hdsn | Orange | 12520 | G | 4043 | Union Ave | N |  | 2.61 | [13 empty] | NM | N | 9 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-11-23 | 2021-12-08 | 9 | 2021-12-08 | [14 empty] | 2021-12-30 | 2021-12-30 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-14511 | Newburgh | New Windsor | Orange | 12553 | G | 4097 | Bethlehem Rd | N |  | 14.4 | [13 empty] | NM | N | 60 Enphase Energy IQ7-60-x-US (240V) | 2021-11-23 | 2021-12-08 | 9 | 2021-12-08 | [14 empty] | 2022-02-01 | 2022-02-07 |  | Y
Central Hudson |  | PLUGPV LLC | CH-14512 | Newburgh | New Paltz | Ulster | 12561 | G | 5011 | Modena | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000H-US (240V) | 2021-11-23 | 2021-12-08 | 9 | 2021-12-08 | [14 empty] | 2022-01-19 | 2022-01-26 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-14514 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6046 | Spackenkill | N |  | 11.76 | [13 empty] | NM | N | 49 Enphase Energy IQ7-60-x-US (240V) | 2021-11-23 | 2021-12-08 | 9 | 2021-12-08 | [14 empty] | 2022-04-01 | 2022-04-06 |  | Y
Central Hudson |  | SunCommon | CH-14516 | Poughkeepsie | Millbrook | Dutchess | 12545 | G | 7025 | Tinkertown | N |  | 12.76 | [13 empty] | NM | N | 44 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-11-23 | 2021-12-08 | 9 | 2021-12-08 | [14 empty] | 2022-01-31 | 2022-02-04 |  | Y
Central Hudson |  | New York State Solar Farm | CH-14517 | Poughkeepsie | Staatsburg | Dutchess | 12580 | G | 7041 | Staatsburg | N |  | 5.67 | [13 empty] | NM | N | 18 SunPower SPR-X22-360-E-AC (240V) | 2021-11-24 | 2021-12-08 | 8 | 2021-12-08 | [14 empty] | 2022-01-24 | 2022-02-01 |  | Y
Central Hudson |  | Hudson River Solar | CH-14518 | Kingston | Stone Ridge | Ulster | 12484 | G | 3023 | High Falls | Y | CH-10577 | 9 | 9 | [12 empty] | NM | N | 1 Sol-Ark Sol-Ark-12K-P (240V) 1Sol-ArkSOL-ARK 12K-P | 2021-12-20 | 2022-01-04 | 8 | 2022-01-04 | [14 empty] | 2022-03-25 | 2022-03-28 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-14519 | Fishkill | Beacon | Dutchess | 12508 | G | 8085 | Tioronda | N |  | 7.83 | [13 empty] | NM | N | 27 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-11-24 | 2021-12-08 | 8 | 2021-12-08 | [14 empty] | 2022-01-31 | 2022-02-04 |  | Y
Central Hudson |  | SunCommon | CH-14520 | Kingston | W Shokan | Ulster | 12494 | G | 3011 | Woodstock | Y |  | 5.51 | 5 | [12 empty] | NM | N | 19 Enphase Energy IQ7PLUS-72-x-US (240V) 1TeslaPowerwall 2 | 2021-11-24 | 2021-12-08 | 8 | 2021-12-08 | [14 empty] | 2022-01-20 | 2022-01-27 |  | Y
Central Hudson |  | PlugPV, LLC. | CH-14521 | Newburgh | Wallkill | Ulster | 12589 | G | 5033 | Galeville | N |  | 13.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) 1 SolarEdge Technologies SE6000H-US (240V) | 2021-11-24 | 2021-12-08 | 8 | 2021-12-08 | [14 empty] | 2022-01-04 | 2022-01-04 |  | Y
Central Hudson |  | New York State Solar Farm | CH-14522 | Newburgh | Highland | Ulster | 12528 | G | 5081 | Highland | N |  | 4.41 | [13 empty] | NM | N | 14 SunPower SPR-X22-360-E-AC (240V) | 2021-11-29 | 2021-12-08 | 7 | 2021-12-08 | [14 empty] | 2022-01-18 | 2022-01-25 |  | Y
Central Hudson |  | PlugPV LLC | CH-14526 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 3.8 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3800H-US (240V) | 2021-11-29 | 2021-12-13 | 10 | 2021-12-13 | [14 empty] | 2022-02-09 | 2022-02-15 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-14523 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6008 | Reynolds Hill | N |  | 4.35 | [13 empty] | NM | N | 15 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-11-29 | 2021-12-13 | 10 | 2021-12-13 | [14 empty] | 2022-02-17 | 2022-02-23 |  | Y
Central Hudson |  | Trinity Solar | CH-14527 | Newburgh | Washingtonvle | Orange | 10992 | G | 5052 | Maybrook | N |  | 12 | [13 empty] | NM | N | 2 SolarEdge Technologies SE6000H-US (240V) | 2021-12-13 | 2021-12-22 | 7 | 2021-12-22 | [14 empty] | 2022-01-24 | 2022-01-31 |  | Y
Central Hudson |  | PlugPV, LLC. | CH-14524 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2021-11-29 | 2021-12-13 | 10 | 2021-12-13 | [14 empty] | 2021-12-29 | 2021-12-29 |  | Y
Central Hudson |  | PlugPV LLC | CH-14525 | Newburgh | Highland | Ulster | 12528 | G | 5082 | Highland | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE11400H-US (240V) | 2021-11-29 | 2021-12-13 | 10 | 2021-12-13 | [14 empty] | 2022-01-04 | 2022-01-04 |  | Y
Central Hudson |  | Albany Solar Solutions LLC | CH-14529 | Catskill | Ravena | Albany | 12143 | G | 1082 | New Baltimore | N |  | 9.83 | [13 empty] | NM | N | 34 Chilicon Power CP-250E-60/72-208/240-MC4 (240V) [SI1] | 2021-12-13 | 2021-12-21 | 6 | 2021-12-21 | [14 empty] | 2021-12-30 | 2021-12-30 |  | Y
Central Hudson |  | PlugPV LLC | CH-14531 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6052 | Todd Hill | N |  | 13.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) 1 SolarEdge Technologies SE6000H-US (240V) | 2021-11-30 | 2021-12-14 | 10 | 2021-12-14 | [14 empty] | 2022-01-24 | 2022-01-31 |  | Y
Central Hudson |  | Kasselman Solar, LLC | CH-14530 | Poughkeepsie | Tivoli | Dutchess | 12583 | G | 7062 | Milan | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) [SI1] | 2021-12-21 | 2022-01-04 | 7 | 2022-01-04 | [14 empty] | 2022-01-11 | 2022-01-11 |  | W
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14532 | Kingston | Port Ewen | Ulster | 12466 | G | 1012 | Boulevard | N | CH-14532 | 7.68 | [13 empty] | NM | N | 2 Delta Electronics M4-TL-US (240V) [SI1] | 2021-11-30 | 2021-12-14 | 10 | 2021-12-14 | [14 empty] | 2022-05-26 | 2022-05-31 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14533 | Poughkeepsie | Stanfordville | Dutchess | 12581 | G | 7072 | Stanfordville | N |  | 17.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3800H-US (240V) [SI1] 1 SolarEdge Technologies SE6000H-US (240V) 1 SolarEdge Technologies SE7600H-US (240V) | 2021-12-16 | 2022-01-04 | 10 | 2022-01-04 | [8 empty] | 350 | 350 |  | 2022-02-28 | 2022-02-28 | 2022-05-09 | 2022-05-12 | 2022-05-16 |  | Y
Central Hudson |  | New York State Solar Farm | CH-14536 | Kingston | Olivebridge | Ulster | 12461 | G | 3082 | Kerhonkson | N |  | 7.875 | [13 empty] | NM | N | 25 SunPower SPR-X22-360-E-AC (240V) | 2021-12-01 | 2021-12-15 | 10 | 2021-12-15 | [14 empty] | 2021-12-15 | 2021-12-22 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14534 | Newburgh | New Paltz | Ulster | 12561 | G | 5011 | Modena | N |  | 9.8 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) 1 SolarEdge Technologies SE3800H-US (240V) [SI1] | 2021-12-01 | 2021-12-15 | 10 | 2021-12-15 | [14 empty] | 2022-08-15 | 2022-08-17 |  | Y
Central Hudson |  | New York State Solar Farm | CH-14535 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7061 | Milan | N |  | 7.245 | [13 empty] | NM | N | 23 SunPower SPR-X22-360-E-AC (240V) | 2021-12-01 | 2021-12-15 | 10 | 2021-12-15 | [14 empty] | 2022-01-11 | 2022-01-11 |  | Y
Central Hudson |  | New York State Solar Farm | CH-14539 | Poughkeepsie | Staatsburg | Dutchess | 12580 | G | 7041 | Staatsburg | N |  | 4.095 | [13 empty] | NM | N | 13 SunPower SPR-X22-360-E-AC (240V) | 2021-12-01 | 2021-12-15 | 10 | 2021-12-15 | [14 empty] | 2022-01-14 | 2022-01-21 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14537 | Fishkill | Cold Spring | Putnam | 10516 | G | 8087 | Tioronda | N |  | 9.8 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) 1 SolarEdge Technologies SE3800H-US (240V) | 2021-12-01 | 2021-12-15 | 10 | 2021-12-15 | [14 empty] | 2022-05-26 | 2022-05-31 |  | Y
Central Hudson |  | PlugPV, LLC. | CH-14538 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2021-12-01 | 2021-12-15 | 10 | 2021-12-15 | [14 empty] | 2022-01-05 | 2022-01-10 |  | Y
Central Hudson |  | SolarCity dba Tesla Energy Operations, Inc. | CH-14543 | Newburgh | Salisbury Mls | Orange | 12577 | G | 4097 | Bethlehem Rd | Y |  | 7.6 | 5 | [12 empty] | NM | N | 1 Tesla 1538000-xx-y (240V) - may be a component of Powerwall+ (185000-XX-Y) [SI1] 1TeslaAC Powerwall 2.0 | 2022-01-11 | 2022-01-13 | 2 | 2022-01-13 | [14 empty] | 2022-01-31 | 2022-02-07 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-14542 | Fishkill | Hopewell Junctio | Dutchess | 12533 | G | 8094 | Fishkill Plains | N |  | 13.92 | [13 empty] | NM | N | 48 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-12-02 | 2021-12-15 | 9 | 2021-12-15 | [14 empty] | 2021-12-16 | 2021-12-21 |  | Y
Central Hudson |  | PlugPV LLC | CH-14540 | Fishkill | Wappingers Falls | Dutchess | 12590 | G | 8046 | Myers Corners | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000H-US (240V) | 2021-12-02 | 2021-12-15 | 9 | 2021-12-15 | [17 empty] | W
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14541 | Fishkill | Wappingers Falls | Dutchess | 12590 | G | 8043 | Myers Corners | N |  | 9.8 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3800H-US (240V) 1 SolarEdge Technologies SE6000H-US (240V) | 2021-12-02 | 2021-12-15 | 9 | 2021-12-15 | [14 empty] | 2022-07-18 | 2022-07-19 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14549 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 7024 | Tinkertown | Y |  | 12 | 10 | [12 empty] | NM | N | 2 SolarEdge Technologies SE6000H-US (240V) 2SolarEdge TechnologiesSE6000H-USS3 | 2021-12-22 | 2022-01-04 | 6 | 2022-01-04 | [14 empty] | 2022-04-08 | 2022-04-13 |  | Y
Central Hudson |  | SolarCity dba Tesla Energy Operations, Inc. | CH-14552 | Newburgh | Maybrook | Orange | 12543 | G | 5052 | Maybrook | Y |  | 11.4 | 10 | [12 empty] | NM | N | 1 Tesla 1538000-xx-y (240V) - may be a component of Powerwall+ (1850000-XX-Y) [SI1] 1 Tesla 1534000-xx-y (240V) [SI1] 2TeslaAC Powerwall 2.0 | 2021-12-03 | 2021-12-15 | 8 | 2021-12-15 | [14 empty] | 2021-12-28 | 2021-12-28 |  | Y
Central Hudson |  | Lighthouse Solar | CH-14546 | Poughkeepsie | Lagrangeville | Dutchess | 12540 | G | 6055 | Todd Hill | N |  | 22.34 | [13 empty] | NM | N | 64 Enphase Energy IQ7A-72-2-US (240V) [SI1] | 2021-12-16 | 2021-12-22 | 4 | 2021-12-22 | [17 empty] | W
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14545 | Kingston | Kingston | Ulster | 12401 | G | 2013 | Lincoln Park | N |  | 9.6 | [13 empty] | NM | N | 2 Delta Electronics M5-TL-US (240V) [SI1] | 2021-12-03 | 2021-12-15 | 8 | 2021-12-15 | [14 empty] | 2022-04-27 | 2022-05-04 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14544 | Newburgh | Highland | Ulster | 12528 | G | 5081 | Highland | N |  | 7.7 | [13 empty] | NM | N | 2 Delta Electronics M4-TL-US (240V) [SI1] | 2021-12-03 | 2021-12-15 | 8 | 2021-12-15 | [14 empty] | 2022-02-16 | 2022-02-22 |  | Y
Central Hudson |  | PlugPV, LLC | CH-14547 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6052 | Todd Hill | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2021-12-03 | 2021-12-15 | 8 | 2021-12-15 | [14 empty] | 2022-01-06 | 2022-01-06 |  | Y
Central Hudson |  | New York Power Solutions | CH-14548 | Newburgh | Cornwall | Orange | 12518 | G | 4041 | Union Ave | N |  | 12.47 | [13 empty] | NM | N | 43 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-12-03 | 2021-12-15 | 8 | 2021-12-15 | [14 empty] | 2022-03-31 | 2022-04-01 |  | Y
Central Hudson |  | New York Power Solutions | CH-14550 | Poughkeepsie | Pleasant Valley | Dutchess | 12569 | G | 7025 | Tinkertown | N |  | 7.83 | [13 empty] | NM | N | 27 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-12-03 | 2021-12-15 | 8 | 2021-12-15 | [14 empty] | 2022-04-05 | 2022-04-07 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14555 | Kingston | Saugerties | Ulster | 12477 | G | 2015 | Lincoln Park | Y |  | 6 | 5 | [12 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) 1TeslaPowerwall 2 AC | 2021-12-06 | 2021-12-15 | 7 | 2021-12-15 | [14 empty] | 2022-03-02 | 2022-03-04 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-14560 | Newburgh | Newburgh | Orange | 12550 | G | 4011 | West Balmville | N |  | 9.36 | [13 empty] | NM | N | 39 Enphase Energy IQ7-60-x-US (240V) | 2021-12-06 | 2021-12-15 | 7 | 2021-12-15 | [14 empty] | 2022-03-04 | 2022-03-07 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14558 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6056 | Todd Hill | N | CH-14558 | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2021-12-06 | 2021-12-15 | 7 | 2021-12-15 | [14 empty] | 2022-02-09 | 2022-02-22 |  | Y
Central Hudson |  | PlugPV, LLC | CH-14556 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6092 | Manchester | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2021-12-06 | 2021-12-15 | 7 | 2021-12-15 | [14 empty] | 2022-01-06 | 2022-01-06 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14554 | Fishkill | Wappingers Falls | Dutchess | 12590 | G | 8043 | Myers Corners | N | CH-08757 | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2021-12-15 | 2021-12-22 | 5 | 2021-12-22 | [14 empty] | 2022-07-12 | 2022-07-14 |  | Y
Central Hudson |  | Autonomous Energies LLC | CH-14553 | Newburgh | New Paltz | Ulster | 12561 | G | 5031 | Galeville | N |  | 15.6 | [13 empty] | NM | N | 23 Enphase Energy IQ7A-72-M-US (240V) [SI1] 15 Enphase Energy IQ7PLUS-72-2-US (240V) [SI1] 11 Enphase Energy IQ7PLUS-72-2-US (240V) [SI1] | 2021-12-20 | 2022-01-04 | 8 | 2022-01-04 | [8 empty] | 350 | 350 |  | 2022-01-04 | 2022-01-04 | 2022-01-14 | 2022-02-07 | 2022-02-22 |  | Y
Central Hudson |  | New York Power Solutions | CH-14557 | Newburgh | Campbell Hall | Orange | 10916 | G | 5052 | Maybrook | Y |  | 14.5 | 7.68 | [12 empty] | NM | N | 50 Enphase Energy IQ7PLUS-72-x-US (240V) 2EnphaseEncharge 10 | 2022-02-03 | 2022-02-17 | 10 | 2022-02-17 | [14 empty] | 2022-06-14 | 2022-06-21 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-14559 | Newburgh | Newburgh | Orange | 12550 | G | 5004 | Marlboro | N |  | 9.28 | [13 empty] | NM | N | 32 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-12-06 | 2021-12-15 | 7 | 2021-12-15 | [14 empty] | 2022-02-22 | 2022-02-28 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-14561 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6042 | Spackenkill | N |  | 9.6 | [13 empty] | NM | N | 33 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-12-07 | 2021-12-20 | 9 | 2021-12-20 | [14 empty] | 2022-01-11 | 2022-01-11 |  | Y
Central Hudson |  | Trinity Solar | CH-14563 | Newburgh | Campbell Hall | Orange | 10916 | G | 5052 | Maybrook | N |  | 15 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) 1 SolarEdge Technologies SE5000H-US (240V) | 2021-12-07 | 2021-12-20 | 9 | 2021-12-20 | [14 empty] | 2022-02-15 | 2022-02-24 |  | Y
Central Hudson |  | Trinity Solar | CH-14564 | Kingston | Ulster Park | Ulster | 12487 | G | 1023 | East Kingston | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2021-12-07 | 2021-12-20 | 9 | 2021-12-20 | [14 empty] | 2022-11-17 | 2022-11-21 |  | Y
Central Hudson |  | PlugPV LLC | CH-14562 | Fishkill | Hopewell Junctio | Dutchess | 12533 | G | 8091 | Fishkill Plains | N |  | 15.2 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) 1 SolarEdge Technologies SE7600H-US (240V) | 2021-12-07 | 2021-12-20 | 9 | 2021-12-20 | [14 empty] | 2022-02-28 | 2022-02-28 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14565 | Newburgh | Newburgh | Orange | 12550 | G | 4046 | Union Ave | N | CH-14565 | 5.8 | [13 empty] | NM | N | 1 Delta Electronics M6-TL-US (240V) [SI1] | 2021-12-08 | 2021-12-20 | 8 | 2021-12-20 | [14 empty] | 2022-03-18 | 2022-03-21 |  | Y
Central Hudson |  | New York Power Solutions | CH-14567 | Fishkill | Wappingers Falls | Dutchess | 12590 | G | 8043 | Myers Corners | N |  | 7.83 | [13 empty] | NM | N | 27 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-12-08 | 2021-12-20 | 8 | 2021-12-20 | [14 empty] | 2022-03-31 | 2022-04-05 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14566 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6011 | Sand Dock | N | CH-09424 | 3.8 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3800H-US (240V) | 2021-12-08 | 2021-12-20 | 8 | 2021-12-20 | [14 empty] | 2022-05-20 | 2022-05-23 |  | Y
Central Hudson |  | PlugPV, LLC | CH-14568 | Kingston | Hurley | Ulster | 12443 | G | 2093 | Hurley Ave | N |  | 20 | [13 empty] | NM | N | 2 SolarEdge Technologies SE10000H-US (240V) | 2021-12-08 | 2021-12-20 | 8 | 2021-12-20 | [8 empty] | 350 | 350 |  | 2022-01-05 | 2022-01-05 | 2022-01-26 | 2022-01-28 | 2022-02-09 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-14570 | Poughkeepsie | Staatsburg | Dutchess | 12580 | G | 7041 | Staatsburg | N |  | 11.02 | [13 empty] | NM | N | 38 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-12-08 | 2021-12-20 | 8 | 2021-12-20 | [14 empty] | 2022-02-17 | 2022-02-23 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-14573 | Newburgh | Montgomery | Orange | 12549 | G | 5073 | Montgomery | N |  | 8.12 | [13 empty] | NM | N | 28 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-12-09 | 2021-12-20 | 7 | 2021-12-20 | [14 empty] | 2022-02-07 | 2022-02-11 |  | Y
Central Hudson |  | PlugPV, LLC. | CH-14574 | Fishkill | Wappingers Falls | Dutchess | 12590 | G | 8091 | Fishkill Plains | N |  | 13.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) 1 SolarEdge Technologies SE6000H-US (240V) | 2021-12-09 | 2021-12-20 | 7 | 2021-12-20 | [14 empty] | 2022-02-01 | 2022-02-07 |  | Y
Central Hudson |  | PlugPV, LLC. | CH-14571 | Newburgh | Newburgh | Orange | 12550 | G | 4012 | West Balmville | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2021-12-09 | 2021-12-20 | 7 | 2021-12-20 | [14 empty] | 2022-02-14 | 2022-02-25 |  | Y
Central Hudson |  | PlugPV LLC | CH-14572 | Fishkill | Hopewell Junctio | Dutchess | 12533 | G | 8095 | Fishkill Plains | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2021-12-09 | 2021-12-20 | 7 | 2021-12-20 | [14 empty] | 2022-02-15 | 2022-02-22 |  | Y
Central Hudson |  | SolarCity dba Tesla Energy Operations, Inc. | CH-14577 | Newburgh | Milton | Ulster | 12547 | G | 5083 | Highland | Y | CH-05168 | 7.6 | 7.6 | [12 empty] | NM | N | 1 Tesla 1538000-xx-y (240V) - may be a component of Powerwall+ (1850000-XX-Y) [SI1] 1Tesla1850000-10-B | 2022-01-11 | 2022-01-13 | 2 | 2022-01-13 | [14 empty] | 2022-02-02 | 2022-02-08 |  | Y
Central Hudson |  | PlugPV LLC | CH-14578 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6046 | Spackenkill | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2021-12-10 | 2021-12-20 | 6 | 2021-12-20 | [14 empty] | 2022-01-13 | 2022-01-20 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-14575 | Catskill | Cairo | Greene | 12413 | G | 2043 | South Cairo | N |  | 8.7 | [13 empty] | NM | N | 30 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-12-10 | 2021-12-20 | 6 | 2021-12-20 | [14 empty] | 2022-03-14 | 2022-03-17 |  | Y
Central Hudson |  | PlugPV LLC | CH-14576 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6056 | Todd Hill | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2021-12-10 | 2021-12-20 | 6 | 2021-12-20 | [14 empty] | 2021-12-30 | 2021-12-30 |  | Y
Central Hudson |  | New York State Solar Farm | CH-14580 | Fishkill | Wappingers Falls | Dutchess | 12590 | G | 8045 | Myers Corners | N | CH-23327 | 4.41 | [13 empty] | NM | N | 14 SunPower SPR-X22-360-E-AC (240V) | 2021-12-13 | 2021-12-21 | 6 | 2021-12-21 | [14 empty] | 2022-02-16 | 2022-02-22 |  | Y
Central Hudson |  | New York State Solar Farm | CH-14579 | Poughkeepsie | Verbank | Dutchess | 12585 | G | 6057 | Todd Hill | N |  | 13.86 | [13 empty] | NM | N | 44 SunPower SPR-X22-360-E-AC (240V) | 2021-12-13 | 2021-12-20 | 5 | 2021-12-20 | [8 empty] | 350 | 350 |  | 2022-01-21 | 2022-01-21 | 2022-03-02 | 2022-03-16 | 2022-03-18 |  | Y
Central Hudson |  | New York State Solar Farm | CH-14581 | Catskill | Durham | Greene | 12422 | G | 1092 | Westerlo | N |  | 9.45 | [13 empty] | NM | N | 30 SunPower SPR-X22-360-E-AC (240V) | 2021-12-13 | 2021-12-20 | 5 | 2021-12-20 | [14 empty] | 2022-04-08 | 2022-04-13 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-14587 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6003 | Reynolds Hill | N |  | 3.5 | [13 empty] | NM | N | 12 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-12-13 | 2021-12-21 | 6 | 2021-12-21 | [14 empty] | 2022-02-03 | 2022-02-09 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-14588 | Poughkeepsie | Poughkeepsie |  | 12601 | G | 6003 | Reynolds Hill | N |  | 3.5 | [13 empty] | NM | N | 12 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-12-13 | 2021-12-21 | 6 | 2021-12-21 | [17 empty] | W
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14583 | Kingston | Kingston | Ulster | 12401 | G | 2014 | Lincoln Park | N |  | 12 | [13 empty] | NM | N | 2 SolarEdge Technologies SE6000H-US (240V) | 2021-12-13 | 2021-12-20 | 5 | 2021-12-20 | [14 empty] | 2022-05-16 | 2022-05-18 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14582 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6092 | Manchester | Y |  | 3.8 | 3.8 | [12 empty] | NM | N | 1 SolarEdge Technologies SE3800H-US (240V) 1SolarEdge TechnologiesSE3800H-USM3 | 2021-12-13 | 2021-12-20 | 5 | 2021-12-20 | [17 empty] | W
Central Hudson |  | Empire Solar Solutions | CH-14589 | Poughkeepsie | Pine Plains | Dutchess | 12567 | G | 7091 | Pulvers Corners | N |  | 10.44 | [13 empty] | NM | N | 36 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-12-13 | 2021-12-21 | 6 | 2021-12-21 | [8 empty] | 350 | 350 |  | 2022-01-05 | 2022-01-05 | 2022-01-27 | 2022-02-23 | 2022-02-28 |  | Y
Central Hudson |  | PlugPV LLC | CH-14590 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6043 | Spackenkill | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2021-12-13 | 2021-12-21 | 6 | 2021-12-21 | [14 empty] | 2022-03-03 | 2022-03-07 |  | Y
Central Hudson |  | PlugPV, LLC. | CH-14585 | Kingston | Lake Katrine | Ulster | 12449 | G | 2011 | Lincoln Park | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE11400H-US (240V) | 2021-12-13 | 2021-12-20 | 5 | 2021-12-20 | [14 empty] | 2022-02-14 | 2022-02-18 |  | Y
Central Hudson |  | PlugPV, LLC. | CH-14592 | Poughkeepsie | Hyde Park | Dutchess | 12538 | G | 6075 | East Park | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2021-12-13 | 2021-12-21 | 6 | 2021-12-21 | [14 empty] | 2022-02-11 | 2022-02-17 |  | Y
Central Hudson |  | PlugPV LLC | CH-14591 | Newburgh | New Windsor | Orange | 12553 | G | 4095 | Bethlehem Rd | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2021-12-13 | 2021-12-21 | 6 | 2021-12-21 | [14 empty] | 2022-01-27 | 2022-02-01 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-14584 | Fishkill | Wappingers Falls | Dutchess | 12590 | G | 8092 | Fishkill Plains | N |  | 9.86 | [13 empty] | NM | N | 34 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-12-13 | 2021-12-20 | 5 | 2021-12-20 | [14 empty] | 2022-02-17 | 2022-02-23 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14586 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6062 | Inwood Ave | N |  | 7.7 | [13 empty] | NM | N | 1 Delta Electronics M8-TL-US (240V) [SI1] | 2021-12-13 | 2021-12-21 | 6 | 2021-12-21 | [14 empty] | 2022-04-29 | 2022-05-05 |  | Y
Central Hudson |  | PlugPV, LLC. | CH-14593 | Newburgh | New Windsor | Orange | 12553 | G | 4046 | Union Ave | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2021-12-13 | 2021-12-21 | 6 | 2021-12-21 | [14 empty] | 2022-01-27 | 2022-02-02 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-14595 | Newburgh | Montgomery | Orange | 12549 | G | 5073 | Montgomery | N |  | 6.7 | [13 empty] | NM | N | 23 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-12-14 | 2021-12-21 | 5 | 2021-12-21 | [14 empty] | 2021-12-28 | 2021-12-28 |  | Y
Central Hudson |  | PlugPV LLC | CH-14601 | Newburgh | Highland | Ulster | 12528 | G | 5083 | Highland | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2021-12-14 | 2021-12-21 | 5 | 2021-12-21 | [14 empty] | 2022-03-11 | 2022-03-17 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14594 | Newburgh | Highland | Ulster | 12528 | G | 5083 | Highland | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2022-01-03 | 2022-01-06 | 3 | 2022-01-06 | [14 empty] | 2022-08-24 | 2022-08-26 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14600 | Poughkeepsie | Hyde Park | Dutchess | 12538 | G | 6068 | Inwood Ave | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2021-12-14 | 2021-12-21 | 5 | 2021-12-21 | [17 empty] | W
Central Hudson |  | SunPower Direct (NY) | CH-14598 | Kingston | Stone Ridge | Ulster | 12484 | G | 3024 | High Falls | N |  | 8.725 | [13 empty] | NM | N | 25 Enphase Energy IQ7AS-66-ACM-US (240V) [SI1] | 2021-12-14 | 2021-12-28 | 8 | 2021-12-28 | [17 empty] | W
Central Hudson |  | Empire Solar Solutions | CH-14596 | Newburgh | New Windsor | Orange | 12553 | G | 4094 | Bethlehem Rd | N |  | 7.54 | [13 empty] | NM | N | 26 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-12-14 | 2021-12-21 | 5 | 2021-12-21 | [14 empty] | 2022-01-31 | 2022-02-03 |  | Y
Central Hudson |  | New York Power Solutions | CH-14597 | Fishkill | Beacon | Dutchess | 12508 | G | 8015 | Forgebrook | N |  | 4.35 | [13 empty] | NM | N | 15 Enphase Energy IQ7PLUS-72-2-US (240V) [SI1] | 2021-12-14 | 2021-12-21 | 5 | 2021-12-21 | [14 empty] | 2022-02-08 | 2022-02-14 |  | Y
Central Hudson |  | Hudson River Renewables LLC | CH-14599 | Kingston | Tillson | Ulster | 12486 | G | 3022 | High Falls | Y |  | 18 | 18 | [12 empty] | NM | N | 2 Sol-Ark Sol-Ark-12K-P (240V) 2Sol-ark12K-P | 2021-12-22 | 2022-01-04 | 6 | 2022-01-04 | [14 empty] | 2022-01-10 | 2022-01-26 |  | Y
Central Hudson |  | PlugPV LLC | CH-14602 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7013 | Hibernia | N |  | 67 | [13 empty] | NM | N | 5 SolarEdge Technologies SE11400H-US (240V) 1 SolarEdge Technologies SE10000H-US (240V) | 2022-01-04 | 2022-01-18 | 10 | 2022-01-18 | 2022-01-18 | 2022-02-08 | 15 | [11 empty] | 2022-08-16 | 2022-08-16 |  | Y
Central Hudson |  | PlugPV LLC | CH-14603 | Newburgh | Cornwall | Orange | 12518 | G | 4093 | Bethlehem Rd | N |  | 13.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) 1 SolarEdge Technologies SE6000H-US (240V) | 2021-12-15 | 2021-12-22 | 5 | 2021-12-22 | [14 empty] | 2022-01-31 | 2022-02-03 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-14606 | Kingston | Cragsmoor | Ulster | 12420 | G | 3078 | Greenfield Rd | N |  | 17.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) 1 SolarEdge Technologies SE7600H-US (240V) | 2021-12-22 | 2022-01-04 | 6 | 2022-01-04 | [14 empty] | 2022-01-24 | 2022-02-01 |  | Y
Central Hudson |  | PlugPV, LLC. | CH-14607 | Poughkeepsie | Hyde Park | Dutchess | 12538 | G | 7041 | Staatsburg | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000x (240V) [SI1] | 2021-12-15 | 2021-12-22 | 5 | 2021-12-22 | [14 empty] | 2022-03-29 | 2022-03-31 |  | Y
Central Hudson |  | Trinity Solar | CH-14605 | Newburgh | Clintondale | Ulster | 12515 | G | 5012 | Modena | N |  | 15.2 | [13 empty] | NM | N | 2 SolarEdge Technologies SE7600H-US (240V) | 2021-12-15 | 2021-12-22 | 5 | 2021-12-22 | [8 empty] | 350 | 350 |  | 2021-12-29 | 2021-12-29 | 2022-03-22 | 2022-04-13 | 2022-04-20 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14604 | Fishkill | Poughkeepsie | Dutchess | 12601 | G | 8021 | Knapps Corners | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2021-12-15 | 2021-12-22 | 5 | 2021-12-22 | [14 empty] | 2022-06-10 | 2022-06-16 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-14608 | Kingston | Accord | Ulster | 12404 | G | 3024 | High Falls | N |  | 11.6 | [13 empty] | NM | N | 40 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-12-15 | 2021-12-22 | 5 | 2021-12-22 | [14 empty] | 2022-02-25 | 2022-03-02 |  | Y
Central Hudson |  | Trinity Solar | CH-14620 | Newburgh | Campbell Hall | Orange | 10916 | G | 5051 | Maybrook | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000H-US (240V) | 2021-12-16 | 2022-01-04 | 10 | 2022-01-04 | [14 empty] | 2022-02-09 | 2022-02-15 |  | Y
Central Hudson |  | PlugPV LLC | CH-14614 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6046 | Spackenkill | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2021-12-27 | 2022-01-05 | 6 | 2022-01-05 | [14 empty] | 2022-01-13 | 2022-01-20 |  | Y
Central Hudson |  | PlugPV LLC | CH-14609 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6044 | Spackenkill | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2021-12-16 | 2021-12-22 | 4 | 2021-12-22 | [14 empty] | 2022-02-08 | 2022-03-04 |  | Y
Central Hudson |  | Albany Solar Solutions LLC | CH-14610 | Newburgh | Marlboro | Ulster | 12542 | G | 5001 | Marlboro | N |  | 15.409 | [13 empty] | NM | N | 12 Chilicon Power CP-720-60/72/96-208/240-MC4 (240V) [SI1] 8 Chilicon Power CP-720-60/72/96-208/240-MC4 (240V) [SI1] 1 Chilicon Power CP-720-60/72/96-208/240-MC4 (240V) [SI1] 1 Chilicon Power CP-250E-60/72-208/240-MC4 (240V) | 2021-12-22 | 2022-01-05 | 7 | 2022-01-05 | [14 empty] | 2022-02-24 | 2022-02-25 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14611 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6073 | East Park | N |  | 9.8 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3800H-US (240V) 1 SolarEdge Technologies SE6000H-US (240V) | 2021-12-16 | 2021-12-22 | 4 | 2021-12-22 | [14 empty] | 2022-04-05 | 2022-04-08 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-14612 | Fishkill | Wappingers Falls | Dutchess | 12590 | G | 8045 | Myers Corners | N |  | 7.83 | [13 empty] | NM | N | 27 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-12-16 | 2021-12-22 | 4 | 2021-12-22 | [14 empty] | 2022-03-25 | 2022-03-31 |  | Y
Central Hudson |  | PlugPV, LLC. | CH-14613 | Newburgh | Newburgh | Orange | 12550 | G | 4045 | Union Ave | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2021-12-16 | 2021-12-22 | 4 | 2021-12-22 | [8 empty] | 350 | 350 |  | 2022-01-11 | 2022-01-11 | 2022-03-04 | 2022-03-16 | 2022-03-18 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14616 | Newburgh | Newburgh | Orange | 12550 | G | 5004 | Marlboro | Y | CH-14616 | 3.84 | 3.84 | [12 empty] | NM | N | 1 Delta Electronics E4-TL-US (240V) [SI1] 1Delta ElectronicsE4-TL-US | 2022-01-06 | 2022-01-12 | 4 | 2022-01-12 | [14 empty] | 2022-08-31 | 2022-09-02 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-14617 | Poughkeepsie | Poughkeepsie |  | 12603 | G | 6046 | Spackenkill | N |  | 5.8 | [13 empty] | NM | N | 20 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-12-16 | 2021-12-28 | 6 | 2021-12-28 | [17 empty] | W
Central Hudson |  | Empire Solar Solutions | CH-14619 | Kingston | Kingston | Ulster | 12401 | G | 2013 | Lincoln Park | N |  | 7 | [13 empty] | NM | N | 24 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-12-16 | 2021-12-28 | 6 | 2021-12-28 | [14 empty] | 2022-04-12 | 2022-04-19 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-14618 | Catskill | Jewett | Greene | 12444 | E | 2081 | Hunter | N |  | 16 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) 1 SolarEdge Technologies SE6000H-US (240V) | 2021-12-16 | 2021-12-28 | 6 | 2021-12-28 | [8 empty] | 350 | 350 |  | 2021-12-28 | 2021-12-28 | 2022-01-05 | 2022-01-13 | 2022-01-13 |  | Y
Central Hudson |  | PlugPV, LLC | CH-14624 | Kingston | Grahamsville | Sullivan | 12740 | G | 3091 | Neversink | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2021-12-17 | 2021-12-28 | 5 | 2021-12-28 | [14 empty] | 2022-03-18 | 2022-03-25 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14621 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6046 | Spackenkill | Y |  | 11.4 | 5 | [12 empty] | NM | N | 1 SolarEdge Technologies SE3800H-US (240V) 1 SolarEdge Technologies SE7600H-US (240V) 2TeslaAC Powerwall 2.0 | 2022-01-06 | 2022-01-12 | 4 | 2022-01-12 | [14 empty] | 2022-07-13 | 2022-07-25 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-14625 | Fishkill | Cold Spring | Putnam | 10516 | G | 8087 | Tioronda | N |  | 7.54 | [13 empty] | NM | N | 26 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-12-17 | 2021-12-28 | 5 | 2021-12-28 | [14 empty] | 2022-03-02 | 2022-03-04 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-14623 | Newburgh | Newburgh | Orange | 12550 | G | 4012 | West Balmville | N |  | 16.24 | [13 empty] | NM | N | 56 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-12-17 | 2021-12-28 | 5 | 2021-12-28 | [14 empty] | 2022-02-25 | 2022-03-02 |  | Y
Central Hudson |  | Solar Liberty Energy Systems, Inc. | CH-14622 | Newburgh | Newburgh | Orange | 12550 | G | 4011 | West Balmville | N |  | 5000 | [13 empty] | CDG | Y | 40 Chint Power Systems America CPS SCH125KTL-DO/US-600 (600V) | 2022-01-19 | 2022-01-28 | 7 | 2022-01-28 | 2022-01-28 | 2022-02-18 | 15 | 2022-05-25 | 2022-06-03 | 2022-08-29 | 60 | 23665.27 | 3892970.8 | [7 empty] | 2023-04-17 | W
Central Hudson |  | Empire Solar Solutions | CH-14626 | Newburgh | Newburgh | Orange | 12550 | G | 4022 | Coldenham | N |  | 8.41 | [13 empty] | NM | N | 29 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-12-17 | 2021-12-28 | 5 | 2021-12-28 | [14 empty] | 2022-02-14 | 2022-02-18 |  | Y
Central Hudson |  | PlugPV, LLC. | CH-14627 | Newburgh | Milton | Ulster | 12547 | G | 5083 | Highland | N |  | 12 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) 1 SolarEdge Technologies SE6000H-US (240V) | 2021-12-17 | 2021-12-28 | 5 | 2021-12-28 | [14 empty] | 2022-01-27 | 2022-02-02 |  | Y
Central Hudson |  | PlugPV, LLC. | CH-14628 | Poughkeepsie | Pleasant Valley | Dutchess | 12569 | G | 7011 | Hibernia | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2021-12-17 | 2021-12-28 | 5 | 2021-12-28 | [14 empty] | 2022-02-11 | 2022-02-17 |  | Y
Central Hudson |  | Gottschalk Solutions | CH-14629 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6092 | Manchester | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2021-12-20 | 2022-01-04 | 8 | 2022-01-04 | [14 empty] | 2022-01-21 | 2022-01-27 |  | Y
Central Hudson |  | New York State Solar Farm | CH-14630 | Poughkeepsie | Hyde Park | Dutchess | 12538 | G | 7042 | Staatsburg | N |  | 10.47 | [13 empty] | NM | N | 30 SunPower SPR-A400-BLK-G-AC (240V) [SI1] | 2021-12-20 | 2021-12-30 | 6 | 2021-12-30 | [14 empty] | 2022-02-16 | 2022-02-17 |  | Y
Central Hudson |  | SunCommon | CH-14636 | Fishkill | Wappingers Falls | Dutchess | 12590 | G | 8092 | Fishkill Plains | N |  | 9.86 | [13 empty] | NM | N | 34 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-12-20 | 2022-01-04 | 8 | 2022-01-04 | [14 empty] | 2022-02-14 | 2022-02-18 |  | Y
Central Hudson |  | Solar Generation | CH-14634 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6044 | Spackenkill | N |  | 11.6 | [13 empty] | NM | N | 40 Enphase Energy IQ6PLUS-72-2-US (240V) [SI1] | 2021-12-30 | 2022-01-14 | 10 | 2022-01-14 | [14 empty] | 2022-03-31 | 2022-04-01 |  | Y
Central Hudson |  | Suncommon | CH-14637 | Poughkeepsie | Staatsburg | Dutchess | 12580 | G | 7041 | Staatsburg | Y | CH-02087 | 2.385 | [13 empty] | NM | N | 5 Enphase Energy IQ7A-72-2-US (240V) [SI1] 2 SunPower SPR-X21-335-D-AC (240V) [SI1] | 2022-01-05 | 2022-01-11 | 4 | 2022-01-11 | [14 empty] | 2022-06-09 | 2022-06-14 |  | Y
Central Hudson |  | SunCommon | CH-14638 | Newburgh | New Paltz | Ulster | 12561 | G | 5023 | Ohioville | N | CH-01450 | 6.96 | [13 empty] | NM | N | 24 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-12-20 | 2022-01-04 | 8 | 2022-01-04 | [14 empty] | 2022-03-07 | 2022-03-09 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14631 | Newburgh | New Windsor | Orange | 12553 | G | 4054 | Union Ave | N | CH-14631 | 3.84 | [13 empty] | NM | N | 1 Delta Electronics M4-TL-US (240V) [SI1] | 2021-12-20 | 2021-12-30 | 6 | 2021-12-30 | [14 empty] | 2022-03-25 | 2022-03-31 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14632 | Kingston | New Paltz | Ulster | 12561 | G | 3041 | Sturgeon Pool | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2021-12-20 | 2021-12-30 | 6 | 2021-12-30 | [14 empty] | 2022-05-13 | 2022-05-17 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14633 | Kingston | Olivebridge | Ulster | 12461 | G | 3024 | High Falls | N |  | 9.8 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3800H-US (240V) 1 SolarEdge Technologies SE6000H-US (240V) | 2021-12-20 | 2021-12-30 | 6 | 2021-12-30 | [14 empty] | 2022-06-02 | 2022-06-06 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-14635 | Catskill | Jewett | Greene | 12444 | E | 2081 | Hunter | N |  | 6.67 | [13 empty] | NM | N | 23 Enphase Energy IQ7PLUS-72-x-US (240V) | 2022-01-04 | 2022-01-11 | 5 | 2022-01-11 | [14 empty] | 2022-05-12 | 2022-05-16 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-14640 | Fishkill | Wappingers Falls | Dutchess | 12590 | G | 8092 | Fishkill Plains | N |  | 3.36 | [13 empty] | NM | N | 14 Enphase Energy IQ7-60-x-US (240V) | 2021-12-21 | 2022-01-04 | 7 | 2022-01-04 | [14 empty] | 2022-05-11 | 2022-05-12 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14639 | Newburgh | Marlboro | Ulster | 12542 | G | 5004 | Marlboro | Y | CH-14639 | 5.76 | 9.6 | [12 empty] | NM | N | 1 Delta Electronics E6-TL-US (240V) [SI1] 1Delta ElectronicsE6-TL-US | 2022-01-06 | 2022-01-12 | 4 | 2022-01-12 | [14 empty] | 2022-04-05 | 2022-04-08 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-14641 | Newburgh | Highland | Ulster | 12528 | G | 5012 | Modena | N |  | 10.44 | [13 empty] | NM | N | 36 Enphase Energy IQ7PLUS-72-2-US (240V) [SI1] | 2021-12-21 | 2022-01-04 | 7 | 2022-01-04 | [14 empty] | 2022-01-31 | 2022-02-04 |  | Y
Central Hudson |  | Sunrise Power Solutions | CH-14644 | Newburgh | New Windsor | Orange | 12553 | G | 4045 | Union Ave | N |  | 150 | [13 empty] | NM | N | 3 SMA America STP 50-US-41 (480V) | 2022-01-27 | 2022-02-10 | 10 | 2022-02-10 | 2022-02-10 | 2022-03-01 | 12 | [11 empty] | 2022-07-08 | 2022-07-08 |  | Y
Central Hudson |  | Sunrise Power Solutions | CH-14643 | Newburgh | Newburgh | Orange | 12550 | G | 4022 | Coldenham | N |  | 133.3 | [13 empty] | NM | N | 1 SMA America STP 50-US-41 (480V) 1 SMA America STP 33-US-41 (480V) 1 SMA America STP50-US-40 (480V) [SI1] | 2022-02-08 | 2022-02-22 | 9 | 2022-02-22 | 2022-02-22 | 2022-03-01 | 5 | [11 empty] | 2022-04-28 | 2022-04-28 |  | Y
Central Hudson |  | Industrial Process Design Engineering | CH-14646 | Catskill | Selkirk | Albany | 12158 | G | 1082 | New Baltimore | N |  |  | 660 | [12 empty] | NM | Y | 1SungrowSC 1200UD-US | 2022-02-18 | 2022-03-07 | 10 | 2022-03-07 | 2022-03-07 | 2022-03-28 | 15 | 2022-04-19 | 2022-05-20 | 2022-09-26 | 88 | 24394.11 | 425132 | [7 empty] | 2023-03-29 | W |  | 8/17/2022 – Applicant notified that CESIR deadline extended to 9/30/2022.
Central Hudson |  | New York State Solar Farm | CH-14649 | Fishkill | Hopewell Junctio | Dutchess | 12533 | G | 8095 | Fishkill Plains | N |  | 8.19 | [13 empty] | NM | N | 26 SunPower SPR-X22-360-E-AC (240V) | 2021-12-22 | 2022-01-05 | 7 | 2022-01-05 | [14 empty] | 2022-02-08 | 2022-02-14 |  | Y
Central Hudson |  | PlugPV, LLC. | CH-14645 | Newburgh | Newburgh | Orange | 12550 | G | 4011 | West Balmville | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2021-12-22 | 2022-01-04 | 6 | 2022-01-04 | [14 empty] | 2022-02-09 | 2022-02-15 |  | Y
Central Hudson |  | New York State Solar Farm | CH-14648 | Newburgh | Gardiner | Ulster | 12525 | G | 5011 | Modena | N |  | 11.34 | [13 empty] | NM | N | 36 SunPower SPR-X22-360-E-AC (240V) | 2021-12-22 | 2022-01-05 | 7 | 2022-01-05 | [14 empty] | 2022-01-31 | 2022-02-03 |  | Y
Central Hudson |  | New York State Solar Farm | CH-14647 | Kingston | Kingston | Ulster | 12401 | G | 1024 | East Kingston | N |  | 3.78 | [13 empty] | NM | N | 12 SunPower SPR-X22-360-E-AC (240V) | 2021-12-22 | 2022-01-04 | 6 | 2022-01-04 | [14 empty] | 2022-02-28 | 2022-03-04 |  | Y
Central Hudson |  | Nexamp | CH-14642 | Catskill | Greenville | Greene | 12083 | G | 2061 | Freehold | N |  | 4200 | [13 empty] | CDG | Y | 28 SMA America SHP 150-US-20 (600V) | 2022-02-17 | 2022-03-01 | 7 | 2022-03-01 | 2022-03-01 | 2022-03-04 | 3 | 2022-04-07 | 2022-05-02 | 2022-07-27 | 60 | 20628.16 | 8710298.95 | [7 empty] | 2023-02-07 | W
Central Hudson |  | PlugPV, LLC | CH-14653 | Fishkill | Wappingers Falls | Dutchess | 12590 | G | 8091 | Fishkill Plains | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2021-12-28 | 2022-01-05 | 5 | 2022-01-05 | [14 empty] | 2022-02-08 | 2022-02-14 |  | Y
Central Hudson |  | PlugPV LLC | CH-14651 | Kingston | Kingston | Ulster | 12401 | G | 1021 | East Kingston | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2021-12-28 | 2022-01-05 | 5 | 2022-01-05 | [14 empty] | 2022-03-10 | 2022-03-14 |  | Y
Central Hudson |  | PlugPV LLC | CH-14650 | Kingston | Kingston | Ulster | 12401 | G | 1022 | East Kingston | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000H-US (240V) | 2021-12-28 | 2022-01-05 | 5 | 2022-01-05 | [14 empty] | 2022-02-28 | 2022-03-04 |  | Y
Central Hudson |  | SunCommon | CH-14652 | Poughkeepsie | Ancram | Columbia | 12502 | G | 7085 | Ancram | N |  | 9.57 | [13 empty] | NM | N | 33 Enphase Energy IQ7PLUS-72-x-US (240V) | 2021-12-28 | 2022-01-12 | 10 | 2022-01-12 | [14 empty] | 2022-03-16 | 2022-03-18 |  | Y
Central Hudson |  | Trinity Solar | CH-14656 | Kingston | Kingston | Ulster | 12401 | G | 2014 | Lincoln Park | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2021-12-29 | 2022-01-05 | 4 | 2022-01-05 | [14 empty] | 2022-05-09 | 2022-05-11 |  | Y
Central Hudson |  | Kasselman Solar, LLC | CH-14657 | Fishkill | Wappingers Falls | Dutchess | 12590 | G | 8051 | North Chelsea | N |  | 7 | [13 empty] | NM | N | 20 Enphase Energy IQ7A-72-2-US (240V) [SI1] | 2021-12-29 | 2022-01-05 | 4 | 2022-01-05 | [14 empty] | 2022-01-12 | 2022-01-12 |  | Y
Central Hudson |  | PlugPV, LLC. | CH-14654 | Newburgh | Wallkill | Ulster | 12589 | G | 5042 | East Walden | N |  | 20 | [13 empty] | NM | N | 2 SolarEdge Technologies SE10000H-US (240V) | 2021-12-29 | 2022-01-05 | 4 | 2022-01-05 | [14 empty] | 2022-02-14 | 2022-02-18 |  | Y
Central Hudson |  | PlugPV, LLC. | CH-14661 | Newburgh | Wallkill | Ulster | 12589 | G | 5041 | East Walden | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2021-12-30 | 2022-01-06 | 4 | 2022-01-06 | [14 empty] | 2022-02-14 | 2022-02-18 |  | Y
Central Hudson |  | PlugPV LLC | CH-14658 | Fishkill | Wappingers Falls | Dutchess | 12590 | G | 8056 | North Chelsea | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2021-12-30 | 2022-01-05 | 3 | 2022-01-05 | [14 empty] | 2022-04-05 | 2022-04-08 |  | Y
Central Hudson |  | New York State Solar Farm | CH-14663 | Kingston | Saugerties | Ulster | 12477 | G | 3004 | Saugerties | N |  | 6.93 | [13 empty] | NM | N | 22 SunPower SPR-X22-360-E-AC (240V) | 2021-12-30 | 2022-01-06 | 4 | 2022-01-06 | [14 empty] | 2022-01-28 | 2022-02-02 |  | Y
Central Hudson |  | New York State Solar Farm | CH-14665 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7041 | Staatsburg | N |  | 4.41 | [13 empty] | NM | N | 14 SunPower SPR-X22-360-E-AC (240V) | 2021-12-30 | 2022-01-06 | 4 | 2022-01-06 | [14 empty] | 2022-02-22 | 2022-02-28 |  | Y
Central Hudson |  | PlugPV, LLC. | CH-14660 | Newburgh | Wallkill | Ulster | 12589 | G | 5042 | East Walden | N |  | 13.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) 1 SolarEdge Technologies SE6000H-US (240V) | 2021-12-30 | 2022-01-05 | 3 | 2022-01-05 | [14 empty] | 2022-02-14 | 2022-02-18 |  | Y
Central Hudson |  | Suncommon | CH-14659 | Kingston | Woodstock | Ulster | 12498 | G | 3012 | Woodstock | Y | CH-13850 |  | 5 | [12 empty] | NM | N | 1TeslaPowerwall 2 | 2021-12-30 | 2022-01-06 | 4 | 2022-01-06 | [14 empty] | 2022-11-01 | 2022-11-04 |  | Y
Central Hudson |  | New York Power Solutions | CH-14662 | Fishkill | Fishkill | Dutchess | 12524 | G | 8065 | Merritt Park | N |  | 9.28 | [13 empty] | NM | N | 32 Enphase Energy IQ7PLUS-72-x-US (240V) | 2022-01-06 | 2022-01-12 | 4 | 2022-01-12 | [14 empty] | 2022-04-22 | 2022-04-25 |  | Y
Central Hudson |  | Kasselman Solar, LLC | CH-14664 | Newburgh | Highland | Ulster | 12528 | G | 5083 | Highland | N |  | 6.3 | [13 empty] | NM | N | 18 Enphase Energy IQ7A-72-2-US (240V) [SI1] | 2021-12-30 | 2022-01-06 | 4 | 2022-01-06 | [14 empty] | 2022-01-10 | 2022-01-17 |  | Y
Central Hudson |  | PLUGPV LLC | CH-14666 | Poughkeepsie | Poughkeepsie |  | 12603 | G | 6065 | Inwood Ave | Y |  | 3.8 | 5 | [12 empty] | NM | N | 1 SolarEdge Technologies SE3800H-US (240V) 1TESLAPOWERWALL 2 | 2022-01-13 | 2022-01-13 | 0 | 2022-01-13 | [17 empty] | W
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14667 | Newburgh | Newburgh | Orange | 12550 | G | 4055 | Union Ave | N |  | 9.8 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3800H-US (240V) 1 SolarEdge Technologies SE6000H-US (240V) | 2022-01-03 | 2022-01-06 | 3 | 2022-01-06 | [14 empty] | 2022-02-23 | 2022-03-11 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14668 | Newburgh | Plattekill | Ulster | 12568 | G | 5013 | Modena | N |  | 9.8 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) 1 SolarEdge Technologies SE3800H-US (240V) | 2022-01-03 | 2022-01-06 | 3 | 2022-01-06 | [14 empty] | 2022-06-03 | 2022-06-07 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-14671 | Fishkill | Stormville | Dutchess | 12582 | G | 8093 | Fishkill Plains | N |  | 9.6 | [13 empty] | NM | N | 40 Enphase Energy IQ7-60-x-US (240V) | 2022-01-03 | 2022-01-06 | 3 | 2022-01-06 | [14 empty] | 2022-04-05 | 2022-04-08 |  | Y
Central Hudson |  | Lighthouse Solar | CH-14670 | Kingston | Kerhonkson | Ulster | 12446 | G | 3071 | Honk Falls | N |  | 7.2 | [13 empty] | NM | N | 25 Enphase Energy IQ7PLUS-72-2-US (240V) [SI1] | 2022-01-03 | 2022-01-17 | 10 | 2022-01-17 | [14 empty] | 2022-02-25 | 2022-03-02 |  | Y
Central Hudson |  | Lighthouse Solar | CH-14669 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6043 | Spackenkill | N |  | 6.4 | [13 empty] | NM | N | 22 Enphase Energy IQ7PLUS-72-2-US (240V) [SI1] | 2022-01-03 | 2022-01-06 | 3 | 2022-01-06 | [14 empty] | 2022-02-10 | 2022-02-15 |  | Y
Central Hudson |  | PlugPV LLC | CH-14672 | Fishkill | Beacon | Dutchess | 12508 | G | 8087 | Tioronda | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000H-US (240V) | 2022-01-03 | 2022-01-06 | 3 | 2022-01-06 | [14 empty] | 2022-03-11 | 2022-03-15 |  | Y
Central Hudson |  | PlugPV LLC | CH-14673 | Kingston | Stone Ridge | Ulster | 12484 | G | 3024 | High Falls | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2022-01-03 | 2022-01-06 | 3 | 2022-01-06 | [14 empty] | 2022-03-23 | 2022-03-24 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-14676 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 10.32 | [13 empty] | NM | N | 43 Enphase Energy IQ7-60-x-US (240V) | 2022-01-04 | 2022-01-06 | 2 | 2022-01-06 | [14 empty] | 2022-02-01 | 2022-02-07 |  | Y
Central Hudson |  | New York State Solar Farm | CH-14677 | Kingston | Kerhonkson | Ulster | 12446 | G | 3082 | Kerhonkson | N |  | 4.886 | [13 empty] | NM | N | 14 SunPower SPR-A420-G-AC (240V) | 2022-01-04 | 2022-01-11 | 5 | 2022-01-11 | [14 empty] | 2022-03-16 | 2022-03-18 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14675 | Fishkill | Wappingers Falls | Dutchess | 12590 | G | 8052 | North Chelsea | Y |  | 7.68 | 7.68 | [12 empty] | NM | N | 1 Delta Electronics E8-TL-US (240V) [SI1] 1Delta ElectronicsE8-TL-US | 2022-01-19 | 2022-02-02 | 10 | 2022-02-02 | [17 empty] | W
Central Hudson |  | Kasselman Solar, LLC | CH-14678 | Newburgh | Newburgh | Orange | 12550 | G | 4023 | Coldenham | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) [SI1] | 2022-01-04 | 2022-01-11 | 5 | 2022-01-11 | [14 empty] | 2022-01-26 | 2022-02-01 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14674 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6044 | Spackenkill | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2022-01-07 | 2022-01-13 | 4 | 2022-01-13 | [14 empty] | 2022-04-01 | 2022-04-06 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14679 | Newburgh | Wallkill | Ulster | 12589 | G | 5041 | East Walden | N |  | 17.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) [SI1] 1 SolarEdge Technologies SE3800H-US (240V) [SI1] 1 SolarEdge Technologies SE7600H-US (240V) [SI1] | 2022-01-19 | 2022-02-02 | 10 | 2022-02-02 | [17 empty] | N
Central Hudson |  | Kasselman Solar, LLC | CH-14680 | Newburgh | Marlboro | Ulster | 12542 | G | 5003 | Marlboro | N |  | 8.03 | [13 empty] | NM | N | 23 Enphase Energy IQ7A-72-2-US (240V) [SI1] | 2022-01-04 | 2022-01-11 | 5 | 2022-01-11 | [14 empty] | 2022-01-26 | 2022-02-01 |  | Y
Central Hudson |  | Sunrise Power Solutions | CH-14686 | Newburgh | Marlboro | Ulster | 12542 | G | 5003 | Marlboro | N |  | 750 | [13 empty] | RC | Y | 15 SMA America STP 50-US-41 (480V) | 2022-02-08 | 2022-02-14 | 4 | 2022-02-14 | 2022-02-14 | 2022-03-07 | 14 | 2022-03-15 | 2022-05-31 | 2022-08-24 | 60 | 22580.55 | 147334.55 | 156254.89 | 2022-11-08 | 2023-05-01 | 2023-05-01 | 2024-05-17 | 2024-12-18 | 2024-12-18 | 2025-03-17 | Y | Y
Central Hudson |  | Sunrise Power Solutions | CH-14685 | Newburgh | Newburgh | Orange | 12550 | G | 5001 | Marlboro | N |  | 62.5 | [13 empty] | NM | N | 1 SMA America STP 62-US-41 (480V) | 2022-01-28 | 2022-02-01 | 2 | 2022-02-01 | 2022-02-01 | 2022-02-23 | 15 | [11 empty] | 2024-02-22 | 2024-02-22 |  | Y
Central Hudson |  | PlugPV, LLC | CH-14687 | Fishkill | Hopewell Junctio | Dutchess | 12533 | G | 8071 | Shenandoah | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2022-01-05 | 2022-01-12 | 5 | 2022-01-12 | [14 empty] | 2022-01-25 | 2022-02-01 |  | Y
Central Hudson |  | Lighthouse Solar | CH-14681 | Fishkill | Cold Spring | Putnam | 10516 | G | 8063 | Merritt Park | N |  | 8.03 | [13 empty] | NM | N | 23 Enphase Energy IQ7A-72-2-US (240V) [SI1] | 2022-01-05 | 2022-01-11 | 4 | 2022-01-11 | [14 empty] | 2022-03-04 | 2022-03-07 |  | Y
Central Hudson |  | PlugPV, LLC. | CH-14682 | Poughkeepsie | Staatsburg | Dutchess | 12580 | G | 7041 | Staatsburg | N |  | 20 | [13 empty] | NM | N | 2 SolarEdge Technologies SE10000H-US (240V) | 2022-01-05 | 2022-01-11 | 4 | 2022-01-11 | [8 empty] | 350 | 350 |  | 2022-01-11 | 2022-01-11 | 2022-01-19 | 2022-03-29 | 2022-03-31 |  | Y
Central Hudson |  | PlugPV LLC | CH-14684 | Fishkill | Hopewell Junctio | Dutchess | 12533 | G | 8072 | Shenandoah | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2022-01-05 | 2022-01-11 | 4 | 2022-01-11 | [14 empty] | 2022-02-15 | 2022-02-22 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-14683 | Fishkill | Hopewell Junctio | Dutchess | 12533 | G | 8094 | Fishkill Plains | N |  | 9.84 | [13 empty] | NM | N | 41 Enphase Energy IQ7-60-x-US (240V) | 2022-01-05 | 2022-01-11 | 4 | 2022-01-11 | [14 empty] | 2022-02-28 | 2022-03-04 |  | Y
Central Hudson |  | PlugPV, LLC. | CH-14689 | Fishkill | Fishkill | Dutchess | 12524 | G | 8055 | North Chelsea | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE11400H-US (240V) | 2022-01-06 | 2022-01-12 | 4 | 2022-01-12 | [14 empty] | 2022-02-09 | 2022-02-15 |  | Y
Central Hudson |  | SunCommon | CH-14688 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7053 | Rhinebeck | Y |  | 15.2 | 5 | [12 empty] | NM | N | 2 Tesla 1538000-xx-y (240V) - may be a component of Powerwall+ (1850000-XX-Y) [SI1] 1TeslaPowerwall 2 | 2022-01-12 | 2022-01-13 | 1 | 2022-01-13 | [8 empty] | 350 | 350 |  | 2022-01-24 | 2022-01-24 | 2022-01-31 | 2022-06-06 | 2022-06-08 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-14690 | Poughkeepsie | Wassaic | Dutchess | 12592 | G | 7012 | Hibernia | N |  | 8.12 | [13 empty] | NM | N | 28 Enphase Energy IQ7PLUS-72-x-US (240V) | 2022-01-06 | 2022-01-12 | 4 | 2022-01-12 | [14 empty] | 2022-03-23 | 2022-04-04 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14697 | Poughkeepsie | Salt Point | Dutchess | 12578 | G | 7025 | Tinkertown | Y |  | 7.7 | 10 | [12 empty] | NM | N | 2 Delta Electronics M4-TL-US (240V) [SI1] 2TeslaAC Powerwall 2.0 | 2022-01-24 | 2022-02-07 | 10 | 2022-02-07 | [17 empty] | W
Central Hudson |  | PlugPV LLC | CH-14694 | Poughkeepsie | Hyde Park | Dutchess | 12538 | G | 6068 | Inwood Ave | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2022-01-07 | 2022-01-13 | 4 | 2022-01-13 | [14 empty] | 2022-02-15 | 2022-02-25 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-14696 | Poughkeepsie | Lagrangeville | Dutchess | 12540 | G | 6055 | Todd Hill | N |  | 5.51 | [13 empty] | NM | N | 19 Enphase Energy IQ7PLUS-72-x-US (240V) | 2022-01-07 | 2022-01-13 | 4 | 2022-01-13 | [14 empty] | 2022-05-05 | 2022-05-10 |  | Y
Central Hudson |  | PLUGPV LLC | CH-14691 | Fishkill | Wappingers Falls | Dutchess | 12590 | G | 8022 | Knapps Corners | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000H-US (240V) | 2022-01-07 | 2022-01-12 | 3 | 2022-01-12 | [14 empty] | 2022-03-14 | 2022-03-23 |  | Y
Central Hudson |  | Lighthouse Solar | CH-14693 | Newburgh | Wallkill | Ulster | 12589 | G | 5011 | Modena | N |  | 18.6 | [13 empty] | NM | N | 64 Enphase Energy IQ7PLUS-72-2-US (240V) [SI1] | 2022-01-07 | 2022-01-12 | 3 | 2022-01-12 | [14 empty] | 2022-04-12 | 2022-04-19 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-14695 | Fishkill | Hopewell Junctio | Dutchess | 12533 | G | 8072 | Shenandoah | N |  | 8.12 | [13 empty] | NM | N | 28 Enphase Energy IQ7PLUS-72-x-US (240V) | 2022-01-07 | 2022-01-13 | 4 | 2022-01-13 | [14 empty] | 2022-06-01 | 2022-06-03 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-14698 | Catskill | Palenville | Greene | 12463 | G | 2001 | North Catskill | N |  | 6.7 | [13 empty] | NM | N | 23 Enphase Energy IQ7PLUS-72-x-US (240V) | 2022-01-07 | 2022-01-13 | 4 | 2022-01-13 | [14 empty] | 2022-04-21 | 2022-04-25 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-14699 | Catskill | Palenville | Greene | 12463 | G | 2001 | North Catskill | N |  | 0.58 | [13 empty] | NM | N | 2 Enphase Energy IQ7PLUS-72-x-US (240V) | 2022-01-07 | 2022-01-13 | 4 | 2022-01-13 | [14 empty] | 2022-04-21 | 2022-04-27 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14692 | Kingston | Ellenville | Ulster | 12428 | G | 3078 | Greenfield Rd | N | CH-09522 | 3.84 | [13 empty] | NM | N | 1 Delta Electronics M4-TL-US (240V) [SI1] | 2022-01-07 | 2022-01-13 | 4 | 2022-01-13 | [14 empty] | 2022-12-09 | 2022-12-12 |  | W
Central Hudson |  | Empire Solar Solutions | CH-14700 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6046 | Spackenkill | N |  | 9.3 | [13 empty] | NM | N | 32 Enphase Energy IQ7PLUS-72-x-US (240V) | 2022-01-13 | 2022-01-13 | 0 | 2022-01-13 | [8 empty] | 350 | 350 |  | 2022-01-13 | 2022-01-13 | 2022-01-20 | 2022-02-07 | 2022-02-11 |  | Y
Central Hudson |  | PlugPV, LLC | CH-14701 | Fishkill | Wappingers Falls | Dutchess | 12590 | G | 8091 | Fishkill Plains | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2022-01-10 | 2022-01-13 | 3 | 2022-01-13 | [14 empty] | 2022-02-14 | 2022-02-18 |  | Y
Central Hudson |  | SolarCity dba Tesla Energy Operations, Inc. | CH-14703 | Catskill | Tannersville | Greene | 12485 | G | 2385 | Lawrenceville | N |  | 7.6 | [13 empty] | NM | N | 1 Tesla 1538000-xx-y (240V) - may be a component of Powerwall+ (1850000-XX-Y) [SI1] | 2022-01-10 | 2022-01-13 | 3 | 2022-01-13 | [14 empty] | 2022-02-01 | 2022-02-07 |  | Y
Central Hudson |  | SolarCity dba Tesla Energy Operations, Inc. | CH-14702 | Fishkill | Hopewell Junctio | Dutchess | 12533 | G | 8095 | Fishkill Plains | N |  | 11.4 | [13 empty] | NM | N | 1 Tesla 1534000-xx-y (240V) [SI1] 1 Tesla 1538000-xx-y (240V) - may be a component of Powerwall+ (1850000-XX-Y) [SI1] | 2022-01-10 | 2022-01-13 | 3 | 2022-01-13 | [14 empty] | 2022-02-17 | 2022-02-23 |  | Y
Central Hudson |  | PlugPV, LLC. | CH-14704 | Fishkill | Hopewell Junctio | Dutchess | 12533 | G | 8095 | Fishkill Plains | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE11400H-US (240V) | 2022-01-10 | 2022-01-13 | 3 | 2022-01-13 | [14 empty] | 2022-03-17 | 2022-03-18 |  | Y
Central Hudson |  | Trinity Solar | CH-14705 | Newburgh | Newburgh | Orange | 12550 | G | 4012 | West Balmville | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2022-01-14 | 2022-01-26 | 8 | 2022-01-26 | [14 empty] | 2022-02-24 | 2022-03-04 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14707 | Poughkeepsie | Pleasant Valley | Dutchess | 12569 | G | 7011 | Hibernia | Y |  | 6 | 5 | [12 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) 1TeslaPowerwall 2 AC | 2022-01-11 | 2022-01-13 | 2 | 2022-01-13 | [14 empty] | 2022-06-03 | 2022-06-08 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14706 | Newburgh | Newburgh | Orange | 12550 | G | 4051 | Union Ave | N | CH-14706 | 4.8 | [13 empty] | NM | N | 1 Delta Electronics M5-TL-US (240V) [SI1] | 2022-02-11 | 2022-02-25 | 9 | 2022-02-25 | [14 empty] | 2022-03-25 | 2022-03-28 |  | Y
Central Hudson |  | New York Power Solutions | CH-14710 | Fishkill | Wappingers Falls | Dutchess | 12590 | G | 8044 | Myers Corners | Y |  | 15.2 | 7.6 | [12 empty] | NM | N | 2 Generac Power Systems X7602 (240V) 1GENERACPWEcell APKE00014 | 2022-02-02 | 2022-02-16 | 10 | 2022-02-16 | [14 empty] | 2022-06-07 | 2022-06-08 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-14709 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 11.52 | [13 empty] | NM | N | 48 Enphase Energy IQ7-60-x-US (240V) | 2022-01-25 | 2022-02-07 | 9 | 2022-02-07 | [14 empty] | 2022-02-22 | 2022-02-25 |  | Y
Central Hudson |  | PlugPV, LLC. | CH-14712 | Newburgh | Newburgh | Orange | 12550 | G | 4012 | West Balmville | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2022-01-12 | 2022-01-13 | 1 | 2022-01-13 | [14 empty] | 2022-04-21 | 2022-04-21 |  | Y
Central Hudson |  | PlugPV, LLC. | CH-14713 | Newburgh | Newburgh | Orange | 12550 | G | 4011 | West Balmville | N |  | 12 | [13 empty] | NM | N | 2 SolarEdge Technologies SE6000H-US (240V) | 2022-01-12 | 2022-01-13 | 1 | 2022-01-13 | [14 empty] | 2022-02-28 | 2022-03-04 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14708 | Kingston | W Shokan | Ulster | 12494 | G | 3011 | Woodstock | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2022-01-12 | 2022-01-25 | 9 | 2022-01-25 | [14 empty] | 2022-03-25 | 2022-03-28 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-14711 | Fishkill | Wappingers Falls | Dutchess | 12590 | G | 8045 | Myers Corners | N |  | 6.96 | [13 empty] | NM | N | 24 Enphase Energy IQ7PLUS-72-x-US (240V) | 2022-01-12 | 2022-01-13 | 1 | 2022-01-13 | [8 empty] | 350 | 350 |  | 2022-01-13 | 2022-01-13 | 2022-02-15 | 2022-03-28 | 2022-03-31 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-14714 | Newburgh | New Windsor | Orange | 12553 | G | 4095 | Bethlehem Rd | N |  | 8.7 | [13 empty] | NM | N | 30 Enphase Energy IQ7PLUS-72-x-US (240V) | 2022-01-13 | 2022-01-24 | 7 | 2022-01-24 | [17 empty] | W
Central Hudson |  | Empire Solar Solutions | CH-14717 | Newburgh | Wallkill | Ulster | 12589 | G | 5043 | East Walden | N |  | 13.34 | [13 empty] | NM | N | 46 Enphase Energy IQ7PLUS-72-x-US (240V) | 2022-01-13 | 2022-01-14 | 1 | 2022-01-14 | [17 empty] | W
Central Hudson |  | New York State Solar Farm | CH-14719 | Newburgh | New Windsor | Orange | 12553 | G | 4045 | Union Ave | N |  | 5.235 | [13 empty] | NM | N | 15 SunPower SPR-A400-G-AC (240V) | 2022-01-13 | 2022-01-20 | 5 | 2022-01-20 | [14 empty] | 2022-01-31 | 2022-02-04 |  | Y
Central Hudson |  | New York State Solar Farm | CH-14716 | Poughkeepsie | Millbrook | Dutchess | 12545 | G | 7025 | Tinkertown | N | CH-11955 | 4.608 | [13 empty] | NM | N | 12 SunPower SPR-M440-H-AC (240V) [SI1] | 2022-01-13 | 2022-01-26 | 9 | 2022-01-26 | [14 empty] | 2022-02-22 | 2022-02-25 |  | Y
Central Hudson |  | PlugPV LLC | CH-14718 | Poughkeepsie | Pleasant Valley | Dutchess | 12569 | G | 7024 | Tinkertown | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2022-01-13 | 2022-01-25 | 8 | 2022-01-25 | [14 empty] | 2022-03-09 | 2022-03-14 |  | Y
Central Hudson |  | SolarCity dba Tesla Energy Operations, Inc. | CH-14715 | Newburgh | Newburgh | Orange | 12550 | G | 5001 | Marlboro | N | CH-14715 | 7.6 | [13 empty] | NM | N | 1 Tesla 1538000-xx-y (240V) - may be a component of Powerwall+ (1850000-XX-Y) [SI1] | 2022-01-13 | 2022-01-13 | 0 | 2022-01-13 | [14 empty] | 2022-05-12 | 2022-05-16 |  | Y
Central Hudson |  | SunPower Direct (NY) | CH-14722 | Poughkeepsie | Stanfordville | Dutchess | 12581 | G | 7072 | Stanfordville | N |  | 14.49 | [13 empty] | NM | N | 46 SunPower SPR-E20-327-E-AC (208V) | 2022-01-24 | 2022-02-03 | 8 | 2022-02-03 | [14 empty] | 2022-04-08 | 2022-04-13 |  | Y
Central Hudson |  | Kasselman Solar, LLC | CH-14720 | Kingston | Accord | Ulster | 12404 | G | 3081 | Kerhonkson | N |  | 7 | [13 empty] | NM | N | 20 Enphase Energy IQ7A-72-2-US (240V) [SI1] | 2022-01-24 | 2022-02-03 | 8 | 2022-02-03 | [14 empty] | 2022-02-09 | 2022-02-15 |  | Y
Central Hudson |  | Kasselman Solar, LLC | CH-14721 | Fishkill | Hopewell Junctio | Dutchess | 12533 | G | 8095 | Fishkill Plains | Y |  | 11.31 | 7.68 | [12 empty] | NM | N | 39 Enphase Energy IQ7PLUS-72-2-US (240V) [SI1] 2Enphase EnergyENCHARGE-10-1P-NA | 2022-03-22 | 2022-04-01 | 8 | 2022-04-01 | [14 empty] | 2022-04-26 | 2022-04-29 |  | Y
Central Hudson |  | Kasselman Solar, LLC | CH-14726 | Catskill | Medusa | Albany | 12120 | G | 1092 | Westerlo | N |  | 7.35 | [13 empty] | NM | N | 21 Enphase Energy IQ7A-72-2-US (240V) [SI1] | 2022-01-28 | 2022-02-09 | 8 | 2022-02-09 | [14 empty] | 2022-02-11 | 2022-02-18 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-14725 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6003 | Reynolds Hill | N |  | 5.22 | [13 empty] | NM | N | 18 Enphase Energy IQ7PLUS-72-x-US (240V) | 2022-01-14 | 2022-01-24 | 6 | 2022-01-24 | [14 empty] | 2022-02-24 | 2022-03-01 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-14723 | Newburgh | Newburgh | Orange | 12550 | G | 4051 | Union Ave | N |  | 8.7 | [13 empty] | NM | N | 30 Enphase Energy IQ7PLUS-72-x-US (240V) | 2022-01-14 | 2022-01-24 | 6 | 2022-01-24 | [14 empty] | 2022-05-18 | 2022-05-19 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-14724 | Poughkeepsie | Millerton | Dutchess | 12546 | G | 7081 | Millerton | N |  | 18.27 | [13 empty] | NM | N | 63 Enphase Energy IQ7PLUS-72-x-US (240V) | 2022-01-14 | 2022-01-24 | 6 | 2022-01-24 | [14 empty] | 2022-05-19 | 2022-05-20 |  | Y
Central Hudson |  | SunCommon | CH-14758 | Poughkeepsie | Pleasant Valley | Dutchess | 12569 | G | 7024 | Tinkertown | N |  | 5.8 | [13 empty] | NM | N | 10 Enphase Energy IQ7PLUS-72-2-US (240V) [SI1] 10 Enphase Energy IQ7PLUS-72-2-US (240V) [SI1] | 2022-01-18 | 2022-01-26 | 6 | 2022-01-26 | [14 empty] | 2022-04-20 | 2022-04-25 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-14753 | Kingston | Ulster Park | Ulster | 12487 | G | 1014 | Boulevard | N |  | 4.93 | [13 empty] | NM | N | 17 Enphase Energy IQ7PLUS-72-x-US (240V) | 2022-01-18 | 2022-01-26 | 6 | 2022-01-26 | [14 empty] | 2022-04-14 | 2022-04-20 |  | Y
Central Hudson |  | Tesla Energy Ops | CH-14756 | Catskill | Athens | Greene | 12015 | G | 1074 | Coxsackie | Y |  | 11.4 | 15 | [12 empty] | NM | N | 1 Tesla 1538000-xx-y (240V) - may be a component of Powerwall+ (1850000-XX-Y) [SI1] 1 Tesla 1534000-xx-y (240V) [SI1] 3TeslaAC Powerwall 2.0 | 2022-01-18 | 2022-02-01 | 10 | 2022-02-01 | [14 empty] | 2022-02-22 | 2022-02-28 |  | Y
Central Hudson |  | PlugPV, LLC | CH-14770 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6097 | Manchester | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2022-01-31 | 2022-02-10 | 8 | 2022-02-10 | [14 empty] | 2022-06-08 | 2022-06-13 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-14779 | Kingston | Kingston | Ulster | 12401 | G | 3021 | High Falls | N |  | 8.99 | [13 empty] | NM | N | 31 Enphase Energy IQ7PLUS-72-x-US (240V) | 2022-01-19 | 2022-01-28 | 7 | 2022-01-28 | [14 empty] | 2022-03-01 | 2022-03-04 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14769 | Newburgh | Wallkill | Ulster | 12589 | G | 5041 | East Walden | N | CH-14769 | 5.76 | [13 empty] | NM | N | 1 Delta Electronics M6-TL-US (240V) [SI1] | 2022-01-19 | 2022-01-27 | 6 | 2022-01-27 | [14 empty] | 2022-04-22 | 2022-04-29 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-14768 | Poughkeepsie | Pleasant Valley | Dutchess | 12569 | G | 7023 | Tinkertown | N | CH-14768 | 6.67 | [13 empty] | NM | N | 23 Enphase Energy IQ7PLUS-72-x-US (240V) | 2022-01-19 | 2022-01-27 | 6 | 2022-01-27 | [14 empty] | 2022-04-19 | 2022-04-27 |  | Y
Central Hudson |  | Green Street Power Partners, LLC | CH-14774 | Catskill | Hannacroix | Greene | 12087 | G | 1083 | New Baltimore | N |  | 4814 | [13 empty] | CDG | Y | 29 Yaskawa Solectria Solar XGI 1500-166/166 (600V) | 2022-01-28 | 2022-02-01 | 2 | 2022-02-01 | 2022-02-01 | 2022-02-22 | 14 | 2022-03-15 | 2022-04-25 | 2022-07-20 | 60 | 21000 | 267841.9 |  | 2023-02-09 | 2023-08-01 | 2023-08-01 |  |  |  |  | N | Y
Central Hudson |  | Empire Solar Solutions | CH-14778 | Kingston | Kingston | Ulster | 12401 | G | 1022 | East Kingston | N |  | 3.77 | [13 empty] | NM | N | 13 Enphase Energy IQ7PLUS-72-x-US (240V) | 2022-01-19 | 2022-01-28 | 7 | 2022-01-28 | [14 empty] | 2022-05-18 | 2022-05-19 |  | Y
Central Hudson |  | PlugPV LLC | CH-14796 | Poughkeepsie | Salt Point | Dutchess | 12578 | G | 7011 | Hibernia | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2022-01-31 | 2022-02-10 | 8 | 2022-02-10 | [14 empty] | 2022-03-08 | 2022-03-11 |  | Y
Central Hudson |  | SunCommon | CH-14789 | Poughkeepsie | Millerton | Dutchess | 12546 | G | 7092 | Pulvers Corners | N |  | 10.15 | [13 empty] | NM | N | 35 Enphase Energy IQ7PLUS-72-2-US (240V) [SI1] | 2022-01-20 | 2022-01-31 | 7 | 2022-01-31 | [14 empty] | 2022-05-23 | 2022-05-24 |  | Y
Central Hudson |  | SolarCity dba Tesla Energy Operations, Inc. | CH-14785 | Fishkill | Garrison | Putnam | 10524 | G | 8066 | Merritt Park | N |  | 7.6 | [13 empty] | NM | N | 1 Tesla 1538000-xx-y (240V) - may be a component of Powerwall+ (1850000-XX-Y) [SI1] | 2022-02-02 | 2022-02-15 | 9 | 2022-02-15 | [14 empty] | 2022-02-23 | 2022-03-03 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14786 | Newburgh | Newburgh | Orange | 12550 | G | 4053 | Union Ave | N |  | 5.76 | [13 empty] | NM | N | 1 Delta Electronics M6-TL-US (240V) [SI1] | 2022-02-11 | 2022-02-25 | 9 | 2022-02-25 | [14 empty] | 2022-08-01 | 2022-08-04 |  | Y
Central Hudson |  | PlugPV, LLC. | CH-14788 | Newburgh | Newburgh | Orange | 12550 | G | 4022 | Coldenham | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2022-01-20 | 2022-01-31 | 7 | 2022-01-31 | [14 empty] | 2022-03-11 | 2022-03-11 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14801 | Kingston | Kingston | Ulster | 12401 | G | 2016 | Lincoln Park | Y |  | 6 | 10 | [12 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) 2TeslaAC Powerwall 2.0 | 2022-01-21 | 2022-02-04 | 10 | 2022-02-04 | [14 empty] | 2022-03-25 | 2022-03-28 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14800 | Newburgh | New Windsor | Orange | 12553 | G | 4045 | Union Ave | Y | CH-13410 | 3.8 | 5 | [12 empty] | NM | N | 1 SolarEdge Technologies SE3800H-US (240V) 1TeslaAC Powerwall 2.0 | 2022-01-21 | 2022-02-04 | 10 | 2022-02-04 | [14 empty] | 2022-06-27 | 2022-06-30 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-14799 | Newburgh | New Windsor | Orange | 12553 | G | 4042 | Union Ave | N |  | 4.64 | [13 empty] | NM | N | 16 Enphase Energy IQ7PLUS-72-x-US (240V) | 2022-01-21 | 2022-01-31 | 6 | 2022-01-31 | [17 empty] | W
Central Hudson |  | Empire Solar Solutions | CH-14798 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6097 | Manchester | N |  | 6.38 | [13 empty] | NM | N | 22 Enphase Energy IQ7PLUS-72-x-US (240V) | 2022-01-21 | 2022-01-31 | 6 | 2022-01-31 | [14 empty] | 2022-05-11 | 2022-05-11 |  | Y
Central Hudson |  | SunCommon | CH-14803 | Kingston | Shokan | Ulster | 12481 | G | 3011 | Woodstock | N |  | 22.8 | [13 empty] | NM | N | 2 SolarEdge Technologies SE11400H-US (240V) [SI1] | 2022-01-21 | 2022-01-31 | 6 | 2022-01-31 | [14 empty] | 2022-04-25 | 2022-05-04 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14807 | Kingston | High Falls | Ulster | 12440 | G | 3023 | High Falls | N | CH-09274 | 3.8 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3800H-US (240V) | 2022-01-24 | 2022-02-03 | 8 | 2022-02-03 | [14 empty] | 2022-06-02 | 2022-06-06 |  | Y
Central Hudson |  | Lighthouse Solar | CH-14810 | Newburgh | Campbell Hall | Orange | 10916 | G | 5052 | Maybrook | N |  | 9.4 | [13 empty] | NM | N | 27 Enphase Energy IQ7A-72-2-US (240V) [SI1] | 2022-01-24 | 2022-02-03 | 8 | 2022-02-03 | [14 empty] | 2022-03-21 | 2022-03-23 |  | Y
Central Hudson |  | SunCommon | CH-14820 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7051 | Rhinebeck | Y |  | 10.44 | 10 | [12 empty] | NM | N | 36 Enphase Energy IQ7PLUS-72-2-US (240V) [SI1] 2TeslaPowerwall 2 | 2022-02-08 | 2022-02-22 | 9 | 2022-02-22 | [14 empty] | 2022-04-01 | 2022-04-04 |  | Y
Central Hudson |  | PlugPV LLC | CH-14813 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6096 | Manchester | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2022-01-25 | 2022-02-07 | 9 | 2022-02-07 | [14 empty] | 2022-03-08 | 2022-03-11 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-14821 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6003 | Reynolds Hill | N |  | 3.48 | [13 empty] | NM | N | 12 Enphase Energy IQ7PLUS-72-x-US (240V) | 2022-01-25 | 2022-02-08 | 10 | 2022-02-08 | [14 empty] | 2022-02-08 | 2022-02-14 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-14826 | Newburgh | Highland | Ulster | 12528 | G | 5082 | Highland | N |  | 18.27 | [13 empty] | NM | N | 63 Enphase Energy IQ7PLUS-72-x-US (240V) | 2022-01-26 | 2022-02-08 | 9 | 2022-02-08 | [14 empty] | 2022-04-05 | 2022-04-08 |  | Y
Central Hudson |  | Kasselman Solar, LLC | CH-14825 | Catskill | Hunter | Greene | 12442 | E | 2389 | Vinegar Hill | N |  | 5.93 | [13 empty] | NM | N | 17 Enphase Energy IQ7A-72-2-US (240V) [SI1] | 2022-01-26 | 2022-02-08 | 9 | 2022-02-08 | [14 empty] | 2022-02-09 | 2022-02-15 |  | Y
Central Hudson |  | SunPower Direct (NY) | CH-14824 | Newburgh | New Windsor | Orange | 12553 | G | 4044 | Union Ave | N |  | 11.52 | [13 empty] | NM | N | 30 Enphase Energy IQ7HS-66-ACM-US (240V) [SI1] | 2022-02-08 | 2022-02-08 | 0 | 2022-02-08 | [14 empty] | 2022-06-08 | 2022-06-13 |  | Y
Central Hudson |  | SunPower Direct (NY) | CH-14823 | Fishkill | Wappingers Falls | Dutchess | 12590 | G | 8055 | North Chelsea | N |  | 8.832 | [13 empty] | NM | N | 23 Enphase Energy IQ7HS-66-ACM-US (240V) [SI1] | 2022-02-08 | 2022-02-08 | 0 | 2022-02-08 | [14 empty] | 2022-05-17 | 2022-05-18 |  | Y
Central Hudson |  | New York State Solar Farm | CH-14829 | Fishkill | Cold Spring | Putnam | 10516 | G | 8063 | Merritt Park | N |  | 14.175 | [13 empty] | NM | N | 45 SunPower SPR-X22-360-E-AC (240V) | 2022-02-10 | 2022-02-24 | 9 | 2022-02-24 | [14 empty] | 2022-09-08 | 2022-09-14 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14831 | Newburgh | Newburgh | Orange | 12550 | G | 4023 | Coldenham | N |  | 9.8 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3800H-US (240V) 1 SolarEdge Technologies SE6000H-US (240V) | 2022-01-28 | 2022-02-11 | 10 | 2022-02-11 | [14 empty] | 2022-06-10 | 2022-06-20 |  | Y
Central Hudson |  | Hudson River Renewables LLC | CH-14832 | Newburgh | West Park | Ulster | 12493 | G | 5084 | Highland | Y |  | 24.9 | 27 | [12 empty] | NM | N | 1 Sol-Ark Sol-Ark-12K-P (240V) 1 Sol-Ark Sol-Ark-12K-P (240V) 3Sol-ArkSol-Ark 12K P OD | 2022-03-11 | 2022-03-23 | 8 | 2022-03-23 | [14 empty] | 2023-05-25 | 2023-05-25 |  | Y
Central Hudson |  | Solar Liberty Energy Systems | CH-14830 | Catskill | Jewett | Greene | 12444 | E | 2389 | Vinegar Hill | N |  | 8.376 | [13 empty] | NM | N | 24 SunPower SPR-A400-G-AC (240V) [SI1] | 2022-02-10 | 2022-02-24 | 9 | 2022-02-24 | [14 empty] | 2022-08-09 | 2022-08-11 |  | Y
Central Hudson |  | Lighthouse Solar | CH-14833 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6046 | Spackenkill | N |  | 7.329 | [13 empty] | NM | N | 21 Enphase Energy IQ7A-72-2-US (240V) [SI1] | 2022-01-28 | 2022-02-10 | 9 | 2022-02-10 | [14 empty] | 2022-03-04 | 2022-03-07 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14834 | Poughkeepsie | Hyde Park | Dutchess | 12538 | G | 6075 | East Park | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2022-01-28 | 2022-02-10 | 9 | 2022-02-10 | [14 empty] | 2022-04-12 | 2022-04-19 |  | Y
Central Hudson |  | New York State Solar Farm | CH-14835 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6095 | Manchester | N |  | 4.224 | [13 empty] | NM | N | 11 SunPower SPR-M440-H-AC (240V) [SI1] | 2022-01-31 | 2022-02-10 | 8 | 2022-02-10 | [14 empty] | 2022-02-10 | 2022-02-16 |  | Y
Central Hudson |  | SunCommon | CH-14838 | Kingston | W Hurley | Ulster | 12491 | G | 3013 | Woodstock | N |  | 9.28 | [13 empty] | NM | N | 32 Enphase Energy IQ7PLUS-72-x-US (240V) | 2022-02-10 | 2022-02-24 | 9 | 2022-02-24 | [17 empty] | W
Central Hudson |  | PlugPV, LLC. | CH-14837 | Fishkill | Hopewell Junctio | Dutchess | 12533 | G | 8095 | Fishkill Plains | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2022-01-31 | 2022-02-10 | 8 | 2022-02-10 | [14 empty] | 2022-03-21 | 2022-03-23 |  | Y
Central Hudson |  | Solar Generation | CH-14836 | Newburgh | Marlboro | Ulster | 12542 | G | 5004 | Marlboro | N |  | 10.47 | [13 empty] | NM | N | 30 Enphase Energy IQ7A-72-2-US (240V) [SI1] | 2022-01-31 | 2022-02-10 | 8 | 2022-02-10 | [14 empty] | 2022-03-22 | 2022-03-28 |  | Y
Central Hudson |  | SolarCity dba Tesla Energy Operations, Inc. | CH-14848 | Poughkeepsie | Stanfordville | Dutchess | 12581 | G | 7072 | Stanfordville | Y |  | 7.6 | 7.6 | [12 empty] | NM | N | 1 Tesla 1538000-xx-y (240V) - may be a component of Powerwall+ (1850000-XX-Y) [SI1] 1Tesla1850000-10-B | 2022-02-01 | 2022-02-15 | 10 | 2022-02-15 | [14 empty] | 2022-11-07 | 2022-11-14 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14842 | Catskill | Hunter | Greene | 12442 | G | 2385 | Lawrenceville | Y |  | 9.8 | 10 | [12 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) 1 SolarEdge Technologies SE3800H-US (240V) 2TeslaAC Powerwall 2.0 | 2022-02-01 | 2022-02-15 | 10 | 2022-02-15 | [14 empty] | 2022-06-08 | 2022-06-13 |  | Y
Central Hudson |  | SolarCity dba Tesla Energy Operations, Inc. | CH-14847 | Fishkill | Cold Spring | Putnam | 10516 | G | 8087 | Tioronda | Y |  | 7.6 | 7.5 | [12 empty] | NM | N | 1 Tesla 1538000-xx-y (240V) - may be a component of Powerwall+ (1850000-XX-Y) [SI1] 1Tesla1850000-10-B | 2022-02-17 | 2022-03-01 | 7 | 2022-03-01 | [14 empty] | 2022-04-25 | 2022-04-28 |  | Y
Central Hudson |  | SolarCity dba Tesla Energy Operations, Inc. | CH-14841 | Fishkill | Hopewell Junctio | Dutchess | 12533 | G | 8091 | Fishkill Plains | Y | CH-10565 |  | 15 | [12 empty] | NM | N | 3TeslaAC Powerwall 2.0 | 2022-02-01 | 2022-02-15 | 10 | 2022-02-15 | [14 empty] | 2023-01-03 | 2023-01-04 |  | Y
Central Hudson |  | PLUGPV LLC | CH-14840 | Poughkeepsie | Millbrook | Dutchess | 12545 | G | 7025 | Tinkertown | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2022-02-01 | 2022-02-11 | 8 | 2022-02-11 | [14 empty] | 2022-03-07 | 2022-03-09 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14845 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6096 | Manchester | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2022-02-01 | 2022-02-11 | 8 | 2022-02-11 | [14 empty] | 2023-03-27 | 2023-03-30 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14844 | Newburgh | Salisbury Mls | Orange | 12577 | G | 4095 | Bethlehem Rd | N |  | 7.7 | [13 empty] | NM | N | 1 Delta Electronics M8-TL-US (240V) [SI1] | 2022-02-01 | 2022-02-11 | 8 | 2022-02-11 | [14 empty] | 2022-05-26 | 2022-06-07 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14846 | Fishkill | Wappingers Falls | Dutchess | 12590 | G | 8043 | Myers Corners | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2022-02-01 | 2022-02-11 | 8 | 2022-02-11 | [14 empty] | 2022-04-27 | 2022-05-04 |  | Y
Central Hudson |  | Suncommon | CH-14849 | Kingston | Ulster Park | Ulster | 12487 | G | 1023 | East Kingston | Y |  | 7.68 | 5 | [12 empty] | NM | N | 1 SMA America SB7.7-1SP-US-41 (240V) [SI1] 1TeslaPowerwall 2 | 2022-02-02 | 2022-02-15 | 9 | 2022-02-15 | [14 empty] | 2022-06-13 | 2022-06-16 |  | Y
Central Hudson |  | SolarCity dba Tesla Energy Operations, Inc. | CH-14852 | Newburgh | Montgomery | Orange | 12549 | G | 5072 | Montgomery | Y |  | 15.2 | 20.2 | [12 empty] | NM | N | 2 Tesla 1538000-xx-y (240V) - may be a component of Powerwall+ (1850000-XX-Y) [SI1] 2Tesla1850000-10-B1TeslaAC Powerwall 2.0 | 2022-03-21 | 2022-04-04 | 10 | 2022-04-04 | [14 empty] | 2022-07-05 | 2022-07-08 |  | Y
Central Hudson |  | Lighthouse Solar | CH-14853 | Kingston | Kerhonkson | Ulster | 12446 | G | 3083 | Kerhonkson | N |  | 11.866 | [13 empty] | NM | N | 34 Enphase Energy IQ7A-72-2-US (240V) [SI1] | 2022-02-02 | 2022-02-16 | 10 | 2022-02-16 | [14 empty] | 2022-03-09 | 2022-03-14 |  | Y
Central Hudson |  | New York State Solar Farm | CH-14858 | Kingston | Olivebridge | Ulster | 12461 | G | 3024 | High Falls | Y |  | 11.97 | 10 | [12 empty] | NM | N | 38 SunPower SPR-X22-360-E-AC (240V) 2TESLATESLA POWERWALL 2 | 2022-02-03 | 2022-02-16 | 9 | 2022-02-16 | [14 empty] | 2022-03-08 | 2022-03-11 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14854 | Newburgh | Marlboro | Ulster | 12542 | G | 5004 | Marlboro | N |  | 5.76 | [13 empty] | NM | N | 1 Delta Electronics E6-TL-US (240V) [SI1] | 2022-02-03 | 2022-02-15 | 8 | 2022-02-15 | [14 empty] | 2022-06-03 | 2022-06-07 |  | Y
Central Hudson |  | New York State Solar Farm | CH-14855 | Newburgh | Gardiner | Ulster | 12525 | G | 5011 | Modena | N | CH-14855 | 6.144 | [13 empty] | NM | N | 16 SunPower SPR-M440-H-AC (240V) [SI1] | 2022-02-03 | 2022-02-16 | 9 | 2022-02-16 | [14 empty] | 2022-02-17 | 2022-02-23 |  | Y
Central Hudson |  | PlugPV LLC | CH-14857 | Newburgh | Wallkill | Ulster | 12589 | G | 5043 | East Walden | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2022-02-03 | 2022-02-16 | 9 | 2022-02-16 | [14 empty] | 2022-03-08 | 2022-03-11 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14859 | Newburgh | Newburgh | Orange | 12550 | G | 4053 | Union Ave | N |  | 3.8 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3800H-US (240V) | 2022-03-11 | 2022-03-18 | 5 | 2022-03-18 | [14 empty] | 2022-05-26 | 2022-05-31 |  | Y
Central Hudson |  | Paradise Energy Solutions | CH-14860 | Poughkeepsie | Ancramdale | Columbia | 12503 | G | 7085 | Ancram | N |  | 21 | [13 empty] | NM | N | 3 SMA America SB7.0-1TP-US-41 (240V) [SI1] | 2022-02-22 | 2022-02-28 | 4 | 2022-02-28 | [8 empty] | 350 | 350 |  | 2022-03-07 | 2022-03-07 | 2022-03-18 | 2022-07-11 | 2022-07-18 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14861 | Newburgh | Newburgh | Orange | 12550 | G | 4053 | Union Ave | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2022-02-04 | 2022-02-18 | 10 | 2022-02-18 | [14 empty] | 2022-05-20 | 2022-05-24 |  | Y
Central Hudson |  | Delaware River Solar | CH-14862 | Kingston | Wawarsing | Ulster | 12428 | G | 3096 | Grimley Rd | N |  | 1000 | [13 empty] | CDG | Y | 1SungrowSG 3425 UD-MV | 2022-03-02 | 2022-03-09 | 5 | 2022-03-09 | 2022-03-09 | 2022-03-29 | 14 | 2022-06-02 | 2022-06-06 | 2022-08-29 | 59 | 19016.36 | 284858.45 | 1958.22 | 2023-01-11 | [5 empty] | 2023-09-27 | W | Y
Central Hudson |  | SunCommon | CH-14867 | Fishkill | Hopewell Junctio | Dutchess | 12533 | G | 8095 | Fishkill Plains | N |  | 6.96 | [13 empty] | NM | N | 24 Enphase Energy IQ7PLUS-72-2-US (240V) [SI1] | 2022-02-07 | 2022-02-22 | 10 | 2022-02-22 | [14 empty] | 2022-02-22 | 2022-02-28 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14864 | Fishkill | Wappingers Falls | Dutchess | 12590 | G | 8092 | Fishkill Plains | Y |  | 6 | 5 | [12 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) 1TeslaAC Powerwall 2.0 | 2022-02-07 | 2022-02-22 | 10 | 2022-02-22 | [17 empty] | W
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14863 | Newburgh | New Windsor | Orange | 12553 | G | 4052 | Union Ave | N |  | 5.76 | [13 empty] | NM | N | 1 Delta Electronics E6-TL-US (240V) [SI1] | 2022-02-07 | 2022-02-22 | 10 | 2022-02-22 | [14 empty] | 2022-06-10 | 2022-06-16 |  | Y
Central Hudson |  | PlugPV LLC | CH-14866 | Kingston | Greenfield Park | Ulster | 12435 | G | 3096 | Grimley Rd | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2022-02-07 | 2022-02-18 | 9 | 2022-02-18 | [17 empty] | W
Central Hudson |  | Infinity Solar Systems | CH-14865 | Newburgh | Newburgh | Orange | 12550 | G | 4015 | West Balmville | N | CH-14865 | 10.15 | [13 empty] | NM | N | 35 Enphase Energy IQ8PLUS-72-2-US (240V) [SI1] | 2022-03-22 | 2022-04-05 | 10 | 2022-04-05 | [14 empty] | 2022-07-18 | 2022-07-20 |  | Y
Central Hudson |  | New York Power Solutions | CH-14868 | Fishkill | Hopewell Junction | Dutchess | 12533 | G | 8091 | Fishkill Plains | N |  | 14.5 | [13 empty] | NM | N | 50 Enphase Energy IQ7PLUS-72-x-US (240V) | 2022-02-07 | 2022-02-22 | 10 | 2022-02-22 | [14 empty] | 2022-04-13 | 2022-04-20 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-14875 | Newburgh | Wallkill | Ulster | 12589 | G | 5041 | East Walden | N |  | 7.54 | [13 empty] | NM | N | 26 Enphase Energy IQ7PLUS-72-x-US (240V) | 2022-02-22 | 2022-03-04 | 8 | 2022-03-04 | [14 empty] | 2022-03-07 | 2022-03-11 |  | Y
Central Hudson |  | SunCommon | CH-14869 | Fishkill | Hopewell Junctio | Dutchess | 12533 | G | 8091 | Fishkill Plains | N |  | 7 | [13 empty] | NM | N | 1 SMA America SB7.0-1SP-US-41 (240V) [SI1] | 2022-04-06 | 2022-04-20 | 9 | 2022-04-20 | [14 empty] | 2023-05-01 | 2023-05-03 |  | Y
Central Hudson |  | SunCommon | CH-14872 | Poughkeepsie | Pine Plains | Dutchess | 12567 | G | 7095 | Smithfield | N |  | 7 | [13 empty] | NM | N | 1 SMA America SB7.0-1TP-US-41 (240V) [SI1] | 2022-02-08 | 2022-02-22 | 9 | 2022-02-22 | [14 empty] | 2022-07-15 | 2022-07-18 |  | Y
Central Hudson |  | SunCommon | CH-14873 | Kingston | Saugerties | Ulster | 12477 | G | 3003 | Saugerties | Y | CH-14488 |  | 5 | [12 empty] | NM | N | 1TelsaPowerwall 2 | 2022-02-08 | 2022-02-23 | 10 | 2022-02-23 | [14 empty] | 2023-02-02 | 2023-02-06 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-14874 | Fishkill | Wappingers Falls | Dutchess | 12590 | G | 8052 | North Chelsea | N |  | 9.28 | [13 empty] | NM | N | 32 Enphase Energy IQ7PLUS-72-x-US (240V) | 2022-02-08 | 2022-02-22 | 9 | 2022-02-22 | [14 empty] | 2022-04-06 | 2022-04-08 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14902 | Kingston | Kingston | Ulster | 12401 | G | 1024 | East Kingston | N |  | 13.7 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) 1 SolarEdge Technologies SE6000H-US (240V) | 2022-02-28 | 2022-03-10 | 8 | 2022-03-10 | [14 empty] | 2022-06-08 | 2022-06-13 |  | Y
Central Hudson |  | SunCommon | CH-14878 | Kingston | Port Ewen | Ulster | 12466 | G | 1012 | Boulevard | Y |  | 9.57 | 5 | [12 empty] | NM | N | 4 Enphase Energy IQ7PLUS-72-2-US (240V) [SI1] 24 Enphase Energy IQ7PLUS-72-2-US (240V) [SI1] 5 Enphase Energy IQ7PLUS-72-2-US (240V) [SI1] 1TeslaTesla Powerwall 2.0 | 2022-02-09 | 2022-02-24 | 10 | 2022-02-24 | [14 empty] | 2022-03-31 | 2022-04-01 |  | Y
Central Hudson |  | PlugPV LLC | CH-14896 | Kingston | Ruby | Ulster | 12475 | G | 2016 | Lincoln Park | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2022-02-09 | 2022-02-22 | 8 | 2022-02-22 | [14 empty] | 2022-07-25 | 2022-07-27 |  | Y
Central Hudson |  | Solar Liberty Energy Systems | CH-14907 | Catskill | Hannacroix | Greene | 12087 | G | 1083 | New Baltimore | N |  | 20.94 | [13 empty] | NM | N | 60 SunPower SPR-A400-G-AC (240V) | 2022-02-24 | 2022-03-04 | 6 | 2022-03-04 | [8 empty] | 350 | 350 |  | 2022-03-07 | 2022-03-07 | 2022-04-01 |  |  |  | W
Central Hudson |  | SunCommon | CH-14908 | Kingston | Saugerties | Ulster | 12477 | G | 3003 | Saugerties | N |  | 5.584 | [13 empty] | NM | N | 16 Enphase Energy IQ7A-72-2-US (240V) [SI1] | 2022-02-10 | 2022-02-24 | 9 | 2022-02-24 | [17 empty] | W
Central Hudson |  | SunCommon | CH-14915 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7061 | Milan | Y |  | 4.35 | 5 | [12 empty] | NM | N | 15 Enphase Energy IQ7PLUS-72-2-US (240V) [SI1] 1TeslaTesla Powerwall 2.0 | 2022-02-10 | 2022-02-24 | 9 | 2022-02-24 | [14 empty] | 2022-04-01 | 2022-04-06 |  | Y
Central Hudson |  | Solar Generation | CH-14913 | Kingston | Saugerties | Ulster | 12477 | G | 3005 | Saugerties | N |  | 100 | [13 empty] | NM | N | 4 Chint Power Systems America CPS SCA25KTL-DO/US-208 (208V) [SI1] | 2022-03-10 | 2022-03-10 | 0 | 2022-03-10 | 2022-03-10 | 2022-03-23 | 9 | [11 empty] | 2022-05-25 | 2022-05-25 |  | Y
Central Hudson |  | SunPower Direct (NY) | CH-14912 | Newburgh | Cornwall | Orange | 12518 | G | 4041 | Union Ave | N |  | 9.6 | [13 empty] | NM | N | 25 SunPower SPR-M425-H-AC (240V) [SI1] | 2022-02-10 | 2022-02-24 | 9 | 2022-02-24 | [14 empty] | 2022-04-19 | 2022-04-25 |  | Y
Central Hudson |  | New York State Solar Farm | CH-14916 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6092 | Manchester | N |  | 6.912 | [13 empty] | NM | N | 18 SunPower SPR-A425-H-AC (240V) [SI1] | 2022-02-11 | 2022-02-25 | 9 | 2022-02-25 | [14 empty] | 2022-03-11 | 2022-03-15 |  | Y
Central Hudson |  | Solar Generation Projects, LLC | CH-14917 | Kingston | Saugerties | Ulster | 12477 | G | 3005 | Saugerties | N |  | 500 | [13 empty] | CDG | Y | 5 Chint Power Systems America CPS SCH125KTL-DO/US-600 (600V) | 2022-03-14 | 2022-03-17 | 3 | 2022-03-17 | 2022-03-17 | 2022-03-29 | 8 | [5 empty] | 138230 | 118091.99 | 2022-08-19 | 2023-02-13 | 2023-02-13 | 2024-01-26 | 2024-01-30 | 2024-02-01 | 2024-04-29 | Y | Y
Central Hudson |  | JA Electric | CH-14919 | Kingston | Saugerties | Ulster | 12477 | G | 3014 | Woodstock | N |  | 20 | [13 empty] | NM | N | 2 Fronius USA Fronius Primo 10.0-1 (240V) | 2022-02-28 | 2022-02-28 | 0 | 2022-02-28 | [14 empty] | 2022-07-27 | 2022-07-29 |  | Y
Central Hudson |  | Albany Solar Solutions LLC | CH-14920 | Catskill | Coxsackie |  | 12051 | G | 1071 | Coxsackie | N |  | 10.404 | [13 empty] | NM | N | 36 Chilicon Power CP-250E-60/72-208/240-MC4 (240V) | 2022-02-14 | 2022-02-28 | 9 | 2022-02-28 | [17 empty] | W
Central Hudson |  | Kasselman Solar | CH-14921 | Fishkill | Hopewell Junctio | Dutchess | 12533 | G | 8071 | Shenandoah | N |  | 10.121 | [13 empty] | NM | N | 29 Enphase Energy IQ7A-72-2-US (240V) [SI1] | 2022-02-14 | 2022-02-28 | 9 | 2022-02-28 | [14 empty] | 2022-03-17 | 2022-03-17 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-14923 | Fishkill | Wappingers Falls | Dutchess | 12590 | G | 8056 | North Chelsea | N |  | 8.12 | [13 empty] | NM | N | 28 Enphase Energy IQ7PLUS-72-x-US (240V) | 2022-02-14 | 2022-02-28 | 9 | 2022-02-28 | [14 empty] | 2022-04-21 | 2022-04-25 |  | Y
Central Hudson |  | PlugPV, LLC. | CH-14927 | Newburgh | Highland | Ulster | 12528 | G | 5082 | Highland | N |  | 13.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) [SI1] 1 SolarEdge Technologies SE6000H-US (240V) [SI1] | 2022-02-15 | 2022-02-28 | 8 | 2022-02-28 | [14 empty] | 2022-03-29 | 2022-03-31 |  | Y
Central Hudson |  | PlugPV, LLC. | CH-14925 | Newburgh | Wallkill | Ulster | 12589 | G | 5043 | East Walden | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE11400H-US (240V) | 2022-02-15 | 2022-02-28 | 8 | 2022-02-28 | [14 empty] | 2022-03-29 | 2022-03-31 |  | Y
Central Hudson |  | New York State Solar Farm | CH-14928 | Poughkeepsie | Lagrangeville | Dutchess | 12540 | G | 6053 | Todd Hill | N |  | 10.08 | [13 empty] | NM | N | 32 SunPower SPR-X22-360-E-AC (240V) | 2022-02-15 | 2022-02-28 | 8 | 2022-02-28 | [14 empty] | 2022-03-07 | 2022-03-08 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-14940 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6046 | Spackenkill | N |  | 9.28 | [13 empty] | NM | N | 32 Enphase Energy IQ7PLUS-72-x-US (240V) | 2022-02-16 | 2022-03-03 | 10 | 2022-03-03 | [14 empty] | 2022-03-15 | 2022-03-18 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-14941 | Newburgh | Newburgh | Orange | 12550 | G | 4054 | Union Ave | N |  | 15.66 | [13 empty] | NM | N | 54 Enphase Energy IQ7PLUS-72-x-US (240V) | 2022-02-16 | 2022-03-02 | 9 | 2022-03-02 | [14 empty] | 2022-03-04 | 2022-03-07 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-14937 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6062 | Inwood Ave | N |  | 5.8 | [13 empty] | NM | N | 20 Enphase Energy IQ8PLUS-72-2-US (240V) [SI1] | 2022-03-31 | 2022-04-13 | 9 | 2022-04-13 | [14 empty] | 2022-07-18 | 2022-07-20 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14935 | Newburgh | Newburgh | Orange | 12550 | G | 4045 | Union Ave | N |  | 3.8 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3800H-US (240V) | 2022-03-04 | 2022-03-15 | 7 | 2022-03-15 | [8 empty] | 350 | 350 |  | 2022-04-26 | 2022-04-26 | 2022-05-10 | 2022-07-06 | 2022-07-08 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-14939 | Newburgh | Newburgh | Orange | 12550 | G | 5001 | Marlboro | N |  | 8.12 | [13 empty] | NM | N | 28 Enphase Energy IQ7PLUS-72-x-US (240V) | 2022-02-16 | 2022-03-02 | 9 | 2022-03-02 | [14 empty] | 2022-03-14 | 2022-03-17 |  | Y
Central Hudson |  | New York Power Solutions | CH-14930 | Newburgh | New Windsor | Orange | 12553 | G | 4046 | Union Ave | N |  | 5.8 | [13 empty] | NM | N | 20 Enphase Energy IQ7PLUS-72-2-US (240V) [SI1] | 2022-02-17 | 2022-03-01 | 7 | 2022-03-01 | [14 empty] | 2022-04-25 | 2022-04-28 |  | Y
Central Hudson |  | PlugPV, LLC. | CH-14936 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6011 | Sand Dock | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE11400H-US (240V) | 2022-02-16 | 2022-03-01 | 8 | 2022-03-01 | [14 empty] | 2022-03-29 | 2022-04-06 |  | Y
Central Hudson |  | PlugPV, LLC. | CH-14938 | Newburgh | Highland | Ulster | 12528 | G | 5082 | Highland | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2022-02-16 | 2022-03-02 | 9 | 2022-03-02 | [14 empty] | 2022-03-21 | 2022-03-23 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-14945 | Newburgh | Newburgh | Orange | 12550 | G | 4051 | Union Ave | N |  | 7.25 | [13 empty] | NM | N | 25 Enphase Energy IQ7PLUS-72-x-US (240V) | 2022-02-17 | 2022-03-03 | 9 | 2022-03-03 | [14 empty] | 2022-03-15 | 2022-03-18 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-14944 | Kingston | Saugerties | Ulster | 12477 | G | 3003 | Saugerties | N |  | 4.06 | [13 empty] | NM | N | 14 Enphase Energy IQ7PLUS-72-x-US (240V) | 2022-02-17 | 2022-03-03 | 9 | 2022-03-03 | [14 empty] | 2022-06-14 | 2022-06-17 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14942 | Newburgh | New Windsor | Orange | 12553 | G | 4046 | Union Ave | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2022-02-17 | 2022-03-03 | 9 | 2022-03-03 | [14 empty] | 2022-07-08 | 2022-07-12 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-14943 | Newburgh | Wallkill | Ulster | 12589 | G | 5041 | East Walden | N |  | 5.8 | [13 empty] | NM | N | 20 Enphase Energy IQ7PLUS-72-x-US (240V) | 2022-02-17 | 2022-03-03 | 9 | 2022-03-03 | [14 empty] | 2022-06-16 | 2022-06-20 |  | Y
Central Hudson |  | PLUGPV LLC | CH-14949 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6095 | Manchester | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2022-03-04 | 2022-03-15 | 7 | 2022-03-15 | [14 empty] | 2022-04-12 | 2022-04-19 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-14948 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6043 | Spackenkill | N |  | 10.44 | [13 empty] | NM | N | 36 Enphase Energy IQ7PLUS-72-x-US (240V) | 2022-02-17 | 2022-03-03 | 9 | 2022-03-03 | [14 empty] | 2022-04-06 | 2022-04-08 |  | Y
Central Hudson |  | Kasselman Solar, LLC | CH-14946 | Kingston | Olivebridge | Ulster | 12461 | G | 3024 | High Falls | N |  | 6.631 | [13 empty] | NM | N | 19 Enphase Energy IQ7A-72-2-US (240V) [SI1] | 2022-03-03 | 2022-03-15 | 8 | 2022-03-15 | [14 empty] | 2022-03-17 | 2022-03-18 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-14947 | Poughkeepsie | Red Hook | Dutchess | 12571 | G | 7061 | Milan | N | CH-14947 | 11.02 | [13 empty] | NM | N | 38 Enphase Energy IQ7PLUS-72-x-US (240V) | 2022-02-17 | 2022-03-03 | 9 | 2022-03-03 | [14 empty] | 2022-06-20 | 2022-06-21 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-14951 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6056 | Todd Hill | N |  | 5.8 | [13 empty] | NM | N | 20 Enphase Energy IQ7PLUS-72-x-US (240V) | 2022-02-17 | 2022-03-03 | 9 | 2022-03-03 | [14 empty] | 2022-04-21 | 2022-04-25 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-14950 | Newburgh | Plattekill | Ulster | 12568 | G | 5013 | Modena | N |  | 6.96 | [13 empty] | NM | N | 24 Enphase Energy IQ7PLUS-72-x-US (240V) | 2022-02-17 | 2022-03-03 | 9 | 2022-03-03 | [14 empty] | 2022-04-22 | 2022-04-25 |  | Y
Central Hudson |  | Eden DevCo LP | CH-14850 | Newburgh | Wallkill | Ulster | 12589 | G | 5043 | East Walden | Y |  | 5000 | 5000 | [12 empty] | CDG | Y | 2Power ElectronicsHEMK FS3190K2Power ElectronicsFS3190K | 2022-03-29 | 2022-04-04 | 4 | 2022-04-04 | 2022-04-04 | 2022-04-12 | 6 |  |  |  |  | 19070 | [9 empty] | W
Central Hudson |  | Kasselman Solar, LLC | CH-14952 | Kingston | Ellenville | Ulster | 12428 | G | 3095 | Grimley Rd | Y |  | 15.2 | 7.6 | [12 empty] | NM | N | 2 SolarEdge Technologies SE7600H-US (240V) [SI1] 1SolarEdge TechnologiesSE7600H-US (PRISM) | 2022-03-18 | 2022-03-25 | 5 | 2022-03-25 | [14 empty] | 2022-05-04 | 2022-05-10 |  | Y
Central Hudson |  | PlugPV LLC | CH-14953 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6092 | Manchester | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2022-02-18 | 2022-03-04 | 9 | 2022-03-04 | [14 empty] | 2022-03-18 | 2022-03-31 |  | Y
Central Hudson |  | Kasselman Solar, LLC | CH-14954 | Catskill | Ravena | Albany | 12143 | G | 1081 | New Baltimore | N |  | 9.772 | [13 empty] | NM | N | 28 Enphase Energy IQ7A-72-2-US (240V) [SI1] | 2022-03-04 | 2022-03-15 | 7 | 2022-03-15 | [14 empty] | 2022-05-19 | 2022-05-19 |  | Y
Central Hudson |  | PlugPV, LLC | CH-14957 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6073 | East Park | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2022-02-22 | 2022-03-04 | 8 | 2022-03-04 | [14 empty] | 2022-03-09 | 2022-03-14 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-14955 | Kingston | Krumville | Ulster | 12461 | G | 3024 | High Falls | N |  | 5.8 | [13 empty] | NM | N | 20 Enphase Energy IQ7PLUS-72-x-US (240V) | 2022-02-22 | 2022-03-04 | 8 | 2022-03-04 | [14 empty] | 2022-04-27 | 2022-05-04 |  | Y
Central Hudson |  | murphy solar and central air | CH-14958 | Catskill | East Durham | Greene | 12423 | G | 2043 | South Cairo | N |  | 7 | [13 empty] | NM | N | 1 SMA America SB7000TL-US-22 (240V) | 2022-03-07 | 2022-03-16 | 7 | 2022-03-16 | [17 empty] | N
Central Hudson |  | PlugPV LLC | CH-14956 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6095 | Manchester | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2022-02-22 | 2022-03-04 | 8 | 2022-03-04 | [14 empty] | 2022-05-05 | 2022-05-10 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-14959 | Kingston | Tillson | Ulster | 12486 | G | 3022 | High Falls | N |  | 5.51 | [13 empty] | NM | N | 19 Enphase Energy IQ8PLUS-72-2-US (240V) [SI1] | 2022-04-05 | 2022-04-05 | 0 | 2022-04-05 | [14 empty] | 2022-07-11 | 2022-07-18 |  | Y
Central Hudson |  | Solar Generation | CH-14960 | Kingston | Bearsville | Ulster | 12409 | G | 3012 | Woodstock | N | CH-11561 | 4.64 | [13 empty] | NM | N | 16 Enphase Energy IQ7PLUS-72-x-US (240V) | 2022-02-24 | 2022-03-04 | 6 | 2022-03-04 | [14 empty] | 2022-04-07 | 2022-04-13 |  | Y
Central Hudson |  | New York Power Solutions | CH-14962 | Newburgh | New Windsor | Orange | 12553 | G | 4044 | Union Ave | N |  | 14.5 | [13 empty] | NM | N | 50 Enphase Energy IQ7PLUS-72-x-US (240V) | 2022-02-24 | 2022-03-04 | 6 | 2022-03-04 | [14 empty] | 2022-08-16 | 2022-08-19 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14963 | Newburgh | Marlboro | Ulster | 12542 | G | 5003 | Marlboro | N | CH-14963 | 7.68 | [13 empty] | NM | N | 1 Delta Electronics M8-TL-US (240V) [SI1] | 2022-02-24 | 2022-03-04 | 6 | 2022-03-04 | [8 empty] | 350 | 350 |  | 2022-05-09 | 2022-05-09 | 2022-05-17 | 2022-05-31 | 2022-06-02 |  | Y
Central Hudson |  | Solar Generation Projects LLC | CH-14961 | Newburgh | New Paltz | Ulster | 12561 | G | 5023 | Ohioville | N |  | 2625 | [13 empty] | CDG | Y | 21 Chint Power Systems America CPS SCH125KTL-DO/US-600 (600V) | 2022-03-18 | 2022-03-22 | 2 | 2022-03-22 | 2022-03-22 | 2022-04-11 | 14 | 2022-05-23 | 2022-06-03 | 2022-08-29 | 60 | 20746.55 | 7630942.45 | [7 empty] | 2023-04-17 | W
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14965 | Kingston | Wawarsing | Ulster | 12489 | G | 3071 | Honk Falls | N |  | 10.56 | [13 empty] | NM | N | 1 Delta Electronics M5-TL-US (240V) [SI1] 1 Delta Electronics M6-TL-US (240V) [SI1] | 2022-02-25 | 2022-03-07 | 6 | 2022-03-07 | [17 empty] | W
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14964 | Newburgh | Maybrook |  | 12543 | G | 5052 | Maybrook | N |  | 7.68 | [13 empty] | NM | N | 1 Delta Electronics M8-TL-US (240V) [SI1] | 2022-02-25 | 2022-03-07 | 6 | 2022-03-07 | [17 empty] | W
Central Hudson |  | Gottschalk Solutions | CH-14966 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6073 | East Park | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000 (240V) | 2022-02-28 | 2022-03-09 | 7 | 2022-03-09 | [14 empty] | 2022-03-10 | 2022-03-14 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-14967 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6002 | Reynolds Hill | N |  | 5.8 | [13 empty] | NM | N | 20 Enphase Energy IQ7PLUS-72-x-US (240V) | 2022-02-28 | 2022-03-09 | 7 | 2022-03-09 | [14 empty] | 2022-11-29 | 2022-12-02 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14971 | Newburgh | Newburgh | Orange | 12550 | G | 5001 | Marlboro | Y | CH-13714 | 3.84 | [13 empty] | NM | N | 1 Delta Electronics M4-TL-US (240V) [SI1] | 2022-02-28 | 2022-03-09 | 7 | 2022-03-09 | [14 empty] | 2022-07-07 | 2022-07-12 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-14969 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6056 | Todd Hill | N |  | 9.57 | [13 empty] | NM | N | 33 Enphase Energy IQ7PLUS-72-x-US (240V) | 2022-02-28 | 2022-03-09 | 7 | 2022-03-09 | [14 empty] | 2022-04-14 | 2022-04-20 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-14970 | Fishkill | Wappingers Falls | Dutchess | 12590 | G | 8055 | North Chelsea | N |  | 10.73 | [13 empty] | NM | N | 37 Enphase Energy IQ7PLUS-72-x-US (240V) | 2022-02-28 | 2022-03-09 | 7 | 2022-03-09 | [8 empty] | 350 | 350 |  | 2022-03-09 | 2022-03-09 | 2022-06-29 | 2022-05-17 | 2022-05-18 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-14972 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6003 | Reynolds Hill | N |  | 7.2 | [13 empty] | NM | N | 30 Enphase Energy IQ7-60-x-US (240V) | 2022-02-28 | 2022-03-10 | 8 | 2022-03-10 | [14 empty] | 2022-05-17 | 2022-05-18 |  | Y
Central Hudson |  | New York State Solar Farm | CH-14975 | Kingston | Cragsmoor | Ulster | 12420 | G | 3078 | Greenfield Rd | N |  | 3.84 | [13 empty] | NM | N | 10 SunPower SPR-M425-H-AC (240V) [SI1] | 2022-02-28 | 2022-03-11 | 9 | 2022-03-11 | [14 empty] | 2022-03-14 | 2022-03-17 |  | Y
Central Hudson |  | PlugPV LLC | CH-14968 | Newburgh | Newburgh | Orange | 12550 | G | 4022 | Coldenham | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2022-02-28 | 2022-03-09 | 7 | 2022-03-09 | [14 empty] | 2022-04-08 | 2022-04-13 |  | Y
Central Hudson |  | SunCommon | CH-14976 | Poughkeepsie | Pleasant Valley | Dutchess | 12569 | G | 7025 | Tinkertown | Y | CH-01810 |  | 5 | [12 empty] | NM | N | 1TeslaTesla Back Up Gateway 2 | 2022-02-28 | 2022-03-11 | 9 | 2022-03-11 | [14 empty] | 2022-05-09 | 2022-05-11 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-14973 | Newburgh | Cornwall Hdsn | Orange | 12520 | G | 4043 | Union Ave | N |  | 5.51 | [13 empty] | NM | N | 19 Enphase Energy IQ7PLUS-72-x-US (240V) | 2022-02-28 | 2022-03-10 | 8 | 2022-03-10 | [14 empty] | 2022-05-11 | 2022-05-12 |  | Y
Central Hudson |  | PlugPV, LLC. | CH-14974 | Poughkeepsie | Poughkeepsie | Dutchess | 12601 | G | 6068 | Inwood Ave | N |  | 16 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) 1 SolarEdge Technologies SE6000H-US (240V) | 2022-03-11 | 2022-03-18 | 5 | 2022-03-18 | [8 empty] | 350 | 350 |  | 2022-03-22 | 2022-03-22 | 2022-05-09 | 2022-06-07 | 2022-06-09 |  | Y
Central Hudson |  | PlugPV, LLC | CH-14977 | Catskill | Rensselaervle | Albany | 12147 | G | 1092 | Westerlo | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2022-03-01 | 2022-03-11 | 8 | 2022-03-11 | [14 empty] | 2022-03-23 | 2022-04-01 |  | Y
Central Hudson |  | PlugPV, LLC. | CH-14980 | Poughkeepsie | Pleasant Valley | Dutchess | 12569 | G | 6051 | Todd Hill | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2022-03-01 | 2022-03-11 | 8 | 2022-03-11 | [14 empty] | 2022-04-14 | 2022-04-20 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-14979 | Fishkill | Stormville | Dutchess | 12582 | G | 8093 | Fishkill Plains | N |  | 8.7 | [13 empty] | NM | N | 30 Enphase Energy IQ7PLUS-72-x-US (240V) | 2022-03-01 | 2022-03-11 | 8 | 2022-03-11 | [14 empty] | 2022-04-04 | 2022-04-06 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-14978 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6044 | Spackenkill | N |  | 12.18 | [13 empty] | NM | N | 42 Enphase Energy IQ7PLUS-72-x-US (240V) | 2022-03-01 | 2022-03-11 | 8 | 2022-03-11 | [14 empty] | 2022-05-03 | 2022-05-09 |  | Y
Central Hudson |  | SunPower Direct (NY) | CH-14981 | Fishkill | Stormville | Dutchess | 12582 | G | 8095 | Fishkill Plains | Y |  | 14.592 | 6.4 | [12 empty] | NM | N | 38 SunPower SPR-M425-H-AC (240V) [SI1] 1SunVaultSV-BASE-13-12-A | 2022-04-08 | 2022-04-25 | 10 | 2022-04-25 | [14 empty] | 2022-08-25 | 2022-08-31 |  | Y
Central Hudson |  | Solar Alchemy, Inc. | CH-14985 | Kingston | High Falls | Ulster | 12440 | G | 3024 | High Falls | N |  | 7.83 | [13 empty] | NM | N | 27 Enphase Energy IQ7PLUS-72-x-US (240V) | 2022-03-02 | 2022-03-14 | 8 | 2022-03-14 | [14 empty] | 2022-07-05 | 2022-07-08 |  | Y
Central Hudson |  | SunCommon | CH-14986 | Catskill | Greenville | Greene | 12083 | G | 2061 | Freehold | Y |  | 13 | 10 | [12 empty] | NM | N | 1 SMA America SB7.0-1TP-US-41 (240V) [SI1] 1 SMA America SB6.0-1TP-US-41 (240V) [SI1] 2TeslaTesla Powerwall 2 | 2022-03-02 | 2022-03-16 | 10 | 2022-03-16 | [14 empty] | 2022-05-09 | 2022-05-11 |  | Y
Central Hudson |  | Kasselman Solar, LLC | CH-14983 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7013 | Hibernia | N |  | 8.725 | [13 empty] | NM | N | 25 Enphase Energy IQ7A-72-2-US (240V) [SI1] | 2022-03-22 | 2022-03-29 | 5 | 2022-03-29 | [14 empty] | 2022-04-04 | 2022-04-06 |  | Y
Central Hudson |  | New York State Solar Farm | CH-14987 | Newburgh | Wallkill | Ulster | 12589 | G | 5041 | East Walden | N |  | 9.45 | [13 empty] | NM | N | 30 SunPower SPR-X22-360-E-AC (240V) | 2022-03-02 | 2022-03-14 | 8 | 2022-03-14 | [14 empty] | 2022-04-07 | 2022-04-13 |  | Y
Central Hudson |  | PlugPV, LLC. | CH-14982 | Fishkill | Hopewell Junction | Dutchess | 12533 | G | 8072 | Shenandoah | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2022-03-02 | 2022-03-11 | 7 | 2022-03-11 | [14 empty] | 2022-04-18 | 2022-04-21 |  | Y
Central Hudson |  | Solar Generation | CH-14984 | Kingston | West Hurley | Ulster | 12491 | G | 3013 | Woodstock | N |  | 14.658 | [13 empty] | NM | N | 42 Enphase Energy IQ7A-72-2-US (240V) [SI1] | 2022-03-16 | 2022-03-23 | 5 | 2022-03-23 | [8 empty] | 350 | 350 |  | 2022-03-28 | 2022-03-28 | 2022-05-06 | 2022-05-26 | 2022-05-31 |  | Y
Central Hudson |  | Trinity Solar | CH-14988 | Newburgh | Montgomery | Orange | 12549 | G | 5071 | Montgomery | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2022-03-15 | 2022-03-22 | 5 | 2022-03-22 | [14 empty] | 2022-07-06 | 2022-07-11 |  | Y
Central Hudson |  | Sunrise Power Solutions | CH-14991 | Newburgh | New Windsor | Orange | 12553 | G | 4097 | Bethlehem Rd | N |  | 100 | [13 empty] | NM | Y | 1 SMA America STP 50-US-41 (480V) 1 SMA America STP 50-US-41 (480V) | 2022-03-11 | 2022-03-16 | 3 | 2022-03-16 | 2022-03-16 | 2022-04-05 | 14 | [11 empty] | 2024-06-27 | 2024-06-27 |  | Y | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14990 | Catskill | Catskill | Greene | 12414 | G | 2002 | North Catskill | N |  | 9.8 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) 1 SolarEdge Technologies SE3800H-US (240V) | 2022-03-03 | 2022-03-15 | 8 | 2022-03-15 | [14 empty] | 2022-08-23 | 2022-08-25 |  | Y
Central Hudson |  | Wiltshire Renewable Energy Systems LLC DBA Empire Solar and Electric | CH-14998 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6042 | Spackenkill | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2022-03-23 | 2022-03-29 | 4 | 2022-03-29 | [14 empty] | 2022-05-24 | 2022-05-25 |  | Y
Central Hudson |  | SunCommon | CH-14994 | Poughkeepsie | Millerton | Dutchess | 12546 | G | 7081 | Millerton | N |  | 6.38 | [13 empty] | NM | N | 22 Enphase Energy IQ7PLUS-72-2-US (240V) [SI1] | 2022-03-04 | 2022-03-16 | 8 | 2022-03-16 | [14 empty] | 2022-05-23 | 2022-05-24 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-14992 | Kingston | Kingston | Ulster | 12401 | G | 1022 | East Kingston | N |  | 3.8 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3800H-US (240V) | 2022-03-04 | 2022-03-15 | 7 | 2022-03-15 | [14 empty] | 2022-06-01 | 2022-06-03 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-14995 | Fishkill | Hopewell Junction | Dutchess | 12533 | G | 8096 | Fishkill Plains | N | CH-22735 | 11.31 | [13 empty] | NM | N | 39 Enphase Energy IQ7PLUS-72-x-US (240V) | 2022-03-04 | 2022-03-16 | 8 | 2022-03-16 | [14 empty] | 2022-03-23 | 2022-03-24 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-14996 | Newburgh | New Windsor | Orange | 12553 | G | 4092 | Bethlehem Rd | N |  | 9.28 | [13 empty] | NM | N | 32 Enphase Energy IQ7PLUS-72-x-US (240V) | 2022-03-04 | 2022-03-16 | 8 | 2022-03-16 | [14 empty] | 2022-04-14 | 2022-04-21 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-14997 | Newburgh | Newburgh | Orange | 12550 | G | 4012 | West Balmville | N |  | 7.54 | [13 empty] | NM | N | 26 Enphase Energy IQ7PLUS-72-x-US (240V) | 2022-03-04 | 2022-03-16 | 8 | 2022-03-16 | [14 empty] | 2022-04-28 | 2022-05-05 |  | Y
Central Hudson |  | PlugPV, LLC. | CH-14993 | Newburgh | Newburgh | Orange | 12550 | G | 4014 | West Balmville | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2022-03-04 | 2022-03-15 | 7 | 2022-03-15 | [14 empty] | 2022-06-13 | 2022-06-28 |  | Y
Central Hudson |  | PlugPV, LLC | CH-15000 | Newburgh | Highland | Ulster | 12528 | G | 5013 | Modena | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2022-03-07 | 2022-03-16 | 7 | 2022-03-16 | [14 empty] | 2022-04-21 | 2022-04-25 |  | Y
Central Hudson |  | Lighthouse Solar | CH-14999 | Kingston | Stone Ridge | Ulster | 12484 | G | 3023 | High Falls | N |  | 12.215 | [13 empty] | NM | N | 35 Enphase Energy IQ7A-72-2-US (240V) [SI1] | 2022-03-07 | 2022-03-16 | 7 | 2022-03-16 | [14 empty] | 2022-03-30 | 2022-04-04 |  | Y
Central Hudson |  | New York State Solar Farm | CH-15001 | Newburgh | Marlboro | Ulster | 12542 | G | 5003 | Marlboro | N |  | 4.725 | [13 empty] | NM | N | 15 SunPower SPR-E20-327-E-AC (240V) [SI1] | 2022-03-07 | 2022-03-16 | 7 | 2022-03-16 | [14 empty] | 2022-03-22 | 2022-03-23 |  | Y
Central Hudson |  | PLUGPV LLC | CH-15012 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6065 | Inwood Ave | N | CH-15012 | 3.8 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3800H-US (240V) | 2022-03-08 | 2022-03-18 | 8 | 2022-03-18 | [14 empty] | 2022-03-22 | 2022-04-01 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-15005 | Kingston | Tillson | Ulster | 12486 | G | 3022 | High Falls | N |  | 9.28 | [13 empty] | NM | N | 32 Enphase Energy IQ7PLUS-72-x-US (240V) | 2022-03-08 | 2022-03-18 | 8 | 2022-03-18 | [14 empty] | 2022-05-02 | 2022-05-09 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-15010 | Newburgh | Marlboro | Ulster | 12542 | G | 5004 | Marlboro | N |  | 9.8 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) 1 SolarEdge Technologies SE3800H-US (240V) | 2022-03-08 | 2022-03-18 | 8 | 2022-03-18 | [14 empty] | 2022-05-26 | 2022-05-31 |  | Y
Central Hudson |  | Kasselman Solar, LLC | CH-15003 | Catskill | Greenville | Greene | 12083 | G | 2061 | Freehold | N |  | 3.839 | [13 empty] | NM | N | 11 Enphase Energy IQ7A-72-2-US (240V) [SI1] | 2022-03-08 | 2022-03-18 | 8 | 2022-03-18 | [14 empty] | 2022-04-08 | 2022-04-13 |  | Y
Central Hudson |  | Kassleman Solar | CH-15004 | Catskill | Westerlo | Albany | 12193 | G | 1092 | Westerlo | N |  | 7.6 | 7.6 | [12 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) [SI1] 1SolarEdge TechnologiesSE7600H-US PRISM | 2022-06-30 | 2022-07-13 | 8 | 2022-07-13 | [14 empty] | 2023-01-17 | 2023-01-23 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-15006 | Kingston | Kerhonkson | Ulster | 12446 | G | 3081 | Kerhonkson | N |  | 4.64 | [13 empty] | NM | N | 16 Enphase Energy IQ7PLUS-72-x-US (240V) | 2022-03-08 | 2022-03-18 | 8 | 2022-03-18 | [14 empty] | 2022-04-18 | 2022-04-21 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-15007 | Kingston | Rosendale | Ulster | 12472 | G | 3021 | High Falls | N |  | 6.67 | [13 empty] | NM | N | 23 Enphase Energy IQ7PLUS-72-x-US (240V) | 2022-03-08 | 2022-03-18 | 8 | 2022-03-18 | [14 empty] | 2022-04-25 | 2022-04-28 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-15002 | Poughkeepsie | Hyde Park | Dutchess | 12538 | G | 6074 | East Park | N | CH-15002 | 11.31 | [13 empty] | NM | N | 39 Enphase Energy IQ7PLUS-72-x-US (240V) | 2022-03-29 | 2022-04-11 | 9 | 2022-04-11 | [14 empty] | 2022-06-01 | 2022-06-06 |  | Y
Central Hudson |  | PlugPV, LLC. | CH-15009 | Fishkill | Hopewell Junction | Dutchess | 12533 | G | 8091 | Fishkill Plains | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2022-03-08 | 2022-03-18 | 8 | 2022-03-18 | [14 empty] | 2022-04-22 | 2022-04-25 |  | Y
Central Hudson |  | PlugPV, LLC. | CH-15008 | Fishkill | Fishkill | Dutchess | 12524 | G | 8016 | Forgebrook | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2022-03-08 | 2022-03-18 | 8 | 2022-03-18 | [14 empty] | 2022-04-18 | 2022-04-21 |  | Y
Central Hudson |  | PlugPV LLC | CH-15011 | Catskill | Athens | Greene | 12015 | G | 2002 | North Catskill | N |  | 13.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) 1 SolarEdge Technologies SE6000H-US (240V) | 2022-03-08 | 2022-03-18 | 8 | 2022-03-18 | [14 empty] | 2022-06-09 | 2022-06-13 |  | Y
Central Hudson |  | Apex Roofing LLC | CH-15016 | Poughkeepsie | Hyde Park | Dutchess | 12538 | G | 7041 | Staatsburg | N |  | 4.64 | [13 empty] | NM | N | 16 Enphase Energy IQ7PLUS-72-2-US (240V) [SI1] | 2022-04-22 | 2022-05-05 | 9 | 2022-05-05 | [14 empty] | 2022-05-05 | 2022-05-10 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-15015 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6046 | Spackenkill | N | CH-13032 | 2.64 | [13 empty] | NM | N | 11 Enphase Energy IQ7-60-x-US (240V) | 2022-03-09 | 2022-03-18 | 7 | 2022-03-18 | [14 empty] | 2022-05-06 | 2022-05-11 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-15014 | Fishkill | Cold Spring | Putnam | 10516 | G | 8063 | Merritt Park | N |  | 6.09 | [13 empty] | NM | N | 21 Enphase Energy IQ8PLUS-72-2-US (240V) [SI1] | 2022-03-25 | 2022-04-06 | 8 | 2022-04-06 | [14 empty] | 2022-05-17 | 2022-05-19 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-15013 | Newburgh | Newburgh | Orange | 12550 | G | 4022 | Coldenham | N |  | 3.84 | [13 empty] | NM | N | 1 Delta Electronics M4-TL-US (240V) [SI1] | 2022-03-09 | 2022-03-18 | 7 | 2022-03-18 | [17 empty] | W
Central Hudson |  | PlugPV LLC | CH-15017 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6096 | Manchester | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2022-03-09 | 2022-03-18 | 7 | 2022-03-18 | [14 empty] | 2022-04-25 | 2022-04-28 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-15022 | Fishkill | Wappingers Falls | Dutchess | 12590 | G | 8023 | Knapps Corners | N |  | 11.6 | [13 empty] | NM | N | 40 Enphase Energy IQ7PLUS-72-x-US (240V) | 2022-03-10 | 2022-03-18 | 6 | 2022-03-18 | [14 empty] | 2022-05-27 | 2022-06-02 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-15021 | Newburgh | New Windsor | Orange | 12553 | G | 4094 | Bethlehem Rd | N |  | 9.6 | [13 empty] | NM | N | 1 Delta Electronics M10-TL-US (240V) [SI1] | 2022-03-10 | 2022-03-18 | 6 | 2022-03-18 | [14 empty] | 2022-06-08 | 2022-06-20 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-15019 | Fishkill | Hopewell Junction | Dutchess | 12533 | G | 8094 | Fishkill Plains | N |  | 9.8 | [13 empty] | NM | N | 1 SolarEdge Technologies SE3800H-US (240V) 1 SolarEdge Technologies SE6000H-US (240V) | 2022-03-10 | 2022-03-18 | 6 | 2022-03-18 | [14 empty] | 2022-05-13 | 2022-05-19 |  | Y
Central Hudson |  | PlugPV, LLC | CH-15020 | Fishkill | Wappingers Falls | Dutchess | 12590 | G | 8054 | North Chelsea | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2022-03-10 | 2022-03-18 | 6 | 2022-03-18 | [14 empty] | 2022-05-23 | 2022-05-24 |  | Y
Central Hudson |  | New York State Solar Farm | CH-15027 | Newburgh | Montgomery | Orange | 12549 | G | 5073 | Montgomery | N |  | 14.805 | [13 empty] | NM | N | 47 SunPower SPR-X22-360-E-AC (240V) | 2022-03-11 | 2022-03-18 | 5 | 2022-03-18 | [14 empty] | 2022-03-24 | 2022-04-05 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-15024 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6094 | Manchester | N |  | 5.76 | [13 empty] | NM | N | 1 Delta Electronics M6-TL-US (240V) [SI1] | 2022-03-11 | 2022-03-18 | 5 | 2022-03-18 | [17 empty] | W
Central Hudson |  | Sunrun Installation Services, Inc. | CH-15023 | Kingston | Woodstock | Ulster | 12498 | G | 3013 | Woodstock | Y |  | 7.6 | 10 | [12 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) 2TeslaAC Powerwall 2.0 | 2022-03-11 | 2022-03-18 | 5 | 2022-03-18 | [14 empty] | 2022-06-08 | 2022-06-13 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-15026 | Kingston | Lake Katrine | Ulster | 12449 | G | 2011 | Lincoln Park | Y |  | 7.6 | 7.6 | [12 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) 1SolarEdge TechnologiesSE7600H-USM3 | 2022-04-07 | 2022-04-20 | 8 | 2022-04-20 | [14 empty] | 2023-01-09 | 2023-01-12 |  | Y
Central Hudson |  | PlugPV, LLC | CH-15028 | Fishkill | Poughkeepsie | Dutchess | 12603 | G | 8022 | Knapps Corners | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2022-03-21 | 2022-03-29 | 6 | 2022-03-29 | [14 empty] | 2022-04-13 | 2022-04-20 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-15029 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6094 | Manchester | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2022-03-14 | 2022-03-22 | 6 | 2022-03-22 | [17 empty] | W
Central Hudson |  | Infinity Solar Systems | CH-15030 | Fishkill | Wappingers Falls | Dutchess | 12590 | G | 8051 | North Chelsea | N |  | 12.47 | [13 empty] | NM | N | 43 Enphase Energy IQ8PLUS-72-2-US (240V) [SI1] | 2022-03-29 | 2022-04-07 | 7 | 2022-04-07 | [17 empty] | W
Central Hudson |  | Sunrun Installation Services, Inc. | CH-15031 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6003 | Reynolds Hill | N |  | 6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) | 2022-03-14 | 2022-03-22 | 6 | 2022-03-22 | [14 empty] | 2022-05-25 | 2022-05-31 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-15034 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6093 | Manchester | N |  | 6.96 | [13 empty] | NM | N | 24 Enphase Energy IQ7PLUS-72-x-US (240V) | 2022-03-15 | 2022-03-22 | 5 | 2022-03-22 | [14 empty] | 2022-04-28 | 2022-05-05 |  | Y
Central Hudson |  | Seed Solar | CH-15037 | Catskill | Preston Holw | Albany | 12469 | G | 1092 | Westerlo | N |  | 7.6 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) | 2022-04-20 | 2022-05-03 | 9 | 2022-05-03 | [14 empty] | 2022-05-04 | 2022-05-10 |  | Y
Central Hudson |  | PlugPV LLC | CH-15039 | Catskill | Earlton | Greene | 12058 | G | 1071 | Coxsackie | N |  | 12 | [13 empty] | NM | N | 1 SolarEdge Technologies SE6000H-US (240V) 1 SolarEdge Technologies SE6000H-US (240V) | 2022-03-15 | 2022-03-22 | 5 | 2022-03-22 | [8 empty] | 350 | 350 |  | 2022-03-22 | 2022-03-22 | 2022-03-30 | 2022-06-29 | 2022-07-07 |  | Y
Central Hudson |  | Solar Generation | CH-15033 | Kingston | High Falls | Ulster | 12440 | G | 3024 | High Falls | N | CH-15033 | 9.772 | [13 empty] | NM | N | 28 Enphase Energy IQ7A-72-2-US (240V) [SI1] | 2022-03-21 | 2022-03-29 | 6 | 2022-03-29 | [14 empty] | 2022-06-07 | 2022-06-09 |  | Y
Central Hudson |  | PlugPV LLC | CH-15041 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6003 | Reynolds Hill | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2022-03-15 | 2022-03-23 | 6 | 2022-03-23 | [14 empty] | 2022-04-13 | 2022-04-20 |  | Y
Central Hudson |  | PlugPV, LLC | CH-15040 | Poughkeepsie | Rhinebeck | Dutchess | 12572 | G | 7056 | Rhinebeck | N |  | 5 | [13 empty] | NM | N | 1 SolarEdge Technologies SE5000H-US (240V) | 2022-03-15 | 2022-03-23 | 6 | 2022-03-23 | [14 empty] | 2022-05-09 | 2022-06-10 |  | Y
Central Hudson |  | PLUGPV LLC | CH-15032 | Fishkill | Beacon | Dutchess | 12508 | G | 8087 | Tioronda | N |  | 11.4 | [13 empty] | NM | N | 1 SolarEdge Technologies SE7600H-US (240V) 1 SolarEdge Technologies SE3800H-US (240V) | 2022-03-15 | 2022-03-22 | 5 | 2022-03-22 | [14 empty] | 2022-09-09 | 2022-09-14 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-15035 | Fishkill | Wappingers Falls | Dutchess | 12590 | G | 8091 | Fishkill Plains | N |  | 4.93 | [13 empty] | NM | N | 17 Enphase Energy IQ7PLUS-72-x-US (240V) | 2022-03-15 | 2022-03-22 | 5 | 2022-03-22 | [14 empty] | 2022-04-04 | 2022-04-06 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-15036 | Poughkeepsie | Tivoli | Dutchess | 12583 | G | 7062 | Milan | N |  | 3.77 | [13 empty] | NM | N | 13 Enphase Energy IQ7PLUS-72-x-US (240V) | 2022-03-15 | 2022-03-22 | 5 | 2022-03-22 | [14 empty] | 2022-05-16 | 2022-05-17 |  | Y
Central Hudson |  | SunCommon | CH-15044 | Kingston | Kingston | Ulster | 12401 | G | 1011 | Boulevard | N |  | 5.8 | [13 empty] | NM | N | 20 Enphase Energy IQ7PLUS-72-x-US (240V) | 2022-03-23 | 2022-03-29 | 4 | 2022-03-29 | [14 empty] | 2022-07-07 | 2022-07-12 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-15043 | Newburgh | Newburgh | Orange | 12550 | G | 4022 | Coldenham | N |  | 4.35 | [13 empty] | NM | N | 15 Enphase Energy IQ7PLUS-72-x-US (240V) | 2022-03-15 | 2022-03-23 | 6 | 2022-03-23 | [14 empty] | 2022-05-16 | 2022-05-17 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-15038 | Poughkeepsie | Poughkeepsie | Dutchess | 12603 | G | 6056 | Todd Hill | N |  | 11.6 | [13 empty] | NM | N | 40 Enphase Energy IQ7PLUS-72-x-US (240V) | 2022-03-15 | 2022-03-22 | 5 | 2022-03-22 | [14 empty] | 2022-05-03 | 2022-05-09 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-15042 | Fishkill | Beacon | Dutchess | 12508 | G | 8087 | Tioronda | N |  | 4.35 | [13 empty] | NM | N | 15 Enphase Energy IQ7PLUS-72-x-US (240V) | 2022-03-23 | 2022-03-29 | 4 | 2022-03-29 | [14 empty] | 2022-03-30 | 2022-04-01 |  | Y
Central Hudson |  | New York Power Solutions | CH-15046 | Newburgh | Montgomery | Orange | 12549 | G | 5073 | Montgomery | N |  | 14.658 | [13 empty] | NM | N | 42 Enphase Energy IQ7A-72-2-US (240V) [SI1] | 2022-03-16 | 2022-03-24 | 6 | 2022-03-24 | [14 empty] | 2022-09-19 | 2022-09-23 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-15045 | Newburgh | Montgomery | Orange | 12549 | G | 5073 | Montgomery | N |  | 10.15 | [13 empty] | NM | N | 35 Enphase Energy IQ7PLUS-72-x-US (240V) | 2022-03-16 | 2022-03-23 | 5 | 2022-03-23 | [14 empty] | 2022-04-25 | 2022-04-28 |  | Y
Central Hudson |  | PLUGPV LLC | CH-15047 | Fishkill | Fishkill | Dutchess | 12524 | G | 8065 | Merritt Park | N |  | 10 | [13 empty] | NM | N | 1 SolarEdge Technologies SE10000H-US (240V) | 2022-03-16 | 2022-03-24 | 6 | 2022-03-24 | [14 empty] | 2022-04-19 | 2022-04-25 |  | Y
Central Hudson |  | Infinity Solar Systems | CH-15048 | Fishkill | Wappingers Falls | Dutchess | 12590 | G | 8046 | Myers Corners | N |  | 12.76 | [13 empty] | NM | N | 44 Enphase Energy IQ8PLUS-72-2-US (240V) [SI1] | 2022-03-24 | 2022-04-06 | 9 | 2022-04-06 | [14 empty] | 2022-07-20 | 2022-07-27 |  | Y
Central Hudson |  | SunCommon | CH-15051 | Poughkeepsie | Tivoli | Dutchess | 12583 | G | 7054 | Rhinebeck | Y |  | 16.8 | 5 | [12 empty] | NM | N | 2 ABB PVI-5000-OUTD-US-Z (240V) 1 ABB PVI-3.0-OUTD-S-US-Z (240 V) 1 SMA America SB3.8-1SP-US-40 (240V) [SI1] 1TeslaPowerwall 2 | 2022-04-04 | 2022-04-14 | 8 | 2022-04-14 | [14 empty] | 2022-06-03 | 2022-06-08 |  | Y
Central Hudson |  | Sunrun Installation Services, Inc. | CH-15058 | Fishkill | Wappingers Falls | Dutchess | 12590 | G | 8052 | North Chelsea | Y |  | 3.8 | 3.8 | [12 empty] | NM | N | 1 SolarEdge Technologies SE3800H-US (240V) 1SolarEdge TechnologiesSE3800H-USM3 | 2022-04-18 | 2022-04-27 | 7 | 2022-04-27 | [14 empty] | 2022-06-06 | 2022-06-08 |  | Y
Central Hudson |  | Empire Solar Solutions | CH-15053 | Poughkeepsie | Staatsburg | Dutchess | 12580 | G | 7041 | Staatsburg | N |  | 6.38 | [13 empty] | NM | N | 22 Enphase Energy IQ7PLUS-72-x-US (240V) | 2022-03-17 | 2022-03-24 | 5 | 2022-03-24 | [14 empty] | 2022-04-25 | 2022-04-28 |  | Y