## Summary
Case: 19-E-0065, 19-G-0066
Draft Updated Response to DPS Interrogatories – Set CSS Petition - DPS-1
This workbook contains 16 attachments supporting the Company updated responses to its April 2023 petition regarding costs associated with its CORE project
Attachment Link | Attachment Name
Attachment 1 | Planned and Actual Costs by Element of Expense
Attachment 2 | Planned and Actual Costs by Cost Category
Attachment 3 | Planned and Actual Cost Variance Descriptions
Attachment 4 | Details of Program Change Requests Approved by the Change Control Board
Attachment 5 | Summary of Planned and Actual Extensions and Interfaces
Attachment 6 | Planned Interfaces
Attachment 7 | Final Actual Interfaces
Attachment 8 | Planned Extensions
Attachment 9 | Final Actual Extensions
Attachment 10 | List of External Labor Vendor Change Orders and Unplanned Costs (Redacted)
Attachment 11 | Original and Updated Cost Model (Assuming original and actual Extension and Interface counts in Attachment 5)
Attachment 12 | Billing Exception Remediation Details
Attachment 13 | PSC Metric Performance Post Go-Live
Attachment 14 | Summary Costs of Peer Utilities
Attachment 15 | Original Cost Benefit Analysis
Attachment 16 | Updated Cost Benefit Analysis

## Attachment 1
Planned and Actual Costs by Element of Expense | [7 empty] | Click Here to Retun To Summary Sheet
Table 1: 2019 Original Estimated Capital Expenditures from 2018 to 2023 ($000)
EOE | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | Total
Labor | 4545 | 3968 | 14783 | 20763 | 21564 | 7206 | 72829
M&S | - | - | 53702 | - | - | - | 53702
A/P | 6818 | 5952 | 39657 | 46543 | 56129 | 22867 | 177966
Other | - | 5333 | 11187 | 15176 | 16811 | 5685 | 54192
Overheads | - | - | 6652 | 9343 | 9704 | 3243 | 28942
AFUDC | 663 | 1035 | 3638 | 8563 | 14892 | 4761 | 33552
Total | 12026 | 16288 | 129619 | 100388 | 119100 | 43762 | 421183
Table 2: 2023 Updated Actual Capital Expenditures from 2017 to 2024 ($000)
EOE | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | Total
Labor | 212.5116 | 1913.6484 | 4226.2579 | 10379.2571 | 20009.4362 | 21258.1891 | 25417.1045 | 2619.2934 | 86035.6982
M&S | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A/P | 664.7652 | 3903.765 | 7630.624 | 27177.3211 | 61834.947 | 89520.1027 | 67803.8496 | 9404.0541 | 267939.4286
Other | 1767.0164 | 53770.8736 | 289.1956 | 9621.646 | 12989.6173 | 13812.8396 | 4165.2927 | 203.8181 | 96620.2993
Overheads | 37.9653 | 601.0329 | 1200.5241 | 2414.8473 | 5010.5283 | 6404.9244 | 10027.684 | 1139.6105 | 26837.1169
AFUDC | 16.1567 | 287.3641 | 805.4844 | 2356.8098 | 5303.7014 | 12770.202 | 10444.2828 | 0 | 31984.0013
Total | 2698.4152 | 60476.6839 | 14152.0861 | 51949.8814 | 105148.2302 | 143766.2579 | 117858.2135 | 13366.7762 | 509416.5443
Table 3: 2023 Billing Exception Remediation Actual a Capital Expenditures from 2019 to 2024 ($000)
EOE | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | Total
Labor | - | - | - | - | - | 1320.9898 | 4178.1271 | - | 5499.117
M&S | - | - | - | - | - | 2.1274 | 53.7187 | - | 55.846
A/P | - | - | - | - | - | 2304.8815 | 13706.2289 | - | 16011.1104
Other | - | - | - | - | - | 0 | 0 | - | 0
Overheads | - | - | - | - | - | 595.8985 | 1642.9214 | - | 2238.8199
AFUDC | - | - | - | - | - | 994.8106 | -1367.8667 | - | -373.0561
Total | - | - | - | - | - | 5218.7079 | 18213.1293 | - | 23431.8372
*Billing Exception Remediation costs are a subset of the total costs in Table 2 above.

## Attachment 2
Planned and Actual Costs by Cost Category | [7 empty] | Click Here to Retun To Summary Sheet
Cost Category | 2017 Actual | 2018 Actual | 2019 Actual | 2020 Actual | 2021 Actual | 2022 Actual | 2023 Actual | 2024 Actual | Total Actual Costs | Total Planned from 2018 Business Plan | Variance Planned vs. Actual | % Variance Planned vs. Actual
Internal Labor | 250476.9224 | 2514681.3259 | 5426782.0469 | 12794104.411 | 25019964.4864 | 25746225.1656 | 29623739.9366 | 3758903.948 | 105134878.2429 | 101878454.984 | 3256423.2589 | 3.196%
External Labor | 664765.22 | 3903764.9525 | 7630623.9623 | 27177321.1108 | 61834946.9731 | 87215221.1499 | 54097620.7025 | 9404054.0975 | 251928318.1686 | 149610335.1657 | 102317983.0029 | 68.39%
Billing Exceptions | 0 | 0 | 0 | 0 | 0 | 5218707.88 | 18213129.34 | 0 | 23431837.22 | 0 | 23431837.22 | 100%
Contingency | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35186513.2725 | -35186513.2725 | NA - Contingency Allocated
Hardware | 0 | 54854.0659 | 109155.2768 | 1353899.8903 | 4634332.8286 | 3224240.8887 | -106020.9297 | 0 | 9270462.0207 | 11819616.4065 | -2549154.3857 | -21.57%
Software | 0 | 53712342.8308 | 27782.3721 | 8083453.3547 | 8119978.9354 | 9181127.6322 | 3526253.0585 | 203818.125 | 82854756.3087 | 84764722.0424 | -1909965.7336 | -2.253%
AFUDC | 16156.71 | 287364.07 | 805484.44 | 2356809.82 | 5303701.41 | 11775391.46 | 11812149.52 | 0 | 32357057.43 | 33551282.0369 | -1194224.6069 | -3.559%
Other | 1767016.3576 | 3676.6749 | 152257.9919 | 184292.8031 | 235305.5164 | 1405343.7335 | 691341.8421 | 0 | 4439234.9195 | 4372076 | 67158.9195 | 1.536%
Total | 2698415.21 | 60476683.92 | 14152086.09 | 51949881.39 | 105148230.15 | 143766257.91 | 117858213.47 | 13366776.1705 | 509416544.3105 | 421182999.9079 | 88233544.4026 | 20.95%

## Attachment 3
Planned and Actual Cost Variance Descpriptions |  |  |  |  | Click Here to Retun To Summary Sheet
Cost Category | Total Actual Costs | Total Planned from 2018 Business Plan | Variance Planned vs. Actual | % Variance Planned vs. Actual | Variance Descriptions
Internal Labor | 105134878.2429 | 101878454.984 | 3256423.2589 | 3.196% | Additional internal labor costs for staff to support additional project effort and risk mitigation, including build, testing and deployment of additional integration and extensions.
External Labor | 251928318.1686 | 149610335.1657 | 102317983.0029 | 68.39% | Additional external labor costs associated with vendor change orders, to support additional project effort and risk mitigation, including build, testing and deployment of additional integration and extensions.
Billing Exceptions | 23431837.22 | 0 | 23431837.22 | 100% | After learning of challenges created by the transition of pending billing exceptions from the existing CIS to a new CIS through benchmarking in 2021, the Company embarked on an initiative to reduce billing exceptions to near zero before Go-Live through the use of augmented vendor staff.
Contingency | 0 | 35186513.2725 | -35186513.2725 | NA - Contingency Allocated | Project contingency of 15% capital spending for labor, travel, and labor overheads. No contingency was applied to hardware and software.
Hardware | 9270462.0207 | 11819616.4065 | -2549154.3857 | -21.57% | Actual hardware costs were less than planned.
Software | 82854756.3087 | 84764722.0424 | -1909965.7336 | -2.253% | Actual software costs were less than planned.
AFUDC | 32357057.43 | 33551282.0369 | -1194224.6069 | -3.559% | Allowance for Funds Used During Construction (AFUDC) costs were less than planned.
Other | 4439234.9195 | 4372076 | 67158.9195 | 1.536% | Lower than expected Facilities costs due to COVID related remote work, offset by training platform and equipment costs.
Total | 509416544.3105 | 421182999.9079 | 88233544.4026 | 20.95%

## Attachment 4
Details of Program Change Requests Approved by the Change Control Board |  |  |  | Click Here to Retun To Summary Sheet
Enhancement Summary
Category | Total | Description
Business Change | 14 | Change Request resulted due to changes in the legacy production system during the implementation period which required CORE changes for solution alignment.
Operational or Technical Efficiency | 38 | Change Request resulted due to impacts significantly disruptive to the existing business or technical operations.
Customer Experience | 29 | Change Request resulted due to ensuring a consistent or enhanced customer experience when compared to the existing customer experience.
Integration Complexities | 37 | Change Request resulted due to additional legacy interfaces identified or new complexities not initially identified.
Regulatory Requirement | 34 | Change Request resulted due to changes in regulatory requirements requiring incorporation to remain compliant.
Unplanned Customer Value | 9 | Change Request resulted from the project identifying customer benefits by implementing additional changes not initially in project scope.
Total | 161
Program Change Requests
ID | Title | Description | Priority | Category
388537 | Financial Report Changes | Changes to Financial Reports based on identified differences between CC&B & legacy reporting mechanisms | 4 - Mandatory | Business Change
158068 | Escalate Option in Emergency Application | New functionality implemented by the business to disable the escalation option for users during storm outage scenarios to prevent impacts to system performance | 3 - High | Business Change
134163 | City of New York - Supplemental Usage File Data and the Meter Exchange File | Additional data requested to be in the monthly file | 3 - High | Business Change
130787 | Updates to Move In / Move Out Process | Changes to proactive email campaigns related to self service move / in move out processes | 3 - High | Business Change
129267 | Website Changes for Value Stack Customers | Adjustments made to current webservices to support Value Stack | 3 - High | Business Change
126086 | Steam Customer Service Changes | New configuration updates to be aligned with updated Steam solution | 3 - High | Business Change
122777 | Commercial Account Integration with Automated Call Vendor | Integration to send file to third party vendor | 3 - High | Business Change
117182 | Landlord Web Portal Preferences and Notifications | Requirement to provide specific landlord and tenant notifications | 4 - Mandatory | Business Change
115740 | Steam Energy Usage Data Visualization Interface | Creation of a centralized data source for billing and data visualization to improve customer experience | 3 - High | Business Change
108867 | CECONY/ORU KIOSK Upgrade | CC&B integration updates required due to the external Kiosk system upgrades | 3 - High | Business Change
99004 | Electric Shock Tickets | UI updates to pre-populate outage ticket information | 4 - Mandatory | Business Change
80884 | Web Market Supply Calculator | New functionality on Web Self Service to create the MSC calculator implemented during the program. | 4 - Mandatory | Business Change
80876 | Web Market Supply Calculator | New functionality on Web Self Service to create the NYISO Day Ahead calculator implemented during the program. | 4 - Mandatory | Business Change
80870 | Web - Start/Stop Enhancements | New functionality added to web self service during implementation to allow predictive address searching for the start service process. | 3 - High | Business Change
115445 | Credit Card Payments Collected in Field | Automate customer credit card payments process | 2 - Medium | Customer Experience
427424 | Customer Preferences | Move the system of record of customer preferences to the CIS to provide a comprehensive view of the customer. | 3 - High | Customer Experience
387661 | Prevent High Bills from sending to Customers. | Flag accounts with bills above a specific threshold for individual review to prevent a negative customer experience of receiving a high bill. | 3 - High | Customer Experience
346385 | Web Experience for Religious Customers | Align the Religious customer experience to commercial for self service to support viewing and downloading of energy usage | 4 - Mandatory | Customer Experience
253386 | Updates to Website to Support Landlord Experience | Additional functionality to support self service "Leave on for landlord" program | 4 - Mandatory | Customer Experience
232734 | Web Access for Third Parties | New functionality implemented in 2021 in response stakeholder requests to access customer data in a customer authorized secure manner | 3 - High | Customer Experience
206838 | Digital Notifications for Arrears, and Payment Agreements | Additional customer notifications regarding payment assistance | 4 - Mandatory | Customer Experience
202148 | Payment Extension Pause Autopay Integration | Customers on Autopay can receive Payment Extension by pausing Autopay. | 3 - High | Customer Experience
182048 | Web Start/Stop/Transfer Updates | New functionality to align to the decision to enhance the Start/Stop functionality | 4 - Mandatory | Customer Experience
171991 | Call Center Account Specific Alerts | Additional logic required to display customer account alerts for call center agents, improving customer service | 3 - High | Customer Experience
159079 | Change Frequency of Electric Customer Data | Business requested updates to customer data be refreshed more frequently (subset of attributes from weekly to daily) | 3 - High | Customer Experience
135149 | Bill Message and Letters Updates for Credit and Collections | Updates to collections communication verbiage | 3 - High | Customer Experience
133726 | Web Interface Changes to Support Report Outage | New functionality to align with current report outage solution | 3 - High | Customer Experience
122779 | Field Activity Customer Surveys | Generate file of detailed list customers transactions for survey purposes | 3 - High | Customer Experience
97605 | Customer Initiated Rate Change | Updated solution design to allow CSRs to create rate change case | 4 - Mandatory | Customer Experience
80872 | Low Income Customer Identification & Program Tier Information | Additional capability to identify low income customers and provide their tier information quickly to provide relevant billing information | 3 - High | Customer Experience
78800 | Pending Start Service Email Confirmation | Customer notification is sent when the start is pending after the expected date to alert customers that no action is required from them. | 3 - High | Customer Experience
78799 | Proactive Moving Campaign | Campaign is sent to vendors to perform proactive notifications to customers who may discontinue service. | 3 - High | Customer Experience
78326 | Manage Programs - Life Sustaining Equipment (LSE) Form | Improved customer experience to allow customers to track the status of their Life Sustaining Equipment consideration request. | 4 - Mandatory | Customer Experience
78325 | Manage Programs - Medical Hardship Form | Improved customer experience to allow customers to submit and track Medical Hardship programs on My Account and updates on approval process for back office | 4 - Mandatory | Customer Experience
78303 | Manage Programs - Concern Form (EBD - Elderly, Blind, Disabled) | Improved customer experience to allow customers to submit enrollment request for Concern Programs on My Account and check for eligibility | 4 - Mandatory | Customer Experience
78291 | Start Service - Cold AMI Meter Start Self Service | Enhancement to self service to allow remote turn on during a start service when AMI meter status is cold | 3 - High | Customer Experience
78290 | Manage Start/Stop - Transfer Service - Cold AMI Meter Transfer | Updates to allow remote turn on during a transfer service when AMI meter status is cold | 3 - High | Customer Experience
78120 | Send notification at outage completion | New functionality added during the implementation to provide notifications when an outage is completed to customers. | 3 - High | Customer Experience
78119 | CECONY & ORU: Functionality Added to Web for NYSIO day ahead pricing. | Updates during the implementation to provide NYISO day ahead pricing to self service. | 4 - Mandatory | Customer Experience
78118 | CECONY: Functionality Added to CSS during project to send data to the Web regarding Complex Billing | Update during the implementation to provide complex billing information & user rate information to self service. | 4 - Mandatory | Customer Experience
78116 | ORU: Functionality Added to CIMS during project to send data to the Web regarding Complex Billing | Update in CIMS during the implementation to provide complex billing information & user rate information to self service. | 4 - Mandatory | Customer Experience
77416 | Low Income Program - Manage Programs | Update User Interface to identify customers that are low income and provide insight on energy savings in the UI | 3 - High | Customer Experience
77415 | Level Payment Plan - Manage Programs | Updates to webservice calls to allow Level Payment Plan enrollment | 3 - High | Customer Experience
466551 | Adding Financial Transaction Data to Payment Report | Gap identified in the reporting to include additional financial information | 4 - Mandatory | Integration Complexities
344237 | Add Boro & Muni to GIS Interface | Required fields missing from the interface file. | 3 - High | Integration Complexities
308691 | Control Total Emails for Outbound Payment Files | Total values missing which will prevent Treasury from releasing the files to banks. | 4 - Mandatory | Integration Complexities
256528 | Data Analytics Interface | Interface alignment across operating companies resulted in additional fields required to designate customer Op Co alignment. | 3 - High | Integration Complexities
255028 | Updates to Integrations to Support Replevin Process | Implement internal changes identified in review with Replevin vendor | 2 - Medium | Integration Complexities
192081 | Interface to calculate Max KVA Attribute | Additional information needed in the interface to calculate the value. | 3 - High | Integration Complexities
186914 | Bill Vendor Preference Update File needs to be split | Individual files required by Operating Company. Unable to send in 1 file as assumed. | 3 - High | Integration Complexities
186544 | Bill Vendor Split Letter file by operating company | Individual files required by Operating Company. Unable to send in 1 file as assumed. | 3 - High | Integration Complexities
186543 | Bill Vendor Split the bill file into multiple files | Individual files required by Operating Company. Unable to send in 1 file as assumed. | 3 - High | Integration Complexities
185204 | NYISO Reconciliation for Net Metered Account | Additional data element required in interface to report net metered usage to the NYISO | 3 - High | Integration Complexities
182541 | Bill Vendor Files for Bill Print (3 files) | Individual files required by Operating Company. Unable to send in 1 file as assumed. | 3 - High | Integration Complexities
171704 | Bill Vendor File Updates | Integration required to process file related to customer communications | 3 - High | Integration Complexities
171241 | Bill Vendor - Electronic Payment Agreement Return File | Integration required to process return file for Operating Company | 3 - High | Integration Complexities
171234 | Bill Vendor - eFail Return File | Integration required to process return file for Operating Company | 3 - High | Integration Complexities
171233 | Bill Vendor - Electronic Payment Agreement Return File | Integration required to process return file for Operating Company | 3 - High | Integration Complexities
159209 | Street Light Portal Tables | Additional tables needed to store Street Light information | 3 - High | Integration Complexities
136055 | Meter Asset Management Interface | Integration required to manage meter exchange and update meter data | 4 - Mandatory | Integration Complexities
135140 | Print Labels for Special Mailings | Integration required to print mailing labels to customers | 4 - Mandatory | Integration Complexities
134181 | Billing Data File Sent for Payments | Duplicate file required for payment processing system | 3 - High | Integration Complexities
134077 | Work Management Interface Design | Integration for Work Mgmt System due to compatibility issues with the mainframe | 4 - Mandatory | Integration Complexities
130951 | Bill Vendor Account Change File | One time extraction file to inform vendor of matching legacy account number with new account number | 3 - High | Integration Complexities
127060 | Streetlight Repair Portal | Integration required to process repair request in portal | 3 - High | Integration Complexities
122936 | Field Service Interface Changes | Integrations required for managing field activity orders | 3 - High | Integration Complexities
110872 | Meter Sync Interface Changes | Integration for systems impacting meters installation to be in sync | 3 - High | Integration Complexities
110133 | Create / Cancel Work Release Update | New web service required for asynchronous communication between systems | 3 - High | Integration Complexities
109887 | Legacy ID Process | Additional functionality to generate legacy IDs required for processes | 3 - High | Integration Complexities
109540 | Home Banking File from Bank | Additional mapping fields required in file | 3 - High | Integration Complexities
109508 | Retrieval of Account Level Info | Integration required to send account information to application that manages ditch repair orders | 3 - High | Integration Complexities
95130 | Changes to Bill Presentation Interface | Updates required to the interface for bill messaging | 3 - High | Integration Complexities
93930 | CECONY Value Stack Subscription Interface Changes | Integration required to send file and apply credits applied to customer's account | 2 - Medium | Integration Complexities
82096 | Meter Asset Validation Updates | Integration required to send Field Activity | 3 - High | Integration Complexities
81881 | Autopay Date Security | Create control guidelines and validation rules around Auto Pay start and end dates and dollar amount withdrawal limits | 3 - High | Integration Complexities
80900 | Outage Management Integration Updates | Additional interfaces needed to communicate outage information and send emergency orders to Outage Management Application | 3 - High | Integration Complexities
80899 | Demand Management System | Integration required to receive multiple inputs vs. single input | 3 - High | Integration Complexities
80897 | Gas Retail Choice Integration | Integration needed to provide billing history data. | 3 - High | Integration Complexities
80896 | Share My Data Changes | Self Service integrates with a system being decommissioned to share retail choice data. | 4 - Mandatory | Integration Complexities
80886 | Day Ahead NYISO Pricing | Web self service pulls this information from a system being decommissioned. A new integration is needed to gather the data | 4 - Mandatory | Integration Complexities
122787 | 1099 Tax Filing Processes | Yearly tax files required to send to financial system for processing | 3 - High | Operational or Technical Efficiency
438358 | Bill Usage Portal Enhancements | Updates to the usage portal to calculate usage and expediate any manual billing of complex customers. | 4 - Mandatory | Operational or Technical Efficiency
391563 | ORU Low Income Benefits and Payments Processing | Additional integrations to process $200k daily low income benefits payments. | 4 - Mandatory | Operational or Technical Efficiency
233375 | Security Improvements for Account Access | Additional security needed to prevent users from accessing unauthorized accounts. | 3 - High | Operational or Technical Efficiency
226447 | Debt Transfer and Write Off Updates | Updates to the write off and transfer customer debt processes as a results of the final customer start / stop solution | 3 - High | Operational or Technical Efficiency
221913 | Converting Inactive Gas Replevin Cases | Updates to replevin case conversion to allow for continued court processing | 3 - High | Operational or Technical Efficiency
199541 | ACH Refunds | Functionality to auto generate checks | 3 - High | Operational or Technical Efficiency
196817 | Meter Test Data Sync Update to Generate Notification for Passed Meter Test | Decision to align across operating companies requires additional work | 2 - Medium | Operational or Technical Efficiency
186920 | Interfaces for O&R Gas Forecasting | Decision to move O&R Gas Forecasting to TCIS requiring integration to CCB that were not originally planned for. | 4 - Mandatory | Operational or Technical Efficiency
182535 | Bill Vendor Address File | Exception handling to automatically process addresses when bar code is not generated. | 3 - High | Operational or Technical Efficiency
180116 | Changes to Reporting Data Extraction | New data extractions needed to support existing business reporting. | 1- Low | Operational or Technical Efficiency
178432 | Automate the existing Manual Process for Payment Cancellations | Automate the existing manual process to stop payments from EBS and cancel in CIS | 3 - High | Operational or Technical Efficiency
175733 | NY PSC Staff Security Updates | Additional solution component needed to prevent the NYC PSC staff from viewing RECO accounts. Requirement did not exist when operating in separate CIS systems. | 4 - Mandatory | Operational or Technical Efficiency
172001 | Print Payment Receipts | Print receipts for walk in center payments | 3 - High | Operational or Technical Efficiency
171998 | Automate Cancellation of Payments when Case in cancelled | Updates to the check cancellation process to reduce manual work | 3 - High | Operational or Technical Efficiency
171994 | Dispute amount handling in Customer Service cases | Automate exception handling by displaying case relevant information, improving customer service while disputes are in progress | 4 - Mandatory | Operational or Technical Efficiency
170320 | Inactive ESCO Handling | Automate the generation of exceptions that require review for dormant ESCOs | 1- Low | Operational or Technical Efficiency
169680 | Data Extraction Required for Reporting | New data extracts needed to support existing business reporting. | 3 - High | Operational or Technical Efficiency
168367 | Theft of Service Solution | Automate bill calculation for theft cases to streamline manual and long process | 4 - Mandatory | Operational or Technical Efficiency
159199 | Rev Demo Integration | Nightly sync process is required to ensure most accurate data exists in the Redeem environment. | 3 - High | Operational or Technical Efficiency
135054 | New Report Requirements Part 1 | New data extractions needed to support existing business reporting. | 3 - High | Operational or Technical Efficiency
134752 | New Report Requirements Part 2 | New data extractions needed to support existing business reporting. | 3 - High | Operational or Technical Efficiency
133790 | Supervisor Out of Office To Do assignment process | User interface updates to track out-of-office users affecting scheduling exceptions work | 3 - High | Operational or Technical Efficiency
133787 | Delegation of Authority Approval process | Functionality to streamline approval process for exception work management | 3 - High | Operational or Technical Efficiency
133782 | Social Service Agency Portal | Portal updates to clarify balances for low income participants that receive agency benefits | 3 - High | Operational or Technical Efficiency
132004 | New Reporting Requirements | New data extractions needed to support existing business reporting. | 3 - High | Operational or Technical Efficiency
124042 | Calculate and Store Avg. Gas Use for Reporting | Additional logic required to support business reporting | 3 - High | Operational or Technical Efficiency
117887 | Retire Additional Legacy System | Updates to new CIS due to decommissioning legacy application | 3 - High | Operational or Technical Efficiency
115662 | Steam Self Service Integration Changes | All Steam Web Self Service backend API's need updates to align with the future technology architecture | 3 - High | Operational or Technical Efficiency
109894 | Field Investigation Form Changes | Automate field investigation forms such as approvals for process efficiency | 4 - Mandatory | Operational or Technical Efficiency
109893 | Financial Statement Form Printing | Printing functionality required for customer form | 4 - Mandatory | Operational or Technical Efficiency
108273 | Replevin Case Lifecycle | Automate Replevin process to avoid intensive manual tracking and end user tasks | 3 - High | Operational or Technical Efficiency
80868 | Bill Print Extract Standardization | A streamlined approach was identified for supporting bill print across both companies to reduce total cost of ownership | 3 - High | Operational or Technical Efficiency
76973 | CCB upgrade to version 2.8 | Upgrade current Oracle CC&B software to Version 2.8 | 3 - High | Operational or Technical Efficiency
76180 | Payment Arrangement Request Process Flow enhancement | Update User Interface to streamline the flow for the user to process Payment Arrangement Request without needing to toggle between multiple screens to reduce call handling time | 2 - Medium | Operational or Technical Efficiency
71602 | Unclaimed Credit Portal | Creation of a custom portal to display information about accounts currently in an active escheatment case | 3 - High | Operational or Technical Efficiency
71599 | Payment Transfer-Cancel Approval Process | Automate the approval process for payment(s) cancellation and/or transfer of payments | 4 - Mandatory | Operational or Technical Efficiency
71598 | Stop all services during Severance | Enhancement to disconnect all customer services when entering the severance process. | 4 - Mandatory | Operational or Technical Efficiency
219343 | Add Over Capacity Alarm for Gas Methane Censors | New gas alarm functionality implemented supporting NYC law requiring censors | 4 - Mandatory | Regulatory Requirement
172714 | CDG Bill Message | Functionality to automate the bill messages from CDG marketers to print on customer bills from Net Metering Order | 4 - Mandatory | Regulatory Requirement
80875 | Web Submetering Calculator | New functionality on Web Self Service to create the Submetering calculator implemented during the program to support sub metering companies who by law cannot exceed Con Edison price | 4 - Mandatory | Regulatory Requirement
133721 | Rate Pilot Updates | Updates to process for DPS approved rate pilot related data interfaces | 3 - High | Regulatory Requirement
466553 | CECONY Rate Case Update for RY1 | Update to CECONY Rates for regulatory changes that occurred in 2023 | 4 - Mandatory | Regulatory Requirement
438483 | Methane Sensors | Updates to address new requirements for methane sensors tracking, to support customer safety. | 4 - Mandatory | Regulatory Requirement
388144 | NYISO Reconciliation Data Source | New data source for conversion to populate ICAP tags for EDI transactions | 4 - Mandatory | Regulatory Requirement
361128 | RECO - New Rates #2 | Additional changes identified from the new RECO rates introduced during the project | 4 - Mandatory | Regulatory Requirement
359406 | RECO - New Rates #1 | New RECO rates introduced during the project | 4 - Mandatory | Regulatory Requirement
252126 | ORU Regulatory Rate Case Changes | Require rate case changes during the implementation. | 4 - Mandatory | Regulatory Requirement
232480 | Retail Access Changes for ESCO Payment | Additional integrations needed to monthly payment of ESCOs for consolidated billing | 4 - Mandatory | Regulatory Requirement
212689 | Use of Customer Preferred Pronouns - PSL 31a McKinney Law | New regulatory requirements to refer to customers based on preferred pronoun. | 4 - Mandatory | Regulatory Requirement
206738 | New Regulatory Requirements | Additional requirements added to CEO certification matrix during the program. | 4 - Mandatory | Regulatory Requirement
206688 | Net Metering / Successor Changes | Updates & changes to rates | 4 - Mandatory | Regulatory Requirement
196319 | Customer Usage System Changes (CUS) | Changes to Customer Usage System (CUS) due to rate changes in 2020/2021 | 4 - Mandatory | Regulatory Requirement
182055 | Weekly Account Info from CC&B to Energy Efficiency Platform To Support Local Law 84 Benchmarking | Consolidation of the Daily and weekly files but due to vendor limitations this requires new integrations | 3 - High | Regulatory Requirement
178996 | Rate update on MSC I | Additional regulatory condition for MSC I | 4 - Mandatory | Regulatory Requirement
172711 | CDG Bill Info | New data elements to be tracked for CDG customers | 4 - Mandatory | Regulatory Requirement
168364 | New Rate Items | New rate configurations | 4 - Mandatory | Regulatory Requirement
168361 | MSC Load Shape Calculations | New batch jobs required to perform rate calculations | 4 - Mandatory | Regulatory Requirement
157707 | NYPA Billing | Regulatory requirement to process NYPA billing with necessary billing details and file format | 4 - Mandatory | Regulatory Requirement
131783 | Mandatory Hour Pricing and Smart Home Rate Interval Billing | Regulatory requirement mandates hourly interval data to be captured in new system for accurate billing calculations | 4 - Mandatory | Regulatory Requirement
122407 | O&R Complex Billing Solution | Updates in MDM system to process complex billing to customers | 3 - High | Regulatory Requirement
110157 | Gas Daily Delivery Services Charge Changes | Integration required to send and receive responses on delivery charges to ESCO's | 4 - Mandatory | Regulatory Requirement
109891 | Multiple Rate Calculation Specific Algorithms | New regulatory requirement to calculate rates accurately | 4 - Mandatory | Regulatory Requirement
108849 | Gas Profiling Data | Regulatory requirement mandates gas profile generation which requires an integration between systems | 4 - Mandatory | Regulatory Requirement
97608 | Create/Cancel Credit Adjustments | Regulatory requirement to allow adjustments for customers on low income programs | 3 - High | Regulatory Requirement
82016 | Enhancements to We Guarantee It, Service First program | Regulatory requirement to generate a report for approval process prior to providing adjustment credit | 4 - Mandatory | Regulatory Requirement
80904 | Payment Agreement Enhancements | Senate ruling requires updates to payment arrangement eligibility related to Covid and Crisis events | 4 - Mandatory | Regulatory Requirement
80902 | Energy Efficiency Benchmarking for Local Law 84 Compliance | Updates to Energy Efficiency Benchmarking Application interfaces after a design update | 3 - High | Regulatory Requirement
78798 | Gas Service Line (GSL) Inspection Process Updates | New functionality that was released in two phases for customer and landlord controlled access | 3 - High | Regulatory Requirement
78785 | PSC Mandated Customer Satisfaction Survey | New functionality implemented during the program to pull daily survey samples based on certain customer transactions. | 4 - Mandatory | Regulatory Requirement
78309 | Manage Account - Update Account For Covid Indicator for CECONY & ORU Residential Customers | Changes due to COVID to provide COVID indicators that resulted from Senate hearings. | 4 - Mandatory | Regulatory Requirement
108434 | Methane Sensor Process Updates | Development of automated process for methane sensor management | 3 - High | Regulatory Requirement
342106 | Billing Window Changes | Expanded bill window to reduce number of estimated or delayed bills | 4 - Mandatory | Unplanned Customer Value
179861 | Standby Billing Functionality Retrofit based on Usage Calculation Decision | Functionality updates to Standby Billing process to align with the usage model solution decision | 4 - Mandatory | Unplanned Customer Value
172003 | Automate Summary Billing Enrollment | Automate summary billing enrollments which are currently manual to mitigate customer impact of delays | 2 - Medium | Unplanned Customer Value
133755 | User Billing / Meter Read View Enhancements | Updates to portal for more billing details display view | 3 - High | Unplanned Customer Value
129210 | New Summary Billing Experience | New Bill Print solution requires updates to the format of the bill print file | 3 - High | Unplanned Customer Value
107280 | Start/Stop Enhancements | Changes to Start/Stop functionality to enhance experience | 3 - High | Unplanned Customer Value
100775 | Summary Billing Web Portal | Additional summary bill capabilities on customer portal | 3 - High | Unplanned Customer Value
100765 | Website Enhancements for Commercial Customer to Access Energy Use Data | Integration for external systems to retrieve account information | 3 - High | Unplanned Customer Value
100562 | CC&B v2.8 Upgrade - Retail Choice | Additional impacts to Retail Choice from upgrading to latest version of Oracle CC&B to align to Oracle roadmap | 3 - High | Unplanned Customer Value

## Attachment 5
Summary of Planned and Actual Extensions and Interfaces | [5 empty] | Click Here to Retun To Summary Sheet
Extensions
Planned |  | Actual |  | Variance
Complexity | Count | Complexity | Count | Variance Count | Variance %
Simple | 200 | Simple | 191 | -9 | -4.5%
Medium | 60 | Medium | 178 | 118 | 196.7%
Complex | 14 | Complex | 17 | 3 | 21.43%
Total | 274 | Total | 386 | 112 | 40.88%
Interfaces
Planned |  | Actual |  | Variance
Complexity | Count | Complexity | Count | Variance Count | Variance %
Simple | 71 | Simple | 43 | -28 | -39.44%
Medium | 356 | Medium | 542 | 186 | 52.25%
Complex | 64 | Complex | 98 | 34 | 53.12%
Total | 491 | Total | 683 | 192 | 39.1%

## Attachment 6
Planned Interfaces |  | Click Here to Retun To Summary Sheet
ID | System Interface | Description | Complexity
113 | Collection Agencies | Collection - On a daily basis CIMS accounts are reviewed by core collection jobs. The jobs determine if an account has a balance that is overdue and must be sent to an outside agency for collections purposes. A agency master file is created and send to agencies. Files are sent to Michael Zager, National Capital Recovery, and Credit Bureau of Hudson Valley. | 3. Medium
114 | Collection Agencies | Receipt of payments- full payment removes customers from collection. | 3. Medium
115 | Electronic Funds Transfers | ABP is handled internally through CIMS and the files are sent to our bank , JP Morgan Chase, for processing. Electronic Funds Transfers (ABP) is offered to the customer via the My Account application or by phone. The customer authorize the company to automatically withdraw their Bill Payment amount each day on the 25 day of the month from their bank account. A draft is send to the Bank at startup to validate the customers account. Once enrolled the payment is withdrawn from customers account each month and posted to the customers account. The debit is send the customers bank for processing as well. | 3. Medium
116 | Electronic Funds Transfers | Bank withdraws the ABP from customers account and send file to ORU for processing | 3. Medium
117 | EZ Pay | Payments processed online in Customer Service Lobbies and thosed entered in CIMS via Online window by Customer Service. Part of CIMS cash processing | 3. Medium
118 | FORD - Field Order Route Design | The Field Order Route Design (FORD) System provides O&R Customer Field Operations the ability to design routes of travel to customer premises for its field workers to perform work orders. The FORD system uses a mapping tool (MAPINFO) to support visual design of routes by showing work orders in a geographic area and then providing tools to select work orders to be included in a route.&nbsp; The FORD uses SQL data base as well as CIMS tables to access and update meter information.&nbsp; FORD processes requests (retrieve orders, create and sequence routes, print field data forms) from desktop clients located at various O&R offices. The Client system of FORD is a 32-bit software application that runs on a standard desktop or laptop PC and performs the following business functions:&nbsp; Specify work load, Resolve geocoding, Build routes, Save and print. On the Mainframe Ford batch programs read and update CIMS and MAMS DB2 tables and to read GRID VSAM files. Batch programs do the following: extract and load of grid coordinates, extract and load of reference data, extract and load of appointments, extract and load of meter and CIMS-generated collection orders, On demand extract and load of user-generated collection orders. | 3. Medium
119 | FORD - Field Order Route Design | On the Mainframe Ford batch programs read and update CIMS and MAMS DB2 tables and to read GRID VSAM files. Batch programs do the following: extract and load of grid coordinates, extract and load of reference data, extract and load of appointments, extract and load of meter and CIMS-generated collection orders, On demand extract and load of user-generated collection orders, and On demand update of status of work dispatched to the field,On demand update of status of work dispatched to the field are also processed in FORD. | 3. Medium
120 | Gas Transportation Metretek | Info for Gas Transportation Billing. The Metretek gathers consumption for gas transported to ORU gas transportation customers. A file is created and pass to the mainframe for processing. | 3. Medium
121 | OR Project Center (NUCON) | A web application that gives the ORU customers the able to create applications to inform New Business of new development both large and small. | 3. Medium
122 | OR Project Center (NUCON) | Customer creates the application and the New Business work process starts. | 3. Medium
125 | KIOSK | A web service used by the KIOSK provides information (account inquiry) along with previous banking information (if available) to the KIOSK application (NCR) and web service to process account payment performed via the application for KIOSK. The customer is then able to make payments and view payment history and other limited functions. | 3. Medium
126 | LPDS- Load Profile Data System SHOULD BE REPLACED BY AMI | Stores interval data for O&R and CIMS accounts to keep both the systems in synch. | 3. Medium
127 | FISERV Credit and Debit Cards | On a daily basis we receive a credit card payment file from FISERV. It contains credit card payments. An e-mail is then compared to the reports sent by FISERV earlier in the day. Totals are matched and verified to insure that the correct data has been received. | 3. Medium
130 | Second Placement Collection Agencies | Accounts with an outstanding balance that have a “final” status in CIMS are sent to collection agencies within the number of days specified in the Final Collection timeline. The days are based on account balance and credit rating. After having been with a collection agency for the period of one year, accounts are then moved to second placement. | 3. Medium
131 | Second Placement Collection Agencies | Receipt of payment triggers the customer to come off of second placement | 3. Medium
132 | O&R WMS | Time Charges | 3. Medium
133 | O&R WMS | CREATES A SEQUENTIAL FILE OF COMPLETED SERVICE INVESTIGATION (BLUECARD) JOBS TO PASS TO THE CUSTOMER/1 SYSTEM | 3. Medium
134 | O&R Mobile Outage Web Service | Create outage ticket and using Web Service that will be used by Mobile app to issue and retrieve status of an electric outage. The CIMSMobilWS web service will reside in the Con-Ed DMZ. The Mobile app will call CIMSMobilWS web service which then will call web service in back of the fire wall to issue and retrieve status of an electric outage. | 3. Medium
135 | O&R Mobile Outage Web Service | Call Cust info and O&R Mobile Electric Outage/Status Web Service. Web Service that will be used by Mobile app to issue and retrieve status of an electric outage. | 3. Medium
136 | webWMS | acct#, serv req. st light req | 2. Simple
137 | webWMS | Completed info | 2. Simple
139 | Grid Coordinate System | Seg/Circ info in PGCX.V119.SEGM.MASTER updated by "SEGM" CICS transaction and referenced by CIMS transaction. (See CIMS program CIRSO003). PGCX.V010.GRID.MASTER updated by nightly batch job and contains XY's for transformers, poles and customers(house XY). PGCX.V055.GRID.ROUTE is subset of V010 master file and contains premise and XY. | 3. Medium
140 | O&R Gas Mobile Dispatch | Interfaces field work from CIMS to TRB to MobileUP for field personnel. Upon completion, back to Oracle and TRB databases. Worktypes include GAS TROUBLE ORDERS, GAS METER ORDERS. | 3. Medium
148 | O&R Storm Center Internet Site - IFACTOR | More commonly known as the O&R Outage Map this tool was developed by a vendor called IFACTOR. The application is maintained and enhanced by the vendor at the request of public affairs. The CIMS IR group performs the role of organizing code moves through the various environments and ultimately to production through "Release to Web" requests. All of this is done after public affairs reviews and validates the test results of the vendor. The application currently shows outages grouped at a community level as well as weather information for the previous two hour timeframe. | 3. Medium
149 | O&R Storm Center Internet Site - IFACTOR | Retrieves data from oms and displays map for customer | 3. Medium
150 | Itron Meter Reading System FCS - O&R | Meter read info | 3. Medium
151 | Large Power Billing | Large Power customers' 15-minute Interval usage data from LPDS is summarized into pre-billing files for CIMS billing. | 3. Medium
153 | Meter Data Management Information System (MDMSI) | Customer, Account, and Meter Info | 3. Medium
154 | NUCON-New Construction System | The NUCON system enables New Business to initiate, manage, and complete a Project in an efficient manner by integrating existing business processes with web technology Major Functions: Initiate a Project Manage a Project and Complete a Project It retrieves customer information from CIMS | 3. Medium
155 | NUCON-New Construction System | The applications for New Business to enter are created by the customer and mailed or by using Project Center. An meter order is created and the new customer account is created if one does not exist. The meter is installed or changed depending on the type of application that was submitted to New Business | 3. Medium
158 | Outage Management Interface (OMI) | file - PCIM.PI915MBT.TARSCH.TAXAREA.SORT (provides customer count information for different rate codes and service classes in all tax districts) DB2 tables - these tables are used in maintaining the OMI rate table SPT_TAR_SCH (service point tariff schedule table) TAR_SCH (tariff schedule table) | 3. Medium
161 | Electric Information Management System | EIMS Streetlight batch processes read the following CIMS tables for validation/editing purposes: BILL_ACCT, SERVICE_PT, TAR_SCH, PAL_COMPONENT_HDR, PAL_STD_MO_UNIT | 3. Medium
162 | O&R Gas Inspection and Maintenance System | Various completed GAS METER ORDER info is sent to CIMS via FORD WebService, based on worktype. | 3. Medium
163 | OR Storm Communication Web Service | OR_StormComm - Internal Web service (on COM servers) that will retrieve ERT status of an electric outage from CIMS PNS tables (DB2 tables). OR_StormComm web service will be called by various web applications the retrieve status of an outage based on premise number. It will be called by CIMS Mobile Web Service, TFCC, VRU and Web pages (OROnline - outage status). Read elec outage status | 3. Medium
164 | ORBIS (My Account) | This web service is called by the Vendor Apogee to provide calculations of O&R customers energy usage from CIMS. This web service is found on the customers My Account page located on www.oru.com. The web service passes the customer account number and energy usage and billed amount for 12 month period. The vendor then creates graphs and other pages for the customer to determine where to save on energy use. | 3. Medium
165 | Dept. of Social Services | ORDSS is a web-based internet application that provides D.S.S agencies with customer information to be used in determining HEAP eligibility. HEAP is a federally funded program that provides eligible customers financial assistance with paying utility bills for each heating season. | 3. Medium
168 | O&R Online Service Request (start service/issue outage) | OR online is a web-based internet application that gives O&R customers the ability to request various service. These customer service request include: Start Service, Report an electric power problem and status and Gas service locator. Customer Request information | 2. Simple
169 | O&R Online Service Request (start service/issue outage) | The customer enters information into the start service page and that inserts into CIMS tables. The outage status and Gas locator pages do not update customer data. | 2. Simple
170 | O&R Power Pick(bid request and response) | The ebids application allows customers to anonymously request bids (through My Account) from energy suppliers. | 2. Simple
171 | O&R Power Pick(bid request and response) | The energy suppliers produces the bids for customers and response directly to the customer. They do this through the ebids Marketer pages. | 2. Simple
172 | O&R Retail Access Portal (EBIDS) | The Retail Access Portal allows the O&R Retail Choice group to view and maintain various supplier information as well as handle eBids. | 3. Medium
173 | O&R Retail Access Portal (EBIDS) | The Portal gives the RA group the ability to update suppliers and keep tracks of tarrifs. It keeps track of number of bids that can in and how many were approved by customer and how many were rejected by customer. Maintain Marketer Information including Storage Type, - Maintain Capacity Obligation Dates- Maintain Marketer Bill Messages- Maintain various aspects of eBids. The Portal also keeps track of number of customers and their accounts that requested bids or rejected bids. | 3. Medium
174 | O&R Storm CSR Storm mode | ORStormCSR was created to retrieve the customer`s account number and phone number. The CSR can retrieve the information by entering either the customer`s name, business name or service address on the Find Account page. This page will be used to access OR_STORM_CSR (CI80TB93) table to retrieve the customer’s information. The database access is coded for a direct hit If multiple customers have the same name, the page will display all matching rows on the table. | 3. Medium
175 | O&R Storm CSR Storm mode | This page will be used to access OR_STORM_CSR (CI80TB93) table to retrieve the customer’s information. | 3. Medium
176 | Retail Access - Capacity Obligation | Customer usage for a designated peak hour. | 4. Complex
177 | Retail Access - Settlement and Capacity/Transmission Obligation | Cims provides a file of active accounts and the usage per account for a designated calendar month. FIle is used in both the monthly Settlement and in the yearly Capacity/Transmission Obligation processes. | 4. Complex
179 | Retail Access Information System - Internet | Retrieve customer data from CIMS DB2 | 3. Medium
180 | RAIS O&R Mainframe | 1) Provides transaction file sent from RAIS application. Transactions are ESCO price changes (RC), accts to be put on HOLD(TA), Accts to be made active with an ESCO (MA). 2) Provices file of accta that require a notification letter from CIMS. 3) Provides file of customers for creation of EDI867 historical usage file and for EDI814 file for accts that errored out during the historical usage process. | 4. Complex
181 | RAIS O&R Mainframe | 1) CIMS file containing monthly electric usage for all customers in current billing cycle. 2) CIMS tables are read by OR RAIS mainframe programs to provide customer name/addr information for the RAIS application. | 4. Complex
182 | O&R Street Light Repairs | SLRepairs contains a page viewed within ORU.com that allows external customers to enter address and pole information about street lights that are out, flickering or damaged. SLRepairs also will receive SL repair requests from CSRs who receive information from customers over the phone. If a customer is calling about a private light and provides account information, information about our contact with them will be maintained in the system. Once requests are received, CSRs will verify address and pole information; as well as determine if the request is a duplicate of one already received. If it is deemed a valid request, it will be forwarded to operations to have the light repaired. | 3. Medium
183 | Synergi 4.5 (old name SynerGEE Gas 4.5) | Synergi (used to be called SynerGEE) gas software is purchased from vendor DNV GL (aka Stoner). It is used to analyze and design our gas systems. The software was installed on gas engineering’s laptops by IR. The software also includes modules MRP (Main Replacement Prioritization) and CMM (Customer Management Module) that require data from company databases (CIMS, GIMS & NRG) to run. This program does not directly interface with company databases. IR and CIMS group have written programs to retrieve the necessary data from CIMS, GIMS & NRG and provides it to us to input into the Synergi program to run. We still need these programs. In fact, we intend to run the CMM program (requires data from CIMS) this quarter and annually thereafter. | 3. Medium
184 | TROUBLE ORDER SYSTEM | Interfaces data from CIMS Trouble Order dialogs to generate Gas and Electric Trouble Orders. Gas orders are sent to GMD, and upon completion stored in mainframe TRB. Electric orders are sent to OMS via tables TRB334/TRB335/TRB336. Also interfaces with VRU via CIMS. Daily Gas Meter Orders fed to TRB via CIMS table CI70TB55 (GMD_METER_ORDERS). | 4. Complex
185 | CIMS 2 Info Central | The CIMS Info Central system is an Intranet application that resides on ConEd servers and is accessed through the O&R intranet. It is used by O&R Customer Service employees to handle various job functions including a 'reporting' page that provides Web Focus dynamic reports. | 4. Complex
186 | CIMS 2 Info Central | The e-bill enrollment page in CIMS 2 application is used to enroll customer and update their e-bill information. The Letter retrieve page is used by CS to retrieve letters that were send to the customer. There is also the ability to view a copy of the customers bill. There are other pages like WFMs created by batch for review by supervisors and Web Focus reports to request. This application also holds a FORD application used by the meter shop | 4. Complex
187 | O&R Customer Interaction Center (IVR) | Request info, process transaction | 3. Medium
188 | O&R Customer Interaction Center (IVR) | Send info, transaction results | 3. Medium
189 | O&R Revenue Protection | Customer information rom CIMS is displayed in application. | 3. Medium
192 | O&R OMS (Oracle OMS) - Customer Call Processing (DB2toOracle) | Retrieve customer calls from trouble order system and process into O&R Oracle OMS | 3. Medium
194 | O&R OMS (Oracle OMS) - DB2 File Extract (NMSDB2Extract) -IFACTOR, IVR, PNS | Send customer outage data to mainframe via FTP in the form of 6 flat files | 4. Complex
200 | O&R NRG - CIMS ADHOC Customer Data Transfer | Retrieve active and inactive customer account data for use in NRG and O&R Oracle NMS, and their associated reporting applications | 3. Medium
201 | Interruptions - OMSI Interface | Send outage info for EOR (Electric Outage Reports - WebFocus) on ORU Intranet | 3. Medium
204 | Enterprise Data Analytics Platform (EDAP) | The source system, CIMS, will provide Account, Premises, ServicePoint, Billing, Usage, Address, Market and Payment data to the EDAP’s Account, Facility, Organization, Service Agreement, Service Point, Market Account, Payment, Billing and Measurement entities. As part of the use case definition, the following Interfaces were determined to be needed from CIMS. EDAP_II_030-CIMS-Account EDAP_II_031-CIMS-Facility EDAP_II_032-CIMS-CustomerOrganization EDAP_II_033-CIMS-ServiceAgreement EDAP_II_034-CIMS-ServicePoint EDAP_II_035-CIMS-ServiceAgreementServicePoint EDAP_II_036-CIMS-BillSummary EDAP_II_037-CIMS-MeasurementSeries EDAP_II_038-CIMS-Measurement EDAP_II_061-CIMS-PaymentAgreement EDAP_II_063-CIMS-BillFormat EDAP_II_064-CIMS-Market EDAP_II_065-CIMS-Payment EDAP_II_066-CIMS-BudgetBilling EDAP_II_070-CIMS-MeterConfiguration | 3. Medium
205 | Pitney Bowes | Code-1 Plus validates, corrects and standardizes customer address data. The technology is CASS Certified by the USPS. The Code-1 Plus standardizes mailing addresses by adding missing address information, Standardizing city names and state abbreviations, Correcting misspelled address elements and appending ZIP + 4 and carrier route information. Once the billing file is run through Code 1 software the file is then used to mail bills. | 3. Medium
206 | Pitney Bowes | Nothing is returned from customer | 3. Medium
207 | Broadridge | Broadridge is the vendor that receive our AFP Bill Print file and prints our Customer Bill formatted to our specifications. The Bills are then stuff into envelopes and Send to our Customers | 3. Medium
208 | Verimove | VeriMove checks customer records against the USPS National Change of Address database (NCOALink). By identifying new addresses of recent moves VeriMove Access helps you reduce undeliverable mail maximize postage discounts and meet the USPS Update requirement. | 3. Medium
209 | Verimove | The customers addresses are quickly updated to new address. | 3. Medium
210 | Questline | Used by Corp Comm to send out email blast to customers | 3. Medium
211 | AEG - Applied Energy Group | AEG provides a wide range of energy efficiency and demand response relates management services to assist clients in designing and implementing programs for their customers. | 3. Medium
212 | Simple Energy | Simple energy is a vendor that is helping utilities own their customers’ energy experience. The customer is able to understand ways to save energy by purchasing energy related products or getting a better understanding of their energy usage. It is a utility branded e-commerce platform that offers energy-saving household products and services with instant rebates. Customers are saving time and money, while utilities are maximizing the effectiveness of demand side management programs. The customers are empowered to make energy-wise decisions and manage their usage. They transform the customer consumption data that is send to them electronically by ORU into a digital experience for the customer. | 3. Medium
213 | Navigant | Navigant Consulting is developing two software tools for O&R. One tool will generate specific outputs relevant to energy efficiency, demand response, customer-sited generation and storage. The tool’s output will be used to inform O&R’s 2018 and beyond DSM planning and filings with the NY Public Service Commission. The second tool will enable O&R to create and analyze granular portfolio scenarios and sensitivities of various distributed energy resource (DER) options, including various non-wires solutions resources. In support of the development of these tools, Navigant requested detailed customer data that was provided by CIMS and other departments. This data was used to populate the tools and support Navigant’s analysis of O&R’s potential for DER in its territory. | 3. Medium
214 | PowerClerk | Distributed Generation entered information into an application. CIMS validates the customer information using a web service. | 3. Medium
215 | PowerClerk | DG completes the application and uses CIMS to create the Service order via a web service. Once meter is install or updated the customer is billed for their Net Metering use. | 3. Medium
216 | WEST | Performs RCD and Volume calls. On a daily basis we send accounts to WEST for collection calls and receive the results back from them the next day. Support Operations monitors the account sent to WEST and the results that they return to us. Billing receipts from WEST are compared to system statistics to insure that they billing are correct. Queries are run against CIMS tables by Support Operations to verify that customers are being contacted in the correct manner. | 3. Medium
217 | TFCC | Twenty First Century Communication is used by the call center to cover overflow of calls during heavy call days and during storms to. TFCC provides a suite of web-based, vendor-hosted solutions for high-speed notification. Our system features both inbound and outbound messaging, with applications ranging from outage reporting to business continuity, employee accountability, and emergency notification. Also transfers calls to West | 3. Medium
218 | TFCC | TFCC stores streams of calls on the icloud and passes them to ORU or West during heavy peak times or during storms | 3. Medium
221 | Cash Acceptance and Receipt Printers | Customer services printers and receipts to give customers receipt and to print that confirmation of payment | 3. Medium
222 | Experian Credit Check - verification | The social security number provided by the NEW customer is entered into CIMS in the Maintain Customer Data screen. The Validate button to insure that the customer provided SSN is not already in CIMS. The Verify button, which will send the new customer’s data to Experian for verification. | 3. Medium
223 | Experian Credit Check - verification | The verification process is expected to take no more than 7 to 10 seconds from the time the request is made until a response is returned from Experian | 3. Medium
224 | Authorized Payment Location | Outside payment locations are used to collect Customers payments near their residents. The payments are collected by APS company and transfered to ORU mainframe twice a day. | 2. Simple
288 | Retail Choice Information System (RCIS) | Query CSS DB2 Adhoc to retrieve Account information | 4. Complex
291 | Meter Data Management (MDM) - Itron Enterprise Edition (IEE) SHOULD BE REPLACED BY AMI | N/A | 4. Complex
292 | Payment Processing (Mavro) | Mainframe job P400R012, Cash Edit File, 3 x Daily | 3. Medium
294 | Itron FCS - Itron meter reading system (FCS) SHOULD BE REPLACED BY AMI | Itron FCS returns the accounts, meters, trips, along with Meter Reads to CSS for billing, uploaded to CSS via Cycle PET -- in MRE (Meter Read Export) format. | 3. Medium
295 | Customer Transaction Processing System (CTPS) | Customer Transactions for File Maintenance. Distributed process loads DB2 staging which is source for mainframe process which pick up and input to CAS FMBC process. | 4. Complex
296 | Retail Access Information System - Mainframe CE (RAIS) | Update of CAS to RAIS DB2 Staging CAS - Latest Daily Transactions for CAS Sort Marketing agencies for Plain Language Billing, Front-End Extracts, Credit and Collections, and CIS Statistics DB2 - RAIS Account Table RAIS Account Request Table RAIS Account Transfers (ATRAs) RAIS Account Refresh RAIS Transactions (for Account and Meter Refreshing) | 3. Medium
297 | Transportation Customer Info System (TCIS) | TCIS Account Price and Marketer information to CUBS | 4. Complex
298 | Customer Project Managment System (CPMS) | Account Setup info | 3. Medium
299 | HR/Payroll (PeopleSoft) | PARS interface - Labor Hours extract to PARS ( Productivity Analysis Reporting System) --- (CAS) | 3. Medium
300 | EBS Supply Chain Management | Check Number,Check Date,Invoice Amount, Amount, Invoice Number, Invoice status, Check status, Vendor id, Status | 3. Medium
301 | ACH Returns | TBD | 2. Simple
303 | Intel-A-Chek [Cash Payment Import] | These files will be transmitted/updated to Intel-A-Chek database) | 3. Medium
304 | Load Profile Data System (LPDS) SHOULD BE REPLACED BY AMI | Billing determinents (Expected to be retired soon) | 3. Medium
305 | Intel-A-Chek [Print] | Cash transaction file (input to Cash Edit process) | 3. Medium
306 | Non-Same Day Cash | Cash Transactions Input to Cash Edit Job P400R099 | 3. Medium
307 | Productivity Analysis Reporting System (PARS) | - Supervisory File(Update) - updates done in CIS, reports run in CAS - The Customer Service Representative (CSR) Productivity Measurement System captures data in an on-line environment as each CSR performs his/her daily tasks. A "reasonable expectancy" completion time for each task is applied and a productivity ratio is calculated daily for each representative. Management reports are produced daily, weekly and monthly reflecting statistics for individuals, groups and at the division level. | 4. Complex
310 | Unclaimed Credits and Refunds | File FTP'd to NewYork State | 3. Medium
312 | Gas Inspection System WEB (GIS WEB) | Daily gas meter work (set, exchange, removal) completion data for posting gas meters and ERT ID with the customer account. | 3. Medium
313 | Direct Payment Information System (DPIS) | CAS - ARCOs to update Direct Payment info for accounts. Account/billing updates for direct payment customers | 3. Medium
314 | Meter Data Management System Interfaces (MDMSI) | Meter readings from the MDM (legacy) | 3. Medium
318 | eFailure - Internet Bill Delivery and Payment System (IBPP) | File created after processing BroadRidge-320 file i.e. 828efail.dat. Contains a list of acocunts that need to be updated or removed from ebill.. after processing accounts in the efailure file a MF file is transmitted to CAS which contains ARCOs to remove email address and eBill indicator | 3. Medium
319 | Final Account Name Matching System | This system uses CSS Master file information to match final unbilled account names to recent turn on within 2 years. The system does two types of matches. o The first match is a name match between the final/UB file and recent turn-on file. o The second type of match is a supplemental match between the final/UB file and four supplemental VSAM account files. o The types of matches include social security, welfare number, primary/ alternate telephone number, and service/mailing addresses. o The resulting matches are input to a report program that produces a series of reports which include the Namematch only, non namematch, multiple match, and voucher transfer. | 4. Complex
320 | Pitney Bowes | Customer Addresses - cleansed | 3. Medium
324 | Reconciliation of CSS and Satellite Systems Financial data (RCSF)/REVSTAT | List of active accounts from Satttelite systems. - Daily transactions extract from all satellite systems are transmitted to CAS//REVSTAT | 4. Complex
326 | CuFLink | ARCOs - all accounts | 3. Medium
341 | Cycle PET Interface System (C-PET) SHOULD BE REPLACED BY AMI | Meter Read data for the requested trip | 3. Medium
342 | Payment Processing (Mavro) | Mainframe job P400R754, Queens Billing Data File | 3. Medium
343 | PayPilot - Customer Refund Check file (CSS) | Cecony Customer refund check file | 3. Medium
346 | Itron FCS - Itron meter reading system (FCS) SHOULD BE REPLACED BY AMI | CSS sends information about accounts, meters, trips, to Itron FCS via Cycle PET | 3. Medium
347 | Dynamic Load Shape (DLS) | Sent RESPIN file from Mainframe to server - RESPIN: Non-Residential and Residential File | 3. Medium
349 | Transportation Customer Info System (TCIS) - Batch | CAS - Voucher Bill GDG Files Unstack TCIS Files DB2 - CAS Account Table CAS Account 2 Table CAS Arrears Table CAS Credit Table CAS Employee Table CAS Gas Bills Table CAS Gas Meter Table CAS Gas Meter Item Table CAS Mail Addresses CAS Vouchers CAS Time of Day Large Accounts Table TCIS Account TCIS Enrolled Account TCIS Gas Meter TCIS Gas Interrupt (Eligible) Service Class TCIS Transaction RAIS Account Transfers (ATRAs) | 3. Medium
350 | EBS Financials (EBS_FIN) | GL Period, Balance Type (A), Ledger Name, Category, Source (CSS), Effective Dt, Currency, Entered_DR/CR, Conversion Type/Rate/Dt, COA, Folio Number, Trip No, Trip Dt COA, Accounting Dt, Folio Number, Trip No, Trip Dt, WS-META-DOLLARS, JE Line Tracking Info | 3. Medium
351 | EBS Supply Chain Management | Invoice Number, Type, description, Date, Amount, Currency code, Payee Code, Terms, Payment method, Operating unit, Line Number, Line Type, Amount, Account Num, PO, PO Line, Purchasing Category | 3. Medium
352 | ACH Returns | TBD | 2. Simple
356 | EBill Enrollments | File FTP'd to Broadridge | 3. Medium
357 | Electronic Cash Payment Receipts | We receive cash payment files from different vendors. We process these transactions in cash edit job, Output from Cash Edit Job will be input to FMBC and payments will be posted in FMBC Process. | 3. Medium
358 | Load Profile Data System (LPDS) SHOULD BE REPLACED BY AMI | Acct/Meter Info to new LPDS | 3. Medium
360 | Load Profile Data System (LPDS) SHOULD BE REPLACED BY AMI | For calculation of billing determinants - functionality already moved to MDM but there are programs that rely on account and meter information from LPDS | 3. Medium
361 | Intel-A-Chek [Print] | Transmitted ACH file from the Intel-A-Check database (see Intel-A-Chek Cash Payment Import) | 3. Medium
362 | Load Profile Data System (LPDS) SHOULD BE REPLACED BY AMI | Contains trip table for billing | 3. Medium
363 | Monthly Master Review (MMR) | FMBC Master Files (6 divisions) | 4. Complex
364 | Non-Same Day Cash | Cash payments | 3. Medium
365 | Productivity Analysis Reporting System (PARS) | Database Security File. employee numbers | 4. Complex
366 | Quarterly Master Review (QMR) | FMBC Master Files (6 divisions) | 3. Medium
367 | Revenue & Statistics (REVSTAT) - Revenue to Oracle GL Interface | RCSF Merged files | 4. Complex
369 | Unclaimed Credits and Refunds | Extract Files from Quarterly Masters. File will be FTPE'd to New York State Department | 4. Complex
370 | VeriMove System | 18 Month flat file and Daily delete file are downlded from USPS website and processed using Client Server Based Pitney Bowes Verimove Application and generates Mainframe Datasets. These files will be processed through Finallist application and Verimove system on Mainframe and updates addresses in CSS Master. | 4. Complex
371 | Gas Inspection System WEB (GIS WEB) | CSS Master extract for updating customer information in GIS assets (meter, regulator, BOPA). Customer information update based on ATRA/ARCO | 3. Medium
372 | Direct Payment Information System (DPIS) | CAS - Account/billing updates for direct payment customers | 3. Medium
373 | Meter Data Management System Interfaces (MDMSI) | CAS: Meter reading requests | 3. Medium
378 | Final Account Name Matching System | CSS master data | 4. Complex
379 | FNL - Finalist / Mailstream plus | Customer Addresses - uncleansed | 4. Complex
380 | Monthly Downloaded Sales System | Downloaded sales data for month | 4. Complex
385 | CuFLink | Customer Data | 4. Complex
388 | MV90 Gas SHOULD BE REPLACED BY AMI | j400.A997.MV90GAS.DATA | 3. Medium
389 | Daily delta data synchronization - AMI | Daily delta data synchronization - CAS to SDPG | 4. Complex
398 | Cycle PET Interface System SHOULD BE REPLACED BY AMI | Trip files in 7104 (Daily file) | 3. Medium
399 | Cycle PET Interface System SHOULD BE REPLACED BY AMI | Trip Schedule (Yearly file) | 3. Medium
401 | iNovah | Cash processing system used when payments do not post to customers accounts (EX: IRIS issues, money deposited yet not credited, etc) | 3. Medium
402 | iNovah | Cash processing system used when payments do not post to customers accounts (EX: IRIS issues, money deposited yet not credited, etc) in comjunction with treasury | 3. Medium
403 | RAIS - Retail Access Information System - Client / Server | RAIS account information, enrollment information, relationships and prices | 3. Medium
404 | HR/Payroll (PeopleSoft) | HRCI004 - Payroll file to CSS -- (CIS) | 3. Medium
406 | Customer Information Voice Response Unit System (IVR) - Customer VRU) | MQ transactions sent from IVR | 3. Medium
408 | ServiceLink | Service Link is used by Field Ops to dispatch and field Customer Service work orders, e.g. turn ons, turn offs, AIO, RMOPs and collections and AMR/AMI maintenance. | 3. Medium
410 | Corporate Customer Info Internet Site | Payment transaction | 3. Medium
418 | MQ Communications from Service Link | Service Link (S/L) sends MQ requests to create RMOP's (Referral to Meter Operations) | 3. Medium
420 | Twenty First Century Communications (TFCC) Information - West | Electric TRBL's sent from TFCC via MQ | 3. Medium
426 | Customer Information Voice Response Unit System (IVR) - ? | CIS sends account information to the IVR | 3. Medium
432 | ServiceLink | Service Link is utiilized by Field Operations to dispatch and field Customer Service work orders including turn-ons, turn-offs, AIOs, RMOPs, collections and AMR/AMI maintenance. | 3. Medium
435 | Customer Data Interface (CDI) | Account lookups for real time data | 2. Simple
440 | Positive Identification System (PosID) | Currenly PosID checks to see if user is signed into CIS to authorize use. This is likely to be phased out | 3. Medium
441 | Public Assistance Central (PAC) | DB2 and CIS - Account information | 3. Medium
443 | System Trouble Analysis and Response (STAR) | CIS sends electric emergency orders | 3. Medium
447 | Robo-Reps | Used by Customer Operations to quickly put a high volume of transactions into CIS | 4. Complex
449 | Twenty First Century Communications (TFCC) Information - West | Overflow emergency orders (TRBL) are sent to TFCC via MQ | 3. Medium
450 | Agency Referral Tables | Application queries credit and account data for finalled accounts | 4. Complex
451 | Aging Analysis | REPORTS | 4. Complex
452 | BI - Call Center | Used to measure the performance of: - Calls - Extensions - Agreements | 4. Complex
453 | BI - Credit & Collections Data Warehouse | Used for: Managing AIL’s Agency Performance Effectiveness of Triggers Tracking Account phase life cycle Effectiveness of field collections Final accounts Agreement Performance | 4. Complex
454 | BI - Customer Accounting Data Warehouse | Account Receivables: Used for Purchase of Receivables, Sales, Cash, Uncollectable reports Revstat and RCSF: Used for generating Revenue statistics and Satellite system reports | 3. Medium
455 | BI - IRIS Data Warehouse | Measures the employee stats on Field Collection route analysis Productivity History | 3. Medium
456 | BI - Meter Reading Data Warehouse | Storing all the meter reads Measures the employee performance on the route Real Time Employee reports Irregular conditions | 3. Medium
457 | BI - REV Demo (O-Power) | Provides customer usage information to Opower on a trip basis or when an account bills on CSS. That data is retrieved from DB2H and moved to a Sql Server data mart. The billed accounts are written to a file by division and moved via BizTalk and RDX to Opower. The process runs on the same batch cycle as CSS. | 3. Medium
460 | Clear Access Tracking | CSS Account, Meter and Credit Information | 3. Medium
461 | Common Data System (CDS) | Validate shell account in account ADHOC table | 3. Medium
462 | Corporate Customer Info Internet Site | Account, billing, meter, payment and usage information | 3. Medium
463 | Customer Project Managment System (CPMS) | - Account setup/creation verification details - AMI Meter sets details (VIEW) - DEPOSIT INFO | 3. Medium
464 | Customer Relationship Managment (CRMS) - PEGA | ACCT info EMETER info GMETER info Customer Inquiries | 3. Medium
465 | CTPS - Customer Transaction Processing System | DB2 - Customer Transactions | 4. Complex
466 | Customer Account Interface Service (CAIS) | Account lookups and bounced checks | 3. Medium
467 | Customer Billing Information Service (CBIS) | Account, billing, meter, payment and usage information | 3. Medium
468 | Customer Data Interface (CDI) | DB2 - Account information(Accoutn attributes,ATRAS, CAG Accounts) | 2. Simple
469 | Customer Usage System (CUS) | Customer usage system is for Bill impacts. | 4. Complex
471 | Direct Payment Information System (DPIS) | DB2 - Account, balance, Direct Payment Info | 3. Medium
472 | Direct Payment Plan Online (DPP Online) | DB2 - Account, balance, Direct Payment Info | 3. Medium
473 | Demand Response Management System (DRMS) | CSS Account and Meter Information | 3. Medium
474 | Emergency Operations System (EMOPSYS) | CUSTNAME, ACCTNO, MUNI, SADD, TOWN, TELE, FEEDERNO, MSPLATENO, VAULT, CLIC, LOADREDUCTION, DAYTELE, NITETELE, CONTACT, ZIP, NETWORK, FOREIGNLANGIND, TPNAName, TPNAAddress1, TPNAAddress2, Latitude, Longitude, LSEEQUIPTYPE | 4. Complex
479 | Meter Data Management System Interfaces (MDMSI) | DB2 - C&I account and meter information | 3. Medium
483 | Public Assistance Central (PAC) | DB2 and CIS - Account information | 3. Medium
486 | Retail Access Information System (RAIS) - Internet | Account information from ADHOC tables | 3. Medium
490 | Work Management System - Logica ARM Suite (WMS) | REPORTS | 4. Complex
492 | HR/Payroll (PeopleSoft) |  | 3. Medium
493 | Transportation Customer Info System (TCIS) - BATCH | DB2: TCIS Account TCIS Enrolled Account TCIS Gas Meter TCIS Gas Interrupt (Eligible) Service Class | 4. Complex
496 | Electric Information Management System | A view of data from the EIMS Streetlight Repository is available for a CIMS batch process to pull data and process for billing of municipality streetlight accounts. | 3. Medium
497 | Large Power Billing | Large Power customer account numbers in a table populated by a CIMS transaction and read in by LSB programs. LSB also refers to CIMS tables for data validation (cycle, read dates, svc pts, etc. ) | 3. Medium
499 | Municipal Streetlights Portal | The following CIMS tables are read by the Municipal Streetlights Portal: BILL_ACCT, SERVICE_PT, TAR_SCH, SAD | 3. Medium
500 | Payment Processing (Mavro) | Mainframe job PI053RIP, Payment File, 3 x Daily | 3. Medium
501 | Payment Processing (Mavro) | Mainframe job PI083DIP, OR Returns Posting File | 3. Medium
502 | Payment Processing (Mavro) | Mainframe job PI781WIP, Account Lookup File to O&R and 3 Point Payment Processing | 3. Medium
503 | Payment Processing (Mavro) | Mainframe job PI539WIP, Billing Data File | 3. Medium
504 | Payment Processing (Mavro) | Mainframe job PS206MIP, Derog (DNAC) File to O&R and 3 Point Payment Processing | 3. Medium
505 | 3 Point Payment Processing - DR Processing - Con Ed AR | Mainframe job PI053DST, Payment File (AR File) from 3 Point Payment Processing, Payment Processing's DR Vendor | 2. Simple
506 | 3 Point Payment Processing - DR Processing - O&R AR | Mainframe job PI069DST, DPP Extract from 3 Point Payment Processing, Payment Processing's DR Vendor | 2. Simple
509 | HEAP Grants (P400R736) | Home Energy Assistance Program Frants | 3. Medium
510 | Inovah Cash Payments (P400R078) | Cash payments from INOVAH | 3. Medium
511 | Collection Payment Receipt Processing | Cash payment records from non-routine Customer Service Transactions are uploaded from Service Link system to FPET and are then accumulated in the FPET DB2 payment table. Further process uses the payment table to create interface file. | 3. Medium
513 | Cashed/Stale Refund Checks(P400R114) | Cashed/Stale Refund Checks File from Bank Of NeeYoek Mellon | 3. Medium
514 | CAS - Tax Remission Vouchers(P400R124, P400R126) | Tax Remission Voucher records from Luthin and Utilisave. Tax Remission Certificates allo non-profit customer to receive tax relief on Gross Receipts Tax for the reseale of Electricity or Steam. | 3. Medium
521 | Enterprise Data Analytics Platform (EDAP) | The source system, CSS, will provide Account, Billing, Usage, Voucher, Measurement, Meter Channel Configuration, Arrear and customer finanical historical data to the EDAP’s Account, Organization, Service Agreement, Billing, Measurement and Measurement Series entities. As part of the use case definition, the following Interfaces were determined to be needed from CSS. EDAP_II_021-CSS-Account EDAP_II_024-CSS-BillDetail-Electric EDAP_II_025-CSS-BillDetail-Gas EDAP_II_026-CSS-MeasurementSeries-Electric EDAP_II_027-CSS-MeasurementSeries-Gas EDAP_II_028-CSS-Measurement-Electric EDAP_II_029-CSS-Measurement-Gas EDAP_II_053-CSS-Credit EDAP_II_056-CSS-Vouchers EDAP_II_057-CSS-Arrears EDAP_II_058-CSS-CashHistory EDAP_II_059-CSS-CreditHistory | 3. Medium
522 | EBS Financials (EBS_FIN) | GL Period, Balance Type (A), Ledger Name, Category, Source (CSS), Effective Dt, Currency, Entered_DR/CR, Conversion Type/Rate/Dt, COA, Folio Number, Trip No, Trip Dt COA, Accounting Dt, Folio Number, Trip No, Trip Dt, WS-META-DOLLARS, JE Line Tracking Info | 3. Medium
523 | Payment Processing (Mavro) | Mainframe job, P400R755, Bronx Billing Data File | 3. Medium
524 | Payment Processing (Mavro) | Mainframe job P400R756, Manhattan Billing Data File | 3. Medium
525 | Payment Processing (Mavro) | Mainframe job P400R757, Westchester Billing Data File | 3. Medium
526 | Payment Processing (Mavro) | Mainframe job P400R758, Brooklyn Billling Date File | 3. Medium
527 | Payment Processing (Mavro) | Mainframe job P400T759, Staten Island Billing Data File | 3. Medium
531 | Payment Processing (Mavro) | Mainframe job P400R080, Con Ed Returns Posting File | 3. Medium
532 | 3 Point Payment Processing - DR Processing - O&R DPP | Mainframe job PR00R066, Cash Edit File from 3 Point Payment Processing, Payment Processing's DR Vendor | 2. Simple
534 | CUFLINK | ELSI ARCOS | 3. Medium
536 | Transportation Customer Info System - Batch | Get Posted Vouchers from CSS | 3. Medium
538 | Transportation Customer Info System - Batch | Account Refresh for CSS Adhoc | 3. Medium
539 | OR MidTier Web Services -- USED FOR IVR, MY ACCT, TFCC | OR MidTier Web Services is a group of web services built by SolutionWorks (Accenture) and hosted on virtual servers within the ConEd firewall. They are accessed by O&R internet and intranet applications for various transactions including payments, outage reporting, budget bill enrollment, collection arrangements, payment agreements, and start/stop service. Also be utilized by the O&R VRU for the same functions. | 3. Medium
542 | OR MidTier Web Services - USED FOR IVR, MY ACCT, TFCC | Web Services hosted on virtual servers within the firewall. They are accessed by internet and intranet applications and utilized by the O&R VRU | 3. Medium
544 | LifeLine | Lifeline is a NJ specific assistance program. The payments automatically come into the system via interface process.&nbsp; NJ pays 112.50 per service. A cartridge is send by NJ Public Services | 3. Medium
546 | O-Power | OPOWER is a vendor that provides personalized energy usage insights to customers. They require a regular feed of billed usage data. CIMS has sent historical usage files, and continues to send daily delta files (two files a day, one for Residential, one for Non-Residential). Files are sent Tuesday through Saturday. | 4. Complex
548 | Web Focus Online Report Writer Application | A Web Application using the Focus language to create different internal reports and programs using the CIMS database tables. | 4. Complex
549 | OR_GIMS V1 REPORTING_Gas Inspection and Maintenance System | GIMS online reporting (ORGIMSRpt) reads various CIMS DB2 tables, such as PREMISE, BUILDING, STREET_NAME | 3. Medium
551 | Broadridge - eFailure | Broadridge transmits eFailure file that has accounts who had hard failure during ebill delivery. | 3. Medium
552 | ITRON - P360R020 | DAILY RUN TO PROCESS TOHOST FILE FROM ITRON-AMR | 3. Medium
571 | DCX (Public Website) | DCX_CIMS_010 Verify Date ORU | 2. Simple
574 | Enerlink Interval Prices for NY/NJ | The hourly commodity prices are retrieved from Enerlink each day using a CRON scheduler on a virtual server (ADDGATEPRD1/PRD2) a file is created CS871A10D and passed to mainframe for updating CIMS Interval Price table for later processing in Billing. The perl scripts retrieves NYISO and PJM prices from web. | 3. Medium
575 | OPOWER | Updates Customer Opower Indicator when a customer opts out from the OPOWER enrollment | 4. Complex
577 | SERVICE LINK FILE - GENERATE METER EXCHANGE | Receives the file from Service Link and Generates Meter Exchanges to be introduced into FMBC | 3. Medium
579 | Broadridge | AFP file - customer communications -postcard | 3. Medium
580 | Broadridge | Line print file. IBM script letter files with customer info. IVR letters | 3. Medium
581 | Broadridge | Flat with customer address data for English AMI 90 Day Postcard | 3. Medium
582 | Broadridge | flat file with customer address data for Spanish AMI 90 Day Postcard | 3. Medium
583 | Broadridge | AMI 90 Day Postcard AFP Image file. | 3. Medium
589 | Electric Information Management System | The EIMS web application reads the following CIMS tables for validation/editing purposes: BILL_ACCT, SERVICE_PT, TAR_SCH, PAL_COMPONENT_HDR, PAL_STD_MO_UNIT, SAD | 3. Medium
592 | O&R WMS | Work Request Processing | 3. Medium
593 | O&R WMS | Customer Information | 3. Medium
594 | O&R WMS | BLUECARD PROCESS | 3. Medium
595 | O&R WMS | Reports: Missing Field Order report Pending Field Order report Dusk to Dawn Street Light report Blue Card report | 3. Medium
596 | O&R WMS | Street Lights processing | 3. Medium
597 | O&R WMS | Tax Information | 3. Medium
598 | O&R WMS | Street Light process | 3. Medium
599 | Unclaimed Credits and Refunds | Unclaimed Credits and Refunds file will be sent to NY State Department every Quarter | 3. Medium
600 | 1099-IRS | 1099 - IRS File | 3. Medium
603 | Broadridge | AFP Letters file.Customer Communications name/addr/balance | 3. Medium
604 | Broadridge | AFP file. Customer communication - ARL Certified Letters | 3. Medium
605 | New York State | flat file - UGC file - name / address info | 3. Medium
606 | New York State | flat file. customer info. DVP file | 3. Medium
609 | O&R NRG - Gas Marketing Report | Retrieve Customer mailing addresses for use on NRG Gas Marketing Report | 3. Medium
610 | New York State | flat file.customer data.welfare file | 3. Medium
611 | CCS- Customer Contact Solutions | flat fiile. customer data:acct# name addr email. collection info | 3. Medium
612 | CCS - Customer Contact Solutions | flat file. customer data - name /addr/ email. collection info | 3. Medium
613 | O&R NRG - Gas Trouble Calls Import | Retrieve gas trouble calls for display on NRG gas map | 3. Medium
614 | O&R NRG - Gas Leak Import | Retrieve gas leaks (active and inactive) for display on NRG gas map | 3. Medium
615 | O&R OMS (Oracle OMS) - Call Priority Codes | Retrieve trouble order system priority codes to match up call priorities with special notes on customer accounts | 3. Medium
617 | Customer Transaction Processing System | Transactions are generated through Roborep are FTPed to CAS System | 4. Complex
618 | Deposit | 0205 DATA RECORDS - MONTHLY CUMULATIVE DEPOSIT/CREDIT REFUND | 3. Medium
619 | Deposit | 0212 RECORDS - MONTHLY CUMULATIVE CASHED REFUND | 3. Medium
620 | Deposit | MONTHLY UNCLAIMED DEPOSIT DATA | 3. Medium
621 | ORU CIMS to AP Invoices (to EBS) | ORU Retail access group is looking to create an interface between the ORU CIMS system and Oracle EBS to process payment for Energy Service Companies (ESCOs). | 3. Medium
664 | ProField | Account Sync CAS will create a full account data file "dump" for every account in the system. The application will take as inputs 3 system extracts - CAS, SDP-G, MAMS - and produce one output | 3. Medium
665 | Customer Account Interface Service (CAIS) - Realtime Account Info | Account info for disconnect notice and current balance are checked | 2. Simple
666 | Customer Account Interface Service (CAIS) - Payment | Payment entered | 2. Simple
667 | MAMS - Meter Asset Management System (AMI) | Updates from Meter Orders (Electric) Produce daily extract for electric meter sets/removes/exchanges. SFTP via RDX the extract to BizTalk | 3. Medium
668 | Customer Account Interface Service (CAIS) - Stop Credit Action | Stop credit action if payment satisfies disconnect amount | 2. Simple
669 | MAMS - Meter Asset Management System (AMI) | Updates from Meter Orders (Gas) Produce daily extract for gas meter sets/removes/exchanges/module retrofits/gas index exchanges. SFTP via RDX the extract to BizTalk | 3. Medium
670 | Meter Data Management System (AMI) | Send Billed Read Produce a batch file containing billed reads to be communicated to the MDMS | 3. Medium
671 | Meter Data Management System (AMI) | On-Cycle Billing Read Request Create extract of meters that need billing reads for the cycle being run in batch today | 3. Medium
672 | Meter Data Management System (AMI) | Off-Cycle Billing Read Request Process same day orders/back-dated orders immediately For future dated orders, wait until the date of execution to send requests to the queue | 3. Medium
673 | MAMS - Meter Asset Management System (AMI) | Send B Meter Test Results CAS will create an extract of B-Meter Test Results conducted the previous day, if any. | 3. Medium
674 | MAMS - Meter Asset Management System (AMI) | Send Annual Consumption File Tracking any development or docuemntation that is needed for the existing creation of Annual Consumption file that will be provided to MAMS at the beginning of the calendar year | 3. Medium
675 | CSS Desktop - Theft Of Service (TOS) | Check CIS authorization | 4. Complex
676 | Customer Account Interface Service (CAIS) - Account Update | Note account | 2. Simple
677 | Customer Data Interface (CDI) - Bill Calc | Bill Calculation | 2. Simple
678 | Customer Data Interface (CDI) - Report Service Issue | Trouble Ticket | 2. Simple
679 | Customer Data Interface (CDI) - Payment | Payment | 2. Simple
680 | Customer Data Interface (CDI) - Account Updates | Inquiries | 2. Simple
682 | MAMS - Meter Asset Management System (AMI) | Gas Module Battery Maintenance Service Request Completion Create Extract of completed gas module battery replacement orders. Send order completion date to MAMS | 3. Medium
685 | SGS ProField Meter | New Route Release Send New Route Release File to AMI Letters Process | 3. Medium
686 | SGS ProField Meter | Post Install File "Consume Post Install Successful Files. Convert files into requisite orders: - Electric Meter Exchange = Meter Exchange, ERT ARCO, AMI Flag ARCO - Gas Module Retrofit = Bill Memo (for possible Gas Index Exchange), ERT ARCO, AMI Flag ARCO - Gas Meter Exchange = Meter Exchange, ERT ARCO, AMI Flag ARCO" | 3. Medium
687 | MAMS - Meter Asset Management System (AMI) | Meter Asset Data "CAS to transform the various updates from MAMS into the following: Meter Billing Constant = dummy meter exchange with new constant Meter Prefix = Meter Prefix ARCO Meter Module ID = ERT ID ARCO" | 3. Medium
688 | Meter Data Management System (AMI) | On-Cycle Billing Read Response Convert billing reads into 5,39 records | 3. Medium
689 | Meter Data Management System (AMI) | Off-Cycle Billing Read Response At some point before AFM processing, take all responses from the CIS response queue, and apply the readings to close out activity records and process through AFM | 3. Medium
690 | Meter Data Management System (AMI) | Commissioning Notification Process commissioning notification file, setting meter to "AMR Ready" | 3. Medium
691 | MAMS - Meter Asset Management System (AMI) | Meter Asset Data to CIS Consume the files - convert them into VSAM files | 3. Medium
692 | MAMS - Meter Asset Management System (AMI) | Meter Test Data to CAS Process Meter Test ARCOs | 3. Medium
693 | SGS ProField Meter | Send RIC Comments Apply RIC Comments and Status to open RIC | 3. Medium
694 | SGS ProField Meter | Post Install File Same as MIV_CO_901 with the addition that this file can contain Sets and Removes in addition to Exchanges | 3. Medium
695 | SGS ProField Meter | Update Deployment Plan Files Process the Deployment Plan Update files | 3. Medium
696 | Telephone Collection (P300R736) | CHICO transactions | 3. Medium
697 | HEAP (P400R736) | UGC ARCOs | 3. Medium
698 | MARC | CHICO transactions | 3. Medium
699 | TCIS | ARCOs, Inquiry transactions | 3. Medium
701 | REPLEVIN - 'PRE HEARING LETTER' Process | Pre Hearing Inquiry transactions | 4. Complex
702 | ADHOC - P400R157 - BX FPET - ServiceLink Info | ARCOs | 3. Medium
703 | NYSERDA Loans File (P400R930) | ARCOs | 3. Medium
704 | EDAP | Daily delta of account changes from CSS to EDAP | 3. Medium
705 | EDAP | Daily delta of BillDetail-Electric from CSS to EDAP | 3. Medium
706 | EDAP | Daily delta of BillDetail-Gas from CSS to EDAP | 3. Medium
707 | EDAP | Daily deltas for MeasurementSeries-Electric (meters) from CSS to EDAP | 3. Medium
708 | EDAP | Daily deltas of MeasurementSeries-Gas (meters) from CSS to EDAP | 3. Medium
709 | EDAP | Daily deltas of Measurement-Electric (meter reads) from CSS to EDAP | 3. Medium
710 | EDAP | Daily delta of Measurement-Gas (meter reads) from CSS to EDAP | 3. Medium
711 | Cycle PET Interface System (C-PET) SHOULD BE REPLACED BY AMI | ARCOs | 3. Medium
713 | EDAP | Daily deltas of Credit from CSS to EDAP | 3. Medium
714 | EDAP | Daily delta of CSS-Inquiry changes from CSS to EDAP | 3. Medium
715 | EDAP | Daily delta from CSS-Vouchers from CSS to EDAP | 3. Medium
716 | EDAP | Daily delta of CSS-Arrears from CSS to EDAP | 3. Medium
717 | EDAP | Daily delta of CSS-CashHistory from CSS to EDAP | 3. Medium
718 | EDAP | Daily delta of CSS-CreditHistory from CSS to EDAP | 3. Medium
719 | DCX (Public Website) | Retreive Account Info, Billing History, Payment History, Transaction Histories | 2. Simple
720 | DCX (Public Website) | Retreive Account Info, Billing History, Payment History, Transaction Histories | 2. Simple
721 | DCX (Public Website) | XPEN Program is being called has a part of Interfaces for DCX services listed below Start Service: DCX_CIS_001 Stop Service: DCX_CIS_002 Transfer Service: DCX_CIS_006 post Meter:DCX_CIS_019 | 2. Simple
722 | DCX (Public Website) | XTON Service is used in below interfaces for DCX Start Service:DCX_CIS_001 Stop Service:DCX_CIS_002 | 2. Simple
723 | DCX (Public Website) QDPP | QDPP call is being made has part of below DCX interfaces: Start Service:DCX_CIS_001 Transfer Service:DCX_CIS_006 Update :DCX_CIS_005 | 2. Simple
724 | DCX (Public Website) - QTOF | QTOF call is being made has part of below DCX interface Stop Service:DCX_CIS_002 | 2. Simple
725 | DCX (Public Website) - QCTF | QCTF is being made has part of below DCX interface Transfer Service:DCX_CIS_006 | 2. Simple
726 | DCX (Public Website) - XEMA | XEMA is called has part of below interface for DCX Update :DCX_CIS_005 | 2. Simple
727 | DCX (Public Website) - QTEL | QTEL call is being made has a part of below interface Update :DCX_CIS_005 | 2. Simple
728 | DCX (Public Website) - XMLA | XMLA call is being made has part of below interface for DCX Update :DCX_CIS_005 | 2. Simple
729 | DCX (Public Website) XBIL | XBIL call is being made has a part of below interface for DCX Update Account :DCX_CIS_005 | 2. Simple
730 | DCX (Public Website) QXTN | QXTN is called has a part interface for DCX Update Account:DCX_CIS_005 | 2. Simple
731 | DCX (Public Website) - XCMP | XCMP call is being made has a part of below interface for DCX Payment:DCX_CIS_014 | 2. Simple
732 | DCX (Public Website) XINE | XINE is being called has part of interface for DCX Payment:DCX_CIS_014 | 2. Simple
733 | DCX (Public Website) - XCMPSHD | XCMPSHD call is being made has a part of itnerface for DCX Payment:DCX_CIS_014 | 2. Simple
734 | DCX (Public Website) - XNOT | XNOT service is being called has a part of DCX interface for Payment:DCX_CIS_014 | 2. Simple
735 | DCX (Public Website) QBLM | QBLM call is being made has a part of interface for DCX for post Meter:DCX_CIS_019 | 2. Simple
736 | DCX (Public Website) - XREF | XREF is called has part of interface for DCX Update Consent:DCX_CIS_020 | 2. Simple
737 | Meter Data Management Information System (MDMSI) | Pricing Data | 3. Medium
738 | Public Assistance Central (PAC) | Cash uploads from checks | 3. Medium
739 | Public Assistance Central (PAC) | Account Updates and Notations | 3. Medium
740 | Public Assistance Central (PAC) | Referrals to departments | 3. Medium
741 | Public Assistance Central (PAC) | Payment Extensions | 3. Medium
742 | Public Assistance Central (PAC) | Reconnect Service | 3. Medium
746 | EDAP | Daily delta of FPET-WorkOrder from FPET to CSS | 3. Medium
747 | Customer Data Interface (CDI) - Stop Service | Turn Off | 2. Simple
748 | Customer Data Interface (CDI) - Start Service | Turn On | 2. Simple
749 | Customer Data Interface (CDI) - Transfer Service | Concurrent Turn On | 2. Simple
750 | Customer Data Interface (CDI) - Reconnect Service | Reconnect | 2. Simple
751 | Customer Data Interface (CDI) - Account Updates | Update Account | 2. Simple
752 | Customer Data Interface (CDI) - Payment Agreement | Payment Agreement | 2. Simple
753 | ITRON | Itron Meter Reading System FCS - ORU | 3. Medium
754 | DCX (Public Website) CUWSO03RetrvCustInterface | CUWSO03RetrvCustInterface web service is called part of interface for DCX. Start Service: DCX_CIMS_001 | 2. Simple
755 | DCX (Public Website) CUWSO08MaintCustomerDataInterface | CUWSO08MaintCustomerDataInterface web service is called part of interface for DCX. Start Service: DCX_CIMS_001 | 2. Simple
756 | DCX (Public Website) CUWSO09AddCustomerDataInterface | CUWSO09AddCustomerDataInterface - web service is called part of interface for DCX. Start Service: DCX_CIMS_001 | 2. Simple
757 | DCX (Public Website) - CUWSO04ReqConnectInfoInterface | CUWSO04ReqConnectInfoInterface web service is called part of interface for DCX. Start Service: DCX_CIMS_001 | 2. Simple
758 | DCX (Public Website) | CUWSO05ProcessConnectInterface web service is called part of interface for DCX. Start Service: DCX_CIMS_001 | 2. Simple
759 | DCX (Public Website) - CUWSO07IssueDisconnectInterface | CUWSO07IssueDisconnectInterface web service is called part of interface for DCX. Stop Service: DCX_CIMS_002 | 2. Simple
760 | DCX (Public Website) - CUWSO19MaintainCustInfoInterface | CUWSO19MaintainCustInfoInterface web service is called part of interface for DCX. Update Service: DCX_CIMS_005 | 2. Simple
761 | DCX (Public Website) | CUGEF01EnrollEFTInterface web service is called part of interface for DCX. Update Service: DCX_CIMS_005 | 2. Simple
762 | DCX (Public Website) | CUGBB01EnrollBudgetBillingInterface web service is called part of interface for DCX. Update Service: DCX_CIMS_005 | 2. Simple
763 | DCX (Public Website) | CUGCL03BPmtAgrUpdateInterface web service is called part of interface for DCX. Update Service: DCX_CIMS_005 | 2. Simple
764 | [pj | CUGCE01CredExtInterface - web service is called part of interface for DCX. Update Service: DCX_CIMS_005 | 2. Simple
765 | DCX (Public Website) | eBillEnroll web service is called part of interface for DCX. Update Service: DCX_CIMS_005 | 2. Simple
766 | DCX (Public Website) - eBillDeEnroll | eBillDeEnroll web service is called part of interface for DCX. Update Service: DCX_CIMS_005 | 2. Simple
767 | DCX (Public Website) - eBillUpdadteEnroll | eBillUpdadteEnroll web service is called part of interface for DCX. Update Service: DCX_CIMS_005 | 2. Simple
768 | DCX (Public Website) - CUGOR01OutageRptInterface | CUGOR01OutageRptInterface web service is called part of interface for DCX. Update Service: DCX_CIMS_005 | 2. Simple
769 | DCX (Public Website) - CUGMR01ValidateReadingInterface | CUGMR01ValidateReadingInterface web service is called part of interface for DCX. Post Meter: DCX_CIMS_022 | 2. Simple
770 | DCX (Public Website) - verify date | CUWSO02AcctDateValidationInterface web service is called part of interface for DCX. Verify Date: DCX_CIMS_010 | 2. Simple
771 | DCX (Public Website) - CUWSO06AcctDateValidationInterface | CUWSO06AcctDateValidationInterface web service is called part of interface for DCX. Verify Date: DCX_CIMS_010 | 2. Simple
772 | O&R Gas Inspection & Maintenance System | GIMS system reads various CIMS system tables such as BILL_ACCT and SAD. | 3. Medium
773 | Revenue & Statistics (REVSTAT) - Revenue DB2 Interface | RCSF Merged files | 3. Medium
774 | Revenue & Statistics (REVSTAT) - Revenue to Other Mainframe Systems Interface | RCSF Merged Files | 4. Complex
775 | Revenue & Statistics (REVSTAT) - Revenue DW Reporting Interface | RCSF Merged files | 4. Complex
776 | SGS ProField Meter | Account Sync CIMS will create a full account data file for every account in the system. To provide the MIV with a daily change file, CIMS will evaluate the current days full sync file vs yesterdays full sync file, and send the records that are different. Provide BizTalk the file to deliver to the MIV | 3. Medium
777 | MAMS - Meter Asset Management System (AMI) | Updates from Meter Orders 1. Produce daily extract for electric and gas meter sets/removes/exchanges/module retrofits/gas index exchanges. SFTP via RDX the extract to BizTalk 2. Update to send Electric Meter SDP Voltage, Gas Meter Drive Rate, Meter Dials value, and Geo Location Quality value | 3. Medium
778 | Meter Data Management System (AMI) | Customer, Account, Service Point, Route, Bill Cycle, Meter Configuration Sync CIMS to provide extract of daily account, meter, trip, billing determinant changes to BizTalk. This extract will contain all the information needed to be passed to the MDMS | 3. Medium
779 | Meter Data Management System (AMI) | Send Billed Read Produce a batch file containing billed reads to be communicated to the MDMS | 3. Medium
780 | Meter Data Management System (AMI) | On-Cycle Billing Read Request Send On-Cycle Billing Read Request to BizTalk | 3. Medium
781 | Meter Data Management System (AMI) | Off-Cycle Billing Read Request "Send Off-Cycle Billing Read Requests to Request Queue for BizTalk Process same day orders/back-dated orders immediately For future dated orders, wait until the date of execution to send requests to the queue" | 3. Medium
782 | MAMS - Meter Asset Management System (AMI) | Get Meter Details Request Adjust meter details screen to send a web service request to MAMS for meter details | 3. Medium
783 | Meter Data Management System (AMI) | Close Service Order Send notification to BizTalk that a AMI Service Order has been closed. Provide either MDMS External Work ID or CIMS Service Order number. | 3. Medium
784 | SGS ProField Meter | New Route Release Send New Route Release File to AMI Letters Process | 3. Medium
785 | SGS ProField Meter | Post Install File 1. "Consume Post Install Successful Files. Convert files into requisite CMOs: - Electric Meter Exchange = Meter Exchange CMO - Gas Module Retrofit = Gas Module Retrofit CMO - Gas Meter Index Exchange (if as found and as left reading is different) = Meter Exchange CMO" 2. Update processing of 907 file to store SDP Voltage in preparation for providing the information to MAMS in the 625 | 3. Medium
786 | Meter Data Management System (AMI) | On-Cycle Billing Read Response Process On-Cycle Billing Reads responses from CIMS response queue | 3. Medium
787 | Meter Data Management System (AMI) | Off-Cycle Billing Read Response Process Off-Cycle Billing Reads responses from CIS response queue | 3. Medium
788 | Meter Data Management System (AMI) | Commissioning Notification Process commissioning notification file, setting meter to "AMR Ready" | 3. Medium
789 | MAMS - Meter Asset Management System (AMI) | Get Meter Details Response Display meter asset information in CIMS | 3. Medium
790 | MAMS - Meter Asset Management System (AMI) | Meter Asset Data to CIMS "Send Meter Asset Data from MAMS to CIMS - this information is used for multiple purposes (See GEMS Impact Analysis.xslx Spreadsheet) including sending FORD meter asset information for service orders. This information will be a daily extract from MAMS containing all meter asset information for O&R. CIMS will drop and reload DB2 tables once daily." CIMS consume the files - populate DB2 databases | 3. Medium
791 | Meter Data Management System (AMI) | Create Service Order Create Service Orders in CIMS. Keep track of MDMS External Work ID | 3. Medium
792 | Meter Data Management System (AMI) | Database Read Response Display register reading and consumption information to CSR in InfoCentral | 3. Medium
793 | Meter Data Management System (AMI) | Power Status Verification Response Create "Get Status" Stored Procedure to retrieve results for PSV for InfoCentral | 3. Medium
794 | Meter Data Management System (AMI) | Remote Connect/Disconnect Switch Status Response Create "Get Status" Stored Procedure to retrieve results for Switch Status for InfoCentral | 3. Medium
795 | Meter Data Management System (AMI) | CSR initiated Remote Connect/Disconnect Response Develop UI Components to process response data from completed Remote Connect or Remote Disconnect transactions for InfoCentral | 3. Medium
796 | Meter Data Management System (AMI) | Database Read Request Update CIMS InfoCentral to send Database Read Requests for AMI Meters to the MDMS | 3. Medium
797 | Meter Data Management System (AMI) | Power Status Verification Request InfoCentral to send Power Status Verification Request to BizTalk to send to MDMS | 3. Medium
798 | Meter Data Management System (AMI) | Remote Connect/Disconnect Switch Status Request InfoCentral to send RCD Switch Status Request to BizTalk to send to MDMS | 3. Medium
799 | Meter Data Management System (AMI) | CSR Initiated Remote Connect/Disconnect Request InfoCentral to Develop UI Components to issue Remote Connect or Remote Disconnect request on AMI Meters | 3. Medium
800 | Retail Access Information System - CECONY Mainframe | Puts 10 gens of ATRAs to server - Put 'J400.P324.A010.RAIS.UNLDATRA(*)' to RAATRA0.TXT | 3. Medium
801 | Retail Access Information System - CECONY Mainframe | Appends latest ATRAs to server - APPEND 'J400.P324.A012.ATRA.COMMON.DATA' to ATRA.TXT | 3. Medium
802 | Retail Access Information System - CECONY Mainframe | Puts Weather (up to date) to server Job P324013F - PUTs 'J400.P324.A013.RAIS.WEATHER' to RAIS.WEATHER.TXT | 3. Medium
803 | Retail Access Information System - CECONY Mainframe | Puts Error Message table to server - JOB P324014F - PUTS 'J400.A510.ERROR.MSG8000' ERR8000.TXT | 3. Medium
804 | Retail Access Information System - CECONY Mainframe | Puts Error Message table to server - Job P324014G - PUTS 'J400.A510.ERROR.MSG8001' to ERR8001.TXT | 3. Medium
805 | Retail Access Information System - CECONY Mainframe | Puts Error Message table to server - Job P324014H - PUTS 'J400.A510.ERROR.MSG8101' to ERR8101.TXT | 3. Medium
806 | Retail Access Information System - CECONY Mainframe | Appends divisional Regular and Time-of-Day Usages to server - APPEND 'J400.P324.A042.*.RACUSAGE' CYUSGE*.TXT' | 3. Medium
807 | Retail Access Information System - CECONY Mainframe | Appends divisional Regular and Time-of-Day Usages to server - APPEND 'J400.P324.A042.*.RACUTOD' BILDTR*.TXT | 3. Medium
808 | Retail Access Information System - CECONY Mainframe | Appends divisional Electric Meter Usages to server - APPEND 'J400.P324.A042.*.RACUEMTR' RACUEM*.TXT | 3. Medium
809 | Retail Access Information System - CECONY Mainframe | Gets Electric Bill History Requests from server - JOB P324050F - GET REQBILLH.TXT 'J400.P324.A050.RAIS.REQEBLH' (REPLACE | 3. Medium
810 | Retail Access Information System - CECONY Mainframe | Puts Electric Bill History Requests to server - JOB P324058F - PUT 'J400.P324.A058.RAIS.EBILHIST' FTPRAIS\EBILHIST.TXT | 3. Medium
811 | Retail Access Information System - CECONY Mainframe | Puts Account Usages to server - JOB P324058G - PUT 'J400.P324.A058.RAIS.RAHUSAGE' RAHUSAGE.TXT | 3. Medium
812 | Retail Access Information System - CECONY Mainframe | Puts Meter Usages to server - JOB P324058H - PUT 'J400.P324.A058.RAIS.METER.USAGE' EBLMETER.TXT | 3. Medium
813 | Retail Access Information System - CECONY Mainframe | Puts Usage Errors to server - JOB P324058I - PUT 'J400.P324.A058.RAIS.RAHERROR' RAHUERR.TXT | 3. Medium
814 | Retail Access Information System - CECONY Mainframe | Puts Transactions to server - JOB P324062F - APPEND 'J400.P324.A062.RAIS.TRANVER' RATRNVER.TXT | 3. Medium
815 | Retail Access Information System - CECONY Mainframe | Puts divisional Cancel Bills to server - JOB P324078F - PUT 'J400.P324.A072.*.CANCEL.ALL.EBILL' CANEBL*.TXT | 3. Medium
816 | Retail Access Information System - CECONY Mainframe | Gets Account Refreshes from server - JOB P324121F - GET RASUBACT.TXT 'J400.P324.A121.RAIS.REFRESH.FTP' (REPLACE | 3. Medium
817 | Retail Access Information System - CECONY Mainframe | Puts divisional Account Refreshes to server - JOB P324122F thru P324127F - PUT 'J400.P324.A12*.RAIS.*REFRES' RAREF*.TXT | 3. Medium
818 | Retail Access Information System - CECONY Mainframe | Puts divisional Meter Refreshes to server - JOB P324122F thru P324127F - PUT 'J400.P324.A12*.RAIS.*REFRES.MTR' RAMTR*.TXT | 3. Medium
819 | Retail Access Information System - CECONY Mainframe | Gets Marketers from server - JOB P324011F - GET MARKAGCY.TXT 'J400.P324.A011.MARKAGCY' (REPLACE | 3. Medium
820 | Transportation Customer Info System - Mainframe | Gets Vouchers from server - JOB P400125F - GET voucfile.txt 'J400.A125.VOUCIN.TCIS' (REPLACE | 4. Complex
821 | Transportation Customer Info System - Mainframe | Puts divisional Cancel Bills to server - JOB P681078F - PUT 'J400.P681.A072.*.CANCEL.ALL.GBILL' CANGBL*.TXT | 3. Medium
822 | Transportation Customer Info System - Mainframe | Puts divisional Arrears to server - JOB P681132F thru P681137F - PUT 'J400.P681.A13*.*.ARREARS.FILE' AREARQN.TXT | 4. Complex
823 | Transportation Customer Info System - Mainframe | Appends divisional Cycle Usages to Server - JOB P681148F - APPEND 'J400.P681.A14*.*.CYCLUS' CYUSGE*.TXT | 4. Complex
824 | Transmission Owners Data Reporting System | Account Maintenance data which details account changes - ie. activity code, SC change, etc. sent from CSS to TODRS | 3. Medium
825 | Transmission Owners Data Reporting System | Daily Billing files sent from CSS to TODRS - Billing data for non-interval metered accounts | 3. Medium
826 | Demand Management Tracking System | Restful API to retrieve customer information upon request | 3. Medium
827 | Energy Efficiency Benchmarking | Restful API to retrieve customer information from CSS Adhoc | 3. Medium
828 | Transportation Customer Info System - Batch | TCIS voucher reconcilitaion procvess. | 3. Medium
829 | Transmission Owners Data Reporting System | Send Billing data for Traction accounts to TODRS | 3. Medium
830 | Retail Access Information System - Batch | Send new and pending enrollments and/or accounts to CIMS - RASUBAEQ.TXT | 3. Medium
831 | Retail Access Information System - Batch | Send new letters from RAIS to CIMS - RASUBCNT.TXT | 3. Medium
832 | Retail Access Information System - Batch | Send price changes from RAIS to CIMS - RASUBPCQ.TXT | 3. Medium
833 | Retail Access Information System - Batch | Send transactions from RAIS to CISM - RASUBTRN.TXT | 3. Medium
834 | Retail Access Information System - Batch | Send new HU requests from ESCO to CIMS - REQBILLH.TXT | 3. Medium
835 | Retail Access Information System - Batch | Send gas nominations to CIMS ~ this is an empty file most of the time except one day a month - REQGSRPT.TXT | 3. Medium
836 | Retail Access Information System - Batch | Send Account Refresh from CIMS to RAIS - RAREFACT.TXT | 3. Medium
837 | Retail Access Information System - Batch | Send enrollment refresh from CIMS to RAIS - RAREFAEQ.TXT | 3. Medium
838 | Retail Access Information System - Batch | Send meter refresh from CIMS to RAIS - RAREFMET.TXT | 3. Medium
839 | Retail Access Information System - Batch | Send transaction refresh from CIMS to RAIS - RAREFTXN.TXT | 3. Medium
840 | Apogee | Apogee vendor that uses the ORBIS web service for retrieve of customer information. Apogee displays different energy pages and ways for customer to save on their electric and gas usage. | 3. Medium
842 | DPET update records | DPET records sent from FPET to CIS | 4. Complex
843 | Daily Update for FPET | Daily update of orders from CAS to FPET | 3. Medium
844 | Service Link | appointment scheduler facility for rmop orders initiated in Service Link to CIS | 3. Medium
845 | Service Link | result (ack or nack) of rmop request initiated in Service Link appointment scheduler | 3. Medium
846 | Work Management System - Logica ARM Suite (WMS) | Receive cancelled RICs information from CIS to WMS. The purpose of this interface is to cancel work request in Logica’s Work Manager for all RICS removed from CIS. The work in CIS is moved over to DB2 AHAR tables (AHTAH004, 001, 007, 013) every night and these tables will be the source of work to be cancelled in Work manager by checking pending work in Work Manager against the list of all work in DB2 AHAR, the pieces of work in Work Manager will be cancelled if a corresponding piece of work does not exist in the DB2 AHAR tables. | 4. Complex
847 | Broadridge | Billing AFP files transmitted to Broadridge for printing, electronic deliveray and archieve | 3. Medium
848 | CAS - NYPA | CSS provides batch files for NYPA system that are further processed in NYPA system and included in the NYPA Bill | 4. Complex
849 | Reconciliation of CSS and Satellite Systems Financial data (RCSF) | This system gets bill transactions from various satellite systems - SB, DG, RNY and TCIS. all the data is stored in RCSF staging tables and then transmitted to REVSTAT | 4. Complex
850 | Reconciliation of CSS and Satellite Systems Financial data (RCSF)/REVSTAT | This system merges Satellelite system revenue fields to CSS REVSTAT. | 4. Complex
851 | Reconciliation of CSS and Satellite Systems Financial data (RCSF)/RNY | RCSF extracts billing details and active account data from RNY(CS) system | 4. Complex
852 | Reconciliation of CSS and Satellite Systems Financial data (RCSF)/DG | RCSF Exstract bill detail and active account data from DG(CS) system | 4. Complex
853 | Reconciliation of CSS and Satellite Systems Financial data (RCSF)/Standby | RCSF Exstract bill detail and active account data from Standby | 4. Complex
854 | Reconciliation of CSS and Satellite Systems Financial data (RCSF)/TCIS | RCSF extracts bill details and active account information from TCIS | 4. Complex
857 | NYPA/ Power for Jobs | NYPA transmits RNY Enrollment file to Con Edison | 3. Medium
862 | IVR Initiated - Direct Payment Enrollment, Payments, Statements | IVR Payments, IVR requets for account staemnts, IVR Direct Payment Enrollment | 2. Simple
868 | NYPA - PFJ | PFJ system transmits usage data to NYPA on daily basis | 3. Medium
869 | DETECTANT DATA EXTRACT - CAS | Detectant Data Extracted from all the boroughs and sent to Detctant Server. This is for Theft of Service | 3. Medium
870 | NYPA - NYPA Vendor | NYPA system transmits NYPA and Traction and Street light bills to New York Power Authority | 3. Medium
871 | CAS- MARC | MARC Data sets are generated from unstack process and FTP'ed to MARC Server | 4. Complex
872 | CIMS EBS General Ledger Postings | The current and previous days GL data created by CIMS is run through CIBGL005 to create the GL interface file for the ORACLE EBS. The module will take the output file created by the daily job PS661DIP and reformat it to be sent to the new GL on a daily basis. PS661DIP uses data files from PS658DIP, PS659DIP AND PS660DIP to create one file to be reformatted and send to EBS. | 4. Complex
873 | Payment Processing (Mavro) | Mainframe job PI069RIP, DPP Extract, 3 x Daily | 3. Medium
874 | Payment Processing (Mavro) | Mainframe job PI082DIP, Bad Check Extract, 3 x Daily | 3. Medium
875 | Pitney Bowes: Code-1 | Code-1 Plus validates, corrects and standardizes customer address data. The technology is CASS Certified by the USPS. The Code-1 Plus standardizes mailing addresses by adding missing address information, Standardizing city names and state abbreviations, Correcting misspelled address elements and appending ZIP + 4 and carrier route information. Once the billing file is run through Code 1 software the file is then used to mail bills. | 3. Medium
876 | Finalist | flatfiles for address cleansing | 3. Medium
877 | Finalist | file with cleansed addresses | 3. Medium
882 | Bill Presentment - Exstream (Open Text) | CECONY: Exstream gets data from CSS and creates customer Bills, postcards and credit/AMI letters. O&R: Exsteam gets data from CIMS and creates bills and letters. | 3. Medium
883 | TROUBLE ORDER SYSTEM | As part of AMI Release3 closed work orders for methane sensors will be sent to CIMS | 3. Medium
884 | Open Text - Exstream Letter and Postcard | flat file with customer data | 3. Medium
885 | Weather Normalization System | Heating Degree Days (HDDs) are the weather related measurement by which the quantification of the impact on sales volumes between current actual weather conditions versus prior actual weather conditions or normal weather conditions during periods of the year where heating of homes and businesses is required. Similarly, Cooling Degree Days (CDDs) are the weather related measurement by which the quantification of the impact on sales volumes between current actual weather conditions versus prior actual weather conditions or normal weather conditions during periods of the year where cooling of homes and businesses is required. This feeds into FMBC. | 2. Simple
AMI-P2 | AMI - MAMS/CAS - Post Install File from ServiceLInk | Post Install File from ServiceLInk | 3. Medium
AMI-P2 | AMI - MAMS/CIMS - Updates from Meter Orders | Updates from Meter Orders | 4. Complex
AMI-P2 | AMI - MDMS/CSSDesktop - On Demand Read Request | On Demand Read Request | 3. Medium
AMI-P2 | AMI - MDMS/CSSDesktop - CSR Initiated Remote Connect/Disconnect Request | CSR Initiated Remote Connect/Disconnect Request | 3. Medium
AMI-P2 | AMI - MDMS/CSSDesktop - Informational Bill Request | Informational Bill Request | 3. Medium
AMI-P2 | AMI - MDMS/CSSDesktop - Power Status Verification Request | Power Status Verification Request | 2. Simple
AMI-P2 | AMI - MDMS/CSSDesktop - Remote Connect/Disconnect Switch Status Request | Remote Connect/Disconnect Switch Status Request | 3. Medium
AMI-P2 | AMI - MDMS/CSSDesktop - Database Read Request | Database Read Request | 2. Simple
AMI-P2 | AMI - MDMS/CSSDesktop - On Demand Read Response | On Demand Read Response | 3. Medium
AMI-P2 | AMI - MDMS/CSSDesktop - CSR initiated Remote Connect/Disconnect Response | CSR initiated Remote Connect/Disconnect Response | 3. Medium
AMI-P2 | AMI - MDMS/CSSDesktop - Informational Bill Response | Informational Bill Response | 3. Medium
AMI-P2 | AMI - MDMS/CSSDesktop - Power Status Verification Response | Power Status Verification Response | 2. Simple
AMI-P2 | AMI - MDMS/CSSDesktop - Remote Connect/Disconnect Switch Status Response | Remote Connect/Disconnect Switch Status Response | 3. Medium
AMI-P2 | AMI - MDMS/CSSDesktop - Database Read Response | Database Read Response | 2. Simple
AMI-P2 | AMI - MDMS/CIMS - Close Service Order | Close Service Order | 3. Medium
AMI-P2 | AMI - SGSProfieldMM/CIMS - Post Install File | Post Install File | 3. Medium
AMI-P3 | AMI - MAMS/CIMS - Methane Sensor Service Order Update (O&R) | Methane Sensor Service Order Update (O&R) | 3. Medium
AMI-P3 | AMI - MDMS/CIS - Get billing determinants for off-cycle reads (i.e. Move Out, Move In, Rate Change, TONP, Seasonal) | Get billing determinants for off-cycle reads (i.e. Move Out, Move In, Rate Change, TONP, Seasonal) | 4. Complex
AMI-P3 | AMI - MDMS/CIMS - Get billing determinants for off-cycle reads (i.e. Move Out, Move In, Rate Change, TONP, Seasonal) | Get billing determinants for off-cycle reads (i.e. Move Out, Move In, Rate Change, TONP, Seasonal) | 4. Complex
AMI-P3 | AMI - MDMS/CIMS - Customer, Account, Service Point, Route, Bill Cycle, Meter Configuration Sync | Customer, Account, Service Point, Route, Bill Cycle, Meter Configuration Sync | 4. Complex
AMI-P3 | AMI - MDMS/CIS - Off-Cycle Billing RCD Request | Off-Cycle Billing RCD Request | 3. Medium
AMI-P3 | AMI - MDMS/CIMS - Off-Cycle Billing RCD Request | Off-Cycle Billing RCD Request | 3. Medium
AMI-P3 | AMI - MDMS/CIMS - Close Methane Sensor Order (O&R) | Close Methane Sensor Order (O&R) | 3. Medium
AMI-P3 | AMI - MDMS/CIS - Off-Cycle Billing Read Request | Off-Cycle Billing Read Request | 3. Medium
AMI-P3 | AMI - MDMS/CIMS - On-Cycle Billing Read Request | On-Cycle Billing Read Request | 3. Medium
AMI-P3 | AMI - MDMS/CIMS - Off-Cycle Billing Read Request | Off-Cycle Billing Read Request | 3. Medium
AMI-P3 | AMI - MDMS/CIS - Off-Cycle Billing RCD Response | Off-Cycle Billing RCD Response | 3. Medium
AMI-P3 | AMI - MDMS/CIMS - Off-Cycle Billing RCD Response | Off-Cycle Billing RCD Response | 3. Medium
AMI-P3 | AMI - MDMS/CIS - Off-Cycle Billing Read Response | Off-Cycle Billing Read Response | 3. Medium
AMI-P3 | AMI - MDMS/CIMS - On-Cycle Billing Read Response | On-Cycle Billing Read Response | 3. Medium
AMI-P3 | AMI - MDMS/CIMS - Off-Cycle Billing Read Response | Off-Cycle Billing Read Response | 3. Medium
AMI-P3 | AMI - CAS - Customer Communications Logging for Rate Pilot | Customer Communications Logging for Rate Pilot | 3. Medium
AMI-P3 | AMI - CIMS - Customer Communications Logging for Rate Pilot (O&R) | Customer Communications Logging for Rate Pilot (O&R) | 3. Medium
AMI-P3 | AMI - OMS/CIS - Critical Customer Type Data Load | Critical Customer Type Data Load | 3. Medium
AMI-P3 | AMI - CAS - Post Install File from ServiceLInk | Post Install File from ServiceLInk | 3. Medium
AMI-P3 | AMI - CIMS - Methane Sensor Installation Information File (O&R) | Methane Sensor Installation Information File (O&R) | 3. Medium
BILL | Bill Presentment - Exstream (Open Text) | Creates bill | 3. Medium
TREASURY | CIMS to PayPilot - Customer Refund Check file |  | 4. Complex
TREASURY | CIMS to PayPilot - Customer Refund Check file |  | 4. Complex
TREASURY | CSS to PayPilot - Customer Refund Check file |  | 4. Complex

## Attachment 7
Final Actual Interfaces |  |  | Click Here to Retun To Summary Sheet
ID | Title | System Interface | Description | Complexity
543658 | CORE-FCC-ICI-1112 | NGD business | CECONY business manually creates the file in order to avoid the errors created through manual entry for NGD’s | 3. Medium
42574 | CORE-AMI-IOI-205 | Intelemeters | Meter Read Upload for Intellimeter. Intellimeter are meters that reside in the Palisade Mall in Nanuet, NY. The Customer Accounting Department has a software on desktop that reads these meters once a month. The readings are saved to a text file which will be sent to middleware which will convert data to XML format and send it to MDM. | 3. Medium
324931 | CORE-AMI-IOI-1050 | Intelemeters | Middleware Changes- This is associated with existing rice-id 205, this interface has to be split into 2 processes – 1 RICE-ID for handling actual file and 2 RICE-ID for handling cross reference data file. | 3. Medium
440514 | CORE-RBP-IAI-1082 | Fiserv Walkin - CCB | EOD Reconciliation Files for NY and ORU/RECO(Fiserv Walkin) | 3. Medium
39142 | CORE-RBP-IAI-383 | 3 POINT PAYMENT PROCESSING | 3 Point Payment Processing system sends the DPP Extract (i.e. Enrollment) to CC&B. | 3. Medium
39136 | CORE-RBP-IAI-377 | 3 POINT PAYMENT PROCESSING | 3-Point Payment (A/R) File (Misc. Payment file) from 3 Point Payment Processing Post payments to customers accounts (Note: 3 Point Payment Processing is assigned some checks on a quarterly basis to verify that its payment process works as expected.) | 3. Medium
168712 | CORE-RBP-IAO-854 | 3 POINT PAYMENT PROCESSING | send billing data file to 3PP.File generated as part of CORE-RBP-IAO-374 needs to be duplicated and sent to 3PP location. | 3. Medium
382926 | CORE-RBP-ICO-1070 | NYPA | Monthly Extract for different record types for NYPA Traction accounts | 3. Medium
381112 | CORE-CUS-ICO-1069 | WDSS | Daily Data extract file to public agency - WDSS for the Customer’s enrolled in DVC program | 3. Medium
381109 | CORE-CUS-ICO-1068 | HRA | Daily Data extract file to public agency - HRA for the Customer’s enrolled in DVC program | 3. Medium
381105 | CORE-CUS-ICO-1067 | HRA | Create an error file for the records that could not be processed from CCB to HRA | 3. Medium
381102 | CORE-CUS-ICO-1066 | HRA | Create an Acknowledgement file for the processed records from CCB to HRA | 3. Medium
360319 | CORE-CUS-ICI-1065 | WDSS | Quarterly response file from Agency WDSS to CCB | 3. Medium
360318 | CORE-CUS-ICI-1064 | HRA | Quarterly response file from Agency HRA to CCB | 3. Medium
360317 | CORE-CUS-ICO-1063 | WDSS | Send Quarterly customer information to WDSS | 3. Medium
360316 | CORE-CUS-ICO-1062 | HRA | Send Quarterly customer information to HRA | 3. Medium
360315 | CORE-CUS-ICO-1061 | WDSS | Send daily arrears and disconnect FA information to WDSS agency. | 3. Medium
360314 | CORE-CUS-ICO-1060 | HRA | Send daily arrears and disconnect FA information to HRA agency. | 3. Medium
360313 | CORE-CUS-ICO-1059 | WDSS | Daily Data extract file to public agencies - WDSS for customers enrolled in UGC Program | 3. Medium
360312 | CORE-CUS-ICO-1058 | HRA | Daily Data extract file to public agencies - HRA for customer enrolled in UGC Program | 3. Medium
360311 | CORE-CUS-ICI-1057 | HRA | Weekly response inbound file from HRA to CCB | 3. Medium
360310 | CORE-CUS-ICO-1056 | HRA | Weekly data extract outbound file from CCB to HRA | 3. Medium
334935 | CORE-CUS-ICI-1053 | HRA | HRA to CCB Agency Data file | 3. Medium
38923 | CORE-CUS-IOO-023 | Intrado - TFCC | Twice a month customer data is shared with TFCC. This is used to verify customer information during GetAccountInformation Webservice failure/outage. Since O&R doesn't have 24*7 call center, this dump is critical for TFCC. | 2. Simple
39121 | CORE-FCC-IOI-513 | Intrado - TFCC | TFCC sends the message log to CC&B for outages reported by customer using text messages for ORU. | 3. Medium
37198 | CORE-FCC-IOI-510 | Intrado - TFCC | TFCC sends failover batch outage request to CC&B for ORU. | 3. Medium
37197 | CORE-FCC-IOI-509 | Intrado - TFCC | TFCC sends real time outage request to CC&B for ORU. | 3. Medium
228209 | CORE-CUS-IOI-1005 | Intrado (TFCC) | Retrieve Customer Information | 3. Medium
37196 | CORE-FCC-ICI-508 | Intrado - TFCC | TFCC retrieves customer information from CC&B for CECONY. | 3. Medium
37195 | CORE-FCC-IAI-507 | Intrado - TFCC | TFCC pings CC&B to check connectivity for CECONY. | 2. Simple
37194 | CORE-FCC-ICI-506 | Intrado - TFCC | TFCC send the Trouble Order creation request to CC&B for CECONY. | 3. Medium
42583 | CORE-RBP-ICO-214 | CUS | This is an extract of usage information from CC&B to the Customer Usage system which is fed to other systems. This should be built as an touchpoint to a data warehouse as CUS is not really a standard integration. | 4. Complex
39115 | CORE-RBP-ICO-524 | CUS | This is an extract of Account information from CC&B to the Customer Usage system which is fed to other systems. This should be built as an touchpoint to a data warehouse as CUS is not really a standard integration. | 3. Medium
235262 | CORE-RBP-ICO-1009 | CUS | RE_STAGE_RPHIST extract | 3. Medium
157669 | CORE-RBP-ICO-726 | CUS | CALENDAR Extract | 2. Simple
157668 | CORE-RBP-ICO-725 | CUS | TRIP_CALENDAR Extract | 2. Simple
39119 | CORE-RBP-ICO-528 | CUS | This is an extract of Gas usage information from CC&B to the Customer Usage system which is fed to other systems. This should be built as an touchpoint to a data warehouse as CUS is not really a standard integration. | 3. Medium
39127 | CORE-RBP-ICO-529 | CUS | This is an extract of Meter Attribute information from CC&B to the Customer Usage system which is fed to other systems. This should be built as an touchpoint to a data warehouse as CUS is not really a standard integration. | 3. Medium
157661 | CORE-RBP-ICO-717 | CUS | RE_STAGE_QTR_GAS_MISSING_BILLS Extract | 4. Complex
157660 | CORE-RBP-ICO-716 | CUS | RE_STAGE_CAP_ACCTTAG Extract | 3. Medium
157643 | CORE-RBP-ICO-699 | CUS | RE_STAGE_EBILLS Extract | 3. Medium
157644 | CORE-RBP-ICO-700 | CUS | RE_STAGE_G_METER Extract | 3. Medium
157645 | CORE-RBP-ICO-701 | CUS | RE_STAGE_GBILLS Extract | 3. Medium
157646 | CORE-RBP-ICO-702 | CUS | RE_STAGE_HEAPINFO Extract | 4. Complex
157647 | CORE-RBP-ICO-703 | CUS | RE_STAGE_RMTRITEM Extract | 3. Medium
157651 | CORE-RBP-ICO-707 | CUS | RE_STAGE_MINFO_TODS Extract | 3. Medium
157653 | CORE-RBP-ICO-709 | CUS | RE_STAGE_GAS_REV_NEW_COLS Extract | 4. Complex
157652 | CORE-RBP-ICO-708 | CUS | D_CSC_PSC_EFF_DT Extract | 3. Medium
157648 | CORE-RBP-ICO-704 | CUS | RE_STAGE_TODL Extract | 4. Complex
157649 | CORE-RBP-ICO-705 | CUS | RE_STAGE_VTOD Extract | 4. Complex
157650 | CORE-RBP-ICO-706 | CUS | RE_STAGE_EBILL_TODS Extract | 3. Medium
37112 | CORE-CUS-IAO-005 | Spectrum | On-line Mailing Address Cleansing/Validation - User should have the ability to validate/update the mailing address using a Finalist Service. User should have an ability NOT to override if the customers does not give the consent. This may be a synchronous process. | 3. Medium
37143 | CORE-FCC-ICI-455 | Gas Central | Gas Central sends daily gas meter work completion information to CC&B. | 3. Medium
170735 | CORE-FCC-IOO-790 | TRBL | MPT_DETAILS_TBL | 4. Complex
170725 | CORE-FCC-IOO-786 | TRBL | SO_FLD_ORD | 4. Complex
170744 | CORE-FCC-IOO-794 | TRBL | MAMS_GAS_MAST | 4. Complex
170754 | CORE-FCC-IOO-798 | TRBL | CRITICAL_ACCT | 4. Complex
170755 | CORE-FCC-IOO-799 | TRBL | BUILDING | 4. Complex
170700 | CORE-FCC-IOO-778 | TRBL | SERV_ORD | 4. Complex
170704 | CORE-FCC-IOO-779 | TRBL | FORD_HDR | 4. Complex
39253 | CORE-FCC-IOO-084 | ORU WMS | CC&B sends service point, account and address information to WMS to create service investigation jobs. | 3. Medium
187491 | CORE-RBP-IOO-914 | OMI | Extract TAR_SCH | 3. Medium
182525 | CORE-RBP-IOO-901 | OMI | Service Point Extract for OMI | 3. Medium
42550 | CORE-RBP-IOO-133 | OMI | Account Extract for OMI | 2. Simple
67868 | CORE-TPI-ICO-582 | TCIS | Interface for sending daily meter refresh information from CC&B to TCIS-CECONY Initially we had same RICE IDS for TCIS (Enroll and HU processing), now we have split all the Account enroll refresh into one FSD and all HUs into other FSD. So, we need two new RICE IDs to support the account enroll refresh FSD and existing ones we are using for HUs FSD | 3. Medium
38995 | CORE-TPI-ICO-252 | TCIS | TCIS will directly query TCBS DB2 table on mainframe to validate the enrollments and accept/reject accordingly. If Enrollment is accepted, TCIS will get information from DB2 tables and builds the Enrollment response. | 3. Medium
38991 | CORE-TPI-IOO-248 | RAIS | Daily meter refresh process for ORU- CC&B provides meter refresh information to RAIS for previous day's cycle date/Meter read date. | 3. Medium
38989 | CORE-TPI-IOO-246 | RAIS | Daily Account Refresh for ORU - CC&B will send daily Account Refresh file to RAIS. The file will have the ESCO customer account information for the all active accounts. | 3. Medium
38985 | CORE-TPI-ICO-242 | RAIS | Daily meter refresh process for CECONY - CC&B provides meter refresh information to RAIS for previous days cycle. | 3. Medium
38984 | CORE-TPI-ICO-241 | RAIS | Daily account refresh process for CECONY - CC&B responds with daily account refresh information to RAIS | 3. Medium
168228 | CORE-FCC-ICO-837 | WMS EIE to CORE EIE | Work order update assignment updated with SDP details - MIV_CI_922 | 3. Medium
37166 | CORE-FCC-IAO-478 | MDMS | CC&B sends Methane Sensor, Hot Socket Field Activity and Over Capacity Alarm completion message to MDMS. MDM_OI_368 MDM_CI_387 | 3. Medium
198376 | CORE-FCC-IAO-933 | MDMS | Allow CC&B to send a fail or pass result (with the Ticket/Outage ID from downstream system if the result is pass) to MDMS as a response to the outage creation request | 3. Medium
39097 | CORE-RBP-ICO-367 | CCG | Account Information Details | 4. Complex
198419 | CORE-RBP-IOI-936 | NYISO | Interface to download hourly interval price information from NYISO-ORU | 3. Medium
37129 | CORE-FCC-ICI-441 | CRMS(PEGA) | CRMS(PEGA) sends referrals and notes to CC&B. | 3. Medium
235291 | CORE-TPI-ICI-1018 | TCIS | MultiMeterAcctMeterUsgLst | 3. Medium
235292 | CORE-TPI-ICI-1019 | TCIS | ValidateAdhocAccount | 3. Medium
67866 | CORE-RBP-IOI-580 | IVR ORU | IVR OR has payment posting functionality. This was not discussed in the Payment IT workshop and this was missed out. While referring to Mid-Tier Webservices this has been captured. We need to add a RICE as IVR-OR is a separate instance. Need to create RICE CORE-RBP-IOI-580 | 3. Medium
207961 | CORE-RBP-IAO-980 | BNY Mellon | ACH refunds | 3. Medium
207962 | CORE-RBP-IAI-981 | BNY Mellon | Process return ACH refund | 3. Medium
185512 | CORE-FCC-ICI-908 | CXS (PEGA) | Post an adjustment for gas inspection | 3. Medium
168288 | CORE-FCC-ICO-850 | eGIS | Methane Sensor extract on add, remove, exchange | 3. Medium
276312 | CORE-CUS-IAI-1040 | Message Broadcast | MB Stop Notify | 3. Medium
137310 | CORE-CUS-ICO-734 | Questline | Send active residential customer information having no language or preferred language other than Spanish | 3. Medium
185547 | CORE-FCC-IOI-910 | DRO | Get Account Information for DRO | 3. Medium
158043 | CORE-FCC-IOO-809 | FORD | Special Project Create master file | 3. Medium
158049 | CORE-FCC-IOI-810 | FORD | Special Project Create Field activity file | 3. Medium
182520 | CORE-FCC-IOO-900 | Outage DB | CC&B retrieves Hot Socket closure information from Outage DB | 3. Medium
185277 | CORE-FCC-IOO-903 | Outage DB | Retrieve Outage Status | 3. Medium
235267 | CORE-CUS-IOO-1010 | Questline | Share ORU residential newly added account information | 3. Medium
223092 | CORE-IT-IAO-1001 | Message Broadcast | Received Payment | 3. Medium
157603 | CORE-IT-IAO-666 | Message Broadcast | overdue payment alert(arrears) notification | 3. Medium
235251 | CORE-FCC-IOO-1007 | TRBL | Send Gas Meter Orders Delta File | 3. Medium
200219 | CORE-TPI-IOI-949 | TCIS | GetMptDetailsTbl | 3. Medium
200221 | CORE-TPI-IOI-951 | TCIS | GetCdTarSch | 3. Medium
235288 | CORE-TPI-ICI-1015 | TCIS | GetSCChangeEffectiveDate | 3. Medium
235289 | CORE-TPI-ICI-1016 | TCIS | SingleMeterAcctUsgList | 3. Medium
235290 | CORE-TPI-ICI-1017 | TCIS | MultiMeterAcctUgSummList | 3. Medium
168177 | CORE-FCC-IOI-824 | ProField | ProField Meter sends Methane Sensor Installation Information file to CC&B - MIV_OO_953 | 3. Medium
185569 | CORE-FCC-IOI-912 | CIMS Central | Create Customer Contact | 3. Medium
37118 | CORE-CUS-IAI-010 | DCX | CE/O&R - DCX Find Account - Returns account information based on input parameters - /v1/accounts/find --> Multi Parameter, subset of information | 2. Simple
39114 | CORE-RBP-ICI-363 | Broadridge | This is an incoming file from Broadridge containing list of customers for which eBill email did not deliver due to incorrect email address. The CC&B process will read this file and remove the customers from e-bill in CC&B (Update Bill Route Type from bill to Postal, Update email address to blank and remove/update account Characteristic of ebill for the customer) | 2. Simple
39179 | CORE-IT-IAO-566 | EDAP | Meter Configuration Extract | 3. Medium
211495 | CORE-RBP-ICO-940 | Message Broadcast | Statement File to MB | 3. Medium
228215 | CORE-IT-IAO-1006 | Message Broadcast | Report Outage confirmation | 3. Medium
131106 | CORE-CUS-IOI-636 | IVR ORU | Retrieve account information for IVR-ORU | 3. Medium
180099 | CORE-RBP-IAI-888 | RevDEMO | Account information sync | 3. Medium
227706 | CORE-RBP-IAO-1004 | RevDEMO | RevDemo Account Details Update | 3. Medium
235294 | CORE-TPI-ICI-1022 | TCIS | GetAccountLPC | 3. Medium
235293 | CORE-TPI-ICI-1021 | TCIS | GetNextCycleDate | 3. Medium
200216 | CORE-TPI-IOI-946 | TCIS | GetAccountTariffRate | 3. Medium
235287 | CORE-TPI-ICI-1014 | TCIS | ADHOCforDiscrepancy | 3. Medium
235286 | CORE-TPI-ICI-1013 | TCIS | GetAdhocAccount | 3. Medium
200214 | CORE-TPI-IOI-944 | TCIS | GetServicePointMeterNumber | 3. Medium
200210 | CORE-TPI-IOI-943 | TCIS | GetPremiseNoCustNumCompanyCode | 3. Medium
180033 | CORE-RBP-ICI-884 | DCX | Provide customer MAIDs who opted out of the Rate Pilot Program | 3. Medium
201247 | CORE-CUS-IAI-959 | DCX | Create Profile with Linked Account | 3. Medium
201251 | CORE-CUS-IAI-960 | DCX | Update Profile and Account Linkage | 3. Medium
235255 | CORE-FCC-IOI-1008 | FORD | Create critical contact for the regulatory Meter test orders dispatched ('Lock and Load') in FORD | 3. Medium
200243 | CORE-RBP-IOO-957 | Exstream-Broadridge | Send Summary Bill extract file generated from CC&B to OpenText Exstream – ORU/RECO | 3. Medium
295002 | CORE-FCC-IOI-1042 | Alorica | IVR Alorica Payment Agreement Results | 3. Medium
295000 | CORE-FCC-IOO-1041 | Alorica | IVR Alorica Payment Agreement | 3. Medium
295003 | CORE-FCC-IOO-1043 | Alorica | IVR Alorica Field Eligible | 3. Medium
224387 | CORE-RBP-ICI-1003 | Paymentus | Processing credit card payments through Paymentus | 3. Medium
137581 | CORE-CUS-IAI-730 | DCX | Get Large Customer information | 4. Complex
137392 | CORE-CUS-ICO-685 | DPT | Customer Contact Extract for residential accounts for DPT survey | 3. Medium
178496 | CORE-CUS-ICO-859 | DPT | Customer Contact Extract for commercial accounts for DPT survey | 3. Medium
160100 | CORE-CUS-ICO-827 | Questline | Send active commercial customer information having no language or preferred language other than Spanish | 3. Medium
168173 | CORE-FCC-ICI-823 | ProField | Methane sensor post install file from PFM - MIV_CO_951 | 3. Medium
168179 | CORE-FCC-ICI-825 | Gas Ops | Gas OPS provides the Methane Sensor location file to be processed at CCB - MIV_CI_950 | 3. Medium
168184 | CORE-FCC-ICO-829 | ProField | Gas OPS provides the Methane Sensor location file to be processed at CCB - MIV_CI_950 | 3. Medium
168187 | CORE-FCC-IAI-830 | ProField | AP Socket/Connected DR creation from PFE to CCB - MIV_AO_940 | 3. Medium
185561 | CORE-FCC-IOI-911 | CIMS Central | Retrieve Meter Information | 3. Medium
37120 | CORE-CUS-IAI-012 | DCX | CE/O&R - DCX Get Account by MAID - Returns the account information based on MAID | 3. Medium
37119 | CORE-CUS-IAI-011 | DCX | CE/O&R - DCX Get Account by Account Number - Returns account information based on input parameters as account number. Returns account information based on input parameters - /v1/accounts --> Parameter is Acct Number, Larger Resp Body with Account Info | 3. Medium
295008 | CORE-FCC-IOI-1046 | Alorica | IVR Alorica Final Bill Reminder Results | 3. Medium
295006 | CORE-FCC-IOO-1045 | Alorica | IVR Alorica Final Bill Reminder | 3. Medium
295005 | CORE-FCC-IOI-1044 | Alorica | IVR Alorica Field Eligible Results | 3. Medium
276326 | CORE-CUS-ICI-1037 | DCX | Get Eligible Parents by OktaUserID | 3. Medium
207985 | CORE-RBP-ICO-982 | DCAS | SARS report data file | 3. Medium
206567 | CORE-TPI-IOI-976 | RAIS-OR | Debit Credits file received as part of daily transactions | 3. Medium
206607 | CORE-TPI-ICI-978 | RAIS-CE | ED/EC transaction as part of daily transaction | 3. Medium
94820 | CORE-FCC-IAO-628 | MDMS | Interface for virutal SP flex sync request | 3. Medium
70885 | CORE-TPI-IOO-611 | Retail Choice Team O&R | Additional touchpoint for the Reconciliation report that goes to business. Interface for sending 810 user file to business as part of their reconciliation | 3. Medium
200802 | CORE-TPI-IOO-958 | RAIS O&R | Interface for sending monthly electric usage User File for all customers in current billing cycle from CC&B to RAIS (O&R) - User File | 3. Medium
158029 | CORE-RBP-IAI-772 | DCX | Retrieve Summary Bill CSV | 4. Complex
67870 | CORE-FCC-ICO-583 | Gas Central | There are 2 distinct touchpoints for Get Outage Tickets and Search Outage Tickets but there was only one RICE defined. Need to add the second RICE for the touchpoint. CORE-FCC-ICI-583: Get Outage Ticket Details | 3. Medium
211657 | CORE-CUS-IAO-994 | DCX | Outbound message on service start | 3. Medium
211661 | CORE-CUS-IAO-995 | DCX | Outbound message on service stop | 3. Medium
157997 | CORE-FCC-ICI-764 | WMS(CE) | CC&B receives RIC Cancellation Response from WMS | 3. Medium
180034 | CORE-RBP-ICI-885 | RevDemo | Pass the customer opted out information from RevDemo API | 3. Medium
157587 | CORE-RBP-ICO-759 | CCG | Last 24 months of TODL for a CORP code. | 4. Complex
157586 | CORE-RBP-ICO-758 | CCG | Last 24 months of steam payments for a CORP code | 4. Complex
157580 | CORE-RBP-ICO-752 | CCG | Last 24 months of steam payments for an account. | 4. Complex
37189 | CORE-FCC-ICI-501 | Service Link | ServiceLink sends Post Install File to CC&B. | 3. Medium
237126 | CORE-CUS-IOI-1029 | IVR-ORU | Retrieve new call event and identify account based on customer details through CTI-IVR mechanism | 3. Medium
237127 | CORE-CUS-IOO-1030 | IVR-ORU | Respond with Passback Account Number for Un-Authenticated calls for interaction ID | 3. Medium
276327 | CORE-CUS-ICI-1038 | DCX | Get Enrolled Parents by OktaUserID | 3. Medium
276329 | CORE-CUS-ICI-1039 | DCX | Get Enrolled Children by Parent Maid | 3. Medium
37187 | CORE-FCC-IAO-499 | MAMS | CC&B sends Methane Sensor installation information to MAMS for CECONY and ORU MAM_CI_714 | 3. Medium
157991 | CORE-FCC-ICI-763 | WMS(CE) | CC&B receives RIC Creation Response from WMS | 3. Medium
37135 | CORE-FCC-ICO-447 | FPET | CC&B sends field activity status update to FPET | 3. Medium
37133 | CORE-FCC-ICO-445 | FPET | CC&B send real-time field activity creation request to FPET. | 4. Complex
94821 | CORE-FCC-IAI-629 | MDMS | Interface for flex sync response | 3. Medium
94822 | CORE-FCC-IAI-630 | MDMS | Interface for virtual SP flex sync response | 3. Medium
157585 | CORE-RBP-ICO-757 | CCG | Last 24 months of electric and gas payments for a CORP code | 4. Complex
157584 | CORE-RBP-ICO-756 | CCG | Electric, gas, steam meter information based on the CORP code | 4. Complex
157583 | CORE-RBP-ICO-755 | CCG | Last 12 or 24 months of electric, steam, gas bills for a CORP code. | 4. Complex
157582 | CORE-RBP-ICO-754 | CCG | Last 24 months of ICAP for an account. | 4. Complex
157581 | CORE-RBP-ICO-753 | CCG | Last 24 months of TODL for an account. | 4. Complex
157579 | CORE-RBP-ICO-751 | CCG | Last 24 months of electric and gas payments for an account. | 4. Complex
157577 | CORE-RBP-ICO-750 | CCG | Electric, gas, steam meter information for an account. | 4. Complex
157576 | CORE-RBP-ICO-749 | CCG | Last 24 months of electric, steam, gas bills for an account. | 4. Complex
157574 | CORE-RBP-ICO-748 | CCG | Summary details related to Usage, Charges, Outstanding balance, Last Payment for all accounts with the CORP code | 4. Complex
158055 | CORE-FCC-IOI-812 | FORD | Lock and Load process - status of order being worked on | 3. Medium
37146 | CORE-FCC-ICI-458 | Gas Central | Gas Central sends RIC status and comments to CC&B. | 3. Medium
198391 | CORE-FCC-IOI-934 | TRBL | Allow TRBL-GMD to send a fail or pass result (with the Outage ID from TRBL-GMD system if the result is pass) to CC&B as a response to the outage creation | 3. Medium
170643 | CORE-RBP-ICO-698 | DCAS | DCAS - Supplemental Meter Exchange File | 4. Complex
189709 | CORE-IT-IOO-921 | Broadridge | EBill Enrollments notifications | 3. Medium
137576 | CORE-RBP-IAI-729 | KIOSK | Interface to do account inquiry along with previous banking information | 3. Medium
37136 | CORE-FCC-ICI-448 | Servicelink | Servicelink sends FA Interim status to CC&B | 4. Complex
235270 | CORE-CUS-IOO-1011 | Questline | Share ORU non-residential newly added account information | 3. Medium
235271 | CORE-CUS-IOO-1012 | Questline | Share RECO residential and non-residential newly added account information | 3. Medium
170767 | CORE-FCC-IOO-808 | Street Light | PAL_MATRIX | 4. Complex
58257 | CORE-IT-IAO-565 | EDAP | Budget-Billing Extract | 3. Medium
137604 | CORE-RBP-IAO-746 | ARC | Payment Summary Extract | 3. Medium
137609 | CORE-RBP-IAO-747 | Blackline | Payment Summary Extract | 3. Medium
157617 | CORE-IT-IAO-671 | Message Broadcast | receive stop service notification | 3. Medium
157614 | CORE-IT-IAO-670 | Message Broadcast | receive transfer service notification | 3. Medium
211671 | CORE-RBP-ICO-997 | DCX_ETL (Opower) | share usage data for non- residential customers | 3. Medium
211667 | CORE-RBP-ICO-996 | DCX_ETL (Opower) | Share usage data for residential customers | 3. Medium
211508 | CORE-IT-IOO-974 | Exstream-Broadridge | Send Letter extract file for ORU Customers | 3. Medium
196878 | CORE-IT-IAO-922 | Message Broadcast | Received start service request | 3. Medium
157611 | CORE-IT-IAO-667 | Message Broadcast | overdue payment alert(PA installment overdue) notification | 3. Medium
157612 | CORE-IT-IAO-668 | Message Broadcast | overdue payment alert(broken PA) notification | 3. Medium
157613 | CORE-IT-IAO-669 | Message Broadcast | agreement reinstatement alert notification | 3. Medium
157619 | CORE-IT-IAO-673 | Message Broadcast | LOFLL_Enrollment – Landlord enrolled an account in LOFLL program | 3. Medium
157620 | CORE-IT-IAO-674 | Message Broadcast | LOFLL_DeEnrollment – Landlord de-enrolled an account in LOFLL program | 3. Medium
157623 | CORE-IT-IAO-676 | Message Broadcast | LOFLL_TurnOn – An account is turned on under the landlord name through the LOFLL program | 3. Medium
157618 | CORE-IT-IAO-672 | Message Broadcast | LOFLL_TurnOff -- Tenant unit turned off. Notify landlord that unit will be transferred to landlord after 7 days | 3. Medium
37121 | CORE-CUS-IAI-013 | DCX | CE/O&R - DCX Get Account Basic for given MAID (Basic) | 2. Simple
94819 | CORE-FCC-IAI-632 | MDMS | Interface for database read response | 3. Medium
311443 | CORE-FCC-IAO-1049 | Gas Ops | Opt Methane Sensor Letter exception file | 3. Medium
334936 | CORE-CUS-ICO-1054 | PAC | Exception file email to PAC | 3. Medium
311440 | CORE-FCC-ICO-1048 | Gas Ops | Methane Sensor service order exception file | 3. Medium
170740 | CORE-FCC-IOO-792 | ORU WMS | PAL_STD_MO_UNIT | 4. Complex
170737 | CORE-FCC-IOO-791 | ORU WMS | TAR_SCH | 4. Complex
170726 | CORE-FCC-IOO-787 | ORU WMS | SPEC_NOTE | 4. Complex
170721 | CORE-FCC-IOO-784 | ORU WMS | PREMISE | 4. Complex
170728 | CORE-FCC-IOO-788 | ORU WMS | ADDRESSES | 4. Complex
170731 | CORE-FCC-IOO-789 | ORU WMS | METER_PT | 4. Complex
170707 | CORE-FCC-IOO-781 | ORU WMS | COLLECTION_INFO | 4. Complex
170705 | CORE-FCC-IOO-780 | ORU WMS | SAD | 4. Complex
170699 | CORE-FCC-IOO-777 | ORU WMS | PAL_COMPONENT_HDR | 4. Complex
170697 | CORE-FCC-IOO-776 | ORU WMS | SERVICE_PT | 4. Complex
170684 | CORE-FCC-IOO-775 | ORU WMS | BILL ACCT | 4. Complex
39362 | CORE-RBP-ICO-050 | SOMIS | Data sync of customer information from CC&B to SOMIS. | 3. Medium
168223 | CORE-FCC-ICI-836 | WMS EIE to CORE EIE | Work order update assignment - MIV_CI_922 | 3. Medium
178558 | CORE-FCC-ICO-867 | GASC (CORE-EIE to GASC-EIE) | Get SDP Id using Meter and borough GASC_IO_1376B.Get SDP Id using Meter and borough | 3. Medium
168211 | CORE-FCC-ICO-833 | ProField (CORE-EIE to AMI-EIE) | Work order schedule enriched at CCB and sent t to PFE - MIV_CI_919 | 3. Medium
211651 | CORE-IT-IOO-993 | Mailroom | Mailroom Printer File with customer address | 3. Medium
68994 | CORE-RBP-IOO-605 | NYPA | This is an extract of usage data of NY Power Authority (NYPA) ORU accounts from CC&B as a flat file. In the As-Is OR is a manual process. but during the discussion it was confirmed that OR account usage need to be considered as well and a separate file need to be shared. | 3. Medium
44210 | CORE-TPI-IOO-303 | RDX | O&R ? Generate 810 (invoicing) flat file with positional layout (not xml). Send this file to RDX. | 4. Complex
44208 | CORE-TPI-ICO-301 | RDX | CECONY ? Generate 810 (invoicing) flat file with XML based tags. Send this file to RDX. NEW810.TXT | 4. Complex
131097 | CORE-CUS-ICO-639 | NYPA - RNY | Create a Validation file for the records that could not be processed | 3. Medium
187549 | CORE-FCC-IOI-920 | Broadridge | CC&B Receives EDPA file from Broadridge | 3. Medium
178490 | CORE-FCC-IOO-858 | CRA | CC&B to create customer contact information details file in .txt format and put it into FTP to CRA Inc. survey vendor | 3. Medium
182526 | CORE-FCC-ICO-902 | Cortera | Share data extract file of CECONY Non-Closed Commercial Accounts Balances with Arrears Details with CORTERA | 3. Medium
207947 | CORE-RBP-IAO-979 | JPM Chase | JPM Chase GO File | 3. Medium
137600 | CORE-RBP-ICO-745 | ORACLE EBS | 1099 - IRS File | 4. Complex
187548 | CORE-RBP-IOI-919 | Broadridge | Broadridge - eFailure file | 3. Medium
39194 | CORE-IT-ICO-538 | Broadridge | Data - DESCRIP : File FTP'd to BroadridgeData DIRECTION _x002 : FROM_CSPlatform : MainframeVendor System : YESData - FileNam : J400.A216.EBILL320.BRDRIDGE(+1)Data TRANSPORT METHO : FTPData - FREQUEN : DailyData - VOLUME_ : 2500 - 2 CylindersCOMMENTS : | 3. Medium
158037 | CORE-CUS-IAO-774 | Broadridge | Retrieve Correspondence Link | 3. Medium
122633 | CORE-RBP-IAO-627 | Broadridge | View Bill Interface for the specific touchpoint call of Get_Bill_Image_by_DocumentID | 3. Medium
137586 | CORE-CUS-ICO-731 | Questline | Send data file for 3 Days Pending Turn On for English Customers to Questline | 3. Medium
182483 | CORE-RBP-ICI-895 | NY State | HEAP Grant Payments | 3. Medium
203725 | CORE-RBP-ICO-963 | OpenText Exstream | Bill extract - NY - Brooklyn - batch CMBECBRK | 3. Medium
203727 | CORE-RBP-ICO-964 | Exstream-Broadridge | Bill extract - NY - Bronx - batch CMBECBRX | 3. Medium
203728 | CORE-RBP-ICO-965 | Exstream-Broadridge | Bill extract - NY - Manhattan - batch CMBECMNH | 3. Medium
39098 | CORE-RBP-ICO-369 | Steam WSS | As part of this integration, customer, account, billing information will be transferred from CC&B to CCG Website. | 4. Complex
94816 | CORE-RBP-ICI-625 | MDMS | Interface for interval usage data upload for value stack accounts | 3. Medium
42561 | CORE-RBP-ICI-192 | MDMS | This process will be the meter read upload file which will be processed to CC&B for event based billing read response for SHR customers. | 3. Medium
42586 | CORE-RBP-ICO-217 | DEP | Steam/SteamApps requires extracts of data from CC&B in order to run its functions. These will be a series of flat file extracts or views populated daily through batch. This should be remediation as these functions currently work with the existing CC&B 2.6 Steam instance. | 3. Medium
39364 | CORE-RBP-ICO-052 | Maximo | Outbound data flow from CC&B to Maximo (JTS) for Job Information. | 3. Medium
168220 | CORE-FCC-ICO-835 | AMI EIE to CORE EIE | Work order request - MIV_CI_921 | 4. Complex
168215 | CORE-FCC-ICI-834 | AMI EIE to CORE EIE | Work order request - MIV_CI_921 | 4. Complex
37186 | CORE-FCC-ICI-498 | ProField | ProField Encore sends Post Install file to CC&B. | 3. Medium
178505 | CORE-FCC-ICI-872 | Gas Central | CC&B receives RIC Creation Response from Gas Central | 3. Medium
178513 | CORE-FCC-ICI-874 | Gas Central | CC&B receives Create Ticket response from Gas Central | 3. Medium
236917 | CORE-FCC-IOI-1028 | DCX | Report Outage | 3. Medium
211568 | CORE-CUS-ICO-989 | EEDES | INQUIRY WEEKLY extract | 3. Medium
185286 | CORE-TPI-ICO-904 | RAIS-CE | Generate Meter Information File | 3. Medium
178540 | CORE-FCC-ICO-862 | MAMS | network assets - item, SP, and Premise need to be created if the network access point are not tied to an existing meter - Response Queue - MAM_AO_963 | 3. Medium
160083 | CORE-CUS-ICO-826 | Questline | Send active residential customer information having preferred language Spanish | 3. Medium
160102 | CORE-CUS-ICO-828 | Questline | Send active commercial customer information having preferred language Spanish | 3. Medium
137591 | CORE-CUS-ICO-732 | Questline | Send Proactive Moving Campaign Data file to Questline for Brooklyn and Manhattan Customers | 3. Medium
178499 | CORE-CUS-ICO-870 | Questline | Send data file for 3 Days Pending Turn On for Spanish Customers to Questline | 3. Medium
178502 | CORE-CUS-ICO-871 | Questline | Send data file for 8 Days Pending Turn On for Spanish Customers to Questline | 3. Medium
203729 | CORE-RBP-ICO-966 | Exstream-Broadridge | Bill extract - NY - Queeens - batch CMBECQNS | 3. Medium
199965 | CORE-RBP-IAO-942 | ORACLE EBS | Sending Stop Cheque Information | 3. Medium
203730 | CORE-RBP-ICO-967 | Exstream-Broadridge | Bill extract - NY - Staten Island - batch CMBECSTI | 3. Medium
178510 | CORE-FCC-ICI-873 | Gas Central | CC&B receives RIC Cancellation Response from Gas Central | 3. Medium
198400 | CORE-FCC-ICO-935 | Gas Central | Create Work from Alarms and Events in Gas Central | 3. Medium
168195 | CORE-FCC-ICI-832 | WMS (AMI-EIE to CORE-EIE) | Work order schedule request to CCB from WMS - MIV_CI_919 | 3. Medium
168259 | CORE-FCC-ICO-843 | eGIS (CORE-EIE to eGIS-EIE) | GIS Mapping system - Provide SDP ID, Premise, Account, Meter information - EGIS_DER_INTI_309 | 3. Medium
178552 | CORE-FCC-ICI-865 | EGIS (EGIS-EIE to CORE-EIE) | GIS Mapping system - Provide SDP ID, Premise, Account, Meter, etc…. EGIS_DER_INTI_309 | 3. Medium
169009 | CORE-FCC-ICI-852 | Gas Central (GASC-EIE to CORE-EIE) | Get SDP Id using Meter and borough GASC_IO_1376B | 3. Medium
168232 | CORE-FCC-ICI-838 | MAMS | network assets - item, SP, and Premise need to be created if the network access point are not tied to an existing meter - MAM_AO_963 | 3. Medium
211608 | CORE-IT-IAO-992 | DCX | Overdue payment alert(broken PA) Push Notification | 3. Medium
276324 | CORE-CUS-ICI-1035 | DCX | GET bopaUnits by OktaUserID | 3. Medium
252841 | CORE-TPI-ICI-1031 | RAIS-CE | RAIS Marketer voucher charges posting : RAIS sends a marketer voucher file that has charges to be posted into CC&B | 3. Medium
252842 | CORE-TPI-ICO-1032 | RAIS-CE | RAIS Marketer voucher Reconciliation : CC&B sends the status of marketer vouchers posted/failed to RAIS. | 3. Medium
252843 | CORE-TPI-ICI-1033 | TCIS | TCIS Marketer voucher charges posting : TCIS sends a marketer voucher file that has charges to be posted into CC&B | 3. Medium
169010 | CORE-FCC-ICI-853 | Gas Central | Create SDP Id for new Gas Meter and Obtain meter asset data for field work GASC_IO_1376 | 3. Medium
211558 | CORE-CUS-ICO-987 | EEDES | EMETER WEEKLY extract | 3. Medium
211562 | CORE-CUS-ICO-988 | EEDES | GMETER WEEKLY extract | 3. Medium
185572 | CORE-CUS-IAI-913 | DCX | Get_Accounts_For_User | 3. Medium
178537 | CORE-FCC-IOI-861 | Gas Ops | Gas OPS provides the Methane Sensor location file to be processed at CCB - MIV_OI_952 | 3. Medium
168249 | CORE-FCC-ICI-841 | Gas Central | Post Methane Sensor Install, Exchange, and Removal Data - GASC_IO_3116 | 3. Medium
203731 | CORE-RBP-ICO-968 | Exstream-Broadridge | Bill extract - NY - Westchester - batch CMBECWCT | 3. Medium
170630 | CORE-RBP-ICO-697 | DCAS | DCAS - Supplemental Usage File Data | 4. Complex
203734 | CORE-RBP-ICO-969 | Exstream-Broadridge | Bill extract - NY - SEG codes - batch CMBECSEG | 3. Medium
203736 | CORE-RBP-IOO-970 | Exstream-Broadridge | Bill extract - ORU - Default - batch CMBEODFL | 3. Medium
203737 | CORE-RBP-IOO-971 | Exstream-Broadridge | Bill extract - ORU - SEG codes - batch CMBEOSEG | 3. Medium
203738 | CORE-RBP-IOO-972 | Exstream-Broadridge | Bill extract - RECO - Default - batch CMBERDFL | 3. Medium
203739 | CORE-RBP-IOO-973 | Exstream-Broadridge | Bill extract - RECO - SEG codes - batch CMBERSEG | 3. Medium
137625 | CORE-RBP-ICO-761 | Uplight | Generate and Sends extract of CC&B Billing Data for CECONY(NY) Complex Billing accounts to the DCX_ETL using integration layer | 3. Medium
170628 | CORE-CUS-ICO-733 | Questline | Send data file for 8 Days Pending Turn On for English Customers to Questline | 3. Medium
137628 | CORE-RBP-IAO-762 | Uplight | Generate and Sends extract of CC&B NYISO day ahead pricing data feed for Complex Billing Account to the DCX_ETL using integration layer | 3. Medium
178520 | CORE-RBP-ICO-879 | Uplight | Generate and Sends extract of CC&B Bill Determinant SDP Account Item Data for CECONY(NY) Complex Billing accounts to the DCX_ETL using integration layer | 4. Complex
178519 | CORE-RBP-ICO-878 | Uplight | Generate and Sends extract of CC&B User rate attribute Data for CECONY(NY) Complex Billing accounts to the DCX_ETL using integration layer | 4. Complex
137612 | CORE-RBP-IOO-760 | Uplight | Generate and Sends extract of CC&B Billing Data for ORU Complex Billing accounts to the DCX_ETL using integration layer | 3. Medium
178516 | CORE-RBP-IOO-875 | Uplight | Generate and Sends extract of CC&B User rate attribute Data for ORU Complex Billing accounts to the DCX_ETL using integration layer | 4. Complex
178517 | CORE-RBP-IOO-876 | Uplight | Generate and Sends extract of CC&B Bill Determinant SDP Account Item Data for ORU Complex Billing accounts to the DCX_ETL using integration layer | 4. Complex
214587 | CORE-IT-ICO-999 | Exstream-Broadridge | Send Postcard extract file for CECONY customers | 3. Medium
214588 | CORE-IT-IOO-1000 | Exstream-Broadridge | Send Postcard extract file for ORU customers | 3. Medium
174449 | CORE-RBP-ICO-857 | Exstream-Broadridge | Send Summary/EDF Bill extract file generated from CC&B to OpenText Exstream – CECONY | 3. Medium
137348 | CORE-FCC-IAO-682 | A/R Debt Solutions | Generate Bad Cheque File to AR Debt solution | 3. Medium
158024 | CORE-FCC-ICI-771 | Gas Central | Gas Central sends the Methane Sensor Emergency Ticket completion to CC&B | 3. Medium
169003 | CORE-FCC-ICI-851 | Gas Central (GASC-EIE to CORE-EIE) | Get Account and Meter info using SDP-ID GASC_IO_1376A | 3. Medium
178555 | CORE-FCC-ICO-866 | GASC (CORE-EIE to GASC-EIE) | Get Account and Meter info using SDP-ID GASC_IO_1376A.Get Account and Meter info using SDP-ID | 3. Medium
178543 | CORE-FCC-ICO-864 | Gas Central | Post Methane Sensor Install, Exchange, and Removal Data response file - GASC_IO_3116 | 3. Medium
178534 | CORE-FCC-ICO-860 | ProField | Daily Sync File to PFE - MIV_CI_933 | 3. Medium
168264 | CORE-FCC-ICO-844 | eGIS | Sends new meter set details to biztalk and biztalk send to GIS - EGIS_INTI_335 | 3. Medium
211601 | CORE-IT-IAO-990 | DCX | Overdue payment alert(arrears) Push Notifications | 3. Medium
211606 | CORE-IT-IAO-991 | DCX | Overdue payment alert(PA installment overdue) Push Notification | 3. Medium
224494 | CORE-TPI-ICO-637 | TCIS | CECONY - TCIS receiving BPP information from CC&B | 3. Medium
168283 | CORE-FCC-IAI-849 | Gas Ops | File to create customer contact for sending Opt Methane Sensor Letter | 3. Medium
158052 | CORE-FCC-IOO-811 | FORD | Special Project Send FA | 3. Medium
168192 | CORE-FCC-IAO-831 | MAMS | AP socket/connected DR response file from CCB to MAMS - MIV_AO_940 | 3. Medium
137357 | CORE-RBP-IOI-683 | DCX | Get hourly prices for New York Mandatory Real Time Pricing | 4. Complex
211677 | CORE-IT-IOI-998 | FORD | PING for system availability check | 2. Simple
95573 | CORE-RBP-ICO-619 | NYSERDA | NYSERDA Loans Transfer of Uncollected Payment File: Process to generate file with details on closed accounts with no payment and send to NYSERDA | 3. Medium
201253 | CORE-CUS-IAI-962 | DCX | Set Notification Preferences | 3. Medium
211551 | CORE-CUS-ICO-985 | EEDES | EBILLS WEEKLY extract | 3. Medium
211552 | CORE-CUS-ICO-986 | EEDES | GBILLS WEEKLY extract | 3. Medium
252844 | CORE-TPI-ICO-1034 | TCIS | TCIS Marketer voucher Reconciliation : CC&B sends the status of marketer vouchers posted/failed to TCIS | 3. Medium
201252 | CORE-CUS-IAI-961 | DCX | Get Notification Preferences | 3. Medium
168169 | CORE-FCC-ICO-822 | ProField | Daily Sync File to PFE - MIV_CI_933 | 3. Medium
200224 | CORE-TPI-IOI-954 | TCIS | GetAddressByCustNo | 3. Medium
200226 | CORE-TPI-IOI-956 | TCIS | GetHeatUsageData | 3. Medium
235382 | CORE-RBP-IAI-1027 | MDMS | Retrieve Badge number and Channel number | 3. Medium
95570 | CORE-RBP-ICO-616 | NYSERDA | NYSERDA Loans Successor File: Process to generate file with details on re-activated accounts reported earlier in the closing file and send to NYSERDA | 3. Medium
95569 | CORE-RBP-ICO-615 | NYSERDA | NYSERDA Loans Closing File: Process to generate file with details on accounts closed with remaining loan instalments and send to NYSERDA | 3. Medium
95568 | CORE-RBP-ICI-614 | NYSERDA | NYSERDA Loans Establishment File: Process to accept file containing the information of new customers enrolling in Loan installment program | 3. Medium
131099 | CORE-CUS-ICO-640 | NYPA - RNY | Create an Acknowledgement file for the processed records | 3. Medium
68995 | CORE-CUS-IOI-606 | NYPA - RNY | The current interface for RNY Enrolment only considers for CECONY. During review it was mentioned that ORU also have the same RNY enrolment process which they want to have the automation. As part of the workshop this was not defined as ORU follows manual process today. As this is confirmed to have the interface touchpoint for RNY ORU accounts enrolment a new RICE is to be defined. | 3. Medium
196879 | CORE-IT-IAO-937 | DCX | Bill Ready Push Notifications | 3. Medium
196881 | CORE-IT-IAO-939 | DCX | Payment Processed Push Notification | 3. Medium
39400 | CORE-FCC-IAO-095 | MDMS | SDPG Interface: When the MDM_CI_100 process completes, SDP-G will identify records pertaining to Large Power Customers which will need subsequent processing via this interface to ensure Virtual SDP configuration is correct. This will be accomplished via the Associated Demand Meter field, which will be brought into SDP-G via CAS_CO_100. The presence of an Associated Demand Meter will provide the needed intelligence to identify a large power customer. Customer, Account, Service Point, Route, Bill Cycle, Meter Configuration Sync SDPG Interface: FlexSync message from SDPG to MDMS | 4. Complex
131101 | CORE-CUS-IOO-641 | NYPA - RNY | Create a Validation file for the records that could not be processed -ORU | 3. Medium
206604 | CORE-TPI-ICI-977 | TCIS | ED/EC transaction as part of daily transaction | 3. Medium
180047 | CORE-FCC-ICO-886 | STAR | Daily Extract of Updated Electric Customer Data | 3. Medium
200218 | CORE-TPI-IOI-948 | TCIS | etTotalUsageHdrByDatePeriod | 3. Medium
187527 | CORE-TPI-ICO-915 | TCIS | Generate Meter Information File | 3. Medium
211549 | CORE-CUS-ICO-984 | EEDES | ACCT WEEKY extract | 3. Medium
211538 | CORE-CUS-ICO-983 | EEDES | ACCTS DAILY extract | 3. Medium
95571 | CORE-RBP-ICO-617 | NYSERDA | NYSERDA Loans Change File: Process to generate file with details on change in utility account number and send to NYSERDA | 3. Medium
95572 | CORE-RBP-ICO-618 | NYSERDA | NYSERDA Loans Remittance File: Process to generate file with details on accounts received payment towards loan instalments and send to NYSERDA | 3. Medium
131102 | CORE-CUS-IOO-642 | NYPA - RNY | Create an Acknowledgement file for the processed records | 3. Medium
94818 | CORE-FCC-IAO-631 | MDMS | Interface for database read request | 3. Medium
39176 | CORE-RBP-IOO-530 | Synergi | This is an extract of information of gas customers from CC&B as a flat file run manually on an adhoc basis every year/other year which is sent to the vendor where it's used to update the databases which allow the application to run. This is only for OR gas customers (all customer classes) | 3. Medium
39177 | CORE-RBP-IOO-531 | Synergi | This is an extract of weather zone of gas customers from CC&B as a flat file run manually on an adhoc basis every year/other year which is sent to the vendor where it's used to update the databases which allow the application to run. This is only for OR gas customers (all customer classes) | 3. Medium
39178 | CORE-RBP-IOO-532 | Synergi | This is an extract of weather zone extractor of gas customers from CC&B as a flat file run manually on an adhoc basis every year/other year which is sent to the vendor where it's used to update the databases which allow the application to run. This is only for OR gas customers (all customer classes) | 3. Medium
196880 | CORE-IT-IAO-938 | DCX | Payment Due Push Notification | 3. Medium
42570 | CORE-RBP-ICI-201 | CyclePET | This process will be the meter read upload (MRI) file which will be processed in CC&B Account Record Change Order also processed in MRI formatting. Please review Reference ID #390, Requirement #28596, when determining how ARCO's will be processed as they are MRI formatted. | 3. Medium
179983 | CORE-FCC-IAI-881 | DCX | Get Account for Outage | 4. Complex
206469 | CORE-FCC-ICO-975 | APS (area profile system) | Send Account billed consumption | 3. Medium
137594 | CORE-FCC-ICI-735 | DCX | Send customer notification on outage reporting | 3. Medium
311434 | CORE-CUS-ICO-1047 | PAC | Send PACMAN file | 3. Medium
276306 | CORE-RBP-ICI-1036 | DCX | 3rd Party Data Export API | 3. Medium
39254 | CORE-FCC-IOI-085 | ORU WMS | WMS sends completed service investigation Jobs details to CC&B | 3. Medium
39374 | CORE-CUS-ICI-104 | PAC | Account Updates and Notations 1. Account Inquiry for HEAP and Grant HEAP Benefit 2. Clear account 3. Process/Reject/Delete applications and add payment 4. Add/Process checks 5. Approve/Reject checks 6. HeartShare inquiry and process | 3. Medium
37132 | CORE-FCC-ICI-444 | FPET | FPET sends the order completion information to CC&B. | 4. Complex
68992 | CORE-FCC-IOO-589 | TRBL | Initially, the interface for meter orders and outage was considered to be the same. However, in a call we had with Wilfredo last week, we realized that the message, mode of sending the message and the batch jobs (in CIMS) to process these messages are entirely different and hence would need to be handled as separate RICE items. So there is a second RICE required for Gas Meter Ordres FA. RICE description: CC&B sends Gas Meter Orders field activity to TRBL Rice Detail: Interfaces data from CIMS Trouble Order dialogs to generate Gas and Electric Trouble Orders. Gas orders are sent to GMD, and upon completion stored in mainframe TRB. Electric orders are sent to OMS via tables TRB334/TRB335/TRB336. Also interfaces with VRU via CIMS. Daily Gas Meter Orders fed to TRB via CIMS table CI70TB55 (GMD_METER_ORDERS) | 3. Medium
37149 | CORE-FCC-ICO-461 | Gas Central | Search Outage ticket List | 3. Medium
39372 | CORE-CUS-ICI-102 | PAC | Retrieve last 4 months amount due, from - to date of the four month period, current disconnect notice and status for a given account number | 3. Medium
39191 | CORE-IT-IAO-535 | Message Broadcast | Data - DESCRIP : My Account Notification web job that queries DB2 for all accounts where payment is due within 10 daysData DIRECTION _x002 : FROM_CSPlatform : InternetVendor System : NoData - FileNam : Data TRANSPORT METHO : Data - FREQUEN : DailyData - VOLUME_ : COMMENTS : | 3. Medium
39190 | CORE-IT-IAO-534 | Message Broadcast | Data - DESCRIP : My Account Notificaiton web job that queries DB2 for all accounts where bill has been issuedData DIRECTION _x002 : FROM_CSPlatform : InternetVendor System : NoData - FileNam : Data TRANSPORT METHO : Data - FREQUEN : DailyData - VOLUME_ : COMMENTS : | 3. Medium
39375 | CORE-CUS-ICI-105 | PAC | Referrals to departments Real Time, Screen Scrape Processing | 3. Medium
37134 | CORE-FCC-ICO-446 | FPET | CC&B sends batch field activity creation request to FPET. | 4. Complex
137336 | CORE-TPI-ICI-727 | Extreme to CC&B | EDIMSG interface from Extreme to CC&B | 3. Medium
42623 | CORE-FCC-ICI-144 | CCS | CCS: Telephone Collection Survey Results are Received from CCS | 3. Medium
42571 | CORE-RBP-IOI-202 | Itron FCS | This process will be the meter read upload (MRI) file which will be processed to CC&B. | 3. Medium
39355 | CORE-RBP-ICI-043 | UtiliSave | CAS - Tax Remission Vouchers (P400R126) | 2. Simple
39354 | CORE-RBP-ICI-042 | Luthin | CAS - Tax Remission Vouchers (P400R124) | 2. Simple
235295 | CORE-TPI-ICI-1023 | TCIS | GetManHrPricingHistory | 3. Medium
137571 | CORE-RBP-IAI-728 | KIOSK | Interface to process account payment performed via the application for KIOSK. | 3. Medium
137443 | CORE-FCC-IOI-662 | Streetlight Portal | create customer contact on approval/reject of repair request | 3. Medium
137436 | CORE-FCC-IOO-661 | Streetlight Portal | create repair request | 3. Medium
94817 | CORE-FCC-IAO-626 | MDMS | Interface for syncing of reads from field work | 3. Medium
94813 | CORE-RBP-IAI-624 | MDMS | Interface for Replacement Read update | 3. Medium
94812 | CORE-RBP-IAI-623 | MDMS | Interface for Large Power Account Usage Response | 4. Complex
94811 | CORE-RBP-IAI-622 | MDMS | Interface for Regular Usage Response | 4. Complex
94810 | CORE-RBP-IAO-621 | MDMS | Interface for Large Power Account Usage Request | 4. Complex
94809 | CORE-RBP-IAO-620 | MDMS | Interface for Regular Usage Request | 4. Complex
42556 | CORE-RBP-IAO-187 | MDMS | This process will be the meter read download file which will be processed to MDMS (AMI) for event based billing for SHR customers The formatting of the requests send to MDMS is consistent with on/off cycle billing read request interfaces, the attributes within the record determining the type of request | 3. Medium
39451 | CORE-RBP-IAO-422 | ORACLE EBS | This interface is for AP Request Payment Extract for Oracle EBS. This include customer refund check file, POR payment, ESCO payment, and NYSERDA loan payments | 3. Medium
39367 | CORE-CUS-ICO-055 | NYPA | Extract daily file data such as Billing Information, Meter Removal and Exchange Information and various other records | 4. Complex
39359 | CORE-RBP-IAI-047 | NYISO | Moving from file based to API calls within 2020. Single API call for all companies and all data for NYISO. A file will be generated from the API call. This file is run for both CECONY and O&R. Day ahead pricing? | 3. Medium
39138 | CORE-RBP-IAI-379 | MAVRO | Mavro system sends the Return Posting File to CC&B. | 3. Medium
39134 | CORE-RBP-IAI-375 | MAVRO | Mavro sends the Payment Upload File to CC&B. | 3. Medium
38999 | CORE-TPI-ICI-257 | TCIS | Inbound Enrollment and other Change Market Transactions from TCIS-CE to CC&B | 4. Complex
38998 | CORE-TPI-ICI-256 | TCIS | Price and other changes for CECONY Gas - TCIS will send the commodity price change or other ESCO account/Marketer related information change to CC&B. | 4. Complex
38990 | CORE-TPI-IOO-247 | RAIS | Daily Account Refresh for ORU (Enrollment) - CC&B will send daily Account Refresh file to RAIS. The file will have the ESCO customer account information for the new Enrollments received from ESCO and pending Enrollments for the requests received in past and awaiting confirmation. | 3. Medium
38987 | CORE-TPI-IOI-244 | RAIS | RAIS ORU will send requests for triggering customer Enrollment notifications or letters to CC&B for new Enrollments. | 3. Medium
38986 | CORE-TPI-IOI-243 | RAIS | Daily account refresh process for ORU - RAIS will send account refresh request to CC&B for pending Enrollment | 3. Medium
38983 | CORE-TPI-ICI-240 | RAIS | Daily account refresh process for CECONY - RAIS will send account refresh request file to CC&B for pending Enrollments. | 3. Medium
39256 | CORE-FCC-IOI-087 | ORU WMS | WMS send the information to CC&B after the Lighting Jobs are completed in field. | 3. Medium
39154 | CORE-RBP-IOO-395 | JPM CHASE | CC&B sends the customer account information when the customer changed the account number (OLD vs NEW) | 3. Medium
39403 | CORE-FCC-IOI-098 | Revenue Protection | CC&B sends customer information to O&R revenue protection system. | 3. Medium
39156 | CORE-RBP-IOO-397 | JPM CHASE | CC&B sends the ACH files generated to JPM Chase BANK. | 3. Medium
39155 | CORE-RBP-ICO-396 | JPM CHASE | CC&B sends the ACH files generated to JPM Chase | 3. Medium
42569 | CORE-RBP-IOO-200 | Itron FCS | Scheduled Meter Read Export (Meter Read Download batch process) - Meter Read Request processing for non-AMI customers which remain in Itron FCS for O&R. | 3. Medium
39376 | CORE-CUS-ICO-106 | NYSS | flat file - UGC file - name / address info (File 918) | 3. Medium
39377 | CORE-CUS-ICO-107 | NYSS | flat file. customer info. DVC file (File 991) | 3. Medium
39378 | CORE-CUS-ICO-108 | NYSS | flat file.customer data.welfare file (File 919) | 3. Medium
58261 | CORE-RBP-ICI-578 | NYSGS | This is an input extract of information on change in Number of loan installments for customers already enrolled in Loan Installment program and received from NY State Govt (NYSGS) to CC&B. On processing this file in CC&B, number of installments would be updated on Loan SA in CC&B. | 3. Medium
39122 | CORE-RBP-ICO-347 | NYSERDA | This is an extract of updated information on outstanding loans for all accounts with NYSERDA loans from CC&B as a flat file. This file will be sent from CC&B to internal RDX server, as part of this integration. Then this file will be shared from internal server RDX server to NY State Govt (NYSGS) using existing integration. | 3. Medium
58262 | CORE-RBP-ICO-579 | NYSGS | This is an extract of information from CC&B which confirms utility processing of NYSERDA Loan Enrollment/Establishment File and reports any exceptions. This file will be sent from CC&B to internal RDX server, as part of this integration. Then this file will be shared from internal server RDX server to NY State Govt (NYSGS) using existing integration. | 3. Medium
42593 | CORE-CUS-IOI-118 | Life-Line | This file exclusively contains lifeline payments. | 3. Medium
39165 | CORE-RBP-ICI-406 | FPET | (Cash payment records from non-routine Customer Service Transactions are uploaded from Service Link system to FPET and are then accumulated in the FPET DB2 payment table. Further process uses the payment table to create interface file.) FPET Terminl sends the cash payment information to CC&B. | 3. Medium
137411 | CORE-TPI-IOI-690 | TCIS | Get POR/BPP Charges | 3. Medium
132792 | CORE-TPI-IAI-652 | DCX | Interface for sending ESCO data from CC&B to DCX | 3. Medium
39153 | CORE-RBP-ICO-394 | JPM CHASE | CC&B sends the customer account information when the customer changed the account number (OLD vs NEW) | 3. Medium
39189 | CORE-IT-IAI-533 | DCX | PING for system availability check | 2. Simple
45925 | CORE-TPI-ICO-317 | RAIS | RAIS picks up the data from CC&B table and updates the system, generates 814C transactions file to RDX ( Tied to previous interface) | 3. Medium
44212 | CORE-TPI-ICO-305 | RAIS | CECONY - RAIS receiving BPP information from CC&B | 3. Medium
42584 | CORE-RBP-IOO-215 | DEW | This is an extract of usage information of electric customers from CC&B as a flat file to the Distribution Engineering Workstation application. | 3. Medium
39020 | CORE-TPI-ICO-282 | RAIS | CECONY : CC&B will send the weather data for all NY stations to RAIS. This is daily feed from CC&B. | 3. Medium
39250 | CORE-FCC-ICI-081 | CATS | CATS reads the account, meter and credit information from CC&B. | 3. Medium
132773 | CORE-RBP-ICI-649 | DCX | NYUSO day-ahead pricing calculator | 4. Complex
137397 | CORE-TPI-ICI-692 | TCIS | Get Gas Profile Bill History | 3. Medium
132802 | CORE-TPI-ICI-654 | TCIS | Interface for sending billing history data from CC&B to TCIS NG website | 4. Complex
137416 | CORE-TPI-ICI-691 | TCIS | Get Gas Profile Acct Info | 3. Medium
39025 | CORE-TPI-ICI-287 | RCIS | The interface retrieves Account information from CC&B, which is displayed to user on Retail Choice Information System (RCIS). RCIS application is used in CECONY to view and perform ESCO related transactions. | 3. Medium
37137 | CORE-FCC-IOI-449 | FORD | CC&B receives field activity completion information from FORD. | 3. Medium
37147 | CORE-FCC-ICO-459 | Gas Central | CC&B sends RIC request to Gas Central. | 4. Complex
37148 | CORE-FCC-ICO-460 | Gas Central | CC&B sends RIC cancellation request to Gas Central | 4. Complex
132797 | CORE-TPI-ICI-653 | RAIS-CE | Interface for sending billing history data from CC&B to RAIS-CE | 4. Complex
39339 | CORE-CUS-IAO-029 | DCX | Validate identification details given by Customer | 2. Simple
37128 | CORE-FCC-ICI-440 | CRMS(PEGA) | CRMS(PEGA) retrieves customer information from CC&B for Customer Ops and Electric Ops | 2. Simple
235364 | CORE-RBP-ICO-1024 | MDMS | Sync Cecony Heating degree Days | 3. Medium
235374 | CORE-RBP-ICO-1025 | MDMS | Sync Cecony Cooling degree Days | 3. Medium
235376 | CORE-RBP-IOO-1026 | MDMS | Sync ORU Heating degree Days | 3. Medium
58302 | CORE-FCC-ICO-516 | WMS(CE) | CC&B sends RIC request to WMS. | 4. Complex
58303 | CORE-FCC-ICO-517 | WMS(CE) | CC&B sends RIC cancellation request to WMS. | 4. Complex
37171 | CORE-FCC-IOI-483 | GIMS | GIMS send the Gas Meter Order completion information to CC&B. | 3. Medium
37185 | CORE-FCC-ICI-497 | ProField | ProField Encore sends RIC comments and status to CC&B. | 3. Medium
37160 | CORE-FCC-ICI-472 | MDMS | MDMS sends the batch Remote Connect/Disconnect response to CC&B for CECONY. | 3. Medium
37164 | CORE-FCC-IOI-476 | MDMS | MDMS sends the batch RCD response to CC&B for ORU. | 3. Medium
37145 | CORE-FCC-ICO-457 | Gas Central | CC&B sends Gas Trouble Ticket creation request to Gas Central. | 3. Medium
134456 | CORE-FCC-ICI-664 | STAR | Send ticket ID from STAR to CC&B for the outage created via CC&B | 3. Medium
132824 | CORE-FCC-IOO-634 | NMS | Interface for sending Electric Outage Information to NMS(ORU) | 3. Medium
132827 | CORE-FCC-IOI-635 | NMS | Send acknowledgment from CORE Integration layer to CC&B for the outage created via CC&B | 3. Medium
37192 | CORE-FCC-IOO-504 | TRBL | CC&B sends Trouble Orders field activity to TRB. | 4. Complex
37190 | CORE-FCC-ICO-502 | STAR | CC&B sends electric emergency orders to STAR. | 3. Medium
37193 | CORE-FCC-IOI-505 | TRBL | TRBL sends the Methane Sensor Emergency Ticket completion to CC&B. The methane Sensor events are outages and not FA. | 3. Medium
39148 | CORE-RBP-IAI-389 | FISERV | FISERV sends the request to CC&B to get the account related information | 3. Medium
38921 | CORE-CUS-ICO-021 | IVR-CE | Respond back with account number | 3. Medium
38920 | CORE-CUS-ICI-020 | IVR-CE | Retrieve new call event and identify account based on customer details through CTI-IVR mechanism | 3. Medium
39351 | CORE-CUS-ICI-041 | DCX | LOFLL Get Landlord Responsible Units | 3. Medium
39347 | CORE-CUS-ICI-037 | DCX | Set's BOPA Ack field in source system for LOFLL tenant accounts | 3. Medium
39348 | CORE-CUS-ICI-038 | DCX | Set/Remove LOFLL Indicator | 3. Medium
39350 | CORE-CUS-ICI-040 | DCX | LOFLL Get Eligible Children | 3. Medium
134459 | CORE-FCC-ICO-665 | STAR | Send update information (Phone# and Remarks) for the existing tickets | 3. Medium
42595 | CORE-FCC-IOO-138 | NUCON | When the Deposit amount is paid successfully in CC&B, a confirmation message is sent from CC&B to NUCON. | 2. Simple
37191 | CORE-FCC-ICI-503 | OUA | CC&B retrieves outage information from OUA | 3. Medium
44207 | CORE-TPI-IAI-299 | DCX | This interface pulls the ESCO bill comparison data for last 12 months | 4. Complex
37168 | CORE-FCC-IOI-480 | Municipal Street Portal | Municipal Streetlights Portal sends streetlight outage request to CC&B. | 3. Medium
39031 | CORE-TPI-ICO-293 | TCIS | Appends divisional Cycle Usages to Server - This monthly usage file | 3. Medium
39000 | CORE-TPI-ICO-258 | TCIS | Daily Account & Meter refresh process between CC&B and TCIS for CECONY Gas Retail choice customers | 3. Medium
37181 | CORE-FCC-IOI-493 | ORU.com | ORU.com sends Streetlight repair requests to CC&B. | 3. Medium
39030 | CORE-TPI-ICO-292 | TCIS | Puts divisional Cancel Bills to TCIS server - This is cancel usage file | 3. Medium
37167 | CORE-FCC-IOI-479 | Municipal Street Portal | Municipal Streetlights Portal retrieves Customer Information from CC&B. | 3. Medium
37152 | CORE-FCC-IOI-464 | NRG GIS | CC&B retrieves X,Y coordinates for the Premises from Grid Coordinate System | 2. Simple
42568 | CORE-RBP-ICO-199 | CyclePET | In order to keep the systems in sync, CC&B will need to provide daily extracts of master data and Bill Cycle information into tables/views, or files in order to keep LPDS, MV90 Gas, and CyclePET in sync with CC&B. | 3. Medium
37180 | CORE-FCC-IOI-492 | O&R Storm CSR Storm mode | ORStormCSR retrieves Customer Information from CC&B. Customer account lookup based on the input address. | 3. Medium
39006 | CORE-TPI-ICI-264 | TCIS | HU Request from TCIS to retrieve the data up to 24 months | 4. Complex
39001 | CORE-TPI-ICI-259 | TCIS | Inbound Notification Transactions from TCIS-CE to CC&B | 3. Medium
37177 | CORE-FCC-IOI-489 | ORU.com | ORU.com sends General Area Outage request to CC&B. | 2. Simple
39009 | CORE-TPI-ICO-267 | TCIS | TCIS HU Response - The exceptions encountered while processing the historical usage request, will be sent in usage error file to TCIS | 4. Complex
58301 | CORE-FCC-ICO-515 | WINS | CC&B sends customer information to WINS. | 3. Medium
42573 | CORE-RBP-ICO-204 | CyclePET | Scheduled Meter Read Export (Meter Read Download batch process) - Meter Read Request processing for non-AMI customers which remain in Cycle PET for CECONY. | 3. Medium
37144 | CORE-FCC-ICO-456 | Gas Central | Send BOPA Referral – Gas Central | 3. Medium
45928 | CORE-TPI-ICO-320 | TODRS | WTC billing data will be coming from CC&B moving forward | 3. Medium
45936 | CORE-TPI-IOO-328 | TODRS | RNY Billing data from CC&B | 3. Medium
45927 | CORE-TPI-ICO-319 | TODRS | RNY billing data will be coming from CC&B moving forward. | 3. Medium
44219 | CORE-TPI-ICO-312 | TODRS | Interface for sending Billing data for Street light accounts to TODRS from CC&B | 3. Medium
39245 | CORE-FCC-ICO-076 | APS (area profile system) | CC&B sends the customer data to APS like Service Address, Muni, Account Number, Meter Number and other premise details | 3. Medium
39244 | CORE-FCC-ICI-075 | eGIS | CC&B updates the network and feeder information received from eGIS | 3. Medium
39108 | CORE-TPI-IOO-521 | TODRS | Account Maintenance data which Rate code information for given account/service point id | 3. Medium
70876 | CORE-TPI-ICO-600 | TCIS | CORE-TPI-ICO-600: Outbound Transaction Confirmation from CC&B to TCIS-CE | 3. Medium
44205 | CORE-TPI-ICI-297 | Agency Biller/Retail Choice Team | Process to remove accounts based on request from EDI biller that removes flag in CC&B. | 3. Medium
44204 | CORE-TPI-ICI-296 | Agency Biller/Retail Choice Team | Process to add accounts based on request from EDI biller that sets flag in CC&B. | 3. Medium
37139 | CORE-FCC-IOO-451 | FORD | CC&B sends real time field activity creation request to FORD. | 3. Medium
37138 | CORE-FCC-IOO-450 | FORD | CC&B sends field activity information to FORD in batch. | 3. Medium
39243 | CORE-FCC-IOI-074 | NUCON | NUCON request the account and other adhoc information from CC&B. | 3. Medium
39385 | CORE-CUS-IOI-115 | ORDSS | Share Customer information, Billing, Payment details | 3. Medium
39008 | CORE-TPI-IOO-266 | RAIS | ORU HU Response (Account & Meter Refresh File) - CC&B will provide the historical billed usage response to RAIS Account & Meter refresh file. | 4. Complex
39004 | CORE-TPI-ICO-262 | RAIS | CECONY HU Response - Along with billed usage, CC&B will also send the corresponding meter information for applicable accounts as received in the request from RAIS | 4. Complex
39003 | CORE-TPI-ICO-261 | RAIS | CECONY HU Response - CC&B will provide the historical billed usage response to RAIS | 4. Complex
39032 | CORE-TPI-IOO-294 | RAIS | File containing monthly electric usage for all customers in current billing cycle. | 3. Medium
39029 | CORE-TPI-ICO-291 | RAIS | Puts divisional Cancel Bills to server - This is cancel usage file | 3. Medium
39028 | CORE-TPI-ICO-290 | RAIS | Appends divisional Electric Meter Usages to server - This is monthly usage file | 3. Medium
39027 | CORE-TPI-ICO-289 | RAIS | Appends divisional Regular and Time-of-Day Usages to server - This is monthly billing determinant file. | 3. Medium
39026 | CORE-TPI-ICO-288 | RAIS | Appends divisional Regular and Time-of-Day Usages to server. This is for monthly usage file. | 3. Medium
37115 | CORE-CUS-IAO-008 | Verimove | Periodic Move Updates Request of all Mailing Addresses in CC&B - All mailing addresses in CC&B should be go through Move Update Process periodically - Request. (Once in a Month) | 2. Simple
38996 | CORE-TPI-IOI-254 | RAIS | RAIS ORU will send the daily transaction file that has Enrollments, drops, switches and change transactions. CC&B will receive this file daily. | 4. Complex
70879 | CORE-TPI-ICI-602 | RAIS-CE | CORE-TPI-ICI-602: Inbound Market Transactions from RAIS-CE to CC&B | 3. Medium
70878 | CORE-TPI-ICI-603 | RAIS-CE | CORE-TPI-ICI-603: Inbound Notifications from RAIS-CE to CC&B | 3. Medium
70877 | CORE-TPI-ICI-601 | RAIS-CE | CORE-TPI-ICI-601: Inbound Price Change Market Transactions from RAIS-CE to CC&B | 3. Medium
38997 | CORE-TPI-IOI-255 | RAIS | Price Change for ORU - RAIS will send commodity price change information received from ESCO, to CC&B as part of Change process | 4. Complex
37114 | CORE-CUS-IAI-007 | Spectrum | Process Response of Periodic Re-certification Request to update Mailing Addresses in CC&B - All mailing addresses in CC&B should be re-certified periodically - Response. (Once in 3 months) | 3. Medium
37113 | CORE-CUS-IAO-006 | Spectrum | Periodic Re-certification Request of all Mailing Addresses in CC&B - All mailing addresses in CC&B should be re-certified periodically - Request. (Once in 3 months) | 3. Medium
45930 | CORE-TPI-IOO-322 | TODRS | Daily Billing files sent from CIMS to TODRS - Billing data for Interval and non-interval metered accounts | 3. Medium
45931 | CORE-TPI-IOO-323 | TODRS | Account Maintenance data which details account changes - ie. activity code, SC change, etc. sent from CC&B to TODRS | 3. Medium
70880 | CORE-TPI-ICO-604 | RAIS-CE | CORE-TPI-ICO-604: Outbound Transaction Confirmation from CC&B to RAIS-CE | 3. Medium
38992 | CORE-TPI-IOO-249 | RAIS | CC&B will send the transaction confirmation to RAIS ORU for all the daily transactions received. (This is confirmation for CORE-TPI-IOI-251) | 3. Medium
39383 | CORE-CUS-ICI-113 | EEBenchMark | Restful API to retrieve customer information from CSS Adhoc | 2. Simple
45932 | CORE-TPI-IOI-324 | TODRS | Every year, Settlement system provides ICAP tag values to CC&B for all active accounts. RAIS will pickup the data | 3. Medium
45926 | CORE-TPI-ICI-318 | TODRS | Daily Obligation tag changes from TODRS to billing system | 3. Medium
45924 | CORE-TPI-ICI-316 | TODRS | Every year, Settlement system provides ICAP tag values to CC&B for all active accounts | 3. Medium
42602 | CORE-FCC-IOO-227 | NRG GIS | Retrieve Customer mailing addresses for use on NRG Gas Marketing Report Retrieve active and inactive customer account data for use in NRG and O&R Oracle NMS, and their associated reporting applications | 2. Simple
42600 | CORE-FCC-IOO-225 | NRG GIS | Retrieve Customer mailing addresses for use on NRG Gas Marketing Report Retrieve active and inactive customer account data for use in NRG and O&R Oracle NMS, and their associated reporting applications | 2. Simple
39360 | CORE-RBP-IAI-048 | PJM | Single API call for all companies and all data for PJM. A file is generated from the API call. This file is run for both CECONY and O&R. Day behind pricing.? | 3. Medium
39252 | CORE-FCC-IOO-083 | NRG GIS | Retrieve active and inactive customer account data from CC&B for use in NRG. | 2. Simple
39251 | CORE-FCC-IOO-082 | NRG GIS | Retrieves Customer Mailing Addresses from CC&B for use on NRG Gas Marketing Report. | 3. Medium
37116 | CORE-CUS-IAI-009 | Verimove | Process Response of Periodic Move Updates Request to update Mailing Addresses in CC&B - All mailing addresses in CC&B should be go through Move Update Process periodically - Response. (Once in a Month) | 2. Simple
39369 | CORE-CUS-ICO-057 | DCAS | Extract Gas Customer data for DCAS (Department of Citywide Administrative Services). This file has multiple records almost similar to Daily Data file. | 4. Complex
37125 | CORE-CUS-IAI-017 | DCX | CE/O&R - DCX Update Account ORU [DCX-ACCT-06] - Possible fields to update account in source system | 3. Medium
39095 | CORE-RBP-ICO-348 | NYPA | This is an extract of usage data of NY Power Authority (NYPA) accounts from CC&B as a flat file. This file will be sent from CC&B to internal RDX server, as part of this integration. Then this file will be shared from internal server RDX server to NY Power Authority (NYPA) using existing integration. | 3. Medium
39236 | CORE-FCC-ICI-067 | CPMS | CPMS sends the account update information to CC&B. (Transaction like CLIC, SBLI, ECOR, GCOR, MLAD and SICD). The update confirmation is sent back to CPMS. | 3. Medium
37165 | CORE-FCC-IAI-477 | MDMS | MDMS sends Methane Sensor, Hot Socket and Over Capacity Alarm creation request to CC&B. MDM_OO_360 MDM_CO_385 | 3. Medium
42513 | CORE-FCC-IOO-152 | A/R Debt Solutions | Final Billed Collection File Sent to A/R Debt Solution | 3. Medium
42515 | CORE-FCC-IOI-154 | A/R Debt Solutions | A/R Debt Solution Response File | 3. Medium
42512 | CORE-FCC-ICI-151 | A/R Debt Solutions | A/R Debt Solution Response File | 3. Medium
42510 | CORE-FCC-ICO-149 | A/R Debt Solutions | Final Billed Collection File Sent to A/R Debt Solution | 3. Medium
42535 | CORE-FCC-IOI-174 | IVR ORU | ORU IVR Sends Payment Agreement Terms for New Customer Enrollment to CC&B | 3. Medium
42536 | CORE-FCC-IOI-175 | IVR ORU | ORU IVR Sends Payment Agreement to CC&B | 3. Medium
37159 | CORE-FCC-ICO-471 | MDMS | CC&B sends batch Connect/Disconnect request to MDMS for CECONY. | 3. Medium
42527 | CORE-FCC-IAI-166 | DCX | DCX Get Payment Agreement base Terms | 3. Medium
42525 | CORE-FCC-IAI-164 | DCX | Submit Payment Agreement Enrollment | 3. Medium
44220 | CORE-TPI-ICO-313 | TODRS | Daily Billing files sent from CC&B to TODRS - Billing data for Interval and non-interval metered accounts | 3. Medium
44221 | CORE-TPI-ICO-314 | TODRS | Account Maintenance data which details account changes - ie. activity code, SC change, etc. sent from CC&B to TODRS | 3. Medium
39144 | CORE-RBP-IAI-385 | MAVRO | Mavro system sends the Bad Check Extracts to CC&B | 3. Medium
39140 | CORE-RBP-IAI-381 | MAVRO | Mavro system sends the DPP Extract (i.e.enrollment) to CC&B. | 3. Medium
39234 | CORE-FCC-ICI-065 | CPMS | CPMS request account information like CATS code from CC&B. | 3. Medium
39231 | CORE-FCC-ICO-062 | CPMS | Will the solution, as implemented, provide that, for temporary service sites, the customer is required to pay a fee or deposit before delivery of meter or equipment (for e.g. energy services account)? Will the solution, as implemented, provide a notification to the target system after all the meters are installed at the newly created Premises associated to a project/case? | 2. Simple
42516 | CORE-FCC-ICO-155 | Bottom Line Impact | CECONY Final With Balance Customer Information Sent to Bottom Line Impact | 3. Medium
42517 | CORE-FCC-ICO-156 | Bottom Line Impact | CECONY Active Customer Information sent to Bottom Line Impact | 3. Medium
39133 | CORE-RBP-IAO-374 | MAVRO | Billing Data file is being sent from CC&B to ConEd boroughs (Queens, Bronx, Manhattan, Westchester, Brooklyn, Staten Island Billing). | 3. Medium
42519 | CORE-FCC-IOO-158 | Bottom Line Impact | ORU Final with Balance Customer Information Sent to Bottom Line Impact | 3. Medium
42537 | CORE-FCC-ICI-176 | IVR | CECONY IVR sends Payment Agreement to CC&B | 3. Medium
38924 | CORE-CUS-ICI-024 | IVR | QCTL (Update Cell Phone) QFAX (Update fax number) QFOR (Foreign Language Flag) QTEL (Update Telephone Number) | 2. Simple
42541 | CORE-FCC-ICI-180 | Broadridge | CC&B Receives EDPA file from Broadridge | 3. Medium
39391 | CORE-CUS-IOO-121 | AEG | Usage file to AEG | 3. Medium
42620 | CORE-FCC-IAO-236 | Detectant | CC&B to extract remarks data information from all the boroughs and send to Detctant Server. | 3. Medium
42619 | CORE-FCC-IAO-235 | Detectant | CC&B to extract mailing address data information from all the boroughs and send to Detctant Server. | 2. Simple
42618 | CORE-FCC-IAO-234 | Detectant | CC&B to extract demand item data information from all the boroughs and send to Detctant Server. | 3. Medium
42617 | CORE-FCC-IAO-233 | Detectant | CC&B to extract gas item data information from all the boroughs and send to Detctant Server. | 3. Medium
42616 | CORE-FCC-IAO-232 | Detectant | CC&B to extract electric item data information from all the boroughs and send to Detctant Server. | 3. Medium
42615 | CORE-FCC-IAO-231 | Detectant | CC&B to extract gas billing data information from all the boroughs and send to Detctant Server. | 3. Medium
42614 | CORE-FCC-IAO-230 | Detectant | CC&B to extract electric billing data information from all the boroughs and send to Detctant Server. | 3. Medium
42613 | CORE-FCC-IAO-229 | Detectant | CC&B to extract gas meter data information from all the boroughs and send to Detctant Server. | 3. Medium
42612 | CORE-FCC-IAO-228 | Detectant | CC&B to extract electric meter data information from all the boroughs and send to Detctant Server. | 3. Medium
39405 | CORE-FCC-IAO-100 | Detectant | CC&B to extract detectant data information from all the boroughs and send to Detctant Server. | 3. Medium
39341 | CORE-CUS-IAI-031 | DCX | This service should also perform below activities. Validate Start dates for an account Retrieve Customer Maintain Existing Customer Details Create New Customer Details Request Connect Info Check Pending Transactions This also includes Start Small Commercial Service. | 3. Medium
39094 | CORE-RBP-IAO-416 | Broadridge | Interface for displaying the bill pdf from CC&B. This shall use the DCX API for bill PDF display https://dcx-api-web-prod.azurewebsites.net/swagger/ui/index#!/CRM/Get_Bill_Image | 2. Simple
39382 | CORE-CUS-ICI-112 | DMTS | Restful API to retrieve customer information upon request | 2. Simple
37188 | CORE-FCC-IOO-500 | ProField | CC&B sends Methane Sensor Installation Location File to ProField Meter for ORU. MIV_OI_952 | 3. Medium
39361 | CORE-RBP-IOO-049 | OMI | This interface extracts customer count information for different rate codes and service classes in all tax districts and loads into OMI. | 2. Simple
37163 | CORE-FCC-IOO-475 | MDMS | CC&B sends batch RCD requests to MDMS for ORU. | 3. Medium
37161 | CORE-FCC-ICO-473 | MDMS | CC&B sends near real time Connect/Disconnect request to MDMS for CECONY. | 3. Medium
37162 | CORE-FCC-ICI-474 | MDMS | MDMS sends the near real time Connect/Disconnect response to CC&B for CECONY. | 3. Medium
132768 | CORE-RBP-ICI-648 | DCX | Submetering calculator | 4. Complex
132784 | CORE-RBP-ICO-651 | DCX | MSC Lookup File | 4. Complex
42577 | CORE-RBP-IOI-208 | DCX | Follows the same mechanism as the other touchpoints with DCX. Get /v1/accounts/{maid}/RtpReportInfo Swagger URL: https://dcx-api-web-prod.azurewebsites.net/swagger/ui/index#/ | 3. Medium
39112 | CORE-RBP-ICI-523 | DCX | Rate Pilot IPP web job performs a Get Batch Bill Web service call after getting the accounts for High Demand | 3. Medium
42582 | CORE-RBP-ICI-213 | DCX | Follows the same mechanism as the other touchpoints with DCX. | 3. Medium
39357 | CORE-RBP-IAI-045 | DCX | Follows the same mechanism as the other touchpoints with DCX. /v1/accounts/{maid}/marketrates /v1/accounts/marketrates Swagger URL: https://dcx-api-web-prod.azurewebsites.net/swagger/ui/index#/ | 3. Medium
68997 | CORE-CUS-IOI-612 | DCX | DCX Streetlight had only interface for getting outage info, but it also has another interface for getting credit info which needs to add the second RICE. RICE Description: Street Light Accounts Credit Information | 3. Medium
39366 | CORE-CUS-IOI-054 | DCX | Street Light Accounts Outage Information | 4. Complex
137404 | CORE-TPI-IOI-687 | TCIS | Post PMA-CashOut charges | 3. Medium
137407 | CORE-TPI-IOI-688 | TCIS | Post WBS charges | 3. Medium
137410 | CORE-TPI-IOI-689 | TCIS | Post Capacity Imbalance charges | 3. Medium
42626 | CORE-FCC-IOI-147 | Alorica | CC&B Receives Regulatory Call Response Information from Alorica | 3. Medium
42624 | CORE-FCC-IOO-145 | Alorica | CC&B Sends Regulatory Agent Call Information to Alorica | 3. Medium
39169 | CORE-RBP-IOI-370 | IVR ORU | IVR sends the request to CC&B for Auto Pay Enrollment. | 3. Medium
37169 | CORE-FCC-IOI-481 | IVR ORU | IVR sends outage request to CC&B. | 3. Medium
42534 | CORE-FCC-IOI-173 | IVR ORU | ORU IVR sends Payment Extension to CC&B | 3. Medium
39160 | CORE-RBP-ICI-401 | PAC | PAC(Public Assistance Central) sends the payment upload to CC&B. | 3. Medium
172929 | CORE-TPI-IOI-856 | TCIS | Post IT marketer cash out charges | 3. Medium
42580 | CORE-RBP-IOI-211 | DCX | Follows the same mechanism as the other touchpoints with DCX. Get /v2/ratepilot/{MaskedAccountNumber}/billingperiods Swagger URL: https://dcx-api-web-prod.azurewebsites.net/swagger/ui/index#/ | 3. Medium
42579 | CORE-RBP-IAI-210 | DCX | Follows the same mechanism as the other touchpoints with DCX. Get /v2/ratepilot/{MaskedAccountNumber}/bills Swagger URL: https://dcx-api-web-prod.azurewebsites.net/swagger/ui/index#/ | 3. Medium
42520 | CORE-FCC-IOO-159 | Bottom Line Impact | ORU Active Customer Information Sent to Bottom Line Impact | 3. Medium
132832 | CORE-FCC-ICO-643 | STAR | Interface for sending customer information from CC&B to STAR(CE) | 3. Medium
132814 | CORE-IT-IAO-656 | EDAP | EDAP - Credit Ext | 3. Medium
132809 | CORE-IT-IAO-655 | EDAP | EDAP - Adjustment Ext | 3. Medium
39220 | CORE-IT-IAO-564 | EDAP | Payment Extract | 3. Medium
39219 | CORE-IT-IAO-563 | EDAP | Grid Asset Extract | 3. Medium
39217 | CORE-IT-IAO-561 | EDAP | Payment-Agreement Extract | 3. Medium
39214 | CORE-IT-IAO-558 | EDAP | Bill Summary Extract | 3. Medium
39213 | CORE-IT-IAO-557 | EDAP | Service Agreement Service Point Extract | 3. Medium
39212 | CORE-IT-IAO-556 | EDAP | Service Point Extract | 3. Medium
39211 | CORE-IT-IAO-555 | EDAP | Service Agreement Extract | 3. Medium
39210 | CORE-IT-IAO-554 | EDAP | Customer Organization Extract | 3. Medium
39209 | CORE-IT-IAO-553 | EDAP | Facility Extract | 3. Medium
39208 | CORE-IT-IAO-552 | EDAP | Account Extract | 3. Medium
39017 | CORE-TPI-IOO-279 | RAIS | RAIS ORU will get data feed from CC&B to generate the 814-Enrollment response to ESCO, for concurrent service requests raised by ESCO customers. This interface will replace the existing data feed from CDS which will be subsumed into CC&B. Note: ESCO portability is approved for ORU also. | 3. Medium
42627 | CORE-FCC-IOI-148 | Alorica | CC&B Receives Automatic Dialer Call Response Information from Alorica | 3. Medium
42625 | CORE-FCC-IOO-146 | Alorica | CC&B Sends Automatic Dialer Call information to Alorica | 3. Medium
132806 | CORE-RBP-IOO-657 | EIMS | Sending acknowledgement file for streetlight Inventory Sync data | 3. Medium
39113 | CORE-RBP-IOO-361 | EIMS | A view of data from the EIMS Streetlight Repository will be available for a CC&B batch process to pull data and process for billing of municipality streetlight accounts. | 3. Medium
39340 | CORE-CUS-IAO-030 | Message Broadcast | Send Start Service confirmation mail to Customer | 2. Simple
39389 | CORE-CUS-IOO-119 | OPOWER / DCX | Usage file of Residential Customers | 2. Simple
39390 | CORE-CUS-IOO-120 | OPOWER / DCX | Usage file of Non-Residential Customers | 2. Simple
70886 | CORE-TPI-ICO-613 | TCIS | As part of ESCO portability FSD, there is two FSD (one for RAIS/TCIS CE and other for RAIS O&R). But now from edge system stand it expects three files (RAIS CE, TCIS CE, RAIS O&R) instead of earlier 2. There is now additional interface for TCIS CE as separate touchpoint. Need to define RICE for TCIS CE as it is separate. | 3. Medium
39016 | CORE-TPI-ICO-278 | RAIS | As part of concurrent service request, RAIS/TCIS is getting data from CDS to generate the 814-enrollment response. As CDS will be subsumed, CC&B will provide the feed to RAIS/TCIS. What information does RASI/TCIS needs from billing system ? NOTE ? ESCO portability is approved for OR also. | 3. Medium
42599 | CORE-FCC-IOO-224 | NRG GIS | Retrieve Customer mailing addresses for use on NRG Gas Marketing Report Retrieve active and inactive customer account data for use in NRG and O&R Oracle NMS, and their associated reporting applications | 2. Simple
45934 | CORE-TPI-IOI-326 | TODRS | Daily Obligation tag changes from TODRS to billing system | 3. Medium
42610 | CORE-FCC-ICO-131 | MAMS | Send Annual Consumption FileTracking any development or docuemntation that is needed for the existing creation of Annual Consumption file that will be provided to MAMS at the beginning of the calendar year | 3. Medium
38925 | CORE-CUS-ICI-025 | IVR | QINQ (Create Inquiry Transaction) | 2. Simple
38926 | CORE-CUS-ICI-026 | IVR | QNTE (Add customer note) | 2. Simple
42538 | CORE-FCC-ICI-177 | IVR | CECONY IVR sends Reconnect Turn-on Request to CC&B | 3. Medium
37127 | CORE-FCC-ICI-439 | IVR | IVR sends trouble ticket creation request to CC&B. | 3. Medium
39167 | CORE-RBP-ICI-408 | IVR | IVR sends the request to post the payment in CC&B | 3. Medium
39170 | CORE-RBP-ICI-410 | IVR | IVR sends the request to CC&B for last bank account information. | 3. Medium
39168 | CORE-RBP-ICI-409 | IVR | IVR sends the request to CC&B for Auto Pay Enrollment. | 3. Medium
39158 | CORE-RBP-ICI-399 | JPM CHASE | JPM Chase sends the ACH Returns after clearance w.r.t. Rejected Payments to CC&B. | 2. Simple
39159 | CORE-RBP-IOI-400 | JPM CHASE | JPM Chase sends the ACH Returns after clearance w.r.t. Rejected Payments to CC&B. | 2. Simple
38918 | CORE-CUS-IAO-018 | Broadridge | Ability to view/identify correspondence in system and history of correspondence | 2. Simple
131552 | CORE-FCC-IAO-638 | MAMS | Asset sync response interface to MAMS | 3. Medium
38922 | CORE-CUS-ICI-022 | IVR | Provide Customer/Account information during heavy peak times (like Storms, Trouble/Outages, Gas Emergency) to TFCC | 2. Simple
45929 | CORE-TPI-ICO-321 | TODRS | Interface for send Billing data for Traction accounts to TODRS. | 3. Medium
39005 | CORE-TPI-ICO-263 | RAIS | CECONY HU Response - The exceptions encountered while processing the historical usage request, will be sent into usage error file to RAIS. | 4. Complex
39344 | CORE-CUS-ICI-034 | DCX | This service should also perform below activities. Cross Reference for Life Support Equipment, Backoffice process to certify whether the customer has Life Saving Equipment. | 3. Medium
42528 | CORE-FCC-IAI-167 | DCX | DCX Validates Payment Agreement Eligibility | 3. Medium
42526 | CORE-FCC-IAI-165 | DCX | DCX Get Payment Agreement Details | 3. Medium
39343 | CORE-CUS-ICI-033 | DCX | This service should also perform below activities. Check Pending Transactions | 3. Medium
39346 | CORE-CUS-IAI-036 | DCX | Process Turn-Off Request | 3. Medium
39013 | CORE-TPI-ICO-275 | RAIS | ESCO data refresh for CECONY Electric - CC&B will run a daily sync up process to update ESCO data to RAIS. This interface will replace CDS-RAIS data refresh. | 4. Complex
42611 | CORE-FCC-IAI-132 | MAMS | Will the solution, as implemented, provide a meter record that will contain meter specific attributes and information including -- meter manufacturer, meter model, manufacturer serial number, last test date, test results 1 (heavy load), 2 (light load), 3 (final average), new meter program date, service size (meter prefix - HT/LT), meter multiplier, number of dials, meter constant, number of elements, single or three phase, voltage, register ratio, class (amperage capacity), demand full scale, high pressure factor, meter casing type. Will the solution, as implemented, provide a mechanism so each equipment record has the capability of online review and update of all attributes and engineering information including -- user definable attributes? Will the solution, as implemented, support meter interface unit information including -- MIU type, sizes? Will the solution, as implemented, provide functionality such that the system does not allow duplicate equipment ID numbers? | 3. Medium
39342 | CORE-CUS-IAI-032 | DCX | This service should also perform below activities. Cross Reference for Life Support Equipment, Backoffice process to certify whether the customer has Life Saving Equipment. | 3. Medium
39345 | CORE-CUS-IAI-035 | DCX | This service should also perform below activities. Check Pending Transactions | 3. Medium
39010 | CORE-TPI-IOO-268 | RAIS | ORU HU Response - The exceptions encountered while processing the historical usage request, will be sent in usage error file to RAIS Current process puts the RA transaction file to RAIS server | 3. Medium
39007 | CORE-TPI-IOI-265 | RAIS | ORU HU Requests - RAIS will send the historical usage requests to CC&B, which is received from ESCO | 4. Complex
42621 | CORE-FCC-ICO-142 | CCS | CCS- Telephone Customer Collection Survey for Residential Customers | 3. Medium
42622 | CORE-FCC-ICO-143 | CCS | CCS- Telephone Customer Collection Survey for Commercial Customers | 3. Medium
42585 | CORE-RBP-IOO-216 | Synergi | This is an extract of usage information of gas customers from CC&B as a flat file run manually on an adhoc basis every year/other year which is sent to the vendor where it's used to update the databases which allow the application to run. This is only for OR gas customers (all customer classes) and only includes gas usage. 18 months data, monthly usage. | 3. Medium
39247 | CORE-FCC-IOI-078 | Power Clerk | Distributed Generation enters information into an application. CC&B validates the account information using a web service and send back the required account information back to Power Clerk. | 3. Medium
39248 | CORE-FCC-IOI-079 | Power Clerk | The applications for New Business to enter are created by the customer and mailed or by using Project Center. An meter order is created and the new customer account is created if one does not exist. The meter is installed or changed depending on the type of application that was submitted to New Business | 4. Complex
39240 | CORE-FCC-IOI-071 | NUCON | The applications for New Business to enter are created by the customer and mailed or by using Project Center. An meter order is created and the new customer account is created if one does not exist. The meter is installed or changed depending on the type of application that was submitted to New Business | 3. Medium
39239 | CORE-FCC-IOI-070 | NUCON | Account Setup info Will the solution, as implemented, have the ability to allow entry of new service address information on a partial basis and provide functionality such that the system understands the address is pending activation following successful completion of construction activities (when a subdivision is created)? Will the solution, as implemented, have the ability to have a block or intersection as address type? Will the solution, as implemented, have the ability to flag a service address for life support (this is for the WI Act 40)? | 3. Medium
39238 | CORE-FCC-IOI-069 | NUCON | Account Setup info Will the solution, as implemented, have the ability to allow entry of new service address information on a partial basis and provide functionality such that the system understands the address is pending activation following successful completion of construction activities (when a subdivision is created)? Will the solution, as implemented, have the ability to have a block or intersection as address type? Will the solution, as implemented, have the ability to flag a service address for life support (this is for the WI Act 40)? | 3. Medium
39370 | CORE-CUS-ICO-058 | NYPA | Extract Money Tape Details (Meter Reading, Demand, Base Charge and Voucher Information) of NYPA | 4. Complex
44211 | CORE-TPI-IOO-304 | ESCOS | O&R ? Generate 820 (payment advice) flat file with XML based tags. Send this file to RDX. Two files are generated by company to RDX. | 4. Complex
42603 | CORE-FCC-IAI-124 | MAMS | MAMS sends the daily billing meter attribute (RCD Indicator, Module ID,Prefix,Billing K and Number of dials) change information to CC&B. | 3. Medium
39229 | CORE-FCC-ICI-060 | CPMS | CPMS sends the information to CC&B for search/creation of new person/account/premise/service point/case. CC&B sends back the person/account/premise/service point/case created confirmation information to CPMS. | 3. Medium
42607 | CORE-FCC-IAO-128 | MAMS | Updates from Meter Orders1. Produce daily extract for electric and gas meter sets/removes/exchanges/module retrofits/gas index exchanges. SFTP via RDX the extract to BizTalk2. Update to send Electric Meter SDP Voltage, Gas Meter Drive Rate, Meter Dials value, and Geo Location Quality value Updates from Meter Orders (Electric)Produce daily extract for electric meter sets/removes/exchanges. SFTP via RDX the extract to BizTalk Updates from Meter Orders (Gas)Produce daily extract for gas meter sets/removes/exchanges/module retrofits/gas index exchanges. SFTP via RDX the extract to BizTalk | 3. Medium
44206 | CORE-TPI-ICO-298 | RDX/Agency Billers | File from Output Billing to EDI CSS sends a flat file (Fixed length) that has data of customer bill to RDX. This interface is part of Agency Billing | 4. Complex
44209 | CORE-TPI-ICO-302 | ESCOS | CECONY ? Generate 820 (payment advice) flat file with XML based tags. Send this file to RDX. CBEDI820.TXT | 4. Complex
45868 | CORE-RBP-IAI-331 | DCX | REQUEST - The ebids application makes a service call to get Customer Tariff information RESPONSE- CC&B will provide the customer tariff information | 3. Medium
45870 | CORE-RBP-IAI-333 | DCX | REQUEST - The ebids application makes a service call to get Customer Tariff information RESPONSE- CC&B will provide the customer tariff information | 3. Medium
39101 | CORE-RBP-IAI-350 | DCX | Follows the same mechanism as the other touchpoints with DCX. Post /v1/accounts/{maid}/getmasterbillinginfo Swagger URL: https://dcx-api-web-prod.azurewebsites.net/swagger/ui/index#/ | 3. Medium
39102 | CORE-RBP-IAI-351 | DCX | Follows the same mechanism as the other touchpoints with DCX. Post /v1/accounts/{maid}/getsubordinatebillingsummaryinfo Swagger URL: https://dcx-api-web-prod.azurewebsites.net/swagger/ui/index#/ | 3. Medium
39174 | CORE-RBP-IAI-414 | DCX | Interface to allow online bill payment postings from Public website for ConEd and ORU customers. This also allows to make Guest Payment. DCX sends the request to post the payment to CC&B for processing. | 3. Medium
39262 | CORE-FCC-IOI-093 | Project Center | Project Center requests for account, billing and rate information from CC&B. | 3. Medium
42598 | CORE-FCC-ICI-141 | CPMS | CPMS retrieves the account information from CC&B | 3. Medium
39368 | CORE-CUS-ICO-056 | MTA | Extract Meter Removal and Meter Exchange data of MTA | 4. Complex
132820 | CORE-RBP-IAI-658 | JPM Chase | Homebanking Payment File Upload | 3. Medium
39371 | CORE-CUS-ICI-059 | NYPA - RNY | Validate and Process NYPA Re-charge New York (RNY) Enrollment file sent to Con Edison and create SA Relationship and Sub-SA's per NYPA configuration Generate Acknowledgement/Confirmation file back to NYPA | 4. Complex
39002 | CORE-TPI-ICI-260 | RAIS | CECONY HU Requests - RAIS will send the Historical usage request to CC&B. | 4. Complex
42606 | CORE-FCC-IAI-127 | MAMS | MAMS sends meter test data information to CC&B | 3. Medium
39175 | CORE-RBP-IAI-415 | DCX | DCX sends the request to get the payment information from CC&B. | 2. Simple
39384 | CORE-CUS-ICO-114 | EEBenchMark | CSS Account and Meter Information | 3. Medium
42548 | CORE-CUS-ICI-135 | EEBenchMark | EEBenchmarking has weekly job that syncs with Steam CC&B2.6 Job to pull aggregated data of 1800 steam accounts. Refer Interface Inventory Data Column for customer field values requested from Steam CC&B | 3. Medium
42514 | CORE-FCC-IOO-153 | A/R Debt Solutions | Payment Confirmation File to A/R Debt Solutions | 3. Medium
42511 | CORE-FCC-ICO-150 | A/R Debt Solutions | Payment Confirmation File to A/R Debt Solutions | 3. Medium
39392 | CORE-CUS-IOO-122 | SE | Customer information from usage file of AEG | 3. Medium
39192 | CORE-IT-IAO-536 | Message Broadcast | Data - DESCRIP : My Account Notification web job that queries DB2 for all recent payments that have been successfully processedData DIRECTION _x002 : FROM_CSPlatform : InternetVendor System : NoData - FileNam : Data TRANSPORT METHO : Data - FREQUEN : DailyData - VOLUME_ : COMMENTS : | 3. Medium
45869 | CORE-RBP-IAI-332 | DCX | REQUEST - The ebids application makes a service call to get Customer Tariff information RESPONSE- CC&B will provide the customer tariff information | 3. Medium
39446 | CORE-RBP-IAO-417 | ORACLE EBS | CC&B sends current and previous day financial transactions which are tagged to General Ledger to Oracle EBS system. This process the GL Data. | 3. Medium
39458 | CORE-RBP-IAI-429 | ORACLE EBS | A/P Feedback: Interface to transfer monthly cumulative refund checks that has been cashed to banks(Feedback - cashed checks) - Deposit Refund Cashed, send monthly unclaimed deposit to banks (Feedback - outstanding checks) - Deposit Unclaimed, Stale date check file from BNY Mellon | 3. Medium
39399 | CORE-FCC-ICI-094 | MDMS | MDMS to send AMI meter commissioning file to CC&B. | 3. Medium
45871 | CORE-FCC-IOI-334 | MDMS | Commissioning Notification Process commissioning notification file, setting meter to 'AMR Ready' | 3. Medium
39096 | CORE-RBP-ICO-365 | OpenText Exstream | Bill extract - NY - Default - batch CMBECDFL | 3. Medium
39195 | CORE-IT-ICO-539 | Exstream-Broadridge | Send Letter extract file for CECONY Customers. | 3. Medium
132760 | CORE-CUS-IAO-647 | DCX | Service Address Extract | 4. Complex
39386 | CORE-CUS-IOI-116 | ORDSS | ORDSS - Update the information of Agency Approval | 3. Medium
45873 | CORE-CUS-ICO-340 | EMOPSYS | Synchronize EMOPSYS with LSE and Major Accounts customer data. | 2. Simple
37126 | CORE-FCC-ICI-438 | CAMP | CAMP sends AMI Inquiry codes to CC&B. | 3. Medium
39402 | CORE-FCC-ICI-097 | CAMP | CC&B to send Account number, customer name, address, meter type, meter number, meter ami commissioned info, and critical/LSE account info to CAMP based on account number or meter number. | 3. Medium
39393 | CORE-CUS-IOO-123 | Questline | Customer information to Questline | 2. Simple
39365 | CORE-CUS-ICO-053 | EMOPSYS | Extract customer data from CC&B to load into EMOPSYS | 2. Simple
132739 | CORE-CUS-IAI-663 | DCX | Retrieve Concern information | 3. Medium
132736 | CORE-CUS-IAI-644 | DCX | Enroll to Concern Form (EBD) | 3. Medium
132744 | CORE-CUS-IAI-645 | DCX | Update Crisis Indicator on Account | 3. Medium
132756 | CORE-CUS-IAI-646 | DCX | Retrieve MH/LSE information | 3. Medium
132730 | CORE-CUS-IAI-659 | DCX | Retrieve Low Income Program details | 3. Medium
39146 | CORE-RBP-IAI-387 | FISERV | FISERV sends the credit card payment information to CC&B | 3. Medium
39149 | CORE-RBP-IAI-390 | FISERV | Account Verification Service Check the existence of the specified account and return account s balance, due date, past due amount (if any) and existing auto-pay information (if any), cash only flag. | 3. Medium

## Attachment 8
Planned Extensions |  |  | Click Here to Retun To Summary Sheet
ID | Description | Complexity | Functional Category | Functional Sub Category
2147 | System can control payment allocation based upon a customer request. Specifically apply a payment to an outstanding receivable, this would override any system parameters. | 4. Complex | Manage Revenue | Manage Settlement Activities
2117 | System shall apply a single payment over multiple accounts. Master accounts paying with a single check, the System must accommodate distributing the payment across multiple sub-accounts. | 4. Complex | Manage Revenue | Manage Settlement Activities
2752 | System shall have the ability to track and trigger an action across a customer's accounts to determine when they reach a certain dollar value. This is the ability to track against specific line items for certain conditions across various service points/customer/premise/accounts. For example, public benefits, Act 141 charges, LEC | 4. Complex | Manage Revenue | Manage Metered Billing
2991 | System supports validation thresholds can be established based on anticipated peaks, valleys, and annual consumption's for premises based on size, general area, equipment, heat factors, etc. | 4. Complex | Manage Revenue | Manage Meter Reads/Consumption
1746 | System allows the method for determining default deposit amounts by -- meter type or size. | 4. Complex | Manage Revenue | Manage Deposits
1107 | The system shall allow batch identification of previous charge-off or bad debt amounts. Including potential batch skip tracing based upon specified search keys (name, drivers license, tax ID, email address). | 4. Complex | Manage Customer | Manage Customer
2551 | The system shall have the ability to standardize a service address into components including, space number. | 4. Complex | Manage Network, Assets and Operations | Manage Premise and Service Point
2544 | The system shall have the ability to standardize a service address into components including, street number. | 4. Complex | Manage Network, Assets and Operations | Manage Premise and Service Point
3709 | The system should allow for scripting based Q&A with the customer to issue an emergency ticket in CIS with preapproved format and verbiage. The application also allows CSRs to view and update existing tickets via external web services. | 4. Complex | Manage Network, Assets and Operations | Manage Field Work
1989 | The system allows orders to be automatically routed to the appropriate service center/dispatch terminal. The system allows user defined flexible routing and sequencing of orders (e.g. request date, order type, order priority, premise, control route, service area and work area). | 4. Complex | Manage Network, Assets and Operations | Manage Field Work
1969 | The system shall provide the ability to enter and complete service orders in one step for emergency orders and field initiated orders. | 4. Complex | Manage Network, Assets and Operations | Manage Field Work
2477 | The system shall provide automated process to correct accidently mixed/switched meters (numbers, attributes, any billing associated information). | 4. Complex | Manage Network, Assets and Operations | Manage Assets (Meters, Items, Equipment)
1082 | The System shall provide online identification of previous charge-off or bad debt amounts. This includes potential online skip tracing based upon specified search keys (name, driver’s license, tax ID). | 4. Complex | Manage Customer | Manage Customer
1291 | The system shall Provide the ability to standardize commonly used customer names so that they will always be spelled the same--for example, grocery chains, etc. | 4. Complex | Manage Customer | Manage Customer
3693 | The system shall be able to provide for theft of Service Bill Calculations | 3. Medium | Manage Revenue | Manage Unmetered and Other Billing
2177 | Process payments from -- advanced payments (post dated checks) - paper checks. | 3. Medium | Manage Revenue | Manage Settlement Activities
2161 | Optionally a percentage discount or incentive, or flat fee credit would be applied to the next bill for those customers paying immediately or in advance. | 3. Medium | Manage Revenue | Manage Settlement Activities
2160 | System will provide flexible discounts for advanced cash payments. Discount amount and date will print on the customer bill, in addition to the regular due date and amount. Flexible discounts may include: senior citizens, commercial accounts, etc. | 3. Medium | Manage Revenue | Manage Settlement Activities
2145 | System can control that payments are applied to the customer account(s) in a user defined hierarchy which is parameter driven and easy to modify. Allocation of partial payments may be based on -- individual calc line items | 3. Medium | Manage Revenue | Manage Settlement Activities
2144 | System can control that payments are applied to the customer account(s) in a user defined hierarchy which is parameter driven and easy to modify. Allocation of partial payments may be based on -- percentage of accounts receivable. | 3. Medium | Manage Revenue | Manage Settlement Activities
2195 | System shall have the ability to support an escheat process for funds due to customers that cannot be located after "x" months/years (unclaimed property). Refund description shall include account details including, description or purpose of check, check print date, check amount, customer/acct information | 3. Medium | Manage Revenue | Manage Settlement Activities
2194 | System shall have the ability to support an escheat process for funds due to customers that cannot be located after "x" months/years (unclaimed property). Refund description shall include account details including, check number. | 3. Medium | Manage Revenue | Manage Settlement Activities
2182 | System has the ability to manage escheatment. | 3. Medium | Manage Revenue | Manage Settlement Activities
2140 | System will recognize payments received on an account that has a transferred service and automatically posts the payment to the account where the balance was transferred. (Assumption is there are multiple accounts under one person) | 3. Medium | Manage Revenue | Manage Settlement Activities
3032 | System can provide comparative analysis of alternate rates for the customer based on past and/or anticipated consumption. | 3. Medium | Manage Revenue | Manage Rates
3090 | System provides a means for daily dynamic assignment of rates based on weather conditions. | 3. Medium | Manage Revenue | Manage Rates
3033 | The system can provide the ability to track weather conditions such as average temp. to account for low revenues, address customer high bill complaints, or for use in estimating, revenue projections and unbilled revenue. | 3. Medium | Manage Revenue | Manage Rates
3670 | The system can run an analytical comparison between two bills in the customer history. | 3. Medium | Manage Revenue | Manage Metered Billing
2930 | System allows the master account the option of receiving a billing summary and/or by detail showing the usage and charges, by service, being billed to each sub-account. | 3. Medium | Manage Revenue | Manage Metered Billing
2922 | The system can control that any bill resulting in a DR/CR under five dollars (user defined) are held back and not sent to the customer. | 3. Medium | Manage Revenue | Manage Metered Billing
2838 | System shall have the ability to incorporate a client-specific estimation method (i.e. weather normalization - degree days) or other methods. | 3. Medium | Manage Revenue | Manage Metered Billing
2712 | System shall provide customers with options on the layout of their bill, for example offer a detailed bill or a summarized bill with limited information. | 3. Medium | Manage Revenue | Manage Metered Billing
2994 | System can forecast future consumption based upon the consumption history/profile of the customer/premise. For individuals or across the entire system. | 3. Medium | Manage Revenue | Manage Meter Reads/Consumption
2993 | System allows multiple validation thresholds can be established for different account types. (for example, one threshold for Commercial accounts, another threshold for Residential accounts) | 3. Medium | Manage Revenue | Manage Meter Reads/Consumption
1095 | System shall have the ability to handle seasonal use on SP when utility determines "it is ok when there is no usage on the meter OR low use" | 3. Medium | Manage Revenue | Manage Meter Reads/Consumption
3684 | The system shall be able to calculate usage charges billed to one meter from another meter based on load determined to be shared | 3. Medium | Manage Revenue | Manage Meter Reads/Consumption
2964 | System allows for weather normalization will be included in the estimate. | 3. Medium | Manage Revenue | Manage Meter Reads/Consumption
2217 | The system supports a method to review the bad debt and charge-off ledger prior to rendering a refund check amount to the customer. Ability to specify search parameter to identify bad debt customer. | 3. Medium | Manage Revenue | Manage Financials
2214 | The system can support an option to return a duplicate payment to the originating source versus the customer. | 3. Medium | Manage Revenue | Manage Financials
2212 | Calculate mass rate credit/refunds according to parameters such as: customer class, account status, rate schedule, effective dates, geographical area, other rate determinants. User defined method of determining refunds. Ability to calculate taxes if necessary. Ability to determine active, inactive or bad debt customers. | 3. Medium | Manage Revenue | Manage Financials
2189 | System shall have the ability to calculate mass rate credit/refunds according to parameters such as: customer class, account status, rate schedule, effective dates, geographical area, other rate determinants. User defined method of determining refunds. Ability to calculate taxes if necessary. Ability to determine active, inactive or bad debt customers. | 3. Medium | Manage Revenue | Manage Financials
2242 | Refund to third parties any credit balances or security deposits paid on customers accounts, for example by an energy assistance agency (DSS). | 3. Medium | Manage Revenue | Manage Financials
2240 | System allows checks that have been issued and not presented for payment within a user defined number of days of issue to be placed in an unclaimed moneys account. Unclaimed moneys are held for specified period and then forwarded to the proper agency. | 3. Medium | Manage Revenue | Manage Financials
1481 | The system must provide for the ability to enforce a 50% down-payment on a Deposit and a 2-period installment plan for the remainder of the security deposit balance | 3. Medium | Manage Revenue | Manage Deposits
1724 | System shall provide a method to review additional or new deposit(s) on an existing or new account based upon customer class and billed usage. Updates to deposit amount will be made automatically when recommendation amounts fall between a configurable range. | 3. Medium | Manage Revenue | Manage Deposits
1723 | System shall calculate a deposit for a customer based upon user defined criterion, customer class, credit history, etc. | 3. Medium | Manage Revenue | Manage Deposits
1721 | System shall allow the method for determining default deposit amounts, based on customer type (residential versus commercial) and regulated calculation logic. Also - discuss the need for a default amount if 12 months of history is not available | 3. Medium | Manage Revenue | Manage Deposits
1702 | Provide a letter of reference to a former customer in order to establish credit with a new utility company. The letter will include specific information about the customer's history such as the number of late payments. | 3. Medium | Manage Revenue | Manage Deposits
1700 | The system will allow a user to view a customer's credit profile for a customer across all accounts. System has the ability to combine multiple accounts together to provide a "credit at a glance" function. | 3. Medium | Manage Revenue | Manage Deposits
2125 | The System shall have the ability to calculate installments for billing deposit(s) given the time period, as well as the ability to bill deposit with a down payment followed by installments for the remainder. Additionally the system shall provide the ability to properly calculate the installments after down payment amount is considered. | 3. Medium | Manage Revenue | Manage Deposits
1630 | Track payment arrangements on final accounts and render notices based on the terms of the payment arrangement in lieu of the criteria established for regular notices. The notices may have additional terminology reflecting default. | 3. Medium | Manage Revenue | Manage Credit and Collections
1668 | Disconnect notices (the notice that says you are going to be disconnected) may be combined into a disconnect bill and must include all billing information in addition to the disconnect information. | 3. Medium | Manage Revenue | Manage Credit and Collections
1600 | The system allows for the printing of a variable expiration date at the time the disconnect notice is created. For example specify a 7 day allowance for payment instead of 15 days. | 3. Medium | Manage Revenue | Manage Credit and Collections
1591 | Allow for preventing turn-off of account due to delinquency for -- Re-Read Order Pending. | 3. Medium | Manage Revenue | Manage Credit and Collections
1021 | The system shall allow An account to be searched by Soundex (phonetic search). | 3. Medium | Manage Customer | Manage Customer
1530 | System shall have the ability to calculate and over-ride how much the payment arrangement should be, based on income/expenses. | 3. Medium | Manage Revenue | Manage Credit and Collections
1525 | The system shall provide a mechanism for receiving a down payment on a Payment Arrangement before activation of the arrangement | 3. Medium | Manage Revenue | Manage Credit and Collections
1523 | The system shall prevent CSR approval of a payment arrangement in excess of a configurable dollar amount. The system shall allow for a tiered approval of payment arrangement amounts based on user role. | 3. Medium | Manage Revenue | Manage Credit and Collections
1555 | System shall have the capability to produce a delinquency listing of all accounts upon request with unpaid amounts greater than x days old since date the bill was mailed. This listing of delinquencies can be produced under various parameters such as customer class. | 3. Medium | Manage Revenue | Manage Credit and Collections
2879 | System allows for the Utility to define eligibility restrictions that must be met for budget billing and allows users to apply or override restrictions on sign-up. Restrictions may include credit history, amount of delinquency, etc. | 3. Medium | Manage Revenue | Manage Budget Billing
2870 | System provides for levelized billing. System recalculates the monthly payment amount for levelized billing by calculating the average monthly consumption over the past rolling user-defined historical period resulting in a varying monthly consumption and payment (along with additional ConEd Specific Logic) | 3. Medium | Manage Revenue | Manage Budget Billing
2616 | The system shall provide a mass update capability to service address changes (i.e. street name). | 3. Medium | Manage Network, Assets and Operations | Manage Premise and Service Point
2596 | The system shall provide a service address that can be identified and accessed by any or all service components. | 3. Medium | Manage Network, Assets and Operations | Manage Premise and Service Point
2068 | The system provides a mechanism for verification of the customers credit history and theft incidents before allowing non-pay disconnect or turn-on service orders to be processed. | 3. Medium | Manage Network, Assets and Operations | Manage Field Work
2019 | The system provides a mechanism so anytime an out read is scheduled, the order is held for "x" period of time to coincide with the meter reading window. The system provides the ability to override this feature. | 3. Medium | Manage Network, Assets and Operations | Manage Field Work
1120 | The system shall conduct mass changes across accounts, customer records, or premises (e.g. - Postal code changes). Add a note explaining the extent of change. | 3. Medium | Manage Customer | Manage Customer
1992 | The system can group pending orders for efficient service purposes (turn-on/turn-off, address). | 3. Medium | Manage Network, Assets and Operations | Manage Field Work
1944 | The system shall provide a mechanism for the cancellation of one pending service order that will automatically cancel the other associated order(s), with override capabilities (e.g. TNOP disconnect orders). | 3. Medium | Manage Network, Assets and Operations | Manage Field Work
1080 | The System shall allow the option of transferring account balance to new account immediately when the first account is finaled and the new account is opened. (New account established under same person name) | 3. Medium | Manage Customer | Manage Customer
1712 | The system shall Transfer the credit score from the old account to the new account (in the case where a new account is created under the same person name) | 3. Medium | Manage Customer | Manage Customer
3702 | The system shall have the ability to generate custom letters from a list of templates. Uses information from CIS and CSR provided data to create the letters. | 3. Medium | Manage Customer | Manage Customer
1401 | The system will Allow CSR's to fax information to customer from the desktop | 3. Medium | Manage Customer | Manage Customer
2141 | The System will automatically transfer terminated account's final credit or debit balance to a new account (in the case where a new account is created under the same person name) | 3. Medium | Manage Customer | Manage Customer
1244 | The system shall have the ability for the customer record to contain many fields of information specific to the customer's first name, middle name, last name, prefix, and suffix. | 3. Medium | Manage Customer | Manage Customer
3685 | The system shall be able to calculate usage cost of various appliances | 2. Simple | Manage Revenue | Manage Unmetered and Other Billing
3028 | The system provides a method for online amortization calculations (towards loans for line extensions) | 2. Simple | Manage Revenue | Manage Unmetered and Other Billing
3025 | The system can configure that Deliver annual customer statement identifying interest paid during the year via print, fax, email, etc. | 2. Simple | Manage Revenue | Manage Unmetered and Other Billing
2106 | System shall have the ability to process payments for advanced payments (post dated checks). | 2. Simple | Manage Revenue | Manage Settlement Activities
1868 | The system must provide a mechanism to cancel a Remittance Advice as per defined business rules. | 2. Simple | Manage Revenue | Manage Settlement Activities
2204 | System shall provide mass update capability to Reverse (duplicate) payments | 2. Simple | Manage Revenue | Manage Settlement Activities
1674 | System can notify the customer of the returned check. Severity of the notice will reflect the recent credit score for the customer. Ability to overlook an NSF for good credit history. | 2. Simple | Manage Revenue | Manage Settlement Activities
3314 | System shall provide mass update capability for annual re-assignment of rates for most non-residential accounts. | 2. Simple | Manage Revenue | Manage Rates
3310 | System shall provide mass update capability to mass rate changes (i.e. needed when frozen rates are retired). | 2. Simple | Manage Revenue | Manage Rates
3041 | System can provide the ability to track weather conditions such as average temp. to account for low revenues, address customer high bill complaints, or for use in estimating, revenue projections and unbilled revenue (for e.g. Sandy situation) | 2. Simple | Manage Revenue | Manage Rates
1789 | Payment Advice Total transaction includes the summarized total that is to be paid by the ESCO for a customers billing cycle (reverse of 820). | 2. Simple | Manage ConEd Specific Processes | Manage Supplier Choice
1790 | Payment Advice Detail transaction contains only one customer per transaction. This is sent if individual information is needed on an individual customer level. If it is used, it has a Payment cross reference number back to the “Payment Advice Total” transaction for the Trading Partner to match up (reverse of 810). | 2. Simple | Manage ConEd Specific Processes | Manage Supplier Choice
1791 | Ability to receive and process application level transaction that is in response to a Meter Data, Invoice and/or Payment Advice transaction to acknowledge whether the transaction was either accepted or rejected within the receivers system (814 change). | 2. Simple | Manage ConEd Specific Processes | Manage Supplier Choice
2832 | System shall have the ability to control a bill under a user defined amount to be held back and not sent to the customer. | 2. Simple | Manage Revenue | Manage Metered Billing
2630 | System shall have the ability to automatically notify the authorized account representative or other designated user of incomplete contract obligation when attempting to close an account. | 2. Simple | Manage Revenue | Manage Metered Billing
2836 | System shall have the ability to link the content of the insert to the printed bill (same information) for electronic bills. | 2. Simple | Manage Revenue | Manage Metered Billing
2748 | System shall generate customer bills to a digital media such as tape or disk or EDI. | 2. Simple | Manage Revenue | Manage Metered Billing
2744 | System shall accommodate different formats for different types of bills. For example, the delinquent bill is in a different format than the regular bill. | 2. Simple | Manage Revenue | Manage Metered Billing
2741 | System shall input a range of bills to be reprinted. For example, the entire bill run does not need to be printed all at one time. | 2. Simple | Manage Revenue | Manage Metered Billing
2722 | System shall print a disconnect notice directly on the bill, on bill formatting, configurable depending on customer class, and ability to turn on/off. | 2. Simple | Manage Revenue | Manage Metered Billing
1802 | Ability to manage situations where no contest period is required (recharge New York). | 2. Simple | Manage ConEd Specific Processes | Manage Supplier Choice
1806 | Ability to send the Change Customer Information transaction from utility to ESCO. | 2. Simple | Manage ConEd Specific Processes | Manage Supplier Choice
1807 | Ability to receive and process the Change Customer Information transaction from ESCO (in case of Agency Billing). | 2. Simple | Manage ConEd Specific Processes | Manage Supplier Choice
1808 | Ability to send a Change Customer Location transaction for customer's move to new premise (within Utility service territory) . | 2. Simple | Manage ConEd Specific Processes | Manage Supplier Choice
1809 | Ability to receive and process a Change Customer Location transaction from ESCO - for customer's move to new premise (within Utility service territory)- in case of Agency Billing scenario. | 2. Simple | Manage ConEd Specific Processes | Manage Supplier Choice
1810 | Calculate and convey distribution charges to the ESCO in ESCO Consolidated Billing (Agency Billing) scenario. | 2. Simple | Manage ConEd Specific Processes | Manage Supplier Choice
2986 | The system has the ability to utilize degree days in usage estimate algorithm | 2. Simple | Manage Revenue | Manage Meter Reads/Consumption
1814 | Ability to process invoice rebill transactions as defined by regulations and business rules. | 2. Simple | Manage ConEd Specific Processes | Manage Supplier Choice
1815 | Ability to receive and process ESCO initiated cancel / rebill transactions (must be received during the bill window/shelf) in addition to the Invoice. | 2. Simple | Manage ConEd Specific Processes | Manage Supplier Choice
1816 | Ability for ESCO to receive and process final usage and billing information for the customer's old location after the reading has been obtained. | 2. Simple | Manage ConEd Specific Processes | Manage Supplier Choice
2972 | System can measure usage based upon the passage of time (for e.g. streetlights, antenna accounts, unmetered, traffic signals, bus shelters, etc.) | 2. Simple | Manage Revenue | Manage Meter Reads/Consumption
1818 | Ability to support the drop transaction in order to terminate a billable enrollment between a customer and the current ESCO (at the next scheduled meter read date). | 2. Simple | Manage ConEd Specific Processes | Manage Supplier Choice
1819 | Ability to support the drop transaction in order to terminate a billable enrollment between a customer and the current ESCO (at a specified meter read date). | 2. Simple | Manage ConEd Specific Processes | Manage Supplier Choice
1820 | Ability to send advance notice of drop as per regulations notifying ESCO that customer is about to be dropped due to collections. | 2. Simple | Manage ConEd Specific Processes | Manage Supplier Choice
1821 | Ability to receive and process drop notifying the Utility that customer will no longer be a customer (customer/ESCO initiated). | 2. Simple | Manage ConEd Specific Processes | Manage Supplier Choice
1822 | Ability to send the Utility initiated drop notifying active or pending active ESCO that customer will no longer be a customer. | 2. Simple | Manage ConEd Specific Processes | Manage Supplier Choice
1823 | Ability to receive and process enrollment requests as per regulations and defined business rules. | 2. Simple | Manage ConEd Specific Processes | Manage Supplier Choice
1824 | Communicate a successful enrollment to the customer based upon the successful processing of the enrollment. | 2. Simple | Manage ConEd Specific Processes | Manage Supplier Choice
1825 | Ability to automatically generate enrollment letter to customer. | 2. Simple | Manage ConEd Specific Processes | Manage Supplier Choice
1826 | Ability to process customer initiated rescinding request as per defined business rules. | 2. Simple | Manage ConEd Specific Processes | Manage Supplier Choice
1827 | Ability to send enrollment responses per business rules matched 100% to enrollment requests. | 2. Simple | Manage ConEd Specific Processes | Manage Supplier Choice
1828 | Ability to follow enrollment effective date regulations including multiple enrollments received during a billing period. | 2. Simple | Manage ConEd Specific Processes | Manage Supplier Choice
1829 | Ability to receive and process enrollment changes as per regulations. | 2. Simple | Manage ConEd Specific Processes | Manage Supplier Choice
1830 | Ability to send enrollment change response as per regulations. | 2. Simple | Manage ConEd Specific Processes | Manage Supplier Choice
1831 | Ability to manage overrides (i.e., where ESCO enrollment transaction can override the standard offer during enrollment period). | 2. Simple | Manage ConEd Specific Processes | Manage Supplier Choice
1832 | Allow only one ESCO per customer per service (electric / gas) for any given billing period. There is no limit to the number of times a customer can enroll with a different ESCO in different billing periods. | 2. Simple | Manage ConEd Specific Processes | Manage Supplier Choice
1833 | Ability to charge for off-cycle meter readings for off-cycle enrollments. | 2. Simple | Manage ConEd Specific Processes | Manage Supplier Choice
1834 | Ability to handle situations where multiple enrollments for the same customer are received from multiple ESCOs in a single billing cycle, the first transaction received by a ESCO as determined by the transaction date and time will be accepted and subsequent transactions will be rejected. | 2. Simple | Manage ConEd Specific Processes | Manage Supplier Choice
1835 | Ability to automatically switch the customer account from Utility to ESCO - effective upon enrollment date. | 2. Simple | Manage ConEd Specific Processes | Manage Supplier Choice
1837 | Ability to support enrollment for Net Metering accounts. | 2. Simple | Manage ConEd Specific Processes | Manage Supplier Choice
1838 | Ability to handle situations where multiple enrollments for the same customer are received from multiple ESCO in a single billing cycle. | 2. Simple | Manage ConEd Specific Processes | Manage Supplier Choice
1839 | Ability to receive and process ESCO bill messages only during 'n' days bill window/shelf. | 2. Simple | Manage ConEd Specific Processes | Manage Supplier Choice
1840 | Ability to receive and process ESCO Prices with ESCO charges only during 'n' days bill window/shelf. | 2. Simple | Manage ConEd Specific Processes | Manage Supplier Choice
1841 | Ability to manually change the 'n' days bill window/shelf on demand. | 2. Simple | Manage ConEd Specific Processes | Manage Supplier Choice
1842 | Ability to send responses (e.g. - NCC - no current charges) to inform ESCO that transaction submitted was not successfully processed. | 2. Simple | Manage ConEd Specific Processes | Manage Supplier Choice
1843 | Ability to reject ESCO Prices (Utility Consolidated Bill Ready) transactions as per defined business rules. | 2. Simple | Manage ConEd Specific Processes | Manage Supplier Choice
2963 | System provides a means to view customers with greater than "x" number of estimated bills over "x" period of time. | 2. Simple | Manage Revenue | Manage Meter Reads/Consumption
3311 | System shall provide mass update capability to apply/reverse tax charges. | 2. Simple | Manage Revenue | Manage Financials
1846 | Ability to receive and process historical usage requests from ESCO (embedded in an enrollment request). | 2. Simple | Manage ConEd Specific Processes | Manage Supplier Choice
1847 | Ability to respond to historical usage requests from ESCO with historical usage (interval). | 2. Simple | Manage ConEd Specific Processes | Manage Supplier Choice
1848 | Ability to respond to historical usage requests from ESCO with historical usage (monthly). | 2. Simple | Manage ConEd Specific Processes | Manage Supplier Choice
1849 | Ability to receive and process historical usage requests from ESCO (as a separate transaction). | 2. Simple | Manage ConEd Specific Processes | Manage Supplier Choice
1850 | Ability to support Trading Partner Invoice type - Settlement Invoice Detail (Invoice used for the settlement between the Utility and ESCO based on market price). “Settlement Detail” transaction contains only one customer per transaction. This is sent if individual information is needed on an individual customer level (Invoice - 810). | 2. Simple | Manage ConEd Specific Processes | Manage Supplier Choice
1851 | Ability to support ESCO invoice transaction - Electric | 2. Simple | Manage ConEd Specific Processes | Manage Supplier Choice
1852 | Ability to support ESCO invoice transaction - Gas | 2. Simple | Manage ConEd Specific Processes | Manage Supplier Choice
1853 | Ability to support Trading Partner Invoice type - Settlement Invoice Detail (Invoice used for the settlement between the Utility and ESCO based on market price). | 2. Simple | Manage ConEd Specific Processes | Manage Supplier Choice
1854 | Provide the ability for Utility to allow Billing Option Change by providing a lead time. | 2. Simple | Manage ConEd Specific Processes | Manage Supplier Choice
1855 | Enforce all applicable customer choice standards, regulations and business rules (including but not limited to switching rules and seamless moves) for associated retail choice decision-making. | 2. Simple | Manage ConEd Specific Processes | Manage Supplier Choice
1856 | Ability to manage market rules (e.g. only one enrollment/switch for a particular billing period can be queued up at a time, switches are effective on the customer’s next scheduled meter reading, etc.). | 2. Simple | Manage ConEd Specific Processes | Manage Supplier Choice
3309 | System shall provide mass update capability to apply/reverse late charges. | 2. Simple | Manage Revenue | Manage Financials
2221 | The system supports the ability To reverse the credit refund back into the corporation after "x" months/years if the customer cannot be located (and check not cashed) | 2. Simple | Manage Revenue | Manage Financials
1859 | Enable integration testing for related enhancements and end-to-end transaction testing with retail market participants. | 2. Simple | Manage ConEd Specific Processes | Manage Supplier Choice
1860 | Provide automated and ad hoc reporting capabilities (for e.g. retail market participant data, transaction counts, financials etc.). | 2. Simple | Manage ConEd Specific Processes | Manage Supplier Choice
1862 | Provide real-time response to incoming transactions. | 2. Simple | Manage ConEd Specific Processes | Manage Supplier Choice
1863 | Allow for situations where a summary billed account may have more than one ESCO serving its detailed accounts. | 2. Simple | Manage ConEd Specific Processes | Manage Supplier Choice
1864 | Ability to send notice of customer payment or payment return to ESCO. | 2. Simple | Manage ConEd Specific Processes | Manage Supplier Choice
1865 | Ability to send payment/remittance transaction to ESCO in conjunction with ACH payment transactions. | 2. Simple | Manage ConEd Specific Processes | Manage Supplier Choice
1867 | Ability to send Remittance Advice to deduct moneys from ESCOs if a bill is cancelled after already paying ESCO. | 2. Simple | Manage ConEd Specific Processes | Manage Supplier Choice
1870 | Ability to cancel a ESCO Remittance Advice / Payment deduct as per defined business rules. | 2. Simple | Manage ConEd Specific Processes | Manage Supplier Choice
1871 | Ability to receive and process reinstatement - reinstating customer to previous ESCO as per regulations. | 2. Simple | Manage ConEd Specific Processes | Manage Supplier Choice
1872 | Ability to support Trading Partner Invoice type - Settlement Invoice Total (Invoice used for the settlement between the Utility and ESCO based on market price). “Settlement Total” transaction includes summary information based on all customers billing cycle (Remittance Advice - 820) | 2. Simple | Manage ConEd Specific Processes | Manage Supplier Choice
1874 | Ability to manage retention periods by providing the lead-time (4 calendar days) for enrollment, drops transactions. | 2. Simple | Manage ConEd Specific Processes | Manage Supplier Choice
1875 | An invoice to ESCO represents the charges and fees (e.g. off-cycle meter reads, billing and payment processing services, Historical Usage transactions, etc.). The ESCO Invoice schedule will be determined as defined per business rules. | 2. Simple | Manage ConEd Specific Processes | Manage Supplier Choice
1876 | An invoice to ESCO represents the charges and fees (e.g. WBS, capacity and balance charges, billing fees, purchase and receivable charge, miscellaneous charges). The ESCO Invoice schedule will be determined as defined per business rules. | 2. Simple | Manage ConEd Specific Processes | Manage Supplier Choice
2199 | System shall have the ability to identify accounts that are not eligible to have an automatic refund based on user defined attributes (i.e. payment source, code, etc.). | 2. Simple | Manage Revenue | Manage Financials
1456 | The system can be configured to send a Deposit Confirmation letter when the deposit is paid in full. | 2. Simple | Manage Revenue | Manage Deposits
1882 | Ability to process Status Advice (SA) transaction used by a Trading Partner for an informational change in status/response to an originating Service Transaction Request (STR) or Meter Data transaction. The SA is sent on an as needed basis. It contains contact information, effective processing dates and descriptions of status changes (814 change). | 2. Simple | Manage ConEd Specific Processes | Manage Supplier Choice
1883 | Ability to send billable usage (monthly or interval) to ESCO for metered accounts as per regulations and defined business rules. | 2. Simple | Manage ConEd Specific Processes | Manage Supplier Choice
1884 | Ability to send billable usage (monthly or interval) to ESCO by account type (for e.g. net-metering accounts) as per regulations and defined business rules. | 2. Simple | Manage ConEd Specific Processes | Manage Supplier Choice
1885 | Ability to send billable usage (monthly or interval) to ESCO by account type (for e.g. true un-metered accounts - such as streetlights, bus shelters, etc.) as per regulations and defined business rules. | 2. Simple | Manage ConEd Specific Processes | Manage Supplier Choice
1886 | Ability to send billable usage (monthly or interval) to ESCO by account type (for e.g. un-metered service - irregular meter conditions, theft of service) as per regulations and defined business rules. | 2. Simple | Manage ConEd Specific Processes | Manage Supplier Choice
1887 | Ability to process all the necessary information in the Usage (such as multiplied consumption and demand). | 2. Simple | Manage ConEd Specific Processes | Manage Supplier Choice
1888 | Sending billing usage will open a 'n' days bill window/shelf for ESCO to reply with Invoice (Utility Consolidated Bill Ready scenario) containing ESCO charges and bill messages. | 2. Simple | Manage ConEd Specific Processes | Manage Supplier Choice
1889 | Ability to send cancellation transaction to ESCOs to cancel original usage. | 2. Simple | Manage ConEd Specific Processes | Manage Supplier Choice
1719 | The system must provide a mechanism to calculate Deposit recommendations as two times the prior occupant's monthly bill over a 12-month period. If the premise has heating, that recommendation amount should be two times the cold-weather period average. | 2. Simple | Manage Revenue | Manage Deposits
1697 | The system must provide a method of using a reference (a series of automated checks using another account in the person's name) account to prevent a request for a deposit on an additional account. | 2. Simple | Manage Revenue | Manage Deposits
2207 | The system provides for automatic deposit refunds to active customers based upon: credit history and length of time the deposit has been on file. A customer with poor credit history is defined as follows: accumulates two consecutive months of arrears without making reasonable payment, defined as one half of the total arrears, or fails to make a reasonable payment on a bimonthly bill within 50 days after the bill is due, provided that the utility requests such deposit within two months of such failure to pay; or had utility service terminated, disconnected or suspended for nonpayment during the preceding six months | 2. Simple | Manage Revenue | Manage Deposits
1769 | The system provides an ability to maintain accurate interest earning records on deposits and overpayments held more than 60 days | 2. Simple | Manage Revenue | Manage Deposits
2124 | The System shall have the ability to set different parameter limits (arrears, length of time) for commercial and residential automatic deposit refunds. | 2. Simple | Manage Revenue | Manage Deposits
1766 | The system shall issue correspondence to be issued to notify the customer of an increase or decrease of deposit amount. | 2. Simple | Manage Revenue | Manage Deposits
1748 | The system shall Determine additional or new deposit(s) for an existing account based upon: actual usage, payment history, credit score, etc. | 2. Simple | Manage Revenue | Manage Deposits
1735 | System shall provide the ability to automatically adjust the deposit on hand for over/under secured deposits. A configurable tolerance percentage (top and bottom range) helps control what we automatically change versus creating a To Do for manual review | 2. Simple | Manage Revenue | Manage Deposits
1727 | The System shall have the ability for the deposit to be assessed based on customers credit rating (internal rating) or external from Equifax if not available internally. | 2. Simple | Manage Revenue | Manage Deposits
1722 | The System shall allow the method for determining default deposit amounts, including billing method (single premise versus aggregate). | 2. Simple | Manage Revenue | Manage Deposits
1540 | System shall provide the ability to generate a "x" day deposit letter for post bankrupt account(s). Requesting for an additional deposit on the new account. | 2. Simple | Manage Revenue | Manage Deposits
1777 | The system must be able to identify properties managed by landlords. In the case of a No Access field completion code, the system must be able to notify the landlord in writing of the No Access alert. | 2. Simple | Manage Revenue | Manage Credit and Collections
1642 | System can trigger the notice of the returned check based on the credit history. Severity of the notice will be depending on where account was in the credit flow. | 2. Simple | Manage Revenue | Manage Credit and Collections
1602 | Delinquency notices or disconnect notices must include specific information including -- customer name, mailing address, delivery point, and/or the customers service address, date. | 2. Simple | Manage Revenue | Manage Credit and Collections
1594 | The system allows for circumvention of the final disconnect notices and non-pay disconnect orders during periods of severe weather. | 2. Simple | Manage Revenue | Manage Credit and Collections
1776 | The system must be able to flag accounts and issue orders for customers eligible for Winter Heat that have been shut off during non-moratorium times | 2. Simple | Manage Revenue | Manage Credit and Collections
1686 | The system provides an ability to suspend collection events by customer designation at various time of the year (shut off) | 2. Simple | Manage Revenue | Manage Credit and Collections
1678 | The system can track payment arrangements on both active and finaled accounts and render notices based on the terms of the payment arrangement in lieu of the criteria established for regular notices. The notices may have additional terminology reflecting default. | 2. Simple | Manage Revenue | Manage Credit and Collections
1624 | System is capable of printing a letter for a Pay Plan after it is established with the customer. | 2. Simple | Manage Revenue | Manage Credit and Collections
1622 | The system can track payment arrangements on active accounts and render notices based on the terms of the payment arrangement in lieu of the criteria established for regular notices. The notices may have additional terminology reflecting default. | 2. Simple | Manage Revenue | Manage Credit and Collections
1612 | The system allows for preventing turn-off of account due to delinquency for -- High Bill Investigation and Bill Disputes for PSC cases. | 2. Simple | Manage Revenue | Manage Credit and Collections
1528 | System shall ensure a broken payment arrangement causes the account to fall back in to accelerate collections. Count the number of these. | 2. Simple | Manage Revenue | Manage Credit and Collections
1526 | The system shall wait X days for payment of a Payment Arrangement down payment before activating the Payment Arrangement. | 2. Simple | Manage Revenue | Manage Credit and Collections
1524 | The system shall automatically generate a Payment Arrangement Terms of Service letter at initiation of the agreement. This is sent to customer. | 2. Simple | Manage Revenue | Manage Credit and Collections
1521 | The system can trigger a notification letting a customer know they are eligible for payment arrangement a configurable amount of days after bill issue and non-payment of said bill. | 2. Simple | Manage Revenue | Manage Credit and Collections
1669 | The system can configure that Delinquency notices or disconnect notices must include specific information. This information may include the following: > The customer name, mailing address, delivery point, and/or the customers service address > Ability to specify if to be delivered in person to the customers service address > State the reason for the proposed termination > Total outstanding balance and past due amount > Date Due > Acceptable method of payment > Available payment location and hours | 2. Simple | Manage Revenue | Manage Credit and Collections
1648 | System can trigger the notice of the returned check and the bank's return reason. | 2. Simple | Manage Revenue | Manage Credit and Collections
1508 | System shall allow for collection activity to be "frozen" so that no action is taken during batch processing. Monetary reasons that would freeze or hold a collection process include: Disputed Amounts (PSC Complaint) - all PSC complaints have money involved that must be isolated from collections Pay Arrangement Pay Plan | 2. Simple | Manage Revenue | Manage Credit and Collections
2882 | System provides flexibility to vary budget billing parameters by company. | 2. Simple | Manage Revenue | Manage Budget Billing
2881 | System can control if a late payment charge is added to a delinquent budget amount. | 2. Simple | Manage Revenue | Manage Budget Billing
2874 | System supports the automatic generation of notice to customer that they are subject to removal from budget billing or that the budget period is ending. | 2. Simple | Manage Revenue | Manage Budget Billing
2668 | The System shall have the ability to provide an online inquiry to contracts by customer and by location. | 2. Simple | Manage Products and Services | Manage Products and Services
2647 | The System shall automatically notify the authorized internal Utility Account Representative of service termination or rate change when contract items exist that relate to the premise or rate - physical equipment (i.e. solar panels, electric vehicle charging equipment, direct load control equipment) or usage programs (i.e. Shared Solar, Green Power Tomorrow). | 2. Simple | Manage Products and Services | Manage Products and Services
1367 | The system will Provide the ability to extract target customer groups for customer surveys to regularly determine if the Utility is meeting customer needs. Provide an external process for mailings. | 2. Simple | Manage Products and Services | Manage Products and Services
3689 | The system shall be able to launch a prorate calculator to help with manual bill calculations | 2. Simple | Manage Network, Assets and Operations | Manage System Mechanics
3524 | The application dis-allows users to be signed onto more than one workstation (CIS sessions) simultaneously. | 2. Simple | Manage Network, Assets and Operations | Manage System Mechanics
3520 | The application provides the ability to build a new screen via configuration | 2. Simple | Manage Network, Assets and Operations | Manage System Mechanics
3518 | The application provides the ability to move display fields to a desired location on the screen via configuration. | 2. Simple | Manage Network, Assets and Operations | Manage System Mechanics
3490 | The application provides the ability to customize the online help | 2. Simple | Manage Network, Assets and Operations | Manage System Mechanics
3489 | The application provides Online help that is context sensitive (system will recognize cursor position for a fast path to the help text) | 2. Simple | Manage Network, Assets and Operations | Manage System Mechanics
3488 | The application provides Online help that is available at the system, function, screen, and field level | 2. Simple | Manage Network, Assets and Operations | Manage System Mechanics
3487 | The application provides Online help where content is exportable via different mediums (email,pdf) | 2. Simple | Manage Network, Assets and Operations | Manage System Mechanics
3486 | The application provides Online help (Process-specific)that includes an index and search capability | 2. Simple | Manage Network, Assets and Operations | Manage System Mechanics
3485 | The application provides Online help (Process-specific)that can be updated with each new version release | 2. Simple | Manage Network, Assets and Operations | Manage System Mechanics
1101 | The system shall optionally generate a summary letter to be given or sent to customer for confirmation of service transfer. | 2. Simple | Manage Customer | Manage Customer
3484 | The application provides customized online help (Process-specific) that is upgradeable to new releases. | 2. Simple | Manage Network, Assets and Operations | Manage System Mechanics
3433 | The system provides a method of defining and constructing online user documentation. | 2. Simple | Manage Network, Assets and Operations | Manage System Mechanics
3413 | The system provides a method to be be placed on key queues to notify users of the need to work the queue (email, sms, etc.). As new items are routed to the queue, users will automatically be alerted. | 2. Simple | Manage Network, Assets and Operations | Manage System Mechanics
3408 | The system shall have functionality to alert proper staff members if exceptions or other work items have aged past a limit set on a per exception or item basis. | 2. Simple | Manage Network, Assets and Operations | Manage System Mechanics
2205 | The system shall provide a mass update capability to Bank routing number changes. | 2. Simple | Manage Network, Assets and Operations | Manage System Mechanics
2614 | The system shall provide a mass update capability to Zip code updates. | 2. Simple | Manage Network, Assets and Operations | Manage Premise and Service Point
2568 | The system shall update service address information for entire selected geographical area as specified (e.g. change in street name or postal code). | 2. Simple | Manage Network, Assets and Operations | Manage Premise and Service Point
1111 | The system shall Establish customer tax or fee exemption status and re-certification dates. Create notification / alert for re-certification status, send automated letter based on expiry of certification. | 2. Simple | Manage Customer | Manage Customer
2071 | The system shall provide a mass update capability to create, cancel or reschedule orders. | 2. Simple | Manage Network, Assets and Operations | Manage Field Work
1115 | The system shall support user requests to identify and list accounts by account classification or category (e.g. - SIC code, Trade Class, Postal Code Area, Life Support Customers, Large Volume Users, etc.). | 2. Simple | Manage Customer | Manage Customer
2000 | The system provides a mechanism so customization of the service order format is user definable. | 2. Simple | Manage Network, Assets and Operations | Manage Field Work
1968 | The system shall provide the ability to mass close multiple orders in one transaction with a user inputted service order number range or by service tech ID. | 2. Simple | Manage Network, Assets and Operations | Manage Field Work
1945 | The system shall identify canceled orders through electronic notification for those orders which have already been printed. | 2. Simple | Manage Network, Assets and Operations | Manage Field Work
1931 | The system shall provide online inquiry of pending orders via -- schedule date. | 2. Simple | Manage Network, Assets and Operations | Manage Field Work
1928 | The system shall provide online inquiry of pending orders via -- service order (control route) area. | 2. Simple | Manage Network, Assets and Operations | Manage Field Work
1907 | The system provides online inquiry and browsing of orders. This may include the following access methods:> Route number | 2. Simple | Manage Network, Assets and Operations | Manage Field Work
1905 | The system provides online inquiry and browsing of orders. This may include the following access methods:> Order Status | 2. Simple | Manage Network, Assets and Operations | Manage Field Work
1138 | The system shall be able to notify different agencies (landlord, tenants, public officials) by sending the duplicate notifications (outstanding balance notifying service could be terminated), letters etc. (for both on active and inactive accounts). | 2. Simple | Manage Customer | Manage Customer
1904 | The system provides online inquiry and browsing of orders. This may include the following access methods:> Schedule Date/Time | 2. Simple | Manage Network, Assets and Operations | Manage Field Work
1902 | The system provides online inquiry and browsing of orders. This may include the following access methods:> Service Order (Control Route) Area | 2. Simple | Manage Network, Assets and Operations | Manage Field Work
2452 | An Online meter search capability is supported that utilizes -- installation date. | 2. Simple | Manage Network, Assets and Operations | Manage Assets (Meters, Items, Equipment)
2451 | The system supports an Online meter search capability that utilizes -- trip number (sequence within route) for specific services. | 2. Simple | Manage Network, Assets and Operations | Manage Assets (Meters, Items, Equipment)
2435 | The system shall provide an automatic delete date on a customer contact | 2. Simple | Manage Network, Assets and Operations | Manage Assets (Meters, Items, Equipment)
2326 | An Online equipment search capability is supported that utilizes -- route number. | 2. Simple | Manage Network, Assets and Operations | Manage Assets (Meters, Items, Equipment)
1469 | The system must be able to trigger a letter to Summary accounts X days after non-payment of a bill, warning them of removal from summary billing for nonpayment. | 2. Simple | Manage Customer | Manage Customer
3697 | The system shall have the ability to analyze accounts online and display results by following business rules established by the business area | 2. Simple | Manage Customer | Manage Customer
3687 | The system shall be able to execute different online analysis (and display results to CSRs) on accounts, starting with General Analysis. | 2. Simple | Manage Customer | Manage Customer
1480 | The system shall generate a Denial of Service letter that must be sent to any customer who refused service at time turn-on call. | 2. Simple | Manage Customer | Manage Customer
1478 | The system must recognize that a non-apartment building has been without service for a period of 6 months or more | 2. Simple | Manage Customer | Manage Customer
1416 | The system must automatically trigger a letter documenting requirements needed to meet LSE (Life Sustaining Equipment) qualifications when LSE Status requested by customer | 2. Simple | Manage Customer | Manage Customer
1351 | The system will identify potential customers who have moved into premises and have not completed the turn-on process yet (active / inactive accounts). | 2. Simple | Manage Customer | Manage Customer
1054 | The system will Identify all services available within a user inputted street block range. | 2. Simple | Manage Customer | Manage Customer
1455 | The system should send a communication to a landlord (via their preferred communication channel) notifying them of pending transfer of service, when a tenant performs a Shut off or transfer of service on a premise managed by a landlord. | 2. Simple | Manage Customer | Manage Customer
2203 | The System shall have the ability to support notification / letters to customers with unclaimed credit balances. | 2. Simple | Manage Customer | Manage Customer
1490 | The System shall provide mass update capability to Creation of customer contacts (notes) | 2. Simple | Manage Customer | Manage Customer
1489 | The System shall provide mass update capability to customer contact entries (notes) | 2. Simple | Manage Customer | Manage Customer
1460 | The system shall Provide a automatic delete or purge date on a note/remark. | 2. Simple | Manage Customer | Manage Customer
1444 | The system shall allow for the development of scripts to be flexible and can be customized to a defined group of users. | 2. Simple | Manage Customer | Manage Customer
1422 | The system shall have the ability to search and view potential and existing customer contacts by any defined field. e.g. date (most recent contact displayed first), service, location, etc. | 2. Simple | Manage Customer | Manage Customer
1400 | The system will Provide for faxing of customer requested information (for e.g. statements). | 2. Simple | Manage Customer | Manage Customer
1361 | The system will Provide for automated follow-up with customers through telephone calls or correspondence triggered through the work queue or similar mechanism. For example: at the completion of certain call types (email, text, fax, etc.), correspondence will automatically be generated, for (e.g. call back confirming receipt of payment, outage calls) | 2. Simple | Manage Customer | Manage Customer
1358 | The System shall provide the ability for automated follow-up with customers through telephone calls or correspondence triggered through the work queue or similar mechanism. For example: at the completion of certain call types, correspondence will automatically be generated. | 2. Simple | Manage Customer | Manage Customer
1232 | The system will Automatically send correspondence for a specific situation including -- Re-connect Forms. | 2. Simple | Manage Customer | Manage Customer
1230 | The system will Automatically send correspondence for a specific situation including -- Preauthorized Debit (based on threshold), a reminder that the money will be taken out of the bank. | 2. Simple | Manage Customer | Manage Customer
1229 | The system will Automatically send correspondence for a specific situation including -- Customer underground or above ground pipe (legal requirement to notify customer they need to maintain). | 2. Simple | Manage Customer | Manage Customer
1228 | The system will Automatically send correspondence for a specific situation including -- Returned check. | 2. Simple | Manage Customer | Manage Customer
1636 | The system shall provide access to a list of customers currently receiving agency assistance and the amount they qualify for. | 2. Simple | Manage Customer | Manage Customer
3312 | The System shall provide the ability to print both financially responsible person names on the bill | 2. Simple | Manage Customer | Manage Customer
2188 | The System shall have the ability to automatically transfer within the service territory within "x" number of days transfer the overpayment to the new account, subject to user defined criteria. | 2. Simple | Manage Customer | Manage Customer
1195 | The system shall provide online access to -- actual image of the bill as it was produced and distributed to the customer. | 2. Simple | Manage Customer | Manage Customer
1670 | The system shall allow access to a list (search/display) of customers that have received agency assistance and the amount they qualify for. | 2. Simple | Manage Customer | Manage Customer
1487 | The system shall list All product and merchandise offerings available to the customer | 2. Simple | Manage Customer | Manage Customer
1198 | Provide an online view of -- total combined consumption across multiple meters and multiple registers. | 2. Simple | Manage Customer | Manage Customer
1454 | Provide the ability for new billing system be programmed in such a way that, after every Xth phone call, a screen pops up to the CSR asking the CSR to categorize the just-completed phone call. The value of X would be chosen in such a way that, over the course of the year, approximately 1,100 phone calls are categorized. This method would eliminate the need for Customer Ops to review phone calls, while still providing RE with the data it needs for unbundling. | 2. Simple | Manage Customer | Manage Customer
1414 | The System automatically generates notification of pending removal of a special condition status in a user specified number of days from the re-certification date. | 2. Simple | Manage Customer | Manage Customer
1365 | The system shall Provide for the download of customer records into Client (Excel, Access) software for subsequent manipulation. | 2. Simple | Manage Customer | Manage Customer
1364 | The system shall Provide for the Online identification and segmentation of the existing customer base through any data entity or data relationship (used to target market customers for any process). | 2. Simple | Manage Customer | Manage Customer
1341 | The system shall Provide the ability to search for and access the customer record by -- Route and Service Cycle Number. | 2. Simple | Manage Customer | Manage Customer
1339 | The system shall Provide the ability to search for and access the customer record by -- Borough and Muni. | 2. Simple | Manage Customer | Manage Customer
1294 | The system shall tailor information data fields and will only display based on the customer type. For example: Commercial customers will have fields for Departmental contacts - residential will not. | 2. Simple | Manage Customer | Manage Customer
1212 | The system shall print a formatted statement of account for example: billing / consumption / payment history for the customer displaying the most recent information first. | 2. Simple | Manage Customer | Manage Customer

## Attachment 9
Final Actual Extensions |  |  | Click Here to Retun To Summary Sheet
ID | Title | Description | Complexity | Functional Category | Functional Sub Category
95982 | CORE-RBP-BPD007-E-022 | A custom algorithm will be developed to extract all fields required for CECONY/O&R bills and provide a simplified XML structure to Exstream for bill formatting. | 2. Simple | Rates, Billing, and Payments | Manage Billing
45805 | CORE-TPI-BPD019-E-001-01 | BO Monitoring Algorithm | 2. Simple | Third Party Interactions | Manage Retail Choice
45810 | CORE-TPI-BPD020-E-004 | CECONY has CSS desktop application that has “RC Apps” under Menu And Applications. This provides the capability to CSR or Specialist to access related applications. This tool allows CSR to choose any of the listed application and navigate based on the discussion with customer. Now CECONY want this feature in CC&B portal where CSR can access and continue to use the set of applications available on “RC Apps”. | 2. Simple | Third Party Interactions | Manage Retail Choice
46907 | CORE-FCC-BPD015-E-011-01 | Turn On referral orders printed in Service Center directly | 2. Simple | Field, Credit, and Collections | Manage Field Work
46896 | CORE-RBP-BPD011-E-001 | A custom portal and query zones will be developed available from the Deposit Control context menu. This portal would display tender controls within the deposit control and a break down of the lobby payments by operating company. This data could be transcribed by the rep onto the deposit slip. A collapsed zone for details of the tenders that make up the total would be available for aid in reconciliation efforts. | 2. Simple | Rates, Billing, and Payments | Manage Remittances
56945 | CORE-RBP-BPD011-E-002 | A custom batch job to split the UNID Payment into 60-40% at the time of escheatment to NY State | 2. Simple | Rates, Billing, and Payments | Manage Remittances
56946 | CORE-RBP-BPD011-E-003 | Custom Algorithm to transfer money into appropriate SA Type with correct GL Accounting on receiving the Stale-Check Cancellation Info from Bank | 2. Simple | Rates, Billing, and Payments | Manage Remittances
56947 | CORE-RBP-BPD011-E-005 | Custom Auto-Transition Algorithm to transition the escheatment cas | 2. Simple | Rates, Billing, and Payments | Manage Remittances
56948 | CORE-RBP-BPD011-E-007 | Custom Batch for post-extract of customer details to escheating authority | 2. Simple | Rates, Billing, and Payments | Manage Remittances
56949 | CORE-RBP-BPD011-E-008 | Custom Algorithm to build the GL String for financial transactions pertaining to Bill Creation/Cancellation, Adjustment Creation/Cancellation (including transfers) and Payment Creation/Cancellation | 2. Simple | Rates, Billing, and Payments | Manage Remittances
45819 | CORE-CUS-BPD002-E-003 | Customer consent will be stored as contact status. 'Pending' status will stand for 'Consent Not Provided' and 'Approved' status will stand for 'Consent provided' and consent date will be stored in characteristics A custom algorithm will be developed which will create a dashboard alert if the contact status is approved and consent date is older than 6 months. When a customer calls CSR and CSR sees this alert, he/she will ask the customer for consent again and, if consent provided, will update the status in person contact to approved with latest date | 2. Simple | Customer Service | Manage Contact
45820 | CORE-CUS-BPD002-E-006 | A custom audit algorithm on customer contact will be developed. This algorithm will prevent update of customer contact fields after the customer contact is created. User can only add new log entries to existing customer contact record. | 2. Simple | Customer Service | Manage Contact
46922 | CORE-CUS-BPD003-E-003 | A custom BO algorithm will be developed and plugged on the Person business object to check if the person is linked to multiple accounts | 2. Simple | Customer Service | Manage Start/Stop
46923 | CORE-CUS-BPD003-E-004 | A custom SA activation algorithm will be developed to create a customer contact for the new accounts | 2. Simple | Customer Service | Manage Start/Stop
46924 | CORE-CUS-BPD003-E-005 | BILLING batch will create a bill as per the schedule defined for bill cycle on the account. The generated bill will contain both the closing bill segment for the old SA and the opening bill segment for the new SA. Solution will require minimal customization to close loan SA | 2. Simple | Customer Service | Manage Start/Stop
46925 | CORE-CUS-BPD003-E-006 | Custom algorithm to create a contact when the same SSN is found on another account on a different premise, which will generate the Red Flag letter. | 2. Simple | Customer Service | Manage Start/Stop
46926 | CORE-CUS-BPD003-E-007 | Custom BO Enter Processing algorithm will be developed on the Start process flow which will create a customer contact to trigger TVN letter for the existing customer at the service location soon after the submission of a B2B order | 2. Simple | Customer Service | Manage Start/Stop
46930 | CORE-CUS-BPD003-E-011 | A custom algorithm will be developed with a provision to supply entity name and characteristic type combinations as a configurable parameter | 2. Simple | Customer Service | Manage Start/Stop
46932 | CORE-CUS-BPD003-E-014.3 | A custom algorithm will be developed to trigger a to-do for a specific group (for both CECONY and O&R) if the response captured for BOPA question during the start process flow was ‘Yes’ Or Unknown/Unanswered. | 2. Simple | Customer Service | Manage Start/Stop
46060 | CORE-CUS-BPD005-E-007 | A custom batch job will be developed in CC&B to pick up the file from an FTP site with a known directory name and file structure on a weekly basis. A response file will be created and posted back to the FTP site, letting NJOIT know that the person in the file is a RECO customer | 2. Simple | Customer Service | Manage Products and Services
45834 | CORE-RBP-BPD006-E-001 | Custom Override proration Algorithm to perform correct proration of the charges as per the business requirement | 2. Simple | Rates, Billing, and Payments | Manage Rates
45835 | CORE-RBP-BPD006-E-002 | A custom Calculation Rule Eligibility Criteria - Field Algorithm will be developed and plugged on the eligibility criteria of Calculation Rule which is configured to calculate Billing and Payment Processing Charge | 2. Simple | Rates, Billing, and Payments | Manage Rates
45841 | CORE-RBP-BPD006-E-010 | A custom batch process will be developed to upload the monthly prices of regular bill factors with new effective dates available in the CSV file. Existing batch process (CM-NYPUP) of CC&B 2.6 which is NYISO Day ahead pricing Upload batch will be used to upload interval prices. | 2. Simple | Rates, Billing, and Payments | Manage Rates
45842 | CORE-RBP-BPD006-E-012 | Existing Custom calculation rule Derive Value algorithm (CM-LONGBILL) will be extended to validate the short bills also along with the long bills. It will generate bill segment error for long and short bills. | 2. Simple | Rates, Billing, and Payments | Manage Rates
45844 | CORE-RBP-BPD006-E-014 | A plug in driven batch will be developed with a custom algorithm. The batch will run on the first day of every year and calculate the rate reduction percentage for that calendar year for all the customers enrolled in BIR program. | 2. Simple | Rates, Billing, and Payments | Manage Rates
95975 | CORE-RBP-BPD009-E-008-02 | Usage Response from MDM – A new IWS will be created including a wrapper script will be developed to transform MDM response format to CCB response format | 2. Simple | Rates, Billing, and Payments | Manage Read and Billing Determinants
95976 | CORE-RBP-BPD009-E-008-03 | Usage response solution to retrieve read for bill print – Create Usage Request BO Enter Status Algorithm to a. retrieves the end read for prior frozen bill segment and update start reading in bill segment read details. b. retrieves the start read and end read from meter set/exchange/remove field activity and update start/end reading in bill segment. c. For First/Final Bill start read will be from Start/Stop Field Activity Read. No validation will be performed for the bill print reads. This will be done for KWH/CCF read only | 2. Simple | Rates, Billing, and Payments | Manage Read and Billing Determinants
95977 | CORE-RBP-BPD009-E-008-04 | Meter Reading View solution – A new query portal zone will be developed to provide a view of billed reads having the following parameters, i.e. Create Date/Time, Customer Name, Bill Segment Link, Meter #, Bill Period Start Date, Bill Period End Date, Unit of Measure, Start Read, End Read, Usage, Num of Days, Average Daily Usage, Degree Days. This portal can be added in the control central dashboard for gas and electric meters. | 2. Simple | Rates, Billing, and Payments | Manage Read and Billing Determinants
45849 | CORE-RBP-BPD009-E-003 | The Control Central 'Premise Information' zone would be extended to incorporate the additional display items | 2. Simple | Rates, Billing, and Payments | Manage Read and Billing Determinants
45850 | CORE-RBP-BPD009-E-004 | Out-of-the-box Hi Low check will be used for High Low Check and Demand load factor validation, For all other validation rules, calculation rule algorithm will be created to create bill segment To Do for VEE rules not existing in CC&B apply the validations that are not supported by CC&B OOB. To Do can be assigned to specific group based on message number override | 2. Simple | Rates, Billing, and Payments | Manage Read and Billing Determinants
45852 | CORE-RBP-BPD009-E-007 | A custom batch program will be developed to process a csv file and upload the service cycle schedule to CC&B | 2. Simple | Rates, Billing, and Payments | Manage Read and Billing Determinants
46888 | CORE-RBP-BPD010-E-003 | A custom batch process that finds cash-only customer on auto pay and stops the auto pay record. | 2. Simple | Rates, Billing, and Payments | Manage Payments
46889 | CORE-RBP-BPD010-E-004 | A custom change handler on the Payment Tender screen to enforce the business rules regarding online payment creation and payment tender modification. | 2. Simple | Rates, Billing, and Payments | Manage Payments
46893 | CORE-RBP-BPD010-E-008-1 | A custom SA Type payment freeze algorithm that would examine the SA type and do the following. * If recurring charge SA, transfer entire payoff balance to the Energy Share/Neighbor fund SA * If excess credit SA and payment FT = $1, transfer $1 balance to the Energy Share/Neighbor fund SA. * Both transfer adjustments will be created with an adjustment characteristic that will be a foreign key to the payment event that created the credit. This is used in case the payment is later cancelled. | 2. Simple | Rates, Billing, and Payments | Manage Payments
59903 | CORE-RBP-BPD010-E-008-2 | A custom customer class Payment Cancellation algorithm that will examine excess credit and recurring charge contribution SAs on the account. The algorithm validates the Pay Event Id against the ID held in characteristic value of transfer adjustment created by the Pay Freeze algorithm above. If the values match, the corresponding transfer adjustment created to credit money into Energy Share/Neighbor Fund account will be cancelled. | 2. Simple | Rates, Billing, and Payments | Manage Payments
59915 | CORE-RBP-BPD010-E-011 | A new audit algorithm on the Payment Event business object will be developed that will execute when the user presses the Save button. it will compare the entered ABA/account combination against the blacklist stored as a configuration. If found, display an error to the user that states the combination is invalid. | 2. Simple | Rates, Billing, and Payments | Manage Payments
45827 | CORE-FCC-BPD012-E-007 | Refund Method Algorithm - Use base logic to create adjustments, excess credit SA and logic to add Bill Message. | 2. Simple | Field, Credit, and Collections | Manage Deposits
46897 | CORE-FCC-BPD015-E-001-01 | Create emergency ticket utilizing scripting-based Q&A | 2. Simple | Field, Credit, and Collections | Manage Field Work
59926 | CORE-FCC-BPD015-E-001-03 | Create Case when LSE indicated using script | 2. Simple | Field, Credit, and Collections | Manage Field Work
59929 | CORE-FCC-BPD015-E-001-06 | Screen to preview call details before submit | 2. Simple | Field, Credit, and Collections | Manage Field Work
59930 | CORE-FCC-BPD015-E-001-07 | Search/update premise before submitting ticket | 2. Simple | Field, Credit, and Collections | Manage Field Work
46899 | CORE-FCC-BPD015-E-003 | Process Field Activities In Mass | 2. Simple | Field, Credit, and Collections | Manage Field Work
46900 | CORE-FCC-BPD015-E-004 | Field Activity Remark Action | 2. Simple | Field, Credit, and Collections | Manage Field Work
46901 | CORE-FCC-BPD015-E-005 | Create Log Entry for FA Schedule Date Update | 2. Simple | Field, Credit, and Collections | Manage Field Work
46906 | CORE-FCC-BPD015-E-010-01 | Apply, Waive Service Fees - On Completion | 2. Simple | Field, Credit, and Collections | Manage Field Work
59932 | CORE-FCC-BPD015-E-010-02 | Apply, Waive Service Fees - Inflight | 2. Simple | Field, Credit, and Collections | Manage Field Work
46908 | CORE-FCC-BPD015-E-012 | Search FA Using Multiple Criteria | 2. Simple | Field, Credit, and Collections | Manage Field Work
46909 | CORE-FCC-BPD015-E-013-01 | Create Follow Up To Do | 2. Simple | Field, Credit, and Collections | Manage Field Work
46911 | CORE-FCC-BPD015-E-013-02 | Send Email | 2. Simple | Field, Credit, and Collections | Manage Field Work
59934 | CORE-FCC-BPD015-E-015-02 | LTV, Posting | 2. Simple | Field, Credit, and Collections | Manage Field Work
59935 | CORE-FCC-BPD015-E-015-03 | FA update, monitoring | 2. Simple | Field, Credit, and Collections | Manage Field Work
59936 | CORE-FCC-BPD015-E-015-04 | Case Auto transition | 2. Simple | Field, Credit, and Collections | Manage Field Work
46085 | CORE-FCC-BPD016-E-001 | CC&B Alert for Cut For Non Pay status algorithm will identify customer account who are disconnected for non-payment and display alert on the customers’ account dashboard. | 2. Simple | Field, Credit, and Collections | Manage Collections
46086 | CORE-FCC-BPD016-E-002 | A custom collection criteria algorithm will be created in CC&B, to create collection process for different scenarios - 1)Customer with budget Plan 2)Customer with budget Plan and Payment Arrangement 3) Customer with Payment Arrangement debt | 2. Simple | Field, Credit, and Collections | Manage Collections
46088 | CORE-FCC-BPD016-E-004 | A custom collection condition algorithm will be developed based on Customer Class and CIS division, to identify LSE customers and trigger respective collection. | 2. Simple | Field, Credit, and Collections | Manage Collections
46089 | CORE-FCC-BPD016-E-005 | A custom LPC calculation algorithm will be created to include the logic for LPC Waiver. The base logic will be replicated in the custom algorithm with the addition of logic to check the Account and Account’s SA’s for canceled LPC adjustments. | 2. Simple | Field, Credit, and Collections | Manage Collections
46094 | CORE-FCC-BPD016-E-010 | To define 3 credit rating tiers in CC&B matching the requirement of CECONY and ORU, a custom configuration will be developed to define the thresholds | 2. Simple | Field, Credit, and Collections | Manage Collections
46095 | CORE-FCC-BPD016-E-011 | CECONY and ORU have a requirement to postpone or cancel ongoing collection and severance activity as a result of customers proving conditions that necessitate Medical Hardship, LSE, and other financial hardship processes | 2. Simple | Field, Credit, and Collections | Manage Collections
46096 | CORE-FCC-BPD016-E-012 | a custom collection condition algorithm to check whether the account needs to be put in is a special handling/key accounts collections path. | 2. Simple | Field, Credit, and Collections | Manage Collections
46098 | CORE-FCC-BPD016-E-014 | a custom severance algorithm to trigger the appropriate multi-dwelling severance template after checking the account characteristics and other eligibility criteria | 2. Simple | Field, Credit, and Collections | Manage Collections
46103 | CORE-FCC-BPD016-E-019 | custom severance event algorithm to generate customer contacts for all tenants and/or premises impacted by multi-dwelling or two family severance process. | 2. Simple | Field, Credit, and Collections | Manage Collections
46108 | CORE-FCC-BPD016-E-024 | A collection event algorithm will be developed to determine Deposit eligibility prior to triggering the custom ‘Deposit Review Method Algorithm’ found on the Account’s SA’s Deposit Class. Eligibility rules may differ between Residential and Non-Residential customers. Some of the eligibility criteria can be maintained on the Collection Event Algorithm. | 2. Simple | Field, Credit, and Collections | Manage Collections
59921 | CORE-FCC-BPD016-E-025-1 | A custom LPC Calculation Algorithm will be developed for Non Residential Payment Arrangement SA Types that are eligible for LPC. Base logic will be extended to do the following when calculating LPC: 1.Retrieve the payoff balance of the SA as of the process date, 2. Add any Over payment amount if one exists to calculate the Total PA SA Arrears Balance, 3. Calculate the Late Payment Charge (LPC) by multiplying the total calculated PA SA Arrears Balance by the LPC Percentage (defined using Bill Factor Code) and levy an adjustment on the SA in Step 1. | 2. Simple | Field, Credit, and Collections | Manage Collections
59922 | CORE-FCC-BPD016-E-025-2 | Code) and levy an adjustment on the SA in Step 1. Additionally, a custom LPC eligibility algorithm will be developed to determining whether a PA SA is active on the Account. If a PA SA is active, then determine if an LPC should be calculated for a Non Res Account by adding the account’s current balance to the PA SA Payoff Balance. If that amount is greater than $0, account is eligible for LPC. If the Non Res Account does not have a PA SA, then ensure current balance is greater than $0. | 2. Simple | Field, Credit, and Collections | Manage Collections
99196 | CORE-FCC-BPD016-E-028 | Solution Document for creating a custom Collection event Algorithm to generate a To Do Type for Summary Billing Accounts in the Collections Process. | 2. Simple | Field, Credit, and Collections | Manage Collections
46148 | CORE-FCC-BPD018-E-001 | Algorithm will be developed to create a custom alert on the account dashboard if broken PA is exists. | 2. Simple | Field, Credit, and Collections | Manage Collections
46149 | CORE-FCC-BPD018-E-002 | BPA script will be developed to offer Pay Plan based on the customer's account attributes and eligibility rules | 2. Simple | Field, Credit, and Collections | Manage Collections
46150 | CORE-FCC-BPD018-E-003 | Algorithm will be developed to create a Payment Arrangement Terms Notice. | 2. Simple | Field, Credit, and Collections | Manage Collections
46152 | CORE-FCC-BPD018-E-005 | User exit/change handler will be developed to limit the payment installment duration for Pay Plans based on OpCo specific rules. | 2. Simple | Field, Credit, and Collections | Manage Collections
59906 | CORE-FCC-BPD018-E-008-4 | Custom Collection Event Type Algorithm to Nominate SA to sever Algorithm ensures Deposit and or PA is broken prior to severance starting on the other service agreements | 2. Simple | Field, Credit, and Collections | Manage Collections
59907 | CORE-FCC-BPD018-E-008-5 | Severance Criteria Algorithm Will exist on the Deposit SA; if only Deposit debt exists then the algorithm will be used to determine if the deposit has installments. Used to trigger appropriate template for severance | 2. Simple | Field, Credit, and Collections | Manage Collections
130319 | CORE-RBP-BPD007-E-025-01 | custom Customer Class - Post Bill Completion Algorithm to automatically create transfer adjustment from subordinate account SAs to master account SA. Any balance in excess credit, deposit service agreement will be excluded from transfer to master SA. | 2. Simple | Rates, Billing, and Payments | Manage Billing
130326 | CORE-IT-BPD021-E-010 | Account Management Group configuration will be used for routing To Dos to different call centers based on the as-is rules for division. This will require additional customizations in start/transfer/new business process to populate AMG for new division accounts based on their boroughs and/or residential solar customer. | 2. Simple | IT | Manage System Mechanics
130348 | CORE-CUS-BPD003-E-038-46 | Carry forward Auto-Pay information during Service Transfer: Auto-pay (Direct payment plan) / eBill - Transfer Scenario - If the customer’s old premise was on direct payment it should automatically be transferred to the new premise. If there is no DPP on the prior account, there should be a prompt for DPP enrolment for the new premise. Likewise for eBill preference. | 2. Simple | Customer Service | Manage Start/Stop
130350 | CORE-CUS-BPD003-E-038-47 | Summary Panel for Start Process Flow Start Process Flow - Display information on the confirmation/Summary Panel. Base does not summarize the start information on a single page. | 2. Simple | Customer Service | Manage Start/Stop
130352 | CORE-CUS-BPD003-E-038-48 | Summary Panel for Transfer Process Flow Transfer Process Flow - Display information on the confirmation/Summary Panel. Base does not summarize the Start/Stop information on a single page. | 2. Simple | Customer Service | Manage Start/Stop
130353 | CORE-CUS-BPD003-E-038-49 | Display 'Start Type' dropdown Start Process Flow - DA Extension (Or POP-up) will be required to inject following static drop down for CSR to select,- Type of Start (RPO, Religious, Residential or Non-Res) Start or Transfer Process Flow - DA Extension - will be required to detect dynamically and inject following custom fields on the screen if the criteria is met. - If there is inactive consumption at selected premise, is the customer willing to accept the responsibility? - If there are credit arrears at the selected premise, is the customer willing to accept the responsibility? | 2. Simple | Customer Service | Manage Start/Stop
130374 | CORE-CUS-BPD003-E-038-53 | Allow only CCG rep to resume work on the forwarded requests to the CCG Group NYPA / CCG Account specific logic (applicable for all three process flows - Start, Stop & Transfer) - Only CCG personal should be allowed to resume the work on the requests which got routed to the CCG group due to CCG/NYPA validation during start/stop/transfer. If regular CSR attempts to search and open a previously forwarded request, he should not be allowed to resume further. Also, system should not create a duplicate to-do in that case. | 2. Simple | Customer Service | Manage Start/Stop
130375 | CORE-CUS-BPD003-E-038-54 | Display & capture NYPA/CCG specific fields NYPA / CCG Account specific logic (applicable for all three process flows - Start, Stop & Transfer) - Following additional fields will need to be captured while handling a CCG or NYPA account during the Start, - Corp Code (as Account Char) - Agency Code (as Account Char) - Account Management Group - NYPA (this is a Customer Class) - PRES Code (as SA Char) - Tax Exemption (as Account Char) | 2. Simple | Customer Service | Manage Start/Stop
130376 | CORE-CUS-BPD003-E-038-55 | Allow only LSE rep to resume work on the forwarded requests to the LSE Group NYPA / CCG Account specific logic (applicable for all three process flows - Start, Stop & Transfer) - Only CCG personal should be allowed to resume the work on the requests which got routed to the CCG group due to CCG/NYPA validation during start/stop/transfer. If regular CSR attempts to search and open a previously forwarded request, he should not be allowed to resume further. Also, system should not create a duplicate to-do in that case. | 2. Simple | Customer Service | Manage Start/Stop
130379 | CORE-CUS-BPD003-E-038-57 | Stop Process Flow - Successor Script with Owner Fields Stop Process Flow - Display Successor script with Owner Address fields. | 2. Simple | Customer Service | Manage Start/Stop
130384 | CORE-CUS-BPD003-E-038-59 | Transfer Process Flow - Display existing person information for CSR verification Transfer Process Flow - Person Record Information for existing customer should be displayed to the CSR so he can view and verify customer information. Base does not display existing customer information anywhere on the transfer process flow. | 2. Simple | Customer Service | Manage Start/Stop
130387 | CORE-CUS-BPD003-E-038-61 | Custom Scripts Base functionality provides a simple 'Yes/No' check-box to capture Paperless Billing preference/ AutoPay (Direct payment plan) etc. Customization will be required to display the ConEd specific texts so that CSR can view and read to the customer. | 2. Simple | Customer Service | Manage Start/Stop
130389 | CORE-CUS-BPD003-E-038-62 | Panel changes on Transfer Process Flow Introduce custom panel to capture customer information for Start before going to the Stop screen. | 2. Simple | Customer Service | Manage Start/Stop
130393 | CORE-CUS-BPD003-E-038-64 | Create 3rd Party CASE Create 3rd party CASE if the customer provides TP details during Concern Referral at the time of Start/Transfer. Capture Third Party address details as attributes on the generated CASE. | 2. Simple | Customer Service | Manage Start/Stop
130394 | CORE-CUS-BPD003-E-038-65 | Create LSE CASE Create LSE CASE if the customer indicates LSE referral at the time of Start/Transfer, capture life support equipment as Case characteristic. | 2. Simple | Customer Service | Manage Start/Stop
130396 | CORE-CUS-BPD003-E-038-66 | Create EDF SA if premise has EDF equipment Create EDF Service Agreements automatically if EDF equipment is present at the premise. | 2. Simple | Customer Service | Manage Start/Stop
130397 | CORE-CUS-BPD003-E-038-67 | Transfer Process Flow - Auto transfer deposit SA Update deposit SA during transfer service requesT | 2. Simple | Customer Service | Manage Start/Stop
130399 | CORE-CUS-BPD003-E-038-68 | Create scenario based To-Do's for Start/Stop/Transfer | 2. Simple | Customer Service | Manage Start/Stop
137229 | CORE-RBP-BPD006-015-03 | CSR to create a Rate Change Case in CC&B which will create a To-Do for the required business user to perform the rate change process using a custom screen. Business user will enter all the required information in custom screen like new PSC code, CSC and TOD code for CECONY, CIMS Rate code for ORU, etc.. and the backend script will map the correct CC&B rate schedule as per the selected codes and add it on the service agreement of the account after performing the required business validations. This involves Custom Rate Change UI Map and Case lifecycle algorithms. | 2. Simple | Rates, Billing, and Payments | Manage Rates
137230 | CORE-RBP-BPD006-015-04 | CSR to create a Rate Change Case in CC&B which will create a To-Do for the required business user to perform the rate change process using a custom screen. Business user will enter all the required information in custom screen like new PSC code, CSC and TOD code for CECONY, CIMS Rate code for ORU, etc.. and the backend script will map the correct CC&B rate schedule as per the selected codes and add it on the service agreement of the account after performing the required business validations. This involves Custom Rate Change UI Map and Case lifecycle algorithms. | 2. Simple | Rates, Billing, and Payments | Manage Rates
137234 | CORE-FCC-BPD016-E-029-02 | The Replevin case that will be used in CC&B to initiate the Replevin process, generate appropriate notices to the customers, prompt field work, and maintain the replevin lifecycle and all relevant information. The remaining analysis with the Credit, Field, integration, Functional and law department teams has been completed to allow us to finalize the case statuses in CC&B and determine the data that needs to be passed to the Replevin Tracking System (RTS) and received back from RTS. This addresses Open Item BPD016-003. The required Replevin Case will need multiple Case Algorithms to meet the regulatory and ConEd requirements - Enter Status Algorithms to - Generate To Dos Evaluate Eligibility for Replevin Generate required notices - CAZ, PHL Generate Adjustments Hold FAs from being dispatched Monitor Algorithms - Determine if Account is still eligible for Replevin and transition to the appropriate status Field Activity BO Enter Status Algorithms to - Determine if Street Cut or Replevin should be triggered Update all Collector Docs with disconnect information if building is street cut | 2. Simple | Field, Credit, and Collections | Manage Collections
137235 | CORE-FCC-BPD016-E-029-03 | The Replevin case that will be used in CC&B to initiate the Replevin process, generate appropriate notices to the customers, prompt field work, and maintain the replevin lifecycle and all relevant information. The remaining analysis with the Credit, Field, integration, Functional and law department teams has been completed to allow us to finalize the case statuses in CC&B and determine the data that needs to be passed to the Replevin Tracking System (RTS) and received back from RTS. This addresses Open Item BPD016-003. The required Replevin Case will need multiple Case Algorithms to meet the regulatory and ConEd requirements - Enter Status Algorithms to - Generate To Dos Evaluate Eligibility for Replevin Generate required notices - CAZ, PHL Generate Adjustments Hold FAs from being dispatched Monitor Algorithms - Determine if Account is still eligible for Replevin and transition to the appropriate status Field Activity BO Enter Status Algorithms to - Determine if Street Cut or Replevin should be triggered Update all Collector Docs with disconnect information if building is street cut | 2. Simple | Field, Credit, and Collections | Manage Collections
137236 | CORE-FCC-BPD016-E-029-04 | The Replevin case that will be used in CC&B to initiate the Replevin process, generate appropriate notices to the customers, prompt field work, and maintain the replevin lifecycle and all relevant information. The remaining analysis with the Credit, Field, integration, Functional and law department teams has been completed to allow us to finalize the case statuses in CC&B and determine the data that needs to be passed to the Replevin Tracking System (RTS) and received back from RTS. This addresses Open Item BPD016-003. The required Replevin Case will need multiple Case Algorithms to meet the regulatory and ConEd requirements - Enter Status Algorithms to - Generate To Dos Evaluate Eligibility for Replevin Generate required notices - CAZ, PHL Generate Adjustments Hold FAs from being dispatched Monitor Algorithms - Determine if Account is still eligible for Replevin and transition to the appropriate status Field Activity BO Enter Status Algorithms to - Determine if Street Cut or Replevin should be triggered Update all Collector Docs with disconnect information if building is street cut | 2. Simple | Field, Credit, and Collections | Manage Collections
137237 | CORE-FCC-BPD016-E-029-05 | The Replevin case that will be used in CC&B to initiate the Replevin process, generate appropriate notices to the customers, prompt field work, and maintain the replevin lifecycle and all relevant information. The remaining analysis with the Credit, Field, integration, Functional and law department teams has been completed to allow us to finalize the case statuses in CC&B and determine the data that needs to be passed to the Replevin Tracking System (RTS) and received back from RTS. This addresses Open Item BPD016-003. The required Replevin Case will need multiple Case Algorithms to meet the regulatory and ConEd requirements - Enter Status Algorithms to - Generate To Dos Evaluate Eligibility for Replevin Generate required notices - CAZ, PHL Generate Adjustments Hold FAs from being dispatched Monitor Algorithms - Determine if Account is still eligible for Replevin and transition to the appropriate status Field Activity BO Enter Status Algorithms to - Determine if Street Cut or Replevin should be triggered Update all Collector Docs with disconnect information if building is street cut | 2. Simple | Field, Credit, and Collections | Manage Collections
137238 | CORE-FCC-BPD016-E-029-06 | The Replevin case that will be used in CC&B to initiate the Replevin process, generate appropriate notices to the customers, prompt field work, and maintain the replevin lifecycle and all relevant information. The remaining analysis with the Credit, Field, integration, Functional and law department teams has been completed to allow us to finalize the case statuses in CC&B and determine the data that needs to be passed to the Replevin Tracking System (RTS) and received back from RTS. This addresses Open Item BPD016-003. The required Replevin Case will need multiple Case Algorithms to meet the regulatory and ConEd requirements - Enter Status Algorithms to - Generate To Dos Evaluate Eligibility for Replevin Generate required notices - CAZ, PHL Generate Adjustments Hold FAs from being dispatched Monitor Algorithms - Determine if Account is still eligible for Replevin and transition to the appropriate status Field Activity BO Enter Status Algorithms to - Determine if Street Cut or Replevin should be triggered Update all Collector Docs with disconnect information if building is street cut | 2. Simple | Field, Credit, and Collections | Manage Collections
137239 | CORE-FCC-BPD016-E-029-07 | The Replevin case that will be used in CC&B to initiate the Replevin process, generate appropriate notices to the customers, prompt field work, and maintain the replevin lifecycle and all relevant information. The remaining analysis with the Credit, Field, integration, Functional and law department teams has been completed to allow us to finalize the case statuses in CC&B and determine the data that needs to be passed to the Replevin Tracking System (RTS) and received back from RTS. This addresses Open Item BPD016-003. The required Replevin Case will need multiple Case Algorithms to meet the regulatory and ConEd requirements - Enter Status Algorithms to - Generate To Dos Evaluate Eligibility for Replevin Generate required notices - CAZ, PHL Generate Adjustments Hold FAs from being dispatched Monitor Algorithms - Determine if Account is still eligible for Replevin and transition to the appropriate status Field Activity BO Enter Status Algorithms to - Determine if Street Cut or Replevin should be triggered Update all Collector Docs with disconnect information if building is street cut | 2. Simple | Field, Credit, and Collections | Manage Collections
137240 | CORE-FCC-BPD016-E-029-08 | The Replevin case that will be used in CC&B to initiate the Replevin process, generate appropriate notices to the customers, prompt field work, and maintain the replevin lifecycle and all relevant information. The remaining analysis with the Credit, Field, integration, Functional and law department teams has been completed to allow us to finalize the case statuses in CC&B and determine the data that needs to be passed to the Replevin Tracking System (RTS) and received back from RTS. This addresses Open Item BPD016-003. The required Replevin Case will need multiple Case Algorithms to meet the regulatory and ConEd requirements - Enter Status Algorithms to - Generate To Dos Evaluate Eligibility for Replevin Generate required notices - CAZ, PHL Generate Adjustments Hold FAs from being dispatched Monitor Algorithms - Determine if Account is still eligible for Replevin and transition to the appropriate status Field Activity BO Enter Status Algorithms to - Determine if Street Cut or Replevin should be triggered Update all Collector Docs with disconnect information if building is street cut | 2. Simple | Field, Credit, and Collections | Manage Collections
170413 | CORE-RBP-BPD009-E-009 | Billed Read View | 2. Simple | Rates, Billing, and Payments | Manage Read and Billing Determinants
170436 | CORE-IT-BPD021-013-01 | Supervisor Out of Office To Do assignment process | 2. Simple | IT | Manage System Mechanics
170438 | CORE-IT-BPD021-013-02 | Supervisor Out of Office To Do assignment process | 2. Simple | IT | Manage System Mechanics
170439 | CORE-IT-BPD021-013-03 | Supervisor Out of Office To Do assignment process | 2. Simple | IT | Manage System Mechanics
170979 | CORE-RBP-BPD007-E-026-02 | NYPA Billing | 2. Simple | Rates, Billing, and Payments | Manage Billing
171006 | CORE-RBP-BPD007-E-027-02 | ORU MHP SHR Billing | 2. Simple | Rates, Billing, and Payments | Manage Billing
172691 | CORE-RBP-BPD007-E-030 | As part of the Case lifecycle, a screen will allow for the retrieval of an historical period of consumption and demand between two dates to calculate the theft of service. The user will be able to export the results as a spreadsheet for analysis. Once the user completes the analysis, the user will choose the calculation method option the user would like to use in a spreadsheet. The output of the calculation will be presented to the user as an Consumption to bill amount so that it can be used for the Base Rate check functionality in CC&B. The Base screens will be used to manually apply the total billed amount as an adjustment on the service agreement. | 2. Simple | Rates, Billing, and Payments | Manage Billing
59901 | CORE-TPI-BPD019-E-001-10 | Monitor Off Cycle Meter Read | 2. Simple | Third Party Interactions | Manage Retail Choice
176548 | CORE-CUS-BPD001-E-013-01 | alert algorithms to provide customer information, ESCO, Meter and Field Activity, payment, high bill, rate, IVR | 2. Simple | Customer Service | Manage Account Setup
176549 | CORE-CUS-BPD001-E-013-02 | alert algorithms to provide customer information, ESCO, Meter and Field Activity, payment, high bill, rate, IVR | 2. Simple | Customer Service | Manage Account Setup
176550 | CORE-CUS-BPD001-E-013-03 | alert algorithms to provide customer information, ESCO, Meter and Field Activity, payment, high bill, rate, IVR | 2. Simple | Customer Service | Manage Account Setup
176551 | CORE-CUS-BPD001-E-013-04 | alert algorithms to provide customer information, ESCO, Meter and Field Activity, payment, high bill, rate, IVR | 2. Simple | Customer Service | Manage Account Setup
176552 | CORE-CUS-BPD001-E-013-05 | alert algorithms to provide customer information, ESCO, Meter and Field Activity, payment, high bill, rate, IVR | 2. Simple | Customer Service | Manage Account Setup
176553 | CORE-CUS-BPD001-E-013-06 | alert algorithms to provide customer information, ESCO, Meter and Field Activity, payment, high bill, rate, IVR | 2. Simple | Customer Service | Manage Account Setup
176555 | CORE-CUS-BPD001-E-013-07 | alert algorithms to provide customer information, ESCO, Meter and Field Activity, payment, high bill, rate, IVR | 2. Simple | Customer Service | Manage Account Setup
176556 | CORE-CUS-BPD001-E-013-08 | alert algorithms to provide customer information, ESCO, Meter and Field Activity, payment, high bill, rate, IVR | 2. Simple | Customer Service | Manage Account Setup
176557 | CORE-CUS-BPD001-E-013-09 | alert algorithms to provide customer information, ESCO, Meter and Field Activity, payment, high bill, rate, IVR | 2. Simple | Customer Service | Manage Account Setup
176558 | CORE-CUS-BPD001-E-013-10 | alert algorithms to provide customer information, ESCO, Meter and Field Activity, payment, high bill, rate, IVR | 2. Simple | Customer Service | Manage Account Setup
176559 | CORE-CUS-BPD001-E-013-11 | alert algorithms to provide customer information, ESCO, Meter and Field Activity, payment, high bill, rate, IVR | 2. Simple | Customer Service | Manage Account Setup
176563 | CORE-RBP-BPD011-E-010 | A Case Lifecycle will be configured to initiate Stop request to AP and receive the response from AP. Custom Case Enter Status Algorithm to cancel the appropriate adjustment when Stop Request is Successful. Notification will need to be sent back to AP to cancel the payment (invoice). Case Enter Status Algorithm to generate To-Do when Stop Request is Successful / Unsuccessful | 2. Simple | Rates, Billing, and Payments | Manage Remittances
176568 | CORE-RBP-BPD010-E-020 | Develop the BPA Script to launch the Print Dialog box from Payment Event Page. Develop the UI Map to reference the BPA Script and the file name and path of Javascript printer library installed on Printer Server. | 2. Simple | Rates, Billing, and Payments | Manage Payments
176572 | CORE-CUS-BPD003-E-048 | Develop customer request completion enter processing algorithm to create a to do to remind the csr for summary billing enrollment when customer opted for summary billing during start conversation. | 2. Simple | Customer Service | Manage Start/Stop
176577 | CORE-RBP-BPD007-E-031 | New data elements user, phone number, email need to be captured as part of value stack CDG project information. This information will be used as information to be printed on bill. | 2. Simple | Rates, Billing, and Payments | Manage Billing
206995 | CORE-RBP-BPD007-E-033-01 | A batch job to pick all accounts eligible for billing on a day based on bill schedules.a. To create Info usage billing request to MDM | 2. Simple | Rates, Billing, and Payments | Manage Billing
207000 | CORE-RBP-BPD007-E-033-02 | SA Type – Bill Eligibility Algorithm : This algorithm will check the Service agreement Type is one of the SA Type configured in Off System Master Configuration and triggered from bath, it would skip from billing. | 2. Simple | Rates, Billing, and Payments | Manage Billing
207001 | CORE-RBP-BPD007-E-033-03 | Enter processing Algorithm – Read the usage response and post the bill determinant on to the custom bill determinant table for further processing during billing. | 2. Simple | Rates, Billing, and Payments | Manage Billing
207002 | CORE-RBP-BPD007-E-033-04 | Enter processing Algorithm – Create Bill Control Service Task to perform validation and billing. | 2. Simple | Rates, Billing, and Payments | Manage Billing
215082 | CORE-TPI-BPD019-E-007 | Develop a batch process to need to identify the inactive ESCOs that has no enroll/billing activity for 90days from current run. A TODO must be created for each such entry, so that business can analyze them to take necessary action. | 2. Simple | Third Party Interactions | Manage Retail Choice
220907 | CORE-RBP-BPD007-E-035 | Key Points Discussed: • When CC&B system goes live in May 2023, AMI roll-out would have completed. • At that point of time going forward CC&B system only needs to look at AMI commissioned flag on the service point to identify if the meter is AMI or not and charge monthly meter reading fee if the meter if Non-AMI. • If a customer opts out after CC&B go-live, the Opt out indicator on the meter/service point will be used to track the Opt out progress only and the Opt out indicator will be set to “Opt Out Pending” . After the field activity is completed and the meter is switched to Non AMI, opt out indicator will be updated to “Opt Out Completed” and the AMI commissioned flag will be set to “Legacy Commissioned” • Monthly reading fee needs to be charged based on AMI commissioned flag only • Monthly fee is at the account level and needs to be charged only once at the account level irrespective of the number of meters opted out • For bi-monthly read customers (opted out), system needs to charge $9.50 for the month the meter is not read and for the month the meter is supposed to be read, system should check if the meter read is fielded or not (attempted or not).. if the meter reading is not attempted, system should not charge $9.50 for that month. Prasant to check if the CORE team already have reason codes documented to indicate the meter read attempted or not.. Send the list to Eugene for final confirmation. • There are scenarios where account is coded not to have any charged levied in CSS system.. for those accounts, CC&B system should not also charge meter reading fee.. Prasant to check if this logic is applicable in CC&B or not. • Inactive accounts should not have meter reading fees levied. CC&B should take care of this automatically. • A new PCR will be created to handle the above changes as part of CORE program this PCR also includes changes to functional, integration and conversion. please see the attached document | 2. Simple | Rates, Billing, and Payments | Manage Billing
59900 | CORE-TPI-BPD019-E-001-09 | Seek Meter Read on Off Cycle date | 2. Simple | Third Party Interactions | Manage Retail Choice
59899 | CORE-TPI-BPD019-E-001-08 | Account Number Change | 2. Simple | Third Party Interactions | Manage Retail Choice
59898 | CORE-TPI-BPD019-E-001-07 | Customer Letter Notification - 14513 | 2. Simple | Third Party Interactions | Manage Retail Choice
97603 | CORE-RBP-BPD010-E-018 | A existing custom UI solution will be enhanced for entering future ACH payments rather than an actual payment posted that day, entering multiple payment schedule date and a payment amount for each date, entering single bank detail for all future payments. A custom Control Central alert algorithm will display for pending service tasks created by this solution to provide visibility to the CSR for future scheduled payments. | 2. Simple | Rates, Billing, and Payments | Manage Payments
124265 | CORE-CUS-BPD002-E-011 | R52 Form | 2. Simple | Customer Service | Manage Contact
124271 | CORE-RBP-BPD006-E-017-001 | Price Proration (>35 Days) | 2. Simple | Rates, Billing, and Payments | Manage Rates
124272 | CORE-RBP-BPD006-E-017-002 | Set Characteristic Collection Values | 2. Simple | Rates, Billing, and Payments | Manage Rates
124273 | CORE-RBP-BPD006-E-017-003 | Set Characteristic Collection Values (using Master Configuration mapping) | 2. Simple | Rates, Billing, and Payments | Manage Rates
124274 | CORE-RBP-BPD006-E-017-004 | Calculate Final Therm Conversion Factor | 2. Simple | Rates, Billing, and Payments | Manage Rates
124275 | CORE-RBP-BPD006-E-017-005 | Calculate AC Seasonal Days | 2. Simple | Rates, Billing, and Payments | Manage Rates
124276 | CORE-RBP-BPD006-E-017-006 | Derive Value using SQI | 2. Simple | Rates, Billing, and Payments | Manage Rates
124277 | CORE-RBP-BPD006-E-017-007 | O&R Ratchet Demand | 2. Simple | Rates, Billing, and Payments | Manage Rates
124286 | CORE-CUS-BPD001-E-011-001 | Account Change Handler Complexity: Low | 2. Simple | Customer Service | Manage Account Setup
124290 | CORE-CUS-BPD001-E-010-001 | Installation Option – Person Name Format Algorithm | 2. Simple | Customer Service | Manage Account Setup
124291 | CORE-CUS-BPD001-E-010-002 | Custom Characteristic Type – Adhoc Validation | 2. Simple | Customer Service | Manage Account Setup
124292 | CORE-CUS-BPD001-E-010-003 | Case Type - Enter Processing Algorithm | 2. Simple | Customer Service | Manage Account Setup
124353 | CORE-RBP-BPD010-E-017 | Autopay Date Security | 2. Simple | Rates, Billing, and Payments | Manage Payments
124444 | CORE-RBP-BPD010-E-023 | LI Protect from Collections | 2. Simple | Rates, Billing, and Payments | Manage Payments
95985 | CORE-RBP-BPD007-E-023 | Custom algorithm will be developed as part of Cancel/Rebill BO to check for thresholds of difference amount for different customer class and stop auto pay on the account if the dollar difference amount is higher than threshold configured. System will also create a bill message to inform the customer. | 2. Simple | Rates, Billing, and Payments | Manage Billing
95988 | CORE-FCC-BPD012-E-008 | A custom solution will be created for users to create an adjustment to completely or partially waive a deposit. A Deposit Waiver Adjustment Type will be configured for users to reduce the Deposit’s Current Balance. If the Deposit is to be completely waived, then a user will generate an adjustment equal to the Current Balance of a Deposit. If the deposit is to be partially reduced, then the Adjustment will be generated equal to that partial amount. The adjustment will go through the DOA approval process and appropriate steps will be executed based on approval and rejection. | 2. Simple | Field, Credit, and Collections | Manage Deposits
59897 | CORE-TPI-BPD019-E-001-06 | Posting ESCO Credit/Debit Adjustment change | 2. Simple | Third Party Interactions | Manage Retail Choice
97599 | CORE-RBP-BPD010-E-016 | A plug-in upload batch process to read the input file and create required adjustments of specified adjustment types directly on the customer account. | 2. Simple | Rates, Billing, and Payments | Manage Payments
67029 | CORE-CUS-BPD003-E-046 | An SA Stop Algorithm will be developed to automatically create a meter exchange Field Activity (FA) when AMI opt out customer stopped the service. | 2. Simple | Customer Service | Manage Start/Stop
69340 | CORE-FCC-BPD015-E-011-06 | Creating a backup Print navigation option for manual printing (SD 11) | 2. Simple | Field, Credit, and Collections | Manage Field Work
69341 | CORE-FCC-BPD015-E-011-07 | Java service for real time printing to the desired printer for ORU ECS, CECONY Gas Central (SD 11) | 2. Simple | Field, Credit, and Collections | Manage Field Work
69343 | CORE-FCC-BPD015-E-014-02 | Exchange meter as a part of Meter Investigation FA (R84), Referral or other similar type (SD 14) | 2. Simple | Field, Credit, and Collections | Manage Field Work
69344 | CORE-FCC-BPD015-E-014-03 | Perform FA completion not in line with FA steps (SD 14) | 2. Simple | Field, Credit, and Collections | Manage Field Work
69346 | CORE-FCC-BPD015-E-014-05 | Exchange/Remove FA completion coming to CC&B from WMS (or another external field system) which was not created from CC&B) (SD 14) | 2. Simple | Field, Credit, and Collections | Manage Field Work
99199 | CORE-RBP-BPD006-E-016 | Solution Document for creating or cancelling adjustments for billing credits. | 2. Simple | Rates, Billing, and Payments | Manage Rates
99202 | CORE-CUS-BPD005-E-008 | To develop custom logic for enrolling and de-enrolling Customers from Budget. Part of Open Item OCI-BPD005-013 For placing ORU-NY customers on levelized (budget) billing solution. | 2. Simple | Customer Service | Manage Products and Services
46937 | CORE-CUS-BPD003-E-043-1 | An alert will be created for the CSR when new tenant is starting service within 7 days of the start date for the landlord service. This will alert the CSR to ask for the Lease Date so as to align the New Tenant start date with the old Tenant’s move out date. | 2. Simple | Customer Service | Manage Start/Stop
46061 | CORE-RBP-BPD007-E-001 | A custom bill completion algorithm will be developed to perform annual reconciliation of the minimum charge. It will also create an automatic To-Do for the business users for re-specification of annual allocation | 2. Simple | Rates, Billing, and Payments | Manage Billing
46066 | CORE-RBP-BPD007-E-004 | custom algorithms will be developed - * Custom SA type FT Freeze algorithm will be developed to stop the NYSERDA Loan SA when all loan installments have been billed. * Custom Bill Eligibility algorithm will be developed to stop remaining loan amount to appear on final bill of the account when the account stops service before completing his loan tenure. | 2. Simple | Rates, Billing, and Payments | Manage Billing
46068 | CORE-RBP-BPD007-E-008 | A custom Calculation Rule-Derive Value algorithm will be developed to segregate and derive LT and HT consumptions for Mixed Tension billing. | 2. Simple | Rates, Billing, and Payments | Manage Billing
46070 | CORE-RBP-BPD007-E-010 | A custom SA Type Bill Eligibility algorithm will be developed to skip billing for service having “HOLD” characteristic on service agreement of the account. | 2. Simple | Rates, Billing, and Payments | Manage Billing
46074 | CORE-RBP-BPD007-E-014 | A custom SA Type Pre Bill Eligibility algorithm will be developed to delete the bill segments in error and to create bill message and To-Do entry | 2. Simple | Rates, Billing, and Payments | Manage Billing
46077 | CORE-RBP-BPD007-E-017-1 | A custom batch will be developed to read the Initial, Interim or the Final file for Outage Credit customers and initiate the case for outage credit. | 2. Simple | Rates, Billing, and Payments | Manage Billing
46078 | CORE-RBP-BPD007-E-018-1 | A BO based user interface would be given for user to enter the daily readings 1. Reference Date 2. Maximum Temp, Minimum Temp 3. 24 reading of dry bulb temp 4. 24 reading s of Dew point | 2. Simple | Rates, Billing, and Payments | Manage Billing
58602 | CORE-CUS-BPD003-E-043-2 | Create a monitor algorithm on the stop process flow. This should monitor for a vacant premise under LOFLL program that is entering into the 8th day of vacancy to start the service under Landlord Account and send the Confirmation Notice(Notification stating you have been put on record for the account) to the landlord. Technical Note - Need to check this against the start/stop process flow. | 2. Simple | Customer Service | Manage Start/Stop
58603 | CORE-CUS-BPD003-E-043-3 | Create a monitor algorithm that will monitor for a BOPA reply from DCX and creates a To Do if it is is Yes. After X days from Landlord Turn-On Date, if no response then default to Yes, and create To Do | 2. Simple | Customer Service | Manage Start/Stop
58605 | CORE-CUS-BPD003-E-044-1 | At time of Start Service, Start Process Flow will automatically create a “Turn On” Field Activity (FA) when system says Hot and customer says it’s Cold. The FA will be scheduled right away and dispatched appropriately only for Same day Order | 2. Simple | Customer Service | Manage Start/Stop
58615 | CORE-CUS-BPD003-E-038-9 | Start Service - Premise Information - Average Service Bill Amount on the Premise (script and display). ConEd specif custom Premise AlertThis is specific alert, it calculates Average Bill Amount at the selected premise, not covered in any other FSD | 2. Simple | Customer Service | Manage Start/Stop
58624 | CORE-CUS-BPD003-E-038-18 | Start Service - Service Information - Auto identification/assignment of billing rate. While previous customer rates are getting selected during start/transfer, default rates are not getting applied. Few Examples: (1) if start option is not present on the previous customer SA (2) falling back from customer to landlord (3) Start type changes (Commercial customer is moving in at location where the existing customer is residential) etc. | 2. Simple | Customer Service | Manage Start/Stop
58637 | CORE-CUS-BPD003-E-038-31 | Start Service -BO Algorithm - Denial Letter generation | 2. Simple | Customer Service | Manage Start/Stop
59542 | CORE-CUS-BPD003-E-038-14 | Start Service - New Customer - POS ID Check Script BPA | 2. Simple | Customer Service | Manage Start/Stop
59585 | CORE-CUS-BPD003-E-044-2 | For future dated Order, on schedule date, custom batch job will cancel the Meter Read FA and create the Turn On FA when customer informed meter status is COLD but CCB identified as HOT | 2. Simple | Customer Service | Manage Start/Stop
59586 | CORE-RBP-BPD007-E-017-2 | Case Type - Enter Status algorithm will be developed which will do the following: Add the Seg Code SEGC98 as SA Chracteristics , LPC’s are suspended on the account , Field credit action including TONP is suspended , No access charges are suspended on the account | 2. Simple | Rates, Billing, and Payments | Manage Billing
59587 | CORE-RBP-BPD007-E-017-3 | Two Calc Rule - Derive value algorithm will be used o One to retrieve the customer charge from Calculation Rule by using characteristic on Calculation Rule o Another one to retrieve the number of days from the adjustment.Based on the No. of Days outage derived, prorate the customer charge and create outage credit adjustment of the same amount on the SA. | 2. Simple | Rates, Billing, and Payments | Manage Billing
59588 | CORE-RBP-BPD007-E-018-2 | Validation (BO validation Alg) · No Data exists with same reference date · The difference between two consecutive dry bulb or dew point temp cannot be more than 9 · Same hours of current day and prev day dry bulb or dew point cannot have more than 20 · Hourly dry bulb temp cannot be more than maximum temp and minimum temp | 2. Simple | Rates, Billing, and Payments | Manage Billing
59591 | CORE-RBP-BPD007-E-018-5 | Batch Job -2 : generate Data files | 2. Simple | Rates, Billing, and Payments | Manage Billing
59596 | CORE-RBP-BPD007-E-020-13 | Enter Processing Algorithm - When the status is moved from Active to Allocate, this algorithm will add a new Subscription Plan Result business object for the month or the on demand request for actual allocation | 2. Simple | Rates, Billing, and Payments | Manage Billing
59597 | CORE-RBP-BPD007-E-020-14 | Enter Processing Algorithm - In case of any error during allocation process, the plan will be moved error and To Do will be created | 2. Simple | Rates, Billing, and Payments | Manage Billing
59599 | CORE-RBP-BPD007-E-020-16 | Enter Processing Algorithm - Move status to Volumetric Allocation or Monetary Allocation based on Project Type and Compensation Type | 2. Simple | Rates, Billing, and Payments | Manage Billing
59605 | CORE-RBP-BPD007-E-020-21 | SA Stop Algorithm - When Host SA Stops, if the account has net metering, it will move the allocation BO status to Close | 2. Simple | Rates, Billing, and Payments | Manage Billing
59608 | CORE-RBP-BPD007-E-020-3 | Enter Processing Algorithm - Create host bank SA with net Metering SA relationship type (If Monetary) | 2. Simple | Rates, Billing, and Payments | Manage Billing
59609 | CORE-RBP-BPD007-E-020-4 | Monitor Algorithm - Monitor the anniversary date of project and move the status to ‘True Up’ and Monitor the End of Service of project and move the status to “Cancel’ | 2. Simple | Rates, Billing, and Payments | Manage Billing
59610 | CORE-RBP-BPD007-E-020-5 | Monitor Algorithm - Monitor the Host is not billed for predefined period of time, create a To Do to notify the user Up’ | 2. Simple | Rates, Billing, and Payments | Manage Billing
59612 | CORE-RBP-BPD007-E-020-7 | Enter Processing Algorithm - At the end of the term of service, customers will forfeit any remaining monetary credit | 2. Simple | Rates, Billing, and Payments | Manage Billing
59614 | CORE-RBP-BPD007-E-020-9 | Enter Processing Algorithm - Validation if any, for the new host during transfer process | 2. Simple | Rates, Billing, and Payments | Manage Billing
59616 | CORE-RBP-BPD007-E-021-3 | System automatically determines if approval is required and invoke approval process Provide capability for approvers to come in and view details and approve/reject | 2. Simple | Rates, Billing, and Payments | Manage Billing
59621 | CORE-RBP-BPD007-E-021-8 | Create a custom screen to allow user to input details for OPI calculation and system automatically calculate OPI. User needs to manually create the adjustment for OPI amount calculated by custom screen | 2. Simple | Rates, Billing, and Payments | Manage Billing
59894 | CORE-TPI-BPD019-E-001-03 | Bill Option Status | 2. Simple | Third Party Interactions | Manage Retail Choice
59895 | CORE-TPI-BPD019-E-001-04 | Commodity Price, Tax Rate, Customer Charge | 2. Simple | Third Party Interactions | Manage Retail Choice
59896 | CORE-TPI-BPD019-E-001-05 | Tax Exempt Rate | 2. Simple | Third Party Interactions | Manage Retail Choice
45806 | CORE-TPI-BPD019-E-002 | SD_Utility Initiated Mass Drops - Solution for generating mass customer drops based on ESCO’s request | 3. Medium | Third Party Interactions | Manage Retail Choice
45807 | CORE-TPI-BPD020-E-001 | ESCO Bill Comparison - This tool allows retail access customers who received a consolidated utility bill from Con Edison to receive a historical 12 month comparison of their ESCO bill compared to what they would have paid for the same period as a full service Con Edison customer. | 3. Medium | Third Party Interactions | Manage Retail Choice
45808 | CORE-TPI-BPD020-E-002 | ESCO Payments - As part of Retail Choice, If the customers are enrolled in Rate Ready billing option with ESCO. Utility has to generate the supply portion on the bill and send EDI 810 transaction to ESCO. During payment settlement process, system will calculate the payments (for POR, BPP and adjustments posted), generate an EDI 820 transaction along with ACH payments file to AP system | 3. Medium | Third Party Interactions | Manage Retail Choice
45809 | CORE-TPI-BPD020-E-003 | CUBS4CSR is intranet application that includes detailed billing information for accounts under the Consolidated Utility Billing option. Unlike RAIS and TCIS, no transactions can be processed using CUBS. CUBS is used for informational purposes only. This tool allows CSR or Specialist to choose various reports for supply portion of the bill. This application is heavily using CUBS DB2 tables that will be decommissioned as part of this implementation. CECONY want these functionality in CC&B as well | 3. Medium | Third Party Interactions | Manage Retail Choice
46910 | CORE-FCC-BPD015-E-014-01 | Payment Posting and Remove meter during Collection Doc (SD14) | 3. Medium | Field, Credit, and Collections | Manage Field Work
46122 | CORE-SM-BPD021-E-002 | Develop a custom To Do Post Processing algorithm to include logic used to calculate the Unbilled dollar amount associated with the To Do entry. This algorithm can also set up the priority based on the Unbilled amount referring to the threshold parameters. | 3. Medium | IT | Manage System Mechanics
46123 | CORE-SM-BPD021-E-003 | Create a To Do Monitor algorithm with the age and plug it in to the Key and Priority To Do Types to notify the assignee, supervisor and/or group via email to work on the priority Aging To Do entries. | 3. Medium | IT | Manage System Mechanics
46124 | CORE-SM-BPD021-E-005 | The custom Control Central Search UI will be extended to limit the search results based on the user’s CIS Division security setting. The resulting search will only retrieve customers that the user has access to. The extension will involve limiting the CIS Division search on the Custom Control Central Search UI. | 3. Medium | IT | Manage System Mechanics
66031 | CORE-SM-BPD021-E-004 | This custom solution requires integration between CC&B and Audit Vault database. Since Audit Vault will be used to capture information that the CSR accessed in CC&B, the account work history would be available in Audit Vault. The data can be accessed by creating synonyms to the table in the CC&B database. The information related to user work history can be retrieve using a query zone. | 3. Medium | IT | Manage System Mechanics
46121 | CORE-IT-BPD021-E-006 | A custom batch process will be designed for mass update of the records provided in the input file in a pre-defined format. The user will manually provide the data in file in the predefined file layout. The file will be processed by a batch job and upon completion of job, would have processed the records present in the file. The custom batch job can be scheduled or run as adhoc for mass updates, as required | 3. Medium | IT | Manage System Mechanics
372935 | CORE-IT-BPD021-E-014 | Non-CCG CSR access needs for CCG Account | 3. Medium | IT | Manage System Mechanics
45815 | CORE-CUS-BPD001-E-001 | A custom audit algorithm on account will be developed. Upon account creation, a service will be called through the audit algorithm to generate a unique 11-character MA ID and store in Account Characteristic | 3. Medium | Customer Service | Manage Account Setup
45816 | CORE-CUS-BPD001-E-003 | The base Control Central Search zone will be extended to allow the additional County field to be available as an additional search criterion for the address search. The extension will involve replicating the base address query search zone and extending the service script to retrieve the county information from the premise address. | 3. Medium | Customer Service | Manage Account Setup
45818 | CORE-CUS-BPD001-E-009 | A custom LSE case enter processing algorithm will be developed This algorithm will search for any LSE denial or unconfirmed cases in the past six months. If there are two or more LSE denial or unconfirmed cases in the last six months, the system shall display a warning message in CCB so that the CSR is notified about this scenario. The CSR can ignore the warning and go ahead with the LSE case creation in the system, which shall put any Credit action on hold on the account. * For LSE cases created under this scenario, a To-Do shall be created for the LSE group so that the LSE back office team can identify such cases and take the necessary action. * For a similar situation, If the LSE request is made through DCX using a webservice, it will generate an error and the error message will be sent back to DCX to notify the customer to contact CSR. | 3. Medium | Customer Service | Manage Account Setup
46920 | CORE-CUS-BPD003-E-001 | A custom SA stop algorithm will be developed to check for an active CASE and transition it to a defined status on its life cycle | 3. Medium | Customer Service | Manage Start/Stop
46929 | CORE-CUS-BPD003-E-010 | A custom SA activation algorithm will be developed and plugged on the utility SA types. This algorithm will take the information from the associated premise of the SA being activated for unit, ledger, folio and serial, and derive one up customer number for every start and derive the check digit using existing logic. | 3. Medium | Customer Service | Manage Start/Stop
58601 | CORE-CUS-BPD003-E-014.1 | A custom algorithm will be developed to Check for the presence of a gas meter at the building. If at least one active gas meter is found at the premise, it will be considered eligible for BOPA script | 3. Medium | Customer Service | Manage Start/Stop
46933 | CORE-CUS-BPD003-E-015 | A custom algorithm will be developed to derive and display alerts for credit arrears using the following logic - Derive the dollar amount in arrears for existing account(s) on the premise;Derive the dollar amount in arrears for each account belonging to the customer requesting the start service | 3. Medium | Customer Service | Manage Start/Stop
46944 | CORE-CUS-BPD003-E-025 | Custom SA Activation algorithm will be developed to check for the following and create a customer contact, - Turn-on process flow created a Deposit SA - No payment was received on the deposit SA yet Customer contact will trigger the disconnect notice | 3. Medium | Customer Service | Manage Start/Stop
46936 | CORE-CUS-BPD003-E-040 | A custom algorithm will be developed to transfer execution during the transfer service request processing which move/transfer deposit SA or active low-income program(s) on the account requesting the transfer. A custom bill completion algorithm to perform the necessary transfers of balance between different Low Income SA’s. | 3. Medium | Customer Service | Manage Start/Stop
45832 | CORE-CUS-BPD004-E-001 | System should generate letters for customers with Unmetered accounts on an annual basis, in order to request them to confirm the overall wattage/ bulb count. | 3. Medium | Customer Service | Manage Special Account Setup
45833 | CORE-CUS-BPD004-E-002 | System should provide a mechanism to add service agreements from different accounts belonging to the same person into one summary billed account. Alternatively, the system should also provide a mechanism to remove individual service agreements from summary account and create separate individual accounts under each premise. | 3. Medium | Customer Service | Manage Special Account Setup
46054 | CORE-CUS-BPD005-E-001 | A custom Zone will be developed for displaying EE information on the Account Portal or Control Central. | 3. Medium | Customer Service | Manage Products and Services
46055 | CORE-CUS-BPD005-E-002 | A custom batch job will be developed in CC&B to process the records from the incoming files based on the Public Assistance program | 3. Medium | Customer Service | Manage Products and Services
46059 | CORE-CUS-BPD005-E-006 | A custom case monitor will be developed to transition the CASE to the next status depending on the due date of last bill during the program since the time it entered the current wait-status. | 3. Medium | Customer Service | Manage Products and Services
45836 | CORE-RBP-BPD006-E-003 | In CC&B2.6 there is already a custom Bill Segment Freeze Algorithm used for Shadow billing which will be extended to calculate the charges under their previously applicable SC rate and put them into custom tables. A custom UI will be developed which will pull all the required data from custom tables and will display the bill amounts of different rates which will be used by the business users to calculate the credit amount. | 3. Medium | Rates, Billing, and Payments | Manage Rates
45837 | CORE-RBP-BPD006-E-004 | A custom batch will be developed which will select all the eligible accounts and verify them for rate-reassignment. It will access the master configuration and will execute the scripts configured against the service classification to validate and perform the rate re-assignment process. | 3. Medium | Rates, Billing, and Payments | Manage Rates
45838 | CORE-RBP-BPD006-E-005 | A custom BO Validation algorithm will be developed and configured at Service agreement to validate the SA setup. A custom master configuration will be created which will maintain the following columns - CIS division, current rate, ineligible rate, rate re-assignment script, validation period. | 3. Medium | Rates, Billing, and Payments | Manage Rates
45839 | CORE-RBP-BPD006-E-006 | A custom calculation rule Derive Value algorithm will be developed which will calculate contract demand for non-standby electric rates of CECONY as per the business process. | 3. Medium | Rates, Billing, and Payments | Manage Rates
45840 | CORE-RBP-BPD006-E-008 | Custom Calculation Rule Derive Value Algorithm will be developed to calculate the estimated usage (kWh) based on item counts, item periods and item types. | 3. Medium | Rates, Billing, and Payments | Manage Rates
45843 | CORE-RBP-BPD006-E-013 | A custom calculation rule BO algorithm of 'Build Bill Line Description' will be developed to override the bill print description of required summary lines with rolled up price and consumption. | 3. Medium | Rates, Billing, and Payments | Manage Rates
46065 | CORE-RBP-BPD008-E-001 | A custom SA type Budget Eligibility algorithm will be developed to determine if a SA is eligible to enroll in budget billing. | 3. Medium | Rates, Billing, and Payments | Manage Budget Billing
56494 | CORE-RBP-BPD008-E-002 | A custom batch and Budget Plan monitor algorithm will be developed to review the budget amount every 4 months and determine if it is required to be changed. | 3. Medium | Rates, Billing, and Payments | Manage Budget Billing
46064 | CORE-RBP-BPD008-E-003 | Custom budget true up algorithm will be developed to handle the requirement | 3. Medium | Rates, Billing, and Payments | Manage Budget Billing
56502 | CORE-RBP-BPD008-E-006 | Credit Refund on Budget Removal | 3. Medium | Rates, Billing, and Payments | Manage Budget Billing
95974 | CORE-RBP-BPD009-E-008-01 | Usage Request to MDM – Usage Request BO enter processing algorithm will be created to include SDP ID, Legacy Acct ID, AMI-Non AMI Flag, Complex Billing Flag, etc. in the usage request custom elements. | 3. Medium | Rates, Billing, and Payments | Manage Read and Billing Determinants
45848 | CORE-RBP-BPD009-E-002 | A custom batch program will be developed to identify estimated bills for non AMI meters. The batch will identify whether estimation was due to irregular read condition based on meter read condition and create event for manage customer contact to send letters, schedule special read field activity and apply 'no access' charges if the manual read was irregular. | 3. Medium | Rates, Billing, and Payments | Manage Read and Billing Determinants
45851 | CORE-RBP-BPD009-E-006 | A custom batch program will be executed after the meter read upload process to detect meter advances for SP/meter not associated with any account. Subsequently a case would be triggered once such a meter is generated to initiate customer contact and initiate disconnection if required. | 3. Medium | Rates, Billing, and Payments | Manage Read and Billing Determinants
46886 | CORE-RBP-BPD010-E-001 | Custom Batch is required to identify such customers and create Customer Contacts through which letter would be generated | 3. Medium | Rates, Billing, and Payments | Manage Payments
46891 | CORE-RBP-BPD010-E-006 | A Custom payment distribution algorithm to automatically distribute payment according to various conditions like LI Programs, NYSERDA Loans, Bankruptcy | 3. Medium | Rates, Billing, and Payments | Manage Payments
46895 | CORE-RBP-BPD010-E-010 | A Custom BO based Approval Screen will be developed for cancelation of adjustments. This screen will allow user to enter the cancelation reason and submit for approval. This will also utilize the Payment Arrangement approval algorithms developed as part of EN BPD018 SD CORE FCC E 007 customization. The base cancel adjustment button will also be disabled. | 3. Medium | Rates, Billing, and Payments | Manage Payments
46887 | CORE-RBP-BPD010-E-002 | Custom Batch is required to be developed to handle mass rate credit/refunds with the parameters mentioned | 3. Medium | Rates, Billing, and Payments | Manage Payments
59916 | CORE-RBP-BPD010-E-012 | A custom audit algorithm for the Account business object that will detect the type of autopay change that has occurred. If the change is a new active autopay record added to the system, the enroll customer contact will be created. If the change is to stop a previously active autopay record, the de enroll customer contact will be created. This contact will send the letters. | 3. Medium | Rates, Billing, and Payments | Manage Payments
78928 | CORE-RBP-BPD010-E-013 | Recommended Solution - Custom solution will be built with following components to automate the approval process for the tender cancellation which results in payment(s) cancellation and/or transfer of payments | 3. Medium | Rates, Billing, and Payments | Manage Payments
78932 | CORE-RBP-BPD011-E-009 | A custom portal to display information about accounts currently in an active escheatment case. The portal would provide a list of the individual credits involved in cases with columns and filters | 3. Medium | Rates, Billing, and Payments | Manage Payments
81400 | CORE-RBP-BPD010-E-015 | ability to hold HEAP payments in an overpayment or temporary status until generation of next bill | 3. Medium | Rates, Billing, and Payments | Manage Payments
59914 | CORE-RBP-BPD010-E-014 | Custom payment event navigation option to develop a new screen that replaces the existing payment event dialog. The new screen will be a portal designed to collect all required info for any allowable tender type. This will also allow customers to also enroll in autopay at the time of payment. Base payment creation objects will be used to create payment based on data entered in the new UI. After payment is created, the user will be navigated to the payment event screen. User access to the base Payment Event Add submenu will be restricted. | 3. Medium | Rates, Billing, and Payments | Manage Payments
45822 | CORE-FCC-BPD012-E-002 | Partial Manual Refund with Interest Calculation - Calculate interest on a deposit when a user manually initiates a partial deposit refund. The adjustment freeze will trigger interest calculation on the deposit and the creation of the withholding amount. | 3. Medium | Field, Credit, and Collections | Manage Deposits
45823 | CORE-FCC-BPD012-E-003 | Deposit Review Method - Algorithm which will document the review rules based on various criteria like Anniversary date, Customer type | 3. Medium | Field, Credit, and Collections | Manage Deposits
45824 | CORE-FCC-BPD012-E-004 | Refund Criteria Algorithm - Auto refund of deposits for Low-income, supplementary income/Elderly type of customers/additional parameters; Look for other conditions - Paid In full, duration on hand, and check for other credit notices in the past X months | 3. Medium | Field, Credit, and Collections | Manage Deposits
45825 | CORE-FCC-BPD012-E-005 | Deposit Interest Calculation with Withholding - Calculate interest on partial refund calculated during deposit review process. Adjustment Freeze Algorithm plus additional logic. Trigger the TaxID process for interest refunds when there is no Tax ID on record. | 3. Medium | Field, Credit, and Collections | Manage Deposits
45826 | CORE-FCC-BPD012-E-006 | Deposit Confirmation Letter - Receipt or notification is sent to the customer when payments are made and when a partial refund of the deposit occurs as part of the review of the Deposit SA. | 3. Medium | Field, Credit, and Collections | Manage Deposits
45828 | CORE-FCC-BPD013-E-001 | A custom monitoring batch job will be built to send notification to CPMS/NUCON when a Deposit(s) billed in CC&B is paid in full. | 3. Medium | Field, Credit, and Collections | Manage New Business/Energy Services
45829 | CORE-FCC-BPD013-E-002 | A custom monitoring batch job will be built to send notification to CPMS/NUCON when all the premises have an effective SP/Meter Installation under a master case received from CPMS/NUCON. | 3. Medium | Field, Credit, and Collections | Manage New Business/Energy Services
45830 | CORE-FCC-BPD013-E-003 | CC&B will monitor for the existence of an effective SP/Meter Installation record indicating a Meter has been set at the service point in the case workflow. | 3. Medium | Field, Credit, and Collections | Manage New Business/Energy Services
45831 | CORE-FCC-BPD013-E-004 | CC&B will monitor for the existence of an effective SP/Meter Installation record and create the Utility SA with read obtained as part of Installation. | 3. Medium | Field, Credit, and Collections | Manage New Business/Energy Services
59925 | CORE-FCC-BPD015-E-001-02 | Screen for displaying and capturing call information, Additional CC&B information in ticket e.g. LSE, CLIC | 3. Medium | Field, Credit, and Collections | Manage Field Work
59927 | CORE-FCC-BPD015-E-001-04 | Update ticket phone number, comments & escalate | 3. Medium | Field, Credit, and Collections | Manage Field Work
59928 | CORE-FCC-BPD015-E-001-05 | Search existing ticket; Fuzzy calls | 3. Medium | Field, Credit, and Collections | Manage Field Work
46905 | CORE-FCC-BPD015-E-009-01 | Hold on FA from being dispatched or waive fees | 3. Medium | Field, Credit, and Collections | Manage Field Work
59931 | CORE-FCC-BPD015-E-009-02 | FA monitor | 3. Medium | Field, Credit, and Collections | Manage Field Work
46087 | CORE-FCC-BPD016-E-003 | Custom Payment Cancellation algorithm to check whether the account should be put in fast collections path based on cancelled payment. The algorithm will start collections for an account if a subsequently cancelled payment was responsible for removing the account from collections or severance. The algorithm has logic to chose the specific collections template. | 3. Medium | Field, Credit, and Collections | Manage Collections
46090 | CORE-FCC-BPD016-E-006 | A custom batch process/report will be developed to select accounts that have (i) no active service, (ii) meter turned-off due to cut for non-pay, inactive advance, or theft of service. The list of such accounts will be reviewed to make sure there is no health impairment before the start of season. | 3. Medium | Field, Credit, and Collections | Manage Collections
46091 | CORE-FCC-BPD016-E-007 | A Collections Event algorithm will be created to determine whether to trigger a physical notice, bill message or both. | 3. Medium | Field, Credit, and Collections | Manage Collections
46092 | CORE-FCC-BPD016-E-008 | A custom batch will be developed to monitor all residential and non-residential multi-dwelling accounts (an account characteristic) having active severance being transitioned to winter season | 3. Medium | Field, Credit, and Collections | Manage Collections
46093 | CORE-FCC-BPD016-E-009 | A custom batch process will be developed to monitor accounts in severance. The job will select all accounts that are in active severance based on the conditions. | 3. Medium | Field, Credit, and Collections | Manage Collections
46097 | CORE-FCC-BPD016-E-013 | trigger a dialer call for Residential/Non-Residential customers during winter/summer periods in the collections timeline and evaluate the response codes to determine whether a field investigation is required or cancel the collections process. | 3. Medium | Field, Credit, and Collections | Manage Collections
46100 | CORE-FCC-BPD016-E-016 | monitoring PA for payment and sending the customer a reminder notice | 3. Medium | Field, Credit, and Collections | Manage Collections
46101 | CORE-FCC-BPD016-E-017 | A collection event algorithm will be developed to determine eligibility for a SAO Payment Arrangement Request. If customer is eligible, the event will trigger the creation of the SAO PA request | 3. Medium | Field, Credit, and Collections | Manage Collections
46104 | CORE-FCC-BPD016-E-020 | Re-Instate the Payment Arrangement (PA) by monitoring the payment received within x days of time after BNA notice is issued and existing PA is broken. | 3. Medium | Field, Credit, and Collections | Manage Collections
46106 | CORE-FCC-BPD016-E-021 | Public officials email ids and county details will be configured as a Master Configuration for all the counties. There will be a series of DLs that each area will map to in CC&B. A custom nightly batch procedure will be created to pull all required data and parse/format it based on the groupings defined in the Master Configuration. The data can be split up and organized by Boro, county, town, etc. The output will then be sent to the appropriate folder to be sent to the corresponding DLs that are organized on the master configuration . | 3. Medium | Field, Credit, and Collections | Manage Collections
46110 | CORE-FCC-BPD016-E-026 | A custom severance criteria algorithm will be plugged into the SA Type’s Severance Criteria plug in spot to invoke the appropriate EBD severance process template based on the system date and characteristic values present on the account. This algorithm can be leveraged to determine more than just EBD customers; and it can be used even more generically to start the winter or summer severance path when the EBD or specified characteristic is not present. The algorithm will have parameters to determine the Winter or Summer period’s From and To Dates. | 3. Medium | Field, Credit, and Collections | Manage Collections
78925 | CORE-FCC-BPD016-E-027 | A custom severance event type algorithm will be created and plugged in on an event prior to the expire SA event type. The custom algorithm will initiate a Stop Service for all SAs with the same debt class as the SA associated to the Severance Event’s Severance Process (includes non-SP based SAs with the same debt class). The initiation of the Stop will trigger the creation of field activities that can be completed with a real read from the MDM or an estimated read. The account will not final bill until all SAs are stopped. | 3. Medium | Field, Credit, and Collections | Manage Collections
46151 | CORE-FCC-BPD018-E-004 | PEGA or a custom screen in CC&B will be used to evaluate FSF (Financial Statement Form) and minimum PA will be triggered for eligible low-income customers determined | 3. Medium | Field, Credit, and Collections | Manage Collections
46153 | CORE-FCC-BPD018-E-006 | New Menu item with modification in BPA script will be developed to offer various PA Request types (Standard, Negotiated) based on the customers' account attributes and eligibility rules. | 3. Medium | Field, Credit, and Collections | Manage Collections
46154 | CORE-FCC-BPD018-E-007 | Solution to customize the PA request BO to include approval levels and lifecycle statuses. The BO will trigger the creation of a To Do only if PA amount is above some threshold. This applies for CECONY only. | 3. Medium | Field, Credit, and Collections | Manage Collections
95972 | CORE-FCC-BPD018-E-009 | A custom BPA Script and custom UI panels to streamline the flow for the user to process Payment Arrangement Request without needing to toggle between multiple screens. This will help them reduce call handling time. | 3. Medium | Field, Credit, and Collections | Manage Collections
46155 | CORE-FCC-BPD018-E-008-1 | Custom Payment Arrangement Request UI and processing logic process flow panels and dropdown will need to be customized to include and present the Deposit Debt as part of the PA amount. The other algorithms are necessary to ensure that the deposit with installments is treated in the same manner as a PA during the collections process. | 3. Medium | Field, Credit, and Collections | Manage Collections
59904 | CORE-FCC-BPD018-E-008-2 | Custom Enter Processing Algorithm Creates the Deposit with Installments and Payment Arrangement as a result of completion of the PA Request | 3. Medium | Field, Credit, and Collections | Manage Collections
59905 | CORE-FCC-BPD018-E-008-3 | Custom Severance Algorithm to Break PA Algorithm will ensure CC&B treats Deposits with installments and Pay Arrangements the same during Collections Breaks both if BNA/termination is not resolved | 3. Medium | Field, Credit, and Collections | Manage Collections
59908 | CORE-FCC-BPD018-E-008-6 | Control Central Zone for PA One stop Payment Arrangement and Deposit Intallment Zone How much debt remains, remaining installments, BNA amounts if customer is in collections, total deposit debt left versus other | 3. Medium | Field, Credit, and Collections | Manage Collections
130311 | CORE-FCC-BPD015-E-016 | Solution document for generating shock incident and sending email to Law department | 3. Medium | Field, Credit, and Collections | Manage Field Work
130320 | CORE-RBP-BPD007-E-025-02 | when SCSR clicks on the ‘Unsummarize All Subordinate Accounts’ button in the summary billing portal then an alert type ‘Pending Unsummarization’ will be created at Master Account level. A plug in batch will be created to look for that alert type and perform the following, A unlink Master Account ID Characteristic will be added on the subordinate account to specify and keep history that it has been unlinked from the master account. Bill Routing of the subordinate accounts will be defaulted to a value specified on the charateristics. Customer Class of the subordinate accounts will be defaulted to a value specified on the characteristic. A Customer Contact will be created on the master account noting that subordinate account has been unlinked from the master account. Verify the Outstanding Master Account balance and keep canceling the transfer adjustments until the master balance become zero, newest one first. In case of remainder balance not able to match total amount of canceled transfer adjustment, create a transfer adjustment back to the Subordinate Account. Alert type will be end dated so that Pending Unsummarization’ display will stop. | 3. Medium | Rates, Billing, and Payments | Manage Billing
130323 | CORE-IT-BPD021-E-011 | A new CCB batch process to auto complete corresponding billing To Do which is already billed and also update the dollar amount for the periods remaining to be billed, as applicable. The unbilled dollar calculation will be based on 12 months (or available months) average bill amounts. Additionally, BPD007-SD14 will be extended to populate the SA ID, Bill Start date and Bill End date for the errored bill segment on the To Do entries so that the unbilled dollar amount can be calculated/recalculated and get populated on the To Dos. | 3. Medium | IT | Manage System Mechanics
130355 | CORE-CUS-BPD003-E-038-50 | Display BOPA script at the qualifying premise for non-res customer Start or Transfer Process Flow - DA Extension - If Start Type is Non-Residential and premise qualifies for BOPA criteria, display the BOPA scrip and capture customers response. | 3. Medium | Customer Service | Manage Start/Stop
130361 | CORE-CUS-BPD003-E-038-51 | Trigger Spectrum Validation for Address fields Whenever Address field is captured (ex: Owner Address on Stop - Successor Script OR Third Party OR while capturing final bill address during Stop/Transfer OR Account-Address override), address validation should Occur. After zipcode is entered fully, launch Spectrum Validation service automatically | 3. Medium | Customer Service | Manage Start/Stop
130372 | CORE-CUS-BPD003-E-038-52 | Validate forwarding conditions (LSE, CCG etc.) and display the pop-up Validate conditions (LSE, CCG, NYPA etc.) and inform to CSR that they are not authorized to take the order based on the condition. Pop-up screen should be displayed to capture the following fields along with a button. - Customer name - Customer phone number - Customer email and - Responsibility date Button click should generate To-Do for the respective group. This is applicable for all three process flows - Start, Stop & Transfer. | 3. Medium | Customer Service | Manage Start/Stop
130378 | CORE-CUS-BPD003-E-038-56 | Start Process Flow - Extract & Display premise alerts Additional Custom Alerts such as meter location, street cut, meter status, CCG, ave bill amount, landlord reversion pending, etc. | 3. Medium | Customer Service | Manage Start/Stop
130382 | CORE-CUS-BPD003-E-038-58 | Transfer Process Flow - Option to send final bill to 'move-to' address Transfer Process Flow - Capture customer preference on whether the final bill from the move out address should be sent automatically to the move in address. This option does not exist in the base functionality (because transfer will create a new Account for the customer). | 3. Medium | Customer Service | Manage Start/Stop
130386 | CORE-CUS-BPD003-E-038-60 | Disable deposit fields/sections if customer indicates EBD or agrees to enroll in Auto-Pay during Start If deposit eligibility algorithm determines that the customer is required to pay upfront deposit, provide a script to CSR upfront with the following questions, - Is customer Elderly, Blind or Disabled? - Is customer willing to enroll in Auto-Pay to avoid Deposit? If customer responds with a 'Yes' to either of the above then, 1. system should not invoke the deposit recommendation algorithm, deposit section should not be displayed on Panel 3 and deposit SA's should not be generated 2. Auto-pay Or EBD information fields should be presented upfront so that CSR can capture the information. Once the information is captured, it should get carried over to Panel4 automatically | 3. Medium | Customer Service | Manage Start/Stop
130392 | CORE-CUS-BPD003-E-038-63 | Custom Deposit Eligibility Logic Base algorithms have been provided for following: 1. C1DEPEXBAGE - Deposit Exemption Based On Age (62 or above) 2. C1DEPEXMPBAH - Deposit Exemption Based On Account History (returning within 60 days) 3. C1REQDEPAID - Require Deposit Based On Available ID (Person ID [SSN] was provided and valid) Apart from the above, custom algorithms will still be required for processing other eligiblity rules like for example Reference Account Check. SD#38.2 explains all the deposit eligibility rules. | 3. Medium | Customer Service | Manage Start/Stop
136966 | CORE-RBP-BPD007-E-027-01 | Currently, hourly interval data required for Mandatory Day Ahead Pricing (MDHP) pricing and Value Stack credit calculation in ORU is performed in CIMS. MDM sends the interval data as part of the response. However, for CECONY MDM calculates a weighted average price based on the hourly intervals using NYISO day ahead hourly price and the interval data required for Value Stack accounts are pushed to CCB 2.6 through a different interface and CCB uses interval billing functionality. As part of the CCB-MDM workshop and subsequent discussions, it was discussed to adopt the existing CECONY process for ORU but MDM team found that the changes to MDM in ORU's existing process is quite high, and the decisions was made to stick with the existing process (i.e. sending the hourly intervals as part of usage response). CCB has to capture the intervals in usage response for master bill segment and process them during billing as required either in supply bill segment or in value stack credit calculation. | 3. Medium | Rates, Billing, and Payments | Manage Billing
137227 | CORE-RBP-BPD006-015-01 | CSR to create a Rate Change Case in CC&B which will create a To-Do for the required business user to perform the rate change process using a custom screen. Business user will enter all the required information in custom screen like new PSC code, CSC and TOD code for CECONY, CIMS Rate code for ORU, etc.. and the backend script will map the correct CC&B rate schedule as per the selected codes and add it on the service agreement of the account after performing the required business validations. This involves Custom Rate Change UI Map and Case lifecycle algorithms. | 3. Medium | Rates, Billing, and Payments | Manage Rates
137228 | CORE-RBP-BPD006-015-02 | CSR to create a Rate Change Case in CC&B which will create a To-Do for the required business user to perform the rate change process using a custom screen. Business user will enter all the required information in custom screen like new PSC code, CSC and TOD code for CECONY, CIMS Rate code for ORU, etc.. and the backend script will map the correct CC&B rate schedule as per the selected codes and add it on the service agreement of the account after performing the required business validations. This involves Custom Rate Change UI Map and Case lifecycle algorithms. | 3. Medium | Rates, Billing, and Payments | Manage Rates
137233 | CORE-FCC-BPD016-E-029-01 | The Replevin case that will be used in CC&B to initiate the Replevin process, generate appropriate notices to the customers, prompt field work, and maintain the replevin lifecycle and all relevant information. The remaining analysis with the Credit, Field, integration, Functional and law department teams has been completed to allow us to finalize the case statuses in CC&B and determine the data that needs to be passed to the Replevin Tracking System (RTS) and received back from RTS. This addresses Open Item BPD016-003. The required Replevin Case will need multiple Case Algorithms to meet the regulatory and ConEd requirements - Enter Status Algorithms to - Generate To Dos Evaluate Eligibility for Replevin Generate required notices - CAZ, PHL Generate Adjustments Hold FAs from being dispatched Monitor Algorithms - Determine if Account is still eligible for Replevin and transition to the appropriate status Field Activity BO Enter Status Algorithms to - Determine if Street Cut or Replevin should be triggered Update all Collector Docs with disconnect information if building is street cut | 3. Medium | Field, Credit, and Collections | Manage Collections
137241 | CORE-FCC-BPD016-E-029-09 | The Replevin case that will be used in CC&B to initiate the Replevin process, generate appropriate notices to the customers, prompt field work, and maintain the replevin lifecycle and all relevant information. The remaining analysis with the Credit, Field, integration, Functional and law department teams has been completed to allow us to finalize the case statuses in CC&B and determine the data that needs to be passed to the Replevin Tracking System (RTS) and received back from RTS. This addresses Open Item BPD016-003. The required Replevin Case will need multiple Case Algorithms to meet the regulatory and ConEd requirements - Enter Status Algorithms to - Generate To Dos Evaluate Eligibility for Replevin Generate required notices - CAZ, PHL Generate Adjustments Hold FAs from being dispatched Monitor Algorithms - Determine if Account is still eligible for Replevin and transition to the appropriate status Field Activity BO Enter Status Algorithms to - Determine if Street Cut or Replevin should be triggered Update all Collector Docs with disconnect information if building is street cut | 3. Medium | Field, Credit, and Collections | Manage Collections
137242 | CORE-FCC-BPD016-E-029-10 | The Replevin case that will be used in CC&B to initiate the Replevin process, generate appropriate notices to the customers, prompt field work, and maintain the replevin lifecycle and all relevant information. The remaining analysis with the Credit, Field, integration, Functional and law department teams has been completed to allow us to finalize the case statuses in CC&B and determine the data that needs to be passed to the Replevin Tracking System (RTS) and received back from RTS. This addresses Open Item BPD016-003. The required Replevin Case will need multiple Case Algorithms to meet the regulatory and ConEd requirements - Enter Status Algorithms to - Generate To Dos Evaluate Eligibility for Replevin Generate required notices - CAZ, PHL Generate Adjustments Hold FAs from being dispatched Monitor Algorithms - Determine if Account is still eligible for Replevin and transition to the appropriate status Field Activity BO Enter Status Algorithms to - Determine if Street Cut or Replevin should be triggered Update all Collector Docs with disconnect information if building is street cut | 3. Medium | Field, Credit, and Collections | Manage Collections
137243 | CORE-FCC-BPD016-E-029-11 | The Replevin case that will be used in CC&B to initiate the Replevin process, generate appropriate notices to the customers, prompt field work, and maintain the replevin lifecycle and all relevant information. The remaining analysis with the Credit, Field, integration, Functional and law department teams has been completed to allow us to finalize the case statuses in CC&B and determine the data that needs to be passed to the Replevin Tracking System (RTS) and received back from RTS. This addresses Open Item BPD016-003. The required Replevin Case will need multiple Case Algorithms to meet the regulatory and ConEd requirements - Enter Status Algorithms to - Generate To Dos Evaluate Eligibility for Replevin Generate required notices - CAZ, PHL Generate Adjustments Hold FAs from being dispatched Monitor Algorithms - Determine if Account is still eligible for Replevin and transition to the appropriate status Field Activity BO Enter Status Algorithms to - Determine if Street Cut or Replevin should be triggered Update all Collector Docs with disconnect information if building is street cut | 3. Medium | Field, Credit, and Collections | Manage Collections
137244 | CORE-FCC-BPD016-E-029-12 | The Replevin case that will be used in CC&B to initiate the Replevin process, generate appropriate notices to the customers, prompt field work, and maintain the replevin lifecycle and all relevant information. The remaining analysis with the Credit, Field, integration, Functional and law department teams has been completed to allow us to finalize the case statuses in CC&B and determine the data that needs to be passed to the Replevin Tracking System (RTS) and received back from RTS. This addresses Open Item BPD016-003. The required Replevin Case will need multiple Case Algorithms to meet the regulatory and ConEd requirements - Enter Status Algorithms to - Generate To Dos Evaluate Eligibility for Replevin Generate required notices - CAZ, PHL Generate Adjustments Hold FAs from being dispatched Monitor Algorithms - Determine if Account is still eligible for Replevin and transition to the appropriate status Field Activity BO Enter Status Algorithms to - Determine if Street Cut or Replevin should be triggered Update all Collector Docs with disconnect information if building is street cut | 3. Medium | Field, Credit, and Collections | Manage Collections
169657 | CORE-RBP-BPD007-E-029 | Calculate and store average gas usage against a SA in CCB | 3. Medium | Rates, Billing, and Payments | Manage Billing
170407 | CORE-RBP-BPD006-E-018 | Rate Pilot Batch | 3. Medium | Rates, Billing, and Payments | Manage Rates
170418 | CORE-RBP-BPD010-E-022 | Account Balance Breakdown Portal | 3. Medium | Rates, Billing, and Payments | Manage Payments
170429 | CORE-IT-BPD021-012 | Populate To Do Characteristics for DOA Approval process | 3. Medium | IT | Manage System Mechanics
170978 | CORE-RBP-BPD007-E-026-01 | NYPA Billing | 3. Medium | Rates, Billing, and Payments | Manage Billing
170982 | CORE-RBP-BPD007-E-026-04 | NYPA Billing | 3. Medium | Rates, Billing, and Payments | Manage Billing
171116 | CORE-RBP-BPD007-E-028-01 | 2 custom batch jobs will be developed – 1st custom job will load the weights file provided by RE into interval bill factor. 2nd custom batch job will be used to calculate the weighted daily price data and load into TOU bill factor based on multiple parameters including Load Weights, Load Day Ahead prices, Capacity Charges, NTAC Factors and Ancillary Charges, Loss Factor Complexity –2 Medium Customizations Related Requirements – New Priority – Mandatory (this is a regulatory requirement; currently this function is performed by a mainframe job that will be de-commissioned after CC&B go-live) | 3. Medium | Rates, Billing, and Payments | Manage Billing
171117 | CORE-RBP-BPD007-E-028-02 | 2 custom batch jobs will be developed – 1st custom job will load the weights file provided by RE into interval bill factor. 2nd custom batch job will be used to calculate the weighted daily price data and load into TOU bill factor based on multiple parameters including Load Weights, Load Day Ahead prices, Capacity Charges, NTAC Factors and Ancillary Charges, Loss Factor Complexity –2 Medium Customizations Related Requirements – New Priority – Mandatory (this is a regulatory requirement; currently this function is performed by a mainframe job that will be de-commissioned after CC&B go-live) | 3. Medium | Rates, Billing, and Payments | Manage Billing
59902 | CORE-TPI-BPD019-E-001-11 | Generate Off Cycle Bill on Off Cycle date | 3. Medium | Third Party Interactions | Manage Retail Choice
176524 | CORE-FCC-BPD015-E-017 | The admin users of QA will disable (gray out) the Escalate button during storms and then enable back for user on a normal day. Admin should control the functionality of the Escalate button in Emergency application for CSS Call Central desktop. The Admin will control the function by region based on the ICS level of serious or above. | 3. Medium | Field, Credit, and Collections | Manage Field Work
176585 | CORE-RBP-BPD007-E-032 | A custom portal need to be developed in CCB to capture and maintain value stack CDG marketer bill messages. This information will be used as information to be printed on bill. | 3. Medium | Rates, Billing, and Payments | Manage Billing
208170 | CORE-RBP-BPD011-E-011-01 | New Adjustment Cancelation Algorithm Create a new adjustment algorithm that will be plugged into the Adjustment Type with the following parameters: PARM 10 – Adjustment Cancel Reason Code (e.g., ACH). This algorithm will triggered when the adjustment is Canceled and when triggered it will create a new adjustment (same adjustment type as the cancelled adjustment) when the cancel reason is equal to PARM 10 to process a paper check. | 3. Medium | Rates, Billing, and Payments | Manage Remittances
208171 | CORE-RBP-BPD011-E-011-02 | New Custom Adjustment FT Creation Algorithm:The base Adjustment FT Creation Algorithm Type Code (e.g., C1-ADJFT-NM) shall be extended to assign the appropriate FT_GL Distribution Codes required for downstream batch extract processing when the AP adjustment is created. | 3. Medium | Rates, Billing, and Payments | Manage Remittances
215077 | CORE-CUS-BPD003-E-049 | Single Service Start | 3. Medium | Customer Service | Manage Start/Stop
231581 | CORE-IT-IAI-1002 | Create Customer Contact for Transactions | 3. Medium | IT | Manage System Mechanics
232538 | CORE-RBP-BPD007-E-036 | Con Edison Electric customers with eligible distributed generation shall be assessed a monthly “Customer Benefit Contribution” (CBC) Charge beginning 1/1/2022. NEM Successor customers on or opting for time-of-use (TOU) rates will receive monetary crediting in-lieu of volumetric banking. | 3. Medium | Rates, Billing, and Payments | Manage Billing
252021 | CORE-CUS-BPD001-E-014 | Customer Service Bill Messages | 3. Medium | Customer Service | Manage Account Setup
253950 | CORE-RBP-BPD007-E-037 | Create Hourly Forecasted Price | 3. Medium | Rates, Billing, and Payments | Manage Billing
253957 | CORE-FCC-BPD017-E-002 | Currently, OpCos transfer the outstanding debt of a final billed account to an active account that is determined to be under same person. CECONY and ORU do this automatically today, and they want to be able to automatically transfer dollars from one account to another in CC&B. Out of the box, CC&B transfers balances to Service Arrangements associated to the same Account; balances are not transferred between Accounts under the same Person automatically. | 3. Medium | Field, Credit, and Collections | Manage Collections
314814 | CORE-CUS-BPD001-E-015 | Preferred Name Change | 3. Medium | Customer Service | Manage Account Setup
362159 | CORE-RBP-BPD007-E-038 | Manage Billing | 3. Medium | Rates, Billing, and Payments | Manage Billing
425373 | CORE-RBP-BPD007-E-039 | Load input files from CUS to CC&B | 3. Medium | Rates, Billing, and Payments | Manage Rates
425375 | CORE-RBP-BPD007-E-041 | Extract output files from CC&B to CUS | 3. Medium | Rates, Billing, and Payments | Manage Rates
437702 | CORE-RBP-BPD007-E-042 | NJ Solar CDG Changes | 3. Medium | Rates, Billing, and Payments | Manage Rates
107512 | CORE-RBP-BPD010-E-019 | Write off Refund Approval | 3. Medium | Rates, Billing, and Payments | Manage Payments
124268 | CORE-FCC-BPD018-E-010 | FSF Print | 3. Medium | Field, Credit, and Collections | Manage Collections
124280 | CORE-FCC-BPD013-E-005 | Legacy ID generation for Premise and SP | 3. Medium | Field, Credit, and Collections | Manage New Business/Energy Services
124283 | CORE-CUS-BPD001-E-012 | System generated Char – field level security Complexity: Medium | 3. Medium | Customer Service | Manage Account Setup
124287 | CORE-CUS-BPD001-E-011-002 | Control Central Search_Check Digit | 3. Medium | Customer Service | Manage Account Setup
69336 | CORE-FCC-BPD015-E-011-02 | R52 form printed for field CSR investigation (SD 11) | 3. Medium | Field, Credit, and Collections | Manage Field Work
69337 | CORE-FCC-BPD015-E-011-03 | R84 form printed for WMS field activity (SD 11) | 3. Medium | Field, Credit, and Collections | Manage Field Work
69338 | CORE-FCC-BPD015-E-011-04 | ORU Gas Emergency form printed in ECS (SD 11) | 3. Medium | Field, Credit, and Collections | Manage Field Work
69339 | CORE-FCC-BPD015-E-011-05 | CECONY Gas Emergency form printed in Gas Central (SD 11) | 3. Medium | Field, Credit, and Collections | Manage Field Work
69345 | CORE-FCC-BPD015-E-014-04 | FA Completion from Service Link for dual service account (SD 14) | 3. Medium | Field, Credit, and Collections | Manage Field Work
56725 | CORE-FCC-BPD017-E-001 | Transfer Final Debt To Another Account - Currently, OpCos transfer the outstanding debt of a final billed account to an active account that is determined to be under same person. CECONY and ORU do this automatically today, and they want to be able to automatically transfer dollars from one account to another in CC&B. Out of the box, CC&B transfers balances to Service Arrangements associated to the same Account; balances are not transferred between Accounts under the same Person automatically. | 3. Medium | Field, Credit, and Collections | Manage Collections
46062 | CORE-RBP-BPD007-E-003 | Custom Batch will be developed which will create a Weather Normalization Factor flat file for uploading to Coned website. | 3. Medium | Rates, Billing, and Payments | Manage Billing
46063 | CORE-RBP-BPD007-E-005 | Custom Account statement portal is required to be developed to display all the required customer information. The details can also be downloaded in an excel format to be sent to the customer. | 3. Medium | Rates, Billing, and Payments | Manage Billing
46067 | CORE-RBP-BPD007-E-007 | An User Exit will be built for SP Multi-Item Page which will automatically copy the last effective dated list of items to the new one when user clicks on the add button in SP Multi-Item Page. | 3. Medium | Rates, Billing, and Payments | Manage Billing
46069 | CORE-RBP-BPD007-E-009 | A custom bill completion algorithm will be developed to stamp the bills with required codes(Seg/Divert/Onsert/Insert/Archive) as bill characteristic values once the bill is completed. | 3. Medium | Rates, Billing, and Payments | Manage Billing
46071 | CORE-RBP-BPD007-E-011 | Custom customer class post bill completion algorithm will be developed to add bill messages related to adjustments and calculation lines within the bill segments at the time of billing | 3. Medium | Rates, Billing, and Payments | Manage Billing
46073 | CORE-RBP-BPD007-E-013 | A custom batch process will be developed which can be run on ad hoc basis for mass cancellation of bills by Rate Schedule or by random account numbers given in the Input file. | 3. Medium | Rates, Billing, and Payments | Manage Billing
46075 | CORE-RBP-BPD007-E-015 | A custom algorithm will be developed by cloning and extending the existing base C1-BSAXMINGR algorithm. This algorithm will have the same base cancellation logic of the bills except that there will be options to exclude records from being auto cancelled based on certain additional attributes. | 3. Medium | Rates, Billing, and Payments | Manage Billing
46079 | CORE-RBP-BPD007-E-019-1 | CC&B 2.6 Retrofits | 3. Medium | Rates, Billing, and Payments | Manage Billing
46081 | CORE-RBP-BPD007-E-002 | A custom Calculation Rule Derive Value Algorithm will be developed to calculate the cumulative sum of normal degree days (NHDD) and actual degree days (AHDD) separately for each bill period from Degree day table. | 3. Medium | Rates, Billing, and Payments | Manage Billing
46082 | CORE-RBP-BPD007-E-020-1 | Maintaining project details for Host - User Interface for maintenance and display portals | 3. Medium | Rates, Billing, and Payments | Manage Billing
46083 | CORE-RBP-BPD007-E-021-1 | Custom Screen to allow users to manually select bill segments, enter reads for individual bill periods for Non AMI meters and provide option for proration and sending out individual bills. Note – For AMI meters, users will not add reads/usage. | 3. Medium | Rates, Billing, and Payments | Manage Billing
58610 | CORE-CUS-BPD003-E-038-4 | Start Service - Premise Information - Data Area and Custom UI Map Start or Transfer Process Flow - DA Extension - will be required to detect dynamically and inject following custom fields on the screen if the criteria is met. - If there is inactive consumption at selected premise, is the customer willing to accept the responsibility? - If there are credit arrears at the selected premise, is the customer willing to accept the responsibility? | 3. Medium | Customer Service | Manage Start/Stop
58617 | CORE-CUS-BPD003-E-038-11 | Start Service - Customer Information - Data Area and Custom UI Map Following scrips (text) will be needed for residential customers only. - For CECONY, script for requesting DOB before POS-ID check - Warn the CSR that by choosing the existing person record indicates that they've verified all information - Capture Red Flag (while CSR should be able to complete the order, processing should be held until the customer comes back with the documents) | 3. Medium | Customer Service | Manage Start/Stop
58623 | CORE-CUS-BPD003-E-038-17 | Start Service - Service Information -Call Deposit Recommendation Algorithm for Deposit Amount. Nothing available OOB, custom algorithm will be required. | 3. Medium | Customer Service | Manage Start/Stop
58626 | CORE-CUS-BPD003-E-038-20 | Start Service - Additional Information - Custom Data Area and UI Map. Following Scripts will need to be displayed (depending on CIS division and Res vs. Non-Res) during Start / Transfer, - Are you the Owner? (only for residential) - Secondary Name (only for residential) - LSE (only for residential) - Concern (EBD value & 3rd Party fields that include - TP Name, TP Street, TP City, TP State, TP Zip) (Only for residential) - My Account - Power your way | 3. Medium | Customer Service | Manage Start/Stop
58628 | CORE-CUS-BPD003-E-038-22 | Start Service - Denial Form - UI Map 'Cancel Process' button has been provided on the process flow and the CS request BO has states for 'Cancelled' and 'Waiting For Additional Actions'. A State transition ui map will capture the Denial Reason when Cancel is clicked. Based on the data entered by the customer, enter state algorithm will create the necessary CC. | 3. Medium | Customer Service | Manage Start/Stop
58634 | CORE-CUS-BPD003-E-038-28 | Start Service -BO Algorithm - My Account resistration and update in CCB | 3. Medium | Customer Service | Manage Start/Stop
58638 | CORE-CUS-BPD003-E-038-32 | Start Service -BO Algorithm - Red Flag letter generation | 3. Medium | Customer Service | Manage Start/Stop
58645 | CORE-CUS-BPD003-E-038-39 | Stop Service - Premise Information - Confirmation Panel Base Confirmation Panel is basic, it does not provide Summary of the entire order on a single page, the way ConEd expects. | 3. Medium | Customer Service | Manage Start/Stop
58650 | CORE-CUS-BPD003-E-038-44 | Transfer Service - ESCO Portability Nothing available OOB, custom algorithm will be required.Transfer Process Flow - Detect if customer service is with ESCO at the current premise. If yes, display ESCO Portability Script and capture customer's response. | 3. Medium | Customer Service | Manage Start/Stop
59544 | CORE-CUS-BPD003-E-038-16 | Start Service - Service Information - Data Area and Custom UI Map. Extend Data Area to Capture Meter Hot / Cold information from the customer for each service. | 3. Medium | Customer Service | Manage Start/Stop
59556 | CORE-CUS-BPD003-E-038-27 | Start Service -BO Algorithm - Move Characteristic from Request BO to Person/Premise/SA We can achieve the following using the base functionality provided: - Customer Service Request Type configuration allows for Person and Account characteristics. - Start Options can be used to default some characteristics on SA's However, there are some additional characteristics (for example RPO char) which still need to be saved based on the Start Type functionality | 3. Medium | Customer Service | Manage Start/Stop
59566 | CORE-CUS-BPD003-E-038-36 | Stop Service - Premise Information - Data Area and Custom UI Map | 3. Medium | Customer Service | Manage Start/Stop
59583 | CORE-CUS-BPD003-E-043-4 | On the Stop Process flow, CC&B will evaluate if tenant is stopping service for a premise enrolled on LOFLL, it will update the Field Activity from Turn Off to Read. This is to prevent automatic disconnect. Inactive Gas process will also be updated to exclude premises with landlord agreement | 3. Medium | Customer Service | Manage Start/Stop
59589 | CORE-RBP-BPD007-E-018-3 | Algorithm to calculate different values and upload into degree days table | 3. Medium | Rates, Billing, and Payments | Manage Billing
59590 | CORE-RBP-BPD007-E-018-4 | Batch Job -1 : generate Data files | 3. Medium | Rates, Billing, and Payments | Manage Billing
59592 | CORE-RBP-BPD007-E-019-2 | SA Type Bill Completion Algorithm to Monitor V-DER allocation Currently, the credit calculation is done in OSB and vouchered back to CSS for both Host and subscriber and the account balance is done at account level. In CCB, the credit amount from one Monthly Bank SA needs to be transferred to the Utility SA based on the bill amount. This Algorithm will check the billed amount on the Utility SA and create a transfer adjustment from Monthly Bank SA to the Utility SAs and keep the remaining on the monthly SA. | 3. Medium | Rates, Billing, and Payments | Manage Billing
59593 | CORE-RBP-BPD007-E-020-10 | Enter Processing Algorithm - A CDG Host may transfer ownership in which case the bank would transfer to the new owner and CDG subscriber list must also transfer | 3. Medium | Rates, Billing, and Payments | Manage Billing
59594 | CORE-RBP-BPD007-E-020-11 | Create custom service task type Business Object for configure different types of project Allocation Type (List Based or Percentage Based) 11a) UI Map o Create Transactional Business Object to capture Subscriber Plan Details Project Id Creation Date Effective date of the plan Subscriber List Percentage allocation (if CDG) 11b) UI Map and display service scripts User Interface for maintenance and display portals | 3. Medium | Rates, Billing, and Payments | Manage Billing
59595 | CORE-RBP-BPD007-E-020-12 | Enter Processing Algorithm- Validate the details of subscriber list e.g. satellite cannot get volumetric credit if it is unmetered and host is non demand billed-.CDG subscriber cannot be net metered or values stack.CDG cannot be RNM subscriber | 3. Medium | Rates, Billing, and Payments | Manage Billing
59598 | CORE-RBP-BPD007-E-020-15 | Manual Compensation Distribution - This could be as a result of monthly compensation distribution or on demand compensation for CDG customer The subscriber allocation plan business object will add a new plan result every time compensation takes place Create Service Task Business Object to capture Credit distribution details including Plan Id,Creation Date,Host Bill Segment,Monetary Credit list,Adjustment Ids,Volumetric Credit List,Banked Energy Ids | 3. Medium | Rates, Billing, and Payments | Manage Billing
59600 | CORE-RBP-BPD007-E-020-17 | Enter Processing Algorithm - For CDG, create credit distribution based on percentage allocation. RNM keep the balance in bank and move to Frozen status. Mass Market -Keep Excess energy of account in bank. Energy banking is done on a Sub SAs Contract quanity with service agreement and energy in debit/credit format and transactions IDs are kept on the portal for reference | 3. Medium | Rates, Billing, and Payments | Manage Billing
59601 | CORE-RBP-BPD007-E-020-18 | Enter Processing Algorithm - CDG - Create credit distribution based on percentage allocation and create transfer adjustment amount from host to subscribers RNM keep the amount on Monthly Bank SA on Host account and will be utilized at the time of subscriber bill freeze. At the time of subscriber billing, the amount will be moved from host SA to subscriber utility SA by ay of transfer adjustment. Mass Market -Keep Excess Amount on the Host Bank SA All transfer adjustments to subscriber accounts are kept on the portal for reference | 3. Medium | Rates, Billing, and Payments | Manage Billing
59602 | CORE-RBP-BPD007-E-020-19 | Enter Processing Algorithm - When host bill segment gets cancelled, the status will be moved from Active to Cancel, so that all transactions done as a result of the bill segments are reversed. - All subscribers bill segments for the month as well get cancelled | 3. Medium | Rates, Billing, and Payments | Manage Billing
59603 | CORE-RBP-BPD007-E-020-2 | Algorithm to Validate Host project details | 3. Medium | Rates, Billing, and Payments | Manage Billing
59604 | CORE-RBP-BPD007-E-020-20 | FT Freeze Algorithm (Host Utility SA BS Freeze) If FT is bill segment and status is freeze, this algorithm will check whether the account has an active project (MM/CDG/RNM) as a host Will fetch the corresponding service task and move the status to allocate, so that the credit distribution will follow the steps as defined in business object enter processing algorithm in Allocate FT Freeze Algorithm (Host Utility SA BS Cancel) If FT is bill segment and status is Cancel, this algorithm will check whether the account has an active project (MM/CDG/RNM) as a host Will fetch the corresponding service task and move the status to Cancel, so that the credit reversal will follow the steps as defined in business object enter processing algorithm Cancel status of Subscriber Result BO If FT is bill segment and status is Cancel, this algorithm will check whether the account is part of an active RNM/CDG project as a subscriber, It will reverse the credit amount or energy. It will also check, whether the subscriber has been removed from the project | 3. Medium | Rates, Billing, and Payments | Manage Billing
59606 | CORE-RBP-BPD007-E-020-22 | Calculation Rule Derive Value Algorithm On Site or Mass Market – Retrieve the Banked energy RNM – Retrieve volumetric credit available on Host account to subscriber bill segment SQ CDG – Retrieve banked energy and current month allocated energy to subscriber bill segment SQ | 3. Medium | Rates, Billing, and Payments | Manage Billing
59607 | CORE-RBP-BPD007-E-020-23 | Batch Job - Power Clerk will send the enrollment file and subsequent update files for enrolling and updating the existing plans | 3. Medium | Rates, Billing, and Payments | Manage Billing
59611 | CORE-RBP-BPD007-E-020-6 | Enter Processing Algorithm - As part of Utility Bill Segment Freeze, the status will be changed from Active to Allocate for credit allocation and once allocation is done, the status will move back to Active. When the status is moved from Active to Allocate, this algorithm will find the most effective Subscriber plan (either monthly or On Demand) and move the Subscriber Plan to ‘Allocate | 3. Medium | Rates, Billing, and Payments | Manage Billing
59615 | CORE-RBP-BPD007-E-021-2 | System automatically calculated total canceled amount and difference amount by invoking rate check in background for all selected bill segments. For AMI meters, a new automated real-time interface from Rate check will be developed to obtain new usage information and use that for Rate check calculations. | 3. Medium | Rates, Billing, and Payments | Manage Billing
59617 | CORE-RBP-BPD007-E-021-4 | Perform cancel/rebill automatically behind the screens and generate customer bills as well as rolled-up summary archived bill as required. For AMI meters, system will interface with MDM directly real-time to obtain usage information as part of cancel-rebill. | 3. Medium | Rates, Billing, and Payments | Manage Billing
59619 | CORE-RBP-BPD007-E-021-6 | Cancel associated financial transactions as applicable like LPC and Payment Arrangements | 3. Medium | Rates, Billing, and Payments | Manage Billing
59620 | CORE-RBP-BPD007-E-021-7 | Calculate OPI (Overpayment Interest) if applicable and post adjustment to be linked to last bill | 3. Medium | Rates, Billing, and Payments | Manage Billing
59893 | CORE-TPI-BPD019-E-001-02 | Enrollment, Drop, Switch | 3. Medium | Third Party Interactions | Manage Retail Choice
45817 | CORE-CUS-BPD001-E-008 | 1.A custom alert zone will be developed for account Information Portal (Control Central Page Search). 2.A master configuration will be maintained to store Key Words of alert text along with the Color Coding to identify the critical alerts amongst all alerts 3.A script will be triggered from the zone to separate out the critical alerts from the complete list of alerts retrieved from base program (Same program used for Base Alert Zones). 4.The list of critical alerts if any, will be displayed on the account Information screen of Control Central Search. Only when user clicks "OK" on the Alert screen, he/she will have access to the rest of the data on the Account Information Screen. | 4. Complex | Customer Service | Manage Account Setup
46056 | CORE-CUS-BPD005-E-003 | Common Routine will be built to create the SA (if needed) and transfer the debt from one SA to another with the ability to retain the age of the debt. | 4. Complex | Customer Service | Manage Products and Services
56499 | CORE-RBP-BPD008-E-004 | Annual Solicitation of Budget | 4. Complex | Rates, Billing, and Payments | Manage Budget Billing
56496 | CORE-RBP-BPD008-E-005 | Calculate Recommended Budget Amount | 4. Complex | Rates, Billing, and Payments | Manage Budget Billing
45821 | CORE-FCC-BPD012-E-001 | Deposit Recommendation Algorithm - Based on various parameters like operating company and customer type, deposit amount is calculated based on historical bills present on the premise. Includes calculation logic for customers with an ESCO. | 4. Complex | Field, Credit, and Collections | Manage Deposits
46898 | CORE-FCC-BPD015-E-002 | Rule based dispatch of field activities | 4. Complex | Field, Credit, and Collections | Manage Field Work
59933 | CORE-FCC-BPD015-E-015-01 | Identify Inactive Gas | 4. Complex | Field, Credit, and Collections | Manage Field Work
137245 | CORE-FCC-BPD016-E-029-13 | The Replevin case that will be used in CC&B to initiate the Replevin process, generate appropriate notices to the customers, prompt field work, and maintain the replevin lifecycle and all relevant information. The remaining analysis with the Credit, Field, integration, Functional and law department teams has been completed to allow us to finalize the case statuses in CC&B and determine the data that needs to be passed to the Replevin Tracking System (RTS) and received back from RTS. This addresses Open Item BPD016-003. The required Replevin Case will need multiple Case Algorithms to meet the regulatory and ConEd requirements - Enter Status Algorithms to - Generate To Dos Evaluate Eligibility for Replevin Generate required notices - CAZ, PHL Generate Adjustments Hold FAs from being dispatched Monitor Algorithms - Determine if Account is still eligible for Replevin and transition to the appropriate status Field Activity BO Enter Status Algorithms to - Determine if Street Cut or Replevin should be triggered Update all Collector Docs with disconnect information if building is street cut | 4. Complex | Field, Credit, and Collections | Manage Collections
170981 | CORE-RBP-BPD007-E-026-03 | NYPA Billing | 4. Complex | Rates, Billing, and Payments | Manage Billing
217575 | CORE-RBP-BPD007-E-034 | Bill Message Enhancements | 4. Complex | Rates, Billing, and Payments | Manage Billing
217578 | CORE-CUS-BPD002-E-012 | Letter Enhancements | 4. Complex | Customer Service | Manage Contact
425374 | CORE-RBP-BPD007-E-040 | Process records and generate bill calc lines | 4. Complex | Rates, Billing, and Payments | Manage Rates
46076 | CORE-RBP-BPD007-E-016 | Custom SA type FT freeze algorithm will be developed to send the full budget amount when partial or blank bill is sent to the customers. | 4. Complex | Rates, Billing, and Payments | Manage Billing
46080 | CORE-RBP-BPD007-E-006 | Custom Bill Comparison portal is required to be developed to display comparative analysis of two bills. | 4. Complex | Rates, Billing, and Payments | Manage Billing
59613 | CORE-RBP-BPD007-E-020-8 | Enter Processing Algorithm Annual process for true up (as maintained in Project) will be done and status will be moved back to Active. Based on refund mechanism (i.e. A/P refund or bill credit) will be given. a. Any monetary credit remaining on the Host Account after all Satellite Account(s) have been credited shall be converted back to the kWhr equivalent at the per-kWhr rate applicable to the Host Account’s Service Classification for the current billing period. The kWhr shall then be converted to a monetary credit based on the Company’s Avoided Energy Cost for the calendar year c. Each year, any Annual Credit on the CDG Host Account will be distributed to one or more of its CDG Satellite Accounts pursuant to the CDG Host’s instructions, and carried forward on that Satellite Account to the next year. Any undistributed portion of the Annual Credit will be carried forward on the CDG Host Account for up to two years and forfeited thereafter NOTE: The rated adjustment types will used in order to use base rate engine functionality. | 4. Complex | Rates, Billing, and Payments | Manage Billing
59618 | CORE-RBP-BPD007-E-021-5 | System automatically derives calc lines for original bill segments and calc lines for rebill scenario and creates billable charge for converted bills | 4. Complex | Rates, Billing, and Payments | Manage Billing
136948 | CORE-RBP-BPD007-024 | a custom Bill Print Extract – Algorithm to include the fields to be printed on the bill in the bill print extract file. | 4. Complex | Rates, Billing, and Payments | Manage Billing

## Attachment 10-Redacted
List of External Labor Vendor Change Orders and Unplanned Costs |  |  |  |  | Click Here to Retun To Summary Sheet
External Labor Change Orders / Contracts
| Category | Amount
| Increased Project Effort | 85996140.33
| Risk Mitigation Measures | 16084633.1775
| Total | 102080773.5075
ID # | Change Order Description | Category | Sub Category | Change Order / Contract Amount | Comments
Contract Award | Initial Contract Award | Increased Project Effort | Scope | REDACTED | After submitting the business case, the Company completed a competitive procurement process. The price differential between the top two vendors was 0.1%. The Company completed contract negotiations and the cost for services was greater than the amount estimated in the business plan. This line item is the cost difference between the fixed fee contract and the business plan estimated amount for services.
A-0018 A-0021 A-0038 A-0051 D-0002 D-0005 D-0013 D-0014 | Extension of the Data Conversion Architects & staffing | Increased Project Effort | Data Conversion | REDACTED | Additional data sources were identified as a result of new requirements and the resources supporting the workstream were extended to complete the additional project activities.
A-0041 A-0053 A-0056 A-0060 | Additional Infrastructure Resources | Increased Project Effort | Infrastructure | REDACTED | Due to the number of interfaces added to the program, additional infrastructure resources were needed to manage the environments, code deployments, performance monitoring, etc.
A-0005 A-0022 A-0043 A-0048 A-0057 A-0065 | Additional costs associated with new interfaces and extensions | Increased Project Effort | Scope | REDACTED | These change orders are for the design, development, and testing of additional interfaces and extensions identified on the project and not within the original fixed fee contract.
A-0018 A-0035 A-0039 A-0042 A-0047 A-0049 A-0052 A-0055 D-0010 | Additional staffing to support User Acceptance Testing | Increased Project Effort | UAT | REDACTED | Additional contractor resources needed to support User Acceptance Testing (UAT) as effort increased due to new integrations and extensions, and to mitigate implementation risk.
C-0001 C-0002 C-0003 C-0004 C-0005 | Additional Staff Augmentation Resources (Deployment & Project Management) | Increased Project Effort | Staff Augmentation | REDACTED | Additional deployment, training, and project management resources were needed to support the project as additional extensions and integrations were identified.
D-0001 D-0003 D-0004 D-0011 D-0012 D-0015 D-0018 D-0019 D-0020 | Additional Staff Augmentation Resources (Middleware & Development) | Increased Project Effort | Staff Augmentation | REDACTED | With the additional interfaces and extensions identified, additional contractor staff augmentation resources were contracted to perform development & middleware for the new interfaces.
Various Contracts | Additional Labor for Legacy System Integrations | Increased Project Effort | Staff Augmentation | REDACTED | Additional labor was needed from the managed service provider and other legacy contractor labor to support additional design, development, and testing related to the additional integrations identified.
Various Contracts | Additional DCX & RPA labor needed to support the program | Increased Project Effort | Staff Augmentation | REDACTED | During the implementation, the business continued to evolve and implement new changes to web and mobile digital platforms. This labor was required to keep up with customers preferences on digital channels, which evolved during the project implementation.
Various Contracts | Additional Reporting Labor (Oracle Utilities Analytics) | Increased Project Effort | Staff Augmentation | REDACTED | Additional labor was needed to support reporting requirements to extract, transform, and load the data required to support reports.
Various Contracts | Additional Internal Infrastructure Resources | Increased Project Effort | Staff Augmentation | REDACTED | Additional labor was required from infrastructure and operations to support additional legacy environments and interfaces identified by the project team. This is the effort for the legacy side of the interfaces identified.
A-0061 | Additional staffing to support extended testing efforts (Parallel Billing, Operational Readiness Testing, etc.) | Risk Mitigation Measures | Testing | REDACTED | This change order is for additional resource support to obtain the enhanced Go Live criteria metrics such as >99.97% bill accuracy across every bill cycle.
A-0037 A-0050 A-0059 | Additional staffing to support testing with Retail Choice providers | Risk Mitigation Measures | Retail Choice | REDACTED | As a part of enhancing the Go Live criteria, this included additional testing with Retail Choice providers. These change orders were for contractor resources needed to support this additional testing effort.
B-0001 | Quality Assurance Advisory Oversight | Risk Mitigation Measures | Quality Assurance | REDACTED | Contracted with a third party independent quality assurance advisory team for the program to help identify indicators of risk and delivery alignment to industry best practices, and provide risk monitoring reporting to the Executive Steering Committee.
B-0002 B-0003 B-0004 | Security, Controls & Compliance Integration Services | Risk Mitigation Measures | Controls & Compliance | REDACTED | Additional external resources to support security, controls, and compliance related to the project, all which were key risks to project implementation.
D-0006 D-0007 D-0008 D-0009 D-0016 | New Knowledge Management Platform Implementation | Risk Mitigation Measures | Learning | REDACTED | Additional unplanned value was identified to implement and new learning platform across the company to more efficiently train and support employees post go-live while providing customer service. This new platform served to reduce call time and therefore customer wait times, a key risk area post go-live.

## Attachment 11
Original and Updated Cost Model (Assuming original and actual Extension and Interface counts in Attachment 5)
Cost Category | Original Business Case Cost | Updated Business Case Cost | Variance | % Variance | Click Here to Retun To Summary Sheet
Internal Labor | 101878454.984 | 132494850.1213 | 30616395.1372 | 30.05%
External Labor | 149610335.1657 | 195350650.0023 | 45740314.8366 | 30.57%
Other | 4372076 | 4637500 | 265424 | 0%
Contingency | 35186513.2725 | 46680051.0185 | 11493537.7461 | 32.66%
Software | 84764722.0424 | 84764722.0424 | 0 | 0%
Hardware | 11819616.4065 | 11819616.4065 | 0 | 0%
AFUDC | 33551282.0369 | 41708355.3538 | 8157073.3169 | 24.31%
Total | 421182999.9079 | 517455744.9447 | 96272745.0368 | 22.86%
Project Hours Estimate
Original Estimated Hours | 906029.9285
Updated Estimated Hours | 1209655.0991
Variance | 303625.1706
% Variance | 33.51%

## Attachment 12
Billing Exception Remediation Details |  |  |  |  | Click Here to Retun To Summary Sheet
Cost Category | 2022 | 2023 - January - September | 2023 October - December | Total
Internal Labor | 1916888.96 | 5726294.83 | 191790.97 | 7834974.76
External Labor | 2304881.55 | 10665039.22 | 3041189.64 | 16011110.41
AFUDC | 994810 | -1464904 | 0 | 0
Other | 2127.37 | 30275.24 | 23443.44 | 55846.05
Total | 5218707.88 | 14956705.29 | 3256424.05 | 23431837.22
Billing Exception Remediation Progress
Week | # of Pending Billing Exceptions
2022-09-15 | 299432
2022-10-15 | 267534
2022-11-15 | 254137
2022-12-15 | 194974
2023-01-18 | 153856
2023-02-15 | 143750
2023-03-15 | 119097
2023-04-15 | 92212
2023-05-15 | 66315
2023-06-15 | 49066
2023-07-15 | 38881
2023-08-15 | 29384
2023-09-15 | 25822
2023-10-11 | 14528

## Attachment 13
PSC Metric Performance Post Go-Live | [5 empty] | Click Here to Retun To Summary Sheet
Metric | PSC Target | Company Performance October 2023 | Company Performance November 2023 | Company Performance December 2023 | Company Performance January 2024 | Comments
Calls Answered in 30 seconds | 66% | 53.6% | 73.5% | 91.9% | 92.7% | Performance below target for one month after go-live, which was remediated and exceeded targets in the following months
Customer Satisfaction - Non Emergency | > or = to 3.75 out of 5 | 3.93 | 4.13 | 4.12 | 4.11 | Performance exceeded target post go-live
Customer Satisfaction - Emergency | > or = to 3.57 out of 5 | 3.59 | 3.25 | 3.88 | 3.81 | Performance exceeded target in October, December and January. A small sample size in November led to below-target results.
PSC Complaints | 2.0 per 100,000 customers | 2.5 | 1.3 | 1.4 | 1.8 | Performance exceeded targets in November, December and January. October performance below target due to one rate consultant submitting a high number of complaints for periods before implementation of the new CIS.
Estimated and Delayed Billing | ≤1.99 for Group 1 Residential and Mass Market ≤6.32 for Group 2 - Large electric commercial and commercial gas | NA | NA | 0.88% for Group 1 5.00% for Group 2 | NA | Performance exceeded targets in 4th Quarter. Metric measured quarterly.

## Attachment 14
Summary Costs of Peer Utilities |  |  |  |  | Click Here to Retun To Summary Sheet
CIS Implementation Utility Benchmarking
Cost Comparisons
Type of Utility | Tier | Location | Number of Customers | Commodity | Total Cost
Investor Owned | Tier 1 | ConEd | 3600000 | Electric, Gas, Steam | 509400000
Investor Owned | Tier 1 | West | 5100000 | Electric | 630000000
Investor Owned | Tier 1 | South | 4400000 | Electric, Gas | 534100000
Investor Owned | Tier 1 | East | 7200000 | Electric, Gas | 550000000

## Attachment 15
Original Cost Benefit Analysis |  |  |  |  | Original Cost Benefit Analysis Graph
Click Here to Retun To Summary Sheet
Year | Cost | Benefit | Net Cash Flow | ∑ Cash flow
2018 | 13714 | - | -13714 | -13714
2019 | 18569 | 2935 | -15634 | -29348
2020 | 147644 | 2979 | -144665 | -174013
2021 | 114675 | 3024 | -111651 | -285664
2022 | 138691 | 3069 | -135622 | -421286
2023 | 71940 | 23447 | -48493 | -469779
2024 | 13987 | 43011 | 29024 | -440756
2025 | 8833 | 45312 | 36479 | -404277
2026 | 8703 | 47798 | 39095 | -365182
2027 | 8589 | 50229 | 41639 | -323542
2028 | 8640 | 53136 | 44496 | -279046
2029 | 8691 | 56288 | 47597 | -231449
2030 | 8743 | 59708 | 50964 | -180485
2031 | 8796 | 63421 | 54625 | -125860
2032 | 8850 | 67457 | 58607 | -67253
2033 | 8904 | 71846 | 62942 | -4311
2034 | 8959 | 76625 | 67665 | 63354
2035 | 9016 | 81830 | 72814 | 136168
2036 | 9072 | 87504 | 78431 | 214599
2037 | 9130 | 93692 | 84562 | 299161
2038 | 9189 | 100446 | 91257 | 390418
2039 | 9248 | 107821 | 98573 | 488990
2040 | 9309 | 115878 | 106570 | 595560
Total | 661892 | 1257456 | 595561
In the original Cost Benefit Analysis, the aggregated financial benefits and costs attributed to the implementation of a new CIS to support both CECONY and O&R resulted in a net benefit of $595.6M

## Attachment 16
Updated Cost Benefit Analysis |  |  |  |  | Updated Cost Benefit Analysis Graph
Click Here to Retun To Summary Sheet
Year | Cost | Benefit | Net Cash Flow | ∑ Cash flow
2018 | 68380.5549 | 0 | -68380.5549 | -68380.5549
2019 | 15346.0274 | 2934.8535 | -12411.1739 | -80791.7288
2020 | 58424.2545 | 2978.8763 | -55445.3782 | -136237.107
2021 | 116758.8852 | 3023.5594 | -113735.3258 | -249972.4328
2022 | 164694.3493 | 3068.9128 | -161625.4365 | -411597.8693
2023 | 158092.2614 | 16099.7222 | -140034.6133 | -551632.4827
2024 | 27603.4115 | 43011.0146 | 15407.6031 | -536224.8796
2025 | 8833.2457 | 45312.0066 | 36478.761 | -499746.1186
2026 | 8702.9967 | 47798.0963 | 39095.0996 | -460651.019
2027 | 8589.4285 | 50228.6906 | 41639.2621 | -419011.7569
2028 | 8639.9611 | 53136.3765 | 44496.4155 | -374515.3414
2029 | 8691.2516 | 56288.1033 | 47596.8516 | -326918.4898
2030 | 8743.3116 | 59707.574 | 50964.2625 | -275954.2273
2031 | 8796.1524 | 63420.8518 | 54624.6994 | -221329.5279
2032 | 8849.7858 | 67456.5951 | 58606.8092 | -162722.7187
2033 | 8904.2238 | 71846.3176 | 62942.0938 | -99780.6249
2034 | 8959.4783 | 76624.6733 | 67665.195 | -32115.4299
2035 | 9015.5616 | 81829.7704 | 72814.2088 | 40698.779
2036 | 9072.4862 | 87503.5167 | 78431.0306 | 119129.8095
2037 | 9130.2646 | 93691.9992 | 84561.7346 | 203691.5441
2038 | 9188.9097 | 100445.9019 | 91256.9921 | 294948.5363
2039 | 9248.4345 | 107820.9653 | 98572.5308 | 393521.0671
2040 | 9308.8522 | 115878.4923 | 106569.6401 | 500090.7072
Total | 751974.0882 | 1250106.8696 | 500090.7072
In the updated Cost Benefit Analysis, the aggregated financial benefits and costs attributed to the implementation of a new CIS to support both CECONY and O&R resulted in a net benefit of $500.1M.

## Summary Table (hidden)
Cost Category | 2017 Actual | 2018 Actual | 2019 Actual | 2020 Actual | 2021 Actual | 2022 Actual | 2023 Actual | 2024 Actual | Total Actual Costs | Total Planned from 2018 Business Plan | Variance Planned vs. Actual | % Variance Planned vs. Actual
Internal Labor | 90744.8748 | 2010883.441 | 4534406.3994 | 11004461.2333 | 21273893.9462 | 23776301.1057 | 25510188.8699 |  | 105693148.0404 | 101878454.984 | 3814693.0564 | 3.744%
External Labor | 664765.22 | 3903764.9525 | 7630623.9623 | 27177321.1108 | 61834946.9731 | 85077443.5122 | 52792600.3497 |  | 239081466.0806 | 149610335.1657 | 89471130.9149 | 59.8%
Other | 1767016.3576 | 3676.6749 | 7263.3267 | 125104.6039 | 218448.3987 | 1515195.4 | -1818475.92 |  | 1818228.8418 |  | 1818228.8418 | 100%
Facilities | 0 | 0 | 144994.6652 | 59188.1992 | 16857.1177 | 0 | 0 |  | 221039.9821 | 4637500 | -4416460.0179 | -95.23%
Billing Exceptions | [5 empty] | 5218707.88 | 18213129.34 |  | 23431837.22 |  | 23431837.22 | 100%
Contingency | [8 empty] | 0 | 35186513.2725 | -35186513.2725 | -100%
Software | 0 | 53712342.8308 | 27782.3721 | 8083453.3547 | 8119978.9354 | 9181127.6322 | 4110806.2235 |  | 83235491.3487 | 84764722.0424 | -1529230.6936 | -1.804%
Hardware | 0 | 54854.0659 | 109155.2768 | 1353899.8903 | 4634332.8286 | 3222267.7531 | 1835476.6444 |  | 11209986.4592 | 11819616.4065 | -609629.9473 | -5.158%
AFUDC | 16156.71 | 287364.07 | 805484.44 | 2356809.82 | 5303701.41 | 10780580.87 | 11812149.52 |  | 31362246.84 | 33551282.0369 | -2189035.1969 | -6.524%
Total | 2538683.1624 | 59972886.0351 | 13259710.4426 | 50160238.2123 | 101402159.6098 | 138771624.1533 | 112455875.0274 | 0 | 496053444.8129 | 421448423.9079 | 74605020.905 | 17.7%
Cost Category | Variance from Planned
Internal Labor | 3256423.2589
External Labor | 102317983.0029
Billing Exception Remediation | -2549154.3857
Other | 1818228.8418
Contingency | -35186513.2725
Facilities | -4416460.0179
Hardware | -609629.9473
Software | -1529230.6936
AFUDC | -2189035.1969
Total | 60912611.5897

## Attachment 5 backup (hidden)
| Original Hours | Original Cost Estimate | Updated Hours | Updated Cost Estimate
Project management
Initiate Project
Understand Project Stakeholder Goals and Expectations | 984.3954 | 192807.5558 | 1282.0916 | 251115.5162
Establish Project Governance | 426.8912 | 71019.2758 | 555.9897 | 92496.5935
Plan Project Scope | 5544.9237 | 851640.8594 | 7221.7937 | 1109190.1101
Mobilize Project | 1017.5723 | 127385.2018 | 1325.3018 | 165908.4395
Manage Project
Manage Project Governance | 3060.5656 | 501104.3268 | 4031.1209 | 660012.6837
Manage Project Scope and Requirements | 2839.8557 | 492206.9484 | 3740.4203 | 648293.8014
Manage Project Releases | 4553.0327 | 715823.1175 | 5996.8737 | 942822.3058
Manage Project Work Plan and Time | 20971.7232 | 2628495.2314 | 27622.1988 | 3462033.9499
Manage Project Performance and Reporting | 3038.5503 | 389062.0489 | 4002.1241 | 512439.9717
Manage Project Issues | 4553.0327 | 715823.1175 | 5996.8737 | 942822.3058
Manage Project Risks | 4404.5856 | 881575.1822 | 5801.3515 | 1161137.0543
Manage Project Quality | 22171.4094 | 4365744.9526 | 29202.325 | 5750193.8988
Manage Project Stakeholder Expectations | 4256.1384 | 939512.0777 | 5605.8293 | 1237446.6845
Manage Suppliers/Alliance Partners - Project | 13554.7542 | 1800975.6084 | 17853.1879 | 2372094.3545
Manage Resources - Project | 4275.0581 | 672120.2324 | 5630.7488 | 885260.523
Manage Configuration - Project | 2190.544 | 529610.2155 | 2885.2013 | 697558.2548
Manage Work Environment - Project | 1063.9719 | 167276.5601 | 1401.3747 | 220322.6862
Manage Business Case - Project | 4389.0919 | 801932.2205 | 5780.9446 | 1056238.0101
Close Project
Sign-off Project | 1790.0058 | 276657.2247 | 2337.3803 | 361257.5832
Close Project | 4185.2651 | 573628.3459 | 5465.0977 | 749040.948
Envision
High level plan
Refine High-level Requirements | 8751.7462 | 1239703.4308 | 11249.2284 | 1593477.0971
Validate Current Application Capabilities | 1394.5001 | 153779.11 | 1792.448 | 197662.9924
Test Spreadsheet - Plan (X) | 1322.6284 | 203470.1994 | 1700.0663 | 261534.4078
Validate Current Technical Architecture Capabilities | 1242.8694 | 133471.1674 | 1597.5465 | 171559.7804
Validate Current Training and Performance Support Capabilities | 991.4506 | 142798.4585 | 1274.3804 | 183548.7968
Refine Solution Blueprint | 3425.2779 | 507274.9895 | 4402.7481 | 652035.8479
Refine Delivery Strategy | 3030.3478 | 469237.6537 | 3895.1169 | 603143.813
Test Spreadsheet - Plan (X) | 2314.079 | 332658.3905 | 2974.4467 | 427588.9807
Validate Planning Deliverables | 1346.5856 | 192197.0361 | 1730.8602 | 247044.2264
Sign-off Planning Deliverables | 1346.5856 | 189754.9268 | 1730.8602 | 243905.2134
Analyze Application
Analyze Business Processes | 845.744 | 105641.1746 | 845.744 | 105641.1746
Identify Application Requirements | 10219.1734 | 1481436.7589 | 12219.6708 | 1771441.6583
Assess Process Gaps | 1843.4312 | 261487.3813 | 1843.4312 | 261487.3813
Perform Fit Gap Analysis | 1748.3858 | 293169.9043 | 1748.8364 | 293245.4587
Define Application Metrics | 2312.0546 | 387686.0794 | 2312.0546 | 387686.0794
Refine Application Metrics | 2312.0546 | 340687.0826 | 2804.3901 | 413233.9547
Analyze User Roles | 2161.5569 | 238366.6396 | 2680.6458 | 295609.406
Select and Update User Roles | 3955.7619 | 447546.1314 | 4939.2619 | 558817.1413
Define RICEFW Inventories | 6781.3453 | 907782.3641 | 8457.3276 | 1132137.1294
Analyze Integration Solution | 955.0731 | 138966.6889 | 955.0731 | 138966.6889
Define Conversion Strategy | 307.0741 | 54465.9345 | 307.0741 | 54465.9345
Adapt Conversion Strategy | 323.4636 | 47534.6084 | 323.4636 | 47534.6084
Plan Integration Test (Product Test) | 2052.2212 | 296346.4157 | 2476.5482 | 357620.4201
Plan Performance Test | 1715.4432 | 244374.2491 | 2139.7703 | 304821.9588
Plan User Acceptance Test | 1494.4129 | 218484.8075 | 1918.6826 | 280513.5084
Validate Application Analysis Deliverables | 972.5586 | 134977.3638 | 1144.7058 | 158868.9489
Sign-off Application Analysis Deliverables | 972.5586 | 141163.3634 | 1144.7058 | 166149.8976
Analyze Technical Architecture
Gather Technical Requirements | 3055.3614 | 311396.102 | 4166.8408 | 424675.7812
Define Application Architecture | 1673.1741 | 195563.7725 | 2281.8414 | 266705.965
Assess Technical Architecture Gaps | 3328.1294 | 297711.3783 | 4538.8363 | 406012.8284
Define System Landscape | 2035.15 | 151974.6029 | 2775.4969 | 207259.9265
Define Development Guidelines | 1454.934 | 145584.1971 | 1984.2099 | 198544.8188
Define Project Tools | 5528.7492 | 488184.7937 | 7539.9977 | 665776.6661
Define Sizing and Output Management | 3176.1844 | 298519.8079 | 4331.6168 | 407115.3486
Analyze Security Needs | 1424.2192 | 195500.4013 | 1942.3217 | 266619.5405
Analyze Technical Integration | 1698.0696 | 146497.5793 | 2315.7934 | 199790.4711
Analyze Operations Supervision | 1063.9151 | 78667.807 | 1450.9462 | 107285.5832
Analyze Operations Management | 2279.8181 | 168573.8722 | 3109.1704 | 229897.6782
Analyze Infrastructure Needs | 1383.902 | 101410.8915 | 1887.3379 | 138302.1473
Validate Technical Architecture Analysis Deliverables | 694.9946 | 76595.729 | 947.8198 | 104459.7246
Sign-off Technical Architecture Analysis Deliverables | 781.5876 | 69959.4308 | 1065.9136 | 95409.2737
Plan
Design Application
Design Detailed Business Processes | 24481.6324 | 3019900.5097 | 30487.6404 | 3760763.9525
Develop Prototype and Conduct Conference Room Pilot | 10677.6055 | 1686941.0681 | 13251.6089 | 2093604.5332
Design Reports and Forms | 4604.1043 | 683782.4138 | 4591.7038 | 681940.7406
Design Extensions | 4717.9719 | 721868.5948 | 7507.7742 | 1148719.5276
Design Data Conversion | 5024.7364 | 812786.5245 | 5024.7364 | 812786.5245
Design Integration Solution | 24198.1221 | 3954307.8308 | 43044.6079 | 7034084.2571
Design Workflows | 0 | 0 | 0 | 0
Plan Assembly Test | 5266.9263 | 819721.9513 | 16848.6584 | 2622253.3767
Validate Application Design Deliverables | 3984.0641 | 605481.7019 | 6103.4301 | 927574.2456
Sign-off Application Design Deliverables | 2432.967 | 354863.8663 | 3727.2101 | 543637.5403
Design Technical Architecture
Set up System Landscape (Project) | 5744.9852 | 432708.6608 | 7834.8961 | 590119.4247
Enable Project Tools | 13532.6319 | 1019269.29 | 18455.5329 | 1390059.0893
Refine Sizing and Perform Output Management Detailed Design | 8918.4796 | 621582.0418 | 12162.8443 | 847701.1674
Design Security | 3391.981 | 460406.3701 | 4625.9159 | 627893.0071
Design Technical Integration | 1346.7815 | 122406.199 | 1836.7136 | 166935.1281
Design Operations Supervision | 2607.7499 | 196398.5862 | 3556.3971 | 267844.4672
Design Operations Management | 4785.0532 | 349872.8234 | 6525.7599 | 477149.5649
Set up Project Infrastructure | 4718.7855 | 318149.784 | 6435.3853 | 433886.3177
Design Production Infrastructure | 918.0788 | 69154.2769 | 1252.0575 | 94311.2209
Validate Technical Architecture Design Deliverables | 2344.0603 | 244626.9618 | 3196.7826 | 333617.3621
Sign-off Technical Architecture Design Deliverables | 1448.2895 | 116740.2878 | 1975.1483 | 159208.0716
Build
Build Application
Build and Test Configuration | 34947.27 | 5286647.3654 | 42806.6632 | 6475576.8658
Perform Detailed Technical Design | 41320.3025 | 5716880.1137 | 62832.9643 | 8693269.4603
Cleanse Existing Data | 3583.2479 | 427855.1239 | 3583.2479 | 427855.1239
Plan Unit Test | 12824.5783 | 1377338.0357 | 17757.2634 | 1907100.0861
Build and Test RICEFW Components | 112093.8774 | 10699690.554 | 157621.6076 | 15045446.4172
Validate Application Build | 1899.2405 | 190014.631 | 2641.6634 | 264292.3246
Sign-off Application Build | 2848.8608 | 348152.6581 | 3962.4951 | 484247.3174
Build Technical Architecture
Maintain System Landscape (Project) | 5763.1552 | 513349.0548 | 7859.6759 | 700095.1826
Manage / Maintain Project Tools | 8644.7329 | 770023.5822 | 11789.5139 | 1050142.7739
Set up System Landscape (Production) | 5595.3075 | 428476.2252 | 7630.7685 | 584347.3136
Build and Test Security Components | 5865.4438 | 734625.1498 | 7999.1751 | 1001867.0992
Build and Test Execution Architecture Components | 4754.5735 | 334051.7907 | 6484.1924 | 455573.1567
Build and Test Operations Supervision Components | 4754.5735 | 334051.7907 | 6484.1924 | 455573.1567
Build and Test Operations Architecture Components | 5450.3648 | 381983.383 | 7433.0986 | 520941.3045
Maintain Project Infrastructure | 1935.2144 | 131718.5768 | 2639.2067 | 179635.1629
Set up Production Infrastructure | 4645.9911 | 318504.7225 | 6336.1099 | 434370.3758
Validate Technical Architecture Build | 501.1439 | 49282.781 | 683.4501 | 67210.8719
Sign-off Technical Architecture Build | 751.7159 | 68292.2197 | 1025.1751 | 93135.5646
Stabilize
Test Application
Prepare and Execute Assembly Test | 44460.0529 | 5662828.2259 | 59235.932 | 7544815.7444
Confirm Assembly-Tested Application | 851.7013 | 102150.0843 | 1134.7562 | 136098.7007
Sign-off Assembly-Tested Application | 1277.552 | 137338.6455 | 1702.1343 | 182981.8483
Prepare and Execute Product Test | 150059.674 | 15677864.8911 | 208385.2451 | 21771576.8071
Prepare and Execute Performance Test | 6061.4176 | 754477.0577 | 8461.503 | 1053220.6039
Perform Mock Conversion | 41341.2902 | 4105054.8359 | 41341.2329 | 4105049.1419
Confirm Product-Tested Application | 851.7013 | 112506.2767 | 1182.7427 | 156235.499
Sign-off Product-Tested Application | 851.7013 | 94448.0231 | 1182.7427 | 131158.318
Prepare and Execute User Acceptance Test | 7952.2957 | 938355.2089 | 10911.4983 | 1287535.2834
Validate User-Accepted Application | 100.7381 | 13088.2968 | 138.2247 | 17958.7045
Sign-off User-Accepted Application | 201.4763 | 27454.763 | 276.4495 | 37671.21
Test Technical Architecture
Maintain System Landscape (Project) | 3378.6801 | 306653.4277 | 4607.7764 | 418207.8168
Manage / Maintain Project Tools | 5957.1464 | 540678.412 | 8124.2373 | 737366.4138
Maintain System Landscape (Production) | 1613.932 | 165951.3296 | 2201.0482 | 226321.1071
Prepare and Execute String Test for Security | 5097.7275 | 524195.3204 | 6952.1789 | 714887.1028
Prepare and Execute String Test for Execution Architecture | 3663.9916 | 372747.9901 | 4996.8786 | 508346.2602
Prepare and Execute String Test for Operations Architecture | 6850.0713 | 696876.6771 | 9341.9904 | 950386.4864
Prepare and Execute String Test for Production Infrastructure | 3186.0797 | 318326.7045 | 4345.1118 | 434127.5984
Maintain Project Infrastructure | 1281.8194 | 89057.1704 | 1748.1197 | 121454.3894
Maintain Production Infrastructure | 1281.8194 | 89057.1704 | 1748.1197 | 121454.3894
Validate Tested Technical Architecture | 323.8998 | 35873.2047 | 441.728 | 48923.1596
Sign-off Tested Technical Architecture | 732.4682 | 71218.9024 | 998.9256 | 97126.9159
Test Training and Performance Support
Define Support Requirements | 7527.7873 | 1046093.0885 | 10266.2459 | 1426640.8497
Determine Impact on Production Operations | 3011.1149 | 420421.9615 | 4106.4984 | 573363.0697
Confirm Compliance with Operational Requirements | 3011.1149 | 411269.136 | 4106.4984 | 560880.6292
Develop Service Introduction Plan | 7527.7873 | 1059444.6124 | 10266.2459 | 1444849.3912
Prepare Production Operations for Application Deployment | 3011.1149 | 423777.845 | 4106.4984 | 577939.7565
Integrate With Production Operations | 6022.2298 | 847555.6899 | 8212.9967 | 1155879.513
Deploy
Go-Live Preparation
Plan for Deployment | 3602.3145 | 576805.1468 | 3602.3145 | 576805.1468
Prepare for Deployment | 3538.2255 | 556750.3124 | 3538.2255 | 556750.3124
Prepare for Migration | 3544.5091 | 448745.9547 | 3544.5091 | 448745.9547
Prepare for Production Simulation | 3495.8704 | 549128.1411 | 3495.8704 | 549128.1411
Authorize Deployment | 53.9028 | 9085.3449 | 53.9028 | 9085.3449
Go-Live Execution
Set Up Deployment Environment | 873.9985 | 85201.954 | 1032.8645 | 100689.0433
Assess Go-Live Readiness | 197.4908 | 31456.8133 | 197.4908 | 31456.8133
Execute Go-Live Plan | 169.4203 | 24427.6433 | 169.4203 | 24427.6433
Migrate to Production | 153.6131 | 12808.0125 | 153.6131 | 12808.0125
Perform Production Simulation | 6439.701 | 937888.0064 | 6439.7118 | 937889.5814
Convert Data | 2209.0788 | 201353.9451 | 2209.0788 | 201353.9451
Validate Deployed Application | 143.7351 | 20430.2518 | 143.7351 | 20430.2518
Sign-off Deployed Application | 219.4385 | 36455.9541 | 219.4385 | 36455.9541
Post Go-Live Support
Fine Tune Application | 4999.3502 | 619385.1053 | 6775.7867 | 839473.3664
Support Production Environment | 31410.101 | 2736153.5982 | 31410.101 | 2736153.5982
Total CC&B Solution Capital | 976851.6749 | 116337751.6154 | 1304210.3495 | 155784162.8299
Total CC&B Solution Capital | 976851.6749 | 116337751.6154 | 1304210.3495 | 155784162.8299
Cost Category | Original Business Case | Update Business Case | Variance | % Variance
Internal Labor | 101878454.984 | 132494850.1213 | 30616395.1372 | 30.05%
External Labor | 149610335.1657 | 195350650.0023 | 45740314.8366 | 30.57%
Other |  |  | 0
Facilities | 4637500 | 4637500 | 0
Billing Exceptions |  |  | 0
Contingency | 35186513.2725 | 46680051.0185 | 11493537.7461 | 32.66%
Software | 84764722.0424 | 84764722.0424 | 0 | 0%
Hardware | 11819616.4065 | 11819616.4065 | 0 | 0%
AFUDC | 33551282.0369 | 41708355.3538 | 8157073.3169 | 24.31%
Total | 421448423.9079 | 517455744.9447 | 96007321.0368 | 22.78%