## PSC SIR Report-Names Redacted
SIR APPLICATION REVIEW PROCESS
2014-09-30
PROJECT INFORMATION | [5 empty] | APPLICATION REVIEW |  | PRELIMINARY REVIEW |  | CESIR |  | SIR COSTS |  |  |  |  | FINAL COMMENTS
[6 empty] | 5-10 business days |  | 10-15 business days |  | up to 60 business days
Company | Case # | System Type | System Capacity (kW) | Net Metered | Protective Equipment | Start Date | End Date | Start Date | End Date | Start Date | End Date | CESIR Cost to Customer | Utility Interconnection Cost | Customer Interconnection Cost | Utility System Upgrade Costs | Customer System Upgrade Costs | Verification Testing Date | Final Letter of Acceptance Date | Any Con Ed Subsidiary Involvement | Project Complete (Y/N) | Comments
CENY-BK | 1308886 | PV | 3.4 | Yes | Inverter | 2012-04-26 | 2012-05-03 | 2012-05-03 | 2012-05-09 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | Cancelled | Case Cancelled 08/26/14
CENY-BK | 1310887 | PV | 5 | Yes | Inverter | 2012-05-04 | 2012-05-10 | 2012-05-10 | 2012-05-16 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | Cancelled | Case Cancelled 08/26/14
CENY-BK | 1318771 | PV | 6 | Yes | Inverter | 2012-06-06 | 2012-06-19 | 2012-06-19 | 2012-07-03 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Ho Chen Chien of Helios Energy Systems requested this job be put on hold until further notice.
CENY-BK | 1325737 | PV | 15.9 | Yes | Inverter | 2012-07-27 | 2012-08-14 | 2012-08-14 | 2012-08-22 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | Cancelled | Case Cancelled 08/26/14
CENY-BK | 1331680 | PV | 7.1 | YES | Inverter | 2012-08-07 | 2012-08-29 | 2012-08-29 | 2012-11-28 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | PENDING PV INSTALL
CENY-BK | 1337986 | PV | 8.4 | Yes | Inverter | 2012-09-04 | 2012-09-24 | 2012-09-24 | 2012-09-24 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | Cancelled | Case Cancelled 08/26/14
CENY-BK | 1344620 | PV | 3 | Yes | Inverter | 2012-09-27 | 2012-10-09 | 2012-10-09 | 2012-10-12 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending Application Documentations
CENY-BK | 1344642 | PV | 4 | Yes | Inverter | 2012-09-27 | 2012-11-27 | 2012-11-27 | 2012-11-27 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | Cancelled | Case Cancelled 08/26/14
CENY-BK | 1345972 | PV | 2.5 | Yes | Inverter | 2012-10-03 | 2012-10-10 | 2012-10-10 | 2012-10-18 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-17 | No | Complete | Pending Net Meter Install
CENY-BK | 1359426 | PV | 4.5 | Yes | Inverter | 2012-11-21 | 2012-11-26 | 2012-12-05 | 2012-12-05 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | Cancelled | Case Cancelled 10/1/14
CENY-BK | 1379835 | ICE | 100 | No | Inverter | 2013-05-03 | 2013-05-05 | 2013-05-06 | 2013-05-06 | 2013-05-06 | 2013-06-07 | 0 | 0 | 350 | 0 | 0 |  |  | No | in progress | PENDING - FULL CUSTOMER SUBMITAL
CENY-BK | 1379841 | ICE | 100 | No | Inverter | 2013-05-03 | 2013-05-05 | 2013-05-06 | 2013-05-06 | 2013-05-06 | 2013-06-07 | 0 | 0 | 350 | 0 | 0 |  |  | No | in progress | PENDING - FULL CUSTOMER SUBMITAL
CENY-BK | 1379842 | ICE | 100 | No | Inverter | 2013-05-03 | 2013-05-05 | 2013-05-06 | 2013-05-06 | 2013-05-06 | 2013-06-07 | 0 | 0 | 350 | 0 | 0 |  |  | No | in progress | PENDING - FULL CUSTOMER SUBMITAL
CENY-BK | 1379844 | ICE | 100 | No | Inverter | 2013-05-03 | 2013-05-05 | 2013-05-06 | 2013-05-06 | 2013-05-06 | 2013-06-07 | 0 | 0 | 350 | 0 | 0 |  |  | No | in progress | PENDING - FULL CUSTOMER SUBMITAL
CENY-BK | 1379846 | ICE | 100 | No | Inverter | 2013-05-03 | 2013-05-05 | 2013-05-06 | 2013-05-06 | 2013-05-06 | 2013-06-07 | 0 | 0 | 350 | 0 | 0 |  |  | No | in progress | PENDING - FULL CUSTOMER SUBMITAL
CENY-BK | 1384627 | PV | 11 | Yes | Inverter | 2013-03-03 | 2013-03-08 | 2013-03-08 | 2013-03-14 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | in progress | Pending PV Install
CENY-BK | 1384630 | PV | 4.2 | Yes | Inverter | 2013-04-04 | 2013-03-08 | 2013-03-14 | 2013-03-28 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending Application Documentations
CENY-BK | 1388460 | PV | 18 | Yes | Inverter | 2013-03-18 | 2013-03-20 | 2013-03-20 | 2013-03-25 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending PV Install
CENY-BK | 1421272 | PV | 4.2 | Yes | Inverter | 2013-05-14 | 2013-05-21 | 2013-05-21 | 2013-05-28 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | Cancelled | Case Cancelled 09/30/14
CENY-BK | 1425490 | PV | 5.6 | Yes | Inverter | 2013-05-23 | 2013-05-29 | 2013-05-29 | 2013-06-05 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-26 | No | Complete | Pending Verification & Close-out
CENY-BK | 1426708 | PV | 150 | Yes | Inverter | 2013-05-28 | 2013-06-04 | 2013-06-12 | 2012-06-12 | 2012-06-12 | 2013-10-01 | 0 | 0 | 0 | 0 | 0 |  |  | No | in progress | PENDING INSTALLATION OF PV INSTALLATION. - PROJECT UNDER CONSIDERATION, IF FINANCIALLY VIABLE - NO CHANGE
CENY-BK | 1516308 | PV | 3.6 | YES | Inverter | 2013-09-04 | 2013-09-17 | 2013-09-17 | 2013-10-23 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | PENDING PV INSTALL
CENY-BK | 1517438 | PV | 36 | Yes | Inverter | 2013-09-18 | 2013-10-14 | 2013-10-14 | 2013-10-14 | 2013-10-15 | 2013-11-01 | 0 | 0 | 0 | 0 | 0 |  | 2014-08-21 | No | Complete | Completed
CENY-BK | 1525013 | PV | 10 | Yes | Inverter | 2013-09-11 | 2013-09-23 | 2013-09-23 | 2013-09-23 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | in progress | PENDING -CUSTOMER READY FOR FINAL
CENY-BK | 1570445 | PV | 3.6 | Yes | Inverter | 2013-09-30 | 2013-10-07 | 2013-10-14 | 2013-10-28 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-07-28 | No | Complete | Pending Validation & Close-out
CENY-BK | 1574996 | PV | 5 | Yes | Inverter | 2013-10-04 | 2013-11-26 18:14 | 2013-10-14 | 2013-10-14 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | PENDING PV INSTALL
CENY-BK | 1577724 | PV | 3.3 | Yes | Inverter | 2013-10-07 | 2013-12-12 08:08 | 2013-11-04 | 2013-11-04 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | PENDING PV INSTALL
CENY-BK | 1577729 | PV | 2.5 | Yes | Inverter | 2013-10-07 | 2013-11-04 | 2013-11-12 | 2013-11-12 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Confirmation if case should remain active
CENY-BK | 1582150 | PV | 5 | Yes | Inverter | 2013-10-11 | 2013-11-05 | 2013-11-05 | 2013-11-05 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | PENDING PV INSTALL
CENY-BK | 1582291 | PV | 31.6 | Yes | Inverter | 2013-10-11 | 2013-12-03 | 2013-11-01 | 2013-11-01 | 2014-01-07 | 2014-01-15 | 0 | 0 | 0 | 0 | 0 |  |  | No | in progress | Emailed Contractor as to when he will be ready for the Pre-OPerational Test. Awaiting Contractor's response
CENY-BK | 1583261 | PV | 4 | Yes | Inverter | 2013-10-14 | 2013-11-26 17:47 | 2013-11-13 | 2013-11-13 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending completion of Retail Work.
CENY-BK | 1590355 | PV | 5 | Yes | Inverter | 2013-10-23 | 2013-11-26 17:40 | 2013-11-15 | 2013-11-15 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending completion of Retail Work
CENY-BK | 1590402 | PV | 30 | Yes | Inverter | 2013-10-23 | 2013-10-25 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | in progress | Waiting on customer
CENY-BK | 1590413 | PV | 20 | yes | Inverter | 2013-10-23 | 2013-11-09 | 2013-11-20 | 2013-11-20 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | Cancelled | Cancelled
CENY-BK | 1590757 | PV | 3.6 | Yes | Inverter | 2013-10-23 | 2013-11-26 17:31 | 2013-11-15 | 2013-11-15 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | PENDING PV INSTALL
CENY-BK | 1591608 | PV | 3 | Yes | Inverter | 2013-10-24 | 2013-11-26 17:26 | 2013-11-18 | 2013-11-18 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | PENDING PV INSTALL
CENY-BK | 1593498 | PV | 3.8 | Yes | Inverter | 2013-10-25 | 2013-12-04 17:55 | 2013-11-20 | 2013-11-20 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | PENDING PV INSTALL
CENY-BK | 1596078 | PV | 3 | Yes | Inverter | 2013-10-29 | 2013-12-04 18:00 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending Requested Documentation
CENY-BK | 1598085 | PV | 3 | Yes | Inverter | 2013-10-31 | 2013-11-01 | 2013-11-06 | 2013-11-25 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | in progress | Pending PV Install
CENY-BK | 1598106 | PV | 3.8 | Yes | Inverter | 2013-10-31 | 2013-12-04 18:02 | 2013-11-25 | 2013-11-25 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | PENDING PV INSTALL
CENY-BK | 1602454 | PV | 217 | Yes | Inverter | 2013-11-06 | 2013-12-04 18:07 | 2013-11-19 | 2013-11-19 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending Requested Documentation
CENY-BK | MC-100343 | PV | 7.2 | Yes | Inverter | 2014-04-29 | 2014-05-06 | 2014-06-30 | 2014-07-02 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-17 | No | Complete | Cloned from MC#75078 / Pending Net Meter Install
CENY-BK | MC-100802 | PV | 2.4 | YES | Inverter | 2014-09-19 | 2014-09-22 11:04 | 2014-09-22 11:05 | 2014-09-22 11:06 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit.
CENY-BK | MC-101117 | PV | 6 | YES | Inverter | 2014-09-22 | 2014-09-22 | 2014-09-26 | 2014-09-26 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit.
CENY-BK | MC-101896 | PV | 1 | Yes | Inverter | 2014-02-03 | 2014-02-10 | 2014-02-10 | 2014-03-03 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-18 | No | Complete | Cloned from MC#59551 / Pending Net Meter Install
CENY-BK | MC-101903 | PV | 2.8 | YES | Inverter | 2014-09-26 | 2014-09-26 | 2014-10-01 | 2014-10-01 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Emailed customer and Contractor regarding approved one line diagram
CENY-BK | MC-39072 | PV | 350 | YES | Inverter | 2013-05-29 | 2013-06-05 | 2013-06-26 | 2013-06-30 | 2013-07-11 | 2013-08-30 | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | awaiting for customer response for inspection - No Change
CENY-BK | MC-40230 | MT | 300 | NO | Inverter | 2012-10-06 | 2012-10-10 | 2012-10-12 | 2012-10-12 | 2012-10-11 | 2012-10-17 | 0 | 0 | 350 | 0 | 0 |  |  | No | IN PROGRESS | Waiting on customer for a verification test - No Change
CENY-BK | MC-40583 | FC | 400 | NO | Inverter | 2013-04-18 | 2013-06-03 | 2013-06-14 | 2013-06-14 | 2013-07-16 | 2013-08-23 | 0 | 0 | 350 | 0 | 0 |  |  | No | Cancelled | Cancelled
CENY-BK | MC-42021 | MT | 210 | NO | Inverter | 2013-08-12 | 2013-08-22 | 2013-08-23 | 2013-08-23 | 2013-10-11 | 2013-10-25 | 0 | 0 | 350 | 0 | 0 |  |  | No | IN PROGRESS | pending verification test - No Change
CENY-BK | MC-45738 | PV | 7.6 | Yes | Inverter | 2013-11-11 10:02 | 2013-11-18 | 2013-12-16 | 2014-01-13 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-10-14 | No | Complete | Pending Net Meter Install
CENY-BK | MC-46214 | PV | 2 | Yes | Inverter | 2013-11-12 21:59 | 2013-11-21 | 2013-12-19 | 2014-01-23 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-22 | No | Complete | Pending Net Meter Install
CENY-BK | MC-47024 | PV | 28 | Yes | Inverter | 2013-11-14 | 2013-11-25 | 2013-11-25 | 2013-11-25 | 2013-11-25 | 2013-12-17 | 0 | 0 | 0 | 0 | 0 |  | 2014-09-10 | No | Complete | Completed
CENY-BK | MC-47039 | PV | 10.2 | Yes | Inverter | 2013-11-14 18:40 | 2013-12-19 14:28 | 2013-12-19 | 2013-12-19 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | PENDING PV INSTALL
CENY-BK | MC-49084 | PV | 100 | Yes | Inverter | 2013-11-25 | 2013-12-04 | 2013-12-04 | 2013-12-04 | 2013-12-05 | 2013-12-10 | 0 | 0 | 0 | 0 | 0 |  |  | No | in progress | Pending cust. Completion of construction
CENY-BK | MC-49689 | PV | 6 | Yes | Inverter | 2013-11-27 | 2013-12-11 | 2013-12-11 | 2013-12-11 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | PENDING PV INSTALL
CENY-BK | MC-49894 | PV | 3.8 | Yes | Inverter | 2013-12-02 | 2013-12-11 | 2013-12-11 | 2013-12-11 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | PENDING PV INSTALL
CENY-BK | MC-51254 | PV | 6 | Yes | Inverter | 2013-12-07 | 2013-12-13 | 2013-12-13 | 2013-12-13 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | PENDING PV INSTALL
CENY-BK | MC-51266 | PV | 7.2 | Yes | Inverter | 2013-12-07 | 2013-12-13 | 2013-12-13 | 2013-12-13 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | PENDING PV INSTALL
CENY-BK | MC-53311 | PV | 100 | Yes | Inverter | 2013-12-17 | 2013-12-22 | 2014-01-05 | 2014-01-05 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | in progress | Waiting on customer
CENY-BK | MC-53314 | PV | 100 | Yes | Inverter | 2013-12-17 | 2013-12-22 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | in progress | Waiting on customer
CENY-BK | MC-53319 | PV | 75 | Yes | Inverter | 2013-12-17 | 2013-12-22 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | in progress | Waiting on customer
CENY-BK | MC-53671 | PV | 45 | Yes | Inverter | 2013-12-18 | 2013-12-19 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-07-18 | No | Complete | Job Completed
CENY-BK | MC-55022 | PV | 85 | Yes | Inverter | 2013-12-26 | 2014-01-02 | 2014-01-02 | 2014-01-02 | 2014-01-02 | 2014-01-16 | 0 | 0 | 0 | 0 | 0 |  | 2014-09-30 | No | Complete | Completed
CENY-BK | MC-55098 | PV | 120 | Yes | Inverter | 2013-12-27 | 2014-01-02 | 2014-01-02 | 2014-01-02 | 2014-01-02 | 2014-01-16 | 0 | 0 | 0 | 0 | 0 |  |  | No | in progress | Pending cust. Completion of construction
CENY-BK | MC-55451 | PV | 15 | Yes | Inverter | 2013-12-31 | 2014-01-09 | 2014-01-23 | 2014-01-23 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-09 | No | Complete | Pending Net Meter Install
CENY-BK | MC-55787 | PV | 170 | Yes | Inverter | 2014-01-03 | 2014-01-09 | 2014-01-09 | 2014-01-09 | 2014-01-09 | 2014-01-14 | 0 | 0 | 0 | 0 | 0 |  |  | No | Cancelled | Cancelled
CENY-BK | MC-56274 | PV | 3.6 | Yes | Inverter | 2014-02-20 12:39 | 2014-02-20 12:46 | 2014-03-17 13:31 | 2014-03-17 13:32 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending PV Install
CENY-BK | MC-57241 | PV | 3 | Yes | Inverter | 2014-02-19 11:45 | 2014-02-19 12:44 | 2014-02-19 12:47 | 2014-03-05 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending Application Documentations
CENY-BK | MC-57971 | PV | 3 | Yes | Inverter | 2014-01-17 | 2014-01-23 | 2014-01-23 | 2014-02-06 17:04 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | in progress | Pending PV Install
CENY-BK | MC-58248 | PV | 6 | Yes | Inverter | 2014-01-27 | 2014-02-07 | 2014-02-09 | 2014-02-24 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-22 | No | Complete | Pending Net Meter Install
CENY-BK | MC-58365 | PV | 3.1 | Yes | Inverter | 2014-02-07 17:00 | 2014-02-07 17:10 | 2014-02-07 17:14 | 2014-03-03 11:18 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending PV Install
CENY-BK | MC-59707 | PV | 3.6 | Yes | Inverter | 2014-01-29 08:13 | 2014-02-03 | 2014-02-10 11:34 | 2014-03-03 12:22 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-10 | No | Complete | Pending Net Meter Install
CENY-BK | MC-60123 | MT | 200 | NO | Inverter | 2014-03-12 | 2014-03-25 | 2014-04-01 | 2014-07-02 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | in progress | Waiting on customer
CENY-BK | MC-60622 | PV | 3 | Yes | Inverter | 2014-02-08 | 2014-02-15 18:16 | 2014-02-24 | 2014-03-11 12:41 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-28 | No | Complete | Pending Net Meter Install
CENY-BK | MC-61253 | PV | 4 | Yes | Inverter | 2014-02-21 14:24 | 2014-02-21 14:30 | 2014-02-21 14:33 | 2014-02-21 14:50 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending PV Install
CENY-BK | MC-63020 | PV | 154 | Yes | Inverter | 2014-02-19 11:37 | 2014-02-26 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Customer to submit application for DE review.
CENY-BK | MC-63640 | PV | 7 | Yes | Inverter | 2014-02-24 16:20 | 2014-02-28 | 2014-02-28 | 2014-03-12 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending Application Documentations
CENY-BK | MC-64188 | PV | 3.2 | Yes | Inverter | 2014-03-03 | 2014-03-10 | 2014-03-10 | 2014-03-21 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending Application Documentations
CENY-BK | MC-64421 | PV | 29.8 | Yes | Inverter | 2014-02-27 | 2014-03-10 | 2014-03-10 | 2014-03-10 | 2014-03-11 | 2014-03-25 | 0 | 0 | 0 | 0 | 0 |  | 2014-10-02 | No | Complete | Completed
CENY-BK | MC-64498 | PV | 100 | Yes | Inverter | 2014-02-28 | 2014-03-07 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | in progress | 1. Pending contact info for 1st Amendment,Signed Appendix A
CENY-BK | MC-64572 | PV | 5 | Yes | Inverter | 2014-03-03 | 2014-03-10 | 2014-03-10 | 2014-04-02 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | PENDING PV INSTALL
CENY-BK | MC-65728 | PV | 1.5 | Yes | Inverter | 2014-03-09 22:39 | 2014-04-09 | 2014-04-09 | 2014-04-10 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Case loaded as PSN3 and s/b PSN1-Pending Requested Docs
CENY-BK | MC-66724 | PV | 6 | Yes | Inverter | 2014-03-18 11:43 | 2014-03-20 | 2014-03-20 | 2014-04-04 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending Application Documentations
CENY-BK | MC-67538 | PV | 1192 | YES | Inverter | 2014-04-01 15:38 | 2014-04-01 16:20 | 2014-04-01 16:23 | 2014-04-01 | 2014-04-08 | 2014-04-22 | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer response to DE comments.
CENY-BK | MC-68448 | PV | 7.5 | Yes | Inverter | 2014-03-24 15:10 | 2014-04-03 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending Application Documentations
CENY-BK | MC-69299 | PV | 4.8 | Yes | Inverter | 2014-03-27 20:02 | 2014-04-03 | 2014-06-13 15:02 | 2014-06-13 15:03 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | PENDING PV INSTALL
CENY-BK | MC-69468 | PV | 384 | Yes | Inverter | 2014-03-28 17:42 | 2014-04-04 | 2014-04-04 | 2014-04-04 | 2014-05-23 | 2014-05-31 | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer response to DE comments - No Change
CENY-BK | MC-69575 | PV | 8 | Yes | Inverter | 2014-03-30 | 2014-04-04 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | in progress | Pending Application Documentations
CENY-BK | MC-70796 | PV | 3.2 | YES | Inverter | 2014-04-07 | 2014-04-11 | 2014-04-11 | 2014-05-13 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | PENDING PV INSTALL
CENY-BK | MC-71436 | PV | 3 | Yes | Inverter | 2014-04-09 | 2014-04-15 | 2014-05-19 | 2014-07-02 14:44 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | in progress | Pending PV Install
CENY-BK | MC-72019 | PV | 20 | YES | Inverter | 2014-04-11 | 2014-05-19 12:30 | 2014-05-19 12:32 | 2014-05-19 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending Requested Documentation
CENY-BK | MC-72483 | PV | 12 | Yes | Inverter | 2014-04-15 | 2014-04-21 | 2014-06-11 12:52 | 2014-06-11 14:40 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | in progress | Pending PV Install
CENY-BK | MC-72688 | PV | 31.6 | Yes | Inverter | 2014-04-15 | 2014-04-16 | 2014-04-17 | 2014-04-17 | 2014-04-21 | 2014-04-23 | 0 | 0 | 0 | 0 | 0 |  |  | No | in progress | Pending cust. Completion of construction
CENY-BK | MC-73521 | PV | 1.6 | YES | Inverter | 2014-04-21 | 2014-04-28 | 2014-05-16 | 2014-06-18 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | REQUESTING DOCUMENTS PENDING REVIEW
CENY-BK | MC-73974 | PV | 50 | YES | Inverter | 2014-04-23 | 2014-05-20 | 2014-09-18 | 2014-09-18 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-15 | No | COMPLETE | Job Completed
CENY-BK | MC-74387 | PV | 4 | YES | Inverter | 2014-04-25 | 2014-05-02 | 2014-08-22 11:03 | 2014-08-22 11:06 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending Requested Documentation
CENY-BK | MC-75045 | PV | 384 | yes | Inverter | 2014-04-29 | 2014-04-30 | 2014-06-16 | 2014-06-26 | 2014-06-26 | 2014-06-30 | 0 | 0 | 350 | 0 | 0 |  |  | NO | In Progress | DE is waitng on Cust Eng for alternate service to complete CESIR study to the customer.
CENY-BK | MC-75078 | PV | 6 | Yes | Inverter | 2014-04-29 | 2014-05-06 | 2014-06-30 | 2014-07-02 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-17 | No | Complete | Pending Net Meter Install under Cloned Case #100343
CENY-BK | MC-76581 | PV | 3 | YES | Inverter | 2014-05-07 | 2014-05-07 | 2014-05-07 | 2014-05-07 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | PENDING PV INSTALL
CENY-BK | MC-76629 | PV | 3 | Yes | Inverter | 2014-05-08 | 2014-05-15 | 2014-06-20 18:14 | 2014-06-20 18:15 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-10 | No | Complete | Pending Net Meter Install
CENY-BK | MC-76658 | ICE | 100 | No | Inverter | 2014-05-07 | 2014-05-21 | 2014-05-22 | 2014-06-03 |  |  | 0 | 0 | 350 | 0 | 0 |  |  | No | in progress | pending customer's revisions as per DE's prelim review.
CENY-BK | MC-76966 | PV | 3.2 | Yes | Inverter | 2014-05-08 | 2014-05-15 12:42 | 2014-07-08 10:47 | 2014-07-08 10:48 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-18 | No | Complete | Pending Net Meter Install
CENY-BK | MC-76992 | PV | 3 | YES | Inverter | 2014-05-08 | 2014-05-21 | 2014-08-15 15:07 | 2014-08-22 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending Requested Documentation
CENY-BK | MC-77643 | WT | 100 | YES | Inverter | 2014-05-13 | 2014-06-02 | 2014-06-02 | 2014-06-18 |  |  | 350 | 0 | 0 | 0 | 0 |  |  | No | in progress | Pending updated customer test procedure
CENY-BK | MC-78200 | PV | 5 | YES | Inverter | 2014-05-15 | 2014-05-16 12:31 | 2014-07-29 08:24 | 2014-08-07 12:36 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | PENDING REVIEW
CENY-BK | MC-79008 | PV | 64 | Yes | Inverter | 2014-04-16 | 2014-05-20 | 2014-05-20 | 2014-05-20 | 2014-05-20 | 2014-05-27 | 0 | 0 | 350 | 0 | 0 |  |  | No | in progress | Pending cust. Completion of construction
CENY-BK | MC-79549 | PV | 7 | YES | Inverter | 2014-05-22 | 2014-06-09 | 2014-07-29 |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | in progress | Waiting on customer to complete work
CENY-BK | MC-79680 | PV | 7 | YES | Inverter | 2014-05-23 | 2014-06-09 | 2014-07-29 |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | in progress | Waiting on customer to complete work
CENY-BK | MC-81559 | PV | 12.6 | YES | Inverter | 2014-06-04 | 2014-06-11 12:49 | 2014-06-11 12:51 | 2014-06-11 12:52 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | Submitted - Case Number Assigned
CENY-BK | MC-81906 | PV | 3.8 | YES | Inverter | 2014-06-05 | 2014-06-11 11:16 | 2014-06-11 11:20 | 2014-06-11 11:25 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | Submitted - Case Number Assigned
CENY-BK | MC-82400 | PV | 7 | YES | Inverter | 2014-06-09 | 2014-06-26 23:11 | 2014-06-26 23:12 | 2014-06-26 23:15 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | Submitted - Case Number Assigned
CENY-BK | MC-83290 | PV | 165 | YES | Inverter | 2014-06-12 | 2014-06-16 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | Cancelled | No progress - Case cancelled.
CENY-BK | MC-83450 | PV | 6 | YES | Inverter | 2014-06-13 | 2014-06-18 11:53 | 2014-06-18 11:57 | 2014-06-18 11:58 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | Submitted - Case Number Assigned
CENY-BK | MC-83684 | PV | 4 | YES | Inverter | 2014-06-16 | 2014-06-20 22:25 | 2014-06-20 22:27 | 2014-06-20 22:33 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | Submitted - Case Number Assigned
CENY-BK | MC-83847 | PV | 20 | YES | Inverter | 2014-06-16 | 2014-06-24 16:19 | 2014-06-24 16:20 | 2014-06-24 16:20 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | Submitted - Case Number Assigned
CENY-BK | MC-83850 | PV | 20 | YES | Inverter | 2014-06-16 | 2014-06-24 16:50 | 2014-06-24 16:51 | 2014-06-24 16:52 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | Submitted - Case Number Assigned
CENY-BK | MC-84090 | PV | 10.6 | YES | Inverter | 2014-06-17 | 2014-06-24 10:17 | 2014-06-24 10:19 | 2014-06-24 10:19 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | Submitted - Case Number Assigned
CENY-BK | MC-84120 | PV | 8.7 | YES | Inverter | 2014-06-17 | 2014-06-24 14:29 | 2014-06-24 14:33 | 2014-06-24 14:37 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | Submitted - Case Number Assigned
CENY-BK | MC-84337 | PV | 400 | yes | Inverter | 2014-06-18 | 2014-06-19 | 2014-06-19 | 2014-06-25 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | no | IN PROGRESS | Pending customer response to DE review comments
CENY-BK | MC-85371 | PV | 3 | YES | Inverter | 2014-06-24 | 2014-06-25 10:28 | 2014-06-25 10:29 | 2014-06-25 10:30 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | Submitted - Case Number Assigned
CENY-BK | MC-85419 | PV | 12.6 | YES | Inverter | 2014-06-24 | 2014-06-25 10:28 | 2014-06-25 10:29 | 2014-06-25 10:30 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | Cancelled | UNDER TEMP METER/ Customer has not submitted all necessary documents/pending customer
CENY-BK | MC-85669 | PV | 8 | YES | Inverter | 2014-06-25 | 2014-06-27 13:23 | 2014-06-27 13:32 | 2014-06-27 13:33 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | Submitted - Case Number Assigned
CENY-BK | MC-85900 | PV | 8.4 | YES | Inverter | 2014-06-26 | 2014-06-29 23:58 | 2014-06-30 | 2014-06-30 00:02 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | Submitted - Case Number Assigned
CENY-BK | MC-86094 | PV | 3 | YES | Inverter | 2014-06-27 | 2014-06-30 00:36 | 2014-06-30 00:37 | 2014-06-30 00:38 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | Submitted - Case Number Assigned
CENY-BK | MC-86305 | PV | 4 | YES | Inverter | 2014-06-30 | 2014-07-01 10:07 | 2014-07-01 10:09 | 2014-07-01 10:10 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | Submitted - Case Number Assigned
CENY-BK | MC-86420 | PV | 3 | YES | Inverter | 2014-06-30 | 2014-07-01 09:07 | 2014-07-01 09:08 | 2014-07-01 09:08 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | Submitted - Case Number Assigned
CENY-BK | MC-86527 | PV | 6.6 | YES | Inverter | 2014-07-01 | 2014-07-02 09:21 | 2014-07-02 09:23 | 2014-07-06 23:26 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-30 | NO | Complete | SBLI 025 entered/Meter exchanged. Case completed
CENY-BK | MC-86859 | PV | 6 | YES | Inverter | 2014-07-02 | 2014-07-03 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | Cancelled | Account # in accurate with address on application. Will calll customer to verify account #.
CENY-BK | MC-86868 | PV | 6 | YES | Inverter | 2014-07-02 | 2014-07-10 10:04 | 2014-07-10 10:05 | 2014-07-10 10:06 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit.
CENY-BK | MC-86869 | PV | 3 | YES | Inverter | 2014-07-02 | 2014-07-03 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | Cancelled | Cancellation Letter sent.
CENY-BK | MC-86954 | PV | 6 | YES | Inverter | 2014-07-03 | 2014-07-14 15:14 | 2014-07-14 15:15 | 2014-07-14 15:15 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit.
CENY-BK | MC-86956 | PV | 3 | YES | Inverter | 2014-07-03 | 2014-07-03 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | Cancelled | cancellation ltr. sent
CENY-BK | MC-87535 | PV | 34.2 | Yes | Inverter | 2014-07-08 | 2014-07-16 | 2014-07-16 | 2014-07-17 | 2014-07-17 | 2014-07-24 | 0 | 0 | 0 | 0 | 0 |  |  | No | in progress | Emailed cust. on 7/24 eng. comments. Awaiting cust. updates.
CENY-BK | MC-87832 | PV | 8 | YES | Inverter | 2014-07-09 | 2014-07-09 | 2014-07-14 | 2014-07-14 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | pending customer
CENY-BK | MC-87919 | PV | 25 | YES | Inverter | 2014-07-09 | 2014-07-09 | 2014-07-14 | 2014-07-14 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | Interconnection Letter sent to customer/contractor. Meter reuest sent to J. Minicozzi.
CENY-BK | MC-88646 | PV | 3 | YES | Inverter | 2014-07-14 | 2014-07-14 | 2014-07-21 | 2014-07-22 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit.
CENY-BK | MC-89002 | ICE | 100 | No | Inverter | 2014-07-15 | 2014-07-16 | 2014-08-05 | 2014-08-11 | 2014-08-13 | 2014-08-13 | 0 | 0 | 0 | 0 | 0 |  |  | No | in progress | Notified customer of Engineering comments on 8/13. Awaiting their updates.
CENY-BK | MC-89386 | PV | 3.6 | YES | Inverter | 2014-07-17 | 2014-07-17 | 2014-07-21 | 2014-07-21 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Customer states solar panels installed since 7/3/14, however all documents received on 7/17 in proj. center.
CENY-BK | MC-89419 | PV | 42 | YES | Inverter | 2014-07-17 | 2014-07-31 | 2014-10-21 |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | in progress | Pending Engineering Review
CENY-BK | MC-89468 | PV | 3.2 | YES | Inverter | 2014-07-17 | 2014-07-17 | 2014-07-21 | 2014-07-21 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit.
CENY-BK | MC-89576 | PV | 3.4 | YES | Inverter | 2014-07-18 | 2014-07-18 | 2014-07-21 | 2014-07-21 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Auhtorization received. Pending customer to complete work and submit Self-Certification Affidavit.
CENY-BK | MC-89593 | PV | 2.8 | YES | Inverter | 2014-07-18 | 2014-07-18 | 2014-07-23 | 2014-07-23 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit.
CENY-BK | MC-89940 | PV | 7.2 | YES | Inverter | 2014-07-21 | 2014-09-15 12:56 | 2014-09-15 12:57 | 2014-09-15 12:58 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit.
CENY-BK | MC-89998 | PV | 3.6 | YES | Inverter | 2014-07-21 | 2014-07-21 | 2014-07-24 | 2014-07-24 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit.
CENY-BK | MC-90105 | PV | 5.4 | YES | Inverter | 2014-07-22 | 2014-07-22 | 2014-07-24 | 2014-07-24 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit.
CENY-BK | MC-90389 | PV | 2.8 | YES | Inverter | 2014-07-23 | 2014-07-23 | 2014-07-25 | 2014-07-25 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit.
CENY-BK | MC-90394 | ICE | 75 | No | Induction | 2014-07-23 | [5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | No | Cancelled | Cancelled
CENY-BK | MC-90674 | PV | 11.8 | YES | Inverter | 2014-07-24 | 2014-07-24 | 2014-07-25 | 2014-07-25 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit.
CENY-BK | MC-91222 | PV | 43.5 | Yes | Inverter | 2014-07-28 | 2014-07-31 | 2014-08-01 | 2014-08-01 | 2014-08-01 | 2014-08-28 | 0 | 0 | 0 | 0 | 0 |  |  | No | in progress | Pending cust. Completion of construction
CENY-BK | MC-91290 | PV | 3 | YES | Inverter | 2014-07-28 | 2014-07-28 | 2014-08-01 | 2014-08-01 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Sent 1 line diagram approval.
CENY-BK | MC-91375 | PV | 7.6 | YES | Inverter | 2014-07-28 | 2014-07-28 | 2014-08-01 | 2014-08-01 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Sent 1 line diagram approval.
CENY-BK | MC-91380 | ICE | 100 | No | Inverter | 2014-09-26 | 2014-09-27 | 2014-09-27 | 2014-09-30 |  |  | 0 | 0 | 350 | 0 | 0 |  |  | No | in progress | pending dob permit and customer's revisions as per DE's prelim review.
CENY-BK | MC-91813 | PV | 3 | YES | Inverter | 2014-07-30 | 2014-07-30 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | Cancelled | CANCELLED
CENY-BK | MC-91835 | PV | 5 | YES | Inverter | 2014-07-30 | 2014-07-30 | 2014-08-01 | 2014-08-01 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval.
CENY-BK | MC-92386 | PV | 1.8 | YES | Inverter | 2014-08-04 | 2014-08-04 | 2014-08-06 | 2014-08-06 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Contractor requested for copy of line diagram approval again - request sent.
CENY-BK | MC-92535 | PV | 3 | YES | Inverter | 2014-08-04 | 2014-08-04 | 2014-08-06 | 2014-08-06 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Recieved full app. Sent line approval.
CENY-BK | MC-92538 | PV | 1978 | YES | Inverter | 2014-08-04 | 2014-08-05 | 2014-08-05 | 2014-08-25 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | in progress | Pending customer's response to DE review.
CENY-BK | MC-92766 | ICE | 75 | No | Induction | 2014-08-05 | 2014-08-05 | 2014-08-05 | 2014-08-29 |  |  | 350 | 0 | 0 | 0 | 0 |  |  | No | in progress | Contractor to submit revised items as per DE First Submittal Document from 8/29/14, CPM waiting for items.
CENY-BK | MC-93079 | PV | 20 | YES | Inverter | 2014-08-06 | 2014-08-06 | 2014-08-08 | 2014-08-08 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval
CENY-BK | MC-93095 | PV | 7.6 | YES | Inverter | 2014-08-06 | 2014-08-06 | 2014-08-08 | 2014-08-08 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval.
CENY-BK | MC-93449 | PV | 5 | YES | Inverter | 2014-08-08 | 2014-08-08 | 2014-08-12 | 2014-08-12 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval.
CENY-BK | MC-93858 | PV | 3 | YES | Inverter | 2014-08-11 | 2014-08-11 | 2014-08-12 | 2014-08-12 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Solar application & CE account number do not match. Told the solar contractor to have the solar applicant added to the CE account
CENY-BK | MC-94009 | PV | 40 | YES | Inverter | 2014-08-12 | 2014-08-14 | 2014-08-14 | 2014-08-29 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | in progress | Sent contract request for updated 3 line diagram to reflect field equipment findings.
CENY-BK | MC-94439 | PV | 2.4 | YES | Inverter | 2014-08-14 | 2014-08-14 | 2014-08-16 | 2014-08-16 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit. Sent Line Diagram approval ltr. to customer/contractor.
CENY-BK | MC-94512 | PV | 170 | Yes | Inverter | 2014-08-14 | 2014-08-27 | 2014-08-27 |  |  |  | 0 | 350 | 0 | 0 | 0 |  |  | No | in progress | PV system greater than load which will cause network protectors to trip Customer has to reduce size of PV system
CENY-BK | MC-94521 | PV | 3.2 | YES | Inverter | 2014-08-14 | 2014-08-14 | 2014-08-16 | 2014-08-16 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS
CENY-BK | MC-94530 | PV | 5.4 | YES | Inverter | 2014-08-14 | 2014-08-14 | 2014-08-16 | 2014-08-16 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit. Sent Line Diagram approval ltr. to customer/contractor.
CENY-BK | MC-94557 | PV | 7 | YES | Inverter | 2014-08-14 | 2014-08-14 | 2014-08-16 | 2014-08-16 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit. Sent Line Diagram approval ltr. to customer/contractor.
CENY-BK | MC-94577 | PV | 5.6 | YES | Inverter | 2014-08-14 | 2014-08-14 | 2014-08-16 | 2014-08-16 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit. Sent Line Diagram approval ltr. to customer/contractor.
CENY-BK | MC-94589 | PV | 6 | YES | Inverter | 2014-08-14 | 2014-08-14 | 2014-08-16 | 2014-08-16 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit. Sent Line Diagram approval ltr. to customer/contractor.
CENY-BK | MC-94615 | PV | 42.76 | YES | Inverter | 2014-08-14 | 2014-08-14 | 2014-08-16 | 2014-08-16 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Revised line diagram received - Pending customer to complete work and submit Self-Certification Affidavit.
CENY-BK | MC-94729 | PV | 63 | Yes | Inverter | 2014-08-15 | 2014-08-26 | 2014-08-26 | 2014-09-08 |  |  | 0 | 350 | 0 | 0 | 0 |  |  | No | in progress | Pending completion of customer construction
CENY-BK | MC-94779 | PV | 3 | YES | Inverter | 2014-08-15 | 2014-08-15 | 2014-08-16 | 2014-08-16 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit. Sent Line Diagram approval ltr. to customer/contractor.
CENY-BK | MC-94955 | PV | 3.2 | YES | Inverter | 2014-08-18 | 2014-08-18 | 2014-08-21 | 2014-08-21 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit. Sent Line Diagram approval ltr. to customer/contractor.
CENY-BK | MC-94969 | PV | 4 | YES | Inverter | 2014-08-18 | 2014-08-18 | 2014-08-21 | 2014-08-21 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit. Sent Line Diagram approval ltr. to customer/contractor.
CENY-BK | MC-95012 | PV | 54 | YES | Inverter | 2014-08-18 | 2014-09-09 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | in progress | Waiting on customer
CENY-BK | MC-95019 | PV | 54 | Yes | Inverter | 2014-08-18 | 2014-09-22 | 2014-09-22 | 2014-09-24 |  |  | 0 | 350 | 0 | 0 | 0 |  |  | No | in progress | Pending completion of customer construction
CENY-BK | MC-95026 | PV | 51.6 | Yes | Inverter | 2014-08-18 | 2014-08-28 | 2014-08-28 | 2014-09-26 | 2014-10-06 | 2014-10-06 | 0 | 0 | 350 | 0 | 0 |  |  | No | in progress | Pending cust. Completion of construction
CENY-BK | MC-95048 | PV | 36 | YES | Inverter | 2014-08-18 | 2014-08-26 |  |  |  |  | 350 | 0 | 0 | 0 | 0 |  |  | No | in progress | Pending 3-line diagram from customer
CENY-BK | MC-95106 | PV | 7.2 | YES | Inverter | 2014-08-18 | 2014-08-18 | 2014-08-21 | 2014-08-21 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit. Sent Line Diagram approval ltr. to customer/contractor.
CENY-BK | MC-95110 | PV | 2.8 | YES | Inverter | 2014-08-18 | 2014-08-18 | 2014-08-21 | 2014-08-21 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit. Sent Line Diagram approval ltr. to customer/contractor.
CENY-BK | MC-95344 | PV | 27 | YES | Inverter | 2014-08-19 | 2014-09-22 | 2014-09-22 | 2014-09-22 |  |  | 350 | 0 | 0 | 0 | 0 |  |  | No | in progress | Pending DE review
CENY-BK | MC-95546 | PV | 54 | YES | Inverter | 2014-10-10 | 2014-10-20 | 2014-10-20 |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | in progress | With DE for review.
CENY-BK | MC-95755 | PV | 6 | YES | Inverter | 2014-08-21 | 2014-08-21 | 2014-08-21 | 2014-08-21 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Sent customer/contractor reminder to rectify name on CIS.
CENY-BK | MC-96020 | PV | 3 | YES | Inverter | 2014-08-22 | 2014-08-22 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | Cancelled | CIS account does not match application name. pending customer
CENY-BK | MC-96241 | PV | 98 | YES | Inverter | 2014-08-25 | 2014-09-23 | 2014-09-23 | 2014-09-25 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | in progress | Solar contractor is currently following items on DE comments, still in progress with Solar installation.
CENY-BK | MC-96549 | PV | 3.8 | YES | Inverter | 2014-08-26 | 2014-08-28 10:20 | 2014-08-28 10:21 | 2014-08-28 10:22 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit. Sent Line Diagram approval ltr. to customer/contractor.
CENY-BK | MC-96575 | PV | 5 | YES | Inverter | 2014-08-26 | 2014-08-28 12:33 | 2014-08-28 12:35 | 2014-08-28 12:36 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit. Sent Line Diagram approval ltr. to customer/contractor.
CENY-BK | MC-96799 | PV | 4.2 | YES | Inverter | 2014-08-27 | 2014-08-27 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | Cancelled | Customer requesting to cancel case and will resubmit another.
CENY-BK | MC-97011 | PV | 4.2 | YES | Inverter | 2014-08-28 | 2014-08-28 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | Cancelled | As per customer's request - Cancel case Refer to MC-97423.
CENY-BK | MC-97177 | PV | 12.6 | YES | Inverter | 2014-08-29 | 2014-08-29 | 2014-09-03 | 2014-09-03 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit. Sent Line Diagram approval ltr. to customer/contractor
CENY-BK | MC-97423 | PV | 4.2 | YES | Inverter | 2014-09-03 | 2014-09-03 | 2014-09-05 | 2014-09-05 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit. Sent Line Diagram approval ltr. to customer/contractor.
CENY-BK | MC-97566 | PV | 3 | YES | Inverter | 2014-09-03 | 2014-09-03 | 2014-09-05 | 2014-09-05 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit. Sent Line Diagram approval ltr. to customer/contractor.
CENY-BK | MC-98024 | PV | 10 | YES | Inverter | 2014-09-04 | 2014-09-04 | 2014-09-05 | 2014-09-05 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit. Sent Line Diagram approval ltr. to customer/contractor.
CENY-BK | MC-98087 | PV | 3.2 | YES | Inverter | 2014-09-05 | 2014-09-05 | 2014-09-08 | 2014-09-08 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS
CENY-BK | MC-98096 | PV | 4 | YES | Inverter | 2014-09-05 | 2014-09-05 | 2014-09-08 | 2014-09-08 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit. Sent Line Diagram approval ltr. to customer/contractor.
CENY-BK | MC-98482 | PV | 9.2 | YES | Inverter | 2014-09-08 | 2014-09-08 | 2014-09-10 | 2014-09-10 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS
CENY-BK | MC-98618 | PV | 3.2 | YES | Inverter | 2014-09-08 | [5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | No | Cancelled | Case Cancelled 09/10/14
CENY-BK | MC-98778 | PV | 4 | YES | Inverter | 2014-09-09 | 2014-09-09 | 2014-09-10 | 2014-09-10 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | revision received. Pending customer to complete work and submit Self-Certification Affidavit.
CENY-BK | MC-98849 | PV | 2.8 | YES | Inverter | 2014-09-09 | 2014-09-09 | 2014-09-10 | 2014-09-10 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit. Sent Line Diagram approval ltr. to customer/contractor.
CENY-BK | MC-98967 | PV | 3.2 | YES | Inverter | 2014-09-10 | 2014-09-10 | 2014-09-12 | 2014-09-12 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit. Sent Line Diagram approval ltr. to customer/contractor.
CENY-BK | MC-99027 | PV | 5 | YES | Inverter | 2014-09-10 | 2014-09-10 | 2014-09-12 | 2014-09-12 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit. Sent Line Diagram approval ltr. to customer/contractor.
CENY-BX | 1232235 | PV | 75 | Yes | Inverter | 2011-06-24 | 2011-06-24 | 2011-06-24 | 2011-06-24 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | pending customer feedback
CENY-BX | 1248392 | MT | 65 | No | Relay | 2013-07-13 05:13 | 2011-08-29 |  |  |  |  | 0 | 0 | 350 | 0 | 0 | 2014-03-06 | 2014-03-06 | NO | Complete | Complete - close case out.
CENY-BX | 1248594 | MT | 75 | No | Relay | 2013-07-13 05:15 | 2011-08-01 | 2013-09-05 | 2013-09-05 |  |  | 0 | 0 | 350 | 0 | 0 |  |  | NO | In Progress | Pending customer build
CENY-BX | 1250543 | PV | 6 | Yes | Inverter | 2012-08-14 | 2014-07-24 | 2014-08-05 | 2014-08-05 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | Cancelled | No activity in over a year - 10 day cancellation issued
CENY-BX | 1267640 | MT | 7 | NO | Inverter | 2011-03-01 | 2011-03-02 | 2011-03-03 | 2011-03-03 | 2011-11-07 | 2011-11-28 | 0 | 0 | 350 | 0 | 0 |  |  | NO | In Progress | Pending Documents from Cust
CENY-BX | 1317818 | ICE | 450 | NO | INVERTER | 2013-08-07 | 2013-10-09 15:52 | 2013-10-09 15:54 | 2013-10-09 15:55 |  |  | 0 | 0 | 350 | 0 | 0 | 2014-07-23 | 2013-07-23 | NO | COMPLETE | Pre-Op test successfully completed on 8/27/14. Pending customer followup submital
CENY-BX | 1317984 | ICE | 150 | NO | Relay | 2012-06-05 | 2012-06-05 | 2012-06-05 | 2012-09-01 | 2012-09-01 | 2012-09-28 | 0 | 0 | 350 | 0 | 0 | 2013-07-13 | 2013-07-13 | NO | Complete | in progress
CENY-BX | 1335702 | MT | 18.8 | no | INVERTER | 2013-08-07 | 2013-01-16 | 2013-01-16 | 2013-01-16 |  |  | 0 | 0 | 350 | 0 | 0 | 2014-02-06 | 2014-02-06 | NO | Complete | Complete
CENY-BX | 1380200 | PV | 42 | Yes | Inverter | 2013-02-14 | 2013-02-18 | 2013-02-28 | 2013-03-01 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | in progress
CENY-BX | 1380201 | PV | 42 | Yes | Inverter | 2013-07-13 12:09 | 2013-02-18 | 2013-02-28 | 2013-03-01 |  |  | 0 | 0 | 0 | 0 | 0 | 2013-04-02 | 2013-04-02 | NO | Complete | Completed
CENY-BX | 1381323 | PV | 150 | Yes | Inverter | 2013-03-13 | 2013-04-04 | 2013-04-04 | 2013-04-14 | 2014-08-11 | 2014-09-08 | 0 | 0 | 350 | 0 | 0 |  |  | NO | In Progress | installation of system
CENY-BX | 1406819 | PV | 3.6 | Yes | Inverter | 2013-04-08 | 2013-04-22 | 2013-04-23 | 2013-04-22 |  |  | 0 | 0 | 0 | 0 | 0 | 2013-05-08 | 2013-05-08 | NO | Complete | Meter was exchange by M&T on 5/8/13. SBLI code changed on CIS. ALL COMPLETE.
CENY-BX | 1411524 | PV | 24 | Yes | Inverter | 2013-07-13 07:23 | 2013-04-19 | 2013-06-27 | 2013-06-27 |  |  | 0 | 0 | 0 | 0 | 0 | 2014-04-30 | 2014-08-13 | NO | Complete | Net meter installed-Pending cust work and verification testing
CENY-BX | 1414533 | PV | 4.2 | Yes | Inverter | 2013-04-25 | 2013-04-29 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-10-22 | NO | Complete | Completed and SBLI code verified.
CENY-BX | 1415081 | PV | 1979.6 | Yes | Inverter | 2013-04-26 | 2013-04-29 | 2013-05-23 | 2013-06-02 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | Cancelled | Resolved-Cancelled
CENY-BX | 1427113 | PV | 500 | Yes | Inverter | 2013-05-29 | 2013-06-19 | 2013-06-19 | 2013-06-19 | 2013-06-19 | 2013-07-10 | 0 | 0 | 127740.37 | 0 | 0 |  |  | NO | In Progress | PENDING CUSTOMER PAYMENT (Work in conjunction with MC-16479)
CENY-BX | 1427116 | PV | 500 | Yes | Inverter | 2013-05-29 | 2013-06-20 | 2013-06-20 | 2013-06-19 | 2013-06-19 | 2013-07-10 | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | PENDING CUSTOMER PAYMENT (Work in conjunction with MC-16478, see cost on that case)
CENY-BX | 1430278 | PV | 200 | Yes | Inverter | 2013-06-06 | 2013-07-18 | 2013-07-18 | 2013-07-19 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | YES | In Progress | Pending customer feedback
CENY-BX | 1430279 | PV | 100 | Yes | Inverter | 2013-06-06 | 2013-06-08 | 2013-07-01 | 2013-07-19 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | YES | In Progress | Pending Customer feedback
CENY-BX | 1433909 | PV | 3.2 | Yes | Inverter | 2013-06-17 | 2013-06-19 | 2013-07-18 | 2013-07-19 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | Approved - Pending Net Meter
CENY-BX | 1437172 | PV | 32.8 | Yes | Inverter | 2013-06-25 | 2013-07-01 | 2013-07-18 | 2013-07-18 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | Pending customer docs
CENY-BX | 1438541 | PV | 54 | Yes | Inverter | 2013-06-28 | 2013-06-02 | 2013-06-28 | 2013-07-18 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | Pending Engineering
CENY-BX | 1442305 | PV | 360 | Yes | Inverter | 2013-07-11 | 2013-07-15 | 2013-09-05 | 2013-09-05 | 2013-09-05 | 2013-09-26 | 0 | 0 | 0 | 0 | 32647.73 |  |  | NO | In Progress | RELEASED SERVICE UPGRADE WORK TO WM - MC-79901
CENY-BX | 1442306 | PV | 600 | Yes | Inverter | 2013-07-11 | 2013-07-12 | 2013-07-14 | 2013-07-23 | 2013-07-23 | 2013-08-13 | 0 | 0 | 90056.35 | 0 | 0 | 2014-08-28 | 2014-09-12 | NO | Complete | PENDING MTR OPS TO COMP TASK IN SYSTEM
CENY-BX | MC-100225 | PV | 84 | Yes | Inverter | 2014-09-16 | 2014-09-16 | 2014-10-16 |  |  |  | 0 | 0 | 350 | 0 | 0 |  |  | NO | IN PROGRESS | Installation of an 87.975 kw PV system
CENY-BX | MC-100619 | PV | 3.8 | Yes | Inverter | 2014-09-18 | 2014-09-19 07:28 | 2014-09-19 07:28 | 2014-09-19 07:28 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending PV installation
CENY-BX | MC-100840 | PV | 3.2 | Yes | Inverter | 2014-09-19 | 2014-09-23 07:12 | 2014-09-23 07:13 | 2014-09-23 07:14 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval
CENY-BX | MC-101379 | PV | 6 | Yes | Inverter | 2014-09-23 | 2014-09-24 09:43 | 2014-09-24 09:43 | 2014-09-24 09:45 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval
CENY-BX | MC-101550 | PV | 3 | Yes | Inverter | 2014-09-24 | 2014-09-24 14:30 | 2014-09-24 14:31 | 2014-09-24 14:32 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval
CENY-BX | MC-101868 | PV | 70 | Yes | Inverter | 2014-09-25 | 2014-09-25 | 2014-10-16 |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Installation of a 85.68 kw solar pv system
CENY-BX | MC-101984 | PV | 2.4 | Yes | Inverter | 2014-09-26 | 2014-09-29 09:53 | 2014-09-29 09:54 | 2014-09-29 09:55 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval.
CENY-BX | MC-15409 | ICE | 300 | NO | INVERTER | 2013-08-07 | 2013-08-14 | 2014-06-03 | 2014-06-16 |  |  | 0 | 0 | 350 | 0 | 0 |  |  | NO | In Progress | waiting for customer to submit city certificate
CENY-BX | MC-1573 | ICE | 75 | NO | INVERTER | 2013-08-06 | 2013-08-13 |  |  |  |  | 0 | 0 | 350 | 0 | 0 |  |  | NO | Cancelled | Cancelled case. No activity since 2011 and no documentation. Remove from list
CENY-BX | MC-18926 | PV | 6 | Yes | Inverter | 2013-07-24 | 2013-07-30 | 2013-08-20 | 2013-08-20 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | Pending customer installation
CENY-BX | MC-20977 | PV | 40 | Yes | Inverter | 2013-08-16 | 2013-08-23 | 2013-09-02 | 2013-09-02 | 2013-09-02 | 2013-12-20 | 0 | 0 | 0 | 0 | 0 | 2014-08-25 |  | NO | IN PROGRESS | pending 1st ammendment and Appendix A signed
CENY-BX | MC-20979 | PV | 30 | Yes | Inverter | 2013-08-16 | 2013-08-23 | 2013-09-03 | 2013-09-03 | 2013-09-04 | 2013-12-20 | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | Pending customer installation
CENY-BX | MC-20983 | PV | 40 | Yes | Inverter | 2013-08-16 | 2013-08-23 | 2013-09-02 | 2013-09-02 | 2013-09-02 | 2013-12-20 | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | pending DOB inspection results
CENY-BX | MC-20987 | PV | 20 | Yes | Inverter | 2013-08-16 | 2013-08-23 | 2013-09-03 | 2013-09-03 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | Pending customer installation
CENY-BX | MC-20991 | PV | 30 | Yes | Inverter | 2013-08-16 | 2013-08-23 | 2013-09-03 | 2013-09-03 | 2013-09-03 | 2013-12-20 | 0 | 0 | 0 | 0 | 0 | 2014-08-25 |  | NO | In Progress | Pending customer corrections of electrical installation
CENY-BX | MC-20995 | PV | 40 | Yes | Inverter | 2013-08-16 | 2013-08-23 | 2013-09-02 | 2013-09-02 | 2013-09-02 | 2013-12-20 | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | Pending customer installation
CENY-BX | MC-20998 | PV | 30 | Yes | Inverter | 2013-08-16 | 2013-08-23 | 2013-09-03 | 2013-09-03 | 2013-09-03 | 2013-12-20 | 0 | 0 | 0 | 0 | 0 | 2014-09-02 | 2014-10-01 | NO | Complete | Complete - close case out.
CENY-BX | MC-21002 | PV | 20 | Yes | Inverter | 2013-08-16 | 2013-08-23 | 2013-09-19 | 2013-09-19 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | Pending customer installation
CENY-BX | MC-21007 | PV | 20 | Yes | Inverter | 2013-08-16 | 2013-09-19 | 2013-09-19 | 2013-09-19 |  |  | 0 | 0 | 0 | 0 | 0 | 2014-09-02 | 2014-09-02 | NO | Complete | Complete - close case out.
CENY-BX | MC-21009 | PV | 20 | Yes | Inverter | 2013-08-16 | 2013-08-23 | 2013-09-02 | 2013-09-02 |  |  | 0 | 0 | 0 | 0 | 0 | 2014-10-06 | 2014-10-08 | NO | Complete | Complete - close case out.
CENY-BX | MC-21011 | PV | 40 | Yes | Inverter | 2013-08-16 | 2013-08-19 | 2013-09-02 | 2013-09-02 | 2013-09-02 | 2013-12-20 | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | Pending documents for correction and installation
CENY-BX | MC-21013 | PV | 40 | Yes | Inverter | 2013-08-16 | 2013-08-23 | 2013-09-02 | 2013-09-02 | 2013-09-02 | 2013-12-20 | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | Pending documents for correction and installation
CENY-BX | MC-21017 | PV | 20 | Yes | Inverter | 2013-08-16 | 2013-08-23 | 2013-12-17 09:11 | 2013-12-17 09:12 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | Pending customer installation
CENY-BX | MC-21031 | PV | 20 | Yes | Inverter | 2013-08-16 | 2013-08-23 | 2013-09-17 07:55 | 2013-12-17 08:25 |  |  | 0 | 0 | 0 | 0 | 0 | 2014-09-02 | 2014-09-02 | NO | Complete | Complete - close case out.
CENY-BX | MC-21032 | PV | 40 | Yes | Inverter | 2013-08-16 | 2013-08-23 | 2013-09-17 07:45 | 2013-09-27 | 2013-09-27 | 2013-12-20 | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | Pending documents for correction and installation
CENY-BX | MC-21033 | PV | 40 | Yes | Inverter | 2013-08-19 | 2013-08-23 | 2013-08-26 | 2013-08-26 | 2013-08-26 | 2013-12-20 | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | Pending customer installation
CENY-BX | MC-21034 | PV | 20 | Yes | Inverter | 2013-08-19 | 2013-08-23 | 2013-08-23 | 2013-08-23 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | pending documents for installation
CENY-BX | MC-21707 | PV | 480 | Yes | Inverter | 2013-08-26 | 2013-08-30 | 2013-09-03 | 2013-10-16 | 2013-09-02 | 2013-10-01 | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | Pending CUSTOMER INSTALLATION
CENY-BX | MC-23139 | PV | 20 | Yes | Inverter | 2013-09-11 | 2013-09-12 | 2013-09-12 | 2013-09-12 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | Pending customer installation
CENY-BX | MC-33396 | PV | 6 | Yes | Inverter | 2013-09-27 | 2013-10-07 | 2013-10-07 | 2013-10-07 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | Installation complete - pending final documents from cust
CENY-BX | MC-33412 | PV | 4.2 | Yes | Inverter | 2013-09-27 | 2013-10-03 | 2013-10-03 | 2013-10-03 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | Pending customer installation
CENY-BX | MC-34894 | PV | 21 | Yes | Inverter | 2013-10-08 14:50 | 2013-10-23 08:18 | 2013-10-23 08:17 | 2014-03-11 18:06 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | Pending customer 3 line revision to proceed
CENY-BX | MC-35481 | PV | 750 | Yes | Inverter | 2013-10-11 | 2013-10-12 | 2014-01-10 | 2014-01-10 | 2014-01-27 | 2014-07-11 | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | PENDING CUSTOMER PAYMENT
CENY-BX | MC-35676 | PV | 40 | Yes | Inverter | 2013-10-15 13:25 | 2013-10-21 09:16 | 2013-10-21 | 2013-10-21 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | pending customer installation
CENY-BX | MC-36858 | PV | 6 | Yes | Inverter | 2013-10-24 08:49 | 2013-10-28 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | Pending documents from customer
CENY-BX | MC-46572 | PV | 6.5 | Yes | Inverter | 2013-11-13 10:22 | 2013-11-15 09:28 | 2013-11-15 09:30 | 2013-11-15 09:31 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | waiting for customer to submit city certificate
CENY-BX | MC-46577 | PV | 4 | Yes | Inverter | 2013-11-13 10:32 | 2013-11-15 14:40 | 2013-11-15 14:42 | 2013-11-15 14:43 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | waiting for customer to submit city certificate
CENY-BX | MC-46580 | PV | 5 | Yes | Inverter | 2013-11-13 10:45 | 2013-12-05 14:03 | 2013-12-05 14:08 | 2014-02-06 10:04 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | waiting for customer to submit city certificate
CENY-BX | MC-48620 | PV | 7.8 | Yes | Inverter | 2013-11-22 08:20 | 2013-11-22 15:36 | 2013-11-22 15:39 | 2013-11-22 15:40 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | waiting for customer to submit city certificate
CENY-BX | MC-54520 | PV | 30 | Yes | Inverter | 2013-12-20 | 2013-12-27 | 2014-01-20 | 2014-02-19 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | case is with Dist. Engineering
CENY-BX | MC-55058 | PV | 300 | Yes | Inverter | 2013-12-26 | 2014-01-02 | 2014-01-13 | 2014-01-13 | 2014-01-28 | 2014-02-03 | 0 | 0 | 0 | 0 | 0 |  |  | NO | Cancelled | Resolved-Cancelled
CENY-BX | MC-56387 | PV | 34.2 | Yes | Inverter | 2014-01-08 07:49 | 2014-01-15 | 2014-07-25 | 2014-07-25 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | Waiting for customer to submit proper documents
CENY-BX | MC-56613 | PV | 4.8 | Yes | Inverter | 2014-01-10 09:16 | 2014-01-10 09:25 | 2014-01-10 09:26 | 2014-01-10 09:27 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | waiting for customer to submit city certificate
CENY-BX | MC-58615 | PV | 3.6 | Yes | Inverter | 2014-01-21 15:02 | 2014-01-23 12:33 | 2014-01-23 12:34 | 2014-02-06 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | wating for customer to submit city certificate
CENY-BX | MC-58625 | PV | 4.3 | Yes | Inverter | 2014-01-21 14:59 | 2014-01-22 14:15 | 2014-01-22 14:16 | 2014-02-05 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | wating for customer to submit city certificate
CENY-BX | MC-61880 | MT | 65 | NO | Inverter | 2014-03-24 14:27 | 2014-03-25 08:43 | 2014-03-25 08:51 | 2014-04-08 | 2014-02-14 | 2014-05-15 | 0 | 0 | 350 | 0 | 0 |  |  | NO | In Progress | Waiting on customer to submit city certificate, we can then order meter
CENY-BX | MC-63186 | WT | 20 | Yes | Inverter | 2014-02-20 11:03 | 2014-02-27 |  |  |  |  | 0 | 0 | 350 | 0 | 0 |  |  | NO | In Progress | Pending CUSTOMER. Project still on hold
CENY-BX | MC-64087 | PV | 6 | Yes | Inverter | 2014-02-27 08:02 | 2014-03-28 13:17 | 2014-03-28 13:19 | 2014-03-28 13:20 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | PENDING CUSTOMER
CENY-BX | MC-66094 | PV | 3 | YES | Inverter | 2014-03-12 08:36 | 2014-03-20 10:49 | 2014-03-20 10:51 | 2014-03-20 10:53 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | pending meter order
CENY-BX | MC-67782 | PV | 3.6 | Yes | Inverter | 2014-03-20 10:55 | 2014-03-27 | 2014-04-11 14:25 | 2014-04-11 14:27 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | awaiting final documents from contractor
CENY-BX | MC-68694 | PV | 25 | Yes | Inverter | 2014-03-25 13:59 | 2014-04-01 | 2014-04-14 15:23 | 2014-04-14 15:25 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | awaiting final documents from contractor
CENY-BX | MC-70791 | PV | 3.2 | Yes | Inverter | 2014-04-07 | 2014-04-11 14:57 | 2014-04-11 15:39 | 2014-04-11 15:40 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | Pending customer build
CENY-BX | MC-70792 | PV | 2.8 | Yes | Inverter | 2014-04-07 | 2014-05-23 07:49 | 2014-05-23 07:50 | 2014-05-23 07:52 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | Pending customer build
CENY-BX | MC-71217 | PV | 80 | Yes | Inverter | 2014-04-08 | 2014-04-14 | 2014-05-28 | 2014-06-11 |  |  | 350 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | Check received, engineering DE is reviewiing case
CENY-BX | MC-71349 | PV | 27 | Yes | Inverter | 2014-04-08 | 2014-04-17 | 2014-09-10 | 2014-09-10 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | in progress
CENY-BX | MC-73778 | PV | 3 | Yes | Inverter | 2014-04-22 | 2014-04-24 11:00 | 2014-04-24 11:04 | 2014-04-24 11:06 |  |  | 0 | 0 | 0 | 0 | 0 | 2014-06-20 | 2014-07-23 | NO | Complete | Sent to CPMS Admin. To progress pass meter order
CENY-BX | MC-75714 | PV | 3 | Yes | Inverter | 2014-05-02 | 2014-05-05 07:56 | 2014-05-05 08:05 | 2014-05-05 08:08 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | waiting on customer to submit city certificate
CENY-BX | MC-75769 | PV | 3.6 | Yes | Inverter | 2014-05-02 | 2014-05-05 12:35 | 2014-05-05 12:37 | 2014-05-05 12:39 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | waiting on customer to submit city certificate
CENY-BX | MC-75836 | ICE | 75 | NO | Induction | 2014-05-02 | 2014-05-14 | 2014-05-14 | 2014-06-09 |  |  | 0 | 0 | 350 | 0 | 0 |  |  | NO | In Progress | case is with Dist. Engineering
CENY-BX | MC-76426 | PV | 5.4 | Yes | Inverter | 2014-05-06 | 2014-05-07 15:04 | 2014-05-07 15:08 | 2014-05-07 15:10 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | PENDING CUSTOMER
CENY-BX | MC-76660 | PV | 3.2 | Yes | Inverter | 2014-05-07 | 2014-05-12 09:15 | 2014-05-12 09:19 | 2014-05-12 09:22 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | PENDING CUSTOMER
CENY-BX | MC-76692 | PV | 3.2 | Yes | Inverter | 2014-05-07 | 2014-05-09 09:19 | 2014-05-09 09:23 | 2014-05-09 09:26 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | PENDING CUSTOMER
CENY-BX | MC-76818 | PV | 4.4 | Yes | Inverter | 2014-05-08 | 2014-05-09 10:10 | 2014-05-09 10:37 | 2014-05-09 10:41 |  |  | 0 | 0 | 0 | 0 | 0 | 2014-08-21 | 2014-08-25 | NO | Complete | Complete - close case out.
CENY-BX | MC-76887 | PV | 2.6 | Yes | Inverter | 2014-05-08 | 2014-05-12 09:52 | 2014-05-12 09:56 | 2014-05-12 09:58 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | PENDING CUSTOMER
CENY-BX | MC-77210 | ICE | 75 | NO | Induction | 2014-05-09 | 2014-05-12 | 2014-05-15 | 2014-06-11 |  |  | 0 | 0 | 350 | 0 | 0 |  |  | NO | In Progress | case is with Dist. Engineering
CENY-BX | MC-77825 | PV | 9 | Yes | Inverter | 2014-05-13 | 2014-06-06 13:17 | 2014-06-06 13:18 | 2014-06-06 13:19 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | Service date pushed back
CENY-BX | MC-78942 | PV | 300 | Yes | Inverter | 2014-05-20 | 2014-05-23 11:06 | 2014-05-23 11:07 | 2014-06-10 | 2014-09-23 |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | PENDING CUSTOMER REVISED DRAWINGS
CENY-BX | MC-79102 | PV | 2.6 | Yes | Inverter | 2014-05-21 | 2014-05-23 13:56 | 2014-05-23 14:10 | 2014-05-23 14:11 |  |  | 0 | 0 | 0 | 0 | 0 | 2014-05-23 | 2014-09-14 | NO | Complete | Complete SBLI account set
CENY-BX | MC-79374 | PV | 2.8 | Yes | Inverter | 2014-05-22 | 2014-05-23 14:43 | 2014-05-23 14:43 | 2014-05-23 14:44 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | waiting on customer to submit city certificate
CENY-BX | MC-80119 | PV | 60 | Yes | Inverter | 2014-05-28 | 2014-05-30 | 2014-10-16 | 2014-10-16 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | Cancelled | cancelled
CENY-BX | MC-80219 | PV | 4.4 | Yes | Inverter | 2014-05-28 | 2014-05-29 09:31 | 2014-05-29 09:32 | 2014-05-29 09:33 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | waiting on customer to submit city certificate
CENY-BX | MC-81023 | PV | 3.2 | Yes | Inverter | 2014-06-02 | 2014-06-02 14:58 | 2014-06-02 14:59 | 2014-06-02 14:59 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending PV installation
CENY-BX | MC-81055 | PV | 2.4 | Yes | Inverter | 2014-06-02 | 2014-06-02 15:22 | 2014-06-02 15:23 | 2014-06-02 15:24 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending PV installation
CENY-BX | MC-81892 | PV | 14 | Yes | Inverter | 2014-06-05 | 2014-06-06 09:39 | 2014-06-06 09:52 | 2014-06-11 07:26 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending PV installation
CENY-BX | MC-82540 | PV | 20 | Yes | Inverter | 2014-06-10 | 2014-06-10 11:34 | 2014-06-10 11:35 | 2014-07-01 10:17 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-15 | No | Complete | Complete
CENY-BX | MC-87032 | PV | 4.2 | Yes | Inverter | 2014-07-03 | 2014-07-07 14:05 | 2014-07-07 14:06 | 2014-07-07 14:06 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Contractor to submit final docs.
CENY-BX | MC-87044 | PV | 4 | Yes | Inverter | 2014-07-03 | 2014-07-07 14:34 | 2014-07-10 07:11 | 2014-07-10 07:11 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Recieved full app & revised DWG. Sent line diagram approval.
CENY-BX | MC-87063 | PV | 5 | Yes | Inverter | 2014-07-03 | 2014-07-07 14:56 | 2014-07-07 14:57 | 2014-07-07 14:57 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending final docs.
CENY-BX | MC-88359 | PV | 5 | Yes | Inverter | 2014-07-11 | 2014-07-11 13:45 | 2014-07-11 13:45 | 2014-07-11 13:45 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval
CENY-BX | MC-89052 | PV | 193.2 | Yes | Inverter | 2014-07-16 | 2014-08-07 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | PENDING FULL APP
CENY-BX | MC-89494 | PV | 4.2 | Yes | Inverter | 2014-07-17 | 2014-07-18 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | PENDING FULL APP
CENY-BX | MC-91009 | PV | 40 | Yes | Inverter | 2014-07-25 | 2014-08-26 | 2014-09-03 | 2014-09-03 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | review comments by DE sent to customer to make changes before final approval.
CENY-BX | MC-91347 | PV | 222.6 | Yes | Inverter | 2014-07-28 | [5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | NO | Cancelled | Cancelled
CENY-BX | MC-91348 | PV | 60 | Yes | Inverter | 2014-07-28 | 2014-07-28 | 2014-09-04 | 2014-09-12 |  |  | 350 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Check received, engineering DE is reviewiing case
CENY-BX | MC-91361 | PV | 60 | Yes | Inverter | 2014-07-28 | 2014-08-26 | 2014-09-03 | 2014-09-09 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | review comments by DE sent to customer to make changes before final approval.
CENY-BX | MC-91364 | PV | 9 | Yes | Inverter | 2014-07-28 | 2014-07-29 09:35 | 2014-07-29 09:39 | 2014-07-29 09:39 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval.
CENY-BX | MC-91369 | PV | 40 | Yes | Inverter | 2014-07-28 | 2014-08-26 | 2014-09-03 | 2014-09-09 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | review comments by DE sent to customer to make changes before final approval.
CENY-BX | MC-92705 | PV | 4.6 | Yes | Inverter | 2014-08-05 | 2014-08-07 11:11 | 2014-08-07 11:11 | 2014-08-07 11:11 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval.
CENY-BX | MC-92992 | PV | 2.4 | Yes | Inverter | 2014-08-06 | 2014-08-06 13:18 | 2014-08-06 13:20 | 2014-08-06 13:20 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval.
CENY-BX | MC-93395 | MT | 130 | NO | Inverter | 2014-08-08 | 2014-10-15 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending Documents to complete SIR package
CENY-BX | MC-93734 | PV | 6.8 | Yes | Inverter | 2014-08-11 | 2014-08-11 14:52 | 2014-08-14 13:03 | 2014-08-14 13:03 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to the application. Still require Form G.
CENY-BX | MC-94070 | PV | 3 | Yes | Inverter | 2014-08-12 | 2014-08-14 06:56 | 2014-08-14 06:57 | 2014-08-14 06:57 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval
CENY-BX | MC-94408 | PV | 6.4 | Yes | Inverter | 2014-08-14 | 2014-08-14 10:41 | 2014-08-14 13:07 | 2014-08-14 13:07 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Sent 1 line diagram approval.
CENY-BX | MC-95042 | PV | 45 | Yes | Inverter | 2014-08-18 | 2014-10-16 |  |  |  |  | 0 | 0 | 350 | 0 | 0 |  |  | NO | IN PROGRESS | Interconnection of Photovoltaic electricity generating system.
CENY-BX | MC-95056 | PV | 63 | Yes | Inverter | 2014-08-18 | 2014-10-16 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Interconnection of Photovoltaic electricity generating system.
CENY-BX | MC-95088 | PV | 3.6 | Yes | Inverter | 2014-08-18 | 2014-08-19 07:16 | 2014-08-19 07:16 | 2014-08-19 07:16 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Prepared mtr reservation. Pending final docs.
CENY-BX | MC-95126 | PV | 156 | Yes | Inverter | 2014-08-18 | 2014-08-20 12:10 | 2014-08-26 10:57 | 2014-09-29 09:14 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | gave to Milano for appt 10/8/14
CENY-BX | MC-95343 | PV | 3 | Yes | Inverter | 2014-08-19 | 2014-08-20 12:37 | 2014-08-20 12:37 | 2014-08-20 12:37 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Prepared mtr reservation. Pending final docs.
CENY-BX | MC-95539 | PV | 36 | Yes | Inverter | 2014-08-20 | 2014-10-16 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Interconnection of Photovoltaic electricity generating system
CENY-BX | MC-95988 | ICE | 1899 | NO | Induction | 2014-08-22 | 2014-09-02 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | reviewed 1 line & sent to DE for overview. take off are tied via generator bus- conflict to con ed procedure
CENY-BX | MC-96226 | PV | 2.8 | Yes | Inverter | 2014-08-25 | 2014-08-26 07:45 | 2014-08-26 07:45 | 2014-08-26 07:45 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval
CENY-BX | MC-96613 | PV | 18 | Yes | Inverter | 2014-08-26 | 2014-08-27 09:29 | 2014-08-27 09:29 | 2014-08-27 09:29 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval.
CENY-BX | MC-98470 | PV | 2.6 | Yes | Inverter | 2014-09-08 | 2014-09-08 13:06 | 2014-09-08 13:06 | 2014-09-08 13:06 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | SENT MTR WR
CENY-BX | MC-98480 | PV | 2.8 | Yes | Inverter | 2014-09-08 | 2014-09-08 14:13 | 2014-09-08 14:14 | 2014-09-08 14:14 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval.
CENY-BX | MC-98547 | PV | 4 | Yes | Inverter | 2014-09-08 | 2014-09-08 | 2014-09-08 | 2014-09-08 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Three Line Diagram Updated to show new inverter SMA America SunnyBoy 3800 TL that replaces the SMA America SunnyBoy 4000
CENY-BX | MC-98999 | PV | 6 | Yes | Inverter | 2014-09-10 | 2014-09-10 11:40 | 2014-09-10 11:41 | 2014-09-10 11:41 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval.
CENY-M | 444714 | PV | 4 | Yes | Inverter | 2007-03-22 | 2007-03-29 | 2010-09-07 | 2007-04-26 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | 10/21/14 status same - Pending Customer response on remaining inspection.
CENY-M | 473381 | MT | 150 | No | SYNCHRONOUS | 2009-11-30 | 2009-12-09 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2011-04-25 |  | no | IN PROGRESS | Pending Customer response back for DE comments 10/24 - No change in status
CENY-M | 473382 | MT | 170 | No | SYNCHRONOUS | 2009-11-30 | 2009-12-09 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | no | IN PROGRESS | Pending Customer response back for DE comments 10/24 - No change in status
CENY-M | 476841 | MT | 400 | No | Inverter | 2010-03-26 | 2010-04-05 | 2010-03-26 | 2010-04-05 | 2010-09-28 | 2010-10-27 | 0 | 0 | 0 | 0 | 0 | 2011-10-29 |  | No | IN PROGRESS | NO CHANGE - Pending final DE approval letter due to customer name issue. 10/24
CENY-M | 483235 | ICE | 8000 | NO | Inverter | 2011-04-16 | 2011-04-16 | 2011-04-16 | 2011-06-30 |  |  | 0 | 0 | 350 | 0 | 0 |  |  | NO | In Progress | Pending customer work
CENY-M | 485483 | PV | 4.5 | Yes | Inverter | 2011-01-04 | 2011-01-11 | 2011-02-01 | 2011-02-04 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | 10/21 - Pending acceptance agreement from customer
CENY-M | 1210948 | GT | 10000 | NO | Inverter | 2012-10-29 | 2012-11-01 | 2012-11-03 | 2012-11-20 | 2012-12-24 | 2013-01-11 | 0 | 0 | 350 | 0 | 0 |  |  | No | IN PROGRESS | Construction will not start until 3/2016.
CENY-M | 1226118 | MT | 65 | no | INVERTER | 2013-09-19 | 2013-09-11 | 2013-09-11 | 2013-09-11 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | no | IN PROGRESS | NO CHANGES - Pending Signatures from customer. 10/24
CENY-M | 1275479 | ST | 275 | No | Inverter | 2011-12-08 | 2011-12-12 | 2012-01-10 | 2012-02-16 | 2012-02-16 | 2012-03-13 | 0 | 0 | 350 | 0 | 0 |  |  | NO | In Progress | Pend Customer Build & Verfication Test
CENY-M | 1304305 | MT | 200 | No | Inverter | 2012-04-06 | 2012-04-11 | 2013-01-31 | 2013-03-12 | 2013-03-12 | 2013-05-05 | 0 | 0 | 350 | 0 | 0 |  |  | NO | In Progress | pending verification testing
CENY-M | 1304965 | ICE | 1400 | NO | INVERTER | 2013-09-19 | 2013-09-19 | 2013-11-27 | 2013-12-04 |  |  | 0 | 0 | 350 | 0 | 0 |  |  | NO | In Progress | Pending customer Build
CENY-M | 1312666 | MT | 780 | No | Inverter | 2012-05-11 | 2012-05-15 | 2012-05-15 | 2012-07-12 | 2012-07-12 | 2012-07-31 | 0 | 0 | 350 | 0 | 0 |  |  | NO | In Progress | DE review complete Pending Pre-op Test
CENY-M | 1317355 | MT | 500 | NO | Inverter | 2012-06-08 | 2012-06-08 | 2012-06-08 | 2012-06-13 | 2012-06-13 | 2012-08-27 | 0 | 0 | 350 | 0 | 0 |  |  | No | IN PROGRESS | Customer is now ready with funding to move project forward. Need approval of flexible hose from FDNY
CENY-M | 1317675 | MT | 65 | No | Inverter | 2012-06-03 | 2012-06-04 | 2013-09-22 | 2012-10-05 | 2012-10-05 | 2013-04-17 | 0 | 0 | 350 | 0 | 0 |  |  | NO | In Progress | Pending Verification Testing
CENY-M | 1329188 | MT | 65 | no | Inverter | 2012-07-26 | 2012-07-27 | 2013-09-11 | 2013-09-22 |  |  | 0 | 0 | 350 | 0 | 0 |  |  | NO | In Progress | Pending DG package Customer Submittal
CENY-M | 1331095 | MT | 65 | No | Inverter | 2012-08-06 | 2012-08-08 | 2013-01-24 | 2013-03-08 | 2013-03-08 | 2013-07-16 | 0 | 0 | 350 | 0 | 0 |  |  | NO | In Progress | Pending Verification Testing
CENY-M | 1331675 | PV | 4.5 | Yes | Inverter | 2012-08-07 | 2012-08-10 | 2012-08-07 | 2012-09-12 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Email sent to customer on the status of the PV installation.
CENY-M | 1346808 | GT | 4500 | No | Synchronous | 2013-09-22 | 2013-09-29 |  |  |  |  | 0 | 0 | 350 | 0 | 0 |  |  | NO | In Progress | Pending DG package Customer Submittal
CENY-M | 1355339 | ICE | 100 | NO | INVERTER | 2012-12-31 | 2013-01-02 | 2013-01-02 | 2013-02-13 | 2013-06-24 | 2013-08-06 | 0 | 0 | 350 | 0 | 0 |  |  | NO | In Progress | Pending customer work
CENY-M | 1366348 | GT | 4500 | no | Synchronous | 2012-12-18 | 2012-12-18 |  |  |  |  | 0 | 0 | 350 | 0 | 0 |  |  | NO | In Progress | Pending application documents
CENY-M | 1370296 | ICE | 100 | NO | INVERTER | 2013-01-08 | 2013-01-09 | 2013-01-09 | 2013-01-14 | 2013-09-14 | 2014-04-09 | 0 | 0 | 350 | 0 | 0 |  |  | NO | In Progress | pending verification testing
CENY-M | 1387634 | ICE | 200 | NO | INVERTER | 2013-03-14 | 2013-03-28 | 2013-04-17 | 2013-04-23 |  |  | 0 | 0 | 350 | 0 | 0 |  |  | NO | In Progress | Pending customer Build
CENY-M | 1391564 | ICE | 250 | NO | INVERTER | 2013-03-28 | 2013-04-03 | 2013-04-03 | 2013-04-17 | 2013-04-17 | 2013-05-09 | 0 | 0 | 350 | 0 | 0 |  |  | NO | In Progress | Pending Verification Testing
CENY-M | 1413628 | ICE | 300 | NO | Inverter | 2013-04-23 | 2013-04-24 | 2013-04-24 | 2013-04-24 | 2013-04-25 | 2013-04-29 | 0 | 0 | 350 | 0 | 0 |  |  | NO | In Progress | Pending Date for Pre Op Test
CENY-M | 1416817 | ICE | 150 | NO | Inverter | 2013-05-01 | 2013-05-30 | 2013-05-30 | 2013-05-30 | 2013-05-30 | 2013-06-26 | 0 | 0 | 350 | 0 | 0 |  |  | NO | In Progress | Pending Verification Testing
CENY-M | 1428761 | ICE | 75 | NO | Inverter | 2013-06-03 | 2013-06-19 | 2013-06-20 | 2013-07-01 | 2013-09-14 | 2013-11-11 | 0 | 0 | 350 | 0 | 0 |  |  | NO | In Progress | Pending customer Cogen build
CENY-M | 1432779 | ICE | 75 | NO | Inverter | 2013-06-13 | 2013-06-19 | 2013-06-19 | 2013-07-01 |  |  | 0 | 0 | 350 | 0 | 0 |  |  | NO | In Progress | Sent Cancellation notice - mangement change at the building and plan to move forward with the installation.
CENY-M | 1439969 | ICE | 300 | NO | Inverter | 2013-07-03 | 2013-07-10 | 2013-08-30 | 2013-08-30 |  |  | 0 | 0 | 350 | 0 | 0 |  |  | NO | In Progress | Pending response to DE 2nd review comments
CENY-M | 1507308 | PV | 3 | Yes | Inverter | 2013-08-16 | 2013-08-20 | 2013-08-20 | 2013-08-20 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending PV installation
CENY-M | 1507309 | PV | 20 | Yes | Inverter | 2013-08-16 | 2013-08-20 | 2013-08-20 | 2013-08-20 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending PV installation
CENY-M | 1514093 | ICE | 75 | NO | Induction | 2013-08-29 | 2013-08-30 | 2014-01-10 | 2014-01-27 |  |  | 0 | 0 | 350 | 0 | 0 |  |  | NO | In Progress | Pending response from customer on DE review.
CENY-M | 1514144 | ICE | 75 | NO | Induction | 2013-08-29 | 2013-08-30 |  |  |  |  | 0 | 0 | 350 | 0 | 0 |  |  | NO | In Progress | Pending customer DG package.
CENY-M | 1516300 | MT | 65 | No | Inverter | 2013-09-04 | 2013-09-09 |  |  |  |  | 0 | 0 | 350 | 0 | 0 |  |  | NO | In Progress | Pending customer DG package.
CENY-M | 1516447 | ICE | 200 | NO | Inverter | 2013-09-04 | 2013-09-05 | 2014-01-15 | 2014-02-11 |  |  | 0 | 0 | 350 | 0 | 0 |  |  | NO | In Progress | Pending response to DE review comments.
CENY-M | MC 23603 | ICE | 80 | No | Induction | 2010-06-08 | 2010-06-08 | 2010-06-08 | 2010-07-01 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | No Change: 10/23/14 cust to complete additional work
CENY-M | MC 23609 | ICE | 80 | No | Induction | 2010-06-08 | 2010-06-08 | 2010-06-08 | 2010-07-01 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | No Change: 10/23/14 cust to complete additional work
CENY-M | MC 23614 | ICE | 80 | No | Induction | 2010-06-08 | 2010-06-08 | 2010-06-08 | 2010-07-01 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | No Change: 10/23/14 cust to complete additional work
CENY-M | MC 23616 | ICE | 80 | No | Induction | 2010-06-08 | 2010-06-08 | 2010-06-08 | 2010-07-01 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | No Change: 10/23/14 cust to complete additional work
CENY-M | MC-100421 | PV | 30 | YES | Inverter | 2014-09-17 | 2014-10-02 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Project Center Form - Other WEGO 839 - Form G Application For Net Metering-pdffiller.pdf - Form G Application For Net Metering
CENY-M | MC-100504 | PV | 30 | YES | Inverter | 2014-09-18 | 2014-10-02 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | PSN2 Case Transfered to PSN CPM
CENY-M | MC-100519 | PV | 30 | YES | Inverter | 2014-09-18 | 2014-10-02 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | PSN 2 Case Transfered To PSN CPM
CENY-M | MC-101267 | PV | 20.1 | Yes | Inverter | 2014-09-23 | 2014-09-23 11:19 | 2014-09-23 11:20 | 2014-09-23 11:21 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | PENDING FULL APP
CENY-M | MC-26310 | GT | 4500 | no | SYNCHRONOUS | 2012-09-16 | 2012-09-16 | 2012-09-28 | 2012-10-09 | 2014-05-05 | 2014-06-30 | 0 | 0 | 350 | 0 | 0 |  |  | NO | In Progress | Pending customer DG package.
CENY-M | MC-31676 | ICE | 75 | NO | Induction | 2013-09-16 | 2013-10-09 | 2013-10-09 | 2013-10-09 | 2013-10-16 | 2013-10-31 | 0 | 0 | 350 | 0 | 0 |  |  | NO | In Progress | Pending customer Build
CENY-M | MC-32694 | PV | 5 | Yes | Inverter | 2013-09-23 | 2013-09-27 | 2013-09-27 | 2013-10-03 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | SENT MTR WR
CENY-M | MC-33189 | ICE | 85 | NO | Induction | 2013-09-26 | 2013-09-27 | 2013-10-01 | 2013-10-01 | 2014-03-11 | 2014-05-19 | 0 | 0 | 350 | 0 | 0 |  |  | NO | In Progress | Pending full DG package from consultant
CENY-M | MC-49545 | MT | 65 | no | Inverter | 2013-11-27 | 2013-11-27 | 2014-09-08 10:15 | 2014-10-10 |  |  | 0 | 0 | 350 | 0 | 0 |  |  | NO | In Progress | Pending full DG package from consultant
CENY-M | MC-58040 | ICE | 250 | NO | Induction | 2014-01-30 06:12 | 2014-02-04 07:33 | 2014-02-04 08:01 | 2014-02-04 |  |  | 0 | 0 | 350 | 0 | 0 |  |  | NO | In Progress | Pending full DG package from consultant
CENY-M | MC-58242 | PV | 7.4 | Yes | Inverter | 2014-01-24 12:51 | 2014-02-03 09:17 | 2014-01-24 12:57 | 2014-02-03 09:19 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | PENDING CIS UPDATE
CENY-M | MC-58244 | PV | 0.8 | Yes | Inverter | 2014-01-24 12:32 | 2014-02-03 09:21 | 2014-01-27 09:42 | 2014-02-03 09:32 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | PENDING CIS UPDATE
CENY-M | MC-58245 | PV | 0.8 | Yes | Inverter | 2014-01-24 09:13 | 2014-02-03 09:06 | 2014-01-24 13:22 | 2014-02-03 09:08 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | PENDING CIS UPDATE
CENY-M | MC-59629 | FC | 1200 | YES | Inverter | 2014-01-30 09:15 | 2014-01-30 | 2014-01-30 | 2014-01-30 |  |  | 0 | 0 | 350 | 0 | 0 |  |  | NO | In Progress | Pending DE Review
CENY-M | MC-60556 | ICE | 75 | NO | Induction | 2014-02-04 11:43 | 2014-02-14 11:26 | 2014-02-14 11:30 | 2014-02-14 11:30 |  |  | 0 | 0 | 350 | 0 | 0 |  |  | NO | In Progress | Pending DE Review
CENY-M | MC-61685 | ICE | 750 | NO | Induction | 2014-02-11 06:13 | 2014-02-11 06:13 | 2014-02-11 06:13 | 2014-02-11 06:13 |  |  | 0 | 0 | 350 | 0 | 0 |  |  | NO | In Progress | Pending DE Review
CENY-M | MC-62007 | ICE | 75 | NO | Induction | 2014-02-12 14:03 | 2014-02-12 15:10 | 2014-02-12 15:11 | 2014-02-12 |  |  | 0 | 0 | 350 | 0 | 0 |  |  | NO | In Progress | Pending DE Review
CENY-M | MC-66067 | ICE | 225 | NO | Inverter | 2014-03-18 07:27 | 2014-03-18 | 2014-03-25 | 2014-03-27 |  |  | 0 | 0 | 350 | 0 | 0 |  |  | NO | In Progress | Pending full DG package from consultant
CENY-M | MC-66259 | ICE | 200 | NO | Inverter | 2014-03-18 07:34 | 2014-03-18 | 2014-03-19 | 2014-04-16 |  |  | 0 | 0 | 350 | 0 | 0 |  |  | NO | In Progress | Pending DE Review
CENY-M | MC-66498 | PV | 120 | YES | Inverter | 2014-03-18 07:17 | 2014-03-18 | 2014-03-18 | 2014-03-21 |  |  | 0 | 0 | 350 | 0 | 0 |  |  | NO | In Progress | Pending full DG package from consultant
CENY-M | MC-68476 | PV | 99 | YES | Inverter | 2014-03-25 06:44 | 2014-03-25 | 2014-03-25 | 2014-03-25 |  |  | 0 | 0 | 350 | 0 | 0 |  | 2014-07-17 | NO | Complete | Complete
CENY-M | MC-68636 | ICE | 75 | NO | Induction | 2014-03-27 06:20 | 2014-03-27 | 2014-05-30 11:03 | 2014-06-19 |  |  | 0 | 0 | 350 | 0 | 0 |  |  | NO | In Progress | Pending full DG package from consultant
CENY-M | MC-68981 | MT | 800 | No | Inverter | 2012-12-04 | 2013-01-22 | 2013-01-22 | 2013-04-12 |  |  | 0 | 0 | 350 | 0 | 0 |  |  | NO | In Progress | Pending customer Build
CENY-M | MC-76414 | ICE | 75 | NO | Induction | 2014-05-06 | 2014-05-07 | 2014-09-23 16:16 | 2014-09-23 16:17 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | Consulant never submitted the required DG package, specs and applications.
CENY-M | MC-81871 | ICE | 100 | NO | Inverter | 2014-06-05 | 2014-06-10 | 2014-07-22 | 2014-08-14 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | Submitted - Case Number Assigned
CENY-M | MC-81875 | PV | 50 | YES | Inverter | 2014-06-05 | 2014-06-10 | 2014-06-13 | 2014-07-14 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | Submitted - Case Number Assigned
CENY-M | MC-82614 | ICE | 75 | NO | Induction | 2014-06-10 | 2014-06-15 | 2014-07-02 | 2014-09-04 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | Submitted - Case Number Assigned
CENY-M | MC-83120 | PV | 4 | Yes | Inverter | 2014-06-12 | 2014-06-12 13:01 | 2014-06-12 13:02 | 2014-06-12 13:03 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-12 | No | Complete | Pending CIS Update
CENY-M | MC-83332 | ICE | 200 | NO | Inverter | 2014-06-13 | 2014-06-18 | 2014-06-13 | 2014-07-15 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | Submitted - Case Number Assigned
CENY-M | MC-83663 | BATT | 252 | NO | Inverter | 2014-06-16 | 2014-06-17 | 2014-07-01 | 2014-09-04 15:16 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | Submitted - Case Number Assigned
CENY-M | MC-83664 | BATT | 360 | NO | Inverter | 2014-06-16 | 2014-06-17 | 2014-07-01 | 2014-09-04 15:16 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | Submitted - Case Number Assigned
CENY-M | MC-83764 | ICE | 75 | NO | Inverter | 2014-06-16 | 2014-06-20 | 2014-06-26 | 2014-07-18 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | Submitted - Case Number Assigned
CENY-M | MC-83976 | ICE | 75 | NO | Induction | 2014-06-17 | 2014-06-21 | 2014-06-26 | 2014-07-18 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | Submitted - Case Number Assigned
CENY-M | MC-84004 | ICE | 75 | NO | Induction | 2014-06-17 | 2014-06-17 | 2014-07-17 | 2014-07-22 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | Submitted - Case Number Assigned
CENY-M | MC-88185 | PV | 52 | YES | Inverter | 2014-07-10 | 2014-07-15 | 2014-08-12 | 2014-09-09 17:23 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | see attached email for review comments.
CENY-M | MC-88593 | BATT | 300 | NO | Inverter | 2014-07-14 | 2014-07-16 | 2014-08-06 | 2014-08-14 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | see attached comments
CENY-M | MC-88963 | ICE | 75 | NO | Induction | 2014-07-15 | [5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | NO | Cancelled | case canceled , see atttached email.
CENY-M | MC-89601 | ICE | 100 | NO | Inverter | 2014-07-18 | 2014-07-18 | 2014-08-12 | 2014-09-04 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | see attached email to the consultant
CENY-M | MC-89822 | ICE | 75 | NO | Induction | 2014-07-21 | [5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | NO | Cancelled | cancelled
CENY-M | MC-89823 | ICE | 75 | NO | Inverter | 2014-07-21 | 2014-08-07 | 2014-08-07 | 2014-08-20 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | gas case is Mc-95474 which is with engineering to review.
CENY-M | MC-89824 | ICE | 75 | NO | Inverter | 2014-07-21 | 2014-08-07 | 2014-08-07 | 2014-10-28 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Case folder resubmitted to DE on 8/7/14.
CENY-M | MC-89825 | ICE | 75 | NO | Inverter | 2014-07-21 | 2014-08-07 | 2014-08-07 | 2014-10-28 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Case folder resubmitted to DE on 8/7/14.
CENY-M | MC-89827 | ICE | 75 | NO | Inverter | 2014-07-21 | 2014-08-07 | 2014-08-07 | 2014-08-18 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | OTG conversion case MC-45956 meter will be a class 1000.
CENY-M | MC-92013 | MT | 65 | No | Inverter | 2014-07-31 | 2014-09-08 09:51 | 2014-09-15 09:51 | 2014-09-15 09:51 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | review comments sent to customer.
CENY-M | MC-92032 | MT | 65 | No | Inverter | 2014-07-31 | 2014-09-08 12:04 | 2014-09-10 12:04 | 2014-09-15 09:51 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | comments set to customer
CENY-M | MC-93294 | BATT | 100 | NO | Inverter | 2014-08-07 | 2014-09-01 | 2014-09-22 | 2014-10-03 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Case folder given to DE Dan Sammon for review.
CENY-M | MC-94852 | PV | 2.4 | Yes | Inverter | 2014-08-18 | 2014-08-19 | 2014-08-19 | 2014-08-19 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Recieved 1 line diagram & spec sheets. Resent outstanding requirements to the contractor.
CENY-M | MC-95990 | BATT | 100 | NO | Inverter | 2014-08-22 | 2014-09-08 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Left voicemail regarding missing Appendix B
CENY-M | MC-95992 | BATT | 100 | NO | Inverter | 2014-08-22 | 2014-09-08 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Left voicemail regarding missing Appendix B
CENY-M | MC-95997 | BATT | 200 | NO | Inverter | 2014-08-22 | 2014-09-08 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Left Voicemail for contractor about missing Appendix B
CENY-M | MC-96067 | PV | 10 | Yes | Inverter | 2014-08-22 | 2014-08-22 | 2014-08-22 | 2014-08-22 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval. Still require Appendix B
CENY-M | MC-97624 | ICE | 200 | NO | Inverter | 2014-09-03 | 2014-09-08 10:45 | 2014-09-08 10:45 | 2014-10-28 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Case folder given to DE Dan Sammon for review.
CENY-M | MC-98028 | PV | 18 | Yes | Inverter | 2014-09-04 | 2014-09-10 11:26 | 2014-09-10 11:28 | 2014-09-10 11:28 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to application. Still require full application.
CENY-M | MC-98630 | MT | 65 | NO | Inverter | 2014-09-08 | [5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | NO | Cancelled | no documents are ready for submittal as per the consultant. Project is months away form starting , so this case is canceled.
CENY-Q | 329527 | GT | 15000 | No | SYNCH | 2008-08-06 | 2008-08-06 | 2008-09-09 | 2008-09-09 | 2009-08-19 | 2009-09-15 | 0 | 0 | 1502845 | 0 | 0 | 2014-10-14 | 2014-10-20 | No | Complete | HTV energized, gas service turned on, cogen final testing in progress.
CENY-Q | 340892 | MT | 100 | No | Inverter | 2009-07-27 | 2009-07-30 | 2009-07-31 | 2009-08-02 | 2009-08-02 | 2009-12-07 | 0 | 0 | 0 | 0 | 0 | 2011-04-27 |  | No | in progress | Failed, re-test to be scheduled by contractor - Final acceptance pend (SAME)
CENY-Q | 353800 | PV | 144 | Yes | Inverter | 2011-01-31 | 2011-02-05 | 2011-04-28 | 2011-05-03 | 2011-05-03 | 2011-05-31 | 0 | 0 | 0 | 0 | 0 |  |  | No | in progress | Still no response from contractor. Pending field verification
CENY-Q | 1263663 | ICE | 75 | No | Induction | 2013-11-08 07:20 | 2011-11-30 | 2014-04-10 13:54 | 2014-04-18 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | in progress | Pending customer payment for review 5,175. advance service date (SAME)
CENY-Q | 1307586 | PV | 2.5 | Yes | Inverter | 2012-04-23 | 2012-04-30 | 2012-04-30 | 2012-05-04 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | Cancelled | Case Cancelled 10/06/14
CENY-Q | 1310111 | PV | 5 | Yes | Inverter | 2012-05-02 | 2012-05-07 | 2012-05-07 | 2012-05-15 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending response / Should case remain active
CENY-Q | 1318682 | PV | 6 | Yes | Inverter | 2012-06-07 | 2012-06-13 | 2012-06-13 | 2012-06-19 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | in progress | Pending PV Install
CENY-Q | 1320844 | PV | 1.5 | Yes | Inverter | 2012-06-14 | 2012-06-19 | 2012-06-19 | 2012-06-25 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | Cancelled | Case Cancelled 10/07/14
CENY-Q | 1336446 | PV | 45 | No | Inverter | 2012-08-27 | 2012-10-24 | 2012-10-24 | 2012-10-24 | 2012-10-24 | 2012-11-21 | 0 | 0 | 0 | 0 | 0 |  |  | No | in progress | Pending Engineering comments / customer items. (SAME)
CENY-Q | 1336451 | BATT | 45 | No | Inverter | 2013-11-08 08:41 | 2012-09-04 | 2012-09-11 | 2012-09-25 | 2012-10-24 | 2012-11-21 | 0 | 0 | 0 | 0 | 0 |  |  | No | in progress | The project is on hold pending, pending funding. (SAME)
CENY-Q | 1339822 | PV | 10 | Yes | Inverter | 2012-09-11 | 2012-09-17 | 2012-09-17 | 2012-09-25 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | in progress | Pending PV Install
CENY-Q | 1346222 | PV | 3.5 | Yes | Inverter | 2012-10-03 | 2012-10-10 | 2012-10-10 | 2012-10-18 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending response / Should case remain active
CENY-Q | 1346962 | ICE | 4000 | No | Induction | 2012-10-04 | 2012-10-04 | 2012-10-05 | 2012-10-31 | 2012-10-05 | 2012-10-31 | 0 | 0 | 350 | 0 | 0 |  |  | No | IN PROGRESS | waiting on customer to move the job forward - No Change
CENY-Q | 1374923 | PV | 96 | YES | Inverter | 2013-01-07 | 2013-01-11 | 2013-01-14 | 2013-01-28 |  |  | 0 | 0 | 350 | 0 | 0 |  |  | No | in progress | Pending permanent service installation (SAME)
CENY-Q | 1393007 | PV | 5.4 | Yes | Inverter | 2013-04-03 | 2013-04-15 | 2013-04-15 | 2013-06-28 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | in progress | Pending PV Install
CENY-Q | 1414041 | PV | 6 | Yes | Inverter | 2013-04-22 | 2013-05-08 | 2013-05-08 | 2013-05-22 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending response if case should remain active
CENY-Q | 1422415 | PV | 75 | Yes | Inverter | 2013-05-15 | 2013-05-20 | 2013-05-28 | 2013-05-31 | 2013-06-05 | 2013-07-03 | 0 | 0 | 0 | 0 | 0 |  |  | No | in progress | Received updated response from customer, pending further DE review. (SAME)
CENY-Q | 1422445 | PV | 200 | Yes | Inverter | 2013-05-17 | 2013-05-20 | 2013-05-20 | 2013-05-31 | 2013-06-05 | 2013-07-03 | 0 | 0 | 0 | 0 | 0 |  |  | No | in progress | Received updated response from customer, pending further DE review. (SAME)
CENY-Q | 1426711 | PV | 200 | Yes | Inverter | 2013-05-28 | 2013-06-03 | 2013-06-24 | 2013-07-20 | 2013-07-25 | 2013-07-27 | 0 | 0 | 0 | 0 | 0 |  |  | No | in progress | Pending contractor install.
CENY-Q | 1426713 | PV | 100 | Yes | Inverter | 2013-05-28 | 2013-06-03 | 2013-06-24 | 2013-07-20 | 2013-07-25 | 2013-07-27 | 0 | 0 | 0 | 0 | 0 |  |  | No | in progress | Pending contractor install.
CENY-Q | 1427152 | PV | 5 | Yes | Inverter | 2013-05-31 | 2013-06-05 | 2013-06-05 | 2013-06-12 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-10 | No | Complete | Pending Net Meter Install
CENY-Q | 1427529 | PV | 15 | Yes | Inverter | 2013-05-30 | 2013-06-12 | 2013-06-12 | 2013-06-26 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | in progress | Pending PV Install
CENY-Q | 1429002 | ICE | 150 | No | Inverter | 2013-06-04 | 2013-06-05 | 2013-06-14 | 2013-06-14 | 2013-06-14 | 2013-08-14 | 0 | 0 | 350 | 0 | 0 |  |  | No | in progress | Building in construction. No progress on Cogen case by customer. Service date changed to 7/30/15.
CENY-Q | 1431899 | GT | 4500 | NO | Synchronous | 2013-06-11 | 2013-06-12 | 2013-08-20 | 2013-08-30 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer's response to DE review.
CENY-Q | 1432751 | PV | 3.1 | Yes | Inverter | 2013-06-17 | 2013-06-26 | 2013-06-26 | 2013-06-28 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending response if case should remain active
CENY-Q | 1471793 | PV | 5.5 | Yes | Inverter | 2013-07-17 | 2013-07-22 | 2013-07-30 | 2013-08-06 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending response if case should remain active
CENY-Q | 1475450 | PV | 5 | Yes | Inverter | 2013-07-19 | 2013-07-24 | 2013-07-31 | 2013-08-20 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-05 | No | Complete | Pending Net Meter Install
CENY-Q | 1504925 | PV | 4.3 | Yes | Inverter | 2013-08-13 | 2013-08-16 | 2013-08-21 | 2013-08-23 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-01 | No | Complete | Pending Validation & Close-out
CENY-Q | 1506750 | PV | 4.8 | Yes | Inverter | 2013-08-15 | 2013-08-21 | 2013-08-26 | 2013-09-18 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-29 | No | Complete | Pending Validation & Close-out
CENY-Q | 1508374 | PV | 3.3 | Yes | Inverter | 2013-08-20 | 2013-08-23 | 2013-08-28 | 2013-09-04 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-23 | No | Complete | Pending Validation & Close-out
CENY-Q | 1508611 | PV | 12 | Yes | Inverter | 2013-08-20 | 2013-08-20 | 2013-08-20 | 2013-08-20 | 2013-09-10 | 2013-09-30 | 0 | 0 | 0 | 0 | 0 |  |  | No | in progress | Customer constructing in steps/phases. It's a combined system with CHP, inverter & battery.
CENY-Q | 1512882 | PV | 5.5 | Yes | Inverter | 2013-08-27 | 2013-09-03 | 2013-09-09 | 2013-09-09 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-07-31 | No | Complete | Pending Validation & Close-out
CENY-Q | 1517465 | PV | 3 | Yes | Inverter | 2013-09-06 | 2013-09-11 | 2014-06-10 07:38 |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | in progress | Pending Application Documentation
CENY-Q | 1566605 | PV | 4.2 | Yes | Inverter | 2013-09-25 | 2013-10-02 | 2013-10-18 | 2013-10-18 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | in progress | Pending Application Documentation
CENY-Q | 1569850 | PV | 5.5 | Yes | Inverter | 2013-09-30 | 2013-10-14 | 2013-10-14 | 2013-10-14 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | Cancelled | Case Cancelled 10/08/14
CENY-Q | 1571533 | MT | 130 | No | Inverter | 2013-10-01 | 2013-10-01 | 2013-10-02 | 2013-10-02 |  |  | 0 | 0 | 350 | 0 | 0 |  |  | No | in progress | Sent documents to DE for review (SAME)
CENY-Q | 1571562 | MT | 65 | No | Inverter | 2013-10-01 | 2013-10-02 | 2013-10-04 | 2013-10-04 |  |  | 0 | 0 | 350 | 0 | 0 |  |  | No | in progress | Sent documents to DE for review (SAME)
CENY-Q | 1583912 | PV | 21 | Yes | Inverter | 2013-10-15 | 2014-01-03 10:53 | 2013-12-12 | 2013-12-12 | 2013-12-13 | 2014-01-10 | 0 | 0 | 0 | 0 | 0 |  |  | No | in progress | Pending PV Install
CENY-Q | 1584546 | PV | 2 | Yes | Inverter | 2013-10-15 | 2013-10-23 | 2013-10-23 | 2013-10-23 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-07-18 | No | Complete | Case Completed - Closed Out 10/02/14
CENY-Q | 1587846 | PV | 350 | Yes | Inverter | 2013-10-20 | 2013-10-23 | 2013-10-23 | 2013-10-23 | 2013-10-28 | 2013-11-15 | 0 | 0 | 0 | 0 | 0 |  |  | no | IN PROGRESS | Waiting on the customer for a verification test - No Change
CENY-Q | 1592553 | PV | 8 | Yes | Inverter | 2013-10-24 | 2013-12-10 07:35 | 2013-11-01 | 2013-11-01 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-10-06 | No | Complete | Pending Net Meter Install
CENY-Q | 1593981 | PV | 5 | Yes | Inverter | 2013-10-27 | 2013-11-04 | 2013-11-04 | 2013-11-04 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-18 | No | Complete | Pending Validation & Close-out
CENY-Q | 1602395 | PV | 600 | Yes | Inverter | 2013-11-06 | 2013-11-12 | 2013-11-12 | 2013-11-12 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | in progress | Customer upgrading service from 50kw to 600kw system. Pending contractor to submit in all new documents for 600kw system.
CENY-Q | 1602403 | PV | 4 | Yes | Inverter | 2013-11-06 | 2013-11-15 | 2013-11-15 | 2013-11-15 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-23 | No | Complete | Pending Validation & Close-out
CENY-Q | 1602672 | ICE | 150 | No | Inverter | 2013-11-07 | 2013-11-16 | 2013-12-03 | 2013-12-03 | 2014-05-30 | 2014-06-10 | 0 | 0 | 350 | 0 | 0 |  |  | No | in progress | DE provided approval to proceed on 6/10/14. Customer constructing in steps/phases.
CENY-Q | MC-100075 | PV | 12 | YES | Inverter | 2014-09-16 | 2014-09-16 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending custome. Line diagram not submitted.
CENY-Q | MC-100375 | PV | 3.8 | YES | Inverter | 2014-09-17 | 2014-09-17 | 2014-09-18 | 2014-09-18 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit. Sent Line Diagram approval ltr. to customer/contractor.
CENY-Q | MC-100396 | PV | 3.8 | YES | Inverter | 2014-09-17 | 2014-09-17 | 2014-09-18 | 2014-09-18 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit. Sent Line Diagram approval ltr. to customer/contractor.
CENY-Q | MC-100425 | PV | 5 | YES | Inverter | 2014-09-17 | 2014-09-17 | 2014-09-18 | 2014-09-18 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit. Sent Line Diagram approval ltr. to customer/contractor.
CENY-Q | MC-100653 | PV | 7.6 | YES | Inverter | 2014-09-18 | 2014-09-18 | 2014-09-22 | 2014-09-22 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit. Sent Line Diagram approval ltr. to customer/contractor.
CENY-Q | MC-100796 | PV | 3.2 | YES | Inverter | 2014-09-19 | 2014-09-22 10:23 | 2014-09-22 10:24 | 2014-09-22 10:26 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit. Sent Line Diagram approval ltr. to customer/contractor.
CENY-Q | MC-100839 | PV | 13 | YES | Inverter | 2014-09-19 | 2014-09-22 11:23 | 2014-09-22 11:24 | 2014-09-22 11:26 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit. Sent Line Diagram approval ltr. to customer/contractor.
CENY-Q | MC-100850 | PV | 8 | YES | Inverter | 2014-09-19 | 2014-09-20 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer, incomplete submittal of documents.
CENY-Q | MC-100860 | PV | 6.8 | YES | Inverter | 2014-09-19 | 2014-09-22 13:44 | 2014-09-22 13:45 | 2014-09-22 13:47 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit. Sent Line Diagram approval ltr. to customer/contractor.
CENY-Q | MC-100887 | PV | 7.6 | YES | Inverter | 2014-09-19 | 2014-09-22 14:07 | 2014-09-22 14:08 | 2014-09-22 14:27 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit. Sent Line Diagram approval ltr. to customer/contractor.
CENY-Q | MC-101341 | PV | 11 | Yes | Inverter | 2014-09-23 | [5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | No | Cancelled | Case Cancelled 09/23/14 by Rosanna Zranchev/Planning
CENY-Q | MC-101376 | PV | 7 | YES | Inverter | 2014-09-23 | 2014-09-24 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | Cancelled | at contractor's request this case has been cancelled.
CENY-Q | MC-101568 | PV | 8 | YES | Inverter | 2014-09-24 | 2014-09-25 09:15 | 2014-09-25 09:17 | 2014-09-25 09:17 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit. Sent Line Diagram approval ltr. to customer/contractor.
CENY-Q | MC-101584 | PV | 7.6 | YES | Inverter | 2014-09-24 | 2014-09-24 | 2014-09-24 | 2014-09-24 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit. Sent Line Diagram approval ltr. to customer/contractor.
CENY-Q | MC-101621 | PV | 5.1 | YES | Inverter | 2014-09-24 | 2014-09-24 | 2014-09-24 | 2014-09-24 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit. Sent Line Diagram approval ltr. to customer/contractor.
CENY-Q | MC-101727 | ICE | 625 | No | Inverter | 2014-09-25 | 2014-10-03 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | in progress | In order to release a firm proposal to the Client , we will need the available fault current on the incoming circuit.
CENY-Q | MC-101763 | PV | 3.8 | YES | Inverter | 2014-09-25 | 2014-09-25 14:04 | 2014-09-25 14:06 | 2014-09-25 14:07 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit. Sent Line Diagram approval ltr. to customer/contractor.
CENY-Q | MC-101792 | PV | 3.4 | YES | Inverter | 2014-09-25 | 2014-09-25 | 2014-09-27 | 2014-09-27 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Emailed customer and Contractor regarding approved one line diagram
CENY-Q | MC-101803 | PV | 8 | YES | Inverter | 2014-09-25 | 2014-09-25 | 2014-09-27 | 2014-09-27 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Emailed customer and Contractor regarding approved one line diagram
CENY-Q | MC-101831 | PV | 4 | YES | Inverter | 2014-09-25 | 2014-09-25 | 2014-09-27 | 2014-09-27 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Emailed customer and Contractor regarding approved one line diagram
CENY-Q | MC-101841 | PV | 3.4 | YES | Inverter | 2014-09-25 | 2014-09-25 | 2014-09-27 | 2014-09-27 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Emailed customer and Contractor regarding approved one line diagram
CENY-Q | MC-101947 | PV | 2.8 | YES | Inverter | 2014-09-26 | 2014-09-26 | 2014-09-27 | 2014-09-27 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit. Sent Line Diagram approval ltr. to customer/contractor.
CENY-Q | MC-101963 | PV | 2.4 | YES | Inverter | 2014-09-26 | 2014-09-26 | 2014-09-27 | 2014-09-27 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Emailed customer and Contractor regarding approved one line diagram
CENY-Q | MC-101968 | PV | 2 | YES | Inverter | 2014-09-26 | 2014-09-26 | 2014-09-27 | 2014-09-27 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Emailed customer and Contractor regarding approved one line diagram
CENY-Q | MC-101985 | PV | 7 | YES | Inverter | 2014-09-26 | 2014-09-26 | 2014-09-27 | 2014-09-27 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Emailed customer and Contractor regarding approved one line diagram
CENY-Q | MC-102309 | PV | 3 | YES | Inverter | 2014-09-29 | 2014-09-29 | 2014-09-29 | 2014-09-29 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Emailed customer and Contractor regarding approved one line diagram
CENY-Q | MC-102473 | PV | 11 | YES | Inverter | 2014-09-30 | 2014-10-01 11:04 | 2014-10-01 11:13 | 2014-10-01 11:25 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit. Sent Line Diagram approval ltr. to customer/contractor.
CENY-Q | MC-102548 | PV | 3 | YES | Inverter | 2014-09-30 | 2014-10-01 15:00 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pendign customer, awaiting for line diagram.
CENY-Q | MC-1367 | PV | 450 | YES | Inverter | 2013-07-03 | 2013-07-07 | 2013-09-05 | 2013-09-05 | 2013-09-06 | 2013-09-20 | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Waiting on the customer to respond to DE review comments - No Change
CENY-Q | MC-32440 | ICE | 300 | NO | Inverter | 2013-09-19 | 2013-09-26 | 2013-10-03 | 2013-10-17 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Waiting on customer to submit required document to forward to DE - No Change
CENY-Q | MC-40157 | ST | 700 | NO | Induction | 2012-10-04 | 2012-10-19 | 2012-11-15 | 2013-02-19 | 2013-02-19 | 2013-03-19 | 0 | 0 | 350 | 0 | 0 |  |  | No | IN PROGRESS | waiting on customer for verification test - No Change
CENY-Q | MC-40342 | PV | 1000 | Yes | Inverter | 2012-12-12 | 2012-12-28 | 2013-04-10 | 2013-04-10 | 2013-06-28 | 2013-07-09 | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending verification test.
CENY-Q | MC-40488 | ICE | 1600 | NO | Synchronous | 2013-02-26 | 2013-04-10 | 2013-04-10 | 2013-04-14 |  |  | 0 | 0 | 350 | 0 | 0 |  |  | No | IN PROGRESS | Waiting on the customer to move the project forward - No Change
CENY-Q | MC-40732 | PV | 600 | YES | Inverter | 2013-03-29 | 2013-04-04 | 2013-04-04 | 2013-04-04 | 2013-04-05 | 2014-05-03 | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Waiting on customer to respond to DE comments - No Change
CENY-Q | MC-40738 | PV | 500 | YES | Inverter | 2013-03-29 | 2013-04-04 | 2013-04-04 | 2013-04-04 | 2013-04-05 | 2013-05-03 | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Waiting on customer to respond to DE comments - No Change
CENY-Q | MC-40934 | PV | 600 | YES | Inverter | 2013-04-29 | 2013-05-07 | 2013-06-25 | 2013-06-30 | 2013-06-30 | 2013-07-16 | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending Verification Test
CENY-Q | MC-41480 | ICE | 375 | NO | Inverter | 2013-06-19 | 2013-06-24 | 2013-09-17 | 2013-09-20 | 2013-10-07 | 2013-10-11 | 0 | 0 | 350 | 0 | 0 |  |  | No | IN PROGRESS | Waiting on the customer to respond to DE review comments
CENY-Q | MC-45739 | PV | 7 | Yes | Inverter | 2013-11-11 10:06 | 2013-12-16 14:59 | 2013-11-18 | 2013-11-18 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending response / Should case remain active
CENY-Q | MC-48696 | PV | 6 | Yes | Inverter | 2013-11-22 12:05 | 2013-12-09 15:06 | 2013-12-09 | 2013-12-09 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | Cancelled | Case Cancelled 10/08/14
CENY-Q | MC-48722 | PV | 5 | Yes | Inverter | 2013-11-22 | 2013-12-02 | 2013-12-02 | 2013-12-02 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | in progress | Pending Application Documentation
CENY-Q | MC-49638 | PV | 5 | Yes | Inverter | 2013-11-27 | 2013-12-11 | 2013-12-11 | 2013-12-11 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-07-30 | No | Complete | Pending Validation & Close-out
CENY-Q | MC-50428 | PV | 660 | yes | Inverter | 2013-12-04 10:03 | 2013-12-11 | 2013-12-11 | 2013-12-11 | 2013-12-14 | 2013-12-19 | 0 | 0 | 0 | 0 | 0 |  |  | no | IN PROGRESS | Pending verification test.
CENY-Q | MC-50887 | ICE | 75 | No | Induction | 2013-12-05 | 2013-12-10 | 2014-03-03 | 2014-03-14 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | in progress | Pending contractor outstanding items. (SAME)
CENY-Q | MC-51180 | PV | 6 | Yes | Inverter | 2013-12-06 | 2013-12-13 | 2013-12-13 | 2013-12-13 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | in progress | Pending Application Documentation
CENY-Q | MC-53424 | PV | 5 | Yes | Inverter | 2013-12-17 | 2013-12-27 | 2013-12-27 | 2013-12-27 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending Application Documents
CENY-Q | MC-54197 | PV | 4 | Yes | Inverter | 2013-12-19 | 2013-12-27 | 2013-12-27 | 2014-01-23 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | in progress | Pending Application Documentation
CENY-Q | MC-54498 | PV | 60 | yes | Inverter | 2013-12-20 | 2014-01-03 | 2014-01-03 | 2014-01-03 | 2014-01-03 | 2014-01-15 | 0 | 0 | 0 | 0 | 0 |  | 2014-07-25 | No | Complete | Approval Letter provided to customer 7/25/14
CENY-Q | MC-54501 | PV | 60 | yes | Inverter | 2013-12-20 | 2014-01-03 | 2014-01-03 | 2014-01-03 | 2014-01-03 | 2014-01-15 | 0 | 0 | 0 | 0 | 0 |  | 2014-07-25 | No | Complete | Approval Letter provided to customer 7/25/14
CENY-Q | MC-54517 | PV | 60 | yes | Inverter | 2013-12-20 | 2014-01-03 | 2014-01-03 | 2014-01-03 | 2014-01-03 | 2014-01-15 | 0 | 0 | 0 | 0 | 0 |  |  | No | in progress | Customer submitted updated documents. Pending DE approval.
CENY-Q | MC-54519 | PV | 80 | Yes | Inverter | 2013-12-20 | 2013-12-24 | 2013-12-26 | 2013-12-26 |  |  | 0 | 0 | 350 | 0 | 0 |  |  | No | in progress | Case is on hold as of now as customer might sell the building.
CENY-Q | MC-55717 | PV | 6 | Yes | Inverter | 2014-01-03 07:59 | 2014-01-09 | 2014-01-09 | 2014-01-23 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-07-14 | No | Complete | Pending Validation & Close-out
CENY-Q | MC-56360 | PV | 7 | Yes | Inverter | 2014-01-17 | 2014-01-28 | 2014-02-13 12:15 | 2014-03-03 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | in progress | Pending Final Documents
CENY-Q | MC-56750 | PV | 3 | Yes | Inverter | 2014-01-09 | 2014-01-17 | 2014-01-17 | 2014-02-20 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-07-15 | No | Complete | Pending Validation & Close-out
CENY-Q | MC-56921 | PV | 3 | Yes | Inverter | 2014-01-10 | 2014-01-17 | 2014-01-17 | 2014-01-29 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-04 | No | Complete | Pending Validation & Close-out
CENY-Q | MC-57578 | PV | 5 | Yes | Inverter | 2014-01-17 | 2014-01-23 | 2014-01-23 | 2014-02-04 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | in progress | Pending Application Documentation
CENY-Q | MC-57664 | PV | 7 | Yes | Inverter | 2014-01-17 | 2014-01-23 | 2014-02-06 15:47 | 2014-02-06 15:49 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | in progress | Pending PV Install
CENY-Q | MC-58345 | PV | 3 | Yes | Inverter | 2014-01-21 | 2014-01-27 | 2014-01-27 | 2014-02-07 14:46 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | in progress | Pending PV Install
CENY-Q | MC-58366 | PV | 5.6 | Yes | Inverter | 2014-01-20 | 2014-01-27 | 2014-01-27 | 2014-02-07 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | in progress | Pending PV Install
CENY-Q | MC-58367 | PV | 4.1 | Yes | Inverter | 2014-01-20 | 2014-01-27 | 2014-01-27 | 2014-02-07 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | in progress | Pending PV Install
CENY-Q | MC-59560 | PV | 98.4 | Yes | Inverter | 2014-02-03 11:01 | 2014-02-26 | 2014-02-26 | 2014-02-26 | 2014-02-26 | 2014-03-17 | 0 | 0 | 0 | 0 | 0 |  |  | No | in progress | Pre-operational test scheduled for 10/20/14.
CENY-Q | MC-59777 | PV | 3.5 | Yes | Inverter | 2014-01-29 | 2014-02-03 | 2014-02-03 | 2014-02-10 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | in progress | Pending PV Install
CENY-Q | MC-59901 | PV | 3.8 | Yes | Inverter | 2014-01-29 | 2014-02-06 | 2014-02-06 | 2014-02-15 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | in progress | Pending PV Install
CENY-Q | MC-60073 | PV | 6.6 | Yes | Inverter | 2014-01-30 | 2014-02-06 | 2014-02-06 | 2014-02-15 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | in progress | Pending Application Documentation
CENY-Q | MC-60130 | PV | 4 | Yes | Inverter | 2014-01-30 | 2014-02-15 | 2014-02-15 13:04 | 2014-02-18 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Contractor Requested Case Remain Active/It Is On Hold
CENY-Q | MC-60195 | FC | 525 | yes | Inverter | 2014-01-30 18:51 | 2014-01-31 | 2014-03-31 | 2014-04-04 | 2014-04-04 | 2014-04-08 | 0 | 0 | 350 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer response to DE review comments
CENY-Q | MC-60365 | PV | 13.4 | Yes | Inverter | 2014-01-31 | 2014-02-05 | 2014-02-05 | 2014-03-10 | 2014-08-19 | 2014-09-16 | 2300 | 0 | 0 | 0 | 0 |  |  | No | in progress | Initial review comments provided to customer. Pending customer action.
CENY-Q | MC-60514 | PV | 6 | Yes | Inverter | 2014-02-05 | 2014-02-08 | 2014-02-19 | 2014-02-19 08:23 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-07-30 | No | Complete | Case Closed Out 10/2/14
CENY-Q | MC-60731 | PV | 50 | Yes | Inverter | 2014-02-06 11:21 | 2014-02-07 09:34 | 2014-04-04 | 2014-04-10 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | in progress | Spoke to customer, pending customer to provide manufacture catalog for inverter. (SAME)
CENY-Q | MC-60733 | PV | 50 | Yes | Inverter | 2014-02-06 09:30 | 2014-02-06 10:53 | 2014-04-04 | 2014-04-10 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | in progress | Spoke to customer, pending customer to provide manufacture catalog for inverter. (SAME)
CENY-Q | MC-60883 | PV | 7.6 | Yes | Inverter | 2014-02-06 | 2014-02-11 | 2014-02-11 | 2014-02-19 10:48 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | in progress | Pending PV Install
CENY-Q | MC-61051 | PV | 4.2 | Yes | Inverter | 2014-02-05 | 2014-02-11 | 2014-02-11 | 2014-02-19 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | in progress | Pending PV Install
CENY-Q | MC-61822 | PV | 8 | Yes | Inverter | 2014-02-10 | 2014-02-14 | 2014-02-14 | 2014-02-26 16:26 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-18 | No | Complete | Pending Net Meter Install
CENY-Q | MC-62056 | PV | 5 | Yes | Inverter | 2014-02-11 | 2014-02-14 | 2014-02-27 10:21 | 2014-02-27 10:21 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | in progress | Pending Application Documentation
CENY-Q | MC-62213 | PV | 6 | Yes | Inverter | 2014-02-13 | 2014-02-21 | 2014-02-21 | 2014-02-28 12:45 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending response if case should remain active
CENY-Q | MC-62506 | PV | 3.8 | Yes | Inverter | 2014-02-18 | 2014-02-24 | 2014-02-24 | 2014-03-11 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | in progress | Pending PV Install
CENY-Q | MC-62734 | PV | 3 | Yes | Inverter | 2014-02-17 | 2014-02-24 | 2014-02-24 | 2014-03-11 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | in progress | Pending Application Documentation
CENY-Q | MC-62796 | PV | 5.9 | Yes | Inverter | 2014-02-18 | 2014-02-24 | 2014-03-11 | 2014-03-14 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-24 | No | Complete | Pending Net Meter Install
CENY-Q | MC-64144 | PV | 7 | Yes | Inverter | 2014-03-03 | 2014-03-10 | 2014-03-10 | 2014-03-21 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-11 | No | Complete | Pending Validation & Close-out
CENY-Q | MC-64536 | WT | 15 | Yes | Inverter | 2014-03-14 06:54 | 2014-03-17 | 2014-04-03 | 2014-04-03 | 2014-09-09 | 2014-09-12 | 0 | 0 | 0 | 0 | 0 |  |  | No | in progress | Customer/contractor working on inverter installation. Once they complete, DE to perform verification testing.
CENY-Q | MC-64552 | PV | 4.2 | Yes | Inverter | 2014-03-03 | 2014-03-10 | 2014-03-14 | 2014-04-02 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-07-17 | No | Complete | Pending Validation & Close-out
CENY-Q | MC-64678 | PV | 3 | Yes | Inverter | 2014-03-03 | 2014-03-12 | 2014-03-12 | 2014-04-03 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-04-28 | No | Complete | Pending Net Meter Install
CENY-Q | MC-66635 | PV | 5.2 | Yes | Inverter | 2014-03-14 | 2014-03-20 | 2014-03-20 | 2014-04-04 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-10-14 | No | Complete | Pending Net Meter Install
CENY-Q | MC-67419 | PV | 28 | Yes | Inverter | 2014-03-26 07:24 | 2014-04-01 | 2014-04-02 | 2014-04-14 |  |  | 0 | 0 | 0 | 0 | 0 | 2014-10-10 |  | No | in progress | Inspection completed, pending contractor items.
CENY-Q | MC-67577 | PV | 100 | Yes | Inverter | 2014-03-24 09:28 | 2014-03-31 | 2014-04-01 | 2014-04-03 | 2014-04-05 | 2014-06-10 | 0 | 0 | 0 | 0 | 0 |  |  | No | in progress | Pending contractor install.
CENY-Q | MC-67584 | PV | 55.5 | Yes | Inverter | 2014-03-24 11:28 | 2014-03-31 | 2014-04-01 | 2014-04-03 | 2014-04-05 | 2014-06-10 | 0 | 0 | 0 | 0 | 0 |  |  | No | in progress | Pending contractor install.
CENY-Q | MC-67615 | PV | 5 | Yes | Inverter | 2014-03-19 13:43 | 2014-04-03 | 2014-04-03 | 2014-04-15 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | in progress | Pending PV Install
CENY-Q | MC-68038 | PV | 4.3 | Yes | Inverter | 2014-03-25 13:29 | 2014-03-31 | 2014-04-01 | 2014-04-11 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | in progress | Pending PV Install
CENY-Q | MC-68099 | PV | 42.8 | Yes | Inverter | 2014-03-25 14:07 | 2014-04-08 | 2014-04-08 | 2014-04-29 | 2014-04-29 | 2014-05-21 | 0 | 0 | 0 | 0 | 0 |  |  | No | in progress | Response received 10/2/14, interconnection approved 10/3/14.
CENY-Q | MC-68616 | PV | 4 | Yes | Inverter | 2014-03-25 11:21 | 2014-04-03 | 2014-04-15 | 2014-04-15 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | in progress | Pending PV Install
CENY-Q | MC-68702 | PV | 4.8 | Yes | Inverter | 2014-03-25 14:08 | 2014-04-03 | 2014-04-16 | 2014-04-16 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-08 | No | Complete | Pending Validation & Close-out
CENY-Q | MC-68918 | PV | 7 | Yes | Inverter | 2014-03-26 12:31 | 2014-04-03 | 2014-04-16 | 2014-04-16 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-12 | No | Complete | Pending Validation & Close-out
CENY-Q | MC-68925 | PV | 4.6 | Yes | Inverter | 2014-03-26 12:53 | 2014-04-03 | 2014-04-16 | 2014-04-16 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | in progress | Pending PV Install
CENY-Q | MC-69020 | PV | 4.8 | Yes | Inverter | 2014-03-26 16:58 | 2014-04-03 | 2014-04-03 | 2014-04-15 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | in progress | Pending Application Documentation
CENY-Q | MC-69754 | PV | 3 | Yes | Inverter | 2014-03-31 16:22 | 2014-04-04 | 2014-04-04 | 2014-04-18 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-10-14 | No | Complete | Pending Net Meter Install
CENY-Q | MC-69977 | PV | 6 | Yes | Inverter | 2014-04-01 | 2014-04-30 10:10 | 2014-04-30 10:12 | 2014-05-16 08:58 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | in progress | Pending PV Install
CENY-Q | MC-70249 | PV | 4 | Yes | Inverter | 2014-04-02 | 2014-05-27 10:57 | 2014-05-27 10:57 | 2014-05-27 10:58 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-15 | No | Complete | Pending Validation & Close-out
CENY-Q | MC-70258 | PV | 4.8 | Yes | Inverter | 2014-04-02 | 2014-05-01 12:28 | 2014-05-01 12:30 | 2014-06-20 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | in progress | Pending PV Install
CENY-Q | MC-70329 | PV | 6 | Yes | Inverter | 2014-04-02 | 2014-04-30 11:16 | 2014-04-30 11:18 | 2014-05-16 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | in progress | Pending PV Install
CENY-Q | MC-70458 | PV | 3 | Yes | Inverter | 2014-04-03 | 2014-05-14 11:45 | 2014-05-14 11:52 | 2014-05-14 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-07-30 | No | Complete | Pending Validation & Close-out
CENY-Q | MC-70784 | PV | 3.4 | Yes | Inverter | 2014-04-07 | 2014-05-12 08:13 | 2014-05-12 08:17 | 2014-06-17 14:51 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-10-14 | No | Complete | Pending Net Meter Install
CENY-Q | MC-70787 | PV | 3.2 | Yes | Inverter | 2014-04-07 | 2014-05-07 14:57 | 2014-05-02 | 2014-06-12 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-29 | No | Complete | Pending Validation & Close-out
CENY-Q | MC-70799 | PV | 3.6 | Yes | Inverter | 2014-04-07 | 2014-05-06 08:30 | 2014-05-06 08:32 | 2014-06-27 15:11 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | in progress | Pending PV Install
CENY-Q | MC-73140 | PV | 3.4 | Yes | Inverter | 2014-04-18 | 2014-06-11 09:45 | 2014-06-16 14:29 | 2014-06-23 13:00 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-10 | No | Complete | Pending Validation & Close-out
CENY-Q | MC-73171 | PV | 3 | Yes | Inverter | 2014-04-18 | 2014-04-28 | 2014-06-16 | 2014-06-16 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | in progress | Pending Application Documentation
CENY-Q | MC-73433 | PV | 6 | Yes | Inverter | 2014-04-21 | 2014-06-17 07:54 | 2014-06-17 07:55 | 2014-06-17 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | in progress | Pending PV Install
CENY-Q | MC-73525 | PV | 5.6 | Yes | Inverter | 2014-04-21 | 2014-06-16 15:11 | 2014-06-16 15:14 | 2014-06-16 15:14 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-16 | No | Complete | Pending Validation & Close-out
CENY-Q | MC-73840 | PV | 10 | Yes | Inverter | 2014-04-23 | 2014-05-02 | 2010-06-20 | 2014-07-10 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-18 | No | Complete | Pending Validation & Close-out
CENY-Q | MC-73926 | PV | 5.2 | Yes | Inverter | 2014-04-23 | 2014-05-13 09:03 | 2014-06-18 14:46 | 2014-06-18 14:46 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-16 | No | Complete | Pending Validation & Close-out
CENY-Q | MC-74477 | PV | 14.4 | Yes | Inverter | 2014-04-25 | 2014-05-02 | 2014-06-25 | 2014-07-10 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending Application Documentation
CENY-Q | MC-75030 | PV | 3.4 | Yes | Inverter | 2014-04-29 | 2014-05-13 11:54 | 2014-06-26 12:52 | 2014-06-27 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-01 | No | Complete | Pending Validation & Close-out
CENY-Q | MC-75058 | PV | 4 | Yes | Inverter | 2014-04-29 | 2014-05-13 12:52 | 2014-06-30 08:00 | 2014-06-30 08:01 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-07-28 | No | Complete | Case Completed - Closed Out 09/29/14
CENY-Q | MC-75304 | PV | 6 | Yes | Inverter | 2014-04-30 | 2014-06-11 10:12 | 2014-07-01 08:54 |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | in progress | Pending Application Documents
CENY-Q | MC-75535 | PV | 10 | Yes | Inverter | 2014-05-01 | 2014-05-12 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | in progress | Pending Application Documents
CENY-Q | MC-76431 | PV | 3 | Yes | Inverter | 2014-05-06 | 2014-06-20 15:20 | 2014-06-20 15:25 | 2014-06-20 15:26 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-07-30 | No | Complete | Pending Validation & Close-out
CENY-Q | MC-76466 | PV | 3.8 | Yes | Inverter | 2014-05-06 | 2014-06-20 16:21 | 2014-06-20 16:22 | 2014-06-20 16:23 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | in progress | Pending PV Install
CENY-Q | MC-76695 | PV | 5 | Yes | Inverter | 2014-05-07 | 2014-05-15 12:52 | 2014-07-07 | 2014-07-07 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-10-16 | No | Complete | Pending Net Meter Install
CENY-Q | MC-78438 | PV | 7 | Yes | Inverter | 2014-05-16 | 2014-05-27 | 2014-07-14 | 2014-07-14 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-07-17 | No | Complete | Pending Validation & Close-out
CENY-Q | MC-78448 | PV | 8 | Yes | Inverter | 2014-05-16 | 2014-05-27 | 2014-08-14 16:37 | 2014-08-14 16:38 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-14 | No | Complete | Pending Validation & Close-out
CENY-Q | MC-78974 | PV | 5 | Yes | Inverter | 2014-05-20 | 2014-06-20 17:12 | 2014-06-20 17:13 | 2014-06-20 17:13 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-12 | No | Complete | Pending Validation & Close-out
CENY-Q | MC-79108 | PV | 6.4 | Yes | Inverter | 2014-05-21 | 2014-06-11 10:22 | 2014-07-31 09:19 | 2014-07-31 09:20 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending PV Install
CENY-Q | MC-79496 | PV | 6 | Yes | Inverter | 2014-05-22 | 2014-06-17 11:23 | 2014-07-29 11:01 | 2014-07-29 11:01 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending PV Install
CENY-Q | MC-79656 | PV | 2.8 | Yes | Inverter | 2014-05-23 | 2014-06-11 10:56 | 2014-07-31 09:18 | 2014-07-31 09:19 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending PV Install
CENY-Q | MC-80516 | PV | 100 | YES | Inverter | 2014-05-29 | 2014-06-03 | 2014-08-13 | 2014-08-14 |  |  | 4100 | 0 | 0 | 0 | 0 |  |  | No | in progress | CE Engineering review and comments sent to Customer 8/14/14, pending customer to submit additional doc
CENY-Q | MC-81015 | PV | 3.2 | YES | Inverter | 2014-06-02 | 2014-07-01 14:20 | 2014-07-01 14:23 | 2014-07-01 14:24 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | Submitted - Case Number Assigned
CENY-Q | MC-81032 | PV | 3.6 | Yes | Inverter | 2014-06-02 | 2014-06-04 13:09 | 2014-06-04 13:12 | 2014-06-04 13:13 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | in progress | This case is with Engineering & Planning/Rosanna Zranchev
CENY-Q | MC-81044 | PV | 4 | YES | Inverter | 2014-06-02 | 2014-06-05 10:28 | 2014-06-05 10:31 | 2014-06-05 10:33 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | Submitted - Case Number Assigned
CENY-Q | MC-81257 | PV | 5 | YES | Inverter | 2014-06-03 | 2014-06-11 10:17 | 2014-06-11 10:20 | 2014-06-11 10:21 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | Submitted - Case Number Assigned
CENY-Q | MC-81262 | PV | 16 | YES | Inverter | 2014-06-03 | 2014-06-06 12:54 | 2014-06-06 13:06 | 2014-06-06 13:23 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | Submitted - Case Number Assigned
CENY-Q | MC-81975 | PV | 3.2 | YES | Inverter | 2014-06-06 | 2014-06-11 09:22 | 2014-06-11 09:25 | 2014-06-11 09:26 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | Submitted - Case Number Assigned
CENY-Q | MC-82094 | PV | 3 | YES | Inverter | 2014-06-06 | 2014-06-12 10:55 | 2014-06-12 11:04 | 2014-06-12 11:05 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | Submitted - Case Number Assigned
CENY-Q | MC-83170 | PV | 5 | YES | Inverter | 2014-06-12 | 2014-06-16 12:11 | 2014-06-16 12:14 | 2014-06-16 12:15 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | Submitted - Case Number Assigned
CENY-Q | MC-83250 | PV | 7.6 | YES | Inverter | 2014-06-12 | 2014-06-16 11:10 | 2014-06-16 11:12 | 2014-06-16 11:13 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | Submitted - Case Number Assigned
CENY-Q | MC-83702 | PV | 6 | YES | Inverter | 2014-06-16 | 2014-06-20 14:25 | 2014-06-20 14:26 | 2014-06-20 14:28 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | Submitted - Case Number Assigned
CENY-Q | MC-83759 | PV | 3.8 | YES | Inverter | 2014-06-16 | 2014-06-19 15:27 | 2014-06-19 15:30 | 2014-06-19 15:31 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | Submitted - Case Number Assigned
CENY-Q | MC-83837 | PV | 5 | YES | Inverter | 2014-06-16 | 2014-06-20 12:52 | 2014-06-20 12:53 | 2014-06-20 12:54 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | Submitted - Case Number Assigned
CENY-Q | MC-84053 | PV | 6 | YES | Inverter | 2014-06-17 | 2014-06-22 14:39 | 2014-06-22 14:40 | 2014-06-22 14:41 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-27 | NO | Complete | COMPLETE
CENY-Q | MC-84126 | PV | 32 | YES | Inverter | 2014-06-17 | 2014-06-23 | 2014-06-23 | 2014-06-29 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | in progress | Package forwarded to DE, waiting for response.
CENY-Q | MC-84138 | PV | 96 | YES | Inverter | 2014-06-17 | 2014-06-25 11:10 | 2014-06-25 11:11 | 2014-06-26 | 2014-06-26 | 2014-07-07 | 0 | 0 | 350 | 0 | 0 |  |  | No | in progress | Customer is resolving some financial issues. Construction postponed for a few weeks.
CENY-Q | MC-84268 | PV | 3 | YES | Inverter | 2014-06-18 | 2014-06-24 17:52 | 2014-06-24 17:53 | 2014-06-24 17:53 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | Submitted - Case Number Assigned
CENY-Q | MC-84394 | PV | 3.8 | YES | Inverter | 2014-06-18 | 2014-06-24 13:28 | 2014-06-24 13:26 | 2014-06-24 13:26 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | Submitted - Case Number Assigned
CENY-Q | MC-84765 | PV | 11 | YES | Inverter | 2014-06-20 | 2014-06-24 18:21 | 2014-06-24 18:23 | 2014-06-24 18:24 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | Submitted - Case Number Assigned
CENY-Q | MC-84771 | PV | 5 | YES | Inverter | 2014-06-20 | 2014-06-24 18:52 | 2014-06-24 18:53 | 2014-06-24 18:53 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | Submitted - Case Number Assigned
CENY-Q | MC-84890 | PV | 5 | YES | Inverter | 2014-06-20 | 2014-06-23 14:21 | 2014-06-23 14:22 | 2014-06-23 14:23 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | Submitted - Case Number Assigned
CENY-Q | MC-85142 | PV | 6 | YES | Inverter | 2014-06-23 | 2014-06-25 09:48 | 2014-06-25 09:48 | 2014-06-25 09:49 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | Submitted - Case Number Assigned
CENY-Q | MC-85666 | PV | 5 | YES | Inverter | 2014-06-25 | 2014-06-27 15:03 | 2014-06-27 15:03 | 2014-06-27 15:06 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | Submitted - Case Number Assigned
CENY-Q | MC-86096 | PV | 11 | YES | Inverter | 2014-06-27 | 2014-06-30 | 2014-06-30 | 2014-06-30 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | Cancelled | Submitted - Case Number Assigned
CENY-Q | MC-86625 | PV | 4 | Yes | Inverter | 2014-07-01 | 2014-07-10 09:41 | 2014-07-10 09:42 | 2014-07-10 09:42 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Recieved clarification from the contractor on the address. Sent line diagram approval.
CENY-Q | MC-86809 | PV | 4.6 | YES | Inverter | 2014-07-02 | 2014-07-09 10:36 | 2014-07-09 10:37 | 2014-07-09 10:38 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit. Sent Line Diagram approval ltr. to customer/contractor.
CENY-Q | MC-86872 | PV | 4 | YES | Inverter | 2014-07-02 | 2014-07-09 11:07 | 2014-07-09 11:09 | 2014-07-09 11:12 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit. Sent Line Diagram approval ltr. to customer/contractor.
CENY-Q | MC-86964 | PV | 57 | YES | Inverter | 2014-07-03 | 2014-07-09 15:57 | 2014-07-09 15:58 | 2014-07-11 | 2014-07-11 | 2014-07-16 | 0 | 0 | 0 | 0 | 0 |  |  | No | in progress | Contractor not ready for verification testing yet.
CENY-Q | MC-87033 | PV | 4 | YES | Inverter | 2014-07-03 | 2014-07-11 10:21 | 2014-07-11 10:22 | 2014-07-11 10:23 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Certification Affidavit reviewed. Meter reservation form sent and interconnection final approval letter sent to customer/contractor.
CENY-Q | MC-87038 | PV | 12 | YES | Inverter | 2014-07-03 | 2014-07-09 14:23 | 2014-07-09 14:25 | 2014-07-09 14:27 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | Cancelled | Cancelled, notified customer to resubmit, account number should match name on account, must be the one to submit application.
CENY-Q | MC-87071 | PV | 7.5 | YES | Inverter | 2014-07-03 | 2014-07-04 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Sent email to customer/contractor to rectify account number application vs. CIS (does not match).
CENY-Q | MC-87077 | PV | 9.8 | YES | Inverter | 2014-07-03 | 2014-07-07 00:10 | 2014-07-07 00:12 | 2014-07-07 00:12 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit. Sent Line Diagram approval ltr. to customer/contractor.
CENY-Q | MC-87308 | PV | 6 | YES | Inverter | 2014-07-07 | 2014-07-14 16:06 | 2014-07-15 09:19 | 2014-07-15 09:19 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit. Sent Line Diagram approval ltr. to customer/contractor.
CENY-Q | MC-87432 | PV | 3 | YES | Inverter | 2014-07-07 | 2014-07-15 11:38 | 2014-07-15 11:41 | 2014-07-15 13:00 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit. Sent Line Diagram approval ltr. to customer/contractor.
CENY-Q | MC-87616 | PV | 3.4 | YES | Inverter | 2014-07-08 | 2014-07-15 16:18 | 2014-07-15 16:24 | 2014-07-15 16:25 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit. Sent Line Diagram approval ltr. to customer/contractor.
CENY-Q | MC-87619 | PV | 5 | YES | Inverter | 2014-07-08 | 2014-07-10 21:15 | 2014-07-10 21:16 | 2014-07-10 21:17 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit. Sent Line Diagram approval ltr. to customer/contractor.
CENY-Q | MC-87655 | PV | 3 | YES | Inverter | 2014-07-08 | 2014-07-10 20:01 | 2014-07-10 20:03 | 2014-07-10 20:05 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit. Sent Line Diagram approval ltr. to customer/contractor.
CENY-Q | MC-87663 | PV | 10 | YES | Inverter | 2014-07-08 | 2014-07-10 15:11 | 2014-07-10 15:12 | 2014-07-10 15:13 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit. Sent Line Diagram approval ltr. to customer/contractor.
CENY-Q | MC-87752 | PV | 3 | YES | Inverter | 2014-07-09 | 2014-07-10 | 2014-07-10 15:12 | 2014-07-10 15:13 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit. Sent Line Diagram approval ltr. to customer/contractor.
CENY-Q | MC-87755 | PV | 5 | YES | Inverter | 2014-07-09 | [5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | NO | Cancelled | Cancel application due to unmatched CIS account number. Customer will re-apply for PSN1.
CENY-Q | MC-87878 | PV | 5 | YES | Inverter | 2014-07-09 | 2014-07-10 | 2014-07-10 15:12 | 2014-07-10 15:13 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Resent line diagram approval letter.
CENY-Q | MC-88051 | PV | 8.4 | YES | Inverter | 2014-07-10 | 2014-09-09 13:36 | 2014-09-09 13:37 | 2014-09-09 13:38 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Certification Affidavit reviewed. Meter reservation form sent and interconnection final approval letter sent to customer/contractor.
CENY-Q | MC-88071 | PV | 3.2 | YES | Inverter | 2014-07-10 | 2014-07-10 | 2014-07-10 | 2014-07-10 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit. Sent Line Diagram approval ltr. to customer/contractor.
CENY-Q | MC-88325 | PV | 5 | YES | Inverter | 2014-07-11 | 2014-07-11 | 2014-07-11 | 2014-07-11 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit. Sent Line Diagram approval ltr. to customer/contractor.
CENY-Q | MC-88335 | PV | 3 | YES | Inverter | 2014-07-11 | 2014-07-11 | 2014-07-11 | 2014-07-11 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit. Sent Line Diagram approval ltr. to customer/contractor.
CENY-Q | MC-88851 | PV | 4 | YES | Inverter | 2014-07-15 | 2014-07-15 | 2014-07-18 | 2014-07-18 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit. Sent Line Diagram approval ltr. to customer/contractor.
CENY-Q | MC-89208 | PV | 3 | YES | Inverter | 2014-07-16 | 2014-07-16 | 2014-07-18 | 2014-07-18 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit. Sent Line Diagram approval ltr. to customer/contractor.
CENY-Q | MC-89362 | PV | 3.6 | YES | Inverter | 2014-07-17 | 2014-07-17 | 2014-07-18 | 2014-07-18 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Certification Affidavit reviewed. Meter reservation form sent and interconnection final approval letter sent to customer/contractor.
CENY-Q | MC-89367 | PV | 6 | YES | Inverter | 2014-07-17 | 2014-07-17 | 2014-07-18 | 2014-07-18 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit. Sent Line Diagram approval ltr. to customer/contractor.
CENY-Q | MC-89369 | PV | 5.2 | YES | Inverter | 2014-07-17 | 2014-07-17 | 2014-07-18 | 2014-07-18 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit. Sent Line Diagram approval ltr. to customer/contractor.
CENY-Q | MC-89376 | PV | 3.8 | YES | Inverter | 2014-07-17 | 2014-07-17 | 2014-07-18 | 2014-07-18 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit. Sent Line Diagram approval ltr. to customer/contractor.
CENY-Q | MC-89390 | PV | 3.8 | YES | Inverter | 2014-07-17 | 2014-07-17 | 2014-07-18 | 2014-07-18 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval.
CENY-Q | MC-89411 | PV | 3.4 | YES | Inverter | 2014-07-17 | 2014-07-17 | 2014-07-18 | 2014-07-18 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit. Sent Line Diagram approval ltr. to customer/contractor.
CENY-Q | MC-89426 | PV | 7.8 | YES | Inverter | 2014-07-17 | 2014-07-17 | 2014-07-18 | 2014-07-18 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit. Sent Line Diagram approval ltr. to customer/contractor.
CENY-Q | MC-89443 | PV | 4.2 | YES | Inverter | 2014-07-17 | 2014-07-17 | 2014-07-18 | 2014-07-18 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit. Sent Line Diagram approval ltr. to customer/contractor.
CENY-Q | MC-89463 | PV | 3 | YES | Inverter | 2014-07-17 | 2014-07-17 | 2014-07-18 | 2014-07-18 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit. Sent Line Diagram approval ltr. to customer/contractor.
CENY-Q | MC-89558 | PV | 2.8 | YES | Inverter | 2014-07-18 | 2014-07-18 | 2014-07-18 | 2014-07-18 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit. Sent Line Diagram approval ltr. to customer/contractor.
CENY-Q | MC-89561 | PV | 3.2 | YES | Inverter | 2014-07-18 | 2014-07-18 | 2014-07-18 | 2014-07-18 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit. Sent Line Diagram approval ltr. to customer/contractor.
CENY-Q | MC-89567 | PV | 6 | YES | Inverter | 2014-07-18 | 2014-07-18 | 2014-07-18 | 2014-07-18 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit. Sent Line Diagram approval ltr. to customer/contractor.
CENY-Q | MC-89590 | PV | 3.2 | YES | Inverter | 2014-07-18 | 2014-07-18 | 2014-07-18 | 2014-07-18 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit. Sent Line Diagram approval ltr. to customer/contractor.
CENY-Q | MC-89661 | PV | 3 | YES | Inverter | 2014-07-18 | 2014-07-18 | 2014-07-18 | 2014-07-18 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit. Sent Line Diagram approval ltr. to customer/contractor.
CENY-Q | MC-89937 | PV | 5 | YES | Inverter | 2014-07-21 | 2014-07-21 | 2014-07-24 | 2014-07-24 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Recieved revised DWG. Sent 1 line diagram approval.
CENY-Q | MC-89973 | PV | 20 | YES | Inverter | 2014-07-21 | 2014-07-21 | 2014-07-24 | 2014-07-24 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit. Sent Line Diagram approval ltr. to customer/contractor.
CENY-Q | MC-89979 | PV | 6 | YES | Inverter | 2014-07-21 | 2014-09-09 12:07 | 2014-09-09 12:08 | 2014-09-09 12:09 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Contractor Certification received on 9/4/19. Interconnection final approval letter sent. Meter request sent.
CENY-Q | MC-89980 | PV | 3.6 | YES | Inverter | 2014-07-21 | 2014-07-21 | 2014-07-24 | 2014-07-24 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit. Sent Line Diagram approval ltr. to customer/contractor.
CENY-Q | MC-89982 | PV | 20 | YES | Inverter | 2014-07-21 | 2014-07-21 | 2014-07-24 | 2014-07-24 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Appendix A received. Pending customer to complete work and submit Self-Certification Affidavit.
CENY-Q | MC-89988 | PV | 10.1 | YES | Inverter | 2014-07-21 | 2014-07-21 | 2014-07-24 | 2014-07-24 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit. Sent Line Diagram approval ltr. to customer/contractor.
CENY-Q | MC-89990 | PV | 5 | YES | Inverter | 2014-07-21 | 2014-07-21 | 2014-07-24 | 2014-07-24 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit. Sent Line Diagram approval ltr. to customer/contractor.
CENY-Q | MC-89995 | PV | 200 | YES | Inverter | 2014-07-21 | 2014-08-08 11:22 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | called CPM Awaiting verification of KW (Application states 200Kw, LOA says 6000KW) from BQ CPM Gurinder.
CENY-Q | MC-90005 | PV | 3.4 | YES | Inverter | 2014-07-21 | 2014-07-21 | 2014-07-24 | 2014-07-24 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit. Sent Line Diagram approval ltr. to customer/contractor.
CENY-Q | MC-90013 | PV | 4.3 | YES | Inverter | 2014-07-21 | 2014-07-21 | 2014-07-24 | 2014-07-24 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit. Sent Line Diagram approval ltr. to customer/contractor.
CENY-Q | MC-90182 | PV | 3.8 | YES | Inverter | 2014-07-22 | 2014-07-22 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending Customer - awaiting documents not submitted.
CENY-Q | MC-90193 | PV | 6 | YES | Inverter | 2014-07-22 | 2014-07-22 | 2014-07-24 | 2014-07-24 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit. Sent Line Diagram approval ltr. to customer/contractor.
CENY-Q | MC-90206 | PV | 3.6 | YES | Inverter | 2014-07-22 | 2014-07-22 | 2014-07-24 | 2014-07-24 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit. Sent Line Diagram approval ltr. to customer/contractor.
CENY-Q | MC-90383 | PV | 2.2 | YES | Inverter | 2014-07-23 | 2014-07-23 | 2014-07-24 | 2014-07-24 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit. Sent Line Diagram approval ltr. to customer/contractor.
CENY-Q | MC-90390 | PV | 5 | YES | Inverter | 2014-07-23 | 2014-07-23 | 2014-07-24 | 2014-07-24 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit. Sent Line Diagram approval ltr. to customer/contractor.
CENY-Q | MC-90397 | PV | 6 | YES | Inverter | 2014-07-23 | 2014-07-23 | 2014-07-24 | 2014-07-24 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit. Sent Line Diagram approval ltr. to customer/contractor.
CENY-Q | MC-90419 | PV | 4 | YES | Inverter | 2014-07-23 | 2014-07-23 | 2014-07-24 | 2014-07-24 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit. Sent Line Diagram approval ltr. to customer/contractor.
CENY-Q | MC-90431 | PV | 3.4 | YES | Inverter | 2014-07-23 | 2014-07-23 | 2014-07-24 | 2014-07-24 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit. Sent Line Diagram approval ltr. to customer/contractor.
CENY-Q | MC-90454 | PV | 3.6 | YES | Inverter | 2014-07-23 | 2014-07-23 | 2014-07-24 | 2014-07-24 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit. Sent Line Diagram approval ltr. to customer/contractor.
CENY-Q | MC-90529 | PV | 6 | YES | Inverter | 2014-07-23 | 2014-07-23 | 2014-07-24 | 2014-07-24 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit. Sent Line Diagram approval ltr. to customer/contractor.
CENY-Q | MC-90685 | PV | 5 | YES | Inverter | 2014-07-24 | 2014-07-24 | 2014-07-24 | 2014-07-24 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | previous note incorrect - wrong case. Pending customer to complete work & submit Self-certification Affidavit.
CENY-Q | MC-90781 | PV | 2.6 | YES | Inverter | 2014-07-24 | 2014-07-24 | 2014-07-24 | 2014-07-24 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Sent customer/contractor email requesting update of this case.
CENY-Q | MC-91569 | PV | 3 | YES | Inverter | 2014-07-29 | 2014-07-29 | 2014-08-02 | 2014-08-02 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval.
CENY-Q | MC-91573 | PV | 10 | YES | Inverter | 2014-07-29 | 2014-07-29 | 2014-08-02 | 2014-08-02 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval.
CENY-Q | MC-92333 | PV | 3 | YES | Inverter | 2014-08-01 | 2014-08-01 | 2014-08-02 | 2014-08-02 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval.
CENY-Q | MC-92604 | PV | 14 | YES | Inverter | 2014-08-04 | [5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | NO | Cancelled | At the customer's request case is cancelled. See MC-95305 for new application.
CENY-Q | MC-92749 | PV | 4 | YES | Inverter | 2014-08-05 | 2014-08-25 13:42 | 2014-08-25 13:55 | 2014-08-25 13:56 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Follow-up Meter Exchange has not been completed will check with M&T group.
CENY-Q | MC-92754 | PV | 10 | YES | Inverter | 2014-08-05 | 2014-08-05 | 2014-08-08 | 2014-08-08 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval.
CENY-Q | MC-92795 | PV | 3.8 | YES | Inverter | 2014-08-05 | 2014-08-05 | 2014-08-08 | 2014-08-08 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval.
CENY-Q | MC-92818 | PV | 3.2 | YES | Inverter | 2014-08-05 | 2014-08-05 | 2014-08-08 | 2014-08-08 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Attached line diagram approval ltr.
CENY-Q | MC-92823 | PV | 4.2 | YES | Inverter | 2014-08-05 | 2014-08-05 | 2014-08-08 | 2014-08-08 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Recieved full package. Sent line diagram approval.
CENY-Q | MC-92856 | PV | 5 | YES | Inverter | 2014-08-05 | 2014-08-05 | 2014-08-08 | 2014-08-08 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval.
CENY-Q | MC-92970 | PV | 4.8 | YES | Inverter | 2014-08-06 | 2014-08-06 | 2014-08-08 | 2014-08-08 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Told her that the solar contractor will have to submit the final docs after the installation is complete.
CENY-Q | MC-92980 | PV | 5.6 | YES | Inverter | 2014-08-06 | 2014-08-06 | 2014-08-08 | 2014-08-08 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval.
CENY-Q | MC-92983 | PV | 4 | YES | Inverter | 2014-08-06 | 2014-08-06 | 2014-08-08 | 2014-08-08 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval
CENY-Q | MC-93006 | PV | 2.8 | YES | Inverter | 2014-08-06 | 2014-08-06 | 2014-08-08 | 2014-08-08 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval
CENY-Q | MC-93015 | PV | 3 | YES | Inverter | 2014-08-06 | 2014-08-06 | 2014-08-08 | 2014-08-08 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval
CENY-Q | MC-93065 | PV | 20 | YES | Inverter | 2014-08-06 | 2014-08-06 | 2014-08-08 | 2014-08-08 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval.
CENY-Q | MC-93085 | PV | 20 | YES | Inverter | 2014-08-06 | 2014-08-06 | 2014-08-08 | 2014-08-08 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval
CENY-Q | MC-93092 | PV | 7.6 | YES | Inverter | 2014-08-06 | 2014-08-06 | 2014-08-08 | 2014-08-08 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval.
CENY-Q | MC-93111 | PV | 5 | YES | Inverter | 2014-08-06 | 2014-08-06 | 2014-08-08 | 2014-08-08 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval.
CENY-Q | MC-93279 | PV | 5 | YES | Inverter | 2014-08-07 | 2014-08-07 | 2014-08-08 | 2014-08-08 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval.
CENY-Q | MC-93286 | PV | 4 | YES | Inverter | 2014-08-07 | 2014-08-07 | 2014-08-08 | 2014-08-08 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit. Sent Line Diagram approval ltr. to customer/contractor.
CENY-Q | MC-93503 | PV | 42 | YES | Inverter | 2014-08-08 | 2014-08-08 | 2014-08-08 | 2014-08-08 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval.
CENY-Q | MC-93725 | PV | 9.2 | YES | Inverter | 2014-08-11 | 2014-08-11 | 2014-08-14 | 2014-08-14 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit. Sent Line Diagram approval ltr. to customer/contractor.
CENY-Q | MC-93852 | PV | 6 | YES | Inverter | 2014-08-11 | 2014-08-11 | 2014-08-14 | 2014-08-14 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval.
CENY-Q | MC-93993 | PV | 7.5 | YES | Inverter | 2014-08-12 | 2014-08-12 | 2014-08-14 | 2014-08-14 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit. Sent Line Diagram approval ltr. to customer/contractor.
CENY-Q | MC-94414 | PV | 3.6 | YES | Inverter | 2014-08-14 | 2014-08-14 | 2014-08-14 | 2014-08-14 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit. Sent Line Diagram approval ltr. to customer/contractor.
CENY-Q | MC-94431 | PV | 3 | YES | Inverter | 2014-08-14 | 2014-08-14 | 2014-08-14 | 2014-08-14 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit. Sent Line Diagram approval ltr. to customer/contractor.
CENY-Q | MC-94445 | PV | 4.4 | YES | Inverter | 2014-08-14 | 2014-08-14 | 2014-08-14 | 2014-08-14 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit. Sent Line Diagram approval ltr. to customer/contractor.
CENY-Q | MC-94514 | PV | 4 | YES | Inverter | 2014-08-14 | 2014-08-14 | 2014-08-14 | 2014-08-14 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit. Sent Line Diagram approval ltr. to customer/contractor.
CENY-Q | MC-94546 | PV | 5 | YES | Inverter | 2014-08-14 | 2014-08-14 | 2014-08-14 | 2014-08-14 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit. Sent Line Diagram approval ltr. to customer/contractor.
CENY-Q | MC-94787 | PV | 4.6 | YES | Inverter | 2014-08-15 | 2014-08-15 | 2014-08-19 | 2014-08-19 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit. Sent Line Diagram approval ltr. to customer/contractor.
CENY-Q | MC-94791 | PV | 6 | YES | Inverter | 2014-08-15 | 2014-08-15 | 2014-08-19 | 2014-08-19 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit. Sent Line Diagram approval ltr. to customer/contractor.
CENY-Q | MC-94944 | PV | 4.4 | YES | Inverter | 2014-08-18 | 2014-08-18 | 2014-08-19 | 2014-08-19 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit. Sent Line Diagram approval ltr. to customer/contractor.
CENY-Q | MC-94997 | PV | 63 | YES | Inverter | 2014-08-18 | 2014-08-26 | 2014-09-04 | 2014-09-05 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | in progress | Comments sent to Customer on 9/5/14. Pending field verification to verify CT size for Meter Shop to prepare net meter
CENY-Q | MC-95005 | PV | 45 | YES | Inverter | 2014-08-18 | 2014-08-26 | 2014-08-26 | 2014-09-08 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | in progress | Pending contractor install.
CENY-Q | MC-95018 | PV | 6 | YES | Inverter | 2014-08-18 | 2014-08-18 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Customer pending...still waiting for documents.
CENY-Q | MC-95027 | PV | 27 | YES | Inverter | 2014-08-18 | 2014-08-27 | 2014-08-27 | 2014-09-09 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | in progress | D. Pearsall inter office package to Dan Sammon for review...at 8/27/14
CENY-Q | MC-95032 | PV | 63 | Yes | Inverter | 2014-08-18 | 2014-08-26 | 2014-08-26 | 2014-08-26 | 2014-10-17 |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Sent documents down to DE for review, pending response.
CENY-Q | MC-95038 | PV | 81 | Yes | Inverter | 2014-08-18 | 2014-08-26 | 2014-08-26 | 2014-08-26 | 2014-10-17 |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Sent documents down to DE for review, pending response.
CENY-Q | MC-95070 | PV | 36 | YES | Inverter | 2014-08-18 | 2014-08-26 | 2014-08-26 | 2014-09-08 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | in progress | Pending contractor install.
CENY-Q | MC-95072 | PV | 3.8 | YES | Inverter | 2014-08-18 | 2014-08-18 | 2014-08-19 | 2014-08-19 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit. Sent Line Diagram approval ltr. to customer/contractor.
CENY-Q | MC-95230 | PV | 8 | YES | Inverter | 2014-08-19 | 2014-08-19 | 2014-08-19 | 2014-08-19 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit. Sent Line Diagram approval ltr. to customer/contractor.
CENY-Q | MC-95234 | PV | 15 | YES | Inverter | 2014-08-19 | [5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | NO | Cancelled | At customer's request - Cancel application.
CENY-Q | MC-95236 | PV | 15 | YES | Inverter | 2014-08-19 | 2014-08-25 12:34 | 2014-08-25 12:35 | 2014-08-25 12:36 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Meter WR had to be submitted again, told customer within the next couple of weeks field reps should be exchanging meter.
CENY-Q | MC-95305 | PV | 14 | YES | Inverter | 2014-08-19 | 2014-08-19 | 2014-08-25 | 2014-08-25 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit. Sent Line Diagram approval ltr. to customer/contractor.
CENY-Q | MC-96320 | PV | 2.6 | YES | Inverter | 2014-08-25 | 2014-08-25 | 2014-08-25 | 2014-08-25 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit. Sent Line Diagram approval ltr. to customer/contractor.
CENY-Q | MC-96357 | PV | 6 | YES | Inverter | 2014-08-25 | 2014-08-25 | 2014-08-25 | 2014-08-25 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit. Sent Line Diagram approval ltr. to customer/contractor.
CENY-Q | MC-96468 | PV | 6 | YES | Inverter | 2014-08-26 | 2014-08-26 | 2014-08-28 | 2014-08-28 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit. Sent Line Diagram approval ltr. to customer/contractor.
CENY-Q | MC-96474 | PV | 6 | YES | Inverter | 2014-08-26 | 2014-08-26 | 2014-08-28 | 2014-08-28 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit. Sent Line Diagram approval ltr. to customer/contractor.
CENY-Q | MC-96543 | PV | 3.8 | YES | Inverter | 2014-08-26 | 2014-08-26 | 2014-08-28 | 2014-08-28 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit. Sent Line Diagram approval ltr. to customer/contractor.
CENY-Q | MC-96553 | PV | 5 | YES | Inverter | 2014-08-26 | 2014-08-26 | 2014-08-28 | 2014-08-28 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit. Sent Line Diagram approval ltr. to customer/contractor.
CENY-Q | MC-96560 | PV | 6.8 | YES | Inverter | 2014-08-26 | 2014-08-26 | 2014-08-28 | 2014-08-28 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit. Sent Line Diagram approval ltr. to customer/contractor.
CENY-Q | MC-96586 | PV | 8 | YES | Inverter | 2014-08-26 | 2014-09-09 10:55 | 2014-09-09 10:56 | 2014-09-09 10:57 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Meter Order submitted; expected meter exchange on or about 09/29/14.
CENY-Q | MC-96592 | PV | 6 | YES | Inverter | 2014-08-26 | 2014-08-26 | 2014-08-28 | 2014-08-28 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit. Sent Line Diagram approval ltr. to customer/contractor.
CENY-Q | MC-96709 | PV | 6 | YES | Inverter | 2014-08-27 | 2014-08-27 | 2014-08-28 | 2014-08-28 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Certification Affidavit reviewed. Meter reservation form sent and interconnection final approval letter sent to customer/contractor.
CENY-Q | MC-96711 | PV | 6 | YES | Inverter | 2014-08-27 | 2014-08-27 | 2014-08-28 | 2014-08-28 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Customer called requesting for when net meter will be installed, necessary paper work has not been submitted.
CENY-Q | MC-96726 | PV | 16 | YES | Inverter | 2014-08-27 | 2014-08-27 | 2014-08-28 | 2014-08-28 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit. Sent Line Diagram approval ltr. to customer/contractor.
CENY-Q | MC-96765 | PV | 3.8 | YES | Inverter | 2014-08-27 | 2014-08-27 | 2014-08-28 | 2014-08-28 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS
CENY-Q | MC-96926 | PV | 4 | YES | Inverter | 2014-08-28 | 2014-08-28 | 2014-08-28 | 2014-08-28 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit. Sent Line Diagram approval ltr. to customer/contractor.
CENY-Q | MC-96933 | PV | 4 | YES | Inverter | 2014-08-28 | 2014-08-28 | 2014-08-28 | 2014-08-28 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit. Sent Line Diagram approval ltr. to customer/contractor.
CENY-Q | MC-96951 | PV | 12.6 | YES | Inverter | 2014-08-28 | 2014-08-28 | 2014-08-28 | 2014-08-28 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit. Sent Line Diagram approval ltr. to customer/contractor.
CENY-Q | MC-97121 | PV | 5 | YES | Inverter | 2014-08-29 | 2014-08-29 | 2014-09-08 | 2014-09-08 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit. Sent Line Diagram approval ltr. to customer/contractor.
CENY-Q | MC-97481 | PV | 4.8 | YES | Inverter | 2014-09-03 | 2014-09-03 | 2014-09-08 | 2014-09-08 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit. Sent Line Diagram approval ltr. to customer/contractor
CENY-Q | MC-97635 | PV | 3 | YES | Inverter | 2014-09-03 | 2014-09-03 | 2014-09-08 | 2014-09-08 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit. Sent Line Diagram approval ltr. to customer/contractor.
CENY-Q | MC-98122 | PV | 4 | YES | Inverter | 2014-09-05 | 2014-09-05 | 2014-09-08 | 2014-09-08 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit. Sent Line Diagram approval ltr. to customer/contractor.
CENY-Q | MC-98161 | PV | 6 | YES | Inverter | 2014-09-05 | 2014-09-05 | 2014-09-08 | 2014-09-08 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit. Sent Line Diagram approval ltr. to customer/contractor
CENY-Q | MC-98168 | PV | 7.6 | YES | Inverter | 2014-09-05 | 2014-09-09 15:18 | 2014-09-09 15:19 | 2014-09-09 15:20 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit. Sent Line Diagram approval ltr. to customer/contractor.
CENY-Q | MC-98205 | PV | 4 | YES | Inverter | 2014-09-05 | 2014-09-05 | 2014-09-10 | 2014-09-10 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit. Sent Line Diagram approval ltr. to customer/contractor.
CENY-Q | MC-98254 | PV | 84 | YES | Inverter | 2014-09-05 | 2014-09-12 | 2014-09-12 | 2014-10-03 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | in progress | Clarification requested from customer 10/22/14.
CENY-Q | MC-98418 | PV | 2.6 | YES | Inverter | 2014-09-08 | 2014-09-08 | 2014-09-10 | 2014-09-10 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit. Sent Line Diagram approval ltr. to customer/contractor
CENY-Q | MC-98436 | PV | 4 | YES | Inverter | 2014-09-08 | 2014-09-08 | 2014-09-10 | 2014-09-10 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit. Sent Line Diagram approval ltr. to customer/contractor.
CENY-Q | MC-98458 | PV | 4.4 | YES | Inverter | 2014-09-08 | 2014-09-08 | 2014-09-10 | 2014-09-10 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit. Sent Line Diagram approval ltr. to customer/contractor.
CENY-Q | MC-98477 | PV | 3.2 | YES | Inverter | 2014-09-08 | 2014-09-08 | 2014-09-10 | 2014-09-10 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit. Sent Line Diagram approval ltr. to customer/contractor.
CENY-Q | MC-98487 | PV | 4 | YES | Inverter | 2014-09-08 | 2014-09-08 | 2014-09-10 | 2014-09-10 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit. Sent Line Diagram approval ltr. to customer/contractor.
CENY-Q | MC-98549 | PV | 4.2 | YES | Inverter | 2014-09-08 | 2014-09-08 | 2014-09-10 | 2014-09-10 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit. Sent Line Diagram approval ltr. to customer/contractor.
CENY-Q | MC-98719 | PV | 2.8 | YES | Inverter | 2014-09-09 | 2014-09-09 | 2014-09-10 | 2014-09-10 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit. Sent Line Diagram approval ltr. to customer/contractor.
CENY-Q | MC-98727 | PV | 3.2 | YES | Inverter | 2014-09-09 | 2014-09-09 | 2014-09-10 | 2014-09-10 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit. Sent Line Diagram approval ltr. to customer/contractor.
CENY-Q | MC-98751 | PV | 3 | YES | Inverter | 2014-09-09 | 2014-09-09 | 2014-09-10 | 2014-09-10 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit. Sent Line Diagram approval ltr. to customer/contractor.
CENY-Q | MC-98770 | PV | 4.2 | YES | Inverter | 2014-09-09 | 2014-09-09 | 2014-09-10 | 2014-09-10 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit. Sent Line Diagram approval ltr. to customer/contractor.
CENY-Q | MC-98823 | PV | 3.8 | YES | Inverter | 2014-09-09 | 2014-09-09 | 2014-09-10 | 2014-09-10 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit. Sent Line Diagram approval ltr. to customer/contractor.
CENY-Q | MC-98956 | PV | 3.6 | YES | Inverter | 2014-09-10 | 2014-09-10 | 2014-09-12 | 2014-09-12 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit. Sent Line Diagram approval ltr. to customer/contractor.
CENY-Q | MC-98977 | PV | 6.6 | YES | Inverter | 2014-09-10 | 2014-09-10 | 2014-09-12 | 2014-09-12 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit. Sent Line Diagram approval ltr. to customer/contractor.
CENY-Q | MC-98986 | PV | 3.6 | YES | Inverter | 2014-09-10 | 2014-09-10 | 2014-09-12 | 2014-09-12 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit. Sent Line Diagram approval ltr. to customer/contractor.
CENY-Q | MC-99062 | PV | 2.4 | YES | Inverter | 2014-09-10 | 2014-09-24 14:25 | 2014-09-24 14:26 | 2014-09-24 14:27 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit. Sent Line Diagram approval ltr. to customer/contractor.
CENY-Q | MC-99254 | PV | 3.2 | YES | Inverter | 2014-09-11 | 2014-09-11 | 2014-09-15 | 2014-09-15 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit. Sent Line Diagram approval ltr. to customer/contractor.
CENY-Q | MC-99520 | PV | 5 | YES | Inverter | 2014-09-12 | 2014-09-12 | 2014-09-15 | 2014-09-15 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit. Sent Line Diagram approval ltr. to customer/contractor.
CENY-Q | MC-99528 | PV | 4 | YES | Inverter | 2014-09-12 | 2014-09-12 | 2014-09-15 | 2014-09-15 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit. Sent Line Diagram approval ltr. to customer/contractor.
CENY-Q | MC-99548 | PV | 3.8 | YES | Inverter | 2014-09-12 | 2014-09-12 | 2014-09-15 | 2014-09-15 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit. Sent Line Diagram approval ltr. to customer/contractor.
CENY-Q | MC-99587 | PV | 3.8 | YES | Inverter | 2014-09-12 | 2014-09-12 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | pending customer. Line diagram not submitted.
CENY-Q | MC-99629 | PV | 3.2 | YES | Inverter | 2014-09-12 | [5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | NO | Cancelled | Pending customer to complete work and submit Self-Certification Affidavit. Sent Line Diagram approval ltr. to customer/contractor.
CENY-Q | MC-99636 | PV | 9 | YES | Inverter | 2014-09-12 | 2014-09-12 | 2014-09-20 | 2014-09-20 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit. Sent Line Diagram approval ltr. to customer/contractor.
CENY-Q | MC-99656 | PV | 3.8 | YES | Inverter | 2014-09-12 | 2014-09-12 | 2014-09-20 | 2014-09-20 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit. Sent Line Diagram approval ltr. to customer/contractor.
CENY-Q | MC-99660 | PV | 3 | YES | Inverter | 2014-09-12 | 2014-09-12 | 2014-09-20 | 2014-09-20 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit. Sent Line Diagram approval ltr. to customer/contractor.
CENY-Q | MC-99941 | PV | 6 | YES | Inverter | 2014-09-15 | 2014-09-15 | 2014-09-20 | 2014-09-20 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit. Sent Line Diagram approval ltr. to customer/contractor.
CENY-Q | MC-99990 | PV | 3.8 | YES | Inverter | 2014-09-15 | 2014-09-15 | 2014-09-20 | 2014-09-20 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit. Sent Line Diagram approval ltr. to customer/contractor.
CENY-SI | 1281654 | PV | 594 | Yes | Inverter | 2012-01-05 | 2012-01-05 | 2012-01-06 | 2012-01-12 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending customer build
CENY-SI | 1345021 | PV | 350 | Yes | Inverter | 2012-09-28 | 2012-10-28 | 2012-09-28 | 2012-10-16 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending customer build
CENY-SI | 1345059 | PV | 100 | Yes | Inverter | 2012-09-28 | 2012-10-05 | 2012-09-28 | 2012-10-16 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-08 | No | Complete | Complete
CENY-SI | MC-100064 | PV | 6 | Yes | Inverter | 2014-09-16 | 2014-09-16 10:55 | 2014-09-16 10:58 | 2014-10-03 07:39 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending final documents
CENY-SI | MC-100081 | PV | 5 | Yes | Inverter | 2014-09-16 | 2014-09-16 13:19 | 2014-10-03 07:44 | 2014-10-03 07:49 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending final documents
CENY-SI | MC-100082 | PV | 3.6 | Yes | Inverter | 2014-09-16 | 2014-09-16 13:17 | 2014-09-16 13:18 | 2014-10-07 13:29 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-100118 | PV | 5.9 | Yes | Inverter | 2014-09-16 | 2014-09-17 12:06 | 2014-10-02 09:34 |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | Cancelled | Cancelled
CENY-SI | MC-100139 | PV | 9 | Yes | Inverter | 2014-09-16 | 2014-09-17 15:23 | 2014-09-17 15:24 | 2014-09-17 15:24 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-100143 | PV | 8.4 | Yes | Inverter | 2014-09-16 | 2014-09-18 07:39 | 2014-09-18 07:46 | 2014-09-18 07:47 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-100175 | PV | 11 | Yes | Inverter | 2014-09-16 | 2014-09-18 07:23 | 2014-09-18 07:24 | 2014-09-18 07:25 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-100180 | PV | 5 | Yes | Inverter | 2014-09-16 | 2014-09-17 15:19 | 2014-09-17 15:20 | 2014-09-17 15:20 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-100188 | PV | 5.5 | Yes | Inverter | 2014-09-16 | 2014-09-18 07:15 | 2014-09-18 07:16 | 2014-09-18 07:17 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-100194 | PV | 5.7 | Yes | Inverter | 2014-09-16 | 2014-09-18 10:36 | 2014-10-07 10:22 | 2014-10-07 10:24 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-100339 | PV | 5 | Yes | Inverter | 2014-09-17 | 2014-09-18 10:37 | 2014-10-07 13:06 | 2014-10-07 13:33 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-100574 | PV | 12.3 | Yes | Inverter | 2014-09-18 | 2014-09-19 14:21 | 2014-10-07 13:34 | 2014-10-07 13:35 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-100581 | PV | 3.2 | Yes | Inverter | 2014-09-18 | 2014-09-19 13:43 | 2014-10-02 09:28 |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | Cancelled | Cancelled
CENY-SI | MC-100588 | PV | 8.4 | Yes | Inverter | 2014-09-18 | 2014-09-19 12:25 | 2014-10-07 14:41 | 2014-10-07 14:44 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-100599 | PV | 5.2 | Yes | Inverter | 2014-09-18 | 2014-09-19 13:40 | 2014-10-07 14:45 | 2014-10-07 14:58 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-100606 | PV | 5.8 | Yes | Inverter | 2014-09-18 | 2014-09-19 13:37 | 2014-10-02 09:30 |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | Cancelled | Cancelled
CENY-SI | MC-100607 | PV | 4.2 | Yes | Inverter | 2014-09-18 | 2014-09-19 14:10 | 2014-10-07 14:59 | 2014-10-07 15:02 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-100609 | PV | 3.2 | Yes | Inverter | 2014-09-18 | 2014-09-19 13:36 | 2014-10-02 09:31 |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | Cancelled | Cancelled
CENY-SI | MC-100614 | PV | 3.4 | Yes | Inverter | 2014-09-18 | 2014-09-19 13:04 | 2014-10-07 15:03 | 2014-10-07 15:05 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-100637 | PV | 7.2 | Yes | Inverter | 2014-09-18 | 2014-09-19 12:59 | 2014-10-07 15:05 | 2014-10-07 15:08 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-100642 | PV | 6.8 | Yes | Inverter | 2014-09-18 | 2014-09-19 12:55 | 2014-10-07 15:09 | 2014-10-07 15:11 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-100649 | PV | 6 | Yes | Inverter | 2014-09-18 | 2014-09-19 12:41 | 2014-10-07 15:12 | 2014-10-07 15:14 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-100673 | PV | 3.8 | Yes | Inverter | 2014-09-18 | 2014-09-19 12:33 | 2014-10-07 15:16 | 2014-10-07 15:18 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-100782 | PV | 12 | Yes | Inverter | 2014-09-19 | 2014-09-22 15:24 | 2014-10-08 14:22 | 2014-10-08 14:25 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-100814 | PV | 3 | Yes | Inverter | 2014-09-19 | 2014-09-22 12:39 | 2014-10-08 14:26 | 2014-10-08 14:28 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-100817 | PV | 6 | Yes | Inverter | 2014-09-19 | 2014-09-22 16:09 | 2014-10-08 14:29 | 2014-10-08 14:31 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-100830 | PV | 6.8 | Yes | Inverter | 2014-09-19 | 2014-09-22 12:29 | 2014-10-08 14:32 | 2014-10-08 14:34 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-100879 | PV | 6.8 | Yes | Inverter | 2014-09-19 | 2014-09-22 15:20 | 2014-10-08 14:35 | 2014-10-08 14:38 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-100989 | PV | 8 | Yes | Inverter | 2014-09-22 | 2014-09-22 12:33 | 2014-10-08 14:38 | 2014-10-08 14:41 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-101022 | PV | 6 | Yes | Inverter | 2014-09-22 | 2014-09-23 14:53 | 2014-10-08 14:42 | 2014-10-08 14:44 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-101063 | PV | 7 | Yes | Inverter | 2014-09-22 | 2014-09-23 14:51 | 2014-10-08 14:45 | 2014-10-08 14:48 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-101132 | PV | 9 | Yes | Inverter | 2014-09-22 | 2014-09-23 14:56 | 2014-10-08 14:49 | 2014-10-08 14:51 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-101150 | PV | 6 | Yes | Inverter | 2014-09-22 | 2014-09-23 14:58 | 2014-10-08 14:52 | 2014-10-08 14:55 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-101172 | PV | 10 | Yes | Inverter | 2014-09-22 | 2014-09-24 08:14 | 2014-10-08 14:56 | 2014-10-08 14:59 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-101176 | PV | 6 | Yes | Inverter | 2014-09-22 | 2014-09-23 15:01 | 2014-10-08 15:00 | 2014-10-08 15:05 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-101177 | PV | 7.6 | Yes | Inverter | 2014-09-22 | 2014-09-23 15:04 | 2014-10-08 15:11 | 2014-10-08 15:13 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-101179 | PV | 11.4 | Yes | Inverter | 2014-09-22 | 2014-09-23 15:06 | 2014-10-08 15:14 | 2014-10-08 15:16 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-101199 | PV | 5.4 | Yes | Inverter | 2014-09-22 | 2014-09-23 15:08 | 2014-10-08 15:17 | 2014-10-08 15:20 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-101318 | PV | 6.6 | Yes | Inverter | 2014-09-23 | 2014-09-24 12:01 | 2014-10-08 15:21 | 2014-10-08 15:23 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-101328 | PV | 4.5 | Yes | Inverter | 2014-09-23 | 2014-09-24 11:38 | 2014-10-08 15:23 | 2014-10-08 15:25 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-101375 | PV | 3.6 | Yes | Inverter | 2014-09-23 | 2014-09-24 11:35 | 2014-10-09 07:16 | 2014-10-09 07:25 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-101382 | PV | 10 | Yes | Inverter | 2014-09-23 | 2014-09-24 12:03 | 2014-10-09 07:25 | 2014-10-09 07:27 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-101486 | PV | 13.2 | Yes | Inverter | 2014-09-24 | 2014-09-30 15:21 | 2014-09-30 15:22 | 2014-09-30 15:22 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-101526 | PV | 17 | Yes | Inverter | 2014-09-24 | 2014-09-30 15:18 | 2014-09-30 15:18 | 2014-09-30 15:19 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-101540 | PV | 5 | Yes | Inverter | 2014-09-24 | 2014-09-25 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | Cancelled | Cancelled
CENY-SI | MC-101542 | PV | 3.2 | Yes | Inverter | 2014-09-24 | 2014-09-30 15:13 | 2014-09-30 15:13 | 2014-09-30 15:14 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-101556 | PV | 4.8 | Yes | Inverter | 2014-09-24 | 2014-09-30 15:03 | 2014-09-30 15:06 | 2014-09-30 15:06 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | Cancelled | Cancelled
CENY-SI | MC-101567 | PV | 6.8 | Yes | Inverter | 2014-09-24 | 2014-09-30 14:54 | 2014-09-30 14:55 | 2014-09-30 14:56 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-101587 | PV | 6.8 | Yes | Inverter | 2014-09-24 | 2014-09-30 14:46 | 2014-09-30 14:50 | 2014-09-30 14:50 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-101685 | PV | 17.5 | Yes | Inverter | 2014-09-25 | 2014-09-25 08:45 | 2014-09-25 08:46 | 2014-09-25 08:46 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-10-02 | No | Complete | Complete
CENY-SI | MC-101706 | PV | 6 | Yes | Inverter | 2014-09-25 | 2014-09-29 12:22 | 2014-09-29 12:23 | 2014-09-29 12:23 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending final documents
CENY-SI | MC-101722 | PV | 6 | Yes | Inverter | 2014-09-25 | 2014-09-29 12:26 | 2014-09-29 12:27 | 2014-09-29 12:27 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending final documents
CENY-SI | MC-101755 | PV | 7.2 | Yes | Inverter | 2014-09-25 | 2014-09-29 12:30 | 2014-09-29 12:30 | 2014-09-29 12:31 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-101848 | PV | 5 | Yes | Inverter | 2014-09-25 | 2014-09-29 12:15 | 2014-09-29 12:16 | 2014-09-29 12:18 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-101915 | PV | 9.8 | Yes | Inverter | 2014-09-26 | 2014-09-30 13:51 | 2014-09-30 13:52 | 2014-09-30 13:52 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-101921 | PV | 5 | Yes | Inverter | 2014-09-26 | 2014-09-30 13:13 | 2014-09-30 13:13 | 2014-09-30 13:14 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-101924 | PV | 6.8 | Yes | Inverter | 2014-09-26 | 2014-09-30 13:08 | 2014-09-30 13:10 | 2014-09-30 13:09 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-101938 | PV | 6.8 | Yes | Inverter | 2014-09-26 | 2014-09-30 13:05 | 2014-09-30 13:06 | 2014-09-30 13:06 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-101939 | PV | 6.8 | Yes | Inverter | 2014-09-26 | 2014-09-30 13:03 | 2014-09-30 13:03 | 2014-09-30 13:03 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-101943 | PV | 7.6 | Yes | Inverter | 2014-09-26 | 2014-09-30 13:00 | 2014-09-30 13:00 | 2014-09-30 13:00 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-101948 | PV | 6 | Yes | Inverter | 2014-09-26 | 2014-09-30 12:57 | 2014-09-30 12:57 | 2014-09-30 12:57 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-101979 | PV | 7.6 | Yes | Inverter | 2014-09-26 | 2014-09-30 12:54 | 2014-09-30 12:54 | 2014-09-30 12:54 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-101988 | PV | 7.6 | Yes | Inverter | 2014-09-26 | 2014-09-30 12:49 | 2014-09-30 12:50 | 2014-09-30 12:51 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-101995 | PV | 3.8 | Yes | Inverter | 2014-09-26 | 2014-09-30 12:47 | 2014-09-30 12:47 | 2014-09-30 12:47 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-102000 | PV | 6 | Yes | Inverter | 2014-09-26 | 2014-09-30 12:44 | 2014-09-30 12:44 | 2014-09-30 12:44 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-102015 | PV | 6.9 | Yes | Inverter | 2014-09-26 | 2014-09-30 12:42 | 2014-09-30 12:42 | 2014-09-30 12:42 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-10-07 | No | Complete | Complete
CENY-SI | MC-102037 | PV | 7.5 | Yes | Inverter | 2014-09-26 | 2014-09-30 12:39 | 2014-09-30 12:39 | 2014-09-30 12:39 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending meter exchange
CENY-SI | MC-102237 | PV | 6 | Yes | Inverter | 2014-09-29 | 2014-09-30 12:31 | 2014-10-09 07:29 | 2014-10-09 07:32 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-102262 | PV | 3 | Yes | Inverter | 2014-09-29 | 2014-09-30 12:27 | 2014-10-09 07:53 | 2014-10-09 08:00 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-102291 | PV | 5 | Yes | Inverter | 2014-09-29 | 2014-09-30 12:24 | 2014-10-09 08:02 | 2014-10-09 08:07 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-102414 | MT | 3.4 | YES | Inverter | 2014-09-30 | 2014-10-01 14:55 | 2014-10-09 08:08 | 2014-10-09 08:14 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-102461 | PV | 12 | Yes | Inverter | 2014-09-30 | 2014-10-01 14:54 | 2014-10-09 08:15 | 2014-10-09 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-102466 | PV | 3.8 | Yes | Inverter | 2014-09-30 | 2014-10-01 14:52 | 2014-10-09 08:19 | 2014-10-09 08:23 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-102489 | PV | 5 | Yes | Inverter | 2014-09-30 | 2014-10-01 14:50 | 2014-10-09 08:27 | 2014-10-09 08:32 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-102506 | PV | 9 | Yes | Inverter | 2014-09-30 | 2014-10-01 14:48 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-102515 | PV | 3.8 | Yes | Inverter | 2014-09-30 | 2014-10-01 14:46 | 2014-10-07 08:07 | 2014-10-07 08:11 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending meter exchange
CENY-SI | MC-102525 | PV | 6 | Yes | Inverter | 2014-09-30 | 2014-10-01 14:44 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-102561 | PV | 5 | Yes | Inverter | 2014-09-30 | 2014-10-01 14:41 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-102573 | PV | 11.4 | Yes | Inverter | 2014-09-30 | 2014-10-01 14:39 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-1207 | PV | 200 | Yes | Inverter | 2013-06-06 | 2013-06-13 | 2013-06-13 | 2013-06-27 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | YES | In Progress | Pending customer build
CENY-SI | MC-1217 | PV | 1000 | Yes | Inverter | 2013-06-09 | 2013-06-15 | 2013-09-19 10:38 | 2013-10-03 | 2013-10-03 | 2013-10-14 | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Forwarded DE review comments on Customer's short circuit & coordination study.
CENY-SI | MC-20244 | PV | 3 | Yes | Inverter | 2013-08-08 | 2013-08-09 | 2013-08-09 | 2013-08-09 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | Cancelled | Cancelled
CENY-SI | MC-20554 | PV | 100 | Yes | Inverter | 2013-08-12 | 2013-08-13 | 2014-08-08 09:38 | 2014-08-08 09:39 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-10-20 | No | Complete | Complete
CENY-SI | MC-20556 | PV | 100 | Yes | Inverter | 2013-08-12 | 2013-08-13 | 2014-08-08 09:53 | 2014-08-08 09:53 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-10-20 | No | Complete | Complete
CENY-SI | MC-22862 | PV | 8.1 | Yes | Inverter | 2013-09-10 | 2013-09-10 | 2013-09-10 | 2013-09-10 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-07-23 | No | Complete | Complete
CENY-SI | MC-22873 | PV | 7.2 | Yes | Inverter | 2013-09-10 | 2013-09-10 | 2013-09-10 | 2013-09-10 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-07-23 | No | Complete | Complete
CENY-SI | MC-22875 | PV | 4.5 | Yes | Inverter | 2013-09-10 | 2013-09-10 | 2013-09-10 | 2013-09-10 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-07-23 | No | Complete | Complete
CENY-SI | MC-31689 | PV | 4 | Yes | Inverter | 2013-09-16 | 2013-09-16 | 2013-09-16 | 2013-09-16 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | Cancelled | Cancelled
CENY-SI | MC-32103 | PV | 2.5 | Yes | Inverter | 2013-09-18 | 2013-09-19 | 2014-06-18 09:44 | 2014-06-18 09:44 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-07-14 | No | Complete | Complete
CENY-SI | MC-32104 | PV | 3 | Yes | Inverter | 2013-09-18 | 2013-09-19 | 2014-06-18 09:53 | 2014-06-18 09:53 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-07-14 | No | Complete | Complete
CENY-SI | MC-32105 | PV | 2.5 | Yes | Inverter | 2013-09-18 | 2013-09-19 | 2014-06-18 09:26 | 2014-06-18 09:26 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-07-14 | No | Complete | Complete
CENY-SI | MC-32107 | PV | 3 | Yes | Inverter | 2013-09-18 | 2013-09-19 | 2014-06-18 09:37 | 2014-06-18 09:38 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-07-14 | No | Complete | Complete
CENY-SI | MC-32151 | PV | 4 | Yes | Inverter | 2013-09-18 | 2013-09-19 | 2013-09-19 | 2013-09-19 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-22 | No | Complete | Complete
CENY-SI | MC-32825 | PV | 4 | Yes | Inverter | 2013-09-23 | 2013-09-23 | 2013-09-24 | 2013-09-24 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | Cancelled | Cancelled
CENY-SI | MC-35451 | PV | 8.4 | Yes | Inverter | 2013-10-11 14:55 | 2013-10-17 08:39 | 2013-10-12 | 2013-10-16 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending final documents
CENY-SI | MC-36250 | PV | 5 | Yes | Inverter | 2013-10-18 16:22 | 2013-10-24 08:10 | 2013-10-22 | 2013-10-22 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-19 | No | Complete | Complete
CENY-SI | MC-36257 | PV | 4.5 | Yes | Inverter | 2013-10-18 16:32 | 2013-10-22 07:45 | 2013-10-29 | 2013-10-29 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-01 | No | Complete | Complete
CENY-SI | MC-36571 | PV | 6 | Yes | Inverter | 2013-10-22 12:06 | 2013-10-31 09:27 | 2013-10-23 | 2013-10-24 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-19 | No | Complete | Complete
CENY-SI | MC-37670 | PV | 9.8 | Yes | Inverter | 2013-10-30 09:41 | 2013-11-07 11:07 | 2013-10-31 | 2013-10-31 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-07-25 | No | Complete | Complete
CENY-SI | MC-37693 | PV | 3 | Yes | Inverter | 2013-10-30 10:41 | 2013-11-15 10:03 | 2013-11-05 | 2013-11-12 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending final documents
CENY-SI | MC-38119 | PV | 3.5 | Yes | Inverter | 2013-11-01 13:11 | 2013-11-14 11:30 | 2013-11-05 | 2013-11-05 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending final documents
CENY-SI | MC-38169 | PV | 11.4 | Yes | Inverter | 2013-11-01 15:42 | 2013-11-15 10:15 | 2013-11-07 | 2013-11-12 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-28 | No | Complete | Complete
CENY-SI | MC-38199 | PV | 6 | Yes | Inverter | 2013-11-01 19:58 | 2013-11-14 09:51 | 2013-11-05 | 2013-11-05 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | Cancelled | Cancelled
CENY-SI | MC-38452 | PV | 3.5 | Yes | Inverter | 2013-11-04 16:48 | 2013-11-15 10:38 | 2013-11-07 | 2013-11-07 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | Cancelled | Cancelled
CENY-SI | MC-38454 | PV | 3.5 | Yes | Inverter | 2013-11-04 16:51 | 2013-11-15 11:02 | 2013-11-07 | 2013-11-07 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-30 | No | Complete | Complete
CENY-SI | MC-38517 | PV | 6.5 | Yes | Inverter | 2013-11-05 09:13 | 2013-11-19 09:48 | 2013-11-07 | 2013-11-07 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | Cancelled | Cancelled
CENY-SI | MC-38518 | PV | 3.5 | Yes | Inverter | 2013-11-05 09:20 | 2013-11-19 09:37 | 2013-11-07 | 2013-11-07 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-24 | No | Complete | Complete
CENY-SI | MC-38556 | PV | 9.6 | Yes | Inverter | 2013-11-05 11:57 | 2013-11-15 15:02 | 2013-11-07 | 2013-11-07 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending final documents
CENY-SI | MC-38866 | PV | 10 | Yes | Inverter | 2013-11-07 10:09 | 2013-11-19 10:38 | 2013-11-12 | 2013-11-12 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-07-25 | No | Complete | Complete
CENY-SI | MC-38893 | PV | 6 | Yes | Inverter | 2013-11-07 11:27 | 2013-11-19 10:53 | 2013-11-12 | 2013-11-12 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending final documents
CENY-SI | MC-45790 | PV | 3.3 | Yes | Inverter | 2013-11-11 13:15 | 2013-11-19 13:45 | 2013-11-12 | 2013-11-12 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-19 | No | Complete | Complete
CENY-SI | MC-46888 | PV | 7.2 | Yes | Inverter | 2013-11-14 10:57 | 2013-11-21 13:21 | 2013-11-14 | 2013-11-14 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-12 | No | Complete | Complete
CENY-SI | MC-47535 | PV | 13 | Yes | Inverter | 2013-11-18 12:44 | 2013-11-22 11:15 | 2013-11-18 | 2013-11-18 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-19 | No | Complete | Complete
CENY-SI | MC-48293 | PV | 6.6 | Yes | Inverter | 2013-11-21 01:42 | 2013-12-13 08:47 | 2013-11-26 | 2013-11-26 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | Cancelled | Cancelled
CENY-SI | MC-48362 | PV | 5 | Yes | Inverter | 2013-11-21 10:45 | 2013-12-06 07:34 | 2013-11-22 | 2013-11-22 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | Cancelled | Cancelled
CENY-SI | MC-48540 | PV | 6 | Yes | Inverter | 2013-11-21 19:59 | 2013-12-03 13:01 | 2013-11-22 | 2013-11-22 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-10-09 | No | Complete | Complete
CENY-SI | MC-48846 | PV | 5 | Yes | Inverter | 2013-11-23 18:31 | 2013-12-30 07:25 | 2013-11-26 | 2013-11-27 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | Cancelled | Cancelled
CENY-SI | MC-48867 | PV | 8 | Yes | Inverter | 2013-11-23 18:31 | 2013-12-23 11:04 | 2013-11-26 | 2013-11-27 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending final documents
CENY-SI | MC-48872 | PV | 15.6 | Yes | Inverter | 2013-11-23 18:32 | 2013-12-26 09:10 | 2013-11-26 | 2013-11-27 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending final documents
CENY-SI | MC-49064 | PV | 11 | Yes | Inverter | 2013-11-25 11:52 | 2013-12-26 10:55 | 2013-11-27 | 2013-11-27 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-07-25 | No | Complete | Complete
CENY-SI | MC-49459 | PV | 3.6 | Yes | Inverter | 2013-11-26 16:16 | 2013-12-27 13:30 | 2013-11-27 | 2013-11-27 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-02 | No | Complete | Complete
CENY-SI | MC-49570 | PV | 4.5 | Yes | Inverter | 2013-11-27 11:17 | 2013-12-17 13:42 | 2013-12-03 | 2013-12-03 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-19 | No | Complete | Complete
CENY-SI | MC-49803 | PV | 3.6 | Yes | Inverter | 2013-11-30 11:43 | 2013-12-13 10:26 | 2013-12-03 | 2013-12-03 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending final documents
CENY-SI | MC-49816 | PV | 12 | Yes | Inverter | 2013-11-30 15:38 | 2013-12-17 11:57 | 2013-12-03 | 2013-12-03 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending final documents
CENY-SI | MC-49821 | PV | 4.2 | Yes | Inverter | 2013-11-30 17:19 | 2013-12-13 10:12 | 2013-12-03 | 2013-12-03 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | Cancelled | Cancelled
CENY-SI | MC-49896 | PV | 3.8 | Yes | Inverter | 2013-12-02 09:29 | 2013-12-27 07:45 | 2013-12-03 | 2013-12-03 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-07-25 | No | Complete | Complete
CENY-SI | MC-49978 | PV | 3.5 | Yes | Inverter | 2013-12-02 13:39 | 2013-12-17 14:44 | 2013-12-03 | 2013-12-03 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | Cancelled | Cancelled
CENY-SI | MC-50059 | PV | 4.6 | Yes | Inverter | 2013-12-02 17:25 | 2013-12-17 14:09 | 2013-12-03 | 2013-12-03 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-24 | No | Complete | Complete
CENY-SI | MC-50086 | PV | 6.6 | Yes | Inverter | 2013-12-02 19:43 | 2013-12-17 13:53 | 2013-12-03 | 2013-12-03 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | Cancelled | Cancelled
CENY-SI | MC-50274 | PV | 10 | Yes | Inverter | 2013-12-03 14:51 | 2013-12-12 11:01 | 2013-12-05 | 2013-12-05 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-07-30 | No | Complete | Complete
CENY-SI | MC-50320 | PV | 7.4 | Yes | Inverter | 2013-12-03 17:36 | 2013-12-05 08:38 | 2013-12-05 08:40 | 2013-12-05 08:41 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-11 | No | Complete | Complete
CENY-SI | MC-50482 | PV | 6 | Yes | Inverter | 2013-12-04 13:33 | 2013-12-06 07:17 | 2013-12-06 07:19 | 2013-12-06 07:20 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-07-30 | No | Complete | Complete
CENY-SI | MC-51118 | PV | 6.6 | Yes | Inverter | 2013-12-06 13:26 | 2013-12-10 08:39 | 2013-12-10 | 2013-12-10 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending final documents
CENY-SI | MC-51124 | PV | 7 | Yes | Inverter | 2013-12-06 13:52 | 2013-12-10 14:30 | 2013-12-10 | 2013-12-10 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-19 | No | Complete | Complete
CENY-SI | MC-51264 | PV | 6.6 | Yes | Inverter | 2013-12-07 12:37 | 2013-12-10 10:29 | 2013-12-10 | 2013-12-10 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-09 | No | Complete | Complete
CENY-SI | MC-51343 | PV | 6 | Yes | Inverter | 2013-12-09 08:59 | 2013-12-10 14:37 | 2013-12-10 | 2013-12-10 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-08 | No | Complete | Complete
CENY-SI | MC-51656 | PV | 8 | Yes | Inverter | 2013-12-10 11:31 | 2013-12-12 09:42 | 2013-12-12 | 2013-12-12 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending final documents
CENY-SI | MC-51927 | PV | 8 | Yes | Inverter | 2013-12-11 11:26 | 2013-12-12 09:25 | 2013-12-12 | 2013-12-12 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-07-25 | No | Complete | Complete
CENY-SI | MC-52020 | PV | 6 | Yes | Inverter | 2013-12-11 15:07 | 2013-12-12 09:35 | 2013-12-12 | 2013-12-12 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending final documents
CENY-SI | MC-52790 | PV | 7.5 | Yes | Inverter | 2013-12-13 13:59 | 2013-12-17 10:53 | 2013-12-17 | 2013-12-17 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending final documents
CENY-SI | MC-52797 | PV | 8.6 | Yes | Inverter | 2013-12-13 14:31 | 2013-12-17 10:47 | 2013-12-17 | 2013-12-17 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending final documents
CENY-SI | MC-52813 | PV | 7.8 | Yes | Inverter | 2013-12-13 15:21 | 2013-12-17 11:09 | 2013-12-17 | 2013-12-17 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending final documents
CENY-SI | MC-52831 | PV | 4.2 | Yes | Inverter | 2013-12-13 16:08 | 2013-12-17 11:22 | 2013-12-17 | 2013-12-17 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-19 | No | Complete | Complete
CENY-SI | MC-53392 | PV | 17.5 | Yes | Inverter | 2013-12-17 13:51 | 2013-12-23 07:49 | 2013-12-19 | 2013-12-19 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-07-23 | No | Complete | Complete
CENY-SI | MC-53406 | PV | 9.2 | Yes | Inverter | 2013-12-17 14:28 | 2013-12-23 07:39 | 2013-12-19 | 2013-12-19 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending final documents
CENY-SI | MC-53446 | PV | 3.6 | Yes | Inverter | 2013-12-17 16:20 | 2013-12-26 14:09 | 2013-12-19 | 2013-12-19 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending final documents
CENY-SI | MC-53577 | PV | 4.2 | Yes | Inverter | 2013-12-18 08:28 | 2013-12-20 08:25 | 2013-12-19 | 2013-12-19 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | Cancelled | Cancelled
CENY-SI | MC-54257 | PV | 12 | Yes | Inverter | 2013-12-19 | 2013-12-19 | 2013-12-19 | 2013-12-19 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-07-25 | No | Complete | Complete
CENY-SI | MC-54304 | PV | 7.6 | Yes | Inverter | 2013-12-19 | 2013-12-20 | 2013-12-20 | 2014-01-02 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending final documents
CENY-SI | MC-54333 | PV | 6 | Yes | Inverter | 2013-12-19 16:09 | 2013-12-23 09:01 | 2013-12-23 | 2013-12-23 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending final documents
CENY-SI | MC-54345 | PV | 6.5 | Yes | Inverter | 2013-12-19 16:43 | 2013-12-23 08:42 | 2013-12-23 | 2013-12-23 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending final documents
CENY-SI | MC-54352 | PV | 14 | Yes | Inverter | 2013-12-19 | 2013-12-20 | 2013-12-20 | 2014-01-02 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending final documents
CENY-SI | MC-54362 | PV | 11 | Yes | Inverter | 2013-12-19 18:09 | 2013-12-23 08:33 | 2013-12-23 | 2013-12-23 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending final documents
CENY-SI | MC-54363 | PV | 6 | Yes | Inverter | 2013-12-19 | 2013-12-20 | 2013-12-20 | 2014-01-02 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending final documents
CENY-SI | MC-54366 | PV | 6 | Yes | Inverter | 2013-12-19 18:45 | 2013-12-23 08:26 | 2013-12-23 | 2013-12-23 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending final documents
CENY-SI | MC-54398 | PV | 4 | Yes | Inverter | 2013-12-20 08:00 | 2013-12-30 10:13 | 2013-12-24 | 2013-12-24 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending final documents
CENY-SI | MC-54409 | PV | 7.8 | Yes | Inverter | 2013-12-20 08:48 | 2013-12-30 08:18 | 2013-12-24 | 2013-12-24 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | Cancelled | Cancelled
CENY-SI | MC-54416 | PV | 11 | Yes | Inverter | 2013-12-20 09:24 | 2013-12-30 08:23 | 2013-12-24 | 2013-12-24 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending final documents
CENY-SI | MC-54436 | PV | 6.5 | Yes | Inverter | 2013-12-20 10:12 | 2013-12-30 08:47 | 2013-12-24 | 2013-12-24 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending final documents
CENY-SI | MC-54448 | PV | 7.2 | Yes | Inverter | 2013-12-20 10:36 | 2013-12-30 08:06 | 2013-12-24 | 2013-12-24 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-01 | No | Complete | Complete
CENY-SI | MC-54452 | PV | 14 | Yes | Inverter | 2013-12-20 10:50 | 2013-12-30 09:52 | 2013-12-24 | 2013-12-24 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending final documents
CENY-SI | MC-54459 | PV | 11 | Yes | Inverter | 2013-12-20 10:58 | 2013-12-30 09:04 | 2013-12-24 | 2013-12-24 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-11 | No | Complete | Complete
CENY-SI | MC-54485 | PV | 3 | Yes | Inverter | 2013-12-20 12:36 | 2013-12-30 10:05 | 2013-12-24 | 2013-12-24 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-08 | No | Complete | Complete
CENY-SI | MC-54678 | PV | 12.2 | Yes | Inverter | 2013-12-23 12:12 | 2013-12-27 10:01 | 2013-12-27 | 2013-12-27 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending final documents
CENY-SI | MC-54698 | PV | 9.2 | Yes | Inverter | 2013-12-23 13:16 | 2013-12-27 10:18 | 2013-12-27 | 2013-12-27 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | Cancelled | Cancelled
CENY-SI | MC-54724 | PV | 7 | Yes | Inverter | 2013-12-23 15:13 | 2013-12-27 10:56 | 2013-12-27 | 2013-12-27 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-19 | No | Complete | Complete
CENY-SI | MC-54760 | PV | 7.5 | Yes | Inverter | 2013-12-23 17:39 | 2013-12-27 12:51 | 2013-12-27 | 2013-12-27 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending final documents
CENY-SI | MC-54764 | PV | 7.8 | Yes | Inverter | 2013-12-23 17:53 | 2013-12-27 12:58 | 2013-12-27 | 2013-12-27 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending final documents
CENY-SI | MC-54836 | PV | 10 | Yes | Inverter | 2013-12-24 09:47 | 2013-12-27 11:17 | 2013-12-27 | 2013-12-27 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-06-26 | No | Complete | Complete
CENY-SI | MC-54863 | PV | 10 | Yes | Inverter | 2013-12-24 11:31 | 2013-12-27 11:42 | 2013-12-27 | 2013-12-27 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-19 | No | Complete | Complete
CENY-SI | MC-54876 | PV | 6 | Yes | Inverter | 2013-12-24 12:23 | 2013-12-27 11:27 | 2013-12-27 | 2013-12-27 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-11 | No | Complete | Complete
CENY-SI | MC-55054 | PV | 8 | Yes | Inverter | 2013-12-26 16:52 | 2013-12-27 13:11 | 2013-12-27 | 2013-12-27 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-26 | No | Complete | Complete
CENY-SI | MC-55060 | PV | 6 | Yes | Inverter | 2013-12-26 17:10 | 2013-12-27 09:24 | 2013-12-27 | 2013-12-27 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-01 | No | Complete | Complete
CENY-SI | MC-55065 | PV | 6 | Yes | Inverter | 2013-12-26 17:26 | 2013-12-27 09:37 | 2013-12-27 | 2013-12-27 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-10-09 | No | Complete | Complete
CENY-SI | MC-55223 | PV | 10 | Yes | Inverter | 2013-12-28 12:30 | 2013-12-30 12:59 | 2013-12-30 | 2013-12-30 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-19 | No | Complete | Complete
CENY-SI | MC-55273 | PV | 8 | Yes | Inverter | 2013-12-30 10:14 | 2014-01-02 11:51 | 2014-01-02 | 2014-01-02 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending final documents
CENY-SI | MC-55292 | PV | 5 | Yes | Inverter | 2013-12-30 | 2013-12-31 | 2014-01-02 | 2014-01-02 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-02 | No | Complete | Complete
CENY-SI | MC-55297 | PV | 10 | Yes | Inverter | 2013-12-30 | 2013-12-31 | 2014-01-02 | 2014-01-02 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending final documents
CENY-SI | MC-55328 | PV | 9 | Yes | Inverter | 2013-12-30 | 2013-12-31 | 2014-01-02 | 2014-01-02 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-19 | No | Complete | Complete
CENY-SI | MC-55342 | PV | 7.8 | Yes | Inverter | 2013-12-30 | 2013-12-31 | 2014-01-02 | 2014-01-02 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending final documents
CENY-SI | MC-55346 | PV | 6.5 | Yes | Inverter | 2013-12-30 | 2013-12-31 | 2014-01-02 | 2014-01-02 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-19 | No | Complete | Complete
CENY-SI | MC-55348 | PV | 6 | Yes | Inverter | 2013-12-30 | 2013-12-31 | 2014-01-02 | 2014-01-02 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending final documents
CENY-SI | MC-55359 | PV | 6.6 | Yes | Inverter | 2013-12-30 | 2013-12-31 | 2014-01-02 | 2014-01-02 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | Cancelled | Cancelled
CENY-SI | MC-55397 | PV | 5 | Yes | Inverter | 2013-12-30 17:28 | 2014-01-02 14:22 | 2014-01-02 | 2014-01-02 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | Cancelled | Cancelled
CENY-SI | MC-55573 | PV | 11 | Yes | Inverter | 2014-01-02 | 2014-01-02 | 2014-01-02 | 2014-01-02 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-08 | No | Complete | Complete
CENY-SI | MC-55609 | PV | 9.6 | Yes | Inverter | 2014-01-02 | 2014-01-03 | 2014-01-06 | 2014-01-06 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending final documents
CENY-SI | MC-55617 | PV | 6.6 | Yes | Inverter | 2014-01-02 | 2014-01-03 | 2014-01-06 | 2014-01-06 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-19 | No | Complete | Complete
CENY-SI | MC-55641 | PV | 7.2 | Yes | Inverter | 2014-01-02 | 2014-01-03 | 2014-01-06 | 2014-01-06 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending final documents
CENY-SI | MC-55990 | PV | 8 | Yes | Inverter | 2014-01-06 | 2014-01-06 | 2014-01-06 | 2014-01-06 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending final documents
CENY-SI | MC-56007 | PV | 17.5 | Yes | Inverter | 2014-01-06 | 2014-01-06 | 2014-01-06 | 2014-01-06 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | Cancelled | Cancelled
CENY-SI | MC-56035 | PV | 6 | Yes | Inverter | 2014-01-06 | 2014-01-06 | 2014-01-07 | 2014-01-07 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending final documents
CENY-SI | MC-56047 | PV | 7.2 | Yes | Inverter | 2014-01-06 | 2014-01-06 | 2014-01-07 | 2014-01-07 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending final documents
CENY-SI | MC-56058 | PV | 12.2 | Yes | Inverter | 2014-01-06 | 2014-01-07 | 2014-01-07 | 2014-01-07 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending final documents
CENY-SI | MC-56062 | PV | 8.6 | Yes | Inverter | 2014-01-06 | 2014-01-07 | 2014-01-07 | 2014-01-07 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-02 | No | Complete | Complete
CENY-SI | MC-56080 | PV | 6.6 | Yes | Inverter | 2014-01-06 | 2014-01-07 | 2014-01-07 | 2014-01-07 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending final documents
CENY-SI | MC-56109 | PV | 6.6 | Yes | Inverter | 2014-01-06 | 2014-01-07 | 2014-01-07 | 2014-01-07 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-25 | No | Complete | Complete
CENY-SI | MC-56116 | PV | 9.6 | Yes | Inverter | 2014-01-06 | 2014-01-07 | 2014-01-07 | 2014-01-07 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | Cancelled | Cancelled
CENY-SI | MC-56190 | PV | 4.2 | Yes | Inverter | 2014-01-07 | 2014-01-07 | 2014-01-08 | 2014-01-08 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | Cancelled | Cancelled
CENY-SI | MC-56235 | PV | 7.5 | Yes | Inverter | 2014-01-07 | 2014-01-07 | 2014-01-08 | 2014-01-08 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | Cancelled | Cancelled
CENY-SI | MC-56237 | PV | 8 | Yes | Inverter | 2014-01-07 | 2014-01-07 | 2014-01-08 | 2014-01-08 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-19 | No | Complete | Complete
CENY-SI | MC-56246 | PV | 5 | Yes | Inverter | 2014-01-07 | 2014-01-07 | 2014-01-08 | 2014-01-08 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | Cancelled | Cancelled
CENY-SI | MC-56271 | PV | 6.6 | Yes | Inverter | 2014-01-07 | 2014-01-07 | 2014-01-08 | 2014-01-08 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-02 | No | Complete | Complete
CENY-SI | MC-56434 | PV | 3 | Yes | Inverter | 2014-01-08 | 2014-01-09 | 2014-01-09 | 2014-01-10 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | Cancelled | Cancelled
CENY-SI | MC-56437 | PV | 8 | Yes | Inverter | 2014-01-08 | 2014-01-09 | 2014-01-09 | 2014-01-10 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-07-21 | No | Complete | Complete
CENY-SI | MC-56466 | PV | 6.6 | Yes | Inverter | 2014-01-08 | 2014-01-09 | 2014-01-09 | 2014-01-10 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-07-21 | No | Complete | Complete
CENY-SI | MC-56482 | PV | 8.6 | Yes | Inverter | 2014-01-08 | 2014-01-09 | 2014-01-09 | 2014-01-10 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending final documents
CENY-SI | MC-56531 | PV | 7.6 | Yes | Inverter | 2014-01-08 | 2014-01-09 | 2014-01-09 | 2014-01-10 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-07-21 | No | Complete | Complete
CENY-SI | MC-56548 | PV | 7.8 | Yes | Inverter | 2014-01-08 | 2014-01-09 | 2014-01-09 | 2014-01-10 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending final documents
CENY-SI | MC-56632 | PV | 3.6 | Yes | Inverter | 2014-01-09 | 2014-01-09 | 2014-01-09 | 2014-01-10 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending final documents
CENY-SI | MC-56648 | PV | 3.8 | Yes | Inverter | 2014-01-09 | 2014-01-10 | 2014-01-10 | 2014-01-10 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-07-23 | No | Complete | Complete
CENY-SI | MC-56680 | PV | 12.5 | Yes | Inverter | 2014-01-09 | 2014-01-10 | 2014-01-10 | 2014-01-10 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending final documents
CENY-SI | MC-56718 | PV | 4.2 | Yes | Inverter | 2014-01-09 | 2014-01-10 | 2014-01-10 | 2014-01-10 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | Cancelled | Cancelled
CENY-SI | MC-56723 | PV | 9.8 | Yes | Inverter | 2014-01-09 | 2014-01-10 | 2014-01-10 | 2014-01-10 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-07-21 | No | Complete | Complete
CENY-SI | MC-56725 | PV | 7.5 | Yes | Inverter | 2014-01-09 | 2014-01-10 | 2014-01-10 | 2014-01-10 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending final documents
CENY-SI | MC-56757 | PV | 5 | Yes | Inverter | 2014-01-09 | 2014-01-10 | 2014-01-10 | 2014-01-10 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending final documents
CENY-SI | MC-56842 | PV | 6.5 | Yes | Inverter | 2014-01-10 | 2014-01-10 | 2014-01-10 | 2014-01-10 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-05 | No | Complete | Complete
CENY-SI | MC-56849 | PV | 7.2 | Yes | Inverter | 2014-01-10 | 2014-01-10 | 2014-01-10 | 2014-01-10 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-19 | No | Complete | Complete
CENY-SI | MC-57212 | PV | 9.6 | Yes | Inverter | 2014-01-13 | 2014-01-14 | 2014-01-15 | 2014-01-15 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | Cancelled | Cancelled
CENY-SI | MC-57218 | PV | 9.8 | Yes | Inverter | 2014-01-13 | 2014-01-14 | 2014-01-15 | 2014-01-15 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-01 | No | Complete | Complete
CENY-SI | MC-57221 | PV | 15 | Yes | Inverter | 2014-01-13 | 2014-01-14 | 2014-01-15 | 2014-01-15 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending final documents
CENY-SI | MC-57226 | PV | 3.6 | Yes | Inverter | 2014-01-13 | 2014-01-14 | 2014-01-15 | 2014-01-15 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | In Progress
CENY-SI | MC-57227 | PV | 6 | Yes | Inverter | 2014-01-13 | 2014-01-14 | 2014-01-15 | 2014-01-15 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-24 | No | Complete | Complete
CENY-SI | MC-58141 | PV | 6 | Yes | Inverter | 2014-01-17 | 2014-01-21 | 2014-01-21 | 2014-01-21 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-10-07 | No | Complete | Complete
CENY-SI | MC-58179 | PV | 6 | Yes | Inverter | 2014-01-17 | 2014-01-21 | 2014-01-21 | 2014-01-21 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | Cancelled | Cancelled
CENY-SI | MC-58181 | PV | 5 | Yes | Inverter | 2014-01-17 | 2014-01-21 | 2014-01-21 | 2014-01-21 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-02 | No | Complete | Complete
CENY-SI | MC-58190 | PV | 12 | Yes | Inverter | 2014-01-17 | 2014-01-21 | 2014-01-21 | 2014-01-21 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | Cancelled | Cancelled
CENY-SI | MC-58326 | PV | 3.8 | Yes | Inverter | 2014-01-20 | 2014-01-21 | 2014-01-21 | 2014-01-21 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | Cancelled | Cancelled
CENY-SI | MC-58368 | PV | 4.3 | Yes | Inverter | 2014-01-20 | 2014-01-21 | 2014-01-21 | 2014-01-21 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-10-03 | No | Complete | Complete
CENY-SI | MC-58493 | PV | 5.1 | Yes | Inverter | 2014-01-20 | 2014-01-21 | 2014-01-21 | 2014-01-21 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending final documents
CENY-SI | MC-58495 | PV | 5.1 | Yes | Inverter | 2014-01-20 | 2014-01-21 | 2014-01-21 | 2014-01-21 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-09 | No | Complete | Complete
CENY-SI | MC-58619 | PV | 5.1 | Yes | Inverter | 2014-01-21 | 2014-01-23 | 2014-01-23 | 2014-01-23 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | Cancelled | Cancelled
CENY-SI | MC-58620 | PV | 7.7 | Yes | Inverter | 2014-01-21 | 2014-01-23 | 2014-01-23 | 2014-01-23 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-19 | No | Complete | Complete
CENY-SI | MC-58622 | PV | 5.1 | Yes | Inverter | 2014-01-21 | 2014-01-23 | 2014-01-23 | 2014-01-23 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-10-03 | No | Complete | Complete
CENY-SI | MC-58634 | PV | 7.4 | Yes | Inverter | 2014-01-21 | 2014-01-23 | 2014-01-23 | 2014-01-23 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-27 | No | Complete | Complete
CENY-SI | MC-58639 | PV | 4.6 | Yes | Inverter | 2014-01-21 | 2014-01-23 | 2014-01-23 | 2014-01-23 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | Cancelled | Cancelled
CENY-SI | MC-58888 | PV | 10 | Yes | Inverter | 2014-01-22 | 2014-01-23 | 2014-01-23 | 2014-01-23 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-11 | No | Complete | Complete
CENY-SI | MC-58896 | PV | 7.4 | Yes | Inverter | 2014-01-22 | 2014-01-23 | 2014-01-23 | 2014-01-23 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-19 | No | Complete | Complete
CENY-SI | MC-58899 | PV | 10.5 | Yes | Inverter | 2014-01-22 | 2014-01-23 | 2014-01-23 | 2014-01-23 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending final documents
CENY-SI | MC-59438 | PV | 7.5 | Yes | Inverter | 2014-01-27 | 2014-01-09 | 2014-01-09 | 2014-01-09 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-10-09 | No | Complete | Complete
CENY-SI | MC-59453 | PV | 3.6 | Yes | Inverter | 2014-01-27 | 2014-01-09 | 2014-01-09 | 2014-01-09 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-24 | No | Complete | Complete
CENY-SI | MC-59461 | PV | 6 | Yes | Inverter | 2014-01-27 | 2014-01-09 | 2014-01-09 | 2014-01-09 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-10-09 | No | Complete | Complete
CENY-SI | MC-59474 | PV | 4.2 | Yes | Inverter | 2014-01-27 | 2014-01-09 | 2014-01-09 | 2014-01-09 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-02 | No | Complete | Complete
CENY-SI | MC-59478 | PV | 12 | Yes | Inverter | 2014-01-27 | 2014-01-09 | 2014-01-09 | 2014-01-09 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending final documents
CENY-SI | MC-59693 | PV | 6.6 | Yes | Inverter | 2014-01-28 | 2014-01-09 | 2014-01-09 | 2014-01-09 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending final documents
CENY-SI | MC-59706 | PV | 10 | Yes | Inverter | 2014-01-28 | 2014-01-09 | 2014-01-09 | 2014-01-09 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending final documents
CENY-SI | MC-59734 | PV | 9 | Yes | Inverter | 2014-01-28 | 2014-01-09 | 2014-01-09 | 2014-01-09 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | Cancelled | Cancelled
CENY-SI | MC-59766 | PV | 9.6 | Yes | Inverter | 2014-01-28 | 2014-01-09 | 2014-01-09 | 2014-01-09 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending final documents
CENY-SI | MC-59775 | PV | 7 | Yes | Inverter | 2014-01-28 | 2014-01-09 | 2014-01-09 | 2014-01-09 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-11 | No | Complete | Complete
CENY-SI | MC-59866 | PV | 7.8 | Yes | Inverter | 2014-01-29 | 2014-01-29 | 2014-01-29 | 2014-01-29 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | Cancelled | Cancelled
CENY-SI | MC-59870 | PV | 3.8 | Yes | Inverter | 2014-01-29 | 2014-02-05 | 2014-01-31 07:47 | 2014-01-31 07:48 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-30 | No | Complete | Complete
CENY-SI | MC-60116 | PV | 3.3 | Yes | Inverter | 2014-01-30 | 2014-01-31 | 2014-01-31 | 2014-01-31 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-10-03 | No | Complete | Complete
CENY-SI | MC-60288 | PV | 5.4 | Yes | Inverter | 2014-01-31 | 2014-01-31 | 2014-01-31 | 2014-01-31 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-07 | No | Complete | Complete
CENY-SI | MC-60752 | PV | 5.9 | Yes | Inverter | 2014-02-04 | 2014-02-06 | 2014-02-10 | 2014-02-10 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-28 | No | Complete | Complete
CENY-SI | MC-60931 | PV | 6 | Yes | Inverter | 2014-02-05 | 2014-02-06 | 2014-02-10 | 2014-02-10 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-10-09 | No | Complete | Complete
CENY-SI | MC-62176 | PV | 12.6 | Yes | Inverter | 2014-02-12 | 2014-02-13 | 2014-02-13 | 2014-02-13 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending final documents
CENY-SI | MC-62202 | PV | 8.5 | Yes | Inverter | 2014-02-12 | 2014-02-13 | 2014-03-19 14:09 | 2014-03-19 14:11 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending final documents
CENY-SI | MC-62205 | PV | 9.6 | Yes | Inverter | 2014-02-12 | 2014-02-13 | 2014-03-19 13:45 | 2014-03-19 13:47 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending final documents
CENY-SI | MC-62460 | PV | 3 | Yes | Inverter | 2014-02-14 | 2014-02-14 | 2014-03-19 | 2014-03-19 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-28 | No | Complete | Complete
CENY-SI | MC-62475 | PV | 7.8 | Yes | Inverter | 2014-02-14 | 2014-02-18 | 2014-02-21 | 2014-02-21 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | Cancelled | Cancelled
CENY-SI | MC-62659 | PV | 7.2 | Yes | Inverter | 2014-02-17 | 2014-02-18 | 2014-02-21 | 2014-02-21 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-11 | No | Complete | Complete
CENY-SI | MC-62705 | PV | 6 | Yes | Inverter | 2014-02-17 | 2014-02-18 | 2014-02-21 | 2014-02-21 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | Cancelled | Cancelled
CENY-SI | MC-62739 | PV | 3 | Yes | Inverter | 2014-02-17 | 2014-02-18 | 2014-03-24 15:05 | 2014-03-24 15:09 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending final documents
CENY-SI | MC-62745 | PV | 6.8 | Yes | Inverter | 2014-02-17 | 2014-02-18 | 2014-03-21 12:41 | 2014-03-21 12:45 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | Cancelled | Cancelled
CENY-SI | MC-63400 | PV | 9 | Yes | Inverter | 2014-02-21 | 2014-02-24 | 2014-03-19 13:24 | 2014-03-19 13:28 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending final documents
CENY-SI | MC-63674 | PV | 10 | Yes | Inverter | 2014-02-24 | 2014-02-24 | 2014-03-03 | 2014-03-03 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending final documents
CENY-SI | MC-63982 | PV | 7 | Yes | Inverter | 2014-02-25 | 2014-02-26 | 2014-02-26 | 2014-02-26 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending final documents
CENY-SI | MC-64119 | PV | 15.2 | Yes | Inverter | 2014-02-26 | 2014-02-27 | 2014-03-03 | 2014-03-03 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | Cancelled | Cancelled
CENY-SI | MC-64193 | PV | 3.2 | Yes | Inverter | 2014-02-26 | 2014-02-27 | 2014-03-03 | 2014-03-03 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-05 | No | Complete | Complete
CENY-SI | MC-64385 | PV | 7.6 | Yes | Inverter | 2014-02-27 | 2014-02-27 | 2014-04-15 08:25 | 2014-04-15 08:27 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending final documents
CENY-SI | MC-64827 | PV | 4 | Yes | Inverter | 2014-03-03 | 2014-03-04 | 2014-03-04 | 2014-03-04 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | Cancelled | Cancelled
CENY-SI | MC-64965 | PV | 6.6 | Yes | Inverter | 2014-03-04 | 2014-03-04 | 2014-03-04 | 2014-03-04 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-07-21 | No | Complete | Complete
CENY-SI | MC-64970 | PV | 12 | Yes | Inverter | 2014-03-04 | 2014-03-04 | 2014-03-04 | 2014-03-04 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending final documents
CENY-SI | MC-65370 | PV | 13.8 | Yes | Inverter | 2014-03-06 | 2014-03-06 | 2014-03-06 | 2014-03-06 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-30 | No | Complete | Complete
CENY-SI | MC-65648 | PV | 6 | Yes | Inverter | 2014-03-07 | 2014-03-10 | 2014-03-12 | 2014-03-12 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending final documents
CENY-SI | MC-65708 | PV | 4.6 | Yes | Inverter | 2014-03-09 | 2014-03-10 | 2014-03-10 | 2014-03-12 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-11 | No | Complete | Complete
CENY-SI | MC-65774 | PV | 4.4 | Yes | Inverter | 2014-03-10 | 2014-03-10 | 2014-03-10 | 2014-03-12 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | Cancelled | Cancelled
CENY-SI | MC-65786 | PV | 4.4 | Yes | Inverter | 2014-03-10 | 2014-03-10 | 2014-03-12 | 2014-03-12 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | Cancelled | Cancelled
CENY-SI | MC-65803 | PV | 10.2 | Yes | Inverter | 2014-03-10 | 2014-03-10 | 2014-03-12 | 2014-03-12 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | Cancelled | Cancelled
CENY-SI | MC-65804 | PV | 3.6 | Yes | Inverter | 2014-03-10 | 2014-03-10 | 2014-03-12 | 2014-03-12 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending final documents
CENY-SI | MC-65810 | PV | 6 | Yes | Inverter | 2014-03-10 | 2014-03-10 | 2014-03-12 | 2014-03-12 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending final documents
CENY-SI | MC-66289 | PV | 6 | Yes | Inverter | 2014-03-12 | 2014-03-13 | 2014-03-19 | 2014-03-19 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-28 | No | Complete | Complete
CENY-SI | MC-66317 | PV | 4.2 | Yes | Inverter | 2014-03-12 | 2014-03-13 | 2014-03-19 | 2014-03-19 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | Cancelled | Cancelled
CENY-SI | MC-66348 | PV | 4.2 | Yes | Inverter | 2014-03-12 | 2014-03-13 | 2014-03-19 | 2014-03-19 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-24 | No | Complete | Complete
CENY-SI | MC-66552 | PV | 15.6 | Yes | Inverter | 2014-03-13 | 2014-03-14 | 2014-03-19 | 2014-03-19 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-19 | No | Complete | Complete
CENY-SI | MC-66679 | PV | 10 | Yes | Inverter | 2014-03-14 | 2014-03-14 | 2014-03-19 | 2014-03-19 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-05 | No | Complete | Complete
CENY-SI | MC-66702 | PV | 3.2 | Yes | Inverter | 2014-03-14 | 2014-03-17 | 2014-03-19 | 2014-03-19 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | Cancelled | Cancelled
CENY-SI | MC-66723 | PV | 13 | Yes | Inverter | 2014-03-14 | 2014-03-17 | 2014-03-19 | 2014-03-19 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending final documents
CENY-SI | MC-67317 | PV | 11 | Yes | Inverter | 2014-03-18 | 2014-03-19 | 2014-03-19 | 2014-03-19 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending final documents
CENY-SI | MC-67320 | PV | 7.2 | Yes | Inverter | 2014-03-18 | 2014-03-19 | 2014-03-19 | 2014-03-19 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending final documents
CENY-SI | MC-67332 | PV | 8.4 | Yes | Inverter | 2014-03-18 | 2014-03-19 | 2014-03-19 | 2014-03-19 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-05 | No | Complete | Complete
CENY-SI | MC-67607 | PV | 14 | Yes | Inverter | 2014-03-19 | 2014-03-20 | 2014-03-26 | 2014-03-26 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending final documents
CENY-SI | MC-67846 | PV | 3.4 | Yes | Inverter | 2014-03-20 | 2014-03-21 | 2014-03-26 | 2014-03-26 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | Cancelled | Cancelled
CENY-SI | MC-68229 | PV | 6 | Yes | Inverter | 2014-03-23 | 2014-03-24 | 2014-03-26 | 2014-03-26 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-24 | No | Complete | Complete
CENY-SI | MC-68414 | PV | 8 | Yes | Inverter | 2014-03-24 | 2014-03-25 | 2014-03-26 | 2014-03-26 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending final documents
CENY-SI | MC-68495 | PV | 5 | Yes | Inverter | 2014-03-24 | 2014-03-28 | 2014-04-15 07:49 | 2014-04-15 07:55 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending final documents
CENY-SI | MC-68637 | PV | 8 | Yes | Inverter | 2014-03-25 | 2014-03-25 | 2014-03-28 | 2014-03-28 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending final documents
CENY-SI | MC-68641 | PV | 6.6 | Yes | Inverter | 2014-03-25 | 2014-03-25 | 2014-03-28 | 2014-03-28 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-07 | No | Complete | Complete
CENY-SI | MC-68802 | PV | 5 | Yes | Inverter | 2014-03-25 | 2014-03-25 | 2014-03-28 | 2014-03-28 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-08 | No | Complete | Complete
CENY-SI | MC-68946 | PV | 3.2 | Yes | Inverter | 2014-03-26 | 2014-03-26 | 2014-03-28 | 2014-03-28 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-22 | No | Complete | Complete
CENY-SI | MC-69456 | PV | 3 | Yes | Inverter | 2014-03-28 | 2014-03-31 | 2014-03-31 | 2014-03-31 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-07-21 | No | Complete | Complete
CENY-SI | MC-69684 | PV | 6 | Yes | Inverter | 2014-03-31 | 2014-04-01 | 2014-04-02 | 2014-04-02 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-16 | No | Complete | Complete
CENY-SI | MC-69688 | PV | 6 | Yes | Inverter | 2014-03-31 | 2014-04-01 | 2014-04-02 | 2014-04-02 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-02 | No | Complete | Complete
CENY-SI | MC-69705 | PV | 6 | Yes | Inverter | 2014-03-31 | 2014-04-01 | 2014-04-02 | 2014-04-02 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending final documents
CENY-SI | MC-69708 | PV | 5 | Yes | Inverter | 2014-03-31 | 2014-04-01 | 2014-04-02 | 2014-04-02 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending final documents
CENY-SI | MC-69741 | PV | 4 | Yes | Inverter | 2014-03-31 | 2014-04-01 | 2014-04-02 | 2014-04-02 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending final documents
CENY-SI | MC-69744 | PV | 3.4 | Yes | Inverter | 2014-03-31 | 2014-04-01 | 2014-04-02 | 2014-04-02 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending final documents
CENY-SI | MC-70136 | PV | 6.6 | Yes | Inverter | 2014-04-02 | 2014-04-21 15:13 | 2014-04-21 15:16 | 2014-04-21 15:17 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending final documents
CENY-SI | MC-70152 | PV | 7.2 | Yes | Inverter | 2014-04-02 | 2014-04-21 14:44 | 2014-04-21 14:46 | 2014-04-21 14:48 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | Cancelled | Cancelled
CENY-SI | MC-70157 | PV | 10 | Yes | Inverter | 2014-04-02 | 2014-04-21 14:22 | 2014-04-21 14:24 | 2014-04-21 14:26 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-08 | No | Complete | Complete
CENY-SI | MC-70227 | PV | 6 | Yes | Inverter | 2014-04-02 | 2014-04-21 14:03 | 2014-04-21 14:06 | 2014-04-21 14:10 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending final documents
CENY-SI | MC-70238 | PV | 8 | Yes | Inverter | 2014-04-02 | 2014-04-21 12:49 | 2014-04-21 12:52 | 2014-04-21 12:53 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | Cancelled | Cancelled
CENY-SI | MC-70244 | PV | 8.6 | Yes | Inverter | 2014-04-02 | 2014-04-21 09:19 | 2014-04-21 09:22 | 2014-04-21 09:23 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | Cancelled | Cancelled
CENY-SI | MC-70285 | PV | 5.2 | Yes | Inverter | 2014-04-02 | 2014-04-22 07:38 | 2014-04-22 07:40 | 2014-04-22 07:41 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending final documents
CENY-SI | MC-70456 | PV | 12.8 | Yes | Inverter | 2014-04-03 | 2014-04-18 15:14 | 2014-04-18 15:17 | 2014-04-18 15:18 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending final documents
CENY-SI | MC-70463 | PV | 14.2 | Yes | Inverter | 2014-04-03 | 2014-04-18 14:45 | 2014-04-18 14:47 | 2014-04-18 14:48 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-08 | No | Complete | Complete
CENY-SI | MC-70467 | PV | 7.2 | Yes | Inverter | 2014-04-03 | 2014-04-18 14:53 | 2014-04-18 14:55 | 2014-04-18 14:56 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | Cancelled | Cancelled
CENY-SI | MC-70473 | PV | 13.6 | Yes | Inverter | 2014-04-03 | 2014-04-18 15:06 | 2014-04-18 15:08 | 2014-04-18 15:09 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending final documents
CENY-SI | MC-70489 | PV | 5 | Yes | Inverter | 2014-04-03 | 2014-04-21 09:08 | 2014-04-21 09:11 | 2014-04-21 09:14 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | Cancelled | Cancelled
CENY-SI | MC-70695 | PV | 13.6 | Yes | Inverter | 2014-04-04 | 2014-04-18 13:54 | 2014-04-18 13:58 | 2014-04-18 13:59 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-07-18 | No | Complete | Complete
CENY-SI | MC-70698 | PV | 5 | Yes | Inverter | 2014-04-04 | 2014-04-18 13:17 | 2014-04-18 13:42 | 2014-04-18 13:43 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-19 | No | Complete | Complete
CENY-SI | MC-70709 | PV | 4.2 | Yes | Inverter | 2014-04-04 | 2014-04-18 14:04 | 2014-04-18 14:06 | 2014-04-18 14:09 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending final documents
CENY-SI | MC-70742 | PV | 12.2 | Yes | Inverter | 2014-04-04 | 2014-04-28 15:16 | 2014-04-30 07:26 | 2014-04-30 07:31 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-16 | No | Complete | Complete
CENY-SI | MC-70789 | PV | 3.2 | Yes | Inverter | 2014-04-07 | 2014-04-18 14:16 | 2014-04-18 14:26 | 2014-04-18 14:27 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-24 | No | Complete | Complete
CENY-SI | MC-71012 | PV | 17 | Yes | Inverter | 2014-04-07 | 2014-04-18 11:47 | 2014-04-18 11:50 | 2014-04-18 11:51 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-04 | No | Complete | Complete
CENY-SI | MC-71018 | PV | 11.6 | Yes | Inverter | 2014-04-07 | 2014-04-18 11:37 | 2014-04-18 11:39 | 2014-04-18 11:42 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending final documents
CENY-SI | MC-71023 | PV | 6 | Yes | Inverter | 2014-04-07 | 2014-04-18 10:49 | 2014-04-18 10:54 | 2014-04-18 10:55 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | Cancelled | Cancelled
CENY-SI | MC-71147 | PV | 4.6 | Yes | Inverter | 2014-04-08 | 2014-04-09 08:55 | 2014-04-14 11:45 | 2014-04-14 11:54 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending final documents
CENY-SI | MC-71153 | PV | 4.8 | Yes | Inverter | 2014-04-08 | 2014-04-09 09:19 | 2014-04-14 12:03 | 2014-04-14 12:08 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-24 | No | Complete | Complete
CENY-SI | MC-71182 | PV | 8.6 | Yes | Inverter | 2014-04-08 | 2014-04-09 09:39 | 2014-04-09 09:45 | 2014-04-09 09:47 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-08 | No | Complete | Complete
CENY-SI | MC-71200 | PV | 21.4 | Yes | Inverter | 2014-04-08 | 2014-04-16 07:26 | 2014-04-16 07:35 | 2014-04-16 07:41 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending final documents
CENY-SI | MC-71211 | PV | 13.2 | Yes | Inverter | 2014-04-08 | 2014-04-09 08:36 | 2014-04-09 08:43 | 2014-04-09 08:46 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending final documents
CENY-SI | MC-71218 | PV | 5 | Yes | Inverter | 2014-04-08 | 2014-04-14 13:33 | 2014-04-14 13:41 | 2014-04-14 13:45 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending final documents
CENY-SI | MC-71418 | PV | 2.8 | Yes | Inverter | 2014-04-09 | 2014-04-09 12:15 | 2014-04-14 11:11 | 2014-04-14 11:33 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending final documents
CENY-SI | MC-71450 | PV | 6.5 | Yes | Inverter | 2014-04-09 | 2014-04-09 12:29 | 2014-04-09 12:39 | 2014-04-09 12:40 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-07-21 | No | Complete | Complete
CENY-SI | MC-71697 | PV | 6 | Yes | Inverter | 2014-04-10 | 2014-04-15 09:11 | 2014-04-15 09:15 | 2014-04-15 09:18 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-09 | No | Complete | Complete
CENY-SI | MC-71706 | PV | 7.5 | Yes | Inverter | 2014-04-10 | 2014-04-15 09:39 | 2014-04-15 09:51 | 2014-04-15 10:12 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-22 | No | Complete | Complete
CENY-SI | MC-71710 | PV | 5.4 | Yes | Inverter | 2014-04-10 | 2014-04-14 14:02 | 2014-04-14 14:08 | 2014-04-14 14:12 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-24 | No | Complete | Complete
CENY-SI | MC-71720 | PV | 18 | Yes | Inverter | 2014-04-10 | 2014-04-15 08:54 | 2014-04-15 09:05 | 2014-04-15 09:08 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending final documents
CENY-SI | MC-72258 | PV | 3.6 | Yes | Inverter | 2014-04-14 | 2014-04-17 14:01 | 2014-04-17 14:09 | 2014-04-17 14:14 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-21 | No | Complete | Complete
CENY-SI | MC-72265 | PV | 12 | Yes | Inverter | 2014-04-14 | 2014-04-16 15:03 | 2014-04-17 08:43 | 2014-04-17 08:45 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-07-21 | No | Complete | Complete
CENY-SI | MC-72274 | PV | 9 | Yes | Inverter | 2014-04-14 | 2014-04-17 14:27 | 2014-04-17 14:32 | 2014-04-17 14:40 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending final documents
CENY-SI | MC-72280 | PV | 9 | Yes | Inverter | 2014-04-14 | 2014-04-17 10:45 | 2014-04-17 11:02 | 2014-04-17 11:06 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-30 | No | Complete | Complete
CENY-SI | MC-72293 | PV | 3 | Yes | Inverter | 2014-04-14 | 2014-04-17 09:43 | 2014-04-17 10:20 | 2014-04-17 10:23 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-21 | No | Complete | Complete
CENY-SI | MC-72295 | PV | 14.3 | Yes | Inverter | 2014-04-14 | 2014-04-17 09:08 | 2014-04-17 09:23 | 2014-04-17 09:31 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-10-09 | No | Complete | Complete
CENY-SI | MC-72299 | PV | 3.6 | Yes | Inverter | 2014-04-14 | 2014-04-17 13:36 | 2014-04-17 13:43 | 2014-04-17 13:46 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-09 | No | Complete | Complete
CENY-SI | MC-72302 | PV | 7.5 | Yes | Inverter | 2014-04-14 | 2014-04-17 13:08 | 2014-04-17 13:19 | 2014-04-17 13:22 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | Cancelled | Cancelled
CENY-SI | MC-72308 | PV | 3 | Yes | Inverter | 2014-04-14 | 2014-04-17 11:26 | 2014-04-17 11:39 | 2014-04-17 12:49 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-16 | No | Complete | Complete
CENY-SI | MC-72572 | PV | 5 | Yes | Inverter | 2014-04-15 | 2014-04-17 07:40 | 2014-04-17 07:48 | 2014-04-17 07:55 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending customer build
CENY-SI | MC-72575 | PV | 5 | Yes | Inverter | 2014-04-15 | 2014-04-17 08:18 | 2014-04-17 08:31 | 2014-04-17 08:37 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending final documents
CENY-SI | MC-72579 | PV | 6.6 | Yes | Inverter | 2014-04-15 | 2014-04-17 07:14 | 2014-04-17 07:22 | 2014-04-17 07:24 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending final documents
CENY-SI | MC-72846 | PV | 4.2 | Yes | Inverter | 2014-04-16 | 2014-04-21 12:39 | 2014-04-21 12:41 | 2014-04-21 12:42 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-09 | No | Complete | Complete
CENY-SI | MC-72858 | PV | 4.2 | Yes | Inverter | 2014-04-16 | 2014-04-21 12:27 | 2014-04-21 12:29 | 2014-04-21 12:30 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-07-23 | No | Complete | Complete
CENY-SI | MC-72947 | PV | 6 | Yes | Inverter | 2014-04-17 | 2014-04-21 11:47 | 2014-04-21 11:49 | 2014-04-21 11:50 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-09 | No | Complete | Complete
CENY-SI | MC-72955 | PV | 11 | Yes | Inverter | 2014-04-17 | 2014-04-21 11:23 | 2014-04-21 11:25 | 2014-04-21 11:27 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-07-30 | No | Complete | Complete
CENY-SI | MC-72958 | PV | 7.8 | Yes | Inverter | 2014-04-17 | 2014-04-21 11:35 | 2014-04-21 11:39 | 2014-04-21 11:41 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-07-23 | No | Complete | Complete
CENY-SI | MC-72968 | PV | 6 | Yes | Inverter | 2014-04-17 | 2014-04-21 11:11 | 2014-04-21 11:14 | 2014-04-21 11:15 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending final documents
CENY-SI | MC-72973 | PV | 7.2 | Yes | Inverter | 2014-04-17 | 2014-04-21 11:01 | 2014-04-21 11:04 | 2014-04-21 11:05 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-19 | No | Complete | Complete
CENY-SI | MC-72979 | PV | 4.2 | Yes | Inverter | 2014-04-17 | 2014-04-21 10:27 | 2014-04-21 10:29 | 2014-04-21 10:46 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-07-21 | No | Complete | Complete
CENY-SI | MC-72983 | PV | 4.2 | Yes | Inverter | 2014-04-17 | 2014-04-21 10:11 | 2014-04-21 10:17 | 2014-04-21 10:20 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-19 | No | Complete | Complete
CENY-SI | MC-72998 | PV | 7.8 | Yes | Inverter | 2014-04-17 | 2014-04-30 07:50 | 2014-04-30 08:02 | 2014-04-30 08:00 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-21 | No | Complete | Complete
CENY-SI | MC-73386 | PV | 13 | Yes | Inverter | 2014-04-21 | 2014-04-22 10:07 | 2014-04-22 10:10 | 2014-04-22 10:12 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-16 | No | Complete | Complete
CENY-SI | MC-73424 | PV | 5 | Yes | Inverter | 2014-04-21 | 2014-04-22 09:02 | 2014-04-22 09:03 | 2014-04-22 09:06 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-16 | No | Complete | Complete
CENY-SI | MC-73524 | PV | 7.2 | Yes | Inverter | 2014-04-21 | 2014-05-02 10:54 | 2014-05-02 11:12 | 2014-05-02 11:17 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-07-18 | No | Complete | Complete
CENY-SI | MC-73527 | PV | 6.8 | Yes | Inverter | 2014-04-21 | 2014-04-28 11:21 | 2014-04-28 11:31 | 2014-04-28 11:35 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-16 | No | Complete | Complete
CENY-SI | MC-73663 | PV | 17.6 | Yes | Inverter | 2014-04-22 | 2014-04-23 11:36 | 2014-04-23 11:39 | 2014-04-23 11:40 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-08 | No | Complete | Complete
CENY-SI | MC-73889 | PV | 44.4 | Yes | Inverter | 2014-04-23 | 2014-04-25 11:06 | 2014-05-07 07:22 | 2014-05-21 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending customer build
CENY-SI | MC-73996 | PV | 5 | Yes | Inverter | 2014-04-23 | 2014-04-25 12:31 | 2014-04-25 12:34 | 2014-04-25 12:40 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | Cancelled | Cancelled
CENY-SI | MC-74246 | PV | 5 | Yes | Inverter | 2014-04-24 | 2014-04-25 12:51 | 2014-04-25 12:54 | 2014-04-25 12:56 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending final documents
CENY-SI | MC-74363 | PV | 7.8 | Yes | Inverter | 2014-04-25 | 2014-04-28 11:20 | 2014-04-28 11:23 | 2014-04-28 11:25 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending final documents
CENY-SI | MC-74376 | PV | 9 | Yes | Inverter | 2014-04-25 | 2014-04-28 10:13 | 2014-04-28 10:18 | 2014-04-28 10:20 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | Cancelled | Cancelled
CENY-SI | MC-74383 | PV | 6.5 | Yes | Inverter | 2014-04-25 | 2014-04-28 10:32 | 2014-04-28 10:35 | 2014-04-28 10:37 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-09 | No | Complete | Complete
CENY-SI | MC-74410 | PV | 8.6 | Yes | Inverter | 2014-04-25 | 2014-04-28 10:48 | 2014-04-28 10:50 | 2014-04-28 10:53 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-21 | No | Complete | Complete
CENY-SI | MC-74422 | PV | 8.6 | Yes | Inverter | 2014-04-25 | 2014-04-28 11:04 | 2014-04-28 11:07 | 2014-04-28 11:08 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-19 | No | Complete | Complete
CENY-SI | MC-74814 | PV | 5 | Yes | Inverter | 2014-04-28 | 2014-05-02 09:33 | 2014-05-02 09:40 | 2014-05-02 09:45 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending final documents
CENY-SI | MC-75019 | PV | 6 | Yes | Inverter | 2014-04-29 | 2014-05-21 10:09 | 2014-05-21 10:16 | 2014-05-21 10:20 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending final documents
CENY-SI | MC-75240 | PV | 11 | Yes | Inverter | 2014-04-30 | 2014-05-01 11:00 | 2014-05-01 11:04 | 2014-05-01 11:07 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-08 | No | Complete | Complete
CENY-SI | MC-75264 | PV | 9 | Yes | Inverter | 2014-04-30 | 2014-05-01 11:16 | 2014-05-01 11:19 | 2014-05-01 11:20 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-21 | No | Complete | Complete
CENY-SI | MC-75381 | PV | 6 | Yes | Inverter | 2014-04-30 | 2014-05-01 11:50 | 2014-05-01 11:51 | 2014-05-01 11:54 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-07-18 | No | Complete | Complete
CENY-SI | MC-75387 | PV | 3 | Yes | Inverter | 2014-04-30 | 2014-05-01 12:04 | 2014-05-02 09:16 | 2014-05-02 09:22 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-07-18 | No | Complete | Complete
CENY-SI | MC-75700 | PV | 2.4 | Yes | Inverter | 2014-05-02 | 2014-05-05 11:03 | 2014-05-05 11:06 | 2014-05-05 11:08 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-16 | No | Complete | Complete
CENY-SI | MC-75773 | PV | 8.6 | Yes | Inverter | 2014-05-02 | 2014-05-05 10:21 | 2014-05-05 10:23 | 2014-05-05 10:26 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending customer build
CENY-SI | MC-75775 | PV | 8.4 | Yes | Inverter | 2014-05-02 | 2014-05-05 10:06 | 2014-05-05 10:09 | 2014-05-05 10:11 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending customer build
CENY-SI | MC-75789 | PV | 3 | Yes | Inverter | 2014-05-02 | 2014-05-05 10:34 | 2014-05-05 10:36 | 2014-05-05 10:41 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | Cancelled | Cancelled
CENY-SI | MC-75795 | PV | 3 | Yes | Inverter | 2014-05-02 | 2014-05-05 10:49 | 2014-05-05 10:51 | 2014-05-05 10:52 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-02 | No | Complete | Complete
CENY-SI | MC-75821 | PV | 7.2 | Yes | Inverter | 2014-05-02 | 2014-05-05 10:59 | 2014-05-05 11:02 | 2014-05-05 11:03 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-16 | No | Complete | Complete
CENY-SI | MC-75825 | PV | 4.2 | Yes | Inverter | 2014-05-02 | 2014-05-05 13:50 | 2014-05-05 13:54 | 2014-05-05 14:00 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | Cancelled | Cancelled
CENY-SI | MC-75828 | PV | 10 | Yes | Inverter | 2014-05-02 | 2014-05-05 13:21 | 2014-05-05 13:30 | 2014-05-09 09:06 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-22 | No | Complete | Complete
CENY-SI | MC-76316 | PV | 6.8 | Yes | Inverter | 2014-05-06 | 2014-05-09 08:21 | 2014-05-09 08:38 | 2014-05-09 08:44 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-29 | No | Complete | Complete
CENY-SI | MC-76319 | PV | 3.8 | Yes | Inverter | 2014-05-06 | 2014-05-07 14:06 | 2014-05-07 14:15 | 2014-05-07 14:17 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-26 | No | Complete | Complete
CENY-SI | MC-76327 | PV | 9.2 | Yes | Inverter | 2014-05-06 | 2014-05-07 14:28 | 2014-05-07 14:37 | 2014-05-07 14:52 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-02 | No | Complete | Complete
CENY-SI | MC-76423 | PV | 2.8 | Yes | Inverter | 2014-05-06 | 2014-05-07 15:07 | 2014-05-07 15:11 | 2014-05-07 15:14 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-16 | No | Complete | Complete
CENY-SI | MC-76425 | PV | 7.2 | Yes | Inverter | 2014-05-06 | 2014-05-09 08:59 | 2014-05-09 09:02 | 2014-05-09 09:04 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending customer build
CENY-SI | MC-76435 | PV | 3.2 | Yes | Inverter | 2014-05-06 | 2014-05-09 07:42 | 2014-05-09 07:51 | 2014-05-09 08:01 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-05 | No | Complete | Complete
CENY-SI | MC-76439 | PV | 3.2 | Yes | Inverter | 2014-05-06 | 2014-05-07 13:48 | 2014-05-07 13:52 | 2014-05-07 13:55 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending customer build
CENY-SI | MC-76540 | PV | 4 | Yes | Inverter | 2014-05-07 | 2014-05-08 15:17 | 2014-05-08 15:22 | 2014-05-08 15:23 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending customer build
CENY-SI | MC-76773 | PV | 12 | Yes | Inverter | 2014-05-08 | 2014-05-09 12:41 | 2014-05-09 12:46 | 2014-05-09 12:51 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-21 | No | Complete | Complete
CENY-SI | MC-76885 | PV | 7.6 | Yes | Inverter | 2014-05-08 | 2014-05-09 12:22 | 2014-05-09 12:28 | 2014-05-09 12:31 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending customer build
CENY-SI | MC-770 | PV | 1040 | Yes | Inverter | 2013-04-22 | 2013-04-29 | 2013-08-30 | 2013-09-13 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | Cancelled | Cancelled
CENY-SI | MC-77071 | PV | 6 | Yes | Inverter | 2014-05-09 | 2014-05-12 12:44 | 2014-05-12 12:50 | 2014-05-12 13:12 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-22 | No | Complete | Complete
CENY-SI | MC-77107 | PV | 10 | Yes | Inverter | 2014-05-09 | 2014-05-12 12:14 | 2014-05-12 12:23 | 2014-05-12 12:28 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-30 | No | Complete | Complete
CENY-SI | MC-77368 | PV | 10.2 | Yes | Inverter | 2014-05-12 | 2014-05-14 08:43 | 2014-05-14 08:47 | 2014-05-14 08:53 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-09 | No | Complete | Complete
CENY-SI | MC-77453 | PV | 3 | Yes | Inverter | 2014-05-12 | 2014-05-13 12:12 | 2014-05-13 12:17 | 2014-05-13 12:18 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | Cancelled | Cancelled
CENY-SI | MC-77463 | PV | 3 | Yes | Inverter | 2014-05-12 | 2014-05-13 12:33 | 2014-05-13 12:37 | 2014-05-13 12:39 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-07-21 | No | Complete | Complete
CENY-SI | MC-77496 | PV | 3 | Yes | Inverter | 2014-05-12 | 2014-05-13 13:07 | 2014-05-13 13:09 | 2014-05-13 13:11 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-07-18 | No | Complete | Complete
CENY-SI | MC-77744 | PV | 4.4 | Yes | Inverter | 2014-05-13 | 2014-05-27 10:43 | 2014-05-27 10:44 | 2014-05-27 10:44 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending customer build
CENY-SI | MC-77951 | PV | 9.8 | Yes | Inverter | 2014-05-14 | 2014-05-15 07:08 | 2014-05-15 07:11 | 2014-05-15 07:12 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-23 | No | Complete | Complete
CENY-SI | MC-78021 | PV | 6.6 | Yes | Inverter | 2014-05-14 | 2014-05-15 11:36 | 2014-05-15 11:42 | 2014-05-15 11:52 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending customer build
CENY-SI | MC-78022 | PV | 7 | Yes | Inverter | 2014-05-14 | 2014-05-15 12:43 | 2014-05-15 12:45 | 2014-05-15 12:47 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending customer build
CENY-SI | MC-78167 | PV | 5.8 | Yes | Inverter | 2014-05-15 | 2014-05-21 10:43 | 2014-05-21 10:51 | 2014-05-21 10:57 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending customer build
CENY-SI | MC-78172 | PV | 5.4 | Yes | Inverter | 2014-05-15 | 2014-05-21 11:11 | 2014-05-21 11:33 | 2014-05-21 11:37 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending customer build
CENY-SI | MC-78193 | PV | 4.8 | Yes | Inverter | 2014-05-15 | 2014-05-21 11:49 | 2014-05-21 11:54 | 2014-05-21 12:01 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-24 | No | Complete | Complete
CENY-SI | MC-78228 | PV | 5.2 | Yes | Inverter | 2014-05-15 | 2014-05-21 13:23 | 2014-05-21 13:29 | 2014-05-21 13:34 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending customer build
CENY-SI | MC-78305 | PV | 4.8 | Yes | Inverter | 2014-05-15 | 2014-05-21 14:05 | 2014-05-21 14:09 | 2014-05-21 14:12 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending customer build
CENY-SI | MC-78327 | PV | 4 | Yes | Inverter | 2014-05-15 | 2014-05-21 14:30 | 2014-05-21 14:39 | 2014-05-21 14:42 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending final documents
CENY-SI | MC-78567 | PV | 6.8 | Yes | Inverter | 2014-05-19 | 2014-05-23 07:21 | 2014-05-23 07:24 | 2014-05-23 07:25 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending customer build
CENY-SI | MC-78573 | PV | 5 | Yes | Inverter | 2014-05-19 | 2014-05-23 07:36 | 2014-05-23 07:39 | 2014-05-23 07:46 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending customer build
CENY-SI | MC-78576 | PV | 4.8 | Yes | Inverter | 2014-05-19 | 2014-05-23 07:51 | 2014-05-23 07:52 | 2014-05-23 07:52 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending customer build
CENY-SI | MC-78639 | PV | 6 | Yes | Inverter | 2014-05-19 | 2014-05-20 09:17 | 2014-05-20 09:20 | 2014-05-20 09:22 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending meter exchange
CENY-SI | MC-78977 | PV | 11.4 | Yes | Inverter | 2014-05-20 | 2014-05-23 08:37 | 2014-05-23 08:38 | 2014-05-23 08:38 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending customer build
CENY-SI | MC-78985 | PV | 10 | Yes | Inverter | 2014-05-20 | 2014-05-23 07:58 | 2014-05-23 08:03 | 2014-05-23 08:05 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-10-09 | No | Complete | Complete
CENY-SI | MC-78994 | PV | 7.2 | Yes | Inverter | 2014-05-20 | 2014-05-23 08:33 | 2014-05-23 08:34 | 2014-05-23 08:32 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-16 | No | Complete | Complete
CENY-SI | MC-79030 | PV | 10 | Yes | Inverter | 2014-05-20 | 2014-05-23 08:23 | 2014-05-23 08:25 | 2014-05-23 08:26 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-29 | No | Complete | Complete
CENY-SI | MC-79124 | PV | 11.3 | Yes | Inverter | 2014-05-21 | 2014-05-23 09:36 | 2014-05-23 09:38 | 2014-05-23 09:38 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | Cancelled | Cancelled
CENY-SI | MC-79142 | PV | 3.8 | Yes | Inverter | 2014-05-21 | 2014-05-23 09:43 | 2014-05-23 09:47 | 2014-05-23 09:48 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-21 | No | Complete | Complete
CENY-SI | MC-79154 | PV | 9 | Yes | Inverter | 2014-05-21 | 2014-05-23 09:54 | 2014-05-23 10:00 | 2014-05-23 09:58 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-07 | No | Complete | Complete
CENY-SI | MC-79165 | PV | 12.8 | Yes | Inverter | 2014-05-21 | 2014-05-23 09:27 | 2014-05-23 09:31 | 2014-05-23 09:33 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending customer build
CENY-SI | MC-79214 | PV | 2.6 | Yes | Inverter | 2014-05-21 | 2014-05-23 07:04 | 2014-05-23 07:05 | 2014-05-23 07:05 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending final documents
CENY-SI | MC-79240 | PV | 5 | Yes | Inverter | 2014-05-21 | 2014-05-23 07:08 | 2014-05-23 07:08 | 2014-05-23 07:09 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-19 | No | Complete | Complete
CENY-SI | MC-79251 | PV | 3.8 | Yes | Inverter | 2014-05-21 | 2014-05-22 15:16 | 2014-05-22 15:17 | 2014-05-22 15:18 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | Cancelled | Cancelled
CENY-SI | MC-79255 | PV | 4.4 | Yes | Inverter | 2014-05-21 | 2014-05-22 15:12 | 2014-05-22 15:12 | 2014-05-22 15:13 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-24 | No | Complete | Complete
CENY-SI | MC-79259 | PV | 3.8 | Yes | Inverter | 2014-05-21 | 2014-05-22 15:08 | 2014-05-22 15:09 | 2014-05-22 15:09 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending customer build
CENY-SI | MC-79383 | PV | 3.2 | Yes | Inverter | 2014-05-22 | 2014-05-27 11:11 | 2014-05-27 11:12 | 2014-05-27 11:12 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-16 | No | Complete | Complete
CENY-SI | MC-79388 | PV | 3.2 | Yes | Inverter | 2014-05-22 | 2014-05-27 08:40 | 2014-05-27 08:44 | 2014-05-27 08:46 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending customer build
CENY-SI | MC-79404 | PV | 3.2 | Yes | Inverter | 2014-05-22 | 2014-05-27 08:33 | 2014-05-27 08:35 | 2014-05-27 08:35 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending customer build
CENY-SI | MC-79411 | PV | 3 | Yes | Inverter | 2014-05-22 | 2014-05-27 07:35 | 2014-05-27 07:37 | 2014-05-27 07:38 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending customer build
CENY-SI | MC-79417 | PV | 3.8 | Yes | Inverter | 2014-05-22 | 2014-05-27 07:59 | 2014-05-27 08:08 | 2014-05-27 08:13 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | Cancelled | Cancelled
CENY-SI | MC-79433 | PV | 5 | Yes | Inverter | 2014-05-22 | 2014-05-27 08:24 | 2014-05-27 08:26 | 2014-05-27 08:28 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-21 | No | Complete | Complete
CENY-SI | MC-79436 | PV | 4.2 | Yes | Inverter | 2014-05-22 | 2014-05-26 | 2014-05-27 07:53 | 2014-05-27 07:54 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-02 | No | Complete | Complete
CENY-SI | MC-79446 | PV | 6.8 | Yes | Inverter | 2014-05-22 | 2014-05-27 10:45 | 2014-05-27 10:46 | 2014-05-27 10:47 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-21 | No | Complete | Complete
CENY-SI | MC-79463 | PV | 2.8 | Yes | Inverter | 2014-05-22 | 2014-05-27 09:10 | 2014-05-27 09:11 | 2014-05-27 09:12 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending customer build
CENY-SI | MC-79471 | PV | 4.2 | Yes | Inverter | 2014-05-22 | 2014-05-27 09:16 | 2014-05-27 09:18 | 2014-05-27 09:21 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-04 | No | Complete | Complete
CENY-SI | MC-79483 | PV | 6 | Yes | Inverter | 2014-05-22 | 2014-06-17 08:54 | 2014-05-27 11:06 | 2014-05-27 11:07 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending customer build
CENY-SI | MC-79491 | PV | 5.2 | Yes | Inverter | 2014-05-22 | 2014-05-27 09:02 | 2014-05-27 09:03 | 2014-05-27 09:04 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending customer build
CENY-SI | MC-79516 | PV | 3.6 | Yes | Inverter | 2014-05-22 | 2014-05-27 07:45 | 2014-05-27 07:47 | 2014-05-27 07:49 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending customer build
CENY-SI | MC-79534 | PV | 4.4 | Yes | Inverter | 2014-05-22 | 2014-05-27 10:57 | 2014-05-27 10:58 | 2014-05-27 10:59 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-23 | No | Complete | Complete
CENY-SI | MC-79546 | PV | 2.8 | Yes | Inverter | 2014-05-22 | 2014-05-27 08:53 | 2014-05-27 08:55 | 2014-05-27 08:56 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-02 | No | Complete | Complete
CENY-SI | MC-79586 | PV | 5.4 | Yes | Inverter | 2014-05-22 | 2014-05-27 11:15 | 2014-05-27 11:16 | 2014-05-27 11:17 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-07-18 | No | Complete | Complete
CENY-SI | MC-79664 | PV | 2.4 | Yes | Inverter | 2014-05-23 | 2014-05-27 11:31 | 2014-05-27 11:34 | 2014-05-27 11:34 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-02 | No | Complete | Complete
CENY-SI | MC-79716 | PV | 2.6 | Yes | Inverter | 2014-05-23 | 2014-05-27 11:13 | 2014-05-27 11:15 | 2014-05-27 11:15 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending customer build
CENY-SI | MC-79764 | PV | 2.4 | Yes | Inverter | 2014-05-23 | 2014-05-27 11:23 | 2014-05-27 11:26 | 2014-05-27 11:26 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-16 | No | Complete | Complete
CENY-SI | MC-79771 | PV | 7.2 | Yes | Inverter | 2014-05-23 | 2014-05-27 11:41 | 2014-05-27 11:43 | 2014-05-27 11:43 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending customer build
CENY-SI | MC-80046 | PV | 8 | Yes | Inverter | 2014-05-28 | 2014-05-28 12:29 | 2014-05-28 12:31 | 2014-05-28 12:32 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending customer build
CENY-SI | MC-80056 | PV | 5 | Yes | Inverter | 2014-05-28 | 2014-05-28 12:23 | 2014-05-28 12:24 | 2014-05-28 12:25 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-19 | No | Complete | Complete
CENY-SI | MC-80066 | PV | 7.2 | Yes | Inverter | 2014-05-28 | 2014-05-28 12:42 | 2014-05-28 12:43 | 2014-05-28 12:44 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending customer build
CENY-SI | MC-80207 | PV | 4.4 | Yes | Inverter | 2014-05-28 | 2014-05-28 12:11 | 2014-05-28 12:12 | 2014-05-28 12:13 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending customer build
CENY-SI | MC-80212 | PV | 4.4 | Yes | Inverter | 2014-05-28 | 2014-05-28 12:18 | 2014-05-28 12:19 | 2014-05-28 12:19 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-16 | No | Complete | Complete
CENY-SI | MC-80325 | PV | 4.2 | Yes | Inverter | 2014-05-28 | 2014-05-29 11:59 | 2014-05-29 12:03 | 2014-05-29 12:53 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending customer build
CENY-SI | MC-80378 | PV | 5 | Yes | Inverter | 2014-05-28 | 2014-05-29 13:01 | 2014-05-29 13:07 | 2014-05-29 13:09 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-28 | No | Complete | Complete
CENY-SI | MC-80614 | PV | 4 | Yes | Inverter | 2014-05-29 | 2014-05-30 08:30 | 2014-05-30 08:32 | 2014-05-30 08:32 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-07-21 | No | Complete | Complete
CENY-SI | MC-80631 | PV | 7 | Yes | Inverter | 2014-05-29 | 2014-05-30 08:36 | 2014-05-30 08:37 | 2014-05-30 08:38 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-07-21 | No | Complete | Complete
CENY-SI | MC-80758 | PV | 6 | Yes | Inverter | 2014-05-30 | 2014-05-30 14:06 | 2014-05-30 14:06 | 2014-05-30 14:07 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending meter exchange
CENY-SI | MC-80765 | PV | 7.2 | Yes | Inverter | 2014-05-30 | 2014-05-30 14:11 | 2014-05-30 14:13 | 2014-05-30 14:13 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-19 | No | Complete | Complete
CENY-SI | MC-80787 | PV | 10 | Yes | Inverter | 2014-05-30 | 2014-05-30 14:01 | 2014-05-30 14:03 | 2014-05-30 14:03 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending customer build
CENY-SI | MC-80831 | PV | 10.2 | Yes | Inverter | 2014-05-30 | 2014-06-03 09:42 | 2014-06-03 10:15 | 2014-06-03 10:28 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-16 | No | Complete | Complete
CENY-SI | MC-80836 | PV | 12 | Yes | Inverter | 2014-05-30 | 2014-06-03 10:45 | 2014-06-03 10:50 | 2014-06-03 10:50 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending customer build
CENY-SI | MC-80839 | PV | 3.8 | Yes | Inverter | 2014-05-30 | 2014-06-03 11:21 | 2014-06-03 11:31 | 2014-06-03 11:34 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending customer build
CENY-SI | MC-80843 | PV | 8 | Yes | Inverter | 2014-05-30 | 2014-06-03 12:18 | 2014-06-03 12:24 | 2014-06-03 12:31 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-21 | No | Complete | Complete
CENY-SI | MC-80847 | PV | 6 | Yes | Inverter | 2014-05-30 | 2014-06-03 13:04 | 2014-06-03 13:43 | 2014-06-03 13:57 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending customer build
CENY-SI | MC-80883 | PV | 14 | Yes | Inverter | 2014-06-02 | 2014-06-03 14:32 | 2014-06-03 14:33 | 2014-06-03 14:35 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending customer build
CENY-SI | MC-81007 | PV | 5 | Yes | Inverter | 2014-06-02 | 2014-06-06 09:00 | 2014-06-06 09:04 | 2014-06-06 09:07 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending meter exchange
CENY-SI | MC-81045 | PV | 6 | Yes | Inverter | 2014-06-02 | 2014-06-06 08:43 | 2014-06-06 08:44 | 2014-06-06 08:46 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending meter exchange
CENY-SI | MC-81047 | PV | 4.4 | Yes | Inverter | 2014-06-02 | 2014-06-06 08:52 | 2014-06-06 08:53 | 2014-06-06 08:54 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending customer build
CENY-SI | MC-81077 | PV | 9 | Yes | Inverter | 2014-06-02 | 2014-06-12 10:21 | 2014-06-12 10:21 | 2014-06-12 10:21 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending customer build
CENY-SI | MC-81200 | PV | 4.6 | Yes | Inverter | 2014-06-03 | 2014-06-06 08:35 | 2014-06-06 08:37 | 2014-06-06 08:38 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending customer build
CENY-SI | MC-81877 | PV | 4.8 | Yes | Inverter | 2014-06-05 | 2014-06-26 08:20 | 2014-06-26 08:20 | 2014-06-26 08:21 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-22 | No | Complete | Complete
CENY-SI | MC-81904 | PV | 6 | Yes | Inverter | 2014-06-05 | 2014-06-06 09:21 | 2014-06-06 09:24 | 2014-06-06 09:25 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-05 | No | Complete | Complete
CENY-SI | MC-81986 | PV | 5.6 | Yes | Inverter | 2014-06-06 | 2014-06-09 09:23 | 2014-06-09 09:30 | 2014-06-09 09:36 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending customer build
CENY-SI | MC-82048 | PV | 7 | Yes | Inverter | 2014-06-06 | 2014-06-09 08:23 | 2014-06-09 08:51 | 2014-06-09 08:58 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending meter exchange
CENY-SI | MC-82081 | PV | 18 | Yes | Inverter | 2014-06-06 | 2014-06-11 09:09 | 2014-06-11 09:10 | 2014-06-11 09:10 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-10-07 | No | Complete | Complete
CENY-SI | MC-82082 | PV | 10.2 | Yes | Inverter | 2014-06-06 | 2014-06-12 10:13 | 2014-06-12 10:14 | 2014-06-12 10:14 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending customer build
CENY-SI | MC-82272 | PV | 10 | Yes | Inverter | 2014-06-09 | 2014-06-11 07:52 | 2014-06-11 07:54 | 2014-06-11 07:57 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending customer build
CENY-SI | MC-82355 | PV | 5 | Yes | Inverter | 2014-06-09 | 2014-06-11 08:20 | 2014-06-11 08:25 | 2014-06-11 08:32 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-19 | No | Complete | Complete
CENY-SI | MC-82371 | PV | 3.6 | Yes | Inverter | 2014-06-09 | 2014-06-11 07:38 | 2014-06-11 07:41 | 2014-06-11 07:42 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-16 | No | Complete | Complete
CENY-SI | MC-82902 | PV | 7.6 | Yes | Inverter | 2014-06-11 | 2014-06-12 15:01 | 2014-06-12 15:01 | 2014-06-12 15:02 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending customer build
CENY-SI | MC-82906 | PV | 9.8 | Yes | Inverter | 2014-06-11 | 2014-06-12 14:57 | 2014-06-12 14:58 | 2014-06-12 14:59 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-11 | No | Complete | Complete
CENY-SI | MC-82924 | PV | 10 | Yes | Inverter | 2014-06-11 | 2014-06-12 11:22 | 2014-06-12 11:26 | 2014-06-12 11:27 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-22 | No | Complete | Complete
CENY-SI | MC-82928 | PV | 6 | Yes | Inverter | 2014-06-11 | 2014-06-12 13:44 | 2014-06-12 13:44 | 2014-06-12 13:45 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-22 | No | Complete | Complete
CENY-SI | MC-82942 | PV | 8 | Yes | Inverter | 2014-06-11 | 2014-06-12 14:08 | 2014-06-12 14:09 | 2014-06-12 14:10 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-11 | No | Complete | Complete
CENY-SI | MC-82949 | PV | 11 | Yes | Inverter | 2014-06-11 | 2014-06-12 15:04 | 2014-06-12 15:05 | 2014-06-12 15:05 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-23 | No | Complete | Complete
CENY-SI | MC-82967 | PV | 12.5 | Yes | Inverter | 2014-06-11 | 2014-06-12 13:32 | 2014-06-12 13:33 | 2014-06-12 13:34 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending customer build
CENY-SI | MC-82972 | PV | 3 | Yes | Inverter | 2014-06-11 | 2014-06-12 13:38 | 2014-06-12 13:39 | 2014-06-12 13:40 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending customer build
CENY-SI | MC-82980 | PV | 5 | Yes | Inverter | 2014-06-11 | 2014-06-12 13:25 | 2014-06-12 13:26 | 2014-06-12 13:27 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending customer build
CENY-SI | MC-82996 | PV | 5 | Yes | Inverter | 2014-06-11 | 2014-06-12 15:07 | 2014-06-12 15:08 | 2014-06-12 15:09 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-30 | No | Complete | Complete
CENY-SI | MC-83001 | PV | 18 | Yes | Inverter | 2014-06-11 | 2014-06-12 15:10 | 2014-06-12 15:11 | 2014-06-12 15:11 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-11 | No | Complete | Complete
CENY-SI | MC-83003 | PV | 10 | Yes | Inverter | 2014-06-11 | 2014-06-11 | 2014-06-12 15:14 | 2014-06-12 15:15 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-16 | No | Complete | Complete
CENY-SI | MC-83024 | PV | 4 | Yes | Inverter | 2014-06-11 | 2014-06-12 15:18 | 2014-06-12 15:18 | 2014-06-12 15:19 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-29 | No | Complete | Complete
CENY-SI | MC-83226 | PV | 5 | Yes | Inverter | 2014-06-12 | 2014-06-26 07:09 | 2014-06-26 07:10 | 2014-06-26 07:11 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending customer build
CENY-SI | MC-83267 | PV | 9 | Yes | Inverter | 2014-06-12 | 2014-06-13 13:05 | 2014-06-13 13:09 | 2014-06-13 13:09 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending customer build
CENY-SI | MC-83415 | PV | 3.4 | Yes | Inverter | 2014-06-13 | 2014-06-17 07:39 | 2014-06-17 07:40 | 2014-06-17 07:40 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending final documents
CENY-SI | MC-83430 | PV | 6 | Yes | Inverter | 2014-06-13 | 2014-06-17 07:54 | 2014-06-17 07:55 | 2014-06-17 07:56 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending customer build
CENY-SI | MC-83488 | PV | 8 | Yes | Inverter | 2014-06-13 | 2014-06-17 08:05 | 2014-06-17 08:06 | 2014-06-17 08:06 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-21 | No | Complete | Complete
CENY-SI | MC-83497 | PV | 10 | Yes | Inverter | 2014-06-13 | 2014-06-17 08:11 | 2014-06-17 08:11 | 2014-06-17 08:12 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-21 | No | Complete | Complete
CENY-SI | MC-83499 | PV | 12 | Yes | Inverter | 2014-06-13 | 2014-06-17 07:51 | 2014-06-17 07:52 | 2014-06-17 07:53 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending meter exchange
CENY-SI | MC-83506 | PV | 6 | Yes | Inverter | 2014-06-13 | 2014-06-17 08:00 | 2014-06-17 08:52 | 2014-06-17 08:52 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending customer build
CENY-SI | MC-83512 | PV | 3.8 | Yes | Inverter | 2014-06-13 | 2014-06-17 10:08 | 2014-06-17 10:09 | 2014-06-17 10:10 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-10-07 | No | Complete | Complete
CENY-SI | MC-83515 | PV | 8 | Yes | Inverter | 2014-06-13 | 2014-06-17 10:12 | 2014-06-17 10:13 | 2014-06-17 10:13 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-10-07 | No | Complete | Complete
CENY-SI | MC-83655 | PV | 6 | Yes | Inverter | 2014-06-16 | 2014-06-17 10:18 | 2014-06-17 10:18 | 2014-06-17 10:19 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending customer build
CENY-SI | MC-83717 | PV | 9 | Yes | Inverter | 2014-06-16 | 2014-06-26 08:25 | 2014-06-26 08:25 | 2014-06-26 08:26 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | Cancelled | Cancelled
CENY-SI | MC-83779 | PV | 12.8 | Yes | Inverter | 2014-06-16 | 2014-06-18 11:49 | 2014-06-18 11:50 | 2014-06-18 11:50 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-10-02 | No | Complete | Complete
CENY-SI | MC-83806 | PV | 7.6 | Yes | Inverter | 2014-06-16 | 2014-06-18 11:56 | 2014-06-18 11:56 | 2014-06-18 11:57 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending customer build
CENY-SI | MC-83815 | PV | 12 | Yes | Inverter | 2014-06-16 | 2014-06-18 11:59 | 2014-06-18 12:00 | 2014-06-18 12:00 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending final documents
CENY-SI | MC-83826 | PV | 12.8 | Yes | Inverter | 2014-06-16 | 2014-06-18 12:02 | 2014-06-18 12:03 | 2014-06-18 12:03 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending customer build
CENY-SI | MC-83833 | PV | 10.2 | Yes | Inverter | 2014-06-16 | 2014-06-17 | 2014-06-18 12:06 | 2014-06-18 12:06 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending customer build
CENY-SI | MC-83843 | PV | 10.2 | Yes | Inverter | 2014-06-16 | 2014-06-18 12:08 | 2014-06-18 12:09 | 2014-06-18 12:09 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending customer build
CENY-SI | MC-84078 | PV | 6 | Yes | Inverter | 2014-06-17 | 2014-06-18 12:14 | 2014-06-18 12:15 | 2014-06-18 12:15 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-19 | No | Complete | Complete
CENY-SI | MC-84100 | PV | 3 | Yes | Inverter | 2014-06-17 | 2014-06-18 12:23 | 2014-06-18 12:24 | 2014-06-18 12:24 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending customer build
CENY-SI | MC-84111 | PV | 6 | Yes | Inverter | 2014-06-17 | 2014-06-18 12:20 | 2014-06-18 12:20 | 2014-06-18 12:21 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending final documents
CENY-SI | MC-84114 | PV | 5 | Yes | Inverter | 2014-06-17 | 2014-06-18 12:17 | 2014-06-18 12:18 | 2014-06-18 12:18 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending customer build
CENY-SI | MC-84117 | PV | 6.8 | Yes | Inverter | 2014-06-17 | 2014-06-18 12:11 | 2014-06-18 12:12 | 2014-06-18 12:12 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-21 | No | Complete | Complete
CENY-SI | MC-84258 | PV | 5.4 | Yes | Inverter | 2014-06-18 | 2014-06-18 12:50 | 2014-06-18 12:50 | 2014-06-18 12:50 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending customer build
CENY-SI | MC-84272 | PV | 5 | Yes | Inverter | 2014-06-18 | 2014-06-18 12:53 | 2014-06-18 12:54 | 2014-06-18 12:54 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending customer build
CENY-SI | MC-84282 | PV | 8 | Yes | Inverter | 2014-06-18 | 2014-07-02 09:18 | 2014-07-02 09:19 | 2014-07-02 09:19 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-16 | No | Complete | Complete
CENY-SI | MC-84289 | PV | 5 | Yes | Inverter | 2014-06-18 | 2014-06-19 07:53 | 2014-06-19 07:54 | 2014-06-19 07:54 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-07-18 | No | Complete | Complete
CENY-SI | MC-84300 | PV | 5 | Yes | Inverter | 2014-06-18 | 2014-06-19 07:57 | 2014-06-19 07:58 | 2014-06-19 07:58 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-07-18 | No | Complete | Complete
CENY-SI | MC-84306 | PV | 5 | Yes | Inverter | 2014-06-18 | 2014-06-19 07:23 | 2014-06-19 07:23 | 2014-06-19 07:24 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-19 | No | Complete | Complete
CENY-SI | MC-84315 | PV | 11 | Yes | Inverter | 2014-06-18 | 2014-06-19 07:58 | 2014-06-19 07:59 | 2014-06-19 07:59 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending customer build
CENY-SI | MC-84327 | PV | 2.8 | Yes | Inverter | 2014-06-18 | 2014-06-19 14:14 | 2014-06-19 14:15 | 2014-06-19 14:15 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-07-18 | No | Complete | Complete
CENY-SI | MC-84385 | PV | 7.8 | Yes | Inverter | 2014-06-18 | 2014-06-19 11:06 | 2014-06-19 11:07 | 2014-06-19 11:07 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-09 | No | Complete | Complete
CENY-SI | MC-84393 | PV | 10 | Yes | Inverter | 2014-06-18 | 2014-06-19 13:23 | 2014-06-19 13:23 | 2014-06-19 13:24 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending customer build
CENY-SI | MC-84395 | PV | 9.8 | Yes | Inverter | 2014-06-18 | 2014-06-19 11:22 | 2014-06-19 11:24 | 2014-06-19 11:25 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-30 | No | Complete | Complete
CENY-SI | MC-84397 | PV | 9.8 | Yes | Inverter | 2014-06-18 | 2014-06-19 13:38 | 2014-06-19 13:38 | 2014-06-19 13:39 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-10-02 | No | Complete | Complete
CENY-SI | MC-84399 | PV | 4 | Yes | Inverter | 2014-06-18 | 2014-06-19 13:54 | 2014-06-19 13:55 | 2014-06-19 13:55 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-07-25 | No | Complete | Complete
CENY-SI | MC-84402 | PV | 4 | Yes | Inverter | 2014-06-18 | 2014-06-19 11:03 | 2014-06-19 11:04 | 2014-06-19 11:04 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-07-25 | No | Complete | Complete
CENY-SI | MC-84404 | PV | 7 | Yes | Inverter | 2014-06-18 | 2014-06-19 11:00 | 2014-06-19 11:00 | 2014-06-19 11:00 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-07-25 | No | Complete | Complete
CENY-SI | MC-84418 | PV | 3 | Yes | Inverter | 2014-06-18 | 2014-06-19 10:56 | 2014-06-19 10:57 | 2014-06-19 10:57 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-19 | No | Complete | Complete
CENY-SI | MC-84579 | PV | 3.8 | Yes | Inverter | 2014-06-19 | 2014-06-20 14:55 | 2014-06-20 14:56 | 2014-06-20 14:56 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-27 | No | Complete | Complete
CENY-SI | MC-84587 | PV | 4.2 | Yes | Inverter | 2014-06-19 | 2014-06-23 11:31 | 2014-06-23 11:32 | 2014-06-23 11:32 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-16 | No | Complete | Complete
CENY-SI | MC-84599 | PV | 11.4 | Yes | Inverter | 2014-06-19 | 2014-06-20 15:10 | 2014-06-20 15:10 | 2014-06-20 15:11 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending customer build
CENY-SI | MC-84654 | PV | 4 | Yes | Inverter | 2014-06-19 | 2014-06-23 11:23 | 2014-06-23 11:23 | 2014-06-23 11:24 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-09 | No | Complete | Complete
CENY-SI | MC-84658 | PV | 3.2 | Yes | Inverter | 2014-06-19 | 2014-06-20 14:54 | 2014-06-23 11:19 | 2014-06-23 11:20 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending final documents
CENY-SI | MC-84671 | PV | 6.2 | Yes | Inverter | 2014-06-19 | 2014-06-20 15:13 | 2014-06-20 15:14 | 2014-06-20 15:14 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-21 | No | Complete | Complete
CENY-SI | MC-84672 | PV | 2.4 | Yes | Inverter | 2014-06-19 | 2014-06-20 14:50 | 2014-06-20 14:50 | 2014-06-20 14:51 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-11 | No | Complete | Complete
CENY-SI | MC-84678 | PV | 12 | Yes | Inverter | 2014-06-19 | 2014-06-20 14:47 | 2014-06-20 14:48 | 2014-06-20 14:48 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-19 | No | Complete | Complete
CENY-SI | MC-84679 | PV | 3 | Yes | Inverter | 2014-06-19 | 2014-06-20 14:44 | 2014-06-20 14:45 | 2014-06-20 14:45 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-07-18 | No | Complete | Complete
CENY-SI | MC-84684 | PV | 3 | Yes | Inverter | 2014-06-19 | 2014-06-20 15:00 | 2014-06-20 15:01 | 2014-06-20 15:01 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-27 | No | Complete | Complete
CENY-SI | MC-84688 | PV | 6 | Yes | Inverter | 2014-06-19 | 2014-06-20 15:06 | 2014-06-20 15:07 | 2014-06-20 15:07 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-05 | No | Complete | Complete
CENY-SI | MC-84849 | PV | 3.8 | Yes | Inverter | 2014-06-20 | 2014-06-23 14:56 | 2014-06-23 14:57 | 2014-06-23 14:57 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-21 | No | Complete | Complete
CENY-SI | MC-84858 | PV | 7.6 | Yes | Inverter | 2014-06-20 | 2014-06-23 14:50 | 2014-06-23 14:51 | 2014-06-23 14:51 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-10-02 | No | Complete | Complete
CENY-SI | MC-84866 | PV | 10 | Yes | Inverter | 2014-06-20 | 2014-06-23 14:34 | 2014-06-23 14:34 | 2014-06-23 14:34 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-24 | No | Complete | Complete
CENY-SI | MC-84927 | PV | 4 | Yes | Inverter | 2014-06-20 | 2014-06-23 14:42 | 2014-06-23 14:43 | 2014-06-23 14:43 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-19 | No | Complete | Complete
CENY-SI | MC-85138 | PV | 5.6 | Yes | Inverter | 2014-06-23 | 2014-06-24 08:20 | 2014-06-24 08:31 | 2014-06-24 08:33 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-07 | No | Complete | Complete
CENY-SI | MC-85342 | PV | 10 | Yes | Inverter | 2014-06-24 | 2014-06-25 | 2014-08-11 11:19 | 2014-08-11 11:19 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-10-07 | No | Complete | Complete
CENY-SI | MC-85682 | PV | 5 | Yes | Inverter | 2014-06-25 | 2014-06-27 15:00 | 2014-06-27 15:00 | 2014-06-27 15:01 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending customer build
CENY-SI | MC-85704 | PV | 12 | Yes | Inverter | 2014-06-25 | 2014-06-27 14:56 | 2014-06-27 14:56 | 2014-06-27 14:57 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending customer build
CENY-SI | MC-85759 | PV | 4 | Yes | Inverter | 2014-06-25 | 2014-06-27 15:03 | 2014-06-27 15:04 | 2014-06-27 15:04 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending customer build
CENY-SI | MC-85803 | PV | 10 | Yes | Inverter | 2014-06-26 | 2014-06-27 | 2014-08-11 10:53 | 2014-08-11 10:54 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-18 | No | Complete | Complete
CENY-SI | MC-85920 | PV | 5 | Yes | Inverter | 2014-06-26 | 2014-06-27 | 2014-08-13 07:53 | 2014-08-13 07:55 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-25 | No | Complete | Complete
CENY-SI | MC-86069 | PV | 2.8 | Yes | Inverter | 2014-06-27 | 2014-06-30 15:13 | 2014-06-30 15:13 | 2014-06-30 15:13 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending customer build
CENY-SI | MC-86102 | PV | 3.2 | Yes | Inverter | 2014-06-27 | 2014-06-30 14:18 | 2014-06-30 14:18 | 2014-06-30 14:19 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending final documents
CENY-SI | MC-86110 | PV | 6 | Yes | Inverter | 2014-06-27 | 2014-06-30 15:06 | 2014-06-30 15:07 | 2014-06-30 15:07 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending customer build
CENY-SI | MC-86114 | PV | 3.4 | Yes | Inverter | 2014-06-27 | 2014-06-30 15:10 | 2014-06-30 15:10 | 2014-06-30 15:10 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-30 | No | Complete | Complete
CENY-SI | MC-86118 | PV | 5 | Yes | Inverter | 2014-06-27 | 2014-06-30 15:08 | 2014-06-30 15:09 | 2014-06-30 15:10 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending customer build
CENY-SI | MC-86124 | PV | 3 | Yes | Inverter | 2014-06-27 | 2014-06-30 14:25 | 2014-06-30 14:25 | 2014-06-30 14:26 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-16 | No | Complete | Complete
CENY-SI | MC-86126 | PV | 15.6 | Yes | Inverter | 2014-06-27 | 2014-06-30 15:13 | 2014-06-30 15:15 | 2014-06-30 15:15 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-19 | No | Complete | Complete
CENY-SI | MC-86127 | PV | 6.2 | Yes | Inverter | 2014-06-27 | 2014-07-01 07:06 | 2014-07-01 07:07 | 2014-07-01 07:07 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending customer build
CENY-SI | MC-86281 | PV | 5 | Yes | Inverter | 2014-06-30 | 2014-07-02 07:56 | 2014-07-02 07:56 | 2014-07-02 07:57 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-22 | No | Complete | Complete
CENY-SI | MC-86417 | PV | 3.4 | Yes | Inverter | 2014-06-30 | 2014-07-02 07:46 | 2014-07-02 07:47 | 2014-07-02 07:47 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-10-02 | No | Complete | Complete
CENY-SI | MC-86556 | PV | 11.4 | Yes | Inverter | 2014-07-01 | 2014-08-26 10:25 | 2014-08-26 10:25 | 2014-08-26 10:26 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending final documents
CENY-SI | MC-86813 | PV | 9 | Yes | Inverter | 2014-07-02 | 2014-07-07 07:39 | 2014-07-07 07:40 | 2014-07-07 07:40 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-86840 | PV | 11.4 | Yes | Inverter | 2014-07-02 | 2014-08-11 12:44 | 2014-08-11 12:45 | 2014-08-11 12:46 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | pending final documents
CENY-SI | MC-86843 | PV | 11.4 | Yes | Inverter | 2014-07-02 | 2014-08-11 10:47 | 2014-08-11 10:47 | 2014-08-11 10:48 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-18 | No | Complete | Complete
CENY-SI | MC-86856 | PV | 11 | Yes | Inverter | 2014-07-02 | 2014-07-07 07:47 | 2014-07-07 07:48 | 2014-07-07 07:49 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-86944 | PV | 7 | Yes | Inverter | 2014-07-03 | 2014-07-07 12:58 | 2014-07-07 12:59 | 2014-07-07 12:59 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-30 | No | Complete | Complete
CENY-SI | MC-86995 | PV | 7.6 | Yes | Inverter | 2014-07-03 | 2014-07-07 13:56 | 2014-07-07 13:57 | 2014-07-07 13:57 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-86999 | PV | 8.8 | Yes | Inverter | 2014-07-03 | 2014-07-07 12:55 | 2014-07-07 12:55 | 2014-07-07 12:56 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-10-02 | No | Complete | Complete
CENY-SI | MC-87008 | PV | 9 | Yes | Inverter | 2014-07-03 | 2014-07-07 12:51 | 2014-07-07 12:52 | 2014-07-07 12:52 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-87022 | PV | 9.8 | Yes | Inverter | 2014-07-03 | 2014-07-07 11:17 | 2014-07-07 11:18 | 2014-07-07 11:18 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-87024 | PV | 3 | Yes | Inverter | 2014-07-03 | 2014-07-07 11:36 | 2014-07-07 11:38 | 2014-07-07 11:40 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-87051 | PV | 6 | Yes | Inverter | 2014-07-03 | 2014-07-07 13:59 | 2014-07-07 14:00 | 2014-07-07 14:01 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-10-02 | No | Complete | Complete
CENY-SI | MC-87052 | PV | 9.8 | Yes | Inverter | 2014-07-03 | 2014-07-07 14:13 | 2014-07-07 14:14 | 2014-07-07 14:14 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-87084 | PV | 9.8 | Yes | Inverter | 2014-07-03 | 2014-07-07 14:20 | 2014-07-07 14:22 | 2014-07-07 14:22 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-09 | No | Complete | Complete
CENY-SI | MC-87409 | PV | 5 | Yes | Inverter | 2014-07-07 | 2014-07-09 11:21 | 2014-07-09 11:21 | 2014-07-09 11:22 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-87472 | PV | 6 | Yes | Inverter | 2014-07-07 | 2014-07-09 11:11 | 2014-07-09 11:12 | 2014-07-09 11:12 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-02 | No | Complete | Complete
CENY-SI | MC-87574 | PV | 5.7 | Yes | Inverter | 2014-07-08 | 2014-08-06 08:06 | 2014-08-06 08:06 | 2014-08-06 08:07 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-09 | No | Complete | Complete
CENY-SI | MC-87652 | PV | 5 | Yes | Inverter | 2014-07-08 | 2014-08-20 13:42 | 2014-08-20 13:42 | 2014-08-20 13:42 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-87665 | PV | 15 | Yes | Inverter | 2014-07-08 | 2014-08-20 13:45 | 2014-08-20 13:45 | 2014-08-20 13:45 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-87740 | PV | 7 | Yes | Inverter | 2014-07-09 | 2014-07-10 08:22 | 2014-07-10 08:23 | 2014-07-10 08:23 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-87774 | PV | 100 | Yes | Inverter | 2014-07-09 | 2014-07-10 08:28 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-87816 | PV | 6.6 | Yes | Inverter | 2014-07-09 | 2014-07-11 14:17 | 2014-07-11 14:18 | 2014-07-11 14:18 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-87831 | PV | 12 | Yes | Inverter | 2014-07-09 | 2014-07-11 14:26 | 2014-07-11 14:27 | 2014-07-11 14:27 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-87843 | PV | 3.8 | Yes | Inverter | 2014-07-09 | 2014-07-11 14:23 | 2014-07-11 14:24 | 2014-07-11 14:24 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-87865 | PV | 5 | Yes | Inverter | 2014-07-09 | 2014-07-11 14:20 | 2014-07-11 14:21 | 2014-07-11 14:21 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-87892 | PV | 3 | Yes | Inverter | 2014-07-09 | 2014-07-11 14:30 | 2014-07-11 14:30 | 2014-07-11 14:31 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-87909 | PV | 12.8 | Yes | Inverter | 2014-07-09 | 2014-07-11 14:33 | 2014-07-11 14:33 | 2014-07-11 14:34 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-23 | No | Complete | Complete
CENY-SI | MC-87912 | PV | 13 | Yes | Inverter | 2014-07-09 | 2014-07-11 14:36 | 2014-07-11 14:36 | 2014-07-11 14:37 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-87918 | PV | 8 | Yes | Inverter | 2014-07-09 | 2014-07-11 14:40 | 2014-07-11 14:40 | 2014-07-11 14:41 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-16 | No | Complete | Complete
CENY-SI | MC-87920 | PV | 17.5 | Yes | Inverter | 2014-07-09 | 2014-07-11 14:44 | 2014-07-11 14:45 | 2014-07-11 14:45 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | Cancelled | Cancelled
CENY-SI | MC-87922 | PV | 3.8 | Yes | Inverter | 2014-07-09 | 2014-07-11 14:14 | 2014-07-11 14:14 | 2014-07-11 14:15 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-88042 | PV | 6 | Yes | Inverter | 2014-07-10 | 2014-07-11 14:48 | 2014-07-11 14:49 | 2014-07-11 14:49 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-25 | No | Complete | Complete
CENY-SI | MC-88127 | PV | 8 | Yes | Inverter | 2014-07-10 | 2014-07-11 14:51 | 2014-07-11 14:54 | 2014-07-11 14:54 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-88151 | PV | 6 | Yes | Inverter | 2014-07-10 | 2014-07-11 14:08 | 2014-07-11 14:08 | 2014-07-11 14:09 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-23 | No | Complete | Complete
CENY-SI | MC-88171 | PV | 6 | Yes | Inverter | 2014-07-10 | 2014-07-11 14:04 | 2014-07-11 14:05 | 2014-07-11 14:05 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-10-02 | No | Complete | Complete
CENY-SI | MC-88178 | PV | 7.5 | Yes | Inverter | 2014-07-10 | 2014-07-11 14:01 | 2014-07-11 14:02 | 2014-07-11 14:02 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-10-02 | No | Complete | Complete
CENY-SI | MC-88181 | PV | 6 | Yes | Inverter | 2014-07-10 | 2014-07-11 13:46 | 2014-07-11 13:47 | 2014-07-11 13:47 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-16 | No | Complete | Complete
CENY-SI | MC-88186 | PV | 8.8 | Yes | Inverter | 2014-07-10 | 2014-07-11 07:46 | 2014-07-11 07:47 | 2014-07-11 07:48 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-24 | No | Complete | Complete
CENY-SI | MC-88191 | PV | 6 | Yes | Inverter | 2014-07-10 | 2014-07-11 13:51 | 2014-07-11 13:51 | 2014-07-11 13:52 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-09 | No | Complete | Complete
CENY-SI | MC-88298 | PV | 8 | Yes | Inverter | 2014-07-11 | 2014-07-15 10:58 | 2014-07-15 10:59 | 2014-07-15 11:00 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-88311 | PV | 8 | Yes | Inverter | 2014-07-11 | 2014-07-15 10:41 | 2014-07-15 10:42 | 2014-07-15 10:42 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-88422 | PV | 6 | Yes | Inverter | 2014-07-11 | 2014-07-16 09:02 | 2014-07-16 09:03 | 2014-07-16 09:03 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-88579 | PV | 6.8 | Yes | Inverter | 2014-07-14 | 2014-07-16 08:58 | 2014-07-16 08:59 | 2014-07-16 08:59 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-88601 | PV | 7.2 | Yes | Inverter | 2014-07-14 | 2014-07-16 09:06 | 2014-07-16 09:07 | 2014-07-16 09:08 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | Cancelled | Cancelled
CENY-SI | MC-88608 | PV | 9.8 | Yes | Inverter | 2014-07-14 | 2014-07-16 09:11 | 2014-07-16 09:12 | 2014-07-16 09:12 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-88613 | PV | 10.2 | Yes | Inverter | 2014-07-14 | 2014-07-16 10:06 | 2014-07-16 10:08 | 2014-07-16 10:09 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-16 | No | Complete | Complete
CENY-SI | MC-88615 | PV | 5 | Yes | Inverter | 2014-07-14 | 2014-07-16 10:18 | 2014-07-16 10:19 | 2014-07-16 10:20 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-88664 | PV | 10.2 | Yes | Inverter | 2014-07-14 | 2014-07-16 10:35 | 2014-07-16 10:36 | 2014-07-16 10:36 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-88669 | PV | 13.5 | Yes | Inverter | 2014-07-14 | 2014-07-16 10:46 | 2014-07-16 10:47 | 2014-07-16 10:48 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-88684 | PV | 5 | Yes | Inverter | 2014-07-14 | 2014-07-16 10:53 | 2014-07-16 10:53 | 2014-07-16 10:54 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-88734 | PV | 4.2 | Yes | Inverter | 2014-07-14 | 2014-07-21 07:45 | 2014-07-21 07:46 | 2014-07-21 07:47 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-10-02 | No | Complete | Complete
CENY-SI | MC-88878 | PV | 8.8 | Yes | Inverter | 2014-07-15 | 2014-07-21 07:33 | 2014-07-21 07:34 | 2014-07-21 07:34 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-88881 | PV | 3.8 | Yes | Inverter | 2014-07-15 | 2014-07-21 07:39 | 2014-07-21 07:41 | 2014-07-21 07:41 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-88890 | PV | 9.2 | Yes | Inverter | 2014-07-15 | 2014-07-21 07:45 | 2014-07-21 07:46 | 2014-07-21 07:46 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | Cancelled | Cancelled
CENY-SI | MC-88906 | PV | 14 | Yes | Inverter | 2014-07-15 | 2014-07-21 07:52 | 2014-07-21 07:57 | 2014-07-21 07:58 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-88927 | PV | 15 | Yes | Inverter | 2014-07-15 | 2014-07-21 08:03 | 2014-07-21 08:04 | 2014-07-21 08:04 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending meter exchange
CENY-SI | MC-88961 | PV | 6.8 | Yes | Inverter | 2014-07-15 | 2014-07-21 08:10 | 2014-07-21 08:12 | 2014-07-21 08:12 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-88964 | PV | 6.8 | Yes | Inverter | 2014-07-15 | 2014-07-21 08:25 | 2014-07-21 08:27 | 2014-07-21 08:27 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-10-02 | No | Complete | Complete
CENY-SI | MC-88983 | PV | 7.6 | Yes | Inverter | 2014-07-15 | 2014-07-21 08:33 | 2014-07-21 08:35 | 2014-07-21 08:35 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-88985 | PV | 7.2 | Yes | Inverter | 2014-07-15 | 2014-07-21 08:39 | 2014-07-21 08:40 | 2014-07-21 08:40 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-16 | No | Complete | Complete
CENY-SI | MC-88988 | PV | 8.4 | Yes | Inverter | 2014-07-15 | 2014-07-21 08:43 | 2014-07-21 08:44 | 2014-07-21 08:44 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-10-02 | No | Complete | Complete
CENY-SI | MC-89151 | PV | 13.5 | Yes | Inverter | 2014-07-16 | 2014-07-17 15:01 | 2014-07-17 15:03 | 2014-07-17 15:03 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-10-02 | No | Complete | Complete
CENY-SI | MC-89164 | PV | 11 | Yes | Inverter | 2014-07-16 | 2014-07-17 15:17 | 2014-07-17 15:17 | 2014-07-17 15:18 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-89166 | PV | 5 | Yes | Inverter | 2014-07-16 | 2014-07-21 07:25 | 2014-07-21 07:26 | 2014-07-21 07:27 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-89169 | PV | 6.8 | Yes | Inverter | 2014-07-16 | 2014-07-21 07:29 | 2014-07-21 07:30 | 2014-07-21 07:30 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-89198 | PV | 7.6 | Yes | Inverter | 2014-07-16 | 2014-07-17 13:52 | 2014-07-17 13:53 | 2014-07-17 14:22 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-89206 | PV | 14 | Yes | Inverter | 2014-07-16 | 2014-07-17 13:45 | 2014-07-17 13:46 | 2014-07-17 13:46 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-89348 | PV | 8 | Yes | Inverter | 2014-07-17 | 2014-07-21 14:52 | 2014-07-21 14:53 | 2014-07-21 14:55 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-89352 | PV | 10.6 | Yes | Inverter | 2014-07-17 | 2014-07-21 14:47 | 2014-07-21 14:48 | 2014-07-21 14:48 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-10-02 | No | Complete | Complete
CENY-SI | MC-89358 | PV | 10.6 | Yes | Inverter | 2014-07-17 | 2014-07-21 14:41 | 2014-07-21 14:42 | 2014-07-21 14:42 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-89361 | PV | 11.4 | Yes | Inverter | 2014-07-17 | 2014-07-21 14:36 | 2014-07-21 14:38 | 2014-07-21 14:38 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-89378 | PV | 8.8 | Yes | Inverter | 2014-07-17 | 2014-07-21 14:28 | 2014-07-21 14:29 | 2014-07-21 14:29 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-10-02 | No | Complete | Complete
CENY-SI | MC-89401 | PV | 23.5 | Yes | Inverter | 2014-07-17 | 2014-07-21 14:23 | 2014-07-21 14:24 | 2014-07-21 14:24 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-10-07 | No | Complete | Complete
CENY-SI | MC-89497 | PV | 9.6 | Yes | Inverter | 2014-07-17 | 2014-07-21 14:11 | 2014-07-21 14:12 | 2014-07-21 14:12 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-29 | No | Complete | Complete
CENY-SI | MC-89501 | PV | 10.8 | Yes | Inverter | 2014-07-17 | 2014-07-21 14:17 | 2014-07-21 14:18 | 2014-07-21 14:18 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-23 | No | Complete | Complete
CENY-SI | MC-89574 | PV | 3 | Yes | Inverter | 2014-07-18 | 2014-07-21 11:47 | 2014-07-21 11:50 | 2014-07-21 11:51 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-89631 | PV | 3 | Yes | Inverter | 2014-07-18 | 2014-07-21 15:00 | 2014-07-21 15:01 | 2014-07-21 15:01 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-16 | No | Complete | Complete
CENY-SI | MC-89683 | PV | 8.8 | Yes | Inverter | 2014-07-18 | 2014-07-21 15:21 | 2014-07-21 15:21 | 2014-07-21 15:22 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-89685 | PV | 3.8 | Yes | Inverter | 2014-07-18 | 2014-07-21 15:16 | 2014-07-21 15:17 | 2014-07-21 15:17 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-89686 | PV | 11.8 | Yes | Inverter | 2014-07-18 | 2014-07-21 15:12 | 2014-07-21 15:13 | 2014-07-21 15:13 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-89688 | PV | 12 | Yes | Inverter | 2014-07-18 | 2014-07-21 15:09 | 2014-07-21 15:09 | 2014-07-21 15:10 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-89690 | PV | 8.8 | Yes | Inverter | 2014-07-18 | 2014-07-21 15:05 | 2014-07-21 15:06 | 2014-07-21 15:06 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-89845 | PV | 11 | Yes | Inverter | 2014-07-21 | 2014-07-23 08:26 | 2014-07-23 08:27 | 2014-07-23 08:28 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-89903 | PV | 6 | Yes | Inverter | 2014-07-21 | 2014-07-23 08:01 | 2014-07-23 08:03 | 2014-07-23 08:03 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-89944 | PV | 5.1 | Yes | Inverter | 2014-07-21 | 2014-07-23 08:37 | 2014-07-23 08:38 | 2014-07-23 08:39 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-89946 | PV | 5 | Yes | Inverter | 2014-07-21 | 2014-07-23 08:15 | 2014-07-23 08:15 | 2014-07-23 08:17 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | pending final documents
CENY-SI | MC-90371 | PV | 4 | Yes | Inverter | 2014-07-23 | 2014-07-25 07:36 | 2014-07-25 07:37 | 2014-07-25 07:37 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-90375 | PV | 5.8 | Yes | Inverter | 2014-07-23 | 2014-07-25 07:43 | 2014-07-25 07:44 | 2014-07-25 07:44 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-90405 | PV | 6.8 | Yes | Inverter | 2014-07-23 | 2014-07-25 07:56 | 2014-07-25 07:57 | 2014-07-25 07:57 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-90466 | PV | 6.6 | Yes | Inverter | 2014-07-23 | 2014-07-25 07:30 | 2014-07-25 07:30 | 2014-07-25 07:30 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-90493 | PV | 5 | Yes | Inverter | 2014-07-23 | 2014-07-25 07:59 | 2014-07-25 08:00 | 2014-07-25 08:00 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-90668 | PV | 4 | Yes | Inverter | 2014-07-24 | 2014-07-28 11:26 | 2014-07-28 11:28 | 2014-07-28 11:28 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-90691 | PV | 7.2 | Yes | Inverter | 2014-07-24 | 2014-07-28 11:33 | 2014-07-28 11:36 | 2014-07-28 11:36 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | Cancelled | Cancelled
CENY-SI | MC-90694 | PV | 5.2 | Yes | Inverter | 2014-07-24 | 2014-07-28 08:43 | 2014-07-28 08:44 | 2014-07-28 08:44 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-90708 | PV | 4.8 | Yes | Inverter | 2014-07-24 | 2014-07-28 11:20 | 2014-07-28 11:21 | 2014-07-28 11:21 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-90775 | PV | 5 | Yes | Inverter | 2014-07-24 | 2014-07-28 10:37 | 2014-07-28 10:38 | 2014-07-28 10:39 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-90793 | PV | 4.6 | Yes | Inverter | 2014-07-24 | 2014-07-28 10:44 | 2014-07-28 10:45 | 2014-07-28 10:46 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-11 | No | Complete | Complete
CENY-SI | MC-90805 | PV | 2.8 | Yes | Inverter | 2014-07-24 | 2014-07-28 10:55 | 2014-07-28 10:56 | 2014-07-28 10:57 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-90816 | PV | 4.6 | Yes | Inverter | 2014-07-24 | 2014-07-28 11:01 | 2014-07-28 11:03 | 2014-07-28 11:03 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-90824 | PV | 32.5 | Yes | Inverter | 2014-07-24 | 2014-07-24 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | Cancelled | Cancelled
CENY-SI | MC-90828 | PV | 4 | Yes | Inverter | 2014-07-24 | 2014-07-28 08:47 | 2014-07-28 08:48 | 2014-07-28 08:48 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-90839 | PV | 4 | Yes | Inverter | 2014-07-24 | 2014-07-28 11:08 | 2014-07-28 11:09 | 2014-07-28 11:10 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-90840 | PV | 5.2 | Yes | Inverter | 2014-07-24 | 2014-07-28 11:14 | 2014-07-28 11:15 | 2014-07-28 11:16 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-90843 | PV | 2.4 | Yes | Inverter | 2014-07-24 | 2014-07-28 08:55 | 2014-07-28 08:56 | 2014-07-28 08:56 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-90913 | PV | 5 | Yes | Inverter | 2014-07-25 | 2014-07-28 11:47 | 2014-07-28 11:48 | 2014-07-28 11:49 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-90923 | PV | 6.4 | Yes | Inverter | 2014-07-25 | 2014-07-28 11:54 | 2014-07-28 11:54 | 2014-07-28 11:55 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-90937 | PV | 9.8 | Yes | Inverter | 2014-07-25 | 2014-07-28 12:04 | 2014-07-28 12:05 | 2014-07-28 12:06 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-90943 | PV | 16.4 | Yes | Inverter | 2014-07-25 | 2014-07-28 11:59 | 2014-07-28 12:00 | 2014-07-28 12:01 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-10-07 | No | Complete | Complete
CENY-SI | MC-90947 | PV | 6.8 | Yes | Inverter | 2014-07-25 | 2014-07-28 11:40 | 2014-07-28 11:40 | 2014-07-28 11:41 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-90963 | PV | 9.2 | Yes | Inverter | 2014-07-25 | 2014-07-28 12:10 | 2014-07-28 12:11 | 2014-07-28 12:11 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-10-03 | No | Complete | Complete
CENY-SI | MC-91073 | PV | 117.6 | Yes | Inverter | 2014-07-25 | 2014-07-25 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | Cancelled | Cancelled
CENY-SI | MC-91217 | PV | 6 | Yes | Inverter | 2014-07-28 | 2014-07-30 14:22 | 2014-07-30 14:27 | 2014-07-30 14:28 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-23 | No | Complete | Complete
CENY-SI | MC-91229 | PV | 6 | Yes | Inverter | 2014-07-28 | 2014-07-29 14:19 | 2014-07-29 14:20 | 2014-07-29 14:20 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-91244 | PV | 4.8 | Yes | Inverter | 2014-07-28 | 2014-07-29 11:26 | 2014-07-29 11:26 | 2014-07-29 11:27 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-23 | No | Complete | Complete
CENY-SI | MC-91245 | PV | 5.7 | Yes | Inverter | 2014-07-28 | 2014-07-28 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | Cancelled | Cancelled
CENY-SI | MC-91253 | PV | 4 | Yes | Inverter | 2014-07-28 | 2014-07-29 11:31 | 2014-07-29 11:32 | 2014-07-29 11:33 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-23 | No | Complete | Complete
CENY-SI | MC-91256 | PV | 6 | Yes | Inverter | 2014-07-28 | 2014-07-29 11:38 | 2014-07-29 11:38 | 2014-07-29 11:39 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-10-07 | No | Complete | Complete
CENY-SI | MC-91264 | PV | 6.3 | Yes | Inverter | 2014-07-28 | 2014-07-29 13:39 | 2014-07-29 13:39 | 2014-07-29 13:40 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-23 | No | Complete | Complete
CENY-SI | MC-91267 | PV | 3.3 | Yes | Inverter | 2014-07-28 | 2014-07-29 13:43 | 2014-07-29 13:43 | 2014-07-29 13:44 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending meter exchange
CENY-SI | MC-91272 | PV | 6 | Yes | Inverter | 2014-07-28 | 2014-07-29 13:47 | 2014-07-29 13:48 | 2014-07-29 13:48 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-10-02 | No | Complete | Complete
CENY-SI | MC-91286 | PV | 10.2 | Yes | Inverter | 2014-07-28 | 2014-07-30 07:53 | 2014-07-30 07:54 | 2014-07-30 07:54 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-23 | No | Complete | Complete
CENY-SI | MC-91300 | PV | 4.5 | Yes | Inverter | 2014-07-28 | 2014-07-29 14:12 | 2014-07-29 14:13 | 2014-07-29 14:13 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-24 | No | Complete | Complete
CENY-SI | MC-91312 | PV | 4.2 | Yes | Inverter | 2014-07-28 | 2014-07-29 14:08 | 2014-07-29 14:08 | 2014-07-29 14:09 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending meter exchange
CENY-SI | MC-91346 | PV | 6 | Yes | Inverter | 2014-07-28 | 2014-07-29 14:29 | 2014-07-29 14:30 | 2014-07-29 14:30 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-23 | No | Complete | Complete
CENY-SI | MC-91385 | PV | 3 | Yes | Inverter | 2014-07-28 | 2014-07-30 08:00 | 2014-07-30 08:02 | 2014-07-30 08:03 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-91395 | PV | 4.8 | Yes | Inverter | 2014-07-28 | 2014-07-28 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | Cancelled | Cancelled
CENY-SI | MC-91399 | PV | 8.1 | Yes | Inverter | 2014-07-28 | 2014-07-30 07:44 | 2014-07-30 07:46 | 2014-07-30 07:46 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | Cancelled | Cancelled
CENY-SI | MC-91400 | PV | 2.4 | Yes | Inverter | 2014-07-28 | 2014-07-30 08:07 | 2014-07-30 08:08 | 2014-07-30 08:08 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-91401 | PV | 3.6 | Yes | Inverter | 2014-07-28 | 2014-07-30 07:27 | 2014-07-30 07:28 | 2014-07-30 07:29 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-10-07 | No | Complete | Complete
CENY-SI | MC-91434 | PV | 8 | Yes | Inverter | 2014-07-29 | 2014-07-30 08:18 | 2014-07-30 08:19 | 2014-07-30 08:20 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-91438 | PV | 3.8 | Yes | Inverter | 2014-07-29 | 2014-07-30 08:13 | 2014-07-30 08:13 | 2014-07-30 08:14 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-91470 | PV | 3 | Yes | Inverter | 2014-07-29 | 2014-08-13 08:50 | 2014-08-13 08:50 | 2014-08-13 08:51 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-91472 | PV | 3.9 | Yes | Inverter | 2014-07-29 | 2014-08-25 07:12 | 2014-08-25 07:13 | 2014-08-25 07:14 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-91562 | PV | 9.3 | Yes | Inverter | 2014-07-29 | 2014-07-30 14:46 | 2014-07-30 14:47 | 2014-07-30 14:47 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-27 | No | Complete | Complete
CENY-SI | MC-91580 | PV | 5.7 | Yes | Inverter | 2014-07-29 | 2014-07-30 15:10 | 2014-07-30 15:11 | 2014-07-30 15:11 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-91608 | PV | 9.2 | Yes | Inverter | 2014-07-29 | 2014-07-30 15:05 | 2014-07-30 15:07 | 2014-07-30 15:07 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-10-02 | No | Complete | Complete
CENY-SI | MC-91618 | PV | 3.8 | Yes | Inverter | 2014-07-29 | 2014-07-30 14:57 | 2014-07-30 14:59 | 2014-07-30 15:00 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-91801 | PV | 11.4 | Yes | Inverter | 2014-07-30 | 2014-08-04 09:01 | 2014-08-04 09:02 | 2014-08-04 09:03 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | pending final documents
CENY-SI | MC-91830 | PV | 3 | Yes | Inverter | 2014-07-30 | 2014-08-04 11:49 | 2014-08-04 11:50 | 2014-08-04 11:50 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-91841 | PV | 9 | Yes | Inverter | 2014-07-30 | 2014-08-04 13:36 | 2014-08-04 13:37 | 2014-08-04 13:37 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-91847 | PV | 23 | Yes | Inverter | 2014-07-30 | 2014-08-04 13:41 | 2014-08-04 13:42 | 2014-08-04 13:42 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-91870 | PV | 4 | Yes | Inverter | 2014-07-30 | 2014-08-04 13:51 | 2014-08-04 13:52 | 2014-08-04 13:52 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-91879 | PV | 9.6 | Yes | Inverter | 2014-07-30 | 2014-08-04 14:10 | 2014-08-04 14:10 | 2014-08-04 14:11 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-91884 | PV | 4.8 | Yes | Inverter | 2014-07-30 | 2014-08-04 14:16 | 2014-08-04 14:17 | 2014-08-04 14:17 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-16 | No | Complete | Complete
CENY-SI | MC-91893 | PV | 6.2 | Yes | Inverter | 2014-07-30 | 2014-08-04 14:20 | 2014-08-04 14:21 | 2014-08-04 14:21 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-91899 | PV | 6 | Yes | Inverter | 2014-07-30 | 2014-08-04 11:52 | 2014-08-04 11:53 | 2014-08-04 11:53 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-91978 | PV | 10 | Yes | Inverter | 2014-07-31 | 2014-08-04 11:46 | 2014-08-04 11:46 | 2014-08-04 11:47 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | pending final documents
CENY-SI | MC-92297 | PV | 10 | Yes | Inverter | 2014-08-01 | 2014-08-04 14:00 | 2014-08-04 14:00 | 2014-08-04 14:01 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | pending final documents
CENY-SI | MC-92319 | PV | 10 | Yes | Inverter | 2014-08-01 | 2014-08-04 14:05 | 2014-08-04 14:06 | 2014-08-04 14:06 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-92474 | PV | 9 | Yes | Inverter | 2014-08-04 | 2014-08-04 14:33 | 2014-08-04 14:34 | 2014-08-04 14:35 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-92484 | PV | 6.4 | Yes | Inverter | 2014-08-04 | 2014-08-04 14:26 | 2014-08-04 14:27 | 2014-08-04 14:27 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-92522 | PV | 5.2 | Yes | Inverter | 2014-08-04 | 2014-08-04 14:43 | 2014-08-04 14:43 | 2014-08-04 14:44 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-92558 | PV | 10.2 | Yes | Inverter | 2014-08-04 | 2014-08-06 07:16 | 2014-08-06 07:17 | 2014-08-06 07:18 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-92624 | PV | 6.8 | Yes | Inverter | 2014-08-04 | 2014-08-06 07:25 | 2014-08-06 07:25 | 2014-08-06 07:25 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-92628 | PV | 6 | Yes | Inverter | 2014-08-04 | 2014-08-06 07:21 | 2014-08-06 07:21 | 2014-08-06 07:22 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-92696 | PV | 3.4 | Yes | Inverter | 2014-08-05 | 2014-08-11 10:23 | 2014-08-11 10:24 | 2014-08-11 10:24 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-92712 | PV | 5.8 | Yes | Inverter | 2014-08-05 | 2014-08-11 10:51 | 2014-08-11 10:52 | 2014-08-11 10:57 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-30 | No | Complete | Complete
CENY-SI | MC-92720 | PV | 3.2 | Yes | Inverter | 2014-08-05 | 2014-08-12 09:01 | 2014-08-12 09:02 | 2014-08-12 09:02 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-92729 | PV | 7 | Yes | Inverter | 2014-08-05 | 2014-08-12 08:56 | 2014-08-12 08:57 | 2014-08-12 08:57 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-92784 | PV | 12.6 | Yes | Inverter | 2014-08-05 | 2014-08-12 08:27 | 2014-08-12 08:27 | 2014-08-12 08:28 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-10-07 | No | Complete | Complete
CENY-SI | MC-92788 | PV | 8 | Yes | Inverter | 2014-08-05 | 2014-08-12 07:36 | 2014-08-12 07:37 | 2014-08-12 07:37 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-92791 | PV | 6 | Yes | Inverter | 2014-08-05 | 2014-08-12 07:26 | 2014-08-12 07:26 | 2014-08-12 07:27 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-92797 | PV | 2.8 | Yes | Inverter | 2014-08-05 | 2014-08-11 11:26 | 2014-08-11 11:27 | 2014-08-11 11:28 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-92802 | PV | 10 | Yes | Inverter | 2014-08-05 | 2014-08-11 12:43 | 2014-08-11 12:44 | 2014-08-11 12:45 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-92803 | PV | 5.6 | Yes | Inverter | 2014-08-05 | 2014-08-11 12:08 | 2014-08-11 12:38 | 2014-08-11 12:39 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-92806 | PV | 6 | Yes | Inverter | 2014-08-05 | 2014-08-11 11:50 | 2014-08-11 11:53 | 2014-08-11 11:55 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-92808 | PV | 4.8 | Yes | Inverter | 2014-08-05 | 2014-08-11 11:39 | 2014-08-11 11:41 | 2014-08-11 11:42 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-92824 | PV | 4 | Yes | Inverter | 2014-08-05 | 2014-08-07 07:24 | 2014-08-07 07:24 | 2014-08-07 07:26 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-92831 | PV | 8 | Yes | Inverter | 2014-08-05 | 2014-08-07 07:35 | 2014-08-07 07:36 | 2014-08-07 07:36 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-10-03 | No | Complete | Complete
CENY-SI | MC-92832 | PV | 5.4 | Yes | Inverter | 2014-08-05 | 2014-08-07 07:46 | 2014-08-07 07:48 | 2014-08-07 07:49 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-92834 | PV | 3.8 | Yes | Inverter | 2014-08-05 | 2014-08-07 07:53 | 2014-08-07 07:54 | 2014-08-07 07:55 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-92845 | PV | 3.2 | Yes | Inverter | 2014-08-05 | 2014-08-07 08:01 | 2014-08-07 08:02 | 2014-08-07 08:02 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-92861 | PV | 11 | Yes | Inverter | 2014-08-05 | 2014-08-07 08:05 | 2014-08-07 08:06 | 2014-08-07 08:06 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-92862 | PV | 7.6 | Yes | Inverter | 2014-08-05 | 2014-08-11 11:12 | 2014-08-11 11:14 | 2014-08-11 11:16 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-92954 | PV | 13 | Yes | Inverter | 2014-08-06 | 2014-08-11 10:13 | 2014-08-11 10:17 | 2014-08-11 10:18 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-93088 | PV | 6 | Yes | Inverter | 2014-08-06 | 2014-08-11 10:34 | 2014-08-11 10:38 | 2014-08-11 10:39 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-10-02 | No | Complete | Complete
CENY-SI | MC-93099 | PV | 5.6 | Yes | Inverter | 2014-08-06 | 2014-08-11 08:56 | 2014-08-11 09:00 | 2014-08-11 09:00 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-93112 | PV | 8.4 | Yes | Inverter | 2014-08-06 | 2014-08-11 08:45 | 2014-08-11 08:46 | 2014-08-11 08:47 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-23 | No | Complete | Complete
CENY-SI | MC-93196 | PV | 6 | Yes | Inverter | 2014-08-07 | 2014-08-11 07:40 | 2014-08-11 07:42 | 2014-08-11 07:43 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-93202 | PV | 10 | Yes | Inverter | 2014-08-07 | 2014-08-11 07:46 | 2014-08-11 07:46 | 2014-08-11 07:47 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-93208 | PV | 6.8 | Yes | Inverter | 2014-08-07 | 2014-08-11 07:50 | 2014-08-11 07:51 | 2014-08-11 07:51 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-93228 | PV | 8.4 | Yes | Inverter | 2014-08-07 | 2014-08-11 07:58 | 2014-08-11 07:59 | 2014-08-11 08:00 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-10-09 | No | Complete | Complete
CENY-SI | MC-93242 | PV | 8.4 | Yes | Inverter | 2014-08-07 | 2014-08-11 08:07 | 2014-08-11 08:08 | 2014-08-11 08:10 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-93249 | PV | 4.2 | Yes | Inverter | 2014-08-07 | 2014-08-11 07:22 | 2014-08-11 07:23 | 2014-08-11 07:23 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-10-02 | No | Complete | Complete
CENY-SI | MC-93272 | PV | 4.8 | Yes | Inverter | 2014-08-07 | 2014-08-11 08:14 | 2014-08-11 08:15 | 2014-08-11 08:15 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-23 | No | Complete | Complete
CENY-SI | MC-93275 | PV | 9.3 | Yes | Inverter | 2014-08-07 | 2014-08-11 08:19 | 2014-08-11 08:19 | 2014-08-11 08:20 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-23 | No | Complete | Complete
CENY-SI | MC-93276 | PV | 6.8 | Yes | Inverter | 2014-08-07 | 2014-08-11 08:22 | 2014-08-11 08:23 | 2014-08-11 08:23 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-93314 | PV | 5.4 | Yes | Inverter | 2014-08-07 | 2014-08-11 08:33 | 2014-08-11 08:36 | 2014-08-11 08:37 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-09 | No | Complete | Complete
CENY-SI | MC-93328 | PV | 7 | Yes | Inverter | 2014-08-07 | 2014-08-11 07:17 | 2014-08-11 07:17 | 2014-08-11 07:18 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-93340 | PV | 10 | Yes | Inverter | 2014-08-07 | 2014-08-11 07:21 | 2014-08-11 07:21 | 2014-08-11 07:22 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-93434 | PV | 7.6 | Yes | Inverter | 2014-08-08 | 2014-08-11 07:32 | 2014-08-11 07:37 | 2014-08-11 07:38 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | pending final documents
CENY-SI | MC-93436 | PV | 13.5 | Yes | Inverter | 2014-08-08 | 2014-08-12 08:02 | 2014-08-12 08:02 | 2014-08-12 08:03 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-93454 | PV | 8 | Yes | Inverter | 2014-08-08 | 2014-08-11 07:53 | 2014-08-11 07:54 | 2014-08-11 07:54 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-93460 | PV | 10.2 | Yes | Inverter | 2014-08-08 | 2014-08-11 07:58 | 2014-08-11 08:01 | 2014-08-11 08:01 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | Cancelled | Cancelled
CENY-SI | MC-93492 | PV | 14.2 | Yes | Inverter | 2014-08-08 | 2014-08-11 08:06 | 2014-08-11 08:10 | 2014-08-11 08:11 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-93498 | PV | 11 | Yes | Inverter | 2014-08-08 | 2014-08-11 08:30 | 2014-08-11 08:49 | 2014-08-11 09:14 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-93717 | PV | 11 | Yes | Inverter | 2014-08-11 | 2014-08-13 15:03 | 2014-08-13 15:04 | 2014-08-13 15:05 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-10-07 | No | Complete | Complete
CENY-SI | MC-93731 | PV | 11 | Yes | Inverter | 2014-08-11 | 2014-08-13 15:07 | 2014-08-13 15:08 | 2014-08-13 15:08 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-93761 | PV | 11 | Yes | Inverter | 2014-08-11 | 2014-08-13 15:28 | 2014-08-13 15:28 | 2014-08-13 15:28 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-93812 | PV | 5 | Yes | Inverter | 2014-08-11 | 2014-08-14 07:23 | 2014-08-14 07:23 | 2014-08-14 07:24 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-93821 | PV | 3 | Yes | Inverter | 2014-08-11 | 2014-08-13 15:24 | 2014-08-13 15:25 | 2014-08-13 15:25 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-93824 | PV | 7.2 | Yes | Inverter | 2014-08-11 | 2014-08-13 14:49 | 2014-08-13 14:50 | 2014-08-13 14:51 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-93831 | PV | 8.8 | Yes | Inverter | 2014-08-11 | 2014-08-13 14:41 | 2014-08-13 14:45 | 2014-08-13 14:45 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-30 | No | Complete | Complete
CENY-SI | MC-93832 | PV | 9.8 | Yes | Inverter | 2014-08-11 | 2014-08-13 14:36 | 2014-08-13 14:37 | 2014-08-13 14:37 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-93999 | PV | 6 | Yes | Inverter | 2014-08-12 | 2014-08-14 07:19 | 2014-08-14 07:19 | 2014-08-14 07:20 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-94007 | PV | 13.5 | Yes | Inverter | 2014-08-12 | 2014-08-14 07:34 | 2014-08-14 07:35 | 2014-08-14 07:36 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-94020 | PV | 9.8 | Yes | Inverter | 2014-08-12 | 2014-08-14 07:28 | 2014-08-14 07:29 | 2014-08-14 07:29 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-94032 | PV | 7.6 | Yes | Inverter | 2014-08-12 | 2014-08-14 07:45 | 2014-08-14 07:48 | 2014-08-14 07:48 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending final documents
CENY-SI | MC-94034 | PV | 9.2 | Yes | Inverter | 2014-08-12 | 2014-08-13 15:13 | 2014-08-13 15:14 | 2014-08-13 15:15 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-94038 | PV | 3 | Yes | Inverter | 2014-08-12 | 2014-08-13 14:48 | 2014-08-13 14:48 | 2014-08-13 14:49 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-94217 | PV | 21 | Yes | Inverter | 2014-08-13 | 2014-08-19 14:15 | 2014-08-19 14:16 | 2014-08-19 14:16 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-94264 | PV | 8.4 | Yes | Inverter | 2014-08-13 | 2014-08-19 14:11 | 2014-08-19 14:12 | 2014-08-19 14:12 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-94276 | PV | 6 | Yes | Inverter | 2014-08-13 | 2014-08-19 14:18 | 2014-08-19 14:18 | 2014-08-19 14:19 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-94281 | PV | 6.8 | Yes | Inverter | 2014-08-13 | 2014-08-19 14:04 | 2014-08-19 14:05 | 2014-08-19 14:05 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending meter exchange
CENY-SI | MC-94287 | PV | 4.2 | Yes | Inverter | 2014-08-13 | 2014-08-19 13:58 | 2014-08-19 13:59 | 2014-08-19 13:59 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-10-07 | No | Complete | Complete
CENY-SI | MC-94290 | PV | 8 | Yes | Inverter | 2014-08-13 | 2014-08-20 13:38 | 2014-08-20 13:38 | 2014-08-20 13:38 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-94297 | PV | 5 | Yes | Inverter | 2014-08-13 | 2014-08-19 13:51 | 2014-08-19 13:52 | 2014-08-19 13:52 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-94302 | PV | 16.8 | Yes | Inverter | 2014-08-13 | 2014-08-19 13:48 | 2014-08-19 13:48 | 2014-08-19 13:49 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-94416 | PV | 4.8 | Yes | Inverter | 2014-08-14 | 2014-08-20 11:13 | 2014-08-20 11:14 | 2014-08-20 11:14 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | pending customer build
CENY-SI | MC-94425 | PV | 6 | Yes | Inverter | 2014-08-14 | 2014-08-20 11:16 | 2014-08-20 11:16 | 2014-08-20 11:17 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-94458 | PV | 3.2 | Yes | Inverter | 2014-08-14 | 2014-08-20 11:30 | 2014-08-20 11:32 | 2014-08-20 11:32 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-94465 | PV | 2.4 | Yes | Inverter | 2014-08-14 | 2014-08-14 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | Cancelled | Cancelled
CENY-SI | MC-94470 | PV | 2.4 | Yes | Inverter | 2014-08-14 | 2014-08-20 11:22 | 2014-08-20 11:23 | 2014-08-20 11:23 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-94482 | PV | 5.8 | Yes | Inverter | 2014-08-14 | 2014-08-20 11:20 | 2014-08-20 11:20 | 2014-08-20 11:21 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-94516 | PV | 2.8 | Yes | Inverter | 2014-08-14 | 2014-08-18 15:19 | 2014-08-18 15:20 | 2014-08-18 15:20 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-94524 | PV | 4 | Yes | Inverter | 2014-08-14 | 2014-08-19 13:40 | 2014-08-19 13:40 | 2014-08-19 13:40 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-94531 | PV | 4 | Yes | Inverter | 2014-08-14 | 2014-08-18 15:22 | 2014-08-18 15:22 | 2014-08-18 15:23 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-94541 | PV | 5.4 | Yes | Inverter | 2014-08-14 | 2014-08-19 13:45 | 2014-08-19 13:46 | 2014-08-19 13:46 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-94550 | PV | 4.2 | Yes | Inverter | 2014-08-14 | 2014-08-19 13:43 | 2014-08-19 13:43 | 2014-08-19 13:43 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-94563 | PV | 4.2 | Yes | Inverter | 2014-08-14 | 2014-08-19 15:16 | 2014-08-19 15:19 | 2014-08-19 15:20 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-94573 | PV | 5 | Yes | Inverter | 2014-08-14 | 2014-08-20 11:06 | 2014-08-20 11:06 | 2014-08-20 11:07 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-94578 | PV | 4.2 | Yes | Inverter | 2014-08-14 | 2014-08-20 11:25 | 2014-08-20 11:26 | 2014-08-20 11:26 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-30 | No | Complete | Complete
CENY-SI | MC-94596 | PV | 6 | Yes | Inverter | 2014-08-14 | 2014-08-20 11:09 | 2014-08-20 11:11 | 2014-08-20 11:11 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-94665 | PV | 7.6 | Yes | Inverter | 2014-08-15 | 2014-08-20 11:35 | 2014-08-20 11:36 | 2014-08-20 11:36 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | pending final documents
CENY-SI | MC-94698 | PV | 9.2 | Yes | Inverter | 2014-08-15 | 2014-08-20 11:37 | 2014-08-20 11:38 | 2014-08-20 11:38 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-94720 | PV | 5.4 | Yes | Inverter | 2014-08-15 | 2014-08-20 11:42 | 2014-08-20 11:42 | 2014-08-20 11:42 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-12 | No | Complete | Complete
CENY-SI | MC-94722 | PV | 6 | Yes | Inverter | 2014-08-15 | 2014-08-20 11:44 | 2014-08-20 11:45 | 2014-08-20 11:47 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-94746 | PV | 7 | Yes | Inverter | 2014-08-15 | 2014-08-18 14:34 | 2014-08-18 14:43 | 2014-08-18 14:43 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-94749 | PV | 3.2 | Yes | Inverter | 2014-08-15 | 2014-08-18 14:45 | 2014-08-18 14:45 | 2014-08-18 14:46 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-94752 | PV | 10.5 | Yes | Inverter | 2014-08-15 | 2014-08-18 14:49 | 2014-08-18 14:50 | 2014-08-18 14:50 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-94760 | PV | 4.4 | Yes | Inverter | 2014-08-15 | 2014-08-20 12:11 | 2014-08-20 12:11 | 2014-08-20 12:12 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-30 | No | Complete | Complete
CENY-SI | MC-94765 | PV | 7.6 | Yes | Inverter | 2014-08-15 | 2014-08-18 14:52 | 2014-08-18 14:52 | 2014-08-18 14:53 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-94769 | PV | 7.2 | Yes | Inverter | 2014-08-15 | 2014-08-20 12:19 | 2014-08-20 12:20 | 2014-08-20 12:20 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-94770 | PV | 4.6 | Yes | Inverter | 2014-08-15 | 2014-08-20 12:14 | 2014-08-20 12:14 | 2014-08-20 12:15 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-94774 | PV | 3 | Yes | Inverter | 2014-08-15 | 2014-08-18 14:54 | 2014-08-18 14:55 | 2014-08-18 14:55 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-10-07 | No | Complete | Complete
CENY-SI | MC-94776 | PV | 3.8 | Yes | Inverter | 2014-08-15 | 2014-08-18 14:57 | 2014-08-18 14:57 | 2014-08-18 14:57 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-94786 | PV | 3.4 | Yes | Inverter | 2014-08-15 | 2014-08-18 14:59 | 2014-08-18 14:59 | 2014-08-18 15:00 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-94802 | PV | 6 | Yes | Inverter | 2014-08-15 | 2014-08-18 15:03 | 2014-08-18 15:04 | 2014-08-18 15:04 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-94807 | PV | 6.8 | Yes | Inverter | 2014-08-15 | 2014-08-18 15:06 | 2014-08-18 15:07 | 2014-08-18 15:07 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-94811 | PV | 6 | Yes | Inverter | 2014-08-15 | 2014-08-18 15:09 | 2014-08-18 15:09 | 2014-08-18 15:09 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-10-02 | No | Complete | Complete
CENY-SI | MC-94817 | PV | 6 | Yes | Inverter | 2014-08-15 | 2014-08-18 15:11 | 2014-08-18 15:11 | 2014-08-18 15:12 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending meter exchange
CENY-SI | MC-94819 | PV | 4.2 | Yes | Inverter | 2014-08-15 | 2014-08-18 14:27 | 2014-08-18 14:27 | 2014-08-18 14:27 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-94929 | PV | 5 | Yes | Inverter | 2014-08-18 | 2014-08-18 | 2014-08-18 14:32 | 2014-08-18 14:32 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-94934 | PV | 4 | Yes | Inverter | 2014-08-18 | 2014-08-18 14:29 | 2014-08-18 14:30 | 2014-08-18 14:30 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-94959 | PV | 6.9 | Yes | Inverter | 2014-08-18 | 2014-08-20 10:42 | 2014-08-20 10:43 | 2014-08-20 10:45 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-94974 | PV | 6.3 | Yes | Inverter | 2014-08-18 | 2014-08-20 10:48 | 2014-08-20 10:48 | 2014-08-20 10:49 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-12 | No | Complete | Complete
CENY-SI | MC-94981 | PV | 6.8 | Yes | Inverter | 2014-08-18 | 2014-08-20 10:08 | 2014-08-20 10:08 | 2014-08-20 10:08 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending final documents
CENY-SI | MC-94988 | PV | 11 | Yes | Inverter | 2014-08-18 | 2014-08-20 10:15 | 2014-08-20 10:16 | 2014-08-20 10:16 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-94989 | PV | 3 | Yes | Inverter | 2014-08-18 | 2014-08-20 10:11 | 2014-08-20 10:12 | 2014-08-20 10:12 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-95001 | PV | 4.6 | Yes | Inverter | 2014-08-18 | 2014-08-20 10:00 | 2014-08-20 10:01 | 2014-08-20 10:02 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-95003 | PV | 16.4 | Yes | Inverter | 2014-08-18 | 2014-08-20 13:20 | 2014-08-20 13:21 | 2014-08-20 13:21 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-95010 | PV | 4.2 | Yes | Inverter | 2014-08-18 | 2014-08-20 13:15 | 2014-08-20 13:16 | 2014-08-20 13:16 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-95014 | PV | 11.4 | Yes | Inverter | 2014-08-18 | 2014-08-20 12:26 | 2014-08-20 12:26 | 2014-08-20 12:27 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | pending final documents
CENY-SI | MC-95025 | PV | 10.2 | Yes | Inverter | 2014-08-18 | 2014-08-20 12:29 | 2014-08-20 12:30 | 2014-08-20 12:30 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-95041 | PV | 8 | Yes | Inverter | 2014-08-18 | 2014-08-20 12:33 | 2014-08-20 12:34 | 2014-08-20 12:34 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-95043 | PV | 3.8 | Yes | Inverter | 2014-08-18 | 2014-08-20 13:12 | 2014-08-20 13:12 | 2014-08-20 13:13 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-95050 | PV | 3.8 | Yes | Inverter | 2014-08-18 | 2014-08-20 12:36 | 2014-08-20 12:37 | 2014-08-20 12:37 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-95063 | PV | 6.8 | Yes | Inverter | 2014-08-18 | 2014-08-20 12:39 | 2014-08-20 12:40 | 2014-08-20 12:40 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-95068 | PV | 5.8 | Yes | Inverter | 2014-08-18 | 2014-08-20 12:42 | 2014-08-20 13:09 | 2014-08-20 13:10 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-95207 | PV | 3.2 | Yes | Inverter | 2014-08-19 | 2014-08-20 13:28 | 2014-08-20 13:29 | 2014-08-20 13:29 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-95221 | PV | 9.9 | Yes | Inverter | 2014-08-19 | 2014-08-20 13:35 | 2014-08-20 13:35 | 2014-08-20 13:35 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-95243 | PV | 4.8 | Yes | Inverter | 2014-08-19 | 2014-08-20 13:32 | 2014-08-20 13:32 | 2014-08-20 13:33 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-95257 | PV | 6 | Yes | Inverter | 2014-08-19 | 2014-08-20 | 2014-08-20 13:25 | 2014-08-20 13:26 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-95511 | PV | 20 | Yes | Inverter | 2014-08-20 | 2014-08-26 07:59 | 2014-08-26 08:04 | 2014-08-26 08:04 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending final documents
CENY-SI | MC-95589 | PV | 6.6 | Yes | Inverter | 2014-08-20 | 2014-08-26 08:08 | 2014-08-26 08:09 | 2014-08-26 08:09 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending meter exchange
CENY-SI | MC-95788 | PV | 1.8 | Yes | Inverter | 2014-08-21 | 2014-08-26 09:38 | 2014-08-26 09:52 | 2014-08-26 09:52 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-05 | No | Complete | Complete
CENY-SI | MC-95789 | PV | 6 | Yes | Inverter | 2014-08-21 | 2014-08-26 10:29 | 2014-08-26 10:29 | 2014-08-26 10:30 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-95863 | PV | 9 | Yes | Inverter | 2014-08-21 | 2014-08-26 09:44 | 2014-08-26 09:45 | 2014-08-26 09:45 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-95975 | PV | 10 | Yes | Inverter | 2014-08-22 | 2014-08-26 08:51 | 2014-08-26 08:56 | 2014-08-26 08:57 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-96022 | PV | 3.8 | Yes | Inverter | 2014-08-22 | 2014-08-26 09:18 | 2014-08-26 09:28 | 2014-08-26 09:29 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-96195 | PV | 4 | Yes | Inverter | 2014-08-25 | 2014-08-26 09:12 | 2014-08-26 09:13 | 2014-08-26 09:13 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-96238 | PV | 4 | Yes | Inverter | 2014-08-25 | 2014-08-26 09:17 | 2014-08-26 09:18 | 2014-08-26 09:18 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-96248 | PV | 4.2 | Yes | Inverter | 2014-08-25 | 2014-08-26 09:20 | 2014-08-26 09:20 | 2014-08-26 09:21 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-96282 | PV | 11 | Yes | Inverter | 2014-08-25 | 2014-08-26 09:34 | 2014-08-26 09:34 | 2014-08-26 09:35 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-96284 | PV | 2.6 | Yes | Inverter | 2014-08-25 | 2014-08-26 09:25 | 2014-08-26 09:26 | 2014-08-26 09:26 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-96290 | PV | 5.2 | Yes | Inverter | 2014-08-25 | 2014-08-26 09:36 | 2014-08-26 09:37 | 2014-08-26 09:37 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-96295 | PV | 10.2 | Yes | Inverter | 2014-08-25 | 2014-08-26 09:39 | 2014-08-26 09:39 | 2014-08-26 09:40 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-96306 | PV | 4.8 | Yes | Inverter | 2014-08-25 | 2014-08-26 09:42 | 2014-08-26 09:42 | 2014-08-26 09:42 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-96312 | PV | 5.4 | Yes | Inverter | 2014-08-25 | 2014-08-26 09:47 | 2014-08-26 09:47 | 2014-08-26 09:47 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-96315 | PV | 13.5 | Yes | Inverter | 2014-08-25 | 2014-08-26 10:34 | 2014-08-26 10:35 | 2014-08-26 10:35 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-10-02 | No | Complete | Complete
CENY-SI | MC-96317 | PV | 7.6 | Yes | Inverter | 2014-08-25 | 2014-08-26 10:37 | 2014-08-26 10:38 | 2014-08-26 10:38 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-96330 | PV | 6 | Yes | Inverter | 2014-08-25 | 2014-08-26 10:41 | 2014-08-26 10:41 | 2014-08-26 10:42 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-96336 | PV | 7.2 | Yes | Inverter | 2014-08-25 | 2014-08-26 10:45 | 2014-08-26 10:45 | 2014-08-26 10:45 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-96340 | PV | 8 | Yes | Inverter | 2014-08-25 | 2014-08-26 10:47 | 2014-08-26 10:48 | 2014-08-26 10:48 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-96350 | PV | 9 | Yes | Inverter | 2014-08-25 | 2014-08-26 10:53 | 2014-08-26 10:53 | 2014-08-26 10:54 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-96352 | PV | 7.2 | Yes | Inverter | 2014-08-25 | 2014-08-26 09:50 | 2014-08-26 09:50 | 2014-08-26 09:50 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-96382 | PV | 9 | Yes | Inverter | 2014-08-25 | 2014-08-26 09:31 | 2014-08-26 09:32 | 2014-08-26 09:32 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-96439 | PV | 20 | Yes | Inverter | 2014-08-26 | 2014-08-28 12:51 | 2014-08-28 12:51 | 2014-08-28 12:51 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-96450 | PV | 5 | Yes | Inverter | 2014-08-26 | 2014-08-28 10:45 | 2014-08-28 10:46 | 2014-08-28 10:47 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-96458 | PV | 5 | Yes | Inverter | 2014-08-26 | 2014-08-28 12:56 | 2014-08-28 12:56 | 2014-08-28 12:56 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-96489 | PV | 5.2 | Yes | Inverter | 2014-08-26 | 2014-08-28 12:58 | 2014-08-28 12:59 | 2014-08-28 12:59 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-96494 | PV | 6.2 | Yes | Inverter | 2014-08-26 | 2014-08-28 13:01 | 2014-08-28 13:02 | 2014-08-28 13:02 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-96502 | PV | 7.8 | Yes | Inverter | 2014-08-26 | 2014-08-28 11:27 | 2014-08-28 11:29 | 2014-08-28 11:29 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-96503 | PV | 5 | Yes | Inverter | 2014-08-26 | 2014-08-28 11:23 | 2014-08-28 11:24 | 2014-08-28 11:25 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-96512 | PV | 5 | Yes | Inverter | 2014-08-26 | 2014-08-28 11:19 | 2014-08-28 11:20 | 2014-08-28 11:20 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-96526 | PV | 5 | Yes | Inverter | 2014-08-26 | 2014-08-28 10:41 | 2014-08-28 10:42 | 2014-08-28 10:42 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-96538 | PV | 4.2 | Yes | Inverter | 2014-08-26 | 2014-08-28 11:11 | 2014-08-28 11:11 | 2014-08-28 11:14 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-96541 | PV | 8.8 | Yes | Inverter | 2014-08-26 | 2014-08-28 13:20 | 2014-08-28 13:20 | 2014-08-28 13:20 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending meter exchange
CENY-SI | MC-96584 | PV | 16.4 | Yes | Inverter | 2014-08-26 | 2014-08-28 12:53 | 2014-08-28 12:54 | 2014-08-28 12:54 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-96590 | PV | 4.2 | Yes | Inverter | 2014-08-26 | 2014-08-28 11:04 | 2014-08-28 11:06 | 2014-08-28 11:06 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-96598 | PV | 4.2 | Yes | Inverter | 2014-08-26 | 2014-08-28 10:57 | 2014-08-28 10:58 | 2014-08-28 11:01 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-96606 | PV | 11 | Yes | Inverter | 2014-08-26 | 2014-08-28 10:52 | 2014-08-28 10:54 | 2014-08-28 10:54 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-96608 | PV | 10.2 | Yes | Inverter | 2014-08-26 | 2014-08-28 13:04 | 2014-08-28 13:04 | 2014-08-28 13:05 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-96611 | PV | 13.5 | Yes | Inverter | 2014-08-26 | 2014-08-28 13:07 | 2014-08-28 13:08 | 2014-08-28 13:08 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-96614 | PV | 8 | Yes | Inverter | 2014-08-26 | 2014-08-28 10:35 | 2014-08-28 10:37 | 2014-08-28 10:37 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-96707 | PV | 7.5 | Yes | Inverter | 2014-08-27 | 2014-08-28 13:16 | 2014-08-28 13:17 | 2014-08-28 13:17 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | Cancelled | Cancelled
CENY-SI | MC-96714 | PV | 7.2 | Yes | Inverter | 2014-08-27 | 2014-08-28 13:33 | 2014-08-28 13:34 | 2014-08-28 13:34 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-96723 | PV | 5 | Yes | Inverter | 2014-08-27 | 2014-08-28 13:30 | 2014-08-28 13:31 | 2014-08-28 13:31 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-96730 | PV | 8 | Yes | Inverter | 2014-08-27 | 2014-08-28 13:25 | 2014-08-28 13:26 | 2014-08-28 13:26 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-96731 | PV | 7 | Yes | Inverter | 2014-08-27 | 2014-08-28 13:22 | 2014-08-28 13:23 | 2014-08-28 13:23 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-96733 | PV | 7.6 | Yes | Inverter | 2014-08-27 | 2014-08-28 13:28 | 2014-08-28 13:28 | 2014-08-28 13:28 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-96759 | PV | 7 | Yes | Inverter | 2014-08-27 | 2014-08-28 13:37 | 2014-08-28 13:37 | 2014-08-28 13:38 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-96771 | PV | 6.8 | Yes | Inverter | 2014-08-27 | 2014-08-28 13:39 | 2014-08-28 13:40 | 2014-08-28 13:40 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-96774 | PV | 7.6 | Yes | Inverter | 2014-08-27 | 2014-08-28 13:42 | 2014-08-28 13:42 | 2014-08-28 13:43 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-96775 | PV | 6.3 | Yes | Inverter | 2014-08-27 | 2014-08-28 13:45 | 2014-08-28 13:45 | 2014-08-28 13:45 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | Cancelled | Cancelled
CENY-SI | MC-96804 | PV | 3.3 | Yes | Inverter | 2014-08-27 | 2014-08-28 13:48 | 2014-08-28 13:48 | 2014-08-28 13:49 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | Cancelled | Cancelled
CENY-SI | MC-96810 | PV | 9.2 | Yes | Inverter | 2014-08-27 | 2014-08-28 13:50 | 2014-08-28 13:51 | 2014-08-28 13:51 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-96820 | PV | 3 | Yes | Inverter | 2014-08-27 | 2014-08-28 13:53 | 2014-08-28 13:53 | 2014-08-28 13:54 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-30 | No | Complete | Complete
CENY-SI | MC-96825 | PV | 6.8 | Yes | Inverter | 2014-08-27 | 2014-08-28 13:55 | 2014-08-28 13:56 | 2014-08-28 13:56 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-96827 | PV | 10.6 | Yes | Inverter | 2014-08-27 | 2014-08-28 13:58 | 2014-08-28 13:58 | 2014-08-28 13:59 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-96831 | PV | 13.5 | Yes | Inverter | 2014-08-27 | 2014-08-28 14:00 | 2014-08-28 14:01 | 2014-08-28 14:01 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-96836 | PV | 6 | Yes | Inverter | 2014-08-27 | 2014-08-28 14:46 | 2014-08-28 14:46 | 2014-08-28 14:46 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-96837 | PV | 7.6 | Yes | Inverter | 2014-08-27 | 2014-08-28 14:49 | 2014-08-28 14:49 | 2014-08-28 14:50 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-96838 | PV | 8 | Yes | Inverter | 2014-08-27 | 2014-08-28 14:51 | 2014-08-28 14:52 | 2014-08-28 14:52 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-96841 | PV | 6.8 | Yes | Inverter | 2014-08-27 | 2014-08-28 13:14 | 2014-08-28 13:14 | 2014-08-28 13:15 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-96842 | PV | 7.5 | Yes | Inverter | 2014-08-27 | 2014-08-28 12:42 | 2014-08-28 13:11 |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | Cancelled | Cancelled
CENY-SI | MC-96843 | PV | 6 | Yes | Inverter | 2014-08-27 | 2014-09-03 10:43 | 2014-09-03 10:43 | 2014-09-03 10:44 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-96952 | PV | 8 | Yes | Inverter | 2014-08-28 | 2014-09-02 15:24 | 2014-09-02 15:24 | 2014-09-02 15:24 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-96962 | PV | 3 | Yes | Inverter | 2014-08-28 | 2014-09-02 15:21 | 2014-09-02 15:22 | 2014-09-02 15:22 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-96966 | PV | 10.5 | Yes | Inverter | 2014-08-28 | 2014-09-02 15:19 | 2014-09-02 15:19 | 2014-09-02 15:20 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-96969 | PV | 10.5 | Yes | Inverter | 2014-08-28 | 2014-09-02 15:17 | 2014-09-02 15:17 | 2014-09-02 15:17 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-96970 | PV | 10 | Yes | Inverter | 2014-08-28 | 2014-09-02 15:13 | 2014-09-02 15:14 | 2014-09-02 15:14 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-96976 | PV | 3 | Yes | Inverter | 2014-08-28 | 2014-09-02 15:10 | 2014-09-02 15:11 | 2014-09-02 15:11 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-96989 | PV | 8.4 | Yes | Inverter | 2014-08-28 | 2014-09-03 10:29 | 2014-09-03 10:30 | 2014-09-03 10:30 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | Cancelled | Cancelled
CENY-SI | MC-96990 | PV | 3.3 | Yes | Inverter | 2014-08-28 | 2014-09-03 10:26 | 2014-09-03 10:27 | 2014-09-03 10:27 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | Cancelled | Cancelled
CENY-SI | MC-97005 | PV | 3.8 | Yes | Inverter | 2014-08-28 | 2014-09-02 15:07 | 2014-09-02 15:08 | 2014-09-02 15:08 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-97007 | PV | 6 | Yes | Inverter | 2014-08-28 | 2014-09-02 15:04 | 2014-09-02 15:05 | 2014-09-02 15:05 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-97019 | PV | 10.2 | Yes | Inverter | 2014-08-28 | 2014-09-02 15:00 | 2014-09-02 15:02 | 2014-09-02 15:03 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-97055 | PV | 9 | Yes | Inverter | 2014-08-28 | 2014-09-02 14:55 | 2014-09-02 14:56 | 2014-09-02 14:57 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-97058 | PV | 11.8 | Yes | Inverter | 2014-08-28 | 2014-09-03 10:22 | 2014-09-03 10:23 | 2014-09-03 10:23 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-97060 | PV | 8 | Yes | Inverter | 2014-08-28 | 2014-09-02 14:53 | 2014-09-02 14:53 | 2014-09-02 14:54 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-97062 | PV | 4.2 | Yes | Inverter | 2014-08-28 | 2014-09-02 14:50 | 2014-09-02 14:51 | 2014-09-02 14:51 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-97158 | PV | 6.8 | Yes | Inverter | 2014-08-29 | 2014-09-03 10:19 | 2014-09-03 10:20 | 2014-09-03 10:20 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-97164 | PV | 11.4 | Yes | Inverter | 2014-08-29 | 2014-09-03 10:16 | 2014-09-03 10:16 | 2014-09-03 10:17 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-97175 | PV | 3.8 | Yes | Inverter | 2014-08-29 | 2014-09-03 10:12 | 2014-09-03 10:14 | 2014-09-03 10:14 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-97179 | PV | 6.8 | Yes | Inverter | 2014-08-29 | 2014-09-03 10:09 | 2014-09-03 10:09 | 2014-09-03 10:10 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-97450 | PV | 3.2 | Yes | Inverter | 2014-09-03 | 2014-09-03 10:36 | 2014-09-03 10:36 | 2014-09-03 10:36 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-97461 | PV | 2.8 | Yes | Inverter | 2014-09-03 | 2014-09-03 10:45 | 2014-09-03 10:46 | 2014-09-03 10:46 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-97466 | PV | 3.4 | Yes | Inverter | 2014-09-03 | 2014-09-03 10:48 | 2014-09-03 10:48 | 2014-09-03 10:48 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-97494 | PV | 3.8 | Yes | Inverter | 2014-09-03 | 2014-09-03 | 2014-09-03 10:54 | 2014-09-03 10:54 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-97505 | PV | 9 | Yes | Inverter | 2014-09-03 | 2014-09-03 10:51 | 2014-09-03 10:51 | 2014-09-03 10:52 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-97508 | PV | 3.6 | Yes | Inverter | 2014-09-03 | 2014-09-03 10:56 | 2014-09-03 10:56 | 2014-09-03 10:56 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-97616 | PV | 3.6 | Yes | Inverter | 2014-09-03 | 2014-09-05 14:37 | 2014-09-05 14:41 | 2014-09-05 14:41 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-97622 | PV | 5.8 | Yes | Inverter | 2014-09-03 | 2014-09-04 14:41 | 2014-09-05 14:42 | 2014-09-05 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-97658 | PV | 2.8 | Yes | Inverter | 2014-09-03 | 2014-09-05 14:46 | 2014-09-05 14:47 | 2014-09-05 14:48 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-97665 | PV | 3 | Yes | Inverter | 2014-09-03 | 2014-09-05 15:18 | 2014-09-05 15:19 | 2014-09-05 15:19 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-97678 | PV | 3 | Yes | Inverter | 2014-09-03 | 2014-09-05 14:52 | 2014-09-05 14:53 | 2014-09-05 14:54 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-97682 | PV | 3.8 | Yes | Inverter | 2014-09-03 | 2014-09-05 12:14 | 2014-09-05 12:15 | 2014-09-05 12:15 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-97715 | PV | 4.2 | Yes | Inverter | 2014-09-03 | 2014-09-05 12:10 | 2014-09-05 12:11 | 2014-09-05 12:12 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-97734 | PV | 3.9 | Yes | Inverter | 2014-09-03 | 2014-09-05 12:06 | 2014-09-05 12:07 | 2014-09-05 12:07 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-97740 | PV | 10 | Yes | Inverter | 2014-09-03 | 2014-09-05 12:00 | 2014-09-05 12:01 | 2014-09-05 12:01 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-97761 | PV | 6 | Yes | Inverter | 2014-09-03 | 2014-09-05 11:53 | 2014-09-05 11:54 | 2014-09-05 11:55 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-97770 | PV | 5 | Yes | Inverter | 2014-09-03 | 2014-09-05 11:48 | 2014-09-05 11:49 | 2014-09-05 11:50 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-97774 | PV | 5 | Yes | Inverter | 2014-09-03 | 2014-09-05 11:44 | 2014-09-05 11:45 | 2014-09-05 11:46 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-97785 | PV | 6 | Yes | Inverter | 2014-09-03 | 2014-09-05 11:40 | 2014-09-05 11:41 | 2014-09-05 11:41 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-97796 | PV | 6.8 | Yes | Inverter | 2014-09-03 | 2014-09-05 11:25 | 2014-09-05 11:25 | 2014-09-05 11:26 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-97837 | PV | 4 | Yes | Inverter | 2014-09-04 | 2014-09-05 15:14 | 2014-09-05 15:16 | 2014-09-05 15:16 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-97840 | PV | 11 | Yes | Inverter | 2014-09-04 | 2014-09-05 13:45 | 2014-09-05 15:12 |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | Cancelled | Cancelled
CENY-SI | MC-97841 | PV | 11 | Yes | Inverter | 2014-09-04 | 2014-09-05 13:52 | 2014-09-05 15:09 |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | Cancelled | Cancelled
CENY-SI | MC-97842 | PV | 8.4 | Yes | Inverter | 2014-09-04 | 2014-09-05 15:07 | 2014-09-05 15:08 | 2014-09-05 15:09 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | Cancelled | Cancelled
CENY-SI | MC-97847 | PV | 3.9 | Yes | Inverter | 2014-09-04 | 2014-09-05 15:02 | 2014-09-05 15:03 | 2014-09-05 15:03 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-30 | No | Complete | Complete
CENY-SI | MC-97848 | PV | 8 | Yes | Inverter | 2014-09-04 | 2014-09-08 10:07 | 2014-09-08 10:07 | 2014-09-08 10:08 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-97854 | PV | 3.6 | Yes | Inverter | 2014-09-04 | 2014-09-08 10:10 | 2014-09-08 10:11 | 2014-09-08 10:11 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-97860 | PV | 4.2 | Yes | Inverter | 2014-09-04 | 2014-09-08 10:19 | 2014-09-08 10:19 | 2014-09-08 10:20 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-97883 | PV | 7.8 | Yes | Inverter | 2014-09-04 | 2014-09-08 10:16 | 2014-09-08 10:16 | 2014-09-08 10:16 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-97896 | PV | 15.2 | Yes | Inverter | 2014-09-04 | 2014-09-08 10:40 | 2014-09-08 10:41 | 2014-09-08 10:41 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-97898 | PV | 11 | Yes | Inverter | 2014-09-04 | 2014-09-08 10:22 | 2014-09-08 10:23 | 2014-09-08 10:23 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-97927 | PV | 6 | Yes | Inverter | 2014-09-04 | 2014-09-08 10:25 | 2014-09-08 10:26 | 2014-09-08 10:26 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-97948 | PV | 11.8 | Yes | Inverter | 2014-09-04 | 2014-09-08 10:28 | 2014-09-08 10:28 | 2014-09-08 10:29 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-97964 | PV | 11 | Yes | Inverter | 2014-09-04 | 2014-09-08 10:31 | 2014-09-08 10:31 | 2014-09-08 10:32 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-97983 | PV | 5 | Yes | Inverter | 2014-09-04 | 2014-09-08 10:55 | 2014-09-08 10:55 | 2014-09-08 10:55 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-98000 | PV | 15 | Yes | Inverter | 2014-09-04 | 2014-09-08 10:34 | 2014-09-08 10:34 | 2014-09-08 10:35 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-98004 | PV | 4.2 | Yes | Inverter | 2014-09-04 | 2014-09-08 10:37 | 2014-09-08 10:37 | 2014-09-08 10:38 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | Cancelled | Cancelled
CENY-SI | MC-98008 | PV | 9.2 | Yes | Inverter | 2014-09-04 | 2014-09-08 10:46 | 2014-09-08 10:47 | 2014-09-08 10:47 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-98013 | PV | 6.8 | Yes | Inverter | 2014-09-04 | 2014-09-08 10:51 | 2014-09-08 10:51 | 2014-09-08 10:52 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-98080 | PV | 7 | Yes | Inverter | 2014-09-05 | 2014-09-08 15:14 | 2014-09-08 15:14 | 2014-09-08 15:14 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-98095 | PV | 6 | Yes | Inverter | 2014-09-05 | 2014-09-08 15:09 | 2014-09-08 15:10 | 2014-09-08 15:10 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-98105 | PV | 11 | Yes | Inverter | 2014-09-05 | 2014-09-08 15:04 | 2014-09-08 15:04 | 2014-09-08 15:04 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-98123 | PV | 10 | Yes | Inverter | 2014-09-05 | 2014-09-08 15:00 | 2014-09-08 15:00 | 2014-09-08 15:00 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-98124 | PV | 4.2 | Yes | Inverter | 2014-09-05 | 2014-09-08 14:55 | 2014-09-08 14:56 | 2014-09-08 14:56 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-98127 | PV | 6 | Yes | Inverter | 2014-09-05 | 2014-09-08 14:50 | 2014-09-08 14:51 | 2014-09-08 14:52 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-98141 | PV | 7 | Yes | Inverter | 2014-09-05 | 2014-09-08 14:46 | 2014-09-08 14:46 | 2014-09-08 14:47 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-98147 | PV | 13 | Yes | Inverter | 2014-09-05 | 2014-09-08 14:37 | 2014-09-08 14:38 | 2014-09-08 14:38 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-98153 | PV | 7.6 | Yes | Inverter | 2014-09-05 | 2014-09-08 14:33 | 2014-09-08 14:34 | 2014-09-08 14:34 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-98155 | PV | 3.6 | Yes | Inverter | 2014-09-05 | 2014-09-08 14:29 | 2014-09-08 14:29 | 2014-09-08 14:29 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-98160 | PV | 15 | Yes | Inverter | 2014-09-05 | 2014-09-08 14:20 | 2014-09-08 14:21 | 2014-09-08 14:21 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-98171 | PV | 5 | Yes | Inverter | 2014-09-05 | 2014-09-08 14:14 | 2014-09-08 14:15 | 2014-09-08 14:15 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-98174 | PV | 6 | Yes | Inverter | 2014-09-05 | 2014-09-08 14:09 | 2014-09-08 14:10 | 2014-09-08 14:10 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-98187 | PV | 5 | Yes | Inverter | 2014-09-05 | 2014-09-08 14:00 | 2014-09-08 14:01 | 2014-09-08 14:01 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-98191 | PV | 6 | Yes | Inverter | 2014-09-05 | 2014-09-08 13:55 | 2014-09-08 13:56 | 2014-09-08 13:56 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-98196 | PV | 6 | Yes | Inverter | 2014-09-05 | 2014-09-08 14:05 | 2014-09-08 14:05 | 2014-09-08 14:06 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-98199 | PV | 9 | Yes | Inverter | 2014-09-05 | 2014-09-08 13:51 | 2014-09-08 13:51 | 2014-09-08 13:51 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-98207 | PV | 5.6 | Yes | Inverter | 2014-09-05 | 2014-09-08 13:47 | 2014-09-08 13:47 | 2014-09-08 13:48 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-98212 | PV | 6 | Yes | Inverter | 2014-09-05 | 2014-09-16 11:13 | 2014-09-16 11:13 | 2014-09-16 11:14 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-98223 | PV | 3.2 | Yes | Inverter | 2014-09-05 | 2014-09-08 14:42 | 2014-09-08 14:42 | 2014-09-08 14:43 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-98270 | PV | 6 | Yes | Inverter | 2014-09-05 | 2014-09-09 11:51 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | Cancelled | Cancelled
CENY-SI | MC-98413 | PV | 9 | Yes | Inverter | 2014-09-08 | 2014-09-16 12:05 | 2014-09-16 12:06 | 2014-09-16 12:07 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-98416 | PV | 6 | Yes | Inverter | 2014-09-08 | 2014-09-09 12:21 | 2014-09-16 13:19 | 2014-09-16 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-98448 | PV | 5.2 | Yes | Inverter | 2014-09-08 | 2014-09-16 12:09 | 2014-09-16 12:10 | 2014-09-16 12:10 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-98451 | PV | 2.6 | Yes | Inverter | 2014-09-08 | 2014-09-16 12:13 | 2014-09-16 12:14 | 2014-09-16 12:14 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-98457 | PV | 4.2 | Yes | Inverter | 2014-09-08 | 2014-09-16 13:16 | 2014-09-16 13:17 | 2014-09-16 13:17 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-98494 | PV | 4 | Yes | Inverter | 2014-09-08 | 2014-09-16 13:22 | 2014-09-16 13:23 | 2014-09-16 13:23 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-98508 | PV | 4.4 | Yes | Inverter | 2014-09-08 | 2014-09-11 10:26 | 2014-09-11 10:38 | 2014-09-11 10:39 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-98518 | PV | 2.8 | Yes | Inverter | 2014-09-08 | 2014-09-11 09:26 | 2014-09-11 09:27 | 2014-09-11 09:28 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-98528 | PV | 5 | Yes | Inverter | 2014-09-08 | 2014-09-09 13:31 | 2014-09-09 15:18 | 2014-09-09 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-98536 | PV | 3 | Yes | Inverter | 2014-09-08 | 2014-09-09 15:16 | 2014-09-09 15:16 | 2014-09-09 15:17 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-98574 | PV | 3.8 | Yes | Inverter | 2014-09-08 | 2014-09-09 15:13 | 2014-09-09 15:14 | 2014-09-09 15:14 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | Cancelled | Cancelled
CENY-SI | MC-98592 | PV | 23.9 | Yes | Inverter | 2014-09-08 | 2014-09-09 15:10 | 2014-09-09 15:10 | 2014-09-09 15:11 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending meter exchange
CENY-SI | MC-98606 | PV | 3.6 | Yes | Inverter | 2014-09-08 | 2014-09-09 15:07 | 2014-09-09 15:07 | 2014-09-09 15:07 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-98611 | PV | 3.2 | Yes | Inverter | 2014-09-08 | 2014-09-09 15:04 | 2014-09-09 15:04 | 2014-09-09 15:05 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-98709 | PV | 10 | Yes | Inverter | 2014-09-09 | 2014-09-11 09:07 | 2014-09-11 09:08 | 2014-09-11 09:09 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-98724 | PV | 11 | Yes | Inverter | 2014-09-09 | 2014-09-11 09:03 | 2014-09-11 09:04 | 2014-09-11 09:05 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-10-02 | No | Complete | Complete
CENY-SI | MC-98739 | PV | 6 | Yes | Inverter | 2014-09-09 | 2014-09-11 08:35 | 2014-09-11 08:37 | 2014-09-11 08:37 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-98740 | PV | 4 | Yes | Inverter | 2014-09-09 | 2014-09-11 08:51 | 2014-09-11 08:52 | 2014-09-11 08:52 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-98743 | PV | 7 | Yes | Inverter | 2014-09-09 | 2014-09-11 08:44 | 2014-09-11 08:46 | 2014-09-11 08:46 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-98758 | PV | 19 | Yes | Inverter | 2014-09-09 | 2014-09-16 07:59 | 2014-09-16 08:01 | 2014-09-16 08:02 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-23 | No | Complete | Complete
CENY-SI | MC-98790 | PV | 11 | Yes | Inverter | 2014-09-09 | 2014-09-11 08:20 | 2014-09-11 08:21 | 2014-09-11 08:22 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-30 | No | Complete | Complete
CENY-SI | MC-98800 | PV | 4.2 | Yes | Inverter | 2014-09-09 | 2014-09-11 08:41 | 2014-09-11 08:41 | 2014-09-11 08:42 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending final documents
CENY-SI | MC-98815 | PV | 4 | Yes | Inverter | 2014-09-09 | 2014-09-11 08:14 | 2014-09-11 08:17 | 2014-09-11 08:18 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-98819 | PV | 4.8 | Yes | Inverter | 2014-09-09 | 2014-09-11 08:11 | 2014-09-11 08:12 | 2014-09-11 08:12 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-98846 | PV | 12 | Yes | Inverter | 2014-09-09 | 2014-09-11 08:08 | 2014-09-11 08:08 | 2014-09-11 08:09 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-98847 | PV | 6 | Yes | Inverter | 2014-09-09 | 2014-09-11 07:58 | 2014-09-11 08:04 | 2014-09-11 08:05 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending final documents
CENY-SI | MC-98851 | PV | 5 | Yes | Inverter | 2014-09-09 | 2014-09-11 07:54 | 2014-09-11 07:55 | 2014-09-11 07:55 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-98852 | PV | 8.4 | Yes | Inverter | 2014-09-09 | 2014-09-11 09:20 | 2014-09-11 09:21 | 2014-09-11 09:22 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending final documents
CENY-SI | MC-98927 | PV | 234.9 | Yes | Inverter | 2014-09-10 | 2014-09-11 09:57 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-98928 | PV | 499.7 | Yes | Inverter | 2014-09-10 | 2014-09-11 09:53 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-98963 | PV | 6.6 | Yes | Inverter | 2014-09-10 | 2014-09-11 12:45 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-98983 | PV | 13.2 | Yes | Inverter | 2014-09-10 | 2014-09-11 10:20 | 2014-09-11 10:21 | 2014-09-11 10:22 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | Cancelled | Cancelled
CENY-SI | MC-99024 | PV | 6 | Yes | Inverter | 2014-09-10 | 2014-09-11 12:40 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-99037 | PV | 4 | Yes | Inverter | 2014-09-10 | 2014-09-16 13:27 | 2014-09-16 13:28 | 2014-09-16 13:29 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-99060 | PV | 4 | Yes | Inverter | 2014-09-10 | 2014-09-16 13:31 | 2014-09-16 13:32 | 2014-09-16 13:32 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-99072 | PV | 6 | Yes | Inverter | 2014-09-10 | 2014-09-12 15:14 | 2014-09-16 13:51 | 2014-09-16 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-99074 | PV | 10 | Yes | Inverter | 2014-09-10 | 2014-09-16 13:54 | 2014-09-16 13:55 | 2014-09-16 13:56 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-99133 | PV | 11 | Yes | Inverter | 2014-09-10 | 2014-09-11 12:57 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-99137 | PV | 5 | Yes | Inverter | 2014-09-10 | 2014-09-11 13:09 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-99280 | PV | 11.4 | Yes | Inverter | 2014-09-11 | 2014-09-16 14:34 | 2014-09-16 14:35 | 2014-09-16 14:35 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-99296 | PV | 4.6 | Yes | Inverter | 2014-09-11 | 2014-09-16 14:02 | 2014-09-16 14:04 | 2014-09-16 14:04 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-99298 | PV | 9.7 | Yes | Inverter | 2014-09-11 | 2014-09-12 11:01 | 2014-10-02 09:36 |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | Cancelled | Cancelled
CENY-SI | MC-99352 | PV | 8 | Yes | Inverter | 2014-09-11 | 2014-09-12 14:50 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-99361 | PV | 5.4 | Yes | Inverter | 2014-09-11 | 2014-09-12 14:38 | 2014-10-07 07:44 | 2014-10-07 07:54 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending meter exchange
CENY-SI | MC-99383 | PV | 6 | Yes | Inverter | 2014-09-11 | 2014-09-12 14:33 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-99384 | PV | 6 | Yes | Inverter | 2014-09-11 | 2014-09-12 10:51 | 2014-09-16 14:37 | 2014-09-16 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-99392 | PV | 7.2 | Yes | Inverter | 2014-09-11 | 2014-09-16 14:39 | 2014-09-16 14:41 | 2014-09-16 14:42 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-99400 | PV | 11 | Yes | Inverter | 2014-09-11 | 2014-09-12 14:24 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-99403 | PV | 6 | Yes | Inverter | 2014-09-11 | 2014-09-16 14:58 | 2014-09-16 14:59 | 2014-09-16 14:59 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-99411 | PV | 5 | Yes | Inverter | 2014-09-11 | 2014-09-16 15:09 | 2014-09-16 15:10 | 2014-09-16 15:12 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-99421 | PV | 9.8 | Yes | Inverter | 2014-09-11 | 2014-09-16 15:14 | 2014-09-16 15:15 | 2014-09-16 15:15 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-99430 | PV | 6.8 | Yes | Inverter | 2014-09-11 | 2014-09-16 15:18 | 2014-09-16 15:19 | 2014-09-16 15:20 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-99437 | PV | 6.8 | Yes | Inverter | 2014-09-11 | 2014-09-12 14:56 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-99490 | PV | 12 | Yes | Inverter | 2014-09-12 | 2014-09-15 13:07 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-99546 | PV | 8.4 | Yes | Inverter | 2014-09-12 | 2014-09-15 13:04 | 2014-09-23 12:51 | 2014-09-23 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-99557 | PV | 10 | Yes | Inverter | 2014-09-12 | 2014-09-23 13:03 | 2014-09-23 13:04 | 2014-09-23 13:04 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-99576 | PV | 3.6 | Yes | Inverter | 2014-09-12 | 2014-09-15 12:57 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-99580 | PV | 7.6 | Yes | Inverter | 2014-09-12 | 2014-09-15 12:53 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-99593 | PV | 8.8 | Yes | Inverter | 2014-09-12 | 2014-09-16 09:41 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-99602 | PV | 6.8 | Yes | Inverter | 2014-09-12 | 2014-09-15 12:49 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-99610 | PV | 3 | Yes | Inverter | 2014-09-12 | 2014-09-15 12:42 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-99645 | PV | 6.8 | Yes | Inverter | 2014-09-12 | 2014-09-15 13:20 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-99647 | PV | 3.8 | Yes | Inverter | 2014-09-12 | 2014-09-15 13:17 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-99648 | PV | 6 | Yes | Inverter | 2014-09-12 | 2014-09-15 13:15 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-99651 | PV | 3.8 | Yes | Inverter | 2014-09-12 | 2014-09-15 13:11 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-99652 | PV | 5 | Yes | Inverter | 2014-09-12 | 2014-09-15 13:08 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-99789 | PV | 13.2 | Yes | Inverter | 2014-09-15 | 2014-09-16 09:43 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-99790 | PV | 15 | Yes | Inverter | 2014-09-15 | 2014-09-25 08:59 | 2014-09-25 09:02 | 2014-09-25 09:04 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-99798 | PV | 4.2 | Yes | Inverter | 2014-09-15 | 2014-09-16 10:02 | 2014-09-16 10:03 | 2014-09-16 10:04 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-99802 | PV | 6 | Yes | Inverter | 2014-09-15 | 2014-09-30 10:14 | 2014-09-30 10:15 | 2014-09-30 10:16 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending final documents
CENY-SI | MC-99803 | PV | 7.6 | Yes | Inverter | 2014-09-15 | 2014-09-16 10:52 | 2014-09-16 10:53 | 2014-09-16 10:55 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | Cancelled | Cancelled
CENY-SI | MC-99804 | PV | 6.8 | Yes | Inverter | 2014-09-15 | 2014-09-16 09:56 | 2014-09-16 10:50 | 2014-09-16 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-99806 | PV | 12.6 | Yes | Inverter | 2014-09-15 | 2014-09-16 10:07 | 2014-09-16 10:07 | 2014-09-16 10:08 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-99810 | PV | 6 | Yes | Inverter | 2014-09-15 | 2014-09-16 10:10 | 2014-09-16 10:11 | 2014-09-16 10:12 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-99811 | PV | 8.8 | Yes | Inverter | 2014-09-15 | 2014-09-16 10:16 | 2014-09-16 10:16 | 2014-09-16 10:17 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-99817 | PV | 3.3 | Yes | Inverter | 2014-09-15 | 2014-09-16 10:31 | 2014-09-16 10:31 | 2014-09-16 10:32 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending meter exchange
CENY-SI | MC-99825 | PV | 9 | Yes | Inverter | 2014-09-15 | 2014-09-16 10:36 | 2014-09-16 10:37 | 2014-09-16 10:37 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-99830 | PV | 6.6 | Yes | Inverter | 2014-09-15 | 2014-09-16 10:40 | 2014-09-16 10:42 | 2014-09-16 10:43 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-10-07 | No | Complete | Complete
CENY-SI | MC-99841 | PV | 6.6 | Yes | Inverter | 2014-09-15 | 2014-09-16 10:21 | 2014-09-16 10:44 | 2014-10-07 09:06 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending meter exchange
CENY-SI | MC-99846 | PV | 4.4 | Yes | Inverter | 2014-09-15 | 2014-09-23 11:40 | 2014-09-23 11:40 | 2014-09-23 11:41 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-99849 | PV | 5.4 | Yes | Inverter | 2014-09-15 | 2014-09-23 12:29 | 2014-09-23 12:30 | 2014-09-23 12:31 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | Cancelled | Cancelled
CENY-SI | MC-99852 | PV | 3.4 | Yes | Inverter | 2014-09-15 | 2014-09-23 12:33 | 2014-09-23 12:34 | 2014-09-23 12:35 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-99856 | PV | 6.3 | Yes | Inverter | 2014-09-15 | 2014-09-23 12:49 | 2014-09-23 12:50 | 2014-09-23 12:50 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending meter exchange
CENY-SI | MC-99869 | PV | 3.6 | Yes | Inverter | 2014-09-15 | 2014-09-16 10:33 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-99871 | PV | 10.2 | Yes | Inverter | 2014-09-15 | 2014-09-16 10:37 | 2014-10-07 09:10 | 2014-10-07 09:12 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending meter exchange
CENY-SI | MC-99876 | PV | 9 | Yes | Inverter | 2014-09-15 | 2014-09-16 10:39 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-99890 | PV | 8.4 | Yes | Inverter | 2014-09-15 | 2014-09-16 10:41 | 2014-10-03 07:57 | 2014-10-03 08:03 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending final documents
CENY-SI | MC-99892 | PV | 7.15 | Yes | Inverter | 2014-09-15 | 2014-09-25 11:57 | 2014-09-25 11:57 | 2014-09-25 11:57 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-99897 | PV | 7.8 | Yes | Inverter | 2014-09-15 | 2014-09-16 10:43 | 2014-10-03 07:27 | 2014-10-03 07:32 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-10-09 | No | Complete | Complete
CENY-SI | MC-99908 | PV | 6 | Yes | Inverter | 2014-09-15 | 2014-09-16 10:52 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-99911 | PV | 11.4 | Yes | Inverter | 2014-09-15 | 2014-09-16 10:57 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-99914 | PV | 8.4 | Yes | Inverter | 2014-09-15 | 2014-09-16 11:03 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-99917 | PV | 5.7 | Yes | Inverter | 2014-09-15 | 2014-09-16 11:05 | 2014-10-07 11:43 | 2014-10-07 11:48 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-99918 | PV | 5.7 | Yes | Inverter | 2014-09-15 | 2014-09-16 11:08 | 2014-09-18 08:26 |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | Cancelled | Cancelled
CENY-SI | MC-99924 | PV | 4 | Yes | Inverter | 2014-09-15 | 2014-09-16 11:12 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-99928 | PV | 3.6 | Yes | Inverter | 2014-09-15 | 2014-09-16 11:14 | 2014-09-16 11:23 |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | Cancelled | Cancelled
CENY-SI | MC-99932 | PV | 8.4 | Yes | Inverter | 2014-09-15 | 2014-09-30 09:45 | 2014-09-30 09:46 | 2014-09-30 09:48 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending final documents
CENY-SI | MC-99938 | PV | 13.8 | Yes | Inverter | 2014-09-15 | 2014-09-16 11:19 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-99942 | PV | 8.7 | Yes | Inverter | 2014-09-15 | 2014-09-16 11:28 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-99962 | PV | 3.9 | Yes | Inverter | 2014-09-15 | 2014-09-16 11:40 | 2014-10-07 07:32 | 2014-10-07 07:35 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending meter exchange
CENY-SI | MC-99964 | PV | 6.3 | Yes | Inverter | 2014-09-15 | 2014-09-16 11:41 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-99972 | PV | 6.9 | Yes | Inverter | 2014-09-15 | 2014-09-16 11:43 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-99975 | PV | 4.5 | Yes | Inverter | 2014-09-15 | 2014-09-23 11:28 | 2014-09-23 11:29 | 2014-09-23 11:30 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-SI | MC-99978 | PV | 5.1 | Yes | Inverter | 2014-09-15 | 2014-09-23 11:11 | 2014-09-23 11:12 | 2014-09-23 11:13 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending meter exchange
CENY-SI | MC-99981 | PV | 7.8 | Yes | Inverter | 2014-09-15 | 2014-09-23 11:06 | 2014-09-23 11:07 | 2014-09-23 11:08 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer build
CENY-W | 1334925 | PV | 50 | Yes | Inverter | 2013-07-13 07:48 | 2012-08-22 | 2012-10-15 | 2012-10-25 | 2013-02-27 | 2013-03-13 | 0 | 350 | 0 | 0 | 0 | 2013-03-14 | 2013-03-29 | NO | Complete | Complete
CENY-W | 1350714 | PV | 110 | Yes | Inverter | 2012-10-19 | 2012-10-19 | 2012-11-13 | 2012-11-23 | 2013-11-23 | 2013-12-20 | 0 | 0 | 350 | 0 | 0 | 2014-07-14 | 2014-08-08 | NO | Complete | complete
CENY-W | 1350743 | PV | 200 | Yes | Inverter | 2012-10-19 | 2012-10-19 | 2012-11-13 | 2013-02-13 | 2013-11-23 | 2013-12-20 | 0 | 0 | 0 | 0 | 0 | 2014-07-14 | 2014-08-08 | NO | Complete | complete
CENY-W | 1350749 | PV | 150 | Yes | Inverter | 2012-10-19 | 2012-10-19 | 2012-11-13 | 2013-02-13 | 2013-11-23 | 2013-12-20 | 0 | 0 | 0 | 0 | 0 | 2014-07-14 | 2014-08-08 | NO | Complete | complete
CENY-W | 1350753 | PV | 100 | Yes | Inverter | 2012-10-19 | 2012-10-19 | 2012-11-13 | 2013-02-13 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-08 | NO | Complete | Complete
CENY-W | 1374603 | PV | 51 | Yes | INVERTER | 2013-01-23 | 2013-01-28 | 2013-02-01 | 2013-02-06 |  |  | 0 | 0 | 350 | 0 | 0 |  |  | NO | In Progress | Pending installation, city cert and inspection of system.
CENY-W | 1411849 | PV | 260 | Yes | Inverter | 2013-04-18 | 2013-05-02 | 2013-05-10 | 2013-05-10 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | PEDNING INSPECTION DATE AND FINAL DOCS FROM CUSTOMER
CENY-W | 1428796 | PV | 333 | Yes | Inverter | 2013-06-03 | 2013-06-05 | 2013-06-26 | 2013-07-02 | 2013-06-26 | 2013-07-02 | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | Pending witness test
CENY-W | 1433956 | PV | 3.2 | Yes | Inverter | 2013-06-17 | 2013-06-23 | 2013-07-01 | 2014-01-06 12:22 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | Waiting for customer information
CENY-W | 1437025 | PV | 4.2 | Yes | Inverter | 2013-06-25 | 2013-07-01 | 2013-06-25 | 2013-07-05 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | Cancelled | cancelled
CENY-W | MC-100109 | PV | 6.4 | Yes | Inverter | 2014-09-16 | 2014-09-19 07:36 | 2014-09-19 07:36 | 2014-09-22 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval
CENY-W | MC-100167 | ICE | 75 | NO | Inverter | 2014-09-16 | 2014-09-24 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | All appendicies and documents are not uploaded to case. Sending correspondance to notify.
CENY-W | MC-100197 | PV | 6.2 | Yes | Inverter | 2014-09-16 | 2014-09-17 10:17 | 2014-09-17 10:19 | 2014-09-19 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval
CENY-W | MC-100295 | PV | 3 | Yes | Inverter | 2014-09-17 | 2014-09-17 10:54 | 2014-09-17 10:56 | 2014-09-19 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval.
CENY-W | MC-100386 | PV | 8.2 | Yes | Inverter | 2014-09-17 | 2014-09-18 06:48 | 2014-09-18 06:50 | 2014-09-21 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval.
CENY-W | MC-100417 | PV | 28 | Yes | Inverter | 2014-09-17 | 2014-09-25 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending documents
CENY-W | MC-100453 | PV | 6 | Yes | Inverter | 2014-09-17 | 2014-09-19 08:32 | 2014-09-19 08:33 | 2014-09-22 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Reserved NET mtr
CENY-W | MC-100456 | PV | 6 | Yes | Inverter | 2014-09-17 | 2014-09-18 | 2014-09-18 | 2014-09-18 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Received final docs. Sent mtr reservation
CENY-W | MC-100500 | PV | 3.6 | Yes | Inverter | 2014-09-18 | 2014-09-19 06:49 | 2014-09-19 06:49 | 2014-09-19 06:49 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval.
CENY-W | MC-100542 | PV | 6 | Yes | Inverter | 2014-09-18 | 2014-09-20 | 2014-09-20 | 2014-09-20 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Recieved final docs. Sent mtr res
CENY-W | MC-100594 | PV | 3 | Yes | Inverter | 2014-09-18 | 2014-09-19 07:28 | 2014-09-19 07:32 | 2014-09-30 13:29 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Recieved final docs. Sent Mtr Res
CENY-W | MC-100600 | PV | 6 | Yes | Inverter | 2014-09-18 | 2014-09-19 07:19 | 2014-09-19 07:19 | 2014-09-26 12:06 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Recieved final docs. Sent mtr reservation
CENY-W | MC-100633 | PV | 4 | Yes | Inverter | 2014-09-18 | 2014-09-19 07:28 | 2014-09-19 07:28 | 2014-09-19 07:28 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval
CENY-W | MC-100774 | PV | 5 | Yes | Inverter | 2014-09-19 | 2014-09-19 13:01 | 2014-09-19 13:02 | 2014-09-23 06:21 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval
CENY-W | MC-100803 | PV | 15.2 | Yes | Inverter | 2014-09-19 | 2014-09-23 06:19 | 2014-09-23 06:20 | 2014-09-23 06:21 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval.
CENY-W | MC-100829 | PV | 3 | Yes | Inverter | 2014-09-19 | 2014-09-23 06:37 | 2014-09-23 06:38 | 2014-09-23 06:39 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval
CENY-W | MC-100836 | PV | 3 | Yes | Inverter | 2014-09-19 | 2014-09-23 06:58 | 2014-09-23 06:59 | 2014-09-23 07:00 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | SENT WR
CENY-W | MC-100856 | PV | 5 | Yes | Inverter | 2014-09-19 | 2014-09-23 09:38 | 2014-09-23 09:39 | 2014-09-23 09:39 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Sent line diagram approval. Still require full application- LOA, FORM G, App B
CENY-W | MC-100899 | PV | 4 | Yes | Inverter | 2014-09-19 | 2014-09-20 | 2014-09-20 | 2014-09-20 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | SENT WR
CENY-W | MC-100903 | PV | 5.4 | Yes | Inverter | 2014-09-19 | 2014-09-23 10:24 | 2014-09-23 10:24 | 2014-09-23 10:26 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval.
CENY-W | MC-100908 | PV | 7.6 | Yes | Inverter | 2014-09-19 | 2014-09-23 10:39 | 2014-09-23 10:40 | 2014-09-23 10:41 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval.
CENY-W | MC-100934 | PV | 4.4 | Yes | Inverter | 2014-09-22 | 2014-09-23 10:39 | 2014-09-23 10:39 | 2014-09-23 10:39 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | SENT WR
CENY-W | MC-101149 | PV | 5.8 | Yes | Inverter | 2014-09-22 | 2014-09-23 08:15 | 2014-09-23 08:15 | 2014-09-23 08:16 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | PENDING CIS UPDATE
CENY-W | MC-101195 | PV | 6 | Yes | Inverter | 2014-09-22 | 2014-09-23 08:50 | 2014-09-23 08:50 | 2014-09-23 08:53 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | PENDING CIS UPDATE
CENY-W | MC-101303 | PV | 5 | Yes | Inverter | 2014-09-23 | 2014-09-23 13:17 | 2014-09-23 13:18 | 2014-09-23 13:18 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | installation of 5.23 kw solar roof mount
CENY-W | MC-101369 | PV | 12 | Yes | Inverter | 2014-09-23 | 2014-09-24 09:57 | 2014-09-24 09:57 | 2014-09-24 09:59 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval
CENY-W | MC-101370 | PV | 3 | Yes | Inverter | 2014-09-23 | 2014-10-01 11:00 | 2014-10-01 11:02 | 2014-10-01 11:03 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Received final docs. Sent mtr reservation
CENY-W | MC-101397 | PV | 6 | Yes | Inverter | 2014-09-23 | 2014-09-24 09:57 | 2014-09-24 09:57 | 2014-09-24 09:59 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval.
CENY-W | MC-101399 | PV | 3.8 | Yes | Inverter | 2014-09-23 | 2014-09-24 10:08 | 2014-09-24 10:09 | 2014-09-24 10:09 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval.
CENY-W | MC-101401 | PV | 5 | Yes | Inverter | 2014-09-23 | 2014-09-24 10:18 | 2014-09-24 10:19 | 2014-09-24 10:20 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval.
CENY-W | MC-101402 | PV | 6.4 | Yes | Inverter | 2014-09-23 | 2014-09-24 10:37 | 2014-09-24 10:38 | 2014-09-24 10:38 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | PENDING CIS UPDATE
CENY-W | MC-101407 | PV | 6 | Yes | Inverter | 2014-09-23 | 2014-09-24 10:37 | 2014-09-24 10:38 | 2014-09-24 10:38 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval
CENY-W | MC-101464 | PV | 10 | Yes | Inverter | 2014-09-24 | 2014-09-24 11:07 | 2014-09-24 11:08 | 2014-09-24 11:08 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval.
CENY-W | MC-101491 | PV | 5 | Yes | Inverter | 2014-09-24 | 2014-09-24 11:20 | 2014-09-24 11:22 | 2014-09-24 11:22 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Recieved full app. Sent line approval
CENY-W | MC-101512 | PV | 8 | Yes | Inverter | 2014-09-24 | 2014-09-24 13:26 | 2014-09-24 13:27 | 2014-09-24 13:28 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval
CENY-W | MC-101535 | PV | 3.8 | Yes | Inverter | 2014-09-24 | 2014-09-24 13:37 | 2014-09-24 13:38 | 2014-09-24 13:39 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval
CENY-W | MC-101541 | PV | 10 | Yes | Inverter | 2014-09-24 | 2014-09-24 14:03 | 2014-09-24 14:03 | 2014-09-24 14:04 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval
CENY-W | MC-101545 | PV | 6 | Yes | Inverter | 2014-09-24 | 2014-09-24 14:15 | 2014-09-24 14:17 | 2014-09-24 14:18 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | SENT WR
CENY-W | MC-101578 | PV | 22 | Yes | Inverter | 2014-09-24 | 2014-09-26 07:11 | 2014-09-26 07:08 | 2014-09-26 07:08 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval
CENY-W | MC-101606 | PV | 12.5 | Yes | Inverter | 2014-09-24 | 2014-10-10 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending documents
CENY-W | MC-101609 | PV | 11 | Yes | Inverter | 2014-09-24 | 2014-10-10 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Pending documents
CENY-W | MC-101625 | PV | 5 | Yes | Inverter | 2014-09-24 | 2014-09-26 06:10 | 2014-09-26 06:12 | 2014-09-26 06:12 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval.
CENY-W | MC-101628 | PV | 3.3 | Yes | Inverter | 2014-09-24 | 2014-09-26 06:40 | 2014-09-26 06:41 | 2014-09-26 06:42 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval.
CENY-W | MC-101643 | PV | 17.6 | Yes | Inverter | 2014-09-24 | 2014-09-26 06:52 | 2014-09-26 06:53 | 2014-09-26 06:54 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval
CENY-W | MC-101731 | PV | 3.6 | Yes | Inverter | 2014-09-25 | 2014-09-26 08:22 | 2014-09-26 08:26 | 2014-09-26 08:27 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval
CENY-W | MC-101732 | PV | 7.6 | Yes | Inverter | 2014-09-25 | 2014-09-26 08:47 | 2014-09-26 08:48 | 2014-09-26 08:49 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval
CENY-W | MC-101738 | PV | 3 | Yes | Inverter | 2014-09-25 | 2014-09-26 09:30 | 2014-09-26 09:34 | 2014-09-26 09:34 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval
CENY-W | MC-101746 | PV | 7.4 | Yes | Inverter | 2014-09-25 | 2014-09-26 10:01 | 2014-09-26 10:02 | 2014-09-26 10:03 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval.
CENY-W | MC-101827 | PV | 3.2 | Yes | Inverter | 2014-09-25 | 2014-09-26 10:16 | 2014-09-26 10:17 | 2014-09-26 10:23 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval
CENY-W | MC-101930 | PV | 13.8 | Yes | Inverter | 2014-09-26 | 2014-09-26 10:38 | 2014-09-26 10:39 | 2014-09-26 10:41 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval.
CENY-W | MC-102019 | PV | 9.8 | Yes | Inverter | 2014-09-26 | 2014-09-29 10:12 | 2014-09-29 10:12 | 2014-09-29 10:13 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval.
CENY-W | MC-102043 | PV | 2.6 | Yes | Inverter | 2014-09-26 | 2014-09-29 10:32 | 2014-09-29 10:33 | 2014-09-29 10:35 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval
CENY-W | MC-102246 | PV | 16 | Yes | Inverter | 2014-09-29 | 2014-09-29 14:19 | 2014-09-29 14:19 | 2014-09-29 14:20 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Sent Mtr Res.
CENY-W | MC-102250 | PV | 17.6 | Yes | Inverter | 2014-09-29 | 2014-09-29 14:59 | 2014-09-29 14:59 | 2014-09-29 15:00 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | attached uw cert and sent over to majors
CENY-W | MC-102267 | PV | 6 | Yes | Inverter | 2014-09-29 | 2014-09-29 15:34 | 2014-09-29 15:35 | 2014-09-29 15:35 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval
CENY-W | MC-102278 | PV | 5 | Yes | Inverter | 2014-09-29 | 2014-09-30 07:28 | 2014-09-30 07:33 | 2014-09-30 07:34 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval
CENY-W | MC-102282 | PV | 3 | Yes | Inverter | 2014-09-29 | 2014-09-30 08:17 | 2014-09-30 08:19 | 2014-09-30 08:19 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval
CENY-W | MC-102326 | PV | 3.6 | Yes | Inverter | 2014-09-29 | 2014-09-30 08:41 | 2014-09-30 08:46 | 2014-09-30 08:46 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval.
CENY-W | MC-102439 | PV | 3.6 | Yes | Inverter | 2014-09-30 | 2014-09-30 11:40 | 2014-09-30 11:41 | 2014-09-30 11:41 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Reserved NET MTR
CENY-W | MC-102497 | PV | 5 | Yes | Inverter | 2014-09-30 | 2014-10-01 | 2014-10-01 | 2014-10-01 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval.
CENY-W | MC-102524 | PV | 17.6 | Yes | Inverter | 2014-09-30 | 2014-10-01 | 2014-10-01 | 2014-10-01 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval.
CENY-W | MC-102537 | PV | 12 | Yes | Inverter | 2014-09-30 | 2014-10-01 | 2014-10-01 | 2014-10-01 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval.
CENY-W | MC-102555 | PV | 6 | Yes | Inverter | 2014-09-30 | 2014-10-01 | 2014-10-01 | 2014-10-01 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval.
CENY-W | MC-18712 | PV | 21.285 | Yes | Inverter | 2013-07-22 | 2013-09-03 | 2013-08-26 | 2013-08-26 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | PEDNING INSPECTION DATE AND FINAL DOCS FROM CUSTOMER
CENY-W | MC-18714 | PV | 21.285 | Yes | Inverter | 2013-07-22 | 2013-09-03 | 2013-08-26 | 2013-08-26 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-18 | NO | Complete | Complete
CENY-W | MC-18941 | FC | 800 | YES | Inverter | 2013-07-24 | 2013-07-24 | 2013-10-18 08:06 | 2014-11-21 11:29 | 2014-01-15 | 2014-01-21 | 0 | 0 | 350 | 0 | 0 |  |  | NO | In Progress | NOT IN DISTRCT
CENY-W | MC-20481 | PV | 9 | Yes | Inverter | 2013-08-12 | 2013-08-12 | 2013-08-12 | 2013-08-12 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | pending customer install
CENY-W | MC-22485 | PV | 10 | Yes | Inverter | 2013-09-03 | 2013-09-03 | 2013-10-08 | 2013-10-08 |  |  | 0 | 0 | 0 | 0 | 0 | 2014-09-17 | 2014-09-25 | NO | COMPLETE | COMPLETE
CENY-W | MC-22490 | PV | 5 | Yes | Inverter | 2013-09-03 | 2013-09-03 | 2013-10-08 | 2013-10-08 |  |  | 0 | 0 | 0 | 0 | 0 | 2014-03-14 | 2014-09-08 | NO | Complete | COMPLETE
CENY-W | MC-22762 | PV | 2.5 | Yes | Inverter | 2013-09-06 | 2013-09-06 | 2013-12-31 09:35 | 2013-12-31 09:37 |  |  | 0 | 0 | 0 | 0 | 0 | 2014-02-12 |  | NO | In Progress | Pending customer electrical certificate submission
CENY-W | MC-23298 | PV | 5.8 | Yes | Inverter | 2013-09-12 | 2013-09-13 | 2013-09-24 | 2013-09-24 |  |  | 0 | 0 | 0 | 0 | 0 | 2014-07-01 | 2014-09-05 | NO | Complete | COMPLETE
CENY-W | MC-33055 | PV | 19.8 | Yes | Inverter | 2013-09-25 | 2013-09-25 | 2013-10-15 12:24 | 2013-12-20 09:25 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | PENDING CUSTOMER
CENY-W | MC-34056 | PV | 5 | Yes | Inverter | 2013-10-02 17:05 | 2013-11-18 08:46 | 2013-11-07 | 2013-11-07 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | PENDING CUSTOMER
CENY-W | MC-35000 | PV | 50 | Yes | Inverter | 2013-10-09 | 2013-10-25 | 2013-01-13 | 2013-01-13 | 2013-01-20 | 2013-01-20 | 0 | 0 | 0 | 0 | 0 | 2014-10-10 | 2014-10-10 | NO | Complete | Complete
CENY-W | MC-38792 | PV | 50 | Yes | Inverter | 2013-11-06 18:09 | 2013-12-06 08:09 | 2013-12-06 | 2013-12-06 | 2013-12-05 | 2013-12-06 | 0 | 0 | 0 | 350 | 0 | 2014-07-03 | 2014-09-04 | NO | Complete | Pending CIS Validation
CENY-W | MC-38794 | PV | 100 | Yes | Inverter | 2013-11-06 | 2013-11-11 | 2013-12-15 | 2013-12-15 | 2014-01-08 | 2014-02-11 | 0 | 0 | 350 | 0 | 0 |  |  | NO | In Progress | Pending customer install - failed inspection
CENY-W | MC-38800 | PV | 192 | Yes | Inverter | 2013-11-06 18:33 | 2013-12-06 11:17 | 2013-11-19 | 2013-11-19 | 2013-12-02 | 2013-12-02 | 0 | 0 | 0 | 350 | 0 | 2014-09-04 | 2014-09-04 | NO | Complete | Complete
CENY-W | MC-38801 | PV | 100 | Yes | Inverter | 2013-11-06 18:37 | 2013-12-06 13:48 | 2013-12-06 | 2013-12-06 | 2013-12-10 | 2014-01-08 | 0 | 0 | 350 | 0 | 0 |  |  | NO | In Progress | pending customer install
CENY-W | MC-45735 | PV | 4.8 | Yes | Inverter | 2013-11-11 09:54 | 2013-11-19 13:50 | 2013-11-11 | 2013-11-11 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | Cancelled | CANCELED by customer
CENY-W | MC-45783 | PV | 5.3 | Yes | Inverter | 2013-11-11 12:49 | 2013-12-24 07:32 | 2013-11-11 | 2013-11-11 |  |  | 0 | 0 | 0 | 0 | 0 | 2014-08-14 | 2014-08-04 | NO | Complete | Complete
CENY-W | MC-46162 | PV | 6 | Yes | Inverter | 2013-11-12 17:15 | 2013-12-11 09:01 | 2013-12-02 | 2013-12-02 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | pending customer install
CENY-W | MC-46181 | PV | 5 | Yes | Inverter | 2013-11-12 18:46 | 2013-12-11 09:32 | 2013-12-02 | 2013-12-02 |  |  | 0 | 0 | 0 | 0 | 0 | 2014-09-08 | 2014-09-08 | NO | Complete | Complete
CENY-W | MC-47301 | PV | 100 | Yes | Inverter | 2013-11-15 | 2014-01-08 | 2014-01-08 | 2014-01-08 | 2013-01-24 | 2013-01-27 | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | Pending customer install - failed inspection
CENY-W | MC-47303 | PV | 50 | Yes | Inverter | 2013-11-15 | 2014-01-08 | 2014-01-09 | 2014-01-09 | 2014-01-09 | 2013-01-27 | 0 | 0 | 0 | 0 | 0 | 2014-08-14 | 2014-08-14 | NO | Complete | Complete
CENY-W | MC-48189 | PV | 42 | Yes | Inverter | 2013-11-20 15:14 | 2013-12-23 09:30 | 2013-12-23 09:41 | 2013-12-23 09:42 |  |  | 0 | 0 | 0 | 0 | 0 | 2014-09-09 | 2014-09-18 | NO | Complete | COMPLETE
CENY-W | MC-50047 | PV | 3.6 | Yes | Inverter | 2013-12-02 16:53 | 2013-12-04 10:27 | 2013-12-04 | 2013-12-04 |  |  | 0 | 0 | 0 | 0 | 0 | 2014-09-23 | 2014-09-23 | NO | Complete | Complete
CENY-W | MC-50471 | PV | 3.6 | Yes | Inverter | 2013-12-04 | 2013-12-05 | 2013-12-06 | 2013-12-06 |  |  | 0 | 0 | 0 | 0 | 0 | 2014-09-24 | 2014-09-30 | NO | Complete | Complete
CENY-W | MC-52776 | PV | 72 | Yes | Inverter | 2013-12-13 | 2014-01-08 | 2014-01-09 | 2014-01-09 | 2013-01-23 | 2013-01-27 | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | Pending customer install
CENY-W | MC-52821 | PV | 500 | Yes | Inverter | 2013-12-13 | 2013-12-15 | 2014-01-02 | 2014-01-02 | 2014-01-03 | 2014-01-16 | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | PENDING CUSTOMER INSTALLATION
CENY-W | MC-52822 | PV | 108 | Yes | Inverter | 2013-12-13 | 2014-01-08 | 2014-01-09 | 2014-01-09 | 2013-01-23 | 2013-01-27 | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | Pending customer install
CENY-W | MC-52824 | PV | 72 | Yes | Inverter | 2013-12-13 | 2014-01-08 | 2014-01-09 | 2014-01-09 | 2013-01-23 | 2013-01-27 | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | Pending customer install
CENY-W | MC-52825 | PV | 96 | Yes | Inverter | 2013-12-13 | 2014-01-08 | 2014-01-09 | 2014-01-09 | 2013-01-23 | 2013-01-27 | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | Pending customer install
CENY-W | MC-52848 | FC | 1250 | yes | Inverter | 2013-12-13 | 2013-12-15 |  |  |  |  | 0 | 0 | 350 | 0 | 0 |  |  | NO | In Progress | NOT IN DISTRCT
CENY-W | MC-52993 | PV | 4.25 | Yes | Inverter | 2013-12-16 07:10 | 2014-01-02 12:49 | 2013-12-18 | 2013-12-18 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | pending customer install
CENY-W | MC-53197 | PV | 6 | Yes | Inverter | 2013-12-16 17:30 | 2014-01-02 13:07 | 2013-12-18 | 2013-12-18 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | pending customer install
CENY-W | MC-53456 | PV | 6 | Yes | Inverter | 2013-12-17 16:47 | 2014-01-02 13:26 | 2013-12-24 | 2013-12-24 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | pending customer install
CENY-W | MC-55136 | PV | 4 | Yes | Inverter | 2013-12-27 11:42 | 2014-01-02 14:34 | 2013-12-31 | 2013-12-31 |  |  | 0 | 0 | 0 | 0 | 0 | 2014-05-19 | 2014-05-19 | NO | Complete | Complete
CENY-W | MC-55158 | PV | 7 | Yes | Inverter | 2013-12-27 13:23 | 2014-01-02 14:44 | 2013-12-31 | 2013-12-31 |  |  | 0 | 0 | 0 | 0 | 0 | 2014-09-08 | 2014-09-08 | NO | Complete | Complete
CENY-W | MC-55625 | PV | 3 | Yes | Inverter | 2014-01-03 11:15 | 2014-01-06 08:37 | 2014-01-06 08:38 | 2014-01-06 08:38 |  |  | 0 | 0 | 0 | 0 | 0 | 2014-09-23 | 2014-09-23 | NO | Complete | Complete
CENY-W | MC-55634 | PV | 8.8 | Yes | Inverter | 2014-01-03 11:09 | 2014-01-08 09:06 | 2014-01-08 09:06 | 2014-01-08 09:07 |  |  | 0 | 0 | 0 | 0 | 0 | 2014-09-23 | 2014-09-23 | NO | Complete | Complete
CENY-W | MC-56874 | PV | 40 | Yes | Inverter | 2014-01-13 07:16 | 2014-01-27 12:11 | 2014-01-27 12:14 | 2014-01-13 | 2014-01-27 12:14 | 2014-01-27 12:14 | 0 | 0 | 0 | 0 | 0 | 2014-09-08 | 2014-09-08 | NO | Complete | Complete
CENY-W | MC-57500 | PV | 10 | Yes | Inverter | 2014-01-24 11:59 | 2014-01-24 13:00 | 2014-01-24 13:01 | 2014-01-24 13:02 |  |  | 0 | 0 | 0 | 0 | 0 | 2014-09-08 | 2014-09-08 | NO | Complete | Complete
CENY-W | MC-58133 | PV | 5.4 | Yes | Inverter | 2014-01-21 07:40 | 2014-02-12 09:36 | 2014-02-12 09:37 | 2014-02-12 09:40 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | pending customer install
CENY-W | MC-58362 | PV | 3.8 | Yes | Inverter | 2014-01-21 08:09 | 2014-01-21 09:50 | 2014-01-21 09:51 | 2014-01-21 09:52 |  |  | 0 | 0 | 0 | 0 | 0 | 2014-06-25 | 2014-06-27 | NO | Complete | Complete
CENY-W | MC-58494 | PV | 6 | Yes | Inverter | 2014-01-21 08:07 | 2014-02-17 13:09 | 2014-02-17 13:11 | 2014-02-17 13:12 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | Cancelled | CANCELED by customer
CENY-W | MC-59996 | PV | 6 | Yes | Inverter | 2014-01-30 07:21 | 2014-02-13 10:09 | 2014-02-13 10:11 | 2014-02-13 10:13 |  |  | 0 | 0 | 0 | 0 | 0 | 2014-07-22 | 2014-08-01 | NO | Complete | Complete
CENY-W | MC-60302 | PV | 7 | Yes | Inverter | 2014-02-03 07:48 | 2014-02-13 10:42 | 2014-02-13 10:44 | 2014-02-13 10:46 |  |  | 0 | 0 | 0 | 0 | 0 | 2014-08-25 | 2014-09-23 | NO | Complete | Complete
CENY-W | MC-61393 | PV | 5 | Yes | Inverter | 2014-02-10 07:26 | 2014-02-10 | 2014-02-10 | 2014-02-10 |  |  | 0 | 0 | 0 | 0 | 0 | 2014-07-30 | 2014-07-30 | NO | COMPLETE | COMPLETE
CENY-W | MC-61960 | PV | 7.8 | Yes | Inverter | 2014-02-12 07:55 | 2014-02-13 14:41 | 2014-02-13 14:43 | 2014-02-13 14:46 |  |  | 0 | 0 | 0 | 0 | 0 | 2014-07-31 | 2014-08-27 | NO | Complete | COMPLETE
CENY-W | MC-62463 | PV | 7 | Yes | Inverter | 2014-02-18 07:19 | 2014-03-05 10:37 | 2014-03-05 11:14 | 2014-03-12 10:45 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | Cancelled | CANCELED by customer
CENY-W | MC-62819 | PV | 7.8 | Yes | Inverter | 2014-02-19 07:31 | 2014-02-24 | 2014-02-26 | 2014-02-26 |  |  | 0 | 0 | 0 | 0 | 0 | 2014-08-05 | 2014-08-14 | NO | COMPLETE | COMPLETE
CENY-W | MC-62933 | PV | 85 | Yes | Inverter | 2014-02-19 08:58 | 2014-03-14 09:55 | 2014-03-14 10:09 | 2014-03-14 10:11 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | PENDING CUSTOMER
CENY-W | MC-62944 | PV | 30 | Yes | Inverter | 2014-02-19 08:29 | 2014-02-19 | 2014-02-19 | 2014-02-19 | 2014-04-03 | 2014-07-24 | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | JOB ON HOLD UNTIL CUSTOMER MAKES REPAIRS TO ROOF
CENY-W | MC-63024 | PV | 5.59 | Yes | Inverter | 2014-02-20 08:58 | 2014-03-11 16:16 | 2014-03-12 07:19 | 2014-03-12 07:20 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | PENDING FINAL DOCUMENTS AND METER SET
CENY-W | MC-63034 | PV | 27 | Yes | Inverter | 2014-02-20 08:48 | 2014-03-03 08:11 | 2014-03-03 08:14 | 2014-03-03 08:15 | 2014-02-28 | 2014-03-03 | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | Pending-PreOPTst
CENY-W | MC-63308 | PV | 3 | Yes | Inverter | 2014-02-21 08:48 | 2014-03-12 07:33 | 2014-03-12 07:38 | 2014-03-12 08:07 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | pending customer install
CENY-W | MC-63729 | PV | 7.2 | Yes | Inverter | 2014-02-24 15:10 | 2014-02-25 10:19 | 2014-02-25 11:01 | 2014-02-25 11:04 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | Pending customer completion of install
CENY-W | MC-63868 | PV | 9.2 | Yes | Inverter | 2014-02-26 07:47 | 2014-03-04 13:56 | 2014-03-04 14:03 | 2014-03-04 14:04 |  |  | 0 | 0 | 0 | 0 | 0 | 2014-08-06 | 2014-08-07 | NO | Complete | COMPLETE
CENY-W | MC-64084 | PV | 3 | Yes | Inverter | 2014-02-27 08:16 | 2014-03-06 | 2014-08-28 12:37 | 2014-08-28 12:38 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-10-14 | NO | Complete | Complete
CENY-W | MC-64130 | PV | 13.4 | Yes | Inverter | 2014-02-27 07:44 | 2014-03-06 14:53 | 2014-03-06 15:07 | 2014-03-06 15:08 |  |  | 0 | 0 | 0 | 0 | 0 | 2014-08-21 | 2014-09-29 | NO | COMPLETE | COMPLETE
CENY-W | MC-64147 | PV | 9 | Yes | Inverter | 2014-02-27 08:52 | 2014-03-06 13:18 | 2014-03-06 13:24 | 2014-03-06 13:26 |  |  | 0 | 0 | 0 | 0 | 0 | 2014-07-15 | 2014-08-19 | NO | Complete | COMPLETE
CENY-W | MC-64202 | PV | 6 | Yes | Inverter | 2014-02-27 07:31 | 2014-03-25 11:00 | 2014-03-25 11:13 | 2014-03-25 11:16 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-04 | NO | Complete | Pending verification testing
CENY-W | MC-64847 | PV | 4 | Yes | Inverter | 2014-03-04 07:45 | 2014-03-06 15:32 | 2014-03-06 15:34 | 2014-03-06 15:34 |  |  | 0 | 0 | 0 | 0 | 0 | 2014-07-17 | 2014-07-17 | NO | Complete | Complete
CENY-W | MC-64997 | PV | 60 | Yes | Inverter | 2014-03-05 08:18 | 2014-03-31 11:17 | 2014-03-31 11:30 | 2014-03-31 11:31 | 2014-03-28 | 2014-03-31 | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | Pending-PreOPTst
CENY-W | MC-65000 | PV | 80 | Yes | Inverter | 2014-03-05 08:22 | 2014-03-06 | 2014-03-06 | 2014-03-12 | 2014-03-28 | 2014-03-31 | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | Pending-PreOPTst
CENY-W | MC-65046 | PV | 6 | Yes | Inverter | 2014-03-05 08:11 | 2014-03-07 10:16 | 2014-03-07 10:18 | 2014-03-07 10:19 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | Cancelled | CANCELED by customer
CENY-W | MC-65317 | PV | 8.8 | Yes | Inverter | 2014-03-06 12:56 | 2014-03-12 08:11 | 2014-03-12 08:13 | 2014-03-12 08:14 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | pending customer install
CENY-W | MC-65722 | PV | 500 | Yes | Inverter | 2014-03-09 20:34 | 2014-03-09 | 2014-04-10 | 2014-04-11 | 2014-04-11 | 2014-04-24 | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | DE APPROVED- PENDIING CUSTOMER INSTALLATION
CENY-W | MC-65813 | PV | 3.8 | Yes | Inverter | 2014-03-10 14:22 | 2014-03-14 15:14 | 2014-03-14 15:17 | 2014-03-28 |  |  | 0 | 0 | 0 | 0 | 0 | 2014-07-17 | 2014-07-17 | NO | Complete | Complete
CENY-W | MC-66106 | PV | 6 | Yes | Inverter | 2014-03-12 08:24 | 2014-03-12 11:29 | 2014-03-12 11:31 | 2014-03-12 11:36 |  |  | 0 | 0 | 0 | 0 | 0 | 2014-08-16 | 2014-09-26 | NO | Complete | Complete
CENY-W | MC-66137 | PV | 9.3 | Yes | Inverter | 2014-03-12 07:37 | 2014-03-19 13:32 | 2014-03-19 13:35 | 2014-03-19 13:37 |  |  | 0 | 0 | 0 | 0 | 0 | 2014-08-16 | 2014-09-26 | NO | Complete | Complete
CENY-W | MC-66363 | FC | 210 | YES | Inverter | 2014-03-17 09:54 | 2014-03-24 |  |  |  |  | 0 | 0 | 350 | 0 | 0 |  |  | NO | In Progress | Pending-CUST APPLICATION DOCUMENTS
CENY-W | MC-67193 | PV | 4.6 | YES | Inverter | 2014-03-17 17:21 | 2014-03-24 | 2014-06-26 09:56 | 2014-06-26 09:56 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | in progress | in progress
CENY-W | MC-67592 | PV | 480 | Yes | Inverter | 2014-03-19 12:03 | 2014-03-26 | 2014-05-23 12:11 | 2014-06-16 | 2014-06-16 | 2014-06-16 | 350 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | in progress
CENY-W | MC-67847 | PV | 14 | Yes | Inverter | 2014-03-21 07:27 | 2014-03-28 | 2014-03-21 | 2014-03-24 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | Pending-PSD
CENY-W | MC-68264 | PV | 6.5 | Yes | Inverter | 2014-03-24 08:24 | 2014-03-31 | 2014-06-12 14:43 | 2014-06-12 14:44 |  |  | 0 | 0 | 0 | 0 | 0 | 2014-06-20 | 2014-06-20 | NO | COMPLETE | COMPLETE
CENY-W | MC-68334 | PV | 6.6 | YES | Inverter | 2014-03-24 10:08 | 2014-03-31 | 2014-04-11 14:52 | 2014-04-11 14:53 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-04 | NO | Complete | Complete
CENY-W | MC-68443 | PV | 4.2 | YES | Inverter | 2014-03-24 15:01 | 2014-03-31 | 2014-07-01 11:17 | 2014-07-01 11:17 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | in progress
CENY-W | MC-68472 | PV | 6 | YES | Inverter | 2014-03-24 16:11 | 2014-03-31 | 2014-04-16 08:37 | 2014-04-16 08:38 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | in progress
CENY-W | MC-68652 | PV | 4 | Yes | Inverter | 2014-03-26 15:03 | 2014-04-02 | 2014-06-06 10:07 | 2014-06-06 10:09 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-12 | NO | Complete | Pending-PSD
CENY-W | MC-68801 | PV | 5 | YES | Inverter | 2014-03-25 21:12 | 2014-04-01 | 2014-07-08 11:57 | 2014-07-08 11:57 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-16 | NO | Complete | Complete
CENY-W | MC-68865 | PV | 6 | Yes | Inverter | 2014-03-26 09:33 | 2014-04-02 | 2014-04-09 | 2014-04-18 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | pending customer install
CENY-W | MC-68924 | PV | 4 | YES | Inverter | 2014-03-26 12:53 | 2014-04-02 | 2014-04-28 | 2014-04-28 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | in progress
CENY-W | MC-69291 | FC | 262.5 | YES | Inverter | 2014-03-28 17:25 | 2014-04-04 | 2014-04-29 12:20 | 2014-03-31 |  |  | 0 | 0 | 350 | 0 | 0 |  | 2014-09-11 | NO | Complete | Pending Application Documents
CENY-W | MC-69479 | PV | 14.5 | YES | Inverter | 2014-03-28 20:09 | 2014-04-04 | 2014-06-30 13:39 | 2014-06-30 15:03 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-18 | NO | Complete | Complete
CENY-W | MC-69573 | PV | 7 | YES | Inverter | 2014-03-30 16:59 | 2014-04-06 | 2014-04-15 15:22 | 2014-04-15 15:25 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | in progress
CENY-W | MC-69576 | PV | 4.8 | Yes | Inverter | 2014-03-30 17:34 | 2014-04-06 | 2014-07-16 | 2014-07-16 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | in progress
CENY-W | MC-69747 | PV | 4.8 | YES | Inverter | 2014-03-31 15:56 | 2014-04-07 | 2014-05-14 09:02 | 2014-05-14 09:04 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-25 | NO | Complete | Complete
CENY-W | MC-69749 | PV | 2.2 | YES | Inverter | 2014-03-31 16:05 | 2014-04-07 | 2014-05-14 10:26 | 2014-05-14 10:27 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | in progress
CENY-W | MC-70439 | PV | 5 | YES | Inverter | 2014-04-03 | 2014-04-08 12:32 | 2014-04-08 12:38 | 2014-04-08 12:41 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | PENDING CUSTOMER/CONTRACTOR
CENY-W | MC-70713 | PV | 3.8 | Yes | Inverter | 2014-04-04 | 2014-04-11 12:46 | 2014-04-11 12:54 | 2014-04-11 12:55 |  |  | 0 | 0 | 0 | 0 | 0 | 2014-07-22 | 2014-07-23 | NO | Complete | complete
CENY-W | MC-70720 | PV | 24 | Yes | Inverter | 2014-04-04 | 2014-04-11 13:34 | 2014-04-11 13:36 | 2014-04-11 13:44 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | Pending verification testing
CENY-W | MC-70731 | PV | 3 | Yes | Inverter | 2014-04-04 | 2014-04-09 08:24 | 2014-04-09 08:40 | 2014-04-09 08:41 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | Pending verification testing
CENY-W | MC-71278 | PV | 120 | Yes | RELAY | 2014-04-08 | 2014-04-21 14:09 | 2014-04-21 14:13 | 2014-04-21 14:14 |  |  | 0 | 0 | 350 | 0 | 0 |  |  | NO | In Progress | Pending verification testing
CENY-W | MC-71468 | PV | 7.2 | Yes | Inverter | 2014-04-09 | 2014-04-14 14:46 | 2014-04-14 14:51 | 2014-04-14 14:53 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | pending customer install
CENY-W | MC-71520 | PV | 5 | Yes | Inverter | 2014-04-09 | 2014-04-16 10:32 | 2014-04-16 10:37 | 2014-04-16 10:46 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | Pending verification testing
CENY-W | MC-71900 | PV | 7.6 | Yes | Inverter | 2014-04-11 | 2014-04-16 14:10 | 2014-04-16 14:15 | 2014-04-16 14:17 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | Pending Final documents
CENY-W | MC-71940 | PV | 9.8 | Yes | Inverter | 2014-04-11 | 2014-04-11 | 2014-04-11 | 2014-04-16 |  |  | 0 | 0 | 0 | 0 | 0 | 2014-09-18 | 2014-09-24 | NO | Complete | complete
CENY-W | MC-72286 | PV | 12 | Yes | Inverter | 2014-04-14 | 2014-04-17 09:23 | 2014-04-17 09:35 | 2014-04-17 09:54 |  |  | 0 | 0 | 0 | 0 | 0 | 2014-06-27 | 2014-08-21 | NO | Complete | complete
CENY-W | MC-72323 | PV | 17.6 | Yes | Inverter | 2014-04-14 | 2014-04-17 09:03 | 2014-04-17 09:05 | 2014-04-17 09:06 |  |  | 0 | 0 | 0 | 0 | 0 | 2014-07-16 | 2014-07-23 | NO | Complete | complete
CENY-W | MC-72397 | PV | 5 | Yes | Inverter | 2014-04-14 | 2014-04-17 10:27 | 2014-04-17 10:32 | 2014-04-17 10:38 |  |  | 0 | 0 | 0 | 0 | 0 | 2014-09-30 | 2014-10-01 | NO | Complete | complete
CENY-W | MC-72400 | PV | 11 | Yes | Inverter | 2014-04-14 | 2014-04-15 | 2014-04-15 | 2014-04-15 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | Pending Final documents
CENY-W | MC-72411 | PV | 7 | Yes | Inverter | 2014-04-14 | 2014-04-15 | 2014-04-15 | 2014-04-15 |  |  | 0 | 0 | 0 | 0 | 0 | 2014-09-24 | 2014-09-25 | NO | Complete | complete
CENY-W | MC-72416 | PV | 5.16 | Yes | Inverter | 2014-04-14 | 2014-04-15 | 2014-04-15 | 2014-04-15 |  |  | 0 | 0 | 0 | 0 | 0 | 2014-08-15 | 2014-08-20 | NO | Complete | complete
CENY-W | MC-72675 | PV | 3.6 | Yes | Inverter | 2014-04-15 | 2014-04-16 | 2014-04-16 | 2014-04-16 |  |  | 0 | 0 | 0 | 0 | 0 | 2014-10-07 | 2014-10-07 | NO | Complete | complete
CENY-W | MC-73143 | PV | 4.6 | Yes | Inverter | 2014-04-18 | 2014-06-24 11:36 | 2014-06-24 11:37 | 2014-06-24 11:37 |  |  | 0 | 0 | 0 | 0 | 0 | 2014-07-03 | 2014-08-22 | NO | Complete | complete
CENY-W | MC-73254 | PV | 6 | Yes | Inverter | 2014-04-18 | 2014-04-21 | 2014-06-25 10:38 | 2014-04-22 |  |  | 0 | 0 | 0 | 0 | 0 | 2014-07-21 | 2014-09-11 | NO | Complete | complete
CENY-W | MC-73259 | PV | 6 | Yes | Inverter | 2014-04-18 | 2014-07-03 07:27 | 2014-07-03 07:30 | 2014-07-03 07:31 |  |  | 0 | 0 | 0 | 0 | 0 | 2014-08-28 | 2014-09-02 | NO | Complete | complete
CENY-W | MC-73326 | PV | 17.6 | Yes | Inverter | 2014-04-21 | 2014-07-02 10:11 | 2014-07-02 10:13 | 2014-07-02 10:13 |  |  | 0 | 0 | 0 | 0 | 0 | 2014-07-29 | 2014-08-18 | NO | Complete | complete
CENY-W | MC-73329 | PV | 3.8 | Yes | Inverter | 2014-04-21 | 2014-04-22 | 2014-06-24 14:46 | 2014-06-24 14:47 |  |  | 0 | 0 | 0 | 0 | 0 | 2014-06-21 | 2014-08-20 | NO | Complete | CMPS glitch
CENY-W | MC-73330 | PV | 5 | Yes | Inverter | 2014-04-21 | 2014-06-10 08:20 | 2014-07-02 09:12 | 2014-07-02 09:13 |  |  | 0 | 0 | 0 | 0 | 0 | 2014-09-05 | 2014-09-05 | NO | Complete | complete
CENY-W | MC-73333 | PV | 13.6 | Yes | Inverter | 2014-04-21 | 2014-07-01 13:55 | 2014-07-01 13:57 | 2014-07-01 13:58 |  |  | 0 | 0 | 0 | 0 | 0 | 2014-07-29 | 2014-08-18 | NO | Complete | complete
CENY-W | MC-73853 | PV | 5 | Yes | Inverter | 2014-04-23 | 2014-07-02 08:08 | 2014-07-02 08:09 | 2014-07-02 08:10 |  |  | 0 | 0 | 0 | 0 | 0 | 2014-07-25 | 2014-07-25 | NO | Complete | complete
CENY-W | MC-73892 | PV | 6 | Yes | Inverter | 2014-04-23 | 2014-07-02 09:48 | 2014-07-02 09:52 | 2014-07-02 09:58 |  |  | 0 | 0 | 0 | 0 | 0 | 2014-07-25 | 2014-07-25 | NO | Complete | complete
CENY-W | MC-74484 | PV | 5 | Yes | Inverter | 2014-04-25 | 2014-05-21 11:06 | 2014-05-21 11:12 | 2014-05-21 11:14 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | Pending customer build
CENY-W | MC-74498 | PV | 6.2 | Yes | Inverter | 2014-04-25 | 2014-05-02 14:20 | 2014-05-02 14:22 | 2014-05-02 14:24 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | Pending verification testing
CENY-W | MC-74511 | PV | 6 | Yes | Inverter | 2014-04-25 | 2014-05-27 07:16 | 2014-05-27 07:17 | 2014-05-27 07:15 |  |  | 0 | 0 | 0 | 0 | 0 | 2014-09-18 | 2014-09-18 | NO | Complete | Complete
CENY-W | MC-74541 | PV | 6 | Yes | Inverter | 2014-04-28 | 2014-05-14 09:40 | 2014-05-14 09:55 | 2014-05-14 10:01 |  |  | 0 | 0 | 0 | 0 | 0 | 2014-09-24 | 2014-09-30 | NO | Complete | complete
CENY-W | MC-74920 | PV | 4.6 | Yes | Inverter | 2014-04-29 | 2014-05-14 15:09 | 2014-05-14 15:11 | 2014-05-14 15:13 |  |  | 0 | 0 | 0 | 0 | 0 | 2014-08-13 | 2014-08-13 | NO | Complete | complete
CENY-W | MC-74991 | PV | 6.6 | Yes | Inverter | 2014-04-29 | 2014-06-16 15:24 | 2014-06-16 15:25 | 2014-06-16 15:27 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | pending customer install
CENY-W | MC-75001 | PV | 7 | Yes | Inverter | 2014-04-29 | 2014-05-22 11:08 | 2014-05-23 15:31 | 2014-05-23 15:32 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | in Progress | Pending custoner install
CENY-W | MC-75153 | PV | 11.2 | Yes | Inverter | 2014-04-29 | 2014-05-19 10:04 | 2014-05-19 10:07 | 2014-05-19 10:02 |  |  | 0 | 0 | 0 | 0 | 0 | 2014-10-09 | 2014-10-10 | NO | Complete | Complete
CENY-W | MC-75350 | PV | 7 | Yes | Inverter | 2014-04-30 | 2014-05-15 07:54 | 2014-05-15 08:29 | 2014-05-15 08:32 |  |  | 0 | 0 | 0 | 0 | 0 | 2014-07-12 | 2014-08-07 | NO | Complete | Completed
CENY-W | MC-75638 | PV | 5 | Yes | Inverter | 2014-05-01 | 2014-05-19 10:26 | 2014-05-19 10:29 | 2014-05-19 10:20 |  |  | 0 | 0 | 0 | 0 | 0 | 2014-09-15 | 2014-09-15 | NO | Complete | Complete
CENY-W | MC-75719 | PV | 7.2 | Yes | Inverter | 2014-05-02 | 2014-05-14 | 2014-05-14 | 2014-06-19 |  |  | 0 | 0 | 0 | 0 | 0 | 2014-08-27 | 2014-08-27 | NO | COMPLETE | COMPLETE
CENY-W | MC-75722 | PV | 343.6 | Yes | Inverter | 2014-05-02 | 2014-05-22 17:01 | 2014-05-23 | 2014-05-23 | 2014-05-24 | 2014-05-27 | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | PENDING CUSTOMER REVISED DRAWING
CENY-W | MC-75741 | PV | 21 | Yes | Inverter | 2014-05-02 | 2014-05-20 10:50 | 2014-05-22 14:27 | 2014-05-22 14:27 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | Pending verification testing
CENY-W | MC-75791 | PV | 5.8 | Yes | Inverter | 2014-05-02 | 2014-05-20 11:21 | 2014-05-20 11:23 | 2014-05-20 11:26 |  |  | 0 | 0 | 0 | 0 | 0 | 2014-09-15 | 2014-09-16 | NO | Complete | COMPLETE
CENY-W | MC-75792 | PV | 3.5 | Yes | Inverter | 2014-05-02 | 2014-06-12 13:54 | 2014-06-12 13:55 | 2014-06-12 13:55 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | pending customer install
CENY-W | MC-75800 | PV | 4.8 | Yes | Inverter | 2014-05-02 | 2014-05-16 09:06 | 2014-05-16 09:12 | 2014-05-16 09:17 |  |  | 0 | 0 | 0 | 0 | 0 | 2014-09-16 | 2014-09-19 | NO | Complete | Completed
CENY-W | MC-75810 | PV | 24.5 | Yes | Inverter | 2014-05-02 | 2014-05-21 07:44 | 2014-05-21 07:47 | 2014-05-21 07:48 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | PENDING CUSTOMER
CENY-W | MC-75913 | PV | 5 | Yes | Inverter | 2014-05-05 | 2014-05-14 08:47 | 2014-05-14 08:49 | 2014-05-14 08:51 |  |  | 0 | 0 | 0 | 0 | 0 | 2014-08-15 | 2014-08-18 | NO | Complete | complete
CENY-W | MC-76129 | PV | 4 | Yes | Inverter | 2014-05-05 | 2014-05-21 08:13 | 2014-05-21 08:15 | 2014-05-21 08:17 |  |  | 0 | 0 | 0 | 0 | 0 | 2014-09-25 | 2014-09-29 | NO | COMPLETE | COMPLETE
CENY-W | MC-76363 | PV | 8 | Yes | Inverter | 2014-05-06 | 2014-05-07 09:34 | 2014-05-07 09:37 | 2014-05-07 09:40 |  |  | 0 | 0 | 0 | 0 | 0 | 2014-09-10 | 2014-09-12 | NO | Complete | COMPLETE
CENY-W | MC-76374 | PV | 7.2 | Yes | Inverter | 2014-05-06 | 2014-05-07 10:46 | 2014-05-07 10:47 | 2014-05-07 10:50 |  |  | 0 | 0 | 0 | 0 | 0 | 2014-07-30 | 2014-08-07 | NO | Complete | COMPLETE
CENY-W | MC-76381 | PV | 6 | Yes | Inverter | 2014-05-06 | 2014-05-13 10:38 | 2014-05-13 11:06 | 2014-05-13 11:08 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | PENDING CUSTOMER/CONTRACTOR
CENY-W | MC-76406 | PV | 7 | Yes | Inverter | 2014-05-06 | 2014-05-07 14:05 | 2014-05-07 14:23 | 2014-05-07 14:25 |  |  | 0 | 0 | 0 | 0 | 0 | 2014-07-25 | 2014-08-07 | NO | COMPLETE | COMPLETE
CENY-W | MC-76433 | PV | 9.6 | Yes | Inverter | 2014-05-06 | 2014-05-19 11:56 | 2014-05-19 11:59 | 2014-05-19 11:51 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | PENDING CUSTOMER/CONTRACTOR
CENY-W | MC-76455 | PV | 4 | Yes | Inverter | 2014-05-06 | 2014-05-13 09:56 | 2014-05-13 09:59 | 2014-05-13 10:04 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | PENDING CUSTOMER/CONTRACTOR
CENY-W | MC-76694 | PV | 15 | Yes | Inverter | 2014-05-07 | 2014-05-09 08:48 | 2014-05-09 09:17 | 2014-05-09 09:21 |  |  | 0 | 0 | 0 | 0 | 0 | 2014-08-20 | 2014-08-20 | NO | Complete | complete
CENY-W | MC-77075 | PV | 8 | Yes | Inverter | 2014-05-09 | 2014-05-15 10:58 | 2014-05-15 11:02 | 2014-05-15 11:04 |  |  | 0 | 0 | 0 | 0 | 0 | 2014-08-20 | 2014-08-20 | NO | Complete | complete
CENY-W | MC-77386 | PV | 3.8 | Yes | Inverter | 2014-05-12 | 2014-05-19 08:17 | 2014-05-19 12:46 | 2014-05-19 12:45 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | PENDING CUSTOMER/CONTRACTOR
CENY-W | MC-77452 | PV | 5 | Yes | Inverter | 2014-05-12 | 2014-05-19 12:13 | 2014-05-19 12:20 | 2014-05-19 12:12 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | PENDING CUSTOMER/CONTRACTOR
CENY-W | MC-77457 | PV | 15.2 | Yes | Inverter | 2014-05-12 | 2014-06-19 | 2014-09-04 | 2014-09-25 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | in progress | pending customer INSTALL
CENY-W | MC-77458 | PV | 5 | Yes | Inverter | 2014-05-12 | 2014-06-19 | 2014-06-19 | 2014-06-19 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | pending customer install
CENY-W | MC-77469 | PV | 18 | Yes | Inverter | 2014-05-12 | 2014-05-16 13:00 | 2014-05-16 13:02 | 2014-05-16 13:03 |  |  | 0 | 0 | 0 | 0 | 0 | 2014-07-01 | 2014-07-30 | NO | Complete | COMPLETE
CENY-W | MC-77483 | PV | 5 | Yes | Inverter | 2014-05-12 | 2014-05-19 07:28 | 2014-05-19 13:06 | 2014-05-19 13:03 |  |  | 0 | 0 | 0 | 0 | 0 | 2014-09-08 | 2014-09-08 | NO | Complete | complete
CENY-W | MC-77770 | PV | 5 | Yes | Inverter | 2014-05-13 | 2014-05-19 08:31 | 2014-05-19 13:20 | 2014-05-19 13:17 |  |  | 0 | 0 | 0 | 0 | 0 | 2014-08-19 | 2014-08-19 | NO | Complete | complete
CENY-W | MC-77828 | PV | 7 | Yes | Inverter | 2014-05-13 | 2014-05-19 08:49 | 2014-05-19 08:58 | 2014-05-19 08:50 |  |  | 0 | 0 | 0 | 0 | 0 | 2014-09-17 | 2014-09-17 | NO | Complete | complete-pending wms close out to progress case to close and validate
CENY-W | MC-77966 | PV | 10 | Yes | Inverter | 2014-05-14 | 2014-05-16 11:20 | 2014-05-16 11:25 | 2014-05-16 11:29 |  |  | 0 | 0 | 0 | 0 | 0 | 2014-08-05 | 2014-08-07 | NO | Complete | COMPLETE
CENY-W | MC-77968 | PV | 6 | Yes | Inverter | 2014-05-14 | 2014-05-16 11:32 | 2014-05-16 11:36 | 2014-05-16 11:38 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | Pending customer installation
CENY-W | MC-77971 | PV | 4 | Yes | Inverter | 2014-05-14 | 2014-05-16 11:40 | 2014-05-16 11:43 | 2014-05-19 11:41 |  |  | 0 | 0 | 0 | 0 | 0 | 2014-09-02 | 2014-09-02 | NO | Complete | complete
CENY-W | MC-78059 | PV | 7.4 | Yes | Inverter | 2014-05-14 | 2014-05-16 15:27 | 2014-05-16 15:32 | 2014-05-16 15:35 |  |  | 0 | 0 | 0 | 0 | 0 | 2014-05-25 | 2014-06-23 | NO | Complete | COMPLETE
CENY-W | MC-78463 | PV | 12 | Yes | Inverter | 2014-05-16 | 2014-05-23 09:02 | 2014-05-23 09:03 | 2014-05-23 09:04 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | PENDING CUSTOMER
CENY-W | MC-78658 | PV | 6 | Yes | Inverter | 2014-05-19 | 2014-06-17 09:55 | 2014-06-17 09:56 | 2014-06-17 09:57 |  |  | 0 | 0 | 0 | 0 | 0 | 2014-07-25 | 2014-07-25 | NO | Complete | Complete
CENY-W | MC-78694 | PV | 6 | Yes | Inverter | 2014-05-19 | 2014-06-17 | 2014-05-19 | 2014-07-24 |  |  | 0 | 0 | 0 | 0 | 0 | 2014-08-27 | 2014-09-19 | NO | Complete | complete
CENY-W | MC-78743 | PV | 11.4 | Yes | Inverter | 2014-05-19 | 2014-05-27 10:58 | 2014-05-27 10:58 | 2014-05-27 10:59 |  |  | 0 | 0 | 0 | 0 | 0 | 2014-09-29 | 2014-10-01 | NO | COMPLETE | COMPLETE
CENY-W | MC-78758 | PV | 15.6 | Yes | Inverter | 2014-05-19 | 2014-05-22 12:01 | 2014-05-22 12:16 | 2014-05-22 12:23 |  |  | 0 | 0 | 0 | 0 | 0 | 2014-08-20 | 2014-08-25 | NO | Complete | Completed
CENY-W | MC-78897 | PV | 7.5 | Yes | Inverter | 2014-05-20 | 2014-05-23 10:16 | 2014-05-23 10:30 | 2014-05-27 13:44 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | in Progress | Pending custoner install
CENY-W | MC-78917 | PV | 9.9 | Yes | Inverter | 2014-05-20 | 2014-05-27 08:49 | 2014-05-22 09:38 | 2014-05-27 08:47 |  |  | 0 | 0 | 0 | 0 | 0 | 2014-10-02 | 2014-10-06 | NO | complete | complete
CENY-W | MC-79014 | PV | 9.8 | Yes | Inverter | 2014-05-20 | 2014-06-03 08:29 | 2014-06-03 08:30 | 2014-06-03 08:30 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | Pending installation, city cert and inspection of system.
CENY-W | MC-79023 | PV | 4.2 | Yes | Inverter | 2014-05-20 | 2014-05-28 07:53 | 2014-05-22 12:15 | 2014-05-22 12:05 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In progress | Pending customer installation
CENY-W | MC-79032 | PV | 4 | Yes | Inverter | 2014-05-20 | 2014-05-28 07:16 | 2014-05-28 07:22 | 2014-05-28 07:13 |  |  | 0 | 0 | 0 | 0 | 0 | 2014-09-17 | 2014-09-17 | NO | Complete | complete
CENY-W | MC-79379 | PV | 6.4 | Yes | Inverter | 2014-05-22 | 2014-05-27 09:12 | 2014-05-27 09:24 | 2014-05-27 09:31 |  |  | 0 | 0 | 0 | 0 | 0 | 2014-07-07 | 2014-08-25 | NO | Complete | Completed
CENY-W | MC-79454 | PV | 3 | Yes | Inverter | 2014-05-22 | 2014-06-02 15:09 | 2014-06-02 15:12 | 2014-06-02 15:12 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | Pending installation, city cert and inspection of system.
CENY-W | MC-79523 | PV | 6 | Yes | Inverter | 2014-05-22 | 2014-05-28 07:41 | 2014-05-28 07:44 | 2014-05-28 07:40 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | Pending customer installation
CENY-W | MC-79741 | PV | 3 | Yes | Inverter | 2014-05-23 | 2014-05-28 09:40 | 2014-05-28 09:41 | 2014-05-28 09:33 |  |  | 0 | 0 | 0 | 0 | 0 | 2014-07-23 | 2014-07-23 | NO | complete | complete
CENY-W | MC-79749 | PV | 3 | Yes | Inverter | 2014-05-23 | 2014-05-28 08:32 | 2014-05-28 08:33 | 2014-05-28 08:30 |  |  | 0 | 0 | 0 | 0 | 0 | 2014-08-29 | 2014-08-29 | NO | complete | complete
CENY-W | MC-80124 | PV | 8 | Yes | Inverter | 2014-05-28 | 2014-05-29 09:33 | 2014-05-29 09:32 | 2014-05-29 09:30 |  |  | 0 | 0 | 0 | 0 | 0 | 2014-09-17 | 2014-09-17 | NO | Complete | complete
CENY-W | MC-80214 | PV | 8 | Yes | Inverter | 2014-05-28 | 2014-06-24 14:04 | 2014-06-24 14:06 | 2014-06-24 14:07 |  |  | 0 | 0 | 0 | 0 | 0 | 2014-07-18 | 2014-07-31 | NO | COMPLETE | COMPLETE
CENY-W | MC-80218 | PV | 14 | Yes | Inverter | 2014-05-28 | 2014-06-24 13:40 | 2014-06-24 13:44 | 2014-06-24 13:44 |  |  | 0 | 0 | 0 | 0 | 0 | 2014-07-18 | 2014-07-31 | NO | COMPLETE | COMPLETE
CENY-W | MC-80252 | PV | 10.4 | Yes | Inverter | 2014-05-28 | 2014-06-11 | 2014-05-28 | 2014-06-11 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | pending customer install
CENY-W | MC-80278 | PV | 7.6 | Yes | Inverter | 2014-05-28 | 2014-05-30 10:16 | 2014-05-30 10:17 | 2014-05-30 10:18 |  |  | 0 | 0 | 0 | 0 | 0 | 2014-08-07 | 2014-08-14 | NO | Complete | COMPLETE
CENY-W | MC-80560 | PV | 5 | Yes | Inverter | 2014-05-29 | 2014-06-03 15:18 | 2014-06-03 15:19 | 2014-06-03 15:20 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | Pedning verification test and contractor's affidavit.
CENY-W | MC-80639 | PV | 5 | Yes | Inverter | 2014-05-29 | 2014-07-01 12:09 | 2014-07-01 12:17 | 2014-07-01 12:26 |  |  | 0 | 0 | 0 | 0 | 0 | 2014-10-07 | 2014-10-22 | NO | COMPLETE | Completed
CENY-W | MC-81011 | PV | 24 | Yes | Inverter | 2014-06-02 | 2014-06-03 06:18 | 2014-06-03 06:19 | 2014-06-03 06:25 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-08 | No | Complete | Complete
CENY-W | MC-81054 | PV | 5.4 | Yes | Inverter | 2014-06-02 | 2014-06-02 14:24 | 2014-06-02 14:25 | 2014-06-02 14:25 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-22 | No | Complete | Pending PV installation
CENY-W | MC-81146 | PV | 6 | Yes | Inverter | 2014-06-02 | 2014-06-03 07:27 | 2014-06-03 07:27 | 2014-06-03 07:28 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-10 | No | Complete | Complete
CENY-W | MC-81299 | PV | 3 | Yes | Inverter | 2014-06-03 | 2014-06-03 12:55 | 2014-06-03 12:56 | 2014-06-03 12:56 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending PV installation
CENY-W | MC-81349 | PV | 3.6 | Yes | Inverter | 2014-06-03 | 2014-06-04 09:23 | 2014-06-04 09:24 | 2014-06-04 09:24 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending PV installation
CENY-W | MC-81375 | PV | 8.8 | Yes | Inverter | 2014-06-03 | 2014-06-04 10:51 | 2014-06-04 10:52 | 2014-06-04 10:52 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending PV installation
CENY-W | MC-81668 | PV | 7 | Yes | Inverter | 2014-06-04 | 2014-06-16 08:34 | 2014-06-16 08:35 | 2014-06-16 08:35 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending PV installation
CENY-W | MC-81921 | PV | 3.2 | Yes | Inverter | 2014-06-05 | 2014-06-06 07:15 | 2014-06-09 09:13 | 2014-06-09 09:13 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending PV installation
CENY-W | MC-81924 | PV | 4 | Yes | Inverter | 2014-06-05 | 2014-06-06 07:37 | 2014-06-09 09:03 | 2014-06-16 06:51 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-16 | No | Complete | Complete
CENY-W | MC-82074 | PV | 8 | Yes | Inverter | 2014-06-06 | 2014-06-09 11:17 | 2014-06-09 11:18 | 2014-06-09 11:18 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending PV installation
CENY-W | MC-82085 | PV | 10 | Yes | Inverter | 2014-06-06 | 2014-06-09 12:59 | 2014-06-09 13:01 | 2014-06-09 13:01 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending PV installation
CENY-W | MC-82124 | PV | 4 | Yes | Inverter | 2014-06-06 | 2014-06-09 13:27 | 2014-06-09 13:28 | 2014-06-09 13:28 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-10-10 | No | Complete | Complete
CENY-W | MC-82334 | PV | 540 | Yes | Inverter | 2014-06-09 | 2014-06-10 | 2014-07-01 | 2014-07-07 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | DE APPROVED- PENDIING CUSTOMER INSTALLATION
CENY-W | MC-82335 | PV | 140 | Yes | Inverter | 2014-06-09 | 2014-06-10 | 2014-07-01 | 2014-07-07 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | DE APPROVED- PENDIING CUSTOMER INSTALLATION
CENY-W | MC-82344 | PV | 400 | Yes | Inverter | 2014-06-09 | 2014-06-10 | 2014-07-01 | 2014-07-07 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | DE APPROVED- PENDIING CUSTOMER INSTALLATION
CENY-W | MC-82387 | PV | 4 | Yes | Inverter | 2014-06-09 | 2014-06-09 14:25 | 2014-06-09 14:26 | 2014-06-09 14:26 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending PV installation
CENY-W | MC-82405 | PV | 6 | Yes | Inverter | 2014-06-09 | 2014-06-10 06:28 | 2014-06-10 06:29 | 2014-06-12 09:58 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending PV installation
CENY-W | MC-82420 | PV | 5 | Yes | Inverter | 2014-06-09 | 2014-06-10 07:01 | 2014-06-10 07:03 | 2014-06-16 06:48 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending PV installation
CENY-W | MC-82422 | PV | 6 | Yes | Inverter | 2014-06-09 | 2014-06-10 07:41 | 2014-06-10 07:43 | 2014-06-10 07:43 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-11 | No | Complete | Complete
CENY-W | MC-82521 | PV | 8.4 | Yes | Inverter | 2014-06-10 | 2014-06-10 09:22 | 2014-06-10 09:23 | 2014-06-10 09:23 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-10-08 | No | Complete | Complete
CENY-W | MC-82549 | PV | 5 | Yes | Inverter | 2014-06-10 | 2014-06-11 06:11 | 2014-06-11 06:12 | 2014-06-11 08:23 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending PV installation
CENY-W | MC-82807 | PV | 5 | Yes | Inverter | 2014-06-11 | 2014-06-11 12:42 | 2014-06-11 12:44 | 2014-06-11 12:50 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-15 | No | Complete | Complete
CENY-W | MC-82869 | PV | 15.8 | Yes | Inverter | 2014-06-11 | 2014-06-12 07:03 | 2014-06-12 07:04 | 2014-06-12 07:04 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending PV installation
CENY-W | MC-83031 | PV | 5 | Yes | Inverter | 2014-06-11 | 2014-06-12 07:58 | 2014-06-12 07:59 | 2014-06-12 07:59 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-30 | No | Complete | Complete
CENY-W | MC-83078 | PV | 50 | Yes | Inverter | 2014-06-12 | 2014-06-30 | 2014-06-19 | 2014-06-19 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | In Progress | pending customer install
CENY-W | MC-83382 | PV | 3.2 | Yes | Inverter | 2014-06-13 | 2014-06-13 12:55 | 2014-06-13 12:55 | 2014-06-13 12:56 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending PV installation
CENY-W | MC-83386 | PV | 6 | Yes | Inverter | 2014-06-13 | 2014-06-16 06:12 | 2014-06-16 06:13 | 2014-06-16 06:19 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-15 | No | Complete | Complete
CENY-W | MC-83734 | PV | 3.8 | Yes | Inverter | 2014-06-16 | 2014-06-17 07:28 | 2014-06-17 07:28 | 2014-06-27 09:31 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-15 | No | Complete | Complete
CENY-W | MC-83744 | PV | 39 | Yes | Inverter | 2014-06-16 | 2014-06-30 | 2014-06-30 | 2014-07-23 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | in progress | in progress
CENY-W | MC-83753 | PV | 22 | Yes | Inverter | 2014-06-16 | 2014-06-17 08:02 | 2014-06-17 08:06 | 2014-06-17 08:06 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-28 | No | Complete | Complete
CENY-W | MC-83758 | PV | 22 | Yes | Inverter | 2014-06-16 | 2014-06-17 09:46 | 2014-06-17 09:47 | 2014-06-17 09:47 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending PV installation
CENY-W | MC-83761 | PV | 5 | Yes | Inverter | 2014-06-16 | 2014-06-17 09:15 | 2014-06-17 09:16 | 2014-06-17 09:23 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending PV installation
CENY-W | MC-83848 | PV | 17.6 | Yes | Inverter | 2014-06-16 | 2014-06-17 10:21 | 2014-06-17 10:22 | 2014-06-17 10:22 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending PV installation
CENY-W | MC-83853 | PV | 3.8 | Yes | Inverter | 2014-06-16 | 2014-06-17 11:26 | 2014-06-17 11:27 | 2014-06-17 11:27 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending PV installation
CENY-W | MC-84010 | PV | 5 | Yes | Inverter | 2014-06-17 | 2014-06-17 13:24 | 2014-06-19 06:46 | 2014-06-19 06:46 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending PV installation
CENY-W | MC-84016 | PV | 13.6 | Yes | Inverter | 2014-06-17 | 2014-06-19 06:36 | 2014-06-19 06:37 | 2014-06-19 06:38 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-09 | No | Complete | Complete
CENY-W | MC-84025 | PV | 3 | Yes | Inverter | 2014-06-17 | 2014-06-19 06:13 | 2014-06-19 06:13 | 2014-06-19 06:13 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-15 | No | Complete | Complete
CENY-W | MC-84033 | PV | 6 | Yes | Inverter | 2014-06-17 | 2014-06-19 07:03 | 2014-06-19 07:04 | 2014-06-19 07:05 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-15 | No | Complete | Complete
CENY-W | MC-84037 | PV | 3 | Yes | Inverter | 2014-06-17 | 2014-06-19 07:27 | 2014-06-19 07:27 | 2014-06-19 07:27 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending PV installation
CENY-W | MC-84042 | PV | 4.8 | Yes | Inverter | 2014-06-17 | 2014-06-19 07:49 | 2014-06-19 07:50 | 2014-06-19 07:50 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending PV installation
CENY-W | MC-84045 | PV | 3 | Yes | Inverter | 2014-06-17 | 2014-06-19 08:51 | 2014-06-19 08:52 | 2014-06-19 13:04 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending PV installation
CENY-W | MC-84054 | PV | 3.8 | Yes | Inverter | 2014-06-17 | 2014-06-19 11:58 | 2014-06-19 11:59 | 2014-06-19 12:07 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-28 | No | Complete | Complete
CENY-W | MC-84060 | PV | 4.4 | Yes | Inverter | 2014-06-17 | 2014-06-19 13:22 | 2014-06-19 13:22 | 2014-06-19 13:23 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-09 | No | Complete | Complete
CENY-W | MC-84106 | PV | 4.8 | Yes | Inverter | 2014-06-17 | 2014-06-20 09:16 | 2014-06-20 09:17 | 2014-06-20 09:17 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-22 | No | Complete | Complete
CENY-W | MC-84301 | PV | 5.8 | Yes | Inverter | 2014-06-18 | 2014-06-20 06:19 | 2014-06-20 06:20 | 2014-06-20 06:20 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending PV installation
CENY-W | MC-84332 | PV | 5.6 | Yes | Inverter | 2014-06-18 | 2014-06-20 06:34 | 2014-06-20 06:35 | 2014-06-20 06:35 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending PV installation
CENY-W | MC-84412 | PV | 11.6 | Yes | Inverter | 2014-06-18 | 2014-06-20 06:51 | 2014-06-20 06:52 | 2014-06-20 06:52 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending PV installation
CENY-W | MC-84420 | PV | 4.4 | Yes | Inverter | 2014-06-18 | 2014-06-20 07:07 | 2014-06-20 07:08 | 2014-06-20 07:08 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending PV installation
CENY-W | MC-84644 | PV | 3.3 | Yes | Inverter | 2014-06-19 | 2014-06-23 11:13 | 2014-06-23 11:13 | 2014-06-23 11:14 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending PV installation
CENY-W | MC-84649 | PV | 16.2 | Yes | Inverter | 2014-06-19 | 2014-07-01 07:16 | 2014-07-01 07:19 | 2014-07-01 07:20 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending PV installation
CENY-W | MC-84782 | PV | 4 | Yes | Inverter | 2014-06-20 | 2014-06-23 09:20 | 2014-06-23 09:21 | 2014-06-23 09:39 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending PV installation
CENY-W | MC-84793 | PV | 5 | Yes | Inverter | 2014-06-20 | 2014-06-20 12:50 | 2014-06-20 12:51 | 2014-06-20 12:51 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending PV installation
CENY-W | MC-84961 | PV | 40 | Yes | Inverter | 2014-06-20 | 2014-06-20 | 2014-06-20 | 2014-06-20 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | in progress | Pending customer build
CENY-W | MC-84962 | PV | 3.2 | Yes | Inverter | 2014-06-20 | 2014-06-23 10:12 | 2014-06-23 10:13 | 2014-06-23 10:13 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending PV installation
CENY-W | MC-84964 | PV | 4.2 | Yes | Inverter | 2014-06-20 | 2014-06-23 10:46 | 2014-06-23 10:48 | 2014-06-23 10:48 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending PV installation
CENY-W | MC-84967 | PV | 5 | Yes | Inverter | 2014-06-20 | 2014-06-23 11:30 | 2014-06-23 11:31 | 2014-06-23 11:31 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending PV installation
CENY-W | MC-85150 | PV | 5 | Yes | Inverter | 2014-06-23 | 2014-06-23 13:56 | 2014-06-23 13:58 | 2014-06-23 13:58 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-15 | No | Complete | Complete
CENY-W | MC-85158 | PV | 9 | Yes | Inverter | 2014-06-23 | 2014-06-23 14:43 | 2014-06-23 14:44 | 2014-06-23 14:44 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending PV installation
CENY-W | MC-85166 | PV | 12.8 | Yes | Inverter | 2014-06-23 | 2014-06-24 07:02 | 2014-06-24 07:03 | 2014-06-24 07:03 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-16 | No | Complete | Complete
CENY-W | MC-85187 | PV | 9.6 | Yes | Inverter | 2014-06-23 | 2014-06-23 15:03 | 2014-06-23 15:04 | 2014-06-23 15:04 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-09 | No | Complete | Complete
CENY-W | MC-85199 | PV | 17.8 | Yes | Inverter | 2014-06-23 | 2014-06-24 06:30 | 2014-06-24 06:30 | 2014-06-24 06:30 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-22 | No | Complete | Complete
CENY-W | MC-85214 | PV | 8 | Yes | Inverter | 2014-06-23 | 2014-06-24 07:53 | 2014-06-24 07:40 | 2014-06-24 07:40 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-10-21 | No | Complete | Complete
CENY-W | MC-85215 | PV | 6 | Yes | Inverter | 2014-06-23 | 2014-06-24 08:37 | 2014-06-24 08:38 | 2014-06-24 08:38 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending PV installation
CENY-W | MC-85246 | PV | 6 | Yes | Inverter | 2014-06-23 | 2014-06-24 08:56 | 2014-06-24 08:56 | 2014-06-24 08:56 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-10-17 | No | Complete | Complete
CENY-W | MC-85378 | PV | 120 | Yes | Inverter | 2014-06-24 | 2014-07-07 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | in progress | in progress
CENY-W | MC-85407 | PV | 5 | Yes | Inverter | 2014-06-24 | 2014-06-24 | 2014-06-24 | 2014-06-24 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending PV installation
CENY-W | MC-85413 | PV | 3.8 | Yes | Inverter | 2014-06-24 | 2014-06-24 13:21 | 2014-06-24 13:22 | 2014-06-24 13:22 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending PV installation
CENY-W | MC-85423 | PV | 61.5 | Yes | Inverter | 2014-06-24 | 2014-07-28 13:36 | 2014-07-28 13:37 | 2014-07-28 13:37 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | in progress | in progress
CENY-W | MC-85427 | PV | 3.8 | Yes | Inverter | 2014-06-24 | 2014-06-26 10:52 | 2014-06-26 10:53 | 2014-06-26 10:53 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-15 | No | Complete | Complete
CENY-W | MC-85428 | PV | 9 | Yes | Inverter | 2014-06-24 | 2014-06-24 | 2014-06-24 | 2014-06-24 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | New Building- UNDER TEMP METER
CENY-W | MC-85434 | PV | 160 | Yes | Inverter | 2014-06-24 | 2014-06-25 | 2014-06-27 | 2014-07-01 | 2014-07-08 | 2014-07-08 | 0 | 0 | 350 | 0 | 0 |  |  | NO | In Progress | Pending - Customers decsion
CENY-W | MC-85456 | PV | 7.2 | Yes | Inverter | 2014-06-24 | 2014-06-25 09:51 | 2014-06-25 09:52 | 2014-06-25 09:52 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending PV installation
CENY-W | MC-85620 | PV | 7.5 | Yes | Inverter | 2014-06-25 | 2014-06-26 11:27 | 2014-06-26 11:27 | 2014-06-26 11:27 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-10-07 | No | Complete | Complete
CENY-W | MC-85639 | PV | 8.8 | Yes | Inverter | 2014-06-25 | 2014-06-25 13:25 | 2014-06-25 13:26 | 2014-06-25 13:27 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending PV installation
CENY-W | MC-85697 | PV | 7.6 | Yes | Inverter | 2014-06-25 | 2014-06-25 15:17 | 2014-06-25 15:18 | 2014-06-25 15:18 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending PV installation
CENY-W | MC-85724 | PV | 6 | Yes | Inverter | 2014-06-25 | 2014-06-26 07:09 | 2014-06-26 07:12 | 2014-06-26 07:16 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending PV installation
CENY-W | MC-85751 | PV | 6 | Yes | Inverter | 2014-06-25 | 2014-06-26 08:36 | 2014-06-26 08:37 | 2014-06-26 08:39 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending PV installation
CENY-W | MC-85909 | PV | 14 | Yes | Inverter | 2014-06-26 | 2014-06-27 07:36 | 2014-06-27 07:37 | 2014-06-27 07:37 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending PV installation
CENY-W | MC-85925 | PV | 2.8 | Yes | Inverter | 2014-06-26 | 2014-06-27 08:20 | 2014-06-27 08:21 | 2014-06-27 08:21 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending PV installation
CENY-W | MC-86000 | PV | 6.8 | Yes | Inverter | 2014-06-27 | 2014-06-27 10:28 | 2014-06-27 10:28 | 2014-06-27 10:28 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending PV installation
CENY-W | MC-86042 | PV | 4 | Yes | Inverter | 2014-06-27 | 2014-06-27 13:16 | 2014-06-27 13:17 | 2014-06-27 13:18 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending PV installation
CENY-W | MC-86052 | PV | 11 | Yes | Inverter | 2014-06-27 | 2014-06-30 09:59 | 2014-06-30 09:55 | 2014-06-30 09:55 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-11 | No | Complete | Complete
CENY-W | MC-86072 | PV | 7 | Yes | Inverter | 2014-06-27 | 2014-06-30 10:15 | 2014-06-30 10:16 | 2014-06-30 10:16 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-10-21 | No | Complete | Complete
CENY-W | MC-86141 | PV | 5.6 | Yes | Inverter | 2014-06-27 | 2014-06-30 10:33 | 2014-06-30 10:33 | 2014-06-30 10:33 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-16 | No | Complete | Complete
CENY-W | MC-86285 | PV | 5 | Yes | Inverter | 2014-06-30 | 2014-06-30 10:49 | 2014-06-30 10:49 | 2014-06-30 10:49 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-15 | No | Complete | Complete
CENY-W | MC-86333 | PV | 50.4 | Yes | Inverter | 2014-06-30 | 2014-06-30 13:14 | 2014-06-30 13:15 | 2014-06-30 13:15 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending PV installation
CENY-W | MC-86358 | PV | 14 | Yes | Inverter | 2014-06-30 | 2014-06-30 15:04 | 2014-06-30 15:05 | 2014-06-30 15:05 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending PV installation
CENY-W | MC-86385 | PV | 220.8 | Yes | Inverter | 2014-06-30 | 2014-07-22 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | in progress | PENDING COMPLETED APPLICATION
CENY-W | MC-86386 | PV | 193.2 | Yes | Inverter | 2014-06-30 | 2014-07-22 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | in progress | PENDING COMPLETED APPLICATION
CENY-W | MC-86387 | PV | 220.8 | Yes | Inverter | 2014-06-30 | 2014-07-22 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | in progress | PENDING COMPLETED APPLICATION
CENY-W | MC-86388 | PV | 220.8 | Yes | Inverter | 2014-06-30 | 2014-07-22 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | in progress | PENDING COMPLETED APPLICATION
CENY-W | MC-86389 | PV | 193.2 | Yes | Inverter | 2014-06-30 | 2014-07-22 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | in progress | PENDING COMPLETED APPLICATION
CENY-W | MC-86402 | PV | 11.4 | Yes | Inverter | 2014-06-30 | 2014-06-30 | 2014-06-30 | 2014-06-30 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Pending PV installation
CENY-W | MC-86528 | PV | 6 | Yes | Inverter | 2014-07-01 | 2014-07-01 11:52 | 2014-07-01 11:53 | 2014-07-01 11:53 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | In Progress | Responded to contractor interconnection application. Sent 1 line diagram approval
CENY-W | MC-86534 | PV | 9.2 | Yes | Inverter | 2014-07-01 | 2014-07-01 12:50 | 2014-07-01 12:51 | 2014-09-15 14:47 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-09 | No | Complete | Complete
CENY-W | MC-86555 | PV | 4.6 | Yes | Inverter | 2014-07-01 | 2014-07-01 14:37 | 2014-07-01 14:39 | 2014-08-28 09:50 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-18 | No | Complete | Complete
CENY-W | MC-86574 | PV | 6 | Yes | Inverter | 2014-07-01 | 2014-07-02 06:15 | 2014-07-02 06:17 | 2014-08-28 09:54 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-22 | No | Complete | Complete
CENY-W | MC-86582 | PV | 5.2 | Yes | Inverter | 2014-07-01 | 2014-07-02 06:46 | 2014-07-02 06:47 | 2014-07-02 06:47 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending PV installation
CENY-W | MC-86584 | PV | 3.4 | Yes | Inverter | 2014-07-01 | 2014-07-02 07:09 | 2014-07-02 07:10 | 2014-09-19 12:00 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-10-10 | No | Complete | Complete
CENY-W | MC-86597 | PV | 7.4 | Yes | Inverter | 2014-07-01 | 2014-07-02 07:31 | 2014-07-02 07:31 | 2014-07-02 07:31 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending PV installation
CENY-W | MC-86632 | PV | 4.4 | Yes | Inverter | 2014-07-01 | 2014-07-02 07:55 | 2014-07-02 07:56 | 2014-07-02 07:56 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval.
CENY-W | MC-86745 | PV | 6 | Yes | Inverter | 2014-07-02 | 2014-07-02 09:30 | 2014-07-02 09:31 | 2014-08-28 10:01 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-15 | No | Complete | Complete
CENY-W | MC-86792 | PV | 5 | Yes | Inverter | 2014-07-02 | 2014-07-02 12:50 | 2014-07-02 12:50 | 2014-09-19 11:47 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-10-20 | No | Complete | Complete
CENY-W | MC-86815 | PV | 10 | Yes | Inverter | 2014-07-02 | 2014-07-02 13:23 | 2014-07-02 13:24 | 2014-07-02 13:30 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-10-20 | No | Complete | Complete
CENY-W | MC-86834 | PV | 4.8 | Yes | Inverter | 2014-07-02 | 2014-07-02 13:53 | 2014-07-07 09:17 | 2014-07-07 09:17 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Contractor to submit final docs.
CENY-W | MC-86849 | PV | 6.8 | Yes | Inverter | 2014-07-02 | 2014-07-07 10:06 | 2014-07-07 10:07 | 2014-08-29 06:28 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-29 | No | Complete | Complete
CENY-W | MC-86866 | PV | 7.6 | Yes | Inverter | 2014-07-02 | 2014-07-07 10:33 | 2014-07-07 10:34 | 2014-07-07 10:34 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval.
CENY-W | MC-86949 | PV | 10 | Yes | Inverter | 2014-07-03 | 2014-07-07 11:15 | 2014-07-07 11:16 | 2014-10-01 06:27 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Sent Mtr reservation.
CENY-W | MC-86996 | PV | 3.8 | Yes | Inverter | 2014-07-03 | 2014-07-07 11:58 | 2014-07-07 11:59 | 2014-08-28 09:47 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-15 | No | Complete | Complete
CENY-W | MC-87012 | PV | 3.6 | Yes | Inverter | 2014-07-03 | 2014-07-07 12:12 | 2014-07-07 12:17 | 2014-07-07 10:34 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Recieved final docs. Sent mtr reservation.
CENY-W | MC-87017 | PV | 3.2 | Yes | Inverter | 2014-07-03 | 2014-07-07 13:16 | 2014-07-07 13:17 | 2014-07-29 08:32 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | Cancelled | Cancelled
CENY-W | MC-87021 | PV | 6 | Yes | Inverter | 2014-07-03 | 2014-07-07 13:39 | 2014-07-07 13:39 | 2014-07-07 13:39 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-15 | No | Complete | Complete
CENY-W | MC-87291 | PV | 55.5 | Yes | Inverter | 2014-07-07 | 2014-07-07 15:15 | 2014-07-07 15:15 | 2014-07-07 15:15 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Contractor to submit final docs
CENY-W | MC-87296 | PV | 12 | Yes | Inverter | 2014-07-07 | [5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | NO | cancelled | cancelled
CENY-W | MC-87378 | PV | 5 | Yes | Inverter | 2014-07-07 | 2014-07-07 16:30 | 2014-07-07 16:31 | 2014-08-16 06:36 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-15 | No | Complete | Complete
CENY-W | MC-87412 | PV | 4.4 | Yes | Inverter | 2014-07-07 | 2014-07-07 17:01 | 2014-07-07 17:02 | 2014-07-07 17:02 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-10-22 | No | Complete | Complete
CENY-W | MC-87424 | PV | 5.8 | Yes | Inverter | 2014-07-07 | 2014-07-07 17:11 | 2014-07-07 17:12 | 2014-09-29 09:29 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Sent mtr WR
CENY-W | MC-87630 | PV | 5 | Yes | Inverter | 2014-07-08 | 2014-07-09 10:29 | 2014-07-09 10:30 | 2014-09-04 11:38 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-28 | No | Complete | Complete
CENY-W | MC-87820 | PV | 6 | Yes | Inverter | 2014-07-09 | 2014-07-09 13:40 | 2014-07-09 13:41 | 2014-09-04 11:34 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-28 | No | Complete | Complete
CENY-W | MC-87896 | PV | 6 | Yes | Inverter | 2014-07-09 | 2014-07-10 06:48 | 2014-07-10 06:49 | 2014-07-10 06:49 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Sent Mtr Reservation
CENY-W | MC-88119 | PV | 4.6 | Yes | Inverter | 2014-07-10 | 2014-07-11 09:55 | 2014-07-11 09:55 | 2014-09-05 09:05 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | Cancelled | Cancelled
CENY-W | MC-88226 | PV | 5 | Yes | Inverter | 2014-07-10 | 2014-07-11 09:21 | 2014-07-11 09:22 | 2014-08-07 07:05 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-03 | No | Complete | Complete
CENY-W | MC-88362 | PV | 109.2 | Yes | Inverter | 2014-07-11 | 2014-07-15 08:57 | 2014-07-15 08:58 | 2014-07-15 08:58 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Recieved full app. Sent line diagram approval.
CENY-W | MC-88730 | PV | 3.2 | Yes | Inverter | 2014-07-14 | 2014-07-15 08:14 | 2014-07-15 08:15 | 2014-09-08 09:36 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-09 | No | Complete | Complete
CENY-W | MC-88740 | PV | 5.2 | Yes | Inverter | 2014-07-14 | 2014-07-15 08:50 | 2014-07-15 08:51 | 2014-07-15 08:51 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval
CENY-W | MC-88812 | PV | 5 | Yes | Inverter | 2014-07-15 | 2014-07-15 10:04 | 2014-07-15 10:05 | 2014-07-15 10:05 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-10-21 | No | Complete | Complete
CENY-W | MC-88845 | PV | 10 | Yes | Inverter | 2014-07-15 | 2014-07-15 10:50 | 2014-07-15 10:51 | 2014-07-15 10:51 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval.
CENY-W | MC-88857 | PV | 4 | Yes | Inverter | 2014-07-15 | 2014-07-15 12:36 | 2014-07-15 12:37 | 2014-07-15 12:37 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval.
CENY-W | MC-89389 | PV | 22 | Yes | Inverter | 2014-07-17 | 2014-07-17 13:16 | 2014-07-17 13:17 | 2014-07-17 13:17 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval.
CENY-W | MC-89392 | PV | 4 | Yes | Inverter | 2014-07-17 | 2014-07-17 | 2014-07-18 07:49 | 2014-09-24 15:07 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Sent mtr wr
CENY-W | MC-89948 | PV | 9 | Yes | Inverter | 2014-07-21 | 2014-07-29 06:57 | 2014-07-29 06:59 | 2014-08-28 09:53 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-18 | No | Complete | Complete
CENY-W | MC-89949 | PV | 6 | Yes | Inverter | 2014-07-21 | 2014-07-29 07:17 | 2014-07-29 07:18 | 2014-07-29 07:18 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval
CENY-W | MC-89969 | PV | 12 | Yes | Inverter | 2014-07-21 | 2014-08-20 15:11 | 2014-08-21 06:59 | 2014-08-21 06:59 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Prepared mtr reservation. Pending final docs from contractor
CENY-W | MC-90012 | PV | 9.2 | Yes | Inverter | 2014-07-21 | 2014-07-29 06:44 | 2014-07-29 06:45 | 2014-07-29 06:45 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval.
CENY-W | MC-90044 | PV | 4 | Yes | Inverter | 2014-07-22 | 2014-07-28 14:26 | 2014-07-28 14:27 | 2014-07-28 14:27 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval.
CENY-W | MC-90045 | PV | 6 | Yes | Inverter | 2014-07-22 | 2014-07-29 06:22 | 2014-07-29 06:23 | 2014-07-29 06:23 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Pending customer to complete work and submit Self-Certification Affidavit.
CENY-W | MC-90088 | PV | 4.8 | Yes | Inverter | 2014-07-22 | 2014-07-29 06:12 | 2014-07-29 06:12 | 2014-07-29 06:12 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval.
CENY-W | MC-90235 | PV | 49 | Yes | Inverter | 2014-07-22 | 2014-07-28 15:09 | 2014-07-28 15:11 | 2014-07-28 15:11 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | 7/28/14 Case is truly a PSN 1 and let kevin know. I tried and cannot edit the triage in this case. May need to cancel & restart
CENY-W | MC-90241 | PV | 5 | Yes | Inverter | 2014-07-22 | 2014-07-28 14:08 | 2014-07-28 14:09 | 2014-09-08 10:57 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-09 | No | Complete | Complete
CENY-W | MC-90467 | PV | 5 | Yes | Inverter | 2014-07-23 | 2014-07-28 12:11 | 2014-07-28 12:11 | 2014-09-19 11:40 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-10-20 | No | Complete | Complete
CENY-W | MC-90469 | PV | 3 | Yes | Inverter | 2014-07-23 | 2014-07-28 13:09 | 2014-07-28 13:14 | 2014-07-28 13:14 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | SENT MTR WR
CENY-W | MC-90539 | PV | 65.6 | Yes | Inverter | 2014-07-23 | 2014-07-28 11:53 | 2014-07-28 11:53 | 2014-07-28 11:53 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval
CENY-W | MC-90543 | PV | 9.2 | Yes | Inverter | 2014-07-23 | 2014-07-28 11:37 | 2014-07-28 11:37 | 2014-07-28 11:37 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval
CENY-W | MC-90550 | PV | 171.6 | Yes | Inverter | 2014-07-23 | 2014-07-28 11:24 | 2014-07-28 11:25 | 2014-07-28 11:25 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | SENT MTR WR
CENY-W | MC-90565 | PV | 5.4 | Yes | Inverter | 2014-07-23 | 2014-07-28 11:09 | 2014-07-28 11:10 | 2014-07-28 11:10 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval.
CENY-W | MC-90609 | PV | 17 | Yes | Inverter | 2014-07-23 | 2014-07-28 10:47 | 2014-07-28 10:48 | 2014-07-28 10:48 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval
CENY-W | MC-90651 | PV | 449.4 | Yes | Inverter | 2014-07-24 | 2014-07-28 10:32 | 2014-07-28 10:33 | 2014-07-28 10:33 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval
CENY-W | MC-90750 | PV | 169 | Yes | Inverter | 2014-07-24 | 2014-07-28 09:46 | 2014-07-28 09:56 | 2014-07-28 09:56 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval.
CENY-W | MC-90844 | PV | 13.975 | Yes | Inverter | 2014-07-24 | 2014-10-10 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Installer mistaken with PV size numbers. Most likely 65 x 260W panels into a 13.97KW inverter.
CENY-W | MC-90987 | PV | 7.2 | Yes | Inverter | 2014-07-25 | 2014-07-28 09:24 | 2014-07-28 09:24 | 2014-07-28 09:24 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval.
CENY-W | MC-91307 | PV | 7.6 | Yes | Inverter | 2014-07-28 | 2014-07-29 07:46 | 2014-07-29 07:49 | 2014-07-29 07:49 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval.
CENY-W | MC-91320 | PV | 64 | Yes | Inverter | 2014-07-28 | 2014-07-29 08:02 | 2014-07-29 08:16 | 2014-07-29 08:16 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval.
CENY-W | MC-91325 | PV | 5.8 | Yes | Inverter | 2014-07-28 | 2014-07-29 08:50 | 2014-07-29 08:52 | 2014-07-29 08:52 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-09 | No | Complete | Complete
CENY-W | MC-91359 | PV | 5 | Yes | Inverter | 2014-07-28 | 2014-07-29 09:16 | 2014-07-29 09:17 | 2014-09-04 11:47 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-08-28 | No | Complete | Complete
CENY-W | MC-91396 | PV | 12 | Yes | Inverter | 2014-07-28 | 2014-07-29 10:02 | 2014-07-29 10:02 | 2014-07-29 10:02 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval.
CENY-W | MC-91456 | PV | 7.8 | Yes | Inverter | 2014-07-29 | 2014-09-11 10:38 | 2014-09-11 10:39 | 2014-09-24 11:33 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Sent MTR WR
CENY-W | MC-91485 | PV | 12 | Yes | Inverter | 2014-07-29 | [5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | NO | Cancelled | cancelled
CENY-W | MC-91530 | PV | 8.4 | Yes | Inverter | 2014-07-29 | 2014-07-31 10:37 | 2014-07-31 10:42 | 2014-07-31 10:42 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval.
CENY-W | MC-91913 | PV | 9.4 | Yes | Inverter | 2014-07-30 | 2014-07-31 07:11 | 2014-07-31 07:12 | 2014-07-31 07:12 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval
CENY-W | MC-92048 | MT | 2.4 | Yes | Inverter | 2014-07-31 | 2014-07-31 13:13 | 2014-07-31 13:14 | 2014-07-31 13:14 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval.
CENY-W | MC-92076 | PV | 6.6 | Yes | Inverter | 2014-07-31 | 2014-08-01 07:35 | 2014-08-01 07:40 | 2014-09-23 09:08 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-10-15 | No | Complete | Complete
CENY-W | MC-92092 | PV | 5.6 | Yes | Inverter | 2014-07-31 | 2014-08-01 08:38 | 2014-08-01 08:40 | 2014-08-01 08:40 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-16 | No | Complete | Complete
CENY-W | MC-92113 | PV | 6 | Yes | Inverter | 2014-07-31 | 2014-08-01 08:59 | 2014-08-01 09:05 | 2014-08-01 09:05 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Sent Meter WR
CENY-W | MC-92120 | PV | 5 | Yes | Inverter | 2014-07-31 | 2014-08-01 09:51 | 2014-08-01 09:52 | 2014-08-01 09:52 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval.
CENY-W | MC-92127 | PV | 19.6 | Yes | Inverter | 2014-07-31 | 2014-08-01 10:22 | 2014-08-01 10:27 | 2014-09-29 09:36 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Sent WR
CENY-W | MC-92142 | PV | 6 | Yes | Inverter | 2014-07-31 | 2014-08-21 08:49 | 2014-08-21 08:50 | 2014-08-21 08:50 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Prepared Mtr reservation. Pending final docs from contractor
CENY-W | MC-92144 | PV | 3.8 | Yes | Inverter | 2014-07-31 | 2014-08-01 10:45 | 2014-08-01 10:46 | 2014-08-01 10:46 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval.
CENY-W | MC-92305 | PV | 372 | Yes | Inverter | 2014-08-01 | 2014-08-04 13:51 | 2014-08-04 13:54 | 2014-08-04 13:54 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval.
CENY-W | MC-92354 | PV | 6.6 | Yes | Inverter | 2014-08-01 | 2014-08-04 09:15 | 2014-08-04 09:15 | 2014-09-26 08:13 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Recieved final docs. Sent mtr reservation
CENY-W | MC-92356 | PV | 4 | Yes | Inverter | 2014-08-01 | 2014-08-04 09:28 | 2014-08-04 09:29 | 2014-08-04 09:29 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval.
CENY-W | MC-92544 | PV | 5.4 | Yes | Inverter | 2014-08-04 | 2014-08-04 14:36 | 2014-08-05 06:58 | 2014-08-06 13:26 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | Cancelled | Cancelled by customer.
CENY-W | MC-92577 | PV | 57 | Yes | Inverter | 2014-08-04 | 2014-08-05 11:44 | 2014-08-04 09:29 | 2014-08-04 09:29 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval.
CENY-W | MC-92687 | PV | 7.6 | Yes | Inverter | 2014-08-05 | 2014-08-05 09:37 | 2014-08-05 09:38 | 2014-08-26 12:25 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | Cancelled | Cancelled
CENY-W | MC-92730 | PV | 225 | Yes | Inverter | 2014-08-05 | 2014-08-05 11:21 | 2014-08-05 11:22 | 2014-08-05 11:22 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval.
CENY-W | MC-92793 | PV | 575 | Yes | Inverter | 2014-08-05 | 2014-08-25 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | notice to customer pend'g acttion
CENY-W | MC-92852 | PV | 3 | Yes | Inverter | 2014-08-05 | 2014-08-07 11:20 | 2014-08-07 11:21 | 2014-08-07 11:21 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval
CENY-W | MC-93256 | PV | 77.9 | Yes | Inverter | 2014-08-07 | 2014-08-07 12:49 | 2014-08-07 12:50 | 2014-08-07 12:50 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval.
CENY-W | MC-93291 | PV | 5 | Yes | Inverter | 2014-08-07 | 2014-08-08 08:25 | 2014-08-08 08:27 | 2014-09-29 15:13 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-10-20 | No | Complete | Complete
CENY-W | MC-93490 | PV | 3096 | Yes | Inverter | 2014-08-08 | [5 empty] | 0 | 0 | 0 | 0 | 0 |  |  | NO | Cancelled | cancelled
CENY-W | MC-93520 | PV | 14 | Yes | Inverter | 2014-08-08 | 2014-08-11 09:21 | 2014-08-11 09:23 | 2014-08-11 09:23 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval.
CENY-W | MC-93817 | PV | 3.6 | Yes | Inverter | 2014-08-11 | 2014-08-12 09:26 | 2014-08-12 09:27 | 2014-09-23 09:24 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-16 | No | Complete | Complete
CENY-W | MC-93843 | PV | 8 | Yes | Inverter | 2014-08-11 | 2014-08-12 09:02 | 2014-08-12 09:03 | 2014-08-12 09:03 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval. Still require application Form G.
CENY-W | MC-93913 | PV | 7.2 | Yes | Inverter | 2014-08-12 | 2014-08-28 10:47 | 2014-08-28 10:48 | 2014-08-28 10:48 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval
CENY-W | MC-93960 | PV | 4 | Yes | Inverter | 2014-08-12 | 2014-08-12 12:42 | 2014-08-12 12:43 | 2014-08-12 12:43 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Sent line diagram approval.
CENY-W | MC-94162 | PV | 6.4 | Yes | Inverter | 2014-08-13 | 2014-08-14 07:39 | 2014-08-14 07:23 | 2014-09-19 12:06 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-10-03 | No | Complete | Complete
CENY-W | MC-94175 | PV | 7.4 | Yes | Inverter | 2014-08-13 | 2014-08-13 11:32 | 2014-08-13 11:33 | 2014-09-23 07:35 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-10-15 | No | Complete | Complete
CENY-W | MC-94181 | PV | 5.6 | Yes | Inverter | 2014-08-13 | 2014-08-13 11:48 | 2014-08-13 11:49 | 2014-08-13 11:49 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval.
CENY-W | MC-94190 | PV | 6.6 | Yes | Inverter | 2014-08-13 | 2014-08-13 12:26 | 2014-08-13 12:30 | 2014-08-13 12:30 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval.
CENY-W | MC-94200 | PV | 6.6 | Yes | Inverter | 2014-08-13 | 2014-08-14 06:15 | 2014-08-14 06:16 | 2014-08-14 06:16 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval.
CENY-W | MC-94247 | PV | 2.8 | Yes | Inverter | 2014-08-13 | 2014-08-14 09:22 | 2014-08-14 09:25 | 2014-08-14 09:25 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval.
CENY-W | MC-94249 | PV | 3.2 | Yes | Inverter | 2014-08-13 | 2014-08-14 09:47 | 2014-08-14 09:47 | 2014-08-14 09:47 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval
CENY-W | MC-94552 | PV | 5 | Yes | Inverter | 2014-08-14 | 2014-08-15 07:09 | 2014-08-15 07:10 | 2014-08-15 07:10 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval
CENY-W | MC-94781 | PV | 7.5 | Yes | Inverter | 2014-08-15 | 2014-08-18 10:11 | 2014-08-18 10:13 | 2014-08-18 10:13 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | installation of 7.85 kW solar roof mount
CENY-W | MC-94784 | PV | 5.2 | Yes | Inverter | 2014-08-15 | 2014-08-15 | 2014-08-15 | 2014-08-15 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | PENDING CIS UPDATE
CENY-W | MC-94945 | PV | 6.6 | Yes | Inverter | 2014-08-18 | 2014-08-21 10:35 | 2014-08-21 10:36 | 2014-08-21 10:36 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Prepared mtr reservation. Pending final docs.
CENY-W | MC-95049 | PV | 11.2 | Yes | Inverter | 2014-08-18 | 2014-08-18 14:48 | 2014-08-18 14:53 | 2014-08-18 14:53 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Prepared mtr reservation. Pending final docs from contractor
CENY-W | MC-95074 | PV | 10 | Yes | Inverter | 2014-08-18 | 2014-08-19 09:04 | 2014-08-19 09:05 | 2014-08-19 09:05 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Prepared meter reservation. Pending final docs.
CENY-W | MC-95083 | PV | 80 | Yes | Inverter | 2014-08-18 | 2014-08-25 | 2014-10-21 |  |  |  | 0 | 0 | 350 | 0 | 0 |  |  | NO | IN PROGRESS | Prep for DG review
CENY-W | MC-95085 | PV | 117 | Yes | Inverter | 2014-08-18 | 2014-10-13 | 2014-10-13 | 2014-10-16 |  |  | 0 | 0 | 350 | 0 | 0 |  |  | NO | IN PROGRESS | Sent to DG for review
CENY-W | MC-95091 | PV | 45 | Yes | Inverter | 2014-08-18 | 2014-10-09 | 2014-10-09 | 2014-10-14 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | pending documents to compile for DG
CENY-W | MC-95092 | PV | 4 | Yes | Inverter | 2014-08-18 | 2014-08-19 08:29 | 2014-08-19 08:29 | 2014-08-19 08:29 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Prepared meter reservation. Pending final docs.
CENY-W | MC-95276 | PV | 5 | Yes | Inverter | 2014-08-19 | 2014-08-21 11:49 | 2014-08-21 11:51 | 2014-08-21 11:51 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval.
CENY-W | MC-95283 | PV | 6 | Yes | Inverter | 2014-08-19 | 2014-08-21 11:38 | 2014-08-21 11:39 | 2014-09-19 11:45 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Sent mtr WR
CENY-W | MC-95284 | PV | 2.6 | Yes | Inverter | 2014-08-19 | 2014-08-21 11:26 | 2014-08-21 11:27 | 2014-08-21 11:27 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval
CENY-W | MC-95290 | PV | 7.4 | Yes | Inverter | 2014-08-19 | 2014-08-21 11:17 | 2014-08-21 11:18 | 2014-08-21 11:18 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval
CENY-W | MC-95317 | PV | 5 | Yes | Inverter | 2014-08-19 | 2014-08-21 11:05 | 2014-08-21 11:06 | 2014-08-21 11:06 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval
CENY-W | MC-95355 | PV | 7.8 | Yes | Inverter | 2014-08-19 | 2014-08-21 10:16 | 2014-08-21 10:17 | 2014-08-21 10:17 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Prepared mtr reservation. Pending final docs.
CENY-W | MC-95365 | PV | 7.2 | Yes | Inverter | 2014-08-19 | 2014-08-21 09:24 | 2014-08-21 09:25 | 2014-09-24 11:27 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-10-06 | No | Complete | Complete
CENY-W | MC-95369 | PV | 3.8 | Yes | Inverter | 2014-08-19 | 2014-08-21 07:26 | 2014-08-21 07:27 | 2014-08-21 07:27 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Contractor changed inverter. Attached updated docs.
CENY-W | MC-95374 | PV | 7.6 | Yes | Inverter | 2014-08-19 | 2014-08-21 07:09 | 2014-08-21 07:11 | 2014-08-21 07:11 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Prepared mtr reservation. Pending final docs from contractor.
CENY-W | MC-95409 | PV | 6.6 | Yes | Inverter | 2014-08-19 | 2014-08-21 09:04 | 2014-08-21 09:04 | 2014-08-21 09:04 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Prepard mtr reservation. Pending final docs.
CENY-W | MC-95608 | ICE | 10 | NO | Inverter | 2014-08-20 | 2014-08-27 | 2014-08-27 | 2014-09-08 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Install (1) 10KW gas fired reciprocating engine.
CENY-W | MC-95819 | PV | 2.8 | Yes | Inverter | 2014-08-21 | 2014-08-22 08:33 | 2014-08-22 08:36 | 2014-08-22 08:36 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval
CENY-W | MC-96017 | PV | 7.8 | Yes | Inverter | 2014-08-22 | 2014-09-24 10:46 | 2014-09-24 10:46 | 2014-09-24 10:46 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-10-15 | No | Complete | Complete
CENY-W | MC-96093 | PV | 3 | Yes | Inverter | 2014-08-22 | 2014-08-26 07:58 | 2014-08-26 08:00 | 2014-08-26 08:00 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval
CENY-W | MC-96096 | PV | 6 | Yes | Inverter | 2014-08-22 | 2014-08-26 08:15 | 2014-08-26 08:16 | 2014-08-26 08:16 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval.
CENY-W | MC-96097 | PV | 5.8 | Yes | Inverter | 2014-08-22 | 2014-08-25 07:14 | 2014-08-25 07:15 | 2014-08-25 07:15 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval
CENY-W | MC-96154 | PV | 6 | Yes | Inverter | 2014-08-25 | 2014-08-26 08:38 | 2014-08-26 08:39 | 2014-08-26 08:39 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-10-22 | No | Complete | Complete
CENY-W | MC-96323 | PV | 4 | Yes | Inverter | 2014-08-25 | 2014-08-26 08:26 | 2014-08-26 08:27 | 2014-08-26 08:27 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval.
CENY-W | MC-96369 | PV | 3.8 | Yes | Inverter | 2014-08-25 | 2014-08-26 09:01 | 2014-08-26 09:01 | 2014-08-26 09:01 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval
CENY-W | MC-96435 | PV | 6.3 | Yes | Inverter | 2014-08-26 | 2014-08-26 10:07 | 2014-08-26 10:08 | 2014-08-26 10:08 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval.
CENY-W | MC-96532 | PV | 8 | Yes | Inverter | 2014-08-26 | 2014-08-27 11:00 | 2014-08-27 11:16 | 2014-08-27 11:16 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | attached temp cert. Will put in bin Majors.
CENY-W | MC-96544 | PV | 14 | Yes | Inverter | 2014-08-26 | 2014-08-27 10:04 | 2014-08-27 10:29 | 2014-10-01 13:12 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Sent Mtr Res
CENY-W | MC-96754 | PV | 6 | Yes | Inverter | 2014-08-27 | 2014-08-27 14:12 | 2014-08-27 14:13 | 2014-08-27 14:13 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval.
CENY-W | MC-96773 | PV | 3.8 | Yes | Inverter | 2014-08-27 | 2014-08-27 14:45 | 2014-08-27 14:46 | 2014-09-23 07:48 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Sent WR
CENY-W | MC-96781 | PV | 22 | Yes | Inverter | 2014-08-27 | 2014-08-27 14:45 | 2014-08-27 15:06 | 2014-09-23 07:25 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Sent mtr WR
CENY-W | MC-96784 | PV | 3.2 | Yes | Inverter | 2014-08-27 | 2014-08-28 07:06 | 2014-08-28 07:07 | 2014-08-28 07:07 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval.
CENY-W | MC-96832 | PV | 3.4 | Yes | Inverter | 2014-08-27 | 2014-08-28 07:37 | 2014-08-28 07:37 | 2014-09-23 09:21 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-09-16 | No | Complete | Complete
CENY-W | MC-96983 | PV | 3 | Yes | Inverter | 2014-08-28 | 2014-09-23 07:56 | 2014-09-23 07:57 | 2014-09-23 07:57 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | SENT MTR WR
CENY-W | MC-97059 | PV | 10.4 | Yes | Inverter | 2014-08-28 | 2014-08-29 08:07 | 2014-08-29 08:08 | 2014-08-29 08:08 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval.
CENY-W | MC-97063 | PV | 5.2 | Yes | Inverter | 2014-08-28 | 2014-08-29 08:26 | 2014-08-29 08:27 | 2014-08-29 08:27 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Sent mtr reservation
CENY-W | MC-97208 | PV | 6 | Yes | Inverter | 2014-08-29 | 2014-09-03 09:56 | 2014-09-03 09:57 | 2014-09-03 09:57 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval.
CENY-W | MC-97268 | PV | 6.8 | Yes | Inverter | 2014-09-01 | 2014-09-03 10:34 | 2014-09-03 10:50 | 2014-09-03 10:50 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval.
CENY-W | MC-97269 | PV | 4.8 | Yes | Inverter | 2014-09-01 | 2014-09-03 11:24 | 2014-09-03 11:25 | 2014-09-03 11:25 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval
CENY-W | MC-97281 | PV | 4.6 | Yes | Inverter | 2014-09-01 | 2014-09-03 11:49 | 2014-09-03 11:50 | 2014-09-03 11:50 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval
CENY-W | MC-97284 | PV | 4.8 | Yes | Inverter | 2014-09-01 | 2014-09-03 14:09 | 2014-09-03 14:10 | 2014-09-03 14:10 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval.
CENY-W | MC-97291 | PV | 5.4 | Yes | Inverter | 2014-09-01 | 2014-09-03 14:23 | 2014-09-03 14:25 | 2014-09-03 14:25 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval.
CENY-W | MC-97292 | PV | 16 | Yes | Inverter | 2014-09-01 | 2014-09-03 14:41 | 2014-09-03 14:42 | 2014-09-03 14:42 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval
CENY-W | MC-97337 | PV | 3.8 | Yes | Inverter | 2014-09-01 | 2014-09-03 15:05 | 2014-09-03 15:06 | 2014-09-03 15:06 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | PENDING CIS UPDATE
CENY-W | MC-97391 | PV | 8.2 | Yes | Inverter | 2014-09-03 | 2014-09-03 15:17 | 2014-09-04 07:21 | 2014-09-04 07:21 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval
CENY-W | MC-97442 | PV | 6.6 | Yes | Inverter | 2014-09-03 | 2014-09-04 07:00 | 2014-09-04 07:02 | 2014-09-04 07:02 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Installation of a 9.08 kW solar photovoltaic system on the roof of the house located at 76 Chatsworth Ave., Larchmont, New York.
CENY-W | MC-97496 | ICE | 75 | NO | Inverter | 2014-09-03 | 2014-09-12 | 2014-09-12 | 2014-09-16 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | Engineering comments forwarded to customer today.
CENY-W | MC-97667 | PV | 12 | Yes | Inverter | 2014-09-03 | 2014-09-04 08:34 | 2014-09-04 08:47 | 2014-09-04 08:47 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval
CENY-W | MC-97712 | PV | 4.8 | Yes | Inverter | 2014-09-03 | 2014-09-04 08:07 | 2014-09-04 08:08 | 2014-09-04 08:08 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval.
CENY-W | MC-97771 | PV | 3 | Yes | Inverter | 2014-09-03 | 2014-09-04 10:00 | 2014-09-04 09:49 | 2014-09-04 09:49 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval
CENY-W | MC-97912 | PV | 19.6 | Yes | Inverter | 2014-09-04 | 2014-09-05 07:40 | 2014-09-05 07:41 | 2014-09-05 07:41 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval
CENY-W | MC-98078 | PV | 4 | Yes | Inverter | 2014-09-05 | 2014-09-05 10:01 | 2014-09-05 10:02 | 2014-09-05 10:02 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Customer name added to CE account. Sent line diagram approval.
CENY-W | MC-98126 | PV | 5 | Yes | Inverter | 2014-09-05 | 2014-09-05 | 2014-09-05 | 2014-09-05 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Recieved full application. Sent diagram approval.
CENY-W | MC-98159 | PV | 2.4 | Yes | Inverter | 2014-09-05 | 2014-09-08 09:56 | 2014-09-08 09:57 | 2014-09-08 09:57 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | PENDING CIS UPDATE
CENY-W | MC-98180 | PV | 6 | Yes | Inverter | 2014-09-05 | 2014-09-08 11:28 | 2014-09-08 11:29 | 2014-09-08 11:29 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval
CENY-W | MC-98464 | PV | 9.8 | Yes | Inverter | 2014-09-08 | 2014-09-08 12:09 | 2014-09-08 12:11 | 2014-09-08 12:11 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval
CENY-W | MC-98496 | PV | 16.8 | Yes | Inverter | 2014-09-08 | 2014-09-08 14:32 | 2014-09-08 14:33 | 2014-09-08 14:33 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval
CENY-W | MC-98633 | PV | 15.2 | Yes | Inverter | 2014-09-08 | 2014-09-09 07:07 | 2014-09-09 07:08 | 2014-09-09 07:08 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval.
CENY-W | MC-98649 | PV | 6 | Yes | Inverter | 2014-09-08 | 2014-09-09 07:07 | 2014-09-09 07:08 | 2014-09-09 07:08 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | SENT MTR WR
CENY-W | MC-98886 | PV | 10 | Yes | Inverter | 2014-09-09 | 2014-09-10 09:36 | 2014-09-10 09:38 | 2014-09-10 09:38 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval.
CENY-W | MC-99029 | PV | 8 | Yes | Inverter | 2014-09-10 | 2014-09-10 14:08 | 2014-09-10 14:10 | 2014-09-10 14:10 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval.
CENY-W | MC-99049 | PV | 7.6 | Yes | Inverter | 2014-09-10 | 2014-09-10 15:04 | 2014-09-10 15:05 | 2014-09-10 15:05 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval
CENY-W | MC-99188 | PV | 6.6 | Yes | Inverter | 2014-09-10 | 2014-09-11 07:54 | 2014-09-11 07:55 | 2014-09-11 07:55 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval
CENY-W | MC-99330 | PV | 5 | Yes | Inverter | 2014-09-11 | 2014-09-12 07:02 | 2014-09-12 07:03 | 2014-09-12 07:03 |  |  | 0 | 0 | 0 | 0 | 0 |  | 2014-10-21 | No | Complete | Complete
CENY-W | MC-99335 | PV | 3 | Yes | Inverter | 2014-09-11 | 2014-09-12 06:54 | 2014-09-12 06:55 | 2014-09-23 08:03 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Recieved final docs. Meter reservation attached.
CENY-W | MC-99342 | PV | 3 | Yes | Inverter | 2014-09-11 | 2014-09-12 07:41 | 2014-09-12 07:41 | 2014-09-12 07:41 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval.
CENY-W | MC-99343 | PV | 20 | Yes | Inverter | 2014-09-11 | 2014-09-12 07:54 | 2014-09-12 07:54 | 2014-09-12 07:54 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval.
CENY-W | MC-99346 | PV | 22 | Yes | Inverter | 2014-09-11 | 2014-09-12 08:40 | 2014-09-12 08:49 | 2014-09-12 08:49 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | please note that the customer lives in white plains and not hartsdale.
CENY-W | MC-99380 | PV | 8.6 | Yes | Inverter | 2014-09-11 | 2014-09-12 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | PENDING FULL APP
CENY-W | MC-99381 | PV | 5 | Yes | Inverter | 2014-09-11 | 2014-09-12 09:25 | 2014-09-12 09:32 | 2014-09-12 09:32 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval
CENY-W | MC-99396 | PV | 3.8 | Yes | Inverter | 2014-09-11 | 2014-09-12 09:44 | 2014-09-12 09:44 | 2014-09-12 09:44 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval.
CENY-W | MC-99401 | PV | 9 | Yes | Inverter | 2014-09-11 | 2014-09-12 10:16 | 2014-09-12 10:17 | 2014-09-12 10:17 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to interconnection application. Sent 1 line diagram approval
CENY-W | MC-99596 | PV | 3 | Yes | Inverter | 2014-09-12 | 2014-09-15 09:16 | 2014-09-15 09:17 | 2014-09-15 09:17 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval.
CENY-W | MC-99619 | ICE | 10 | YES | Inverter | 2014-09-12 | 2014-09-16 | 2014-09-16 | 2014-10-02 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | NO | IN PROGRESS | MICRO-CHP PSN1
CENY-W | MC-99663 | PV | 6.8 | Yes | Inverter | 2014-09-12 | 2014-09-15 10:42 | 2014-09-15 10:43 | 2014-09-29 12:26 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Recieved revised DWG and docs attached to case
CENY-W | MC-99665 | PV | 11.2 | Yes | Inverter | 2014-09-12 | 2014-09-15 10:08 | 2014-09-15 10:09 | 2014-09-15 10:09 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | SENT MTR WR
CENY-W | MC-99673 | PV | 14 | Yes | Inverter | 2014-09-12 | 2014-09-15 12:03 | 2014-09-15 12:05 | 2014-09-15 12:05 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval.
CENY-W | MC-99676 | PV | 4.8 | Yes | Inverter | 2014-09-12 | 2014-09-15 14:56 | 2014-09-15 14:57 | 2014-09-15 14:57 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval.
CENY-W | MC-99680 | PV | 5.8 | Yes | Inverter | 2014-09-12 | 2014-09-15 15:10 | 2014-09-15 15:11 | 2014-09-24 11:25 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval.
CENY-W | MC-99712 | PV | 5 | Yes | Inverter | 2014-09-15 | 2014-09-16 06:38 | 2014-09-16 06:40 | 2014-09-16 06:40 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval
CENY-W | MC-99780 | PV | 9.8 | Yes | Inverter | 2014-09-15 | 2014-09-16 06:38 | 2014-09-16 06:40 | 2014-09-16 06:40 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval
CENY-W | MC-99931 | PV | 9 | Yes | Inverter | 2014-09-15 | 2014-09-19 09:00 | 2014-09-19 09:01 | 2014-09-20 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | No | IN PROGRESS | Responded to contractor interconnection application. Sent 1 line diagram approval. Still require Application Form G