## Report
[5 empty] | 11.0561 | 37.0815 |  | 51.181 | 2288.2724 |  |  |  | 2339.4534
| Transmission System Phase 2 Projects (NYSEG & RGE) |  |  |  | 11.0561 | 37.0815 |  | 51.181 | 2288.2724 |  |  |  | 2412.0091
[5 empty] | 2025 Spend |  |  | Total Approved Spend | [5 empty] | 0 | 0
Article VII Grouping Plan | Project Name | Project Description (per March 2022 Phase 2 Petition) | Projected In-Service Date | Initial In-Service Date4 | 2025 YTD Spend | 2025 YTD Budget | 2025 Variance (Actuals - Approved) | Actual Spend To Date1 | Remaining Forecasted Cost | Total Approved Cost2 | Variance (Forecasted - Approved) | January 1, 2025 Filing Estimated Cost | Current Project Estimate (+50/-25%) | Explanation of Schedule and Cost Variance | Progress Made from Last Report3
Group 1 | NYSEG 230 kV Line 68 Full Rebuild | Rebuild the existing 24-mile 230 kV line with bundled 1192 Bunting ACSR conductor on an offset with steel H-Frame structures. | 2031 | 2029 | 0.6708 | 1.2358 | -0.56496 | 3.5288 | 168.8121 | 181.8 | -9.4591 | 182.7026 | 172.3409 | In-service date extended from 2030 to 2031 since prior report due to changes in construction outage sequencing within this Article VII bundle. Cost estimate remains within +/- 10% of last report. | Conceptual design complete and Article VII application submitted (Case 25-T-0246).
Group 1 | NYSEG 230 kV Line 69 Full Rebuild | Rebuild the existing 1-mile 230 kV line with 2156 Bluebird ACSR conductor on an offset with steel monopole structures. | 2029 | 2029 | 0.20922 | 0.4634 | -0.25418 | 1.1481 | 20.6266 | 34.7 | -12.9254 | 33.9823 | 21.7746 | In-service date accelerated from 2031 to 2029 since prior report due to changes in construction outage sequencing within this Article VII bundle. Significant cost reduction due to detailed engineering analysis confirming ability to repurpose half of the existing lattice towers. | Conceptual design complete and Article VII application submitted (Case 25-T-0246).
Group 1 | NYSEG 230 kV Line 72 Full Rebuild | Rebuild the existing 27-mile 230 kV line with 2156 Bluebird ACSR conductor on an offset with steel H-Frame structures. | 2031 | 2029 | 0.91487 | 0.86139 | 0.053474 | 3.8582 | 221.5232 | 224.4 | 0.98137 | 245.1817 | 225.3814 | In-service date accelerated from 2032 to 2031 since prior report due to changes in construction outage sequencing within this Article VII bundle. Cost estimate remains within +/- 10% of prior report. | Conceptual design complete and Article VII application submitted (Case 25-T-0246).
Group 2 | Bath 115/34.5 kV Substation Rebuild | Full rebuild of substation as 115 kV three-bay breaker-and-a-half (BAAH) air insulated substation (AIS) with two (2) new 115/34.5 kV 50 MVA transformers, a +150/-150 MVAR dynamic VAR compensation unit (STATCOM) | 2030 | 2027 | -0.058004 | 1.569 | -1.627 | 4.3854 | 128.0787 | 114 | 18.4641 | 145.922 | 145.922 | Cost estimate remains within +/- 10% of prior report. | Conceptual design completed. Procurement process of STATCOM and main equipment (transformer and circuit breaker) in progress.
Group 2 | Bennett 115/34.5 kV Substation Expansion and Upgrades and Power Flow Device | Partial rebuild of the substation with a 115kV bus expansion (extra position for interconnecting a new generator), a 0.05pu Power Flow Control Device, and terminal work on L725. | 2030 | 2025 | 0.25389 | 2.4478 | -2.1939 | 1.0178 | 41.5681 | 25.7 | 16.8858 | 42.0043 | 42.0043 | Cost estimate remains within +/- 10% of last reported. The current project estimate is at +20/-15 level of accuracy. | Conceptual design is complete. Procurement of long lead materials including smart valve and SF6-free breakers have started. Land acquisition for samrt valve is in progress.
Group 2 | NYSEG 115 kV Line 932 Power Flow Control Device & Structure Replacements | Install a Power Flow Control Device at Bennett Substation and p Perform in-kind structure replacements where required to address all asset condition issues. | 2026 | 2029 | 0.40505 | 0.26968 | 0.13537 | 0.8882 | 22.331 | 27.8 | -4.5808 | 23.2643 | 23.2643 | Cost estimate is within +/- 10% from prior report. The current cost estimate is at +20/-15 level of accuracy. | Detailed engineering has been completed and materials have been ordered. Waiting for permits to start construction.
Group 2 | NYSEG 115 kV Line 723 Full Rebuild | Rebuild the existing 15-mile 115 kV line with bundled 795 Drake ACSR conductor on an offset with light duty steel monopole structures. | 2029 | 2029 | 0.20535 | 0.39975 | -0.1944 | 1.1398 | 67.3549 | 75.86 | -7.3653 | 73.8711 | 73.8711 | Cost estimate remains within +/- 10% of prior report. The current project estimate is at +20/-15 level of accuracy. | Conceptual design is complete and the detailed engineering is in progress. Currently working on land title search and easements for the extended right-of-way and other required environmental studies .
Group 2 | NYSEG 115 kV Line 953 Full Rebuild | Rebuild the existing 5-mile 115 kV line with 2156 Bluebird ACSR conductor on an offset with light duty steel monopole structures. | 2028 | 2026 | 0.076866 | 0.36616 | -0.28929 | 1.1604 | 23.6897 | 18.09 | 6.7601 | 26.8969 | 26.8969 | Cost estimate remains within +/- 10% of prior report. The current cost estimate is at +20/-15 level of accuracy. | Conceptual design is complete and the detailed engineering is in progress. Currently working on land title search and easements for the extended right-of-way and other required environmental studies .
Group 2 | NYSEG 115 kV Line 965 Full Rebuild | Rebuild the existing 22-mile 115 kV line with bundled 795 Drake ACSR conductor on an offset with light duty steel monopole structures. | 2030 | 2029 | 0.29374 | 0.43005 | -0.13632 | 1.4088 | 79.3003 | 116.11 | -35.4009 | 87.121 | 87.121 | Cost estimate remains within +/- 10% of prior report. The current cost estimate is at +20/-15 level of accuracy. | Conceptual design is complete and the detailed engineering is in progress. Currently working on land title search and easements for the extended right-of-way and other required environmental studies .
Group 3 | NYSEG 115 kV Line 711 Full Rebuild | Rebuild the existing 3-mile 115 kV line with 2156 Bluebird ACSR conductor on an offset with light duty steel monopole structures. | 2029 | 2026 | 0.14273 | 0.17664 | -0.033907 | 0.69158 | 18.7003 | 11.1 | 8.2919 | 11.1674 | 11.1674 | Cost estimate remains within +/- 10% of prior report. | Conceptual design has been completed and planning for the start of detailed engineering.
Group 3 | NYSEG 115 kV Line 712 Full Rebuild | Rebuild the existing 6-mile 115 kV line with 2156 Bluebird ACSR conductor on an offset with light duty steel monopole structures. | 2029 | 2026 | 0.22533 | 0.32936 | -0.10404 | 0.90003 | 29.6558 | 23.6827 | 6.8732 | 23.6981 | 23.6981 | Cost estimate remains within +/- 10% of prior report. | Conceptual design has been completed and planning for the start of detailed engineering.
Group 3 | NYSEG 115 kV Line 935 Full Rebuild | Rebuild the existing 9-mile 115 kV line with 2156 Bluebird ACSR conductor on an offset with light duty steel monopole structures. | 2029 | 2026 | 0.20945 | 0.62663 | -0.41719 | 0.74798 | 31.1448 | 31.55 | 0.34282 | 32.0964 | 32.0964 | Cost estimate remains within +/- 10% of prior report. The current cost estimate is at +50/-25 level of accuracy. | Conceptual design has been completed and planning for additional engineering analysis required for alternative Hickling sites.
Group 3 | Stoney Ridge Transformer Replacement | Replace transformer Bank 1 with one (1) new 448 MVA transformer. | 2029 | 2024 | 0.20757 | 0.54592 | -0.33835 | 0.79133 | 36.6331 | 16.9 | 20.5245 | 36.6622 | 36.6622 | Cost estimate remains within +/- 10% of prior report. The current cost estimate is at +50/-25 level of accuracy. | Conceptual design has been completed and planning for the start of detailed engineering.
Group 3 | Hickling 115/34.5 kV Substation Rebuild | Full rebuild of the substation as a 115 kV four-bay breaker-and-a-half (BAAH) air insulated substation (AIS) design, two (2) new 115/34.5 kV 50 MVA transformers, a new 34.5 kV GIS straight bus with a tie breaker as well as a 12.5 kV GIS straight bus. | 2029 | 2027 | 0.67783 | 2.9221 | -2.2442 | 2.1592 | 133.9236 | 134.29 | 1.7928 | 143.2634 | 143.2634 | Cost estimate remains within +/- 10% of prior report. The current cost estimate is at +50/-25 level of accuracy. | Conceptual design and site alternative analysis has been completed. Planning further engineering evaluation of the impact of site location on the overall project scope and associated line re-routes.
Group 4 | Eelpot 115 kV Substation Expansion | Addition of a new 115 kV circuit breaker, a +150/-150 MVAR new dynamic VAR compensation unit (STATCOM), and 115 kV line terminal work. | 2031 | 2025 | 0.38023 | 5.0115 | -4.6313 | 1.3087 | 99.6372 | 76.66 | 24.2859 | 108.977 | 108.977 | In-service date accelerated from 2032 to 2031 since prior report due to changes in construction outage sequencing within this Article VII bundle resulting in acceleration of project completion date. Cost estimate remains within +/- 10% of prior report. | Conceptual design completed. Procurement process of STATCOM and main equipment (transformer and circuit breaker) in progress. STATCOM power updated to +150/-150 MVAR for operational and construction efficiencies.
Group 4 | Greenidge 115 kV Substation Upgrades | One (1) new 115 kV circuit breaker for Line 968, Line 968 terminal work, and a new 30 MVAR capacitor bank (with 115 kV circuit breaker). | 2031 | 2024 | 0.14011 | 0.32148 | -0.18137 | 0.66002 | 15.5564 | 17.24 | -1.0236 | 16.7205 | 16.7205 | In-service date extended from 2029 to 2031 since prior report due to changes in construction outage sequencing within this Article VII bundle resulting in extension of project completion date. Cost estimate remains within +/- 10% from prior report. | Conceptual design completed. Procurement process of main equipment in progress.
Group 4 | NYSEG 115 kV Line 722 Full Rebuild | Rebuild the existing 23-mile 115 kV line with 1590 Falcon ACSR conductor on an offset with light duty steel monopole structures. | 2031 | 2030 | 0.50939 | 1.281 | -0.77164 | 1.9726 | 130.3617 | 114.17 | 18.1643 | 131.3912 | 131.3912 | Cost estimate remains within +/- 10% of prior report. | Conceptual design in progress. Preliminary environmental, archeological, and historical field work in progress.
Group 4 | NYSEG 115 kV Line 724 Full Rebuild | Rebuild the existing 15-mile 115 kV line with 1590 Falcon ACSR conductor on an offset with light duty steel monopole structures. | 2031 | 2029 | 0.15327 | 0.75761 | -0.60433 | 1.1825 | 72.781 | 63.83 | 10.1335 | 66.4548 | 66.4548 | In-service date accelerated from 2033 to 2031 since prior report due to changes in construction outage sequencing within this Article VII bundle resulting in acceleration of project completion date. Cost estimate increased due to conceptual engineering (90% completion) and survey results showing the need for additional matting. | Conceptual design in progress. Preliminary environmental, archeological, and historical field work in progress.
Group 4 | NYSEG 115 kV Line 968 Full Rebuild | Rebuild the existing 5-mile 115 kV line with 1590 Falcon ACSR conductor on an offset with light duty steel monopole structures. | 2031 | 2026 | 0.30359 | 0.1702 | 0.13338 | 0.88589 | 26.0123 | 18.48 | 8.4182 | 19.4322 | 19.4322 | Cost estimate remains within +/- 10% of prior report. | Conceptual design in progress. Preliminary environmental, archeological, and historical field work in progress.
Group 5 | Watercure 345/230/115 kV Substation Expansion | Expand the 345 kV two-bay breaker-and-a-half (BAAH) with an extra bay that has one (1) empty bay position, adding a three-bay BAAH for a 115 kV addition, rerouting the Hillside 115 kV lines to Watercure Road’s new 115 kV BAAH, and adding one (1) new 345/115 kV three winding 448 MVA transformer. The transformer will connect with the new 115 kV BAAH and the 345 kV BAAH expansion. | 2029 | 2027 | 0.45763 | 2.4053 | -1.9477 | 2.7545 | 100.3598 | 138.3 | -35.1857 | 111.4115 | 111.4115 | Cost estimate remains within +/- 10% of prior report. | Article VII application submitted (Case 25-T-0080).
Group 5 | Hillside 230/115/34.5 kV Substation Upgrades | Decommissioning the substation’s 115 kV bus work, decommissioning the two (2) 115/34.5 kV transformers (Banks 1 and 2), re-routing the 115 kV lines to a new 115 kV at Watercure Road substation (at least 1.3 miles), replacing two 230 kV breakers, separating the 34.5 kV breaker position of Bank 3 and 4 (new 34.5 kV breaker and position for Bank 3), grounding the 115 kV side at the 230 kV transformers. | 2032 | 2027 (230 kV work by 2024) | 0.11032 | 0.25399 | -0.14367 | 0.48381 | 11.7742 | 10.17 | 2.088 | 12.4825 | 12.4825 | In-service date delayed due to dependencies on other permit applications before decommissioning work can commence. Cost estimate remains within +/- 10% of prior report. | Constructability, outage sequencing and access plans initiated.
Group 5 | Montour Falls 115/34.5 kV Substation Rebuild | Full rebuild of the substation as a four-bay breaker-and-a-half (BAAH) air insulated substation (AIS) design, two (2) new 115/34.5 kV 50 MVA transformers, two (2) new 115 kV 30 MVAR capacitor banks, a new 34.5 kV GIS straight bus, well as a 12.5 kV GIS straight bus (converted from 8.3 kV). | 2031 | 2027 | 0.42645 | 2.816 | -2.3896 | 2.4395 | 142.7222 | 135.94 | 9.2217 | 166.2943 | 166.2943 | Cost estimate remains within +/- 10% of prior report. The current project estimate is at +20/-15 level of accuracy. | Substations conceptual design complete . Reroute conceptual design in progress. Procurement of long lead items in progress. Preliminary environmental field work has been completed.
Group 5 | NYSEG 115 kV Line 978 Full Rebuild | 115 kV Line 978 is double circuit with 115 kV Line 963 from Montour Falls to Ridge Road to Hillside. Rebuild the existing 16-mile double circuit line with 1192 Bunting ACSR 1590 Falcon ACSR from Montour Falls to Ridge Road and 1192 Bunting ACSR 1590 Falcon ACSR from Ridge Road to Hilliside. The new double circuit line would be rebuilt on an offset with custom steel structures. | 2031 | 2029 | 0.18455 | 0.58172 | -0.39718 | 1.1155 | 79.3737 | 74.61 | 5.8792 | 87.5952 | 87.5952 | Cost estimate remains within +/- 10% of prior report. The current project estimate is at +20/-15 level of accuracy. | Conceptual design and preliminary environmental field work have been completed.
Group 5 | NYSEG 115 kV Line 963 Partial Rebuild | 115 kV Line 963 is double circuit with 115 kV Line 978 from Montour Falls to Ridge Road to Hillside. Rebuild the existing 16-mile double circuit line with 1590 Falcon ACSR from Montour Falls to Ridge Road and 1590 Falcon ACSR from Ridge Road to Hilliside. The new double circuit line would be rebuilt on an offset with custom steel structures. | 2031 | 2029 | 0.28355 | 0.38595 | -0.10239 | 1.309 | 80.0507 | 74.61 | 6.7497 | 87.6631 | 87.6631 | Costs remain within +/- 10% of last reported. The current project estimate is at +20/-15 level of accuracy. | Conceptual design and preliminary environmental field work have been completed.
Group 6 | NYSEG 230 kV Line 67 Full Rebuild | Rebuild the existing 11-mile 230 kV line with bundled 1192 Bunting ACSR conductor on an offset with steel monopole structures. | 2031 | 2029 | 0.6854 | 1.9608 | -1.2754 | 1.9038 | 85.991 | 93.05 | -5.1551 | 95.0408 | 95.0408 | Cost estimate remains within +/- 10% of prior report. The current project estimate is at +20/-15 level of accuracy. | Conceptual design complete and currently working on permit applications and supporting exhibits.
Group 7 | RGE 115 kV Line 906 Full Rebuild | Rebuild the existing 30-mile 115 kV line with 1590 Falcon ACSR conductor on an offset with light duty steel monopole structures. | 2031 | 2030 | 0.41885 | 1.8283 | -1.4095 | 1.9394 | 157.8141 | 156.81 | 2.9435 | 159.7869 | 159.7869 | Cost estimate remains within +/- 10% of prior report. The current project estimate is at +50/-25 level of accuracy. | Concpetual design is in progress and evaluating the need for mico reroutes around the existing center line due to found conditions in the field.
Group 8 | NYSEG 115 kV Line 934 Full Rebuild | Rebuild the existing 19-mile 115 kV line with 795 Drake ACSR conductor on an offset with light duty steel monopole structures. | 2030 | 2029 | 0.45255 | 2.1551 | -1.7025 | 2.569 | 90.268 | 89.39 | 3.4469 | 91.3501 | 91.3501 | Project on track to be submitted as Article VII vs Article VIII resulting in acceleration of In-service date from 2032 to 2030. Cost estimate remains within +/- 10% from prior report. | Conceptual design 95% completion. Article VII application in progress.
Group 9 | NYSEG 34.5 kV Line 539 Partial Rebuild | Rebuild 2 miles from Marshall to Marsh Hill of the existing 13-mile 34.5 kV line with 477 Pelican ACSR conductor on an offset with light duty steel monopole structures. | N/A | 2026 | 0.011739 | 0.50307 | -0.49134 | 0.40767 | 0 | 8.2 | -7.7923 | 12.2727 | 0.40767 | This project has been removed from PNY scope after a detailed ratings review of the lines and terminal ends. The ratings review and drone inspection demonstrated that the existing conductor satisfied the needs of CLCPA II.
Group 9 | NYSEG 34.5 kV Line 542 Full Rebuild | Rebuild the existing 6-mile 34.5 kV line with 477 Pelican ACSR conductor on an offset with light duty steel monopole structures. | 2027 | 2026 | 0.29667 | 0.57666 | -0.27998 | 1.0477 | 26.8703 | 21.84 | 6.078 | 27.7977 | 27.7977 | Cost estimate remains within +/- 10% from prior report. The current project estimate is at +15/-10 level of accuracy. | Detailed design is 95% complete and currently working on procurement of materials and construction permits.
Group 9 | NYSEG 34.5 kV Line 546 Partial Rebuild | Rebuild 8 miles of 34.5 kV line from Troupsburg to Marsh Hill with 477 Pelican ACSR conductor on an offset with light duty steel monopole structures. Rebuild 3 miles of the existing 8-mile 34.5 kV line from Troupsburg to Woodhull with 477 Pelican conductor on an offset with light duty steel monopole structures. | 2027 | 2026 | 0.35038 | 2.2606 | -1.9102 | 1.2647 | 49.4931 | 42.75 | 8.0078 | 61.2893 | 61.2893 | Cost estimate remains within +/- 10% from prior report. The current project estimate is at +15/-10 level of accuracy. | Detailed design is 95% complete and currently working on procurement of materials and construction permits.
Group 9 | NYSEG 34.5 kV Line 565 Full Rebuild | Rebuild the existing 8-mile 34.5 kV line with 477 Pelican ACSR conductor on an offset with light duty steel monopole structures. | 2027 | 2026 | 0.74503 | 0.3652 | 0.37983 | 1.5081 | 33.4336 | 30.97 | 3.9716 | 38.9096 | 38.9096 | Cost estimate is within +/- 10% from prior report. The current project estimate is at +15/-10 level of accuracy. | Detailed design is 95% complete and currently working on procurement of materials and construction permits.
Group 9 | Minor Substation Upgrades | Terminal Equipment at the following stations will be replaced. Final Scopes to be confirmed. Moraine Rd: ISD 2025 Flat St Spencer Hill Yawger Rd Caton Ave West Erie Ave Sta 128 Sullivan Park | 2033 | 2028 | 0.18687 | 0.34847 | -0.1616 | 0.66562 | 10.8394 | 9.2 | 2.305 | 10.0114 | 10.0114 | Several Minor SS Upgrades are being incorporated into the Article VII/Article VIII application resulting in extension of final project in sevice date from 2032 - 2033. | Moraine SS- energized May 2025. Project closure in progress.
Group 10 | NYSEG 115 kV Line 910 Full Rebuild | Rebuild the existing 11-mile 115 kV line with 795 Drake ACSR conductor on an offset with light duty steel monopole structures. | 2031 | 2030 | 0.52481 | 0.45499 | 0.069828 | 1.9375 | 51.5916 | 39 | 14.5291 | 57.2085 | 53.5291 | In-service date accelerated from 2032 to 2031 due to improvement in estimated permitting durations. Cost estimate remains within +/- 10% of prior report. | Conceptual design complete and Article VII application submitted (Case 25-T-0236).
Note 1: Actual Spend to Date is through 5+7 (May 31, 2025). |  |  |  |  | 0.0067813 | 0.01398 |  | 0.14188 | 2.0451 |  |  | 2469.9232 | 2412.0091
Note 2: Total Approved Cost based on the State of New York Public Service Commission’s Case 20-E-0197: Order Approving Phase 2 Areas Of Concern Transmission Upgrades, February 16, 2023. |  |  |  |  | 0 | 0 |  | 0 | 0
Note 3: For all projects, we have performed scope validation, reviewed existing property rights and preparing RFP for engineering. Developed Resource Management Plan, Procurement plan and Article 7 Submission permitting plan strategy. |  |  |  |  | 0 | 0 |  | 0 | 0
Note 4: ISD based on original petition filed in March of 2022
Note 5: 2024 YTD Budget based on budget data through 5+7 (May 31, 2025).
Note 6: Article 7 two year approval period includes EMCP approvals
Note 7: An explanation of variances exceeding ten percent have been provided. Variances below $1M are not explained in detail due to the inherent variability of the relatively small budgets for most projects.

## 6-20 ISDs P6 (hidden)
U-Project Definition | Activity Name | Finish | ISD
UH-N0006900 | In Service Date (ISD) | 29-Jun-29* | 29-Jun-29
UH-N0006902 | In Service Date (ISD) | 07-Oct-30* | 2030-10-07
UH-N0006904 | In Service Date (ISD) | 07-Jun-30* | 2030-06-07
UH-N0006906 | In Service Date (ISD) | 18-Nov-30* | 2030-11-18
UH-N0006908 | In Service Date (ISD) | 07-Jan-27* | 07-Jan-27
UH-N0006910 | In Service Date (ISD) | 30-Jun-27* | 30-Jun-27
UH-N0006912 | In Service Date (ISD) | 08-Dec-28* | 08-Dec-28
UH-N0006914 | In Service Date (ISD) | 25-Apr-29* | 25-Apr-29
UH-N0006916 | In Service Date (ISD) | 08-Dec-28* | 08-Dec-28
UH-N0006918 | In Service Date (ISD) | 13-Oct-28* | 13-Oct-28
UH-N0006920 | In Service Date (ISD) | 17-Oct-28* | 17-Oct-28
UH-N0006922 | In Service Date (ISD) | 11-Oct-29* | 11-Oct-29
UH-N0006924 | In Service Date (ISD) | 10-May-28* | 10-May-28
UH-N0006926 | In Service Date (ISD) | 01-Apr-30* | 2030-04-01
UH-N0006928 | In Service Date (ISD) | 08-Feb-30* | 2030-02-08
UH-N0006930 | In Service Date (ISD) | 08-Dec-28* | 08-Dec-28
UH-N0006932 | In Service Date (ISD) | 02-Jul-29* | 02-Jul-29
UH-N0006934 | In Service Date (ISD) | 05-Mar-26* | 05-Mar-26
UH-N0006936 | In Service Date (ISD) | 13-Aug-26* | 13-Aug-26
UH-N0006938 | In Service Date (ISD) | 18-Dec-26* | 18-Dec-26
UH-N0006940 | In Service Date (ISD) | 07-Oct-26* | 07-Oct-26
UH-N0006942 | In Service Date (ISD) | 21-Aug-30* | 2030-08-21
UH-N0006944 | ISD | 31-Jan-28* | 31-Jan-28
UH-N0006946 | ISD | 12-Jun-29* | 12-Jun-29
UH-N0006948 | ISD | 07-Nov-28* | 07-Nov-28
UH-N0006950 | ISD | 08-Nov-28* | 08-Nov-28
UH-N0006952 | In Service Date (ISD) | 04-Apr-29* | 04-Apr-29
UH-N0006954 | ISD | 31-Jul-29* | 31-Jul-29
UH-N0006956 | ISD | 27-Sep-29* | 27-Sep-29
UH-N0006958 | ISD | 23-Jan-29* | 23-Jan-29
UH-N0006960 | ISD | 16-Jul-30* | 2030-07-16
UH-N0006962 | ISD | 07-Apr-31* | 07-Apr-31
UH-N0006962 | ISD | 03-Jul-30* | 2030-07-03
UH-R0005910 | In Service Date (ISD) | 30-Apr-30* | 2030-04-30
UH-R0005912 | ISD | 17-Dec-30* | 2030-12-17

## 2023 PPR (hidden)
Month |  |  | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Oct | Oct | Oct | Oct | Oct | Oct | Oct | Oct | Oct | Oct | Nov | Nov | Nov | Nov | Nov | Nov | Nov | Nov | Nov | Nov | Dec | Dec | Dec | Dec | Dec | Dec | Dec | Dec | Dec | Dec | Total | Total | Total | Total | Total | Total | Total | Total | Total | Total
Project Def | Project Name | Project PM | EOY | Plan | Variance($) | EOY Cum | Plan Cum | Variance Cum($) | EOY Contribution | EOY Production | EOY Int | EOY Ext | EOY | Plan | Variance($) | EOY Cum | Plan Cum | Variance Cum($) | EOY Contribution | EOY Production | EOY Int | EOY Ext | EOY | Plan | Variance($) | EOY Cum | Plan Cum | Variance Cum($) | EOY Contribution | EOY Production | EOY Int | EOY Ext | EOY | Plan | Variance($) | EOY Cum | Plan Cum | Variance Cum($) | EOY Contribution | EOY Production | EOY Int | EOY Ext | EOY | Plan | Variance($) | EOY Cum | Plan Cum | Variance Cum($) | EOY Contribution | EOY Production | EOY Int | EOY Ext
UH-N0006900 | CLCPA Phase II Lines - Line 67 | Salvador Cordero | 13170.88 |  | 13170.88 | 13170.88 |  | 13170.88 | 0 | 13170.88 | 13008.95 | 161.93 | 15267.99 |  | 15267.99 | 28438.87 |  | 28438.87 | 0 | 15267.99 | 9583.83 | 5684.16 | 80371.7 |  | 80371.7 | 108810.57 |  | 108810.57 | 0 | 80371.7 | 31773.09 | 48598.61 | 77313.63 |  | 77313.63 | 186124.2 |  | 186124.2 | 0 | 77313.63 | 36000.95 | 41312.68 | 186124.2 |  | 186124.2 | 186124.2 |  | 186124.2 | 0 | 186124.2 | 90366.82 | 95757.38
UH-N0006902 | CLCPA Phase II Lines - Line 68 | Gideon Oppong Darko | 4005.32 |  | 4005.32 | 4005.32 |  | 4005.32 | 0 | 4005.32 | 4005.32 | 0 | 12174.02 |  | 12174.02 | 16179.34 |  | 16179.34 | 0 | 12174.02 | 7219.14 | 4954.88 | 25853.96 |  | 25853.96 | 42033.3 |  | 42033.3 | 0 | 25853.96 | 18412.62 | 7441.34 | 37541.26 |  | 37541.26 | 79574.56 |  | 79574.56 | 0 | 37541.26 | 27569.43 | 9971.83 | 79574.56 |  | 79574.56 | 79574.56 |  | 79574.56 | 0 | 79574.56 | 57206.51 | 22368.05
UH-N0006904 | CLCPA Phase II Lines - Line 69 | Gideon Oppong Darko | 3307.03 |  | 3307.03 | 3307.03 |  | 3307.03 | 0 | 3307.03 | 3307.03 | 0 | 8208.66 |  | 8208.66 | 11515.69 |  | 11515.69 | 0 | 8208.66 | 5312.66 | 2896 | 20262.32 |  | 20262.32 | 31778.01 |  | 31778.01 | 0 | 20262.32 | 15436.26 | 4826.06 | 32506.86 |  | 32506.86 | 64284.87 |  | 64284.87 | 0 | 32506.86 | 21918.96 | 10587.9 | 64284.87 |  | 64284.87 | 64284.87 |  | 64284.87 | 0 | 64284.87 | 45974.91 | 18309.96
UH-N0006906 | CLCPA Phase II Lines - Line 72 | Gideon Oppong Darko | 3307.03 |  | 3307.03 | 3307.03 |  | 3307.03 | 0 | 3307.03 | 3307.03 | 0 | 8797.81 |  | 8797.81 | 12104.84 |  | 12104.84 | 0 | 8797.81 | 5177.81 | 3620 | 17843.87 |  | 17843.87 | 29948.71 |  | 29948.71 | 0 | 17843.87 | 11991.31 | 5852.56 | 33137.5 |  | 33137.5 | 63086.21 |  | 63086.21 | 0 | 33137.5 | 24003.08 | 9134.42 | 63086.21 |  | 63086.21 | 63086.21 |  | 63086.21 | 0 | 63086.21 | 44479.23 | 18606.98
UH-N0006908 | CLCPA Phase II Lines - Line 711 | Salvador Cordero | 11761.34 |  | 11761.34 | 11761.34 |  | 11761.34 | 0 | 11761.34 | 11761.34 | 0 | 20777.45 |  | 20777.45 | 32538.79 |  | 32538.79 | 0 | 20777.45 | 11914.11 | 8863.34 | 46648.54 |  | 46648.54 | 79187.33 |  | 79187.33 | 0 | 46648.54 | 21324.85 | 25323.69 | 26032.73 |  | 26032.73 | 105220.06 |  | 105220.06 | 0 | 26032.73 | 18455.03 | 7577.7 | 105220.06 |  | 105220.06 | 105220.06 |  | 105220.06 | 0 | 105220.06 | 63455.33 | 41764.73
UH-N0006910 | CLCPA Phase II Lines - Line 712 | Salvador Cordero | 11093.57 |  | 11093.57 | 11093.57 |  | 11093.57 | 0 | 11093.57 | 11093.57 | 0 | 21398.95 |  | 21398.95 | 32492.52 |  | 32492.52 | 0 | 21398.95 | 12535.61 | 8863.34 | 50276.84 |  | 50276.84 | 82769.36 |  | 82769.36 | 0 | 50276.84 | 23387.3 | 26889.54 | 21434.77 |  | 21434.77 | 104204.13 |  | 104204.13 | 0 | 21434.77 | 13693.9 | 7740.87 | 104204.13 |  | 104204.13 | 104204.13 |  | 104204.13 | 0 | 104204.13 | 60710.38 | 43493.75
UH-N0006912 | CLCPA Phase II Lines - Line 722 | Noellia Fernandez | 3561.6 |  | 3561.6 | 3561.6 |  | 3561.6 | 0 | 3561.6 | 3480.63 | 80.97 | 11524.96 |  | 11524.96 | 15086.56 |  | 15086.56 | 0 | 11524.96 | 7180.96 | 4344 | 67446.79 |  | 67446.79 | 82533.35 |  | 82533.35 | 0 | 67446.79 | 25841.18 | 41605.61 | 30556.88 |  | 30556.88 | 113090.23 |  | 113090.23 | 0 | 30556.88 | 17856.39 | 12700.49 | 113090.23 |  | 113090.23 | 113090.23 |  | 113090.23 | 0 | 113090.23 | 54359.16 | 58731.07
UH-N0006914 | CLCPA Phase II Lines - Line 723 | Gideon Oppong Darko | 2434.16 |  | 2434.16 | 2434.16 |  | 2434.16 | 0 | 2434.16 | 2434.16 | 0 | 7972.55 |  | 7972.55 | 10406.71 |  | 10406.71 | 0 | 7972.55 | 4352.55 | 3620 | 15193.4 |  | 15193.4 | 25600.11 |  | 25600.11 | 0 | 15193.4 | 7090.76 | 8102.64 | 21372.42 |  | 21372.42 | 46972.53 |  | 46972.53 | 0 | 21372.42 | 10858 | 10514.42 | 46972.53 |  | 46972.53 | 46972.53 |  | 46972.53 | 0 | 46972.53 | 24735.47 | 22237.06
UH-N0006916 | CLCPA Phase II Lines - Line 724 | Noellia Fernandez | 7279.69 |  | 7279.69 | 7279.69 |  | 7279.69 | 0 | 7279.69 | 7198.72 | 80.97 | 9395.67 |  | 9395.67 | 16675.36 |  | 16675.36 | 0 | 9395.67 | 5775.67 | 3620 | 21578.58 |  | 21578.58 | 38253.94 |  | 38253.94 | 0 | 21578.58 | 10953.09 | 10625.49 | 23055.04 |  | 23055.04 | 61308.98 |  | 61308.98 | 0 | 23055.04 | 11102.22 | 11952.82 | 61308.98 |  | 61308.98 | 61308.98 |  | 61308.98 | 0 | 61308.98 | 35029.7 | 26279.28
UH-N0006918 | CLCPA Phase II Lines - Line 932 | Gideon Oppong Darko | [10 empty] | 6018.75 |  | 6018.75 | 6018.75 |  | 6018.75 | 0 | 6018.75 | 3122.75 | 2896 | 9090.99 |  | 9090.99 | 15109.74 |  | 15109.74 | 0 | 9090.99 | 4264.93 | 4826.06 | 12638.73 |  | 12638.73 | 27748.47 |  | 27748.47 | 0 | 12638.73 | 5147.8 | 7490.93 | 27748.47 |  | 27748.47 | 27748.47 |  | 27748.47 | 0 | 27748.47 | 12535.48 | 15212.99
UH-N0006920 | CLCPA Phase II Lines - Line 934 | Noellia Fernandez | 1409.52 |  | 1409.52 | 1409.52 |  | 1409.52 | 0 | 1409.52 | 1247.59 | 161.93 | 15724.22 |  | 15724.22 | 17133.74 |  | 17133.74 | 0 | 15724.22 | 10040.06 | 5684.16 | 71128.66 |  | 71128.66 | 88262.4 |  | 88262.4 | 0 | 71128.66 | 26592.41 | 44536.25 | 82024.16 |  | 82024.16 | 170286.56 |  | 170286.56 | 0 | 82024.16 | 51737.17 | 30286.99 | 170286.56 |  | 170286.56 | 170286.56 |  | 170286.56 | 0 | 170286.56 | 89617.23 | 80669.33
UH-N0006922 | CLCPA Phase II Lines - Line 935 | Salvador Cordero | 1194.47 |  | 1194.47 | 1194.47 |  | 1194.47 | 0 | 1194.47 | 1194.47 | 0 | 15926.05 |  | 15926.05 | 17120.52 |  | 17120.52 | 0 | 15926.05 | 9608.77 | 6317.28 | 7403.47 |  | 7403.47 | 24523.99 |  | 24523.99 | 0 | 7403.47 | 3627.81 | 3775.66 | 42924.4 |  | 42924.4 | 67448.39 |  | 67448.39 | 0 | 42924.4 | 15415.19 | 27509.21 | 67448.39 |  | 67448.39 | 67448.39 |  | 67448.39 | 0 | 67448.39 | 29846.24 | 37602.15
UH-N0006924 | CLCPA Phase II Lines - Line 953 | Gideon Oppong Darko | [10 empty] | 5256.26 |  | 5256.26 | 5256.26 |  | 5256.26 | 0 | 5256.26 | 5256.26 | 0 | 9879.83 |  | 9879.83 | 15136.09 |  | 15136.09 | 0 | 9879.83 | 9400.97 | 478.86 | 25840.74 |  | 25840.74 | 40976.83 |  | 40976.83 | 0 | 25840.74 | 22361.45 | 3479.29 | 40976.83 |  | 40976.83 | 40976.83 |  | 40976.83 | 0 | 40976.83 | 37018.68 | 3958.15
UH-N0006926 | CLCPA Phase II Lines - Line 963 | Gideon Oppong Darko | 174.57 |  | 174.57 | 174.57 |  | 174.57 | 0 | 174.57 | 174.57 | 0 | 14105.74 |  | 14105.74 | 14280.31 |  | 14280.31 | 0 | 14105.74 | 10535.99 | 3569.75 | 8929.67 |  | 8929.67 | 23209.98 |  | 23209.98 | 0 | 8929.67 | 3782.33 | 5147.34 | 19959.1 |  | 19959.1 | 43169.08 |  | 43169.08 | 0 | 19959.1 | 13002.01 | 6957.09 | 43169.08 |  | 43169.08 | 43169.08 |  | 43169.08 | 0 | 43169.08 | 27494.9 | 15674.18
UH-N0006928 | CLCPA Phase II Lines - Line 965 | Gideon Oppong Darko | [10 empty] | 5057.2 |  | 5057.2 | 5057.2 |  | 5057.2 | 0 | 5057.2 | 2885.2 | 2172 | 6310.44 |  | 6310.44 | 11367.64 |  | 11367.64 | 0 | 6310.44 | 2490.28 | 3820.16 | 14322.24 |  | 14322.24 | 25689.88 |  | 25689.88 | 0 | 14322.24 | 8011.95 | 6310.29 | 25689.88 |  | 25689.88 | 25689.88 |  | 25689.88 | 0 | 25689.88 | 13387.43 | 12302.45
UH-N0006930 | CLCPA Phase II Lines - Line 968 | Noellia Fernandez | 3532.85 |  | 3532.85 | 3532.85 |  | 3532.85 | 0 | 3532.85 | 3451.88 | 80.97 | 8334.56 |  | 8334.56 | 11867.41 |  | 11867.41 | 0 | 8334.56 | 7610.56 | 724 | 15923.15 |  | 15923.15 | 27790.56 |  | 27790.56 | 0 | 15923.15 | 9336.94 | 6586.21 | 37206.94 |  | 37206.94 | 64997.5 |  | 64997.5 | 0 | 37206.94 | 14365.05 | 22841.89 | 64997.5 |  | 64997.5 | 64997.5 |  | 64997.5 | 0 | 64997.5 | 34764.43 | 30233.07
UH-N0006932 | CLCPA Phase II Lines - Line 978 | Gideon Oppong Darko | 174.57 |  | 174.57 | 174.57 |  | 174.57 | 0 | 174.57 | 174.57 | 0 | 6977.07 |  | 6977.07 | 7151.64 |  | 7151.64 | 0 | 6977.07 | 3357.07 | 3620 | 20601.25 |  | 20601.25 | 27752.89 |  | 27752.89 | 0 | 20601.25 | 15521.26 | 5079.99 | 33603.33 |  | 33603.33 | 61356.22 |  | 61356.22 | 0 | 33603.33 | 25536.08 | 8067.25 | 61356.22 |  | 61356.22 | 61356.22 |  | 61356.22 | 0 | 61356.22 | 44588.98 | 16767.24
UH-N0006934 | CLCPA Phase II Lines - Line 539 | Gideon Oppong Darko | [10 empty] | 3134.08 |  | 3134.08 | 3134.08 |  | 3134.08 | 0 | 3134.08 | 2410.08 | 724 | 3097.36 |  | 3097.36 | 6231.44 |  | 6231.44 | 0 | 3097.36 | 1825.47 | 1271.89 | 6261.2 |  | 6261.2 | 12492.64 |  | 12492.64 | 0 | 6261.2 | 5189.05 | 1072.15 | 12492.64 |  | 12492.64 | 12492.64 |  | 12492.64 | 0 | 12492.64 | 9424.6 | 3068.04
UH-N0006936 | CLCPA Phase II Lines - Line 542 | Gideon Oppong Darko | [10 empty] | 4065.12 |  | 4065.12 | 4065.12 |  | 4065.12 | 0 | 4065.12 | 3341.12 | 724 | 6382.45 |  | 6382.45 | 10447.57 |  | 10447.57 | 0 | 6382.45 | 5020.56 | 1361.89 | 13041.12 |  | 13041.12 | 23488.69 |  | 23488.69 | 0 | 13041.12 | 11968.97 | 1072.15 | 23488.69 |  | 23488.69 | 23488.69 |  | 23488.69 | 0 | 23488.69 | 20330.65 | 3158.04
UH-N0006938 | CLCPA Phase II Lines - Line 546 | Gideon Oppong Darko | [10 empty] | 4468.07 |  | 4468.07 | 4468.07 |  | 4468.07 | 0 | 4468.07 | 3020.07 | 1448 | 8041.64 |  | 8041.64 | 12509.71 |  | 12509.71 | 0 | 8041.64 | 5430.47 | 2611.17 | 11330.06 |  | 11330.06 | 23839.77 |  | 23839.77 | 0 | 11330.06 | 8861.43 | 2468.63 | 23839.77 |  | 23839.77 | 23839.77 |  | 23839.77 | 0 | 23839.77 | 17311.97 | 6527.8
UH-N0006940 | CLCPA Phase II Lines - Line 565 | Gideon Oppong Darko | [10 empty] | 961.56 |  | 961.56 | 961.56 |  | 961.56 | 0 | 961.56 | 237.56 | 724 | 3097.36 |  | 3097.36 | 4058.92 |  | 4058.92 | 0 | 3097.36 | 1825.47 | 1271.89 | 7273.61 |  | 7273.61 | 11332.53 |  | 11332.53 | 0 | 7273.61 | 5972.66 | 1300.95 | 11332.53 |  | 11332.53 | 11332.53 |  | 11332.53 | 0 | 11332.53 | 8035.69 | 3296.84
UH-N0006942 | CLCPA Phase II Lines - Willis – Malone | Andrew Schimek | 174.57 |  | 174.57 | 174.57 |  | 174.57 | 0 | 174.57 | 174.57 | 0 | 5006.4 |  | 5006.4 | 5180.97 |  | 5180.97 | 0 | 5006.4 | 1492.4 | 3514 | 9229.59 |  | 9229.59 | 14410.56 |  | 14410.56 | 0 | 9229.59 | 6884.59 | 2345 | 19471.16 |  | 19471.16 | 33881.72 |  | 33881.72 | 0 | 19471.16 | 14217.74 | 5253.42 | 33881.72 |  | 33881.72 | 33881.72 |  | 33881.72 | 0 | 33881.72 | 22769.3 | 11112.42
UH-N0006944 | CLCPA Phase II - SS - Bath | Zoran Oluic | 2259.59 |  | 2259.59 | 2259.59 |  | 2259.59 | 0 | 2259.59 | 2259.59 | 0 | 5976.99 |  | 5976.99 | 8236.58 |  | 8236.58 | 0 | 5976.99 | 3080.99 | 2896 | 78794.4 |  | 78794.4 | 87030.98 |  | 87030.98 | 0 | 78794.4 | 25881.57 | 52912.83 | 35103.25 |  | 35103.25 | 122134.23 |  | 122134.23 | 0 | 35103.25 | 26440.12 | 8663.13 | 122134.23 |  | 122134.23 | 122134.23 |  | 122134.23 | 0 | 122134.23 | 57662.27 | 64471.96
UH-N0006946 | CLCPA Phase II - SS - Bennett | Zoran Oluic | 2259.59 |  | 2259.59 | 2259.59 |  | 2259.59 | 0 | 2259.59 | 2259.59 | 0 | 4884.98 |  | 4884.98 | 7144.57 |  | 7144.57 | 0 | 4884.98 | 2712.98 | 2172 | 57335.84 |  | 57335.84 | 64480.41 |  | 64480.41 | 0 | 57335.84 | 19140.76 | 38195.08 | 22002.02 |  | 22002.02 | 86482.43 |  | 86482.43 | 0 | 22002.02 | 12623.39 | 9378.63 | 86482.43 |  | 86482.43 | 86482.43 |  | 86482.43 | 0 | 86482.43 | 36736.72 | 49745.71
UH-N0006948 | CLCPA Phase II - SS - Eelpot | Noellia Fernandez | 2259.59 |  | 2259.59 | 2259.59 |  | 2259.59 | 0 | 2259.59 | 2259.59 | 0 | 7561.56 |  | 7561.56 | 9821.15 |  | 9821.15 | 0 | 7561.56 | 5389.56 | 2172 | 53122.58 |  | 53122.58 | 62943.73 |  | 62943.73 | 0 | 53122.58 | 19069.84 | 34052.74 | 78358.41 |  | 78358.41 | 141302.14 |  | 141302.14 | 0 | 78358.41 | 48729.01 | 29629.4 | 141302.14 |  | 141302.14 | 141302.14 |  | 141302.14 | 0 | 141302.14 | 75448 | 65854.14
UH-N0006950 | CLCPA Phase II - SS - Greenidge | Noellia Fernandez | [10 empty] | 10099.69 |  | 10099.69 | 10099.69 |  | 10099.69 | 0 | 10099.69 | 8651.69 | 1448 | 21379.24 |  | 21379.24 | 31478.93 |  | 31478.93 | 0 | 21379.24 | 10441.62 | 10937.62 | 24009.84 |  | 24009.84 | 55488.77 |  | 55488.77 | 0 | 24009.84 | 17606.69 | 6403.15 | 55488.77 |  | 55488.77 | 55488.77 |  | 55488.77 | 0 | 55488.77 | 36700 | 18788.77
UH-N0006952 | CLCPA Phase II - SS - Hickling | Salvador Cordero | [10 empty] | 61390.26 |  | 61390.26 | 61390.26 |  | 61390.26 | 0 | 61390.26 | 20930.42 | 40459.84 | 13996.13 |  | 13996.13 | 75386.39 |  | 75386.39 | 0 | 13996.13 | 8617.57 | 5378.56 | 107034.89 |  | 107034.89 | 182421.28 |  | 182421.28 | 0 | 107034.89 | 41057.52 | 65977.37 | 182421.28 |  | 182421.28 | 182421.28 |  | 182421.28 | 0 | 182421.28 | 70605.51 | 111815.77
UH-N0006954 | CLCPA Phase II - SS - Hillside | Zoran Oluic | [10 empty] | 5057.2 |  | 5057.2 | 5057.2 |  | 5057.2 | 0 | 5057.2 | 2885.2 | 2172 | 15398.4 |  | 15398.4 | 20455.6 |  | 20455.6 | 0 | 15398.4 | 3804.27 | 11594.13 | 16681.44 |  | 16681.44 | 37137.04 |  | 37137.04 | 0 | 16681.44 | 9010.89 | 7670.55 | 37137.04 |  | 37137.04 | 37137.04 |  | 37137.04 | 0 | 37137.04 | 15700.36 | 21436.68
UH-N0006956 | CLCPA Phase II - SS - Montour Falls | Zoran Oluic | [10 empty] | 10244.3 |  | 10244.3 | 10244.3 |  | 10244.3 | 0 | 10244.3 | 5738.37 | 4505.93 | 28538.71 |  | 28538.71 | 38783.01 |  | 38783.01 | 0 | 28538.71 | 9211.72 | 19326.99 | 91303.53 |  | 91303.53 | 130086.54 |  | 130086.54 | 0 | 91303.53 | 58373.21 | 32930.32 | 130086.54 |  | 130086.54 | 130086.54 |  | 130086.54 | 0 | 130086.54 | 73323.3 | 56763.24
UH-N0006958 | CLCPA Phase II - SS - Stoney Ridge | Salvador Cordero | [10 empty] | 41173.19 |  | 41173.19 | 41173.19 |  | 41173.19 | 0 | 41173.19 | 15935.67 | 25237.52 | 7872.82 |  | 7872.82 | 49046.01 |  | 49046.01 | 0 | 7872.82 | 6072.82 | 1800 | 54638.98 |  | 54638.98 | 103684.99 |  | 103684.99 | 0 | 54638.98 | 24090.69 | 30548.29 | 103684.99 |  | 103684.99 | 103684.99 |  | 103684.99 | 0 | 103684.99 | 46099.18 | 57585.81
UH-N0006960 | CLCPA Phase II - SS - Watercure | Zoran Oluic | [10 empty] | 6242.86 |  | 6242.86 | 6242.86 |  | 6242.86 | 0 | 6242.86 | 2622.86 | 3620 | 86995.49 |  | 86995.49 | 93238.35 |  | 93238.35 | 0 | 86995.49 | 24636.12 | 62359.37 | 57557.99 |  | 57557.99 | 150796.34 |  | 150796.34 | 0 | 57557.99 | 45762.94 | 11795.05 | 150796.34 |  | 150796.34 | 150796.34 |  | 150796.34 | 0 | 150796.34 | 73021.92 | 77774.42
UH-R0005910 | CLCPA Phase II - Lines - Line 906 | Aitor Aguirregabiria | Nov: 3862.84; Nov: 3862.84; Nov: 3862.84; Nov: 3862.84; Nov: 0; Nov: 3862.84; Nov: 2984.28; Nov: 878.56; Dec: 3637.59; Dec: 3637.59; Dec: 7500.43; Dec: 7500.43; Dec: 0; Dec: 3637.59; Dec: 3547.59; Dec: 90; Total: 7500.43; Total: 7500.43; Total: 7500.43; Total: 7500.43; Total: 0; Total: 7500.43; Total: 6531.87; Total: 968.56
2447608.24
Applied filters: program_group is CLCPA Phase II Year is 2023

## 2024 5+7 PPR (hidden)
Month |  |  | Jan | Jan | Jan | Jan | Jan | Jan | Jan | Jan | Jan | Jan | Feb | Feb | Feb | Feb | Feb | Feb | Feb | Feb | Feb | Feb | Mar | Mar | Mar | Mar | Mar | Mar | Mar | Mar | Mar | Mar | Apr | Apr | Apr | Apr | Apr | Apr | Apr | Apr | Apr | Apr | May | May | May | May | May | May | May | May | May | May | Jun | Jun | Jun | Jun | Jun | Jun | Jun | Jun | Jun | Jun | Jul | Jul | Jul | Jul | Jul | Jul | Jul | Jul | Jul | Jul | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Oct | Oct | Oct | Oct | Oct | Oct | Oct | Oct | Oct | Oct | Nov | Nov | Nov | Nov | Nov | Nov | Nov | Nov | Nov | Nov | Dec | Dec | Dec | Dec | Dec | Dec | Dec | Dec | Dec | Dec | Total | Total | Total | Total | Total | Total | Total | Total | Total | Total
Project Def | Project Name | Project PM | EOY | Plan | Variance($) | EOY Cum | Plan Cum | Variance Cum($) | EOY Contribution | EOY Production | EOY Int | EOY Ext | EOY | Plan | Variance($) | EOY Cum | Plan Cum | Variance Cum($) | EOY Contribution | EOY Production | EOY Int | EOY Ext | EOY | Plan | Variance($) | EOY Cum | Plan Cum | Variance Cum($) | EOY Contribution | EOY Production | EOY Int | EOY Ext | EOY | Plan | Variance($) | EOY Cum | Plan Cum | Variance Cum($) | EOY Contribution | EOY Production | EOY Int | EOY Ext | EOY | Plan | Variance($) | EOY Cum | Plan Cum | Variance Cum($) | EOY Contribution | EOY Production | EOY Int | EOY Ext | EOY | Plan | Variance($) | EOY Cum | Plan Cum | Variance Cum($) | EOY Contribution | EOY Production | EOY Int | EOY Ext | EOY | Plan | Variance($) | EOY Cum | Plan Cum | Variance Cum($) | EOY Contribution | EOY Production | EOY Int | EOY Ext | EOY | Plan | Variance($) | EOY Cum | Plan Cum | Variance Cum($) | EOY Contribution | EOY Production | EOY Int | EOY Ext | EOY | Plan | Variance($) | EOY Cum | Plan Cum | Variance Cum($) | EOY Contribution | EOY Production | EOY Int | EOY Ext | EOY | Plan | Variance($) | EOY Cum | Plan Cum | Variance Cum($) | EOY Contribution | EOY Production | EOY Int | EOY Ext | EOY | Plan | Variance($) | EOY Cum | Plan Cum | Variance Cum($) | EOY Contribution | EOY Production | EOY Int | EOY Ext | EOY | Plan | Variance($) | EOY Cum | Plan Cum | Variance Cum($) | EOY Contribution | EOY Production | EOY Int | EOY Ext | EOY | Plan | Variance($) | EOY Cum | Plan Cum | Variance Cum($) | EOY Contribution | EOY Production | EOY Int | EOY Ext
UH-N0006900 | CLCPA Phase II Lines - Line 67 | Michael Miranda | 55524.01 | 267792.8 | -212268.79 | 55524.01 | 267792.8 | -212268.79 | 0 | 55524.01 | 25146.81 | 30377.2 | 848916.86 | 267792.8 | 581124.06 | 904440.87 | 535585.6 | 368855.27 | 0 | 848916.86 | 294439.6 | 554477.26 | 23060.03 | 267792.8 | -244732.77 | 927500.9 | 803378.4 | 124122.5 | 0 | 23060.03 | 17606.67 | 5453.36 | 72831.39 | 267792.8 | -194961.41 | 1000332.29 | 1071171.2 | -70838.91 | 0 | 72831.39 | 37372.06 | 35459.33 | 32844.99 | 267792.8 | -234947.81 | 1033177.28 | 1338964 | -305786.72 | 0 | 32844.99 | 23420.7 | 9424.29 | 12038.1 | 267792.8 | -255754.7 | 1045215.38 | 1606756.8 | -561541.42 | 0 | 12038.1 | 8744.47 | 3293.63 | 85347.89 | 267792.8 | -182444.91 | 1130563.27 | 1874549.6 | -743986.33 | 0 | 85347.89 | 27103.96 | 58243.93 | 53247.06 | 267792.8 | -214545.74 | 1183810.33 | 2142342.4 | -958532.07 | 0 | 53247.06 | 19175.9 | 34071.16 | 44187.09 | 267792.8 | -223605.71 | 1227997.42 | 2410135.2 | -1182137.78 | 0 | 44187.09 | 16448.84 | 27738.25 | 2363091.9 | 267792.8 | 2095299.1 | 3591089.32 | 2677928 | 913161.32 | 0 | 2363091.9 | 692646.65 | 1670445.25 | 169455.2 | 267792.8 | -98337.6 | 3760544.52 | 2945720.8 | 814823.72 | 0 | 169455.2 | 51803.99 | 117651.21 | 37369.85 | 267792.64 | -230422.79 | 3797914.37 | 3213513.44 | 584400.93 | 0 | 37369.85 | 15051.51 | 22318.34 | 3797914.37 | 3213513.44 | 584400.93 | 3797914.37 | 3213513.44 | 584400.93 | 0 | 3797914.37 | 1228961.16 | 2568953.21 | 1033177.28 | 1338964
UH-N0006902 | CLCPA Phase II Lines - Line 68 | Jeffrey Crandlemire | 23359.12 | 630169.45 | -606810.33 | 23359.12 | 630169.45 | -606810.33 | 0 | 23359.12 | 21994.84 | 1364.28 | 934343.45 | 630169.45 | 304174 | 957702.57 | 1260338.9 | -302636.33 | 0 | 934343.45 | 490263.54 | 444079.91 | 21305.65 | 630169.45 | -608863.8 | 979008.22 | 1890508.35 | -911500.13 | 0 | 21305.65 | 14542.5 | 6763.15 | 133572.85 | 630169.45 | -496596.6 | 1112581.07 | 2520677.8 | -1408096.73 | 0 | 133572.85 | 57514.64 | 76058.21 | 319903.04 | 630169.45 | -310266.41 | 1432484.11 | 3150847.25 | -1718363.14 | 0 | 319903.04 | 116372.43 | 203530.61 | 147338.17 | 630169.45 | -482831.28 | 1579822.28 | 3781016.7 | -2201194.42 | 0 | 147338.17 | 57388.38 | 89949.79 | 138844.8 | 630169.45 | -491324.65 | 1718667.08 | 4411186.15 | -2692519.07 | 0 | 138844.8 | 55321.88 | 83522.92 | 646947.4 | 630169.45 | 16777.95 | 2365614.48 | 5041355.6 | -2675741.12 | 0 | 646947.4 | 199829.16 | 447118.24 | 5351698.05 | 630169.45 | 4721528.6 | 7717312.53 | 5671525.05 | 2045787.48 | 0 | 5351698.05 | 1574233.86 | 3777464.19 | 189805.92 | 630169.45 | -440363.53 | 7907118.45 | 6301694.5 | 1605423.95 | 0 | 189805.92 | 67721.08 | 122084.84 | 149070.67 | 630169.45 | -481098.78 | 8056189.12 | 6931863.95 | 1124325.17 | 0 | 149070.67 | 57809.9 | 91260.77 | 437294.45 | 630169.06 | -192874.61 | 8493483.57 | 7562033.01 | 931450.56 | 0 | 437294.45 | 143632.44 | 293662.01 | 8493483.57 | 7562033.01 | 931450.56 | 8493483.57 | 7562033.01 | 931450.56 | 0 | 8493483.57 | 2856624.65 | 5636858.92 | 1432484.11 | 3150847.25
UH-N0006904 | CLCPA Phase II Lines - Line 69 | Andrew Schimek | 15069.44 | 120754.63 | -105685.19 | 15069.44 | 120754.63 | -105685.19 | 0 | 15069.44 | 13705.32 | 1364.12 | 137034.35 | 120754.63 | 16279.72 | 152103.79 | 241509.26 | -89405.47 | 0 | 137034.35 | 53688.15 | 83346.2 | 13102.88 | 120754.63 | -107651.75 | 165206.67 | 362263.89 | -197057.22 | 0 | 13102.88 | 11895.55 | 1207.33 | 80263.14 | 120754.63 | -40491.49 | 245469.81 | 483018.52 | -237548.71 | 0 | 80263.14 | 39112.84 | 41150.3 | 204018.89 | 120754.63 | 83264.26 | 449488.7 | 603773.15 | -154284.45 | 0 | 204018.89 | 66104 | 137914.89 | 139720.68 | 120754.63 | 18966.05 | 589209.38 | 724527.78 | -135318.4 | 0 | 139720.68 | 50748.33 | 88972.35 | 71605.94 | 120754.63 | -49148.69 | 660815.32 | 845282.41 | -184467.09 | 0 | 71605.94 | 34175.53 | 37430.41 | 73208.98 | 120754.63 | -47545.65 | 734024.3 | 966037.04 | -232012.74 | 0 | 73208.98 | 34565.56 | 38643.42 | 72935.03 | 120754.63 | -47819.6 | 806959.33 | 1086791.67 | -279832.34 | 0 | 72935.03 | 34498.91 | 38436.12 | 65698.67 | 120754.63 | -55055.96 | 872658 | 1207546.3 | -334888.3 | 0 | 65698.67 | 32738.25 | 32960.42 | 101205.01 | 120754.63 | -19549.62 | 973863.01 | 1328300.93 | -354437.92 | 0 | 101205.01 | 41377.2 | 59827.81 | 60858.02 | 120754.56 | -59896.54 | 1034721.03 | 1449055.49 | -414334.46 | 0 | 60858.02 | 32410.74 | 28447.28 | 1034721.03 | 1449055.49 | -414334.46 | 1034721.03 | 1449055.49 | -414334.46 | 0 | 1034721.03 | 445020.38 | 589700.65 | 449488.7 | 603773.15
UH-N0006906 | CLCPA Phase II Lines - Line 72 | Andrew Schimek | 11679.4 | 779874.01 | -768194.61 | 11679.4 | 779874.01 | -768194.61 | 0 | 11679.4 | 11679.4 | 0 | 1140957.56 | 779874.01 | 361083.55 | 1152636.96 | 1559748.02 | -407111.06 | 0 | 1140957.56 | 472271.63 | 668685.93 | 48055.78 | 779874.01 | -731818.23 | 1200692.74 | 2339622.03 | -1138929.29 | 0 | 48055.78 | 24857.86 | 23197.92 | 142051.82 | 779874.01 | -637822.19 | 1342744.56 | 3119496.04 | -1776751.48 | 0 | 142051.82 | 60298.9 | 81752.92 | 371617.91 | 779874.01 | -408256.1 | 1714362.47 | 3899370.05 | -2185007.58 | 0 | 371617.91 | 133599.56 | 238018.35 | 201263.83 | 779874.01 | -578610.18 | 1915626.3 | 4679244.06 | -2763617.76 | 0 | 201263.83 | 70508.87 | 130754.96 | 130294.13 | 779874.01 | -649579.88 | 2045920.43 | 5459118.07 | -3413197.64 | 0 | 130294.13 | 53241.44 | 77052.69 | 115061.01 | 779874.01 | -664813 | 2160981.44 | 6238992.08 | -4078010.64 | 0 | 115061.01 | 49535.12 | 65525.89 | 2928974.38 | 779874.01 | 2149100.37 | 5089955.82 | 7018866.09 | -1928910.27 | 0 | 2928974.38 | 868686.89 | 2060287.49 | 109657.23 | 779874.01 | -670216.78 | 5199613.05 | 7798740.1 | -2599127.05 | 0 | 109657.23 | 48220.34 | 61436.89 | 335811.05 | 779874.01 | -444062.96 | 5535424.1 | 8578614.11 | -3043190.01 | 0 | 335811.05 | 103245.16 | 232565.89 | 3260258.66 | 779873.52 | 2480385.14 | 8795682.76 | 9358487.63 | -562804.87 | 0 | 3260258.66 | 966948.31 | 2293310.35 | 8795682.76 | 9358487.63 | -562804.87 | 8795682.76 | 9358487.63 | -562804.87 | 0 | 8795682.76 | 2863093.48 | 5932589.28 | 1714362.47 | 3899370.05
UH-N0006908 | CLCPA Phase II Lines - Line 711 | Adam Aesch | 12467.88 | 31437.22 | -18969.34 | 12467.88 | 31437.22 | -18969.34 | 0 | 12467.88 | 12467.88 | 0 | 61737.28 | 31437.22 | 30300.06 | 74205.16 | 62874.44 | 11330.72 | 0 | 61737.28 | 23512.42 | 38224.86 | 19838.12 | 31437.22 | -11599.1 | 94043.28 | 94311.66 | -268.38 | 0 | 19838.12 | 13311.8 | 6526.32 | 32785.88 | 31437.22 | 1348.66 | 126829.16 | 125748.88 | 1080.28 | 0 | 32785.88 | 20415.07 | 12370.81 | 27983.41 | 31437.22 | -3453.81 | 154812.57 | 157186.1 | -2373.53 | 0 | 27983.41 | 20064.05 | 7919.36 | 46314.42 | 31437.22 | 14877.2 | 201126.99 | 188623.32 | 12503.67 | 0 | 46314.42 | 17132.81 | 29181.61 | 35429.82 | 31437.22 | 3992.6 | 236556.81 | 220060.54 | 16496.27 | 0 | 35429.82 | 15070.93 | 20358.89 | 15476.26 | 31437.22 | -15960.96 | 252033.07 | 251497.76 | 535.31 | 0 | 15476.26 | 10383.03 | 5093.23 | 117478.01 | 31437.22 | 86040.79 | 369511.08 | 282934.98 | 86576.1 | 0 | 117478.01 | 39514.45 | 77963.56 | 61105.49 | 31437.22 | 29668.27 | 430616.57 | 314372.2 | 116244.37 | 0 | 61105.49 | 23852.07 | 37253.42 | 11830.41 | 31437.22 | -19606.81 | 442446.98 | 345809.42 | 96637.56 | 0 | 11830.41 | 8449.4 | 3381.01 | 403586.02 | 31437.2 | 372148.82 | 846033 | 377246.62 | 468786.38 | 0 | 403586.02 | 123151.82 | 280434.2 | 846033 | 377246.62 | 468786.38 | 846033 | 377246.62 | 468786.38 | 0 | 846033 | 327325.73 | 518707.27 | 154812.57 | 157186.1
UH-N0006910 | CLCPA Phase II Lines - Line 712 | Salvador Cordero | 13361.54 | 92801.37 | -79439.83 | 13361.54 | 92801.37 | -79439.83 | 0 | 13361.54 | 13361.54 | 0 | 120280.4 | 92801.37 | 27479.03 | 133641.94 | 185602.74 | -51960.8 | 0 | 120280.4 | 46900.16 | 73380.24 | 32457.56 | 92801.37 | -60343.81 | 166099.5 | 278404.11 | -112304.61 | 0 | 32457.56 | 18784.02 | 13673.54 | 30495.71 | 92801.37 | -62305.66 | 196595.21 | 371205.48 | -174610.27 | 0 | 30495.71 | 18214.7 | 12281.01 | 42247.84 | 92801.37 | -50553.53 | 238843.05 | 464006.85 | -225163.8 | 0 | 42247.84 | 16354.05 | 25893.79 | 43834.56 | 92801.37 | -48966.81 | 282677.61 | 556808.22 | -274130.61 | 0 | 43834.56 | 19038.13 | 24796.43 | 36402.42 | 92801.37 | -56398.95 | 319080.03 | 649609.59 | -330529.56 | 0 | 36402.42 | 18067.12 | 18335.3 | 24875.48 | 92801.37 | -67925.89 | 343955.51 | 742410.96 | -398455.45 | 0 | 24875.48 | 15667.06 | 9208.42 | 361442.92 | 92801.37 | 268641.55 | 705398.43 | 835212.33 | -129813.9 | 0 | 361442.92 | 113051.06 | 248391.86 | 123454.91 | 92801.37 | 30653.54 | 828853.34 | 928013.7 | -99160.36 | 0 | 123454.91 | 44899.14 | 78555.77 | 11726.87 | 92801.37 | -81074.5 | 840580.21 | 1020815.07 | -180234.86 | 0 | 11726.87 | 10807.46 | 919.41 | 1257655.78 | 92801.33 | 1164854.45 | 2098235.99 | 1113616.4 | 984619.59 | 0 | 1257655.78 | 374524.99 | 883130.79 | 2098235.99 | 1113616.4 | 984619.59 | 2098235.99 | 1113616.4 | 984619.59 | 0 | 2098235.99 | 709669.43 | 1388566.56 | 238843.05 | 464006.85
UH-N0006912 | CLCPA Phase II Lines - Line 722 | Noellia Fernandez | 2776.97 | 401056.74 | -398279.77 | 2776.97 | 401056.74 | -398279.77 | 0 | 2776.97 | 2776.97 | 0 | 364081.48 | 401056.74 | -36975.26 | 366858.45 | 802113.48 | -435255.03 | 0 | 364081.48 | 128213.47 | 235868.01 | 32078.42 | 401056.74 | -368978.32 | 398936.87 | 1203170.22 | -804233.35 | 0 | 32078.42 | 28515.93 | 3562.49 | 59398.21 | 401056.74 | -341658.53 | 458335.08 | 1604226.96 | -1145891.88 | 0 | 59398.21 | 24830.36 | 34567.85 | 41462.35 | 401056.74 | -359594.39 | 499797.43 | 2005283.7 | -1505486.27 | 0 | 41462.35 | 25504.21 | 15958.14 | 173694.01 | 401056.74 | -227362.73 | 673491.44 | 2406340.44 | -1732849 | 0 | 173694.01 | 42260.97 | 131433.04 | 179200.63 | 401056.74 | -221856.11 | 852692.07 | 2807397.18 | -1954705.11 | 0 | 179200.63 | 43606.76 | 135593.87 | 189672.96 | 401056.74 | -211383.78 | 1042365.03 | 3208453.92 | -2166088.89 | 0 | 189672.96 | 46148.77 | 143524.19 | 188213.84 | 401056.74 | -212842.9 | 1230578.87 | 3609510.66 | -2378931.79 | 0 | 188213.84 | 45793.75 | 142420.09 | 189596.9 | 401056.74 | -211459.84 | 1420175.77 | 4010567.4 | -2590391.63 | 0 | 189596.9 | 46130.26 | 143466.64 | 187705.25 | 401056.74 | -213351.49 | 1607881.02 | 4411624.14 | -2803743.12 | 0 | 187705.25 | 45670.01 | 142035.24 | 2518375.33 | 401056.49 | 2117318.84 | 4126256.35 | 4812680.63 | -686424.28 | 0 | 2518375.33 | 724520.39 | 1793854.94 | 4126256.35 | 4812680.63 | -686424.28 | 4126256.35 | 4812680.63 | -686424.28 | 0 | 4126256.35 | 1203971.85 | 2922284.5 | 499797.43 | 2005283.7
UH-N0006914 | CLCPA Phase II Lines - Line 723 | Jason Jones | 11612.96 | 257761.01 | -246148.05 | 11612.96 | 257761.01 | -246148.05 | 0 | 11612.96 | 8769.04 | 2843.92 | 252501.95 | 257761.01 | -5259.06 | 264114.91 | 515522.02 | -251407.11 | 0 | 252501.95 | 90627.62 | 161874.33 | 92376 | 257761.01 | -165385.01 | 356490.91 | 773283.03 | -416792.12 | 0 | 92376 | 28266.87 | 64109.13 | 49118.9 | 257761.01 | -208642.11 | 405609.81 | 1031044.04 | -625434.23 | 0 | 49118.9 | 20162.03 | 28956.87 | 136545.77 | 257761.01 | -121215.24 | 542155.58 | 1288805.05 | -746649.47 | 0 | 136545.77 | 48476.59 | 88069.18 | 60668.52 | 257761.01 | -197092.49 | 602824.1 | 1546566.06 | -943741.96 | 0 | 60668.52 | 18351.07 | 42317.45 | 860665.46 | 257761.01 | 602904.45 | 1463489.56 | 1804327.07 | -340837.51 | 0 | 860665.46 | 251347.01 | 609318.45 | 61042.07 | 257761.01 | -196718.94 | 1524531.63 | 2062088.08 | -537556.45 | 0 | 61042.07 | 18441.96 | 42600.11 | 1551063.92 | 257761.01 | 1293302.91 | 3075595.55 | 2319849.09 | 755746.46 | 0 | 1551063.92 | 452477.27 | 1098586.65 | 61326.53 | 257761.01 | -196434.48 | 3136922.08 | 2577610.1 | 559311.98 | 0 | 61326.53 | 18511.18 | 42815.35 | 60777.7 | 257761.01 | -196983.31 | 3197699.78 | 2835371.11 | 362328.67 | 0 | 60777.7 | 18377.64 | 42400.06 | 87718.08 | 257760.85 | -170042.77 | 3285417.86 | 3093131.96 | 192285.9 | 0 | 87718.08 | 24932.42 | 62785.66 | 3285417.86 | 3093131.96 | 192285.9 | 3285417.86 | 3093131.96 | 192285.9 | 0 | 3285417.86 | 998740.7 | 2286677.16 | 542155.58 | 1288805.05
UH-N0006916 | CLCPA Phase II Lines - Line 724 | Noellia Fernandez | 13221.18 | 215447.33 | -202226.15 | 13221.18 | 215447.33 | -202226.15 | 0 | 13221.18 | 13221.18 | 0 | 220184.39 | 215447.33 | 4737.06 | 233405.57 | 430894.66 | -197489.09 | 0 | 220184.39 | 81854.04 | 138330.35 | 28891.28 | 215447.33 | -186556.05 | 262296.85 | 646341.99 | -384045.14 | 0 | 28891.28 | 26334.27 | 2557.01 | 46445.99 | 215447.33 | -169001.34 | 308742.84 | 861789.32 | -553046.48 | 0 | 46445.99 | 20944.99 | 25501 | 37262.76 | 215447.33 | -178184.57 | 346005.6 | 1077236.65 | -731231.05 | 0 | 37262.76 | 25520.85 | 11741.91 | 102606.3 | 215447.33 | -112841.03 | 448611.9 | 1292683.98 | -844072.08 | 0 | 102606.3 | 24964.84 | 77641.46 | 105123.48 | 215447.33 | -110323.85 | 553735.38 | 1508131.31 | -954395.93 | 0 | 105123.48 | 25583.27 | 79540.21 | 110432.26 | 215447.33 | -105015.07 | 664167.64 | 1723578.64 | -1059411 | 0 | 110432.26 | 26868.95 | 83563.31 | 110054.55 | 215447.33 | -105392.78 | 774222.19 | 1939025.97 | -1164803.78 | 0 | 110054.55 | 26777.05 | 83277.5 | 111226.47 | 215447.33 | -104220.86 | 885448.66 | 2154473.3 | -1269024.64 | 0 | 111226.47 | 27062.19 | 84164.28 | 109858.19 | 215447.33 | -105589.14 | 995306.85 | 2369920.63 | -1374613.78 | 0 | 109858.19 | 26729.27 | 83128.92 | 1428656.24 | 215447.2 | 1213209.04 | 2423963.09 | 2585367.83 | -161404.74 | 0 | 1428656.24 | 410863.33 | 1017792.91 | 2423963.09 | 2585367.83 | -161404.74 | 2423963.09 | 2585367.83 | -161404.74 | 0 | 2423963.09 | 736724.23 | 1687238.86 | 346005.6 | 1077236.65
UH-N0006918 | CLCPA Phase II Lines - Line 932 | Cody Liberati | 1612.45 | 112309.1 | -110696.65 | 1612.45 | 112309.1 | -110696.65 | 0 | 1612.45 | 419.04 | 1193.41 | 120225.05 | 112309.1 | 7915.95 | 121837.5 | 224618.2 | -102780.7 | 0 | 120225.05 | 44893.7 | 75331.35 | 3548.06 | 112309.1 | -108761.04 | 125385.56 | 336927.3 | -211541.74 | 0 | 3548.06 | 2798.33 | 749.73 | 23814.95 | 112309.1 | -88494.15 | 149200.51 | 449236.4 | -300035.89 | 0 | 23814.95 | 9191.31 | 14623.64 | 28579.6 | 112309.1 | -83729.5 | 177780.11 | 561545.5 | -383765.39 | 0 | 28579.6 | 17938.85 | 10640.75 | 26950.6 | 112309.1 | -85358.5 | 204730.71 | 673854.6 | -469123.89 | 0 | 26950.6 | 8950.6 | 18000 | 54756.77 | 112309.1 | -57552.33 | 259487.48 | 786163.7 | -526676.22 | 0 | 54756.77 | 15716.04 | 39040.73 | 7127.5 | 112309.1 | -105181.6 | 266614.98 | 898472.8 | -631857.82 | 0 | 7127.5 | 4127.5 | 3000 | 39244.45 | 112309.1 | -73064.65 | 305859.43 | 1010781.9 | -704922.47 | 0 | 39244.45 | 11941.78 | 27302.67 | 44021.09 | 112309.1 | -68288.01 | 349880.52 | 1123091 | -773210.48 | 0 | 44021.09 | 13103.97 | 30917.12 | 37652.24 | 112309.1 | -74656.86 | 387532.76 | 1235400.1 | -847867.34 | 0 | 37652.24 | 11554.38 | 26097.86 | 58184.04 | 112309.04 | -54125 | 445716.8 | 1347709.14 | -901992.34 | 0 | 58184.04 | 16549.92 | 41634.12 | 445716.8 | 1347709.14 | -901992.34 | 445716.8 | 1347709.14 | -901992.34 | 0 | 445716.8 | 157185.42 | 288531.38 | 177780.11 | 561545.5
UH-N0006920 | CLCPA Phase II Lines - Line 934 | Noellia Fernandez | 16674.34 | 321125.91 | -304451.57 | 16674.34 | 321125.91 | -304451.57 | 0 | 16674.34 | 15246.34 | 1428 | 663572.1 | 321125.91 | 342446.19 | 680246.44 | 642251.82 | 37994.62 | 0 | 663572.1 | 267095.05 | 396477.05 | 107146.33 | 321125.91 | -213979.58 | 787392.77 | 963377.73 | -175984.96 | 0 | 107146.33 | 66792.23 | 40354.1 | 98423.58 | 321125.91 | -222702.33 | 885816.35 | 1284503.64 | -398687.29 | 0 | 98423.58 | 52426.11 | 45997.47 | 152429.3 | 321125.91 | -168696.61 | 1038245.65 | 1605629.55 | -567383.9 | 0 | 152429.3 | 67769.98 | 84659.32 | 136548.32 | 321125.91 | -184577.59 | 1174793.97 | 1926755.46 | -751961.49 | 0 | 136548.32 | 33223.17 | 103325.15 | 143248.57 | 321125.91 | -177877.34 | 1318042.54 | 2247881.37 | -929838.83 | 0 | 143248.57 | 37135.86 | 106112.71 | 153623.16 | 321125.91 | -167502.75 | 1471665.7 | 2569007.28 | -1097341.58 | 0 | 153623.16 | 39763.59 | 113859.57 | 151417.7 | 321125.91 | -169708.21 | 1623083.4 | 2890133.19 | -1267049.79 | 0 | 151417.7 | 39009.59 | 112408.11 | 151524.13 | 321125.91 | -169601.78 | 1774607.53 | 3211259.1 | -1436651.57 | 0 | 151524.13 | 39360.77 | 112163.36 | 147452.1 | 321125.91 | -173673.81 | 1922059.63 | 3532385.01 | -1610325.38 | 0 | 147452.1 | 37936.3 | 109515.8 | 2164923.6 | 321125.7 | 1843797.9 | 4086983.23 | 3853510.71 | 233472.52 | 0 | 2164923.6 | 621146.16 | 1543777.44 | 4086983.23 | 3853510.71 | 233472.52 | 4086983.23 | 3853510.71 | 233472.52 | 0 | 4086983.23 | 1316905.15 | 2770078.08 | 1038245.65 | 1605629.55
UH-N0006922 | CLCPA Phase II Lines - Line 935 | Salvador Cordero | 3015.41 | 111701.7 | -108686.29 | 3015.41 | 111701.7 | -108686.29 | 0 | 3015.41 | 2136.85 | 878.56 | 152420.32 | 111701.7 | 40718.62 | 155435.73 | 223403.4 | -67967.67 | 0 | 152420.32 | 54206.56 | 98213.76 | 19320.38 | 111701.7 | -92381.32 | 174756.11 | 335105.1 | -160348.99 | 0 | 19320.38 | 7262.34 | 12058.04 | 16137.26 | 111701.7 | -95564.44 | 190893.37 | 446806.8 | -255913.43 | 0 | 16137.26 | 6559.59 | 9577.67 | 52573.64 | 111701.7 | -59128.06 | 243467.01 | 558508.5 | -315041.49 | 0 | 52573.64 | 19132.44 | 33441.2 | 41245.68 | 111701.7 | -70456.02 | 284712.69 | 670210.2 | -385497.51 | 0 | 41245.68 | 13932.82 | 27312.86 | 45039.37 | 111701.7 | -66662.33 | 329752.06 | 781911.9 | -452159.84 | 0 | 45039.37 | 15245.6 | 29793.77 | 145910.31 | 111701.7 | 34208.61 | 475662.37 | 893613.6 | -417951.23 | 0 | 145910.31 | 45310.23 | 100600.08 | 15284.59 | 111701.7 | -96417.11 | 490946.96 | 1005315.3 | -514368.34 | 0 | 15284.59 | 7616.31 | 7668.28 | 1201652.22 | 111701.7 | 1089950.52 | 1692599.18 | 1117017 | 575582.18 | 0 | 1201652.22 | 353971.88 | 847680.34 | 23489.95 | 111701.7 | -88211.75 | 1716089.13 | 1228718.7 | 487370.43 | 0 | 23489.95 | 9417.86 | 14072.09 | 95489.86 | 111701.63 | -16211.77 | 1811578.99 | 1340420.33 | 471158.66 | 0 | 95489.86 | 31492.32 | 63997.54 | 1811578.99 | 1340420.33 | 471158.66 | 1811578.99 | 1340420.33 | 471158.66 | 0 | 1811578.99 | 566284.8 | 1245294.19 | 243467.01 | 558508.5
UH-N0006924 | CLCPA Phase II Lines - Line 953 | Jason Jones | 11302.15 | 62455.51 | -51153.36 | 11302.15 | 62455.51 | -51153.36 | 0 | 11302.15 | 11302.15 | 0 | 675986.76 | 62455.51 | 613531.25 | 687288.91 | 124911.02 | 562377.89 | 0 | 675986.76 | 338210.24 | 337776.52 | 13727.61 | 62455.51 | -48727.9 | 701016.52 | 187366.53 | 513649.99 | 0 | 13727.61 | 13014.31 | 713.3 | 20330.41 | 62455.51 | -42125.1 | 721346.93 | 249822.04 | 471524.89 | 0 | 20330.41 | 14085.81 | 6244.6 | 61213.73 | 62455.51 | -1241.78 | 782560.66 | 312277.55 | 470283.11 | 0 | 61213.73 | 30201.4 | 31012.33 | 26675.48 | 62455.51 | -35780.03 | 809236.14 | 374733.06 | 434503.08 | 0 | 26675.48 | 13670.32 | 13005.16 | 223573.1 | 62455.51 | 161117.59 | 1032809.24 | 437188.57 | 595620.67 | 0 | 223573.1 | 69868.83 | 153704.27 | 100190.22 | 62455.51 | 37734.71 | 1132999.46 | 499644.08 | 633355.38 | 0 | 100190.22 | 33911.32 | 66278.9 | 408248.95 | 62455.51 | 345793.44 | 1541248.41 | 562099.59 | 979148.82 | 0 | 408248.95 | 123717.69 | 284531.26 | 52778.11 | 62455.51 | -9677.4 | 1594026.52 | 624555.1 | 969471.42 | 0 | 52778.11 | 20021.28 | 32756.83 | 49315.02 | 62455.51 | -13140.49 | 1643341.54 | 687010.61 | 956330.93 | 0 | 49315.02 | 19178.68 | 30136.34 | 71805.55 | 62455.46 | 9350.09 | 1715147.09 | 749466.07 | 965681.02 | 0 | 71805.55 | 24650.79 | 47154.76 | 1715147.09 | 749466.07 | 965681.02 | 1715147.09 | 749466.07 | 965681.02 | 0 | 1715147.09 | 711832.82 | 1003314.27 | 782560.66 | 312277.55
UH-N0006926 | CLCPA Phase II Lines - Line 963 | Jason Jones | 105043.34 | 260258.2 | -155214.86 | 105043.34 | 260258.2 | -155214.86 | 0 | 105043.34 | 29692.18 | 75351.16 | 255896.41 | 260258.2 | -4361.79 | 360939.75 | 520516.4 | -159576.65 | 0 | 255896.41 | 89585.98 | 166310.43 | 15747.33 | 260258.2 | -244510.87 | 376687.08 | 780774.6 | -404087.52 | 0 | 15747.33 | 14576.73 | 1170.6 | 55365.93 | 260258.2 | -204892.27 | 432053.01 | 1041032.8 | -608979.79 | 0 | 55365.93 | 27063.14 | 28302.79 | 39387.26 | 260258.2 | -220870.94 | 471440.27 | 1301291 | -829850.73 | 0 | 39387.26 | 25531 | 13856.26 | 64087.59 | 260258.2 | -196170.61 | 535527.86 | 1561549.2 | -1026021.34 | 0 | 64087.59 | 29952.94 | 34134.65 | 1105499.06 | 260258.2 | 845240.86 | 1641026.92 | 1821807.4 | -180780.48 | 0 | 1105499.06 | 332053.84 | 773445.22 | 75550.28 | 260258.2 | -184707.92 | 1716577.2 | 2082065.6 | -365488.4 | 0 | 75550.28 | 32741.89 | 42808.39 | 2127836.38 | 260258.2 | 1867578.18 | 3844413.58 | 2342323.8 | 1502089.78 | 0 | 2127836.38 | 630626.61 | 1497209.77 | 75776.65 | 260258.2 | -184481.55 | 3920190.23 | 2602582 | 1317608.23 | 0 | 75776.65 | 32796.97 | 42979.68 | 72524.87 | 260258.2 | -187733.33 | 3992715.1 | 2862840.2 | 1129874.9 | 0 | 72524.87 | 32005.79 | 40519.08 | 133889.62 | 260258.03 | -126368.41 | 4126604.72 | 3123098.23 | 1003506.49 | 0 | 133889.62 | 46936.26 | 86953.36 | 4126604.72 | 3123098.23 | 1003506.49 | 4126604.72 | 3123098.23 | 1003506.49 | 0 | 4126604.72 | 1323563.33 | 2803041.39 | 471440.27 | 1301291
UH-N0006928 | CLCPA Phase II Lines - Line 965 | Jason Jones | 5098.6 | 394844.14 | -389745.54 | 5098.6 | 394844.14 | -389745.54 | 0 | 5098.6 | 4845.6 | 253 | 382873.07 | 394844.14 | -11971.07 | 387971.67 | 789688.28 | -401716.61 | 0 | 382873.07 | 131737.69 | 251135.38 | 18623.47 | 394844.14 | -376220.67 | 406595.14 | 1184532.42 | -777937.28 | 0 | 18623.47 | 10899.25 | 7724.22 | 48957.69 | 394844.14 | -345886.45 | 455552.83 | 1579376.56 | -1123823.73 | 0 | 48957.69 | 20565.93 | 28391.76 | 38785.67 | 394844.14 | -356058.47 | 494338.5 | 1974220.7 | -1479882.2 | 0 | 38785.67 | 21421.1 | 17364.57 | 110771.1 | 394844.14 | -284073.04 | 605109.6 | 2369064.84 | -1763955.24 | 0 | 110771.1 | 30541.38 | 80229.72 | 1238640.23 | 394844.14 | 843796.09 | 1843749.83 | 2763908.98 | -920159.15 | 0 | 1238640.23 | 359556.1 | 879084.13 | 100762.92 | 394844.14 | -294081.22 | 1944512.75 | 3158753.12 | -1214240.37 | 0 | 100762.92 | 28106.32 | 72656.6 | 2194794.58 | 394844.14 | 1799950.44 | 4139307.33 | 3553597.26 | 585710.07 | 0 | 2194794.58 | 638072.19 | 1556722.39 | 100762.93 | 394844.14 | -294081.21 | 4240070.26 | 3948441.4 | 291628.86 | 0 | 100762.93 | 28106.32 | 72656.61 | 100762.95 | 394844.14 | -294081.19 | 4340833.21 | 4343285.54 | -2452.33 | 0 | 100762.95 | 28106.33 | 72656.62 | 127067.13 | 394843.9 | -267776.77 | 4467900.34 | 4738129.44 | -270229.1 | 0 | 127067.13 | 34506.32 | 92560.81 | 4467900.34 | 4738129.44 | -270229.1 | 4467900.34 | 4738129.44 | -270229.1 | 0 | 4467900.34 | 1336464.53 | 3131435.81 | 494338.5 | 1974220.7
UH-N0006930 | CLCPA Phase II Lines - Line 968 | Noellia Fernandez | 12216.76 | 52229.2 | -40012.44 | 12216.76 | 52229.2 | -40012.44 | 0 | 12216.76 | 9212.08 | 3004.68 | 77625.29 | 52229.2 | 25396.09 | 89842.05 | 104458.4 | -14616.35 | 0 | 77625.29 | 30704.62 | 46920.67 | 25786.27 | 52229.2 | -26442.93 | 115628.32 | 156687.6 | -41059.28 | 0 | 25786.27 | 23367.44 | 2418.83 | 20315.86 | 52229.2 | -31913.34 | 135944.18 | 208916.8 | -72972.62 | 0 | 20315.86 | 11095.82 | 9220.04 | 28188.13 | 52229.2 | -24041.07 | 164132.31 | 261146 | -97013.69 | 0 | 28188.13 | 20616.72 | 7571.41 | 35522.77 | 52229.2 | -16706.43 | 199655.08 | 313375.2 | -113720.12 | 0 | 35522.77 | 8642.94 | 26879.83 | 42860.33 | 52229.2 | -9368.87 | 242515.41 | 365604.4 | -123088.99 | 0 | 42860.33 | 10434.2 | 32426.13 | 44863.17 | 52229.2 | -7366.03 | 287378.58 | 417833.6 | -130455.02 | 0 | 44863.17 | 10915.53 | 33947.64 | 44361.74 | 52229.2 | -7867.46 | 331740.32 | 470062.8 | -138322.48 | 0 | 44361.74 | 10793.53 | 33568.21 | 44673.36 | 52229.2 | -7555.84 | 376413.68 | 522292 | -145878.32 | 0 | 44673.36 | 10869.35 | 33804.01 | 44251.86 | 52229.2 | -7977.34 | 420665.54 | 574521.2 | -153855.66 | 0 | 44251.86 | 10766.79 | 33485.07 | 569407.33 | 52229.16 | 517178.17 | 990072.87 | 626750.36 | 363322.51 | 0 | 569407.33 | 163722.46 | 405684.87 | 990072.87 | 626750.36 | 363322.51 | 990072.87 | 626750.36 | 363322.51 | 0 | 990072.87 | 321141.48 | 668931.39 | 164132.31 | 261146
UH-N0006932 | CLCPA Phase II Lines - Line 978 | Jason Jones | 31085.53 | 252665.4 | -221579.87 | 31085.53 | 252665.4 | -221579.87 | 0 | 31085.53 | 20488.35 | 10597.18 | 262266.05 | 252665.4 | 9600.65 | 293351.58 | 505330.8 | -211979.22 | 0 | 262266.05 | 99284.01 | 162982.04 | 40118.11 | 252665.4 | -212547.29 | 333469.69 | 757996.2 | -424526.51 | 0 | 40118.11 | 29009.3 | 11108.81 | 81604.48 | 252665.4 | -171060.92 | 415074.17 | 1010661.6 | -595587.43 | 0 | 81604.48 | 40923.06 | 40681.42 | 67682.29 | 252665.4 | -184983.11 | 482756.46 | 1263327 | -780570.54 | 0 | 67682.29 | 45412.32 | 22269.97 | 125926.99 | 252665.4 | -126738.41 | 608683.45 | 1515992.4 | -907308.95 | 0 | 125926.99 | 48588.89 | 77338.1 | 80173.2 | 252665.4 | -172492.2 | 688856.65 | 1768657.8 | -1079801.15 | 0 | 80173.2 | 37456.67 | 42716.53 | 72045.73 | 252665.4 | -180619.67 | 760902.38 | 2021323.2 | -1260420.82 | 0 | 72045.73 | 35479.2 | 36566.53 | 71497.29 | 252665.4 | -181168.11 | 832399.67 | 2273988.6 | -1441588.93 | 0 | 71497.29 | 35345.76 | 36151.53 | 72643.01 | 252665.4 | -180022.39 | 905042.68 | 2526654 | -1621611.32 | 0 | 72643.01 | 35624.52 | 37018.49 | 71513.49 | 252665.4 | -181151.91 | 976556.17 | 2779319.4 | -1802763.23 | 0 | 71513.49 | 35349.71 | 36163.78 | 141883.6 | 252665.23 | -110781.63 | 1118439.77 | 3031984.63 | -1913544.86 | 0 | 141883.6 | 52471.25 | 89412.35 | 1118439.77 | 3031984.63 | -1913544.86 | 1118439.77 | 3031984.63 | -1913544.86 | 0 | 1118439.77 | 515433.04 | 603006.73 | 482756.46 | 1263327
UH-N0006934 | CLCPA Phase II Lines - Line 539 | Jason Jones | 10906.98 | 27939.16 | -17032.18 | 10906.98 | 27939.16 | -17032.18 | 0 | 10906.98 | 10234.98 | 672 | 49354.6 | 27939.16 | 21415.44 | 60261.58 | 55878.32 | 4383.26 | 0 | 49354.6 | 21460 | 27894.6 | 9067.08 | 27939.16 | -18872.08 | 69328.66 | 83817.48 | -14488.82 | 0 | 9067.08 | 8834.25 | 232.83 | 26668.29 | 27939.16 | -1270.87 | 95996.95 | 111756.64 | -15759.69 | 0 | 26668.29 | 21995.05 | 4673.24 | 90228.59 | 27939.16 | 62289.43 | 186225.54 | 139695.8 | 46529.74 | 0 | 90228.59 | 29652.45 | 60576.14 | 54252.22 | 27939.16 | 26313.06 | 240477.76 | 167634.96 | 72842.8 | 0 | 54252.22 | 21576.6 | 32675.62 | 186366.82 | 27939.16 | 158427.66 | 426844.58 | 195574.12 | 231270.46 | 0 | 186366.82 | 61410.11 | 124956.71 | 19065.37 | 27939.16 | -8873.79 | 445909.95 | 223513.28 | 222396.67 | 0 | 19065.37 | 13015.39 | 6049.98 | 155391.63 | 27939.16 | 127452.47 | 601301.58 | 251452.44 | 349849.14 | 0 | 155391.63 | 52751.04 | 102640.59 | 19330.81 | 27939.16 | -8608.35 | 620632.39 | 279391.6 | 341240.79 | 0 | 19330.81 | 13079.97 | 6250.84 | 16126.25 | 27939.16 | -11812.91 | 636758.64 | 307330.76 | 329427.88 | 0 | 16126.25 | 12300.28 | 3825.97 | 416246.81 | 27939.14 | 388307.67 | 1053005.45 | 335269.9 | 717735.55 | 0 | 416246.81 | 114298.28 | 301948.53 | 1053005.45 | 335269.9 | 717735.55 | 1053005.45 | 335269.9 | 717735.55 | 0 | 1053005.45 | 380608.4 | 672397.05 | 186225.54 | 139695.8
UH-N0006936 | CLCPA Phase II Lines - Line 542 | Jason Jones | 23304.28 | 76825.96 | -53521.68 | 23304.28 | 76825.96 | -53521.68 | 0 | 23304.28 | 17988.96 | 5315.32 | 103996.81 | 76825.96 | 27170.85 | 127301.09 | 153651.92 | -26350.83 | 0 | 103996.81 | 45574.75 | 58422.06 | 22219.98 | 76825.96 | -54605.98 | 149521.07 | 230477.88 | -80956.81 | 0 | 22219.98 | 17422.35 | 4797.63 | 50334.28 | 76825.96 | -26491.68 | 199855.35 | 307303.84 | -107448.49 | 0 | 50334.28 | 32438.4 | 17895.88 | 109058.45 | 76825.96 | 32232.49 | 308913.8 | 384129.8 | -75216 | 0 | 109058.45 | 46934.99 | 62123.46 | 79402.39 | 76825.96 | 2576.43 | 388316.19 | 460955.76 | -72639.57 | 0 | 79402.39 | 30089.14 | 49313.25 | 46433.56 | 76825.96 | -30392.4 | 434749.75 | 537781.72 | -103031.97 | 0 | 46433.56 | 22067.59 | 24365.97 | 557805.49 | 76825.96 | 480979.53 | 992555.24 | 614607.68 | 377947.56 | 0 | 557805.49 | 171022.35 | 386783.14 | 46225.24 | 76825.96 | -30600.72 | 1038780.48 | 691433.64 | 347346.84 | 0 | 46225.24 | 22016.91 | 24208.33 | 482277.44 | 76825.96 | 405451.48 | 1521057.92 | 768259.6 | 752798.32 | 0 | 482277.44 | 149016.13 | 333261.31 | 247839.93 | 76825.96 | 171013.97 | 1768897.85 | 845085.56 | 923812.29 | 0 | 247839.93 | 71071.18 | 176768.75 | 361770.94 | 76825.91 | 284945.03 | 2130668.79 | 921911.47 | 1208757.32 | 0 | 361770.94 | 114050.5 | 247720.44 | 2130668.79 | 921911.47 | 1208757.32 | 2130668.79 | 921911.47 | 1208757.32 | 0 | 2130668.79 | 739693.25 | 1390975.54 | 308913.8 | 384129.8
UH-N0006938 | CLCPA Phase II Lines - Line 546 | Jason Jones | 23527.85 | 146921.59 | -123393.74 | 23527.85 | 146921.59 | -123393.74 | 0 | 23527.85 | 18126.05 | 5401.8 | 155610.25 | 146921.59 | 8688.66 | 179138.1 | 293843.18 | -114705.08 | 0 | 155610.25 | 62562.13 | 93048.12 | 19062.8 | 146921.59 | -127858.79 | 198200.9 | 440764.77 | -242563.87 | 0 | 19062.8 | 14265.17 | 4797.63 | 57726.91 | 146921.59 | -89194.68 | 255927.81 | 587686.36 | -331758.55 | 0 | 57726.91 | 33585.86 | 24141.05 | 132730.58 | 146921.59 | -14191.01 | 388658.39 | 734607.95 | -345949.56 | 0 | 132730.58 | 47589.69 | 85140.89 | 300001.26 | 146921.59 | 153079.67 | 688659.65 | 881529.54 | -192869.89 | 0 | 300001.26 | 84959.06 | 215042.2 | 1004993.55 | 146921.59 | 858071.96 | 1693653.2 | 1028451.13 | 665202.07 | 0 | 1004993.55 | 298413.56 | 706579.99 | 35310.02 | 146921.59 | -111611.57 | 1728963.22 | 1175372.72 | 553590.5 | 0 | 35310.02 | 20557.82 | 14752.2 | 779257.85 | 146921.59 | 632336.26 | 2508221.07 | 1322294.31 | 1185926.76 | 0 | 779257.85 | 237278.8 | 541979.05 | 31608.12 | 146921.59 | -115313.47 | 2539829.19 | 1469215.9 | 1070613.29 | 0 | 31608.12 | 19657.12 | 11951 | 29306.33 | 146921.59 | -117615.26 | 2569135.52 | 1616137.49 | 952998.03 | 0 | 29306.33 | 19097.08 | 10209.25 | 582091.52 | 146921.5 | 435170.02 | 3151227.04 | 1763058.99 | 1388168.05 | 0 | 582091.52 | 179145.77 | 402945.75 | 3151227.04 | 1763058.99 | 1388168.05 | 3151227.04 | 1763058.99 | 1388168.05 | 0 | 3151227.04 | 1035238.11 | 2115988.93 | 388658.39 | 734607.95
UH-N0006940 | CLCPA Phase II Lines - Line 565 | Jason Jones | 23849.53 | 107158.45 | -83308.92 | 23849.53 | 107158.45 | -83308.92 | 0 | 23849.53 | 17673.49 | 6176.04 | 114133.82 | 107158.45 | 6975.37 | 137983.35 | 214316.9 | -76333.55 | 0 | 114133.82 | 44487.35 | 69646.47 | 18807.37 | 107158.45 | -88351.08 | 156790.72 | 321475.35 | -164684.63 | 0 | 18807.37 | 13398.86 | 5408.51 | 43998.46 | 107158.45 | -63159.99 | 200789.18 | 428633.8 | -227844.62 | 0 | 43998.46 | 24936.56 | 19061.9 | 88595.35 | 107158.45 | -18563.1 | 289384.53 | 535792.25 | -246407.72 | 0 | 88595.35 | 29123.26 | 59472.09 | 111665.42 | 107158.45 | 4506.97 | 401049.95 | 642950.7 | -241900.75 | 0 | 111665.42 | 33152.31 | 78513.11 | 40357.4 | 107158.45 | -66801.05 | 441407.35 | 750109.15 | -308701.8 | 0 | 40357.4 | 15802.56 | 24554.84 | 681034.53 | 107158.45 | 573876.08 | 1122441.88 | 857267.6 | 265174.28 | 0 | 681034.53 | 202424 | 478610.53 | 40160.4 | 107158.45 | -66998.05 | 1162602.28 | 964426.05 | 198176.23 | 0 | 40160.4 | 15754.63 | 24405.77 | 585206.48 | 107158.45 | 478048.03 | 1747808.76 | 1071584.5 | 676224.26 | 0 | 585206.48 | 174505.73 | 410700.75 | 71546.52 | 107158.45 | -35611.93 | 1819355.28 | 1178742.95 | 640612.33 | 0 | 71546.52 | 23391.1 | 48155.42 | 486013.54 | 107158.37 | 378855.17 | 2305368.82 | 1285901.32 | 1019467.5 | 0 | 486013.54 | 143638.11 | 342375.43 | 2305368.82 | 1285901.32 | 1019467.5 | 2305368.82 | 1285901.32 | 1019467.5 | 0 | 2305368.82 | 738287.96 | 1567080.86 | 289384.53 | 535792.25
UH-N0006942 | CLCPA Phase II Lines - Willis – Malone | Andrew Schimek | 85310.37 | 147106.87 | -61796.5 | 85310.37 | 147106.87 | -61796.5 | 0 | 85310.37 | 31661.58 | 53648.79 | 220679.75 | 147106.87 | 73572.88 | 305990.12 | 294213.74 | 11776.38 | 0 | 220679.75 | 80789.75 | 139890 | 52520.39 | 147106.87 | -94586.48 | 358510.51 | 441320.61 | -82810.1 | 0 | 52520.39 | 25316.39 | 27204 | 84014.3 | 147106.87 | -63092.57 | 442524.81 | 588427.48 | -145902.67 | 0 | 84014.3 | 38917.37 | 45096.93 | 90457.2 | 147106.87 | -56649.67 | 532982.01 | 735534.35 | -202552.34 | 0 | 90457.2 | 38489.73 | 51967.47 | 94784.7 | 147106.87 | -52322.17 | 627766.71 | 882641.22 | -254874.51 | 0 | 94784.7 | 37421.76 | 57362.94 | 115283.02 | 147106.87 | -31823.85 | 743049.73 | 1029748.09 | -286698.36 | 0 | 115283.02 | 42409.14 | 72873.88 | 312207.42 | 147106.87 | 165100.55 | 1055257.15 | 1176854.96 | -121597.81 | 0 | 312207.42 | 100347.93 | 211859.49 | 565635.57 | 147106.87 | 418528.7 | 1620892.72 | 1323961.83 | 296930.89 | 0 | 565635.57 | 176044.75 | 389590.82 | 804342.73 | 147106.87 | 657235.86 | 2425235.45 | 1471068.7 | 954166.75 | 0 | 804342.73 | 244149.57 | 560193.16 | 145958.11 | 147106.87 | -1148.76 | 2571193.56 | 1618175.57 | 953017.99 | 0 | 145958.11 | 49872.61 | 96085.5 | 292748.55 | 147106.77 | 145641.78 | 2863942.11 | 1765282.34 | 1098659.77 | 0 | 292748.55 | 92847.03 | 199901.52 | 2863942.11 | 1765282.34 | 1098659.77 | 2863942.11 | 1765282.34 | 1098659.77 | 0 | 2863942.11 | 958267.61 | 1905674.5 | 532982.01 | 735534.35
UH-N0006944 | CLCPA Phase II - SS - Bath | Zoran Oluic | 36084.28 | 713750.17 | -677665.89 | 36084.28 | 713750.17 | -677665.89 | 0 | 36084.28 | 36084.28 | 0 | 500116.98 | 713750.17 | -213633.19 | 536201.26 | 1427500.34 | -891299.08 | 0 | 500116.98 | 180122.85 | 319994.13 | 57161.65 | 713750.17 | -656588.52 | 593362.91 | 2141250.51 | -1547887.6 | 0 | 57161.65 | 46181.03 | 10980.62 | 87393.99 | 713750.17 | -626356.18 | 680756.9 | 2855000.68 | -2174243.78 | 0 | 87393.99 | 46626.38 | 40767.61 | 58981.73 | 713750.17 | -654768.44 | 739738.63 | 3568750.85 | -2829012.22 | 0 | 58981.73 | 52631.07 | 6350.66 | 29026.01 | 713750.17 | -684724.16 | 768764.64 | 4282501.02 | -3513736.38 | 0 | 29026.01 | 7062.23 | 21963.78 | 39481.71 | 713750.17 | -674268.46 | 808246.35 | 4996251.19 | -4188004.84 | 0 | 39481.71 | 14469.04 | 25012.67 | 32499.56 | 713750.17 | -681250.61 | 840745.91 | 5710001.36 | -4869255.45 | 0 | 32499.56 | 13231.01 | 19268.55 | 5664323.5 | 713750.17 | 4950573.33 | 6505069.41 | 6423751.53 | 81317.88 | 0 | 5664323.5 | 1653614.13 | 4010709.37 | 308318.56 | 713750.17 | -405431.61 | 6813387.97 | 7137501.7 | -324113.73 | 0 | 308318.56 | 94151.72 | 214166.84 | 22229.33 | 713750.17 | -691520.84 | 6835617.3 | 7851251.87 | -1015634.57 | 0 | 22229.33 | 10005.78 | 12223.55 | 8142428.26 | 713749.72 | 7428678.54 | 14978045.56 | 8565001.59 | 6413043.97 | 0 | 8142428.26 | 2375709.43 | 5766718.83 | 14978045.56 | 8565001.59 | 6413043.97 | 14978045.56 | 8565001.59 | 6413043.97 | 0 | 14978045.56 | 4529888.95 | 10448156.61 | 739738.63 | 3568750.85
UH-N0006946 | CLCPA Phase II - SS - Bennett | Cody Liberati | 21312.93 | 83187.51 | -61874.58 | 21312.93 | 83187.51 | -61874.58 | 0 | 21312.93 | 21312.93 | 0 | 137973.72 | 83187.51 | 54786.21 | 159286.65 | 166375.02 | -7088.37 | 0 | 137973.72 | 60684.8 | 77288.92 | 32868.78 | 83187.51 | -50318.73 | 192155.43 | 249562.53 | -57407.1 | 0 | 32868.78 | 17389.87 | 15478.91 | 83430.74 | 83187.51 | 243.23 | 275586.17 | 332750.04 | -57163.87 | 0 | 83430.74 | 39693.02 | 43737.72 | 31805.26 | 83187.51 | -51382.25 | 307391.43 | 415937.55 | -108546.12 | 0 | 31805.26 | 27746.59 | 4058.67 | 30257.73 | 83187.51 | -52929.78 | 337649.16 | 499125.06 | -161475.9 | 0 | 30257.73 | 15738.57 | 14519.16 | 302299.06 | 83187.51 | 219111.55 | 639948.22 | 582312.57 | 57635.65 | 0 | 302299.06 | 95619.57 | 206679.49 | 27912.1 | 83187.51 | -55275.41 | 667860.32 | 665500.08 | 2360.24 | 0 | 27912.1 | 15167.87 | 12744.23 | 193661.24 | 83187.51 | 110473.73 | 861521.56 | 748687.59 | 112833.97 | 0 | 193661.24 | 55495.8 | 138165.44 | 289692.29 | 83187.51 | 206504.78 | 1151213.85 | 831875.1 | 319338.75 | 0 | 289692.29 | 89016.03 | 200676.26 | 67358.65 | 83187.51 | -15828.86 | 1218572.5 | 915062.61 | 303509.89 | 0 | 67358.65 | 24765.48 | 42593.17 | 136877.05 | 83187.46 | 53689.59 | 1355449.55 | 998250.07 | 357199.48 | 0 | 136877.05 | 41679.8 | 95197.25 | 1355449.55 | 998250.07 | 357199.48 | 1355449.55 | 998250.07 | 357199.48 | 0 | 1355449.55 | 504310.33 | 851139.22 | 307391.43 | 415937.55
UH-N0006948 | CLCPA Phase II - SS - Eelpot | Noellia Fernandez | 40349.68 | 441155.45 | -400805.77 | 40349.68 | 441155.45 | -400805.77 | 0 | 40349.68 | 40349.68 | 0 | 271146.25 | 441155.45 | -170009.2 | 311495.93 | 882310.9 | -570814.97 | 0 | 271146.25 | 108720.92 | 162425.33 | 57503.65 | 441155.45 | -383651.8 | 368999.58 | 1323466.35 | -954466.77 | 0 | 57503.65 | 55145.38 | 2358.27 | 73144.74 | 441155.45 | -368010.71 | 442144.32 | 1764621.8 | -1322477.48 | 0 | 73144.74 | 47264.07 | 25880.67 | 60625.23 | 441155.45 | -380530.22 | 502769.55 | 2205777.25 | -1703007.7 | 0 | 60625.23 | 43115.59 | 17509.64 | 46917.48 | 441155.45 | -394237.97 | 549687.03 | 2646932.7 | -2097245.67 | 0 | 46917.48 | 12004.97 | 34912.51 | 131359.58 | 441155.45 | -309795.87 | 681046.61 | 3088088.15 | -2407041.54 | 0 | 131359.58 | 36684.67 | 94674.91 | 178093.38 | 441155.45 | -263062.07 | 859139.99 | 3529243.6 | -2670103.61 | 0 | 178093.38 | 52775.58 | 125317.8 | 116542.96 | 441155.45 | -324612.49 | 975682.95 | 3970399.05 | -2994716.1 | 0 | 116542.96 | 34371.7 | 82171.26 | 97558.72 | 441155.45 | -343596.73 | 1073241.67 | 4411554.5 | -3338312.83 | 0 | 97558.72 | 29136.64 | 68422.08 | 79562.04 | 441155.45 | -361593.41 | 1152803.71 | 4852709.95 | -3699906.24 | 0 | 79562.04 | 23540.44 | 56021.6 | 10348257.02 | 441155.18 | 9907101.84 | 11501060.73 | 5293865.13 | 6207195.6 | 0 | 10348257.02 | 3014824.92 | 7333432.1 | 11501060.73 | 5293865.13 | 6207195.6 | 11501060.73 | 5293865.13 | 6207195.6 | 0 | 11501060.73 | 3497934.56 | 8003126.17 | 502769.55 | 2205777.25
UH-N0006950 | CLCPA Phase II - SS - Greenidge | Noellia Fernandez | 39485.08 | 63777.36 | -24292.28 | 39485.08 | 63777.36 | -24292.28 | 0 | 39485.08 | 39485.08 | 0 | 88988.66 | 63777.36 | 25211.3 | 128473.74 | 127554.72 | 919.02 | 0 | 88988.66 | 43682.08 | 45306.58 | 31206.01 | 63777.36 | -32571.35 | 159679.75 | 191332.08 | -31652.33 | 0 | 31206.01 | 28408.46 | 2797.55 | 73536.3 | 63777.36 | 9758.94 | 233216.05 | 255109.44 | -21893.39 | 0 | 73536.3 | 34945.07 | 38591.23 | 35748.49 | 63777.36 | -28028.87 | 268964.54 | 318886.8 | -49922.26 | 0 | 35748.49 | 29760.36 | 5988.13 | 37645.98 | 63777.36 | -26131.38 | 306610.52 | 382664.16 | -76053.64 | 0 | 37645.98 | 9159.53 | 28486.45 | 82947.57 | 63777.36 | 19170.21 | 389558.09 | 446441.52 | -56883.43 | 0 | 82947.57 | 22372.64 | 60574.93 | 74174.97 | 63777.36 | 10397.61 | 463733.06 | 510218.88 | -46485.82 | 0 | 74174.97 | 20233.32 | 53941.65 | 70838.11 | 63777.36 | 7060.75 | 534571.17 | 573996.24 | -39425.07 | 0 | 70838.11 | 19222.22 | 51615.89 | 76769.91 | 63777.36 | 12992.55 | 611341.08 | 637773.6 | -26432.52 | 0 | 76769.91 | 21157.85 | 55612.06 | 62374.33 | 63777.36 | -1403.03 | 673715.41 | 701550.96 | -27835.55 | 0 | 62374.33 | 16981.52 | 45392.81 | 276505.7 | 63777.32 | 212728.38 | 950221.11 | 765328.28 | 184892.83 | 0 | 276505.7 | 79288.46 | 197217.24 | 950221.11 | 765328.28 | 184892.83 | 950221.11 | 765328.28 | 184892.83 | 0 | 950221.11 | 364696.59 | 585524.52 | 268964.54 | 318886.8
UH-N0006952 | CLCPA Phase II - SS - Hickling | Adam Aesch | 48897.12 | 395220.29 | -346323.17 | 48897.12 | 395220.29 | -346323.17 | 0 | 48897.12 | 48897.12 | 0 | 465107.65 | 395220.29 | 69887.36 | 514004.77 | 790440.58 | -276435.81 | 0 | 465107.65 | 177785.19 | 287322.46 | 38301.84 | 395220.29 | -356918.45 | 552306.61 | 1185660.87 | -633354.26 | 0 | 38301.84 | 35065.01 | 3236.83 | 87527.25 | 395220.29 | -307693.04 | 639833.86 | 1580881.16 | -941047.3 | 0 | 87527.25 | 50328.04 | 37199.21 | 47266.68 | 395220.29 | -347953.61 | 687100.54 | 1976101.45 | -1289000.91 | 0 | 47266.68 | 26255.45 | 21011.23 | 76408.34 | 395220.29 | -318811.95 | 763508.88 | 2371321.74 | -1607812.86 | -0.8 | 76409.14 | 32054.33 | 44354.01 | 324769.11 | 395220.29 | -70451.18 | 1088277.99 | 2766542.03 | -1678264.04 | -0.88 | 324769.99 | 105339.98 | 219429.13 | 80806.46 | 395220.29 | -314413.83 | 1169084.45 | 3161762.32 | -1992677.87 | -0.88 | 80807.34 | 34470.79 | 46335.67 | 230027.76 | 395220.29 | -165192.53 | 1399112.21 | 3556982.61 | -2157870.4 | -0.8 | 230028.56 | 72736.1 | 157291.66 | 3903694.4 | 395220.29 | 3508474.11 | 5302806.61 | 3952202.9 | 1350603.71 | -0.96 | 3903695.36 | 1148686.03 | 2755008.37 | 90484.6 | 395220.29 | -304735.69 | 5393291.21 | 4347423.19 | 1045868.02 | -0.72 | 90485.32 | 34806.04 | 55678.56 | 4237544.51 | 395220.03 | 3842324.48 | 9630835.72 | 4742643.22 | 4888192.5 | -0.8 | 4237545.31 | 1243575.16 | 2993969.35 | 9630835.72 | 4742643.22 | 4888192.5 | 9630835.72 | 4742643.22 | 4888192.5 | -5.84 | 9630841.56 | 3009999.24 | 6620836.48 | 687100.54 | 1976101.45
UH-N0006954 | CLCPA Phase II - SS - Hillside | Jeffrey Crandlemire | 15602.58 | 33516.24 | -17913.66 | 15602.58 | 33516.24 | -17913.66 | 0 | 15602.58 | 15602.58 | 0 | 85036.24 | 33516.24 | 51520 | 100638.82 | 67032.48 | 33606.34 | 0 | 85036.24 | 41388.59 | 43647.65 | 23394.65 | 33516.24 | -10121.59 | 124033.47 | 100548.72 | 23484.75 | 0 | 23394.65 | 20586.14 | 2808.51 | 39211.66 | 33516.24 | 5695.42 | 163245.13 | 134064.96 | 29180.17 | 0 | 39211.66 | 23028.13 | 16183.53 | 27307.68 | 33516.24 | -6208.56 | 190552.81 | 167581.2 | 22971.61 | 0 | 27307.68 | 23258.64 | 4049.04 | 26487.56 | 33516.24 | -7028.68 | 217040.37 | 201097.44 | 15942.93 | 0 | 26487.56 | 16017.93 | 10469.63 | 29071.68 | 33516.24 | -4444.56 | 246112.05 | 234613.68 | 11498.37 | 0 | 29071.68 | 16646.66 | 12425.02 | 29071.68 | 33516.24 | -4444.56 | 275183.73 | 268129.92 | 7053.81 | 0 | 29071.68 | 16646.66 | 12425.02 | 29028.13 | 33516.24 | -4488.11 | 304211.86 | 301646.16 | 2565.7 | 0 | 29028.13 | 16636.07 | 12392.06 | 29182.83 | 33516.24 | -4333.41 | 333394.69 | 335162.4 | -1767.71 | 0 | 29182.83 | 16673.71 | 12509.12 | 23489.11 | 33516.24 | -10027.13 | 356883.8 | 368678.64 | -11794.84 | 0 | 23489.11 | 15288.38 | 8200.73 | 23762.51 | 33516.22 | -9753.71 | 380646.31 | 402194.86 | -21548.55 | 0 | 23762.51 | 15354.9 | 8407.61 | 380646.31 | 402194.86 | -21548.55 | 380646.31 | 402194.86 | -21548.55 | 0 | 380646.31 | 237128.39 | 143517.92 | 190552.81 | 167581.2
UH-N0006956 | CLCPA Phase II - SS - Montour Falls | Cody Liberati | 24248.26 | 762084.6 | -737836.34 | 24248.26 | 762084.6 | -737836.34 | 0 | 24248.26 | 24038.06 | 210.2 | 496659.6 | 762084.6 | -265425 | 520907.86 | 1524169.2 | -1003261.34 | 0 | 496659.6 | 177474.63 | 319184.97 | 110766.55 | 762084.6 | -651318.05 | 631674.41 | 2286253.8 | -1654579.39 | 0 | 110766.55 | 45049.83 | 65716.72 | 100188.25 | 762084.6 | -661896.35 | 731862.66 | 3048338.4 | -2316475.74 | 0 | 100188.25 | 45871.08 | 54317.17 | 70151.45 | 762084.6 | -691933.15 | 802014.11 | 3810423 | -3008408.89 | 0 | 70151.45 | 51045.4 | 19106.05 | 83536.7 | 762084.6 | -678547.9 | 885550.81 | 4572507.6 | -3686956.79 | 0 | 83536.7 | 33488.38 | 50048.32 | 3750403.51 | 762084.6 | 2988318.91 | 4635954.32 | 5334592.2 | -698637.88 | 0 | 3750403.51 | 1103795.99 | 2646607.52 | 160041.05 | 762084.6 | -602043.55 | 4795995.37 | 6096676.8 | -1300681.43 | 0 | 160041.05 | 52102.4 | 107938.65 | 570398.29 | 762084.6 | -191686.31 | 5366393.66 | 6858761.4 | -1492367.74 | 0 | 570398.29 | 151945.24 | 418453.05 | 242833.41 | 762084.6 | -519251.19 | 5609227.07 | 7620846 | -2011618.93 | 0 | 242833.41 | 72246.39 | 170587.02 | 251807.19 | 762084.6 | -510277.41 | 5861034.26 | 8382930.6 | -2521896.34 | 0 | 251807.19 | 88789.75 | 163017.44 | 3431728.04 | 762084.12 | 2669643.92 | 9292762.3 | 9145014.72 | 147747.58 | 0 | 3431728.04 | 1009226.91 | 2422501.13 | 9292762.3 | 9145014.72 | 147747.58 | 9292762.3 | 9145014.72 | 147747.58 | 0 | 9292762.3 | 2855074.06 | 6437688.24 | 802014.11 | 3810423
UH-N0006958 | CLCPA Phase II - SS - Stoney Ridge | Adam Aesch | 63691.05 | 117190.83 | -53499.78 | 63691.05 | 117190.83 | -53499.78 | 0 | 63691.05 | 44403.15 | 19287.9 | 88151.8 | 117190.83 | -29039.03 | 151842.85 | 234381.66 | -82538.81 | 0 | 88151.8 | 42191.8 | 45960 | 23935.6 | 117190.83 | -93255.23 | 175778.45 | 351572.49 | -175794.04 | 0 | 23935.6 | 21577.33 | 2358.27 | 41394.44 | 117190.83 | -75796.39 | 217172.89 | 468763.32 | -251590.43 | 0 | 41394.44 | 26415.33 | 14979.11 | 43805.02 | 117190.83 | -73385.81 | 260977.91 | 585954.15 | -324976.24 | 0 | 43805.02 | 22914.26 | 20890.76 | 22527.03 | 117190.83 | -94663.8 | 283504.94 | 703144.98 | -419640.04 | 0 | 22527.03 | 15522.91 | 7004.12 | 23164.64 | 117190.83 | -94026.19 | 306669.58 | 820335.81 | -513666.23 | 0 | 23164.64 | 17497.13 | 5667.51 | 21645.98 | 117190.83 | -95544.85 | 328315.56 | 937526.64 | -609211.08 | 0 | 21645.98 | 17127.64 | 4518.34 | 18627.71 | 117190.83 | -98563.12 | 346943.27 | 1054717.47 | -707774.2 | 0 | 18627.71 | 15315 | 3312.71 | 297043.02 | 117190.83 | 179852.19 | 643986.29 | 1171908.3 | -527922.01 | 0 | 297043.02 | 97897.02 | 199146 | 17082.9 | 117190.83 | -100107.93 | 661069.19 | 1289099.13 | -628029.94 | 0 | 17082.9 | 14400 | 2682.9 | 3730066.17 | 117190.75 | 3612875.42 | 4391135.36 | 1406289.88 | 2984845.48 | 0 | 3730066.17 | 1096984.52 | 2633081.65 | 4391135.36 | 1406289.88 | 2984845.48 | 4391135.36 | 1406289.88 | 2984845.48 | 0 | 4391135.36 | 1432246.09 | 2958889.27 | 260977.91 | 585954.15
UH-N0006960 | CLCPA Phase II - SS - Watercure | Jeffrey Crandlemire | 52108.98 | 442820.59 | -390711.61 | 52108.98 | 442820.59 | -390711.61 | 0 | 52108.98 | 52108.98 | 0 | 558053.97 | 442820.59 | 115233.38 | 610162.95 | 885641.18 | -275478.23 | 0 | 558053.97 | 203611.5 | 354442.47 | 61880.58 | 442820.59 | -380940.01 | 672043.53 | 1328461.77 | -656418.24 | 0 | 61880.58 | 40390.84 | 21489.74 | 123458.27 | 442820.59 | -319362.32 | 795501.8 | 1771282.36 | -975780.56 | 0 | 123458.27 | 56419 | 67039.27 | 56735.53 | 442820.59 | -386085.06 | 852237.33 | 2214102.95 | -1361865.62 | 0 | 56735.53 | 41144.22 | 15591.31 | 50289.8 | 442820.59 | -392530.79 | 902527.13 | 2656923.54 | -1754396.41 | 0 | 50289.8 | 32579.16 | 17710.64 | 43826.08 | 442820.59 | -398994.51 | 946353.21 | 3099744.13 | -2153390.92 | 0 | 43826.08 | 31006.49 | 12819.59 | 42777.87 | 442820.59 | -400042.72 | 989131.08 | 3542564.72 | -2553433.64 | 0 | 42777.87 | 30751.45 | 12026.42 | 38337.01 | 442820.59 | -404483.58 | 1027468.09 | 3985385.31 | -2957917.22 | 0 | 38337.01 | 29670.96 | 8666.05 | 4670523.32 | 442820.59 | 4227702.73 | 5697991.41 | 4428205.9 | 1269785.51 | 0 | 4670523.32 | 1378947.09 | 3291576.23 | 38337.98 | 442820.59 | -404482.61 | 5736329.39 | 4871026.49 | 865302.9 | 0 | 38337.98 | 29671.2 | 8666.78 | 38533.84 | 442820.31 | -404286.47 | 5774863.23 | 5313846.8 | 461016.43 | 0 | 38533.84 | 29718.85 | 8814.99 | 5774863.23 | 5313846.8 | 461016.43 | 5774863.23 | 5313846.8 | 461016.43 | 0 | 5774863.23 | 1956019.74 | 3818843.49 | 852237.33 | 2214102.95
UH-N0006962 | CLCPA Phase II - SS - Minor SS Upgrade | Zoran Oluic | 2967.62 | 26644.03 | -23676.41 | 2967.62 | 26644.03 | -23676.41 | 0 | 2967.62 | 771.22 | 2196.4 | 48343.01 | 26644.03 | 21698.98 | 51310.63 | 53288.06 | -1977.43 | 0 | 48343.01 | 16960.68 | 31382.33 | 1716.46 | 26644.03 | -24927.57 | 53027.09 | 79932.09 | -26905 | 0 | 1716.46 | 1277.18 | 439.28 | 14815.2 | 26644.03 | -11828.83 | 67842.29 | 106576.12 | -38733.83 | 0 | 14815.2 | 4167.6 | 10647.6 | 60181.44 | 26644.03 | 33537.41 | 128023.73 | 133220.15 | -5196.42 | 0 | 60181.44 | 17812.84 | 42368.6 | 28954.93 | 26644.03 | 2310.9 | 156978.66 | 159864.18 | -2885.52 | 0 | 28954.93 | 7044.94 | 21909.99 | 87981.9 | 26644.03 | 61337.87 | 244960.56 | 186508.21 | 58452.35 | 0 | 87981.9 | 21461.08 | 66520.82 | 83874.08 | 26644.03 | 57230.05 | 328834.64 | 213152.24 | 115682.4 | 0 | 83874.08 | 20412.55 | 63461.53 | 45364.94 | 26644.03 | 18720.91 | 374199.58 | 239796.27 | 134403.31 | 0 | 45364.94 | 11037.6 | 34327.34 | 51811.33 | 26644.03 | 25167.3 | 426010.91 | 266440.3 | 159570.61 | 0 | 51811.33 | 12606.06 | 39205.27 | 42991.38 | 26644.03 | 16347.35 | 469002.29 | 293084.33 | 175917.96 | 0 | 42991.38 | 10460.12 | 32531.26 | 80167.16 | 26644.02 | 53523.14 | 549169.45 | 319728.35 | 229441.1 | 0 | 80167.16 | 20742.84 | 59424.32 | 549169.45 | 319728.35 | 229441.1 | 549169.45 | 319728.35 | 229441.1 | 0 | 549169.45 | 144754.71 | 404414.74 | 128023.73 | 133220.15
UH-N0007335 | CLCPA Phase II - Hickling RR | Salvador Cordero | Jan: 106591.63; Jan: -106591.63; Jan: 106591.63; Jan: -106591.63; Feb: 106591.63; Feb: -106591.63; Feb: 213183.26; Feb: -213183.26; Mar: 106591.63; Mar: -106591.63; Mar: 319774.89; Mar: -319774.89; Apr: 106591.63; Apr: -106591.63; Apr: 426366.52; Apr: -426366.52; May: 106591.63; May: -106591.63; May: 532958.15; May: -532958.15; Jun: 106591.63; Jun: -106591.63; Jun: 639549.78; Jun: -639549.78; Jul: 106591.63; Jul: -106591.63; Jul: 746141.41; Jul: -746141.41; Aug: 106591.63; Aug: -106591.63; Aug: 852733.04; Aug: -852733.04; Sep: 106591.63; Sep: -106591.63; Sep: 959324.67; Sep: -959324.67; Oct: 106591.63; Oct: -106591.63; Oct: 1065916.3; Oct: -1065916.3; Nov: 106591.63; Nov: -106591.63; Nov: 1172507.93; Nov: -1172507.93; Dec: 106591.56; Dec: -106591.56; Dec: 1279099.49; Dec: -1279099.49; Total: 1279099.49; Total: -1279099.49; Total: 1279099.49; Total: -1279099.49 | 0 | 532958.15
UH-R0005910 | CLCPA Phase II - Lines - Line 906 | Adam Aesch | 1800.09 | 275000 | -273199.91 | 1800.09 | 275000 | -273199.91 | 0 | 1800.09 | 1800.09 | 0 | 682182.62 | 275000 | 407182.62 | 683982.71 | 550000 | 133982.71 | 0 | 682182.62 | 432015.86 | 250166.76 | 1338.57 | 275000 | -273661.43 | 685321.28 | 825000 | -139678.72 | 0 | 1338.57 | 1338.57 | 0 | 7557.78 | 275000 | -267442.22 | 692879.06 | 1100000 | -407120.94 | 0 | 7557.78 | 5822.08 | 1735.7 | 32824.2 | 275000 | -242175.8 | 725703.26 | 1375000 | -649296.74 | 0 | 32824.2 | 14805.22 | 18018.98 | 2395.02 | 275000 | -272604.98 | 728098.28 | 1650000 | -921901.72 | 0 | 2395.02 | 1543.47 | 851.55 | 69623.25 | 275000 | -205376.75 | 797721.53 | 1925000 | -1127278.47 | 0 | 69623.25 | 13780.91 | 55842.34 | 77218.06 | 275000 | -197781.94 | 874939.59 | 2200000 | -1325060.41 | 0 | 77218.06 | 15150.82 | 62067.24 | 70902.83 | 275000 | -204097.17 | 945842.42 | 2475000 | -1529157.58 | 0 | 70902.83 | 13900.56 | 57002.27 | 105058.41 | 275000 | -169941.59 | 1050900.83 | 2750000 | -1699099.17 | 0 | 105058.41 | 20228.1 | 84830.31 | 59003.55 | 275000 | -215996.45 | 1109904.38 | 3025000 | -1915095.62 | 0 | 59003.55 | 11698.66 | 47304.89 | 12736.66 | 275000 | -262263.34 | 1122641.04 | 3300000 | -2177358.96 | 0 | 12736.66 | 3464.42 | 9272.24 | 1122641.04 | 3300000 | -2177358.96 | 1122641.04 | 3300000 | -2177358.96 | 0 | 1122641.04 | 535548.76 | 587092.28 | 725703.26 | 1375000
UH-R0005912 | CLCPA Phase II - SS - Minor SS Upgrade | Zoran Oluic | [10 empty] | 75116.56 |  | 75116.56 | 75116.56 |  | 75116.56 | 0 | 75116.56 | 47456.22 | 27660.34 | 975.81 |  | 975.81 | 76092.37 |  | 76092.37 | 0 | 975.81 | 975.81 | 0 | 7859.36 |  | 7859.36 | 83951.73 |  | 83951.73 | 0 | 7859.36 | 7859.36 | 0 |  |  |  | 83951.73 |  | 83951.73 |  |  |  |  | 5104.03 |  | 5104.03 | 89055.76 |  | 89055.76 | 0 | 5104.03 | 920.64 | 4183.39 | 5110.98 |  | 5110.98 | 94166.74 |  | 94166.74 | 0 | 5110.98 | 927.59 | 4183.39 | 5104.72 |  | 5104.72 | 99271.46 |  | 99271.46 | 0 | 5104.72 | 921.33 | 4183.39 |  |  |  | 99271.46 |  | 99271.46 | [7 empty] | 99271.46 |  | 99271.46 |  |  |  |  | 2022.86 |  | 2022.86 | 101294.32 |  | 101294.32 | 0 | 2022.86 | 364.87 | 1657.99 | 2235.81 |  | 2235.81 | 103530.13 |  | 103530.13 | 0 | 2235.81 | 403.29 | 1832.52 | 103530.13 |  | 103530.13 | 103530.13 |  | 103530.13 | 0 | 103530.13 | 59829.11 | 43701.02 | 83951.73 | 0
[133 empty] | 17521437.6 | 41657872.25
Applied filters: Year is 2024 Program Group is CLCPA Phase II

## Sheet2 (hidden)
Project Name | Project Description | MW Impact | Proposed In-Service Date | Order of Magnitude Cost Estimate ($000s)[1]